## Report 1
District | Contract_Num | Ea | Cnty_Rt_Pm | Highway_Program_Code | Federal_Aid_Location | Contractor | Contractor_Addr | Contractor_City | Contractor_Phone | Resident_Engineer_Phone | Re_Addr | Re_Loc | Re_Engineer | C_Ci_Pay_Est | C_Ew_Pay_Est | C_Ac_Pay_Est | C_Mobil_Pay_Est | C_Ped_Est_Date | Type_Of_Work | Loc_Desc | Elapsed_Time_Pct | Work_Completed_Pct | Work_Comp_To_Date_Amt | Bid_Amt | Authorized_Final_Amt | Contract_Number | Est_Comp_Date | Approval_Date | Award_Date | Acceptance_Date | Construction_Suspended | Actual_No_Days_Worked | Cco_Other_Days | Orig_No_Working_Days | Change_Order_Days | Pep_Status | C_Spm
01 | 01-0P4304 | 0P4304 | 01-DN-101-2.0/16.5 | 20.XX 201130 |  | Gr Sundberg Inc | 5211 Boyd Road | Arcata Ca 95521 |  | 7073469027 | 5065 Boyd Road Suite H | Arcata Ca 95521 | Dunne Ryan | 0 | 1404112.83 | 0 | 0 | 2026-01-20 | Repair Storm Damage | Repair Storm Damage Del Norte Cnty 8 Miles South Crescent Cityrepair Retaining Walla And Subsurface Dir'S Emergency F.A. | 57 | 25 | 2126304.33 | 43725 | 8485000 | 60077 | 2026-09-01 | 2025-05-07 | 2025-04-14 |  |  | 86 | 0 | 150 | 0 |  | X
01 | 01-0J2104 | 0J2104 | 01-DN-101-2.6/23.9 |  | ACNH-Q101- (442)E | Mercer-Fraser Company | 200 Dinsmore Dr | Fortuna Ca 95540 |  | 7078155620 | 1444 Parkway Drive | Crescent City, Ca 95531 | Valley, Aaron | 0 | 0 | 0 | 0 |  | Rhma, Hma, And Cold Plane Asphalt Concrete | Del Norte County In And Near Klamath From 1.2 Miles South Of Klamath River Overflow To 1.1 Mile North Of Hamilton Road | 0 | 0 | 0 | 22896896 | 22919396 | 60035 |  | 2025-08-26 | 2025-06-06 |  | S | 0 | 0 | 240 | 0
01 | 01-0G1004 | 0G1004 | 01-DN-101-12.5/15.5 | 20.20 201130 |  | G R Sundberg, Inc. | 5211 Boyd Road | Arcata, Ca 95521 | 7078256565 | 7074984009 | 207 Price Mall | Crescent City, Ca 95531 | Sanders, Karen | 23475 | 0 | 0 | 0 | 2021-04-09 | Roadway Stabilization And Retaining Wall R | In Del Norte County Near Klamath From 0.4 Mile South Of Wilson Creek Bridge To 1.7 Miles North Of Rudisil Road Dir'S Emergency F. | 100 | 100 | 11984108.87 | 23475 | 11985000 | 33563 | 2021-04-09 | 2016-05-04 | 2016-02-16 |  |  | 160 | 0 | 60 | 0 |  | X
01 | 01-0K9504 | 0K9504 | 01-DN-101-15.6/16.2 |  | HSNH-Q101- (447)E | Granite Construction Company | 1324 S. State Street | Ukiah Ca 95482 | [5 empty] | 0 | 0 | 0 | 0 |  | Place Roadway Section, Install Guardrail, | Del Norte County About 10.0 Miles South Ofcrescent City From 3.0 Miles North To 3.6 Miles North Of Wilson Creek Bridge | 0 | 0 | 0 | 4097307.19 | 4097307.19 | 60161 |  | 2025-11-05 | 2025-09-22 |  |  | 0 | 0 | 320 | 0
01 | 01-436404 | 436404 | 01-DN-101-35.8/36.5 | HA21 | ACNH-Q101- (398)E | Mcm Construction, Inc. | Po Box 620 | North Highlands Ca 95660 | 9163341221 | 7074965581 | 207 Price Mall Suite 100 | Crescent City, Ca 95531 | Malmberg, Clayton | 1065347.65 | 194202.57 | 0 | 0 | 2026-02-20 | Replace Bridge | In Del Norte County Near Crescent City From 0.3 Mile South Of Smith River Bridge To 0.4 Mile North Of Smith River Bridge | 90 | 88 | 66774568.93 | 72443463 | 75445656.24 | 43785 | 2026-05-12 | 2022-08-02 | 2022-07-11 |  | S | 773 | 0 | 860 | 0 |  | X
01 | 01-0L4304 | 0L4304 | 01-DN-101-39.2/39.7 |  | HSNH-Q101- (458)E | Tidewater Contractors, Inc. | 16156 Hwy 101 South | Brookings Or 97415 | [5 empty] | 0 | 0 | 0 | 0 |  | Earthwork, Lighting System, And Place Road | Del Norte County Near Smith River From East Denney Street To Rowdy Creek Bridge | 0 | 0 | 0 | 2360880.5 | 2360880.5 | 60347 |  | 2026-01-21 | 2025-12-23 |  |  | 0 | 0 | 330 | 0
01 | 01-0L9904 | 0L9904 | 01-DN-199-.5/.8 |  | HSNH-P199- (041)E | S.T. Rhoades Construction, Inc. | 8780 Old Oregon Trail | Redding Ca 96002 | [5 empty] | 0 | 0 | 0 | 0 |  | Construct Roundabout And Lighting. | Del Norte County Near Crescent City From The S199-S101 Connector Overcrossing To 0.1 Mile North Of Kings Valley Road | 0 | 0 | 0 | 5173703.07 | 5173703.07 | 60447 |  | 2026-02-25 | 2026-01-30 |  |  | 0 | 0 | 410 | 0
01 | 01-0J8904 | 0J8904 | 01-HUM-36-3.9/6 |  | NHHS-S036- (122)E | Mercer-Fraser Company | 200 Dinsmore Dr | Fortuna Ca 95540 | 7074430332 | 7074960332 | 1487 Sandy Prairie Court Ste E | Fortuna Ca 95501 | Long Cody | 0 | 93335.77 | 0 | 0 | 2026-02-20 | Hot Mix Asphalt, Aggregate Base, And Struc | Humboldt County At Carlotta From 0.2 Mile West Of Fisher Road To 0.2 Mile West Of Wilder Road | 36 | 52 | 6088714.54 | 11410410 | 11575940.55 | 57129 | 2026-12-31 | 2025-01-29 | 2024-12-06 |  |  | 135 | 0 | 370 | 0 |  | X
01 | 01-0C5004 | 0C5004 | 01-HUM-36-11.3/34.6 | HA21 | ACNH-S036- (118)E | Mercer Fraser Company | 200 Dinsmore Dr | Fortuna Ca 95540 |  | 7076210000 | 1487 Sandy Praire Court Ste. E | Fortuna, Ca 95540 | Rodriguez, Joaquin | 138750 | 0 | 0 | 0 | 2026-01-20 | Replace Bridge Rails. | Humboldt County On Route 36 At Hely Creek Bridge 04-0092 At Little Larabee Creek Bridge 04-0102 And At Butte Creek Bridge 04-0116 | 69 | 66 | 10115530.14 | 14853018.91 | 15136437.3 | 48230 | 2026-07-27 | 2023-03-24 | 2023-03-02 |  | S | 289 | 0 | 420 | 0 |  | X
01 | 01-0H6104 | 0H6104 | 01-HUM-36-13.5/36.1 | HA22 | ACNH-S036- (119)E | Mercer Fraser Company | 200 Dinsmore Dr | Fortuna Ca 95540 |  | 7076210000 | 1487 Sandy Praire Court Ste E | Fortuna, Ca 95540 | Rodriguez, Joaquin | -70475.8 | 208076.68 | 0 | 0 | 2026-02-20 | Cold Plane And Overlay Hma, & Replace Guar | Humboldt County At And Near Bridgeville From 3.4 Miles West Of Grizzly Creek Bridge To 0.8 Mile East Of South Fork Van Duzen River | 89 | 99 | 37988780.07 | 36777777 | 37290777 | 54144 | 2026-03-16 | 2023-11-30 | 2023-10-31 |  | S | 124 | 0 | 140 | 0 |  | X
01 | 01-461704 | 461704 | 01-HUM-36-25.4/0 |  |  | Nico Engineering, Inc. | 1409 Colin St | San Pablo Ca 94806 | 5103138166 | 7074960332 | 1487 Sany Prairie Court Ste E | Fortuna Ca 95540 | Cody Long | 176720 | 5000 | 0 | 0 | 2025-12-20 | Water Treatment System Upgrade And Replace | Humboldt County Near Bridgeville At The Bridgeville Maintenance Station | 32 | 83 | 698016 | 835886 | 840886 | 59377 | 2026-02-20 | 2025-07-16 | 2025-05-28 |  |  | 43 | 0 | 135 | 0 |  | X
01 | 01-0P1804 | 0P1804 | 01-HUM-36-25.4/26 | 20.XX 201130 |  | Gr Sundberg, Inc. | 5211 Boyd Road | Arcata, Ca 95521 |  | 7074960332 | 1487 Sandy Prairie Court Ste. E | Fortuna Ca 95501 | Long, Cody | 0 | 460183.65 | 0 | 0 | 2026-01-20 | Repair Slipout | In Humboldt County Near Bridgeville From Caltrans Maintenance Station To 0.6 Mile East Of Caltrans Maintenance Station Dir'S Emerg | 89 | 90 | 11383317.49 | 43485 | 12675000 | 55965 | 2026-06-01 | 2024-05-21 | 2024-04-15 |  |  | 187 | 0 | 209 | 0 |  | X
01 | 01-0P8204 | 0P8204 | 01-HUM-36-155.0/16.5 | 20.XX 201130 |  | Gr Sundberg Inc | 5211 Boyd Rd | Arcata Ca 95521 |  | 7074960332 | 1487 Sandy Prarie Court Ste E | Fortuna Ca 95501 | Long Cody | 0 | 368965.5 | 0 | 0 | 2026-02-20 | Pavement Repairs | Repair Slide Hum Cnty 10 Miles E Of Carlotta Erosion Cntrl Slide Removal Invest Slope Dir'S Emergency F.A. | 0 | 48 | 13162141.56 | 15975 | 27285000 | 57070 | 2026-08-20 | 2025-02-11 | 2024-12-17 |  |  | 0 | 0 | 120 | 0 |  | X
01 | 01-0P9504 | 0P9504 | 01-HUM-36-170.0/24 | 20.XX 201130 |  | Mccullough Construction Inc. | 57 Aldergrove Road | Arcata Ca 95521 |  | 7074960332 | 1487 Sandy Prairie Court Ste. E | Fortuna Ca 95501 | Long Cody | 0 | 54664.93 | 0 | 0 | 2026-01-20 | Slide Repair | Repair Slide Hum Cnty Near Bridgeville From Grizzly Slide Removal And Slope Grading Dir'S Emergency F.A. | 12 | 45 | 890054.19 | 10350 | 1985000 | 57385 | 2026-07-28 | 2025-03-20 | 2025-02-04 |  |  | 14 | 0 | 120 | 0 |  | X
01 | 01-0P9004 | 0P9004 | 01-HUM-36-190.0/20.1 | 20.XX 201130 |  | J.F. Shea Construction | 667 Brea Canyon Road Ste 30 | Walnut Ca 91789 |  | 7076210000 | 1487 Sandy Prairie Court Ste E | Fortuna Ca 95540 | Rodriguez Joaquin | 0 | 369749.55 | 0 | 0 | 2026-02-20 | Repair Storm Damage | Repair Storm Damage In Hum Cnty Near Bridgeville Repair Roadway Embankment With Retaining Dir'S Emergency F.A. | 38 | 97 | 7228437.6 | 30000 | 7485000 | 57397 | 2026-06-08 | 2025-03-26 | 2025-03-10 |  |  | 46 | 0 | 120 | 0 |  | X
01 | 01-0Q0304 | 0Q0304 | 01-HUM-36-279.0/27.9 | 20.XX 201130 |  | Mercer Fraser Company | 200 Dinsmore Dr | Fortuna Ca 95540 |  | 7076210000 | 1487 Sandy Prairie Court Suite E | Fortuna Ca 95540 | Rodriguez Joaquin | 0 | 697101.33 | 0 | 0 | 2025-12-20 | Pavement Repair | Repair Storm Damage Hum Cnty Near Bridgeville At 2.5 Miles Repair Roadway And Replace Culvert Dir'S Emergency F.A. | 59 | 86 | 1100657.43 | 7560 | 1285000 | 57916 | 2026-03-16 | 2025-04-16 | 2025-02-21 |  |  | 89 | 0 | 150 | 0 |  | X
01 | 01-0F9204 | 0F9204 | 01-HUM-96-43.7/0 |  |  | Wylatti Resource Management, Inc | 23601 Cemetery Lane | Covelo Ca 95428 | 7079838135 | 7074982122 | 5065 Boyd Road Suite H | Arcata, Ca 95521 | Zimmerer, Jeffrey | 29234 | 0 | 0 | 0 | 2026-01-20 | Restore Disposal Site | In Humboldt County Near Orleans At 1.2 Miles West Of Siskiyou County Line | 60 | 76 | 510491.05 | 640523.23 | 664323.23 | 42244 | 2028-12-15 | 2022-03-16 | 2022-02-03 |  |  | 776 | 0 | 1290 | 0 |  | X
01 | 01-0Q2004 | 0Q2004 | 01-HUM-96-400.0/.1 | 20.XX 201130 |  | Roger Brown Construction Company Inc | Po Box 406 | Willow Creek Ca 95573 |  | 7074961086 | 5065 Boyd Rd Suite H | Arcata Ca 95521 | Banuelos Efren | 0 | 126575.95 | 0 | 0 | 2026-02-20 | Repair Drainage | Repair Sink Humboldt Cnty Near Orleans Repair Drainage Dir'S Emergency L.B. | 8 | 5 | 126575.95 | 12094 | 2485000 | 60239 | 2026-06-15 | 2025-07-24 | 2025-07-21 |  |  | 7 | 0 | 90 | 0 |  | X
01 | 01-464804 | 464804 | 01-HUM-101-1.1/2.5 |  | ACNH-Q101- (448)E | Mercer-Fraser Company | 200 Dinsmore Dr | Fortuna Ca 95540 | [5 empty] | 0 | 0 | 0 | 0 |  | Install Soldier Pile Wall, And Remove And | Humboldt County Near Garberville From 0.5 Mile South To 0.9 Mile North Of Richardsongrove Undercrossing | 0 | 0 | 0 | 5683203 | 5683203 | 60349 |  | 2026-01-21 | 2025-12-15 |  |  | 0 | 0 | 280 | 0
01 | 01-0H6404 | 0H6404 | 01-HUM-101-2.4/M53.9 |  | PTNH-Q101- (436)E | Wylatti Resource Management, Inc. | 23601 Cemetery Lane | Covelo Ca 95428 |  | 7076210000 | 1487 Sandy Prairie Court Ste E | Fortuna, Ca 95540 | Rodriguez, Joaquin | 23117.4 | 0 | 0 | 0 | 2025-11-20 | Wsp Trenchless Installation, Csp, And Eros | Humboldt County At Various Locations From 2.4 Miles North Of The Mendocino County Border To Eel River Bridge 04-0016R | 42 | 50 | 6621964.76 | 13097292.18 | 13247292.18 | 57072 | 2026-02-25 | 2025-01-29 | 2025-01-13 |  | S | 99 | 0 | 235 | 0 |  | X
01 | 01-0H6504 | 0H6504 | 01-HUM-101-55.9/136.4 |  | ACNH-Q101- (445)E | Wahlund Construction, Inc. | 690 Indianola Rd | Eureka Ca 95503 |  | 7072725831 | 5601 South Broadway Street | Eureka, Ca 95503 | Collins, Robin | 0 | 0 | 0 | 0 |  | Construct & Repair Tms Elements; Csp, Rcp, | Humboldt County Near Alton From 0.3 Mile South Of Van Duzen River Bridge 4-17 To Del Norte County Line | 0 | 0 | 0 | 16016104.15 | 16016104.15 | 59798 |  | 2025-08-12 | 2025-07-25 |  | S | 0 | 0 | 191 | 0
01 | 01-0K9404 | 0K9404 | 01-HUM-101-74.8/76.1 |  | ACNH-Q101- (434)E | G R Sundberg, Inc. | 5211 Boyd Road | Arcata Ca 95521 |  | 7072725831 | 5601 South Broadway St Suite A | Eureka, Ca 95503 | Collins, Robin | 879990.26 | 0 | 0 | 0 | 2026-02-20 | Lighting System, Fiber Optic Cable System, | Humboldt County In And Near Eureka From Herrick Avenue Overcrossing To 0.1 Mile North Of Highland Avenue | 34 | 70 | 7684309.55 | 10429084 | 10788124 | 57130 | 2027-06-24 | 2024-12-27 | 2024-12-12 |  |  | 151 | 0 | 450 | 0 |  | X
01 | 01-0N6604 | 0N6604 | 01-HUM-101-78.0/79.6 |  |  | G R Sundberg, Inc. | 5211 Boyd Road | Arcata Ca 95521 |  | 7072725831 | 6501 South Broadway St | Eureka, Ca 95503 | Collins, Robin | 0 | 57953.27 | 0 | 0 | 2026-01-20 | Rectangular Rapid Flashing Beacons Systems | Humboldt County In Eureka On Route 101 From 0.1 Mile South Of Commercial Street To Y Street And On Route 255 At 3Rd Street | 56 | 62 | 710023.36 | 1041244.25 | 1146244.25 | 59799 | 2026-02-19 | 2025-07-02 | 2025-06-19 |  |  | 25 | 0 | 45 | 0 |  | X
01 | 01-366004 | 366004 | 01-HUM-101-80.0/84 |  | ACNH-394 - (E )000 | Granite Construction Company | 1324 S. State Street | Ukiah Ca 95482 | 7074674100 | 7074961086 | 5065 Boyd Road | Arcata, Ca 95521 | Banuelos, Efren | 208016.39 | 95076.82 | 0 | 0 | 2026-02-20 | Construct Interchange, Structure Undercros | Humboldt County Near Eureka From Eureka Slough Bridge To Bayside Cutoff | 77 | 93 | 46032386.53 | 46643866.36 | 49148172.82 | 46464 | 2027-09-19 | 2023-01-26 | 2022-12-29 |  |  | 379 | 0 | 490 | 5 |  | X
01 | 01-0J3604 | 0J3604 | 01-HUM-101-103.3/103.7 |  |  | G R Sundberg, Inc. | 5211 Boyd Road | Arcata Ca 95521 |  | 7073469027 | 5065 Boyd Road Suite H | Arcata, Ca 95521 | Dunne, Ryan | 0 | 0 | 0 | 0 |  | Stream Intake, Well Sump, And Water Backwa | Humboldt County Near Trinidad From Seawooddrive Undercrossing To 0.3 Mile North Of Seawood Drive Undercrossing | 0 | 0 | 0 | 790060 | 790060 | 59156 |  | 2025-06-26 | 2025-06-11 |  |  | 0 | 0 | 100 | 0
01 | 01-0K1504 | 0K1504 | 01-HUM-101-125.2/126.1 |  | HSNH-Q101- (446)E | G R Sundberg, Inc. | 5211 Boyd Road | Arcata Ca 95521 | [5 empty] | 0 | 0 | 0 | 0 |  | Earthwork, Hma-A, Drainage, And High Frict | Humboldt County Near Orick From 0.9 Mile South To South Prairie Creek Park Undercrossing | 0 | 0 | 0 | 3107996.5 | 3107996.5 | 60177 |  | 2025-11-18 | 2025-10-24 |  | S | 0 | 0 | 335 | 0
01 | 01-0P8704 | 0P8704 | 01-HUM-101-330.0/18 | 20.XX 201130 |  | Ford Logging Inc. Dba Pacific Earthscape | 1225 Central Ave. #11 | Mckinleyville Ca 95519 |  | 7074960332 | 1487 Sandy Prairie Court Ste. E | Fortuna Ca 95501 | Long Cody | 0 | 5173.41 | 0 | 0 | 2026-01-20 | Repair Landslide | Repair Landslide Hum Cnty At Various Locations Construct Retaining Wall Repair Damage Dir'S Emergency F.A. | 0 | 8 | 535149.88 | 37475 | 6985000 | 59196 | 2026-10-20 | 2025-06-25 | 2025-03-13 |  |  | 0 | 0 | 120 | 0 |  | X
01 | 01-0K4204 | 0K4204 | 01-HUM-101-595.0/0 | 20.80 524000 |  | Mountainside Construction | 13884 Shangrila Drive | Redding, Ca 96003 |  | 7077251020 | 1487 Sandy Prairie Court Ste. E | Fortuna, Ca 95501 | Rodriguez, Joaquin | 0 | 1546.98 | 0 | 0 | 2021-02-02 | Repair To Prevent Further Power Outages | In Fortuna Maintenance Station And Some Electrical System Rehabilitation At The Leggett Maintenance Station. Dir'S Emergency L.B. | 100 | 100 | 253357.98 | 4900 | 245000 | 40971 | 2021-02-02 | 2020-05-03 | 2020-02-21 |  |  | 120 | 0 | 120 | 0 |  | X
01 | 01-0P0604 | 0P0604 | 01-HUM-101-834.0/83.4 | 20.10 201352 |  | Wylatti Resource Management, Inc. | Po Box 575 | Covelo, Ca 95428 |  | 7072725831 | 5601 South Broadway St. | Eureka, Ca 95503 | Collins, Robin | 0 | 70397.27 | 0 | 0 | 2025-08-20 | Maintenance Station Security Improvements | In Del Norte, Humboldt, Lake And Mendocino Counties At Various Locations Dir'S Emergency L.B. | 36 | 91 | 2531157.57 | 17475 | 2785000 | 56554 | 2025-09-30 | 2024-08-22 | 2024-06-03 |  |  | 107 | 0 | 300 | 0 |  | X
01 | 01-0H4104 | 0H4104 | 01-HUM-169-15.0/33.8 |  |  | R. Brown Construction Company,Inc. | 18 China Creek Rd. | Willow Creek Ca 95573 |  | 7074961086 | 5065 Boyd Road Suite G | Arcata, Ca 95521 | Baneulos, Efren | 2000 | 0 | 0 | 0 | 2026-02-20 | Csp, Structural Concrete, And Rsp. | Humboldt County Near Weitchpec At Various Locations From 0.6 Mile East Of Pecwan Creek Bridge To Route 96 | 36 | 81 | 2745168.7 | 3281191.6 | 3330191.6 | 58398 | 2026-05-28 | 2024-10-31 | 2024-10-09 |  |  | 72 | 0 | 200 | 0 |  | X
01 | 01-0P8904 | 0P8904 | 01-HUM-169-250.0/26 | 20.XX 201130 |  | R. Brown Construction Company | Po Box 406 | Willow Creek Ca 95573 |  | 7074961086 | 5065 Boyd Rd Suite H | Arccata Ca 95521 | Banuelos Efren | 0 | 29183.07 | 0 | 0 | 2025-10-20 | Pavement Repair | Repair Storm Damage Hum Cnty Near Weitchpec From Mawah Creek Repair Roadway Embankment With Retain Walldir'S Emergency F.A. | 9 | 4 | 281766.18 | 35568 | 7485000 | 58676 | 2026-04-02 | 2025-03-10 | 2025-03-03 |  |  | 11 | 0 | 120 | 0 |  | X
01 | 01-0M6304 | 0M6304 | 01-HUM-211-74.2/79.3 |  |  | Dryco Construction, Inc. Dba Dryco | 9390 Elder Creek Road | Sacramento Ca 95829 |  | 7076210000 | 1487 Sandy Prairrie Court St E | Fortuna, Ca 95540 | Rodriguez, Joaquin | 401644.32 | 0 | 0 | 0 | 2025-11-20 | Micro-Surfacing, Replace Ac Surfacing, And | Humboldt County In And Near Ferndale From 0.4 Mile South Of Salt River Overflow To Singley Road | 12 | 34 | 401644.32 | 1061579.2 | 1061579.2 | 59828 | 2025-12-26 | 2025-04-21 | 2025-03-26 |  | S | 3 | 0 | 25 | 0 |  | X
01 | 01-0M7304 | 0M7304 | 01-HUM-211-772.0/78.6 | 20.20 201130 |  | Myers & Sons Construction Llc | 45 Morrison Ave. | Sacramento, Ca 95838 |  | 7078340219 | 1487 Sandy Praire Court Suite E | Fortuna, Ca 95501 | Morgan-Marbet, Tai | 0 | 901547.26 | 0 | 0 | 2026-01-20 | Fernbridge Bridge Repair | Emergency Earthquake Bridge Repair Dir'S Emergency F.A. | 86 | 95 | 26571454.76 | 36000 | 27985000 | 46364 | 2026-03-23 | 2023-01-06 | 2022-12-20 |  |  | 216 | 0 | 250 | 0 |  | X
01 | 01-0N7304 | 0N7304 | 01-HUM-255-8.3/8.7 |  |  | St. Francis Electric, Llc | 975 Carden St | San Leandro Ca 94577 | [5 empty] | 0 | 0 | 0 | 0 |  | Modify Signal And Lighting Systems And Tra | Humboldt County In Arcata From K Street Tof Street | 0 | 0 | 0 | 693700 | 693700 | 59299 |  | 2025-07-09 | 2025-06-13 |  |  | 0 | 0 | 30 | 0
01 | 01-0N0904 | 0N0904 | 01-HUM-299-9.0/.6 | 20.XX 201130 |  | Mccullough Construction Inc | 57 Aldergrove Rd | Arcata Ca 95521 | 7078251014 | 7072230030 | 5065 Boyd Rd | Arcata Ca 9551 | Retherford, Ethan | 0 | 93463.31 | 0 | 0 | 2026-02-20 | Pavement Repairs | Repair Storm Damage Humboldt Cnty 19 M West Of Willow Creek Traffic Control Remove Embank Etc. Dir'S Emergency F.A. | 79 | 80 | 3997804.84 | 26719 | 4985000 | 52885 | 2026-03-20 | 2023-07-25 | 2023-06-19 | 2026-02-25 |  | 79 | 0 | 100 | 0 |  | X
01 | 01-0P4004 | 0P4004 | 01-HUM-299-22.0/2.2 | 20.XX 201130 |  | Granite Construction Inc | 1324 S State Street | Ukiah Ca 95482 |  | 7074961086 | 5065 Boyd Rd Suite H | Arcata Ca 95521 | Banuelos, Efren | 0 | 400434.38 | 0 | 0 | 2025-07-20 | Repair Fire Damage | Repair Fire Damage Humbodlt Cnty Glendale At 0.3 Miles East Traffic Cntrl Hazard Tree Removal Dir'S Emergency F.A. | 47 | 89 | 701176 | 1800 | 785000 | 56846 | 2025-09-03 | 2024-12-18 | 2024-07-03 |  |  | 28 | 0 | 60 | 0 |  | X
01 | 01-0J4104 | 0J4104 | 01-HUM-299-30.7/33.4 | HB1 | HSNH-P299- (214)E | Mccullough Construction Inc | 57 Aldergrove Road | Arcata Ca 95521 |  | 7072230030 | 5065 Boyd Road, Suite G | Arcata, Ca 95521 | Retherford, Ethan | 1932 | 26156.24 | 0 | 0 | 2026-02-20 | Construct Soldier Pile Ground Anchor Walls | Humboldt County Near Willow Creek From 0.1Mile East Of Cedar Creek Road To 0.1 Mile East Of East Fork Willow Creek Bridge | 87 | 94 | 19099377.22 | 19584945.52 | 20210465.52 | 46186 | 2026-03-09 | 2022-12-27 | 2022-11-28 |  | S | 374 | 0 | 365 | 65 |  | X
01 | 01-0Q2304 | 0Q2304 | 01-HUM-299-79.0/9.8 | 20.XX 201130 |  | Gr Sundberg, Inc | 5211 Boyd Rd | Arcata Ca 95521 |  | 7072230030 | 5065 Boyd Rd Suite G | Arcata Ca 95521 | Retherford Ethan | 0 | 3565.64 | 0 | 0 | 2026-02-20 | Repair Drainage & Rdwy Embankment | Repair Storm Damage Hum Co Nr Blu Lak 0.73-2.63M E Blu Lak Bvlrepair Drainage & Rdwy Embankment Dir'S Emergency F.A. | 9 | 0 | 3565.64 | 18475 | 2985000 | 60313 | 2026-07-27 | 2025-07-08 | 2025-05-19 |  |  | 11 | 0 | 120 | 0 |  | X
01 | 01-0P9104 | 0P9104 | 01-HUM-299-210.0/22 | 20.XX 201130 |  | Kernen Construction | 2350 Glendale Drive | Mckinleyville Ca 95519 | 7078268686 | 7072230030 | 5065 Boyd Rd | Suite G Arcata 95521 | Retherford Ethan | 0 | 66181.85 | 0 | 0 | 2026-02-20 | Pavement Repairs | Repair Storm Damage Hum Cnty 14 Miles East Of Blue Lake Repair Roadyway And Drainage Dir'S Emergency F.A. | 14 | 18 | 265487.6 | 7250 | 1485000 | 58175 | 2026-06-01 | 2025-05-06 | 2025-04-08 |  |  | 11 | 0 | 80 | 0 |  | X
01 | 01-0Q1104 | 0Q1104 | 01-HUM-299-235.0/27.3 | 20.XX 201130 |  | Mccullough Construction Inc | 57 Alder Grove Rd | Arcata Ca 95521 |  | 7072230032 | 6501 South Broadway Street Suite A | Eureka Ca 95503 | Walker Kristina | 0 | 22539.17 | 0 | 0 | 2026-02-20 | Repair Storm Damage | Repair Storm Damage Hum Cnty 12 Miles West Of Willow Creek Stabilize Slope Repair Guardrail Dir'S Emergency F.A. | 13 | 15 | 513163.86 | 17888 | 3485000 | 60142 | 2026-06-15 | 2025-06-09 | 2025-05-05 |  |  | 16 | 0 | 120 | 0 |  | X
01 | 01-0P8404 | 0P8404 | 01-HUM-451-30.0/4 | 20.XX 201130 |  | Ford Logging, Inc Dba Pacific Earthscape | 1225 Central Avenue, Suite 11 | Mckinleyville, Ca 95519 |  | 7074960332 | 1487 Sandy Prairie Court Ste. E | Fortuna Ca 95501 | Long, Cody | 0 | 5442.18 | 0 | 0 | 2026-01-20 | Repair Storm Damage | In Humboldt County Near Phillipsville From0.23 Mile North Of Franklin Grove To 0.8 Msouth Of Maple Hills Road Dir'S Emergency F.A | 25 | 53 | 1570525.5 | 6975 | 2985000 | 57215 | 2026-06-04 | 2025-02-27 | 2024-12-19 |  |  | 30 | 0 | 120 | 0 |  | X
01 | 01-0H8404 | 0H8404 | 01-LAK-20-2.0/2.8 | HB1 | HSST-P020- (201)E | Ghilotti Construction Company,Inc. | 246 Ghilotti Avenue | Santa Rosa Ca 95407 | 7079780441 | 7072231213 | Po Box 457 | Lower Lake, Ca 95457 | Seyoum, Kassaye | 450 | 47426.26 | 0 | 0 | 2026-02-20 | Rdwy Exc, Place Hma-A & Rhma, Const Soldie | Lake County About 6 Miles West Of Upper Lake From 0.6 Mile West Of Irvine Avenue To 0.1 Mile East Of Mid Lake Road | 96 | 98 | 15759454.86 | 15624772.41 | 16226045.41 | 52267 | 2026-10-09 | 2023-08-23 | 2023-07-21 |  |  | 299 | 0 | 310 | 0 |  | X
01 | 01-0N6804 | 0N6804 | 01-LAK-20-16.6/18.1 |  |  | American Civil Constructors West Coast, Llc | 2990 Bay Vista Court, Suite D | Benicia Ca 94510 | [5 empty] | 0 | 0 | 0 | 0 |  | Rectangular Rapid Flashing, Surface Treatm | Lake County At Lucerne From Grove Street To Ogden Road | 0 | 0 | 0 | 694000 | 694000 | 59515 |  | 2025-07-23 | 2025-06-10 |  |  | 0 | 0 | 30 | 0
01 | 01-0P9604 | 0P9604 | 01-MEN-1-6.0/.6 | 20.XX 201130 |  | Wylatti Resource Management | P.O. Box 575 | Covelo Ca 95428 |  | 7074985816 | 925 N Franklin Street | Fort Bragg Ca 95437 | Mosallai Mojtaba | 0 | 330612.78 | 0 | 0 | 2026-02-20 | Pavement Repairs | Repair Storm Damage Men County New Gualala At Old State Hwwy Repair Roadway And Drainage Dir'S Emergency Order F.A. | 87 | 80 | 7867671.6 | 49325 | 9885000 | 58658 | 2026-03-25 | 2025-05-06 | 2025-04-14 |  |  | 157 | 0 | 180 | 0 |  | X
01 | 01-0F7104 | 0F7104 | 01-MEN-1-6.4/9.5 |  | HSST-S001- (667)E | Ghilotti Construction Company,Inc. | 246 Ghilotti Avenue | Santa Rosa Ca 95407 |  |  | 925 N. Franklin Street | Fort Bragg, Ca 95437 | Chen, Peng | 1760 | 0 | 0 | 0 | 2026-02-20 | Hma-A, Roadway Excavation, And Mechanicall | Mendocino County Near Gualala From 0.3 Mile North Of Havens Neck Drive To Gypsy Flat Road And From 0.5 Mile To 0.2 Mile South Of I | 19 | 92 | 3804032.55 | 3962961.2 | 4087961.2 | 56928 | 2026-10-23 | 2025-01-07 | 2024-12-26 |  |  | 60 | 0 | 310 | 0 |  | X
01 | 01-0E11U4 | 0E11U4 | 01-MEN-1-31.1/31.6 |  | ACST-S001- (662)E | Granite Construction Company | 580 W Beach Street | Watsonville Ca 95076 | 7074674100 | 7074985816 | 925 N Franklin St | Fort Bragg Ca 95437 | Mosallai Mojtaba | 8258 | 0 | 0 | 0 | 2026-02-20 | Structural Conc Bridge, Temp Bridge And Ba | Mendocino County Near Elk From 0.2 Mile South Of Elk Creek Bridge To 0.2 Mile North Of Elk Creek Bridge | 99 | 97 | 12207976.9 | 11983837.38 | 12469800.27 | 54644 | 2026-10-28 | 2023-12-13 | 2023-11-15 |  |  | 190 | 0 | 175 | 17 |  | X
01 | 01-0H6004 | 0H6004 | 01-MEN-1-33.7/51 |  | ACST-S001- (668)E | Argonaut Constructors | 360 Sutton Place | Santa Rosa Ca 95407 |  | 7074985816 | 925 N Franklin Street | Fort Bragg, Ca 95437 | Mosallai, Mojtaba | 201447.75 | 750 | -195831.9 | 0 | 2026-02-20 | Hma, Rhma, Cold Plane, Guardrail, And Deli | Mendocino County Near Elk From 0.1 Mile North Of Greenwood Creek Bridge To 0.2 Mile North Of Little Lake Road At Mendocino | 69 | 92 | 23212994.95 | 24565444 | 24717291.27 | 57128 | 2026-02-27 | 2025-01-24 | 2024-11-25 |  | S | 125 | 0 | 180 | 0 |  | X
01 | 01-0B22U4 | 0B22U4 | 01-MEN-1-59.8/62.1 |  | ACST-S001- (671)E | Ghilotti Construction Company,Inc. | 246 Ghilotti Avenue | Santa Rosa Ca 95407 | [5 empty] | 0 | 0 | 0 | 0 |  | Retaining Walls, Minor Concrete, Earthwork | Mendocino County In Fort Bragg From Route 20 To Pudding Creek Bridge | 0 | 0 | 0 | 6967644.05 | 6967644.05 | 60445 |  | 2026-02-25 | 2026-02-05 |  |  | 0 | 0 | 620 | 0
01 | 01-0P7404 | 0P7404 | 01-MEN-1-114.0/11.6 | 20.XX 201130 |  | Engelke Construction Inc | Po Box 1387 | Healdsburg Ca 95448 |  | 7074338389 | 925 N Franklin Street | Fort Bragg Ca 95437 | Mossallai Mojtaba | 0 | 154494.07 | 0 | 0 | 2026-02-20 | Pavement Repair | Repair Slipout In Mendo Cnty In Galloway From 0.02 Mile Erosion Cntrl Guardrail Repair Roadway Dir'S Emergency F.A. | 100 | 61 | 1212854.63 | 12975 | 1985000 | 57132 | 2026-03-30 | 2025-02-25 | 2024-12-16 |  |  | 233 | 0 | 120 | 0
01 | 01-0Q9904 | 0Q9904 | 01-MEN-1-196.0/19.6 | 20.20 201130 |  | Argonaut Constructor'S, Inc. | 360 Sutton Place | Santa Rosa, Ca 95407 |  | 7074985816 | 925 N Franklin Street | Fort Bragg, Ca 95437 | Mosallai, Mojtaba | 0 | 453017.37 | 0 | 0 | 2026-02-20 | Repair Drainage & Roadway | In Mendocino County Repair Drainage And Roadway Dir'S Emergency Lb | 43 | 51 | 453017.37 | 4118 | 885000 | 60374 | 2026-04-10 | 2026-02-02 | 2026-01-06 |  |  | 26 | 0 | 60 | 0 |  | X
01 | 01-0Q1004 | 0Q1004 | 01-MEN-1-418.0/42.5 | 20.XX 201130 |  | Wylatti Resource Management | P.O. Box 575 | Covelo Ca 95428 |  | 7074985816 | 925 N. Franklin Street | Fort Bragg Ca 95437 | Mosallai Mojtaba | 0 | 4020.59 | 0 | 0 | 2026-02-20 | Repair Slide | Repair Slide Men Cnty Two Miles South Of Albion Stabelize Cutslope With Dirt Filled Rsp Dir'S Emergency F.A. | 50 | 80 | 1595069.35 | 12975 | 1985000 | 58955 | 2026-04-27 | 2025-05-07 | 2025-05-05 |  |  | 45 | 0 | 90 | 0 |  | X
01 | 01-0Q5804 | 0Q5804 | 01-MEN-1-611.0/61.1 | 20.80 251000 |  | Engelke Construction Inc | Po Box 1387 | Healdsburg Ca 95448 |  | 7076849518 | 925 N Franklin St | Fort Bragg Ca 95437 | Chen Peng | 0 | 384820.48 | 0 | 0 | 2026-02-02 | Repair Storm Damage | Repair Sink Men Cty Ft Bragg At Maple St Repair Drainage And Rdwy Dir'S Emergency F.A. | 22 | 32 | 482413.02 | 9975 | 1485000 | 60237 | 2026-04-29 | 2025-12-04 | 2025-11-12 |  |  | 13 | 0 | 60 | 0 |  | X
01 | 01-0P1704 | 0P1704 | 01-MEN-1-749.0/78 | 20.XX 201130 |  | Wylatti Resource Management | Po Box 575 | Covelo Ca 95428 |  | 7076665954 | 925 N Franklin Street | Fort Bragg, Ca 95437 | Moore, Douglas | 0 | 439493.52 | 0 | 0 | 2026-02-20 | Repair Sink | Multiple Landslide Repair Mendo Cnty Westport Blue Slide Gulch Traffic Cntrl Reconstruct Roadway Dir'S Emergency Order F.A. | 100 | 79 | 1952964.12 | 15775 | 2485000 | 55802 | 2026-03-30 | 2024-05-21 | 2024-04-22 |  |  | 356 | 0 | 170 | 0
01 | 01-0N4404 | 0N4404 | 01-MEN-1-750.0/76.5 | 20.XX 201130 |  | Myers & Sons Construction Llc | 45 Morrison Ave | Sacramento Ca 95838 |  | 7076685954 | 925 North Franklin Street | Fort Bragg, Ca 95437 | Moore, Douglas | 0 | 6195237.75 | 0 | 0 | 2026-02-20 | Pavement Repairs | Repair Landslide Men Cnty Near Westport Traffic Control Repair Drainage Etc Dir'S Emergency L.B. | 89 | 67 | 73581927.93 | 180000 | 109985000 | 54244 | 2026-05-19 | 2023-09-28 | 2023-09-28 |  |  | 506 | 0 | 240 | 327
01 | 01-0Q9704 | 0Q9704 | 01-MEN-1-781.0/78.3 | 20.XX 201130 |  | Wylatti Resource Management In | Po Box 575 | Covelo Ca 95428 |  | 7076665954 | 925 N Franklin St | Fort Bragg Ca 95437 | Moore Douglas | 0 | 0 | 0 | 0 |  | Soldier Pile Ground Anchor Retaining Wall | Men-1 Westport - Repair Slipout Men Co Near Westport 0.2M S Wages Crk Brdgsoldier Pile Ground Anchor Retaining Wall Dir'S Emergen | 0 | 0 | 0 | 59725 | 14985000 | 60384 | 2026-10-09 | 2026-01-22 | 2025-12-22 |  |  | 0 | 0 | 180 | 0
01 | 01-0P0704 | 0P0704 | 01-MEN-1-821.0/82.9 | 20.XX 201130 |  | Granite Construction Company | 1324 S. State Street | Ukiah Ca 95482 |  | 7076665954 | 925 North Franklin Street | Fort Bragg, Ca 95437 | Moore, Douglas | 0 | 1313293.24 | 0 | 0 | 2026-02-20 | Multiple Location Slipout Repairs | Repair Multiple Slipouts Men Cnty Near Rockport Traffic Cntrl Recon Restruct Rdway Dir'S Emergency F.A. | 100 | 76 | 18952274.66 | 11250 | 24985000 | 55881 | 2026-03-30 | 2024-03-29 | 2024-03-18 |  |  | 307 | 0 | 180 | 120
01 | 01-0E0904 | 0E0904 | 01-MEN-20-33.3/34.4 | HA21 | ACNH-P020- (198)E | Myers & Sons Construction, Llc | 4600 Northgate Blvd, Suite 10 | Sacramento Ca 95834 | 9162839950 | 7074964355 | 6301 North State Street | Redwood Valley, Ca 95470 | Geoffrey Wright | 10640 | 0 | 0 | 0 | 2026-01-20 | Replace Two Bridges | In Mendocino County Near Ukiah From 0.3 Mile West Of Russian River Bridge And Overhead To 0.4 Mile East Of County Road 144 | 68 | 100 | 27052212.3 | 26008165.8 | 27331030.75 | 42689 | 2026-03-18 | 2022-06-09 | 2022-05-06 |  |  | 532 | 0 | 780 | 2 |  | X
01 | 01-0E0914 | 0E0914 | 01-MEN-20-33.3/34.4 |  |  | Wylatti Resource Management, Inc. | 23601 Cemetery Lane | Covelo Ca 95428 | [5 empty] | 0 | 0 | 0 | 0 |  | Replace Plants And Plant Establishment Wor | Mendocino County Near Ukiah From 0.3 Mile West Of Russian River Bridge And Overhead To 0.3 Mile East Of County Road 144 | 0 | 0 | 0 | 430242.45 | 430242.45 | 60385 |  | 2026-01-28 | 2026-01-08 |  |  | 0 | 0 | 750 | 0
01 | 01-0P8604 | 0P8604 | 01-MEN-20-328.0/32.8 | 201.XX201130 |  | Bouthillier Construction | 1571 S Main St | Willits Ca 95490 |  | 7078341151 | 21340 Baechtel Rd | Willits Ca 95490 | Winter Brian | 0 | 0 | 0 | 0 |  | Repair Storm Damage | Repair Storm Damage Men Cnty Near Willits Broaddus Creek Repair Erosion At Southeast Abutment Dir'S Emergency L.B. | 0 | 0 | 0 | 3000 | 485000 | 60180 | 2025-11-28 | 2025-03-24 | 2025-03-03 | 2026-01-27 |  | 0 | 0 | 20 | 0
01 | 01-0H1404 | 0H1404 | 01-MEN-101-10.7/11.2 |  | ACNH-Q101- (451)E | O.C. Jones & Sons, Inc. | 1520 Fourth Street | Berkeley Ca 94710 |  | 7079945074 | P.O. Box 457 | Lower Lake, Ca 95457 | Hadipour, Roozbeh | 0 | 0 | 0 | 0 |  | Reconstruct Roadway And Construct Faciliti | Mendocino County At Hopland From Feliz Creek Bridge To 0.2 Mile North Of First Street | 0 | 0 | 0 | 6432677 | 6508977 | 60279 |  | 2025-12-30 | 2025-12-02 |  |  | 0 | 0 | 241 | 0
01 | 01-0H5704 | 0H5704 | 01-MEN-101-20.9/28.6 |  | ACNH-Q101- (455)E | Ghilotti Bros., Inc. | 525 Jacoby Street | San Rafael Ca 94901 | [5 empty] | 0 | 0 | 0 | 0 |  | Place Asphalt, Vegetation Control & Instal | Mendocino County In And Near Ukiah From North Of Robinson Creek Bridge To Pomo Lane Undercrossing | 0 | 0 | 0 | 45982579 | 45982579 | 60446 |  | 2026-02-25 | 2026-01-15 |  |  | 0 | 0 | 480 | 0
01 | 01-0H1604 | 0H1604 | 01-MEN-101-33.7/43.2 | HA22 | ACNH-Q101- (416)E | Granite Construction Company | 715 Comstock St | Santa Clara Ca 95054 | 7074674118 | 7074964355 | 6301 North State Street | Redwood Valley, Ca 95470 | Steve Tisell | 0 | 3785.21 | 0 | 0 | 2026-02-20 | Replace Ac Surfacing, Place Hma-A, Rhma-G | Mendocino County Near Willits From 1.1 Miles North Of West Road Overcrossing To 0.6 Mile South Of Haehl Creek Bridge | 98 | 98 | 23679110.3 | 23216265.6 | 24968039.1 | 50104 | 2026-05-29 | 2023-06-08 | 2023-05-04 |  |  | 168 | 0 | 165 | 6 |  | X
01 | 01-0K4104 | 0K4104 | 01-MEN-101-41.3/43.3 |  | NHHS-Q101- (430)E | Gr Sundberg, Inc. | 5211 Boyd Road | Arcata Ca 95521 | 7078256565 | 7078341151 | 21340 Baechtel Road | Willits, Ca 95490 | Winter Brian | 230297.2 | 62424.44 | 0 | 0 | 2026-02-20 | Concrete Barrier, Wildlife Fence, Clearing | Mendocino County Near Willits From 0.4 Mile North Of Black Bart Road To 0.2 Mile South Of Northbound Offramp To Route 20 | 95 | 91 | 7708101.29 | 7851744.9 | 8155746.82 | 57120 | 2026-05-01 | 2024-10-31 | 2024-10-03 |  |  | 138 | 0 | 145 | 0 |  | X
01 | 01-0H1704 | 0H1704 | 01-MEN-101-48.9/55.1 | HA22 | ACNH-Q101- (423)E | Granite Construction Company 1324 South State Street Ukiah, Ca 95482 | 580 W Beach Street | Watsonville Ca 95076 |  | 7078155647 | 6301 North State Street | Redwood Valley, Ca 95470 | Tisell, Steve | 0 | 50083.58 | 0 | 0 | 2025-12-20 | Cold Plane Ac Pavement And Place Hma-A, Rh | Mendocino County Near Willits From 0.6 Mile North Of Upp Creek Bridge To 0.1 Milesouth Of Big Trails Drive | 72 | 93 | 8877039.9 | 8955869.78 | 9393987.92 | 55911 | 2025-12-30 | 2024-06-05 | 2024-04-26 |  |  | 68 | 0 | 95 | 0 |  | X
01 | 01-0K8904 | 0K8904 | 01-MEN-101-50.7/52.2 |  | NHHS-Q101- (444)E | Granite Construction Company | 1324 S. State Street | Ukiah Ca 95482 |  | 7078155647 | 6301 North State Street | Redwood Valley, Ca 95470 | Tisell, Steve | 6877.4 | 34979.27 | 0 | 0 | 2026-02-20 | Hma, Roadway Excavation, And High Friction | Mendocino County Near Willits From Outlet Creek To 1.5 Miles North Of Outlet Creek | 12 | 38 | 2237055.89 | 5707962.2 | 5779403.04 | 59275 | 2026-04-06 | 2025-07-01 | 2025-05-21 |  |  | 41 | 0 | 355 | 0 |  | X
01 | 01-0H5504 | 0H5504 | 01-MEN-101-55.0/64.9 |  | ACNH-Q101- (427)E | Granite Construction Company | 580 W Beach Street | Watsonville Ca 95076 |  | 7072231213 |  |  | Seyoum, Kassaye | 324367.36 | 127288.2 | 0 | 0 | 2026-02-20 | Hma, Rhma, And Cold Plane Asphalt Concrete | Mendocino County Near Longvale From 2.6 Miles South Of Arnold Bridge Overhead 10-179 To 0.1 Mile North Of Long Valley Creek Bridge | 68 | 96 | 21078895.89 | 22900700.3 | 23618947.97 | 56414 | 2026-06-01 | 2024-09-18 | 2024-08-15 |  |  | 114 | 0 | 120 | 2 |  | X
01 | 01-0P2604 | 0P2604 | 01-MEN-101-599.0/59.9 | 20.XX 201130 |  | Myers & Sons Construction, Llc | 45 Morrison Ave, | Sacramento, Ca 95838 |  | 7074964368 | 6301 North State Street | Redwood Valley, Ca 95470 | Hadipour, Roozbeh | 0 | 5463.77 | 0 | 0 | 2026-01-20 | Emergency Bridge Deck Repair | In Mendocino County Near Longvale At Long Valley Creek Bridge. Dir'S Emergency F.A. | 100 | 77 | 7461608 | 36000 | 9692000 | 56278 | 2026-06-30 | 2024-07-30 | 2024-07-15 |  |  | 280 | 0 | 123 | 23
01 | 01-0Q2604 | 0Q2604 | 01-MEN-101-727.0/72.7 | 20.XX 201130 |  | Ghilotti Construction Company | 246 Ghilotti Avenue | Santa Rosa Ca 95407 |  | 7074964368 | 6301 North State Street | Redwood Valley Ca 95470 | Hadipour Roozbeh | 0 | 158453.24 | 0 | 0 | 2026-02-20 | Repair Storm Damage | Repair Storm Damage Men Cnty Near Laytonville Repair Sink And Drainage Dir'S Emergency L.B. | 100 | 85 | 3930574 | 4430 | 4635000 | 58916 | 2026-03-31 | 2025-06-13 | 2025-04-11 |  |  | 214 | 0 | 180 | 0 |  | X
01 | 01-0P0904 | 0P0904 | 01-MEN-101-860.0/87.5 | 20.XX 201130 |  | Ghilotti Construction Company,Inc. | 246 Ghilotti Avenue | Santa Rosa, Ca 95407 |  | 7078155647 |  |  | Tisell, Steve | 0 | 23553.5 | 0 | 0 | 2025-12-20 | Repair Slide Damage | In Mendocino County Near Cummings On Route101 From 1.7 Miles South To 0.2 Mile Southof Grizzly Creek 101/271 Seperation Dir'S Emer | 41 | 82 | 3266765.09 | 11340 | 3985000 | 55679 | 2026-06-08 | 2024-04-24 | 2024-03-10 |  |  | 82 | 0 | 201 | 0 |  | X
01 | 01-0Q4004 | 0Q4004 | 01-MEN-101-873.0/87.3 | 20.XX 201130 |  | Mercer-Fraser Company | 77 W 2Nd Street | Eureka Ca 95501 |  | 7078155647 | 6301 North State Street | Redwood Valley Ca 95470 | Tisell Steve | 0 | 0 | 0 | 0 |  | Subsurf Drainage Geotech Study & Rdwy Rep | Repair Pushup Men Cty Near Cummings 0.3Mi S Rte 101/271 Subsurf Drainage Geotech Study & Rdwy Rep Dir'S Emergency F.A. | 0 | 0 | 0 | 14040 | 2485000 | 60253 | 2026-03-24 | 2025-09-26 | 2025-09-02 |  |  | 0 | 0 | 90 | 0
01 | 01-0N8104 | 0N8104 | 01-MEN-128-40.9/44.3 |  |  | Doolittle Construction Llc | 15 Business Parkway Suite 105 | Sacramento Ca 95828 |  | 7078155647 | 2617 Hwy 20 | Nice, Ca 95464 | Tisell, Steve | 23154.6 | 0 | 0 | 0 | 2025-08-20 | Replace Ac Surfacing, Slurry Seal, And Pav | Mendocino County Near Yorkville From 2.1 Miles East Of Beebe Creek Bridge To 0.8 Mile East Of Dry Creek Bridge | 95 | 98 | 758175.74 | 739000 | 739000 | 59436 | 2025-09-03 | 2025-04-21 | 2025-03-26 |  |  | 19 | 0 | 20 | 0 |  | X
01 | 01-0Q0604 | 0Q0604 | 01-MEN-128-281.0/28.1 | 20.XX 201130 |  | Pomilia Civil | P.O. Box 719 | Redwood Valley Ca 95470 |  | 7074985816 | 925 N. Franklin Street | Fort Bragg Ca 95437 | Mosallai Mojtaba | 0 | 92184.13 | 0 | 0 | 2025-12-20 | Repair Storm Damage Men-128 | Repair Storm Damage Men Cnty In Boonville At Maint Station Stabilize Slope Between Anderson Creek Dir'S Emergency F.A. | 86 | 69 | 1022609.18 | 37500 | 1485000 | 59536 | 2026-01-09 | 2025-04-30 | 2025-04-14 |  |  | 77 | 0 | 90 | 0
01 | 01-0A1314 | 0A1314 | 01-MEN-162-8.0/8.4 |  | ACST-P162- (043)E | Ghilotti Construction Company,Inc. | 246 Ghilotti Avenue | Santa Rosa Ca 95407 | 7075851221 | 7074964368 | 6301 North State Street | Redwood, Valley Ca 95470 | Hadipour, Roozbeh | 310590 | 298378.49 | 750000 | 0 | 2026-02-20 | Replace Bridge. | Mendocino County About 8 Miles East Of Longvale From 0.2 Mile West To 0.1 Mile East Of Eel River Bridge | 23 | 47 | 9090746.7 | 17026070.6 | 19415025.14 | 50804 | 2027-05-28 | 2023-07-03 | 2023-06-12 |  | S | 93 | 0 | 410 | 0 |  | X
01 | 01-0P9704 | 0P9704 | 01-MEN-162-161.0/16.2 | 20XX 201130 |  | Wylatti Resource Management | Po Box 575 | Covelo Ca 95428 |  | 7074964368 | 6301 North State Street | Redwood Valley Ca 95470 | Hadipour Roozbeh | 0 | 17116.69 | 0 | 0 | 2026-02-20 | Pavement Repairs | Repair Slipout Men Cnty Along Hwy 162 At Postmile 16.1 Retaining Wall Repairs To Roadway Dir'S Emergency F.A. | 100 | 5 | 506241.92 | 49725 | 9985000 | 58638 | 2026-10-29 | 2025-05-15 | 2025-04-21 |  |  | 164 | 0 | 150 | 0
01 | 01-0Q2504 | 0Q2504 | 01-MEN-162-211.0/21.1 | 20.XX 201130 |  | Granite Construction Company | 1324 South State St | Ukiah Ca 95482 |  | 7078155647 | 21340 Baechtel Rd | Willits Ca 95490 | Tisell Steve | 0 | 1893.27 | 0 | 0 | 2026-01-20 | Stabilize Rdwy Embank W Rock Buttress | Repair Sink Men Cty Near Covelo 1.3Miles E Of Sandbankstabilize Rdwy Embank W Rock Buttress Dir'S Emergency F.A. | 3 | 1 | 15751.45 | 4500 | 1985000 | 60220 | 2026-04-14 | 2025-07-08 | 2025-06-16 |  |  | 2 | 0 | 60 | 0 |  | X
01 | 01-0H1504 | 0H1504 | 01-MEN-162-/25.7 | HA22 | ACST-P162- (044)E | Granite Construction Company | 1324 S. State Street | Ukiah Ca 95482 |  | 7078155647 | 6301 North State Street | Redwood Valley, Ca 95470 | Tisell, Steve | 0 | 7948.6 | 0 | 0 | 2026-02-20 | Hma, Rhma, And Geosynthetic Pavement Inter | Mendocino County Near Longvale From Route 101 To 1.1 Miles South Of Poonkinney Road Near Covelo | 40 | 62 | 22593823.51 | 36081257.15 | 36481247 | 55785 | 2026-07-13 | 2024-05-15 | 2024-03-26 |  | S | 66 | 0 | 165 | 0 |  | X
01 | 01-0Q4204 | 0Q4204 | 01-MEN-175-62.0/6.4 | 20.XX 201130 |  | Rege Construction Inc | 600 Santana Dr | Cloverdale Ca 95425 |  | 7076849518 | 925 N. Franklin Street | Fort Bragg Ca 95437 | Chen Peng | 0 | 100411.52 | 0 | 0 | 2026-01-20 | Repair Slip Out | Repair Slip Out In Men Cnty About 2 Miles West Of Oasis Retaining Wall Subsurface Drainage Dir'S Emergency L.B. | 4 | 1 | 100411.52 | 43725 | 8485000 | 60182 | 2026-08-03 | 2025-09-30 | 2025-09-02 |  |  | 5 | 0 | 140 | 0 |  | X
01 | 01-0P3504 | 0P3504 | 01-MEN-253-130.0/13 | 20.XX 201130 |  | Rege Construction Inc. | 600 Santana Dr | Cloverdale Ca 95425 |  | 7076849518 | 925 N. Franklin Street | Fort Bragg Ca 95437 | Chen Peng | 0 | 48955.48 | 0 | 0 | 2025-10-20 | Repair Slipout | Repair Slipout Men Cnty Near Ukiah Erosion Cntrl Mechanically Stabilized Dir'S Emergency F.A. | 52 | 73 | 1449958.51 | 9975 | 1985000 | 57475 | 2025-12-31 | 2025-03-11 | 2025-02-24 |  |  | 83 | 0 | 120 | 40 |  | X
01 | 01-0P9404 | 0P9404 | 01-MEN-271-24.0/2.5 | 20.20 201130 |  | Bud Garman Const. Services Inc | 24900 N. Hwy 101, | Willits, Ca 94590 |  | 7074985816 | 925 N. Franklin Street | Fort Bragg, Ca 95437 | Mojtaba Mosallai | 0 | 2956.77 | 0 | 0 | 2026-02-20 | Slide Repair | In Mendocino County Near Cummings From 0.68 Mile To 0.78 Mile South Of 101/271 Separation Dir'S Emergency Fa | 100 | 66 | 981011.64 | 9975 | 1485000 | 57377 | 2026-03-30 | 2025-03-11 | 2025-02-03 |  |  | 163 | 0 | 120 | 0
01 | 01-0H1204 | 0H1204 | 01-VAR-101-84.0/85.5 | 20.20 201130 |  | Steelhead Constructions, Inc. | Po Box 997 | Palo Cedro, Ca 96073 |  | 7074851010 | 6301 North State Street | Redwood Valley, Ca 95470 | Seyoum, Kassaye | 0 | 16359.14 | 0 | 0 | 2021-04-20 | Slope Stabilization & Reconstruct Roadway | In Mendocino County On Rt 101 From Truck Passing Lane Rt To 0.4 Mile North Of End Truck Passing Lane Rt & On Rt 271 From 3.5Dir'S | 100 | 90 | 5401364.3 | 31425 | 5985000 | 37246 | 2021-05-04 | 2017-05-25 | 2017-03-31 |  |  | 963 | 0 | 75 | 0 |  | X
01 | 01-0Q9804 | 0Q9804 | 01-VAR--/0 | 20.20 201130 |  | Bud Garman Construction Inc | 24900 N. Hwy 101 | Willits, Ca 94590 |  | 7076849518 | 925 North Franklin Street | Fort Bragg, Ca 95437 | Chen, Peng | 0 | 386387.84 | 0 | 0 | 2026-02-20 | Repair Slide | In Mendocino County Repair Slide Slide Removal Dir'S Emergency Lb | 60 | 26 | 386387.84 | 9975 | 1485000 | 60376 | 2026-03-18 | 2026-01-03 | 2026-01-03 |  |  | 27 | 0 | 45 | 0 |  | X
01 | 01-0N2904 | 0N2904 | 01-VAR--/0 |  | ACST-X015- (017)E | Mccullough Construction, Inc. | 57 Aldergrove Road | Arcata Ca 95521 | [5 empty] | 0 | 0 | 0 | 0 |  | Replace Bridge, Excavation, And Retaining | Del Norte County At Various Locations | 0 | 0 | 0 | 47768135.84 | 47768135.84 | 60425 |  | 2026-02-17 | 2025-12-30 |  |  | 0 | 0 | 735 | 0
01 | 01-0M9604 | 0M9604 | 01-VAR--/0 |  |  | Mccuen Construction, Inc. | 3269 Swetzer Road | Loomis Ca 95650 |  | 7078155647 | 6301 North State Street | California 95470 | Tisell, Steve | 0 | 0 | 0 | 0 |  | Polyester Concrete Overlay, Hma, & Cold Pl | Mendocino County At Various Locations | 0 | 0 | 0 | 1043788.7 | 1043788.7 | 59797 |  | 2025-07-14 | 2025-06-23 |  |  | 0 | 0 | 60 | 0
02 | 02-1J75U4 | 1J75U4 | 02-LAS-36-14.4/16.8 |  | HSNH-S036- (121)E | Hat Creek Construction & Materials, Inc. | 24339 State Hwy 89 N. | Burney Ca 96013 | 5303405464 | 5307593733 | 471-800 Diane Drive | Susanville Ca 96130 | Gibbs Daniel | 597092.8 | 0 | 0 | 0 | 2025-10-20 | Place Hma And Class 2 Ab, Excavate Roadway | Lassen County About 9 Miles West Of Susanville From 1.3 Miles West To 1.2 Miles East Of Willard Creek Road | 43 | 37 | 5107129.6 | 13839809 | 13866728.87 | 57134 | 2025-01-22 | 2025-02-13 | 2025-01-23 |  | S | 52 | 0 | 120 | 0 |  | X
02 | 02-2K5404 | 2K5404 | 02-LAS-36-100.0/14 | 20.XX 201130 |  | Tullis Inc | Po Box 493416 | Redding Ca 96049 |  | 5303405464 | 471-800 Diane Drive | Johnstonville Ca 96130 | Gibbs Daniel | 0 | 132028.78 | 0 | 0 | 2026-02-20 | Pavement Repairs | Bad Fred Do N Lassen Cnty About 7 Miles East Westwood Traffic Cntrl Place Hma Leveling Courses Dir'S Emergency L.B. | 100 | 78 | 9599969.01 | 21491 | 12261000 | 57257 | 2029-02-07 | 2025-03-19 | 2025-01-31 |  |  | 376 | 0 | 365 | 0
02 | 02-4H0604 | 4H0604 | 02-LAS-36-/6.1 |  | ACNH-S036- (120)E | Hat Creek Construction & Materials, Inc. | 24339 State Hwy 89 N. | Burney Ca 96013 | 5303355501 | 5307593733 | 471-800 Diane Lane | Susanville Ca 96130 | Gibbs Daniel | 0 | 950.88 | 0 | 0 | 2026-02-20 | Roadway Exc. Class 2 Aggregate Base, Hma, | Lassen And Plumas Counties From Melissa Avenue To 0.6 Mile East Of Red River Canal | 68 | 87 | 35703797.89 | 38245254 | 40727664.2 | 56746 | 2026-05-11 | 2024-12-03 | 2024-11-05 |  | S | 115 | 0 | 170 | 0 |  | X
02 | 02-4H0704 | 4H0704 | 02-LAS-139-.7/11 |  | ACST-S139- (025)E | Hat Creek Construction & Materials, Inc. | 24339 State Hwy 89 N. | Burney Ca 96013 | 5303355501 | 5307593733 | 471-800 Diane Drive | Susanville Ca 96130 | Gibbs Daniel | 0 | 38451.36 | 27317.15 | 0 | 2026-01-15 | Place Hma (Type A), Traffic Control System | Lassen County Near Susanville From 0.1 Mile North Of Chestnut Street To 2.6 Milessouth Of Horse Lake Road | 100 | 100 | 14134418.88 | 13850085 | 14056388.17 | 57133 | 2026-01-15 | 2025-02-13 | 2025-01-29 | 2026-01-21 |  | 145 | 0 | 145 | 0 |  | X
02 | 02-0K6104 | 0K6104 | 02-PLU-70-32.9/33.2 |  |  | Studebaker Electric, Inc. | 3237 Rippey Road, Ste 100 | Loomis Ca 95650 | 9162592395 | 5307593778 | 2535 Notre Dame Blvd | Chico Ca 95928 | Farley Damion | 0 | 0 | 0 | 0 | 2026-01-20 | Modify Highway Advisory Radio System And C | Plumas County Near Paxton From 0.1 Mile West To 0.2 Mile East Of North Junction Route 89 | 0 | 0 | 0 | 825625.5 | 825625.5 | 59155 | 2026-06-18 | 2025-06-26 | 2025-06-18 |  | S | 0 | 0 | 45 | 0 |  | X
02 | 02-1H58U4 | 1H58U4 | 02-PLU-70-58.2/78.4 |  | ACNH-P070- (146)E | Mercer Fraser Company | 200 Dinsmore Dr | Fortuna Ca 95540 | 5303567818 | 5303567818 | 546 Lawrence St | Quincy Ca 95971 | Zdenek Mike | 140218.93 | 212800 | 0 | 0 | 2026-02-20 | Reconstruct Roadway, Hma Paving, Drainage | Plumas County At And Near Cromberg From Gill Ranch Road To 0.2 Mile West Of Big Grizzly Creek Bridge | 45 | 52 | 50779554.02 | 85593593 | 94948898.2 | 52264 | 2026-08-11 | 2023-08-18 | 2023-06-27 |  | S | 162 | 0 | 360 | 0 |  | X
02 | 02-4H0104 | 4H0104 | 02-PLU-70-78.3/90.3 |  | ACST-P070- (149)E | Hat Creek Construction & Materials, Inc. | 24339 State Hwy 89 N. | Burney Ca 96013 | 5302387553 | 5303567818 | 546 Lawrence St | Quincy Ca 95971 | Zdenek Mike | 0 | 335464 | 0 | 0 | 2026-02-20 | Replace Ac Surfacing, Place Hma And Thermo | Plumas County Near Portola From 0.4 Mile West Of Big Grizzly Creek Bridge To 0.8 Mile West Of Summit School Drive | 46 | 55 | 12459361.71 | 15696969 | 22555667.88 | 58896 | 2026-07-15 | 2025-02-18 | 2025-01-29 |  |  | 124 | 0 | 150 | 120 |  | X
02 | 02-3H6904 | 3H6904 | 02-PLU-89-30.2/42.2 |  | TBGP-S089- (034)E | Dig It Construction, Inc. | 803 Lorraine Drive | Chester Ca 96020 | 5303355501 | 5309452437 | 1253 Lorraine Dr | Redding Ca 96001 | Mendoza Sergio | 13775 | 427836.79 | 25000 | 0 | 2026-02-20 | Place Hma, Full Depth Recycling-Foamed Asp | Plumas County Near Canyon Dam From 0.1 Mile North Of Lake Almanor Spillway To Route 36 | 58 | 61 | 21981227.57 | 34450290.72 | 35972905.25 | 57124 | 2026-03-23 | 2025-01-14 | 2024-11-21 |  |  | 99 | 0 | 160 | 10 |  | X
02 | 02-0K7804 | 0K7804 | 02-PLU-89-200.0/20.6 | 20.20 201130 |  | Darren Taylor Construction Inc | 19672 N. Hirch Ct. | Anderson, Ca 96007 |  | 5303569242 | 13700 Highway 36 East | Red Bluff Ca. 96080 | Higgins Kyle | 0 | 0 | 0 | 0 |  | Greenville Paving | Remove And Replace Ac Surface, Fix Stripesplumas County Near Wolf Creek Remove And Replace With 0.1 Grind &Overlaydir'S Emergency | 0 | 0 | 0 | 5820 | 373000 | 52024 |  | 2023-07-25 | 2023-07-06 |  |  | 0 | 0 | 20 | 0
02 | 02-4H1504 | 4H1504 | 02-SHA-5-4.9/5.1 | 20.20 201130 |  | J.F. Shea Construction, Inc. | P. O. Box 494519 | Redding, Ca 96049 |  | 5306045102 | 1031 Butte Street | Redding, Ca 96001 | Alexander, Nathan | 1265 | 139575.92 | 0 | 0 | 2018-01-13 | Remove 1.8 Feet Of Embankment Under Bridge | In Shasta County In Anderson From Anderson Creek Overflow To 0.1 Mile North Of Anderson Creek Bridge. Dir'S Emergency L.B. | 100 | 52 | 140840.92 | 1265 | 270000 | 39084 | 2018-01-13 | 2018-03-07 | 2017-12-06 |  |  | 38 | 0 | 20 | 0
02 | 02-1J8904 | 1J8904 | 02-SHA-5-30.5/31 |  |  | Mccuen Construction, Inc. | 3269 Swetzer Road | Loomis Ca 95650 | 9166527824 | 5303569242 | 13700 Hwy 36 East | Red Bluff Ca 96080 | Higgins Kyle | 18233.11 | 2371.88 | 0 | 0 | 2025-12-20 | Replace Pavement And Place Polyester Concr | Shasta County Near O'Brien From 0.1 Mile South Of Tunnel Gulch Viaduct To The O'Brien Rest Area | 91 | 65 | 1816868.89 | 2739586.99 | 2762950.63 | 59517 | 2026-04-15 | 2025-07-23 | 2025-07-02 |  | S | 50 | 0 | 55 | 0
02 | 02-2K6904 | 2K6904 | 02-SHA-5-401.0/40.1 | 20.XX 201130 |  | J.F. Shea Construction Inc | P.O. Box 494519 | Redding Ca 96049 |  | 5309176666 | 1031 Butte Street | Redding Ca 96001 | Sears Mike | 0 | 0 | 0 | 0 |  | Rmve & Repl Expnsn Jnts Prov Trf Cntrl | Lake Sha (Antlers) Bridge Joint Replcmnt Sha Cty Nr Lakehead 0.6M S To 0.1 S Antlerrmve & Repl Expnsn Jnts Prov Trf Cntrl Dir'S Em | 0 | 0 | 0 | 12268 | 3052000 | 60366 | 2026-04-30 | 2025-08-13 | 2025-07-24 |  |  | 0 | 0 | 175 | 0
02 | 02-1K0504 | 1K0504 | 02-SHA-44-.4/L1.8 |  |  | J.F. Shea Construction, Inc. | 17400 Clear Creek Road | Redding Ca 96001 | 5302464292 | 5306045102 | 1031 Butte St | Redding Ca 96001 | Alexander Nathan | 0 | 112345 | 8716.91 | 0 | 2025-10-31 | Cold Plane Ac Pvmt And Rhma (Gap Graded). | Shasta County In Redding From Continental Undercrossing No. 06-0135L To Route 5/44 Separation | 100 | 100 | 1922555.91 | 1668346 | 1916457.46 | 59816 | 2025-10-31 | 2025-06-03 | 2025-05-15 | 2026-02-11 |  | 18 | 0 | 30 | 0 |  | X
02 | 02-4H0504 | 4H0504 | 02-SHA-273-18.5/18.7 |  | ACNH-X089- (124)E | Tullis, Inc. | 16951 Clear Creek Road | Redding Ca 96001 | 5302415105 | 5306045102 | 1031 Butte St, Suite 205 | Redding, Ca 96001 | Alexander, Nathan | 0 | 1821504.35 | 137500 | 0 | 2025-11-20 | Place Rhma, Hma, Minor Concrete, And Repla | Shasta County In And Near Redding On Route273 From 0.5 Mile North Of Sulphur Creek Bridge To 0.2 Mile South Of Twin View Boulevard | 100 | 95 | 30451803.31 | 28458713 | 31489963.57 | 54945 | 2025-12-15 | 2023-12-13 | 2023-11-16 |  |  | 111 | 0 | 100 | 0 |  | X
02 | 02-1J2904 | 1J2904 | 02-SHA-299-88.1/89.5 |  | PTST-S299- (164)000 | Bugler Construction, Inc. | 4847 Hopyard Rd. Suite 4-395 | Pleasanton Ca 94588 | [5 empty] | 0 | 0 | 0 | 0 |  | Cable Net Attenuator, Roadway Excavation A | Shasta County Near Fall River Mills From 2.7 Miles West Of Fall River Golf Road To 1.2 Miles West Of Fall River Golf Road | 0 | 0 | 0 | 8944385 | 8944385 | 60259 |  | 2025-12-15 | 2025-11-04 |  |  | 0 | 0 | 120 | 0
02 | 02-1K4004 | 1K4004 | 02-SIS-0-/0 | 20.10 201352 |  | Robert J Frank Construction | 2806 Tarmac Rd | Redding Ca 96003 |  | 5303569242 | 13700 Highway 36 East | Red Bluff Ca 96080 | Higgins Kyle | 0 | 37648.71 | 0 | 0 | 2026-02-20 | Pavement Repairs | Security Measures At Maintenance Stations22 Maintenance Stations In District 2 Scope Of Work Includes Install Of Fencing Dir'S Eme | 100 | 48 | 1325284.27 | 17475 | 2785000 | 57073 | 2029-02-07 | 2025-02-25 | 2024-06-19 |  |  | 376 | 0 | 180 | 0
02 | 02-1H7104 | 1H7104 | 02-SIS-3-47.4/0 |  |  | Mccuen Construction, Inc. | 3269 Swetzer Road | Loomis Ca 95650 | 9166527824 | 5306055861 | 1745 S Main Street | Yreka Ca 96097 | Henry Austin | 55578.21 | 0 | 0 | 0 | 2026-02-20 | New Mechanic Shop At Yreka Maintenance Sta | Siskiyou County In Yreka On Route 3 At Yreka Maintenance Station And On Route 5 From 0.2 Mile South To 0.4 Mile North Of South Yre | 53 | 50 | 2788997.33 | 5477278.5 | 5584410.98 | 56747 | 2026-07-13 | 2024-12-04 | 2024-11-13 |  |  | 116 | 0 | 200 | 17 |  | X
02 | 02-0J8504 | 0J8504 | 02-SIS-89-20.3/34.6 |  | ACNH-P089- (126)000 | Tullis, Inc. | 16951 Clear Creek Road | Redding Ca 96001 | 5304104426 | 5306055861 | 1625 Mott Rd | Mt Shasta Ca 96067 | Henry Austin | 158652.4 | 0 | 0 | 0 | 2025-12-20 | Hma, Culverts, Guardrail, Fencing | Siskiyou County At And Near Mccloud From 0.8 Mile South Of Mud Creek Bridge To Route 5 | 0 | 1 | 158652.4 | 16381305 | 16381305 | 60036 | 2026-06-09 | 2025-08-26 | 2025-08-05 |  | S | 0 | 0 | 120 | 0 |  | X
02 | 02-4F90U4 | 4F90U4 | 02-SIS-96-41.0/41.8 |  |  | S.T. Rhoades Construction, Inc. | 8585 Commercial Way | Redding Ca 96002 | 5302239322 | 5303560630 | 1625 Mott Road | Mount Shsata Ca 96067 | Riddle Nicholas | 0 | 0 | 0 | 0 |  | Hma Pavement, Electrical, Landscaping And | Siskiyou County At And Near Happy Camp From Indian Creek Bridge To 0.2 Mile East Of Davis Road | 0 | 0 | 0 | 8877021.32 | 8877021.32 | 60165 |  | 2025-11-10 | 2025-10-21 |  | S | 0 | 0 | 450 | 0
02 | 02-1H5904 | 1H5904 | 02-SIS-96-43.5/58 |  | ACNH-P096- (064)E | J.F. Shea Construction, Inc. | 17400 Clear Creek Road | Redding Ca 96001 | 5302464292 | 5309497994 | 1625 Mott Road | Mount Shasta Ca 96067 | Riddle Nicholas | -78167.9 | 38177 | 0 | 0 | 2026-02-20 | Replace Culverts With Bridges, Streambed R | Siskiyou County At And Near Happy Camp At 0.8 Mile West Of Gordon'S Ferry Road And At Portuguese Creek | 98 | 92 | 10733079.71 | 11040419 | 11561678.24 | 52265 | 2028-01-21 | 2023-08-30 | 2023-08-07 |  | S | 314 | 0 | 320 | 0 |  | X
02 | 02-0K6404 | 0K6404 | 02-SIS-97-18.0/22.4 |  | ACNH-P097- (045)E | Mccuen Construction, Inc. | 1326 Swetzer Road | Loomis Ca 95650 | 9166527824 | 5306055861 | 1625 Mott Road | Mount Shasta Ca 96067 | Henry Austin | 171544.37 | 9845.1 | 0 | 0 | 2026-02-20 | Construct Wildlife Overpass, Install Culve | Siskiyou County Near Grass Lake From 1.4 Miles North Of Deer Mountain Road To 0.6 Mile North Of Grass Lake Rest Area | 97 | 92 | 13113849.97 | 13293018.19 | 14127393.19 | 57122 | 2026-02-24 | 2025-01-21 | 2024-12-31 |  | S | 145 | 0 | 120 | 29 |  | X
02 | 02-0J5504 | 0J5504 | 02-SIS-161-4.5/9.1 |  | ACST-S161- (003)000 | Rocky Mountain Construction, Llc | 4815 Tingley Lane #A | Klamath Falls Or 97603 | [5 empty] | 0 | 0 | 0 | 0 |  | Full Depth Recycling-Cement, Place Hma & R | Siskiyou County Near Dorris From 4.5 Mileseast Of Route 97 To 2.1 Miles West Of Fugate Road | 0 | 0 | 0 | 5912969 | 5912969 | 60258 |  | 2025-12-19 | 2025-11-20 |  |  | 0 | 0 | 55 | 0
02 | 02-0K0104 | 0K0104 | 02-TEH-5-5.6/42 |  |  | Central Striping Service, Inc. | 3489 Luyung Drive | Rancho Cordova Ca 95742 | 9166355175 | 5303569242 | 13700 Highway 36 East | Red Bluff Ca 96080 | Higgins Kyle | 0 | 14373.55 | 0 | 0 | 2025-06-17 | Roadside Sign - One Post, Thermoplastic St | Tehama County Near Corning At Various Locations From 0.2 Mile South Of Liberal Avenue Overcrossing To Cottonwood Creek Bridge Over | 100 | 100 | 687992.56 | 672170.77 | 684670.77 | 57008 | 2025-06-17 | 2024-08-30 | 2024-06-17 | 2026-02-02 |  | 30 | 0 | 30 | 0 |  | X
02 | 02-3J52U4 | 3J52U4 | 02-TEH-36-15.7/16.4 |  | HSNH-S036- (123)000 | J.F. Shea Construction, Inc. | 17400 Clear Creek Road | Redding Ca 96001 | [5 empty] | 0 | 0 | 0 | 0 |  | Place Hma And Replace Culverts And Fencing | Tehama County About 26 Miles West Of Red Bluff From 5.3 Miles East To 6.1 Miles East Of Dry Creek Bridge | 0 | 0 | 0 | 3468598 | 3468598 | 60408 |  | 2026-02-11 | 2026-01-12 |  |  | 0 | 0 | 85 | 0
02 | 02-1K9004 | 1K9004 | 02-TEH-36-618.0/.2 | 20XX 202130 |  | Jf Shea Construction Inc | Po Box 494519 | Redding Ca 96049 |  | 5307593778 | 2707 Notre Dame Blvd | Chico Ca 95926 | Farley Damion | 4000 | 9105.67 | 0 | 0 | 2026-01-12 | Pavement Repairs | D2 Park Fire Do Plu Sha Teh Butte Cntys Var Locations Traffic Contrl Remove Trees Replace Culverdir'S Emergency L.B. | 100 | 100 | 20670412.61 | 4000 | 23620000 | 56322 | 2026-01-12 | 2024-09-10 | 2024-07-30 | 2026-01-29 |  | 479 | 0 | 35 | 207 |  | X
02 | 02-0J0104 | 0J0104 | 02-TEH-99-4.2/4.8 |  | HSNH-P099- (685)E | Baldwin Contracting Company Inc. Dba Knife River Construction | 1764 Skyway | Chico Ca 95928 | 5308916555 | 5306045118 | 2600 Gateway Dr | Anderson Ca 96007 | Worden Edward | 88498.6 | 0 | 0 | 0 | 2026-01-20 | Place Hma, Cctv Tower And Install Lighting | Tehama County About 7.0 Miles South Of Losmolinos From 0.3 Mile South Of South Avenue To 0.6 Mile South Of Vina Road | 92 | 90 | 9255306.72 | 9805715.5 | 10203160.4 | 56661 | 2026-02-04 | 2024-08-07 | 2024-07-11 |  |  | 138 | 0 | 150 | 0 |  | X
02 | 02-3H7704 | 3H7704 | 02-TEH-99-/12.5 |  | ACNH-P099- (695)E | Desilva Gates Construction, Llc | 11555 Dublin Blvd. | Dublin Ca 94568 | [5 empty] | 0 | 0 | 0 | 0 |  | Place Hma, Install Culverts, Install Guard | Tehama County In And Near Los Molinos Frombutte County Line To Los Molinos Creek Bridge | 0 | 0 | 0 | 36477477 | 36477477 | 60169 |  | 2025-11-10 | 2025-10-24 |  |  | 0 | 0 | 160 | 0
02 | 02-3H70U4 | 3H70U4 | 02-TRI-299-15.0/25.7 |  | ACNH-P299- (217)E | J.F. Shea Construction, Inc. | 17400 Clear Creek Road | Redding Ca 96001 | 5302464292 | 5306045118 | 1031 Butte Street | Redding Ca 96001 | Worden Edward | 267222 | 0 | 0 | 0 | 2026-01-20 | Rhma-G, Hma (Type A), Cold Plane Ac, & Sol | Trinity County Near Del Loma From 1.0 Mileeast Of Trinity River Bridge No.05-0006 To0.1 Mile West Of Prairie Creek Road | 78 | 87 | 15359447.98 | 17226140 | 17502890.44 | 56312 | 2026-03-20 | 2024-09-03 | 2024-08-09 |  |  | 132 | 0 | 170 | 0 |  | X
02 | 02-0K6004 | 0K6004 | 02-VAR--/0 |  |  | Teichert Energy & Utilities Group, Inc. | 3500 American River Drive | Sacramento Ca 95864 | 9164388500 | 5306826584 | 703 B St | Marysville Ca 95901 | Granados Anthony | 0 | 1361.27 | 0 | 0 | 2025-11-20 | Construct Middle Mile Broadband Network | Humboldt, Mendocino, Lake, Trinity, Siskiyou, Modoc, Tehama, Shasta, Lassen, Plumas, Butte, Glenn, Sierra, Colusa, Nevada, Placer, | 0 | 77 | 69036.26 | 200 | 90000 | 54404 | 2026-12-31 | 2023-08-09 | 2023-08-09 |  |  | 0 | 0 | 1 | 0 |  | X
02 | 02-2J9704 | 2J9704 | 02-VAR--/0 |  |  | Mccuen Construction, Inc. 13700 Hwy 36 Red Bluff Ca 96080 | 3269 Swetzer Road | Loomis Ca 95650 |  | 5303569242 |  |  | Kyle Higgins | 551644.66 | 0 | 0 | 0 | 2025-11-20 | Bridge Polyester Concrete Overlay And Meth | Shasta County On Route 5 At Various Locations From Antler Undercrossing To Soda Creek Road Undercrossing And On Route89 At Various | 20 | 53 | 1666598.96 | 3143311.34 | 3092084.61 | 59815 | 2026-02-28 | 2025-03-13 | 2025-02-26 |  |  | 28 | 0 | 138 | 0 |  | X
02 | 02-3J3304 | 3J3304 | 02-VAR--/0 |  |  | Mccuen Construction, Inc. | 3269 Swetzer Road | Loomis Ca 95650 | 9166527824 | 5306045102 | 1031 Butte St 205 Ms 60 | Redding Ca 96001 | Alexander Nathan | 60070.04 | 0 | 0 | 0 | 2025-10-20 | Furnish And Place Polyester Concrete Overl | Shasta And Tehama Counties At Various Locations | 73 | 14 | 390126.79 | 2837770.9 | 2837770.9 | 58517 | 2025-11-20 | 2025-06-04 | 2025-05-13 |  |  | 40 | 0 | 55 | 0 |  | X
02 | 02-2K1104 | 2K1104 | 02-VAR--/0 | 20.XX 201130 |  | Jf Shea Construction Inc | 17400 Clear Creek Road | Redding Ca 96001 |  | 5306045102 | 1031 Butte St Suite 205 Ms 60 | Redding Ca 96001 | Alexander Nathan | 0 | 24685.08 | 0 | 0 | 2025-10-20 | Pavement Repairs | Cottonwood Creek Bridge Joint Replacement Var Cnty Near Cottonwood Creek Overhead Remove Replace Expansion Joints Dir'S Emergency | 4 | 9 | 155735.83 | 7136 | 1769000 | 57074 | 2025-12-31 | 2024-12-05 | 2024-10-21 |  |  | 4 | 0 | 112 | 0 |  | X
03 | 03-4H76U4 | 4H76U4 | 03-BUT-32-5.0/10.2 |  | HSNH-P032- (051)E | Baldwin Contracting Company Inc. Dba Knife River Construction | 1764 Skyway | Chino Ca 95928 |  |  | 2707 Notre Dame Blvd | Chico, Ca 95928 | Rechs, Daniel | 1118012.02 | 187074.6 | -215487.87 | 0 | 2026-02-20 | Rehabilitate Pavement, Install Signal, Lig | Butte County In Chico From Muir Avenue To Interchange Of State Routes 99 And 32 | 52 | 78 | 25234137.62 | 30772086 | 31834657.2 | 56089 | 2026-05-28 | 2024-07-10 | 2024-06-17 |  |  | 129 | 0 | 250 | 0 |  | X
03 | 03-3G3804 | 3G3804 | 03-BUT-32-23.9/30.8 |  |  | Lamon Construction Co., Inc. | 871 Von Geldern Way | Yuba City Ca 95991 |  | 5307137814 | 2707 Notre Dame Blvd | Chico, Ca 95928 | Grandy, Dwayne | 433634.29 | 0 | 0 | 0 | 2025-12-20 | Hma Overlay, Cold Plane, And Remove & Repl | Butte County Near Chico From Nopel Avenue To 1.3 Miles West Of Carpenter Ridge Road And From 1.1 Miles West Of Carpenter Ridgeroad | 100 | 95 | 4013747.08 | 3839193.95 | 3839193.95 | 58617 | 2025-12-19 | 2025-06-09 | 2025-05-27 |  |  | 45 | 0 | 45 | 0 |  | X
03 | 03-3G0704 | 3G0704 | 03-BUT-32-31.5/37.8 |  |  | Lamon Construction Co., Inc. | 871 Von Geldern Way | Yuba City Ca 95991 | 5303926008 | 5306737814 | 2707 Notre Dame Blvd | Chico, Ca 95928 | Dwayne Grandy | 33845.2 | 0 | 0 | 0 | 2025-12-20 | Cold Plane And Place Hma. | Butte County From 1.6 Miles North Of 120G/Platt Mountain Road To Tehama County Line | 89 | 97 | 1910447.14 | 1951572.9 | 1981317.6 | 58716 | 2020-12-29 | 2024-07-17 | 2024-06-25 |  |  | 40 | 0 | 45 | 0 |  | X
03 | 03-1N5504 | 1N5504 | 03-BUT-70-350.0/36 | 20.XX 201130 |  | Steelhead Constructors Jv | P.O. Box 536 | Palo Cedro, Ca 96073 |  | 5309540879 | 2707 Notre Dame Blvd | Chico, Ca 95928 | Makhoul, Husam | 0 | 245133.04 | 0 | 0 | 2026-02-20 | But 70 Viaduct | Mobilization, Excavation, Backfill, Haul Away Slide Material, Construct Viaduct/Structure Type Selection Dir'S Emergency L.B. | 76 | 80 | 5590852.24 | 35663 | 7000000 | 57897 | 2026-05-01 | 2025-03-03 | 2025-02-03 |  |  | 151 | 0 | 200 | 0 |  | X
03 | 03-1H1404 | 1H1404 | 03-BUT-99-3.1/5 |  | ACNH-P099- (690)E | Martin Brothers Construction | 8801 Folsom Boulevard Ste 260 | Sacramento Ca 95826 |  | 5303206457 | 2704 Notre Dame Blvd | Chico, Ca 95928 | Watts, Dustin | 492738.13 | 128325.54 | 0 | 56500 | 2026-02-20 | Rhma, Hma, Lighting Systems, Curb Ramps, S | Butte County In And Near Gridley From Hollis Lane To 0.2 Mile North Of Ford Avenue | 19 | 56 | 10591082.82 | 18182285 | 18781805.65 | 57125 | 2027-04-30 | 2025-02-10 | 2025-01-08 |  |  | 68 | 0 | 365 | 0 |  | X
03 | 03-0J4404 | 0J4404 | 03-BUT-162-15.6/18.5 |  | ACNH-P162- (045)E | A. Teichert & Son, Inc. Dba Teichert Construction | 3500 American River Dr | Sacramento Ca 95864 | [5 empty] | 0 | 0 | 0 | 0 |  | Cold Plane Ac Pvmt, Hma, Minor Concrete, S | Butte County In Oroville From Feather River Bridge To Foothill Boulevard | 0 | 0 | 0 | 21501560 | 21501560 | 60345 |  | 2026-01-21 | 2025-12-31 |  |  | 0 | 0 | 140 | 0
03 | 03-0J4604 | 0J4604 | 03-COL-5-24.3/0 |  | CIMG-0057- (101)E | Lamon Construction Co., Inc. | 871 Von Geldern Way | Yuba City Ca 95991 | [5 empty] | 0 | 0 | 0 | 0 |  | Building Work, Minor Concrete, & Concrete | Colusa County Near Maxwell At The Maxwell Safety Roadside Rest Area | 0 | 0 | 0 | 11028353.75 | 11028353.75 | 60428 |  | 2026-02-18 | 2025-12-17 |  |  | 0 | 0 | 475 | 0
03 | 03-3G5304 | 3G5304 | 03-ED-49-16.5/20.1 |  |  | Martin Brothers Construction | 8801 Folsom Boulevard Ste 260 | Sacramento Ca 95826 |  | 5305653834 | 3461 Robin Ln. Suite #4 | Cameron Park, Ca 95682 | Thompson, Brian | 104161.25 | 0 | 0 | 0 | 2025-11-20 | Install Cured-In-Place Pipeliners And Repl | El Dorado County Near Placerville At Various Locations From 0.2 Mile North Of Diana Street To 0.5 Mile North Of Woodridge Road | 11 | 77 | 585564.75 | 759881.57 | 759881.57 | 59826 | 2025-12-31 | 2025-07-14 | 2025-06-06 |  |  | 5 | 0 | 45 | 0 |  | X
03 | 03-3G5204 | 3G5204 | 03-ED-49-23.6/25.2 |  |  | Lamassu Utility Services, Inc. | 3193 Enterprise Court | Loomis Ca 95650 | 9162591576 | 5305653834 | 3461 Robin Ln. Suite #4, | Cameron Park, Ca 95682 | Thompson, Brian | 34664.13 | 0 | 0 | 0 | 2025-10-20 | Cipp And Rcp. | El Dorado County Near Coloma At Various Locations From 0.4 Mile South Of South Fork American River Bridge To 0.1 Mile North Of Del | 6 | 6 | 34664.13 | 610479.91 | 610479.91 | 59825 | 2025-12-31 | 2025-06-26 | 2025-06-03 |  |  | 2 | 0 | 35 | 0 |  | X
03 | 03-1J1604 | 1J1604 | 03-ED-50-35.1/0 |  | ACNH-P050- (158)000 | George Reed, Inc. | 1200 Scenic Drive, Suite 200 | Modesto Ca 95350 | [5 empty] | 0 | 0 | 0 | 0 |  | Hma (Type A), Cold Plane Ac Pvmt, And Drai | El Dorado County Near Pollock Pines At 0.1Mile West Of Peavine Ridge Road And From 0.1 Mile West Of Ice House Road To 0.5 Mile Eas | 0 | 0 | 0 | 21267483 | 21267483 | 60373 |  | 2026-01-26 | 2025-12-31 |  |  | 0 | 0 | 280 | 0
03 | 03-4H8904 | 4H8904 | 03-ED-50-75.4/8 |  | HSNH-P050- (157)E | St. Francis Electric Llc | 975 Carden St | San Leandro Ca 94577 |  | 5309571110 | 3976 Durock Road, Suite 102 | Shingle Springs, Ca 95682 | Alterton, Nathan | 0 | 0 | 0 | 0 | 2025-08-20 | Modify Lighting And Fiber Optic Cable Syst | El Dorado County In South Lake Tahoe From North Junction Route 89 To Pioneer Trail | 60 | 65 | 13747407.68 | 21097000 | 21277175.29 | 55772 | 2025-09-08 | 2024-04-19 | 2024-03-28 |  |  | 126 | 0 | 210 | 0 |  | X
03 | 03-2N0704 | 2N0704 | 03-ED-50-180.0/18 |  |  | Doug Veerkamp General Engineering, Inc. | 3701 Trade Way | Cameron Park, Ca 95682 |  | 5309571110 | 3461Robin Ln Suite #4, Cameron Park, Ca 95682 |  | Alterton, Nathan | 0 | 37099.47 | 0 | 0 | 2025-12-20 | Roadway Dip | Site Preparation Traffic Control Sawcut Excavation Slurry Backfill Minor Hma Paving Striping And Incidental Work Dir'S Emergency F | 38 | 83 | 400903.14 | 4300 | 485000 | 58995 | 2025-06-26 | 2025-06-18 | 2025-06-07 |  |  | 15 | 0 | 40 | 0 |  | X
03 | 03-1N1804 | 1N1804 | 03-ED-50-189.0/18.9 | 20.XX 201130 |  | Doug Veerkamp General Engineering, Inc. | 3701 Trade Way | Cameron Park, Ca 95682 |  | 5305653834 | 3976 Durock Road, Ste. 102 | Shingle Springs, Ca 95682 | Thompson, Brian | 0 | 95315.51 | 0 | 0 | 2026-01-20 | Retaining Wall | In Placer County At 3065 Blairs Ln, Placerville, Ca 95667 At The Caltrans Placerville Maintenance Station Dir'S Emergency F.A. | 28 | 76 | 339033.86 | 2973 | 446000 | 56079 | 2026-02-18 | 2024-06-20 | 2024-05-30 |  |  | 25 | 0 | 90 | 0 |  | X
03 | 03-0N6504 | 0N6504 | 03-ED-50-672.0/67.2 | 20.XX 201130 |  | Neil'S Controlled Blasting Lp | P.O. Box 749 | Newcastle, Ca 95658 |  | 5309571110 | 3976 Durock Road, Suite 102 | Shingle Spring Ca 95682 | Alterton, Nathan | 0 | 60437.66 | 0 | 0 | 2025-11-20 | Ed 50 Rockfall - Slope Stabilization | Mobilization, Rockfall Mitigation, Slope Stabilization, Debris Removal, Traffic Control, And Incidental Work. Dir'S Emergency F.A. | 17 | 30 | 238792.5 | 5775 | 785000 | 55324 | 2026-04-23 | 2024-04-15 | 2023-12-21 |  |  | 10 | 0 | 60 | 0 |  | X
03 | 03-3G8104 | 3G8104 | 03-ED-89-81.0/8.1 |  |  | Acco Engineered Systems, Inc. | 888 E. Walnut Street | Pasadena, Ca 91101 |  | 5308126239 | 3461 Robin Ln Ste 4 | Cameron Park, Ca 95682 | Lopez, Andrew | 0 | 0 | 0 | 0 |  | South Lake Tahoe Mtce Station Rehab | Mobilization, Repair/Replace Residence Roof, Siding/Windows, Structural And Incidental Work Dir'S Emergency F.A. | 0 | 0 | 0 | 3825 | 985000 | 60100 | 2025-11-18 | 2025-11-20 | 2025-03-20 |  |  | 0 | 0 | 30 | 0
03 | 03-3G4304 | 3G4304 | 03-ED-89-/8.5 |  |  | All-American Construction, Inc. | 1700 Acacia Avenue | Sutter Ca 95982 | [5 empty] | 0 | 0 | 0 | 0 |  | Cold Plane Ac Pvmt And Hma (Type A) Overla | El Dorado County Near Meyers From Alpine County Line To Pomo Street | 0 | 0 | 0 | 3959843.26 | 3959843.26 | 59279 |  | 2025-07-01 | 2025-06-06 |  |  | 0 | 0 | 45 | 0
03 | 03-2G9804 | 2G9804 | 03-ED-193-2.0/8.9 |  |  | Doug Veerkamp General Engineering, Inc. | 2585 Cold Springs Rd | Placerville Ca 95667 | 5306760825 | 5305653834 | 3461 Robin Ln. Suite #4, | Cameron Park, Ca 95682 | Thompson, Brian | 112396.35 | 0 | 0 | 0 | 2025-10-20 | Replace Culverts. | El Dorado County At Various Locations Fromcramer Road To 0.2 Mile East Of Weed Patchcourt | 42 | 79 | 507068.35 | 637367.4 | 637367.4 | 59827 | 2025-12-31 | 2025-06-19 | 2025-05-29 |  |  | 19 | 0 | 45 | 0 |  | X
03 | 03-2G9304 | 2G9304 | 03-ED-193-3.5/5.6 |  |  | Robert J. Frank Construction, Inc. | 2806 Tarmac Road | Redding Ca 96003 | 5302221408 | 5305653834 | 3976 Durock Rd | Shingle Springs, Ca 95682 | Thompson, Brian | 135130 | 0 | 0 | 0 | 2025-10-20 | Install Cured-In-Place Pipeliner & Concret | El Dorado County Near Greenwood At Variouslocations From 0.3 Mile North Of Brush N Rocks Lane To 0.2 Mile South Of Pilgrim Court | 63 | 89 | 335710 | 375823 | 375823 | 59855 | 2025-12-31 | 2024-07-31 | 2024-06-28 |  | S | 19 | 0 | 30 | 0 |  | X
03 | 03-2G9704 | 2G9704 | 03-ED-193-11.9/17.3 |  |  | Wylatti Resource Management, Inc. | 23601 Cemetery Lane | Covelo Ca 95428 |  | 5305653834 | 3461 Robin Ln. Suite #4 | Cameron Park, Ca 95682 | Thompson, Brian | 313724.51 | 0 | 0 | 0 | 2025-11-20 | Replace Culverts. | El Dorado County Near Georgetown At Various Locations From 0.1 Mile West Of Spanish Dry Diggins Road To 0.5 Mile West Of Traverse | 28 | 94 | 1021933.63 | 1081125.47 | 1081125.47 | 58216 | 2025-12-31 | 2025-05-19 | 2025-04-29 |  |  | 22 | 0 | 80 | 0 |  | X
03 | 03-2N4704 | 2N4704 | 03-ED-193-88.0/8.8 | 20.XX 201130 |  | Doug Veerkamp General Engineering, Inc. | 3701 Trade Way | Cameron Park, Ca 95682 |  | 5309571110 | 3461 Robin Ln. | Cameron Park, Ca 95682 | Alterton, Nathan | 0 | 0 | 0 | 0 |  | Replace Culverts | In El Dorado County Along State Route 193 Approximately 1.607 Miles East Of Ricci Road, Rt Dir'S Emergency F.A. | 0 | 0 | 0 | 5025 | 885000 | 60363 | 2026-04-01 | 2025-11-05 | 2025-10-26 |  |  | 0 | 0 | 90 | 0
03 | 03-2J5904 | 2J5904 | 03-GLE-32-2.8/3.2 |  | SNHG-P032- (052)E | Studebaker Electric, Inc. | 3237 Rippey Road, Ste 100 | Loomis Ca 95650 | 9162592395 | 5309540879 | 2707 Notre Dame Blvd | Chico, Ca 95928 | Makhoul, Husam | 67962.6 | 0 | 0 | 0 | 2025-12-20 | Install Traffic Signal. | Glenn County Near Orland From 0.2 Mile West To 0.2 Mile East Of County Road P | 85 | 91 | 1429566.6 | 1587834.6 | 1571734.6 | 57127 | 2025-12-26 | 2025-01-21 | 2024-12-23 |  |  | 51 | 0 | 60 | 0 |  | X
03 | 03-3J4324 | 3J4324 | 03-GLE-162-65.5/69.7 |  |  | Teichert Energy & Utilities Group, Inc. | 3500 American River Drive | Sacramento Ca 95864 | 9164388537 | 5309540879 | 2707 Notre Dame Blvd | Chico Ca 95928 | Makhoul, Husam | 27884.25 | 0 | 0 | 0 | 2026-01-20 | Middle-Mile Broadband Network | Glenn County In And Near Willows From Route 162/5 Separation To County Road P | 100 | 82 | 3116816.95 | 3650384.17 | 3657031.3 | 56908 | 2025-09-02 | 2024-11-19 | 2024-09-23 |  |  | 58 | 0 | 58 | 0
03 | 03-3F0604 | 3F0604 | 03-GLE-162-76.3/78.6 |  | ACST-P162- (041)E | Golden State Bridge, Inc. | 3701 Mallard Drive | Benicia Ca 94510 | 9253728000 | 5303206457 | 2707 Notre Dame Blvd | Chico, Ca 95928 | Watts, Dustin | 537340.02 | 14097.15 | 0 | 0 | 2026-02-20 | Replace Sacramento River Bridge | At Butte City, From Route 45 To 0.1 Mile East Of Mcdougall Street. | 88 | 98 | 83347113.93 | 70777777.47 | 85294233.13 | 42077 | 2027-01-22 | 2022-02-02 | 2022-01-07 |  |  | 377 | 0 | 430 | 0 |  | X
03 | 03-3H51U4 | 3H51U4 | 03-NEV-49-10.3/13.8 |  | HSNH-P049- (193)E | Granite Construction Company | 4001 Bradshaw Road | Sacramento Ca 95827 |  | 5302659864 | 138 New Mohawk Rd, Ste B | Nevada City, Ca 95959 | Plaza, Renee | 71143.3 | 0 | 0 | 0 | 2026-02-20 | Rdwy Excavation, Place Hma, Trenchless Cul | Nevada County Near Grass Valley From 0.2 Mile South Of La Barr Meadows Road To 0.1 Mile North Of South Grass Valley Overcrossing | 0 | 0 | 71143.3 | 65928657.2 | 66083657.2 | 60409 | 2027-09-20 | 2026-02-10 | 2025-12-29 |  |  | 1 | 0 | 500 | 0 |  | X
03 | 03-3G7404 | 3G7404 | 03-NEV-80-156.0/15.6 | 20.80 521000 |  | Acco Engineered Systems, Inc. | 888 East Walnut Street | Pasadena, Ca 91101 |  | 5308213938 | 10183 Truckee Airport Rd., Suite 202, | Truckee, Ca 96161 | Hobbs, Douglas | 0 | 76541.03 | 0 | 0 | 2026-02-20 | Truckee Boiler Replacement | In Nevada County Near Interstate 80 At Thecaltrans Truckee Maintenance Station Locatat 10152 Keiser Avenue, Truckee, Ca 96161 Dir' | 75 | 91 | 698777.56 | 3103 | 765000 | 60122 | 2026-03-01 | 2025-06-13 | 2025-02-18 |  |  | 15 | 0 | 20 | 0 |  | X
03 | 03-2N4304 | 2N4304 | 03-NEV-80-247.0/30.2 |  |  | Neil'S Controlled Blasting Lp | 490 Main Street/P.O. Box 749 | Newcastle, Ca 95658 |  | 5302655736 | 12453 Willow Valley Road | Nevada City, Ca 95959 | Hobbs, Doug | 0 | 339041.36 | 0 | 0 | 2026-02-20 | Nev 80 Landslides | In Nevada County Along Interstate 80 Approximately 1.221 Miles East Hinton Rd Uc 17 60 To Approximately 0.627 Miles Eastdir'S Emer | 87 | 13 | 2840819 | 28598 | 22585000 | 60175 | 2026-07-30 | 2025-12-04 | 2025-10-14 |  |  | 87 | 0 | 100 | 0
03 | 03-3J3604 | 3J3604 | 03-NEV-89-5.3/8.7 |  |  | Teichert Energy & Utilities Group, Inc. | 3500 American River Drive | Sacramento Ca 95864 | 9166454874 | 6616236769 | 10183 Truckee Airport Rd. | Truckee Ca 96161 | Shawn Hagstrom | 0 | 13750 | 0 | 0 | 2026-01-20 | Construct Middle Mile Broadband Network | Nevada And Sierra Counties From Route 80/89 Separation In Truckee To Plumas County Line About 6 Miles North Of Calpine | 52 | 50 | 17327533.16 | 33746241.75 | 34007341.01 | 57675 | 2026-11-10 | 2025-03-06 | 2025-02-21 |  |  | 115 | 0 | 220 | 0 |  | X
03 | 03-0J01U4 | 0J01U4 | 03-PLA-28-.1/11 |  | CSTP-P028- (012)E | Mercer Fraser Company | 200 Dinsmore Dr | Fortuna Ca 95540 |  | 5302181752 | 10183 Truckee Airport Rd. Ste | 202, Truckee, Ca 96161 | Salehi, Reza | 67380 | 0 | 0 | 0 | 2026-02-20 | Hma (Type A), Cold Plane Ac Pvmt, Rdwy Exc | Placer County From 0.1 Mile East Of Route 89 At Tahoe City To The Nevada State Line At Kings Beach | 14 | 30 | 6796635.1 | 22645645 | 22978913.64 | 57379 | 2026-04-22 | 2024-12-03 | 2024-10-02 |  |  | 31 | 0 | 220 | 0 |  | X
03 | 03-1H2404 | 1H2404 | 03-PLA-49-2.2/2.4 |  | SNHG-P049- (186)E | Lamon Construction | 871 Von Geldern Way | Yuba City Ca 95991 | 5308452282 | 9168256388 | 33 Depot St Po Box 1807 | Colfax Ca, 95713 | Clark, Martin | 0 | 764301.45 | 0 | 0 | 2026-01-20 | Realign Roadway And Construct | In Placer County In Auburn From 0.1 Mile South Of The Intersection Of Route 49 And Lincoln Way / Borland Avenue To Lincoln Way | 95 | 100 | 7505105.85 | 5200075 | 7409673.97 | 42764 | 2026-02-18 | 2022-06-29 | 2022-05-27 | 2026-02-10 |  | 340 | 0 | 130 | 229 |  | X
03 | 03-3H8304 | 3H8304 | 03-PLA-49-3.5/7.5 |  | PCML-6203- (071)E | Pacific Infrastructure Construction, Llc | 871 Cotting Court Ste A | Vacaville Ca 95688 | 7074493604 | 5307908595 | 138 New Mohawk Rd Suite B | Nevada City, Ca 95959 | Price, Lucas | 146200 | 15159.2 | 0 | 0 | 2026-02-20 | Construct Sidewalks, Curb Ramps And Draina | Placer County In And Near Auburn From 0.3 Mile North Of Route 80/49 Separation To 0.1 Mile North Of Dry Creek Road | 58 | 67 | 6704217.34 | 9784573.9 | 9985597.65 | 57126 | 2026-07-03 | 2025-01-29 | 2025-01-06 |  | S | 115 | 0 | 200 | 0 |  | X
03 | 03-3F23U4 | 3F23U4 | 03-PLA-80-.1/2.2 |  | ACIM-0803- (252)E | Ghilotti Construction Company,Inc. | 246 Ghilotti Avenue | Santa Rosa Ca 95407 | 7075851221 | 9168256388 | 33 Depot St. Po Box 1807 | Colfax Ca 95713 | Clark, Martin | 1260 | 7330.7 | 2500 | 0 | 2026-02-20 | Roadway Excavation, Place C12-Ab, Hma, Str | Placer County In Roseville From 0.1 Mile West Of Riverside Avenue Overcrossing To 0.3 Mile East Of Douglas Boulevard Overcrossing | 100 | 98 | 38699913.53 | 36651367.56 | 38591170.77 | 51165 | 2026-06-02 | 2023-06-16 | 2023-05-25 |  |  | 242 | 0 | 240 | 0 |  | X
03 | 03-0J4104 | 0J4104 | 03-PLA-80-33.0/44.9 |  | ACIM-0804- (339)E | A. Teichert & Son, Inc. Dba Teichert Construction | 3500 American River Dr | Sacramento Ca 95864 | [5 empty] | 0 | 0 | 0 | 0 |  | Cold Plane Ac Pvmt, Hma, Class 2 Ab, Rdwy | Placer County In And Near Colfax From 0.1 Mile West Of Route 174/80 Separation To 0.1 Mile East Of Alta Road Undercrossing | 0 | 0 | 0 | 20038550 | 20038550 | 60276 |  | 2025-12-30 | 2025-12-05 |  |  | 0 | 0 | 170 | 0
03 | 03-3H6104 | 3H6104 | 03-PLA-80-42.7/49.3 |  | ACIM-0804- (336)E | Desilva Gates Construction Llc | 11555 Dublin Blvd. | Dublin Ca 94568 | 9253611533 | 9167994858 | Po Box 1807 | Colfax, Ca 95713 | Sampson, Tad | 605191.49 | 699531.84 | 0 | 0 | 2026-02-20 | Rdwy Exc, Hma, Jpcp, Alt Pipeliner, Steel | Placer County About 9.4 Miles North Of Colfax From 0.5 Mile West Of Monte Vista Overcrossing To 0.3 Mile East Of Drum Forebay Over | 21 | 62 | 78766722.77 | 121121121 | 126492466 | 55404 | 2026-12-31 | 2024-03-01 | 2024-02-15 |  | S | 123 | 0 | 590 | 1 |  | X
03 | 03-0J5604 | 0J5604 | 03-PLA-80-49.3/68.7 |  | PTIM-0804- (338)E | Mercer-Fraser Company | 200 Dinsmore Dr | Fortuna Ca 95540 | 7074436371 | 9167994858 | 33 Depot Street, Po Box 1807 | Colfax Ca 95713 | Sampson, Tad | 107503.2 | 0 | 0 | 0 | 2026-02-20 | Rcp, Wsp, And Electrical Systems. | Placer And Nevada Counties From 0.3 Mile East Of Drum Forebay Overcrossing To 0.2 Mile East Of Troy Undercrossing | 5 | 7 | 1113787.56 | 15654240.33 | 15714240.33 | 59835 | 2026-09-21 | 2025-08-20 | 2025-07-11 |  | S | 7 | 0 | 155 | 0 |  | X
03 | 03-0J5504 | 0J5504 | 03-PLA-80-50.7/0 |  |  | Mccuen Construction, Inc. | 3269 Swetzer Road | Loomis Ca 95650 | 9166527824 | 5308218470 | 45 Central St | Colfax Ca 95713 | Anderson, Carl | 0 | 0 | 0 | 0 | 2026-02-20 | Building Work, Jpcp, And Camera Systems. | Placer County Near Blue Canyon At The Whitmore Maintenance Station At 7748 Whitmore Road | 0 | 0 | 0 | 12246357.4 | 12246357.4 | 60402 | 2027-02-04 | 2026-02-10 | 2026-01-08 |  |  | 1 | 0 | 240 | 0 |  | X
03 | 03-1H9904 | 1H9904 | 03-PLA-80-68.3/69.7 |  | ACIM-0804- (337)E | A. Teichert & Son Inc Dba Teichert Construction | 3500 American River Dr | Sacramento Ca 95864 | 9164843011 | 9168256388 | 33 Depot St | Colfax, Ca 95713 | Clark, Martin | 9211.78 | 21011.33 | 19315 | 0 | 2026-02-20 | Rdwy Exc, Place Hma & Jpcp, Slab Replaceme | Placer And Nevada Counties Near Kingvale From 0.3 Mile West Of Troy Undercrossing To 0.2 Mile East Of Soda Springs Overcrossing | 88 | 95 | 70787676.47 | 68586826 | 73777199.28 | 54867 | 2026-03-20 | 2023-12-21 | 2023-11-07 |  | S | 150 | 0 | 170 | 0 |  | X
03 | 03-1J1704 | 1J1704 | 03-PLA-89-13.0/21.6 |  | ACST-S089- (035)E | A. Teichert & Son, Inc. Dba Teichert Construction | 3500 American River Dr | Sacramento Ca 95864 | [5 empty] | 0 | 0 | 0 | 0 |  | Hma, Camera System, And Traffic Stripe. | Placer And Nevada Counties In And Near Truckee On Route 89 From 0.8 Mile North Ofalpine Meadows Road To Nevada County And From Pla | 0 | 0 | 0 | 12378062 | 12378062 | 60240 |  | 2025-12-10 | 2025-11-12 |  |  | 0 | 0 | 115 | 0
03 | 03-4F6404 | 4F6404 | 03-SAC-5-.2/34.3 |  | SNHG-X067- (080)E | Dreambuilder | 18543 Yorba Linda Blvd # 376 | Yorba Linda Ca 92886 | 7146463697 | 9169521149 | 2777 Del Monte Street | West Sacramento, Ca 95691 | Olguin, Jorge | 202027.55 | 22643.75 | 0 | 0 | 2019-11-20 | Upgrade Metal Beam Guard Rail And | In Sacramento County On Routes 5, 80 And 99 At Various Locations | 100 | 87 | 2313487.22 | 2589061 | 2647135.34 | 40268 | 2019-11-22 | 2019-05-21 | 2019-04-19 |  | S | 92 | 0 | 55 | 0 |  | X
03 | 03-0N8504 | 0N8504 | 03-SAC-5-16.2/0 |  |  | Martin Brothers Construction | 8801 Folsom Boulevard Ste 260 | Sacramento Ca 95826 | [5 empty] | 0 | 0 | 0 | 0 |  | Minor Conc, Cl 2 Ab, Hma, And Modifying Li | Sacramento County In Sacramento At Pocket Road Overcrossing | 0 | 0 | 0 | 1067000 | 1067000 | 59457 |  | 2025-07-22 | 2025-06-19 |  |  | 0 | 0 | 45 | 0
03 | 03-2H1304 | 2H1304 | 03-SAC-5-22.4/22.9 |  | ACIM-0056- (359)E | Wabo Landscape & Construction, Inc. | 726 Alfred Nobel Dr. | Hercules Ca 94547 | 5107419226 | 9167992649 | 3855 N Freeway Blvd Suite 120 | Sacramento, Ca 95834 | Chander, Rakesh | 1620 | 0 | 0 | 0 | 2026-02-20 | Highway Planting Rehabilitation. | In The City Of Sacramento, From South Of Broadway To 0.12 Mile South Of R Street. | 92 | 92 | 1383865.31 | 1685711.5 | 1485873.91 | 44505 | 2026-12-31 | 2022-08-19 | 2022-07-19 |  |  | 144 | 0 | 150 | 7 |  | X
03 | 03-3J5334 | 3J5334 | 03-SAC-5-26.7/29 |  |  | Teichert Energy & Utilities Group, Inc. | 3500 American River Drive | Sacramento Ca 95864 | 9164388500 | 5306496925 | 2777 Del Monte St | West Sacramento Ca 95691 | Ephrem Teweldeberhan | 213510.87 | 11131.5 | 0 | 0 | 2025-07-20 | Middle-Mile Broadband Network | Sacramento County In And Near Sacramento On Route 80 From Sacramento River Bridge And Overhead (Bryte Bend) To Route 5 And On Rout | 85 | 100 | 4088263.74 | 4111816.52 | 4122948.02 | 57296 | 2025-05-30 | 2025-01-29 | 2024-12-20 |  |  | 55 | 0 | 65 | 0 |  | X
03 | 03-3J3304 | 3J3304 | 03-SAC-12-/.5 | 20.20201131 |  | Golden State Bridge, Inc. | 3701 Mallard Drive | Benicia, Ca 95510 |  | 5306496925 | 2777 Del Monte St | West Sacramento, Ca 95691 | Teweldeberhan, Ephrem | 0 | 410456.64 | 0 | 0 | 2026-02-20 | Rio Vista Bridge | The Rio Vista Bridge (Br # 23-0024) State Route 12, Near Postmile 0 To 0.5 In Sacramento County | 100 | 78 | 21232907.08 | 72724 | 27200000 | 45264 | 2023-08-25 | 2022-11-09 | 2022-09-26 |  |  | 794 | 0 | 180 | 0
03 | 03-0H08U4 | 0H08U4 | 03-SAC-50-.2/6.1 |  |  | Flatiron Dragados West Llc | 1200 Concord Ave, Suite 250 | Concord, Ca 94520 | 7077426000 | 5306497022 | 2520 Warren Drive Suite A | Rocklin Ca 95677 | Ruzic, John | 375100 | 0 | 249750 | 0 | 2026-02-20 | Add High Occupancy Vehicle Lane And | In Sacramento County On Route 50 From I-5 Junction To Watt Ave. | 87 | 98 | 449185840.21 | 387675001 | 456736880.5 | 41166 | 2026-10-14 | 2020-06-30 | 2020-04-29 |  |  | 1065 | 0 | 925 | 304 |  | X
03 | 03-1N7904 | 1N7904 | 03-SAC-50-21.0/2.1 | 20.XX 201130 |  | Acco Engineered Systems, Inc. | 888 East Walnut Street | Pasadena, Ca 91101 |  | 5309540113 | 5900 Folsom Blvd | Sacramento, Ca 95819 | Angel Zaragoza, Gustavo | 0 | 837211.79 | 0 | 0 | 2026-01-20 | Asbestos Abatement | Mobilization, Cleaning And Decontaminationasbestos And Other Hazardous Materials Abareplacement, Duct Removal, Repair Other Dadir' | 1 | 28 | 2242910.27 | 22785 | 7985000 | 59836 | 2026-08-30 | 2025-06-16 | 2025-03-03 |  |  | 1 | 0 | 90 | 0 |  | X
03 | 03-0N6204 | 0N6204 | 03-SAC-50-21.0/2.1 |  |  | Acco Engineered Systems, Inc. | 888 E Walnut St. | Pasadena, Ca 91101 |  | 5309540113 | 5900 Folsom Blvd | Sacramento, Ca 95819 | Zaragoza, Gustavo | 0 | 351468.14 | 0 | 0 | 2025-10-20 | Translab Hvac System Repairs | In Sacramento County At 5900 Folsom Blvd. Sacramento, Ca, 95819. Dir'S Emergency F.A. | 79 | 5 | 1735660.99 | 38045 | 35985000 | 56274 | 2026-06-30 | 2024-08-28 | 2024-01-29 |  |  | 198 | 0 | 250 | 0
03 | 03-3F0704 | 3F0704 | 03-SAC-51-.2/3.5 | HA21 | ACNH-P051- (039)E | American River Constructors A Joint Venture | P.O. Box 50085 | Watsonville Ca 95077 | 9168554400 | 5306497022 | 1610 Arden Way Ste 277 | Sacramento Ca 95815 | John Ruzic | 1732702.69 | 782693 | 0 | 0 | 2026-02-20 | Deck Replacement | Sacramento County In Sacramento From 0.4 Mile South Of Elvas Underpass To 0.1 Mile North Of Exposition Boulevard | 64 | 90 | 121102810.81 | 131049478.34 | 133231134.39 | 52724 | 2026-08-24 | 2023-08-28 | 2023-08-28 |  |  | 576 | 0 | 900 | 0 |  | X
03 | 03-3F0734 | 3F0734 | 03-SAC-51-2.0/3.3 |  |  | American River Constructors A Joint Venture | Po Box 50085 | Watsonville Ca 95077 | 5306932155 | 9167683597 | 3855 N. Freeway Blvd #120 | Sacramento, Ca 95834 | Dean Elghassein | 0 | 65363.21 | 0 | 0 | 2026-02-20 | Dredge, Construct In-Water Foundation. | Sacramento County In Sacramento From 0.4 Mile South Of Elvas Underpass To 0.1 Mile North Of Exposition Boulevard | 91 | 98 | 55016019.5 | 50137078.3 | 55856529.75 | 43464 | 2027-02-28 | 2022-06-28 | 2022-06-28 |  |  | 246 | 0 | 270 | 0 |  | X
03 | 03-1J6304 | 1J6304 | 03-SAC-99-6.1/7 |  | ACNH-P099- (696)000 | Granite Construction Company | 4001 Bradshaw Road | Sacramento Ca 95827 | [5 empty] | 0 | 0 | 0 | 0 |  | Structural Concrete, Steel Girder, And Hma | Sacramento County Near Elk Grove From 0.2 Mile North Of Arno Road To 0.4 Mile South Of Dillard Road | 0 | 0 | 0 | 9747880.83 | 9779304.25 | 60261 |  | 2025-12-15 | 2025-11-06 |  |  | 0 | 0 | 135 | 0
03 | 03-2N4604 | 2N4604 | 03-SAC-160-25.0/2.5 | 20.XX 201130 |  | Rhino Engineering Inc. | Po Box 4315 | Eldorado Hills, Ca 95762 |  | 5306823842 | 2777 Del Monte St | West Sacramento, Ca 95691 | Griffith, Garrett | 0 | 0 | 0 | 0 |  | Sac 160 Sinkhole | Mobilization, Remove Failed Cmp Culvert And Replace With Rxp Culvert, Excavation, Backfill, Water Diversion, Shoring Dir'S Emergen | 0 | 0 | 0 | 27000 | 900000 | 60314 | 2025-11-12 | 2026-02-02 | 2025-11-03 |  |  | 0 | 0 | 30 | 0
03 | 03-3J9004 | 3J9004 | 03-SAC-160-44.9/0 |  | HSNH-P160- (027)000 | Pacific Infrastructure Construction, Llc | 871 Cotting Court Ste A | Vacaville Ca 95688 | [5 empty] | 0 | 0 | 0 | 0 |  | Modify Signal And Lighting Systems. | Sacramento County In Sacramento At 0.1 Mile South Of North Sacramento Undercrossing | 0 | 0 | 0 | 1436652.4 | 1436652.4 | 59796 |  | 2025-08-12 | 2025-08-05 |  |  | 0 | 0 | 45 | 0
03 | 03-1N0104 | 1N0104 | 03-SAC-160-/0 | 20.XX 201131 |  | Golden State Bridge Inc. | 3701 Mallard Drive | Benicia Ca 94510 |  | 5306496925 | 2777 Del Monte St. | W. Sacramento Ca 95691 | Griffith, Garrett | 0 | 203389.53 | 0 | 0 | 2026-01-20 | Repair/Replace Bridge Components | Mobilization Repair And Or Replace Electrical And Mechanical Bridge Components Traffic Control Dir'S Emergency F.A. | 90 | 52 | 10401193.66 | 87620 | 19985000 | 56108 | 2026-03-11 | 2024-07-19 | 2024-05-31 |  |  | 360 | 0 | 400 | 0
03 | 03-4H9704 | 4H9704 | 03-SAC-5500-/0 |  |  | Creekside Commercial Builders,Inc. | 3131 Peacekeeper Way Ste 400 | Mcclellan Ca 95652 |  | 5302155427 | 3461 Robin Ln. Ste. 4 | Cameron Park, Ca 95682 | Thompson, Brian | 111282.93 | 0 | 54234.8 | 0 | 2026-02-20 | Heating Ventilation And Air Conditioning R | Sacramento County In Rancho Cordova At Theregional Transportation Management Center,3165 Gold Valley Drive | 11 | 100 | 4399050.6 | 4263463 | 4416879.13 | 56748 | 2026-02-27 | 2024-12-03 | 2024-11-01 |  |  | 20 | 0 | 150 | 25 |  | X
03 | 03-3J6804 | 3J6804 | 03-SUT-20-15.7/16.1 |  | HSNH-P020- (205)E | Lamon Construction Co., Inc. | 871 Von Geldern Way | Yuba City Ca 95991 | [5 empty] | 0 | 0 | 0 | 0 |  | Signal And Lighting Systems, Hma, And Curb | Sutter County In Yuba City From Gray Avenue To Clark Avenue | 0 | 0 | 0 | 2055771.24 | 2055771.24 | 60157 |  | 2025-11-03 | 2025-10-20 |  |  | 0 | 0 | 170 | 0
03 | 03-4H8704 | 4H8704 | 03-SUT-99-25.0/26.2 |  | HSNH-P099- (686)E | O.C. Jones & Sons, Inc. | 1520 Fourth Street | Berkeley Ca 94710 |  | 5308125727 | 379 Colusa Ave | Yuba City, Ca 95991 | Horse, Dustin | 3605 | 33486.08 | 52367.06 | 0 | 2026-01-20 | Rdwy Exc, Place Hma-A And Crcp, Install Si | Sutter County Near Yuba City From 0.6 Milesouth To 0.6 Mile North Of Oswald Road | 70 | 97 | 6325852.05 | 6224280 | 6610852.58 | 56601 | 2026-03-31 | 2024-10-29 | 2024-10-09 |  | S | 70 | 0 | 100 | 0 |  | X
03 | 03-0J3504 | 0J3504 | 03-VAR-149-/5.3 | 20.20 201130 |  | A. Teichert & Son, Inc. Dba Teichert Construction | 400 Sunrise Ave Ste 300 | Roseville Ca 95661 |  | 5307137814 | 2707 Notre Dame Blvd., | Chico, Ca 95928 | Grandy, Dwayne | 7500 | 1239.56 | 0 | 0 | 2021-03-29 | Camp Fire Mission Tasks | In Butte, Yuba And Sutter Counties On Routes 65, 70, 99, 149 And 191 At Various Locations. Dir'S Emergency L.B. | 100 | 74 | 1828973.13 | 7500 | 2485000 | 40395 | 2021-03-29 | 2019-07-24 | 2019-06-14 |  |  | 200 | 0 | 200 | 0
03 | 03-0J5204 | 0J5204 | 03-VAR--/0 |  | ACNH-P020- (204)E | Baldwin Contracting Company, Inc. Dba Knife River Construction | 1764 Skyway | Chico Ca 95928 | 5308916555 | 5307908595 | 138 New Mohawk Rd Suite B | Nevada City, Ca 95959 | Price, Lucas | 0 | 0 | 0 | 0 |  | Cold Plane Ac Pvmt, Hma (Type A), & Draina | Nevada And Placer Counties At Various Locations From 0.1 Mile East Of Dow Road To 0.5 Mile East Of Yuba Pass Separation And Overhe | 0 | 0 | 0 | 18414350.44 | 18414350.44 | 60260 |  | 2025-12-15 | 2025-11-10 |  | S | 0 | 0 | 240 | 0
03 | 03-0J6204 | 0J6204 | 03-VAR--/0 |  | PTNH-X067- (085)E | Thompson Builders Corporation | 5400 Hanna Ranch Road | Novato Ca 94945 | [5 empty] | 0 | 0 | 0 | 0 |  | Drainage Pump Plant Work. | Sacramento County At Various Locations | 0 | 0 | 0 | 12762654.8 | 12762654.8 | 60277 |  | 2025-12-30 | 2025-12-09 |  |  | 0 | 0 | 165 | 0
03 | 03-3H9014 | 3H9014 | 03-VAR--/0 |  | NFRA-6203- (070)000 | Desilva Gates Construction Llc | 11555 Dublin Blvd. | Dublin Ca 94568 |  | 5308213881 | 2777 Del Monte Street | West Sacramento, Ca 95691 | Wild, Joseph | 2299357.65 | 482985.97 | -27701.05 | 0 | 2026-02-20 | Hma, Rhma, Sign Structure, Camera Systems, | Solano And Yolo Counties At Various Locations | 42 | 43 | 54593902.42 | 124798898 | 127328979.42 | 56621 | 2026-10-22 | 2024-10-23 | 2024-09-27 |  |  | 125 | 0 | 295 | 0 |  | X
03 | 03-3G2304 | 3G2304 | 03-VAR--/0 |  |  | Myers & Sons Construction, Llc | 45 Morrison Ave | Sacramento Ca 95838 |  | 5306496925 | 2777 Del Monte St | West Sacramento, Ca 95691 | Teweldeberhan, Ephrem | 10471.82 | 0 | 0 | 0 | 2026-02-20 | Furnish And Place Polyester Concrete Overl | Sacramento County At Various Locations | 36 | 93 | 3294822.61 | 3374372 | 3411854.67 | 59375 | 2026-03-03 | 2025-07-16 | 2025-06-19 |  | S | 74 | 0 | 205 | 0 |  | X
03 | 03-1N0004 | 1N0004 | 03-VAR--/0 | 20.10 201352 |  | Pisor Fence Division, Inc | Po Box 7213 | Citrus Heights, Ca 95621 |  | 5306823842 | 379 Colusa Ave | Yuba City, Ca 95991 | Griffith, Garrett | 0 | 685061.91 | 0 | 0 | 2026-01-20 | Security Measures | Mobilization, Install New Fencing, Replace Security Gates Install New Security System Dir'S Emergency L.B. | 100 | 79 | 3296407.11 | 24275 | 4160000 | 57098 | 2026-03-20 | 2024-12-03 | 2024-05-17 |  |  | 80 | 0 | 30 | 0
03 | 03-3H5604 | 3H5604 | 03-VAR--/0 |  | BFNH-000C- (560)E | Flatiron Dragados West Llc | 1200 Concord Ave, Ste 465 | Concord, Ca 94520 | 7077426000 | 9167994858 | 33 Depot Street, Po Box 1807 | Colfax, Ca 95713 | Sampson, Tad | 333848.87 | 390649.99 | -43096.76 | 0 | 2026-02-20 | Structural Conc, Bar Reinforcing Steel, Br | Placer And Nevada Counties Near Cisco Grove On Route 80 From 0.4 Mile West Of Lake Valley Overcrossing To 0.9 Mile East Of Yuba Pa | 43 | 57 | 51653519.23 | 82988787.14 | 90022280.14 | 55913 | 2026-09-14 | 2024-06-05 | 2024-05-10 |  | S | 222 | 0 | 515 | 0 |  | X
03 | 03-3G4904 | 3G4904 | 03-VAR--/0 |  |  | Studebaker Electric, Inc. | 3237 Rippey Road, Ste 100 | Loomis Ca 95650 | [5 empty] | 0 | 0 | 0 | 0 |  | Modify Cms. | Placer County At Various Locations | 0 | 0 | 0 | 823180 | 608002.1 | 58516 |  | 2025-06-04 | 2025-05-15 |  |  | 0 | 0 | 15 | 0
03 | 03-3J40U4 | 3J40U4 | 03-VAR--/0 |  |  | Teichert Energy & Utilities Group, Inc. | 3500 American River Drive | Sacramento Ca 95864 |  | 5306825837 | 10183 Truckee Airport Rd #202 | Truckee, Ca 96161 | Hagstorm, Shawn | 1479311.62 | 0 | 0 | 0 | 2026-01-20 | Middle-Mile Broadband Network | Alpine, El Dorado, And Placer Counties In And Near South Lake Tahoe On Route 89 Fromroute 88 To Route 28 And On Route 50 From Sout | 26 | 35 | 18107359.89 | 51749000.73 | 52096049.78 | 57695 | 2026-11-09 | 2025-03-12 | 2025-03-12 |  |  | 84 | 0 | 329 | 0 |  | X
03 | 03-3G4804 | 3G4804 | 03-VAR--/0 |  |  | Studebaker Electric, Inc. | 3237 Rippey Road, Ste 100 | Loomis Ca 95650 |  | 5308218282 | 3855 N. Freeway Blvd #120 | Sacramento, Ca 95834 | Tji, Jony | 112334 | 0 | 0 | 0 | 2026-02-20 | Modify Cms Systems. | Butte, Sacramento, Sutter And Yolo Counties At Various Locations | 87 | 98 | 779390 | 794500 | 794500 | 59824 | 2026-03-06 | 2025-06-09 | 2025-05-22 |  |  | 13 | 0 | 15 | 0 |  | X
03 | 03-3G4704 | 3G4704 | 03-VAR--/0 |  |  | Studebaker Electric, Inc. | 3237 Rippey Road, Ste 100 | Loomis Ca 95650 |  | 5308218282 | 3855 N. Freeway Blvd #120 | Sacramento, Ca 95834 | Tji, Jony | 262980 | 0 | 11550 | 0 | 2026-02-20 | Modify Cms Systems. | Butte, El Dorado And Sacramento Counties At Various Locations | 100 | 98 | 692224 | 697580 | 709130 | 59823 | 2026-03-01 | 2025-05-23 | 2025-05-02 |  |  | 20 | 0 | 20 | 0 |  | X
03 | 03-3G4604 | 3G4604 | 03-VAR--/0 |  |  | Studebaker Electric, Inc. | 3237 Rippey Road, Ste 100 | Loomis Ca 95650 | 9162592395 | 9167994858 | 33 Depot St | Colfax, Ca 95713 | Sampson, Tad | 69815 | 0 | 0 | 0 | 2026-02-20 | Modify Cms Systems. | Nevada And Placer Counties At Various Locations | 90 | 96 | 776640 | 796300 | 806300 | 59822 | 2026-02-24 | 2025-06-10 | 2025-06-03 |  |  | 18 | 0 | 20 | 0 |  | X
03 | 03-3G6204 | 3G6204 | 03-YOL-5-22.8/28.9 |  |  | All-American Construction, Inc. | 1700 Acacia Avenue | Sutter Ca 95982 |  | 5308125727 | 379 Colusa Avenue | Yuba City, Ca 95991 | Horse, Dustin | 0 | 15422.2 | 0 | 0 | 2026-02-20 | Cold Plane Ac Pvmt And Hma (Type A). | Yolo County Near Dunnigan From 0.2 Mile North Of Route 505/5 Separation To The Colusa County Line | 63 | 92 | 5414475.08 | 2896607 | 5845176.85 | 59296 | 2026-03-30 | 2025-07-09 | 2025-06-03 |  |  | 25 | 0 | 40 | 0 |  | X
03 | 03-4J1204 | 4J1204 | 03-YOL-16-37.3/37.8 |  | HSST-S016- (001)E | Bay Cities Paving & Grading, Inc. | 1450 Civic Ct Bldg B #400 | Concord Ca 94520 | [5 empty] | 0 | 0 | 0 | 0 |  | Hma, Flashing Beacon System, And Roadway E | Yolo County Near Woodland 0.2 Mile West Ofcounty Road 95 To 0.2 Mile East Of County Road 95 | 0 | 0 | 0 | 1779057.81 | 1779057.81 | 60118 |  | 2025-10-13 | 2025-09-05 |  |  | 0 | 0 | 50 | 0
03 | 03-4F6504 | 4F6504 | 03-YOL-50-/2.5 |  | ACNH-X113- (036)E | Flat-Iron Teichert A Joint Venture | 1200 Concord Avenue Suite 465 | Concord Ca 94520 | 7077426000 | 9168013455 | 1016 N. Market Blvd Ste 50/60 | Sacramento, Ca 95834 | Mehari, Mirak | 4528982.97 | 2372653.38 | 1246301.2 | 0 | 2026-02-20 | Crcp, Hma (Type A), Rdwy Exc, Class 2 Ab, | Yolo County In And Near West Sacramento Onroute 80 From 1.7 Miles East Of Mace Boulevard Overcrossing To Sacramento Riverbridge An | 77 | 90 | 216957312.98 | 204804408.8 | 234802273.66 | 47744 | 2026-08-17 | 2023-03-17 | 2023-02-14 |  |  | 421 | 0 | 505 | 44 |  | X
03 | 03-1N6204 | 1N6204 | 03-YOL-275-130.0/13 | 20.XX 201131 |  | Valentine Corporation | 111 Pelican Way | San Rafael, Ca 94901 |  | 5306496925 | 2777 Del Monte St | West Sacramento, Ca 95691 | Griffith, Garrett | 0 | 37810.6 | 0 | 0 | 2026-01-20 | Tower Bridge Cables | Mobilization, Remove All Traveling Cables And Conductors, Install New Cables And Conductors Dir'S Emergency L.B. | 0 | 6 | 178012.76 | 15355 | 3000000 | 60159 | 2026-10-26 | 2025-08-15 | 2024-12-14 |  |  | 0 | 0 | 180 | 0 |  | X
03 | 03-1N9304 | 1N9304 | 03-YUB-70-82.0/13.6 | 20.XX 201130 |  | Tyrrell Resources, Inc. | P.O. Box 8219 | Truckee, Ca 96162 |  | 5308125727 | 379 Colusa Avenue | Yuba City, Ca 95991 | Horse, Dustin | 0 | 552727.78 | 0 | 0 | 2026-02-20 | Yuba 70 Tree Removal | Mobilization, Remove Damaged/Structurally Weak/Dying Trees, Remove Branches, Stump Grinding, Tree Disposal,Incidental Director'S E | 23 | 37 | 1459570.84 | 78000 | 3900000 | 60181 | 2026-06-05 | 2025-10-02 | 2025-04-22 |  |  | 23 | 0 | 100 | 0 |  | X
04 | 04-3Y1904 | 3Y1904 | 04-ALA-0-/0 | 20.20.201130 |  | Norcal General Construction Corporation | 751 Mabury Rd | San Jose, Ca, 95133 | 4085954015 | 3414009265 | 1007 Knox Ave | San Jose, Ca 95122 | Li, Peijie | 0 | 451863.65 | 0 | 0 | 2024-12-24 | Repair Knocked Down Electrical Assets- Pol | District South-Wide Repair Of Electrical Edistrict South-Wide Repair Of Electrical Edistrict South-Wide Repair Of Electrical Edir' | 99 | 86 | 1170129.55 | 29000 | 1365500 | 48265 | 2025-10-15 | 2023-03-29 | 2023-01-20 |  |  | 79 | 0 | 80 | 0 |  | X
04 | 04-2G4614 | 2G4614 | 04-ALA-13-10.7/13 |  | ACNH-P013- (138)E | Accurate Earthworks, Inc. | 501 Cesar Chavez Suite 212A | San Francisco Ca 94124 | 7144235566 | 9257665224 | 3401 Regatta Blvd | Richmond, Ca 94804 | Seng, Ta | 101542.17 | 0 | 0 | 0 | 2025-12-29 | Reconstruct Ada Curb Ramps. | Alameda County In Berkeley At Various Locations From Domingo Avenue To Mabel Street | 100 | 100 | 735530.31 | 777321 | 827321 | 46424 | 2025-12-29 | 2023-04-17 | 2023-01-26 | 2026-01-21 |  | 60 | 0 | 60 | 0 |  | X
04 | 04-3W9304 | 3W9304 | 04-ALA-80-5.7/6 |  |  | Marina Landscape Inc. | 3707 W Garden Grove Blvd | Orange Ca 92868 | 7149396600 | 5107746276 | 3401 Regatta Blvd. | Richmond Ca.94804 | Luckel, Kasaia | 1610 | 0 | 0 | 0 | 2026-02-20 | Highway Planting And Irrigation System, Ro | Alameda County In Berkeley From 0.1 Mile West To 0.2 Mile East Of University Avenueovercrossing | 96 | 94 | 2015340.6 | 2120678.25 | 2140906.7 | 47847 | 2026-03-30 | 2023-03-22 | 2023-02-24 |  |  | 685 | 0 | 840 | 130 |  | X
04 | 04-3J2604 | 3J2604 | 04-ALA-80-5.9/6.4 |  | SIMG-000C- (562)E | O.C. Jones & Sons, Inc. | 1520 Fourth Street | Berkeley Ca 94710 | 5106840157 | 5108676156 | 3401 Regatta Blvd | Richmond, Ca 94804 | Faustin, Glenn | 58175 | 0 | 0 | 0 | 2026-02-19 | Install Cb, Wrought Iron Fence, Modify Lig | Alameda County In Fremont From 0.1 Mile South Of Mission San Jose 680/238 Separation To 0.3 Mile North Of Mission San Jose 680/238 | 100 | 65 | 3348399.53 | 4525446.5 | 5313885.99 | 57117 | 2026-02-27 | 2025-01-07 | 2024-12-13 |  |  | 100 | 0 | 100 | 0
04 | 04-0A7724 | 0A7724 | 04-ALA-80-6.4/6.8 |  | ACIM-0801- (121)E | O.C. Jones & Sons, Inc. | 1520 Fourth Street | Berkeley Ca 94710 | 5105263424 | 5108676093 | 3847 Breakwater Ave. | Hayward, Ca 94545 | Champaneria, Vinay | 830 | 0 | 1856.4 | 0 | 2026-02-20 | Construct Double Roundabouts At | On I-80 At Gilman Street Interchange From 0.6 Miles North Of University Avenue Oc To 0.5 Mile South Of El Cerrito Separation In An | 88 | 97 | 33547128.23 | 25231719.98 | 34275348.8 | 42059 | 2026-07-01 | 2022-01-27 | 2022-01-04 |  |  | 596 | 0 | 600 | 81 |  | X
04 | 04-0K1604 | 0K1604 | 04-ALA-80-7.6/8 |  | SIMG-0801- (998)E | Bay Cities Paving & Grading, Inc. | 1450 Civic Ct Bldg B #400 | Concord Ca 94520 | 9256876666 | 9166346646 | 3401 Regatta Blvd. | Richmond, Ca 94804 | Nou, Bunma | 207958.72 | 570716.38 | 0 | 0 | 2026-02-20 | Construct Rhma, Lighting System, And Concr | Alameda And Contra Costa Counties In Albany And Crockett From 0.4 Mile South Ofalameda County Line To 0.2 Mile South Of Pomona Str | 100 | 94 | 56416794.41 | 55089000 | 59454783.11 | 49124 | 2026-03-31 | 2023-03-02 | 2023-02-08 |  |  | 350 | 0 | 350 | 0 |  | X
04 | 04-4Y1804 | 4Y1804 | 04-ALA-80-/1.8 |  |  | Ghilotti Bros And St Francis Electric Jv | 525 Jacoby Street | San Rafael Ca 94901 | 4154547011 | 5108674545 | 575 Linda Mar Blvd. | Pacifica, Ca 94044 | Larwin, Thomas | 0 | 0 | 0 | 0 |  | Middle-Mile Broadband Network (Mmbn) On Sa | On San Francisco Bay Bridge | 0 | 0 | 0 | 1725640.72 | 1725640.72 | 57597 |  | 2025-03-12 | 2025-03-12 |  |  | 0 | 0 | 75 | 0
04 | 04-3Q8504 | 3Q8504 | 04-ALA-84-10.8/18 |  | HSNH-P084- (060)E | Tennyson Electric, Llc | 7275 National Dr Ste A-2 | Livermore Ca 94550 | 9256061038 | 5104592581 | 5675-B Gibraltar Drive | Pleassanton, Ca 94588 | Sadeghi-Nedjad, Amir-Fardin | 177555 | 0 | 0 | 0 | 2025-11-20 | Flashing Beacon Systems. | Alameda County In Fremont, Union City And At Sunol From Route 238 To 0.1 Mile West Of Route 680 | 66 | 73 | 1682054.75 | 2298130 | 2298130 | 57676 | 2026-01-30 | 2025-03-27 | 2025-02-13 |  |  | 79 | 0 | 120 | 0 |  | X
04 | 04-160314 | 160314 | 04-ALA-84-11.0/18 |  |  | Bortolussi & Watkin, Inc. | 77 Larkspur Street | San Rafael Ca 94901 | 4154534675 | 5107746276 | 3401 Regatta Blvd. | Richmond, Ca 94804 | Luckel, Kasaia | 10521.26 | 0 | 0 | 0 | 2026-02-20 | Maintain Existing Planted Area, Highway Pl | Alameda County In And Near Fremont And In Sunol At Various Locations From 0.2 Mile East Of Route 238 Junction (Mission Boulevard) | 20 | 30 | 183058.93 | 599975 | 614975 | 56807 | 2029-03-02 | 2024-12-10 | 2024-11-22 |  |  | 210 | 0 | 1040 | 0 |  | X
04 | 04-1X2804 | 1X2804 | 04-ALA-84-11.2/15.5 | 20.20.201130 |  | Pacific Coast Drilling Co.,Inc | 364 Bellevue Ave. | Santa Rosa, Ca 95407 | 7077788316 | 9252505611 | 5675-B Gibraltar Drive | Pleasanton, Ca 94588 | Dike, Eddie | 0 | 999706.11 | 0 | 0 | 2026-01-30 | Niles Canyon Slipout | In Alameda County In Sunol Hwy 84 Niles Canyon Slope And Retaining Wall Repair Dir'S Order Emergency F.A. | 100 | 99 | 6550040.09 | 34658 | 6570000 | 55465 | 2025-11-30 | 2024-03-13 | 2024-02-20 |  |  | 484 | 0 | 240 | 0 |  | X
04 | 04-0J5504 | 0J5504 | 04-ALA-84-17.0/17.4 |  | ACNH-S084- (042)E | Ghilotti Construction Company,Inc. | 246 Ghilotti Avenue | Santa Rosa Ca 95407 | 7073260647 | 5108676181 | 5675 B Gibraltar Drive | Pleasanton, Ca 94588 | Tun, Yannaing | 0 | 0 | 0 | 0 |  | Replace Bridge, Widen Roadway, & Construct | Alameda County At Sunol From Silver Springroad Underpass To Pleasanton Sunol Road | 0 | 0 | 0 | 24888172.55 | 24888172.55 | 60372 | 2028-09-13 | 2026-01-13 | 2025-12-30 |  |  | 0 | 0 | 875 | 0
04 | 04-297634 | 297634 | 04-ALA-84-17.9/22.9 |  |  | Bay Cities Paving & Grading, Inc. | 1450 Civic Ct Building B#400 | Concord, Ca 94524-6227 | 9252276296 | 5108676694 | 5675 B Gibraltar Drive | Pleasanton, Ca 94588 | Pandher, Paramjit | 256344.33 | 145547.32 | 0 | 0 | 2026-02-20 | Widening Route 84 To Expressway And | In And Near Sunol, Pleasanton And Livermore On Rte 680 From 1.2 Mi South To 1.8 Mi North Of Rte 84 And On Rte 84 From 0.1 Mi East | 73 | 98 | 142741164.74 | 133802176.49 | 143986238.98 | 41508 | 2026-12-17 | 2021-03-11 | 2021-02-19 |  |  | 733 | 0 | 1000 | 0 |  | X
04 | 04-0X6604 | 0X6604 | 04-ALA-84-21.4/23.1 |  |  | Bay Cities Paving & Grading, Inc. | 1450 Civic Ct Bldg B #400 | Concord Ca 94520 | 9256876666 | 5108676694 | 5675 B Gibraltar Drive | Pleasanton, Ca 94588 | Pandher, Paramjit | 3040.76 | 0 | 0 | 0 | 2026-01-20 | Cold Plane Ac Pavement And Overlay With Rh | Alameda County In And Near Pleasanton And Livermore From 0.1 Mile South Of Vehicle Undercrossing South To 0.1 Mile South Of Ruby H | 100 | 88 | 1342712.15 | 1524597.25 | 1524597.25 | 59736 | 2025-12-22 | 2025-07-29 | 2025-06-25 |  |  | 45 | 0 | 45 | 0 |  | X
04 | 04-2Q7604 | 2Q7604 | 04-ALA-238-.7/.8 |  | ACNH-X001- (671)E | Ghilotti Bros., Inc. | 525 Jacoby Street | San Rafael Ca 94901 | 4154547011 | 5103858001 | 5675 B Gibraltar Drive | Pleasanton, Ca 94588 | Reza, Kamkar | 0 | 0 | 0 | 0 | 2025-12-16 | Rectangular Rapid Flashing Beacon Systems, | Alameda County In Fremont On Route 680 At Off-Ramp To Scott Creek Road And On Route 238 At Mission Ridge Court | 100 | 100 | 2038754.98 | 1988816.01 | 2069807.01 | 55946 | 2025-12-16 | 2024-06-17 | 2024-05-22 | 2026-01-27 |  | 279 | 0 | 395 | 0 |  | X
04 | 04-0G3604 | 0G3604 | 04-ALA-260-.8/1.9 |  | ACNH-X001- (692)E | Bay Cities Paving & Grading, Inc. | 1450 Civic Ct Bldg B #400 | Concord Ca 94520 | 9256876666 | 5103857081 | 3847 Breakwater Avenue | Hayward, Ca 94545 | Champaneria, Vinay | 0 | 109591.46 | 0 | 0 | 2026-02-20 | Modify Ramps, Hma Pvmt, Bridges, Drainage, | Alameda County In Oakland And Alameda On Route 260 From Willie Stargell Avenue To 7Th Street And On Route 880 From 23Rd Avenue To | 0 | 0 | 109591.46 | 95207833.25 | 95717833.25 | 59915 | 2029-09-05 | 2025-08-27 | 2025-08-08 |  |  | 0 | 0 | 1130 | 0 |  | X
04 | 04-2W7404 | 2W7404 | 04-ALA-260-1.1/1.9 | 20.20.201130 |  | Monterey Mechanical Co | 8275 San Leandro Street | Oakland, Ca 95621 | 5106323173 | 5108676694 | 5675 Gibraltar Drive, Suite B, | Pleasanton, 94588 | Pandher, Paramjit | 0 | 24774.84 | 0 | 0 | 2026-02-24 | Install Fuel Cell Power System | In Alameda County, At The Posey-Webster Tubes Install Fuel Cell Power System | 97 | 83 | 7930057.44 | 38005 | 9544000 | 42145 | 2026-05-31 | 2022-01-11 | 2021-09-06 |  |  | 418 | 0 | 340 | 92 |  | X
04 | 04-1Y3404 | 1Y3404 | 04-ALA-260-1.2/0 |  |  | Disney Construction, Inc. | 533 Airport Blvd., Suite 120 | Burlingame Ca 94010 | 6502599545 | 5103857081 | 3847 Breakwater Ave. | Hayward, Ca 94545 | Champaneria, Vinay | 1033097.6 | 51840.22 | 0 | 18500 | 2026-02-20 | Repair Spalled Surface Area And Replace Po | Alameda County In Alameda And Oakland At The Posey Tube And Webster Street Tube | 100 | 80 | 3299158.69 | 3833333 | 4369230.72 | 58737 | 2026-03-31 | 2025-06-09 | 2025-05-19 |  |  | 110 | 0 | 110 | 0
04 | 04-3X9504 | 3X9504 | 04-ALA-580-4.6/4.7 | 20.20.201130 |  | Redgwick Construction Company | 21 Hegenberger Ct | Oakland, Ca 94621 | 0254706675 | 5103939557 | 5675-B Gibraltar Dr | Pleasanton, Ca 94588 | Shah, Purvi | 0 | 0 | 0 | 0 |  | Dir'S Order Emergency F.A. | Livermore Repair Livermore Culvert Replace Livermore Culvert Repair/Replace Culvert | 0 | 0 | 0 | 4500 | 635000 | 60128 | 2026-06-10 | 2025-10-17 | 2025-08-27 |  |  | 0 | 0 | 40 | 0
04 | 04-3Y5504 | 3Y5504 | 04-ALA-580-4.7/4.8 | 20.20.201130 |  | Viking Construction Company, Inc. | Po Box 1508 | Rancho Cordova Ca 95741 | 9168525530 | 5108676694 | 5675 B Gibraltar Drive | Pleasanton Ca 94588 | Pandher, Paramjit | 0 | 288358.23 | 0 | 0 | 2025-11-21 | Repair Failed Slope And Construct New Rw | Efa Contract To Repair Rw On Eb 580 Pm4.7 To 4.8 Efa Contract To Repair Rw On Eb 580 Pm4.7 Dir'S Order Emergency F.A. | 99 | 96 | 12711085.12 | 18775 | 13276000 | 48504 | 2025-12-02 | 2023-05-31 | 2023-03-20 |  |  | 392 | 0 | 80 | 317 |  | X
04 | 04-0Q1004 | 0Q1004 | 04-ALA-580-20.7/30.8 |  | ACIM-5801- (984)E | Fbd Vanguard Construction | 550 Greenville Road | Livermore Ca 94550 | 9252451300 | 5108676694 | 5675 B Gibraltar Drive | Pleasanton, Ca 94588 | Pandher, Paramjit | 453231 | 34156.38 | 0 | 0 | 2026-02-20 | Individual Slab Replacement, Hma, Rhma, Ap | Alameda County In Pleasanton And Castro Valley From Route 680/580 Separation To Route 580/238 Separation | 62 | 83 | 45434665.91 | 47466283.6 | 48841206.34 | 56337 | 2026-09-16 | 2024-09-10 | 2024-07-11 |  |  | 234 | 0 | 350 | 28 |  | X
04 | 04-2Y8604 | 2Y8604 | 04-ALA-580-26.2/26.2 | 20.20.201130 |  | Redgwick Construction Company | 21 Hegenberger Ct, | Oakland 94621 | 5107921727 | 5108676694 | 5675-B Gibraltar Dr., | Pleasanton, Ca | Pandher, Paramjit | 0 | 184124.77 | 0 | 0 | 2026-01-22 | Slide And Slipout Repair Along Wb 580 Eden | Ala 580&680 Var Loc , Incl Eden Canyon & Sherdian, Sunol Grade - Slipouts | 100 | 70 | 3342771 | 7380 | 4805000 | 46665 | 2026-03-31 | 2023-02-08 | 2023-01-03 |  |  | 139 | 86 | 20 | 0
04 | 04-0Y6804 | 0Y6804 | 04-ALA-580-35.0/45.2 |  |  | Ghilotti Bros And St Francis Electric Jv | 525 Jacoby Street | San Rafael, Ca 94901 | 4154547011 | 5103857081 | 3847 Breakwater Ave. | Hayward, Ca 94545 | Baluyot, Rodelio | 717633.68 | 144879.28 | 0 | 44188.65 | 2026-02-20 | Install Broadband Conduit And Fiber For Br | In Alameda County, On Route 580 From Ala-580 Pm 35 To Pm 45.193 | 65 | 61 | 5910612.34 | 8841107.02 | 9748584.62 | 57615 | 2026-06-30 | 2025-02-26 | 2025-02-26 |  |  | 170 | 0 | 260 | 0 |  | X
04 | 04-0P9004 | 0P9004 | 04-ALA-580-41.3/44.8 |  | BFIM-5801- (985)E | Golden State Bridge, Inc. | 3701 Mallard Drive | Benicia Ca 94510 | 9253728000 | 5108676079 | 3847 Breakwater Ave. | Hayward, Ca 94545 | Singh, Jasmaninder | 0 | 0 | 0 | 0 |  | Br Removal, Col Casing, Cb, Cold Plane Ac | Alameda County In Oakland From 0.1 Mile West Of Webster Street Undercrossing To 0.1 Mile East Of Fruitvale Avenue Undercrossing | 0 | 0 | 0 | 12696329.25 | 12696329.25 | 60429 | 2027-06-01 | 2026-01-21 | 2026-01-06 |  |  | 0 | 0 | 300 | 0
04 | 04-2Y8204 | 2Y8204 | 04-ALA-580-/32.7 | 20.20.201130 |  | Pipe And Plant Solutions, Inc. | 23286 Foley Street, | Hayward, Ca 94545 |  | 5103857081 | 3847 Breakwater Ave. | Hayward Ca 94545 | Champaneria, Vinay | 0 | 49251.87 | 0 | 0 | 2025-12-17 | Repair And Replace Damaged Pump Plant | Repair And Replace Damaged Pump Plant | 100 | 75 | 2114706.17 | 6975 | 2803000 | 47484 | 2026-02-27 | 2023-04-18 | 2023-01-09 |  |  | 450 | 0 | 30 | 0
04 | 04-0P9204 | 0P9204 | 04-ALA-680-6.3/6.7 |  | ACIM-6801- (993)E | Myers & Sons Construction, Llc | 45 Morrison Ave | Sacramento Ca 95838 | 9162839950 | 5108676181 | 5675 B Gibraltar Drive | Pleasanton, Ca 94588 | Tun, Yannaing | 0 | 100471.52 | 0 | 0 | 2026-01-20 | Hma And Rhma Surfacing, Deck Repair, Polye | Alameda County In Fremont From 0.1 Mile South Of Mission San Jose 680/238 Separation To 0.3 Mile North Of Mission San Jose 680/238 | 99 | 98 | 8035954.67 | 7447650.3 | 7920269.88 | 57010 | 2026-01-21 | 2025-01-16 | 2024-12-20 | 2026-02-05 |  | 134 | 0 | 135 | 0 |  | X
04 | 04-0Q30U4 | 0Q30U4 | 04-ALA-680-11.0/21.9 |  | ACIM-6801- (990)E | Bay Cities Paving & Grading, Inc. | 1450 Civic Ct Building B #400 | Concord Ca 94520 | 9256876666 | 5108676181 | 5675 B Gibraltar Drive | Pleasanton, Ca 94588 | Tun, Yannaing | 414674.99 | 267668.33 | 0 | 0 | 2026-02-20 | Construct Express Lanes And | In Alamed And Contra Costa Counties At Sunol And In San Ramon From Koopmann Road Undercrossing To 0.9 Mile North Of Alcosta Boulva | 70 | 98 | 178416353.98 | 175969550.24 | 180532755.94 | 45964 | 2027-04-23 | 2022-12-13 | 2022-11-23 |  |  | 662 | 0 | 950 | 0 |  | X
04 | 04-2W4604 | 2W4604 | 04-ALA-680-15.6/0 |  |  | Serafix Engineering Contractors, Inc. | 7 Crow Canyon Court Ste 250 | San Ramon Ca 94583 | 9255528253 | 9252505611 | 5675 B Gibraltar Drive | Pleasanton, Ca 94588 | Dike, Eddie | 0 | 0 | 0 | 0 | 2025-10-17 | Slope Repair And Replace Downdrains And In | Alameda County In Pleasanton At South Pleasanton Overhead | 100 | 100 | 735522.38 | 717460 | 733733.93 | 59335 | 2025-10-17 | 2025-07-14 | 2025-06-25 | 2026-02-04 |  | 47 | 0 | 30 | 0 |  | X
04 | 04-0V1604 | 0V1604 | 04-ALA-680-20.7/20.7 | 20.20.201130 |  | Golden State Bridge, Inc. | 3701 Mallard Drive | Benicia, Ca 94510 | 9253728000 | 5103858001 | 5675 B Gibraltar Dr. | Pleasanton, Ca 94588 | Kamkar, Reza | 0 | 44598.38 | 0 | 0 | 2026-02-20 | Repair Steel Joint Seal Assembly | S 680 / E580 Connector In Pleasanton Repail Steel Joint Seal Assembly At Hinges 14 And 17 Dir'S Order Emergency F.A. | 70 | 2 | 44598.38 | 12267 | 1950000 | 60350 | 2026-03-16 | 2026-01-21 | 2025-12-11 |  |  | 42 | 0 | 60 | 0 |  | X
04 | 04-0Q1804 | 0Q1804 | 04-ALA-880-6.2/25.5 |  | ACIM-8801- (989)E | Anvil Builders Inc. | 1550 Park Ave | Emeryville Ca 94608 | 4152855000 | 5108676079 | 3847 Breakwater Ave. | Hayward, Ca 94545 | Singh, Jasmaninder | 0 | 170348.58 | 0 | 0 | 2025-12-20 | Install Trash Net, Concrete Ditch, Welded | Alameda County At Various Locations From Stevenson Boulevard Overcrossing In Fremont To Hegenberger Road Overcrossing In Oakland | 100 | 96 | 2792374.6 | 2491642.8 | 2875170.9 | 55775 | 2026-01-30 | 2024-05-08 | 2024-04-08 |  |  | 120 | 0 | 120 | 0 |  | X
04 | 04-2X4204 | 2X4204 | 04-ALA-880-/25.7 | 20.20.201130 |  | Redgwick Construction Company | 21 Hegenberger Ct, | Oakland, Ca 94621 |  | 5107147039 | 3847 Breakwater Ave Ste 100, | Hayward, Ca 94545 | Safi, Saeed | 0 | 0 | 0 | 0 |  | Homeless Encampment | In Oakland, Hegenberger Rdrdrd Homeless Encampment | 0 | 0 | 0 | 18306 | 3035000 | 60444 | 2026-08-18 | 2025-10-24 | 2025-10-24 |  |  | 0 | 0 | 140 | 0
04 | 04-2K7004 | 2K7004 | 04-ALA-880-/11.8 |  | ACIM-8801- (987)E | Bay Cities Paving & Grading, Inc. | 1450 Civic Ct Bldg B #400 | Concord Ca 94520 | 9256876666 | 5108676083 | 3847 Breakwater Ave | Hayward, Ca 94545 | Baluyot, Rodelio | 0 | 61993.63 | 0 | 0 | 2026-02-20 | Cold Plane Pavement And Overlay With Rhma- | Alameda County In Fremont And Newark From Santa Clara County Line To 0.4 Mile North Of Fremont Boulevard Overcrossing | 87 | 99 | 81806074.59 | 76445361 | 82154516.47 | 52424 | 2026-04-20 | 2023-08-16 | 2023-07-13 |  | S | 253 | 0 | 290 | 0 |  | X
04 | 04-1X3804 | 1X3804 | 04-ALA-880-/28.9 | 20.10.201352 |  | Anvil Builders, Inc. | 1550 Park Ave. | Emeryville, Ca 94608 | 4152855000 | 5108676083 | 3847 Breakwater Ave. | Hayward, Ca 94545 | Baluyot, Rodelio | 0 | 70236.23 | 0 | 0 | 2025-12-03 | Install/Replace Video Surveillance System | Maintenance Facilities In Ala, Cc, Scl And Sol Counties Install/Replace Video Surveillance System Dir'S Order Emergency F.A. | 27 | 97 | 970097.98 | 4322 | 1003000 | 56318 | 2026-01-30 | 2024-08-28 | 2024-08-07 |  |  | 145 | 0 | 530 | 0 |  | X
04 | 04-4K9804 | 4K9804 | 04-ALA-980-1.1/1.1 | 20.20.201130 |  | San Francisco Elevator Services, Llc | 6509 Sierra Lane | Dublin, Ca 94568 | 9258295400 | 5103858001 | 5675-B Gibraltar Drive | Pleasanton, Ca 94588 | Kamkar, Reza | 0 | 36288.43 | 0 | 0 | 2025-08-22 | Building Elevator Rehab | In Oakland, At The Caltrans District 4 Headquarters Office Building, 111 Grand Avenue Order Emergency F.A. | 35 | 53 | 2973767.11 | 70325 | 5611000 | 42026 | 2026-08-07 | 2021-12-23 | 2021-10-11 |  |  | 303 | 0 | 335 | 535 |  | X
04 | 04-3W9104 | 3W9104 | 04-ALA-980-1.2/0 |  | ACST-000C- (558)E | Parsons Transportation Group, Inc. | 555 12Th Street, Suite 2150 | Oakland Ca 94607 | 5104183801 | 3414009265 | 1007 Knox Avenue | San Jose, Ca 95122 | Li, Peijie | 1124711.89 | 0 | 0 | 0 | 2026-02-20 | Upgrade Controllers In Vehicle Detection A | At Various Locations | 59 | 40 | 7913054.34 | 19826704.19 | 19655049.82 | 56609 | 2027-01-07 | 2024-08-15 | 2024-08-15 |  |  | 336 | 0 | 574 | 0 |  | X
04 | 04-2K9504 | 2K9504 | 04-ALA-5501-/14.4 |  |  | Walsh Construction Company Ii,Llc | 1390 Willow Pass Road | Concord Ca 94520 |  | 5104592581 | 5675-B Gibraltar Drive | Pleasanton, Ca 94588 | Sadeghi-Nedjad, Amir-Fardin | 77561 | 61255.85 | 0 | 0 | 2026-02-20 | Construct Material Testing Laboratory Buil | Alameda County In Livermore At 2201 Kitty Hawk Road | 70 | 97 | 19051281.24 | 16132760.3 | 19528855.2 | 47524 | 2026-02-23 | 2023-03-02 | 2023-02-02 |  |  | 576 | 0 | 625 | 202 |  | X
04 | 04-3X5804 | 3X5804 | 04-CC-4-19.8/19.8 | 20.20.201130 |  | G N Henley Inc | 3107 Morgan Territory Rd, | Clayton, Ca 94517 |  | 5104075226 | 2525 Stanwell, Suite 100, | Concord, Ca 94520 | Kim, Jaeyoon | 0 | 753769.52 | 0 | 0 | 2026-02-12 | Slope Repair And Repaid Displaced Downdra | Slope Repair And Repaid Displaced Downdrain | 100 | 97 | 753769.52 | 7727 | 777500 | 59637 | 2026-03-20 | 2025-08-05 | 2025-04-24 |  |  | 100 | 0 | 50 | 0 |  | X
04 | 04-2Q7004 | 2Q7004 | 04-CC-4-/14.3 |  | ACNH-P004- (163)E | Bay Cities Paving & Grading, Inc. | 1450 Civic Ct Bldg B #400 | Concord Ca 94520 | 9256876666 | 5107744383 | 2525 Stanwell Drive, Ste 100 | Concord, Ca 94520 | Mukherjee, Rabindra | 227301.51 | 0 | 100427.44 | 0 | 2026-02-20 | Replace Asphalt Concrete Surfacing And Ins | Contra Costa County In Hercules And Concord From San Pablo Avenue To Route 4/242 Separation | 83 | 92 | 35574325.03 | 35010000 | 37179152.89 | 55873 | 2026-05-22 | 2024-05-29 | 2024-04-26 |  | S | 315 | 0 | 350 | 30 |  | X
04 | 04-3X7404 | 3X7404 | 04-CC-24-5.1/5.4 | 20.20.201130 |  | Brannon Corporation | 10492 Dougherty Ave | Morgan Hill Ca 95037 |  | 5104075226 | 2525 Stanwell, Suite 100, | Concord, Ca 94520 | Kim, Jaeyoon | 0 | 0 | 0 | 0 |  | Pavement Delineation And Any Additional Wo | Repair Roadway Settlement, Polyurethane Injection.Reconstruct Hma Dikes And Mgs,Erosion Control. Pavement Delineation And Any Addi | 0 | 0 | 0 | 4476 | 1806000 | 60130 | 2026-03-06 | 2025-10-21 | 2025-07-08 |  |  | 0 | 0 | 30 | 0
04 | 04-0Q2104 | 0Q2104 | 04-CC-80-.2/10.7 |  | ACIM-0801- (996)E | Bay Cities Paving & Grading, Inc. | 1450 Civic Ct Bldg B #400 | Concord Ca 94520 | 9256876666 | 5106316697 | 3401 Regatta Blvd. | Richmond, Ca 94804 | Culp, Matthew | 40851.9 | 1171.55 | 0 | 0 | 2026-02-20 | Install Gross Solids Removal Devices And T | Contra Costa County At Various Locations From Central Avenue Undercrossing To Willow Avenue Undercrossing. | 34 | 76 | 4420027.49 | 6870000 | 5838217.99 | 56727 | 2026-07-06 | 2024-09-18 | 2024-09-04 |  |  | 187 | 0 | 550 | 0 |  | X
04 | 04-0P9304 | 0P9304 | 04-CC-80-7.6/0 |  | BFIM-0801- (958)E | Bugler Construction, Inc. | 4847 Hopyard Rd. Suite 4-395 | Pleasanton Ca 94588 | 9254160700 | 9166346646 | 3401 Regatta Blvd. | Richmond, Ca 94804 | Nou, Bunma | 317016.75 | 17067.16 | 0 | 0 | 2026-02-20 | Bridge Railing, Mvp, Curb & Gutter, Sidewa | Contra Costa County In Pinole At Appian Way Overcrossing And At Crockett At Cummings Skyway Overcrossing. | 68 | 45 | 3167607.04 | 6368565.5 | 7022915.5 | 57777 | 2026-03-13 | 2025-04-15 | 2025-03-19 |  |  | 109 | 0 | 160 | 0 |  | X
04 | 04-4X3804 | 4X3804 | 04-CC-80-7.6/7.6 | 20.10.201130 |  | Golden State Bridge, Inc. | 3701 Mallard Drive | Benicia, Ca 94510 | 9253728000 | 5108676156 | 3401 Regatta Blvd. | Richmond, Ca 94804 | Faustin, Glenn | 0 | 194409.73 | 0 | 0 | 2025-12-20 | Bridge Repair | Cc-80-Pm 7.6, Br. No. 28 0146R Applian Way Overcrossing (West) Bridge Repair Dir'S Order Emergency F.A. | 4 | 2 | 194409.73 | 39933 | 7820000 | 60080 | 2026-02-19 | 2025-09-18 | 2025-07-24 |  |  | 5 | 0 | 140 | 0 |  | X
04 | 04-1Y7004 | 1Y7004 | 04-CC-80-13.8/14.1 |  |  | O.C. Jones & Sons, Inc. | 1520 Fourth Street | Berkeley Ca 94710 | 5105263424 | 5108676107 | 3401 Regatta Blvd. | Richmond, Ca 94804 | Halali, Behzad | 0 | 0 | 0 | 0 |  | Remove Ac Surfacing, Hma (Bridge) And Crac | Contra Costa And Solano Counties At Crockett And In Vallejo From Union Pacificrailroad Overhead To 0.8 Mile South Of Route 80/29 S | 0 | 0 | 0 | 1322484.65 | 1322484.65 | 60421 | 2026-09-30 | 2026-01-29 | 2025-12-29 |  |  | 0 | 0 | 30 | 0
04 | 04-0X6904 | 0X6904 | 04-CC-160-/.7 |  |  | Fbd Vanguard Construction, Inc. | 550 Greenville Road | Livermore Ca 94550 | 9252451300 | 5103857211 | 2525 Stanwell Drive, Suite 100 | Concord, Ca 94520 | Lee, Steven | 50000.28 | 0 | 0 | 0 | 2026-02-20 | Individual Slab Replacement, & Place Joint | Contra Costa County In And Near Antioch From 0.2 Mile West Of Route 4/160 Connector To 0.1 Mile South Of Antioch Bridge | 100 | 99 | 3393312.88 | 3330224 | 3330224 | 57955 | 2026-03-20 | 2025-04-21 | 2025-04-04 |  |  | 80 | 0 | 80 | 0 |  | X
04 | 04-0W0304 | 0W0304 | 04-CC-580-1.4/6.3 |  |  | Flatiron Dragados West Llc | 1200 Concord Avenue Ste 465 | Concord Ca 94520 | 5107191299 | 5108676107 | 3401 Regatta Blvd. | Richmond, Ca 94804 | Halali, Behzad | 230701.15 | 0 | 0 | 0 | 2026-01-20 | Replace Existing Toll Booths With New Ort | Contra Costa County In Richmond On Route 580 From 0.14 Mile North Of Bayview Ave Overcrossing To 0.1 Mile West Of Richmond-San Raf | 10 | 1 | 230701.15 | 18840000 | 19025000 | 60179 | 2027-01-04 | 2025-10-16 | 2025-10-16 |  |  | 27 | 0 | 265 | 0 |  | X
04 | 04-3G3644 | 3G3644 | 04-CC-580-6.1/7.8 |  |  | Studebaker Electric, Inc. | 3237 Rippey Road | Loomis Ca 95660 | 9162592395 | 5108676107 | 3401 Regatta Blvd | Richmond, Ca 94804 | Halali, Behzad | 65790 | 385663.25 | 0 | 0 | 2026-02-20 | Electrical Substations, Power Cables, And | Contra Costa And Marin Counties In Richmond And San Rafael From 0.3 Mile Westof Toll Plaza To 0.1 Mile West Of Main Street Undercr | 84 | 43 | 9815319.53 | 13371480 | 22950009.93 | 54946 | 2026-10-19 | 2024-01-23 | 2024-01-04 |  |  | 478 | 0 | 400 | 171
04 | 04-3X9804 | 3X9804 | 04-CC-680-8.0/8.2 | 20.20.201130 |  | Bridgeway Civil Constructors Inc | 3333 Vaca Valley Pkwy #2000 | Vacaville Ca 95688 | 7074557033 | 5104075226 | 2525 Stanwell, Suite 100, | Concord, Ca 94520 | Kim, Jaeyoon | 0 | 0 | 0 | 0 |  | Repair Roadway Settlement | Repair Roadway Settlement Replace Soundwall,Reconstruct Mgs Repair Slope Erosion And Other Work As Directed. | 0 | 0 | 0 | 16710 | 3470000 | 60348 | 2026-05-01 | 2025-09-19 | 2025-07-15 |  |  | 0 | 0 | 120 | 0
04 | 04-2Q6504 | 2Q6504 | 04-CC-680-/21 |  | ACIM-6801- (994)E | Bay Cities Paving & Grading, Inc. | 1450 Civic Ct Bldg B #400 | Concord Ca 94520 | 9256876666 | 5104218049 | 2525 Stanwell, Suite 100, | Concord, Ca 94520 | Kalantari, Ramin | 73415.36 | 0 | 0 | 0 | 2026-02-20 | Install Trash Capture Housing Devices, Mvp | Contra Costa County At Various Locations From Alameda County Line To Route 4/ 680 Separation | 62 | 46 | 2361966 | 4950981.06 | 5170981.06 | 57935 | 2026-09-08 | 2025-04-24 | 2025-03-27 |  |  | 130 | 0 | 210 | 0 |  | X
04 | 04-0AA244 | 0AA244 | 04-CC-680-/7.7 |  | ACIM- 680- (995)E | Bay Cities Paving & Grading, Inc. | 1450 Civic Ct. Bldg B #400 | Concord Ca 94520 | 9256876666 | 9252505611 | 5675 B Gibraltar Drive | Pleasanton, Ca 94588 | Dike, Eddie | 0 | 0 | 0 | 0 |  | Individual Slab Replacement, Cold Plan Ac | Contra Costa County In San Ramon And Danville From The Alameda County Line To 0.2 Mile North Of Diablo Road Undercrossing | 0 | 0 | 0 | 28968311.5 | 28968311.5 | 60364 | 2026-12-18 | 2026-01-26 | 2025-12-18 |  |  | 0 | 0 | 475 | 0
04 | 04-1X0304 | 1X0304 | 04-MRN-1-8.7/8.7 | 20.10.201130 |  | Terracon Constructors, Inc. | Po Box 276 | Healdsburg, Ca 95448 | 7074330323 | 5107746297 | 384 Bel Marin Keys Blvd,Ste200 | Novato, Ca 94949 | Russell, Steve | 0 | 160322.29 | 0 | 0 | 2025-07-25 | Repair Drainage, Sinkholes & Pavement | In Marin County On State Rte 1, Pm 8.69 Repair Drainage, Sinkholes And Pavement Settement Dir'S Order Emergency F.A. | 100 | 96 | 865960.78 | 6090 | 900000 | 55782 | 2026-01-31 | 2024-05-08 | 2024-03-08 |  |  | 47 | 0 | 30 | 0 |  | X
04 | 04-1J9604 | 1J9604 | 04-MRN-1-22.8/33 |  | ACST-P001- (693)E | O.C. Jones & Sons, Inc. | 1520 Fourth Street | Berkeley Ca 94710 | 5105263424 | 5105939011 | 384 Bel Marin Keys Blvd. | Novato, Ca 94949 | Wong, Andrew | 27618 | 133270.27 | 0 | 0 | 2026-02-20 | Cold Plane, Rhma, Hma, Mgs, Curb Ramps, Si | Marin County In And Near Point Reyes Station From Five Brooks To 1.9 Miles North Of Cypress Road And In And Near Tomales From 0.2 | 51 | 90 | 14937180.19 | 14588627.5 | 16293216.82 | 55409 | 2026-08-01 | 2024-03-07 | 2024-02-13 |  |  | 259 | 0 | 510 | 0 |  | X
04 | 04-3X2604 | 3X2604 | 04-MRN-1-/19.3 | 20.20.201130 |  | Marinship Development Interestllc | 1485 Bayshore Blvd, Ste 200, | San Francisco, Ca 94124 | 4157163965 | 5107746297 | 384 Bel Marin Keys Blvd, | Novato, Ca 94949-5361 | Russell, Steve | 0 | 112035.2 | 0 | 0 | 2026-01-20 | Install Gabion Basket Retaining Wall, Repa | Install Gabion Basket Retaining Wall, Repair Drainage | 60 | 67 | 584062.22 | 5809 | 875000 | 58275 | 2026-03-31 | 2025-04-16 | 2025-04-16 |  |  | 30 | 0 | 50 | 0 |  | X
04 | 04-2K7404 | 2K7404 | 04-MRN-37-11.2/14.5 |  | ACNH-P037- (219)E | Bay Cities Paving & Grading, Inc. | 1450 Civic Ct Bldg B #400 | Concord Ca 94520 | 9256876666 | 5106817264 | 384 Bel Marin Keys Blvd Ste200 | Novato, Ca 94949 | Prokop, Christopher | 155196.66 | 171490.14 | 0 | 0 | 2026-02-20 | Cold Plane Ac Pvmt, Place Rhma And Replace | Marin County In And Near Novato From Ignacio Overhead To Petaluma River Bridge | 42 | 86 | 9103299.78 | 9755877.29 | 10558995.07 | 57009 | 2026-11-20 | 2025-01-21 | 2024-12-20 |  |  | 157 | 0 | 370 | 0 |  | X
04 | 04-3X3604 | 3X3604 | 04-MRN-101-3.0/3 | 20.20.201130 |  | Maggiora & Ghilotti, Inc. | 555 Dubois St, | San Rafael, Ca 94901 |  | 5107746297 | 384 Bel Marin Keys Blvd. | Novato, Ca 94949 | Russell, Steve | 0 | 1586.31 | 0 | 0 | 2025-07-31 | Slide Repair | Sb Waldo Grade, Sausalito | 83 | 96 | 664112.61 | 3330 | 695000 | 58375 | 2025-07-31 | 2025-05-29 | 2025-02-14 |  |  | 50 | 0 | 60 | 0 |  | X
04 | 04-0K8004 | 0K8004 | 04-MRN-101-13.7/0 |  | ACNH-Q101- (428)E | Ghilotti Bros., Inc. | 525 Jacoby Street | San Rafael Ca 94901 | 4154547011 | 5103856980 | 384 Bel Marin Keys Blvd. | Novato, Ca 94949 | Habteselassie, Dawit | 32070 | 269713.54 | 0 | 31150 | 2026-02-20 | Construct Roundabout, Curb Ramps And Sw, S | Marin County In San Rafael At Freitas Parkway Overcrossing | 30 | 53 | 3680731.15 | 6242312 | 6963110.95 | 57259 | 2026-10-16 | 2025-02-27 | 2025-02-05 |  |  | 104 | 0 | 345 | 0 |  | X
04 | 04-264724 | 264724 | 04-MRN-101-20.8/27.1 |  | CML -6204- (132)N | Ghilotti Construction Company,Inc. | 2301 Kerner Blvd #E | Santa Rafael, Ca 94901 | 4152561525 | 5104969271 | 384 Bel Marin Keys Blvd. | Ste 200 Novato, Ca 94949 | La Serna, Fabio | 271406.25 | 224035.18 | 8015.5 | 0 | 2026-02-20 | Roadway And Bridge Widening For Hov | In Marin County In And Near Novato From 0.1 Mile South Of Franklin Avenue Overhead To 0.5 Mile South Of San Antonio Creek Bridge | 67 | 97 | 87400870.75 | 78860144.47 | 92080602.22 | 42410 | 2026-07-07 | 2022-05-13 | 2022-04-26 |  |  | 703 | 0 | 1000 | 52 |  | X
04 | 04-2X9404 | 2X9404 | 04-MRN-101-/9.3 | 20.20.201130 |  | Ghilotti Bros, Inc | 525 Jacoby Street | San Rafael, Ca 94901 | 4154547011 | 5107746297 | 384 Bel Marin Keys Blvd. Suite 200 | Novato, Ca 94949 | Russell, Steve | 0 | 7532.5 | 0 | 0 | 2026-01-20 | Clear Debris From Landslide, Regrade Slope | Clear Debris From Landslide, Regrade Slope And Install Erosion Control | 95 | 82 | 1108766.11 | 8327 | 1355000 | 57096 | 2026-01-31 | 2024-11-26 | 2024-11-26 |  |  | 57 | 0 | 60 | 0 |  | X
04 | 04-3X1504 | 3X1504 | 04-MRN-580-6.0/7.8 | 20.20.201130 |  | Studebaker Electric, Inc | 3237 Rippey Rd, Ste 100, | Loomis, Ca 95650 | 9162592395 | 5108676107 | 3401 Regatta Blvd, | Richmond, Ca 94804-4594 | Halali, Behzad | 0 | 59166.35 | 0 | 0 | 2026-02-27 | Replace Stolen Wires | Rsr Bridge Replace Stolen Wires | 100 | 75 | 759583.54 | 11100 | 1008500 | 58657 | 2026-09-30 | 2025-06-10 | 2025-02-14 |  |  | 131 | 0 | 40 | 0
04 | 04-4J4114 | 4J4114 | 04-NAP-29-1.7/0 |  |  | John Semsen Landscaping Co., Inc. | 21161 Lyons Bald Mountain Roa | Sonora Ca 95370 | 2097434911 | 5108674515 | 3401 Regatta Blvd | Richmond, Ca 94804 | Simpson, John | 4050 | 0 | 0 | 0 | 2026-02-20 | Maintain Existing Planted Area. | Napa County In And Near American Canyon Atrio Del Mar And At 0.4 Mile South Of Northkelly Road | 4 | 34 | 97945 | 276870 | 284870 | 60221 | 2029-01-30 | 2025-11-26 | 2025-10-28 |  |  | 32 | 0 | 780 | 0 |  | X
04 | 04-281204 | 281204 | 04-NAP-29-5.0/6.7 | HE11 | ACNH-X055- (060)E | Ghilotti Construction Company,Inc. | 246 Ghilotti Ave | Santa Rosa Ca 95407 | 7075851221 | 9252505595 | 324 Campus Lane Ste T | Fairfeild, Ca 94534 | Isada, Darren | 0 | 18175.55 | 0 | 0 | 2026-02-20 | Intersection Improvements | In Napa County At The Intersection Of Routes 29/12 And Route 221 | 100 | 99 | 36025803.69 | 31606566.6 | 36183921.42 | 42412 | 2026-10-30 | 2022-05-13 | 2022-03-21 |  |  | 747 | 0 | 710 | 12 |  | X
04 | 04-2Q6104 | 2Q6104 | 04-NAP-29-7.3/13.5 |  | ACNH-P029- (155)E | Granite Rock Company | 5225 Hellyer Avenue, Suite 22 | San Jose Ca 95138 | 4085741400 | 9252606460 | 324 Campus Lane, Suite T | Fairfield, Ca 94534 | Brar, Paramdeep | 1850 | 6702.83 | 173149.69 | 0 | 2026-02-20 | Cold Plane, Rhma Overlay, Install Mgs, Cur | Napa County In And Near Napa From 0.2 Milenorth Of Napa River Bridge Overhead To 0.1Mile South Of Sierra Avenue. | 90 | 94 | 16947499.84 | 17680347.75 | 17438751.36 | 56886 | 2026-03-31 | 2024-11-26 | 2024-11-04 |  |  | 208 | 0 | 230 | 0 |  | X
04 | 04-0Q8204 | 0Q8204 | 04-NAP-29-11.6/13 |  | PTNH-P029- (153)E | Ranger Pipelines Incorporated | 833 Featherstone Road | Rockford Il 61104 | 4158223700 | 5102246309 | 324 Campus Lane Suite T | Fairfield, Ca 94534 | Patenia, Danilo | 236936.5 | 23493.25 | 0 | 0 | 2026-02-20 | Const Drainage Systems, Mod Pumping Equipm | Napa County In Napa From 0.1 Mile North Offirst Street Overcrossing To 0.1 Mile South Of Trancas Street Overcrossing | 42 | 98 | 22154661.51 | 23068709 | 22547361.41 | 56536 | 2026-06-30 | 2024-10-01 | 2024-08-29 |  |  | 196 | 0 | 470 | 0 |  | X
04 | 04-0K6304 | 0K6304 | 04-NAP-29-16.4/19 |  |  | Gordon N. Ball, Inc. | 1777 Oakland Blvd. Ste 300 | Walnut Creek, Ca 94596 | 9258385675 | 5102246309 | 324 Campus Lane, Suite T | Fairfield, Ca 94534 | Patenia, Danilo | 3960 | 0 | 0 | 0 | 2025-11-07 | Bridge Rail Replacement And Shoulder Widen | Napa County Near Yountville At Various Locations From 0.1 Mile South Of Dry Creekbridge To 0.1 Mile North Of California Drive Unde | 100 | 100 | 3436715.53 | 3246583 | 3420580.7 | 51104 | 2025-11-07 | 2023-07-14 | 2023-06-27 | 2026-02-02 |  | 323 | 0 | 440 | 0 |  | X
04 | 04-4X4904 | 4X4904 | 04-NAP-29-19.8/21.5 | 20.10.201130 |  | Team Ghilotti, Inc. | 2531 Petaluma Blvd. So. | Petaluma, Ca 94952 | 7077638700 | 5102246309 | 324 Campus Lane, Ste T | Fairfield, Ca 94534 | Patenia, Danilo | 0 | 506463.96 | 0 | 0 | 2026-02-18 | Pavement Repair | In Napa Co, Rte 29 Pavement Repair, Hma-A Paving,Cold Plane, Digouts, Polyuretahane Injection,Gpi Class Ii Pavement Grid Dir'S Ord | 38 | 28 | 659119.85 | 14910 | 2370000 | 60300 | 2026-07-31 | 2026-01-08 | 2025-11-19 |  |  | 23 | 0 | 60 | 0 |  | X
04 | 04-4X5304 | 4X5304 | 04-NAP-29-23.5/23.5 | 20.10.201130 |  | Granite Rock Company | 5225 Hellyer Ave., Ste 220 | San Jose, Ca 95138 | 4085741400 | 9252606460 | 324 Compus Lane, Suite T | Fairfield, Ca 94534 | Brar, Paramdeep | 0 | 690460.68 | 0 | 0 | 2026-01-05 | Dir'S Order Emergency F.A. | In Napa Co. Hwy 29 Pm 23.54 Remove And Existing Culvert And Replace With Cast In Place Box Culvert And Repair Roadway Replace Culv | 0 | 38 | 690460.68 | 5508 | 1821000 | 60265 | 2026-03-31 | 2025-12-19 | 2025-10-15 |  |  | 0 | 0 | 60 | 0 |  | X
04 | 04-3X4904 | 3X4904 | 04-NAP-29-45.5/45.5 | 20.20.201130 |  | Piazza Construction | 5200 Carroll Road, | Petaluma, Ca 94952 | 7078763410 | 5102246309 | 324 Campus Lane, | Fairfield, Ca 94534 | Patenia, Danilo | 0 | 33836.76 | 0 | 0 | 2026-01-20 | Install Rsp, Repair Drainage | Calistoga Install, Rsp Repair Drainage Install Rsp, Repair Drainage | 100 | 75 | 455608.12 | 4314 | 645000 | 58215 | 2026-03-31 | 2025-05-14 | 2025-04-17 |  |  | 31 | 0 | 30 | 0
04 | 04-0Q8304 | 0Q8304 | 04-NAP-29-46.1/0 |  |  | Gordon N. Ball, Inc. | 333 Camille Avenue | Alamo Ca 94507 | 9258385675 | 9252606460 | 324 Campus Lane, Suite T | Fairfield, Ca 94534 | Brar, Paramdeep | 2600 | 0 | 0 | 0 | 2025-12-20 | Soldier Pile, Conc Backfill, Hma, Timber L | Napa County Near Calistoga At 2.5 Miles South Of Lake County Line | 87 | 98 | 1041131.5 | 1018909 | 1033909 | 56124 | 2026-07-09 | 2024-07-12 | 2024-06-18 |  |  | 299 | 0 | 345 | 0 |  | X
04 | 04-4G21A4 | 4G21A4 | 04-NAP-121-.5/1 |  | HSST-P121- (133)EST - - ( ) | John Semsen Landscaping Co., Inc. | 21161 Lyons Bald Mountain Roa | Sonora Ca 95370 | 2097434911 | 5108674515 | 3401 Regatta Blvd | Richmond Ca 94804 | Simpson, John | 3840 | 0 | 0 | 0 | 2026-02-20 | Maintain Existing Planted Area. | Napa County Near Napa From 0.2 Mile South To 0.3 Mile North Of Huichica Creek Bridge | 49 | 65 | 261359.06 | 381240 | 401240 | 54884 | 2028-04-18 | 2023-12-20 | 2023-11-28 |  |  | 521 | 0 | 1060 | 0 |  | X
04 | 04-0Q7904 | 0Q7904 | 04-NAP-121-13.4/20.7 |  | ACST-S121- (018)E | Gordon N. Ball, Inc. | 333 Camille Avenue | Alamo, Ca 94507 | 9258385675 | 5102246309 | 324 Campus Lane, Suite T | Fairfield, Ca 94534 | Patenia, Danilo | 0 | 0 | 0 | 0 |  | Install Sheet Pile Walls, Rock Slope Prote | Napa County Near Napa At Various Locationsfrom 0.7 Mile West Of Wild Horse Valley Road To 1 Mile South Of Route 128 | 0 | 0 | 0 | 1566865 | 1566865 | 60245 | 2026-08-13 | 2025-11-18 | 2025-10-22 |  | S | 0 | 0 | 400 | 0
04 | 04-4G84A4 | 4G84A4 | 04-NAP-128-20.1/20.4 |  |  | Bortolussi & Watkin, Inc. | 77 Larkspur Street | San Rafael Ca 94901 | 4154534675 | 5107746276 | 3401 Regatta Blvd | Richmond Ca.94804 | Luckel, Kasaia | 6652.76 | 0 | 0 | 0 | 2026-02-20 | Environmental Permit Mitigation & | Near Napa, At Capell Creek Bridge No. 21-0078. Environmental Mitigation And Plant Establishment For Rehabilitate Bridge Project Ea | 71 | 62 | 289831.6 | 445858 | 463858 | 45905 | 2027-05-11 | 2022-11-21 | 2022-11-17 |  |  | 736 | 0 | 1040 | 0 |  | X
04 | 04-3X0204 | 3X0204 | 04-NAP-128-/25.9 | 20.20.201130 |  | Valentine Corporation | 111 Pelican Way, | San Rafael, Ca 94901 | 4154533732 | 9252505595 | 324 Campus Lane, Suite T, | Fairfield, 94534 | Isada, Darren | 0 | 271593.75 | 0 | 0 | 2026-02-18 | Slipout And Drainage Repair | At Wragg Creek At Wragg Creek | 79 | 43 | 1156524.85 | 14021 | 2665000 | 57317 | 2026-04-30 | 2025-02-20 | 2025-02-20 |  |  | 79 | 0 | 100 | 0
04 | 04-1X1004 | 1X1004 | 04-SCL-9-4.0/4 | 20.20.201130 |  | Qa Constructors, Inc | 850 S Van Ness Ave., Ste 35 | San Francisco, Ca 94110 | 4153407283 | 5108676047 | 1007 Knox Ave. | San Jose, Ca 95122 | Nikzad, Ali | 0 | 130826.65 | 0 | 0 | 2025-12-15 | Stabilize Slope And Remove Debris | On Rte 9 In Santa Clara Co Remove Debris, Clean Drainage System, And Regrade Slope Dir'S Order Emergency F.A. | 100 | 89 | 10574350.37 | 7454 | 11885000 | 55686 | 2026-06-24 | 2024-04-24 | 2024-02-19 |  |  | 80 | 0 | 50 | 0 |  | X
04 | 04-1X4304 | 1X4304 | 04-SCL-9-4.5/5.5 | 20.10.201130 |  | Qa Contructors, Inc. | 800 S Van Ness, Ste 35 | San Francisco, Ca 94110 | 4153407283 | 4085954015 | 1007 Knox Ave. | San Jose, Ca 95122 | Malonzo, Gene Earl | 0 | 36053.07 | 0 | 0 | 2025-12-02 | Repair Slide | In Santa Clara Co From 0.35 Mile South Of Saratoga Creek Br. No.37-0074 To 37-0075 Repair Slope And Roadway, Adjust Drainage Dir'S | 85 | 94 | 1831634.26 | 11611 | 1945000 | 57256 | 2025-12-21 | 2024-06-28 | 2024-03-13 |  |  | 85 | 0 | 100 | 0 |  | X
04 | 04-3G6304 | 3G6304 | 04-SCL-9-4.9/4.9 |  |  | Myers & Sons Construction, Llc | 45 Morrison Ave | Sacramento Ca 95838 | 4243356087 | 5108676009 | 1007 Knox Ave | San Jose Ca, 95122 | Le, Tuan | 10315.15 | 0 | 0 | 0 | 2025-11-25 | Cidh Piling, Structural Steel, Bridge Rail | Santa Clara County Near Saratoga At Saratoga Creek | 100 | 100 | 14764632.58 | 11925924.75 | 14870180.23 | 46064 | 2025-11-25 | 2022-11-23 | 2022-11-08 | 2026-01-26 |  | 466 | 0 | 825 | 52 |  | X
04 | 04-0P9704 | 0P9704 | 04-SCL-17-6.2/0 |  |  | Ghilotti Construction Company,Inc. | 246 Ghilotti Avenue | Santa Rosa Ca 95407 | 4083146349 | 5107159940 | 1007 Knox Avenue | San Jose, Ca 95122 | Farsipour Naghibi, Sina | 84180 | 111875.46 | 0 | 0 | 2026-02-20 | Replace Bridge Rails, Sidewalk, And Mainte | Santa Clara County In Los Gatos At Santa Cruz Avenue Undercrossing And At Main Street Overcrossing. | 100 | 97 | 5077008.21 | 4723427.46 | 5217327.46 | 56590 | 2026-03-05 | 2024-10-01 | 2024-08-30 |  |  | 180 | 0 | 180 | 0 |  | X
04 | 04-3Y2904 | 3Y2904 | 04-SCL-17-/3.5 | 20.20.201130 |  | Granite Rock Company | 5225 Hellyer Ave, Suite 220 | San Jose, Ca 95138 | 4085741400 | 5108676047 | 1007 Knox Avenue | San Jose, Ca | Nikzad, Ali | 11419.47 | 1875.5 | 0 | 0 | 2024-11-11 | Guardrail, Krail, Concrete Barrier | Scl 17 - Guardrail Repairs, Concrete Barriscl 17 - Guardrail Repairs, Concrete Barriscl 17 - Guardrail Repairs, Concrete Barridir' | 100 | 100 | 3818455.37 | 12279 | 4078000 | 50124 | 2024-11-11 | 2023-06-13 | 2023-04-17 | 2026-01-27 |  | 200 | 0 | 100 | 0 |  | X
04 | 04-0P9804 | 0P9804 | 04-SCL-82-11.4/26.3 |  |  | Bugler Construction, Inc. | 4847 Hopyard Rd. Suite 4-395 | Pleasanton Ca 94588 | 9254160700 | 5103857130 | 1007 Knox Ave | San Jose, Ca 95122 | Nguyen, Hung | 229482 | 197500 | 0 | 0 | 2025-12-20 | Replace Bridge Rail, Curb Ramp, Sidewalk, | Santa Clara County At Various Locations From De La Cruz Boulevard Overcrossing To San Francisquito Creek Bridge | 93 | 99 | 8695248.71 | 8177636.5 | 8563636.5 | 55846 | 2026-03-30 | 2024-05-13 | 2024-04-04 |  |  | 210 | 0 | 225 | 0 |  | X
04 | 04-4J89U4 | 4J89U4 | 04-SCL-82-18.2/26.4 |  | ACNH-P082- (032)E | O.C. Jones & Sons, Inc. | 1520 Fourth Street | Berkeley Ca 94710 | 5105263424 | 5108676009 | 1007 Knox Ave | San Jose Ca 96122 | Le, Tuan | 40049.98 | 73788.6 | 0 | 0 | 2026-02-20 | Cold Plane Ac, Rhma, Slab Repl, Curb Ramps | Santa Clara County At Various Locations From Knickerbocker Drive In Sunnyvale To San Mateo County Line In Palo Alto | 85 | 97 | 35105191.83 | 27269716.43 | 35427496.49 | 52484 | 2026-03-30 | 2023-09-13 | 2023-08-17 |  |  | 298 | 0 | 300 | 50 |  | X
04 | 04-4X5504 | 4X5504 | 04-SCL-82-18.8/18.8 | 20.20.201130 |  | Myers & Sons Construction,Llc. | 45 Morrison Ave. | Sacramento, Ca 95838 | 9162839950 | 5108676009 | 1007 Knox Ave. | San Jose, Ca 95135 | Le, Tuan | 0 | 0 | 0 | 0 |  | Bridge Deck Hole Repair | In Santa Clara Co. Rte 82 At Pm 18.82 Remove Concrete, Repair Bridge Deck, Add Rebar & Recast Portions Of Damaged Deck Dir'S Order | 0 | 0 | 0 | 4080 | 665000 | 60368 | 2026-03-25 | 2026-01-06 | 2025-11-14 |  |  | 0 | 0 | 30 | 0
04 | 04-4J9104 | 4J9104 | 04-SCL-87-/6.1 |  | ACNH-P087- (034)E | O.C. Jones & Sons, Inc. | 1520 Fourth Street | Berkeley Ca 94710 | 5105263424 | 5108676047 | 7007 Knox Ave | San Jose, Ca 95122 | Nikzad, Ali | 2400 | 16618.56 | 0 | 0 | 2026-02-20 | Cold Plane Ac, Paving With Rhma, Upgrade M | Santa Clara County In San Jose From Route 85/87 Separation To 0.1 Mile North Of Julian Street Undercrossing | 68 | 96 | 55750839.65 | 51342522.85 | 56863192.3 | 49524 | 2026-12-15 | 2023-05-22 | 2023-04-19 |  |  | 424 | 0 | 620 | 0 |  | X
04 | 04-3Q6004 | 3Q6004 | 04-SCL-101-.7/19.2 |  |  | Truesdell Corporation Of California, Inc. | 1310 W. 23Rd Street | Tempe Az 85282 | 6024371711 | 5107159940 | 1007 Knox Ave | San Jose Ca 95122 | Farsipour Naghibi, Sina | 0 | 108070.32 | 0 | 0 | 2025-07-20 | Place Polyester Concrete Overlay And Remov | Santa Clara County At Various Locations | 100 | 93 | 3031019.97 | 3093093 | 3202093 | 51384 | 2025-02-07 | 2023-07-25 | 2023-06-27 |  | S | 160 | 0 | 160 | 0 |  | X
04 | 04-0X6304 | 0X6304 | 04-SCL-101-4.5/17.5 |  |  | Fbd Vanguard Construction, Inc. | 550 Greenville Road | Livermore Ca 94550 | 9252451300 | 5104969525 | 1007 Knox Ave | San Jose, Ca 95122 | Kabbani, Muhieddine | 5875 | 916951 | 0 | 0 | 2026-01-20 | Individual Slab Replacement (Rsc). | Santa Clara County From 0.4 Mile South Of Monterey Road Undercrossing To 0.1 Mile South Of Cochrane Road Overcrossing | 45 | 98 | 2387716 | 1449740 | 2413033 | 59376 | 2026-02-20 | 2025-06-17 | 2025-05-22 |  |  | 27 | 0 | 60 | 0 |  | X
04 | 04-4J9304 | 4J9304 | 04-SCL-101-30.7/31.1 |  | ACNH-Q101- (397)E | Bortolussi & Watkin, Inc. | 77 Larkspur Street | San Rafael Ca 94901 | 4154534675 | 9166346562 | 3401 Regatta Blvd | Richmond, Ca 94804 | Cruz, Albert | 3937.87 | 0 | 0 | 0 | 2026-02-20 | Upgrade Irrigation System For | In Santa Clara County, In San Jose From 0.3 Mile South To 0.1 Mile North Of The Yereba Buena Road Uc And 0.1 Mile South Of East R | 98 | 79 | 1405135.15 | 1720610 | 1774610 | 42013 | 2026-04-10 | 2021-10-22 | 2021-09-27 |  |  | 891 | 0 | 910 | 0
04 | 04-2Y8504 | 2Y8504 | 04-SCL-101-33.0/49 | 20.20.201130 |  | Bugler Construction Inc. | 4847 Hopyard Rd, Suite 4-395 | Pleasanton, Ca 94588 | 9254160700 | 4085954015 | 1007 Knox Ave, | San Jose, Ca | Muench, John | 10737.2 | 0 | 0 | 0 | 2024-09-13 | Repair Failed Culvert | Scl 101 At Three Locations Scl 101 At Three Locations Scl 101 At Three Locations Scl 101 At Three Locations | 100 | 100 | 1670132.58 | 15790 | 1785000 | 47924 | 2024-09-13 | 2023-03-20 | 2023-01-06 | 2026-02-08 | S | 75 | 0 | 80 | 0 |  | X
04 | 04-1Y6204 | 1Y6204 | 04-SCL-101-38.0/38.1 | 20.80.010 |  | Pump Repair Service Co., Inc. | 405 Allan St. | San Francisco, Ca 94134 | 4154672150 | 4085954003 | 1007 Knox Ave. | San Jose, Ca 95122 | Patel, Nim | 0 | 416673.3 | 0 | 0 | 2025-09-04 | Replace Pumps | Replace Pumps Route 101 And 10Th Street Pump Station Dir'S Order Emergency F.A. | 0 | 43 | 1454231.74 | 35475 | 3795173 | 47848 | 2025-10-15 | 2023-03-10 | 2023-01-18 |  |  | 0 | 0 | 60 | 0 |  | X
04 | 04-1J5674 | 1J5674 | 04-SCL-101-51.7/52.5 |  |  | Marina Landscape Inc. | 3707 W Garden Grove Blvd | Orange Ca 92868 | 7149396600 | 9166346562 | 3401 Regatta Blvd. | Richmond, Ca 94804 | Cruz, Albert | 5719.2 | 0 | 0 | 0 | 2026-02-20 | Highway Planting And Irrigation Systems. | Santa Clara And San Mateo Counties At Various Locations From 0.3 Mile South Of Oregon Expressway Overcrossing To 0.3 Milesouth Of | 0 | 0 | 5785127.62 | 5958858.5 | 6318858.5 | 54286 | 2028-09-15 | 2023-11-30 | 2023-10-25 |  |  | 358 | 0 | 1000 | 0 | X | X
04 | 04-4X8504 | 4X8504 | 04-SCL-101-/30 | 20.20.201130 |  | Redgwick Construction Co. | 21 Hegenberger Court | Oakland, Ca 94621 | 9254706675 | 5104069696 | 1007 Knox Ave. | San Jose, Ca 95122 | Ngo, Hung T | 0 | 0 | 0 | 0 |  | Pavement Settlement Repair | In San Jose Near 101/880 Interchange Embankment Slipout And Pavement Settlementrepair Dir'S Order Emergency F.A. | 0 | 0 | 0 | 6132 | 907000 | 60442 | 2026-07-31 | 2026-02-06 | 2025-12-05 |  |  | 0 | 0 | 25 | 0
04 | 04-1W1904 | 1W1904 | 04-SCL-101-/2.7 |  | ACNH-Q101- (450)E | Desilva Gates Construction, Llc | 11555 Dublin Blvd. | Dublin Ca 94568 | 5105263424 | 5108676047 | 1007 Knox Ave. | San Jose, Ca 95122 | Nikzad, Ali | 0 | 0 | 0 | 0 |  | Cold Plane Ac Pvmt & Rhma Overlay, Const M | Santa Clara County From The San Benito County Line To 0.5 Mile South Of Route 25/101 Separation | 0 | 0 | 0 | 2418814 | 2418814 | 60194 | 2026-05-08 | 2025-11-10 | 2025-10-21 |  | S | 0 | 0 | 110 | 0
04 | 04-2Y7404 | 2Y7404 | 04-SCL-152-12.6/12.6 | 20.20.201130 |  | Absl Construction | 29393 Pacific St. | Hayward, Ca 94544 |  | 4085954019 | 1007 Knox Ave., | San Jose, Ca | Khan, Arif | 11830 | 0 | 0 | 0 | 2024-09-13 | Remove Silt/Sediment From Creek, Clear Cul | Scl 152 @ Johnson Creek - Blocked Culverts And Channel | 100 | 100 | 2090808.1 | 11830 | 2264000 | 47385 | 2024-09-13 | 2023-02-14 | 2022-12-23 | 2026-02-17 |  | 59 | 0 | 60 | 0 |  | X
04 | 04-0Q05U4 | 0Q05U4 | 04-SCL-152-16.8/23.3 |  |  | Pacific Infrastructure Construction, Llc | 871 Cotting Court Ste A | Vacaville Ca 95688 | 7074493604 | 5104969525 | 1007 Knox Ave. | San Jose, Ca 95122 | Kabbani, Muhieddin | 0 | 120885.93 | 17500 | 0 | 2026-01-20 | Excavation, Hma, Drainage, Rsp, Signing, M | Santa Clara County Near Gilroy At Various Locations From 1.9 Miles East Of Bloomfield Avenue To 0.1 Mile West Of Casade Fruta Unde | 82 | 100 | 5454166.31 | 5130777.7 | 5812068.55 | 56808 | 2025-12-19 | 2024-12-03 | 2024-11-06 |  |  | 98 | 0 | 120 | 0 |  | X
04 | 04-2Y5404 | 2Y5404 | 04-SCL-237-1.5/6.4 |  |  | Granite Rock Company | 5225 Hellyer Avenue, Suite 22 | San Jose Ca 95138 | 4085741415 | 5104069696 | 1007 Knox Ave | San Jose, Ca 95122 | Ngo, Hung T | 766.57 | 0 | 0 | 0 | 2025-11-20 | Cold Plane Ac Pavement, Place Hma (A), & P | Santa Clara County On Route 237 At Variouslocations From Middlefield Road Undercrossing To Guadalupe River Bridge And On Route 88 | 85 | 99 | 1744230.47 | 1686420 | 1686420 | 59199 | 2025-12-15 | 2025-06-10 | 2025-05-06 |  |  | 34 | 0 | 40 | 0 |  | X
04 | 04-0Y5004 | 0Y5004 | 04-SCL-280-2.9/2.9 | 20.20.201130 |  | O.C. Jones & Sons, Inc. | 1520 Fourth St. | Berkeley, Ca 94710 | 5105263424 | 4085954003 | 1007 Knox Ave. | San Jose, Ca 95122 | Patel, Nim | 0 | 479050.97 | 0 | 0 | 2026-01-26 | Repair/Replace Damaged Pump | In San Jose, Santa Clara County, Near Route 87 Repair/Replace Damaged Pump Dir'S Order Emergency F.A. | 0 | 76 | 1664508.17 | 6095 | 2185000 | 42188 | 2026-05-29 | 2022-03-03 | 2022-01-15 |  |  | 0 | 0 | 150 | 0 |  | X
04 | 04-3Y0004 | 3Y0004 | 04-SCL-280-4.6/4.6 | 20.20.201130 |  | Pump Repair Service Co., Inc. | Po Box 34327 | San Francisco, Ca 94134 | 4154672150 | 4085954003 | 1007 Knox Ave | San Jose Ca | Patel, Nim | 0 | 286979.86 | 0 | 0 | 2026-01-26 | Repair And Replace Damaged Pumps | Scl 280 At Winchester Blvd - Groundwater Pump Repair Dir'S Order Emergency F.A. | 0 | 47 | 1310973.7 | 32250 | 2810000 | 48584 | 2026-03-31 | 2023-04-17 | 2023-01-12 |  |  | 0 | 0 | 100 | 0 |  | X
04 | 04-1Q4604 | 1Q4604 | 04-SCL-280-/2.7 |  | ACIM-2801- (992)E | O.C. Jones & Sons, Inc. | 1520 Fourth Street | Berkeley Ca 94710 | 5108093490 | 4085954003 | 1007 Knox Ave. | San Jose, Ca 96122 | Patel, Nim | 785810 | 110008.46 | 0 | 0 | 2026-02-20 | Rhma-G Surfacing And Construct Bridge Appr | Santa Clara County In San Jose From Route 280/680/101 Separation To 0.2 Mile West Ofbird Avenue Overcrossing | 63 | 83 | 17975766.82 | 20793388.4 | 21582388.4 | 55845 | 2026-07-31 | 2024-06-17 | 2024-05-02 |  |  | 158 | 0 | 250 | 0 |  | X
04 | 04-0X2604 | 0X2604 | 04-SCL-280-/3.8 | 20.10.201131 |  | Pump Repair Service Co., Inc. | 405 Allan St | San Francisco, Ca 94134 | 4154672150 | 5104069696 | 1007 Knox Ave. | San Francisco, Ca 94134 | Ngo, Hung T | 0 | 28082.97 | 0 | 0 | 2025-08-14 | Repair/Replace Pumps | Southwest Pump Plant Replace Existing Pumps Including Mechanical And Electrical Elements Dir'S Order Emergency F.A. | 0 | 24 | 347448.74 | 18150 | 1450000 | 56418 | 2025-12-31 | 2024-07-12 | 2024-07-12 |  |  | 0 | 0 | 150 | 0 |  | X
04 | 04-4X0204 | 4X0204 | 04-SCL-880-1.7/1.9 | 20.20.201130 |  | Absl Construction | 29393 Pacific St. | Hayward, Ca 94544 | 5107270900 | 5104069696 | 1007 Knox Ave. | San Jose, Ca 95122 | Ngo, Hung T | 0 | 36004.28 | 0 | 0 | 2025-12-31 | Repair Sinkhole | On Rte 880 In Santa Clara County At The Alameda Nb Offramp And Sb Onramp Repair Sinkhole, Settlement & Drainage Dir'S Order Emerge | 0 | 18 | 307536.8 | 10230 | 1692500 | 59715 | 2026-06-30 | 2025-08-11 | 2025-06-03 |  |  | 0 | 0 | 40 | 0 |  | X
04 | 04-0AA624 | 0AA624 | 04-SF-1-.9/4.1 |  | ACNH-P001- (709)E | Granite Rock Company | 5225 Hellyer Avenue, Suite 22 | San Jose Ca 95138 | 4085741415 | 5107156644 | 585 Linda Mar Blvd. | Pacifica, Ca 94044 | Koos, Charles | 105502.4 | 19687.91 | 0 | 0 | 2026-02-20 | Cold Plane Ac Pvmt, Hma (Type A) And Indiv | The City And County Of San Francisco From Holloway Avenue To Lincoln Way And At California Street | 18 | 34 | 3773158.71 | 11080899.5 | 11180899.5 | 60176 | 2026-07-23 | 2025-09-16 | 2025-07-23 |  |  | 36 | 0 | 200 | 0 |  | X
04 | 04-0Q0204 | 0Q0204 | 04-SF-80-3.8/5 |  | ACBR-NHX0-7(505)4E | Myers - Acc A Joint Venture | 45 Morrison Avenue | Sacramento Ca 95838 | 9162839984 | 9166343561 | 585 Linda Mar Blvd. | Pacifica, Ca 94044 | Giang, Biana | 1335980.27 | 0 | 0 | 0 | 2026-02-20 | Polyester Concrete Overlay, Joint Seals, G | In The City And County Of San Francisco Onroute 80 From Western Of Bayshore To Sfobbapproach Upper Deck And On Route 101 From 0.3 | 5 | 3 | 1553948.83 | 58000000 | 58120000 | 60340 | 2027-09-01 | 2025-12-03 | 2025-11-17 |  |  | 21 | 0 | 405 | 0 |  | X
04 | 04-0X9104 | 0X9104 | 04-SF-80-3.9/4.5 | 20.20.201130 |  | Yerba Buena Engineering & Construction, Inc. | 1340 Egbert Ave. | San Francisco, Ca 94124 | 4158224400 | 5108676069 | 585 Linda Mar Blvd. | Pacifica, Ca 94044 | Sihra, Chetan | 0 | 152550.6 | 0 | 0 | 2025-12-01 | Repair Bridge Railing | Replace Damaged Concrete Barrier And Tubular Railing On Highways 80 And 101 Dir'S Order Emergency F.A. | 83 | 98 | 2913809.53 | 17937 | 2960000 | 55681 | 2026-03-31 | 2024-04-17 | 2024-04-02 |  |  | 50 | 0 | 60 | 0 |  | X
04 | 04-1Y7204 | 1Y7204 | 04-SF-80-5.7/7.7 |  |  | Golden State Bridge, Inc. | 3701 Mallard Drive | Benicia Ca 94510 | 9253728000 | 5108674545 | 575 Linda Mar Blvd. | Pacifica, Ca 94044 | Larwin, Thomas | 899499.7 | 16036.67 | 0 | 0 | 2026-02-20 | Structural Concrete, Bridge (Rsc) & Joint | The City And County Of San Francisco At Various Locations From 0.1 Mile East Of Fremont Street Off-Ramp To 0.2 Mile West Of Yerba | 24 | 39 | 5887058.82 | 14148449 | 15144832.95 | 58738 | 2027-07-06 | 2025-06-03 | 2025-05-16 |  |  | 108 | 0 | 450 | 0 |  | X
04 | 04-3G4874 | 3G4874 | 04-SF-80-5.7/7.7 |  |  | F.D. Thomas, Inc. | 200 Harris Ave | Sacramento Ca 95838 | 5416643010 | 9499226576 | 575 Linda Mar Blvd | Pacifica, Ca 94044 | Plata, Omar | 0 | 0 | 0 | 0 |  | Repair Spall, Clean And Paint Structural S | The City And County Of San Francisco From 0.1 Mile East Of Fremont Street Off-Ramp To 0.2 Mile West Of Yerba Buena Island Off-Ramp | 0 | 0 | 0 | 148230545 | 148230545 | 60412 | 2031-06-09 | 2026-02-10 | 2025-12-23 |  |  | 0 | 0 | 1350 | 0
04 | 04-1Y5004 | 1Y5004 | 04-SF-280-2.7/4.2 |  |  | Mccuen Construction, Inc. | 3269 Swetzer Road | Loomis Ca 95650 | 9166527824 | 5109088819 | 585 Linda Mar Blvd. | Pacifica, Ca 94044 | Kardavani, Kayvan | 0 | 17661.91 | 0 | 0 | 2025-09-20 | Place Polyester Concrete Overlay, And Repl | The City And County Of San Francisco At Various Locations From Monterey Boulevard On-Ramp Overcrossing To Route 280/101 Separation | 99 | 94 | 5400266.43 | 5386262.78 | 5651562.78 | 56158 | 2026-01-30 | 2024-07-12 | 2024-06-17 | 2026-02-05 |  | 89 | 0 | 90 | 0 |  | X
04 | 04-4X1404 | 4X1404 | 04-SF-280-6.6/7.2 | 20.10.201130 |  | Golden State Bridge, Inc. | 3701 Mallard Drive | Benicia, Ca 94510 | 9253728008 | 5107156644 | 585 Linda Mar Blvd | Pacifica, Ca 94044 | Koos, Charles | 0 | 151671.83 | 0 | 0 | 2025-10-24 | China Basin Viaduct Girder Replacement | Replace Cracked Girder At China Basin Viaduct (Bridge No. 34-0100) Dir'S Order Emergency F.A. | 37 | 28 | 1624435.59 | 30973 | 16777000 | 59895 | 2026-03-03 | 2025-08-06 | 2025-07-14 |  |  | 67 | 0 | 180 | 0 |  | X
04 | 04-2X0704 | 2X0704 | 04-SF0-80-8.3/8.3 | 20.20.201130 |  | Usa Hoist Company, Inc. | 175 Prairie Lake, | East Dundee, Il 60118 | 6195491440 | 5105668214 | 585 Linda Mar Blvd | Pacifica, Ca 94044 | Baron, Marcus | 0 | 432168.59 | 0 | 0 | 2026-01-30 | Repair Elevator System | Sfobb East Span Sfobb East Span | 0 | 15 | 432168.59 | 22195 | 2975000 | 57387 | 2027-03-08 | 2025-03-20 | 2024-12-02 |  |  | 0 | 0 | 200 | 0 |  | X
04 | 04-0Q1304 | 0Q1304 | 04-SM-1-27.5/34.8 |  | ACNH-P001- (707)E | O.C. Jones & Sons, Inc. | 1520 Fourth Street | Berkeley Ca 94710 | 5109099601 | 5108676069 | 585 Linda Mar Blvd | Pacifica, Ca 94044 | Sihra, Chetan | 918615.92 | 0 | 0 | 664000 | 2026-02-20 | Cold Plane Ac, Place Hma, Modify Signal An | San Mateo County In And Near Half Moon Bayfrom Wavecrest Road To 0.1 Mile South Of Marine Boulevard | 17 | 11 | 2333080 | 20518678.3 | 20723678.3 | 59639 | 2026-03-12 | 2025-07-29 | 2025-07-02 |  |  | 51 | 0 | 300 | 0 |  | X
04 | 04-2J7904 | 2J7904 | 04-SM-1-28.9/0 |  |  | Disney Construction, Inc. | 533 Airport Blvd., Suite 120 | Burlingame Ca 94010 | 4156807752 | 6502227241 | 2350 Page Mill Rd | Palo Alto, Ca 94304 | Booshehri, Fred | 2490 | 188796.51 | 0 | 0 | 2026-02-20 | Channel Excavation And Partially Grouted R | San Mateo County In Half Moon Bay On Route1 At Pilarcitos Creek Bridge And Near La Honda On Route 84 At San Gregorio Creek Bridge | 33 | 99 | 4202026.74 | 3777333 | 4265517.21 | 56134 | 2026-12-31 | 2024-07-24 | 2024-06-21 |  |  | 126 | 0 | 380 | 0 |  | X
04 | 04-0X0804 | 0X0804 | 04-SM-1-32.2/32.2 | 20.20.201130 |  | Yerba Buena Engineering & Construction, Inc. | 1340 Egbert Avenue | San Francisco, Ca 94124 | 4158224400 | 9166219754 | 585 Linda Mar Blvd | Pacifica, Ca 94044 | Marabeh, Hisham | 0 | 42286.62 | 0 | 0 | 2025-12-15 | Replace Rsp, Pathway, And Stair | Remove And Replace Rsp, Concrete Stairway, Ac Pathway On Surfer'S Beach Dir'S Order Emergency F.A. | 100 | 54 | 975698.42 | 11044 | 1795000 | 54984 | 2026-03-31 | 2024-01-25 | 2023-09-04 |  |  | 60 | 0 | 60 | 0
04 | 04-4X4504 | 4X4504 | 04-SM-1-47.6/47.6 | 20.20.201130 |  | Santamaria Concrete, Inc. | 785 Lincoln Ave. | San Jose, Ca 95126 | 4086344209 | 5105907543 | 585 Linda Mar Blvd. | Pacifica, Ca 94044 | Zhu, Jiahong | 0 | 43191.37 | 0 | 0 | 2026-02-09 | Slope Erosion Repair | In San Mateo County Highway 1 Pm 47.6 Slope Erosion Repair Dir'S Order Emergency F.A. | 8 | 5 | 43191.37 | 20250 | 795000 | 60244 | 2026-12-31 | 2025-12-03 | 2025-10-01 |  |  | 5 | 0 | 60 | 0 |  | X
04 | 04-3X5104 | 3X5104 | 04-SM-1-47.8/47.8 | 20.20.201130 |  | Alexander Santamaria Concrete | 785 Lincoln Ave | San Jose, Ca 95126 | 4086344209 | 5105907543 | 585 Linda Mar Blvd, | Pacifica, Ca 94044 | Zhu, Jiahong | 0 | 42174.25 | 0 | 0 | 2025-12-31 | Repair Slipout | Near Sullivan Avenue Repair Slipout | 25 | 55 | 348142.3 | 19560 | 637000 | 59656 | 2026-07-10 | 2025-08-11 | 2025-04-03 |  |  | 10 | 0 | 40 | 0 |  | X
04 | 04-3Y7604 | 3Y7604 | 04-SM-35-8.7/8.7 | 20.20.201130 |  | Redwood Engineering Construction | 416 D Street | Redwood City Ca 94083 |  | 6502227241 | 2350 Page Mill Road | Palo Alto Ca 94304 | Booshehri, Fred | 0 | 155498.1 | 0 | 0 | 2026-01-05 | Repair Sinkhole | Sm-35 In Portola Valley Sm-35 In Portola Valley Sm-35 In Portola Valley Dir'S Order Emergency F.A. | 100 | 63 | 3329856.93 | 29679 | 5252574 | 50965 | 2026-12-30 | 2023-07-07 | 2023-05-05 |  |  | 189 | 0 | 100 | 0
04 | 04-1X9604 | 1X9604 | 04-SM-82-9.2/9.2 | 20.10.201130 |  | Santamaria Concrete, Inc. | 785 Lincoln Ave. | San Jose, Ca 95126 | 4086344209 | 5104216332 | 1700 S. Amphlett Blvd. | San Mateo, Ca 94402 | Moe, Alvin | 0 | 60784.57 | 0 | 0 | 2025-08-25 | Repair Sinkhole | In San Maeo County Route 82 Frontage Road Repair Sinkhole Dir'S Order Emergency F.A. | 63 | 61 | 308236.29 | 15570 | 504000 | 57115 | 2026-02-01 | 2024-12-09 | 2024-08-29 | 2026-02-04 |  | 25 | 0 | 40 | 0 |  | X
04 | 04-1Q5304 | 1Q5304 | 04-SM-82-9.3/0 |  |  | American Civil Constructors West Coast, Llc Dba Acc West Coast | 2990 Bay Vista Court, Suite D | Benicia Ca 94510 | 7077468028 | 5103856850 | 1700 S Amphlett Blvd. | San Mateo, Ca 94402 | Aung, Phone | 30601.92 | 61534 | 0 | 0 | 2026-02-20 | Replace Bridge Railing, Construct Ada Curb | San Mateo County In San Mateo At Hillsdaleboulevard Overcrossing | 83 | 100 | 1765552.91 | 1343000 | 1737516.99 | 57261 | 2025-12-31 | 2025-02-12 | 2025-01-13 |  |  | 100 | 0 | 100 | 20 |  | X
04 | 04-2Y5604 | 2Y5604 | 04-SM-82-9.6/11.8 |  |  | Fbd Vanguard Construction, Inc | 550 Greenville Road | Livermore Ca 94550 | 9252451300 | 6503334036 | 1700 S Amphlett Blvd | San Mateo, Ca 94402 | Inori, Douglas | 31133.8 | 0 | 0 | 0 | 2026-02-20 | Individual Slab Replacement (Rsc). | San Mateo County In San Mateo From 0.1 Mile North Of Hillsdale Boulevard Overcrossing To Second Avenue | 100 | 99 | 1148952.78 | 834700 | 1135760 | 56066 | 2026-02-01 | 2024-04-29 | 2024-04-04 |  |  | 40 | 0 | 40 | 0 |  | X
04 | 04-0K81U4 | 0K81U4 | 04-SM-82-12.3/15.9 |  | ACNH-P082- (033)E | A. Teichert & Son, Inc. Dba Teichert Construction | 5200 Franklin Dr. Suite 115 | Pleasanton, Ca 94588 | 9256275700 | 5104969286 | 1700 South Amphlett Blvd. | San Mateo, Ca 94402 | Bustamante, Grace | 3624580 | 48368.45 | 0 | 5687500 | 2026-02-20 | Pavement Rrr And Upgrade Of Pedestrian Inf | In San Mateo County From East Santa Inez Avenue In San Mateo To Millbrae Avenue In Millbrae | 2 | 9 | 10701633.91 | 113750000 | 114300000 | 60346 | 2032-08-30 | 2025-12-02 | 2025-12-02 |  |  | 26 | 0 | 1650 | 0 |  | X
04 | 04-0Q4804 | 0Q4804 | 04-SM-84-7.8/0 |  | ACNH-P084- (061)E | Ghilotti Construction Company,Inc. | 246 Ghilotti Avenue | Santa Rosa Ca 95407 | 7075851221 | 6502227241 | 2350 Page Mill Road | Palo Alto, Ca 94304 | Booshehri, Fred | 0 | 0 | 0 | 0 |  | Construct Retaining Wall, Drainage Systems | San Mateo County Near La Honda At 0.5 Milewest Of Pescadero Creek Road | 0 | 0 | 0 | 5508082.03 | 5508082.03 | 60420 | 2026-12-15 | 2026-01-29 | 2026-01-07 |  | S | 0 | 0 | 350 | 0
04 | 04-4X4304 | 4X4304 | 04-SM-84-16.1/16.1 | 20.20.201130 |  | Redwood Engineering Construction | 416 D Street | Redwood City, Ca 94063 | 9258192960 | 5108132594 | 2350 Page Mill Road | Palo Alto, Ca 94304 | Rahmanyar, Khalil Rahman | 0 | 202666.53 | 0 | 0 | 2026-01-29 | Repair Sinkhole & Failed Culvert | San Mateo State Highway 84 Pm 16.07 Repair Sinkhole, Failed Culvert, Repave Dir'S Order Emergency F.A. | 38 | 30 | 202666.53 | 5139 | 679000 | 60275 | 2026-08-30 | 2025-12-19 | 2025-09-12 |  |  | 15 | 0 | 40 | 0 |  | X
04 | 04-2Y5204 | 2Y5204 | 04-SM-84-27.7/29.2 |  |  | O.C. Jones & Sons, Inc. | 1520 Fourth Street | Berkeley Ca 94710 | 5105263424 | 2792342197 | 1700 S Amphlett Blvd | San Mateo, Ca 94402 | Malonzo, Ethan | 5705 | 0 | 0 | 0 | 2026-01-20 | Cold Plane Ac Pavement And Overlay With Rh | San Mateo County In Menlo Park On Route 84From Route 114 To Dumbarton Bridge And On Willow Road At Route 114/101 Separation | 37 | 88 | 2632313.76 | 2848474.5 | 2968474.5 | 59255 | 2026-03-02 | 2025-07-03 | 2025-06-16 |  |  | 22 | 0 | 60 | 0 |  | X
04 | 04-0X3304 | 0X3304 | 04-SM-84-28.0/2 | 20.20.201130 |  | Monterey Mechanical Co. | 8275 San Leandro St. | Oakland, Ca 94621 | 5106323173 | 6502227241 | 2350 Page Mill Rd. | Palo Alto, Ca 94304 | Booshehri, Fred | 0 | 28342.43 | 0 | 0 | 2026-01-26 | Repair/Replace Pumps | Ravenswood Pump Plant, Menlo Park Repair/Replace Pumps Dir'S Order Emergency F.A. | 46 | 23 | 299892.49 | 9207 | 1280000 | 55722 | 2026-10-30 | 2024-05-01 | 2024-04-02 |  |  | 37 | 0 | 80 | 0 |  | X
04 | 04-3X6404 | 3X6404 | 04-SM-92-4.0/5 | 20.20.201130 |  | Granite Rock Company | 5225 Hellyer Ave, Suite 220, | San Jose, Ca 95138 | 8317682000 | 5103931593 | 1700 So.Amphlett, 101 & 103, | San Mateo, Ca 94402-1986 | Lam, Peter | 0 | 36967.36 | 0 | 0 | 2026-02-24 | Repair Pavement | West Of Route 35, Remove Asphalt Concrete Pavement, Hot Mix Asphalt, Hma Dike, Install Underdrain, Lined V-Ditch, Trafficcontrol S | 67 | 61 | 835521.01 | 4152 | 1369000 | 59462 | 2026-03-02 | 2025-07-22 | 2025-06-16 |  |  | 40 | 0 | 60 | 0 |  | X
04 | 04-2Q8004 | 2Q8004 | 04-SM-92-12.0/13.1 |  | CPFL-6204- (136)000 | Gordon N. Ball, Inc. | 1777 Oakland Blvd. Ste 300 | Walnut Creek, Ca 94596 | 9258385675 | 5103931593 | 1700 South Amphlett Blvd | San Mateo, Ca 94402 | Lam, Peter | 1070285 | 36339.05 | 0 | 0 | 2026-02-20 | Bridge Widening, Hma, Curb Ramp, Conc Barr | San Mateo County In Foster City And San Mateo On Route 92 From 0.2 Mile East Of South Delaware Street Undercrossing To 0.3Mile Wes | 38 | 47 | 13387656.73 | 27715570.55 | 28698480.55 | 57316 | 2027-05-18 | 2025-03-13 | 2025-01-22 |  |  | 192 | 0 | 500 | 0 |  | X
04 | 04-0X6504 | 0X6504 | 04-SM-92-/.5 |  |  | O.C. Jones & Sons, Inc. | 1520 Fourth Street | Berkeley Ca 94710 | 5105263424 | 2792342197 | 1700 S Amphlett Blvd. | San Mateo, Ca 94402 | Malonzo, Ethan | 8981.09 | 0 | 0 | 0 | 2026-01-20 | Hm-1 Cold Plane Ac Pavement, Place Hma (A) | In San Mateo County In And Near Half Moon Bay From Route 1 To 0.3 Mile East Of Main Street. | 100 | 100 | 813821.98 | 751123.55 | 751123.55 | 60119 | 2026-01-13 | 2025-09-26 | 2025-06-04 |  |  | 30 | 0 | 30 | 0 |  | X
04 | 04-1X2204 | 1X2204 | 04-SM-92-/13.6 | 20.10.201352 |  | Norcal General Construction Co | 751 Mabury Rd. | San Jose, Ca 95133 | 4088860335 | 5103856741 | 1700 South Amphlett Blvd,#101 | San Mateo, Ca 94402 | Chen, Roy | 0 | 218516.92 | 0 | 0 | 2025-11-17 | Replace Fence And Gates | In San Mateo County And San Francisco County Replace Fence And Gates Dir'S Order Emergency F.A. | 33 | 11 | 218516.92 | 34250 | 1935000 | 56434 | 2026-03-30 | 2024-08-15 | 2024-08-15 |  |  | 40 | 0 | 120 | 0 |  | X
04 | 04-2J7304 | 2J7304 | 04-SM-101-6.9/7.6 |  | ACNH-Q101- (415)E | Myers & Sons Construction, Llc | 45 Morrison Ave | Sacramento Ca 95838 | 9162086416 | 5103931593 | 1700 So. Amphlett Blvd, Ste101 | San Mateo, Ca 94402 | Lam, Peter | 14535 | 2604.01 | 0 | 0 | 2026-02-20 | Replace Box Culvert Bridge. | San Mateo County In Redwood City And San Carlos From 0.3 Mile South Of Cordilleras Creek Bridge To 0.1 Mile South Of Pulgas Creek | 100 | 94 | 21612228.45 | 16195350.3 | 22333260.36 | 49645 | 2026-02-16 | 2023-04-07 | 2023-03-20 |  |  | 333 | 0 | 275 | 0 |  | X
04 | 04-0X0604 | 0X0604 | 04-SM-101-9.1/9.1 | 20.20.201130 |  | Sierra Mountain Construction, Inc. | 19500 Nugget Blvd. | Sonora, Ca 95370 | 4153087260 | 5104216332 | 1700 S Amphlett Blvd | San Mateo, Ca 94402 | Moe, Alvin | 0 | 46933 | 0 | 0 | 2025-12-31 | Creek Clearing | In San Mateo County In Belmont At Belmont Creek Culvert Debris And Sidement Removal Dir'S Order Emergency F.A. | 80 | 91 | 1980683.39 | 14121 | 2176000 | 55804 | 2025-12-31 | 2024-05-14 | 2023-08-31 |  |  | 80 | 0 | 100 | 0 |  | X
04 | 04-1Q8204 | 1Q8204 | 04-SM-101-25.6/26.1 |  | ACNH-Q101- (454)E | Fbd Vanguard Construction, Inc. | 550 Greenville Road | Livermore Ca 94550 | 9253375169 | 9166343561 | 585 Linda Mar Blvd. | Pacifica, Ca 94044 | Giang, Biana | 1066592 | 0 | 0 | 0 | 2026-02-20 | Replace Concrete Pavement Slabs And Upgrad | San Mateo County And The City And County Of San Francisco At Various Locations Fromharney Way To Market Street | 10 | 11 | 9794354.78 | 92222000 | 92222000 | 60056 | 2028-03-07 | 2025-08-28 | 2025-08-20 |  |  | 60 | 0 | 590 | 0 |  | X
04 | 04-1Q5824 | 1Q5824 | 04-SM-101-/21.8 |  | ACNH-Q101- (441)E | Bay Cities Paving & Grading, Inc. | 1450 Civic Ct Bldg B #400 | Concord Ca 94520 | 9256876666 | 2792342197 | 1700 S. Amphlett Blvd. | San Mateo, Ca 94402 | Malonzo, Ethan | 0 | 0 | 0 | 0 |  | Ac Pavement, Guardrails, Tms, Drainage Sys | San Mateo County From San Mateo County Line In East Palo Alto To 0.2 Mile North Of Colma Creek Bridge In South San Francisco | 0 | 0 | 0 | 74224488.07 | 75254488.07 | 60178 | 2027-06-22 | 2025-11-10 | 2025-10-20 |  | S | 0 | 0 | 360 | 0
04 | 04-1X2404 | 1X2404 | 04-SM-101-/6.2 | 20.10.201131 |  | Golden State Bridge, Inc. | 3701 Mallard Dr. | Benicia, Ca 94510 | 9253728000 | 5108676052 | 1700 South Amphlett Blvd., Suite 101 | San Mateo, Ca 94402 | Lam, Peter | 0 | 13746.48 | 0 | 0 | 2025-12-17 | Bridge Repair | Redwood Creek Bridge No. 35-0145 Repair Damaged Bridge Colums, Abutment, Bent Cap & Soffit, & Mitigate Local Scour Dir'S Order Eme | 50 | 1 | 18525.98 | 8712 | 1351500 | 56138 | 2025-05-15 | 2024-07-17 | 2024-06-14 |  |  | 20 | 0 | 40 | 0 |  | X
04 | 04-1X6604 | 1X6604 | 04-SM-280-10.2/10.2 | 20.10.201130 |  | Ghilotti Construction Company,Inc. | 246 Ghilotti Ave. | Santa Rosa, Ca 95407 | 7075851221 | 5103931593 | 1700 S. Amphlett Blvd. Ste 101 | San Mateo, Ca 94402 | Lam, Peter | 0 | 11234.41 | 0 | 0 | 2025-12-03 | Replace Culvert | In San Mateo Co. On Route 280 Nb In The City Of Belmont Replace Culvert Dir'S Order Emergency F.A. | 100 | 89 | 901528.11 | 6078 | 1010500 | 56555 | 2026-04-30 | 2024-09-17 | 2024-07-05 |  |  | 40 | 0 | 40 | 0 |  | X
04 | 04-3Y0804 | 3Y0804 | 04-SM-280-10.2/10.2 | 20.20.201130 |  | Aqua Sierra Controls, Inc | 13265 Bill Francis Drive | Auburn, Ca 95603 | 5308233241 | 6503334036 | 1700 S. Amphlett Blvd | San Mateo, Ca | Inori, Douglas | 0 | 57634.27 | 0 | 0 | 2025-08-07 | Repair Pumps | Sm 280-Canada Pump Station Rehab- Prevent Detention Basin Overflow Into Other Reservsm 280-Canada Pump Station Rehab- Prevent Dir' | 100 | 98 | 1086721.05 | 17663 | 1090286.29 | 48304 | 2025-09-30 | 2023-04-06 | 2023-01-14 |  |  | 180 | 0 | 100 | 0 |  | X
04 | 04-4J8504 | 4J8504 | 04-SM-280-/21 |  | ACIM-2801- (999)E | Golden State Bridge, Inc. | 3701 Mallard Drive | Benicia Ca 94510 | 9253728000 | 5103931593 | 1700 S Amphlette Blvd | San Mateo Ca 94402 | Lam, Peter | 0 | 1168.68 | 0 | 0 | 2026-01-20 | Install Column Casings, Conc Barriers And | San Mateo County At Various Locations Fromalpine Road Undercrossing To Route 280/380Separation | 85 | 96 | 10723135.87 | 9787756.68 | 10896106.45 | 52685 | 2026-12-22 | 2023-04-25 | 2023-04-18 |  |  | 478 | 0 | 550 | 12 |  | X
04 | 04-3Y4104 | 3Y4104 | 04-SM-680-/16.5 | 20.20.201130 |  | Golden State Bridge, Inc. | 3701 Mallard Drive | Benicia Ca 94510 | 9253728000 | 5108133347 | 3401 Regatta Blvd | Richmond, Ca 948041650 | Atako, Kingston | 0 | 730175 | 0 | 0 | 2026-02-20 | Perform Non-Destructive Testing On Butt We | In Cc, Sol And Sm Counties - Routes 680, 8In Cc, Sol And Sm Counties - Routes 680, 8In Cc, Sol And Sm Counties - Routes 680, 8Dir' | 81 | 97 | 26715752.52 | 63786 | 27537000 | 51185 | 2026-04-10 | 2023-07-17 | 2023-05-19 |  |  | 457 | 0 | 200 | 367 |  | X
04 | 04-0A53T4 | 0A53T4 | 04-SOL-12-1.8/L3.2 |  |  | Kiewit Infrastructure West Co. | 4650 Business Center Drive | Fairfield Ca 94534 | 7074397300 | 9252505595 | 324 Campus Lane, Suite T | Fairfield, Ca 94534 | Isada, Darren | 5558059.69 | 197362.03 | 9166 | 1552204.53 | 2026-02-20 | I-80 Wb Truck Scales | Solano County In And Near Fairfield On Route 12 From The 80/12 East Junction To 0.9 Mile East Of Chadbourne Road Undercrossing And | 14 | 27 | 41280147.69 | 152000000 | 153055288.96 | 59176 | 2029-02-20 | 2025-06-20 | 2025-06-20 |  |  | 117 | 0 | 865 | 0 |  | X
04 | 04-0W1104 | 0W1104 | 04-SOL-12-3.2/7.5 |  | SNHG-P012- (131)E | Hoseley Corporation | 96F Pier Admin Building Ste20 | San Francisco Ca 94124 | 4154048997 | 5108676033 | 324 Campus Lane, Suite T | Fiarfield, Ca 94534 | Lane, Isaiah | 47700 | 0 | 6927.8 | 0 | 2025-10-20 | Install Mgs And Modify Signal And Lighting | Solano County In And Near Suisun City At Various Locations From 0.2 Mile East Of Beck Avenue To 0.2 Mile West Of Walters Road | 100 | 97 | 2343815.25 | 2323604 | 2475531.8 | 56240 | 2025-07-21 | 2024-08-16 | 2024-07-25 |  |  | 110 | 0 | 110 | 0 |  | X
04 | 04-2Q5504 | 2Q5504 | 04-SOL-12-7.7/14.1 |  | ACNH-P012- (132)E | Bay Cities Paving & Grading, Inc. | 1450 Civic Ct Bldg B #400 | Concord Ca 94520 | 9256876666 | 5108071407 | 324 Campus Lane, Ste T | Fairfield, Ca 94533 | Sarwary, Asadullah | -18237.1 | 62579.3 | 162161.73 | 0 | 2026-02-20 | Rhma Overlay, Replace Culverts, Bridge Rai | Solano County Near Suisun City From 0.2 Mile East Of Lawler Ranch Parkway To 0.5 Mile East Of Shiloh Road | 32 | 43 | 8650120.94 | 18916084.55 | 19961965.86 | 57262 | 2027-02-04 | 2025-03-06 | 2025-02-14 |  |  | 111 | 0 | 350 | 1 |  | X
04 | 04-1X3604 | 1X3604 | 04-SOL-28-/9.8 | 20.20.201130 |  | Redgwick Construction Co. | 21 Hegenberger Court, | Oakland, Ca 94621 | 5107921727 | 5107738499 | 324 Campus Lane,Suite T | Fairfield, Ca 94534 | Tran, Quang | 0 | 689726.85 | 0 | 0 | 2026-01-28 | Replace/Improve Existing Fences And Gates | In Solano County Vallejo, Fairfield And Dixon Maintenance Stations And Dixon Maintenance Stations | 98 | 95 | 1992670.81 | 13332 | 2107000 | 56607 | 2026-03-01 | 2024-11-04 | 2024-08-27 |  |  | 117 | 0 | 120 | 0 |  | X
04 | 04-2Q5204 | 2Q5204 | 04-SOL-29-/6 |  | ACNH-P029- (158)E | Bay Cities Paving & Grading, Inc. | 1450 Civic Ct Bldg B #400 | Concord Ca 94520 | 9256876666 | 5107738499 | 324 Campus Lane Suite T | Fairfield, Ca 94534 | Tran, Quang | 1238651.93 | 0 | 0 | 624500 | 2026-02-20 | Hma Pvmt, Mod Drainage, Signals, Sidewalks | Solano County In Vallejo From 0.2 Mile North Of Route 80/ 29 Separation To Napa County Line | 15 | 18 | 4431221.51 | 24980108.76 | 25130108.76 | 59540 | 2027-07-14 | 2025-07-29 | 2025-07-14 |  |  | 62 | 0 | 410 | 0 |  | X
04 | 04-3X5004 | 3X5004 | 04-SOL-80-6.7/6.7 | 20.20.201130 |  | O C Jones & Sons Inc. | 1520 Fourth Street, | Berkeley Ca 94710 | 5105263424 | 5102246309 | 324 Campus Lane, | Fairfield, Ca 94534 | Quang, Tran | 0 | 94862.05 | 0 | 0 | 2026-01-28 | Lanslide And Bike Repair | Haul Off Slide Material At Closed Bike Trail And Disposal, Hazmat Soil Testing, Roadway Excavation, Embankment Grading, "Solano Bi | 81 | 46 | 1169465.39 | 10496 | 2560000 | 59561 | 2026-04-17 | 2025-07-29 | 2025-03-28 |  |  | 122 | 0 | 150 | 0
04 | 04-3X1604 | 3X1604 | 04-SOL-80-10.1/10.6 | 20.20.201130 |  | Maggiora Bros Drilling, Inc. | 595 Airport Blvd., | Watsonville, Ca 95076 | 8317241338 | 5107738499 | 324 Campus Lane, | Fairfield, Ca 94534 | Tran, Quang | 0 | 662064.18 | 0 | 0 | 2026-01-20 | Pump Station Repair | Pump Station Asset Id# 23 0014Dwr/L | 0 | 52 | 662064.18 | 8730 | 1277500 | 57895 | 2026-04-17 | 2025-03-28 | 2025-02-24 |  |  | 0 | 0 | 60 | 0 |  | X
04 | 04-4G0804 | 4G0804 | 04-SOL-80-10.4/30.2 | HB4C | ACIM-0802- (375)E | O.C. Jones & Sons, Inc. | 1520 Fourth Street | Berkeley Ca 94710 | 5105263424 | 5104064596 | 324 Campus Lane Suite T | Fairfield Ca 94534 | Tatum, Justen | 80095 | 0 | 0 | 0 | 2026-02-20 | Convert Existing Hov Lane To Expres | From 0.95 West Of Red Top Road Undercrossing To 0.4 Mile East Of Leisure Town Road Overcrossing | 95 | 99 | 160241229.93 | 143352700.48 | 162105430.86 | 42082 | 2026-07-15 | 2022-02-02 | 2022-01-18 |  |  | 889 | 0 | 940 | 0 |  | X
04 | 04-3X4704 | 3X4704 | 04-SOL-80-12.9/12.9 | 20.20.201130 |  | Gordon N Ball Inc | 1777 Oakland Blvd St 300, | Walnut Creek, Ca 94596 | 9258385675 | 5104064596 | 324 Campus Lane, | Fairfield, Ca 94534 | Tatum, Justen | 0 | 124816.42 | 0 | 0 | 2026-02-18 | "Repair Ac Pavement, Address Exposed Found | Pavement Settlement And Embankment Reconstruction | 98 | 56 | 551953.65 | 6508 | 994000 | 59676 | 2026-02-19 | 2025-08-05 | 2025-03-31 |  |  | 59 | 0 | 60 | 0
04 | 04-4G8734 | 4G8734 | 04-SOL-80-13.9/14.5 |  |  | John Semsen Landscaping Co., Inc. | 21161 Lyons Bald Mt. Road | Sonora Ca 95370 | 2097434911 | 5107746276 | 3401 Regatta Blvd | Richmond Ca, 94804 | Luckel, Kasaia | 5080 | 0 | 0 | 0 | 2026-02-20 | Maintain Existing Planted Areas. | Solano County In And Near Fairfield At Danwilson Creek Bridge And At Suisun Creek Bridge | 73 | 78 | 436920 | 540300 | 561040 | 46264 | 2027-04-08 | 2023-01-13 | 2022-11-21 |  |  | 759 | 0 | 1040 | 0 |  | X
04 | 04-0K6404 | 0K6404 | 04-SOL-80-15.9/30.2 |  | ACIM-0801- (995)E | O.C. Jones & Sons, Inc. | 1520 Fourth Street | Berkeley Ca 94710 | 5105263424 | 5104064596 | 324 Campus Lane, Suite T | Fairfield, Ca 94534 | Tatum, Justen | 156105.32 | 265677.84 | 0 | 0 | 2026-02-20 | Cold Plane, Overlay, Mgs, Ramp Metering, L | Solano County On Route 80 In And Near Fairfield And Vacaville At Various Locations From 1.5 Miles East Of Suisun Valley Road Overc | 90 | 88 | 14068917.19 | 15116851.5 | 16026236.99 | 57066 | 2026-03-24 | 2025-01-16 | 2024-12-17 |  |  | 208 | 0 | 230 | 0 |  | X
04 | 04-4K3004 | 4K3004 | 04-SOL-80-22.1/23 |  | SIMG-0802- (377)E | Gordon N. Ball, Inc. | 1777 Oakland Blvd., Ste 300 | Walnut Creek, Ca 94596 | 9258385675 | 5108676033 | 324 Campus Lane, Suite T | Fairfield, Ca 94534 | Lane, Isaiah | 49120 | 0 | -31752.51 | 0 | 2026-02-20 | Construct Concrete Barrier And Install Dra | Solano County From 1.2 Miles East Of Northtexas Street Overcrossing In Fairfield To 0.1 Mile West Of Cherry Glen Road Overcrossing | 100 | 97 | 3930814.57 | 3491799 | 4050015.01 | 56786 | 2025-08-12 | 2024-12-03 | 2024-11-05 |  |  | 120 | 0 | 120 | 0 |  | X
04 | 04-0J6014 | 0J6014 | 04-SOL-80-34.4/34.5 |  |  | Empire Landscaping Inc. | 26945 County Road 97D | Davis Ca 95616 | 5304003944 | 5107746276 | 3401 Regatta Blvd. | Richmond, Ca 94804 | Luckel, Kasaia | 3210 | 0 | 0 | 0 | 2026-02-20 | Maintain Existing Planted Areas. | Solano County In And Near Dixon And Vacaville On Route 80 At Mc Cune Creek Bridge And On Route 505 At Horse Creek Bridge | 69 | 70 | 132972.5 | 190665 | 190665 | 47906 | 2027-06-10 | 2023-03-20 | 2023-01-13 |  |  | 715 | 0 | 1040 | 0 |  | X
04 | 04-3X7004 | 3X7004 | 04-SOL-80-/.5 | 20.20.201130 |  | Yerba Buena Engineering & Construction, Inc. | 1340 Egbert Avenue, | San Francisco, Ca 94124 |  | 5108132587 | 3401 Regatta Blvd, | Richmond, Ca 94804-4594 | Aldabbas, Mahmoud | 0 | 0 | 0 | 0 |  | Repair Damaged Toll Plaza Building And Ano | Toll Plaza Building Repair | 0 | 0 | 0 | 12750 | 2010000 | 60234 | 2026-02-23 | 2025-08-25 | 2025-08-25 |  |  | 0 | 0 | 60 | 0
04 | 04-4X8104 | 4X8104 | 04-SOL-84-12.1/12.1 | 20.10.201130 |  | Disney Construction, Inc. | 533 Airport Blvd., Ste 120 | Burlingame, Ca 94010 | 6502599545 | 5108071407 | 324 Campus Lane, Ste T | Fairfield, Ca 94534 | Sarwary, Asadullah | 0 | 248912.92 | 0 | 0 | 2026-02-27 | Repair Deck Failure | Replace Failed Timber Plank Deck Members, Extend Corrugated Steel Deck And Pave Back Hma Deck Wearing Surface Dir'S Order Emergenc | 67 | 34 | 248912.92 | 5148 | 743000 | 60367 | 2026-03-06 | 2026-01-23 | 2025-12-18 |  |  | 10 | 0 | 15 | 0 |  | X
04 | 04-0X7604 | 0X7604 | 04-SOL-113-18.3/21.2 |  |  | Doolittle Construction, Llc Dba Doolitlle Road Construction | 15 Business Parkway Suite 105 | Sacramento Ca 95828 | 7756917232 | 5108071407 | 324 Campus Lane, Suite T | Fairfield, Ca 94534 | Sarwary, Asadullah | 10000 | 0 | 0 | 0 | 2025-12-20 | Cold Plane Ac Pavement, Place Hma And Over | Solano County In And Near Dixon From Parkway Boulevard To Route 113/80 Separation | 97 | 97 | 1458172.5 | 1449000 | 1590723.18 | 59115 | 2026-03-31 | 2025-06-26 | 2025-06-12 |  |  | 29 | 0 | 30 | 0 |  | X
04 | 04-0J3014 | 0J3014 | 04-SON-1-26.7/27.1 |  |  | Empire Landscaping Inc. | 26945 County Road 97D | Davis Ca 95616 | 5304003943 | 5104069754 | 4030 Occidental Rd., Unit A | Santa Rosa, Ca 95401 | Paulo, Harley | 6400 | 0 | 0 | 0 | 2026-02-20 | Maintain Existing Planted Areas And Erosio | Sonoma County Near Jenner From 0.3 Mile To0.7 Mile North Of Meyers Grade Road | 11 | 23 | 161934 | 696100 | 696100 | 57575 | 2029-08-06 | 2025-03-13 | 2024-10-31 |  |  | 124 | 0 | 1080 | 0 |  | X
04 | 04-1K7304 | 1K7304 | 04-SON-1-30.8/40.6 |  |  | Wylatti Resource Management, Inc. | 23601 Cemetery Lane | Covelo Ca 95428 | 7079838135 | 5104069754 | 4030 Occidental Rd., Unit A | Santa Rosa, Ca 95401 | Paulo, Harley | 100802.42 | 0 | 0 | 0 | 2025-11-20 | Remove And Replace Culverts, And Establish | Sonoma County At Various Locations From Mill Gulch To 0.5 Mile South Of Miller Creek | 36 | 93 | 2479520.21 | 2554842.04 | 2616842.04 | 53804 | 2025-12-31 | 2023-11-08 | 2023-10-18 |  |  | 145 | 0 | 400 | 0 |  | X
04 | 04-1K7314 | 1K7314 | 04-SON-1-30.8/40.6 |  |  | Wylatti Resource Management, Inc. | 23601 Cemetery Lane | Covelo Ca 95428 | 7079838135 | 5108674515 | 3401 Regatta Blvd | Richmond, Ca 94804 | Simpson, John | 0 | 0 | 0 | 0 |  | Maintain Existing Planted Area And Erosion | Sonoma County At Various Locations From 2.2 Miles South Of Fort Ross Road To 0.7 Mile North Of Moon Rock Campground | 0 | 0 | 0 | 280763.2 | 280763.2 | 60139 | 2029-01-30 | 2025-10-24 | 2025-10-02 |  |  | 0 | 0 | 1080 | 0
04 | 04-1X3204 | 1X3204 | 04-SON-1-38.6/38.6 | 20.10.201130 |  | O.C. Jones & Sons, Inc. | 1520 Fourth St | Berkeley Ca 94710 | 5105263424 | 5104069754 | 4030 Occidental Rd., Unit A | Santa Rosa, Ca 95401 | Paulo, Harley | 0 | 298441.88 | 0 | 0 | 2026-01-09 | Construct Soldier Pile Wall & Drainage | In Sonoma Co. On Rte 1 At Pm 38.58 At Walsh Construct Soldier Pile Wall, And Drainage Facilities Dir'S Order Emergency F.A. | 100 | 93 | 7979784.86 | 20611 | 8615000 | 55661 | 2026-02-28 | 2024-02-23 | 2024-02-22 |  |  | 298 | 0 | 120 | 0 |  | X
04 | 04-1K7514 | 1K7514 | 04-SON-1-41.2/54.6 |  |  | Wylatti Resource Management, Inc. | 23601 Cemetery Lane | Covelo Ca 95428 | 7079838135 | 5108674515 | 3401 Regatta Blvd. | Richmond, Ca 94804 | Simpson, John | 0 | 0 | 0 | 0 |  | Maintain Existing Planted Area And Erosion | Sonoma County At Various Locations From 0.2 Mile North Of Miller Creek To 0.1 Milenorth Of Vantage Road | 0 | 0 | 0 | 338430.92 | 338430.92 | 60263 | 2029-01-30 | 2025-12-19 | 2025-10-03 |  |  | 0 | 0 | 1080 | 0
04 | 04-1K7504 | 1K7504 | 04-SON-1-41.2/54.6 |  |  | Wylatti Resource Management, Inc. | 23601 Cemetery Lane | Covelo Ca 95428 | 7079838135 | 5104069754 | 4030 Occidental Rd., Unit A | Santa Rosa, Ca 95401 | Paulo, Harley | 32628.08 | 0 | 0 | 0 | 2026-02-20 | Remove Culvert, Rcp, Corrugated Steel Pipe | Sonoma County At Various Locations From 0.2 Mile North Of Miller Creek To 0.1 Milenorth Of Vantage Road | 59 | 95 | 2745927.79 | 2762871.22 | 2850831.42 | 53805 | 2026-03-31 | 2023-11-09 | 2023-10-25 |  |  | 250 | 0 | 425 | 0 |  | X
04 | 04-1K7604 | 1K7604 | 04-SON-1-45.4/0 |  |  | Rege Construction, Inc. | 600 Santana Drive | Cloverdale, Ca 95425 | 7073183762 | 5104069754 | 4030 Occidental Rd., Unit A | Santa Rosa, Ca 95401 | Paulo, Harley | 739.82 | 0 | 0 | 0 | 2026-02-20 | Construct Pipe Culvert Wingwall And Draina | Sonoma County Near Stewarts Point At 2.7 Miles South Of Skaggs Springs Road | 45 | 95 | 987299.67 | 1026808 | 1026808 | 57898 | 2026-11-07 | 2025-03-27 | 2025-03-03 |  |  | 131 | 0 | 290 | 0 |  | X
04 | 04-4G7804 | 4G7804 | 04-SON-1-/58.6 |  | HSST-P001- (704)E | O.C. Jones & Sons, Inc. | 1520 Fourth Street | Berkeley Ca 94710 | 5108162955 | 5104069754 | 4030 Occidental Rd., Unit A | Santa Rosa, Ca 95401 | Paulo, Harley | 27799.8 | 0 | 0 | 0 | 2026-02-20 | Centerline Rumble Strip,Shoulder Widening, | Sonoma County At Various Locations From Marin County Line To Mendocino County Line | 16 | 50 | 2527475.3 | 5034621.5 | 5086621.5 | 57495 | 2026-04-28 | 2025-03-13 | 2025-02-14 |  |  | 68 | 0 | 420 | 0 |  | X
04 | 04-1X1404 | 1X1404 | 04-SON-1-/24.7 | 20.20.201130 |  | Engelke Construction, Inc. | Po Box 1387 | Healdsburg, Ca 95448 | 7074338389 | 5104069754 | 4030 Occidental Rd, Unit A | Santa Rosa, Ca 95401 | Paulo, Harley | 0 | 31186.88 | 0 | 0 | 2026-01-09 | Install Horizontal Drains & Underdrains | On Route 1, In Sonoma County, Between Pm 24.65 & 24.73 Install Horizontal Drains & Underdrains And Repair Pavement Dir'S Order Em | 100 | 92 | 1974442.65 | 11775 | 2135000 | 56685 | 2026-01-31 | 2024-11-08 | 2024-08-29 |  |  | 109 | 0 | 105 | 0 |  | X
04 | 04-3X0804 | 3X0804 | 04-SON-1-/7.2 | 20.20.201130 |  | Ghilotti Construction Company,Inc. | 246 Ghilotti Avenue, | Santa Rosa, 95407 |  | 5104069754 | 4030 Occidental, Bldg A, | Santa Rosa, Ca 95401-5801 | Paulo, Harley | 0 | 274161.59 | 0 | 0 | 2026-02-24 | Near Bodega Bay Slipout | Near Bodega Bay Near Bodega Bay | 100 | 60 | 2827665.06 | 24052 | 4745000 | 57266 | 2026-04-06 | 2025-02-20 | 2025-02-20 |  |  | 186 | 0 | 140 | 0
04 | 04-4X4604 | 4X4604 | 04-SON-1-/10.4 | 20.20.201130 |  | Terracon Constructors, Inc. | 18184 Geyserville Ave. | Geyserville, Ca 95441 | 7074330323 | 5104069754 | 4030 Occidental Rd., Unit A | Santa Rosa, Ca 95401 | Paulo, Harley | 0 | 0 | 0 | 0 |  | Roadway Settlement Repair | Repair Roadway Settlement Install Micropile Wass, Repair Drainage System & Restore Pavement Dir'S Order Emergency F.A. | 0 | 0 | 0 | 9690 | 1500000 | 60413 | 2026-08-01 | 2025-12-17 | 2025-12-17 |  |  | 0 | 0 | 80 | 0
04 | 04-3X1004 | 3X1004 | 04-SON-1-/36.4 | 20.20.201130 |  | Precision Excavating & Gradinginc | 129 N Cloverdale Blvd #7, | Cloverdale, Ca 95425 |  | 5104069754 | 4030 Occidental, Bldg A, | Santa Rosa, Ca 95401-5801 | Paulo, Harley | 0 | 266260.31 | 0 | 0 | 2026-02-11 | Repair Slipout | Lee Drive At Stillwater Cove | 100 | 56 | 869448.25 | 47202 | 1558400 | 58895 | 2026-05-31 | 2025-06-16 | 2025-04-21 |  |  | 115 | 0 | 60 | 0
04 | 04-4H0514 | 4H0514 | 04-SON-12-25.8/0 |  |  | Empire Landscaping, Inc. | 26945 County Road 97D | Davis Ca 95616 | 5304003943 | 7072497557 | 4030 Occidental Rd. Unit A | Santa Rosa, Ca 95401 | Brajnikoff, Leonard | 6000 | 0 | 0 | 0 | 2026-02-20 | Maintain Existing Planted Area And Erosion | Sonoma County Near Santa Rosa At Sonoma Creek Bridge And At Hooker Creek Bridge | 16 | 20 | 92400 | 457080 | 457080 | 58959 | 2029-08-29 | 2025-06-13 | 2025-05-29 |  |  | 164 | 0 | 1040 | 0 |  | X
04 | 04-4A1304 | 4A1304 | 04-SON-101-18.5/18.5 | HE11 | NH - - ( ) | Ghilotti Construction Company,Inc. | 246 Ghilotti Avenue | Santa Rosa Ca 95407 | 7075851221 | 5103856972 | 4030 Occidental Road | Santa Rosa, Ca 94501 | Valeh, Syd | 85093.5 | 230264.56 | 0 | 0 | 2026-02-20 | Hma, Widen & Replace Hearn Ave Oc. | Sonoma County In Santa Rosa At Hearn Avenue Overcrossing | 57 | 96 | 25246175.5 | 25158888.65 | 26251733.88 | 54424 | 2027-04-22 | 2023-12-13 | 2023-11-17 |  |  | 388 | 0 | 679 | 0 |  | X
04 | 04-1Q7004 | 1Q7004 | 04-SON-101-22.8/32.8 |  |  | Ghilotti Construction Company,Inc. | 246 Ghilotti Avenue | Santa Rosa Ca 95407 | 7079756334 | 7072497557 | 4030 Occidental Road | Santa Rosa, Ca 94501 | Brajnikoff, Leonard | 66225 | 13732.14 | 0 | 0 | 2026-02-20 | Replace Bridge Railing And Guardrail, & Re | Sonoma County At Various Locations From Mendocino Avenue Overcrossing To Limerick Lane Overcrossing | 90 | 90 | 7448073.8 | 7965469.13 | 8214956.31 | 57382 | 2026-03-25 | 2025-03-06 | 2025-02-06 |  |  | 179 | 0 | 200 | 0 |  | X
04 | 04-2K3604 | 2K3604 | 04-SON-116-9.6/0 |  | ACST-S097- (001)E | Ghilotti Bros., Inc. | 525 Jacoby Street | San Rafael Ca 94901 | 4157202114 | 7072497557 | 4030 Occidental Rd, Unit A | Santa Rosa, Ca 95401 | Brajnikoff, Leonard | 21792.85 | 1760 | 0 | 0 | 2026-02-20 | Repair Side Slope And Construct Soil Nail | Sonoma County Near Monte Rio At 0.2 Mile West Of Cnopius Road | 10 | 28 | 1510096.65 | 5116996 | 5381996 | 59098 | 2027-02-10 | 2025-06-19 | 2025-05-07 |  |  | 57 | 0 | 550 | 0 |  | X
04 | 04-3X0504 | 3X0504 | 04-SON-116-10.4/10.4 | 20.20.201130 |  | Piazza Construction | 5200 Carroll Road, | Petaluma, Ca 94952 |  | 7072497557 | 4030 Occidental Road,Unit A | Santa Rosa, Ca 95401 | Brajnikoff, Leonard | 0 | 48283.15 | 0 | 0 | 2026-01-06 | Slipout And Drainage Repair | In Gue In Guerne In Guerneville | 100 | 65 | 4750860.4 | 54577 | 7255000 | 57376 | 2026-01-30 | 2025-03-20 | 2025-01-02 |  |  | 216 | 0 | 180 | 0
04 | 04-4J4604 | 4J4604 | 04-SON-116-11.8/12.2 |  | ACST-P116- (051)E | California Highway Construction Group, Inc. | 1647 Willow Pass Road #150 | Concord Ca 94520 | 9257661714 | 9163201724 | 4030 Occidental Road | Santa Rosa 95401 | Brajnikoff, Leonard | 14454.75 | 41656.72 | 0 | 0 | 2026-02-20 | Replace Curb Ramps, Sidewalk, Driveway, Li | Sonoma County At Guerneville From Brookside Lane To Old River Road | 100 | 89 | 6795865.36 | 6686888 | 7360296.17 | 55699 | 2026-07-03 | 2024-04-29 | 2024-04-16 |  |  | 214 | 0 | 210 | 0 |  | X
04 | 04-3G9004 | 3G9004 | 04-SON-116-46.5/46.8 | HB4N | CSTG-X097- (044)E | O.C. Jones & Sons, Inc. | 1520 Fourth Street | Berkeley Ca 94710 | 5105263424 | 5104969271 | 384 Bel Marin Keys Ste 200 | Novato Ca 94949 | La Serna, Fabio | 29044.5 | 131485.58 | 0 | 0 | 2026-02-20 | Rdwy Exc, Hma, Drainage, Rock Blanket, Min | Sonoma County Near Schellville On Route 116 From 0.3 Mile North Of Bonneau Road Toroute 121 And On Route 121 From 0.2 Mile South O | 54 | 98 | 12113431.63 | 10572056.8 | 11953090.36 | 52107 | 2026-03-20 | 2023-08-23 | 2023-07-31 |  |  | 310 | 0 | 575 | 0 |  | X
04 | 04-3G9014 | 3G9014 | 04-SON-116-46.5/46.8 |  |  | Hanford Applied Restoration & Conservation | 775 Baywood Drive, Suite 207 | Petaluma Ca 94954 | 7079966633 | 5108674515 | 3401 Regatta Blvd | Richmond, Ca 94804 | Simpson, John | 0 | 0 | 0 | 0 |  | Maintain Existing Planted Area And Erosion | Sonoma County Near Schellville On Route 116 From 0.3 Mile North Of Bonneau Road Toroute 121 And On Route 121 From 0.2 Mile South O | 0 | 0 | 0 | 299739 | 299739 | 60441 | 2029-03-30 | 2026-02-18 | 2026-01-09 |  |  | 0 | 0 | 1080 | 0
04 | 04-2Q4404 | 2Q4404 | 04-SON-121-6.5/0 |  |  | Gordon N. Ball, Inc. | 1777 Oakland Blvd. Suite 300 | Walnut Creek Ca 94596 | 9258385675 | 5104969271 | 384 Bel Marin Keys Ste 200 | Novato, Ca 94949 | La Serna, Fabio | 192217.8 | 191658.99 | 0 | 0 | 2026-02-20 | Remove Br And Ac Surf, Construct Br Deck, | Sonoma County Near Sonoma At Yellow Creek Bridge And At Arroyo Seco Bridge | 20 | 93 | 3968414.66 | 3378400 | 4241013.9 | 58276 | 2026-04-14 | 2025-04-24 | 2025-04-07 |  |  | 97 | 0 | 480 | 0 |  | X
04 | 04-3X4204 | 3X4204 | 04-SON-128-16.6/16.7 | 20.20.201130 |  | Terracon Constructors Inc | Po Box 276 | Healdsburg, Ca 95448 |  | 5108676107 | 4030 Occidental, Bldg A, | Santa Rosa, Ca 95401-5801 | Brajnikoff, Leonard | 0 | 348814.75 | 0 | 0 | 2025-10-31 | Construct Rock Slope Protection (Rsp) And | Slipout On Westbound Son 128 Due To Storm Events | 49 | 19 | 348814.75 | 11661 | 1792000 | 59300 | 2025-12-04 | 2025-07-08 | 2025-03-19 |  |  | 39 | 0 | 80 | 0 |  | X
04 | 04-4X5704 | 4X5704 | 04-SON-128-/3.2 | 20.20.201130 |  | Rege Construction, Inc. | 600 Santana Dr. | Cloverdale, Ca 95425 |  | 7072497557 | 4030 Occidental Rd. | Santa Rosa, Ca 95401 | Brajnikoff, Leonard | 0 | 219564.83 | 0 | 0 | 2026-02-26 | Cloverdale Rockslide Repair | Repair Rockslide & Landslide Install Double Twisted Wire Mesh-Anchored And Regrade Slope Dir'S Order Emergency F.A. | 63 | 25 | 219564.83 | 6315 | 875000 | 60414 | 2026-03-20 | 2026-01-27 | 2025-12-04 |  |  | 25 | 0 | 40 | 0 |  | X
04 | 04-0Y8004 | 0Y8004 | 04-VAR-82-25.9/25.9 |  |  | Truesdell Corporation Of California, Inc. | 1310 W. 23Rd Street | Tempe Az 85282 | 6024371711 | 5104069696 | 1007 Knox Ave | San Jose, Ca 95122 | Ngo, Hung T | 40373 | 0 | 0 | 0 | 2025-06-20 | Place Polyester Concrete Overlay, Treat Br | Santa Clara County At Various Locations | 69 | 94 | 3203905.11 | 3197197 | 3319142.5 | 55866 | 2026-01-30 | 2024-05-17 | 2024-04-22 |  |  | 86 | 0 | 120 | 5 |  | X
04 | 04-2Q5704 | 2Q5704 | 04-VAR-101-18.7/18.7 |  | ACNH-X085- (066)E | Disney Construction, Inc. | 533 Airport Blvd., Suite 120 | Burlingame Ca 94010 | 6507321004 | 4085954003 | 1007 Knox Ave | San Jose, Ca 96122 | Patel, Nim | 0 | 0 | 0 | 0 | 2025-12-20 | Replace Stormwater Pumps And Construct Dra | Santa Clara County In And Near Morgan Hilland San Jose At Various Locations | 61 | 80 | 9514948.13 | 9999786 | 11966346.59 | 55793 | 2025-12-31 | 2024-03-14 | 2024-01-29 |  | S | 178 | 0 | 250 | 43 |  | X
04 | 04-3Q6104 | 3Q6104 | 04-VAR-101-21.3/26.5 |  |  | Truesdell Corporation Of California, Inc. | 1310 W. 23Rd Street | Tempe Az 85282 | 6024371711 | 5107159940 | 1007 Knox Ave | San Jose Ca 95122 | Farsipour Naghibi, Sina | 0 | 103511 | 0 | 0 | 2025-12-22 | Polyester Concrete Overlay, And Structural | Santa Clara County At Various Locations | 100 | 94 | 3689667.55 | 3569569 | 3733080 | 52604 | 2025-01-31 | 2023-07-05 | 2023-06-15 |  |  | 120 | 0 | 120 | 0 |  | X
04 | 04-0K1104 | 0K1104 | 04-VAR-280-/0 |  | ACST-000C- (553)E | Fbd Vanguard Construction | 550 Greenville Road | Livermore Ca 94550 | 9252451300 | 5104969525 | 1007 Knox Ave. | San Jose, Ca 95122 | Kabbani, Muhieddine | 252864 | 0 | 0 | 0 | 2026-02-20 | Construct Concrete Barrier Transition And | Santa Clara County At Various Locations | 95 | 81 | 13464849.83 | 15597831 | 16413831 | 55774 | 2025-03-20 | 2024-04-29 | 2024-04-05 |  |  | 381 | 0 | 400 | 0 |  | X
04 | 04-0K1204 | 0K1204 | 04-VAR-580-/0 |  | HSNH-000C- (543)E | Perry Electric Incorporated | 130 Murwood Court | Walnut Creek Ca 94596 | 9257662778 | 5104218049 | 2525 Stanwell Dr., Ste 100 | Concord, Ca 94520 | Kalantari, Ramin | 46924.44 | 0 | 0 | 0 | 2025-10-20 | Install Rectangular Rapid Flashing Beacon | Alameda And Contra Costa Counties At Various Locations | 88 | 98 | 8571942.72 | 7428226.5 | 8743268.2 | 47764 | 2025-12-01 | 2023-03-15 | 2023-02-17 |  |  | 500 | 0 | 500 | 69 |  | X
04 | 04-4Q2504 | 4Q2504 | 04-VAR-680-.1/20.7 |  |  | Bay Line Cutting & Coring | 501 Cesar Chavez, Suite 101B | San Francisco Ca 94124 | 5107154838 | 3447662454 | 3847 Breakwater Ave | Hayward Ca 94545 | Onate, Ernesto | 7607 | 0 | 0 | 0 | 2026-01-15 | Place Polyester Concrete Overlay, And Repl | Alameda County At Various Locations | 100 | 100 | 3693975.65 | 3997000 | 3955540.2 | 51325 | 2026-01-15 | 2023-07-24 | 2023-06-16 | 2026-01-26 |  | 80 | 0 | 80 | 0 |  | X
04 | 04-0Q4404 | 0Q4404 | 04-VAR-880-/10 |  | ACNH-X081- (036)E | Hoseley Corporation | Po Box 881386 | San Francisco, Ca 94188 | 4154048997 | 5109088819 | 585 Linda Mar Blvd. | Pacifica, Ca 94044 | Kardavani, Kayvan | 3320 | 0 | 0 | 0 | 2026-02-20 | Install Trash Capture Devices And Maintena | San Mateo County At Various Locations | 36 | 96 | 2620123.34 | 2449000 | 2681815 | 55685 | 2026-11-01 | 2024-04-23 | 2024-04-02 |  |  | 140 | 0 | 390 | 0 |  | X
04 | 04-0Q0704 | 0Q0704 | 04-VAR-880-/32 |  | ACST-000C- (559)E | St. Francis Electric Llc | 975 Carden St | San Leandro Ca 94577 | 5104215523 | 5108676156 | 3401 Regatta Blvd. | Richmond, Ca 94804 | Faustin, Glenn | 436757.38 | 0 | 0 | 0 | 2025-07-20 | Modify Ramp Metering Systems, Install Guar | Alameda, Contra Costa, San Mateo, Santa Clara, And Solano Counties At Various Locations | 90 | 63 | 5682132.58 | 8987000 | 9037000 | 55684 | 2025-12-31 | 2024-04-17 | 2024-03-25 |  | S | 180 | 0 | 200 | 0
04 | 04-2Q6404 | 2Q6404 | 04-VAR--/0 |  | ACIM-0802- (378)E | Bay Cities Paving & Grading, Inc. | 1450 Civic Ct Bldg B #400 | Concord Ca 94520 | 9256876666 | 5108071407 | 324 Campus Lane, Ste T | Fairfield, Ca 94534 | Sarwary, Asadullah | 0 | 0 | 0 | 0 |  | Install Trash Capture Housing Devices, Mvp | Solano County At Various Locations | 0 | 0 | 0 | 3884000 | 3884000 | 60388 | 2027-01-11 | 2026-01-29 | 2025-12-15 |  |  | 0 | 0 | 200 | 0
04 | 04-4AC904 | 4AC904 | 04-VAR--/0 |  | HSST-X055- (061)E | Highway Specialty Company, Inc. | Po Box 141 | Palo Cedro Ca 96073 | 5309495637 | 9252606460 | 324 Campus Lane Suite T | Fairfield, Ca 94534 | Brar, Paramdeep | 0 | 0 | 0 | 0 |  | Install Roadside Signs. | Napa County At Various Locations | 0 | 0 | 0 | 1263778.4 | 1263778.4 | 60343 | 2026-11-05 | 2025-12-30 | 2025-11-13 |  |  | 0 | 0 | 250 | 0
04 | 04-0X5804 | 0X5804 | 04-VAR--/0 |  |  | Gba Engineering, Inc. | 18543 Yorba Linda Blvd #394 | Yorba Linda Ca 92886 | 7145106700 | 5107156899 | 585 Linda Mar Blvd. | Pacifica, Ca 94044 | Alshaer, Abdelrahman | 50905.6 | 0 | 0 | 0 | 2025-11-20 | Install Roadside Signs And Pavement Deline | The City And County Of San Francisco At Various Locations | 72 | 12 | 207705.6 | 1673946 | 1673946 | 59395 | 2025-12-15 | 2025-07-14 | 2025-06-05 |  |  | 36 | 0 | 50 | 0 |  | X
04 | 04-0X5704 | 0X5704 | 04-VAR--/0 |  |  | Central Striping Service, Inc. | 3489 Luyung Drive | Rancho Cordova, Ca 95742 | 9166355175 | 5105939011 | 756 Francisco Blvd West | San Rafael, Ca 94901 | Wong, Andrew | 297597.6 | 0 | 0 | 0 | 2025-09-20 | Replace Pavement Delineation, Cold Plane A | Alameda And Sonoma Counties At Various Locations | 100 | 91 | 857740.6 | 924676 | 944676 | 58595 | 2025-12-30 | 2025-06-04 | 2025-05-12 |  |  | 40 | 0 | 40 | 0 |  | X
04 | 04-1W0904 | 1W0904 | 04-VAR--/0 |  | ACST-000C- (569)E | Crosstown Electrical & Data, Inc. John Bejar | 5454 Diaz Street | Irwindale Ca 91706 | 6264850175 | 5103931593 | 1700 South Amphlett Blvd. | San Mateo, Ca 94402 | Inori, Douglas | 630656.3 | 0 | 0 | 250000 | 2026-02-20 | Modifying Traffic Monitoring Station Syste | Marin, Napa, Santa Clara, San Francisco, San Mateo, And Sonoma Counties At Various Locations | 16 | 17 | 2410945.9 | 13963728 | 14198728 | 59638 | 2027-10-25 | 2025-08-01 | 2025-06-19 |  |  | 82 | 0 | 500 | 0 |  | X
04 | 04-0X5904 | 0X5904 | 04-VAR--/0 |  |  | Gba Engineering, Inc. | 18543 Yorba Linda Blvd #394 | Yorba Linda Ca 92886 | 7145106700 | 5104069696 | 1007 Knox Ave. | San Jose, Ca 95122 | Ngo, Hung T. | 375981.38 | 0 | 0 | 0 | 2026-02-20 | Install Roadside Signs And Pavement Deline | Santa Clara County At Various Locations | 51 | 27 | 375981.38 | 1372681 | 1372681 | 59595 | 2026-05-29 | 2025-07-14 | 2025-06-11 |  |  | 23 | 0 | 45 | 0 |  | X
04 | 04-3AC804 | 3AC804 | 04-VAR--/0 |  | HSST-X075- (053)E | Fbd Vanguard Construction, Inc. | 550 Greenville Road | Livermore Ca 94550 | 9252451300 | 5105907543 | 585 Linda Mar Blvd | Pacifica, Ca 94044 | Zhu, Jiahong | 0 | 0 | 0 | 0 |  | Install Advance Warning Signs. | The City And County Of San Francisco At Various Locations | 0 | 0 | 0 | 607770 | 607770 | 60369 | 2026-12-31 | 2026-01-21 | 2025-12-18 |  |  | 0 | 0 | 85 | 0
04 | 04-4AC404 | 4AC404 | 04-VAR--/0 |  | SNHG- X09- (045)E | Peterson-Chase General Engineering Construction, Inc. | 16351 Construction Circle Wes | Irvine Ca 92606 | 9492520441 | 9166348700 | 4030 Occidental Rd. Bldg A | Santa Rosa, Ca 95401 | Galla, Venkat Varun | 0 | 0 | 0 | 0 |  | Install Advance Warning Signs. | Sonoma County At Various Locations | 0 | 0 | 0 | 1147519.5 | 1172519.5 | 60341 | 2026-07-23 | 2026-01-14 | 2025-10-31 |  |  | 0 | 0 | 120 | 0
04 | 04-2Q7404 | 2Q7404 | 04-VAR--/0 |  | ACNH-000C- (548)E | St. Francis Electric, Llc | 975 Carden St | San Leandro Ca 94577 | 5106390639 | 9253603252 | 585 Linda Mar, | Pacifica, Ca 94044-3334 | Taleb, Mohamed | 0 | 0 | 0 | 0 |  | Install Fiber Optic Cable Systems And Modi | Alameda, Santa Clara, San Mateo, And San Francisco Counties At Various Locations | 0 | 0 | 0 | 55957000 | 56147000 | 60262 | 2027-02-11 | 2025-12-15 | 2025-10-24 |  |  | 0 | 0 | 500 | 0
04 | 04-3Y5904 | 3Y5904 | 04-VAR--/0 |  |  | American Civil Constructors West Coast, Llc | 2990 Bay Vista Court, Suite D | Benicia Ca 94510 | 7077468028 | 5104218049 | 2525 Stanwell Drive. Suite 100 | Concord, Ca 94520 | Kalantari, Ramin | 18718 | 0 | 0 | 0 | 2026-01-20 | Place Polyester Concrete Overlay, Grind Br | Contra Costa County At Various Locations | 100 | 85 | 2411923.17 | 2736000 | 2736000 | 59538 | 2026-01-20 | 2025-07-01 | 2025-05-23 |  |  | 70 | 0 | 70 | 0 |  | X
04 | 04-1Q7214 | 1Q7214 | 04-VAR--/0 |  | ACIM-000C- (568)E | Bay Cities Paving & Grading, Inc. | 1450 Civic Ct Bldg B #400 | Concord Ca 94520 | 9256872122 | 9252505611 | 5675 B Gibraltar Drive | Pleasanton, Ca 94588 | Dike, Eddie | 1380793.16 | 0 | 0 | 0 | 2026-02-20 | Install Fiber Optic Cable System, Ramp Met | Alameda, Contra Costa And Solano Counties At Various Locations | 4 | 2 | 1564595.66 | 93523406.06 | 93623406.06 | 60164 | 2028-12-20 | 2025-10-24 | 2025-09-25 |  |  | 30 | 0 | 700 | 0 |  | X
04 | 04-0Y8404 | 0Y8404 | 04-VAR--/0 |  |  | Myers & Sons Construction, Llc | 45 Morrison Ave | Sacramento Ca 95838 | 9162839950 | 5107159940 | 1007 Knox Ave. | San Jose, Ca 95122 | Farsipour Naghibi, Sina | 0 | 35166.72 | 0 | 0 | 2025-10-20 | Place Polyester Concrete Overlay, Treat Br | Santa Clara County At Various Locations | 70 | 96 | 3147659.89 | 3122120 | 3156120 | 56099 | 2025-03-10 | 2024-06-05 | 2024-04-04 |  |  | 63 | 0 | 90 | 0 |  | X
04 | 04-0AA804 | 0AA804 | 04-VAR--/0 |  | ACST-000C- (573)E | Alfaro Communications Construction, Inc. | 15614 S. Atlantic Avenue | Compton Ca 90221 | 3106698949 | 5103857079 | 3847 Breakwater Ave. | Hayward, Ca 94545 | Nguyen, Danh-Ngon | 0 | 0 | 0 | 0 |  | Modifying Camera Systems & Changeable Mess | Alameda, Contra Costa, Sonoma And Solano Counties At Various Locations | 0 | 0 | 0 | 7977736.72 | 7977736.72 | 60371 | 2027-07-01 | 2026-01-26 | 2025-12-10 |  |  | 0 | 0 | 340 | 0
04 | 04-155004 | 155004 | 04-VAR--/0 |  | ACIM-000C- (566)E | Teichert Energy & Utilities Group, Inc. | 3500 American River Drive | Sacramento Ca 95864 | 9164385800 | 9166346646 | 3401 Regatta Blvd. | Richmond, Ca 94520 | Nou, Bunma | 197205.56 | 0 | 0 | 0 | 2026-02-20 | Install Fiber Optic Communication System. | Alameda, Contra Costa And Solano Counties At Various Locations | 2 | 0 | 197205.56 | 53123992 | 53293992 | 60235 | 2028-03-16 | 2025-11-26 | 2025-10-20 |  |  | 8 | 0 | 530 | 0 |  | X
04 | 04-0K1004 | 0K1004 | 04-VAR--/0 |  | HSST-X095- (038)E | Mike Brown Electric Co. | 561 Mercantile Drive | Cotati Ca 94931 | 7077928100 | 5108676033 | 324 Campus Lane Suite T | Fairfield, Ca 94534 | Lane, Isaiah | 16970 | 10529.22 | 0 | 0 | 2025-12-20 | Install Accessible Pedestrian Signal Syste | Solano County At Various Locations. | 100 | 95 | 2734114.48 | 3550160 | 2857365.87 | 56766 | 2025-12-19 | 2024-11-08 | 2024-10-10 |  |  | 210 | 0 | 210 | 0 |  | X
04 | 04-1Q2004 | 1Q2004 | 04-VAR--/0 |  | HSST-X081- (037)E | Columbia Electric, Inc. | 1980 Davis St. | San Leandro Ca 94577 | 5104309505 | 5103931593 | 1700 South Amphlett Blvd. | San Mateo, Ca 94402 | Lam, Peter | 145632.28 | 4839.74 | 0 | 0 | 2026-02-20 | Install Rectangular Rapid Flashing Beacon | San Mateo County At Various Locations | 54 | 43 | 3031846.28 | 6792399 | 7002399 | 57071 | 2026-07-08 | 2025-01-14 | 2024-11-21 |  |  | 107 | 0 | 200 | 0 |  | X
04 | 04-0P7604 | 0P7604 | 04-VAR--/0 |  | HSST-X095- (037)E | St. Francis Electric, Llc | 975 Carden St | San Leandro Ca 94577 | 5106390639 | 5108676033 | 324 Campus Lane Suite T | Fairfield, Ca 94534 | Lane, Isaiah | 378616.13 | 15073.3 | 0 | 0 | 2026-02-20 | Ped Hybrid Beacon Systems & Modifying Sign | Solano County At Various Locations | 81 | 49 | 3023458.31 | 6167000 | 6147547.59 | 57116 | 2026-03-30 | 2025-02-05 | 2024-12-17 |  |  | 114 | 0 | 140 | 0
04 | 04-0Y6604 | 0Y6604 | 04-VAR--/0 |  | SHIM-X001- (673)E | Wgj Enterprises, Inc. Dba Pci | 975 W. 1St Street | Azusa Ca 91702 | 5622180504 | 5105992574 | 3401 Regatta Blvd. | Richmond, Ca 94804 | Aldabbas, Mohammad | 2000 | 0 | 0 | 0 | 2026-02-20 | Replace Pavement Delineation, And Install | Alameda County At Various Locations | 13 | 1 | 2000 | 357105 | 367105 | 60365 | 2026-05-05 | 2026-01-21 | 2025-11-04 |  |  | 8 | 0 | 60 | 0 |  | X
05 | 05-1S4904 | 1S4904 | 05-0SB-1-10.1/10.1 | 20.20.201130 |  | Security Paving Company, Inc. | 3075 Townsgate Road, Ste. 200 | Westlake Village, Ca 91361 |  | 8056108218 | 2053 Preisker Lane, Suite E | Santa Maria, Ca 93454 | Moreno, Arturo | 0 | 804341.68 | 0 | 0 | 2026-02-20 | Rep.Embankment,Wall Construction & Tc | Excavating&Grading,Repair/Stabalize Embanksoldier Pile Wall Construction,Paving And Traffic Control. Dirs Efa 05A | 46 | 50 | 2363187.75 | 23500 | 4685000 | 57260 | 2026-02-20 | 2025-03-10 | 2025-02-17 |  |  | 46 | 0 | 100 | 0 |  | X
05 | 05-1T9904 | 1T9904 | 05-0SB-1-72.0/.3 | 20.20.201130 |  | David Crye General Engineeringcontractor Inc. | 1170 Quintana Road | Morro Bay, Ca 93442 |  | 8059221611 | 2053 Preisker Lane, Suite E | Santa Maria, Ca 93454 | Reed,Albert (Gaston, Philip) | 0 | 0 | 0 | 0 |  | Rem.Sediment&Slide Matl.,Tc & Erosion Ctrl | Remove Sediment,Restore Hydraulic Capacityremove Slide Material,Tc & Erosion Controlrem.Sediment&Slide Matl.,Tc & Erosion Ctrldirs | 0 | 0 | 0 | 4750 | 935000 | 60375 | 2026-03-23 | 2026-01-09 | 2026-01-08 |  |  | 0 | 0 | 50 | 0
05 | 05-1T9704 | 1T9704 | 05-0SB-101-2.0/.4 | 20.20.201130 |  | John Madonna Construction | Po Box 5310 | San Luis Obispo, Ca 93403 |  | 8054418439 | 270 E. Hwy 246 Suite 202-203 | Buelton, Ca 93427 | Murdock, Kevin & Joe Persons | 0 | 0 | 0 | 0 |  | Remove Mudslide,Rep.Erosion,Tc And Re-Est. | Relieve Tc, Remove Mudslide, Rep. Erosion Clear Debris And Re-Establish Travelway Remove Mudslide,Rep.Erosion,Tc And Re-Est.Dirs E | 0 | 0 | 0 | 18500 | 3700000 | 60312 | 2026-04-22 | 2026-01-03 | 2026-01-03 |  |  | 0 | 0 | 75 | 0
05 | 05-1T9604 | 1T9604 | 05-0SB-101-3.0/.3 | 20.20.201130 |  | Calportland Construction | 1625 East Donovan Road | Santa Maria, Ca 93454 |  | 8054418439 | 270 E.Hwy 246, Suite 202 | Buelton, Ca 93427 | Murdock, Kevin | 0 | 0 | 0 | 0 |  | Inj.Poly,Concrete Base,Restore Pavement | Inj.Polyurethane,Place Concrete Base, Restore Pavement And Temp Traffic Control Inj.Poly,Concrete Base,Restore Pavement Dirs Efa 0 | 0 | 0 | 0 | 7500 | 1485000 | 60433 | 2026-04-30 | 2026-02-12 | 2026-01-09 |  |  | 0 | 0 | 75 | 0
05 | 05-1T9804 | 1T9804 | 05-0SB-154-260.0/26.3 | 20.20.201130 |  | Access Limited Construction | 1102 Pike Lane | Oceano, Ca 93445 |  | 8056885920 | 270 E. Hwy 246 Suite 202-203 | Buelton, Ca 93427 | Murdock, Kevin/Person, Person, Joe | 0 | 0 | 0 | 0 |  | Repair Rockfall Protection System | Rockfall Protection System,Clear Catchmntsrepair Flexible Rock Fences,Anchors & Tc Clr Rck And Debris,Rep.Rck Fence,Anchors Dirs E | 0 | 0 | 0 | 3000 | 3000 | 60422 | 2026-04-02 | 2026-01-19 | 2026-01-19 |  |  | 0 | 0 | 50 | 0
05 | 05-1S8404 | 1S8404 | 05-MON-1-10.4/10.4 | 20.20.201130 |  | Kinyon Construction, Inc. | 1533 W.Betteravia Road | Santa Maria,Ca 93455 |  | 8057482342 | 3230 Riverside Avenue, Suite 30 | Paso Robles, Ca 93446 | Iman, Hassan | 0 | 46312.5 | 0 | 0 | 2025-01-31 | Const.,Install & Connect New Pv Elec.Equip | Willow Springs Solar Replacement Remove Existing Pv Elec.Equip. Construct, Install & Connectg New Pv Elec. Equip Dirs Efa 05A2821 | 35 | 4 | 46312.5 | 5625 | 1110000 | 57077 | 2025-05-14 | 2025-01-24 | 2024-11-13 |  |  | 35 | 0 | 100 | 0 |  | X
05 | 05-1R6404 | 1R6404 | 05-MON-1-27.8/27.8 | 20.20.201130 |  | Papich Construction Co Inc | 398 Sunrise Terrace | Arroyo Grande, Ca 93420 |  | 8055500734 | 3230 Riverside Ave Ste 30 | Paso Robles, Ca 93446 | Silva, Rick | 0 | 1315865.2 | 0 | 0 | 2026-02-19 | Regent Slide Rock Slide Repair | Regent Slide. Remove/Haul Away Material. Restore Hma Pavement Sect. Install Rockfalprotection. Erosion & Traffic Control Dirs Efa | 100 | 63 | 52419749.8 | 25000 | 82585000 | 55640 | 2024-11-12 | 2024-02-23 | 2024-02-23 |  |  | 214 | 0 | 180 | 0
05 | 05-1R6304 | 1R6304 | 05-MON-1-29.5/29.5 | 20.20.201130 |  | Papich Construction Co Inc | 398 Sunrise Terrace | Arroyo Grande, Ca 93420 |  | 8054712102 | 3230 Riverside Ave Ste 30 | Paso Robles, Ca 93446 | Silva, Rick | 0 | 14767.4 | 0 | 0 | 2025-07-20 | Remove Slide Material/Install Netting | Dolan Park Landslide On Hwy 001. Remove Slide Material Restore Roadway. Install Rockfall Netting And Traffic Control Dirs Efa 05A | 100 | 65 | 5710073.09 | 9000 | 8785000 | 55565 | 2025-10-25 | 2024-05-08 | 2024-02-09 |  |  | 84 | 0 | 50 | 0
05 | 05-1P2104 | 1P2104 | 05-MON-1-44.3/0 |  | ACST-ER - (15E)004 | Granite Rock Company | 5225 Hellyer Avenue, Suite 22 | San Jose Ca 95138 |  | 8053935930 | 1529 Salinas Highway | Monterey Ca 93940 | Sandhu,Mandip | 0 | 0 | 0 | 0 |  | Construct Soldier Pile Wall And Structural | Monterey County Near Big Sur About 1.1 Miles South Of Pfeiffer Canyon Bridge | 0 | 0 | 0 | 3034376.1 | 3034376.1 | 60362 |  | 2026-01-21 | 2025-12-19 |  |  | 0 | 0 | 425 | 0
05 | 05-1Q8004 | 1Q8004 | 05-MON-1-44.7/69.8 | 20.20.201130 |  | Granite Rock Company | 5225 Hellyer Ave Ste 220 | San Jose, Ca 95138 | 4805741400 | 8055409841 | 1529 Hwy 68 | Monterey, Ca 93940 | Pannu, Art | 0 | 310326.59 | 0 | 0 | 2026-02-20 | Clear Mud And Debris. Clean Culverts | In Mon Cnty On Rte 001 Pm 42.2/72.0 Clear Mud And Debris. Clean Culverts And Repair Erosion. Provide Temp Traffic Contrdirs Efa 05 | 28 | 26 | 6665969.65 | 4750 | 25262750 | 48424 | 2026-02-28 | 2023-05-02 | 2023-01-12 |  |  | 28 | 0 | 100 | 0 |  | X
05 | 05-1T2104 | 1T2104 | 05-MON-1-50.0/54 | 20.20.201130 |  | Granite Rock Company | 5225 Hellyer Avenue, Ste 220 | San Jose, Ca 95138 |  | 8053935930 | 1529 Salinas Highway | Monterey, Ca 93940 | Sandhu, Mandip | 0 | 57138.31 | 0 | 0 | 2026-01-31 | Culvert Repair/Replace And Traffic Control | Repair/Replace Culverts & Traffic Control Culvert Repair Or Replace And Traffic Ctrlpoint Sur Drainage Repairs/Culvert Repair Dirs | 62 | 19 | 86125.63 | 2305 | 446000 | 60096 | 2026-01-31 | 2025-10-10 | 2025-09-24 |  |  | 31 | 0 | 50 | 0 |  | X
05 | 05-1Q1604 | 1Q1604 | 05-MON-1-60.0/0 |  | BFST-S001- (674)E | American Civil Constructors West Coast, Llc | 2990 Bay Vista Court, Suite D | Benicia Ca 94510 |  | 8053935930 | 1529 Salinas Highway | Monterey Ca 93940 | Sandhu,Mandip | 0 | 0 | 0 | 0 |  | Electrochemical Chloride Extraction (Ece) | Monterey County Near Big Sur At Rocky Creek Bridge | 0 | 0 | 0 | 9057000 | 9057000 | 60317 |  | 2026-01-14 | 2025-12-08 |  |  | 0 | 0 | 530 | 0
05 | 05-1Q9604 | 1Q9604 | 05-MON-1-100.0/1 | 20.20.201130 |  | A.Teichert & Son, Inc Dba Teichert Construction | 3500 American River Dr | Sacramento, Ca 95864 |  | 8055409841 | 1529 Hwy 68 | Monterey, Ca 93940 | Pannu, Art | 0 | 18771.57 | 0 | 0 | 2026-01-31 | Remove Flood Debris | Pajaro River Bridge/Surrounding Areas Thatneed To Remove Flood Debris. Flood Water Pumping. Temp Traffic Control Dirs Efa 05A2621 | 31 | 68 | 1251687.85 | 9250 | 1835000 | 49784 | 2026-01-31 | 2023-05-24 | 2023-03-12 |  |  | 31 | 0 | 100 | 0 |  | X
05 | 05-1K6404 | 1K6404 | 05-MON-1-101.5/102 |  | PTNH-P001- (702)E | Granite Construction Company | 585 W Beach Street | Watsonville Ca 95076 | 8318890275 | 8057486095 | 140 Dubois Street Ste E | Santa Cruz, Ca 95060 | Nguyen, Ian | 539146.85 | 0 | 0 | 0 | 2025-12-20 | Widening Mvp, Install Culverts And Modify | Monterey And Santa Cruz Counties At Various Locations From Trafton Road Undercrossing To 0.2 Mile North Of Larkin Valley Road. | 100 | 88 | 2719901.47 | 2959959.95 | 3020818.06 | 57239 | 2026-04-20 | 2025-02-26 | 2025-01-30 |  |  | 90 | 0 | 75 | 0 |  | X
05 | 05-1S1604 | 1S1604 | 05-MON-1-600.0/60 | 20.20.201130 |  | Gordon N. Ball, Inc. | 1777 Oakland Blvd Ste 300 | Walnut Creek, Ca 94596 |  | 8319981546 | 1529 Hwy 68/Salinas Hwy | Monterey, Ca 93940 | Uberhuaga, Jorge | 0 | 24727.69 | 0 | 0 | 2026-02-05 | New Viaduct To Restore Two Way Traffic | Bld New Rocky Creek Viaduct After Slipout Construct Viaduct Structure Restore Two Way Traffic/ Traffic Controll Dirs Efa 05A2765 | 8 | 58 | 12113504.28 | 105000 | 20985000 | 56204 | 2026-02-28 | 2024-07-16 | 2024-06-14 |  |  | 28 | 0 | 350 | 0 |  | X
05 | 05-1S9504 | 1S9504 | 05-MON-1-/0 | 20.20.201130 |  | Access Limited Construction | 1102 Pike Lane | Oceano, Ca 93445 |  | 8054712102 | 775 Arlington Street | Cambria, Ca 93428 | Silva, Rick | 0 | 53561.74 | 0 | 0 | 2026-02-20 | Repair Rockfall Protection System & Tc | Clear Rockfall Catchements.Repair Rockfallprotection Systems. Traffic Control Rep.Rockfall Protection System And Tc Dirs Efa 05A28 | 14 | 12 | 53561.74 | 2305 | 446000 | 60370 | 2026-04-16 | 2025-05-27 | 2025-05-01 |  |  | 7 | 0 | 50 | 0 |  | X
05 | 05-1J8904 | 1J8904 | 05-MON-101-28.2/97.5 |  | PTNH-Q101- (452)E | A. Teichert & Son, Inc. Dba Teichert Construction | 3500 American River Dr | Sacramento Ca 95864 |  | 8055501306 | 8115 Prunedale North Road | Prunedale, Ca 93907 | Ontiveros, David | 0 | 0 | 0 | 0 |  | Repair And Replace Drainage Culverts, And | Monterey County At Various Locations From 0.1 Mile North Of Paris Valley Road Overcrossing To 0.4 Mile South Of Mallory Canyon Roa | 0 | 0 | 0 | 14122511 | 14122511 | 60360 |  | 2026-01-26 | 2025-12-22 |  |  | 0 | 0 | 605 | 0
05 | 05-0T9914 | 0T9914 | 05-MON-101-41.1/42.2 | HB1 | HSNH-Q101- (407)E | Wabo Landscape & Construction,Inc. | 726 Alfred Nobel Drive | Hercules Ca 94547 |  | 5623705097 |  |  | Rianda Adam | 3905 | 0 | 0 | 0 | 2026-02-20 | Landscape Mitigation Planting, Irrigation, | Monterey County In And Near King City From0.1 Mile South Of Broadway Street To 0.2 Mile North Of Jolon Road | 75 | 94 | 809126.66 | 843669 | 860069 | 50024 | 2026-11-16 | 2023-06-08 | 2023-04-18 |  |  | 637 | 0 | 845 | 0 |  | X
05 | 05-1P5344 | 1P5344 | 05-MON-101-86.1/87.3 |  |  | Gordon N. Ball, Inc. | 1777 Oakland Blvd., Ste 300 | Walnut Creek, Ca 94596 |  | 8314555466 | 8115 Prunedale North Road | Prunedale, Ca 93907 | Garcia, Santiago | 0 | 0 | 0 | 0 | 2026-01-27 | Planting, Irrigation, Slope Paving And Tra | Monterey County In Salinas At Various Locations From Sanborn Road Undercrossing To East Market Street Undercrossing | 100 | 100 | 1813363.72 | 1714170 | 1828339.35 | 47844 | 2026-01-27 | 2023-03-22 | 2023-02-28 | 2026-01-30 |  | 120 | 0 | 370 | 0 |  | X
05 | 05-1H6914 | 1H6914 | 05-MON-101-98.8/100.3 |  | PTNH-Q101- (435)E | Precision Grade, Inc. | 25 San Juan Grade Road, Suite | Salinas Ca 93906 |  | 8056108215 | 8115 Prunedale North Road | Prunedale, Ca 93907 | Brar, Baljinder | 34368.2 | 0 | 0 | 0 | 2026-02-20 | Install Culverts, Concrete Barrrier And M | Monterey County Near Prunedale From 0.4 Mile North Of Crazy Horse Canyon Rd To Dunbarton Road | 40 | 91 | 6395295.02 | 6818314 | 7153314 | 57877 | 2026-12-31 | 2025-04-29 | 2025-03-28 |  |  | 145 | 0 | 360 | 0 |  | X
05 | 05-1P5334 | 1P5334 | 05-MON-156-1.4/1.3 |  |  | Hoseley Corporation | 96F Pier Admin Building Suite | San Francisco Ca 94124 |  | 8314555466 | 8115 Prunedale North Road | Prunedale, Ca 93907 | Garcia, Santiago | 2310 | 0 | 0 | 0 | 2026-02-20 | Planting, Irrigation Work And Ornamental F | Monterey County In Castroville At Geil Street Pedestrian Overcrossing | 14 | 96 | 955224.5 | 940000 | 987452.31 | 55024 | 2026-02-28 | 2024-01-29 | 2023-12-12 |  |  | 82 | 0 | 580 | 0 |  | X
05 | 05-1H6504 | 1H6504 | 05-MON-183-8.3/9.9 |  | ACST-S183- (006)E | Granite Construction Company | 580 W Beach Street | Watsonville Ca 95076 |  | 8053190940 | 8115 Prunedale North Road | Pruendale, Ca 93907 | Munes,Nash | 698895.06 | 30723.81 | 0 | 0 | 2026-02-19 | Hma (Type A), Rhma-G, Drainage, Landscape, | Monterey County In Castroville From 0.1 Mile South Of Del Monte Avenue To Route 1/183 Junction. | 27 | 34 | 6562065.63 | 19123028 | 19418517.9 | 57240 | 2026-11-04 | 2025-02-26 | 2025-01-17 |  |  | 161 | 0 | 600 | 0 |  | X
05 | 05-1S9104 | 1S9104 | 05-SB-1-19.8/20.1 | 20.20.201130 |  | Calportland Construction | 1625 East Donovan Road | Santa Maria, Ca 93454 | 8053453581 | 8054418439 | 270 E. Hwy 246, Ste. 202 | Buellton, Ca 93427 | Murdock, Kevin | 0 | 59214.25 | 0 | 0 | 2026-01-22 | Remove Failed Pavement Etc. & Hma | Remove Failed Pavement, Exvacate To Subgrdplace Cl2 Ab On Subgrade Geotextile, Lean Concrete Base, Hma Dirs Efa 05A2903 | 23 | 3 | 59214.25 | 10500 | 2085000 | 60162 | 2026-01-22 | 2025-09-02 | 2025-07-07 | 2026-01-25 |  | 35 | 0 | 150 | 0 |  | X
05 | 05-1T4004 | 1T4004 | 05-SB-1-46.5/46.5 | 20.20.201130 |  | Granite Construction Company | 5335 Debbie Road | Santa Barbara, Ca 93111 | 8059649951 | 8056108218 | 2053 Preisker Lane, Ste E | Santa Maria, Ca 93454 | Moreno, Arturo | 0 | 144818.42 | 0 | 0 | 2026-01-20 | Rep.Washout,Rockery,Pavement & Trfc Ctrl | Repair Washout, Plack Rockery,Restore Pavement, Reinstall Guardrail, Install Down Drain & Perform Temp Traffic Ctrl Dirs Efa 05A29 | 34 | 30 | 595853.59 | 10000 | 1985000 | 60163 | 2026-02-02 | 2025-12-12 | 2025-09-26 |  |  | 17 | 0 | 50 | 0 |  | X
05 | 05-1H4404 | 1H4404 | 05-SB-1-50.3/50.6 |  | BFST-S001- (670)E | M.C.M. Construction, Inc. | 6413 32Nd Street Suite A | North Highlands Ca 95660 | 9163341221 | 8057481087 | 35 S. La Patera Lane, Suite E | Goleta, Ca 93117 | Jacob Cooper | 27057.2 | 0 | 0 | 0 | 2026-02-20 | Santa Maria River Bridge (Replace). | Santa Barbara And San Luis Obispo Countiesin And Near Guadalupe At Santa Maria Riverbridge | 2 | 0 | 27057.2 | 47133513 | 47408513 | 60344 | 2030-03-15 | 2025-11-10 | 2025-09-30 |  |  | 27 | 0 | 1290 | 0 |  | X
05 | 05-0N71Y4 | 0N71Y4 | 05-SB-101-1.4/4.8 |  |  | Granite Construction Company | 5335 Debbie Road | Santa Barbara, Ca 93111 | 8053312649 | 8057483132 | 3561 Foothill Road | Carpinteria, Ca 93013 | Jones, David | 12109.44 | 0 | 0 | 0 | 2026-02-20 | Install Mitigation Planting | Santa Barbara County In Carpenteria From 0.2 Mile South Of Bailard Avenue Overcrossing To 0.7 Mile South Of South Padaro Lane | 100 | 92 | 2884417.48 | 2989274.75 | 3122862.77 | 42664 | 2026-09-25 | 2022-05-23 | 2022-05-23 |  |  | 774 | 0 | 210 | 7 |  | X
05 | 05-0N72Y4 | 0N72Y4 | 05-SB-101-4.4/7.7 |  |  | Granite Construction Company | Po Box 50085 | Watsonville Ca 95077 |  | 8057483132 | 35 S. La Patera Lane, Sutie E | Goleta, Ca 93117 | Jones, David | 490962 | 33388.13 | 1800 | 0 | 2026-02-20 | Sb 101 4B (Padaro) Landscape Planting Proj | Santa Barbara County Near Carpinteria And Summerland, From 0.9 Miles South Of South Padaro Lane Undercrossing To 0.6 Miles North O | 1 | 84 | 4049853.16 | 4593515.98 | 4746234.1 | 57069 | 2029-02-09 | 2024-12-24 | 2024-10-21 |  |  | 8 | 0 | 950 | 0 |  | X
05 | 05-0N73Y4 | 0N73Y4 | 05-SB-101-7.3/9.6 |  |  | Granite Construction Company | 580 W Beach Street | Watsonville Ca 95076 |  | 8057483132 | 35 S. La Patera Lane, Suite E | Goleta, Ca 93117 | David Jones | 7896 | 0 | 0 | 0 | 2026-02-20 | Install Mitigation Planting | Santa Barbara County, In And Near Summerland From 0.2 Miles North Of Padaro Lane Overcrossing To San Ysidro Creek Bridge | 99 | 86 | 2787119 | 3149406 | 3224504.54 | 51945 | 2028-02-02 | 2023-08-02 | 2023-04-21 |  |  | 263 | 0 | 265 | 0 |  | X
05 | 05-0N74V4 | 0N74V4 | 05-SB-101-9.2/9.7 |  | ACNH-Q101- (426)E | Granite Construction Company | Po Box 50085 | Watsonville Ca 95077 |  | 8056982393 | 3690 Santa Claus Lane | Carpinteria, Ca 93013 | Jason Kline | 1364752.68 | 28808.31 | 0 | 0 | 2026-02-20 | Highway 101: Carpinteria To Santa Barbara | Santa Barbara County At Montecito From 0.2Mile North Of Sheffield Drive Undercrossing To 0.3 Mile South Of San Ysidro Road Overcro | 65 | 74 | 49576519.31 | 63821017 | 66843622.26 | 55922 | 2026-12-10 | 2024-06-07 | 2024-06-07 |  |  | 368 | 0 | 570 | 0 |  | X
05 | 05-0N74U4 | 0N74U4 | 05-SB-101-9.7/10.6 | HE11 | ACNH-Q101- (420)E | Granite Construction Company | 3005 James Rd | Bakersfield Ca 93308 |  | 8056982393 |  |  | Kline, Jason | 686473.39 | 0 | 0 | 0 | 2026-02-20 | Highway 101: Carpinteria To Santa Barbara | Santa Barbara County In And Near Santa Barbara From 0.3 Mile South Of San Ysidro Road Overcrossing To 0.1 Mile North Of Olive Mill | 83 | 91 | 47608510.64 | 48227222.66 | 52434688.08 | 50964 | 2026-07-15 | 2023-06-16 | 2023-06-16 |  |  | 484 | 0 | 580 | 5 |  | X
05 | 05-1K03U4 | 1K03U4 | 05-SB-101-10.0/10.5 |  |  | Granite Construction Company | 5335 Debbie Road | Santa Barbara Ca 93111 |  | 8057228935 | 3690 Santa Claus Lane | Carpinteria, Ca 93013 | Jason Kline/Taylor Merlo | 3322.5 | 0 | 0 | 0 | 2025-12-20 | Highway 101: Carpinteria To Santa Barbara | Santa Barbara County In And Near Santa Barbara From 0.1 Mile South Of San Ysidro Road Overcossing To 0.1 Mile North Of Olive Mill | 100 | 96 | 15041109.27 | 13936108.17 | 15468969.51 | 45724 | 2025-12-20 | 2022-11-29 | 2022-11-29 |  |  | 260 | 0 | 260 | 0 |  | X
05 | 05-0N7054 | 0N7054 | 05-SB-101-10.4/11.1 |  |  | Granite Construction Company | Po Box 50085 | Watsonville Ca 95077 | 7605733649 | 8054403057 | 3690 Santa Claus Lane | Carpinteria, Ca 93013 | Tristan Gebhart | 1269039.49 | 805254.22 | 0 | 0 | 2026-02-20 | Highway 101: Carpinteria To Santa Barbara | In Santa Barbara County In And Near Santa Barbara From 0.1 Mile South Of Olive Mill Road Overcrossing To 0.3 Mile South Of Cabrill | 60 | 62 | 28719555.73 | 38261867.36 | 45986055.32 | 56213 | 2026-12-21 | 2024-07-23 | 2024-07-23 |  |  | 317 | 0 | 526 | 0 |  | X
05 | 05-1H4304 | 1H4304 | 05-SB-101-21.4/21.9 | HA21 | ACNH-Q101- (410)E | M.C.M. Construction, Inc. | 6413 32Nd Street | North Highlands Ca 95660 |  | 9517502468 | 35 S. La Patera Lane | Goleta, Ca 93117 | Yogarajah, Manny/ Chhay, Alis | 1250 | 67865.46 | 0 | 0 | 2026-02-20 | Replace Structural Concrete Bridges. | Santa Barbara County In Goleta From Route 101/217 Separation To 0.3 Mile North Of San Jose Creek Bridge | 65 | 98 | 20765255.55 | 19884404.3 | 20765147.82 | 48210 | 2026-07-21 | 2023-04-04 | 2023-03-02 |  |  | 468 | 0 | 720 | 2 |  | X
05 | 05-1C9504 | 1C9504 | 05-SB-101-36.0/37 |  | BFNH-Q101- (424)E | M.C.M. Construction, Inc. | 6413 32Nd Street Suite A | North Highlands Ca 95660 |  | 8057481087 | 270 Hwy 246, Suite 203 | Buellton, Ca 93427 | Jacob Cooper | 782948 | 0 | 0 | 0 | 2026-02-20 | Cold Plane Ac Pvmt, Rhma, Lighting Systems | Santa Barbara County About 8.0 Miles West Of Goleta From 0.6 Mile East Of Refugio Road Undercrossing To 0.4 Mile West Of Refugio R | 43 | 31 | 16507431.29 | 52456947 | 52822747 | 56129 | 2027-12-15 | 2024-07-25 | 2024-07-09 |  |  | 304 | 0 | 700 | 0 |  | X
05 | 05-1H8604 | 1H8604 | 05-SB-101-46.2/52.3 | HA22 | ACNH-Q101- (409)E | Calportland Construction | 1625 East Donovan Rd | Santa Maria Ca 93456 |  | 9095605695 | 35 S. La Patera Lane, Suite E | Goleta, Ca 93117 | Jason Torres/Kevin Murdock | 52000 | 1176007.74 | 3306.17 | 0 | 2026-01-23 | Cold Plane Ac Pvmt, Place Hma, Rhma-G, Hma | Santa Barbara County Near Gaviota From 0.1Mile North Of Gaviota Beach State Park To Old Coast Highway | 100 | 100 | 49541537.53 | 46517000 | 55030678.45 | 47265 | 2026-01-23 | 2023-03-03 | 2023-02-01 | 2026-01-25 |  | 420 | 0 | 330 | 93 |  | X
05 | 05-1R1404 | 1R1404 | 05-SB-101-47.0/47.3 | 20.20.201130 |  | Calportland Construction | 1625 E Donovan Rd | Santa Maria, Ca 93454 |  | 8054418439 | 270 E. Hwy 246, Ste 202 | Buellton, Ca 93427 | Murdock,Kevin/Engler, Jaime | 0 | 165067.87 | 0 | 0 | 2026-02-20 | Gaviota Creek Repairs | Gaviota Creek Scour Repairs, Sb Cnty 101 @Gaviota Tunnels. Repair Secant Pile Wall &Repair Embankment. Dirs Efa 05A2625 | 100 | 91 | 15995698.24 | 75000 | 17485000 | 50887 | 2025-10-31 | 2023-05-26 | 2023-05-15 |  |  | 266 | 0 | 100 | 0 |  | X
05 | 05-1K4504 | 1K4504 | 05-SB-101-52.3/56.1 |  | ACNH-Q101- (438)E | Calportland Construction | 1625 East Donovan Rd | Santa Maria Ca 93456 |  | 9095605695 | 270 Hwy 246, Suite 203 | Buellton, Ca 93427 | Jason Torres/Kevin Murdock | 245872.5 | 36726.27 | 0 | 0 | 2026-02-18 | Cold Plane And Rhma/Hma Roadway And Bridge | Santa Barbara County Near Buellton From Old Coast Highway To 0.4 Mile South Of Santa Rosa Road Overcrossing | 54 | 45 | 7376449.74 | 16456569.9 | 16538667.95 | 57265 | 2026-11-19 | 2025-03-03 | 2025-01-28 |  | S | 97 | 0 | 180 | 0 |  | X
05 | 05-1F7904 | 1F7904 | 05-SB-101-55.9/56.2 | HA21 |  | Spectrum Construction Group, Inc. | 16 Goodyear, Ste. 140 | Irvine Ca 92618 | 9492991400 | 8056885920 | 270 E Hwy 246 #203 | Buellton, Ca 93427 | Ballentine, David | 13303.8 | 0 | 0 | 0 | 2021-10-20 | Bridge Rail Upgrade | In Santa Barbara County Near Buellton From 0.1 Mile South Of Nojoqui Creek Bridge To 0.3 Mile South Of Santa Rosa Road Overcross | 27 | 16 | 956780.16 | 5840830.83 | 5895830.83 | 41248 | 2022-07-01 | 2020-09-21 | 2020-08-20 |  |  | 67 | 0 | 505 | 0 |  | X
05 | 05-1M1004 | 1M1004 | 05-SB-101-56.1/65 |  | NH -Q101- (456) E | Calportland Construction | 1625 East Donovan Rd | Santa Maria Ca 93456 |  | 8057481087 | 270 Hwy 246, Suite 203 | Buellton, Ca 93427 | Jacob Cooper/Jason Torres | 0 | 0 | 0 | 0 |  | Hma (Type A), Rhma-G Overlay, Install Ligh | Santa Barbara County From 0.2 Mile South Of Santa Rosa Road To 2.4 Miles South Of San Antonio Creek | 0 | 0 | 0 | 26492863.02 | 26546863.02 | 60380 |  | 2026-01-29 | 2025-12-30 |  |  | 0 | 0 | 240 | 0
05 | 05-1K5104 | 1K5104 | 05-SB-101-65.0/84.1 |  | PTNH-Q101- (437)E | Central Coast Financial Group,Inc. Dba Ccfg Construction | 17750 Wards Ferry Rd | Sonora Ca 95370 |  | 8056108218 | 2053 Preisker Ln, Ste E | Santa Maria, Ca 93454 | Arturo Moreno | 47957.9 | 0 | 0 | 0 | 2026-02-20 | Drainage Systems, Lighting Systems And Rep | Santa Barbara County At And Near Los Alamos And Orcutt At Various Locations From 2.3 Miles North Of Route 154/101 Separation To 0. | 29 | 83 | 3022728.31 | 3351395 | 3530894.32 | 57264 | 2027-04-08 | 2025-03-03 | 2025-01-31 |  |  | 115 | 0 | 400 | 0 |  | X
05 | 05-1H3114 | 1H3114 | 05-SB-154-5.7/6.2 |  |  | Marina Landscape, Inc. | 3707 W Garden Grove Blvd | Orange Ca 92868 | [5 empty] | 0 | 0 | 0 | 0 |  | Landscape Planting. | Santa Barbara County Near Santa Ynez From 0.2 Mile North Of Edison Street/Baseline Avenue To 0.3 Mile South Of Edison Street/Basel | 0 | 0 | 0 | 374370 | 374370 | 60423 |  | 2026-02-17 | 2025-11-18 |  |  | 0 | 0 | 810 | 0
05 | 05-1R6504 | 1R6504 | 05-SB-154-26.0/30.2 | 20.20.201130 |  | Calportland Construction | 1625 E Donovan Road | Santa Maria, Ca 93454 |  | 8054418439 | 270 E. Hwy 246, Suite 202 | Buellton, Ca 93427 | Murdock, Kevin/Person, Joe | 0 | 1350698.32 | 0 | 0 | 2026-02-20 | Repair Slipouts,Slides & Rockfall Fence | Slipouts, Slides And Rockfall Fence Repairin Santa Barbara County On Hwy 154 At San Marcos And San Antonio Dirs Efa 05A | 100 | 85 | 14079477.47 | 21000 | 20086000 | 55658 | 2025-09-01 | 2024-05-21 | 2024-02-26 |  |  | 349 | 0 | 50 | 0 |  | X
05 | 05-1P5384 | 1P5384 | 05-SB-166-63.9/64.9 |  |  | Cal Electro, Inc. | 3710 Electro Way | Redding Ca 96002 |  | 8059221611 | 2053 Preisker Ln Def | Santa Maria Ca 93454 | Reed, Albert/Gaston,Phil | 0 | 10877.44 | 0 | 0 | 2026-01-16 | Irrigation, Planting, Vehicle Charging Sys | Santa Barbara County In New Cuyama From 0.2 Mile West Of Branch Canyon Bridge To Newsome Street | 100 | 100 | 958539.8 | 941110 | 961529.36 | 48206 | 2026-01-16 | 2023-04-04 | 2023-01-31 | 2026-01-23 |  | 560 | 0 | 560 | 0 |  | X
05 | 05-1T4204 | 1T4204 | 05-SB-192-6.9/20.7 | 20.20.201130 |  | Granite Construction Company | Po Box 742478 | Los Angeles, Ca 90074-2478 | 8059649951 | 8057210091 | 35 S. La Pantera Lane, Suite E | Goleta, Ca 93117 | Chhay, Alis | 0 | 115598.93 | 0 | 0 | 2026-02-20 | Rep. Slipout,Drainage, Erosion Ctrl & Tc | Rep. Slipout, Place Rockery,Restore Pvmnt Rep. Drainage Sys,Erosion Control & Tc Rep. Slipout,Drainage, Erosion Ctrl & Tc Dirs Efa | 90 | 17 | 270648.55 | 8000 | 1585000 | 60215 | 2026-02-27 | 2026-01-09 | 2025-11-16 |  |  | 45 | 0 | 50 | 0
05 | 05-1C3604 | 1C3604 | 05-SB-217-.9/1.4 | HA21 | ACNH-P217- (003)E | M.C.M. Construction, Inc. | 6413 32Nd Street | North Highlands Ca 95660 |  | 9517502468 | 35 S. La Patera Lane | Goleta, Ca 93117 | Yogarajah, Manny/ Chhay, Alis | 133837.5 | 168414.26 | 0 | 0 | 2026-02-20 | Replace Bridge. | Santa Barbara County Near Goleta From 0.2 Mile East Of Goleta Slough Bridge To 0.4 Mile East Of San Jose Creek Bridge | 61 | 83 | 24773698.45 | 26134014.5 | 29723142.54 | 46964 | 2026-06-09 | 2023-02-21 | 2023-01-31 |  |  | 524 | 0 | 800 | 62 |  | X
05 | 05-1H8114 | 1H8114 | 05-SBT-25-18.8/19.2 |  |  | John Semsen Landscaping Co., Inc. | 21161 Lyons Bald Mountain Roa | Sonora Ca 95370 |  | 8314555466 | 8115 Prunedale North Road | Prunedale, Ca 93907 | Garcia, Santiago | 2520 | 0 | 0 | 0 | 2026-02-20 | Planting Mitigation. | San Benito County About 32 Miles South Of Hollister From 0.8 Mile North Of San Benito Lateral To 2.0 Miles South Of Route146 | 19 | 79 | 300365 | 381675 | 381675 | 58796 | 2028-09-28 | 2025-06-10 | 2025-04-29 |  |  | 156 | 0 | 810 | 0 |  | X
05 | 05-1P5314 | 1P5314 | 05-SBT-25-49.5/51.1 |  |  | Bortolussi & Watkin, Inc. | 77 Larksput Street | San Rafael Ca Ca 94901 |  | 8314555466 | 8115 Prunedale North Road | Prunedale, Ca 93907 | Garcia, Santiago | 3100.5 | 0 | 0 | 0 | 2026-02-20 | Planting And Irrigation And Install Transp | San Benito County In And Near Hollister From 0.1 Mile South Of Sunset Drive To Santa Ana Road | 16 | 97 | 1062274.84 | 929993 | 1074138.08 | 48205 | 2026-02-28 | 2023-04-04 | 2023-03-02 |  |  | 79 | 0 | 500 | 0 |  | X
05 | 05-1J4814 | 1J4814 | 05-SBT-25-53.7/54.3 |  |  | John Semsen Landscaping Co., Inc. | 21161 Lyons Bald Mountain Roa | Sonora Ca 95370 |  | 8314555466 | 8115 Prunedale North Road | Prunedale, Ca 93907 | Garcia, Santiago | 2520 | 0 | 0 | 0 | 2026-02-20 | Highway Planting And Plant Establishment W | San Benito County Near Hollister On Route 25 From 0.4 Mile East To 0.3 Mile West Of Route 156 And On Route 156 From 0.4 Mile South | 62 | 87 | 245560 | 281040 | 281040 | 54064 | 2027-04-16 | 2023-11-30 | 2023-10-31 |  |  | 486 | 0 | 780 | 0 |  | X
05 | 05-1S9004 | 1S9004 | 05-SBT-101-1.5/1.7 | 20.20.201130 |  | Midstate Barrier, Inc. | Po Box 30550 | Stockton, Ca 95213-0550 |  | 8056108215 | 8115 Prunedale North Road | Prunedale, Ca 93907 | Brar, Baljinder | 0 | 9672.56 | 0 | 0 | 2026-01-23 | Mod.Guardrail,Turnpocket,Striping And Tc | Modify Guardrail And Turn Pocket Modify Striping And Install Signs Provide Traffic Control Dirs Efa 05A | 100 | 100 | 510277.38 | 4270 | 839000 | 59075 | 2026-01-23 | 2025-06-24 | 2025-05-23 | 2026-01-30 |  | 13 | 0 | 45 | 0 |  | X
05 | 05-1S5104 | 1S5104 | 05-SBT-101-4.2/4.5 | 20.20.201130 |  | Top Tier Grading, Llc | 8305 Prunedale N. Rd. #155 | Salinas, Ca 93907 | 8317899273 | 8056108215 | 8115 Prunedale N. Rd. | Prunedale, Ca 93907 | Brar, Baljinder | 0 | 29970.37 | 0 | 0 | 2026-02-19 | Culvert Repair, Line Culvert & Erosion Ctl | Exc Embankment To Replace Portion Of Culvtline Culvert, Fill Voids & Gaps With Groutrep.Sinkhole, Bio Monitoring & Erosion Ctldirs | 100 | 75 | 4079204.95 | 17500 | 5459000 | 58095 | 2025-09-04 | 2025-05-06 | 2025-04-02 |  |  | 124 | 0 | 75 | 0
05 | 05-1S0104 | 1S0104 | 05-SBT-101-12.0/2.1 |  |  | Community Tree Service | 416 Salina Road | Pajaro, Ca 95076 |  | 8056108215 | 8115 Prunedale North Road | Prunedale, Ca 93907 | Brar, Baljinder | 0 | 206.14 | 0 | 0 | 2026-02-20 | Tree Removal,Site Restoration & Monitoring | Eucalyptus Tree Removal, Traffic Control &Arborist & Environmental Monitoring Site Restoration & Erosion Contol Dirs Efa 05A2797 | 100 | 86 | 2235093.34 | 13000 | 2585000 | 56608 | 2026-11-29 | 2024-10-25 | 2024-09-03 |  |  | 175 | 0 | 50 | 0 |  | X
05 | 05-344904 | 344904 | 05-SBT-156-3.0/8.2 | HE13 | ACNH-P156- (024)EHIPL-6205- (029) | A. Teichert & Son, Inc. Dba Teichert Construction | 400 Sunrise Ave. Suite 300 | Roseville Ca 95661 | 9167576400 | 8054416931 | 8115 Prunedale North Road | Prunedale, Ca 93907 | Nash Munes | 9256.83 | 78928.15 | 0 | 0 | 2026-02-20 | Widen 2 To 4 Lanes San Jaun | On State Route 156 In San Benito County, In And Near San Juan Bautista From The Alameda St To 0.2 Mi East Of Fourth Street/Busine | 100 | 99 | 85722221.46 | 70580000 | 87875622.81 | 42745 | 2024-08-14 | 2022-06-29 | 2022-06-10 |  |  | 490 | 0 | 480 | 0 |  | X
05 | 05-2A0004 | 2A0004 | 05-SCR-1-1.0/.2 | 20.20.201130 |  | Serafix Engineering Contractor | 7 Crow Canyon Ct., Ste. 250 | San Ramon, Ca 94583 |  | 8057486095 | 1500 Green Hillds Road, Ste. 201 | Scotts Valley, Ca 95066 | Nguyen, Ian | 0 | 0 | 0 | 0 |  | Repair Scour & Fill Voids,Place Rsp & Tc | Repair Scour And Fill Voids.Place Rsp, Tc Repair Scour & Fill Voids,Place Rsp & Tc Rep. Scour & Fill Voids,Place Rsp,Trfc Ctldirs | 0 | 0 | 0 | 5000 | 985000 | 60378 | 2026-04-16 | 2026-01-16 | 2026-01-16 |  |  | 0 | 0 | 50 | 0
05 | 05-1S9204 | 1S9204 | 05-SCR-1-3.5/3.9 |  |  | Granite Construction Company | 580 West Beach Street | Watsonville, Ca 95076 |  | 8314274706 | 140 Dubois Street, Suite "E" | Santa Cruz, Ca 95060 | Nguyen, Ian | 0 | 13346.41 | 0 | 0 | 2026-02-20 | Repair Culvert,Restore Site & Trfc Control | Replace Culvert, Restore Site & Trfc Ctrl Repair Sinkhole,Slurry Backfill, Hma And Traffic Control Dirs Efa 05A | 100 | 63 | 3260156.46 | 26000 | 5185000 | 59495 | 2026-04-24 | 2025-08-21 | 2025-06-01 |  |  | 220 | 0 | 180 | 0
05 | 05-2A0304 | 2A0304 | 05-SCR-1-6.0/.7 | 20.20.201130 |  | Serafix Engineering Contractor | 7 Crow Canyon Ct, Ste. 250 | San Ramon, Ca 94583 |  | 8057486095 | 1500 Green Hill Road, Ste. 201 | Scotts Valley, Ca 95066 | Nguyen, Ian | 0 | 0 | 0 | 0 |  | Gen.Access,Place Rsp & Traffic Control | Generate Access,Place Rsp And Traffic Ctrlplace Rsp And Provide Traffic Control Gen.Access,Place Rsp & Traffic Control Dirs Efa 05 | 0 | 0 | 0 | 19065 | 3798000 | 60432 | 2026-04-29 | 2026-02-15 | 2026-02-17 |  |  | 0 | 0 | 50 | 0
05 | 05-0C7334 | 0C7334 | 05-SCR-1-10.5/13.4 | HE13 |  | Granite Construction Company | 580 W Beach Street | Watsonville Ca 95076 | 8317287561 | 8055504651 | 140 Dubois St, Ste E | Santa Cruz, Ca 95060 | Nnam, Martin | 1440037.29 | 121814.92 | 9486.59 | 0 | 2026-02-20 | Construct Overcrossing And Auxiliary Lane. | Santa Cruz County In And Near City Of Capitola From State Park Drive Overcrossing To 0.2 Mile North Of Bay Avenue Undercrossing | 23 | 64 | 48282842.17 | 72398200.21 | 75716258.55 | 51348 | 2026-06-25 | 2023-07-24 | 2023-06-29 |  |  | 305 | 0 | 1335 | 0 |  | X
05 | 05-0C7324 | 0C7324 | 05-SCR-1-13.6/14.9 |  | ACNH-P001- (675)E | Granite Construction Company | 580 West Beach Street | Watsonville Ca 95076 | 8317636100 | 8055504651 | 140 Dubois Street Suite E | Santa Cruz Ca 95060 | Nnam, Martin | 12650 | 102628.14 | 0 | 0 | 2026-02-20 | Construct Auxiliary Lanes And | 41St Avenue To Soquel Avenue Auxiliary Lanes (Near The City Of Santa Cruz And Capitola, From 41St Avenue To Soquel Avenue. | 38 | 95 | 33926239.4 | 28994748.81 | 35032410.69 | 45444 | 2026-03-30 | 2022-11-16 | 2022-10-14 |  |  | 450 | 0 | 1170 | 0 |  | X
05 | 05-1Q9404 | 1Q9404 | 05-SCR-1-33.0/33 | 20.20.201130 |  | Serafix Engineering Contractors, Inc | 7 Crow Canyon Ct Ste 250 | San Ramon, Ca 94583 |  | 8314274706 | 140 Dubois St Ste E | Santa Cruz, Ca 95060 | Nguyen, Ian | 0 | 18641.46 | 0 | 0 | 2024-04-20 | Repair Emankment | In Santa Cruz Cnty Rte 001 @ Pm 33.0 Repair Embankment Provide Temp Erosion Control. Provide Traffic Control Dirs Efa 05A2632 | 50 | 19 | 776071.86 | 2250 | 4135000 | 52185 | 2024-09-20 | 2023-06-02 | 2023-03-10 |  |  | 50 | 0 | 100 | 0 |  | X
05 | 05-1Q9904 | 1Q9904 | 05-SCR-1-360.0/37.5 | 20.20.201130 |  | Serafix Engineering Contractors Inc | 7 Crow Canyon Ct, Ste 250 | San Ramon, Ca 94583 |  | 8314274706 | 140 Dubois Street, Suite E | Santa Cruz, Ca 95060 | Nguyen, Ian | 0 | 44085.22 | 0 | 0 | 2026-01-20 | Clearing/Hauling Slide Debris. Traffic Ctl | Clear And Hauling Slide Debris.Traffic Ctlclear Debris Catchment. Repair Rocknet Sysclear/Haul Slide Debris. Traffic Control Dirs | 33 | 99 | 450174.69 | 2305 | 492100 | 60104 | 2026-06-24 | 2025-09-30 | 2025-09-15 |  |  | 25 | 0 | 75 | 0 |  | X
05 | 05-1Q0804 | 1Q0804 | 05-SCR-1-/0 | 20.20.201130 |  | Granite Construction Company | 580 West Beach Street | Watsonville, Ca 95076 | 8317636100 | 8314274706 | 140 Dubois St Ste E | Santa Cruz, Ca 95060 | Nguyen, Ian | 0 | 62820.39 | 0 | 0 | 2026-02-20 | Clearing/Hauling Slide & Bridge Debris | Santa Cruz Cnty On Rts 1 & 9 @ Var P.M. Clearing & Hauling Slide & Bridge Debris. Repair Washout. Temp Traffic Control Dirs Efa 05 | 100 | 100 | 17951236.32 | 6500 | 18000000 | 47424 | 2026-08-20 | 2023-03-17 | 2022-12-31 |  |  | 350 | 0 | 200 | 0 |  | X
05 | 05-1M4004 | 1M4004 | 05-SCR-9-6.3/7.2 |  | HSST-S009- (032)E | Granite Rock Company | 5225 Hellyer Avenue, Suite 22 | San Jose Ca 95138 | [5 empty] | 0 | 0 | 0 | 0 |  | Construct Sidewalks, Curb Ramps, Driveways | Santa Cruz County From 0.1 Mile North Of Kirby Street To 0.1 Mile North Of Fall Creek Drive | 0 | 0 | 0 | 4927295.05 | 4927295.05 | 60218 |  | 2025-11-26 | 2025-10-23 |  |  | 0 | 0 | 405 | 0
05 | 05-1G9504 | 1G9504 | 05-SCR-9-9.0/25.5 |  | PTST-S009- (029)E | Gordon N. Ball, Inc. | 1777 Oakland Blvd. Suite 300 | Walnut Creek Ca 94596 | 9258385675 | 8057486095 | 1500 Green Hills Rd, Ste 201 | Scotts Valley, Ca 95066 | Nguyen, Ian | 149223.25 | 0 | 0 | 250000 | 2026-02-20 | Drainage System Upgrades And Slope Stabili | Santa Cruz County Near Ben Lomond At Various Locations From Scenic Way To 4.7 Miles North Of The Northern Junction Of Routes 9/236 | 13 | 16 | 1649843.5 | 10244158 | 10279158 | 59235 | 2027-09-01 | 2025-07-03 | 2025-06-13 |  |  | 67 | 0 | 520 | 0 |  | X
05 | 05-1S3604 | 1S3604 | 05-SCR-9-12.1/12.1 | 20.20.201130 |  | Granite Constructions Company | 580 W. Beach Street | Watsonville, Ca95076 |  | 8314274884 | 140 Dubois Street, Suite "E" | Santa Cruz, Ca 95060 | Nguyen, Ian | 0 | 110849.35 | 0 | 0 | 2026-02-20 | Replace Retaining Wall, Culvert & Tc | Prospect Ave Retaining Wall In Sc On Rte 9Replace Retaining Wall & Culvert. Tc Replace Retaining Wall, Culvert & Trfc Ctldirs Efa | 60 | 99 | 4671293.45 | 23500 | 4685000 | 57068 | 2026-04-20 | 2025-01-16 | 2024-12-02 |  |  | 150 | 0 | 250 | 0 |  | X
05 | 05-1H4704 | 1H4704 | 05-SCR-9-13.6/0 |  | BFST-S009- (030)E | Gordon N. Ball, Inc. | 1777 Oakland Blvd. Suite 300 | Walnut Creek Ca 94596 |  | 8057486095 | 1500 Green Hills Rd, Ste 201 | Scotts Valley, Ca 95066 | Nguyen, Ian | 35748 | 0 | 0 | 0 | 2026-02-20 | Replace Bridges And Install Mgs. | Santa Cruz County Near Boulder Creek At San Lorenzo River Bridge And At Kings Creek Bridge | 1 | 0 | 35748 | 14208691 | 14208691 | 60217 | 2028-09-01 | 2025-09-16 | 2025-09-05 |  |  | 10 | 0 | 745 | 0 |  | X
05 | 05-1T3904 | 1T3904 | 05-SCR-17-8.4/8.4 | 20.20.201130 |  | Granite Construction Company | 580 West Beach Street | Watsonville, Ca 95076 | 8317636100 | 8314274706 | 140 Dubois Street, Suite "E" | Santa Cruz, Ca 95060 | Nguyen, Ian | 0 | 76288.04 | 0 | 0 | 2026-02-20 | Grind/Rep Damaged Pavement & Rep. Wall | Grind And Replace Damaged Pavement Repair Cidh Retaining Wall Reconstruct Guardrail And Traffic Control Dirs Efa 05A | 60 | 22 | 256381.88 | 5860 | 1157000 | 60137 | 2026-12-24 | 2025-10-30 | 2025-10-14 |  |  | 30 | 0 | 50 | 0 |  | X
05 | 05-1P5304 | 1P5304 | 05-SCR-129-1.1/L1.5 |  |  | Bortolussi & Watkin, Inc. | 77 Larksput Street | San Rafael Ca Ca 94901 |  | 8055343065 | 8115 Prunedale North Road | Prunedale, Ca 93907 | Bailey, Jessica | 0 | 10012.87 | 0 | 0 | 2026-01-09 | Planting, Irrigation Work And Transportati | Santa Cruz County In Watsonville On Route 129 From Locust Street To Main Street And On Route 152 From Holm Road To Freedom Bouleva | 100 | 100 | 1177753 | 1129763 | 1204283.53 | 48744 | 2026-01-09 | 2023-04-24 | 2023-03-10 | 2026-01-30 |  | 250 | 0 | 360 | 0 |  | X
05 | 05-1J8304 | 1J8304 | 05-SCR-129-/.6 |  | ST -X087- (033)E | A. Teichert & Son, Inc. Dba Teichert Construction | 3500 American River Dr | Sacramento Ca 95864 |  | 8312626572 | 1529 Hwy 68 | Monterey, Ca 93940 | Tyler Lavering | 0 | 0 | 0 | 0 |  | Pavement, Lighting, Curb Ramps, Sidewalk, | Santa Cruz County In And Near Watsonville On Route 129 From Route 1/129 Separation To Salsipuedes Creek Bridge And On Route 152 Fr | 0 | 0 | 0 | 8130810 | 8130810 | 60381 |  | 2026-01-29 | 2026-01-06 |  |  | 0 | 0 | 595 | 0
05 | 05-1S3804 | 1S3804 | 05-SCR-152-1.3/T1.5 | 20.20.201130 |  | Granite Rock Company | 5225 Hellyer Ave. Suite 220 | San Jose, Ca 95138 | 4085741400 | 8314274706 | 140 Dubois Street, Suite "E" | Santa Cruz, Ca 95060 | Nguyen, Ian | 0 | 329974.59 | 0 | 0 | 2026-02-05 | Paving,Sidewalk,Curb/Gutter&Const Drainage | Excavation And Place Lightweight Fill Paving, Sidewalk, Curb/Gutter Construct And Modify Drainage Dirs Efa 05A | 13 | 12 | 596946.62 | 25850 | 5155000 | 60136 | 2026-05-24 | 2025-10-27 | 2025-09-12 |  |  | 20 | 0 | 150 | 0 |  | X
05 | 05-1S2804 | 1S2804 | 05-SLO-0-/0 | 20.20.201130 |  | Central Coast Fence Inc. | 540 S. 4Th Street | Grover Beach, Ca 93433 |  | 8059221611 | 2053 Preisker Lane, Suite E | Santa Maria, Ca 93454 | Reed, Albert | 0 | 15190.34 | 0 | 0 | 2025-12-20 | Replace Fence&Install Securty Cameras | Slo&Sb Co Maint. Stations Security Improvereplace Fence&Install Security Cameras Security Improvements At Maint. Stations Dirs Efa | 100 | 93 | 1926697.23 | 10450 | 2075000 | 56767 | 2025-12-20 | 2024-09-06 | 2024-06-03 |  |  | 224 | 0 | 100 | 0 |  | X
05 | 05-492864 | 492864 | 05-SLO-1-6.4/67.2 |  |  | Hanford Applied Restoration & Conservation | 755 Baywood Drive, Suite 380 | Petaluma Ca 94954 |  | 8054712102 | 775 Arlington St. | Cambria,Ca 93428 | Silva,Rick | 18400 | 0 | 0 | 0 | 2026-02-20 | Landscape Planting, Wetland Mitigation And | San Luis Obispo County About 9 Miles Northof San Siemon From 0.3 Mile North Of Piedras Blancas Lighthouse Road To 0.3 Mile North O | 13 | 75 | 3752121.44 | 4982635 | 5003699.74 | 55847 | 2027-11-04 | 2024-05-22 | 2024-04-22 |  |  | 156 | 0 | 1215 | 0 |  | X
05 | 05-1P5354 | 1P5354 | 05-SLO-1-12.1/12.2 |  |  | R. Burke Corporation | 865 Capitolio Way | San Luis Obispo Ca 93401 |  | 5599774632 | 2053 Preisker Ln Def | Santa Maria Ca 93454 | Reed, Al/Gaston, Phil | 2400 | 0 | 0 | 0 | 2025-12-20 | Irrigation, Planting And Concrete Work. | San Luis Obispo County At Oceano At Beach Street And Seventeenth Street | 68 | 97 | 1453501.89 | 1402634.6 | 1478722.01 | 53844 | 2026-08-20 | 2023-11-17 | 2023-09-06 |  |  | 388 | 0 | 570 | 0 |  | X
05 | 05-1Q0604 | 1Q0604 | 05-SLO-1-12.6/12.7 | 20.20.201130 |  | Souza Engineering Contracting,Inc. Dba Souza Construction | Po Box 3810 | San Luis Obispo, Ca 93403 | 8055493406 | 8059221611 | 2053 Preisker Lane Ste E | Santa Maria, Ca 93454 | Reed, Albert/Gaston, Phil | 0 | 4154.17 | 0 | 0 | 2025-06-11 | Repair Seismic Damper Block On Bridge | Slo Cnty Route 001 Bridge 49-12. Repair Seismic Damper Block & Void. Restore Asphtconcrete Shoulder. Install Ue Determent Dirs Efa | 22 | 28 | 195113.8 | 3500 | 685000 | 46884 | 2025-06-11 | 2023-02-15 | 2022-12-13 |  |  | 11 | 0 | 50 | 0 |  | X
05 | 05-1N3804 | 1N3804 | 05-SLO-1-17.3/0 |  |  | Lamassu Utility Services, Inc. | 3193 Enterprise Court | Loomis Ca 95650 |  |  | 3230 Riverside Avenue #130 | Paso Robles, Ca 93446 | Andrew Borelli | 127849.62 | 0 | 0 | 0 | 2025-12-23 | Cured-In-Place Pipeliner And Culvert Repla | San Luis Obispo County In San Luis Obispo At Foothill Boulevard | 100 | 100 | 869286.67 | 932292.55 | 932292.55 | 59257 | 2025-12-23 | 2025-06-26 | 2025-06-10 | 2026-02-05 |  | 53 | 0 | 45 | 0 |  | X
05 | 05-1R1004 | 1R1004 | 05-SLO-1-32.6/0 |  | BFST-S001- (673)E | Souza Engineering Contracting,Inc. Dba Souza Construction | 4027 Santa Fe Road | San Luis Obispo Ca 93401 |  | 8054712102 | 775 Arlington St. | Cambria, Ca 93428 | Silva, Rick | 43565 | 0 | 0 | 0 | 2026-02-20 | Bridge Replacement, Hma, And Rsp Protectio | San Luis Obispo County Near Morro Bay At Toro Creek Bridge | 1 | 1 | 43565 | 6785921.4 | 6785921.4 | 60278 | 2027-10-15 | 2025-12-30 | 2025-12-10 |  |  | 2 | 0 | 250 | 0 |  | X
05 | 05-3307C4 | 3307C4 | 05-SLO-41-44.5/45.3 | HE13 |  | Guy F Atkinson Construction Llc | 611 Anton Blvd, Suite 1100 | Costa Mesa, Ca 92626 | 7142871356 | 8053935820 | 102 S Whitley Gardens Dr | Paso Robles, Ca 93446 | R,Eric/Harrington,Brian | 2633122.61 | 403606.53 | 0 | 0 | 2026-02-20 | Convert To A 4 Lane Expressway | San Luis Obispo County At And Near Cholameon Route 41 From Route 41/46 Separation To0.8 Mile North Of Route 41/46 Separation And O | 53 | 91 | 139329996.09 | 148301868.03 | 152497668.44 | 47545 | 2025-04-16 | 2023-03-03 | 2023-03-03 |  |  | 449 | 0 | 850 | 0 |  | X
05 | 05-1T4104 | 1T4104 | 05-SLO-41-495.0/49.5 | 20.20.201130 |  | Drill Tech Drilling And Shoring, Inc. | 2200 Wymore Way | Antioch, Ca 94509 |  | 8053935820 | 102 S. Whitley Gardens Drive | Paso Robles, Ca 93446 | Riddiough, Eric | 0 | 0 | 0 | 0 |  | Remove Rockslide, Stabilize Slope & Tc | Relieve Maintenance Tc, Remove Rockslide, Stabilize Slope And Re-Establish Travelwayremove Rockslide,Stabilize Slope & Tc Dirs Efa | 0 | 0 | 0 | 9500 | 9500 | 60282 | 2026-03-12 | 2025-12-29 | 2025-12-29 |  |  | 0 | 0 | 50 | 0
05 | 05-1S4804 | 1S4804 | 05-SLO-46-4.3/5.1 | 20.20.201130 |  | Souza Engineering Cont. Inc. Dba Souza Construction | P.O. Box 3810 | San Luis Obispo, Ca 93403 |  | 8057482342 | 3230 Riverside Avenue, Suite 30 | Paso Robles, Ca 93446 | Iman, Hassan | 0 | 10402.13 | 0 | 0 | 2026-02-20 | Repair Slipouts,Damaged Pavement & Tc | Repair Slipouts, Repair Pavement, Tc Slipouts, Damaged Pavement & Traffic Ctrl Repair Slipouts,Damaged Pavement & Tc Dirs Efa/05A | 88 | 72 | 8856197.5 | 8500 | 12285000 | 57095 | 2026-03-01 | 2025-02-05 | 2025-01-15 |  |  | 44 | 0 | 50 | 0
05 | 05-1Q03U4 | 1Q03U4 | 05-SLO-46-60.3/60.8 |  | STPL-6205- (033)000 | Papich Construction Company, Inc. | 398 Sunrise Terrace | Arroyo Grande Ca 93420 |  | 8053313023 | 102 S Whitley Gardens Dr | Paso Robles, Ca 93446 | R, Eric/Borrelli,Andrew | 253880.26 | 0 | 0 | 0 | 2026-02-20 | Vertical Curve And Extend Existing Truck C | San Luis Obispo And Kern Counties Near Cholame From 2.0 Miles East Of Antelope Road To 0.4 Mile East Of The Kern County Line. | 86 | 89 | 4101049.62 | 4417997 | 4575395.04 | 57097 | 2026-03-20 | 2025-02-05 | 2024-12-13 |  |  | 155 | 0 | 180 | 0 |  | X
05 | 05-1J9704 | 1J9704 | 05-SLO-58-1.8/6.9 |  |  | Calportland Construction | 1625 East Donovan Rd | Santa Maria Ca 93456 | 8053453400 | 8055503058 | 3230 Riverside Aveste 130 | Paso Robles, Ca 93446 | Michael Schmidt | 473216.58 | 0 | 0 | 0 | 2026-02-20 | Pavement Preservation, Drainage Improvemen | San Luis Obispo County In And Near Santa Margarita From I Street To State Route 229. | 100 | 87 | 6178000.26 | 6697059.3 | 6855938.67 | 57375 | 2026-12-09 | 2025-03-21 | 2025-03-05 |  |  | 138 | 0 | 135 | 0 |  | X
05 | 05-1J9714 | 1J9714 | 05-SLO-58-2.0/7.1 |  |  | Marina Landscape, Inc. | 3707 W Garden Grove Blvd | Orange Ca 92868 |  | 8055503058 | 3230 Riverside Dr | Paso Robles Ca | Michael Schmidt | 0 | 0 | 0 | 0 |  | Planting And Irrigation. | San Luis Obispo County In And Near Santa Margarita At Various Locations From 0.2 Mile East Of I Street To 0.3 Mile East Of Route 2 | 0 | 0 | 0 | 427962 | 427962 | 60216 |  | 2025-11-18 | 2025-10-22 |  |  | 0 | 0 | 800 | 0
05 | 05-1J8604 | 1J8604 | 05-SLO-101-7.8/16.5 |  | ACNH-Q101- (432)E | Papich Construction Company, Inc. | 398 Sunrise Terrace | Arroyo Grande Ca 93420 |  | 8059221611 | 2053 Preisker Lane, Suite E | Santa Maria Ca 93454 | Albert Reed Sr/Phil Gaston Are | 1094489.94 | 0 | 0 | 0 | 2026-02-20 | Cold Plane Ac Pavement, Rhma-G, Drainage S | San Luis Obispo County In And Near Arroyo Grande And Pismo Beach From Los Berros Road Undercrossing To Pismo Creek Bridge | 26 | 36 | 11997654.84 | 31975207 | 32577455.24 | 57337 | 2027-11-02 | 2025-03-12 | 2025-02-12 |  |  | 152 | 0 | 585 | 0 |  | X
05 | 05-1G6804 | 1G6804 | 05-SLO-101-16.0/22.5 |  | CML -HIP - (620)023 | Granite Construction Company | 5335 Debbie Rd | Santa Barbara Ca 93111 | [5 empty] | 0 | 0 | 0 | 0 |  | Widen Bridges, Retaining Wall, Hma, Rhma, | San Luis Obispo County In And Near Pismo Beach From Pismo Beach Overhead To 0.2 Mile North Of North Avila Road Overcrossing | 0 | 0 | 0 | 55325312 | 55325312 | 60361 |  | 2026-01-21 | 2025-12-30 |  |  | 0 | 0 | 755 | 0
05 | 05-1N3404 | 1N3404 | 05-SLO-101-28.6/29.6 |  | HSNH-Q101- (433)E | Souza Engineering Contracting,Inc. Dba Souza Construction | 4027 Santa Fe Road | San Luis Obispo Ca 93401 |  | 8054712102 | 775 Arlington St. | Cambria, Ca 93428 | Silva, Rick | 396126.64 | 18146.2 | 0 | 0 | 2026-02-20 | Minor Concrete, Vegetation Control, Guardr | San Luis Obispo County At Various Locations From Broad Street Exit 202B To California Boulevard Exit 203C. | 44 | 93 | 2067729.61 | 2082242 | 2172749.46 | 58295 | 2026-02-27 | 2025-05-20 | 2025-04-29 |  |  | 95 | 0 | 215 | 0 |  | X
05 | 05-1J7804 | 1J7804 | 05-SLO-101-61.7/62.1 |  | HSNH-Q101- (429)E | Calportland Construction | 1625 East Donovan Rd | Santa Maria Ca 93456 |  | 8055503058 | 3230 Riverside Ave., #130 | Paso Robles, Ca 93446 | Schmidt, Michael | 567370.5 | 0 | 0 | 0 | 2026-02-20 | Construct Undercrossing, Structural Concre | San Luis Obispo County Near Paso Robles From 0.7 Mile North Of Exline Road To 1.0 Mile South Of Monterey Road | 93 | 73 | 9228299.47 | 12198939.36 | 12658191.11 | 56683 | 2026-02-13 | 2024-11-08 | 2024-10-22 |  |  | 232 | 0 | 250 | 0
05 | 05-1S9304 | 1S9304 | 05-SLO-101-250.0/85 | 20.20.201130 |  | John Madonna Construction Company Inc. | Po Box 5310 | San Luis Obispo, Ca 93403 | 8055437751 | 8056108212 | 2053 Preisker Lane, Ste E | Santa Maria, Ca 93454 | Moreno, Arturo | 0 | 1589731.72 | 0 | 0 | 2026-02-20 | Repair/Clear Fire Damage And Traffic Ctrl | Rep. Burnt Drainage Systems, Rep.Guardrailclear Fire Debris From Inlets/Ditch Temp. Traffic Control Dirs Efa 05A | 52 | 86 | 6519586.14 | 38000 | 7585000 | 60095 | 2026-02-20 | 2025-10-02 | 2025-08-03 |  |  | 52 | 0 | 100 | 0 |  | X
05 | 05-1S3204 | 1S3204 | 05-VAR--/0 |  |  | Truesdell Corporation Of California, Inc. | 1310 W. 23Rd Street | Tempe Az 85282 | [5 empty] | 0 | 0 | 0 | 0 |  | Bridge Deck Polyester Concrete Overlays An | Santa Cruz County At Various Locations | 0 | 0 | 0 | 823823 | 823823 | 60424 |  | 2026-02-17 | 2026-02-02 |  |  | 0 | 0 | 30 | 0
06 | 06-0X2904 | 0X2904 | 06-FRE-33-13.9/16.7 |  | ACST-S033- (095)E | Cal Valley Construction, Inc. | 5125 N Gates Ave Ste 102 | Fresno Ca 93722 |  | 5594175927 | 90 W Ashlan Ave | Clovis Ca 93721 | Dadawalla Din | 0 | 0 | 0 | 0 |  | Hma (Type A), Rdwy Exc, Cl 2 Ab, Curb Ramp | Fresno County In And Near Coalinga From Enterprise Parkway To Los Gatos Creek South Channel Bridge | 0 | 0 | 0 | 9894195.5 | 9894195.5 | 60281 | 2026-12-09 | 2025-12-30 | 2025-12-05 |  |  | 0 | 0 | 200 | 0
06 | 06-1G8204 | 1G8204 | 06-FRE-33-46.8/47.4 |  |  | Archer Civil Construction, Llc | 1353 South J Street | Tulare Ca 93274 | [5 empty] | 59172.5 | 0 | 0 | 0 | 2026-01-28 | Partial Depth Recycling And Hma. | Fresno County In And Near Mendota From 0.4Mile North Of Kamm Avenue To Mountain Viewavenue And From Adams Avenue To Belmont Avenue | 100 | 100 | 3571136.83 | 3782111.17 | 3731088.47 | 58555 | 2026-01-28 | 2025-06-03 | 2025-04-01 | 2026-01-30 |  | 35 | 0 | 35 | 0 |  | X
06 | 06-0X3004 | 0X3004 | 06-FRE-33-69.4/71.5 | HA22 | ACST-S033- (093)E | Bay Cities Paving & Grading, Inc. | 1450 Civic Ct Bldg B #400 | Concord Ca 94520 |  | 5594175927 | 90 W. Ashlan Avenue, Ste 110 | Clovis, Ca 93612 | Din Dadawalla | 0 | 1 | 0 | 0 | 2026-02-20 | Replace Roadway Pavement. | Fresno County In And Near Firebaugh From Morris Kyle Drive To Lyon Avenue | 100 | 95 | 13555993.71 | 13443175.09 | 14055143.14 | 55408 | 2026-02-26 | 2024-03-11 | 2024-02-06 |  |  | 196 | 0 | 150 | 46 |  | X
06 | 06-1E7604 | 1E7604 | 06-FRE-41-21.1/32.2 |  |  | California Turf And Landscaping | 7726 N First St Ste 158 | Fresno Ca 93720 |  | 5599775551 | 90 W Ashlan Ave, Suite 110 | Clovis, Ca 93612 | Chantha Chap | 231500 | 0 | 0 | 0 | 2026-02-20 | Transportation Art, Irrigation, And Planti | Fresno County In Fresno At Various Locations From 0.5 Mile South Of Jensen Avenue Overcrossing To 0.5 Mile North Of Audubon Drive | 93 | 82 | 1840018 | 2183605.3 | 2237058.7 | 56377 | 2026-03-26 | 2024-09-17 | 2024-08-07 |  |  | 307 | 0 | 330 | 0 |  | X
06 | 06-0X7804 | 0X7804 | 06-FRE-41-23.2/31.7 |  | ACNH-P041- (605)E | Ibarra General Engineering Inc | 4325 Tyrolite St | Riverside Ca 92509 | 9093428447 | 5592075363 | 90 West Ashlan Ave, Suite 110 | Clovis, Ca 93612 | Fernando De Alba | 6415.81 | 0 | 0 | 0 | 2026-01-20 | Construct Slope Paving (Stamped Concrete) | Fresno County In Fresno At Various Locations From Ventura Avenue Viaduct To Friant Road Undercrossing | 99 | 89 | 9129102.58 | 9924538.1 | 10275798.1 | 56119 | 2026-02-24 | 2024-07-17 | 2024-06-04 |  |  | 207 | 0 | 210 | 0 |  | X
06 | 06-1E7304 | 1E7304 | 06-FRE-41-25.3/0 |  |  | California Turf And Landscaping | 7726 N First St Ste 158 | Fresno Ca 93720 |  | 5592888603 | 90 West Ashlan Ave, Suite 110 | Clovis, Ca 93612 | Fernando De Alba | 33102 | 0 | 0 | 0 | 2026-02-20 | Prefabricated Building, Wrought Iron Fence | Fresno County In Fresno At Mckinley Avenue | 97 | 84 | 1291069.36 | 1470832.4 | 1529642.4 | 56515 | 2026-03-16 | 2024-09-18 | 2024-08-20 |  |  | 116 | 0 | 120 | 0 |  | X
06 | 06-1G0904 | 1G0904 | 06-FRE-41-28.2/28.2 | 20.20.201130 |  | Koch & Koch Inc | 13084 John Bauer Ave | Grass Valley, Ca 95945 |  | 5592544877 | 90 W. Ashlan Ave, Suite#110 | Clovis, Ca 93612 | Fernando De Alba | 0 | 100163.88 | 0 | 0 | 2026-02-02 | Remove/Replace Pump And Assoc Appurtenance | In Fresno County Along Route 41 Near Pm R28.2 At Pump Plant Between Shaw And Santa Ana Dir'S Emergency F.A. | 83 | 89 | 1694803.36 | 6825 | 1900000 | 52284 | 2026-02-20 | 2023-07-28 | 2023-07-10 |  |  | 25 | 0 | 30 | 0 |  | X
06 | 06-0U4214 | 0U4214 | 06-FRE-99-4.9/7.2 |  |  | Wabo Landscape & Construction,Inc. | 726 Alfred Nobel Drive | Hercules Ca 94547 |  | 5592075363 | 90 W. Ashlan Avenue, Suite 110 | Clovis, Ca 93612 | Fernando De Alba | 3617 | 27198.73 | 0 | 0 | 2026-01-20 | Replace Highway Planting And Install Irrig | Fresno County In And Near Selma And Fowlerfrom 0.4 Mile South Of Second Street Undercrossing To 0.7 Mile North Of Floral Avenue An | 21 | 91 | 1677135.91 | 1730273 | 1830273 | 56603 | 2028-12-19 | 2024-10-31 | 2024-09-19 |  |  | 186 | 0 | 880 | 0 |  | X
06 | 06-1G3504 | 1G3504 | 06-FRE-99-233.0/0 | 20.20 201131 |  | Gruen Engineering, Inc. | 12418 Gruen St | Pacoima Ca 91331 |  | 5592888603 | 90 W Ashlan Ave, Suite 110 | Clovis Ca 93612 | De Alba, Fernando | 0 | 124964.95 | 0 | 0 | 2026-01-20 | Repair D06 Materials Lab | Construction And Installation Of New Ceiling, Fume Hoods, Motors, Ducts, Monitoring System, Vent Stacks, Hvac System, Thermostdir | 38 | 23 | 639724.2 | 13775 | 2740000 | 56828 | 2026-01-20 | 2024-12-08 | 2024-12-08 |  |  | 25 | 0 | 65 | 0 |  | X
06 | 06-0X2204 | 0X2204 | 06-FRE-168-8.1/45.8 |  | PTST-S168- (068)E | Wylatti Resource Management, Inc. | 23601 Cemetery Lane | Covelo Ca 95428 | [5 empty] | 0 | 0 | 0 | 0 |  | Rcp Culverts, Cipp, Structural Concrete (D | Fresno County In And Near Clovis At Various Locations From 0.1 Mile East Of Fowler Avenue Overcrossing To 0.1 Mile East Of Warbler | 0 | 0 | 0 | 8764262.72 | 8764262.72 | 60309 |  | 2026-01-12 | 2025-12-22 |  |  | 0 | 0 | 240 | 0
06 | 06-0Q5204 | 0Q5204 | 06-FRE-168-48.2/0 |  |  | Granite Construction Company | 2716 Granite Court | Fresno Ca 93706 |  | 5592888603 | 90 W. Ashlan Ave, Suite 110 | Clovis, Ca 93612 | Fernando De Alba | 123502 | 264683 | 0 | 2500 | 2025-11-20 | Place Concrete Barrier And Structural Conc | Fresno County Near Shaver Lake At Stevenson Creek | 43 | 86 | 696926.75 | 533646 | 798329 | 60097 | 2025-01-02 | 2025-07-15 | 2025-06-13 |  |  | 26 | 0 | 60 | 0 |  | X
06 | 06-1A0904 | 1A0904 | 06-FRE-168-49.1/49.5 |  | PTST-S168- (067)E | Viking Construction Company, Inc. | 3835 Security Park Drive | Rancho Cordova Ca 95742 |  | 5599398827 | 90 W. Ashlan Ave, Suite#110 | Clovis, Ca 93612 | Mohammed Alqutami | 0 | 0 | 0 | 0 |  | Construct Sidehill Viaduct Structure. | Fresno County Near Shaver Lake From 1.3 Miles East Of Dalton Avenue To 0.2 Mile West Of Huntington Lake Road | 0 | 0 | 0 | 32666120 | 32666120 | 60386 |  | 2026-01-29 | 2025-12-19 |  |  | 0 | 0 | 610 | 0
06 | 06-0Y4104 | 0Y4104 | 06-FRE-180-47.4/47.8 |  | SSTG-P180- (066)E | Cal Valley Construction, Inc. | 5125 N Gates Ave Ste 102 | Fresno Ca 93722 | [5 empty] | 0 | 0 | 0 | 0 |  | Place Hma, Minor Concrete, Jpcp, Roadway E | Fresno County Near Rolinda From 0.2 Mile West To 0.2 Mile East Of Dickenson Avenue | 0 | 0 | 0 | 8039741 | 8039741 | 60401 |  | 2026-02-10 | 2026-01-12 |  |  | 0 | 0 | 185 | 0
06 | 06-342354 | 342354 | 06-FRE-180-54.1/56 |  |  | Marina Landscape, Inc. | 3707 W. Garden Grove Blvd | Orange Ca 92868 | 7149396600 | 5594175927 | 3240 N. Millbrook | Fresno, Ca 93726 | Din Dadawalla | 3480 | 0 | 0 | 0 | 2026-02-20 | Highway Planting | In And Near Fresno From 0.2 Mile West Of Brawley Avenue To Teilman Avenue | 0 | 0 | 4807270.66 | 5328436.25 | 5329948.24 | 43144 | 2024-12-13 | 2022-07-15 | 2022-05-20 |  |  | 200 | 0 | 950 | 0 | X | X
06 | 06-1J3304 | 1J3304 | 06-FRE-180-/0 | 20.20.201130 |  | Al Var Fence Co | 15275 Stony Oaks Ln | Prather Ca 93651 |  | 5599172597 | 90 W Ashlan Ave | Clovis Ca 93612 | Alaa Ghoneim | 0 | 0 | 0 | 0 |  | Remove & Replace Fence & Gates | In Fresno County Hwy 180/41 At Various Locations Dir Order Emergency F.A. | 0 | 0 | 0 | 5000 | 985000 | 60440 | 2026-04-30 | 2025-09-16 | 2025-09-14 |  |  | 0 | 0 | 60 | 0
06 | 06-0X0604 | 0X0604 | 06-FRE-198-.5/19.5 |  | ACST-S198- (077)E | A. Teichert & Son Inc Dba Teichert Construction | 400 Sunrise Blvd. Suite 300 | Roseville Ca 95661 | 9167576400 | 6613034187 | 8530 W Roosevelt Ave | Visalia Ca 93291 | Michael R Garrett | 19077.57 | 0 | 0 | 0 | 2026-01-20 | Remove And Replace Culverts And Cured In P | Fresno County At Various Locations From 1.3 Miles West Of Warthan Creek Overcrossing To 1.7 Miles West Of Firestone Avenue | 27 | 32 | 2771975.56 | 8972350 | 8796490.42 | 55950 | 2026-08-18 | 2024-06-07 | 2024-05-08 |  |  | 52 | 0 | 195 | 0 |  | X
06 | 06-0Y7604 | 0Y7604 | 06-FRE-5506-/0 |  |  | Radman Electric | 25013 Whitman Street #15-S | Hayward Ca 94544 |  | 5599398827 | 90 W Ashlan Ave, Suite 110 | Clovis, Ca 93612 | Mohammed Alqutami | 17070 | 0 | 0 | 0 | 2025-12-20 | Modification Of Electrical System. | Fresno County In Fresno At The West Avenuemaintenance Station 1283 North West Avenueand At The District Office 1352 West Oliveaven | 100 | 100 | 1177649.83 | 996500 | 1177649.83 | 56081 | 2025-12-30 | 2024-06-07 | 2024-05-08 |  |  | 60 | 0 | 60 | 0 |  | X
06 | 06-0X4304 | 0X4304 | 06-FRE-5725-/0 |  |  | Bowe Contractors, Inc. | 609 Bailey Court | Tehachapi Ca 93561 |  | 5599398827 | 90 W. Ashlan Avenue, Suite#110 | Clovis, Ca 93612 | Mohammed Alqutami | 0 | 0 | 0 | 0 |  | Tree Crew And Special Crews Building. | Fresno County In Fresno At West Avenue Maintenance Station At 1283 North West Avenue | 0 | 0 | 0 | 12538938.86 | 12538938.86 | 60255 |  | 2025-12-19 | 2025-11-14 |  |  | 0 | 0 | 335 | 0
06 | 06-0X5704 | 0X5704 | 06-KER-5-.8/0 |  | CIMG-005 - (4 )209 | Tsi Engineering, Inc. | 4600 Roseville Rd Suite 140 | North Highlands Ca 95660 |  | 5599775450 | 3600 N, Sillect Ave |  | Robert Decker | 0 | 0 | 0 | 0 |  | Building Work, Mobilization, Guardrail, Tr | Kern County Near Lebec At The Tejon Safetyroadside Rest Area | 0 | 0 | 0 | 6598786 | 6598786 | 60280 |  | 2025-12-30 | 2025-12-10 |  |  | 0 | 0 | 240 | 0
06 | 06-0W9204 | 0W9204 | 06-KER-5-4.1/10.7 |  | ACIM-005 - (4 )208 | C. A. Rasmussen, Inc. | 28548 Livingston Avenue | Valencia Ca 91355 |  | 5599775450 | 3600 N. Sillect Ave | Bakersfield, Ca 93308 | Robert Decker | 0 | 0 | 0 | 0 |  | Rdwy Exc, Crcp, Jpcp, Hma, Temp Barrier Sy | Kern County Near Grapevine From 0.3 Mile South Of Grapevine Creek Bridge To 0.5 Mile North Of Grapevine Road Undercrossing | 0 | 0 | 0 | 77041402.3 | 77041402.3 | 60307 |  | 2026-01-12 | 2025-12-18 |  |  | 0 | 0 | 430 | 0
06 | 06-0U5004 | 0U5004 | 06-KER-5-10.2/16 |  | ACIM-005 - (4 )207 | Security Paving Company, Inc. | 3075 Townsgate Road, Suite 20 | Westlake Village Ca 91361 |  | 5599775450 | 3600 N. Sillect Avenue | Bakersfield, Ca 93308 | Robert Decker | 260759.75 | 0 | 0 | 0 | 2026-01-20 | Individual Slab Replacement (Rsc) And Hma | Kern County At And Near Wheeler Ridge Fromgrapevine Undercrossing To Route 5/99 Separation | 100 | 95 | 20828775.69 | 19016164 | 20769028.81 | 56324 | 2026-03-27 | 2024-09-10 | 2024-08-29 |  |  | 283 | 0 | 135 | 128 |  | X
06 | 06-1G1804 | 1G1804 | 06-KER-5-/0 |  |  | Truesdell Corporation Of California, Inc. | 1310 W. 23Rd Street | Tempe Az 85282 | 6024371711 | 5599774455 | 3600 N. Sillect Ave | Bakersfield, Ca 93308 | Bob Decker | 83293.9 | 0 | 50156.87 | 0 | 2025-11-20 | Furnish And Place Polyester Concrete Overl | Kern County At Various Locations From Grapevine Creek Bridge To Kern River Floodcanal Bridge | 82 | 87 | 2811616.37 | 3068068 | 3171754.67 | 57536 | 2025-12-22 | 2025-04-04 | 2025-03-19 |  |  | 90 | 0 | 110 | 0 |  | X
06 | 06-0X2404 | 0X2404 | 06-KER-33-21.8/39.8 |  |  | Doja, Inc. | 5050 Mission Blvd | Ontario Ca 91762 |  | 5599775450 | 3600 N. Sillect Avenue | Bakersfield, Ca 93308 | Bob Decker | 101553.7 | 0 | 0 | 0 | 2025-11-20 | Structural Concrete And Rcp Drainage Culve | Kern County At Various Locations From 0.9 Mile South Of Henry Road To 0.2 Mile Northof Cymric Road (North) | 64 | 20 | 985308.48 | 5100000 | 4960671.9 | 57595 | 2026-02-18 | 2025-04-02 | 2025-03-07 |  |  | 103 | 0 | 160 | 0 |  | X
06 | 06-0Y1304 | 0Y1304 | 06-KER-33-40.4/59.3 |  | ACST-S033- (094)E | Granite Construction Company | 3005 James Road | Bakersfield Ca 93308 |  | 5599051299 | 3600 N. Sillect Ave | Bakersfield, Ca 93308 | Jake Garcia | 630385.61 | 70221.27 | -151910.5 | 0 | 2026-02-20 | Cold Plane, Place Hma And Rhma-G, And Repl | Kern County About 8 Miles North Of Mckittrick From Cymric Wash Bridge To 0.8 Mile South Of Route 46 | 93 | 96 | 27589637.84 | 27529328 | 28896621.49 | 56073 | 2026-03-25 | 2024-07-10 | 2024-06-20 |  |  | 305 | 0 | 200 | 128 |  | X
06 | 06-3HT0U4 | 3HT0U4 | 06-KER-43-25.1/25.4 |  | 6206-037 - ( )000 | Griffith Company | 3050 E. Birch St | Brea Ca 92821 |  | 6613335825 | 3600 N.Sillect Ave | Bakersfield, Ca 93308 | Amarjit Dhaliwal | 1851.75 | 0 | 0 | 0 | 2026-02-20 | Roundabout, Widen Lanes, Temporary Shoofly | Kern County In Wasco On Route 46 From E Street To 0.2 Mile East Of Route 43/46 East Junction And On Route 43 From 0.1 Mile South O | 0 | 0 | 1851.75 | 70155735 | 70155735 | 60405 | 2028-11-08 | 2026-02-11 | 2026-01-28 |  |  | 0 | 0 | 500 | 0 |  | X
06 | 06-1A7604 | 1A7604 | 06-KER-46-51.4/57.9 |  | ACNH-P046- (063)E | Granite Construction Company | 3005 James Road | Bakersfield Ca 93308 |  | 6613335825 | 3600 N. Sillect Ave | Bakersfield, Ca 93308 | Amarjit Dhaliwal | 0 | 0 | 0 | 0 |  | Cold Plane Ac Pavement, Rhma Overlay, Conc | Kern County In And Near Wasco From 0.20 Mile East Of Route 43 To 0.30 Mile East Ofroute 46/99 Separation | 0 | 0 | 0 | 6424600 | 6519710 | 60183 |  | 2025-11-10 | 2025-10-20 |  |  | 0 | 0 | 115 | 0
06 | 06-0Q2814 | 0Q2814 | 06-KER-99-23.6/28.4 |  |  | Griffith Company | 1128 Carrier Parkway Ave | Bakersfield Ca 93308 |  | 6613320538 | 3600 N. Sillect Road | Bakersfield, Ca 93308 | Amrit Brar | 12150 | 0 | 0 | 0 | 2026-01-20 | Replacement Planting. | Kern County In Bakersfield From Palm Avenue Overcrossing To Beardsley Canal Bridge | 0 | 0 | 5818355.17 | 5388904 | 6223405.89 | 47604 | 2027-10-31 | 2023-03-15 | 2023-02-16 |  |  | 250 | 0 | 1000 | 0 | X | X
06 | 06-0W79U4 | 0W79U4 | 06-KER-99-56.4/57.6 |  | ACNH-P099- (689)E | Security Paving Company, Inc. | 3075 Townsgate Road, Suite 20 | Westlake Village Ca 91361 |  | 5599051299 | 3600 N.Sillect Avenue | Bakersfield, Ca 93308 | Jake Garcia | 2548078.42 | 36850 | 0 | 0 | 2026-02-20 | Rdwy Exc, Hma, Aggregate Base, Crcp, Sign | Kern And Tulare Counties In And Near Delano From 0.2 Mile South Of Cecil Avenueovercrossing To 0.7 Mile North Of Avenue 100 Overcr | 25 | 21 | 27470409.25 | 130076704.7 | 130436734.51 | 57875 | 2027-07-01 | 2025-04-24 | 2025-04-10 |  |  | 111 | 0 | 450 | 1 |  | X
06 | 06-0V6104 | 0V6104 | 06-KER-119-28.2/31.3 |  | ACST-S119- (022)E | Griffith Company | 3050 E. Birch St | Brea Ca 92821 | [5 empty] | 0 | 0 | 0 | 0 |  | Hma (Type A), Rcp, Class 2 Ab, Roadway Exc | Kern County In And Near Bakersfield From 0.1 Mile West Of Ashe Road To Route 119/99Separation | 0 | 0 | 0 | 30202735 | 30202735 | 60306 |  | 2026-01-12 | 2025-12-24 |  |  | 0 | 0 | 350 | 0
06 | 06-1H0604 | 1H0604 | 06-KER-155-17.8/39.6 |  |  | Lamassu Utility Services, Inc. | 3193 Enterprise Court | Loomis Ca 95650 |  | 6613320538 | 3600 N. Sillect Road | Bakersfield, Ca 93308 | Amrit Brar | 0 | 0 | 0 | 0 |  | Remove And Replace Culverts, And Cured-In- | Kern County At Various Locations From 6.7 Miles East Of Route 65 To 0.4 Mile West Ofwhite River Road | 0 | 0 | 0 | 363553.44 | 363553.44 | 60075 |  | 2025-07-22 | 2025-04-23 | 2026-02-18 |  | 0 | 0 | 25 | 0
06 | 06-0S0504 | 0S0504 | 06-KER-166-17.5/0 |  |  | Granite Construction Company | 580 W Beach Street | Watsonville Ca 95076 |  | 5599774455 | 3600 N. Sillect Avenue | Bakersfield, Ca 93308 | Bob Decker | 508910 | 97025.83 | 48593.77 | 0 | 2026-02-20 | Micropiling, Structural Concrete, And Hot | Kern County Near Mettler At California Aqueduct Bridge | 79 | 92 | 6283014.79 | 6183322 | 6978640.77 | 56518 | 2026-04-29 | 2024-09-10 | 2024-08-23 |  |  | 166 | 0 | 170 | 41 |  | X
06 | 06-0U2904 | 0U2904 | 06-KER-184-1.1/8.3 |  | ACNH-P184- (018)E | Griffith Company | 1128 Carrier Parkway Ave | Bakersfield Ca 93308 |  | 6613320538 | 3600 N. Sillect Road | Bakersfield Ca 93308 | Amrit Brar | 1379933.77 | 0 | 0 | 1600000 | 2026-02-20 | Cold Plane & Overlay With Hma/Rhma, Constr | Kern County Near Bakersfield From Wharton Avenue To Edison Highway | 10 | 10 | 2979933.77 | 30715735 | 30715735 | 60158 | 2026-11-06 | 2025-08-25 | 2025-08-14 |  |  | 22 | 0 | 220 | 0 |  | X
06 | 06-1C0604 | 1C0604 | 06-KER-223-1.8/10.4 |  | ACST-S223- (013)E | Granite Construction Company | 3005 James Road | Bakersfield Ca 93308 |  | 5595131469 | 3600 N.Sillect Ave | Bakersfield, Ca, 93308 | Samuel Garcia | 0 | 0 | 0 | 0 |  | Full Depth Recycle And V-Ditches. | Kern County Near Bakersfield From Route 223/5 Separation To 0.1 Mile West Of Route223/99 Separation | 0 | 0 | 0 | 9328350 | 9328350 | 60320 |  | 2026-01-14 | 2025-11-26 |  |  | 0 | 0 | 110 | 0
06 | 06-1H0504 | 1H0504 | 06-KER-223-12.5/30.1 |  |  | Jabre Contracting, Inc. | 1813 Manzanita Lane | Manhattan Beach Ca 90266 |  | 6613335825 | 3600 N.Sillect Avenue | Bakersfield, Ca 93308 | Amarjit Dhaliwal | 206982.5 | 0 | 0 | 0 | 2026-02-20 | Replace Culverts And Cured-In-Place Pipeli | Kern County At Various Locations From 0.5 Mile West Of Adobe Road To 1.9 Miles Southof Route 58 | 85 | 73 | 242657.5 | 329600 | 329600 | 59535 | 2026-02-24 | 2025-07-29 | 2025-04-29 |  |  | 17 | 0 | 20 | 0 |  | X
06 | 06-1G7704 | 1G7704 | 06-KIN-5-16.6/26.7 |  |  | Granite Construction Company | 2716 Granite Court | Fresno Ca 93706 |  | 5599775551 | 90 W Ashlan Ave, Suite 110 | Clovis, Ca 93612 | Chantha Chap | 72793.8 | 0 | 0 | 0 | 2026-01-20 | Remove And Replace Asphalt Concrete Overla | Kings County In And Near Avenal From Route5/41 Separation To Fresno County Line | 71 | 77 | 3454653.33 | 4396049 | 4341602.61 | 57896 | 2026-02-26 | 2025-04-29 | 2025-04-01 |  |  | 32 | 0 | 45 | 0 |  | X
06 | 06-0W8204 | 0W8204 | 06-KIN-41-28.4/40.1 |  | ACNH- P04- (606)E | Granite Construction Company | 2716 Granite Court | Fresno Ca 93706 |  | 5599776478 | 90 W. Ashlan Avenue, Ste 110 | Clovis, Ca 93612 | Oscar Sherrill | 0 | 2332.04 | 0 | 0 | 2026-01-20 | Cold Plane With Hot Mix Asphalt (Type A) A | Kings County At And Near Stratford From Nevada Avenue To Route 41/198 Separation | 100 | 100 | 15067656.21 | 15123990.6 | 15725752.43 | 55949 | 2026-01-20 | 2024-06-05 | 2024-05-22 | 2026-01-29 |  | 210 | 0 | 150 | 0 |  | X
06 | 06-0Y1704 | 0Y1704 | 06-KIN-41-/15.5 |  | ACNH-P041- (607)E | Granite Construction Company | Po Box 742478 | Los Angeles Ca 90074 |  | 5599776478 | 90 W. Ashlan Ave Suite 110 | Clovis, Ca 93612 | Sherrill, Oscar | 17139.55 | 0 | 0 | 0 | 2026-02-20 | Cold Plane Ac Pvmt, Overlay Hma And Rhma. | Kings County Near Kettleman City From The Kern County Line To 0.8 Mile South Of Route 5 | 59 | 82 | 13509241.86 | 16147997 | 16033472 | 57596 | 2026-05-18 | 2025-04-02 | 2025-03-03 |  |  | 91 | 0 | 155 | 0 |  | X
06 | 06-0X7004 | 0X7004 | 06-TUL-63-5.8/L8 | HA22 | ACNH-P063- (023)E | Cal Valley Construction, Inc. | 5125 N Gates Ave Ste 102 | Fresno Ca 93722 |  | 5596518317 | 8530 W Roosevelt Ave | Visalia Ca 93291 | Javier Huerta | 2533424.26 | 635318.89 | -1609952.11 | 0 | 2025-10-15 | Cold Plane Pavement, Place Rhma-G, Modify | Tulare County In Visalia From 0.2 Mile South Of Caldwell Avenue To Route 63/198 Separation | 100 | 100 | 7770503.83 | 7779370 | 8119062.89 | 54764 | 2025-10-15 | 2023-12-01 | 2023-09-21 |  |  | 191 | 0 | 140 | 10 |  | X
06 | 06-1G7404 | 1G7404 | 06-TUL-63-12.1/21.6 |  |  | Archer Civil Construction, Llc | 1353 South J Street | Tulare Ca 93274 | 5593721838 |  | 8530 W Roosevelt Ave | Visalia Ca 93291 | Mike Garrett | 413122.55 | 0 | 0 | 0 | 2025-11-20 | Rumble Strips And Striping. | Tulare County Near Visalia On Route 63 From 0.3 Mile North Of Avenue 326 To 0.5 Mile North Of Avenue 396 And In Porterville On Ro | 95 | 89 | 1156978.38 | 1303933.36 | 1326084.79 | 59096 | 2025-12-01 | 2025-06-26 | 2025-05-28 |  |  | 38 | 0 | 40 | 0 |  | X
06 | 06-1E6904 | 1E6904 | 06-TUL-99-9.8/40.7 |  |  | Marina Landscape Inc. | 3707 W Garden Grove Blvd | Orange Ca 92868 | 7149396600 | 6613034187 | 8530 W Roosevelt Ave | Visalia Ca 93291 | Michael R Garrett | 2725.5 | 0 | 0 | 0 | 2026-01-20 | Landscape Planting, Irrigation, And Plant | Tulare County In And Near Teviston At Various Locations From 0.1 Mile North Of Avenue 76 To 0.1 Mile South Of Betty Drive | 86 | 95 | 539442.87 | 445462.5 | 569319.71 | 47266 | 2026-07-01 | 2023-03-03 | 2023-02-06 |  |  | 688 | 0 | 800 | 0 |  | X
06 | 06-1G8404 | 1G8404 | 06-TUL-99-13.5/19.5 |  |  | Archer Civil Construction, Llc | 1353 South J Street | Tulare Ca 93274 | 5593721838 | 5592867590 | 8530 W Roosevelt Ave | Visalia Ca 93291 | Javier Huerta | 44592.63 | 0 | 0 | 0 | 2026-02-20 | Cold Plane Ac Pavement And Hma. | Tulare County At Tipton From 0.1 Mile North Of Road 124 On Ramp To Avenue 152 Overcrossing | 93 | 88 | 2955041.62 | 3380065.17 | 3374438.67 | 57735 | 2026-03-02 | 2025-04-15 | 2025-03-14 |  |  | 51 | 0 | 55 | 0 |  | X
06 | 06-0U8804 | 0U8804 | 06-TUL-99-26.3/27.6 |  | ILDL-6206- (033)000 | Security Paving Company, Inc. | 13170 Telfair Ave | Sylmar Ca 91342 |  | 5592867590 | 8530 W Roosevelt Ave | Visalia Ca 93291 | Javier Huerta | 1218562.3 | 29859.6 | 290843.27 | 0 | 2026-02-20 | Construct Interchange. | Tulare County In Tulare From 0.9 Mile North Of Avenue 200 Overcrossing To Paige Road Overcrossing | 93 | 75 | 35688907.18 | 45538438 | 46926259.69 | 46924 | 2026-05-07 | 2023-02-17 | 2023-01-23 |  |  | 484 | 0 | 465 | 58
06 | 06-0W9104 | 0W9104 | 06-TUL-99-27.6/30.6 |  | ACNH-P099- (687)E | Granite Construction Company | 580 W Beach Street | Watsonville Ca 95076 |  | 5592508186 | 8530 W Roosevelt Ave | Visalia Ca 93291 | Amir Zamanian | 47352.5 | 289616.1 | 0 | 0 | 2026-02-20 | Hma, Rhma-G, Jointed Plain Conc Pvmt (Rsc) | Tulare County In And Near Tulare From Paige Avenue Overcrossing To Prosperity Avenue Overcrossing. | 64 | 73 | 16157810.06 | 21213662 | 21353884.15 | 56606 | 2026-06-10 | 2024-10-01 | 2024-09-16 |  |  | 141 | 0 | 220 | 0 |  | X
06 | 06-360304 | 360304 | 06-TUL-99-30.2/35.2 |  |  | Empire Landscaping Inc. | 26945 County Road 97D | Davis Ca 95616 |  | 5592508186 | 8530 W. Roosevelt Ave | Visalia Ca 93291 | Amir Zamanian | 21230 | 0 | 0 | 0 | 2026-02-20 | Install Irrigation System And Planting. | Tulare County In And Near Tulare From 0.4 Mile South Of Prosperity Avenue Overcrossing To 1.2 Miles South Of Avenue 280 Overcross | 20 | 86 | 2092068.38 | 2397750 | 2418448.46 | 56029 | 2029-01-03 | 2024-05-17 | 2024-05-03 |  |  | 174 | 0 | 880 | 0 |  | X
06 | 06-487404 | 487404 | 06-TUL-99-35.8/37.1 |  | 6206-039 - ( )000 | Granite Construction Company | 2716 Granite Court | Fresno Ca 93706 |  | 5592508186 | 8530 W. Roosevelt Ave | Visalia Ca 93291 | Amir Zamanian | 150640 | 0 | 0 | 0 | 2026-02-20 | Replace Bridge Structures And Construct Ro | Tulare County In And Near Visalia From 0.6Mile South Of Avenue 280 Overcrossing To 0.7 Mile North Of Avenue 280 Overcrossing | 0 | 1 | 544879.73 | 66170188 | 67135147.11 | 57297 | 2027-10-06 | 2025-02-12 | 2025-01-14 |  |  | 2 | 0 | 420 | 0 |  | X
06 | 06-1A3104 | 1A3104 | 06-TUL-190-11.2/11.6 |  | SSTG-P190- (025)E | Archer Civil Construction, Llc | 1353 South J Street | Tulare Ca 93274 | [5 empty] | 0 | 0 | 0 | 0 |  | Construct Roundabout. | Tulare County Near Porterville From 0.2 Mile West Of Road 208 To 0.2 Mile East Of Road 208 | 0 | 0 | 0 | 2676997.06 | 2676997.06 | 60167 |  | 2025-11-10 | 2025-10-20 |  |  | 0 | 0 | 95 | 0
06 | 06-0Q4324 | 0Q4324 | 06-TUL-190-13.1/16.6 |  |  | Cal Valley Construction, Inc. | 5125 N Gates Ave Ste 102 | Fresno Ca 93722 | 5592740300 | 6613034187 | 8530 W Roosevelt Ave | Visalia Ca 93291 | Michael Garrett | 616937.52 | 0 | 0 | 170000 | 2026-02-20 | Hma, Minor Concrete And Jpcp. | Tulare County In And Near Porterville At Various Locations From 0.2 Mile West Of Westwood Street To 0.1 Mile East Of South Main St | 31 | 28 | 2701198.95 | 9474093.75 | 9481093.75 | 59519 | 2026-07-09 | 2025-07-23 | 2025-06-27 |  |  | 43 | 0 | 140 | 0 |  | X
06 | 06-1H6904 | 1H6904 | 06-TUL-190-42.7/42.8 | 20.20.201130 |  | Ccfg Construction | 17750 Wards Ferry Rd | Sonora Ca 95370 | 2097434911 | 5599056468 | 8530 Roosevelt Ave | Visalia Ca 93291 | Mandujano, Cesar | 0 | 1910347.93 | 0 | 0 | 2026-02-20 | Cleaning The Slope And Performing A Half | Constructing Cip/Rc Box Girder (Full Width), Roadway Construction/Excavation, Drainage Systems, Permanent Erosion Control Dir Efa | 18 | 33 | 5079398.93 | 152178 | 15430328 | 60116 | 2026-10-05 | 2025-07-30 | 2025-07-14 |  |  | 66 | 0 | 359 | 0 |  | X
06 | 06-1H6704 | 1H6704 | 06-TUL-190-366.0/0 | 20.20.201130 |  | Chapco Construction Llc | 6000 Mortono Street | Sacramento Ca 95828 |  | 5599056468 | 8530 W Roosevelt Ave | Visalia Ca 93291 | Mandujano, Cesar | 0 | 0 | 0 | 0 |  | Replace Existing Bridge Rail | Replacement Of Existing Bridge Rail On Eb Direction Of Sr 190, Demolition And Reconstruction Of The Overhang, Removal Of The Dirs | 0 | 0 | 0 | 26500 | 2648250 | 60115 | 2026-02-04 | 2025-07-10 | 2025-06-26 |  |  | 0 | 0 | 60 | 0
06 | 06-0X2604 | 0X2604 | 06-TUL-198-1.6/43.9 |  | ACNH-P198- (082)E | Teichert Construction | 3500 American River Dr | Sacramento Ca 95864 | 9167576400 | 6613034187 | 8530 W. Roosevelt Ave | Visalia Ca 93291 | Micahel R Garrett | 107830 | 0 | 0 | 0 | 2025-11-20 | Remove, Install, And Repair Drainage Facil | Tulare County In And Near Visalia At Various Locations From 1.6 Miles East Of Kings County Line To 0.2 Mile West Of Sequoia Nation | 96 | 90 | 10869257.57 | 12142114 | 12729899.47 | 56336 | 2025-12-04 | 2024-05-13 | 2024-03-13 |  |  | 269 | 0 | 280 | 0 |  | X
06 | 06-0W90U4 | 0W90U4 | 06-TUL-198-11.6/11.9 |  | ACNH-P216- (007)E | Teichert Construction | 3500 American River Dr | Sacramento Ca 95864 | 9164843011 | 6613034187 | 8530 W Roosevelt Ave | Visalia Ca 93291 | Mike Garrett | 378705.55 | 0 | 0 | 0 | 2026-02-20 | Hma And Modifying Signal And Lighting Syst | Tulare County In And Near Visalia On Route216 From 0.2 Mile South Of Lovers Lane Undercrossing To 0.2 Mile East Of Mcauliffstreet | 29 | 48 | 11804024.75 | 24704119 | 24828092.1 | 56605 | 2026-09-30 | 2024-09-13 | 2024-08-29 |  |  | 211 | 0 | 720 | 0 |  | X
06 | 06-0X0704 | 0X0704 | 06-TUL-245-/33 |  | PTST-S245- (002)E | Genuine Engineering, Inc. | 13306 Indian Bow Circle | Corona Ca 92883 | [5 empty] | 0 | 0 | 0 | 0 |  | Remove And Replace Csp And Rcp Culverts. | Tulare County At Various Locations From Route 198/245 Separation To Fresno County Line | 0 | 0 | 0 | 4979623 | 4979623 | 60308 |  | 2026-01-13 | 2025-12-11 |  |  | 0 | 0 | 220 | 0
06 | 06-1H9604 | 1H9604 | 06-VAR--/0 |  |  | Griffith Company | 1128 Carrier Parkway Ave | Bakersfield Ca 93308 |  | 6613335825 | 3600 N.Sillect Avenue | Bakersfield, Ca 93308 | Amarjit Dhaliwal | 0 | 43451.79 | 58631.59 | 0 | 2026-02-20 | Cold Plane Ac Pavement And Placing Rhma Ty | Kern County At Various Locations | 11 | 14 | 727552.79 | 5337735 | 5215383.06 | 60168 | 2026-04-20 | 2025-11-10 | 2025-10-22 |  |  | 5 | 0 | 45 | 0 |  | X
06 | 06-0W9704 | 0W9704 | 06-VAR--/0 |  | ACNH-P099- (684)E | Bortolussi & Watkin, Inc. | 77 Larkspur Street | San Rafael Ca 94901 |  | 5592888603 | 90 W. Ashlan Ave, Suite#110 | Clovis, Ca 93612 | Fernando De Alba | 59714.64 | 0 | 0 | 0 | 2026-02-20 | Planting, Maintaining Existing Planting Ar | Fresno County At Various Locations | 27 | 73 | 9956893.86 | 13106999 | 13702999 | 56118 | 2026-10-19 | 2024-05-15 | 2024-02-23 |  |  | 348 | 0 | 1285 | 0 |  | X
06 | 06-1F9004 | 1F9004 | 06-VAR--/0 |  |  | Archer Civil Construction, Llc | 1353 South J Street | Tulare Ca 93274 | 5593721838 | 5592867590 | 8530 W Roosevelt Ave | Visalia Ca 93291 | Javier Huerta | 175435.46 | 0 | 0 | 0 | 2025-11-20 | Hma (Type A) And Rhma (Gap Graded). | Tulare County At Various Locations | 100 | 8 | 280566.06 | 3460217.26 | 3460217.26 | 59097 | 2025-12-01 | 2025-06-26 | 2025-05-08 |  |  | 48 | 0 | 45 | 0
07 | 07-2XM404 | 2XM404 | 07-LA-0-/0 | 20.10 201352 |  | Izurieta Fence Company Inc | 3000 Gilroy St | Los Angeles, Ca 90039 |  | 3103455704 | 13230 Firestone Blvd Suite A | Santa Fe Springs, Ca 90670 | Frempong, Sam | 0 | 86611.4 | 0 | 0 | 2026-02-20 | Replace/Upgrade Perimeter Fence/Systems | La County/Cities-Hawthorne,Commerce& Long Beach@Felton,Willow,Commerece&Butler Mt Strepair/Replace Fences&Perimeter Laser Systdir' | 100 | 97 | 3491097 | 21454 | 3580800 | 57011 | 2026-03-30 | 2024-08-22 | 2024-06-17 |  |  | 218 | 0 | 180 | 0 |  | X
07 | 07-346104 | 346104 | 07-LA-1-7.0/7.4 |  | BFNH-P001- (708)000 | Powell Constructors, Inc. | 8555 Banana Avenue | Fontana Ca 92335 | 9093568880 | 3102618467 | 18000 Studebaker Rd Ste 360 | Cerritos Ca 90703 | Ton, Thang | 376513 | 7827.37 | 0 | 0 | 2026-02-20 | Retrofit Bridge, Replace Bridge Railings, | Los Angeles County In Long Beach From Golden Avenue To Harbor Avenue | 13 | 34 | 2985637.78 | 8758604 | 8838604 | 59537 | 2028-09-22 | 2025-07-29 | 2025-07-15 |  |  | 98 | 0 | 750 | 0 |  | X
07 | 07-4V2104 | 4V2104 | 07-LA-1-10.4/10.4 | HB4N |  | Servitek Electric, Inc. | 13330 Bloomfield Ave #102-114 | Norwalk, Ca 90650 | 6262271650 | 5629167962 | 18000 Studebaker Rd. Suite 360 | Cerritos, Ca 90703 | Ton, Thang | 63254.25 | 43210.02 | 0 | 0 | 2026-02-10 | Modifying Signal And Lighting. | In Los Angeles County At Broad Avenue | 100 | 100 | 695667.02 | 652457 | 702457 | 52364 | 2026-02-10 | 2023-08-11 | 2023-03-01 | 2026-02-10 |  | 140 | 0 | 140 | 0 |  | X
07 | 07-325804 | 325804 | 07-LA-1-18.0/33.3 |  | ACNH-P001- (695)000 | R.J. Noble Company | 15505 East Lincoln Avenue | Orange Ca 92856 |  | 2133581518 | 970 W.19Th Suite 270 | Torrance, Ca 90502 | Ngo,Huy | 0 | 0 | 0 | 0 |  | Place Rhma And Replace Asphalt Concrete Su | Los Angeles County At Various Locations Onroute 1 From Paseo De Las Delicias To Dewey Street | 0 | 0 | 0 | 52283349 | 52283349 | 60219 | 2029-03-29 | 2025-11-26 | 2025-10-22 |  |  | 0 | 0 | 750 | 0
07 | 07-377604 | 377604 | 07-LA-1-29.4/0 |  | SNHG-P001- (701)E | Ptm General Engineering Services, Inc. | 5942 Acorn St. | Riverside Ca 92504 |  |  |  |  | Martinez, Elizabeth | 0 | 0 | 0 | 0 |  | Modifying Signal And Lighting Systems (Cit | Los Angeles County In And Near Los Angelesat Eight-Third Street And At Fiji Way | 0 | 0 | 0 | 684048 | 684048 | 57079 | 2026-12-31 | 2025-02-04 | 2024-11-22 |  |  | 0 | 0 | 100 | 0
07 | 07-2XR604 | 2XR604 | 07-LA-1-34.9/38 | 20.20.201130 |  | Full Traffic Maintenance Inc | 217 Lewis Court | Corona, Ca 92882 |  | 2133939051 | 12975 W Culver Blvd | Los Angeles Ca 90066 | Martinez, Elizabeth | 0 | 52426.76 | 0 | 0 | 2025-12-20 | Set Up Traffic Control | La-1 Wildfire Damage. Set Up Traffic Cont-Rol. Maintain Traffic Control 24/7. Provi-De Flaggers To Facilitate Const Activitiesdir' | 100 | 57 | 2095519.57 | 14439 | 3677600 | 57458 | 2026-07-05 | 2025-03-20 | 2025-01-28 |  |  | 71 | 0 | 30 | 0
07 | 07-2XS304 | 2XS304 | 07-LA-1-36.0/41 | 20.20.201130 |  | Staples Construction Company | 1501 Eastman Ave | Ventura, Ca 93003 |  | 3107159500 | 12975 W. Culver Blvd | Los Angeles, Ca 90066 | Martinez, Elizabeth | 0 | 27125.45 | 0 | 0 | 2026-02-20 | Repair Fire Damage Assets | In La County, On La-1 South Of California Incline To Topanga Creek-Repair Fire Dmagestabilize Slopes,Erosion Cntrl&Drainge Sysdir' | 83 | 57 | 3774251.84 | 35364 | 6664100 | 58395 | 2026-06-26 | 2025-03-26 | 2025-02-28 |  |  | 165 | 0 | 200 | 0
07 | 07-2XS204 | 2XS204 | 07-LA-1-37.0/46 | 20.XX 201130 |  | C.A. Rasmussen Inc | 28548 Livingston Ave | Valencia, Ca 91355 |  | 3107159500 | 12975 W. Culver Blvd | Los Angeles, Ca 90066 | Martinez, Elizabeth | 0 | 31007.88 | 0 | 0 | 2026-01-20 | Divert Debris Due To Fire Damage | La County,Cities Of La&Malibu From Entradadr To Sweetwater Canyon Drive To Divert Debris/Mudslides & Cleanup Due To Fires Dir'S Em | 890 | 33 | 2622222.76 | 9987 | 7955500 | 57241 | 2026-07-07 | 2025-02-25 | 2025-02-20 |  |  | 182 | 360 | 20 | 0 |  | X
07 | 07-313504 | 313504 | 07-LA-1-37.7/62.9 | HA22 | ACNH-P001- (689)E | Security Paving Company, Inc. | 13170 Telfair Ave | Sylmar Ca 91342 | 818612859 | 5625725852 | 12975 W Culver Blvd | Los Angeles Ca 90066 | Sheik, Hakim | 274571.95 | 47161.68 | 0 | 0 | 2026-02-20 | Remove And Construct Bridge And Culverts. | Los Angeles And Ventura Counties At Various Locations From 0.4 Mile South Of Temescal Canyon Road To 0.1 Mile North Of Tonga Stree | 100 | 69 | 19236284.33 | 26563881.4 | 27875936.4 | 52304 | 2026-12-20 | 2023-09-01 | 2023-07-20 |  |  | 490 | 0 | 430 | 0
07 | 07-2XS104 | 2XS104 | 07-LA-1-39.9/40 | 20.XX 201130 |  | Skanska Usa Civil West California District Inc | 1995 Agua Mansa Road | Riverside Ca 92509 |  | 3107159500 | 12975 W Culver Blvd | Los Angeles, Ca 90066 | Martinez, Elizabeth | 0 | 95480.57 | 0 | 0 | 2026-01-20 | Repair Fire Damage To Getty Wall | In La County, City Of La N/B La 1 N/Of Porto Marina Wy To Getty Villa Dr To Remov& Replace Fire Damage & Ds To Getty Wall Dir'S Em | 19 | 29 | 2194702.81 | 30316 | 7673000 | 59460 | 2026-09-30 | 2025-05-21 | 2025-02-28 |  |  | 56 | 0 | 300 | 0 |  | X
07 | 07-2XQ704 | 2XQ704 | 07-LA-1-40.7/54.1 | 20.XX 201130 |  | Crosstown Electrical &Data Inc | 5454 Diaz Street | Irwindale, Ca 91706 |  | 3107159500 | 12975 W. Culver Blvd | Los Angeles, Ca 90066 | Martinez, Elizabeth | 0 | 186196.01 | 0 | 0 | 2026-02-20 | Maintain Traffic Signals Due To Fire Damag | In La County La-1 From Topanga Cyn Blvd Tokanan Dume Rd To Maintain Functional Trafcsignals @ 20 Loctns Due To Wildfire Damagedir' | 100 | 75 | 5397619.87 | 3118 | 7175000 | 57118 | 2026-09-25 | 2025-02-10 | 2024-12-10 |  |  | 144 | 0 | 30 | 0
07 | 07-2XS404 | 2XS404 | 07-LA-1-41.0/45.6 | 20.20.201130 |  | Rv Concrete Inc | 605 E Commercial St | Anaheim, Ca 92801 |  | 3107159500 | 12975 W. Culver Blvd | Los Angeles, Ca 90066 | Martinez, Elizabeth | 0 | 24376.08 | 0 | 0 | 2026-02-20 | Repair Fire Damage | La County,Cities Of La & Malibu Pch South Of Tuna Canyon Rd To North Of Carbon Beachrepair Fire Damage State Assets,Slopes& Dsdir' | 51 | 90 | 4610900.22 | 102900 | 5130000 | 58155 | 2027-07-07 | 2025-04-10 | 2025-02-28 |  |  | 142 | 0 | 280 | 0 |  | X
07 | 07-2XT304 | 2XT304 | 07-LA-1-42.0/44 | 20.XX 201130 |  | Granite Construction Company | 16700 Valley View Ave #300 | La Mirada, Ca 90638 |  | 3107159500 | 12975 W Culver Blvd | Los Angeles, Ca 90066 | Martinez, Elizabeth | 0 | 232318.55 | 0 | 0 | 2026-02-20 | Place Shoring & Retaining Walls | In La County, City Of Malibu N Of Pena Rd To S Of Las Flores Cyn Rd To Place Temporary Shoring & Construct Retaining Walls Dir'S E | 12 | 10 | 725352.12 | 15953 | 7075000 | 59475 | 2026-08-16 | 2025-06-10 | 2025-04-28 |  |  | 38 | 0 | 330 | 0 |  | X
07 | 07-2XR204 | 2XR204 | 07-LA-1-42.2/42.4 | 20.20.201130 |  | Myers & Sons Construction Llc | 45 Morrison Ave | Sacramento, Ca 95838 |  | 3107159500 | 12975 W. Culver Blvd | Los Angeles, Ca 90066 | Martinez, Elizabeth | 0 | 231795.04 | 0 | 0 | 2026-02-20 | Replace Fire Damaged Retaining Wall | La County, Pch East Of Big Rock Drive To Place Temp Railing(Type K)K-Rail, Slopeprotection Covering, Remove Fire Debris Dir'S Emer | 88 | 62 | 8745686.21 | 84056 | 13994300 | 57383 | 2027-04-08 | 2025-03-20 | 2025-01-24 |  |  | 159 | 0 | 180 | 0
07 | 07-4X9704 | 4X9704 | 07-LA-1-42.4/0 |  | PTNH-P001- (694) E | Beador Construction Company, Inc. | 2900 Bristol Street D204 | Costa Mesa Ca 92626 | 9516747352 | 8184829191 | 12975 W Culver Blvd | Los Angeles, Ca 90066 | Sheik, Hakim | 424085 | 51358.33 | 0 | 0 | 2026-02-20 | Construct Drilled Hole And Drilled Hole (R | Los Angeles County In Malibu At 0.1 Mile South Of Big Rock Drive | 42 | 39 | 2423394.34 | 6117700 | 6261700 | 57139 | 2026-08-19 | 2025-02-13 | 2025-01-16 |  |  | 105 | 0 | 250 | 0 |  | X
07 | 07-2XR904 | 2XR904 | 07-LA-1-43.5/45.5 | 20.20.201130 |  | Maneri Traffic Control Inc | 4949 2Nd St | Fallbrook, Ca 92028 |  | 3107159500 | 12975 W. Culver Blvd | Los Angeles, Ca 90066 | Martinez, Elizabeth | 0 | 187304.2 | 0 | 0 | 2026-02-20 | Provide Traffic Control Frm Palisade Fire | La County, From N/Of Las Flores Cyn Rd To Carbon Beach Terrace To Provide Traffic Control On Pch Due To Palisades Fire Dir'S Emerg | 100 | 52 | 3947563.09 | 13126 | 7527600 | 57355 | 2026-03-25 | 2025-03-18 | 2025-01-28 |  |  | 90 | 0 | 30 | 0
07 | 07-2XR104 | 2XR104 | 07-LA-1-43.7/43.7 | 20.XX 201130 |  | Pcn3 Inc | 10591 Humbolt St Unit A | Los Alamitos, Ca 90720 |  | 3107159500 | 12975 W. Culver Blvd | Los Angeles, Ca 90066 | Martinez, Elizabeth | 0 | 121169.85 | 0 | 0 | 2025-10-20 | Repair Fire Damage To Maintenance Station | La County In City Of Malibu On La-1 At Thelas Flores Maintenance Station-Repair Firedamage To Building Property & Fuel Island Dir' | 15 | 1 | 141665.16 | 83785 | 12031000 | 59295 | 2026-04-23 | 2025-05-21 | 2025-04-24 |  |  | 35 | 0 | 240 | 0 |  | X
07 | 07-2XG904 | 2XG904 | 07-LA-1-44.1/58.5 | 20.XX 201130 |  | Ptm General Engineering Servcs | 5942 Acorn Street | Riverside, Ca 92504 |  | 3102133136 | 12975 W Culver Blvd | Los Angeles, Ca 90066 | Shin, Frank | 0 | 34171.16 | 0 | 0 | 2025-12-20 | Repair & Clean Debris From Storm Damage | La County On La-1 Pch In City Of Malibu Remove Landslide & Stockpild Debris,Repaireroded Slope Areas,Clean Ds Due To Storms Dir'S | 99 | 88 | 1786767 | 24858 | 2030000 | 52564 | 2026-05-31 | 2023-06-27 | 2023-05-10 |  |  | 89 | 0 | 90 | 0 |  | X
07 | 07-2XR504 | 2XR504 | 07-LA-1-46.3/49.4 | 20.XX 201130 |  | Magellan Construction Inc | 1650 Zanker Rd Ste 130 | San Jose, Ca 95112 |  | 3102133136 | 12975 W. Culver Blvd | Los Angeles, Ca 90066 | Shin, Frank | 0 | 71046.41 | 0 | 0 | 2026-02-20 | Repair/Clean Fire Damage To Ds & Slopes | In City Of Malibu South Of Sweetwater Cyn Dr To N/Of Puerco Cyn Rd To Clean/Repair Fire Damage Drainage Systems & Side Slopesdir'S | 75 | 26 | 557677.83 | 13719 | 2109000 | 59756 | 2026-10-30 | 2025-05-21 | 2025-02-14 |  |  | 113 | 0 | 150 | 0
07 | 07-291404 | 291404 | 07-LA-1-56.5/56.9 | HA21 | ACST-P001- (674)E | Stacy And Witbeck, Inc. | 2800 Harbor Bay Parkway | Alameda Ca 94502 | 5107481870 | 2132688221 | 12975 W Culver Blvd | Los Angeles, Ca 90066 | Shin,Frank | 0 | 5573.21 | 0 | 0 | 2026-02-20 | Bridge Replacement | In Los Angeles County In Malibu From Guernsey Ave To Trancas Canyon Road | 52 | 96 | 16789784.61 | 10781073.25 | 17133355.32 | 41480 | 2026-02-28 | 2021-03-09 | 2021-02-18 | 2026-02-27 |  | 793 | 0 | 1515 | 0 |  | X
07 | 07-2XG804 | 2XG804 | 07-LA-1-352.0/44.1 | 20.XX 201130 |  | Drill Tech Drilling & Shoring Dba Apex Rockfall Mitigation | 2200 Wymore Way | Antioch, Ca 94509 |  | 3102133136 | 12975 W. Culver Blvd | Los Angeles, Ca 90066 | Shin, Frank | 0 | 340752.58 | 0 | 0 | 2026-02-20 | Repair/Replace Slope Protection System | In La County On Pch La-1 In Cities Of Malibu,Pacific Palisades&Santa Monica To Remove Debris&Repair Drapery Protect Systmdir'S Eme | 100 | 96 | 3463821.65 | 15486 | 3591000 | 51124 | 2026-05-30 | 2023-06-06 | 2023-04-26 |  |  | 129 | 0 | 90 | 0 |  | X
07 | 07-2XR704 | 2XR704 | 07-LA-1-380.0/40 | 20.XX 201130 |  | Fryman Management Inc | 18 Goodyear Ste 105 | Irvine, Ca 92618 |  | 3107159500 | 12975 W. Culver Blvd | Los Angeles, Ca 90066 | Martinez, Elizabeth | 0 | 13021.9 | 0 | 0 | 2026-02-20 | Provide Traffic Control | La County Pch N/Of Temescal Cny Rd To S/Oftopanga Cny Blvd To Provide Traffic Cntrolfor Repopulation Efforts From Palisade Firdir' | 100 | 87 | 3190642.65 | 19252 | 3677600 | 57300 | 2026-07-05 | 2025-03-11 | 2025-03-03 |  |  | 109 | 0 | 30 | 0 |  | X
07 | 07-2XP704 | 2XP704 | 07-LA-1-388.0/40.4 | 20.XX 201130 |  | Interstate Civil Construction | Po Box 2819 | Wrightwood, Ca 92397 |  | 2133939051 | 12975 W Culver Blvd | Los Angeles, Ca 90066 | Martinez, Elizabeth | 0 | 10238.89 | 0 | 0 | 2026-02-20 | Pavement Delineation Realignment La-1 | In La County,City Of La Pch La-1@ Tramontoslide Area To Realign Pavement Delineation& Pave Shoulder As Necessary Dir'S Emergency | 24 | 72 | 1529268.51 | 13761 | 2116000 | 56037 | 2027-05-25 | 2024-07-02 | 2024-05-25 |  |  | 29 | 0 | 120 | 0 |  | X
07 | 07-2XR804 | 2XR804 | 07-LA-1-400.0/43.5 | 20.20.201130 |  | Dc Traffic Control | 13905 Artesia Blvd | Cerritos, Ca 90703 |  | 3107159500 | 12975 W. Culver Blvd | Los Angeles, Ca 90066 | Martinez, Elizabeth | 0 | 300315.11 | 0 | 0 | 2026-02-20 | Provide Traffic Control | La County On Pch From North Of Topanga Cynla-27 To South Las Flores Cny Rd To Providtraffic Control Due To Palisades Fire Dir'S Em | 100 | 51 | 4260429.8 | 28918 | 8297600 | 57336 | 2026-03-24 | 2025-03-17 | 2025-01-28 |  |  | 111 | 0 | 30 | 0
07 | 07-321604 | 321604 | 07-LA-1-/18 | HA22 | ACNH-P001- (692)E | R.J. Noble Company | 15505 East Lincoln Avenue | Orange Ca 92856 |  | 5628605963 | 18000 Studebaker Rd Suite 360 | Cerritos, Ca 90703 | Ton, Thang | 980365.43 | 35004.73 | 0 | 0 | 2026-02-20 | Cold Plane Ac And Overlay Ac Pavement And | Los Angeles County From Studebaker Road Topaseo De Las Delicias | 81 | 95 | 49896156.36 | 48208586.5 | 50002950.07 | 54985 | 2026-07-02 | 2024-01-23 | 2023-12-20 |  |  | 427 | 0 | 525 | 0 |  | X
07 | 07-333604 | 333604 | 07-LA-2-2.3/14.2 |  | ACST-P002- (043)E | Sully-Miller Contracting Company | 135 S. State College Blvd #40 | Brea Ca 92821 |  | 2139526068 | 601 S Glenoaks Blvd #310 | Burbank, Ca 91502 | Salman Ridwan | 1756549.89 | 91618.17 | 0 | 1225000 | 2026-02-20 | Cold Plane Ac, Place Hma, Replace Curb Ram | Los Angeles County In Los Angeles At Various Locations From Centinela Avenue Toglendale Boulevard Undercrossing | 28 | 20 | 9897771.45 | 49868999.3 | 49846247.03 | 56906 | 2028-11-21 | 2024-12-17 | 2024-11-26 |  |  | 212 | 0 | 750 | 0 |  | X
07 | 07-348504 | 348504 | 07-LA-2-15.0/26.5 |  | ACNH-P002- (044)E | Yakar | 689 East San Bernardino Rd | Covina Ca 91723 | 9095991612 | 8184829304 | 2090 Fern Lane | Glendale, Ca 91208 | Tran, Danglong | 24583 | 0 | 0 | 0 | 2026-02-20 | Construct Ada Curb Ramps And Modify Signal | Los Angeles County At Various Locations From Riverside Drive To Gould Mesa | 15 | 3 | 126872.5 | 4794008 | 4794008 | 59459 | 2027-03-01 | 2025-07-22 | 2025-06-06 |  |  | 46 | 0 | 300 | 0 |  | X
07 | 07-351304 | 351304 | 07-LA-2-15.1/15.3 |  | ACNH-X037- (235)E | Powell Constructors Inc | 8555 Banana Avenue | Fontana Ca 92335 |  | 2139526068 | 601 S Glenoaks Blvd Suite# 310 | Burbank, Ca 91502 | Salman Ridwan | 167985 | 55082.74 | 0 | 0 | 2026-02-20 | Seismic Retrofit And Guardrail Upgrade. | Los Angeles County At Route 2/5 Separation | 100 | 38 | 3082633.08 | 6879634 | 8561969.06 | 55224 | 2027-03-19 | 2024-02-16 | 2024-01-16 |  |  | 397 | 0 | 525 | 0
07 | 07-2XK404 | 2XK404 | 07-LA-2-15.8/15.8 | 20.XX 201130 |  | Stacy And Witbeck Inc | 2800 Harbor Bay Parkway | Alameda, Ca 94502 |  | 2139526068 | 601 S Glenoaks Blvd | Burbank, Ca 91502 | Salman, Ridwan | 0 | 34034.61 | 0 | 0 | 2026-02-20 | Repair Bridge Damage Due To Fire | La County, City Of La On La-2 @Taylor Yardoverheard Br#53-1039 To Repair/Replace Fire Damaged Braces,Girders&Construct Fencdir'S E | 100 | 74 | 3568347.87 | 11428 | 4842100 | 55642 | 2026-04-05 | 2024-02-23 | 2023-10-13 |  |  | 294 | 0 | 70 | 0
07 | 07-0W2104 | 0W2104 | 07-LA-2-18.7/0 |  |  | Splice Construction Co, Inc. 28441 Rancho De Linda Laguna Niguil Ca 92677 | 28441 Rancho De Linda | Laguna Niguel Ca 92677 |  | 8182665626 | 2090 Fern Lane | Glendale Ca 91208 | Amorsolo, Mark | 40230 | 0 | 0 | 0 | 2025-12-20 | Place Class 3 Aggregate Base And Hot Mix A | Los Angeles County In Los Angeles At Los Angeles Regional Transportation Managementcenter At 2901 At West Broadway | 100 | 100 | 530264.1 | 468650 | 468650 | 59316 | 2026-05-02 | 2025-07-08 | 2025-06-23 |  |  | 60 | 0 | 50 | 0 |  | X
07 | 07-2XA604 | 2XA604 | 07-LA-2-65.2/66.4 | 20.XX 201130 |  | Sgv Enterprises Inc | 615 Las Tunas Dr Ste J | Arcadia, Ca 91007 |  | 8182547383 | 2090 Fern Lane | Glendale, Ca 91208 | Shalviri, Ali | 0 | 151100.19 | 0 | 0 | 2025-08-27 | Repair Slopes Due To Storm Damage | In Unincorporated Area Of La County In Theangeles National Forest On La-2 To Repair & Reconstruct Damaged Side Slopes,Berms Dir'S | 100 | 100 | 7831599.18 | 10950 | 8585000 | 51424 | 2025-08-27 | 2023-02-10 | 2022-12-16 |  |  | 304 | 0 | 60 | 244 |  | X
07 | 07-357304 | 357304 | 07-LA-5-6.6/13.1 | HA22 | ACIM-0052- (037)E | Peterson-Chase General Engineering Construction, Inc. | 16351 Construction Circle Wes | Irvine Ca 92606 |  | 2133306640 | 4281 Katella Ave #221 | Los Alamitos, Ca 90720 | Oregel, Martin | 320632.4 | 9378.73 | 0 | 0 | 2026-02-20 | Replace Concrete Slabs And Median Barrier, | Los Angeles County In Santa Fe Springs, Downey And City Of Commerce From 0.2 Mile South Of Route 5/605 Separation To 0.1 Mile Nort | 100 | 90 | 23112789.2 | 23988111.6 | 24486715.09 | 49584 | 2026-03-09 | 2023-05-22 | 2023-04-27 |  |  | 320 | 0 | 320 | 0 |  | X
07 | 07-2XQ404 | 2XQ404 | 07-LA-5-6.8/0 | 20.XX 201131 |  | Quality Fence Co Inc | 14929 Garfield Avenue | Paramount, Ca 90723 |  | 2133100860 | 970 W. 190Th Street Suite 270 | Torrance, Ca 90502 | Shahriari, Shahnam | 0 | 263167.17 | 0 | 0 | 2026-02-20 | Install Security System@Var Communictn Hub | In La County In Various Cities,La-5 Norwlkcomm Hub,La-105 Lax Hub&La-605 San Gabrielconstruct Gate/Door&Replace W/Security Sysdir' | 43 | 12 | 263167.17 | 12219 | 2211000 | 58935 | 2026-06-01 | 2025-05-21 | 2025-04-30 |  |  | 51 | 0 | 120 | 0 |  | X
07 | 07-4V3004 | 4V3004 | 07-LA-5-8.2/8.2 | HB4N |  | Ptm General Engineering Services Inc. | 5942 Acorn St. | Riverside Ca Ca 92509 |  | 5623459865 | 13230 Firestone Blvd | Santa Fe Springs, Ca 90670 | Frempong, Samuel | 1500 | 0 | 0 | 0 | 2025-08-20 | Upgrade Traffic Signal And Lighting. | Los Angeles County In Downey At Route 5/19Separation | 100 | 100 | 439041.93 | 373000 | 435201.93 | 42844 | 2026-03-30 | 2022-06-30 | 2022-06-16 |  |  | 60 | 0 | 60 | 0 |  | X
07 | 07-2XJ004 | 2XJ004 | 07-LA-5-16.0/17.3 | 20.XX 201130 |  | Dbx Inc | 42024 Avenida Alvarado Ste A | Temecula, Ca 92590 | 9512969909 | 2137937193 | 1041 W Badillo Suite 112 | Covina, Ca 91722 | Pham, Ryan | 23875 | 0 | 0 | 0 | 2025-12-31 | Restore/Repair Fiber Optic Theft Damage | In La County@ Ela Interchange Routes 5,10,60 & 101 To Restore/Repair Highway Lightng& Associated Rdwy Electrical &Comm Systemsdir' | 100 | 100 | 4031306.29 | 23875 | 4065000 | 52184 | 2025-12-31 | 2023-07-18 | 2023-06-12 | 2026-01-23 |  | 90 | 0 | 90 | 0 |  | X
07 | 07-372604 | 372604 | 07-LA-5-18.7/0 |  | ACIM-X037- (244)000 | Calpromax Engineering, Inc. | 650 N. Rose Dr. #186 | Placentia Ca 92870 |  | 2137937193 | 21073 Pathfinder Rd Ste 100 | Diamond Bar, Ca 91765 | Pham, Ryan | 0 | 0 | 0 | 0 |  | Modify Signal & Lighting, And Construct Ad | Los Angeles County In Los Angeles At Soto-Marengo Street Overcrossing And At Northbound Route 5 Off-Ramp To Soto Street | 0 | 0 | 0 | 1715305.5 | 1715305.5 | 60431 |  | 2026-02-17 | 2026-01-21 |  |  | 0 | 0 | 160 | 0
07 | 07-344204 | 344204 | 07-LA-5-23.2/36.3 |  | ACIM-X037- (234)E | Powell Constructors Inc | 8555 Banana Avenue | Fontana Ca 92335 |  | 8184829304 | 2090 Fern Lane | Glendale, Ca 91208 | Tran, Danglong | 189125.94 | 60686.52 | 0 | 0 | 2026-02-20 | Construct Gsrds, Mvps, And Bioswales. | Los Angeles County At Various Locations | 48 | 73 | 4016333.83 | 4957414.25 | 5452414.25 | 56075 | 2027-03-25 | 2024-07-12 | 2024-06-13 |  |  | 233 | 0 | 490 | 0 |  | X
07 | 07-370804 | 370804 | 07-LA-5-30.6/31.6 |  | ACIM-0052- (057)000 | Security Paving Company, Inc. | 3075 Townsgate Rd Ste 200 | Westlake Village Ca 91361 | 8183629200 | 8184829304 | 2090 Fern Lane | Glendale, Ca 91208 | Tran, Danglong | 1382732.7 | 0 | 0 | 825000 | 2026-02-20 | Remove Concrete Pavement And Base, And Pla | Los Angeles County In Burbank From 0.2 Mile North Of San Fernando Boulevard To 0.2 Mile South Of Cohasset Street | 12 | 20 | 2277362.7 | 11222414 | 11422414 | 60166 | 2026-12-24 | 2025-11-10 | 2025-10-22 |  |  | 28 | 0 | 240 | 0 |  | X
07 | 07-0W1004 | 0W1004 | 07-LA-5-31.8/42.6 | HM1 |  | C. A. Rasmussen, Inc. | 28548 Livingston Avenue | Valencia Ca 91355 | 6613679040 | 8186130956 | 23369 Leonora Dr | Woodland Hills, Ca 91367 | Gurfinkel, Vladimir | 13102.6 | 0 | 0 | 0 | 2025-10-20 | Replace Pcc Slabs,Grind Pcc | In Los Angeles County In Los Angeles From Cohasset Street Under- Crossing To Roxford Street Under- Crossing | 100 | 98 | 8587560.71 | 8295854 | 8401277.25 | 42964 | 2025-10-28 | 2022-07-11 | 2022-06-28 |  |  | 174 | 0 | 160 | 0 |  | X
07 | 07-384404 | 384404 | 07-LA-5-33.1/39.1 |  |  | Martinez Landscape Co., Inc | 12357 San Fernando Road | Sylmar Ca 91342 | 8183649188 | 8182628853 | 9225 Cranford Ave | Pacoima, Ca 91331 | Bui, Kevin | 0 | 10411.68 | 0 | 0 | 2025-10-20 | Clean Ca Beautification | La Co. Route 5 Between Pm 33.1 And Pm 39.1 | 100 | 93 | 4854592.01 | 5042930.5 | 5211685.5 | 43984 | 2026-02-27 | 2022-08-25 | 2022-07-06 |  |  | 560 | 0 | 1000 | 440 |  | X
07 | 07-2XT804 | 2XT804 | 07-LA-5-36.0/36 | 20.XX 201130 |  | Interstate Civil Construction | P.O. Box 2819 | Wrightwood, Ca 92397 | 7602810188 | 5625725983 | 9225 Cranford Ave | Pacoima, Ca 91331 | Bui, Kevin | 0 | 100988.11 | 0 | 0 | 2026-01-20 | Repair Damages To Bridge Superstructure | In La County City Of Sun Valley S/B 5 At Sheldon Street O/C Brdge#53-1120 Constructsupport & Repair Damages To Bridge Structrdir'S | 3 | 9 | 100988.11 | 7887 | 1137000 | 60254 | 2026-05-29 | 2025-09-26 | 2025-08-04 |  |  | 2 | 0 | 60 | 0 |  | X
07 | 07-2XS804 | 2XS804 | 07-LA-5-53.7/53.7 | 20.XX 201130 |  | Interstate Civil Construction | P.O. Box 2819 | Wrightwood, Ca 92397 | 7602810188 | 2138170162 | 25061 W Avenue Stanford Suite 70 | Valencia, Ca 91355 | Bakhet, Wassem | 0 | 181696.7 | 0 | 0 | 2026-02-20 | Remove/Replace Bridge Joint | In La County, City Of Valencia S/B I-5 At Abutment 1 Santa Clara River Brdge 53-2925Remove&Replace Damaged Steel Joint Assmblydir' | 60 | 21 | 257380.9 | 8367 | 1217000 | 60103 | 2026-04-22 | 2025-08-28 | 2025-06-27 |  |  | 18 | 0 | 30 | 0 |  | X
07 | 07-4V5404 | 4V5404 | 07-LA-5-56.4/56.7 |  | SIMG-0052- (777)000 | Genuine Engineering, Inc. Attn Kristi Stelle | 11762 De Palma Rd Ste 1C-255 | Corona Ca 92883 | 9516745000 | 8182628913 | 9225 Cranford Ave | Pacoima Ca 91331 | Bui, Kevin | 0 | 35336.49 | 0 | 0 | 2026-02-20 | Modify Single Lane Roundabout. | Los Angeles County In Castaic From 0.2 Mile South Of Hasley Canyon Road Overcrossing To 0.1 Mile North Of Hasley Canyon Road Overc | 72 | 96 | 922110.74 | 868426.5 | 936676.5 | 59477 | 2026-03-27 | 2025-07-22 | 2025-06-19 |  |  | 36 | 0 | 50 | 0 |  | X
07 | 07-323404 | 323404 | 07-LA-5-59.5/67.9 | HA22 | ACIM-0053- (074)E | Security Paving Company, Inc. | 3075 Townsgate Road | Westlake Village Ca 91361 | 8183629200 | 2137925518 | 25061 West Ave Stanford Ste 70 | Valencia, Ca 91355 | Osorio, Oscar | 17986.67 | 0 | 0 | 0 | 2026-02-20 | Replace Slabs, Upgrade Drainage | At Valencia And Castaic, From Lake Hughes Road Undercrossing To 1.9 Miles North Of Templin Highway. | 93 | 93 | 24324725.32 | 23715762 | 26201835.17 | 42284 | 2026-04-15 | 2022-03-30 | 2022-02-25 |  |  | 632 | 0 | 680 | 0 |  | X
07 | 07-370404 | 370404 | 07-LA-5-59.5/73.7 |  | ACIM-0053- (999)E | Griffith Company | 3050 E. Birch St | Brea Ca 92821 | 9093566880 | 2135050610 | 25061 W Avenue Stanford Ste 70 | Valencia, Ca 91355 | Salman, Ridwan | 1161278.6 | 8786.73 | 77239.17 | 0 | 2026-02-20 | Cold Plane Ac Pavement, Place Hot Mix Asph | Los Angeles County From Lake Hughes Road Undercrossing To 0.7 Mile South Of Vista Del Lago Road Overcrossing. | 32 | 60 | 29503804.72 | 47662735 | 48994855.9 | 57238 | 2027-08-19 | 2025-02-27 | 2025-02-06 |  |  | 176 | 0 | 800 | 0 |  | X
07 | 07-352304 | 352304 | 07-LA-5-60.0/75 |  | PTIM-0053- (113)E | Powell Constructors Inc | 8555 Banana Avenue | Fontana Ca 92335 | 9093568880 | 2137925518 | 25061 W Ave Stanford #70 | Valencia Ca 91355 | Osorio, Oscar | 144714.6 | 18684 | 2000 | 0 | 2026-01-20 | Replace Drainage Systems, Install Gsrd, An | Los Angeles County In And Near Castaic From 0.5 Mile North Of Lake Hughes Road To0.5 Mile North Of Vista Del Lago Road | 57 | 90 | 6472788.41 | 6989277 | 7083777 | 56009 | 2026-02-28 | 2024-06-20 | 2024-06-03 |  |  | 303 | 0 | 530 | 0 |  | X
07 | 07-2XT504 | 2XT504 | 07-LA-5-138.0/13.8 | 20.XX 201130 |  | Jfl Electric Inc | 8257 Compton Avenue | Los Angeles, Ca 90001 |  | 2137924801 | 1201 Baldwin Park Blvd | Baldwin Park, Ca 91706 | Ngo, Jason | 0 | 120984.33 | 0 | 0 | 2026-02-20 | Repair & Install Security@ Pump Plant | La County,City Of La On S/B La-5 @Eastern Ave Pump Plant To Repair Damages To Servcecabinet & Install Security Systems Dir'S Emerg | 27 | 33 | 456751.39 | 15851 | 1373000 | 58736 | 2026-05-29 | 2025-06-10 | 2025-06-03 |  |  | 24 | 0 | 90 | 0 |  | X
07 | 07-0Y1504 | 0Y1504 | 07-LA-5-151.1/188.2 |  |  | Interstate Civil Construction | 6025 Park Dr | Wrightwood Ca 92397 |  |  | 902 San Gabriel Blvd | Rosemead Ca 91770 | Azam Shoaib Bin | 0 | 0 | 0 | 0 |  | Individual Slab Replacement, Digouts, And | Los Angeles County In Los Angeles At Various Locations From 0.2 Mile East Of Esperanza Street Undercrossing To Mission Road Overcr | 0 | 0 | 0 | 2956965.8 | 2956965.8 | 59618 | 2026-06-25 | 2025-08-05 | 2025-06-26 |  |  | 0 | 0 | 100 | 0
07 | 07-2XW404 | 2XW404 | 07-LA-5-658.0/66 | 20.XX 201130 |  | Griffith Company | 3050 E Birch St | Brea Ca 92821 |  | 2135052610 | 25061 W Avenue Stanford Ste 70 | Valencia Ca 91355 | Wassem Bakhet | 0 | 0 | 0 | 0 |  | Repair Storm Damage | In La County At Sb Interstate 5 South Of Templin Highway,Inspect Repair Pavement&Subgrade&Shoulders, Remove Debris. Dir'S Emergen | 0 | 0 | 0 | 3227 | 756300 | 60400 | 2026-05-04 | 2026-01-16 | 2025-12-11 |  |  | 0 | 0 | 60 | 0
07 | 07-319304 | 319304 | 07-LA-5-/19.5 | HB1 | HSST-X037- (224)E | Re Chaffee Construction Inc. | 1253 Evergreen Rd | Wrightwood Ca 92397 | 7602498068 | 2137008447 | 1525 Rancho Conejo Blvd Ste102 | Thousand Oaks, Ca 91320. | Tehrani, Joseph | 2676.81 | 0 | 0 | 0 | 2026-02-20 | Reduce Severity Collisions By | From County Line To Broadway, Reduce Severity Collisions | 100 | 91 | 3693755.14 | 3797765 | 4056168.08 | 45544 | 2026-05-30 | 2022-11-18 | 2022-10-07 |  |  | 318 | 0 | 180 | 0 |  | X
07 | 07-347504 | 347504 | 07-LA-10-2.2/4.9 | HA25 | ACIM-0101- (858)E | Griffith Company | 3050 E. Birch St | Brea Ca 92821 |  | 2139526068 | 601 S Glenoaks Blvd Suite 310 | Burbank, Ca 95102 | Salman,Ridwan | 2286.25 | 0 | 0 | 0 | 2025-12-20 | Rehabilitate Highway Planting And Modify I | Los Angeles County In Santa Monica And Losangeles From Lincoln Boulevard Overcrossing To Gateway Boulevard Undercrossing | 100 | 11 | 260625.1 | 2390787.5 | 2430287.5 | 55348 | 2028-12-04 | 2024-02-28 | 2024-01-09 |  |  | 252 | 0 | 1000 | 0
07 | 07-2XH804 | 2XH804 | 07-LA-10-2.2/5.2 | 20.XX 201130 |  | Baltazar Construction, Inc | 236 E. Arrow Hwy | Covina, Ca 91722 |  | 5625725852 | 12975 W. Culver Blvd | Los Angeles, Ca 90066 | Martinez, Elizabeth | 0 | 71744.84 | 0 | 0 | 2024-04-20 | Clean & Repair Storm Damage | In La County Cities Of Santa Monica& La-10To Reconstruct Eroded Slopes,Remove Debrisrepair Irrigation&Clean Ds @ 4 Locations Dir'S | 90 | 58 | 426239.36 | 5475 | 735000 | 53505 | 2026-04-30 | 2023-07-27 | 2023-07-12 |  |  | 27 | 0 | 30 | 0
07 | 07-332004 | 332004 | 07-LA-10-4.5/5.5 | HA42 |  | Marina Landscape, Inc. | 3707 W. Garden Grove Blvd | Orange Ca 92868 | 7149396600 | 3102133136 | 12975 Culver Blvd | Los Angeles, Ca 90066 | Shin, Frank | 4500 | 0 | 0 | 0 | 2026-02-20 | Install Irrigation System And Plant | In The City Of Los Angeles From Bundy Drive To Sepulveda Boulevard Undercrossing; And On Rte 405 From Olympic Blvd To National Bl | 100 | 93 | 1405148.29 | 1463402 | 1503402 | 44624 | 2027-03-05 | 2022-09-27 | 2022-09-02 |  |  | 740 | 0 | 1000 | 0 |  | X
07 | 07-358404 | 358404 | 07-LA-10-4.7/18.9 |  | PTIM-0101- (859)E | Yakar | 689 East San Bernardino Rd | Covina Ca 91723 | 9095991612 | 2139652415 | 902 San Gabriel Blvd | Rosemead, Ca 91770 | Minovi,Sepand | 1620 | 0 | -357.43 | 0 | 2026-02-20 | Replace And Line Culvert And Construct Gro | The City And County Of Los Angeles At Various Locations From 0.2 Mile East Bundydrive Undercrossing To 0.1 Mile West Soto Street O | 0 | 0 | 3061361.31 | 2938925 | 3136714.1 | 56927 | 2026-08-13 | 2025-01-07 | 2024-12-17 |  |  | 248 | 0 | 370 | 0 | X | X
07 | 07-328304 | 328304 | 07-LA-10-28.2/31 | HA21 |  | Beador Construction Company, Inc. | 2900 Bristol Street D204 | Costa Mesa, Ca 92626 |  | 9512323742 | 1041 W Badillo St#112 | Covina, Ca 91722 | Hong, Hai | 0 | 27849.25 | 0 | 0 | 2026-02-20 | Construct Bridge Closure Pour. | Los Angeles County At Various Locations Inel Monte And Baldwin Park From Rio Hondo Bridge To San Gabriel River Bridge | 90 | 91 | 5448149.41 | 5247700 | 5984319.25 | 53304 | 2026-04-17 | 2023-10-18 | 2023-09-26 |  |  | 361 | 0 | 400 | 0 |  | X
07 | 07-316804 | 316804 | 07-LA-10-28.3/28.3 | HA21 |  | Powell Constructors,Inc. | 8555 Banana Avenue | Fontana Ca 92335 | 9093568880 | 2132164198 | 902 San Gabriel Blvd. | Rosemead, Ca 91770 | Azam, Shoaib Bin | 118007.5 | 0 | 0 | 0 | 2026-02-20 | Replace Bridge Deck. | Los Angeles County In El Monte At The Rio Hondo Busway Bridge | 88 | 97 | 5130909.66 | 5201229.6 | 5304693.3 | 55326 | 2026-05-08 | 2024-02-14 | 2024-01-26 |  |  | 385 | 0 | 440 | 0 |  | X
07 | 07-398404 | 398404 | 07-LA-10-28.5/30.8 |  |  | Martinez Landscape Co., Inc. | 12357 San Fernando Road | Sylmar Ca 91342 | 8183649188 | 2137924801 | 1201 Baldwin Park Blvd | Baldwin Park, Ca 91706 | Ngo, Jason | 0 | 0 | 0 | 0 | 2026-01-20 | Replace Irrigation System, Highway Plantin | Los Angeles County In El Monte 0.2 Mile West Of Santa Anita Avenue Undercrossing To The San Gabriel River | 100 | 100 | 1021473.65 | 999330.75 | 1011387.87 | 56587 | 2026-01-20 | 2024-10-23 | 2024-08-30 | 2026-01-29 |  | 231 | 0 | 239 | 0 |  | X
07 | 07-4V5304 | 4V5304 | 07-LA-10-47.9/0 |  |  | Bosco Constructors Inc. | 21353 Mayall St. | Chatsworth Ca 91311 |  |  |  |  | Raj, Punjabi | 0 | 0 | 0 | 0 |  | Modify Drainage System And Construct Dppia | Los Angeles County In Claremont At 0.1 Mile East Of South Indian Hill Boulevard | 0 | 0 | 0 | 951098.96 | 951098.96 | 59458 | 2026-09-21 | 2025-07-22 | 2025-06-24 |  |  | 0 | 0 | 140 | 0
07 | 07-2XP804 | 2XP804 | 07-LA-10-78.0/9.3 | 20.20 201130 |  | Flo Concrete | 902 S Vanhorn Ave | West Covina, Ca 91790 |  | 2139526068 | 601 South Glenoaks Blvd | Burbank Ca, 91502 | Salman Ridwan | 0 | 7999.63 | 0 | 0 | 2026-02-20 | Remove Concrete Slabs | La-10 Remove Concrete Slabs, Fill Voids W-Ith Slurry,Reconstruct Hma Shoulder, Reco-Nstruct Side Slopes, Construct Handscape. Dir' | 100 | 85 | 1378018.47 | 31296 | 1629800 | 56641 | 2026-03-31 | 2024-09-13 | 2024-09-09 |  |  | 209 | 0 | 60 | 0 |  | X
07 | 07-316004 | 316004 | 07-LA-14-60.7/77 | H |  | Guy F. Atkinson | 611 Anton Blvd. Suite 1100 | Costa Mesa, Ca 92626 | 9498559755 | 2137937522 | 39115 Trade Center Dr Ste, 210 | Palmdale, Ca 95331 | Shih, James | 2527045.24 | 195542.5 | 139802.1 | 0 | 2026-02-20 | Reconstruct Pavement Structural | In Palmdale And Lancaster, From Technology Drive Undercrossing To Avenue A Overcrossing | 73 | 82 | 147663053 | 160193801 | 178813495.97 | 47290 | 2027-01-26 | 2023-03-03 | 2023-02-07 |  |  | 618 | 0 | 700 | 150 |  | X
07 | 07-322904 | 322904 | 07-LA-27-/18.6 | HA22 | CSTP-S027- (006)E | C. A. Rasmussen, Inc. | 28548 Livingston Avenue | Valencia Ca 91355 | 6613679040 | 8186130956 | 23369 Leonora Dr | Woodland Hills, Ca 91367 | Gurfinkel, Vladimir | 70400 | 41437.07 | 0 | 0 | 2026-02-20 | Remove Existing Ac Pavement & Hma Overlay. | Los Angeles County In And Near Los Angelesfrom Route 1 To Devonshire Street | 79 | 76 | 33278006.76 | 40633353 | 43554981.26 | 54084 | 2026-08-28 | 2023-11-30 | 2023-11-06 |  |  | 472 | 0 | 600 | 0 |  | X
07 | 07-2XN904 | 2XN904 | 07-LA-27-/5 | 20.XX 201130 |  | Flo Engineering Inc Dba Flo Concrete | 902 S Vanhorn Ave | West Covina, Ca 91790 |  | 3107159500 | 12975 W Culver Blvd | Los Angeles, Ca 90066 | Martinez, Elizabeth | 0 | 671281.62 | 0 | 0 | 2026-02-20 | Repair Slope Due To Storm Damage | In La County On La-27 Pm 0.0 To 5.0 Stabilize/Repair Var Slope Location Repaireroded Concrt Rsp Due To Heavy Storms Dir'S Emergenc | 63 | 34 | 6425881.71 | 53136 | 19121800 | 55769 | 2026-06-28 | 2024-05-10 | 2024-03-20 |  |  | 140 | 65 | 120 | 0 |  | X
07 | 07-2XR304 | 2XR304 | 07-LA-27-/11 | 20.XX 201130 |  | Flo Engineering Inc | 902 S Vanhorn Ave | West Covina, Ca 91790 |  | 3107159500 | 112975 W. Culver Blvd | Los Angeles, Ca 90066 | Martinez, Elizabeth | 0 | 1567256.67 | 0 | 0 | 2026-02-20 | Repair Storm & Fire Damage/Debris | La County,City Of La On La-27 From La-1Pchto Mulholland Dr To Stabilize Damagd Slopefrom Fire & Storm-Clean Debris & D-Systemsdir' | 4 | 43 | 14047867.95 | 251300 | 33050000 | 57340 | 2028-03-24 | 2025-03-18 | 2025-03-04 |  |  | 12 | 0 | 300 | 0 |  | X
07 | 07-390204 | 390204 | 07-LA-47-.4/2.1 |  | ACNH-P047- (017)000 | Skanska-Cec Joint Venture | 1995 Agua Mansa Road | Riverside Ca 92509 |  | 3103456188 | 18101 Bailey Dr | Torrance, Ca 90502 | Gallardo, Sam | 0 | 0 | 0 | 0 |  | Bridge Deck Replacement | Los Angeles County In Los Angeles At Vincent Thomas Bridge | 0 | 0 | 0 | 534077177 | 534077177 | 60389 | 2029-09-24 | 2026-01-08 | 2025-12-12 |  |  | 0 | 0 | 1235 | 0
07 | 07-2XT904 | 2XT904 | 07-LA-47-1.6/1.6 | 20.20 201130 |  | Griffith Company | 3050 E Birch St | Brea, Ca 92821 |  | 2133100860 | 970 W 190Th Ste 270 | Torrance Ca 90502 | Shahriari, Shahnam | 0 | 113895.75 | 0 | 0 | 2026-01-20 | Repair Steel Fingers | La-47 To Repair Steel Fingers At Vtb. Weldsteel Plates.Remove & Replace Fractured & Failed Steel Fingers. Dir'S Emergency Force Ac | 73 | 15 | 746745.97 | 16958 | 4868500 | 59695 | 2026-10-31 | 2025-06-11 | 2025-05-16 |  |  | 44 | 0 | 60 | 0 |  | X
07 | 07-368704 | 368704 | 07-LA-57-11.0/12.3 |  | ACIM-X037- (242)000 | Powell Constructors, Inc. | 8555 Banana Avenue | Fontana Ca 92335 |  | 9512323742 | 21073 Pathfinder Rd Ste 100 | Diamond Bar, Ca 91765 | Hong, Hai | 0 | 0 | 0 | 0 |  | Replace Lighting System. | Los Angeles County In Glendora And San Dimas On Route 57 From 0.3 Mile South Of Gladstone Street Undercrossing To Route 210/57 Sep | 0 | 0 | 0 | 5868871 | 5868871 | 60222 | 2028-01-15 | 2025-12-01 | 2025-11-14 |  |  | 0 | 0 | 340 | 0
07 | 07-0Y1804 | 0Y1804 | 07-LA-60-/3.3 |  |  | Pavement Coatings Co. | 10240 San Sevaine Way | Jurupa Valley Ca 91752 | 9519344719 | 2132691320 | 902 San Gabriel Blvd | Rosemead Ca 91770 | Vong, Jeanette | 0 | 93474.56 | -3919.51 | 0 | 2026-02-20 | Replace Asphalt Concrete Surfacing And Slu | Los Angeles County At Various Locations From Junction Route 10 To Route 60/710 Separation | 99 | 98 | 1441702.33 | 1456586.3 | 1593666.79 | 58616 | 2026-03-31 | 2025-06-09 | 2025-04-28 |  |  | 99 | 0 | 100 | 0 |  | X
07 | 07-210624 | 210624 | 07-LA-71-1.6/4.8 | HE13 |  | Ohl Usa, Inc. | 34 Executive Park Suite 180 | Irvine Ca 92614 | 9492424432 | 3102619100 | 1041 W Badillo, Suite 112 | Covina, Ca 91722 | Wang, Mike | 601010.34 | 129676.33 | 1950.39 | 0 | 2026-02-20 | Upgrade From Expressway To Freeway | La County Route 71 Pm R1.6/4.8 In Pomona From Mission Blvd To Rte 60 | 92 | 96 | 110709383.97 | 85920262.42 | 114218758.39 | 41521 | 2026-03-31 | 2021-03-16 | 2021-02-05 |  |  | 992 | 0 | 970 | 104 |  | X
07 | 07-346504 | 346504 | 07-LA-91-6.0/20.7 |  | ACNH-P091- (160)E | Security Paving Company, Inc. | 3075 Townsgate Road, Suite 20 | Westlake Village Ca 91361 | 8183629200 | 2137937974 | 4281 Katella Ave Ste 221 | Los Alamitos, Ca 90720 | Taing,Steven | 366717.59 | 2313.75 | 0 | 1247470.06 | 2026-02-20 | Replace Overhead Signs & Sign Structures, | Los Angeles County On Route 91 At Various Locations From Vermont Avenue In Los Angeles To The Orange County Line In Cerritos | 7 | 10 | 2468292.32 | 24031447 | 24531447 | 59557 | 2028-07-28 | 2025-07-30 | 2025-07-14 |  |  | 44 | 0 | 610 | 0 |  | X
07 | 07-3203U4 | 3203U4 | 07-LA-91-16.6/16.8 | HA22 | ACIM-X037- (232)E | Rasmussen/Vanguard | 28548 Livingston Avenue | Valencia Ca 91335 | 6613679040 | 2133306640 | 4281 Katella Ave Suite 221 | Los Alamitos, Ca 90720 | Oregel, Martin | 753656.84 | 410148.2 | -30868.3 | 0 | 2026-02-20 | Place Concrete Pavement And High Friction | Los Angeles County On Route 605 From 0.2 Mile North Of Katella Avenue Undecrossing To 0.1 Mile North Of Telegraph Road Undercrossi | 62 | 91 | 49526615.92 | 49941871.9 | 53867328.83 | 50885 | 2026-06-17 | 2023-07-06 | 2023-06-20 |  |  | 537 | 0 | 870 | 0 |  | X
07 | 07-0W0604 | 0W0604 | 07-LA-101-1.0/9.2 | HM1 |  | 3Sixty Innovation, Inc. | 3555 Rosecrans St 114-110 | San Diego Ca 92110 | 8583041093 | 5623459865 | 13320 S Firestone Blvd Ste A | Santa Fe Springs, Ca 90670 | Frempong, Sam | 31707.26 | 0 | 0 | 0 | 2025-07-20 | Slabs Repair, Digouts - Shoulders, | In Los Angeles County In Los Angeles From Spring St Oc To Barham Blvd Oc, Slabs Repair, Digouts - Shoulders, Gores, 2 Ramps | 98 | 91 | 2871157.76 | 3028403.5 | 3097385.63 | 43964 | 2026-05-30 | 2022-08-24 | 2022-06-28 |  |  | 295 | 0 | 300 | 0 |  | X
07 | 07-0W2904 | 0W2904 | 07-LA-101-1.5/10.9 | HM |  | Peterson-Chase General Engineering Construction, Inc. | 16351 Construction Circle Wes | Irvine Ca 92606 |  | 2132691320 | 902 San Gabriel Blvd | Rosemead, Ca 91770 | Vong, Jeanette | 22880 | 46021.85 | 0 | 0 | 2026-02-20 | Deck Methacrylate, Joint Seal Replacement, | Los Angeles County In Los Angeles At Various Locations | 100 | 99 | 6757352.05 | 6442038.48 | 7006795.1 | 50726 | 2026-02-28 | 2023-06-29 | 2023-06-08 |  |  | 299 | 0 | 300 | 0 |  | X
07 | 07-329604 | 329604 | 07-LA-101-6.2/8 | HB34 | ACNH-Q101- (406)E | Bosco Constructors, Inc. | 21353 Mayall St. | Chatsworth Ca 91311 | 8187000304 | 2139526068 | 601 S Glenoaks Blvd Suite 310 | Burbank, Ca 91502 | Salman Ridwan | 269067 | 0 | 0 | 0 | 2026-02-20 | Roadside Safety Improvements | In The City And County Of Los Angeles From Wilton Place Overcrossing To Pilgrimage Overcrossing | 23 | 40 | 1405467 | 3189245 | 3554309.03 | 47404 | 2027-05-17 | 2023-03-08 | 2023-02-08 |  |  | 105 | 0 | 460 | 0 |  | X
07 | 07-346304 | 346304 | 07-LA-101-7.9/11.8 |  | ACNH-Q101- (439)E | Chumo Construction, Inc. | 14425 Joanbridge Street | Baldwin Park Ca 91706 |  | 8186130956 | 23369 Leonora Dr | Woodland Hills, Ca 91367 | Gurfinkel, Vladimir | 486896.51 | 70648.54 | 9038.4 | 1025000 | 2026-02-20 | Install Rubberized Hot Mixed Asphalt. | Los Angeles County In The City And County Of Los Angeles From 0.1 Mile South Of Pilgrimage Overcrossing To Route 101/170 Separatio | 14 | 10 | 2215930 | 21039634.56 | 21485581.22 | 58396 | 2027-11-26 | 2025-05-28 | 2025-04-28 |  |  | 112 | 0 | 810 | 0 |  | X
07 | 07-307104 | 307104 | 07-LA-101-32.8/33.8 |  |  | C. A. Rasmussen, Inc. | 28548 Livingston Avenue | Valencia Ca 91355 | 6643679040 | 3103456201 | 23369 Leonora Dr | Woodland Hills, Ca 91367 | Gurfinkel, Vladimir | 59850 | 223230.15 | 0 | 0 | 2026-02-20 | Wildlife Habitat Connectivity | In La, Wildlife Crossing @ Liberty Canyon At Or In The Vicinity Of Liberty | 68 | 58 | 32974607.61 | 22719732.3 | 56606840.33 | 42300 | 2027-08-18 | 2022-04-14 | 2022-03-17 |  |  | 855 | 0 | 1250 | 0 |  | X
07 | 07-320104 | 320104 | 07-LA-101-/1.5 | HA42 |  | Fec Future Contractors And Engineers, Inc. | 184 Technology Drive, Suite 2 | Irvine Ca 92618 | 9493289758 | 9093224628 | 902 San Gabriel Blvd. | Rosemead, Ca 91770 | Minovi, Sepand | 2100 | 0 | 0 | 0 | 2026-02-20 | Stormwater Source Control | In Los Angeles County In Los Angeles, From Routes 5/101 Interchange To Figueroa Street | 0 | 0 | 3705743.39 | 3720860.53 | 3734935.16 | 9843 | 2028-02-24 | 2022-11-28 | 2022-11-01 |  |  | 495 | 0 | 930 | 56 | X
07 | 07-327304 | 327304 | 07-LA-103-.1/.1 | HA22 | ACNH-P103- (005) | Shimmick Construction Company, Inc. | 530 Technology Dr. #300 | Irvine Ca 92618 | 9493331500 | 5625725852 | 12975 Culver Blvd | Los Angeles, Ca 90066 | Martinez, Elizabeth | 1896 | 149188.3 | 0 | 0 | 2026-02-20 | Construct Larger Pump Plant | In Los Angeles County In Los Angeles At Henry Ford Avenue Off-Ramp | 95 | 94 | 18542369.99 | 12248070.82 | 19597483.78 | 42467 | 2026-03-13 | 2022-06-09 | 2022-04-21 |  |  | 759 | 0 | 590 | 205 |  | X
07 | 07-355604 | 355604 | 07-LA-105-2.0/0 |  |  | Griffith Company | 3050 E. Birch St | Brea Ca 92821 | 3235858585 | 2133100860 | 970 W. 190Th Street Suite 270 | Torrance, Ca 90502 | Shahriari, Shahnam | 727924.22 | 29380.98 | 251199.33 | 0 | 2026-02-20 | Construct A Maintenance Equipment Training | Los Angeles County In Los Angeles At 0.1 Mile West Of Route 105/405 Separation | 22 | 26 | 4001041 | 14796999 | 15156833.01 | 57555 | 2027-09-09 | 2025-03-13 | 2025-02-20 |  |  | 112 | 0 | 500 | 0 |  | X
07 | 07-2XH7A4 | 2XH7A4 | 07-LA-105-2.2/2.2 | 20.20 201130 |  | Crosstown Electrical & Data Inc | 5454 Diaz St | Irwindale Ca 91706 |  | 8182547484 | 13230 Firestone Blvd Ste E | Santa Fe Springs Ca 90670 | Karout, Ali | 0 | 13271.26 | 0 | 0 | 2024-11-20 | Repair Failed Vfd In Tunnel#4 | La-105 City Of Hawthorne To Repair Failed Vfd'S/Breakers Within Ventilation System'Smotor Control In Tunnel 53-2441F Tunnel#4 Dir' | 16 | 96 | 701817.72 | 4487 | 777000 | 55365 | 2026-03-12 | 2024-02-13 | 2023-12-29 |  |  | 59 | 0 | 60 | 300 |  | X
07 | 07-364604 | 364604 | 07-LA-105-14.1/14.7 |  |  | Powell Constructors, Inc. | 8555 Banana Avenue | Fontana Ca 92335 |  |  |  |  | Lee, Peter | 0 | 0 | 0 | 0 |  | Dewatering Wells Work, Place Retaining Wal | Los Angeles County In Paramount And South Gate From 0.1 Mile East Of Garfield Avenueto 0.1 Mile East Of Paramount Boulevard | 0 | 0 | 0 | 6146056.5 | 6146056.5 | 60383 | 2028-06-23 | 2026-01-29 | 2026-01-07 |  |  | 0 | 0 | 560 | 0
07 | 07-4V4904 | 4V4904 | 07-LA-105-17.5/17.8 |  |  | Accu Construction, Inc. | 14751 Plaza Drive Suite L | Tustin Ca 92780 | 7146414730 | 5623459894 | 13230 Firestone Blvd. | Santa Fe Springs, Ca 90670 | Martinez, Francisco | 2014 | 0 | 0 | 0 | 2025-12-20 | Replace Planting And Irrigation System. | Los Angeles County In Norwalk From The Sangabriel River To Route 105/605 Separation | 85 | 95 | 626672.16 | 632142 | 660402.29 | 56136 | 2026-03-17 | 2024-07-03 | 2024-06-06 |  |  | 318 | 0 | 375 | 0 |  | X
07 | 07-2XJ504 | 2XJ504 | 07-LA-105-20.0/2 | 20.XX 201130 |  | Crosstown Electrical&Data Inc | 5454 Diaz Street | Irwindale, Ca 91706 | 6268136693 | 8182547484 | 13230 Firestone Blvd | Santa Fe Springs, Ca 90670 | Karout, Ali | 0 | 51199.07 | 0 | 0 | 2026-02-20 | Repair/Replace Vfd In Various System | La County City Of Hawthorne@E105 N&S 405 Connector Tunnels 5&8 53-2436G 53-2437G Repair/Replace Vfd In Vent,Fire&Electricaldir'S E | 98 | 89 | 3098441.68 | 15383 | 3495000 | 56580 | 2026-05-21 | 2024-10-04 | 2024-09-23 |  |  | 147 | 0 | 150 | 0 |  | X
07 | 07-2XQ304 | 2XQ304 | 07-LA-105-/18.1 | 20.20.201131 |  | Jfl Electric Inc | 8257 Compton Avenue | Los Angeles, Ca 90001 | 2138172443 | 8182547484 | 13230 Firestone Blvd | Santa Fe Springs, Ca 90670 | Karout, Ali | 0 | 923.29 | 0 | 0 | 2026-02-20 | Repair Transportation Management Systems | La County,Various Cities On La-105 To Repair/Remove/Replace Damaged Tms Elementsinstall Security Measures&Restore Tms Elemdir'S Em | 55 | 70 | 2393776.53 | 23524 | 3417000 | 58235 | 2026-07-23 | 2025-05-15 | 2025-04-25 |  | S | 133 | 0 | 240 | 0 |  | X
07 | 07-4W7804 | 4W7804 | 07-LA-110-6.8/19.5 | HM3 |  | Autobahn Construction, Inc. | 933 N. Batavia St. | Orange Ca 92867 | 7147697025 | 3103456267 | 970 W. 190Th Street Suite 270 | Torrance, Ca 90502 | Gallardo, Samuel | 22950 | 58296.32 | 0 | 0 | 2024-01-20 | Apply Deck Methacrylate, Replace | 07-110- Pm 6.8/19.5 | 91 | 65 | 1463252.14 | 2144980.84 | 2217292.84 | 41665 | 2026-03-31 | 2021-05-20 | 2021-04-26 |  |  | 109 | 0 | 120 | 0
07 | 07-2XV904 | 2XV904 | 07-LA-110-19.4/19.5 | 20.80 240.00 |  | Interstate Civil Construction | P.O. Box 2819 | Wrightwood, Ca 92397 | 7602810188 | 5623459894 | 13230 Firestone Blvd Suite A2 | Santa Fe Springs, Ca 90670 | Martinez, Francisco | 0 | 0 | 0 | 0 |  | Repair & Construct Fence & Gates | In La County In City Of La On I-110 At Mlk Jr.Blvd To Remove & Construct Fence & Gates,Place Concrete,Large Rocks&Plants Dir'S Eme | 0 | 0 | 0 | 6633 | 928000 | 60311 | 2026-04-30 | 2025-12-19 | 2025-11-21 |  |  | 0 | 0 | 120 | 0
07 | 07-2XJ104 | 2XJ104 | 07-LA-110-21.4/25.7 | 20.XX 201130 |  | Ferreira Construction Co Inc Dba Ferreira Coastal Constr.Co | 10370 Commerce Center Dr B200 | Rancho Cucamonga, Ca 91730 |  | 8182547484 | 13230 Firestone Blvd Suite E | Santa Fe Springs, Ca 90670 | Karout, Ali | 0 | 566032.78 | 0 | 0 | 2026-02-20 | Repair Vandalized Communication Systems | La County In City Of La At The Dtla Wrap- Around On Routes 110,5,10 & 101 To Restorerepair Hwy Lighting & Fiber Optics Comm Sydir' | 86 | 69 | 7778516.38 | 19656 | 11250000 | 53144 | 2026-05-21 | 2023-09-29 | 2023-08-15 |  |  | 387 | 0 | 90 | 360
07 | 07-2XQ504 | 2XQ504 | 07-LA-110-26.7/30.7 | 20.XX 201131 |  | P T M General Engineering Services Inc | 5942 Acorn St | Riverside, Ca 92504 |  | 2137937193 | 1041 W. Badillo Suite 112 | Covina, Ca 91722 | Pham, Ryan | 0 | 126410.93 | 0 | 0 | 2026-02-20 | Restore & Repair Wire Theft Damages | In La County In City Of La On La-110 Alongarroyo Seco Parkway To Restore & Repair Wire Theft Damages Dir'S Emergency Force Account | 88 | 66 | 1843795.21 | 13810 | 2792000 | 58936 | 2026-03-23 | 2025-05-20 | 2025-04-25 |  |  | 159 | 0 | 180 | 0
07 | 07-2XT604 | 2XT604 | 07-LA-110-30.5/30.7 | 20.XX 201130 |  | Hartfield Construction Corp | 11908 Clark St Unit A | Arcadia, Ca 91006 |  | 8184829304 | 2090 Fern Lane | Glendale, Ca 91208 | Tran, Danglong | 0 | 17760.26 | 0 | 0 | 2025-12-20 | Repair Roadway Slope & Irrigation | In La County, City Of S Pasadena S/B La 110 At Prospect Ave To Repair Roadway Cutslope/Side Slide Down To Ln 3 On S/B La 110Dir'S | 100 | 48 | 306747.85 | 13194 | 644700 | 59461 | 2027-01-31 | 2025-07-15 | 2025-04-17 |  |  | 169 | 0 | 60 | 0
07 | 07-2XV804 | 2XV804 | 07-LA-110-149.0/16.2 | 20.80 240 |  | Izurieta Fence Company Inc | 3000 Gilroy St | Los Angeles Ca 90039 |  | 5623459894 | 13230 Firestone Blvd Suite A2 | Santa Fe Springs 90670 | Martinez,Francisco | 0 | 0 | 0 | 0 |  | Clean Debris And Install Fence | In The City Of La Interstate 110 At Var Locations. Cleaning Debris And Construct Fence And Gate. Dir'S Emergency F.A | 0 | 0 | 0 | 8601 | 928000 | 60377 | 2026-04-30 | 2025-12-05 | 2025-10-20 |  |  | 0 | 0 | 90 | 0
07 | 07-2XW504 | 2XW504 | 07-LA-110-792.0/82.2 | 20.XX 201130 |  | Sgv Enterprises Inc | 615 Las Tunas Dr Suite J | Arcadia Ca 91007 |  | 8182547383 | 2090 Fern Ln | Glendale Ca 91208 | Shalviri, Ali | 0 | 79655.57 | 0 | 0 | 2026-02-20 | Repair Landslide Caused By Storm Damage | In The Area Of La&Sbd City Of Wrightwood Oon Route Sr-2, Repair&Reconstruct Side Slope, Shoulder And Roadway Dir'S Emergency F.A. | 17 | 2 | 79655.57 | 37865 | 3733600 | 60427 | 2026-12-31 | 2026-02-16 | 2026-01-16 |  |  | 30 | 0 | 180 | 0 |  | X
07 | 07-336804 | 336804 | 07-LA-118-4.5/9.1 | HB34 | ACNH-P118- (069)E | Martinez Landscape Co., Inc | 12357 San Fernando Road | Sylmar Ca 91342 | 8183649188 | 8183642760 | 13171 Telfair Ave Suite 101 | Sylmar, Ca 91342 | Chavez, Efraim | 32572 | 0 | 0 | 0 | 2026-02-20 | Construct Maintenance Vehicle | In The Cities Of Granada Hills And Porter Ranch, From 700 Feet West Of Tampa Avenue To Woodley Avenue | 100 | 89 | 1488360.08 | 1871647 | 1672025.5 | 47005 | 2026-02-23 | 2023-02-23 | 2022-11-17 | 2026-02-23 |  | 409 | 0 | 410 | 0 |  | X
07 | 07-2XS604 | 2XS604 | 07-LA-118-/0 | 20.20 201130 |  | Baltazar Construction, Inc | 236 E. Arrow Hwy | Covina, Ca 91722 |  | 8187460669 | 13171 Telfair Ave Ste 101 | Sylmar, Ca 91342 | Mohsenzadeh, Ali | 0 | 38623.43 | 0 | 0 | 2026-01-20 | Remove/Repair Damaged Trees&Erosion Contrl | La County La-118,210,2,5,101,134 & 710 At Various Post Miles To Remove Fire-Damaged Trees&Repair Side Slopes&Erosion Control Dir'S | 84 | 93 | 1023084.69 | 7660 | 1099200 | 57696 | 2026-04-06 | 2025-04-14 | 2025-02-21 |  |  | 84 | 0 | 100 | 0 |  | X
07 | 07-333704 | 333704 | 07-LA-138-43.4/51.4 |  | ACNH-P138- (067)E | A. M. Concrete, Inc. | 3075 Townsgate Rd #200 | Westlake Village Ca 91361 | 8183628400 | 2137929662 | 39115 Trade Ctr Dr | Palmdale Ca 93551 | Martinez, Roberto | 18000 | 0 | 0 | 0 | 2025-12-20 | Construct Ada Curb Ramps, Sidewalk, And Dr | Los Angeles County In Palmdale From Route 14 Junction (South) To Avenue T | 90 | 47 | 5141969.85 | 10394258.5 | 10762400.7 | 56291 | 2026-04-30 | 2024-08-30 | 2024-07-30 |  |  | 226 | 0 | 250 | 0
07 | 07-4V5204 | 4V5204 | 07-LA-138-59.7/0 |  |  | Polo Engineering, Inc. | 30758 Sloan Canyon Rd | Castaic Ca 91384 | 3104862065 | 2133939940 | 39115 Trade Ctr Dr Ste. 210 | Palmdale Ca 93551 | Beshara, Ramy | 1850 | 0 | 5784.25 | 0 | 2026-02-20 | Signal And Lighting System. | Los Angeles County At Pearblossom At 126Thstreet East | 38 | 92 | 1164016.54 | 1178090.5 | 1241874.54 | 56130 | 2026-03-24 | 2024-07-26 | 2024-06-25 |  |  | 98 | 0 | 120 | 140 |  | X
07 | 07-320804 | 320804 | 07-LA-164-4.0/6.9 | HB71 | CSTP-S164- (003)E | Calpromax Engineering, Inc. | 650 N. Rose Dr. #186 | Placentia Ca 92870 | 7145734599 | 2132164198 | 902 San Gabriel Blvd. | Rosemead, Ca 91770 | Azam, Shoaib Bin | 134273.11 | 59964.06 | 10426.6 | 0 | 2026-02-20 | Construct Minor Concrete And Modifying Sig | Los Angeles County In South El Monte, El Monte And Rosemead At Various Locations Onroute 164 From Rush Street To Rudell Underpass | 56 | 81 | 6440780.42 | 7188691.9 | 7873130.83 | 54264 | 2026-05-13 | 2023-11-30 | 2023-11-01 |  |  | 393 | 0 | 700 | 0 |  | X
07 | 07-326804 | 326804 | 07-LA-210-9.7/51.9 | HB71 |  | Sully-Miller Contracting Company | 135 S State College Blvd #400 | Brea Ca 92821 | 7145789600 | 8182665626 | 9225 Cranford Avenue | Pacoima, Ca 91331 | Shih, James | 13500 | 5800 | 222676.64 | 0 | 2025-08-20 | Americans With Disability (Ada) | At Route 210 From Pm R9.71 To Pm R51.923 | 96 | 100 | 23984208.36 | 23680000 | 24120233.77 | 42429 | 2025-08-31 | 2021-12-23 | 2021-12-14 |  |  | 780 | 0 | 810 | 0 |  | X
07 | 07-0Y1604 | 0Y1604 | 07-LA-210-9.9/22.5 |  |  | Rv Concrete, Inc. | 605 E. Commercial Street | Anaheim Ca 92801 |  | 8184829304 | 2090 Fern Lane | Glendale, Ca 91208 | Tran, Bill | 142500 | 0 | 0 | 0 | 2026-02-20 | Slab Replacement, Slurry Seal, And Digouts | Los Angeles County, In Los Angeles, La Canada Flintridge, Glendale, And Pasadena From Big Tujunga Wash Bridge To Arroyo Boulevard | 93 | 93 | 5065959.47 | 4864456 | 4864456 | 59278 | 2026-02-26 | 2025-07-09 | 2025-06-26 |  |  | 112 | 0 | 120 | 0 |  | X
07 | 07-361804 | 361804 | 07-LA-210-11.0/11.5 |  |  | Autobahn Construction, Inc. | 933 N. Batavia St. | Orange Ca 92867 |  |  |  |  | Ngo,Jason | 0 | 0 | 0 | 0 |  | Drainage System Restoration. | Los Angeles County In Los Angeles City From 0.1 Mile North Of Sunland Boulevard To 0.4 Mile South Of Sunland Boulevard | 0 | 0 | 0 | 2135653 | 2135653 | 60256 |  | 2025-12-15 | 2025-11-13 |  |  | 0 | 0 | 370 | 0
07 | 07-330704 | 330704 | 07-LA-210-15.6/18.5 | HA25 | ACIM-210 -1(853)E | Martinez Landscape Co., Inc | 12357 San Fernando Road | Sylmar Ca 91342 | 8183649188 | 8186372506 | 2090 Fern Lane | Glendale, Ca 91208 | Shalviri, Ali | 5400 | 0 | 0 | 0 | 2026-02-20 | To Restore Existing Irrigation | In Los Angeles County In Glendale And La Canada Flintridge From Lowell Avenue Undercrossing To Waltonia Drive Undercrossing | 0 | 0 | 3243459.5 | 3258059.5 | 3278059.5 | 9847 | 2026-05-29 | 2021-10-01 | 2021-09-09 |  |  | 250 | 0 | 1000 | 0 | X | X
07 | 07-348704 | 348704 | 07-LA-210-18.7/19.7 |  | ACIM-2101- (857)E | Aldridge Electric, Inc. | 844 East Rockland Road | Libertyville Il 60048 | 8476805200 | 8184829304 | 2090 Fern Lane | Glendale, Ca 91208 | Tran, Danglong | 46117.4 | 0 | 0 | 0 | 2026-02-20 | Modify Tunnel Lighting Systems. | Los Angeles County In La Canada Flintridgeat E2-W210 Connector Undercrossing And At Foothill La Canada Tunnel | 19 | 5 | 398132.75 | 7717103.4 | 7717103.4 | 56494 | 2026-12-16 | 2024-10-03 | 2024-08-13 |  |  | 49 | 0 | 255 | 0 |  | X
07 | 07-348204 | 348204 | 07-LA-210-19.4/27 |  | ACIM-2101- (858)E | Bosco Constructors Inc. | 21353 Mayall St. | Chatsworth Ca 91311 | 8187000304 | 8184829304 | 2090 Fern Ln | Glendale, Ca 91208 | Tran, Danglong | 118122 | 0 | 0 | 0 | 2026-02-20 | Restore Bridge And Drainage System, And Co | Los Angeles County In La Canada Flintridgeand Pasadena At Various Locations From 0.1Mile East Of Winery Canyon Flume Overcrossing | 20 | 28 | 2720553.2 | 9556359.5 | 9656359.5 | 58075 | 2028-03-21 | 2025-05-09 | 2025-03-17 |  |  | 130 | 0 | 650 | 0 |  | X
07 | 07-301704 | 301704 | 07-LA-210-33.6/36.5 | HA42 | ACNH-X037- (227)E | Griffith Company | 3050 East Birch Street | Brea Ca 92821 | 7149845500 | 6265726732 | 1201 Baldwin Park Blvd | Baldwin Park, Ca 91706 | Chaudhari, Sushil | 3000 | 0 | 0 | 0 | 2026-02-20 | Stabilize Soil And Erosion Control. | On Rte 210 From 0.1 Mile West Of South Magnolia Ave Uc To 0.1 Mile East Of Rte 210/605 Sep And Rte 605 From 0.1 Mile South To 0.2 | 0 | 0 | 2965410.74 | 3081915.2 | 3514069.99 | 42353 | 2027-10-06 | 2022-04-20 | 2022-03-22 |  |  | 593 | 0 | 1000 | 0 | X | X
07 | 07-356104 | 356104 | 07-LA-210-37.8/39.1 |  |  | Doja Inc | 5050 Mission Blvd | Ontario Ca 92761 | 9096281999 | 5622547785 | 1041 W Badillo St #112 | Covina Ca 91722 | Barbosa, Jose | 221519.8 | 0 | 0 | 84769.39 | 2025-08-20 | Replace Pump Plant, Drainage, & Electrical | Los Angeles County In Azusa From 0.1 Mile West Of Irwindale Avenue To 0.2 Mile East Of West Vernon Avenue | 34 | 15 | 1015193.46 | 6900000 | 6960198.8 | 56495 | 2026-04-23 | 2024-10-01 | 2024-08-27 |  |  | 85 | 0 | 250 | 0 |  | X
07 | 07-2XQ604 | 2XQ604 | 07-LA-210-/0 | 20.XX 201130 |  | Diverscape Inc Dba Diversifiedlandscape Co | 21730 Bundy Canyon Rd | Wildomar, Ca 92595 | 9512451686 | 8058577053 | 13171 Telfair Avenue Suite 101 | Sylmar, Ca 91342 | Chavez, Efraim | 0 | 66815.12 | 0 | 0 | 2026-02-20 | Remove Hazardous Fallen Trees | In La County On Various Routes Across Multiple Cities To Remove Hazardous Trees That Have Fallen As A Result Of High Windsdir'S Em | 65 | 49 | 386181.42 | 3564 | 789000 | 59935 | 2026-03-30 | 2025-07-10 | 2025-03-07 |  |  | 39 | 0 | 60 | 0 |  | X
07 | 07-4V1404 | 4V1404 | 07-LA-213-6.2/6.2 | HB4N |  | Crosstown Electrical And Data, Inc. | 5454 Diaz Street | Irwindale Ca 91706 | 6268136693 | 5623453134 | 13230 Firestone Blvd.,Ste E-2 | Santa Fe Springs, Ca 90670 | Turay, Sulaiman | 0 | 0 | 0 | 0 |  | Install Traffic Signal And Ada | Intersection Of Western Ave (Sr-213) And 242Nd Place In The City Of La | 0 | 0 | 0 | 623377 | 623377 | 41568 | 2026-05-18 | 2021-04-08 | 2021-03-18 |  | S | 0 | 0 | 60 | 0
07 | 07-4V2304 | 4V2304 | 07-LA-213-6.4/0 |  |  | Ptm General Engineering Services Inc. | 5942 Acorn St. | Riverside Ca 92504 |  | 5623453142 | 13230 Firestone Blvd | Santa Fe Springs, Ca 90670 | Arikat, Ata | 0 | 0 | 0 | 0 |  | Modifying Signal And Lighting Systems. | Los Angeles County In Los Angeles At 238Thstreet | 0 | 0 | 0 | 624024 | 624024 | 56133 | 2026-08-05 | 2024-07-26 | 2024-06-28 |  |  | 0 | 0 | 120 | 0
07 | 07-338704 | 338704 | 07-LA-405-12.9/21.5 | HB34 | ACIM-4053- (013)000 | Martinez Landscape Co., Inc. | 12357 San Fernando Road | Sylmar Ca Ca |  | 2137922518 | 970 W 190Th Street, Suite 270 | Torrance, Ca 90502 | Gallardo, Samuel | 5500 | 0 | 0 | 0 | 2025-11-20 | Construct Rock Blanket And Remove/Install | Los Angeles County At Various Locations From 405/110 Separation Pm 12.9 To North Of 405/105 Separation Pm R21.5 | 99 | 90 | 2702951.59 | 2967990.7 | 3003990.7 | 47384 | 2025-12-31 | 2023-03-08 | 2023-02-07 | 2026-01-26 |  | 405 | 0 | 410 | 0 |  | X
07 | 07-350704 | 350704 | 07-LA-405-19.2/26 |  |  | Parsons Transportation Group, Inc. | 19900 Macarthur Blvd. Ste 850 | Irvine Ca 92612 | 9499334645 | 8182547484 | 13230 Firestone Blvd | Santa Fe Springs, Ca 90670 | Karout, Ali | 365086.36 | 0 | 0 | 0 | 2026-02-20 | New Active Traffic Management (Atm) & Traf | Los Angeles County At Various Routes And Various Locations | 4 | 1 | 453300.34 | 32200000 | 32200000 | 60127 | 2028-02-04 | 2025-06-26 | 2025-06-25 |  |  | 22 | 0 | 515 | 0 |  | X
07 | 07-347904 | 347904 | 07-LA-405-31.2/41.4 |  | ACIM-4053- (853)E | Rasmussen/Vanguard | 28548 Livingston Avenue | Valencia Ca 91335 |  | 2139526068 | 601 S Gleanoaks Blvd | Burbank Ca 91502 | Salman Ridwan | 2963268.6 | 0 | 0 | 0 | 2026-02-20 | Cold Plane, Place Hma, Rhma, & Jpcp, Isr, | Los Angeles From Wilshire Boulevard Undercrossing To Victory Boulevard Undercrossing | 23 | 34 | 36064896.12 | 103932363 | 104528335.4 | 57415 | 2027-12-11 | 2025-03-27 | 2025-03-07 |  |  | 188 | 0 | 810 | 0 |  | X
07 | 07-2XM804 | 2XM804 | 07-LA-405-36.3/37.1 | 20.XX 201130 |  | C A Rasmussen Inc | 28548 Livingston Ave | Valencia, Ca 91355 | 6613679040 | 8186130956 | 23369 Leonora Dr. | Woodland Hills, Ca 91367 | Gurfinkel, Vladimir | 0 | 107814.06 | 0 | 0 | 2024-08-20 | Repair Sinkhole Damage | La County, City Of La @ N/B & S/B 405 Off-Ramp Skirball Ctr Drive& Sepulveda On-Ramprepair Sinkhole, Drainage,Slope Paving Dir'S E | 60 | 99 | 922850.33 | 3849 | 929300 | 55614 | 2025-12-31 | 2024-03-29 | 2024-02-13 |  |  | 36 | 0 | 60 | 0 |  | X
07 | 07-320204 | 320204 | 07-LA-405-40.1/48.1 | HA42 | ACIM-4053- (001)E | Martinez Landscape Co., Inc | 12357 San Fernando Road | Sylmar Ca 91342 | 8183649188 | 5625725983 | 9225 Cranford Ave. | Pacoima, Ca 91331 | Bui, Kevin | 0 | 48065.64 | 0 | 0 | 2026-02-20 | Storm Water Source Control | In Los Angeles County In Los Angeles From 0.2 Mile South Of Burbank Boulevard Overcrossing To 0.3 Mile North Of Rinaldi Street Un | 0 | 0 | 2585060.87 | 2828911 | 2923528 | 42189 | 2026-08-31 | 2022-03-10 | 2022-01-31 |  |  | 490 | 0 | 1000 | 0 | X | X
07 | 07-353204 | 353204 | 07-LA-405-/12.8 |  | ACIM-4053- (990)E | Powell Constructors, Inc. | 8555 Banana Avenue | Fontana Ca 92335 | 9093568880 | 3102618467 | 18000 Studebaker Rd Suite 360 | Cerritos, Ca 90703 | Ton, Thang | 0 | 0 | 0 | 0 |  | Cold Plane Ac Pavement, Place Hma And Conc | Los Angeles County On Route 405 And At Various Locations From Orange County Line To Route 405/110 Separation | 0 | 0 | 0 | 100915340.5 | 100915340.5 | 60406 | 2030-08-14 | 2026-02-11 | 2026-01-22 |  |  | 0 | 0 | 1000 | 0
07 | 07-356604 | 356604 | 07-LA-605-10.2/20.2 | HA22 | ACIM-6052- (088)E | Myers & Sons Construction, Llc | 5777 W Century Blvd., Ste. 60 | Los Angeles, Ca 90045 | 9169381991 | 5623453125 | 13230 Firestone Blvd. | Santa Fe Springs, Ca 90670 | Arabe, Jerome | 4756627.66 | 354827 | 0 | 0 | 2026-02-20 | Lane & Slab Replacement, Cold Plane And Hm | Los Angeles County In Santa Fe Springs, Pico Rivera, Whittier, City Of Industry And El Monte From Telegraph Road Undercrossing To | 14 | 35 | 58097863.29 | 161382241 | 166423580.24 | 55727 | 2031-11-18 | 2024-04-30 | 2024-04-04 |  |  | 239 | 0 | 1670 | 0 |  | X
07 | 07-3255U4 | 3255U4 | 07-LA-605-20.2/26 | HA22 | ACIM-6052- (007)E | Peterson-Chase General Engineering Construction, Inc. | 16351 Construction Circle Wes | Irvine Ca 92606 | 9492520441 | 213798535 | 4281 Katella Ave Ste 221 | Los Alamitos,Ca 90720 | Lee, Peter | 331194.6 | 117962.05 | 0 | 0 | 2026-02-20 | Individual Slab Replacement, Cold Plane Ac | Los Angeles County In Baldwin Park And Irwindale From Route 10/605 Separation To 0.2 Mile North Of Route 210/605 Separation | 66 | 92 | 17092449.21 | 16259458.5 | 17922610.47 | 49304 | 2026-11-02 | 2023-05-12 | 2023-04-12 |  |  | 496 | 0 | 750 | 0 |  | X
07 | 07-345104 | 345104 | 07-LA-710-5.0/9.5 |  | ACIM-7101- (844)E | Alfaro Communications Construction, Inc. | 15614 S. Atlantic Avenue | Compton Ca 90221 | 3106698949 | 5623453144 | 13230 Firestone Blvd., Ste. E2 | Santa Fe Springs, Ca 90670 | Wang, Paul | 209263.56 | 0 | 0 | 0 | 2026-02-20 | Modifying Fiber Optic Cable Systems. | Los Angeles County In And Near Long Beach From 1 Mile South Of Pico Avenue On-Ramp Overhead To 0.1 Mile North Of Route 405/710 Sep | 53 | 91 | 10495255.08 | 11007496.62 | 11496024.57 | 56199 | 2026-09-16 | 2024-08-06 | 2024-07-11 |  |  | 305 | 0 | 575 | 0 |  | X
07 | 07-349904 | 349904 | 07-LA-710-6.0/14.1 |  | ACIM-7101- (845)E | Westcoast Public Works, Inc. | 20058 Ventura Blvd, #318 | Woodland Hills Ca 91364 | 8189684444 | 2138193025 | 18000 Studebaker Rd. Ste. 360 | Cerritos, Ca 90703 | Townsend, Jeffrey | 269504.93 | 10783.15 | 0 | 0 | 2026-02-20 | Construct Mvps, Mgs, Rock Blankets,And Pav | Los Angeles County In Long Beach And Comptom From Shoreline Drive To 0.2 Mile North Of Alondra Boulevard Overcrossing | 45 | 79 | 4720561.03 | 5377816.92 | 5675320.5 | 56686 | 2027-06-21 | 2024-11-22 | 2024-09-12 |  |  | 268 | 0 | 600 | 0 |  | X
07 | 07-4V4204 | 4V4204 | 07-LA-710-6.2/7.2 | HA25 |  | Accu Construction, Inc. | 14751 Plaza Drive Suite L | Tustin Ca 92780 | 7146414730 | 5623459894 | 13230 Firestone Blvd. | Santa Fe Springs, Ca 90670 | Martinez, Francisco | 4005 | 0 | 0 | 0 | 2025-12-20 | Planting Restoration. | Los Angeles County In Long Beach From Shoemaker Bridge To 0.3 Mile North Of Route 1/710 Separation | 79 | 84 | 823949.11 | 695920 | 980699.84 | 50886 | 2027-05-03 | 2023-07-05 | 2023-06-19 |  |  | 142 | 0 | 930 | 0 |  | X
07 | 07-347004 | 347004 | 07-LA-710-9.6/T32.1 | HA22 |  | Doja Inc | 5050 Mission Blvd | Ontario Ca 92761 | 9096281999 | 8054314352 | 13230 South Firestone Blvd #A | Santa Fe Springs, Ca 90670 | Robillos, Ramon | 299702.8 | 0 | 0 | 0 | 2026-02-20 | Drainage System Restoration. | Los Angeles County In Long Beach And Pasadena At Various Locations | 76 | 51 | 2708413.48 | 5300000 | 5314900 | 54024 | 2026-03-31 | 2023-11-01 | 2023-09-28 |  |  | 137 | 0 | 180 | 0
07 | 07-385804 | 385804 | 07-LA-710-13.8/15.3 |  |  | West Coast Public Works, Inc. | 20058 Ventura Blvd, #318 | Woodland Hills Ca 91364 |  | 3103455704 | 13230 South Firestone Blvd A | Santa Fe Springs, Ca 90670 | Nguyen, Khanh-Van | 0 | 0 | 0 | 0 | 2025-09-20 | Place Planting And Install Irrigation Syst | Los Angeles County In Compton And Paramount From 0.2 Mile South Of Alondra Boulevard Overcrossing To 0.4 Mile North Of Rosecrans A | 0 | 0 | 2876178.54 | 2987753 | 3008753 | 52905 | 2027-07-19 | 2023-09-28 | 2023-07-14 |  |  | 190 | 0 | 930 | 0 | X | X
07 | 07-390804 | 390804 | 07-LA-710-19.6/19.9 |  |  | Calpromax Engineering, Inc. | 650 N. Rose Dr. #186 | Placentia Ca 92870 |  |  |  |  | Oregel, Martin | 87502.5 | 0 | 0 | 0 | 2026-02-20 | Construct Ada Curb Ramps And Install Flash | Los Angeles County In City Of Bell From 0.1 Mile South Of Florence Avenue Overcrossing To 0.2 Mile North Of Florenceavenue Overcro | 30 | 25 | 390438.75 | 1520057.9 | 1585057.9 | 59297 | 2026-07-29 | 2025-07-08 | 2025-06-06 |  |  | 45 | 0 | 150 | 0 |  | X
07 | 07-354704 | 354704 | 07-LA-710-22.0/0 |  | BFIM-7101- (846)E | Certified Coatings Company | 2320 Cordelia Rd | Fairfield Ca 94534 |  | 2134076627 | 4281 Katella Ave. #221 | Los Alamitos, Ca 90720 | Oregel, Martin | 470306.63 | 0 | 0 | 0 | 2026-02-20 | Clean And Paint Bridge. | Los Angeles County In Commerce And Vernon At Hobart Yard Overhead And At Atlantic Boulevard And Bandini Boulevard On-Ramp | 36 | 45 | 5725351.94 | 10336185 | 12766086.77 | 57299 | 2027-07-16 | 2025-03-06 | 2025-02-06 |  |  | 192 | 0 | 540 | 0 |  | X
07 | 07-331804 | 331804 | 07-LA-710-26.0/26.7 | HA42 | ACIM-X037- (229)E | Griffith Company | 3050 East Birch Street | Brea, Ca 92821 | 7149840228 | 5625725031 | 4281 Katella Ave Ste 221 | Los Alamitos, Ca 90720 | Vergara, Joahnna | 6360 | 0 | 87093.3 | 0 | 2026-02-20 | Install Irrigation Systems, Erosion | In Los Angeles County In And Near Monterey Park On Rte 10 From 0.1 Mile East Of North Eastern Ave To 0.2 Mile West Of South Garvey | 75 | 98 | 2644506.43 | 2646751.18 | 2830478.83 | 45566 | 2026-08-18 | 2022-11-18 | 2022-09-26 |  |  | 750 | 0 | 1000 | 0 |  | X
07 | 07-354804 | 354804 | 07-LA-5808-/2.5 | HA12 |  | Mercer Fraser Company | 28548 Livingston Ave | Valencia, Ca 91355 | 6613679040 | 8184829191 | 12975 W Culver Blvd. | Los Angeles, Ca 90066 | Sheik, Hakim | 242645.75 | 0 | 0 | 0 | 2026-02-20 | Building Work. | Los Angeles County In Culver City At The Culver City Maintenance Station At 5650 Selmaraine Drive | 100 | 35 | 3230865.45 | 8895895 | 9345895 | 55803 | 2026-06-12 | 2024-05-13 | 2024-04-03 |  |  | 277 | 0 | 210 | 19
07 | 07-358204 | 358204 | 07-LA-5823-/7.2 | HA12 |  | Mercer Fraser Company | 200 Dinsmore Dr | Fortuna Ca 95540 | 7074436371 | 2138193025 | 18000 Studebaker Rd. Suite 360 | Cerritos, Ca 90703 | Townsend, Jeffrey | 264000 | 0 | 0 | 0 | 2026-02-20 | Provide Building Work At A Maintenance Sta | Los Angeles County In Long Beach At The Pacific Place Maintenance Station At North3725 Pacific Place | 100 | 74 | 3865750 | 4965380 | 5238580.41 | 55790 | 2026-06-30 | 2024-05-13 | 2024-03-29 |  |  | 356 | 0 | 260 | 0
07 | 07-322704 | 322704 | 07-VAR-1-1.3/26.6 | HA42 | ACNH-X111- (080)E | Autobahn Construction Inc. | 933 N. Batavia St. | Orange Ca 92867 |  | 2133306650 | 1525 Rancho Conejo Blvd #102 | Thousand Oaks, Ca 91320 | Singh, Ranjit | 27417.5 | 0 | 0 | 0 | 2026-02-20 | Construct Pervious Concrete Pavement And D | Ventura County At Various Locations | 89 | 95 | 4747590.85 | 5179766 | 5017330.75 | 47264 | 2026-07-31 | 2023-03-03 | 2023-01-31 |  |  | 542 | 0 | 610 | 0 |  | X
07 | 07-0W8804 | 0W8804 | 07-VAR-1-23.1/23.1 | HM4 |  | Bc Rentals Llc Dba Bc Traffic Specialist | 13261 Garden Grove Blvd | Garden Grove Ca 92843 | 9519075163 | 3106090364 | 1201 Baldwin Park Blvd. | Baldwin Park, Ca 91706 | Herrera, Edgar | 1400 | 0 | 0 | 0 | 2025-06-20 | Upgrade Existing Basic Crosswalks To Ladde | Los Angeles County At Various Locations | 60 | 98 | 681968.18 | 489485 | 685411.18 | 55791 | 2026-03-13 | 2024-05-13 | 2024-04-15 |  |  | 54 | 0 | 90 | 0 |  | X
07 | 07-348804 | 348804 | 07-VAR-2-18.7/18.7 | HB4N | ACNH-000C- (555)E | Alfaro Communications Construction, Inc. | 15614 S. Atlantic Avenue | Compton Ca 90221 | 3106698949 | 2137937340 | 13171 Telfair Ave.#101 | Sylmar, Ca 91342 | Hossain, Muhammad | 660854.96 | 1875.48 | 0 | 0 | 2025-10-20 | Cameras Systems. | Los Angeles County And Ventura County At Various Locations | 48 | 82 | 4334019.97 | 5048024.52 | 5721024.52 | 55551 | 2026-11-13 | 2024-03-27 | 2024-02-28 |  |  | 240 | 0 | 500 | 0 |  | X
07 | 07-0W6104 | 0W6104 | 07-VAR-5-/40 | HM4 |  | Traffic Loops Crackfilling, Inc. | 946 S. Emerald Street | Anaheim Ca 92804 | 7145204026 | 2137937193 | 1041 W Badillo, Ste 112 | Covina, Ca 91722 | Pham,Ryan | 0 | 0 | 0 | 0 | 2024-11-20 | Repair Traffic Monitoring Detection Statio | Los Angeles County At Various Locations | 80 | 22 | 257255 | 1176020 | 1176020 | 53184 | 2026-03-24 | 2023-10-12 | 2023-05-31 |  |  | 88 | 0 | 110 | 0
07 | 07-346204 | 346204 | 07-VAR-23-3.6/11.4 | HA22 | ACNH-000C- (556)E | Select Electric, Inc. | 2790 Business Park Drive | Vista Ca 92081 | 5629390418 | 2137008447 | 1525 Rancho Conejo Blvd. | Thousand Oaks, Ca 91320 | Tehrani, Joseph Solaiman | 1194032.02 | 146796.87 | 0 | 0 | 2026-02-20 | Upgrade And Install New Transportation Man | Los Angeles And Ventura Counties At Various Locations | 100 | 84 | 9655249.21 | 10106415 | 11348918.4 | 56008 | 2026-06-20 | 2024-06-20 | 2024-04-10 |  |  | 300 | 0 | 300 | 0
07 | 07-338604 | 338604 | 07-VAR-91-6.1/20.7 | HB4N | ACNH-X037- (231)E | Alfaro Communications Construction, Inc. | 15614 S. Atlantic Avenue | Compton Ca 90221 | 3106698949 | 5623453145 | 13230 Firestone Blvd., Ste.E-2 | Santa Fe Springs, Ca 90670 | Alonzo, Bernard | 118744 | 0 | 0 | 0 | 2026-02-20 | Modifying Ramp Metering, Fiber Optic Cable | Los Angeles County At Various Locations | 54 | 94 | 12729653.25 | 12972892.52 | 13538880.26 | 55464 | 2026-06-22 | 2024-03-04 | 2024-01-22 |  |  | 339 | 0 | 630 | 0 |  | X
07 | 07-355104 | 355104 | 07-VAR-105-2.1/2.1 | HA22 | ACIM-X037- (233)E | Aldridge Electric, Inc. | 1000 E Santa Ana Blvd Ste 300 | Santa Ana, Ca 92701 | 8472573670 | 8182547484 | 13230 Firestone Blvd Suite | Santa Fe Springs, Ca 90670 | Karout, Ali | 233248.96 | 167810.38 | 0 | 0 | 2025-11-20 | Upgrade Tunnel Lighting Systems And Instal | Los Angeles County At Various Locations | 54 | 94 | 18543627.49 | 19249130.5 | 19731022.16 | 55704 | 2026-08-05 | 2024-04-29 | 2024-03-07 |  |  | 206 | 0 | 380 | 0 |  | X
07 | 07-0W5904 | 0W5904 | 07-VAR-110-15.1/23 | HM4 |  | Bc Rentals Llc Dba Bc Traffic Specialist | 13261 Garden Grove Blvd | Garden Grove Ca 92843 |  | 8186130956 | 23369 Leonora Dr | Woodland Hills, Ca 91367 | Gurfinkel, Vladimir | 0 | 7000 | 7656.64 | 0 | 2025-11-20 | Install Traffic Stripe, Pavement Marking, | Los Angeles And Ventura Counties At Various Locations | 100 | 93 | 898237.62 | 952176 | 1028549.33 | 52084 | 2026-01-31 | 2023-08-18 | 2023-05-25 |  |  | 103 | 0 | 60 | 0 |  | X
07 | 07-349504 | 349504 | 07-VAR-170-14.5/20.5 | HB4N | ACNH-P170- (008)E | Alfaro Communications Construction, Inc. | 15614 S. Atlantic Avenue | Compton Ca 90221 |  | 5625725983 | 9225 Cranford Ave | Pacoima Ca 91331 | Bui, Kevin | 92002.04 | 13837.02 | 0 | 0 | 2026-02-20 | Install New Transportation Management Syst | Los Angeles County In Los Angeles From Route 134/170 Separation To Route 170/5 Separation | 49 | 94 | 9655492.12 | 9214672.88 | 10123232.82 | 55553 | 2026-08-21 | 2024-03-27 | 2024-02-29 |  |  | 254 | 0 | 522 | 0 |  | X
07 | 07-349104 | 349104 | 07-VAR-210-43.9/46.7 | HB4N |  | International Line Builders, Inc. | 3955 Temescal Canyon Road | Corona Ca 92883 | 9513828189 | 2137937193 | 21073 Pathfinder Rd Ste 100 | Diamond Bar, Ca 91765 | Pham, Ryan | 17621.07 | 0 | 0 | 0 | 2026-02-20 | Upgrade The Existing Communication System. | Los Angeles County At Various Locations | 94 | 78 | 2752225.7 | 3538423 | 3558423 | 55552 | 2026-03-12 | 2024-03-27 | 2024-02-21 |  |  | 236 | 0 | 250 | 0
07 | 07-351124 | 351124 | 07-VAR--/0 |  |  | Select Electric, Inc. | 1700 E. Via Burton | Anaheim Ca 92806 |  | 2133082033 |  |  | Pham, Ryan | 1363318.52 | 0 | 0 | 13646.2 | 2026-02-20 | Install And Replace Cctv Camera Systems. | Los Angeles County At Various Locations | 30 | 64 | 3242233.62 | 4998035 | 5086593.8 | 57195 | 2026-09-01 | 2025-02-18 | 2024-12-24 |  |  | 165 | 0 | 550 | 0 |  | X
07 | 07-374304 | 374304 | 07-VAR--/0 |  | ACNH-X037- (245)E | Peterson-Chase General Engineering Construction, Inc. | 16351 Construction Circle Wes | Irvine Ca 92606 |  |  |  |  | Liu, Chen | 0 | 0 | 0 | 0 |  | Modify Overhead And Roadside Sign Panels. | Los Angeles County At Various Locations | 0 | 0 | 0 | 7549361.5 | 7549361.5 | 60390 |  | 2026-02-04 | 2026-01-08 |  |  | 0 | 0 | 600 | 0
07 | 07-0Y2004 | 0Y2004 | 07-VAR--/0 |  |  | Autobahn Construction, Inc. | 933 N. Batavia St. | Orange Ca 92867 | 7147697025 | 3103456188 | 970 W 190Th Ste 270 | Torrance, Ca 90502 | Gallardo, Samuel | 27607.5 | 0 | 0 | 0 | 2025-12-20 | Wrong Way Driver Preventive Counter Measur | Los Angeles County At Various Locations | 79 | 98 | 501075.5 | 494126 | 494126 | 59516 | 2026-02-28 | 2025-07-23 | 2025-06-24 |  |  | 59 | 0 | 75 | 0 |  | X
07 | 07-301604 | 301604 | 07-VAR--/0 |  | BFNH-X037- (236)E | Powell Constructors Inc | 8555 Banana Avenue | Fontana Ca 92335 | 9093568880 | 5623459865 | 13320 S Firestone Blvd, Ste A | Santa Fe Springs, Ca 90670 | Robillos, Ramon | 240276.5 | 0 | 0 | 0 | 2026-02-20 | Install Fiber Reinforced Polymer System (C | Los Angeles County At Various Locations | 69 | 39 | 5635859.02 | 13964693 | 14335221.91 | 56272 | 2026-09-30 | 2024-08-23 | 2024-07-31 |  |  | 274 | 0 | 400 | 0 |  | X
07 | 07-353804 | 353804 | 07-VAR--/0 |  | ACIM-0053- (110)E | Crosstown Electrical & Data, Inc. | 5454 Diaz Street | Irwindale Ca 91706 |  | 8183642760 | 13171 Telfair Ave,Ste101 | Sylmar Ca 91342 | Chavez, Efraim | 898792.3 | 0 | 0 | 0 | 2026-02-20 | Modify Fiber Optic Cable Systems, Lighting | Los Angeles County At Various Locations | 63 | 71 | 12552168.78 | 17468150.6 | 17726596.03 | 56575 | 2026-06-26 | 2024-10-16 | 2024-09-10 |  |  | 189 | 0 | 300 | 0 |  | X
07 | 07-0Y0904 | 0Y0904 | 07-VAR--/0 |  |  | Jabre Contracting, Inc. | 1813 Manzanita Lane | Manhattan Beach Ca 90266 |  | 8187460669 | 13171 Telfair Ave Ste 101 | Sylmar Ca 91342 | Mohsenzadeh Ali | 63325.1 | 0 | 0 | 0 | 2026-02-20 | Cleaning, Repair And Retrofit Of Culverts. | Los Angeles County At Various Locations | 98 | 95 | 663091.2 | 866260 | 664848 | 59197 | 2026-02-24 | 2025-06-25 | 2025-05-30 |  | S | 78 | 0 | 80 | 0 |  | X
07 | 07-0W9804 | 0W9804 | 07-VAR--/0 |  |  | Myers & Sons Construction, Llc | 45 Morrison Ave | Sacramento Ca 95838 | 91683950 | 2136053208 | 1525 Rancho Conejo Blvd Ste102 | Thousand Oaks, Ca 91302 | Saeidian Justin | 1342417.74 | 4069.62 | 0 | 0 | 2026-02-20 | Treat Bridge Deck, Repair Joint Seals, And | Ventura County At Various Locations | 49 | 79 | 5613481.05 | 6828826 | 6999847.31 | 59215 | 2026-07-29 | 2025-06-26 | 2025-06-10 |  |  | 113 | 0 | 230 | 0 |  | X
07 | 07-0W6504 | 0W6504 | 07-VAR--/0 |  |  | Peterson-Chase General Engineering Construction, Inc. | 16351 Construction Circle Wes | Irvine Ca 92606 | 9492520441 | 5625725852 | 12975 Culver Blvd | Los Angeles, Ca 90066 | Martinez, Elizabeth | 96009.5 | 0 | 0 | 0 | 2025-12-20 | Structural Conc, Approach Slab, Polyester | Los Angeles County At Various Locations | 99 | 99 | 3726964.02 | 3581539.6 | 3651539.6 | 56132 | 2026-01-20 | 2024-07-24 | 2024-06-27 |  |  | 178 | 0 | 180 | 0 |  | X
07 | 07-0W7704 | 0W7704 | 07-VAR--/0 |  |  | Lamassu Utility Services, Inc. | 3193 Enterprise Court | Loomis Ca 95650 | 9162591576 | 2137008447 | 1525 Rancho Conejo Blvd Ste102 | Thousand Oaks Ca 91302 | Tehrani, Joseph Solaiman | 0 | 70047.56 | 0 | 0 | 2025-12-20 | Culvert Lining. | Ventura County At Various Locations | 100 | 86 | 538243.39 | 383032.72 | 610532.72 | 56074 | 2026-02-20 | 2024-07-12 | 2024-06-14 |  |  | 73 | 0 | 70 | 0 |  | X
07 | 07-350334 | 350334 | 07-VAR--/0 |  | ACNH-X037- (238)E | Crosstown Electrical & Data, Inc. | 5454 Diaz Street | Irwindale Ca 91706 | 6267036532 | 5625725031 | 1370 Valley Vista Dr Ste 150C | Diamond Bar, Ca 91765 | Ferrer, Jose | 8750 | 0 | 0 | 0 | 2026-02-20 | Install Changeable Message Signs, And Traf | Los Angeles County At Various Locations | 18 | 3 | 499998 | 16365395 | 16415395 | 58135 | 2027-10-13 | 2025-05-13 | 2025-03-17 |  |  | 89 | 0 | 500 | 0 |  | X
07 | 07-0W9704 | 0W9704 | 07-VAR--/0 |  |  | J. Francis Company | 16197 Krameria Ave. | Riverside Ca 92504 | 9517769100 | 9512323742 | 1041 W Badillo St Ste 112 | Covina, Ca 91722 | Hong, Hai | 565848.5 | 0 | 0 | 0 | 2026-02-20 | Methacrylate, Polyester Overlay, Joint Sea | Los Angeles County At Various Locations | 52 | 57 | 3605670.98 | 6197847.1 | 6217847.1 | 59055 | 2026-07-02 | 2025-06-19 | 2025-06-02 |  |  | 98 | 0 | 190 | 0 |  | X
07 | 07-350314 | 350314 | 07-VAR--/0 |  | ACNH-000C- (563)E | Crosstown Electrical & Data, Inc. | 5454 Diaz Street | Irwindale Ca 91706 |  |  | 13171 Telfair Ave | Sylmar, Ca 91342 | Hossain, Muhammad Ismail | 802082.11 | 0 | 0 | 0 | 2026-02-20 | Install Changeable Message Signs, And Fibe | Los Angeles And Ventura Counties At Various Locations | 16 | 12 | 2453241.26 | 20349394 | 20379394 | 57755 | 2027-08-30 | 2025-04-15 | 2025-03-20 |  |  | 119 | 0 | 750 | 0 |  | X
07 | 07-351114 | 351114 | 07-VAR--/0 |  |  | Calpromax Engineering, Inc. | 650 N. Rose Dr. #186 | Placentia Ca 92870 | 7145734599 | 5623453145 | 13230 Firestone Blvd. Ste E-2 | Sante Fe Springs, Ca 90670 | Alonzo, Bernard | 79800 | 11024.66 | 0 | 0 | 2026-02-20 | Install And Upgrade Camera Systems. | Los Angeles County At Various Locations | 37 | 22 | 1228184.66 | 5358200 | 5519224.66 | 56585 | 2026-10-05 | 2024-10-29 | 2024-10-04 |  |  | 112 | 0 | 300 | 0 |  | X
07 | 07-0W6604 | 0W6604 | 07-VAR--/0 |  |  | Velarde Concrete Construction | 523 S. Brand Blvd., Ste. #201 | San Fernando Ca 91340 |  | 2133939751 | 4281 Katella Ave Suite 221 | Los Alamitos, Ca 90720 | Vergara, Joahnna | 177607.9 | 0 | 0 | 0 | 2026-02-20 | Methacrylate, Polyester Overlay And Joint | Los Angeles County At Various Locations | 74 | 83 | 8028269.56 | 9475294.9 | 9594948.7 | 56078 | 2026-05-22 | 2024-07-15 | 2024-06-26 |  |  | 200 | 0 | 270 | 0 |  | X
07 | 07-350404 | 350404 | 07-VAR--/0 |  |  | Alfaro Communications Construction, Inc. | 15614 S. Atlantic Avenue | Compton Ca 90221 |  | 5623453144 |  |  | Wang, Paul | 315563.76 | 0 | 0 | 0 | 2026-02-20 | Modifying Fiber Optic Cable Systems. | Los Angeles County At Various Locations | 36 | 84 | 3716753.28 | 3769131.07 | 4439470.34 | 57298 | 2026-12-23 | 2025-03-06 | 2025-01-23 |  |  | 189 | 0 | 525 | 0 |  | X
07 | 07-0W9904 | 0W9904 | 07-VAR--/0 |  |  | Peterson-Chase General Engineering Construction, Inc. | 16351 Construction Circle Wes | Irvine Ca 92606 |  |  | 4281 Katella Ave Suite 221 | Los Alamitos Ca 90720 | Vergara Joahnna | 94010 | 0 | 0 | 0 | 2026-02-20 | Methacrylate, Polyester Overlay, Joint Sea | Los Angeles County At Various Locations | 57 | 96 | 2290410.36 | 2382274.8 | 2329113 | 59575 | 2026-03-30 | 2025-07-29 | 2025-06-16 |  |  | 103 | 0 | 180 | 0 |  | X
07 | 07-0Y1904 | 0Y1904 | 07-VAR--/0 |  |  | Specialized Pavement Marking, Llc | 11095 Sw Industrial Way Ste A | Tualatin Or 97062 | 5308850420 | 5625725983 | 9225 Cranford Ave | Pacoima, Ca 91331 | Bui, Kevin | 41378 | 4651.9 | 0 | 0 | 2026-02-20 | Striping. | Los Angeles County At Various Locations | 90 | 96 | 1342616.7 | 1330792.5 | 1365792.5 | 59317 | 2026-03-31 | 2025-07-08 | 2025-06-24 |  |  | 108 | 0 | 120 | 0 |  | X
07 | 07-350324 | 350324 | 07-VAR--/0 |  | ACNH-X037- (239)E | Jfl Electric, Inc. | 8257 Compton Avenue | Los Angeles Ca 90001 | 3235814400 | 5622545045 | 13230 Firestone Blvd Unit E2 | Santa Fe Springs Ca 90670 | Turay, Sulaiman | 0 | 0 | 0 | 0 |  | Replace Exsistiing Cms, Tcs, And Tmds/Vds, | Los Angeles County At Various Locations | 0 | 0 | 0 | 23414925 | 23414925 | 57778 | 2028-02-23 | 2025-04-15 | 2025-03-10 |  | S | 0 | 0 | 500 | 0
07 | 07-0W8904 | 0W8904 | 07-VAR--/0 |  |  | Polo Engineering, Inc. | 30758 Sloan Canyon Rd | Castaic Ca 91384 | 8184276324 | 2135055907 | 21073 Pathfinder Rd | Diamond Bar, Ca 91765 | Punjabi, Raj | 158242.81 | 0 | 0 | 26373.15 | 2026-02-20 | Install Advance Curve Warning Signs | Los Angeles County At Various Locations | 24 | 32 | 461511.98 | 1450412.78 | 1450412.78 | 59975 | 2026-07-28 | 2025-07-23 | 2025-04-11 |  |  | 35 | 0 | 145 | 0 |  | X
07 | 07-360604 | 360604 | 07-VAR--/0 |  |  | Truesdell Corporation Of California, Inc. | 1310 W. 23Rd Street | Tempe Az 85282 |  | 2134006110 | 9225 Cranford Ave | Pacoima Ca 91331 | Matevosyan,Nzhde | 0 | 0 | 0 | 0 |  | Remove And Place Approach Slabs, And Place | Los Angeles County In Los Angeles At Various Locations | 0 | 0 | 0 | 8642642 | 8642642 | 60310 | 2027-09-13 | 2026-01-12 | 2025-12-05 |  |  | 0 | 0 | 170 | 0
07 | 07-351504 | 351504 | 07-VAR--/0 |  |  | Powell Constructors, Inc. | 8555 Banana Avenue | Fontana Ca 92335 |  | 2139526068 | 601 S Glenoaks Blvd #310 | Burbank, Ca 91502 | Salman Ridwan | 362740.5 | 0 | 0 | 182500 | 2026-02-20 | Construct Bridge Rails, Guardrail, Oh Sign | Los Angeles County In Los Angeles At Various Locations | 35 | 16 | 1231959.1 | 7355032.35 | 7475032.35 | 57775 | 2026-12-31 | 2025-04-18 | 2025-03-26 |  |  | 84 | 0 | 240 | 0 |  | X
07 | 07-0Y1004 | 0Y1004 | 07-VAR--/0 |  |  | Jabre Contracting, Inc. | 1813 Manzanita Lane | Manhattan Beach Ca 90266 |  | 2137008447 | 1525 Rancho Conejo Blvd | Thousand Oaks, Ca 91320 | Tehrani, Joseph | 535808 | 0 | 0 | 22500 | 2026-02-20 | Cured-In-Place Pipeliner. | Ventura County At Various Locations | 100 | 95 | 841149.68 | 1173550 | 860780 | 59276 | 2026-07-29 | 2025-07-01 | 2025-05-27 |  |  | 60 | 0 | 60 | 0 |  | X
07 | 07-351704 | 351704 | 07-VAR--/0 |  | ACNH-X111- (081)E | C. A. Rasmussen, Inc. | 28548 Livingston Avenue | Valencia Ca 91355 | 6613679040 | 2137008447 | 1525 Rancho Conejo Blvd #102 | Thousand Oaks, Ca 91320 | Tehrani, Joseph Solaiman | 1360911.17 | 3637.71 | 0 | 270000 | 2026-02-20 | Cold Plane Ac Pavement And Place Rubberize | Ventura County In Moorpark At Various Locations | 37 | 30 | 4534044.5 | 15225552 | 15275552 | 57855 | 2027-03-29 | 2025-04-24 | 2025-03-25 |  |  | 161 | 0 | 440 | 0 |  | X
07 | 07-0Y0504 | 0Y0504 | 07-VAR--/0 |  |  | Baker Electric & Renewables, Llc | 1298 Pacific Oaks Place | Escondido Ca 92029 | 7607452001 | 8058577070 | 1525 Rancho Conejo Blvd Ste102 | Thousand Oaks, Ca 91320 | Ira, Alfred | 0 | 0 | 0 | 0 |  | Modify Traffic Signal, Roadside Signs And | Ventura County At Various Locations | 0 | 0 | 0 | 610318.66 | 610318.66 | 59675 | 2026-04-14 | 2025-08-13 | 2025-06-06 |  |  | 0 | 0 | 70 | 0
07 | 07-4P8504 | 4P8504 | 07-VEN-1-1.0/1.3 |  | SNHG-P001- (703)E | Polo Engineering, Inc. | 30758 Sloan Canyon Rd | Castaic Ca 91384 |  | 2133306650 | 1525 Rancho Conejo Blvd, #102 | Thousand Oaks, Ca 91320 | Singh, Ranjit | 58751.3 | 0 | 0 | 16250 | 2026-02-20 | Install Marked Crosswalk With Pedestrian H | Ventura County From 0.1 Mile South Of Yerba Buena Road To 0.1 Mile North Of Little Sycamore Creek Bridge | 19 | 21 | 148996.3 | 704550.5 | 719550.5 | 56867 | 2026-06-30 | 2024-12-17 | 2024-11-20 |  |  | 17 | 0 | 90 | 0 |  | X
07 | 07-318204 | 318204 | 07-VEN-1-4.0/4.2 | HA23 |  | Flatiron-Drill Tech A Joint Venture | 16470 West Bernardo Dr #120 | San Diego Ca 92127 | 9095978413 | 2137928141 | 1525 Rancho Conejo Blvd., #102 | Thousand Oks, Ca 91320 | Verma, Niketa | 10382.7 | 0 | 0 | 0 | 2025-11-21 | Construct Secant Walls, Slope | In Ventura County, South Of Point Mugu State Park And Sycamore Canyon Road | 100 | 100 | 53609580.42 | 42505506.3 | 53338043.44 | 41904 | 2025-11-21 | 2021-09-17 | 2021-09-15 | 2026-01-28 |  | 636 | 0 | 550 | 86 |  | X
07 | 07-319604 | 319604 | 07-VEN-1-21.3/21.9 |  | BFNH-X111- (082)000 | Beador Construction Company, Inc. | 2900 Bristol Street, Suite D2 | Costa Mesa Ca 92626 |  | 2133306650 | 1525 Rancho Conejo Blvd#102 | Thousand Oaks, Ca 91320 | Ranjit Singh | 339629 | 0 | 0 | 0 | 2026-02-20 | Remove And Construct Bridge. | The City And County Of Ventura On Route 1 From 1.8 Miles North Of Route 1/33 Separation To 2.0 Miles South Of A Lease Canyon Road | 9 | 1 | 545354 | 46620300 | 47020300 | 60123 | 2031-02-28 | 2025-10-13 | 2025-09-16 |  |  | 50 | 0 | 1300 | 0 |  | X
07 | 07-323904 | 323904 | 07-VEN-1-21.3/28.4 | HA22 |  | C. A. Rasmussen, Inc. | 28548 Livingston Avenue | Valencia Ca 91355 |  | 8058577070 | 1525 Rancho Conejo Blvd, 102 | Thousand Oaks, Ca 91320 | Ira, Alfred | 88950 | 0 | 0 | 0 | 2026-02-20 | Cold Plane Ac, Place Rubberized Hot Mix As | Ventura County Near Ventura From Route 1/101 Separation To Mobil Pier Road. | 100 | 81 | 6558023.56 | 7435330.4 | 7967421.18 | 48384 | 2026-04-23 | 2023-04-10 | 2023-03-27 |  |  | 624 | 0 | 580 | 0
07 | 07-2XE704 | 2XE704 | 07-VEN-23-17.7/24.1 | 20.20 201130 |  | Burns Pacific Construction Inc | 3541 Old Conejo Rd Ste 114 | Newbury Park, Ca 91320 |  | 2135077938 | 1525 Rancho Conejo Blvd Suite 102 | Thousand Oaks, Ca 91320 | Ira, Alfred | 0 | 118904.01 | 0 | 0 | 2026-02-20 | Repair Storm Damage | In Ventura County, City Of Fillmore Ven-23To Remove Mud/Debris,Fallen Trees,Drainagesystems & Repair Roadway Damage From Stormdir' | 100 | 99 | 3239672.26 | 9675 | 3260000 | 47986 | 2026-02-28 | 2023-03-24 | 2023-01-25 |  |  | 291 | 0 | 60 | 0 |  | X
07 | 07-348404 | 348404 | 07-VEN-23-/3.3 |  | ACST-P023- (042)E | Accu Construction, Inc. | 14751 Plaza Drive Suite L | Tustin Ca 92780 | 7146414730 | 2137008447 | 1525 Rancho Conejo Blvd #102 | Thousand Oaks, Ca 91302 | Tehrani, Joseph Solaiman | 26250 | 82648.6 | 0 | 0 | 2026-01-20 | Construct Design Pollution Prevention Infi | Ventura County In And Near Thousand Oaks And Moorpark At Various Locations From 0.1Mile North Of Sycamore Canyon Drive To Potrero | 100 | 96 | 1539246.6 | 1816005 | 1601185 | 56787 | 2026-06-30 | 2024-11-08 | 2024-10-22 |  |  | 194 | 0 | 430 | 0 |  | X
07 | 07-355204 | 355204 | 07-VEN-33-3.3/21.2 |  | ACNH-P033- (093)000 | Granite Construction Company | 4820 Mcgrath St., Suite 101 | Ventura Ca 93003 | 8317684020 | 2138170162 |  |  | Bakhet, Wassem | 109963.86 | 0 | 0 | 0 | 2026-02-20 | Roadway Excavation And Place Class 3 Aggre | Ventura County At Various Locations From 0.7 Mile North Of Shell Road Undercrossingto 3.5 Miles North Of Nordhoff Ridge Road | 54 | 80 | 605542.83 | 722722 | 753722 | 59875 | 2026-05-11 | 2025-08-13 | 2025-07-15 |  |  | 65 | 0 | 120 | 0 |  | X
07 | 07-332304 | 332304 | 07-VEN-33-18.9/19.1 |  | HSNH-P033- (092)E | Toro Enterprises, Inc. | 2101 E. Ventura Blvd. | Oxnard Ca 93036 | 8054834515 | 2137928141 | 1525 Rancho Conejo Blvd Ste102 | Thousand Oaks, Ca 91320 | Verma, Niketa | 64118.68 | 16405.99 | 0 | 0 | 2026-02-20 | Construct Structural Concrete Barrier Slab | Ventura County Near Ojai From 0.5 Mile South Of Bear Creek Bridge To 0.1 Mile North Of North Fork Matilija Creek Bridge | 79 | 91 | 3713862.55 | 3725967 | 4048373.24 | 57335 | 2026-02-28 | 2025-03-14 | 2025-02-21 |  |  | 119 | 0 | 150 | 0 |  | X
07 | 07-2XF604 | 2XF604 | 07-VEN-33-24.2/27.3 | 20.XX 201130 |  | Granite Construction Company | 4820 Mcgrath Ste #101 | Ventura, Ca 93003 |  | 2137008447 | 1525 Rancho Conejo Blvd. Suite 102 | Thousand Oaks, Ca 91320 | Tehrani, Joseph | 0 | 953542.56 | 0 | 0 | 2026-02-20 | Repair Storm Damage | In Ventura County In City Of Ojai Ven-33 To Repair Slopes/Shoulders,Dikes,Guardrailconstruct Spw Due To Storm Damage Dir'S Emergen | 100 | 93 | 26210530.58 | 41917 | 28050000 | 49065 | 2026-02-28 | 2023-04-11 | 2023-03-02 |  |  | 590 | 0 | 240 | 0 |  | X
07 | 07-356804 | 356804 | 07-VEN-33-26.9/41.7 |  | ACNH-X111- (083)000 | Accu Construction, Inc. | 14751 Plaza Drive Suite L | Tustin Ca 92780 | 7146414730 | 2137008447 | 1525 Rancho Conejo Blvd Ste102 | Thousand Oaks, Ca 91320 | Tehrani,Joseph | 51405 | 0 | 0 | 5000 | 2026-02-20 | Construct Treatment Bmps. | Ventura County At Various Locations On Route 33 From 1.1 Miles North Of Rose Valley Road To 1.0 Mile South Of Potrero Seco Road An | 9 | 15 | 98405 | 585248 | 635248 | 60015 | 2027-12-30 | 2025-09-04 | 2025-08-22 |  |  | 18 | 0 | 200 | 0 |  | X
07 | 07-2XF704 | 2XF704 | 07-VEN-33-44.2/57.2 | 20.XX 201130 |  | R&R Demo And Grading Corp | 21777 Ventura Blvd Suite 245 | Woodland Hills, Ca 91364 |  | 2137008447 | 1525 Rancho Conejo Blvd Suite 102 | Thousand Oaks, Ca 91320 | Tehrani, Joseph | 0 | 236170.77 | 0 | 0 | 2026-02-20 | Winter Storm Repairs | Ven County In City Of Ojai Route 33 To Repair Eroded Slopes, Rebuild Rsp, Rock Scaling And Clean Drainage Systems Dir'S Emergency | 100 | 92 | 12956329.27 | 78750 | 14080000 | 50404 | 2026-02-28 | 2023-05-31 | 2023-03-02 |  |  | 643 | 0 | 120 | 0 |  | X
07 | 07-3311U4 | 3311U4 | 07-VEN-101-.2/40.8 | HB1 | ACNH-X111- (079)E | Peterson-Chase General Engineering Construction, Inc. | 16351 Construction Cir W | Irvine Ca 92606 | 9492520441 | 8058577070 | 1525 Rancho Conejo Blvd Ste102 | Thousand Oaks Ca 91320 | Ira, Alfred | 317319.86 | 37147 | 0 | 0 | 2026-02-20 | Upgrade End Treatments And Bridge | In Ventura County On Route 101 From The Los Angeles/Ventura County Line To Old Pacific Coast Highway And On Route 23 From Route 23 | 100 | 73 | 20233106.42 | 25548905 | 28212594.03 | 44564 | 2026-03-31 | 2022-09-23 | 2022-08-31 |  |  | 560 | 0 | 415 | 0
07 | 07-2XT104 | 2XT104 | 07-VEN-101-2.2/2.2 | 20.XX 201130 |  | Summer Construction Inc | Po Box 30 | Santa Paula Ca 93061 |  | 2137928141 | 1525 Rancho Conejo Blvd Ste 102 | Thousand Oaks Ca 91320 | Verma, Niketa | 0 | 40106.93 | 0 | 0 | 2025-11-20 | Repair Vehicular Collision Damages | In Ven County, City Of To N/B Us-101 N Of S Conejo School Rd To Remove &Replace Dam Aged Sound Wall, Transition & Terminal Sysdir' | 100 | 43 | 208723.99 | 4005 | 490000 | 59558 | 2026-03-14 | 2025-06-10 | 2025-04-25 |  |  | 80 | 0 | 60 | 0
07 | 07-0W3904 | 0W3904 | 07-VEN-101-10.7/26.7 | HM1 |  | Intermountain Slurry Seal, Inc. | 1120 Terminal Way | Reno Nv 89502 | 7753989694 | 8058577070 | 1525 Rancho Conejo Blvd #102 | Thousand Oaks, Ca 91320 | Ira, Alfred | 0 | 7689.41 | 0 | 0 | 2025-08-20 | Slurry Seal. | Ventura County From Camarillo Springs Roadundercrossing In Camarillo To Main Street Undercrossing In Ventura | 81 | 97 | 9114913.02 | 8783680 | 8990504.27 | 51485 | 2026-03-31 | 2023-07-28 | 2023-06-20 |  |  | 211 | 0 | 260 | 0 |  | X
07 | 07-0Y1304 | 0Y1304 | 07-VEN-101-25.9/30.6 |  |  | Rv Concrete, Inc. | 605 E. Commercial Street | Anaheim Ca 92801 | 7148884201 | 2133306650 | 1525 Rancho Conejo Blvd #102 | Thousand Oaks, Ca 95630 | Singh, Ranjit | 83400 | 0 | 0 | 0 | 2026-01-20 | Mainline Individual Slab Replacement. | Ventura County In Ventura From 0.1 Mile West Of Telephone Rd Undercrossing To Ventura Avenue Undercrossing | 95 | 89 | 1902682 | 2099000 | 2099000 | 59277 | 2026-03-14 | 2025-07-01 | 2025-05-22 |  |  | 76 | 0 | 80 | 0 |  | X
07 | 07-0W4004 | 0W4004 | 07-VEN-101-30.9/36.3 | HM1 |  | Re Chaffee Construction Inc | 1253 Evergreen Road, Suite 3 | Wrightwood Ca 92397 | 7606628068 | 8058577070 | 1525 Rancho Conejo Blvd.#102 | Thousand Oaks, Ca 91320 | Ira, Alfred | 0 | 0 | 5581.3 | 0 | 2024-11-20 | Concrete Pavement Slabs Replacement & Slur | Ventura County In And Near Ventura From Ventura River Bridge To 0.4 Mile South Of Padre Juan Canyon Road Overcrossing And From 0.4 | 100 | 98 | 2919259.79 | 2705704 | 2904169.92 | 50685 | 2026-03-31 | 2023-06-27 | 2023-05-16 |  |  | 162 | 0 | 120 | 0 |  | X
07 | 07-2XW704 | 2XW704 | 07-VEN-101-316.0/33.7 | 20.XX 201130 |  | Summer Construction Inc | P.O. Box 30 | Santa Paula Ca 93061 |  | 2137928141 | 1525 Rancho Conejo Blvd Suite 102 | Thousand Oaks Ca 91320 | Niketa Verma | 0 | 0 | 0 | 0 |  | Clean Drainage System & Remove Debris | In The Area Of Ventura County, On Northbound Ven101,Remove Debris Racks And Repair Slopes Dir'S Emergency F.A. | 0 | 0 | 0 | 7523 | 1076400 | 60430 | 2026-04-29 | 2026-02-10 | 2026-01-21 |  |  | 0 | 0 | 180 | 0
07 | 07-369704 | 369704 | 07-VEN-118-12.0/13.4 |  | PTNH-P118- (072)000 | C. A. Rasmussen, Inc. | 28548 Livingston Avenue | Valencia Ca 91355 | 8053310878 | 2137008447 | 1525 Rancho Conejo Blvd Ste102 | Thousand Oaks, Ca 91320 | Tehrani, Joseph Solaiman | 422673 | 15262.28 | 0 | 460000 | 2026-02-20 | Construct Soldier Pile Walls, Slope Protec | Ventura County In Somis From Sand Canyon Road To 0.1 Mile East Of Balcom Canyon Road | 19 | 20 | 4764089.8 | 23759126 | 24379126 | 58397 | 2027-12-30 | 2025-05-28 | 2025-04-25 |  |  | 128 | 0 | 690 | 0 |  | X
07 | 07-341604 | 341604 | 07-VEN-118-13.3/15.6 |  |  | 3Sixty Innovation, Inc. | 3555 Rosecrans St 114-110 | San Diego Ca 92110 | 8583041093 | 2137008447 |  |  | Tehrani, Jospeph | 12144.14 | 0 | 0 | 0 | 2025-10-20 | Construct New Modular Office | In And Near Moorpark, At The Eastbound And Westbound Commercial Vehicle Enforcement Facilities. | 100 | 66 | 1630789.02 | 2299998.47 | 2444390.76 | 45946 | 2026-06-30 | 2022-12-22 | 2022-10-25 |  |  | 230 | 0 | 230 | 0
07 | 07-387904 | 387904 | 07-VEN-118-18.4/T18.8 |  |  | Autobahn Construction, Inc. | 933 N. Batavia St. | Orange Ca 92867 | 7147697025 | 2137928141 | 1525 Rancho Conejo Blvd Ste102 | Thousand Oaks, Ca 91320 | Verma, Niketa | 547350 | 40787.17 | 0 | 13500 | 2026-02-20 | Install Chain Link Railing (Type 7 Modifie | Ventura County In Moorpark From 0.2 Mile North Of Route 23 To 0.1 Mile North Of Princeton Avenue Undercrossing. | 64 | 59 | 1688925.17 | 2793820 | 2847120 | 57776 | 2026-05-18 | 2025-04-15 | 2025-03-18 |  |  | 61 | 0 | 95 | 0 |  | X
07 | 07-356504 | 356504 | 07-VEN-126-14.6/34.5 |  | ACNH-P126- (060)E | Accu Construction, Inc. | 14751 Plaza Drive Suite L | Tustin Ca 92780 |  | 2133306650 | 1525 Rancho Conejo #102 | Thousand Oaks, Ca 91320 | Singh, Ranjit | 85198.47 | 0 | 0 | 0 | 2026-02-20 | Install Dpp Infiltration Area And Hot Mix | Ventura County In And Near Fillmore At Various Locations From 0.2 Mile East Of Boosey Road To 0.1 Mile West Of The Los Angeles Cou | 99 | 87 | 1404414.71 | 1557705 | 1612531.23 | 57175 | 2026-03-30 | 2025-02-18 | 2025-01-23 |  |  | 217 | 0 | 220 | 0 |  | X
07 | 07-1XW104 | 1XW104 | 07-VEN-126-20.3/20.3 | 20.XX 201131 |  | Mgp Construction Dba Michael G Porteous | Po Box 355 | Upland, Ca 91785 |  | 8058577070 | 1525 Rancho Conejo Blvd Suite 102 | Thousand Oaks, Ca 91320 | Ira, Alfred | 0 | 9150.23 | 0 | 0 | 2026-01-06 | Construct/Replace Maintenace Station | Ventura County In City Of Fillmore Ven-126Replace/Construct The Fillmore Maintenancestation Damaged By High Winds Dir'S Emergency | 100 | 94 | 3575846.1 | 76270 | 3798500 | 55657 | 2026-06-30 | 2024-04-15 | 2024-01-26 |  |  | 234 | 0 | 120 | 115 |  | X
07 | 07-2XP204 | 2XP204 | 07-VEN-126-/0 | 20.XX 201130 |  | Baltazar Construction, Inc | 236 E. Arrow Hwy | Covina, Ca 91722 |  | 2137928141 | 1525 Rancho Conejo Blvd Suite 102 | Thousand Oaks, Ca 91320 | Verma, Niketa | 0 | 91046.04 | 0 | 0 | 2026-02-20 | Repair Mudslide Debris Due To Storm Damage | Ventura County,City Of Piru, Santa Paula,&Fillmore Var Locations Clear Shoulders & Rdway Of Mudslide/Debris,Ds &Erosion Cntrldir'S | 99 | 90 | 1518488.75 | 7251 | 1681000 | 56005 | 2026-03-31 | 2024-06-20 | 2024-05-30 |  |  | 132 | 0 | 60 | 73 |  | X
07 | 07-3237U4 | 3237U4 | 07-VEN-150-13.3/19 | HA22 | ACNH-P150- (028)E | C. A. Rasmussen, Inc. | 28548 Livingston Avenue | Valencia Ca 91355 |  | 2137008447 | 1525 Rancho Conejo Blvd #102 | Thousand Oaks, Ca 91320 | Tehrani, Joseph | 0 | 30953.32 | 0 | 0 | 2025-11-20 | Place Hma (Type A) And Cold Plane Asphalt | Ventura County In And Near Ojai From Burnham Road To Gorham Road | 100 | 99 | 8848528.29 | 8145315.4 | 8770789.78 | 49205 | 2026-03-30 | 2023-05-10 | 2023-03-27 |  |  | 360 | 0 | 360 | 0 |  | X
07 | 07-2XN104 | 2XN104 | 07-VEN-150-20.0/32.2 | 20.XX 201130 |  | R & R Demo And Grading Corp | 1180 S Beverly Drive Suite310 | Los Angeles, Ca 90035 |  | 2137008447 | 1525 Rancho Conejo Blvd Ste 102 | Thousand Oaks, Ca 91320 | Tehrani, Joseph | 0 | 195180.96 | 0 | 0 | 2026-02-20 | Repair Damage Due To Rainstorms | In Ventura County, In&Around Santa Paula On Ven-150 @Multiple Locations To Remove/ Repair Damaged Slopes Due To Rainstorms Dir'S E | 100 | 94 | 29523747.69 | 76148 | 31495900 | 55594 | 2026-02-28 | 2024-04-05 | 2024-02-22 |  |  | 507 | 0 | 120 | 0 |  | X
07 | 07-344504 | 344504 | 07-VEN-150-31.3/34.4 |  |  | Granite Construction Company | 4820 Mcgrath St., Suite 101 | Ventura Ca 93003 | 6619029460 | 2137008447 | 1525 Rancho Conejo Blvd Ste102 | Thousand Oaks Ca 91320 | Solaiman Tehrani, J. | 203442.2 | 61279.45 | 265673.07 | 0 | 2026-02-20 | Cold Plane And Overlay, Modify Traffic Sig | Ventura County In Santa Paula From 0.2 Mile North Of Bridge Road To Santa Maria Street | 74 | 48 | 3874428.91 | 7631505 | 8031505 | 57341 | 2026-06-20 | 2025-03-12 | 2025-02-14 |  |  | 155 | 0 | 210 | 0 |  | X
07 | 07-346804 | 346804 | 07-VEN-232-.4/4.1 |  | ACNH-S232- (003)E | Toro Enterprises, Inc. | 2101 E. Ventura Blvd. | Oxnard Ca 93036 |  | 2137008447 | 1525 Rancho Conejo Blvd | Thousand Oaks, Ca 91320 | Solaiman Tehrani, J. | 1261835 | 0 | 0 | 220000 | 2026-02-20 | Cold Plane And Overlay With Hma & Rhma. | Ventura County In And Near Oxnard From Route 232/101 Separation To Route 118 | 44 | 29 | 5020121.76 | 16282743.7 | 16624207.2 | 57655 | 2026-11-30 | 2025-03-14 | 2025-02-04 |  |  | 177 | 0 | 400 | 0 |  | X
07 | 07-2XM504 | 2XM504 | 07-VEN--/0 | 20.10 201352 |  | Izurieta Fence Company Inc | 3000 Gilroy St | Los Angeles, Ca 90039 |  | 2137008447 | 1525 Rancho Conejo Blvd Ste 102 | Thousand Oaks, Ca 91302 | Tehrani, Joseph Soleiman | 0 | 43193.41 | 0 | 0 | 2026-02-20 | Fences/Gates& Detection Systems | Ventura Cty In City Of Santa Paula&Malibu Big Sycamore Ms To Construct Fences/Gates & Perimeter Laser Detection System Dir'S Emerg | 100 | 86 | 829082.4 | 6880 | 969100 | 56417 | 2026-02-28 | 2024-08-21 | 2024-07-16 |  |  | 331 | 0 | 180 | 0 |  | X
08 | 08-1P0804 | 1P0804 | 08-RIV-10-7.0/44.5 |  |  | Truesdell Corporation Of California, Inc. | 1310 W. 23Rd Street | Tempe Az 85282 | 6028096032 | 9518306845 | 850 S Via Lata #104 | Colton, Ca 92324 | Rahman, Md | 110310 | 64732.34 | 0 | 0 | 2026-02-20 | Furnish & Place Polyester Concrete Overlay | Riverside County At Various Locations Fromveile Avenue Undercrossing In Beaumont To Monterey Avenue Overcrossing At Thousand Palms | 48 | 71 | 3581453.28 | 4928928 | 5024563.64 | 59337 | 2026-05-22 | 2025-06-13 | 2025-06-03 |  |  | 62 | 0 | 130 | 0 |  | X
08 | 08-1L9504 | 1L9504 | 08-RIV-10-12.6/13.4 |  |  | Diversified Landscape Company Anthony Rodriguez Project Manager | 21730 Bundy Canyon Road | Wildomar Ca 92595 | 9518308725 | 9512328549 | 937 S. Via Lata Suite 650 | Colton, Ca 92324 | Gonzalez, Daniel | 2190 | 0 | 0 | 0 | 2026-02-20 | Restore And Rehabilitate Existing | In The City Of Banning From 0.25 Miles West Of 8Th Street I.C. To S. San Gorgonio Ave. | 0 | 0 | 1060709.83 | 986640.5 | 1059810.5 | 44004 | 2026-08-17 | 2022-07-29 | 2022-06-13 |  |  | 791 | 0 | 860 | 0 | X | X
08 | 08-1K9604 | 1K9604 | 08-RIV-10-14.6/16.3 |  | ACIM-0103- (114)E | Powell Constructors, Inc. | 8555 Banana Avenue | Fontana Ca 92335 | 9094544243 | 9518306845 | 850 S Via Lata #104 | Colton Ca 92324 | Rahman, Md | 0 | 0 | 0 | 0 |  | Building Work. | Riverside County In Banning From 0.2 Mile East Of Hathaway Street To 0.1 Mile West Of Malki Road | 0 | 0 | 0 | 9653519.5 | 9653519.5 | 60274 | 2027-12-16 | 2025-12-18 | 2025-11-26 |  | S | 0 | 0 | 250 | 0
08 | 08-0G8504 | 0G8504 | 08-RIV-10-71.2/72.6 |  | CIMG-0104- (068)E | Granite Construction Company | Po Box 742478 | Los Angeles, Ca 90074-2478 | 8317287561 | 9512326263 | 41601 Corporate Way | Palm Desert, Ca 92260 | Vu, Khoi | 4092435.88 | 2767.83 | 0 | 0 | 2026-02-20 | Building Work. | Riverside County Near Indio From 0.9 Mile West To 0.5 Mile East Of The Cactus City Safety Roadside Rest Areas | 11 | 41 | 15786752.17 | 38224000 | 38325773 | 58656 | 2026-11-13 | 2025-05-07 | 2025-04-03 |  |  | 112 | 0 | 1050 | 0 |  | X
08 | 08-1C08U4 | 1C08U4 | 08-RIV-10-134.0/156.5 |  | ACNH-0105- (052)E | Fisher Sand & Gravel Co. Dba Southwest Asphalt Paving | 1302 W. Drivers Way | Tempe Az 85284 | 7029293157 | 9512326161 | 134 E Hobson Way | Blythe, Ca 92225 | Brown, Paul | 6084869.5 | 611439.01 | 0 | 0 | 2026-02-20 | Place Hma (Type A), Jpcp, Imported Borrow, | Riverside County From 1.1 Miles West Of Wiley Well Road Overcrossing To California/ Arizona State Line | 53 | 76 | 168474825.27 | 232232232.32 | 222521313.81 | 53666 | 2026-10-14 | 2023-07-24 | 2023-06-22 |  |  | 452 | 0 | 850 | 0 |  | X
08 | 08-1R4504 | 1R4504 | 08-RIV-15-.6/1.6 | 20.20 201130 |  | Myers & Sons Construction Llc | 45 Morrison Ave | Sacramento Ca 95838 | 9162839950 | 9512326052 | 119 N Maple Street #A | Corona Ca 92878 | Joe Lopez | 0 | 432368.55 | 0 | 0 | 2026-02-20 | Repair Damage 66" Csp Culvert | Damage Repair For Existing 66" Culvert Crossing Underneath I-15 Dir'S Order Emergency F.A | 48 | 45 | 1569577.06 | 21000 | 4385000 | 60099 | 2026-04-10 | 2025-07-22 | 2025-06-12 |  |  | 29 | 0 | 60 | 0 |  | X
08 | 08-1K4004 | 1K4004 | 08-RIV-15-3.5/6.8 |  | ACIM-0155- (175)E | Beador Construction Company, Inc. | 2900 Bristol Street D204 | Costa Mesa Ca 92626 | 9516747352 | 9512327608 | 119 N. Maple St. Ste.A | Corona, Ca 92880 | Sostrom, Denise | 2462376.03 | 7405.32 | 75213.18 | 0 | 2026-02-20 | Hma (Type A), Rdwy Exc, Str Conc Ret Wall, | Temecula From 0.1 Mi North Of Temecula Parkway To 0.2 Mi North Of Winchester Road | 51 | 67 | 21209113.55 | 30393300 | 31408838.3 | 57389 | 2027-10-07 | 2025-02-27 | 2025-01-29 |  |  | 185 | 0 | 610 | 0 |  | X
08 | 08-1J8704 | 1J8704 | 08-RIV-15-16.3/52.3 |  | ACIM-0155- (173)E | Beador Construction Company, Inc. | 2900 Bristol Street D204 | Costa Mesa Ca 92626 | 9516747352 | 9518306837 | 119 North Maple Suite A | Corona, Ca 92880 | Avila, Xavier | 2420 | 3555.97 | 0 | 0 | 2026-02-20 | Minor Concrete, Hma (Type A), Modifying Si | Riverside County At Various Locations Frombundy Canyon Road Undercrossing In Wildomar To Philadelphia Street Undercrossing In Eas | 53 | 93 | 2405777.42 | 2537700 | 2507700 | 56214 | 2026-11-23 | 2024-08-08 | 2024-07-10 |  |  | 190 | 0 | 360 | 0 |  | X
08 | 08-1R3804 | 1R3804 | 08-RIV-15-18.7/19 | 20.20 201130 |  | Baltazar Construction Inc. | 236 E Arrow Hwy | Covina, Ca 91722 |  | 9512326052 | 119 N Maple Street #A | Corona, Ca 92878 | Joe Lopez | 0 | 31162.06 | 0 | 0 | 2026-01-26 | Replace Damaged Culvert Resulted From Fire | Replace Damaged Culvert Resulted From Fire Set By An Unsheltered Encampment Individual Dir'S Order Emergency F.A. | 100 | 96 | 5366814.66 | 16975 | 5585000 | 57678 | 2026-01-26 | 2024-11-05 | 2024-11-05 |  |  | 130 | 0 | 30 | 0 |  | X
08 | 08-1L8104 | 1L8104 | 08-RIV-15-33.9/52.3 |  | ACIM-0155- (176)E | Alfaro Communications Construction, Inc. | 15614 S. Atlantic Avenue | Compton Ca 90221 |  | 9512323784 | 10370 Commerce Center Dr #110 | Rancho Cucamonga Ca 91730 | Nguyen, Vu | 0 | 0 | 0 | 0 |  | Mod Fiber Optic Cable Systems, Vegetation | Riverside And San Bernardino Counties At Various Locations From 0.6 Mile North Of Temescal Canyon Road To 1.1 Miles North Ofhodge | 0 | 0 | 0 | 6408824.79 | 6408824.79 | 60242 | 2026-11-10 | 2025-12-10 | 2025-11-26 |  |  | 0 | 0 | 150 | 0
08 | 08-1R4204 | 1R4204 | 08-RIV-15-35.1/35.1 | 20.20.201130 |  | Bcm Group, Inc | 9339 Feron Blvd | Rancho Cucamonga, Ca 91730 |  | 9096015089 | 850 S. Via Lata, Suite 100A | Colton, Ca 92324 | Ulloa, Irma | 0 | 106776.45 | 0 | 0 | 2023-09-20 | Replace Backup Generator | Replace Damaged Backup Generator For The Santiago Peak Radio Communication Tower From The Airport Fire Dir'S Order Emegency F.A. | 100 | 96 | 367969 | 6655 | 410000 | 58176 | 2026-01-30 | 2024-11-23 | 2024-11-22 |  |  | 269 | 0 | 45 | 0 |  | X
08 | 08-1P0704 | 1P0704 | 08-RIV-15-46.5/49.3 |  |  | Diverscape, Inc. Dba Diversified Landscape Co. | 21730 Bundy Canyon Road | Wildomar Ca 92595 | 9512451168 | 9518306803 | 937 South Via Lata Suite 650 | Colton, Ca 92324 | Macias, Daniel | 3948 | 0 | 0 | 0 | 2026-02-20 | Roadside Clearing And Hydroseed. | Riverside County In Eastvale From Santa Ana River Bridge To Bellegrave Avenue Overcrossing | 0 | 0 | 748369.4 | 912680.2 | 918880.2 | 56135 | 2028-08-01 | 2024-07-10 | 2024-06-13 |  |  | 281 | 0 | 870 | 0 | X | X
08 | 08-1H3804 | 1H3804 | 08-RIV-60-6.1/8 |  | ACNH-P060- (164)E | Accu Construction, Inc. | 14751 Plaza Drive Suite L | Tustin Ca 92780 | 7146414730 | 9512328549 | 937 S Via Lata Suite 650 | Colton, Ca 92324 | Gonzalez, Daniel | 3240 | 0 | 0 | 0 | 2026-02-20 | Minor Conc, Water Service Connection, And | Riverside County In Jurupa Valley From 0.5Mile East Of Pyrite Street To 0.4 Mile West Of Pacific Avenue | 0 | 0 | 4274361.35 | 4392608 | 4312255.5 | 55124 | 2028-01-31 | 2023-12-21 | 2023-12-05 |  |  | 486 | 0 | 950 | 0 | X | X
08 | 08-1G4704 | 1G4704 | 08-RIV-74-3.1/3 |  | B1ST-S074- (073)E | Beador Construction Company, Inc. | 2900 Bristol Street D204 | Costa Mesa, Ca 92626 | 9516747352 | 9512323739 | 9225 Stellar Court, Ste B | Corona, Ca 92883 | Bergevin, Mike | 3612 | 0 | 0 | 0 | 2026-02-20 | Structural Conc Br, Conc Slab, Hma (Type A | Riverside County Near Lake Elsinore At Morrill Canyon Bridge And Near Hemet At Strawberry Creek Bridge. | 78 | 97 | 8935762.99 | 8485300 | 9284120.39 | 50005 | 2026-07-29 | 2023-05-10 | 2023-04-06 |  |  | 390 | 0 | 500 | 0 |  | X
08 | 08-1R3704 | 1R3704 | 08-RIV-74-3.9/11.8 | 20.20 201130 |  | Skanska Usa Civil West California District, Inc. | 1995 Agua Mansa Rd | Riverside, Ca 92509 |  | 9512323739 | 9225 Stellar Ct., Ste B | Corona, Ca 92883 | Bergevin, Mike | 0 | 10175 | 0 | 0 | 2026-01-20 | Fire Damage Repairs | Repair Damages Resulted From Airport Fire Dir'S Order Emergency F.A. | 100 | 31 | 1217719.85 | 15800 | 3985000 | 57137 | 2026-04-20 | 2025-01-02 | 2024-10-07 |  |  | 239 | 0 | 50 | 0
08 | 08-1K6904 | 1K6904 | 08-RIV-74-5.7/11.8 |  | HSST-S074- (077)E | Granite Construction Company | 38000 Monroe Street | Indio Ca 92203 | 7605343239 | 9512326052 | 119 N Maple Street Suite A | Corona, Ca 92880 | Lopez, Joesph | 2013956.41 | 0 | 0 | 0 | 2026-02-20 | Rock Excavation, Hma (Type A), Rhma-G, And | Riverside County In And Near Lake Elsinorefrom Monte Vista Street To Grand Avenue | 23 | 44 | 39435616.27 | 87942000 | 88832410 | 57390 | 2028-06-30 | 2025-02-10 | 2025-01-09 |  |  | 154 | 0 | 675 | 0 |  | X
08 | 08-1L3104 | 1L3104 | 08-RIV-74-11.8/17.3 |  |  | R.J. Noble Company | 15505 East Lincoln Avenue | Orange Ca 92856 | 7146371550 | 5918306837 | 119 N Maple Ste A | Corona Ca 92880 | Xavier Avila | 19450 | 0 | 0 | 0 | 2026-02-20 | Rhma (Gap Graded), Replace Ac Surf, And Co | Riverside County In Lake Elsinore From Grand Avenue To Route 15/74 Separation | 40 | 13 | 700727.5 | 5478166.5 | 5528166.5 | 59616 | 2026-06-09 | 2025-07-15 | 2025-06-06 |  |  | 50 | 0 | 125 | 0 |  | X
08 | 08-1C07U4 | 1C07U4 | 08-RIV-74-27.5/34.3 |  | ACNH-P074- (073)E | Griffith Company | 3050 E. Birch St | Brea Ca 92821 | 7149845500 | 9096654132 | 9225 Stellar Court Suite B | Corona, Ca 92883 | Sanchez, Omar | 432282.38 | 0 | 0 | 455500 | 2026-02-20 | Rubberized Hma, Fiber Optic Cable Systems, | Riverside County At And Near Romoland And Homeland From Bonnie Drive To Winchester Road | 11 | 6 | 1029167.15 | 17882900 | 17970400 | 60120 | 2026-11-04 | 2025-08-22 | 2025-08-11 |  |  | 21 | 0 | 200 | 0 |  | X
08 | 08-1G6704 | 1G6704 | 08-RIV-79-5.4/11.4 |  | SSTG-S079- (047)E | Ortiz Enterprises, Inc. | 6 Cushing Suite 200 | Irvine Ca 92618 | 9497531414 | 9518309182 | 9225 Stellar Court, Suite B | Corona, Ca 92883 | Abdalla, Osama | 1538455.1 | 561336.71 | 49523.03 | 0 | 2026-02-20 | Hot Mix Asphalt, Soil Nail, Structural Con | Riverside County Near Temecula From 0.4 Mile South Of Sage Road To 1.1 Miles Southof Pauba Road | 41 | 48 | 29658673.97 | 60801162.1 | 61337579.44 | 56084 | 2028-03-02 | 2024-06-17 | 2024-05-23 |  |  | 349 | 0 | 690 | 166 |  | X
08 | 08-0R0104 | 0R0104 | 08-RIV-91-.3/0 |  |  | Beador Construction Company, Inc. | 2900 Bristol Street, Suite D2 | Costa Mesa Ca 92626 | 9516747352 | 9518306837 | 119 N. Maple St | Corona, Ca. 92880 | Avila, Xavier | 37500 | 0 | 0 | 0 | 2026-02-20 | Str Exc, Furnish Precast Rcb Culvert And S | Riverside County Near Corona At 0.7 Miles West Of Green River Road Overcrossing | 7 | 2 | 106000 | 5400300 | 5400300 | 60301 | 2027-09-30 | 2025-09-10 | 2025-08-27 |  |  | 28 | 0 | 430 | 0 |  | X
08 | 08-1P2804 | 1P2804 | 08-RIV-91-8.3/9 |  | SNHG-P091- (161)E | America Pacific Construction Inc | 7161 Citrus Valley Ave | Eastvale Ca 92880 | 5595779999 | 9098443312 | 4334 Latham Street, Suite 100 | Riverside, Ca 92501 | St.Jacques, Michael | 119300 | 29102.32 | 0 | 0 | 2026-02-20 | Mod Fo Cable Systems, Vegetation Control ( | Riverside County In Corona From 0.3 Mile East Of Promenade Avenue Overcrossing To 0.1 Mile West Of Mckinley Street Undercrossing | 90 | 91 | 622246.32 | 630330 | 669432.32 | 59542 | 2026-02-27 | 2025-07-22 | 2025-06-11 |  |  | 18 | 0 | 20 | 0 |  | X
08 | 08-1L1804 | 1L1804 | 08-RIV-91-13.5/16.8 |  | ACNH-P091- (162)E | Granite Construction Company | Po Box 742478 | Los Angeles Ca 90074-2478 |  | 9098443312 | 4334 Latham Street, Suite 100 | Riverside, Ca 92501 | St.Jacques, Michael | 686158.25 | 0 | 0 | 0 | 2026-02-20 | Jpcp (Rsc), Individual Slab Replacement (R | Riverside County In Riverside From 0.6 Mile West Of Van Buren Boulevard Overcrossing To 0.2 Mile East Of Madison Street Undercross | 11 | 4 | 686158.25 | 17403078 | 17403078 | 60305 | 2026-11-03 | 2025-11-10 | 2025-10-20 |  |  | 22 | 0 | 200 | 0 |  | X
08 | 08-1L3204 | 1L3204 | 08-RIV-91-15.6/21.6 |  | ACNH-P091- (155)E | Diversified Landscape Co. | 21735 Bundy Canyon Road | Wildomar Ca 92595 | 9512451686 | 9518306803 | 937 S. Via Lata Suite 650 | Colton, Ca 92324 | Macias, Daniel | 4858 | 0 | 0 | 0 | 2026-02-20 | Minor Concrete, Wood Mulch & Plant Establi | Riverside County In Riverside From 0.1 Mile West Of Adams Street To Route 60/91/215 Separation | 0 | 0 | 4047319.3 | 4394267.25 | 4478743.2 | 53705 | 2028-03-24 | 2023-11-01 | 2023-09-25 |  |  | 505 | 0 | 1000 | 0 | X | X
08 | 08-1J2904 | 1J2904 | 08-RIV-215-25.0/31.2 |  | ACIM-2151- (254)E | Coffman Specialties, Inc. | 9685 Via Excelencia, Suite 20 | San Diego Ca 92126 | 8585363100 | 9512323777 | 9225 Stellar Court Suite B | Corona, Ca 92883 | Guglielmana, Thomas | 637726.76 | 36724.85 | 0 | 0 | 2026-02-20 | Rhma, Hma, Replace Ac Surfacing, And Cold | Riverside County In And Near Perris From 0.1 Mile South Of San Jacinto River Bridgeto 0.3 Mile North Of Ramona Expressway | 3 | 93 | 27271626.5 | 27535000 | 28477573.33 | 56087 | 2026-10-19 | 2024-07-12 | 2024-06-18 |  |  | 17 | 0 | 500 | 0 |  | X
08 | 08-1J6104 | 1J6104 | 08-RIV-215-40.5/42.7 |  | ACIM-2151- (256)E | Fbd Vanguard Construction | 550 Greenville Road | Livermore Ca 94550 |  | 9518306853 | 4334 Latham Street Suite 100 | Riverside, Ca 92501 | Alam, Mahfual | 841524.05 | 0 | 0 | 103000 | 2026-02-20 | Individual Slab Replacement (Rsc), Rhma, A | Riverside County In Riverside From 0.8 Mile South Of Route 60/91 Separation To 0.4 Mile South Of Martin Luther King Boulevard Unde | 43 | 59 | 13703850.97 | 22714677.9 | 23149101.9 | 57080 | 2026-11-13 | 2024-12-03 | 2024-11-05 |  |  | 141 | 0 | 325 | 0 |  | X
08 | 08-1J4504 | 1J4504 | 08-RIV-243-/29.7 |  | ACST-S243- (002)E | All American Asphalt | 400 East Sixth Street | Corona Ca 92879 | 8587768840 | 9518306845 | 850 S Via Lata #104 | Colton, Ca 92324 | Rahman, Md | 776980.16 | 16272.57 | 0 | 0 | 2026-02-20 | Hma, Thermoplastic Traffic Stripe, And Col | Riverside County From Route 74 At Mountaincenter To Route 10 In Banning | 19 | 35 | 6239482.31 | 16898959 | 17461772.7 | 58655 | 2027-12-20 | 2025-05-23 | 2025-03-07 |  |  | 111 | 0 | 550 | 21 |  | X
08 | 08-1J3204 | 1J3204 | 08-RIV-5732-/0 |  |  | Nationwide Contracting Services, Inc. Dba Nationwide General Construction Services | 7660 Liberty Dr | Huntington Beach Ca 92647 | 5626078886 | 9096654302 | 9225 Stellar Court, Suite B | Corona, Ca 92883 | Shbaita, Jason | 606920 | 0 | 0 | 0 | 2026-02-20 | Building Work, Wrought Iron Fence, Hot Mix | Riverside County Near Lake Elsinore At Lake Elsinore Maintenance Station At 18745Conard Avenue | 17 | 24 | 2085207.59 | 8717880.1 | 8732545.84 | 59560 | 2026-09-23 | 2025-06-19 | 2025-05-29 |  |  | 82 | 0 | 480 | 0 |  | X
08 | 08-1J6204 | 1J6204 | 08-SBD-0-/0 |  |  | Preferred General Services | 19622 Shoshonee Road | Apple Valley Ca 92307 | 7602403236 | 9512326497 | 222 E Main St, Ste 202 | Barstow, Ca 92311 | Adodo, Jegbefume | 186719.14 | 0 | 0 | 0 | 2026-02-20 | Building Work. | San Bernardino County At Essex At The Essex Maintenance Station | 46 | 77 | 739435 | 958522.5 | 958522.5 | 56320 | 2026-05-29 | 2024-09-10 | 2024-06-21 |  |  | 39 | 0 | 85 | 0 |  | X
08 | 08-1J5404 | 1J5404 | 08-SBD-15-2.4/0 |  | BFIM-0151- (252)E | Flatiron Dragados West Llc | 14726 Ramona Avenue, Suite 30 | Chino, Ca 91710 | 9095978413 | 9518408248 | 10370 Commerce Center,Ste B110 | Rancho Cucamonga, Ca 91730 | Tran, Giang-Sinh | 1413613.51 | 40204.36 | 0 | 0 | 2026-02-20 | Cb, Jpcp, Structural Concrete And Bridge R | San Bernardino County In Ontario At Route 10/15 Separation | 66 | 59 | 8050227.7 | 14694000 | 13629351.99 | 58596 | 2026-04-20 | 2025-04-24 | 2025-04-02 |  |  | 128 | 0 | 195 | 0 |  | X
08 | 08-0R42A4 | 0R42A4 | 08-SBD-15-7.4/7.4 | 20.20 201130 |  | Exbon Development Inc | 13831 Newhope St | Garden Grove Ca 92843 | 7145392222 | 9096014064 | 10370 Commerce Center Dr Suite B-110 | Rancho Cucamonga Ca 91730 | Gonzalez, Alfonso | 0 | 10454.11 | 0 | 0 | 2026-01-20 | Fontana Maintenance Station | Build Maintenance Facility Adjacent To Southern Regional Lab Dir'S Emergency F.A | 14 | 0 | 10454.11 | 250000 | 24985000 | 60236 | 2028-06-23 | 2025-12-05 | 2025-04-24 |  |  | 101 | 0 | 708 | 0 |  | X
08 | 08-1R2804 | 1R2804 | 08-SBD-15-7.6/7.6 | 20.20 201130 |  | Conti, Llc | 14 Morgan | Irvine, Ca 92618 |  | 9096015089 | 850 S. Via Lata, Suite 100A | Colton, Ca 92324 | Ulloa, Irma | 0 | 88189.91 | 0 | 0 | 2026-01-20 | Replace The Nonfunctional Chiller System | Replace The Nonfunctional Chiller System Dir'S Order Emergency F.A. | 68 | 69 | 487642.68 | 2538 | 710000 | 59342 | 2026-02-27 | 2025-06-05 | 2025-01-17 |  |  | 169 | 0 | 45 | 0 |  | X
08 | 08-1L5104 | 1L5104 | 08-SBD-15-15.9/0 |  |  | Peterson-Chase General Engineering Construction, Inc. | 16351 Construction Circle Wes | Irvine Ca 92606 | 9492520441 | 9096014064 | 10370 Commerce Center Dr B-110 | Rancho Cucamonga Ca 91730 | Alfonso Gonzalez | 53059.5 | 0 | 0 | 0 | 2026-01-30 | Furnish And Place Polyester Concrete Overl | San Bernardino County Near San Bernardino At Devore Overhead | 100 | 98 | 1490384.17 | 1666347.87 | 1511547.87 | 60079 | 2026-01-30 | 2025-09-09 | 2025-08-12 | 2026-02-26 |  | 55 | 0 | 55 | 0 |  | X
08 | 08-1H3904 | 1H3904 | 08-SBD-15-20.5/21.6 |  | ACIM-0151- (250)E | Powell Constructors Inc | 8555 Banana Avenue | Fontana Ca 92335 | 9093568880 | 9096014349 | 15255 Bear Valley Road | Hesperia, Ca 92345 | Saoud, Walid | -602200 | 101409.73 | 0 | 0 | 2026-02-20 | Construct Building, Roadway Exc, Jpcp, And | San Bernardino County From 0.6 Mile North Of Cleghorn Road Undercrossing To 0.5 Milesouth Of Route 138 And From 0.5 Mile Southof T | 86 | 87 | 22509424.28 | 25227230 | 25867921.18 | 52244 | 2026-04-17 | 2023-08-30 | 2023-07-13 |  |  | 257 | 0 | 300 | 0 |  | X
08 | 08-1J3304 | 1J3304 | 08-SBD-15-160.9/161.5 |  | CIMG-0153- (049)E | Tsi Engineering, Inc. | 4600 Roseville Rd Suite 140 | North Highlands Ca 95660 | 9168869066 | 9512328611 | 222 E. Main St. Suite #208 | Barstow, Ca 92311 | Nguyen, Khoa | 568967 | 164000 | 0 | 0 | 2026-02-20 | Building Work. | San Bernardino County Near Mountain Pass From 0.2 Mile South To 0.4 Mile North Of Valley Wells Safety Roadside Rest Area | 44 | 49 | 5931170.84 | 12349786 | 12036674 | 57138 | 2026-09-09 | 2025-01-27 | 2024-12-24 |  |  | 109 | 0 | 250 | 0 |  | X
08 | 08-1N1214 | 1N1214 | 08-SBD-15-180.9/185.5 |  |  | Ferreira Construction Co., Inc. | 10370 Commerce Drive, Suite B | Rancho Cucamonga Ca 91730 | 9092172665 | 2134349325 | 464 W 4Th Street | San Bernardino, Ca 92401 | Yaacoub Lawrance | 0 | 0 | 69425.93 | 8767.8 | 2025-08-20 | Lane Control Sign Systems. | San Bernardino County About 43 Miles Northof Baker At Various Locations From 0.5 Mile South Of Yates Well Road Overcrossingto 0.7 | 67 | 43 | 1279144.28 | 2889921 | 3076606.93 | 55547 | 2025-10-31 | 2024-03-21 | 2023-12-18 |  | S | 40 | 0 | 60 | 0 |  | X
08 | 08-1R5004 | 1R5004 | 08-SBD-18-18.4/19.2 | 20.20 201130 |  | Myers & Sons Construction Llc | 45 Morrison Ave | Sacramento, Ca 95838 | 9162839950 | 9096654200 | 850 S Via Lata, Suite 100A | Colton,Ca 92323 | Mineo, Nicholas | 0 | 13500.86 | 0 | 0 | 2026-02-12 | Repair Deteriorating Collapsing Retaining | Repair Deteriorating And Collapsing Retaining Wall At Pm 18.76, Scaling And Installing Net Drapery Systems At Pm 18.48Dir'S Order | 100 | 100 | 2119857.59 | 29400 | 4885000 | 59195 | 2026-02-12 | 2025-04-03 | 2025-01-06 | 2026-02-12 |  | 60 | 0 | 60 | 0 |  | X
08 | 08-1J3104 | 1J3104 | 08-SBD-18-34.0/44.3 |  | PTST-P018- (064)E | Interstate Civil Construction | 6025 Park Dr | Wrightwood Ca 92397 | 7602810188 | 9512124988 | 850 S Via Lata Suite 104 | Colton Ca 92324 | Elzawy, George | 0 | 0 | 0 | 0 |  | Csp, Cms System, And Structural Concrete. | San Bernardino County Near Big Bear Lake At Various Locations From Arrowbear Drive To Route 38 | 0 | 0 | 0 | 4919416.7 | 4919416.7 | 60304 |  | 2025-08-25 | 2025-08-08 |  |  | 0 | 0 | 105 | 0
08 | 08-1J3004 | 1J3004 | 08-SBD-18-90.9/96.6 |  | ACNH-P018- (065)E | Sully-Miller Contracting Company | 135 S. State College Blvd #40 | Brea Ca 92821 | 7145789600 | 9096014064 | 15255 Bear Valley Road | Hesperia, Ca 92345 | Gonzalez, Alfonso | 249983.18 | 0 | 0 | 0 | 2026-02-20 | Hma (Type A), Mod Signal & Ltg Systems, & | San Bernardino County In And Near Victorville From Apple Valley Inn Road To Route 15/18 Separation | 71 | 81 | 10805014.12 | 12766200.1 | 13468647.96 | 57136 | 2026-06-08 | 2025-01-22 | 2024-12-06 |  |  | 181 | 0 | 255 | 0 |  | X
08 | 08-1T3304 | 1T3304 | 08-SBD-38-14.9/44.2 | 20.20 201130 |  | Riverside Construction Company, Inc. | Po Box 1146 | Riverside, Ca 92502 | 9516828308 | 9096659931 | 850 Via Lata Suite 104 | Colton, Ca 92324 | Contreras, Marco | 0 | 2629158.6 | 0 | 0 | 2026-02-20 | Repair The Damaged Roadway | Repair The Damaged Roadway Dir'S Order Emergency F.A. | 39 | 35 | 9186216.76 | 54132 | 26285000 | 60129 | 2026-07-29 | 2025-10-17 | 2025-09-22 |  |  | 104 | 0 | 270 | 0 |  | X
08 | 08-1T2804 | 1T2804 | 08-SBD-40-5.0/7 | 2020 201130 |  | Sully Miller Contracting Co | 135 S.State College Blvd #400 | Brea, Ca 92821 | 7145789600 | 9512328611 | 222 East Main St. Suite 208 | Barstow Ca 92311 | Nguyen, Khoa | 0 | 268708.85 | 0 | 0 | 2026-02-20 | Repair Damaged Roadway | Repair Damaged Roadway On Route 40 Due To Storm Damage Dir'S Emergency F.A. | 81 | 84 | 2079282.53 | 6675 | 2485000 | 60140 | 2026-03-26 | 2025-10-17 | 2025-09-04 |  |  | 57 | 0 | 70 | 0 |  | X
08 | 08-1K4904 | 1K4904 | 08-SBD-40-105.1/105.9 |  | ACIM-0402- (070)E | Granite Construction Company | 580 W Beach Street | Watsonville Ca 95076 | 4426371608 | 9518408222 | 1044 E. Broadway St | Needles, Ca 92363 | Doan, Anthony | 966880.29 | 1250 | 0 | 0 | 2026-02-20 | Building Work, Hma, And Temporary Portable | San Bernardino County About 36 Miles West Of Needles From 2.1 Miles To 1.3 Miles West Of Goffs Road Undercrossing | 46 | 62 | 28096267.33 | 45454108 | 45585370.53 | 56271 | 2026-06-30 | 2024-06-18 | 2024-05-28 |  |  | 291 | 0 | 630 | 0 |  | X
08 | 08-1N7804 | 1N7804 | 08-SBD-40-129.8/135.9 |  |  | Sully-Miller Contracting Company | 135 S. State College Blvd #40 | Brea Ca 92821 |  | 9518408222 | 1044 E Broadway St | Needles Ca 92363 | Anthony Doan | 194648 | 0 | 0 | 0 | 2026-02-20 | Rubberized Hma, Cold Plane Ac Pvmt And Rep | San Bernardino County From 2.9 Miles West To 3.2 Miles East Of Route 95 | 87 | 90 | 8092711.3 | 8773157.5 | 8773157.5 | 59635 | 2026-03-04 | 2025-07-14 | 2025-06-24 |  |  | 65 | 0 | 75 | 0 |  | X
08 | 08-1M0404 | 1M0404 | 08-SBD-40-140.0/142.2 |  | HSIM-0402- (071)E | Interstate Civil Construction | 6025 Park Dr | Wrightwood Ca 92397 | 7602810188 | 9512328611 | 1044 East Broadway St. | Needles, Ca 92363 | Anthony Doan | 425936.67 | 314645.06 | 0 | 0 | 2026-02-20 | Cold Plane Ac & Rhma, Vegetation Control ( | San Bernardino County In Needles From Fox Wash Overflow To L Street Undercrossing | 88 | 62 | 4494375.16 | 6881495.3 | 7212441.7 | 59556 | 2026-04-07 | 2025-06-17 | 2025-06-06 |  |  | 53 | 0 | 60 | 0
08 | 08-1J7204 | 1J7204 | 08-SBD-40-/S.8 |  | ACIM-0401- (092)E | Sully-Miller Contracting Company | 135 S. State College Blvd #40 | Brea Ca 92821 | 9145789600 | 9512328611 | 222 E. Main St. Suite #208 | Barstow, Ca 92311 | Nguyen, Khoa | 749623.7 | 87853.37 | 0 | 0 | 2026-02-20 | Replace Ac Surfacing, Cold Plane Ac Paveme | San Bernardino County In And Near Barstow From 0.1 Mile West Of Roberta Street To Montara Road And From Route 15 To 0.4 Mileeast O | 80 | 89 | 36860893.43 | 39875395.4 | 40425034.9 | 57242 | 2026-04-28 | 2025-02-10 | 2025-01-17 |  |  | 192 | 0 | 240 | 0 |  | X
08 | 08-1T2604 | 1T2604 | 08-SBD-62-30.7/31.3 | 20.20 201130 |  | Griffith Company | 12200 Bloomfield Ave | Santa Fe Springs Ca 90670 | 5629291128 | 9512326263 | 41601 Corporate Way | Palm Desert, Ca 92260 | Vu, Khoi | 0 | 198864.84 | 0 | 0 | 2026-02-20 | Repair Road,Paving,Railings,Embankments | Repair Roadway, Slope Paving, Bridge Railings, Bridge Embankments, Sidewalks, Drainage Systems Dir'S Order Emergency F.A. | 100 | 7 | 198864.84 | 11025 | 2985000 | 60135 | 2026-02-26 | 2025-11-06 | 2025-08-26 |  |  | 117 | 0 | 60 | 0
08 | 08-1T3504 | 1T3504 | 08-SBD-62-54.0/79.5 | 20.20 201130 |  | Griffith Company | 12200 Bloomfield Ave | Santa Fe Springs Ca 90670 | 5629291128 | 9512326263 | 41601 Corporate Way | Palm Desert, Ca 92260 | Vu, Khoi | 0 | 10571.17 | 0 | 0 | 2026-02-20 | Repair Flood Damaged Roadway | Repair Flood Damaged Roadway Dir'S Order Emergency F.A. | 100 | 60 | 1079444.63 | 6930 | 1785000 | 60134 | 2026-02-25 | 2025-11-06 | 2025-09-22 |  |  | 82 | 0 | 40 | 0
08 | 08-1L2404 | 1L2404 | 08-SBD-95-57.2/64.5 |  |  | Sully-Miller Contracting Company | 135 S. State College Blvd #40 | Brea Ca 92821 | 8004319842 | 9518408222 | 1044 East Broadway St | Needles, Ca 92363 | Doan, Anthony | 0 | 0 | 0 | 0 |  | Rhma (Gap Graded), Replace Ac Surfacing, A | San Bernardino County Near Needles From Route 40/95 Separation To 0.5 Mile North Of Goffs Road | 0 | 0 | 0 | 6949949 | 6949949 | 60141 | 2026-06-24 | 2025-10-24 | 2025-10-09 |  |  | 0 | 0 | 80 | 0
08 | 08-1R7304 | 1R7304 | 08-SBD-138-18.9/19.5 | 20.20 201130 |  | Steve P. Rados Inc | Po Box 15128 | Santa Ana, Ca 92705 | 7148354612 | 9096014698 | 15255 Bear Valley Rd | Hesperia, Ca, 92345 | Flores, Roberto | 0 | 391083.62 | 0 | 0 | 2026-02-04 | Install Drainage System | Install Drainage System To Mitigate Concentrated Flow Crossing The Highway During Rainfall And Flooding Dir'S Order Emergency F.A | 100 | 26 | 932667.52 | 21990 | 3585000 | 60098 | 2026-02-04 | 2025-09-12 | 2025-07-31 | 2026-02-12 |  | 60 | 0 | 60 | 0
08 | 08-1T5304 | 1T5304 | 08-SBD-138-/0 | 20.20 201130 |  | Steve P. Rados | P.O Box 15128 | Santa Ana, Ca 92705 |  | 9096014698 | 15255 Bear Valley Rd | Hesperia Ca 92345 | Flores, Roberto | 0 | 0 | 0 | 0 |  | Repair Flooded Roadway | Repair Flooded Roadway Order Emergency F.A | 0 | 0 | 0 | 23170 | 3815000 | 60415 | 2026-04-15 | 2026-02-12 | 2026-01-19 |  |  | 0 | 0 | 75 | 0
08 | 08-1N7704 | 1N7704 | 08-SBD-173-/L7.7 |  |  | Calmex Engineering, Inc. | 2750 S. Lilac Ave | Bloomington Ca 92316 | 9095461311 | 9096654200 | 850 S. Via Lata, Suite 100A | Colton, Ca 92324 | Mineo, Nicholas | 4831.5 | 0 | 0 | 0 | 2025-12-20 | Cold Plane Ac Pvmt, Hma (Type A), And Repl | San Bernardino County In Hesperia From Route 138 To 0.5 Mile East Of Arrowhead Lake Road | 100 | 91 | 3079151.04 | 3260585 | 3260585 | 59355 | 2025-12-20 | 2025-05-13 | 2025-04-25 |  |  | 30 | 0 | 30 | 0 |  | X
08 | 08-1T3204 | 1T3204 | 08-SBD-178-10.0/12 | 2020 201130 |  | Beador Construction Company | 2900 Bristol St Suite D204 | Costa Mesa Ca 92626 | 7145525818 | 9096014717 | 15255 Bear Valley Rd | Hesperia Ca 92345 | Loza, Shaun | 0 | 1545971.19 | 0 | 0 | 2025-10-06 | Repair Damaged Sbd 178 | Repair/Restore Damage Roadway Sbd 178 Washout Directors Order Emergency F.A | 28 | 78 | 1545971.19 | 9750 | 1985000 | 60156 | 2025-10-06 | 2025-10-24 | 2025-09-22 | 2026-02-26 |  | 11 | 0 | 40 | 0 |  | X
08 | 08-1M7404 | 1M7404 | 08-SBD-210-1.2/1.6 |  | HSNH-P210- (018)E | Interstate Civil Construction | 6025 Park Dr | Wrightwood Ca 92397 | 7606621771 | 9512323784 | 10370 Commerce Center Dr.,#110 | Rancho Cucamonga, Ca 91730 | Nguyen, Vu | 1859.76 | 0 | 0 | 0 | 2026-02-20 | Jpcp (Rsc), Rdwy Exc, Lcb Rapid Setting, & | Sanbernardino County In Upland From 0.3 Mile West To 0.1 Mile East Of Mountain Avenue Overcrossing | 45 | 92 | 2835883.81 | 2968222.1 | 3017372.1 | 58456 | 2026-08-12 | 2025-03-27 | 2025-03-12 |  |  | 130 | 0 | 290 | 0 |  | X
08 | 08-0N0604 | 0N0604 | 08-SBD-210-14.6/16.4 |  |  | John Semsen Landscaping Co., Inc. | 21161 Lyons Bald Mountain Roa | Sonora Ca 95370 | 2097434911 | 9518306803 | 937 S Via Lata Suite 650 | Colton, Ca | Macias, Daniel | 1512 | 0 | 0 | 0 | 2026-02-20 | Plastic Pipe (Supply Line), Roadside Clear | San Bernardino County In Fontana And Rialto From 0.3 Mile West Of Sierra Avenueovercrossing To Locust Avenue Overcrossing | 0 | 0 | 728648.5 | 840940 | 837230 | 59559 | 2029-01-30 | 2025-07-08 | 2025-06-16 |  |  | 101 | 0 | 835 | 0 | X | X
08 | 08-1P0604 | 1P0604 | 08-SBD-210-15.7/17.9 |  |  | John Semsen Landscaping Co., Inc. | 21161 Lyons Bald Mountain Roa | Sonora Ca 95370 | 2097436809 | 9518306803 | 937 S. Via Lata Ste 650 | Colton, Ca 92324 | Macias, Daniel | 2100 | 0 | 0 | 0 | 2026-02-20 | Plastic Pipe (Supply Line), Wood Munch & M | San Bernardino County In Rialto From 0.2 Mile West Of Alder Avenue Overcrossing To Cactus Avenue Overcrossing | 0 | 0 | 897007.94 | 931690 | 941690 | 56233 | 2028-02-08 | 2024-07-17 | 2024-06-28 |  |  | 388 | 0 | 855 | 0 | X | X
08 | 08-1L9704 | 1L9704 | 08-SBD-210-23.1/24.7 |  |  | Diversified Landscape Co. | 21730 Bundy Canyon Road | Wildomar Ca 92595 | 9512451686 | 9095189727 | 937 S Via Lata Ste 650 | Colton, Ca 92324 | Mcnicoll, Joseph | 1887.2 | 0 | 0 | 0 | 2026-02-20 | Wood Mulch, Roadside Clearing, & Modifying | San Bernardino County In San Bernardino Onroute 210 From Route 210/259 Separation To0.5 Mile East Of North Waterman Overcrossing | 0 | 0 | 1317838.31 | 1294010.7 | 1432755.2 | 53424 | 2027-09-22 | 2023-07-24 | 2023-06-13 |  |  | 530 | 0 | 890 | 0 | X | X
08 | 08-1M5604 | 1M5604 | 08-SBD-210-24.0/0 |  | HSNH-P210- (019)E | Riverside Construction Company, Inc. | Po Box 1146 | Riverside Ca 92502 | 9516828308 | 9096654200 | 850 S. Via Lata, Suite 100A | Colton, Ca 92324 | Mineo, Nicholas | 0 | 0 | 0 | 0 |  | Str Conc Rw, Str Exc (Rw), Rdwy Exc, Jpcp | San Bernardino County In San Bernardino Atwaterman Avenue Eastbound Exit Ramp | 0 | 0 | 0 | 4774890.5 | 4774890.5 | 60443 | 2027-11-01 | 2025-12-17 | 2025-11-25 |  |  | 0 | 0 | 430 | 0
08 | 08-1T2704 | 1T2704 | 08-SBD-247-46.1/76.9 | 2020 201103 |  | Sully-Miller Contracting Co. | 135 S State College Blvd #400 | Brea Ca 92821 | 7145789600 | 9096014349 | 15255 Bear Valley Road | Hesperia Ca 92345 | Saoud, Walid | 0 | 566303.6 | 0 | 0 | 2026-01-09 | Repair Roadway Pavement And Embankment | Repair Roadway Pavement And Embankment Dir'S Order Emergency F.A. | 100 | 100 | 1850103.05 | 5340 | 1985000 | 60138 | 2026-01-09 | 2025-11-06 | 2025-08-29 | 2026-02-12 |  | 42 | 0 | 60 | 0 |  | X
08 | 08-1J2704 | 1J2704 | 08-SBD-247-/23 |  | ACST-P247- (015)E | Sully-Miller Contracting Company | 135 S. State College Blvd #40 | Brea Ca 92821 | 7149491771 | 9096014349 | 15255 Bear Valley Road | Hesperia, Ca 92345 | Saoud, Walid | 167439.5 | 5044.92 | 0 | 0 | 2026-02-20 | Rubberized Hma, Hma (Type A), Cold Plane A | San Bernardino County In Yucca Valley Fromroute 62 To 0.4 Mile West Of Gin Road | 96 | 93 | 21102660.83 | 21990603.4 | 22295189.67 | 57388 | 2026-02-27 | 2025-03-06 | 2025-01-31 |  |  | 120 | 0 | 125 | 0 |  | X
08 | 08-1T4604 | 1T4604 | 08-SBD-330-34.0/42 | 20.20 201130 |  | Sema Construction Inc | 7353 S Eagle Street | Centennial Co 80112 | 3036272600 | 9512326415 | 850 S Via Lata Unit 104 | Colton Ca 92324 | Wang, Tsung | 0 | 111863.5 | 0 | 0 | 2026-02-20 | Repair And Restore Roadway Debris Barriers | Restore Roadway Bebris Removal Restore Drainage Capacity Repair Debris Flow Racks Repair Flexible Debris Flow Barrier Dir'S Order | 37 | 15 | 743880.43 | 10438 | 4995438 | 60243 | 2026-03-31 | 2026-01-30 | 2025-11-20 |  |  | 52 | 0 | 140 | 0 |  | X
08 | 08-1G6404 | 1G6404 | 08-SBD-395-4.0/49 |  | ACNH-P395- (351)E | Sully-Miller Contracting Company | 135 S. State College Blvd #40 | Brea Ca 92821 | 7145789600 | 9096014717 | 15255 Bear Valley Road | Hesperia, Ca 92345 | Loza, Shaun | 18750 | 61823.03 | 0 | 0 | 2025-09-20 | Replace Asphalt Concrete Surfacing, Cold P | San Bernardino County At Various Locationsfrom Route 15/395 Separation To 3.1 Miles North Of Route 58/395 Separation | 100 | 95 | 35806915 | 35935000 | 36702372.03 | 53964 | 2025-09-20 | 2023-11-28 | 2023-10-25 |  |  | 120 | 0 | 120 | 0 |  | X
08 | 08-1H9924 | 1H9924 | 08-VAR--/0 |  | ACST-000C- (552)E | Gba Engineering, Inc. | 18543 Yorba Linda Blvd #394 | Yorba Linda Ca 92886 | 7145106700 | 9096654200 | 850 S. Via Lata, Suite 100A | Colton, Ca 92324 | Mineo, Nicholas | 198510.39 | 0 | 0 | 0 | 2025-10-20 | Install Roadside Sign-One Post, & Furnish | Riverside And San Bernardino Counties At Various Locations | 100 | 97 | 2112922.59 | 2135964 | 2290711.35 | 56251 | 2026-02-02 | 2024-06-05 | 2024-04-15 |  |  | 110 | 0 | 110 | 0 |  | X
08 | 08-1J8604 | 1J8604 | 08-VAR--/0 |  | ACNH-X071- (076)E | Peterson-Chase General Engineering Construction, Inc. | 16351 Construction Circle Wes | Irvine Ca 92606 | 9492926906 | 2134349325 | 464 W 4Th Street | San Bernardino, Ca 92401 | Yaacoub, Lawrance | 1150727.65 | 0 | 0 | 25000 | 2026-02-20 | Modifying Cms Systems And Furnish Sign Str | San Bernardino County At Various Locations | 80 | 44 | 6287238.91 | 13973863 | 14228863 | 56123 | 2026-07-30 | 2024-06-05 | 2024-05-01 |  | S | 184 | 0 | 230 | 0
08 | 08-1J8504 | 1J8504 | 08-VAR--/0 |  | ACST-X071- (077)E | Powell Constructors Inc | 8555 Banana Avenue | Fontana Ca 92335 | 9093568880 | 9512124988 | 850 S. Via Lata Suite 104 | Colton, Ca 92324 | Elzawy, George | 3400300 | 16719.1 | 0 | 50598.8 | 2026-02-20 | Furnish Sign Structure And Install Changea | San Bernardino County At Various Locations | 79 | 55 | 7912596.97 | 14057592 | 14318561.2 | 56321 | 2026-04-09 | 2024-09-10 | 2024-08-29 |  |  | 143 | 0 | 180 | 0
08 | 08-1N4704 | 1N4704 | 08-VAR--/0 |  |  | Select Electric, Inc. | 2790 Business Park Drive | Vista Ca 92081 | 6199193869 | 2134349325 | 464 W 4Th Street | San Bernardino, Ca 92401 | Yaacoub, Lawrance | 0 | 18131.06 | 0 | 0 | 2026-01-20 | Modify Fo Cable, Camera & Roadside Weather | Riverside And San Bernardino Counties At Various Locations | 87 | 85 | 2389290.32 | 2690689 | 2802642.49 | 56435 | 2026-02-27 | 2024-08-07 | 2024-06-26 | 2026-02-06 | S | 130 | 0 | 150 | 0 |  | X
08 | 08-1H8804 | 1H8804 | 08-VAR--/0 |  |  | Indus General Inc. | 1851 Heritage Lane Ste 129 | Sacramento Ca 95821 |  | 9512327608 | 119 N. Maple St. Ste A | Corona, Ca 92880 | Sostrom, Denise | 42658.86 | 25476 | 0 | 761.75 | 2026-02-20 | Camera Systems, Rolled Erosion Control Pro | Riverside County At Various Locations | 79 | 70 | 340908.64 | 593973.36 | 499207.76 | 56535 | 2026-03-11 | 2024-10-01 | 2024-06-27 |  |  | 63 | 0 | 80 | 0 |  | X
08 | 08-1P6604 | 1P6604 | 08-VAR--/0 |  |  | Alfaro Communications Construction, Inc. | 15614 S. Atlantic Avenue | Compton Ca 90221 | 3106698949 | 9096654200 | 850 S. Via Lata 100A | Colton, Ca 92324 | Mineo,Nicholas | 132062.61 | 0 | 0 | 2015 | 2026-02-20 | Wrong Way Flashing Sign Systems And Roadsi | Riverside And San Bernardino Counties At Various Locations | 80 | 72 | 511052.61 | 708950.59 | 708950.59 | 59555 | 2026-03-10 | 2025-06-09 | 2025-05-27 |  |  | 48 | 0 | 60 | 0 |  | X
08 | 08-1J8404 | 1J8404 | 08-VAR--/0 |  | ACST-000C- (557)E | Peterson-Chase General Engineering Construction, Inc. | 16351 Construction Circle Wes | Irvine Ca 92606 | 9492520441 | 9512328611 | 222 E Main St Ste#208 | Barstow, Ca 92311 | Nguyen, Khoa | 525285 | 0 | 0 | 0 | 2026-02-20 | Install Cms System, Furnish Sign Structure | San Bernardino County At Various Locations | 88 | 72 | 9311292.62 | 12467540 | 12587961 | 56232 | 2026-04-15 | 2024-08-14 | 2024-06-28 |  |  | 158 | 0 | 180 | 0
08 | 08-1R0404 | 1R0404 | 08-VAR--/0 |  |  | Techbleed | 53 Glenflow Ct. | Glendale Ca 91206 | 8183336068 | 9096014064 | 10370 Commerce Center Drb-110 | Rancho Cucamonga Ca 91730 | Gonzalez, Alfonso | 0 | 0 | 0 | 0 |  | Modifying Traffic Monitoring Stations. | Riverside And San Bernardino Counties At Various Locations | 0 | 0 | 0 | 372859 | 372859 | 59620 | 2026-04-09 | 2025-07-30 | 2025-06-13 |  |  | 0 | 0 | 40 | 0
08 | 08-1P8904 | 1P8904 | 08-VAR--/0 |  |  | Kanaan Construction, Inc. | 5040 Heintz Street | Baldwin Park Ca 91706 | 6263345775 | 2134349325 | 464 W 4Th Street | San Bernardino, Ca 92401 | Yaacoub, Lawrance | 380128 | 0 | 0 | 0 | 2026-02-20 | Modifying Traffic Monitoring Stations And | Riverside And San Bernardino Counties At Various Locations | 52 | 92 | 820485.44 | 842080 | 892080 | 59455 | 2026-02-27 | 2025-06-03 | 2025-05-07 |  |  | 31 | 0 | 60 | 0 |  | X
08 | 08-1E1404 | 1E1404 | 08-VAR--/0 |  | SSTG-S079- (048)E | Beador Construction Company, Inc. | 2900 Bristol Street Ste D204 | Costa Mesa, Ca 92626 | 9516747352 | 9512323777 | 9225 Stellar Court Suite B | Corona, Ca 92883 | Guglielmana, Thomas | 32800 | 77752.37 | 0 | 0 | 2026-02-04 | Mgs, Concrete Barrier And Vegetation Contr | Riverside County At Various Locations | 100 | 100 | 7956563.4 | 7481300 | 8131536.84 | 56063 | 2026-02-04 | 2024-06-05 | 2024-04-25 | 2026-02-04 |  | 270 | 0 | 270 | 0 |  | X
09 | 09-374704 | 374704 | 09-INY-168-17.6/18.3 |  | ACST-X027- (012)E | Granite Construction Company | Po Box 742478 | Los Angeles Ca 90074-2478 |  | 6194332514 | 500 S Main Street, Bishop Ca |  | John Gentry | 657805.61 | 346746.64 | 11035.56 | 0 | 2026-02-15 | Hma (Type A), Minor Concrete, And Lighting | Inyo County In And Near Bishop On Route 395 From 0.1 Mile South Of Jay Street To Barlow Lane And On Route 168 From Pioneer Lane To | 56 | 46 | 10716376.42 | 22608806 | 23179958.26 | 57380 | 2026-06-29 | 2025-03-18 | 2025-02-21 |  |  | 117 | 0 | 210 | 0 |  | X
09 | 09-213404 | 213404 | 09-INY-395-29.2/41.8 | HE14 | ACNH-P395- (348)E | Fisher Sand & Gravel Co | 1302 W. Drivers Way | Tempe Az 85284 | 4807301033 | 7609203460 | 500 South Main Street | Bishop, Ca 93514 | Damon Cherenzia | 1500 | 826629.26 | 0 | 0 | 2026-02-15 | Construct 4 Lane Expressway | In Inyo County Near Olancha And Cartago From 1.4 Miles South Of Los Angeles Aqueduct Bridge To 0.2 Mile South Of Ash Creek Bridge | 100 | 94 | 96337570.81 | 69696969.69 | 100947131.4 | 41974 | 2026-01-15 | 2021-11-23 | 2021-10-22 |  |  | 878 | 0 | 500 | 359 |  | X
09 | 09-374504 | 374504 | 09-INY-395-56.8/57.4 |  | ACNH-P395- (356)E | California Highway Construction Group, Inc. | 1647 Willow Pass Road #150 | Concord Ca 94520 | [5 empty] | 0 | 0 | 0 | 0 |  | Construct Sidewalk, Curb Ramps, And Draina | Inyo County At And Near Lone Pine From Teya Road To East Inyo Street And From Begole Street To East Lubken Avenue | 0 | 0 | 0 | 5886888 | 5886888 | 60160 |  | 2025-11-05 | 2025-09-19 |  |  | 0 | 0 | 140 | 0
09 | 09-390204 | 390204 | 09-INY-395-57.4/0 |  |  | Interstate Civil Construction | 6025 Park Dr | Wrightwood Ca 92397 | 7606621771 | 7609203613 | 500 S Main Street | Bishop, Ca 93514 | Scott Eagan | 179013.24 | 0 | 0 | 0 | 2026-02-19 | Construct Minor Concrete And Install Hybri | Inyo County At Lone Pine At East Muir Street | 58 | 42 | 282224.9 | 668415.1 | 668415.1 | 59198 | 2026-03-04 | 2025-07-02 | 2025-06-16 |  |  | 23 | 0 | 40 | 0 |  | X
09 | 09-379004 | 379004 | 09-INY-395-65.0/76 |  | NH -P395- (359)E | Road And Highway Builders, Llc | 950 E. Mustang Road | Sparks Nv 89434 | [5 empty] | 0 | 0 | 0 | 0 |  | Full Depth Recycling, Cold Plane, Hma And | Inyo County At And Near Independence From 3 Miles South Of Manzanar Reward Road To 0.3 Mile North Of Shabbell Lane | 0 | 0 | 0 | 45777777 | 45777777 | 60411 |  | 2026-02-10 | 2025-12-24 |  |  | 0 | 0 | 220 | 0
09 | 09-379104 | 379104 | 09-INY-395-91.6/100.8 |  | ACNH-P395- (354)E | Road And Highway Builders, Llc. | 950 E Mustang Rd | Sparks Nv 89434 | 7758527283 | 7609203406 | 500 S. Main St. | Bishop, Ca 93514 | Adam Zumstein | 750133.1 | 0 | 0 | 0 | 2025-12-19 | Construct Hma, Curb Ramps, And Electrical | Inyo County At And Near Big Pine From 0.1 Mile South Of Elna Road To South Junction Route 168 | 63 | 84 | 25594913.77 | 28888888 | 29702479 | 57381 | 2026-03-19 | 2025-03-21 | 2025-02-20 |  |  | 121 | 0 | 190 | 3 |  | X
09 | 09-374804 | 374804 | 09-INY-395-115.0/0 |  |  | Bowe Contractors, Inc. | 609 Bailey Court | Tehachapi Ca 93561 | 6619400899 | 7609378955 | 500 South Main St. | Bishop, Ca 93514 | David Carruba | 447540.15 | 0 | 0 | 0 | 2026-02-20 | Building Work And Place Hma (Type A). | Inyo County In Bishop At The District Office At 500 South Main Street | 4 | 3 | 447540.15 | 13624634.61 | 13624634.61 | 60155 | 2027-08-25 | 2025-11-03 | 2025-10-03 |  |  | 22 | 0 | 525 | 0 |  | X
09 | 09-398604 | 398604 | 09-INY-395-115.0/0 |  |  | Re Com Development Company | 2488 Dixon Lane | Bishop Ca 93514 | [5 empty] | 0 | 0 | 0 | 0 |  | Replace Water Line. | Inyo County In Bishop At The District Office At 500 South Main Street | 0 | 0 | 0 | 710128.62 | 710128.62 | 60241 |  | 2025-12-10 | 2025-10-22 |  |  | 0 | 0 | 70 | 0
09 | 09-366804 | 366804 | 09-INY-395-117.3/117.9 |  | ACNH-P395- (355)E | Granite Construction Company | Po Box 742478 | Los Angeles Ca 90074-2478 |  | 7609203406 | 500 S. Main St. | Bishop, Ca 93514 | Adam Zumstein | 1050821.11 | 0 | 0 | 0 | 2026-02-19 | Construct Sidewalks, Retaining Walls, Brid | Inyo County Near Bishop From 0.1 Mile Eastof See Vee Lane To Barlow Lane | 66 | 49 | 6233033.46 | 12864995 | 12811695.2 | 58055 | 2026-04-27 | 2025-05-07 | 2025-04-03 |  |  | 132 | 0 | 200 | 0 |  | X
09 | 09-378804 | 378804 | 09-MNO-395-9.8/12.6 |  | ACNH-P395- (353)E | Hat Creek Construction & Materials, Inc. | 24339 State Hwy 89 N. | Burney Ca 96013 | 5303355501 | 7609378955 | 500 S Main Street | Bishop, Ca 93514 | David Carruba | 3666 | 249876 | 0 | 0 | 2025-11-20 | Place Hma And Asphalt Base, Recycle Paveme | Mono County Near Tom'S Place From 0.5 Milenorth Of Lower Rock Creek Road To 1.3 Miles South Of South Landing Overcrossing | 94 | 95 | 13274677.92 | 13528809 | 13806405.12 | 56584 | 2026-05-29 | 2024-10-30 | 2024-08-29 |  |  | 89 | 0 | 95 | 0 |  | X
09 | 09-368004 | 368004 | 09-MNO-395-91.6/93.4 |  | HSNH-P395- (352)E | Granite Construction Company | Po Box 742478 | Los Angeles Ca 90074-2478 |  | 7609378955 | 500 South Main Street |  | David Carruba | 18128 | 0 | 0 | 0 | 2026-01-26 | Hot Mix Asphalt (Type A), Rail Element Wal | Mono County About 16 Miles North Of Bridgeport From Burcham Flat Road To 0.3 Mile South Of Route 108 | 100 | 100 | 15980413.44 | 15297000 | 16658789.92 | 55683 | 2026-01-26 | 2024-03-20 | 2024-02-29 | 2026-01-26 |  | 238 | 0 | 410 | 0 |  | X
10 | 10-0J7204 | 0J7204 | 10-ALP-4-/31.7 |  | ACST-X003- (032)E | A. Teichert & Son, Inc. Dba Teichert Construction | 3500 American River Dr | Sacramento Ca 95864 | [5 empty] | 0 | 0 | 0 | 0 |  | Replace Culverts, Cold Plane Ac Pavement A | Alpine County At And Near Bear Valley On Route 4 From Alpine County Line To 0.2 Mile East Of Eat Carson River Bridge And On Route | 0 | 0 | 0 | 29830200 | 29830200 | 60387 |  | 2026-01-29 | 2026-01-08 |  |  | 0 | 0 | 380 | 0
10 | 10-1U8004 | 1U8004 | 10-ALP-88-1.9/1.9 | 20.20.201130 |  | Acco Engineered System Inc | 888 E Walnut Street | Pasadena Ca 91101 |  | 2092793514 | 19596 Mono Way, | Sonora Ca 95370 | Jonathan Ngai | 0 | 0 | 0 | 0 |  | Repair Boilers, Remove Concrete | Schneider Cow Camp Road, South Lake Tahoe Ca 96150 Repair Boilers 10A2887 | 0 | 0 | 0 | 35000 | 685000 | 60403 | 2026-02-24 | 2026-02-06 | 2025-11-11 |  |  | 0 | 0 | 50 | 0
10 | 10-0Q2104 | 0Q2104 | 10-AMA-88-5.5/14.3 |  | ACNH-P088- (074)E | Bay Cities Paving & Grading, Inc. | 1450 Civic Ct Bldg B #400 | Concord Ca 94520 |  | 2092793514 | 19596 Mono Way | Sonora Ca. 95370 | Jonathan Ngai | 1800 | 21993.49 | 0 | 0 | 2026-01-26 | Repair Failed Pavement And Resurface Exist | Amador County Near Martell From 0.7 Mile West Of Ione-Buena Vista Road To 0.2 Mile East Of Kennedy Flat Road | 100 | 100 | 8415172.59 | 7919500 | 9147944.38 | 57076 | 2026-01-26 | 2024-12-18 | 2024-11-25 | 2026-01-26 |  | 125 | 0 | 125 | 0 |  | X
10 | 10-1H5004 | 1H5004 | 10-CAL-4-15.9/16.3 | HA21 |  | Viking Construction Company | 11315 Sunrise Gold Circle St | Rancho Cordova Ca 95742 | 9168525530 | 5105017727 | 850 South Guild Ave. Suite 107 | Lodi Ca 95240 | Elaine Yip | 66690 | 8715.22 | -29842.81 | 0 | 2026-02-20 | Bridge Replacement | .Near Angels Camp, At West Branch Cherokee Creek Bridge No. 30-0036. Cherokee Creek Bridge | 100 | 86 | 4363934.75 | 4398785 | 4547490.57 | 49624 | 2026-01-25 | 2022-12-01 | 2022-11-18 |  |  | 131 | 0 | 120 | 0 |  | X
10 | 10-1L8004 | 1L8004 | 10-CAL-4-21.8/0 |  |  | S.T. Rhoades Construction, Inc. | Po Box 494520 | Redding Ca 96049 | [5 empty] | 0 | 0 | 0 | 0 |  | Construct A Vehicle Turnout Lane With Hma | Calaveras County Near Angels Camp At 0.1 Mile West Of Murphys Grade Undercrossing | 0 | 0 | 0 | 537517 | 537517 | 60426 |  | 2026-02-18 | 2026-01-23 |  |  | 0 | 0 | 50 | 0
10 | 10-1J8204 | 1J8204 | 10-CAL-12-9.9/10.3 |  | HSST-S012- (001)E | George Reed, Inc. | P.O. Box 4760 | Modesto Ca 95352 | 2095230734 | 2094793608 | 850 South Guild Ave. Suite 107 | Lodica 95240 | Iqbal Aulakh | 6450 | 16599.23 | 0 | 0 | 2026-02-20 | Construct Intersection Signal, Curb Ramps, | Calaveras County In And Near Valley Springs From 0.1 Mile East Of Chestnut Street To 0.1 Mile West Of Lime Creek Road | 61 | 76 | 2848006.88 | 3682280 | 3601159 | 57715 | 2026-03-26 | 2025-04-15 | 2025-03-24 |  |  | 64 | 0 | 105 | 0 |  | X
10 | 10-0X7404 | 0X7404 | 10-CAL-12-17.1/17.5 |  | BFST-S012- (002)E | Steelhead Constructors Jv | 2940 Innsbruck Drive | Redding Ca 96003 | 5302266400 | 5105017727 | 850 South Guild Ave Suite107 | Lodi Ca 95240 | Elaine Yip | 0 | 0 | 0 | 500000 | 2026-02-20 | Bridge Replacement. | Calaveras County Near San Andreas From 0.2Mile West Of North Fork Calaveras River Bridge To 0.2 Mile East Of North Calaverasriver | 0 | 4 | 507000 | 12328635 | 12378635 | 60076 | 2027-06-24 | 2025-09-22 | 2025-09-03 |  |  | 1 | 0 | 440 | 0 |  | X
10 | 10-1K8204 | 1K8204 | 10-CAL-26-18.1/0 |  | SSTG-S026- (033)E | George Reed, Inc. | Po Box 4760 | Modesto Ca 95352 | [5 empty] | 0 | 0 | 0 | 0 |  | Construct Roundabout, Jpcp, Erosion Contro | Calaveras County Near Mokelumne Hill At Intersection Of Junction Route 26 And Route 49 | 0 | 0 | 0 | 4491051 | 4491051 | 60319 |  | 2026-01-14 | 2025-12-01 |  |  | 0 | 0 | 420 | 0
10 | 10-0V4804 | 0V4804 | 10-CAL-26-21.8/30.3 |  | ACST-S026- (032)E | Viking Construction Company, Inc. | 11315 Sunrise Gold Circle Sui | Rancho Cordova Ca 95742 |  | 2092793514 | 19596 Mono Way | Sonora Ca 95370 | Jonathan Ngai | 0 | 157663.33 | -2000 | 0 | 2026-02-20 | Slope Stabilization And Construct Retainin | Calaveras County Near Mokelumne Hill At Various Locations From 3.6 Miles East Of Route 49 To 0.9 Mile West Of Woodhouse Mine Road | 96 | 98 | 7507527.87 | 7197400 | 7600991.25 | 56523 | 2026-03-04 | 2024-10-08 | 2024-09-09 |  |  | 180 | 0 | 180 | 8 |  | X
10 | 10-1H7004 | 1H7004 | 10-CAL-49-7.5/9.4 |  | ACNH-P049- (192)E | George Reed, Inc. | 140 Empire Avenue | Modesto Ca 95354 |  | 5593412018 | 850 S Guild Ave Sute 107 | Lodi, Ca 95240 | Troy Scheiber | 89319 | 33972.02 | 0 | 0 | 2025-12-20 | Construct Curbs Ramps, Sidewalks, Driveway | Calaveras County In Angels Camp From Bret Harte Road To Copello Drive | 2 | 14 | 1006388.75 | 7061213 | 7191213 | 58956 | 2026-08-18 | 2025-06-10 | 2025-05-09 |  |  | 20 | 0 | 985 | 0 |  | X
10 | 10-1J5104 | 1J5104 | 10-MER-99-.6/0 |  |  | Bobo Construction, Inc. | 9722 Kent Street, Suite A | Elk Grove Ca 95624 | [5 empty] | 0 | 0 | 0 | 0 |  | Repair Commercial Vehicle Enforcement Faci | Merced County Near Chowchilla At The Chowchilla River Commercial Vehicle Enforcement Facility | 0 | 0 | 0 | 4012059.94 | 4012059.94 | 60382 |  | 2026-01-30 | 2025-12-10 |  |  | 0 | 0 | 180 | 0
10 | 10-1K0904 | 1K0904 | 10-MER-99-3.3/6.9 |  |  | Empire Landscaping Inc. | 26945 Country Road 97D | Davis Ca 95616 | 5304003943 | 5308703106 | 530 W. 16Th St, Suite D | Merced, Ca 95340 | Jagga Dhami | 8500 | 0 | 0 | 0 | 2026-02-20 | Plant Establishment And Install Decorative | Merced County Near Merced At Various Locations From Plainsburg Road Overcrossing To Le Grand Road Overcrossing | 100 | 64 | 637353.88 | 975210 | 1047420.07 | 50624 | 2029-05-03 | 2023-06-26 | 2023-05-30 |  |  | 453 | 0 | 1385 | 0
10 | 10-1U5204 | 1U5204 | 10-MER-99-12.1/12.1 | 20.20.201330 |  | Coral Construction Company | Po Box 347 | Wilsonville Or 97070 |  | 2094794053 | 3663 Arch Road Suite 500 | Stockton, Ca 95215 | Chris Hansen | 0 | 106606.34 | 0 | 0 | 2026-01-27 | Replace Damaged Sign Structure | Replace Damaged Sign Structure Highway 99 Exit 185 10-1U5204 10A2816 | 100 | 100 | 106606.34 | 1000 | 444695 | 60410 | 2026-01-27 | 2025-07-14 | 2025-05-28 | 2026-02-02 |  | 1 | 0 | 247 | 0 |  | X
10 | 10-3A7214 | 3A7214 | 10-MER-99-19.5/20.7 | HA22 |  | Wabo Landscape & Construction, Inc. | 726 Alfred Nobel Drive | Hercules Ca 94547 | 5107419226 | 5308703106 | 530 W. 16Th St, Suit | Merced Ca 95430 | Jagga Dhami | 990 | 0 | 0 | 0 | 2026-02-20 | Highway Planting And Irrigation | In And Near Atwater, At Atwater - Merced Expressway Interchange. | 0 | 0 | 1341848 | 1399949 | 1386254.92 | 45906 | 2026-11-13 | 2022-12-21 | 2022-11-15 |  |  | 712 | 0 | 900 | 0 | X | X
10 | 10-1M1704 | 1M1704 | 10-MER-140-43.5/43.9 |  | SNHG-P140- (044)E | Yarbs Grading And Paving, Inc. | 11339 S. Peach Avenue | Fowler Ca 93725 | [5 empty] | 0 | 0 | 0 | 0 |  | Construct Roundabout. | Merced County At Planada From 0.2 Mile West Of Plainsburg Road To 0.2 Mile West Of Stutter Street. | 0 | 0 | 0 | 3234820 | 3234820 | 60249 |  | 2025-12-10 | 2025-11-20 |  |  | 0 | 0 | 345 | 0
10 | 10-1L8704 | 1L8704 | 10-MER-165-32.9/0 |  | SSTG-S165- (117)E | Granite Construction Company | 2716 Granite Court | Fresno Ca 93706 | [5 empty] | 0 | 0 | 0 | 0 |  | Install Signal And Lighting System, Curb R | Merced County At Hilmar At Geer Avenue | 0 | 0 | 0 | 1548548 | 1548548 | 60251 |  | 2025-04-02 | 2025-02-21 |  |  | 0 | 0 | 65 | 0
10 | 10-1S6404 | 1S6404 | 10-MER-165-/7 |  |  | A. Teichert & Son, Inc. Dba Teichert Construction | 3500 American River Dr | Sacramento Ca 95864 |  | 5308703106 | 530 W. 16Th Street Suite D | Merced, Ca 95340 | Jagga Dhami | 247166.52 | 0 | 0 | 0 | 2026-02-20 | Resurface Pavement With Rhma And Hma. | Merced County In And Near Los Banos From 0.3 Mile South Of Pole Line Road To 0.2 Mile South Of Mason Road And From 0.1 Mile South | 100 | 93 | 7499613.66 | 8017200 | 7904450 | 59735 | 2026-02-21 | 2025-06-03 | 2025-05-13 |  |  | 85 | 0 | 85 | 0 |  | X
10 | 10-0P9244 | 0P9244 | 10-MPA-140-42.0/42.7 |  | ACST-43M9- (004)E | Myers And Sons/R L Wadsworth Joint Venture | 45 Morrison Avenue | Sacramento Ca 95838 |  | 2094709468 | 19596 Mono Way | Sonora Ca 95370 | Junhao Liu | 9585.94 | 2821568.39 | 931354.65 | 0 | 2026-02-20 | Construct Avalanche Shed. | Mariposa County About 8.0 Miles West Of Elportal From 1.2 Miles West Of South Fork Merced River Bridge To 0.5 Mile West Of South F | 3 | 10 | 35858347.36 | 343657293.94 | 346984639.48 | 60101 | 2031-12-23 | 2025-09-05 | 2025-08-22 |  |  | 46 | 0 | 1500 | 0 |  | X
10 | 10-1R9904 | 1R9904 | 10-SJ-4-.5/.5 | 20.20.201130 |  | Golden State Bridge Inc. | 3701 Mallard Dr. | Benicia, Ca. 94510 |  | 2094794053 | 3663 Arch Road,Suite 500 | Stockton, Ca. 95215 | Chris Hanson | 0 | 0 | 0 | 0 |  | Replace Submarine Cable & Maritime Beacons | Replace Submarine Cable Maritime Navigation Beacons @ Little Potato Slough Bridge. Co.Sj, Rte 4,12, Pm 0.51, 5.00 Dirs Efa 10A2602 | 0 | 0 | 0 | 4875 | 960000 | 56909 | 2026-06-01 | 2023-10-09 | 2023-08-11 |  |  | 0 | 0 | 15 | 0
10 | 10-1U5904 | 1U5904 | 10-SJ-4-14.1/14.1 | 20.20.201130 |  | Valentine Corporation | 111 Pelican Way | San Rafael, Ca 94901 | 4154533732 | 2096078786 | 952 Goodwin Dr, | Ripon, Ca 95366 | Magdy Farid | 0 | 96831.81 | 0 | 0 | 2026-01-20 | Repair Of Fire Damaged Garwood Bridge | Repair Of Fire Damaged Bridge San Joaquin County River Bridge No. 29-0050 Garwood Bridge 10A2858 | 65 | 9 | 96831.81 | 5750 | 1135000 | 60238 | 2026-02-18 | 2025-11-25 | 2025-06-25 |  |  | 39 | 0 | 60 | 0 |  | X
10 | 10-1F1804 | 1F1804 | 10-SJ-4-16.0/19.4 |  | ACNH-P004- (162)E | Viking Construction Company, Inc. | 11315 Sunrise Gold Circle Sui | Rancho Cordova Ca 95742 |  | 5593412018 | 850 So Guild Ave Suite 107 | Lodi, Ca 95240 | Troy Scheiber | 895869.5 | 22343.87 | 0 | 0 | 2026-02-20 | Bridge Work, Concrete Barrier, And Install | San Joaquin County In Stockton At Various Locations From 0.3 Mile East Of Route 4/5 Separation To 0.4 Mile West Of Route 4/99 Sepa | 89 | 85 | 23094214.09 | 26248389.25 | 26831845.66 | 54604 | 2026-03-16 | 2023-10-05 | 2023-09-20 |  |  | 363 | 0 | 380 | 29 |  | X
10 | 10-1C0504 | 1C0504 | 10-SJ-4-19.4/38.1 |  | ACST-S004- (129)E | George Reed, Inc. | Po Box 4760 | Modesto Ca 95352 | [5 empty] | 0 | 0 | 0 | 0 |  | Rhma (Gap Graded), Hma And Cold Plane Asph | San Joaquin And Stanislaus Counties In Andnear Stockton From 1.3 Miles West Of Walker Lane To 0.5 Mile East Of Dunton Road | 0 | 0 | 0 | 17827987.03 | 17827987.03 | 60315 |  | 2026-01-14 | 2025-12-10 |  |  | 0 | 0 | 300 | 0
10 | 10-1L2804 | 1L2804 | 10-SJ-4-20.5/20.8 |  | HSNH-P004- (165)E | O.C. Jones & Sons, Inc. | 1520 Fourth Street | Berkeley Ca 94710 | 5108093437 | 2094835812 | 3663 Arch Road, Suite 500 | Stockton, Ca 95215 | David Abledu | 47802 | 84923.89 | 0 | 0 | 2026-02-20 | Install Left-Turn Channelization. | San Joaquin County Near Stockton From 0.2 Mile West Of Walker Lane To 0.1 Mile East Of Walker Lane | 98 | 96 | 1463142.1 | 1333591.5 | 1496091.5 | 57236 | 2026-03-13 | 2025-02-27 | 2025-01-28 |  |  | 105 | 0 | 60 | 47 |  | X
10 | 10-1R8804 | 1R8804 | 10-SJ-4-141.0/14.1 | 20.20.201130 |  | Myers & Sons Construction Llc. | 45 Morrison Avenue. | Sacramento, Ca. 95838 |  | 2096078786 | 952 Goodwin Dr. | Ripon, Ca.95366 | Magdy Farid | 0 | 64794.04 | 0 | 0 | 2025-06-20 | Repair Garwood Bridgewith Emergency Work.0 | Repair Garwood Bridge (29-0050) Damaged By Firein Sj County. Ct10-1R8804,10230000243 Dirs Efa 10A2592 | 100 | 67 | 652079.21 | 4950 | 975000 | 56192 | 2025-11-15 | 2023-09-18 | 2023-07-14 |  |  | 88 | 0 | 15 | 0
10 | 10-1F3204 | 1F3204 | 10-SJ-4-/8.9 |  | ACNH-P004- (166)E | Bay Cities Paving & Grading, Inc. | 1450 Civic Ct Bldg B #400 | Concord Ca 94520 | [5 empty] | 0 | 0 | 0 | 0 |  | Place Rhma And Replace Asphalt Concrete Su | San Joaquin County Near Discovery Bay Fromold River Bridge To 0.9 Mile East Of Baconisland Road | 0 | 0 | 0 | 9055325 | 9055325 | 60264 |  | 2025-12-22 | 2025-11-14 |  |  | 0 | 0 | 185 | 0
10 | 10-1H3604 | 1H3604 | 10-SJ-4-/0 |  |  | Disney Construction, Inc. | 533 Airport Blvd., Suite 120 | Burlingame Ca 94010 | 6502599545 | 2094835812 | 3663 Arch Road, Suite 500 | Stockton, Ca 95215 | David Abledu | 263588.62 | 0 | 0 | 250061 | 2026-02-20 | Paint Bridge Structural Steel And Place Po | San Joaquin County Near Discovery Bay At Old River Bridge | 14 | 12 | 629210.62 | 5193333 | 5193333 | 60078 | 2026-11-20 | 2025-09-16 | 2025-08-27 |  |  | 31 | 0 | 220 | 0 |  | X
10 | 10-1L3404 | 1L3404 | 10-SJ-5-7.5/0 |  |  | Myers & Sons Construction, Llc | 45 Morrison Ave | Sacramento Ca 95838 | 9162839950 | 2094835812 | 3663 Arch Road, Suite 500 | Stockton, Ca 95215 | David Abledu | 1657858.3 | 0 | 0 | 254000 | 2026-02-20 | Install Jointed Plain Concrete Pavement (R | San Joaquin County Near Tracy At Linne Road Overcrossing | 37 | 74 | 2009736.86 | 2560558 | 2560558 | 60057 | 2026-05-29 | 2025-09-16 | 2025-08-20 |  |  | 22 | 0 | 60 | 0 |  | X
10 | 10-1E3004 | 1E3004 | 10-SJ-5-32.5/49.8 |  | B1IM-0056- (361)E | Bay Cities Paving & Grading, Inc. | 1450 Civic Ct Bldg B #400 | Concord Ca 94520 |  | 2096394686 | 850 S. Guild Avenue Suite 107 | Lodi, Ca 95240 | Ariel Mendoza | 4612362.58 | 58668.89 | 0 | 0 | 2026-02-20 | Remove Existing Pavement And Replace With | San Joaquin County In And Near Stockton From 0.2 Mile South Of Hammer Lane Undercrossing To Sacramento County Line | 66 | 84 | 91183212.73 | 101114962.55 | 103639133.69 | 55909 | 2026-07-24 | 2024-03-08 | 2024-01-12 |  |  | 197 | 0 | 300 | 0 |  | X
10 | 10-1U7104 | 1U7104 | 10-SJ-12-23.9/25.7 | 20.20.201130 |  | Tom Mayo Construction Inc | 4735 E Fremont Street | Stockton Ca 95215 | 2099436248 | 2094794053 | 3663 Arch Road Suite 500 | Stockton Ca 95215 | Chris Hanson | 0 | 0 | 0 | 0 |  | Repair Washout And Failed Overside Drain | Sj-12 Emergency Drainage And Erosion Repair Highway 12 West Of Cord Road 10A2861 | 0 | 0 | 0 | 1000 | 435000 | 60246 | 2025-12-31 | 2025-11-21 | 2025-09-22 |  |  | 0 | 0 | 30 | 0
10 | 10-1T5604 | 1T5604 | 10-SJ-99-7.9/7.9 | 20.20.201130 |  | Valentine Corporation | 111 Pelican Way | San Rafael, Ca. 94901 |  | 2094794053 | 3663 Arch Road, Ste 500 | Stockton, Ca. 95215 | Chris Hanson | 0 | 150828.29 | 0 | 0 | 2025-02-13 | Bidge Girder Repair | Bridge Girder Repair In Sj County At Acampo Rdand Louise Ave,In Sta Co At Kansas Ave10A2765, 10-1T5604 Dirs Efa 10A2765 | 100 | 74 | 878690.86 | 3750 | 1185000 | 57815 | 2026-02-28 | 2024-11-25 | 2024-11-08 |  |  | 221 | 0 | 35 | 0
10 | 10-1N9004 | 1N9004 | 10-SJ-99-21.6/0 |  | HSNH-P099- (694)E | Fbd Vanguard Construction, Inc. | 550 Greenville Road | Livermore Ca 94550 |  | 5593412018 | 850 So Guild Ave Suite 200 | Lodi, Ca 95240 | Troy Scheiber | 0 | 8052 | 28550 | 0 | 2025-11-20 | Replace Guardrail With Concrete Barrier An | San Joaquin County Near Stockton At Wilsonway Overcrossing | 72 | 59 | 470855 | 735010 | 794612 | 57798 | 2025-12-03 | 2025-04-24 | 2025-03-28 |  |  | 18 | 0 | 25 | 0 |  | X
10 | 10-1U1004 | 1U1004 | 10-SJ-99-21.9/21.9 | 20.20.201130 |  | Viking Construction Co Inc. | 3835 Security Park Drive | Rancho Cordova, Ca 95752 |  | 2094794503 | 3663 Arch Road, Suite 500 | Stockton, 95215 | Chris Hanson | 0 | 115662.48 | 0 | 0 | 2026-01-20 | Replace Damaged Girder 1 And Diaphragm1 | Repair Calvaras River Oc Bridge Hit Bridge 290095 10A2779 Dirs Efa 101U1004 | 100 | 68 | 842315.08 | 6250 | 1235000 | 57275 | 2026-11-30 | 2025-02-20 | 2024-12-06 |  |  | 257 | 0 | 100 | 0
10 | 10-1H6504 | 1H6504 | 10-SJ-99-28.7/31.7 | HA25 | ACNH-P099- (681)E | Marina Landscape Inc. | 3707 W Garden Grove Blvd | Orange Ca 92868 |  | 2096394686 | 850 S. Guild Ave. | Lodi, Ca 95240 | Ariel Mendoza | 5520 | 0 | 0 | 0 | 2025-11-20 | Highway Planting And Irrigation. | San Joaquin County In And Near Lodi From 0.4 Mile North Of Harney Lane Overcrossingto 0.2 Mile North Of Turner Road Overcrossing | 0 | 0 | 3637501.29 | 3498360 | 3619013.5 | 55304 | 2028-04-28 | 2023-11-28 | 2023-10-19 |  |  | 146 | 0 | 1000 | 0 | X | X
10 | 10-1C3304 | 1C3304 | 10-SJ-205-4.6/9 | HB4N | ACIM-2056- (356)E | Bay Cities Paving & Grading, Inc. | 1450 Civic Ct | Concord Ca 94520 | 9256876666 | 2096074910 | 952 Goodwin Drive | Ripon Ca 95366 | Harminder Deol | 574970 | 0 | 0 | 0 | 2026-02-20 | Install Its- Phase 2 | In Tracy, West Of Grant Line Road To East Of Macarthur Drive, Install Ramp Meters And Other Intelligent Transportation System (Its | 29 | 66 | 11864272.7 | 17382378.09 | 17815911.59 | 42366 | 2027-01-11 | 2022-05-03 | 2022-04-05 |  | S | 92 | 0 | 300 | 14 |  | X
10 | 10-1U5604 | 1U5604 | 10-SJ-580-12.7/12.7 | 20.20.201130 |  | Golden State Bridge Inc | 3701 Mallard Drive | Benecia Ca 94510 | 9253728000 | 2047940533 | 3663 Arch Road Suite 500 | Stockton Ca 95215 | Chris Hanson | 0 | 0 | 0 | 0 |  | Replace Bay Of Deck For Traffic Detour | Replace Full Length Of Bay 3-4 Of Deck, Install Crossovers For Detours Highway 580 10A2860 | 0 | 0 | 0 | 1000 | 7405000 | 60247 | 2026-12-31 | 2025-11-25 | 2025-09-15 |  |  | 0 | 0 | 50 | 0
10 | 10-1C2704 | 1C2704 | 10-STA-5-27.1/27.4 | HA26 | CIMG-005 - (5 )160 | Tsi Engineering | 4600 Roseville Rd Suite 140 | North Highlands Ca 95660 |  | 5599775907 | 952 Goodwin Dr | Ripon, Ca 95366 | Anwar, Zubair | 344233.24 | 23498.23 | 0 | 0 | 2026-02-19 | Replace Safety Roadside Rest Area. | Stanislaus County About 1.0 Mile South Of San Joaquin County Line At The Westley Safety Roadside Rest Area | 85 | 92 | 19749832.86 | 20375786 | 20789181.7 | 56109 | 2026-04-27 | 2024-04-22 | 2024-03-28 |  |  | 263 | 0 | 310 | 0 |  | X
10 | 10-1R7704 | 1R7704 | 10-STA-99-1.5/16 | 20.20.201130 |  | Sinclair General Engineering Construction, Inc. | P.O. Box 1453 | Oakdale, Ca 95361 |  | 2096094910 | 952 Goodwin Drive | Ripon, Ca 95355 | Harminder Deol | 0 | 0 | 0 | 0 |  | Repair Storm Damage | On Sr 99 In Sta County Between Pms R1.5 And R16 Remove Debris, Stabilize Slopes, Place Slope Protection And Traffic Cntrl Dirs Efa | 0 | 0 | 0 | 2000 | 385000 | 52105 | 2023-09-29 | 2023-05-23 | 2023-03-30 |  |  | 0 | 0 | 15 | 0
10 | 10-1S4904 | 1S4904 | 10-STA-99-17.0/17 | 20.20.201130 |  | Synergy Const & Delopment Corp | 5109 Pomerado Way | Bakersfield Ca 93313 |  | 2094708782 | 952 Goodwin Drive | Ripon Ca 95366 | Obaidullah Rashid | 0 | 101644.12 | 0 | 0 | 2026-01-20 | Replace Fence, Gate And Gate System | Replace Fence And Gate Withvandal-Deterrent Cochraneclear Vuinvisible Wall Fence Andgate System. 10A2730-Dirs Efa | 98 | 95 | 1890503.18 | 9995 | 1984000 | 57026 | 2026-01-28 | 2025-01-01 | 2024-12-31 |  |  | 147 | 0 | 150 | 0 |  | X
10 | 10-1K8404 | 1K8404 | 10-STA-108-33.2/33.5 |  | HSST-P108- (055)E | Mountain Cascade, Inc. | 555 Exchange Court | Livermore Ca 94550 |  | 2096078786 | 952 Goodwin Drive | Ripon, Ca 95366 | Magdy Farid | 0 | 0 | 0 | 53000 | 2026-02-20 | Place Hot Mix Asphalt, Install Signal And | Stanislaus County Near Riverbank From 0.1 Mile West Of Topeka Street To 0.2 Mile East Of Claus Road | 0 | 3 | 53000 | 1940646.8 | 1940646.8 | 59435 | 2026-06-20 | 2025-06-26 | 2025-06-06 |  |  | 0 | 0 | 70 | 0 |  | X
10 | 10-0G8304 | 0G8304 | 10-VAR-59-/0 | HA21 | B1ST-X077- (014)E | Viking Construction Company, Inc. | 11315 Sunrise Gold Circle Sui | Rancho Cordova Ca 95742 |  | 5308703106 | 530 W. 16Th Street Suite D | Merced, Ca 95340 | Jagga Dhami | 149690 | 79623.18 | 0 | 0 | 2026-02-20 | Bridge Seismic Restoration. | Merced County At Various Locations | 98 | 97 | 15733576.16 | 15385439.5 | 15956334.77 | 55084 | 2026-03-03 | 2023-11-27 | 2023-10-31 |  |  | 444 | 0 | 450 | 3 |  | X
10 | 10-1G6204 | 1G6204 | 10-VAR--/0 |  |  | Wylatti Resource Management, Inc. | Po Box 575 | Covelo Ca 95428 |  | 2092793514 | 19596 Mono Way | Sonora Ca 95370 | Jonathan Ngai | 0 | 0 | 0 | 0 |  | Remove And Replace Culverts And Concrete I | Calaveras And Tuolumne Counties At Variouslocations. | 0 | 0 | 0 | 2116207.17 | 2116207.17 | 60257 | 2026-07-02 | 2025-12-15 | 2025-11-13 |  |  | 0 | 0 | 100 | 0
10 | 10-1G0204 | 1G0204 | 10-VAR--/0 |  |  | Studebaker Electric, Inc. | 3237 Rippey Road, Ste 100 | Loomis Ca 95650 | [5 empty] | 0 | 0 | 0 | 0 |  | Install Transportation Management Systems. | Alpine, Amador, And El Dorado Counties At Various Locations | 0 | 0 | 0 | 7348780.16 | 7348780.16 | 60126 |  | 2025-10-16 | 2025-09-29 |  |  | 0 | 0 | 150 | 0
10 | 10-1F2504 | 1F2504 | 10-VAR--/0 |  |  | Wylatti Resource Management, Inc. | 23601 Cemetery Lane | Covelo Ca 95428 |  | 2092793514 | 19596 Mono Way | Sonora Ca 95370 | Jonathan Ngai | 75457.34 | 0 | 0 | 0 | 2026-02-20 | Remove And Replace Drainage Systems. | Calaveras And Tuolumne Counties At Variouslocations | 4 | 3 | 75457.34 | 2523387.52 | 2543387.52 | 60250 | 2026-08-04 | 2025-12-10 | 2025-11-04 |  |  | 5 | 0 | 120 | 0 |  | X
10 | 10-1F9704 | 1F9704 | 10-VAR--/0 |  |  | Pacific Infrastructure Construction, Llc | 871 Cotting Court Ste A | Vacaville Ca 95688 |  | 2096394306 | 952 Goodwin Drive | Ripon, Ca 95366 | Ranbir Bhullar | 765589 | 30716.46 | 0 | 0 | 2026-02-20 | Upgrade Tms Element And Maintenance Vehicl | San Joaquin And Stanislaus Counties At Various Locations | 66 | 61 | 6822971.94 | 10743752 | 11016874 | 57616 | 2026-06-17 | 2025-03-27 | 2025-02-26 |  |  | 158 | 0 | 240 | 0 |  | X
10 | 10-1R7204 | 1R7204 | 10-VAR--/0 |  |  | Mccuen Construction, Inc. | 3269 Swetzer Road | Loomis Ca 95650 | 9166257824 | 2094835812 | 3663 Arch Road, Suite 500 | Stockton, Ca 95215 | David Abledu | 17376 | 0 | 0 | 0 | 2026-01-20 | Place Polyester Concrete Overlay, Traffic | San Joaquin County At Various Locations | 78 | 37 | 1075770.87 | 2861840.58 | 2930840.58 | 59955 | 2026-03-29 | 2025-05-23 | 2025-05-01 |  | S | 78 | 0 | 100 | 0
10 | 10-1L8604 | 1L8604 | 10-VAR--/0 |  |  | Central Coast Financial Group,Inc. Dba Ccfg Construction | 17750 Wards Ferry Rd | Sonora Ca 95370 | [5 empty] | 0 | 0 | 0 | 0 |  | Install New Transportation Management Syst | Amador, Mariposa, And Tuolumne Counties Atvarious Locations. | 0 | 0 | 0 | 2053700 | 2053700 | 60117 |  | 2025-10-08 | 2025-09-15 |  |  | 0 | 0 | 85 | 0
10 | 10-1F9604 | 1F9604 | 10-VAR--/0 |  |  | Studebaker Electric, Inc. | 3237 Rippey Road, Ste 100 | Loomis Ca 95650 | 9162592395 | 2094835812 | 3663 Arch Road, Suite 500 | Stockton, Ca 95215 | David Abledu | 136130.2 | 66886.06 | 0 | 0 | 2026-02-19 | Install Fiber Optic System & Modify Intell | San Joaquin County At Various Locations | 84 | 79 | 5233391.11 | 6298734 | 6573734 | 57339 | 2026-04-07 | 2025-01-24 | 2024-11-19 |  |  | 172 | 0 | 205 | 0 |  | X
10 | 10-0T69U4 | 0T69U4 | 10-VAR--/0 |  | ACST-000C- (571)E | Cal Valley Construction, Inc. | 5125 N Gates Ave Ste 102 | Fresno Ca 93722 | [5 empty] | 0 | 0 | 0 | 0 |  | Hot Mix Asphalt Paving And Install Electri | Merced And Stanislaus Counties At Various Locations | 0 | 0 | 0 | 3919962 | 3919962 | 60316 |  | 2026-01-14 | 2025-12-05 |  |  | 0 | 0 | 110 | 0
11 | 11-432934 | 432934 | 11-IMP-0-/0 | 20.20 201130 |  | Raine General Engineering, Inc | P.O. Box 228 | El Centro Ca 92244 |  | 7606044249 | 4050 Taylor Street | San Diego, Ca 92110 | Rodolfo Guiao | 0 | 121387.76 | 0 | 0 | 2025-12-31 | Repair Storm Damage Due To Monsoonal Storm | Repair Storm Damage Along Sr-78, Sr-86, Sr-111, I-8 And Sr-115Imperial County Dir'S Emergency F. A. | 2 | 91 | 15495242.72 | 97171 | 23485000 | 60125 | 2026-06-30 | 2025-10-14 | 2025-08-25 |  |  | 1 | 0 | 60 | 0 |  | X
11 | 11-2N1764 | 2N1764 | 11-IMP-8-50.3/96.7 |  |  | Pavement Coatings Co. | 10240 San Sevaine Way | Jurupa Valley Ca 91752 |  | 7605942006 | 1102 Montenegro Way | El Centro, Ca 92243 | Jose G. Sillas | 0 | 0 | 0 | 0 |  | Micro-Surfacing, Rhma-G, Shoulder Backing, | Imperial County At Various Locations From 0.2 Mile West Of Bonds Corner Overcrossingto 0.2 Mile East Of Fourth Avenue Overcrossing | 0 | 0 | 0 | 2581165.7 | 2581165.7 | 58598 | 2026-05-12 | 2025-06-09 | 2025-05-01 |  | S | 0 | 0 | 80 | 0
11 | 11-2N1784 | 2N1784 | 11-IMP-8-/10.3 |  |  | Intermountain Slurry Seal, Inc. | 1120 Terminal Way | Reno Nv 89502 |  | 7605942006 | 1102 Montenegro Way | El Centro, Ca 92243 | Jose G. Sillas | 102568.65 | 213962.29 | 0 | 0 | 2026-02-20 | Micro-Surfacing, Cold Plane Ac Pavement, P | Imperial County From Imperial County Line (R0.0R) To 98/8 Flyover (R10.3) And 98/8 Interchange | 95 | 89 | 5105110.97 | 5047889 | 5797889 | 59177 | 2026-02-27 | 2025-06-25 | 2025-05-29 |  |  | 57 | 0 | 60 | 0 |  | X
11 | 11-2N2284 | 2N2284 | 11-IMP-78-/13.2 |  |  | Intermountain Slurry Seal, Inc. | 1120 Terminal Way | Reno Nv 89502 | 8317684020 | 7605912006 | 1102 Montenegro Way | El Centro, Ca 92243 | Jose G. Sillas | 285512.2 | 0 | 0 | 0 | 2025-10-20 | Place Micro-Surfacing, Rumble Strip, And P | Imperial County Near Ocotillo Wells From San Diego County Line To North Junction Route 86 | 100 | 90 | 960483.88 | 1047130 | 1047130 | 59340 | 2026-02-05 | 2025-07-08 | 2025-06-03 |  |  | 50 | 0 | 50 | 0 |  | X
11 | 11-2N2304 | 2N2304 | 11-IMP-86-4.5/L8.5 |  |  | Pavement Coatings Co. | 10240 San Sevaine Way | Jurupa Valley Ca 91752 |  | 7605942006 | 1102 Montenegro Way | El Centro, Ca 92243 | Jose G. Sillas | 305066.24 | 0 | 0 | 0 | 2026-02-20 | Micro-Surfacing, Pavement Marking, Rumble | Imperial County In And Near El Centro And Brawley From Mccabe Road To Imperial Avenue And From I Street To 0.3 Mile Northof New Ri | 97 | 85 | 1880628.69 | 2198568.38 | 2198568.38 | 58637 | 2026-03-15 | 2025-06-09 | 2025-05-02 |  | S | 58 | 0 | 60 | 0 |  | X
11 | 11-2N2264 | 2N2264 | 11-IMP-98-30.0/57 |  |  | Sb General Engineering, Inc. | 12125 Lakeside Avenue | Lakeside Ca 92040 |  | 7605942006 | 1102 Montenegro Way | El Centro, Ca 92243 | Jose G. Sillas | 329057.07 | 0 | 0 | 22000 | 2026-02-20 | Place Rumble Strips And Pavement Delineati | Imperial County In And Near Calexico From 2.3 Miles West Of Route 111 To Evan Hewes Highway | 50 | 52 | 583963.07 | 1123085.26 | 1123085.26 | 58495 | 2026-05-05 | 2025-06-04 | 2025-05-15 |  | S | 30 | 0 | 60 | 0 |  | X
11 | 11-080284 | 080284 | 11-IMP-98-32.1/32.5 |  | ACNH-P098- (029)EPL16-6211- (134) | Spectrum Construction Group, Inc. | 16 Goodyear, Ste. 140 | Irvine Ca 92618 | 9492991400 | 7605942008 | 1102 Montenegro Way | El Centro, Ca 92243 | Daniel Hernandez-Duarte | 163756.9 | 22535.97 | -349966.86 | 0 | 2022-03-20 | Widening Sr-98 Highway From 4 Lanes | In Imperial County In Calexico From Ollie Avenue To 0.1 Mile East Of Rockwood Avenue. | 25 | 18 | 1272123.67 | 6999337.87 | 7246161.17 | 41392 | 2023-03-30 | 2020-12-24 | 2020-12-04 |  |  | 121 | 0 | 475 | 0 |  | X
11 | 11-2N1974 | 2N1974 | 11-IMP-111-23.5/32.1 |  |  | Hazard Construction Company | 10529 Vine Street | Lakeside Ca 92040 |  | 7605942006 | 1102 Montenegro Way | El Centro, Ca 92243 | Jose G. Sillas | 44544 | 0 | 0 | 0 | 2025-12-20 | Cold Plane, Hma-A, Rhma-G, Microsurfacing, | Imperial County Near Brawley And Calipatria At Various Locations From 0.2 Mile South Of Route 78 To 0.4 Mile South Of Route 115 | 90 | 95 | 1554045.61 | 1658805 | 1938805 | 58575 | 2026-03-25 | 2025-06-06 | 2025-04-16 |  | S | 45 | 0 | 50 | 0 |  | X
11 | 11-2N1474 | 2N1474 | 11-IMP-111-50.7/0 |  |  | Rv Concrete, Inc. | 605 E. Commercial Street | Anaheim Ca 92801 | 9148884201 | 7605942006 | 1102 Montenegro Way | El Centro, Ca 92243 | Jose G. Sillas | 0 | 0 | 0 | 0 |  | Repair Two Culverts. | Imperial County Near Salton Sea At Clay Wash And At Frink Wash | 0 | 0 | 0 | 464464 | 464464 | 59318 | 2026-05-02 | 2025-07-08 | 2025-05-22 |  |  | 0 | 0 | 40 | 0
11 | 11-432854 | 432854 | 11-SD-0-/0 | 20.20 201130 |  | Rove Engineering, Inc. | P.O. Box 2108 | El Centro, Ca 92244 |  | 7606044249 | 4050 Taylor Street | San Diego, Ca 92110 | Rodolfo Guiao | 4360.5 | 38521.46 | 0 | 0 | 2025-08-25 | Replace Failed Drainage Systems | Replace Failed Drainage Systems Multiple Locations San Diego County Dir'S Emergency L.B. | 1 | 74 | 1178352.01 | 8721 | 1585000 | 58435 | 2025-12-31 | 2025-05-13 | 2025-04-01 |  |  | 1 | 0 | 90 | 0 |  | X
11 | 11-432784 | 432784 | 11-SD-0-/0 | 20.20 201131 |  | Sb General Engineering Inc | Po Box 1400 | Lakeside, Ca 92040 |  | 6194967561 | 4050 Taylor Street | San Diego, Ca 92110 | Christian Antonio | 0 | 929689.42 | 0 | 0 | 2026-01-30 | Restore Drainage Channel Cross Sections | Clean Drainage Channels Various Locations Along Routes 8,15,78,805San Diego County Dir'S Emergency L.B | 11 | 30 | 2840013.04 | 46920 | 9485000 | 59615 | 2026-07-31 | 2025-07-29 | 2025-06-02 |  |  | 22 | 0 | 200 | 0 |  | X
11 | 11-432674 | 432674 | 11-SD-0-/0 | 20.20 201130 |  | Sb General Engineering, Inc. | Po Box 1400 | Lakeside, Ca 92040 |  | 6195394431 | 4050 Taylor Street | San Diego, Ca 92110 | Ahmad Haidari | 0 | 229015.29 | 0 | 0 | 2026-01-12 | Replace Damaged Tms Elements | Replace Damaged Tms Elements Multiple Locations San Diego County Dir'S Emergency L.B. | 10 | 44 | 1767305.52 | 23899 | 3985000 | 57295 | 2027-12-30 | 2025-02-19 | 2024-12-16 |  |  | 10 | 0 | 100 | 0 |  | X
11 | 11-431274 | 431274 | 11-SD-5-.3/36 |  |  | Kiewit Infrastructure West Co. | 12700 Stowe Drive, Suite 180 | Poway Ca 92064 |  | 6199366265 | 2863 Carmel Valley Road | Del Mar, Ca 92014 | Timothy Poppe | 3240342.11 | 237644.35 | 0 | 0 | 2026-02-20 | Pavement Rehab, Bridge Rehab, Drainage, An | San Diego County At Various Locations Fromcamino De La Plaza Overcrossing To 0.3 Mile South Of Via De La Valle Undercrossing | 29 | 54 | 44040828.11 | 79019295.99 | 81810644 | 57386 | 2028-01-05 | 2025-01-28 | 2025-01-28 |  |  | 191 | 0 | 660 | 0 |  | X
11 | 11-4C0034 | 4C0034 | 11-SD-5-.9/0 |  |  | Hazard Construction Engr Llc | 10529 Vine Street | Lakeside Ca 92040 |  | 8586881520 | 2863 Carmel Valley Rd | Del Mar Ca 92014 | Alfredo Martinez | 0 | 4231.22 | 0 | 0 | 2026-02-20 | Replace Gateway Sign, Install Landscape, H | San Diego County In San Ysidro At The Route 5/805 Separation | 87 | 90 | 1979942.83 | 1597008.5 | 2306913.72 | 50866 | 2026-03-20 | 2023-07-05 | 2023-06-16 |  |  | 359 | 0 | 360 | 55 |  | X
11 | 11-2T0444 | 2T0444 | 11-SD-5-4.4/4.5 |  |  | Flatiron-Skanska-Stacy And Witbeck, A Joint Venture | 12121 Scripps Summit Dr, #400 | San Diego Ca 92131 |  | 8586881435 | 2863 Carmel Valley Rd | Del Mar, Ca 92014 | Steve Mcmillan | 5125020.61 | 0 | -16000 | 0 | 2026-02-20 | Batiquitos Lagoon Double Track Project | San Diego County In Encinitas And Carlsbadfrom La Costa Br 235.17 To 0.1 Miles Northof Avenida Encinas Br 234.5 0.5 Miles Westof R | 31 | 53 | 54545850.34 | 100800000 | 102105444.02 | 56231 | 2029-04-17 | 2024-07-03 | 2024-06-21 |  |  | 362 | 0 | 1155 | 0 |  | X
11 | 11-432304 | 432304 | 11-SD-5-4.6/4.6 | 20.20 201130 |  | Alvarez And Shaw, Inc. | 2101 Alpine Blvd, Ste C | Alpine, Ca. 91901 |  | 6198574332 | 4050 Taylor Street | San Diego, Ca 92110 | Nelmark, Jodi | 0 | 41059.99 | 0 | 0 | 2025-10-13 | Replace Pump System | Replace Pump System And Failed Components In San Diego County Along I-5 At Palm Ave Pump Station Dir'S Emergency L.B. | 1 | 29 | 575413.93 | 15181 | 1985000 | 55588 | 2026-06-19 | 2024-03-01 | 2024-01-26 |  |  | 1 | 0 | 100 | 0 |  | X
11 | 11-4B0334 | 4B0334 | 11-SD-5-9.1/16.1 |  |  | Griffith Company - Henkels & Mccoy Joint Venture | 3050 E. Birch St | Brea Ca 92821 |  | 8586881376 | 1102 Montenegro Way | El Centro, Ca 92243 | Alfredo Hernandez Medina | -5675.28 | 5335 | 0 | 0 | 2026-01-20 | Mmbn Project On Route 005 - Phase 1 | For Construction On State Highway In San Diego County On Route 5 From 0.3 Mile South Of Sweetwater River Bridge To 0.2 Mile South | 98 | 96 | 2416036.02 | 1679439.8 | 1779726.97 | 58836 | 2026-02-28 | 2025-03-06 | 2025-03-06 |  |  | 93 | 0 | 95 | 0 |  | X
11 | 11-4B0044 | 4B0044 | 11-SD-5-9.5/0 |  |  | Griffith Company - Henkels & Mccoy Joint Venture | 3050 E. Birch St | Brea Ca 92821 | 7149845500 | 8586881376 | 1102 Montenegro Way | El Centro, Ca 92243 | Alfredo Hernandez Medina | 325175.19 | 0 | 0 | 0 | 2026-02-20 | Broadband Fiber Optic Network Installation | San Diego County In And Near San Diego, National City And Chula Vista On Route 5 At Mile North Of Sweetwater River Bridge And On R | 99 | 89 | 5702411.24 | 5420180.79 | 5423508.79 | 58957 | 2026-03-31 | 2025-03-12 | 2025-03-12 |  |  | 153 | 0 | 155 | 0 |  | X
11 | 11-432714 | 432714 | 11-SD-5-10.4/10.4 | 20.20 201130 |  | Sb General Engineering, Inc. | Po Box 1400 | Lakeside, Ca 92040 |  | 6199910827 | 4050 Taylor Street | San Diego, Ca 92110 | Carlos G. Lopez | 0 | 860522.79 | 0 | 0 | 2026-02-05 | Bridge Deck Repair Due To Pavement Failure | Bridge Deck Repair Due To Pavement Failurenb I-5 At The 18Th Street Uc(57-0252R) San Diego County Dir'S Emergency L.B. | 8 | 69 | 4109670.79 | 32340 | 5985000 | 58077 | 2026-06-30 | 2025-04-30 | 2025-03-17 |  |  | 5 | 0 | 60 | 0 |  | X
11 | 11-432694 | 432694 | 11-SD-5-19.4/19.4 | 20.20 201130 |  | Rove Engineering, Inc. | Po Box 2108 | El Centro, Ca 92244 | 7604250001 | 6199910827 | 4050 Taylor Street | San Diego, Ca 92110 | Carlos G. Lopez | 0 | 26516.28 | 0 | 0 | 2026-02-24 | Repair Bridge At The Old Town Viaduct | Repair Bridge At The Old Town Viaduct San Diego County Dir'S Emergency L.B | 3 | 52 | 3117603.54 | 41226 | 5985000 | 57975 | 2026-12-31 | 2025-04-14 | 2024-12-30 |  |  | 1 | 0 | 40 | 0 |  | X
11 | 11-2N1754 | 2N1754 | 11-SD-5-30.6/52.8 |  |  | Flatiron West Inc. | 1770 La Costa Meadows Drive | San Marcos Ca 92078 |  | 6193185524 | 4050 Taylor Street | San Diego, Ca 92110 | Alex Balce | 0 | 0 | 57648.5 | 0 | 2026-02-20 | Structural Concrete, Polyester Concrete Ov | San Diego County At Various Locations Fromroute 5/805 Separation To Brooks Street Overcrossing | 100 | 97 | 7629016.91 | 7379228.1 | 7803218.05 | 56196 | 2026-04-01 | 2024-08-06 | 2024-06-28 |  |  | 85 | 0 | 85 | 0 |  | X
11 | 11-2E1544 | 2E1544 | 11-SD-5-34.7/36.3 |  |  | Marathon Construction Corporation | 10108 Riverford Rd | Ca, Lakeside 92040 | 6192764401 | 8582203986 | 990 Highland Dr. #308 | Solana Beach Ca 92075 | Jared Corbitt | 161287.2 | 41054.87 | 0 | 0 | 2026-02-20 | To Lower Existing Elevations At The | In Sdc In Sd From 0.6 Mile North Of Del Mar Heights Rd Overcrossing To Villa De La Valle Underxing. | 52 | 88 | 62751534.3 | 66100000 | 71287891 | 42060 | 2029-09-24 | 2021-12-21 | 2021-12-10 |  |  | 977 | 0 | 1875 | 0 |  | X
11 | 11-2T36U4 | 2T36U4 | 11-SD-5-37.4/52.6 |  | ACIM-0051- (996)E6211-156 - ( )000 | Flatiron-Skanska-Stacy And Witbeck, A Joint Venture | 12121 Scripps Summit Dr #400 | San Diego Ca 92131 |  | 8586881481 | 2863 Carmel Valley Rd | Del Mar, Ca 92014 | Yong Pak | 80564.38 | 171295.72 | 24043.22 | 0 | 2026-02-20 | Construct Multi-Modal Enhancement, Sound W | San Diego County At Various Locations Fromlomas Santa Fe Drive Undercrossing To 0.2 Miles North Of Oceanside Boulevard Undercrossi | 81 | 97 | 82647030.13 | 72520000 | 84391518.57 | 54324 | 2026-11-26 | 2023-11-20 | 2023-10-20 |  |  | 529 | 0 | 650 | 0 |  | X
11 | 11-431004 | 431004 | 11-SD-5-49.3/53.2 |  | ACIM-005 - (1 )999 | Montano Pipeline, Inc. | 231 4Th Ave | Chula Vista Ca 91910 | [5 empty] | 0 | 0 | 0 | 0 |  | Ada Curb Ramps And Realignment Of Mission | San Diego County In Carlsbad And Oceansidefrom Tamarack Avenue Overcrossing To Mission Avenue Overcrossing | 0 | 0 | 0 | 5694017 | 5694017 | 60302 |  | 2026-01-12 | 2025-12-23 |  |  | 0 | 0 | 450 | 0
11 | 11-2N1684 | 2N1684 | 11-SD-5-53.9/63.7 |  |  | Mccuen Construction, Inc. | 3269 Swetzer Road | Loomis Ca 95650 |  | 6193185524 | 4050 Taylor Street | San Diego, Ca 92110 | Alex Balce | 127482.11 | 0 | 0 | 0 | 2025-11-20 | Polyester Concrete, Methacrylate, Joint Se | San Diego County At Various Locations Fromroute 5/76 Separation To Agra Overhead | 71 | 86 | 4208454.01 | 4803824.33 | 4857824.33 | 58296 | 2026-05-01 | 2025-05-22 | 2025-05-02 |  | S | 64 | 0 | 90 | 0 |  | X
11 | 11-430824 | 430824 | 11-SD-5-66.2/67.4 |  |  | Montano Pipeline Dan Scheider | 231 Fourth Avenue | Chula Vista Ca 91910 |  | 7605942034 | 2863 Carmel Valley Road | Del Mar Ca 92014 | Rosemarie Pagunsan | 0 | 0 | 0 | 0 |  | Pcc & Hma Paving, Signs And Striping, Wsms | San Diego County About 12 Miles North Of Oceanside From 1.2 Miles South Of San Onofre Commercial Vehicle Enforcement Facilities To | 0 | 0 | 0 | 3488900 | 3488900 | 60133 | 2027-05-13 | 2025-10-24 | 2025-10-01 |  |  | 0 | 0 | 140 | 0
11 | 11-4B0084 | 4B0084 | 11-SD-8-15.8/21.9 |  |  | Griffith Company - Henkels & Mccoy Joint Venture | 3050 E. Birch St | Brea Ca 92821 | 7149845500 | 8586881376 | 2863 Carmel Valley Rd | Del Mar, Ca 92014 | Alfredo Hernandez Medina | 578305.19 | 0 | 0 | 0 | 2026-02-20 | Mmbn Project On I-8 Pm 15.8/R21.9 | San Diego County In And Near El Cajon Fromroute 8/Route 67 Separation To Lake Jennings Park Road Undercrossing | 95 | 92 | 8513930.99 | 8437204.53 | 8440532.53 | 58958 | 2026-03-31 | 2025-03-13 | 2025-03-13 |  |  | 147 | 0 | 155 | 0 |  | X
11 | 11-432824 | 432824 | 11-SD-8-41.8/41.8 | 20.20 201130 |  | Rove Engineering, Inc. | Po Box 2108 | El Centro, Ca 92244 |  | 6199910827 | 4050 Taylor Street | San Diego, Ca 92110 | Carlos G. Lopez | 0 | 3684695.07 | 0 | 0 | 2026-01-15 | Bridge Deck Repairs | Bridge Deck Repairs Along I-8 At The Pine Valley Creek Bridgessan Diego County Dir'S Emergency L.B | 5 | 43 | 7229689.01 | 59669 | 16685000 | 59236 | 2026-12-31 | 2025-05-21 | 2025-03-17 |  |  | 5 | 0 | 100 | 0 |  | X
11 | 11-433034 | 433034 | 11-SD-8-69.2/69.2 | 20.20 201130 |  | Montano Pipeline, Inc. | 231 4Th Avenue | Chula Vista, Ca 91910 | 6197392504 | 6194554399 | 4050 Taylor Street | San Diego, Ca 92110 | Isabella Evans | 0 | 41640.9 | 0 | 0 | 2026-02-06 | Repair Damage Caused By Vehicle Fire | Repair Damage Caused By Vehicle Fire Along I-8 San Diego County Dir'S Emergency L.B. | 5 | 38 | 548147.66 | 5824 | 1439000 | 60248 | 2026-02-28 | 2025-12-11 | 2025-10-21 |  |  | 2 | 0 | 40 | 0 |  | X
11 | 11-2N2324 | 2N2324 | 11-SD-8-73.0/77.8 |  |  | Intermountain Slurry Seal, Inc. | 1120 Terminal Way | Reno Nv 89502 |  | 7605942006 | 1102 Montenegro Way | El Centro, Ca 92243 | Jose G. Sillas | 7852.66 | 104976.3 | 0 | 0 | 2026-02-20 | Micro-Surfacing, Striping, Rumble Stripe, | San Diego County Near Jacumba From 0.9 Mile West Of Carrizo Road Undercrossing Toimperial County Line | 95 | 94 | 2804335.91 | 3006843.92 | 3176843.92 | 58317 | 2026-02-27 | 2025-05-23 | 2025-04-28 |  |  | 57 | 0 | 60 | 0 |  | X
11 | 11-430194 | 430194 | 11-SD-15-.4/10.2 |  | PTIM-015 - (4 )211 | Hazard Construction Company | 10529 Vine Street | Lakeside Ca 92040 |  | 8586881376 | 2863 Carmel Valley Road | Del Mar, Ca 92014 | Genaro Genel | 690212 | 106662.8 | 0 | 0 | 2026-02-20 | Culvert Restoration, Tunnel Co Monitoring | San Diego County In San Diego From 0.2 Mile South Of Route 5/15 Separation To 0.4Mile South Of Route 52/15 Separation. | 22 | 39 | 5989029.05 | 15072875 | 15461002.1 | 58577 | 2027-07-09 | 2025-06-06 | 2025-04-16 |  |  | 99 | 0 | 445 | 0 |  | X
11 | 11-432444 | 432444 | 11-SD-15-2.1/2.2 | 20.20 201130 |  | Montano Pipeline, Inc. | 231 4Th Ave | Chula Vista, Ca 91910 |  | 6194909264 | 4050 Taylor Street | San Diego, Ca 92110 | Aguilar, Pedro | 0 | 24184.07 | 0 | 0 | 2025-04-19 | Repair Drainage Channel | Repair Drainage Channel Due To Storm Eventin San Diego County In San Diego Along Theeb-94 And Sb I-15 Connector Ramp. Dir'S Emerge | 69 | 57 | 1353948.71 | 21357 | 2385000 | 55786 | 2025-12-31 | 2024-05-08 | 2024-02-01 |  |  | 55 | 0 | 80 | 0 |  | X
11 | 11-430514 | 430514 | 11-SD-15-31.3/37.1 |  | ACSB-0154- (210)E | Security Paving Company, Inc. | 3075 Townsgate Road | Westlake Village Ca 91361 | 8183629200 | 8586881473 | 871 N Broadway | Escondido, Ca 92025 | Jason Alsheikh | 17816.85 | 88436.13 | 0 | 0 | 2026-02-20 | Mainline Pavement Rehabilitation, | In San Diego County In And Near Escondido From 0.2 Mile South Of Route 15/78 Separaton To 0.5 Mile North Of Deer Springs Road Ove | 100 | 92 | 41015378.98 | 45969872 | 45449452.65 | 42665 | 2026-03-30 | 2022-06-27 | 2022-05-27 |  |  | 524 | 0 | 450 | 74 |  | X
11 | 11-432914 | 432914 | 11-SD-15-45.0/4.5 | 20.80 240000 |  | Montano Pipeline, Inc. | 231 4Th Avenue | Chula Vista, Ca 91910 |  | 6195394431 | 4050 Taylor Street | San Diego, Ca 92110 | Ahmad Haidari | 0 | 62080.86 | 0 | 0 | 2026-02-20 | Install Encampment Exclusionary Measures | Install Encampment Exclusionary Measures Along I-15 And I-805 San Diego County Dir'S Emergency L.B. | 10 | 84 | 831051.08 | 4190 | 985000 | 60102 | 2026-12-31 | 2025-10-03 | 2025-09-22 |  |  | 6 | 0 | 60 | 0 |  | X
11 | 11-430254 | 430254 | 11-SD-52-5.1/9 |  | ACNH-P052- (021)E | Scj Csi Cja A Joint Venture | 9685 Via Excelencia Ste 200 | San Diego Ca 92126 |  | 6199367067 | 5377 Otay Mesa Rd | San Diego, Ca 92110 | Karl Hartline | 636695.43 | 375003.67 | -442444.4 | 0 | 2025-12-20 | Const Aux Lane, Compaction Grouting, Rhma, | San Diego County In San Diego From 0.4 Mile West Of Convoy Street Overcrossing To0.3 Mile East Of Santo Road Overcrossing | 53 | 93 | 55141373.51 | 54685000 | 58541101.24 | 55064 | 2027-05-27 | 2024-01-29 | 2023-12-21 |  |  | 395 | 0 | 750 | 0 |  | X
11 | 11-411904 | 411904 | 11-SD-56-.3/9.7 |  |  | Montano Pipeline Inc | 231 Fourth Ave | Chula Vista Ca 91910 | 6198386848 | 8586881435 | 2863 Carmel Valley Rd | Del Mar, Ca 92014 | Steve Mcmillan | 6022.4 | 1210.32 | 0 | 0 | 2026-02-20 | Construct Rock Blanket, Fence, Striping, L | San Diego County At Various Locations Fromel Camino Real Undercrossing To Route 56/15 Separation | 100 | 94 | 2963927.3 | 3076495 | 3173507.09 | 55504 | 2026-10-01 | 2024-03-21 | 2024-02-13 |  |  | 334 | 0 | 325 | 0 |  | X
11 | 11-2T3644 | 2T3644 | 11-SD-56-.3/3 |  |  | Granite Construction Company | 580 W Beach Street | Watsonville Ca 95076 |  | 8586881435 | 2863 Carmel Valley Rd | Del Mar, Ca 92014 | Steve Mcmillan | -17556 | 1738.91 | 53100 | 0 | 2026-02-20 | Construct Jpcp, Hma, Rhma-G, Signs, Barrie | San Diego County In San Diego From El Camino Real Undercrossing To 0.3 Mile Westof Carmel Valley Road Overcrossing | 55 | 98 | 17372383.92 | 17984025.07 | 17894994.33 | 53827 | 2026-10-01 | 2023-11-14 | 2023-10-17 |  |  | 308 | 0 | 550 | 8 |  | X
11 | 11-4B0054 | 4B0054 | 11-SD-67-3.9/6.1 |  |  | Griffith Company - Henkels & Mccoy Joint Venture | 3050 E. Birch St | Brea Ca 92821 | 7149845500 | 9167098761 | 1102 Montenegro Way | El Centro Ca 92243 | Sanchez Del Real Ignacio | 69497.93 | 0 | 0 | 0 | 2026-01-20 | In San Diego County Near Santee On Route 6 | San Diego County Near Santee On Route 67 From Riverford Road Undercrossing To Lakeside Avenue | 69 | 14 | 381655.22 | 2814749.74 | 2814749.74 | 59035 | 2026-03-25 | 2025-03-12 | 2025-03-12 |  |  | 59 | 0 | 85 | 0 |  | X
11 | 11-430314 | 430314 | 11-SD-67-4.1/15.9 |  | PTST-P067- (077)E | Hazard Construction Engr, Llc | 10529 Vine Street | Lakeside Ca 92040 | 8585873600 | 6196020333 | 817 Sweetwater Road | Spring Valley, Ca 91977 | Sultan Ghazialam | 300589 | 0 | 0 | 0 | 2026-02-20 | Culvert Restoration, Replace Signs, Ada Cu | San Diego County From 0.2 Mile North Of Riverford Road At Lakeside To Ellie Lane In Poway | 4 | 3 | 300589 | 11526444 | 11526444 | 60252 | 2028-06-02 | 2025-12-17 | 2025-11-21 |  |  | 22 | 0 | 550 | 0 |  | X
11 | 11-2N0204 | 2N0204 | 11-SD-76-17.2/24.1 |  |  | Griffith Company | 3050 E. Birch St | Brea Ca 92821 |  | 6194032596 | 4050 Taylor St. | San Diego, Ca 92110 | Fahad Masud | 16500 | 5610 | 0 | 0 | 2026-01-20 | Cold Plane And Overlay With Rhma Gap Grade | San Diego County Near Pala From Route 76/15 Separation To Pala Mission Road | 100 | 94 | 5208859.15 | 4422244 | 4852143 | 56071 | 2026-04-01 | 2024-07-12 | 2024-06-14 |  |  | 97 | 0 | 60 | 3 |  | X
11 | 11-430274 | 430274 | 11-SD-76-17.5/52.2 |  | ACST-S076- (033)E | Interstate Civil Construction | 6025 Park Dr | Wrightwood Ca 92397 | [5 empty] | 0 | 0 | 0 | 0 |  | Culvert Restoration, Install Curb Ramps, G | San Diego County At Various Locations From0.2 Mile East Of Route 15 To 0.1 Mile Westof Route 79 | 0 | 0 | 0 | 8483781.25 | 8483781.25 | 60303 |  | 2026-01-12 | 2025-12-18 |  |  | 0 | 0 | 520 | 0
11 | 11-431644 | 431644 | 11-SD-78-/N17.7 |  | ACNH-P078- (123)E | Skanska Usa Civil West California District Inc. | 1995 Agua Mansa Road | Riverside Ca 92509 |  | 8586881481 | 871 N. Brodway | Escondido, Ca 92025 | Yong Pak | 3186657.12 | 23299.69 | 0 | 2040000 | 2026-02-20 | Sr-78 Asset Management | Pavement Rehab, Ada,Its, Op, Improvements,Complete Streets, Bridge Rail Upgrade, Safety | 25 | 30 | 31051277.45 | 102000000 | 103663191.48 | 58116 | 2028-02-24 | 2025-03-21 | 2025-02-25 |  |  | 165 | 0 | 670 | 0 |  | X
11 | 11-2N2244 | 2N2244 | 11-SD-79-.6/52.9 |  |  | Gba Engineering, Inc. | 18543 Yorba Linda Blvd #394 | Yorba Linda Ca 92886 |  | 6193185524 | 4050 Taylor Street | San Diego, Ca 92110 | Alex Balce | 45108 | 0 | 0 | 0 | 2026-02-20 | Remove And Install Roadside Signs. | San Diego County Near Descanso From 0.6 Mile North Of Route 8/79 Separation To 0.1Mile South Of Riverside County Line | 73 | 89 | 523450 | 585835 | 585835 | 58297 | 2026-04-01 | 2025-05-23 | 2025-05-08 |  |  | 73 | 0 | 100 | 0 |  | X
11 | 11-430814 | 430814 | 11-SD-79-11.2/20.2 |  | ACST-S079- (049)E | R.J. Noble Company | 15505 East Lincoln Avenue | Orange Ca 92856 | [5 empty] | 0 | 0 | 0 | 0 |  | Cold Plane, Place Rhma, Replace Railing, D | San Diego County Near Julian From 0.6 Milesouth Of Wolahi Road To East Junction Route 78 And Near Warner Springs From Westjunction | 0 | 0 | 0 | 22715595 | 22715595 | 60318 |  | 2026-01-14 | 2025-12-02 |  |  | 0 | 0 | 300 | 0
11 | 11-430364 | 430364 | 11-SD-79-20.2/53 |  |  | Nationwide Contracting Services, Inc. Dba Nationwide General Construction Services | 7660 Liberty Dr | Huntington Beach Ca 92647 |  | 8586881433 | 7177 Opportunity Road | San Diego, Ca 92111 | Ryan Sresovich | 693005.51 | 0 | 0 | 0 | 2026-02-20 | Culvert Repair, Guardrail, Flashing Beacon | San Diego County At Various Locations Fromwest Junction Route 78 To Riverside Countyline | 68 | 49 | 3014576.31 | 5969061 | 6116061 | 58076 | 2026-05-14 | 2025-05-09 | 2025-03-19 |  |  | 122 | 0 | 180 | 0 |  | X
11 | 11-2N2064 | 2N2064 | 11-SD-94-1.6/13.3 |  |  | Truesdell Corporation Of California, Inc. | 1310 W. 23Rd Street | Tempe Az 85282 |  | 6194032596 | 4050 Taylor Street | San Diego, Ca 92110 | Fahad Masud | 346609.49 | 4450 | 0 | 0 | 2026-02-20 | Polyester Concrete, Methacrylate, Joint Se | San Diego County At Various Locations From22Nd Street Overcrossing To Avocado Boulevard Overcrossing | 90 | 95 | 3796809 | 3659659 | 3738649.7 | 58875 | 2026-03-01 | 2025-06-17 | 2025-06-03 |  |  | 100 | 0 | 110 | 1 |  | X
11 | 11-430264 | 430264 | 11-SD-94-15.2/65.3 |  | ACST-X073- (157)E | Lb Civil Construction, Inc. | 324 East Valley Parkway | Escondido Ca 92025 | [5 empty] | 0 | 0 | 0 | 0 |  | Drainage Restoration, Ada Curb Ramps & Com | San Diego County About 6 Miles East Of Lemon Grove On Route 94 From Sweetwater River Bridge To Avenue De Robles Verdes Near Manzan | 0 | 0 | 0 | 7765462 | 7765462 | 60379 |  | 2026-01-30 | 2026-01-08 |  |  | 0 | 0 | 370 | 0
11 | 11-430244 | 430244 | 11-SD-125-9.3/13 |  | B1NH-P125- (021)E | Hazard Construction Engr Llc | 10529 Vine Street | Lakeside Ca 92040 |  | 6196020333 | 817 Sweetwater Rd | Spring Valley, Ca 91977 | Sultan Ghazialam | 10720 | 7231.14 | 0 | 0 | 2026-02-20 | Place Hma, Rhma, Slab Replacement, And Ele | San Diego County In And Near Lemon Grove From 0.3 Mile South Of Elkelton Place Undercrossing To 0.2 Mile South Of Route 125/94 Sep | 91 | 94 | 32822851.77 | 29997770.55 | 33468444.14 | 53044 | 2026-07-06 | 2023-10-05 | 2023-09-06 |  |  | 463 | 0 | 510 | 0 |  | X
11 | 11-411404 | 411404 | 11-SD-125-9.6/13.2 | HA | ACNH-P125- (020)E | Spectrum Construction Group, Inc. | 16 Goodyear, Suite 140 | Irvine Ca 92618 | 9492991400 | 6196020333 | 817 Sweetwater Road | Spring Valley, Ca 91977 | Sultan Ghazialam | 136237.93 | 0 | 0 | 0 | 2022-04-20 | Roadside Safety Improvements. | In San Diego County In San Diego And Lemon Grove From 0.1 Mile South Of Elkelton Place Undercrossing To Route 94/125 Separation | 16 | 21 | 672142.54 | 3086723.65 | 3186723.65 | 41864 | 2023-06-19 | 2021-09-14 | 2021-08-11 |  |  | 65 | 0 | 400 | 0 |  | X
11 | 11-4B0124 | 4B0124 | 11-SD-125-12.9/22.3 |  |  | Griffith Company - Henkels & Mccoy Joint Venture | 3050 E. Birch St | Brea Ca 92821 |  | 6196020333 | 817 Sweetwater Road | Spring Valley, Ca 91977 | Sultan Ghazialam | 2063836.65 | 240234 | 0 | 0 | 2026-02-20 | Installation Of Fiber Optic Conduit System | San Diego County On Route 125 From 0.6 Mile South Of Spring Street Undercrossing Near La Mesa To Mission Gorge Road In Santee | 94 | 93 | 7428464.53 | 5594070.32 | 7969439.79 | 58835 | 2026-05-15 | 2025-03-12 | 2025-03-12 |  |  | 160 | 0 | 170 | 0 |  | X
11 | 11-4B0394 | 4B0394 | 11-SD-163-.7/3.1 |  |  | Griffith Company - Henkels & Mccoy Joint Venture | 3050 E. Birch St | Brea Ca 92821 |  | 9167098761 | 1102 Montenegro Way | El Centro Ca 92243 | Sanchez Del Real Ignacio | 543469.28 | 0 | 0 | 192.36 | 2026-02-20 | Install Conduit, Fiber Optic Cable, Jct Bo | San Diego County On Route 5 From 0.3 Mile South Of Sweetwater River Bridge To 0.2 Mile South Of Sixth Avenue Overcrossing | 96 | 57 | 1478787.48 | 2369990.29 | 2369990.29 | 58975 | 2026-03-05 | 2025-03-12 | 2025-03-12 |  |  | 77 | 0 | 80 | 0
11 | 11-4B0384 | 4B0384 | 11-SD-163-3.1/10.9 |  |  | Griffith Company - Henkels & Mccoy Joint Venture | 3050 E. Birch St | Brea Ca 92821 |  | 8586881376 | 2863 Carmel Valley Road | Del Mar, Ca 92014 | Alfredo Hernandez Medina | 510048.66 | 256993.92 | 8049.6 | 0 | 2026-01-20 | Mmbn Project On Route 163-Phase 1. Install | San Diego County In San Diego From 0.6 Mile South Of Route 8/163 Separation To 0.1 Mile North Of Kearny Villa Road Overcrossing | 98 | 97 | 3151360.64 | 2035741.55 | 3161164.29 | 58915 | 2026-02-27 | 2025-03-12 | 2025-03-12 |  |  | 118 | 0 | 120 | 0 |  | X
11 | 11-430484 | 430484 | 11-SD-163-4.3/10.8 |  |  | Hazard Construction Engr Llc | 10529 Vine Street | Lakeside Ca 92040 |  | 8586881376 | 2863 Carmel Valley Road | Del Mar, Ca 92014 | Genaro Genel | 18260 | 31228.77 | 0 | 0 | 2026-02-20 | Upgrade Roadside Safety Elements, Electric | San Diego County In San Diego At Various Locations From 0.1 Mile South Of Friars Road Overcrossing To Kearny Villa Road Overcrossi | 84 | 98 | 8675059.31 | 7689119.28 | 8542850.77 | 54704 | 2026-04-21 | 2024-01-10 | 2023-12-06 |  |  | 327 | 0 | 390 | 0 |  | X
11 | 11-430234 | 430234 | 11-SD-805-.1/14.6 |  | ACIM-8051- (647)E | Griffith Company | 13400 Sabre Springs Ste 200 | San Diego Ca 92128 |  | 8586881473 | 5377 Otay Mesa Road | San Diego Ca 92154 | Jason Alsheikh | 113182.43 | 0 | 0 | 0 | 2026-02-20 | Replace Conc Pvmt, Construct Aux Lane & Bi | San Diego County In San Diego, Chula Vistaand National City From 0.3 Mile South Of Route 805/5 Separation To Route 805/15 Separati | 1 | 0 | 195682.43 | 138758858 | 139747858 | 60132 | 2032-08-20 | 2025-10-23 | 2025-10-02 |  |  | 13 | 0 | 1150 | 0 |  | X
11 | 11-2N1714 | 2N1714 | 11-SD-805-.5/14.6 |  |  | Peterson-Chase General Engineering Construction, Inc. | 16351 Construction Circle Wes | Irvine Ca 92606 |  | 9166394314 | 4050 Taylor St | San Diego, Ca 92110 | John Tran | 244472.66 | 17637.79 | 0 | 0 | 2026-02-20 | Methacrylate Replace Approach Slabs, Joint | San Diego County At Various Locations Fromsouth Route 805/5 Separation To Route 805/15 Separation | 80 | 89 | 8850403.83 | 9224063.6 | 9523045.59 | 56101 | 2026-03-01 | 2024-07-24 | 2024-06-28 |  |  | 136 | 0 | 170 | 0 |  | X
11 | 11-2T3434 | 2T3434 | 11-SD-805-5.1/8.3 |  | TPLN-6211- (139)000 | Walsh Construction Company Ii,Llc | 1390 Willow Pass Road Suite 9 | Concord Ca 94520 |  | 8586881511 | 817 Sweetwater Road | Spring Valley, Ca 91977 | Tan Cao | 1185426.74 | 82692.74 | 25155.38 | 0 | 2026-02-20 | Soundwalls, Widen Freeway, Structures, Lan | San Diego County In Chula Vista From Palomar Street Overcrossing To 0.5 Mile North Of Bonita Road Undercrossing | 51 | 56 | 18827836.08 | 32678020 | 33520247.28 | 55344 | 2027-12-31 | 2024-02-28 | 2024-01-29 |  |  | 433 | 0 | 850 | 0 |  | X
11 | 11-432944 | 432944 | 11-SD-805-11.2/13.3 | 20.80 240000 |  | Lb Civil Construction, Inc. | 324 East Valley Parkway | Escondido, Ca 92025 | 7602940974 | 6199910827 | 4050 Taylor Street | San Diego, Ca 92110 | Carlos G. Lopez | 0 | 203939.64 | 0 | 0 | 2026-02-05 | Install Encampment Exclusionary Mearusres | Install Encampment Exclusionary Mearusres Along I-805 From Division St To Hilltop Drsan Diego County Dir'S Emergency L.B. | 8 | 87 | 857719.61 | 10000 | 985000 | 60154 | 2026-09-16 | 2025-10-09 | 2025-09-22 |  |  | 5 | 0 | 60 | 0 |  | X
11 | 11-430324 | 430324 | 11-SD-805-14.6/23.7 |  | ACIM-8051- (645)E | Coffman Specialties, Inc. | 9685 Via Excelencia, Suite 20 | San Diego Ca 92126 |  | 6199957332 | 1463 Broadway | El Cajon, Ca 92021 | Art Pannu | 1821747.21 | 40742.69 | 0 | 0 | 2026-02-20 | Modify Electrical, Concrete Pavement, Drai | San Diego County In San Diego From Route 805/15 Separation To 0.1 Mile North Of Route 805/52 Separation | 36 | 37 | 28774645.99 | 76865000 | 77399779.27 | 56335 | 2027-10-21 | 2024-09-10 | 2024-08-23 |  |  | 249 | 0 | 700 | 0 |  | X
11 | 11-430384 | 430384 | 11-SD-805-23.7/28.5 |  | ACIM-805 - (1 )646 | Hazard Construction Engr, Llc | 10529 Vine Street | Lakeside Ca 92040 |  | 8586881443 | 5377 Otay Mesa Rd | San Diego, Ca 92154 | Tai Lam | 1971005.52 | 77926.32 | 12252.78 | 0 | 2026-02-20 | Replace Drainage, Concrete Pavement, And M | San Diego County In San Diego From 0.1 Mile North Of Route 805/52 Separation To Route 5/805 Separation | 35 | 78 | 28636242.12 | 34966331.1 | 35749132.11 | 56682 | 2027-12-31 | 2024-10-30 | 2024-10-09 |  |  | 246 | 0 | 695 | 0 |  | X
11 | 11-430394 | 430394 | 11-SD-805-23.9/25.1 |  | ACIM-805 - (1 )644 | Griffith Company | 12200 Bloomfield Ave | Santa Fe Springs Ca 90670 |  | 7605942021 | 817 Sweetwater Rd | Spring Valley, Ca 91977 | Tyler Jones | 2940 | 0 | 0 | 0 | 2026-02-20 | Widen Freeway, Structures, Construct Signs | San Diego County In San Diego From 0.2 Mile North Of Route 805/52 Separation To 0.3 Mile South Of Nobel Drive Overcrossing | 86 | 100 | 23174310.63 | 22322322 | 23304865.41 | 54044 | 2026-06-02 | 2023-11-30 | 2023-11-03 |  |  | 486 | 0 | 565 | 0 |  | X
11 | 11-432024 | 432024 | 11-SD--/0 | 20.20 201130 |  | E-4 Construction Inc Dba Cali Construction | 12935 Pomerado Rd Suite C | Poway, Ca 92064 | 6192082401 | 8586881480 | 4050 Taylor St | San Diego, Ca 92110 | Kemp, Lauren | 36000 | 0 | 0 | 0 | 2024-05-20 | Tree Removal | In San Diego County And Imperial County On Various Routes At Various Locations Tree Removal Dir'S Emergency L.B. | 46 | 98 | 1947224.77 | 60000 | 1985000 | 53605 | 2025-06-30 | 2023-10-27 | 2023-06-30 |  |  | 91 | 0 | 200 | 0 |  | X
11 | 11-2N2074 | 2N2074 | 11-VAR--/0 |  |  | Truesdell Corporation Of California, Inc. | 1310 W. 23Rd Street | Tempe Az 85282 |  | 6194559259 | 4050 Taylor Street | San Diego, Ca 92110 | Peris Salih | 206949.15 | 0 | 0 | 0 | 2026-02-20 | Grind Bridge Decks, Polyester Concrete Ove | San Diego County At Various Locations | 100 | 90 | 3874379.61 | 4197197 | 4263447 | 58599 | 2026-03-01 | 2025-06-09 | 2025-05-23 |  |  | 90 | 0 | 90 | 0 |  | X
11 | 11-430904 | 430904 | 11-VAR--/0 |  |  | J. Francis Company | 16197 Krameria Ave. | Riverside Ca 92504 |  | 6199367037 | 2863 Carmel Valley Road | Del Mar, Ca 92014 | Navid Borzouei | 200828.9 | 0 | 0 | 0 | 2026-02-20 | Resurface Bridge, Replace Bridge Barrier, | San Diego County At Various Locations | 56 | 97 | 8271953.6 | 8454740.75 | 8715219.28 | 57315 | 2026-09-11 | 2025-03-13 | 2025-02-12 |  |  | 183 | 0 | 325 | 0 |  | X
11 | 11-2N2334 | 2N2334 | 11-VAR--/0 |  |  | Pavement Coatings Co. | 10240 San Sevaine Way | Jurupa Valley Ca 91752 |  | 6194032596 | 4050 Taylor Street | San Diego, Ca 92110 | Fahad Masud | 239849.68 | 139232.6 | 0 | 0 | 2025-11-20 | Microsurfacing, Cold Plane, Hma Type A, Si | San Diego County At Various Locations | 100 | 85 | 1070058.84 | 1061767.95 | 1268367.84 | 58815 | 2026-03-01 | 2025-06-12 | 2025-05-22 |  |  | 51 | 0 | 50 | 1 |  | X
11 | 11-2N1774 | 2N1774 | 11-VAR--/0 |  |  | Griffith Company | 3050 E. Birch St | Brea Ca 92821 |  | 6194559259 | 4050 Taylor St. | San Diego, Ca 92110 | Peris Salih | 4625 | 17000.1 | 0 | 0 | 2025-12-20 | Micro-Surfacing, Hma, Pavement Marking And | San Diego County At Various Locations | 100 | 94 | 2975423.68 | 3314000 | 3146117.98 | 56311 | 2026-03-01 | 2024-09-04 | 2024-06-24 |  |  | 71 | 0 | 55 | 3 |  | X
11 | 11-430344 | 430344 | 11-VAR--/0 |  | ACNH-X073- (156)E | Griffith Company | 3050 E. Birch St | Brea Ca 92821 | [5 empty] | 0 | 0 | 0 | 0 |  | Culverts Restoration, Rhma, Jpcp, Isr, Bar | San Diego County At Various Locations | 0 | 0 | 0 | 64818818 | 64818818 | 60407 |  | 2026-02-10 | 2026-01-21 |  |  | 0 | 0 | 705 | 0
11 | 11-2N2254 | 2N2254 | 11-VAR--/0 |  |  | Specialized Pavement Marking, Llc | 11095 Sw Industrial Way, Suit | Tualatin Or 97062 |  | 7605942006 | 1102 Montenegro Way | El Centro, Ca 92243 | Jose G. Sillas | 0 | 0 | 0 | 0 |  | Install Rumble Strips And Place Pavement D | San Diego And Imperial Counties At Variouslocations | 0 | 0 | 0 | 1168200 | 1168200 | 59339 | 2026-05-25 | 2025-07-08 | 2025-04-18 |  |  | 0 | 0 | 55 | 0
12 | 12-0V4404 | 0V4404 | 12-0RA-241-30.0/31 | 20.XX 201130 |  | Powell Constructors Inc | 8555 Banana Avenue | Fontana, Ca 92335 | 9093568880 | 9493929174 | 15700 Tustin Village Way, #2 | Tustin, Ca 92780 | Tran, Tuan/Ce-Kim, Steven | 0 | 192317.96 | 0 | 0 | 2026-02-20 | Reconstruct The Failed Slope And Roadway. | In Orange County, On Northbound Sr241 Justsouth Of Loma Ridge Toll Plaza. Reconstruct The Failed Slope And Roadway. Dir'S Order E | 100 | 39 | 2576048.13 | 29456 | 6592000 | 57258 | 2026-02-28 | 2025-01-29 | 2025-01-23 |  |  | 198 | 0 | 180 | 0
12 | 12-0R3114 | 0R3114 | 12-LA-91-20.6/20.7 |  | ACNH-P091- (159)E | Beador Construction Company, Inc. | 2900 Bristol Street, Suite D2 | Costa Mesa Ca 92626 | 9516747352 | 5624497999 | 15700 Tustin Village Way | Tustin, Ca 92780 | Luna, Franklin | 397000.49 | 0 | 0 | 0 | 2026-02-20 | Place Jpcp (Rsc) And Rhma, And Modify Elec | Los Angeles And Orange Counties From 0.1 Mile West Of The Los Angeles County Line In Cerritos To 0.1 Mile East Of Acacia Street Un | 30 | 46 | 20119658.46 | 42861700 | 43485439.07 | 57455 | 2027-10-01 | 2025-03-14 | 2025-03-03 |  |  | 198 | 0 | 660 | 0 |  | X
12 | 12-0S7504 | 0S7504 | 12-ORA-1-.8/0 |  | ACNH-P001- (697)E | Beador Construction Company, Inc. | 2900 Bristol Street D204 | Costa Mesa Ca 92626 | 9516747352 | 9492798466 | 4 Venture, Suite 150 | Irvine, Ca 92618 | Sidhu,Gangadeep/Ce-Essayli, M. | 143990.08 | 0 | 0 | 0 | 2025-12-20 | Modify Traffic Signal, Lighting, Curb Ramp | Orange County In Dana Point At Doheny Parkroad Undercrossing | 89 | 89 | 2974489.26 | 3095300 | 3290300 | 56122 | 2026-01-15 | 2024-07-19 | 2024-07-02 | 2026-02-11 |  | 133 | 0 | 150 | 0 |  | X
12 | 12-0P69U4 | 0P69U4 | 12-ORA-1-5.5/7.9 |  | ACST-P001- (680)E | Griffith Company | 12200 Bloomfield Ave | Santa Fe Springs Ca 90670 |  | 4244131143 | 15700 Tustin Village Way | Tustin, Ca 92780 | Merati, Artin | 145345.4 | 304964.33 | 16188.68 | 0 | 2026-02-20 | Reconstruct Curb Ramps And Cold Plane Pave | Orange County In Laguna Beach From 7Th Avenue To Ruby Street | 100 | 93 | 15858774.66 | 16163520 | 16968815.89 | 50527 | 2026-02-23 | 2023-06-08 | 2023-04-20 |  |  | 399 | 0 | 400 | 0 |  | X
12 | 12-0M82U4 | 0M82U4 | 12-ORA-1-7.9/10.5 |  | ANCH-P001- (673)E | Spectrum Construction Group, Inc. | 16 Goodyear, Ste. 140 | Irvine Ca 92618 | 9492991400 | 9492798502 | 15700 Tustin Village Way | Tustin Ca 92780 | Berrios, Jose/Ce- Zokai, Farid | 15840 | 0 | 0 | 0 | 2022-04-20 | Upgrade Sidewalk To Americans With | In Orange County In Laguna Beach, On State Route 1 (Also Known As Pacific Coast Highway Or Sr-1) From Ruby Street (Pm 7.9) To Led | 30 | 13 | 1218562.4 | 9580910.45 | 9668673.33 | 41453 | 2023-06-01 | 2021-02-18 | 2021-01-26 |  |  | 127 | 0 | 430 | 0 |  | X
12 | 12-0P68U4 | 0P68U4 | 12-ORA-1-13.0/33.7 |  | ACST- P00- (682)E | Chumo Construction Inc. | 14425 Joanbridge Street | Baldwin Park Ca 91706 |  | 9492798880 | 4 Venture Ste 150 | Irvine, Ca 92618 | Blanco, Chris/Ce- Karam, Imad | 345035.04 | 14493.27 | 0 | 0 | 2026-02-20 | Cold Plane, Place Rhma And Modify Curb Ram | Orange County At Various Locations From Crystal Heights Drive To Los Angeles/Orange County Line | 100 | 96 | 37234667.03 | 36829575.68 | 38401470.02 | 52104 | 2026-03-31 | 2023-08-23 | 2023-07-12 |  |  | 433 | 0 | 330 | 0 |  | X
12 | 12-0S1404 | 0S1404 | 12-ORA-1-21.5/31.1 |  | HSNH-P001- (700)E | Chumo Construction Inc. | 14425 Joanbridge Street | Baldwin Park Ca 91706 | 6269609502 | 9492795213 | 4 Venture Suite 150 | Irvine, Ca 92618 | Karam, Imad | 610640 | 54876.14 | 0 | 250000 | 2026-02-20 | Install Conc Barrier, Curb, Hma Pvmt, Traf | Orange County In And Near Huntington Beachand Seal Beach From Santa Ana River Bridgeto Anderson Street And At Seal Beach Boulevard | 14 | 18 | 1975241.34 | 10578115.72 | 10856871 | 56826 | 2027-09-20 | 2024-11-20 | 2024-10-22 |  |  | 64 | 0 | 450 | 0 |  | X
12 | 12-0T8604 | 0T8604 | 12-ORA-5-2.3/19.9 |  |  | Peterson-Chase General Engineering Construction, Inc. | 16351 Construction Circle Wes | Irvine Ca 92606 |  | 9492798502 | 15700 Tustin Village Way | Tustin, Ca | Merati, Artin | 43869 | 0 | 0 | 0 | 2026-02-20 | Apply Methacrylate And Polyester Concrete | Orange County At Various Locations From Avenida Presidio Undercrossing To Lake Forest Drive Overcrossing | 90 | 66 | 1720726.41 | 2386997.7 | 2548613.55 | 55789 | 2026-03-01 | 2024-05-13 | 2024-03-13 |  |  | 81 | 0 | 90 | 0
12 | 12-0U9204 | 0U9204 | 12-ORA-5-6.5/0 |  | HSIM-0052- (051)E | Ptm General Engineering Services, Inc. | 5942 Acorn St. | Riverside Ca 92504 | [5 empty] | 0 | 0 | 0 | 0 |  | Signal Modification And Sign Installation. | Orange County In San Juan Capistrano At 0.2 Mile South Of Route 5/1 Separation Andat 0.4 Mile North Of Route 5/1 Separation | 0 | 0 | 0 | 488088 | 488088 | 58776 |  | 2025-06-12 | 2025-05-15 |  |  | 0 | 0 | 50 | 0
12 | 12-0S2804 | 0S2804 | 12-ORA-5-9.6/10.4 |  | HSIM-0052- (045)E | Powell Constructors Inc | 8555 Banana Avenue | Fontana Ca 92335 |  | 9492798640 | 4 Venture, Ste 150 | Irvine, Ca 92618 | Vazquez, Luis/Ce- Karam, Imad | 362472 | 4804.81 | 0 | 0 | 2026-02-20 | Add Secondary Auxiliary Lane. | Orange County In San Juan Capistrano From Route 74/5 Separation To 0.5 Mile South Ofjunipero Serra Road Undercrossing | 100 | 86 | 4778169.07 | 5075573 | 5510143.32 | 56121 | 2026-03-06 | 2024-07-22 | 2024-06-24 |  |  | 289 | 0 | 290 | 0 |  | X
12 | 12-0S3804 | 0S3804 | 12-ORA-5-10.0/21.3 |  | ACIM-0052- (056)E | Beador Construction Company, Inc. | 2900 Bristol Street, Suite D2 | Costa Mesa Ca 92626 | 9516747352 | 4244131143 | 15700 Tustin Village Way | Tustin, Ca | Vuong, Tai/Ce-Merati, Artin | 220000 | 0 | 0 | 0 | 2026-02-20 | Slab Replacement (Rsc), Rhma-Paving, Signa | Orange County From El Horno Street Undercrossing In San Juan Capistrano To Route 405/5 Separation In Irvine | 9 | 1 | 277500 | 30700300 | 30715300 | 60174 | 2027-04-12 | 2025-11-10 | 2025-10-20 |  |  | 29 | 0 | 315 | 0 |  | X
12 | 12-0K0244 | 0K0244 | 12-ORA-5-12.4/18.9 |  |  | Diverscape, Inc. Dba Diversified Landscape Co. | 21730 Bundy Canyon Road | Wildomar Ca 92595 |  | 9493929174 | 15700 Tustin Village Way | Tustin, Ca 92780 | Tran, Tuan/Ce- Kim, Steven | 201493.95 | 0 | 0 | 0 | 2026-02-20 | Replace Landscaping And Irrigation. Instal | Orange County From 0.5 Mile South Of Averyparkway Undercrossing In San Juan Capistrano To 0.2 Mile North Of El Toro Road Undercros | 54 | 51 | 4354178.67 | 8312913.3 | 8624934.32 | 58715 | 2029-08-02 | 2025-06-10 | 2025-05-07 |  |  | 134 | 0 | 1000 | 0 |  | X
12 | 12-0K61U4 | 0K61U4 | 12-ORA-5-21.3/25.8 |  | ACIM-0052- (059)E | Security Paving Company, Inc. | 3075 Townsgate Road, Ste 200 | Westlake Village Ca 91361 | [5 empty] | 0 | 0 | 0 | 0 |  | Const Bridges, Rw, Sw, Overlay, Replace Sl | Orange County In Irvine From Route 5/405 Separation To Yale Avenue Overcrossing | 0 | 0 | 0 | 165748150.35 | 165748150.35 | 60404 |  | 2026-02-11 | 2026-01-29 |  |  | 0 | 0 | 975 | 0
12 | 12-0K62U4 | 0K62U4 | 12-ORA-5-25.8/30.3 |  | ACIM-0052- (058)E | Granite Construction Company | 4820 Mcgrath St., Suite 101 | Ventura Ca 93003 |  | 9492893551 | 230 Commerce, Suite 180 | Irvine, Ca 92602 | Ware, Elizabeth | 54578.59 | 0 | 0 | 0 | 2026-02-20 | Const Bridge, Rw, Sw, Pavement, Drainage, | Orange County In Irvine And Tustin From Yale Avenue Overcrossing To Route 5/55 Separation | 1 | 0 | 54578.59 | 147515937.38 | 147515937.38 | 60342 | 2030-01-08 | 2025-12-10 | 2025-11-12 |  |  | 8 | 0 | 980 | 0 |  | X
12 | 12-0S3104 | 0S3104 | 12-ORA-5-26.3/42.2 |  | HSIM-0052- (044)E | Autobahn Construction Inc. | 933 N. Batavia St. | Orange Ca 92867 |  | 9492798491 | 15700 Tustin Village Way | Tustin, Ca | Ruba, Nabil/Ce- Merati, Artin | 21928 | 0 | 0 | 0 | 2025-10-20 | Refresh Pavement Delineation, Replace Sign | Orange County At Various Locations From Culver Driver Overcrossing In Irvine To Route 91/5 Separation In Fullerton | 99 | 92 | 2272661.25 | 2341485 | 2376485 | 55787 | 2025-11-30 | 2024-05-13 | 2024-03-22 |  |  | 138 | 0 | 140 | 0 |  | X
12 | 12-0J34U4 | 0J34U4 | 12-ORA-5-29.6/29.6 |  | ACNH-X059- (084)E | Security Paving Company, Inc. | 3075 Townsgate Road | Westlake Village Ca 91361 | 8183629200 | 9492798488 | 1221 E. Dyer Road, Suite #265 | Santa Ana, Ca 92705 | Wu, Adrian | 3064157.33 | 240383.19 | 0 | 0 | 2026-02-20 | Construct Northbound Auxiliary Lane | In Orange County In Irvine, Santa Ana, And Tustin On Rte 5 At Newport Ave Undercrossing And On Rte 55 From 0.4 Mi North Of Rte 55 | 69 | 66 | 132044936.86 | 193587475.71 | 201177066.51 | 42479 | 2028-04-14 | 2022-06-16 | 2022-05-27 |  |  | 643 | 0 | 880 | 54 |  | X
12 | 12-0S8404 | 0S8404 | 12-ORA-5-36.7/0 |  | HSIM-0052- (052)E | Baker Electric & Renewables, Llc | 1298 Pacific Oaks Place | Escondido Ca 92029 |  | 9492798801 | 3350 E Birch Street, Ste 250 | Brea, Ca 92821 | Chaudry, Monas | 0 | 0 | 0 | 35000 | 2026-02-20 | Modify Existing Traffic Signals, Curb Ramp | Orange County In Anaheim 0.1 Mile North Ofanaheim Boulevard Undercrossing | 2 | 3 | 35000 | 1140951 | 1185071.58 | 59655 | 2026-12-18 | 2025-08-12 | 2025-06-11 |  | S | 4 | 0 | 210 | 0 |  | X
12 | 12-0S1104 | 0S1104 | 12-ORA-22-.9/9.4 |  | HSNH-P022- (031)E | Beador Construction Company, Inc. | 2900 Bristol Street D204 | Costa Mesa Ca 92626 |  | 5624497999 | 15700 Tustin Village Way | Tustin, Ca 92780 | Luna, Franklin | 1803657.05 | 205464.95 | 0 | 0 | 2026-02-20 | Replace Concrete Barrier And Modify Lighti | Orange From Bolsa Chica Road Overcrossing In Garden Grove To Lewis Street Overcrossing In Orange | 66 | 75 | 22642157.9 | 29300700 | 29825700 | 56534 | 2026-09-25 | 2024-10-10 | 2024-09-04 |  |  | 298 | 0 | 450 | 0 |  | X
12 | 12-0S7004 | 0S7004 | 12-ORA-22-8.6/0 |  | ACNH-P022- (032)E | Autobahn Construction, Inc. | 933 N. Batavia St. | Orange Ca 92867 |  | 9492798744 | 15700 Tustin Village Way | Tustin, Ca 92780 | Luna, Franklin | 77343.2 | 0 | 0 | 0 | 2026-01-22 | Install High Friction Surface Treatment At | Orange County In Garden Grove At 0.2 Mile West Of Garden Grove Boulevard Undercrossing | 100 | 100 | 419845.9 | 395976 | 419868.7 | 57156 | 2026-01-22 | 2025-02-12 | 2025-01-09 | 2026-01-22 |  | 50 | 0 | 50 | 0 |  | X
12 | 12-0S1904 | 0S1904 | 12-ORA-22-11.6/12.5 |  | HSNH-P022- (030)E | Ortiz Enterprises, Inc. | 6 Cushing Suite 200 | Irvine Ca 92618 |  | 9515297048 | 15700 Tustin Village Way | Tustin, Ca 92780 | Luna. Franklin | 1650 | 0 | 0 | 0 | 2026-02-20 | Auxiliary Lane Extension. | Orange County In Santa Ana And Orange From0.1 Mile West Of Santiago Creek To 0.2 Mile East Of Cambridge Street Overcrossing | 74 | 100 | 7339373.96 | 6851174.28 | 7286480.91 | 56070 | 2026-02-24 | 2024-07-12 | 2024-06-06 |  |  | 345 | 0 | 320 | 145 |  | X
12 | 12-0R32U4 | 0R32U4 | 12-ORA-55-.2/17.8 |  | ACNH-P055- (067)E | R.J. Noble Company | 15505 East Lincoln Avenue | Orange Ca 92856 |  | 9492798488 | 15700 Tustin Village Way | Tustin, Ca 92780 | Wu, Adrian | 2350353.1 | 94751.87 | 0 | 0 | 2026-02-20 | Cold Plane, Place Rhma, Replace Cb, Signs | Orange County From 0.1 Mile South Of Route55/1 Separation In Newport Beach To Route 55/91 Separation In Anaheim | 18 | 20 | 21362646.13 | 106148205.6 | 107346645.6 | 57395 | 2028-07-11 | 2025-03-18 | 2025-02-07 |  |  | 142 | 0 | 750 | 18 |  | X
12 | 12-0S3304 | 0S3304 | 12-ORA-57-11.0/22.6 |  | HSNH-P057- (075)E | Chumo Construction Inc. | 14425 Joanbridge Street | Baldwin Park Ca 91706 |  | 9492798491 | 15700 Tustin Village Way | Tustin, Ca | Ruda, Nabil/Ce- Merati, Artin | 6625 | 4114.23 | 0 | 0 | 2026-02-20 | Modify Lighting And Replace Pavement Delin | Orange County In Orange And Brea From 0.2 Mile South Of Chapman Avenue Undercrossingto Orange County Line | 100 | 92 | 8374151.34 | 8661572.2 | 8945400.64 | 55921 | 2026-02-28 | 2024-06-05 | 2024-05-03 |  |  | 217 | 0 | 200 | 0 |  | X
12 | 12-0M9704 | 0M9704 | 12-ORA-57-11.5/12.5 |  | TPLN-6212- (027)000 | Ortiz Enterprises, Inc. | 6 Cushing Suite 200 | Irvine Ca 92618 |  | 9492795213 | 4 Venture Suite 150 | Irvine, Ca 92618 | Al-Saleh ,A./Ce-Karam, I. | 449361.39 | 0 | 0 | 0 | 2026-02-20 | Const Bridges, Ret Walls, Jpcp, Hma, Conc | Orange County In Orange And Anaheim From 0.2 Mile South Of Orangewood Avenue Undercrossing To Katella Avenue Undercrossing | 5 | 9 | 5796827.41 | 68141634.66 | 68141634.66 | 60121 | 2029-04-06 | 2025-10-13 | 2025-09-25 |  |  | 41 | 0 | 825 | 0 |  | X
12 | 12-0K93U4 | 0K93U4 | 12-ORA-57-13.9/16.1 |  | ACNH-X059- (088)ECDSL-6212- (033)000 | Ohla Usa, Inc. | 34 Executive Park, Suite 180 | Irvine Ca 92614 |  | 5624497999 | 15700 Tustin Village Way | Tustin, Ca 92780 | Luna, Franklin | 34500 | 0 | 0 | 0 | 2026-02-20 | Const Bridges, Rw, Sw, Pavement, Drainage | Anaheim And Placentia On Route 57 From Wagner Avenue Overcrossing To 0.2 Mile North Of Miraloma Avenue Overcrossing And On Route 9 | 1 | 0 | 34500 | 127765447.52 | 127765447.52 | 60214 | 2030-09-09 | 2025-12-01 | 2025-10-20 |  |  | 6 | 0 | 1140 | 0 |  | X
12 | 12-0S5304 | 0S5304 | 12-ORA-57-15.9/0 |  | HSNH-P057- (077)E | Granite Construction Company | 4820 Mcgrath St., Suite 101 | Ventura Ca 93003 | 8317684020 | 9492798502 | 15700 Tustin Village Way | Tustin, Ca | Berrios, Jose/Ce- Merati,Artin | 268726.4 | 2720.38 | 0 | 0 | 2026-02-20 | Place Jpcp (Rsc) And Hma, Modify Ramp And | Orange County In Anaheim At Southbound Route 57 Off-Ramp To Westbound Route 91 | 32 | 22 | 1148127.73 | 5295527 | 5305527 | 60081 | 2026-10-14 | 2025-09-22 | 2025-09-05 |  |  | 77 | 0 | 240 | 0 |  | X
12 | 12-0U9804 | 0U9804 | 12-ORA-57-19.6/20.1 |  |  | R.J. Noble Company | 15505 East Lincoln Avenue | Orange Ca 92856 | 7146371550 | 9498928208 | 15700 Tustin Village Way | Tustin, Ca 92780 | Tai, Vuong/Ce- Merati, Artin | 17814.5 | 0 | 0 | 0 | 2026-02-20 | Cold Plane And Overlay Existing Pavement W | Orange County In Brea And Fullerton On Route 57 From Associated Road Undercrossing To 0.2 Mile South Of Birch Street Undercrossing | 100 | 94 | 951408.7 | 1009857 | 1009857 | 57006 | 2026-04-15 | 2025-01-15 | 2024-12-11 |  | S | 60 | 0 | 60 | 0 |  | X
12 | 12-0C1114 | 0C1114 | 12-ORA-57-20.3/21.6 |  |  | Diversified Landscape Co. | 21730 Bundy Canyon Road | Wildomar Ca 92595 | 9512451686 | 9493929229 | 15700 Tustin Village Way | Tustin, Ca 92780 | Pham, Theodore/Ce- Kim, Steven | 1236.8 | 0 | 0 | 0 | 2025-12-20 | Placement Planting And New | In Orange County In Brea At Lambert Road | 0 | 0 | 1015139.82 | 998968.5 | 1052014.46 | 43424 | 2026-11-19 | 2022-07-19 | 2022-06-22 |  |  | 440 | 0 | 680 | 0 | X | X
12 | 12-0U5904 | 0U5904 | 12-ORA-73-10.3/26.8 |  |  | Peterson-Chase General Engineering Construction, Inc. | 16351 Construction Circle Wes | Irvine Ca 92606 |  | 9492798590 | 4 Venture Ste 135 | Irvine, Ca 92618 | Shahidi, Mona/Ce Nguyen, Irvin | 17428.5 | 0 | 0 | 0 | 2025-12-20 | Apply Methacrylate, Replace Joint Seals & | Orange County At Various Locations From S73-S5 Connector Viaduct In Laguna Niguel To Bristol Street Undercrossing In Costa Mesa | 98 | 83 | 1052987.87 | 1240447.68 | 1312786.88 | 58336 | 2026-02-22 | 2025-05-23 | 2025-04-02 |  | S | 78 | 0 | 80 | 0 |  | X
12 | 12-0P0314 | 0P0314 | 12-ORA-74-11.5/16.6 |  | ACST-S074- (076)E | Pacific Restoration Group, Inc. | 506 W Graham Avenue, Suite 20 | Lake Elsinore Ca 92530 | 9514574118 | 9492798511 | 10681 Pamela Street | Cypress, Ca 90630 | Nowak, John/Ce-Karam, Imad | 10494 | 0 | 0 | 0 | 2026-02-20 | Establish Existing Planting. | Orange County Near San Juan Capistrano From 1.0 Mile West Of San Juan Hot Springsroad To Riverside County Line | 30 | 41 | 229561.25 | 553475 | 553475 | 56315 | 2028-09-08 | 2024-09-04 | 2024-08-07 |  |  | 295 | 0 | 1000 | 0 |  | X
12 | 12-0R3134 | 0R3134 | 12-ORA-91-6.4/9.2 |  | ACNH-P091- (158)E | Peterson-Chase General Engineering Construction, Inc. | 16351 Construction Circle Wes | Irvine Ca 92606 | 9492520441 | 9498863914 | 15700 Tustin Village Way | Tustin, Ca 92780 | Zadeh, Ali | 1651509.05 | 200 | 0 | 0 | 2026-02-20 | Place Jpcp, Remove Conc Pvmt And Base, And | Orange County In Anaheim From 0.3 Mile East Of Route 91/57 Separation To 0.1 Mileeast Of Route 91/55 Separation | 28 | 37 | 7056330.63 | 18914449.5 | 18964449.5 | 57078 | 2026-12-24 | 2025-01-29 | 2024-11-26 |  |  | 84 | 0 | 300 | 0 |  | X
12 | 12-0K91U4 | 0K91U4 | 12-ORA-91-9.2/11.4 |  | ACNH-P091- (156)ECDSL-6212- (031)000 | Granite Construction Company | 4820 Mcgrath St., Suite 101 | Ventura Ca 93003 |  | 9492798821 | 15700 Tustin Village Way | Tustin, Ca 92780 | Kim, Steven | 1705455.93 | 105124.4 | 0 | 0 | 2026-02-20 | Const Bridges, Rw, Sw, Pavement, Drainage | Orange County In Anaheim From 0.9 Mile West To 1.3 Miles East Of Lakeview Avenue Overcrossing | 22 | 31 | 25106792.89 | 78658036.1 | 80314220.14 | 57157 | 2027-08-16 | 2025-02-12 | 2025-01-03 |  |  | 199 | 0 | 917 | 0 |  | X
12 | 12-0R3154 | 0R3154 | 12-ORA-91-10.8/18.9 |  | ACNH-P091- (157)E | Powell Constructors, Inc. | 8555 Banana Avenue | Fontana Ca 92335 |  | 9492798412 | 15700 Tustin Village Way #2 | Tustin, Ca 92780 | Pham, Theodore/Ce- Kim, Steven | 313836 | 34368.19 | 0 | 0 | 2026-02-20 | Modify Fiber Optic Cable, Signal, Lighting | Orange County In Anaheim And Yorba Linda From 0.7 Mile West Of Route 90 To Riverside County Line | 30 | 37 | 4007748 | 10469301 | 10799101 | 57047 | 2027-12-29 | 2025-01-21 | 2025-01-02 |  |  | 210 | 0 | 690 | 0 |  | X
12 | 12-0P94U4 | 0P94U4 | 12-ORA-133-3.2/4.1 |  | ACNH-P133- (018) | Granite Construction Company | 5860 El Camino Real | Carlsbad Ca 92008 | 7604441032 | 5624497999 | 15700 Tustin Village Way | Tustin, Ca 92780 | Luna, Franklin | 22366.5 | 641275.78 | 0 | 0 | 2026-02-20 | Roadway Widening, Restriping And | In Orange County, In The City Of Laguna Beach, From 0.2 Mile South Of El Toro Road To Route 73/133 Separation | 39 | 88 | 12011336.43 | 6845845 | 13441993.36 | 41518 | 2030-07-09 | 2021-03-11 | 2021-02-23 |  | S | 708 | 0 | 1800 | 0 |  | X
12 | 12-0N8904 | 0N8904 | 12-ORA-133-8.3/M9.3 |  | ACNH-P133- (019)E | Security Paving Company, Inc. | 13170 Telfair Ave | Sylmar Ca 91342 |  | 9515297048 | 15700 Tustin Village Way | Tustin, Ca 92780 | Luna, Franklin | 105786.5 | 29195.36 | 0 | 0 | 2026-02-20 | Construct Auxiliary Lane. | Orange County In Irvine From Route 133/405Separation To Irvine Center Drive Overcrossing | 83 | 96 | 21503885.67 | 21301897 | 21721897 | 54284 | 2027-07-21 | 2023-12-06 | 2023-11-09 |  |  | 497 | 0 | 600 | 0 |  | X
12 | 12-0Q9804 | 0Q9804 | 12-ORA-241-14.5/25.7 |  | ACNH-P241- (010)E | Chumo Construction Inc. | 14425 Joanbridge Street | Baldwin Park Ca 91706 |  | 9492893551 | 4 Venture Suite 150 | Irvine, Ca 92618 | Ware, Elizabeth | 1501666.27 | 104346.33 | -10852.8 | 0 | 2026-02-20 | Treat Bridge Deck With Methacrylate, Insta | Orange County From Oso Parkway In Rancho Santa Margarita To 0.7 Mile North Of Portola Parkway Overcrossing In Irvine | 65 | 69 | 15600984.29 | 21285988.87 | 22639073.02 | 56589 | 2026-07-21 | 2024-10-01 | 2024-08-30 |  |  | 194 | 0 | 300 | 0 |  | X
12 | 12-0Q9704 | 0Q9704 | 12-ORA-405-.2/11.4 |  | ACIM-4052- (003)E | Guy F. Atkinson Construction, Llc Dba Guy F. Atkinson | 611 Anton Blvd., Suite 1100 | Costa Mesa, Ca 92626 |  | 9492798590 | 15700 Tustin Village Way | Tustin, Ca 92780 | Shahidi, Mona/Ce-Nguyen, Irvin | 7945112.5 | 137106.21 | 0 | 0 | 2026-02-20 | Pavement Rehab, Roadside Safety Improvemen | In Orange County In Irvine And In Orange County In Irvine And Costa Mesa On Rte 405 From I-5 To Harbor Blvd | 90 | 81 | 176019308.85 | 216030188.2 | 216089089.61 | 52744 | 2026-05-18 | 2023-08-18 | 2023-07-27 |  |  | 565 | 0 | 625 | 0 |  | X
12 | 12-0R57U4 | 0R57U4 | 12-ORA-405-11.4/24.2 |  | ACIM-4052- (004)E | Security Paving Company, Inc. | 3075 Townsgate Road, Suite 20 | Westlake Village Ca 91361 |  | 9498863914 | 15700 Tustin Village Way | Tustin, Ca 92780 | Leon, Mario/Ce- Zadeh, Ali | 3384268.36 | 4710.4 | 0 | 172500.07 | 2026-02-20 | Place Jpcp (Rsc) And Rhma, And Modify Elec | Orange County From Harbor Boulevard Undercrossing In Costa Mesa To Los Angelescounty Line At Rossmoor | 16 | 63 | 27076076.24 | 41668479 | 41896479 | 57176 | 2028-07-26 | 2025-02-18 | 2025-01-14 |  |  | 119 | 0 | 730 | 0 |  | X
12 | 12-0R6804 | 0R6804 | 12-ORA-605-.2/1.6 |  | HSIM-6052- (995)E | Chumo Construction Inc. | 14425 Joanbridge Street | Baldwin Park Ca 91706 |  | 9492798826 | 3350 E Birch St, Ste 250 | Brea, Ca 92821 | Najm, Elie | 277770.5 | 71822.7 | 0 | 0 | 2026-02-20 | Modify Lighting Systems. | Orange And Los Angeles Counties In Los Alamitos And Long Beach From 0.2 Mile North Of Route 605/405 Separation To 0.2 Mile North O | 71 | 77 | 5882988.59 | 7240143.17 | 7651666.6 | 55910 | 2026-07-20 | 2024-06-05 | 2024-05-10 |  |  | 270 | 0 | 380 | 1 |  | X
12 | 12-0K8704 | 0K8704 | 12-ORA-605-.6/1.6 |  | TPLN-6212- (032)000 | Ortiz Enterprises, Inc. | 6 Cushing Suite 200 | Irvine Ca 92618 |  | 9492798838 | 10355 Los Alamitos Blvd | Los Alamitos, Ca 90720 | Zadeh, Ali | 410889.7 | 0 | 0 | 0 | 2026-02-20 | Modify Ramps, Lighting And Ramp Metering S | Orange County In Los Alamitos From 0.8 Mile South To 0.2 Mile North Of Katella Avenue Undercrossing | 22 | 28 | 7166973.76 | 24892102.9 | 25186342.9 | 57857 | 2027-03-12 | 2025-04-25 | 2025-04-03 |  |  | 142 | 0 | 650 | 6 |  | X
12 | 12-0R5604 | 0R5604 | 12-VAR-55-5.5/17.8 | HA22 | ACNH-X059- (087)E | Security Paving Company, Inc. | 13170 Telfair Ave | Sylmar Ca 91342 |  | 4244131143 | 4 Venture, Ste 150 | Irvine, Ca 92618 | Ware, Elizabeth | 48653 | 40638.97 | 0 | 0 | 2026-01-20 | Place Rhma-G, Hma, Slab Replacement And Jp | Orange County At Various Locations | 53 | 91 | 36060319.38 | 37466672 | 39452621.33 | 50424 | 2026-08-28 | 2023-06-08 | 2023-04-12 |  |  | 375 | 0 | 625 | 80 |  | X
12 | 12-0U7904 | 0U7904 | 12-VAR--/0 |  |  | Specialized Pavement Marking, Llc | 11095 Sw Industrial Way Suite | Tualatin Or 97062 |  | 5624497999 | 15700 Tustin Village Way | Tustin, Ca 92780 | Luna, Franklin | 74778 | 0 | 0 | 0 | 2025-12-20 | Install Pvmt Marking, Signs, Rumble Strips | Orange County At Various Locations | 100 | 71 | 1027891.1 | 1445832.5 | 1418071.1 | 58515 | 2026-03-12 | 2025-06-04 | 2025-04-30 |  | S | 81 | 0 | 80 | 0

## Report 2
District | EA | Contract ID | CNTY_RT_PM
01 | 0P4304 | 01-0P4304 | 01-DN-101-2.0/16.5
01 | 0G1004 | 01-0G1004 | 01-DN-101-12.5/15.5
01 | 0K9504 | 01-0K9504 | 01-DN-101-15.6/16.2
01 | 436404 | 01-436404 | 01-DN-101-35.8/36.5
01 | 0L4304 | 01-0L4304 | 01-DN-101-39.2/39.7
01 | 0J2104 | 01-0J2104 | 01-DN-101-2.6/23.9
01 | 0L9904 | 01-0L9904 | 01-DN-199-.5/.8
01 | 0J8904 | 01-0J8904 | 01-HUM-36-3.9/6
01 | 0C5004 | 01-0C5004 | 01-HUM-36-11.3/34.6
01 | 0H6104 | 01-0H6104 | 01-HUM-36-13.5/36.1
01 | 461704 | 01-461704 | 01-HUM-36-25.4/0
01 | 0P1804 | 01-0P1804 | 01-HUM-36-25.4/26
01 | 0P8204 | 01-0P8204 | 01-HUM-36-155.0/16.5
01 | 0P9504 | 01-0P9504 | 01-HUM-36-170.0/24
01 | 0P9004 | 01-0P9004 | 01-HUM-36-190.0/20.1
01 | 0Q0304 | 01-0Q0304 | 01-HUM-36-279.0/27.9
01 | 0F9204 | 01-0F9204 | 01-HUM-96-43.7/0
01 | 0Q2004 | 01-0Q2004 | 01-HUM-96-400.0/.1
01 | 464804 | 01-464804 | 01-HUM-101-1.1/2.5
01 | 0H6404 | 01-0H6404 | 01-HUM-101-2.4/M53.9
01 | 0H6504 | 01-0H6504 | 01-HUM-101-55.9/136.4
01 | 0K9404 | 01-0K9404 | 01-HUM-101-74.8/76.1
01 | 0N6604 | 01-0N6604 | 01-HUM-101-78.0/79.6
01 | 366004 | 01-366004 | 01-HUM-101-80.0/84
01 | 0K1504 | 01-0K1504 | 01-HUM-101-125.2/126.1
01 | 0P8704 | 01-0P8704 | 01-HUM-101-330.0/18
01 | 0K4204 | 01-0K4204 | 01-HUM-101-595.0/0
01 | 0P0604 | 01-0P0604 | 01-HUM-101-834.0/83.4
01 | 0J3604 | 01-0J3604 | 01-HUM-101-103.3/103.7
01 | 0H4104 | 01-0H4104 | 01-HUM-169-15.0/33.8
01 | 0P8904 | 01-0P8904 | 01-HUM-169-250.0/26
01 | 0M7304 | 01-0M7304 | 01-HUM-211-772.0/78.6
01 | 0M6304 | 01-0M6304 | 01-HUM-211-74.2/79.3
01 | 0N7304 | 01-0N7304 | 01-HUM-255-8.3/8.7
01 | 0N0904 | 01-0N0904 | 01-HUM-299-9.0/.6
01 | 0P4004 | 01-0P4004 | 01-HUM-299-22.0/2.2
01 | 0J4104 | 01-0J4104 | 01-HUM-299-30.7/33.4
01 | 0Q2304 | 01-0Q2304 | 01-HUM-299-79.0/9.8
01 | 0P9104 | 01-0P9104 | 01-HUM-299-210.0/22
01 | 0Q1104 | 01-0Q1104 | 01-HUM-299-235.0/27.3
01 | 0P8404 | 01-0P8404 | 01-HUM-451-30.0/4
01 | 0H8404 | 01-0H8404 | 01-LAK-20-2.0/2.8
01 | 0N6804 | 01-0N6804 | 01-LAK-20-16.6/18.1
01 | 0P9604 | 01-0P9604 | 01-MEN-1-6.0/.6
01 | 0F7104 | 01-0F7104 | 01-MEN-1-6.4/9.5
01 | 0E11U4 | 01-0E11U4 | 01-MEN-1-31.1/31.6
01 | 0H6004 | 01-0H6004 | 01-MEN-1-33.7/51
01 | 0B22U4 | 01-0B22U4 | 01-MEN-1-59.8/62.1
01 | 0P7404 | 01-0P7404 | 01-MEN-1-114.0/11.6
01 | 0Q9904 | 01-0Q9904 | 01-MEN-1-196.0/19.6
01 | 0Q1004 | 01-0Q1004 | 01-MEN-1-418.0/42.5
01 | 0Q5804 | 01-0Q5804 | 01-MEN-1-611.0/61.1
01 | 0P1704 | 01-0P1704 | 01-MEN-1-749.0/78
01 | 0N4404 | 01-0N4404 | 01-MEN-1-750.0/76.5
01 | 0Q9704 | 01-0Q9704 | 01-MEN-1-781.0/78.3
01 | 0P0704 | 01-0P0704 | 01-MEN-1-821.0/82.9
01 | 0E0904 | 01-0E0904 | 01-MEN-20-33.3/34.4
01 | 0E0914 | 01-0E0914 | 01-MEN-20-33.3/34.4
01 | 0P8604 | 01-0P8604 | 01-MEN-20-328.0/32.8
01 | 0H1404 | 01-0H1404 | 01-MEN-101-10.7/11.2
01 | 0H5704 | 01-0H5704 | 01-MEN-101-20.9/28.6
01 | 0K4104 | 01-0K4104 | 01-MEN-101-41.3/43.3
01 | 0K8904 | 01-0K8904 | 01-MEN-101-50.7/52.2
01 | 0H5504 | 01-0H5504 | 01-MEN-101-55.0/64.9
01 | 0P2604 | 01-0P2604 | 01-MEN-101-599.0/59.9
01 | 0Q2604 | 01-0Q2604 | 01-MEN-101-727.0/72.7
01 | 0P0904 | 01-0P0904 | 01-MEN-101-860.0/87.5
01 | 0Q4004 | 01-0Q4004 | 01-MEN-101-873.0/87.3
01 | 0H1604 | 01-0H1604 | 01-MEN-101-33.7/43.2
01 | 0H1704 | 01-0H1704 | 01-MEN-101-48.9/55.1
01 | 0N8104 | 01-0N8104 | 01-MEN-128-40.9/44.3
01 | 0Q0604 | 01-0Q0604 | 01-MEN-128-281.0/28.1
01 | 0A1314 | 01-0A1314 | 01-MEN-162-8.0/8.4
01 | 0P9704 | 01-0P9704 | 01-MEN-162-161.0/16.2
01 | 0Q2504 | 01-0Q2504 | 01-MEN-162-211.0/21.1
01 | 0H1504 | 01-0H1504 | 01-MEN-162-/25.7
01 | 0Q4204 | 01-0Q4204 | 01-MEN-175-62.0/6.4
01 | 0P3504 | 01-0P3504 | 01-MEN-253-130.0/13
01 | 0P9404 | 01-0P9404 | 01-MEN-271-24.0/2.5
01 | 0H1204 | 01-0H1204 | 01-VAR-101-84.0/85.5
01 | 0M9604 | 01-0M9604 | 01-VAR--/0
01 | 0N2904 | 01-0N2904 | 01-VAR--/0
01 | 0Q9804 | 01-0Q9804 | 01-VAR--/0
02 | 1J75U4 | 02-1J75U4 | 02-LAS-36-14.4/16.8
02 | 2K5404 | 02-2K5404 | 02-LAS-36-100.0/14
02 | 4H0604 | 02-4H0604 | 02-LAS-36-/6.1
02 | 4H0704 | 02-4H0704 | 02-LAS-139-.7/11
02 | 0K6104 | 02-0K6104 | 02-PLU-70-32.9/33.2
02 | 1H58U4 | 02-1H58U4 | 02-PLU-70-58.2/78.4
02 | 4H0104 | 02-4H0104 | 02-PLU-70-78.3/90.3
02 | 3H6904 | 02-3H6904 | 02-PLU-89-30.2/42.2
02 | 0K7804 | 02-0K7804 | 02-PLU-89-200.0/20.6
02 | 4H1504 | 02-4H1504 | 02-SHA-5-4.9/5.1
02 | 2K6904 | 02-2K6904 | 02-SHA-5-401.0/40.1
02 | 1J8904 | 02-1J8904 | 02-SHA-5-30.5/31
02 | 1K0504 | 02-1K0504 | 02-SHA-44-.4/L1.8
02 | 4H0504 | 02-4H0504 | 02-SHA-273-18.5/18.7
02 | 1J2904 | 02-1J2904 | 02-SHA-299-88.1/89.5
02 | 1K4004 | 02-1K4004 | 02-SIS-0-/0
02 | 1H7104 | 02-1H7104 | 02-SIS-3-47.4/0
02 | 0J8504 | 02-0J8504 | 02-SIS-89-20.3/34.6
02 | 4F90U4 | 02-4F90U4 | 02-SIS-96-41.0/41.8
02 | 1H5904 | 02-1H5904 | 02-SIS-96-43.5/58
02 | 0K6404 | 02-0K6404 | 02-SIS-97-18.0/22.4
02 | 0J5504 | 02-0J5504 | 02-SIS-161-4.5/9.1
02 | 0K0104 | 02-0K0104 | 02-TEH-5-5.6/42
02 | 3J52U4 | 02-3J52U4 | 02-TEH-36-15.7/16.4
02 | 1K9004 | 02-1K9004 | 02-TEH-36-618.0/.2
02 | 0J0104 | 02-0J0104 | 02-TEH-99-4.2/4.8
02 | 3H7704 | 02-3H7704 | 02-TEH-99-/12.5
02 | 3H70U4 | 02-3H70U4 | 02-TRI-299-15.0/25.7
02 | 0K6004 | 02-0K6004 | 02-VAR--/0
02 | 2J9704 | 02-2J9704 | 02-VAR--/0
02 | 3J3304 | 02-3J3304 | 02-VAR--/0
02 | 2K1104 | 02-2K1104 | 02-VAR--/0
03 | 4H76U4 | 03-4H76U4 | 03-BUT-32-5.0/10.2
03 | 3G0704 | 03-3G0704 | 03-BUT-32-31.5/37.8
03 | 3G3804 | 03-3G3804 | 03-BUT-32-23.9/30.8
03 | 1N5504 | 03-1N5504 | 03-BUT-70-350.0/36
03 | 1H1404 | 03-1H1404 | 03-BUT-99-3.1/5
03 | 0J4404 | 03-0J4404 | 03-BUT-162-15.6/18.5
03 | 0J4604 | 03-0J4604 | 03-COL-5-24.3/0
03 | 3G5304 | 03-3G5304 | 03-ED-49-16.5/20.1
03 | 3G5204 | 03-3G5204 | 03-ED-49-23.6/25.2
03 | 1J1604 | 03-1J1604 | 03-ED-50-35.1/0
03 | 4H8904 | 03-4H8904 | 03-ED-50-75.4/8
03 | 2N0704 | 03-2N0704 | 03-ED-50-180.0/18
03 | 1N1804 | 03-1N1804 | 03-ED-50-189.0/18.9
03 | 0N6504 | 03-0N6504 | 03-ED-50-672.0/67.2
03 | 3G8104 | 03-3G8104 | 03-ED-89-81.0/8.1
03 | 3G4304 | 03-3G4304 | 03-ED-89-/8.5
03 | 2G9704 | 03-2G9704 | 03-ED-193-11.9/17.3
03 | 2N4704 | 03-2N4704 | 03-ED-193-88.0/8.8
03 | 2G9804 | 03-2G9804 | 03-ED-193-2.0/8.9
03 | 2G9304 | 03-2G9304 | 03-ED-193-3.5/5.6
03 | 2J5904 | 03-2J5904 | 03-GLE-32-2.8/3.2
03 | 3J4324 | 03-3J4324 | 03-GLE-162-65.5/69.7
03 | 3F0604 | 03-3F0604 | 03-GLE-162-76.3/78.6
03 | 3H51U4 | 03-3H51U4 | 03-NEV-49-10.3/13.8
03 | 3G7404 | 03-3G7404 | 03-NEV-80-156.0/15.6
03 | 2N4304 | 03-2N4304 | 03-NEV-80-247.0/30.2
03 | 3J3604 | 03-3J3604 | 03-NEV-89-5.3/8.7
03 | 0J01U4 | 03-0J01U4 | 03-PLA-28-.1/11
03 | 1H2404 | 03-1H2404 | 03-PLA-49-2.2/2.4
03 | 3H8304 | 03-3H8304 | 03-PLA-49-3.5/7.5
03 | 3F23U4 | 03-3F23U4 | 03-PLA-80-.1/2.2
03 | 0J4104 | 03-0J4104 | 03-PLA-80-33.0/44.9
03 | 3H6104 | 03-3H6104 | 03-PLA-80-42.7/49.3
03 | 0J5604 | 03-0J5604 | 03-PLA-80-49.3/68.7
03 | 0J5504 | 03-0J5504 | 03-PLA-80-50.7/0
03 | 1H9904 | 03-1H9904 | 03-PLA-80-68.3/69.7
03 | 1J1704 | 03-1J1704 | 03-PLA-89-13.0/21.6
03 | 4F6404 | 03-4F6404 | 03-SAC-5-.2/34.3
03 | 0N8504 | 03-0N8504 | 03-SAC-5-16.2/0
03 | 2H1304 | 03-2H1304 | 03-SAC-5-22.4/22.9
03 | 3J5334 | 03-3J5334 | 03-SAC-5-26.7/29
03 | 3J3304 | 03-3J3304 | 03-SAC-12-/.5
03 | 1N7904 | 03-1N7904 | 03-SAC-50-21.0/2.1
03 | 0N6204 | 03-0N6204 | 03-SAC-50-21.0/2.1
03 | 0H08U4 | 03-0H08U4 | 03-SAC-50-.2/6.1
03 | 3F0704 | 03-3F0704 | 03-SAC-51-.2/3.5
03 | 3F0734 | 03-3F0734 | 03-SAC-51-2.0/3.3
03 | 1J6304 | 03-1J6304 | 03-SAC-99-6.1/7
03 | 2N4604 | 03-2N4604 | 03-SAC-160-25.0/2.5
03 | 3J9004 | 03-3J9004 | 03-SAC-160-44.9/0
03 | 1N0104 | 03-1N0104 | 03-SAC-160-/0
03 | 4H9704 | 03-4H9704 | 03-SAC-5500-/0
03 | 3J6804 | 03-3J6804 | 03-SUT-20-15.7/16.1
03 | 4H8704 | 03-4H8704 | 03-SUT-99-25.0/26.2
03 | 0J3504 | 03-0J3504 | 03-VAR-149-/5.3
03 | 0J5204 | 03-0J5204 | 03-VAR--/0
03 | 0J6204 | 03-0J6204 | 03-VAR--/0
03 | 3H9014 | 03-3H9014 | 03-VAR--/0
03 | 3G2304 | 03-3G2304 | 03-VAR--/0
03 | 1N0004 | 03-1N0004 | 03-VAR--/0
03 | 3H5604 | 03-3H5604 | 03-VAR--/0
03 | 3G4904 | 03-3G4904 | 03-VAR--/0
03 | 3J40U4 | 03-3J40U4 | 03-VAR--/0
03 | 3G4804 | 03-3G4804 | 03-VAR--/0
03 | 3G4704 | 03-3G4704 | 03-VAR--/0
03 | 3G4604 | 03-3G4604 | 03-VAR--/0
03 | 3G6204 | 03-3G6204 | 03-YOL-5-22.8/28.9
03 | 4J1204 | 03-4J1204 | 03-YOL-16-37.3/37.8
03 | 4F6504 | 03-4F6504 | 03-YOL-50-/2.5
03 | 1N6204 | 03-1N6204 | 03-YOL-275-130.0/13
03 | 1N9304 | 03-1N9304 | 03-YUB-70-82.0/13.6
04 | 3Y1904 | 04-3Y1904 | 04-ALA-0-/0
04 | 2G4614 | 04-2G4614 | 04-ALA-13-10.7/13
04 | 3W9304 | 04-3W9304 | 04-ALA-80-5.7/6
04 | 3J2604 | 04-3J2604 | 04-ALA-80-5.9/6.4
04 | 0A7724 | 04-0A7724 | 04-ALA-80-6.4/6.8
04 | 0K1604 | 04-0K1604 | 04-ALA-80-7.6/8
04 | 4Y1804 | 04-4Y1804 | 04-ALA-80-/1.8
04 | 3Q8504 | 04-3Q8504 | 04-ALA-84-10.8/18
04 | 160314 | 04-160314 | 04-ALA-84-11.0/18
04 | 1X2804 | 04-1X2804 | 04-ALA-84-11.2/15.5
04 | 0J5504 | 04-0J5504 | 04-ALA-84-17.0/17.4
04 | 297634 | 04-297634 | 04-ALA-84-17.9/22.9
04 | 0X6604 | 04-0X6604 | 04-ALA-84-21.4/23.1
04 | 2Q7604 | 04-2Q7604 | 04-ALA-238-.7/.8
04 | 0G3604 | 04-0G3604 | 04-ALA-260-.8/1.9
04 | 2W7404 | 04-2W7404 | 04-ALA-260-1.1/1.9
04 | 1Y3404 | 04-1Y3404 | 04-ALA-260-1.2/0
04 | 3Y5504 | 04-3Y5504 | 04-ALA-580-4.7/4.8
04 | 0Q1004 | 04-0Q1004 | 04-ALA-580-20.7/30.8
04 | 2Y8604 | 04-2Y8604 | 04-ALA-580-26.2/26.2
04 | 0Y6804 | 04-0Y6804 | 04-ALA-580-35.0/45.2
04 | 3X9504 | 04-3X9504 | 04-ALA-580-4.6/4.7
04 | 0P9004 | 04-0P9004 | 04-ALA-580-41.3/44.8
04 | 2Y8204 | 04-2Y8204 | 04-ALA-580-/32.7
04 | 0P9204 | 04-0P9204 | 04-ALA-680-6.3/6.7
04 | 0Q30U4 | 04-0Q30U4 | 04-ALA-680-11.0/21.9
04 | 2W4604 | 04-2W4604 | 04-ALA-680-15.6/0
04 | 0V1604 | 04-0V1604 | 04-ALA-680-20.7/20.7
04 | 0Q1804 | 04-0Q1804 | 04-ALA-880-6.2/25.5
04 | 2K7004 | 04-2K7004 | 04-ALA-880-/11.8
04 | 1X3804 | 04-1X3804 | 04-ALA-880-/28.9
04 | 2X4204 | 04-2X4204 | 04-ALA-880-/25.7
04 | 4K9804 | 04-4K9804 | 04-ALA-980-1.1/1.1
04 | 3W9104 | 04-3W9104 | 04-ALA-980-1.2/0
04 | 2K9504 | 04-2K9504 | 04-ALA-5501-/14.4
04 | 3X5804 | 04-3X5804 | 04-CC-4-19.8/19.8
04 | 2Q7004 | 04-2Q7004 | 04-CC-4-/14.3
04 | 3X7404 | 04-3X7404 | 04-CC-24-5.1/5.4
04 | 0Q2104 | 04-0Q2104 | 04-CC-80-.2/10.7
04 | 0P9304 | 04-0P9304 | 04-CC-80-7.6/0
04 | 4X3804 | 04-4X3804 | 04-CC-80-7.6/7.6
04 | 1Y7004 | 04-1Y7004 | 04-CC-80-13.8/14.1
04 | 0X6904 | 04-0X6904 | 04-CC-160-/.7
04 | 0W0304 | 04-0W0304 | 04-CC-580-1.4/6.3
04 | 3G3644 | 04-3G3644 | 04-CC-580-6.1/7.8
04 | 3X9804 | 04-3X9804 | 04-CC-680-8.0/8.2
04 | 2Q6504 | 04-2Q6504 | 04-CC-680-/21
04 | 0AA244 | 04-0AA244 | 04-CC-680-/7.7
04 | 1X0304 | 04-1X0304 | 04-MRN-1-8.7/8.7
04 | 1J9604 | 04-1J9604 | 04-MRN-1-22.8/33
04 | 3X2604 | 04-3X2604 | 04-MRN-1-/19.3
04 | 2K7404 | 04-2K7404 | 04-MRN-37-11.2/14.5
04 | 3X3604 | 04-3X3604 | 04-MRN-101-3.0/3
04 | 0K8004 | 04-0K8004 | 04-MRN-101-13.7/0
04 | 264724 | 04-264724 | 04-MRN-101-20.8/27.1
04 | 2X9404 | 04-2X9404 | 04-MRN-101-/9.3
04 | 3X1504 | 04-3X1504 | 04-MRN-580-6.0/7.8
04 | 4J4114 | 04-4J4114 | 04-NAP-29-1.7/0
04 | 281204 | 04-281204 | 04-NAP-29-5.0/6.7
04 | 0Q8204 | 04-0Q8204 | 04-NAP-29-11.6/13
04 | 0K6304 | 04-0K6304 | 04-NAP-29-16.4/19
04 | 4X4904 | 04-4X4904 | 04-NAP-29-19.8/21.5
04 | 4X5304 | 04-4X5304 | 04-NAP-29-23.5/23.5
04 | 3X4904 | 04-3X4904 | 04-NAP-29-45.5/45.5
04 | 0Q8304 | 04-0Q8304 | 04-NAP-29-46.1/0
04 | 2Q6104 | 04-2Q6104 | 04-NAP-29-7.3/13.5
04 | 4G21A4 | 04-4G21A4 | 04-NAP-121-.5/1
04 | 0Q7904 | 04-0Q7904 | 04-NAP-121-13.4/20.7
04 | 4G84A4 | 04-4G84A4 | 04-NAP-128-20.1/20.4
04 | 3X0204 | 04-3X0204 | 04-NAP-128-/25.9
04 | 1X1004 | 04-1X1004 | 04-SCL-9-4.0/4
04 | 1X4304 | 04-1X4304 | 04-SCL-9-4.5/5.5
04 | 3G6304 | 04-3G6304 | 04-SCL-9-4.9/4.9
04 | 0P9704 | 04-0P9704 | 04-SCL-17-6.2/0
04 | 3Y2904 | 04-3Y2904 | 04-SCL-17-/3.5
04 | 0P9804 | 04-0P9804 | 04-SCL-82-11.4/26.3
04 | 4J89U4 | 04-4J89U4 | 04-SCL-82-18.2/26.4
04 | 4X5504 | 04-4X5504 | 04-SCL-82-18.8/18.8
04 | 4J9104 | 04-4J9104 | 04-SCL-87-/6.1
04 | 4J9304 | 04-4J9304 | 04-SCL-101-30.7/31.1
04 | 2Y8504 | 04-2Y8504 | 04-SCL-101-33.0/49
04 | 1Y6204 | 04-1Y6204 | 04-SCL-101-38.0/38.1
04 | 1J5674 | 04-1J5674 | 04-SCL-101-51.7/52.5
04 | 3Q6004 | 04-3Q6004 | 04-SCL-101-.7/19.2
04 | 0X6304 | 04-0X6304 | 04-SCL-101-4.5/17.5
04 | 4X8504 | 04-4X8504 | 04-SCL-101-/30
04 | 1W1904 | 04-1W1904 | 04-SCL-101-/2.7
04 | 2Y7404 | 04-2Y7404 | 04-SCL-152-12.6/12.6
04 | 0Q05U4 | 04-0Q05U4 | 04-SCL-152-16.8/23.3
04 | 2Y5404 | 04-2Y5404 | 04-SCL-237-1.5/6.4
04 | 0Y5004 | 04-0Y5004 | 04-SCL-280-2.9/2.9
04 | 3Y0004 | 04-3Y0004 | 04-SCL-280-4.6/4.6
04 | 1Q4604 | 04-1Q4604 | 04-SCL-280-/2.7
04 | 0X2604 | 04-0X2604 | 04-SCL-280-/3.8
04 | 4X0204 | 04-4X0204 | 04-SCL-880-1.7/1.9
04 | 0AA624 | 04-0AA624 | 04-SF-1-.9/4.1
04 | 0X9104 | 04-0X9104 | 04-SF-80-3.9/4.5
04 | 1Y7204 | 04-1Y7204 | 04-SF-80-5.7/7.7
04 | 3G4874 | 04-3G4874 | 04-SF-80-5.7/7.7
04 | 0Q0204 | 04-0Q0204 | 04-SF-80-3.8/5
04 | 4X1404 | 04-4X1404 | 04-SF-280-6.6/7.2
04 | 1Y5004 | 04-1Y5004 | 04-SF-280-2.7/4.2
04 | 2X0704 | 04-2X0704 | 04-SF0-80-8.3/8.3
04 | 0Q1304 | 04-0Q1304 | 04-SM-1-27.5/34.8
04 | 2J7904 | 04-2J7904 | 04-SM-1-28.9/0
04 | 0X0804 | 04-0X0804 | 04-SM-1-32.2/32.2
04 | 3X5104 | 04-3X5104 | 04-SM-1-47.8/47.8
04 | 4X4504 | 04-4X4504 | 04-SM-1-47.6/47.6
04 | 3Y7604 | 04-3Y7604 | 04-SM-35-8.7/8.7
04 | 1X9604 | 04-1X9604 | 04-SM-82-9.2/9.2
04 | 1Q5304 | 04-1Q5304 | 04-SM-82-9.3/0
04 | 2Y5604 | 04-2Y5604 | 04-SM-82-9.6/11.8
04 | 0K81U4 | 04-0K81U4 | 04-SM-82-12.3/15.9
04 | 0Q4804 | 04-0Q4804 | 04-SM-84-7.8/0
04 | 4X4304 | 04-4X4304 | 04-SM-84-16.1/16.1
04 | 0X3304 | 04-0X3304 | 04-SM-84-28.0/2
04 | 2Y5204 | 04-2Y5204 | 04-SM-84-27.7/29.2
04 | 3X6404 | 04-3X6404 | 04-SM-92-4.0/5
04 | 2Q8004 | 04-2Q8004 | 04-SM-92-12.0/13.1
04 | 0X6504 | 04-0X6504 | 04-SM-92-/.5
04 | 1X2204 | 04-1X2204 | 04-SM-92-/13.6
04 | 2J7304 | 04-2J7304 | 04-SM-101-6.9/7.6
04 | 0X0604 | 04-0X0604 | 04-SM-101-9.1/9.1
04 | 1Q8204 | 04-1Q8204 | 04-SM-101-25.6/26.1
04 | 1Q5824 | 04-1Q5824 | 04-SM-101-/21.8
04 | 1X2404 | 04-1X2404 | 04-SM-101-/6.2
04 | 1X6604 | 04-1X6604 | 04-SM-280-10.2/10.2
04 | 3Y0804 | 04-3Y0804 | 04-SM-280-10.2/10.2
04 | 4J8504 | 04-4J8504 | 04-SM-280-/21
04 | 3Y4104 | 04-3Y4104 | 04-SM-680-/16.5
04 | 2Q5504 | 04-2Q5504 | 04-SOL-12-7.7/14.1
04 | 0A53T4 | 04-0A53T4 | 04-SOL-12-1.8/L3.2
04 | 0W1104 | 04-0W1104 | 04-SOL-12-3.2/7.5
04 | 1X3604 | 04-1X3604 | 04-SOL-28-/9.8
04 | 2Q5204 | 04-2Q5204 | 04-SOL-29-/6
04 | 3X5004 | 04-3X5004 | 04-SOL-80-6.7/6.7
04 | 3X4704 | 04-3X4704 | 04-SOL-80-12.9/12.9
04 | 4G8734 | 04-4G8734 | 04-SOL-80-13.9/14.5
04 | 0K6404 | 04-0K6404 | 04-SOL-80-15.9/30.2
04 | 4K3004 | 04-4K3004 | 04-SOL-80-22.1/23
04 | 0J6014 | 04-0J6014 | 04-SOL-80-34.4/34.5
04 | 3X1604 | 04-3X1604 | 04-SOL-80-10.1/10.6
04 | 4G0804 | 04-4G0804 | 04-SOL-80-10.4/30.2
04 | 3X7004 | 04-3X7004 | 04-SOL-80-/.5
04 | 4X8104 | 04-4X8104 | 04-SOL-84-12.1/12.1
04 | 0X7604 | 04-0X7604 | 04-SOL-113-18.3/21.2
04 | 0J3014 | 04-0J3014 | 04-SON-1-26.7/27.1
04 | 1K7304 | 04-1K7304 | 04-SON-1-30.8/40.6
04 | 1K7314 | 04-1K7314 | 04-SON-1-30.8/40.6
04 | 1X3204 | 04-1X3204 | 04-SON-1-38.6/38.6
04 | 1K7514 | 04-1K7514 | 04-SON-1-41.2/54.6
04 | 1K7504 | 04-1K7504 | 04-SON-1-41.2/54.6
04 | 1K7604 | 04-1K7604 | 04-SON-1-45.4/0
04 | 3X0804 | 04-3X0804 | 04-SON-1-/7.2
04 | 4G7804 | 04-4G7804 | 04-SON-1-/58.6
04 | 1X1404 | 04-1X1404 | 04-SON-1-/24.7
04 | 4X4604 | 04-4X4604 | 04-SON-1-/10.4
04 | 3X1004 | 04-3X1004 | 04-SON-1-/36.4
04 | 4H0514 | 04-4H0514 | 04-SON-12-25.8/0
04 | 4A1304 | 04-4A1304 | 04-SON-101-18.5/18.5
04 | 1Q7004 | 04-1Q7004 | 04-SON-101-22.8/32.8
04 | 2K3604 | 04-2K3604 | 04-SON-116-9.6/0
04 | 3X0504 | 04-3X0504 | 04-SON-116-10.4/10.4
04 | 4J4604 | 04-4J4604 | 04-SON-116-11.8/12.2
04 | 3G9004 | 04-3G9004 | 04-SON-116-46.5/46.8
04 | 3G9014 | 04-3G9014 | 04-SON-116-46.5/46.8
04 | 2Q4404 | 04-2Q4404 | 04-SON-121-6.5/0
04 | 3X4204 | 04-3X4204 | 04-SON-128-16.6/16.7
04 | 4X5704 | 04-4X5704 | 04-SON-128-/3.2
04 | 0Y8004 | 04-0Y8004 | 04-VAR-82-25.9/25.9
04 | 2Q5704 | 04-2Q5704 | 04-VAR-101-18.7/18.7
04 | 3Q6104 | 04-3Q6104 | 04-VAR-101-21.3/26.5
04 | 0K1104 | 04-0K1104 | 04-VAR-280-/0
04 | 0K1204 | 04-0K1204 | 04-VAR-580-/0
04 | 4Q2504 | 04-4Q2504 | 04-VAR-680-.1/20.7
04 | 0Q4404 | 04-0Q4404 | 04-VAR-880-/10
04 | 0Q0704 | 04-0Q0704 | 04-VAR-880-/32
04 | 2Q6404 | 04-2Q6404 | 04-VAR--/0
04 | 4AC904 | 04-4AC904 | 04-VAR--/0
04 | 0X5804 | 04-0X5804 | 04-VAR--/0
04 | 0X5704 | 04-0X5704 | 04-VAR--/0
04 | 1W0904 | 04-1W0904 | 04-VAR--/0
04 | 0X5904 | 04-0X5904 | 04-VAR--/0
04 | 3AC804 | 04-3AC804 | 04-VAR--/0
04 | 4AC404 | 04-4AC404 | 04-VAR--/0
04 | 2Q7404 | 04-2Q7404 | 04-VAR--/0
04 | 3Y5904 | 04-3Y5904 | 04-VAR--/0
04 | 1Q7214 | 04-1Q7214 | 04-VAR--/0
04 | 0Y8404 | 04-0Y8404 | 04-VAR--/0
04 | 0AA804 | 04-0AA804 | 04-VAR--/0
04 | 155004 | 04-155004 | 04-VAR--/0
04 | 0K1004 | 04-0K1004 | 04-VAR--/0
04 | 1Q2004 | 04-1Q2004 | 04-VAR--/0
04 | 0P7604 | 04-0P7604 | 04-VAR--/0
04 | 0Y6604 | 04-0Y6604 | 04-VAR--/0
05 | 1S4904 | 05-1S4904 | 05-0SB-1-10.1/10.1
05 | 1T9904 | 05-1T9904 | 05-0SB-1-72.0/.3
05 | 1T9704 | 05-1T9704 | 05-0SB-101-2.0/.4
05 | 1T9604 | 05-1T9604 | 05-0SB-101-3.0/.3
05 | 1T9804 | 05-1T9804 | 05-0SB-154-260.0/26.3
05 | 1S8404 | 05-1S8404 | 05-MON-1-10.4/10.4
05 | 1R6404 | 05-1R6404 | 05-MON-1-27.8/27.8
05 | 1R6304 | 05-1R6304 | 05-MON-1-29.5/29.5
05 | 1P2104 | 05-1P2104 | 05-MON-1-44.3/0
05 | 1Q8004 | 05-1Q8004 | 05-MON-1-44.7/69.8
05 | 1T2104 | 05-1T2104 | 05-MON-1-50.0/54
05 | 1Q1604 | 05-1Q1604 | 05-MON-1-60.0/0
05 | 1Q9604 | 05-1Q9604 | 05-MON-1-100.0/1
05 | 1S1604 | 05-1S1604 | 05-MON-1-600.0/60
05 | 1K6404 | 05-1K6404 | 05-MON-1-101.5/102
05 | 1S9504 | 05-1S9504 | 05-MON-1-/0
05 | 1P5344 | 05-1P5344 | 05-MON-101-86.1/87.3
05 | 1H6914 | 05-1H6914 | 05-MON-101-98.8/100.3
05 | 1J8904 | 05-1J8904 | 05-MON-101-28.2/97.5
05 | 0T9914 | 05-0T9914 | 05-MON-101-41.1/42.2
05 | 1P5334 | 05-1P5334 | 05-MON-156-1.4/1.3
05 | 1H6504 | 05-1H6504 | 05-MON-183-8.3/9.9
05 | 1S9104 | 05-1S9104 | 05-SB-1-19.8/20.1
05 | 1T4004 | 05-1T4004 | 05-SB-1-46.5/46.5
05 | 1H4404 | 05-1H4404 | 05-SB-1-50.3/50.6
05 | 0N71Y4 | 05-0N71Y4 | 05-SB-101-1.4/4.8
05 | 0N72Y4 | 05-0N72Y4 | 05-SB-101-4.4/7.7
05 | 0N73Y4 | 05-0N73Y4 | 05-SB-101-7.3/9.6
05 | 0N74V4 | 05-0N74V4 | 05-SB-101-9.2/9.7
05 | 0N74U4 | 05-0N74U4 | 05-SB-101-9.7/10.6
05 | 1K03U4 | 05-1K03U4 | 05-SB-101-10.0/10.5
05 | 0N7054 | 05-0N7054 | 05-SB-101-10.4/11.1
05 | 1H4304 | 05-1H4304 | 05-SB-101-21.4/21.9
05 | 1H8604 | 05-1H8604 | 05-SB-101-46.2/52.3
05 | 1R1404 | 05-1R1404 | 05-SB-101-47.0/47.3
05 | 1F7904 | 05-1F7904 | 05-SB-101-55.9/56.2
05 | 1K5104 | 05-1K5104 | 05-SB-101-65.0/84.1
05 | 1C9504 | 05-1C9504 | 05-SB-101-36.0/37
05 | 1K4504 | 05-1K4504 | 05-SB-101-52.3/56.1
05 | 1M1004 | 05-1M1004 | 05-SB-101-56.1/65
05 | 1R6504 | 05-1R6504 | 05-SB-154-26.0/30.2
05 | 1H3114 | 05-1H3114 | 05-SB-154-5.7/6.2
05 | 1P5384 | 05-1P5384 | 05-SB-166-63.9/64.9
05 | 1T4204 | 05-1T4204 | 05-SB-192-6.9/20.7
05 | 1C3604 | 05-1C3604 | 05-SB-217-.9/1.4
05 | 1H8114 | 05-1H8114 | 05-SBT-25-18.8/19.2
05 | 1P5314 | 05-1P5314 | 05-SBT-25-49.5/51.1
05 | 1J4814 | 05-1J4814 | 05-SBT-25-53.7/54.3
05 | 1S9004 | 05-1S9004 | 05-SBT-101-1.5/1.7
05 | 1S5104 | 05-1S5104 | 05-SBT-101-4.2/4.5
05 | 1S0104 | 05-1S0104 | 05-SBT-101-12.0/2.1
05 | 344904 | 05-344904 | 05-SBT-156-3.0/8.2
05 | 2A0004 | 05-2A0004 | 05-SCR-1-1.0/.2
05 | 1S9204 | 05-1S9204 | 05-SCR-1-3.5/3.9
05 | 2A0304 | 05-2A0304 | 05-SCR-1-6.0/.7
05 | 0C7334 | 05-0C7334 | 05-SCR-1-10.5/13.4
05 | 0C7324 | 05-0C7324 | 05-SCR-1-13.6/14.9
05 | 1Q9404 | 05-1Q9404 | 05-SCR-1-33.0/33
05 | 1Q9904 | 05-1Q9904 | 05-SCR-1-360.0/37.5
05 | 1Q0804 | 05-1Q0804 | 05-SCR-1-/0
05 | 1M4004 | 05-1M4004 | 05-SCR-9-6.3/7.2
05 | 1G9504 | 05-1G9504 | 05-SCR-9-9.0/25.5
05 | 1S3604 | 05-1S3604 | 05-SCR-9-12.1/12.1
05 | 1H4704 | 05-1H4704 | 05-SCR-9-13.6/0
05 | 1T3904 | 05-1T3904 | 05-SCR-17-8.4/8.4
05 | 1J8304 | 05-1J8304 | 05-SCR-129-/.6
05 | 1P5304 | 05-1P5304 | 05-SCR-129-1.1/L1.5
05 | 1S3804 | 05-1S3804 | 05-SCR-152-1.3/T1.5
05 | 1S2804 | 05-1S2804 | 05-SLO-0-/0
05 | 492864 | 05-492864 | 05-SLO-1-6.4/67.2
05 | 1P5354 | 05-1P5354 | 05-SLO-1-12.1/12.2
05 | 1Q0604 | 05-1Q0604 | 05-SLO-1-12.6/12.7
05 | 1N3804 | 05-1N3804 | 05-SLO-1-17.3/0
05 | 1R1004 | 05-1R1004 | 05-SLO-1-32.6/0
05 | 3307C4 | 05-3307C4 | 05-SLO-41-44.5/45.3
05 | 1T4104 | 05-1T4104 | 05-SLO-41-495.0/49.5
05 | 1S4804 | 05-1S4804 | 05-SLO-46-4.3/5.1
05 | 1Q03U4 | 05-1Q03U4 | 05-SLO-46-60.3/60.8
05 | 1J9704 | 05-1J9704 | 05-SLO-58-1.8/6.9
05 | 1J9714 | 05-1J9714 | 05-SLO-58-2.0/7.1
05 | 1J8604 | 05-1J8604 | 05-SLO-101-7.8/16.5
05 | 1G6804 | 05-1G6804 | 05-SLO-101-16.0/22.5
05 | 1N3404 | 05-1N3404 | 05-SLO-101-28.6/29.6
05 | 1J7804 | 05-1J7804 | 05-SLO-101-61.7/62.1
05 | 1S9304 | 05-1S9304 | 05-SLO-101-250.0/85
05 | 1S3204 | 05-1S3204 | 05-VAR--/0
06 | 0X2904 | 06-0X2904 | 06-FRE-33-13.9/16.7
06 | 1G8204 | 06-1G8204 | 06-FRE-33-46.8/47.4
06 | 0X3004 | 06-0X3004 | 06-FRE-33-69.4/71.5
06 | 1G0904 | 06-1G0904 | 06-FRE-41-28.2/28.2
06 | 1E7604 | 06-1E7604 | 06-FRE-41-21.1/32.2
06 | 0X7804 | 06-0X7804 | 06-FRE-41-23.2/31.7
06 | 1E7304 | 06-1E7304 | 06-FRE-41-25.3/0
06 | 1G3504 | 06-1G3504 | 06-FRE-99-233.0/0
06 | 0U4214 | 06-0U4214 | 06-FRE-99-4.9/7.2
06 | 0Q5204 | 06-0Q5204 | 06-FRE-168-48.2/0
06 | 1A0904 | 06-1A0904 | 06-FRE-168-49.1/49.5
06 | 0X2204 | 06-0X2204 | 06-FRE-168-8.1/45.8
06 | 0Y4104 | 06-0Y4104 | 06-FRE-180-47.4/47.8
06 | 342354 | 06-342354 | 06-FRE-180-54.1/56
06 | 1J3304 | 06-1J3304 | 06-FRE-180-/0
06 | 0X0604 | 06-0X0604 | 06-FRE-198-.5/19.5
06 | 0Y7604 | 06-0Y7604 | 06-FRE-5506-/0
06 | 0X4304 | 06-0X4304 | 06-FRE-5725-/0
06 | 0X5704 | 06-0X5704 | 06-KER-5-.8/0
06 | 0W9204 | 06-0W9204 | 06-KER-5-4.1/10.7
06 | 0U5004 | 06-0U5004 | 06-KER-5-10.2/16
06 | 1G1804 | 06-1G1804 | 06-KER-5-/0
06 | 0X2404 | 06-0X2404 | 06-KER-33-21.8/39.8
06 | 0Y1304 | 06-0Y1304 | 06-KER-33-40.4/59.3
06 | 3HT0U4 | 06-3HT0U4 | 06-KER-43-25.1/25.4
06 | 1A7604 | 06-1A7604 | 06-KER-46-51.4/57.9
06 | 0Q2814 | 06-0Q2814 | 06-KER-99-23.6/28.4
06 | 0W79U4 | 06-0W79U4 | 06-KER-99-56.4/57.6
06 | 0V6104 | 06-0V6104 | 06-KER-119-28.2/31.3
06 | 1H0604 | 06-1H0604 | 06-KER-155-17.8/39.6
06 | 0S0504 | 06-0S0504 | 06-KER-166-17.5/0
06 | 0U2904 | 06-0U2904 | 06-KER-184-1.1/8.3
06 | 1C0604 | 06-1C0604 | 06-KER-223-1.8/10.4
06 | 1H0504 | 06-1H0504 | 06-KER-223-12.5/30.1
06 | 1G7704 | 06-1G7704 | 06-KIN-5-16.6/26.7
06 | 0W8204 | 06-0W8204 | 06-KIN-41-28.4/40.1
06 | 0Y1704 | 06-0Y1704 | 06-KIN-41-/15.5
06 | 0X7004 | 06-0X7004 | 06-TUL-63-5.8/L8
06 | 1G7404 | 06-1G7404 | 06-TUL-63-12.1/21.6
06 | 1E6904 | 06-1E6904 | 06-TUL-99-9.8/40.7
06 | 1G8404 | 06-1G8404 | 06-TUL-99-13.5/19.5
06 | 0U8804 | 06-0U8804 | 06-TUL-99-26.3/27.6
06 | 0W9104 | 06-0W9104 | 06-TUL-99-27.6/30.6
06 | 360304 | 06-360304 | 06-TUL-99-30.2/35.2
06 | 487404 | 06-487404 | 06-TUL-99-35.8/37.1
06 | 1A3104 | 06-1A3104 | 06-TUL-190-11.2/11.6
06 | 0Q4324 | 06-0Q4324 | 06-TUL-190-13.1/16.6
06 | 1H6904 | 06-1H6904 | 06-TUL-190-42.7/42.8
06 | 1H6704 | 06-1H6704 | 06-TUL-190-366.0/0
06 | 0X2604 | 06-0X2604 | 06-TUL-198-1.6/43.9
06 | 0W90U4 | 06-0W90U4 | 06-TUL-198-11.6/11.9
06 | 0X0704 | 06-0X0704 | 06-TUL-245-/33
06 | 1H9604 | 06-1H9604 | 06-VAR--/0
06 | 0W9704 | 06-0W9704 | 06-VAR--/0
06 | 1F9004 | 06-1F9004 | 06-VAR--/0
07 | 2XM404 | 07-2XM404 | 07-LA-0-/0
07 | 346104 | 07-346104 | 07-LA-1-7.0/7.4
07 | 4V2104 | 07-4V2104 | 07-LA-1-10.4/10.4
07 | 325804 | 07-325804 | 07-LA-1-18.0/33.3
07 | 377604 | 07-377604 | 07-LA-1-29.4/0
07 | 2XR604 | 07-2XR604 | 07-LA-1-34.9/38
07 | 2XS304 | 07-2XS304 | 07-LA-1-36.0/41
07 | 2XS204 | 07-2XS204 | 07-LA-1-37.0/46
07 | 313504 | 07-313504 | 07-LA-1-37.7/62.9
07 | 2XS104 | 07-2XS104 | 07-LA-1-39.9/40
07 | 2XQ704 | 07-2XQ704 | 07-LA-1-40.7/54.1
07 | 2XS404 | 07-2XS404 | 07-LA-1-41.0/45.6
07 | 2XT304 | 07-2XT304 | 07-LA-1-42.0/44
07 | 2XR204 | 07-2XR204 | 07-LA-1-42.2/42.4
07 | 4X9704 | 07-4X9704 | 07-LA-1-42.4/0
07 | 2XR904 | 07-2XR904 | 07-LA-1-43.5/45.5
07 | 2XR104 | 07-2XR104 | 07-LA-1-43.7/43.7
07 | 2XG904 | 07-2XG904 | 07-LA-1-44.1/58.5
07 | 2XR504 | 07-2XR504 | 07-LA-1-46.3/49.4
07 | 291404 | 07-291404 | 07-LA-1-56.5/56.9
07 | 2XG804 | 07-2XG804 | 07-LA-1-352.0/44.1
07 | 2XR704 | 07-2XR704 | 07-LA-1-380.0/40
07 | 2XP704 | 07-2XP704 | 07-LA-1-388.0/40.4
07 | 2XR804 | 07-2XR804 | 07-LA-1-400.0/43.5
07 | 321604 | 07-321604 | 07-LA-1-/18
07 | 333604 | 07-333604 | 07-LA-2-2.3/14.2
07 | 348504 | 07-348504 | 07-LA-2-15.0/26.5
07 | 351304 | 07-351304 | 07-LA-2-15.1/15.3
07 | 2XK404 | 07-2XK404 | 07-LA-2-15.8/15.8
07 | 2XA604 | 07-2XA604 | 07-LA-2-65.2/66.4
07 | 0W2104 | 07-0W2104 | 07-LA-2-18.7/0
07 | 357304 | 07-357304 | 07-LA-5-6.6/13.1
07 | 2XQ404 | 07-2XQ404 | 07-LA-5-6.8/0
07 | 4V3004 | 07-4V3004 | 07-LA-5-8.2/8.2
07 | 2XJ004 | 07-2XJ004 | 07-LA-5-16.0/17.3
07 | 372604 | 07-372604 | 07-LA-5-18.7/0
07 | 344204 | 07-344204 | 07-LA-5-23.2/36.3
07 | 370804 | 07-370804 | 07-LA-5-30.6/31.6
07 | 0W1004 | 07-0W1004 | 07-LA-5-31.8/42.6
07 | 384404 | 07-384404 | 07-LA-5-33.1/39.1
07 | 2XT804 | 07-2XT804 | 07-LA-5-36.0/36
07 | 2XS804 | 07-2XS804 | 07-LA-5-53.7/53.7
07 | 2XT504 | 07-2XT504 | 07-LA-5-138.0/13.8
07 | 0Y1504 | 07-0Y1504 | 07-LA-5-151.1/188.2
07 | 2XW404 | 07-2XW404 | 07-LA-5-658.0/66
07 | 4V5404 | 07-4V5404 | 07-LA-5-56.4/56.7
07 | 323404 | 07-323404 | 07-LA-5-59.5/67.9
07 | 370404 | 07-370404 | 07-LA-5-59.5/73.7
07 | 352304 | 07-352304 | 07-LA-5-60.0/75
07 | 319304 | 07-319304 | 07-LA-5-/19.5
07 | 2XH804 | 07-2XH804 | 07-LA-10-2.2/5.2
07 | 328304 | 07-328304 | 07-LA-10-28.2/31
07 | 316804 | 07-316804 | 07-LA-10-28.3/28.3
07 | 398404 | 07-398404 | 07-LA-10-28.5/30.8
07 | 4V5304 | 07-4V5304 | 07-LA-10-47.9/0
07 | 2XP804 | 07-2XP804 | 07-LA-10-78.0/9.3
07 | 347504 | 07-347504 | 07-LA-10-2.2/4.9
07 | 332004 | 07-332004 | 07-LA-10-4.5/5.5
07 | 358404 | 07-358404 | 07-LA-10-4.7/18.9
07 | 316004 | 07-316004 | 07-LA-14-60.7/77
07 | 322904 | 07-322904 | 07-LA-27-/18.6
07 | 2XN904 | 07-2XN904 | 07-LA-27-/5
07 | 2XR304 | 07-2XR304 | 07-LA-27-/11
07 | 2XT904 | 07-2XT904 | 07-LA-47-1.6/1.6
07 | 390204 | 07-390204 | 07-LA-47-.4/2.1
07 | 368704 | 07-368704 | 07-LA-57-11.0/12.3
07 | 0Y1804 | 07-0Y1804 | 07-LA-60-/3.3
07 | 210624 | 07-210624 | 07-LA-71-1.6/4.8
07 | 346504 | 07-346504 | 07-LA-91-6.0/20.7
07 | 3203U4 | 07-3203U4 | 07-LA-91-16.6/16.8
07 | 0W0604 | 07-0W0604 | 07-LA-101-1.0/9.2
07 | 0W2904 | 07-0W2904 | 07-LA-101-1.5/10.9
07 | 346304 | 07-346304 | 07-LA-101-7.9/11.8
07 | 307104 | 07-307104 | 07-LA-101-32.8/33.8
07 | 329604 | 07-329604 | 07-LA-101-6.2/8
07 | 320104 | 07-320104 | 07-LA-101-/1.5
07 | 327304 | 07-327304 | 07-LA-103-.1/.1
07 | 2XH7A4 | 07-2XH7A4 | 07-LA-105-2.2/2.2
07 | 2XJ504 | 07-2XJ504 | 07-LA-105-20.0/2
07 | 2XQ304 | 07-2XQ304 | 07-LA-105-/18.1
07 | 355604 | 07-355604 | 07-LA-105-2.0/0
07 | 364604 | 07-364604 | 07-LA-105-14.1/14.7
07 | 4V4904 | 07-4V4904 | 07-LA-105-17.5/17.8
07 | 4W7804 | 07-4W7804 | 07-LA-110-6.8/19.5
07 | 2XV904 | 07-2XV904 | 07-LA-110-19.4/19.5
07 | 2XJ104 | 07-2XJ104 | 07-LA-110-21.4/25.7
07 | 2XQ504 | 07-2XQ504 | 07-LA-110-26.7/30.7
07 | 2XT604 | 07-2XT604 | 07-LA-110-30.5/30.7
07 | 2XV804 | 07-2XV804 | 07-LA-110-149.0/16.2
07 | 2XW504 | 07-2XW504 | 07-LA-110-792.0/82.2
07 | 336804 | 07-336804 | 07-LA-118-4.5/9.1
07 | 2XS604 | 07-2XS604 | 07-LA-118-/0
07 | 333704 | 07-333704 | 07-LA-138-43.4/51.4
07 | 4V5204 | 07-4V5204 | 07-LA-138-59.7/0
07 | 320804 | 07-320804 | 07-LA-164-4.0/6.9
07 | 326804 | 07-326804 | 07-LA-210-9.7/51.9
07 | 0Y1604 | 07-0Y1604 | 07-LA-210-9.9/22.5
07 | 361804 | 07-361804 | 07-LA-210-11.0/11.5
07 | 330704 | 07-330704 | 07-LA-210-15.6/18.5
07 | 348704 | 07-348704 | 07-LA-210-18.7/19.7
07 | 348204 | 07-348204 | 07-LA-210-19.4/27
07 | 301704 | 07-301704 | 07-LA-210-33.6/36.5
07 | 356104 | 07-356104 | 07-LA-210-37.8/39.1
07 | 2XQ604 | 07-2XQ604 | 07-LA-210-/0
07 | 4V1404 | 07-4V1404 | 07-LA-213-6.2/6.2
07 | 4V2304 | 07-4V2304 | 07-LA-213-6.4/0
07 | 338704 | 07-338704 | 07-LA-405-12.9/21.5
07 | 350704 | 07-350704 | 07-LA-405-19.2/26
07 | 347904 | 07-347904 | 07-LA-405-31.2/41.4
07 | 2XM804 | 07-2XM804 | 07-LA-405-36.3/37.1
07 | 320204 | 07-320204 | 07-LA-405-40.1/48.1
07 | 353204 | 07-353204 | 07-LA-405-/12.8
07 | 356604 | 07-356604 | 07-LA-605-10.2/20.2
07 | 3255U4 | 07-3255U4 | 07-LA-605-20.2/26
07 | 345104 | 07-345104 | 07-LA-710-5.0/9.5
07 | 349904 | 07-349904 | 07-LA-710-6.0/14.1
07 | 4V4204 | 07-4V4204 | 07-LA-710-6.2/7.2
07 | 347004 | 07-347004 | 07-LA-710-9.6/T32.1
07 | 385804 | 07-385804 | 07-LA-710-13.8/15.3
07 | 390804 | 07-390804 | 07-LA-710-19.6/19.9
07 | 354704 | 07-354704 | 07-LA-710-22.0/0
07 | 331804 | 07-331804 | 07-LA-710-26.0/26.7
07 | 354804 | 07-354804 | 07-LA-5808-/2.5
07 | 358204 | 07-358204 | 07-LA-5823-/7.2
07 | 322704 | 07-322704 | 07-VAR-1-1.3/26.6
07 | 0W8804 | 07-0W8804 | 07-VAR-1-23.1/23.1
07 | 348804 | 07-348804 | 07-VAR-2-18.7/18.7
07 | 0W6104 | 07-0W6104 | 07-VAR-5-/40
07 | 346204 | 07-346204 | 07-VAR-23-3.6/11.4
07 | 338604 | 07-338604 | 07-VAR-91-6.1/20.7
07 | 355104 | 07-355104 | 07-VAR-105-2.1/2.1
07 | 0W5904 | 07-0W5904 | 07-VAR-110-15.1/23
07 | 349504 | 07-349504 | 07-VAR-170-14.5/20.5
07 | 349104 | 07-349104 | 07-VAR-210-43.9/46.7
07 | 374304 | 07-374304 | 07-VAR--/0
07 | 0Y2004 | 07-0Y2004 | 07-VAR--/0
07 | 301604 | 07-301604 | 07-VAR--/0
07 | 353804 | 07-353804 | 07-VAR--/0
07 | 0Y0904 | 07-0Y0904 | 07-VAR--/0
07 | 0W9804 | 07-0W9804 | 07-VAR--/0
07 | 0W6504 | 07-0W6504 | 07-VAR--/0
07 | 0W7704 | 07-0W7704 | 07-VAR--/0
07 | 350334 | 07-350334 | 07-VAR--/0
07 | 351124 | 07-351124 | 07-VAR--/0
07 | 0W9704 | 07-0W9704 | 07-VAR--/0
07 | 350314 | 07-350314 | 07-VAR--/0
07 | 351114 | 07-351114 | 07-VAR--/0
07 | 0W6604 | 07-0W6604 | 07-VAR--/0
07 | 350404 | 07-350404 | 07-VAR--/0
07 | 350324 | 07-350324 | 07-VAR--/0
07 | 0W8904 | 07-0W8904 | 07-VAR--/0
07 | 360604 | 07-360604 | 07-VAR--/0
07 | 351504 | 07-351504 | 07-VAR--/0
07 | 0Y1004 | 07-0Y1004 | 07-VAR--/0
07 | 351704 | 07-351704 | 07-VAR--/0
07 | 0Y0504 | 07-0Y0504 | 07-VAR--/0
07 | 0Y1904 | 07-0Y1904 | 07-VAR--/0
07 | 0W9904 | 07-0W9904 | 07-VAR--/0
07 | 4P8504 | 07-4P8504 | 07-VEN-1-1.0/1.3
07 | 318204 | 07-318204 | 07-VEN-1-4.0/4.2
07 | 323904 | 07-323904 | 07-VEN-1-21.3/28.4
07 | 319604 | 07-319604 | 07-VEN-1-21.3/21.9
07 | 2XE704 | 07-2XE704 | 07-VEN-23-17.7/24.1
07 | 348404 | 07-348404 | 07-VEN-23-/3.3
07 | 332304 | 07-332304 | 07-VEN-33-18.9/19.1
07 | 2XF604 | 07-2XF604 | 07-VEN-33-24.2/27.3
07 | 356804 | 07-356804 | 07-VEN-33-26.9/41.7
07 | 2XF704 | 07-2XF704 | 07-VEN-33-44.2/57.2
07 | 355204 | 07-355204 | 07-VEN-33-3.3/21.2
07 | 3311U4 | 07-3311U4 | 07-VEN-101-.2/40.8
07 | 2XT104 | 07-2XT104 | 07-VEN-101-2.2/2.2
07 | 0W3904 | 07-0W3904 | 07-VEN-101-10.7/26.7
07 | 0Y1304 | 07-0Y1304 | 07-VEN-101-25.9/30.6
07 | 0W4004 | 07-0W4004 | 07-VEN-101-30.9/36.3
07 | 2XW704 | 07-2XW704 | 07-VEN-101-316.0/33.7
07 | 369704 | 07-369704 | 07-VEN-118-12.0/13.4
07 | 341604 | 07-341604 | 07-VEN-118-13.3/15.6
07 | 387904 | 07-387904 | 07-VEN-118-18.4/T18.8
07 | 1XW104 | 07-1XW104 | 07-VEN-126-20.3/20.3
07 | 356504 | 07-356504 | 07-VEN-126-14.6/34.5
07 | 2XP204 | 07-2XP204 | 07-VEN-126-/0
07 | 2XN104 | 07-2XN104 | 07-VEN-150-20.0/32.2
07 | 344504 | 07-344504 | 07-VEN-150-31.3/34.4
07 | 3237U4 | 07-3237U4 | 07-VEN-150-13.3/19
07 | 346804 | 07-346804 | 07-VEN-232-.4/4.1
07 | 2XM504 | 07-2XM504 | 07-VEN--/0
08 | 1P0804 | 08-1P0804 | 08-RIV-10-7.0/44.5
08 | 1L9504 | 08-1L9504 | 08-RIV-10-12.6/13.4
08 | 1K9604 | 08-1K9604 | 08-RIV-10-14.6/16.3
08 | 0G8504 | 08-0G8504 | 08-RIV-10-71.2/72.6
08 | 1C08U4 | 08-1C08U4 | 08-RIV-10-134.0/156.5
08 | 1K4004 | 08-1K4004 | 08-RIV-15-3.5/6.8
08 | 1J8704 | 08-1J8704 | 08-RIV-15-16.3/52.3
08 | 1R3804 | 08-1R3804 | 08-RIV-15-18.7/19
08 | 1L8104 | 08-1L8104 | 08-RIV-15-33.9/52.3
08 | 1R4204 | 08-1R4204 | 08-RIV-15-35.1/35.1
08 | 1P0704 | 08-1P0704 | 08-RIV-15-46.5/49.3
08 | 1R4504 | 08-1R4504 | 08-RIV-15-.6/1.6
08 | 1H3804 | 08-1H3804 | 08-RIV-60-6.1/8
08 | 1G4704 | 08-1G4704 | 08-RIV-74-3.1/3
08 | 1R3704 | 08-1R3704 | 08-RIV-74-3.9/11.8
08 | 1K6904 | 08-1K6904 | 08-RIV-74-5.7/11.8
08 | 1L3104 | 08-1L3104 | 08-RIV-74-11.8/17.3
08 | 1C07U4 | 08-1C07U4 | 08-RIV-74-27.5/34.3
08 | 1G6704 | 08-1G6704 | 08-RIV-79-5.4/11.4
08 | 1P2804 | 08-1P2804 | 08-RIV-91-8.3/9
08 | 1L1804 | 08-1L1804 | 08-RIV-91-13.5/16.8
08 | 1L3204 | 08-1L3204 | 08-RIV-91-15.6/21.6
08 | 0R0104 | 08-0R0104 | 08-RIV-91-.3/0
08 | 1J2904 | 08-1J2904 | 08-RIV-215-25.0/31.2
08 | 1J6104 | 08-1J6104 | 08-RIV-215-40.5/42.7
08 | 1J4504 | 08-1J4504 | 08-RIV-243-/29.7
08 | 1J3204 | 08-1J3204 | 08-RIV-5732-/0
08 | 1J6204 | 08-1J6204 | 08-SBD-0-/0
08 | 1J5404 | 08-1J5404 | 08-SBD-15-2.4/0
08 | 0R42A4 | 08-0R42A4 | 08-SBD-15-7.4/7.4
08 | 1R2804 | 08-1R2804 | 08-SBD-15-7.6/7.6
08 | 1L5104 | 08-1L5104 | 08-SBD-15-15.9/0
08 | 1J3304 | 08-1J3304 | 08-SBD-15-160.9/161.5
08 | 1N1214 | 08-1N1214 | 08-SBD-15-180.9/185.5
08 | 1H3904 | 08-1H3904 | 08-SBD-15-20.5/21.6
08 | 1R5004 | 08-1R5004 | 08-SBD-18-18.4/19.2
08 | 1J3104 | 08-1J3104 | 08-SBD-18-34.0/44.3
08 | 1J3004 | 08-1J3004 | 08-SBD-18-90.9/96.6
08 | 1T3304 | 08-1T3304 | 08-SBD-38-14.9/44.2
08 | 1T2804 | 08-1T2804 | 08-SBD-40-5.0/7
08 | 1K4904 | 08-1K4904 | 08-SBD-40-105.1/105.9
08 | 1N7804 | 08-1N7804 | 08-SBD-40-129.8/135.9
08 | 1M0404 | 08-1M0404 | 08-SBD-40-140.0/142.2
08 | 1J7204 | 08-1J7204 | 08-SBD-40-/S.8
08 | 1T2604 | 08-1T2604 | 08-SBD-62-30.7/31.3
08 | 1T3504 | 08-1T3504 | 08-SBD-62-54.0/79.5
08 | 1L2404 | 08-1L2404 | 08-SBD-95-57.2/64.5
08 | 1R7304 | 08-1R7304 | 08-SBD-138-18.9/19.5
08 | 1T5304 | 08-1T5304 | 08-SBD-138-/0
08 | 1N7704 | 08-1N7704 | 08-SBD-173-/L7.7
08 | 1T3204 | 08-1T3204 | 08-SBD-178-10.0/12
08 | 1M7404 | 08-1M7404 | 08-SBD-210-1.2/1.6
08 | 0N0604 | 08-0N0604 | 08-SBD-210-14.6/16.4
08 | 1P0604 | 08-1P0604 | 08-SBD-210-15.7/17.9
08 | 1L9704 | 08-1L9704 | 08-SBD-210-23.1/24.7
08 | 1M5604 | 08-1M5604 | 08-SBD-210-24.0/0
08 | 1T2704 | 08-1T2704 | 08-SBD-247-46.1/76.9
08 | 1J2704 | 08-1J2704 | 08-SBD-247-/23
08 | 1T4604 | 08-1T4604 | 08-SBD-330-34.0/42
08 | 1G6404 | 08-1G6404 | 08-SBD-395-4.0/49
08 | 1H9924 | 08-1H9924 | 08-VAR--/0
08 | 1J8604 | 08-1J8604 | 08-VAR--/0
08 | 1J8504 | 08-1J8504 | 08-VAR--/0
08 | 1N4704 | 08-1N4704 | 08-VAR--/0
08 | 1H8804 | 08-1H8804 | 08-VAR--/0
08 | 1P6604 | 08-1P6604 | 08-VAR--/0
08 | 1J8404 | 08-1J8404 | 08-VAR--/0
08 | 1R0404 | 08-1R0404 | 08-VAR--/0
08 | 1P8904 | 08-1P8904 | 08-VAR--/0
08 | 1E1404 | 08-1E1404 | 08-VAR--/0
09 | 374704 | 09-374704 | 09-INY-168-17.6/18.3
09 | 213404 | 09-213404 | 09-INY-395-29.2/41.8
09 | 374504 | 09-374504 | 09-INY-395-56.8/57.4
09 | 390204 | 09-390204 | 09-INY-395-57.4/0
09 | 379104 | 09-379104 | 09-INY-395-91.6/100.8
09 | 374804 | 09-374804 | 09-INY-395-115.0/0
09 | 398604 | 09-398604 | 09-INY-395-115.0/0
09 | 366804 | 09-366804 | 09-INY-395-117.3/117.9
09 | 379004 | 09-379004 | 09-INY-395-65.0/76
09 | 368004 | 09-368004 | 09-MNO-395-91.6/93.4
09 | 378804 | 09-378804 | 09-MNO-395-9.8/12.6
10 | 0J7204 | 10-0J7204 | 10-ALP-4-/31.7
10 | 1U8004 | 10-1U8004 | 10-ALP-88-1.9/1.9
10 | 0Q2104 | 10-0Q2104 | 10-AMA-88-5.5/14.3
10 | 1H5004 | 10-1H5004 | 10-CAL-4-15.9/16.3
10 | 1L8004 | 10-1L8004 | 10-CAL-4-21.8/0
10 | 1J8204 | 10-1J8204 | 10-CAL-12-9.9/10.3
10 | 0X7404 | 10-0X7404 | 10-CAL-12-17.1/17.5
10 | 1K8204 | 10-1K8204 | 10-CAL-26-18.1/0
10 | 0V4804 | 10-0V4804 | 10-CAL-26-21.8/30.3
10 | 1H7004 | 10-1H7004 | 10-CAL-49-7.5/9.4
10 | 1J5104 | 10-1J5104 | 10-MER-99-.6/0
10 | 3A7214 | 10-3A7214 | 10-MER-99-19.5/20.7
10 | 1K0904 | 10-1K0904 | 10-MER-99-3.3/6.9
10 | 1U5204 | 10-1U5204 | 10-MER-99-12.1/12.1
10 | 1M1704 | 10-1M1704 | 10-MER-140-43.5/43.9
10 | 1L8704 | 10-1L8704 | 10-MER-165-32.9/0
10 | 1S6404 | 10-1S6404 | 10-MER-165-/7
10 | 0P9244 | 10-0P9244 | 10-MPA-140-42.0/42.7
10 | 1R9904 | 10-1R9904 | 10-SJ-4-.5/.5
10 | 1U5904 | 10-1U5904 | 10-SJ-4-14.1/14.1
10 | 1L2804 | 10-1L2804 | 10-SJ-4-20.5/20.8
10 | 1R8804 | 10-1R8804 | 10-SJ-4-141.0/14.1
10 | 1F1804 | 10-1F1804 | 10-SJ-4-16.0/19.4
10 | 1C0504 | 10-1C0504 | 10-SJ-4-19.4/38.1
10 | 1F3204 | 10-1F3204 | 10-SJ-4-/8.9
10 | 1H3604 | 10-1H3604 | 10-SJ-4-/0
10 | 1L3404 | 10-1L3404 | 10-SJ-5-7.5/0
10 | 1E3004 | 10-1E3004 | 10-SJ-5-32.5/49.8
10 | 1U7104 | 10-1U7104 | 10-SJ-12-23.9/25.7
10 | 1T5604 | 10-1T5604 | 10-SJ-99-7.9/7.9
10 | 1N9004 | 10-1N9004 | 10-SJ-99-21.6/0
10 | 1U1004 | 10-1U1004 | 10-SJ-99-21.9/21.9
10 | 1H6504 | 10-1H6504 | 10-SJ-99-28.7/31.7
10 | 1C3304 | 10-1C3304 | 10-SJ-205-4.6/9
10 | 1U5604 | 10-1U5604 | 10-SJ-580-12.7/12.7
10 | 1C2704 | 10-1C2704 | 10-STA-5-27.1/27.4
10 | 1R7704 | 10-1R7704 | 10-STA-99-1.5/16
10 | 1S4904 | 10-1S4904 | 10-STA-99-17.0/17
10 | 1K8404 | 10-1K8404 | 10-STA-108-33.2/33.5
10 | 0G8304 | 10-0G8304 | 10-VAR-59-/0
10 | 1F9704 | 10-1F9704 | 10-VAR--/0
10 | 1F9604 | 10-1F9604 | 10-VAR--/0
10 | 1L8604 | 10-1L8604 | 10-VAR--/0
10 | 1G0204 | 10-1G0204 | 10-VAR--/0
10 | 1G6204 | 10-1G6204 | 10-VAR--/0
10 | 1F2504 | 10-1F2504 | 10-VAR--/0
10 | 1R7204 | 10-1R7204 | 10-VAR--/0
10 | 0T69U4 | 10-0T69U4 | 10-VAR--/0
11 | 432934 | 11-432934 | 11-IMP-0-/0
11 | 2N1784 | 11-2N1784 | 11-IMP-8-/10.3
11 | 2N1764 | 11-2N1764 | 11-IMP-8-50.3/96.7
11 | 2N2284 | 11-2N2284 | 11-IMP-78-/13.2
11 | 2N2304 | 11-2N2304 | 11-IMP-86-4.5/L8.5
11 | 2N2264 | 11-2N2264 | 11-IMP-98-30.0/57
11 | 080284 | 11-080284 | 11-IMP-98-32.1/32.5
11 | 2N1974 | 11-2N1974 | 11-IMP-111-23.5/32.1
11 | 2N1474 | 11-2N1474 | 11-IMP-111-50.7/0
11 | 432854 | 11-432854 | 11-SD-0-/0
11 | 432784 | 11-432784 | 11-SD-0-/0
11 | 432674 | 11-432674 | 11-SD-0-/0
11 | 432304 | 11-432304 | 11-SD-5-4.6/4.6
11 | 4B0334 | 11-4B0334 | 11-SD-5-9.1/16.1
11 | 4B0044 | 11-4B0044 | 11-SD-5-9.5/0
11 | 432714 | 11-432714 | 11-SD-5-10.4/10.4
11 | 2E1544 | 11-2E1544 | 11-SD-5-34.7/36.3
11 | 431274 | 11-431274 | 11-SD-5-.3/36
11 | 4C0034 | 11-4C0034 | 11-SD-5-.9/0
11 | 2T0444 | 11-2T0444 | 11-SD-5-4.4/4.5
11 | 432694 | 11-432694 | 11-SD-5-19.4/19.4
11 | 2N1754 | 11-2N1754 | 11-SD-5-30.6/52.8
11 | 2T36U4 | 11-2T36U4 | 11-SD-5-37.4/52.6
11 | 431004 | 11-431004 | 11-SD-5-49.3/53.2
11 | 2N1684 | 11-2N1684 | 11-SD-5-53.9/63.7
11 | 430824 | 11-430824 | 11-SD-5-66.2/67.4
11 | 4B0084 | 11-4B0084 | 11-SD-8-15.8/21.9
11 | 432824 | 11-432824 | 11-SD-8-41.8/41.8
11 | 433034 | 11-433034 | 11-SD-8-69.2/69.2
11 | 2N2324 | 11-2N2324 | 11-SD-8-73.0/77.8
11 | 430194 | 11-430194 | 11-SD-15-.4/10.2
11 | 432444 | 11-432444 | 11-SD-15-2.1/2.2
11 | 432914 | 11-432914 | 11-SD-15-45.0/4.5
11 | 430514 | 11-430514 | 11-SD-15-31.3/37.1
11 | 430254 | 11-430254 | 11-SD-52-5.1/9
11 | 411904 | 11-411904 | 11-SD-56-.3/9.7
11 | 2T3644 | 11-2T3644 | 11-SD-56-.3/3
11 | 4B0054 | 11-4B0054 | 11-SD-67-3.9/6.1
11 | 430314 | 11-430314 | 11-SD-67-4.1/15.9
11 | 2N0204 | 11-2N0204 | 11-SD-76-17.2/24.1
11 | 430274 | 11-430274 | 11-SD-76-17.5/52.2
11 | 431644 | 11-431644 | 11-SD-78-/N17.7
11 | 430814 | 11-430814 | 11-SD-79-11.2/20.2
11 | 430364 | 11-430364 | 11-SD-79-20.2/53
11 | 2N2244 | 11-2N2244 | 11-SD-79-.6/52.9
11 | 2N2064 | 11-2N2064 | 11-SD-94-1.6/13.3
11 | 430264 | 11-430264 | 11-SD-94-15.2/65.3
11 | 430244 | 11-430244 | 11-SD-125-9.3/13
11 | 411404 | 11-411404 | 11-SD-125-9.6/13.2
11 | 4B0124 | 11-4B0124 | 11-SD-125-12.9/22.3
11 | 4B0394 | 11-4B0394 | 11-SD-163-.7/3.1
11 | 4B0384 | 11-4B0384 | 11-SD-163-3.1/10.9
11 | 430484 | 11-430484 | 11-SD-163-4.3/10.8
11 | 430234 | 11-430234 | 11-SD-805-.1/14.6
11 | 2N1714 | 11-2N1714 | 11-SD-805-.5/14.6
11 | 2T3434 | 11-2T3434 | 11-SD-805-5.1/8.3
11 | 432944 | 11-432944 | 11-SD-805-11.2/13.3
11 | 430324 | 11-430324 | 11-SD-805-14.6/23.7
11 | 430384 | 11-430384 | 11-SD-805-23.7/28.5
11 | 430394 | 11-430394 | 11-SD-805-23.9/25.1
11 | 432024 | 11-432024 | 11-SD--/0
11 | 2N2074 | 11-2N2074 | 11-VAR--/0
11 | 430904 | 11-430904 | 11-VAR--/0
11 | 2N2334 | 11-2N2334 | 11-VAR--/0
11 | 2N1774 | 11-2N1774 | 11-VAR--/0
11 | 430344 | 11-430344 | 11-VAR--/0
11 | 2N2254 | 11-2N2254 | 11-VAR--/0
12 | 0V4404 | 12-0V4404 | 12-0RA-241-30.0/31
12 | 0R3114 | 12-0R3114 | 12-LA-91-20.6/20.7
12 | 0P69U4 | 12-0P69U4 | 12-ORA-1-5.5/7.9
12 | 0M82U4 | 12-0M82U4 | 12-ORA-1-7.9/10.5
12 | 0P68U4 | 12-0P68U4 | 12-ORA-1-13.0/33.7
12 | 0S1404 | 12-0S1404 | 12-ORA-1-21.5/31.1
12 | 0S7504 | 12-0S7504 | 12-ORA-1-.8/0
12 | 0T8604 | 12-0T8604 | 12-ORA-5-2.3/19.9
12 | 0U9204 | 12-0U9204 | 12-ORA-5-6.5/0
12 | 0S2804 | 12-0S2804 | 12-ORA-5-9.6/10.4
12 | 0S3804 | 12-0S3804 | 12-ORA-5-10.0/21.3
12 | 0K0244 | 12-0K0244 | 12-ORA-5-12.4/18.9
12 | 0K61U4 | 12-0K61U4 | 12-ORA-5-21.3/25.8
12 | 0J34U4 | 12-0J34U4 | 12-ORA-5-29.6/29.6
12 | 0S8404 | 12-0S8404 | 12-ORA-5-36.7/0
12 | 0K62U4 | 12-0K62U4 | 12-ORA-5-25.8/30.3
12 | 0S3104 | 12-0S3104 | 12-ORA-5-26.3/42.2
12 | 0S1104 | 12-0S1104 | 12-ORA-22-.9/9.4
12 | 0S7004 | 12-0S7004 | 12-ORA-22-8.6/0
12 | 0S1904 | 12-0S1904 | 12-ORA-22-11.6/12.5
12 | 0R32U4 | 12-0R32U4 | 12-ORA-55-.2/17.8
12 | 0S3304 | 12-0S3304 | 12-ORA-57-11.0/22.6
12 | 0M9704 | 12-0M9704 | 12-ORA-57-11.5/12.5
12 | 0K93U4 | 12-0K93U4 | 12-ORA-57-13.9/16.1
12 | 0S5304 | 12-0S5304 | 12-ORA-57-15.9/0
12 | 0U9804 | 12-0U9804 | 12-ORA-57-19.6/20.1
12 | 0C1114 | 12-0C1114 | 12-ORA-57-20.3/21.6
12 | 0U5904 | 12-0U5904 | 12-ORA-73-10.3/26.8
12 | 0P0314 | 12-0P0314 | 12-ORA-74-11.5/16.6
12 | 0R3134 | 12-0R3134 | 12-ORA-91-6.4/9.2
12 | 0K91U4 | 12-0K91U4 | 12-ORA-91-9.2/11.4
12 | 0R3154 | 12-0R3154 | 12-ORA-91-10.8/18.9
12 | 0P94U4 | 12-0P94U4 | 12-ORA-133-3.2/4.1
12 | 0N8904 | 12-0N8904 | 12-ORA-133-8.3/M9.3
12 | 0Q9804 | 12-0Q9804 | 12-ORA-241-14.5/25.7
12 | 0Q9704 | 12-0Q9704 | 12-ORA-405-.2/11.4
12 | 0R57U4 | 12-0R57U4 | 12-ORA-405-11.4/24.2
12 | 0R6804 | 12-0R6804 | 12-ORA-605-.2/1.6
12 | 0K8704 | 12-0K8704 | 12-ORA-605-.6/1.6
12 | 0R5604 | 12-0R5604 | 12-VAR-55-5.5/17.8
12 | 0U7904 | 12-0U7904 | 12-VAR--/0

## Report 3
District | Rtrim(Federal_Aid.Category) | Rtrim(Federal_Aid.Header) | Sum_Auth_Final | Sum_Work_Comp
10 | Federal Aid (Interstate) | -I- | 17815911.59 | 11864272.7
12 | Federal Aid (Primary) | -F- | 690818122.75 | 298303473.9
04 | Federal Aid (Primary) | -F- | 811972556.64 | 295153748.14
06 | Federal Aid (Secondary) | -S- | 101173535.55 | 43917607.11
08 | Federal Aid (Secondary) | -S- | 68954195.92 | 46678955.32
07 | Federal Aid (Interstate) | -I- | 654268377.04 | 304883742.13
02 | Federal Aid (Primary) | -F- | 263217269.84 | 156300185.28
06 | Federal Aid (Primary) | -F- | 290441139.65 | 124714833.74
03 | Federal Aid (Secondary) | -S- | 97672295.13 | 83347113.93
11 | Federal Aid (Secondary) | -S- | 38964838.25 | 0
04 |  |  | 1222402790.8 | 705406249.92
05 |  |  | 852340994.06 | 467319885.72
06 |  |  | 353033393.06 | 88759227.18
08 |  |  | 406703487.5 | 182432263.68
09 |  |  | 31661968.25 | 16710178.49
08 | Federal Aid (Primary) | -F- | 331085673.5 | 231410999.35
10 | Federal Aid (Primary) | -F- | 55845341.54 | 36153276.72
07 | Federal Aid (Secondary) | -S- | 68580787.35 | 28226802.66
07 |  |  | 1170785689.92 | 777303068.55
04 | Federal Aid (Interstate) | -I- | 757988339.64 | 561585396.5
03 | Federal Aid (Interstate) | -I- | 260385259.96 | 189638178.08
08 | Federal Aid (Interstate) | -I- | 213483884.43 | 152056953.48
09 | Federal Aid (Secondary) | -S- | 23179958.26 | 10716376.42
05 | Federal Aid (Secondary) | -S- | 27028289.04 | 10663115.25
03 |  |  | 1221690400.03 | 800581146.93
10 |  |  | 248471515.39 | 166164941.24
06 | Federal Aid (Interstate) | -I- | 97810431.11 | 20828775.69
01 | Federal Aid (Primary) | -F- | 370231432.25 | 249282833.61
04 | Federal Aid (Secondary) | -S- | 97884719.53 | 52714124.85
11 | Federal Aid (Interstate) | -I- | 366287170.36 | 163427911.3
12 | Federal Aid (Interstate) | -I- | 601964956.34 | 203427463.68
11 | Federal Aid (Primary) | -F- | 237455995.54 | 88136917.17
07 | Federal Aid (Primary) | -F- | 948105813.24 | 191389154.42
03 | Federal Aid (Primary) | -F- | 457777911.39 | 348651206.61
01 | Federal Aid (Secondary) | -S- | 147819143.57 | 67105542.06
02 | Federal Aid (Secondary) | -S- | 42525025.05 | 26593780.59
10 | Federal Aid (Secondary) | -S- | 406163779.76 | 43365875.23
11 |  |  | 613320927.53 | 424521192.57
02 |  |  | 143256769.69 | 77578083.23
09 | Federal Aid (Primary) | -F- | 208932375.72 | 141440195.96
05 | Federal Aid (Primary) | -F- | 423368298.86 | 331288086.92
12 | Federal Aid (Secondary) | -S- | 55923760.91 | 53323002.94
01 |  |  | 464148757.41 | 282989303.64
12 |  |  | 204986362.25 | 81328615.45

## Report 4
District | PED_COMP_TOT
03 | 7409673.97
09 | 16658789.92
08 | 21389179.33
01 | 485000
05 | 62881123.24
12 | 3710168.7
06 | 19820394.34
04 | 48079995.73
02 | 40277516.4
10 | 9592639.38
07 | 62120879.01

## Report 5
Rtrim(Federal_Aid.Category) | Rtrim(Federal_Aid.Header) | Sum_Auth_Final | Sum_Work_Comp
Federal Aid (Interstate) | -I- | 2970004330.47 | 1607712693.56
Federal Aid (Secondary) | -S- | 1175870328.32 | 466652296.36
Federal Aid (Primary) | -F- | 5089251930.92 | 2492224911.82
|  | 6932803055.89 | 4071094156.6