## Report 1
District | Contract_Num | Ea | Cnty_Rt_Pm | Highway_Program_Code | Federal_Aid_Location | Contractor | Contractor_Addr | Contractor_City | Contractor_Phone | Resident_Engineer_Phone | Re_Addr | Re_Loc | Re_Engineer | C_Ci_Pay_Est | C_Ew_Pay_Est | C_Ac_Pay_Est | C_Mobil_Pay_Est | C_Ped_Est_Date | Type_Of_Work | Loc_Desc | Elapsed_Time_Pct | Work_Completed_Pct | Work_Comp_To_Date_Amt | Bid_Amt | Authorized_Final_Amt | Contract_Number | Est_Comp_Date | Approval_Date | Award_Date | Acceptance_Date | Construction_Suspended | Actual_No_Days_Worked | Cco_Other_Days | Orig_No_Working_Days | Change_Order_Days | Pep_Status | C_Spm
01 | 01-0Q0804 | 0Q0804 | 01-DEL-199-91.0/9.4 | 20.XX 201130 |  | Tidewater Contractors Inc. | Po Box 1956 | Brookings Or 97415 |  | 7078155620 | 1444 Parkway Dr. | Crescent City Ca 95531 | Valley Aaron | 0 | 0 | 0 | 0 | 2025-10-20 | Repair Sink | Repair Sink Del Norte Cnty 4 Miles East Of Hiouchi Stabilize Slope With Mechanically Dir'S Emergency F.A. | 27 | 13 | 590946.73 | 17663 | 4485000 | 59677 | 2026-04-01 | 2025-05-07 | 2025-04-21 |  |  | 41 | 0 | 150 | 0 |  | X
01 | 01-0P4304 | 0P4304 | 01-DN-101-2.0/16.5 | 20.XX 201130 |  | Gr Sundberg Inc | 5211 Boyd Road | Arcata Ca 95521 |  | 7073469027 | 5065 Boyd Road Suite H | Arcata Ca 95521 | Dunne Ryan | 0 | 0 | 0 | 0 |  | Repair Storm Damage | Repair Storm Damage Del Norte Cnty 8 Miles South Crescent Cityrepair Retaining Walla And Subsurface Dir'S Emergency F.A. | 0 | 0 | 0 | 43725 | 8485000 | 60077 | 2026-08-01 | 2025-05-07 | 2025-04-14 |  |  | 0 | 0 | 150 | 0
01 | 01-0J2104 | 0J2104 | 01-DN-101-2.6/23.9 |  | ACNH-Q101- (442)E | Mercer-Fraser Company | 200 Dinsmore Dr | Fortuna Ca 95540 |  | 7078155620 | 1444 Parkway Drive | Crescent City, Ca 95531 | Valley, Aaron | 0 | 0 | 0 | 0 |  | Rhma, Hma, And Cold Plane Asphalt Concrete | Del Norte County In And Near Klamath From 1.2 Miles South Of Klamath River Overflow To 1.1 Mile North Of Hamilton Road | 0 | 0 | 0 | 22896896 | 22896896 | 60035 |  | 2025-08-26 | 2025-06-06 |  |  | 0 | 0 | 240 | 0
01 | 01-0G1004 | 0G1004 | 01-DN-101-12.5/15.5 | 20.20 201130 |  | G R Sundberg, Inc. | 5211 Boyd Road | Arcata, Ca 95521 | 7078256565 | 7074984009 | 207 Price Mall | Crescent City, Ca 95531 | Sanders, Karen | 23475 | 0 | 0 | 0 | 2021-04-09 | Roadway Stabilization And Retaining Wall R | In Del Norte County Near Klamath From 0.4 Mile South Of Wilson Creek Bridge To 1.7 Miles North Of Rudisil Road Dir'S Emergency F. | 100 | 100 | 11984108.87 | 23475 | 11985000 | 33563 | 2021-04-09 | 2016-05-04 | 2016-02-16 |  |  | 160 | 0 | 60 | 0 |  | X
01 | 01-436404 | 436404 | 01-DN-101-35.8/36.5 | HA21 | ACNH-Q101- (398)E | Mcm Construction, Inc. | Po Box 620 | North Highlands Ca 95660 | 9163341221 | 7074965581 | 207 Price Mall Suite 100 | Crescent City, Ca 95531 | Malmberg, Clayton | 4532695.81 | 25704.26 | 0 | 0 | 2025-10-20 | Replace Bridge | In Del Norte County Near Crescent City From 0.3 Mile South Of Smith River Bridge To 0.4 Mile North Of Smith River Bridge | 89 | 83 | 62915600.54 | 72443463 | 75010314.99 | 43785 | 2026-01-18 | 2022-08-02 | 2022-07-11 |  |  | 768 | 0 | 860 | 0 |  | X
01 | 01-0J8904 | 0J8904 | 01-HUM-36-3.9/6 |  | NHHS-S036- (122)E | Mercer-Fraser Company | 200 Dinsmore Dr | Fortuna Ca 95540 | 7074430332 | 7074960332 | 1487 Sandy Prairie Court Ste E | Fortuna Ca 95501 | Long Cody | 912824.01 | 0 | 0 | 0 | 2025-10-20 | Hot Mix Asphalt, Aggregate Base, And Struc | Humboldt County At Carlotta From 0.2 Mile West Of Fisher Road To 0.2 Mile West Of Wilder Road | 26 | 48 | 5587002.97 | 11410410 | 11519640.55 | 57129 | 2026-12-01 | 2025-01-29 | 2024-12-06 |  |  | 98 | 0 | 370 | 0 |  | X
01 | 01-0C5004 | 0C5004 | 01-HUM-36-11.3/34.6 | HA21 | ACNH-S036- (118)E | Mercer Fraser Company | 200 Dinsmore Dr | Fortuna Ca 95540 |  | 7076210000 | 1487 Sandy Praire Court Ste. E | Fortuna, Ca 95540 | Rodriguez, Joaquin | 443094.77 | 0 | 0 | 0 | 2025-10-20 | Replace Bridge Rails. | Humboldt County On Route 36 At Hely Creek Bridge 04-0092 At Little Larabee Creek Bridge 04-0102 And At Butte Creek Bridge 04-0116 | 69 | 62 | 9502635.14 | 14853018.91 | 15136437.3 | 48230 | 2026-05-01 | 2023-03-24 | 2023-03-02 |  |  | 289 | 0 | 420 | 0 |  | X
01 | 01-0H6104 | 0H6104 | 01-HUM-36-13.5/36.1 | HA22 | ACNH-S036- (119)E | Mercer Fraser Company | 200 Dinsmore Dr | Fortuna Ca 95540 |  | 7076210000 | 1487 Sandy Praire Court Ste E | Fortuna, Ca 95540 | Rodriguez, Joaquin | 634565.9 | 0 | 0 | 0 | 2025-10-20 | Cold Plane And Overlay Hma, & Replace Guar | Humboldt County At And Near Bridgeville From 3.4 Miles West Of Grizzly Creek Bridge To 0.8 Mile East Of South Fork Van Duzen River | 91 | 99 | 37838146.69 | 36777777 | 37290777 | 54144 | 2025-11-10 | 2023-11-30 | 2023-10-31 |  | S | 128 | 0 | 140 | 0 |  | X
01 | 01-0P1804 | 0P1804 | 01-HUM-36-25.4/26 | 20.XX 201130 |  | Gr Sundberg, Inc. | 5211 Boyd Road | Arcata, Ca 95521 |  | 7074960332 | 1487 Sandy Prairie Court Ste. E | Fortuna Ca 95501 | Long, Cody | 0 | 0 | 0 | 0 | 2025-09-20 | Repair Slipout | In Humboldt County Near Bridgeville From Caltrans Maintenance Station To 0.6 Mile East Of Caltrans Maintenance Station Dir'S Emerg | 100 | 77 | 9757906.83 | 43485 | 12675000 | 55965 | 2025-10-30 | 2024-05-21 | 2024-04-15 |  |  | 183 | 0 | 119 | 0
01 | 01-461704 | 461704 | 01-HUM-36-25.4/0 |  |  | Nico Engineering, Inc. | 1409 Colin St | San Pablo Ca 94806 | [5 empty] | 0 | 0 | 0 | 0 |  | Water Treatment System Upgrade And Replace | Humboldt County Near Bridgeville At The Bridgeville Maintenance Station | 0 | 0 | 0 | 835886 | 835886 | 59377 |  | 2025-07-16 | 2025-05-28 |  |  | 0 | 0 | 135 | 0
01 | 01-0M8104 | 0M8104 | 01-HUM-36-70.0/42 | 20.20 201130 |  | G R Sunberg Inc. | 5211 Boyd Road | Arcata, Ca 95521 |  | 7078340219 | 1487 Sandy Praire Court Suite E | Fortuna, Ca 95501 | Morgan-Marbet, Tai | 0 | 0 | 0 | 0 | 2025-07-20 | Repair Drainage Systems | Mobilization, Traffic Control, Remove Slide Debris, Stabilize Slope, Repair Drainage And Other Items As Required | 89 | 96 | 23642296.71 | 28475 | 24550000 | 47705 | 2025-09-01 | 2023-03-13 | 2023-01-10 | 2025-10-17 |  | 216 | 0 | 242 | 0 |  | X
01 | 01-0P8204 | 0P8204 | 01-HUM-36-155.0/16.5 | 20.XX 201130 |  | Gr Sundberg Inc | 5211 Boyd Rd | Arcata Ca 95521 |  | 7074960332 | 1487 Sandy Prarie Court Ste E | Fortuna Ca 95501 | Long Cody | 0 | 0 | 0 | 0 | 2025-10-20 | Pavement Repairs | Repair Slide Hum Cnty 10 Miles E Of Carlotta Erosion Cntrl Slide Removal Invest Slope Dir'S Emergency F.A. | 0 | 74 | 9142590.55 | 15975 | 27285000 | 57070 | 2026-07-20 | 2025-02-11 | 2024-12-17 |  |  | 0 | 0 | 120 | 0 |  | X
01 | 01-0P9504 | 0P9504 | 01-HUM-36-170.0/24 | 20.XX 201130 |  | Mccullough Construction Inc. | 57 Aldergrove Road | Arcata Ca 95521 |  | 7074960332 | 1487 Sandy Prairie Court Ste. E | Fortuna Ca 95501 | Long Cody | 0 | 0 | 0 | 0 | 2025-06-20 | Slide Repair | Repair Slide Hum Cnty Near Bridgeville From Grizzly Slide Removal And Slope Grading Dir'S Emergency F.A. | 0 | 31 | 607171.13 | 10350 | 1985000 | 57385 | 2025-12-12 | 2025-03-20 | 2025-02-04 |  |  | 0 | 0 | 120 | 0 |  | X
01 | 01-0P9004 | 0P9004 | 01-HUM-36-190.0/20.1 | 20.XX 201130 |  | J.F. Shea Construction | 667 Brea Canyon Road Ste 30 | Walnut Ca 91789 |  | 7076210000 | 1487 Sandy Prairie Court Ste E | Fortuna Ca 95540 | Rodriguez Joaquin | 0 | 0 | 0 | 0 | 2025-10-20 | Repair Storm Damage | Repair Storm Damage In Hum Cnty Near Bridgeville Repair Roadway Embankment With Retaining Dir'S Emergency F.A. | 32 | 61 | 4556232.57 | 30000 | 7485000 | 57397 | 2026-02-20 | 2025-03-26 | 2025-03-10 |  |  | 38 | 0 | 120 | 0 |  | X
01 | 01-0Q0304 | 0Q0304 | 01-HUM-36-279.0/27.9 | 20.XX 201130 |  | Mercer Fraser Company | 200 Dinsmore Dr | Fortuna Ca 95540 |  | 7076210000 | 1487 Sandy Prairie Court Suite E | Fortuna Ca 95540 | Rodriguez Joaquin | 0 | 0 | 0 | 0 | 2025-06-20 | Pavement Repair | Repair Storm Damage Hum Cnty Near Bridgeville At 2.5 Miles Repair Roadway And Replace Culvert Dir'S Emergency F.A. | 56 | 20 | 255837.56 | 7560 | 1285000 | 57916 | 2025-09-24 | 2025-04-16 | 2025-02-21 |  |  | 84 | 0 | 150 | 0 |  | X
01 | 01-0N4504 | 0N4504 | 01-HUM-36-365.0/40 | 20.20 201130 |  | Garth R. Sunberg, Jr. Gr Sunberg, Inc. | 5211 Boyd Road | Arcata, Ca 95521 |  | 7074960332 | 1487 Sandy Praire Court Suite E | Fortuna, Ca 95540 | Long, Cody | 0 | 0 | 0 | 0 | 2025-04-20 | Repair Storm Damage | Major Items Of Work Include Traffic Control, Roadway Excavation, Rock Slope, Reconstruct Roadway, Erosion Control Dir'S Emergency | 27 | 41 | 1022272.99 | 15975 | 2485000 | 53784 | 2025-08-04 | 2023-08-25 | 2023-08-20 | 2025-10-22 |  | 27 | 0 | 100 | 0 |  | X
01 | 01-0N8304 | 0N8304 | 01-HUM-96-4.9/13.3 |  |  | American Pavement Systems, Inc. | 1012 11Th Street | Modesto Ca 95354 |  | 7072230030 | 5065 Boyd Rd, Suite G | Arcata, Ca 95521 | Ethan Retherford | 16000 | 0 | 0 | 0 | 2025-08-26 | Place Rubber Chip Seal, Micro-Surfacing, A | Humboldt County At Hoopa From 4.6 Miles East Of Willow Creek Bridge To Hostler Creek Bridge | 100 | 100 | 2466584 | 2522785 | 2552785 | 58695 | 2025-08-26 | 2025-04-24 | 2025-04-03 | 2025-09-23 |  | 36 | 0 | 40 | 0 |  | X
01 | 01-0F9204 | 0F9204 | 01-HUM-96-43.7/0 |  |  | Wylatti Resource Management, Inc | 23601 Cemetery Lane | Covelo Ca 95428 | 7079838135 | 7074982122 | 5065 Boyd Road Suite H | Arcata, Ca 95521 | Zimmerer, Jeffrey | 0 | 0 | 0 | 0 | 2025-10-20 | Restore Disposal Site | In Humboldt County Near Orleans At 1.2 Miles West Of Siskiyou County Line | 53 | 72 | 481257.05 | 640523.23 | 664323.23 | 42244 | 2028-12-15 | 2022-03-16 | 2022-02-03 |  |  | 689 | 0 | 1290 | 0 |  | X
01 | 01-0H6404 | 0H6404 | 01-HUM-101-2.4/M53.9 |  | PTNH-Q101- (436)E | Wylatti Resource Management, Inc. | 23601 Cemetery Lane | Covelo Ca 95428 |  | 7076210000 | 1487 Sandy Prairie Court Ste E | Fortuna, Ca 95540 | Rodriguez, Joaquin | 806080.58 | 45462.91 | 0 | 32391.69 | 2025-10-20 | Wsp Trenchless Installation, Csp, And Eros | Humboldt County At Various Locations From 2.4 Miles North Of The Mendocino County Border To Eel River Bridge 04-0016R | 42 | 50 | 6598847.36 | 13097292.18 | 13247292.18 | 57072 | 2026-01-27 | 2025-01-29 | 2025-01-13 |  |  | 99 | 0 | 235 | 0 |  | X
01 | 01-0H6504 | 0H6504 | 01-HUM-101-55.9/136.4 |  | ACNH-Q101- (445)E | Wahlund Construction, Inc. | 690 Indianola Rd | Eureka Ca 95503 | [5 empty] | 0 | 0 | 0 | 0 |  | Construct & Repair Tms Elements; Csp, Rcp, | Humboldt County Near Alton From 0.3 Mile South Of Van Duzen River Bridge 4-17 To Del Norte County Line | 0 | 0 | 0 | 16016104.15 | 16016104.15 | 59798 |  | 2025-08-12 | 2025-07-25 |  |  | 0 | 0 | 191 | 0
01 | 01-0K9404 | 0K9404 | 01-HUM-101-74.8/76.1 |  | ACNH-Q101- (434)E | G R Sundberg, Inc. | 5211 Boyd Road | Arcata Ca 95521 |  | 7072725831 | 5601 South Broadway St Suite A | Eureka, Ca 95503 | Collins, Robin | 535768.85 | 0 | 0 | 0 | 2025-10-20 | Lighting System, Fiber Optic Cable System, | Humboldt County In And Near Eureka From Herrick Avenue Overcrossing To 0.1 Mile North Of Highland Avenue | 24 | 54 | 5797050.57 | 10429084 | 10653124 | 57130 | 2027-06-24 | 2024-12-27 | 2024-12-12 |  |  | 110 | 0 | 450 | 0 |  | X
01 | 01-0P9804 | 0P9804 | 01-HUM-101-75.0/108.5 | 20.XX 201130 |  | Kernen Construction | 2350 Glendale Drive | Mckinleyville Ca 95519 |  | 7073469027 | 5065 Boyd Road Suite G | Arcata Ca 95521 | Dunne Ryan | 0 | 0 | 0 | 0 |  | Repair Storm Damage | Repair Storm Damage Hum Cnty Near Big Lagoon Install Underdrain Dir'S Emergency F.A. | 0 | 0 | 0 | 7250 | 1485000 | 59995 | 2025-08-22 | 2025-07-29 | 2025-06-30 |  |  | 0 | 0 | 60 | 0
01 | 01-0N6604 | 0N6604 | 01-HUM-101-78.0/79.6 |  |  | G R Sundberg, Inc. | 5211 Boyd Road | Arcata Ca 95521 |  | 7072725831 | 6501 South Broadway St | Eureka, Ca 95503 | Collins, Robin | 107484.44 | 0 | 0 | 0 | 2025-10-20 | Rectangular Rapid Flashing Beacons Systems | Humboldt County In Eureka On Route 101 From 0.1 Mile South Of Commercial Street To Y Street And On Route 255 At 3Rd Street | 40 | 37 | 407283.6 | 1041244.25 | 1101244.25 | 59799 | 2025-12-08 | 2025-07-02 | 2025-06-19 |  |  | 18 | 0 | 45 | 0 |  | X
01 | 01-366004 | 366004 | 01-HUM-101-80.0/84 |  | ACNH-394 - (E )000 | Granite Construction Company | 1324 S. State Street | Ukiah Ca 95482 | 7074674100 | 7074961086 | 5065 Boyd Road | Arcata, Ca 95521 | Banuelos, Efren | 3043880.97 | 61967.28 | 0 | 0 | 2025-10-20 | Construct Interchange, Structure Undercros | Humboldt County Near Eureka From Eureka Slough Bridge To Bayside Cutoff | 68 | 86 | 42998713.83 | 46643866.36 | 48989478.09 | 46464 | 2027-07-23 | 2023-01-26 | 2022-12-29 |  |  | 339 | 0 | 490 | 5 |  | X
01 | 01-0J3604 | 0J3604 | 01-HUM-101-103.3/103.7 |  |  | G R Sundberg, Inc. | 5211 Boyd Road | Arcata Ca 95521 |  | 7073469027 | 5065 Boyd Road Suite H | Arcata, Ca 95521 | Dunne, Ryan | 0 | 0 | 0 | 0 |  | Stream Intake, Well Sump, And Water Backwa | Humboldt County Near Trinidad From Seawooddrive Undercrossing To 0.3 Mile North Of Seawood Drive Undercrossing | 0 | 0 | 0 | 790060 | 790060 | 59156 |  | 2025-06-26 | 2025-06-11 |  |  | 0 | 0 | 100 | 0
01 | 01-0M6504 | 0M6504 | 01-HUM-101-125.7/131.7 |  |  | Granite Construction Company | 1324 S. State Street | Ukiah Ca 95482 |  | 7073469027 | 5065 Boyd Road Suite G | Arcata, Ca 95521 | Dunne, Ryan | 665809.8 | 0 | 0 | 0 | 2025-09-16 | Replace Ac Surfacing And Delineation. | Humboldt County On Route 101 From 0.40 Mile South Of South Prairie Creek Undercrossing To 2.76 Miles North Of Boyescreek Viaduct | 100 | 100 | 2854758.64 | 2970101 | 2970101 | 59298 | 2025-09-16 | 2025-07-09 | 2025-06-09 | 2025-10-14 |  | 27 | 0 | 30 | 0 |  | X
01 | 01-0P8704 | 0P8704 | 01-HUM-101-330.0/18 | 20.XX 201130 |  | Ford Logging Inc. Dba Pacific Earthscape | 1225 Central Ave. #11 | Mckinleyville Ca 95519 |  | 7074960332 | 1487 Sandy Prairie Court Ste. E | Fortuna Ca 95501 | Long Cody | 0 | 0 | 0 | 0 | 2025-10-20 | Repair Landslide | Repair Landslide Hum Cnty At Various Locations Construct Retaining Wall Repair Damage Dir'S Emergency F.A. | 0 | 8 | 529976.47 | 37475 | 6985000 | 59196 | 2026-10-20 | 2025-06-25 | 2025-03-13 |  |  | 0 | 0 | 120 | 0 |  | X
01 | 01-0K4204 | 0K4204 | 01-HUM-101-595.0/0 | 20.80 524000 |  | Mountainside Construction | 13884 Shangrila Drive | Redding, Ca 96003 |  | 7077251020 | 1487 Sandy Prairie Court Ste. E | Fortuna, Ca 95501 | Rodriguez, Joaquin | 0 | 0 | 0 | 0 | 2021-02-02 | Repair To Prevent Further Power Outages | In Fortuna Maintenance Station And Some Electrical System Rehabilitation At The Leggett Maintenance Station. Dir'S Emergency L.B. | 100 | 100 | 253357.98 | 4900 | 245000 | 40971 | 2021-02-02 | 2020-05-03 | 2020-02-21 |  |  | 120 | 0 | 120 | 0 |  | X
01 | 01-0P0604 | 0P0604 | 01-HUM-101-834.0/83.4 | 20.10 201352 |  | Wylatti Resource Management, Inc. | Po Box 575 | Covelo, Ca 95428 |  | 7072725831 | 5601 South Broadway St. | Eureka, Ca 95503 | Collins, Robin | 0 | 0 | 0 | 0 | 2025-08-20 | Maintenance Station Security Improvements | In Del Norte, Humboldt, Lake And Mendocino Counties At Various Locations Dir'S Emergency L.B. | 36 | 91 | 2531157.57 | 17475 | 2785000 | 56554 | 2025-09-30 | 2024-08-22 | 2024-06-03 |  |  | 107 | 0 | 300 | 0 |  | X
01 | 01-0H4104 | 0H4104 | 01-HUM-169-15.0/33.8 |  |  | R. Brown Construction Company,Inc. | 18 China Creek Rd. | Willow Creek Ca 95573 |  | 7074961086 | 5065 Boyd Road Suite G | Arcata, Ca 95521 | Baneulos, Efren | 724575.8 | 0 | 0 | 12500 | 2025-10-20 | Csp, Structural Concrete, And Rsp. | Humboldt County Near Weitchpec At Various Locations From 0.6 Mile East Of Pecwan Creek Bridge To Route 96 | 32 | 73 | 2431203.7 | 3281191.6 | 3281191.6 | 58398 | 2026-02-13 | 2024-10-31 | 2024-10-09 |  |  | 63 | 0 | 200 | 0 |  | X
01 | 01-0P8904 | 0P8904 | 01-HUM-169-250.0/26 | 20.XX 201130 |  | R. Brown Construction Company | Po Box 406 | Willow Creek Ca 95573 |  | 7074961086 | 5065 Boyd Rd Suite H | Arccata Ca 95521 | Banuelos Efren | 0 | 0 | 0 | 0 | 2025-10-20 | Pavement Repair | Repair Storm Damage Hum Cnty Near Weitchpec From Mawah Creek Repair Roadway Embankment With Retain Walldir'S Emergency F.A. | 9 | 4 | 281766.18 | 35568 | 7485000 | 58676 | 2026-04-02 | 2025-03-10 | 2025-03-03 |  |  | 11 | 0 | 120 | 0 |  | X
01 | 01-0M6304 | 0M6304 | 01-HUM-211-74.2/79.3 |  |  | Dryco Construction, Inc. Dba Dryco | 9390 Elder Creek Road | Sacramento Ca 95829 |  | 7076210000 | 1487 Sandy Prairrie Court St E | Fortuna, Ca 95540 | Rodriguez, Joaquin | 0 | 0 | 0 | 0 |  | Micro-Surfacing, Replace Ac Surfacing, And | Humboldt County In And Near Ferndale From 0.4 Mile South Of Salt River Overflow To Singley Road | 0 | 0 | 0 | 1061579.2 | 1061579.2 | 59828 | 2025-12-08 | 2025-04-21 | 2025-03-26 |  |  | 0 | 0 | 25 | 0
01 | 01-0M7304 | 0M7304 | 01-HUM-211-772.0/78.6 | 20.20 201130 |  | Myers & Sons Construction Llc | 45 Morrison Ave. | Sacramento, Ca 95838 |  | 7078340219 | 1487 Sandy Praire Court Suite E | Fortuna, Ca 95501 | Morgan-Marbet, Tai | 0 | 0 | 0 | 0 | 2025-10-20 | Fernbridge Bridge Repair | Emergency Earthquake Bridge Repair Dir'S Emergency F.A. | 83 | 90 | 25075466.64 | 36000 | 27985000 | 46364 | 2025-12-29 | 2023-01-06 | 2022-12-20 |  |  | 208 | 0 | 250 | 0 |  | X
01 | 01-0H8004 | 0H8004 | 01-HUM-254-4.3/4.7 |  | ACST-ER - (31D)004 | Mccullough Construction Inc | 57 Aldergrove Road | Arcata Ca 95521 |  | 7074960332 | 1487 Sandy Prairie Ct., Ste. E | Fortuna, Ca 95501 | Long, Cody | 14427.4 | 0 | 0 | 0 | 2025-10-20 | Rdwy Exc, Steel Soldier Piles, Structural | Humboldt County Near Miranda From 0.1 Milenorth Of Fish Creek Road To 0.1 Mile Southof Maple Hills Road | 96 | 98 | 8816459.69 | 8657906.89 | 8887691.42 | 48229 | 2025-10-31 | 2023-04-04 | 2023-03-10 | 2025-10-30 |  | 249 | 0 | 260 | 0 |  | X
01 | 01-0N7304 | 0N7304 | 01-HUM-255-8.3/8.7 |  |  | St. Francis Electric, Llc | 975 Carden St | San Leandro Ca 94577 | [5 empty] | 0 | 0 | 0 | 0 |  | Modify Signal And Lighting Systems And Tra | Humboldt County In Arcata From K Street Tof Street | 0 | 0 | 0 | 693700 | 693700 | 59299 |  | 2025-07-09 | 2025-06-13 |  |  | 0 | 0 | 30 | 0
01 | 01-0H5804 | 0H5804 | 01-HUM-299-7.6/29.2 | HA22 | ACNH-P299- (216)E | Granite Construction Company | 580 W Beach Street | Watsonville Ca 95076 |  | 7072725831 | 5601 South Broadway Suite A | Eureka, Ca 95503 | Collins, Robin | 273002.65 | 24229.03 | 0 | 0 | 2025-08-20 | Rhma, Hma And Replace Ac Surfacing. | Humboldt County At Various Locations From 0.5 Mile East Of Blue Lake Boulevard To 0.1 Mile East Of Titlow Hill Road | 99 | 92 | 14124014.11 | 13953679 | 14208588.87 | 53464 | 2025-10-24 | 2023-10-25 | 2023-09-25 |  |  | 131 | 0 | 130 | 2 |  | X
01 | 01-0N0904 | 0N0904 | 01-HUM-299-9.0/.6 | 20.XX 201130 |  | Mccullough Construction Inc | 57 Aldergrove Rd | Arcata Ca 95521 | 7078251014 | 7072230030 | 5065 Boyd Rd | Arcata Ca 9551 | Retherford, Ethan | 0 | 594921.63 | 0 | 0 | 2025-10-20 | Pavement Repairs | Repair Storm Damage Humboldt Cnty 19 M West Of Willow Creek Traffic Control Remove Embank Etc. Dir'S Emergency F.A. | 67 | 49 | 2434364.18 | 26719 | 4985000 | 52885 | 2025-12-09 | 2023-07-25 | 2023-06-19 |  |  | 67 | 0 | 100 | 0 |  | X
01 | 01-0P4004 | 0P4004 | 01-HUM-299-22.0/2.2 | 20.XX 201130 |  | Granite Construction Inc | 1324 S State Street | Ukiah Ca 95482 |  | 7074961086 | 5065 Boyd Rd Suite H | Arcata Ca 95521 | Banuelos, Efren | 0 | 0 | 0 | 0 | 2025-07-20 | Repair Fire Damage | Repair Fire Damage Humbodlt Cnty Glendale At 0.3 Miles East Traffic Cntrl Hazard Tree Removal Dir'S Emergency F.A. | 47 | 89 | 701176 | 1800 | 785000 | 56846 | 2025-09-03 | 2024-12-18 | 2024-07-03 |  |  | 28 | 0 | 60 | 0 |  | X
01 | 01-0J4104 | 0J4104 | 01-HUM-299-30.7/33.4 | HB1 | HSNH-P299- (214)E | Mccullough Construction Inc | 57 Aldergrove Road | Arcata Ca 95521 |  | 7072230030 | 5065 Boyd Road, Suite G | Arcata, Ca 95521 | Retherford, Ethan | 1770968.1 | 15629.67 | 0 | 0 | 2025-10-20 | Construct Soldier Pile Ground Anchor Walls | Humboldt County Near Willow Creek From 0.1Mile East Of Cedar Creek Road To 0.1 Mile East Of East Fork Willow Creek Bridge | 100 | 90 | 18368717.72 | 19584945.52 | 20105351.72 | 46186 | 2025-10-31 | 2022-12-27 | 2022-11-28 |  |  | 356 | 0 | 320 | 0 |  | X
01 | 01-0P9104 | 0P9104 | 01-HUM-299-210.0/22 | 20.XX 201130 |  | Kernen Construction | 2350 Glendale Drive | Mckinleyville Ca 95519 | 7078268686 | 7072230030 | 5065 Boyd Rd | Suite G Arcata 95521 | Retherford Ethan | 0 | 0 | 0 | 0 | 2025-10-20 | Pavement Repairs | Repair Storm Damage Hum Cnty 14 Miles East Of Blue Lake Repair Roadyway And Drainage Dir'S Emergency F.A. | 4 | 4 | 52492.84 | 7250 | 1485000 | 58175 | 2026-02-13 | 2025-05-06 | 2025-04-08 |  |  | 3 | 0 | 80 | 0 |  | X
01 | 01-0Q1104 | 0Q1104 | 01-HUM-299-235.0/27.3 | 20.XX 201130 |  | Mccullough Construction Inc | 57 Alder Grove Rd | Arcata Ca 95521 |  | 7072230032 | 6501 South Broadway Street Suite A | Eureka Ca 95503 | Walker Kristina | 0 | 0 | 0 | 0 |  | Repair Storm Damage | Repair Storm Damage Hum Cnty 12 Miles West Of Willow Creek Stabilize Slope Repair Guardrail Dir'S Emergency F.A. | 0 | 0 | 0 | 17888 | 3485000 | 60142 | 2026-04-09 | 2025-06-09 | 2025-05-05 |  |  | 0 | 0 | 120 | 0
01 | 01-0P8404 | 0P8404 | 01-HUM-451-30.0/4 | 20.XX 201130 |  | Ford Logging, Inc Dba Pacific Earthscape | 1225 Central Avenue, Suite 11 | Mckinleyville, Ca 95519 |  | 7074960332 | 1487 Sandy Prairie Court Ste. E | Fortuna Ca 95501 | Long, Cody | 0 | 0 | 0 | 0 | 2025-10-20 | Repair Storm Damage | In Humboldt County Near Phillipsville From0.23 Mile North Of Franklin Grove To 0.8 Msouth Of Maple Hills Road Dir'S Emergency F.A | 0 | 28 | 824875.28 | 6975 | 2985000 | 57215 | 2026-10-31 | 2025-02-27 | 2024-12-19 |  |  | 0 | 0 | 120 | 0 |  | X
01 | 01-0H8404 | 0H8404 | 01-LAK-20-2.0/2.8 | HB1 | HSST-P020- (201)E | Ghilotti Construction Company,Inc. | 246 Ghilotti Avenue | Santa Rosa Ca 95407 | 7079780441 | 7072231213 | Po Box 457 | Lower Lake, Ca 95457 | Seyoum, Kassaye | 541870.79 | 4571 | -4378.98 | 0 | 2025-10-20 | Rdwy Exc, Place Hma-A & Rhma, Const Soldie | Lake County About 6 Miles West Of Upper Lake From 0.6 Mile West Of Irvine Avenue To 0.1 Mile East Of Mid Lake Road | 97 | 96 | 15565219.85 | 15624772.41 | 16191045.41 | 52267 | 2026-10-20 | 2023-08-23 | 2023-07-21 |  |  | 302 | 0 | 310 | 0 |  | X
01 | 01-0N6804 | 0N6804 | 01-LAK-20-16.6/18.1 |  |  | American Civil Constructors West Coast, Llc | 2990 Bay Vista Court, Suite D | Benicia Ca 94510 | [5 empty] | 0 | 0 | 0 | 0 |  | Rectangular Rapid Flashing, Surface Treatm | Lake County At Lucerne From Grove Street To Ogden Road | 0 | 0 | 0 | 694000 | 694000 | 59515 |  | 2025-07-23 | 2025-06-10 |  |  | 0 | 0 | 30 | 0
01 | 01-0N8204 | 0N8204 | 01-LAK-29-23.6/33.1 |  |  | Doolittle Construction, Llc Dba Doolitlle Road Construction | 15 Business Parkway Suite 105 | Sacramento Ca 95828 |  | 7079945074 | P.O. Box 457 | Lower Lake, Ca 95457 | Seyoum, Kassaye | 235549.15 | 0 | 0 | 0 | 2025-10-20 | Micro-Surfacing, Replace Ac Surfacing, And | Lake County Near Kelseyville From 3.23 Miles North Of Seigler Creek Bridge To Cole Creek Road | 92 | 98 | 1071441.71 | 1029000 | 1041500 | 58217 | 2025-10-27 | 2025-05-19 | 2025-04-29 | 2025-10-22 |  | 23 | 0 | 25 | 0 |  | X
01 | 01-0P3604 | 0P3604 | 01-LAK-175-/8.2 |  |  | Argonaut Constructors, Inc. | 360 Sutton Place | Santa Rosa Ca 95407 |  | 7078341151 | Po Box 457 | Lower Lake, Ca 95457 | Winter, Brian | 79396.43 | 0 | 0 | 0 | 2025-10-20 | Replace Ac Surfacing, Micro-Surfacing, And | Lake County Near Lakeport From The Mendocino County Line To 1.3 Miles East Ofmathews Road | 69 | 99 | 3027248.97 | 3022843.15 | 3054843.15 | 58618 | 2025-10-27 | 2025-06-09 | 2025-05-22 |  |  | 38 | 0 | 55 | 0 |  | X
01 | 01-0P7704 | 0P7704 | 01-LAK-200-447.0/45.2 | 20.XX 201130 |  | Ghilotti Construction Company, Inc | 246 Ghilotti Ave. | Santa Rosa, Ca 95407 |  | 7079945074 | P.O. Box 457 | Lower Lake, Ca 95457 | Seyoum, Kassaye | 0 | 0 | 0 | 0 | 2025-08-20 | Repair Slipout | In Lake County About 16 Miles East Of Clearlake Oaks From 1.1 To 1.6 Miles East Of Walker Ridge Road Dir'S Emergency F.A. | 99 | 37 | 1090075.7 | 16255 | 2985000 | 57384 | 2025-09-30 | 2025-02-27 | 2024-12-16 |  |  | 119 | 0 | 120 | 0
01 | 01-0P9604 | 0P9604 | 01-MEN-1-6.0/.6 | 20.XX 201130 |  | Wylatti Resource Management | P.O. Box 575 | Covelo Ca 95428 |  | 7074985816 | 925 N Franklin Street | Fort Bragg Ca 95437 | Mosallai Mojtaba | 0 | 0 | 0 | 0 | 2025-10-20 | Pavement Repairs | Repair Storm Damage Men County New Gualala At Old State Hwwy Repair Roadway And Drainage Dir'S Emergency Order F.A. | 62 | 37 | 3673871.77 | 49325 | 9885000 | 58658 | 2026-01-30 | 2025-05-06 | 2025-04-14 |  |  | 112 | 0 | 180 | 0 |  | X
01 | 01-0F7104 | 0F7104 | 01-MEN-1-6.4/9.5 |  | HSST-S001- (667)E | Ghilotti Construction Company,Inc. | 246 Ghilotti Avenue | Santa Rosa Ca 95407 |  |  | 925 N. Franklin Street | Fort Bragg, Ca 95437 | Chen, Peng | 340336.74 | 0 | 0 | 0 | 2025-10-20 | Hma-A, Roadway Excavation, And Mechanicall | Mendocino County Near Gualala From 0.3 Mile North Of Havens Neck Drive To Gypsy Flat Road And From 0.5 Mile To 0.2 Mile South Of I | 17 | 83 | 3398595.78 | 3962961.2 | 4077961.2 | 56928 | 2025-10-30 | 2025-01-07 | 2024-12-26 |  | S | 52 | 0 | 310 | 0 |  | X
01 | 01-0E11U4 | 0E11U4 | 01-MEN-1-31.1/31.6 |  | ACST-S001- (662)E | Granite Construction Company | 580 W Beach Street | Watsonville Ca 95076 | 7074674100 | 7074985816 | 925 N Franklin St | Fort Bragg Ca 95437 | Mosallai Mojtaba | 971060.57 | 10270.18 | 0 | 0 | 2025-10-20 | Structural Conc Bridge, Temp Bridge And Ba | Mendocino County Near Elk From 0.2 Mile South Of Elk Creek Bridge To 0.2 Mile North Of Elk Creek Bridge | 99 | 87 | 10774382.81 | 11983837.38 | 12347545.08 | 54644 | 2025-10-31 | 2023-12-13 | 2023-11-15 |  |  | 176 | 0 | 175 | 2 |  | X
01 | 01-0H6004 | 0H6004 | 01-MEN-1-33.7/51 |  | ACST-S001- (668)E | Argonaut Constructors | 360 Sutton Place | Santa Rosa Ca 95407 |  | 7074985816 | 925 N Franklin Street | Fort Bragg, Ca 95437 | Mosallai, Mojtaba | 620862.88 | 63889.44 | -24344.93 | 0 | 2025-10-20 | Hma, Rhma, Cold Plane, Guardrail, And Deli | Mendocino County Near Elk From 0.1 Mile North Of Greenwood Creek Bridge To 0.2 Mile North Of Little Lake Road At Mendocino | 55 | 87 | 21861612.84 | 24565444 | 24833123.17 | 57128 | 2025-12-05 | 2025-01-24 | 2024-11-25 |  |  | 99 | 0 | 180 | 0 |  | X
01 | 01-434844 | 434844 | 01-MEN-1-51.3/52.1 | HA21 | ACST-S001- (664)E | Mccullough Construction Inc | 57 Aldergrove Road | Arcata Ca 95521 | 7078251014 | 7074985816 | 925 N Franklin Street | Fort Bragg, Ca 95437 | Mosallai, Mojtaba | 895200.36 | 16245.98 | 0 | 0 | 2025-10-20 | Structural Concrete, Bar Reinforcing Steel | Mendocino County At Mendocino From Larkin Road To 0.2 Mile South Of Surfwood Estatesroad | 98 | 92 | 11361443.31 | 11390269.44 | 12302525.86 | 54724 | 2025-10-30 | 2024-01-10 | 2023-12-12 |  | S | 280 | 0 | 285 | 0 |  | X
01 | 01-0P7404 | 0P7404 | 01-MEN-1-114.0/11.6 | 20.XX 201130 |  | Engelke Construction Inc | Po Box 1387 | Healdsburg Ca 95448 |  | 7074338389 | 925 N Franklin Street | Fort Bragg Ca 95437 | Mossallai Mojtaba | 0 | 0 | 0 | 0 | 2025-09-20 | Pavement Repair | Repair Slipout In Mendo Cnty In Galloway From 0.02 Mile Erosion Cntrl Guardrail Repair Roadway Dir'S Emergency F.A. | 100 | 49 | 981070.46 | 12975 | 1985000 | 57132 | 2025-12-31 | 2025-02-25 | 2024-12-16 |  |  | 199 | 0 | 120 | 0
01 | 01-0Q1004 | 0Q1004 | 01-MEN-1-418.0/42.5 | 20.XX 201130 |  | Wylatti Resource Management | P.O. Box 575 | Covelo Ca 95428 |  | 7074985816 | 925 N. Franklin Street | Fort Bragg Ca 95437 | Mosallai Mojtaba | 0 | 0 | 0 | 0 | 2025-09-20 | Repair Slide | Repair Slide Men Cnty Two Miles South Of Albion Stabelize Cutslope With Dirt Filled Rsp Dir'S Emergency F.A. | 50 | 73 | 1452280.32 | 12975 | 1985000 | 58955 | 2025-11-25 | 2025-05-07 | 2025-05-05 |  |  | 45 | 0 | 90 | 0 |  | X
01 | 01-0P1704 | 0P1704 | 01-MEN-1-749.0/78 | 20.XX 201130 |  | Wylatti Resource Management | Po Box 575 | Covelo Ca 95428 |  | 7074964368 | 6301 North State Street | Redwood Valley Ca 95470 | Hadipour Roozbeh | 0 | 0 | 0 | 0 | 2025-10-20 | Repair Sink | Multiple Landslide Repair Mendo Cnty Westport Blue Slide Gulch Traffic Cntrl Reconstruct Roadway Dir'S Emergency Order F.A. | 100 | 32 | 796023.53 | 15775 | 2485000 | 55802 | 2025-12-31 | 2024-05-21 | 2024-04-22 |  |  | 293 | 0 | 170 | 0
01 | 01-0N4404 | 0N4404 | 01-MEN-1-750.0/76.5 | 20.XX 201130 |  | Myers & Sons Construction Llc | 45 Morrison Ave | Sacramento Ca 95838 |  | 7074964368 | 6301 North State Street | Redwood Valley Ca 95470 | Hadipour Roozbeh | 0 | 0 | 0 | 0 | 2025-10-20 | Pavement Repairs | Repair Landslide Men Cnty Near Westport Traffic Control Repair Drainage Etc Dir'S Emergency L.B. | 77 | 35 | 38249122.19 | 180000 | 109985000 | 54244 | 2026-05-11 | 2023-09-28 | 2023-09-28 |  |  | 434 | 0 | 240 | 327
01 | 01-0P0704 | 0P0704 | 01-MEN-1-821.0/82.9 | 20.XX 201130 |  | Granite Construction Company | 1324 S. State Street | Ukiah Ca 95482 |  | 7074964368 | 6301 North State Street | Redwood Valley Ca 95470 | Hadipour Roozbeh | 0 | 0 | 0 | 0 | 2025-10-20 | Multiple Location Slipout Repairs | Repair Multiple Slipouts Men Cnty Near Rockport Traffic Cntrl Recon Restruct Rdway Dir'S Emergency F.A. | 79 | 50 | 12392158.69 | 11250 | 24985000 | 55881 | 2026-01-23 | 2024-03-29 | 2024-03-18 |  |  | 237 | 0 | 180 | 120
01 | 01-0N6104 | 0N6104 | 01-MEN-20-14.2/24.4 |  |  | Stimpel-Wiebelhaus Associates,Inc. | 1168 Industrial Street | Redding Ca 96002 |  | 7074985816 | 925 N. Franklin Street | Fort Bragg, Ca 95437 | Mosallai, Mojtaba | 376340 | 0 | 0 | 0 | 2025-09-20 | Replace Drainage Systems. | Mendocino County At Various Locations From0.1 Mile East Of Three Chop Road - Road 8146 To 1.9 Miles West Of Road 8145 | 63 | 82 | 376340 | 458160 | 458160 | 60055 | 2025-10-06 | 2025-07-14 | 2025-06-16 |  |  | 19 | 0 | 30 | 0 |  | X
01 | 01-0E0904 | 0E0904 | 01-MEN-20-33.3/34.4 | HA21 | ACNH-P020- (198)E | Myers & Sons Construction, Llc | 4600 Northgate Blvd, Suite 10 | Sacramento Ca 95834 | 9162839950 | 7074964355 | 6301 North State Street | Redwood Valley, Ca 95470 | Geoffrey Wright | 11200 | 66594.84 | 0 | 0 | 2025-10-20 | Replace Two Bridges | In Mendocino County Near Ukiah From 0.3 Mile West Of Russian River Bridge And Overhead To 0.4 Mile East Of County Road 144 | 66 | 97 | 26987565.68 | 26008165.8 | 27331030.75 | 42689 | 2026-03-18 | 2022-06-09 | 2022-05-06 |  |  | 514 | 0 | 780 | 2 |  | X
01 | 01-0H1604 | 0H1604 | 01-MEN-101-33.7/43.2 | HA22 | ACNH-Q101- (416)E | Granite Construction Company | 715 Comstock St | Santa Clara Ca 95054 | 7074674118 | 7074964355 | 6301 North State Street | Redwood Valley, Ca 95470 | Steve Tisell | 0 | 70617.66 | 0 | 0 | 2025-10-20 | Replace Ac Surfacing, Place Hma-A, Rhma-G | Mendocino County Near Willits From 1.1 Miles North Of West Road Overcrossing To 0.6 Mile South Of Haehl Creek Bridge | 98 | 97 | 23557579.41 | 23216265.6 | 24869039.1 | 50104 | 2025-12-06 | 2023-06-08 | 2023-05-04 |  |  | 168 | 0 | 165 | 6 |  | X
01 | 01-0K4104 | 0K4104 | 01-MEN-101-41.3/43.3 |  | NHHS-Q101- (430)E | Gr Sundberg, Inc. | 5211 Boyd Road | Arcata Ca 95521 | 7078256565 | 7078341151 | 21340 Baechtel Road | Willits, Ca 95490 | Winter Brian | 492990.9 | 14063.3 | 0 | 0 | 2025-10-20 | Concrete Barrier, Wildlife Fence, Clearing | Mendocino County Near Willits From 0.4 Mile North Of Black Bart Road To 0.2 Mile South Of Northbound Offramp To Route 20 | 75 | 65 | 5262660.03 | 7851744.9 | 7906814.13 | 57120 | 2025-12-15 | 2024-10-31 | 2024-10-03 |  |  | 109 | 0 | 145 | 0 |  | X
01 | 01-0H1704 | 0H1704 | 01-MEN-101-48.9/55.1 | HA22 | ACNH-Q101- (423)E | Granite Construction Company 1324 South State Street Ukiah, Ca 95482 | 580 W Beach Street | Watsonville Ca 95076 |  | 7078155647 | 6301 North State Street | Redwood Valley, Ca 95470 | Tisell, Steve | 153040.28 | 2200.54 | 0 | 0 | 2025-05-20 | Cold Plane Ac Pavement And Place Hma-A, Rh | Mendocino County Near Willits From 0.6 Mile North Of Upp Creek Bridge To 0.1 Milesouth Of Big Trails Drive | 74 | 93 | 8670886.27 | 8955869.78 | 9282438.2 | 55911 | 2025-04-21 | 2024-06-05 | 2024-04-26 |  |  | 70 | 0 | 95 | 0 |  | X
01 | 01-0K8904 | 0K8904 | 01-MEN-101-50.7/52.2 |  | NHHS-Q101- (444)E | Granite Construction Company | 1324 S. State Street | Ukiah Ca 95482 |  | 7078155647 | 6301 North State Street | Redwood Valley, Ca 95470 | Tisell, Steve | 283608.2 | 0 | 0 | 142500 | 2025-10-20 | Hma, Roadway Excavation, And High Friction | Mendocino County Near Willits From Outlet Creek To 1.5 Miles North Of Outlet Creek | 6 | 18 | 1020811.2 | 5707962.2 | 5707962.2 | 59275 | 2026-01-08 | 2025-07-01 | 2025-05-21 |  |  | 21 | 0 | 355 | 0 |  | X
01 | 01-0H5504 | 0H5504 | 01-MEN-101-55.0/64.9 |  | ACNH-Q101- (427)E | Granite Construction Company | 580 W Beach Street | Watsonville Ca 95076 |  | 7072231213 |  |  | Seyoum, Kassaye | 319361.97 | 30895.6 | 0 | 0 | 2025-10-20 | Hma, Rhma, And Cold Plane Asphalt Concrete | Mendocino County Near Longvale From 2.6 Miles South Of Arnold Bridge Overhead 10-179 To 0.1 Mile North Of Long Valley Creek Bridge | 57 | 85 | 18214808.87 | 22900700.3 | 23068912.97 | 56414 | 2026-01-01 | 2024-09-18 | 2024-08-15 |  |  | 96 | 0 | 170 | 2 |  | X
01 | 01-0P2604 | 0P2604 | 01-MEN-101-599.0/59.9 | 20.XX 201130 |  | Myers & Sons Construction, Llc | 45 Morrison Ave, | Sacramento, Ca 95838 |  | 7074964368 | 6301 North State Street | Redwood Valley, Ca 95470 | Hadipour, Roozbeh | 0 | 0 | 0 | 0 | 2025-10-20 | Emergency Bridge Deck Repair | In Mendocino County Near Longvale At Long Valley Creek Bridge. Dir'S Emergency F.A. | 100 | 75 | 7280076.62 | 36000 | 9692000 | 56278 | 2025-12-31 | 2024-07-30 | 2024-07-15 |  |  | 251 | 0 | 123 | 23
01 | 01-0Q2604 | 0Q2604 | 01-MEN-101-727.0/72.7 | 20.XX 201130 |  | Ghilotti Construction Company | 246 Ghilotti Avenue | Santa Rosa Ca 95407 |  | 7074964368 | 6301 North State Street | Redwood Valley Ca 95470 | Hadipour Roozbeh | 0 | 0 | 0 | 0 | 2025-10-20 | Repair Storm Damage | Repair Storm Damage Men Cnty Near Laytonville Repair Sink And Drainage Dir'S Emergency L.B. | 74 | 12 | 473504.05 | 4430 | 3985000 | 58916 | 2025-12-30 | 2025-06-13 | 2025-04-11 |  |  | 133 | 0 | 180 | 0 |  | X
01 | 01-0P0904 | 0P0904 | 01-MEN-101-860.0/87.5 | 20.XX 201130 |  | Ghilotti Construction Company,Inc. | 246 Ghilotti Avenue | Santa Rosa, Ca 95407 |  | 7078155647 |  |  | Tisell, Steve | 0 | 0 | 0 | 0 | 2025-10-20 | Repair Slide Damage | In Mendocino County Near Cummings On Route101 From 1.7 Miles South To 0.2 Mile Southof Grizzly Creek 101/271 Seperation Dir'S Emer | 41 | 77 | 3058287.4 | 11340 | 3985000 | 55679 | 2026-04-15 | 2024-04-24 | 2024-03-10 |  |  | 82 | 0 | 201 | 0 |  | X
01 | 01-0L7404 | 0L7404 | 01-MEN-128-37.4/49.4 |  |  | Northwest Construction, Inc. | 9011 Colony Drive | Redwood Valley Ca 95470 |  | 7078341151 | 21340 Baechtel Road | Willits, Ca 95490 | Winter, Brian | 410714 | 0 | 0 | 0 | 2025-07-20 | Corrugated Steel Pipe, Structural Concrete | Mendocino County At Various Locations From0.9 Mile East Of Fish Rock Road - Road 122To 1.5 Miles West Of End Of County | 51 | 99 | 410714 | 412810 | 413554 | 56519 | 2025-08-05 | 2024-10-02 | 2024-06-25 |  |  | 18 | 0 | 35 | 0 |  | X
01 | 01-0N8104 | 0N8104 | 01-MEN-128-40.9/44.3 |  |  | Doolittle Construction Llc | 15 Business Parkway Suite 105 | Sacramento Ca 95828 |  | 7078155647 | 2617 Hwy 20 | Nice, Ca 95464 | Tisell, Steve | 23154.6 | 0 | 0 | 0 | 2025-08-20 | Replace Ac Surfacing, Slurry Seal, And Pav | Mendocino County Near Yorkville From 2.1 Miles East Of Beebe Creek Bridge To 0.8 Mile East Of Dry Creek Bridge | 95 | 98 | 758175.74 | 739000 | 739000 | 59436 | 2025-09-03 | 2025-04-21 | 2025-03-26 |  |  | 19 | 0 | 20 | 0 |  | X
01 | 01-0Q0604 | 0Q0604 | 01-MEN-128-281.0/28.1 | 20.XX 201130 |  | Pomilia Civil | P.O. Box 719 | Redwood Valley Ca 95470 |  | 7074985816 | 925 N. Franklin Street | Fort Bragg Ca 95437 | Mosallai Mojtaba | 0 | 0 | 0 | 0 | 2025-10-20 | Repair Storm Damage Men-128 | Repair Storm Damage Men Cnty In Boonville At Maint Station Stabilize Slope Between Anderson Creek Dir'S Emergency F.A. | 60 | 59 | 878264.19 | 37500 | 1485000 | 59536 | 2025-12-12 | 2025-04-30 | 2025-04-14 |  |  | 54 | 0 | 90 | 0 |  | X
01 | 01-0N6304 | 0N6304 | 01-MEN-162-2.6/4.4 |  |  | Stimpel-Wiebelhaus Associates,Inc. | 1168 Industrial Street | Redding Ca 96002 |  | 7078341151 |  |  | Winter, Brian | 250036 | 0 | 0 | 0 | 2025-10-20 | Culvert Installation And Removal. | Mendocino County At Various Locations From0.4 Miles East Of Road 8152 To 2.8 Miles West Of Bloody Run Creek Bridge 10-235 | 37 | 65 | 250036 | 386783 | 386783 | 59200 | 2025-11-17 | 2025-07-01 | 2025-06-18 |  |  | 11 | 0 | 30 | 0 |  | X
01 | 01-0A1314 | 0A1314 | 01-MEN-162-8.0/8.4 |  | ACST-P162- (043)E | Ghilotti Construction Company,Inc. | 246 Ghilotti Avenue | Santa Rosa Ca 95407 | 7075851221 | 7074964368 | 6301 North State Street | Redwood, Valley Ca 95470 | Hadipour, Roozbeh | 153953.1 | 46391.42 | 0 | 0 | 2025-10-20 | Replace Bridge. | Mendocino County About 8 Miles East Of Longvale From 0.2 Mile West To 0.1 Mile East Of Eel River Bridge | 22 | 44 | 7690699.16 | 17026070.6 | 17521495.6 | 50804 | 2027-02-05 | 2023-07-03 | 2023-06-12 |  |  | 89 | 0 | 410 | 0 |  | X
01 | 01-0B5304 | 0B5304 | 01-MEN-162-11.5/11.8 | HA23 | STER-19FF- (004)E | Mercer-Fraser Company | 200 Dinsmore Dr | Fortuna Ca 95502 | 7074436371 | 7074964368 | 6301 North State Street | Redwood Valley Ca 95470 | Roosbeh Hadipour | 0 | 58751.95 | 0 | 0 | 2025-09-20 | Stabilize Roadway | In Mendocino Near Dos Rios From 1.4 To 1.7 Miles East Of Rodeo Creek Br #10-237 | 99 | 99 | 20933289.56 | 20065914.63 | 22357173.25 | 41989 | 2025-10-31 | 2021-11-30 | 2021-11-08 |  |  | 313 | 0 | 315 | 0 |  | X
01 | 01-0P9704 | 0P9704 | 01-MEN-162-161.0/16.2 | 20XX 201130 |  | Wylatti Resource Management | Po Box 575 | Covelo Ca 95428 |  | 7074964368 | 6301 North State Street | Redwood Valley Ca 95470 | Hadipour Roozbeh | 0 | 0 | 0 | 0 | 2025-10-20 | Pavement Repairs | Repair Slipout Men Cnty Along Hwy 162 At Postmile 16.1 Retaining Wall Repairs To Roadway Dir'S Emergency F.A. | 85 | 3 | 312122.04 | 49725 | 9985000 | 58638 | 2025-11-21 | 2025-05-15 | 2025-04-21 |  |  | 127 | 0 | 150 | 0
01 | 01-0H1504 | 0H1504 | 01-MEN-162-/25.7 | HA22 | ACST-P162- (044)E | Granite Construction Company | 1324 S. State Street | Ukiah Ca 95482 |  | 7078155647 | 6301 North State Street | Redwood Valley, Ca 95470 | Tisell, Steve | 31358.37 | 375 | 305654.83 | 0 | 2025-10-20 | Hma, Rhma, And Geosynthetic Pavement Inter | Mendocino County Near Longvale From Route 101 To 1.1 Miles South Of Poonkinney Road Near Covelo | 45 | 62 | 22509343.33 | 36081257.15 | 36473534.49 | 55785 | 2025-03-05 | 2024-05-15 | 2024-03-26 |  | S | 74 | 0 | 165 | 0 |  | X
01 | 01-0N6204 | 0N6204 | 01-MEN-253-5.8/17.2 |  |  | Wylatti Resource Management, Inc. | 23601 Cemetery Lane | Covelo Ca 95428 |  | 7076849518 | 925 North Franklin Street | Fort Bragg, Ca 95437 | Chen, Peng | 463309.59 | 0 | 0 | 0 | 2025-09-20 | Install Corrugated Steel Pipe And Remove C | Mendocino County At Various Locations From1.5 Miles East Of Cattle Pass To Junction State Route 101 | 96 | 99 | 463309.59 | 470273.09 | 470273.09 | 59378 | 2025-09-22 | 2025-07-16 | 2025-06-26 | 2025-09-29 |  | 24 | 0 | 25 | 0 |  | X
01 | 01-0P3504 | 0P3504 | 01-MEN-253-130.0/13 | 20.XX 201130 |  | Rege Construction Inc. | 600 Santana Dr | Cloverdale Ca 95425 |  | 7076849518 | 925 N. Franklin Street | Fort Bragg Ca 95437 | Chen Peng | 0 | 0 | 0 | 0 | 2025-10-20 | Repair Slipout | Repair Slipout Men Cnty Near Ukiah Erosion Cntrl Mechanically Stabilized Dir'S Emergency F.A. | 52 | 73 | 1449958.51 | 9975 | 1985000 | 57475 | 2025-12-31 | 2025-03-11 | 2025-02-24 |  |  | 83 | 0 | 120 | 40 |  | X
01 | 01-0P9404 | 0P9404 | 01-MEN-271-24.0/2.5 | 20.20 201130 |  | Bud Garman Const. Services Inc | 24900 N. Hwy 101, | Willits, Ca 94590 |  | 7074985816 | 925 N. Franklin Street | Fort Bragg, Ca 95437 | Mojtaba Mosallai | 0 | 0 | 0 | 0 | 2025-10-20 | Slide Repair | In Mendocino County Near Cummings From 0.68 Mile To 0.78 Mile South Of 101/271 Separation Dir'S Emergency Fa | 100 | 66 | 978054.87 | 9975 | 1485000 | 57377 | 2025-12-31 | 2025-03-11 | 2025-02-03 |  |  | 140 | 0 | 120 | 0
01 | 01-0H1204 | 0H1204 | 01-VAR-101-84.0/85.5 | 20.20 201130 |  | Steelhead Constructions, Inc. | Po Box 997 | Palo Cedro, Ca 96073 |  | 7074851010 | 6301 North State Street | Redwood Valley, Ca 95470 | Seyoum, Kassaye | 0 | 16359.14 | 0 | 0 | 2021-04-20 | Slope Stabilization & Reconstruct Roadway | In Mendocino County On Rt 101 From Truck Passing Lane Rt To 0.4 Mile North Of End Truck Passing Lane Rt & On Rt 271 From 3.5Dir'S | 100 | 90 | 5401364.3 | 31425 | 5985000 | 37246 | 2021-05-04 | 2017-05-25 | 2017-03-31 |  |  | 963 | 0 | 75 | 0 |  | X
01 | 01-0M9104 | 0M9104 | 01-VAR--/0 |  |  | Sterndahl Enterprises Llc | 11861 Branford Street | Sun Valley Ca 91352 |  | 7078155647 | 21340 Baechtel Road | Willits, Ca 95490 | Tisell, Steve | 1323013.2 | 0 | 0 | 0 | 2025-08-20 | Thermoplastic Pavement Markings, Traffic S | Del Norte, Humboldt, Lake, And Mendocino Counties At Various Locations | 70 | 75 | 1796828.3 | 2358160 | 2358160 | 55917 | 2025-09-08 | 2024-06-11 | 2024-05-23 |  | S | 28 | 0 | 40 | 0 |  | X
01 | 01-0L9604 | 0L9604 | 01-VAR--/0 |  |  | T.P.A. Construction, Inc. | 1770 Booth Road | Roseville Ca 95747 |  | 7079945074 | Po Box 457 | Lower Lake, Ca 95457 | Seyoum, Kassaye | 397568.5 | 0 | 0 | 0 | 2025-10-20 | Polyester Concrete Overlay, Hma-A, Cold Pl | Mendocino County At Various Locations | 62 | 94 | 1934604.14 | 2157233.55 | 1979990.88 | 56212 | 2025-11-03 | 2024-05-31 | 2024-05-02 |  |  | 46 | 0 | 75 | 1 |  | X
01 | 01-0M9604 | 0M9604 | 01-VAR--/0 |  |  | Mccuen Construction, Inc. | 3269 Swetzer Road | Loomis Ca 95650 | [5 empty] | 0 | 0 | 0 | 0 |  | Polyester Concrete Overlay, Hma, & Cold Pl | Mendocino County At Various Locations | 0 | 0 | 0 | 1043788.7 | 1043788.7 | 59797 |  | 2025-07-14 | 2025-06-23 |  |  | 0 | 0 | 60 | 0
01 | 01-0N8804 | 0N8804 | 01-VAR--/0 | 20.20 201130 |  | Gr Sundberg, Inc. | 5521 Boyd Road | Arcata, Ca 95521 |  | 7073469027 | 5065 Boyd Road, Suite H | Arcata, Ca 95521 | Dunne, Ryan | 15975 | 0 | 0 | 0 | 2025-06-06 | Emergency Slide Repair | Major Items Of Work Include Traffic Control, Remove Slide Debris, Erosion Control And Additional Items Dir'S Emergency F.A. | 100 | 100 | 1570609.23 | 15975 | 2485000 | 54805 | 2025-06-06 | 2024-01-18 | 2023-12-05 | 2025-10-01 |  | 64 | 0 | 185 | 0 |  | X
02 | 02-1J75U4 | 1J75U4 | 02-LAS-36-14.4/16.8 |  | HSNH-S036- (121)E | Hat Creek Construction & Materials, Inc. | 24339 State Hwy 89 N. | Burney Ca 96013 | 5303405464 | 5307593733 | 471-800 Diane Drive | Susanville Ca 96130 | Gibbs Daniel | 597092.8 | 0 | 0 | 0 | 2025-10-20 | Place Hma And Class 2 Ab, Excavate Roadway | Lassen County About 9 Miles West Of Susanville From 1.3 Miles West To 1.2 Miles East Of Willard Creek Road | 43 | 37 | 5107129.6 | 13839809 | 13839809 | 57134 | 2025-01-22 | 2025-02-13 | 2025-01-23 |  | S | 52 | 0 | 120 | 0 |  | X
02 | 02-2K5404 | 2K5404 | 02-LAS-36-100.0/14 | 20.XX 201130 |  | Tullis Inc | Po Box 493416 | Redding Ca 96049 |  | 5303405464 | 471-800 Diane Drive | Johnstonville Ca 96130 | Gibbs Daniel | 0 | 0 | 0 | 0 | 2025-10-20 | Pavement Repairs | Bad Fred Do N Lassen Cnty About 7 Miles East Westwood Traffic Cntrl Place Hma Leveling Courses Dir'S Emergency L.B. | 66 | 52 | 6365675.84 | 21491 | 12261000 | 57257 | 2029-02-06 | 2025-03-19 | 2025-01-31 |  |  | 241 | 0 | 365 | 0 |  | X
02 | 02-4H0604 | 4H0604 | 02-LAS-36-/6.1 |  | ACNH-S036- (120)E | Hat Creek Construction & Materials, Inc. | 24339 State Hwy 89 N. | Burney Ca 96013 | 5303355501 | 5307593733 | 471-800 Diane Lane | Susanville Ca 96130 | Gibbs Daniel | 3720269.31 | 56572.28 | 0 | 0 | 2025-10-20 | Roadway Exc. Class 2 Aggregate Base, Hma, | Lassen And Plumas Counties From Melissa Avenue To 0.6 Mile East Of Red River Canal | 66 | 80 | 32649791.01 | 38245254 | 40473145.43 | 56746 | 2026-01-14 | 2024-12-03 | 2024-11-05 |  |  | 113 | 0 | 170 | 0 |  | X
02 | 02-4H0704 | 4H0704 | 02-LAS-139-.7/11 |  | ACST-S139- (025)E | Hat Creek Construction & Materials, Inc. | 24339 State Hwy 89 N. | Burney Ca 96013 | 5303355501 | 5307593733 | 471-800 Diane Drive | Susanville Ca 96130 | Gibbs Daniel | 1307259.86 | 0 | 0 | 0 | 2025-10-20 | Place Hma (Type A), Traffic Control System | Lassen County Near Susanville From 0.1 Mile North Of Chestnut Street To 2.6 Milessouth Of Horse Lake Road | 90 | 92 | 13081980.88 | 13850085 | 14005559.02 | 57133 | 2025-11-07 | 2025-02-13 | 2025-01-29 |  |  | 131 | 0 | 145 | 0 |  | X
02 | 02-1K0704 | 1K0704 | 02-LAS-139-11.0/16 |  |  | S.T. Rhoades Construction, Inc. | 8780 Old Oregon Trail | Redding Ca 96002 | 5302239322 | 5307593733 | 471-800 Diane Drive | Susanville Ca 96130 | Gibbs Daniel | 1971054.61 | 0 | 0 | 0 | 2025-10-20 | Perform Partial Depth Recycling And Place | Lassen County About 9 Miles North Of Susanville From 1.2 Miles South Of Hagata Road To 0.9 Mile South Of Meadow Channel Bridge | 83 | 89 | 2370698.76 | 2642736 | 2641501.67 | 59817 | 2025-11-03 | 2025-05-09 | 2025-04-09 |  |  | 25 | 0 | 30 | 0 |  | X
02 | 02-1K0904 | 1K0904 | 02-MOD-139-28.0/34 |  |  | American Pavement Systems, Inc. | 1012 11 Street Suite 1000 | Modesto Ca 95354 | 2092028779 | 5303560630 | 1625 Mott Road | Mount Shasta Ca 96067 | Henry Austin | 1089716.9 | 0 | 0 | 0 | 2025-09-20 | Place Asphalt Rubber Chip Seal And Replace | Modoc County Near Perez From 0.1 Mile North To 6.1 Miles North Of Tionesta Road | 90 | 95 | 1089716.9 | 1133698 | 1133698 | 59755 | 2025-09-16 | 2025-06-26 | 2025-05-29 | 2025-10-01 |  | 18 | 0 | 20 | 0 |  | X
02 | 02-1K0804 | 1K0804 | 02-MOD-395-/5 |  |  | Hat Creek Construction & Materials, Inc. | 24339 State Hwy 89 N. | Burney Ca 96013 | 5303555501 | 5303569242 | 13700 Highway 36 East | Red Bluff Ca 96080 | Higgins Kyle | 1821695.1 | 0 | 0 | 0 | 2025-10-20 | Place Hma Overlay And Replace Asphalt Conc | Modoc County Near Likely From Lassen County Line To 0.8 Mile North Of County Road 189 | 84 | 93 | 2029241.2 | 2121989 | 2174353.16 | 59818 | 2025-10-20 | 2025-06-17 | 2025-05-30 |  |  | 21 | 0 | 25 | 0 |  | X
02 | 02-0K6104 | 0K6104 | 02-PLU-70-32.9/33.2 |  |  | Studebaker Electric, Inc. | 3237 Rippey Road, Ste 100 | Loomis Ca 95650 | [5 empty] | 0 | 0 | 0 | 0 |  | Modify Highway Advisory Radio System And C | Plumas County Near Paxton From 0.1 Mile West To 0.2 Mile East Of North Junction Route 89 | 0 | 0 | 0 | 825625.5 | 825625.5 | 59155 |  | 2025-06-26 | 2025-06-18 |  |  | 0 | 0 | 45 | 0
02 | 02-1H58U4 | 1H58U4 | 02-PLU-70-58.2/78.4 |  | ACNH-P070- (146)E | Mercer Fraser Company | 200 Dinsmore Dr | Fortuna Ca 95540 | 5303567818 | 5303567818 | 546 Lawrence St | Quincy Ca 95971 | Zdenek Mike | 3926878.37 | 0 | 0 | 0 | 2025-10-20 | Reconstruct Roadway, Hma Paving, Drainage | Plumas County At And Near Cromberg From Gill Ranch Road To 0.2 Mile West Of Big Grizzly Creek Bridge | 46 | 47 | 45386192.1 | 85593593 | 94948898.2 | 52264 | 2026-04-09 | 2023-08-18 | 2023-06-27 |  |  | 166 | 0 | 360 | 0 |  | X
02 | 02-4H0104 | 4H0104 | 02-PLU-70-78.3/90.3 |  | ACST-P070- (149)E | Hat Creek Construction & Materials, Inc. | 24339 State Hwy 89 N. | Burney Ca 96013 | 5302387553 | 5303567818 | 546 Lawrence St | Quincy Ca 95971 | Zdenek Mike | 451607.99 | 2004100.55 | 1250 | 0 | 2025-10-20 | Replace Ac Surfacing, Place Hma And Thermo | Plumas County Near Portola From 0.4 Mile West Of Big Grizzly Creek Bridge To 0.8 Mile West Of Summit School Drive | 25 | 37 | 8318773.68 | 15696969 | 22548394.28 | 58896 | 2026-06-11 | 2025-02-18 | 2025-01-29 |  |  | 67 | 0 | 150 | 120 |  | X
02 | 02-4H03U4 | 4H03U4 | 02-PLU-89-12.9/20 |  | TBGP-S089- (033)E | Hat Creek Construction & Materials, Inc. | 24339 State Hwy 89 N. | Burney Ca 96013 | 5309628402 | 5307593778 | 2707 Notre Dame Blvd | Chico Ca 95928 | Farley Damion | 749629.19 | 111258.9 | 15000 | 0 | 2025-10-20 | Hma Overlay. | Plumas County In And Near Greenville From 0.8 Mile South Of Dixie Canyon Road To Wolf Creek Bridge And From Mill Street To 0.4 Mil | 87 | 96 | 13904212.48 | 13389389 | 14434631.38 | 57123 | 2025-11-13 | 2025-01-14 | 2024-12-20 |  |  | 118 | 0 | 130 | 6 |  | X
02 | 02-3H6904 | 3H6904 | 02-PLU-89-30.2/42.2 |  | TBGP-S089- (034)E | Dig It Construction, Inc. | 803 Lorraine Drive | Chester Ca 96020 | 5303355501 | 5309452437 | 1253 Lorraine Dr | Redding Ca 96001 | Mendoza Sergio | 3779142.79 | 9396.77 | 0 | 0 | 2025-10-20 | Place Hma, Full Depth Recycling-Foamed Asp | Plumas County Near Canyon Dam From 0.1 Mile North Of Lake Almanor Spillway To Route 36 | 56 | 54 | 19257814.06 | 34450290.72 | 35345863.25 | 57124 | 2026-02-04 | 2025-01-14 | 2024-11-21 |  |  | 90 | 0 | 160 | 0 |  | X
02 | 02-0K7804 | 0K7804 | 02-PLU-89-200.0/20.6 | 20.20 201130 |  | Darren Taylor Construction Inc | 19672 N. Hirch Ct. | Anderson, Ca 96007 |  | 5303569242 | 13700 Highway 36 East | Red Bluff Ca. 96080 | Higgins Kyle | 0 | 0 | 0 | 0 |  | Greenville Paving | Remove And Replace Ac Surface, Fix Stripesplumas County Near Wolf Creek Remove And Replace With 0.1 Grind &Overlaydir'S Emergency | 0 | 0 | 0 | 5820 | 373000 | 52024 |  | 2023-07-25 | 2023-07-06 |  |  | 0 | 0 | 20 | 0
02 | 02-4H1504 | 4H1504 | 02-SHA-5-4.9/5.1 | 20.20 201130 |  | J.F. Shea Construction, Inc. | P. O. Box 494519 | Redding, Ca 96049 |  | 5306045102 | 1031 Butte Street | Redding, Ca 96001 | Alexander, Nathan | 1265 | 139575.92 | 0 | 0 | 2018-01-13 | Remove 1.8 Feet Of Embankment Under Bridge | In Shasta County In Anderson From Anderson Creek Overflow To 0.1 Mile North Of Anderson Creek Bridge. Dir'S Emergency L.B. | 100 | 52 | 140840.92 | 1265 | 270000 | 39084 | 2018-01-13 | 2018-03-07 | 2017-12-06 |  |  | 38 | 0 | 20 | 0
02 | 02-1J8904 | 1J8904 | 02-SHA-5-30.5/31 |  |  | Mccuen Construction, Inc. | 3269 Swetzer Road | Loomis Ca 95650 | 9166527824 | 5303569242 | 13700 Hwy 36 East | Red Bluff Ca 96080 | Higgins Kyle | 599475.25 | 0 | 0 | 0 | 2025-10-20 | Replace Pavement And Place Polyester Concr | Shasta County Near O'Brien From 0.1 Mile South Of Tunnel Gulch Viaduct To The O'Brien Rest Area | 76 | 52 | 1427196.53 | 2739586.99 | 2739586.99 | 59517 | 2025-11-06 | 2025-07-23 | 2025-07-02 |  |  | 42 | 0 | 55 | 0
02 | 02-1K0504 | 1K0504 | 02-SHA-44-.4/L1.8 |  |  | J.F. Shea Construction, Inc. | 17400 Clear Creek Road | Redding Ca 96001 | 5302464292 | 5306045102 | 1031 Butte St | Redding Ca 96001 | Alexander Nathan | 1801494 | 0 | 0 | 0 | 2025-08-20 | Cold Plane Ac Pvmt And Rhma (Gap Graded). | Shasta County In Redding From Continental Undercrossing No. 06-0135L To Route 5/44 Separation | 57 | 98 | 1801494 | 1668346 | 1668346 | 59816 | 2025-09-11 | 2025-06-03 | 2025-05-15 |  |  | 17 | 0 | 30 | 0 |  | X
02 | 02-4H0504 | 4H0504 | 02-SHA-273-18.5/18.7 |  | ACNH-X089- (124)E | Tullis, Inc. | 16951 Clear Creek Road | Redding Ca 96001 | 5302415105 | 5306045102 | 1031 Butte St, Suite 205 | Redding, Ca 96001 | Alexander, Nathan | 0 | 357190.57 | 0 | 0 | 2025-10-20 | Place Rhma, Hma, Minor Concrete, And Repla | Shasta County In And Near Redding On Route273 From 0.5 Mile North Of Sulphur Creek Bridge To 0.2 Mile South Of Twin View Boulevard | 100 | 89 | 28492798.96 | 28458713 | 31489963.57 | 54945 | 2025-12-03 | 2023-12-13 | 2023-11-16 |  |  | 100 | 0 | 100 | 0 |  | X
02 | 02-1K1904 | 1K1904 | 02-SHA-299-20.4/21.5 |  |  | Specialized Pavement Marking, Llc | 11095 Sw Industrial Way Suite | Tualatin Or 97062 | 5303654000 | 5303569242 | 13700 Hwy 36 East | Red Bluff Ca 96080 | Higgins Kyle | 59945 | 0 | 0 | 0 | 2025-10-08 | Install Shoulder And Center-Line Rumble St | Shasta County In And Near Redding From 0.1Mile East Of Iron Mountain Road To 0.4 Mile East Of Lower Springs Road | 100 | 100 | 59945 | 64350 | 60150 | 59518 | 2025-10-08 | 2025-07-23 | 2025-05-28 | 2025-10-23 |  | 1 | 0 | 10 | 0 |  | X
02 | 02-1K4004 | 1K4004 | 02-SIS-0-/0 | 20.10 201352 |  | Robert J Frank Construction | 2806 Tarmac Rd | Redding Ca 96003 |  | 5303569242 | 13700 Highway 36 East | Red Bluff Ca 96080 | Higgins Kyle | 0 | 0 | 0 | 0 | 2025-09-20 | Pavement Repairs | Security Measures At Maintenance Stations22 Maintenance Stations In District 2 Scope Of Work Includes Install Of Fencing Dir'S Eme | 88 | 41 | 1128064.15 | 17475 | 2785000 | 57073 | 2026-05-24 | 2025-02-25 | 2024-06-19 |  |  | 159 | 0 | 180 | 0
02 | 02-1H7104 | 1H7104 | 02-SIS-3-47.4/0 |  |  | Mccuen Construction, Inc. | 3269 Swetzer Road | Loomis Ca 95650 | 9166527824 | 5306055861 | 1745 S Main Street | Yreka Ca 96097 | Henry Austin | 500702.52 | 0 | 0 | 0 | 2025-10-20 | New Mechanic Shop At Yreka Maintenance Sta | Siskiyou County In Yreka On Route 3 At Yreka Maintenance Station And On Route 5 From 0.2 Mile South To 0.4 Mile North Of South Yre | 50 | 35 | 1942373.59 | 5477278.5 | 5477278.5 | 56747 | 2026-03-19 | 2024-12-04 | 2024-11-13 |  |  | 100 | 0 | 200 | 0 |  | X
02 | 02-3H32U4 | 3H32U4 | 02-SIS-5-2.5/15.9 |  | ACNH-0059- (181)E | Walsh-Myers Joint Venture | 929 W Adams Street | Chicago Il 60607 | 3125635452 | 5306055861 | 1625 Mott Rd | Mt Shasta 96067 | Henry Austin | 294807.74 | 9934.48 | 324167.3 | 0 | 2025-10-20 | Pavement Rehabilitation And Deck Replaceme | Siskiyou County At And Near Dunsmuir From Central Dunsmuir Undercrossing To Black Butte Overhead | 100 | 98 | 151032688.95 | 140630444.1 | 150941900.15 | 50984 | 2025-10-21 | 2023-06-06 | 2023-04-28 |  |  | 521 | 0 | 520 | 2 |  | X
02 | 02-0J8504 | 0J8504 | 02-SIS-89-20.3/34.6 |  | ACNH-P089- (126)000 | Tullis, Inc. | 16951 Clear Creek Road | Redding Ca 96001 | [5 empty] | 0 | 0 | 0 | 0 |  | Hma, Culverts, Guardrail, Fencing | Siskiyou County At And Near Mccloud From 0.8 Mile South Of Mud Creek Bridge To Route 5 | 0 | 0 | 0 | 16381305 | 16381305 | 60036 |  | 2025-08-26 | 2025-08-05 |  |  | 0 | 0 | 120 | 0
02 | 02-1H5904 | 1H5904 | 02-SIS-96-43.5/58 |  | ACNH-P096- (064)E | J.F. Shea Construction, Inc. | 17400 Clear Creek Road | Redding Ca 96001 | 5302464292 | 5309497994 | 1625 Mott Road | Mount Shasta Ca 96067 | Riddle Nicholas | 37143.5 | 34295.65 | -2120.76 | 0 | 2025-10-20 | Replace Culverts With Bridges, Streambed R | Siskiyou County At And Near Happy Camp At 0.8 Mile West Of Gordon'S Ferry Road And At Portuguese Creek | 95 | 84 | 9697374.41 | 11040419 | 11499178.24 | 52265 | 2025-11-12 | 2023-08-30 | 2023-08-07 |  |  | 304 | 0 | 320 | 0 |  | X
02 | 02-1H3604 | 1H3604 | 02-SIS-96-76.8/78 |  |  | Myers & Sons Construction, Llc | 45 Morrison Ave | Sacramento Ca 95838 | 9162839950 | 5309497994 | 1625 Mott Rd | Mount Shasta Ca 96067 | Riddle Nicholas | 148572.2 | 0 | 0 | 0 | 2025-10-20 | Replace Bridge. | Siskiyou County Near Horse Creek From 0.4 Mile West Of Klamath River Bridge To 2.1 Miles West Of Kohl Creek | 100 | 98 | 33339743.66 | 32429250 | 32788992.46 | 55771 | 2025-10-31 | 2024-05-10 | 2024-03-22 |  | S | 254 | 0 | 320 | 0 |  | X
02 | 02-0K6404 | 0K6404 | 02-SIS-97-18.0/22.4 |  | ACNH-P097- (045)E | Mccuen Construction, Inc. | 1326 Swetzer Road | Loomis Ca 95650 | 9166527824 | 5306055861 | 1625 Mott Road | Mount Shasta Ca 96067 | Henry Austin | 1797341.79 | 77862.03 | 0 | 0 | 2025-10-20 | Construct Wildlife Overpass, Install Culve | Siskiyou County Near Grass Lake From 1.4 Miles North Of Deer Mountain Road To 0.6 Mile North Of Grass Lake Rest Area | 87 | 85 | 12037495.74 | 13293018.19 | 14127393.19 | 57122 | 2025-11-17 | 2025-01-21 | 2024-12-31 |  |  | 130 | 0 | 120 | 29 |  | X
02 | 02-1K1004 | 1K1004 | 02-SIS-97-29.0/34.5 |  |  | Vss International, Inc. | 3785 Channel Drive | West Sacramento Ca 95691 | 9163731500 | 5306055861 | 1625 Mott Road | Mount Shasta Ca 96067 | Henry Austin | 388926.83 | 0 | 0 | 0 | 2025-09-26 | Place Ar Chip Seal And Slurry Seal. | Siskiyou County About 11 Miles South Of Macdoel From 1.2 Miles North Of Tennant Road To 1.7 Miles South Of Ball Mountain Road | 100 | 100 | 1612693.13 | 1686325 | 1686325 | 58518 | 2025-09-26 | 2025-06-04 | 2025-05-23 | 2025-10-24 |  | 19 | 0 | 20 | 0 |  | X
02 | 02-4H0004 | 4H0004 | 02-SIS-97-45.0/54.1 |  | ACNH-X089- (011)E | Rocky Mountain Construction | 4815 Tingley Lane #A | Klamath Falls Or 97603 | 5418828377 | 5306055861 | 1745 S Main St | Yreka Ca 96097 | Henry Austin | 239188.9 | 37322.03 | 0 | 0 | 2025-08-20 | Hot Mix Asphalt, Pavement Delineation, & E | Siskiyou County In And Near Dorris On Route 97 From 0.3 Mile South Of Sams Neck Road To Oregon State Line And On Route 161From Rou | 100 | 95 | 10896114.64 | 10995880.46 | 11236559.7 | 56151 | 2025-08-25 | 2024-05-22 | 2024-02-23 |  |  | 64 | 0 | 60 | 0 |  | X
02 | 02-0K0104 | 0K0104 | 02-TEH-5-5.6/42 |  |  | Central Striping Service, Inc. | 3489 Luyung Drive | Rancho Cordova Ca 95742 | 9166355175 | 5303569242 | 13700 Highway 36 East | Red Bluff Ca 96080 | Higgins Kyle | 62618.71 | 0 | 0 | 0 | 2025-09-20 | Roadside Sign - One Post, Thermoplastic St | Tehama County Near Corning At Various Locations From 0.2 Mile South Of Liberal Avenue Overcrossing To Cottonwood Creek Bridge Over | 100 | 94 | 639843.88 | 672170.77 | 684670.77 | 57008 | 2025-10-24 | 2024-08-30 | 2024-06-17 |  |  | 30 | 0 | 30 | 0 |  | X
02 | 02-1K9004 | 1K9004 | 02-TEH-36-618.0/.2 | 20XX 202130 |  | Jf Shea Construction Inc | Po Box 494519 | Redding Ca 96049 |  | 5307593778 | 2707 Notre Dame Blvd | Chico Ca 95926 | Farley Damion | 0 | 0 | 0 | 0 | 2025-09-20 | Pavement Repairs | D2 Park Fire Do Plu Sha Teh Butte Cntys Var Locations Traffic Contrl Remove Trees Replace Culverdir'S Emergency L.B. | 100 | 75 | 17624615.97 | 4000 | 23620000 | 56322 | 2025-11-02 | 2024-09-10 | 2024-07-30 |  |  | 404 | 0 | 35 | 207
02 | 02-0J0104 | 0J0104 | 02-TEH-99-4.2/4.8 |  | HSNH-P099- (685)E | Baldwin Contracting Company Inc. Dba Knife River Construction | 1764 Skyway | Chico Ca 95928 | 5308916555 | 5306045118 | 2600 Gateway Dr | Anderson Ca 96007 | Worden Edward | 224739.05 | 31426.93 | 0 | 0 | 2025-10-20 | Place Hma, Cctv Tower And Install Lighting | Tehama County About 7.0 Miles South Of Losmolinos From 0.3 Mile South Of South Avenue To 0.6 Mile South Of Vina Road | 78 | 85 | 8731479.8 | 9805715.5 | 10182843.2 | 56661 | 2025-12-08 | 2024-08-07 | 2024-07-11 |  |  | 117 | 0 | 150 | 0 |  | X
02 | 02-3H70U4 | 3H70U4 | 02-TRI-299-15.0/25.7 |  | ACNH-P299- (217)E | J.F. Shea Construction, Inc. | 17400 Clear Creek Road | Redding Ca 96001 | 5302464292 | 5306045118 | 1031 Butte Street | Redding Ca 96001 | Worden Edward | 682528 | 26088.23 | 0 | 0 | 2025-10-20 | Rhma-G, Hma (Type A), Cold Plane Ac, & Sol | Trinity County Near Del Loma From 1.0 Mileeast Of Trinity River Bridge No.05-0006 To0.1 Mile West Of Prairie Creek Road | 67 | 79 | 13895842.49 | 17226140 | 17452890.44 | 56312 | 2026-01-12 | 2024-09-03 | 2024-08-09 |  |  | 114 | 0 | 170 | 0 |  | X
02 | 02-2K7504 | 2K7504 | 02-TRI-299-286.0/28.6 | 20.XX 201130 |  | Tullis Inc | Po Box 493416 | Redding Ca 96049 |  | 5306045102 | 1031 Butte St First Floor | Redding Ca 96001 | Alexander Nathan | 0 | 0 | 0 | 0 | 2025-09-20 | Corral Bottom Disposal Site Slide Repair | Coral Bottom Disposal Site Slide Repair In Tri Cnty At Big Par Corral Bottom Rd Excavation And Removal Of Failed Slide Dir'S Emerg | 41 | 31 | 1782338.68 | 27938 | 5742000 | 59696 | 2025-12-31 | 2025-08-11 | 2025-07-15 |  |  | 39 | 0 | 95 | 0 |  | X
02 | 02-2K1104 | 2K1104 | 02-VAR--/0 | 20.XX 201130 |  | Jf Shea Construction Inc | 17400 Clear Creek Road | Redding Ca 96001 |  | 5306045102 | 1031 Butte St Suite 205 Ms 60 | Redding Ca 96001 | Alexander Nathan | 0 | 0 | 0 | 0 | 2025-10-20 | Pavement Repairs | Cottonwood Creek Bridge Joint Replacement Var Cnty Near Cottonwood Creek Overhead Remove Replace Expansion Joints Dir'S Emergency | 4 | 9 | 155735.83 | 7136 | 1769000 | 57074 | 2025-12-31 | 2024-12-05 | 2024-10-21 |  |  | 4 | 0 | 112 | 0 |  | X
02 | 02-2J2204 | 2J2204 | 02-VAR--/0 |  | SNHG-000C- (567)E | Highway Specialty Company, Inc. | 6591 Eastside Road | Redding Ca 96001 | 5309495637 | 5303569242 | 13700 Hwy 36 East | Red Bluff Ca 96080 | Higgins Kyle | 409313.53 | 0 | 0 | 10000 | 2025-10-20 | Install Curve Warning Roadside Signs. | Butte, Lassen, Modoc, Plumas, Shasta, Siskiyou, Tehama And Trinity Counties At Various Locations | 12 | 36 | 533788.53 | 1488552 | 1488552 | 59237 | 2026-06-01 | 2025-07-03 | 2025-06-23 |  |  | 20 | 0 | 170 | 0 |  | X
02 | 02-0K6004 | 0K6004 | 02-VAR--/0 |  |  | Teichert Energy & Utilities Group, Inc. | 3500 American River Drive | Sacramento Ca 95864 | 9164388500 | 5306826584 | 703 B St | Marysville Ca 95901 | Granados Anthony | 0 | 0 | 0 | 0 | 2025-05-20 | Construct Middle Mile Broadband Network | Humboldt, Mendocino, Lake, Trinity, Siskiyou, Modoc, Tehama, Shasta, Lassen, Plumas, Butte, Glenn, Sierra, Colusa, Nevada, Placer, | 0 | 75 | 67674.99 | 200 | 90000 | 54404 | 2026-12-31 | 2023-08-09 | 2023-08-09 |  |  | 0 | 0 | 1 | 0 |  | X
02 | 02-2K2704 | 2K2704 | 02-VAR--/0 | 20.XX 201130 |  | Mercer-Fraser Company | Po Box 1006 | Eureka Ca 95502 |  | 5303567818 | 546 Lawrence Street | Quincy Ca 95971 | Zdenek Mike | 0 | 0 | 0 | 0 | 2025-03-20 | Pavement Repairs | Nov 24 Sr 70 Slides In Butte And Pluma Cntys From Jarbo Gap Traffic Cntrl, Clear Slide Material Dir'S Emergency F.A. | 82 | 93 | 1416850.4 | 5940 | 1525000 | 56806 | 2025-04-01 | 2025-01-06 | 2024-11-23 |  |  | 36 | 0 | 30 | 14 |  | X
02 | 02-3J3304 | 3J3304 | 02-VAR--/0 |  |  | Mccuen Construction, Inc. | 3269 Swetzer Road | Loomis Ca 95650 | 9166527824 | 5306045102 | 1031 Butte St 205 Ms 60 | Redding Ca 96001 | Alexander Nathan | 60070.04 | 0 | 0 | 0 | 2025-10-20 | Furnish And Place Polyester Concrete Overl | Shasta And Tehama Counties At Various Locations | 73 | 14 | 390126.79 | 2837770.9 | 2837770.9 | 58517 | 2025-11-20 | 2025-06-04 | 2025-05-13 |  |  | 40 | 0 | 55 | 0 |  | X
02 | 02-1K1804 | 1K1804 | 02-VAR--/0 |  |  | Roll'N Rock Construction, Inc. | 5527 Truck Village Dr. | Mount Shasta Ca 96067 | 5309253444 | 5303560630 | 1625 Mott Road | Mount Shasta Ca 96067 | Riddle Nicholas | 1001762.25 | 0 | 0 | 0 | 2025-10-20 | Roadside Signs And Pavement Delineation. | Siskiyou County Near Dunsmuir At Various Locations From 0.1 Mile South Of Southbound Dunsmuir Undercrossing To 0.1 Mile North Of H | 43 | 95 | 1041774.75 | 1080590.5 | 1112590.5 | 59819 | 2025-11-13 | 2025-06-25 | 2025-05-20 |  |  | 17 | 0 | 40 | 0 |  | X
02 | 02-2J9704 | 2J9704 | 02-VAR--/0 |  |  | Mccuen Construction, Inc. 13700 Hwy 36 Red Bluff Ca 96080 | 3269 Swetzer Road | Loomis Ca 95650 |  | 5303569242 |  |  | Kyle Higgins | 807584.29 | 0 | 0 | 293550 | 2025-10-20 | Bridge Polyester Concrete Overlay And Meth | Shasta County On Route 5 At Various Locations From Antler Undercrossing To Soda Creek Road Undercrossing And On Route89 At Various | 14 | 35 | 1114954.29 | 3143311.34 | 3143311.34 | 59815 | 2026-02-11 | 2025-03-13 | 2025-02-26 |  |  | 19 | 0 | 138 | 0 |  | X
02 | 02-3J3204 | 3J3204 | 02-VAR--/0 |  |  | Q&D Construction Llc | 1050 S. 21St Street | Sparks Nv 89431 | 7757862677 | 5307516116 | 2660 Gateway Dr | Anderson Ca 96007 | Worden Edward | 132698.54 | 0 | 0 | 0 | 2025-10-20 | Bridge Polyester Concrete Overlay & Methac | Trinity County At Various Locations | 95 | 95 | 5240314.04 | 4912269 | 5474563.26 | 55975 | 2025-11-05 | 2024-06-20 | 2024-06-06 |  |  | 90 | 0 | 95 | 0 |  | X
03 | 03-4H76U4 | 4H76U4 | 03-BUT-32-5.0/10.2 |  | HSNH-P032- (051)E | Baldwin Contracting Company Inc. Dba Knife River Construction | 1764 Skyway | Chino Ca 95928 |  |  | 2707 Notre Dame Blvd | Chico, Ca 95928 | Rechs, Daniel | 3143152.85 | 0 | 0 | 145000 | 2025-10-20 | Rehabilitate Pavement, Install Signal, Lig | Butte County In Chico From Muir Avenue To Interchange Of State Routes 99 And 32 | 33 | 65 | 21070523.84 | 30772086 | 32032645.07 | 56089 | 2026-04-16 | 2024-07-10 | 2024-06-17 |  |  | 83 | 0 | 250 | 0 |  | X
03 | 03-3G3804 | 3G3804 | 03-BUT-32-23.9/30.8 |  |  | Lamon Construction Co., Inc. | 871 Von Geldern Way | Yuba City Ca 95991 |  | 5307137814 | 2707 Notre Dame Blvd | Chico, Ca 95928 | Grandy, Dwayne | 762590.51 | 0 | 0 | 0 | 2025-10-20 | Hma Overlay, Cold Plane, And Remove & Repl | Butte County Near Chico From Nopel Avenue To 1.3 Miles West Of Carpenter Ridge Road And From 1.1 Miles West Of Carpenter Ridgeroad | 93 | 85 | 3512986.3 | 3839193.95 | 3839193.95 | 58617 | 2025-09-30 | 2025-06-09 | 2025-05-27 |  |  | 42 | 0 | 45 | 0 |  | X
03 | 03-3G0704 | 3G0704 | 03-BUT-32-31.5/37.8 |  |  | Lamon Construction Co., Inc. | 871 Von Geldern Way | Yuba City Ca 95991 | 5303926008 | 5306737814 | 2707 Notre Dame Blvd | Chico, Ca 95928 | Dwayne Grandy | 229125.41 | 0 | 0 | 0 | 2025-07-20 | Cold Plane And Place Hma. | Butte County From 1.6 Miles North Of 120G/Platt Mountain Road To Tehama County Line | 67 | 96 | 1876601.94 | 1951572.9 | 1951572.9 | 58716 | 2025-08-08 | 2024-07-17 | 2024-06-25 |  |  | 30 | 0 | 45 | 0 |  | X
03 | 03-1N4404 | 1N4404 | 03-BUT-32-174.0/37.7 | 20.XX 201130 |  | Lamon Construction Company | 871 Von Geldern Way | Yuba City, Ca 95991 |  | 5302181567 | 2707 Notre Dame Blvd | Chico, Ca 95928 | Rechs, Dan | 0 | 0 | 0 | 0 | 2025-07-20 | Park Fire | Hazardous Tree/Debris Removal Pavement Repair, Replace Damaged R/W Fencing/Guardrail And Signs Dir'S Emergency F.A. | 82 | 91 | 3656309.05 | 6975 | 3921489.96 | 56681 | 2025-08-27 | 2024-10-08 | 2024-08-16 |  |  | 123 | 0 | 150 | 0 |  | X
03 | 03-1N5504 | 1N5504 | 03-BUT-70-350.0/36 | 20.XX 201130 |  | Steelhead Constructors Jv | P.O. Box 536 | Palo Cedro, Ca 96073 |  | 5309540879 | 2707 Notre Dame Blvd | Chico, Ca 95928 | Makhoul, Husam | 0 | 0 | 0 | 0 | 2025-10-20 | But 70 Viaduct | Mobilization, Excavation, Backfill, Haul Away Slide Material, Construct Viaduct/Structure Type Selection Dir'S Emergency L.B. | 62 | 53 | 3723403.68 | 35663 | 7000000 | 57897 | 2026-02-06 | 2025-03-03 | 2025-02-03 |  |  | 123 | 0 | 200 | 0 |  | X
03 | 03-2N0104 | 2N0104 | 03-BUT-70-364.0/42.3 | 20.XX 201130 |  | Baldwin Contracting Co., Dba Knife River Construction | 1764 Skyway | Chico, Ca 95928 |  | 5307137814 | 2707 Notre Dame Blvd | Chico, Ca 95928 | Grandy, Dwayne | 0 | 0 | 0 | 0 | 2025-07-20 | But 70 Slip Outs | In Butte County Along State Route 70 Approximately 0.1 Miles East Of Grandview Station Rt To Approximately 0.3 Miles Eastdir'S Eme | 11 | 21 | 526867.35 | 4029 | 2485000 | 58535 | 2025-05-30 | 2025-05-13 | 2025-04-29 |  |  | 13 | 0 | 120 | 0 |  | X
03 | 03-1H1404 | 1H1404 | 03-BUT-99-3.1/5 |  | ACNH-P099- (690)E | Martin Brothers Construction | 8801 Folsom Boulevard Ste 260 | Sacramento Ca 95826 |  | 5303206457 | 2704 Notre Dame Blvd | Chico, Ca 95928 | Watts, Dustin | 528186.35 | 36555.35 | 0 | 0 | 2025-10-20 | Rhma, Hma, Lighting Systems, Curb Ramps, S | Butte County In And Near Gridley From Hollis Lane To 0.2 Mile North Of Ford Avenue | 14 | 42 | 7804843.19 | 18182285 | 18591805.65 | 57125 | 2027-01-27 | 2025-02-10 | 2025-01-08 |  |  | 50 | 0 | 365 | 0 |  | X
03 | 03-4J2104 | 4J2104 | 03-COL-5-30.0/10 | 20.20 201130 |  | Vintage Paving Company, Inc | 119 Main Street | Winters, Ca 95694 |  | 5306823842 | 379 Colusa Ave. | Yuba City, Ca 95991 | Griffith, Garrett | 0 | 0 | 0 | 0 | 2024-07-20 | Col 5 Pavement | An Emergency Project To Repair Failed Pavement Director'S Emergency F.A. | 42 | 90 | 1343214.16 | 9600 | 1500000 | 52725 | 2024-10-01 | 2023-09-22 | 2023-03-03 |  |  | 25 | 0 | 60 | 0 |  | X
03 | 03-3G5304 | 3G5304 | 03-ED-49-16.5/20.1 |  |  | Martin Brothers Construction | 8801 Folsom Boulevard Ste 260 | Sacramento Ca 95826 |  | 5305653834 | 3461 Robin Ln. Suite #4 | Cameron Park, Ca 95682 | Thompson, Brian | 350898.4 | 0 | 0 | 0 | 2025-10-20 | Install Cured-In-Place Pipeliners And Repl | El Dorado County Near Placerville At Various Locations From 0.2 Mile North Of Diana Street To 0.5 Mile North Of Woodridge Road | 47 | 63 | 481403.5 | 759881.57 | 759881.57 | 59826 | 2025-12-31 | 2025-07-14 | 2025-06-06 |  |  | 21 | 0 | 45 | 0 |  | X
03 | 03-3G5204 | 3G5204 | 03-ED-49-23.6/25.2 |  |  | Lamassu Utility Services, Inc. | 3193 Enterprise Court | Loomis Ca 95650 | 9162591576 | 5305653834 | 3461 Robin Ln. Suite #4, | Cameron Park, Ca 95682 | Thompson, Brian | 34664.13 | 0 | 0 | 0 | 2025-10-20 | Cipp And Rcp. | El Dorado County Near Coloma At Various Locations From 0.4 Mile South Of South Fork American River Bridge To 0.1 Mile North Of Del | 6 | 6 | 34664.13 | 610479.91 | 610479.91 | 59825 | 2025-12-31 | 2025-06-26 | 2025-06-03 |  |  | 2 | 0 | 35 | 0 |  | X
03 | 03-4H8904 | 4H8904 | 03-ED-50-75.4/8 |  | HSNH-P050- (157)E | St. Francis Electric Llc | 975 Carden St | San Leandro Ca 94577 |  | 5309571110 | 3976 Durock Road, Suite 102 | Shingle Springs, Ca 95682 | Alterton, Nathan | 0 | 0 | 0 | 0 | 2025-08-20 | Modify Lighting And Fiber Optic Cable Syst | El Dorado County In South Lake Tahoe From North Junction Route 89 To Pioneer Trail | 60 | 65 | 13747407.68 | 21097000 | 21277175.29 | 55772 | 2025-09-08 | 2024-04-19 | 2024-03-28 |  |  | 126 | 0 | 210 | 0 |  | X
03 | 03-2N0704 | 2N0704 | 03-ED-50-180.0/18 |  |  | Doug Veerkamp General Engineering, Inc. | 3701 Trade Way | Cameron Park, Ca 95682 |  | 5309571110 | 3461Robin Ln Suite #4, Cameron Park, Ca 95682 |  | Alterton, Nathan | 0 | 0 | 0 | 0 | 2025-07-20 | Roadway Dip | Site Preparation Traffic Control Sawcut Excavation Slurry Backfill Minor Hma Paving Striping And Incidental Work Dir'S Emergency F | 100 | 30 | 143436.61 | 4300 | 485000 | 58995 | 2025-08-31 | 2025-06-18 | 2025-06-07 |  |  | 40 | 0 | 40 | 0
03 | 03-1N1804 | 1N1804 | 03-ED-50-189.0/18.9 | 20.XX 201130 |  | Doug Veerkamp General Engineering, Inc. | 3701 Trade Way | Cameron Park, Ca 95682 |  | 5305653834 | 3976 Durock Road, Ste. 102 | Shingle Springs, Ca 95682 | Thompson, Brian | 0 | 0 | 0 | 0 | 2025-08-20 | Retaining Wall | In Placer County At 3065 Blairs Ln, Placerville, Ca 95667 At The Caltrans Placerville Maintenance Station Dir'S Emergency F.A. | 28 | 55 | 243718.35 | 2973 | 446000 | 56079 | 2025-11-26 | 2024-06-20 | 2024-05-30 |  |  | 25 | 0 | 90 | 0 |  | X
03 | 03-0N6504 | 0N6504 | 03-ED-50-672.0/67.2 | 20.XX 201130 |  | Neil'S Controlled Blasting Lp | P.O. Box 749 | Newcastle, Ca 95658 |  | 5309571110 | 3976 Durock Road, Suite 102 | Shingle Spring Ca 95682 | Alterton, Nathan | 0 | 0 | 0 | 0 | 2025-05-20 | Ed 50 Rockfall - Slope Stabilization | Mobilization, Rockfall Mitigation, Slope Stabilization, Debris Removal, Traffic Control, And Incidental Work. Dir'S Emergency F.A. | 15 | 23 | 178354.84 | 5775 | 785000 | 55324 | 2026-04-23 | 2024-04-15 | 2023-12-21 |  |  | 9 | 0 | 60 | 0 |  | X
03 | 03-3G8104 | 3G8104 | 03-ED-89-81.0/8.1 |  |  | Acco Engineered Systems, Inc. | 888 E. Walnut Street | Pasadena, Ca 91101 |  | 5308126239 | 3461 Robin Ln Ste 4 | Cameron Park, Ca 95682 | Lopez, Andrew | 0 | 0 | 0 | 0 |  | South Lake Tahoe Mtce Station Rehab | Mobilization, Repair/Replace Residence Roof, Siding/Windows, Structural And Incidental Work Dir'S Emergency F.A. | 0 | 0 | 0 | 3825 | 985000 | 60100 | 2025-11-18 | 2025-10-06 | 2025-03-20 |  |  | 0 | 0 | 30 | 0
03 | 03-3G4304 | 3G4304 | 03-ED-89-/8.5 |  |  | All-American Construction, Inc. | 1700 Acacia Avenue | Sutter Ca 95982 | [5 empty] | 0 | 0 | 0 | 0 |  | Cold Plane Ac Pvmt And Hma (Type A) Overla | El Dorado County Near Meyers From Alpine County Line To Pomo Street | 0 | 0 | 0 | 3959843.26 | 3959843.26 | 59279 |  | 2025-07-01 | 2025-06-06 |  |  | 0 | 0 | 45 | 0
03 | 03-2G9804 | 2G9804 | 03-ED-193-2.0/8.9 |  |  | Doug Veerkamp General Engineering, Inc. | 2585 Cold Springs Rd | Placerville Ca 95667 | 5306760825 | 5305653834 | 3461 Robin Ln. Suite #4, | Cameron Park, Ca 95682 | Thompson, Brian | 112396.35 | 0 | 0 | 0 | 2025-10-20 | Replace Culverts. | El Dorado County At Various Locations Fromcramer Road To 0.2 Mile East Of Weed Patchcourt | 42 | 79 | 507068.35 | 637367.4 | 637367.4 | 59827 | 2025-12-31 | 2025-06-19 | 2025-05-29 |  |  | 19 | 0 | 45 | 0 |  | X
03 | 03-2G9304 | 2G9304 | 03-ED-193-3.5/5.6 |  |  | Robert J. Frank Construction, Inc. | 2806 Tarmac Road | Redding Ca 96003 | 5302221408 | 5305653834 | 3976 Durock Rd | Shingle Springs, Ca 95682 | Thompson, Brian | 135130 | 0 | 0 | 0 | 2025-10-20 | Install Cured-In-Place Pipeliner & Concret | El Dorado County Near Greenwood At Variouslocations From 0.3 Mile North Of Brush N Rocks Lane To 0.2 Mile South Of Pilgrim Court | 63 | 89 | 335710 | 375823 | 375823 | 59855 | 2025-12-31 | 2024-07-31 | 2024-06-28 |  | S | 19 | 0 | 30 | 0 |  | X
03 | 03-2G9704 | 2G9704 | 03-ED-193-11.9/17.3 |  |  | Wylatti Resource Management, Inc. | 23601 Cemetery Lane | Covelo Ca 95428 |  | 5305653834 | 3461 Robin Ln. Suite #4 | Cameron Park, Ca 95682 | Thompson, Brian | 403536.08 | 0 | 0 | 1638.92 | 2025-10-20 | Replace Culverts. | El Dorado County Near Georgetown At Various Locations From 0.1 Mile West Of Spanish Dry Diggins Road To 0.5 Mile West Of Traverse | 26 | 65 | 708209.12 | 1081125.47 | 1081125.47 | 58216 | 2025-12-31 | 2025-05-19 | 2025-04-29 |  |  | 21 | 0 | 80 | 0 |  | X
03 | 03-2J5904 | 2J5904 | 03-GLE-32-2.8/3.2 |  | SNHG-P032- (052)E | Studebaker Electric, Inc. | 3237 Rippey Road, Ste 100 | Loomis Ca 95650 | 9162592395 | 5309540879 | 2707 Notre Dame Blvd | Chico, Ca 95928 | Makhoul, Husam | 226255 | 0 | 0 | 5350 | 2025-06-20 | Install Traffic Signal. | Glenn County Near Orland From 0.2 Mile West To 0.2 Mile East Of County Road P | 58 | 66 | 1040146 | 1587834.6 | 1566234.6 | 57127 | 2025-07-28 | 2025-01-21 | 2024-12-23 |  |  | 35 | 0 | 60 | 0 |  | X
03 | 03-3J4324 | 3J4324 | 03-GLE-162-65.5/69.7 |  |  | Teichert Energy & Utilities Group, Inc. | 3500 American River Drive | Sacramento Ca 95864 | 9164388537 | 5309540879 | 2707 Notre Dame Blvd | Chico Ca 95928 | Makhoul, Husam | 167131.33 | 0 | 0 | 0 | 2025-10-20 | Middle-Mile Broadband Network | Glenn County In And Near Willows From Route 162/5 Separation To County Road P | 100 | 82 | 3088932.7 | 3650384.17 | 3650384.17 | 56908 | 2025-09-05 | 2024-11-19 | 2024-09-23 |  |  | 58 | 0 | 58 | 0
03 | 03-3F0604 | 3F0604 | 03-GLE-162-76.3/78.6 |  | ACST-P162- (041)E | Golden State Bridge, Inc. | 3701 Mallard Drive | Benicia Ca 94510 | 9253728000 | 5303206457 | 2707 Notre Dame Blvd | Chico, Ca 95928 | Watts, Dustin | 616905.62 | 408786.71 | 0 | 0 | 2025-10-20 | Replace Sacramento River Bridge | At Butte City, From Route 45 To 0.1 Mile East Of Mcdougall Street. | 76 | 96 | 81478002.67 | 70777777.47 | 85122654.42 | 42077 | 2026-03-27 | 2022-02-02 | 2022-01-07 |  |  | 328 | 0 | 430 | 0 |  | X
03 | 03-2H6214 | 2H6214 | 03-NEV-20-301.0/30.1 | 20.XX 201130 |  | Granite Construction Company | Po Box 742478 | Los Angeles, Ca 90074 |  | 5302659864 | 138 New Mohawk Rd, Suite B | Nevada City Ca 95959 | Johnson, Jeff | 7700 | 0 | 0 | 0 | 2025-08-15 | White Cloud Slip Out | Mobilization, Stabilize Slope, Place Rsp Remove Slide Material, Traffic Control, And Incidental Work. Dir'S Emergency L.B. | 100 | 100 | 5728773.94 | 7700 | 6985000 | 55728 | 2025-08-15 | 2024-06-06 | 2024-04-01 | 2025-09-23 |  | 132 | 0 | 200 | 0 |  | X
03 | 03-2G7904 | 2G7904 | 03-NEV-80-9.1/9.1 |  |  | Euro Style Management | 1401 Marin Ave | Sacramento Ca 95838 |  |  |  |  | Salehi, Reza | 152406.6 | 0 | 0 | 0 | 2025-10-15 | Spot Blast Clean And Paint Bridge. | Nevada County Near Truckee At Donner Lake Undercrossing | 68 | 77 | 718993.4 | 787400 | 936400 | 56105 | 2025-10-23 | 2024-07-17 | 2024-05-08 |  |  | 41 | 0 | 60 | 0 |  | X
03 | 03-3G7404 | 3G7404 | 03-NEV-80-156.0/15.6 | 20.80 521000 |  | Acco Engineered Systems, Inc. | 888 East Walnut Street | Pasadena, Ca 91101 |  | 5308213938 | 10183 Truckee Airport Rd., Suite 202, | Truckee, Ca 96161 | Hobbs, Douglas | 0 | 0 | 0 | 0 | 2025-10-20 | Truckee Boiler Replacement | In Nevada County Near Interstate 80 At Thecaltrans Truckee Maintenance Station Locatat 10152 Keiser Avenue, Truckee, Ca 96161 Dir' | 75 | 20 | 154166.73 | 3103 | 765000 | 60122 | 2025-11-01 | 2025-06-13 | 2025-02-18 |  |  | 15 | 0 | 20 | 0
03 | 03-3J3604 | 3J3604 | 03-NEV-89-5.3/8.7 |  |  | Teichert Energy & Utilities Group, Inc. | 3500 American River Drive | Sacramento Ca 95864 | 9166454874 | 6616236769 | 10183 Truckee Airport Rd. | Truckee Ca 96161 | Shawn Hagstrom | 2546505.09 | 0 | 0 | 0 | 2025-10-20 | Construct Middle Mile Broadband Network | Nevada And Sierra Counties From Route 80/89 Separation In Truckee To Plumas County Line About 6 Miles North Of Calpine | 47 | 48 | 16477701.53 | 33746241.75 | 33897841.01 | 57675 | 2026-11-05 | 2025-03-06 | 2025-02-21 |  |  | 103 | 0 | 220 | 0 |  | X
03 | 03-0J01U4 | 0J01U4 | 03-PLA-28-.1/11 |  | CSTP-P028- (012)E | Mercer Fraser Company | 200 Dinsmore Dr | Fortuna Ca 95540 |  | 5302181752 | 10183 Truckee Airport Rd. Ste | 202, Truckee, Ca 96161 | Salehi, Reza | 1728381.3 | 0 | 0 | 450000 | 2025-10-20 | Hma (Type A), Cold Plane Ac Pvmt, Rdwy Exc | Placer County From 0.1 Mile East Of Route 89 At Tahoe City To The Nevada State Line At Kings Beach | 14 | 28 | 6455871.92 | 22645645 | 22881428.56 | 57379 | 2026-04-22 | 2024-12-03 | 2024-10-02 |  |  | 31 | 0 | 220 | 0 |  | X
03 | 03-1H2404 | 1H2404 | 03-PLA-49-2.2/2.4 |  | SNHG-P049- (186)E | Lamon Construction | 871 Von Geldern Way | Yuba City Ca 95991 | 5308452282 | 9168256388 | 33 Depot St Po Box 1807 | Colfax Ca, 95713 | Clark, Martin | 18055.84 | 234927.4 | 0 | 0 | 2025-10-20 | Realign Roadway And Construct | In Placer County In Auburn From 0.1 Mile South Of The Intersection Of Route 49 And Lincoln Way / Borland Avenue To Lincoln Way | 85 | 76 | 5040083.74 | 5200075 | 6534673.97 | 42764 | 2026-01-09 | 2022-06-29 | 2022-05-27 |  |  | 305 | 0 | 130 | 229 |  | X
03 | 03-3H8304 | 3H8304 | 03-PLA-49-3.5/7.5 |  | PCML-6203- (071)E | Pacific Infrastructure Construction, Llc | 871 Cotting Court Ste A | Vacaville Ca 95688 | 7074493604 | 5307908595 | 138 New Mohawk Rd Suite B | Nevada City, Ca 95959 | Price, Lucas | 707867.66 | 30455.37 | 0 | 42000 | 2025-10-20 | Construct Sidewalks, Curb Ramps And Draina | Placer County In And Near Auburn From 0.3 Mile North Of Route 80/49 Separation To 0.1 Mile North Of Dry Creek Road | 49 | 60 | 5962722.39 | 9784573.9 | 9885780.99 | 57126 | 2026-03-20 | 2025-01-29 | 2025-01-06 |  |  | 98 | 0 | 200 | 0 |  | X
03 | 03-4H6004 | 4H6004 | 03-PLA-49-8.7/10.6 |  | SNHG-P049- (190)E | Desilva Gates Construction Llc | 11555 Dublin Blvd. | Dublin Ca 94568 | 9253611533 | 5302659864 | 138 New Mohawk Rd Suite B | Nevada City, Ca 95959 | Johnson, Jeff D. | 1942675.6 | 294125.33 | 145592 | 0 | 2025-10-20 | Conc Barrier, Jpcp, Hma, Rdwy Exc, Rcp And | Placer County Near Auburn From 0.3 Mile South Of Lorenson Road/Florence Lane To 0.4 Mile North Of Lone Star Road | 83 | 86 | 24631977.54 | 24318318 | 27604090.63 | 55164 | 2025-12-08 | 2024-02-13 | 2023-12-08 |  |  | 157 | 0 | 190 | 0 |  | X
03 | 03-3F23U4 | 3F23U4 | 03-PLA-80-.1/2.2 |  | ACIM-0803- (252)E | Ghilotti Construction Company,Inc. | 246 Ghilotti Avenue | Santa Rosa Ca 95407 | 7075851221 | 9168256388 | 33 Depot St. Po Box 1807 | Colfax Ca 95713 | Clark, Martin | 1440 | 280665.6 | 0 | 0 | 2025-09-20 | Roadway Excavation, Place C12-Ab, Hma, Str | Placer County In Roseville From 0.1 Mile West Of Riverside Avenue Overcrossing To 0.3 Mile East Of Douglas Boulevard Overcrossing | 100 | 98 | 38506324.85 | 36651367.56 | 38564464.7 | 51165 | 2026-06-02 | 2023-06-16 | 2023-05-25 |  |  | 242 | 0 | 240 | 2 |  | X
03 | 03-3H6104 | 3H6104 | 03-PLA-80-42.7/49.3 |  | ACIM-0804- (336)E | Desilva Gates Construction Llc | 11555 Dublin Blvd. | Dublin Ca 94568 | 9253611533 | 9167994858 | Po Box 1807 | Colfax, Ca 95713 | Sampson, Tad | 2661257.18 | 1721818.67 | -127083.18 | 0 | 2025-10-20 | Rdwy Exc, Hma, Jpcp, Alt Pipeliner, Steel | Placer County About 9.4 Miles North Of Colfax From 0.5 Mile West Of Monte Vista Overcrossing To 0.3 Mile East Of Drum Forebay Over | 18 | 54 | 67515750.69 | 121121121 | 124050578.82 | 55404 | 2026-09-18 | 2024-03-01 | 2024-02-15 |  |  | 107 | 0 | 590 | 5 |  | X
03 | 03-0J5604 | 0J5604 | 03-PLA-80-49.3/68.7 |  | PTIM-0804- (338)E | Mercer-Fraser Company | 200 Dinsmore Dr | Fortuna Ca 95540 | 7074436371 | 9167994858 | 33 Depot Street, Po Box 1807 | Colfax Ca 95713 | Sampson, Tad | 0 | 0 | 0 | 0 |  | Rcp, Wsp, And Electrical Systems. | Placer And Nevada Counties From 0.3 Mile East Of Drum Forebay Overcrossing To 0.2 Mile East Of Troy Undercrossing | 0 | 0 | 0 | 15654240.33 | 15654240.33 | 59835 |  | 2025-08-20 | 2025-07-11 |  |  | 0 | 0 | 155 | 0
03 | 03-1H9904 | 1H9904 | 03-PLA-80-68.3/69.7 |  | ACIM-0804- (337)E | A. Teichert & Son Inc Dba Teichert Construction | 3500 American River Dr | Sacramento Ca 95864 | 9164843011 | 9168256388 | 33 Depot St | Colfax, Ca 95713 | Clark, Martin | 1876997.38 | 4730 | 66162 | 0 | 2025-10-20 | Rdwy Exc, Place Hma & Jpcp, Slab Replaceme | Placer And Nevada Counties Near Kingvale From 0.3 Mile West Of Troy Undercrossing To 0.2 Mile East Of Soda Springs Overcrossing | 96 | 92 | 68598976.81 | 68586826 | 73387807.48 | 54867 | 2025-10-28 | 2023-12-21 | 2023-11-07 |  | S | 164 | 0 | 170 | 0 |  | X
03 | 03-4F6404 | 4F6404 | 03-SAC-5-.2/34.3 |  | SNHG-X067- (080)E | Dreambuilder | 18543 Yorba Linda Blvd # 376 | Yorba Linda Ca 92886 | 7146463697 | 9169521149 | 2777 Del Monte Street | West Sacramento, Ca 95691 | Olguin, Jorge | 202027.55 | 22643.75 | 0 | 0 | 2019-11-20 | Upgrade Metal Beam Guard Rail And | In Sacramento County On Routes 5, 80 And 99 At Various Locations | 100 | 87 | 2313487.22 | 2589061 | 2647135.34 | 40268 | 2019-11-22 | 2019-05-21 | 2019-04-19 |  | S | 92 | 0 | 55 | 0 |  | X
03 | 03-0N8504 | 0N8504 | 03-SAC-5-16.2/0 |  |  | Martin Brothers Construction | 8801 Folsom Boulevard Ste 260 | Sacramento Ca 95826 | [5 empty] | 0 | 0 | 0 | 0 |  | Minor Conc, Cl 2 Ab, Hma, And Modifying Li | Sacramento County In Sacramento At Pocket Road Overcrossing | 0 | 0 | 0 | 1067000 | 1067000 | 59457 |  | 2025-07-22 | 2025-06-19 |  |  | 0 | 0 | 45 | 0
03 | 03-2H1304 | 2H1304 | 03-SAC-5-22.4/22.9 |  | ACIM-0056- (359)E | Wabo Landscape & Construction, Inc. | 726 Alfred Nobel Dr. | Hercules Ca 94547 | 5107419226 | 9167992649 | 3855 N Freeway Blvd Suite 120 | Sacramento, Ca 95834 | Chander, Rakesh | 8100 | 10600 | 0 | 0 | 2025-10-20 | Highway Planting Rehabilitation. | In The City Of Sacramento, From South Of Broadway To 0.12 Mile South Of R Street. | 92 | 91 | 1377385.31 | 1685711.5 | 1485873.91 | 44505 | 2026-12-31 | 2022-08-19 | 2022-07-19 |  |  | 144 | 0 | 150 | 7 |  | X
03 | 03-3J5334 | 3J5334 | 03-SAC-5-26.7/29 |  |  | Teichert Energy & Utilities Group, Inc. | 3500 American River Drive | Sacramento Ca 95864 | 9164388500 | 5306496925 | 2777 Del Monte St | West Sacramento Ca 95691 | Ephrem Teweldeberhan | 213510.87 | 0 | 0 | 0 | 2025-07-20 | Middle-Mile Broadband Network | Sacramento County In And Near Sacramento On Route 80 From Sacramento River Bridge And Overhead (Bryte Bend) To Route 5 And On Rout | 85 | 100 | 4088263.74 | 4111816.52 | 4122948.02 | 57296 | 2025-05-30 | 2025-01-29 | 2024-12-20 |  |  | 55 | 0 | 65 | 0 |  | X
03 | 03-3J3304 | 3J3304 | 03-SAC-12-/.5 | 20.20201131 |  | Golden State Bridge, Inc. | 3701 Mallard Drive | Benicia, Ca 95510 |  | 5306496925 | 2777 Del Monte St | West Sacramento, Ca 95691 | Teweldeberhan, Ephrem | 0 | 0 | 0 | 0 | 2025-10-20 | Rio Vista Bridge | The Rio Vista Bridge (Br # 23-0024) State Route 12, Near Postmile 0 To 0.5 In Sacramento County | 100 | 69 | 18887261.54 | 72724 | 27200000 | 45264 | 2023-08-07 | 2022-11-09 | 2022-09-26 |  |  | 727 | 0 | 180 | 0
03 | 03-0H08U4 | 0H08U4 | 03-SAC-50-.2/6.1 |  |  | Flatiron Dragados West Llc | 1200 Concord Ave, Suite 250 | Concord, Ca 94520 | 7077426000 | 5306497022 | 2520 Warren Drive Suite A | Rocklin Ca 95677 | Ruzic, John | 1584250 | 136533.33 | -546026.75 | 0 | 2025-10-20 | Add High Occupancy Vehicle Lane And | In Sacramento County On Route 50 From I-5 Junction To Watt Ave. | 89 | 98 | 427633508.59 | 387675001 | 437983948.04 | 41166 | 2026-05-01 | 2020-06-30 | 2020-04-29 |  |  | 1037 | 0 | 925 | 242 |  | X
03 | 03-1N7904 | 1N7904 | 03-SAC-50-21.0/2.1 | 20.XX 201130 |  | Acco Engineered Systems, Inc. | 888 East Walnut Street | Pasadena, Ca 91101 |  | 5309540113 | 5900 Folsom Blvd | Sacramento, Ca 95819 | Angel Zaragoza, Gustavo | 0 | 0 | 0 | 0 | 2025-09-20 | Asbestos Abatement | Mobilization, Cleaning And Decontaminationasbestos And Other Hazardous Materials Abareplacement, Duct Removal, Repair Other Dadir' | 1 | 18 | 1405698.48 | 22785 | 7985000 | 59836 | 2026-08-30 | 2025-06-16 | 2025-03-03 |  |  | 1 | 0 | 90 | 0 |  | X
03 | 03-0N6204 | 0N6204 | 03-SAC-50-21.0/2.1 |  |  | Acco Engineered Systems, Inc. | 888 E Walnut St. | Pasadena, Ca 91101 |  | 5309540113 | 5900 Folsom Blvd | Sacramento, Ca 95819 | Zaragoza, Gustavo | 0 | 0 | 0 | 0 | 2025-10-20 | Translab Hvac System Repairs | In Sacramento County At 5900 Folsom Blvd. Sacramento, Ca, 95819. Dir'S Emergency F.A. | 79 | 5 | 1735660.99 | 38045 | 35985000 | 56274 | 2026-06-30 | 2024-08-28 | 2024-01-29 |  |  | 198 | 0 | 250 | 0
03 | 03-3F0704 | 3F0704 | 03-SAC-51-.2/3.5 | HA21 | ACNH-P051- (039)E | American River Constructors A Joint Venture | P.O. Box 50085 | Watsonville Ca 95077 | 9168554400 | 5306497022 | 1610 Arden Way Ste 277 | Sacramento Ca 95815 | John Ruzic | 1327284.94 | 239736.27 | 0 | 0 | 2025-10-20 | Deck Replacement | Sacramento County In Sacramento From 0.4 Mile South Of Elvas Underpass To 0.1 Mile North Of Exposition Boulevard | 56 | 85 | 112018630.14 | 131049478.34 | 131432518.86 | 52724 | 2026-08-03 | 2023-08-28 | 2023-08-28 |  |  | 506 | 0 | 900 | 0 |  | X
03 | 03-3F0734 | 3F0734 | 03-SAC-51-2.0/3.3 |  |  | American River Constructors A Joint Venture | Po Box 50085 | Watsonville Ca 95077 | 5306932155 | 9167683597 | 3855 N. Freeway Blvd #120 | Sacramento, Ca 95834 | Dean Elghassein | 0 | 102841.15 | 0 | 0 | 2025-09-20 | Dredge, Construct In-Water Foundation. | Sacramento County In Sacramento From 0.4 Mile South Of Elvas Underpass To 0.1 Mile North Of Exposition Boulevard | 91 | 98 | 54860179.97 | 50137078.3 | 55856529.75 | 43464 | 2027-02-28 | 2022-06-28 | 2022-06-28 |  |  | 246 | 0 | 270 | 0 |  | X
03 | 03-1N5404 | 1N5404 | 03-SAC-51-17.0/1.7 | 20.80 521000 |  | Mcm Roofing Company Inc. | 3410 Flight Lane Bldg. 25 | Mcclellan, Ca 95652 |  | 5308218422 | 1610 Arden Way #277 | Sacramento, Ca, 95815 | Charak, Michael | 0 | 0 | 0 | 0 | 2025-09-20 | Facility Roof Repairs | At The Sunrise Bridge Crew Maintenance Station Located At 2809 B St., Sacramento, Ca 95819 Dir'S Emergency F.A. | 100 | 80 | 790905.18 | 6975 | 985000 | 58195 | 2025-09-26 | 2025-02-24 | 2024-11-22 |  |  | 60 | 0 | 60 | 0
03 | 03-1H6304 | 1H6304 | 03-SAC-99-12.7/16.3 |  | ACNH-P099- (683)E | O.C. Jones & Sons, Inc. | 1520 Fourth Street | Berkeley Ca 94710 |  | 5302184829 | 2777 Del Monte St | West Sacramento, Ca 95691 | Saed, Masoud | 386214.83 | 82196.46 | -19487.04 | 0 | 2025-10-20 | Construct Two Aux Lanes, Conc Barrier, & M | Sacramento County In And Near Elk Grove From 0.1 Mile South Of Elk Grove Boulevardovercrossing To Calvine Road Overcrossing | 70 | 88 | 16292292.07 | 18279906.25 | 18343173.37 | 55825 | 2025-10-07 | 2024-02-29 | 2024-01-30 |  |  | 168 | 0 | 240 | 0 |  | X
03 | 03-3J9004 | 3J9004 | 03-SAC-160-44.9/0 |  | HSNH-P160- (027)000 | Pacific Infrastructure Construction, Llc | 871 Cotting Court Ste A | Vacaville Ca 95688 | [5 empty] | 0 | 0 | 0 | 0 |  | Modify Signal And Lighting Systems. | Sacramento County In Sacramento At 0.1 Mile South Of North Sacramento Undercrossing | 0 | 0 | 0 | 1436652.4 | 1436652.4 | 59796 |  | 2025-08-12 | 2025-08-05 |  |  | 0 | 0 | 45 | 0
03 | 03-1N0104 | 1N0104 | 03-SAC-160-/0 | 20.XX 201131 |  | Golden State Bridge Inc. | 3701 Mallard Drive | Benicia Ca 94510 |  | 5306496925 | 2777 Del Monte St. | W. Sacramento Ca 95691 | Teweldeberhan, Ephrem | 0 | 0 | 0 | 0 | 2025-10-20 | Repair/Replace Bridge Components | Mobilization Repair And Or Replace Electrical And Mechanical Bridge Components Traffic Control Dir'S Emergency F.A. | 77 | 50 | 10037652.66 | 87620 | 19985000 | 56108 | 2026-03-04 | 2024-07-19 | 2024-05-31 |  |  | 309 | 0 | 400 | 0
03 | 03-4H9704 | 4H9704 | 03-SAC-5500-/0 |  |  | Creekside Commercial Builders,Inc. | 3131 Peacekeeper Way Ste 400 | Mcclellan Ca 95652 |  | 5302155427 | 3461 Robin Ln. Ste. 4 | Cameron Park, Ca 95682 | Thompson, Brian | 666023.17 | 0 | 0 | 0 | 2025-10-20 | Heating Ventilation And Air Conditioning R | Sacramento County In Rancho Cordova At Theregional Transportation Management Center,3165 Gold Valley Drive | 14 | 82 | 3495670.96 | 4263463 | 4263463 | 56748 | 2026-01-06 | 2024-12-03 | 2024-11-01 |  |  | 21 | 0 | 150 | 0 |  | X
03 | 03-3G4104 | 3G4104 | 03-SUT-70-2.4/5.4 |  |  | A. Teichert & Son, Inc. Dba Teichert Construction | 3500 American River Dr | Sacramento Ca 95864 |  | 5308125727 | 379 Colusa Hwy | Yuba City, Ca 95991 | Horse, Dustin | 666338.35 | 0 | 0 | 0 | 2025-09-20 | Rhma, Hma, And Cold Plane Ac Pavement. | Sutter County About 17 Miles South Of Marysville From 0.6 Mile South Of Marcum Road Overcrossing To 0.3 Mile North Of Cornelius Av | 54 | 96 | 2038940.43 | 1994894 | 2080894 | 59821 | 2025-09-29 | 2025-06-26 | 2025-06-13 |  |  | 19 | 0 | 35 | 0 |  | X
03 | 03-4H8704 | 4H8704 | 03-SUT-99-25.0/26.2 |  | HSNH-P099- (686)E | O.C. Jones & Sons, Inc. | 1520 Fourth Street | Berkeley Ca 94710 |  | 5308125727 | 379 Colusa Ave | Yuba City, Ca 95991 | Horse, Dustin | 0 | 60188.76 | 40414.52 | 0 | 2025-09-20 | Rdwy Exc, Place Hma-A And Crcp, Install Si | Sutter County Near Yuba City From 0.6 Milesouth To 0.6 Mile North Of Oswald Road | 69 | 95 | 6059742.32 | 6224280 | 6524999.44 | 56601 | 2025-10-31 | 2024-10-29 | 2024-10-09 |  | S | 69 | 0 | 100 | 0 |  | X
03 | 03-0J3504 | 0J3504 | 03-VAR-149-/5.3 | 20.20 201130 |  | A. Teichert & Son, Inc. Dba Teichert Construction | 400 Sunrise Ave Ste 300 | Roseville Ca 95661 |  | 5307137814 | 2707 Notre Dame Blvd., | Chico, Ca 95928 | Grandy, Dwayne | 7500 | 8775 | 0 | 0 | 2021-03-29 | Camp Fire Mission Tasks | In Butte, Yuba And Sutter Counties On Routes 65, 70, 99, 149 And 191 At Various Locations. Dir'S Emergency L.B. | 100 | 74 | 1828973.13 | 7500 | 2485000 | 40395 | 2021-03-29 | 2019-07-24 | 2019-06-14 |  |  | 200 | 0 | 200 | 0
03 | 03-3G2304 | 3G2304 | 03-VAR--/0 |  |  | Myers & Sons Construction, Llc | 45 Morrison Ave | Sacramento Ca 95838 |  | 5306496925 | 2777 Del Monte St | West Sacramento, Ca 95691 | Teweldeberhan, Ephrem | 1264591.95 | 0 | 0 | 75000 | 2025-10-20 | Furnish And Place Polyester Concrete Overl | Sacramento County At Various Locations | 24 | 61 | 2063319.57 | 3374372 | 3352346.88 | 59375 | 2025-12-12 | 2025-07-16 | 2025-06-19 |  |  | 49 | 0 | 205 | 0 |  | X
03 | 03-1N0004 | 1N0004 | 03-VAR--/0 | 20.10 201352 |  | Pisor Fence Division, Inc | Po Box 7213 | Citrus Heights, Ca 95621 |  | 5306823842 | 379 Colusa Ave | Yuba City, Ca 95991 | Griffith, Garrett | 0 | 0 | 0 | 0 | 2025-10-20 | Security Measures | Mobilization, Install New Fencing, Replace Security Gates Install New Security System Dir'S Emergency L.B. | 100 | 58 | 2416472.41 | 24275 | 4160000 | 57098 | 2025-12-31 | 2024-12-03 | 2024-05-17 |  |  | 80 | 0 | 30 | 0
03 | 03-3H5604 | 3H5604 | 03-VAR--/0 |  | BFNH-000C- (560)E | Flatiron Dragados West Llc | 1200 Concord Ave, Ste 465 | Concord, Ca 94520 | 7077426000 | 9167994858 | 33 Depot Street, Po Box 1807 | Colfax, Ca 95713 | Sampson, Tad | 6852954.25 | 122628.22 | 0 | 0 | 2025-10-20 | Structural Conc, Bar Reinforcing Steel, Br | Placer And Nevada Counties Near Cisco Grove On Route 80 From 0.4 Mile West Of Lake Valley Overcrossing To 0.9 Mile East Of Yuba Pa | 37 | 51 | 45438992.01 | 82988787.14 | 88588322.85 | 55913 | 2026-07-06 | 2024-06-05 | 2024-05-10 |  |  | 190 | 0 | 515 | 0 |  | X
03 | 03-3H9014 | 3H9014 | 03-VAR--/0 |  | NFRA-6203- (070)000 | Desilva Gates Construction Llc | 11555 Dublin Blvd. | Dublin Ca 94568 |  | 5308213881 | 2777 Del Monte Street | West Sacramento, Ca 95691 | Wild, Joseph | 6126647.69 | 24626.94 | 24300 | 2480000 | 2025-10-20 | Hma, Rhma, Sign Structure, Camera Systems, | Solano And Yolo Counties At Various Locations | 35 | 31 | 38666533.01 | 124798898 | 125891319.2 | 56621 | 2026-07-29 | 2024-10-23 | 2024-09-27 |  |  | 103 | 0 | 295 | 0 |  | X
03 | 03-3J40U4 | 3J40U4 | 03-VAR--/0 |  |  | Teichert Energy & Utilities Group, Inc. | 3500 American River Drive | Sacramento Ca 95864 |  | 5309571110 | 3461 Robin Lane, Suite 4 | Cameron Park, Ca 95682 | Alterton, Nathan | 3599147.57 | 0 | 0 | 0 | 2025-10-20 | Middle-Mile Broadband Network | Alpine, El Dorado, And Placer Counties In And Near South Lake Tahoe On Route 89 Fromroute 88 To Route 28 And On Route 50 From Sout | 20 | 26 | 13649187.88 | 51749000.73 | 51799000.73 | 57695 | 2026-11-12 | 2025-03-12 | 2025-03-12 |  |  | 67 | 0 | 329 | 0 |  | X
03 | 03-3G4804 | 3G4804 | 03-VAR--/0 |  |  | Studebaker Electric, Inc. | 3237 Rippey Road, Ste 100 | Loomis Ca 95650 |  | 5308218282 | 3855 N. Freeway Blvd #120 | Sacramento, Ca 95834 | Tji, Jony | 825 | 0 | 0 | 0 | 2025-08-20 | Modify Cms Systems. | Butte, Sacramento, Sutter And Yolo Counties At Various Locations | 0 | 0 | 825 | 794500 | 794500 | 59824 | 2026-03-31 | 2025-06-09 | 2025-05-22 |  |  | 0 | 0 | 15 | 0 |  | X
03 | 03-3G4704 | 3G4704 | 03-VAR--/0 |  |  | Studebaker Electric, Inc. | 3237 Rippey Road, Ste 100 | Loomis Ca 95650 |  | 5308218282 | 3855 N. Freeway Blvd #120 | Sacramento, Ca 95834 | Tji, Jony | 900 | 0 | 0 | 0 | 2025-08-20 | Modify Cms Systems. | Butte, El Dorado And Sacramento Counties At Various Locations | 0 | 0 | 900 | 697580 | 697580 | 59823 | 2026-03-31 | 2025-05-23 | 2025-05-02 |  |  | 0 | 0 | 20 | 0 |  | X
03 | 03-3G4604 | 3G4604 | 03-VAR--/0 |  |  | Studebaker Electric, Inc. | 3237 Rippey Road, Ste 100 | Loomis Ca 95650 | 9162592395 | 9167994858 | 33 Depot St | Colfax, Ca 95713 | Sampson, Tad | 0 | 0 | 0 | 0 |  | Modify Cms Systems. | Nevada And Placer Counties At Various Locations | 0 | 0 | 0 | 796300 | 796300 | 59822 |  | 2025-06-10 | 2025-06-03 |  |  | 0 | 0 | 20 | 0
03 | 03-3G4904 | 3G4904 | 03-VAR--/0 |  |  | Studebaker Electric, Inc. | 3237 Rippey Road, Ste 100 | Loomis Ca 95650 | [5 empty] | 0 | 0 | 0 | 0 |  | Modify Cms. | Placer County At Various Locations | 0 | 0 | 0 | 823180 | 608002.1 | 58516 |  | 2025-06-04 | 2025-05-15 |  |  | 0 | 0 | 15 | 0
03 | 03-3G1704 | 3G1704 | 03-VAR--/0 |  |  | St. Francis Electric Llc | 975 Carden St | San Leandro Ca 94577 |  | 5302183679 | 379 Ca-20 | Yuba City, Ca 95991 | Manoharan, Selvendran | 0 | 0 | 0 | 0 | 2025-10-20 | Modify Traffic Monitoring Stations. | Butte, Colusa, Glenn, Sacramento, Sutter, Yolo, And Yuba Counties At Various Locations | 80 | 97 | 457332.07 | 444300 | 472332.07 | 55924 | 2025-01-28 | 2024-06-11 | 2024-04-25 |  |  | 24 | 0 | 30 | 0 |  | X
03 | 03-3G1804 | 3G1804 | 03-VAR--/0 |  |  | Central Striping Service, Inc. | 3489 Luyung Drive | Rancho Cordova Ca 95742 |  | 5302183679 | 379 Ca-20 | Yuba City, Ca 95991 | Manoharan, Selvendran | 181488.7 | 0 | 0 | 0 | 2025-06-20 | Remove And Place Traffic Stripe And Paveme | Butte, El Dorado, Nevada, Placer, Sutter, And Yuba Counties At Various Locations | 55 | 79 | 1634929.25 | 2043201.77 | 2043201.77 | 55877 | 2025-07-15 | 2024-05-31 | 2024-03-29 |  |  | 55 | 0 | 100 | 0 |  | X
03 | 03-3G3704 | 3G3704 | 03-VAR--/0 |  |  | Specialized Pavement Marking, Llc | 11095 Sw Industrial Way Suite | Tualatin Or 97062 | 5308850420 | 9164167513 | 3855 N.Freeway Blvd # 120 |  | Eissa, Hani | 1101967.73 | 0 | 0 | 85500 | 2025-10-20 | Remove And Place Pavement Delineation. | Colusa, Glenn, Nevada, Placer, Sacramento,And Yolo Counties At Various Locations | 40 | 40 | 1187467.73 | 2996619.5 | 2996619.5 | 59820 | 2025-12-25 | 2025-07-02 | 2025-06-10 |  |  | 32 | 0 | 80 | 0 |  | X
03 | 03-3G6204 | 3G6204 | 03-YOL-5-22.8/28.9 |  |  | All-American Construction, Inc. | 1700 Acacia Avenue | Sutter Ca 95982 |  | 5308125727 | 379 Colusa Avenue | Yuba City, Ca 95991 | Horse, Dustin | 1953964.36 | 0 | 0 | 0 | 2025-10-20 | Cold Plane Ac Pvmt And Hma (Type A). | Yolo County Near Dunnigan From 0.2 Mile North Of Route 505/5 Separation To The Colusa County Line | 28 | 80 | 2304783.96 | 2896607 | 2896607 | 59296 | 2025-11-10 | 2025-07-09 | 2025-06-03 |  |  | 11 | 0 | 40 | 0 |  | X
03 | 03-3G4004 | 3G4004 | 03-YOL-16-10.0/15 |  |  | All-American Construction, Inc. | 1700 Acacia Avenue | Sutter Ca 95982 |  | 5306496925 | 2777 Del Monte St | West Sacramento, Ca 95691 | Teweldeberhan, Ephrem | 227058.71 | 0 | 0 | 0 | 2025-10-06 | Partial Depth Recycling, And Rhma-G. | Yolo County At And Near Guinda From 0.2 Mile East Of County Road 43 East Intersection To 0.1 Mile West Of County Road 68 | 100 | 100 | 2634337.07 | 2709877.5 | 2706048.61 | 59396 | 2025-10-06 | 2025-07-15 | 2025-06-11 | 2025-10-14 |  | 40 | 0 | 40 | 0 |  | X
03 | 03-4J1204 | 4J1204 | 03-YOL-16-37.3/37.8 |  | HSST-S016- (001)E | Bay Cities Paving & Grading, Inc. | 1450 Civic Ct Bldg B #400 | Concord Ca 94520 | [5 empty] | 0 | 0 | 0 | 0 |  | Hma, Flashing Beacon System, And Roadway E | Yolo County Near Woodland 0.2 Mile West Ofcounty Road 95 To 0.2 Mile East Of County Road 95 | 0 | 0 | 0 | 1779057.81 | 1779057.81 | 60118 |  | 2025-10-13 | 2025-09-05 |  |  | 0 | 0 | 50 | 0
03 | 03-4F6504 | 4F6504 | 03-YOL-50-/2.5 |  | ACNH-X113- (036)E | Flat-Iron Teichert A Joint Venture | 1200 Concord Avenue Suite 465 | Concord Ca 94520 | 7077426000 | 9168013455 | 1016 N. Market Blvd Ste 50/60 | Sacramento, Ca 95834 | Mehari, Mirak | 11321828.56 | 500338.05 | 499043.93 | 0 | 2025-10-20 | Crcp, Hma (Type A), Rdwy Exc, Class 2 Ab, | Yolo County In And Near West Sacramento Onroute 80 From 1.7 Miles East Of Mace Boulevard Overcrossing To Sacramento Riverbridge An | 67 | 82 | 194536711.68 | 204804408.8 | 232576962.25 | 47744 | 2026-07-10 | 2023-03-17 | 2023-02-14 |  |  | 370 | 0 | 505 | 44 |  | X
03 | 03-0H3704 | 0H3704 | 03-YUB-65-.5/1.8 |  |  | Baldwin Contracting Co., Inc. Dba Knife River Construction | 1764 Skyway | Chico Ca 95928 | 5305185548 | 5303206457 | 2707 Notre Dame Blvd | Chico, Ca 95928 | Watts, Dustin | 20700 | 0 | 0 | 0 | 2025-09-22 | Place Hma, Rhma & Conc Curb/Sidewalk, Inst | Yuba County Near Wheatland From 0.2 Mile South Of Main Street To Grasshopper Sloughbridge | 100 | 100 | 6552445.98 | 7000277.5 | 6746914.54 | 50765 | 2025-09-22 | 2023-06-29 | 2023-06-08 | 2025-10-09 |  | 80 | 0 | 385 | 0 |  | X
04 | 04-3Y1904 | 3Y1904 | 04-ALA-0-/0 | 20.20.201130 |  | Norcal General Construction Corporation | 751 Mabury Rd | San Jose, Ca, 95133 | 4085954015 | 3414009265 | 1007 Knox Ave | San Jose, Ca 95122 | Li, Peijie | 0 | 0 | 0 | 0 | 2024-12-24 | Repair Knocked Down Electrical Assets- Pol | District South-Wide Repair Of Electrical Edistrict South-Wide Repair Of Electrical Edistrict South-Wide Repair Of Electrical Edir' | 99 | 86 | 1170129.55 | 29000 | 1365500 | 48265 | 2025-10-15 | 2023-03-29 | 2023-01-20 |  |  | 79 | 0 | 80 | 0 |  | X
04 | 04-2G4614 | 2G4614 | 04-ALA-13-10.7/13 |  | ACNH-P013- (138)E | Accurate Earthworks, Inc. | 501 Cesar Chavez Suite 212A | San Francisco Ca 94124 | 7144235566 | 9257665224 | 3401 Regatta Blvd | Richmond, Ca 94804 | Seng, Ta | 162380.67 | 0 | 0 | 0 | 2024-05-20 | Reconstruct Ada Curb Ramps. | Alameda County In Berkeley At Various Locations From Domingo Avenue To Mabel Street | 93 | 77 | 633988.14 | 777321 | 827321 | 46424 | 2024-05-31 | 2023-04-17 | 2023-01-26 |  |  | 56 | 0 | 60 | 0
04 | 04-3W9304 | 3W9304 | 04-ALA-80-5.7/6 |  |  | Marina Landscape Inc. | 3707 W Garden Grove Blvd | Orange Ca 92868 | 7149396600 | 5107746276 | 3401 Regatta Blvd. | Richmond Ca.94804 | Luckel, Kasaia | 2173.5 | 0 | 0 | 0 | 2025-09-20 | Highway Planting And Irrigation System, Ro | Alameda County In Berkeley From 0.1 Mile West To 0.2 Mile East Of University Avenueovercrossing | 70 | 94 | 2007011.15 | 2120678.25 | 2140906.7 | 47847 | 2026-09-30 | 2023-03-22 | 2023-02-24 |  |  | 588 | 0 | 840 | 0 |  | X
04 | 04-3J2604 | 3J2604 | 04-ALA-80-5.9/6.4 |  | SIMG-000C- (562)E | O.C. Jones & Sons, Inc. | 1520 Fourth Street | Berkeley Ca 94710 | 5106840157 | 5108676156 | 3401 Regatta Blvd | Richmond, Ca 94804 | Faustin, Glenn | 383648.65 | 52076.03 | 0 | 22500 | 2025-10-20 | Install Cb, Wrought Iron Fence, Modify Lig | Alameda County In Fremont From 0.1 Mile South Of Mission San Jose 680/238 Separation To 0.3 Mile North Of Mission San Jose 680/238 | 100 | 63 | 3066307.14 | 4525446.5 | 4873491.99 | 57117 | 2025-09-17 | 2025-01-07 | 2024-12-13 |  |  | 100 | 0 | 100 | 0
04 | 04-0A7724 | 0A7724 | 04-ALA-80-6.4/6.8 |  | ACIM-0801- (121)E | O.C. Jones & Sons, Inc. | 1520 Fourth Street | Berkeley Ca 94710 | 5105263424 | 5108676093 | 3847 Breakwater Ave. | Hayward, Ca 94545 | Champaneria, Vinay | 17705 | 88072.94 | 0 | 0 | 2025-10-20 | Construct Double Roundabouts At | On I-80 At Gilman Street Interchange From 0.6 Miles North Of University Avenue Oc To 0.5 Mile South Of El Cerrito Separation In An | 78 | 97 | 32993940.54 | 25231719.98 | 33833337.31 | 42059 | 2026-05-30 | 2022-01-27 | 2022-01-04 |  |  | 531 | 0 | 600 | 81 |  | X
04 | 04-0K1604 | 0K1604 | 04-ALA-80-7.6/8 |  | SIMG-0801- (998)E | Bay Cities Paving & Grading, Inc. | 1450 Civic Ct Bldg B #400 | Concord Ca 94520 | 9256876666 | 9166346646 | 3401 Regatta Blvd. | Richmond, Ca 94804 | Nou, Bunma | 3709344.25 | 10890.36 | -200248.34 | 0 | 2025-10-20 | Construct Rhma, Lighting System, And Concr | Alameda And Contra Costa Counties In Albany And Crockett From 0.4 Mile South Ofalameda County Line To 0.2 Mile South Of Pomona Str | 100 | 91 | 52415349.99 | 55089000 | 56827565.43 | 49124 | 2025-12-31 | 2023-03-02 | 2023-02-08 |  |  | 354 | 0 | 350 | 0 |  | X
04 | 04-4Y1804 | 4Y1804 | 04-ALA-80-/1.8 |  |  | Ghilotti Bros And St Francis Electric Jv | 525 Jacoby Street | San Rafael Ca 94901 | 4154547011 | 5108674545 | 575 Linda Mar Blvd. | Pacifica, Ca 94044 | Larwin, Thomas | 0 | 0 | 0 | 0 |  | Middle-Mile Broadband Network (Mmbn) On Sa | On San Francisco Bay Bridge | 0 | 0 | 0 | 1725640.72 | 1725640.72 | 57597 |  | 2025-03-12 | 2025-03-12 |  |  | 0 | 0 | 75 | 0
04 | 04-3Q8504 | 3Q8504 | 04-ALA-84-10.8/18 |  | HSNH-P084- (060)E | Tennyson Electric, Llc | 7275 National Dr Ste A-2 | Livermore Ca 94550 | 9256061038 | 5104592581 | 5675-B Gibraltar Drive | Pleassanton, Ca 94588 | Sadeghi-Nedjad, Amir-Fardin | 291548.55 | 0 | 0 | 9250 | 2025-10-20 | Flashing Beacon Systems. | Alameda County In Fremont, Union City And At Sunol From Route 238 To 0.1 Mile West Of Route 680 | 72 | 65 | 1504499.75 | 2298130 | 2298130 | 57676 | 2025-12-31 | 2025-03-27 | 2025-02-13 |  |  | 86 | 0 | 120 | 0 |  | X
04 | 04-160314 | 160314 | 04-ALA-84-11.0/18 |  |  | Bortolussi & Watkin, Inc. | 77 Larkspur Street | San Rafael Ca 94901 | 4154534675 | 5107746276 | 3401 Regatta Blvd. | Richmond, Ca 94804 | Luckel, Kasaia | 1293.55 | 0 | 0 | 0 | 2025-10-20 | Maintain Existing Planted Area, Highway Pl | Alameda County In And Near Fremont And In Sunol At Various Locations From 0.2 Mile East Of Route 238 Junction (Mission Boulevard) | 12 | 22 | 136602.42 | 599975 | 614975 | 56807 | 2029-03-02 | 2024-12-10 | 2024-11-22 |  |  | 129 | 0 | 1040 | 0 |  | X
04 | 04-1X2804 | 1X2804 | 04-ALA-84-11.2/15.5 | 20.20.201130 |  | Pacific Coast Drilling Co.,Inc | 364 Bellevue Ave. | Santa Rosa, Ca 95407 | 7077788316 | 9252505611 | 5675-B Gibraltar Drive | Pleasanton, Ca 94588 | Dike, Eddie | 0 | 0 | 0 | 0 | 2025-10-20 | Niles Canyon Slipout | In Alameda County In Sunol Hwy 84 Niles Canyon Slope And Retaining Wall Repair Dir'S Order Emergency F.A. | 100 | 97 | 5250191.78 | 34658 | 5385000 | 55465 | 2025-10-30 | 2024-03-13 | 2024-02-20 |  |  | 427 | 0 | 240 | 0 |  | X
04 | 04-297634 | 297634 | 04-ALA-84-17.9/22.9 |  |  | Bay Cities Paving & Grading, Inc. | 1450 Civic Ct Building B#400 | Concord, Ca 94524-6227 | 9252276296 | 5108676694 | 5675 B Gibraltar Drive | Pleasanton, Ca 94588 | Pandher, Paramjit | 600559.53 | 0 | 0 | 0 | 2025-10-20 | Widening Route 84 To Expressway And | In And Near Sunol, Pleasanton And Livermore On Rte 680 From 1.2 Mi South To 1.8 Mi North Of Rte 84 And On Rte 84 From 0.1 Mi East | 65 | 96 | 140429474.51 | 133802176.49 | 143201224.98 | 41508 | 2026-01-12 | 2021-03-11 | 2021-02-19 |  |  | 651 | 0 | 1000 | 0 |  | X
04 | 04-0X6604 | 0X6604 | 04-ALA-84-21.4/23.1 |  |  | Bay Cities Paving & Grading, Inc. | 1450 Civic Ct Bldg B #400 | Concord Ca 94520 | 9256876666 | 5108676694 | 5675 B Gibraltar Drive | Pleasanton, Ca 94588 | Pandher, Paramjit | 1130504.68 | 0 | 0 | 0 | 2025-10-20 | Cold Plane Ac Pavement And Overlay With Rh | Alameda County In And Near Pleasanton And Livermore From 0.1 Mile South Of Vehicle Undercrossing South To 0.1 Mile South Of Ruby H | 29 | 74 | 1134104.68 | 1524597.25 | 1524597.25 | 59736 | 2025-12-08 | 2025-07-29 | 2025-06-25 |  |  | 13 | 0 | 45 | 0 |  | X
04 | 04-2Q7604 | 2Q7604 | 04-ALA-238-.7/.8 |  | ACNH-X001- (671)E | Ghilotti Bros., Inc. | 525 Jacoby Street | San Rafael Ca 94901 | 4154547011 | 5103858001 | 5675 B Gibraltar Drive | Pleasanton, Ca 94588 | Reza, Kamkar | 6750 | 4229.1 | 0 | 0 | 2025-10-20 | Rectangular Rapid Flashing Beacon Systems, | Alameda County In Fremont On Route 680 At Off-Ramp To Scott Creek Road And On Route 238 At Mission Ridge Court | 41 | 95 | 2017336.43 | 1988816.01 | 2069807.01 | 55946 | 2025-12-17 | 2024-06-17 | 2024-05-22 |  |  | 163 | 0 | 395 | 0 |  | X
04 | 04-0G3604 | 0G3604 | 04-ALA-260-.8/1.9 |  | ACNH-X001- (692)E | Bay Cities Paving & Grading, Inc. | 1450 Civic Ct Bldg B #400 | Concord Ca 94520 | 9256876666 | 5103857081 | 3847 Breakwater Avenue | Hayward, Ca 94545 | Champaneria, Vinay | 0 | 0 | 0 | 0 |  | Modify Ramps, Hma Pvmt, Bridges, Drainage, | Alameda County In Oakland And Alameda On Route 260 From Willie Stargell Avenue To 7Th Street And On Route 880 From 23Rd Avenue To | 0 | 0 | 0 | 95207833.25 | 95477833.25 | 59915 | 2030-07-18 | 2025-08-27 | 2025-08-08 |  | S | 0 | 0 | 1130 | 0
04 | 04-2W7404 | 2W7404 | 04-ALA-260-1.1/1.9 | 20.20.201130 |  | Monterey Mechanical Co | 8275 San Leandro Street | Oakland, Ca 95621 | 5106323173 | 5108676694 | 5675 Gibraltar Drive, Suite B, | Pleasanton, 94588 | Pandher, Paramjit | 0 | 0 | 0 | 0 | 2025-10-03 | Install Fuel Cell Power System | In Alameda County, At The Posey-Webster Tubes Install Fuel Cell Power System | 97 | 82 | 7835598.13 | 38005 | 9544000 | 42145 | 2025-12-31 | 2022-01-11 | 2021-09-06 |  |  | 418 | 0 | 340 | 92 |  | X
04 | 04-1Y3404 | 1Y3404 | 04-ALA-260-1.2/0 |  |  | Disney Construction, Inc. | 533 Airport Blvd., Suite 120 | Burlingame Ca 94010 | 6502599545 | 5103857081 | 3847 Breakwater Ave. | Hayward, Ca 94545 | Champaneria, Vinay | 88290.12 | 0 | 0 | 0 | 2025-10-20 | Repair Spalled Surface Area And Replace Po | Alameda County In Alameda And Oakland At The Posey Tube And Webster Street Tube | 34 | 12 | 455515.12 | 3833333 | 3903833 | 58737 | 2026-02-09 | 2025-06-09 | 2025-05-19 |  |  | 37 | 0 | 110 | 0 |  | X
04 | 04-3X9504 | 3X9504 | 04-ALA-580-4.6/4.7 | 20.20.201130 |  | Redgwick Construction Company | 21 Hegenberger Ct | Oakland, Ca 94621 | 0254706675 | 5103939557 | 5675-B Gibraltar Dr | Pleasanton, Ca 94588 | Shah, Purvi | 0 | 0 | 0 | 0 |  | Dir'S Order Emergency F.A. | Livermore Repair Livermore Culvert Replace Livermore Culvert Repair/Replace Culvert | 0 | 0 | 0 | 4500 | 635000 | 60128 | 2026-06-10 | 2025-10-17 | 2025-08-27 |  |  | 0 | 0 | 40 | 0
04 | 04-3Y5504 | 3Y5504 | 04-ALA-580-4.7/4.8 | 20.20.201130 |  | Viking Construction Company, Inc. | Po Box 1508 | Rancho Cordova Ca 95741 | 9168525530 | 5108676694 | 5675 B Gibraltar Drive | Pleasanton Ca 94588 | Pandher, Paramjit | 0 | 0 | 0 | 0 | 2025-09-19 | Repair Failed Slope And Construct New Rw | Efa Contract To Repair Rw On Eb 580 Pm4.7 To 4.8 Efa Contract To Repair Rw On Eb 580 Pm4.7 Dir'S Order Emergency F.A. | 97 | 94 | 12422726.89 | 18775 | 13276000 | 48504 | 2025-10-03 | 2023-05-31 | 2023-03-20 |  |  | 387 | 0 | 80 | 317 |  | X
04 | 04-0Q1004 | 0Q1004 | 04-ALA-580-20.7/30.8 |  | ACIM-5801- (984)E | Fbd Vanguard Construction | 550 Greenville Road | Livermore Ca 94550 | 9252451300 | 5108676694 | 5675 B Gibraltar Drive | Pleasanton, Ca 94588 | Pandher, Paramjit | 2568707.1 | 30949.11 | 0 | 0 | 2025-10-20 | Individual Slab Replacement, Hma, Rhma, Ap | Alameda County In Pleasanton And Castro Valley From Route 680/580 Separation To Route 580/238 Separation | 47 | 79 | 40187613.36 | 47466283.6 | 48769135.68 | 56337 | 2026-08-07 | 2024-09-10 | 2024-07-11 |  |  | 179 | 0 | 350 | 28 |  | X
04 | 04-2Y8604 | 2Y8604 | 04-ALA-580-26.2/26.2 | 20.20.201130 |  | Redgwick Construction Company | 21 Hegenberger Ct, | Oakland 94621 | 5107921727 | 5108676694 | 5675-B Gibraltar Dr., | Pleasanton, Ca | Pandher, Paramjit | 0 | 0 | 0 | 0 | 2025-10-20 | Slide And Slipout Repair Along Wb 580 Eden | Ala 580&680 Var Loc , Incl Eden Canyon & Sherdian, Sunol Grade - Slipouts | 100 | 55 | 2654391.03 | 7380 | 4805000 | 46665 | 2025-12-31 | 2023-02-08 | 2023-01-03 |  |  | 139 | 0 | 20 | 0
04 | 04-0Y6804 | 0Y6804 | 04-ALA-580-35.0/45.2 |  |  | Ghilotti Bros And St Francis Electric Jv | 525 Jacoby Street | San Rafael, Ca 94901 | 4154547011 | 5103857081 | 3847 Breakwater Ave. | Hayward, Ca 94545 | Baluyot, Rodelio | 1149919.48 | 0 | 0 | 397697.81 | 2025-10-20 | Install Broadband Conduit And Fiber For Br | In Alameda County, On Route 580 From Ala-580 Pm 35 To Pm 45.193 | 42 | 29 | 2631002.93 | 8841107.02 | 8926107.02 | 57615 | 2025-06-01 | 2025-02-26 | 2025-02-26 |  |  | 110 | 0 | 260 | 0 |  | X
04 | 04-3Y1304 | 3Y1304 | 04-ALA-580-43.1/43.1 | 20.20.201130 |  | Redgwick Construction Company | 21 Hegenberger Court | Oakland Ca 94621 | 5107921727 | 5108676031 | 3847 Breakwater Ave | Hayward, Ca 94545 | Zhang, Rui | 0 | 0 | 0 | 0 | 2025-06-20 | Perform Polyurethane Foam Injection, Insta | In Alameda County In The City Of Oakland -In Alameda County In The City Of Oakland -In Alameda County In The City Of Oakland -Dir' | 50 | 89 | 1178185.2 | 9000 | 1325000 | 49927 | 2024-12-30 | 2023-05-26 | 2023-01-16 | 2025-10-31 |  | 50 | 0 | 100 | 0 |  | X
04 | 04-2K7904 | 2K7904 | 04-ALA-580-45.4/45.8 |  | ACNH-000C- (533)E | Bortolussi & Watkin, Inc. | 77 Larkspur Street | San Rafael Ca 94901 | 4154534675 | 5107746276 | 3401 Regatta Blvd | Richmond, Ca 94804 | Luckel, Kasaia | 0 | 33804.58 | 0 | 0 | 2025-10-20 | Highway Planting And Irrigation | In Alameda And Solano Counties At Various Locations | 100 | 90 | 1315807.23 | 1419349 | 1449349 | 41923 | 2025-10-30 | 2021-10-22 | 2021-09-28 |  |  | 888 | 0 | 870 | 0 |  | X
04 | 04-2Y8204 | 2Y8204 | 04-ALA-580-/32.7 | 20.20.201130 |  | Pipe And Plant Solutions, Inc. | 23286 Foley Street, | Hayward, Ca 94545 |  | 5103857081 | 3847 Breakwater Ave. | Hayward Ca 94545 | Champaneria, Vinay | 0 | 0 | 0 | 0 | 2025-09-15 | Repair And Replace Damaged Pump Plant | Repair And Replace Damaged Pump Plant | 100 | 74 | 2065454.3 | 6975 | 2803000 | 47484 | 2025-12-30 | 2023-04-18 | 2023-01-09 |  |  | 450 | 0 | 30 | 0
04 | 04-0P9204 | 0P9204 | 04-ALA-680-6.3/6.7 |  | ACIM-6801- (993)E | Myers & Sons Construction, Llc | 45 Morrison Ave | Sacramento Ca 95838 | 9162839950 | 5108676181 | 5675 B Gibraltar Drive | Pleasanton, Ca 94588 | Tun, Yannaing | 100209.05 | 296794.36 | 0 | 0 | 2025-10-20 | Hma And Rhma Surfacing, Deck Repair, Polye | Alameda County In Fremont From 0.1 Mile South Of Mission San Jose 680/238 Separation To 0.3 Mile North Of Mission San Jose 680/238 | 93 | 96 | 7707947.76 | 7447650.3 | 7844763.1 | 57010 | 2025-11-03 | 2025-01-16 | 2024-12-20 |  |  | 125 | 0 | 135 | 0 |  | X
04 | 04-0Q30U4 | 0Q30U4 | 04-ALA-680-11.0/21.9 |  | ACIM-6801- (990)E | Bay Cities Paving & Grading, Inc. | 1450 Civic Ct Building B #400 | Concord Ca 94520 | 9256876666 | 5108676181 | 5675 B Gibraltar Drive | Pleasanton, Ca 94588 | Tun, Yannaing | 1554188.06 | 1340374.31 | -130576.96 | 0 | 2025-10-20 | Construct Express Lanes And | In Alamed And Contra Costa Counties At Sunol And In San Ramon From Koopmann Road Undercrossing To 0.9 Mile North Of Alcosta Boulva | 62 | 96 | 174191334.8 | 175969550.24 | 179860340.28 | 45964 | 2027-04-02 | 2022-12-13 | 2022-11-23 |  |  | 592 | 0 | 950 | 0 |  | X
04 | 04-2W4604 | 2W4604 | 04-ALA-680-15.6/0 |  |  | Serafix Engineering Contractors, Inc. | 7 Crow Canyon Court Ste 250 | San Ramon Ca 94583 | 9255528253 | 9252505611 | 5675 B Gibraltar Drive | Pleasanton, Ca 94588 | Dike, Eddie | 135560 | 0 | 0 | 0 | 2025-10-20 | Slope Repair And Replace Downdrains And In | Alameda County In Pleasanton At South Pleasanton Overhead | 100 | 98 | 594326.56 | 717460 | 729460 | 59335 | 2025-10-30 | 2025-07-14 | 2025-06-25 |  |  | 30 | 0 | 30 | 0 |  | X
04 | 04-0Q1804 | 0Q1804 | 04-ALA-880-6.2/25.5 |  | ACIM-8801- (989)E | Anvil Builders Inc. | 1550 Park Ave | Emeryville Ca 94608 | 4152855000 | 5108676079 | 3847 Breakwater Ave. | Hayward, Ca 94545 | Singh, Jasmaninder | 62212.1 | 116493.74 | 0 | 0 | 2025-07-20 | Install Trash Net, Concrete Ditch, Welded | Alameda County At Various Locations From Stevenson Boulevard Overcrossing In Fremont To Hegenberger Road Overcrossing In Oakland | 98 | 94 | 2622026.02 | 2491642.8 | 2875170.9 | 55775 | 2025-08-31 | 2024-05-08 | 2024-04-08 |  |  | 118 | 0 | 120 | 0 |  | X
04 | 04-1X3804 | 1X3804 | 04-ALA-880-/28.9 | 20.10.201352 |  | Anvil Builders, Inc. | 1550 Park Ave. | Emeryville, Ca 94608 | 4152855000 | 5108676083 | 3847 Breakwater Ave. | Hayward, Ca 94545 | Baluyot, Rodelio | 0 | 0 | 0 | 0 | 2025-08-31 | Install/Replace Video Surveillance System | Maintenance Facilities In Ala, Cc, Scl And Sol Counties Install/Replace Video Surveillance System Dir'S Order Emergency F.A. | 24 | 90 | 899861.75 | 4322 | 1003000 | 56318 | 2026-09-28 | 2024-08-28 | 2024-08-07 |  |  | 125 | 0 | 530 | 0 |  | X
04 | 04-2K7004 | 2K7004 | 04-ALA-880-/11.8 |  | ACIM-8801- (987)E | Bay Cities Paving & Grading, Inc. | 1450 Civic Ct Bldg B #400 | Concord Ca 94520 | 9256876666 | 5108676083 | 3847 Breakwater Ave | Hayward, Ca 94545 | Baluyot, Rodelio | 206438.44 | 116626.74 | 0 | 0 | 2025-09-20 | Cold Plane Pavement And Overlay With Rhma- | Alameda County In Fremont And Newark From Santa Clara County Line To 0.4 Mile North Of Fremont Boulevard Overcrossing | 87 | 99 | 81281531.3 | 76445361 | 81829980.73 | 52424 | 2025-05-30 | 2023-08-16 | 2023-07-13 |  | S | 252 | 0 | 290 | 0 |  | X
04 | 04-4K9804 | 4K9804 | 04-ALA-980-1.1/1.1 | 20.20.201130 |  | San Francisco Elevator Services, Llc | 6509 Sierra Lane | Dublin, Ca 94568 | 9258295400 | 5103858001 | 5675-B Gibraltar Drive | Pleasanton, Ca 94588 | Kamkar, Reza | 0 | 0 | 0 | 0 | 2025-08-22 | Building Elevator Rehab | In Oakland, At The Caltrans District 4 Headquarters Office Building, 111 Grand Avenue Order Emergency F.A. | 35 | 53 | 2973767.11 | 70325 | 5611000 | 42026 | 2026-08-07 | 2021-12-23 | 2021-10-11 |  |  | 303 | 0 | 335 | 535 |  | X
04 | 04-3W9104 | 3W9104 | 04-ALA-980-1.2/0 |  | ACST-000C- (558)E | Parsons Transportation Group, Inc. | 555 12Th Street, Suite 2150 | Oakland Ca 94607 | 5104183801 | 3414009265 | 1007 Knox Avenue | San Jose, Ca 95122 | Li, Peijie | 85245.61 | 0 | 0 | 0 | 2025-10-20 | Upgrade Controllers In Vehicle Detection A | At Various Locations | 48 | 23 | 4633629.15 | 19826704.19 | 19881704.19 | 56609 | 2026-12-22 | 2024-08-15 | 2024-08-15 |  |  | 276 | 0 | 574 | 0 |  | X
04 | 04-2K9504 | 2K9504 | 04-ALA-5501-/14.4 |  |  | Walsh Construction Company Ii,Llc | 1390 Willow Pass Road | Concord Ca 94520 |  | 5104592581 | 5675-B Gibraltar Drive | Pleasanton, Ca 94588 | Sadeghi-Nedjad, Amir-Fardin | 98074.23 | 0 | 0 | 0 | 2025-10-20 | Construct Material Testing Laboratory Buil | Alameda County In Livermore At 2201 Kitty Hawk Road | 70 | 97 | 18254203.57 | 16132760.3 | 18872994.85 | 47524 | 2025-10-21 | 2023-03-02 | 2023-02-02 |  |  | 576 | 0 | 625 | 202 |  | X
04 | 04-0Q2004 | 0Q2004 | 04-CC-4-12.4/25 |  | ACNH-P004- (164)E | Ghilotti Bros., Inc. | 525 Jacoby Street | San Rafael Ca 94901 | 4154547011 | 5104218049 | 2525 Stanwell Drive, Suite 100 | Concord, Ca 94520 | Kalantari, Ramin | 120797.67 | 0 | 0 | 0 | 2025-10-20 | Concrete (Ditch Lining) & Trash Net (Open | Contra Costa County At Various Locations From Pacheco Boulevard Undercrossing To Century Boulevard Undercrossing | 94 | 91 | 1516252.89 | 1519319 | 1662179 | 57435 | 2025-11-20 | 2025-03-27 | 2025-03-11 |  |  | 113 | 0 | 120 | 0 |  | X
04 | 04-3X5804 | 3X5804 | 04-CC-4-19.8/19.8 | 20.20.201130 |  | G N Henley Inc | 3107 Morgan Territory Rd, | Clayton, Ca 94517 |  | 5104075226 | 2525 Stanwell, Suite 100, | Concord, Ca 94520 | Kim, Jaeyoon | 0 | 0 | 0 | 0 |  | Slope Repair And Repaid Displaced Downdra | Slope Repair And Repaid Displaced Downdrain | 0 | 0 | 0 | 7727 | 777500 | 59637 | 2025-12-22 | 2025-08-05 | 2025-04-24 |  |  | 0 | 0 | 50 | 0
04 | 04-2Q7004 | 2Q7004 | 04-CC-4-/14.3 |  | ACNH-P004- (163)E | Bay Cities Paving & Grading, Inc. | 1450 Civic Ct Bldg B #400 | Concord Ca 94520 | 9256876666 | 5107744383 | 2525 Stanwell Drive, Ste 100 | Concord, Ca 94520 | Mukherjee, Rabindra | 4043268.61 | 0 | 0 | 0 | 2025-10-20 | Replace Asphalt Concrete Surfacing And Ins | Contra Costa County In Hercules And Concord From San Pablo Avenue To Route 4/242 Separation | 71 | 70 | 26428694.35 | 35010000 | 37179152.89 | 55873 | 2026-04-08 | 2024-05-29 | 2024-04-26 |  |  | 268 | 0 | 350 | 30 |  | X
04 | 04-3X7404 | 3X7404 | 04-CC-24-5.1/5.4 | 20.20.201130 |  | Brannon Corporation | 10492 Dougherty Ave | Morgan Hill Ca 95037 |  | 5104075226 | 2525 Stanwell, Suite 100, | Concord, Ca 94520 | Kim, Jaeyoon | 0 | 0 | 0 | 0 |  | Pavement Delineation And Any Additional Wo | Repair Roadway Settlement, Polyurethane Injection.Reconstruct Hma Dikes And Mgs,Erosion Control. Pavement Delineation And Any Addi | 0 | 0 | 0 | 4476 | 606000 | 60130 | 2026-03-06 | 2025-10-21 | 2025-07-08 |  |  | 0 | 0 | 30 | 0
04 | 04-0Q2104 | 0Q2104 | 04-CC-80-.2/10.7 |  | ACIM-0801- (996)E | Bay Cities Paving & Grading, Inc. | 1450 Civic Ct Bldg B #400 | Concord Ca 94520 | 9256876666 | 5106316697 | 3401 Regatta Blvd. | Richmond, Ca 94804 | Culp, Matthew | 449894.13 | 77940.85 | -508.64 | 34350 | 2025-10-20 | Install Gross Solids Removal Devices And T | Contra Costa County At Various Locations From Central Avenue Undercrossing To Willow Avenue Undercrossing. | 25 | 72 | 4181665.53 | 6870000 | 5776134.81 | 56727 | 2026-09-29 | 2024-09-18 | 2024-09-04 |  |  | 138 | 0 | 550 | 0 |  | X
04 | 04-0P9304 | 0P9304 | 04-CC-80-7.6/0 |  | BFIM-0801- (958)E | Bugler Construction, Inc. | 4847 Hopyard Rd. Suite 4-395 | Pleasanton Ca 94588 | 9254160700 | 7079758086 | 3401 Regatta Blvd. | Richmond, Ca 94804 | Deng, Zhuohang | 334391.25 | 0 | 0 | 0 | 2025-10-20 | Bridge Railing, Mvp, Curb & Gutter, Sidewa | Contra Costa County In Pinole At Appian Way Overcrossing And At Crockett At Cummings Skyway Overcrossing. | 32 | 24 | 1574616.25 | 6368565.5 | 6877915.5 | 57777 | 2026-04-03 | 2025-04-15 | 2025-03-19 |  |  | 51 | 0 | 160 | 0 |  | X
04 | 04-4X3804 | 4X3804 | 04-CC-80-7.6/7.6 | 20.10.201130 |  | Golden State Bridge, Inc. | 3701 Mallard Drive | Benicia, Ca 94510 | 9253728000 | 5108676156 | 3401 Regatta Blvd. | Richmond, Ca 94804 | Faustin, Glenn | 0 | 0 | 0 | 0 |  | Bridge Repair | Cc-80-Pm 7.6, Br. No. 28 0146R Applian Way Overcrossing (West) Bridge Repair Dir'S Order Emergency F.A. | 0 | 0 | 0 | 39933 | 7820000 | 60080 | 2026-02-19 | 2025-09-18 | 2025-07-24 |  |  | 0 | 0 | 140 | 0
04 | 04-0X6904 | 0X6904 | 04-CC-160-/.7 |  |  | Fbd Vanguard Construction, Inc. | 550 Greenville Road | Livermore Ca 94550 | 9252451300 | 5103857211 | 2525 Stanwell Drive, Suite 100 | Concord, Ca 94520 | Lee, Steven | 1835890 | 0 | 0 | 323000 | 2025-10-20 | Individual Slab Replacement, & Place Joint | Contra Costa County In And Near Antioch From 0.2 Mile West Of Route 4/160 Connector To 0.1 Mile South Of Antioch Bridge | 43 | 65 | 2158890 | 3330224 | 3330224 | 57955 | 2025-12-29 | 2025-04-21 | 2025-04-04 |  |  | 34 | 0 | 80 | 0 |  | X
04 | 04-3G3644 | 3G3644 | 04-CC-580-6.1/7.8 |  |  | Studebaker Electric, Inc. | 3237 Rippey Road | Loomis Ca 95660 | 9162592395 | 5108676107 | 3401 Regatta Blvd | Richmond, Ca 94804 | Halali, Behzad | 1116980 | 0 | 0 | 18000 | 2025-10-20 | Electrical Substations, Power Cables, And | Contra Costa And Marin Counties In Richmond And San Rafael From 0.3 Mile Westof Toll Plaza To 0.1 Mile West Of Main Street Undercr | 78 | 34 | 7120680.97 | 13371480 | 20746044.93 | 54946 | 2026-06-04 | 2024-01-23 | 2024-01-04 |  |  | 397 | 0 | 400 | 110
04 | 04-2Q6504 | 2Q6504 | 04-CC-680-/21 |  | ACIM-6801- (994)E | Bay Cities Paving & Grading, Inc. | 1450 Civic Ct Bldg B #400 | Concord Ca 94520 | 9256876666 | 5104218049 | 2525 Stanwell, Suite 100, | Concord, Ca 94520 | Kalantari, Ramin | 226167.23 | 0 | 0 | 0 | 2025-10-20 | Install Trash Capture Housing Devices, Mvp | Contra Costa County At Various Locations From Alameda County Line To Route 4/ 680 Separation | 25 | 13 | 622150.25 | 4950981.06 | 4950981.06 | 57935 | 2026-06-09 | 2025-04-24 | 2025-03-27 |  |  | 53 | 0 | 210 | 0 |  | X
04 | 04-1X0304 | 1X0304 | 04-MRN-1-8.7/8.7 | 20.10.201130 |  | Terracon Constructors, Inc. | Po Box 276 | Healdsburg, Ca 95448 | 7074330323 | 5107746297 | 384 Bel Marin Keys Blvd,Ste200 | Novato, Ca 94949 | Russell, Steve | 0 | 0 | 0 | 0 | 2025-07-25 | Repair Drainage, Sinkholes & Pavement | In Marin County On State Rte 1, Pm 8.69 Repair Drainage, Sinkholes And Pavement Settement Dir'S Order Emergency F.A. | 100 | 96 | 865960.78 | 6090 | 900000 | 55782 | 2025-07-31 | 2024-05-08 | 2024-03-08 |  |  | 47 | 0 | 30 | 0 |  | X
04 | 04-1J9604 | 1J9604 | 04-MRN-1-22.8/33 |  | ACST-P001- (693)E | O.C. Jones & Sons, Inc. | 1520 Fourth Street | Berkeley Ca 94710 | 5105263424 | 5105939011 | 384 Bel Marin Keys Blvd. | Novato, Ca 94949 | Wong, Andrew | 539002.4 | 282185.84 | 0 | 0 | 2025-10-20 | Cold Plane, Rhma, Hma, Mgs, Curb Ramps, Si | Marin County In And Near Point Reyes Station From Five Brooks To 1.9 Miles North Of Cypress Road And In And Near Tomales From 0.2 | 47 | 88 | 14598544.06 | 14588627.5 | 16044065.35 | 55409 | 2026-04-14 | 2024-03-07 | 2024-02-13 |  |  | 241 | 0 | 510 | 0 |  | X
04 | 04-3X2604 | 3X2604 | 04-MRN-1-/19.3 | 20.20.201130 |  | Marinship Development Interestllc | 1485 Bayshore Blvd, Ste 200, | San Francisco, Ca 94124 | 4157163965 | 5107746297 | 384 Bel Marin Keys Blvd, | Novato, Ca 94949-5361 | Russell, Steve | 0 | 0 | 0 | 0 |  | Install Gabion Basket Retaining Wall, Repa | Install Gabion Basket Retaining Wall, Repair Drainage | 0 | 0 | 0 | 5809 | 875000 | 58275 | 2025-09-30 | 2025-04-16 | 2025-04-16 |  |  | 0 | 0 | 50 | 0
04 | 04-2K7404 | 2K7404 | 04-MRN-37-11.2/14.5 |  | ACNH-P037- (219)E | Bay Cities Paving & Grading, Inc. | 1450 Civic Ct Bldg B #400 | Concord Ca 94520 | 9256876666 | 5106817264 | 384 Bel Marin Keys Blvd Ste200 | Novato, Ca 94949 | Prokop, Christopher | 790255.06 | 13069.04 | 0 | 0 | 2025-10-20 | Cold Plane Ac Pvmt, Place Rhma And Replace | Marin County In And Near Novato From Ignacio Overhead To Petaluma River Bridge | 23 | 41 | 4168394.36 | 9755877.29 | 10143742.56 | 57009 | 2025-11-20 | 2025-01-21 | 2024-12-20 |  |  | 85 | 0 | 370 | 0 |  | X
04 | 04-3X3604 | 3X3604 | 04-MRN-101-3.0/3 | 20.20.201130 |  | Maggiora & Ghilotti, Inc. | 555 Dubois St, | San Rafael, Ca 94901 |  | 5107746297 | 384 Bel Marin Keys Blvd. | Novato, Ca 94949 | Russell, Steve | 0 | 0 | 0 | 0 | 2025-07-31 | Slide Repair | Sb Waldo Grade, Sausalito | 83 | 96 | 664112.61 | 3330 | 695000 | 58375 | 2025-07-31 | 2025-05-29 | 2025-02-14 |  |  | 50 | 0 | 60 | 0 |  | X
04 | 04-0K8004 | 0K8004 | 04-MRN-101-13.7/0 |  | ACNH-Q101- (428)E | Ghilotti Bros., Inc. | 525 Jacoby Street | San Rafael Ca 94901 | 4154547011 | 5103856980 | 384 Bel Marin Keys Blvd. | Novato, Ca 94949 | Habteselassie, Dawit | 146511.19 | 0 | 0 | 0 | 2025-10-20 | Construct Roundabout, Curb Ramps And Sw, S | Marin County In San Rafael At Freitas Parkway Overcrossing | 30 | 50 | 3304404.52 | 6242312 | 6600284 | 57259 | 2026-10-16 | 2025-02-27 | 2025-02-05 |  |  | 104 | 0 | 345 | 0 |  | X
04 | 04-264724 | 264724 | 04-MRN-101-20.8/27.1 |  | CML -6204- (132)N | Ghilotti Construction Company,Inc. | 2301 Kerner Blvd #E | Santa Rafael, Ca 94901 | 4152561525 | 5104969271 | 384 Bel Marin Keys Blvd. | Ste 200 Novato, Ca 94949 | La Serna, Fabio | 2832734.6 | 2080.39 | 0 | 0 | 2025-10-20 | Roadway And Bridge Widening For Hov | In Marin County In And Near Novato From 0.1 Mile South Of Franklin Avenue Overhead To 0.5 Mile South Of San Antonio Creek Bridge | 68 | 91 | 83816452.32 | 78860144.47 | 89717220.72 | 42410 | 2026-11-17 | 2022-05-13 | 2022-04-26 |  |  | 714 | 0 | 1000 | 52 |  | X
04 | 04-2X9404 | 2X9404 | 04-MRN-101-/9.3 | 20.20.201130 |  | Ghilotti Bros, Inc | 525 Jacoby Street | San Rafael, Ca 94901 | 4154547011 | 5107746297 | 384 Bel Marin Keys Blvd. Suite 200 | Novato, Ca 94949 | Russell, Steve | 0 | 0 | 0 | 0 | 2025-08-20 | Clear Debris From Landslide, Regrade Slope | Clear Debris From Landslide, Regrade Slope And Install Erosion Control | 92 | 81 | 1097454.67 | 8327 | 1355000 | 57096 | 2025-09-30 | 2024-11-26 | 2024-11-26 |  |  | 55 | 0 | 60 | 0 |  | X
04 | 04-3X1504 | 3X1504 | 04-MRN-580-6.0/7.8 | 20.20.201130 |  | Studebaker Electric, Inc | 3237 Rippey Rd, Ste 100, | Loomis, Ca 95650 | 9162592395 | 5108676107 | 3401 Regatta Blvd, | Richmond, Ca 94804-4594 | Halali, Behzad | 0 | 0 | 0 | 0 |  | Replace Stolen Wires | Rsr Bridge Replace Stolen Wires | 0 | 0 | 0 | 11100 | 910000 | 58657 | 2025-11-28 | 2025-06-10 | 2025-02-14 |  |  | 0 | 0 | 40 | 0
04 | 04-4J4104 | 4J4104 | 04-NAP-29-1.7/1.7 |  |  | Terracon Constructors, Inc. | 150 Alexander Valley Rd | Healdsburg Ca 95448 | 7074330323 | 9252606460 | 324 Campus Lane Ste T | Fairfield Ca 94534 | Brar, Paramdeep | 0 | 0 | 0 | 0 | 2025-10-20 | Replace And Place Cement Liner On Rcb Culv | Napa County In And Near American Canyon At Rio Del Mar And 0.4 Mile South Of Northkelly Road | 100 | 90 | 1651291.89 | 1773041.94 | 1815669.44 | 49265 | 2025-11-01 | 2023-04-07 | 2023-03-21 |  |  | 569 | 0 | 330 | 0 |  | X
04 | 04-281204 | 281204 | 04-NAP-29-5.0/6.7 | HE11 | ACNH-X055- (060)E | Ghilotti Construction Company,Inc. | 246 Ghilotti Ave | Santa Rosa Ca 95407 | 7075851221 | 9252505595 | 324 Campus Lane Ste T | Fairfeild, Ca 94534 | Isada, Darren | 4880 | 82303.18 | 0 | 0 | 2025-10-20 | Intersection Improvements | In Napa County At The Intersection Of Routes 29/12 And Route 221 | 90 | 100 | 35901267.65 | 31606566.6 | 35963721.42 | 42412 | 2025-12-31 | 2022-05-13 | 2022-03-21 |  |  | 640 | 0 | 710 | 0 |  | X
04 | 04-2Q6104 | 2Q6104 | 04-NAP-29-7.3/13.5 |  | ACNH-P029- (155)E | Granite Rock Company | 5225 Hellyer Avenue, Suite 22 | San Jose Ca 95138 | 4085741400 | 9252606460 | 324 Campus Lane, Suite T | Fairfield, Ca 94534 | Brar, Paramdeep | 1100098.04 | 48242.78 | 0 | 0 | 2025-10-20 | Cold Plane, Rhma Overlay, Install Mgs, Cur | Napa County In And Near Napa From 0.2 Milenorth Of Napa River Bridge Overhead To 0.1Mile South Of Sierra Avenue. | 57 | 84 | 14457868.77 | 17680347.75 | 16736694.18 | 56886 | 2025-12-30 | 2024-11-26 | 2024-11-04 |  |  | 130 | 0 | 230 | 0 |  | X
04 | 04-0Q8204 | 0Q8204 | 04-NAP-29-11.6/13 |  | PTNH-P029- (153)E | Ranger Pipelines Incorporated | 833 Featherstone Road | Rockford Il 61104 | 4158223700 | 5102246309 | 324 Campus Lane Suite T | Fairfield, Ca 94534 | Patenia, Danilo | 1208177.5 | 93917.28 | 0 | 0 | 2025-10-20 | Const Drainage Systems, Mod Pumping Equipm | Napa County In Napa From 0.1 Mile North Offirst Street Overcrossing To 0.1 Mile South Of Trancas Street Overcrossing | 29 | 95 | 20861584 | 23068709 | 22159366.14 | 56536 | 2025-12-31 | 2024-10-01 | 2024-08-29 |  |  | 135 | 0 | 470 | 0 |  | X
04 | 04-0K6304 | 0K6304 | 04-NAP-29-16.4/19 |  |  | Gordon N. Ball, Inc. | 1777 Oakland Blvd. Ste 300 | Walnut Creek, Ca 94596 | 9258385675 | 5102246309 | 324 Campus Lane, Suite T | Fairfield, Ca 94534 | Patenia, Danilo | 7920 | 0 | 0 | 0 | 2025-10-20 | Bridge Rail Replacement And Shoulder Widen | Napa County Near Yountville At Various Locations From 0.1 Mile South Of Dry Creekbridge To 0.1 Mile North Of California Drive Unde | 64 | 95 | 3428795.53 | 3246583 | 3420580.7 | 51104 | 2025-12-20 | 2023-07-14 | 2023-06-27 |  |  | 283 | 0 | 440 | 0 |  | X
04 | 04-3X4904 | 3X4904 | 04-NAP-29-45.5/45.5 | 20.20.201130 |  | Piazza Construction | 5200 Carroll Road, | Petaluma, Ca 94952 | 7078763410 | 5102246309 | 324 Campus Lane, | Fairfield, Ca 94534 | Patenia, Danilo | 0 | 0 | 0 | 0 | 2025-10-20 | Install Rsp, Repair Drainage | Calistoga Install, Rsp Repair Drainage Install Rsp, Repair Drainage | 100 | 19 | 116261.97 | 4314 | 611000 | 58215 | 2025-12-31 | 2025-05-14 | 2025-04-17 |  |  | 31 | 0 | 30 | 0
04 | 04-0Q8304 | 0Q8304 | 04-NAP-29-46.1/0 |  |  | Gordon N. Ball, Inc. | 333 Camille Avenue | Alamo Ca 94507 | 9258385675 | 9252606460 | 324 Campus Lane, Suite T | Fairfield, Ca 94534 | Brar, Paramdeep | 1200 | 0 | 0 | 0 | 2025-10-20 | Soldier Pile, Conc Backfill, Hma, Timber L | Napa County Near Calistoga At 2.5 Miles South Of Lake County Line | 81 | 97 | 1037331.5 | 1018909 | 1033909 | 56124 | 2026-07-09 | 2024-07-12 | 2024-06-18 |  |  | 279 | 0 | 345 | 0 |  | X
04 | 04-4G21A4 | 4G21A4 | 04-NAP-121-.5/1 |  | HSST-P121- (133)EST - - ( ) | John Semsen Landscaping Co., Inc. | 21161 Lyons Bald Mountain Roa | Sonora Ca 95370 | 2097434911 | 5108674515 | 3401 Regatta Blvd | Richmond Ca 94804 | Simpson, John | 4032 | 0 | 0 | 0 | 2025-10-20 | Maintain Existing Planted Area. | Napa County Near Napa From 0.2 Mile South To 0.3 Mile North Of Huichica Creek Bridge | 42 | 61 | 244499.06 | 381240 | 401240 | 54884 | 2028-04-18 | 2023-12-20 | 2023-11-28 |  |  | 441 | 0 | 1060 | 0 |  | X
04 | 04-3X2804 | 3X2804 | 04-NAP-121-19.5/19.5 | 20.20.201130 |  | Valentine Corporation | 111 Pelican Way, | San Rafael, Ca 94901 | 4157204443 | 9252606460 | 324 Campus Lane, | Fairfield, Ca 94534 | Brar, Paramdeep | 0 | 0 | 0 | 0 | 2025-10-20 | Slipout And Pavement Repair | Nap-121 121-19.5 Slipout And Pavement Repair | 100 | 75 | 2516767.22 | 16902 | 3355000 | 57779 | 2025-12-31 | 2025-02-06 | 2025-02-06 |  |  | 124 | 0 | 100 | 0
04 | 04-4G84A4 | 4G84A4 | 04-NAP-128-20.1/20.4 |  |  | Bortolussi & Watkin, Inc. | 77 Larkspur Street | San Rafael Ca 94901 | 4154534675 | 5107746276 | 3401 Regatta Blvd | Richmond Ca.94804 | Luckel, Kasaia | 6652.76 | 0 | 0 | 2225 | 2025-10-20 | Environmental Permit Mitigation & | Near Napa, At Capell Creek Bridge No. 21-0078. Environmental Mitigation And Plant Establishment For Rehabilitate Bridge Project Ea | 63 | 59 | 263220.56 | 445858 | 463858 | 45905 | 2027-05-11 | 2022-11-21 | 2022-11-17 |  |  | 656 | 0 | 1040 | 0 |  | X
04 | 04-3X0204 | 3X0204 | 04-NAP-128-/25.9 | 20.20.201130 |  | Valentine Corporation | 111 Pelican Way, | San Rafael, Ca 94901 | 4154533732 | 9252505595 | 324 Campus Lane, Suite T, | Fairfield, 94534 | Isada, Darren | 0 | 0 | 0 | 0 | 2025-10-20 | Slipout And Drainage Repair | At Wragg Creek At Wragg Creek | 22 | 18 | 487447.41 | 14021 | 2665000 | 57317 | 2025-11-19 | 2025-02-20 | 2025-02-20 |  |  | 22 | 0 | 100 | 0 |  | X
04 | 04-3Y8904 | 3Y8904 | 04-NAP-128-/29.7 | 20.20.201130 |  | Valentine Corporation | 111 Pelican Way | San Rafael Ca 94901 | 4155720443 | 9252606460 | 324 Campus Lane, Suite T | Fairfirld, Ca, 94534 | Brar, Paramdeep | 0 | 0 | 0 | 0 | 2025-08-20 | Repair Roadway Embankment, Side Slopes And | In Napa County East Of Wragg Creek Bridge In Napa County East Of Wragg Creek Bridge In Napa County East Of Wragg Creek Bridge In N | 100 | 100 | 5689571.27 | 25586 | 5705000 | 56056 | 2025-12-31 | 2024-04-04 | 2024-04-04 |  |  | 172 | 0 | 105 | 0 |  | X
04 | 04-1X1004 | 1X1004 | 04-SCL-9-4.0/4 | 20.20.201130 |  | Qa Constructors, Inc | 850 S Van Ness Ave., Ste 35 | San Francisco, Ca 94110 | 4153407283 | 4085954019 | 1007 Knox Ave. | San Jose, Ca 95122 | Malonzo, Gene Earl | 0 | 0 | 0 | 0 | 2025-09-22 | Stabilize Slope And Remove Debris | On Rte 9 In Santa Clara Co Remove Debris, Clean Drainage System, And Regrade Slope Dir'S Order Emergency F.A. | 100 | 83 | 9911842 | 7454 | 11885000 | 55686 | 2025-12-12 | 2024-04-24 | 2024-02-19 |  |  | 80 | 0 | 50 | 0
04 | 04-1X4304 | 1X4304 | 04-SCL-9-4.5/5.5 | 20.10.201130 |  | Qa Contructors, Inc. | 800 S Van Ness, Ste 35 | San Francisco, Ca 94110 | 4153407283 | 4085954015 | 1007 Knox Ave. | San Jose, Ca 95122 | Malonzo, Gene Earl | 0 | 0 | 0 | 0 | 2025-08-29 | Repair Slide | In Santa Clara Co From 0.35 Mile South Of Saratoga Creek Br. No.37-0074 To 37-0075 Repair Slope And Roadway, Adjust Drainage Dir'S | 85 | 92 | 1795581.19 | 11611 | 1945000 | 57256 | 2025-12-21 | 2024-06-28 | 2024-03-13 |  |  | 85 | 0 | 100 | 0 |  | X
04 | 04-3G6304 | 3G6304 | 04-SCL-9-4.9/4.9 |  |  | Myers & Sons Construction, Llc | 45 Morrison Ave | Sacramento Ca 95838 | 4243356087 | 5108676009 | 1007 Knox Ave | San Jose Ca, 95122 | Le, Tuan | 5157.58 | 0 | 0 | 0 | 2025-10-20 | Cidh Piling, Structural Steel, Bridge Rail | Santa Clara County Near Saratoga At Saratoga Creek | 46 | 98 | 14683835.02 | 11925924.75 | 14870180.23 | 46064 | 2025-12-30 | 2022-11-23 | 2022-11-08 |  |  | 405 | 0 | 825 | 52 |  | X
04 | 04-0P9704 | 0P9704 | 04-SCL-17-6.2/0 |  |  | Ghilotti Construction Company,Inc. | 246 Ghilotti Avenue | Santa Rosa Ca 95407 | 4083146349 | 5107159940 | 1007 Knox Avenue | San Jose, Ca 95122 | Farsipour Naghibi, Sina | 633089.72 | 0 | 0 | 0 | 2025-10-20 | Replace Bridge Rails, Sidewalk, And Mainte | Santa Clara County In Los Gatos At Santa Cruz Avenue Undercrossing And At Main Street Overcrossing. | 72 | 74 | 3674253.29 | 4723427.46 | 4978427.46 | 56590 | 2025-01-07 | 2024-10-01 | 2024-08-30 |  |  | 130 | 0 | 180 | 0 |  | X
04 | 04-3Y2904 | 3Y2904 | 04-SCL-17-/3.5 | 20.20.201130 |  | Granite Rock Company | 5225 Hellyer Ave, Suite 220 | San Jose, Ca 95138 | 4085741400 | 5108676047 | 1007 Knox Avenue | San Jose, Ca | Nikzad, Ali | 0 | 0 | 0 | 0 | 2025-04-28 | Guardrail, Krail, Concrete Barrier | Scl 17 - Guardrail Repairs, Concrete Barriscl 17 - Guardrail Repairs, Concrete Barriscl 17 - Guardrail Repairs, Concrete Barridir' | 100 | 93 | 3805160.4 | 12279 | 4078000 | 50124 | 2025-04-30 | 2023-06-13 | 2023-04-17 |  |  | 200 | 0 | 100 | 0 |  | X
04 | 04-1X0204 | 1X0204 | 04-SCL-35-2.0/2 | 20.20.201130 |  | Redwood Engineering Construction | 416 D. Street | Redwood City, Ca 94063 | 9258192960 | 6502227241 | 2350 Page Mill Rd. | Palo Alto, Ca 94304 | Booshehri, Fred | 0 | 0 | 0 | 0 | 2024-08-19 | Repair Sinkhole | In Santa Clara Co On Route 35 Repair Sinkhole And Minor Slope Repair Dir'S Order Emergency F.A. | 58 | 65 | 279545.49 | 3563 | 430000 | 55778 | 2025-12-30 | 2024-05-10 | 2024-02-29 |  |  | 35 | 0 | 60 | 0 |  | X
04 | 04-0P9804 | 0P9804 | 04-SCL-82-11.4/26.3 |  |  | Bugler Construction, Inc. | 4847 Hopyard Rd. Suite 4-395 | Pleasanton Ca 94588 | 9254160700 | 5103857130 | 1007 Knox Ave | San Jose, Ca 95122 | Nguyen, Hung | 124878.5 | 0 | 0 | 0 | 2025-10-20 | Replace Bridge Rail, Curb Ramp, Sidewalk, | Santa Clara County At Various Locations From De La Cruz Boulevard Overcrossing To San Francisquito Creek Bridge | 93 | 94 | 7860701.84 | 8177636.5 | 8365636.5 | 55846 | 2026-03-30 | 2024-05-13 | 2024-04-04 |  |  | 210 | 0 | 225 | 0 |  | X
04 | 04-4X1304 | 4X1304 | 04-SCL-82-14.6/14.6 | 20.20.201130 |  | O.C. Jones & Sons, Inc. | 1520 Fourth Street | Berkeley, Ca 94710 | 5105263424 | 5108676009 | 1007 Knox Ave. | San Jose, Ca 95122 | Le, Tuan | 0 | 0 | 0 | 0 |  | Repair Sinkhole | On Route 82 Pm 14.6 In Santa Clara County Sinkhole And Drainage Repair Dir'S Order Emergency F.A. | 0 | 0 | 0 | 2752 | 565000 | 60131 | 2025-11-30 | 2025-10-17 | 2025-07-25 |  |  | 0 | 0 | 30 | 0
04 | 04-4J89U4 | 4J89U4 | 04-SCL-82-18.2/26.4 |  | ACNH-P082- (032)E | O.C. Jones & Sons, Inc. | 1520 Fourth Street | Berkeley Ca 94710 | 5105263424 | 5108676009 | 1007 Knox Ave | San Jose Ca 96122 | Le, Tuan | 10777.23 | 0 | 0 | 0 | 2025-10-20 | Cold Plane Ac, Rhma, Slab Repl, Curb Ramps | Santa Clara County At Various Locations From Knickerbocker Drive In Sunnyvale To San Mateo County Line In Palo Alto | 85 | 96 | 34248430.83 | 27269716.43 | 35127496.49 | 52484 | 2025-12-31 | 2023-09-13 | 2023-08-17 |  |  | 298 | 0 | 300 | 50 |  | X
04 | 04-1X2304 | 1X2304 | 04-SCL-85-/38.9 | 20.10.201352 |  | Mission Constructors, Inc. | 195 Bayshore Blvd. | San Francisco, Ca 94124 | 4152828453 | 5108676083 | 3847 Breakwater Ave. | Hayward, Ca 94545 | Baluyot, Rodelio | 17170.53 | 0 | 0 | 0 | 2025-10-20 | Replace Fence And Gates | In Counties Of Santa Clara, Alameda, And Contra Costa Replace Fence And Gates Dir'S Order Emergency F.A. | 100 | 100 | 2800662.11 | 18325 | 2955000 | 56789 | 2025-10-20 | 2024-11-21 | 2024-07-24 | 2025-10-22 |  | 160 | 0 | 160 | 0 |  | X
04 | 04-2W4504 | 2W4504 | 04-SCL-87-4.8/10.1 |  |  | Granite Rock Company | 5225 Hellyer Avenue, Suite 22 | San Jose Ca 95138 | 4085741400 | 5108676047 | 1007 Knox Ave | San Jose, Ca 95122 | Nikzad, Ali | 0 | 0 | 0 | 0 | 2025-10-20 | Masonry Block Sound Wall, Minor Concrete A | Santa Clara County In San Jose Near West Virginia Street | 100 | 99 | 1137173.75 | 1084945 | 1134945 | 55880 | 2025-10-28 | 2024-05-22 | 2024-05-02 |  |  | 100 | 0 | 100 | 0 |  | X
04 | 04-4J9104 | 4J9104 | 04-SCL-87-/6.1 |  | ACNH-P087- (034)E | O.C. Jones & Sons, Inc. | 1520 Fourth Street | Berkeley Ca 94710 | 5105263424 | 5108676047 | 7007 Knox Ave | San Jose, Ca 95122 | Nikzad, Ali | 164500.2 | 208197.52 | 360000 | 0 | 2025-10-20 | Cold Plane Ac, Paving With Rhma, Upgrade M | Santa Clara County In San Jose From Route 85/87 Separation To 0.1 Mile North Of Julian Street Undercrossing | 75 | 95 | 54942757.88 | 51342522.85 | 56386626.68 | 49524 | 2026-05-20 | 2023-05-22 | 2023-04-19 |  |  | 462 | 0 | 620 | 0 |  | X
04 | 04-3Q6004 | 3Q6004 | 04-SCL-101-.7/19.2 |  |  | Truesdell Corporation Of California, Inc. | 1310 W. 23Rd Street | Tempe Az 85282 | 6024371711 | 5107159940 | 1007 Knox Ave | San Jose Ca 95122 | Farsipour Naghibi, Sina | 0 | 0 | 0 | 0 | 2025-07-20 | Place Polyester Concrete Overlay And Remov | Santa Clara County At Various Locations | 100 | 93 | 3031019.97 | 3093093 | 3202093 | 51384 | 2025-02-07 | 2023-07-25 | 2023-06-27 |  | S | 160 | 0 | 160 | 0 |  | X
04 | 04-0X6304 | 0X6304 | 04-SCL-101-4.5/17.5 |  |  | Fbd Vanguard Construction, Inc. | 550 Greenville Road | Livermore Ca 94550 | 9252451300 | 5104969525 | 1007 Knox Ave | San Jose, Ca 95122 | Kabbani, Muhieddine | 118479.75 | 0 | 0 | 0 | 2025-10-20 | Individual Slab Replacement (Rsc). | Santa Clara County From 0.4 Mile South Of Monterey Road Undercrossing To 0.1 Mile South Of Cochrane Road Overcrossing | 45 | 100 | 1464890 | 1449740 | 1449740 | 59376 | 2025-09-09 | 2025-06-17 | 2025-05-22 |  |  | 27 | 0 | 60 | 0 |  | X
04 | 04-4J9304 | 4J9304 | 04-SCL-101-30.7/31.1 |  | ACNH-Q101- (397)E | Bortolussi & Watkin, Inc. | 77 Larkspur Street | San Rafael Ca 94901 | 4154534675 | 9166346562 | 3401 Regatta Blvd | Richmond, Ca 94804 | Cruz, Albert | 3937.87 | 0 | 0 | 0 | 2025-10-20 | Upgrade Irrigation System For | In Santa Clara County, In San Jose From 0.3 Mile South To 0.1 Mile North Of The Yereba Buena Road Uc And 0.1 Mile South Of East R | 89 | 78 | 1389383.67 | 1720610 | 1774610 | 42013 | 2026-04-10 | 2021-10-22 | 2021-09-27 |  |  | 810 | 0 | 910 | 0 |  | X
04 | 04-2Y8504 | 2Y8504 | 04-SCL-101-33.0/49 | 20.20.201130 |  | Bugler Construction Inc. | 4847 Hopyard Rd, Suite 4-395 | Pleasanton, Ca 94588 | 9254160700 | 4085954015 | 1007 Knox Ave, | San Jose, Ca | Malonzo, Gene Earl | 0 | 0 | 0 | 0 | 2024-02-03 | Repair Failed Culvert | Scl 101 At Three Locations Scl 101 At Three Locations Scl 101 At Three Locations Scl 101 At Three Locations | 94 | 93 | 1659395.38 | 15790 | 1785000 | 47924 | 2024-04-30 | 2023-03-20 | 2023-01-06 |  | S | 75 | 0 | 80 | 0 |  | X
04 | 04-1Y6204 | 1Y6204 | 04-SCL-101-38.0/38.1 | 20.80.010 |  | Pump Repair Service Co., Inc. | 405 Allan St. | San Francisco, Ca 94134 | 4154672150 | 4085954003 | 1007 Knox Ave. | San Jose, Ca 95122 | Patel, Nim | 0 | 0 | 0 | 0 | 2025-09-04 | Replace Pumps | Replace Pumps Route 101 And 10Th Street Pump Station Dir'S Order Emergency F.A. | 0 | 43 | 1454231.74 | 35475 | 3795173 | 47848 | 2025-10-15 | 2023-03-10 | 2023-01-18 |  |  | 0 | 0 | 60 | 0 |  | X
04 | 04-1J5674 | 1J5674 | 04-SCL-101-51.7/52.5 |  |  | Marina Landscape Inc. | 3707 W Garden Grove Blvd | Orange Ca 92868 | 7149396600 | 9166346562 | 3401 Regatta Blvd. | Richmond, Ca 94804 | Cruz, Albert | 20407.25 | 0 | 0 | 0 | 2025-10-20 | Highway Planting And Irrigation Systems. | Santa Clara And San Mateo Counties At Various Locations From 0.3 Mile South Of Oregon Expressway Overcrossing To 0.3 Milesouth Of | 0 | 0 | 5626475.21 | 5958858.5 | 6318858.5 | 54286 | 2028-03-27 | 2023-11-30 | 2023-10-25 |  |  | 277 | 0 | 1000 | 0 | X | X
04 | 04-2Y7404 | 2Y7404 | 04-SCL-152-12.6/12.6 | 20.20.201130 |  | Absl Construction | 29393 Pacific St. | Hayward, Ca 94544 |  | 4085954019 | 1007 Knox Ave., | San Jose, Ca | Malonzo, Gene Earl | 0 | 0 | 0 | 0 | 2025-05-30 | Remove Silt/Sediment From Creek, Clear Cul | Scl 152 @ Johnson Creek - Blocked Culverts And Channel | 98 | 91 | 2060828.1 | 11830 | 2264000 | 47385 | 2025-06-30 | 2023-02-14 | 2022-12-23 |  |  | 59 | 0 | 60 | 0 |  | X
04 | 04-0Q05U4 | 0Q05U4 | 04-SCL-152-16.8/23.3 |  |  | Pacific Infrastructure Construction, Llc | 871 Cotting Court Ste A | Vacaville Ca 95688 | 7074493604 | 4085954015 | 1007 Knox Ave. | San Jose, Ca 95122 | Malonzo, Gene Earl | 36335 | 0 | 0 | 0 | 2025-10-20 | Excavation, Hma, Drainage, Rsp, Signing, M | Santa Clara County Near Gilroy At Various Locations From 1.9 Miles East Of Bloomfield Avenue To 0.1 Mile West Of Casade Fruta Unde | 82 | 99 | 5159645.35 | 5130777.7 | 5602568.55 | 56808 | 2025-11-19 | 2024-12-03 | 2024-11-06 |  |  | 98 | 0 | 120 | 0 |  | X
04 | 04-2Y5404 | 2Y5404 | 04-SCL-237-1.5/6.4 |  |  | Granite Rock Company | 5225 Hellyer Avenue, Suite 22 | San Jose Ca 95138 | 4085741415 | 5104069696 | 1007 Knox Ave | San Jose, Ca 95122 | Ngo, Hung T | 371440.3 | 0 | 0 | 0 | 2025-10-20 | Cold Plane Ac Pavement, Place Hma (A), & P | Santa Clara County On Route 237 At Variouslocations From Middlefield Road Undercrossing To Guadalupe River Bridge And On Route 88 | 85 | 99 | 1743463.9 | 1686420 | 1686420 | 59199 | 2025-12-15 | 2025-06-10 | 2025-05-06 |  |  | 34 | 0 | 40 | 0 |  | X
04 | 04-3X5204 | 3X5204 | 04-SCL-237-9.1/9.1 | 20.20.201130 |  | Absl Construction | 29393 Pacific St | Hayward, Ca 94544 | 5107270900 | 4085954003 | 1007 Knox Ave, | San Jose, Ca 95122-2124 | Patel, Nim | 0 | 0 | 0 | 0 | 2025-06-27 | Pavement And Slope Repair | Eb Mccarthy Blvd Onramp | 0 | 44 | 499186.77 | 7219 | 1132000 | 58415 | 2025-09-30 | 2025-05-02 | 2025-05-02 |  |  | 0 | 0 | 40 | 0 |  | X
04 | 04-0Y5004 | 0Y5004 | 04-SCL-280-2.9/2.9 | 20.20.201130 |  | O.C. Jones & Sons, Inc. | 1520 Fourth St. | Berkeley, Ca 94710 | 5105263424 | 4085954003 | 1007 Knox Ave. | San Jose, Ca 95122 | Patel, Nim | 0 | 0 | 0 | 0 | 2024-09-09 | Repair/Replace Damaged Pump | In San Jose, Santa Clara County, Near Route 87 Repair/Replace Damaged Pump Dir'S Order Emergency F.A. | 0 | 86 | 1185457.2 | 6095 | 2185000 | 42188 | 2025-06-30 | 2022-03-03 | 2022-01-15 |  |  | 0 | 0 | 150 | 0 |  | X
04 | 04-3Y0004 | 3Y0004 | 04-SCL-280-4.6/4.6 | 20.20.201130 |  | Pump Repair Service Co., Inc. | Po Box 34327 | San Francisco, Ca 94134 | 4154672150 | 4085954003 | 1007 Knox Ave | San Jose Ca | Patel, Nim | 0 | 0 | 0 | 0 | 2025-10-10 | Repair And Replace Damaged Pumps | Scl 280 At Winchester Blvd - Groundwater Pump Repair Dir'S Order Emergency F.A. | 0 | 25 | 691724.44 | 32250 | 2810000 | 48584 | 2025-12-30 | 2023-04-17 | 2023-01-12 |  |  | 0 | 0 | 100 | 0 |  | X
04 | 04-0X2604 | 0X2604 | 04-SCL-280-/3.8 | 20.10.201131 |  | Pump Repair Service Co., Inc. | 405 Allan St | San Francisco, Ca 94134 | 4154672150 | 5104069696 | 1007 Knox Ave. | San Francisco, Ca 94134 | Ngo, Hung T | 0 | 0 | 0 | 0 | 2025-08-14 | Repair/Replace Pumps | Southwest Pump Plant Replace Existing Pumps Including Mechanical And Electrical Elements Dir'S Order Emergency F.A. | 0 | 24 | 347448.74 | 18150 | 1450000 | 56418 | 2025-12-31 | 2024-07-12 | 2024-07-12 |  |  | 0 | 0 | 150 | 0 |  | X
04 | 04-1Q4604 | 1Q4604 | 04-SCL-280-/2.7 |  | ACIM-2801- (992)E | O.C. Jones & Sons, Inc. | 1520 Fourth Street | Berkeley Ca 94710 | 5108093490 | 4085954003 | 1007 Knox Ave. | San Jose, Ca 96122 | Patel, Nim | 4384928.5 | 0 | 0 | 93250 | 2025-10-20 | Rhma-G Surfacing And Construct Bridge Appr | Santa Clara County In San Jose From Route 280/680/101 Separation To 0.2 Mile West Ofbird Avenue Overcrossing | 92 | 73 | 15430201.47 | 20793388.4 | 21106388.4 | 55845 | 2025-12-31 | 2024-06-17 | 2024-05-02 |  |  | 229 | 0 | 250 | 0
04 | 04-4X0204 | 4X0204 | 04-SCL-880-1.7/1.9 | 20.20.201130 |  | Absl Construction | 29393 Pacific St. | Hayward, Ca 94544 | 5107270900 | 5104069696 | 1007 Knox Ave. | San Jose, Ca 95122 | Ngo, Hung T | 0 | 0 | 0 | 0 | 2025-10-31 | Repair Sinkhole | On Rte 880 In Santa Clara County At The Alameda Nb Offramp And Sb Onramp Repair Sinkhole, Settlement & Drainage Dir'S Order Emerge | 0 | 13 | 227827.36 | 10230 | 1692500 | 59715 | 2026-06-30 | 2025-08-11 | 2025-06-03 |  |  | 0 | 0 | 40 | 0 |  | X
04 | 04-0X9104 | 0X9104 | 04-SF-80-3.9/4.5 | 20.20.201130 |  | Yerba Buena Engineering & Construction, Inc. | 1340 Egbert Ave. | San Francisco, Ca 94124 | 4158224400 | 5108676069 | 585 Linda Mar Blvd. | Pacifica, Ca 94044 | Sihra, Chetan | 0 | 0 | 0 | 0 | 2025-06-01 | Repair Bridge Railing | Replace Damaged Concrete Barrier And Tubular Railing On Highways 80 And 101 Dir'S Order Emergency F.A. | 82 | 91 | 2679191.21 | 17937 | 2960000 | 55681 | 2025-12-31 | 2024-04-17 | 2024-04-02 |  |  | 49 | 0 | 60 | 0 |  | X
04 | 04-1Y7204 | 1Y7204 | 04-SF-80-5.7/7.7 |  |  | Golden State Bridge, Inc. | 3701 Mallard Drive | Benicia Ca 94510 | 9253728000 | 5108674545 | 575 Linda Mar Blvd. | Pacifica, Ca 94044 | Larwin, Thomas | 723283.9 | 0 | 0 | 350000 | 2025-10-20 | Structural Concrete, Bridge (Rsc) & Joint | The City And County Of San Francisco At Various Locations From 0.1 Mile East Of Fremont Street Off-Ramp To 0.2 Mile West Of Yerba | 10 | 19 | 2690867.52 | 14148449 | 14316392.95 | 58738 | 2027-05-20 | 2025-06-03 | 2025-05-16 |  |  | 46 | 0 | 450 | 0 |  | X
04 | 04-3G4444 | 3G4444 | 04-SF-80-5.7/7.5 |  |  | American Bridge Company | 1000 American Bridge Way | Coraopolis Pa 15108 | 4125779256 | 5102217437 | 585 Linda Mar Blvd | Pacifica, Ca 94044 | Larwin, Thomas | 0 | 0 | 0 | 0 | 2025-09-08 | Repair Main Cable And Replace Suspender Ro | The City And County Of San Francisco At Various Locations From 0.1 Mile North Of San Francisco Anchorage To 0.1 Mile South Of Yerb | 100 | 100 | 20790091.12 | 19647888 | 20849682.89 | 55165 | 2025-09-08 | 2024-02-09 | 2023-12-28 | 2025-09-24 |  | 193 | 0 | 180 | 13 |  | X
04 | 04-4W9504 | 4W9504 | 04-SF-80-/7.8 | 20.20.201130 |  | Perry Electric Incorporated | 130 Murwood Court | Walnut Creek Ca 94596 | 9257662778 | 5108674545 | 585 Linda Mar Blvd | Pacifica Ca 94044 | Larwin, Thomas | 0 | 0 | 0 | 0 | 2025-10-09 | Replace Failed Power Source | Sfobb Yerba Buena Island Dir S Order Emergency F.A. | 100 | 93 | 4238384.89 | 11040 | 4552000 | 42409 | 2024-04-30 | 2022-05-10 | 2022-02-07 |  |  | 790 | 0 | 160 | 0 |  | X
04 | 04-2Q4604 | 2Q4604 | 04-SF-101-.8/0 |  |  | Disney Construction, Inc. | 533 Airport Blvd., Suite 120 | Burlingame Ca 94010 | 6502599545 | 5107156644 | 585 Linda Mar Blvd | Pacifica, Ca 94044 | Koos, Charles | 58835.5 | 0 | 0 | 0 | 2025-10-20 | Bridge Rail Replacement. | The City And County Of San Francisco At Third Street Undercrossing And At Twenty Third Street Overcrossing | 95 | 98 | 5409253.99 | 4977333.33 | 5325403.82 | 56475 | 2025-11-30 | 2024-09-17 | 2024-08-28 |  |  | 176 | 0 | 175 | 10 |  | X
04 | 04-1Y5004 | 1Y5004 | 04-SF-280-2.7/4.2 |  |  | Mccuen Construction, Inc. | 3269 Swetzer Road | Loomis Ca 95650 | 9166527824 | 5109088819 | 585 Linda Mar Blvd. | Pacifica, Ca 94044 | Kardavani, Kayvan | 0 | 0 | 0 | 0 | 2025-09-20 | Place Polyester Concrete Overlay, And Repl | The City And County Of San Francisco At Various Locations From Monterey Boulevard On-Ramp Overcrossing To Route 280/101 Separation | 99 | 94 | 5400266.43 | 5386262.78 | 5651562.78 | 56158 | 2025-09-30 | 2024-07-12 | 2024-06-17 |  |  | 89 | 0 | 90 | 0 |  | X
04 | 04-1W1404 | 1W1404 | 04-SF-280-6.6/T7.2 |  |  | Golden State Bridge, Inc. | 3701 Mallard Drive | Benicia Ca 94510 | 9253728000 | 5107156644 | 555 Linda Mar Blvd. | Pacifica, Ca 94044 | Koos, Charles | 13420 | 0 | 0 | 0 | 2025-10-20 | Repair Concrete Bridge, Drill And Bond Dow | The City And County Of San Francisco From 25Th Street To 0.8 Mile North Of Mariposa Street Separation | 100 | 94 | 3689785.6 | 3630251 | 3994251 | 50405 | 2025-11-30 | 2023-06-08 | 2023-05-18 |  |  | 140 | 0 | 140 | 0 |  | X
04 | 04-4X1404 | 4X1404 | 04-SF-280-6.6/7.2 | 20.10.201130 |  | Golden State Bridge, Inc. | 3701 Mallard Drive | Benicia, Ca 94510 | 9253728008 | 5107156644 | 585 Linda Mar Blvd | Pacifica, Ca 94044 | Koos, Charles | 0 | 0 | 0 | 0 | 2025-10-02 | China Basin Viaduct Girder Replacement | Replace Cracked Girder At China Basin Viaduct (Bridge No. 34-0100) Dir'S Order Emergency F.A. | 29 | 26 | 1472763.76 | 30973 | 5747000 | 59895 | 2026-03-03 | 2025-08-06 | 2025-07-14 |  |  | 52 | 0 | 180 | 0 |  | X
04 | 04-2X0704 | 2X0704 | 04-SF0-80-8.3/8.3 | 20.20.201130 |  | Usa Hoist Company, Inc. | 175 Prairie Lake, | East Dundee, Il 60118 |  | 5108674545 | 3401 Regatta Blvd, | Richmond, Ca 94804-4594 | Larwin, Thomas | 0 | 0 | 0 | 0 |  | Repair Elevator System | Sfobb East Span Sfobb East Span | 0 | 0 | 0 | 22195 | 2975000 | 57387 | 2025-09-30 | 2025-03-20 | 2024-12-02 |  |  | 0 | 0 | 200 | 0
04 | 04-2K8804 | 2K8804 | 04-SM-1-26.3/47.3 |  |  | Norcal General Construction Corporation | 1950 Majestic Ct | San Jose Ca 95132 | 4088860335 | 5108676069 | 585 Linda Mar Blvd | Pacifica, Ca 94044 | Sihra, Chetan | 395808 | 0 | 0 | 23000 | 2025-10-20 | Traffic Monitoring Station System. | San Mateo County At Various Locations | 67 | 69 | 651231.2 | 947422 | 947422 | 54164 | 2023-12-31 | 2023-08-11 | 2023-06-26 |  | S | 80 | 0 | 120 | 0 |  | X
04 | 04-0Q1304 | 0Q1304 | 04-SM-1-27.5/34.8 |  | ACNH-P001- (707)E | O.C. Jones & Sons, Inc. | 1520 Fourth Street | Berkeley Ca 94710 | 5109099601 | 5108676069 | 585 Linda Mar Blvd | Pacifica, Ca 94044 | Sihra, Chetan | 0 | 0 | 0 | 0 |  | Cold Plane Ac, Place Hma, Modify Signal An | San Mateo County In And Near Half Moon Bayfrom Wavecrest Road To 0.1 Mile South Of Marine Boulevard | 0 | 0 | 0 | 20518678.3 | 20568678.3 | 59639 | 2026-12-11 | 2025-07-29 | 2025-07-02 |  | S | 0 | 0 | 300 | 0
04 | 04-2J7904 | 2J7904 | 04-SM-1-28.9/0 |  |  | Disney Construction, Inc. | 533 Airport Blvd., Suite 120 | Burlingame Ca 94010 | 4156807752 | 6502227241 | 2350 Page Mill Rd | Palo Alto, Ca 94304 | Booshehri, Fred | 860266.5 | 0 | 0 | 0 | 2025-10-20 | Channel Excavation And Partially Grouted R | San Mateo County In Half Moon Bay On Route1 At Pilarcitos Creek Bridge And Near La Honda On Route 84 At San Gregorio Creek Bridge | 23 | 89 | 3709167.39 | 3777333 | 4012625.89 | 56134 | 2026-12-31 | 2024-07-24 | 2024-06-21 |  |  | 86 | 0 | 380 | 0 |  | X
04 | 04-0X0804 | 0X0804 | 04-SM-1-32.2/32.2 | 20.20.201130 |  | Yerba Buena Engineering & Construction, Inc. | 1340 Egbert Avenue | San Francisco, Ca 94124 | 4158224400 | 9166219754 | 585 Linda Mar Blvd | Pacifica, Ca 94044 | Marabeh, Hisham | 0 | 0 | 0 | 0 | 2025-10-01 | Replace Rsp, Pathway, And Stair | Remove And Replace Rsp, Concrete Stairway, Ac Pathway On Surfer'S Beach Dir'S Order Emergency F.A. | 92 | 42 | 761761.99 | 11044 | 1795000 | 54984 | 2025-12-31 | 2024-01-25 | 2023-09-04 |  |  | 55 | 0 | 60 | 0
04 | 04-3X5104 | 3X5104 | 04-SM-1-47.8/47.8 | 20.20.201130 |  | Santamaria Concrete Inc. | 785 Lincoln Ave | San Jose, Ca 95126 | 4086344209 | 6502227516 | 585 Linda Mar Blvd, | Pacifica, Ca 94044 | Ebrahimi, Mohammad | 0 | 0 | 0 | 0 |  | Repair Slipout | Near Sullivan Avenue Repair Slipout | 0 | 0 | 0 | 19560 | 637000 | 59656 | 2025-11-19 | 2025-08-11 | 2025-04-03 |  |  | 0 | 0 | 40 | 0
04 | 04-0X0004 | 0X0004 | 04-SM-35-1.7/1.7 | 20.20.201130 |  | Redwood Engineering Construction | 416 D Street | Redwood City, Ca 94063 | 9258192960 | 6502227241 | 2350 Page Mill Rd. | Palo Alto, Ca 94304 | Booshehri, Fred | 0 | 0 | 0 | 0 | 2024-07-05 | Drainage And Rsp | 0.2 Mile South Of Page Mill Road Drainage And Rsp Dir'S Order Emergency F.A. | 100 | 74 | 1409184.44 | 12483 | 1903000 | 52784 | 2025-12-15 | 2023-09-25 | 2023-08-07 |  |  | 99 | 0 | 60 | 0
04 | 04-3Y7604 | 3Y7604 | 04-SM-35-8.7/8.7 | 20.20.201130 |  | Redwood Engineering Construction | 416 D Street | Redwood City Ca 94083 |  | 6502227241 | 2350 Page Mill Road | Palo Alto Ca 94304 | Booshehri, Fred | 0 | 0 | 0 | 0 | 2025-09-21 | Repair Sinkhole | Sm-35 In Portola Valley Sm-35 In Portola Valley Sm-35 In Portola Valley Dir'S Order Emergency F.A. | 100 | 52 | 2733412.9 | 29679 | 5252574 | 50965 | 2025-12-30 | 2023-07-07 | 2023-05-05 |  |  | 152 | 0 | 100 | 0
04 | 04-1X9604 | 1X9604 | 04-SM-82-9.2/9.2 | 20.10.201130 |  | Santamaria Concrete, Inc. | 785 Lincoln Ave. | San Jose, Ca 95126 | 4086344209 | 5104216332 | 1700 S. Amphlett Blvd. | San Mateo, Ca 94402 | Moe, Alvin | 0 | 0 | 0 | 0 | 2025-08-25 | Repair Sinkhole | In San Maeo County Route 82 Frontage Road Repair Sinkhole Dir'S Order Emergency F.A. | 63 | 61 | 308236.29 | 15570 | 504000 | 57115 | 2025-07-18 | 2024-12-09 | 2024-08-29 |  |  | 25 | 0 | 40 | 0 |  | X
04 | 04-1Q5304 | 1Q5304 | 04-SM-82-9.3/0 |  |  | American Civil Constructors West Coast, Llc Dba Acc West Coast | 2990 Bay Vista Court, Suite D | Benicia Ca 94510 | 7077468028 | 5103856850 | 1700 S Amphlett Blvd. | San Mateo, Ca 94402 | Aung, Phone | 101148 | 0 | 0 | 0 | 2025-10-20 | Replace Bridge Railing, Construct Ada Curb | San Mateo County In San Mateo At Hillsdaleboulevard Overcrossing | 87 | 84 | 1351256.54 | 1343000 | 1587516.99 | 57261 | 2026-07-30 | 2025-02-12 | 2025-01-13 |  |  | 111 | 0 | 100 | 27 |  | X
04 | 04-2Y5604 | 2Y5604 | 04-SM-82-9.6/11.8 |  |  | Fbd Vanguard Construction, Inc | 550 Greenville Road | Livermore Ca 94550 | 9252451300 | 6503334036 | 1700 S Amphlett Blvd | San Mateo, Ca 94402 | Inori, Douglas | 0 | 0 | 0 | 0 | 2025-10-20 | Individual Slab Replacement (Rsc). | San Mateo County In San Mateo From 0.1 Mile North Of Hillsdale Boulevard Overcrossing To Second Avenue | 100 | 93 | 1058774.33 | 834700 | 1135760 | 56066 | 2025-08-29 | 2024-04-29 | 2024-04-04 |  |  | 100 | 0 | 40 | 0 |  | X
04 | 04-3Y5004 | 3Y5004 | 04-SM-84-17.9/17.9 | 20.20.201130 |  | Joseph J. Albanese, Inc | 851 Martin Avenue | Santa Clara Ca 95050 | 4087575700 | 6502227241 | 2350 Page Mill Road | Palo Alto Ca 94304 | Booshehri, Fred | 0 | 0 | 0 | 0 | 2024-12-20 | Repair Slope And Drainage Systems And Cons | In San Mateo County On Highway 84- Pm 17.9In San Mateo County On Highway 84- Pm 17.9In San Mateo County On Highway 84- Pm 17.9Dir' | 100 | 89 | 10114678.11 | 37163 | 11365648.94 | 49344 | 2025-12-30 | 2023-05-11 | 2023-03-10 |  |  | 432 | 0 | 150 | 0 |  | X
04 | 04-2Y5204 | 2Y5204 | 04-SM-84-27.7/29.2 |  |  | O.C. Jones & Sons, Inc. | 1520 Fourth Street | Berkeley Ca 94710 | 5105263424 | 2792342197 | 1700 S Amphlett Blvd | San Mateo, Ca 94402 | Malonzo, Ethan | 1916267 | 0 | 0 | 140000 | 2025-10-20 | Cold Plane Ac Pavement And Overlay With Rh | San Mateo County In Menlo Park On Route 84From Route 114 To Dumbarton Bridge And On Willow Road At Route 114/101 Separation | 18 | 72 | 2056267 | 2848474.5 | 2848474.5 | 59255 | 2026-01-02 | 2025-07-03 | 2025-06-16 |  |  | 11 | 0 | 60 | 0 |  | X
04 | 04-0X3304 | 0X3304 | 04-SM-84-28.0/2 | 20.20.201130 |  | Monterey Mechanical Co. | 8275 San Leandro St. | Oakland, Ca 94621 | 5106323173 | 6502227241 | 2350 Page Mill Rd. | Palo Alto, Ca 94304 | Booshehri, Fred | 0 | 0 | 0 | 0 | 2024-12-25 | Repair/Replace Pumps | Ravenswood Pump Plant, Menlo Park Repair/Replace Pumps Dir'S Order Emergency F.A. | 4 | 1 | 17152.9 | 9207 | 1280000 | 55722 | 2025-12-31 | 2024-05-01 | 2024-04-02 |  |  | 3 | 0 | 80 | 0 |  | X
04 | 04-3X6404 | 3X6404 | 04-SM-92-4.0/5 | 20.20.201130 |  | Granite Rock Company | 5225 Hellyer Ave, Suite 220, | San Jose, Ca 95138 | 8317682000 | 5103931593 | 1700 So.Amphlett, 101 & 103, | San Mateo, Ca 94402-1986 | Lam, Peter | 0 | 0 | 0 | 0 | 2025-10-23 | Repair Pavement | West Of Route 35, Remove Asphalt Concrete Pavement, Hot Mix Asphalt, Hma Dike, Install Underdrain, Lined V-Ditch, Trafficcontrol S | 50 | 26 | 361111.97 | 4152 | 1369000 | 59462 | 2026-03-02 | 2025-07-22 | 2025-06-16 |  |  | 30 | 0 | 60 | 0 |  | X
04 | 04-2Q8004 | 2Q8004 | 04-SM-92-12.0/13.1 |  | CPFL-6204- (136)000 | Gordon N. Ball, Inc. | 1777 Oakland Blvd. Ste 300 | Walnut Creek, Ca 94596 | 9258385675 | 5103931593 | 1700 South Amphlett Blvd | San Mateo, Ca 94402 | Lam, Peter | 2688603.75 | 10706.95 | 0 | 547000 | 2025-10-20 | Bridge Widening, Hma, Curb Ramp, Conc Barr | San Mateo County In Foster City And San Mateo On Route 92 From 0.2 Mile East Of South Delaware Street Undercrossing To 0.3Mile Wes | 24 | 36 | 10303248.27 | 27715570.55 | 28441625.55 | 57316 | 2027-04-30 | 2025-03-13 | 2025-01-22 |  |  | 122 | 0 | 500 | 0 |  | X
04 | 04-1X2204 | 1X2204 | 04-SM-92-/13.6 | 20.10.201352 |  | Norcal General Construction Co | 751 Mabury Rd. | San Jose, Ca 95133 | 4088860335 | 5103856741 | 1700 South Amphlett Blvd,#101 | San Mateo, Ca 94402 | Chen, Roy | 0 | 0 | 0 | 0 |  | Replace Fence And Gates | In San Mateo County And San Francisco County Replace Fence And Gates Dir'S Order Emergency F.A. | 0 | 0 | 0 | 34250 | 1935000 | 56434 | 2025-06-29 | 2024-08-15 | 2024-08-15 |  |  | 0 | 0 | 120 | 0
04 | 04-0X6504 | 0X6504 | 04-SM-92-/.5 |  |  | O.C. Jones & Sons, Inc. | 1520 Fourth Street | Berkeley Ca 94710 | 5105263424 | 2792342197 | 1700 S Amphlett Blvd. | San Mateo, Ca 94402 | Malonzo, Ethan | 0 | 0 | 0 | 0 |  | Hm-1 Cold Plane Ac Pavement, Place Hma (A) | In San Mateo County In And Near Half Moon Bay From Route 1 To 0.3 Mile East Of Main Street. | 0 | 0 | 0 | 751123.55 | 751123.55 | 60119 | 2025-12-11 | 2025-09-26 | 2025-06-04 |  |  | 0 | 0 | 30 | 0
04 | 04-1Q8204 | 1Q8204 | 04-SM-101-2.5/2.6 |  |  | Fbd Vanguard Construction, Inc. | 550 Greenville Road | Livermore Ca 94550 | 9253375169 | 5103856818 | 585 Linda Mar Blvd. | Pacifica, Ca 94044 | Lui, Patrick | 26094.6 | 0 | 0 | 0 | 2025-10-20 | Replace Concrete Pavement Slabs And Upgrad | San Mateo County And The City And County Of San Francisco At Various Locations Fromharney Way To Market Street | 0 | 0 | 26094.6 | 92222000 | 92222000 | 60056 | 2028-03-07 | 2025-08-28 | 2025-08-20 |  |  | 1 | 0 | 590 | 0 |  | X
04 | 04-2J7304 | 2J7304 | 04-SM-101-6.9/7.6 |  | ACNH-Q101- (415)E | Myers & Sons Construction, Llc | 45 Morrison Ave | Sacramento Ca 95838 | 9162086416 | 5103931593 | 1700 So. Amphlett Blvd, Ste101 | San Mateo, Ca 94402 | Lam, Peter | 9955 | 2587.35 | 0 | 0 | 2025-10-20 | Replace Box Culvert Bridge. | San Mateo County In Redwood City And San Carlos From 0.3 Mile South Of Cordilleras Creek Bridge To 0.1 Mile South Of Pulgas Creek | 100 | 94 | 21548889.22 | 16195350.3 | 22321959.09 | 49645 | 2025-03-15 | 2023-04-07 | 2023-03-20 |  |  | 333 | 0 | 275 | 0 |  | X
04 | 04-0X0604 | 0X0604 | 04-SM-101-9.1/9.1 | 20.20.201130 |  | Sierra Mountain Construction, Inc. | 19500 Nugget Blvd. | Sonora, Ca 95370 | 4153087260 | 5104216332 | 1700 S Amphlett Blvd | San Mateo, Ca 94402 | Moe, Alvin | 0 | 0 | 0 | 0 | 2025-10-23 | Creek Clearing | In San Mateo County In Belmont At Belmont Creek Culvert Debris And Sidement Removal Dir'S Order Emergency F.A. | 80 | 65 | 1421950.41 | 14121 | 2176000 | 55804 | 2025-12-31 | 2024-05-14 | 2023-08-31 |  |  | 80 | 0 | 100 | 0 |  | X
04 | 04-1Q5814 | 1Q5814 | 04-SM-101-/6.5 |  | ACNH-Q101- (422)E | Bay Cities Paving & Grading, Inc. | 1450 Civic Ct Bldg B #400 | Concord Ca 94520 | 9256876666 | 2792342197 | 1700 S Amphlett Blvd. | San Mateo, Ca 94402 | Malonzo, Ethan | -333895.01 | 578346.62 | -189245.5 | 0 | 2025-10-20 | Cold Plane Ac Pvmt, Rhma Overlay, And Conc | San Mateo County From San Mateo County Line In East Palo Alto To Whipple Avenue In Redwood City | 71 | 97 | 41517223.31 | 37271945.19 | 41981931.98 | 55184 | 2025-11-30 | 2024-01-12 | 2024-01-10 |  |  | 177 | 0 | 250 | 0 |  | X
04 | 04-1X2404 | 1X2404 | 04-SM-101-/6.2 | 20.10.201131 |  | Golden State Bridge, Inc. | 3701 Mallard Dr. | Benicia, Ca 94510 | 9253728000 | 5108676052 | 1700 South Amphlett Blvd., Suite 101 | San Mateo, Ca 94402 | Lam, Peter | 0 | 0 | 0 | 0 | 2025-10-23 | Bridge Repair | Redwood Creek Bridge No. 35-0145 Repair Damaged Bridge Colums, Abutment, Bent Cap & Soffit, & Mitigate Local Scour Dir'S Order Eme | 25 | 0 | 4779.5 | 8712 | 1351500 | 56138 | 2025-05-15 | 2024-07-17 | 2024-06-14 |  |  | 10 | 0 | 40 | 0 |  | X
04 | 04-1X6604 | 1X6604 | 04-SM-280-10.2/10.2 | 20.10.201130 |  | Ghilotti Construction Company,Inc. | 246 Ghilotti Ave. | Santa Rosa, Ca 95407 | 7075851221 | 5103931593 | 1700 S. Amphlett Blvd. Ste 101 | San Mateo, Ca 94402 | Lam, Peter | 0 | 0 | 0 | 0 | 2025-04-11 | Replace Culvert | In San Mateo Co. On Route 280 Nb In The City Of Belmont Replace Culvert Dir'S Order Emergency F.A. | 75 | 80 | 803949.17 | 6078 | 1010500 | 56555 | 2025-04-30 | 2024-09-17 | 2024-07-05 |  |  | 30 | 0 | 40 | 0 |  | X
04 | 04-3Y0804 | 3Y0804 | 04-SM-280-10.2/10.2 | 20.20.201130 |  | Aqua Sierra Controls, Inc | 13265 Bill Francis Drive | Auburn, Ca 95603 | 5308233241 | 6503334036 | 1700 S. Amphlett Blvd | San Mateo, Ca | Inori, Douglas | 0 | 0 | 0 | 0 | 2025-08-07 | Repair Pumps | Sm 280-Canada Pump Station Rehab- Prevent Detention Basin Overflow Into Other Reservsm 280-Canada Pump Station Rehab- Prevent Dir' | 100 | 98 | 1086721.05 | 17663 | 1090286.29 | 48304 | 2025-09-30 | 2023-04-06 | 2023-01-14 |  |  | 180 | 0 | 100 | 0 |  | X
04 | 04-2X0104 | 2X0104 | 04-SM-280-232.0/23.2 | 20.20.201130 |  | Disney Construction Inc | 533 Airport Blvd, #120, | Burlingame, Ca 94010 |  | 5108676069 | 585 Linda Mar Blvd, | Pacifica, Ca 94044 | Sihra, Chetan | 0 | 0 | 0 | 0 | 2025-08-11 | Along Route 280 Near King Drive | Along Route 280 Near King Drive | 75 | 77 | 403604.33 | 3840 | 525000 | 56791 | 2025-12-31 | 2024-12-05 | 2024-10-03 | 2025-10-15 |  | 30 | 0 | 40 | 0 |  | X
04 | 04-4J8504 | 4J8504 | 04-SM-280-/21 |  | ACIM-2801- (999)E | Golden State Bridge, Inc. | 3701 Mallard Drive | Benicia Ca 94510 | 9253728000 | 5103931593 | 1700 S Amphlette Blvd | San Mateo Ca 94402 | Lam, Peter | 0 | 105044.62 | 0 | 0 | 2025-10-20 | Install Column Casings, Conc Barriers And | San Mateo County At Various Locations Fromalpine Road Undercrossing To Route 280/380Separation | 78 | 96 | 10693800.71 | 9787756.68 | 10896106.45 | 52685 | 2025-11-07 | 2023-04-25 | 2023-04-18 |  |  | 436 | 0 | 550 | 12 |  | X
04 | 04-3Y4104 | 3Y4104 | 04-SM-680-/16.5 | 20.20.201130 |  | Golden State Bridge, Inc. | 3701 Mallard Drive | Benicia Ca 94510 | 9253728000 | 5108133347 | 3401 Regatta Blvd | Richmond, Ca 948041650 | Atako, Kingston | 0 | 0 | 0 | 0 | 2025-10-24 | Perform Non-Destructive Testing On Butt We | In Cc, Sol And Sm Counties - Routes 680, 8In Cc, Sol And Sm Counties - Routes 680, 8In Cc, Sol And Sm Counties - Routes 680, 8Dir' | 91 | 93 | 23748406.98 | 63786 | 25405000 | 51185 | 2025-12-31 | 2023-07-17 | 2023-05-19 |  |  | 518 | 0 | 200 | 369 |  | X
04 | 04-0A53T4 | 0A53T4 | 04-SOL-12-1.8/L3.2 |  |  | Kiewit Infrastructure West Co. | 4650 Business Center Drive | Fairfield Ca 94534 | 7074397300 | 9252505595 | 324 Campus Lane, Suite T | Fairfield, Ca 94534 | Isada, Darren | 5164190.53 | 0 | 0 | 3880511.34 | 2025-10-20 | I-80 Wb Truck Scales | Solano County In And Near Fairfield On Route 12 From The 80/12 East Junction To 0.9 Mile East Of Chadbourne Road Undercrossing And | 6 | 9 | 14449024.41 | 152000000 | 152424156.96 | 59176 | 2029-01-31 | 2025-06-20 | 2025-06-20 |  |  | 48 | 0 | 865 | 0 |  | X
04 | 04-0W1104 | 0W1104 | 04-SOL-12-3.2/7.5 |  | SNHG-P012- (131)E | Hoseley Corporation | 96F Pier Admin Building Ste20 | San Francisco Ca 94124 | 4154048997 | 5108676033 | 324 Campus Lane, Suite T | Fiarfield, Ca 94534 | Lane, Isaiah | 47700 | 0 | 6927.8 | 0 | 2025-10-20 | Install Mgs And Modify Signal And Lighting | Solano County In And Near Suisun City At Various Locations From 0.2 Mile East Of Beck Avenue To 0.2 Mile West Of Walters Road | 100 | 97 | 2343815.25 | 2323604 | 2415531.8 | 56240 | 2025-07-21 | 2024-08-16 | 2024-07-25 |  |  | 110 | 0 | 110 | 0 |  | X
04 | 04-2Q5504 | 2Q5504 | 04-SOL-12-7.7/14.1 |  | ACNH-P012- (132)E | Bay Cities Paving & Grading, Inc. | 1450 Civic Ct Bldg B #400 | Concord Ca 94520 | 9256876666 | 5108071407 | 324 Campus Lane, Ste T | Fairfield, Ca 94533 | Sarwary, Asadullah | 0 | 0 | 12884.6 | 0 | 2025-10-20 | Rhma Overlay, Replace Culverts, Bridge Rai | Solano County Near Suisun City From 0.2 Mile East Of Lawler Ranch Parkway To 0.5 Mile East Of Shiloh Road | 24 | 30 | 5840839.85 | 18916084.55 | 19372244.99 | 57262 | 2026-11-09 | 2025-03-06 | 2025-02-14 |  |  | 85 | 0 | 350 | 0 |  | X
04 | 04-1X3604 | 1X3604 | 04-SOL-28-/9.8 | 20.20.201130 |  | Redgwick Construction Co. | 21 Hegenberger Court, | Oakland, Ca 94621 | 5107921727 | 5107738499 | 324 Campus Lane,Suite T | Fairfield, Ca 94534 | Tran, Quang | 0 | 0 | 0 | 0 | 2025-11-03 | Replace/Improve Existing Fences And Gates | In Solano County Vallejo, Fairfield And Dixon Maintenance Stations And Dixon Maintenance Stations | 31 | 53 | 1108441.39 | 13332 | 2107000 | 56607 | 2025-12-31 | 2024-11-04 | 2024-08-27 |  |  | 37 | 0 | 120 | 0 |  | X
04 | 04-2Q5204 | 2Q5204 | 04-SOL-29-/6 |  | ACNH-P029- (158)E | Bay Cities Paving & Grading, Inc. | 1450 Civic Ct Bldg B #400 | Concord Ca 94520 | 9256876666 | 5107738499 | 324 Campus Lane Suite T | Fairfield, Ca 94534 | Tran, Quang | 0 | 0 | 0 | 0 |  | Hma Pvmt, Mod Drainage, Signals, Sidewalks | Solano County In Vallejo From 0.2 Mile North Of Route 80/ 29 Separation To Napa County Line | 0 | 0 | 0 | 24980108.76 | 25080108.76 | 59540 | 2026-06-01 | 2025-07-29 | 2025-07-14 |  |  | 0 | 0 | 410 | 0
04 | 04-3X5004 | 3X5004 | 04-SOL-80-6.7/6.7 | 20.20.201130 |  | O C Jones & Sons Inc. | 1520 Fourth Street, | Berkeley Ca 94710 | 5105263424 | 5102246309 | 324 Campus Lane, | Fairfield, Ca 94534 | Quang, Tran | 0 | 0 | 0 | 0 | 2025-10-29 | Lanslide And Bike Repair | Haul Off Slide Material At Closed Bike Trail And Disposal, Hazmat Soil Testing, Roadway Excavation, Embankment Grading, "Solano Bi | 43 | 23 | 598713.47 | 10496 | 2560000 | 59561 | 2026-03-27 | 2025-07-29 | 2025-03-28 |  |  | 64 | 0 | 150 | 0 |  | X
04 | 04-3X1604 | 3X1604 | 04-SOL-80-10.1/10.6 | 20.20.201130 |  | Maggiora Bros Drilling, Inc. | 595 Airport Blvd., | Watsonville, Ca 95076 | 8317241338 | 5107738499 | 324 Campus Lane, | Fairfield, Ca 94534 | Tran, Quang | 0 | 0 | 0 | 0 |  | Pump Station Repair | Pump Station Asset Id# 23 0014Dwr/L | 0 | 0 | 0 | 8730 | 1277500 | 57895 | 2025-12-31 | 2025-03-28 | 2025-02-24 |  |  | 0 | 0 | 60 | 0
04 | 04-4G0804 | 4G0804 | 04-SOL-80-10.4/30.2 | HB4C | ACIM-0802- (375)E | O.C. Jones & Sons, Inc. | 1520 Fourth Street | Berkeley Ca 94710 | 5105263424 | 5104064596 | 324 Campus Lane Suite T | Fairfield Ca 94534 | Tatum, Justen | 7500 | 138600.9 | 591011.76 | 0 | 2025-10-20 | Convert Existing Hov Lane To Expres | From 0.95 West Of Red Top Road Undercrossing To 0.4 Mile East Of Leisure Town Road Overcrossing | 82 | 99 | 157335451.27 | 143352700.48 | 159668875.48 | 42082 | 2026-07-08 | 2022-02-02 | 2022-01-18 |  |  | 813 | 0 | 940 | 50 |  | X
04 | 04-3X4704 | 3X4704 | 04-SOL-80-12.9/12.9 | 20.20.201130 |  | Gordon N Ball Inc | 1777 Oakland Blvd St 300, | Walnut Creek, Ca 94596 |  | 5104064596 | 324 Campus Lane, | Fairfield, Ca 94534 | Tatum, Justen | 0 | 0 | 0 | 0 |  | "Repair Ac Pavement, Address Exposed Found | Pavement Settlement And Embankment Reconstruction | 0 | 0 | 0 | 6508 | 994000 | 59676 | 2025-10-14 | 2025-08-05 | 2025-03-31 |  |  | 0 | 0 | 60 | 0
04 | 04-4G8734 | 4G8734 | 04-SOL-80-13.9/14.5 |  |  | John Semsen Landscaping Co., Inc. | 21161 Lyons Bald Mt. Road | Sonora Ca 95370 | 2097434911 | 5107746276 | 3401 Regatta Blvd | Richmond Ca, 94804 | Luckel, Kasaia | 5080 | 0 | 0 | 0 | 2025-10-20 | Maintain Existing Planted Areas. | Solano County In And Near Fairfield At Danwilson Creek Bridge And At Suisun Creek Bridge | 65 | 75 | 402860 | 540300 | 561040 | 46264 | 2027-04-08 | 2023-01-13 | 2022-11-21 |  |  | 678 | 0 | 1040 | 0 |  | X
04 | 04-0K6404 | 0K6404 | 04-SOL-80-15.9/30.2 |  | ACIM-0801- (995)E | O.C. Jones & Sons, Inc. | 1520 Fourth Street | Berkeley Ca 94710 | 5105263424 | 5104064596 | 324 Campus Lane, Suite T | Fairfield, Ca 94534 | Tatum, Justen | 217970.85 | 0 | 0 | 0 | 2025-10-20 | Cold Plane, Overlay, Mgs, Ramp Metering, L | Solano County On Route 80 In And Near Fairfield And Vacaville At Various Locations From 1.5 Miles East Of Suisun Valley Road Overc | 65 | 65 | 11824581.09 | 15116851.5 | 15446851.5 | 57066 | 2026-02-19 | 2025-01-16 | 2024-12-17 |  |  | 150 | 0 | 230 | 0 |  | X
04 | 04-4K3004 | 4K3004 | 04-SOL-80-22.1/23 |  | SIMG-0802- (377)E | Gordon N. Ball, Inc. | 1777 Oakland Blvd., Ste 300 | Walnut Creek, Ca 94596 | 9258385675 | 5108676033 | 324 Campus Lane, Suite T | Fairfield, Ca 94534 | Lane, Isaiah | 0 | 69972.01 | 0 | 0 | 2025-10-20 | Construct Concrete Barrier And Install Dra | Solano County From 1.2 Miles East Of Northtexas Street Overcrossing In Fairfield To 0.1 Mile West Of Cherry Glen Road Overcrossing | 100 | 95 | 3786891.19 | 3491799 | 4000367.52 | 56786 | 2025-08-12 | 2024-12-03 | 2024-11-05 |  |  | 120 | 0 | 120 | 0 |  | X
04 | 04-0J6014 | 0J6014 | 04-SOL-80-34.4/34.5 |  |  | Empire Landscaping Inc. | 26945 County Road 97D | Davis Ca 95616 | 5304003944 | 5107746276 | 3401 Regatta Blvd. | Richmond, Ca 94804 | Luckel, Kasaia | 3210 | 0 | 0 | 0 | 2025-10-20 | Maintain Existing Planted Areas. | Solano County In And Near Dixon And Vacaville On Route 80 At Mc Cune Creek Bridge And On Route 505 At Horse Creek Bridge | 61 | 63 | 120132.5 | 190665 | 190665 | 47906 | 2027-06-10 | 2023-03-20 | 2023-01-13 |  |  | 635 | 0 | 1040 | 0 |  | X
04 | 04-0X7004 | 0X7004 | 04-SOL-84-3.0/13.6 |  |  | O.C. Jones & Sons, Inc. | 1520 Fourth Street | Berkeley Ca 94710 | 5105263424 | 5108071407 | 324 Campus Lane, Suite T | Fairfield, Ca 94534 | Sarwary, Asadullah | 810745.86 | 0 | 0 | 0 | 2025-10-20 | Cold Plane Ac Pavement And Overlay With Rh | Solano County Near Rio Vista From 0.4 Milenorth Of Cache Slough Ferry To Yolo Countyline | 78 | 93 | 2127440.83 | 2250755 | 2239695.85 | 59338 | 2025-11-04 | 2025-07-14 | 2025-06-25 |  |  | 35 | 0 | 45 | 0 |  | X
04 | 04-0X7604 | 0X7604 | 04-SOL-113-18.3/21.2 |  |  | Doolittle Construction, Llc Dba Doolitlle Road Construction | 15 Business Parkway Suite 105 | Sacramento Ca 95828 | 7756917232 | 5108071407 | 324 Campus Lane, Suite T | Fairfield, Ca 94534 | Sarwary, Asadullah | 836157.07 | 0 | 0 | 0 | 2025-10-20 | Cold Plane Ac Pavement, Place Hma And Over | Solano County In And Near Dixon From Parkway Boulevard To Route 113/80 Separation | 100 | 91 | 1415946.32 | 1449000 | 1490417 | 59115 | 2025-10-16 | 2025-06-26 | 2025-06-12 |  |  | 30 | 0 | 30 | 0 |  | X
04 | 04-0J3004 | 0J3004 | 04-SON-1-26.7/27.1 |  | ACST-P001- (679)E | Argonaut Constructors | 360 Sutton Place | Santa Rosa Ca 95407 | 7075424862 | 5104969271 | 4030 Occidental Rd., Unit A | Santa Rosa, Ca 95401 | La Serna, Fabio | 0 | 32202.76 | 0 | 0 | 2025-09-20 | Permanent Restoration Of Roadway | In Sonoma County Near Jenner, From 0.3 To 0.7 Miles North Of Myers Grade Road | 58 | 100 | 14924915.22 | 12965088.05 | 14664352.18 | 43764 | 2025-08-20 | 2022-08-05 | 2022-07-08 | 2025-10-30 |  | 319 | 0 | 550 | 4 |  | X
04 | 04-0J3014 | 0J3014 | 04-SON-1-26.7/27.1 |  |  | Empire Landscaping Inc. | 26945 County Road 97D | Davis Ca 95616 | 5304003943 | 5104069754 | 4030 Occidental Rd., Unit A | Santa Rosa, Ca 95401 | Paulo, Harley | 12900 | 0 | 0 | 0 | 2025-10-20 | Maintain Existing Planted Areas And Erosio | Sonoma County Near Jenner From 0.3 Mile To0.7 Mile North Of Meyers Grade Road | 4 | 18 | 127400 | 696100 | 696100 | 57575 | 2029-08-06 | 2025-03-13 | 2024-10-31 |  |  | 42 | 0 | 1080 | 0 |  | X
04 | 04-1K7314 | 1K7314 | 04-SON-1-30.8/40.6 |  |  | Wylatti Resource Management, Inc. | 23601 Cemetery Lane | Covelo Ca 95428 | 7079838135 | 5108674515 | 3401 Regatta Blvd | Richmond, Ca 94804 | Simpson, John | 0 | 0 | 0 | 0 |  | Maintain Existing Planted Area And Erosion | Sonoma County At Various Locations From 2.2 Miles South Of Fort Ross Road To 0.7 Mile North Of Moon Rock Campground | 0 | 0 | 0 | 280763.2 | 280763.2 | 60139 | 2029-01-30 | 2025-10-24 | 2025-10-02 |  |  | 0 | 0 | 1080 | 0
04 | 04-1K7304 | 1K7304 | 04-SON-1-30.8/40.6 |  |  | Wylatti Resource Management, Inc. | 23601 Cemetery Lane | Covelo Ca 95428 | 7079838135 | 5104069754 | 4030 Occidental Rd., Unit A | Santa Rosa, Ca 95401 | Paulo, Harley | 70165.05 | 0 | 0 | 0 | 2025-10-20 | Remove And Replace Culverts, And Establish | Sonoma County At Various Locations From Mill Gulch To 0.5 Mile South Of Miller Creek | 36 | 89 | 2378717.79 | 2554842.04 | 2616842.04 | 53804 | 2025-12-31 | 2023-11-08 | 2023-10-18 |  |  | 145 | 0 | 400 | 0 |  | X
04 | 04-1X3204 | 1X3204 | 04-SON-1-38.6/38.6 | 20.10.201130 |  | O.C. Jones & Sons, Inc. | 1520 Fourth St | Berkeley Ca 94710 | 5105263424 | 5104069754 | 4030 Occidental Rd., Unit A | Santa Rosa, Ca 95401 | Paulo, Harley | 0 | 0 | 0 | 0 | 2025-11-03 | Construct Soldier Pile Wall & Drainage | In Sonoma Co. On Rte 1 At Pm 38.58 At Walsh Construct Soldier Pile Wall, And Drainage Facilities Dir'S Order Emergency F.A. | 100 | 84 | 7251033.27 | 20611 | 8615000 | 55661 | 2025-12-31 | 2024-02-23 | 2024-02-22 |  |  | 280 | 0 | 120 | 0
04 | 04-1K7504 | 1K7504 | 04-SON-1-41.2/54.6 |  |  | Wylatti Resource Management, Inc. | 23601 Cemetery Lane | Covelo Ca 95428 | 7079838135 | 5104069754 | 4030 Occidental Rd., Unit A | Santa Rosa, Ca 95401 | Paulo, Harley | 126448.41 | 0 | 0 | 0 | 2025-10-20 | Remove Culvert, Rcp, Corrugated Steel Pipe | Sonoma County At Various Locations From 0.2 Mile North Of Miller Creek To 0.1 Milenorth Of Vantage Road | 34 | 90 | 2584970.63 | 2762871.22 | 2850831.42 | 53805 | 2025-12-31 | 2023-11-09 | 2023-10-25 |  |  | 143 | 0 | 425 | 0 |  | X
04 | 04-1K7604 | 1K7604 | 04-SON-1-45.4/0 |  |  | Rege Construction, Inc. | 600 Santana Drive | Cloverdale, Ca 95425 | 7073183762 | 5104069754 | 4030 Occidental Rd., Unit A | Santa Rosa, Ca 95401 | Paulo, Harley | 388857.49 | 0 | 0 | 0 | 2025-10-20 | Construct Pipe Culvert Wingwall And Draina | Sonoma County Near Stewarts Point At 2.7 Miles South Of Skaggs Springs Road | 17 | 73 | 761612.09 | 1026808 | 1026808 | 57898 | 2025-11-28 | 2025-03-27 | 2025-03-03 |  |  | 50 | 0 | 290 | 0 |  | X
04 | 04-3X0804 | 3X0804 | 04-SON-1-/7.2 | 20.20.201130 |  | Ghilotti Construction Company,Inc. | 246 Ghilotti Avenue, | Santa Rosa, 95407 |  | 5104069754 | 4030 Occidental, Bldg A, | Santa Rosa, Ca 95401-5801 | Paulo, Harley | 0 | 0 | 0 | 0 | 2025-11-03 | Near Bodega Bay Slipout | Near Bodega Bay Near Bodega Bay | 100 | 43 | 2062231.44 | 24052 | 4745000 | 57266 | 2025-12-31 | 2025-02-20 | 2025-02-20 |  |  | 140 | 0 | 140 | 0
04 | 04-1X1404 | 1X1404 | 04-SON-1-/24.7 | 20.20.201130 |  | Engelke Construction, Inc. | Po Box 1387 | Healdsburg, Ca 95448 | 7074338389 | 5104069754 | 4030 Occidental Rd, Unit A | Santa Rosa, Ca 95401 | Paulo, Harley | 0 | 0 | 0 | 0 | 2025-11-03 | Install Horizontal Drains & Underdrains | On Route 1, In Sonoma County, Between Pm 24.65 & 24.73 Install Horizontal Drains & Underdrains And Repair Pavement Dir'S Order Em | 81 | 91 | 1943255.77 | 11775 | 2135000 | 56685 | 2025-12-31 | 2024-11-08 | 2024-08-29 |  |  | 85 | 0 | 105 | 0 |  | X
04 | 04-3X1004 | 3X1004 | 04-SON-1-/36.4 | 20.20.201130 |  | Precision Excavating & Gradinginc | 129 N Cloverdale Blvd #7, | Cloverdale, Ca 95425 |  | 5104069754 | 4030 Occidental, Bldg A, | Santa Rosa, Ca 95401-5801 | Paulo, Harley | 0 | 0 | 0 | 0 | 2025-11-03 | Repair Slipout | Lee Drive At Stillwater Cove | 33 | 19 | 300410.84 | 47202 | 1558400 | 58895 | 2025-11-13 | 2025-06-16 | 2025-04-21 |  |  | 20 | 0 | 60 | 0 |  | X
04 | 04-4G7804 | 4G7804 | 04-SON-1-/58.6 |  | HSST-P001- (704)E | O.C. Jones & Sons, Inc. | 1520 Fourth Street | Berkeley Ca 94710 | 5108162955 | 5104069754 | 4030 Occidental Rd., Unit A | Santa Rosa, Ca 95401 | Paulo, Harley | 1438110 | 0 | 0 | 100000 | 2025-10-20 | Centerline Rumble Strip,Shoulder Widening, | Sonoma County At Various Locations From Marin County Line To Mendocino County Line | 16 | 48 | 2432886 | 5034621.5 | 5086621.5 | 57495 | 2026-12-12 | 2025-03-13 | 2025-02-14 |  |  | 68 | 0 | 420 | 0 |  | X
04 | 04-4H0514 | 4H0514 | 04-SON-12-25.8/0 |  |  | Empire Landscaping, Inc. | 26945 County Road 97D | Davis Ca 95616 | 5304003943 | 7072497557 | 4030 Occidental Rd. Unit A | Santa Rosa, Ca 95401 | Brajnikoff, Leonard | 8400 | 0 | 0 | 0 | 2025-10-20 | Maintain Existing Planted Area And Erosion | Sonoma County Near Santa Rosa At Sonoma Creek Bridge And At Hooker Creek Bridge | 8 | 13 | 58400 | 457080 | 457080 | 58959 | 2029-08-29 | 2025-06-13 | 2025-05-29 |  |  | 84 | 0 | 1040 | 0 |  | X
04 | 04-4A1304 | 4A1304 | 04-SON-101-18.5/18.5 | HE11 | NH - - ( ) | Ghilotti Construction Company,Inc. | 246 Ghilotti Avenue | Santa Rosa Ca 95407 | 7075851221 | 5103856972 | 4030 Occidental Road | Santa Rosa, Ca 94501 | Valeh, Syd | 2236704.4 | 0 | 0 | 0 | 2025-10-20 | Hma, Widen & Replace Hearn Ave Oc. | Sonoma County In Santa Rosa At Hearn Avenue Overcrossing | 48 | 77 | 20042769.62 | 25158888.65 | 25985073.47 | 54424 | 2027-03-25 | 2023-12-13 | 2023-11-17 |  |  | 326 | 0 | 679 | 0 |  | X
04 | 04-1Q7004 | 1Q7004 | 04-SON-101-22.8/32.8 |  |  | Ghilotti Construction Company,Inc. | 246 Ghilotti Avenue | Santa Rosa Ca 95407 | 7079756334 | 7072497557 | 4030 Occidental Road | Santa Rosa, Ca 94501 | Brajnikoff, Leonard | 797272.08 | 0 | 0 | 0 | 2025-10-20 | Replace Bridge Railing And Guardrail, & Re | Sonoma County At Various Locations From Mendocino Avenue Overcrossing To Limerick Lane Overcrossing | 59 | 83 | 6735229.97 | 7965469.13 | 8097806.93 | 57382 | 2026-02-24 | 2025-03-06 | 2025-02-06 |  |  | 117 | 0 | 200 | 0 |  | X
04 | 04-3J0804 | 3J0804 | 04-SON-101-/0 |  |  | Ghilotti Bros., Inc. | 525 Jacoby Street | San Rafael Ca 94901 | 4154547011 | 5108674515 | 384 Bel Marin Keys Blvd Ste200 | Novato, Ca 94949 | Simpson, John | 0 | 0 | 0 | 0 | 2025-10-20 | Construct Steel Sheet Pile Wall And Concre | Sonoma County Near Petaluma At San Antonio Creek Bridge | 85 | 98 | 1420403.96 | 1233333 | 1504533 | 47607 | 2025-11-12 | 2023-03-15 | 2023-02-15 |  |  | 512 | 0 | 350 | 250 |  | X
04 | 04-2K3604 | 2K3604 | 04-SON-116-9.6/0 |  | ACST-S097- (001)E | Ghilotti Bros., Inc. | 525 Jacoby Street | San Rafael Ca 94901 | 4157202114 | 7072497557 | 4030 Occidental Rd, Unit A | Santa Rosa, Ca 95401 | Brajnikoff, Leonard | 166033.85 | 0 | 0 | 255000 | 2025-10-20 | Repair Side Slope And Construct Soil Nail | Sonoma County Near Monte Rio At 0.2 Mile West Of Cnopius Road | 5 | 11 | 577803.25 | 5116996 | 5206996 | 59098 | 2026-11-20 | 2025-06-19 | 2025-05-07 |  |  | 28 | 0 | 550 | 0 |  | X
04 | 04-3X0504 | 3X0504 | 04-SON-116-10.4/10.4 | 20.20.201130 |  | Piazza Construction | 5200 Carroll Road, | Petaluma, Ca 94952 |  | 7072497557 | 4030 Occidental Road,Unit A | Santa Rosa, Ca 95401 | Brajnikoff, Leonard | 0 | 0 | 0 | 0 | 2025-10-03 | Slipout And Drainage Repair | In Gue In Guerne In Guerneville | 87 | 59 | 4266502.42 | 54577 | 7255000 | 57376 | 2025-11-07 | 2025-03-20 | 2025-01-02 |  |  | 157 | 0 | 180 | 0
04 | 04-4J4604 | 4J4604 | 04-SON-116-11.8/12.2 |  | ACST-P116- (051)E | California Highway Construction Group, Inc. | 1647 Willow Pass Road #150 | Concord Ca 94520 | 9257661714 | 9163201724 | 4030 Occidental Road | Santa Rosa 95401 | Brajnikoff, Leonard | 286157.06 | 63121.09 | 0 | 0 | 2025-10-20 | Replace Curb Ramps, Sidewalk, Driveway, Li | Sonoma County At Guerneville From Brookside Lane To Old River Road | 100 | 83 | 6304736.05 | 6686888 | 7265296.17 | 55699 | 2025-10-27 | 2024-04-29 | 2024-04-16 |  |  | 209 | 0 | 210 | 0
04 | 04-3G9004 | 3G9004 | 04-SON-116-46.5/46.8 | HB4N | CSTG-X097- (044)E | O.C. Jones & Sons, Inc. | 1520 Fourth Street | Berkeley Ca 94710 | 5105263424 | 5104969271 | 384 Bel Marin Keys Ste 200 | Novato Ca 94949 | La Serna, Fabio | 882238.18 | 0 | -3072.6 | 0 | 2025-10-20 | Rdwy Exc, Hma, Drainage, Rock Blanket, Min | Sonoma County Near Schellville On Route 116 From 0.3 Mile North Of Bonneau Road Toroute 121 And On Route 121 From 0.2 Mile South O | 53 | 94 | 11575080.93 | 10572056.8 | 11795130.48 | 52107 | 2026-02-11 | 2023-08-23 | 2023-07-31 |  |  | 302 | 0 | 575 | 0 |  | X
04 | 04-2Q4404 | 2Q4404 | 04-SON-121-6.5/0 |  |  | Gordon N. Ball, Inc. | 1777 Oakland Blvd. Suite 300 | Walnut Creek Ca 94596 | 9258385675 | 5104969271 | 384 Bel Marin Keys Ste 200 | Novato, Ca 94949 | La Serna, Fabio | 938692 | 0 | 0 | 165000 | 2025-10-20 | Remove Br And Ac Surf, Construct Br Deck, | Sonoma County Near Sonoma At Yellow Creek Bridge And At Arroyo Seco Bridge | 4 | 39 | 1358095 | 3378400 | 3483400 | 58276 | 2026-04-14 | 2025-04-24 | 2025-04-07 |  |  | 20 | 0 | 480 | 0 |  | X
04 | 04-0X7204 | 0X7204 | 04-SON-128-12.2/24.8 |  |  | O.C. Jones & Sons, Inc. | 1520 Fourth Street | Berkeley Ca 94710 | 5105263424 | 7072497557 | 4030 Occidental Rd., Unit A | Santa Rosa, Ca 95401 | Brajnikoff, Leonard | 110978.52 | 0 | 0 | 0 | 2025-10-20 | Pavement Preservation | Sonoma County At And Near Kellogg From Sausal Creek Bridge To Napa County Line | 100 | 93 | 958016.75 | 999110.6 | 999110.6 | 59539 | 2025-10-20 | 2025-07-22 | 2025-05-21 | 2025-10-30 |  | 30 | 0 | 30 | 0 |  | X
04 | 04-3X4204 | 3X4204 | 04-SON-128-16.6/16.7 | 20.20.201130 |  | Terracon Constructors Inc | Po Box 276 | Healdsburg, Ca 95448 |  | 5108676107 | 4030 Occidental, Bldg A, | Santa Rosa, Ca 95401-5801 | Brajnikoff, Leonard | 0 | 0 | 0 | 0 |  | Construct Rock Slope Protection (Rsp) And | Slipout On Westbound Son 128 Due To Storm Events | 0 | 0 | 0 | 11661 | 1792000 | 59300 | 2026-02-02 | 2025-07-08 | 2025-03-19 |  |  | 0 | 0 | 80 | 0
04 | 04-0Y8004 | 0Y8004 | 04-VAR-82-25.9/25.9 |  |  | Truesdell Corporation Of California, Inc. | 1310 W. 23Rd Street | Tempe Az 85282 | 6024371711 | 5104069696 | 1007 Knox Ave | San Jose, Ca 95122 | Ngo, Hung T | 40373 | 0 | 0 | 0 | 2025-06-20 | Place Polyester Concrete Overlay, Treat Br | Santa Clara County At Various Locations | 69 | 94 | 3203905.11 | 3197197 | 3319142.5 | 55866 | 2025-10-31 | 2024-05-17 | 2024-04-22 |  |  | 86 | 0 | 120 | 5 |  | X
04 | 04-2Q5704 | 2Q5704 | 04-VAR-101-18.7/18.7 |  | ACNH-X085- (066)E | Disney Construction, Inc. | 533 Airport Blvd., Suite 120 | Burlingame Ca 94010 | 6507321004 | 4085954003 | 1007 Knox Ave | San Jose, Ca 96122 | Patel, Nim | 0 | 0 | 0 | 0 | 2025-07-20 | Replace Stormwater Pumps And Construct Dra | Santa Clara County In And Near Morgan Hilland San Jose At Various Locations | 61 | 79 | 9382665.77 | 9999786 | 11931346.59 | 55793 | 2025-12-31 | 2024-03-14 | 2024-01-29 |  | S | 178 | 0 | 250 | 43 |  | X
04 | 04-3Q6104 | 3Q6104 | 04-VAR-101-21.3/26.5 |  |  | Truesdell Corporation Of California, Inc. | 1310 W. 23Rd Street | Tempe Az 85282 | 6024371711 | 5107159940 | 1007 Knox Ave | San Jose Ca 95122 | Farsipour Naghibi, Sina | 90065 | 0 | 0 | 0 | 2025-04-20 | Polyester Concrete Overlay, And Structural | Santa Clara County At Various Locations | 100 | 91 | 3586156.55 | 3569569 | 3733080 | 52604 | 2025-01-31 | 2023-07-05 | 2023-06-15 |  |  | 120 | 0 | 120 | 0 |  | X
04 | 04-0K1104 | 0K1104 | 04-VAR-280-/0 |  | ACST-000C- (553)E | Fbd Vanguard Construction | 550 Greenville Road | Livermore Ca 94550 | 9252451300 | 5104969525 | 1007 Knox Ave. | San Jose, Ca 95122 | Kabbani, Muhieddine | 1342749.34 | 0 | 0 | 0 | 2025-10-20 | Construct Concrete Barrier Transition And | Santa Clara County At Various Locations | 76 | 76 | 12069332.89 | 15597831 | 15696831 | 55774 | 2026-03-05 | 2024-04-29 | 2024-04-05 |  |  | 302 | 0 | 400 | 0 |  | X
04 | 04-0K1204 | 0K1204 | 04-VAR-580-/0 |  | HSNH-000C- (543)E | Perry Electric Incorporated | 130 Murwood Court | Walnut Creek Ca 94596 | 9257662778 | 5104218049 | 2525 Stanwell Dr., Ste 100 | Concord, Ca 94520 | Kalantari, Ramin | 46924.44 | 0 | 0 | 0 | 2025-10-20 | Install Rectangular Rapid Flashing Beacon | Alameda And Contra Costa Counties At Various Locations | 88 | 98 | 8571942.72 | 7428226.5 | 8743268.2 | 47764 | 2025-12-01 | 2023-03-15 | 2023-02-17 |  |  | 500 | 0 | 500 | 69 |  | X
04 | 04-4Q2504 | 4Q2504 | 04-VAR-680-.1/20.7 |  |  | Bay Line Cutting & Coring | 501 Cesar Chavez, Suite 101B | San Francisco Ca 94124 | 5107154838 | 3447662454 | 3847 Breakwater Ave | Hayward Ca 94545 | Onate, Ernesto | 177313.9 | 0 | 0 | 0 | 2025-10-20 | Place Polyester Concrete Overlay, And Repl | Alameda County At Various Locations | 98 | 88 | 3470681.17 | 3997000 | 3852212.72 | 51325 | 2025-12-19 | 2023-07-24 | 2023-06-16 |  |  | 78 | 0 | 80 | 0 |  | X
04 | 04-0Q0704 | 0Q0704 | 04-VAR-880-/32 |  | ACST-000C- (559)E | St. Francis Electric Llc | 975 Carden St | San Leandro Ca 94577 | 5104215523 | 5108676156 | 3401 Regatta Blvd. | Richmond, Ca 94804 | Faustin, Glenn | 436757.38 | 0 | 0 | 0 | 2025-07-20 | Modify Ramp Metering Systems, Install Guar | Alameda, Contra Costa, San Mateo, Santa Clara, And Solano Counties At Various Locations | 90 | 63 | 5682132.58 | 8987000 | 9037000 | 55684 | 2025-12-31 | 2024-04-17 | 2024-03-25 |  | S | 180 | 0 | 200 | 0
04 | 04-0Q4404 | 0Q4404 | 04-VAR-880-/10 |  | ACNH-X081- (036)E | Hoseley Corporation | Po Box 881386 | San Francisco, Ca 94188 | 4154048997 | 5109088819 | 585 Linda Mar Blvd. | Pacifica, Ca 94044 | Kardavani, Kayvan | 22320.25 | 103516.15 | 0 | 0 | 2025-10-20 | Install Trash Capture Devices And Maintena | San Mateo County At Various Locations | 36 | 95 | 2592310.93 | 2449000 | 2681815 | 55685 | 2025-12-02 | 2024-04-23 | 2024-04-02 |  |  | 140 | 0 | 390 | 0 |  | X
04 | 04-3Y5204 | 3Y5204 | 04-VAR--/0 |  |  | Specialized Pavement Marking Llc | 11095 Sw Industrial Way Suite | Tualatin Or 97062 | 5038850420 | 5103857079 | 3847 Breakwater Ave | Hayward Ca 94545 | Nguyen, Danh-Ngon | 1500 | 0 | 0 | 0 | 2025-10-02 | Replace Pavement Delineation. | Alameda And Contra Costa Counties At Various Locations | 100 | 100 | 1293346.55 | 1400874.15 | 1465147.9 | 55879 | 2025-10-02 | 2024-05-10 | 2024-03-19 | 2025-10-03 |  | 45 | 0 | 45 | 0 |  | X
04 | 04-0K1004 | 0K1004 | 04-VAR--/0 |  | HSST-X095- (038)E | Mike Brown Electric Co. | 561 Mercantile Drive | Cotati Ca 94931 | 7077928100 | 5108676033 | 324 Campus Lane Suite T | Fairfield, Ca 94534 | Lane, Isaiah | 484078.14 | 0 | -420561.13 | 0 | 2025-10-20 | Install Accessible Pedestrian Signal Syste | Solano County At Various Locations. | 98 | 81 | 2617098.8 | 3550160 | 2857365.87 | 56766 | 2025-10-27 | 2024-11-08 | 2024-10-10 |  |  | 205 | 0 | 210 | 0
04 | 04-1Q2004 | 1Q2004 | 04-VAR--/0 |  | HSST-X081- (037)E | Columbia Electric, Inc. | 1980 Davis St. | San Leandro Ca 94577 | 5104309505 | 5103931593 | 1700 South Amphlett Blvd. | San Mateo, Ca 94402 | Lam, Peter | 382973.05 | 0 | 0 | 0 | 2025-10-20 | Install Rectangular Rapid Flashing Beacon | San Mateo County At Various Locations | 24 | 21 | 1472265.6 | 6792399 | 6852399 | 57071 | 2026-06-04 | 2025-01-14 | 2024-11-21 |  |  | 48 | 0 | 200 | 0 |  | X
04 | 04-1W0904 | 1W0904 | 04-VAR--/0 |  | ACST-000C- (569)E | Crosstown Electrical & Data, Inc. John Bejar | 5454 Diaz Street | Irwindale Ca 91706 | 6264850175 | 5103931593 | 1700 South Amphlett Blvd. | San Mateo, Ca 94402 | Inori, Douglas | 9705 | 0 | 0 | 0 | 2025-10-20 | Modifying Traffic Monitoring Station Syste | Marin, Napa, Santa Clara, San Francisco, San Mateo, And Sonoma Counties At Various Locations | 3 | 0 | 9705 | 13963728 | 13963728 | 59638 | 2027-09-30 | 2025-08-01 | 2025-06-19 |  |  | 16 | 0 | 500 | 0 |  | X
04 | 04-0X5904 | 0X5904 | 04-VAR--/0 |  |  | Gba Engineering, Inc. | 18543 Yorba Linda Blvd #394 | Yorba Linda Ca 92886 | 7145106700 | 5104069696 | 1007 Knox Ave. | San Jose, Ca 95122 | Ngo, Hung T. | 0 | 0 | 0 | 0 |  | Install Roadside Signs And Pavement Deline | Santa Clara County At Various Locations | 0 | 0 | 0 | 1372681 | 1372681 | 59595 | 2026-05-29 | 2025-07-14 | 2025-06-11 |  | S | 0 | 0 | 45 | 0
04 | 04-3Y5904 | 3Y5904 | 04-VAR--/0 |  |  | American Civil Constructors West Coast, Llc | 2990 Bay Vista Court, Suite D | Benicia Ca 94510 | 7077468028 | 5104218049 | 2525 Stanwell Drive. Suite 100 | Concord, Ca 94520 | Kalantari, Ramin | 523150.27 | 0 | 0 | 121500 | 2025-10-20 | Place Polyester Concrete Overlay, Grind Br | Contra Costa County At Various Locations | 51 | 35 | 961005.45 | 2736000 | 2736000 | 59538 | 2025-12-10 | 2025-07-01 | 2025-05-23 |  |  | 36 | 0 | 70 | 0 |  | X
04 | 04-3W5604 | 3W5604 | 04-VAR--/0 |  | ACIM-X095- (036)E | Myers & Sons Construction, Llc | 45 Morrison Ave | Sacramento Ca 95838 | 9162839950 | 5104064596 | 324 Campus Lane, Suite T | Fairfield, Ca 94534 | Tatum, Justen | 0 | 116870.84 | 0 | 0 | 2025-08-27 | Place Polyester Concrete Overlay. | Solano County At Various Locations | 100 | 100 | 9939707.74 | 9848846 | 9968846 | 56395 | 2025-08-27 | 2024-09-19 | 2024-09-03 | 2025-09-28 |  | 136 | 0 | 200 | 0 |  | X
04 | 04-0X6004 | 0X6004 | 04-VAR--/0 |  |  | Central Striping Service, Inc. | 3489 Luyung Drive | Rancho Cordova Ca 95742 | 9166355175 | 9166342015 | 1700 S Amphlett Blvd | San Mateo, Ca 94402 | Fong, Garrison | 0 | 0 | 0 | 0 | 2025-09-12 | Install Traffic Stripes, Crosswalk Marking | San Mateo County On Route 82 And Route 101At Various Locations | 100 | 100 | 582465.85 | 777966.77 | 859229.27 | 58255 | 2025-09-12 | 2025-05-19 | 2025-04-30 | 2025-09-22 |  | 24 | 0 | 60 | 0 |  | X
04 | 04-0Y8404 | 0Y8404 | 04-VAR--/0 |  |  | Myers & Sons Construction, Llc | 45 Morrison Ave | Sacramento Ca 95838 | 9162839950 | 5107159940 | 1007 Knox Ave. | San Jose, Ca 95122 | Farsipour Naghibi, Sina | 0 | 0 | 0 | 0 | 2025-10-20 | Place Polyester Concrete Overlay, Treat Br | Santa Clara County At Various Locations | 70 | 96 | 3147659.89 | 3122120 | 3156120 | 56099 | 2025-03-10 | 2024-06-05 | 2024-04-04 |  |  | 63 | 0 | 90 | 0 |  | X
04 | 04-0X5704 | 0X5704 | 04-VAR--/0 |  |  | Central Striping Service, Inc. | 3489 Luyung Drive | Rancho Cordova, Ca 95742 | 9166355175 | 5105939011 | 756 Francisco Blvd West | San Rafael, Ca 94901 | Wong, Andrew | 297597.6 | 0 | 0 | 0 | 2025-09-20 | Replace Pavement Delineation, Cold Plane A | Alameda And Sonoma Counties At Various Locations | 100 | 91 | 857740.6 | 924676 | 944676 | 58595 | 2025-12-30 | 2025-06-04 | 2025-05-12 |  |  | 40 | 0 | 40 | 0 |  | X
04 | 04-0X5804 | 0X5804 | 04-VAR--/0 |  |  | Gba Engineering, Inc. | 18543 Yorba Linda Blvd #394 | Yorba Linda Ca 92886 | 7145106700 | 5108676017 | 585 Linda Mar Blvd. | Pacifica, Ca 94044 | Ebrahimi, Mohammad | 86800 | 0 | 0 | 70000 | 2025-10-20 | Install Roadside Signs And Pavement Deline | The City And County Of San Francisco At Various Locations | 48 | 9 | 156800 | 1673946 | 1673946 | 59395 | 2025-11-25 | 2025-07-14 | 2025-06-05 |  |  | 24 | 0 | 50 | 0 |  | X
04 | 04-0P7604 | 0P7604 | 04-VAR--/0 |  | HSST-X095- (037)E | St. Francis Electric, Llc | 975 Carden St | San Leandro Ca 94577 | 5106390639 | 5108676033 | 324 Campus Lane Suite T | Fairfield, Ca 94534 | Lane, Isaiah | 334356.12 | 0 | 0 | 0 | 2025-10-20 | Ped Hybrid Beacon Systems & Modifying Sign | Solano County At Various Locations | 71 | 33 | 2040130.73 | 6167000 | 6147547.59 | 57116 | 2025-12-19 | 2025-02-05 | 2024-12-17 |  |  | 99 | 0 | 140 | 0 |  | X
05 | 05-1S4904 | 1S4904 | 05-0SB-1-10.1/10.1 | 20.20.201130 |  | Security Paving Company, Inc. | 3075 Townsgate Road, Ste. 200 | Westlake Village, Ca 91361 |  | 8056108218 | 2053 Preisker Lane, Suite E | Santa Maria, Ca 93454 | Moreno, Arturo | 0 | 283779.57 | 0 | 0 | 2025-10-20 | Rep.Embankment,Wall Construction & Tc | Excavating&Grading,Repair/Stabalize Embanksoldier Pile Wall Construction,Paving And Traffic Control. Dirs Efa 05A | 46 | 21 | 976489.13 | 23500 | 4685000 | 57260 | 2026-01-20 | 2025-03-10 | 2025-02-17 |  |  | 46 | 0 | 100 | 0 |  | X
05 | 05-1S3704 | 1S3704 | 05-0SB-1-10.7/11 | 20.20.201130 |  | John Madonna Construction Company Inc. | Po Box 5310 | San Luis Obispo, Ca 93403 |  | 8057481087 | 270 E. Hwy 246 Suite 202-203 | Buellton, Ca 93427 | Cooper, Jacob | 0 | 70275.2 | 0 | 0 | 2025-09-20 | Rep. Damaged Culvert Section/Restoresite | Repair Damaged Culvert Sections,Fill Voidsline The Pipe & Restore Site Rep. Damaged Culvert Sec. & Restore Site Dirs Efa 05A2818 | 37 | 64 | 1016686.24 | 8000 | 1585000 | 57263 | 2025-06-30 | 2025-01-02 | 2024-11-14 |  |  | 37 | 0 | 100 | 0 |  | X
05 | 05-1S2904 | 1S2904 | 05-MON-0-/0 | 20.20.201130 |  | Big Wakoo Fence, Inc. | 358 E. Ormonde Road | Arroyo Grande, Ca 93420 |  | 8056108215 | 8115 Prunedale North Road | Prunedale, Ca 93907 | Brar, Baljinder | 0 | 8589.57 | 0 | 0 | 2025-09-22 | Security Fence, Gates & Cameras Install | Perimeter Fence, Gates & Camera Install Monterey, S.Benito & Santa Cruz Maintenancsecurity Improvements At Maint. Stations Dirs Ef | 100 | 100 | 582399.77 | 3075 | 600000 | 56888 | 2025-09-22 | 2024-06-03 | 2024-06-03 | 2025-09-29 |  | 47 | 0 | 100 | 0 |  | X
05 | 05-1R1904 | 1R1904 | 05-MON-1-7.2/9.2 | 20.20.201130 |  | John Madonna Construction Co Inc | Po Box 3810 | San Luis Obispo, Ca 93403 |  | 8059274559 | 775 Arlington St | Cambria, Ca 93428 | Silva, Rick | 0 | 0 | 0 | 0 | 2025-10-06 | Repair Rsp & Gabion Basket Revetments | Mon Cnty Rte 1. Big Sur Rsp Repair. Repairrsp & Gabion Basket Revetments. Restore Access Routes And Traffic Control Dirs Efa 05A27 | 100 | 100 | 81306980.21 | 255000 | 81555000 | 55524 | 2025-10-06 | 2024-03-18 | 2024-01-12 | 2025-10-06 |  | 388 | 0 | 320 | 0 |  | X
05 | 05-1S8404 | 1S8404 | 05-MON-1-10.4/10.4 | 20.20.201130 |  | Kinyon Construction, Inc. | 1533 W.Betteravia Road | Santa Maria,Ca 93455 |  | 8057482342 | 3230 Riverside Avenue, Suite 30 | Paso Robles, Ca 93446 | Iman, Hassan | 0 | 46312.5 | 0 | 0 | 2025-01-31 | Const.,Install & Connect New Pv Elec.Equip | Willow Springs Solar Replacement Remove Existing Pv Elec.Equip. Construct, Install & Connectg New Pv Elec. Equip Dirs Efa 05A2821 | 35 | 4 | 46312.5 | 5625 | 1110000 | 57077 | 2025-05-14 | 2025-01-24 | 2024-11-13 |  |  | 35 | 0 | 100 | 0 |  | X
05 | 05-1R6404 | 1R6404 | 05-MON-1-27.8/27.8 | 20.20.201130 |  | Papich Construction Co Inc | 398 Sunrise Terrace | Arroyo Grande, Ca 93420 |  | 8055500734 | 3230 Riverside Ave Ste 30 | Paso Robles, Ca 93446 | Silva, Rick | 0 | 0 | 0 | 0 | 2025-10-20 | Regent Slide Rock Slide Repair | Regent Slide. Remove/Haul Away Material. Restore Hma Pavement Sect. Install Rockfalprotection. Erosion & Traffic Control Dirs Efa | 100 | 39 | 32067689.46 | 25000 | 82585000 | 55640 | 2024-11-12 | 2024-02-23 | 2024-02-23 |  |  | 214 | 0 | 180 | 0
05 | 05-1R6304 | 1R6304 | 05-MON-1-29.5/29.5 | 20.20.201130 |  | Papich Construction Co Inc | 398 Sunrise Terrace | Arroyo Grande, Ca 93420 |  | 8054712102 | 3230 Riverside Ave Ste 30 | Paso Robles, Ca 93446 | Silva, Rick | 0 | 0 | 0 | 0 | 2025-07-20 | Remove Slide Material/Install Netting | Dolan Park Landslide On Hwy 001. Remove Slide Material Restore Roadway. Install Rockfall Netting And Traffic Control Dirs Efa 05A | 100 | 65 | 5710073.09 | 9000 | 8785000 | 55565 | 2025-10-25 | 2024-05-08 | 2024-02-09 |  |  | 84 | 0 | 50 | 0
05 | 05-1Q8004 | 1Q8004 | 05-MON-1-44.7/69.8 | 20.20.201130 |  | Granite Rock Company | 5225 Hellyer Ave Ste 220 | San Jose, Ca 95138 | 4805741400 | 8055409841 | 1529 Hwy 68 | Monterey, Ca 93940 | Pannu, Art | 0 | 0 | 0 | 0 | 2025-10-20 | Clear Mud And Debris. Clean Culverts | In Mon Cnty On Rte 001 Pm 42.2/72.0 Clear Mud And Debris. Clean Culverts And Repair Erosion. Provide Temp Traffic Contrdirs Efa 05 | 31 | 25 | 6270091.92 | 4750 | 25262750 | 48424 | 2025-10-31 | 2023-05-02 | 2023-01-12 |  |  | 31 | 0 | 100 | 0 |  | X
05 | 05-1T2104 | 1T2104 | 05-MON-1-50.0/54 | 20.20.201130 |  | Granite Rock Company | 5225 Hellyer Avenue, Ste 220 | San Jose, Ca 95138 |  | 8053935930 | 1529 Salinas Highway | Monterey, Ca 93940 | Sandhu, Mandip | 0 | 0 | 0 | 0 |  | Culvert Repair/Replace And Traffic Control | Repair/Replace Culverts & Traffic Control Culvert Repair Or Replace And Traffic Ctrlpoint Sur Drainage Repairs/Culvert Repair Dirs | 0 | 0 | 0 | 2305 | 2305 | 60096 | 2025-12-09 | 2025-10-10 | 2025-09-24 |  |  | 0 | 0 | 50 | 0
05 | 05-1S0404 | 1S0404 | 05-MON-1-60.0/60 | 20.20.201130 |  | A Teichert & Son Inc Dba Teichert Construction | 5200 Franklin Dr. Suite 115 | Pleasanton, Ca 94588 |  | 8319981546 | 1528 Salinas Hwy/ Hwy 68 | Monterey, Ca 93940 | Uberhuaga, Jorge | 0 | 0 | 0 | 0 | 2025-10-20 | Secure And Stabilize The Site. | Mon Cnty Rte 1 Just North Of Rocky Creek Bridge Ocean Side. Traffic Control Secure And Stabilize The Site. Dir Efa 05A | 62 | 95 | 8961145.62 | 5000 | 9385000 | 55641 | 2025-10-31 | 2024-05-21 | 2024-03-30 |  |  | 31 | 0 | 50 | 0 |  | X
05 | 05-1Q9604 | 1Q9604 | 05-MON-1-100.0/1 | 20.20.201130 |  | A.Teichert & Son, Inc Dba Teichert Construction | 3500 American River Dr | Sacramento, Ca 95864 |  | 8055409841 | 1529 Hwy 68 | Monterey, Ca 93940 | Pannu, Art | 0 | 0 | 0 | 0 | 2025-04-03 | Remove Flood Debris | Pajaro River Bridge/Surrounding Areas Thatneed To Remove Flood Debris. Flood Water Pumping. Temp Traffic Control Dirs Efa 05A2621 | 20 | 66 | 1219492.7 | 9250 | 1835000 | 49784 | 2025-04-30 | 2023-05-24 | 2023-03-12 |  |  | 20 | 0 | 100 | 0 |  | X
05 | 05-1K6404 | 1K6404 | 05-MON-1-101.5/102 |  | PTNH-P001- (702)E | Granite Construction Company | 585 W Beach Street | Watsonville Ca 95076 | 8318890275 | 8057486095 | 140 Dubois Street Ste E | Santa Cruz, Ca 95060 | Nguyen, Ian | 737220.22 | 0 | 0 | 58000 | 2025-10-20 | Widening Mvp, Install Culverts And Modify | Monterey And Santa Cruz Counties At Various Locations From Trafton Road Undercrossing To 0.2 Mile North Of Larkin Valley Road. | 100 | 45 | 1405689.79 | 2959959.95 | 3007161.91 | 57239 | 2025-11-27 | 2025-02-26 | 2025-01-30 |  |  | 75 | 0 | 75 | 0
05 | 05-1S1604 | 1S1604 | 05-MON-1-600.0/60 | 20.20.201130 |  | Gordon N. Ball, Inc. | 333 Camille Avenue | Alamo, Ca 94507 |  | 8319981546 | 1529 Hwy 68/Salinas Hwy | Monterey, Ca 93940 | Uberhuaga, Jorge | 0 | 52840.13 | 0 | 0 | 2025-10-20 | New Viaduct To Restore Two Way Traffic | Bld New Rocky Creek Viaduct After Slipout Construct Viaduct Structure Restore Two Way Traffic/ Traffic Controll Dirs Efa 05A2765 | 9 | 56 | 11839209.12 | 105000 | 20985000 | 56204 | 2025-10-31 | 2024-07-16 | 2024-06-14 |  |  | 31 | 0 | 350 | 0 |  | X
05 | 05-0T9914 | 0T9914 | 05-MON-101-41.1/42.2 | HB1 | HSNH-Q101- (407)E | Wabo Landscape & Construction,Inc. | 726 Alfred Nobel Drive | Hercules Ca 94547 |  | 5623705097 |  |  | Rianda Adam | 7858 | 0 | 0 | 0 | 2025-10-20 | Landscape Mitigation Planting, Irrigation, | Monterey County In And Near King City From0.1 Mile South Of Broadway Street To 0.2 Mile North Of Jolon Road | 65 | 92 | 792359.66 | 843669 | 860069 | 50024 | 2026-01-16 | 2023-06-08 | 2023-04-18 |  |  | 553 | 0 | 845 | 0 |  | X
05 | 05-1P5344 | 1P5344 | 05-MON-101-86.1/87.3 |  |  | Gordon N. Ball, Inc. | 333 Camille Avenue | Alamo Ca 94507 |  | 8314555466 | 8115 Prunedale North Road | Prunedale, Ca 93907 | Garcia, Santiago | 0 | 6600 | 0 | 0 | 2025-07-20 | Planting, Irrigation, Slope Paving And Tra | Monterey County In Salinas At Various Locations From Sanborn Road Undercrossing To East Market Street Undercrossing | 76 | 99 | 1813363.72 | 1714170 | 1828339.35 | 47844 | 2025-07-31 | 2023-03-22 | 2023-02-28 |  |  | 280 | 0 | 370 | 0 |  | X
05 | 05-1H6904 | 1H6904 | 05-MON-101-91.3/98.8 |  | ACNH-Q101- (411)E | Desilva Gates Construction | 11555 Dublin Blvd. | Dublin Ca 94568 |  | 8054416931 | 8115 Prunedale North Road | Prunedale, Ca 93907 | Nash Munes | 113680 | 0 | 0 | 0 | 2025-10-20 | Place Rhma, Install Concrete Barrier And D | Monterey County At And Near Prunedale And Salinas From 0.3 Mile North Of Boronda Road Overcrossing To 0.4 Mile North Of Crazy Hors | 100 | 99 | 38445802.41 | 32998998 | 38168831.46 | 46684 | 2025-10-20 | 2023-02-09 | 2022-12-27 |  |  | 326 | 0 | 290 | 0 |  | X
05 | 05-1H6914 | 1H6914 | 05-MON-101-98.8/100.3 |  | PTNH-Q101- (435)E | Precision Grade, Inc. | 25 San Juan Grade Road, Suite | Salinas Ca 93906 |  | 8056108215 | 8115 Prunedale North Road | Prunedale, Ca 93907 | Brar, Baljinder | 1153411.7 | 0 | 0 | 19500 | 2025-10-20 | Install Culverts, Concrete Barrrier And M | Monterey County Near Prunedale From 0.4 Mile North Of Crazy Horse Canyon Rd To Dunbarton Road | 21 | 62 | 4258287.27 | 6818314 | 6843314 | 57877 | 2026-12-11 | 2025-04-29 | 2025-03-28 |  |  | 76 | 0 | 360 | 0 |  | X
05 | 05-1S9404 | 1S9404 | 05-MON-101-870.0/87 | 20.20.201130 |  | A.Teichert & Son, Inc. Dba Teichert Construction | 5200 Franklin Drive, Ste. 115 | Pleasanton, Ca 94588 |  | 8056108215 | 8115 Prunedale North Road | Prunedale, Ca 93907 | Brar, Baljinder | 0 | 0 | 0 | 0 |  | Repair Guardrail & Embankment | Repair Guardrail, Embankment, Downdrain Bin Wall And Traffic Control Guardrail & Embankment Repair Dirs Efa 05A | 0 | 0 | 0 | 4710 | 4710 | 59775 | 2025-10-31 | 2025-08-01 | 2025-08-01 |  |  | 0 | 0 | 50 | 0
05 | 05-1P5334 | 1P5334 | 05-MON-156-1.4/1.3 |  |  | Hoseley Corporation | 96F Pier Admin Building Suite | San Francisco Ca 94124 |  | 8314555466 | 8115 Prunedale North Road | Prunedale, Ca 93907 | Garcia, Santiago | 2200 | 0 | 0 | 0 | 2025-10-20 | Planting, Irrigation Work And Ornamental F | Monterey County In Castroville At Geil Street Pedestrian Overcrossing | 14 | 94 | 934893.06 | 940000 | 987452.31 | 55024 | 2025-10-31 | 2024-01-29 | 2023-12-12 |  |  | 80 | 0 | 580 | 0 |  | X
05 | 05-1H6504 | 1H6504 | 05-MON-183-8.3/9.9 |  | ACST-S183- (006)E | Granite Construction Company | 580 W Beach Street | Watsonville Ca 95076 |  | 8053190940 | 8115 Prunedale North Road | Pruendale, Ca 93907 | Munes,Nash | 474959.27 | 18155 | 0 | 0 | 2025-10-20 | Hma (Type A), Rhma-G, Drainage, Landscape, | Monterey County In Castroville From 0.1 Mile South Of Del Monte Avenue To Route 1/183 Junction. | 16 | 21 | 4142905.66 | 19123028 | 19344172.9 | 57240 | 2026-10-26 | 2025-02-26 | 2025-01-17 |  |  | 96 | 0 | 600 | 0 |  | X
05 | 05-0N71Y4 | 0N71Y4 | 05-SB-101-1.4/4.8 |  |  | Granite Construction Company | 5335 Debbie Road | Santa Barbara, Ca 93111 | 8053312649 | 8057483132 | 3561 Foothill Road | Carpinteria, Ca 93013 | Jones, David | 6168.96 | 0 | 0 | 0 | 2025-10-20 | Install Mitigation Planting | Santa Barbara County In Carpenteria From 0.2 Mile South Of Bailard Avenue Overcrossing To 0.7 Mile South Of South Padaro Lane | 100 | 91 | 2859970.12 | 2989274.75 | 3122862.77 | 42664 | 2026-09-25 | 2022-05-23 | 2022-05-23 |  |  | 693 | 0 | 210 | 7 |  | X
05 | 05-0N72Y4 | 0N72Y4 | 05-SB-101-4.4/7.7 |  |  | Granite Construction Company | Po Box 50085 | Watsonville Ca 95077 |  | 8057483132 | 35 S. La Patera Lane, Sutie E | Goleta, Ca 93117 | Jones, David | 294192 | 8375.79 | 0 | 0 | 2025-10-20 | Sb 101 4B (Padaro) Landscape Planting Proj | Santa Barbara County Near Carpinteria And Summerland, From 0.9 Miles South Of South Padaro Lane Undercrossing To 0.6 Miles North O | 17 | 48 | 2246618.57 | 4593515.98 | 4708841.1 | 57069 | 2028-12-15 | 2024-12-24 | 2024-10-21 |  |  | 160 | 0 | 950 | 3 |  | X
05 | 05-0N72U4 | 0N72U4 | 05-SB-101-4.4/7.7 |  | ACNH-Q101- (395)E | Granite Construction Company | Po Box 50085 | Watsonville Ca 950775085 | 8317241011 | 8057228935 | P.O. Box 996 | Carpinteria Ca | Luobao Cai | 0 | 525 | 0 | 0 | 2025-10-20 | Construct Hov Lanes And | In Santa Barbara County, In And Near Carpinteria And At Summerland From 0.9 Mile South Of South Padaro Lane Undercrossing To 0.6 | 100 | 99 | 159095536.46 | 151000000 | 159455641.2 | 41720 | 2025-10-20 | 2021-06-05 | 2021-06-05 |  |  | 859 | 0 | 840 | 20 |  | X
05 | 05-0N73Y4 | 0N73Y4 | 05-SB-101-7.3/9.6 |  |  | Granite Construction Company | 580 W Beach Street | Watsonville Ca 95076 |  | 8057483132 | 35 S. La Patera Lane, Suite E | Goleta, Ca 93117 | David Jones | 7614 | 0 | 0 | 0 | 2025-10-20 | Install Mitigation Planting | Santa Barbara County, In And Near Summerland From 0.2 Miles North Of Padaro Lane Overcrossing To San Ysidro Creek Bridge | 100 | 84 | 2713932.68 | 3149406 | 3224504.54 | 51945 | 2028-01-28 | 2023-08-02 | 2023-04-21 |  |  | 445 | 0 | 265 | 5
05 | 05-0N74V4 | 0N74V4 | 05-SB-101-9.2/9.7 |  | ACNH-Q101- (426)E | Granite Construction Company | Po Box 50085 | Watsonville Ca 95077 |  | 8056982393 | 3690 Santa Claus Lane | Carpinteria, Ca 93013 | Jason Kline | 1274813.51 | 133263.32 | 0 | 0 | 2025-10-20 | Highway 101: Carpinteria To Santa Barbara | Santa Barbara County At Montecito From 0.2Mile North Of Sheffield Drive Undercrossing To 0.3 Mile South Of San Ysidro Road Overcro | 52 | 62 | 41492962.1 | 63821017 | 66689094.66 | 55922 | 2026-11-20 | 2024-06-07 | 2024-06-07 |  |  | 299 | 0 | 570 | 0 |  | X
05 | 05-0N74U4 | 0N74U4 | 05-SB-101-9.7/10.6 | HE11 | ACNH-Q101- (420)E | Granite Construction Company | 3005 James Rd | Bakersfield Ca 93308 |  | 8056982393 |  |  | Kline, Jason | 850104.42 | 84376.34 | 0 | 0 | 2025-10-20 | Highway 101: Carpinteria To Santa Barbara | Santa Barbara County In And Near Santa Barbara From 0.3 Mile South Of San Ysidro Road Overcrossing To 0.1 Mile North Of Olive Mill | 71 | 83 | 43272667.26 | 48227222.66 | 52380423.18 | 50964 | 2026-06-30 | 2023-06-16 | 2023-06-16 |  |  | 414 | 0 | 580 | 5 |  | X
05 | 05-1K03U4 | 1K03U4 | 05-SB-101-10.0/10.5 |  |  | Granite Construction Company | 5335 Debbie Road | Santa Barbara Ca 93111 |  | 8057228935 | 3690 Santa Claus Lane | Carpinteria, Ca 93013 | Jason Kline/Taylor Merlo | 3544 | 0 | 0 | 0 | 2025-10-20 | Highway 101: Carpinteria To Santa Barbara | Santa Barbara County In And Near Santa Barbara From 0.1 Mile South Of San Ysidro Road Overcossing To 0.1 Mile North Of Olive Mill | 100 | 96 | 15033799.77 | 13936108.17 | 15468969.51 | 45724 | 2025-10-20 | 2022-11-29 | 2022-11-29 |  |  | 260 | 0 | 260 | 0 |  | X
05 | 05-0N7054 | 0N7054 | 05-SB-101-10.4/11.1 |  |  | Granite Construction Company | Po Box 50085 | Watsonville Ca 95077 | 7605733649 | 8054403057 | 3690 Santa Claus Lane | Carpinteria, Ca 93013 | Tristan Gebhart | 810418.01 | 838680.96 | 0 | 151301.49 | 2025-10-20 | Highway 101: Carpinteria To Santa Barbara | In Santa Barbara County In And Near Santa Barbara From 0.1 Mile South Of Olive Mill Road Overcrossing To 0.3 Mile South Of Cabrill | 47 | 50 | 22502708.46 | 38261867.36 | 45209134.28 | 56213 | 2026-12-04 | 2024-07-23 | 2024-07-23 |  |  | 246 | 0 | 526 | 0 |  | X
05 | 05-1K3804 | 1K3804 | 05-SB-101-12.3/13.2 | HA25 |  | Ccfg Construction | 17750 Wards Ferry Rd | Sonora Ca 95370 | 2097434911 | 8057485218 | Po Box 996 | Carpinteria, Ca 93013 | Jones, David | 2717 | 0 | 0 | 0 | 2025-09-20 | Rehabilitate Landscape Planting And | In Santa Barbara County In Santa Barbara From Sycamore Creek Bridge To 0.2 Mile South Of Garden Street Undercrossing | 100 | 99 | 915240.06 | 882512.5 | 922962.5 | 42351 | 2025-09-17 | 2022-04-26 | 2022-04-05 |  |  | 796 | 0 | 795 | 1 |  | X
05 | 05-1H4304 | 1H4304 | 05-SB-101-21.4/21.9 | HA21 | ACNH-Q101- (410)E | M.C.M. Construction, Inc. | 6413 32Nd Street | North Highlands Ca 95660 |  | 9517502468 | 35 S. La Patera Lane | Goleta, Ca 93117 | Yogarajah, Manny/ Lao, Arturo | 1250 | 81276.85 | -5000 | 0 | 2025-10-20 | Replace Structural Concrete Bridges. | Santa Barbara County In Goleta From Route 101/217 Separation To 0.3 Mile North Of San Jose Creek Bridge | 65 | 98 | 20577909.86 | 19884404.3 | 20688147.82 | 48210 | 2026-07-21 | 2023-04-04 | 2023-03-02 |  |  | 468 | 0 | 720 | 2 |  | X
05 | 05-1C9504 | 1C9504 | 05-SB-101-36.0/37 |  | BFNH-Q101- (424)E | M.C.M. Construction, Inc. | 6413 32Nd Street Suite A | North Highlands Ca 95660 |  | 8057481087 | 270 Hwy 246, Suite 203 | Buellton, Ca 93427 | Jacob Cooper | 1218141.7 | 6146.34 | 0 | 0 | 2025-10-20 | Cold Plane Ac Pvmt, Rhma, Lighting Systems | Santa Barbara County About 8.0 Miles West Of Goleta From 0.6 Mile East Of Refugio Road Undercrossing To 0.4 Mile West Of Refugio R | 35 | 28 | 15038937.18 | 52456947 | 52772747 | 56129 | 2027-08-20 | 2024-07-25 | 2024-07-09 |  |  | 243 | 0 | 700 | 0 |  | X
05 | 05-1H8604 | 1H8604 | 05-SB-101-46.2/52.3 | HA22 | ACNH-Q101- (409)E | Calportland Construction | 1625 East Donovan Rd | Santa Maria Ca 93456 |  | 9095605695 | 35 S. La Patera Lane, Suite E | Goleta, Ca 93117 | Jason Torres/Kevin Murdock | 1344319.8 | 504926 | 0 | 0 | 2025-10-20 | Cold Plane Ac Pvmt, Place Hma, Rhma-G, Hma | Santa Barbara County Near Gaviota From 0.1Mile North Of Gaviota Beach State Park To Old Coast Highway | 93 | 88 | 46364471.49 | 46517000 | 53934522.36 | 47265 | 2025-11-24 | 2023-03-03 | 2023-02-01 |  |  | 382 | 0 | 330 | 81 |  | X
05 | 05-1R1404 | 1R1404 | 05-SB-101-47.0/47.3 | 20.20.201130 |  | Calportland Construction | 1625 E Donovan Rd | Santa Maria, Ca 93454 |  | 8054418439 | 270 E. Hwy 246, Ste 202 | Buellton, Ca 93427 | Murdock,Kevin/Engler, Jaime | 0 | 0 | 0 | 0 | 2025-10-20 | Gaviota Creek Repairs | Gaviota Creek Scour Repairs, Sb Cnty 101 @Gaviota Tunnels. Repair Secant Pile Wall &Repair Embankment. Dirs Efa 05A2625 | 100 | 89 | 15508351.53 | 75000 | 17485000 | 50887 | 2025-10-31 | 2023-05-26 | 2023-05-15 |  |  | 263 | 0 | 100 | 0 |  | X
05 | 05-1K4504 | 1K4504 | 05-SB-101-52.3/56.1 |  | ACNH-Q101- (438)E | Calportland Construction | 1625 East Donovan Rd | Santa Maria Ca 93456 |  | 9095605695 | 270 Hwy 246, Suite 203 | Buellton, Ca 93427 | Jason Torres/Kevin Murdock | 528214.07 | 1480.04 | 0 | 0 | 2025-10-20 | Cold Plane And Rhma/Hma Roadway And Bridge | Santa Barbara County Near Buellton From Old Coast Highway To 0.4 Mile South Of Santa Rosa Road Overcrossing | 47 | 33 | 5259042.43 | 16456569.9 | 16090592.2 | 57265 | 2026-03-05 | 2025-03-03 | 2025-01-28 |  |  | 85 | 0 | 180 | 0 |  | X
05 | 05-1F79A4 | 1F79A4 | 05-SB-101-55.9/56.2 | HA21 |  | Souza Construction Inc | Po Box 3810 | San Luis Obispo Ca 93403 | 8055468288 | 8057481087 | 270 E Hwy 246 #203 | Buellton, Ca 93427 | Jacob Cooper | 6624 | 0 | 0 | 0 | 2025-09-20 | Bridge Rail Upgrade | In Santa Barbara County Near Buellton From 0.1 Mile South Of Nojoqui Creek Bridge To 0.3 Mile South Of Santa Rosa Road Overcross | 0 | 0 | 5729997.86 | 5441692.4 | 5852106.33 | 45005 | 2025-11-03 | 2022-10-06 | 2022-09-13 |  |  | 186 | 0 | 438 | 9 | X | X
05 | 05-1F7904 | 1F7904 | 05-SB-101-55.9/56.2 | HA21 |  | Spectrum Construction Group, Inc. | 16 Goodyear, Ste. 140 | Irvine Ca 92618 | 9492991400 | 8056885920 | 270 E Hwy 246 #203 | Buellton, Ca 93427 | Ballentine, David | 13303.8 | 0 | 0 | 0 | 2021-10-20 | Bridge Rail Upgrade | In Santa Barbara County Near Buellton From 0.1 Mile South Of Nojoqui Creek Bridge To 0.3 Mile South Of Santa Rosa Road Overcross | 27 | 16 | 956780.16 | 5840830.83 | 5895830.83 | 41248 | 2022-07-01 | 2020-09-21 | 2020-08-20 |  |  | 67 | 0 | 505 | 0 |  | X
05 | 05-1K5104 | 1K5104 | 05-SB-101-65.0/84.1 |  | PTNH-Q101- (437)E | Central Coast Financial Group,Inc. Dba Ccfg Construction | 17750 Wards Ferry Rd | Sonora Ca 95370 |  | 8056108218 | 2053 Preisker Ln, Ste E | Santa Maria, Ca 93454 | Arturo Moreno | 306909.85 | 26250.75 | 0 | 0 | 2025-10-20 | Drainage Systems, Lighting Systems And Rep | Santa Barbara County At And Near Los Alamos And Orcutt At Various Locations From 2.3 Miles North Of Route 154/101 Separation To 0. | 28 | 73 | 2623311.32 | 3351395 | 3504394.32 | 57264 | 2026-12-11 | 2025-03-03 | 2025-01-31 |  |  | 111 | 0 | 400 | 0 |  | X
05 | 05-1R7204 | 1R7204 | 05-SB-101-84.0/87 |  |  | Doolittle Construction, Llc Dba Doolitlle Road Construction | 15 Business Parkway Suite 105 | Sacramento Ca 95828 |  | 8059221611 | 2053 Preisker Ln, Ste E | Santa Maria, Ca 93454 | Albert Reed,Sr/Jason Torres | 667784.75 | 0 | 0 | 0 | 2025-10-20 | Micro-Surfacing. | Santa Barbara County In Santa Maria From 0.3 Mile South Of South Santa Maria Undercrossing To 0.4 Mile North Of Betteravia Road Ov | 31 | 88 | 1015057.65 | 1179000 | 1236805.12 | 59336 | 2025-10-23 | 2025-07-14 | 2025-05-06 | 2025-10-30 |  | 11 | 0 | 35 | 0 |  | X
05 | 05-1R7504 | 1R7504 | 05-SB-101-/2.2 |  |  | Granite Construction Company | 5335 Debbie Rd | Santa Barbara Ca 93111 |  | 8057210091 | 35 S. La Patera Lane | Goleta, Ca 93117 | Chhay, Alis; Doom, Trevor | 184019.05 | 0 | 0 | 0 | 2025-10-20 | Cold Plane And Overlay Hma Pavement. | Santa Barbara County In And Near Carpinteria From Ventura County Line To 0.3 Mile South Of Carpinteria Creek Bridge | 83 | 83 | 2643066.76 | 3093950 | 3166917.5 | 58795 | 2025-11-03 | 2025-05-23 | 2025-04-21 |  |  | 50 | 0 | 60 | 0 |  | X
05 | 05-1R7304 | 1R7304 | 05-SB-135-7.2/M9.7 |  |  | Calportland Construction | 1625 East Donovan Rd | Santa Maria Ca 93456 |  | 9095605695 | 2053 Preisker Ln, Ste E | Santa Maria, Ca 93454 | Torres,Jason Are/Al Reed Srre | 1115368.89 | 0 | 0 | 13500 | 2025-10-20 | Partial Depth Recycling And Rhma-G Overlay | Santa Barbara County About 7 Miles North Of Los Alamos From San Antonio Creek Bridge To San Antonio Road | 80 | 90 | 2485392.89 | 2742782 | 2737733.87 | 57876 | 2025-10-28 | 2025-04-24 | 2025-04-14 |  |  | 44 | 0 | 55 | 0 |  | X
05 | 05-1C4104 | 1C4104 | 05-SB-154-2.6/0 | HA21 |  | M.C.M. Construction, Inc. | 6413 32Nd Street | North Highlands Ca 95660 |  | 8057481087 | 270 E Highway 246,#203 | Buellton, Ca 93427 | Jacob Cooper | 0 | 10348.8 | 0 | 0 | 2025-09-20 | Replace Pedestrian Bridge. | Santa Barbara County Near Los Olivos At Alamo Pintado Creek Pedestrian Bridge | 38 | 94 | 3763316.04 | 3875375 | 3985945.52 | 47204 | 2025-11-07 | 2023-03-02 | 2023-01-18 |  |  | 150 | 0 | 400 | 0 |  | X
05 | 05-1R6504 | 1R6504 | 05-SB-154-26.0/30.2 | 20.20.201130 |  | Calportland Construction | 1625 E Donovan Road | Santa Maria, Ca 93454 |  | 8054418439 | 270 E. Hwy 246, Suite 202 | Buellton, Ca 93427 | Murdock, Kevin/Person, Joe | 0 | 0 | 0 | 0 | 2025-10-20 | Repair Slipouts,Slides & Rockfall Fence | Slipouts, Slides And Rockfall Fence Repairin Santa Barbara County On Hwy 154 At San Marcos And San Antonio Dirs Efa 05A | 100 | 71 | 11766330.33 | 21000 | 16586000 | 55658 | 2025-09-01 | 2024-05-21 | 2024-02-26 |  |  | 278 | 0 | 50 | 0
05 | 05-1P5384 | 1P5384 | 05-SB-166-63.9/64.9 |  |  | Cal Electro, Inc. | 3710 Electro Way | Redding Ca 96002 |  | 8059221611 | 2053 Preisker Ln Def | Santa Maria Ca 93454 | Reed, Albert/Gaston,Phil | 4935 | 0 | 0 | 0 | 2025-10-20 | Irrigation, Planting, Vehicle Charging Sys | Santa Barbara County In New Cuyama From 0.2 Mile West Of Branch Canyon Bridge To Newsome Street | 81 | 98 | 937112.36 | 941110 | 953582.36 | 48206 | 2026-01-16 | 2023-04-04 | 2023-01-31 |  |  | 452 | 0 | 560 | 0 |  | X
05 | 05-1C3604 | 1C3604 | 05-SB-217-.9/1.4 | HA21 | ACNH-P217- (003)E | M.C.M. Construction, Inc. | 6413 32Nd Street | North Highlands Ca 95660 |  | 9517502468 | 35 S. La Patera Lane | Goleta, Ca 93117 | Yogarajah, Manny/ Lao, Arturo | 465635.38 | 6528.64 | 0 | 0 | 2025-10-20 | Replace Bridge. | Santa Barbara County Near Goleta From 0.2 Mile East Of Goleta Slough Bridge To 0.4 Mile East Of San Jose Creek Bridge | 53 | 72 | 21371188.75 | 26134014.5 | 29723142.54 | 46964 | 2026-06-09 | 2023-02-21 | 2023-01-31 |  |  | 455 | 0 | 800 | 62 |  | X
05 | 05-1P5394 | 1P5394 | 05-SB-246-32.8/33.2 |  |  | Ccfg Construction | 17750 Wards Ferry Rd | Sonora Ca 95370 | 2097434911 | 8057483132 | 3651 Foothill Road. | Carpintera, Ca 93013 | Jones, David | 2970 | 0 | 0 | 0 | 2025-10-20 | Install Beautification, | On Route 246 In Santa Barbara County From Cuesta Road To Edison Street | 93 | 96 | 1191913.09 | 1177526 | 1241831.11 | 43506 | 2025-11-04 | 2022-07-29 | 2022-06-15 |  |  | 739 | 0 | 795 | 0 |  | X
05 | 05-1H8114 | 1H8114 | 05-SBT-25-18.8/19.2 |  |  | John Semsen Landscaping Co., Inc. | 21161 Lyons Bald Mountain Roa | Sonora Ca 95370 |  | 8314555466 | 8115 Prunedale North Road | Prunedale, Ca 93907 | Garcia, Santiago | 2430 | 0 | 0 | 0 | 2025-10-20 | Planting Mitigation. | San Benito County About 32 Miles South Of Hollister From 0.8 Mile North Of San Benito Lateral To 2.0 Miles South Of Route146 | 10 | 76 | 290645 | 381675 | 381675 | 58796 | 2028-09-28 | 2025-06-10 | 2025-04-29 |  |  | 77 | 0 | 810 | 0 |  | X
05 | 05-1P5314 | 1P5314 | 05-SBT-25-49.5/51.1 |  |  | Bortolussi & Watkin, Inc. | 77 Larksput Street | San Rafael Ca Ca 94901 |  | 8314555466 | 8115 Prunedale North Road | Prunedale, Ca 93907 | Garcia, Santiago | 3100.5 | 0 | 0 | 0 | 2025-10-20 | Planting And Irrigation And Install Transp | San Benito County In And Near Hollister From 0.1 Mile South Of Sunset Drive To Santa Ana Road | 16 | 96 | 1049872.85 | 929993 | 1074138.08 | 48205 | 2025-10-31 | 2023-04-04 | 2023-03-02 |  |  | 79 | 0 | 500 | 0 |  | X
05 | 05-1J4814 | 1J4814 | 05-SBT-25-53.7/54.3 |  |  | John Semsen Landscaping Co., Inc. | 21161 Lyons Bald Mountain Roa | Sonora Ca 95370 |  | 8314555466 | 8115 Prunedale North Road | Prunedale, Ca 93907 | Garcia, Santiago | 2430 | 0 | 0 | 0 | 2025-10-20 | Highway Planting And Plant Establishment W | San Benito County Near Hollister On Route 25 From 0.4 Mile East To 0.3 Mile West Of Route 156 And On Route 156 From 0.4 Mile South | 52 | 84 | 235840 | 281040 | 281040 | 54064 | 2027-04-16 | 2023-11-30 | 2023-10-31 |  |  | 408 | 0 | 780 | 0 |  | X
05 | 05-1S9004 | 1S9004 | 05-SBT-101-1.5/1.7 | 20.20.201130 |  | Midstate Barrier, Inc. | Po Box 30550 | Stockton, Ca 95213-0550 |  | 8056108215 | 8115 Prunedale North Road | Prunedale, Ca 93907 | Brar, Baljinder | 0 | 23754.85 | 0 | 0 | 2025-10-05 | Mod.Guardrail,Turnpocket,Striping And Tc | Modify Guardrail And Turn Pocket Modify Striping And Install Signs Provide Traffic Control Dirs Efa 05A | 22 | 13 | 107594.36 | 4270 | 839000 | 59075 | 2025-12-03 | 2025-06-24 | 2025-05-23 |  |  | 10 | 0 | 45 | 0 |  | X
05 | 05-1S5104 | 1S5104 | 05-SBT-101-4.2/4.5 | 20.20.201130 |  | Top Tier Grading, Llc | 8305 Prunedale N. Rd. #155 | Salinas, Ca 93907 | 8317899273 | 8056108215 | 8115 Prunedale N. Rd. | Prunedale, Ca 93907 | Brar, Baljinder | 0 | 692686.63 | 0 | 0 | 2025-10-20 | Culvert Repair, Line Culvert & Erosion Ctl | Exc Embankment To Replace Portion Of Culvtline Culvert, Fill Voids & Gaps With Groutrep.Sinkhole, Bio Monitoring & Erosion Ctldirs | 100 | 93 | 3242529.43 | 17500 | 3485000 | 58095 | 2025-09-04 | 2025-05-06 | 2025-04-02 |  |  | 95 | 0 | 75 | 0 |  | X
05 | 05-1S0104 | 1S0104 | 05-SBT-101-12.0/2.1 |  |  | Community Tree Service | 416 Salina Road | Pajaro, Ca 95076 |  | 8056108215 | 8115 Prunedale North Road | Prunedale, Ca 93907 | Brar, Baljinder | 0 | 21427.95 | 0 | 0 | 2025-10-20 | Tree Removal,Site Restoration & Monitoring | Eucalyptus Tree Removal, Traffic Control &Arborist & Environmental Monitoring Site Restoration & Erosion Contol Dirs Efa 05A2797 | 100 | 85 | 2208790.13 | 13000 | 2585000 | 56608 | 2026-05-29 | 2024-10-25 | 2024-09-03 |  |  | 148 | 0 | 50 | 0 |  | X
05 | 05-1P5324 | 1P5324 | 05-SBT-156-2.7/2.7 |  |  | Granite Rock Company | 5225 Hellyer Avenue, Suite 22 | San Jose Ca 95138 |  | 8314555466 | 8115 Prunedale North Road | Prunedale, Ca 93907 | Santiago Garcia | 172.8 | 0 | 0 | 0 | 2025-09-25 | Planting, Irrigation, Slope Paving And Tra | San Benito County In San Juan Bautista At The Washington Street Undercrossing | 100 | 100 | 779010.75 | 737850 | 757650 | 47987 | 2025-09-25 | 2023-03-24 | 2023-03-03 | 2025-10-03 |  | 525 | 0 | 595 | 0 |  | X
05 | 05-344904 | 344904 | 05-SBT-156-3.0/8.2 | HE13 | ACNH-P156- (024)EHIPL-6205- (029) | A. Teichert & Son, Inc. Dba Teichert Construction | 400 Sunrise Ave. Suite 300 | Roseville Ca 95661 | 9167576400 | 8054416931 | 8115 Prunedale North Road | Prunedale, Ca 93907 | Nash Munes | 92803.2 | 882493.02 | 0 | 0 | 2025-10-20 | Widen 2 To 4 Lanes San Jaun | On State Route 156 In San Benito County, In And Near San Juan Bautista From The Alameda St To 0.2 Mi East Of Fourth Street/Busine | 100 | 96 | 85555497.65 | 70580000 | 87650822.06 | 42745 | 2024-08-14 | 2022-06-29 | 2022-06-10 |  |  | 490 | 0 | 480 | 0 |  | X
05 | 05-1S9204 | 1S9204 | 05-SCR-1-3.5/3.9 |  |  | Granite Construction Company | 580 West Beach Street | Watsonville, Ca 95076 |  | 8314274706 | 140 Dubois Street, Suite "E" | Santa Cruz, Ca 95060 | Nguyen, Ian | 0 | 55027.7 | 0 | 0 | 2025-10-20 | Repair Culvert,Restore Site & Trfc Control | Replace Culvert, Restore Site & Trfc Ctrl Repair Sinkhole,Slurry Backfill, Hma And Traffic Control Dirs Efa 05A | 100 | 8 | 401497.57 | 26000 | 5185000 | 59495 | 2026-02-24 | 2025-08-21 | 2025-06-01 |  |  | 185 | 0 | 180 | 0
05 | 05-1P1804 | 1P1804 | 05-SCR-1-5.0/8.2 |  | HSNH-P001- (699)E | Granite Rock Company | 5225 Hellyer Avenue, Suite 22 | San Jose Ca 95138 |  | 8312626572 | 1529 Hwy 68 | Monterey, Ca 93940 | Tyler Lavering | 134161.15 | 17383.26 | 0 | 0 | 2025-10-20 | Shoulders Widening, Roadway Excavation, Hm | Santa Cruz County From 0.9 Mile North Of Buena Vista Drive Undercrossing To 0.2 Mile South Of Rob Roy Junction Overcrossing | 100 | 91 | 3335418.78 | 3606826 | 3634209.26 | 57456 | 2025-10-20 | 2024-10-01 | 2024-09-04 |  | S | 100 | 0 | 90 | 0 |  | X
05 | 05-0C7334 | 0C7334 | 05-SCR-1-10.5/13.4 | HE13 |  | Granite Construction Company | 580 W Beach Street | Watsonville Ca 95076 | 8317287561 | 8055504651 | 140 Dubois St, Ste E | Santa Cruz, Ca 95060 | Nnam, Martin | 821713.37 | 12738.7 | 0 | 0 | 2025-10-20 | Construct Overcrossing And Auxiliary Lane. | Santa Cruz County In And Near City Of Capitola From State Park Drive Overcrossing To 0.2 Mile North Of Bay Avenue Undercrossing | 23 | 55 | 40486923.49 | 72398200.21 | 74965793.44 | 51348 | 2026-06-25 | 2023-07-24 | 2023-06-29 |  |  | 305 | 0 | 1335 | 0 |  | X
05 | 05-0C7324 | 0C7324 | 05-SCR-1-13.6/14.9 |  | ACNH-P001- (675)E | Granite Construction Company | 580 West Beach Street | Watsonville Ca 95076 | 8317636100 | 8055504651 | 140 Dubois Street Suite E | Santa Cruz Ca 95060 | Nnam, Martin | 566240 | 0 | 0 | 0 | 2025-10-20 | Construct Auxiliary Lanes And | 41St Avenue To Soquel Avenue Auxiliary Lanes (Near The City Of Santa Cruz And Capitola, From 41St Avenue To Soquel Avenue. | 38 | 95 | 33396201 | 28994748.81 | 33782181.72 | 45444 | 2026-03-30 | 2022-11-16 | 2022-10-14 |  |  | 446 | 0 | 1170 | 0 |  | X
05 | 05-1Q9404 | 1Q9404 | 05-SCR-1-33.0/33 | 20.20.201130 |  | Serafix Engineering Contractors, Inc | 7 Crow Canyon Ct Ste 250 | San Ramon, Ca 94583 |  | 8314274706 | 140 Dubois St Ste E | Santa Cruz, Ca 95060 | Nguyen, Ian | 0 | 0 | 0 | 0 | 2024-04-20 | Repair Emankment | In Santa Cruz Cnty Rte 001 @ Pm 33.0 Repair Embankment Provide Temp Erosion Control. Provide Traffic Control Dirs Efa 05A2632 | 50 | 19 | 776071.86 | 2250 | 4135000 | 52185 | 2024-09-20 | 2023-06-02 | 2023-03-10 |  |  | 50 | 0 | 100 | 0 |  | X
05 | 05-1Q9904 | 1Q9904 | 05-SCR-1-360.0/37.5 | 20.20.201130 |  | Serafix Engineering Contractor | 7 Crow Canyon Ct, Ste 250 | San Ramon, Ca 94583 |  | 8314274706 | 140 Dubois Street, Suite E | Santa Cruz, Ca 95060 | Nguyen, Ian | 0 | 0 | 0 | 0 |  | Clearing/Hauling Slide Debris. Traffic Ctl | Clear And Hauling Slide Debris.Traffic Ctlclear Debris Catchment. Repair Rocknet Sysclear/Haul Slide Debris. Traffic Control Dirs | 0 | 0 | 0 | 2305 | 446000 | 60104 | 2026-01-06 | 2025-09-30 | 2025-09-15 |  |  | 0 | 0 | 75 | 0
05 | 05-1Q0804 | 1Q0804 | 05-SCR-1-/0 | 20.20.201130 |  | Granite Construction Company | 580 West Beach Street | Watsonville, Ca 95076 | 8317636100 | 8314274706 | 140 Dubois St Ste E | Santa Cruz, Ca 95060 | Nguyen, Ian | 0 | 0 | 0 | 0 | 2025-07-05 | Clearing/Hauling Slide & Bridge Debris | Santa Cruz Cnty On Rts 1 & 9 @ Var P.M. Clearing & Hauling Slide & Bridge Debris. Repair Washout. Temp Traffic Control Dirs Efa 05 | 100 | 99 | 17888415.93 | 6500 | 18000000 | 47424 | 2025-08-20 | 2023-03-17 | 2022-12-31 |  |  | 340 | 0 | 200 | 0 |  | X
05 | 05-1G9504 | 1G9504 | 05-SCR-9-9.0/25.5 |  | PTST-S009- (029)E | Gordon N. Ball, Inc. | 1777 Oakland Blvd. Suite 300 | Walnut Creek Ca 94596 | 9258385675 | 8057486095 | 140 Dubois Street Ste E | Santa Cruz, Ca 95060 | Nguyen, Ian | 82420 | 0 | 0 | 0 | 2025-10-20 | Drainage System Upgrades And Slope Stabili | Santa Cruz County Near Ben Lomond At Various Locations From Scenic Way To 4.7 Miles North Of The Northern Junction Of Routes 9/236 | 100 | 2 | 184295 | 10244158 | 10279158 | 59235 | 2027-09-01 | 2025-07-03 | 2025-06-13 |  |  | 520 | 0 | 520 | 0
05 | 05-1S3604 | 1S3604 | 05-SCR-9-12.1/12.1 | 20.20.201130 |  | Granite Constructions Company | 580 W. Beach Street | Watsonville, Ca95076 |  | 8314274884 | 140 Dubois Street, Suite "E" | Santa Cruz, Ca 95060 | Nguyen, Ian | 0 | 65518.08 | 0 | 0 | 2025-10-05 | Replace Retaining Wall, Culvert & Tc | Prospect Ave Retaining Wall In Sc On Rte 9Replace Retaining Wall & Culvert. Tc Replace Retaining Wall, Culvert & Trfc Ctldirs Efa | 48 | 20 | 927401.45 | 23500 | 4685000 | 57068 | 2026-01-20 | 2025-01-16 | 2024-12-02 |  |  | 120 | 0 | 250 | 0 |  | X
05 | 05-1T3904 | 1T3904 | 05-SCR-17-8.4/8.4 | 20.20.201130 |  | Granite Construction Company | 580 West Beach Street | Watsonville, Ca 95076 | 8317636100 | 8314274706 | 140 Dubois Street, Suite "E" | Santa Cruz, Ca 95060 | Nguyen, Ian | 0 | 0 | 0 | 0 |  | Grind/Rep Damaged Pavement & Rep. Wall | Grind And Replace Damaged Pavement Repair Cidh Retaining Wall Reconstruct Guardrail And Traffic Control Dirs Efa 05A | 0 | 0 | 0 | 5860 | 1157000 | 60137 | 2026-01-09 | 2025-10-30 | 2025-10-14 |  |  | 0 | 0 | 50 | 0
05 | 05-1Q6904 | 1Q6904 | 05-SCR-35-3.0/3 | 20.20.201130 |  | Case Pacific Company | 2121 Ardmore Rd | Paso Robles, Ca 93446 | 8052378851 | 8314274706 | 140 Dubois Street Ste E | Santa Cruz, Ca 95060 | Nguyen, Ian | 0 | 0 | 0 | 0 | 2025-09-20 | Install Soldier Pile Wall | Santa Cruz Cnty On Rte 35 At Pm 3.0 Install Soldier Pile Wall Restore Site. Provide Temp Traffic Control Dirs Efa 05A | 100 | 92 | 4115947.73 | 7500 | 4472750 | 47425 | 2025-10-20 | 2023-03-22 | 2023-01-09 | 2025-10-23 |  | 220 | 0 | 150 | 0 |  | X
05 | 05-1P5304 | 1P5304 | 05-SCR-129-1.1/L1.5 |  |  | Bortolussi & Watkin, Inc. | 77 Larksput Street | San Rafael Ca Ca 94901 |  | 8055343065 | 8115 Prunedale North Road | Prunedale, Ca 93907 | Bailey, Jessica | 0 | 28454.07 | 0 | 0 | 2025-09-20 | Planting, Irrigation Work And Transportati | Santa Cruz County In Watsonville On Route 129 From Locust Street To Main Street And On Route 152 From Holm Road To Freedom Bouleva | 77 | 95 | 1157953.8 | 1129763 | 1204283.53 | 48744 | 2025-09-30 | 2023-04-24 | 2023-03-10 |  |  | 277 | 0 | 360 | 0 |  | X
05 | 05-1S3804 | 1S3804 | 05-SCR-152-1.3/T1.5 | 20.20.201130 |  | Granite Rock Company | 5225 Hellyer Ave. Suite 220 | San Jose, Ca 95138 | 4085741400 | 8314274706 | 140 Dubois Street, Suite "E" | Santa Cruz, Ca 95060 | Nguyen, Ian | 0 | 0 | 0 | 0 |  | Paving,Sidewalk,Curb/Gutter&Const Drainage | Excavation And Place Lightweight Fill Paving, Sidewalk, Curb/Gutter Construct And Modify Drainage Dirs Efa 05A | 0 | 0 | 0 | 25850 | 25850 | 60136 | 2026-07-03 | 2025-10-27 | 2025-09-12 |  |  | 0 | 0 | 150 | 0
05 | 05-1S2804 | 1S2804 | 05-SLO-0-/0 | 20.20.201130 |  | Central Coast Fence Inc. | 540 S. 4Th Street | Grover Beach, Ca 93433 |  | 8059221611 | 2053 Preisker Lane, Suite E | Santa Maria, Ca 93454 | Reed, Albert | 0 | 152378.79 | 0 | 0 | 2025-10-20 | Replace Fence&Install Securty Cameras | Slo&Sb Co Maint. Stations Security Improvereplace Fence&Install Security Cameras Security Improvements At Maint. Stations Dirs Efa | 100 | 82 | 1711796.97 | 10450 | 2075000 | 56767 | 2025-10-20 | 2024-09-06 | 2024-06-03 |  |  | 224 | 0 | 100 | 0
05 | 05-492864 | 492864 | 05-SLO-1-6.4/67.2 |  |  | Hanford Applied Restoration & Conservation | 755 Baywood Drive, Suite 380 | Petaluma Ca 94954 |  | 8054712102 | 775 Arlington St. | Cambria,Ca 93428 | Silva,Rick | 17600 | 0 | 0 | 0 | 2025-10-20 | Landscape Planting, Wetland Mitigation And | San Luis Obispo County About 9 Miles Northof San Siemon From 0.3 Mile North Of Piedras Blancas Lighthouse Road To 0.3 Mile North O | 13 | 73 | 3685721.44 | 4982635 | 5003699.74 | 55847 | 2025-10-20 | 2024-05-22 | 2024-04-22 |  |  | 159 | 0 | 1215 | 0 |  | X
05 | 05-1P5354 | 1P5354 | 05-SLO-1-12.1/12.2 |  |  | R. Burke Corporation | 865 Capitolio Way | San Luis Obispo Ca 93401 |  | 5599774632 | 2053 Preisker Ln Def | Santa Maria Ca 93454 | Reed, Al/Gaston, Phil | 5400 | 0 | 0 | 0 | 2025-09-20 | Irrigation, Planting And Concrete Work. | San Luis Obispo County At Oceano At Beach Street And Seventeenth Street | 58 | 97 | 1446301.89 | 1402634.6 | 1478722.01 | 53844 | 2026-08-20 | 2023-11-17 | 2023-09-06 |  |  | 331 | 0 | 570 | 0 |  | X
05 | 05-1Q0604 | 1Q0604 | 05-SLO-1-12.6/12.7 | 20.20.201130 |  | Souza Engineering Contracting,Inc. Dba Souza Construction | Po Box 3810 | San Luis Obispo, Ca 93403 | 8055493406 | 8059221611 | 2053 Preisker Lane Ste E | Santa Maria, Ca 93454 | Reed, Albert/Gaston, Phil | 0 | 0 | 0 | 0 | 2025-06-11 | Repair Seismic Damper Block On Bridge | Slo Cnty Route 001 Bridge 49-12. Repair Seismic Damper Block & Void. Restore Asphtconcrete Shoulder. Install Ue Determent Dirs Efa | 22 | 28 | 195113.8 | 3500 | 685000 | 46884 | 2025-06-11 | 2023-02-15 | 2022-12-13 |  |  | 11 | 0 | 50 | 0 |  | X
05 | 05-1N3804 | 1N3804 | 05-SLO-1-17.3/0 |  |  | Lamassu Utility Services, Inc. | 3193 Enterprise Court | Loomis Ca 95650 |  |  | 3230 Riverside Avenue #130 | Paso Robles, Ca 93446 | Andrew Borelli | 153085.7 | 0 | 0 | 0 | 2025-10-20 | Cured-In-Place Pipeliner And Culvert Repla | San Luis Obispo County In San Luis Obispo At Foothill Boulevard | 56 | 16 | 153085.7 | 932292.55 | 932292.55 | 59257 | 2025-11-10 | 2025-06-26 | 2025-06-10 |  |  | 25 | 0 | 45 | 0 |  | X
05 | 05-3307C4 | 3307C4 | 05-SLO-41-44.5/45.3 | HE13 |  | Guy F Atkinson Construction Llc | 611 Anton Blvd, Suite 1100 | Costa Mesa, Ca 92626 | 7142871356 | 8053935820 | 102 S Whitley Gardens Dr | Paso Robles, Ca 93446 | R,Eric/Harrington,Brian | 1615246.85 | 38471.06 | 16489.37 | 0 | 2025-10-20 | Convert To A 4 Lane Expressway | San Luis Obispo County At And Near Cholameon Route 41 From Route 41/46 Separation To0.8 Mile North Of Route 41/46 Separation And O | 46 | 84 | 129430510.33 | 148301868.03 | 152706603.08 | 47545 | 2025-04-16 | 2023-03-03 | 2023-03-03 |  |  | 387 | 0 | 850 | 0 |  | X
05 | 05-1S4804 | 1S4804 | 05-SLO-46-4.3/5.1 | 20.20.201130 |  | Souza Engineering Cont. Inc. Dba Souza Construction | P.O. Box 3810 | San Luis Obispo, Ca 93403 |  | 8057482342 | 3230 Riverside Avenue, Suite 30 | Paso Robles, Ca 93446 | Iman, Hassan | 0 | 202265.26 | 0 | 0 | 2025-10-05 | Repair Slipouts,Damaged Pavement & Tc | Repair Slipouts, Repair Pavement, Tc Slipouts, Damaged Pavement & Traffic Ctrl Repair Slipouts,Damaged Pavement & Tc Dirs Efa/05A | 0 | 66 | 8082062.62 | 8500 | 12285000 | 57095 | 2025-10-31 | 2025-02-05 | 2025-01-15 |  |  | 0 | 0 | 50 | 0 |  | X
05 | 05-1Q03U4 | 1Q03U4 | 05-SLO-46-60.3/60.8 |  | STPL-6205- (033)000 | Papich Construction Company, Inc. | 398 Sunrise Terrace | Arroyo Grande Ca 93420 |  | 8053313023 | 102 S Whitley Gardens Dr | Paso Robles, Ca 93446 | R, Eric/Borrelli,Andrew | 197865.02 | 0 | 0 | 0 | 2025-10-20 | Vertical Curve And Extend Existing Truck C | San Luis Obispo And Kern Counties Near Cholame From 2.0 Miles East Of Antelope Road To 0.4 Mile East Of The Kern County Line. | 62 | 71 | 3247470.94 | 4417997 | 4554430.04 | 57097 | 2026-01-29 | 2025-02-05 | 2024-12-13 |  |  | 111 | 0 | 180 | 0 |  | X
05 | 05-1J9704 | 1J9704 | 05-SLO-58-1.8/6.9 |  |  | Calportland Construction | 1625 East Donovan Rd | Santa Maria Ca 93456 | 8053453400 | 8055503058 | 3230 Riverside Aveste 130 | Paso Robles, Ca 93446 | Michael Schmidt | 1091335.03 | 0 | 0 | 0 | 2025-10-20 | Pavement Preservation, Drainage Improvemen | San Luis Obispo County In And Near Santa Margarita From I Street To State Route 229. | 57 | 43 | 2930464.83 | 6697059.3 | 6838550.6 | 57375 | 2026-12-09 | 2025-03-21 | 2025-03-05 |  |  | 77 | 0 | 135 | 0 |  | X
05 | 05-1Q4704 | 1Q4704 | 05-SLO-58-51.0/57.2 |  |  | Griffith Company | 3050 E. Birch St | Brea Ca 92821 |  | 8055503058 | 3230 Riverside Ave Suite 130 | Paso Robles Ca 93446 | Michael Schmidt | 218393.78 | 0 | -13810.13 | 0 | 2025-10-20 | Partial Depth Recycling And Overlay With R | San Luis Obispo County About 16 Miles Westof Mckittrick From 0.3 Mile East Of Boulder Creek Road To Kern County Line. | 88 | 95 | 4370495.98 | 4454155 | 4513599.87 | 56574 | 2025-10-14 | 2024-10-16 | 2024-09-17 |  |  | 75 | 0 | 85 | 0 |  | X
05 | 05-1J8604 | 1J8604 | 05-SLO-101-7.8/16.5 |  | ACNH-Q101- (432)E | Papich Construction Company, Inc. | 398 Sunrise Terrace | Arroyo Grande Ca 93420 |  | 8059221611 | 2053 Preisker Lane, Suite E | Santa Maria Ca 93454 | Albert Reed Sr/Phil Gaston Are | 1216912.37 | 548.39 | 0 | 642000 | 2025-10-20 | Cold Plane Ac Pavement, Rhma-G, Drainage S | San Luis Obispo County In And Near Arroyo Grande And Pismo Beach From Los Berros Road Undercrossing To Pismo Creek Bridge | 12 | 28 | 9002623.5 | 31975207 | 32594337.04 | 57337 | 2027-09-20 | 2025-03-12 | 2025-02-12 |  |  | 70 | 0 | 585 | 0 |  | X
05 | 05-1N3404 | 1N3404 | 05-SLO-101-28.6/29.6 |  | HSNH-Q101- (433)E | Souza Engineering Contracting,Inc. Dba Souza Construction | 4027 Santa Fe Road | San Luis Obispo Ca 93401 |  | 8054712102 | 775 Arlington St. | Cambria, Ca 93428 | Silva, Rick | 491892.74 | 0 | 0 | 16000 | 2025-10-20 | Minor Concrete, Vegetation Control, Guardr | San Luis Obispo County At Various Locations From Broad Street Exit 202B To California Boulevard Exit 203C. | 20 | 37 | 773120.84 | 2082242 | 2102242 | 58295 | 2025-12-31 | 2025-05-20 | 2025-04-29 |  |  | 43 | 0 | 215 | 0 |  | X
05 | 05-1J7804 | 1J7804 | 05-SLO-101-61.7/62.1 |  | HSNH-Q101- (429)E | Calportland Construction | 1625 East Donovan Rd | Santa Maria Ca 93456 |  | 8055503058 | 3230 Riverside Ave., #130 | Paso Robles, Ca 93446 | Schmidt, Michael | 350579.68 | 98933.98 | -4644.64 | 0 | 2025-10-20 | Construct Undercrossing, Structural Concre | San Luis Obispo County Near Paso Robles From 0.7 Mile North Of Exline Road To 1.0 Mile South Of Monterey Road | 68 | 56 | 7038211.24 | 12198939.36 | 12603291.11 | 56683 | 2026-02-13 | 2024-11-08 | 2024-10-22 |  |  | 169 | 0 | 250 | 0 |  | X
05 | 05-1S9304 | 1S9304 | 05-SLO-101-250.0/85 | 20.20.201130 |  | John Madonna Construction Company Inc. | Po Box 5310 | San Luis Obispo, Ca 93403 | 8055437751 | 8056108212 | 2053 Preisker Lane, Ste E | Santa Maria, Ca 93454 | Moreno, Arturo | 0 | 104454.41 | 0 | 0 | 2025-10-20 | Repair/Clear Fire Damage And Traffic Ctrl | Rep. Burnt Drainage Systems, Rep.Guardrailclear Fire Debris From Inlets/Ditch Temp. Traffic Control Dirs Efa 05A | 52 | 1 | 104454.41 | 38000 | 7585000 | 60095 | 2025-12-30 | 2025-10-02 | 2025-08-03 |  |  | 52 | 0 | 100 | 0 |  | X
05 | 05-1R2904 | 1R2904 | 05-VAR--/0 |  |  | Truesdell Corporation Of California, Inc. | 1310 W. 23Rd Street | Tempe Az 85282 |  | 8057210091 | 35 S. La Patera Lane, Suite E | Goleta, Ca 93117 | Chhay, Alis/Doom, Trevor | 324621.5 | 39767.05 | 0 | 0 | 2025-10-20 | Bridge Deck Repairs, Polyster Concrete Ove | Santa Barbara County At Various Locations. | 97 | 96 | 2128798.3 | 2181181 | 2161271.07 | 58015 | 2025-10-22 | 2025-04-21 | 2025-04-02 |  |  | 68 | 0 | 70 | 0 |  | X
06 | 06-1G8204 | 1G8204 | 06-FRE-33-46.8/47.4 |  |  | Archer Civil Construction, Llc | 1353 South J Street | Tulare Ca 93274 | [5 empty] | 2586041.35 | 0 | 0 | 0 | 2025-10-20 | Partial Depth Recycling And Hma. | Fresno County In And Near Mendota From 0.4Mile North Of Kamm Avenue To Mountain Viewavenue And From Adams Avenue To Belmont Avenue | 43 | 68 | 2586041.35 | 3782111.17 | 3782111.17 | 58555 | 2025-11-18 | 2025-06-03 | 2025-04-01 |  |  | 15 | 0 | 35 | 0 |  | X
06 | 06-0X3004 | 0X3004 | 06-FRE-33-69.4/71.5 | HA22 | ACST-S033- (093)E | Bay Cities Paving & Grading, Inc. | 1450 Civic Ct Bldg B #400 | Concord Ca 94520 |  | 5594175927 | 90 W. Ashlan Avenue, Ste 110 | Clovis, Ca 93612 | Din Dadawalla | 13186.5 | 117954.24 | 0 | 0 | 2025-10-20 | Replace Roadway Pavement. | Fresno County In And Near Firebaugh From Morris Kyle Drive To Lyon Avenue | 100 | 95 | 13445195.27 | 13443175.09 | 13974558.14 | 55408 | 2025-10-23 | 2024-03-11 | 2024-02-06 |  |  | 196 | 0 | 150 | 0 |  | X
06 | 06-1E7604 | 1E7604 | 06-FRE-41-21.1/32.2 |  |  | California Turf And Landscaping | 7726 N First St Ste 158 | Fresno Ca 93720 |  | 5599775551 | 90 W Ashlan Ave, Suite 110 | Clovis, Ca 93612 | Chantha Chap | 34639.85 | 0 | 0 | 0 | 2025-09-20 | Transportation Art, Irrigation, And Planti | Fresno County In Fresno At Various Locations From 0.5 Mile South Of Jensen Avenue Overcrossing To 0.5 Mile North Of Audubon Drive | 24 | 71 | 1549909.8 | 2183605.3 | 2183605.3 | 56377 | 2026-03-17 | 2024-09-17 | 2024-08-07 |  |  | 80 | 0 | 330 | 0 |  | X
06 | 06-0X7804 | 0X7804 | 06-FRE-41-23.2/31.7 |  | ACNH-P041- (605)E | Ibarra General Engineering Inc | 4325 Tyrolite St | Riverside Ca 92509 | 9093428447 | 5592075363 | 90 West Ashlan Ave, Suite 110 | Clovis, Ca 93612 | Enquanhone, Gashu | 222917.6 | 50000 | 0 | 0 | 2025-10-20 | Construct Slope Paving (Stamped Concrete) | Fresno County In Fresno At Various Locations From Ventura Avenue Viaduct To Friant Road Undercrossing | 98 | 87 | 8855321.47 | 9924538.1 | 10295238.1 | 56119 | 2025-10-30 | 2024-07-17 | 2024-06-04 |  |  | 206 | 0 | 210 | 0 |  | X
06 | 06-1G4504 | 1G4504 | 06-FRE-41-23.7/24.5 |  |  | Cal Valley Construction, Inc. | 5125 N Gates Ave Ste 102 | Fresno Ca 93722 |  | 5592888603 | 90 W. Ashlan Ave, Suite#110 | Clovis, Ca 93612 | Fernando De Alba | 496995.64 | 0 | 0 | 0 | 2025-09-20 | Cold Plane Ac Pavement, And Replace With H | Fresno County In Fresno On Route 41 From Divisadero Street Overcrossing To Route 41/180 Separation And On Route 180 At 0.1 Mile Ea | 93 | 85 | 843703.81 | 979864 | 979864 | 59135 | 2025-09-30 | 2025-06-25 | 2025-05-20 | 2025-10-23 |  | 37 | 0 | 40 | 0 |  | X
06 | 06-1E7304 | 1E7304 | 06-FRE-41-25.3/0 |  |  | California Turf And Landscaping | 7726 N First St Ste 158 | Fresno Ca 93720 |  | 5592888603 | 90 West Ashlan Ave, Suite 110 | Clovis, Ca 93612 | Fernando De Alba | 80319.5 | 0 | 0 | 0 | 2025-10-20 | Prefabricated Building, Wrought Iron Fence | Fresno County In Fresno At Mckinley Avenue | 97 | 48 | 708363.44 | 1470832.4 | 1489682.4 | 56515 | 2025-10-23 | 2024-09-18 | 2024-08-20 |  |  | 116 | 0 | 120 | 0
06 | 06-0W1704 | 0W1704 | 06-FRE-41-27.4/28.5 | HB4N | ACNH-P041- (602)E | Rnr Construction, Inc. | 8589 Thys Court | Sacramento Ca 95828 | 9163790957 | 5592888603 | 90 W. Ashlan Ave, Suite#110 | Fresno Ca 93726 | Fernando De Alba | 3600 | 45776.67 | 0 | 0 | 2025-10-20 | Construct Auxiliary Lane | In Fresno From Northbound On-Ramp From Ashlan Ave To Northbound Off-Ramp To Shaw Ave | 99 | 98 | 15633918.57 | 14990202.5 | 15824169.79 | 45904 | 2025-11-12 | 2022-12-21 | 2022-11-08 |  |  | 408 | 0 | 370 | 43 |  | X
06 | 06-1G0904 | 1G0904 | 06-FRE-41-28.2/28.2 | 20.20.201130 |  | Koch & Koch Inc | 13084 John Bauer Ave | Grass Valley, Ca 95945 |  | 5592544877 | 3240 N Millbrook Ave. | Fresno, Ca 93726 | Mengoni, Mark | 0 | 42750.97 | 0 | 0 | 2025-09-20 | Remove/Replace Pump And Assoc Appurtenance | In Fresno County Along Route 41 Near Pm R28.2 At Pump Plant Between Shaw And Santa Ana Dir'S Emergency F.A. | 83 | 77 | 1461203.01 | 6825 | 1900000 | 52284 | 2025-10-01 | 2023-07-28 | 2023-07-10 |  |  | 25 | 0 | 30 | 0 |  | X
06 | 06-0U4214 | 0U4214 | 06-FRE-99-4.9/7.2 |  |  | Wabo Landscape & Construction,Inc. | 726 Alfred Nobel Drive | Hercules Ca 94547 |  | 5592075363 | 90 W. Ashlan Avenue, Suite 110 | Clovis, Ca 93612 | Gashu Enquanhone | 80075 | 0 | 0 | 0 | 2025-10-20 | Replace Highway Planting And Install Irrig | Fresno County In And Near Selma And Fowlerfrom 0.4 Mile South Of Second Street Undercrossing To 0.7 Mile North Of Floral Avenue An | 14 | 84 | 1534616.12 | 1730273 | 1830273 | 56603 | 2028-10-30 | 2024-10-31 | 2024-09-19 |  |  | 124 | 0 | 880 | 0 |  | X
06 | 06-1G3504 | 1G3504 | 06-FRE-99-233.0/0 | 20.20 201131 |  | Gruen Engineering, Inc. | 12418 Gruen St | Pacoima Ca 91331 |  | 5592888603 | 90 W Ashlan Ave, Suite 110 | Clovis Ca 93612 | De Alba, Fernando | 0 | 0 | 0 | 0 | 2025-06-20 | Repair D06 Materials Lab | Construction And Installation Of New Ceiling, Fume Hoods, Motors, Ducts, Monitoring System, Vent Stacks, Hvac System, Thermostdir | 0 | 10 | 281001.17 | 13775 | 2740000 | 56828 | 2025-07-20 | 2024-12-08 | 2024-12-08 |  |  | 0 | 0 | 65 | 0 |  | X
06 | 06-1F8204 | 1F8204 | 06-FRE-168-39.6/45.7 |  |  | Agee Construction Corporation | 1039 Hoblitt Avenue | Clovis Ca 93612 |  | 5593412795 | 90 West Ashlan Ave, Suite 110 | Clovis, Ca 93612 | Carpenter, Jesse | 504172.33 | 0 | 0 | 0 | 2025-02-20 | Cold Plane Ac Pvmt, Hma (Type A), Paint Tr | Fresno County In And Near Shaver Lake From0.2 Mile West Of Cressman Road To Warbler Road | 100 | 99 | 2669288.11 | 2176983 | 2657930.66 | 55951 | 2025-02-28 | 2024-06-17 | 2024-05-10 | 2025-10-27 |  | 30 | 0 | 30 | 0 |  | X
06 | 06-0Q5204 | 0Q5204 | 06-FRE-168-48.2/0 |  |  | Granite Construction Company | 2716 Granite Court | Fresno Ca 93706 |  | 5592888603 | 90 W. Ashlan Ave, Suite 110 | Clovis, Ca 93612 | Fernando De Alba | 258741.75 | 0 | 0 | 47500 | 2025-10-20 | Place Concrete Barrier And Structural Conc | Fresno County Near Shaver Lake At Stevenson Creek | 20 | 57 | 306241.75 | 533646 | 533646 | 60097 | 2026-01-02 | 2025-07-15 | 2025-06-13 |  |  | 12 | 0 | 60 | 0 |  | X
06 | 06-1F8304 | 1F8304 | 06-FRE-180-43.5/53.6 |  |  | Cal Valley Construction, Inc. | 5125 N Gates Ave Ste 102 | Fresno Ca 93722 |  | 5599397192 | 90 W. Ashlan Suite 110 | Clovis, Ca 93612 | Mustafa, Hamza | 193255 | 0 | 0 | 0 | 2025-09-18 | Cold Plane Ac Pavement, Rhma-G And Hma (Ty | Fresno County Near Kerman From Goldenrod Avenue To Brawley Avenue | 100 | 100 | 3938335.57 | 3714829 | 3714829 | 56153 | 2025-09-18 | 2024-07-19 | 2024-06-11 | 2025-09-22 |  | 45 | 0 | 45 | 0 |  | X
06 | 06-342354 | 342354 | 06-FRE-180-54.1/56 |  |  | Marina Landscape, Inc. | 3707 W. Garden Grove Blvd | Orange Ca 92868 | 7149396600 | 5594175927 | 3240 N. Millbrook | Fresno, Ca 93726 | Din Dadawalla | 3360 | 0 | 0 | 0 | 2025-10-20 | Highway Planting | In And Near Fresno From 0.2 Mile West Of Brawley Avenue To Teilman Avenue | 0 | 0 | 4794310.66 | 5328436.25 | 5329948.24 | 43144 | 2025-12-13 | 2022-07-15 | 2022-05-20 |  |  | 200 | 0 | 950 | 0 | X | X
06 | 06-0X0604 | 0X0604 | 06-FRE-198-.5/19.5 |  | ACST-S198- (077)E | A. Teichert & Son Inc Dba Teichert Construction | 400 Sunrise Blvd. Suite 300 | Roseville Ca 95661 | 9167576400 | 6613034187 | 8530 W Roosevelt Ave | Visalia Ca 93291 | Michael R Garrett | 323216.96 | 0 | 0 | 0 | 2025-10-20 | Remove And Replace Culverts And Cured In P | Fresno County At Various Locations From 1.3 Miles West Of Warthan Creek Overcrossing To 1.7 Miles West Of Firestone Avenue | 25 | 24 | 2077569.33 | 8972350 | 8791490.42 | 55950 | 2026-05-27 | 2024-06-07 | 2024-05-08 |  |  | 49 | 0 | 195 | 0 |  | X
06 | 06-0Y7604 | 0Y7604 | 06-FRE-5506-/0 |  |  | Radman Electric | 25013 Whitman Street #15-S | Hayward Ca 94544 |  | 5599398827 | 90 W Ashlan Ave, Suite 110 | Clovis, Ca 93612 | Mohammed Alqutami | 0 | 0 | 0 | 0 | 2025-09-20 | Modification Of Electrical System. | Fresno County In Fresno At The West Avenuemaintenance Station 1283 North West Avenueand At The District Office 1352 West Oliveaven | 62 | 97 | 1113973.83 | 996500 | 1142693.83 | 56081 | 2025-09-30 | 2024-06-07 | 2024-05-08 |  |  | 37 | 0 | 60 | 0 |  | X
06 | 06-0U5004 | 0U5004 | 06-KER-5-10.2/16 |  | ACIM-005 - (4 )207 | Security Paving Company, Inc. | 3075 Townsgate Road, Suite 20 | Westlake Village Ca 91361 |  | 5599775450 | 1824 Norris Road | Bakersfield, Ca 93308 | Robert Decker | 752495.19 | 0 | 0 | 0 | 2025-10-20 | Individual Slab Replacement (Rsc) And Hma | Kern County At And Near Wheeler Ridge Fromgrapevine Undercrossing To Route 5/99 Separation | 100 | 88 | 19258136.85 | 19016164 | 21167444 | 56324 | 2025-12-31 | 2024-09-10 | 2024-08-29 |  |  | 153 | 0 | 135 | 0 |  | X
06 | 06-0X3304 | 0X3304 | 06-KER-5-/4.4 |  | ACIM-005 - (4 )206 | Security Paving Company, Inc. | 13170 Telfair Ave | Sylmar Ca 91342 |  | 5599774455 | 1824 Norris Road | Bakersfield, Ca 93308 | James Burford | 18506.89 | 0 | 0 | 0 | 2025-10-31 | Replace Roadway Pavement With Hma And Conc | Kern County At And Near Lebec From Los Angeles County Line To Grapevine Creek Bridge | 100 | 100 | 18937836.51 | 19069000 | 19193000 | 55388 | 2025-10-31 | 2023-11-30 | 2023-10-23 | 2025-10-31 |  | 286 | 0 | 220 | 999 |  | X
06 | 06-0X2404 | 0X2404 | 06-KER-33-21.8/39.8 |  |  | Doja, Inc. | 5050 Mission Blvd | Ontario Ca 91762 |  | 5599775450 | 1824 Norris Road | Bakersfield, Ca 93308 | Bob Decker | 167832.7 | 0 | 0 | 0 | 2025-10-20 | Structural Concrete And Rcp Drainage Culve | Kern County At Various Locations From 0.9 Mile South Of Henry Road To 0.2 Mile Northof Cymric Road (North) | 54 | 18 | 883754.78 | 5100000 | 4982101.1 | 57595 | 2026-02-02 | 2025-04-02 | 2025-03-07 |  |  | 86 | 0 | 160 | 0 |  | X
06 | 06-0Y1304 | 0Y1304 | 06-KER-33-40.4/59.3 |  | ACST-S033- (094)E | Granite Construction Company | 3005 James Road | Bakersfield Ca 93308 |  | 5599051299 | 1824 Norris Rd | Bakersfield, Ca 93308 | Jake Garcia | 3325858.66 | 20374.67 | 343270.1 | 0 | 2025-10-20 | Cold Plane, Place Hma And Rhma-G, And Repl | Kern County About 8 Miles North Of Mckittrick From Cymric Wash Bridge To 0.8 Mile South Of Route 46 | 77 | 70 | 20705159.96 | 27529328 | 29699319.34 | 56073 | 2026-02-10 | 2024-07-10 | 2024-06-20 |  |  | 254 | 0 | 200 | 128 |  | X
06 | 06-0Q2814 | 0Q2814 | 06-KER-99-23.6/28.4 |  |  | Griffith Company | 1128 Carrier Parkway Ave | Bakersfield Ca 93308 |  | 6613320538 | 1824 Norris Road | Bakersfield, Ca 93308 | Amrit Brar | 5400 | 0 | 0 | 0 | 2025-09-20 | Replacement Planting. | Kern County In Bakersfield From Palm Avenue Overcrossing To Beardsley Canal Bridge | 0 | 0 | 5507876.64 | 5388904 | 6223405.89 | 47604 | 2027-10-31 | 2023-03-15 | 2023-02-16 |  |  | 284 | 0 | 1000 | 0 | X | X
06 | 06-1G8004 | 1G8004 | 06-KER-99-29.4/33.1 |  |  | Griffith Company | 3050 E. Birch St | Brea Ca 92821 |  | 6613320538 | 1824 Norris Road | Bakersfield, Ca 93308 | Amrit Brar | 299223.17 | 0 | 0 | 0 | 2025-10-20 | Cold Plane Ac Pavement, Remove Concrete Pa | Kern County Near Bakersfield From 0.5 Milesouth Of Route 65/99 Separation To 0.7 Mile North Of Lerdo Canal Bridge | 84 | 90 | 2787726.47 | 3022735 | 2998162.3 | 57635 | 2025-10-31 | 2025-04-10 | 2025-03-27 |  |  | 46 | 0 | 55 | 0 |  | X
06 | 06-1E7804 | 1E7804 | 06-KER-99-49.3/50.4 |  |  | Griffith Company | 12200 Bloomfield Ave | Santa Fe Springs Ca 90670 |  | 6613335825 | 1824 Norris Road | Bakersfield, Ca 93308 | Amarjit Dhaliwal | 0 | 0 | 0 | 0 | 2025-09-20 | Wrought Iron Fence, Planting And Irrigatio | Kern County In Mcfarland And Delano From 0.1 Mile South Of Sherwood Avenue To 0.1 Mile North Of Perkins Avenue And From Route 155/ | 99 | 100 | 2081408.05 | 2069908.05 | 2106408.05 | 54204 | 2025-09-25 | 2023-11-14 | 2023-10-13 |  |  | 326 | 0 | 330 | 0 |  | X
06 | 06-0W79U4 | 0W79U4 | 06-KER-99-56.4/57.6 |  | ACNH-P099- (689)E | Security Paving Company, Inc. | 3075 Townsgate Road, Suite 20 | Westlake Village Ca 91361 |  | 5599051299 | 1824 Norris Road | Bakersfield, Ca 93308 | Jake Garcia | 0 | 219252 | 0 | 1837500 | 2025-10-20 | Rdwy Exc, Hma, Aggregate Base, Crcp, Sign | Kern And Tulare Counties In And Near Delano From 0.2 Mile South Of Cecil Avenueovercrossing To 0.7 Mile North Of Avenue 100 Overcr | 14 | 13 | 17351120.76 | 130076704.7 | 130172157.52 | 57875 | 2027-05-12 | 2025-04-24 | 2025-04-10 |  |  | 65 | 0 | 450 | 1 |  | X
06 | 06-1H0604 | 1H0604 | 06-KER-155-17.8/39.6 |  |  | Lamassu Utility Services, Inc. | 3193 Enterprise Court | Loomis Ca 95650 |  | 6613320538 | 1824 Norris Road | Bakersfield, Ca 93308 | Amrit Brar | 0 | 0 | 0 | 0 |  | Remove And Replace Culverts, And Cured-In- | Kern County At Various Locations From 6.7 Miles East Of Route 65 To 0.4 Mile West Ofwhite River Road | 0 | 0 | 0 | 363553.44 | 363553.44 | 60075 |  | 2025-07-22 | 2025-04-23 |  |  | 0 | 0 | 25 | 0
06 | 06-0S0504 | 0S0504 | 06-KER-166-17.5/0 |  |  | Granite Construction Company | 580 W Beach Street | Watsonville Ca 95076 |  | 5599774455 | 1824 Norris Road | Bakersfield, Ca 93308 | James Burford | 232685.45 | 0 | 0 | 0 | 2025-10-20 | Micropiling, Structural Concrete, And Hot | Kern County Near Mettler At California Aqueduct Bridge | 28 | 32 | 2134208.86 | 6183322 | 6556522 | 56518 | 2026-02-26 | 2024-09-10 | 2024-08-23 |  |  | 48 | 0 | 170 | 0 |  | X
06 | 06-0X3804 | 0X3804 | 06-KER-166-/10.2 | HA22 | ACST-S166- (003)E | Griffith Company | 12200 Bloomfield Ave | Santa Fe Springs Ca 90670 |  | 5599774455 | 1824 Norris Road | Bakersfield, Ca 93308 | James Burford | 3680 | 99500 | 0 | 0 | 2025-09-20 | Cold Plane, Place Hma And Concrete Pavemen | Kern County In And Near Maricopa From South Junction Route 33 To 2.3 Miles West Of San Emigdio Creek Bridge | 100 | 97 | 12641025.32 | 12032735 | 13274167.46 | 55508 | 2025-09-21 | 2024-03-22 | 2024-02-28 |  |  | 153 | 0 | 140 | 0 |  | X
06 | 06-0U4304 | 0U4304 | 06-KER-184-8.5/11.6 | HA22 | ACNH-P184- (017)E | Griffith Company | 3050 E. Birch St | Brea Ca 92821 |  | 6613320538 | 1824 Norris Road | Bakersfield, Ca 93308 | Amrit Brar | 59350 | 25825.59 | 0 | 0 | 2025-05-20 | Resurface Lanes And Shoulders. | Kern County In And Near Bakersfield From 0.1 Mile North Of Edison Highway To 0.1 Mile North Of Chase Avenue | 93 | 93 | 16280443.8 | 16812735 | 17337235 | 54444 | 2025-06-30 | 2023-11-30 | 2023-10-26 |  |  | 135 | 0 | 135 | 10 |  | X
06 | 06-1H0504 | 1H0504 | 06-KER-223-12.5/30.1 |  |  | Jabre Contracting, Inc. | 1813 Manzanita Lane | Manhattan Beach Ca 90266 |  | 6613335825 | 1824 Norris Road | Bakersfield, Ca 93308 | Amarjit Dhaliwal | 35675 | 0 | 0 | 0 | 2025-10-20 | Replace Culverts And Cured-In-Place Pipeli | Kern County At Various Locations From 0.5 Mile West Of Adobe Road To 1.9 Miles Southof Route 58 | 10 | 11 | 35675 | 329600 | 329600 | 59535 | 2025-11-14 | 2025-07-29 | 2025-04-29 |  |  | 2 | 0 | 20 | 0 |  | X
06 | 06-1E6704 | 1E6704 | 06-KER-223-20.1/21.1 |  |  | Marina Landscape Inc. | 3707 W Garden Grove Blvd | Orange Ca 92868 |  | 5595131469 | 1824 Norris Road | Bakersfield, Ca93308 | Samuel Garcia | 760 | 0 | 0 | 0 | 2025-06-20 | Planting, Irrigation Work And Thermoplasti | Kern County In Arvin From 0.1 Mile West Ofcomanche Drive To El Tejon Highway | 74 | 99 | 1069975.74 | 436224 | 1068024.63 | 48864 | 2025-11-14 | 2023-04-04 | 2023-03-07 |  |  | 311 | 0 | 310 | 110 |  | X
06 | 06-1G7704 | 1G7704 | 06-KIN-5-16.6/26.7 |  |  | Granite Construction Company | 2716 Granite Court | Fresno Ca 93706 | [5 empty] | 0 | 0 | 0 | 0 |  | Remove And Replace Asphalt Concrete Overla | Kings County In And Near Avenal From Route5/41 Separation To Fresno County Line | 0 | 0 | 0 | 4396049 | 4396049 | 57896 |  | 2025-04-29 | 2025-04-01 |  |  | 0 | 0 | 45 | 0
06 | 06-0W8204 | 0W8204 | 06-KIN-41-28.4/40.1 |  | ACNH- P04- (606)E | Granite Construction Company | 2716 Granite Court | Fresno Ca 93706 |  | 5599776478 | 90 W. Ashlan Avenue, Ste 110 | Clovis, Ca 93612 | Oscar Sherrill | 330023.2 | 71358.83 | 0 | 0 | 2025-10-20 | Cold Plane With Hot Mix Asphalt (Type A) A | Kings County At And Near Stratford From Nevada Avenue To Route 41/198 Separation | 72 | 92 | 14193323.24 | 15123990.6 | 15633530.2 | 55949 | 2025-12-22 | 2024-06-05 | 2024-05-22 |  |  | 108 | 0 | 150 | 0 |  | X
06 | 06-0Y1704 | 0Y1704 | 06-KIN-41-/15.5 |  | ACNH-P041- (607)E | Papich Construction Company, Inc. | 398 Sunrise Terrace | Arroyo Grande Ca 93420 |  | 5599776478 | 90 W. Ashlan Ave Suite 110 | Clovis, Ca 93612 | Sherrill, Oscar | 2200453.93 | 0 | -109860.24 | 80000 | 2025-10-20 | Cold Plane Ac Pvmt, Overlay Hma And Rhma. | Kings County Near Kettleman City From The Kern County Line To 0.8 Mile South Of Route 5 | 53 | 66 | 10544518.82 | 16147997 | 16033472 | 57596 | 2026-02-06 | 2025-04-02 | 2025-03-03 |  |  | 82 | 0 | 155 | 0 |  | X
06 | 06-0V1204 | 0V1204 | 06-MAD-99-6.9/7.6 | HA21 | ACNH-P099- (671)E | Security Paving Company, Inc. | 3075 Townsgate Road | Westlake Village Ca 91361 | 8183629200 | 5594175927 | 3240 N. Millbrook Avenue | Fresno, Ca 93726 | Gill, Gurjot (K. Arowosegbe) | 277865.06 | 204888.74 | 0 | 0 | 2025-10-10 | Replace 3 Bridges; Br. No. 41-0065 | In Madera County About 2 Mi. South Of Madera From 0.3 Mi South Of Cottonwood Creek To Avenue 12 Overcrossing. | 100 | 100 | 21826317.41 | 22171328.94 | 23187890.02 | 43264 | 2025-10-10 | 2022-07-20 | 2022-06-22 | 2025-10-14 |  | 555 | 0 | 420 | 0 |  | X
06 | 06-1G5804 | 1G5804 | 06-MPA-41-3.1/3.1 | 20.20.732000 |  | Lee Wilson Electric | P.O. Box 250 | Arroyo Grande Ca 93421 |  | 5599770927 | 3240 N Millbrook Ave | Fresno, Ca 93726 | Gill, Gurjot | 0 | 0 | 0 | 0 |  | Remove And Replace Existing Antenna Pole | In The County Of Mariposa Pm 3.1 At The Fish Camp Rescue Building Dir Order Emergency Fa | 0 | 0 | 0 | 775 | 130000 | 55346 | 2024-08-14 | 2024-01-16 | 2024-01-16 |  |  | 0 | 0 | 15 | 0
06 | 06-0X7004 | 0X7004 | 06-TUL-63-5.8/L8 | HA22 | ACNH-P063- (023)E | Cal Valley Construction, Inc. | 5125 N Gates Ave Ste 102 | Fresno Ca 93722 |  | 5596518317 | 8530 W Roosevelt Ave | Visalia Ca 93291 | Javier Huerta | 1612846.05 | 0 | 0 | 0 | 2025-02-20 | Cold Plane Pavement, Place Rhma-G, Modify | Tulare County In Visalia From 0.2 Mile South Of Caldwell Avenue To Route 63/198 Separation | 84 | 82 | 6211712.79 | 7779370 | 8119062.89 | 54764 | 2025-04-10 | 2023-12-01 | 2023-09-21 |  |  | 117 | 0 | 140 | 0 |  | X
06 | 06-1G7404 | 1G7404 | 06-TUL-63-12.1/21.6 |  |  | Archer Civil Construction, Llc | 1353 South J Street | Tulare Ca 93274 | [5 empty] | 39884.28 | 0 | 0 | 0 | 2025-10-20 | Rumble Strips And Striping. | Tulare County Near Visalia On Route 63 From 0.3 Mile North Of Avenue 326 To 0.5 Mile North Of Avenue 396 And In Porterville On Ro | 83 | 57 | 743855.84 | 1303933.36 | 1303933.36 | 59096 | 2025-10-30 | 2025-06-26 | 2025-05-28 |  |  | 33 | 0 | 40 | 0
06 | 06-1G8104 | 1G8104 | 06-TUL-63-19.2/24.3 |  |  | Archer Civil Construction, Llc | 1353 South J Street | Tulare Ca 93274 | [5 empty] | 77180.23 | 0 | 0 | 0 | 2025-10-20 | Hma (Type A), Rhma-G, And Cold Plane Ac Pa | Tulare County At And Near Cutler And Orosifrom Avenue 384 To Avenue 422 | 55 | 42 | 621520.37 | 1489476.32 | 1489476.32 | 59315 | 2025-11-17 | 2025-06-09 | 2025-04-28 |  |  | 22 | 0 | 40 | 0 |  | X
06 | 06-1E8004 | 1E8004 | 06-TUL-63-21.7/24.3 |  |  | Vss International, Inc. | 3785 Channel Drive | West Sacramento Ca 95691 | 9163731500 | 6613034187 | 8530 W Roosevelt Ave | Visalia Ca 93291 | Mike Garrett | 0 | 24363.9 | 0 | 0 | 2025-07-20 | Place Slurry Seal, Thermoplastic Traffic S | Tulare County In Cutler And Orosi From 0.1Mile South Of Avenue 402 To Avenue 422 | 100 | 89 | 1291770.03 | 1375325 | 1491005 | 54124 | 2025-08-01 | 2023-10-31 | 2023-10-10 |  |  | 37 | 0 | 35 | 0 |  | X
06 | 06-1E6904 | 1E6904 | 06-TUL-99-9.8/40.7 |  |  | Marina Landscape Inc. | 3707 W Garden Grove Blvd | Orange Ca 92868 | 7149396600 | 6613034187 | 8530 W Roosevelt Ave | Visalia Ca 93291 | Michael R Garrett | 3045.5 | 0 | 0 | 0 | 2025-10-20 | Landscape Planting, Irrigation, And Plant | Tulare County In And Near Teviston At Various Locations From 0.1 Mile North Of Avenue 76 To 0.1 Mile South Of Betty Drive | 79 | 93 | 530992.87 | 445462.5 | 569319.71 | 47266 | 2026-07-01 | 2023-03-03 | 2023-02-06 |  |  | 629 | 0 | 800 | 0 |  | X
06 | 06-1G8404 | 1G8404 | 06-TUL-99-13.5/19.5 |  |  | Archer Civil Construction, Llc | 1353 South J Street | Tulare Ca 93274 | 5593721838 | 5592867590 | 8530 W Roosevelt Ave | Visalia Ca 93291 | Javier Huerta | 791041.35 | 0 | 0 | 28028 | 2025-10-20 | Cold Plane Ac Pavement And Hma. | Tulare County At Tipton From 0.1 Mile North Of Road 124 On Ramp To Avenue 152 Overcrossing | 73 | 38 | 1274851.41 | 3380065.17 | 3380065.17 | 57735 | 2025-11-12 | 2025-04-15 | 2025-03-14 |  |  | 40 | 0 | 55 | 0 |  | X
06 | 06-0X2504 | 0X2504 | 06-TUL-99-20.8/53.1 |  | PTNH-P099- (691)E | Granite Construction Company | 580 W Beach Street | Watsonville Ca 95076 |  | 5592867590 | 8530 W Roosevelt Ave | Visalia Ca 93291 | Javier Huerta | 60172.74 | 0 | 0 | 0 | 2025-10-20 | Repair And Replace Culverts And Install Cu | Tulare County At Various Locations From 1.4 Miles North Of Avenue 152 Overcrossingto 0.7 Mile South Of Mendocino Avenue Overcrossi | 60 | 82 | 1778279.51 | 2117803.5 | 2167803.5 | 56827 | 2025-12-08 | 2024-12-10 | 2024-11-12 |  |  | 48 | 0 | 80 | 0 |  | X
06 | 06-0U8804 | 0U8804 | 06-TUL-99-26.3/27.6 |  | ILDL-6206- (033)000 | Security Paving Company, Inc. | 13170 Telfair Ave | Sylmar Ca 91342 |  | 5592867590 | 8530 W Roosevelt Ave | Visalia Ca 93291 | Javier Huerta | 0 | 0 | 0 | 0 | 2025-10-20 | Construct Interchange. | Tulare County In Tulare From 0.9 Mile North Of Avenue 200 Overcrossing To Paige Road Overcrossing | 83 | 65 | 30314107.99 | 45538438 | 46642082.15 | 46924 | 2026-04-02 | 2023-02-17 | 2023-01-23 |  |  | 433 | 0 | 465 | 58
06 | 06-0W9104 | 0W9104 | 06-TUL-99-27.6/30.6 |  | ACNH-P099- (687)E | Granite Construction Company | 580 W Beach Street | Watsonville Ca 95076 |  | 5592508186 | 8530 W Roosevelt Ave | Visalia Ca 93291 | Amir Zamanian | 1642938.72 | 8508.77 | -174466.14 | 0 | 2025-10-20 | Hma, Rhma-G, Jointed Plain Conc Pvmt (Rsc) | Tulare County In And Near Tulare From Paige Avenue Overcrossing To Prosperity Avenue Overcrossing. | 55 | 67 | 14673744.15 | 21213662 | 21144444.15 | 56606 | 2026-03-23 | 2024-10-01 | 2024-09-16 |  |  | 121 | 0 | 220 | 0 |  | X
06 | 06-360304 | 360304 | 06-TUL-99-30.2/35.2 |  |  | Empire Landscaping Inc. | 26945 County Road 97D | Davis Ca 95616 |  | 5592508186 | 8530 W. Roosevelt Ave | Visalia Ca 93291 | Amir Zamanian | 782102 | 0 | 0 | 7000 | 2025-10-20 | Install Irrigation System And Planting. | Tulare County In And Near Tulare From 0.4 Mile South Of Prosperity Avenue Overcrossing To 1.2 Miles South Of Avenue 280 Overcross | 14 | 78 | 1862530 | 2397750 | 2428982.4 | 56029 | 2025-11-04 | 2024-05-17 | 2024-05-03 |  |  | 122 | 0 | 880 | 0 |  | X
06 | 06-360244 | 360244 | 06-TUL-99-30.6/35.2 | HE13 | ACNH-P099- (665)E | Security Paving Company, Inc. | 3075 Townsgate Road | Westlake Village Ca 91361 | 8183629200 | 5596518319 | 8530 W Roosevelt | Visalia Ca 93291 | Huerta Javier | 198982 | 0 | 0 | 0 | 2025-10-20 | 4F To 6F | On Route 99 In Tulare County Near Tulare From Prosperity Ave To 1.2 Miles South Of Avenue 280 Overcrossing (Br No. 46-0195) | 100 | 95 | 55860435.12 | 48856761.4 | 57548856.66 | 41699 | 2025-11-01 | 2021-06-11 | 2021-04-26 |  |  | 766 | 0 | 415 | 0 |  | X
06 | 06-487404 | 487404 | 06-TUL-99-35.8/37.1 |  | 6206-039 - ( )000 | Granite Construction Company | 2716 Granite Court | Fresno Ca 93706 |  | 5592508186 | 8530 W. Roosevelt Ave | Visalia Ca 93291 | Amir Zamanian | 244000 | 43451.6 | 0 | 0 | 2025-10-20 | Replace Bridge Structures And Construct Ro | Tulare County In And Near Visalia From 0.6Mile South Of Avenue 280 Overcrossing To 0.7 Mile North Of Avenue 280 Overcrossing | 0 | 1 | 360053.64 | 66170188 | 67135147.11 | 57297 | 2027-06-23 | 2025-02-12 | 2025-01-14 |  |  | 2 | 0 | 420 | 0 |  | X
06 | 06-0Q4324 | 0Q4324 | 06-TUL-190-13.1/16.6 |  |  | Cal Valley Construction, Inc. | 5125 N Gates Ave Ste 102 | Fresno Ca 93722 | [5 empty] | 0 | 0 | 0 | 0 |  | Hma, Minor Concrete And Jpcp. | Tulare County In And Near Porterville At Various Locations From 0.2 Mile West Of Westwood Street To 0.1 Mile East Of South Main St | 0 | 0 | 0 | 9474093.75 | 9481093.75 | 59519 |  | 2025-07-23 | 2025-06-27 |  |  | 0 | 0 | 140 | 0
06 | 06-1H6904 | 1H6904 | 06-TUL-190-42.7/42.8 | 20.20.201130 |  | Ccfg Construction | 17750 Wards Ferry Rd | Sonora Ca 95370 | 2097434911 | 5599056468 | 8530 Roosevelt Ave | Visalia Ca 93291 | Mandujano, Cesar | 0 | 0 | 0 | 0 |  | Cleaning The Slope And Performing A Half | Constructing Cip/Rc Box Girder (Full Width), Roadway Construction/Excavation, Drainage Systems, Permanent Erosion Control Dir Efa | 0 | 0 | 0 | 152178 | 15430328 | 60116 | 2026-10-04 | 2025-07-30 | 2025-07-14 |  |  | 0 | 0 | 359 | 0
06 | 06-1H6704 | 1H6704 | 06-TUL-190-366.0/0 | 20.20.201130 |  | Chapco Construction Llc | 6000 Mortono Street | Sacramento Ca 95828 |  | 5599056468 | 8530 W Roosevelt Ave | Visalia Ca 93291 | Mandujano, Cesar | 0 | 0 | 0 | 0 |  | Replace Existing Bridge Rail | Replacement Of Existing Bridge Rail On Eb Direction Of Sr 190, Demolition And Reconstruction Of The Overhang, Removal Of The Dirs | 0 | 0 | 0 | 26500 | 2648250 | 60115 | 2026-02-04 | 2025-07-10 | 2025-06-26 |  |  | 0 | 0 | 60 | 0
06 | 06-0X2604 | 0X2604 | 06-TUL-198-1.6/43.9 |  | ACNH-P198- (082)E | Teichert Construction | 3500 American River Dr | Sacramento Ca 95864 | 9167576400 | 6613034187 | 8530 W. Roosevelt Ave | Visalia Ca 93291 | Micahel R Garrett | 184895.51 | 0 | 0 | 0 | 2025-10-20 | Remove, Install, And Repair Drainage Facil | Tulare County In And Near Visalia At Various Locations From 1.6 Miles East Of Kings County Line To 0.2 Mile West Of Sequoia Nation | 89 | 88 | 10761427.57 | 12142114 | 12311304.47 | 56336 | 2025-12-04 | 2024-05-13 | 2024-03-13 |  |  | 250 | 0 | 280 | 0 |  | X
06 | 06-0W90U4 | 0W90U4 | 06-TUL-198-11.6/11.9 |  | ACNH-P216- (007)E | Teichert Construction | 3500 American River Dr | Sacramento Ca 95864 | 9164843011 | 6613034187 | 8530 W Roosevelt Ave | Visalia Ca 93291 | Mike Garrett | 1096305.12 | 0 | 0 | 0 | 2025-10-20 | Hma And Modifying Signal And Lighting Syst | Tulare County In And Near Visalia On Route216 From 0.2 Mile South Of Lovers Lane Undercrossing To 0.2 Mile East Of Mcauliffstreet | 20 | 40 | 9815176.66 | 24704119 | 24813119 | 56605 | 2026-02-12 | 2024-09-13 | 2024-08-29 |  |  | 143 | 0 | 720 | 0 |  | X
06 | 06-0W9704 | 0W9704 | 06-VAR--/0 |  | ACNH-P099- (684)E | Bortolussi & Watkin, Inc. | 77 Larkspur Street | San Rafael Ca 94901 |  | 5592888603 | 90 W. Ashlan Ave, Suite#110 | Clovis, Ca 93612 | Fernando De Alba | 1282725.8 | 92857.98 | 0 | 0 | 2025-10-20 | Planting, Maintaining Existing Planting Ar | Fresno County At Various Locations | 23 | 69 | 9120430.84 | 13106999 | 13282999 | 56118 | 2026-10-09 | 2024-05-15 | 2024-02-23 |  |  | 292 | 0 | 1285 | 0 |  | X
06 | 06-1F9004 | 1F9004 | 06-VAR--/0 |  |  | Archer Civil Construction, Llc | 1353 South J Street | Tulare Ca 93274 | 5593721838 | 5592867590 | 8530 W Roosevelt Ave | Visalia Ca 93291 | Javier Huerta | 105130.6 | 0 | 0 | 0 | 2025-09-20 | Hma (Type A) And Rhma (Gap Graded). | Tulare County At Various Locations | 60 | 3 | 105130.6 | 3460217.26 | 3460217.26 | 59097 | 2025-10-09 | 2025-06-26 | 2025-05-08 |  |  | 27 | 0 | 45 | 0 |  | X
06 | 06-1G1804 | 1G1804 | 06-VAR--/0 |  |  | Truesdell Corporation Of California, Inc. | 1310 W. 23Rd Street | Tempe Az 85282 | 6024371711 | 5599774455 | 1824 Norris Road | Bakersfield, Ca 93308 | James Burford | 236538.1 | 0 | 0 | 0 | 2025-10-20 | Furnish And Place Polyester Concrete Overl | Kern County At Various Locations From Grapevine Creek Bridge To Kern River Floodcanal Bridge | 65 | 83 | 2678165.6 | 3068068 | 3165054.67 | 57536 | 2025-12-16 | 2025-04-04 | 2025-03-19 |  |  | 71 | 0 | 110 | 0 |  | X
07 | 07-2XM404 | 2XM404 | 07-LA-0-/0 | 20.10 201352 |  | Izurieta Fence Company Inc | 3000 Gilroy St | Los Angeles, Ca 90039 |  | 3103455704 | 13230 Firestone Blvd Suite A | Santa Fe Springs, Ca 90670 | Frempong, Sam | 0 | 0 | 0 | 0 | 2025-10-20 | Replace/Upgrade Perimeter Fence/Systems | La County/Cities-Hawthorne,Commerce& Long Beach@Felton,Willow,Commerece&Butler Mt Strepair/Replace Fences&Perimeter Laser Systdir' | 96 | 90 | 3213972.64 | 21454 | 3580800 | 57011 | 2025-11-29 | 2024-08-22 | 2024-06-17 |  |  | 173 | 0 | 180 | 0 |  | X
07 | 07-2XM204 | 2XM204 | 07-LA-1-1.4/7.3 | 20.20 201130 |  | Myers & Sons Construction Llc | 45 Morrison Ave | Sacramento Ca 95838 |  | 8058577070 | 1525 Rancho Conejo Blvd Ste 102 | Thousand Oaks Ca 91320 | Ira, Alfred | 0 | 0 | 0 | 0 | 2025-10-20 | Replace Rsp | Ven-1 Protect The Roadway From Erosion Dueto Storm Surge & High Tides, Replace & Re-Construct Rsp, Reconstruct Right Shoulder Dir' | 100 | 81 | 8100449.22 | 60283 | 10032200 | 55466 | 2025-11-14 | 2024-03-07 | 2024-02-06 |  |  | 247 | 0 | 180 | 0
07 | 07-346104 | 346104 | 07-LA-1-7.0/7.4 |  | BFNH-P001- (708)000 | Powell Constructors, Inc. | 8555 Banana Avenue | Fontana Ca 92335 | 9093568880 | 3102618467 | 18000 Studebaker Rd Ste 360 | Cerritos Ca 90703 | Ton, Thang | 673040.55 | 0 | 0 | 431972.5 | 2025-10-20 | Retrofit Bridge, Replace Bridge Railings, | Los Angeles County In Long Beach From Golden Avenue To Harbor Avenue | 3 | 13 | 1105013.05 | 8758604 | 8838604 | 59537 | 2028-09-22 | 2025-07-29 | 2025-07-15 |  |  | 19 | 0 | 750 | 0 |  | X
07 | 07-4V2104 | 4V2104 | 07-LA-1-10.4/10.4 | HB4N |  | Servitek Electric, Inc. | 13330 Bloomfield Ave #102-114 | Norwalk, Ca 90650 | 6262271650 | 5629167962 | 18000 Studebaker Rd. Suite 360 | Cerritos, Ca 90703 | Ton, Thang | 9212 | 0 | 0 | 0 | 2025-10-20 | Modifying Signal And Lighting. | In Los Angeles County At Broad Avenue | 87 | 83 | 581142.75 | 652457 | 702457 | 52364 | 2025-10-31 | 2023-08-11 | 2023-03-01 |  |  | 122 | 0 | 140 | 0 |  | X
07 | 07-377604 | 377604 | 07-LA-1-29.4/0 |  | SNHG-P001- (701)E | Ptm General Engineering Services, Inc. | 5942 Acorn St. | Riverside Ca 92504 |  |  |  |  | Leon, Dan | 0 | 0 | 0 | 0 |  | Modifying Signal And Lighting Systems (Cit | Los Angeles County In And Near Los Angelesat Eight-Third Street And At Fiji Way | 0 | 0 | 0 | 684048 | 684048 | 57079 | 2026-06-02 | 2025-02-04 | 2024-11-22 |  |  | 0 | 0 | 100 | 0
07 | 07-2XR604 | 2XR604 | 07-LA-1-34.9/38 | 20.20.201130 |  | Full Traffic Maintenance Inc | 217 Lewis Court | Corona, Ca 92882 |  | 2133939051 | 12975 W Culver Blvd | Los Angeles Ca 90066 | Martinez, Elizabeth | 0 | 0 | 0 | 0 | 2025-08-20 | Set Up Traffic Control | La-1 Wildfire Damage. Set Up Traffic Cont-Rol. Maintain Traffic Control 24/7. Provi-De Flaggers To Facilitate Const Activitiesdir' | 93 | 52 | 1903394.82 | 14439 | 3677600 | 57458 | 2026-03-25 | 2025-03-20 | 2025-01-28 |  |  | 28 | 0 | 30 | 0
07 | 07-2XS304 | 2XS304 | 07-LA-1-36.0/41 | 20.20.201130 |  | Staples Construction Company | 1501 Eastman Ave | Ventura, Ca 93003 |  | 3107159500 | 12975 W. Culver Blvd | Los Angeles, Ca 90066 | Martinez, Elizabeth | 0 | 0 | 0 | 0 | 2025-10-20 | Repair Fire Damage Assets | In La County, On La-1 South Of California Incline To Topanga Creek-Repair Fire Dmagestabilize Slopes,Erosion Cntrl&Drainge Sysdir' | 56 | 54 | 2928372.31 | 35364 | 6664100 | 58395 | 2026-06-26 | 2025-03-26 | 2025-02-28 |  |  | 112 | 0 | 200 | 0 |  | X
07 | 07-2XS204 | 2XS204 | 07-LA-1-37.0/46 | 20.XX 201130 |  | C.A. Rasmussen Inc | 28548 Livingston Ave | Valencia, Ca 91355 |  | 3107159500 | 12975 W. Culver Blvd | Los Angeles, Ca 90066 | Martinez, Elizabeth | 0 | 0 | 0 | 0 | 2025-10-20 | Divert Debris Due To Fire Damage | La County,Cities Of La&Malibu From Entradadr To Sweetwater Canyon Drive To Divert Debris/Mudslides & Cleanup Due To Fires Dir'S Em | 200 | 85 | 2269264.35 | 9987 | 2655500 | 57241 | 2026-07-07 | 2025-02-25 | 2025-02-20 |  |  | 120 | 360 | 20 | 0 |  | X
07 | 07-313504 | 313504 | 07-LA-1-37.7/62.9 | HA22 | ACNH-P001- (689)E | Security Paving Company, Inc. | 13170 Telfair Ave | Sylmar Ca 91342 | 818612859 | 5625725852 | 12975 W Culver Blvd | Los Angeles Ca 90066 | Martinez, Elizabeth | 1105131.26 | 0 | 0 | 0 | 2025-10-20 | Remove And Construct Bridge And Culverts. | Los Angeles And Ventura Counties At Various Locations From 0.4 Mile South Of Temescal Canyon Road To 0.1 Mile North Of Tonga Stree | 100 | 51 | 14148973.27 | 26563881.4 | 27775936.4 | 52304 | 2026-12-10 | 2023-09-01 | 2023-07-20 |  |  | 450 | 0 | 430 | 0
07 | 07-2XS104 | 2XS104 | 07-LA-1-39.9/40 | 20.XX 201130 |  | Skanska Usa Civil West California District Inc | 1995 Agua Mansa Road | Riverside Ca 92509 |  | 3107159500 | 12975 W Culver Blvd | Los Angeles, Ca 90066 | Martinez, Elizabeth | 0 | 0 | 0 | 0 | 2025-10-20 | Repair Fire Damage To Getty Wall | In La County, City Of La N/B La 1 N/Of Porto Marina Wy To Getty Villa Dr To Remov& Replace Fire Damage & Ds To Getty Wall Dir'S Em | 5 | 1 | 90702.33 | 30316 | 7673000 | 59460 | 2026-09-30 | 2025-05-21 | 2025-02-28 |  |  | 15 | 0 | 300 | 0 |  | X
07 | 07-2XE004 | 2XE004 | 07-LA-1-40.0/40.5 | 20.XX 201130 |  | Chumo Construction Inc | 14425 Joanbridge Street | Baldwin Park, Ca 91706 |  | 3103456270 | 12975 W. Culver Blvd | Los Angeles, Ca 90066 | Martinez, Elizabeth | 0 | 0 | 0 | 0 | 2025-05-20 | Storm Damage Repair | In La County Southbound Pch La-1 To Repairslopes,Damaged Cross Drains,Reconstruct Rsp & Place Geofabric Due To Winter Stormsdir'S | 78 | 7 | 980812.6 | 58000 | 13890000 | 49184 | 2025-12-30 | 2023-02-27 | 2023-01-12 |  |  | 140 | 0 | 180 | 0
07 | 07-2XQ704 | 2XQ704 | 07-LA-1-40.7/54.1 | 20.XX 201130 |  | Crosstown Electrical &Data Inc | 5454 Diaz Street | Irwindale, Ca 91706 |  | 3107159500 | 12975 W. Culver Blvd | Los Angeles, Ca 90066 | Martinez, Elizabeth | 0 | 0 | 0 | 0 | 2025-08-20 | Maintain Traffic Signals Due To Fire Damag | In La County La-1 From Topanga Cyn Blvd Tokanan Dume Rd To Maintain Functional Trafcsignals @ 20 Loctns Due To Wildfire Damagedir' | 100 | 100 | 3186619.79 | 3118 | 3175000 | 57118 | 2025-10-27 | 2025-02-10 | 2024-12-10 |  |  | 65 | 0 | 30 | 0 |  | X
07 | 07-2XS404 | 2XS404 | 07-LA-1-41.0/45.6 | 20.20.201130 |  | Rv Concrete Inc | 605 E Commercial St | Anaheim, Ca 92801 |  | 3107159500 | 12975 W. Culver Blvd | Los Angeles, Ca 90066 | Martinez, Elizabeth | 0 | 0 | 0 | 0 | 2025-10-20 | Repair Fire Damage | La County,Cities Of La & Malibu Pch South Of Tuna Canyon Rd To North Of Carbon Beachrepair Fire Damage State Assets,Slopes& Dsdir' | 40 | 65 | 3337658.75 | 102900 | 5130000 | 58155 | 2027-07-07 | 2025-04-10 | 2025-02-28 |  |  | 113 | 0 | 280 | 0 |  | X
07 | 07-2XT304 | 2XT304 | 07-LA-1-42.0/44 | 20.XX 201130 |  | Granite Construction Company | 16700 Valley View Ave #300 | La Mirada, Ca 90638 |  | 3107159500 | 12975 W Culver Blvd | Los Angeles, Ca 90066 | Martinez, Elizabeth | 0 | 0 | 0 | 0 | 2025-10-20 | Place Shoring & Retaining Walls | In La County, City Of Malibu N Of Pena Rd To S Of Las Flores Cyn Rd To Place Temporary Shoring & Construct Retaining Walls Dir'S E | 11 | 3 | 247282.57 | 15953 | 7075000 | 59475 | 2026-08-16 | 2025-06-10 | 2025-04-28 |  |  | 35 | 0 | 330 | 0 |  | X
07 | 07-2XR204 | 2XR204 | 07-LA-1-42.2/42.4 | 20.20.201130 |  | Myers & Sons Construction Llc | 45 Morrison Ave | Sacramento, Ca 95838 |  | 3107159500 | 12975 W. Culver Blvd | Los Angeles, Ca 90066 | Martinez, Elizabeth | 0 | 0 | 0 | 0 | 2025-10-20 | Replace Fire Damaged Retaining Wall | La County, Pch East Of Big Rock Drive To Place Temp Railing(Type K)K-Rail, Slopeprotection Covering, Remove Fire Debris Dir'S Emer | 76 | 52 | 7260495.75 | 84056 | 13994300 | 57383 | 2026-03-25 | 2025-03-20 | 2025-01-24 |  |  | 136 | 0 | 180 | 0
07 | 07-4X9704 | 4X9704 | 07-LA-1-42.4/0 |  | PTNH-P001- (694) E | Beador Construction Company, Inc. | 2900 Bristol Street D204 | Costa Mesa Ca 92626 | 9516747352 | 8184829191 | 12975 W Culver Blvd | Los Angeles, Ca 90066 | Sheik, Hakim | 339284.5 | 0 | 0 | 0 | 2025-10-20 | Construct Drilled Hole And Drilled Hole (R | Los Angeles County In Malibu At 0.1 Mile South Of Big Rock Drive | 16 | 20 | 1246136.5 | 6117700 | 6151700 | 57139 | 2026-09-30 | 2025-02-13 | 2025-01-16 |  |  | 40 | 0 | 250 | 0 |  | X
07 | 07-2XR904 | 2XR904 | 07-LA-1-43.5/45.5 | 20.20.201130 |  | Maneri Traffic Control Inc | 4949 2Nd St | Fallbrook, Ca 92028 |  | 3107159500 | 12975 W. Culver Blvd | Los Angeles, Ca 90066 | Martinez, Elizabeth | 0 | 0 | 0 | 0 | 2025-10-20 | Provide Traffic Control Frm Palisade Fire | La County, From N/Of Las Flores Cyn Rd To Carbon Beach Terrace To Provide Traffic Control On Pch Due To Palisades Fire Dir'S Emerg | 100 | 88 | 3252404.35 | 13126 | 3677600 | 57355 | 2026-03-25 | 2025-03-18 | 2025-01-28 |  |  | 49 | 0 | 30 | 0 |  | X
07 | 07-2XR104 | 2XR104 | 07-LA-1-43.7/43.7 | 20.XX 201130 |  | Pcn3 Inc | 10591 Humbolt St Unit A | Los Alamitos, Ca 90720 |  | 3107159500 | 12975 W. Culver Blvd | Los Angeles, Ca 90066 | Martinez, Elizabeth | 0 | 0 | 0 | 0 | 2025-10-20 | Repair Fire Damage To Maintenance Station | La County In City Of Malibu On La-1 At Thelas Flores Maintenance Station-Repair Firedamage To Building Property & Fuel Island Dir' | 15 | 1 | 141665.16 | 83785 | 12031000 | 59295 | 2026-04-23 | 2025-05-21 | 2025-04-24 |  |  | 35 | 0 | 240 | 0 |  | X
07 | 07-2XG904 | 2XG904 | 07-LA-1-44.1/58.5 | 20.XX 201130 |  | Ptm General Engineering Servcs | 5942 Acorn Street | Riverside, Ca 92504 |  | 3102133136 | 12975 W Culver Blvd | Los Angeles, Ca 90066 | Shin, Frank | 0 | 0 | 0 | 0 | 2025-10-20 | Repair & Clean Debris From Storm Damage | La County On La-1 Pch In City Of Malibu Remove Landslide & Stockpild Debris,Repaireroded Slope Areas,Clean Ds Due To Storms Dir'S | 98 | 85 | 1721130.62 | 24858 | 2030000 | 52564 | 2025-12-30 | 2023-06-27 | 2023-05-10 |  |  | 88 | 0 | 90 | 0 |  | X
07 | 07-4V3804 | 4V3804 | 07-LA-1-45.6/45.9 |  | SNHG-P001- (698)E | Crosstown Electrical & Data, Inc. | 5454 Diaz Street | Irwindale Ca 91706 |  |  |  |  | Leon, Dan | 16103.38 | 28404.83 | 0 | 0 | 2025-10-20 | Convert Continuous Yellow Flashing Beacon | Los Angeles County In Malibu From 0.6 Milenorth Of Carbon Canyon Road To 0.5 Mile South Of Sweetwater Canyon Road | 100 | 99 | 932496.7 | 890260 | 937533.22 | 56100 | 2025-12-30 | 2024-07-17 | 2024-06-27 | 2025-10-31 |  | 120 | 0 | 120 | 0 |  | X
07 | 07-2XR504 | 2XR504 | 07-LA-1-46.3/49.4 | 20.XX 201130 |  | Magellan Construction Inc | 1650 Zanker Rd Ste 130 | San Jose, Ca 95112 |  | 3102133136 | 12975 W. Culver Blvd | Los Angeles, Ca 90066 | Shin, Frank | 0 | 0 | 0 | 0 | 2025-10-20 | Repair/Clean Fire Damage To Ds & Slopes | In City Of Malibu South Of Sweetwater Cyn Dr To N/Of Puerco Cyn Rd To Clean/Repair Fire Damage Drainage Systems & Side Slopesdir'S | 36 | 11 | 230749.51 | 13719 | 2109000 | 59756 | 2026-04-29 | 2025-05-21 | 2025-02-14 |  |  | 54 | 0 | 150 | 0 |  | X
07 | 07-291404 | 291404 | 07-LA-1-56.5/56.9 | HA21 | ACST-P001- (674)E | Stacy And Witbeck, Inc. | 2800 Harbor Bay Parkway | Alameda Ca 94502 | 5107481870 | 8184829191 | 12975 W Culver Blvd | Los Angeles, Ca 90066 | Sheik, Hakim | 19466 | 7747.37 | 0 | 0 | 2025-10-20 | Bridge Replacement | In Los Angeles County In Malibu From Guernsey Ave To Trancas Canyon Road | 52 | 95 | 16698303 | 10781073.25 | 17117167.3 | 41480 | 2025-12-31 | 2021-03-09 | 2021-02-18 |  |  | 781 | 0 | 1515 | 0 |  | X
07 | 07-2XG804 | 2XG804 | 07-LA-1-352.0/44.1 | 20.XX 201130 |  | Drill Tech Drilling & Shoring Dba Apex Rockfall Mitigation | 2200 Wymore Way | Antioch, Ca 94509 |  | 3102133136 | 12975 W. Culver Blvd | Los Angeles, Ca 90066 | Shin, Frank | 0 | 0 | 0 | 0 | 2025-08-20 | Repair/Replace Slope Protection System | In La County On Pch La-1 In Cities Of Malibu,Pacific Palisades&Santa Monica To Remove Debris&Repair Drapery Protect Systmdir'S Eme | 99 | 98 | 2903969.11 | 15486 | 2971000 | 51124 | 2025-12-31 | 2023-06-06 | 2023-04-26 |  |  | 89 | 0 | 90 | 0 |  | X
07 | 07-2XR704 | 2XR704 | 07-LA-1-380.0/40 | 20.XX 201130 |  | Fryman Management Inc | 18 Goodyear Ste 105 | Irvine, Ca 92618 |  | 3107159500 | 12975 W. Culver Blvd | Los Angeles, Ca 90066 | Martinez, Elizabeth | 0 | 0 | 0 | 0 | 2025-10-20 | Provide Traffic Control | La County Pch N/Of Temescal Cny Rd To S/Oftopanga Cny Blvd To Provide Traffic Cntrolfor Repopulation Efforts From Palisade Firdir' | 100 | 77 | 2815172.15 | 19252 | 3677600 | 57300 | 2026-02-05 | 2025-03-11 | 2025-03-03 |  |  | 89 | 0 | 30 | 0
07 | 07-2XP704 | 2XP704 | 07-LA-1-388.0/40.4 | 20.XX 201130 |  | Interstate Civil Construction | Po Box 2819 | Wrightwood, Ca 92397 |  | 2133939051 | 12975 W Culver Blvd | Los Angeles, Ca 90066 | Martinez, Elizabeth | 0 | 0 | 0 | 0 | 2025-05-20 | Pavement Delineation Realignment La-1 | In La County,City Of La Pch La-1@ Tramontoslide Area To Realign Pavement Delineation& Pave Shoulder As Necessary Dir'S Emergency | 23 | 70 | 1473725.91 | 13761 | 2116000 | 56037 | 2025-12-24 | 2024-07-02 | 2024-05-25 |  |  | 27 | 0 | 120 | 0 |  | X
07 | 07-2XR804 | 2XR804 | 07-LA-1-400.0/43.5 | 20.20.201130 |  | Dc Traffic Control | 13905 Artesia Blvd | Cerritos, Ca 90703 |  | 3107159500 | 12975 W. Culver Blvd | Los Angeles, Ca 90066 | Martinez, Elizabeth | 0 | 0 | 0 | 0 | 2025-09-20 | Provide Traffic Control | La County On Pch From North Of Topanga Cynla-27 To South Las Flores Cny Rd To Providtraffic Control Due To Palisades Fire Dir'S Em | 100 | 99 | 3660982.18 | 28918 | 3677600 | 57336 | 2026-03-24 | 2025-03-17 | 2025-01-28 |  |  | 95 | 0 | 30 | 0 |  | X
07 | 07-321604 | 321604 | 07-LA-1-/18 | HA22 | ACNH-P001- (692)E | R.J. Noble Company | 15505 East Lincoln Avenue | Orange Ca 92856 |  | 5628605963 | 18000 Studebaker Rd Suite 360 | Cerritos, Ca 90703 | Ton, Thang | 3490739.41 | 67030.96 | 0 | 0 | 2025-10-20 | Cold Plane Ac And Overlay Ac Pavement And | Los Angeles County From Studebaker Road Topaseo De Las Delicias | 66 | 90 | 47382773.68 | 48208586.5 | 49918443.57 | 54985 | 2026-07-02 | 2024-01-23 | 2023-12-20 |  |  | 348 | 0 | 525 | 0 |  | X
07 | 07-333604 | 333604 | 07-LA-2-2.3/14.2 |  | ACST-P002- (043)E | Sully-Miller Contracting Company | 135 S. State College Blvd #40 | Brea Ca 92821 |  | 2139526068 | 601 S Glenoaks Blvd #310 | Burbank, Ca 91502 | Bautista, Denrick | 879641.75 | 0 | 0 | 0 | 2025-10-20 | Cold Plane Ac, Place Hma, Replace Curb Ram | Los Angeles County In Los Angeles At Various Locations From Centinela Avenue Toglendale Boulevard Undercrossing | 11 | 2 | 924257.75 | 49868999.3 | 50489158.43 | 56906 | 2028-11-21 | 2024-12-17 | 2024-11-26 |  |  | 84 | 0 | 750 | 0 |  | X
07 | 07-348504 | 348504 | 07-LA-2-15.0/26.5 |  | ACNH-P002- (044)E | Yakar | 689 East San Bernardino Rd | Covina Ca 91723 |  |  |  |  | Tran, Danglong | 0 | 0 | 0 | 0 |  | Construct Ada Curb Ramps And Modify Signal | Los Angeles County At Various Locations From Riverside Drive To Gould Mesa | 0 | 0 | 0 | 4794008 | 4794008 | 59459 | 2027-01-31 | 2025-07-22 | 2025-06-06 |  |  | 0 | 0 | 300 | 0
07 | 07-355404 | 355404 | 07-LA-2-15.0/57.5 | HA22 |  | Chumo Construction Inc. | 14425 Joanbridge Street | Baldwin Park Ca 91706 |  | 8184829304 | 2090 Fern Lane | Glendale, Ca 91208 | Tran, Danglong | 336247.49 | 0 | 0 | 0 | 2025-10-20 | Replace And Install Drainage System, And P | Los Angeles County On Route 2 From 1.0 Mile North Of Clifford Street To Mount Waterman Ski Lifts And On Route 210 From 0.5 Mile Ea | 99 | 93 | 6198030.99 | 6071642.21 | 6340518.26 | 55349 | 2025-10-29 | 2024-02-28 | 2024-01-30 |  |  | 267 | 0 | 270 | 0 |  | X
07 | 07-351304 | 351304 | 07-LA-2-15.1/15.3 |  | ACNH-X037- (235)E | Powell Constructors Inc | 8555 Banana Avenue | Fontana Ca 92335 |  | 2139526068 | 601 S Glenoaks Blvd Suite# 310 | Burbank, Ca 91502 | Bautista, Denrick | 15880 | 0 | 56808.8 | 0 | 2025-10-20 | Seismic Retrofit And Guardrail Upgrade. | Los Angeles County At Route 2/5 Separation | 100 | 31 | 2207942.8 | 6879634 | 7144095.84 | 55224 | 2027-03-19 | 2024-02-16 | 2024-01-16 |  |  | 313 | 0 | 525 | 0
07 | 07-2XK404 | 2XK404 | 07-LA-2-15.8/15.8 | 20.XX 201130 |  | Stacy And Witbeck Inc | 2800 Harbor Bay Parkway | Alameda, Ca 94502 |  | 2139526068 | 601 S Glenoaks Blvd | Burbank, Ca 91502 | Bautista, Denrick | 0 | 0 | 0 | 0 | 2025-10-20 | Repair Bridge Damage Due To Fire | La County, City Of La On La-2 @Taylor Yardoverheard Br#53-1039 To Repair/Replace Fire Damaged Braces,Girders&Construct Fencdir'S E | 100 | 65 | 3134602.71 | 11428 | 4842100 | 55642 | 2025-12-05 | 2024-02-23 | 2023-10-13 |  |  | 210 | 0 | 70 | 0
07 | 07-0W2104 | 0W2104 | 07-LA-2-18.7/0 |  |  | Splice Construction Co, Inc. 28441 Rancho De Linda Laguna Niguil Ca 92677 | 28441 Rancho De Linda | Laguna Niguel Ca 92677 |  | 8182665626 | 2090 Fern Lane | Glendale Ca 91208 | Amorsolo, Mark | 221120.1 | 0 | 0 | 0 | 2025-10-20 | Place Class 3 Aggregate Base And Hot Mix A | Los Angeles County In Los Angeles At Los Angeles Regional Transportation Managementcenter At 2901 At West Broadway | 100 | 100 | 490034.1 | 468650 | 468650 | 59316 | 2025-11-26 | 2025-07-08 | 2025-06-23 |  |  | 50 | 0 | 50 | 0 |  | X
07 | 07-349004 | 349004 | 07-LA-2-68.1/82.1 | HA22 |  | Lamassu Utility Services, Inc. | 3193 Enterprise Court | Loomis Ca 95650 |  | 8184829304 | 2090 Fern Lane | Glendale, Ca 91208 | Tran, Danglong | 106923.55 | 0 | 0 | 0 | 2025-08-20 | Replace Culvert And Install Cured-In-Place | Los Angeles County From Stone Bridge To San Bernardino County Line | 100 | 84 | 1146863.47 | 1370000 | 1334931.25 | 54384 | 2025-09-25 | 2023-12-13 | 2023-11-15 | 2025-10-13 |  | 180 | 0 | 180 | 0
07 | 07-357304 | 357304 | 07-LA-5-6.6/13.1 | HA22 | ACIM-0052- (037)E | Peterson-Chase General Engineering Construction, Inc. | 16351 Construction Circle Wes | Irvine Ca 92606 |  | 2133306640 | 4281 Katella Ave #221 | Los Alamitos, Ca 90720 | Oregel, Martin | 332121.25 | 125610.25 | 0 | 0 | 2025-10-20 | Replace Concrete Slabs And Median Barrier, | Los Angeles County In Santa Fe Springs, Downey And City Of Commerce From 0.2 Mile South Of Route 5/605 Separation To 0.1 Mile Nort | 99 | 86 | 20951740.99 | 23988111.6 | 24436715.09 | 49584 | 2025-11-01 | 2023-05-22 | 2023-04-27 |  |  | 318 | 0 | 320 | 0 |  | X
07 | 07-2XQ404 | 2XQ404 | 07-LA-5-6.8/0 | 20.XX 201131 |  | Quality Fence Co Inc | 14929 Garfield Avenue | Paramount, Ca 90723 |  | 2133100860 | 970 W. 190Th Street Suite 270 | Torrance, Ca 90502 | Shahriari, Shahnam | 0 | 0 | 0 | 0 |  | Install Security System@Var Communictn Hub | In La County In Various Cities,La-5 Norwlkcomm Hub,La-105 Lax Hub&La-605 San Gabrielconstruct Gate/Door&Replace W/Security Sysdir' | 0 | 0 | 0 | 12219 | 2211000 | 58935 | 2026-01-30 | 2025-05-21 | 2025-04-30 |  |  | 0 | 0 | 120 | 0
07 | 07-4V3004 | 4V3004 | 07-LA-5-8.2/8.2 | HB4N |  | Ptm General Engineering Services Inc. | 5942 Acorn St. | Riverside Ca Ca 92509 |  | 5623459865 | 13230 Firestone Blvd | Santa Fe Springs, Ca 90670 | Frempong, Samuel | 1500 | 0 | 0 | 0 | 2025-08-20 | Upgrade Traffic Signal And Lighting. | Los Angeles County In Downey At Route 5/19Separation | 100 | 100 | 439041.93 | 373000 | 435201.93 | 42844 | 2025-11-30 | 2022-06-30 | 2022-06-16 |  |  | 60 | 0 | 60 | 0 |  | X
07 | 07-2XJ004 | 2XJ004 | 07-LA-5-16.0/17.3 | 20.XX 201130 |  | Dbx Inc | 42024 Avenida Alvarado Ste A | Temecula, Ca 92590 | 9512969909 | 2137937193 | 1041 W Badillo Suite 112 | Covina, Ca 91722 | Pham, Ryan | 0 | 0 | 0 | 0 | 2025-09-20 | Restore/Repair Fiber Optic Theft Damage | In La County@ Ela Interchange Routes 5,10,60 & 101 To Restore/Repair Highway Lightng& Associated Rdwy Electrical &Comm Systemsdir' | 100 | 99 | 4007431.29 | 23875 | 4065000 | 52184 | 2025-10-27 | 2023-07-18 | 2023-06-12 |  |  | 250 | 0 | 90 | 0 |  | X
07 | 07-344204 | 344204 | 07-LA-5-23.2/36.3 |  | ACIM-X037- (234)E | Powell Constructors Inc | 8555 Banana Avenue | Fontana Ca 92335 |  | 8184829304 | 2090 Fern Lane | Glendale, Ca 91208 | Tran, Danglong | 141809 | 0 | 0 | 0 | 2025-10-20 | Construct Gsrds, Mvps, And Bioswales. | Los Angeles County At Various Locations | 46 | 53 | 2765185.07 | 4957414.25 | 5202414.25 | 56075 | 2026-11-19 | 2024-07-12 | 2024-06-13 |  |  | 224 | 0 | 490 | 0 |  | X
07 | 07-0W1004 | 0W1004 | 07-LA-5-31.8/42.6 | HM1 |  | C. A. Rasmussen, Inc. | 28548 Livingston Avenue | Valencia Ca 91355 | 6613679040 | 8186130956 | 23369 Leonora Dr | Woodland Hills, Ca 91367 | Gurfinkel, Vladimir | 0 | 0 | 0 | 0 | 2025-10-20 | Replace Pcc Slabs,Grind Pcc | In Los Angeles County In Los Angeles From Cohasset Street Under- Crossing To Roxford Street Under- Crossing | 100 | 98 | 8574458.11 | 8295854 | 8401277.25 | 42964 | 2025-10-28 | 2022-07-11 | 2022-06-28 |  |  | 174 | 0 | 160 | 0 |  | X
07 | 07-384404 | 384404 | 07-LA-5-33.1/39.1 |  |  | Martinez Landscape Co., Inc | 12357 San Fernando Road | Sylmar Ca 91342 | 8183649188 | 8182628853 | 9225 Cranford Ave | Pacoima, Ca 91331 | Bui, Kevin | 0 | 0 | 0 | 0 | 2025-10-20 | Clean Ca Beautification | La Co. Route 5 Between Pm 33.1 And Pm 39.1 | 100 | 93 | 4854592.01 | 5042930.5 | 5181685.5 | 43984 | 2025-12-31 | 2022-08-25 | 2022-07-06 |  |  | 560 | 0 | 1000 | 440 |  | X
07 | 07-2XS804 | 2XS804 | 07-LA-5-53.7/53.7 | 20.XX 201130 |  | Interstate Civil Construction | P.O. Box 2819 | Wrightwood, Ca 92397 | 7602810188 | 2138170162 | 25061 W Avenue Stanford Suite 70 | Valencia, Ca 91355 | Bakhet, Wassem | 0 | 0 | 0 | 0 |  | Remove/Replace Bridge Joint | In La County, City Of Valencia S/B I-5 At Abutment 1 Santa Clara River Brdge 53-2925Remove&Replace Damaged Steel Joint Assmblydir' | 0 | 0 | 0 | 8367 | 1217000 | 60103 | 2025-12-10 | 2025-08-28 | 2025-06-27 |  |  | 0 | 0 | 30 | 0
07 | 07-4V5404 | 4V5404 | 07-LA-5-56.4/56.7 |  | SIMG-0052- (777)000 | Genuine Engineering, Inc. Attn Kristi Stelle | 11762 De Palma Rd Ste 1C-255 | Corona Ca 92883 | 9516745000 | 8182628913 | 9225 Cranford Ave | Pacoima Ca 91331 | Bui, Kevin | 0 | 0 | 0 | 0 |  | Modify Single Lane Roundabout. | Los Angeles County In Castaic From 0.2 Mile South Of Hasley Canyon Road Overcrossing To 0.1 Mile North Of Hasley Canyon Road Overc | 0 | 0 | 0 | 868426.5 | 868426.5 | 59477 | 2026-01-09 | 2025-07-22 | 2025-06-19 |  | S | 0 | 0 | 50 | 0
07 | 07-370404 | 370404 | 07-LA-5-59.5/73.7 |  | ACIM-0053- (999)E | Griffith Company | 3050 E. Birch St | Brea Ca 92821 | 9093566880 | 2135050610 | 25061 W Avenue Stanford Ste 70 | Valencia, Ca 91355 | Salman, Ridwan | 2652988.93 | 0 | 0 | 0 | 2025-10-20 | Cold Plane Ac Pavement, Place Hot Mix Asph | Los Angeles County From Lake Hughes Road Undercrossing To 0.7 Mile South Of Vista Del Lago Road Overcrossing. | 20 | 54 | 26363118.8 | 47662735 | 48896382.53 | 57238 | 2027-07-29 | 2025-02-27 | 2025-02-06 |  |  | 110 | 0 | 800 | 0 |  | X
07 | 07-323404 | 323404 | 07-LA-5-59.5/67.9 | HA22 | ACIM-0053- (074)E | Security Paving Company, Inc. | 3075 Townsgate Road | Westlake Village Ca 91361 | 8183629200 | 2137925518 | 25061 West Ave Stanford Ste 70 | Valencia, Ca 91355 | Osorio, Oscar | 70080.6 | 0 | 0 | 0 | 2025-09-20 | Replace Slabs, Upgrade Drainage | At Valencia And Castaic, From Lake Hughes Road Undercrossing To 1.9 Miles North Of Templin Highway. | 81 | 91 | 23731147.97 | 23715762 | 26217041.67 | 42284 | 2025-09-30 | 2022-03-30 | 2022-02-25 |  |  | 550 | 0 | 680 | 0 |  | X
07 | 07-352304 | 352304 | 07-LA-5-60.0/75 |  | PTIM-0053- (113)E | Powell Constructors Inc | 8555 Banana Avenue | Fontana Ca 92335 | 9093568880 | 2137925518 | 25061 W Ave Stanford #70 | Valencia Ca 91355 | Osorio, Oscar | 115844.88 | 4786.14 | 0 | 0 | 2025-10-20 | Replace Drainage Systems, Install Gsrd, An | Los Angeles County In And Near Castaic From 0.5 Mile North Of Lake Hughes Road To0.5 Mile North Of Vista Del Lago Road | 49 | 87 | 6201103.81 | 6989277 | 7033777 | 56009 | 2025-11-19 | 2024-06-20 | 2024-06-03 |  |  | 260 | 0 | 530 | 0 |  | X
07 | 07-2XT504 | 2XT504 | 07-LA-5-138.0/13.8 | 20.XX 201130 |  | Jfl Electric Inc | 8257 Compton Avenue | Los Angeles, Ca 90001 |  | 2137924801 | 1201 Baldwin Park Blvd | Baldwin Park, Ca 91706 | Ngo, Jason | 0 | 0 | 0 | 0 | 2025-10-20 | Repair & Install Security@ Pump Plant | La County,City Of La On S/B La-5 @Eastern Ave Pump Plant To Repair Damages To Servcecabinet & Install Security Systems Dir'S Emerg | 2 | 3 | 44087.35 | 15851 | 1373000 | 58736 | 2026-02-27 | 2025-06-10 | 2025-06-03 |  |  | 2 | 0 | 90 | 0 |  | X
07 | 07-0Y1504 | 0Y1504 | 07-LA-5-151.1/188.2 |  |  | Interstate Civil Construction | 6025 Park Dr | Wrightwood Ca 92397 |  |  | 902 San Gabriel Blvd | Rosemead Ca 91770 | Azam Shoaib Bin | 0 | 0 | 0 | 0 |  | Individual Slab Replacement, Digouts, And | Los Angeles County In Los Angeles At Various Locations From 0.2 Mile East Of Esperanza Street Undercrossing To Mission Road Overcr | 0 | 0 | 0 | 2956965.8 | 2956965.8 | 59618 | 2026-03-28 | 2025-08-05 | 2025-06-26 |  |  | 0 | 0 | 100 | 0
07 | 07-319304 | 319304 | 07-LA-5-/19.5 | HB1 | HSST-X037- (224)E | Re Chaffee Construction Inc. | 1253 Evergreen Rd | Wrightwood Ca 92397 | 7602498068 | 2137008447 | 1525 Rancho Conejo Blvd Ste102 | Thousand Oaks, Ca 91320. | Tehrani, Joseph | 6316.8 | 0 | 0 | 0 | 2025-10-20 | Reduce Severity Collisions By | From County Line To Broadway, Reduce Severity Collisions | 100 | 90 | 3677010.2 | 3797765 | 4056168.08 | 45544 | 2025-11-30 | 2022-11-18 | 2022-10-07 |  |  | 265 | 0 | 180 | 0 |  | X
07 | 07-347504 | 347504 | 07-LA-10-2.2/4.9 | HA25 | ACIM-0101- (858)E | Griffith Company | 3050 E. Birch St | Brea Ca 92821 |  | 2139526068 | 601 S Glenoaks Blvd Suite 310 | Burbank, Ca 95102 | Bautista, Denrick | 536.25 | 0 | 0 | 0 | 2025-09-20 | Rehabilitate Highway Planting And Modify I | Los Angeles County In Santa Monica And Losangeles From Lincoln Boulevard Overcrossing To Gateway Boulevard Undercrossing | 76 | 11 | 257802.6 | 2390787.5 | 2430287.5 | 55348 | 2028-12-04 | 2024-02-28 | 2024-01-09 |  |  | 189 | 0 | 1000 | 0
07 | 07-2XH804 | 2XH804 | 07-LA-10-2.2/5.2 | 20.XX 201130 |  | Baltazar Construction, Inc | 236 E. Arrow Hwy | Covina, Ca 91722 |  | 5625725852 | 12975 W. Culver Blvd | Los Angeles, Ca 90066 | Martinez, Elizabeth | 0 | 0 | 0 | 0 | 2024-04-20 | Clean & Repair Storm Damage | In La County Cities Of Santa Monica& La-10To Reconstruct Eroded Slopes,Remove Debrisrepair Irrigation&Clean Ds @ 4 Locations Dir'S | 90 | 58 | 426239.36 | 5475 | 735000 | 53505 | 2025-12-26 | 2023-07-27 | 2023-07-12 |  |  | 27 | 0 | 30 | 0
07 | 07-332004 | 332004 | 07-LA-10-4.5/5.5 | HA42 |  | Marina Landscape, Inc. | 3707 W. Garden Grove Blvd | Orange Ca 92868 | 7149396600 | 3102133136 | 12975 Culver Blvd | Los Angeles, Ca 90066 | Shin, Frank | 4500 | 0 | 0 | 0 | 2025-10-20 | Install Irrigation System And Plant | In The City Of Los Angeles From Bundy Drive To Sepulveda Boulevard Undercrossing; And On Rte 405 From Olympic Blvd To National Bl | 100 | 92 | 1387148.29 | 1463402 | 1503402 | 44624 | 2027-03-05 | 2022-09-27 | 2022-09-02 |  |  | 679 | 0 | 1000 | 0 |  | X
07 | 07-358404 | 358404 | 07-LA-10-4.7/18.9 |  | PTIM-0101- (859)E | Yakar | 689 East San Bernardino Rd | Covina Ca 91723 | 9095991612 | 2132691320 | 902 San Gabriel Blvd | Rosemead, Ca 91770 | Vong, Jeanette | 4020 | 0 | 0 | 0 | 2025-10-20 | Replace And Line Culvert And Construct Gro | The City And County Of Los Angeles At Various Locations From 0.2 Mile East Bundydrive Undercrossing To 0.1 Mile West Soto Street O | 0 | 0 | 3055238.74 | 2938925 | 3137071.53 | 56927 | 2026-08-13 | 2025-01-07 | 2024-12-17 |  |  | 167 | 0 | 370 | 0 | X | X
07 | 07-2XL304 | 2XL304 | 07-LA-10-14.5/17.4 | 20.XX 201130 |  | Griffith Company | 3050 E Birch Street | Brea, Ca 92821 |  | 9093224628 | 902 San Gabriel Blvd | Rosemead, Ca 91770 | Minovi, Sepand | 0 | 0 | 0 | 0 | 2025-10-20 | Repair & Install Security Monitoring | City Of La La-10 Santamonica Viaduct Br # 53-1301 & La-5 @Sheldon St To Remove Haz Waste Mtrls &Provide Security Monitoring Dir'S | 83 | 99 | 11352350.38 | 34871 | 11483700 | 55347 | 2025-11-03 | 2024-02-23 | 2023-11-18 |  |  | 428 | 279 | 180 | 0 |  | X
07 | 07-2XL004 | 2XL004 | 07-LA-10-17.0/17.7 | 20.XX 201103 |  | Griffith Company | 3050 E Birch Street | Brea, Ca 92821 |  | 9093224628 | 902 San Gabriel Blvd | Rosemead, Ca 91770 | Minovi, Sepand | 0 | 0 | 0 | 0 | 2025-08-20 | Cleanup Debris Due To Fire | In La County City Of La On La-10 From 15Thst&Alameda St To Santa Fe Avenu Br#53-1301Remove & Cleanup Burn Site & Fire Debris Dir'S | 100 | 100 | 6029100.63 | 11025 | 6405000 | 54184 | 2025-09-03 | 2023-12-06 | 2023-11-11 |  |  | 422 | 270 | 60 | 0 |  | X
07 | 07-386004 | 386004 | 07-LA-10-18.8/20.5 |  |  | West Coast Public Works, Inc. | 20058 Ventura Blvd, #318 | Woodland Hills Ca 91364 |  | 2132691320 | 902 San Gabriel Blvd | Rosemead, Ca 91770 | Vong, Jeanette | 580 | 0 | 0 | 0 | 2025-10-20 | Rock Blanket, Plant Establishment Work And | Los Angeles County In And Near Los Angelesfrom 0.3 Mile East Of State Street Overcrossing To 0.3 Mile West Of Eastern Avenue Overc | 0 | 0 | 1321658.48 | 1241709 | 1436998.9 | 49005 | 2025-12-01 | 2023-04-28 | 2023-03-13 |  |  | 566 | 0 | 870 | 277 | X | X
07 | 07-328304 | 328304 | 07-LA-10-28.2/31 | HA21 |  | Beador Construction Company, Inc. | 2900 Bristol Street D204 | Costa Mesa, Ca 92626 |  | 9512323742 | 1041 W Badillo St#112 | Covina, Ca 91722 | Hong, Hai | 19455.66 | 0 | 0 | 0 | 2025-09-20 | Construct Bridge Closure Pour. | Los Angeles County At Various Locations Inel Monte And Baldwin Park From Rio Hondo Bridge To San Gabriel River Bridge | 88 | 75 | 4530666.51 | 5247700 | 5978690 | 53304 | 2025-12-28 | 2023-10-18 | 2023-09-26 |  |  | 353 | 0 | 400 | 0 |  | X
07 | 07-316804 | 316804 | 07-LA-10-28.3/28.3 | HA21 |  | Powell Constructors,Inc. | 8555 Banana Avenue | Fontana Ca 92335 | 9093568880 | 2132164198 | 902 San Gabriel Blvd. | Rosemead, Ca 91770 | Chan, Jacky | 61200 | 0 | 0 | 0 | 2025-10-20 | Replace Bridge Deck. | Los Angeles County In El Monte At The Rio Hondo Busway Bridge | 73 | 89 | 4715307.16 | 5201229.6 | 5304693.3 | 55326 | 2026-04-16 | 2024-02-14 | 2024-01-26 |  |  | 320 | 0 | 440 | 0 |  | X
07 | 07-398404 | 398404 | 07-LA-10-28.5/30.8 |  |  | Martinez Landscape Co., Inc. | 12357 San Fernando Road | Sylmar Ca 91342 | 8183649188 | 2137924801 | 1201 Baldwin Park Blvd | Baldwin Park, Ca 91706 | Ngo, Jason | 9874 | 0 | 0 | 0 | 2025-10-20 | Replace Irrigation System, Highway Plantin | Los Angeles County In El Monte 0.2 Mile West Of Santa Anita Avenue Undercrossing To The San Gabriel River | 0 | 0 | 949870.53 | 999330.75 | 1014202.75 | 56587 | 2026-08-04 | 2024-10-23 | 2024-08-30 |  |  | 182 | 0 | 239 | 0 | X | X
07 | 07-4V5304 | 4V5304 | 07-LA-10-47.9/0 |  |  | Bosco Constructors Inc. | 21353 Mayall St. | Chatsworth Ca 91311 |  |  |  |  | Raj, Punjabi | 0 | 0 | 0 | 0 |  | Modify Drainage System And Construct Dppia | Los Angeles County In Claremont At 0.1 Mile East Of South Indian Hill Boulevard | 0 | 0 | 0 | 951098.96 | 951098.96 | 59458 |  | 2025-07-22 | 2025-06-24 |  |  | 0 | 0 | 140 | 0
07 | 07-2XP804 | 2XP804 | 07-LA-10-78.0/9.3 | 20.20 201130 |  | Flo Concrete | 902 S Vanhorn Ave | West Covina, Ca 91790 |  | 2139526068 | 601 South Glenoaks Blvd | Burbank Ca, 91502 | Bautista, Denrick | 0 | 0 | 0 | 0 | 2025-09-20 | Remove Concrete Slabs | La-10 Remove Concrete Slabs, Fill Voids W-Ith Slurry,Reconstruct Hma Shoulder, Reco-Nstruct Side Slopes, Construct Handscape. Dir' | 100 | 80 | 1302825.02 | 31296 | 1629800 | 56641 | 2026-01-31 | 2024-09-13 | 2024-09-09 |  |  | 146 | 0 | 60 | 0
07 | 07-339604 | 339604 | 07-LA-14-29.0/29.5 | HA42 | ACNH-P014- (107)E | Sukut Construction, Llc | 4010 W. Chandler Avenue | Santa Ana Ca 92704 | 7145405351 | 8187460669 | 13171 Telfair Ave Ste 101 | Sylmar, Ca 91342 | Mohsenzadeh, Ali | 19480 | 0 | 0 | 0 | 2025-08-20 | Protective Betterment, Regrade | In Santa Clarita From 0.9 Mile North Of Placerita Canyon Road To 0.2 Mile South Of Golden Valley Road | 69 | 98 | 16334943.93 | 15992648 | 16224825.64 | 43625 | 2026-04-20 | 2022-08-01 | 2022-07-06 | 2025-10-13 |  | 476 | 0 | 690 | 0 |  | X
07 | 07-316004 | 316004 | 07-LA-14-60.7/77 | H |  | Guy F. Atkinson | 611 Anton Blvd. Suite 1100 | Costa Mesa, Ca 92626 | 9498559755 | 2137937522 | 39115 Trade Center Dr Ste, 210 | Palmdale, Ca 95331 | Shih, James | 4371215.59 | 45842.81 | -192028.36 | 0 | 2025-10-20 | Reconstruct Pavement Structural | In Palmdale And Lancaster, From Technology Drive Undercrossing To Avenue A Overcrossing | 77 | 76 | 135107889.81 | 160193801 | 177766912.71 | 47290 | 2026-12-31 | 2023-03-03 | 2023-02-07 |  |  | 548 | 0 | 700 | 11 |  | X
07 | 07-2XK004 | 2XK004 | 07-LA-23-/0 | 20.20 201130 |  | Summer Construction, Inc. | P.O. Box 30 | Santa Paula, Ca 93061 | 8059339364 | 2137008447 | 1525 Rancho Conejo Blvd Ste 102 | Thousand Oaks, Ca 91320 | Tehrani, Joseph | 0 | 0 | 0 | 0 | 2025-09-20 | Repair Eroded Slopes | La 0.0 - Ven 3.3 To Clean Debris, Repair Eroded Slopes, Repave Damaged Roadway, Replace Damaged Drainage System And Headwallsdir'S | 100 | 60 | 1565211.51 | 29432 | 2609300 | 56476 | 2025-09-30 | 2024-09-12 | 2024-08-20 | 2025-10-15 |  | 241 | 0 | 120 | 0
07 | 07-0W4104 | 0W4104 | 07-LA-23-/8.9 | HM1 |  | Pavement Coatings Co. | 10240 San Sevaine Way | Jurupa Valley Ca 91752 |  | 2133306650 | 1525 Rancho Conejo, Ste 102 | Thousand Oaks, Ca 91320 | Singh, Ranjit | 5621.94 | 0 | 0 | 0 | 2025-10-20 | Apply Slurry Seal And Install Thermoplasti | Los Angeles County In And Near Malibu And Westlake Village From Route 1 To Ventura County Line | 99 | 93 | 2242202.99 | 2372011.25 | 2401411.25 | 51404 | 2025-11-26 | 2023-07-24 | 2023-06-19 |  |  | 89 | 0 | 90 | 0 |  | X
07 | 07-2XR304 | 2XR304 | 07-LA-27-/11 | 20.XX 201130 |  | Flo Engineering Inc | 902 S Vanhorn Ave | West Covina, Ca 91790 |  | 3107159500 | 112975 W. Culver Blvd | Los Angeles, Ca 90066 | Martinez, Elizabeth | 0 | 0 | 0 | 0 | 2025-10-20 | Repair Storm & Fire Damage/Debris | La County,City Of La On La-27 From La-1Pchto Mulholland Dr To Stabilize Damagd Slopefrom Fire & Storm-Clean Debris & D-Systemsdir' | 54 | 85 | 10618672.4 | 251300 | 12550000 | 57340 | 2028-03-24 | 2025-03-18 | 2025-03-04 |  |  | 162 | 0 | 300 | 0 |  | X
07 | 07-322904 | 322904 | 07-LA-27-/18.6 | HA22 | CSTP-S027- (006)E | C. A. Rasmussen, Inc. | 28548 Livingston Avenue | Valencia Ca 91355 | 6613679040 | 8186130956 | 23369 Leonora Dr | Woodland Hills, Ca 91367 | Gurfinkel, Vladimir | 344729.35 | 1180627.68 | 171449.7 | 0 | 2025-10-20 | Remove Existing Ac Pavement & Hma Overlay. | Los Angeles County In And Near Los Angelesfrom Route 1 To Devonshire Street | 65 | 74 | 32814688.34 | 40633353 | 43430230.98 | 54084 | 2026-08-28 | 2023-11-30 | 2023-11-06 |  |  | 390 | 0 | 600 | 0 |  | X
07 | 07-2XN904 | 2XN904 | 07-LA-27-/5 | 20.XX 201130 |  | Flo Engineering Inc Dba Flo Concrete | 902 S Vanhorn Ave | West Covina, Ca 91790 |  | 3107159500 | 12975 W Culver Blvd | Los Angeles, Ca 90066 | Martinez, Elizabeth | 0 | 0 | 0 | 0 | 2025-10-20 | Repair Slope Due To Storm Damage | In La County On La-27 Pm 0.0 To 5.0 Stabilize/Repair Var Slope Location Repaireroded Concrt Rsp Due To Heavy Storms Dir'S Emergenc | 94 | 22 | 4206728.19 | 53136 | 19121800 | 55769 | 2026-03-30 | 2024-05-10 | 2024-03-20 |  |  | 178 | 65 | 120 | 0
07 | 07-2XT904 | 2XT904 | 07-LA-47-1.6/1.6 | 20.20 201130 |  | Griffith Company | 3050 E Birch St | Brea, Ca 92821 |  | 2133100860 | 970 W 190Th Ste 270 | Torrance Ca 90502 | Shahriari, Shahnam | 0 | 0 | 0 | 0 | 2025-10-20 | Repair Steel Fingers | La-47 To Repair Steel Fingers At Vtb. Weldsteel Plates.Remove & Replace Fractured & Failed Steel Fingers. Dir'S Emergency Force Ac | 10 | 5 | 234639.43 | 16958 | 4868500 | 59695 | 2026-01-09 | 2025-06-11 | 2025-05-16 |  |  | 6 | 0 | 60 | 0 |  | X
07 | 07-2XA704 | 2XA704 | 07-LA-47-/3.3 | 20.80 110.00 |  | R.J. Noble Company | 15505 E Lincoln Ave | Orange, Ca 92865 |  | 2137985950 | 13230 Firestone Blvd Suite A | Santa Fe Springs, Ca 90670 | Nguyen, Khanh-Van | 0 | 0 | 0 | 0 | 2025-09-20 | Remove/Replace Ac Surfacing (Digouts) | La County City Of Carson Sr-47 From Lomitablvd To Del Amo Blvd To Remove/Replace Ac Digouts&Replace Pavement Markings/Delinetndir' | 100 | 77 | 3053233.47 | 11929 | 3961400 | 57515 | 2025-09-30 | 2024-10-09 | 2024-09-27 |  |  | 66 | 0 | 60 | 0
07 | 07-0Y1404 | 0Y1404 | 07-LA-60-23.0/0 |  |  | Rv Concrete, Inc. | 605 E. Commercial Street | Anaheim Ca 92801 |  | 9093967586 | 721 Brea Canyon Rd #6 | Walnut, Ca 91789 | Doughly, Joe | 0 | 0 | 0 | 0 | 2025-09-23 | Mainline Slabs, Ramps, Gores, Aux Lanes, S | Los Angeles County In Diamond Bar From Brea Canyon Road Undercrossing To 0.4 Mileeast Of Grand Avenue Overcrossing | 100 | 100 | 1234992.89 | 1234567.89 | 1234567.89 | 58635 | 2025-09-23 | 2025-06-09 | 2025-04-29 | 2025-10-22 |  | 37 | 0 | 100 | 0 |  | X
07 | 07-0Y1804 | 0Y1804 | 07-LA-60-/3.3 |  |  | Pavement Coatings Co. | 10240 San Sevaine Way | Jurupa Valley Ca 91752 | 9519344719 | 2132691320 | 902 San Gabriel Blvd | Rosemead Ca 91770 | Vong, Jeanette | 516808.49 | 0 | 0 | 2500 | 2025-10-20 | Replace Asphalt Concrete Surfacing And Slu | Los Angeles County At Various Locations From Junction Route 10 To Route 60/710 Separation | 58 | 76 | 1231471.06 | 1456586.3 | 1551586.3 | 58616 | 2025-12-22 | 2025-06-09 | 2025-04-28 |  |  | 58 | 0 | 100 | 0 |  | X
07 | 07-210624 | 210624 | 07-LA-71-1.6/4.8 | HE13 |  | Ohl Usa, Inc. | 34 Executive Park Suite 180 | Irvine Ca 92614 | 9492424432 | 3102619100 | 1041 W Badillo, Suite 112 | Covina, Ca 91722 | Wang, Mike | 3092954.37 | 0 | 0 | 0 | 2025-10-20 | Upgrade From Expressway To Freeway | La County Route 71 Pm R1.6/4.8 In Pomona From Mission Blvd To Rte 60 | 91 | 90 | 102231363.99 | 85920262.42 | 113795039.62 | 41521 | 2026-10-31 | 2021-03-16 | 2021-02-05 |  |  | 975 | 0 | 970 | 104 |  | X
07 | 07-0Y1704 | 0Y1704 | 07-LA-71-3.4/14.8 |  |  | Rv Concrete, Inc. | 605 E. Commercial Street | Anaheim Ca 92801 |  | 9512323742 | 1041 W. Badillo St Suite 112 | Covina, Ca 91722 | Hong, Hai | 15400 | 0 | 0 | 0 | 2025-10-20 | Slurry Seal. | Los Angeles County From Junction Route 57 To Valley Boulevard Undercrossing | 28 | 95 | 983983.03 | 949949 | 964967.13 | 58636 | 2026-01-28 | 2025-06-09 | 2025-06-03 | 2025-10-31 |  | 25 | 0 | 90 | 0 |  | X
07 | 07-346504 | 346504 | 07-LA-91-6.0/20.7 |  | ACNH-P091- (160)E | Security Paving Company, Inc. | 3075 Townsgate Road, Suite 20 | Westlake Village Ca 91361 | 8183629200 | 2137937974 | 4281 Katella Ave Ste 221 | Los Alamitos, Ca 90720 | Lee, Peter | 0 | 0 | 0 | 0 |  | Replace Overhead Signs & Sign Structures, | Los Angeles County On Route 91 At Various Locations From Vermont Avenue In Los Angeles To The Orange County Line In Cerritos | 0 | 0 | 0 | 24031447 | 24031447 | 59557 | 2028-07-03 | 2025-07-30 | 2025-07-14 |  |  | 0 | 0 | 610 | 0
07 | 07-3203U4 | 3203U4 | 07-LA-91-16.6/16.8 | HA22 | ACIM-X037- (232)E | Rasmussen/Vanguard | 28548 Livingston Avenue | Valencia Ca 91335 | 6613679040 | 2133306640 | 4281 Katella Ave Suite 221 | Los Alamitos, Ca 90720 | Oregel, Martin | 539130.94 | 36413.61 | 20106.34 | 0 | 2025-10-20 | Place Concrete Pavement And High Friction | Los Angeles County On Route 605 From 0.2 Mile North Of Katella Avenue Undecrossing To 0.1 Mile North Of Telegraph Road Undercrossi | 54 | 87 | 46492437.36 | 49941871.9 | 52260440.32 | 50885 | 2026-05-20 | 2023-07-06 | 2023-06-20 |  |  | 474 | 0 | 870 | 0 |  | X
07 | 07-0W0604 | 0W0604 | 07-LA-101-1.0/9.2 | HM1 |  | 3Sixty Innovation, Inc. | 3555 Rosecrans St 114-110 | San Diego Ca 92110 | 8583041093 | 5623459865 | 13320 S Firestone Blvd Ste A | Santa Fe Springs, Ca 90670 | Frempong, Sam | 31707.26 | 0 | 0 | 0 | 2025-07-20 | Slabs Repair, Digouts - Shoulders, | In Los Angeles County In Los Angeles From Spring St Oc To Barham Blvd Oc, Slabs Repair, Digouts - Shoulders, Gores, 2 Ramps | 98 | 91 | 2871157.76 | 3028403.5 | 3097385.63 | 43964 | 2025-11-30 | 2022-08-24 | 2022-06-28 |  |  | 295 | 0 | 300 | 0 |  | X
07 | 07-385204 | 385204 | 07-LA-101-1.0/10.3 |  |  | Yakar | 689 East San Bernardino Rd | Covina Ca 91723 | 9095991612 | 2132691320 | 902 San Gabriel Blvd | Rosemead, Ca 91770 | Vong, Jeanette | 1200 | 0 | 0 | 0 | 2025-10-20 | La-101, Clean Ca Beautification | The Project Is Located On Route 101 In Los Angeles County Between Lankershim Blvd And Beaudry Ave | 96 | 90 | 4837777.41 | 4442641 | 5790947.5 | 43825 | 2025-12-01 | 2022-08-15 | 2022-07-12 |  |  | 689 | 0 | 1000 | 282 |  | X
07 | 07-0W2904 | 0W2904 | 07-LA-101-1.5/10.9 | HM |  | Peterson-Chase General Engineering Construction, Inc. | 16351 Construction Circle Wes | Irvine Ca 92606 |  | 2132691320 | 902 San Gabriel Blvd | Rosemead, Ca 91770 | Vong, Jeanette | 925 | 0 | 0 | 0 | 2025-10-20 | Deck Methacrylate, Joint Seal Replacement, | Los Angeles County In Los Angeles At Various Locations | 99 | 96 | 6536061.93 | 6442038.48 | 6956795.1 | 50726 | 2025-10-23 | 2023-06-29 | 2023-06-08 |  |  | 296 | 0 | 300 | 0 |  | X
07 | 07-329604 | 329604 | 07-LA-101-6.2/8 | HB34 | ACNH-Q101- (406)E | Bosco Constructors, Inc. | 21353 Mayall St. | Chatsworth Ca 91311 | 8187000304 | 2139526068 | 601 S Glenoaks Blvd Suite 310 | Burbank, Ca 91502 | Bautista, Denrick | 15500 | 0 | 0 | 0 | 2025-07-20 | Roadside Safety Improvements | In The City And County Of Los Angeles From Wilton Place Overcrossing To Pilgrimage Overcrossing | 9 | 15 | 482000 | 3189245 | 3554309.03 | 47404 | 2026-07-20 | 2023-03-08 | 2023-02-08 |  |  | 42 | 0 | 460 | 0 |  | X
07 | 07-346304 | 346304 | 07-LA-101-7.9/11.8 |  | ACNH-Q101- (439)E | Chumo Construction, Inc. | 14425 Joanbridge Street | Baldwin Park Ca 91706 |  | 8186130956 | 23369 Leonora Dr | Woodland Hills, Ca 91367 | Gurfinkel, Vladimir | 11716 | 0 | 0 | 0 | 2025-10-20 | Install Rubberized Hot Mixed Asphalt. | Los Angeles County In The City And County Of Los Angeles From 0.1 Mile South Of Pilgrimage Overcrossing To Route 101/170 Separatio | 4 | 1 | 314613.11 | 21039634.56 | 21109634.56 | 58396 | 2027-11-19 | 2025-05-28 | 2025-04-28 |  |  | 36 | 0 | 810 | 0 |  | X
07 | 07-385404 | 385404 | 07-LA-101-10.3/10.3 |  |  | Griffith Company | 12200 Bloomfield Ave | Santa Fe Springs Ca 90670 |  | 8186130956 | 23369 Leonora Dr | Woodland Hills, Ca 91367 | Gurfinkel, Vladimir | 3040 | 0 | 0 | 0 | 2025-10-20 | Install Chain Link Fence And Place Wood Mu | Los Angeles County In Los Angeles On Route101 At Lankershim Boulevard And On Route 170 From Route 134/101/170 Separation To 0.2 Mi | 0 | 0 | 2237163.43 | 2230430.5 | 2300498.9 | 50725 | 2025-11-10 | 2023-06-22 | 2023-05-26 |  |  | 366 | 0 | 375 | 0 | X | X
07 | 07-346004 | 346004 | 07-LA-101-11.0/23.5 |  | ACNH-Q101- (425)E | Yakar | 689 East San Bernardino Rd | Covina Ca 91723 | 9095991612 | 8186130956 | 23369 Leonora Dr | Woodland Hills, Ca 91367 | Gurfinkel, Vladimir | 88280 | 0 | 0 | 0 | 2025-10-20 | Construct Mvps, Pave Beyond The Gore, Inst | Los Angeles County At Various Locations From North Of Vineland Avenue To North Of Winnetka Avenue | 91 | 93 | 2532433.91 | 2464577 | 2624788.62 | 56215 | 2025-11-12 | 2024-08-13 | 2024-07-12 |  |  | 177 | 0 | 195 | 0 |  | X
07 | 07-388704 | 388704 | 07-LA-101-19.7/20 | HB71 |  | Snz Contractors Inc | 8583 Irvine Center Drive #224 | Irvine Ca 92618 |  | 5625725983 | 9225 Cranford Ave | Pacoima, Ca 91331 | Bui, Kevin | 0 | 0 | 0 | 0 | 2025-02-20 | Construct Temporary Chain Link Railing And | Los Angeles County In Los Angeles At Louise Avenue Overcrossing | 100 | 99 | 427294.44 | 350007 | 423944.5 | 9923 | 2025-12-29 | 2023-02-21 | 2023-01-11 |  |  | 55 | 0 | 40 | 0 |  | X
07 | 07-307104 | 307104 | 07-LA-101-32.8/33.8 |  |  | C. A. Rasmussen, Inc. | 28548 Livingston Avenue | Valencia Ca 91355 | 6643679040 | 3103456201 | 23369 Leonora Dr | Woodland Hills, Ca 91367 | Gurfinkel, Vladimir | 1326 | 0 | 0 | 0 | 2025-10-20 | Wildlife Habitat Connectivity | In La, Wildlife Crossing @ Liberty Canyon At Or In The Vicinity Of Liberty | 62 | 43 | 24435002.78 | 22719732.3 | 56295740.33 | 42300 | 2027-08-18 | 2022-04-14 | 2022-03-17 |  |  | 774 | 0 | 1250 | 0 |  | X
07 | 07-320104 | 320104 | 07-LA-101-/1.5 | HA42 |  | Fec Future Contractors And Engineers, Inc. | 184 Technology Drive, Suite 2 | Irvine Ca 92618 | 9493289758 | 9093224628 | 902 San Gabriel Blvd. | Rosemead, Ca 91770 | Vong, Jeanette | 2250 | 4683.65 | 0 | 0 | 2025-09-20 | Stormwater Source Control | In Los Angeles County In Los Angeles, From Routes 5/101 Interchange To Figueroa Street | 0 | 0 | 3700493.39 | 3720860.53 | 3734935.16 | 9843 | 2027-11-16 | 2022-11-28 | 2022-11-01 |  |  | 454 | 0 | 930 | 56 | X | X
07 | 07-327304 | 327304 | 07-LA-103-.1/.1 | HA22 | ACNH-P103- (005) | Shimmick Construction Company, Inc. | 530 Technology Dr. #300 | Irvine Ca 92618 | 9493331500 | 5625725852 | 12975 Culver Blvd | Los Angeles, Ca 90066 | Martinez, Elizabeth | 1896 | 0 | 0 | 0 | 2025-10-20 | Construct Larger Pump Plant | In Los Angeles County In Los Angeles At Henry Ford Avenue Off-Ramp | 88 | 92 | 18146988.93 | 12248070.82 | 19597483.78 | 42467 | 2026-03-13 | 2022-06-09 | 2022-04-21 |  |  | 699 | 0 | 590 | 205 |  | X
07 | 07-355604 | 355604 | 07-LA-105-2.0/0 |  |  | Griffith Company | 3050 E. Birch St | Brea Ca 92821 | 3235858585 | 2133100860 | 970 W. 190Th Street Suite 270 | Torrance, Ca 90502 | Shahriari, Shahnam | 150058.2 | 0 | 0 | 0 | 2025-10-20 | Construct A Maintenance Equipment Training | Los Angeles County In Los Angeles At 0.1 Mile West Of Route 105/405 Separation | 4 | 2 | 260353.7 | 14796999 | 14848732.6 | 57555 | 2027-09-03 | 2025-03-13 | 2025-02-20 |  |  | 19 | 0 | 500 | 0 |  | X
07 | 07-2XH7A4 | 2XH7A4 | 07-LA-105-2.2/2.2 | 20.20 201130 |  | Crosstown Electrical & Data Inc | 5454 Diaz St | Irwindale Ca 91706 |  | 8182547484 | 13230 Firestone Blvd Ste E | Santa Fe Springs Ca 90670 | Karout, Ali | 0 | 0 | 0 | 0 | 2024-11-20 | Repair Failed Vfd In Tunnel#4 | La-105 City Of Hawthorne To Repair Failed Vfd'S/Breakers Within Ventilation System'Smotor Control In Tunnel 53-2441F Tunnel#4 Dir' | 16 | 96 | 701817.72 | 4487 | 777000 | 55365 | 2025-12-12 | 2024-02-13 | 2023-12-29 |  |  | 59 | 0 | 60 | 300 |  | X
07 | 07-357004 | 357004 | 07-LA-105-4.3/5 | HB1 | HSIM-1053- (993)E | Polo Engineering, Inc. | 30758 Sloan Canyon Rd | Castaic, Ca 91384 | 3104862065 | 2133939751 | 4281 Katella Ave., Suite 221 | Los Alamitos, Ca 90720 | Vergara,Joahnna | 134491.65 | 40452.14 | 0 | 0 | 2025-07-20 | Modifying Ramp Metering Systems. | Los Angeles County In Inglewood And Hawthorne From 0.1 Mile East Of Yukon Avenue Under Crossing To 0.3 Mile East Of Crenshaw Boule | 97 | 88 | 2240675.35 | 2398430.6 | 2393353.14 | 55389 | 2025-08-13 | 2024-03-07 | 2024-02-08 |  |  | 232 | 0 | 240 | 0 |  | X
07 | 07-385604 | 385604 | 07-LA-105-9.0/9.4 |  |  | Jfl Electric, Inc | 8257 Compton Avenue | Los Angeles Ca 90001 | 3235814400 | 5625725983 | 4281 Katella Ave. | Los Alamitos, Ca 90720 | Oregel, Martin | 6300 | 0 | 0 | 0 | 2025-07-20 | Clean Ca Beautification | On Rte 105 In The Community Of Willowbrook From Pm R9.0 To Pm 9.4 | 77 | 97 | 1998349.14 | 1923018 | 2013768.51 | 43504 | 2026-01-12 | 2022-07-29 | 2022-07-07 |  |  | 384 | 0 | 500 | 0 |  | X
07 | 07-4V4904 | 4V4904 | 07-LA-105-17.5/17.8 |  |  | Accu Construction, Inc. | 14751 Plaza Drive Suite L | Tustin Ca 92780 | 7146414730 | 5623459894 | 13230 Firestone Blvd. | Santa Fe Springs, Ca 90670 | Martinez, Francisco | 2920 | 0 | 0 | 0 | 2025-10-20 | Replace Planting And Irrigation System. | Los Angeles County In Norwalk From The Sangabriel River To Route 105/605 Separation | 74 | 94 | 621826.16 | 632142 | 660402.29 | 56136 | 2026-03-17 | 2024-07-03 | 2024-06-06 |  |  | 277 | 0 | 375 | 0 |  | X
07 | 07-2XJ504 | 2XJ504 | 07-LA-105-20.0/2 | 20.XX 201130 |  | Crosstown Electrical&Data Inc | 5454 Diaz Street | Irwindale, Ca 91706 | 6268136693 | 8182547484 | 13230 Firestone Blvd | Santa Fe Springs, Ca 90670 | Karout, Ali | 0 | 0 | 0 | 0 | 2025-10-20 | Repair/Replace Vfd In Various System | La County City Of Hawthorne@E105 N&S 405 Connector Tunnels 5&8 53-2436G 53-2437G Repair/Replace Vfd In Vent,Fire&Electricaldir'S E | 58 | 75 | 2634131.3 | 15383 | 3495000 | 56580 | 2026-01-23 | 2024-10-04 | 2024-09-23 |  |  | 87 | 0 | 150 | 0 |  | X
07 | 07-2XQ304 | 2XQ304 | 07-LA-105-/18.1 | 20.20.201131 |  | Jfl Electric Inc | 8257 Compton Avenue | Los Angeles, Ca 90001 | 2138172443 | 8182547484 | 13230 Firestone Blvd | Santa Fe Springs, Ca 90670 | Karout, Ali | 0 | 0 | 0 | 0 | 2025-10-20 | Repair Transportation Management Systems | La County,Various Cities On La-105 To Repair/Remove/Replace Damaged Tms Elementsinstall Security Measures&Restore Tms Elemdir'S Em | 25 | 59 | 2011205.97 | 23524 | 3417000 | 58235 | 2026-07-14 | 2025-05-15 | 2025-04-25 |  | S | 59 | 0 | 240 | 0 |  | X
07 | 07-4W7804 | 4W7804 | 07-LA-110-6.8/19.5 | HM3 |  | Autobahn Construction, Inc. | 933 N. Batavia St. | Orange Ca 92867 | 7147697025 | 3103456267 | 970 W. 190Th Street Suite 270 | Torrance, Ca 90502 | Herrera, Edgar | 22950 | 0 | 0 | 0 | 2024-01-20 | Apply Deck Methacrylate, Replace | 07-110- Pm 6.8/19.5 | 91 | 65 | 1463252.14 | 2144980.84 | 2217292.84 | 41665 | 2025-11-30 | 2021-05-20 | 2021-04-26 |  |  | 109 | 0 | 120 | 0
07 | 07-386304 | 386304 | 07-LA-110-14.0/21 |  |  | Diversified Landscape Co. | 21730 Bundy Canyon Road | Wildomar Ca 92595 |  | 3103456188 | 970 W. 190Th Street Suite 270 | Torrance, Ca 90502 | Gallardo, Samuel | 7527 | 0 | 0 | 0 | 2025-10-20 | Construct Chain Link Fences, Rock Blanket, | Los Angeles County In Los Angeles From Imperial Highway Overcrossing To Twenty-First Street Pedestrian Overcrossing | 100 | 93 | 2227186.69 | 2372646.35 | 2296379.69 | 9916 | 2025-12-05 | 2023-04-07 | 2023-03-13 |  |  | 533 | 0 | 870 | 0 |  | X
07 | 07-2XJ104 | 2XJ104 | 07-LA-110-21.4/25.7 | 20.XX 201130 |  | Ferreira Construction Co Inc Dba Ferreira Coastal Constr.Co | 10370 Commerce Center Dr B200 | Rancho Cucamonga, Ca 91730 |  | 8182547484 | 13230 Firestone Blvd Suite E | Santa Fe Springs, Ca 90670 | Karout, Ali | 0 | 0 | 0 | 0 | 2025-10-20 | Repair Vandalized Communication Systems | La County In City Of La At The Dtla Wrap- Around On Routes 110,5,10 & 101 To Restorerepair Hwy Lighting & Fiber Optics Comm Sydir' | 83 | 53 | 6010843.74 | 19656 | 11250000 | 53144 | 2026-01-30 | 2023-09-29 | 2023-08-15 |  |  | 322 | 0 | 90 | 300
07 | 07-2XQ504 | 2XQ504 | 07-LA-110-26.7/30.7 | 20.XX 201131 |  | P T M General Engineering Services Inc | 5942 Acorn St | Riverside, Ca 92504 |  | 2137937193 | 1041 W. Badillo Suite 112 | Covina, Ca 91722 | Pham, Ryan | 0 | 0 | 0 | 0 | 2025-10-20 | Restore & Repair Wire Theft Damages | In La County In City Of La On La-110 Alongarroyo Seco Parkway To Restore & Repair Wire Theft Damages Dir'S Emergency Force Account | 54 | 22 | 624288.99 | 13810 | 2792000 | 58936 | 2025-11-20 | 2025-05-20 | 2025-04-25 |  |  | 98 | 0 | 180 | 0 |  | X
07 | 07-2XT604 | 2XT604 | 07-LA-110-30.5/30.7 | 20.XX 201130 |  | Hartfield Construction Corp | 11908 Clark St Unit A | Arcadia, Ca 91006 |  | 8184829304 | 2090 Fern Lane | Glendale, Ca 91208 | Tran, Danglong | 0 | 0 | 0 | 0 | 2025-08-20 | Repair Roadway Slope & Irrigation | In La County, City Of S Pasadena S/B La 110 At Prospect Ave To Repair Roadway Cutslope/Side Slide Down To Ln 3 On S/B La 110Dir'S | 100 | 23 | 150075.34 | 13194 | 644700 | 59461 | 2026-09-10 | 2025-07-15 | 2025-04-17 |  |  | 87 | 0 | 60 | 0
07 | 07-336804 | 336804 | 07-LA-118-4.5/9.1 | HB34 | ACNH-P118- (069)E | Martinez Landscape Co., Inc | 12357 San Fernando Road | Sylmar Ca 91342 | 8183649188 | 8183642760 | 13171 Telfair Ave Suite 101 | Sylmar, Ca 91342 | Chavez, Efraim | 34125 | 6431.44 | 0 | 0 | 2025-10-20 | Construct Maintenance Vehicle | In The Cities Of Granada Hills And Porter Ranch, From 700 Feet West Of Tampa Avenue To Woodley Avenue | 81 | 85 | 1417839.92 | 1871647 | 1672025.5 | 47005 | 2025-10-21 | 2023-02-23 | 2022-11-17 |  |  | 333 | 0 | 410 | 0 |  | X
07 | 07-385904 | 385904 | 07-LA-118-10.0/13.2 |  |  | Accu Construction, Inc. | 14751 Plaza Drive Suite L | Tustin Ca 92780 | 7146414730 | 5625725983 | 9225 Cranford Ave. | Pacoima, Ca 91331 | Bui, Kevin | 2660 | 0 | 0 | 0 | 2025-08-20 | Install Irrigation Systems & Place Rock Bl | Los Angeles County In Los Angeles From 0.1Mile West Of Sepulveda Boulevard Undercrossing To Glenoaks Boulevard Undercrossing | 92 | 95 | 4076780.61 | 4064251 | 4152171.7 | 49324 | 2025-12-31 | 2023-05-12 | 2023-04-14 |  |  | 512 | 0 | 895 | 340 |  | X
07 | 07-322004 | 322004 | 07-LA-118-11.0/14 | HA42 | ACNH-P118- (071)E | Powell Constructors Inc | 8555 Banana Avenue | Fontana Ca 92335 | 9093568880 | 2138170162 | 25061 W Avenue Stanford,Ste 70 | Valencia, Ca 91355 | Bakhet, Wassem | 0 | 6016.09 | 0 | 0 | 2025-09-20 | Construct Stormwater Treatment Devices. | The City And County Of Los Angeles From 0.1 Mile West Of Arleta Avenue Undercrossing To 0.1 Mile West Of Route 118/210 Separation | 85 | 96 | 4497219.16 | 4229039.2 | 4618099.13 | 46526 | 2026-01-29 | 2023-02-01 | 2023-01-11 |  |  | 595 | 0 | 700 | 0 |  | X
07 | 07-355004 | 355004 | 07-LA-118-13.0/13.9 | HA22 |  | Beador Construction Company, Inc. | 26320 Lester Circle | Corona Ca 92883 | 9516747352 | 5625725983 | 9225 Cranford Ave | Pacoima Ca 91331 | Bui, Kevin | 16350 | 0 | 0 | 0 | 2025-09-20 | Replace Culvert Systems And Install Cured- | The City And County Of Los Angeles From 0.1 Mile East Of Herrick Avenue Undercrossing To 0.1 Mile West Of Route 118/210 Separatio | 38 | 89 | 1890159.25 | 2025300 | 2101934 | 55615 | 2025-10-30 | 2024-04-10 | 2024-03-19 | 2025-10-21 |  | 157 | 0 | 410 | 0 |  | X
07 | 07-2XS604 | 2XS604 | 07-LA-118-/0 | 20.20 201130 |  | Baltazar Construction, Inc | 236 E. Arrow Hwy | Covina, Ca 91722 |  | 8187460669 | 13171 Telfair Ave Ste 101 | Sylmar, Ca 91342 | Mohsenzadeh, Ali | 0 | 0 | 0 | 0 | 2025-10-20 | Remove/Repair Damaged Trees&Erosion Contrl | La County La-118,210,2,5,101,134 & 710 At Various Post Miles To Remove Fire-Damaged Trees&Repair Side Slopes&Erosion Control Dir'S | 84 | 70 | 769271.33 | 7660 | 1099200 | 57696 | 2025-10-28 | 2025-04-14 | 2025-02-21 |  |  | 84 | 0 | 100 | 0 |  | X
07 | 07-333704 | 333704 | 07-LA-138-43.4/51.4 |  | ACNH-P138- (067)E | A. M. Concrete, Inc. | 3075 Townsgate Rd #200 | Westlake Village Ca 91361 | 8183628400 | 2137929662 | 39115 Trade Ctr Dr | Palmdale Ca 93551 | Martinez, Roberto | 89220.88 | 102032.29 | 29246.9 | 0 | 2025-10-20 | Construct Ada Curb Ramps, Sidewalk, And Dr | Los Angeles County In Palmdale From Route 14 Junction (South) To Avenue T | 82 | 46 | 5057969.85 | 10394258.5 | 10756850.64 | 56291 | 2025-12-29 | 2024-08-30 | 2024-07-30 |  |  | 204 | 0 | 250 | 0
07 | 07-4V5204 | 4V5204 | 07-LA-138-59.7/0 |  |  | Polo Engineering, Inc. | 30758 Sloan Canyon Rd | Castaic Ca 91384 | 3104862065 | 2133939940 | 39115 Trade Ctr Dr Ste. 210 | Palmdale Ca 93551 | Martinez, Roberto | 310857.9 | 0 | 0 | 0 | 2025-10-20 | Signal And Lighting System. | Los Angeles County At Pearblossom At 126Thstreet East | 34 | 70 | 852092.34 | 1178090.5 | 1178090.5 | 56130 | 2025-12-02 | 2024-07-26 | 2024-06-25 |  |  | 89 | 0 | 120 | 140 |  | X
07 | 07-320804 | 320804 | 07-LA-164-4.0/6.9 | HB71 | CSTP-S164- (003)E | Calpromax Engineering, Inc. | 650 N. Rose Dr. #186 | Placentia Ca 92870 | 7145734599 | 2132164198 | 902 San Gabriel Blvd. | Rosemead, Ca 91770 | Azam, Shoaib Bin | 144531.92 | 90668.41 | 0 | 0 | 2025-10-20 | Construct Minor Concrete And Modifying Sig | Los Angeles County In South El Monte, El Monte And Rosemead At Various Locations Onroute 164 From Rush Street To Rudell Underpass | 47 | 58 | 4560480.58 | 7188691.9 | 7875255.03 | 54264 | 2026-04-16 | 2023-11-30 | 2023-11-01 |  |  | 331 | 0 | 700 | 0 |  | X
07 | 07-358804 | 358804 | 07-LA-170-16.6/19.8 | HB1 | HSNH-P170- (007)E | Truesdell Corporation Of California, Inc. | 1310 W 23Rd Street | Tempe Az 85282 | 6024371711 | 5625725983 | 9225 Cranford Ave | Pacoima, Ca | Bui, Kevin | 0 | 104111.9 | 0 | 0 | 2025-09-20 | Install High Friction Surface | On Route 170 In Los Angeles County From Oxnard Street To Roscoe Blvd. (Pm R16.6/R19.8) | 80 | 98 | 641541.5 | 459459 | 655608.4 | 45365 | 2025-12-12 | 2022-11-15 | 2022-10-05 | 2025-09-22 |  | 80 | 0 | 100 | 0 |  | X
07 | 07-326804 | 326804 | 07-LA-210-9.7/51.9 | HB71 |  | Sully-Miller Contracting Company | 135 S State College Blvd #400 | Brea Ca 92821 | 7145789600 | 8182665626 | 9225 Cranford Avenue | Pacoima, Ca 91331 | Shih, James | 13500 | 0 | 0 | 0 | 2025-08-20 | Americans With Disability (Ada) | At Route 210 From Pm R9.71 To Pm R51.923 | 96 | 100 | 23984208.36 | 23680000 | 24120233.77 | 42429 | 2025-08-31 | 2021-12-23 | 2021-12-14 |  |  | 780 | 0 | 810 | 0 |  | X
07 | 07-0Y1604 | 0Y1604 | 07-LA-210-9.9/22.5 |  |  | Rv Concrete, Inc. | 605 E. Commercial Street | Anaheim Ca 92801 |  | 8184829304 | 2090 Fern Lane | Glendale, Ca 91208 | Tran, Bill | 3029756.07 | 0 | 0 | 20000 | 2025-10-20 | Slab Replacement, Slurry Seal, And Digouts | Los Angeles County, In Los Angeles, La Canada Flintridge, Glendale, And Pasadena From Big Tujunga Wash Bridge To Arroyo Boulevard | 44 | 80 | 4361656.34 | 4864456 | 4864456 | 59278 | 2026-01-29 | 2025-07-09 | 2025-06-26 |  |  | 53 | 0 | 120 | 0 |  | X
07 | 07-2XF404 | 2XF404 | 07-LA-210-15.4/15.4 | 20.201130 |  | Sgv Enterprises, Inc. | 615 Las Tunas Dr, Suite J | Arcadia, Ca 91007 |  | 8182547383 | 2090 Fern Lane | Glendale, Ca 91208 | Shalviri, Ali | 0 | 0 | 0 | 0 | 2025-08-20 |  | Los Angeles County On La 210 La Crescenta Repair Damage System, Repair Sinkhole And Shoulder Of La 210 Dir'S Emergency Force Accou | 100 | 50 | 2367736.77 | 8700 | 4695000 | 48885 | 2025-12-30 | 2023-04-24 | 2023-02-28 |  |  | 30 | 0 | 30 | 0
07 | 07-330704 | 330704 | 07-LA-210-15.6/18.5 | HA25 | ACIM-210 -1(853)E | Martinez Landscape Co., Inc | 12357 San Fernando Road | Sylmar Ca 91342 | 8183649188 | 8186372506 | 2090 Fern Lane | Glendale, Ca 91208 | Shalviri, Ali | 5400 | 0 | 0 | 0 | 2025-10-20 | To Restore Existing Irrigation | In Los Angeles County In Glendale And La Canada Flintridge From Lowell Avenue Undercrossing To Waltonia Drive Undercrossing | 0 | 0 | 3219109.5 | 3258059.5 | 3278059.5 | 9847 | 2026-03-30 | 2021-10-01 | 2021-09-09 |  |  | 272 | 0 | 1000 | 0 | X | X
07 | 07-348704 | 348704 | 07-LA-210-18.7/19.7 |  | ACIM-2101- (857)E | Aldridge Electric, Inc. | 844 East Rockland Road | Libertyville Il 60048 | 8476805200 | 8184829304 | 2090 Fern Lane | Glendale, Ca 91208 | Tran, Danglong | 0 | 0 | 0 | 0 |  | Modify Tunnel Lighting Systems. | Los Angeles County In La Canada Flintridgeat E2-W210 Connector Undercrossing And At Foothill La Canada Tunnel | 0 | 0 | 0 | 7717103.4 | 7717103.4 | 56494 | 2027-01-31 | 2024-10-03 | 2024-08-13 |  | S | 0 | 0 | 255 | 0
07 | 07-348204 | 348204 | 07-LA-210-19.4/27 |  | ACIM-2101- (858)E | Bosco Constructors Inc. | 21353 Mayall St. | Chatsworth Ca 91311 | 8187000304 | 8184829304 | 2090 Fern Ln | Glendale, Ca 91208 | Tran, Danglong | 825406 | 0 | 0 | 525000 | 2025-10-20 | Restore Bridge And Drainage System, And Co | Los Angeles County In La Canada Flintridgeand Pasadena At Various Locations From 0.1Mile East Of Winery Canyon Flume Overcrossing | 11 | 17 | 1652757.5 | 9556359.5 | 9556359.5 | 58075 | 2028-02-22 | 2025-05-09 | 2025-03-17 |  |  | 69 | 0 | 650 | 0 |  | X
07 | 07-4V5004 | 4V5004 | 07-LA-210-24.7/25.3 |  |  | Calmex Engineering, Inc. | 2750 S. Lilac Ave | Bloomington Ca 92316 | 9095461311 | 8182547383 | 2090 Fern Lane | Glendale California 91208 | Shalviri Aliasghar | 165649.29 | 0 | 0 | 0 | 2025-10-20 | Overlay Ac Shoulder, Replace Shoulder, And | Los Angeles County In Pasadena From 0.1 Mile East Of Orange Grove Boulevard Overcrossing To 0.2 Mile West Of Marengo Avenue Overcr | 100 | 99 | 742192.49 | 789025.1 | 699295.1 | 59095 | 2025-11-26 | 2025-06-26 | 2025-06-13 |  |  | 60 | 0 | 60 | 0 |  | X
07 | 07-301704 | 301704 | 07-LA-210-33.6/36.5 | HA42 | ACNH-X037- (227)E | Griffith Company | 3050 East Birch Street | Brea Ca 92821 | 7149845500 | 6265726732 | 1201 Baldwin Park Blvd | Baldwin Park, Ca 91706 | Chaudhari, Sushil | 3500 | 0 | 0 | 0 | 2025-10-20 | Stabilize Soil And Erosion Control. | On Rte 210 From 0.1 Mile West Of South Magnolia Ave Uc To 0.1 Mile East Of Rte 210/605 Sep And Rte 605 From 0.1 Mile South To 0.2 | 0 | 0 | 2944854.35 | 3081915.2 | 3514069.99 | 42353 | 2027-10-06 | 2022-04-20 | 2022-03-22 |  |  | 512 | 0 | 1000 | 0 | X | X
07 | 07-356104 | 356104 | 07-LA-210-37.8/39.1 |  |  | Doja Inc | 5050 Mission Blvd | Ontario Ca 92761 | 9096281999 | 5622547785 | 1041 W Badillo St #112 | Covina Ca 91722 | Barbosa, Jose | 221519.8 | 0 | 0 | 84769.39 | 2025-08-20 | Replace Pump Plant, Drainage, & Electrical | Los Angeles County In Azusa From 0.1 Mile West Of Irwindale Avenue To 0.2 Mile East Of West Vernon Avenue | 34 | 15 | 1015193.46 | 6900000 | 6960198.8 | 56495 | 2026-04-23 | 2024-10-01 | 2024-08-27 |  |  | 85 | 0 | 250 | 0 |  | X
07 | 07-2XQ604 | 2XQ604 | 07-LA-210-/0 | 20.XX 201130 |  | Diverscape Inc Dba Diversifiedlandscape Co | 21730 Bundy Canyon Rd | Wildomar, Ca 92595 | 9512451686 | 8058577053 | 13171 Telfair Avenue Suite 101 | Sylmar, Ca 91342 | Chavez, Efraim | 0 | 0 | 0 | 0 | 2025-10-20 | Remove Hazardous Fallen Trees | In La County On Various Routes Across Multiple Cities To Remove Hazardous Trees That Have Fallen As A Result Of High Windsdir'S Em | 50 | 10 | 77588.33 | 3564 | 789000 | 59935 | 2025-12-01 | 2025-07-10 | 2025-03-07 |  |  | 30 | 0 | 60 | 0 |  | X
07 | 07-4V1404 | 4V1404 | 07-LA-213-6.2/6.2 | HB4N |  | Crosstown Electrical And Data, Inc. | 5454 Diaz Street | Irwindale Ca 91706 | 6268136693 | 5623453134 | 13230 Firestone Blvd.,Ste E-2 | Santa Fe Springs, Ca 90670 | Turay, Sulaiman | 0 | 0 | 0 | 0 |  | Install Traffic Signal And Ada | Intersection Of Western Ave (Sr-213) And 242Nd Place In The City Of La | 0 | 0 | 0 | 623377 | 623377 | 41568 | 2025-12-11 | 2021-04-08 | 2021-03-18 |  | S | 0 | 0 | 60 | 0
07 | 07-4V2304 | 4V2304 | 07-LA-213-6.4/0 |  |  | Ptm General Engineering Services Inc. | 5942 Acorn St. | Riverside Ca 92504 |  | 5623453142 | 13230 Firestone Blvd | Santa Fe Springs, Ca 90670 | Arikat, Ata | 0 | 0 | 0 | 0 |  | Modifying Signal And Lighting Systems. | Los Angeles County In Los Angeles At 238Thstreet | 0 | 0 | 0 | 624024 | 624024 | 56133 | 2026-03-12 | 2024-07-26 | 2024-06-28 |  |  | 0 | 0 | 120 | 0
07 | 07-338704 | 338704 | 07-LA-405-12.9/21.5 | HB34 | ACIM-4053- (013)000 | Martinez Landscape Co., Inc. | 12357 San Fernando Road | Sylmar Ca Ca |  | 2137922518 | 970 W 190Th Street, Suite 270 | Torrance, Ca 90502 | Gallardo, Samuel | 50417.05 | 0 | 0 | 0 | 2025-10-20 | Construct Rock Blanket And Remove/Install | Los Angeles County At Various Locations From 405/110 Separation Pm 12.9 To North Of 405/105 Separation Pm R21.5 | 98 | 89 | 2697451.59 | 2967990.7 | 3003990.7 | 47384 | 2025-11-03 | 2023-03-08 | 2023-02-07 |  |  | 401 | 0 | 410 | 0 |  | X
07 | 07-4V3204 | 4V3204 | 07-LA-405-22.2/23.5 | HA25 |  | Kormex Construction, Inc. | 2324 S. Vineyard Ave., Ste. K | Ontario Ca 91761 | 9192185700 | 5625725852 | 12975 W Culver Blvd | Los Angeles, Ca 90066 | Martinez, Elizabeth | 3960 | 0 | 0 | 0 | 2025-09-20 | Perform Plant Establishment And Install Ir | Los Angeles County In Inglewood From Century Boulevard Undercrossing To Florence Avenue Overcrossing | 0 | 0 | 835042.13 | 819812 | 884812 | 55688 | 2025-10-01 | 2024-04-24 | 2024-04-09 |  |  | 275 | 0 | 375 | 0 | X | X
07 | 07-4V4304 | 4V4304 | 07-LA-405-30.1/33 | HA25 |  | Kormax Construction, Inc. | 2324 S. Vineyard Ave., Ste. K | Ontario Ca 91761 |  | 5625725852 | 12975 W. Culver Blvd. | Los Angeles, Ca 90066 | Martinez, Elizabeth | 3000 | 0 | 0 | 0 | 2025-07-20 | Install Irrigation Systems And Perform Pla | The City And County Of Los Angeles From Olympic Boulevard Undercrossing To Sunset Boulevard Overcrossing | 0 | 0 | 660005.5 | 674590 | 667840 | 51465 | 2025-09-30 | 2023-07-25 | 2023-05-26 |  |  | 375 | 0 | 375 | 0 | X | X
07 | 07-347904 | 347904 | 07-LA-405-31.2/41.4 |  | ACIM-4053- (853)E | Rasmussen/Vanguard | 28548 Livingston Avenue | Valencia Ca 91335 |  | 2139526068 | 601 S Gleanoaks Blvd | Burbank Ca 91502 | Bautista, Denrick | 4256374.7 | 0 | 0 | 0 | 2025-10-20 | Cold Plane, Place Hma, Rhma, & Jpcp, Isr, | Los Angeles From Wilshire Boulevard Undercrossing To Victory Boulevard Undercrossing | 13 | 22 | 23064050.55 | 103932363 | 104422363 | 57415 | 2027-12-11 | 2025-03-27 | 2025-03-07 |  |  | 104 | 0 | 810 | 0 |  | X
07 | 07-2XG604 | 2XG604 | 07-LA-405-36.3/36.3 | 20.XX 201130 |  | Peterson-Chase Gen Engineeringconstruction Inc | 16351 Construction Circlewest | Irvine, Ca 92606-4414 |  | 5625725852 | 12975 W. Culver Blvd | Los Angeles, Ca 90066 | Martinez, Elizabeth | 0 | 0 | 0 | 0 | 2025-06-20 | Repair 2-Lane Onramp Damage | In La County City Of La On La-405 Repair S/B Skirball Center Dr 2-Lane Upheaved On-Ramp Pavement Due To Water Infiltration Dir'S E | 97 | 27 | 280452.25 | 6336 | 1025000 | 50324 | 2025-12-30 | 2023-05-31 | 2023-03-31 |  |  | 29 | 0 | 30 | 0
07 | 07-2XM804 | 2XM804 | 07-LA-405-36.3/37.1 | 20.XX 201130 |  | C A Rasmussen Inc | 28548 Livingston Ave | Valencia, Ca 91355 | 6613679040 | 8186130956 | 23369 Leonora Dr. | Woodland Hills, Ca 91367 | Gurfinkel, Vladimir | 0 | 0 | 0 | 0 | 2024-08-20 | Repair Sinkhole Damage | La County, City Of La @ N/B & S/B 405 Off-Ramp Skirball Ctr Drive& Sepulveda On-Ramprepair Sinkhole, Drainage,Slope Paving Dir'S E | 60 | 99 | 922850.33 | 3849 | 929300 | 55614 | 2025-12-31 | 2024-03-29 | 2024-02-13 |  |  | 36 | 0 | 60 | 0 |  | X
07 | 07-320204 | 320204 | 07-LA-405-40.1/48.1 | HA42 | ACIM-4053- (001)E | Martinez Landscape Co., Inc | 12357 San Fernando Road | Sylmar Ca 91342 | 8183649188 | 5625725983 | 9225 Cranford Ave. | Pacoima, Ca 91331 | Bui, Kevin | 0 | 31303.72 | 0 | 0 | 2025-10-20 | Storm Water Source Control | In Los Angeles County In Los Angeles From 0.2 Mile South Of Burbank Boulevard Overcrossing To 0.3 Mile North Of Rinaldi Street Un | 0 | 0 | 2536995.23 | 2828911 | 2903528 | 42189 | 2026-08-31 | 2022-03-10 | 2022-01-31 |  |  | 471 | 0 | 1000 | 0 | X | X
07 | 07-0W7004 | 0W7004 | 07-LA-405-44.7/486.4 |  |  | Interstate Civil Construction | 1253 Evergreen Road, Suite 2 | Wrightwood Ca 92397 |  | 8187460669 | 13171 Telfair Ave. | Sylmar, Ca 91342 | Mohsenzadeh, Ali | 370376.5 | 0 | 0 | 0 | 2025-07-20 | Individual Slab Replacement (Rsc), & Grind | Los Angeles County In Los Angeles From Nordhoff Street Undercrossing To Route 5/405 Separation | 69 | 95 | 5677399.21 | 5526410.9 | 5749560.9 | 56088 | 2025-08-20 | 2024-07-15 | 2024-06-19 |  |  | 137 | 0 | 200 | 0 |  | X
07 | 07-356604 | 356604 | 07-LA-605-10.2/20.2 | HA22 | ACIM-6052- (088)E | Myers & Sons Construction, Llc | 5777 W Century Blvd., Ste. 60 | Los Angeles, Ca 90045 | 9169381991 | 5623453125 | 13230 Firestone Blvd. | Santa Fe Springs, Ca 90670 | Arabe, Jerome | 4818604.55 | 113974.32 | 0 | 3080000 | 2025-10-20 | Lane & Slab Replacement, Cold Plane And Hm | Los Angeles County In Santa Fe Springs, Pico Rivera, Whittier, City Of Industry And El Monte From Telegraph Road Undercrossing To | 13 | 28 | 46403966.8 | 161382241 | 164527125.76 | 55727 | 2031-08-15 | 2024-04-30 | 2024-04-04 |  |  | 210 | 0 | 1670 | 0 |  | X
07 | 07-3255U4 | 3255U4 | 07-LA-605-20.2/26 | HA22 | ACIM-6052- (007)E | Peterson-Chase General Engineering Construction, Inc. | 16351 Construction Circle Wes | Irvine Ca 92606 | 9492520441 | 213798535 | 4281 Katella Ave Ste 221 | Los Alamitos,Ca 90720 | Lee, Peter | 978830.11 | 13593.92 | 0 | 0 | 2025-10-20 | Individual Slab Replacement, Cold Plane Ac | Los Angeles County In Baldwin Park And Irwindale From Route 10/605 Separation To 0.2 Mile North Of Route 210/605 Separation | 65 | 85 | 15628754.71 | 16259458.5 | 17813015.38 | 49304 | 2026-11-02 | 2023-05-12 | 2023-04-12 |  |  | 488 | 0 | 750 | 0 |  | X
07 | 07-345104 | 345104 | 07-LA-710-5.0/9.5 |  | ACIM-7101- (844)E | Alfaro Communications Construction, Inc. | 15614 S. Atlantic Avenue | Compton Ca 90221 | 3106698949 | 5623453144 | 13230 Firestone Blvd., Ste. E2 | Santa Fe Springs, Ca 90670 | Wang, Paul | 813085.92 | 32955.93 | 0 | 0 | 2025-10-20 | Modifying Fiber Optic Cable Systems. | Los Angeles County In And Near Long Beach From 1 Mile South Of Pico Avenue On-Ramp Overhead To 0.1 Mile North Of Route 405/710 Sep | 40 | 79 | 9095384.83 | 11007496.62 | 11496024.57 | 56199 | 2026-09-08 | 2024-08-06 | 2024-07-11 |  |  | 230 | 0 | 575 | 0 |  | X
07 | 07-349904 | 349904 | 07-LA-710-6.0/14.1 |  | ACIM-7101- (845)E | Westcoast Public Works, Inc. | 20058 Ventura Blvd, #318 | Woodland Hills Ca 91364 | 8189684444 | 2138193025 | 18000 Studebaker Rd. Ste. 360 | Cerritos, Ca 90703 | Townsend, Jeffrey | 436422.4 | 141075.86 | 0 | 26373.8 | 2025-10-20 | Construct Mvps, Mgs, Rock Blankets,And Pav | Los Angeles County In Long Beach And Comptom From Shoreline Drive To 0.2 Mile North Of Alondra Boulevard Overcrossing | 32 | 57 | 3321169.64 | 5377816.92 | 5579397.3 | 56686 | 2027-06-21 | 2024-11-22 | 2024-09-12 |  |  | 189 | 0 | 600 | 0 |  | X
07 | 07-4V4204 | 4V4204 | 07-LA-710-6.2/7.2 | HA25 |  | Accu Construction, Inc. | 14751 Plaza Drive Suite L | Tustin Ca 92780 | 7146414730 | 5623459894 | 13230 Firestone Blvd. | Santa Fe Springs, Ca 90670 | Martinez, Francisco | 4855.4 | 0 | 0 | 0 | 2025-10-20 | Planting Restoration. | Los Angeles County In Long Beach From Shoemaker Bridge To 0.3 Mile North Of Route 1/710 Separation | 79 | 83 | 815939.11 | 695920 | 980699.84 | 50886 | 2027-05-03 | 2023-07-05 | 2023-06-19 |  |  | 142 | 0 | 930 | 0 |  | X
07 | 07-347004 | 347004 | 07-LA-710-9.6/T32.1 | HA22 |  | Doja Inc | 5050 Mission Blvd | Ontario Ca 92761 | 9096281999 | 8054314352 | 13230 South Firestone Blvd #A | Santa Fe Springs, Ca 90670 | Robillos, Ramon | 284032.8 | 0 | 0 | 0 | 2025-06-20 | Drainage System Restoration. | Los Angeles County In Long Beach And Pasadena At Various Locations | 53 | 39 | 2091510.68 | 5300000 | 5314900 | 54024 | 2026-05-29 | 2023-11-01 | 2023-09-28 |  |  | 96 | 0 | 180 | 0 |  | X
07 | 07-385804 | 385804 | 07-LA-710-13.8/15.3 |  |  | West Coast Public Works, Inc. | 20058 Ventura Blvd, #318 | Woodland Hills Ca 91364 |  | 3103455704 | 13230 South Firestone Blvd A | Santa Fe Springs, Ca 90670 | Nguyen, Khanh-Van | 0 | 0 | 0 | 0 | 2025-09-20 | Place Planting And Install Irrigation Syst | Los Angeles County In Compton And Paramount From 0.2 Mile South Of Alondra Boulevard Overcrossing To 0.4 Mile North Of Rosecrans A | 0 | 0 | 2876178.54 | 2987753 | 3008753 | 52905 | 2027-07-19 | 2023-09-28 | 2023-07-14 |  |  | 190 | 0 | 930 | 0 | X | X
07 | 07-390804 | 390804 | 07-LA-710-19.6/19.9 |  |  | Calpromax Engineering, Inc. | 650 N. Rose Dr. #186 | Placentia Ca 92870 |  |  |  |  | Oregel, Martin | 0 | 0 | 0 | 0 |  | Construct Ada Curb Ramps And Install Flash | Los Angeles County In City Of Bell From 0.1 Mile South Of Florence Avenue Overcrossing To 0.2 Mile North Of Florenceavenue Overcro | 0 | 0 | 0 | 1520057.9 | 1585057.9 | 59297 | 2026-04-01 | 2025-07-08 | 2025-06-06 |  |  | 0 | 0 | 150 | 0
07 | 07-354704 | 354704 | 07-LA-710-22.0/0 |  | BFIM-7101- (846)E | Certified Coatings Company | 2320 Cordelia Rd | Fairfield Ca 94534 |  | 2134076627 | 4281 Katella Ave. #221 | Los Alamitos, Ca 90720 | Oregel, Martin | 570171.52 | 10282.33 | 0 | 206600 | 2025-10-20 | Clean And Paint Bridge. | Los Angeles County In Commerce And Vernon At Hobart Yard Overhead And At Atlantic Boulevard And Bandini Boulevard On-Ramp | 22 | 27 | 3371966.24 | 10336185 | 12696185 | 57299 | 2027-07-02 | 2025-03-06 | 2025-02-06 |  |  | 118 | 0 | 540 | 0 |  | X
07 | 07-331804 | 331804 | 07-LA-710-26.0/26.7 | HA42 | ACIM-X037- (229)E | Griffith Company | 3050 East Birch Street | Brea, Ca 92821 | 7149840228 | 5625725031 | 4281 Katella Ave Ste 221 | Los Alamitos, Ca 90720 | Vergara, Joahnna | 6360 | 0 | 0 | 0 | 2025-10-20 | Install Irrigation Systems, Erosion | In Los Angeles County In And Near Monterey Park On Rte 10 From 0.1 Mile East Of North Eastern Ave To 0.2 Mile West Of South Garvey | 67 | 97 | 2529793.13 | 2646751.18 | 2743385.53 | 45566 | 2026-08-18 | 2022-11-18 | 2022-09-26 |  |  | 669 | 0 | 1000 | 0 |  | X
07 | 07-2XT404 | 2XT404 | 07-LA-710-194.0/19.4 | 20.XX 201130 |  | Beador Construction Company | 2900 Bristol St Suite D204 | Costa Mesa, Ca 92626 |  | 2133100860 | 970 W. 190Th Street Suite 270 | Torrance, Ca 90502 | Shahriari, Shahnam | 0 | 0 | 0 | 0 | 2025-10-20 | Repair Damaged Girders N/B La-710 | In La County, City Of Bell On N/B La-710 @Clara Street Oc, Br.No.53-0833 To Repair/ Reconstruct Damaged Girders Dir'S Emergency Fo | 68 | 92 | 946113.76 | 8879 | 1027400 | 58735 | 2025-11-17 | 2025-06-12 | 2025-04-18 |  |  | 41 | 0 | 60 | 0 |  | X
07 | 07-354804 | 354804 | 07-LA-5808-/2.5 | HA12 |  | Mercer Fraser Company | 28548 Livingston Ave | Valencia, Ca 91355 | 6613679040 | 8184829191 | 12975 W Culver Blvd. | Los Angeles, Ca 90066 | Sheik, Hakim | 123184.95 | 0 | 0 | 0 | 2025-10-20 | Building Work. | Los Angeles County In Culver City At The Culver City Maintenance Station At 5650 Selmaraine Drive | 100 | 32 | 2929669.93 | 8895895 | 9195895 | 55803 | 2026-04-12 | 2024-05-13 | 2024-04-03 |  |  | 277 | 0 | 210 | 0
07 | 07-358204 | 358204 | 07-LA-5823-/7.2 | HA12 |  | Mercer Fraser Company | 200 Dinsmore Dr | Fortuna Ca 95540 | 7074436371 | 2138193025 | 18000 Studebaker Rd. Suite 360 | Cerritos, Ca 90703 | Townsend, Jeffrey | 180125 | 0 | 0 | 0 | 2025-10-20 | Provide Building Work At A Maintenance Sta | Los Angeles County In Long Beach At The Pacific Place Maintenance Station At North3725 Pacific Place | 100 | 64 | 3254375 | 4965380 | 5197143.41 | 55790 | 2026-01-05 | 2024-05-13 | 2024-03-29 |  |  | 277 | 0 | 260 | 0
07 | 07-322704 | 322704 | 07-VAR-1-1.3/26.6 | HA42 | ACNH-X111- (080)E | Autobahn Construction Inc. | 933 N. Batavia St. | Orange Ca 92867 |  | 2133306650 | 1525 Rancho Conejo Blvd #102 | Thousand Oaks, Ca 91320 | Singh, Ranjit | 51920 | 0 | 0 | 0 | 2025-10-20 | Construct Pervious Concrete Pavement And D | Ventura County At Various Locations | 76 | 86 | 4608956.57 | 5179766 | 5281728.5 | 47264 | 2026-06-30 | 2023-03-03 | 2023-01-31 |  |  | 461 | 0 | 610 | 0 |  | X
07 | 07-0W8804 | 0W8804 | 07-VAR-1-23.1/23.1 | HM4 |  | Bc Rentals Llc Dba Bc Traffic Specialist | 13261 Garden Grove Blvd | Garden Grove Ca 92843 | 9519075163 | 3106090364 | 1201 Baldwin Park Blvd. | Baldwin Park, Ca 91706 | Herrera, Edgar | 1400 | 0 | 0 | 0 | 2025-06-20 | Upgrade Existing Basic Crosswalks To Ladde | Los Angeles County At Various Locations | 60 | 98 | 681968.18 | 489485 | 685411.18 | 55791 | 2025-11-14 | 2024-05-13 | 2024-04-15 |  |  | 54 | 0 | 90 | 0 |  | X
07 | 07-348804 | 348804 | 07-VAR-2-18.7/18.7 | HB4N | ACNH-000C- (555)E | Alfaro Communications Construction, Inc. | 15614 S. Atlantic Avenue | Compton Ca 90221 | 3106698949 | 2137937340 | 13171 Telfair Ave.#101 | Sylmar, Ca 91342 | Hossain, Muhammad | 660854.96 | 1875.48 | 0 | 0 | 2025-10-20 | Cameras Systems. | Los Angeles County And Ventura County At Various Locations | 48 | 82 | 4334019.97 | 5048024.52 | 5271024.52 | 55551 | 2026-11-04 | 2024-03-27 | 2024-02-28 |  |  | 240 | 0 | 500 | 0 |  | X
07 | 07-0W6104 | 0W6104 | 07-VAR-5-/40 | HM4 |  | Traffic Loops Crackfilling, Inc. | 946 S. Emerald Street | Anaheim Ca 92804 | 7145204026 | 2137937193 | 1041 W Badillo, Ste 112 | Covina, Ca 91722 | Pham,Ryan | 0 | 0 | 0 | 0 | 2024-11-20 | Repair Traffic Monitoring Detection Statio | Los Angeles County At Various Locations | 80 | 22 | 257255 | 1176020 | 1176020 | 53184 | 2025-11-20 | 2023-10-12 | 2023-05-31 |  |  | 88 | 0 | 110 | 0
07 | 07-346204 | 346204 | 07-VAR-23-3.6/11.4 | HA22 | ACNH-000C- (556)E | Select Electric, Inc. | 2790 Business Park Drive | Vista Ca 92081 | 5629390418 | 2137008447 | 1525 Rancho Conejo Blvd. | Thousand Oaks, Ca 91320 | Tehrani, Joseph Solaiman | 138199.89 | 0 | 0 | 0 | 2025-10-20 | Upgrade And Install New Transportation Man | Los Angeles And Ventura Counties At Various Locations | 94 | 62 | 6917648.33 | 10106415 | 11081614.96 | 56008 | 2025-11-30 | 2024-06-20 | 2024-04-10 |  |  | 282 | 0 | 300 | 0
07 | 07-338604 | 338604 | 07-VAR-91-6.1/20.7 | HB4N | ACNH-X037- (231)E | Alfaro Communications Construction, Inc. | 15614 S. Atlantic Avenue | Compton Ca 90221 | 3106698949 | 5623453145 | 13230 Firestone Blvd., Ste.E-2 | Santa Fe Springs, Ca 90670 | Alonzo, Bernard | 1034647.79 | 0 | 0 | 0 | 2025-10-20 | Modifying Ramp Metering, Fiber Optic Cable | Los Angeles County At Various Locations | 50 | 93 | 12526366.23 | 12972892.52 | 13471541 | 55464 | 2026-06-22 | 2024-03-04 | 2024-01-22 |  |  | 316 | 0 | 630 | 0 |  | X
07 | 07-355104 | 355104 | 07-VAR-105-2.1/2.1 | HA22 | ACIM-X037- (233)E | Aldridge Electric, Inc. | 1000 E Santa Ana Blvd Ste 300 | Santa Ana, Ca 92701 | 8472573670 | 8182547484 | 13230 Firestone Blvd Suite | Santa Fe Springs, Ca 90670 | Karout, Ali | 1439071.2 | 52030.08 | 0 | 0 | 2025-10-20 | Upgrade Tunnel Lighting Systems And Instal | Los Angeles County At Various Locations | 49 | 92 | 18142568.16 | 19249130.5 | 19731022.16 | 55704 | 2026-07-29 | 2024-04-29 | 2024-03-07 |  |  | 188 | 0 | 380 | 0 |  | X
07 | 07-0W5904 | 0W5904 | 07-VAR-110-15.1/23 | HM4 |  | Bc Rentals Llc Dba Bc Traffic Specialist | 13261 Garden Grove Blvd | Garden Grove Ca 92843 |  | 8186130956 | 23369 Leonora Dr | Woodland Hills, Ca 91367 | Gurfinkel, Vladimir | -14208.2 | 0 | 0 | 0 | 2025-10-20 | Install Traffic Stripe, Pavement Marking, | Los Angeles And Ventura Counties At Various Locations | 100 | 93 | 883580.98 | 952176 | 1028549.33 | 52084 | 2025-12-31 | 2023-08-18 | 2023-05-25 |  |  | 81 | 0 | 60 | 0 |  | X
07 | 07-349504 | 349504 | 07-VAR-170-14.5/20.5 | HB4N | ACNH-P170- (008)E | Alfaro Communications Construction, Inc. | 15614 S. Atlantic Avenue | Compton Ca 90221 |  | 5625725983 | 9225 Cranford Ave | Pacoima Ca 91331 | Bui, Kevin | 127429.25 | 11861.16 | 0 | 0 | 2025-10-20 | Install New Transportation Management Syst | Los Angeles County In Los Angeles From Route 134/170 Separation To Route 170/5 Separation | 49 | 85 | 8608171.47 | 9214672.88 | 10047587.58 | 55553 | 2026-08-21 | 2024-03-27 | 2024-02-29 |  |  | 254 | 0 | 522 | 0 |  | X
07 | 07-349104 | 349104 | 07-VAR-210-43.9/46.7 | HB4N |  | International Line Builders, Inc. | 3955 Temescal Canyon Road | Corona Ca 92883 |  | 2137937193 | 1041 W. Badillo St. Ste 112 | Covina, Ca 91722 | Pham, Ryan | 422106.25 | 0 | 0 | 9500 | 2025-10-20 | Upgrade The Existing Communication System. | Los Angeles County At Various Locations | 73 | 62 | 2187331.5 | 3538423 | 3538423 | 55552 | 2026-01-30 | 2024-03-27 | 2024-02-21 |  |  | 182 | 0 | 250 | 0 |  | X
07 | 07-350334 | 350334 | 07-VAR--/0 |  | ACNH-X037- (238)E | Crosstown Electrical & Data, Inc. | 5454 Diaz Street | Irwindale Ca 91706 | 6267036532 | 5625725031 | 1370 Valley Vista Dr Ste 150C | Diamond Bar, Ca 91765 | Ferrer, Jose | 40075 | 0 | 0 | 0 | 2025-10-20 | Install Changeable Message Signs, And Traf | Los Angeles County At Various Locations | 5 | 0 | 40075 | 16365395 | 16365395 | 58135 | 2027-09-15 | 2025-05-13 | 2025-03-17 |  |  | 26 | 0 | 500 | 0 |  | X
07 | 07-350404 | 350404 | 07-VAR--/0 |  |  | Alfaro Communications Construction, Inc. | 15614 S. Atlantic Avenue | Compton Ca 90221 |  | 5623453144 |  |  | Wang, Paul | 512261.46 | 0 | 0 | 13000 | 2025-10-20 | Modifying Fiber Optic Cable Systems. | Los Angeles County At Various Locations | 21 | 52 | 2302802.61 | 3769131.07 | 4439470.34 | 57298 | 2026-12-08 | 2025-03-06 | 2025-01-23 |  |  | 109 | 0 | 525 | 0 |  | X
07 | 07-0W6604 | 0W6604 | 07-VAR--/0 |  |  | Velarde Concrete Construction | 523 S. Brand Blvd., Ste. #201 | San Fernando Ca 91340 |  |  |  |  | Vergara, Joahnna | 675145.98 | 0 | 0 | 39772.48 | 2025-10-20 | Methacrylate, Polyester Overlay And Joint | Los Angeles County At Various Locations | 56 | 59 | 5671061.79 | 9475294.9 | 9580948.7 | 56078 | 2026-04-24 | 2024-07-15 | 2024-06-26 |  |  | 152 | 0 | 270 | 0 |  | X
07 | 07-504444 | 504444 | 07-VAR--/0 |  |  | Hp Communications, Inc. | 13341 Temescal Canyon Rd | Corona Ca 92883 |  | 8186130956 | 23369 Leonora Dr | Woodland Hills, Ca 91367 | Gurfinkel, Vladimir | 92584.73 | 0 | 0 | 0 | 2025-07-20 | Mmbn Project On Routes 101 And 405 | On Route 405 From Wilshire Boulevard To Route 101/ 405 Separation And On Route 101 From Route 101/ 405 Separation To Balboa Boulev | 98 | 99 | 15671580.63 | 10913901.19 | 15570140.62 | 56206 | 2025-07-21 | 2024-07-09 | 2024-07-05 | 2025-09-23 |  | 164 | 0 | 100 | 67 |  | X
07 | 07-0W8704 | 0W8704 | 07-VAR--/0 |  |  | Sterndahl Enterprises Llc | 11861 Branford Street | Sun Valley Ca 91352 | 8188348199 | 3106090364 | 1201 Baldwin Park Blvd | Baldwin Park Ca 91706 | Herrera, Edgar | 17700 | 0 | 0 | 0 | 2025-10-20 | Install Traffic Stripe, Pavement Marking, | Los Angeles County At Various Locations | 99 | 96 | 1627950.13 | 1963665 | 1578912.25 | 56077 | 2025-11-14 | 2024-07-15 | 2024-06-27 |  |  | 79 | 0 | 80 | 0 |  | X
07 | 07-351124 | 351124 | 07-VAR--/0 |  |  | Select Electric, Inc. | 1700 E. Via Burton | Anaheim Ca 92806 |  | 2133082033 |  |  | Pham, Ryan | 172847.25 | 0 | 0 | 0 | 2025-10-20 | Install And Replace Cctv Camera Systems. | Los Angeles County At Various Locations | 17 | 16 | 832746.6 | 4998035 | 5060357.2 | 57195 | 2026-08-21 | 2025-02-18 | 2024-12-24 |  |  | 91 | 0 | 550 | 0 |  | X
07 | 07-0W7604 | 0W7604 | 07-VAR--/0 |  |  | Jabre Contracting Inc. | 1813 Manzanita Lane | Manhattan Beach Ca 90266 | 3107202277 | 2135050610 | 25061 W Avenue Stanford Ste 70 | Valencia Ca 91350 | Salman, Ridwan | 0 | 0 | 0 | 0 | 2025-09-23 | Clean And Line Culverts. | Los Angeles County At Various Locations | 100 | 100 | 505372.78 | 317250 | 538000 | 56117 | 2025-09-23 | 2024-07-17 | 2024-06-25 | 2025-09-25 |  | 66 | 0 | 80 | 0 |  | X
07 | 07-0Y2004 | 0Y2004 | 07-VAR--/0 |  |  | Autobahn Construction, Inc. | 933 N. Batavia St. | Orange Ca 92867 | 7147697025 | 3103456188 | 970 W 190Th Ste 270 | Torrance, Ca 90502 | Gallardo, Samuel | 16850 | 0 | 0 | 0 | 2025-10-20 | Wrong Way Driver Preventive Counter Measur | Los Angeles County At Various Locations | 67 | 13 | 61875 | 494126 | 494126 | 59516 | 2025-11-25 | 2025-07-23 | 2025-06-24 |  |  | 50 | 0 | 75 | 0 |  | X
07 | 07-350704 | 350704 | 07-VAR--/0 |  |  | Parsons Transportation Group, Inc. | 19900 Macarthur Blvd., Suite | Irvine Ca 92612 |  | 5623453142 | 13230 Firestone Blvd | Santa Fe Springs, Ca 90670 | Karout, Ali | 0 | 0 | 0 | 0 |  | New Active Traffic Management (Atm) & Traf | Los Angeles County At Various Routes And Various Locations | 0 | 0 | 0 | 32200000 | 32200000 | 60127 | 2027-06-28 | 2025-06-26 | 2025-06-25 |  |  | 0 | 0 | 515 | 0
07 | 07-301604 | 301604 | 07-VAR--/0 |  | BFNH-X037- (236)E | Powell Constructors Inc | 8555 Banana Avenue | Fontana Ca 92335 | 9093568880 | 5623459865 | 13320 S Firestone Blvd, Ste A | Santa Fe Springs, Ca 90670 | Robillos, Ramon | 1170740 | 0 | 0 | 264302 | 2025-10-20 | Install Fiber Reinforced Polymer System (C | Los Angeles County At Various Locations | 49 | 28 | 3946106.09 | 13964693 | 14223914.83 | 56272 | 2026-09-30 | 2024-08-23 | 2024-07-31 |  |  | 196 | 0 | 400 | 0 |  | X
07 | 07-353804 | 353804 | 07-VAR--/0 |  | ACIM-0053- (110)E | Crosstown Electrical & Data, Inc. | 5454 Diaz Street | Irwindale Ca 91706 |  | 8183642760 | 13171 Telfair Ave,Ste101 | Sylmar Ca 91342 | Chavez, Efraim | 1363736.95 | 0 | 0 | 0 | 2025-10-20 | Modify Fiber Optic Cable Systems, Lighting | Los Angeles County At Various Locations | 42 | 50 | 8742741.52 | 17468150.6 | 17618150.6 | 56575 | 2026-06-26 | 2024-10-16 | 2024-09-10 |  |  | 127 | 0 | 300 | 0 |  | X
07 | 07-0W8904 | 0W8904 | 07-VAR--/0 |  |  | Polo Engineering, Inc. | 30758 Sloan Canyon Rd | Castaic Ca 91384 |  | 6263391601 | 1041 W Badillo St #112 | Covina, Ca 91722 | Punjabi, Raj | 0 | 0 | 0 | 0 |  | Install Advance Curve Warning Signs | Los Angeles County At Various Locations | 0 | 0 | 0 | 1450412.78 | 1450412.78 | 59975 |  | 2025-07-23 | 2025-04-11 |  |  | 0 | 0 | 145 | 0
07 | 07-350324 | 350324 | 07-VAR--/0 |  | ACNH-X037- (239)E | Jfl Electric, Inc. | 8257 Compton Avenue | Los Angeles Ca 90001 | 3235814400 | 5622545045 | 13230 Firestone Blvd Unit E2 | Santa Fe Springs Ca 90670 | Turay, Sulaiman | 0 | 0 | 0 | 0 |  | Replace Exsistiing Cms, Tcs, And Tmds/Vds, | Los Angeles County At Various Locations | 0 | 0 | 0 | 23414925 | 23414925 | 57778 | 2027-10-25 | 2025-04-15 | 2025-03-10 |  | S | 0 | 0 | 500 | 0
07 | 07-351704 | 351704 | 07-VAR--/0 |  | ACNH-X111- (081)E | C. A. Rasmussen, Inc. | 28548 Livingston Avenue | Valencia Ca 91355 | 6613679040 | 2137008447 | 1525 Rancho Conejo Blvd #102 | Thousand Oaks, Ca 91320 | Tehrani, Joseph Solaiman | 571903.67 | 0 | 0 | 675000 | 2025-10-20 | Cold Plane Ac Pavement And Place Rubberize | Ventura County In Moorpark At Various Locations | 16 | 12 | 1764767.53 | 15225552 | 15225552 | 57855 | 2027-03-29 | 2025-04-24 | 2025-03-25 |  |  | 72 | 0 | 440 | 0 |  | X
07 | 07-0W9904 | 0W9904 | 07-VAR--/0 |  |  | Peterson-Chase General Engineering Construction, Inc. | 16351 Construction Circle Wes | Irvine Ca 92606 |  |  | 4281 Katella Ave Suite 221 | Los Alamitos Ca 90720 | Vergara Joahnna | 1120804.76 | 0 | 0 | 4000 | 2025-10-20 | Methacrylate, Polyester Overlay, Joint Sea | Los Angeles County At Various Locations | 22 | 70 | 1698499.96 | 2382274.8 | 2382274.8 | 59575 | 2026-06-11 | 2025-07-29 | 2025-06-16 |  |  | 40 | 0 | 180 | 0 |  | X
07 | 07-0Y1904 | 0Y1904 | 07-VAR--/0 |  |  | Specialized Pavement Marking, Llc | 11095 Sw Industrial Way Ste A | Tualatin Or 97062 | 5308850420 | 5625725983 | 9225 Cranford Ave | Pacoima, Ca 91331 | Bui, Kevin | 0 | 0 | 0 | 0 |  | Striping. | Los Angeles County At Various Locations | 0 | 0 | 0 | 1330792.5 | 1330792.5 | 59317 | 2026-02-09 | 2025-07-08 | 2025-06-24 |  |  | 0 | 0 | 120 | 0
07 | 07-0Y0504 | 0Y0504 | 07-VAR--/0 |  |  | Baker Electric & Renewables, Llc | 1298 Pacific Oaks Place | Escondido Ca 92029 | 7607452001 | 8058577070 | 1525 Rancho Conejo Blvd Ste102 | Thousand Oaks, Ca 91320 | Ira, Alfred | 0 | 0 | 0 | 0 |  | Modify Traffic Signal, Roadside Signs And | Ventura County At Various Locations | 0 | 0 | 0 | 610318.66 | 610318.66 | 59675 | 2025-12-14 | 2025-08-13 | 2025-06-06 |  |  | 0 | 0 | 70 | 0
07 | 07-0Y1004 | 0Y1004 | 07-VAR--/0 |  |  | Jabre Contracting, Inc. | 1813 Manzanita Lane | Manhattan Beach Ca 90266 |  |  |  |  | Tehrani, J. | 206400 | 0 | 0 | 67500 | 2025-10-20 | Cured-In-Place Pipeliner. | Ventura County At Various Locations | 33 | 23 | 273900 | 1173550 | 1205050 | 59276 | 2026-07-29 | 2025-07-01 | 2025-05-27 |  |  | 20 | 0 | 60 | 0 |  | X
07 | 07-351504 | 351504 | 07-VAR--/0 |  |  | Powell Constructors, Inc. | 8555 Banana Avenue | Fontana Ca 92335 |  | 2139526068 | 601 S Glenoaks Blvd #310 | Burbank, Ca 91502 | Bautista, Denrick | 8000 | 0 | 0 | 0 | 2025-10-20 | Construct Bridge Rails, Guardrail, Oh Sign | Los Angeles County In Los Angeles At Various Locations | 9 | 0 | 8000 | 7355032.35 | 7455032.35 | 57775 | 2026-12-31 | 2025-04-18 | 2025-03-26 |  |  | 21 | 0 | 240 | 0 |  | X
07 | 07-0W7704 | 0W7704 | 07-VAR--/0 |  |  | Lamassu Utility Services, Inc. | 3193 Enterprise Court | Loomis Ca 95650 | 9162591576 | 2137008447 | 1525 Rancho Conejo Blvd Ste102 | Thousand Oaks Ca 91302 | Tehrani, Joseph Solaiman | 0 | 0 | 0 | 0 | 2025-10-20 | Culvert Lining. | Ventura County At Various Locations | 100 | 76 | 468195.83 | 383032.72 | 610532.72 | 56074 | 2025-11-20 | 2024-07-12 | 2024-06-14 |  |  | 73 | 0 | 70 | 0
07 | 07-0Y0904 | 0Y0904 | 07-VAR--/0 |  |  | Jabre Contracting, Inc. | 1813 Manzanita Lane | Manhattan Beach Ca 90266 |  | 8187460669 | 13171 Telfair Ave Ste 101 | Sylmar Ca 91342 | Mohsenzadeh Ali | 20060 | 0 | 0 | 0 | 2025-09-20 | Cleaning, Repair And Retrofit Of Culverts. | Los Angeles County At Various Locations | 38 | 20 | 174410 | 866260 | 891260 | 59197 | 2026-01-30 | 2025-06-25 | 2025-05-30 |  | S | 30 | 0 | 80 | 0 |  | X
07 | 07-0W9804 | 0W9804 | 07-VAR--/0 |  |  | Myers & Sons Construction, Llc | 45 Morrison Ave | Sacramento Ca 95838 | 91683950 | 2137008447 | 1525 Rancho Conejo Blvd Ste102 | Thousand Oaks, Ca 91302 | Tehrani, Joseph Solaiman | 796018.09 | 0 | 0 | 487500 | 2025-10-20 | Treat Bridge Deck, Repair Joint Seals, And | Ventura County At Various Locations | 16 | 20 | 1377828.09 | 6828826 | 6943826 | 59215 | 2026-07-29 | 2025-06-26 | 2025-06-10 |  |  | 36 | 0 | 230 | 0 |  | X
07 | 07-0W6504 | 0W6504 | 07-VAR--/0 |  |  | Peterson-Chase General Engineering Construction, Inc. | 16351 Construction Circle Wes | Irvine Ca 92606 | 9492520441 | 5625725852 | 12975 Culver Blvd | Los Angeles, Ca 90066 | Martinez, Elizabeth | 488198 | 0 | 0 | 0 | 2025-10-20 | Structural Conc, Approach Slab, Polyester | Los Angeles County At Various Locations | 79 | 90 | 3378753.52 | 3581539.6 | 3651539.6 | 56132 | 2025-12-26 | 2024-07-24 | 2024-06-27 |  |  | 143 | 0 | 180 | 0 |  | X
07 | 07-351114 | 351114 | 07-VAR--/0 |  |  | Calpromax Engineering, Inc. | 650 N. Rose Dr. #186 | Placentia Ca 92870 | 7145734599 | 5623453145 | 13230 Firestone Blvd. Ste E-2 | Sante Fe Springs, Ca 90670 | Alonzo, Bernard | 298920 | 0 | 0 | 0 | 2025-10-20 | Install And Upgrade Camera Systems. | Los Angeles County At Various Locations | 18 | 14 | 796320 | 5358200 | 5519224.66 | 56585 | 2026-10-05 | 2024-10-29 | 2024-10-04 |  |  | 55 | 0 | 300 | 0 |  | X
07 | 07-350314 | 350314 | 07-VAR--/0 |  | ACNH-000C- (563)E | Crosstown Electrical & Data, Inc. | 5454 Diaz Street | Irwindale Ca 91706 |  |  | 13171 Telfair Ave | Sylmar, Ca 91342 | Hossain, Muhammad Ismail | 118133.75 | 0 | 0 | 500000 | 2025-10-20 | Install Changeable Message Signs, And Fibe | Los Angeles And Ventura Counties At Various Locations | 6 | 3 | 618133.75 | 20349394 | 20379394 | 57755 | 2027-08-17 | 2025-04-15 | 2025-03-20 |  |  | 47 | 0 | 750 | 0 |  | X
07 | 07-0W9704 | 0W9704 | 07-VAR--/0 |  |  | J. Francis Company | 16197 Krameria Ave. | Riverside Ca 92504 | 9517769100 | 9512323742 | 1041 W Badillo St Ste 112 | Covina, Ca 91722 | Hong, Hai | 779906.2 | 0 | 0 | 97000 | 2025-10-20 | Methacrylate, Polyester Overlay, Joint Sea | Los Angeles County At Various Locations | 37 | 31 | 1937899.14 | 6197847.1 | 6197847.1 | 59055 | 2026-04-17 | 2025-06-19 | 2025-06-02 |  |  | 70 | 0 | 190 | 0 |  | X
07 | 07-4P8504 | 4P8504 | 07-VEN-1-1.0/1.3 |  | SNHG-P001- (703)E | Polo Engineering, Inc. | 30758 Sloan Canyon Rd | Castaic Ca 91384 |  | 2133306650 | 1525 Rancho Conejo Blvd, #102 | Thousand Oaks, Ca 91320 | Singh, Ranjit | 0 | 0 | 0 | 0 |  | Install Marked Crosswalk With Pedestrian H | Ventura County From 0.1 Mile South Of Yerba Buena Road To 0.1 Mile North Of Little Sycamore Creek Bridge | 0 | 0 | 0 | 704550.5 | 719550.5 | 56867 | 2026-05-31 | 2024-12-17 | 2024-11-20 |  |  | 0 | 0 | 90 | 0
07 | 07-318204 | 318204 | 07-VEN-1-4.0/4.2 | HA23 |  | Flatiron-Drill Tech A Joint Venture | 16470 West Bernardo Dr #120 | San Diego Ca 92127 | 9095978413 | 2137928141 | 1525 Rancho Conejo Blvd., #102 | Thousand Oks, Ca 91320 | Verma, Niketa | 0 | 92021.87 | 0 | 0 | 2025-10-20 | Construct Secant Walls, Slope | In Ventura County, South Of Point Mugu State Park And Sycamore Canyon Road | 100 | 99 | 53542502.14 | 42505506.3 | 53338043.44 | 41904 | 2025-10-31 | 2021-09-17 | 2021-09-15 |  |  | 635 | 0 | 550 | 86 |  | X
07 | 07-323904 | 323904 | 07-VEN-1-21.3/28.4 | HA22 |  | C. A. Rasmussen, Inc. | 28548 Livingston Avenue | Valencia Ca 91355 |  | 8058577070 | 1525 Rancho Conejo Blvd, 102 | Thousand Oaks, Ca 91320 | Ira, Alfred | 32640 | 0 | 0 | 0 | 2025-10-20 | Cold Plane Ac, Place Rubberized Hot Mix As | Ventura County Near Ventura From Route 1/101 Separation To Mobil Pier Road. | 100 | 79 | 6287619.66 | 7435330.4 | 7917421.18 | 48384 | 2025-11-16 | 2023-04-10 | 2023-03-27 |  |  | 580 | 0 | 580 | 0
07 | 07-319604 | 319604 | 07-VEN-1-21.3/21.9 |  | BFNH-X111- (082)000 | Beador Construction Company, Inc. | 2900 Bristol Street, Suite D2 | Costa Mesa Ca 92626 |  | 2133306650 | 1525 Rancho Conejo Blvd#102 | Thousand Oaks, Ca 91320 | Ranjit Singh | 0 | 0 | 0 | 0 |  | Remove And Construct Bridge. | The City And County Of Ventura On Route 1 From 1.8 Miles North Of Route 1/33 Separation To 2.0 Miles South Of A Lease Canyon Road | 0 | 0 | 0 | 46620300 | 46620300 | 60123 | 2031-02-28 | 2025-10-13 | 2025-09-16 |  |  | 0 | 0 | 1300 | 0
07 | 07-2XE704 | 2XE704 | 07-VEN-23-17.7/24.1 | 20.20 201130 |  | Burns Pacific Construction Inc | 3541 Old Conejo Rd Ste 114 | Newbury Park, Ca 91320 |  | 2135077938 | 1525 Rancho Conejo Blvd Suite 102 | Thousand Oaks, Ca 91320 | Ira, Alfred | 0 | 0 | 0 | 0 | 2024-02-06 | Repair Storm Damage | In Ventura County, City Of Fillmore Ven-23To Remove Mud/Debris,Fallen Trees,Drainagesystems & Repair Roadway Damage From Stormdir' | 100 | 99 | 2214052.27 | 9675 | 3224052.27 | 47986 | 2025-10-31 | 2023-03-24 | 2023-01-25 |  |  | 273 | 0 | 60 | 0 |  | X
07 | 07-348404 | 348404 | 07-VEN-23-/3.3 |  | ACST-P023- (042)E | Accu Construction, Inc. | 14751 Plaza Drive Suite L | Tustin Ca 92780 | 7146414730 | 2137008447 | 1525 Rancho Conejo Blvd #102 | Thousand Oaks, Ca 91302 | Tehrani, Joseph Solaiman | 102895 | 0 | 0 | 0 | 2025-10-20 | Construct Design Pollution Prevention Infi | Ventura County In And Near Thousand Oaks And Moorpark At Various Locations From 0.1Mile North Of Sycamore Canyon Drive To Potrero | 94 | 90 | 1374548 | 1816005 | 1651185 | 56787 | 2025-11-30 | 2024-11-08 | 2024-10-22 |  |  | 170 | 0 | 430 | 0 |  | X
07 | 07-355204 | 355204 | 07-VEN-33-3.3/21.2 |  | ACNH-P033- (093)000 | Granite Construction Company | 4820 Mcgrath St., Suite 101 | Ventura Ca 93003 |  |  |  |  | Tehrani, J. | 0 | 0 | 0 | 0 |  | Roadway Excavation And Place Class 3 Aggre | Ventura County At Various Locations From 0.7 Mile North Of Shell Road Undercrossingto 3.5 Miles North Of Nordhoff Ridge Road | 0 | 0 | 0 | 722722 | 722722 | 59875 | 2025-12-05 | 2025-08-13 | 2025-07-15 |  |  | 0 | 0 | 120 | 0
07 | 07-2XC604 | 2XC604 | 07-VEN-33-12.6/16.5 | 20.20 201130 |  | Union Engineering Company, Inc. | P.O. Box 1000 | Ventura, Ca 93002 | 8066443373 | 2137008447 | 1525 Rancho Conejo Blvd, Suite 102 | Thousand Oaks, Ca 91320 | Tehrani, Joseph | 0 | 0 | 0 | 0 | 2025-09-20 | Repair & Restoration Of Storm Damage | In Ventura County City Of Ojai Rte 33 To Repair Storm Damage Incl.Debris Removal, Clean Ds &Basin,Rebuild Shoulders & Berms Dir'S | 100 | 94 | 18920393.23 | 6600 | 20110000 | 47464 | 2025-09-30 | 2023-02-28 | 2023-01-11 |  |  | 670 | 0 | 60 | 0 |  | X
07 | 07-332304 | 332304 | 07-VEN-33-18.9/19.1 |  | HSNH-P033- (092)E | Toro Enterprises, Inc. | 2101 E. Ventura Blvd. | Oxnard Ca 93036 | 8054834515 | 2137928141 | 1525 Rancho Conejo Blvd Ste102 | Thousand Oaks, Ca 91320 | Verma, Niketa | 1206960.15 | 43601.34 | 0 | 16250.75 | 2025-10-20 | Construct Structural Concrete Barrier Slab | Ventura County Near Ojai From 0.5 Mile South Of Bear Creek Bridge To 0.1 Mile North Of North Fork Matilija Creek Bridge | 45 | 68 | 2633763.89 | 3725967 | 3870967 | 57335 | 2025-12-15 | 2025-03-14 | 2025-02-21 |  |  | 67 | 0 | 150 | 0 |  | X
07 | 07-2XF604 | 2XF604 | 07-VEN-33-24.2/27.3 | 20.XX 201130 |  | Granite Construction Company | 4820 Mcgrath Ste #101 | Ventura, Ca 93003 |  | 2137008447 | 1525 Rancho Conejo Blvd. Suite 102 | Thousand Oaks, Ca 91320 | Tehrani, Joseph | 0 | 0 | 0 | 0 | 2025-05-20 | Repair Storm Damage | In Ventura County In City Of Ojai Ven-33 To Repair Slopes/Shoulders,Dikes,Guardrailconstruct Spw Due To Storm Damage Dir'S Emergen | 100 | 100 | 18568046.89 | 41917 | 28050000 | 49065 | 2025-09-30 | 2023-04-11 | 2023-03-02 |  |  | 532 | 0 | 240 | 0 |  | X
07 | 07-356804 | 356804 | 07-VEN-33-26.9/41.7 |  | ACNH-X111- (083)000 | Accu Construction, Inc. | 14751 Plaza Drive Suite L | Tustin Ca 92780 |  |  |  |  | Tehrani, J. | 0 | 0 | 0 | 0 |  | Construct Treatment Bmps. | Ventura County At Various Locations On Route 33 From 1.1 Miles North Of Rose Valley Road To 1.0 Mile South Of Potrero Seco Road An | 0 | 0 | 0 | 585248 | 585248 | 60015 |  | 2025-09-04 | 2025-08-22 |  |  | 0 | 0 | 200 | 0
07 | 07-2XF704 | 2XF704 | 07-VEN-33-44.2/57.2 | 20.XX 201130 |  | R&R Demo And Grading Corp | 21777 Ventura Blvd Suite 245 | Woodland Hills, Ca 91364 |  | 2137008447 | 1525 Rancho Conejo Blvd Suite 102 | Thousand Oaks, Ca 91320 | Tehrani, Joseph | 0 | 0 | 0 | 0 | 2025-10-06 | Winter Storm Repairs | Ven County In City Of Ojai Route 33 To Repair Eroded Slopes, Rebuild Rsp, Rock Scaling And Clean Drainage Systems Dir'S Emergency | 100 | 88 | 12395392.19 | 78750 | 14080000 | 50404 | 2025-11-30 | 2023-05-31 | 2023-03-02 |  |  | 555 | 0 | 120 | 0 |  | X
07 | 07-3311U4 | 3311U4 | 07-VEN-101-.2/40.8 | HB1 | ACNH-X111- (079)E | Peterson-Chase General Engineering Construction, Inc. | 16351 Construction Cir W | Irvine Ca 92606 | 9492520441 | 8058577070 | 1525 Rancho Conejo Blvd Ste102 | Thousand Oaks Ca 91320 | Ira, Alfred | 276903.84 | 267900.17 | 0 | 0 | 2025-10-20 | Upgrade End Treatments And Bridge | In Ventura County On Route 101 From The Los Angeles/Ventura County Line To Old Pacific Coast Highway And On Route 23 From Route 23 | 100 | 69 | 18803040.08 | 25548905 | 27697594.03 | 44564 | 2025-12-20 | 2022-09-23 | 2022-08-31 |  |  | 512 | 0 | 415 | 0
07 | 07-2XT104 | 2XT104 | 07-VEN-101-2.2/2.2 | 20.XX 201130 |  | Summer Construction Inc | Po Box 30 | Santa Paula Ca 93061 |  | 2137928141 | 1525 Rancho Conejo Blvd Ste 102 | Thousand Oaks Ca 91320 | Verma, Niketa | 0 | 0 | 0 | 0 | 2025-10-20 | Repair Vehicular Collision Damages | In Ven County, City Of To N/B Us-101 N Of S Conejo School Rd To Remove &Replace Dam Aged Sound Wall, Transition & Terminal Sysdir' | 100 | 26 | 125435.04 | 4005 | 490000 | 59558 | 2025-12-15 | 2025-06-10 | 2025-04-25 |  |  | 74 | 0 | 60 | 0
07 | 07-0W3904 | 0W3904 | 07-VEN-101-10.7/26.7 | HM1 |  | Intermountain Slurry Seal, Inc. | 1120 Terminal Way | Reno Nv 89502 | 7753989694 | 8058577070 | 1525 Rancho Conejo Blvd #102 | Thousand Oaks, Ca 91320 | Ira, Alfred | 0 | 0 | 0 | 0 | 2025-08-20 | Slurry Seal. | Ventura County From Camarillo Springs Roadundercrossing In Camarillo To Main Street Undercrossing In Ventura | 81 | 97 | 9114913.02 | 8783680 | 8990504.27 | 51485 | 2025-10-31 | 2023-07-28 | 2023-06-20 |  |  | 211 | 0 | 260 | 0 |  | X
07 | 07-0Y1304 | 0Y1304 | 07-VEN-101-25.9/30.6 |  |  | Rv Concrete, Inc. | 605 E. Commercial Street | Anaheim Ca 92801 | 7148884201 | 2133306650 | 1525 Rancho Conejo Blvd #102 | Thousand Oaks, Ca 95630 | Singh, Ranjit | 450623 | 0 | 0 | 141075 | 2025-10-20 | Mainline Individual Slab Replacement. | Ventura County In Ventura From 0.1 Mile West Of Telephone Rd Undercrossing To Ventura Avenue Undercrossing | 69 | 31 | 647495.5 | 2099000 | 2099000 | 59277 | 2025-11-19 | 2025-07-01 | 2025-05-22 |  |  | 55 | 0 | 80 | 0 |  | X
07 | 07-0W4004 | 0W4004 | 07-VEN-101-30.9/36.3 | HM1 |  | Re Chaffee Construction Inc | 1253 Evergreen Road, Suite 3 | Wrightwood Ca 92397 | 7606628068 | 8058577070 | 1525 Rancho Conejo Blvd.#102 | Thousand Oaks, Ca 91320 | Ira, Alfred | 0 | 0 | 0 | 0 | 2024-11-20 | Concrete Pavement Slabs Replacement & Slur | Ventura County In And Near Ventura From Ventura River Bridge To 0.4 Mile South Of Padre Juan Canyon Road Overcrossing And From 0.4 | 100 | 98 | 2919259.79 | 2705704 | 2788169.92 | 50685 | 2025-10-31 | 2023-06-27 | 2023-05-16 |  |  | 162 | 0 | 120 | 0 |  | X
07 | 07-336004 | 336004 | 07-VEN-118-1.4/1.8 | HA42 | ACNH-P118- (070)E | Beador Construction Company, Inc. | 2900 Bristol Street Ste D204 | Costa Mesa Ca 92626 | 9516747352 | 2137008447 | 1525 Rancho Conejo Blvd, #102 | Thousand Oaks, Ca | Tehrani, Joseph | 0 | 36082.78 | 0 | 0 | 2025-10-20 | Construct Stormwater Treatment Best | In Ventura County Near Saticoy From 0.2 Miles East Of Nardo Street To 0.1 Mile West Of Santa Clara River. | 95 | 98 | 5426209.46 | 5087700 | 5522889.57 | 45945 | 2025-11-20 | 2022-12-22 | 2022-12-07 |  |  | 435 | 0 | 460 | 0 |  | X
07 | 07-369704 | 369704 | 07-VEN-118-12.0/13.4 |  | PTNH-P118- (072)000 | C. A. Rasmussen, Inc. | 28548 Livingston Avenue | Valencia Ca 91355 |  |  |  |  | Tehrani, Joseph Solaiman | 659467.2 | 0 | 0 | 0 | 2025-10-20 | Construct Soldier Pile Walls, Slope Protec | Ventura County In Somis From Sand Canyon Road To 0.1 Mile East Of Balcom Canyon Road | 9 | 3 | 816617.2 | 23759126 | 23759126 | 58397 | 2027-12-30 | 2025-05-28 | 2025-04-25 |  |  | 63 | 0 | 690 | 0 |  | X
07 | 07-341604 | 341604 | 07-VEN-118-13.3/15.6 |  |  | 3Sixty Innovation, Inc. | 3555 Rosecrans St 114-110 | San Diego Ca 92110 | 8583041093 | 2137008447 |  |  | Tehrani, Jospeph | 12144.14 | 0 | 0 | 0 | 2025-10-20 | Construct New Modular Office | In And Near Moorpark, At The Eastbound And Westbound Commercial Vehicle Enforcement Facilities. | 100 | 66 | 1630789.02 | 2299998.47 | 2444390.76 | 45946 | 2025-12-20 | 2022-12-22 | 2022-10-25 |  |  | 230 | 0 | 230 | 0
07 | 07-387904 | 387904 | 07-VEN-118-18.4/T18.8 |  |  | Autobahn Construction, Inc. | 933 N. Batavia St. | Orange Ca 92867 | 7147697025 | 2137928141 | 1525 Rancho Conejo Blvd Ste102 | Thousand Oaks, Ca 91320 | Verma, Niketa | 0 | 0 | 0 | 0 |  | Install Chain Link Railing (Type 7 Modifie | Ventura County In Moorpark From 0.2 Mile North Of Route 23 To 0.1 Mile North Of Princeton Avenue Undercrossing. | 0 | 0 | 0 | 2793820 | 2793820 | 57776 | 2025-12-15 | 2025-04-15 | 2025-03-18 |  |  | 0 | 0 | 95 | 0
07 | 07-385104 | 385104 | 07-VEN-118-23.5/30.5 |  |  | Martinez Landscape Co., Inc. | 12357 San Fernando Road | Sylmar Ca 91342 |  | 2137928141 | 1525 Rancho Conejo Blvd, #102 | Thousand Oaks, Ca 91320 | Verma, Niketa | 2400 | 0 | 0 | 0 | 2025-10-20 | Construct Minor Concrete And Place Mulch. | Ventura County In Simi Valley From 0.3 Mile West Of First Street Overcrossing To 0.1 Mile East Of Kuehner Drive Undercrossing | 38 | 89 | 2498052.85 | 2817815.81 | 2789815.81 | 48964 | 2025-11-30 | 2023-04-28 | 2023-04-04 |  |  | 327 | 0 | 870 | 0 |  | X
07 | 07-2XE104 | 2XE104 | 07-VEN-126-9.7/24.6 | 20.20 201130 |  | Summer Construction Inc | 606 Sespe Ave, Suite 202 | Filmore Ca 93015 | 8059339364 | 2135077938 | 1525 Rancho Conejo Blvd Suite 102 | Thousand Oaks, Ca 91320 | Ira, Alfred | 0 | 0 | 0 | 0 | 2025-10-20 | Repair Storm Damage On Ven 126 | In Ventura County On Ven 126 Cities Of Santa Paula,Fillmore And Piru To Repair Storm Damge, Mud Slides,Clean Ds&Erosion Dir'S Emer | 100 | 89 | 5619562.09 | 58500 | 6305000 | 47324 | 2025-10-31 | 2023-03-03 | 2023-01-15 |  |  | 528 | 0 | 120 | 0 |  | X
07 | 07-356504 | 356504 | 07-VEN-126-14.6/34.5 |  | ACNH-P126- (060)E | Accu Construction, Inc. | 14751 Plaza Drive Suite L | Tustin Ca 92780 |  | 2133306650 | 1525 Rancho Conejo #102 | Thousand Oaks, Ca 91320 | Singh, Ranjit | 91140 | 0 | 0 | 0 | 2025-10-20 | Install Dpp Infiltration Area And Hot Mix | Ventura County In And Near Fillmore At Various Locations From 0.2 Mile East Of Boosey Road To 0.1 Mile West Of The Los Angeles Cou | 71 | 66 | 1082285.71 | 1557705 | 1636705 | 57175 | 2026-01-30 | 2025-02-18 | 2025-01-23 |  |  | 157 | 0 | 220 | 0 |  | X
07 | 07-1XW104 | 1XW104 | 07-VEN-126-20.3/20.3 | 20.XX 201131 |  | Mgp Construction Dba Michael G Porteous | Po Box 355 | Upland, Ca 91785 |  | 8058577070 | 1525 Rancho Conejo Blvd Suite 102 | Thousand Oaks, Ca 91320 | Ira, Alfred | 0 | 0 | 0 | 0 | 2025-10-20 | Construct/Replace Maintenace Station | Ventura County In City Of Fillmore Ven-126Replace/Construct The Fillmore Maintenancestation Damaged By High Winds Dir'S Emergency | 100 | 80 | 3029281.8 | 76270 | 3798500 | 55657 | 2025-12-31 | 2024-04-15 | 2024-01-26 |  |  | 220 | 0 | 120 | 0
07 | 07-2XP204 | 2XP204 | 07-VEN-126-/0 | 20.XX 201130 |  | Baltazar Construction, Inc | 236 E. Arrow Hwy | Covina, Ca 91722 |  | 2137928141 | 1525 Rancho Conejo Blvd Suite 102 | Thousand Oaks, Ca 91320 | Verma, Niketa | 0 | 0 | 0 | 0 | 2025-05-20 | Repair Mudslide Debris Due To Storm Damage | Ventura County,City Of Piru, Santa Paula,&Fillmore Var Locations Clear Shoulders & Rdway Of Mudslide/Debris,Ds &Erosion Cntrldir'S | 100 | 60 | 1001375.21 | 7251 | 1681000 | 56005 | 2025-12-31 | 2024-06-20 | 2024-05-30 |  |  | 91 | 0 | 60 | 0
07 | 07-3237U4 | 3237U4 | 07-VEN-150-13.3/19 | HA22 | ACNH-P150- (028)E | C. A. Rasmussen, Inc. | 28548 Livingston Avenue | Valencia Ca 91355 |  | 2137008447 | 1525 Rancho Conejo Blvd #102 | Thousand Oaks, Ca 91320 | Tehrani, Joseph | 31300 | 45473.01 | 0 | 0 | 2025-08-20 | Place Hma (Type A) And Cold Plane Asphalt | Ventura County In And Near Ojai From Burnham Road To Gorham Road | 100 | 99 | 8817574.97 | 8145315.4 | 8555664.04 | 49205 | 2025-11-30 | 2023-05-10 | 2023-03-27 |  |  | 360 | 0 | 360 | 0 |  | X
07 | 07-2XN104 | 2XN104 | 07-VEN-150-20.0/32.2 | 20.XX 201130 |  | R & R Demo And Grading Corp | 1180 S Beverly Drive Suite310 | Los Angeles, Ca 90035 |  | 2137008447 | 1525 Rancho Conejo Blvd Ste 102 | Thousand Oaks, Ca 91320 | Tehrani, Joseph | 0 | 0 | 0 | 0 | 2025-10-06 | Repair Damage Due To Rainstorms | In Ventura County, In&Around Santa Paula On Ven-150 @Multiple Locations To Remove/ Repair Damaged Slopes Due To Rainstorms Dir'S E | 100 | 87 | 27382812.83 | 76148 | 31495900 | 55594 | 2025-11-30 | 2024-04-05 | 2024-02-22 |  |  | 407 | 0 | 120 | 0 |  | X
07 | 07-344504 | 344504 | 07-VEN-150-31.3/34.4 |  |  | Granite Construction Company | 4820 Mcgrath St., Suite 101 | Ventura Ca 93003 | 6619029460 | 2137008447 | 1525 Rancho Conejo Blvd Ste102 | Thousand Oaks Ca 91320 | Solaiman Tehrani, J. | 418422.4 | 0 | 0 | 0 | 2025-10-20 | Cold Plane And Overlay, Modify Traffic Sig | Ventura County In Santa Paula From 0.2 Mile North Of Bridge Road To Santa Maria Street | 46 | 25 | 1949546.45 | 7631505 | 7781505 | 57341 | 2026-03-11 | 2025-03-12 | 2025-02-14 |  |  | 96 | 0 | 210 | 0 |  | X
07 | 07-346804 | 346804 | 07-VEN-232-.4/4.1 |  | ACNH-S232- (003)E | Toro Enterprises, Inc. | 2101 E. Ventura Blvd. | Oxnard Ca 93036 |  | 2137008447 | 1525 Rancho Conejo Blvd | Thousand Oaks, Ca 91320 | Solaiman Tehrani, J. | 948899.92 | 0 | 0 | 275000 | 2025-10-20 | Cold Plane And Overlay With Hma & Rhma. | Ventura County In And Near Oxnard From Route 232/101 Separation To Route 118 | 15 | 17 | 2925573.76 | 16282743.7 | 16282743.7 | 57655 | 2026-11-30 | 2025-03-14 | 2025-02-04 |  |  | 60 | 0 | 400 | 0 |  | X
07 | 07-2XM504 | 2XM504 | 07-VEN--/0 | 20.10 201352 |  | Izurieta Fence Company Inc | 3000 Gilroy St | Los Angeles, Ca 90039 |  | 2137008447 | 1525 Rancho Conejo Blvd Ste 102 | Thousand Oaks, Ca 91302 | Tehrani, Joseph Soleiman | 0 | 0 | 0 | 0 | 2025-10-06 | Fences/Gates& Detection Systems | Ventura Cty In City Of Santa Paula&Malibu Big Sycamore Ms To Construct Fences/Gates & Perimeter Laser Detection System Dir'S Emerg | 100 | 47 | 455350.09 | 6880 | 969100 | 56417 | 2025-11-30 | 2024-08-21 | 2024-07-16 |  |  | 1038 | 0 | 180 | 0
08 | 08-1P0804 | 1P0804 | 08-RIV-10-7.0/44.5 |  |  | Truesdell Corporation Of California, Inc. | 1310 W. 23Rd Street | Tempe Az 85282 | 6028096032 | 9518306845 | 850 S Via Lata #104 | Colton, Ca 92324 | Rahman, Md | 1048408.6 | 0 | 0 | 376393.04 | 2025-10-20 | Furnish & Place Polyester Concrete Overlay | Riverside County At Various Locations Fromveile Avenue Undercrossing In Beaumont To Monterey Avenue Overcrossing At Thousand Palms | 10 | 29 | 1424801.64 | 4928928 | 4940928 | 59337 | 2026-04-14 | 2025-06-13 | 2025-06-03 |  |  | 13 | 0 | 130 | 0 |  | X
08 | 08-1L9504 | 1L9504 | 08-RIV-10-12.6/13.4 |  |  | Diversified Landscape Company Anthony Rodriguez Project Manager | 21730 Bundy Canyon Road | Wildomar Ca 92595 | 9518308725 | 9512326478 | 937 S. Via Lata Suite 650 | Colton, Ca 92324 | Benson, David | 2190 | 0 | 0 | 0 | 2025-10-20 | Restore And Rehabilitate Existing | In The City Of Banning From 0.25 Miles West Of 8Th Street I.C. To S. San Gorgonio Ave. | 0 | 0 | 1051949.83 | 986640.5 | 1059810.5 | 44004 | 2026-08-10 | 2022-07-29 | 2022-06-13 |  |  | 706 | 0 | 860 | 0 | X | X
08 | 08-1C0814 | 1C0814 | 08-RIV-10-60.7/74.3 |  |  | Coffman Specialties, Inc. | 9685 Via Excelencia Suite 200 | San Diego Ca 92126 | 858363100 | 9098440619 | 41601 Corporate Way | Palm Desert, Ca 92211 | Koury, Peter | 391250 | 618652.92 | 72289.2 | 0 | 2025-10-20 | Pavement Rehab | Riverside County In Coachella And At Cactus City From 1.8 Miles East Of Dillon Road Undercrossing To 0.5 Miles West Of East Cactus | 97 | 97 | 190418850.27 | 188155000 | 197087091.94 | 42347 | 2025-11-21 | 2022-03-28 | 2022-03-28 |  |  | 867 | 0 | 830 | 60 |  | X
08 | 08-0G8504 | 0G8504 | 08-RIV-10-71.2/72.6 |  | CIMG-0104- (068)E | Granite Construction Company | Po Box 742478 | Los Angeles, Ca 90074-2478 | 8317287561 | 9512326263 | 41601 Corporate Way | Palm Desert, Ca 92260 | Vu, Khoi | 1273228 | 100916.02 | 0 | 950000 | 2025-10-20 | Building Work. | Riverside County Near Indio From 0.9 Mile West To 0.5 Mile East Of The Cactus City Safety Roadside Rest Areas | 66 | 17 | 6447174.52 | 38224000 | 38329027.34 | 58656 | 2029-11-16 | 2025-05-07 | 2025-04-03 |  |  | 33 | 0 | 1050 | 0 |  | X
08 | 08-1C08U4 | 1C08U4 | 08-RIV-10-134.0/156.5 |  | ACNH-0105- (052)E | Fisher Sand & Gravel Co. Dba Southwest Asphalt Paving | 1302 W. Drivers Way | Tempe Az 85284 | 7029293157 | 9512326161 | 134 E Hobson Way | Blythe, Ca 92225 | Brown, Paul | 3408231.75 | 1012989.35 | 0 | 0 | 2025-10-20 | Place Hma (Type A), Jpcp, Imported Borrow, | Riverside County From 1.1 Miles West Of Wiley Well Road Overcrossing To California/ Arizona State Line | 44 | 65 | 142982049.13 | 232232232.32 | 219809875.23 | 53666 | 2026-09-16 | 2023-07-24 | 2023-06-22 |  |  | 374 | 0 | 850 | 0 |  | X
08 | 08-1T1404 | 1T1404 | 08-RIV-10-748.0/81.7 | 20.20 201130 |  | Coffman Specialties, Inc. | 9685 Via Excelencia Suite 200 | San Diego, Ca 92126 |  | 9512326263 | 41601 Corporate Way | Palm Desert, Ca 92260 | Vu, Khoi | 0 | 0 | 0 | 0 |  | Repair Fire Damaged Structure | Repair Fire Damaged Structure Dir'S Order Emergency F.A. | 0 | 0 | 0 | 18060 | 2985000 | 60124 | 2025-09-11 | 2025-10-10 | 2025-08-19 |  |  | 0 | 0 | 60 | 0
08 | 08-1R4504 | 1R4504 | 08-RIV-15-.6/1.6 | 20.20 201130 |  | Myers & Sons Construction Llc | 45 Morrison Ave | Sacramento Ca 95838 | 9162839950 | 9512326052 | 119 N Maple Street #A | Corona Ca 92878 | Joe Lopez | 0 | 0 | 0 | 0 |  | Repair Damage 66" Csp Culvert | Damage Repair For Existing 66" Culvert Crossing Underneath I-15 Dir'S Order Emergency F.A | 0 | 0 | 0 | 21000 | 3485000 | 60099 | 2026-01-31 | 2025-07-22 | 2025-06-12 |  |  | 0 | 0 | 60 | 0
08 | 08-1K4004 | 1K4004 | 08-RIV-15-3.5/6.8 |  | ACIM-0155- (175)E | Beador Construction Company, Inc. | 2900 Bristol Street D204 | Costa Mesa Ca 92626 | 9516747352 | 9512327608 | 119 N. Maple St. Ste.A | Corona, Ca 92880 | Sostrom, Denise | 1317634.43 | 21894.72 | 0 | 0 | 2025-10-20 | Hma (Type A), Rdwy Exc, Str Conc Ret Wall, | Temecula From 0.1 Mi North Of Temecula Parkway To 0.2 Mi North Of Winchester Road | 33 | 43 | 13344204.16 | 30393300 | 30744275 | 57389 | 2027-10-07 | 2025-02-27 | 2025-01-29 |  |  | 119 | 0 | 610 | 0 |  | X
08 | 08-1E3404 | 1E3404 | 08-RIV-15-15.9/20.3 | HA42 | ACIM-0155- (172)E | Diverscape, Inc. Dba Diversified Landscape Co. | 21730 Bundy Canyon Road | Wildomar Ca 92595 | 9512451686 | 9095189827 | 937 S Via Lata Suite 650 | Colton, Ca 92324 | Mcnicoll, Joseph | 45505 | 9851.69 | 0 | 0 | 2025-09-26 | Bonded Fiber Matrix, Minor Stamped Conc, R | Riverside County In Wildomar And Lake Elsinore From 0.4 Mile South Of Bundy Canyon Road To 0.5 Mile North Of Grunder Drive/Frankli | 100 | 100 | 3605600.39 | 3624967.2 | 3707663.12 | 55916 | 2025-09-26 | 2024-04-17 | 2024-03-28 | 2025-10-15 |  | 170 | 0 | 180 | 0 |  | X
08 | 08-1J8704 | 1J8704 | 08-RIV-15-16.3/52.3 |  | ACIM-0155- (173)E | Beador Construction Company, Inc. | 2900 Bristol Street D204 | Costa Mesa Ca 92626 | 9516747352 | 9518306837 | 119 North Maple Suite A | Corona, Ca 92880 | Avila, Xavier | 651557.55 | 0 | 0 | 12500 | 2025-10-20 | Minor Concrete, Hma (Type A), Modifying Si | Riverside County At Various Locations Frombundy Canyon Road Undercrossing In Wildomar To Philadelphia Street Undercrossing In Eas | 30 | 80 | 2111593.98 | 2537700 | 2587700 | 56214 | 2026-11-23 | 2024-08-08 | 2024-07-10 |  |  | 107 | 0 | 360 | 0 |  | X
08 | 08-1R3804 | 1R3804 | 08-RIV-15-18.7/19 | 20.20 201130 |  | Baltazar Construction Inc. | 236 E Arrow Hwy | Covina, Ca 91722 |  | 9512326052 | 119 N Maple Street #A | Corona, Ca 92878 | Joe Lopez | 0 | 0 | 0 | 0 | 2025-09-20 | Replace Damaged Culvert Resulted From Fire | Replace Damaged Culvert Resulted From Fire Set By An Unsheltered Encampment Individual Dir'S Order Emergency F.A. | 100 | 79 | 3707049.97 | 16975 | 4685000 | 57678 | 2025-12-30 | 2024-11-05 | 2024-11-05 |  |  | 75 | 0 | 30 | 0
08 | 08-1R4204 | 1R4204 | 08-RIV-15-35.1/35.1 | 20.20.201130 |  | Bcm Group, Inc | 9339 Feron Blvd | Rancho Cucamonga, Ca 91730 |  | 9096015089 | 850 S. Via Lata, Suite 100A | Colton, Ca 92324 | Ulloa, Irma | 0 | 0 | 0 | 0 | 2023-09-20 | Replace Backup Generator | Replace Damaged Backup Generator For The Santiago Peak Radio Communication Tower From The Airport Fire Dir'S Order Emegency F.A. | 100 | 96 | 367969 | 6655 | 385000 | 58176 | 2026-01-30 | 2024-11-23 | 2024-11-22 |  |  | 269 | 0 | 45 | 0 |  | X
08 | 08-1P0704 | 1P0704 | 08-RIV-15-46.5/49.3 |  |  | Diverscape, Inc. Dba Diversified Landscape Co. | 21730 Bundy Canyon Road | Wildomar Ca 92595 | 9512451168 | 9512326478 | 937 South Via Lata Suite 650 | Colton, Ca 92324 | Benson, David | 3807 | 0 | 0 | 0 | 2025-10-20 | Roadside Clearing And Hydroseed. | Riverside County In Eastvale From Santa Ana River Bridge To Bellegrave Avenue Overcrossing | 0 | 0 | 732013.4 | 912680.2 | 918880.2 | 56135 | 2028-07-20 | 2024-07-10 | 2024-06-13 |  |  | 199 | 0 | 870 | 0 | X | X
08 | 08-1H3804 | 1H3804 | 08-RIV-60-6.1/8 |  | ACNH-P060- (164)E | Accu Construction, Inc. | 14751 Plaza Drive Suite L | Tustin Ca 92780 | 7146414730 | 9512326478 | 937 S Via Lata Suite 650 | Colton, Ca 92324 | Benson, David | 3240 | 0 | 0 | 0 | 2025-10-20 | Minor Conc, Water Service Connection, And | Riverside County In Jurupa Valley From 0.5Mile East Of Pyrite Street To 0.4 Mile West Of Pacific Avenue | 0 | 0 | 4232721.35 | 4392608 | 4312255.5 | 55124 | 2028-01-24 | 2023-12-21 | 2023-12-05 |  |  | 401 | 0 | 950 | 0 | X | X
08 | 08-1P6804 | 1P6804 | 08-RIV-62-3.3/6.5 | 20.20 201130 |  | Granite Construction Company | 38000 Monroe Street | Indio, Ca 92203 | 7603916297 | 9518306828 | 41601 Corporate Way | Palm Desert, Ca 92316 | Hossain, Sadique | 0 | 3367.62 | 0 | 0 | 2025-05-20 | Repair Damaged Bridge Piers | 2023 Hurricane Hillary Tropical Storm Damage On Sr 62 Place Rsp, Restore Undermined Pavement Dir'S Order Emergency F.A. | 100 | 99 | 4325244.31 | 9450 | 4397000 | 54484 | 2025-07-30 | 2023-10-23 | 2023-08-28 | 2025-10-27 |  | 198 | 0 | 30 | 0 |  | X
08 | 08-1G4704 | 1G4704 | 08-RIV-74-3.1/3 |  | B1ST-S074- (073)E | Beador Construction Company, Inc. | 2900 Bristol Street D204 | Costa Mesa, Ca 92626 | 9516747352 | 9512323739 | 9225 Stellar Court, Ste B | Corona, Ca 92883 | Bergevin, Mike | 3440 | 0 | 0 | 0 | 2025-10-20 | Structural Conc Br, Conc Slab, Hma (Type A | Riverside County Near Lake Elsinore At Morrill Canyon Bridge And Near Hemet At Strawberry Creek Bridge. | 62 | 96 | 8921830.99 | 8485300 | 9284120.39 | 50005 | 2026-08-05 | 2023-05-10 | 2023-04-06 |  |  | 309 | 0 | 500 | 0 |  | X
08 | 08-1R3704 | 1R3704 | 08-RIV-74-3.9/11.8 | 20.20 201130 |  | Skanska Usa Civil West California District, Inc. | 1995 Agua Mansa Rd | Riverside, Ca 92509 |  | 9512323739 | 9225 Stellar Ct., Ste B | Corona, Ca 92883 | Bergevin, Mike | 0 | 1424.5 | 0 | 0 | 2025-10-20 | Fire Damage Repairs | Repair Damages Resulted From Airport Fire Dir'S Order Emergency F.A. | 100 | 30 | 1191623.82 | 15800 | 3985000 | 57137 | 2026-04-30 | 2025-01-02 | 2024-10-07 |  |  | 179 | 0 | 50 | 0
08 | 08-1K6904 | 1K6904 | 08-RIV-74-5.7/11.8 |  | HSST-S074- (077)E | Granite Construction Company | 38000 Monroe Street | Indio Ca 92203 | 7605343239 | 9512326052 | 119 N Maple Street Suite A | Corona, Ca 92880 | Lopez, Joesph | 9369910.38 | 0 | 0 | 1747000 | 2025-10-20 | Rock Excavation, Hma (Type A), Rhma-G, And | Riverside County In And Near Lake Elsinorefrom Monte Vista Street To Grand Avenue | 14 | 30 | 26959057.58 | 87942000 | 88734890 | 57390 | 2028-06-30 | 2025-02-10 | 2025-01-09 |  |  | 97 | 0 | 675 | 0 |  | X
08 | 08-1L3104 | 1L3104 | 08-RIV-74-11.8/17.3 |  |  | R.J. Noble Company | 15505 East Lincoln Avenue | Orange Ca 92856 | 7146371550 | 5918306837 | 119 N Maple Ste A | Corona Ca 92880 | Xavier Avila | 0 | 0 | 0 | 0 |  | Rhma (Gap Graded), Replace Ac Surf, And Co | Riverside County In Lake Elsinore From Grand Avenue To Route 15/74 Separation | 0 | 0 | 0 | 5478166.5 | 5478166.5 | 59616 | 2026-03-25 | 2025-07-15 | 2025-06-06 |  |  | 0 | 0 | 125 | 0
08 | 08-1C07U4 | 1C07U4 | 08-RIV-74-27.5/34.3 |  | ACNH-P074- (073)E | Griffith Company | 3050 E. Birch St | Brea Ca 92821 | 7149845500 | 9096654132 | 9225 Stellar Court Suite B | Corona, Ca 92883 | Sanchez, Omar | 0 | 0 | 0 | 0 |  | Rubberized Hma, Fiber Optic Cable Systems, | Riverside County At And Near Romoland And Homeland From Bonnie Drive To Winchester Road | 0 | 0 | 0 | 17882900 | 17882900 | 60120 | 2027-01-07 | 2025-08-22 | 2025-08-11 |  |  | 0 | 0 | 200 | 0
08 | 08-1G6704 | 1G6704 | 08-RIV-79-5.4/11.4 |  | SSTG-S079- (047)E | Ortiz Enterprises, Inc. | 6 Cushing Suite 200 | Irvine Ca 92618 | 9497531414 | 9518309182 | 9225 Stellar Court, Suite B | Corona, Ca 92883 | Abdalla, Osama | 1623093.5 | 307590.65 | -14183.85 | 0 | 2025-10-20 | Hot Mix Asphalt, Soil Nail, Structural Con | Riverside County Near Temecula From 0.4 Mile South Of Sage Road To 1.1 Miles Southof Pauba Road | 32 | 35 | 20922120.35 | 60801162.1 | 60857377.48 | 56084 | 2028-01-25 | 2024-06-17 | 2024-05-23 |  |  | 269 | 0 | 690 | 142 |  | X
08 | 08-1P2804 | 1P2804 | 08-RIV-91-8.3/9 |  | SNHG-P091- (161)E | America Pacific Construction Inc | 7161 Citrus Valley Ave | Eastvale Ca 92880 | 5595779999 | 9098443312 | 4334 Latham Street, Suite 100 | Riverside, Ca 92501 | St.Jacques, Michael | 0 | 0 | 0 | 0 |  | Mod Fo Cable Systems, Vegetation Control ( | Riverside County In Corona From 0.3 Mile East Of Promenade Avenue Overcrossing To 0.1 Mile West Of Mckinley Street Undercrossing | 0 | 0 | 0 | 630330 | 630330 | 59542 | 2025-11-21 | 2025-07-22 | 2025-06-11 |  |  | 0 | 0 | 20 | 0
08 | 08-1L3204 | 1L3204 | 08-RIV-91-15.6/21.6 |  | ACNH-P091- (155)E | Diversified Landscape Co. | 21735 Bundy Canyon Road | Wildomar Ca 92595 | 9512451686 | 9095189827 | 937 S. Via Lata Suite 650 | Colton, Ca 92324 | Mcnicoll,Joseph | 4684.5 | 0 | 0 | 0 | 2025-10-20 | Minor Concrete, Wood Mulch & Plant Establi | Riverside County In Riverside From 0.1 Mile West Of Adams Street To Route 60/91/215 Separation | 0 | 0 | 4027713.8 | 4394267.25 | 4478743.2 | 53705 | 2028-04-24 | 2023-11-01 | 2023-09-25 |  |  | 395 | 0 | 1000 | 0 | X | X
08 | 08-1G6304 | 1G6304 | 08-RIV-111-47.2/55.3 |  | ACNH-P111- (080)E | Granite Construction Company | 38000 Monroe Street | Indio Ca 92203 | 7602967967 | 9518306828 | 41601 Corporate Way | Palm Desert, Ca 92316 | Sadique Hossain | 233969.29 | 43800 | -231540.21 | 0 | 2025-10-20 | Rhma-G, Replace Ac Surfacing, And Cold Pla | Riverside County In Palm Springs From Golfclub Drive To West Gateway Drive | 70 | 92 | 12202578.82 | 13077031 | 13022874.79 | 56967 | 2026-02-05 | 2024-10-04 | 2024-09-05 |  |  | 168 | 0 | 240 | 0 |  | X
08 | 08-0R7904 | 0R7904 | 08-RIV-111-53.9/0 |  |  | Calpromax Engineering, Inc. | 650 N. Rose Dr. #186 | Placentia Ca 92870 | 7145734599 | 9512326263 | 41601 Corporate Way | Palm Desert, Ca 92260 | Vu,Khoi | 252325 | 0 | 0 | 0 | 2025-08-20 | Signal And Lighting System. | Riverside County In Palm Springs At Vista Chino | 84 | 82 | 590892.78 | 672225 | 710225 | 56522 | 2025-09-03 | 2024-07-19 | 2024-06-20 |  |  | 38 | 0 | 45 | 0 |  | X
08 | 08-1N9704 | 1N9704 | 08-RIV-215-9.0/38 |  |  | Kanaan Construction, Inc. | 5040 Heintz Street | Baldwin Park, Ca 91706 | 6263345775 | 9096015120 | 750 S Via Lata Suite 100 | Colton, Ca 92324 | Salloum, George | 0 | 0 | 0 | 0 | 2025-09-23 | Fiber Optic Cable Systems. | Riverside County At Various Locations From0.5 Mile South Of Murrieta Hot Spring Roadin Murrieta To 0.6 Mile North Of Eucalyptus Av | 100 | 100 | 506164.8 | 488380 | 505380 | 56238 | 2025-09-23 | 2024-08-16 | 2024-06-26 | 2025-09-23 |  | 45 | 0 | 45 | 0 |  | X
08 | 08-1J2604 | 1J2604 | 08-RIV-215-13.5/19.5 |  | ACIM-2151- (253)E | Martin Marietta San Diego Aggregates Llc Dba Atp Generalengineering Contractors | 4211 Ponderosa Ave Ste C | San Diego Ca 92123 | 8589446711 | 9518309182 | 9225 Stellar Ct., Suite B | Corona, Ca 92883 | Abdalla, Osama | 3765756 | 133958.43 | -129868.79 | 0 | 2025-10-20 | Rhma, Replace Ac Surfacing, Rock Blanket, | Riverside County In Murrieta And Menifee From 1 Mile North Of Clinton Keith Road To1 Mile North Of Newport Road | 89 | 90 | 21307218.39 | 22549794 | 23533721.81 | 55328 | 2025-12-10 | 2024-02-09 | 2024-01-10 |  |  | 267 | 0 | 300 | 0 |  | X
08 | 08-1J2904 | 1J2904 | 08-RIV-215-25.0/31.2 |  | ACIM-2151- (254)E | Coffman Specialties, Inc. | 9685 Via Excelencia, Suite 20 | San Diego Ca 92126 | 8585363100 | 9512323777 | 9225 Stellar Court Suite B | Corona, Ca 92883 | Guglielmana, Thomas | 1092496.47 | 0 | 0 | 0 | 2025-10-20 | Rhma, Hma, Replace Ac Surfacing, And Cold | Riverside County In And Near Perris From 0.1 Mile South Of San Jacinto River Bridgeto 0.3 Mile North Of Ramona Expressway | 33 | 84 | 24356935.09 | 27535000 | 28271487.59 | 56087 | 2026-10-19 | 2024-07-12 | 2024-06-18 |  |  | 165 | 0 | 500 | 0 |  | X
08 | 08-1J6104 | 1J6104 | 08-RIV-215-40.5/42.7 |  | ACIM-2151- (256)E | Fbd Vanguard Construction | 550 Greenville Road | Livermore Ca 94550 |  | 9518306853 | 4334 Latham Street Suite 100 | Riverside, Ca 92501 | Alam, Mahfual | 1926404.5 | 30511.8 | 0 | 0 | 2025-10-20 | Individual Slab Replacement (Rsc), Rhma, A | Riverside County In Riverside From 0.8 Mile South Of Route 60/91 Separation To 0.4 Mile South Of Martin Luther King Boulevard Unde | 24 | 35 | 8065031.37 | 22714677.9 | 22972101.9 | 57080 | 2026-10-16 | 2024-12-03 | 2024-11-05 |  |  | 79 | 0 | 325 | 0 |  | X
08 | 08-1J4504 | 1J4504 | 08-RIV-243-/29.7 |  | ACST-S243- (002)E | All American Asphalt | 400 East Sixth Street | Corona Ca 92879 | 8587768840 | 9518306845 | 850 S Via Lata #104 | Colton, Ca 92324 | Rahman, Md | 1175338.09 | 105130 | 0 | 0 | 2025-10-20 | Hma, Thermoplastic Traffic Stripe, And Col | Riverside County From Route 74 At Mountaincenter To Route 10 In Banning | 10 | 19 | 3374880.69 | 16898959 | 17343921.5 | 58655 | 2027-11-04 | 2025-05-23 | 2025-03-07 |  |  | 55 | 0 | 550 | 13 |  | X
08 | 08-1J3204 | 1J3204 | 08-RIV-5732-/0 |  |  | Nationwide Contracting Services, Inc. Dba Nationwide General Construction Services | 7660 Liberty Dr | Huntington Beach Ca 92647 | 5626078886 | 9096654132 | 9225 Stellar Court, Suite B | Corona, Ca 92883 | Sanchez, Omar | 325108.84 | 0 | 0 | 0 | 2025-10-20 | Building Work, Wrought Iron Fence, Hot Mix | Riverside County Near Lake Elsinore At Lake Elsinore Maintenance Station At 18745Conard Avenue | 4 | 4 | 325108.84 | 8717880.1 | 8727880.1 | 59560 | 2027-08-26 | 2025-06-19 | 2025-05-29 |  |  | 19 | 0 | 480 | 0 |  | X
08 | 08-1J6204 | 1J6204 | 08-SBD-0-/0 |  |  | Preferred General Services | 19622 Shoshonee Road | Apple Valley Ca 92307 | 7602403236 | 9512326497 | 222 E Main St, Ste 202 | Barstow, Ca 92311 | Adodo, Jegbefume | 851.76 | 0 | 0 | 0 | 2025-06-20 | Building Work. | San Bernardino County At Essex At The Essex Maintenance Station | 28 | 18 | 167858.4 | 958522.5 | 958522.5 | 56320 | 2025-10-27 | 2024-09-10 | 2024-06-21 |  | S | 24 | 0 | 85 | 0 |  | X
08 | 08-1J5404 | 1J5404 | 08-SBD-15-2.4/0 |  | BFIM-0151- (252)E | Flatiron Dragados West Llc | 14726 Ramona Avenue, Suite 30 | Chino, Ca 91710 | 9095978413 | 9518408248 | 10370 Commerce Center,Ste B110 | Rancho Cucamonga, Ca 91730 | Tran, Giang-Sinh | 1108804 | 53251.85 | 0 | 0 | 2025-10-20 | Cb, Jpcp, Structural Concrete And Bridge R | San Bernardino County In Ontario At Route 10/15 Separation | 39 | 28 | 3682303.42 | 14694000 | 13326059.11 | 58596 | 2026-04-15 | 2025-04-24 | 2025-04-02 |  |  | 76 | 0 | 195 | 0 |  | X
08 | 08-1R2804 | 1R2804 | 08-SBD-15-7.6/7.6 | 20.20 201130 |  | Conti, Llc | 14 Morgan | Irvine, Ca 92618 |  | 9096015089 | 850 S. Via Lata, Suite 100A | Colton, Ca 92324 | Ulloa, Irma | 0 | 0 | 0 | 0 | 2025-10-20 | Replace The Nonfunctional Chiller System | Replace The Nonfunctional Chiller System Dir'S Order Emergency F.A. | 58 | 56 | 399452.77 | 2538 | 710000 | 59342 | 2025-01-30 | 2025-06-05 | 2025-01-17 |  |  | 151 | 0 | 45 | 0 |  | X
08 | 08-1L5104 | 1L5104 | 08-SBD-15-15.9/0 |  |  | Peterson-Chase General Engineering Construction, Inc. | 16351 Construction Circle Wes | Irvine Ca 92606 | 9492520441 | 9096014064 | 10370 Commerce Center Dr B-110 | Rancho Cucamonga Ca 91730 | Alfonso Gonzalez | 76025.5 | 0 | 0 | 60000 | 2025-10-20 | Furnish And Place Polyester Concrete Overl | San Bernardino County Near San Bernardino At Devore Overhead | 25 | 8 | 136025.5 | 1666347.87 | 1666347.87 | 60079 | 2025-12-19 | 2025-09-09 | 2025-08-12 |  |  | 14 | 0 | 55 | 0 |  | X
08 | 08-1H3904 | 1H3904 | 08-SBD-15-20.5/21.6 |  | ACIM-0151- (250)E | Powell Constructors Inc | 8555 Banana Avenue | Fontana Ca 92335 | 9093568880 | 9096015118 | 15255 Bear Valley Road | Hesperia, Ca 92345 | Santa Cruz, Mauricio | 76650 | 0 | 0 | 0 | 2025-09-20 | Construct Building, Roadway Exc, Jpcp, And | San Bernardino County From 0.6 Mile North Of Cleghorn Road Undercrossing To 0.5 Milesouth Of Route 138 And From 0.5 Mile Southof T | 82 | 90 | 23010214.55 | 25227230 | 25412580.16 | 52244 | 2025-12-11 | 2023-08-30 | 2023-07-13 |  |  | 245 | 0 | 300 | 0 |  | X
08 | 08-1J3304 | 1J3304 | 08-SBD-15-160.9/161.5 |  | CIMG-0153- (049)E | Tsi Engineering, Inc. | 4600 Roseville Rd Suite 140 | North Highlands Ca 95660 | 9168869066 | 9512328611 | 222 E. Main St. Suite #208 | Barstow, Ca 92311 | Nguyen, Khoa | 1448246.5 | 14195.14 | 0 | 0 | 2025-10-20 | Building Work. | San Bernardino County Near Mountain Pass From 0.2 Mile South To 0.4 Mile North Of Valley Wells Safety Roadside Rest Area | 21 | 27 | 3209318.84 | 12349786 | 11872674 | 57138 | 2026-08-20 | 2025-01-27 | 2024-12-24 |  |  | 52 | 0 | 250 | 0 |  | X
08 | 08-1N1214 | 1N1214 | 08-SBD-15-180.9/185.5 |  |  | Ferreira Construction Co., Inc. | 10370 Commerce Drive, Suite B | Rancho Cucamonga Ca 91730 | 9092172665 | 2134349325 | 464 W 4Th Street | San Bernardino, Ca 92401 | Yaacoub Lawrance | 0 | 0 | 0 | 8767.8 | 2025-08-20 | Lane Control Sign Systems. | San Bernardino County About 43 Miles Northof Baker At Various Locations From 0.5 Mile South Of Yates Well Road Overcrossingto 0.7 | 67 | 43 | 1279144.28 | 2889921 | 2839356.93 | 55547 | 2025-10-31 | 2024-03-21 | 2023-12-18 |  | S | 40 | 0 | 60 | 0 |  | X
08 | 08-0N0804 | 0N0804 | 08-SBD-15-/0 | 20.20 201130 |  | Jpus Builders Corp | 3010 W Orange Ave #102 | Anaheim, Ca 92804 | 6572632411 | 9096014064 | 15255 Bear Valley Road | Hesperia, Ca 92345 | Gonzalez, Alfonso | 0 | 10343.64 | 0 | 0 | 2025-09-20 | Upgrade Fencing And Lighting | Upgrade Security Measures At Two Maintenance Stations Cajon L5707 And Victorville L5710 Dir'S Order Emergency F.A. | 100 | 99 | 1635936.56 | 18000 | 1651000 | 56517 | 2025-09-30 | 2024-09-06 | 2024-05-24 |  |  | 232 | 0 | 120 | 0 |  | X
08 | 08-1R5004 | 1R5004 | 08-SBD-18-18.4/19.2 | 20.20 201130 |  | Myers & Sons Construction Llc | 45 Morrison Ave | Sacramento, Ca 95838 | 9162839950 | 9096654200 | 850 S Via Lata, Suite 100A | Colton,Ca 92323 | Mineo, Nicholas | 0 | 0 | 0 | 0 | 2025-10-20 | Repair Deteriorating Collapsing Retaining | Repair Deteriorating And Collapsing Retaining Wall At Pm 18.76, Scaling And Installing Net Drapery Systems At Pm 18.48Dir'S Order | 100 | 38 | 1844648.12 | 29400 | 4885000 | 59195 | 2025-12-15 | 2025-04-03 | 2025-01-06 |  |  | 60 | 0 | 60 | 0
08 | 08-1J3004 | 1J3004 | 08-SBD-18-90.9/96.6 |  | ACNH-P018- (065)E | Sully-Miller Contracting Company | 135 S. State College Blvd #40 | Brea Ca 92821 | 7145789600 | 9096014064 | 15255 Bear Valley Road | Hesperia, Ca 92345 | Gonzalez, Alfonso | 3454861.24 | 24038.03 | 8723.9 | 35000 | 2025-10-18 | Hma (Type A), Mod Signal & Ltg Systems, & | San Bernardino County In And Near Victorville From Apple Valley Inn Road To Route 15/18 Separation | 50 | 70 | 9230484.45 | 12766200.1 | 13201654.64 | 57136 | 2026-04-28 | 2025-01-22 | 2024-12-06 |  |  | 127 | 0 | 255 | 0 |  | X
08 | 08-1T3304 | 1T3304 | 08-SBD-38-14.9/44.2 | 20.20 201130 |  | Riverside Construction Company, Inc. | Po Box 1146 | Riverside, Ca 92502 | 9516828308 | 9096659931 | 850 Via Lata Suite 104 | Colton, Ca 92324 | Contreras, Marco | 0 | 0 | 0 | 0 |  | Repair The Damaged Roadway | Repair The Damaged Roadway Dir'S Order Emergency F.A. | 0 | 0 | 0 | 54132 | 9485000 | 60129 | 2025-10-23 | 2025-10-17 | 2025-09-22 |  |  | 0 | 0 | 270 | 0
08 | 08-1T2804 | 1T2804 | 08-SBD-40-5.0/7 | 2020 201130 |  | Sully Miller Contracting Co | 135 S.State College Blvd #400 | Brea, Ca 92821 | 7145789600 | 9512328611 | 222 East Main St. Suite 208 | Barstow Ca 92311 | Nguyen, Khoa | 0 | 0 | 0 | 0 |  | Repair Damaged Roadway | Repair Damaged Roadway On Route 40 Due To Storm Damage Dir'S Emergency F.A. | 0 | 0 | 0 | 6675 | 2485000 | 60140 | 2026-04-15 | 2025-10-17 | 2025-09-04 |  |  | 0 | 0 | 70 | 0
08 | 08-1K4904 | 1K4904 | 08-SBD-40-105.1/105.9 |  | ACIM-0402- (070)E | Granite Construction Company | 580 W Beach Street | Watsonville Ca 95076 | 4426371608 | 9518408222 | 1044 E. Broadway St | Needles, Ca 92363 | Doan, Anthony | 2049806.51 | 26762.53 | 0 | 0 | 2025-10-20 | Building Work, Hma, And Temporary Portable | San Bernardino County About 36 Miles West Of Needles From 2.1 Miles To 1.3 Miles West Of Goffs Road Undercrossing | 37 | 53 | 24107887.28 | 45454108 | 45585370.53 | 56271 | 2026-05-29 | 2024-06-18 | 2024-05-28 |  |  | 230 | 0 | 630 | 0 |  | X
08 | 08-1N7804 | 1N7804 | 08-SBD-40-129.8/135.9 |  |  | Sully-Miller Contracting Company | 135 S. State College Blvd #40 | Brea Ca 92821 |  | 9518408222 | 1044 E Broadway St | Needles Ca 92363 | Anthony Doan | 0 | 0 | 0 | 0 |  | Rubberized Hma, Cold Plane Ac Pvmt And Rep | San Bernardino County From 2.9 Miles West To 3.2 Miles East Of Route 95 | 0 | 0 | 0 | 8773157.5 | 8773157.5 | 59635 | 2026-01-29 | 2025-07-14 | 2025-06-24 |  |  | 0 | 0 | 75 | 0
08 | 08-1M0404 | 1M0404 | 08-SBD-40-140.0/142.2 |  | HSIM-0402- (071)E | Interstate Civil Construction | 6025 Park Dr | Wrightwood Ca 92397 | 7602810188 | 9512328611 | 1044 East Broadway St. | Needles, Ca 92363 | Anthony Doan | 115537 | 0 | 0 | 0 | 2025-10-20 | Cold Plane Ac & Rhma, Vegetation Control ( | San Bernardino County In Needles From Fox Wash Overflow To L Street Undercrossing | 35 | 8 | 573802 | 6881495.3 | 6881495.3 | 59556 | 2025-12-15 | 2025-06-17 | 2025-06-06 |  |  | 21 | 0 | 60 | 0 |  | X
08 | 08-1J7204 | 1J7204 | 08-SBD-40-/S.8 |  | ACIM-0401- (092)E | Sully-Miller Contracting Company | 135 S. State College Blvd #40 | Brea Ca 92821 | 9145789600 | 9512328611 | 222 E. Main St. Suite #208 | Barstow, Ca 92311 | Nguyen, Khoa | 792568.48 | 0 | 0 | 0 | 2025-10-20 | Replace Ac Surfacing, Cold Plane Ac Paveme | San Bernardino County In And Near Barstow From 0.1 Mile West Of Roberta Street To Montara Road And From Route 15 To 0.4 Mileeast O | 56 | 80 | 32699393.26 | 39875395.4 | 40145034.9 | 57242 | 2026-04-01 | 2025-02-10 | 2025-01-17 |  |  | 135 | 0 | 240 | 0 |  | X
08 | 08-1P1204 | 1P1204 | 08-SBD-60-6.9/9.9 |  |  | American Civil Constructors West Coast, Llc | 2990 Bay Vista Court, Suite D | Benicia Ca 94510 | 7077468028 | 9518306837 | 119 N. Maple Suite A | Corona, Ca 92880 | Avila, Xavier | 480937 | 0 | 0 | 15000 | 2025-10-20 | Grind Exist Bridge Deck, Furnish & Place P | San Bernardino County In Ontario At Various Locations From Vineyard Avenue Undercrossing To Milliken Avenue Undercrossing | 87 | 68 | 2264597.52 | 3250000 | 3265000 | 59636 | 2025-10-30 | 2025-06-10 | 2025-05-15 |  |  | 52 | 0 | 60 | 0
08 | 08-1T2604 | 1T2604 | 08-SBD-62-307.0/31.3 | 20.20 201130 |  | Griffith Company | 3050 E. Birch Street | Brea, Ca 92821 |  | 9512326263 | 41601 Corporate Way | Palm Desert, Ca 92260 | Vu, Khoi | 0 | 0 | 0 | 0 |  | Repair Road,Paving,Railings,Embankments | Repair Roadway, Slope Paving, Bridge Railings, Brideg Embankments, Sidewalks, Drainage Systems Dir'S Order Emergency F.A. | 0 | 0 | 0 | 11025 | 2985000 | 60135 | 2025-12-26 | 2025-09-15 | 2025-08-26 |  |  | 0 | 0 | 80 | 0
08 | 08-1T3504 | 1T3504 | 08-SBD-62-540.0/79.5 | 20.20 201130 |  | Griffith Company | 3050 E. Birch Street | Brea, Ca 92821 |  | 9512326263 | 41601 Corporate Way | Palm Desert, Ca 92260 | Vu, Khoi | 0 | 0 | 0 | 0 |  | Repair The Damaged Roadway | Repair The Damaged Roadway Dir'S Order Emergency F.A. | 0 | 0 | 0 | 6930 | 1785000 | 60134 | 2025-12-11 | 2025-10-07 | 2025-09-22 |  |  | 0 | 0 | 50 | 0
08 | 08-1L2404 | 1L2404 | 08-SBD-95-57.2/64.5 |  |  | Sully-Miller Contracting Company | 135 S. State College Blvd #40 | Brea Ca 92821 | [5 empty] | 0 | 0 | 0 | 0 |  | Rhma (Gap Graded), Replace Ac Surfacing, A | San Bernardino County Near Needles From Route 40/95 Separation To 0.5 Mile North Of Goffs Road | 0 | 0 | 0 | 6949949 | 6949949 | 60141 |  | 2025-10-24 | 2025-10-09 |  |  | 0 | 0 | 80 | 0
08 | 08-1R7304 | 1R7304 | 08-SBD-138-18.9/19.5 | 20.20 201130 |  | Steve P. Rados Inc | 2002 E. Mcfadden Avenue # 200 | Santa Ana, Ca 92705 | 7148354612 | 9096014698 | 15255 Bear Valley Rd | Hesperia, Ca, 92345 | Roberto Flores | 0 | 0 | 0 | 0 |  | Install Drainage System | Install Drainage System To Mitigate Concentrated Flow Crossing The Highway During Rainfall And Flooding Dir'S Order Emergency F.A | 0 | 0 | 0 | 21990 | 21990 | 60098 | 2026-01-09 | 2025-09-03 | 2025-07-31 |  |  | 0 | 0 | 60 | 0
08 | 08-1N7504 | 1N7504 | 08-SBD-138-21.4/37.8 |  |  | Pavement Coatings Co. | 10240 San Sevaine Way | Jurupa Valley Ca 91752 | 9517035268 | 9518306845 | 850 S Via Lata #104 | Colton, Ca 92324 | Rahman, Md | 46341.9 | 0 | 0 | 0 | 2025-10-20 | Slurry Seal, Two-Component Paint Traffic S | San Bernardino County On Route 138 From Bolingbroke Road To Route 18 And On Route 189 From Route 18 To Route 173 | 91 | 92 | 3944112.21 | 4132980 | 4202429.65 | 56080 | 2025-10-27 | 2024-07-10 | 2024-06-12 |  |  | 64 | 0 | 70 | 0 |  | X
08 | 08-1T1004 | 1T1004 | 08-SBD-138-23.9/33.6 | 20.20 201130 |  | Baltazar Construction Inc | 236 E Arrow Hwy | Covina, Ca 91722 |  | 9518083255 | 15255 Bear Valley Rd | Hesperia, Ca 92345 | Canuti, Larry | 0 | 0 | 0 | 0 | 2025-10-20 | Repair Fire Damaged Roadway | Repair Fire Damaged Roadway Dir'S Order Emergency F.A. | 90 | 29 | 1159255.54 | 23475 | 3985000 | 59617 | 2025-10-31 | 2025-08-14 | 2025-07-02 |  |  | 76 | 0 | 60 | 24
08 | 08-1N7704 | 1N7704 | 08-SBD-173-/L7.7 |  |  | Calmex Engineering, Inc. | 2750 S. Lilac Ave | Bloomington Ca 92316 | 9095461311 | 9096654200 | 850 S. Via Lata, Suite 100A | Colton, Ca 92324 | Mineo, Nicholas | 631308.25 | 0 | 0 | 0 | 2025-08-29 | Cold Plane Ac Pvmt, Hma (Type A), And Repl | San Bernardino County In Hesperia From Route 138 To 0.5 Mile East Of Arrowhead Lake Road | 100 | 91 | 3074319.54 | 3260585 | 3260585 | 59355 | 2025-08-29 | 2025-05-13 | 2025-04-25 |  |  | 30 | 0 | 30 | 0 |  | X
08 | 08-1M7404 | 1M7404 | 08-SBD-210-1.2/1.6 |  | HSNH-P210- (018)E | Interstate Civil Construction | 6025 Park Dr | Wrightwood Ca 92397 | 7606621771 | 9512323784 | 10370 Commerce Center Dr.,#110 | Rancho Cucamonga, Ca 91730 | Nguyen, Vu | 2785.51 | 20792.18 | 0 | 0 | 2025-10-20 | Jpcp (Rsc), Rdwy Exc, Lcb Rapid Setting, & | Sanbernardino County In Upland From 0.3 Mile West To 0.1 Mile East Of Mountain Avenue Overcrossing | 17 | 92 | 2797618.54 | 2968222.1 | 3017372.1 | 58456 | 2026-08-12 | 2025-03-27 | 2025-03-12 |  |  | 49 | 0 | 290 | 0 |  | X
08 | 08-0N0604 | 0N0604 | 08-SBD-210-14.6/16.4 |  |  | John Semsen Landscaping Co., Inc. | 21161 Lyons Bald Mountain Roa | Sonora Ca 95370 | 2097434911 | 9512326478 | 937 S Via Lata Suite 650 | Colton, Ca | Benson, David | 131605 | 0 | 0 | 28500 | 2025-10-20 | Plastic Pipe (Supply Line), Roadside Clear | San Bernardino County In Fontana And Rialto From 0.3 Mile West Of Sierra Avenueovercrossing To Locust Avenue Overcrossing | 27 | 23 | 190405 | 840940 | 840940 | 59559 | 2029-01-23 | 2025-07-08 | 2025-06-16 |  | S | 23 | 0 | 835 | 0 |  | X
08 | 08-1P0604 | 1P0604 | 08-SBD-210-15.7/17.9 |  |  | John Semsen Landscaping Co., Inc. | 21161 Lyons Bald Mountain Roa | Sonora Ca 95370 | 2097436809 | 9512326478 | 937 S. Via Lata Ste 650 | Colton, Ca 92324 | Benson, David | 2025 | 0 | 0 | 0 | 2025-10-20 | Plastic Pipe (Supply Line), Wood Munch & M | San Bernardino County In Rialto From 0.2 Mile West Of Alder Avenue Overcrossing To Cactus Avenue Overcrossing | 0 | 0 | 888607.94 | 931690 | 941690 | 56233 | 2028-02-01 | 2024-07-17 | 2024-06-28 |  |  | 303 | 0 | 855 | 0 | X | X
08 | 08-1L9704 | 1L9704 | 08-SBD-210-23.1/24.7 |  |  | Diversified Landscape Co. | 21730 Bundy Canyon Road | Wildomar Ca 92595 | 9512451686 | 9095189727 | 937 S Via Lata Ste 650 | Colton, Ca 92324 | Mcnicoll, Joseph | 1887.2 | 0 | 0 | 0 | 2025-10-20 | Wood Mulch, Roadside Clearing, & Modifying | San Bernardino County In San Bernardino Onroute 210 From Route 210/259 Separation To0.5 Mile East Of North Waterman Overcrossing | 0 | 0 | 1310289.51 | 1294010.7 | 1432755.2 | 53424 | 2027-09-15 | 2023-07-24 | 2023-06-13 |  |  | 445 | 0 | 890 | 0 | X | X
08 | 08-1P6104 | 1P6104 | 08-SBD-210-/33.2 |  |  | Specialized Pavement Marking, Llc | 11095 Sw Industrial Way Suite | Tualatin Or 97062 | 5038850420 | 9096014046 | 10370 Commerce Center Dr Ste B | -110 Rancho Cucamonga Ca 91730 | Giang-Sinh Tran | 575225 | 0 | 0 | 5000 | 2025-10-08 | Rumble Strip (Ac Pavement And Concrete Pav | San Bernardino County From Los Angeles County Line To Route 10 | 72 | 87 | 928637 | 1027100 | 1057100 | 59619 | 2025-10-08 | 2025-07-08 | 2025-05-22 |  |  | 36 | 0 | 50 | 0 |  | X
08 | 08-1J2704 | 1J2704 | 08-SBD-247-/23 |  | ACST-P247- (015)E | Sully-Miller Contracting Company | 135 S. State College Blvd #40 | Brea Ca 92821 | 7149491771 | 9096014349 | 15255 Bear Valley Road | Hesperia, Ca 92345 | Saoud, Walid | 431724.52 | 0 | 0 | 0 | 2025-10-20 | Rubberized Hma, Hma (Type A), Cold Plane A | San Bernardino County In Yucca Valley Fromroute 62 To 0.4 Mile West Of Gin Road | 85 | 91 | 20509411.89 | 21990603.4 | 22179241.8 | 57388 | 2025-11-14 | 2025-03-06 | 2025-01-31 |  |  | 106 | 0 | 125 | 0 |  | X
08 | 08-1T2704 | 1T2704 | 08-SBD-247-/0 | 2020 201103 |  | Sully-Miller Contracting Co. | 135 S State College Blvd #400 | Brea Ca 92821 |  | 9096014349 | 15255 Bear Valley Road | Hesperia Ca 92345 | Walid Saoud | 0 | 0 | 0 | 0 |  | Repair Roadway Pavement And Embankment | Repair Roadway Pavement And Embankment Dir'S Order Emergency F.A. | 0 | 0 | 0 | 5340 | 1985000 | 60138 | 2025-12-31 | 2025-10-01 | 2025-08-29 |  |  | 0 | 0 | 60 | 0
08 | 08-1R6404 | 1R6404 | 08-SBD-330-29.6/43.9 | 20.20.201130 |  | Riverside Construction Company, Inc. | 4225 Garner Road | Riverside, Ca 92501 |  | 9512326415 | 850 S Via Lata Unit 104 | Colton, Ca 92324 | Wang, Tsung | 0 | 320420.97 | 0 | 0 | 2025-09-20 | Damage Repair Cause By Atmospheric Storm | Damage Repair Resulted From An Atmospheric River Storm From February 12 To 14, 2025. Dir'S Order Emergency F.A. | 100 | 93 | 6112344.25 | 23361 | 6585000 | 57617 | 2025-08-21 | 2025-02-27 | 2025-02-27 | 2025-09-24 |  | 122 | 0 | 50 | 0 |  | X
08 | 08-1R3304 | 1R3304 | 08-SBD-330-296.0/43.9 | 20.20 201130 |  | Riverside Construction Co. | 4225 Garner Road | Riverside, Ca 92501 |  | 9512326415 | 850 S Via Lata Unit 104 | Colton, Ca 92324 | Wang, Tsung | 0 | 23804.5 | 0 | 0 | 2025-09-20 | Repair Damages Caused By Line Fire | Repair Damages From Line Fire From Highland Ave Oc Bridge To Sr-18 /Sr-330 Junction Dir'S Order Emergency F.A. | 100 | 100 | 14161455.54 | 29922 | 14185000 | 56684 | 2025-08-21 | 2024-11-14 | 2024-09-16 | 2025-09-29 |  | 217 | 0 | 60 | 0 |  | X
08 | 08-1G6404 | 1G6404 | 08-SBD-395-4.0/49 |  | ACNH-P395- (351)E | Sully-Miller Contracting Company | 135 S. State College Blvd #40 | Brea Ca 92821 | 7145789600 | 9096014717 | 15255 Bear Valley Road | Hesperia, Ca 92345 | Loza, Shaun | 18750 | 61823.03 | 0 | 0 | 2025-09-20 | Replace Asphalt Concrete Surfacing, Cold P | San Bernardino County At Various Locationsfrom Route 15/395 Separation To 3.1 Miles North Of Route 58/395 Separation | 100 | 95 | 35806915 | 35935000 | 36660302.64 | 53964 | 2025-09-20 | 2023-11-28 | 2023-10-25 |  |  | 120 | 0 | 120 | 0 |  | X
08 | 08-1R0404 | 1R0404 | 08-VAR--/0 |  |  | Techbleed | 53 Glenflow Ct. | Glendale Ca 91206 | [5 empty] | 0 | 0 | 0 | 0 |  | Modifying Traffic Monitoring Stations. | Riverside And San Bernardino Counties At Various Locations | 0 | 0 | 0 | 372859 | 372859 | 59620 |  | 2025-07-30 | 2025-06-13 |  |  | 0 | 0 | 40 | 0
08 | 08-1P0904 | 1P0904 | 08-VAR--/0 |  |  | Myers & Sons Construction, Llc | 45 Morrison Ave | Sacramento Ca 95838 | 9162839950 | 9518306837 | 119 N. Maple St. | Corona, Ca 92880 | Avila, Xavier | 344348.27 | 0 | 0 | 0 | 2025-10-20 | Furnish And Place Polyester Concrete Overl | Riverside County At Various Locations | 91 | 99 | 3040287.78 | 2845843 | 2845843 | 59341 | 2025-10-31 | 2025-05-23 | 2025-05-09 |  |  | 41 | 0 | 45 | 0 |  | X
08 | 08-1N4704 | 1N4704 | 08-VAR--/0 |  |  | Select Electric, Inc. | 2790 Business Park Drive | Vista Ca 92081 | 6199193869 | 2134349325 | 464 W 4Th Street | San Bernardino, Ca 92401 | Yaacoub, Lawrance | 99710.6 | 0 | 0 | 0 | 2025-09-20 | Modify Fo Cable, Camera & Roadside Weather | Riverside And San Bernardino Counties At Various Locations | 84 | 85 | 2371159.26 | 2690689 | 2802642.49 | 56435 | 2026-02-20 | 2024-08-07 | 2024-06-26 |  | S | 126 | 0 | 150 | 0 |  | X
08 | 08-1J8504 | 1J8504 | 08-VAR--/0 |  | ACST-X071- (077)E | Powell Constructors Inc | 8555 Banana Avenue | Fontana Ca 92335 | 9093568880 | 9512124988 | 850 S. Via Lata Suite 104 | Colton, Ca 92324 | Elzawy, George | 476543.9 | 0 | 0 | 0 | 2025-10-20 | Furnish Sign Structure And Install Changea | San Bernardino County At Various Locations | 48 | 25 | 3519306.18 | 14057592 | 14178561.2 | 56321 | 2026-03-10 | 2024-09-10 | 2024-08-29 |  |  | 87 | 0 | 180 | 0 |  | X
08 | 08-1J8604 | 1J8604 | 08-VAR--/0 |  | ACNH-X071- (076)E | Peterson-Chase General Engineering Construction, Inc. | 16351 Construction Circle Wes | Irvine Ca 92606 | 9492926906 | 2134349325 | 464 W 4Th Street | San Bernardino, Ca 92401 | Yaacoub, Lawrance | 356050 | 0 | 0 | 0 | 2025-10-20 | Modifying Cms Systems And Furnish Sign Str | San Bernardino County At Various Locations | 54 | 26 | 3644860.31 | 13973863 | 14103863 | 56123 | 2026-03-25 | 2024-06-05 | 2024-05-01 |  |  | 125 | 0 | 230 | 0 |  | X
08 | 08-1H9924 | 1H9924 | 08-VAR--/0 |  | ACST-000C- (552)E | Gba Engineering, Inc. | 18543 Yorba Linda Blvd #394 | Yorba Linda Ca 92886 | 7145106700 | 9096654200 | 850 S. Via Lata, Suite 100A | Colton, Ca 92324 | Mineo, Nicholas | 198510.39 | 0 | 0 | 0 | 2025-10-20 | Install Roadside Sign-One Post, & Furnish | Riverside And San Bernardino Counties At Various Locations | 100 | 97 | 2112922.59 | 2135964 | 2167155.59 | 56251 | 2026-02-02 | 2024-06-05 | 2024-04-15 |  |  | 110 | 0 | 110 | 0 |  | X
08 | 08-1P8904 | 1P8904 | 08-VAR--/0 |  |  | Kanaan Construction, Inc. | 5040 Heintz Street | Baldwin Park Ca 91706 | 6263345775 | 2134349325 | 464 W 4Th Street | San Bernardino, Ca 92401 | Yaacoub, Lawrance | 87000 | 0 | 0 | 0 | 2025-10-20 | Modifying Traffic Monitoring Stations And | Riverside And San Bernardino Counties At Various Locations | 38 | 49 | 440357.44 | 842080 | 892080 | 59455 | 2025-12-12 | 2025-06-03 | 2025-05-07 |  | S | 23 | 0 | 60 | 0 |  | X
08 | 08-1H8804 | 1H8804 | 08-VAR--/0 |  |  | Indus General Inc. | 1851 Heritage Lane Ste 129 | Sacramento Ca 95821 |  | 9512327608 | 119 N. Maple St. Ste A | Corona, Ca 92880 | Sostrom, Denise | 127704.35 | 0 | 0 | 0 | 2025-05-20 | Camera Systems, Rolled Erosion Control Pro | Riverside County At Various Locations | 63 | 46 | 272012.04 | 593973.36 | 489207.76 | 56535 | 2025-11-30 | 2024-10-01 | 2024-06-27 |  | S | 50 | 0 | 80 | 0 |  | X
08 | 08-1J8404 | 1J8404 | 08-VAR--/0 |  | ACST-000C- (557)E | Peterson-Chase General Engineering Construction, Inc. | 16351 Construction Circle Wes | Irvine Ca 92606 | 9492520441 | 9512328611 | 222 E Main St Ste#208 | Barstow, Ca 92311 | Nguyen, Khoa | 1149539.25 | 60782.67 | 0 | 0 | 2025-10-20 | Install Cms System, Furnish Sign Structure | San Bernardino County At Various Locations | 70 | 53 | 6821363.22 | 12467540 | 12587961 | 56232 | 2026-01-14 | 2024-08-14 | 2024-06-28 |  |  | 126 | 0 | 180 | 0 |  | X
08 | 08-1P6604 | 1P6604 | 08-VAR--/0 |  |  | Alfaro Communications Construction, Inc. | 15614 S. Atlantic Avenue | Compton Ca 90221 | 3106698949 | 9096654302 | 850 S. Via Lata 100A | Colton, Ca 92324 | Shbaita, Jason | 0 | 0 | 0 | 0 |  | Wrong Way Flashing Sign Systems And Roadsi | Riverside And San Bernardino Counties At Various Locations | 0 | 0 | 0 | 708950.59 | 708950.59 | 59555 | 2026-02-28 | 2025-06-09 | 2025-05-27 |  | S | 0 | 0 | 60 | 0
08 | 08-1E1404 | 1E1404 | 08-VAR--/0 |  | SSTG-S079- (048)E | Beador Construction Company, Inc. | 2900 Bristol Street Ste D204 | Costa Mesa, Ca 92626 | 9516747352 | 9512323777 | 9225 Stellar Court Suite B | Corona, Ca 92883 | Guglielmana, Thomas | 468555.09 | 1571.3 | 0 | 0 | 2025-10-20 | Mgs, Concrete Barrier And Vegetation Contr | Riverside County At Various Locations | 72 | 86 | 7126578.03 | 7481300 | 7995736.84 | 56063 | 2026-02-06 | 2024-06-05 | 2024-04-25 |  |  | 194 | 0 | 270 | 0 |  | X
08 | 08-1H9914 | 1H9914 | 08-VAR--/0 |  | SSTG-000C- (554)E | Peterson-Chase General Engineering Construction, Inc. | 16351 Construction Circle Wes | Irvine Ca 92606 | 9492520441 | 9518306837 | 119 N Maple St Ste A | Corona, Ca 92880 | Avila, Xavier | 0 | 12535.82 | 0 | 0 | 2025-10-20 | Install Roadside Sign-One Post, Furnish Si | Riverside And San Bernardino Counties At Various Locations | 100 | 92 | 3391073.86 | 3618670 | 3668670 | 55144 | 2025-10-30 | 2024-01-23 | 2024-01-03 |  |  | 229 | 0 | 230 | 0 |  | X
09 | 09-374704 | 374704 | 09-INY-168-17.6/18.3 |  | ACST-X027- (012)E | Papich Construction Company, Inc. | 398 Sunrise Terrace | Arroyo Grande Ca 93420 | 8059044664 | 6194332514 | 500 S Main Street, Bishop Ca |  | John Gentry | 509334.81 | 89777.54 | 0 | 0 | 2025-10-15 | Hma (Type A), Minor Concrete, And Lighting | Inyo County In And Near Bishop On Route 395 From 0.1 Mile South Of Jay Street To Barlow Lane And On Route 168 From Pioneer Lane To | 31 | 26 | 5833643.21 | 22608806 | 23088925.63 | 57380 | 2026-04-20 | 2025-03-18 | 2025-02-21 |  |  | 66 | 0 | 210 | 0 |  | X
09 | 09-213404 | 213404 | 09-INY-395-29.2/41.8 | HE14 | ACNH-P395- (348)E | Fisher Sand & Gravel Co | 1302 W. Drivers Way | Tempe Az 85284 | 4807301033 | 7609203460 | 500 South Main Street | Bishop, Ca 93514 | Damon Cherenzia | 305454.2 | 648784.37 | 560984.07 | 0 | 2025-10-15 | Construct 4 Lane Expressway | In Inyo County Near Olancha And Cartago From 1.4 Miles South Of Los Angeles Aqueduct Bridge To 0.2 Mile South Of Ash Creek Bridge | 97 | 93 | 94250202.87 | 69696969.69 | 99950803.63 | 41974 | 2025-11-19 | 2021-11-23 | 2021-10-22 |  |  | 835 | 0 | 500 | 359 |  | X
09 | 09-390204 | 390204 | 09-INY-395-57.4/0 |  |  | Interstate Civil Construction | 6025 Park Dr | Wrightwood Ca 92397 | [5 empty] | 0 | 0 | 0 | 0 |  | Construct Minor Concrete And Install Hybri | Inyo County At Lone Pine At East Muir Street | 0 | 0 | 0 | 668415.1 | 668415.1 | 59198 |  | 2025-07-02 | 2025-06-16 |  |  | 0 | 0 | 40 | 0
09 | 09-379104 | 379104 | 09-INY-395-91.6/100.8 |  | ACNH-P395- (354)E | Road And Highway Builders, Llc. | 950 E Mustang Rd | Sparks Nv 89434 | 7758527283 | 7609203406 | 500 S. Main St. | Bishop, Ca 93514 | Adam Zumstein | 3256655.42 | 0 | 0 | 0 | 2025-10-20 | Construct Hma, Curb Ramps, And Electrical | Inyo County At And Near Big Pine From 0.1 Mile South Of Elna Road To South Junction Route 168 | 48 | 69 | 20765529.18 | 28888888 | 29703154 | 57381 | 2026-03-19 | 2025-03-21 | 2025-02-20 |  |  | 93 | 0 | 190 | 3 |  | X
09 | 09-366804 | 366804 | 09-INY-395-117.3/117.9 |  | ACNH-P395- (355)E | Papich Contruction Company Inc. | 398 Sunrise Terrace | Arroyo Grande, Ca 93420 |  | 7609203406 | 500 S. Main St. | Bishop, Ca 93514 | Adam Zumstein | 699360.92 | 26394.2 | 0 | 0 | 2025-10-20 | Construct Sidewalks, Retaining Walls, Brid | Inyo County Near Bishop From 0.1 Mile Eastof See Vee Lane To Barlow Lane | 36 | 26 | 3264259.78 | 12864995 | 12811695.2 | 58055 | 2026-04-30 | 2025-05-07 | 2025-04-03 |  |  | 71 | 0 | 200 | 0 |  | X
09 | 09-398404 | 398404 | 09-INY-395-122.0/129.5 |  |  | American Pavement Systems, Inc. | 1012 11Th Street | Modesto Ca 95354 | 2096786204 | 7609202460 | 500 S Main Street | Bishop Ca 93514 | Garrett Rottner | 2218690.34 | 0 | 0 | 0 | 2025-10-14 | Asphaltic Emulsion (Fog Seal Coat) & Preco | Inyo County In And Near Mesa From 0.4 Milesouth Of Pleasant Valley Dam Road To 1.3 Miles North Of Gorge Road | 100 | 100 | 2454372.94 | 2360955 | 2362055 | 58597 | 2025-10-14 | 2025-06-09 | 2025-05-14 | 2025-10-08 |  | 30 | 0 | 30 | 0 |  | X
09 | 09-379504 | 379504 | 09-INY-5709-/0 |  |  | Fec Future Contractors And Engineers Inc | 184 Technology Drive, Suite 2 | Irvine Ca 92618 | 9493289758 | 7609202475 | 500 South Main Street | Bishop, Ca 93514 | George Elzawy | 33066 | 0 | 0 | 0 | 2025-09-16 | Construct Building And Place Hma. | Inyo County At Independence At The Independence Maintenance Station At 665 North Edwards Street | 100 | 98 | 4494024.08 | 4535550 | 4574212.11 | 56026 | 2025-09-26 | 2024-06-26 | 2024-05-17 | 2025-10-28 |  | 185 | 0 | 185 | 0 |  | X
09 | 09-367504 | 367504 | 09-KER-5756-/92 | HA12 |  | Bowe Contractors Inc. | 609 Bailey Ct | Tehachapi Ca 93561 | 6619400899 | 7609373243 | 1858 Rosamond Blvd. | Rosamond, Ca 93560 | Hin Hartanto | 14020 | 0 | 0 | 0 | 2025-10-16 | Building Work, Hot Mix Asphalt (Type A). | Kern County In Tehachapi At The Tehachapi Highway Maintenance Station At 305 Industrial Parkway | 100 | 100 | 17338795.61 | 16327378.86 | 17561546.24 | 49924 | 2025-10-16 | 2023-06-05 | 2023-03-23 | 2025-10-16 |  | 300 | 0 | 665 | 0 |  | X
09 | 09-404304 | 404304 | 09-MNO-120-32.1/35 |  |  | Papich Construction Company, Inc. | 398 Sunrise Terrace | Arroyo Grande Ca 93420 |  | 7609378955 | 500 S Main St | Bishop Ca 93514 | David Carruba | 317106.36 | 0 | 0 | 0 | 2025-09-04 | Cold In-Place Recycle Existing Pavement An | Mono County Near Benton From 0.5 Mile Eastto 3.4 Miles East Of Baxter'S Road And From 2.0 Miles West Of Black Lake Road To Black L | 85 | 99 | 3681517.64 | 3493943 | 3493943 | 58316 | 2025-09-04 | 2025-05-23 | 2025-04-28 |  |  | 34 | 0 | 40 | 0 |  | X
09 | 09-378804 | 378804 | 09-MNO-395-9.8/12.6 |  | ACNH-P395- (353)E | Hat Creek Construction & Materials, Inc. | 24339 State Hwy 89 N. | Burney Ca 96013 | 5303355501 | 7609378955 | 500 S Main Street | Bishop, Ca 93514 | David Carruba | 140844.18 | 0 | 0 | 0 | 2025-10-20 | Place Hma And Asphalt Base, Recycle Paveme | Mono County Near Tom'S Place From 0.5 Milenorth Of Lower Rock Creek Road To 1.3 Miles South Of South Landing Overcrossing | 95 | 95 | 13021135.92 | 13528809 | 13498609 | 56584 | 2026-05-29 | 2024-10-30 | 2024-08-29 |  |  | 90 | 0 | 95 | 0 |  | X
09 | 09-398504 | 398504 | 09-MNO-395-44.6/50.7 |  |  | American Pavement Systems, Inc. | 1012 11Th Street | Modesto Ca 95354 | 2095222277 | 7609203613 | 500 S. Main St. | Bishop, Ca 93514 | Scott Eagan | 436227.8 | 1650 | 0 | 0 | 2025-10-09 | Asphaltic Emulsion (Fog Seal Coat) & Preco | Mono County Near Lee Vining From 0.3 Mile South Of Old West Portal Road To 0.2 Mile South Of Utility Road | 100 | 100 | 1968803.3 | 1997055 | 1998705 | 57915 | 2025-10-09 | 2025-04-25 | 2025-04-10 | 2025-10-09 |  | 25 | 0 | 25 | 0 |  | X
09 | 09-368004 | 368004 | 09-MNO-395-91.6/93.4 |  | HSNH-P395- (352)E | Papich Construction Company, Inc. | 398 Sunrise Terrace | Arroyo Grande Ca 93420 |  | 7609378955 | 500 South Main Street |  | David Carruba | 43548 | 35909.21 | 69197.93 | 0 | 2025-10-20 | Hot Mix Asphalt (Type A), Rail Element Wal | Mono County About 16 Miles North Of Bridgeport From Burcham Flat Road To 0.3 Mile South Of Route 108 | 43 | 97 | 15801441.35 | 15297000 | 16665911.57 | 55683 | 2025-10-17 | 2024-03-20 | 2024-02-29 |  |  | 175 | 0 | 410 | 0 |  | X
10 | 10-0Q2104 | 0Q2104 | 10-AMA-88-5.5/14.3 |  | ACNH-P088- (074)E | Bay Cities Paving & Grading, Inc. | 1450 Civic Ct Bldg B #400 | Concord Ca 94520 |  | 2092793514 | 19596 Mono Way | Sonora Ca. 95370 | Jonathan Ngai | 253985.34 | 35477.96 | 142529.05 | 0 | 2025-10-20 | Repair Failed Pavement And Resurface Exist | Amador County Near Martell From 0.7 Mile West Of Ione-Buena Vista Road To 0.2 Mile East Of Kennedy Flat Road | 98 | 90 | 7498893.35 | 7919500 | 8306316.99 | 57076 | 2025-10-23 | 2024-12-18 | 2024-11-25 |  |  | 122 | 0 | 125 | 0 |  | X
10 | 10-0K1304 | 0K1304 | 10-AMA-88-54.7/60.8 |  |  | Wylatti Resource Management, Inc. | 23601 Cemetery Lane | Covelo Ca 95428 |  | 2094793608 | 850 South Guild Ave. Suite 107 | Lodi Ca 95240 | Iqbal Aulakh | 154107.67 | 0 | 0 | 0 | 2025-09-20 | Remove And Replace Drainage Pipes And Resu | Amador County About 40 Miles East Of Jackson At Various Locations From Foster Meadow Road To 0.9 Mile East Of Shot Rock Vista Poin | 97 | 95 | 2040399.93 | 2149409.54 | 2172409.54 | 57677 | 2025-09-23 | 2024-12-27 | 2024-12-04 | 2025-10-27 |  | 58 | 0 | 60 | 0 |  | X
10 | 10-1H5004 | 1H5004 | 10-CAL-4-15.9/16.3 | HA21 |  | Viking Construction Company | 11315 Sunrise Gold Circle St | Rancho Cordova Ca 95742 | 9168525530 | 5105017727 | 850 South Guild Ave. Suite 107 | Lodi Ca 95240 | Elaine Yip | 781459.65 | 0 | 0 | 21250 | 2025-10-20 | Bridge Replacement | .Near Angels Camp, At West Branch Cherokee Creek Bridge No. 30-0036. Cherokee Creek Bridge | 73 | 61 | 2734627.53 | 4398785 | 4487333.38 | 49624 | 2025-12-09 | 2022-12-01 | 2022-11-18 |  |  | 87 | 0 | 120 | 0 |  | X
10 | 10-1S6504 | 1S6504 | 10-CAL-12-2.9/9.9 |  |  | Vss International, Inc. | 3785 Channel Drive | West Sacramento Ca 95691 |  | 2096078786 | 952 Goodwin Drive | Ripon, Ca 95366 | Magdy Farid | 537513.95 | 0 | 0 | 6347.89 | 2025-10-20 | Place Slurry Seal And Pavement Markings. | Calaveras County At And Near Burson And Valley Springs From 0.5 Mile East Of Southworth Road To 0.1 Mile West Of Chestnut Street | 88 | 76 | 929555.38 | 1222120 | 1222120 | 58675 | 2025-10-28 | 2025-06-12 | 2025-05-28 |  |  | 44 | 0 | 50 | 0 |  | X
10 | 10-1J8204 | 1J8204 | 10-CAL-12-9.9/10.3 |  | HSST-S012- (001)E | George Reed, Inc. | P.O. Box 4760 | Modesto Ca 95352 | 2095230734 | 2094793608 | 850 South Guild Ave. Suite 107 | Lodica 95240 | Iqbal Aulakh | 825815.5 | 0 | 0 | 0 | 2025-10-20 | Construct Intersection Signal, Curb Ramps, | Calaveras County In And Near Valley Springs From 0.1 Mile East Of Chestnut Street To 0.1 Mile West Of Lime Creek Road | 39 | 44 | 1640193 | 3682280 | 3682280 | 57715 | 2026-01-23 | 2025-04-15 | 2025-03-24 |  |  | 41 | 0 | 105 | 0 |  | X
10 | 10-0X7404 | 0X7404 | 10-CAL-12-17.1/17.5 |  | BFST-S012- (002)E | Steelhead Constructors Jv | 2940 Innsbruck Drive | Redding Ca 96003 | [5 empty] | 0 | 0 | 0 | 0 |  | Bridge Replacement. | Calaveras County Near San Andreas From 0.2Mile West Of North Fork Calaveras River Bridge To 0.2 Mile East Of North Calaverasriver | 0 | 0 | 0 | 12328635 | 12328635 | 60076 |  | 2025-09-22 | 2025-09-03 |  |  | 0 | 0 | 440 | 0
10 | 10-0V4804 | 0V4804 | 10-CAL-26-21.8/30.3 |  | ACST-S026- (032)E | Viking Construction Company, Inc. | 11315 Sunrise Gold Circle Sui | Rancho Cordova Ca 95742 |  | 2092793514 | 19596 Mono Way | Sonora Ca 95370 | Jonathan Ngai | 531730.43 | 13659.49 | 0 | 0 | 2025-10-20 | Slope Stabilization And Construct Retainin | Calaveras County Near Mokelumne Hill At Various Locations From 3.6 Miles East Of Route 49 To 0.9 Mile West Of Woodhouse Mine Road | 77 | 70 | 5290032.35 | 7197400 | 7518010 | 56523 | 2025-12-22 | 2024-10-08 | 2024-09-09 |  |  | 138 | 0 | 180 | 0 |  | X
10 | 10-1H7004 | 1H7004 | 10-CAL-49-7.5/9.4 |  | ACNH-P049- (192)E | George Reed, Inc. | 140 Empire Avenue | Modesto Ca 95354 |  | 5593412018 | 850 S Guild Ave Sute 107 | Lodi, Ca 95240 | Troy Scheiber | 285265 | 45796.43 | 0 | 25000 | 2025-10-20 | Construct Curbs Ramps, Sidewalks, Driveway | Calaveras County In Angels Camp From Bret Harte Road To Copello Drive | 2 | 12 | 868282.53 | 7061213 | 7191213 | 58956 | 2025-07-13 | 2025-06-10 | 2025-05-09 |  |  | 20 | 0 | 985 | 0 |  | X
10 | 10-1C7904 | 1C7904 | 10-MER-5-.5/.8 | HA26 | CIMG-005 -5(156)E | Walsh Construction Company Ii, Llc | 1390 Willow Pass Rd., Suite 9 | Concord Ca 94520 | 9256271700 | 5599775907 | 952 Goodwin Dr. | Ripon Ca 95366 | Zubair Anwar | 805980 | 0 | 0 | 0 | 2025-06-20 | Replace Safety Roadside Rest Area | In Merced County, On Interstate 5, South Of Los Banos, At The John Erreca Srra | 100 | 100 | 32210981.69 | 27859941.4 | 31140241.16 | 42029 | 2025-06-30 | 2022-01-06 | 2021-12-17 |  |  | 372 | 0 | 350 | 0 |  | X
10 | 10-1G2504 | 1G2504 | 10-MER-33-.6/1.5 | HB71 | ACST-X047- (015)E | Dirt Dynasty, Inc. | 4110 Meadow Oaks Dr. | Valley Springs Ca 95252 |  | 5308703106 | 530 W.16Th St Suite#D | Merced Ca 95340 | Jagga Dhami | 167009 | 0 | 0 | 0 | 2025-10-20 | Construct Curb Ramp, Sidewalk, And Drivewa | Merced County In And Near Dos Palos On Route 33 From 0.3 Mile South Of Valeria Street To 0.1 Mile North Of Santos Street And In Gu | 49 | 98 | 5166981.01 | 4508592.5 | 5361788.82 | 55526 | 2025-11-30 | 2023-12-27 | 2023-12-04 |  |  | 180 | 0 | 180 | 186 |  | X
10 | 10-1K0904 | 1K0904 | 10-MER-99-3.3/6.9 |  |  | Empire Landscaping Inc. | 26945 Country Road 97D | Davis Ca 95616 | 5304003943 | 5308703106 | 530 W. 16Th St, Suite D | Merced, Ca 95340 | Jagga Dhami | 8000 | 0 | 0 | 0 | 2025-10-20 | Plant Establishment And Install Decorative | Merced County Near Merced At Various Locations From Plainsburg Road Overcrossing To Le Grand Road Overcrossing | 100 | 60 | 605353.88 | 975210 | 1047420.07 | 50624 | 2029-05-03 | 2023-06-26 | 2023-05-30 |  |  | 371 | 0 | 1385 | 0
10 | 10-3A7214 | 3A7214 | 10-MER-99-19.5/20.7 | HA22 |  | Wabo Landscape & Construction, Inc. | 726 Alfred Nobel Drive | Hercules Ca 94547 | 5107419226 | 5308703106 | 530 W. 16Th St, Suit | Merced Ca 95430 | Jagga Dhami | 990 | 0 | 0 | 0 | 2025-10-20 | Highway Planting And Irrigation | In And Near Atwater, At Atwater - Merced Expressway Interchange. | 0 | 0 | 1337888 | 1399949 | 1386254.92 | 45906 | 2025-11-13 | 2022-12-21 | 2022-11-15 |  |  | 631 | 0 | 900 | 0 | X | X
10 | 10-1K4304 | 1K4304 | 10-MER-165-16.5/26.8 |  |  | Cal Valley Construction, Inc. | 5125 N Gates Ave Ste 102 | Fresno Ca 93722 |  | 5308703106 | 530 W 16Th Street Suite D | Merced, Ca 95340 | Jagga Dhami | 314383.95 | 0 | 0 | 0 | 2025-10-20 | Rhma (Gap Graded), Hma And Cold Plane Asph | Merced County Near Los Banos From 1.5 Miles North Of Wolfsen Road To 0.1 Mile South Of Route 140 | 100 | 100 | 6165051.21 | 5999312 | 5955344.2 | 56155 | 2025-10-28 | 2024-07-31 | 2024-06-26 | 2025-10-22 |  | 90 | 0 | 90 | 0 |  | X
10 | 10-1S6404 | 1S6404 | 10-MER-165-/7 |  |  | A. Teichert & Son, Inc. Dba Teichert Construction | 3500 American River Dr | Sacramento Ca 95864 |  | 5308703106 | 530 W. 16Th Street Suite D | Merced, Ca 95340 | Jagga Dhami | 2214903.1 | 0 | 0 | 160000 | 2025-10-20 | Resurface Pavement With Rhma And Hma. | Merced County In And Near Los Banos From 0.3 Mile South Of Pole Line Road To 0.2 Mile South Of Mason Road And From 0.1 Mile South | 51 | 51 | 4060084.05 | 8017200 | 7895700 | 59735 | 2025-12-01 | 2025-06-03 | 2025-05-13 |  |  | 43 | 0 | 85 | 0 |  | X
10 | 10-0P9244 | 0P9244 | 10-MPA-140-42.0/42.7 |  | ACST-43M9- (004)E | Myers And Sons/R L Wadsworth Joint Venture | 45 Morrison Avenue | Sacramento Ca 95838 |  | 2094709468 | 19596 Mono Way | Sonora Ca 95370 | Junhao Liu | 0 | 0 | 0 | 0 |  | Construct Avalanche Shed. | Mariposa County About 8.0 Miles West Of Elportal From 1.2 Miles West Of South Fork Merced River Bridge To 0.5 Mile West Of South F | 0 | 0 | 0 | 343657293.94 | 343657293.94 | 60101 | 2030-12-31 | 2025-09-05 | 2025-08-22 |  |  | 0 | 0 | 1500 | 0
10 | 10-1S5204 | 1S5204 | 10-MPA-140-293.0/29.3 | 20.202011130 |  | Ranch Fence Inc. | 5071 Cole Road | Mariposa Ca 95338 |  | 2092793514 | 19596 Mono Way | Sonora Ca 95370 | Jonathan Ngai | 0 | 0 | 0 | 0 | 2025-10-20 | Replace Fence, Gate And Gate Control | Replace Fence, Gate And Gate Control Ama And Mpa County 10A2717 Dirs Efa 10A2717 | 84 | 100 | 1990995 | 10005 | 1986000 | 56986 | 2025-11-24 | 2024-12-31 | 2024-12-31 | 2025-10-22 |  | 126 | 0 | 150 | 0 |  | X
10 | 10-1R9904 | 1R9904 | 10-SJ-4-.5/.5 | 20.20.201130 |  | Golden State Bridge Inc. | 3701 Mallard Dr. | Benicia, Ca. 94510 |  | 2094794053 | 3663 Arch Road,Suite 500 | Stockton, Ca. 95215 | Chris Hanson | 0 | 0 | 0 | 0 |  | Replace Submarine Cable & Maritime Beacons | Replace Submarine Cable Maritime Navigation Beacons @ Little Potato Slough Bridge. Co.Sj, Rte 4,12, Pm 0.51, 5.00 Dirs Efa 10A2602 | 0 | 0 | 0 | 4875 | 960000 | 56909 | 2026-06-01 | 2023-10-09 | 2023-08-11 |  |  | 0 | 0 | 15 | 0
10 | 10-1F1804 | 1F1804 | 10-SJ-4-16.0/19.4 |  | ACNH-P004- (162)E | Viking Construction Company, Inc. | 11315 Sunrise Gold Circle Sui | Rancho Cordova Ca 95742 |  | 5593412018 | 850 So Guild Ave Suite 107 | Lodi, Ca 95240 | Troy Scheiber | 623916 | 5848.83 | 1590 | 0 | 2025-10-20 | Bridge Work, Concrete Barrier, And Install | San Joaquin County In Stockton At Various Locations From 0.3 Mile East Of Route 4/5 Separation To 0.4 Mile West Of Route 4/99 Sepa | 80 | 73 | 19875578.76 | 26248389.25 | 26984021.66 | 54604 | 2026-02-23 | 2023-10-05 | 2023-09-20 |  |  | 327 | 0 | 380 | 29 |  | X
10 | 10-1L2804 | 1L2804 | 10-SJ-4-20.5/20.8 |  | HSNH-P004- (165)E | O.C. Jones & Sons, Inc. | 1520 Fourth Street | Berkeley Ca 94710 | 5108093437 | 2094835812 | 3663 Arch Road, Suite 500 | Stockton, Ca 95215 | David Abledu | 96831 | 0 | 0 | 31250 | 2025-10-20 | Install Left-Turn Channelization. | San Joaquin County Near Stockton From 0.2 Mile West Of Walker Lane To 0.1 Mile East Of Walker Lane | 10 | 20 | 268713.6 | 1333591.5 | 1333591.5 | 57236 | 2025-11-14 | 2025-02-27 | 2025-01-28 |  |  | 6 | 0 | 60 | 0 |  | X
10 | 10-1R8804 | 1R8804 | 10-SJ-4-141.0/14.1 | 20.20.201130 |  | Myers & Sons Construction Llc. | 45 Morrison Avenue. | Sacramento, Ca. 95838 |  | 2096078786 | 952 Goodwin Dr. | Ripon, Ca.95366 | Magdy Farid | 0 | 0 | 0 | 0 | 2025-06-09 | Repair Garwood Bridgewith Emergency Work.0 | Repair Garwood Bridge (29-0050) Damaged By Firein Sj County. Ct10-1R8804,10230000243 Dirs Efa 10A2592 | 100 | 60 | 587285.17 | 4950 | 975000 | 56192 | 2025-11-15 | 2023-09-18 | 2023-07-14 |  |  | 88 | 0 | 15 | 0
10 | 10-1H3604 | 1H3604 | 10-SJ-4-/0 |  |  | Disney Construction, Inc. | 533 Airport Blvd., Suite 120 | Burlingame Ca 94010 | [5 empty] | 0 | 0 | 0 | 0 |  | Paint Bridge Structural Steel And Place Po | San Joaquin County Near Discovery Bay At Old River Bridge | 0 | 0 | 0 | 5193333 | 5193333 | 60078 |  | 2025-09-16 | 2025-08-27 |  |  | 0 | 0 | 220 | 0
10 | 10-1R7004 | 1R7004 | 10-SJ-5-.3/3.5 |  |  | Myers & Sons Construction, Llc | 45 Morrison Ave | Sacramento Ca 95838 |  | 5593412018 | 850 So Guild Ave Suite 107 | Lodi Ca 95240 | Troy Scheiber | 573867.95 | 0 | 0 | 0 | 2025-10-20 | Replace Joint Seal And Place Polyester Con | San Joaquin County Near Lathorp At Variouslocations From Gaffery Road Overcrossing To Route 5/132 Separation | 72 | 95 | 2508692.5 | 2569567 | 2569567 | 57716 | 2025-11-25 | 2025-04-18 | 2025-04-03 |  |  | 65 | 0 | 90 | 0 |  | X
10 | 10-1L3404 | 1L3404 | 10-SJ-5-7.5/0 |  |  | Myers & Sons Construction, Llc | 45 Morrison Ave | Sacramento Ca 95838 | [5 empty] | 0 | 0 | 0 | 0 |  | Install Jointed Plain Concrete Pavement (R | San Joaquin County Near Tracy At Linne Road Overcrossing | 0 | 0 | 0 | 2560558 | 2560558 | 60057 |  | 2025-09-16 | 2025-08-20 |  |  | 0 | 0 | 60 | 0
10 | 10-1E3004 | 1E3004 | 10-SJ-5-32.5/49.8 |  | B1IM-0056- (361)E | Bay Cities Paving & Grading, Inc. | 1450 Civic Ct Bldg B #400 | Concord Ca 94520 |  | 2096394686 | 850 S. Guild Avenue Suite 107 | Lodi, Ca 95240 | Ariel Mendoza | 5364229.74 | 32246.33 | 0 | 0 | 2025-10-20 | Remove Existing Pavement And Replace With | San Joaquin County In And Near Stockton From 0.2 Mile South Of Hammer Lane Undercrossing To Sacramento County Line | 48 | 78 | 83255928.65 | 101114962.55 | 103520824.26 | 55909 | 2026-04-13 | 2024-03-08 | 2024-01-12 |  |  | 186 | 0 | 390 | 0 |  | X
10 | 10-1T5604 | 1T5604 | 10-SJ-99-7.9/7.9 | 20.20.201130 |  | Valentine Corporation | 111 Pelican Way | San Rafael, Ca. 94901 |  | 2094794053 | 3663 Arch Road, Ste 500 | Stockton, Ca. 95215 | Chris Hanson | 0 | 0 | 0 | 0 | 2025-07-02 | Bidge Girder Repair | Bridge Girder Repair In Sj County At Acampo Rdand Louise Ave,In Sta Co At Kansas Ave10A2765, 10-1T5604 Dirs Efa 10A2765 | 100 | 67 | 495035.01 | 3750 | 735000 | 57815 | 2025-12-31 | 2024-11-25 | 2024-11-08 |  |  | 124 | 0 | 35 | 0
10 | 10-1N9004 | 1N9004 | 10-SJ-99-21.6/0 |  | HSNH-P099- (694)E | Fbd Vanguard Construction, Inc. | 550 Greenville Road | Livermore Ca 94550 |  | 5593412018 | 850 So Guild Ave Suite 200 | Lodi, Ca 95240 | Troy Scheiber | 348153 | 0 | 0 | 0 | 2025-10-20 | Replace Guardrail With Concrete Barrier An | San Joaquin County Near Stockton At Wilsonway Overcrossing | 72 | 56 | 434253 | 735010 | 763560 | 57798 | 2025-10-29 | 2025-04-24 | 2025-03-28 |  |  | 18 | 0 | 25 | 0 |  | X
10 | 10-1U1004 | 1U1004 | 10-SJ-99-21.9/21.9 | 20.20.201130 |  | Viking Construction Co Inc. | 3835 Security Park Drive | Rancho Cordova, Ca 95752 |  | 2094794503 | 3663 Arch Road, Suite 500 | Stockton, 95215 | Chris Hanson | 0 | 0 | 0 | 0 | 2025-08-20 | Replace Damaged Girder 1 And Diaphragm1 | Repair Calvaras River Oc Bridge Hit Bridge 290095 10A2779 Dirs Efa 101U1004 | 100 | 36 | 446540.67 | 6250 | 1235000 | 57275 | 2025-12-31 | 2025-02-20 | 2024-12-06 |  |  | 160 | 0 | 100 | 0
10 | 10-1H6504 | 1H6504 | 10-SJ-99-28.7/31.7 | HA25 | ACNH-P099- (681)E | Marina Landscape Inc. | 3707 W Garden Grove Blvd | Orange Ca 92868 |  | 2096394686 | 850 S. Guild Ave. | Lodi, Ca 95240 | Ariel Mendoza | 2760 | 0 | 0 | 0 | 2025-09-20 | Highway Planting And Irrigation. | San Joaquin County In And Near Lodi From 0.4 Mile North Of Harney Lane Overcrossingto 0.2 Mile North Of Turner Road Overcrossing | 0 | 0 | 3631981.29 | 3498360 | 3619013.5 | 55304 | 2028-04-28 | 2023-11-28 | 2023-10-19 |  |  | 81 | 0 | 1000 | 0 | X | X
10 | 10-1C3304 | 1C3304 | 10-SJ-205-4.6/9 | HB4N | ACIM-2056- (356)E | Bay Cities Paving & Grading, Inc. | 1450 Civic Ct | Concord Ca 94520 | 9256876666 | 2096074910 | 952 Goodwin Drive | Ripon Ca 95366 | Harminder Deol | 0 | 0 | 0 | 0 | 2025-08-20 | Install Its- Phase 2 | In Tracy, West Of Grant Line Road To East Of Macarthur Drive, Install Ramp Meters And Other Intelligent Transportation System (Its | 29 | 63 | 11289302.7 | 17382378.09 | 17815911.59 | 42366 | 2026-07-17 | 2022-05-03 | 2022-04-05 |  | S | 92 | 0 | 300 | 14 |  | X
10 | 10-1U4704 | 1U4704 | 10-SJ-580-12.7/12.7 | 20.20.201130 |  | Bridgeway Civil Const Inc | 3333 Vaca Valley Pkwy | Suite 2000 Vacaville Ca 95688 |  | 2094794053 | 3663 Arch Road Suite 500 | Stockton Ca 95215 | Chris Hanson | 0 | 0 | 0 | 0 | 2025-09-29 |  | Repair Bridge Deck At East Midway Overheads J County 10A2803 10-1U4704 | 100 | 100 | 210972.17 | 1000 | 385000 | 58475 | 2025-09-29 | 2025-05-28 | 2025-03-19 | 2025-10-15 |  | 69 | 0 | 30 | 0 |  | X
10 | 10-1H2804 | 1H2804 | 10-STA-5-10.7/25.5 | HA21 |  | Myers And Sons Construction Llc | 45 Morrison Ave | Sacramento Ca 95838 |  | 5599775907 | 952 Goodwin Dr | Ripon, Ca 95366 | Anwar, Zubair | 733479.33 | 0 | 0 | 0 | 2025-09-09 | Place Polyester Concrete Surfacing On Brid | Stanislaus County In And Near Patterson Atvarious Locations From Fink Road Undercrossing To Khalsa Road Undercrossing | 100 | 88 | 10722200.52 | 10843840 | 10843840 | 55945 | 2025-10-17 | 2024-03-13 | 2024-02-06 |  |  | 152 | 0 | 145 | 0 |  | X
10 | 10-1C2704 | 1C2704 | 10-STA-5-27.1/27.4 | HA26 | CIMG-005 - (5 )160 | Tsi Engineering | 4600 Roseville Rd Suite 140 | North Highlands Ca 95660 |  | 5599775907 | 952 Goodwin Dr | Ripon, Ca 95366 | Anwar, Zubair | 1032668.02 | 0 | 0 | 0 | 2025-10-20 | Replace Safety Roadside Rest Area. | Stanislaus County About 1.0 Mile South Of San Joaquin County Line At The Westley Safety Roadside Rest Area | 85 | 79 | 16613159.2 | 20375786 | 20669181.7 | 56109 | 2025-12-26 | 2024-04-22 | 2024-03-28 |  |  | 263 | 0 | 310 | 0 |  | X
10 | 10-1R7704 | 1R7704 | 10-STA-99-1.5/16 | 20.20.201130 |  | Sinclair General Engineering Construction, Inc. | P.O. Box 1453 | Oakdale, Ca 95361 |  | 2096094910 | 952 Goodwin Drive | Ripon, Ca 95355 | Harminder Deol | 0 | 0 | 0 | 0 |  | Repair Storm Damage | On Sr 99 In Sta County Between Pms R1.5 And R16 Remove Debris, Stabilize Slopes, Place Slope Protection And Traffic Cntrl Dirs Efa | 0 | 0 | 0 | 2000 | 385000 | 52105 | 2023-09-29 | 2023-05-23 | 2023-03-30 |  |  | 0 | 0 | 15 | 0
10 | 10-1S4904 | 1S4904 | 10-STA-99-17.0/17 | 20.20.201130 |  | Synergy Const & Delopment Corp | 5109 Pomerado Way | Bakersfield Ca 93313 |  | 2094708782 | 952 Goodwin Drive | Ripon Ca 95366 | Obaidullah Rashid | 0 | 0 | 0 | 0 | 2025-10-20 | Replace Fence, Gate And Gate System | Replace Fence And Gate Withvandal-Deterrent Cochraneclear Vuinvisible Wall Fence Andgate System. 10A2730-Dirs Efa | 89 | 81 | 1612165.86 | 9995 | 1984000 | 57026 | 2025-11-04 | 2025-01-01 | 2024-12-31 |  |  | 133 | 0 | 150 | 0 |  | X
10 | 10-1K8404 | 1K8404 | 10-STA-108-33.2/33.5 |  | HSST-P108- (055)E | Mountain Cascade, Inc. | 555 Exchange Court | Livermore Ca 94550 |  | 2096078786 | 952 Goodwin Drive | Ripon, Ca 95366 | Magdy Farid | 0 | 0 | 0 | 0 |  | Place Hot Mix Asphalt, Install Signal And | Stanislaus County Near Riverbank From 0.1 Mile West Of Topeka Street To 0.2 Mile East Of Claus Road | 0 | 0 | 0 | 1940646.8 | 1940646.8 | 59435 |  | 2025-06-26 | 2025-06-06 |  |  | 0 | 0 | 70 | 0
10 | 10-0G8304 | 0G8304 | 10-VAR-59-/0 | HA21 | B1ST-X077- (014)E | Viking Construction Company, Inc. | 11315 Sunrise Gold Circle Sui | Rancho Cordova Ca 95742 |  | 5308703106 | 530 W. 16Th Street Suite D | Merced, Ca 95340 | Jagga Dhami | 249948 | 76390.96 | 0 | 0 | 2025-10-20 | Bridge Seismic Restoration. | Merced County At Various Locations | 89 | 90 | 14453177.99 | 15385439.5 | 15877678.13 | 55084 | 2026-01-02 | 2023-11-27 | 2023-10-31 |  |  | 402 | 0 | 450 | 0 |  | X
10 | 10-1S3304 | 1S3304 | 10-VAR--/0 |  |  | Central Striping Service, Inc. | 3489 Luyung Drive | Rancho Cordova Ca 95742 | 9163807232 | 9162931122 | 952 Goodwin Drive |  | Wali Waziri | 392971.8 | 0 | 0 | 22545.36 | 2025-10-20 | Install Roadside Sign, Traffic Stripe, And | Merced, San Joaquin, And Stanislaus Counties At Various Locations | 42 | 59 | 593776.43 | 997000 | 1004000 | 58615 | 2025-12-09 | 2025-06-09 | 2025-05-13 |  |  | 21 | 0 | 50 | 0 |  | X
10 | 10-1G0204 | 1G0204 | 10-VAR--/0 |  |  | Studebaker Electric, Inc. | 3237 Rippey Road, Ste 100 | Loomis Ca 95650 | [5 empty] | 0 | 0 | 0 | 0 |  | Install Transportation Management Systems. | Alpine, Amador, And El Dorado Counties At Various Locations | 0 | 0 | 0 | 7348780.16 | 7348780.16 | 60126 |  | 2025-10-16 | 2025-09-29 |  |  | 0 | 0 | 150 | 0
10 | 10-1S5804 | 1S5804 | 10-VAR--/0 |  |  | Quimu Contracting, Inc. | 5830 Dixon Avenue West | Dixon Ca 95620 |  | 2096094910 | 952 Goodwin Drive | Ripon Ca 95366 | Harminder Deol | 196586.32 | 0 | 0 | 2500 | 2025-09-20 | Culvert Replacement And Erosion Control. | Merced County Near Los Banos At Various Locations | 71 | 86 | 515836.32 | 597619.5 | 597619.5 | 58777 | 2025-11-07 | 2025-06-10 | 2025-04-29 |  |  | 46 | 0 | 65 | 0 |  | X
10 | 10-1F9704 | 1F9704 | 10-VAR--/0 |  |  | Pacific Infrastructure Construction, Llc | 871 Cotting Court Ste A | Vacaville Ca 95688 |  | 2096394306 | 952 Goodwin Drive | Ripon, Ca 95366 | Ranbir Bhullar | 888045 | 0 | 0 | 0 | 2025-10-20 | Upgrade Tms Element And Maintenance Vehicl | San Joaquin And Stanislaus Counties At Various Locations | 43 | 46 | 4973127 | 10743752 | 10844752 | 57616 | 2025-05-14 | 2025-03-27 | 2025-02-26 |  |  | 102 | 0 | 240 | 0 |  | X
10 | 10-1F9604 | 1F9604 | 10-VAR--/0 |  |  | Studebaker Electric, Inc. | 3237 Rippey Road, Ste 100 | Loomis Ca 95650 | 9162592395 | 2094835812 | 3663 Arch Road, Suite 500 | Stockton, Ca 95215 | David Abledu | 720650.5 | 0 | 0 | 7700 | 2025-10-20 | Install Fiber Optic System & Modify Intell | San Joaquin County At Various Locations | 48 | 57 | 3628023.73 | 6298734 | 6403734 | 57339 | 2026-02-17 | 2025-01-24 | 2024-11-19 |  |  | 98 | 0 | 205 | 0 |  | X
10 | 10-1L8604 | 1L8604 | 10-VAR--/0 |  |  | Central Coast Financial Group,Inc. Dba Ccfg Construction | 17750 Wards Ferry Rd | Sonora Ca 95370 | [5 empty] | 0 | 0 | 0 | 0 |  | Install New Transportation Management Syst | Amador, Mariposa, And Tuolumne Counties Atvarious Locations. | 0 | 0 | 0 | 2053700 | 2053700 | 60117 |  | 2025-10-08 | 2025-09-15 |  |  | 0 | 0 | 85 | 0
10 | 10-1R7204 | 1R7204 | 10-VAR--/0 |  |  | Mccuen Construction, Inc. | 3269 Swetzer Road | Loomis Ca 95650 | 9166257824 | 2094835812 | 3663 Arch Road, Suite 500 | Stockton, Ca 95215 | David Abledu | 350139.46 | 0 | 0 | 51800 | 2025-10-20 | Place Polyester Concrete Overlay, Traffic | San Joaquin County At Various Locations | 65 | 28 | 815105.66 | 2861840.58 | 2861840.58 | 59955 | 2025-11-26 | 2025-05-23 | 2025-05-01 |  |  | 65 | 0 | 100 | 0 |  | X
11 | 11-432194 | 432194 | 11-IMP-0-/0 | 20.20 201130 |  | Rove Engineering, Inc. | P.O. Box 2108 | El Centro, Ca. 92244 |  | 6199910827 | 4050 Taylor Street | San Diego Ca. 92110 | Lopez, Carlos | 27125 | 0 | 0 | 0 | 2024-08-18 | Repair Storm Damage | Repair Storm Damage Due To Weather Event And Flash Flooding In Imperial County At Multiple Locations Dir S Emergency L.B. | 50 | 100 | 5999979.39 | 54250 | 5985000 | 55587 | 2024-12-31 | 2024-03-15 | 2023-09-01 |  |  | 45 | 0 | 90 | 0 |  | X
11 | 11-432934 | 432934 | 11-IMP-0-/0 | 20.20 201130 |  | Raine General Engineering, Inc | P.O. Box 228 | El Centro Ca 92244 |  | 7606044249 | 4050 Taylor Street | San Diego, Ca 92110 | Rodolfo Guiao | 0 | 0 | 0 | 0 |  | Repair Storm Damage Due To Monsoonal Storm | Repair Storm Damage Along Sr-78, Sr-86, Sr-111, I-8 And Sr-115Imperial County Dir'S Emergency F. A. | 0 | 0 | 0 | 97171 | 16985000 | 60125 | 2026-12-31 | 2025-10-14 | 2025-08-25 |  |  | 0 | 0 | 60 | 0
11 | 11-2N1764 | 2N1764 | 11-IMP-8-50.3/96.7 |  |  | Pavement Coatings Co. | 10240 San Sevaine Way | Jurupa Valley Ca 91752 |  | 7605942006 | 1102 Montenegro Way | El Centro, Ca 92243 | Jose G. Sillas | 0 | 0 | 0 | 0 |  | Micro-Surfacing, Rhma-G, Shoulder Backing, | Imperial County At Various Locations From 0.2 Mile West Of Bonds Corner Overcrossingto 0.2 Mile East Of Fourth Avenue Overcrossing | 0 | 0 | 0 | 2581165.7 | 2581165.7 | 58598 | 2026-05-12 | 2025-06-09 | 2025-05-01 |  | S | 0 | 0 | 80 | 0
11 | 11-2N1784 | 2N1784 | 11-IMP-8-/10.3 |  |  | Intermountain Slurry Seal, Inc. | 1120 Terminal Way | Reno Nv 89502 |  | 7605942006 | 1102 Montenegro Way | El Centro, Ca 92243 | Jose G. Sillas | 825266.16 | 0 | 0 | 24750 | 2025-10-20 | Micro-Surfacing, Cold Plane Ac Pavement, P | Imperial County From Imperial County Line (R0.0R) To 98/8 Flyover (R10.3) And 98/8 Interchange | 95 | 73 | 3781263.03 | 5047889 | 5047889 | 59177 | 2026-02-05 | 2025-06-25 | 2025-05-29 |  |  | 57 | 0 | 60 | 0
11 | 11-2N2284 | 2N2284 | 11-IMP-78-/13.2 |  |  | Intermountain Slurry Seal, Inc. | 1120 Terminal Way | Reno Nv 89502 | 8317684020 | 7605912006 | 1102 Montenegro Way | El Centro, Ca 92243 | Jose G. Sillas | 285512.2 | 0 | 0 | 0 | 2025-10-20 | Place Micro-Surfacing, Rumble Strip, And P | Imperial County Near Ocotillo Wells From San Diego County Line To North Junction Route 86 | 100 | 90 | 960483.88 | 1047130 | 1047130 | 59340 | 2026-02-05 | 2025-07-08 | 2025-06-03 |  |  | 50 | 0 | 50 | 0 |  | X
11 | 11-2N2304 | 2N2304 | 11-IMP-86-4.5/L8.5 |  |  | Pavement Coatings Co. | 10240 San Sevaine Way | Jurupa Valley Ca 91752 |  | 7605942006 | 1102 Montenegro Way | El Centro, Ca 92243 | Jose G. Sillas | 0 | 0 | 0 | 0 |  | Micro-Surfacing, Pavement Marking, Rumble | Imperial County In And Near El Centro And Brawley From Mccabe Road To Imperial Avenue And From I Street To 0.3 Mile Northof New Ri | 0 | 0 | 0 | 2198568.38 | 2198568.38 | 58637 | 2026-04-25 | 2025-06-09 | 2025-05-02 |  | S | 0 | 0 | 60 | 0
11 | 11-2N2264 | 2N2264 | 11-IMP-98-30.0/57 |  |  | Sb General Engineering, Inc. | 12125 Lakeside Avenue | Lakeside Ca 92040 |  | 7605942006 | 1102 Montenegro Way | El Centro, Ca 92243 | Jose G. Sillas | 0 | 0 | 0 | 0 |  | Place Rumble Strips And Pavement Delineati | Imperial County In And Near Calexico From 2.3 Miles West Of Route 111 To Evan Hewes Highway | 0 | 0 | 0 | 1123085.26 | 1123085.26 | 58495 | 2026-05-05 | 2025-06-04 | 2025-05-15 |  | S | 0 | 0 | 60 | 0
11 | 11-080284 | 080284 | 11-IMP-98-32.1/32.5 |  | ACNH-P098- (029)EPL16-6211- (134) | Spectrum Construction Group, Inc. | 16 Goodyear, Ste. 140 | Irvine Ca 92618 | 9492991400 | 7605942008 | 1102 Montenegro Way | El Centro, Ca 92243 | Daniel Hernandez-Duarte | 163756.9 | 22535.97 | -349966.86 | 0 | 2022-03-20 | Widening Sr-98 Highway From 4 Lanes | In Imperial County In Calexico From Ollie Avenue To 0.1 Mile East Of Rockwood Avenue. | 25 | 18 | 1272123.67 | 6999337.87 | 7246161.17 | 41392 | 2023-03-30 | 2020-12-24 | 2020-12-04 |  |  | 121 | 0 | 475 | 0 |  | X
11 | 11-2N1974 | 2N1974 | 11-IMP-111-23.5/32.1 |  |  | Hazard Construction Company | 10529 Vine Street | Lakeside Ca 92040 |  | 7605942006 | 1102 Montenegro Way | El Centro, Ca 92243 | Jose G. Sillas | 694047.31 | 0 | 0 | 8300 | 2025-10-20 | Cold Plane, Hma-A, Rhma-G, Microsurfacing, | Imperial County Near Brawley And Calipatria At Various Locations From 0.2 Mile South Of Route 78 To 0.4 Mile South Of Route 115 | 44 | 78 | 1315624.31 | 1658805 | 1658805 | 58575 | 2026-03-25 | 2025-06-06 | 2025-04-16 |  | S | 22 | 0 | 50 | 0 |  | X
11 | 11-2N1474 | 2N1474 | 11-IMP-111-50.7/0 |  |  | Rv Concrete, Inc. | 605 E. Commercial Street | Anaheim Ca 92801 | 9148884201 | 7605942006 | 1102 Montenegro Way | El Centro, Ca 92243 | Jose G. Sillas | 0 | 0 | 0 | 0 |  | Repair Two Culverts. | Imperial County Near Salton Sea At Clay Wash And At Frink Wash | 0 | 0 | 0 | 464464 | 464464 | 59318 | 2026-05-02 | 2025-07-08 | 2025-05-22 |  |  | 0 | 0 | 40 | 0
11 | 11-432854 | 432854 | 11-SD-0-/0 | 20.20 201130 |  | Rove Engineering, Inc. | P.O. Box 2108 | El Centro, Ca 92244 |  | 7606044249 | 4050 Taylor Street | San Diego, Ca 92110 | Rodolfo Guiao | 4360.5 | 0 | 0 | 0 | 2025-08-25 | Replace Failed Drainage Systems | Replace Failed Drainage Systems Multiple Locations San Diego County Dir'S Emergency L.B. | 1 | 74 | 1178352.01 | 8721 | 1585000 | 58435 | 2025-12-31 | 2025-05-13 | 2025-04-01 |  |  | 1 | 0 | 90 | 0 |  | X
11 | 11-432784 | 432784 | 11-SD-0-/0 | 20.20 201131 |  | Sb General Engineering Inc | Po Box 1400 | Lakeside, Ca 92040 |  | 6194967561 | 4050 Taylor Street | San Diego, Ca 92110 | Christian Antonio | 0 | 0 | 0 | 0 | 2025-09-19 | Restore Drainage Channel Cross Sections | Clean Drainage Channels Various Locations Along Routes 8,15,78,805San Diego County Dir'S Emergency L.B | 8 | 6 | 585652.54 | 46920 | 9485000 | 59615 | 2026-07-31 | 2025-07-29 | 2025-06-02 |  |  | 16 | 0 | 200 | 0 |  | X
11 | 11-432674 | 432674 | 11-SD-0-/0 | 20.20 201130 |  | Sb General Engineering, Inc. | Po Box 1400 | Lakeside, Ca 92040 |  | 6195394431 | 4050 Taylor Street | San Diego, Ca 92110 | Ahmad Haidari | 0 | 0 | 0 | 0 | 2025-09-25 | Replace Damaged Tms Elements | Replace Damaged Tms Elements Multiple Locations San Diego County Dir'S Emergency L.B. | 10 | 33 | 1328834.18 | 23899 | 3985000 | 57295 | 2027-12-30 | 2025-02-19 | 2024-12-16 |  |  | 10 | 0 | 100 | 0 |  | X
11 | 11-432504 | 432504 | 11-SD-0-/0 | 20.20 201130 |  | Lb Civil Construction, Inc. | 324 E. Valley Pkwy | Escondido, Ca 92025 |  | 8585182236 | 4050 Taylor Street | San Diego, Ca 92110 | Ho, Tyler | 0 | 0 | 0 | 0 | 2024-03-30 | Repair Failed Drainage | In San Diego County Along Various Routes. Repair Failed Drainage Systems Repair Damaged Pavement Dir'S Emergency L.B. | 100 | 74 | 1848960.83 | 22000 | 2485000 | 55510 | 2025-02-21 | 2024-03-15 | 2024-02-13 |  |  | 100 | 0 | 50 | 0
11 | 11-432564 | 432564 | 11-SD-0-/0 | 20.80 420000 |  | Sb General Engineering, Inc. | Po Box 1400 | Lakeside, Ca 92040 | 6193906570 | 6194909264 | 4050 Taylor Street | San Diego, Ca 92110 | Pedro Aguilar | 0 | 0 | 0 | 0 | 2025-08-28 | Ww Enhanced Deterrents | Wrong Way Enhanced Deterrents Multiple Locations San Diego County Dir'S Emergency L.B. | 100 | 99 | 1089923.58 | 7200 | 1085000 | 56374 | 2025-12-31 | 2024-07-17 | 2024-06-21 |  |  | 50 | 0 | 50 | 0 |  | X
11 | 11-431274 | 431274 | 11-SD-5-.3/36 |  |  | Kiewit Infrastructure West Co. | 12700 Stowe Drive, Suite 180 | Poway Ca 92064 |  | 6199366265 | 2863 Carmel Valley Road | Del Mar, Ca 92014 | Timothy Poppe | 4440596.4 | 365209.75 | 0 | 0 | 2025-10-20 | Pavement Rehab, Bridge Rehab, Drainage, An | San Diego County At Various Locations Fromcamino De La Plaza Overcrossing To 0.3 Mile South Of Via De La Valle Undercrossing | 20 | 36 | 28729952.01 | 79019295.99 | 80001309.28 | 57386 | 2027-12-14 | 2025-01-28 | 2025-01-28 |  |  | 127 | 0 | 625 | 0 |  | X
11 | 11-4C0034 | 4C0034 | 11-SD-5-.9/0 |  |  | Hazard Construction Engr Llc | 10529 Vine Street | Lakeside Ca 92040 |  | 8586881520 | 2863 Carmel Valley Rd | Del Mar Ca 92014 | Alfredo Martinez | 760 | 23686.01 | 0 | 0 | 2025-09-20 | Replace Gateway Sign, Install Landscape, H | San Diego County In San Ysidro At The Route 5/805 Separation | 100 | 94 | 1886505.59 | 1597008.5 | 2066460.19 | 50866 | 2025-12-20 | 2023-07-05 | 2023-06-16 |  |  | 359 | 0 | 360 | 0 |  | X
11 | 11-2T0444 | 2T0444 | 11-SD-5-4.4/4.5 |  |  | Flatiron-Skanska-Stacy And Witbeck, A Joint Venture | 12121 Scripps Summit Dr, #400 | San Diego Ca 92131 |  | 8586881435 | 2863 Carmel Valley Rd | Del Mar, Ca 92014 | Steve Mcmillan | 3574537.07 | 0 | 0 | 0 | 2025-10-20 | Batiquitos Lagoon Double Track Project | San Diego County In Encinitas And Carlsbadfrom La Costa Br 235.17 To 0.1 Miles Northof Avenida Encinas Br 234.5 0.5 Miles Westof R | 25 | 41 | 41852965.91 | 100800000 | 100969297.64 | 56231 | 2029-04-11 | 2024-07-03 | 2024-06-21 |  |  | 287 | 0 | 1155 | 0 |  | X
11 | 11-432304 | 432304 | 11-SD-5-4.6/4.6 | 20.20 201130 |  | Alvarez And Shaw, Inc. | 2101 Alpine Blvd, Ste C | Alpine, Ca. 91901 |  | 6198574332 | 4050 Taylor Street | San Diego, Ca 92110 | Nelmark, Jodi | 0 | 0 | 0 | 0 | 2025-10-13 | Replace Pump System | Replace Pump System And Failed Components In San Diego County Along I-5 At Palm Ave Pump Station Dir'S Emergency L.B. | 1 | 29 | 575413.93 | 15181 | 1985000 | 55588 | 2026-06-19 | 2024-03-01 | 2024-01-26 |  |  | 1 | 0 | 100 | 0 |  | X
11 | 11-4B0334 | 4B0334 | 11-SD-5-9.1/16.1 |  |  | Griffith Company - Henkels & Mccoy Joint Venture | 3050 E. Birch St | Brea Ca 92821 |  | 8586881376 | 1102 Montenegro Way | El Centro, Ca 92243 | Alfredo Hernandez Medina | 335652.84 | 29184.36 | 0 | 0 | 2025-09-20 | Mmbn Project On Route 005 - Phase 1 | For Construction On State Highway In San Diego County On Route 5 From 0.3 Mile South Of Sweetwater River Bridge To 0.2 Mile South | 94 | 88 | 1906215.61 | 1679439.8 | 1779726.97 | 58836 | 2025-12-24 | 2025-03-06 | 2025-03-06 |  |  | 89 | 0 | 95 | 0 |  | X
11 | 11-4B0044 | 4B0044 | 11-SD-5-9.5/0 |  |  | Griffith Company - Henkels & Mccoy Joint Venture | 3050 E. Birch St | Brea Ca 92821 | 7149845500 | 8586881376 | 1102 Montenegro Way | El Centro, Ca 92243 | Alfredo Hernandez Medina | 429050 | 0 | 0 | 0 | 2025-10-20 | Broadband Fiber Optic Network Installation | San Diego County In And Near San Diego, National City And Chula Vista On Route 5 At Mile North Of Sweetwater River Bridge And On R | 59 | 74 | 4378833.79 | 5420180.79 | 5423508.79 | 58957 | 2026-03-31 | 2025-03-12 | 2025-03-12 |  |  | 92 | 0 | 155 | 0 |  | X
11 | 11-432714 | 432714 | 11-SD-5-10.4/10.4 | 20.20 201130 |  | Sb General Engineering, Inc. | Po Box 1400 | Lakeside, Ca 92040 |  | 6199910827 | 4050 Taylor Street | San Diego, Ca 92110 | Carlos G. Lopez | 0 | 0 | 0 | 0 | 2025-10-22 | Bridge Deck Repair Due To Pavement Failure | Bridge Deck Repair Due To Pavement Failurenb I-5 At The 18Th Street Uc(57-0252R) San Diego County Dir'S Emergency L.B. | 17 | 32 | 1924766.44 | 32340 | 5985000 | 58077 | 2025-12-31 | 2025-04-30 | 2025-03-17 |  |  | 10 | 0 | 60 | 0 |  | X
11 | 11-431994 | 431994 | 11-SD-5-16.0/16 | 20.20 201130 |  | Sb General Engineering, Inc. | Po Box 1400 | Lakeside, Ca 92040 |  | 6199910827 | 4050 Taylor St. | San Diego, Ca 92110 | Lopez, Carlos G. | 16170 | 0 | 0 | 0 | 2024-08-18 | Repair Bridge Deck | Repair Bridge Deck At 5/163 Separation In San Diego County In San Diego On I-5 At 5/163 Separation (Br.No. 57-0391) Dir'S Emergenc | 2 | 98 | 5858925.08 | 32340 | 5985000 | 53384 | 2024-12-31 | 2023-10-09 | 2023-08-09 |  |  | 1 | 0 | 45 | 0 |  | X
11 | 11-432694 | 432694 | 11-SD-5-19.4/19.4 | 20.20 201130 |  | Rove Engineering, Inc. | Po Box 2108 | El Centro, Ca 92244 |  | 6199910827 | 4050 Taylor Street | San Diego, Ca 92110 | Carlos Lopez | 0 | 0 | 0 | 0 | 2025-08-24 | Repair Bridge At The Old Town Viaduct | Repair Bridge At The Old Town Viaduct San Diego County Dir'S Emergency L.B | 13 | 34 | 2017400.63 | 41226 | 5985000 | 57975 | 2025-12-31 | 2025-04-14 | 2024-12-30 |  |  | 5 | 0 | 40 | 0 |  | X
11 | 11-2N1754 | 2N1754 | 11-SD-5-30.6/52.8 |  |  | Flatiron West Inc. | 1770 La Costa Meadows Drive | San Marcos Ca 92078 |  | 6193185524 | 4050 Taylor Street | San Diego, Ca 92110 | Alex Balce | 93622.1 | 0 | 0 | 0 | 2025-08-20 | Structural Concrete, Polyester Concrete Ov | San Diego County At Various Locations Fromroute 5/805 Separation To Brooks Street Overcrossing | 94 | 96 | 7406838.2 | 7379228.1 | 7655569.55 | 56196 | 2025-09-16 | 2024-08-06 | 2024-06-28 |  |  | 80 | 0 | 85 | 0 |  | X
11 | 11-2E1544 | 2E1544 | 11-SD-5-34.7/36.3 |  |  | Marathon Construction Corporation | 10108 Riverford Rd | Ca, Lakeside 92040 | 6192764401 | 8582203986 | 990 Highland Dr. #308 | Solana Beach Ca 92075 | Jared Corbitt | 143366.4 | 24892.01 | 0 | 0 | 2025-10-20 | To Lower Existing Elevations At The | In Sdc In Sd From 0.6 Mile North Of Del Mar Heights Rd Overcrossing To Villa De La Valle Underxing. | 48 | 87 | 61887847.35 | 66100000 | 71287891 | 42060 | 2029-09-24 | 2021-12-21 | 2021-12-10 |  |  | 896 | 0 | 1875 | 0 |  | X
11 | 11-2T36U4 | 2T36U4 | 11-SD-5-37.4/52.6 |  | ACIM-0051- (996)E6211-156 - ( )000 | Flatiron-Skanska-Stacy And Witbeck, A Joint Venture | 12121 Scripps Summit Dr #400 | San Diego Ca 92131 |  | 8586881481 | 2863 Carmel Valley Rd | Del Mar, Ca 92014 | Yong Pak | 807449.66 | 336152.17 | -5900.4 | 0 | 2025-10-20 | Construct Multi-Modal Enhancement, Sound W | San Diego County At Various Locations Fromlomas Santa Fe Drive Undercrossing To 0.2 Miles North Of Oceanside Boulevard Undercrossi | 72 | 95 | 81074208.03 | 72520000 | 83764946.34 | 54324 | 2029-04-11 | 2023-11-20 | 2023-10-20 |  |  | 467 | 0 | 650 | 0 |  | X
11 | 11-2T35U4 | 2T35U4 | 11-SD-5-37.4/52.6 |  |  | Flatiron-Skanska-Stacy And Witbeck A Joint Venture | 12121 Scripps Summit Dr. #400 | San Diego, Ca 92131 | 7606370654 | 8585183505 | 2863 Camel Valley Rd | Del Mar, Ca 92014 | Steve Mcmillan | 27933.62 | 360716.92 | 39151.09 | 0 | 2025-09-30 | Construct One Hov Lane In Each | In City Of Carlsbad From Palomar Airport Rd To Sr78 | 100 | 100 | 63717916.25 | 61865000 | 64608713.9 | 41917 | 2025-09-30 | 2021-10-04 | 2021-09-07 | 2025-09-30 |  | 898 | 0 | 370 | 46 |  | X
11 | 11-2N1684 | 2N1684 | 11-SD-5-53.9/63.7 |  |  | Mccuen Construction, Inc. | 3269 Swetzer Road | Loomis Ca 95650 |  | 6193185524 | 4050 Taylor Street | San Diego, Ca 92110 | Alex Balce | 213203.33 | 0 | 0 | 0 | 2025-10-20 | Polyester Concrete, Methacrylate, Joint Se | San Diego County At Various Locations Fromroute 5/76 Separation To Agra Overhead | 51 | 84 | 4080971.9 | 4803824.33 | 4857824.33 | 58296 | 2025-12-24 | 2025-05-22 | 2025-05-02 |  |  | 46 | 0 | 90 | 0 |  | X
11 | 11-432434 | 432434 | 11-SD-5-54.2/54.2 | 20.20 201130 |  | Montano Pipeline, Inc. | 231 4Th Ave | Chula Vista, Ca 91910 |  | 6194556151 | 4050 Taylor Street | San Diego, Ca 92110 | Daabas, Jalal | 10500 | 0 | 0 | 0 | 2024-09-18 | Repair Failed Culverts | In San Diego County In The City Of Oceanside On I-5 Remove And Replace Failed Drainage Systemsdir S Emergency L.B. | 4 | 100 | 696778.69 | 10500 | 685000 | 55721 | 2024-12-30 | 2024-04-23 | 2024-01-22 |  |  | 1 | 0 | 25 | 0 |  | X
11 | 11-430824 | 430824 | 11-SD-5-66.2/67.4 |  |  | Montano Pipeline, Inc. | 231 4Th Ave | Chula Vista Ca 91910 |  |  |  |  | Rosemarie Pagunsan | 0 | 0 | 0 | 0 |  | Pcc & Hma Paving, Signs And Striping, Wsms | San Diego County About 12 Miles North Of Oceanside From 1.2 Miles South Of San Onofre Commercial Vehicle Enforcement Facilities To | 0 | 0 | 0 | 3488900 | 3488900 | 60133 |  | 2025-10-24 | 2025-10-01 |  |  | 0 | 0 | 140 | 0
11 | 11-4B0084 | 4B0084 | 11-SD-8-15.8/21.9 |  |  | Griffith Company - Henkels & Mccoy Joint Venture | 3050 E. Birch St | Brea Ca 92821 | 7149845500 | 8586881376 | 2863 Carmel Valley Rd | Del Mar, Ca 92014 | Alfredo Hernandez Medina | 452126.96 | 0 | 0 | 0 | 2025-10-20 | Mmbn Project On I-8 Pm 15.8/R21.9 | San Diego County In And Near El Cajon Fromroute 8/Route 67 Separation To Lake Jennings Park Road Undercrossing | 47 | 44 | 3748761.13 | 8437204.53 | 8440532.53 | 58958 | 2026-04-30 | 2025-03-13 | 2025-03-13 |  |  | 73 | 0 | 155 | 0 |  | X
11 | 11-432844 | 432844 | 11-SD-8-26.0/32 | 20.20 201131 |  | Raine General Engineering Inc | Po Box 228 | El Centro, Ca 92244 |  | 6199910827 | 4050 Taylor Street | San Diego, Ca 92110 | Carlos G. Lopez | 0 | 0 | 0 | 0 | 2025-10-22 | Replace Failing Pavement | Pavement Repair I-8 Eb And Wb Directions San Diego County Dir'S Emergency L.B. | 8 | 93 | 22382377.02 | 132171 | 23985000 | 59256 | 2026-06-30 | 2025-06-25 | 2025-06-02 |  |  | 10 | 0 | 120 | 0 |  | X
11 | 11-432824 | 432824 | 11-SD-8-41.8/41.8 | 20.20 201130 |  | Rove Engineering, Inc. | Po Box 2108 | El Centro, Ca 92244 |  | 6199910827 | 4050 Taylor Street | San Diego, Ca 92110 | Carlos G. Lopez | 0 | 0 | 0 | 0 | 2025-10-23 | Bridge Deck Repairs | Bridge Deck Repairs Along I-8 At The Pine Valley Creek Bridgessan Diego County Dir'S Emergency L.B | 10 | 20 | 3313753.21 | 59669 | 16685000 | 59236 | 2025-12-31 | 2025-05-21 | 2025-03-17 |  |  | 10 | 0 | 100 | 0 |  | X
11 | 11-2N2324 | 2N2324 | 11-SD-8-73.0/77.8 |  |  | Intermountain Slurry Seal, Inc. | 1120 Terminal Way | Reno Nv 89502 |  | 7605942006 | 1102 Montenegro Way | El Centro, Ca 92243 | Jose G. Sillas | 675384.62 | 0 | 0 | 21250 | 2025-10-20 | Micro-Surfacing, Striping, Rumble Stripe, | San Diego County Near Jacumba From 0.9 Mile West Of Carrizo Road Undercrossing Toimperial County Line | 93 | 82 | 2560151.82 | 3006843.92 | 3006843.92 | 58317 | 2026-02-03 | 2025-05-23 | 2025-04-28 |  |  | 56 | 0 | 60 | 0 |  | X
11 | 11-056404 | 056404 | 11-SD-11-.6/2.7 |  | ACNH-P011- (011)E | Hazard Construction Engr, Llc | 10529 Vine Street | Lakeside Ca 92040 |  | 8586881435 | 5377 Otay Mesa Rd | San Diego, Ca 92154 | Steve Mcmillan | 957877.77 | 54264.9 | 0 | 0 | 2025-10-20 | Perform Grading, Construct Drainage Facili | San Diego County Near San Diego From 0.2 Mile West Of Sanyo Avenue Undercrossing To0.2 Mile East Of Siempre Viva Road Overcrossing | 100 | 96 | 13058395.68 | 13185891.5 | 13160632.75 | 12569 | 2025-10-24 | 2025-01-21 | 2024-12-20 |  |  | 154 | 0 | 100 | 42 |  | X
11 | 11-430194 | 430194 | 11-SD-15-.4/10.2 |  | PTIM-015 - (4 )211 | Hazard Construction Company | 10529 Vine Street | Lakeside Ca 92040 |  | 8586881376 | 2863 Carmel Valley Road | Del Mar, Ca 92014 | Genaro Genel | 665564 | 0 | 0 | 750000 | 2025-10-20 | Culvert Restoration, Tunnel Co Monitoring | San Diego County In San Diego From 0.2 Mile South Of Route 5/15 Separation To 0.4Mile South Of Route 52/15 Separation. | 7 | 13 | 1903452.6 | 15072875 | 15192875 | 58577 | 2027-06-23 | 2025-06-06 | 2025-04-16 |  |  | 30 | 0 | 445 | 0 |  | X
11 | 11-2N2344 | 2N2344 | 11-SD-15-.4/T2.8 |  |  | Hazard Construction Engr, Llc | 10529 Vine Street | Lakeside Ca 92040 |  | 6193185524 | 4050 Taylor Street | San Diego, Ca 92110 | Alex Balce | 181266.5 | 0 | 0 | 0 | 2025-09-20 | Cold Plane Ac, Rhma-G Overlay, Pavement Ma | San Diego County In San Diego From Main Street Undercrossing To 0.6 Mile North Of Route 15/94 Separation | 60 | 89 | 2021772.2 | 2262999.7 | 2262999.7 | 58576 | 2025-11-12 | 2025-06-06 | 2025-05-20 |  |  | 54 | 0 | 90 | 0 |  | X
11 | 11-432444 | 432444 | 11-SD-15-2.1/2.2 | 20.20 201130 |  | Montano Pipeline, Inc. | 231 4Th Ave | Chula Vista, Ca 91910 |  | 6194909264 | 4050 Taylor Street | San Diego, Ca 92110 | Aguilar, Pedro | 0 | 0 | 0 | 0 | 2025-04-19 | Repair Drainage Channel | Repair Drainage Channel Due To Storm Eventin San Diego County In San Diego Along Theeb-94 And Sb I-15 Connector Ramp. Dir'S Emerge | 69 | 57 | 1353948.71 | 21357 | 2385000 | 55786 | 2025-12-31 | 2024-05-08 | 2024-02-01 |  |  | 55 | 0 | 80 | 0 |  | X
11 | 11-430514 | 430514 | 11-SD-15-31.3/37.1 |  | ACSB-0154- (210)E | Security Paving Company, Inc. | 3075 Townsgate Road | Westlake Village Ca 91361 | 8183629200 | 8586881473 | 871 N Broadway | Escondido, Ca 92025 | Jason Alsheikh | 1211548.47 | 0 | 3923.89 | 0 | 2025-10-20 | Mainline Pavement Rehabilitation, | In San Diego County In And Near Escondido From 0.2 Mile South Of Route 15/78 Separaton To 0.5 Mile North Of Deer Springs Road Ove | 100 | 89 | 39749635.03 | 45969872 | 45161629.54 | 42665 | 2025-12-31 | 2022-06-27 | 2022-05-27 |  |  | 524 | 0 | 450 | 74 |  | X
11 | 11-432914 | 432914 | 11-SD-15-45.0/4.5 | 20.80 240000 |  | Montano Pipeline, Inc. | 231 4Th Avenue | Chula Vista, Ca 91910 |  | 6195394431 | 4050 Taylor Street | San Diego, Ca 92110 | Ahmad Haidari | 0 | 0 | 0 | 0 | 2025-10-26 | Install Encampment Exclusionary Measures | Install Encampment Exclusionary Measures Along I-15 And I-805 San Diego County Dir'S Emergency L.B. | 13 | 22 | 216852.13 | 4190 | 985000 | 60102 | 2025-12-31 | 2025-10-03 | 2025-09-22 |  |  | 8 | 0 | 60 | 0 |  | X
11 | 11-430254 | 430254 | 11-SD-52-5.1/9 |  | ACNH-P052- (021)E | Scj Csi Cja A Joint Venture | 9685 Via Excelencia Ste 200 | San Diego Ca 92126 |  | 6199367067 | 5377 Otay Mesa Rd | San Diego, Ca 92110 | Karl Hartline | 916794.87 | 79620.43 | 296467.87 | 0 | 2025-10-20 | Const Aux Lane, Compaction Grouting, Rhma, | San Diego County In San Diego From 0.4 Mile West Of Convoy Street Overcrossing To0.3 Mile East Of Santo Road Overcrossing | 48 | 91 | 54103454.68 | 54685000 | 57400576.25 | 55064 | 2027-05-12 | 2024-01-29 | 2023-12-21 |  |  | 361 | 0 | 750 | 0 |  | X
11 | 11-2T3644 | 2T3644 | 11-SD-56-.3/3 |  |  | Granite Construction Company | 580 W Beach Street | Watsonville Ca 95076 |  | 8586881435 | 2863 Carmel Valley Rd | Del Mar, Ca 92014 | Steve Mcmillan | 20569 | 163395.18 | -2309.3 | 0 | 2025-10-20 | Construct Jpcp, Hma, Rhma-G, Signs, Barrie | San Diego County In San Diego From El Camino Real Undercrossing To 0.3 Mile Westof Carmel Valley Road Overcrossing | 55 | 94 | 16826573.51 | 17984025.07 | 17858375.16 | 53827 | 2026-09-29 | 2023-11-14 | 2023-10-17 |  |  | 302 | 0 | 550 | 0 |  | X
11 | 11-411904 | 411904 | 11-SD-56-.3/9.7 |  |  | Montano Pipeline Inc | 231 Fourth Ave | Chula Vista Ca 91910 | 6198386848 | 8586881435 | 2863 Carmel Valley Rd | Del Mar, Ca 92014 | Steve Mcmillan | 110154 | 91627.45 | 47459.42 | 0 | 2025-10-20 | Construct Rock Blanket, Fence, Striping, L | San Diego County At Various Locations Fromel Camino Real Undercrossing To Route 56/15 Separation | 89 | 92 | 2885750.69 | 3076495 | 3173507.09 | 55504 | 2025-12-09 | 2024-03-21 | 2024-02-13 |  |  | 290 | 0 | 325 | 0 |  | X
11 | 11-4B0054 | 4B0054 | 11-SD-67-3.9/6.1 |  |  | Griffith Company - Henkels & Mccoy Joint Venture | 3050 E. Birch St | Brea Ca 92821 |  | 8586881376 | 2863 Carmel Valley Road | Del Mar, Ca 92014 | Genaro Genel | 136522.46 | 0 | 0 | 2284.64 | 2025-10-20 | In San Diego County Near Santee On Route 6 | San Diego County Near Santee On Route 67 From Riverford Road Undercrossing To Lakeside Avenue | 13 | 5 | 138807.1 | 2814749.74 | 2814749.74 | 59035 | 2026-03-25 | 2025-03-12 | 2025-03-12 |  |  | 11 | 0 | 85 | 0 |  | X
11 | 11-2N0204 | 2N0204 | 11-SD-76-17.2/24.1 |  |  | Griffith Company | 3050 E. Birch St | Brea Ca 92821 |  | 6194032596 | 4050 Taylor St. | San Diego, Ca 92110 | Fahad Masud | 308999.78 | 0 | 0 | 0 | 2025-10-20 | Cold Plane And Overlay With Rhma Gap Grade | San Diego County Near Pala From Route 76/15 Separation To Pala Mission Road | 80 | 86 | 4403180.76 | 4422244 | 4440244 | 56071 | 2025-11-05 | 2024-07-12 | 2024-06-14 |  |  | 48 | 0 | 60 | 0 |  | X
11 | 11-431644 | 431644 | 11-SD-78-/N17.7 |  | ACNH-P078- (123)E | Skanska Usa Civil West California District Inc. | 1995 Agua Mansa Road | Riverside Ca 92509 |  | 8586881481 | 871 N. Brodway | Escondido, Ca 92025 | Yong Pak | 2526688.46 | 0 | 0 | 2550000 | 2025-10-20 | Sr-78 Asset Management | Pavement Rehab, Ada,Its, Op, Improvements,Complete Streets, Bridge Rail Upgrade, Safety | 16 | 16 | 16342634.1 | 102000000 | 102550000 | 58116 | 2028-01-31 | 2025-03-21 | 2025-02-25 |  |  | 104 | 0 | 670 | 0 |  | X
11 | 11-2N2244 | 2N2244 | 11-SD-79-.6/52.9 |  |  | Gba Engineering, Inc. | 18543 Yorba Linda Blvd #394 | Yorba Linda Ca 92886 |  | 6193185524 | 4050 Taylor Street | San Diego, Ca 92110 | Alex Balce | 27762 | 0 | 0 | 19000 | 2025-10-20 | Remove And Install Roadside Signs. | San Diego County Near Descanso From 0.6 Mile North Of Route 8/79 Separation To 0.1Mile South Of Riverside County Line | 9 | 8 | 46762 | 585835 | 585835 | 58297 | 2026-03-06 | 2025-05-23 | 2025-05-08 |  |  | 9 | 0 | 100 | 0 |  | X
11 | 11-430364 | 430364 | 11-SD-79-20.2/53 |  |  | Nationwide Contracting Services, Inc. Dba Nationwide General Construction Services | 7660 Liberty Dr | Huntington Beach Ca 92647 |  | 8586881433 | 7177 Opportunity Road | San Diego, Ca 92111 | Ryan Sresovich | 84687.22 | 0 | 0 | 0 | 2025-10-20 | Culvert Repair, Guardrail, Flashing Beacon | San Diego County At Various Locations Fromwest Junction Route 78 To Riverside Countyline | 33 | 14 | 870736.63 | 5969061 | 6114061 | 58076 | 2026-04-20 | 2025-05-09 | 2025-03-19 |  |  | 59 | 0 | 180 | 0 |  | X
11 | 11-2N2064 | 2N2064 | 11-SD-94-1.6/13.3 |  |  | Truesdell Corporation Of California, Inc. | 1310 W. 23Rd Street | Tempe Az 85282 |  | 6194032596 | 4050 Taylor Street | San Diego, Ca 92110 | Fahad Masud | 671993.6 | 0 | 0 | 14471.66 | 2025-10-20 | Polyester Concrete, Methacrylate, Joint Se | San Diego County At Various Locations From22Nd Street Overcrossing To Avocado Boulevard Overcrossing | 36 | 60 | 2247987.44 | 3659659 | 3668549 | 58875 | 2026-02-05 | 2025-06-17 | 2025-06-03 |  |  | 40 | 0 | 110 | 0 |  | X
11 | 11-430244 | 430244 | 11-SD-125-9.3/13 |  | B1NH-P125- (021)E | Hazard Construction Engr Llc | 10529 Vine Street | Lakeside Ca 92040 |  | 6196020333 | 817 Sweetwater Rd | Spring Valley, Ca 91977 | Sultan Ghazialam | 66586.87 | 754.8 | 0 | 0 | 2025-10-20 | Place Hma, Rhma, Slab Replacement, And Ele | San Diego County In And Near Lemon Grove From 0.3 Mile South Of Elkelton Place Undercrossing To 0.2 Mile South Of Route 125/94 Sep | 75 | 94 | 32435566 | 29997770.55 | 33324379.88 | 53044 | 2026-07-06 | 2023-10-05 | 2023-09-06 |  |  | 381 | 0 | 510 | 0 |  | X
11 | 11-411404 | 411404 | 11-SD-125-9.6/13.2 | HA | ACNH-P125- (020)E | Spectrum Construction Group, Inc. | 16 Goodyear, Suite 140 | Irvine Ca 92618 | 9492991400 | 6196020333 | 817 Sweetwater Road | Spring Valley, Ca 91977 | Sultan Ghazialam | 136237.93 | 0 | 0 | 0 | 2022-04-20 | Roadside Safety Improvements. | In San Diego County In San Diego And Lemon Grove From 0.1 Mile South Of Elkelton Place Undercrossing To Route 94/125 Separation | 16 | 21 | 672142.54 | 3086723.65 | 3186723.65 | 41864 | 2023-06-19 | 2021-09-14 | 2021-08-11 |  |  | 65 | 0 | 400 | 0 |  | X
11 | 11-4B0124 | 4B0124 | 11-SD-125-12.9/22.3 |  |  | Griffith Company - Henkels & Mccoy Joint Venture | 3050 E. Birch St | Brea Ca 92821 |  | 6196020333 | 817 Sweetwater Road | Spring Valley, Ca 91977 | Sultan Ghazialam | 515659.56 | 88425.26 | 0 | 0 | 2025-10-20 | Installation Of Fiber Optic Conduit System | San Diego County On Route 125 From 0.6 Mile South Of Spring Street Undercrossing Near La Mesa To Mission Gorge Road In Santee | 56 | 62 | 3832965.29 | 5594070.32 | 6153290.21 | 58835 | 2026-01-30 | 2025-03-12 | 2025-03-12 |  |  | 96 | 0 | 170 | 0 |  | X
11 | 11-4B0394 | 4B0394 | 11-SD-163-.7/3.1 |  |  | Griffith Company - Henkels & Mccoy Joint Venture | 3050 E. Birch St | Brea Ca 92821 |  | 8586881376 | 2863 Carmel Valley Road | Del Mar Ca 92014 | Genel Genaro | 309864.56 | 0 | 0 | 2885.46 | 2025-10-20 | Install Conduit, Fiber Optic Cable, Jct Bo | San Diego County On Route 5 From 0.3 Mile South Of Sweetwater River Bridge To 0.2 Mile South Of Sixth Avenue Overcrossing | 29 | 14 | 325835.54 | 2369990.29 | 2369990.29 | 58975 | 2026-01-16 | 2025-03-12 | 2025-03-12 |  |  | 23 | 0 | 80 | 0 |  | X
11 | 11-4B0384 | 4B0384 | 11-SD-163-3.1/10.9 |  |  | Griffith Company - Henkels & Mccoy Joint Venture | 3050 E. Birch St | Brea Ca 92821 |  | 8586881376 | 2863 Carmel Valley Road | Del Mar, Ca 92014 | Alfredo Hernandez Medina | 503148.57 | 0 | 0 | 0 | 2025-10-20 | Mmbn Project On Route 163-Phase 1. Install | San Diego County In San Diego From 0.6 Mile South Of Route 8/163 Separation To 0.1 Mile North Of Kearny Villa Road Overcrossing | 85 | 88 | 2056553.24 | 2035741.55 | 2039810.81 | 58915 | 2025-12-30 | 2025-03-12 | 2025-03-12 |  |  | 102 | 0 | 120 | 0 |  | X
11 | 11-430484 | 430484 | 11-SD-163-4.3/10.8 |  |  | Hazard Construction Engr Llc | 10529 Vine Street | Lakeside Ca 92040 |  | 8586881376 | 2863 Carmel Valley Road | Del Mar, Ca 92014 | Genaro Genel | 800 | 0 | 0 | 0 | 2025-10-20 | Upgrade Roadside Safety Elements, Electric | San Diego County In San Diego At Various Locations From 0.1 Mile South Of Friars Road Overcrossing To Kearny Villa Road Overcrossi | 63 | 100 | 8428670.54 | 7689119.28 | 8104619.28 | 54704 | 2026-04-21 | 2024-01-10 | 2023-12-06 |  |  | 245 | 0 | 390 | 0 |  | X
11 | 11-430234 | 430234 | 11-SD-805-.1/14.6 |  | ACIM-8051- (647)E | Griffith Company | 3050 E. Birch St | Brea Ca 92821 |  |  |  |  | Jason Alsheikh | 0 | 0 | 0 | 0 |  | Replace Conc Pvmt, Construct Aux Lane & Bi | San Diego County In San Diego, Chula Vistaand National City From 0.3 Mile South Of Route 805/5 Separation To Route 805/15 Separati | 0 | 0 | 0 | 138758858 | 138758858 | 60132 |  | 2025-10-23 | 2025-10-02 |  |  | 0 | 0 | 1150 | 0
11 | 11-2N1714 | 2N1714 | 11-SD-805-.5/14.6 |  |  | Peterson-Chase General Engineering Construction, Inc. | 16351 Construction Circle Wes | Irvine Ca 92606 |  | 9166394314 | 4050 Taylor St | San Diego, Ca 92110 | John Tran | 278033.92 | 0 | 0 | 0 | 2025-10-20 | Methacrylate Replace Approach Slabs, Joint | San Diego County At Various Locations Fromsouth Route 805/5 Separation To Route 805/15 Separation | 71 | 82 | 8104037.88 | 9224063.6 | 9523045.59 | 56101 | 2025-12-31 | 2024-07-24 | 2024-06-28 |  |  | 120 | 0 | 170 | 0 |  | X
11 | 11-2T3434 | 2T3434 | 11-SD-805-5.1/8.3 |  | TPLN-6211- (139)000 | Walsh Construction Company Ii,Llc | 1390 Willow Pass Road Suite 9 | Concord Ca 94520 |  | 8586881511 | 817 Sweetwater Road | Spring Valley, Ca 91977 | Tan Cao | 911638.05 | 34805.51 | 0 | 0 | 2025-10-20 | Soundwalls, Widen Freeway, Structures, Lan | San Diego County In Chula Vista From Palomar Street Overcrossing To 0.5 Mile North Of Bonita Road Undercrossing | 42 | 47 | 15765908.9 | 32678020 | 33303317.45 | 55344 | 2027-12-31 | 2024-02-28 | 2024-01-29 |  |  | 360 | 0 | 850 | 0 |  | X
11 | 11-432944 | 432944 | 11-SD-805-11.2/13.3 | 20.80 240000 |  | Lb Civil Construction, Inc. | 324 East Valley Parkway | Escondido, Ca 92025 | 7602940974 | 6199910827 | 4050 Taylor Street | San Diego, Ca 92110 | Carlos G. Lopez | 0 | 0 | 0 | 0 |  | Install Encampment Exclusionary Mearusres | Install Encampment Exclusionary Mearusres Along I-805 From Division St To Hilltop Drsan Diego County Dir'S Emergency L.B. | 0 | 0 | 0 | 10000 | 985000 | 60154 | 2026-09-16 | 2025-10-09 | 2025-09-22 |  |  | 0 | 0 | 60 | 0
11 | 11-430324 | 430324 | 11-SD-805-14.6/23.7 |  | ACIM-8051- (645)E | Coffman Specialties, Inc. | 9685 Via Excelencia, Suite 20 | San Diego Ca 92126 |  | 6199957332 | 1463 Broadway | El Cajon, Ca 92021 | Art Pannu | 1238498.02 | 7968.59 | 0 | 0 | 2025-10-20 | Modify Electrical, Concrete Pavement, Drai | San Diego County In San Diego From Route 805/15 Separation To 0.1 Mile North Of Route 805/52 Separation | 28 | 30 | 23123560.82 | 76865000 | 76967191.27 | 56335 | 2027-10-21 | 2024-09-10 | 2024-08-23 |  |  | 195 | 0 | 700 | 0 |  | X
11 | 11-430384 | 430384 | 11-SD-805-23.7/28.5 |  | ACIM-805 - (1 )646 | Hazard Construction Engr, Llc | 10529 Vine Street | Lakeside Ca 92040 |  | 8586881443 | 5377 Otay Mesa Rd | San Diego, Ca 92154 | Tai Lam | 2012738.07 | 6267.18 | 0 | 0 | 2025-10-20 | Replace Drainage, Concrete Pavement, And M | San Diego County In San Diego From 0.1 Mile North Of Route 805/52 Separation To Route 5/805 Separation | 25 | 55 | 19860315.81 | 34966331.1 | 35415373.86 | 56682 | 2027-12-31 | 2024-10-30 | 2024-10-09 |  |  | 176 | 0 | 695 | 0 |  | X
11 | 11-430394 | 430394 | 11-SD-805-23.9/25.1 |  | ACIM-805 - (1 )644 | Griffith Company | 12200 Bloomfield Ave | Santa Fe Springs Ca 90670 |  | 7605942021 | 817 Sweetwater Rd | Spring Valley, Ca 91977 | Tyler Jones | 2800 | 55300.56 | 0 | 0 | 2025-10-20 | Widen Freeway, Structures, Construct Signs | San Diego County In San Diego From 0.2 Mile North Of Route 805/52 Separation To 0.3 Mile South Of Nobel Drive Overcrossing | 72 | 98 | 23108642.19 | 22322322 | 23304865.41 | 54044 | 2026-06-02 | 2023-11-30 | 2023-11-03 |  |  | 405 | 0 | 565 | 0 |  | X
11 | 11-431064 | 431064 | 11-SD-905-6.4/10.1 |  | ACNH-P905- (023)E | Griffith Company | 3050 East Birch Street | Brea Ca 92821 | 7149845500 | 8586881366 | 5377 Otay Mesa Rd | San Diego, Ca 92154 | Karl Hartline | 2660 | 0 | 0 | 0 | 2023-09-20 | Construct Sr-905 Landscaping At | In San Diego County In San Diego From 0.3 Mile West Of Caliente Avenue Overcrossing To 0.4 Mile East Of La Media Road Undercrossi | 0 | 0 | 4088824.27 | 4247463.1 | 4421333.35 | 43606 | 2026-08-26 | 2022-08-02 | 2022-07-11 |  |  | 518 | 0 | 870 | 0 | X | X
11 | 11-432024 | 432024 | 11-SD--/0 | 20.20 201130 |  | E-4 Construction Inc Dba Cali Construction | 12935 Pomerado Rd Suite C | Poway, Ca 92064 | 6192082401 | 8586881480 | 4050 Taylor St | San Diego, Ca 92110 | Kemp, Lauren | 36000 | 0 | 0 | 0 | 2024-05-20 | Tree Removal | In San Diego County And Imperial County On Various Routes At Various Locations Tree Removal Dir'S Emergency L.B. | 46 | 98 | 1947224.77 | 60000 | 1985000 | 53605 | 2025-06-30 | 2023-10-27 | 2023-06-30 |  |  | 91 | 0 | 200 | 0 |  | X
11 | 11-2N2254 | 2N2254 | 11-VAR--/0 |  |  | Specialized Pavement Marking, Llc | 11095 Sw Industrial Way, Suit | Tualatin Or 97062 |  | 7605942006 | 1102 Montenegro Way | El Centro, Ca 92243 | Jose G. Sillas | 0 | 0 | 0 | 0 |  | Install Rumble Strips And Place Pavement D | San Diego And Imperial Counties At Variouslocations | 0 | 0 | 0 | 1168200 | 1168200 | 59339 | 2026-05-25 | 2025-07-08 | 2025-04-18 |  |  | 0 | 0 | 55 | 0
11 | 11-430904 | 430904 | 11-VAR--/0 |  |  | J. Francis Company | 16197 Krameria Ave. | Riverside Ca 92504 |  | 6199367037 | 2863 Carmel Valley Road | Del Mar, Ca 92014 | Navid Borzouei | 909589.83 | 0 | 0 | 0 | 2025-10-20 | Resurface Bridge, Replace Bridge Barrier, | San Diego County At Various Locations | 33 | 82 | 6982746.18 | 8454740.75 | 8665219.28 | 57315 | 2026-08-28 | 2025-03-13 | 2025-02-12 |  |  | 107 | 0 | 325 | 0 |  | X
11 | 11-2N1774 | 2N1774 | 11-VAR--/0 |  |  | Griffith Company | 3050 E. Birch St | Brea Ca 92821 |  | 6194559259 | 4050 Taylor St. | San Diego, Ca 92110 | Peris Salih | 3944.33 | 0 | 0 | 0 | 2025-10-20 | Micro-Surfacing, Hma, Pavement Marking And | San Diego County At Various Locations | 100 | 94 | 2940488.58 | 3314000 | 3115807.88 | 56311 | 2025-11-07 | 2024-09-04 | 2024-06-24 |  |  | 71 | 0 | 55 | 3 |  | X
11 | 11-2N2334 | 2N2334 | 11-VAR--/0 |  |  | Pavement Coatings Co. | 10240 San Sevaine Way | Jurupa Valley Ca 91752 |  | 6194032596 | 4050 Taylor Street | San Diego, Ca 92110 | Fahad Masud | 415745.4 | 0 | 0 | 2500 | 2025-10-20 | Microsurfacing, Cold Plane, Hma Type A, Si | San Diego County At Various Locations | 84 | 63 | 690976.56 | 1061767.95 | 1239567.84 | 58815 | 2025-10-30 | 2025-06-12 | 2025-05-22 |  |  | 42 | 0 | 50 | 0
11 | 11-2N2074 | 2N2074 | 11-VAR--/0 |  |  | Truesdell Corporation Of California, Inc. | 1310 W. 23Rd Street | Tempe Az 85282 |  | 6194559259 | 4050 Taylor Street | San Diego, Ca 92110 | Peris Salih | 130671 | 0 | 0 | 0 | 2025-10-20 | Grind Bridge Decks, Polyester Concrete Ove | San Diego County At Various Locations | 41 | 61 | 2580937.62 | 4197197 | 4251197 | 58599 | 2026-01-08 | 2025-06-09 | 2025-05-23 |  |  | 37 | 0 | 90 | 0 |  | X
11 | 11-432454 | 432454 | 11-VAR--/0 | 20.10 201352 |  | Sb General Engineering, Inc. | Po Box 1400 | Lakeside, Ca 92040 |  | 6198574332 | 4050 Taylor Street | San Diego, Ca 92110 | Jodi Nelmark | 0 | 0 | 0 | 0 | 2025-06-26 | Security Measures | Do - Emergency - Security Measures In San Diego And Imperial County At Various Maintenance Stations Dir'S Emergency L.B. | 3 | 70 | 2497758.03 | 21012 | 3585000 | 56069 | 2025-12-31 | 2024-06-24 | 2024-05-17 |  |  | 5 | 0 | 150 | 0 |  | X
12 | 12-0V4404 | 0V4404 | 12-0RA-241-30.0/31 | 20.XX 201130 |  | Powell Constructors Inc | 8555 Banana Avenue | Fontana, Ca 92335 | 9093568880 | 9493929174 | 15700 Tustin Village Way, #2 | Tustin, Ca 92780 | Tran, Tuan/Ce-Kim, Steven | 0 | 0 | 0 | 0 | 2025-10-20 | Reconstruct The Failed Slope And Roadway. | In Orange County, On Northbound Sr241 Justsouth Of Loma Ridge Toll Plaza. Reconstruct The Failed Slope And Roadway. Dir'S Order E | 93 | 22 | 1420026.23 | 29456 | 6592000 | 57258 | 2025-11-25 | 2025-01-29 | 2025-01-23 |  |  | 168 | 0 | 180 | 0
12 | 12-0R3114 | 0R3114 | 12-LA-91-20.6/20.7 |  | ACNH-P091- (159)E | Beador Construction Company, Inc. | 2900 Bristol Street, Suite D2 | Costa Mesa Ca 92626 | 9516747352 | 5624497999 | 15700 Tustin Village Way | Tustin, Ca 92780 | Luna, Franklin | 1554150.94 | 22018.5 | 0 | 0 | 2025-10-20 | Place Jpcp (Rsc) And Rhma, And Modify Elec | Los Angeles And Orange Counties From 0.1 Mile West Of The Los Angeles County Line In Cerritos To 0.1 Mile East Of Acacia Street Un | 18 | 37 | 15861150.96 | 42861700 | 42991700 | 57455 | 2027-10-01 | 2025-03-14 | 2025-03-03 |  |  | 117 | 0 | 660 | 0 |  | X
12 | 12-0Q9904 | 0Q9904 | 12-ORA-1-.1/.9 |  | ACNH-P001- (690)E | Accu Construction, Inc. | 14751 Plaza Drive Suite L | Tustin Ca 92780 |  | 9492798638 | 4 Venture #150 | Irvine, Ca 92618 | Joubeen, Jay/Ce- Ware, E | 3200 | 0 | 0 | 0 | 2025-10-20 | Planting, Irrigation, Rock Blanket, Gravel | Orange County In Dana Point And San Juan Capistrano From Camino Las Ramblas Undercrossing To 0.1 Mile West Of Doheny Park Road Und | 92 | 99 | 4025066.96 | 3876585.5 | 4052269.41 | 52384 | 2025-12-23 | 2023-09-06 | 2023-08-16 |  |  | 459 | 0 | 500 | 0 |  | X
12 | 12-0S7504 | 0S7504 | 12-ORA-1-.8/0 |  | ACNH-P001- (697)E | Beador Construction Company, Inc. | 2900 Bristol Street D204 | Costa Mesa Ca 92626 | 9516747352 | 9492798466 | 4 Venture, Suite 150 | Irvine, Ca 92618 | Sidhu,Gangadeep/Ce-Essayli, M. | 0 | 12494.06 | 0 | 0 | 2025-10-20 | Modify Traffic Signal, Lighting, Curb Ramp | Orange County In Dana Point At Doheny Parkroad Undercrossing | 75 | 88 | 2830499.18 | 3095300 | 3210300 | 56122 | 2025-12-15 | 2024-07-19 | 2024-07-02 |  |  | 112 | 0 | 150 | 0 |  | X
12 | 12-0P69U4 | 0P69U4 | 12-ORA-1-5.5/7.9 |  | ACST-P001- (680)E | Griffith Company | 12200 Bloomfield Ave | Santa Fe Springs Ca 90670 |  | 4244131143 | 15700 Tustin Village Way | Tustin, Ca 92780 | Merati, Artin | 67484.03 | 32112.26 | 0 | 0 | 2025-10-20 | Reconstruct Curb Ramps And Cold Plane Pave | Orange County In Laguna Beach From 7Th Avenue To Ruby Street | 81 | 71 | 11990877.37 | 16163520 | 16483174.65 | 50527 | 2026-01-12 | 2023-06-08 | 2023-04-20 |  |  | 324 | 0 | 400 | 0 |  | X
12 | 12-0M82U4 | 0M82U4 | 12-ORA-1-7.9/10.5 |  | ANCH-P001- (673)E | Spectrum Construction Group, Inc. | 16 Goodyear, Ste. 140 | Irvine Ca 92618 | 9492991400 | 9492798502 | 15700 Tustin Village Way | Tustin Ca 92780 | Berrios, Jose/Ce- Zokai, Farid | 15840 | 0 | 0 | 0 | 2022-04-20 | Upgrade Sidewalk To Americans With | In Orange County In Laguna Beach, On State Route 1 (Also Known As Pacific Coast Highway Or Sr-1) From Ruby Street (Pm 7.9) To Led | 30 | 13 | 1218562.4 | 9580910.45 | 9668673.33 | 41453 | 2023-06-01 | 2021-02-18 | 2021-01-26 |  |  | 127 | 0 | 430 | 0 |  | X
12 | 12-0P68U4 | 0P68U4 | 12-ORA-1-13.0/33.7 |  | ACST- P00- (682)E | Chumo Construction Inc. | 14425 Joanbridge Street | Baldwin Park Ca 91706 |  | 9492798880 | 4 Venture Ste 150 | Irvine, Ca 92618 | Blanco, Chris/Ce- Karam, Imad | 1171219.96 | 8826.36 | 0 | 0 | 2025-10-20 | Cold Plane, Place Rhma And Modify Curb Ram | Orange County At Various Locations From Crystal Heights Drive To Los Angeles/Orange County Line | 100 | 92 | 35296540.2 | 36829575.68 | 38212036.44 | 52104 | 2025-12-05 | 2023-08-23 | 2023-07-12 |  |  | 374 | 0 | 330 | 0 |  | X
12 | 12-0S1404 | 0S1404 | 12-ORA-1-21.5/31.1 |  | HSNH-P001- (700)E | Chumo Construction Inc. | 14425 Joanbridge Street | Baldwin Park Ca 91706 | 6269609502 | 9492795213 | 4 Venture Suite 150 | Irvine, Ca 92618 | Karam, Imad | 34580 | 0 | 0 | 0 | 2025-09-20 | Install Conc Barrier, Curb, Hma Pvmt, Traf | Orange County In And Near Huntington Beachand Seal Beach From Santa Ana River Bridgeto Anderson Street And At Seal Beach Boulevard | 1 | 0 | 34580 | 10578115.72 | 10578115.72 | 56826 | 2026-07-07 | 2024-11-20 | 2024-10-22 |  |  | 4 | 0 | 450 | 0 |  | X
12 | 12-0P42U4 | 0P42U4 | 12-ORA-5-.6/43 |  | ACNH-X059- (083)E | International Line Builders, Inc. | 3955 Temescal Canyon Road | Corona Ca 92883 | 9516822982 | 9492798801 | 3350 E. Birch Street, Ste 250 | Brea, Ca 02821 | Chaudry, Monas | 24805 | 7471.3 | 0 | 0 | 2025-10-20 | Install & Modify Its Elements | In Orange County At Various Locations | 100 | 96 | 20377731.59 | 15999144.99 | 21207337.9 | 41306 | 2025-12-30 | 2020-10-02 | 2020-09-15 |  |  | 1010 | 0 | 760 | 193 |  | X
12 | 12-0T8604 | 0T8604 | 12-ORA-5-2.3/19.9 |  |  | Peterson-Chase General Engineering Construction, Inc. | 16351 Construction Circle Wes | Irvine Ca 92606 |  | 9492798502 | 15700 Tustin Village Way | Tustin, Ca | Merati, Artin | -17940 | 21348.6 | 0 | 0 | 2025-10-20 | Apply Methacrylate And Polyester Concrete | Orange County At Various Locations From Avenida Presidio Undercrossing To Lake Forest Drive Overcrossing | 67 | 29 | 744386.16 | 2386997.7 | 2530406.3 | 55789 | 2025-10-25 | 2024-05-13 | 2024-03-13 |  |  | 60 | 0 | 90 | 0 |  | X
12 | 12-0S1704 | 0S1704 | 12-ORA-5-5.3/7.3 |  | HSIM-0052- (039)E | Chumo Construction Inc. | 14425 Joanbridge Street | Baldwin Park Ca 91706 |  | 9492798433 | 4 Venture, Ste 150 | Irvine, Ca 92618 | Mazdiyasni, Omid/Ce- Karam, I | 9053.24 | 0 | 0 | 0 | 2025-10-20 | Replace Median Concrete Barrier And Instal | Orange County From 0.5 Mile South Of Camino De Estrella In San Clemente To 0.5 Mile North Of Route 1 In San Juan Capistrano | 100 | 95 | 5026528.6 | 4801389.98 | 5266606.21 | 51804 | 2025-12-01 | 2023-08-11 | 2023-07-18 |  |  | 249 | 0 | 250 | 0 |  | X
12 | 12-0U9204 | 0U9204 | 12-ORA-5-6.5/0 |  | HSIM-0052- (051)E | Ptm General Engineering Services, Inc. | 5942 Acorn St. | Riverside Ca 92504 | [5 empty] | 0 | 0 | 0 | 0 |  | Signal Modification And Sign Installation. | Orange County In San Juan Capistrano At 0.2 Mile South Of Route 5/1 Separation Andat 0.4 Mile North Of Route 5/1 Separation | 0 | 0 | 0 | 488088 | 488088 | 58776 |  | 2025-06-12 | 2025-05-15 |  |  | 0 | 0 | 50 | 0
12 | 12-0S2804 | 0S2804 | 12-ORA-5-9.6/10.4 |  | HSIM-0052- (045)E | Powell Constructors Inc | 8555 Banana Avenue | Fontana Ca 92335 |  | 9492798640 | 4 Venture, Ste 150 | Irvine, Ca 92618 | Vazquez, Luis/Ce- Karam, Imad | 213930 | 0 | 0 | 0 | 2025-10-20 | Add Secondary Auxiliary Lane. | Orange County In San Juan Capistrano From Route 74/5 Separation To 0.5 Mile South Ofjunipero Serra Road Undercrossing | 79 | 68 | 3755861.45 | 5075573 | 5463302.01 | 56121 | 2026-01-28 | 2024-07-22 | 2024-06-24 |  |  | 230 | 0 | 290 | 0 |  | X
12 | 12-0K0244 | 0K0244 | 12-ORA-5-12.4/18.9 |  |  | Diverscape, Inc. Dba Diversified Landscape Co. | 21730 Bundy Canyon Road | Wildomar Ca 92595 |  | 9493929174 | 15700 Tustin Village Way | Tustin, Ca 92780 | Tran, Tuan/Ce- Kim, Steven | 880156.85 | 0 | 0 | 98100 | 2025-10-20 | Replace Landscaping And Irrigation. Instal | Orange County From 0.5 Mile South Of Averyparkway Undercrossing In San Juan Capistrano To 0.2 Mile North Of El Toro Road Undercros | 30 | 33 | 2768569.2 | 8312913.3 | 8554934.32 | 58715 | 2029-07-03 | 2025-06-10 | 2025-05-07 |  |  | 75 | 0 | 1000 | 0 |  | X
12 | 12-0K0234 | 0K0234 | 12-ORA-5-17.1/18.9 |  | TPLN-6212- (024) | Guy F Atkinson Construction Llc | 18201 Von Karman Avenue | Irvine Ca 92612 | 7032161395 | 9492893551 | 320 Goddard Way Suite 125 | Irvine, Ca 92618 | Nguyen, Irvin | 36647.5 | 431924.5 | 2002096.82 | 0 | 2025-10-20 | Widen Freeway And Bridges, | In Ora Co In Mission Viejo, Laguna Woods And Lake Forest From 0.4 Mile South Of Alicia Parkway Oc To 0.2 Mile North Of El Toro Roa | 81 | 97 | 113614230.69 | 90405498 | 116344750.42 | 41303 | 2025-12-16 | 2020-10-13 | 2020-09-23 |  |  | 1093 | 0 | 1000 | 343 |  | X
12 | 12-0S3104 | 0S3104 | 12-ORA-5-26.3/42.2 |  | HSIM-0052- (044)E | Autobahn Construction Inc. | 933 N. Batavia St. | Orange Ca 92867 |  | 9492798491 | 15700 Tustin Village Way | Tustin, Ca | Ruba, Nabil/Ce- Merati, Artin | 21928 | 0 | 0 | 0 | 2025-10-20 | Refresh Pavement Delineation, Replace Sign | Orange County At Various Locations From Culver Driver Overcrossing In Irvine To Route 91/5 Separation In Fullerton | 99 | 92 | 2272661.25 | 2341485 | 2376485 | 55787 | 2025-11-30 | 2024-05-13 | 2024-03-22 |  |  | 138 | 0 | 140 | 0 |  | X
12 | 12-0J34U4 | 0J34U4 | 12-ORA-5-29.6/29.6 |  | ACNH-X059- (084)E | Security Paving Company, Inc. | 3075 Townsgate Road | Westlake Village Ca 91361 | 8183629200 | 9492798488 | 1221 E. Dyer Road, Suite #265 | Santa Ana, Ca 92705 | Wu, Adrian | 3760423.46 | 97192.01 | 0 | 0 | 2025-10-20 | Construct Northbound Auxiliary Lane | In Orange County In Irvine, Santa Ana, And Tustin On Rte 5 At Newport Ave Undercrossing And On Rte 55 From 0.4 Mi North Of Rte 55 | 62 | 58 | 117336841.78 | 193587475.71 | 200687066.51 | 42479 | 2028-03-23 | 2022-06-16 | 2022-05-27 |  |  | 582 | 0 | 880 | 54 |  | X
12 | 12-0S6904 | 0S6904 | 12-ORA-5-35.7/44.1 |  | HSIM-0052- (046)E | Bc Rentals Llc Dba Bc Traffic Specialist | 13261 Garden Grove Blvd | Garden Grove Ca 92843 | 9519075163 | 9492798821 | 15700 Tustin Village Way, #2 | Tustin, Ca 92780 | Tran, Tuan/Ce-Kim, Steven | 1050 | 0 | 0 | 0 | 2025-10-20 | Install Pavement Delineation, Striping And | Orange County At Various Locations From 0.9 Mile North Of Chapman Avenue To Artesia Boulevard | 95 | 82 | 922313.75 | 1097531 | 1134742 | 56323 | 2025-10-31 | 2024-09-10 | 2024-08-09 |  |  | 142 | 0 | 150 | 0 |  | X
12 | 12-0S8404 | 0S8404 | 12-ORA-5-36.7/0 |  | HSIM-0052- (052)E | Baker Electric & Renewables, Llc | 1298 Pacific Oaks Place | Escondido Ca 92029 | [5 empty] | 0 | 0 | 0 | 0 |  | Modify Existing Traffic Signals, Curb Ramp | Orange County In Anaheim 0.1 Mile North Ofanaheim Boulevard Undercrossing | 0 | 0 | 0 | 1140951 | 1140951 | 59655 |  | 2025-08-12 | 2025-06-11 |  |  | 0 | 0 | 210 | 0
12 | 12-0S1104 | 0S1104 | 12-ORA-22-.9/9.4 |  | HSNH-P022- (031)E | Beador Construction Company, Inc. | 2900 Bristol Street D204 | Costa Mesa Ca 92626 |  | 5624497999 | 15700 Tustin Village Way | Tustin, Ca 92780 | Luna, Franklin | 1880486.1 | 33953.03 | 0 | 0 | 2025-10-20 | Replace Concrete Barrier And Modify Lighti | Orange From Bolsa Chica Road Overcrossing In Garden Grove To Lewis Street Overcrossing In Orange | 48 | 57 | 16758360.66 | 29300700 | 29475700 | 56534 | 2026-09-25 | 2024-10-10 | 2024-09-04 |  |  | 217 | 0 | 450 | 0 |  | X
12 | 12-0S7004 | 0S7004 | 12-ORA-22-8.6/0 |  | ACNH-P022- (032)E | Autobahn Construction, Inc. | 933 N. Batavia St. | Orange Ca 92867 |  | 9492798744 | 15700 Tustin Village Way | Tustin, Ca 92780 | Ezzedine, Mike/Ce- Luna, Frank | 0 | 0 | 0 | 0 |  | Install High Friction Surface Treatment At | Orange County In Garden Grove At 0.2 Mile West Of Garden Grove Boulevard Undercrossing | 0 | 0 | 0 | 395976 | 395976 | 57156 | 2025-10-09 | 2025-02-12 | 2025-01-09 |  | S | 0 | 0 | 50 | 0
12 | 12-0S1904 | 0S1904 | 12-ORA-22-11.6/12.5 |  | HSNH-P022- (030)E | Ortiz Enterprises, Inc. | 6 Cushing Suite 200 | Irvine Ca 92618 |  | 9515297048 | 15700 Tustin Village Way | Tustin, Ca 92780 | Luna. Franklin | 550 | 21255.36 | 0 | 0 | 2025-10-20 | Auxiliary Lane Extension. | Orange County In Santa Ana And Orange From0.1 Mile West Of Santiago Creek To 0.2 Mile East Of Cambridge Street Overcrossing | 56 | 100 | 7335473.96 | 6851174.28 | 7286480.91 | 56070 | 2026-02-24 | 2024-07-12 | 2024-06-06 |  |  | 262 | 0 | 320 | 145 |  | X
12 | 12-0U9704 | 0U9704 | 12-ORA-22-/5.1 |  |  | Alfaro Communications Construction, Inc. | 15614 S. Atlantic Avenue | Compton Ca 90221 |  | 5624497999 | 15700 Tustin Village Way | Tustin, Ca 92780 | Luna, Franklin | 150811.84 | 0 | 0 | 0 | 2025-10-20 | Place Jpcp(Rsc) Random, Lcb, Rhma, Remove | Orange County From Los Angeles County Lineto 0.1 Mile East Of Route 22/605 Separation And From Bolsa Chica Road Overcrossing To 0. | 99 | 83 | 1940747.24 | 2333678.8 | 2333678.8 | 57081 | 2025-11-07 | 2025-02-03 | 2024-12-24 |  |  | 69 | 0 | 70 | 0
12 | 12-0R32U4 | 0R32U4 | 12-ORA-55-.2/17.8 |  | ACNH-P055- (067)E | R.J. Noble Company | 15505 East Lincoln Avenue | Orange Ca 92856 |  | 9492798488 | 15700 Tustin Village Way | Tustin, Ca 92780 | Wu, Adrian | 2080750 | 89569.99 | 0 | 0 | 2025-10-20 | Cold Plane, Place Rhma, Replace Cb, Signs | Orange County From 0.1 Mile South Of Route55/1 Separation In Newport Beach To Route 55/91 Separation In Anaheim | 12 | 9 | 9700068.35 | 106148205.6 | 106328205.6 | 57395 | 2027-04-03 | 2025-03-18 | 2025-02-07 |  |  | 90 | 0 | 750 | 0 |  | X
12 | 12-0U5804 | 0U5804 | 12-ORA-55-12.3/17 |  |  | Myers & Sons Construction, Llc | 45 Morrison Ave | Sacramento Ca 95838 |  | 9492798766 | 15700 Tustin Village Way | Tustin, Ca 92780 | Wu, Adrian | 1070892.53 | 0 | 0 | 0 | 2025-09-20 | Apply Methacrylate, Overlay Polyester & Re | Orange County At Various Locations On Route 55 From Santa Clara Avenue Overcrossing To Lincoln Avenue Undercrossing And On Route 5 | 69 | 86 | 3279045.65 | 3615614 | 3741053 | 57835 | 2025-10-29 | 2025-04-21 | 2025-03-28 | 2025-10-29 |  | 62 | 0 | 90 | 0 |  | X
12 | 12-0U8104 | 0U8104 | 12-ORA-57-11.0/22.5 |  |  | Autobahn Construction, Inc. | 933 N. Batavia St. | Orange Ca 92867 |  | 9492798502 | 15700 Tustin Village Way | Tustin, Ca | Berrios, Jose/Ce-Merati, Artin | 377133.3 | 0 | 0 | 0 | 2025-10-20 | Remove And Replace Rhma, Pavement Marking | Orange County At Various Locations From Route 5/22/57 Separation To 0.3 Mile Southof Los Angeles County Line | 100 | 94 | 1654277.1 | 1723320 | 1723320 | 58339 | 2025-10-30 | 2025-05-23 | 2025-04-17 |  |  | 60 | 0 | 60 | 0 |  | X
12 | 12-0S3304 | 0S3304 | 12-ORA-57-11.0/22.6 |  | HSNH-P057- (075)E | Chumo Construction Inc. | 14425 Joanbridge Street | Baldwin Park Ca 91706 |  | 9492798491 | 15700 Tustin Village Way | Tustin, Ca | Ruda, Nabil/Ce- Merati, Artin | 923297.51 | 40352.9 | 0 | 0 | 2025-10-20 | Modify Lighting And Replace Pavement Delin | Orange County In Orange And Brea From 0.2 Mile South Of Chapman Avenue Undercrossingto Orange County Line | 64 | 87 | 7900478.14 | 8661572.2 | 8900400.64 | 55921 | 2025-12-08 | 2024-06-05 | 2024-05-03 |  |  | 128 | 0 | 200 | 0 |  | X
12 | 12-0M9704 | 0M9704 | 12-ORA-57-11.5/12.5 |  | TPLN-6212- (027)000 | Ortiz Enterprises, Inc. | 6 Cushing Suite 200 | Irvine Ca 92618 | [5 empty] | 0 | 0 | 0 | 0 |  | Const Bridges, Ret Walls, Jpcp, Hma, Conc | Orange County In Orange And Anaheim From 0.2 Mile South Of Orangewood Avenue Undercrossing To Katella Avenue Undercrossing | 0 | 0 | 0 | 68141634.66 | 68141634.66 | 60121 |  | 2025-10-13 | 2025-09-25 |  |  | 0 | 0 | 825 | 0
12 | 12-0S5304 | 0S5304 | 12-ORA-57-15.9/0 |  | HSNH-P057- (077)E | Granite Construction Company | 4820 Mcgrath St., Suite 101 | Ventura Ca 93003 | 8317684020 | 9492798502 | 15700 Tustin Village Way | Tustin, Ca | Berrios, Jose/Ce- Merati,Artin | 0 | 0 | 0 | 0 |  | Place Jpcp (Rsc) And Hma, Modify Ramp And | Orange County In Anaheim At Southbound Route 57 Off-Ramp To Westbound Route 91 | 0 | 0 | 0 | 5295527 | 5295527 | 60081 | 2026-10-15 | 2025-09-22 | 2025-09-05 |  |  | 0 | 0 | 240 | 0
12 | 12-0U9804 | 0U9804 | 12-ORA-57-19.6/20.1 |  |  | R.J. Noble Company | 15505 East Lincoln Avenue | Orange Ca 92856 | 7146371550 | 9498928208 | 15700 Tustin Village Way | Tustin, Ca 92780 | Tai, Vuong | 0 | 0 | 0 | 0 |  | Cold Plane And Overlay Existing Pavement W | Orange County In Brea And Fullerton On Route 57 From Associated Road Undercrossing To 0.2 Mile South Of Birch Street Undercrossing | 0 | 0 | 0 | 1009857 | 1009857 | 57006 | 2025-12-05 | 2025-01-15 | 2024-12-11 |  | S | 0 | 0 | 60 | 0
12 | 12-0C1114 | 0C1114 | 12-ORA-57-20.3/21.6 |  |  | Diversified Landscape Co. | 21730 Bundy Canyon Road | Wildomar Ca 92595 | 9512451686 | 9493929229 | 15700 Tustin Village Way | Tustin, Ca 92780 | Pham, Theodore/Ce- Kim, Steven | 1460 | 0 | 0 | 0 | 2025-10-20 | Placement Planting And New | In Orange County In Brea At Lambert Road | 0 | 0 | 1012295.02 | 998968.5 | 1052014.46 | 43424 | 2026-11-19 | 2022-07-19 | 2022-06-22 |  |  | 357 | 0 | 680 | 0 | X | X
12 | 12-0U5904 | 0U5904 | 12-ORA-73-10.3/26.8 |  |  | Peterson-Chase General Engineering Construction, Inc. | 16351 Construction Circle Wes | Irvine Ca 92606 |  | 9492798590 | 4 Venture Ste 135 | Irvine, Ca 92618 | Shahidi, Mona/Ce Nguyen, Irvin | 330297.38 | 0 | 0 | 3550 | 2025-10-20 | Apply Methacrylate, Replace Joint Seals & | Orange County At Various Locations From S73-S5 Connector Viaduct In Laguna Niguel To Bristol Street Undercrossing In Costa Mesa | 98 | 72 | 913129.37 | 1240447.68 | 1250447.68 | 58336 | 2025-10-21 | 2025-05-23 | 2025-04-02 |  | S | 78 | 0 | 80 | 0
12 | 12-0U9104 | 0U9104 | 12-ORA-73-23.5/23.8 |  | HSNH-P073- (142)E | Chumo Construction, Inc. | 14425 Joanbridge Street | Baldwin Park Ca 91706 |  | 9492893551 | 4 Venture Ste 150 | Irvine, Ca 92618 | Ware, Elizabeth | 211043.43 | 0 | 0 | 5000 | 2025-10-20 | Construct Concrete Barrier And Install Dra | Orange County In Irvine From Bison Avenue Overcrossing To Macarthur Boulevard Overcrossing | 63 | 78 | 762865.88 | 979819.35 | 979819.35 | 58775 | 2025-12-04 | 2025-06-10 | 2025-05-13 |  |  | 47 | 0 | 75 | 0 |  | X
12 | 12-0P0314 | 0P0314 | 12-ORA-74-11.5/16.6 |  | ACST-S074- (076)E | Pacific Restoration Group, Inc. | 506 W Graham Avenue, Suite 20 | Lake Elsinore Ca 92530 | 9514574118 | 9492798511 | 10681 Pamela Street | Cypress, Ca 90630 | Nowak, John/Ce-Karam, Imad | 10494 | 0 | 0 | 0 | 2025-10-20 | Establish Existing Planting. | Orange County Near San Juan Capistrano From 1.0 Mile West Of San Juan Hot Springsroad To Riverside County Line | 21 | 34 | 187585.25 | 553475 | 553475 | 56315 | 2028-09-08 | 2024-09-04 | 2024-08-07 |  |  | 214 | 0 | 1000 | 0 |  | X
12 | 12-0V0404 | 0V0404 | 12-ORA-90-5.4/0 |  |  | Beador Construction Company, Inc. | 2900 Bristol Street, Suite D2 | Costa Mesa Ca 92626 |  | 9498928208 | 15700 Tustin Village Way | Tustin, Ca 92780 | Merati, Artin | 5496.75 | 0 | 0 | 0 | 2025-10-20 | Cleaning, Inspecting, Preparing Culverts, | Orange County In Brea At Route 90/57 Separation | 100 | 76 | 921120 | 914700 | 1116200 | 57796 | 2025-11-03 | 2025-04-18 | 2025-04-01 |  |  | 60 | 0 | 60 | 0
12 | 12-0R3134 | 0R3134 | 12-ORA-91-6.4/9.2 |  | ACNH-P091- (158)E | Peterson-Chase General Engineering Construction, Inc. | 16351 Construction Circle Wes | Irvine Ca 92606 | 9492520441 | 9498863914 | 15700 Tustin Village Way | Tustin, Ca 92780 | Zadeh, Ali | 1185350.7 | 3306.44 | 0 | 600000 | 2025-10-20 | Place Jpcp, Remove Conc Pvmt And Base, And | Orange County In Anaheim From 0.3 Mile East Of Route 91/57 Separation To 0.1 Mileeast Of Route 91/55 Separation | 5 | 9 | 1788657.14 | 18914449.5 | 18964449.5 | 57078 | 2026-12-16 | 2025-01-29 | 2024-11-26 |  |  | 14 | 0 | 300 | 0 |  | X
12 | 12-0K91U4 | 0K91U4 | 12-ORA-91-9.2/11.4 |  | ACNH-P091- (156)ECDSL-6212- (031)000 | Granite Construction Company | 4820 Mcgrath St., Suite 101 | Ventura Ca 93003 |  | 9492798821 | 15700 Tustin Village Way | Tustin, Ca 92780 | Kim, Steven | 1595738.97 | 75787.38 | 0 | 0 | 2025-10-20 | Const Bridges, Rw, Sw, Pavement, Drainage | Orange County In Anaheim From 0.9 Mile West To 1.3 Miles East Of Lakeview Avenue Overcrossing | 15 | 19 | 15065375.46 | 78658036.1 | 79700722.89 | 57157 | 2027-07-28 | 2025-02-12 | 2025-01-03 |  |  | 136 | 0 | 917 | 0 |  | X
12 | 12-0U2404 | 0U2404 | 12-ORA-91-9.8/18.9 |  |  | Peterson-Chase General Engineering Construction, Inc. | 16351 Construction Circle Wes | Irvine Ca 92606 |  | 9492798412 | 15700 Tustin Village Way #2 | Tustin, Ca 92780 | Pham, Theodore/Ce- Kim, Steven | 8600.6 | 0 | 0 | 0 | 2025-09-20 | Replace Concrete Slabs, Existing Loop Dete | Orange County In Anaheim And Yorba Linda From 0.3 Mile West Of Lakeview Avenue Overcrossing To Riverside County Line | 93 | 93 | 4260374.93 | 4347091 | 4512549.8 | 55591 | 2025-10-31 | 2024-04-03 | 2024-03-12 |  |  | 65 | 0 | 70 | 0 |  | X
12 | 12-0R3154 | 0R3154 | 12-ORA-91-10.8/18.9 |  | ACNH-P091- (157)E | Powell Constructors, Inc. | 8555 Banana Avenue | Fontana Ca 92335 |  | 9492798412 | 15700 Tustin Village Way #2 | Tustin, Ca 92780 | Pham, Theodore/Ce- Kim, Steven | 232413 | 73982.93 | 0 | 0 | 2025-10-20 | Modify Fiber Optic Cable, Signal, Lighting | Orange County In Anaheim And Yorba Linda From 0.7 Mile West Of Route 90 To Riverside County Line | 19 | 23 | 2474439.86 | 10469301 | 10784301 | 57047 | 2027-12-22 | 2025-01-21 | 2025-01-02 |  |  | 129 | 0 | 690 | 0 |  | X
12 | 12-0P94U4 | 0P94U4 | 12-ORA-133-3.2/4.1 |  | ACNH-P133- (018) | Granite Construction Company | 5860 El Camino Real | Carlsbad Ca 92008 | 7604441032 | 5624497999 | 15700 Tustin Village Way | Tustin, Ca 92780 | Luna, Franklin | 214355.44 | 1546064.21 | 53663.1 | 0 | 2025-10-20 | Roadway Widening, Restriping And | In Orange County, In The City Of Laguna Beach, From 0.2 Mile South Of El Toro Road To Route 73/133 Separation | 21 | 76 | 9091726.59 | 6845845 | 11830319.91 | 41518 | 2031-06-27 | 2021-03-11 | 2021-02-23 |  | S | 386 | 0 | 1800 | 0 |  | X
12 | 12-0N8904 | 0N8904 | 12-ORA-133-8.3/M9.3 |  | ACNH-P133- (019)E | Security Paving Company, Inc. | 13170 Telfair Ave | Sylmar Ca 91342 |  | 9515297048 | 15700 Tustin Village Way | Tustin, Ca 92780 | Luna, Franklin | 353463.59 | 0 | 0 | 0 | 2025-10-20 | Construct Auxiliary Lane. | Orange County In Irvine From Route 133/405Separation To Irvine Center Drive Overcrossing | 69 | 94 | 20924018.54 | 21301897 | 21591897 | 54284 | 2027-07-21 | 2023-12-06 | 2023-11-09 |  |  | 411 | 0 | 600 | 0 |  | X
12 | 12-0Q9804 | 0Q9804 | 12-ORA-241-14.5/25.7 |  | ACNH-P241- (010)E | Chumo Construction Inc. | 14425 Joanbridge Street | Baldwin Park Ca 91706 |  | 9492893551 | 4 Venture Suite 150 | Irvine, Ca 92618 | Ware, Elizabeth | 951972.38 | 123777.06 | 0 | 0 | 2025-10-20 | Treat Bridge Deck With Methacrylate, Insta | Orange County From Oso Parkway In Rancho Santa Margarita To 0.7 Mile North Of Portola Parkway Overcrossing In Irvine | 44 | 39 | 8505120.69 | 21285988.87 | 22343373.02 | 56589 | 2026-06-24 | 2024-10-01 | 2024-08-30 |  |  | 133 | 0 | 300 | 0 |  | X
12 | 12-0Q9704 | 0Q9704 | 12-ORA-405-.2/11.4 |  | ACIM-4052- (003)E | Guy F. Atkinson Construction, Llc Dba Guy F. Atkinson | 611 Anton Blvd., Suite 1100 | Costa Mesa, Ca 92626 |  | 9492798590 | 15700 Tustin Village Way | Tustin, Ca 92780 | Shahidi, Mona/Ce-Nguyen, Irvin | 8463339.13 | 321051.11 | -599417.97 | 0 | 2025-10-20 | Pavement Rehab, Roadside Safety Improvemen | In Orange County In Irvine And In Orange County In Irvine And Costa Mesa On Rte 405 From I-5 To Harbor Blvd | 82 | 69 | 148831302.92 | 216030188.2 | 216438616.98 | 52744 | 2026-04-08 | 2023-08-18 | 2023-07-27 |  |  | 512 | 0 | 625 | 0 |  | X
12 | 12-0R57U4 | 0R57U4 | 12-ORA-405-11.4/24.2 |  | ACIM-4052- (004)E | Security Paving Company, Inc. | 3075 Townsgate Road, Suite 20 | Westlake Village Ca 91361 |  | 9498863914 | 15700 Tustin Village Way | Tustin, Ca 92780 | Zadeh, Ali | 3241886.93 | 0 | 0 | 690000.26 | 2025-10-20 | Place Jpcp (Rsc) And Rhma, And Modify Elec | Orange County From Harbor Boulevard Undercrossing In Costa Mesa To Los Angelescounty Line At Rossmoor | 9 | 31 | 12817825.9 | 41668479 | 41896479 | 57176 | 2028-06-19 | 2025-02-18 | 2025-01-14 |  |  | 63 | 0 | 730 | 0 |  | X
12 | 12-0R6804 | 0R6804 | 12-ORA-605-.2/1.6 |  | HSIM-6052- (995)E | Chumo Construction Inc. | 14425 Joanbridge Street | Baldwin Park Ca 91706 |  | 9492798826 | 3350 E Birch St, Ste 250 | Brea, Ca 92821 | Najm, Elie | 52542 | 60890.62 | 0 | 0 | 2025-10-20 | Modify Lighting Systems. | Orange And Los Angeles Counties In Los Alamitos And Long Beach From 0.2 Mile North Of Route 605/405 Separation To 0.2 Mile North O | 52 | 63 | 4810696.04 | 7240143.17 | 7578666.6 | 55910 | 2026-07-14 | 2024-06-05 | 2024-05-10 |  |  | 197 | 0 | 380 | 1 |  | X
12 | 12-0K8704 | 0K8704 | 12-ORA-605-.6/1.6 |  | TPLN-6212- (032)000 | Ortiz Enterprises, Inc. | 6 Cushing Suite 200 | Irvine Ca 92618 |  | 9492798838 | 10355 Los Alamitos Blvd | Los Alamitos, Ca 90720 | Zadeh, Ali | 1009881.5 | 50939.37 | 0 | 0 | 2025-10-20 | Modify Ramps, Lighting And Ramp Metering S | Orange County In Los Alamitos From 0.8 Mile South To 0.2 Mile North Of Katella Avenue Undercrossing | 3 | 20 | 4984597.37 | 24892102.9 | 25089102.9 | 57857 | 2027-01-29 | 2025-04-25 | 2025-04-03 |  |  | 19 | 0 | 650 | 0 |  | X
12 | 12-0R5604 | 0R5604 | 12-VAR-55-5.5/17.8 | HA22 | ACNH-X059- (087)E | Security Paving Company, Inc. | 13170 Telfair Ave | Sylmar Ca 91342 |  | 4244131143 | 4 Venture, Ste 150 | Irvine, Ca 92618 | Ware, Elizabeth | 647220.35 | 66460.91 | 0 | 0 | 2025-10-20 | Place Rhma-G, Hma, Slab Replacement And Jp | Orange County At Various Locations | 60 | 87 | 34507713.58 | 37466672 | 39683109.86 | 50424 | 2026-04-13 | 2023-06-08 | 2023-04-12 |  |  | 375 | 0 | 625 | 0 |  | X
12 | 12-0U7904 | 0U7904 | 12-VAR--/0 |  |  | Specialized Pavement Marking, Llc | 11095 Sw Industrial Way Suite | Tualatin Or 97062 |  | 5624497999 | 15700 Tustin Village Way | Tustin, Ca 92780 | Luna, Franklin | 388770 | 0 | 0 | 6250 | 2025-10-20 | Install Pvmt Marking, Signs, Rumble Strips | Orange County At Various Locations | 96 | 65 | 953113.1 | 1445832.5 | 1450832.5 | 58515 | 2025-10-23 | 2025-06-04 | 2025-04-30 |  |  | 77 | 0 | 80 | 0

## Report 2
District | Ea | Contract_Id | Cnty_Rt_Pm
01 | 0Q0804 | 01-0Q0804 | 01-DEL-199-91.0/9.4
01 | 0P4304 | 01-0P4304 | 01-DN-101-2.0/16.5
01 | 0G1004 | 01-0G1004 | 01-DN-101-12.5/15.5
01 | 436404 | 01-436404 | 01-DN-101-35.8/36.5
01 | 0J2104 | 01-0J2104 | 01-DN-101-2.6/23.9
01 | 0J8904 | 01-0J8904 | 01-HUM-36-3.9/6
01 | 0C5004 | 01-0C5004 | 01-HUM-36-11.3/34.6
01 | 0H6104 | 01-0H6104 | 01-HUM-36-13.5/36.1
01 | 461704 | 01-461704 | 01-HUM-36-25.4/0
01 | 0P1804 | 01-0P1804 | 01-HUM-36-25.4/26
01 | 0M8104 | 01-0M8104 | 01-HUM-36-70.0/42
01 | 0P8204 | 01-0P8204 | 01-HUM-36-155.0/16.5
01 | 0P9504 | 01-0P9504 | 01-HUM-36-170.0/24
01 | 0P9004 | 01-0P9004 | 01-HUM-36-190.0/20.1
01 | 0Q0304 | 01-0Q0304 | 01-HUM-36-279.0/27.9
01 | 0N4504 | 01-0N4504 | 01-HUM-36-365.0/40
01 | 0N8304 | 01-0N8304 | 01-HUM-96-4.9/13.3
01 | 0F9204 | 01-0F9204 | 01-HUM-96-43.7/0
01 | 0H6404 | 01-0H6404 | 01-HUM-101-2.4/M53.9
01 | 0H6504 | 01-0H6504 | 01-HUM-101-55.9/136.4
01 | 0K9404 | 01-0K9404 | 01-HUM-101-74.8/76.1
01 | 0P9804 | 01-0P9804 | 01-HUM-101-75.0/108.5
01 | 0N6604 | 01-0N6604 | 01-HUM-101-78.0/79.6
01 | 366004 | 01-366004 | 01-HUM-101-80.0/84
01 | 0M6504 | 01-0M6504 | 01-HUM-101-125.7/131.7
01 | 0P8704 | 01-0P8704 | 01-HUM-101-330.0/18
01 | 0K4204 | 01-0K4204 | 01-HUM-101-595.0/0
01 | 0P0604 | 01-0P0604 | 01-HUM-101-834.0/83.4
01 | 0J3604 | 01-0J3604 | 01-HUM-101-103.3/103.7
01 | 0H4104 | 01-0H4104 | 01-HUM-169-15.0/33.8
01 | 0P8904 | 01-0P8904 | 01-HUM-169-250.0/26
01 | 0M7304 | 01-0M7304 | 01-HUM-211-772.0/78.6
01 | 0M6304 | 01-0M6304 | 01-HUM-211-74.2/79.3
01 | 0H8004 | 01-0H8004 | 01-HUM-254-4.3/4.7
01 | 0N7304 | 01-0N7304 | 01-HUM-255-8.3/8.7
01 | 0N0904 | 01-0N0904 | 01-HUM-299-9.0/.6
01 | 0P4004 | 01-0P4004 | 01-HUM-299-22.0/2.2
01 | 0J4104 | 01-0J4104 | 01-HUM-299-30.7/33.4
01 | 0P9104 | 01-0P9104 | 01-HUM-299-210.0/22
01 | 0Q1104 | 01-0Q1104 | 01-HUM-299-235.0/27.3
01 | 0H5804 | 01-0H5804 | 01-HUM-299-7.6/29.2
01 | 0P8404 | 01-0P8404 | 01-HUM-451-30.0/4
01 | 0H8404 | 01-0H8404 | 01-LAK-20-2.0/2.8
01 | 0N6804 | 01-0N6804 | 01-LAK-20-16.6/18.1
01 | 0N8204 | 01-0N8204 | 01-LAK-29-23.6/33.1
01 | 0P3604 | 01-0P3604 | 01-LAK-175-/8.2
01 | 0P7704 | 01-0P7704 | 01-LAK-200-447.0/45.2
01 | 0P9604 | 01-0P9604 | 01-MEN-1-6.0/.6
01 | 0F7104 | 01-0F7104 | 01-MEN-1-6.4/9.5
01 | 0E11U4 | 01-0E11U4 | 01-MEN-1-31.1/31.6
01 | 0H6004 | 01-0H6004 | 01-MEN-1-33.7/51
01 | 0P7404 | 01-0P7404 | 01-MEN-1-114.0/11.6
01 | 0Q1004 | 01-0Q1004 | 01-MEN-1-418.0/42.5
01 | 0P1704 | 01-0P1704 | 01-MEN-1-749.0/78
01 | 0N4404 | 01-0N4404 | 01-MEN-1-750.0/76.5
01 | 0P0704 | 01-0P0704 | 01-MEN-1-821.0/82.9
01 | 434844 | 01-434844 | 01-MEN-1-51.3/52.1
01 | 0N6104 | 01-0N6104 | 01-MEN-20-14.2/24.4
01 | 0E0904 | 01-0E0904 | 01-MEN-20-33.3/34.4
01 | 0K4104 | 01-0K4104 | 01-MEN-101-41.3/43.3
01 | 0K8904 | 01-0K8904 | 01-MEN-101-50.7/52.2
01 | 0H5504 | 01-0H5504 | 01-MEN-101-55.0/64.9
01 | 0P2604 | 01-0P2604 | 01-MEN-101-599.0/59.9
01 | 0Q2604 | 01-0Q2604 | 01-MEN-101-727.0/72.7
01 | 0P0904 | 01-0P0904 | 01-MEN-101-860.0/87.5
01 | 0H1604 | 01-0H1604 | 01-MEN-101-33.7/43.2
01 | 0H1704 | 01-0H1704 | 01-MEN-101-48.9/55.1
01 | 0L7404 | 01-0L7404 | 01-MEN-128-37.4/49.4
01 | 0N8104 | 01-0N8104 | 01-MEN-128-40.9/44.3
01 | 0Q0604 | 01-0Q0604 | 01-MEN-128-281.0/28.1
01 | 0N6304 | 01-0N6304 | 01-MEN-162-2.6/4.4
01 | 0A1314 | 01-0A1314 | 01-MEN-162-8.0/8.4
01 | 0B5304 | 01-0B5304 | 01-MEN-162-11.5/11.8
01 | 0P9704 | 01-0P9704 | 01-MEN-162-161.0/16.2
01 | 0H1504 | 01-0H1504 | 01-MEN-162-/25.7
01 | 0N6204 | 01-0N6204 | 01-MEN-253-5.8/17.2
01 | 0P3504 | 01-0P3504 | 01-MEN-253-130.0/13
01 | 0P9404 | 01-0P9404 | 01-MEN-271-24.0/2.5
01 | 0H1204 | 01-0H1204 | 01-VAR-101-84.0/85.5
01 | 0N8804 | 01-0N8804 | 01-VAR--/0
01 | 0L9604 | 01-0L9604 | 01-VAR--/0
01 | 0M9104 | 01-0M9104 | 01-VAR--/0
01 | 0M9604 | 01-0M9604 | 01-VAR--/0
02 | 1J75U4 | 02-1J75U4 | 02-LAS-36-14.4/16.8
02 | 2K5404 | 02-2K5404 | 02-LAS-36-100.0/14
02 | 4H0604 | 02-4H0604 | 02-LAS-36-/6.1
02 | 4H0704 | 02-4H0704 | 02-LAS-139-.7/11
02 | 1K0704 | 02-1K0704 | 02-LAS-139-11.0/16
02 | 1K0904 | 02-1K0904 | 02-MOD-139-28.0/34
02 | 1K0804 | 02-1K0804 | 02-MOD-395-/5
02 | 0K6104 | 02-0K6104 | 02-PLU-70-32.9/33.2
02 | 1H58U4 | 02-1H58U4 | 02-PLU-70-58.2/78.4
02 | 4H0104 | 02-4H0104 | 02-PLU-70-78.3/90.3
02 | 4H03U4 | 02-4H03U4 | 02-PLU-89-12.9/20
02 | 3H6904 | 02-3H6904 | 02-PLU-89-30.2/42.2
02 | 0K7804 | 02-0K7804 | 02-PLU-89-200.0/20.6
02 | 4H1504 | 02-4H1504 | 02-SHA-5-4.9/5.1
02 | 1J8904 | 02-1J8904 | 02-SHA-5-30.5/31
02 | 1K0504 | 02-1K0504 | 02-SHA-44-.4/L1.8
02 | 4H0504 | 02-4H0504 | 02-SHA-273-18.5/18.7
02 | 1K1904 | 02-1K1904 | 02-SHA-299-20.4/21.5
02 | 1K4004 | 02-1K4004 | 02-SIS-0-/0
02 | 1H7104 | 02-1H7104 | 02-SIS-3-47.4/0
02 | 3H32U4 | 02-3H32U4 | 02-SIS-5-2.5/15.9
02 | 0J8504 | 02-0J8504 | 02-SIS-89-20.3/34.6
02 | 1H5904 | 02-1H5904 | 02-SIS-96-43.5/58
02 | 1H3604 | 02-1H3604 | 02-SIS-96-76.8/78
02 | 0K6404 | 02-0K6404 | 02-SIS-97-18.0/22.4
02 | 1K1004 | 02-1K1004 | 02-SIS-97-29.0/34.5
02 | 4H0004 | 02-4H0004 | 02-SIS-97-45.0/54.1
02 | 0K0104 | 02-0K0104 | 02-TEH-5-5.6/42
02 | 1K9004 | 02-1K9004 | 02-TEH-36-618.0/.2
02 | 0J0104 | 02-0J0104 | 02-TEH-99-4.2/4.8
02 | 3H70U4 | 02-3H70U4 | 02-TRI-299-15.0/25.7
02 | 2K7504 | 02-2K7504 | 02-TRI-299-286.0/28.6
02 | 2K1104 | 02-2K1104 | 02-VAR--/0
02 | 2J2204 | 02-2J2204 | 02-VAR--/0
02 | 0K6004 | 02-0K6004 | 02-VAR--/0
02 | 2K2704 | 02-2K2704 | 02-VAR--/0
02 | 3J3304 | 02-3J3304 | 02-VAR--/0
02 | 1K1804 | 02-1K1804 | 02-VAR--/0
02 | 2J9704 | 02-2J9704 | 02-VAR--/0
02 | 3J3204 | 02-3J3204 | 02-VAR--/0
03 | 4H76U4 | 03-4H76U4 | 03-BUT-32-5.0/10.2
03 | 3G0704 | 03-3G0704 | 03-BUT-32-31.5/37.8
03 | 1N4404 | 03-1N4404 | 03-BUT-32-174.0/37.7
03 | 3G3804 | 03-3G3804 | 03-BUT-32-23.9/30.8
03 | 1N5504 | 03-1N5504 | 03-BUT-70-350.0/36
03 | 2N0104 | 03-2N0104 | 03-BUT-70-364.0/42.3
03 | 1H1404 | 03-1H1404 | 03-BUT-99-3.1/5
03 | 4J2104 | 03-4J2104 | 03-COL-5-30.0/10
03 | 3G5304 | 03-3G5304 | 03-ED-49-16.5/20.1
03 | 3G5204 | 03-3G5204 | 03-ED-49-23.6/25.2
03 | 4H8904 | 03-4H8904 | 03-ED-50-75.4/8
03 | 2N0704 | 03-2N0704 | 03-ED-50-180.0/18
03 | 1N1804 | 03-1N1804 | 03-ED-50-189.0/18.9
03 | 0N6504 | 03-0N6504 | 03-ED-50-672.0/67.2
03 | 3G8104 | 03-3G8104 | 03-ED-89-81.0/8.1
03 | 3G4304 | 03-3G4304 | 03-ED-89-/8.5
03 | 2G9704 | 03-2G9704 | 03-ED-193-11.9/17.3
03 | 2G9804 | 03-2G9804 | 03-ED-193-2.0/8.9
03 | 2G9304 | 03-2G9304 | 03-ED-193-3.5/5.6
03 | 2J5904 | 03-2J5904 | 03-GLE-32-2.8/3.2
03 | 3J4324 | 03-3J4324 | 03-GLE-162-65.5/69.7
03 | 3F0604 | 03-3F0604 | 03-GLE-162-76.3/78.6
03 | 2H6214 | 03-2H6214 | 03-NEV-20-301.0/30.1
03 | 3G7404 | 03-3G7404 | 03-NEV-80-156.0/15.6
03 | 2G7904 | 03-2G7904 | 03-NEV-80-9.1/9.1
03 | 3J3604 | 03-3J3604 | 03-NEV-89-5.3/8.7
03 | 0J01U4 | 03-0J01U4 | 03-PLA-28-.1/11
03 | 1H2404 | 03-1H2404 | 03-PLA-49-2.2/2.4
03 | 3H8304 | 03-3H8304 | 03-PLA-49-3.5/7.5
03 | 4H6004 | 03-4H6004 | 03-PLA-49-8.7/10.6
03 | 3F23U4 | 03-3F23U4 | 03-PLA-80-.1/2.2
03 | 3H6104 | 03-3H6104 | 03-PLA-80-42.7/49.3
03 | 0J5604 | 03-0J5604 | 03-PLA-80-49.3/68.7
03 | 1H9904 | 03-1H9904 | 03-PLA-80-68.3/69.7
03 | 4F6404 | 03-4F6404 | 03-SAC-5-.2/34.3
03 | 0N8504 | 03-0N8504 | 03-SAC-5-16.2/0
03 | 2H1304 | 03-2H1304 | 03-SAC-5-22.4/22.9
03 | 3J5334 | 03-3J5334 | 03-SAC-5-26.7/29
03 | 3J3304 | 03-3J3304 | 03-SAC-12-/.5
03 | 1N7904 | 03-1N7904 | 03-SAC-50-21.0/2.1
03 | 0N6204 | 03-0N6204 | 03-SAC-50-21.0/2.1
03 | 0H08U4 | 03-0H08U4 | 03-SAC-50-.2/6.1
03 | 3F0704 | 03-3F0704 | 03-SAC-51-.2/3.5
03 | 3F0734 | 03-3F0734 | 03-SAC-51-2.0/3.3
03 | 1N5404 | 03-1N5404 | 03-SAC-51-17.0/1.7
03 | 1H6304 | 03-1H6304 | 03-SAC-99-12.7/16.3
03 | 3J9004 | 03-3J9004 | 03-SAC-160-44.9/0
03 | 1N0104 | 03-1N0104 | 03-SAC-160-/0
03 | 4H9704 | 03-4H9704 | 03-SAC-5500-/0
03 | 3G4104 | 03-3G4104 | 03-SUT-70-2.4/5.4
03 | 4H8704 | 03-4H8704 | 03-SUT-99-25.0/26.2
03 | 0J3504 | 03-0J3504 | 03-VAR-149-/5.3
03 | 1N0004 | 03-1N0004 | 03-VAR--/0
03 | 3H5604 | 03-3H5604 | 03-VAR--/0
03 | 3G2304 | 03-3G2304 | 03-VAR--/0
03 | 3J40U4 | 03-3J40U4 | 03-VAR--/0
03 | 3G4804 | 03-3G4804 | 03-VAR--/0
03 | 3G4704 | 03-3G4704 | 03-VAR--/0
03 | 3G4604 | 03-3G4604 | 03-VAR--/0
03 | 3H9014 | 03-3H9014 | 03-VAR--/0
03 | 3G4904 | 03-3G4904 | 03-VAR--/0
03 | 3G1704 | 03-3G1704 | 03-VAR--/0
03 | 3G1804 | 03-3G1804 | 03-VAR--/0
03 | 3G3704 | 03-3G3704 | 03-VAR--/0
03 | 3G6204 | 03-3G6204 | 03-YOL-5-22.8/28.9
03 | 3G4004 | 03-3G4004 | 03-YOL-16-10.0/15
03 | 4J1204 | 03-4J1204 | 03-YOL-16-37.3/37.8
03 | 4F6504 | 03-4F6504 | 03-YOL-50-/2.5
03 | 0H3704 | 03-0H3704 | 03-YUB-65-.5/1.8
04 | 3Y1904 | 04-3Y1904 | 04-ALA-0-/0
04 | 2G4614 | 04-2G4614 | 04-ALA-13-10.7/13
04 | 3W9304 | 04-3W9304 | 04-ALA-80-5.7/6
04 | 3J2604 | 04-3J2604 | 04-ALA-80-5.9/6.4
04 | 0A7724 | 04-0A7724 | 04-ALA-80-6.4/6.8
04 | 0K1604 | 04-0K1604 | 04-ALA-80-7.6/8
04 | 4Y1804 | 04-4Y1804 | 04-ALA-80-/1.8
04 | 3Q8504 | 04-3Q8504 | 04-ALA-84-10.8/18
04 | 160314 | 04-160314 | 04-ALA-84-11.0/18
04 | 1X2804 | 04-1X2804 | 04-ALA-84-11.2/15.5
04 | 297634 | 04-297634 | 04-ALA-84-17.9/22.9
04 | 0X6604 | 04-0X6604 | 04-ALA-84-21.4/23.1
04 | 2Q7604 | 04-2Q7604 | 04-ALA-238-.7/.8
04 | 0G3604 | 04-0G3604 | 04-ALA-260-.8/1.9
04 | 2W7404 | 04-2W7404 | 04-ALA-260-1.1/1.9
04 | 1Y3404 | 04-1Y3404 | 04-ALA-260-1.2/0
04 | 3Y5504 | 04-3Y5504 | 04-ALA-580-4.7/4.8
04 | 0Q1004 | 04-0Q1004 | 04-ALA-580-20.7/30.8
04 | 2Y8604 | 04-2Y8604 | 04-ALA-580-26.2/26.2
04 | 0Y6804 | 04-0Y6804 | 04-ALA-580-35.0/45.2
04 | 3Y1304 | 04-3Y1304 | 04-ALA-580-43.1/43.1
04 | 2K7904 | 04-2K7904 | 04-ALA-580-45.4/45.8
04 | 3X9504 | 04-3X9504 | 04-ALA-580-4.6/4.7
04 | 2Y8204 | 04-2Y8204 | 04-ALA-580-/32.7
04 | 0P9204 | 04-0P9204 | 04-ALA-680-6.3/6.7
04 | 0Q30U4 | 04-0Q30U4 | 04-ALA-680-11.0/21.9
04 | 2W4604 | 04-2W4604 | 04-ALA-680-15.6/0
04 | 0Q1804 | 04-0Q1804 | 04-ALA-880-6.2/25.5
04 | 2K7004 | 04-2K7004 | 04-ALA-880-/11.8
04 | 1X3804 | 04-1X3804 | 04-ALA-880-/28.9
04 | 4K9804 | 04-4K9804 | 04-ALA-980-1.1/1.1
04 | 3W9104 | 04-3W9104 | 04-ALA-980-1.2/0
04 | 2K9504 | 04-2K9504 | 04-ALA-5501-/14.4
04 | 0Q2004 | 04-0Q2004 | 04-CC-4-12.4/25
04 | 3X5804 | 04-3X5804 | 04-CC-4-19.8/19.8
04 | 2Q7004 | 04-2Q7004 | 04-CC-4-/14.3
04 | 3X7404 | 04-3X7404 | 04-CC-24-5.1/5.4
04 | 0Q2104 | 04-0Q2104 | 04-CC-80-.2/10.7
04 | 0P9304 | 04-0P9304 | 04-CC-80-7.6/0
04 | 4X3804 | 04-4X3804 | 04-CC-80-7.6/7.6
04 | 0X6904 | 04-0X6904 | 04-CC-160-/.7
04 | 3G3644 | 04-3G3644 | 04-CC-580-6.1/7.8
04 | 2Q6504 | 04-2Q6504 | 04-CC-680-/21
04 | 1X0304 | 04-1X0304 | 04-MRN-1-8.7/8.7
04 | 1J9604 | 04-1J9604 | 04-MRN-1-22.8/33
04 | 3X2604 | 04-3X2604 | 04-MRN-1-/19.3
04 | 2K7404 | 04-2K7404 | 04-MRN-37-11.2/14.5
04 | 3X3604 | 04-3X3604 | 04-MRN-101-3.0/3
04 | 0K8004 | 04-0K8004 | 04-MRN-101-13.7/0
04 | 264724 | 04-264724 | 04-MRN-101-20.8/27.1
04 | 2X9404 | 04-2X9404 | 04-MRN-101-/9.3
04 | 3X1504 | 04-3X1504 | 04-MRN-580-6.0/7.8
04 | 4J4104 | 04-4J4104 | 04-NAP-29-1.7/1.7
04 | 281204 | 04-281204 | 04-NAP-29-5.0/6.7
04 | 0Q8204 | 04-0Q8204 | 04-NAP-29-11.6/13
04 | 0K6304 | 04-0K6304 | 04-NAP-29-16.4/19
04 | 3X4904 | 04-3X4904 | 04-NAP-29-45.5/45.5
04 | 0Q8304 | 04-0Q8304 | 04-NAP-29-46.1/0
04 | 2Q6104 | 04-2Q6104 | 04-NAP-29-7.3/13.5
04 | 4G21A4 | 04-4G21A4 | 04-NAP-121-.5/1
04 | 3X2804 | 04-3X2804 | 04-NAP-121-19.5/19.5
04 | 4G84A4 | 04-4G84A4 | 04-NAP-128-20.1/20.4
04 | 3X0204 | 04-3X0204 | 04-NAP-128-/25.9
04 | 3Y8904 | 04-3Y8904 | 04-NAP-128-/29.7
04 | 1X1004 | 04-1X1004 | 04-SCL-9-4.0/4
04 | 1X4304 | 04-1X4304 | 04-SCL-9-4.5/5.5
04 | 3G6304 | 04-3G6304 | 04-SCL-9-4.9/4.9
04 | 0P9704 | 04-0P9704 | 04-SCL-17-6.2/0
04 | 3Y2904 | 04-3Y2904 | 04-SCL-17-/3.5
04 | 1X0204 | 04-1X0204 | 04-SCL-35-2.0/2
04 | 0P9804 | 04-0P9804 | 04-SCL-82-11.4/26.3
04 | 4X1304 | 04-4X1304 | 04-SCL-82-14.6/14.6
04 | 4J89U4 | 04-4J89U4 | 04-SCL-82-18.2/26.4
04 | 1X2304 | 04-1X2304 | 04-SCL-85-/38.9
04 | 2W4504 | 04-2W4504 | 04-SCL-87-4.8/10.1
04 | 4J9104 | 04-4J9104 | 04-SCL-87-/6.1
04 | 4J9304 | 04-4J9304 | 04-SCL-101-30.7/31.1
04 | 2Y8504 | 04-2Y8504 | 04-SCL-101-33.0/49
04 | 1Y6204 | 04-1Y6204 | 04-SCL-101-38.0/38.1
04 | 1J5674 | 04-1J5674 | 04-SCL-101-51.7/52.5
04 | 3Q6004 | 04-3Q6004 | 04-SCL-101-.7/19.2
04 | 0X6304 | 04-0X6304 | 04-SCL-101-4.5/17.5
04 | 2Y7404 | 04-2Y7404 | 04-SCL-152-12.6/12.6
04 | 0Q05U4 | 04-0Q05U4 | 04-SCL-152-16.8/23.3
04 | 3X5204 | 04-3X5204 | 04-SCL-237-9.1/9.1
04 | 2Y5404 | 04-2Y5404 | 04-SCL-237-1.5/6.4
04 | 0Y5004 | 04-0Y5004 | 04-SCL-280-2.9/2.9
04 | 3Y0004 | 04-3Y0004 | 04-SCL-280-4.6/4.6
04 | 1Q4604 | 04-1Q4604 | 04-SCL-280-/2.7
04 | 0X2604 | 04-0X2604 | 04-SCL-280-/3.8
04 | 4X0204 | 04-4X0204 | 04-SCL-880-1.7/1.9
04 | 0X9104 | 04-0X9104 | 04-SF-80-3.9/4.5
04 | 1Y7204 | 04-1Y7204 | 04-SF-80-5.7/7.7
04 | 3G4444 | 04-3G4444 | 04-SF-80-5.7/7.5
04 | 4W9504 | 04-4W9504 | 04-SF-80-/7.8
04 | 2Q4604 | 04-2Q4604 | 04-SF-101-.8/0
04 | 4X1404 | 04-4X1404 | 04-SF-280-6.6/7.2
04 | 1Y5004 | 04-1Y5004 | 04-SF-280-2.7/4.2
04 | 1W1404 | 04-1W1404 | 04-SF-280-6.6/T7.2
04 | 2X0704 | 04-2X0704 | 04-SF0-80-8.3/8.3
04 | 2K8804 | 04-2K8804 | 04-SM-1-26.3/47.3
04 | 0Q1304 | 04-0Q1304 | 04-SM-1-27.5/34.8
04 | 2J7904 | 04-2J7904 | 04-SM-1-28.9/0
04 | 0X0804 | 04-0X0804 | 04-SM-1-32.2/32.2
04 | 3X5104 | 04-3X5104 | 04-SM-1-47.8/47.8
04 | 0X0004 | 04-0X0004 | 04-SM-35-1.7/1.7
04 | 3Y7604 | 04-3Y7604 | 04-SM-35-8.7/8.7
04 | 1X9604 | 04-1X9604 | 04-SM-82-9.2/9.2
04 | 1Q5304 | 04-1Q5304 | 04-SM-82-9.3/0
04 | 2Y5604 | 04-2Y5604 | 04-SM-82-9.6/11.8
04 | 3Y5004 | 04-3Y5004 | 04-SM-84-17.9/17.9
04 | 0X3304 | 04-0X3304 | 04-SM-84-28.0/2
04 | 2Y5204 | 04-2Y5204 | 04-SM-84-27.7/29.2
04 | 3X6404 | 04-3X6404 | 04-SM-92-4.0/5
04 | 2Q8004 | 04-2Q8004 | 04-SM-92-12.0/13.1
04 | 1X2204 | 04-1X2204 | 04-SM-92-/13.6
04 | 0X6504 | 04-0X6504 | 04-SM-92-/.5
04 | 1Q8204 | 04-1Q8204 | 04-SM-101-2.5/2.6
04 | 2J7304 | 04-2J7304 | 04-SM-101-6.9/7.6
04 | 0X0604 | 04-0X0604 | 04-SM-101-9.1/9.1
04 | 1X2404 | 04-1X2404 | 04-SM-101-/6.2
04 | 1Q5814 | 04-1Q5814 | 04-SM-101-/6.5
04 | 1X6604 | 04-1X6604 | 04-SM-280-10.2/10.2
04 | 3Y0804 | 04-3Y0804 | 04-SM-280-10.2/10.2
04 | 2X0104 | 04-2X0104 | 04-SM-280-232.0/23.2
04 | 4J8504 | 04-4J8504 | 04-SM-280-/21
04 | 3Y4104 | 04-3Y4104 | 04-SM-680-/16.5
04 | 2Q5504 | 04-2Q5504 | 04-SOL-12-7.7/14.1
04 | 0A53T4 | 04-0A53T4 | 04-SOL-12-1.8/L3.2
04 | 0W1104 | 04-0W1104 | 04-SOL-12-3.2/7.5
04 | 1X3604 | 04-1X3604 | 04-SOL-28-/9.8
04 | 2Q5204 | 04-2Q5204 | 04-SOL-29-/6
04 | 3X5004 | 04-3X5004 | 04-SOL-80-6.7/6.7
04 | 3X4704 | 04-3X4704 | 04-SOL-80-12.9/12.9
04 | 4G8734 | 04-4G8734 | 04-SOL-80-13.9/14.5
04 | 0K6404 | 04-0K6404 | 04-SOL-80-15.9/30.2
04 | 4K3004 | 04-4K3004 | 04-SOL-80-22.1/23
04 | 0J6014 | 04-0J6014 | 04-SOL-80-34.4/34.5
04 | 3X1604 | 04-3X1604 | 04-SOL-80-10.1/10.6
04 | 4G0804 | 04-4G0804 | 04-SOL-80-10.4/30.2
04 | 0X7004 | 04-0X7004 | 04-SOL-84-3.0/13.6
04 | 0X7604 | 04-0X7604 | 04-SOL-113-18.3/21.2
04 | 0J3004 | 04-0J3004 | 04-SON-1-26.7/27.1
04 | 0J3014 | 04-0J3014 | 04-SON-1-26.7/27.1
04 | 1K7314 | 04-1K7314 | 04-SON-1-30.8/40.6
04 | 1K7304 | 04-1K7304 | 04-SON-1-30.8/40.6
04 | 1X3204 | 04-1X3204 | 04-SON-1-38.6/38.6
04 | 1K7504 | 04-1K7504 | 04-SON-1-41.2/54.6
04 | 1K7604 | 04-1K7604 | 04-SON-1-45.4/0
04 | 3X0804 | 04-3X0804 | 04-SON-1-/7.2
04 | 1X1404 | 04-1X1404 | 04-SON-1-/24.7
04 | 3X1004 | 04-3X1004 | 04-SON-1-/36.4
04 | 4G7804 | 04-4G7804 | 04-SON-1-/58.6
04 | 4H0514 | 04-4H0514 | 04-SON-12-25.8/0
04 | 4A1304 | 04-4A1304 | 04-SON-101-18.5/18.5
04 | 1Q7004 | 04-1Q7004 | 04-SON-101-22.8/32.8
04 | 3J0804 | 04-3J0804 | 04-SON-101-/0
04 | 2K3604 | 04-2K3604 | 04-SON-116-9.6/0
04 | 3X0504 | 04-3X0504 | 04-SON-116-10.4/10.4
04 | 4J4604 | 04-4J4604 | 04-SON-116-11.8/12.2
04 | 3G9004 | 04-3G9004 | 04-SON-116-46.5/46.8
04 | 2Q4404 | 04-2Q4404 | 04-SON-121-6.5/0
04 | 0X7204 | 04-0X7204 | 04-SON-128-12.2/24.8
04 | 3X4204 | 04-3X4204 | 04-SON-128-16.6/16.7
04 | 0Y8004 | 04-0Y8004 | 04-VAR-82-25.9/25.9
04 | 2Q5704 | 04-2Q5704 | 04-VAR-101-18.7/18.7
04 | 3Q6104 | 04-3Q6104 | 04-VAR-101-21.3/26.5
04 | 0K1104 | 04-0K1104 | 04-VAR-280-/0
04 | 0K1204 | 04-0K1204 | 04-VAR-580-/0
04 | 4Q2504 | 04-4Q2504 | 04-VAR-680-.1/20.7
04 | 0Q0704 | 04-0Q0704 | 04-VAR-880-/32
04 | 0Q4404 | 04-0Q4404 | 04-VAR-880-/10
04 | 3Y5204 | 04-3Y5204 | 04-VAR--/0
04 | 0K1004 | 04-0K1004 | 04-VAR--/0
04 | 1Q2004 | 04-1Q2004 | 04-VAR--/0
04 | 1W0904 | 04-1W0904 | 04-VAR--/0
04 | 0X5904 | 04-0X5904 | 04-VAR--/0
04 | 3Y5904 | 04-3Y5904 | 04-VAR--/0
04 | 3W5604 | 04-3W5604 | 04-VAR--/0
04 | 0X6004 | 04-0X6004 | 04-VAR--/0
04 | 0Y8404 | 04-0Y8404 | 04-VAR--/0
04 | 0X5704 | 04-0X5704 | 04-VAR--/0
04 | 0X5804 | 04-0X5804 | 04-VAR--/0
04 | 0P7604 | 04-0P7604 | 04-VAR--/0
05 | 1S4904 | 05-1S4904 | 05-0SB-1-10.1/10.1
05 | 1S3704 | 05-1S3704 | 05-0SB-1-10.7/11
05 | 1S2904 | 05-1S2904 | 05-MON-0-/0
05 | 1R1904 | 05-1R1904 | 05-MON-1-7.2/9.2
05 | 1S8404 | 05-1S8404 | 05-MON-1-10.4/10.4
05 | 1R6404 | 05-1R6404 | 05-MON-1-27.8/27.8
05 | 1R6304 | 05-1R6304 | 05-MON-1-29.5/29.5
05 | 1Q8004 | 05-1Q8004 | 05-MON-1-44.7/69.8
05 | 1T2104 | 05-1T2104 | 05-MON-1-50.0/54
05 | 1S0404 | 05-1S0404 | 05-MON-1-60.0/60
05 | 1Q9604 | 05-1Q9604 | 05-MON-1-100.0/1
05 | 1S1604 | 05-1S1604 | 05-MON-1-600.0/60
05 | 1K6404 | 05-1K6404 | 05-MON-1-101.5/102
05 | 1P5344 | 05-1P5344 | 05-MON-101-86.1/87.3
05 | 1H6914 | 05-1H6914 | 05-MON-101-98.8/100.3
05 | 1S9404 | 05-1S9404 | 05-MON-101-870.0/87
05 | 0T9914 | 05-0T9914 | 05-MON-101-41.1/42.2
05 | 1H6904 | 05-1H6904 | 05-MON-101-91.3/98.8
05 | 1P5334 | 05-1P5334 | 05-MON-156-1.4/1.3
05 | 1H6504 | 05-1H6504 | 05-MON-183-8.3/9.9
05 | 0N71Y4 | 05-0N71Y4 | 05-SB-101-1.4/4.8
05 | 0N72U4 | 05-0N72U4 | 05-SB-101-4.4/7.7
05 | 0N72Y4 | 05-0N72Y4 | 05-SB-101-4.4/7.7
05 | 0N73Y4 | 05-0N73Y4 | 05-SB-101-7.3/9.6
05 | 0N74V4 | 05-0N74V4 | 05-SB-101-9.2/9.7
05 | 0N74U4 | 05-0N74U4 | 05-SB-101-9.7/10.6
05 | 1K03U4 | 05-1K03U4 | 05-SB-101-10.0/10.5
05 | 0N7054 | 05-0N7054 | 05-SB-101-10.4/11.1
05 | 1K3804 | 05-1K3804 | 05-SB-101-12.3/13.2
05 | 1H4304 | 05-1H4304 | 05-SB-101-21.4/21.9
05 | 1H8604 | 05-1H8604 | 05-SB-101-46.2/52.3
05 | 1R1404 | 05-1R1404 | 05-SB-101-47.0/47.3
05 | 1F79A4 | 05-1F79A4 | 05-SB-101-55.9/56.2
05 | 1F7904 | 05-1F7904 | 05-SB-101-55.9/56.2
05 | 1K5104 | 05-1K5104 | 05-SB-101-65.0/84.1
05 | 1R7204 | 05-1R7204 | 05-SB-101-84.0/87
05 | 1R7504 | 05-1R7504 | 05-SB-101-/2.2
05 | 1C9504 | 05-1C9504 | 05-SB-101-36.0/37
05 | 1K4504 | 05-1K4504 | 05-SB-101-52.3/56.1
05 | 1R7304 | 05-1R7304 | 05-SB-135-7.2/M9.7
05 | 1R6504 | 05-1R6504 | 05-SB-154-26.0/30.2
05 | 1C4104 | 05-1C4104 | 05-SB-154-2.6/0
05 | 1P5384 | 05-1P5384 | 05-SB-166-63.9/64.9
05 | 1C3604 | 05-1C3604 | 05-SB-217-.9/1.4
05 | 1P5394 | 05-1P5394 | 05-SB-246-32.8/33.2
05 | 1H8114 | 05-1H8114 | 05-SBT-25-18.8/19.2
05 | 1P5314 | 05-1P5314 | 05-SBT-25-49.5/51.1
05 | 1J4814 | 05-1J4814 | 05-SBT-25-53.7/54.3
05 | 1S9004 | 05-1S9004 | 05-SBT-101-1.5/1.7
05 | 1S5104 | 05-1S5104 | 05-SBT-101-4.2/4.5
05 | 1S0104 | 05-1S0104 | 05-SBT-101-12.0/2.1
05 | 1P5324 | 05-1P5324 | 05-SBT-156-2.7/2.7
05 | 344904 | 05-344904 | 05-SBT-156-3.0/8.2
05 | 1S9204 | 05-1S9204 | 05-SCR-1-3.5/3.9
05 | 0C7334 | 05-0C7334 | 05-SCR-1-10.5/13.4
05 | 0C7324 | 05-0C7324 | 05-SCR-1-13.6/14.9
05 | 1Q9404 | 05-1Q9404 | 05-SCR-1-33.0/33
05 | 1Q9904 | 05-1Q9904 | 05-SCR-1-360.0/37.5
05 | 1P1804 | 05-1P1804 | 05-SCR-1-5.0/8.2
05 | 1Q0804 | 05-1Q0804 | 05-SCR-1-/0
05 | 1G9504 | 05-1G9504 | 05-SCR-9-9.0/25.5
05 | 1S3604 | 05-1S3604 | 05-SCR-9-12.1/12.1
05 | 1T3904 | 05-1T3904 | 05-SCR-17-8.4/8.4
05 | 1Q6904 | 05-1Q6904 | 05-SCR-35-3.0/3
05 | 1P5304 | 05-1P5304 | 05-SCR-129-1.1/L1.5
05 | 1S3804 | 05-1S3804 | 05-SCR-152-1.3/T1.5
05 | 1S2804 | 05-1S2804 | 05-SLO-0-/0
05 | 492864 | 05-492864 | 05-SLO-1-6.4/67.2
05 | 1P5354 | 05-1P5354 | 05-SLO-1-12.1/12.2
05 | 1Q0604 | 05-1Q0604 | 05-SLO-1-12.6/12.7
05 | 1N3804 | 05-1N3804 | 05-SLO-1-17.3/0
05 | 3307C4 | 05-3307C4 | 05-SLO-41-44.5/45.3
05 | 1S4804 | 05-1S4804 | 05-SLO-46-4.3/5.1
05 | 1Q03U4 | 05-1Q03U4 | 05-SLO-46-60.3/60.8
05 | 1J9704 | 05-1J9704 | 05-SLO-58-1.8/6.9
05 | 1Q4704 | 05-1Q4704 | 05-SLO-58-51.0/57.2
05 | 1J8604 | 05-1J8604 | 05-SLO-101-7.8/16.5
05 | 1N3404 | 05-1N3404 | 05-SLO-101-28.6/29.6
05 | 1J7804 | 05-1J7804 | 05-SLO-101-61.7/62.1
05 | 1S9304 | 05-1S9304 | 05-SLO-101-250.0/85
05 | 1R2904 | 05-1R2904 | 05-VAR--/0
06 | 1G8204 | 06-1G8204 | 06-FRE-33-46.8/47.4
06 | 0X3004 | 06-0X3004 | 06-FRE-33-69.4/71.5
06 | 1G0904 | 06-1G0904 | 06-FRE-41-28.2/28.2
06 | 1E7604 | 06-1E7604 | 06-FRE-41-21.1/32.2
06 | 0X7804 | 06-0X7804 | 06-FRE-41-23.2/31.7
06 | 1G4504 | 06-1G4504 | 06-FRE-41-23.7/24.5
06 | 1E7304 | 06-1E7304 | 06-FRE-41-25.3/0
06 | 0W1704 | 06-0W1704 | 06-FRE-41-27.4/28.5
06 | 1G3504 | 06-1G3504 | 06-FRE-99-233.0/0
06 | 0U4214 | 06-0U4214 | 06-FRE-99-4.9/7.2
06 | 1F8204 | 06-1F8204 | 06-FRE-168-39.6/45.7
06 | 0Q5204 | 06-0Q5204 | 06-FRE-168-48.2/0
06 | 1F8304 | 06-1F8304 | 06-FRE-180-43.5/53.6
06 | 342354 | 06-342354 | 06-FRE-180-54.1/56
06 | 0X0604 | 06-0X0604 | 06-FRE-198-.5/19.5
06 | 0Y7604 | 06-0Y7604 | 06-FRE-5506-/0
06 | 0U5004 | 06-0U5004 | 06-KER-5-10.2/16
06 | 0X3304 | 06-0X3304 | 06-KER-5-/4.4
06 | 0X2404 | 06-0X2404 | 06-KER-33-21.8/39.8
06 | 0Y1304 | 06-0Y1304 | 06-KER-33-40.4/59.3
06 | 0Q2814 | 06-0Q2814 | 06-KER-99-23.6/28.4
06 | 1E7804 | 06-1E7804 | 06-KER-99-49.3/50.4
06 | 0W79U4 | 06-0W79U4 | 06-KER-99-56.4/57.6
06 | 1G8004 | 06-1G8004 | 06-KER-99-29.4/33.1
06 | 1H0604 | 06-1H0604 | 06-KER-155-17.8/39.6
06 | 0S0504 | 06-0S0504 | 06-KER-166-17.5/0
06 | 0X3804 | 06-0X3804 | 06-KER-166-/10.2
06 | 0U4304 | 06-0U4304 | 06-KER-184-8.5/11.6
06 | 1H0504 | 06-1H0504 | 06-KER-223-12.5/30.1
06 | 1E6704 | 06-1E6704 | 06-KER-223-20.1/21.1
06 | 1G7704 | 06-1G7704 | 06-KIN-5-16.6/26.7
06 | 0W8204 | 06-0W8204 | 06-KIN-41-28.4/40.1
06 | 0Y1704 | 06-0Y1704 | 06-KIN-41-/15.5
06 | 0V1204 | 06-0V1204 | 06-MAD-99-6.9/7.6
06 | 1G5804 | 06-1G5804 | 06-MPA-41-3.1/3.1
06 | 0X7004 | 06-0X7004 | 06-TUL-63-5.8/L8
06 | 1G7404 | 06-1G7404 | 06-TUL-63-12.1/21.6
06 | 1E8004 | 06-1E8004 | 06-TUL-63-21.7/24.3
06 | 1G8104 | 06-1G8104 | 06-TUL-63-19.2/24.3
06 | 1E6904 | 06-1E6904 | 06-TUL-99-9.8/40.7
06 | 1G8404 | 06-1G8404 | 06-TUL-99-13.5/19.5
06 | 0X2504 | 06-0X2504 | 06-TUL-99-20.8/53.1
06 | 0U8804 | 06-0U8804 | 06-TUL-99-26.3/27.6
06 | 0W9104 | 06-0W9104 | 06-TUL-99-27.6/30.6
06 | 360304 | 06-360304 | 06-TUL-99-30.2/35.2
06 | 360244 | 06-360244 | 06-TUL-99-30.6/35.2
06 | 487404 | 06-487404 | 06-TUL-99-35.8/37.1
06 | 0Q4324 | 06-0Q4324 | 06-TUL-190-13.1/16.6
06 | 1H6904 | 06-1H6904 | 06-TUL-190-42.7/42.8
06 | 1H6704 | 06-1H6704 | 06-TUL-190-366.0/0
06 | 0X2604 | 06-0X2604 | 06-TUL-198-1.6/43.9
06 | 0W90U4 | 06-0W90U4 | 06-TUL-198-11.6/11.9
06 | 0W9704 | 06-0W9704 | 06-VAR--/0
06 | 1F9004 | 06-1F9004 | 06-VAR--/0
06 | 1G1804 | 06-1G1804 | 06-VAR--/0
07 | 2XM404 | 07-2XM404 | 07-LA-0-/0
07 | 2XM204 | 07-2XM204 | 07-LA-1-1.4/7.3
07 | 346104 | 07-346104 | 07-LA-1-7.0/7.4
07 | 4V2104 | 07-4V2104 | 07-LA-1-10.4/10.4
07 | 377604 | 07-377604 | 07-LA-1-29.4/0
07 | 2XR604 | 07-2XR604 | 07-LA-1-34.9/38
07 | 2XS304 | 07-2XS304 | 07-LA-1-36.0/41
07 | 2XS204 | 07-2XS204 | 07-LA-1-37.0/46
07 | 313504 | 07-313504 | 07-LA-1-37.7/62.9
07 | 2XS104 | 07-2XS104 | 07-LA-1-39.9/40
07 | 2XE004 | 07-2XE004 | 07-LA-1-40.0/40.5
07 | 2XQ704 | 07-2XQ704 | 07-LA-1-40.7/54.1
07 | 2XS404 | 07-2XS404 | 07-LA-1-41.0/45.6
07 | 2XT304 | 07-2XT304 | 07-LA-1-42.0/44
07 | 2XR204 | 07-2XR204 | 07-LA-1-42.2/42.4
07 | 4X9704 | 07-4X9704 | 07-LA-1-42.4/0
07 | 2XR904 | 07-2XR904 | 07-LA-1-43.5/45.5
07 | 2XR104 | 07-2XR104 | 07-LA-1-43.7/43.7
07 | 2XG904 | 07-2XG904 | 07-LA-1-44.1/58.5
07 | 4V3804 | 07-4V3804 | 07-LA-1-45.6/45.9
07 | 2XR504 | 07-2XR504 | 07-LA-1-46.3/49.4
07 | 291404 | 07-291404 | 07-LA-1-56.5/56.9
07 | 2XG804 | 07-2XG804 | 07-LA-1-352.0/44.1
07 | 2XR704 | 07-2XR704 | 07-LA-1-380.0/40
07 | 2XP704 | 07-2XP704 | 07-LA-1-388.0/40.4
07 | 2XR804 | 07-2XR804 | 07-LA-1-400.0/43.5
07 | 321604 | 07-321604 | 07-LA-1-/18
07 | 333604 | 07-333604 | 07-LA-2-2.3/14.2
07 | 348504 | 07-348504 | 07-LA-2-15.0/26.5
07 | 355404 | 07-355404 | 07-LA-2-15.0/57.5
07 | 351304 | 07-351304 | 07-LA-2-15.1/15.3
07 | 2XK404 | 07-2XK404 | 07-LA-2-15.8/15.8
07 | 349004 | 07-349004 | 07-LA-2-68.1/82.1
07 | 0W2104 | 07-0W2104 | 07-LA-2-18.7/0
07 | 357304 | 07-357304 | 07-LA-5-6.6/13.1
07 | 2XQ404 | 07-2XQ404 | 07-LA-5-6.8/0
07 | 4V3004 | 07-4V3004 | 07-LA-5-8.2/8.2
07 | 2XJ004 | 07-2XJ004 | 07-LA-5-16.0/17.3
07 | 344204 | 07-344204 | 07-LA-5-23.2/36.3
07 | 0W1004 | 07-0W1004 | 07-LA-5-31.8/42.6
07 | 384404 | 07-384404 | 07-LA-5-33.1/39.1
07 | 2XS804 | 07-2XS804 | 07-LA-5-53.7/53.7
07 | 2XT504 | 07-2XT504 | 07-LA-5-138.0/13.8
07 | 0Y1504 | 07-0Y1504 | 07-LA-5-151.1/188.2
07 | 4V5404 | 07-4V5404 | 07-LA-5-56.4/56.7
07 | 370404 | 07-370404 | 07-LA-5-59.5/73.7
07 | 323404 | 07-323404 | 07-LA-5-59.5/67.9
07 | 352304 | 07-352304 | 07-LA-5-60.0/75
07 | 319304 | 07-319304 | 07-LA-5-/19.5
07 | 2XH804 | 07-2XH804 | 07-LA-10-2.2/5.2
07 | 2XL304 | 07-2XL304 | 07-LA-10-14.5/17.4
07 | 2XL004 | 07-2XL004 | 07-LA-10-17.0/17.7
07 | 386004 | 07-386004 | 07-LA-10-18.8/20.5
07 | 328304 | 07-328304 | 07-LA-10-28.2/31
07 | 316804 | 07-316804 | 07-LA-10-28.3/28.3
07 | 398404 | 07-398404 | 07-LA-10-28.5/30.8
07 | 4V5304 | 07-4V5304 | 07-LA-10-47.9/0
07 | 2XP804 | 07-2XP804 | 07-LA-10-78.0/9.3
07 | 347504 | 07-347504 | 07-LA-10-2.2/4.9
07 | 332004 | 07-332004 | 07-LA-10-4.5/5.5
07 | 358404 | 07-358404 | 07-LA-10-4.7/18.9
07 | 339604 | 07-339604 | 07-LA-14-29.0/29.5
07 | 316004 | 07-316004 | 07-LA-14-60.7/77
07 | 2XK004 | 07-2XK004 | 07-LA-23-/0
07 | 0W4104 | 07-0W4104 | 07-LA-23-/8.9
07 | 2XR304 | 07-2XR304 | 07-LA-27-/11
07 | 322904 | 07-322904 | 07-LA-27-/18.6
07 | 2XN904 | 07-2XN904 | 07-LA-27-/5
07 | 2XT904 | 07-2XT904 | 07-LA-47-1.6/1.6
07 | 2XA704 | 07-2XA704 | 07-LA-47-/3.3
07 | 0Y1404 | 07-0Y1404 | 07-LA-60-23.0/0
07 | 0Y1804 | 07-0Y1804 | 07-LA-60-/3.3
07 | 210624 | 07-210624 | 07-LA-71-1.6/4.8
07 | 0Y1704 | 07-0Y1704 | 07-LA-71-3.4/14.8
07 | 346504 | 07-346504 | 07-LA-91-6.0/20.7
07 | 3203U4 | 07-3203U4 | 07-LA-91-16.6/16.8
07 | 0W0604 | 07-0W0604 | 07-LA-101-1.0/9.2
07 | 0W2904 | 07-0W2904 | 07-LA-101-1.5/10.9
07 | 346304 | 07-346304 | 07-LA-101-7.9/11.8
07 | 385404 | 07-385404 | 07-LA-101-10.3/10.3
07 | 346004 | 07-346004 | 07-LA-101-11.0/23.5
07 | 388704 | 07-388704 | 07-LA-101-19.7/20
07 | 307104 | 07-307104 | 07-LA-101-32.8/33.8
07 | 385204 | 07-385204 | 07-LA-101-1.0/10.3
07 | 329604 | 07-329604 | 07-LA-101-6.2/8
07 | 320104 | 07-320104 | 07-LA-101-/1.5
07 | 327304 | 07-327304 | 07-LA-103-.1/.1
07 | 2XH7A4 | 07-2XH7A4 | 07-LA-105-2.2/2.2
07 | 2XJ504 | 07-2XJ504 | 07-LA-105-20.0/2
07 | 2XQ304 | 07-2XQ304 | 07-LA-105-/18.1
07 | 355604 | 07-355604 | 07-LA-105-2.0/0
07 | 357004 | 07-357004 | 07-LA-105-4.3/5
07 | 385604 | 07-385604 | 07-LA-105-9.0/9.4
07 | 4V4904 | 07-4V4904 | 07-LA-105-17.5/17.8
07 | 4W7804 | 07-4W7804 | 07-LA-110-6.8/19.5
07 | 386304 | 07-386304 | 07-LA-110-14.0/21
07 | 2XJ104 | 07-2XJ104 | 07-LA-110-21.4/25.7
07 | 2XQ504 | 07-2XQ504 | 07-LA-110-26.7/30.7
07 | 2XT604 | 07-2XT604 | 07-LA-110-30.5/30.7
07 | 336804 | 07-336804 | 07-LA-118-4.5/9.1
07 | 385904 | 07-385904 | 07-LA-118-10.0/13.2
07 | 322004 | 07-322004 | 07-LA-118-11.0/14
07 | 355004 | 07-355004 | 07-LA-118-13.0/13.9
07 | 2XS604 | 07-2XS604 | 07-LA-118-/0
07 | 333704 | 07-333704 | 07-LA-138-43.4/51.4
07 | 4V5204 | 07-4V5204 | 07-LA-138-59.7/0
07 | 320804 | 07-320804 | 07-LA-164-4.0/6.9
07 | 358804 | 07-358804 | 07-LA-170-16.6/19.8
07 | 326804 | 07-326804 | 07-LA-210-9.7/51.9
07 | 2XF404 | 07-2XF404 | 07-LA-210-15.4/15.4
07 | 0Y1604 | 07-0Y1604 | 07-LA-210-9.9/22.5
07 | 330704 | 07-330704 | 07-LA-210-15.6/18.5
07 | 348704 | 07-348704 | 07-LA-210-18.7/19.7
07 | 348204 | 07-348204 | 07-LA-210-19.4/27
07 | 4V5004 | 07-4V5004 | 07-LA-210-24.7/25.3
07 | 301704 | 07-301704 | 07-LA-210-33.6/36.5
07 | 356104 | 07-356104 | 07-LA-210-37.8/39.1
07 | 2XQ604 | 07-2XQ604 | 07-LA-210-/0
07 | 4V1404 | 07-4V1404 | 07-LA-213-6.2/6.2
07 | 4V2304 | 07-4V2304 | 07-LA-213-6.4/0
07 | 338704 | 07-338704 | 07-LA-405-12.9/21.5
07 | 4V3204 | 07-4V3204 | 07-LA-405-22.2/23.5
07 | 4V4304 | 07-4V4304 | 07-LA-405-30.1/33
07 | 347904 | 07-347904 | 07-LA-405-31.2/41.4
07 | 2XG604 | 07-2XG604 | 07-LA-405-36.3/36.3
07 | 2XM804 | 07-2XM804 | 07-LA-405-36.3/37.1
07 | 320204 | 07-320204 | 07-LA-405-40.1/48.1
07 | 0W7004 | 07-0W7004 | 07-LA-405-44.7/486.4
07 | 356604 | 07-356604 | 07-LA-605-10.2/20.2
07 | 3255U4 | 07-3255U4 | 07-LA-605-20.2/26
07 | 345104 | 07-345104 | 07-LA-710-5.0/9.5
07 | 349904 | 07-349904 | 07-LA-710-6.0/14.1
07 | 4V4204 | 07-4V4204 | 07-LA-710-6.2/7.2
07 | 347004 | 07-347004 | 07-LA-710-9.6/T32.1
07 | 385804 | 07-385804 | 07-LA-710-13.8/15.3
07 | 390804 | 07-390804 | 07-LA-710-19.6/19.9
07 | 354704 | 07-354704 | 07-LA-710-22.0/0
07 | 331804 | 07-331804 | 07-LA-710-26.0/26.7
07 | 2XT404 | 07-2XT404 | 07-LA-710-194.0/19.4
07 | 354804 | 07-354804 | 07-LA-5808-/2.5
07 | 358204 | 07-358204 | 07-LA-5823-/7.2
07 | 322704 | 07-322704 | 07-VAR-1-1.3/26.6
07 | 0W8804 | 07-0W8804 | 07-VAR-1-23.1/23.1
07 | 348804 | 07-348804 | 07-VAR-2-18.7/18.7
07 | 0W6104 | 07-0W6104 | 07-VAR-5-/40
07 | 346204 | 07-346204 | 07-VAR-23-3.6/11.4
07 | 338604 | 07-338604 | 07-VAR-91-6.1/20.7
07 | 355104 | 07-355104 | 07-VAR-105-2.1/2.1
07 | 0W5904 | 07-0W5904 | 07-VAR-110-15.1/23
07 | 349504 | 07-349504 | 07-VAR-170-14.5/20.5
07 | 349104 | 07-349104 | 07-VAR-210-43.9/46.7
07 | 350334 | 07-350334 | 07-VAR--/0
07 | 350404 | 07-350404 | 07-VAR--/0
07 | 0W6604 | 07-0W6604 | 07-VAR--/0
07 | 504444 | 07-504444 | 07-VAR--/0
07 | 0W8704 | 07-0W8704 | 07-VAR--/0
07 | 351124 | 07-351124 | 07-VAR--/0
07 | 0W7604 | 07-0W7604 | 07-VAR--/0
07 | 0Y2004 | 07-0Y2004 | 07-VAR--/0
07 | 350704 | 07-350704 | 07-VAR--/0
07 | 301604 | 07-301604 | 07-VAR--/0
07 | 353804 | 07-353804 | 07-VAR--/0
07 | 0W8904 | 07-0W8904 | 07-VAR--/0
07 | 350324 | 07-350324 | 07-VAR--/0
07 | 351704 | 07-351704 | 07-VAR--/0
07 | 0W9904 | 07-0W9904 | 07-VAR--/0
07 | 0Y1904 | 07-0Y1904 | 07-VAR--/0
07 | 0Y0504 | 07-0Y0504 | 07-VAR--/0
07 | 0Y1004 | 07-0Y1004 | 07-VAR--/0
07 | 351504 | 07-351504 | 07-VAR--/0
07 | 0W7704 | 07-0W7704 | 07-VAR--/0
07 | 0Y0904 | 07-0Y0904 | 07-VAR--/0
07 | 0W9804 | 07-0W9804 | 07-VAR--/0
07 | 0W6504 | 07-0W6504 | 07-VAR--/0
07 | 351114 | 07-351114 | 07-VAR--/0
07 | 350314 | 07-350314 | 07-VAR--/0
07 | 0W9704 | 07-0W9704 | 07-VAR--/0
07 | 4P8504 | 07-4P8504 | 07-VEN-1-1.0/1.3
07 | 318204 | 07-318204 | 07-VEN-1-4.0/4.2
07 | 323904 | 07-323904 | 07-VEN-1-21.3/28.4
07 | 319604 | 07-319604 | 07-VEN-1-21.3/21.9
07 | 2XE704 | 07-2XE704 | 07-VEN-23-17.7/24.1
07 | 348404 | 07-348404 | 07-VEN-23-/3.3
07 | 2XC604 | 07-2XC604 | 07-VEN-33-12.6/16.5
07 | 332304 | 07-332304 | 07-VEN-33-18.9/19.1
07 | 2XF604 | 07-2XF604 | 07-VEN-33-24.2/27.3
07 | 356804 | 07-356804 | 07-VEN-33-26.9/41.7
07 | 2XF704 | 07-2XF704 | 07-VEN-33-44.2/57.2
07 | 355204 | 07-355204 | 07-VEN-33-3.3/21.2
07 | 3311U4 | 07-3311U4 | 07-VEN-101-.2/40.8
07 | 2XT104 | 07-2XT104 | 07-VEN-101-2.2/2.2
07 | 0W3904 | 07-0W3904 | 07-VEN-101-10.7/26.7
07 | 0Y1304 | 07-0Y1304 | 07-VEN-101-25.9/30.6
07 | 0W4004 | 07-0W4004 | 07-VEN-101-30.9/36.3
07 | 369704 | 07-369704 | 07-VEN-118-12.0/13.4
07 | 341604 | 07-341604 | 07-VEN-118-13.3/15.6
07 | 336004 | 07-336004 | 07-VEN-118-1.4/1.8
07 | 385104 | 07-385104 | 07-VEN-118-23.5/30.5
07 | 387904 | 07-387904 | 07-VEN-118-18.4/T18.8
07 | 2XE104 | 07-2XE104 | 07-VEN-126-9.7/24.6
07 | 1XW104 | 07-1XW104 | 07-VEN-126-20.3/20.3
07 | 356504 | 07-356504 | 07-VEN-126-14.6/34.5
07 | 2XP204 | 07-2XP204 | 07-VEN-126-/0
07 | 2XN104 | 07-2XN104 | 07-VEN-150-20.0/32.2
07 | 344504 | 07-344504 | 07-VEN-150-31.3/34.4
07 | 3237U4 | 07-3237U4 | 07-VEN-150-13.3/19
07 | 346804 | 07-346804 | 07-VEN-232-.4/4.1
07 | 2XM504 | 07-2XM504 | 07-VEN--/0
08 | 1P0804 | 08-1P0804 | 08-RIV-10-7.0/44.5
08 | 1L9504 | 08-1L9504 | 08-RIV-10-12.6/13.4
08 | 1T1404 | 08-1T1404 | 08-RIV-10-748.0/81.7
08 | 1C0814 | 08-1C0814 | 08-RIV-10-60.7/74.3
08 | 0G8504 | 08-0G8504 | 08-RIV-10-71.2/72.6
08 | 1C08U4 | 08-1C08U4 | 08-RIV-10-134.0/156.5
08 | 1K4004 | 08-1K4004 | 08-RIV-15-3.5/6.8
08 | 1E3404 | 08-1E3404 | 08-RIV-15-15.9/20.3
08 | 1J8704 | 08-1J8704 | 08-RIV-15-16.3/52.3
08 | 1R3804 | 08-1R3804 | 08-RIV-15-18.7/19
08 | 1R4204 | 08-1R4204 | 08-RIV-15-35.1/35.1
08 | 1P0704 | 08-1P0704 | 08-RIV-15-46.5/49.3
08 | 1R4504 | 08-1R4504 | 08-RIV-15-.6/1.6
08 | 1H3804 | 08-1H3804 | 08-RIV-60-6.1/8
08 | 1P6804 | 08-1P6804 | 08-RIV-62-3.3/6.5
08 | 1G4704 | 08-1G4704 | 08-RIV-74-3.1/3
08 | 1R3704 | 08-1R3704 | 08-RIV-74-3.9/11.8
08 | 1K6904 | 08-1K6904 | 08-RIV-74-5.7/11.8
08 | 1L3104 | 08-1L3104 | 08-RIV-74-11.8/17.3
08 | 1C07U4 | 08-1C07U4 | 08-RIV-74-27.5/34.3
08 | 1G6704 | 08-1G6704 | 08-RIV-79-5.4/11.4
08 | 1P2804 | 08-1P2804 | 08-RIV-91-8.3/9
08 | 1L3204 | 08-1L3204 | 08-RIV-91-15.6/21.6
08 | 1G6304 | 08-1G6304 | 08-RIV-111-47.2/55.3
08 | 0R7904 | 08-0R7904 | 08-RIV-111-53.9/0
08 | 1J2904 | 08-1J2904 | 08-RIV-215-25.0/31.2
08 | 1J6104 | 08-1J6104 | 08-RIV-215-40.5/42.7
08 | 1N9704 | 08-1N9704 | 08-RIV-215-9.0/38
08 | 1J2604 | 08-1J2604 | 08-RIV-215-13.5/19.5
08 | 1J4504 | 08-1J4504 | 08-RIV-243-/29.7
08 | 1J3204 | 08-1J3204 | 08-RIV-5732-/0
08 | 1J6204 | 08-1J6204 | 08-SBD-0-/0
08 | 1J5404 | 08-1J5404 | 08-SBD-15-2.4/0
08 | 1R2804 | 08-1R2804 | 08-SBD-15-7.6/7.6
08 | 1L5104 | 08-1L5104 | 08-SBD-15-15.9/0
08 | 1J3304 | 08-1J3304 | 08-SBD-15-160.9/161.5
08 | 1N1214 | 08-1N1214 | 08-SBD-15-180.9/185.5
08 | 1H3904 | 08-1H3904 | 08-SBD-15-20.5/21.6
08 | 0N0804 | 08-0N0804 | 08-SBD-15-/0
08 | 1R5004 | 08-1R5004 | 08-SBD-18-18.4/19.2
08 | 1J3004 | 08-1J3004 | 08-SBD-18-90.9/96.6
08 | 1T3304 | 08-1T3304 | 08-SBD-38-14.9/44.2
08 | 1T2804 | 08-1T2804 | 08-SBD-40-5.0/7
08 | 1K4904 | 08-1K4904 | 08-SBD-40-105.1/105.9
08 | 1N7804 | 08-1N7804 | 08-SBD-40-129.8/135.9
08 | 1M0404 | 08-1M0404 | 08-SBD-40-140.0/142.2
08 | 1J7204 | 08-1J7204 | 08-SBD-40-/S.8
08 | 1P1204 | 08-1P1204 | 08-SBD-60-6.9/9.9
08 | 1T2604 | 08-1T2604 | 08-SBD-62-307.0/31.3
08 | 1T3504 | 08-1T3504 | 08-SBD-62-540.0/79.5
08 | 1L2404 | 08-1L2404 | 08-SBD-95-57.2/64.5
08 | 1N7504 | 08-1N7504 | 08-SBD-138-21.4/37.8
08 | 1T1004 | 08-1T1004 | 08-SBD-138-23.9/33.6
08 | 1R7304 | 08-1R7304 | 08-SBD-138-18.9/19.5
08 | 1N7704 | 08-1N7704 | 08-SBD-173-/L7.7
08 | 1M7404 | 08-1M7404 | 08-SBD-210-1.2/1.6
08 | 0N0604 | 08-0N0604 | 08-SBD-210-14.6/16.4
08 | 1P0604 | 08-1P0604 | 08-SBD-210-15.7/17.9
08 | 1L9704 | 08-1L9704 | 08-SBD-210-23.1/24.7
08 | 1P6104 | 08-1P6104 | 08-SBD-210-/33.2
08 | 1J2704 | 08-1J2704 | 08-SBD-247-/23
08 | 1T2704 | 08-1T2704 | 08-SBD-247-/0
08 | 1R3304 | 08-1R3304 | 08-SBD-330-296.0/43.9
08 | 1R6404 | 08-1R6404 | 08-SBD-330-29.6/43.9
08 | 1G6404 | 08-1G6404 | 08-SBD-395-4.0/49
08 | 1R0404 | 08-1R0404 | 08-VAR--/0
08 | 1P0904 | 08-1P0904 | 08-VAR--/0
08 | 1N4704 | 08-1N4704 | 08-VAR--/0
08 | 1J8504 | 08-1J8504 | 08-VAR--/0
08 | 1J8604 | 08-1J8604 | 08-VAR--/0
08 | 1H9924 | 08-1H9924 | 08-VAR--/0
08 | 1P8904 | 08-1P8904 | 08-VAR--/0
08 | 1H8804 | 08-1H8804 | 08-VAR--/0
08 | 1J8404 | 08-1J8404 | 08-VAR--/0
08 | 1P6604 | 08-1P6604 | 08-VAR--/0
08 | 1E1404 | 08-1E1404 | 08-VAR--/0
08 | 1H9914 | 08-1H9914 | 08-VAR--/0
09 | 374704 | 09-374704 | 09-INY-168-17.6/18.3
09 | 213404 | 09-213404 | 09-INY-395-29.2/41.8
09 | 390204 | 09-390204 | 09-INY-395-57.4/0
09 | 379104 | 09-379104 | 09-INY-395-91.6/100.8
09 | 366804 | 09-366804 | 09-INY-395-117.3/117.9
09 | 398404 | 09-398404 | 09-INY-395-122.0/129.5
09 | 379504 | 09-379504 | 09-INY-5709-/0
09 | 367504 | 09-367504 | 09-KER-5756-/92
09 | 404304 | 09-404304 | 09-MNO-120-32.1/35
09 | 368004 | 09-368004 | 09-MNO-395-91.6/93.4
09 | 378804 | 09-378804 | 09-MNO-395-9.8/12.6
09 | 398504 | 09-398504 | 09-MNO-395-44.6/50.7
10 | 0Q2104 | 10-0Q2104 | 10-AMA-88-5.5/14.3
10 | 0K1304 | 10-0K1304 | 10-AMA-88-54.7/60.8
10 | 1H5004 | 10-1H5004 | 10-CAL-4-15.9/16.3
10 | 1S6504 | 10-1S6504 | 10-CAL-12-2.9/9.9
10 | 1J8204 | 10-1J8204 | 10-CAL-12-9.9/10.3
10 | 0X7404 | 10-0X7404 | 10-CAL-12-17.1/17.5
10 | 0V4804 | 10-0V4804 | 10-CAL-26-21.8/30.3
10 | 1H7004 | 10-1H7004 | 10-CAL-49-7.5/9.4
10 | 1C7904 | 10-1C7904 | 10-MER-5-.5/.8
10 | 1G2504 | 10-1G2504 | 10-MER-33-.6/1.5
10 | 3A7214 | 10-3A7214 | 10-MER-99-19.5/20.7
10 | 1K0904 | 10-1K0904 | 10-MER-99-3.3/6.9
10 | 1K4304 | 10-1K4304 | 10-MER-165-16.5/26.8
10 | 1S6404 | 10-1S6404 | 10-MER-165-/7
10 | 0P9244 | 10-0P9244 | 10-MPA-140-42.0/42.7
10 | 1S5204 | 10-1S5204 | 10-MPA-140-293.0/29.3
10 | 1R9904 | 10-1R9904 | 10-SJ-4-.5/.5
10 | 1L2804 | 10-1L2804 | 10-SJ-4-20.5/20.8
10 | 1R8804 | 10-1R8804 | 10-SJ-4-141.0/14.1
10 | 1F1804 | 10-1F1804 | 10-SJ-4-16.0/19.4
10 | 1H3604 | 10-1H3604 | 10-SJ-4-/0
10 | 1R7004 | 10-1R7004 | 10-SJ-5-.3/3.5
10 | 1L3404 | 10-1L3404 | 10-SJ-5-7.5/0
10 | 1E3004 | 10-1E3004 | 10-SJ-5-32.5/49.8
10 | 1T5604 | 10-1T5604 | 10-SJ-99-7.9/7.9
10 | 1N9004 | 10-1N9004 | 10-SJ-99-21.6/0
10 | 1U1004 | 10-1U1004 | 10-SJ-99-21.9/21.9
10 | 1H6504 | 10-1H6504 | 10-SJ-99-28.7/31.7
10 | 1C3304 | 10-1C3304 | 10-SJ-205-4.6/9
10 | 1U4704 | 10-1U4704 | 10-SJ-580-12.7/12.7
10 | 1H2804 | 10-1H2804 | 10-STA-5-10.7/25.5
10 | 1C2704 | 10-1C2704 | 10-STA-5-27.1/27.4
10 | 1R7704 | 10-1R7704 | 10-STA-99-1.5/16
10 | 1S4904 | 10-1S4904 | 10-STA-99-17.0/17
10 | 1K8404 | 10-1K8404 | 10-STA-108-33.2/33.5
10 | 0G8304 | 10-0G8304 | 10-VAR-59-/0
10 | 1S3304 | 10-1S3304 | 10-VAR--/0
10 | 1G0204 | 10-1G0204 | 10-VAR--/0
10 | 1S5804 | 10-1S5804 | 10-VAR--/0
10 | 1F9704 | 10-1F9704 | 10-VAR--/0
10 | 1F9604 | 10-1F9604 | 10-VAR--/0
10 | 1L8604 | 10-1L8604 | 10-VAR--/0
10 | 1R7204 | 10-1R7204 | 10-VAR--/0
11 | 432194 | 11-432194 | 11-IMP-0-/0
11 | 432934 | 11-432934 | 11-IMP-0-/0
11 | 2N1784 | 11-2N1784 | 11-IMP-8-/10.3
11 | 2N1764 | 11-2N1764 | 11-IMP-8-50.3/96.7
11 | 2N2284 | 11-2N2284 | 11-IMP-78-/13.2
11 | 2N2304 | 11-2N2304 | 11-IMP-86-4.5/L8.5
11 | 2N2264 | 11-2N2264 | 11-IMP-98-30.0/57
11 | 080284 | 11-080284 | 11-IMP-98-32.1/32.5
11 | 2N1974 | 11-2N1974 | 11-IMP-111-23.5/32.1
11 | 2N1474 | 11-2N1474 | 11-IMP-111-50.7/0
11 | 432564 | 11-432564 | 11-SD-0-/0
11 | 432854 | 11-432854 | 11-SD-0-/0
11 | 432504 | 11-432504 | 11-SD-0-/0
11 | 432784 | 11-432784 | 11-SD-0-/0
11 | 432674 | 11-432674 | 11-SD-0-/0
11 | 432304 | 11-432304 | 11-SD-5-4.6/4.6
11 | 4B0334 | 11-4B0334 | 11-SD-5-9.1/16.1
11 | 4B0044 | 11-4B0044 | 11-SD-5-9.5/0
11 | 432714 | 11-432714 | 11-SD-5-10.4/10.4
11 | 2E1544 | 11-2E1544 | 11-SD-5-34.7/36.3
11 | 2T35U4 | 11-2T35U4 | 11-SD-5-37.4/52.6
11 | 431274 | 11-431274 | 11-SD-5-.3/36
11 | 4C0034 | 11-4C0034 | 11-SD-5-.9/0
11 | 2T0444 | 11-2T0444 | 11-SD-5-4.4/4.5
11 | 431994 | 11-431994 | 11-SD-5-16.0/16
11 | 432694 | 11-432694 | 11-SD-5-19.4/19.4
11 | 2N1754 | 11-2N1754 | 11-SD-5-30.6/52.8
11 | 2T36U4 | 11-2T36U4 | 11-SD-5-37.4/52.6
11 | 2N1684 | 11-2N1684 | 11-SD-5-53.9/63.7
11 | 432434 | 11-432434 | 11-SD-5-54.2/54.2
11 | 430824 | 11-430824 | 11-SD-5-66.2/67.4
11 | 4B0084 | 11-4B0084 | 11-SD-8-15.8/21.9
11 | 432844 | 11-432844 | 11-SD-8-26.0/32
11 | 432824 | 11-432824 | 11-SD-8-41.8/41.8
11 | 2N2324 | 11-2N2324 | 11-SD-8-73.0/77.8
11 | 056404 | 11-056404 | 11-SD-11-.6/2.7
11 | 430194 | 11-430194 | 11-SD-15-.4/10.2
11 | 2N2344 | 11-2N2344 | 11-SD-15-.4/T2.8
11 | 432444 | 11-432444 | 11-SD-15-2.1/2.2
11 | 432914 | 11-432914 | 11-SD-15-45.0/4.5
11 | 430514 | 11-430514 | 11-SD-15-31.3/37.1
11 | 430254 | 11-430254 | 11-SD-52-5.1/9
11 | 2T3644 | 11-2T3644 | 11-SD-56-.3/3
11 | 411904 | 11-411904 | 11-SD-56-.3/9.7
11 | 4B0054 | 11-4B0054 | 11-SD-67-3.9/6.1
11 | 2N0204 | 11-2N0204 | 11-SD-76-17.2/24.1
11 | 431644 | 11-431644 | 11-SD-78-/N17.7
11 | 430364 | 11-430364 | 11-SD-79-20.2/53
11 | 2N2244 | 11-2N2244 | 11-SD-79-.6/52.9
11 | 2N2064 | 11-2N2064 | 11-SD-94-1.6/13.3
11 | 430244 | 11-430244 | 11-SD-125-9.3/13
11 | 411404 | 11-411404 | 11-SD-125-9.6/13.2
11 | 4B0124 | 11-4B0124 | 11-SD-125-12.9/22.3
11 | 4B0394 | 11-4B0394 | 11-SD-163-.7/3.1
11 | 4B0384 | 11-4B0384 | 11-SD-163-3.1/10.9
11 | 430484 | 11-430484 | 11-SD-163-4.3/10.8
11 | 430234 | 11-430234 | 11-SD-805-.1/14.6
11 | 2N1714 | 11-2N1714 | 11-SD-805-.5/14.6
11 | 2T3434 | 11-2T3434 | 11-SD-805-5.1/8.3
11 | 432944 | 11-432944 | 11-SD-805-11.2/13.3
11 | 430324 | 11-430324 | 11-SD-805-14.6/23.7
11 | 430384 | 11-430384 | 11-SD-805-23.7/28.5
11 | 430394 | 11-430394 | 11-SD-805-23.9/25.1
11 | 431064 | 11-431064 | 11-SD-905-6.4/10.1
11 | 432024 | 11-432024 | 11-SD--/0
11 | 2N2254 | 11-2N2254 | 11-VAR--/0
11 | 430904 | 11-430904 | 11-VAR--/0
11 | 2N1774 | 11-2N1774 | 11-VAR--/0
11 | 2N2334 | 11-2N2334 | 11-VAR--/0
11 | 2N2074 | 11-2N2074 | 11-VAR--/0
11 | 432454 | 11-432454 | 11-VAR--/0
12 | 0V4404 | 12-0V4404 | 12-0RA-241-30.0/31
12 | 0R3114 | 12-0R3114 | 12-LA-91-20.6/20.7
12 | 0P69U4 | 12-0P69U4 | 12-ORA-1-5.5/7.9
12 | 0M82U4 | 12-0M82U4 | 12-ORA-1-7.9/10.5
12 | 0P68U4 | 12-0P68U4 | 12-ORA-1-13.0/33.7
12 | 0S1404 | 12-0S1404 | 12-ORA-1-21.5/31.1
12 | 0Q9904 | 12-0Q9904 | 12-ORA-1-.1/.9
12 | 0S7504 | 12-0S7504 | 12-ORA-1-.8/0
12 | 0P42U4 | 12-0P42U4 | 12-ORA-5-.6/43
12 | 0T8604 | 12-0T8604 | 12-ORA-5-2.3/19.9
12 | 0S1704 | 12-0S1704 | 12-ORA-5-5.3/7.3
12 | 0U9204 | 12-0U9204 | 12-ORA-5-6.5/0
12 | 0S2804 | 12-0S2804 | 12-ORA-5-9.6/10.4
12 | 0K0244 | 12-0K0244 | 12-ORA-5-12.4/18.9
12 | 0K0234 | 12-0K0234 | 12-ORA-5-17.1/18.9
12 | 0J34U4 | 12-0J34U4 | 12-ORA-5-29.6/29.6
12 | 0S6904 | 12-0S6904 | 12-ORA-5-35.7/44.1
12 | 0S8404 | 12-0S8404 | 12-ORA-5-36.7/0
12 | 0S3104 | 12-0S3104 | 12-ORA-5-26.3/42.2
12 | 0S1104 | 12-0S1104 | 12-ORA-22-.9/9.4
12 | 0S7004 | 12-0S7004 | 12-ORA-22-8.6/0
12 | 0S1904 | 12-0S1904 | 12-ORA-22-11.6/12.5
12 | 0U9704 | 12-0U9704 | 12-ORA-22-/5.1
12 | 0R32U4 | 12-0R32U4 | 12-ORA-55-.2/17.8
12 | 0U5804 | 12-0U5804 | 12-ORA-55-12.3/17
12 | 0S3304 | 12-0S3304 | 12-ORA-57-11.0/22.6
12 | 0U8104 | 12-0U8104 | 12-ORA-57-11.0/22.5
12 | 0M9704 | 12-0M9704 | 12-ORA-57-11.5/12.5
12 | 0S5304 | 12-0S5304 | 12-ORA-57-15.9/0
12 | 0U9804 | 12-0U9804 | 12-ORA-57-19.6/20.1
12 | 0C1114 | 12-0C1114 | 12-ORA-57-20.3/21.6
12 | 0U5904 | 12-0U5904 | 12-ORA-73-10.3/26.8
12 | 0U9104 | 12-0U9104 | 12-ORA-73-23.5/23.8
12 | 0P0314 | 12-0P0314 | 12-ORA-74-11.5/16.6
12 | 0V0404 | 12-0V0404 | 12-ORA-90-5.4/0
12 | 0R3134 | 12-0R3134 | 12-ORA-91-6.4/9.2
12 | 0K91U4 | 12-0K91U4 | 12-ORA-91-9.2/11.4
12 | 0U2404 | 12-0U2404 | 12-ORA-91-9.8/18.9
12 | 0R3154 | 12-0R3154 | 12-ORA-91-10.8/18.9
12 | 0P94U4 | 12-0P94U4 | 12-ORA-133-3.2/4.1
12 | 0N8904 | 12-0N8904 | 12-ORA-133-8.3/M9.3
12 | 0Q9804 | 12-0Q9804 | 12-ORA-241-14.5/25.7
12 | 0Q9704 | 12-0Q9704 | 12-ORA-405-.2/11.4
12 | 0R57U4 | 12-0R57U4 | 12-ORA-405-11.4/24.2
12 | 0R6804 | 12-0R6804 | 12-ORA-605-.2/1.6
12 | 0K8704 | 12-0K8704 | 12-ORA-605-.6/1.6
12 | 0R5604 | 12-0R5604 | 12-VAR-55-5.5/17.8
12 | 0U7904 | 12-0U7904 | 12-VAR--/0

## Report 3
District | Rtrim(Federal_Aid.Category) | Rtrim(Federal_Aid.Header) | Sum_Auth_Final | Sum_Work_Comp
10 | Federal Aid (Interstate) | -I- | 17815911.59 | 11289302.7
12 | Federal Aid (Primary) | -F- | 583771028.6 | 262488410.68
04 | Federal Aid (Primary) | -F- | 471321975.66 | 281249285.42
06 | Federal Aid (Secondary) | -S- | 65739535.36 | 48868949.88
08 | Federal Aid (Secondary) | -S- | 68456841.09 | 36337884.57
07 | Federal Aid (Interstate) | -I- | 529832806.76 | 257596175.95
06 | Federal Aid (Primary) | -F- | 365703478.8 | 211127891.2
02 | Federal Aid (Primary) | -F- | 388551233.92 | 304088298.3
03 | Federal Aid (Secondary) | -S- | 85122654.42 | 81478002.67
04 |  |  | 1093098466.11 | 677004295.95
06 |  |  | 218231168.41 | 77848872.02
05 |  |  | 788546089.57 | 508371346.57
08 |  |  | 578995521.29 | 334293452.99
09 |  |  | 47324788.02 | 45738954.92
08 | Federal Aid (Primary) | -F- | 323472469 | 212127322.86
10 | Federal Aid (Primary) | -F- | 46100565.15 | 31874735.93
07 | Federal Aid (Secondary) | -S- | 69257510.73 | 18997108.75
07 |  |  | 1240357535.42 | 775431411.71
04 | Federal Aid (Interstate) | -I- | 582826911.7 | 549011951.84
03 | Federal Aid (Interstate) | -I- | 237488724.91 | 175998437.66
08 | Federal Aid (Interstate) | -I- | 222959935.01 | 152608078.47
09 | Federal Aid (Secondary) | -S- | 23088925.63 | 5833643.21
05 | Federal Aid (Secondary) | -S- | 23898602.94 | 7390376.6
03 |  |  | 1121430395.09 | 773572719.94
10 |  |  | 276349944.9 | 195849123.15
06 | Federal Aid (Interstate) | -I- | 40360444 | 38195973.36
01 | Federal Aid (Primary) | -F- | 324753141.42 | 250607001.11
04 | Federal Aid (Secondary) | -S- | 101759972.89 | 58800798.2
11 | Federal Aid (Interstate) | -I- | 358211234.88 | 147166726.85
12 | Federal Aid (Interstate) | -I- | 258335095.98 | 161649128.82
11 | Federal Aid (Primary) | -F- | 187965427.17 | 89537574.94
07 | Federal Aid (Primary) | -F- | 378878346.6 | 191941375.74
03 | Federal Aid (Primary) | -F- | 400944460.13 | 330652477.08
01 | Federal Aid (Secondary) | -S- | 112365915.62 | 83013941.14
02 | Federal Aid (Secondary) | -S- | 36553953.3 | 21400754.56
10 | Federal Aid (Secondary) | -S- | 356537092.76 | 10457013.36
11 |  |  | 695053956.18 | 438270576.24
02 |  |  | 188175462.88 | 130316337.77
09 | Federal Aid (Primary) | -F- | 155964261.83 | 131301127.75
05 | Federal Aid (Primary) | -F- | 591157736.24 | 503833902.91
12 | Federal Aid (Secondary) | -S- | 55248686.09 | 47475002.82
01 |  |  | 486471163.74 | 269745770.86
12 |  |  | 341076339.61 | 189264294.19

## Report 4
District | Ped_Comp_Tot
03 | 16437963.15
09 | 21922306.24
01 | 33028159.09
08 | 24983043.12
05 | 82912650
06 | 26902719.02
10 | 385000
04 | 33667906.06
02 | 1133698
07 | 36932805.91
11 | 64608713.9

## Report 5
Rtrim(Federal_Aid.Category) | Rtrim(Federal_Aid.Header) | Sum_Auth_Final | Sum_Work_Comp
Federal Aid (Interstate) | -I- | 2247831064.83 | 1493515775.65
Federal Aid (Secondary) | -S- | 998029690.83 | 420053475.76
Federal Aid (Primary) | -F- | 4218584124.52 | 2800829403.92
|  | 7075110831.22 | 4415707156.31