PRELIMINARY VA STUDY REPORT

The purpose of this report is to document VA alternatives developed and 
to present supporting project information at the time of the VA study to properly put the VA alternatives into perspective. This documentation is done in order to allow the review of these VA alternatives and decide each of their dispositions.

It is important to note that this is a Preliminary Report – a working copy – 
not a Draft Report. As such, it is not “official” and not discoverable until 
project management and/or project stakeholders have properly reviewed it and commented on all VA alternatives. At that point, a Final Report will be developed to document the disposition of the VA alternatives and other report comments. 
The Final Report is discussed later in the Report Guide.

Note: the Preliminary Report, only the sections that are different are colored red. Sections that are unchanged are colored gray.  Also, if necessary, the unchanged sections may be edited to correct information that may have been in error within the Preliminary Report.

Preliminary Value Analysis Study Report

Include an image representative of the project.  This could be a photograph of the project area taken during the site visit or an aerial photograph identifying the project limits.

District #, Project Title

(include county[s] if needed for route location)

PN 100000000

D#-County-Route(s) PM 1.0/2.9

Contract No. 12345

Task Order No. 6789

Month-Year of VA Study

Prepared by

XYZ Value Analysis Consultant

| XYZ Value Analysis Consultant |  | Preliminary Value Analysis Study Report Project Title (include county[s] if needed for route location) CALTRANS DISTRICT # – County, CA | Contract 12345 |  | T.O. 6789 Month-Year of VA Study |
| --- | --- | --- | --- | --- | --- |
| XYZ Value Analysis Consultant |  | Preliminary Value Analysis Study Report Project Title (include county[s] if needed for route location) CALTRANS DISTRICT # – County, CA | Contract 12345 |  | T.O. 6789 Month-Year of VA Study |
| XYZ Value Analysis Consultant |  | Preliminary Value Analysis Study Report Project Title (include county[s] if needed for route location) CALTRANS DISTRICT # – County, CA | Contract 12345 |  | T.O. 6789 Month-Year of VA Study |
| XYZ Value Analysis Consultant |  | Preliminary Value Analysis Study Report Project Title (include county[s] if needed for route location) CALTRANS DISTRICT # – County, CA | Contract 12345 |  | T.O. 6789 Month-Year of VA Study |
| XYZ Value Analysis Consultant |  | Preliminary Value Analysis Study Report Project Title (include county[s] if needed for route location) CALTRANS DISTRICT # – County, CA | Contract 12345 |  | T.O. 6789 Month-Year of VA Study |
| XYZ Value Analysis Consultant |  | Preliminary Value Analysis Study Report Project Title (include county[s] if needed for route location) CALTRANS DISTRICT # – County, CA | Contract 12345 |  | T.O. 6789 Month-Year of VA Study |

Date:	February 28, 2011

To:	Caltrans Project Manager

Subject:	Preliminary VA Study Report (Task Order 6789)

District #, Project Title (include county[s] if needed for route location)

Dear Caltrans Project Manager,

XYZ Value Analysis Consultant is pleased to submit this Preliminary VA Study Report for the referenced project.  This report summarizes the results and events of the study conducted study dates at study location. The purpose of this report is to document VA alternatives developed and to present supporting project information at the time of the VA study to properly put the VA alternatives into perspective. This documentation is done in order to allow the review of these VA alternatives and decide each of their dispositions.

It is important to note that this is a Preliminary Report – a working copy – As such, it is not “official” until project management and/or project stakeholders have properly reviewed it and commented on all VA alternatives. At that point, and based on the disposition of the VA alternatives and other report comments, a Final Report will be prepared and the results of the study reported to Caltrans HQ.  They in turn will submit the results of the study to FHWA annually.  The VA Study is not complete until the Final VA Report is submitted.

Please submit the enclosed VA Alternative Project Stakeholder Implementation Action Recommendation Forms no later than Month 00, Year to District # VA Coordinator.

If you have any questions or comments concerning this preliminary report, please do not hesitate to contact me at signatory’s contact information.

Sincerely,

XYZ Value Analysis Consultant

Signature

Signatory Name & Accreditation(s)

VA Study Team Leader

Copy:	(PDF)  Addressee

(PDF)  District VA Coordinator

(PDF)  Richel Espinoza-Noss, HQ VA Branch

NOTE TO DECISION-MAKERS

DISTRICT #, PROJECT TITLE (INCLUDE COUNTY[S] IF NEEDED FOR 
ROUTE LOCATION)

A VA Implementation Meeting will be scheduled at a future date at the District # Offices.  You will be asked to accept, conditionally accept, or reject each VA alternative included in this report.

In addition, you will be asked to agree or disagree with the cost savings and performance attribute ratings the VA team applied to each VA alternative that is accepted or conditionally accepted.

Acceptance of alternatives denotes intent to implement, based on current information, in the given project development phase (PID, PA&ED or PS&E).  It is recognized that future conditions may change this disposition.  The validation of disposition, the cost changes, and performance changes for the alternative is required by Caltrans to ensure that the project decision makers agree with the study results.  Furthermore, these validated results become the basis for the VA Program reportables.

The VA process is complete only when the implementation decisions for every VA alternative have been received from the Project Manager and documented in the VA Study Report.  The Assess Alternatives and Resolve Alternatives activities provide the VA team, the project manager, and district/region management the assurance that the alternatives are properly evaluated and the implementation decisions are based on the merit of the alternative.  This process helps to eliminate inaccurate study alternatives and legitimizes the results of the study and the VA Program.

Please complete your review of the VA alternatives and provide your written comments on the VA Alternative Project Stakeholder Implementation Action Recommendation forms no later than Month 00, Year to:

e-mail:  districtVAcoordinator@dot.ca.gov

During the Implementation Meeting, we will review the individual Implementation Action Recommendation Form responses, develop a consensus for each VA alternative, document the responses to each alternative, and conclude decisions related to implementation.  After that meeting, we will integrate the results into the Final VA Study Report.

Responses prepared by:

Date:

VA ALTERNATIVE 1.0

Alternative 1.0 title

Disposition Recommendation:  (Select one)

AGREE    AGREE WITH MODIFICATIONS    FURTHER STUDY NEEDED    DISAGREE

Explain, comment, and/or discuss rationale for disposition recommendation:

________________________

VA ALTERNATIVE 2.1

Alternative 2.1 title

Disposition Recommendation:  (Select one)

AGREE    AGREE WITH MODIFICATIONS    FURTHER STUDY NEEDED    DISAGREE

Explain, comment, and/or discuss rationale for disposition recommendation:

________________________

VA ALTERNATIVE 2.2

Alternative 2.2 title

Disposition Recommendation:  (Select one)

AGREE    AGREE WITH MODIFICATIONS    FURTHER STUDY NEEDED    DISAGREE

Explain, comment, and/or discuss rationale for disposition recommendation:

TABLE OF CONTENTS	PRELIMINARY

| VA STUDY SUMMARY REPORT X Project Summary Project Purpose and Need VA Study Timing VA Study Objectives Key Project Issues Evaluation of Baseline Concept - Performance Attributes VA Alternatives VA Strategies VA Study Results VA Team VA ALTERNATIVES X VA Strategy VA Alternative Summary Tables - VA Alternatives - VA Strategies Other Considerations Summary of Performance Improvements - Proposed VA Alternative Documentation PROJECT INFORMATION X Background Project Description Project Design Exceptions Information Provided to the VA Team Project Drawings Project Cost Estimate PROJECT ANALYSIS X Summary of Analysis Key Project Factors - Project Issues - Site Visit Observations Cost Model Function Analysis - Random Function Determination - FAST Diagram | PROJECT ANALYSIS (continued) Value Metrics - Define Performance Requirements - Define Performance Attributes and Scales - Prioritize Performance Attributes - Measure Performance of Baseline Concept - Measure Performance of Design Options - Measure Performance of VA Alternatives - Define VA Strategies - Compare Performance – Baseline Concept and VA Strategies - Rating Rationale for VA Strategies - Compare Value - Value Matrix – Baseline Concept and VA Strategies Risk Analysis - Qualitative Risk Analysis - Risk Tornado Diagrams - Risk Bubble Diagrams - Risk Registers - Risk Management Plan IDEA EVALUATION X Performance Attributes Evaluation Process Idea Summary Idea Summary List Detailed Idea Evaluation Summary VALUE ANALYSIS PROCESS X Pre-Study VA Study VA Report Caltrans VA Study Activity Chart VA Study Agenda VA Study Meeting Attendees |
| --- | --- |

| VA Study Summary Report – Preliminary Findings District #, Project Title (include county[s] if needed for route location) | PN 100000000 D#-County-Route(s) PM 1.0/2.9 |
| --- | --- |

Include an image representative of the project.

This could be a photograph of the project area taken during the site visit or 
an aerial photograph identifying the project limits.

Summarize the VA study logistics. Include the sponsoring District # – or in the case of a locally funded project, the local agency – the facilitating consultant. Also include the month the VA study was conducted and location of the study.

PROJECT SUMMARY

Provide a brief (one- or two-paragraph) summary of the project – both how/why it was initiated and a description of the project.

Total project costs for all elements of the project are currently estimated at $XX,000,000.

PROJECT PURPOSE AND NEED

Describe the purpose and need of the project.  This section should explain what is precipitating the need for this project (higher-order function) and how the project is addressing this need (basic function).

VA STUDY TIMING

Identify the timing of the VA study relative to the current milestone, and milestone dates. Also, add the RTL date.

VA STUDY OBJECTIVES

Enter the specific objectives that the value study should meet. Typically, there is more than one objective.

KEY PROJECT ISSUES

List the key drivers, constraints, or issues being addressed by the project and considered during the VA study to identify possible improvements. Project Issues can be grouped into several categories. These include, but are not limited to:

  - Stakeholder Issues identified during the Pre-Study or Kick-Off meetings. The question posed to stakeholders is:  “What are your concerns regarding this project? What are the challenges you see? What are your primary objectives?” Record what they say with as little filtering as possible.

  - Value Team Issues – After the Kick-Off meeting, you may want to ask the value team members what are the issues that they see concerning the project. Try and capture observations here – often these can also be collected under Site Visit Observations, but there is not always a site visit included in a study.

This list should be pared down to the only key project issues.  Otherwise, this ceases to be a “summary.”

Performance Attributes

Identify (in list form) the performance attributes utilized to analyze the baseline concept (Typically, there are 4 to 7 key attributes identified for a project.)

EVALUATION OF BASELINE CONCEPT

Discuss how well the baseline concept supported the project need and purpose. Also discuss how the concept satisfied the project requirements, how well the concept performed in terms of the attributes critical to this project, and identify risks associated with current design concept.

A major component of the analysis of the baseline concept is Value Metrics, which seeks to assess the elements of cost, performance, time, and risk as they relate to project value. The key performance attributes identified for the project should be listed in the table to the right and developed thoroughly in later sections of this report.

This text is intended to discuss and summarize the key conclusions and observations made by the VA team during the course of its analysis of the project.  What did we learn?  What led us to the alternatives that were developed?

VA ALTERNATIVES

Describe the number of VA alternatives developed by the VA team, and, if pertinent, the number of Design Suggestions generated by the VA team.  Summarize each VA alternative in a tabular format (Reference below), then give a brief synopsis of the alternative concept and its benefits. Do not discuss Design Suggestions here as these will be discussed in the next section of the report.

| Alternative No. and Description | Initial Cost Savings | LCC Savings | Change in Schedule | Change in Performance |
| --- | --- | --- | --- | --- |

| 1.0 Alternative title | $X,000,000 | $X,000,000 | # months | +/- % |
| --- | --- | --- | --- | --- |

(In tabular format, list the number of the alternative, title, and summary of initial and LCC cost savings, change in schedule, and change in performance. If LCC analysis was indeed performed and the result is $0 savings, then use $0. If no analysis was performed, use dashes (---).  Change in schedule is recorded in terms of increases (+) or reductions (-) to the baseline schedule, just as change in performance or value would be presented.)

A single paragraph should be developed that briefly explains the essence of the concept and the potential benefits. Include an image, sketch, or drawing if this will better convey the proposed alternative. This paragraph should be a refined version of the Discussion from the VA Alternative.

| 2.1 Alternative title | $X,000,000 | $X,000,000 | # months | +/- % |
| --- | --- | --- | --- | --- |

(Summarize each VA alternative in a tabular format as shown above. List the number of the alternative, title, and summary of initial and LCC cost savings, change in schedule, and change in performance. If LCC analysis was indeed performed and the result is $0 savings, then use $0. If no analysis was performed, use dashes (---).  Change in schedule is recorded in terms of increases (+) or reductions (-) to the baseline schedule, just as change in performance or value would be presented.)

A single paragraph should be developed that briefly explains the essence of the concept and the potential benefits. Include an image, sketch, or drawing if this will better convey the proposed alternative.

| 2.2 Alternative title | $X,000,000 | $X,000,000 | # months | +/- % |
| --- | --- | --- | --- | --- |

(Summarize each VA alternative in a tabular format as shown above. List the number of the alternative, title, and summary of initial and LCC cost savings, change in schedule, and change in performance. If LCC analysis was indeed performed and the result is $0 savings, then use $0. If no analysis was performed, use dashes (---).  Change in schedule is recorded in terms of increases (+) or reductions (-) to the baseline schedule, just as change in performance or value would be presented.)

A single paragraph should be developed that briefly explains the essence of the concept and the potential benefits. Include an image, sketch, or drawing if this will better convey the proposed alternative.

VA STUDY RESULTS

Provide an explanation of what key alternatives and strategies were developed and what their potential benefits mean for the project. The information here must clearly and concisely describe in words what the summary tables and charts mean. For example, if a proposed strategy is decreasing performance and accelerating the schedule, explain why.

IMPORTANT: If there is more than one VA Strategy, one strategy must be identified as the “VA Team Recommended Strategy.”  When doing so, you must discuss why this strategy was recommended. You must also discuss why other strategies were developed but not recommended.

Comparison of Value - Baseline Concept and VA Strategies

Prepare a bar chart that shows the performance scores, cost/time scores, and change in value of the VA strategies as compared to the baseline concept and any additional design concepts that were developed prior to the VA study by the Project Team.

Summary of VA Strategies

Insert a table summarizing the VA strategies. This table should include the initial cost and life-cycle cost savings and changes in schedule, performance, and value. Give the VA strategy a title which very briefly describes its features and/or benefits. If there is more than one VA strategy, indicate which is the “VA Team Recommended Strategy” in this table.

| Strategy Description | Initial Cost Savings | LCC Savings | Change in Schedule | Change in Performance | Value Change |
| --- | --- | --- | --- | --- | --- |
| VA Strategy 1: Strategy Title Alternative Nos. X, Y, Z | $X,000,000 | $X,000,000 | # months | +/- % | +/- % |
| Recommended VA Strategy VA Strategy 2: Strategy Title Alternative Nos. X, Y | $X,000,000 | $X,000,000 | # months | +/- % | +/- % |
| VA Strategy 3: Strategy Title Alternative Nos. Y, Z | $X,000,000 | $X,000,000 | # months | +/- % | +/- % |

Note:  Because the cost data depicted above represent savings, a number in parentheses represents a cost increase.

VA TEAM

Identify the study participants including the VA study team members and key contacts such as the DVAC, Project Manager, and other key stakeholders as required who played a role in supporting the study.

Always list the DVAC under Key Contacts, even if he or she did not have the opportunity to attend the VA study. (This also applies to locally funded projects.) In the list of Key Project Contacts, only list those individuals that have decision-making authority.

VA Study Team

| Name | Organization | Title |
| --- | --- | --- |
| Name | XYZ Value Analysis Consultant | VE Team Leader |
| Name | Organization | Title |
| Name | Organization | Title |
| Name | Organization | Title |
| Name | Organization | Title |

Key Project Contacts

| Name | Organization | Title |
| --- | --- | --- |
| Name | Organization | Title |
| Name | Organization | Title |
| Name | Caltrans | District/Region VA Coordinator |

# VA ALTERNATIVES	preliminary

Introductory paragraph to define what a VA alternative is as compared to the baseline concept and what each alternative form to follow will entail: a summary of the baseline concept, a description of the suggested change, a listing of its advantages and disadvantages, a cost comparison, change in performance and value, discussion of schedule and risk impacts (if applicable), and a brief narrative comparing the baseline design with the alternative. The cost comparisons reflect a comparable level of detail as in the baseline estimate.  A life cycle cost (LCC) analysis is included where appropriate.

VA STRATEGIES

The VA team develops a VA strategy(s) (combination of VA alternatives) that represents their opinion of the best combination of alternatives for the project to assist the decision makers in their evaluation of the VA alternatives.  The VA strategy is based on factors that include improved performance, likelihood of implementation, least community impact, cost savings, or any combination of project’s performance attributes.  This information is a guide and is not intended to reject the other alternatives from project stakeholder consideration.  The rationale for not including some alternatives in the recommended VA strategy, if applicable, should be discussed in the previous section: VA Study Summary Report – Preliminary Findings.

VA ALTERNATIVE SUMMARY TABLES

In tabular format, list the number of the alternative, title, and summary of initial and LCC cost savings, change in schedule, and change in performance. If LCC analysis was indeed performed and the result is $0 savings, then use $0. If no analysis was performed, use dashes (---).  Change in schedule is recorded in terms of increases (+) or reductions (-) to the baseline schedule, just as change in performance or value would be presented.

Summary of VA Alternatives

| Alternative No. & Description | Initial Cost Savings | LCC Savings | Change in Schedule | Performance Change | Value Change |
| --- | --- | --- | --- | --- | --- |
| 1.0 Alternative title | $X,000,000 | $X,000,000 | # months | +/- % | +/- % |
| 2.1 Alternative title | $X,000,000 | $X,000,000 | # months | +/- % | +/- % |
| 2.2 Alternative title | $X,000,000 | $X,000,000 | # months | +/- % | +/- % |

Note:  Because the cost data depicted above represent savings, a number in parentheses represents a cost increase.

Summary of VA Strategies

Insert a table summarizing the VA strategies. This table should include the initial cost and life-cycle cost savings and changes in schedule, performance, and value. Give the VA strategy a title which very briefly describes its features and/or benefits. If there is more than one VA strategy, indicate which is the “VA Team Recommended Strategy” in this table.

| Strategy Description | Initial Cost Savings | LCC Savings | Change in Schedule | Change in Performance | Value Change |
| --- | --- | --- | --- | --- | --- |
| VA Strategy 1: Strategy Title Alternative Nos. X, Y, Z | $X,000,000 | $X,000,000 | # months | +/- % | +/- % |
| Recommended VA Strategy VA Strategy 2: Strategy Title Alternative Nos. X, Y, Z | $X,000,000 | $X,000,000 | # months | +/- % | +/- % |
| VA Strategy 3: Strategy Title Alternative Nos. X, Y, Z | $X,000,000 | $X,000,000 | # months | +/- % | +/- % |

Note:  Because the cost data depicted above represent savings, a number in parentheses represents a cost increase.

OTHER CONSIDERATIONS

Identify and describe in as much detail as possible the Other Considerations (sometimes referred to as Design Suggestions) generated by the VA team for consideration by the Project Team.

IMPORTANT: Other Considerations are NOT VA alternatives that simply lack either quantifiable cost data and/or adequate time to perform a cost analysis/comparison. Nor are they VA alternatives that offer $0 cost savings upon analyzing cost data. Other Considerations are general in nature.

- Idea No. 1  Design Suggestion

Description of design suggestion.

- Idea No. 2  Design Suggestion

Description of design suggestion.

- Idea No. 3  Design Suggestion

Description of design suggestion.

- Idea No. 4  Design Suggestion

Description of design suggestion.

Summary of Performance Improvements

This table is used by Caltrans HQ for internal measurement and monitoring of their VA Program and for reporting performance statistics to FHWA. Identify if each alternative improved one or more of the performance areas identified in this chart. The same performance areas are used for all Caltrans VA studies, regardless of their applicability. If the alternative did not impact a performance area or reduced it, leave it blank. If it was improved, than enter “Improved” as appropriate.  Only the six standard Caltrans performance attributes shown in the table below are to be documented. Caltrans does not require reporting of the performance of any other attributes utilized in this study.

This should appear on its own page.

Summary of Proposed VA Alternative Performance Improvements

| Alt. No. | Mainline Operations | Local Operations | Maintainability | Environmental Impacts | Construction Impacts | Project Schedule |
| --- | --- | --- | --- | --- | --- | --- |
| 1.0 | Improved | Improved | Improved | Improved | Improved | Improved |
| 2.1 | Improved | Improved | Improved | Improved | Improved | Improved |
| 2.2 | Improved | Improved | Improved | Improved | Improved | Improved |

| The title is an abridged description of the concept. Do not use this area to describe the reason(s) for the alternative. Initial Cost Savings: | Numbering Conventions: VA Alternatives that are not mutually exclusive should be numbered as follows: X.0, Y.0, Z.0, and so on. Mutually exclusive VA Alternatives should be numbered as follows: X.1, X.2, X.3, and so on. Calculate |
| --- | --- |
| LCC Savings: | Calculate |
| Change in Schedule: | Calculate |
| Performance Change: | Calculate |
| Value Change: | Calculate |

Description of Baseline Concept:  What is currently planned? Describe the project element(s) as presented in the Kick-Off Meeting and available drawings and cost estimates. Be as descriptive and specific as possible, but only include those elements that are relevant to the alternative concept being proposed below.

Description of Alternative Concept:  What is the change(s) proposed by the VA Study Team? Describe the proposed change(s) to the baseline concept described above. Be as descriptive and specific as possible, but do not discuss the rationale for the change or its benefits.

Advantages: Why is the Alternative Concept better?

- Benefits (“Pros”) of implementing the Alternative Concept

- Use concise statements (one per line), not full sentences

Disadvantages: What challenges or disadvantages does the Alternative Concept introduce?

- Detriments (“Cons”) of implementing the Alternative Concept

- Use concise statements (one per line), not full sentences

Discussion:  Describe IN DETAIL why the Alternative Concept should be implemented. Provide an in-depth narrative about the Baseline and Alternative Concepts and thorough analysis of the Alternative’s advantages and disadvantages, etc.  For instance, if you listed “Reduces required retaining wall maintenance” in the Advantages above, it is critical to expand on this comment and describe why and how in this section. The Discussion section is intended to PROVE to project stakeholders, owners, and Project Team that this alternative should be implemented.

Technical Review Comments:  Highlight issues/concerns for the Project Team or technical personnel considerations. If there is a Technical Review session during the VA Study, use this space to relate the comments of the reviewers as to the technical feasibility of the Alternative Concept. It is acceptable to paraphrase reviewer comments, and it is not necessary to identify the commenter.

Project Management Considerations:  What will the PM have to do to implement this alternate concept? Also, how are the PM’s continuing responsibilities affected by implementing this alternative?

Discussion of Schedule Impacts:  Describe how implementing the Alternative Concept will impact the project schedule. Be specific as to the phases, activities, etc., to be impacted. While you are welcome to provide exact durations for every potential impact, it is not always possible. Therefore, if necessary, estimate lengths of time based on your best judgment and expertise.

Discussion of Risk Impacts:  Describe how the Alternative Concept will address existing risks and/or opportunities, as well as any new risks/opportunities introduced by implementing this Alternative. It is possible for an alternative to simultaneously address an existing risk and introduce a new one. In this case, discuss the trade-offs and demonstrate why it is still good practice to implement the Alternative Concept.

Comparison of Performance

Using the identified performance attributes, include a chart that depicts the differences in performance ratings between the Baseline Concept and the Alternative Concept.

Be sure that the ratings are aligned with the performance weighting scales defined prior to 
the study and presented in the Project Analysis section of the report.

Performance Assessment

Include a table discussing the rationale for the Alternative Concept’s performance ratings shown 
in the chart above. Describe any improvements or degradations in performance to the Baseline Concept that would be created by implementing the VA Alternative.

| Performance Attribute | Rationale for Change in Performance |
| --- | --- |
| Performance Attribute 1 | How will the alternative impact each of the various performance attributes? Is performance better or worse? Explain why. At times, this information is captured from discussions during group Idea Evaluation; elaborate on this information. |
| Performance Attribute 2 | Is performance better or worse? Explain why. |
| Performance Attribute 3 | Is performance better or worse? Explain why. |
| Performance Attribute 4 | Is performance better or worse? Explain why. |

Baseline Concept Sketch

Provide a visual depiction of the Baseline Concept. This could include plans/drawings, hand-drawn sketches, photos, or figures. Scale and precision are not required, though it is encouraged if it is available. Please limit the area to that which is relevant to the Alternative Concept. Make sure this is legible, and reproducible .

VA Alternative Concept Sketch

Provide a visual depiction of the Alternative Concept. This could include marked-up plans/drawings, hand-drawn sketches, photos, or figures. Scale and precision are not required, though it is encouraged if it is available. Make sure this is legible, reproducible and annotated or highlighted to clearly communicate the change.

Assumptions and Calculations:  What was assumed in order to develop the cost impact of this VA alternative? Provide assumed quantities, unit costs, calculations (to show unit costs or quantities), and/or activities that must be (or must not be) performed. This enables development alternative and the cost estimate/comparison, as shown on the “Initial Cost Estimate” on the following page.

Initial Cost Estimates

Calculate initial cost savings estimates using order-of-magnitude comparisons.

Life-Cycle Cost Estimates

Perform a life-cycle cost analysis if the relevant information is available and there is a high likelihood that life-cycle cost savings can be realized by implementing the VA Alternative.

# PROJECT INFORMATION

BACKGROUND

The project background is intended to summarize the events, circumstances, and conditions leading to the initiation of the project.

PROJECT DESCRIPTION

The project background is intended to summarize the events, circumstances, and conditions leading to the initiation of the project.

PROJECT DESIGN EXCEPTIONS

Caltrans requires the listing of all known project design exceptions at the time of the VA study. If there were none, enter “None” in either or both of the categories – but do not delete this section.

Mandatory Design Exceptions

- None.

Advisory Design Exceptions

- None.

INFORMATION PROVIDED TO THE VA TEAM

Identify all project documents that were made available during the VA study. Make sure all the documents are dated. If no date is available, write “undated.” The information presented in this section of the report may be excerpted either in part or in full from the documents/information provided to the VA team listed above, but this should be disclaimed.

PROJECT DRAWINGS

Provide key drawings that explain the design used as the baseline during the VA study.

PROJECT COST ESTIMATE

Provide at the end of this section the entire cost estimate used as the baseline during the VA study.

# PROJECT ANALYSIS

SUMMARY OF ANALYSIS

The following analysis tools were used to study the project:

- Key Project Factors

- Cost Model

- Function Analysis

- Value Metrics

- Risk Analysis

KEY PROJECT FACTORS

The first day of the VA study typically includes meetings with the project stakeholders and a site visit.  Summarizes below the key project issues and site visit observations identified during these sessions.

Project Issues (Stakeholders)

- Project Issue

- Project Issue

- Project Issue

VA Team Project Issues and/or Site Visit Observations

Identify the VA Team’s observations and remarks related to the project and site visit.

Site Visit Observation

- Site Visit Observation

- Site Visit Observation

COST MODEL

Prepare a cost model from the cost estimate presented in the Project Information section of the report, which organizes major construction elements or trade categories, the original estimated costs, and the percent of total project cost for the significant cost items to clearly show the cost drivers for the project and guide the VA team during the VA study.

Provide a discussion of what was learned and what assumptions were derived from the development of the cost model and analysis of the cost estimate.

Cost Model

Include any histograms or other related charts or analysis of the cost estimate.

FUNCTION ANALYSIS

Provide a discussion of what was learned during the process of function analysis.  Highlight any observations made concerning the FAST diagram here as well.

Include the Random Function Determination matrix developed for the project. Make sure that functions are concise verb+noun abridgments. It is standard to identify function cost, performance, and schedule/time relationships.

Random Function Determination

| Project Element | Function | Cost | Performance | Time | Risk |
| --- | --- | --- | --- | --- | --- |
| Project Element | Verb+Noun Function | $M | Perf | Time | Risk |
| Project Element | Verb+Noun Function | $M | Perf | Time | Risk |
| Project Element | Verb+Noun Function | $M | Perf | Time | Risk |

FAST Diagram

Include the dimensioned FAST Diagram of the project.

VALUE METRICS

Briefly, but generally, describe Value Metrics and its benefits. The steps of the Value Metrics process are listed below.

Define Performance Requirements

Identify the performance requirements for the project. The standard requirements are shown here. Be sure to include any additional performance requirements that are unique to the project.

| Performance Requirement | Definition |
| --- | --- |
| Highway Design Standards | Any deviation from the Caltrans Highway Design Manual must be approvable by the District’s Design Reviewer. |
| Structural Design Standards | Any structure on the project must comply with current seismic design standards and meet the Load Resistance Design Factor. |
| Environmental Review Process | Any concept or design modification considered must comply with state and federal environmental law and be compatible with the environmental review process. |
| Critical Project Milestones | List the critical schedule milestones must be met in order to meet legislative and/or funding requirements. If there are no specific milestones or dates, then ipso facto, this is not a requirement and should be omitted. |

Define Performance Attributes and Scales

Identify each performance attribute for the project, its definition in this context, and its related measurement scales. Every increment in an attribute’s rating scales is not required to be defined, though if information and time permits, it is encouraged. Sometimes ratings are very subjective. In all cases, define the ideal rating and lowest acceptable rating.

Below are the Caltrans standard attributes and their definitions and rating scale descriptions. Be advised that these scales are samples only. It is very possible that one project’s “Very Good” rating would be the equivalent of a “Fair” rating on another project, especially attributes involving Levels of Service (LOS). (For example, an LOS D in District 7 may be rated “Very Good” depending on the highway, whereas such an LOS would be considered “Poor” in District 1.) Therefore, customize these scales to fit the project.

Mainline Operations

An assessment of traffic operations and safety on the mainline facility(s), including off-ramps and collector-distributor roads. Operational considerations include level of service relative to the 20-year traffic projections, as well as geometric considerations such as design speed, sight distance, lane widths, and shoulder widths.

| Rating | Label | Description |
| --- | --- | --- |
| 0.0 | Unacceptable | Mainline operations equivalent to LOS F during peak hour. Very poor level of traffic operations. May require multiple design exceptions. |
| 2.0 | Poor | Mainline operations equivalent to LOS E during peak hour. Poor level of traffic operations. May require multiple design exceptions. |
| 4.0 | Fair | Mainline operations equivalent to LOS D during peak hour. Fair level of traffic operations. May require some design exceptions. |
| 6.0 | Good | Mainline operations equivalent to LOS C during peak hour. Good level of traffic operations. Meets all or most design standards. |
| 8.0 | Very Good | Mainline operations equivalent to LOS B during peak hour. High level of traffic operations. Meets all mandatory design standards. Meets all or most advisory design standards. |
| 10.0 | Excellent | Mainline operations equivalent to LOS A during peak hour. Highest level of traffic operations. Meets or exceeds all design standards. |

Local Operations

An assessment of traffic operations and safety on the local roadway infrastructure, including on-ramps and frontage roads. Operational considerations include level of service relative to the 20-year traffic projections; geometric considerations such as design speed, sight distance, and lane widths; bicycle and pedestrian operations and access.

| Rating | Label | Description |
| --- | --- | --- |
| 0.0 | Unacceptable | Local operations equivalent to LOS F during peak hour. Very poor level of traffic operations. Severely impacts existing local access. May require multiple design exceptions. |
| 2.0 | Poor | Local operations equivalent to LOS E during peak hour. Poor level of traffic operations. Significantly impacts existing local access. May require multiple design exceptions. |
| 4.0 | Fair | Local operations equivalent to LOS D during peak hour. Fair level of traffic operations. Somewhat impacts existing local access. May require some design exceptions. |
| 6.0 | Good | Local operations equivalent to LOS C during peak hour. Good level of traffic operations. Maintains existing local access. Meets all or most design standards. |
| 8.0 | Very Good | Local operations equivalent to LOS B during peak hour. High level of traffic operations. Maintains or improves existing local access. Meets all mandatory design standards. Meets all or most advisory design standards. |
| 10.0 | Excellent | Local operations equivalent to LOS A during peak hour. Highest level of traffic operations. Significantly maintains or improves upon existing local access. Meets or exceeds all design standards. |

Maintainability

An assessment of the long-term maintainability of the transportation facility(s). Maintenance considerations include the overall durability, longevity, and maintainability of pavements, structures, and systems; ease of maintenance; accessibility and safety considerations for maintenance personnel.

| Rating | Label | Description |
| --- | --- | --- |
| 0.0 | Unacceptable | The anticipated level of maintenance for the project will be extreme and unacceptably high. |
| 2.0 | Poor | The project is expected to require maintenance that far exceeds the norm for a facility of its kind. |
| 4.0 | Fair | The highway facility is expected to require greater than normal maintenance due to existing site conditions or materials selection. |
| 6.0 | Good | The project provides a satisfactory level of maintainability and is typical of a highway facility of this kind statewide. |
| 8.0 | Very Good | The project provides a high level of maintainability. The facility utilizes many low-maintenance features and is better than average in terms of expected maintenance. |
| 10.0 | Excellent | The project provides the highest possible level of maintainability and far exceeds expectations when compared to comparable facilities statewide. Examples are the use of long-life pavement, low-maintenance water quality facilities, low maintenance structures, etc. |

Environmental Impacts

An assessment of the permanent impacts to the environment, including ecological (i.e., flora, fauna, air quality, water quality, visual, noise); socioeconomic impacts (i.e., environmental justice); impacts to cultural, recreational, and historic resources. Also considered under this attribute are drainage and hydraulic issues.

| Rating | Label | Description |
| --- | --- | --- |
| 0.0 | Unacceptable | The environmental impacts are severe and the project does not comply with state and/or federal environmental laws. |
| 2.0 | Poor | The project introduces environmental impacts that are both significant in number and impact that require extensive mitigation. |
| 4.0 | Fair | The project introduces many new environmental impacts that will require extensive mitigation. |
| 6.0 | Good | The project introduces some new environmental impacts that can be addressed through standard and accepted mitigation approaches. |
| 8.0 | Very Good | The project introduces no new environmental impacts. |
| 10.0 | Excellent | The project improves upon the existing environmental conditions while introducing no new environmental impacts. |

Construction Impacts

An assessment of the temporary impacts to the public during construction related to traffic disruptions, detours, and delays; impacts to businesses and residents relative to access, visual, noise, vibration, dust, and construction traffic; environmental impacts related to water quality, air quality, soil erosion, and local flora and fauna.

| Rating | Label | Description |
| --- | --- | --- |
| 0.0 | Unacceptable | Temporary traffic and/or environmental impacts will be severe and create impacts that are unacceptable to the public. |
| 2.0 | Poor | Temporary traffic impacts will be extensive, lengthy, and very disruptive. Temporary environmental impacts will require extraordinary mitigation measures and create major inconveniences to the public. |
| 4.0 | Fair | Temporary traffic impacts will be significant and be much greater than what would normally be anticipated for similar projects. Temporary environmental impacts will be more significant in nature and require greater mitigation measures and/or inconveniences to the public. |
| 6.0 | Good | There will be some nighttime lane closures and/or temporary ramp closures. There will be some minor to moderate temporary environmental impacts. Impacts will be fairly “typical” for this type of project and can be handled through normal processes and procedures. |
| 8.0 | Very Good | There will be some minor temporary traffic and/or environmental impacts expected during construction. Impacts will be less than typical. |
| 10.0 | Excellent | There will be no temporary traffic or environmental impacts during construction. |

Prioritize Performance Attributes

Systematically prioritize the performance attributes to determine their relative importance in meeting the project’s need and purpose.  Compare them in pairs, asking the question:  “An improvement to which attribute will provide the greatest benefit relative to the project’s need and purpose?”

Performance Attribute Prioritization

Include a chart showing the relative priorities of the performance attributes

Measure Performance of Baseline Concept

Using the scales previously defined, provide a performance rating for each of the project’s selected performance attributes, then discuss the rationale for the given ratings of the baseline concept.

## Performance Attribute 1

## Rating:  10

Rationale:  Discuss the rationale for the given rating.

## Performance Attribute 2

## Rating:  10

Rationale:  Discuss the rationale for the given rating.

## Performance Attribute 3

## Rating:  10

Rationale:  Discuss the rationale for the given rating.

## Performance Attribute 4

## Rating:  10

Rationale:  Discuss the rationale for the given rating.

Measure Performance of Design Options

(If applicable) Using the scales previously defined, provide a performance rating for each of the project’s selected performance attributes, then discuss the rationale for the given ratings of the additional Design Options.

## Performance Attribute 1

## Rating:  10

Rationale:  Discuss the rationale for the given rating.

## Performance Attribute 2

## Rating:  10

Rationale:  Discuss the rationale for the given rating.

## Performance Attribute 3

## Rating:  10

Rationale:  Discuss the rationale for the given rating.

## Performance Attribute 4

## Rating:  10

Rationale:  Discuss the rationale for the given rating.

Measure Performance of VA Alternatives

The rationale for any change in performance as compared to the Baseline Concept was recorded.  Please refer to the individual performance assessments for each VA alternative as presented in the VA Alternatives section of this report.

Define VA Strategies

Summary of VA Strategies

Insert a table summarizing the VA strategies. This table should include the initial cost and life-cycle cost savings and changes in schedule, performance, and value. Give the VA strategy a title which very briefly describes its features and/or benefits. If there is more than one VA strategy, indicate which is the “VA Team Recommended Strategy” in this table.

| Strategy Description | Initial Cost Savings | LCC Savings | Change in Schedule | Change in Performance | Value Change |
| --- | --- | --- | --- | --- | --- |
| VA Strategy 1: Strategy Title Alternative Nos. X, Y, Z | $X,000,000 | $X,000,000 | # months | +/- % | +/- % |
| Recommended VA Strategy VA Strategy 2: Strategy Title Alternative Nos. X, Y | $X,000,000 | $X,000,000 | # months | +/- % | +/- % |
| VA Strategy 3: Strategy Title Alternative Nos. Y, Z | $X,000,000 | $X,000,000 | # months | +/- % | +/- % |

Note:  Because the cost data depicted above represent savings, a number in parentheses represents a cost increase.

Compare Performance –Baseline Concept and VA Strategies

Comparison of Performance

Include a chart comparing the performance scores for the Baseline Concept, 
any applicable Design Options, and all VA strategies.

Rating Rationale for VA Strategies

Using the scales previously defined, provide a performance rating for each of the project’s selected performance attributes, then discuss the rationale for the given ratings for each of the VA strategies. Be sure that the rating is aligned with the scales, and describe the differences between the VA strategy(s) and the baseline concept.

VA Strategy 1 – Give the VA strategy a title which very briefly describes its features and/or benefits

## Performance Attribute 1

## Rating:  10

Rationale:  Discuss the rationale for the given rating.

## Performance Attribute 2

## Rating:  10

Rationale:  Discuss the rationale for the given rating.

## Performance Attribute 3

## Rating:  10

Rationale:  Discuss the rationale for the given rating.

## Performance Attribute 4

## Rating:  10

Rationale:  Discuss the rationale for the given rating.

VA Strategy 2 – Give the VA strategy a title which very briefly describes its features and/or benefits

## Performance Attribute 1

## Rating:  10

Rationale:  Discuss the rationale for the given rating.

## Performance Attribute 2

## Rating:  10

Rationale:  Discuss the rationale for the given rating.

## Performance Attribute 3

## Rating:  10

Rationale:  Discuss the rationale for the given rating.

## Performance Attribute 4

## Rating:  10

Rationale:  Discuss the rationale for the given rating.

VA Strategy 3 – Give the VA strategy a title which very briefly describes its features and/or benefits

## Performance Attribute 1

## Rating:  10

Rationale:  Discuss the rationale for the given rating.

## Performance Attribute 2

## Rating:  10

Rationale:  Discuss the rationale for the given rating.

## Performance Attribute 3

## Rating:  10

Rationale:  Discuss the rationale for the given rating.

## Performance Attribute 4

## Rating:  10

Rationale:  Discuss the rationale for the given rating.

Compare Value

Identify the normalized cost scores for the Baseline Concept, any Design Options, and VA strategies.

| Strategies | Cost | Score |
| --- | --- | --- |
| Baseline Concept | $M | 0.200 |
| Design Option | $M | 0.200 |
| VA Strategy 1 | $M | 0.200 |
| VA Strategy 2 | $M | 0.200 |
| VA Strategy 3 | $M | 0.200 |
| TOTAL | $M | 1.000 |

Identify the normalized time scores for the Baseline Concept, any Design Options, and VA strategies.

| Strategies | Time | Score |
| --- | --- | --- |
| Baseline Concept | X months | 0.200 |
| Design Option | X months | 0.200 |
| VA Strategy 1 | X months | 0.200 |
| VA Strategy 2 | X months | 0.200 |
| VA Strategy 3 | X months | 0.200 |
| TOTAL | X months | 1.000 |

Identify the relative importance of the cost and time for the project, then provide the rationale for the cost-time prioritization/trade-off.

| Relative Importance |  |
| --- | --- |
| COST | 68.18 % |
| TIME | 31.82 % |

Next, synthesize a value index for the Baseline Concept, any Design Options, and each of the VA strategies.  This is achieved by applying the following algorithm for value:

| - V = Value | - P = Performance | - t = Time |
| --- | --- | --- |
| - f = Function | - C = Cost | - α = Risk |

Value Matrix
Baseline Concept and VA Strategies

Prepare a Value Matrix.  The performance scores for each strategy are divided by the 
total cost/time scores for each strategy to derive a value index.  The value indices for the VA strategies are then compared against the value index of the Baseline Concept and the difference 
is expressed as a percent (±%) deviation.

| Strategies | Performance Score | Change in Performance | Cost/Time Score | Net Change | Value Index | Change in Value |
| --- | --- | --- | --- | --- | --- | --- |
| Baseline Concept | 0.608 | --- | 0.253 | --- | 2.403 | --- |
| Design Option | 0.559 | -8% | 0.313 | +24% | 2.560 | +7% |
| VA Strategy 1 | 0.560 | -7% | 0.244 | -4% | 2.211 | -8% |
| VA Strategy 2 | 0.587 | -3% | 0.352 | +39% | 2.668 | +11% |
| VA Strategy 3 | 0.625 | +3% | 0.257 | +2% | 2.559 | +6% |

Comparison of Value - Baseline Concept and VA Strategies

Prepare a bar chart that shows the performance scores, cost/time scores, and change in value of the VA strategies as compared to the baseline concept and any additional design concepts that were developed prior to the VA study by the Project Team.

RISK ANALYSIS

Include a summary of the Risk Analysis, if performed, here.  Note the table below represents a minimum expectation for the Risk Analysis; if a more complex Risk Analysis was performed include the appropriate information.

Risk Identification List

Include a list of the risks identified as a result of the Risk Analysis, if applicable.

| ID | Type | Category | Name | Description | Probability | Impact |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Threat or Opportunity | Risk Category | Name | Description | Very High High Medium Low Very Low | Very High High Medium Low Very Low |
| 2 | Threat or Opportunity | Risk Category | Name | Description | Very High High Medium Low Very Low | Very High High Medium Low Very Low |

# Idea evaluation

PERFORMANCE ATTRIBUTES

Identify key performance attributes for this project used to assist the VA team in evaluating the ideas:

- Performance Attribute 1

- Performance Attribute 2

- Performance Attribute 3

- Performance Attribute 4

EVALUATION PROCESS

Briefly describe the evaluation process of the ideas generated during the Speculation Phase of the VA study.

IDEA SUMMARY

Include a legend to link the Idea Codes to the related functions used during brainstorming.

| Idea Code | Related Function |
| --- | --- |
| Idea Code | Related Function |
| Idea Code | Related Function |

Include a summary list of the ideas. This should be limited to the Idea Code, Idea Description, and the Rating of the idea. Organize the ideas by Idea Code in alphanumeric order.

Idea Summary List

| Idea Code and Description | Rating |
| --- | --- |
| Idea Code-1: Idea Description | 1 to 7, Or one of the abbreviations listed below |
| Idea Code-2: Idea Description | 1 to 7, Or one of the abbreviations listed below |
| Idea Code-3: Idea Description | 1 to 7, Or one of the abbreviations listed below |
| Idea Code-4: Idea Description | 1 to 7, Or one of the abbreviations listed below |
| Idea Code-5: Idea Description | 1 to 7, Or one of the abbreviations listed below |

DEV:  Develop [as a VA Alternative]

DS:  Design Suggestion

ABD:  Already Being Done [in the Baseline Concept]

DIS:  Dismissed

DETAILED IDEA EVALUATION SUMMARY

Include a detailed idea evaluation summary, which includes additional information related to how each idea improves or degrades the elements of performance, cost, time (schedule), and risk.  Only include those elements where the idea differs from the baseline concept.

| Idea Code-1: Idea Description Overall Rating: 5 |  |  |
| --- | --- | --- |
| Attributes | Rating | Comments |
| Performance Attribute 1 | Improved Degraded Unchanged | Comment |
| General comments: Insert any other general comments. |  |  |

| Idea Code-2: Idea Description |  |  | Overall Rating: 5 |
| --- | --- | --- | --- |
| Attributes | Rating | Comments |  |
| Performance Attribute 1 | Improved Degraded Unchanged | Comment |  |
| General comments: Insert any other general comments. |  |  |  |

| Idea Code-3: Idea Description |  |  | Overall Rating: 5 |
| --- | --- | --- | --- |
| Attributes | Rating | Comments |  |
| Performance Attribute 1 | Improved Degraded Unchanged | Comment |  |
| General comments: Insert any other general comments. |  |  |  |

| Idea Code-4: Idea Description |  |  | Overall Rating: 5 |
| --- | --- | --- | --- |
| Attributes | Rating | Comments |  |
| Performance Attribute 1 | Improved Degraded Unchanged | Comment |  |
| General comments: Insert any other general comments. |  |  |  |

| Idea Code-5: Idea Description |  |  | Overall Rating: 5 |
| --- | --- | --- | --- |
| Attributes | Rating | Comments |  |
| Performance Attribute 1 | Improved Degraded Unchanged | Comment |  |
| General comments: Insert any other general comments. |  |  |  |

Use this standard description of the 
Caltrans VA Process.

VALUE ANALYSIS PROCESS

The Caltrans VA process involves 16 activities needed to accomplish a VA study, organized in three parts:  Pre-study, VA Study, and Report.  Integral to Caltrans’ VA process is the Value Metrics process.  Value Metrics offers the cornerstone of the Caltrans VA process by providing a systematic and structured means of considering the relationship of a project’s performance and cost as they relate to value.

Value Analysis has traditionally been perceived as an effective means for reducing project costs.  This paradigm only addresses one part of the value equation, oftentimes at the expense of the role that VA can play with regard to improving project performance.  Project costs are fairly easy to quantify and compare; performance is not.

Project performance must be properly defined and concurred by the stakeholders at the beginning of the VA study.  The performance attributes and requirements developed are then used throughout the study to identify, evaluate, and document alternatives.  This process, Value Metrics, emphasizes the interrelationship between cost and performance and can be quantified and compared in terms of how they contribute to overall value.

Value Metrics provides a standardized means of identifying, defining, evaluating, and measuring performance.  Once this has been achieved, and costs for all VA alternatives have been developed, measuring value is straightforward.

Value Metrics can improve VA studies by:

- Building consensus among project stakeholders (especially those holding conflicting views)

- Developing a better understanding of a project’s goals and objectives as they relate to purpose and need

- Developing a baseline understanding of how the project is meeting performance goals and objectives

- Identifying areas where project performance can be improved through the VA process

- Developing a better understanding of an alternative concept’s effect on project performance

- Developing a deeper understanding of the relationship between performance and cost in determining value

- Using value as the basis for selecting the best project or design concept

The following provides an overview of the Caltrans approach to VA.  The Caltrans VA Study Activity Chart at the end of this narrative identifies the steps in each activity, which are detailed as follows.

PRE-STUDY

Meaningful and measurable results are directly related to the pre-study work performed.  Depending on the type of study, all or part of the following information needs to be determined during the pre-study phase:

- Clear definition of the current situation and study objectives

- Identification of study team members

- Identification of project stakeholders

- Definition of how stakeholders are impacted by the project

- Identification of key issues and concerns

- Identification of project’s performance requirements and attributes

- Status of project cost estimate

- Project data gathered to be distributed to VA team

In preparation for the VA study, the team leader confers with owners and stakeholders to outline the VA process, initiate data gathering, refine project scope and objectives, structure the scope and team members and technical specialists, and finalize study plans.  Specific deliverables are provided.

Following the initial planning meeting, the team leader reviews the data collected for the project and develops a cost model.  The team leader also consults with the technical specialists to prepare them for the VA study.

VA STUDY

The VA Job Plan guides the VA team in their search to enhance value in the project or process.  Caltrans follows a seven-phase VA Job Plan:

1.	Information Phase

2.	Function Phase

3.	Speculation Phase

4.	Evaluation Phase

5.	Development Phase

6.	Presentation Phase

7.	Implementation Phase

Information Phase

At the beginning of the VA study, the design team presents a more detailed review of the design and the various systems.  This includes an overview of the project and its various requirements, which further enhances the VA team's knowledge and understanding of the project.  The project team also responds to questions posed by the VA team.

The project’s performance requirements and attributes are discussed, and the performance of the baseline concept is evaluated.

Function Phase

Key to the VA process is the function analysis techniques used during the Function Phase.  Analyzing the functional requirements of a project is essential to assuring an owner that the project has been designed to meet the stated criteria and its need and purpose.  The analysis of these functions in terms cost, performance, time, and risk is a primary element in a VA study, and is used to develop alternatives.  This procedure is beneficial to the VA team, as it forces the participants to think in terms of functions and their relative value in meeting the project’s need and purpose.  This facilitates a deeper understanding of the project.

Speculation Phase

The Speculation Phase involves identifying and listing creative ideas.  During this phase, the VA team participates in a brainstorming session to identify as many means as possible to provide the necessary project functions.  Judgment of the ideas is not permitted in order to generate a broad range of ideas.

The idea list includes all of the ideas suggested during the study.  These ideas should be reviewed further by the project team, since they may contain ideas that are worthy of further evaluation and may be used as the design develops.  These ideas could also help stimulate additional ideas by others.

Evaluation Phase

The purpose of the Evaluation Phase is to systematically assess the potential impacts of ideas generated during the Speculation Phase relative to their potential for value improvement.  Each idea is evaluated in terms of its potential impact to performance, cost, time, and risk.  Once each idea is fully evaluated, it is given a total rating number.  This is based on a scale of 1 to 7, as indicated by the following rating index:

| 7 = Major Value Improvement | These ratings represent the subjective opinion of the VA team regarding the potential benefits of the concepts in order to prioritize them for development. |
| --- | --- |
| 6 = Moderate Value Improvement |  |
| 5 = Minor Value Improvement |  |
| 4 = Possible Value Improvement |  |
| 3 = Minor Value Degradation | Concept results in a minor cost or performance improvement at the expense of the other. |
| 2 = Moderate Value Degradation | Concept reduces cost but creates an unacceptable degradation to performance. |
| 1 = Major Value Degradation | Concept is not technically feasible or does not meet project need and purpose. |

Ideas rated 4 to 7 are developed further and those found to have the greatest potential for value improvement are documented in the VA Alternatives section of this report.  A more refined definition of what a 4-7 rating is (Major Value Improvement, etc.) will be developed by the team leader and team for each study. The rationale for why ideas were rated highly but not developed as alternatives is documented in the Idea Evaluation section of the report.

Development Phase

During the Development Phase, the highly rated ideas are expanded and developed into VA alternatives.  The development process considers the impact to performance, cost, time, and risk of the alternative concepts relative to the baseline concept.  This analysis is prepared as appropriate for each alternative, and the information may include a performance assessment, initial cost and life-cycle cost comparisons, schedule analysis, and an assessment of risk.  Each alternative describes the baseline concept and proposed changes and includes a technical discussion.  Sketches and calculations are also prepared for each alternative as appropriate.

Presentation Phase

The VA study concludes with a preliminary presentation of the VA team’s assessment of the project and VA alternatives.  The presentation provides an opportunity for the owner, project team, and stakeholders to preview the alternatives and develop an understanding of the rationale behind them.

Implementation Phase

After the stakeholders have had an opportunity to review the alternatives identified by the VA team, the team leader conducts an implementation meeting to discuss the alternatives and resolve appropriate action for each VA alternative.  If necessary, any other VA report edits requested by the representatives are also made by the VA team leader and a final report is issued.

This implementation meeting helps to ensure that savings or process improvements are not lost due to lack of communication, and that those VA alternatives that are accepted are properly integrated into the project design.

VA REPORT

Preliminary Report

Following the completion of the VA study, the team leader compiles the information developed during the VA study into the Preliminary Value Analysis Study Report.  This report, documenting viable alternatives, is provided to the customer within the timeframe requested (usually within two weeks).  The preliminary report also contains a VA Study Summary Report – Preliminary Findings, designed to highlight critical elements of the VA study, including detailed documentation of VA alternatives, in a concise manner for the use of parties without the opportunity to review the report in its entirety.  More details can be found in the complete preliminary report, which consists of the following documentation:  Executive Summary, VA Alternatives, Project Information, Project Analysis, Idea Evaluation, and VA Process.

Written Report – VA Implementation Action Memo

If the disposition of all VA alternatives cannot be determined at the Implementation Meeting, then a VA Implementation Action Memo is submitted.  This memo states which alternatives are accepted, which are rejected and the rationale for rejection, and which VA alternatives are conditionally accepted with further study required.  For these alternatives, the memo states what action must be completed so that a decision can be made as to the disposition of this VA alternative, when that action is expected to be completed, and who is responsible to complete this action.  If all VA alternatives are either accepted or rejected then this memo is not required.

Written Report – Final Report

Once all VA alternatives have been either accepted or rejected, the team leader updates the Preliminary Value Analysis Study Report to show the final results of the study in a Final Value Analysis Study Report.  In addition, a Value Analysis Study Summary Report (VASSR) is sent to Caltrans HQ to permit easy documentation into the Caltrans Annual Report to FHWA.

The following Caltrans VA Study Activity Chart describes each activity.

CALTRANS VA STUDY ACTIVITY CHART

| PREPARATION |  |  |  | INITIATE STUDY - Identify study project - Identify study roles and responsibilities - Define study goals - Select team leader - Prepare draft Study Charter 1 | ORGANIZE STUDY - Conduct Pre-Study Meeting - Select team members - Identify stakeholders, decision-makers, and technical reviewers - Identify data collection - Select study dates - Determine study logistics - Update VA Study Charter - Identify and define performance requirements 2 | PREPARE DATA - Collect and distribute data - Develop construction cost models - Develop highway user benefit / life cycle cost (LCC) model (if required) Insert the Caltrans VA Study Activity Chart. 3 |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| VA STUDY |  | Segment 1 |  | INFORM TEAM - Review study activities and confirm reviewers - Present design concept - Present stakeholders’ interests - Review project issues and objectives - Rate performance of baseline concept - Visit project site 4 | ANALYZE FUNCTIONS - Analyze project data - Expand project functions - Prepare FAST diagram - Determine functional cost drivers and performance 5 | CREATE IDEAS - Focus on functions - List all ideas - Apply creativity and innovation techniques (group and individual) 6 | EVALUATE IDEAS - Apply key performance attributes to rate idea - List advantages and disadvantages - Consider cost impacts - Rank all ideas - Assign alternatives for development 7 |
|  |  | Segment 2 |  | DEVELOP ALTERNATIVES - Develop alternative concepts - Prepare sketches and calculations - Measure performance - Estimate costs, LCC benefits/costs 8 | CRITIQUE ALTERNATIVES - VA Alternatives Technical Review - VA Alternatives Team Consensus Review - Identify mutually exclusive groups of alternatives - Identify VA strategies - Validate performance 9 | PRESENT ALTERNATIVES* - Present findings - Document feedback - Confirm pending reviews - Prepare preliminary report *Interim presentation of study findings 10 |  |
|  |  | Segment 3 |  | ASSESS ALTERNATIVES** - Review Preliminary Report - Assess alternatives for project acceptance - Prepare draft implementation dispositions **Activities performed by PDT, Technical Reviewers, and Stakeholders 11 | RESOLVE ALTERNATIVES - Review implementation dispositions - Resolve implementation actions with decision-makers and stakeholders - Edit alternatives - Revisit rejected alternatives, if needed 12 | PRESENT RESULTS* - Present results - Obtain management approval on implemented alternatives - Summarize performance, cost, and value improvements *Final presentation of study results 13 |  |
| REPORT |  |  |  | DOCUMENT STUDY - Document process and study findings - Distribute Preliminary VA Report - Distribute electronic report to HQ VA Branch - Conduct Implementation Meeting 14 | VA IMPLEMENTATION ACTION MEMO (If Conditionally Accepted Alternatives exist) - Publish memo to document action plan to complete study - Resolve Conditionally Accepted Alternatives 15 | PUBLISH RESULTS - Document process and study results - Incorporate all comments and implementation actions - Distribute Final VA Report - Distribute electronic report to HQ VA Branch - Update VA Study Summary Report (VASSR) - Provide HQ the Final VA Report in PDF format 16 | Note: The dashed boxes indicate steps that may not be required in some VA Studies. |

Standard 5-day VA Study Agenda

## District # – EA# XXXXX: Project Title

City(or County)

### Day 1 – Day of the week, Month, Day, Meeting Location

Kick-Off Meeting

8:00	VA Team Set-up

8:15	Introductions (All) and VA Agenda Review (VA Team Leader)

8:20	Project Overview (Project Manager and Engineers)

8:45	Stakeholder Issues and Concerns

9:00	Performance Attributes and Requirements and Analysis of Design Alternatives

9:30	Review projects risks

Conclusion of Kick-Off Meeting

10:00	Break

10:15	Site Visit

12:15	Lunch

1:15	Recap Site Visit, and Review Project Information and Cost Estimate

2:00	Function Analysis/Fast Diagram

2:30	Break

2:45	Cost/Function and Performance/Function Analysis

3:30	Team Brainstorming

### Day 2 – Day of the week, Month, Day, Meeting Location

8:00	Team Brainstorming (Cont)

10:15	Break

10:30	Evaluation of Ideas

12:00 	Lunch

1:00 	Evaluation of Ideas (Cont), Team Assignments for Development

3:00 	Break

3:15 	Review Alternative Development Process

3:30	Research and Refine Ideas

### Day 3 – Day of the week, Month, Day, Meeting Location

8:00	Research and Refine Ideas (Cont)

10:15	Break

10:30	Research and Refine Ideas (Cont)

12:00	Lunch

1:00	Review of VA Alternatives (Technical Reviewers)

2:00	Alternative Development

3:00	Break

3:15	Alternative Development (Cont)

### Day 4 – Day of the week, Month, Day, Meeting Location

8:00	Alternative Development (Cont)

10:15	Break

10:30	Alternative Development (Cont)

12:00	Lunch

1:00	Complete Alternative Development

### Day 5 – Day of the week, Month, Day, Meeting Location

8:00	Group Review and Ranking of VA Alternatives/Strategy; Presentation Preparation

11:00	Finalize Alternatives and Prepare Presentation

12:00	Lunch

11:00	Finalize Alternatives and Prepare Presentation

2:00	Presentation of VA Alternatives Meeting (Presentation of VA Study Results to Management and Stakeholders)

Standard 6-day VA Study Agenda

## District # – EA# XXXXX: Project Title

City(or County)

### Day 1 – Day of the week, Month, Day, Meeting Location

Kick-Off Meeting

8:00	VA Team Set-up

8:15	Introductions (All) and VA Agenda Review (VA Team Leader)

8:30	Project Overview (Project Manager and Engineers)

9:15	Stakeholder Issues and Concerns

9:30	Break

9:45	Performance Attributes and Requirements and Analysis of Design Alternatives

10:30	Qualitative risk analysis

11:00	Conclusion of Kick-Off Meeting

11:00	Team Review of Review Project Information, Cost Estimate, Cost Model, and Issues

11:30	Lunch

12:30	Site Visit

3:30	Recap Site Visit, and Identify Added Team Issues

4:30	Adjourn

### Day 2 – Day of the week, Month, Day, Meeting Location

8:00	Function Analysis/Fast Diagram

8:45	Cost/Function and Performance/Function Analysis

9:30	Team Brainstorming

12:00 	Lunch

1:00	Team Brainstorming (Cont)

4:30	Adjourn

### Day 3 – Day of the week, Month, Day, Meeting Location

8:00 	 Evaluation of Ideas

12:00	Lunch

1:00	Evaluation of Ideas (Cont), Team Assignments for Development

2:45 	Review Alternative Development Process

3:00	Research and Refine Ideas

4:30	Adjourn

### Day 4 – Day of the week, Month, Day, Meeting Location

8:00 	Research and Refine Ideas (Cont)

10:00	Review of VA Alternatives (Technical Reviewers)

11:30	Develop and Document Alternatives

12:00	Lunch

1:00	Develop and Document Alternatives (Cont)

4:30	Adjourn

### Day 5 – Day of the week, Month, Day, Meeting Location

8:00	Develop and Document Alternatives (Cont)

12:00	Lunch

1:00	Complete Alternative Development

4:30	Adjourn

### Day 6 – Day of the week, Month, Day, Meeting Location

8:00	Group Review and Ranking of VA Alternatives/Strategy; Presentation Preparation

11:00	Finalize Alternatives and Prepare Presentation

12:00	Lunch

11:00	Finalize Alternatives and Prepare Presentation

2:00	Presentation of VA Alternatives Meeting (Presentation of VA Study Results to Management and Stakeholders)

MEETING ATTENDEES

Include the attendance and contact information for all VA Study participants.

| Pre-Study | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Name | Position/Role | Organization | Telephone | E-mail |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| X | X | X | X | X | X | Name | Title | Organization | 555-555-1212 | john.doe@dot.ca.gov |
| X | X | X | X | X | X | Name | Title | Organization | 555-555-1212 | john.doe@dot.ca.gov |
| X | X | X | X | X | X | Name | Title | Organization | 555-555-1212 | john.doe@dot.ca.gov |
| X | X | X | X | X | X | Name | Title | Organization | 555-555-1212 | john.doe@dot.ca.gov |
| X | X | X | X | X | X | Name | Title | Organization | 555-555-1212 | john.doe@dot.ca.gov |
| X | X | X | X | X | X | Name | Title | Organization | 555-555-1212 | john.doe@dot.ca.gov |