Page 1 of 8

Section 19-17. Use for ground movement and vibration monitoring during geotechnical related construction, such as construction of embankment, earth retaining system, ground improvement, tunnel, and trenchless construction.

This specification specifies only monitoring equipment and submittal requirements.

Project specific specifications that specify thresholds for suspension of construction or termination of construction is needed. The project specific specification can refer to this section. The layout of monitoring equipment should be shown on the Plans.

Replace section 19-17 with:

19-17  GROUND MOVEMENT AND VIBRATION MONITORING

## 19-17.01  GENERAL

### 19-17.01A  Summary

1

Section 19-17 includes specifications for ground movement and vibration monitoring. Ground movement and vibration monitoring includes:

1.	Installing ground movement and vibration monitoring sensors at locations shown

2.	Installing data acquisition devices, radio transceivers, internet gateway providing internet connection, power supply, and software or web service to process, transmit, analyze, and display monitoring data

3.	Monitoring ground movement and vibration

2. Enter the construction job component, start date, which may be the start or completion of the construction of the job component, and the end of monitoring period in the construction stage as provided in the geotechnical report. Edit the first sentence to clearly identify the start and end dates of monitoring period for the job component.

Monitoring period for the construction of _____ is from the ___ of construction of the job component to __ days after completing construction of the job component. Do not start construction of the job component before acceptance of installation report, system verification report, baseline readings, and commission of installed monitoring system.

### 19-17.01B  Definitions

3

real-time data and information: data and information that is delivered immediately after collection.

### 19-17.01C  Submittals

#### 19-17.01C(1)  General

4

Submit:

1.	Shop drawings, including:

1.1.	Plan sheets showing the layout of instruments, sensors, cables, tubes, conduits, data acquisition devices, radio transceivers, and cellular gateway

1.2.	Conceptual installation and monitoring schedules, including controlling construction activities that affect system installation, monitoring, and salvage or abandonment of equipment

1.3.	Equipment data sheet

1.4.	Manufacturer's calibration certificates that are traceable to the U.S. National Institute of Standards and Technology, if applicable

2.	Installation report after the installation, including:

2.1.	Plan sheets showing layout, identifications, locations, coordinates, and elevations of sensors, cables, tubes, conduits, data acquisition devices, radio transceivers, and cellular gateway

2.2.	Drill logs with geological profiles and water levels if applicable

3.	System verification report

4.	Baseline readings

#### 19-17.01C(2)  Baseline Vibration Level Report

5

Include:

1.	Date of existing baseline condition for each monitoring location

2.	Description of each monitoring location

3.	Maximum single-component and resultant peak particle velocities at 15-second intervals

#### 19-17.01C(3)  Monitoring Data and Information

6

Transmit real-time monitoring data and information electronically by wireless network or cellular data transmission. Furnish software or web service with secure login that processes, calculates, displays monitoring data, and provides warning if monitored movement or vibration exceeds threshold values described.

7

Maintain continuous and scheduled data collection and transmission. Resolve any data outage caused by damaged or faulty equipment or systems within 72 hours.

8

For data needed to determine thresholds for immediate suspension of construction, suspend construction if the data is not collected and transmitted.

9

For automated motorized total station (AMTS) ground surface movement monitoring, evaluate weather, site, and traffic conditions to set the time and frequency of readings to obtain complete data coverage in each monitoring cycle.

10

Submit both raw and processed monitoring data in csv, xml, or JavaScript Object Notation (JSON) format within 5 days after termination of each monitoring system. Include instructions on data structures and field names for monitoring data.

#### 19-17.01C(4)  Reusable Equipment

11

Salvage and submit reusable equipment to the Engineer.

12

Reusable equipment includes settlement profile and movement profile monitoring systems, data acquisition devices, data transceivers, cellular gateway, solar panel assemblies, battery packs, electricity assemblies, protective boxes, and software paid for by the Contract.

### 19-17.01D  Quality Assurance

#### 19-17.01D(1)  General

13

Not Used

#### 19-17.01D(2)  Monitoring and Survey Data

14

AMTS movement monitoring data and survey data must comply with quality requirements described in the Department's Survey Manual and supplemental guidance.

## 19-17.02  MATERIALS

### 19-17.02A  General

15

Not Used

### 19-17.02B  Wireless Networks, Software, and Web Service

#### 19-17.02B(1)  General

#### 19-17.02B(2)  Wireless Networks

16

Wireless sensor networks include:

1.	Nodes, which include standalone or embedded:

1.1.	Data acquisition device for conditioning, converting, and processing data.

1.2.	Radio transceiver for transmitting data to cellular gateway or network. Transceiver must be able to: continuously transmit real-time data and information to the cellular gateway at a consistent frequency.

2.	Standalone or embedded cellular gateways that can receive data from nodes and transmit the data through cellular or satellite service to a cloud service or local network so that you, the Engineer, and the Engineer's representatives can monitor the data.

3.	Solar panel assembly, battery packs, or electrical supply that can power wireless networks for the duration of monitoring period.

4.	Protective enclosure with security lock for wireless nodes and cellular gateway.

5.	Surge and lightning protection.

17

The nodes for wireless network must be IP67 rated with temperature range between -40 degree C and 70 degree C.

#### 19-17.02B(3)  Data Process and Display Software or Web Service

18

Furnish software or web service to the Engineer and the Engineer's representatives. The software or web service must include IT security, data backup and recovery, and features that allow users to access, process, analyze, and display data, and set threshold warning values and transmit warning immediately when a threshold is exceeded.

### 19-17.02C  Monitoring System

#### 19-17.02C(1)  General

Not Used

#### 19-17.02C(2)  Settlement Gauge Monitoring System

19

Settlement gauge monitoring system must include:

1.	Settlement gauges with a semiconductor, vibrating wire, or fiber optic pressure transducer type including a thermistor. Each settlement gauge must include:

1.1.	Factory-attached signal cables of sufficient length to route to the data acquisition system. Use system manufacturer recommended splice kit if splicing is required.

1.2.	Designated reservoir or reservoirs for each settlement gauge or circuit placed in the protective enclosure attached to a base that is outside the zone of influence shown or as ordered.

1.3.	Twin tubing when using hydraulic type of settlement system.

1.4.	Survey markers for reservoir if not outside the zone of influence.

2.	Conduits for signal cables and tubes.

3.	Data acquisition device and radio transceivers.

4.	Solar panel assembly, battery packs, or electrical assembly that can power data acquisition device and radio transceiver for the duration of monitoring period.

5.	Protective enclosure with security lock for data acquisition device, reservoir, and radio transceiver.

6.	Surge and lightning protection for the monitoring system.

20

Settlement gauge must comply with the requirements shown in the following table:

| Settlement Gauge |  |
| --- | --- |
| Quality characteristic | Requirement |
| Range (feet) | 6 |
| Resolution (max, % full scale) | ±0.025 |
| Accuracy (max, % full scale) | ±0.1 |
| Fluid type | Antifreeze solution |
| Temperature range (ºC) | -40–80 |
| Thermal drift (max, % full scale / ºC) | ±0.1 |
| Corrosion resistance | Yes |

#### 19-17.02C(3)  Movement Profile Monitoring System

21

Movement profile monitoring system must include:

1.	In-place inclinometers (IPI) with micro-electro-mechanical systems (MEMS) that can be configured and installed horizontally to monitor settlement profile or vertically to monitor movement profile.

2.	Casing for IPI MEMS sensors:

2.1.	Casing for IPI MEMS must be grooved ABS pipe with load rating of at least 1500 lb and collapse rating of at least 190 psi. Measuring axes of the casing must be clearly marked on casing outside surface.

2.2.	Casing for shape array must be bell-end style PVC pipe with inside diameter of 2 ± 0.01 inches and outside diameter of 2.38 ± 0.01 inches or grooved ABS pipe with a load rating of at least 1500 lb and collapse rating of at least 190 psi. Measuring axes of the casing must be clearly marked under manufacturer's recommendations.

3.	Signal cables supplied by the system manufacturer with sufficient length to route to the data acquisition device. Use system manufacturer recommended splice kit if splicing is required.

4.	Conduits for signal cables.

5.	Data acquisition device and radio transceivers.

6.	Solar panel assembly, battery packs, and electrical assembly that can power data acquisition device and radio transceiver for the duration of monitoring period.

7.	Protective enclosure with security lock for data acquisition device, and radio transceiver.

8.	Surge and lightning protection for the monitoring system.

22

Movement profile monitoring system must comply with the requirements shown in the following table:

| Movement profile monitoring system |  |
| --- | --- |
| Quality characteristic | Requirement |
| Reading interval along profile (max, feet) | 8 |
| Resolution (arc seconds) | ±4 |
| Accuracy (arc seconds) | ±10 |
| Temperature range (ºC) | −40–80 |

#### 19-17.02C(4)  Automated Motorized Total Station Ground Surface Movement Monitoring System

23. Automated Motorized Total Station (AMTS) is usually paid for as a monthly rental for the duration of monitoring period.

Enter the number of monitoring prisms for the monitoring area for item 3 in the list. The default value is 8.

The practical range of current AMTS is 300 feet.

Automated Motorized Total Station (AMTS) ground surface movement monitoring system must include:

1.	AMTS installed at locations shown and be able to automatically target, take, and transmit survey data of designated control prisms, monitoring prisms, and settlement monitoring location array through wireless networks

2.	At least 5 control prisms for each AMTS. Place the control prisms:

2.1.	Outside the zone of influence

2.2.	In the light of sight of the AMTS throughout the duration of the monitoring period

2.3.	Evenly distributed around 360 degrees of the AMTS

2.4.	With varying distances from the AMTS

3.	At least 8 monitoring prisms installed at locations evenly distributed in the monitoring coverage area of the AMTS

4.	Instrument tower and brackets for AMTS must:

4.1.	Provide clearance and scanning angles so that the AMTS can scan prisms and reference points in the designated coverage areas and provide required accuracy

4.2.	Be stable and support the instruments without movement or vibrations during the monitoring period

4.3.	Include safety measures to protect AMTS from theft and protect workers while working at height

5.	Data acquisition device and radio transceiver that allows remote access for troubleshooting.

6.	Solar panel assembly, battery packs, and electrical assembly that can power data acquisition device and radio transceiver for the duration of monitoring period

7.	Surge and lightning protection for the monitoring system

24

AMTS ground surface movement monitoring system must comply with the requirements shown in the following table:

| AMTS Ground Surface Movement Monitoring System |  |
| --- | --- |
| Quality characteristic | Requirement |
| Range with no-prism target surface (max, feet) | 300 |
| Angle accuracy (max, seconds) | 1 |
| Accuracy with prism (max, inches) | 0.04 + 1 ppm |
| Accuracy with no-prism surface (max, inches) | 0.08 + 2 ppm |
| Elevation accuracy with prism (max, inches) | 0.1 |
| Elevation accuracy with no-prism surface (max, inches) | 0.2 |
| Temperature range (ºC) | −20–50 |

#### 19-17.02C(5)  Vibration Monitoring System

25

Vibration monitoring system must include:

1.	3-axis vibration transducer that:

1.1.	Is factory calibrated annually by the manufacturer

1.2.	includes self-test function

2.	Signal cables supplied by the system manufacturer with sufficient length to route to data acquisition device. Use system manufacturer recommended splice kit If splicing is required.

3.	Conduits for signal cables.

4.	Data acquisition device and radio transceiver

5.	Solar panel assembly, battery packs, and electrical assembly that can power data acquisition device and radio transceiver for the duration of monitoring period.

6.	Protective enclosure with security lock for data acquisition device and radio transceiver.

7.	Surge and lightning protection for the monitoring system.

26

Vibration monitoring system must comply with the requirements shown in the following table:

| 3-Axis Velocity Transducer |  |
| --- | --- |
| Quality characteristic | Requirement |
| Range (in/sec) | 0.01–4 |
| Resolution (max, in/sec) | 0.0025 |
| Accuracy (max, %) | 5 |
| Frequency response range (Hz) | 2–250 |

#### 19-17.02C(6)  Tilt Sensing System

27

Tilt sensing system must include tilt sensors that:

1.	Are battery powered

2.	Can transmit data using LoRa or Mesh systems to a cellular gateway

3.	Can transmit data from waterproof enclosure with antennae, or connectors if the sensor is under continuous submerged condition

4.	Can detect tilt motion greater than 1 degree/second

5.	Can immediately transmit warnings if threshold is exceeded

6.	Can be operational at any angle

28

Tilt sensing system must comply with the requirements shown in the following table:

| Tilt sensor |  |
| --- | --- |
| Quality characteristic | Requirement |
| Range (min, degrees) | ±90 |
| Resolution (max, degrees) | 0.0001 |
| Repeatability (max, degrees) | ±0.0003 |
| Reporting frequency (max, seconds) | 9.6 |
| International Protection (IP) rating | 68 |
| Operating temperature range (ºC) | −40–80 |

## 19-17.03  CONSTRUCTION

### 19-17.03A  General

29

Protect sensors, conduits, exposed cables, data acquisition devices, transceivers, and cellular gateway. Use hand operated compactor to compact the first 3-foot backfill over the instruments, conduits, and exposed cables. Do not operate construction equipment over the instruments and conduits before placement of hand-compacted backfill.

30

Protect monitoring systems under section 5-1.36 for the duration of monitoring. Immediately notify the Engineer upon discovering a monitoring system is damaged or no longer functioning. Repair or restore damaged monitoring system under section 5-1.39 within 3 days of discovering the damage.

### 19-17.03B  Installation

31

Install ground movement and vibration monitoring systems at locations and elevations shown.

32

Install IPI head assemblies casing under manufacturer's instructions

33

Install 3-axis vibration transducer as follows:

1.	Firmly attach on the surface of the object to be monitored, or firmly set in undisturbed soil

2. 	Align transducer longitudinal direction of measurement parallel to the alignment of the object

3. 	Align transducer transverse direction of measurement perpendicular to the alignment of the object

34

Install tilt sensors at locations with low temperature fluctuation. For tilt sensors to be subjected to direct sunlight, provide radiant barrier or sun shield.

35

Route cables through the conduits and establish data transmission links between monitoring sensor, data acquisition device, and radio transceiver.

36

Mark sensors, cables, tubes, conduits, data acquisition devices, radio transceivers, and cellular gateway to allow identification on the site.

### 19-17.03C  System Calibration, Verification, and Maintenance

37

Calibrate and verify that the installed systems meet the requirements. Submit system calibration and verification report within 7 days of system installation. Commission equipment and instruments in the presence of the Engineer.

38

During monitoring period, maintain and calibrate installed systems under manufacturer's recommended schedules and procedures.

### 19-17.03D  Monitor Baseline Vibration Levels

39

Before construction, monitor and record vibration at least two nonconsecutive workdays, spanning the hours during which construction activities will take place to establish baseline vibration levels.

### 19-17.03E  Salvage Reusable Equipment

40. Remove if the entire ground movement and vibration monitoring system is paid as monthly rental.

After completion of settlement, movement or vibration monitoring, salvage reusable equipment and submit to the Engineer.

## 19-17.04  PAYMENT

41. Edit if part of the monitoring system is paid as monthly rental, such as AMTS ground surface movement monitoring system. Replace with “Not Used” if no equipment is paid as rental.

The ground movement and vibration monitoring systems are paid as monthly rental for the duration of the monitoring period.