## SRL 1
Attachment 1 - FY 13/14 Project Workload File
CD | Project Type | ID | co | rte | Work Description | Total FTE | Document | Document Year | PPNO | Environmental | Design | Right of Way | Construction | OVERSIGHT | Total Capital Cost* | Approved Total Support Budget* | Environmental Support Budget | Design Support Budget | Right of Way Support Budget | Construction Support Budget | Total Prior Year(s) Expenditures | Approved Support To Capital % | Estimated Construction Start Date** | Estimated Construction End Date*** | Environmental FTEs FY 13/14 | Design FTEs FY 13/14 | Right of Way FTEs FY 13/14 | Construction FTEs FY 13/14 | PAED Implementing Agency | PSE Implementing Agency | ROW Implementing Agency | CON Implementing Agency
01 | ARRA | 38050 | MEN | 222 | REPLACE BRIDGE (SCOUR) | 0.3 | SHOPP | 2008 | 0222 | [5 empty] | 11650000 | 4832000 | 1049000 | 1898000 | 25000 | 1860000 | 5432377.89 | 41.48% | 2009-05-18 | 2012-01-06 | 0 | 0 | 0.04635 | 0.25365 | Caltrans | Caltrans | Caltrans | Caltrans
02 | ARRA | 37310 | PLU | 070 | CONSTRUCT BRIDGE | 3.9176 | SHOPP | 2008 | 3066 | [5 empty] | 45870000 | 12194000 | 2144000 | 2700000 | 600000 | 6750000 | 9391782.21 | 26.58% | 2010-05-03 | 2015-01-15 | 0 | 0 | 0.13949 | 3.7781 | Caltrans | Caltrans | Caltrans | Caltrans
02 | ARRA | 2C50U | TEH | 005 | BRIDGE DECK MAINTENANCE, REPLACE PCC PAVEMENT | 2.3546 | SHOPP | 2008 | 3224 | [5 empty] | 36000000 | 6851000 | 1204000 | 1765000 | 246000 | 3636000 | 6017399.3 | 19.03% | 2009-06-26 | 2012-02-03 | 0 | 0 | 0.03232 | 2.3223 | Caltrans | Caltrans | Caltrans | Caltrans
02 | ARRA | 4C94U | SHA | 044 | IMPROVE CRUVE AND SHOULDER WIDENING | 0.34736 | SHOPP | 2008 | 3343 | [5 empty] | 6384000 | 2395803 | 589968 | 637649 | 294065 | 874121 | 1246304.82 | 37.53% | 2010-01-21 | 2010-12-08 | 0 | 0 | 0 | 0.34736 | Caltrans | Caltrans | Caltrans | Caltrans
03 | ARRA | 36690 | BUT | 099 | WIDEN SHOULDER | 0.45124 | SHOPP | 2008 | 0011N | [5 empty] | 21054000 | 8460000 | 1497000 | 2943000 | 940000 | 3080000 | 7199858.15 | 40.18% | 2009-06-26 | 2012-02-29 | 0 | 0 | 0.06 | 0.39124 | Caltrans | Caltrans | Caltrans | Caltrans
03 | ARRA | 1E030 | COL | 020 | RECONSTRUCT EMBANKMENT SLOPE RECONSTRUCT SHLDR, REPL GUARDRAIL | 1.7792 | SHOPP | 2008 | 2939 | [5 empty] | 8552000 | 2220000 | 452000 | 669000 | 75000 | 1024000 | 1972495.54 | 25.96% | 2009-07-31 | 2011-10-11 | 0 | 0 | 0.01 | 1.7692 | Caltrans | Caltrans | Caltrans | Caltrans
03 | ARRA | 0C281 | COL | 005 | INSTALL CMS AND CCTV | 0.29791 | SHOPP | 2008 | 6198A | [5 empty] | 10580000 | 2636000 | 347000 | 975000 | 149000 | 1165000 | 1907686.88 | 24.91% | 2009-06-17 | 2011-03-28 | 0 | 0 | 0.0948 | 0.20311 | Caltrans | Caltrans | Caltrans | Caltrans
03 | ARRA | 1A841 | ED | 089 | INSTALL DRAINAGE FACILITIES | 0.42563 | SHOPP | 2008 | 3453A | [5 empty] | 26401000 | 9505000 | 2910000 | 2726000 | 252000 | 3617000 | 8979574.64 | 36% | 2009-05-29 | 2012-02-03 | 0 | 0 | 0.2345 | 0.19113 | Caltrans | Caltrans | Caltrans | Caltrans
03 | ARRA | 3C880 | SUT | 099 | REPLACE OPEN GRADED ASPHALT | 0.07334 | SHOPP | 2008 | 8367 | [5 empty] | 21200000 | 2414000 | 12000 | 711000 | 11000 | 1680000 | 1031889.49 | 11.39% | 2009-06-05 | 2010-01-06 | 0 | 0 | 0 | 0.07334 | Caltrans | Caltrans | Caltrans | Caltrans
03 | ARRA | 4C030 | SAC | 005 | INSTALL TRAFFIC MONITORING STATIONS | 0.14652 | SHOPP | 2008 | 5815 | [5 empty] | 5411000 | 2017000 | 296000 | 759000 | 281000 | 681000 | 1295036.8 | 37.28% | 2009-05-15 | 2009-12-24 | 0 | 0 | 0.10269 | 0.04383 | Caltrans | Caltrans | Caltrans | Caltrans
03 | ARRA | 4C090 | ED | 049 | WIDEN ROADWAY | 0.22845 | SHOPP | 2008 | 3112 | [5 empty] | 10200000 | 6055000 | 1197000 | 2221000 | 962000 | 1675000 | 5955012.71 | 59.36% | 2009-06-12 | 2010-10-25 | 0 | 0 | 0.01579 | 0.21266 | Caltrans | Caltrans | Caltrans | Caltrans
04 | ARRA | 15034 | SCL | 280 | INSTALL RAMP METERING SYSTEMS | 0.00863 | PARTNERSHIP
04 | ARRA | 15340 | SM | 280 | INSTALL RAMP METERING SYSTEMS | 0.01258 | PARTNERSHIP
04 | ARRA | 16374 | SF | 101 | CONSTRUCT TUNNNEL / RETAINING WALLS | 1.6765 | STIP | 2012 | 0619A | [5 empty] | 128606000.0125 | 18135000 | H | 4256000 | N | 13879000 | 26907932.2967 | 14.1% | 2010-02-04 | 2012-12-31 | 0 | 0.06365 | 0.03305 | 1.5798 | Local | Caltrans | Caltrans | Caltrans
04 | ARRA | 22614 | MRN | 101 | WIDEN FREEWAY | 1.2052 | STIP | 2006 | 342L4 | [5 empty] | 92009000 | 30441000 | 1567000 | 10072000 | 6636000 | 12166000 | 27419032.99 | 33.08% | 2007-08-15 | 2011-09-27 | 0 | 0 | 0.56488 | 0.64036 | Caltrans | Caltrans | Caltrans | Caltrans
04 | ARRA | 29491 | ALA | 024 | CONSTRUCT TUNNEL AND BUILDING | 28.3873 | STIP | 2008 | 0057A |  |  |  | X |  | 277334000 | 95423000 | 20483000 | 32670000 | 270000 | 42000000 | 42625838.8374 | 34.41% | 2009-11-10 | 2014-02-01 | 0 | 0 | 0.87291 | 27.5144 | Caltrans | Caltrans | Caltrans | Caltrans
04 | ARRA | 0G190 | ALA | 580 | CONVERT EB LANE TO HOT LANE | 4.3382 | PARTNERSHIP | [6 empty] | O
04 | ARRA | 1A980 | SCL | 101 | WIDEN FREEWAY | 1.1793 | SHOPP | 2008 | 0468G | [5 empty] | 35469000 | 16894000 | 3396000 | 6646000 | 19000 | 6833000 | 9244056.36 | 47.63% | 2010-10-01 | 2012-08-31 | 0 | 0 | 0.6627 | 0.51659 | Local | Local | Local | Caltrans
04 | ARRA | 4A790 | SCL | 101 | CONVERT HIGH OCCUPANCY VEHICLE LANES TO TWO HOT LANES | 4.4977 | PARTNERSHIP
05 | ARRA | 0G030 | SLO | 101 | HIGHWAY REHABILITATION | 3.9149 | SHOPP | 2008 | 0030 | [5 empty] | 40450000 | 10300000 | 1300000 | 3200000 | 100000 | 5700000 | 10227322.47 | 25.46% | 2009-12-30 | 2014-07-15 | 0 | 0 | 0.03581 | 3.8791 | Caltrans | Caltrans | Caltrans | Caltrans
06 | ARRA | 41610 | MAD | 145 | ASPHALT CONCRETE OVERLAY | 0.02564 | SHOPP | 2008 | 5458 | [5 empty] | 17696000 | 6402000 | 834000 | 1965000 | 1883000 | 1720000 | 6012540.39 | 36.18% | 2009-06-08 | 2010-09-20 | 0 | 0 | 0.01818 | 0.00746 | Caltrans | Caltrans | Caltrans | Caltrans
06 | ARRA | 0K890 | KER | 005 | REPLACE CONCRETE PANEL | 0.95523 | SHOPP | 2008 | 6487 | [5 empty] | 33300000 | 5420000 | E | 1900000 | 20000 | 3500000 | 3038863.33 | 16.28% | 2010-12-13 | 2013-05-01 | 0 | 0 | 0 | 0.95523 | Caltrans | Caltrans | Caltrans | Caltrans
07 | ARRA | 26900 | LA | 710 | PLACE HOT MIX ASPHALT | 2.2495 | SHOPP | 2008 | 4045 |  |  |  | X |  | 65850000 | 18000000 | E | 7000000 | 300000 | 10700000 | 12028862.57 | 27.33% | 2009-08-06 | 2013-07-12 | 0 | 0 | 0.01783 | 2.2317 | Caltrans | Caltrans | Caltrans | Caltrans
07 | ARRA | 1218V | LA | 005 | CONSTRUCT HOV LANES | 17.8634 | STIP | 2008 | 0151E |  |  |  | X |  | 103851472 | 28507020 | 780000 | 12800100 | 1730000 | 13196920 | 23005914.0687 | 27.45% | 2010-10-14 | 2014-05-19 | 0 | 0 | 0.31903 | 17.5444 | Caltrans | Caltrans | Caltrans | Caltrans
10 | ARRA | 0H04U | SJ | 004 | REALIGN CURVE | 1.1707 | SHOPP | 2008 | 7025 | [5 empty] | 20907000 | 6759000 | H | 2137000 | 515000 | 4107000 | 4877324.83 | 32.33% | 2009-09-03 | 2012-11-09 | 0 | 0 | 0.1337 | 1.037 | Caltrans | Caltrans | Caltrans | Caltrans
10 | ARRA | 0K020 | MER | 099 | REPLACE BRIDGES | 1.0565 | SHOPP | 2008 | 5423 | [5 empty] | 44669000 | 6584000 | 1261000 | 2425000 | 468000 | 2430000 | 8839578.53 | 14.74% | 2009-10-08 | 2013-04-01 | 0 | 0 | 0.59182 | 0.46473 | Caltrans | Caltrans | Caltrans | Caltrans
10 | ARRA | 0L570 | SJ | 205 | HIGHWAY PLANTING AND IRRIGATION | 0.13029 | STIP | 2008 | 0001 |  |  |  | X |  | 1364000 | 827000 | 76000 | 350000 | 1000 | 400000 | 627430.92 | 60.63% | 2010-04-05 | 2014-05-16 | 0 | 0 | 0 | 0.13029 | Caltrans | Caltrans | Caltrans | Caltrans
02 | BOND CMIA | 37100 | SHA | 005 | WIDEN ROADWAY | 0.61433 | STIP | 2008 | 3329 | [5 empty] | 11745000 | 4734000 | 305000 | 1363000 | 966000 | 2100000 | 2945010.01 | 40.31% | 2010-04-21 | 2011-11-17 | 0 | 0 | 0.0019 | 0.61243 | Caltrans | Caltrans | Caltrans | Caltrans
02 | BOND CMIA | 4C401 | SHA | 005 | WIDEN BRIDGES WITH PCPS GIRDERS | 0.96301 | STIP | 2010 | 3331 | [5 empty] | 19463000 | 4005000 | 1195000 | 510000 | 50000 | 2250000 | 3098759.39 | 20.58% | 2011-05-09 | 2013-01-31 | 0 | 0 | 0 | 0.96301 | Caltrans | Caltrans | Caltrans | Caltrans
03 | BOND CMIA | 36782 | PLA | 080 | CONSTRUCT AUXILIARY AND HOV LANES | 0.66358 | STIP | 2008 | 0146C | [5 empty] | 31400000 | 16177000 | 2136000 | 6498000 | 400000 | 7143000 | 14602042.0867 | 51.52% | 2008-05-01 | 2012-10-18 | 0 | 0 | 0.16358 | 0.5 | Caltrans | Caltrans | Caltrans | Caltrans
03 | BOND CMIA | 36783 | PLA | 080 | CONSTRUCT HOV LANES | 1.308 | STIP | 2008 | 0146F | [5 empty] | 40374000 | 9000000 | H | 3500000 | 200000 | 5300000 | 7970563.69 | 22.29% | 2009-08-10 | 2012-10-01 | 0 | 0 | 0.3 | 1.008 | Caltrans | Caltrans | Caltrans | Caltrans
03 | BOND CMIA | 44161 | SAC | 050 | WIDEN FREEWAY | 1.6536 | STIP | 2008 | 6199C | [5 empty] | 80549000 | 25544043 | 5180205 | 7510780 | 1353058 | 11500000 | 25878205.1157 | 31.71% | 2009-10-26 | 2013-01-15 | 0 | 0 | 0.1 | 1.5536 | Caltrans | Caltrans | Caltrans | Caltrans
03 | BOND CMIA | 1E490 | BUT | 032 | WIDEN TO FOUR LANES | 1.26 | PARTNERSHIP | 2010 | 2107 |  |  |  |  | O
03 | BOND CMIA | 2A690 | NEV | 049 | WIDEN ROADWAY WITH HOT MIX ASPHALT | 2.6812 | STIP | 2010 | 4107 | [5 empty] | 18947000 | 11072000 | 2900000 | 2672000 | 2000000 | 3500000 | 10200963.06 | 58.44% | 2010-05-28 | 2014-12-01 | 0 | 0 | 1 | 1.6812 | Caltrans | Caltrans | Caltrans | Caltrans
03 | BOND CMIA | 2E510 | ED | 050 | RAMP IMPROVEMENTS | 0.52198 | PARTNERSHIP | [6 empty] | O
03 | BOND CMIA | 3338U | PLA | 065 | CONSTRUCT NEW FREEWAY AND BRIDGES | 6.41 | STIP | 2012 | 0145M | [5 empty] | 248203000 | 44000000 | 5600000 | 13400000 | 3000000 | 22000000 | 41691559.42 | 17.73% | 2008-06-09 | 2013-06-15 | 0 | 0 | 0.75 | 5.66 | Caltrans | Caltrans | Caltrans | Caltrans
03 | BOND CMIA | 3797U | SAC | 080 | REPLACE PCCP AND PLACE HMA | 27.4166 | SHOPP | 2010 | 6683 | [5 empty] | 105788000 | 27523000 | 2915000 | 7972000 | 636000 | 16000000 | 14530362.04 | 26.02% | 2011-07-29 | 2015-11-15 | 0 | 0 | 2.68 | 24.7366 | Caltrans | Caltrans | Caltrans | Caltrans
03 | BOND CMIA | 3A711 | ED | 050 | CONSTRUCT HOV LANES BY ADDING ADDITIONAL LANES IN THE MEDIAN | 0.27447 | STIP | 2008 | 3283A | [5 empty] | 37908000 | 6660000 | H | 3000000 | 100000 | 3560000 | 1072347.39 | 17.57% | 2008-11-18 | 2012-09-04 | 0 | 0 | 0.07342 | 0.20105 | Caltrans | Local | Local | Local
04 | BOND CMIA | 12965 | SON | 101 | WIDEN AND RECONSTRUCT INTERCHANGE | 1.4975 | STIP | 2010 | 0781E | [5 empty] | 56480000 | 21072000 | 5018000 | 8104000 | 1350000 | 6600000 | 19283002.73 | 37.31% | 2009-03-03 | 2012-12-30 | 0 | 0 | 0.49862 | 0.9989 | Caltrans | Caltrans | Caltrans | Caltrans
04 | BOND CMIA | 15113 | ALA | 580 | INSTALL RAMP METERING AND HOV BYPASS AT VARIOUS ON RAMPS | 2.4655 | SHOPP | 2010 | 7965F | [5 empty] | 9010000 | 4416000 | 1472000 | 1178000 | 220000 | 1546000 | 3006283.27 | 49.01% | 2012-10-24 | 2014-10-01 | 0 | 0 | 0.06589 | 2.3996 | Caltrans | Caltrans | Caltrans | Caltrans
04 | BOND CMIA | 15300 | ALA | 092 | INSTALL RAMP METERING | 6.2301 | STIP | 2012 | 0024 | [5 empty] | 5172692.4913 | 2365000.0001 | 635000 | 783999.9999 | 118000 | 828000.0002 | 1783083.73 | 45.72% | 2012-10-15 | 2014-12-01 | 0 | 0 | 0.04957 | 6.1805 | Caltrans | Caltrans | Caltrans | Caltrans
04 | BOND CMIA | 15320 | SCL | 680 | INSTALL RAMP METERING & TRAFFIC OPERATIONS SYSTEMS | 6.3779 | SHOPP | 2010 | 0521F | [5 empty] | 16295000 | 5891000 | D | 3647000 | 280000 | 1964000 | 2992285.78 | 36.15% | 2012-11-20 | 2014-12-31 | 0 | 0.07687 | 0.02834 | 6.2726 | Caltrans | Caltrans | Caltrans | Caltrans
04 | BOND CMIA | 15350 | SOL | 080 | INSTALL RAMP METERING AND TRAFFIC OPERARTIONS SYSTEMS ELEMENTS | 3.0023 | STIP | 2012 | 0024 |  |  |  | X |  | 21384000 | 7018000 | 1888000 | 2504000 | 108000 | 2518000 | 3858815.19 | 32.82% | 2012-08-31 | 2013-12-12 | 0 | 0 | 0.09258 | 2.9097 | Caltrans | Caltrans | Caltrans | Caltrans
04 | BOND CMIA | 15420 | SCL | 085 | INSTALL RAMP METERING AND TRAFFIC OPERATIONS SYSTEMS | 6.7197 | SHOPP | 2010 | 0440E | [5 empty] | 9562000 | 3292000 | D | 2038000 | 157000 | 1097000 | 2031691.53 | 34.43% | 2012-07-22 | 2014-12-31 | 0 | 0.03218 | 0.04784 | 6.6397 | Caltrans | Caltrans | Caltrans | Caltrans
04 | BOND CMIA | 17131 | ALA | 084 | WIDEN ROADWAY AND RELOCCATE UTILITIES | 0.11037 | PARTNERSHIP | 2010 | 0115E |  |  |  |  | O
04 | BOND CMIA | 23563 | SM | 101 | WIDEN ROADWAY AND BRIDGE | 1.8328 | STIP | 2010 | 0658B |  |  |  | X |  | 23207000 | 17431000 | 2800000 | 6056000 | 316000 | 8259000 | 13209049.3783 | 75.11% | 2011-06-01 | 2013-07-01 | 0 | 0 | 0.32868 | 1.5041 | Caltrans | Caltrans | Caltrans | Caltrans
04 | BOND CMIA | 23564 | SM | 101 | CONSTRUCT NEW AUXILIARY LANES | 2.1497 | STIP | 2010 | 0658C |  |  |  | X |  | 14448000 | 8066000 | 1300000 | 2788000 | 176000 | 3802000 | 5921006.0017 | 55.83% | 2012-05-24 | 2013-11-09 | 0 | 0.05508 | 0.27349 | 1.8211 | Caltrans | Caltrans | Caltrans | Caltrans
04 | BOND CMIA | 24657 | CC | 004 | CONSTRUCT INTERCHANGE | 5.1644 | PARTNERSHIP | [6 empty] | O
04 | BOND CMIA | 26406 | MRN | 101 | CONSTRUCT HOV LANES | 1.3056 | STIP | 2010 | 0360F | [5 empty] | 28750000 | 21092000 | 9520000 | 4507000 | 65000 | 7000000 | 9675619.25 | 73.36% | 2011-06-02 | 2012-12-17 | 0 | 0 | 0.01335 | 1.2923 | Caltrans | Caltrans | Caltrans | Caltrans
04 | BOND CMIA | 26407 | MRN | 101 | CONSTRUCT INTERCHANGE ON RTE 101 AT SAN ANTONIO RD;INCLUDING FRONTAGE | 10.5138 | STIP | 2012 | 0360J | [5 empty] | 56722000 | 23960000 | 8822000 | 7573000 | 2595000 | 4970000 | 3689751.03 | 42.24% | 2012-09-14 | 2014-12-01 | 0 | 0 | 3.108 | 7.4058 | Caltrans | Local | Caltrans | Caltrans
04 | BOND CMIA | 26408 | SON | 101 | CONSTRUCT INTERCHANGE ON RTE 101 AT PETALUMA BLVD;INCLUDING FRONTAGE | 1.9222 | STIP | 2010 | 0360H | [5 empty] | I | I | I | I | I | I | 3612004.98 | NA | 2012-11-01 | 2014-12-01 | 0 | 0 | 1.8949 | 0.027308 | Caltrans | Local | Caltrans | Caltrans
04 | BOND CMIA | 26413 | NAP | 012 | CONSTRUCT TWO ADDITIONAL LANES | 13.2085 | STIP | 2010 | 0367I | [5 empty] | 39790000 | 10650000 | 1790000 | 3190000 | 820000 | 4850000 | 7529740.5683 | 26.77% | 2012-01-26 | 2014-12-01 | 0 | 0 | 0.43685 | 12.7717 | Caltrans | Local | Caltrans | Caltrans
04 | BOND CMIA | 26414 | NAP | 012 | CONSTRUCT TWO ADDIONAL LANES | 20.3279 | STIP | 2010 | 0367D | [5 empty] | 84162000 | 20010000 | 3320000 | 5910000 | 1530000 | 9250000 | 10636403.1717 | 23.78% | 2012-01-11 | 2015-02-01 | 0 | 0 | 0.49494 | 19.833 | Caltrans | Local | Caltrans | Caltrans
04 | BOND CMIA | 29083 | ALA | 580 | CONSTRUCT HOV LANES | 0.61531 | SHOPP | 2008 | 0117F | [5 empty] | 35203000 | 11288000 | 6300000 | 530000 | H | 4458000 | 8155844.24 | 32.07% | 2009-07-22 | 2011-09-30 | 0 | 0 | 0 | 0.61531 | Local | Local | Local | Caltrans
04 | BOND CMIA | 29084 | ALA | 580 | WIDEN ROADWAY | 0.1827 | STIP | 2008 | 0112A | [5 empty] | 55238000.0004 | 11870000 | 5700000 | 470000 | H | 5700000 | 8344793.92 | 21.49% | 2008-07-28 | 2010-02-04 | 0 | 0 | 0 | 0.1827 | Local | Local | Local | Caltrans
04 | BOND CMIA | 29761 | ALA | 084 | XPWAY WIDENING SEG1 (N) FROM 2-4 LN FROM CONANNON TO STANLEY & FROM 4- | 9.9612 | STIP | 2012 | 0081G |  |  |  | X |  | 32085000 | 8980000 | 1000000 | 4200000 | G | 3780000 | 2561887.8795 | 27.99% | 2012-03-21 | 2014-01-01 | 0 | 0 | 0 | 9.9612 | Local | Local | Local | Caltrans
04 | BOND CMIA | 29830 | SCL | 880 | WIDEN FROM 6 TO 8 LANES FOR HOV | 17.1901 | STIP | 2010 | 0415 |  |  |  | X |  | 73490000 | 21510000 | 5500000 | 6200000 | G | 9810000 | 4548736.29 | 29.27% | 2011-08-29 | 2014-06-30 | 0 | 0 | 0.32141 | 16.8687 | Local | Local | Local | Caltrans
04 | BOND CMIA | 44560 | SCL | 880 | IMPROVEMENTS AT SR-17/I-280/I-880 INTERCHANGE, I-280/WINCHESTER BLVD | 7.4998 | PARTNERSHIP | 2012 | 0408G |  |  |  |  | O
04 | BOND CMIA | 0A10A | SON | 101 | FOLLOW UP LANDSCAPING PROJECT | 5.1268 | PARTNERSHIP
04 | BOND CMIA | 0A184 | SON | 101 | WIDEN ROADWAY AND BRIDGE | 1.7562 | STIP | 2010 | 0775A |  |  |  | X |  | 13977000 | 4656000 | H | 1506000 | 150000 | 3000000 | 5497309.97 | 33.31% | 2011-05-19 | 2013-12-31 | 0 | 0 | 0.1801 | 1.5761 | Local | Local | Caltrans | Caltrans
04 | BOND CMIA | 0A18U | SON | 101 | WIDEN HIGHWAY AND BRIDGE | 0.95944 | STIP | 2010 | 0775 | [5 empty] | 68011000 | 24750000 | 3500000 | 10000000 | 750000 | 10500000 | 17341831.36 | 36.39% | 2009-10-12 | 2012-08-31 | 0 | 0 | 0.95944 | 0 | Local | Local | Caltrans | Caltrans
04 | BOND CMIA | 0A532 | SOL | 080 | RAMP METERING AND WEIGH IN MOTION SYSTEM | 0.34444 | STIP | 2010 | 8320C | [5 empty] | 4768000 | 1319000 | H | 1500000 | C | 1319000 | 1074130.34 | 27.66% | 2010-10-12 | 2012-02-29 | 0 | 0 | 0.11691 | 0.22753 | Local | Local | Local | Caltrans
04 | BOND CMIA | 0A534 | SOL | 080 | RECONSTRUCT 1-80 WB/SR WB CONNECTOR AND GREEN VALLY RD. INTERCHANGE | 15.0338 | STIP | 2012 | 5301L | [5 empty] | 78880000 | 8460000 | H | 8880000 | G | 8460000 | 990996.84 | 10.73% | 2013-08-10 | 2015-12-31 | 0 | 0.91093 | 0.09053 | 14.0324 | Local | Local | Local | Caltrans
04 | BOND CMIA | 1G360 | SCL | 101 | IMPROVEMENTS TO SB OFF RAMP AT YERBA BUENA ROAD AND AUXILLARY LANE | 3.8227 | PARTNERSHIP | 2012 | 0460G |  |  |  | X
04 | BOND CMIA | 1G940 | CC | 004 | WIDEN ROADWAY AND RECONSTRUCT INTERCHANGE | 21.2585 | STIP | 2008 | 0192I | [5 empty] | 59775000 | 13389000 | H | 7443000 | G | 13389000 | 3003379.181 | 22.4% | 2012-05-25 | 2015-08-01 | 0 | 0 | 0.08969 | 21.1688 | Local | Local | Local | Caltrans
04 | BOND CMIA | 1G941 | CC | 004 | WIDEN ROADWAY AND RECONSTRUCT INTERCHANGE | 8.3 | PARTNERSHIP | 2010 | 0192L |  |  |  |  | O
04 | BOND CMIA | 2285C | CC | 004 | HIGHWAY WIDENING AND RECONSTRUCT SOMERVILLE INTERCHANGE | 5.5695 | STIP | 2008 | 0192F |  |  |  | X |  | 39641000 | 10608000 | H | 6242000 | G | 10608000 | 6692768.6084 | 26.76% | 2011-01-05 | 2013-09-01 | 0 | 0 | 0.1733 | 5.3962 | Local | Local | Local | Caltrans
04 | BOND CMIA | 2285E | CC | 004 | WIDEN ROADWAY AND RECONSTRUCT INTERCHANGE | 19.4342 | STIP | 2008 | 0192H | [5 empty] | 48717000 | 14395000 | H | 8754000 | G | 14395000 | 4762155.251 | 29.55% | 2011-10-20 | 2015-07-01 | 0 | 0 | 0.02796 | 19.4063 | Local | Local | Local | Caltrans
04 | BOND CMIA | 2640K | SON | 101 | IN SON CO, MODIFY SR 116/101 INTERCHANGE | 15.1154 | STIP | 2010 | 0360R | [5 empty] | 25929000 | 5750000 | H | 950000 | H | 4800000 | 196372.11 | 22.18% | 2012-11-02 | 2014-10-01 | 0 | 0 | 0.01137 | 15.1041 | Caltrans | Local | Caltrans | Caltrans
04 | BOND CMIA | 2640U | MRN | 101 | WIDEN FOR HOV LANES AND CONVERT AN EXISTING FOUR-LANE EXPRESSWAY TO A | 27.214 | STIP | 2012 | 0360H | [5 empty] | 90406000 | 32727000 | 7600000 | 11037000 | 1900000 | 12190000 | 725063.71 | 36.2% | 2012-11-01 | 2014-12-01 | 0 | 0 | 0.26125 | 26.9528 | Caltrans | Local | Caltrans | Caltrans
04 | BOND CMIA | 2641A | NAP | 012 | REPLACE LANDSCAPE | 3.8054 | STIP | 2012 | 0367J | [5 empty] | 715000 | 285000 | H | 140000 | 5000 | 140000 | 0 | 39.86% | 2015-02-01 | 2018-10-01 | 0 | 3.6271 | 0.17829 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
04 | BOND CMIA | 2908C | ALA | 580 | CONSTRUCT WB HOV LANE AND AUX LANES :REAB ROADWAY | 24.6322 | PARTNERSHIP | 2012 | 0112B
04 | BOND CMIA | 2908E | ALA | 580 | CONSTRUCT WB HOV LANE AND AUX LANE REHAB ROADWAY | 18.1409 | PARTNERSHIP | 2008 | 0112F
04 | BOND CMIA | 2908V | ALA | 580 | CONS. EB AUX LANES FRM FIRST ST. TO ISABEL, WDN TWO ARROYO L POSITAS B | 17.8666 | STIP | 2012 | 0012E | [5 empty] | 36244000 | 6695000 | 1575000 | 1570000 | H | 3550000 | 1577669.976 | 18.47% | 2012-08-23 | 2014-11-01 | 0 | 0 | 0 | 17.8666 | Local | Local | Local | Caltrans
04 | BOND CMIA | 3A23U | SON | 101 | RECONSTRUCT THE EXISTING AIRPORT BLVD INTERCHANGE AND CONSTRUCT | 25.5879 | STIP | 2010 | 0749D | [5 empty] | 39451000 | 10170000 | 790000 | 4130000 | 750000 | 4500000 | 1479016.35 | 25.78% | 2012-12-03 | 2014-08-30 | 0 | 0 | 0.42747 | 25.1604 | Caltrans | Caltrans | Caltrans | Caltrans
04 | BOND CMIA | 3A771 | ALA | 080 | CONSTRUCT TRAFFIC OPERATIONS SYSTS. | 0.02064 | PARTNERSHIP | 2010 | 0062I
04 | BOND CMIA | 3A774 | ALA | 080 | TOS SOFTWARE PROCREMENT AND INTEGRATION | 2.6022 | PARTNERSHIP | 2010 | 0062G
04 | BOND CMIA | 3A775 | ALA | 080 | SPECIALTY MATERIALS PROCUREMENT FOR TOS | 1.4075 | PARTNERSHIP | 2010 | 0062H
04 | BOND CMIA | 3A776 | ALA | 080 | ADAPTIVE RAMP METERING | 2.8373 | STIP | 2012 | 0062J |  |  |  | X |  | 7962000 | 2792000 | 650000 | 650000 | C | 1492000 | 1088884.8141 | 35.07% | 2012-09-15 | 2014-03-01 | 0 | 0 | 0.06188 | 2.7754 | Caltrans | Local | Local | Caltrans
04 | BOND CMIA | 3A777 | ALA | 080 | TOS ACTIVE TRAFFIC MANAGEMENT | 9.8058 | STIP | 2012 | 0062E | [5 empty] | 18656000 | 9480000 | 2597000 | 3208000 | C | 3675000 | 1499653.8042 | 50.81% | 2012-10-15 | 2014-08-01 | 0 | 0 | 0.00883 | 9.7969 | Caltrans | Local | Local | Caltrans
04 | BOND CMIA | 3A921 | ALA | 880 | CONSTRUCT NEW SOUTHBOUND HOV LANES | 21.5097 | PARTNERSHIP | 2008 | 0036F
04 | BOND CMIA | 3A922 | ALA | 880 | WIDEN MAINLINE AND BRIDGE FOR HOV LANE | 20.3118 | PARTNERSHIP | 2012 | 0036J
04 | BOND CMIA | 4A330 | SCL | 101 | CONSTRUCT AUXILIARY LANES | 6.4669 | STIP | 2010 | 0483I |  |  |  | X |  | 49968000 | 23231000 | 3971000 | 8180000 | G | 11080000 | 4125934.21 | 46.49% | 2011-10-01 | 2013-08-01 | 0 | 0 | 0.90064 | 5.5663 | Local | Local | Local | Caltrans
05 | BOND CMIA | 31580 | MON | 101 | CONSTRUCT NEW INTERCHANGE AT SAN JUAN ROAD | 22.5296 | STIP | 2012 | 0058E | [5 empty] | 73100000 | 17500000 | 4700000 | 5000000 | 2000000 | 5800000 | 13366239.43 | 23.94% | 2012-09-27 | 2014-12-26 | 0 | 0.0078 | 1.2784 | 21.2435 | Caltrans | Caltrans | Caltrans | Caltrans
05 | BOND CMIA | 31592 | MON | 001 | CONSTRUCT NEW INTERCHANGE | 1.5982 | STIP | 2012 | 0032G | [5 empty] | 18820000 | 11203000 | 3068000 | 2950000 | 757000 | 4428000 | 10920564.24 | 59.53% | 2009-10-07 | 2014-08-06 | 0 | 0 | 0.42467 | 1.1735 | Caltrans | Caltrans | Caltrans | Caltrans
05 | BOND CMIA | 33072 | SLO | 046 | WIDEN HIGHWAY TO FOUR LANES | 12.1474 | STIP | 2010 | 0226C |  |  |  | X |  | 68505000 | 14600000 | H | 6400000 | 1200000 | 7000000 | 13887616.593 | 21.31% | 2010-10-25 | 2014-02-01 | 0 | 0 | 1.8436 | 10.3038 | Caltrans | Caltrans | Caltrans | Caltrans
05 | BOND CMIA | 33077 | SLO | 046 | CONVERT TO 4-LANE EXPRESSWAY | 11.5596 | STIP | 2010 | 0226G | [5 empty] | 44400000 | 14600000 | H | 6000000 | 1600000 | 7000000 | 7494482.3444 | 32.88% | 2012-05-18 | 2015-09-08 | 0 | 0 | 1.0574 | 10.5022 | Caltrans | Caltrans | Caltrans | Caltrans
05 | BOND CMIA | 44590 | SLO | 101 | REPLACE SUTRUCTURE, ADD LAND AND BIKE PATH | 9.2323 | STIP | 2010 | A4459 | [5 empty] | 37526000 | 12773000 | 1796000 | 4112000 | 265000 | 6600000 | 8066074.26 | 34.04% | 2011-06-21 | 2015-10-01 | 0 | 0 | 0.21779 | 9.0145 | Caltrans | Caltrans | Caltrans | Caltrans
05 | BOND CMIA | 0F650 | SCR | 001 | CONSTRUCT NB AND SB AUXILIARY LANES | 5.4078 | STIP | 2010 | 6500 | [5 empty] | 16234000 | 3851000 | 2367000 | 1290000 | 194000 | G | 1885406.76 | 23.72% | 2012-01-05 | 2013-11-01 | 0 | 0 | 0.35787 | 5.0499 | Local | Local | Caltrans | Local
06 | BOND CMIA | 42370 | TUL | 198 | MODIFY INTERCHANGE | 0.94154 | PARTNERSHIP | 2012 | 0105
06 | BOND CMIA | 44252 | KER | 046 | WIDEN TO FOUR LANES | 9.0236 | STIP | 2008 | 3386A | [5 empty] | 60598000 | 14972000 | 438000 | 3579000 | 1055000 | 9900000 | 8943671.647 | 24.71% | 2011-01-26 | 2014-07-26 | 0 | 0 | 0.36758 | 8.656 | Caltrans | Caltrans | Caltrans | Caltrans
06 | BOND CMIA | 0L050 | KIN | 198 | HIGHWAY PLANTING | 0.81279 | STIP | 2010 | A4360Y | [5 empty] | 3600000 | 900000 | 100000 | 295000 | 5000 | 500000 | 317752.63 | 25% | 2012-05-22 | 2016-07-01 | 0 | 0 | 0 | 0.81279 | Caltrans | Caltrans | Caltrans | Caltrans
06 | BOND CMIA | 3568U | KIN | 198 | 2-LN CONVENTIONAL TO 4-LN EXPRESSWAY | 2.9528 | STIP | 2012 | A4360B |  |  |  | X |  | 73583000 | 20458000 | 2039000 | 5768000 | 3137000 | 9514000 | 19479061.79 | 27.8% | 2009-09-01 | 2013-08-01 | 0 | 0 | 0.54974 | 2.403 | Caltrans | Caltrans | Caltrans | Caltrans
07 | BOND CMIA | 12030 | LA | 405 | WIDEN FOR HOV LANE | 29.0821 | STIP | 2012 | 0851G | [5 empty] | 984100000 | 76000000 | 22000000 | 39000000 | 15000000 | M | 56901409.04 | 7.723% | 2009-04-23 | 2013-12-10 | 0 | 0.07827 | 3.8932 | 25.1106 | Caltrans | Caltrans | Caltrans | Local
07 | BOND CMIA | 12184 | LA | 005 | CONSTRUCT HOV LANES | 35.3344 | STIP | 2008 | 3987 | [5 empty] | 121786000 | 30838000 | 1300000 | 15020000 | 1800000 | 12718000 | 23362678.4863 | 25.32% | 2010-12-06 | 2015-02-20 | 0 | 0 | 1.3844 | 33.95 | Caltrans | Caltrans | Caltrans | Caltrans
07 | BOND CMIA | 21591 | LA | 005 | ROADWAY WIDENING (SEG 1) | 24.8599 | STIP | 2010 | 4153 |  |  |  | X |  | 75247000 | 15198000 | 1384000 | 5608000 | 1470000 | 6736000 | 11149202.5449 | 20.2% | 2011-11-28 | 2014-05-05 | 0 | 1.1242 | 2.4118 | 21.3238 | Caltrans | Caltrans | Caltrans | Caltrans
07 | BOND CMIA | 26070 | VEN | 101 | HOV LANES | 18.192 | STIP | 2010 | 3918 | [5 empty] | 67973000 | 33190000 | 5070000 | 12179000 | 641000 | 15300000 | 17694906.51 | 48.83% | 2012-01-03 | 2016-09-22 | 0 | 0 | 0.32461 | 17.8674 | Caltrans | Caltrans | Caltrans | Caltrans
07 | BOND CMIA | 1193U | LA | 010 | CONSTRUCT HOV LANE IN EA DIRECTION | 11.5128 | STIP | 2012 | 0310B |  | X | X |  |  | 192840000 | 42021000 | 643000 | 19961000 | 2525000 | 18892000 | 17464944.07 | 21.79% | 2015-03-16 | 2018-04-11 | 0 | 6.9559 | 4.557 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
07 | BOND CMIA | 1218W | LA | 005 | CONST HOV LN & IC MODIFICATION | 39.4689 | STIP | 2012 | 3985 | [5 empty] | 269877000 | 85482000 | 2050000 | 48000000 | 2432000 | 33000000 | 53497968.725 | 31.67% | 2012-11-29 | 2016-05-16 | 0 | 0.42241 | 1.8276 | 37.2189 | Caltrans | Caltrans | Caltrans | Caltrans
07 | BOND CMIA | 1219U | LA | 005 | CONSTRUCT HOV LANES | 21.7315 | STIP | 2010 | 0158K |  |  |  | X |  | 199355232 | 52121830 | 1626000 | 27899950 | 4840000 | 17755880 | 42185620.75 | 26.15% | 2010-05-06 | 2013-12-02 | 0 | 0 | 0.37425 | 21.3573 | Caltrans | Caltrans | Caltrans | Caltrans
08 | BOND CMIA | 44840 | RIV | 091 | ADD HOV LANES, MODIFY IC'S | 33.3372 | STIP | 2010 | 0092A | [5 empty] | 196296000 | 45153000 | 3193000 | 20262000 | 1100000 | 20598000 | 29136018.77 | 23% | 2012-02-10 | 2016-02-05 | 0 | 0 | 0.59372 | 32.7435 | Local | Caltrans | Local | Caltrans
08 | BOND CMIA | 49750 | SBD | 010 | CONSTRUCT LANES SHOULDERS AND WIDEN EXIT RAMP | 0.29459 | STIP | 2008 | 0137M | [5 empty] | 12260000 | 6040000 | 650000 | 1670000 | 440000 | 3280000 | 5619036.3 | 49.27% | 2010-10-12 | 2012-12-20 | 0 | 0 | 0 | 0.29459 | Caltrans | Caltrans | Caltrans | Caltrans
08 | BOND CMIA | 0071V | SBD | 215 | ADD TWO HOV LANES AND OPERATIONAL IMPROVEMENTS | 5.3858 | STIP | 2008 | 0247P | [5 empty] | 270043000 | 75602000 | 816000 | 26792000 | 10090000 | 37904000 | 24017772.4243 | 28% | 2009-08-27 | 2013-09-13 | 0 | 0 | 1.1112 | 4.2746 | Caltrans | Local | Caltrans | Local
08 | BOND CMIA | 0F150 | SBD | 010 | CONSTRUCT 1 W/B MIXED-FLOW LANE ADDITION | 0.7007 | PARTNERSHIP | 2008 | 1132L |  |  |  |  | O
08 | BOND CMIA | 0F161 | RIV | 215 | ADD ONE MIXED FLOW LANE IN EACH DIRECTION | 0.78827 | PARTNERSHIP | 2010 | 9991A |  |  |  |  | O
08 | BOND CMIA | 4440U | SBD | 215 | CONSTRUCT BRIDGES | 2.6923 | STIP | 2008 | 0194Q |  |  |  | X |  | 86545000 | 34532000 | 1800000 | 9931000 | 2585000 | 20216000 | 17034388.8217 | 39.9% | 2009-10-23 | 2013-11-15 | 0 | 0 | 0 | 2.6923 | Local | Local | Caltrans | Caltrans
10 | BOND CMIA | 34042 | TUO | 108 | CONSTRUCT STAGE 2 OF SONORA BYPASS | 14.114 | STIP | 2010 | 0021B |  |  |  | X |  | 38538000 | 14440000 | 120000 | 6000000 | 2820000 | 5500000 | 10740153.58 | 37.47% | 2011-12-16 | 2014-06-30 | 0 | 0 | 1.5731 | 12.5409 | Caltrans | Caltrans | Caltrans | Caltrans
10 | BOND CMIA | 0A870 | STA | 219 | WIDEN AND RESURFACE ROADWAY | 0.12919 | STIP | 2006 | 9940 | [5 empty] | 35844000 | 9736000 | 1648000 | 2828000 | 3260000 | 2000000 | 10338023.06 | 27.16% | 2008-06-19 | 2010-06-30 | 0 | 0 | 0.12919 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
10 | BOND CMIA | 0A872 | STA | 219 | WIDEN TO 4 LANES AND INTERSECTION IMPROVEMENTS | 16.0321 | STIP | 2010 | 9940C | [5 empty] | 43281000 | 9900000 | H | 3100000 | 2500000 | 4300000 | 5741467.14 | 22.87% | 2012-08-30 | 2015-12-31 | 0 | 0 | 0.93811 | 15.094 | Caltrans | Caltrans | Caltrans | Caltrans
10 | BOND CMIA | 0G470 | SJ | 005 | WIDEN BRIDGES AND FREEWAY LANES | 25.8819 | SHOPP | 2010 | 0274 | [5 empty] | 122658000 | 31430000 | 4000000 | 12470000 | 100000 | 14860000 | 7868615.82 | 25.62% | 2011-06-02 | 2015-03-31 | 0 | 0 | 0.22541 | 25.6565 | Local | Local | Caltrans | Caltrans
10 | BOND CMIA | 0Q270 | SJ | 205 | CONSTRUCT ADDITIONAL LANES AND RETAINING WALLS | 1.284 | STIP | 2006 | 1111 |  |  |  | X |  | 27073000 | 8999000 | 1169000 | 4830000 | 100000 | 2900000 | 2614748.29 | 33.24% | 2010-10-12 | 2013-07-31 | 0 | 0 | 0 | 1.284 | Local | Local | Local | Caltrans
11 | BOND CMIA | 25714 | SD | 076 | INTERCHANGE | 5.7579 | STIP | 2012 | 0760A | [5 empty] | 27061000 | 12265000 | 3778000 | 3381000 | 250000 | 4856000 | 3723326.23 | 45.32% | 2012-08-01 | 2014-08-30 | 0 | 0.26911 | 0.49979 | 4.989 | Caltrans | Caltrans | Caltrans | Caltrans
11 | BOND CMIA | 2358U | SD | 005 | CONSTRUCT HOV LANE | 0.0239 | STIP | 2006 | 0701 | [5 empty] | 37937000 | 9386000 | N | 1389000 | 210000 | 7787000 | 11473160.46 | 24.74% | 2007-08-15 | 2010-07-14 | 0 | 0 | 0 | 0.0239 | Caltrans | Caltrans | Caltrans | Caltrans
11 | BOND CMIA | 2T040 | SD | 805 | CONSTRUCT HOV LANES | 10.0195 | STIP | 2008 | 0716 | [5 empty] | 55525000 | 28418000 | 2891000 | 13044000 | 1000000 | 11483000 | 20119048.56 | 51.18% | 2011-01-28 | 2014-08-20 | 0 | 0.00311 | 0.46999 | 9.5464 | Caltrans | Caltrans | Caltrans | Caltrans
11 | BOND CMIA | 2T081 | SD | 015 | CONSTRUCT MANAGED LANES - NORTH | 1.1116 | STIP | 2006 | 0672F | [5 empty] | 58482296 | 19086991 | H | 4869632 | 2122535 | 12094824 | 13621711.459 | 32.64% | 2008-11-20 | 2013-03-29 | 0 | 0 | 0 | 1.1116 | Caltrans | Caltrans | Caltrans | Caltrans
11 | BOND CMIA | 2T082 | SD | 015 | CONSTRUCT MANAGED LANES - NORTH SEGMENT | 0.17319 | STIP | 2006 | 0672F | [5 empty] | 52198000 | 18824715 | H | 6313098 | 1741520 | 10770097 | 16699782.491 | 36.06% | 2008-07-21 | 2012-06-27 | 0 | 0 | 0 | 0.17319 | Caltrans | Caltrans | Caltrans | Caltrans
11 | BOND CMIA | 2T092 | SD | 015 | CONSTRUCT MANAGED LANES - SOUTH SEGMENT | 0.09435 | STIP | 2008 | 0661B | [5 empty] | 97970074 | 28786766 | H | 6880766 | 470000 | 21436000 | 22807515.9372 | 29.38% | 2008-07-25 | 2012-06-14 | 0 | 0 | 0 | 0.09435 | Caltrans | Caltrans | Caltrans | Caltrans
11 | BOND CMIA | 2T095 | SD | 015 | CONSTRUCT DAR AND TRANSIT STATION | 16.1259 | STIP | 2012 | 0672G | [5 empty] | 48800000 | 13232238 | 770238 | 2683000 | 1779000 | 8000000 | 4437027.75 | 27.12% | 2012-04-04 | 2015-06-30 | 0 | 0 | 0.39509 | 15.7308 | Caltrans | Caltrans | Caltrans | Caltrans
11 | BOND CMIA | 2T180 | SD | 805 | EXPRESS LANES | 5.08 | STIP | 2010 | 0730A |  |  |  | X |  | 17837000 | 5477490 | H | 2077490 | C | 3400000 | 6479475.61 | 30.71% | 2012-03-27 | 2013-09-24 | 0 | 0 | 0 | 5.08 | Caltrans | Caltrans | Caltrans | Caltrans
11 | BOND CMIA | 2T181 | SD | 805 | EXPRESS LANES | 11.3018 | STIP | 2010 | 0730B |  |  |  | X |  | 34278000 | 9652914 | H | 4708914 | C | 4944000 | 9575398.19 | 28.16% | 2012-04-27 | 2014-01-26 | 0 | 0 | 0 | 11.3018 | Caltrans | Caltrans | Caltrans | Caltrans
11 | BOND CMIA | 2T200 | SD | 805 | ADD HOV LANES | 33.5509 | STIP | 2010 | 0732A | [5 empty] | 90600000 | 30900000 | H | 2711000 | 2047000 | 26142000 | 2904833.3341 | 34.11% | 2012-03-15 | 2016-03-11 | 0 | 1.3354 | 0.32008 | 31.8955 | Caltrans | Caltrans | Caltrans | Caltrans
12 | BOND CMIA | 07162 | ORA | 022 | WIDEN FREEWAY AND CONSTRUCT BRIDGES | 18.5686 | STIP | 2008 | 2868B | [5 empty] | 137300000 | 31700000 | E | 13500000 | G | 18200000 | 10091716.42 | 23.09% | 2010-06-11 | 2015-01-16 | 0 | 0 | 0.03658 | 18.532 | Caltrans | Local | Local | Caltrans
12 | BOND CMIA | 07163 | ORA | 022 | RECONSTRUCT INTERCHANGE | 24.9319 | STIP | 2010 | 2868C | [5 empty] | 120630000 | 39000000 | E | 14000000 | G | 25000000 | 12265482.66 | 32.33% | 2010-10-12 | 2015-06-07 | 0 | 0 | 0.03342 | 24.8985 | Caltrans | Local | Local | Caltrans
12 | BOND CMIA | 0F031 | ORA | 057 | WIDEN FREEWAY AND BRIDGES | 11.1717 | STIP | 2010 | 3788 |  |  |  | X |  | 33963000 | 17996000 | 572000 | 7475000 | 769000 | 9180000 | 7749948.695 | 52.99% | 2010-10-12 | 2014-02-10 | 0 | 0 | 0.35366 | 10.818 | Local | Local | Caltrans | Caltrans
12 | BOND CMIA | 0F032 | ORA | 057 | WIDEN LANES, RAMPS AND BRIDGES | 10.5179 | STIP | 2010 | 3788A | [5 empty] | 34572000 | 17787000 | 596000 | 7000000 | 1011000 | 9180000 | 8031722.805 | 51.45% | 2010-10-13 | 2014-07-01 | 0 | 0 | 0.50761 | 10.0103 | Local | Local | Caltrans | Caltrans
12 | BOND CMIA | 0F040 | ORA | 057 | ADD NORTHBOUND LANE | 11.3941 | STIP | 2010 | 3829 | [5 empty] | 20985000 | 10693000 | 1328000 | 3528000 | 545000 | 5292000 | 4086657.36 | 50.96% | 2011-10-26 | 2015-03-01 | 0 | 0 | 0.20245 | 11.1916 | Local | Local | Caltrans | Caltrans
12 | BOND CMIA | 0G330 | ORA | 091 | WIDEN FREEWAY AND BRIDGES | 1.2119 | STIP | 2010 | 4598A |  |  |  | X |  | 55253000 | 22257000 | 4649000 | 8825000 | 150000 | 8633000 | 18303369.57 | 40.28% | 2011-05-03 | 2013-09-01 | 0 | 0 | 0.04264 | 1.1692 | Caltrans | Caltrans | Caltrans | Caltrans
12 | BOND CMIA | 0G331 | ORA | 091 | HIGHWAY REPLACEMENT PLANTING | 0.42112 | STIP | 2012 | 4598D | [5 empty] | 1875000 | 623000 | 114000 | 225000 | 40000 | 244000 | 110497.15 | 33.23% | 2013-10-10 | 2017-11-01 | 0 | 0.19709 | 0 | 0.22403 | Caltrans | Caltrans | Caltrans | Caltrans
12 | BOND CMIA | 0M130 | ORA | 405 | WIDEN RAMP FOR DECELERATION LANE | 2.14 | STIP | 2012 | 4981 | [5 empty] | 1910000 | 1320000 | 155000 | 665000 | C | 500000 | 831944.67 | 69.11% | 2012-10-11 | 2014-07-01 | 0 | 0 | 0 | 2.14 | Caltrans | Caltrans | Caltrans | Caltrans
03 | BOND RTE 99 | 37150 | SAC | 099 | CONSTRUCT INTERCHANGE(FULL SQUARE PARTIAL CLOVERLEAF) (DKJ-MMM) | 2.0442 | PARTNERSHIP | 2012 | 0259D |  |  |  |  | O
03 | BOND RTE 99 | 40660 | SUT | 099 | CONSTRUCT INTERCHANGE (TJC- ) | 11.5571 | STIP | 2012 | 3L44 |  |  |  | X |  | 26000000 | 7020000 | 520000 | 2500000 | 500000 | 3500000 | 3472596.62 | 27% | 2012-10-01 | 2014-01-15 | 0 | 0 | 0.25024 | 11.3069 | Local | Caltrans | Caltrans | Caltrans
03 | BOND RTE 99 | 1A432 | SUT | 099 | WIDEN TO FOUR LANES | 8.13 | STIP | 2012 | 8361B | [5 empty] | 44961000 | 12850000 | H | 3600000 | 750000 | 8500000 | 7065530.03 | 28.58% | 2010-07-14 | 2015-12-01 | 0 | 0 | 2.19 | 5.94 | Caltrans | Caltrans | Caltrans | Caltrans
03 | BOND RTE 99 | 1A464 | SUT | 099 | CONSTRUCT 99/113 INTERCHANGE | 8.16 | STIP | 2012 | 8373 | [5 empty] | 15750000 | 3600000 | H | 1000000 | 100000 | 2500000 | 1407922.33 | 22.86% | 2012-10-16 | 2014-12-01 | 0 | 0 | 0.92 | 7.24 | Caltrans | Caltrans | Caltrans | Caltrans
03 | BOND RTE 99 | 3A042 | BUT | 099 | WIDEN ROADWAY AND BRIDGES | 7.27 | STIP | 2010 | 2410B |  |  |  | X |  | 28000000 | 9859000 | H | 5465000 | G | 4394000 | 2023100.64 | 35.21% | 2011-07-08 | 2013-10-15 | 0 | 0 | 0.3 | 6.97 | Local | Local | Local | Caltrans
03 | BOND RTE 99 | 3E390 | SAC | 099 | REALIGN RAMP | 0.30848 | STIP | 2010 | 6908 | [5 empty] | 5521000 | 1925000 | 300000 | 800000 | 75000 | 750000 | 2068134.91 | 34.87% | 2010-06-23 | 2012-10-15 | 0 | 0 | 0.15 | 0.15848 | Caltrans | Caltrans | Caltrans | Caltrans
06 | BOND RTE 99 | 32450 | TUL | 099 | WIDEN ROAD WITH HOT MIX ASPHALT | 22.881 | STIP | 2010 | 6480 | [5 empty] | 78767000 | 23990000 | 2390000 | 8000000 | 600000 | 13000000 | 14999065.81 | 30.46% | 2011-01-04 | 2014-08-01 | 0 | 0 | 0.07206 | 22.8089 | Caltrans | Caltrans | Caltrans | Caltrans
06 | BOND RTE 99 | 32451 | TUL | 099 | REPLACEMENT PLANTING | 0.60496 | STIP | 2012 | 6480Y | [5 empty] | 5000000 | 1200000 | H | 500000 | H | 700000 | 466391.02 | 24% | 2012-10-01 | 2018-08-01 | 0 | 0 | 0 | 0.60496 | Caltrans | Caltrans | Caltrans | Caltrans
06 | BOND RTE 99 | 44261 | FRE | 099 | WIDEN FREEWAY AND BRIDGES | 0.18846 | STIP | 2008 | 6274A | [5 empty] | 17520000 | 5700000 | 500000 | 1500000 | 200000 | 3500000 | 5638503.4057 | 32.53% | 2010-08-10 | 2012-02-03 | 0 | 0 | 0.18002 | 0.00844 | Caltrans | Caltrans | Caltrans | Caltrans
06 | BOND RTE 99 | 44262 | FRE | 099 | WIDEN 4-LANE FWY TO 6-LANE FWY | 12.2737 | STIP | 2012 | 6274 | [5 empty] | 54113000 | 14100000 | 2700000 | 3400000 | 500000 | 7500000 | 7102547.1343 | 26.06% | 2012-10-10 | 2016-07-01 | 0 | 0 | 0.07951 | 12.1942 | Caltrans | Caltrans | Caltrans | Caltrans
06 | BOND RTE 99 | 47100 | MAD | 099 | MODIFY INTERCHANGE | 13.6096 | STIP | 2012 | 5346 | [5 empty] | 69402000 | 14800000 | 2000000 | 4000000 | 2000000 | 6800000 | 9027149.62 | 21.33% | 2012-12-07 | 2015-11-01 | 0 | 0 | 0.14933 | 13.4603 | Caltrans | Caltrans | Caltrans | Caltrans
10 | BOND RTE 99 | 41570 | MER | 099 | 4E TO 6F ON 8F R/W ALIGNMENT | 22.7569 | STIP | 2010 | 5414 | [5 empty] | 150900000 | 25887000 | 4917000 | 6400000 | 2570000 | 12000000 | 12802144.41 | 17.16% | 2012-04-06 | 2015-05-02 | 0 | 0 | 0.70098 | 22.0559 | Caltrans | Caltrans | Caltrans | Caltrans
10 | BOND RTE 99 | 41580 | MER | 099 | 4E TO 6F ON 8F R/W ALIGNMENT | 18.7801 | STIP | 2010 | 5401 | [5 empty] | 101177000 | 17543000 | 3243000 | 5300000 | 700000 | 8300000 | 8277605.29 | 17.34% | 2012-07-12 | 2015-06-20 | 0 | 0 | 0.41959 | 18.3605 | Caltrans | Caltrans | Caltrans | Caltrans
10 | BOND RTE 99 | 0E611 | SJ | 099 | MAINLINE (PHASE 1) | 13.3815 | STIP | 2010 | 7634 | [5 empty] | 31644000 | 10456000 | H | 5456000 | N | 5000000 | 1667809.8339 | 33.04% | 2012-03-27 | 2014-07-01 | 0 | 0 | 0.07904 | 13.3025 | Local | Local | Caltrans | Caltrans
10 | BOND RTE 99 | 0E612 | SJ | 099 | FRENCH CAMP INTERCHANGE (PHASE 2) | 18.4483 | STIP | 2010 | 7634 | [5 empty] | 32953000 | 13497000 | H | 5697000 | 800000 | 7000000 | 1473249.4573 | 40.96% | 2012-06-27 | 2015-04-01 | 0 | 0 | 0.22172 | 18.2266 | Local | Local | Caltrans | Caltrans
10 | BOND RTE 99 | 0E613 | SJ | 099 | LATHROP INTERCHANGE (PHASE 3) | 13.7322 | STIP | 2010 | 7634 | [5 empty] | 47288000 | 16442000 | H | 6757000 | 2185000 | 7500000 | 1973829.3373 | 34.77% | 2012-10-11 | 2015-10-01 | 0 | 0 | 0.43924 | 13.2929 | Local | Local | Caltrans | Caltrans
10 | BOND RTE 99 | 0G440 | MER | 099 | CONSTRUCT A NEW ALIGNMENT | 0.86556 | PARTNERSHIP | 2012 | 5264A
10 | BOND RTE 99 | 3A100 | SJ | 099 | WIDEN TO 6 LANES | 30.5803 | STIP | 2012 | 7668 | [5 empty] | 173928000 | 40530000 | 6030000 | 12000000 | 7000000 | 15500000 | 22893405.37 | 23.3% | 2012-10-16 | 2016-03-05 | 0 | 0 | 2.1838 | 28.3965 | Caltrans | Caltrans | Caltrans | Caltrans
03 | BOND SHOPP AUGMENTATION | 4E110 | ED | 050 | INSTALL DETECTION SYSTEMS | 0.02 | SHOPP | 2006 | 3286 | [5 empty] | 2520000 | 756000 | 30000 | 80000 | 20000 | 626000 | 327899.59 | 30% | 2008-01-24 | 2008-11-13 | 0 | 0 | 0 | 0.02 | Caltrans | Caltrans | Caltrans | Caltrans
03 | BOND SHOPP AUGMENTATION | 0A633 | NEV | 080 | PORTLAND CEMENT CONCRETE OVERLAY | 0.65558 | SHOPP | 2006 | 4257C | [5 empty] | 78000000 | 12500000 | 100000 | 1000000 | 100000 | 11300000 | 6111350.19 | 16.03% | 2008-07-28 | 2012-11-05 | 0 | 0 | 0.01558 | 0.64 | Caltrans | Caltrans | Caltrans | Caltrans
03 | BOND SHOPP AUGMENTATION | 1C12U | SAC | 050 | WIDEN RAMPS WITH HMA OVER AB | 2.7103 | SHOPP | 2008 | 6206 |  |  |  | X |  | 15130000 | 5300000 | 1000000 | 2000000 | 300000 | 2000000 | 3716911.79 | 35.03% | 2011-07-22 | 2013-08-01 | 0 | 0 | 0.10282 | 2.6075 | Caltrans | Caltrans | Caltrans | Caltrans
04 | BOND SHOPP AUGMENTATION | 4A010 | SOL | 080 | CRACK- SEAT AND OVERLAY EXISTING PCC PAVEMENT | 10.8131 | SHOPP | 2010 | 8378B |  |  |  | X |  | 50000000 | 3009000 | 510000 | 1190000 | 204000 | 1105000 | 3227637.27 | 6.018% | 2012-09-26 | 2013-12-01 | 0 | 0.10473 | 0.10226 | 10.6061 | Caltrans | Caltrans | Caltrans | Caltrans
07 | BOND SHOPP AUGMENTATION | 25990 | LA | 710 | PLACE RUBBERIZED HOT MIX ASPHALT | 0.58054 | SHOPP | 2006 | 4005 | [5 empty] | 39000000 | 12000000 | E | 4000000 | 100000 | 7900000 | 9974333.84 | 30.77% | 2008-08-19 | 2011-07-21 | 0 | 0 | 0.00331 | 0.57723 | Caltrans | Caltrans | Caltrans | Caltrans
08 | BOND SHOPP AUGMENTATION | 38434 | SBD | 010 | INSTALL RMS & VDS & WIDEN ON-RAMPS | 5.1965 | SHOPP | 2010 | 0134J |  |  |  | X |  | 19234000 | 5150000 | 1500000 | 1700000 | 50000 | 1900000 | 3275845.7 | 26.78% | 2012-03-26 | 2014-06-12 | 0 | 0 | 0.13689 | 5.0596 | Caltrans | Caltrans | Caltrans | Caltrans
11 | BOND SHOPP AUGMENTATION | 29310 | SD | 078 | EXTEND CONNECTOR RAMP | 0.10013 | SHOPP | 2010 | 0892 | [5 empty] | 3065000 | 2095375 | 546000 | 509375 | 90000 | 950000 | 1704243.31 | 68.36% | 2011-05-05 | 2013-03-22 | 0 | 0 | 0 | 0.10013 | Caltrans | Caltrans | Caltrans | Caltrans
01 | BOND STIP AUGMENTATION | 29030 | HUM | 101 | CONSTRUCT INTERCHANGE AND FRONTAGE ROADS 36/101 | 0.3 | STIP | 2008 | 0050 | [5 empty] | 22260000 | 5919000 | 2290000 | 1003000 | 526000 | 2100000 | 8210472.14 | 26.59% | 2008-10-08 | 2011-02-14 | 0 | 0 | 8.9816e-05 | 0.29991 | Caltrans | Caltrans | Caltrans | Caltrans
02 | BOND STIP AUGMENTATION | 32803 | SHA | 005 | WIDEN HIGHWAY AND RAMPS | 0.96865 | STIP | 2006 | 6650 | [5 empty] | 66057000 | 12886000 | 1228000 | 4458000 | 333000 | 6867000 | 14803799.8933 | 19.51% | 2008-03-05 | 2011-05-31 | 0 | 0 | 0 | 0.96865 | Caltrans | Caltrans | Caltrans | Caltrans
03 | BOND STIP AUGMENTATION | 37200 | SAC | 099 | RECONSTRUCT INTERCHANGE | 0.15385 | PARTNERSHIP | 2006 | 0247J |  |  |  |  | O
03 | BOND STIP AUGMENTATION | 38800 | YOL | 050 | WIDEN CONCRETE BRIDGE | 0.07 | STIP | 2008 | 0332D | [5 empty] | 28012000 | 9875000 | 700000 | 4000000 | 1350000 | 3825000 | 11647555.71 | 35.25% | 2009-05-14 | 2011-08-01 | 0 | 0 | 0.03 | 0.04 | Caltrans | Caltrans | Caltrans | Caltrans
03 | BOND STIP AUGMENTATION | 0E930 | BUT | 070 | WIDEN ROADWAY AND PLACE RUBBERIZED HMA AND HMA TYPE A | 4.5934 | STIP | 2010 | 2273 |  |  |  | X |  | 14600000 | 4800000 | 216000 | 1950000 | 834000 | 1800000 | 3653513.89 | 32.88% | 2011-03-03 | 2013-12-02 | 0 | 0 | 0.42 | 4.1734 | Caltrans | Caltrans | Caltrans | Caltrans
03 | BOND STIP AUGMENTATION | 1A461 | SUT | 099 | CONSTRUCT FOUR LANE EXPRESSWAY | 0.47 | STIP | 2008 | 8362A | [5 empty] | 41400000 | 13446000 | 137000 | 4358000 | 2951000 | 6000000 | 13053770.71 | 32.48% | 2008-07-24 | 2011-08-31 | 0 | 0 | 0.04 | 0.43 | Caltrans | Caltrans | Caltrans | Caltrans
03 | BOND STIP AUGMENTATION | 3A631 | BUT | 070 | WIDEN TO FOUR LANES | 2.51 | STIP | 2008 | 2262A | [5 empty] | 15325000 | 5500000 | E | 2000000 | 1000000 | 2500000 | 6452702.13 | 35.89% | 2009-08-12 | 2012-10-04 | 0 | 0 | 1.58 | 0.93 | Caltrans | Caltrans | Caltrans | Caltrans
04 | BOND STIP AUGMENTATION | 2537A | ALA | 680 | WIDEN FREEWAY, CONSTRUCT AUXILIARY LANES, & INSTALL RAMP METERS | 4.9667 | STIP | 2008 | A0157D |  |  | X |  |  | 3405000 | 1400000 | N | 600000 | C | 800000 | 0 | 41.12% | 2014-10-08 | 2015-11-15 | 0 | 4.6161 | 0.35061 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
04 | BOND STIP AUGMENTATION | 2A472 | SCL | 680 | CONVERT SB HOV LANE ON ROUTE 680 TO COMBINED HOV AND HOT LANE | 1.0601 | PARTNERSHIP | 2006 | 0016O |  |  |  | X
04 | BOND STIP AUGMENTATION | 4A922 | SM | 082 | INSTALL TOS | 0.29688 | PARTNERSHIP | 2010 | 2140F
04 | BOND STIP AUGMENTATION | 4A923 | SM | 082 | INSTALL TOS | 0.07705 | STIP | 2012 | 2140Q | [5 empty] | 10240000 | 3407000 | H | 1847000 | 30000 | 1530000 | 3571021.07 | 33.27% | 2010-09-01 | 2013-04-15 | 0 | 0 | 0.03506 | 0.04199 | Local | Caltrans | Caltrans | Caltrans
05 | BOND STIP AUGMENTATION | 44780 | SB | 101 | RECONSTRUCT TWO INTERCHANGES ADD LANES AND RAMP | 0.00532 | STIP | 2012 | 0478 | [5 empty] | 69382000 | 26342000 | 3000000 | 6610000 | 2200000 | 14532000 | 24376804.34 | 37.97% | 2008-04-02 | 2012-06-22 | 0 | 0 | 0.00347 | 0.00185 | Caltrans | Caltrans | Caltrans | Caltrans
06 | BOND STIP AUGMENTATION | 44253 | KER | 046 | WIDEN ROUTE 46 AND REALIGN ROUTE 33 | 0.08636 | STIP | 2008 | 3386 | [5 empty] | 36505000 | 9525000 | 1525000 | 1910000 | 1790000 | 4300000 | 9744598.0564 | 26.09% | 2009-09-01 | 2011-11-03 | 0 | 0 | 0.08636 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
07 | BOND STIP AUGMENTATION | 11707 | LA | 010 | CONSTRUCT HOV LANES | 1.8371 | STIP | 2008 | 0306H |  |  |  | X |  | 159200000 | 40980000 | 3542000 | 13110000 | 6024000 | 18304000 | 37373834.9 | 25.74% | 2009-04-30 | 2014-02-28 | 0 | 0 | 0.61937 | 1.2178 | Caltrans | Caltrans | Caltrans | Caltrans
09 | BOND STIP AUGMENTATION | 2144U | INY | 395 | WIDEN TO FOUR-LANE EXPRESSWAY | 0.0356 | STIP | 2006 | 0172 | [5 empty] | 47299000 | 26275000 | 4968000 | 6719000 | 3896000 | 10692000 | 14696358.56 | 55.55% | 2008-06-16 | 2010-11-16 | 0 | 0 | 0.0356 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
10 | BOND STIP AUGMENTATION | 2A770 | STA | 099 | RECONSTRUCT INTERCHANGE | 0.52578 | STIP | 2006 | 9401 | [5 empty] | 32399000 | 9577000 | 615000 | 2781000 | 2181000 | 4000000 | 10529515.63 | 29.56% | 2008-06-23 | 2011-06-23 | 0 | 0 | 0.52299 | 0.00279 | Caltrans | Caltrans | Caltrans | Caltrans
11 | BOND STIP AUGMENTATION | 09182 | SD | 905 | CONSTRUCT NEW FREEWAY - PHASE 1A | 1.5146 | STIP | 2006 | 0374K | [5 empty] | 314488000 | 35370000 | 2771000 | 18850000 | 5000000 | 8749000 | 53566443.08 | 11.25% | 2008-01-30 | 2011-06-30 | 0 | 0 | 1.3698 | 0.14484 | Caltrans | Caltrans | Caltrans | Caltrans
11 | BOND STIP AUGMENTATION | 16788 | IMP | 078 | CONSTRUCT FOUR-LANE EXPRESSWAY AND INTERCHANGE - (STAGE 2) | 6.1228 | STIP | 2010 | 0021 | [5 empty] | 96989120 | 35949100 | 5966530 | 10123140 | 8526430 | 11333000 | 29069367.3329 | 37.07% | 2008-03-11 | 2011-06-29 | 0 | 0 | 0.73156 | 5.3912 | Caltrans | Caltrans | Caltrans | Caltrans
11 | BOND STIP AUGMENTATION | 2T000 | SD | 052 | CONSTRUCT FREEWAY AND INTERCHANGE | 0.09754 | STIP | 2008 | 0260F | [5 empty] | 118658000 | 26553000 | H | 4022000 | 5895000 | 16636000 | 26929862.55 | 22.38% | 2008-03-26 | 2011-06-27 | 0 | 0 | 0 | 0.09754 | Caltrans | Caltrans | Caltrans | Caltrans
07 | BOND TRADE CORRIDOR IMPROVEMENTS | 26060 | LA | 110 | WIDENING OF RAMPS AND CONNECTOR | 6.4864 | PARTNERSHIP | 2012 | TC19
08 | BOND TRADE CORRIDOR IMPROVEMENTS | 42230 | SBD | 010 | MODIFY IC & WIDEN RIVERSIDE AVE | 0.47429 | PARTNERSHIP | 2008 | 0146D |  |  |  |  | O
08 | BOND TRADE CORRIDOR IMPROVEMENTS | 46420 | RIV | 074 | RIV 215/74 INTERCHANGE MODIFICATION | 1.4909 | PARTNERSHIP | 2010 | 0054D |  |  |  |  | O
08 | BOND TRADE CORRIDOR IMPROVEMENTS | 46800 | SBD | 010 | RECONSTRUCT IC & WIDEN CHERRY AVE | 6.0691 | PARTNERSHIP | 2004 | 0137K |  |  |  |  | O
08 | BOND TRADE CORRIDOR IMPROVEMENTS | 46810 | SBD | 010 | RECONSTRUCT IC & WIDEN BRIDGE | 3.4097 | PARTNERSHIP | 2008 | 0138G |  |  |  |  | O
10 | BOND TRADE CORRIDOR IMPROVEMENTS | 0S110 | SJ | 004 | EXTEND FREEWAY | 25.7205 | PARTNERSHIP | 2010 | 0284
11 | BOND TRADE CORRIDOR IMPROVEMENTS | 05632 | SD | 011 | CONSTRUCT FREEWAY TO FREEWAY CONNECTORS | 26.81 | STIP | 2010 | 1000 | [5 empty] | 98700000 | 18800000 | N | 7300000 | 2100000 | 9400000 | 7456558.355 | 19.05% | 2013-09-30 | 2016-03-30 | 0 | 5.11 | 3.34 | 18.36 | Caltrans | Caltrans | Caltrans | Caltrans
11 | BOND TRADE CORRIDOR IMPROVEMENTS | 28880 | SD | 905 | CONSTRUCT NEW FREEWAY - PHASE 1B | 1.8389 | STIP | 2010 | 0703 |  |  |  | X |  | 186705000 | 12300000 | H | 399000 | C | 11901000 | 12981189.23 | 6.588% | 2009-05-08 | 2013-12-31 | 0 | 0 | 0 | 1.8389 | Caltrans | Caltrans | Caltrans | Caltrans
11 | BOND TRADE CORRIDOR IMPROVEMENTS | 29770 | SD | 005 | GRADE SEPARATION IMPROVEMENTS | 0.05054 | STIP | 2010 | TC70 | [5 empty] | 54290000 | 12910000 | 2150000 | 3760000 | C | 7000000 | 832548.8 | 23.78% | - - | 2014-07-07 | 0 | 0.05054 | 0 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
11 | BOND TRADE CORRIDOR IMPROVEMENTS | 2976U | SD | 005 | AT-GRADE IMPROVEMENTS | 0.06591 | STIP | 2010 | TC69 |  |  |  | X |  | 3963000 | 2497000 | 971000 | 864000 | 15000 | 647000 | 1671484.82 | 63.01% | 2012-06-21 | 2013-11-26 | 0 | 0 | 0 | 0.06591 | Caltrans | Caltrans | Caltrans | Caltrans
06 | HIGH SPEED RAIL | 2HT10 | MER | 099 | HIGH SPEED RAIL | 31.2464 | PARTNERSHIP
01 | PARTNERSHIP | 43730 | HUM | 036 | REALIGNMENT AND WIDENING AT BUCK MOUNTAIN | 0.6 | PARTNERSHIP | 2012 | 2272 |  |  |  | X
01 | PARTNERSHIP | 0A760 | MEN | 101 | PEER REVIEW @ TALMAGE ROAD | 0.35 | PARTNERSHIP
01 | PARTNERSHIP | 0B130 | DN | 101 | HMA LEVELING | 0.87 | PARTNERSHIP | [5 empty] | X
02 | PARTNERSHIP | 34760 | SHA | 005 | RECONSTRUCT INTERCHANGE | 0.27044 | PARTNERSHIP | 2012 | 3488 |  |  |  |  | O
02 | PARTNERSHIP | 37960 | SHA | 005 | LOCAL CAPITAL OVERSIGHT OASIS | 3.0743 | PARTNERSHIP
02 | PARTNERSHIP | 1E970 | TEH | 005 | MODIFY INTERSECTION | 4.3 | PARTNERSHIP
03 | PARTNERSHIP | 33382 | PLA | 065 | CONSTRUCT SOUTHBOUND LANES | 8.0373 | PARTNERSHIP | 2012 | 4895 |  |  |  | X
03 | PARTNERSHIP | 36880 | BUT | 099 | WIDEN OC & REV RAMPS | 0.33276 | PARTNERSHIP
03 | PARTNERSHIP | 36930 | YOL | 005 | REVISE INTERCHANGE (MSF-BDC) | 0.18447 | PARTNERSHIP
03 | PARTNERSHIP | 37000 | ED | 050 | REVISE INTERCHANGE (MSF-NLB) | 0.17727 | PARTNERSHIP | 2006 | 3L19 |  |  |  |  | O
03 | PARTNERSHIP | 37611 | YUB | 070 | CONSTRUCT NEW INTERCHANGE | 0.92983 | PARTNERSHIP | 2012 | 0366D
03 | PARTNERSHIP | 42550 | SAC | 005 | CONSTRUCT INTERCHANGE (MSF-NLB) | 0.33773 | PARTNERSHIP |  |  |  |  | X
03 | PARTNERSHIP | 44166 | SAC | 050 | IMPROVE, ENHANCE, AND ESTABLISH | 0.58 | PARTNERSHIP | [6 empty] | O
03 | PARTNERSHIP | 3E010 | YUB | 070 | NEW HIGHWAY CONSTRUCTION | 1.4579 | PARTNERSHIP
03 | PARTNERSHIP | 1E090 | BUT | 162 | SEISMIC RETROFIT INSTL HINGE RESTRAINERS, SEAT EXT | 8 | PARTNERSHIP | [5 empty] | X
03 | PARTNERSHIP | 4E140 | PLA | 080 | WIDEN EASTBOUND RAMPS | 0.22 | PARTNERSHIP
03 | PARTNERSHIP | 3E210 | SUT | 020 | NEW SIGNALIZED PUBLIC RD CONNECTION | 0.36 | PARTNERSHIP
03 | PARTNERSHIP | 3E260 | NEV | 089 | CONSTRUCT ROUNDABOUTS | 0.1225 | PARTNERSHIP
03 | PARTNERSHIP | 1E270 | SAC | 050 | CONSTRUCT NEW INTERCHANGE | 1.1988 | PARTNERSHIP
03 | PARTNERSHIP | 1E290 | ED | 050 | SILVA VALLEY PARKWAY | 4.0151 | PARTNERSHIP | 2012 | 3302 |  |  |  |  | O
03 | PARTNERSHIP | 0E620 | PLA | 065 | CONSTRUCT NEW BRIDGE AND OVERHEAD PHASE 2, SOUTH HALF, BR #19-0179R | 0.04357 | PARTNERSHIP
03 | PARTNERSHIP | 0E960 | ED | 049 | REALIGN AND REDESIGNATE ROADWAY | 1.3148 | PARTNERSHIP | 2012 | 3163
03 | PARTNERSHIP | 0F110 | SUT | 099 | EXPAND PARK AND RIDE FACILITY | 0.40214 | PARTNERSHIP
03 | PARTNERSHIP | 0F120 | BUT | 099 | RECONSTRUCT INTERCHANGE IN PHASES | 1.04 | PARTNERSHIP
03 | PARTNERSHIP | 1A340 | SAC | 099 | RECONSTRUCT INTERCHANGE | 0.09489 | PARTNERSHIP
03 | PARTNERSHIP | 1E330 | ED | 050 | DEVELOP PSR FOR MULTI-MODAL TRANSP & COMMUNITY ENHANCEMENTS | 2.5129 | PARTNERSHIP
03 | PARTNERSHIP | 1E410 | SAC | 099 | CONSTRUCT NEW NORTHBOUND ON-RAMP | 0.74448 | PARTNERSHIP | [6 empty] | O
03 | PARTNERSHIP | 1F180 | SAC | 005 | ADD AUXILIARY LANE | 0.60845 | PARTNERSHIP
03 | PARTNERSHIP | 1F580 | PLA | 089 | CONSTRUCT SIGNALIZED INTERSECTION | 1.013 | PARTNERSHIP
03 | PARTNERSHIP | 2A820 | PLA | 065 | CONSTRUCT INTERCHANGE | 0.11069 | PARTNERSHIP
03 | PARTNERSHIP | 2C590 | PLA | 065 | CONSTRUCT NEW INTERCHANGE | 0.54701 | PARTNERSHIP |  |  |  |  | X
03 | PARTNERSHIP | 2E480 | ED | 049 | CONSTRUCT BIKE LANES | 1.23 | PARTNERSHIP | 2006 | 3120C |  |  |  |  | O
03 | PARTNERSHIP | 2E540 | ED | 050 | UPGRADE INTERCHANGE | 0.04668 | PARTNERSHIP
03 | PARTNERSHIP | 2E550 | ED | 050 | UPGRADE INTERCHANGE | 0.6624 | PARTNERSHIP |  |  |  |  | X
03 | PARTNERSHIP | 2E560 | ED | 050 | UPGRADE INTERCHANGE | 0.50986 | PARTNERSHIP
03 | PARTNERSHIP | 2F160 | SAC | 160 | RE-ALIGN ROUTE | 7.3581 | PARTNERSHIP | [6 empty] | O
03 | PARTNERSHIP | 2F930 | SAC | 099 | CONSTRUCT NEW PEDESTRIAN OC | 0.4794 | PARTNERSHIP
03 | PARTNERSHIP | 2F940 | SAC | 099 | INTERCHANGE MODIFICATION | 0.72806 | PARTNERSHIP
03 | PARTNERSHIP | 2F950 | PLA | 089 | CONSTRUCT NEW CLASS 1 BICYCLE PATH | 0.8238 | PARTNERSHIP |  |  |  |  | X
03 | PARTNERSHIP | 3A712 | ED | 050 | CONSTRUCT HOV LANES BY ADDING ADDITIONAL LANES IN THE MEDIAN | 1.58 | PARTNERSHIP | 2012 | 3283B
03 | PARTNERSHIP | 3C000 | SAC | 005 | CONST HOV LANES | 0.1 | PARTNERSHIP
03 | PARTNERSHIP | 3C001 | SAC | 005 | CONST HOV LANES | 5.9609 | PARTNERSHIP | 2012 | 5835
03 | PARTNERSHIP | 3F120 | COL | 020 | PUBLIC ROAD CONNECTION | 0.9 | PARTNERSHIP
03 | PARTNERSHIP | 3F280 | YUB | 070 | PASSING LANES AT VARIOUS LOCATIONS | 0.5 | PARTNERSHIP | [6 empty] | O
03 | PARTNERSHIP | 3F360 | SAC | 050 | BUS/CARPOOL LANE ADDITIONS | 6.5007 | PARTNERSHIP
03 | PARTNERSHIP | 3F370 | SUT | 099 | BRIDGE RAIL REPLACEMENT | 0.65 | PARTNERSHIP | [6 empty] | O
03 | PARTNERSHIP | 3F600 | SAC | 050 | WORK ON LOCAL ROAD UNDER BRIGHTON OVERHEAD | 0.7 | PARTNERSHIP
03 | PARTNERSHIP | 4A190 | NEV | 080 | OVERSIGHT DESIGN AG STATION | 0.04836 | PARTNERSHIP
03 | PARTNERSHIP | 4C440 | SAC | 080 | CONSTRUCT PEDESTRIAN OVERCROSSING | 0.15369 | PARTNERSHIP
03 | PARTNERSHIP | 4C480 | YOL | 016 | IMPROVE SIX AT-GRADE INTERSECTIONS | 0.10295 | PARTNERSHIP
03 | PARTNERSHIP | 4E840 | SAC | 005 | MODIFY RAMPS AND SIGNALS, MAKE IMPROVEMENTS ON ACCESS STREETS | 0.39738 | PARTNERSHIP
04 | PARTNERSHIP | 15148 | ALA | 880 | TO INSTALL RAMP METERS & TRAFFIC OPERATIONS SYSTEMS (TOS) | 6.5777 | PARTNERSHIP |  |  | X
04 | PARTNERSHIP | 15160 | MRN | 101 | INSTALL RAMP METERING | 12.1681 | PARTNERSHIP |  |  | X
04 | PARTNERSHIP | 15271 | CC | 004 | REPAIR EXISTING RAMP METERS | 0.06073 | PARTNERSHIP
04 | PARTNERSHIP | 15272 | CC | 004 | INSTALL RAMP METERS AND TOS ELEMENT WIDEN ON-RAMPS TO PROVIDE HOV | 2.0631 | PARTNERSHIP |  |  |  | X | X
04 | PARTNERSHIP | 15330 | SCL | 101 | INSTALL RAMP METERING & TRAFFIC OPERATION SYSTEMS. | 10.0789 | PARTNERSHIP
04 | PARTNERSHIP | 22857 | CC | 680 | LANDSCAPING | 1.6142 | PARTNERSHIP | 2004 | 0274H |  |  |  |  | O
04 | PARTNERSHIP | 23552 | SM | 092 | INTERCHANGE IMPROVEMENT | 2.1983 | PARTNERSHIP |  |  | X
04 | PARTNERSHIP | 24545 | SON | 101 | CONNECT & IMPROVE 6TH STREET FROM DAVIS TO MORGAN STREET | 0.09378 | PARTNERSHIP | 2010 | 5156K
04 | PARTNERSHIP | 26470 | SCL | 101 | MODIFY INTERCHANGE | 1.3993 | PARTNERSHIP | [6 empty] | O
04 | PARTNERSHIP | 26560 | SM | 001 | REPLACE 2-LANE BRIDGE | 4.9011 | PARTNERSHIP | 2012 | 2140H |  |  |  |  | O
04 | PARTNERSHIP | 27282 | SM | 101 | MODIFY SOUTHBOUND RAMPS AT ROUTE 101/UNIVERSITY AVENUE & WIDEN UNIV | 2.0228 | PARTNERSHIP | [6 empty] | O
04 | PARTNERSHIP | 27830 | ALA | 185 | HIGHWAY BEAUTIFICATION | 1.9829 | PARTNERSHIP | [6 empty] | O
04 | PARTNERSHIP | 29762 | ALA | 084 | EXPRESSWAY WIDENING | 2.21 | PARTNERSHIP | 2012 | 0081H
04 | PARTNERSHIP | 44800 | ALA | 185 | MODIFICATION OF CONVENTIONAL HWY | 3.3603 | PARTNERSHIP
04 | PARTNERSHIP | 0A080 | CC | 080 | RECONSTRUCT THE INTERCHANGE TO IMPROVE OVERALL TRAFFIC OPERATIONS | 6.5448 | PARTNERSHIP | [6 empty] | O
04 | PARTNERSHIP | 0A185 | SON | 101 | RECONSTRUCT OLD REDWOOD HIGHWAY INTERCHANGE | 9.6117 | PARTNERSHIP | 2012 | 0775H
04 | PARTNERSHIP | 0A18A | SON | 101 | FOLLOW UP LANDSCAPING PROJECT | 2.7481 | PARTNERSHIP
04 | PARTNERSHIP | 0A310 | ALA | 680 | CNSTRUCT & MODIFY I-680/BERNAL AVE INTERCHANGE | 1.0087 | PARTNERSHIP | [6 empty] | O
04 | PARTNERSHIP | 0A350 | SCL | 152 | CONSTRUCT TWO AT-GRADE INTERSECTION AND WIDEN THE SHOULDERS FOR THE | 2.5001 | PARTNERSHIP | [6 empty] | O
04 | PARTNERSHIP | 0A632 | SON | 116 | WIDENING AND NEW SIGNAL INSTALLATION (PHASE 2) | 2.1587 | PARTNERSHIP
04 | PARTNERSHIP | 0A660 | SM | 101 | DESIGN & CONSTRUCT BIKE/PEDESTRIAN PATH AND BIKE/PEDESTRIAN | 3.7772 | PARTNERSHIP | [6 empty] | O
04 | PARTNERSHIP | 0A850 | ALA | 880 | CONSTRUCT AUTOMATED GUIDEWAY TRANSI T CONNECTING BART COLISUEM TO | 7.5396 | PARTNERSHIP | [6 empty] | O
04 | PARTNERSHIP | 0G090 | ALA | 680 | SAN FRANCISCO PUBLIC UTILITIES COMMISSION (SFPUC)-WATER SYSTEM | 3.6565 | PARTNERSHIP | [6 empty] | O
04 | PARTNERSHIP | 0G200 | ALA | 080 | CONSTRUCT BICYCLE-PEDESTRIAN OVERCROSSING | 2.293 | PARTNERSHIP
04 | PARTNERSHIP | 0G251 | SF | 080 | NEW BUS RAMPS TO/FROM THE NEW TERMINAL TO I-80 AND BUS STORAGE | 4.9409 | PARTNERSHIP | [6 empty] | O
04 | PARTNERSHIP | 0G252 | SF | 080 | NEW BUS STORAGE FACILITY UNDER I-80 | 6.9597 | PARTNERSHIP | [6 empty] | O
04 | PARTNERSHIP | 0G253 | SF | 080 | PHASE 2 OF TRASBAY CENTER PROGRAM, EXTENDING CALTRAIN LINE TO NEW | 0.15737 | PARTNERSHIP
04 | PARTNERSHIP | 0G340 | SCL | 085 | CONSTRUCT POC SUPERSTRUCTURE & BENT IN THE MEDIAN. MODIFY CONCRETE | 0.45352 | PARTNERSHIP | [6 empty] | O
04 | PARTNERSHIP | 0G350 | SF | 001 | CONSTRUCT BUS AND PEDESTRIAN BUL-OUT IMPROVEMENTS | 3.8663 | PARTNERSHIP
04 | PARTNERSHIP | 0G390 | CC | 680 | CONSTRUCT AN ADDITIONAL LANE ALONG NB DIAGONAL OFF-RAMP AND NB | 3.3311 | PARTNERSHIP | [6 empty] | O
04 | PARTNERSHIP | 0T043 | MRN | 101 | OFF SITE MITIGATION WETLANDS | 0.05397 | PARTNERSHIP
04 | PARTNERSHIP | 1A100 | SM | 001 | CONSTRUCT NORTHBOUND AND SOUTHBOUND OFF RAMP | 1.6179 | PARTNERSHIP
04 | PARTNERSHIP | 1A421 | SON | 116 | SIGNALIZATION OF THE INTERSECTION OF ROUTE 116 & MIRABEL ROAD | 4.3406 | PARTNERSHIP | [6 empty] | O
04 | PARTNERSHIP | 1A510 | SCL | 280 | CONSTRUCT MARY AVE PEDESTRIAN OC (BICYCLE BRIDGE) ACROSS INTERSTATE | 0.18438 | PARTNERSHIP | [6 empty] | O
04 | PARTNERSHIP | 1A660 | MRN | 101 | IMPROVE 101/SIR FRANCIS DRAKE BLVD AND TAMALPAIS DR INTERCHANGES | 6.3939 | PARTNERSHIP | [6 empty] | O
04 | PARTNERSHIP | 1A710 | SCL | 101 | CONSTRUCT PEDESTRIAN / BICYCLE OVERCROSSING | 0.45236 | PARTNERSHIP | [6 empty] | O
04 | PARTNERSHIP | 1A910 | CC | 004 | RAMP RELOCATION | 1.4442 | PARTNERSHIP | [6 empty] | O
04 | PARTNERSHIP | 1G090 | ALA | 580 | MODIFY ON & OFF RAMPS AT THE I-580 SAN RAMON RD OVERCROSSING | 1.5817 | PARTNERSHIP | [6 empty] | O
04 | PARTNERSHIP | 1G340 | SF | 080 | CONSTRUCT TUNNEL AND OPEN PORTAL TUNNEL UNDER I-80 | 1.6756 | PARTNERSHIP
04 | PARTNERSHIP | 1G970 | SCL | 880 | CITY OF MILPITAS REQUEST FOR CALTRANS TO PROVIDE REIMBURSED R/W | 0.03387 | PARTNERSHIP
04 | PARTNERSHIP | 1G990 | ALA | 580 | CONSTRUCT NEW ROADWAY TO CONNECT DIRECTLY FROM STROBRIDGE AVE WB OFF | 1.1389 | PARTNERSHIP | [6 empty] | O
04 | PARTNERSHIP | 2285A | CC | 004 | LANDSCAPING | 3.8497 | PARTNERSHIP | 2008 | 0192J
04 | PARTNERSHIP | 2285G | CC | 680 | LANDSCAPE | 1.1791 | PARTNERSHIP
04 | PARTNERSHIP | 2285H | CC | 680 | ADD AUXILIARY LANES IN BOTH DIRECTIONS | 14.1703 | PARTNERSHIP
04 | PARTNERSHIP | 2332H | SCL | 237 | WETLAND MITIGATION MONITORING IN SANTA CLARA ADJACENT TO RTE 237 | 0.209 | PARTNERSHIP
04 | PARTNERSHIP | 2356A | SM | 101 | REPLACEMENT LANDSCAPING | 1.5041 | PARTNERSHIP | 2008 | 0658D
04 | PARTNERSHIP | 2640F | SON | 101 | CONSTRUCT HOV LANES INCLUDING SOUND WALLS, BRIDGES, MEDIAN AND RAMP | 3.3635 | PARTNERSHIP |  |  |  |  | X
04 | PARTNERSHIP | 2640G | MRN | 101 | WIDEN BRIDGE AND HMA ROADWAY | 3.4985 | PARTNERSHIP | 2010 | 0360M |  |  |  | X
04 | PARTNERSHIP | 2640L | MRN | 101 | CONSTRUCT NORTHBOUND HOV LANE | 9.7408 | PARTNERSHIP | 2010 | 0360S |  |  |  | X
04 | PARTNERSHIP | 2640N | SON | 101 | WIDEN NB & SB HOV LANES FROM MRN/ SON COUNTY LINE TO PETALUMA BLVD. | 2.8105 | PARTNERSHIP
04 | PARTNERSHIP | 2A170 | CC | 004 | WIDEN HIGHWAY | 9.5195 | PARTNERSHIP | [6 empty] | O
04 | PARTNERSHIP | 2A200 | SCL | 237 | CONSTRUCT RAPID TRANSIT SYSTEM BART EXTENSION | 1.9276 | PARTNERSHIP | [6 empty] | O
04 | PARTNERSHIP | 2A400 | ALA | 185 | BUS RAPID TRANSIT | 2.5306 | PARTNERSHIP
04 | PARTNERSHIP | 2G000 | ALA | 185 | INSTALL ADDITIONAL LEFT-TURN LANE ON SB E-14 STREET AND EB HESPERIAN | 0.81421 | PARTNERSHIP
04 | PARTNERSHIP | 2G310 | SON | 101 | INSTALL RAMP METERING AND TRAFFIC OPERATIONS SYSTEMS ELEMENTS | 13.2736 | PARTNERSHIP |  |  | X |  | X
04 | PARTNERSHIP | 2G362 | ALA | 092 | REPLACEMENT PLANTING ANG IRRIGATION | 1.2915 | PARTNERSHIP |  |  |  | X | X
04 | PARTNERSHIP | 2G490 | ALA | 580 | HOV CONVERSION TO HOT LANE | 3.9152 | PARTNERSHIP
04 | PARTNERSHIP | 2G510 | CC | 004 | CONSTRUCT SR-4/BYPASS ROAD DIRECT CONNECTOR | 3.8903 | PARTNERSHIP |  |  |  |  | X
04 | PARTNERSHIP | 2G710 | SCL | 101 | CONVERT HIGH OCCUPANCY VEHICLE TO EXPRESS LANES | 5.9409 | PARTNERSHIP | [6 empty] | O
04 | PARTNERSHIP | 3A160 | SCL | 101 | WIDENING OF SR 101 | 1.6192 | PARTNERSHIP | [6 empty] | O
04 | PARTNERSHIP | 3A270 | SF | 101 | CONSTRUCT RAPID TRANSIT BUSLANES ON VAN NESS AVE | 1.0306 | PARTNERSHIP
04 | PARTNERSHIP | 3A410 | SCL | 085 | CONSTRUCT ON RAMP AND OFF RAMP AND ELIMINATE NB LEFT TURN LANE | 1.7604 | PARTNERSHIP | [6 empty] | O
04 | PARTNERSHIP | 3A511 | ALA | 024 | BART SEISMIC RETROFIC - SEGMENT 1 (FIVE CONSTRUCTION CONTRACTS) | 0.06635 | PARTNERSHIP
04 | PARTNERSHIP | 3A512 | SF | 280 | BART SEISMIC RETROFIT - OUTSIDE OF SEGMENT 1 (SEVEN CONSTRUCTION | 0.24476 | PARTNERSHIP | [6 empty] | O
04 | PARTNERSHIP | 3A580 | CC | 680 | SB HOV LANE GAP CLOSURE | 2.4829 | PARTNERSHIP
04 | PARTNERSHIP | 3A620 | CC | 004 | CONSTRUCT TRANSIT HUB AND PARK AND RIDE LOT | 2.1141 | PARTNERSHIP | [6 empty] | O
04 | PARTNERSHIP | 3A640 | SF | 080 | MODIFY EXISTING INTERCHANGE EXIT AND ENTRANCE RAMPS | 2.2901 | PARTNERSHIP
04 | PARTNERSHIP | 3A860 | CC | 680 | DIRECT HOV RAMPS AT NORRIS CANYON ROAD | 1.1994 | PARTNERSHIP
04 | PARTNERSHIP | 3G790 | SM | 101 | CONSTRUCT NB 101 OFF-RAMP IMPROVEME NT | 1.2211 | PARTNERSHIP
04 | PARTNERSHIP | 3G800 | SM | 101 | CONSTRUCT NB 101 OFF-RAMP IMPROVEME NT | 1.5046 | PARTNERSHIP
04 | PARTNERSHIP | 3G810 | SM | 101 | CONSTRUCT NB 101 OFF-RAMP IMPROVEME NT | 0.53302 | PARTNERSHIP
04 | PARTNERSHIP | 4396A | SCL | 087 | LANDSCAPE PLANT ESTABLISHMENT | 0.42931 | PARTNERSHIP
04 | PARTNERSHIP | 4A020 | CC | 080 | PREPARATION OF AGREEMENT & OVERSIGH FOR DESIGN & CONSTRUCTION OF | 3.4104 | PARTNERSHIP
04 | PARTNERSHIP | 4A441 | SOL | 080 | IMPROVE THE FRONTAGE ROADS. IMPROVE I-80/REDWOOD PARKWAY & RTE 37/FAIR | 5.6548 | PARTNERSHIP
04 | PARTNERSHIP | 4A924 | SM | 082 | PROCURE HARDWARE AND SOFTWARE | 0.43777 | PARTNERSHIP | 2010 | 2140R
04 | PARTNERSHIP | 4A930 | CC | 004 | CONSTRUCT EBART EXTENSION | 4.7698 | PARTNERSHIP
04 | PARTNERSHIP | 4A990 | SCL | 082 | CONSTRUCT NEW PEDESTRIAN AND BICYCLIST OVERCROSSING | 0.19064 | PARTNERSHIP | [6 empty] | O
04 | PARTNERSHIP | 4G080 | SOL | 080 | CONVERT EXISTING HOV LANE TO EXPRES LANE PM11.2/20.1 & CONST NEW EXPRE | 2.2132 | PARTNERSHIP
04 | PARTNERSHIP | 4G110 | SCL | 101 | IMPROVING TOS BY INSTALLING RAMP METERING EQUIPMENTS AND WIDENING | 3.3182 | PARTNERSHIP
04 | PARTNERSHIP | 4G120 | SCL | 017 | IMPROVE TRAFFIC OPERATIONS SYSTEMS (TOS),INSTALL RAMP METERING EQUIP.& | 0.62217 | PARTNERSHIP |  |  |  |  | X
04 | PARTNERSHIP | 4G130 | SCL | 101 | IMPROVE TRAFFIC OPERATIONS (TOS) | 0.5759 | PARTNERSHIP |  |  |  |  | X
04 | PARTNERSHIP | 4G190 | ALA | 580 | INSTALL RAMP METERING AND TOS ELEMENTS | 3.0594 | PARTNERSHIP |  |  | X
04 | PARTNERSHIP | 4G320 | SOL | 080 | SHOULDER IMPROVEMENT, RECONSTRUCT SIGNAL INTERSECTION, CONSTRUCT NEW | 2.2745 | PARTNERSHIP | [6 empty] | O
04 | PARTNERSHIP | 4G690 | SCL | 017 | MODIFY LANE CONFIGURATION UNDER SPA MAIN SPAN BETWEEN EXITING INTERIOR | 0.08629 | PARTNERSHIP | [6 empty] | O
04 | PARTNERSHIP | 4H130 | SCL | 101 | CONSTRUCT PEDESTRIAN / BICYCLE OVERCROSSING | 0.04167 | PARTNERSHIP
04 | PARTNERSHIP | 4H150 | SM | 082 | CONSTRUCT CROSSWALKS, SIDEWALK, CURB RAMPS AND LANDSCAPING | 0.9398 | PARTNERSHIP |  |  |  |  | X
04 | PARTNERSHIP | 4H160 | CC | 004 | CONSTRUCT A GRADE SEPARATED BALFOUR ROAD INTERCHANGE | 2.5097 | PARTNERSHIP | [6 empty] | O
05 | PARTNERSHIP | 44782 | SB | 101 | BIKE/PED IMPROVEMENTS AT RR STRUCTURE | 0.06682 | PARTNERSHIP | 2008 | 0478A
05 | PARTNERSHIP | 46580 | SCR | 001 | INTERSECTION IMPROVEMENTS | 0.64873 | PARTNERSHIP | 2012 | 4658
05 | PARTNERSHIP | 0A370 | SLO | 101 | INTERCHANGE AND RAMP MODIFICATIONS | 1.2976 | PARTNERSHIP | [6 empty] | O
05 | PARTNERSHIP | 0G840 | SB | 101 | OPERATIONAL IMPROVEMENTS TO EXISTING INTERCHANGE | 0.95565 | PARTNERSHIP | [6 empty] | O
05 | PARTNERSHIP | 0H310 | SB | 101 | NEW INTERCHANGE | 0.26352 | PARTNERSHIP | [6 empty] | O
05 | PARTNERSHIP | 0K650 | SLO | 001 | REALIGN I/C AND NEW BRIDGE | 0.88092 | PARTNERSHIP
05 | PARTNERSHIP | 0P160 | MON | 101 | NEW INTERCHANGE | 1.2087 | PARTNERSHIP
05 | PARTNERSHIP | 1C530 | MON | 156 | CONSTRUCT PEDESTRIAN/BICYCLE PATH AT UPRR CROSSING W OF CASTROVILLE | 0.16628 | PARTNERSHIP |  |  |  |  | X
05 | PARTNERSHIP | 1F290 | SB | 166 | INTERSECTION IMPROVEMENTS | 0.68783 | PARTNERSHIP | [6 empty] | O
05 | PARTNERSHIP | 1F300 | SB | 166 | INTERSECTION IMPROVEMENTS | 0.68783 | PARTNERSHIP | [6 empty] | O
06 | PARTNERSHIP | 33220 | TUL | 099 | MODIFY INTERCHANGE (DSF) | 2.8134 | PARTNERSHIP | [5 empty] | X
06 | PARTNERSHIP | 43960 | TUL | 198 | WIDEN OC AND SIGNALIZE OFF-RAMP | 0.0206 | PARTNERSHIP
06 | PARTNERSHIP | 46380 | FRE | 180 | ADD PASSING LANES | 2.5166 | PARTNERSHIP
06 | PARTNERSHIP | 48450 | KER | 099 | EXTENSION AND CONNECTION TO RTE 204 | 4.9126 | PARTNERSHIP
06 | PARTNERSHIP | 48460 | KER | 058 | CONSTRUCT 6/8 LANE FREEWAY | 13.8363 | PARTNERSHIP | 2012 | 3705
06 | PARTNERSHIP | 48470 | KER | 178 | WIDEN 24TH ST (SR 178) BY ONE LANE EACH DIRECTION | 2.0347 | PARTNERSHIP
06 | PARTNERSHIP | 49390 | KER | 178 | INTERSECTION IMPROVEMENTS AND WIDENING OF 24TH ST (SR 178) | 2.2639 | PARTNERSHIP |  |  |  |  | X
06 | PARTNERSHIP | 0A350 | MAD | 041 | INTERSECTION WIDENING/IMPROVEMENT | 0.63936 | PARTNERSHIP |  |  | X
06 | PARTNERSHIP | 0C930 | KER | 099 | CONSTRUCT NEW INTERCHANGE | 1.0084 | PARTNERSHIP
06 | PARTNERSHIP | 0C940 | KER | 178 | CONSTRUCT NEW INTERCHANGE | 2.4439 | PARTNERSHIP
06 | PARTNERSHIP | 0F350 | KER | 178 | HIGHWAY WIDENING | 1.7643 | PARTNERSHIP |  |  |  |  | X
06 | PARTNERSHIP | 0F360 | KER | 058 | WIDEN TO 4 OR 6 LANES | 3.2742 | PARTNERSHIP |  |  |  |  | X
06 | PARTNERSHIP | 0G850 | KER | 058 | WIDEN FREEWAY FROM 4 TO 6 LANES | 2.3659 | PARTNERSHIP
06 | PARTNERSHIP | 0G860 | KER | 119 | WIDEN W/B SR 119 TO 3 LANES | 0.34618 | PARTNERSHIP | [6 empty] | O
06 | PARTNERSHIP | 0G900 | MAD | 041 | CONSTRUCT PASSING LANES | 2.1366 | PARTNERSHIP | 2012 | 6606 |  | X | X
06 | PARTNERSHIP | 0G920 | KER | 099 | MODIFY INTERCHANGE | 0.03947 | PARTNERSHIP
06 | PARTNERSHIP | 0H360 | FRE | 099 | NEW INTERCHANGE | 5.8931 | PARTNERSHIP
06 | PARTNERSHIP | 0J170 | FRE | 041 | RECONSTRUCT INTERCHANGE | 0.0143 | PARTNERSHIP
06 | PARTNERSHIP | 0L030 | FRE | 099 | OVERSIGHT - REMOVE OFF-RAMP AND INTERSECTION IMPROVEMENTS | 0.20605 | PARTNERSHIP | [5 empty] | X
06 | PARTNERSHIP | 0N490 | KER | 099 | CONSTRUCT SB AUX LANE AND WIDEN OLIVE DRIVE OFF-RAMP | 0.21126 | PARTNERSHIP | [5 empty] | X
06 | PARTNERSHIP | 0P670 | TUL | 245 | WOODLAKE ROUNDABOUT OVERSIGHT | 0.5894 | PARTNERSHIP
06 | PARTNERSHIP | 0Q210 | FRE | 180 | FREEWAY LANDSCAPING | 2.0144 | PARTNERSHIP |  |  |  |  | X
07 | PARTNERSHIP | 00343 | VEN | 101 | RECONSTRUCT IC | 0.39842 | PARTNERSHIP | 2010 | 3430 |  |  |  |  | O
07 | PARTNERSHIP | 12038 | VEN | 101 | MODIFY INTERCHANGE | 1.4827 | PARTNERSHIP | [6 empty] | O
07 | PARTNERSHIP | 16860 | LA | 014 | MODIFY INTERCHANGE | 0.69741 | PARTNERSHIP
07 | PARTNERSHIP | 18701 | LA | 005 | RECONSTRUCT RTE 5/126 INTERCHANGE *POR/187000*OVERSIGHT ONLY*PHASE-2 | 0.73434 | PARTNERSHIP
07 | PARTNERSHIP | 18702 | LA | 126 | REALIGN, WIDEN MAGIC MNTN PKWY | 1.7258 | PARTNERSHIP |  |  |  |  | X
07 | PARTNERSHIP | 18722 | LA | 126 | IC IMPROVEMENT | 3.1852 | PARTNERSHIP
07 | PARTNERSHIP | 19320 | LA | 005 | IMPRV IC AND OC *OVERSIGHT | 0.06618 | PARTNERSHIP
07 | PARTNERSHIP | 19580 | VEN | 034 | WIDEN FROM 2 TO 4 LANES | 0.59183 | PARTNERSHIP
07 | PARTNERSHIP | 20190 | LA | 101 | WIDEN STREET | 3.0811 | PARTNERSHIP |  |  | X
07 | PARTNERSHIP | 20320 | LA | 010 | ADDING NEW LANE *OVERSIGHT ONLY; MTA FUND; LADOT | 0.41411 | PARTNERSHIP
07 | PARTNERSHIP | 20551 | LA | 002 | REPLACE FLASHING BEACONS, RETROFIT | 0.32449 | PARTNERSHIP | [5 empty] | X
07 | PARTNERSHIP | 20552 | LA | 002 | LANDSCAPE AND CONST SOUNDWALLS | 3.6234 | PARTNERSHIP |  |  |  | X | X
07 | PARTNERSHIP | 22050 | LA | 001 | ROADWAY WIDENING OS/02/03/09 DESIGN COOP AGRE | 1.6853 | PARTNERSHIP
07 | PARTNERSHIP | 22410 | LA | 060 | CONSTRUCT INTERCHANGE | 4.1251 | PARTNERSHIP |  |  |  |  | X
07 | PARTNERSHIP | 22450 | LA | 210 | CONSTRUCT SOUND WALL | 0.03541 | PARTNERSHIP
07 | PARTNERSHIP | 22460 | LA | 405 | CONSTRUCTION OF SOUNDWALL | 3.2551 | PARTNERSHIP
07 | PARTNERSHIP | 22610 | LA | 710 | SEISMIC RETROFIT PROJECT | 0.27944 | PARTNERSHIP
07 | PARTNERSHIP | 23280 | LA | 170 | CONSTRUCTION OF SOUND WALL | 2.993 | PARTNERSHIP
07 | PARTNERSHIP | 23290 | LA | 210 | CONSTRUCTION OF SOUNDWALL | 0.21789 | PARTNERSHIP |  |  |  | X | X
07 | PARTNERSHIP | 23310 | LA | 605 | CONSTRUCTION OF SOUNDWALL | 3.3386 | PARTNERSHIP
07 | PARTNERSHIP | 23380 | LA | 110 | FAIR OAKS AVE IC IMPROVEMENTS | 0.66015 | PARTNERSHIP
07 | PARTNERSHIP | 23390 | LA | 405 | MODIFY INTERCHANGE | 1.1857 | PARTNERSHIP | [6 empty] | O
07 | PARTNERSHIP | 23400 | LA | 405 | MODIFY INTERCHANGE | 2.0699 | PARTNERSHIP
07 | PARTNERSHIP | 23640 | LA | 710 | HIGHWAY PLANTING RESTORATION | 1.8585 | PARTNERSHIP
07 | PARTNERSHIP | 23750 | LA | 005 | WIDEN HYPERION OVERCROSSING | 1.0018 | PARTNERSHIP |  |  |  |  | X
07 | PARTNERSHIP | 23850 | LA | 047 | ALAMEDA CORRIDOR TRUCK EXPRESSWAY | 4.7511 | PARTNERSHIP
07 | PARTNERSHIP | 24080 | LA | 014 | MODIFY INTERCHANGE | 1.3946 | PARTNERSHIP |  |  |  |  | X
07 | PARTNERSHIP | 24230 | LA | 101 | IMPROVE INTERCHANGE | 2.1468 | PARTNERSHIP |  |  |  |  | X
07 | PARTNERSHIP | 24560 | LA | 010 | BRIDGE WIDENING | 1.0222 | PARTNERSHIP
07 | PARTNERSHIP | 25060 | LA | 210 | CONST. SOUNDWALL WITH MASONRY BLOCK *CONSTRUCTION BY METRO | 0.50095 | PARTNERSHIP
07 | PARTNERSHIP | 25120 | LA | 101 | STRUCTURE REPLACEMENT *100% LOCAL FUNDS; OVERSIGHT EFFORT | 1.477 | PARTNERSHIP
07 | PARTNERSHIP | 25510 | LA | 060 | CONTRUCT ON-RAMPS | 1.0068 | PARTNERSHIP |  |  |  |  | X
07 | PARTNERSHIP | 25720 | LA | 101 | MODIFY INTERCHANGE | 1.6671 | PARTNERSHIP
07 | PARTNERSHIP | 25810 | LA | 101 | ROAD WIDENING (PHASE 1) | 1.2496 | PARTNERSHIP
07 | PARTNERSHIP | 26020 | LA | 405 | CONSTRUCTION OF SOUNDWALL | 1.5149 | PARTNERSHIP
07 | PARTNERSHIP | 26030 | LA | 134 | CONSTRUCTION OF SOUNDWALL | 3.641 | PARTNERSHIP
07 | PARTNERSHIP | 26480 | LA | 110 | REPLACE INTERCHANGE & INTERSECTIONS *100% OVERSIGHT | 6.1093 | PARTNERSHIP | 2010 | TC20
07 | PARTNERSHIP | 26510 | LA | 138 | WIDENING TO 6-LANE *NO FUNDING | 32.39 | PARTNERSHIP
07 | PARTNERSHIP | 27280 | LA | 010 | LIGHT RAIL TRANSIT | 1.2769 | PARTNERSHIP |  |  | X |  | X
07 | PARTNERSHIP | 27290 | LA | 060 | CONSTRUCT RETAINING WALLS * OVERSIGHT PROJECT | 0.04443 | PARTNERSHIP
07 | PARTNERSHIP | 27300 | LA | 710 | REPLACE BRIDGE *O/S, INACTIVE | 0.69213 | PARTNERSHIP |  |  | X
07 | PARTNERSHIP | 27440 | LA | 010 | HIGH OCCUPANCY TOLL LANES | 4.3401 | PARTNERSHIP | 2010 | 4135
07 | PARTNERSHIP | 27640 | LA | 405 | LIGHT RAIL TRANSIT | 2.4801 | PARTNERSHIP
07 | PARTNERSHIP | 27800 | LA | 110 | CONSTRUCT AN HOV CONNECTOR | 7.743 | PARTNERSHIP |  |  | X
07 | PARTNERSHIP | 27860 | LA | 210 | SOUNDWALL CONSTRUCTION | 1.5008 | PARTNERSHIP
07 | PARTNERSHIP | 27870 | LA | 710 | RAMP MODIFICATION | 1.602 | PARTNERSHIP | [6 empty] | O
07 | PARTNERSHIP | 27910 | LA | 057 | ADD WB AUXILIARY LANE/OC/RAMP/CONN | 5.6962 | PARTNERSHIP
07 | PARTNERSHIP | 27920 | VEN | 023 | CONSTRUCT SOUNDWALL | 1.1015 | PARTNERSHIP
07 | PARTNERSHIP | 28160 | VEN | 118 | ROAD WIDENING | 0.80782 | PARTNERSHIP |  |  | X |  | X
07 | PARTNERSHIP | 28490 | LA | 118 | WIDENING OFF-RAMP | 0.4599 | PARTNERSHIP |  |  | X | X | X
07 | PARTNERSHIP | 28510 | LA | 010 | CONSTRUCT NEW BUSWAY STATION | 1.8348 | PARTNERSHIP | [6 empty] | O
07 | PARTNERSHIP | 28540 | LA | 187 | LIGHT RAIL TRANSIT | 3.75 | PARTNERSHIP
07 | PARTNERSHIP | 28570 | LA | 405 | HEAVY RAIL TRANSIT, HRT | 0.46604 | PARTNERSHIP
07 | PARTNERSHIP | 28780 | LA | 001 | REMOVAL/RECONSTRUCTION OF OC *ENCROACHMENT PERMIT APPLICATION | 0.57002 | PARTNERSHIP |  |  | X
07 | PARTNERSHIP | 29020 | LA | 060 | CONSTRUCT LIGHT RAIL TRANSIT | 5.23 | PARTNERSHIP
07 | PARTNERSHIP | 29360 | LA | 405 | WIDEN AND IMPROVEMENT ON/OFF RAMP | 6.4757 | PARTNERSHIP
07 | PARTNERSHIP | 29370 | LA | 110 | CONSTRUCT AN AUXILIARY LANE | 4.4147 | PARTNERSHIP
07 | PARTNERSHIP | 29380 | LA | 001 | RAMP/ARTERIAL SIGNALILIZED INTERSEC | 3 | PARTNERSHIP |  |  | X | X | X
07 | PARTNERSHIP | 29400 | LA | 210 | LIGHT RAIL TRANSIT | 1.7589 | PARTNERSHIP |  |  |  |  | X
07 | PARTNERSHIP | 29420 | LA | 014 | WIDEN NORTHBOUND OFF-RAMP | 0.31209 | PARTNERSHIP
07 | PARTNERSHIP | 29760 | LA | 027 | STREET IMPROVEMENT | 2.58 | PARTNERSHIP | [6 empty] | O
07 | PARTNERSHIP | 29800 | LA | 710 | SOUND WALL | 1.9586 | PARTNERSHIP | [6 empty] | O
07 | PARTNERSHIP | 29810 | LA | 091 | ADD ONE LANE ON MAIN LINE | 0.17702 | PARTNERSHIP | [6 empty] | O
07 | PARTNERSHIP | 29820 | LA | 605 | WIDEN BY ADDING ONE LANE | 3.9131 | PARTNERSHIP | [6 empty] | O
07 | PARTNERSHIP | 1952U | VEN | 101 | INTERCHANGE IMPROVEMENT | 24.0787 | PARTNERSHIP | 2012 | 2291
07 | PARTNERSHIP | 1965U | LA | 101 | IMPROVE INTERCHANGE | 0.09513 | PARTNERSHIP
07 | PARTNERSHIP | 2332E | LA | 005 | CONSTRUCT HOV AND TRUCK LANE | 36.0509 | PARTNERSHIP
07 | PARTNERSHIP | 2382U | LA | 110 | LIGHT RAIL TRANSIT CROSSINGS | 0.08561 | PARTNERSHIP
07 | PARTNERSHIP | 2600U | LA | 138 | CONSTRUCTION OF FREEWAY/EXPRESSWAY | 31.9857 | PARTNERSHIP | 2012 | 0393F
07 | PARTNERSHIP | 4U449 | LA | 014 | HIGHWAY PLANTING *OVERSIGHT ONLY | 0.28035 | PARTNERSHIP | 2012 | 4098 |  |  | X
08 | PARTNERSHIP | 0E140 | RIV | 015 | CONSTRUCT NEW INTERCHANGE | 1.082 | PARTNERSHIP
08 | PARTNERSHIP | 0E150 | RIV | 015 | INTERCHANGE IMPROVEMENTS | 1.3268 | PARTNERSHIP
08 | PARTNERSHIP | 32300 | RIV | 060 | RECONSTRUCT & REALIGN RAMPS W/AUX LANE & WIDEN NASON ST | 0.1769 | PARTNERSHIP | [6 empty] | O
08 | PARTNERSHIP | 32301 | RIV | 060 | INTERCHANGE MODIFICATIONS PHASE 1 | 0.86714 | PARTNERSHIP | [6 empty] | O
08 | PARTNERSHIP | 32302 | RIV | 060 | REPLACE NASON ST OC | 1.0359 | PARTNERSHIP | 2010 | 1143 |  |  |  |  | O
08 | PARTNERSHIP | 32750 | RIV | 015 | CONSTRUCT IC | 0.10165 | PARTNERSHIP | [6 empty] | O
08 | PARTNERSHIP | 32780 | RIV | 215 | RECONSTRUCT INTERCHANGE | 0.5979 | PARTNERSHIP | [6 empty] | O
08 | PARTNERSHIP | 32781 | RIV | 215 | UPGRADE LANDSCAPING & IRRIGATION SYSTEM | 0.037066 | PARTNERSHIP
08 | PARTNERSHIP | 32840 | RIV | 091 | WIDEN BRIDGE | 0.53526 | PARTNERSHIP | [6 empty] | O
08 | PARTNERSHIP | 33471 | RIV | 010 | CONSTRUCT GRADE-SEPARATION UNDER- PASS FOR UPRR. | 0.45907 | PARTNERSHIP
08 | PARTNERSHIP | 34090 | SBD | 010 | CONSTRUCT INTERCHANGE (URBAN) | 3.215 | PARTNERSHIP | [6 empty] | O
08 | PARTNERSHIP | 34141 | RIV | 060 | CONSTRUCT OVERCROSSING (PHASE 1) | 4.2688 | PARTNERSHIP
08 | PARTNERSHIP | 34142 | RIV | 060 | CONSTRUCT RAMPS (PHASE 2) | 0.465 | PARTNERSHIP |  |  |  |  | X
08 | PARTNERSHIP | 34143 | RIV | 060 | CONSTRUCT DECELERATIION AND ACCELERATION LANE, INSTALL CONCRETE | 0.050474 | PARTNERSHIP
08 | PARTNERSHIP | 40830 | SBD | 010 | MODIFY INTERCHANGE | 0.90831 | PARTNERSHIP
08 | PARTNERSHIP | 40931 | SBD | 010 | INSTALL LANDSCAPING & IRRIGATION | 0.08463 | PARTNERSHIP | [6 empty] | O
08 | PARTNERSHIP | 43230 | RIV | 015 | INTERCHANGE IMPROVEMENTS | 5.9218 | PARTNERSHIP | [6 empty] | O
08 | PARTNERSHIP | 43271 | RIV | 015 | CONSTRUCT NEW IC | 1.5119 | PARTNERSHIP | [5 empty] | X
08 | PARTNERSHIP | 44324 | SBD | 210 | CONSTRUCT OVERCROSSINGS | 0.051828 | PARTNERSHIP
08 | PARTNERSHIP | 44360 | SBD | 210 | CONST 6 LANE FREEWAY & 2 HOV LNS | 0.026332 | PARTNERSHIP
08 | PARTNERSHIP | 44394 | SBD | 210 | CONSTRUCT INTERCHANGE | 2.7645 | PARTNERSHIP
08 | PARTNERSHIP | 44811 | SBD | 010 | CONSTRUCT EB AUX LANE, EB OFF RAMP, RETAINING WALLS EB, TEA 21 DEMO PR | 0.42946 | PARTNERSHIP | 2012 | 0154D
08 | PARTNERSHIP | 45210 | RIV | 010 | CONST NEW INTERCHANGE | 1.2815 | PARTNERSHIP | [6 empty] | O
08 | PARTNERSHIP | 45220 | RIV | 015 | CONSTRUCT NEW RAMP AND WIDEN BRIDGE | 0.064445 | PARTNERSHIP
08 | PARTNERSHIP | 46350 | RIV | 060 | BRIDGE DECKING; RECONFIGURE RAMPS; SIGNALS | 0.0065183 | PARTNERSHIP | [6 empty] | O
08 | PARTNERSHIP | 46411 | RIV | 074 | ADD 2 LANES (SEGMENT 2) | 0.36713 | PARTNERSHIP
08 | PARTNERSHIP | 46412 | RIV | 074 | ADD 2 LANES (SEGMENT 1) | 0.04723 | PARTNERSHIP
08 | PARTNERSHIP | 46461 | RIV | 079 | WIDEN TO 4-LANE HIGHWAY | 0.35669 | PARTNERSHIP
08 | PARTNERSHIP | 46462 | RIV | 079 | WIDEN TO 4-LANE HIGHWAY | 1.2822 | PARTNERSHIP
08 | PARTNERSHIP | 49400 | RIV | 079 | REALIGNMENT OF SR-79 | 1.6201 | PARTNERSHIP | [6 empty] | O
08 | PARTNERSHIP | 49710 | SBD | 015 | IMPROVE IC, WIDEN BASELINE ROAD TO 6 LANES, WIDEN RAMPS & INSTALL | 1.6285 | PARTNERSHIP | 2010 | 0168J
08 | PARTNERSHIP | 0071H | SBD | 066 | REPLACE LANDSCAPE & IRRIGATION | 0.82317 | PARTNERSHIP |  |  |  |  | X
08 | PARTNERSHIP | 0071J | SBD | 215 | REPLACE LANDSCAPE AND IRRIGATION | 1.6663 | PARTNERSHIP |  |  |  |  | X
08 | PARTNERSHIP | 0071K | SBD | 215 | REPLACE LANDSCAPE AND IRRIGATION | 0.24294 | PARTNERSHIP |  |  |  | X
08 | PARTNERSHIP | 0071L | SBD | 215 | REPLACE LANDSCAPE AND IRRIGATION | 1.0129 | PARTNERSHIP
08 | PARTNERSHIP | 0A020 | RIV | 215 | RECONSTRUCT INTERCHANGE | 0.76026 | PARTNERSHIP | [6 empty] | O
08 | PARTNERSHIP | 0A440 | RIV | 015 | RECONSTRUCT IC, AUX LN, WIDEN RAMP | 1.3823 | PARTNERSHIP
08 | PARTNERSHIP | 0C700 | SBD | 210 | CONSTRUCT MF LANE IN EACH DIRECTION & WIDEN UNDERCROSSINGS | 1.2415 | PARTNERSHIP | [6 empty] | O
08 | PARTNERSHIP | 0E420 | SBD | 215 | CONSTRUCT RAMP, WIDEN OVERCROSSSING RECONFIGURE S/B ENTRANCE RAMP | 1.9106 | PARTNERSHIP | [6 empty] | O
08 | PARTNERSHIP | 0E450 | RIV | 015 | IC IMPROVEMENT | 0.28706 | PARTNERSHIP | 2010 | 0021N |  |  |  |  | O
08 | PARTNERSHIP | 0E520 | RIV | 215 | INTERCHANGE IMPROVEMENT | 3.3077 | PARTNERSHIP | 2010 | 0041C |  |  |  |  | O
08 | PARTNERSHIP | 0F050 | RIV | 010 | RECONSTRUCT RAMPS AT INTERCHANGE | 2.0036 | PARTNERSHIP | [6 empty] | O
08 | PARTNERSHIP | 0F120 | RIV | 010 | CONSTRUCT NEW IC | 2.6836 | PARTNERSHIP
08 | PARTNERSHIP | 0F163 | RIV | 215 | ADD LANE TO S/B CONNECTOR AT MURRIETA HOT SPRINGS RD | 2.7871 | PARTNERSHIP
08 | PARTNERSHIP | 0F320 | RIV | 999 | CONSTRUCT SIX-LANE FREEWAY | 0.87321 | PARTNERSHIP | [6 empty] | O
08 | PARTNERSHIP | 0F540 | RIV | 091 | CONSTRUCT ONE MIXED FLOW LANE | 41.5938 | PARTNERSHIP | 2012 | 0077J |  |  |  |  | O
08 | PARTNERSHIP | 0F580 | RIV | 015 | WIDEN AND EXPAND OC & I/C | 0.39956 | PARTNERSHIP | [6 empty] | O
08 | PARTNERSHIP | 0F630 | SBD | 395 | WIDEN HIGHWAY TO 4 LANES WITH 2 WAY LEFT TURN LANE | 11.7102 | PARTNERSHIP
08 | PARTNERSHIP | 0G930 | SBD | 062 | WIDENING AND REALIGNMENT | 1.9096 | PARTNERSHIP | [6 empty] | O
08 | PARTNERSHIP | 0G980 | RIV | 215 | WIDEN RAMP & BRIDGE | 0.31583 | PARTNERSHIP
08 | PARTNERSHIP | 0H130 | SBD | 015 | CONSTRUCT NEW INTERCHANGE AT I-15 | 2.4675 | PARTNERSHIP | 2010 | 0168Q |  |  |  |  | O
08 | PARTNERSHIP | 0H380 | RIV | 015 | OVERCROSSING REPLACEMENT FROM 2 LANES TO 4LANES | 1.9953 | PARTNERSHIP | 2012 | 0019N |  |  |  |  | O
08 | PARTNERSHIP | 0J080 | RIV | 015 | ADD ONE HOV LANE AND ONE MIXED- FLOW LANE AND INSTALL MEDIAN | 7.8021 | PARTNERSHIP
08 | PARTNERSHIP | 0J120 | SBD | 010 | CONSTRUCT INTERCHANGE | 1.0324 | PARTNERSHIP
08 | PARTNERSHIP | 0J400 | SBD | 010 | CONSTRUCT PARTIAL CLOVERLEAF AT GROVE AVENUE | 0.5215 | PARTNERSHIP
08 | PARTNERSHIP | 0J440 | RIV | 215 | WIDEN NEWPORT RD OC, RECONSRUCT THE INTERCHANGE RAMPS | 2.9804 | PARTNERSHIP | [6 empty] | O
08 | PARTNERSHIP | 0J610 | RIV | 015 | RECONSTRUCT EXISTING IC, REPLACE OC AND REALIGN CAJALCO ROAD | 1.579 | PARTNERSHIP
08 | PARTNERSHIP | 0K400 | RIV | 079 | IMPROVEMENTS ON RTE 79 | 0.46121 | PARTNERSHIP | [6 empty] | O
08 | PARTNERSHIP | 0K520 | SBD | 015 | CONSTRUCT MASTER PLANNED STORM DRAIN FACILITY | 2 | PARTNERSHIP | [6 empty] | O
08 | PARTNERSHIP | 0L100 | SBD | 395 | INSTALL TRAFFIC SIGNALS SIDEWALKS AND DRIVEWAYS | 0.64472 | PARTNERSHIP
08 | PARTNERSHIP | 0L190 | RIV | 079 | MODIFY INTERSECTION TO A FOUR LEGGED SIGNALIZED INTERSECTION | 0.5383 | PARTNERSHIP
08 | PARTNERSHIP | 0L690 | SBD | 062 | ROADWAY WIDENING, RAISED MEDIAN ISLANDS, SIDE WALK, STREET LIGHTING | 0.66979 | PARTNERSHIP
08 | PARTNERSHIP | 0L840 | RIV | 215 | ENHANCE LANDSCAPE | 0.02041 | PARTNERSHIP
08 | PARTNERSHIP | 0M470 | RIV | 215 | INSTALL LANDSCAPE & IRRIGATION SYSTEM | 0.27536 | PARTNERSHIP
08 | PARTNERSHIP | 0M630 | SBD | 215 | INSTALL RAMP METERS | 2.0229 | PARTNERSHIP
08 | PARTNERSHIP | 0M900 | RIV | 111 | CONSTRUCT SINGLE OVERHEAD BRIDGE STRUCTURE | 0.075112 | PARTNERSHIP
08 | PARTNERSHIP | 0N360 | RIV | 074 | WIDEN SOUTH SIDE OF SR-74 TO 8'SHLD REALIGN CALVERT AV TO MEET SR-74 | 0.093458 | PARTNERSHIP
08 | PARTNERSHIP | 0N580 | SBD | 018 | REALIGN AND EXPAND INTERSECTION | 0.70322 | PARTNERSHIP
08 | PARTNERSHIP | 0N600 | RIV | 010 | INSTALL/REPLACE LANDSCAPING, IRRIGATION SYSTEM & ROCK BLANKET | 0.046567 | PARTNERSHIP
08 | PARTNERSHIP | 0N750 | RIV | 010 | IMPROVEMENTS ON INTERCHANGE - STREAMLINED OVERSIGHT PERMIT JOB | 0.012374 | PARTNERSHIP
08 | PARTNERSHIP | 0N890 | RIV | 215 | EXTEND LANE NUMBER 4 | 0.06687 | PARTNERSHIP | [6 empty] | O
08 | PARTNERSHIP | 0P300 | SBD | 215 | CONSTRUCT PARK AND RIDE FACILITY | 0.31009 | PARTNERSHIP
08 | PARTNERSHIP | 0P760 | SBD | 066 | INTERCHANGE IMPROVEMENTS | 0.77563 | PARTNERSHIP |  |  |  | X
08 | PARTNERSHIP | 0Q160 | SBD | 062 | IMPROVEMENT ON INTERCHANGE - OVERSIGHT ONLY | 0.40293 | PARTNERSHIP |  |  |  | X | X
08 | PARTNERSHIP | 0Q320 | SBD | 210 | WIDEN TO 6 LANES | 1.1807 | PARTNERSHIP
08 | PARTNERSHIP | 0Q530 | RIV | 015 | INTERCHANGE IMPROVEMENTS | 0.89234 | PARTNERSHIP |  |  |  | X | X
08 | PARTNERSHIP | 0Q580 | SBD | 010 | INSTALL/REPLACE LANDSCAPING. INSTALL/UPGRADE IRRIGATION SYSTEM | 0.15097 | PARTNERSHIP
08 | PARTNERSHIP | 0Q640 | RIV | 091 | CONSTRUCT EMBANKMENT & MAINTENANCE ROAD AND EXTEND CULVERT. | 0.1609 | PARTNERSHIP
08 | PARTNERSHIP | 0Q670 | RIV | 215 | WIDEN RAMPS. INSTALL/MODIFY SIGNALS CONSTRUCT DRAINAGE SYSTEMS. | 0.24535 | PARTNERSHIP
08 | PARTNERSHIP | 0Q970 | SBD | 018 | HWY WIDENING, MEDIAN ADDITIONS AND TRAFFIC SIGNALS | 0.23397 | PARTNERSHIP
08 | PARTNERSHIP | 0R250 | RIV | 010 | CONSTRUCT ON/OFF RAMPS (ENCROACHMENT PERMIT) | 0.057417 | PARTNERSHIP
08 | PARTNERSHIP | 1A450 | SBD | 015 | CONSTRUCT NEW INTERCHANGE | 1.3075 | PARTNERSHIP
08 | PARTNERSHIP | 1A830 | SBD | 010 | MODIFY IC & WIDEN CEDAR AVE | 6.0994 | PARTNERSHIP
08 | PARTNERSHIP | 4430U | SBD | 210 | CONSTRUCT 6-LANE FWY & 2 HOV LANES; INSTALL CCTV, VDS, RMS & CMS | 0.051527 | PARTNERSHIP | 2000 | 0193R
08 | PARTNERSHIP | 4431U | SBD | 210 | CONSTRUCT 6-LANE FWY & 2 HOV LANES; INSTALL CCTV, VDS & RMS | 0.043896 | PARTNERSHIP | 2000 | 0193Q
08 | PARTNERSHIP | 4437L | SBD | 210 | HIGHWAY LANDSCAPING | 0.83202 | PARTNERSHIP | 2008 | 4434G
08 | PARTNERSHIP | 4438L | SBD | 210 | PROVIDE HIGHWAY LANDSCAPING | 0.4197 | PARTNERSHIP | 2010 | 4434H
08 | PARTNERSHIP | 4439L | SBD | 210 | HIGHWAY LANDSCAPING | 0.5208 | PARTNERSHIP | 2010 | 4434J
08 | PARTNERSHIP | 4440L | SBD | 210 | HIGHWAY LANDSCAPING | 1.1186 | PARTNERSHIP
09 | PARTNERSHIP | 30320 | MNO | 203 | OVERSIGHT FOR PLANNING | 0.16774 | PARTNERSHIP
10 | PARTNERSHIP | 47210 | STA | 099 | MODIFY INTERCHANGE. | 2.8417 | PARTNERSHIP | 2012 | 9460
10 | PARTNERSHIP | 0H880 | SJ | 205 | OVERSIGHT CONSTRUCT NEW I/C AT PARDISE CUT BRIDGE. | 4.1306 | PARTNERSHIP
10 | PARTNERSHIP | 0H890 | SJ | 120 | OVERSIGHT TO CONSTRUCT NEW INTER- CHANGE | 2.6069 | PARTNERSHIP
10 | PARTNERSHIP | 0H910 | SJ | 205 | OVERSIGHT TO CONST NEW IC | 1.3824 | PARTNERSHIP |  |  |  | X | X
10 | PARTNERSHIP | 0L320 | STA | 099 | RECONSTRUCT INTERCHANGE | 2.7642 | PARTNERSHIP
10 | PARTNERSHIP | 0L330 | STA | 099 | RECONSTRUCT INTERCHANGE | 2.3142 | PARTNERSHIP | 2012 | 9463 |  |  |  |  | O
10 | PARTNERSHIP | 0P200 | SJ | 120 | INTERCHANGE UPGRADE | 1.1035 | PARTNERSHIP
10 | PARTNERSHIP | 0P650 | SJ | 120 | OVERSIGHT OVER INTERCHANGE MODIFICATIONS | 1.32 | PARTNERSHIP
10 | PARTNERSHIP | 0P730 | SJ | 099 | OVERSIGHT OF INTERCHANGE MODIFICATIONS | 0.72448 | PARTNERSHIP
10 | PARTNERSHIP | 0P740 | MER | 059 | OVERSIGHT OF NEW INTERSECTION CONSTRUCTION | 0.56109 | PARTNERSHIP
10 | PARTNERSHIP | 0Q880 | AMA | 049 | INTERSECTION IMPROVEMENTS | 1.6415 | PARTNERSHIP
10 | PARTNERSHIP | 0T630 | SJ | 088 | SIGNALIZE AND IMPROVE INTERSECTIONS | 0.54186 | PARTNERSHIP
10 | PARTNERSHIP | 0T730 | CAL | 012 | INTERSECTION IMPROVEMENTS | 0.92424 | PARTNERSHIP
10 | PARTNERSHIP | 0W350 | MER | 140 | CONSTRUCT ROUNDABOUT | 0.27 | PARTNERSHIP
10 | PARTNERSHIP | 1A690 | STA | 099 | RECONSTRUCT INTERCHANGE | 5.1576 | PARTNERSHIP
10 | PARTNERSHIP | 2A780 | SJ | 132 | CONSTRUCT NEW INTERCHANGE | 8.9516 | PARTNERSHIP
11 | PARTNERSHIP | 2E000 | SD | 999 | SD CNTY PROSPECTIVE MITIGAT. SITES | 0.22064 | PARTNERSHIP
11 | PARTNERSHIP | 2E002 | SD | 005 | IN SAN DIEGO COUNTY IN CARLSBAD PURCHASE AND RESTORE MITIGATION PAR | 0.483 | PARTNERSHIP
11 | PARTNERSHIP | 2E003 | SD | 005 | IN SAN DIEGO COUNTY IN DEL MAR PURCHASE AND RESTORE MITIGATION | 0.64162 | PARTNERSHIP
11 | PARTNERSHIP | 07890 | SD | 005 | MODIFY INTERCHANGE/CONST AUX LANE/ CONST DIRECT CONNECTORS | 16.472 | PARTNERSHIP
11 | PARTNERSHIP | 08010 | SD | 076 | CONSTRUCT FOUR LANE HIGHWAY | 1.7259 | PARTNERSHIP | [5 empty] | X
11 | PARTNERSHIP | 08017 | SD | 076 | PLANT ESTABLISHMENT EA | 1.3243 | PARTNERSHIP |  |  |  | X | X
11 | PARTNERSHIP | 08578 | SD | 163 | REVISE INTERCHANGE/WIDEN OC AND APPROACH | 4.4866 | PARTNERSHIP | [6 empty] | O
11 | PARTNERSHIP | 08975 | SD | 805 | INTERCHANGE IMPROVEMENTS & ROAD WIDENING | 0.24565 | PARTNERSHIP
11 | PARTNERSHIP | 17370 | SD | 805 | REVISE INTERCHANGE | 2.594 | PARTNERSHIP
11 | PARTNERSHIP | 17790 | SD | 005 | CONSTRUCT DIRECT FREEWAY TO FREEWAY CONNECTORS | 3.8388 | PARTNERSHIP |  |  | X
11 | PARTNERSHIP | 2E004 | SD | L5515 | MITIGATION SITE PRESERVATION | 0.31325 | PARTNERSHIP
11 | PARTNERSHIP | 23230 | SD | 125 | CONST 4-LANE HWY W/ PROVISIONS FOR HOV LANES & TEMPORARY CONNECTION | 0.71615 | PARTNERSHIP
11 | PARTNERSHIP | 24151 | SD | 163 | INTERCHANGE RECONFIGURATION FOR TRAFFIC HANDLING IMPROVEMENTS | 7.2773 | PARTNERSHIP
11 | PARTNERSHIP | 24640 | SD | 067 | MODIFY EXISTING INTERCHANGE | 1.9512 | PARTNERSHIP |  |  |  |  | X
11 | PARTNERSHIP | 25715 | SD | 076 | CONSTRUCT 4 LANE HIGHWAY | 20.9629 | PARTNERSHIP |  |  |  | X | X
11 | PARTNERSHIP | 25980 | SD | 078 | REPLACE NORDAHL BRIDGE & WIDEN OFF RAMP:CT PROVIDE 100% OVERSIGHT | 1.2269 | PARTNERSHIP | [5 empty] | X
11 | PARTNERSHIP | 26071 | SD | 015 | HIGHWAY PLANTING AND IRRIGATION | 0.26212 | PARTNERSHIP
11 | PARTNERSHIP | 26072 | SD | 015 | INSTALL PLANTING AND WATER SYSTEM. FOR HWY STAGES 2 & 3 | 0.48693 | PARTNERSHIP
11 | PARTNERSHIP | 26073 | SD | 015 | INSTALL HIGHWAY PLANTING SYSTEMS | 0.53883 | PARTNERSHIP
11 | PARTNERSHIP | 26340 | SD | 005 | ENCINITAS BLVD I/C IMPROVEMENT | 1.877 | PARTNERSHIP
11 | PARTNERSHIP | 26390 | SD | 805 | REVISE INTERCHANGE | 0.86513 | PARTNERSHIP
11 | PARTNERSHIP | 26411 | SD | 163 | SEISMIC RETROFIT | 18.7057 | PARTNERSHIP
11 | PARTNERSHIP | 27150 | SD | 005 | RECONSTRUCT INTERCHANGE | 1.5761 | PARTNERSHIP
11 | PARTNERSHIP | 27921 | SD | 076 | MITIGATION SITE PRESERVATION | 0.10483 | PARTNERSHIP
11 | PARTNERSHIP | 27924 | SD | 076 | MITIGATION SITE PRESERVATION | 0.0672 | PARTNERSHIP
11 | PARTNERSHIP | 27928 | SD | 076 | MITIGATION SITE PRESERVATION | 0.01581 | PARTNERSHIP
11 | PARTNERSHIP | 28720 | SD | 078 | CONSTRUCT NEW STRUCTURE | 0.13172 | PARTNERSHIP
11 | PARTNERSHIP | 28870 | IMP | 111 | ROADWAY WIDENING FOR DEDICATED LEFT AND RIGHT TURN LANES | 1.3071 | PARTNERSHIP
11 | PARTNERSHIP | 28900 | IMP | 008 | MODIFY RAMP AND WIDEN BRIDGE | 1.5329 | PARTNERSHIP |  |  |  |  | X
11 | PARTNERSHIP | 29420 | IMP | 086 | ROADWAY WIDENING AND INSTALLATION OF TRAFFIC SIGNALS | 0.14014 | PARTNERSHIP
11 | PARTNERSHIP | 40680 | SD | 008 | WIDEN EXIT RAMP | 0.68712 | PARTNERSHIP |  |  |  |  | X
11 | PARTNERSHIP | 40990 | SD | 076 | HIGHWAY RE-ALIGNMENT | 0.41532 | PARTNERSHIP | [5 empty] | X
11 | PARTNERSHIP | 41510 | SD | 078 | EXIT RAMPS - WIDENING | 1.0935 | PARTNERSHIP | [5 empty] | X
11 | PARTNERSHIP | 41560 | SD | 008 | CHECKPOINT IMPROVEMENTS | 0.2763 | PARTNERSHIP | [6 empty] | O
11 | PARTNERSHIP | 2E005 | SD | 005 | MITIGATION SITE PRESERVATION | 0.10902 | PARTNERSHIP
11 | PARTNERSHIP | 2E006 | SD | 056 | MITIGATION SITE HABITAT RESTORATION | 1.6415 | PARTNERSHIP
11 | PARTNERSHIP | 2E007 | SD | 056 | MITIGATION SITE HABITAT RESTORATION | 0.88223 | PARTNERSHIP
11 | PARTNERSHIP | 2E008 | SD | L5515 | MITIGATION SITE PRESERVATION | 0.67737 | PARTNERSHIP
11 | PARTNERSHIP | 2E040 | SD | 905 | MITIGATION SITE PRESERVATION | 0.15792 | PARTNERSHIP
11 | PARTNERSHIP | 2E043 | SD | 076 | MITIGATION SITE PRESERVATION | 0.26576 | PARTNERSHIP
11 | PARTNERSHIP | 2E044 | SD | L5515 | MITIGATION SITE PRESERVATION | 0.03913 | PARTNERSHIP
11 | PARTNERSHIP | 2E045 | SD | 999 | MITIGATION SITE PRESERVATION | 0.27592 | PARTNERSHIP
11 | PARTNERSHIP | 2E046 | SD | 076 | MITIGATION SITE PRESERVATION | 0.24833 | PARTNERSHIP
11 | PARTNERSHIP | 2E047 | SD | L5515 | MITIGATION SITE PRESERVATION | 0.13455 | PARTNERSHIP
11 | PARTNERSHIP | 2E048 | SD | 999 | MITIGATION SITE PRESERVATION | 0.02131 | PARTNERSHIP
11 | PARTNERSHIP | 2E051 | SD | L5515 | MITIGATION SITE PRESERVATION | 0.07827 | PARTNERSHIP
11 | PARTNERSHIP | 2E061 | SD | 076 | MITIGATION SITE PRESERVATION | 0.06997 | PARTNERSHIP
11 | PARTNERSHIP | 0223U | SD | 005 | RECONST INTERCHANGE, SIGNAL INTERSECTION AND ADD AUX LANES | 14.5593 | PARTNERSHIP
11 | PARTNERSHIP | 2T001 | SD | 052 | EROSION CONTROL WORK | 0.31511 | PARTNERSHIP
11 | PARTNERSHIP | 2T011 | SD | 052 | PLANTING,IRRIGATION,EROSION CONTROL | 0.42722 | PARTNERSHIP
11 | PARTNERSHIP | 2T070 | SD | 052 | PLANTING AND EROSION WORK | 0.5243 | PARTNERSHIP
11 | PARTNERSHIP | 2T086 | SD | 015 | HWY PLANTING & AUTO IRRIGATION SYS | 0.75886 | PARTNERSHIP
11 | PARTNERSHIP | 2T087 | SD | 015 | LANDSCAPE: MANAGED LANES - NORTH SEGMENT | 0.92234 | PARTNERSHIP
11 | PARTNERSHIP | 2T088 | SD | 015 | LANDSCAPE: MANAGED LANES - NORTH SEGMENT | 0.88997 | PARTNERSHIP
11 | PARTNERSHIP | 2T097 | SD | 015 | LANDSCAPE: MANAGED LANES - SOUTH SEGMENT | 0.91547 | PARTNERSHIP | 2012 | 0672G
11 | PARTNERSHIP | 2T098 | SD | 015 | LANDSCAPE: MANAGED LANES - SOUTH SEGMENT | 0.85814 | PARTNERSHIP | 2012 | 0672G
11 | PARTNERSHIP | 2T099 | SD | 015 | LANDSCAPE: MANAGED LANES - SOUTH SEGMENT | 0.70937 | PARTNERSHIP | 2012 | 0672G
11 | PARTNERSHIP | 2T110 | SD | 015 | PART OF THE 4 MANAGED LANES, OVER- SIGHT OF THE VALUE PRICING PROGRAM | 0.24512 | PARTNERSHIP
11 | PARTNERSHIP | 2T120 | SD | 015 | BUS RAPID TRANSIT (BRT) STATIONS ON THE MANAGED LANES (OVERSIGHT | 0.39873 | PARTNERSHIP
11 | PARTNERSHIP | 2T130 | SD | 015 | BRT STATIONS ONTHE MANAGED LANES (OVERSIGHT PROJECT) | 4.0163 | PARTNERSHIP |  |  |  |  | X
11 | PARTNERSHIP | 2T150 | SD | 805 | INSTALL BRT LANES ON 905, 125, 805N NEW BRIDGE, RAMP REALIGNMENT, | 10.467 | PARTNERSHIP | [6 empty] | O
11 | PARTNERSHIP | 2T170 | SD | 005 | CONSTRUCT SOUNDWALLS IN THE NORTH AND SOUTH BOUND DIRECTIONS | 24.4787 | PARTNERSHIP | 2012 | 0615B
11 | PARTNERSHIP | 2T171 | SD | 005 | CONSTRUCT 1 HOV LANE IN SB & NB DIRECTIONS | 36.0431 | PARTNERSHIP | 2012 | 0615A
11 | PARTNERSHIP | 2T172 | SD | 005 | REPLACE SAN ELIJO BRIDGE, BUILD RET WALLS N AND S BOUND REALIGN | 33.9678 | PARTNERSHIP | 2012 | 0615C
11 | PARTNERSHIP | 2T173 | SD | 005 | TRANSIT 100% OVERSIGHT | 7.8355 | PARTNERSHIP
11 | PARTNERSHIP | 2T175 | SD | 005 | CONSTRUCTING OVERCROSSING | 3.8419 | PARTNERSHIP
11 | PARTNERSHIP | 2T177 | SD | 005 | I-5 LANDSCAPE | 0.36377 | PARTNERSHIP |  |  |  | X
11 | PARTNERSHIP | 2T178 | SD | 005 | I-5 LANDSCAPE | 1.7649 | PARTNERSHIP |  |  |  | X
11 | PARTNERSHIP | 2T182 | SD | 805 | DAR | 21.5528 | PARTNERSHIP
11 | PARTNERSHIP | 2T183 | SD | 805 | SOUNDWALLS | 7.2413 | PARTNERSHIP
11 | PARTNERSHIP | 2T190 | SD | 015 | CONSTRUCT CLASS 1 BIKE PATH | 0.02799 | PARTNERSHIP
11 | PARTNERSHIP | 2T230 | SD | 078 | SR-78 LANDSCAPE | 0.68344 | PARTNERSHIP
11 | PARTNERSHIP | 2T240 | SD | 078 | HOV/MANAGED LANES | 0.02633 | PARTNERSHIP
11 | PARTNERSHIP | 2T241 | SD | 078 | HOV CONNECTORS | 1.2699 | PARTNERSHIP
11 | PARTNERSHIP | 2T250 | SD | 805 | OUTSIDE WIDENING | 9.2669 | PARTNERSHIP |  |  |  | X | X
11 | PARTNERSHIP | 2T260 | SD | 805 | CONSTRUCT EXPRESS LANES | 13.1343 | PARTNERSHIP
11 | PARTNERSHIP | 2T270 | SD | 805 | CONSTRUCT FREEWAY TO FREEWAY | 30.3604 | PARTNERSHIP
12 | PARTNERSHIP | 07810 | ORA | 055 | CONSTRUCT NEW INTERCHANGE | 3.2449 | PARTNERSHIP | [6 empty] | O
12 | PARTNERSHIP | 08790 | ORA | 022 | MODIFY INTERCHANGE KP R12.60 | 0.11972 | PARTNERSHIP | [6 empty] | O
12 | PARTNERSHIP | 09820 | ORA | 405 | WIDENING RAMPS, RAMP INTERSECTIONS, AND BRIDGE APPROACHES | 0.00697 | PARTNERSHIP | [6 empty] | O
12 | PARTNERSHIP | 10287 | ORA | 005 | CONST IC | 1.1871 | PARTNERSHIP | [6 empty] | O
12 | PARTNERSHIP | 11100 | ORA | 261 | CONST FREEWAY 111000 SPL:038610-2-3-4-5-6-7-8-90 | 0.3862 | PARTNERSHIP | [6 empty] | O
12 | PARTNERSHIP | 11102 | ORA | 241 | FOOTHILL TRANS CORRIDOR (SOUTH) | 11 | PARTNERSHIP
12 | PARTNERSHIP | 0695U | ORA | 405 | HOV CONNECTOR AND IMPROVEMENTS | 0.73212 | PARTNERSHIP
12 | PARTNERSHIP | 0716U | ORA | 022 | HIGHWAY REPLACEMENT LANDSCAPE | 1.0568 | PARTNERSHIP
12 | PARTNERSHIP | 0A040 | ORA | 133 | ROADWAY WIDENING | 0.02527 | PARTNERSHIP | [6 empty] | O
12 | PARTNERSHIP | 0C110 | ORA | 057 | RECONFIGURE RAMP AT SR-57 & LAMBERT | 1.8273 | PARTNERSHIP
12 | PARTNERSHIP | 0C510 | ORA | 005 | CONSTRUCT OC | 0.06385 | PARTNERSHIP
12 | PARTNERSHIP | 0C570 | ORA | 091 | CONVERT WB AUXILIARY LANES AT VARIOUS LOCATIONS INTO A THROUGH | 8.2229 | PARTNERSHIP | 2010 | 4516A
12 | PARTNERSHIP | 0C821 | ORA | 241 | CONSTRUCT D STREET OVERCROSSING | 0.13471 | PARTNERSHIP
12 | PARTNERSHIP | 0C890 | ORA | 005 | PROVIDE A SECOND HOV LANE IN BOTH DIRECTIONS | 3.3929 | PARTNERSHIP | 2012 | 2883A
12 | PARTNERSHIP | 0F03U | ORA | 057 | HIGHWAY REPLACEMENT PLANTING | 0.9979 | PARTNERSHIP |  |  |  |  | X
12 | PARTNERSHIP | 0F04A | ORA | 057 | HIGHWAY REPLACEMMENT PLANTING | 1.6611 | PARTNERSHIP
12 | PARTNERSHIP | 0F96A | ORA | 005 | ADD ONE HOV LANE | 6.6705 | PARTNERSHIP | 2012 | 2531D |  |  | X
12 | PARTNERSHIP | 0F96C | ORA | 005 | ADD ONE HOV LANE | 10.4478 | PARTNERSHIP | 2012 | 2531E
12 | PARTNERSHIP | 0F96E | ORA | 005 | ADD ONE HOV LANE | 12.0646 | PARTNERSHIP | 2012 | 2531F
12 | PARTNERSHIP | 0G010 | ORA | 241 | WEIR CANYON ROAD IC ADD TWO RAMPS ON THE SOUTH | 1.7 | PARTNERSHIP
12 | PARTNERSHIP | 0G012 | ORA | 241 | FTC SB WIDENING. ADD ONE LN SB FR S OF SANTA MARGARITA PKWY TO N OF | 0.97012 | PARTNERSHIP
12 | PARTNERSHIP | 0G260 | ORA | 005 | ROUTE 5/ROUTE 55 INTERCHANGE IMPROVEMENT | 0.48118 | PARTNERSHIP |  |  |  |  | X
12 | PARTNERSHIP | 0G850 | ORA | 241 | PREPARE PSR/PR, PS&E & CONSTRUCTION OF MOUNTAIN PARK OVERCROSSING ON | 0.26512 | PARTNERSHIP
12 | PARTNERSHIP | 0H021 | ORA | 005 | MODIFY RAMP/INTERCHANGE | 0.50822 | PARTNERSHIP
12 | PARTNERSHIP | 0H027 | ORA | 005 | WIDEN SAND CANYON AVENUE THROUGH THE INTERCHANGE, WIDEN RAMPS | 1.4804 | PARTNERSHIP
12 | PARTNERSHIP | 0H036 | ORA | 405 | WIDEN LAGUNA CANYON ROAD OVERCROSS | 0.12329 | PARTNERSHIP
12 | PARTNERSHIP | 0H100 | ORA | 405 | ONE-LANE WIDENING IN EACH DIRECTION & ADDING AUXILIARY LANES AT VARIOU | 17.0002 | PARTNERSHIP
12 | PARTNERSHIP | 0H560 | ORA | 133 | WIDEN SR-133 | 0.23857 | PARTNERSHIP
12 | PARTNERSHIP | 0H860 | ORA | 005 | MODIFY RAMPS/INTERCHANGES | 1.0631 | PARTNERSHIP
12 | PARTNERSHIP | 0J340 | ORA | 055 | WIDEN TO INCLUDE ONE NEW GENERAL PURPOSE LANE AND ONE NEW AUXILLIARY | 6.312 | PARTNERSHIP
12 | PARTNERSHIP | 0J440 | ORA | 405 | REMOVE EXISTED HOV BUFFER. RESTRIPE FREEWAY TO PROVIDE A CONTINUOUS HO | 1.6916 | PARTNERSHIP | 2012 | 4926C |  |  | X
12 | PARTNERSHIP | 0J510 | ORA | 005 | JAMBOREE RD. ADD ONE THROUGH LN ON EACH DIRECTIONS (EB&WB) FROM | 0.19316 | PARTNERSHIP
12 | PARTNERSHIP | 0J680 | ORA | 241 | CONSTRUCT THREE GENERAL PURPOSE LANES ON SB SR-241 | 0.12597 | PARTNERSHIP
12 | PARTNERSHIP | 0K020 | ORA | 005 | OPERATIONAL IMPROVEMENT THAT INCLUDE MAINLINE LN ADD, HOV, AUX | 9.0687 | PARTNERSHIP
12 | PARTNERSHIP | 0K560 | ORA | 090 | R/W ACQ, STREET TRAFFIC SIGNING, STRIPING & LANDSCAPE MEDIAN | 0.11426 | PARTNERSHIP
12 | PARTNERSHIP | 0K670 | ORA | 005 | PROVIDE NEW LANES ON BOTH DIRECTION AND IMPROVE THE INTERCHANGE AT THE | 5.5988 | PARTNERSHIP
12 | PARTNERSHIP | 0K970 | ORA | 091 | PROVIDE DIRECT CONNECTOR BETWEEN SR-241 & SR-91 | 6 | PARTNERSHIP |  |  |  |  | X
12 | PARTNERSHIP | 0K980 | ORA | 091 | IMPROVE COMPLEX INTERCHANGES, INCLUDING NEARBY LOCAL INTERCHANGES | 5.9679 | PARTNERSHIP
12 | PARTNERSHIP | 0L280 | ORA | 005 | WIDENTING OF SAN JUAN CREEK RD. | 1.0491 | PARTNERSHIP |  |  | X |  | X
12 | PARTNERSHIP | 0L320 | ORA | 005 | M2 FREEWAY MITIGATION PROGRAM | 1.1863 | PARTNERSHIP
12 | PARTNERSHIP | 0L400 | ORA | 091 | CORRIDOR IMPROVEMENT WIDENING | 2.1489 | PARTNERSHIP
12 | PARTNERSHIP | 0L610 | ORA | 001 | PEDESTRIAN BRIDGE OVERCOSSING | 1.0472 | PARTNERSHIP |  |  | X |  | X
12 | PARTNERSHIP | 0L850 | ORA | 005 | CONTINNOUS ACCESS ON HOV | 1.4352 | PARTNERSHIP | 2012 | 2678 |  |  | X
12 | PARTNERSHIP | 0L950 | ORA | 057 | ARTIC-ANAHEIM REGIONAL TRANSPORTATION INTERMODAL CENTER. | 0.35249 | PARTNERSHIP
12 | PARTNERSHIP | 0M530 | ORA | 005 | WIDEN KATELLA TO PROVIDE BETTER LOS | 0.85228 | PARTNERSHIP | [6 empty] | O
12 | PARTNERSHIP | 0M800 | ORA | 241 | ALL ELECTRONIC TOLLING. | 1.2236 | PARTNERSHIP | [6 empty] | O
12 | PARTNERSHIP | 0M980 | ORA | 005 | INTERCHANGE RECONFIGURATION. | 0.80793 | PARTNERSHIP
12 | PARTNERSHIP | 1016A | ORA | 005 | HIGHWAY PLANTING AND IRRIGATION | 0.11551 | PARTNERSHIP
12 | PARTNERSHIP | 1072C | ORA | 133 | PLANTING AND IRRIGATION | 0.3686 | PARTNERSHIP
12 | PARTNERSHIP | 1072E | ORA | 133 | WETLAND MITIGATION | 0.34474 | PARTNERSHIP
03 | REAL PROPERTY SERVICES | 0R000 | VAR | 000 | REAL PROPERTY SERVICES | 6
03 | REAL PROPERTY SERVICES | 0R003 | VAR | 000 | REAL PROPERTY SERVICES | 2.5
03 | REAL PROPERTY SERVICES | 0R004 | VAR | 000 | REAL PROPERTY SERVICES | 1.5
04 | REAL PROPERTY SERVICES | 15531 | ALA | 238 | REAL PROPERTY SERVICES | 18.0384
04 | REAL PROPERTY SERVICES | 0R000 | SM | 035 | REAL PROPERTY SERVICES | 28.2876
05 | REAL PROPERTY SERVICES | 0R000 | VAR | 000 | REAL PROPERTY SERVICES | 3.07
05 | REAL PROPERTY SERVICES | 0R003 | VAR | 000 | REAL PROPERTY SERVICES | 0.12
06 | REAL PROPERTY SERVICES | 0R000 | VAR | 000 | REAL PROPERTY SERVICES | 1.39
06 | REAL PROPERTY SERVICES | 0R003 | VAR | 000 | REAL PROPERTY SERVICES | 0.43
07 | REAL PROPERTY SERVICES | 0R000 | VAR | 000 | REAL PROPERTY SERVICES | 38.7129
08 | REAL PROPERTY SERVICES | 0R000 | VAR | 002 | REAL PROPERTY SERVICES | 3.8357
08 | REAL PROPERTY SERVICES | 0R003 | VAR | 999 | REAL PROPERTY SERVICES | 3.2236
10 | REAL PROPERTY SERVICES | 0R000 | VAR | 000 | REAL PROPERTY SERVICES | 1.39
10 | REAL PROPERTY SERVICES | 0R003 | VAR | 000 | REAL PROPERTY SERVICES | 0.43
10 | REAL PROPERTY SERVICES | 0R004 | VAR | 000 | REAL PROPERTY SERVICES | 0.27
11 | REAL PROPERTY SERVICES | 0R000 | VAR | 000 | REAL PROPERTY SERVICES | 6.1285
11 | REAL PROPERTY SERVICES | 0R00D | VAR | 999 | REAL PROPERTY SERVICES | 1.8693
12 | REAL PROPERTY SERVICES | 0R000 | VAR | 000 | REAL PROPERTY SERVICES | 1.8862
04 | REGIONAL MEASURE 1 | 01601 | ALA | 092 | RECONSTRUCT INTERCHANGE | 0.74069 | PARTNERSHIP
04 | REGIONAL MEASURE 1 | 0060C | CC | 680 | REPLACEMENT PLANTING | 3.9828 | PARTNERSHIP | [5 empty] | X
04 | REGIONAL MEASURE 1 | 0130J | CC | 680 | POST CONSTRUCTION MONITORING AND REMEDIATION OF THE NEW FISH HABITAT | 0.37731 | PARTNERSHIP | [5 empty] | X
01 | SEISMIC/TOLL BRIDGE/OTHER TOLL | 29670 | HUM | 255 | SEISMIC RETROFIT - PHASE 2 | 0.34 | SHOPP | 1998 | 0100C | [5 empty] | 28585000 | 7232000 | 272000 | 2746000 | 308000 | 3906000 | 8491753.59 | 25.3% | 2003-02-11 | 2006-04-24 | 0 | 0 | 0 | 0.34 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SEISMIC/TOLL BRIDGE/OTHER TOLL | 37801 | MEN | 001 | SIESMIC RETROFIT- REPLACE BRIDGE | 0.23 | SHOPP | 1998 | 0154R | [5 empty] | 18191000 | 3816000 | 3816000 | F | F | F | 9492165.16 | 20.98% | 2002-03-28 | 2006-11-20 | 0 | 0 | 0.040188 | 0.18981 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SEISMIC/TOLL BRIDGE/OTHER TOLL | 38570 | MEN | 001 | REPLACE BRIDGE SEISMIC RETROFIT - PHASE 2 | 0.64 | SHOPP | 2006 | 0155T | [5 empty] | 19860000 | 11052000 | 11052000 | F | F | F | 15459202.89 | 55.65% | 2007-01-11 | 2010-08-17 | 0 | 0 | 0.17344 | 0.46656 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SEISMIC/TOLL BRIDGE/OTHER TOLL | 00297 | ALA | L5785 | REPLACE ADMIN BLDGS | 3.2758 | PARTNERSHIP
04 | SEISMIC/TOLL BRIDGE/OTHER TOLL | 00394 | CC | 580 | REPLACE MAINTENANCE BUILDINGS | 8.8467 | PARTNERSHIP
04 | SEISMIC/TOLL BRIDGE/OTHER TOLL | 01209 | SF | 080 | EXISTING EAST SPAN DEMOLITION | 44.79 | PARTNERSHIP |  |  |  | X | X
04 | SEISMIC/TOLL BRIDGE/OTHER TOLL | 01350 | SF | 080 | LANDSCAPE AND RESTORE VEGERATIONS AND PLANTS | 2.0317 | PARTNERSHIP
04 | SEISMIC/TOLL BRIDGE/OTHER TOLL | 04100 | SM | 092 | RESURFACE ORTHOTROPIC DECK | 12.4412 | PARTNERSHIP |  |  |  | X | X
04 | SEISMIC/TOLL BRIDGE/OTHER TOLL | 04224 | SM | 092 | REPLACE 12KV ELECTRIC SWITCHGEARS | 0.45408 | PARTNERSHIP
04 | SEISMIC/TOLL BRIDGE/OTHER TOLL | 04907 | CC | 080 | REPLACE TIMBER FENDERS PIERS 2 & 3 AND REPAIR PILE AND RING BEAMS | 1.1857 | PARTNERSHIP | [5 empty] | X
04 | SEISMIC/TOLL BRIDGE/OTHER TOLL | 16542 | ALA | 880 | REPLACE BRIDGES AND CONSTRUCT ROAD | 3.1743 | SHOPP | 2008 | 0040E | [5 empty] | 93309000 | 32423000 | 32423000 | F | F | F | 35922284.34 | 34.75% | 2009-07-21 | 2013-06-28 | 0 | 0 | 1.0272 | 2.1471 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SEISMIC/TOLL BRIDGE/OTHER TOLL | 29226 | ALA | 080 | CONSTRUCT BIKEWAY | 3.3067 | SHOPP | 2010 | 0054N |  |  |  | X |  | 8724000 | 8107000 | 7000 | 5800000 | 300000 | 2000000 | 7082064.31 | 92.93% | 2012-05-21 | 2013-09-30 | 0 | 0 | 0.47273 | 2.834 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SEISMIC/TOLL BRIDGE/OTHER TOLL | 44083 | SM | 101 | REQ'ENVIR MITGTN (SETTLEMENT BASIN) | 0.74919 | PARTNERSHIP
04 | SEISMIC/TOLL BRIDGE/OTHER TOLL | 0120F | SF | 080 | CONSTRUCT SELF ANCHORED SUSPENSION BRIDGE | 140.6053 | PARTNERSHIP
04 | SEISMIC/TOLL BRIDGE/OTHER TOLL | 0120M | ALA | 080 | CONSTRUCT BRIDGES, ROADWAY AND ELECTRICAL SYSTEM | 45.7821 | PARTNERSHIP
04 | SEISMIC/TOLL BRIDGE/OTHER TOLL | 0120S | SF | 080 | CONSTRUCT BRIDGES AND ROADWAY AND INSTALL ELECTRICAL SYSTEM | 31.5655 | PARTNERSHIP | [5 empty] | X
04 | SEISMIC/TOLL BRIDGE/OTHER TOLL | 0120T | SF | 080 | CONSTRUCT EB ONRAMP & OFFRAMP TO AND FROM ROUTE 80 | 43.7515 | PARTNERSHIP
04 | SEISMIC/TOLL BRIDGE/OTHER TOLL | 0435E | SF | 080 | LANDSCAPING AND LIGHTING | 1.1922 | PARTNERSHIP
04 | SEISMIC/TOLL BRIDGE/OTHER TOLL | 0G610 | CC | 160 | REPLACE DRAINAGE GRATES AT THE TOLL PLAZA | 0.53426 | PARTNERSHIP | [5 empty] | X
04 | SEISMIC/TOLL BRIDGE/OTHER TOLL | 1A522 | SM | 084 | DUMBARTON BRIDGE SEISMIC RETROFIT | 2.2367 | PARTNERSHIP
04 | SEISMIC/TOLL BRIDGE/OTHER TOLL | 1G250 | SF | 080 | REPLACE FLUORESCENT LIGHTING WITH HIGH PRESSURE SODIUM VAPOR LIGHTING | 1.1562 | PARTNERSHIP | [5 empty] | X
04 | SEISMIC/TOLL BRIDGE/OTHER TOLL | 1G260 | SF | 080 | REPLACE FLUORESCENT LIGHTING WITH HIGH PRESSURE SODIUM VAPOR LIGHTING | 1.1006 | PARTNERSHIP | [5 empty] | X
04 | SEISMIC/TOLL BRIDGE/OTHER TOLL | 1G270 | CC | 580 | REPLACE DRAINAGE GRATES AT THE TOLL PLAZAS | 0.16928 | PARTNERSHIP
04 | SEISMIC/TOLL BRIDGE/OTHER TOLL | 2G260 | ALA | 084 | REPLACE DRAINAGE GRATES AT THE TOLL PLAZA | 0.19829 | PARTNERSHIP
04 | SEISMIC/TOLL BRIDGE/OTHER TOLL | 2G361 | ALA | 092 | REPLACEMENT PLANTING AND IRRIGATION | 0.24965 | PARTNERSHIP
04 | SEISMIC/TOLL BRIDGE/OTHER TOLL | 2G420 | ALA | 080 | PROVIDE OVERSIGHT UNDER PERMIT ISSUED TO BATA FOR MAINTENANCE WORK | 1.9791 | PARTNERSHIP
04 | SEISMIC/TOLL BRIDGE/OTHER TOLL | 2G670 | SM | 092 | REREMOVE & INSTALL CONCRETE GIRDERS SLABS BETWEEN PIER 38 AND BENT 286 | 0.06903 | PARTNERSHIP
04 | SEISMIC/TOLL BRIDGE/OTHER TOLL | 3G300 | CC | 160 | FENDER SYSTEM | 3.9129 | PARTNERSHIP
04 | SEISMIC/TOLL BRIDGE/OTHER TOLL | 3G442 | SF | 080 | GENERATORS(SAN FRANCISCO-OAKLAND BAY BRIDGE) | 3.3032 | PARTNERSHIP
04 | SEISMIC/TOLL BRIDGE/OTHER TOLL | 3G443 | SM | 092 | GENERATORS (SAN MATEO-HAYWARD BRIDGE) | 1.388 | PARTNERSHIP |  |  |  | X | X
04 | SEISMIC/TOLL BRIDGE/OTHER TOLL | 3G450 | CC | 580 | REPLACE JOINT SEALS | 5.1636 | PARTNERSHIP |  |  |  | X | X
04 | SEISMIC/TOLL BRIDGE/OTHER TOLL | 3G470 | ALA | 080 | TRAVELER REPLACEMENT AND RAIL UP-R GRADES (SAN FRANCISCO- OAKLAND BAY | 1.622 | PARTNERSHIP |  |  |  |  | X
04 | SEISMIC/TOLL BRIDGE/OTHER TOLL | 3G474 | CC | 580 | REPLACE TRAVELERS AND RAILS | 2.7168 | PARTNERSHIP |  |  |  | X | X
04 | SEISMIC/TOLL BRIDGE/OTHER TOLL | 3G480 | SF | 080 | PIER FORMWORK REMOVAL (SAN FRANCIS CO-OAKLAND BAY BRIDGE) | 3.3346 | PARTNERSHIP |  |  |  | X
04 | SEISMIC/TOLL BRIDGE/OTHER TOLL | 3G484 | CC | 580 | STRUCTURAL STEEL PAINTING | 1.4572 | PARTNERSHIP |  |  |  | X | X
04 | SEISMIC/TOLL BRIDGE/OTHER TOLL | 3G486 | SM | 092 | STRUCTURAL STEEL PAINTING | 1.8998 | PARTNERSHIP |  |  |  | X | X
04 | SEISMIC/TOLL BRIDGE/OTHER TOLL | 3G487 | SF | 080 | STRUTURAL STEEL PAINTING (CONTRACT #1) | 0.87758 | PARTNERSHIP |  |  |  | X | X
04 | SEISMIC/TOLL BRIDGE/OTHER TOLL | 4G280 | ALA | 080 | TOLL PLAZA CANOPY CLADDING REPLACEMENT AND TOLL LANES PAVEMENT | 1.2269 | PARTNERSHIP
04 | SEISMIC/TOLL BRIDGE/OTHER TOLL | 4G290 | ALA | 080 | PUMP STATION CLADDING REPLACEMENT AND TOLL PLAZA CRASH CUSHION | 0.428 | PARTNERSHIP
01 | SHOPP | 29171 | MEN | 001 | CONSTRUCT TIEBACK RETAINING WALL | 0.2581 | SHOPP | 2008 | 0140B | [5 empty] | 7303000 | 4689000 | 1273000 | 1711000 | 184000 | 1521000 | 3192603.55 | 64.21% | 2008-12-11 | 2010-07-12 | 0 | 0 | 0.10779 | 0.15031 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 29302 | MEN | 101 | REPLACE BRIDGE AND RAIL UPGRADE | 2.3 | SHOPP | 2012 | 4453 | [5 empty] | 3934000 | 2643000 | 407000 | 896000 | 209000 | 1131000 | 0 | 67.18% | 2019-01-08 | 2020-09-09 | 1.6953 | 0.60467 | 0 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 29313 | DN | 101 | WIDEN ROADWAY AND BRIDGES | 0.02 | SHOPP | 2004 | 0001J | [5 empty] | 3981000 | 1734000 | 1734000 | F | F | F | 3193631.4634 | 43.56% | 2005-08-15 | 2007-11-20 | 0 | 0 | 0.0031454 | 0.016855 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 29314 | DN | 199 | REPLACE BRIDGE | 0.01 | SHOPP | 2006 | 0013 | [5 empty] | 3718000 | 2733000 | 2733000 | F | F | F | 3254475.7966 | 73.51% | 2007-05-11 | 2009-07-27 | 0 | 0 | 0.0032283 | 0.0067717 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 29610 | HUM | 101 | REPLACE BRIDGES (SCOUR) | 4.9491 | SHOPP | 2006 | 0073N |  |  |  | X |  | 50074000 | 11138000 | 11138000 | F | F | F | 16702271.82 | 22.24% | 2008-09-18 | 2014-02-01 | 0 | 0 | 1.3176 | 3.6315 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 29611 | HUM | 255 | WETLAND MITIGATION | 0.66 | SHOPP | 2012 | 0073X |  | X | X |  |  | 500000 | 211000 | 20000 | 60000 | 8000 | 123000 | 11222.54 | 42.2% | 2006-12-16 | 2015-09-01 | 0 | 0.56682 | 0.059458 | 0.033726 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 29612 | HUM | 299 | FISH & RIPARIAN MITIGATION (CULVERT REHABILITATION) | 0.32 | SHOPP | 2010 | 0073Y |  |  |  | X |  | 1010000 | 334000 | 30000 | 112000 | 16000 | 176000 | 163073.97 | 33.07% | 2012-08-01 | 2013-08-01 | 0 | 0 | 0.06423 | 0.25577 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 30790 | MEN | 001 | REALIGN ROADWAY | 0.16 | SHOPP | 2004 | 0135 | [5 empty] | 2102000 | 1726000 | 1726000 | F | F | F | 2969882.03 | 82.11% | 2006-02-10 | 2007-11-20 | 0 | 0 | 0 | 0.16 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 31010 | MEN | 001 | REPLACE BRIDGE (SCOUR) | 5.3791 | SHOPP | 2010 | 0140A | [5 empty] | 9700000 | 9220000 | 2175000 | 3575000 | 475000 | 2995000 | 7070801.76 | 95.05% | 2011-11-08 | 2014-12-01 | 0 | 0.068648 | 0.05495 | 5.2555 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 31440 | HUM | 101 | BRIDGE REPLACEMENT (SCOUR) | 0.12509 | SHOPP | 2004 | 0054A | [5 empty] | 11058000 | 2022000 | 2022000 | F | F | F | 5969935.34 | 18.29% | 2005-06-30 | 2008-05-19 | 0 | 0 | 0 | 0.12509 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 32330 | HUM | 036 | WIDEN FOR LEFT-TURN CHANNELIZATION | 7.2636 | SHOPP | 2010 | 0017G |  |  |  | X |  | 8000000 | 6948000 | 1180000 | 2400000 | 2400000 | 968000 | 4728720.56 | 86.85% | 2013-01-01 | 2014-05-01 | 0 | 0 | 1.0594 | 6.2041 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 32470 | DN | 101 | CONSTRUCT RETAINING WALL (6 LOC) | 0.85702 | SHOPP | 2008 | 0002F | [5 empty] | 11483000 | 6606000 | 3696000 | 750000 | 160000 | 2000000 | 6752140.66 | 57.53% | 2009-06-02 | 2010-04-12 | 0 | 0 | 0.17992 | 0.6771 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 34540 | DN | 101 | SHOULDER WIDENING AND LEFT TURN | 0.13 | SHOPP | 2006 | 0100F | [5 empty] | 9463000 | 4405000 | 4405000 | F | F | F | 5644293.2 | 46.55% | 2007-05-11 | 2009-12-02 | 0 | 0 | 0.029464 | 0.10054 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 36432 | MEN | 020 | REHABILITATE DRAINAGE | 1.7232 | SHOPP | 2012 | 0161D | [5 empty] | 1983000 | 3520000 | 735000 | 1655000 | 500000 | 630000 | 3211649.3438 | 177.5% | 2013-02-01 | 2015-01-01 | 0 | 0 | 0.28793 | 1.4353 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 36460 | HUM | 169 | REPLACE BRIDGES | 0.51609 | SHOPP | 2008 | 0093B | [5 empty] | 11891000 | 4888000 | 1020000 | 1600000 | 200000 | 2068000 | 6012691.56 | 41.11% | 2009-03-04 | 2012-12-13 | 0 | 0 | 0.076737 | 0.43936 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 37815 | MEN | 128 | REPLACE CULVERTS | 1.0779 | SHOPP | 2008 | 4505 |  |  |  | X |  | 3242000 | 3153000 | 719000 | 864000 | 725000 | 845000 | 3353445.5235 | 97.25% | 2011-03-04 | 2013-10-01 | 0 | 0.028182 | 0.51531 | 0.53439 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 37816 | MEN | 128 | CULVERT REHABILITATION | 2.9927 | SHOPP | 2012 | 0200 | [5 empty] | 5200000 | 5422000 | 912000 | 2260000 | 1100000 | 1150000 | 3727361.5995 | 104.3% | 2013-05-01 | 2015-08-01 | 0 | 0.13436 | 0.3734 | 2.485 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 37817 | MEN | 128 | CULVERT REHABILITATION | 2.47 | SHOPP | 2012 | 4506 |  | X | X |  |  | 3908000 | 3684000 | 742000 | 1575000 | 430000 | 937000 | 2745031.8971 | 94.27% | 2014-05-15 | 2015-12-01 | 0 | 1.4321 | 0.74521 | 0.29269 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 38560 | LAK | 029 | SCOUR MITIGATION | 0.89 | SHOPP | 2012 | 3087 |  | X | X | X |  | 311000 | 333000 | 71000 | 112000 | 16000 | 134000 | 0 | 107.1% | 2013-08-15 | 2014-01-01 | 0.019921 | 0.21303 | 0.10481 | 0.55224 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 38572 | MEN | 001 | REMOVE CULVERT, CONSTRUCT BRIDGE, IMPROVE FISH PASSAGE | 3.2416 | SHOPP | 2010 | 0155Z |  |  |  | X |  | 4220000 | 2791000 | 591000 | 1250000 | 50000 | 900000 | 2079593.63 | 66.14% | 2012-08-01 | 2014-03-31 | 0 | 0 | 0.085422 | 3.1562 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 39751 | MEN | 101 | REALIGN ROADWAY | 2.8754 | SHOPP | 2004 | 0179T | [5 empty] | 73359000 | 14076000 | 14076000 | F | F | F | 22619214.21 | 19.19% | 2006-06-05 | 2010-02-18 | 0 | 0 | 0.38582 | 2.4895 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 39754 | MEN | 101 | DECOMMISSION EXISTING ROADWAY | 0.74 | SHOPP | 2010 | 4427 |  |  |  | X |  | 7951000 | 3153000 | 300000 | 850000 | 431000 | 1572000 | 1467777.35 | 39.66% | 2011-08-22 | 2013-07-15 | 0 | 0 | 0.25186 | 0.48814 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 39755 | MEN | 101 | CONSTRUCT CONCRETE BAFFLES AND PLACE ROCK CLUSTERS IN ARCH CULVERT | 0.01 | SHOPP | 2008 | 4502 | [5 empty] | 510000 | 320000 | 88000 | 78000 | 36000 | 118000 | 264393.4 | 62.75% | 2010-05-25 | 2010-10-28 | 0 | 0 | 0.0043778 | 0.0056222 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 39910 | HUM | 036 | CAPITAL PREVENTIVE MAINTENANCE | 1.39 | SHOPP | 2010 | 0018 |  |  |  | X |  | 13300000 | 2686000 | 20000 | 1076000 | 20000 | 1570000 | 725326.37 | 20.2% | 2011-11-30 | 2013-11-01 | 0 | 0 | 0.07152 | 1.3185 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 40110 | MEN | 001 | REPLACE BRIDGE | 16.38 | SHOPP | 2012 | 4490 | X |  |  |  |  | 50900000 | 17245000 | 3104000 | 5164000 | 794000 | 8183000 | 279611.46 | 33.88% | 2016-09-01 | 2019-11-01 | 10.3447 | 5.9087 | 0.12663 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 40140 | MEN | 001 | BRIDGE REPLACEMENT | 16.54 | SHOPP | 2012 | 4491 | X |  |  |  |  | 55000000 | 14638000 | 4392000 | 5593000 | 748000 | 3905000 | 293452.63 | 26.61% | 2016-04-15 | 2018-10-01 | 3.8618 | 12.1343 | 0.5439 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 40280 | MEN | 101 | CULVERT REHABILITATION | 2.918 | SHOPP | 2012 | 0181A | [5 empty] | 3320000 | 3264000 | 1250000 | 852000 | 281000 | 881000 | 2170771.24 | 98.31% | 2013-11-01 | 2014-12-01 | 0 | 0 | 0 | 2.918 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 42370 | HUM | 299 | RECONSTRUCT ROADWAY | 9.8994 | SHOPP | 2010 | 2274 |  |  |  | X |  | 15531000 | 5538000 | 1170000 | 1703000 | 65000 | 2600000 | 2029075.6 | 35.66% | 2013-01-01 | 2014-02-01 | 0 | 0 | 0.12109 | 9.7783 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 43060 | HUM | 254 | REPLACE BRIDGE RAILS AND WIDEN (FOUR BRIDGES) | 3.4018 | SHOPP | 2012 | 0046D | X |  |  |  |  | 9770000 | 4566000 | 1600000 | 1069000 | 197000 | 1700000 | 1294068.17 | 46.73% | 2015-03-25 | 2016-04-02 | 0.2513 | 1.1325 | 0.48316 | 1.5349 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 43480 | MEN | 001 | BRIDGE RAIL UPGRADE AND WIDENING | 10.67 | SHOPP | 2012 | 4507 | [5 empty] | 12846000 | 6170000 | 1790000 | 2825000 | 341000 | 1214000 | 0 | 48.03% | 2016-11-15 | 2018-11-01 | 6.7786 | 3.8914 | 0 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 43640 | DN | 101 | REPLACE BRIDGE | 16.32 | SHOPP | 2012 | 0100V | X |  |  |  |  | 52952000 | 15489000 | 4905000 | 4002000 | 369000 | 6213000 | 3104841.72 | 29.25% | 2016-10-04 | 2019-12-02 | 7.5928 | 8.4894 | 0.23786 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 45090 | HUM | 169 | WIDENING AND MBGR | 2.7355 | SHOPP | 2012 | 2028 | [5 empty] | 5716000 | 4618000 | 1300000 | 1458000 | 560000 | 1300000 | 2883338.06 | 80.79% | 2013-10-15 | 2015-05-01 | 0 | 0.14388 | 0.20806 | 2.3836 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 45470 | LAK | 029 | SHOULDER WIDENING | 0.13 | SHOPP | 2006 | 3039 | [5 empty] | 2656000 | 951000 | 951000 | F | F | F | 1033646.93 | 35.81% | 2007-05-15 | 2007-11-06 | 0 | 0 | 0.045221 | 0.084779 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 45940 | HUM | 096 | REHABILITATE PAVEMENT | 0.07 | SHOPP | 2010 | 2209 | [5 empty] | 4950000 | 982000 | E | 462000 | 27000 | 493000 | 403160.19 | 19.84% | 2010-11-24 | 2011-12-07 | 0 | 0 | 0.0049815 | 0.065018 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 45970 | HUM | 101 | SEISMIC RETROFIT | 4.3872 | SHOPP | 2012 | 2208 | [5 empty] | 4026000 | 3557000 | E | 1516000 | 95000 | 1946000 | 1224520.32 | 88.35% | 2013-07-01 | 2015-10-01 | 0 | 0 | 0 | 4.3872 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 46391 | HUM | 299 | RECONSTRUCT GUARD RAILING | 2.09 | SHOPP | 2010 | 2210 |  |  |  | X |  | 3603000 | 838000 | 133000 | 371000 | C | 334000 | 524857.6 | 23.26% | 2012-12-13 | 2014-01-01 | 0 | 0 | 0.023954 | 2.066 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 46392 | HUM | VAR | RECONSTRUCT GUARD RAILING | 2.5 | SHOPP | 2012 | 2210B | X | X | X |  |  | 4607000 | 522000 | 140000 | 105000 | 30000 | 247000 | 0 | 11.33% | 2014-09-01 | 2015-10-01 | 0.60355 | 1.8431 | 0.053374 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 46420 | MEN | VAR | RECONSTRUCT GUARD RAILING | 3.3334 | SHOPP | 2010 | 4452 | [5 empty] | 8915000 | 2867000 | 350000 | 640000 | 97000 | 1780000 | 1259025 | 32.16% | 2012-02-28 | 2014-08-01 | 0 | 0 | 0.18326 | 3.1502 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 46440 | LAK | VAR | METAL BEAM GUARD RAIL | 0.04 | SHOPP | 2010 | 3056 | [5 empty] | 3076000 | 1041000 | 178000 | 339000 | 29000 | 495000 | 1160198.28 | 33.84% | 2010-12-10 | 2013-02-01 | 0 | 0 | 0.0053632 | 0.034637 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 46480 | HUM | 101 | STAA OPERATIONAL IMPROVEMENT PROJECT | 2.2552 | SHOPP | 2012 | 2251 | [5 empty] | 5654000 | 4399000 | 1307000 | 1565000 | 327000 | 1200000 | 3503321.1 | 77.8% | 2011-06-15 | 2015-02-01 | 0.15957 | 0.0044805 | 1.3196 | 0.7715 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 47021 | HUM | 101 | CONSTRUCT RETAINING WALL | 0.23 | SHOPP | 2006 | 2045 | [5 empty] | 10000000 | 3889000 | 3889000 | F | F | F | 2706362.24 | 38.89% | 2008-08-19 | 2011-06-14 | 0 | 0 | 0 | 0.23 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 47220 | HUM | 096 | RECONSTRUCT ROADWAY, REPAIR SLOPE AND REPAIR DRAINAGE | 0.02 | SHOPP | 2010 | 2204 | [5 empty] | 426000 | 1011000 | 56000 | 825000 | 35000 | 95000 | 843513.86 | 237.3% | 2011-02-22 | 2011-12-15 | 0 | 0 | 0.01 | 0.01 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 47230 | HUM | 096 | HOT MIX ASPHALT OVERLAY | 0.12 | SHOPP | 2008 | 2206 | [5 empty] | 1710000 | 1142000 | 78000 | 585000 | 149000 | 330000 | 959398.97 | 66.78% | 2010-07-29 | 2011-03-01 | 0 | 0 | 0 | 0.12 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 47260 | MEN | 001 | CONSTRUCT TIEBACK RETAINING WALL METAL BEAM GUARD RAIL AND PLACE | 0.37 | SHOPP | 2008 | 4451 | [5 empty] | 3073000 | 1928000 | 200000 | 900000 | 55000 | 773000 | 2075485.93 | 62.74% | 2010-10-07 | 2012-04-23 | 0 | 0 | 0.14028 | 0.22972 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 47441 | HUM | 299 | REPAIR SLIDE & REPLACE DRAINAGE | 2.2449 | SHOPP | 2010 | 2347 |  |  |  | X |  | 5025000 | 872000 | N | 100000 | 20000 | 752000 | 2333653.95 | 17.35% | 2012-06-18 | 2014-04-03 | 0 | 0 | 0.16877 | 2.0762 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 47480 | MEN | 001 | REPAIR STORM DAMAGE | 0.57 | SHOPP | 2010 | 4458 | [5 empty] | 3700000 | 1691000 | 131000 | 610000 | 300000 | 650000 | 1515423.16 | 45.7% | 2011-10-25 | 2012-10-26 | 0 | 0 | 0.10047 | 0.46953 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 47490 | MEN | 001 | REPAIR STORM DAMAGE | 3.4863 | SHOPP | 2012 | 4459 | [5 empty] | 5148000 | 1526500 | 625000 | 1500 | 180000 | 720000 | 2462967.34 | 29.65% | 2013-11-01 | 2014-10-01 | 0 | 1.3761 | 0.12332 | 1.9869 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 47501 | HUM | 254 | REPAIR STORM DAMAGE | 1.6565 | SHOPP | 2010 | 2281 |  |  |  | X |  | 2020000 | 1393000 | 58000 | 640000 | 125000 | 570000 | 1095638.8081 | 68.96% | 2012-01-27 | 2013-10-15 | 0 | 0 | 0.02406 | 1.6324 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 47502 | HUM | 254 | REPAIR STORM DAMAGE | 0.52735 | SHOPP | 2012 | 2216 |  |  |  | X |  | 940000 | 915000 | 100000 | 575000 | 15000 | 225000 | 813683.1119 | 97.34% | 2012-11-19 | 2013-10-01 | 0 | 0 | 0.070169 | 0.45718 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 47510 | HUM | 254 | RECONSTRUCT HIGHWAY WITH TIEBACK RETAINING WALLS REPLACE CULVERTS | 0.17 | SHOPP | 2008 | 2217 | [5 empty] | 4550000 | 2670000 | 300000 | 1400000 | 66000 | 904000 | 2443495.61 | 58.68% | 2010-10-28 | 2011-08-31 | 0 | 0 | 0.091562 | 0.078438 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 47520 | HUM | 254 | REPAIR STORM DAMAGE | 0.35 | SHOPP | 2010 | 2218 |  |  |  | X |  | 788000 | 1137000 | 172000 | 770000 | 35000 | 160000 | 1104101.01 | 144.3% | 2011-10-14 | 2013-11-01 | 0 | 0 | 0.022006 | 0.32799 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 47530 | HUM | 254 | RESURFACE ROADWAY | 0.02 | SHOPP | 2008 | 2219 | [5 empty] | 810000 | 873000 | 79000 | 299000 | 167000 | 328000 | 755964.69 | 107.8% | 2009-09-03 | 2010-10-28 | 0 | 0 | 0.01 | 0.01 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 47550 | HUM | 036 | REPAIR STORM DAMAGE | 0.34 | SHOPP | 2010 | 2221 |  |  |  | X |  | 1538000 | 1377000 | 97000 | 900000 | 105000 | 275000 | 1244593.02 | 89.53% | 2011-12-07 | 2013-11-01 | 0 | 0 | 0.078226 | 0.26177 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 47560 | HUM | 036 | COLD PLANE AC PAVEMENT PLACE HMA TYPE A AND CONSTRUCT TIEBACK WALL | 0.09 | SHOPP | 2008 | 2222 | [5 empty] | 1434000 | 1351000 | 200000 | 650000 | 105000 | 396000 | 1313915.16 | 94.21% | 2010-12-08 | 2012-05-30 | 0 | 0 | 0.047654 | 0.042346 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 47580 | HUM | 036 | CONSTRUCT TIEBACK RETAINING WALL | 0.15 | SHOPP | 2008 | 2224 | [5 empty] | 937000 | 1260000 | 77000 | 750000 | 100000 | 333000 | 1100062.25 | 134.5% | 2010-10-13 | 2011-12-19 | 0 | 0 | 0.038428 | 0.11157 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 47610 | MEN | 253 | CONSTRUCT RETAINING WALL | 0.09 | SHOPP | 2008 | 4462 | [5 empty] | 2303000 | 1037000 | 25000 | 471000 | 35000 | 506000 | 1181763.51 | 45.03% | 2009-07-20 | 2010-11-22 | 0 | 0 | 0.043018 | 0.046982 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 47620 | MEN | 253 | REPAIR STORM DAMAGE | 1.6153 | SHOPP | 2010 | 4474 |  |  |  | X |  | 4319000 | 2348000 | 227000 | 1170000 | 91000 | 860000 | 1705765.36 | 54.36% | 2011-12-21 | 2013-08-20 | 0 | 0 | 0.089685 | 1.5256 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 47630 | MEN | 162 | RECONSTRUCT AND REALIGN ROADWAY | 0.33 | SHOPP | 2008 | 4464 | [5 empty] | 3210000 | 1464000 | 80000 | 593000 | 189000 | 602000 | 906035.69 | 45.61% | 2009-06-23 | 2010-01-04 | 0 | 0 | 0.059784 | 0.27022 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 47660 | MEN | 128 | REPAIR STORM DAMAGE | 2.5218 | SHOPP | 2012 | 4463 | [5 empty] | 10383000 | 5935000 | 989000 | 2473000 | 495000 | 1978000 | 1608783.92 | 57.16% | 2013-09-15 | 2016-03-02 | 0 | 0.25286 | 0.078484 | 2.1904 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 47690 | DN | 101 | REMOVE & RECONSTRUCT HINGES @ SPANS 2, 8 & 11 | 2.7992 | SHOPP | 2012 | 1039 | [5 empty] | 7300000 | 3046000 | 800000 | 421000 | 125000 | 1700000 | 1108579.34 | 41.73% | 2013-02-04 | 2016-12-02 | 0 | 0 | 0.086734 | 2.7125 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 47710 | MEN | 175 | RECONSTRUCT HIGHWAY EMBANKMENT REPLACE CULVERTS AND PLACE HMA | 0.13 | SHOPP | 2008 | 4473 | [5 empty] | 1595000 | 1053000 | 28000 | 600000 | 75000 | 350000 | 1169188.95 | 66.02% | 2010-12-08 | 2011-11-10 | 0 | 0 | 0.082866 | 0.047134 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 47770 | MEN | 101 | CONSTRUCT SOLDIER PILE RET WALL | 0.11 | SHOPP | 2010 | 4469 | [5 empty] | 2491000 | 1525000 | 115000 | 880000 | 20000 | 510000 | 1457595.97 | 61.22% | 2011-05-10 | 2012-10-24 | 0 | 0 | 0 | 0.11 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 47830 | HUM | 169 | CONSTRUCT TIEBACK RETAINING WALL | 0.21 | SHOPP | 2008 | 2230 | [5 empty] | 2625000 | 1394000 | 105000 | 568000 | 134000 | 587000 | 1672621.5 | 53.1% | 2010-06-21 | 2011-12-28 | 0 | 0 | 0.037081 | 0.17292 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 47850 | HUM | 169 | REPAIR STORM DAMAGE | 0.02 | SHOPP | 2008 | 2229 | [5 empty] | 1466000 | 1152000 | 129000 | 450000 | 100000 | 473000 | 1004706.87 | 78.58% | 2010-12-08 | 2011-11-03 | 0 | 0 | 0.0074163 | 0.012584 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 47880 | HUM | 101 | GRIND AND REPAVE ASPHALT SURFACING | 0.01 | SHOPP | 2008 | 2232 | [5 empty] | 12410000 | 1117000 | 20000 | 470000 | 27000 | 600000 | 977146.47 | 9.001% | 2010-12-08 | 2011-11-17 | 0 | 0 | 0.0054861 | 0.0045139 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 47920 | LAK | 029 | REPLACE OGAC, INSTALL INGROUND RUMBLE STRIP & RECONSTRUCT MBGR | 0.12 | SHOPP | 2010 | 3066 | [5 empty] | 7915000 | 1400000 | 20000 | 360000 | 20000 | 1000000 | 394865.34 | 17.69% | 2011-12-08 | 2013-01-15 | 0 | 0 | 0.03604 | 0.08396 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 48050 | LAK | 020 | INSTALL ROUNDABOUT | 0.51 | SHOPP | 2010 | 3067 |  |  |  | X |  | 4808000 | 1625000 | 250000 | 400000 | 350000 | 625000 | 1965273.53 | 33.8% | 2011-10-28 | 2013-10-01 | 0 | 0 | 0.1511 | 0.3589 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 48240 | HUM | 299 | INSTALL IRRIGATION SYSTEM | 0.85 | SHOPP | 2010 | 2245 | [5 empty] | 1620000 | 757000 | 194000 | 357000 | 51000 | 155000 | 869904.9 | 46.73% | 2011-01-26 | 2012-02-10 | 0 | 0 | 0.012169 | 0.83783 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 48270 | DN | 199 | CONSTRUCT CABLE MESH DRAPERY SYSTEM | 0.07 | SHOPP | 2008 | 1050 | [5 empty] | 2550000 | 829000 | 226000 | 233000 | 46000 | 324000 | 684160.58 | 32.51% | 2010-07-01 | 2011-08-22 | 0 | 0 | 0.022278 | 0.047722 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 48470 | MEN | 001 | CONSTRUCT MBGR & CENTERLINE RUMBLE STRIPS, UPGRADE DRAINAGE INLETS | 1.6 | SHOPP | 2012 | 4492 |  |  |  | X |  | 2515000 | 1358000 | 30000 | 709000 | 45000 | 574000 | 557756.18 | 54% | 2013-08-01 | 2014-06-15 | 0 | 0.44895 | 0.030411 | 1.1206 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 48860 | LAK | 020 | IMPROVE INTERSECTION | 1.2144 | SHOPP | 2012 | 3073 |  | X | X |  |  | 4659000 | 1698000 | 286000 | 587000 | 316000 | 509000 | 435048.53 | 36.45% | 2014-06-15 | 2015-07-01 | 0 | 0 | 0.02445 | 1.1899 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 49070 | MEN | 020 | OGAC OVERLAY, CENTERLINE RUMBLE STRIPS, UPGRADE MBGR | 0.32 | SHOPP | 2010 | 4503 | [5 empty] | 3584000 | 1040000 | E | 613000 | 24000 | 403000 | 478007.45 | 29.02% | 2012-04-19 | 2012-11-07 | 0 | 0 | 0 | 0.32 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 49080 | MEN | 101 | INSTALL CENTERLINE RUMBLE STRIPS & SHOULDER RUMBLE STRIPS, WIDEN | 0.02 | SHOPP | 2010 | 4504 | [5 empty] | 538000 | 373000 | E | 189000 | 12000 | 172000 | 290607.86 | 69.33% | 2011-09-08 | 2012-10-22 | 0 | 0 | 0.013362 | 0.0066376 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 49360 | VAR | VAR | BRIDGE DECK REPAIR | 0.1 | SHOPP | 2010 | 7005 | [5 empty] | 1121000 | 366000 | 20000 | 90000 | 6000 | 250000 | 353944.32 | 32.65% | 2011-06-14 | 2012-12-15 | 0.0033677 | 0 | 0.035522 | 0.06111 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 49370 | HUM | 096 | SHOULDER WIDENING/LIGHT GUARD CROSSWALK | 2.47 | SHOPP | 2012 | 2278 | X |  |  |  |  | 1392000 | 1077000 | 271000 | 466000 | 53000 | 287000 | 0 | 77.37% | 2014-12-01 | 2016-01-31 | 0.37891 | 2.013 | 0.078118 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 49580 | VAR | VAR | INSTALL RUMBLE STRIPS | 0.02 | SHOPP | 2010 | 7006 | [5 empty] | 1018000 | 346000 | 81000 | 102000 | 20000 | 143000 | 174350.41 | 33.99% | 2011-01-06 | 2011-06-14 | 0 | 0 | 0.0048896 | 0.01511 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 49650 | HUM | 101 | EXCAVATE HAZARDOUS WASTE | 2.5667 | SHOPP | 2012 | 2284 |  | X | X |  |  | 2150000 | 1280000 | 298000 | 520000 | 72000 | 390000 | 75736.1 | 59.53% | 2014-04-01 | 2015-05-01 | 0 | 0 | 0 | 2.5667 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 49710 | MEN | 271 | HAZARDOUS WASTE MITIGATION | 1.41 | SHOPP | 2012 | 4510 |  | X | X |  |  | 556000 | 501000 | 159000 | 162000 | 27000 | 153000 | 107371.13 | 90.11% | 2014-03-01 | 2015-05-15 | 0 | 0.67847 | 0.43715 | 0.29438 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 49771 | MEN | 001 | PERMANENT RESTORATION: REPAIR SLIPOUT / REPAIR DRAINAGE | 4.33 | SHOPP | 2012 | 4513 | X |  |  |  |  | 1840000 | 1350000 | 200000 | 600000 | 100000 | 450000 | 129908.32 | 73.37% | 2015-04-01 | 2016-05-01 | 0.1092 | 3.6843 | 0.53648 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 49830 | HUM | 299 | GRIND-IN SHOULDER RUMBLE STRIPS | 5 | SHOPP | 2012 | 2292 | X |  |  |  |  | 21075000 | 7279000 | 2107000 | 1536000 | 54000 | 3582000 | 0 | 34.54% | 2016-03-01 | 2017-04-01 | 2.4092 | 2.5899 | 0.00091075 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 49870 | DN | 101 | PAVEMENT OVERLAY, CENTERLINE RUMBLE STRIPS,RESTRIPE & REPLACE RECESSED | 0.16 | SHOPP | 2010 | 1063 | [5 empty] | 1898000 | 548000 | E | 213000 | 39000 | 296000 | 256844.26 | 28.87% | 2012-01-31 | 2012-09-19 | 0 | 0 | 0.034621 | 0.12538 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 49880 | HUM | 101 | PLACE HMA TYPE OG AND INSTALL CENTERLINE & RIGHT SHOULDER RUMBLE | 0.13 | SHOPP | 2010 | 2296 |  |  |  | X |  | 880000 | 259000 | 52000 | 83000 | 8000 | 116000 | 317410.04 | 29.43% | 2012-03-06 | 2013-07-01 | 0 | 0 | 0.01822 | 0.11178 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 49990 | MEN | 101 | INSTALL MEDIAN CABLE BARRIER | 0.12 | SHOPP | 2010 | 4519 | [5 empty] | 5500000 | 1870000 | 440000 | 550000 | 110000 | 770000 | 798851.83 | 34% | 2010-12-09 | 2010-02-17 | 0 | 0 | 0 | 0.12 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 0A040 | LAK | 175 | SHOULDER WIDENING | 6.42 | SHOPP | 2012 | 3080 | X |  |  |  |  | 13904000 | 6226000 | 1324000 | 2161000 | 582000 | 2159000 | 0 | 44.78% | 2016-10-01 | 2018-02-01 | 2.1517 | 3.4721 | 0.79616 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 0A100 | DN | VAR | BRIDGE SEISMIC RETROFIT | 4.35 | SHOPP | 2012 | 1065 | [5 empty] | 16316000 | 5156000 | 1219000 | 1706000 | 84000 | 2147000 | 2964.91 | 31.6% | 2017-01-01 | 2018-10-01 | 2.7092 | 1.5186 | 0.12224 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 0A230 | MEN | 020 | CONSTRUCT SIDEWALK, CURB-RAMPS & RETAINING WALL | 0.5 | SHOPP | 2012 | 4525 |  |  |  | X |  | 575000 | 85000 | H | H | H | 85000 | 572636.66 | 14.78% | 2012-07-23 | 2013-11-22 | 0 | 0 | 0.053604 | 0.4464 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 0A320 | HUM | 299 | CURVE IMPROVEMENT | 1.4157 | SHOPP | 2012 | 2305 | X | X | X |  |  | 1427000 | 1091000 | 275000 | 448000 | 54000 | 314000 | 83481.87 | 76.45% | 2014-09-01 | 2016-03-01 | 1.0912 | 0 | 0.0024251 | 0.32198 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 0A360 | HUM | 299 | CURVE IMPROVEMENT | 2.11 | SHOPP | 2012 | 2306 | X | X | X |  |  | 3046000 | 1599000 | 360000 | 596000 | 59000 | 584000 | 102934.01 | 52.5% | 2014-06-01 | 2015-07-01 | 0.21816 | 0.90669 | 0.13506 | 0.85008 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 0A370 | HUM | 299 | SHOULDER WIDENING | 1.51 | SHOPP | 2012 | 2307 | [5 empty] | 1928000 | 1284000 | 339000 | 475000 | 54000 | 416000 | 0 | 66.6% | 2016-04-01 | 2017-02-01 | 1.508 | 0 | 0.0019905 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 0A380 | HUM | 255 | REHABILITATE BRIDGE | 0.08 | SHOPP | 2010 | 2309 | [5 empty] | 1894000 | 566000 | 36000 | 121000 | 6000 | 403000 | 125525.59 | 29.88% | 2012-09-13 | 2014-09-15 | 0 | 0 | 0 | 0.08 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 0A490 | HUM | 299 | CURVE IMPROVEMENT | 4.42 | SHOPP | 2012 | 2308 | X | X | X |  |  | 4134000 | 1470000 | 398000 | 652000 | 52000 | 368000 | 69623.83 | 35.56% | 2014-09-01 | 2016-03-01 | 0.60945 | 3.5942 | 0.21632 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 0A520 | HUM | 299 | CURVE IMPROVEMENT | 3.44 | SHOPP | 2012 | 2311 | X |  |  |  |  | 2329000 | 1397000 | 526000 | 525000 | 66000 | 280000 | 0 | 59.98% | 2015-06-01 | 2016-09-01 | 1.3395 | 1.9062 | 0.1943 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 0A590 | MEN | 001 | REHAB BRIDGE DECKS | 1.8939 | SHOPP | 2010 | 4533 |  |  |  | X |  | 3730000 | 751000 | 47000 | 161000 | 8000 | 535000 | 130251.56 | 20.13% | 2012-10-26 | 2014-05-04 | 0 | 0.0073469 | 0.016733 | 1.8698 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 0A690 | LAK | 020 | INSTALL MBGR | 0.69 | SHOPP | 2012 | 3082 | X |  |  |  |  | 1254000 | 1113000 | 151000 | 329000 | 11000 | 622000 | 0 | 88.76% | 2015-05-15 | 2016-11-01 | 0.095758 | 0.58328 | 0.010959 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 0A990 | HUM | 096 | CURVE IMPROVEMENT | 1.07 | SHOPP | 2012 | 2329 | [5 empty] | 3736000 | 2313000 | 491000 | 975000 | 67000 | 780000 | 0 | 61.91% | 2018-02-01 | 2019-07-01 | 1.0478 | 0 | 0.022175 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 0B000 | LAK | 020 | REPLACE HOT MIX ASPHALT, APPLY GAP GRADED RUBBERIZED HOT MIX ASPHALT | 3.21 | SHOPP | 2012 | 3083 |  | X | X |  |  | 23558000 | 1657000 | 300000 | 380000 | 47000 | 930000 | 0 | 7.034% | 2014-05-15 | 2015-08-01 | 0 | 2.4301 | 0.10065 | 0.67921 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 0B030 | HUM | 096 | CURVE IMPROVEMENT | 3.14 | SHOPP | 2012 | 2328 | X |  |  |  |  | 1895000 | 1137000 | 363000 | 417000 | 67000 | 290000 | 0 | 60% | 2015-01-01 | 2016-12-01 | 0.34558 | 2.5783 | 0.21611 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 0B080 | DN | 101 | AC OVERLAY | 1.84 | SHOPP | 2012 | 1071 |  | X | X |  |  | 3218000 | 575000 | 100000 | 85000 | 15000 | 375000 | 0 | 17.87% | 2014-01-31 | 2015-09-15 | 0.087259 | 1.1828 | 0.044699 | 0.52522 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 0B100 | HUM | 101 | INSTALL CABLE MEDIAN BARRIER | 1.14 | SHOPP | 2012 | 2330 |  |  |  | X |  | 986000 | 556000 | 141000 | 267000 | 14000 | 134000 | 75829.76 | 56.39% | 2013-08-15 | 2014-06-15 | 0 | 0.20972 | 0.034923 | 0.89536 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 0B120 | LAK | 020 | UPGRADE CURB RAMPS & SIDEWALK | 1.73 | SHOPP | 2012 | 3086 | X |  |  |  |  | 1322000 | 1037000 | 109000 | 252000 | 445000 | 231000 | 0 | 78.44% | 2016-03-02 | 2016-12-01 | 0.61516 | 0.92722 | 0.18762 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 0B190 | HUM | 101 | INSTALL MEDIAN BARRIER | 0.89 | SHOPP | 2012 | 2331 | [5 empty] | 1105000 | 706000 | 222000 | 270000 | 49000 | 165000 | 134457.93 | 63.89% | 2013-07-24 | 2014-09-01 | 0 | 0.11526 | 0.049123 | 0.72562 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 0B260 | DN | 199 | SHOULDER WIDENING | 0.85 | SHOPP | 2012 | 1076 | [5 empty] | 4327000 | 3436000 | 1035000 | 685000 | 33000 | 1683000 | 0 | 79.41% | 2018-06-01 | 2020-12-01 | 0.85 | 0 | 0 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 0B270 | DN | 101 | REPAIR ROADWAY FAILURES | 3.8094 | SHOPP | 2012 | 1077 |  | X | X |  |  | 4410000 | 2634000 | 437000 | 1311000 | 8000 | 878000 | 111811.85 | 59.73% | 2013-11-15 | 2015-08-01 | 0.1461 | 2.0387 | 0.057557 | 1.567 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 0B280 | DN | 101 | RECONSTRUCT ROADWAY | 6.0585 | SHOPP | 2012 | 1078 | X | X | X |  |  | 1660000 | 990000 | 164000 | 492000 | 4000 | 330000 | 52652.09 | 59.64% | 2013-12-15 | 2015-10-01 | 0.78632 | 4.0299 | 0.32994 | 0.91226 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 0B290 | DN | 101 | REPAIR SLIPOUTS | 1.08 | SHOPP | 2012 | 1079 | X | X | X |  |  | 1010000 | 600000 | 99000 | 297000 | 4000 | 200000 | 16028.18 | 59.41% | 2013-12-15 | 2015-10-01 | 0.063106 | 0.82964 | 0.063025 | 0.12423 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 0B300 | DN | 101 | STABILIZE ROADWAY | 2.2484 | SHOPP | 2012 | 1080 | X | X | X |  |  | 1510000 | 900000 | 149000 | 447000 | 4000 | 300000 | 95441 | 59.6% | 2013-12-15 | 2015-10-01 | 0.13769 | 1.6775 | 0.1257 | 0.30752 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 0B310 | DN | 199 | CONSTRUCT BUTTRESSES | 1.3362 | SHOPP | 2012 | 1081 | X | X | X |  |  | 1270000 | 750000 | 123000 | 369000 | 8000 | 250000 | 48593.45 | 59.06% | 2014-03-01 | 2015-10-01 | 0.12964 | 0.90108 | 0.015543 | 0.28993 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 0B320 | DN | 199 | CONSTRUCT SOLDIER PILE WALL | 2.1323 | SHOPP | 2012 | 1082 | X | X | X |  |  | 3010000 | 1800000 | 299000 | 897000 | 4000 | 600000 | 36672.17 | 59.8% | 2014-03-01 | 2015-10-01 | 0.1806 | 1.3524 | 0.015057 | 0.58428 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 0B330 | DN | 199 | RECONSTRUCT ROADWAY & DRAINAGE | 2.12 | SHOPP | 2012 | 1083 | X | X | X |  |  | 860000 | 510000 | 84000 | 252000 | 4000 | 170000 | 34216.76 | 59.3% | 2014-05-18 | 2015-12-18 | 0.067258 | 1.0413 | 0.89476 | 0.11668 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 0B340 | HUM | 036 | RECONSTRUCT ROADWAY & DRAINAGE | 1.91 | SHOPP | 2012 | 2332 | X | X | X |  |  | 1415000 | 846000 | 141000 | 421000 | 2000 | 282000 | 95622.53 | 59.79% | 2013-12-15 | 2015-10-01 | 0.059748 | 1.5715 | 0.069805 | 0.20895 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 0B350 | HUM | 036 | STABILIZE ROADWAY | 1.9375 | SHOPP | 2012 | 2333 | X | X | X |  |  | 1355000 | 811000 | 135000 | 404000 | 2000 | 270000 | 129187.88 | 59.85% | 2013-12-15 | 2015-10-01 | 0.24259 | 1.2957 | 0.14466 | 0.25454 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 0B360 | HUM | 036 | RECONSTRUCT ROADWAY & DRAINAGE | 2.43 | SHOPP | 2012 | 2334 | X | X | X |  |  | 4830000 | 2778000 | 443000 | 1329000 | 80000 | 926000 | 74135.85 | 57.52% | 2013-12-15 | 2015-10-01 | 0.059337 | 1.6637 | 0.10346 | 0.60352 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 0B370 | HUM | 036 | SLIDE REPAIR | 2.4818 | SHOPP | 2012 | 2335 | X | X | X |  |  | 1610000 | 960000 | 159000 | 477000 | 4000 | 320000 | 48409.09 | 59.63% | 2013-12-15 | 2015-10-01 | 0.14264 | 1.5983 | 0.16065 | 0.58028 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 0B380 | HUM | 096 | SLIDE REPAIR | 2.3729 | SHOPP | 2012 | 2336 | X | X | X |  |  | 1610000 | 960000 | 159000 | 477000 | 4000 | 320000 | 16360.98 | 59.63% | 2013-12-15 | 2015-10-01 | 0.11969 | 1.5932 | 0.12748 | 0.53257 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 0B390 | HUM | 096 | STABILIZE ROADWAY | 2.58 | SHOPP | 2012 | 2337 | X | X | X |  |  | 8010000 | 4800000 | 799000 | 2397000 | 4000 | 1600000 | 75559.8 | 59.93% | 2014-02-15 | 2015-12-03 | 0.26586 | 2.0316 | 0.10283 | 0.17973 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 0B400 | HUM | 101 | RECONSTRUCT ROADWAY & DRAINAGE | 3.9958 | SHOPP | 2012 | 2338 | X | X | X |  |  | 2190000 | 1308000 | 217000 | 651000 | 4000 | 436000 | 29866.19 | 59.73% | 2013-12-15 | 2015-10-01 | 0.071171 | 2.8584 | 0.17735 | 0.88886 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 0B410 | HUM | 101 | RECONSTRUCT ROADWAY & DEWATER | 2.6 | SHOPP | 2012 | 2339 | X | X | X |  |  | 1455000 | 871000 | 145000 | 434000 | 2000 | 290000 | 36771.39 | 59.86% | 2013-12-15 | 2015-10-01 | 0.054962 | 2.1641 | 0.090088 | 0.2909 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 0B420 | HUM | 101 | CONSTRUCT BUTTRESSES & DEWATER | 3.9872 | SHOPP | 2012 | 2340 | X | X | X |  |  | 1970000 | 1170000 | 193000 | 579000 | 8000 | 390000 | 71667.65 | 59.39% | 2014-01-28 | 2015-11-14 | 0.089342 | 1.1657 | 2.5078 | 0.22425 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 0B430 | HUM | 101 | BIG LAGOON SLIPOUT REPAIR | 4.3759 | SHOPP | 2012 | 2341 |  | X | X |  |  | 4505000 | 2701000 | 450000 | 1349000 | 2000 | 900000 | 236363.32 | 59.96% | 2013-12-15 | 2015-10-01 | 0.54194 | 3.4392 | 0.12117 | 0.27361 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 0B440 | HUM | 169 | REPAIR SLIPOUTS | 4.0282 | SHOPP | 2012 | 2342 | X | X | X |  |  | 2800000 | 1662000 | 274000 | 822000 | 12000 | 554000 | 117272.2 | 59.36% | 2013-12-15 | 2015-10-01 | 0.13885 | 3.2871 | 0.050101 | 0.55212 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 0B450 | HUM | 299 | REPAIR SLIDES & SLIPOUTS | 1.6474 | SHOPP | 2012 | 2343 | X | X | X |  |  | 2590000 | 1536000 | 253000 | 759000 | 12000 | 512000 | 50153.86 | 59.31% | 2013-12-15 | 2015-10-01 | 0.17966 | 0.79924 | 0.48654 | 0.18198 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 0B460 | HUM | 299 | STABILIZE ROADWAY | 2.3976 | SHOPP | 2012 | 2344 | X | X | X |  |  | 1360000 | 810000 | 134000 | 402000 | 4000 | 270000 | 25021.16 | 59.56% | 2013-12-15 | 2015-10-01 | 0.17491 | 1.8431 | 0.040825 | 0.3388 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 0B470 | MEN | 001 | REPAIR SLIPOUT | 1.44 | SHOPP | 2012 | 4547 |  | X | X |  |  | 550000 | 270000 | 35000 | 105000 | 40000 | 90000 | 43757.5 | 49.09% | 2014-02-15 | 2015-07-15 | 0.54237 | 0.88608 | 0.011552 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 0B490 | MEN | 001 | REPAIR SLIPOUTS | 2.59 | SHOPP | 2012 | 4549 | X | X | X |  |  | 1460000 | 780000 | 114000 | 342000 | 64000 | 260000 | 54893.91 | 53.42% | 2014-04-01 | 2015-09-15 | 1.0329 | 1.4905 | 0.066572 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 0B500 | MEN | 101 | REPAIR SLIDES | 2.7684 | SHOPP | 2012 | 4550 | X | X | X |  |  | 7400000 | 2710000 | 370000 | 1110000 | 120000 | 1110000 | 232962.7 | 36.62% | 2014-02-15 | 2015-07-15 | 0.037639 | 1.6583 | 0.14934 | 0.92314 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 0B510 | MEN | 101 | REPAIR SLIDES & SLIPOUT | 4.083 | SHOPP | 2012 | 4551 | X | X | X |  |  | 2670000 | 1530000 | 243000 | 729000 | 48000 | 510000 | 84093.32 | 57.3% | 2014-03-15 | 2015-08-15 | 0.15131 | 3.0742 | 0.14012 | 0.7174 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 0B520 | MEN | 128 | STABILIZE ROADWAY | 4.92 | SHOPP | 2012 | 4552 | X | X | X |  |  | 3900000 | 2280000 | 370000 | 1110000 | 40000 | 760000 | 82641.73 | 58.46% | 2014-05-31 | 2015-10-31 | 0.16915 | 4.1593 | 0.56806 | 0.023468 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 0B540 | MEN | 162 | REPAIR SLIPOUTS | 3.64 | SHOPP | 2012 | 4554 | X | X | X |  |  | 1890000 | 1050000 | 161000 | 483000 | 56000 | 350000 | 118169.03 | 55.56% | 2014-04-18 | 2015-09-15 | 0.52887 | 2.0538 | 0.4646 | 0.59271 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 0B550 | MEN | 162 | STABILIZE ROADWAY | 3.2328 | SHOPP | 2012 | 4555 | X | X | X |  |  | 2900000 | 1680000 | 270000 | 810000 | 40000 | 560000 | 149315.77 | 57.93% | 2014-03-17 | 2015-08-14 | 0.082771 | 2.3536 | 0.27953 | 0.51692 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 0B560 | MEN | 253 | BOONVILLE SLIDE | 0.74 | SHOPP | 2012 | 4556 | X | X | X |  |  | 710000 | 390000 | 59000 | 177000 | 24000 | 130000 | 25080.51 | 54.93% | 2014-04-15 | 2015-09-15 | 0.13688 | 0.46135 | 0.028706 | 0.11306 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 0B570 | MEN | 253 | STABILIZE ROADWAY | 2.945 | SHOPP | 2012 | 4557 | X | X | X |  |  | 2510000 | 1500000 | 249000 | 747000 | 4000 | 500000 | 70827.04 | 59.76% | 2014-03-15 | 2015-08-15 | 0.10572 | 2.4006 | 0.020343 | 0.41831 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 0B63U | HUM | 101 | PLACE HIGH FRICTION COURSE TREATMENT | 0.43 | SHOPP | 2012 | 2303 |  |  |  | X |  | 1351000 | 437000 | E | 219000 | 16000 | 202000 | 151888.47 | 32.35% | 2012-07-31 | 2013-09-15 | 0 | 0 | 0.028773 | 0.40123 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 0B850 | HUM | 101 | REPAIR SLIDE | 0.41 | SHOPP | 2010 | 2353 | [5 empty] | 1510000 | 320000 | R | R | 20000 | 300000 | 186697.91 | 21.19% | - - | 2012-10-30 | 0.015007 | 0.025792 | 0 | 0.3692 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 0C120 | MEN | 001 | REPAIR SLIPOUT | 0.53 | SHOPP | 2012 | 4565 | X | X | X |  |  | 475000 | 276000 | 46000 | 115000 | 23000 | 92000 | 0 | 58.11% | 2014-08-01 | 2016-01-01 | 0.093399 | 0.40827 | 0.028335 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 0C180 | HUM | 169 | REPAIR SLIPOUT | 0.53513 | SHOPP | 2010 | 2356 | [5 empty] | 3650000 | 1460000 | R | R | 60000 | 1400000 | 290117.1 | 40% | - - | - - | 0 | 0 | 0 | 0.53513 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 0C190 | DN | 199 | REPAIR SLIDE | 0.61 | SHOPP | 2010 | 1088 | [5 empty] | 422000 | 190000 | R | R | 20000 | 170000 | 33280.79 | 45.02% | - - | - - | 0 | 0 | 0 | 0.61 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 0C200 | LAK | 053 | REPAIR STORM DAMAGE | 0.58 | SHOPP | 2010 | 3091 | [5 empty] | 500000 | 220000 | R | R | 20000 | 200000 | 29268.93 | 44% | - - | 2012-10-26 | 0 | 0 | 0 | 0.58 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 0C210 | MEN | 101 | REPAIR SLIDE | 0.66 | SHOPP | 2010 | 4560 | [5 empty] | 420000 | 200000 | R | R | 40000 | 160000 | 38655.07 | 47.62% | - - | 2012-05-24 | 0 | 0 | 0 | 0.66 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 0C230 | MEN | 162 | REPAIR SLIDE | 0.7 | SHOPP | 2010 | 4568 | [5 empty] | 1550000 | 640000 | R | R | 40000 | 600000 | 44049.24 | 41.29% | - - | 2012-05-29 | 0.11053 | 0 | 0 | 0.58947 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 0C240 | DN | 101 | REPAIR SLIPOUT | 0.54 | SHOPP | 2010 | 1090 | [5 empty] | 930000 | 330000 | R | R | 20000 | 310000 | 206896.59 | 35.48% | - - | 2012-10-30 | 0.017078 | 0 | 0 | 0.52292 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 0C250 | DN | 197 | REPAIR SLIDE | 0.51589 | SHOPP | 2010 | 1089 | [5 empty] | 560000 | 240000 | R | R | 20000 | 220000 | 59234.7 | 42.86% | - - | 2012-10-30 | 0 | 0 | 0 | 0.51589 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 0C260 | DN | 101 | REPAIR SLIPOUT | 0.4 | SHOPP | 2010 | 1091 | [5 empty] | 320000 | 130000 | H | H | H | 130000 | 35539.84 | 40.62% | - - | - - | 0 | 0 | 0 | 0.4 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 0C270 | MEN | 001 | REPAIR SLIDE | 0.57 | SHOPP | 2010 | 4569 | [5 empty] | 550000 | 200000 | R | R | 20000 | 180000 | 34893.5 | 36.36% | - - | 2013-01-25 | 0.0065386 | 0 | 0 | 0.56346 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 0C280 | HUM | 101 | REPAIR SLIDE | 0.57 | SHOPP | 2010 | 2357 | [5 empty] | 310000 | 140000 | R | R | 20000 | 120000 | 26601.62 | 45.16% | - - | 2012-07-23 | 0 | 0 | 0 | 0.57 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 0C300 | HUM | 096 | REPAIR SLIPOUT | 0.58322 | SHOPP | 2010 | 2359 | [5 empty] | 2110000 | 800000 | R | R | 60000 | 740000 | 367572.2 | 37.91% | - - | - - | 0 | 0 | 0 | 0.58322 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 0C310 | HUM | 101 | DRAINAGE REPAIR (STORM DAMAGE) | 0.57 | SHOPP | 2010 | 2360 | [5 empty] | 280000 | 122000 | R | R | 10000 | 112000 | 14887.13 | 43.57% | - - | 2012-07-19 | 0 | 0 | 0 | 0.57 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 0C320 | HUM | 200 | REPAIR SLIDE | 0.57 | SHOPP | 2010 | 2361 | [5 empty] | 450000 | 200000 | R | R | 40000 | 160000 | 10780.6 | 44.44% | - - | 2010-09-28 | 0 | 0 | 0 | 0.57 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 0C330 | HUM | 299 | REPAIR SLIDE | 0.57 | SHOPP | 2010 | 2362 | [5 empty] | 410000 | 180000 | R | R | 20000 | 160000 | 38621.22 | 43.9% | - - | 2012-09-24 | 0 | 0 | 0 | 0.57 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 0C340 | MEN | 001 | REPAIR CULVERT -REPAIR STORM DAMAGE | 0.61 | SHOPP | 2010 | 4570 | [5 empty] | 620000 | 260000 | R | R | 20000 | 240000 | 82114.32 | 41.94% | - - | 2012-12-26 | 0 | 0 | 0 | 0.61 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 0C360 | MEN | 101 | INSTALL HIGH FRICTION COURSE TREATMENT | 3.4276 | SHOPP | 2012 | 4575 | [5 empty] | 919000 | 670000 | 138000 | 282000 | 19000 | 231000 | 0 | 72.91% | 2013-08-15 | 2014-10-15 | 0 | 0 | 0 | 3.4276 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 0C380 | DN | 101 | REPAIR SLIPOUT | 0.61 | SHOPP | 2010 | 1092 | [5 empty] | 410000 | 220000 | R | R | 20000 | 200000 | 46226.74 | 53.66% | - - | - - | 0.0032948 | 0 | 0 | 0.60671 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 0C390 | DN | 101 | REPAIR SLIPOUT | 1.2695 | SHOPP | 2010 | 1093 | [5 empty] | 4850000 | 2000000 | R | R | 200000 | 1800000 | 326285.5 | 41.24% | - - | - - | 0 | 0 | 0 | 1.2695 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 0C510 | VAR | VAR | INSTALL HIGH FRICTION SURFACE TREATMENT | 0.66 | SHOPP | 2012 | 7010 |  |  |  | X |  | 805000 | 240000 | 48000 | 75000 | 21000 | 96000 | 0 | 29.81% | 2013-05-01 | 2013-07-15 | 0 | 0.01655 | 0.071989 | 0.57146 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 0C560 | HUM | 101 | REPAIR STORM DAMAGE (CULVERT) | 1 | SHOPP | 2012 | 2367 | [5 empty] | 360000 | 150000 | R | R | 10000 | 140000 | 33744.2 | 41.67% | - - | 2012-10-09 | 0 | 0 | 0 | 1 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 0C620 | LAK | 020 | MAJOR DAMAGE WILD FIRES | 0.47 | SHOPP | 2012 | 3094 | [5 empty] | 1210000 | 150000 | R | R | 10000 | 140000 | 1963.53 | 12.4% | - - | - - | 0.0070486 | 0 | 0 | 0.46295 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 3116U | MEN | 253 | WIDEN BRIDGES AND UPGRADE RAIL | 0.1 | SHOPP | 2006 | 0219 | [5 empty] | 4350000 | 2557000 | 2557000 | F | F | F | 4276473.1 | 58.78% | 2008-01-29 | 2010-11-19 | 0 | 0 | 0.031883 | 0.068117 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 3633U | HUM | 101 | HMA OVERLAY AND RECONSTRUCT MBGR | 1.5 | SHOPP | 2010 | 0071Y |  |  |  | X |  | 17765000 | 6883000 | 3010000 | 2283000 | 90000 | 1500000 | 76659.9 | 38.74% | 2012-10-18 | 2014-01-15 | 0 | 0 | 0.10882 | 1.3912 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 3637U | MEN | 128 | CAPTIAL PREVENTATIVE MAINTENANCE | 2.11 | SHOPP | 2010 | 0139G |  |  |  | X |  | 12890000 | 2648000 | 40000 | 1044000 | 40000 | 1524000 | 336137.85 | 20.54% | 2011-10-06 | 2013-10-15 | 0 | 0 | 0.057549 | 2.0525 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 3986U | LAK | 053 | WIDEN ROADWAY WITH HMA OVER AB | 2.34 | SHOPP | 2008 | 0129I | [5 empty] | 17192000 | 5534000 | 939000 | 1338000 | 576000 | 2681000 | 4763753.7 | 32.19% | 2011-01-05 | 2014-10-01 | 0 | 0 | 0.34283 | 1.9972 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 3994U | LAK | 175 | HMA OVERLAY RECONSTRUCT MBGR | 0.02 | SHOPP | 2010 | 0130B | [5 empty] | 18560000 | 3769000 | 40000 | 1499000 | 40000 | 2190000 | 1459209.85 | 20.31% | 2011-06-15 | 2012-08-10 | 0 | 0 | 0.0082957 | 0.011704 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 4146V | LAK | 020 | REHABILITATE ROADWAY AND REALIGN CURVES | 0.2 | SHOPP | 2006 | 0119C | [5 empty] | 20165000 | 7311000 | 7311000 | F | F | F | 7472853.74 | 36.26% | 2006-09-14 | 2009-11-05 | 0 | 0 | 0.025413 | 0.17459 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | 4500U | DN | 199 | WIDENING | 4.19 | SHOPP | 2012 | 1073 |  | X | X |  |  | 4700000 | 2050000 | 300000 | 700000 | 150000 | 900000 | 802116.37 | 43.62% | 2014-02-15 | 2016-12-01 | 0 | 1.2824 | 2.5783 | 0.32929 | Caltrans | Caltrans | Caltrans | Caltrans
01 | SHOPP | MINOR |  |  | SHOPP MINOR | 13.6613 | MINOR
02 | SHOPP | 0E090 | SHA | 005 | SEISMIC RETROFIT DOG CREEK BR | 4.2432 | SHOPP | 2012 | 3346 | X |  |  |  |  | 11043000 | 3771000 | 671000 | 1278000 | 52000 | 1770000 | 0 | 34.15% | 2019-08-22 | 2019-11-07 | 0.74864 | 0 | 0.01593 | 3.4787 | Caltrans | Caltrans | Caltrans | Caltrans
02 | SHOPP | 0E300 | SHA | 005 | REPAIR SLOPE WITH RSP | 0.7297 | SHOPP | 2006 | 3357 | [5 empty] | 345000 | 210000 | 210000 | F | F | F | 261060.53 | 60.87% | 2008-09-15 | 2008-11-26 | 0.7297 | 0 | 0 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
02 | SHOPP | 0E200 | LAS | 036 | REHABILITATE PAVEMENT | 1.2198 | SHOPP | 2008 | 3351 | [5 empty] | 6600000 | 760000 | 5000 | 50000 | 5000 | 700000 | 596212.12 | 11.52% | 2010-12-08 | 2011-12-22 | 0 | 0 | 0 | 1.2198 | Caltrans | Caltrans | Caltrans | Caltrans
02 | SHOPP | 0E180 | PLU | 089 | DECK REPLACEMENT | 3.1513 | SHOPP | 2012 | 3349 | [5 empty] | 9060000 | 4300000 | 1100000 | 1300000 | 300000 | 1600000 | 1009.95 | 47.46% | 2016-09-01 | 2019-01-07 | 1.7204 | 1.3486 | 0.08229 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
02 | SHOPP | 2E000 | PLU | 070 | HOT MIX ASPHALT | 0.26973 | SHOPP | 2010 | 3414 | [5 empty] | 2200000 | 908000 | 228000 | 212000 | 96000 | 372000 | 941197.03 | 41.27% | 2010-12-16 | 2011-08-31 | 0 | 0 | 0 | 0.26973 | Caltrans | Caltrans | Caltrans | Caltrans
02 | SHOPP | 25147 | TEH | 099 | BRIDGE REPLACEMENT (SCOUR) | 0.20973 | SHOPP | 2004 | 8420 | [5 empty] | 6371000 | 1329000 | 1329000 | F | F | F | 4193294.63 | 20.86% | 2006-02-16 | 2007-10-09 | 0 | 0 | 0 | 0.20973 | Caltrans | Caltrans | Caltrans | Caltrans
02 | SHOPP | 25850 | LAS | 395 | ROADWAY REHABILITATION | 0.03099 | SHOPP | 2002 | 0022H | [5 empty] | 9820000 | 2602000 | 2602000 | F | F | F | 3201587.51 | 26.5% | 2003-03-24 | 2009-09-17 | 0 | 0 | 0 | 0.03099 | Caltrans | Caltrans | Caltrans | Caltrans
02 | SHOPP | 26336 | PLU | 070 | ROADWAY REHABILITATION | 0.30065 | SHOPP | 2002 | 0076L | [5 empty] | 5413000 | 1622000 | 1622000 | F | F | F | 2459578.313 | 29.96% | 2002-10-11 | 2003-11-13 | 0 | 0 | 0 | 0.30065 | Caltrans | Caltrans | Caltrans | Caltrans
02 | SHOPP | 29592 | TEH | 099 | REPLACE BRIDGE #8-11 | 0.39175 | SHOPP | 2004 | 8630A | [5 empty] | 5075000 | 1483000 | 1483000 | F | F | F | 2396621.862 | 29.22% | 2005-11-02 | 2006-12-12 | 0 | 0 | 0 | 0.39175 | Caltrans | Caltrans | Caltrans | Caltrans
02 | SHOPP | 30170 | TEH | 005 | CONSTRUCT NORTHBOUND MEDIAN LANE | 0.35833 | SHOPP | 2004 | 8150 | [5 empty] | 4354000 | 1523000 | 1523000 | F | F | F | 1684079.59 | 34.98% | 2005-10-19 | 2006-12-15 | 0 | 0 | 0 | 0.35833 | Caltrans | Caltrans | Caltrans | Caltrans
02 | SHOPP | 30171 | TEH | 005 | CONSTRUCT TRUCK CLIMBING LANE IRDAP #8130A | 0.59497 | SHOPP | 2004 | 8130 | [5 empty] | 5963000 | 1545000 | 1545000 | F | F | F | 1888390.76 | 25.91% | 2005-10-11 | 2007-02-02 | 0 | 0 | 0 | 0.59497 | Caltrans | Caltrans | Caltrans | Caltrans
02 | SHOPP | 31040 | SHA | 089 | RESURFACE ASPHALT CONCRETE | 0.68881 | SHOPP | 2004 | 0157 | [5 empty] | 20550000 | 2384000 | 2384000 | F | F | F | 8820249.49 | 11.6% | 2005-08-10 | 2008-02-25 | 0 | 0 | 0.1545 | 0.53431 | Caltrans | Caltrans | Caltrans | Caltrans
02 | SHOPP | 32503 | LAS | 395 | DEVELOP WETLANDS MITIGATION BANK | 0.23946 | SHOPP | 1998 | 3490 | [5 empty] | 430000 | 276000 | H | 20000 | 3000 | 253000 | 257927.18 | 64.19% | 2003-11-05 | 2004-04-23 | 0 | 0 | 0 | 0.23946 | Caltrans | Caltrans | Caltrans | Caltrans
02 | SHOPP | 36070 | SHA | 299 | ROADWAY REHABILITATION | 10.6073 | SHOPP | 2012 | 3017 | [5 empty] | 30092000 | 9300000 | 2000000 | 2500000 | 1000000 | 3800000 | 3708823.54 | 30.91% | 2013-11-06 | 2015-11-03 | 0 | 5.08 | 0.5 | 5.0273 | Caltrans | Caltrans | Caltrans | Caltrans
02 | SHOPP | 37430 | TRI | 299 | RAIL UPGRADE, WIDEN | 1.128 | SHOPP | 2012 | 3085 |  |  |  | X |  | 1724000 | 1173000 | 142000 | 550000 | 44000 | 437000 | 497616.52 | 68.04% | 2012-09-16 | 2013-08-06 | 0 | 0 | 0 | 1.128 | Caltrans | Caltrans | Caltrans | Caltrans
02 | SHOPP | 37781 | PLU | 070 | REPLACE SAFETY ROADSIDE REST AREA | 0.1131 | SHOPP | 2008 | 3333 | [5 empty] | 3200000 | 2075000 | 160000 | 788000 | 7000 | 1120000 | 1850780.33 | 64.84% | 2009-07-23 | 2011-07-01 | 0 | 0 | 0 | 0.1131 | Caltrans | Caltrans | Caltrans | Caltrans
02 | SHOPP | 37890 | SHA | 005 | BRIDGE REPLACEMENT (ANTLER) | 24.8565 | SHOPP | 2008 | 3090 | [5 empty] | 135020000 | 33919000 | 2765000 | 7870000 | 645000 | 22639000 | 23302767.47 | 25.12% | 2009-09-25 | 2015-07-15 | 0 | 0 | 0.56 | 24.2965 | Caltrans | Caltrans | Caltrans | Caltrans
02 | SHOPP | 38160 | LAS | 395 | SHOULDER WIDENING AND RUMBLE STRIP | 1.3328 | SHOPP | 2006 | 3096 | [5 empty] | 30094000 | 5596000 | 5596000 | F | F | F | 6215308.48 | 18.6% | 2007-01-23 | 2008-11-13 | 0 | 0 | 0 | 1.3328 | Caltrans | Caltrans | Caltrans | Caltrans
02 | SHOPP | 39790 | SHA | 299 | REALIGN CURVE AND IMPROVE DRAINAGE | 0.18051 | SHOPP | 2006 | 3143 | [5 empty] | 3324000 | 1427000 | 1427000 | F | F | F | 2158831.33 | 42.93% | 2008-05-09 | 2009-10-12 | 0 | 0 | 0 | 0.18051 | Caltrans | Caltrans | Caltrans | Caltrans
02 | SHOPP | 2E060 | TRI | 036 | REALIGN AND WIDEN ROADWAY | 0.04179 | SHOPP | 2008 | 3415 | [5 empty] | 1100000 | 651000 | 176000 | 175000 | 55000 | 245000 | 468404.6 | 59.18% | 2010-09-01 | 2011-11-30 | 0 | 0 | 0 | 0.04179 | Caltrans | Caltrans | Caltrans | Caltrans
02 | SHOPP | 1E080 | SIS | 097 | PAVEMENT REHABILITATION | 0.82173 | SHOPP | 2008 | 3385 | [5 empty] | 12000000 | 1804000 | 12000 | 272000 | 29000 | 1491000 | 424137.75 | 15.03% | 2011-01-03 | 2012-03-02 | 0 | 0 | 0.00225 | 0.81948 | Caltrans | Caltrans | Caltrans | Caltrans
02 | SHOPP | 2E200 | TRI | 299 | IMPROVE SUPERELEVATION, WIDEN SHOULDERS | 0.77913 | SHOPP | 2010 | 3419 | [5 empty] | 1383000 | 652000 | 140000 | 197000 | 37000 | 278000 | 861658.09 | 47.14% | 2011-09-08 | 2013-01-14 | 0 | 0 | 0.02397 | 0.75516 | Caltrans | Caltrans | Caltrans | Caltrans
02 | SHOPP | 2E240 | SHA | 005 | INSTALL MEDIAN BARRIER | 0.16269 | SHOPP | 2010 | 3420 |  |  |  | X |  | 1535000 | 550000 | 145000 | 175000 | 2000 | 228000 | 441588.19 | 35.83% | 2011-04-25 | 2013-11-29 | 0 | 0 | 0.00039 | 0.1623 | Caltrans | Caltrans | Caltrans | Caltrans
02 | SHOPP | 2E291 | SIS | 096 | BRIDGE MAINTENANCE SIS CO BRIDGE PREVENT MAINT | 2.9262 | SHOPP | 2012 | 3491 | [5 empty] | 7069000 | 1020000 | 5000 | 10000 | 5000 | 1000000 | 11818.35 | 14.43% | 2012-12-26 | 2016-01-15 | 0 | 0 | 0 | 2.9262 | Caltrans | Caltrans | Caltrans | Caltrans
02 | SHOPP | 0C410 | TEH | 036 | CURVE IMPROVEMENT | 0.05131 | SHOPP | 2006 | 3161 | [5 empty] | 1572000 | 730000 | 730000 | F | F | F | 868287.35 | 46.44% | 2007-02-23 | 2007-08-17 | 0 | 0 | 0 | 0.05131 | Caltrans | Caltrans | Caltrans | Caltrans
02 | SHOPP | 0C590 | SHA | 005 | INSTALL ITS | 0.76373 | SHOPP | 2010 | 3165 | [5 empty] | 4921000 | 2191000 | 220000 | 730000 | 338000 | 903000 | 1380500.72 | 44.52% | 2010-11-23 | 2013-01-31 | 0 | 0 | 0 | 0.76373 | Caltrans | Caltrans | Caltrans | Caltrans
02 | SHOPP | 0C970 | TEH | 005 | REPLACE BRIDGE THOMES CREEK / BR #08-0085R/L | 1.1255 | SHOPP | 2006 | 3176 | [5 empty] | 39377000 | 8634000 | 8634000 | F | F | F | 6703842.54 | 21.93% | 2008-05-23 | 2011-11-10 | 0 | 0 | 0.18239 | 0.9431 | Caltrans | Caltrans | Caltrans | Caltrans
02 | SHOPP | 0E360 | TEH | 005 | REBUILD N/B & S/B FACILITIES AT CORNING SRRA'S | 2.7619 | SHOPP | 2012 | 3359 | [5 empty] | 8527000 | 3040000 | 25000 | 1200000 | 15000 | 1800000 | 960969.7 | 35.65% | 2013-10-30 | 2016-02-10 | 0 | 0.90661 | 0.0117 | 1.8436 | Caltrans | Caltrans | Caltrans | Caltrans
02 | SHOPP | 0E530 | TEH | 099 | PAVEMENT REHABILITATION | 0.02836 | SHOPP | 2008 | 3375 | [5 empty] | 10400000 | 485000 | 58000 | 107000 | 4000 | 316000 | 672246.41 | 4.663% | 2011-01-13 | 2012-08-09 | 0 | 0 | 0 | 0.02836 | Caltrans | Caltrans | Caltrans | Caltrans
02 | SHOPP | 1C370 | SIS | 089 | MODIFY HORIZONTAL CURVE | 0.22381 | SHOPP | 2006 | 3189 | [5 empty] | 3766000 | 1120000 | 1120000 | F | F | F | 1308411.09 | 29.74% | 2007-10-25 | 2008-10-10 | 0 | 0 | 0.07367 | 0.15014 | Caltrans | Caltrans | Caltrans | Caltrans
02 | SHOPP | 1C750 | PLU | 070 | BRIDGE REPLACEMENT | 6.4 | SHOPP | 2012 | 3208 | X |  |  |  |  | 6600000 | 3600000 | 880000 | 1220000 | 140000 | 1360000 | 538641.66 | 54.55% | 2015-08-14 | 2018-01-05 | 4.02 | 2.01 | 0.37 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
02 | SHOPP | 1E10U | SHA | 299 | INCREASE CURVE RADII, WIDEN SHOULDER | 5.2413 | SHOPP | 2010 | 3388 |  |  |  | X |  | 12358000 | 5034000 | 1025000 | 1419000 | 235000 | 2355000 | 2533438.81 | 40.73% | 2011-07-12 | 2013-12-11 | 0 | 0 | 0.13516 | 5.1062 | Caltrans | Caltrans | Caltrans | Caltrans
02 | SHOPP | 1E480 | SHA | 299 | INSTALL SIGNALS | 0.00675 | SHOPP | 2008 | 3404 | [5 empty] | 304000 | 548000 | 121000 | 172000 | 77000 | 178000 | 535089.88 | 180.3% | 2010-03-17 | 2011-01-19 | 0 | 0 | 0.00072 | 0.00603 | Caltrans | Caltrans | Caltrans | Caltrans
02 | SHOPP | 1E610 | SHA | 999 | PLACE METHACRYLATE OVERLAY | 0.05185 | SHOPP | 2008 | 3412 | [5 empty] | 1379000 | 856000 | 200000 | 228000 | 100000 | 328000 | 684347.2 | 62.07% | 2010-12-16 | 2012-02-06 | 0 | 0 | 0.00892 | 0.04293 | Caltrans | Caltrans | Caltrans | Caltrans
02 | SHOPP | 1E630 | SIS | 999 | PLACE POLYESTER CONCRETE AND REPLACE JOINT SEALS | 0.04348 | SHOPP | 2008 | 3413 | [5 empty] | 1175000 | 684000 | 160000 | 182000 | 80000 | 262000 | 815891.1 | 58.21% | 2010-11-22 | 2011-12-15 | 0 | 0 | 0.00291 | 0.04057 | Caltrans | Caltrans | Caltrans | Caltrans
02 | SHOPP | 2C090 | PLU | 070 | REPLACE BRIDGE DECK | 9.4582 | SHOPP | 2012 | 3212 | X | X | X |  |  | 15640000 | 5200000 | 800000 | 2000000 | 300000 | 2100000 | 319069.91 | 33.25% | 2014-08-28 | 2018-01-18 | 0.98564 | 7.8158 | 0.65677 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
02 | SHOPP | 2C110 | TEH | 099 | RECONSTRUCT BRIDGE | 0.51767 | SHOPP | 2008 | 3214 | [5 empty] | 2847000 | 3827000 | 480000 | 1880000 | 247000 | 1220000 | 3195045.67 | 134.4% | 2010-08-06 | 2012-01-20 | 0 | 0 | 0.23171 | 0.28596 | Caltrans | Caltrans | Caltrans | Caltrans
02 | SHOPP | 2C112 | TEH | 099 | REPAIR BRIDGE SCOUR | 1.4336 | SHOPP | 2010 | 3376 | [5 empty] | 2514000 | 1906000 | 306000 | 824000 | 108000 | 668000 | 1066953.29 | 75.82% | 2012-08-20 | 2014-09-30 | 0 | 0.09478 | 0 | 1.3389 | Caltrans | Caltrans | Caltrans | Caltrans
02 | SHOPP | 2C221 | MOD | 299 | REPLACE BRIDGE WITH CONCRETE SLAB | 0.72514 | SHOPP | 2010 | 3215A | [5 empty] | 1731000 | 1428000 | 443000 | 447000 | 88000 | 450000 | 1223658.5253 | 82.5% | 2011-08-10 | 2014-11-14 | 0 | 0 | 0.05729 | 0.66785 | Caltrans | Caltrans | Caltrans | Caltrans
02 | SHOPP | 2C222 | SHA | 299 | BRIDGE SCOUR | 1.4202 | SHOPP | 2010 | 3215B | [5 empty] | 2981000 | 2191000 | 602000 | 661000 | 170000 | 758000 | 1876034.216 | 73.5% | 2011-12-08 | 2014-11-14 | 0 | 0 | 0.13332 | 1.2869 | Caltrans | Caltrans | Caltrans | Caltrans
02 | SHOPP | 2C224 | PLU | 089 | BRIDGE REHABILITATION | 0.59319 | SHOPP | 2010 | 3215C | [5 empty] | 1305000 | 843000 | 317000 | 237000 | 65000 | 224000 | 834077.9494 | 64.6% | 2011-08-10 | 2012-10-22 | 0 | 0 | 0.07367 | 0.51952 | Caltrans | Caltrans | Caltrans | Caltrans
02 | SHOPP | 2C225 | TEH | 036 | BRIDGE SCOUR | 0.44514 | SHOPP | 2012 | 3215D | [5 empty] | 920000 | 1000000 | 450000 | 285000 | 55000 | 210000 | 765857.2194 | 108.7% | 2013-07-09 | 2015-10-16 | 0 | 0.06327 | 0.03056 | 0.35131 | Caltrans | Caltrans | Caltrans | Caltrans
02 | SHOPP | 2C230 | SHA | 005 | BRIDGE REHABILITATION | 5.0897 | SHOPP | 2010 | 3216 |  |  |  | X |  | 1900000 | 3600000 | 800000 | 1100000 | 100000 | 1600000 | 1192365.25 | 189.5% | 2011-09-27 | 2013-09-03 | 0 | 0 | 2.4476 | 2.6421 | Caltrans | Caltrans | Caltrans | Caltrans
02 | SHOPP | 2C450 | SHA | 005 | ASPHALT CONCRETE RESURFACING | 4.8142 | SHOPP | 2008 | 3221 |  |  |  | X |  | 34225000 | 3780000 | 180000 | 1140000 | 50000 | 2410000 | 2667090.72 | 11.04% | 2010-11-29 | 2014-01-17 | 0 | 0 | 0.0107 | 4.8035 | Caltrans | Caltrans | Caltrans | Caltrans
02 | SHOPP | 2C460 | MOD | 139 | REPLACE SLAB | 0.03238 | SHOPP | 2010 | 3222 | [5 empty] | 20440000 | 3617000 | 107000 | 1070000 | 86000 | 2354000 | 162826.72 | 17.7% | 2010-11-12 | 2012-03-08 | 0 | 0 | 0.00775 | 0.02463 | Caltrans | Caltrans | Caltrans | Caltrans
02 | SHOPP | 2C580 | SHA | 299 | REALIGN CURVE | 0.48745 | SHOPP | 2008 | 3226 | [5 empty] | 2418000 | 1714000 | 344000 | 480000 | 200000 | 690000 | 1576755.48 | 70.89% | 2009-04-23 | 2009-10-14 | 0 | 0 | 0.13738 | 0.35007 | Caltrans | Caltrans | Caltrans | Caltrans
02 | SHOPP | 2C710 | SIS | 005 | REPLACE BRIDGE DECK | 0.22015 | SHOPP | 2008 | 3229 | [5 empty] | 2567000 | 2040000 | 149000 | 901000 | 90000 | 900000 | 1551866.3 | 79.47% | 2009-05-21 | 2010-06-24 | 0 | 0 | 0.00042 | 0.21973 | Caltrans | Caltrans | Caltrans | Caltrans
02 | SHOPP | 2C810 | SHA | 299 | COLD-PLANING AND CONVENTIONAL ASPHALT OVERLAY WITH DIGOUTS. | 0.58398 | SHOPP | 2010 | 3240 | [5 empty] | 10151000 | 1830000 | 104000 | 531000 | 70000 | 1125000 | 708431.19 | 18.03% | 2012-02-13 | 2013-04-08 | 0 | 0 | 0.20209 | 0.38189 | Caltrans | Caltrans | Caltrans | Caltrans
02 | SHOPP | 2C950 | SIS | 096 | DRAINAGE SYSTEM RESTORATION | 2.0895 | SHOPP | 2010 | 3242 |  |  |  | X |  | 1960000 | 2945000 | 1100000 | 975000 | 170000 | 700000 | 2658540.06 | 150.3% | 2011-10-25 | 2013-12-02 | 0 | 0 | 0.41744 | 1.6721 | Caltrans | Caltrans | Caltrans | Caltrans
02 | SHOPP | 2C990 | TRI | 003 | REPLACE BRIDGE WITH PS CONCRETE | 6.3529 | SHOPP | 2008 | 3248 |  |  |  | X |  | 4948000 | 4298000 | 542000 | 1422000 | 137000 | 2197000 | 3212922.74 | 86.86% | 2011-02-24 | 2013-12-02 | 0 | 0 | 4.043 | 2.3099 | Caltrans | Caltrans | Caltrans | Caltrans
02 | SHOPP | 2E320 | SHA | 005 | WIDEN BRIDGE, REPLACE SLAB AND SEAL | 0.14633 | SHOPP | 2010 | 3427 | [5 empty] | 2757000 | 566000 | 80000 | 252000 | 14000 | 220000 | 407319.59 | 20.53% | 2011-10-03 | 2013-01-31 | 0 | 0 | 0 | 0.14633 | Caltrans | Caltrans | Caltrans | Caltrans
02 | SHOPP | 2E350 | TRI | 299 | CURVE IMPROVEMENT | 5.118 | SHOPP | 2012 | 3421 | [5 empty] | 2500000 | 1679000 | 427000 | 680000 | 27000 | 545000 | 1639006.12 | 67.16% | 2013-05-22 | 2015-01-30 | 0 | 0 | 0 | 5.118 | Caltrans | Caltrans | Caltrans | Caltrans
02 | SHOPP | 2E480 | SIS | 263 | BRIDGE REPLACEMENT | 6.0074 | SHOPP | 2012 | 3424 | [5 empty] | 8200000 | 4530000 | 1400000 | 1500000 | 130000 | 1500000 | 0 | 55.24% | 2016-06-01 | 2019-01-15 | 4.0018 | 1.9911 | 0.01455 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
02 | SHOPP | 2E510 | SHA | 299 | CURVE IMPROVEMENT | 6.6445 | SHOPP | 2010 | 3422 | [5 empty] | 10869000 | 2960000 | 580000 | 910000 | 170000 | 1300000 | 1472159.71 | 27.23% | 2012-11-29 | 2015-11-17 | 0 | 0 | 0.01 | 6.6345 | Caltrans | Caltrans | Caltrans | Caltrans
02 | SHOPP | 2E620 | TEH | 036 | CURVE IMPROVEMENT | 1.5111 | SHOPP | 2012 | 3423 | [5 empty] | 3010000 | 1474000 | 580000 | 254000 | 276000 | 364000 | 716585.87 | 48.97% | 2013-04-24 | 2014-12-01 | 0 | 0.02453 | 0.21747 | 1.2691 | Caltrans | Caltrans | Caltrans | Caltrans
02 | SHOPP | 2E730 | TEH | 032 | CURVE IMPROVEMENT AND SHOULDER WIDENING | 1.4603 | SHOPP | 2012 | 3429 | [5 empty] | 2248000 | 1037000 | 316000 | 239000 | 120000 | 362000 | 433583.99 | 46.13% | 2013-05-07 | 2014-11-21 | 0 | 0 | 0.07555 | 1.3847 | Caltrans | Caltrans | Caltrans | Caltrans
02 | SHOPP | 2E740 | SHA | 299 | CURVE IMPROVEMENT | 2.1826 | SHOPP | 2012 | 3433 |  | X | X |  |  | 2554000 | 903000 | 226000 | 240000 | 122000 | 315000 | 229870.22 | 35.36% | 2014-06-03 | 2015-10-29 | 0 | 1.8998 | 0.25973 | 0.02309 | Caltrans | Caltrans | Caltrans | Caltrans
02 | SHOPP | 2E750 | TEH | 005 | EXTEND ONRAMPS | 0.88445 | SHOPP | 2010 | 3425 |  |  |  | X |  | 2370000 | 830000 | 90000 | 170000 | 100000 | 470000 | 496902.79 | 35.02% | 2012-04-13 | 2013-07-15 | 0 | 0 | 0.13545 | 0.749 | Caltrans | Caltrans | Caltrans | Caltrans
02 | SHOPP | 2E800 | SIS | 005 | UPGRADE FACILITY ENFORCEMENT FACILITY | 0.06822 | SHOPP | 2012 | 3426 | X |  | X |  |  | 3604000 | 1920000 | 300000 | 800000 | 20000 | 800000 | 0 | 53.27% | 2014-11-19 | 2017-01-15 | 0.05375 | 0 | 0 | 0.01447 | Caltrans | Caltrans | Caltrans | Caltrans
02 | SHOPP | 3705U | SHA | 299 | REALIGN HIGHWAY AND CONSTRUCT CLIMBING LANE | 1.4848 | SHOPP | 2006 | 3053 | [5 empty] | 6613000 | 2238000 | 2238000 | F | F | F | 2263355.97 | 33.84% | 2006-11-01 | 2007-12-10 | 0 | 0 | 0.05176 | 1.433 | Caltrans | Caltrans | Caltrans | Caltrans
02 | SHOPP | 3C000 | SHA | 005 | WIDEN RAMP | 0.20313 | SHOPP | 2008 | 3246 | [5 empty] | 7450000 | 4526000 | 536000 | 1960000 | 30000 | 2000000 | 3665952.02 | 60.75% | 2010-12-21 | 2012-11-19 | 0 | 0 | 0 | 0.20313 | Caltrans | Caltrans | Caltrans | Caltrans
02 | SHOPP | 3C071 | LAS | 395 | REHABILITATE ROADWAY. | 2.4116 | SHOPP | 2012 | 3250 |  | X | X |  |  | 16889000 | 2990000 | 500000 | 1145000 | 95000 | 1250000 | 953211.26 | 17.7% | 2014-03-03 | 2016-01-04 | 0 | 1.1763 | 0.05889 | 1.1764 | Caltrans | Caltrans | Caltrans | Caltrans
02 | SHOPP | 3C072 | LAS | 395 | PAVEMENT REHABILITATION | 1.1261 | SHOPP | 2012 | 3250B | [5 empty] | 3015000 | 1619000 | 479000 | 695000 | 45000 | 400000 | 804763.17 | 53.7% | 2013-09-10 | 2015-09-01 | 0 | 0.08634 | 0 | 1.0397 | Caltrans | Caltrans | Caltrans | Caltrans
02 | SHOPP | 3C080 | TRI | 299 | WIDEN SHOULDERS | 0.08556 | SHOPP | 2008 | 3249 | [5 empty] | 3964000 | 2999000 | 656000 | 1093000 | 60000 | 1190000 | 3731991.64 | 75.66% | 2009-04-01 | 2012-04-02 | 0 | 0 | 0 | 0.08556 | Caltrans | Caltrans | Caltrans | Caltrans
02 | SHOPP | 3C300 | PLU | 070 | INSTALL MBGR | 2.4269 | SHOPP | 2010 | 3266 | [5 empty] | 8012000 | 3276000 | 830000 | 950000 | 26000 | 1470000 | 1865378.04 | 40.89% | 2012-06-20 | 2015-10-01 | 0 | 0 | 0.01121 | 2.4157 | Caltrans | Caltrans | Caltrans | Caltrans
02 | SHOPP | 3C810 | SIS | 096 | INSTALL PRECAST CULVERTS | 0.11757 | SHOPP | 2008 | 3289 | [5 empty] | 1088000 | 585000 | 250000 | 200000 | 25000 | 110000 | 1206269.74 | 53.77% | 2008-12-11 | 2010-10-01 | 0 | 0 | 0 | 0.11757 | Caltrans | Caltrans | Caltrans | Caltrans
02 | SHOPP | 3C920 | SIS | 005 | DECK REPLACEMENT, SEISMIC RETROFIT | 2.0179 | SHOPP | 2010 | 3291 | [5 empty] | 9277000 | 5300000 | 1100000 | 1800000 | 280000 | 2120000 | 1227493.66 | 57.13% | 2012-08-22 | 2016-12-01 | 0 | 0 | 0.06007 | 1.9578 | Caltrans | Caltrans | Caltrans | Caltrans
02 | SHOPP | 3E410 | SHA | 299 | HIGHWAY REALIGNMENT | 8.068 | SHOPP | 2012 | 3435 |  | X | X |  |  | 25916000 | 8090000 | 2100000 | 2100000 | 340000 | 3550000 | 797403.64 | 31.22% | 2014-11-14 | 2017-08-17 | 0 | 5.7656 | 2.3024 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
02 | SHOPP | 3E650 | SHA | 910 | BRIDGE MAINTENANCE | 3.524 | SHOPP | 2012 | 3452 | [5 empty] | 3702000 | 1180000 | 285000 | 430000 | 20000 | 445000 | 313326.73 | 31.87% | 2013-04-17 | 2014-08-30 | 0 | 0 | 0.01354 | 3.5104 | Caltrans | Caltrans | Caltrans | Caltrans
02 | SHOPP | 3E690 | MOD | 299 | SHOULDER WIDENING | 0.901 | SHOPP | 2012 | 3437 | [5 empty] | 1146000 | 960000 | 400000 | 215000 | 115000 | 230000 | 402118.61 | 83.77% | 2013-02-28 | 2014-12-28 | 0 | 0 | 0.06092 | 0.84008 | Caltrans | Caltrans | Caltrans | Caltrans
02 | SHOPP | 3E710 | VAR | VAR | PLACE HMA AND HORIZONTAL CURVE | 0.93992 | SHOPP | 2012 | 3439 | [5 empty] | 867000 | 571000 | 137000 | 181000 | 34000 | 219000 | 158933.06 | 65.86% | 2013-04-29 | 2014-10-14 | 0 | 0 | 0.04358 | 0.89634 | Caltrans | Caltrans | Caltrans | Caltrans
02 | SHOPP | 3E730 | SIS | 005 | BRIDGE DECK REPLACEMENT | 1.6 | SHOPP | 2012 | 3455 | X |  |  |  |  | 5814000 | 3190000 | 900000 | 1000000 | 90000 | 1200000 | 0 | 54.87% | 2015-09-02 | 2017-05-16 | 1.58 | 0 | 0.02 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
02 | SHOPP | 3E750 | SIS | 005 | ROADWAY REHABILITATION | 6.5713 | SHOPP | 2010 | 3443 | [5 empty] | 20139000 | 2440000 | 200000 | 700000 | 40000 | 1500000 | 1153109.01 | 12.12% | 2011-11-22 | 2014-11-15 | 0 | 0 | 0.00256 | 6.5687 | Caltrans | Caltrans | Caltrans | Caltrans
02 | SHOPP | 3E760 | SIS | 005 | PAVEMENT REHABILITATION | 9.967 | SHOPP | 2010 | 3444 | [5 empty] | 50759000 | 5300000 | 240000 | 1500000 | 60000 | 3500000 | 1564520.58 | 10.44% | 2011-12-22 | 2014-11-15 | 0 | 0 | 0.03 | 9.937 | Caltrans | Caltrans | Caltrans | Caltrans
02 | SHOPP | 3E770 | TRI | 299 | ADA CURB RAMPS | 3.4145 | SHOPP | 2012 | 3454 | X |  |  |  |  | 11623000 | 2230000 | 420000 | 600000 | 210000 | 1000000 | 6533.27 | 19.19% | 2015-03-04 | 2016-12-30 | 0.60658 | 2.7856 | 0.02225 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
02 | SHOPP | 3E790 | TRI | 299 | CURVE IMPROVEMENTS | 1.6031 | SHOPP | 2012 | 3438 |  | X | X |  |  | 2340000 | 3373000 | 1200000 | 710000 | 63000 | 1400000 | 733824.53 | 144.1% | 2014-07-07 | 2017-01-14 | 0 | 1.592 | 0.01109 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
02 | SHOPP | 3E800 | SHA | 273 | CONSTRUCT & MODIFY ADA CURB RAMPS. | 3.4858 | SHOPP | 2012 | 3469 | X |  |  |  |  | 3720000 | 2600000 | 700000 | 800000 | 600000 | 500000 | 0 | 69.89% | 2015-09-15 | 2016-11-01 | 0.02038 | 1.4539 | 2.0116 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
02 | SHOPP | 3E810 | TEH | 005 | ROADWAY REHABILITATION | 4.3228 | SHOPP | 2010 | 3442 |  |  |  | X |  | 34379000 | 3260000 | 170000 | 950000 | 40000 | 2100000 | 1696166.65 | 9.483% | 2011-12-14 | 2013-11-15 | 0 | 0 | 0.00897 | 4.3138 | Caltrans | Caltrans | Caltrans | Caltrans
02 | SHOPP | 4C010 | SIS | 097 | COLD PLANE AC APPLY RUBBER SEAL COAT AND HMA OVER CLASS 2AB | 2.9481 | SHOPP | 2010 | 3297 |  |  |  | X |  | 16508000 | 3072000 | 40000 | 360000 | 72000 | 2600000 | 2607982.1 | 18.61% | 2011-01-20 | 2014-01-02 | 0 | 0 | 0.03 | 2.9181 | Caltrans | Caltrans | Caltrans | Caltrans
02 | SHOPP | 4E410 | TRI | 299 | WEAVERVILLE CAPM | 1.0753 | SHOPP | 2012 | 3463 |  | X | X |  |  | 9419000 | 1600000 | 250000 | 500000 | 50000 | 800000 | 5458.36 | 16.99% | 2014-04-30 | 2015-12-30 | 0 | 0.88036 | 0.0313 | 0.16361 | Caltrans | Caltrans | Caltrans | Caltrans
02 | SHOPP | 4E420 | LAS | 395 | PAVEMENT REHABILITATION | 5.4062 | SHOPP | 2012 | 3464 | X |  |  |  |  | 14595000 | 2560000 | 550000 | 1200000 | 10000 | 800000 | 1925.67 | 17.54% | 2015-12-01 | 2017-11-06 | 2.9932 | 2.1854 | 0.22757 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
02 | SHOPP | 4E430 | SHA | 044 | PAVEMENT REHABILITATION | 1.6549 | SHOPP | 2012 | 3465 | X |  |  |  |  | 5876000 | 1080000 | 160000 | 360000 | 220000 | 340000 | 0 | 18.38% | 2015-11-17 | 2016-11-01 | 0.11226 | 0.9908 | 0.55185 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
02 | SHOPP | 4E440 | MOD | 139 | PAVEMENT REHABILITATION | 2.6126 | SHOPP | 2012 | 3466 | [5 empty] | 14517000 | 3860000 | 610000 | 1180000 | 190000 | 1880000 | 440.7 | 26.59% | 2016-03-03 | 2017-07-17 | 0.7848 | 1.6684 | 0.15941 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
02 | SHOPP | 4E480 | SIS | 089 | INSTALL FLASHING BEACON. | 1.8645 | SHOPP | 2010 | 3486 |  |  |  | X |  | 235000 | 180000 | 55000 | 45000 | 7000 | 73000 | 167853.91 | 76.6% | 2012-10-31 | 2014-02-15 | 0 | 0 | 0.02261 | 1.8418 | Caltrans | Caltrans | Caltrans | Caltrans
02 | SHOPP | 4E530 | SHA | 005 | BRIDGE REHABILITATION. | 3.1827 | SHOPP | 2012 | 3487 | [5 empty] | 6108000 | 1778000 | 284000 | 574000 | 65000 | 855000 | 30296.55 | 29.11% | 2013-08-23 | 2015-07-24 | 0 | 0.37625 | 0.03941 | 2.767 | Caltrans | Caltrans | Caltrans | Caltrans
02 | SHOPP | 4E610 | TRI | 299 | REPAIR SLIDES. | 0.43582 | SHOPP | 2012 | 3470 |  | X | X |  |  | 355000 | 286000 | 85000 | 94000 | 28000 | 79000 | 96269.14 | 80.56% | 2014-01-15 | 2015-01-21 | 0 | 0.24632 | 0.03103 | 0.15847 | Caltrans | Caltrans | Caltrans | Caltrans
02 | SHOPP | 4E640 | PLU | 147 | REPLACE BRIDGE. | 7.1101 | SHOPP | 2012 | 3472 | X |  |  |  |  | 8108000 | 4450000 | 1400000 | 1200000 | 50000 | 1800000 | 9027.12 | 54.88% | 2015-10-05 | 2017-01-05 | 3.5678 | 3.4567 | 0.08557 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
02 | SHOPP | 4E650 | SIS | 096 | BRIDGE RAIL REPLACEMENT UPGRADE | 4.0444 | SHOPP | 2012 | 3473 | [5 empty] | 10228000 | 3990000 | 900000 | 1500000 | 90000 | 1500000 | 0 | 39.01% | 2016-12-07 | 2019-01-15 | 0.64635 | 2.826 | 0.57208 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
02 | SHOPP | 4E670 | SIS | 005 | REHABILITATE WATER SYSTEMS. | 0.51538 | SHOPP | 2012 | 3476 | [5 empty] | 3550000 | 2000000 | 495000 | 685000 | 265000 | 555000 | 0 | 56.34% | - - | - - | 0.49606 | 0 | 0 | 0.01932 | Caltrans | Caltrans | Caltrans | Caltrans
02 | SHOPP | 4E690 | LAS | 395 | REHABILITATE WATER SYSTEMS | 2.862 | SHOPP | 2012 | 3478 | X |  |  |  |  | 2300000 | 1200000 | 305000 | 534000 | 42000 | 319000 | 1784.85 | 52.17% | 2015-01-05 | 2016-01-14 | 0.25092 | 2.507 | 0.10415 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
02 | SHOPP | 4E810 | PLU | 070 | WORKER SAFETY IMPROVEMENTS | 5.2975 | SHOPP | 2012 | 3479 | X |  |  |  |  | 3400000 | 1340000 | 20000 | 950000 | 40000 | 330000 | 0 | 39.41% | 2015-06-10 | 2016-09-15 | 1.8267 | 3.4078 | 0.06292 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
02 | SHOPP | 4E820 | LAS | 395 | RUMBLE STRIPS, MEDIAN BUFFER, WIDEN SHOULDERS | 0.63245 | SHOPP | 2012 | 3496 |  |  |  | X |  | 389000 | 555000 | 150000 | 200000 | 30000 | 175000 | 75257.5 | 142.7% | 2012-09-13 | 2013-11-22 | 0 | 0 | 0 | 0.63245 | Caltrans | Caltrans | Caltrans | Caltrans
02 | SHOPP | 4E890 | SHA | 299 | MCCANDLESS GULCH CURVE IMPROVEMENT | 2.174 | SHOPP | 2012 | 3480 | X |  |  |  |  | 1750000 | 872000 | 150000 | 247000 | 154000 | 321000 | 321.98 | 49.83% | 2015-01-23 | 2016-03-21 | 1.2243 | 0.76809 | 0.18159 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
02 | SHOPP | 4E900 | TEH | 032 | CURVE IMPROVEMENT .010 | 1.347 | SHOPP | 2012 | 3481 | X |  |  |  |  | 2668000 | 498000 | 231000 | 88000 | 14000 | 165000 | 16657.29 | 18.67% | 2015-01-23 | 2016-03-25 | 0.50931 | 0.67432 | 0.16341 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
02 | SHOPP | 4F100 | PLU | 070 | PERM. RESTORATION | 0.57933 | SHOPP | 2012 | 3497 |  | X | X |  |  | 1670000 | 470000 | 40000 | 200000 | 30000 | 200000 | 1187.16 | 28.14% | 2014-06-10 | 2015-09-30 | 0 | 0.45166 | 0.12767 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
02 | SHOPP | 4F290 | SHA | 044 | SUGARLOAF SUPERELEVATION | 2.76 | SHOPP | 2012 | 3489 | [5 empty] | 1760000 | 672000 | 308000 | 99000 | 72000 | 193000 | 0 | 38.18% | - - | - - | 0.4 | 1.18 | 1.18 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
02 | SHOPP | 4F410 | SIS | 096 | EMEREGENCY PROJECT PERMANENT RESTORATION | 0.07022 | SHOPP | 2012 | 3494 | [5 empty] | 1420000 | 400000 | 90000 | 200000 | 10000 | 100000 | 0 | 28.17% | - - | - - | 0.07022 | 0 | 0 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
02 | SHOPP | 4F430 | SIS | 096 | DIRECTOR'S ORDER ELB | 0.06126 | SHOPP | 2010 | 3499 | [5 empty] | 610000 | 50000 | 5000 | 5000 | 10000 | 30000 | 125020.81 | 8.197% | - - | - - | 0.06126 | 0 | 0 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
02 | SHOPP | 4F450 | SHA | 005 | IMPROVE ROADWAY DRAINAGE | 3.4269 | SHOPP | 2012 | 3500 | [5 empty] | 1925000 | 664000 | 105000 | 262000 | 3000 | 294000 | 375.87 | 34.49% | - - | - - | 0 | 1.67 | 0.1 | 1.6569 | Caltrans | Caltrans | Caltrans | Caltrans
02 | SHOPP | 4F490 | SIS | 005 | EMERGENCY BRIDGE REPAIR | 0.5926 | SHOPP | 2010 | 3504 | [5 empty] | 1050000 | 310000 | J | 150000 | 10000 | 150000 | 111023.17 | 29.52% | - - | - - | 0.55636 | 0.03624 | 0 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
02 | SHOPP | 4F500 | SIS | 005 | EMERGENCY BRIDGE REPAIR | 0.06673 | SHOPP | 2010 | 3505 | [5 empty] | 2505000 | 800000 | J | J | J | 800000 | 140798.9 | 31.94% | - - | - - | 0.06126 | 0 | 0 | 0.00547 | Caltrans | Caltrans | Caltrans | Caltrans
02 | SHOPP | 4F640 | SIS | 096 | REPLACE BRIDGE | 0.08884 | SHOPP | 2012 | 3511 | [5 empty] | 843000 | 250000 | 50000 | 120000 | 10000 | 70000 | 54067.83 | 29.66% | - - | 2012-11-13 | 0 | 0 | 0.08548 | 0.00336 | Caltrans | Caltrans | Caltrans | Caltrans
02 | SHOPP | 4F750 | SHA | 005 | EMERGENCY PROJECT | 0.05483 | SHOPP | 2012 | 3521 | [5 empty] | 1000000 | 200000 | 45000 | 45000 | 10000 | 100000 | 0 | 20% | - - | - - | 0 | 0 | 0.05216 | 0.00267 | Caltrans | Caltrans | Caltrans | Caltrans
02 | SHOPP | 4G010 | SHA | 299 | REPAIR CULVERTS | 0.78775 | SHOPP | 2012 | 3531 | [5 empty] | 425000 | 75000 | J | J | J | 75000 | 0 | 17.65% | - - | 2013-03-04 | 0.74335 | 0 | 0.0128 | 0.0316 | Caltrans | Caltrans | Caltrans | Caltrans
02 | SHOPP | 4G020 | SHA | 299 | SIDESLOPE DAMAGE | 1.3576 | SHOPP | 2012 | 3532 | [5 empty] | 1315000 | 185000 | J | J | J | 185000 | 0 | 14.07% | - - | 2013-02-27 | 0.74059 | 0 | 0 | 0.61702 | Caltrans | Caltrans | Caltrans | Caltrans
02 | SHOPP | MINOR |  |  | SHOPP MINOR | 24.7892 | MINOR
03 | SHOPP | 0E080 | YUB | 070 | REHABILITATE BRIDGE DECK | 3.4269 | SHOPP | 2010 | 9808 | [5 empty] | 5187000 | 2134000 | 153000 | 737000 | 11000 | 1233000 | 622979.34 | 41.14% | 2010-11-24 | 2011-07-20 | 0 | 0 | 0.11 | 3.3169 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 1E000 | PLA | 089 | PAVEMENT REHABILITATION DRAINAGE IMPROVEMENTS | 3.4247 | SHOPP | 2010 | 5283 |  |  |  | X |  | 7010000 | 1860000 | 100000 | 750000 | 10000 | 1000000 | 549498.92 | 26.53% | 2012-06-07 | 2013-12-01 | 0 | 0 | 0.00924 | 3.4154 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 3E000 | ED | 050 | RECONSTRUCT CURVE | 0.0054 | SHOPP | 2006 | 3287 | [5 empty] | 1405000 | 705000 | 705000 | F | F | F | 600668.42 | 50.18% | 2008-06-25 | 2008-11-20 | 0 | 0 | 0 | 0.0054 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 29090 | PLA | 028 | WATER QUALITY IMPROVEMENTS | 0.10088 | SHOPP | 2006 | 0142G | [5 empty] | 3621000 | 464000 | 464000 | F | F | F | 2787280.57 | 12.81% | 2007-04-13 | 2007-10-26 | 0 | 0 | 0 | 0.10088 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 31441 | BUT | 162 | HIGHWAY PLANTING AND IRRIGATION | 0.01092 | SHOPP | 1998 | 0028Y | [5 empty] | 297000 | 128000 | 128000 | F | F | F | 342428.83 | 43.1% | 1999-07-12 | 2003-01-23 | 0 | 0 | 0 | 0.01092 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 31800 | NEV | L5717 | CONSTRUCT MECHANICS FACILITY | 0.17145 | SHOPP | 2008 | 1410 | [5 empty] | 2814000 | 2117000 | 167000 | 1199000 | 12000 | 739000 | 1916414.18 | 75.23% | 2010-04-21 | 2011-12-15 | 0 | 0 | 0.04586 | 0.12559 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 40180 | YUB | 065 | IMPROVE TRAFFIC OPERATIONS | 0.24778 | SHOPP | 2006 | 9726 | [5 empty] | 1659000 | 2160000 | 2160000 | F | F | F | 2356394.05 | 130.2% | 2006-08-29 | 2007-11-27 | 0 | 0 | 0 | 0.24778 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 3E030 | SAC | 080 | UPGRADE MBGR END TREATMENTS ON NON-NHS ROUTES TO 350 STDS | 0.55143 | SHOPP | 2010 | 6907 | [5 empty] | 2863000 | 1499000 | 164000 | 489000 | 47000 | 799000 | 849118.84 | 52.36% | 2012-01-30 | 2012-10-04 | 0 | 0 | 0.00271 | 0.54872 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 3E040 | PLA | 080 | PLACE HOT MIX ASPHALT | 0.56314 | SHOPP | 2008 | 5092 | [5 empty] | 70000000 | 14227000 | 85000 | 4000000 | 32000 | 10110000 | 4969769.26 | 20.32% | 2008-10-21 | 2009-12-02 | 0 | 0 | 0 | 0.56314 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 1E041 | SAC | 050 | CONCRETE MEDIAN BARRIER AND OVERHED SIGNS | 0.18163 | SHOPP | 2006 | 6211B | [5 empty] | 40007000 | 5601000 | 5601000 | F | F | F | 5635935.0343 | 14% | 2008-12-23 | 2010-07-11 | 0 | 0 | 0 | 0.18163 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 2E050 | NEV | 080 | REPLACE BRIDGE DECK | 0.16368 | SHOPP | 2006 | 4273 | [5 empty] | 4823000 | 2082000 | 2082000 | F | F | F | 1206561.44 | 43.17% | 2008-05-05 | 2008-10-17 | 0 | 0 | 0 | 0.16368 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 1E060 | YUB | 070 | REPLACE BRIDGE (SCOUR) | 5.5276 | SHOPP | 2012 | 9812 | X |  |  |  |  | 18248000 | 5766000 | 854000 | 1284000 | 155000 | 3473000 | 128.88 | 31.6% | 2016-04-03 | 2018-03-18 | 4.7578 | 0.61093 | 0.15891 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 3E060 | NEV | 020 | POLYESTER CONCRETE AND HMA OVERLAY | 2.9976 | SHOPP | 2010 | 3986 | [5 empty] | 1511000 | 703000 | 1000 | 350000 | 7000 | 345000 | 329171.39 | 46.53% | 2011-08-24 | 2013-05-15 | 0 | 0 | 0.01644 | 2.9812 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 3E070 | YOL | 005 | AC OVERLAY, WITH JOINT HEADER POLYESTER OVERLAY | 1.0006 | SHOPP | 2010 | 8562 | [5 empty] | 7402000 | 4461000 | 381000 | 2217000 | 151000 | 1712000 | 1623196.86 | 60.27% | 2010-11-24 | 2012-04-24 | 0 | 0 | 0.4712 | 0.5294 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 3E090 | PLA | 080 | PLACE POLYESTER OVERLAY | 0.55721 | SHOPP | 2010 | 5094 | [5 empty] | 13968000 | 2216000 | 1000 | 550000 | 11000 | 1654000 | 1559796.17 | 15.86% | 2011-05-20 | 2012-12-30 | 0 | 0 | 0.02 | 0.53721 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 1E100 | YOL | 080 | GORE PAVING | 0.13 | SHOPP | 2010 | 6696 | [5 empty] | 2503000 | 660000 | E | 300000 | 10000 | 350000 | 279121.97 | 26.37% | 2011-02-02 | 2011-08-22 | 0 | 0 | 0 | 0.13 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 3E100 | PLA | 080 | VERTICAL CLEARANCE FOR PERMIT VEH | 5.8516 | SHOPP | 2012 | 5095 | [5 empty] | 28950000 | 7095000 | 1950000 | 2600000 | 145000 | 2400000 | 3672885.69 | 24.51% | 2013-09-01 | 2015-03-01 | 0 | 0.52334 | 0.22 | 5.1083 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 1E110 | BUT | 070 | INSTALL CABLE RESTRAINERS AND CONCRETE BLOCKS AT PIERS AND | 0.29997 | SHOPP | 2008 | 2267 | [5 empty] | 4600000 | 1958000 | 240000 | 750000 | 18000 | 950000 | 1129505.06 | 42.57% | 2010-12-08 | 2011-09-28 | 0 | 0 | 0.01784 | 0.28213 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 3E110 | NEV | 080 | PAINT STRUCTURES | 0.97 | SHOPP | 2012 | 4281 |  | X | X |  |  | 2400000 | 984000 | 100000 | 250000 | 100000 | 534000 | 142205.02 | 41% | 2014-08-01 | 2016-12-01 | 0 | 0.69 | 0.28 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 2E120 | SAC | 099 | WIDEN EXISTING HIGHWAY | 0.09009 | SHOPP | 2006 | 6905 | [5 empty] | 5900000 | 1228000 | 100000 | 315000 | 3000 | 810000 | 1226413.35 | 20.81% | 2006-10-01 | 2007-10-09 | 0 | 0 | 0 | 0.09009 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 3E120 | BUT | 070 | SEISMIC RETROFIT | 3.5425 | SHOPP | 2012 | 2279 |  | X | X |  |  | 2353000 | 1565000 | 270000 | 600000 | 85000 | 610000 | 160317.1 | 66.51% | 2014-10-22 | 2016-09-02 | 0 | 3.2719 | 0.27061 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 2E130 | SAC | 050 | WIDEN HIGHWAY | 0.04051 | SHOPP | 2006 | 6217 | [5 empty] | 7005000 | D | D | D | D | D | 1073853.03 | NA | 2006-12-14 | 2009-08-28 | 0 | 0 | 0 | 0.04051 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 4E130 | BUT | 070 | UPGRADE GUARD RAIL AND GORE AREAS | 0.07501 | SHOPP | 2008 | 2276 | [5 empty] | 2241000 | 677000 | 90000 | 370000 | 27000 | 190000 | 904640.09 | 30.21% | 2009-07-29 | 2010-12-17 | 0 | 0 | 0 | 0.07501 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 2E140 | SAC | 050 | WIDEN AND RESURFACE ROADWAY | 0.03 | SHOPP | 2006 | 6218 | [5 empty] | 3105000 | 966500 | 139000 | 385000 | 2500 | 440000 | 965768.22 | 31.13% | 2006-11-20 | 2007-10-05 | 0 | 0 | 0 | 0.03 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 1E160 | BUT | 070 | INSTALL SIGNAL,LOWER VERTICAL CURVE | 0.13311 | SHOPP | 2006 | 2268 | [5 empty] | 8248000 | 2881000 | 2881000 | F | F | F | 3582410.8 | 34.93% | 2007-08-20 | 2008-11-06 | 0 | 0 | 0.05068 | 0.08243 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 3E180 | COL | 020 | STABILIZE CUT SLOPE | 0.01 | SHOPP | 2006 | 2941 | [5 empty] | 400000 | 237000 | 237000 | F | F | F | 235333.16 | 59.25% | 2008-01-07 | 2008-06-05 | 0 | 0 | 0 | 0.01 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 4E180 | BUT | 070 | PLACE ROCK SLOPE PROTECTION | 0.01638 | SHOPP | 2006 | 2278 | [5 empty] | 310000 | 303000 | 303000 | F | F | F | 339105.73 | 97.74% | 2008-08-15 | 2009-06-19 | 0 | 0 | 0 | 0.01638 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 4E190 | NEV | 020 | ROUNDABOUT INTERSECTION IMPROVEMENT | 0.03909 | PARTNERSHIP | [6 empty] | O
03 | SHOPP | 3E200 | YUB | 049 | SLOPE REPAIR | 0.01931 | SHOPP | 2006 | 9677 | [5 empty] | 870000 | 534000 | 534000 | F | F | F | 765575.69 | 61.38% | 2008-07-23 | 2008-11-13 | 0 | 0 | 0.0001 | 0.01921 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 4E220 | SAC | 016 | HOT MIX ASPHALT SURFACING | 0.09852 | SHOPP | 2008 | 5982 | [5 empty] | 875000 | 950000 | 215000 | 340000 | 170000 | 225000 | 824527.32 | 108.6% | 2010-09-20 | 2011-07-28 | 0 | 0 | 0.0305 | 0.06802 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 3E230 | BUT | 099 | CONSTRUCT BARRIERS | 0.01631 | SHOPP | 2006 | 2422 | [5 empty] | 1200000 | 389000 | 389000 | F | F | F | 317971.98 | 32.42% | 2008-03-03 | 2008-06-05 | 0 | 0 | 0 | 0.01631 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 1E240 | PLA | 080 | EXTEND TRUCK CLIMBING LANE | 0.13809 | SHOPP | 2006 | 4266 | [5 empty] | 7567000 | 1828000 | 1828000 | F | F | F | 1772700.55 | 24.16% | 2007-07-18 | 2008-11-20 | 0 | 0 | 0 | 0.13809 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 3E250 | BUT | 162 | INSTALL AND UPGRADE ADA CURB RAMPS | 0.01056 | SHOPP | 2008 | 2629 | [5 empty] | 1034000 | 827000 | 175000 | 407000 | 38000 | 207000 | 977948.65 | 79.98% | 2009-06-04 | 2010-06-29 | 0 | 0 | 0 | 0.01056 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 0A360 | SAC | 005 | REHABILITATE STRUCTURE | 0.02735 | SHOPP | 2006 | 5792 | [5 empty] | 54114000 | 9859000 | 9859000 | F | F | F | 11126423.05 | 18.22% | 2008-02-08 | 2009-03-13 | 0 | 0 | 0 | 0.02735 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 0A580 | YUB | 070 | REHAB,UPDATE TRUCK TURN RADII, REPAIR CURB GUTTER AND SIDEWALK | 14.9624 | SHOPP | 2010 | 9578 | [5 empty] | 35100000 | 8250000 | 600000 | 2500000 | 150000 | 5000000 | 7505154.87 | 23.5% | 2012-01-13 | 2015-03-01 | 0 | 0 | 3 | 11.9624 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 0A600 | PLA | 080 | ROADWAY REHABILITATION UPGRADE MBGR, ELECT SYS, & SIGNING | 0.04763 | SHOPP | 2002 | 1517 | [5 empty] | 56000000 | 8300000 | 8300000 | F | F | F | 10389082.23 | 14.82% | 2004-06-24 | 2007-04-30 | 0 | 0 | 0 | 0.04763 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 0A631 | NEV | 080 | REHABILITATE ROADWAY | 2.095 | SHOPP | 2006 | 4257A | [5 empty] | 65781000 | 12897000 | 12897000 | F | F | F | 16005754.1343 | 19.61% | 2007-10-05 | 2012-11-05 | 0 | 0 | 1.0012 | 1.0937 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 0A632 | NEV | 080 | REHABILATE BRIDGES AND ROADWAY | 0.39533 | SHOPP | 2006 | 4257B | [5 empty] | 71000000 | 17225000 | 17225000 | F | F | F | 17146665.4357 | 24.26% | 2007-03-16 | 2012-06-28 | 0 | 0 | 0.1 | 0.29533 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 0A650 | BUT | 070 | HMA OVERLAY, COLD PLANE, MBGR | 0.2594 | SHOPP | 2010 | 2255 | [5 empty] | 8602000 | 1660000 | 200000 | 500000 | 10000 | 950000 | 727871.67 | 19.3% | 2010-12-08 | 2012-01-26 | 0 | 0 | 0.0194 | 0.24 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 0A690 | SIE | 049 | REHABILITATE PAVEMENT SURFACE | 0.78679 | SHOPP | 2010 | 7783 | [5 empty] | 16255000 | 3420000 | 400000 | 1000000 | 20000 | 2000000 | 867913.58 | 21.04% | 2011-12-08 | 2012-11-13 | 0 | 0 | 0.02008 | 0.76671 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 0A710 | YUB | 070 | ASPHALT CONCRETE OVERLAY | 0.04274 | SHOPP | 2006 | 9806A | [5 empty] | 8240000 | 2004000 | 2004000 | F | F | F | 785936.24 | 24.32% | 2008-08-13 | 2009-07-29 | 0 | 0 | 0.00248 | 0.04026 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 0A800 | SAC | 050 | GRIND PAVEMENT AND REPLACE SLAB | 1.8674 | SHOPP | 2008 | 6194 | [5 empty] | 10010000 | 2510000 | E | 1000000 | 10000 | 1500000 | 919600.47 | 25.07% | 2011-07-20 | 2012-12-27 | 0 | 0 | 0 | 1.8674 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 0C000 | SAC | 099 | HIGHWAY PLANTING AND IRRIGATION | 0.11366 | SHOPP | 2006 | 6892 | [5 empty] | 1730000 | 2123000 | 2123000 | F | F | F | 1078954.47 | 122.7% | 2007-12-14 | 2011-10-25 | 0 | 0 | 0 | 0.11366 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 0C340 | BUT | 032 | REPLACE BRIDGE | 0.03 | SHOPP | 2004 | 2102 | [5 empty] | 2968000 | 1101000 | 1101000 | F | F | F | 1812206.2 | 37.1% | 2005-11-02 | 2006-11-16 | 0 | 0 | 0 | 0.03 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 0C470 | YOL | 016 | WIDEN SH & CONSTR LEFT TURN LANE RT TRN POCKETS, INTERSEC IMPROVEMNT | 9.777 | SHOPP | 2012 | 8655 | [5 empty] | 22800000 | 21533000 | 8857000 | 6184000 | 3300000 | 3192000 | 13994597.9 | 94.44% | 2015-07-01 | 2017-11-01 | 3.777 | 4 | 2 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 0C690 | PLA | 080 | REHABILITATE REST AREA | 0.46032 | SHOPP | 2006 | 5070 | [5 empty] | 5233000 | 2680000 | 2680000 | F | F | F | 2322530.75 | 51.21% | 2007-10-01 | 2009-08-10 | 0 | 0 | 0 | 0.46032 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 0C720 | NEV | 080 | STORM WATER MANAGEMENT | 0.1725 | SHOPP | 2008 | 4253 | [5 empty] | 1312000 | 1269000 | 325000 | 296000 | 272000 | 376000 | 924594.7 | 96.72% | 2009-06-30 | 2010-07-01 | 0 | 0 | 0.13101 | 0.04149 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 0C770 | PLA | 080 | OVERLAY CONCRETE ROADWAY | 0.14809 | SHOPP | 2006 | 5072 | [5 empty] | 28520000 | 4237000 | 4237000 | F | F | F | 5662283.13 | 14.86% | 2007-09-12 | 2009-12-02 | 0 | 0 | 0.0134 | 0.13469 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 0E990 | PLA | 267 | PLACE HOT MIX ASPHALT | 0.18722 | SHOPP | 2008 | 5706 | [5 empty] | 5686000 | 1824000 | 285000 | 741000 | 171000 | 627000 | 2334012.94 | 32.08% | 2010-11-17 | 2012-07-20 | 0 | 0 | 0.00788 | 0.17934 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 0F210 | BUT | 099 | UPGRADE MBGR END TREATMENTS AND BRIDGE APPROACH RAIL | 0.22488 | SHOPP | 2010 | 3988 | [5 empty] | 4010000 | 1160000 | 50000 | 350000 | 10000 | 750000 | 303922.49 | 28.93% | 2011-09-28 | 2012-06-22 | 0 | 0 | 0.02714 | 0.19774 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 0F220 | ED | 050 | REPLACE BRIDGE | 4.2413 | SHOPP | 2012 | 3291 |  | X | X |  |  | 6702000 | 1861000 | E | 850000 | 11000 | 1000000 | 153964.73 | 27.77% | 2014-08-18 | 2016-10-01 | 0 | 2.1661 | 0.21 | 1.8652 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 0F230 | SAC | 050 | INSTALL TWO 4" MICRODECK SYSTEMS TO REHABILITATE TWO BRIDGE DECKS | 9.5765 | SHOPP | 2012 | 6226 | [5 empty] | 36685000 | 9520000 | 600000 | 3300000 | 120000 | 5500000 | 2382535.11 | 25.95% | 2013-09-01 | 2015-11-01 | 0 | 0.33857 | 0.58 | 8.6579 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 0F240 | SAC | 005 | PLACE 3/4" POLYESTER OVERLAY, REPLACE JT SEALS, APPROACH SLABS | 4.9198 | SHOPP | 2012 | 5826 | X |  |  |  |  | 8835000 | 2353000 | 257000 | 737000 | 45000 | 1314000 | 300.14 | 26.63% | 2015-01-15 | 2016-10-02 | 0.15402 | 4.6383 | 0.12753 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 0F270 | YUB | 065 | SCOUR MITIGATION BRIDGE REHAB | 1.56 | SHOPP | 2012 | 9730 |  | X | X |  |  | 3222000 | 1281000 | 261000 | 504000 | 95000 | 421000 | 291166.7 | 39.76% | 2014-08-15 | 2015-11-15 | 0 | 1.46 | 0.1 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 0F280 | SAC | 099 | REPLACE NON STANDARD BRIDGE RAIL ON BOTH SIDES OF 3 BRIDGES | 2.0765 | SHOPP | 2012 | 6912 | X |  |  |  |  | 14011000 | 5342000 | 425000 | 1124000 | 448000 | 3345000 | 504.05 | 38.13% | 2019-11-17 | 2021-02-16 | 1.4485 | 0.59515 | 0.03284 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 0F300 | ED | 050 | RETROFIT COLUMNS AND ADD BRACING | 6.9574 | SHOPP | 2012 | 3293 | [5 empty] | 4970000 | 1607000 | 250000 | 600000 | 32000 | 725000 | 575262.34 | 32.33% | 2013-08-15 | 2014-07-15 | 0 | 0.16667 | 2.3937 | 4.3971 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 0F310 | ED | 049 | CROSS BRACING SEISMIC RETROFIT, RAIL UPGRADE | 7.6986 | STIP | 2012 | 3122 | [5 empty] | 14407000 | 4725000 | 710000 | 1731000 | 208000 | 2076000 | 0 | 32.8% | 2016-05-02 | 2018-11-01 | 2.9068 | 4.3374 | 0.45448 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 0F370 | GLE | 005 | RAISE STRUCTURE OR LOWER ROADWAY PROFILE TO IMPROVE VERTICAL | 6.6293 | SHOPP | 2012 | 3707 | X |  |  |  |  | 7434000 | 3550000 | 580000 | 1275000 | 620000 | 1075000 | 0 | 47.75% | 2015-10-01 | 2016-10-01 | 2.2068 | 3.4225 | 1 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 0F520 | SAC | 099 | PLACE OPEN GRADED ASPHALT CONCRETE | 0.05307 | SHOPP | 2008 | 6915 | [5 empty] | 800000 | 432000 | 92000 | 220000 | 10000 | 110000 | 442337.65 | 54% | 2010-03-03 | 2010-09-28 | 0 | 0 | 0 | 0.05307 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 0F530 | BUT | 191 | PLACE HOT MIX ASPHALT | 0.04116 | SHOPP | 2008 | 2704 | [5 empty] | 940000 | 447000 | 120000 | 210000 | 7000 | 110000 | 270788.4 | 47.55% | 2010-07-06 | 2010-09-22 | 0 | 0 | 0 | 0.04116 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 0F580 | SAC | 080 | UPGRADE WEIGH STATION AND CCTV SYSTEMS | 0.1275 | SHOPP | 2008 | 6704 | [5 empty] | 390000 | 236000 | 47000 | 128000 | 15000 | 46000 | 339893.28 | 60.51% | 2010-12-28 | 2012-06-29 | 0 | 0 | 0.0675 | 0.06 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 0F590 | SAC | 005 | PAVEMENT REHABILATION WITH PCC SLAB REPLACEMENT AND HMA SHOULDERS AND | 0.75794 | SHOPP | 2008 | 5779 | [5 empty] | 120100000 | 12520000 | E | 2500000 | 20000 | 10000000 | 4814304.06 | 10.42% | 2011-03-24 | 2013-01-15 | 0 | 0 | 0 | 0.75794 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 0F640 | BUT | 162 | INSTALL TRAFFIC SIGNAL | 0.13679 | SHOPP | 2008 | 2631 | [5 empty] | 1636000 | 713000 | 143000 | 374000 | 50000 | 146000 | 1053692.76 | 43.58% | 2010-11-16 | 2011-11-16 | 0 | 0 | 0.03667 | 0.10012 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 0F680 | SAC | 080 | REPLACE JOINTS AND SUPER-REHAB | 2.1935 | SHOPP | 2012 | 6693 |  |  |  | X |  | 1735000 | 788000 | 105000 | 335000 | 8000 | 340000 | 243076.99 | 45.42% | 2013-04-01 | 2014-02-15 | 0 | 0 | 0.13 | 2.0635 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 0F690 | BUT | 070 | REPLACE BRIDGE | 4.2017 | SHOPP | 2012 | 2282 |  | X | X |  |  | 3505000 | 2090000 | 650000 | 790000 | 50000 | 600000 | 566693.2 | 59.63% | 2014-09-14 | 2016-01-01 | 0 | 3.86 | 0.34 | 0.00166 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 0F700 | YOL | 080 | SHOULDERS TO BE WIDENED | 0.24376 | SHOPP | 2008 | 8911 | [5 empty] | 6558000 | 1629000 | E | 518000 | 29000 | 1082000 | 996092.43 | 24.84% | 2010-12-22 | 2012-07-09 | 0 | 0 | 0 | 0.24376 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 0F810 | NEV | 020 | INSTALL RUMBLE STRIPS,OVERLAY,SIGNS | 0.07 | SHOPP | 2010 | 3989 | [5 empty] | 2588000 | 773000 | E | 318000 | 5000 | 450000 | 561934.45 | 29.87% | 2011-05-25 | 2012-04-26 | 0 | 0 | 0.01 | 0.06 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 0F820 | BUT | 070 | STREET BEAUTIFICATION PROJECT | 0.2 | PARTNERSHIP
03 | SHOPP | 0F880 | SAC | 005 | INSTALL NATIVE LANDSCAPING | 0.16052 | STIP | 2008 | 5827 | [5 empty] | 750000 | 250000 | H | H | H | 250000 | 89294.63 | 33.33% | 2010-04-26 | 2015-12-01 | 0 | 0 | 0.00052 | 0.16 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 0F890 | SUT | 099 | INSTALL NATIVE LANDSCAPING | 0.01052 | STIP | 2008 | 8365 | [5 empty] | 750000 | 250000 | H | H | H | 250000 | 46911.35 | 33.33% | 2010-06-30 | 2015-12-01 | 0 | 0 | 0.00052 | 0.01 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 0F910 | SAC | 016 | PLACE THERMOPLASTIC TRAFFIC STRIPE PLACE THERMOPLASTIC TRAFFIC STRIPE | 0.08309 | SHOPP | 2008 | 5986 | [5 empty] | 700000 | 422000 | 130000 | 200000 | 12000 | 80000 | 164802.31 | 60.29% | 2010-05-19 | 2011-08-25 | 0 | 0 | 0.05459 | 0.0285 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 0F920 | SAC | 050 | COLD PLANE AC PAVEMENT PLACE OPEN GRADED HMA | 0.11028 | SHOPP | 2010 | 6227 | [5 empty] | 998000 | 498000 | 115000 | 210000 | 8000 | 165000 | 508950.63 | 49.9% | 2011-01-24 | 2011-09-26 | 0 | 0 | 0 | 0.11028 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 0F930 | SUT | 099 | WIDEN AND SIGNALIZE OFFRAMPS | 0.05674 | PARTNERSHIP
03 | SHOPP | 1A140 | SAC | 051 | PLANTING AND IRRIGATION | 0.3003 | SHOPP | 2008 | 6386 | [5 empty] | 2200000 | 1318000 | 132000 | 583000 | 16000 | 587000 | 1158032.83 | 59.91% | 2009-10-15 | 2015-02-20 | 0 | 0 | 0.0203 | 0.28 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 1A530 | NEV | 020 | REALIGNMENT AND WIDENING ROADWAY | 0.25488 | SHOPP | 2004 | 3982 | [5 empty] | 22000000 | 4005000 | 4005000 | F | F | F | 10636789.04 | 18.2% | 2006-09-18 | 2008-09-19 | 0 | 0 | 0.17 | 0.08488 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 1A680 | ED | 050 | APPLY HOT MIX ASPHALT | 1.3729 | SHOPP | 2010 | 3229 | [5 empty] | 29202000 | 6010000 | 500000 | 1500000 | 10000 | 4000000 | 1046991.84 | 20.58% | 2010-11-29 | 2012-11-02 | 0 | 0 | 0.23 | 1.1429 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 1A731 | ED | 050 | STORM WATER QUALITY IMPROVEMENTS OVERLAY, WIDEN SHLDR, RPL CULVERTS | 7.7161 | SHOPP | 2012 | 3233A | [5 empty] | 13426000 | 8246000 | 3210000 | 2382000 | 1023000 | 1631000 | 5809726.98 | 61.42% | 2013-08-01 | 2015-01-15 | 0 | 2.95 | 1.35 | 3.4161 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 1A732 | ED | 050 | STORM WATER QUALITY IMPROVEMENTS OVERLAY, WIDEN SHLDR, REPL CULVERTS | 3.6584 | SHOPP | 2012 | 3233B |  |  |  | X |  | 11900000 | 6861000 | 1680000 | 2494000 | 715000 | 1972000 | 4178940.694 | 57.66% | 2013-02-22 | 2014-01-02 | 0 | 0 | 0.45482 | 3.2036 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 1A734 | ED | 050 | WATER QUALITY IMPROVEMENTS | 1.0007 | SHOPP | 2010 | 3233D |  |  |  | X |  | 3950000 | 3690000 | 790000 | 1500000 | 500000 | 900000 | 2883599.7985 | 93.42% | 2012-04-06 | 2013-12-01 | 0 | 0 | 0.29638 | 0.70435 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 1A73U | ED | 050 | STORM WATER QUALITY IMPROVEMENTS, ADD CURB, GUTTER, SIDEWALK, AND | 1.8837 | STIP | 2010 | 3208 |  |  |  | X |  | 60680000 | 30700000 | 4276000 | 12336000 | 3520000 | 10568000 | 16044148.4267 | 50.59% | 2011-02-10 | 2013-12-15 | 0 | 0 | 0.58 | 1.3037 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 1A842 | ED | 089 | STORM WATER QUALITY IMPROVEMENTS O/L, ADD DIKES AND RETENTION BASINS | 5.0102 | SHOPP | 2012 | 3453B |  | X | X |  |  | 19500000 | 9159000 | 1959000 | 3080000 | 600000 | 3520000 | 3634703.11 | 46.97% | 2014-06-15 | 2015-12-01 | 0 | 4.28 | 0.73023 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 1A843 | ED | 089 | STORM WATER QUALITY IMPROVEMENTS O/L, WIDEN, ADD DIKES & RET BASINS | 9.6173 | SHOPP | 2012 | 3453C |  | X | X |  |  | 14938000 | 6615000 | 2066000 | 2102000 | 849000 | 1598000 | 2657402.27 | 44.28% | 2014-10-15 | 2016-12-15 | 0 | 6.4973 | 3.12 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 1A844 | ED | 089 | STORM WATER QUALITY IMPROVEMENTS O/L, WIDEN, ADD DIKES & RET BASINS | 3.886 | SHOPP | 2012 | 3453D | [5 empty] | 22782000 | 8290000 | 2128000 | 2300000 | 1381000 | 2481000 | 5465029.94 | 36.39% | 2013-05-01 | 2016-10-01 | 0 | 0.35 | 0.10023 | 3.4358 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 1A845 | ED | 089 | STORM WATER QUALITY IMPROVEMENTS O/L, WIDEN, ADD DIKES & RET BASINS | 7.1705 | SHOPP | 2012 | 3453E |  | X | X |  |  | 12523000 | 6356000 | 2500000 | 1350000 | 506000 | 2000000 | 2411858.42 | 50.75% | 2014-09-01 | 2017-12-15 | 0 | 5.9005 | 1.27 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 1A910 | SUT | 099 | PAVEMENT REHABILITATION | 0.05786 | SHOPP | 2006 | 8363 | [5 empty] | 16552000 | 4010000 | 4010000 | F | F | F | 5484277.59 | 24.23% | 2007-04-02 | 2009-01-05 | 0 | 0 | 0 | 0.05786 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 1A920 | SUT | 020 | WIDEN SHOULDERS AND REHAB PAVEMENT | 1.1524 | SHOPP PA |  |  | X
03 | SHOPP | 1A950 | YOL | 505 | REPLACE CONCRETE PAVEMENT | 0.17826 | SHOPP | 2008 | 9501 | [5 empty] | 17010000 | 3005000 | E | 1000000 | 5000 | 2000000 | 1030864.96 | 17.67% | 2010-11-18 | 2011-08-26 | 0 | 0 | 0 | 0.17826 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 1A97W | COL | 020 | RESURFACE ASPHALT CONCRETE | 0.52214 | SHOPP | 2006 | 8130 | [5 empty] | 23524000 | 9238000 | 957078.952 | 3239900.0088 | 1854849.3571 | 3186171.6821 | 7562044.11 | 39.27% | 2006-11-22 | 2007-12-13 | 0 | 0 | 0.05381 | 0.46833 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 1C080 | NEV | 089 | WIDEN UNDERPASS | 1.2065 | STIP | 2012 | 3L43 | [5 empty] | 6750000 | 5590000 | 2590000 | 1000000 | 500000 | 1500000 | 1890824.38 | 82.81% | 2014-02-15 | 2015-09-14 | 0 | 0.53202 | 0.07 | 0.60445 | Caltrans | Local | Local | Local
03 | SHOPP | 1C111 | PLA | 089 | INSTALL INTELLIGENT TRANS. SYSTEM | 0.10865 | SHOPP | 2006 | 4262A | [5 empty] | 4185000 | 1376000 | 1376000 | F | F | F | 2330883.62 | 32.88% | 2008-04-18 | 2009-10-30 | 0 | 0 | 0.04869 | 0.05996 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 1C112 | PLA | 089 | INSTALL ITS AND TOS MICROWAVE | 0.37169 | SHOPP | 2010 | 4262B | [5 empty] | 2918000 | 1687000 | 465000 | 754000 | 167000 | 301000 | 1422547.68 | 57.81% | 2011-07-27 | 2012-12-04 | 0 | 0 | 0.14786 | 0.22383 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 1C490 | COL | 020 | REPLACE BRIDGE ON NEW ALIGNMENT (SCOUR) | 0.99687 | SHOPP | 2006 | 2938 | [5 empty] | 9055000 | 4591000 | 4591000 | F | F | F | 4202704.88 | 50.7% | 2008-05-30 | 2009-08-26 | 0 | 0 | 0.25 | 0.74687 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 1C971 | PLA | 267 | WATER QUALITY DRAINAGE IMPROVEMENT | 0.25151 | SHOPP | 2008 | 5702 | [5 empty] | 9097000 | 4472000 | 563000 | 1746000 | 651000 | 1512000 | 4658526.884 | 49.16% | 2009-03-19 | 2010-12-03 | 0 | 0 | 0.16706 | 0.08445 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 1E14U | ED | 050 | RECONSTRUCT BARRIER RAILING | 0.14914 | SHOPP | 2010 | 3262 | [5 empty] | 6028000 | 4055000 | 1244000 | 1004000 | 93000 | 1714000 | 2822064.59 | 67.27% | 2011-02-08 | 2011-11-03 | 0 | 0 | 0.05032 | 0.09882 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 1E510 | BUT | 070 | SEISMIC RETROFIT | 6.4372 | SHOPP | 2012 | 2269 | [5 empty] | 16402000 | 7007000 | 1250000 | 1250000 | 100000 | 4407000 | 2161179.11 | 42.72% | 2013-02-15 | 2016-11-01 | 0 | 0 | 0.25 | 6.1872 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 1E670 | SAC | 099 | RAC OVERLAY | 0.72862 | SHOPP | 2008 | 6901 | [5 empty] | 24010000 | 5010000 | E | 2000000 | 10000 | 3000000 | 2118823.37 | 20.87% | 2010-12-08 | 2013-02-01 | 0 | 0 | 0.00753 | 0.72109 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 1E760 | YUB | 020 | REMOVE MEDIAN LANES AND INSTALL LEFT TURN LANES AND | 3.3966 | SHOPP | 2012 | 9582 | [5 empty] | 3668000 | 1963000 | 100000 | 1000000 | 140000 | 723000 | 787023.72 | 53.52% | 2015-04-01 | 2015-12-01 | 0 | 2.2066 | 1.19 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 1E980 | YOL | 016 | INSTALL TRAFFIC SIGNAL | 0.2511 | SHOPP | 2008 | 8662 | [5 empty] | 1522000 | 1382000 | 456000 | 523000 | 124000 | 279000 | 1805984.5 | 90.8% | 2009-07-15 | 2010-08-04 | 0 | 0 | 0.13031 | 0.12079 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 1E990 | SAC | 099 | CONSTRUCT OUTER SEPARATION BARRIERS | 0.08168 | SHOPP | 2006 | 6906 | [5 empty] | 3600000 | 1229000 | 1229000 | F | F | F | 1237806.48 | 34.14% | 2007-12-05 | 2008-10-10 | 0 | 0 | 0 | 0.08168 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 1F020 | SUT | 020 | INSTALL TRAFFIC SIGNAL | 0.03099 | SHOPP | 2010 | 8137 | [5 empty] | 940000 | 512000 | 94000 | 243000 | 34000 | 141000 | 397413.59 | 54.47% | 2011-08-17 | 2012-03-02 | 0 | 0 | 0.0098 | 0.02119 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 1F030 | BUT | 099 | INSTALL RUMBLE STRIPS | 0.03 | SHOPP | 2010 | 2426 | [5 empty] | 997000 | 403000 | 70000 | 150000 | 3000 | 180000 | 103346.13 | 40.42% | 2011-06-30 | 2011-10-04 | 0 | 0 | 0 | 0.03 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 1F070 | ED | 089 | MITIGATION/PLANTING TREES | 0.16925 | SHOPP | 2008 | 3463 | [5 empty] | 450000 | 120000 | L | L | L | 120000 | 3083.56 | 26.67% | - - | - - | 0 | 0 | 0 | 0.16925 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 1F090 | SAC | 099 | ROUNDABOUT INTERSECTIONS WITH ADA ENHANCEMENTS | 1.0577 | PARTNERSHIP
03 | SHOPP | 1F330 | ED | 193 | IMPROVE SUPERELEVATION OF CURVE | 3.0034 | SHOPP | 2012 | 3626 | [5 empty] | 1705000 | 855000 | 160000 | 250000 | 205000 | 240000 | 239761.65 | 50.15% | 2013-11-01 | 2014-10-15 | 0 | 0.62105 | 0.39713 | 1.9852 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 1F340 | SAC | 051 | INSTALL YELLOW BEACONS AND/OR SIGNAL HEAD INDICATORS AT 8 | 0.0162 | SHOPP | 2010 | 6401 | [5 empty] | 315000 | 335000 | 75000 | 130000 | 5000 | 125000 | 239773.51 | 106.3% | 2011-06-20 | 2012-06-06 | 0 | 0 | 0 | 0.0162 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 1F360 | PLA | 080 | PLACE HOT MIX ASPHALT | 0.12294 | SHOPP | 2008 | 5049 | [5 empty] | 6010000 | 1505000 | E | 600000 | 5000 | 900000 | 587837.69 | 25.04% | 2011-02-03 | 2012-06-20 | 0 | 0 | 0.03097 | 0.09197 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 1F370 | SUT | 099 | PLACE HOT MIX ASPHALT | 0.17557 | SHOPP | 2008 | 8371 | [5 empty] | 16010000 | 2505000 | E | 1000000 | 5000 | 1500000 | 639432.94 | 15.65% | 2010-11-24 | 2011-10-25 | 0 | 0 | 0.01045 | 0.16512 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 1F400 | PLA | 080 | WIDENING EASTBOUND ROADWAY | 8.1308 | PARTNERSHIP
03 | SHOPP | 1F420 | BUT | 099 | SHOULDER WIDENING ON STRUCTURE | 4.95 | SHOPP | 2012 | 2427 |  | X | X |  |  | 2115000 | 1825000 | 350000 | 700000 | 175000 | 600000 | 436184.62 | 86.29% | 2014-10-15 | 2016-11-01 | 0 | 4.28 | 0.67 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 1F440 | SAC | 005 | UPGRADE CRASH CUSHIONS AT VARIOUS LOCATIONS | 0.07868 | SHOPP | 2010 | 5828 | [5 empty] | 3002000 | 910000 | 100000 | 300000 | 10000 | 500000 | 492984.1 | 30.31% | 2010-12-31 | 2011-07-20 | 0 | 0 | 0.00768 | 0.071 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 1F450 | SAC | 005 | PCC SLABS AND AC PAVEMENT TO BE REPLACED | 0.01639 | SHOPP | 2010 | 5829 | [5 empty] | 18002000 | 3410000 | 100000 | 1300000 | 10000 | 2000000 | 1432665.6 | 18.94% | 2010-12-21 | 2011-12-09 | 0 | 0 | 0 | 0.01639 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 1F460 | YUB | 070 | REHABILITATE ROADWAY | 0.19042 | SHOPP | 2010 | 9816 | [5 empty] | 15002000 | 3060000 | 300000 | 750000 | 10000 | 2000000 | 1041855.92 | 20.4% | 2011-01-27 | 2012-03-19 | 0 | 0 | 0.02894 | 0.16148 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 1F470 | SUT | 020 | PAVEMENT REHABILITATION | 0.39046 | SHOPP | 2010 | 8138 | [5 empty] | 16402000 | 3310000 | 300000 | 1000000 | 10000 | 2000000 | 1030604.35 | 20.18% | 2010-12-13 | 2012-01-26 | 0 | 0 | 0 | 0.39046 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 1F480 | YOL | 005 | RAC OVERLAY | 0.03291 | SHOPP | 2010 | 8564 | [5 empty] | 11002000 | 1860000 | 200000 | 550000 | 10000 | 1100000 | 603913.51 | 16.91% | 2010-12-31 | 2011-08-16 | 0 | 0 | 0 | 0.03291 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 1F500 | SUT | 099 | PERFORM HIGHWAY PLANTING AND INSTALL IRRIGATION SYSTEM | 0.14222 | SHOPP | 2010 | 8372 | [5 empty] | 2601000 | 705000 | H | 300000 | 5000 | 400000 | 466265.51 | 27.1% | 2010-12-10 | 2015-03-17 | 0 | 0 | 0.00142 | 0.1408 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 1F700 | SAC | 099 | LANDSCAPE WORK AT TWO INTERCHANGES | 0.05307 | PARTNERSHIP
03 | SHOPP | 1F720 | SAC | 005 | WIDENING, SIGNALIZATION, RAMP METERING, AND OVERHEAD SIGNS | 0.01824 | PARTNERSHIP
03 | SHOPP | 1F740 | COL | 020 | CAPM OVERLAY AND SHOULDER BACKING | 4.266 | SHOPP | 2010 | 2942 | [5 empty] | 9170000 | 2200000 | 250000 | 800000 | 50000 | 1100000 | 443515.25 | 23.99% | 2012-11-19 | 2014-12-15 | 0 | 0 | 0.21 | 4.056 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 1F750 | COL | 020 | AC OVERLAY | 0.48062 | SHOPP | 2010 | 2944 | [5 empty] | 11005000 | 2415000 | 200000 | 800000 | 15000 | 1400000 | 975608.89 | 21.94% | 2011-12-09 | 2012-09-26 | 0 | 0 | 0 | 0.48062 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 1F810 | SUT | 113 | PAVEMENT REHABILITATION AND OVERLAY | 3.8562 | SHOPP | 2010 | 8503 | [5 empty] | 17205000 | 3910000 | 400000 | 1200000 | 10000 | 2300000 | 529097.18 | 22.73% | 2011-08-19 | 2012-09-20 | 0 | 0 | 0.64 | 3.2162 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 1F820 | YUB | 020 | PAVEMENT REHABILITATION AND OVERLAY | 1.1216 | SHOPP | 2010 | 9586 | [5 empty] | 4237000 | 1756000 | 200000 | 520000 | 36000 | 1000000 | 739396.28 | 41.44% | 2011-08-18 | 2012-09-07 | 0 | 0 | 0.11978 | 1.0018 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 1F920 | NEV | 020 | INSTALL CRASH CUSHIONS/GUARD RAILS | 0.5446 | SHOPP | 2010 | 3990 | [5 empty] | 2278000 | 1053000 | E | 350000 | 3000 | 700000 | 280542.88 | 46.22% | 2011-12-07 | 2012-10-04 | 0 | 0 | 0.00815 | 0.53645 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 1F990 | BUT | 032 | ADA COMPLIANCE CURB RAMPS, SIGNALS, SIDEWALKS, CROSS SLOPES, ETC. | 5.0409 | SHOPP | 2012 | 2108 | X |  |  |  |  | 1622000 | 2380000 | 500000 | 700000 | 530000 | 650000 | 0 | 146.7% | 2016-02-15 | 2017-11-15 | 0.47644 | 3.7679 | 0.79654 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 2A920 | PLA | 089 | REHAB PAVEMENT AND DRAINAGE SYSTEM ENV IMPR PROGRAM PROJECT (EIP) | 13.2622 | SHOPP | 2010 | 3454 | [5 empty] | 42800000 | 26162000 | 3754000 | 12000000 | 1851000 | 8557000 | 16335153.27 | 61.13% | 2012-04-10 | 2015-10-14 | 0 | 0 | 2.12 | 11.1422 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 2A921 | PLA | 089 | ASPHALT CONCRETE SURFACING | 0.3057 | SHOPP | 2006 | 5281 | [5 empty] | 24869000 | 11036000 | 11036000 | F | F | F | 8856734.16 | 44.38% | 2007-12-18 | 2010-10-19 | 0 | 0 | 0.14744 | 0.15826 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 2A940 | PLA | 028 | RECONSTRUCT DRAINAGE FACILITIES | 0.48 | SHOPP | 2006 | 4678 | [5 empty] | 48935000 | 17280000 | 17280000 | F | F | F | 21490178.45 | 35.31% | 2008-05-20 | 2011-11-23 | 0 | 0 | 0.25 | 0.23 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 2C210 | PLA | 080 | PLANTING AND IRRIGATION | 0.04333 | SHOPP | 2004 | 5073 | [5 empty] | 1702000 | 857000 | 857000 | F | F | F | 810671.84 | 50.35% | 2006-02-06 | 2009-12-17 | 0 | 0 | 0 | 0.04333 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 2C843 | SAC | L5501 | FIRE AND LIFE SAFETY REPAIRS | 0.24879 | SHOPP | 2006 | 1649 | [5 empty] | 10700000 | 3353000 | 3353000 | F | F | F | 6233466.7 | 31.34% | 2008-04-01 | 2010-05-03 | 0 | 0 | 0 | 0.24879 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 2C844 | SAC | L5501 | CONSTRUCT STORAGE BUILDING AND ADD PHOTOVOLTAIC PANELS | 0.1894 | SHOPP | 2008 | 1653 | [5 empty] | 7778000 | 3219000 | 2000 | 1700000 | 14000 | 1503000 | 3039935.8 | 41.39% | 2010-06-02 | 2011-08-16 | 0 | 0 | 0.05262 | 0.13678 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 2C84U | SAC | L5501 | SAFETY REPAIRS AND NEW BUILDING | 0.16599 | SHOPP | 2004 | 7275 | [5 empty] | 4152000 | 1767000 | 1767000 | F | F | F | 3332017.55 | 42.56% | 2006-08-31 | 2008-03-03 | 0.00027 | 0 | 0 | 0.16572 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 2C860 | PLA | 080 | RECONSTRUCT ROADWAY | 6.2607 | SHOPP | 2008 | 5074 |  |  |  | X |  | 175000000 | 24602000 | N | 5014000 | 428000 | 19160000 | 14980796.51 | 14.06% | 2010-02-22 | 2013-12-01 | 0 | 0 | 0.33594 | 5.9248 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 2E611 | SAC | 080 | INSTALLING SIGNALS AT OFFRAMPS | 0.10904 | PARTNERSHIP
03 | SHOPP | 2E770 | PLA | 080 | REPAIR CULVERTS | 0.01 | SHOPP | 2006 | 5086 | [5 empty] | 350000 | 210000 | 210000 | F | F | F | 246325.14 | 60% | 2007-08-23 | 2007-12-06 | 0 | 0 | 0 | 0.01 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 2E900 | NEV | 049 | PLACE OPEN GRADED ASPHALT CONCRETE | 0.0128 | SHOPP | 2006 | 4114 | [5 empty] | 2700000 | 795000 | 795000 | F | F | F | 796116.2 | 29.44% | 2008-04-23 | 2009-06-29 | 0 | 0 | 0 | 0.0128 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 2E920 | SAC | 104 | REPLACE BRIDGE RAIL, PEDESTRIAN SIGNAL HEADS AND SIDEWALK/CURB | 0.94044 | PARTNERSHIP | [5 empty] | X
03 | SHOPP | 2E980 | PLA | 080 | INSTALL GROUND-IN RUMBLE STRIPS | 0.04508 | SHOPP | 2006 | 5091 | [5 empty] | 1330000 | 313000 | 313000 | F | F | F | 170799.2 | 23.53% | 2008-04-29 | 2008-08-18 | 0 | 0 | 0 | 0.04508 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 2E990 | GLE | 162 | PLACE ROCK SLOPE PROTECTION | 0.01341 | SHOPP | 2006 | 3910 | [5 empty] | 260000 | 268000 | 268000 | F | F | F | 345274.93 | 103.1% | 2008-08-13 | 2008-12-01 | 0 | 0 | 0 | 0.01341 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 2F000 | VAR | VAR | UPGRADE GUARDRAIL END TREATMENTS | 5.3312 | SHOPP | 2012 | 2945 |  | X | X |  |  | 7246000 | 2206000 | 160000 | 540000 | 6000 | 1500000 | 260683.07 | 30.44% | 2014-02-01 | 2015-11-15 | 0 | 3.75 | 0.1 | 1.4812 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 2F010 | YOL | 005 | AC OVERLAY | 0.3448 | SHOPP | 2010 | 8565 | [5 empty] | 16020000 | 2470000 | 150000 | 800000 | 20000 | 1500000 | 925606.47 | 15.42% | 2012-01-27 | 2012-08-02 | 0 | 0 | 0.02729 | 0.31751 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 2F020 | ED | 050 | AC OVERLAY AND PCC REPAIR | 1.1804 | SHOPP | 2010 | 3299 |  |  |  | X |  | 17025000 | 2770000 | 150000 | 1000000 | 20000 | 1600000 | 549080.27 | 16.27% | 2011-12-16 | 2013-08-01 | 0 | 0 | 0.01926 | 1.1612 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 2F030 | PLA | 080 | AC OVERLAY | 0.54131 | SHOPP | 2010 | 6229 | [5 empty] | 17020000 | 2470000 | 150000 | 800000 | 20000 | 1500000 | 545311.08 | 14.51% | 2011-11-14 | 2012-12-31 | 0 | 0 | 0.07541 | 0.4659 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 2F040 | SAC | 080 | PROFILE GRINDING | 0.25267 | SHOPP | 2010 | 6702 | [5 empty] | 7510000 | 960000 | 100000 | 250000 | 10000 | 600000 | 700122.1 | 12.78% | 2011-12-21 | 2012-08-24 | 0 | 0 | 0.0382 | 0.21447 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 2F050 | YOL | 113 | PCC PROFILE GRINDING | 0.33672 | SHOPP | 2010 | 9151 | [5 empty] | 7502000 | 960000 | 100000 | 250000 | 10000 | 600000 | 462556.63 | 12.8% | 2011-12-12 | 2013-05-01 | 0 | 0 | 0.00671 | 0.33001 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 2F150 | ED | 049 | LEFT TURN CHANNELIZATION | 1.2547 | SHOPP | 2012 | 3118 |  | X |  |  |  | 900000 | 720000 | 150000 | 250000 | 70000 | 250000 | 286412.36 | 80% | 2013-11-06 | 2015-09-01 | 0 | 0.28111 | 0.14 | 0.83357 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 2F210 | SAC | 050 | BRIDGE DECK REHABILITATION | 6.6037 | SHOPP | 2012 | 6231 | X |  |  |  |  | 38009000 | 8828000 | 1120000 | 3136000 | 51000 | 4521000 | 12094.32 | 23.23% | 2019-11-18 | 2021-07-18 | 0.06367 | 5.85 | 0.69 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 2F260 | PLA | 080 | REPAIR CUT SLOPE | 0.71 | SHOPP | 2010 | 5099 |  |  |  | X |  | 900000 | 536000 | 120000 | 200000 | 36000 | 180000 | 206213.25 | 59.56% | 2012-11-02 | 2013-12-15 | 0 | 0 | 0.05 | 0.66 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 2F300 | BUT | 070 | REHABILITATE PAVEMENT | 2.6023 | SHOPP | 2010 | 2283 |  |  |  | X |  | 10670000 | 1825000 | 300000 | 600000 | 100000 | 825000 | 373445.12 | 17.1% | 2012-12-05 | 2013-11-15 | 0 | 0 | 0.1033 | 2.499 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 2F350 | NEV | 020 | PAVEMENT REHABILITATION | 0.04066 | SHOPP | 2010 | 3991 |  |  |  | X |  | 12218000 | 3000000 | 500000 | 1000000 | 100000 | 1400000 | 690031.12 | 24.55% | 2012-12-21 | 2014-05-15 | 0 | 0 | 0.04066 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 2F360 | NEV | 020 | AC OVERLAY, REPLACE GUARDRAIL AND AC DIKE | 0.03586 | SHOPP | 2010 | 3992 | [5 empty] | 8541000 | 3000000 | 653000 | 1022000 | 135000 | 1190000 | 233612.93 | 35.12% | 2012-12-21 | 2014-12-15 | 0 | 0 | 0.03586 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 2F580 | SIE | 089 | COLD IN PLACE RECYCLE WITH 0.25 FT HMA OVERLAY | 0.24314 | SHOPP | 2010 | 8007 | [5 empty] | 6005000 | 1270000 | 50000 | 200000 | 20000 | 1000000 | 216105.32 | 21.15% | 2011-11-30 | 2012-09-13 | 0 | 0 | 0 | 0.24314 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 2F590 | YUB | 020 | SHOULDER WIDENING AND CURVE IMPROVEMENTS | 11.0685 | SHOPP | 2012 | 9588 | X |  |  |  |  | 17490000 | 6399000 | 787000 | 1137000 | 1571000 | 2904000 | 11059.15 | 36.59% | 2016-01-02 | 2018-01-02 | 3.8736 | 4.5172 | 2.6776 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 2F700 | YOL | 080 | RECONSTRUCT EMBANKMENT, ELECTRICAL REPAIR, SIDEWALK RECONSTRUCTION | 1.1233 | SHOPP | 2010 | 8912 |  |  |  | X |  | 960000 | 570000 | 50000 | 140000 | 20000 | 360000 | 454950.01 | 59.38% | 2012-10-16 | 2013-11-15 | 0 | 0 | 0.02419 | 1.0991 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 2F970 | COL | 020 | HMA OVERLAY | 4.4779 | SHOPP | 2012 | 2949 | [5 empty] | 2953000 | 755000 | 100000 | 290000 | 10000 | 355000 | 3962.68 | 25.57% | 2013-12-10 | 2015-04-30 | 0 | 0.87896 | 0.1 | 3.499 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 2M900 | SAC | 050 | RESURFACE BRIDGE DECKS | 0.02341 | SHOPP | 2008 | 6213 | [5 empty] | 3130000 | 782000 | E | 208000 | 2000 | 572000 | 516392.77 | 24.98% | 2009-05-20 | 2011-01-28 | 0 | 0 | 0.00341 | 0.02 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 3A010 | SAC | 005 | SLAB REPLACEMENT | 0.02 | SHOPP | 2006 | 5799 | [5 empty] | 21883000 | 4408000 | 4408000 | F | F | F | 2844740.04 | 20.14% | 2007-09-06 | 2009-08-06 | 0 | 0 | 0 | 0.02 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 3A220 | NEV | 080 | REHABILITATE ROADWAY | 1.0494 | SHOPP | 2008 | 4237 | [5 empty] | 73000000 | D | D | D | D | D | 11989927.5 | NA | 2008-10-29 | 2011-07-07 | 0 | 0 | 0.1 | 0.94943 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 3A260 | NEV | 049 | WIDEN AND ADD SHOULDERS | 0.06134 | SHOPP | 2004 | 4109 | [5 empty] | 2502000 | 682000 | 682000 | F | F | F | 2294690.35 | 27.26% | 2005-05-26 | 2006-10-19 | 0 | 0 | 0.01 | 0.05134 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 3C020 | SAC | 051 | PLACE CONCRETE MEDIAN BARRIER | 0.1151 | SHOPP | 2006 | 6395 | [5 empty] | 9337000 | 1959000 | 1959000 | F | F | F | 1736068.52 | 20.98% | 2008-02-06 | 2008-10-07 | 0 | 0 | 0 | 0.1151 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 3C380 | ED | 050 | STORM WATER MITIGATION | 14.4326 | SHOPP | 2012 | 3258 |  | X | X |  |  | 27000000 | 11469000 | 1300000 | 3741000 | 2650000 | 3778000 | 4965635.27 | 42.48% | 2014-11-01 | 2017-12-01 | 0 | 8.36 | 6.07 | 0.00264 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 3C760 | ED | 050 | INSTALL PIPELINERS | 0.26588 | SHOPP | 2008 | 3259 | [5 empty] | 2571000 | 1725000 | 787000 | 511000 | 67000 | 360000 | 1575956.89 | 67.09% | 2011-01-06 | 2011-09-08 | 0 | 0 | 0.22528 | 0.0406 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 3C870 | GLE | 005 | PLACE RUBBERIZED HOT MIX ASPHALT | 0.11608 | SHOPP | 2006 | 3704 | [5 empty] | 6190000 | 1144000 | 1144000 | F | F | F | 1292804.25 | 18.48% | 2008-06-03 | 2009-06-23 | 0 | 0 | 0 | 0.11608 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 3C890 | COL | 005 | RUBBERIZED WARM MIX ASPHALT | 0.4112 | SHOPP | 2008 | 2781 | [5 empty] | 36002000 | 5710000 | E | 2000000 | 10000 | 3700000 | 1518066.55 | 15.86% | 2011-01-13 | 2012-04-11 | 0 | 0 | 0.022 | 0.3892 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 3C900 | SAC | 012 | REHABILITATE PAVEMENT | 4.6758 | SHOPP | 2010 | 5957 |  |  |  | X |  | 7066000 | 1550000 | 200000 | 500000 | 100000 | 750000 | 371887.47 | 21.94% | 2012-10-31 | 2013-10-15 | 0 | 0 | 0.27575 | 4.4 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 3C930 | NEV | 080 | WIDEN EXISTING HIGHWAY | 0.13465 | SHOPP | 2004 | 4265 | [5 empty] | 3289000 | 2299000 | 2299000 | F | F | F | 1433101.6 | 69.9% | 2005-06-17 | 2007-01-05 | 0 | 0 | 0 | 0.13465 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 3E310 | SAC | 220 | REPAIR TRAVEL WAY | 0.1715 | SHOPP | 2006 | 7438 | [5 empty] | 160000 | 207000 | 207000 | F | F | F | 101786.42 | 129.4% | 2007-12-24 | 2008-04-24 | 0 | 0 | 0 | 0.1715 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 3E320 | PLA | 089 | STABILIZE CUT SLOPE WITH WIRE MESH DRAPERY SYSTEM | 0.02731 | SHOPP | 2006 | 5285 | [5 empty] | 184000 | 263000 | 263000 | F | F | F | 286377.92 | 142.9% | 2008-05-16 | 2008-12-04 | 0 | 0 | 0 | 0.02731 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 3E520 | SAC | 099 | SIGNALIZE INTERSECTION | 0.01023 | SHOPP | 2006 | 6909 | [5 empty] | 1000000 | 704000 | 704000 | F | F | F | 850156.41 | 70.4% | 2008-10-01 | 2009-11-20 | 0 | 0 | 0 | 0.01023 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 3E620 | BUT | 099 | REPLACE BRIDGE (SCOUR) | 11.5524 | SHOPP | 2012 | 2421 | [5 empty] | 11597000 | 3920000 | 500000 | 1300000 | 320000 | 1800000 | 2769384.4 | 33.8% | 2013-03-15 | 2014-10-01 | 0 | 0 | 2.0001 | 9.5522 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 3E840 | BUT | 070 | STABILIZE SLOPE | 0.02 | SHOPP | 2006 | 2275 | [5 empty] | 900000 | 358000 | 358000 | F | F | F | 250485.45 | 39.78% | 2007-10-09 | 2007-12-07 | 0 | 0 | 0 | 0.02 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 3E870 | YOL | 050 | IMPROVE BRIDGE DRAINAGE | 0.01124 | SHOPP | 2008 | 8780 | [5 empty] | 416000 | 302000 | 73000 | 110000 | 8000 | 111000 | 343888.1 | 72.6% | 2009-04-01 | 2009-08-27 | 0 | 0 | 0 | 0.01124 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 3E960 | SUT | 099 | MODIFY TRAFFIC SIGNAL | 0.03179 | SHOPP | 2008 | 8369 | [5 empty] | 770000 | 614000 | 133000 | 345000 | 18000 | 118000 | 651921.9 | 79.74% | 2009-07-20 | 2010-06-25 | 0 | 0 | 0 | 0.03179 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 3F000 | YUB | 020 | HMA OVERLAY | 3.4702 | SHOPP | 2012 | 9589 |  |  | X |  |  | 6619000 | 1519000 | 331000 | 560000 | 86000 | 542000 | 448.38 | 22.95% | 2015-01-01 | 2015-12-15 | 0 | 3.3302 | 0.14 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 3F030 | NEV | 080 | INSTALL CONCRETE MEDIAN BARRIER | 1.6102 | SHOPP | 2012 | 4286 |  |  |  | X |  | 722000 | 445000 | 140000 | 140000 | 15000 | 150000 | 252445.69 | 61.63% | 2013-04-15 | 2014-04-01 | 0 | 0.00022 | 0.04 | 1.57 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 3F050 | NEV | 020 | SEISMIC RETROFIT ON 11 BRIDGES | 6.2203 | SHOPP | 2012 | 4626 | X |  |  |  |  | 16685000 | 5590000 | 890000 | 1570000 | 830000 | 2300000 | 0 | 33.5% | 2015-10-18 | 2017-10-01 | 2.03 | 2.8503 | 1.34 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 3F080 | SAC | 051 | REHABILITATE AND RESURFACE BRIDGE DECK | 1.3498 | SHOPP | 2012 | 6403 | X |  |  |  |  | 1790000 | 512000 | 120000 | 123000 | 9000 | 260000 | 0 | 28.6% | 2015-05-01 | 2016-11-01 | 0.13142 | 1.1384 | 0.08 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 3F090 | SAC | 160 | SEISMIC RETROFIT ON 4 BRIDGES | 3.69 | SHOPP | 2012 | 5832 | [5 empty] | 7619000 | 2844000 | 405000 | 801000 | 149000 | 1489000 | 1901.21 | 37.33% | 2020-11-17 | 2023-01-17 | 3.6 | 0 | 0.09001 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 3F170 | SAC | 005 | ROADSIDE PAVEMENT AND SAFE ACCESS FOR MAINTENANCE EMPLOYEES | 1.2737 | SHOPP | 2012 | 5834 | X |  |  |  |  | 2776000 | 638000 | 70000 | 225000 | 18000 | 325000 | 0 | 22.98% | 2018-09-04 | 2019-08-05 | 0.21 | 1.0137 | 0.05 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 3F180 | SAC | 080 | PLACE VEGETATION CONTROL AND GRAVEL | 0.71652 | SHOPP | 2012 | 6705 |  |  | X |  |  | 2441000 | 504000 | 125000 | 160000 | 4000 | 215000 | 3556.52 | 20.65% | 2015-01-15 | 2016-03-01 | 0 | 0.68791 | 0.02861 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 3F240 | PLA | 080 | REPLACE AND INSTALL NEW SIGNS | 0.50175 | ER
03 | SHOPP | 3F320 | SAC | 050 | PLACE THIN HIGH FRICTION SURFACE | 1.6109 | SHOPP | 2012 | 6175 | [5 empty] | 1457000 | 410000 | 50000 | 150000 | 10000 | 200000 | 73889.9 | 28.14% | 2015-10-18 | 2016-02-01 | 0 | 0.00141 | 0.01576 | 1.5937 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 3F340 | SAC | 160 | PAINT ENTIRE BRIDGE | 4.61 | SHOPP | 2012 | 7284 | [5 empty] | 10255000 | 1920000 | 200000 | 510000 | 10000 | 1200000 | 0 | 18.72% | 2015-04-01 | 2016-11-01 | 0 | 4.5 | 0.11 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 3F410 | PLA | 049 | INSTALL METAL BEAM GUARD RAIL AT VARIOUS LOCATIONS | 3.73 | SHOPP | 2012 | 4783 | [5 empty] | 1690000 | 590000 | 140000 | 160000 | 15000 | 275000 | 0 | 34.91% | 2013-11-15 | 2014-11-15 | 0 | 3.67 | 0.06 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 3F440 | PLA | 089 | INSTALL NEW DI'S AND PIPE AND RAISE THE CENTERLINE PROFILE | 3.4402 | SHOPP | 2012 | 5286 |  | X | X |  |  | 3000000 | 1000000 | 100000 | 250000 | 50000 | 600000 | 0 | 33.33% | 2013-12-19 | 2014-11-04 | 0 | 0.68 | 0.36 | 2.4002 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 3F470 | SAC | 051 | REPLACE STOLEN WIRE AT MULTIPLE LOCATIONS | 0.03484 | SHOPP | 2012 | 6404 | [5 empty] | 350000 | 60000 | 5000 | 5000 | C | 50000 | 5777.17 | 17.14% | 2012-08-15 | - - | 0 | 0 | 0 | 0.03484 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 3F760 | BUT | 191 | REALIGN CURVE | 4.67 | PARTNERSHIP | [6 empty] | O
03 | SHOPP | 3M750 | SAC | 080 | REPLACE TOWER BRIDGE OPERATING ROPE | 0.17106 | SHOPP | 2010 | 6694 | [5 empty] | 600000 | 348000 | 70000 | 170000 | 8000 | 100000 | 572330.63 | 58% | 2011-09-23 | 2012-09-10 | 0 | 0 | 0.00104 | 0.17002 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 4A240 | NEV | 080 | REPLACE COMFORT STATIONS | 0.55361 | SHOPP | 2008 | 5058 | [5 empty] | 8492000 | 7196000 | 310000 | 4181000 | 5000 | 2700000 | 4461389.02 | 84.74% | 2009-07-27 | 2013-01-15 | 0 | 0 | 0 | 0.55361 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 4A530 | GLE | 005 | REPLACE METAL BEAM GUARD RAILS AND INSTALL CRASH CUSHIONS | 0.07782 | SHOPP | 2008 | 2851 | [5 empty] | 2405000 | 835000 | 1000 | 351000 | 41000 | 442000 | 348489.27 | 34.72% | 2010-10-11 | 2011-10-14 | 0 | 0 | 0 | 0.07782 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 4A570 | YUB | 070 | WIDEN HIGHWAY | 0.08306 | SHOPP | 2004 | 9804 | [5 empty] | 3496000 | 1116000 | 1116000 | F | F | F | 2631913.34 | 31.92% | 2006-06-30 | 2007-11-15 | 0 | 0 | 0.00466 | 0.0784 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 4A650 | PLA | 080 | REHABILITATE CULVERTS | 0.12793 | SHOPP | 2008 | 5064 | [5 empty] | 2469000 | 2209000 | 839000 | 820000 | 30000 | 520000 | 1687228.3 | 89.47% | 2009-04-15 | 2009-10-30 | 0 | 0 | 0 | 0.12793 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 4A700 | PLA | 080 | REPLACE BRIDGE | 0.24075 | SHOPP | 2006 | 4242 | [5 empty] | 26698000 | 6956000 | 6956000 | F | F | F | 4940025.81 | 26.05% | 2008-02-29 | 2009-12-16 | 0 | 0 | 0.05 | 0.19075 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 4C220 | NEV | 080 | REPLACE HEATING SYSTEM | 0.08129 | SHOPP | 2008 | 4282 | [5 empty] | 2100000 | 1128000 | 282000 | 550000 | 21000 | 275000 | 1083766.59 | 53.71% | 2010-02-09 | 2011-01-05 | 0 | 0 | 0 | 0.08129 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 4E320 | PLA | 065 | RECONSTRUCT INTERCHANGE | 1.46 | PARTNERSHIP
03 | SHOPP | 4E390 | BUT | 070 | ASPHALT CONCRETE DITCH AND PAVING | 0.01 | SHOPP | 2008 | 2280 | [5 empty] | 250000 | 295000 | 74000 | 143000 | 18000 | 60000 | 330163.78 | 118% | 2008-10-02 | 2009-05-22 | 0 | 0 | 0 | 0.01 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 4E410 | ED | 050 | COVER CUT SLOPES WITH WIRE MESH DRAPERY | 0.03268 | SHOPP | 2008 | 3295 | [5 empty] | 900000 | 657000 | 143000 | 262000 | 16000 | 236000 | 518581.19 | 73% | 2009-06-24 | 2010-08-13 | 0 | 0 | 0 | 0.03268 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 4E430 | YUB | 070 | MBGR REMOVE STREES ADD PLANTS AND LANDSCAPE | 0.04358 | SHOPP | 2008 | 9800 | [5 empty] | 1000000 | 466000 | 153000 | 241000 | 1000 | 71000 | 345295.77 | 46.6% | 2011-01-11 | 2012-07-19 | 0 | 0 | 0 | 0.04358 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 4E590 | ED | 049 | INCREASE SUPERELEVATION OF CURVE | 2.3636 | SHOPP | 2012 | 3119 |  |  |  | X |  | 1618000 | 983000 | 164000 | 288000 | 245000 | 286000 | 668383.61 | 60.75% | 2013-05-15 | 2014-04-01 | 0 | 0 | 0.46 | 1.9036 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 4E650 | GLE | 162 | INSTALL ADA RAMP IMPROVE CURVE | 0.08028 | SHOPP | 2010 | 3913 | [5 empty] | 353000 | 462000 | 66000 | 220000 | 56000 | 120000 | 387994.04 | 130.9% | 2011-03-03 | 2011-08-22 | 0 | 0 | 0.03663 | 0.04365 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 4E860 | PLA | 193 | IMPROVE AND WIDEN CURVE | 9.2 | SHOPP | 2012 | 5580 | [5 empty] | 12463000 | 4930000 | 1400000 | 1641000 | 743000 | 1146000 | 1161226.36 | 39.56% | 2015-05-01 | 2016-07-16 | 0 | 5.7 | 3.5 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 4E900 | PLA | 065 | SIGNALIZE AND WIDEN SB EXIT RAMP | 0.08925 | PARTNERSHIP | [6 empty] | O
03 | SHOPP | 4E990 | BUT | 099 | INSTALL TRAFFIC SIGNAL | 0.80481 | SHOPP | 2010 | 2429 |  |  |  | X |  | 900000 | 535000 | 80000 | 240000 | 15000 | 200000 | 457813.02 | 59.44% | 2012-07-19 | 2013-10-15 | 0 | 0 | 0.02334 | 0.78147 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | 4M200 | COL | 005 | SUB-SCOUR MITIGATION-7 BRIDGES | 1.6237 | SHOPP | 2012 | 2789 |  | X | X |  |  | 970000 | 858000 | 250000 | 218000 | 140000 | 250000 | 274851.78 | 88.45% | 2014-04-01 | 2016-01-05 | 0 | 0.83 | 0.52 | 0.27373 | Caltrans | Caltrans | Caltrans | Caltrans
03 | SHOPP | MINOR |  |  | SHOPP MINOR | 25.9744 | MINOR
04 | SHOPP | 01406 | ALA | 080 | CONSTRUCT BUILDING AND FUEL STATION | 1.5618 | SHOPP | 2008 | 0063X | [5 empty] | 9061000 | 6612000 | 764000 | 2600000 | 38000 | 3210000 | 6884529.4332 | 72.97% | 2010-01-01 | 2012-02-13 | 0 | 0 | 0.16607 | 1.3958 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 01407 | ALA | 080 | PLANTING AND IRRIGATION | 5.4804 | SHOPP | 2010 | 0063Y | [5 empty] | 1198000 | 658000 | H | 250000 | 18000 | 390000 | 563269.8668 | 54.92% | 2012-12-30 | 2015-02-01 | 0 | 0.02315 | 0.01877 | 5.4385 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 01408 | ALA | 080 | SFOBB MAINTENANCE OPERATIONS BUILDING-PHASE 1 | 19.7185 | SHOPP | 2012 | 0063L | [5 empty] | 46000000 | 9050000 | 600000 | 4500000 | 50000 | 3900000 | 1367425 | 19.67% | 2013-02-01 | 2014-08-01 | 0 | 0.43345 | 0.33709 | 18.9479 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 01410 | ALA | 080 | SFOBB MAINTENANCE WAREHOUSE PHASE 2 | 9.7307 | SHOPP | 2012 | 0063L |  |  | X |  |  | 21400000 | 5456000 | 656000 | 2300000 | 300000 | 2200000 | 0 | 25.5% | 2014-09-15 | 2016-03-01 | 0 | 9.499 | 0.23163 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 01411 | ALA | 080 | SFOBB RESOURCE CENTER PHASE III | 20.2474 | SHOPP | 2012 | 0063L | [5 empty] | 13286000 | 1453000 | 1400000 | H | 53000 | H | 0 | 10.94% | 2014-12-08 | 2016-03-26 | 0 | 19.9897 | 0.25763 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 16030 | ALA | 084 | REPLACE BRIDGE | 11.0605 | SHOPP | 2012 | 0084B | X | X | X |  |  | 33998000 | 12299000 | 2000000 | 5000000 | 299000 | 5000000 | 2479355.4 | 36.18% | 2015-01-01 | 2017-12-01 | 3.5816 | 7.479 | 0 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 16372 | SF | 101 | SOUTH ACCESS TO GOLDEN GATE BRIDGE, DOYLE DR REPLACEMENT PR, UTILITY | 0.33104 | STIP | 2012 | 0619A | [5 empty] | 22789000 | 4153000 | H | 83000 | N | 4070000 | 2239100.2007 | 18.22% | 2009-06-29 | 2012-12-31 | 0 | 0 | 0.00044 | 0.3306 | Local | Caltrans | Caltrans | Caltrans
04 | SHOPP | 16373 | SF | 101 | RECONSTRUCT INTERCHANGE | 0.61055 | STIP | 2012 | 0619A | [5 empty] | 95520000.3431 | 27233000 | H | 1260000 | N | 25973000 | 29976391.0414 | 28.51% | 2009-10-23 | 2012-07-15 | 0 | 0 | 0.02825 | 0.5823 | Local | Caltrans | Caltrans | Caltrans
04 | SHOPP | 17240 | ALA | 084 | REALIGN CURVES AND SHOULDERS | 1.0839 | SHOPP | 2006 | 0086Z | [5 empty] | 38685000 | 6338000 | 6338000 | F | F | F | 17286981.84 | 16.38% | 2007-01-10 | 2013-04-16 | 0 | 0 | 0 | 1.0839 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 17241 | ALA | 084 | INSTALL EROSION CONTROL | 0.64763 | SHOPP | 2010 | 0087N |  |  |  | X |  | 290000 | 170000 | 20000 | 60000 | 10000 | 80000 | 108332.76 | 58.62% | 2011-02-02 | 2013-12-01 | 0 | 0.00486 | 0.05973 | 0.58304 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 17243 | ALA | 580 | REQUIRED ENVRONMENTAL MITIGATION FOR EA 04-17240 PPNO 0086Z. | 0.46719 | SHOPP | 2010 | 0087R | [5 empty] | 2650000 | 550000 | 10000 | 30000 | 200000 | 310000 | 353267.32 | 20.75% | 2011-09-29 | 2015-12-31 | 0 | 0.02053 | 0.03497 | 0.41169 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 17244 | ALA | 084 | ENVIRONMENTAL MITIGATION | 6.1548 | SHOPP | 2012 | 0085Q | X | X | X |  |  | 3440000 | 1230000 | 130000 | 400000 | 250000 | 450000 | 240167.65 | 35.76% | 2014-10-17 | 2018-11-01 | 0.49869 | 5.3368 | 0.31935 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 20950 | MRN | 001 | REPLACE BRIDGE | 2.4466 | SHOPP | 2012 | 0326A | [5 empty] | 7252000 | 2790000 | 1080000 | 630000 | 270000 | 810000 | 0 | 38.47% | 2016-06-01 | 2017-12-31 | 1.9488 | 0.47156 | 0.02628 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 23562 | SM | 101 | REPLACE BRIDGE STRUCTURE AT SAN FRANCISQUIT0 CREEK | 8.3944 | SHOPP | 2012 | 0685P | [5 empty] | 9720000 | 7156000 | 2431000 | 1600000 | 325000 | 2800000 | 3769553.44 | 73.62% | 2013-11-01 | 2016-04-01 | 0 | 0.74121 | 0.75646 | 6.8967 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 24992 | SM | 082 | MODIFY TRAFFIC SIGNALS | 0.05923 | SHOPP | 2008 | 0645E | [5 empty] | 9267000 | 2210000 | H | 1160000 | 30000 | 1020000 | 3984232.1896 | 23.85% | 2010-07-20 | 2012-10-31 | 0 | 0 | 0.00478 | 0.05445 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 25380 | NAP | 121 | BRIDGE REPLACEMENT | 0.321 | SHOPP | 2002 | 0381H | [5 empty] | 20750000 | 3873000 | 3873000 | F | F | F | 7413160.07 | 18.67% | 2003-02-25 | 2008-01-14 | 0 | 0 | 0.321 | 0 | Local | Local | Local | Caltrans
04 | SHOPP | 25940 | NAP | 029 | LEFT TURN CHANELIZATION AND PAVEMEN REHABILITATION | 11.6493 | SHOPP | 2012 | 0378C |  | X | X |  |  | H | D | H | H | H | H | 0 | NA | 2015-02-01 | 2016-12-31 | 0 | 5.2515 | 6.3977 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 25941 | NAP | 029 | REHABILITATE ROADWAY | 10.2234 | SHOPP | 2012 | 0378C |  | X | X |  |  | 22437669 | 11795000 | 2700000 | 5025000 | 540000 | 3530000 | 8484392.9 | 52.57% | 2015-03-01 | 2017-08-01 | 0 | 6.4618 | 3.7616 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 26490 | SCL | 017 | DRAINAGE SYSTEM TO BE REPLACED | 1.5314 | SHOPP | 2010 | 0390D | [5 empty] | 27773000 | 12632000 | 4155000 | 3252000 | 1160000 | 4065000 | 10832436.99 | 45.48% | 2011-04-25 | 2013-06-30 | 0 | 0 | 0 | 1.5314 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 28381 | SON | 116 | CONSTRUCT RETAINING WALLS | 3.8733 | SHOPP | 2008 | 0832 | [5 empty] | 26828000 | 14030000 | 2330000 | 6800000 | 1200000 | 3700000 | 14974516.11 | 52.3% | 2009-12-14 | 2012-06-07 | 0 | 0 | 0.59782 | 3.2755 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 28382 | SON | 116 | MITIGATION - TREE PLANTING AND CREEK CHANNELIZATION | 7.7287 | SHOPP | 2010 | 0832A | [5 empty] | 6313000 | 2520000 | 20000 | 1000000 | 300000 | 1200000 | 1299454.96 | 39.92% | 2012-12-01 | 2017-04-01 | 0 | 0 | 0.02793 | 7.7008 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 29227 | ALA | 080 | CONSTRUCT BIKEWAY | 0.29728 | SHOPP | 2010 | 0063W | [5 empty] | 5423000 | 2095000 | E | 1000000 | 45000 | 1050000 | 1989898.64 | 38.63% | 2011-11-22 | 2013-02-27 | 0 | 0 | 0.12608 | 0.1712 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 29900 | SOL | 080 | REHABILITATE ROADSIDE REST AREA | 1.5415 | SHOPP | 2008 | 4319 | [5 empty] | 8227000 | 4205000 | 575000 | 2465000 | 15000 | 1150000 | 5641517.67 | 51.11% | 2009-08-12 | 2012-08-30 | 0 | 0 | 0.19256 | 1.3489 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 44421 | NAP | 121 | REALIGN CURVES AND WIDEN SHOULDER | 0.04482 | SHOPP | 2006 | 0380M | [5 empty] | 14870000 | 9270000 | 9270000 | F | F | F | 12702286.99 | 62.34% | 2008-11-27 | 2011-02-03 | 0 | 0 | 0.04482 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 44630 | SOL | 084 | REPLACE CACHE SLOUGH FERRY | 0.00695 | SHOPP | 2006 | 5402 | [5 empty] | 2921000 | 1532000 | 1532000 | A | A | A | 1450257.27 | 52.45% | 2009-03-10 | 2011-01-28 | 0 | 0 | 0.00028 | 0.00667 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 44790 | ALA | 238 | REHABILITATE ROADWAY | 0.14842 | SHOPP | 2008 | 0091N | [5 empty] | 25450000 | 8947000 | 51000 | 3497000 | 399000 | 5000000 | 6167379.42 | 35.16% | 2010-07-06 | 2012-02-10 | 0 | 0 | 0.14842 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 44883 | SCL | 152 | PLANTING AND ENVIRONMENTAL MITIGATION | 3.056 | SHOPP | 2010 | 0485N | [5 empty] | 1085000 | 555000 | 25000 | 350000 | 5000 | 175000 | 584233.59 | 51.15% | 2012-01-10 | 2015-10-01 | 0 | 0 | 0.01269 | 3.0434 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 44884 | SCL | 152 | ENVIRONMENTAL SPECIES MITIGATION | 4.094 | SHOPP | 2012 | 0487M |  |  |  | X |  | 600000 | 173000 | H | 108000 | 5000 | 60000 | 0 | 28.83% | 2013-07-10 | 2014-06-10 | 0 | 0.05403 | 0.10321 | 3.9368 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 1E090 | SCL | 017 | PLACE ASPHALT CONCRETE | 0.06344 | SHOPP | 2010 | 0087P | [5 empty] | 6510000 | 1420000 | 10000 | 650000 | 10000 | 750000 | 911243.53 | 21.81% | 2011-03-03 | 2012-02-02 | 0 | 0 | 0.00685 | 0.05659 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 2E230 | CC | 004 | TREAT BRIDGE DECK WITH METHACRYLATE RESIN,REPLACE JOINT SEALS AND | 0.9728 | SHOPP | 2010 | 2177A | [5 empty] | 1893000 | 661000 | 33000 | 340000 | 5000 | 283000 | 164630.08 | 34.92% | 2012-08-30 | 2014-10-08 | 0 | 0 | 0.0161 | 0.9567 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 0A020 | SON | 001 | REALIGN ROADWAY | 7.0318 | SHOPP | 2012 | 0748E | X |  |  |  |  | 23500000 | 7500000 | 3000000 | 1800000 | 500000 | 2200000 | 2730657.88 | 31.91% | 2016-02-01 | 2017-02-01 | 2.4523 | 4.386 | 0.1935 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 0A090 | SOL | 080 | LENGHTENING ON-RAMP AND WIDEN BRIDGE. | 4.0399 | SHOPP | 2012 | 5302C |  |  |  | X |  | 4079000 | 2698000 | 528000 | 1300000 | 70000 | 800000 | 2903217.44 | 66.14% | 2013-03-19 | 2014-01-31 | 0 | 0.30022 | 0.16707 | 3.5726 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 0A535 | SOL | 080 | EASTBOUND CORDELIA TRUCK SCALES RELOCATION PROJECT | 10.6241 | STIP | 2010 | 5301R |  |  |  | X |  | 118600000 | 29100000 | 6800000 | 12200000 | 400000 | 9700000 | 5447900.55 | 24.54% | 2011-11-16 | 2013-09-30 | 0 | 0 | 1.2239 | 9.4003 | Local | Local | Caltrans | Caltrans
04 | SHOPP | 0A710 | ALA | 880 | MODIFY INTERCHANGE AND CONSTRUCT SOUNDWALLS FOR SAFETY IMPROVEMENTS | 15.0084 | SHOPP | 2010 | 0044C | [5 empty] | 67300000 | 22887000 | 4200000 | 7387000 | G | 11300000 | 4109741.8 | 34.01% | 2013-08-07 | 2017-03-01 | 0 | 0.3459 | 0.34543 | 14.317 | Local | Local | Local | Caltrans
04 | SHOPP | 0A790 | CC | 004 | UPGRADE TRAFFIC BARRIER AND GUARDRAIL END TERMINALS AT VARIOUS | 3.4129 | SHOPP | 2012 | 0075C | [5 empty] | 5301000 | 3085000 | 800000 | 1100000 | 85000 | 1100000 | 1724975.22 | 58.2% | 2013-02-01 | 2016-08-16 | 0 | 0.87637 | 0.30512 | 2.2314 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 0A840 | CC | 004 | INSTALL MEDIAN BUFFER ZONE AND UPGRADE SHOULDERS | 6.2821 | SHOPP | 2008 | 0203H |  |  |  | X |  | 24676000 | 11490000 | 3980000 | 3500000 | 510000 | 3500000 | 10172451.57 | 46.56% | 2011-06-29 | 2013-08-01 | 0 | 0 | 0.50542 | 5.7767 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 0A871 | SF | 001 | UPGRADE GUARDRAIL END TERMINALS | 0.01641 | SHOPP | 2008 | 0622D | [5 empty] | 1757000 | 660000 | H | 450000 | 10000 | 200000 | 1036903.1553 | 37.56% | 2010-08-19 | 2011-07-06 | 0 | 0 | 0.01641 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 0C740 | MRN | 101 | ASPHALT CONCRETE SURFACING | 1.4012 | SHOPP | 2010 | 0342B | [5 empty] | 24463000 | 5130000 | 200000 | 2440000 | 50000 | 2440000 | 1623840.39 | 20.97% | 2012-02-03 | 2013-03-15 | 0 | 0 | 0.64734 | 0.75385 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 0C852 | MRN | 101 | RESURFACING PAVEMENT | 0.37929 | SHOPP | 2010 | 0348C | [5 empty] | 26010000 | 4120000 | 10000 | 1500000 | 10000 | 2600000 | 1688610.58 | 15.84% | 2010-12-31 | 2012-08-31 | 0 | 0 | 0.05258 | 0.32671 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 0G130 | SCL | 082 | INSTALL NEW SIGNALS AND UPGRADE WHEELCHAIR RAMPS | 0.22076 | SHOPP | 2010 | 0425G | [5 empty] | 650000 | 640000 | E | 300000 | 140000 | 200000 | 480985.67 | 98.46% | 2012-11-16 | 2013-05-05 | 0 | 0 | 0.05005 | 0.17071 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 0G140 | SCL | 085 | INSTALL DRAINAGE IMPROVEMENTS | 0.10717 | SHOPP | 2010 | 0429W | [5 empty] | 500000 | 360000 | E | 160000 | 60000 | 140000 | 439003.47 | 72% | 2012-04-13 | 2012-11-01 | 0 | 0 | 0.06456 | 0.04261 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 0G170 | SM | 001 | INSTALL TRAFFIC SIGNAL | 1.1265 | SHOPP | 2010 | 0624F |  |  |  | X |  | 466000 | 230000 | N | 90000 | 10000 | 130000 | 392170.4 | 49.36% | 2012-08-16 | 2013-12-15 | 0 | 0 | 0.1264 | 1.0001 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 0G220 | ALA | VAR | CONSTRUCT NEW ADA COMPLIANT CURB RAMP | 5.5782 | SHOPP | 2012 | 0142F |  | X | X |  |  | 6105000 | 1380000 | 130000 | 520000 | 80000 | 650000 | 279027.02 | 22.6% | 2014-09-29 | 2015-10-01 | 0 | 5.1705 | 0.40777 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 0G310 | SON | 121 | INSTALL SOFT MEDIAN BARRIER AND SHOULDER RUMBLE STRIP | 0.05359 | SHOPP | 2010 | 0814D | [5 empty] | 859000 | 472000 | E | 172000 | 43000 | 257000 | 366902.6 | 54.95% | 2012-07-10 | 2013-02-01 | 0 | 0 | 0.01934 | 0.03425 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 0G640 | SON | 116 | BRIDGE SEISMIC RETROFIT | 1.2082 | SHOPP | 2012 | 0756 | X |  |  |  |  | 14712000 | 5148000 | 1030000 | 1177000 | 735000 | 2206000 | 0 | 34.99% | 2016-11-30 | 2018-11-30 | 1 | 0.20817 | 0 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 0G660 | SOL | 084 | REPLACE BRIDGE SUPERSTRUCTURE | 8.7075 | SHOPP | 2012 | 0886 | [5 empty] | 22950000 | 8442000 | 1836000 | 2754000 | 1098000 | 2754000 | 0 | 36.78% | 2016-08-15 | 2018-10-01 | 8.7075 | 0 | 0 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 0G710 | SCL | 082 | BRIDGE SEISMIC RESTORATION | 2.1718 | SHOPP | 2012 | 0498 |  | X | X |  |  | 1325000 | 768000 | H | 423000 | 7000 | 338000 | 0 | 57.96% | 2014-07-01 | 2015-07-01 | 0 | 2.1539 | 0.01788 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 0G720 | SCL | 152 | UPGRADE INTERSECTION AND INSTALL SIGNAL | 3.3615 | SHOPP | 2012 | 0552 | X |  |  |  |  | 3459000 | 1314000 | 468000 | 432000 | 144000 | 270000 | 0 | 37.99% | 2016-05-01 | 2017-07-01 | 1.8562 | 1.5053 | 0 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 0G750 | SOL | 113 | INSTALL SINGLE & DOUBLE THRIE BEAM MEDIAN BARRIER | 0.77658 | SHOPP | 2012 | 0916 |  | X | X |  |  | 383000 | 275000 | E | 145000 | 10000 | 120000 | 0 | 71.8% | 2014-03-15 | 2015-05-01 | 0 | 0.75508 | 0.02006 | 0.00144 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 0T10U | SOL | 012 | WIDEN AND REHABILITATE ROADWAY | 0.01202 | SHOPP | 2006 | 8059B | [5 empty] | 60045000 | 17517500 | 17507000 | 4000 | 1000 | 5500 | 14967613.752 | 29.17% | 2008-12-17 | 2011-07-05 | 0 | 0 | 0.00575 | 0.00627 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 1123H | SM | 001 | MITIGATION AT DISPOSAL SITE, N & S PORTALS, S ROCK CUT & POND REPAIR | 5.9978 | ER
04 | SHOPP | 1637E | SF | 101 | SOUTH ACCESS TO GOLDEN GATE BRIDGE DOYLE DR REPLACEMENT PROJECT-ALL | 4.8708 | SHOPP | 2010 | 0619E | [5 empty] | 82283000 | 1489000 | K | K | 1489000 | K | 1167373.48 | 1.81% | 2009-09-01 | 2014-07-01 | 0 | 0 | 2.8607 | 2.0101 | Local | Caltrans | Caltrans | Caltrans
04 | SHOPP | 1637F | SF | 101 | SOUTH ACCESS TO GOLDEN GATE BRIDGE ADVANCED ENV MITIGATION, PLANT MATL | 0.63161 | STIP | 2012 | 0619A |  |  |  | X |  | 800000 | 164000 | H | 24000 | N | 140000 | 281933.2611 | 20.5% | 2009-06-15 | 2013-07-01 | 0 | 0 | 0.099 | 0.53261 | Local | Caltrans | Caltrans | Caltrans
04 | SHOPP | 1637G | SF | 101 | SOUTH ACCESS TO GOLDEN GATE BRIDGE DOYLE DR REPLACEMENT PROJ ADVANCED | 0.78507 | STIP | 2012 | 0619A |  |  |  | X |  | 2500000 | 394999.5875 | H | 44999.5875 | N | 350000 | 475722.2533 | 15.8% | 2010-02-15 | 2013-07-15 | 0 | 0 | 0.09753 | 0.68754 | Local | Caltrans | Caltrans | Caltrans
04 | SHOPP | 1637H | SF | 101 | SOUTH ACCESS TO GOLDEN GATE BRIDGE DOYLE DR REPLACEMENT PROJ-ENV | 0.36808 | STIP | 2012 | 0619A | [5 empty] | 3000000.4799 | 1032000 | H | 132000 | N | 900000 | 1084862.5788 | 34.4% | 2009-07-22 | 2012-07-11 | 0 | 0 | 0.00045 | 0.36763 | Local | Caltrans | Caltrans | Caltrans
04 | SHOPP | 1637K | SF | 001 | CREEK MITIGATION CULVERT DRAINAGE MITIGATION . | 1.9261 | SHOPP | 2010 | 0619J | [5 empty] | 900000 | 1200000 | H | 900000 | N | 300000 | 445285.44 | 133.3% | 2011-06-21 | 2012-12-01 | 0 | 0 | 0.42711 | 1.499 | Local | Caltrans | Caltrans | Caltrans
04 | SHOPP | 1637N | SF | 101 | STORM DRAIN AND OUTFALL IMPROVEMENT IMPROVEMENTS | 4.3593 | SHOPP | 2012 | 0619K |  | X | X |  |  | 8200000 | 3400000 | H | 2000000 | N | 1400000 | 117116.11 | 41.46% | 2014-04-01 | 2014-12-01 | 0 | 2.539 | 0.5923 | 1.228 | Local | Caltrans | Caltrans | Caltrans
04 | SHOPP | 1637U | SF | 101 | STRUCTURE REHAB AND SEISMIC RESTORATION OF TUNNELS AND VIADUCTS | 19.2876 | P3 | 2012 | 0619A | [5 empty] | 510981177.5958 | 87014090.1406 | 8957628.6329 | 39495299.7606 | 626000 | 37935161.7471 | 5483942.33 | 17.03% | 2012-08-01 | 2015-09-23 | 0 | 0 | 0.01133 | 19.2762 | Local | Local | Caltrans | Local
04 | SHOPP | 1706U | ALA | 880 | REPLACE BRIDGE | 23.1084 | SHOPP | 2006 | 0040G | [5 empty] | 144130000 | 4326000 | 4326000 | F | F | F | 35291195.12 | 3.001% | 2009-03-25 | 2014-12-01 | 0 | 0 | 0.66807 | 22.4404 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 1A290 | SON | 012 | REPLACE BRIDGE FOR SCOUR | 8.445 | SHOPP | 2012 | 0756F | [5 empty] | 13438000 | 5775000 | 2460000 | 1600000 | 315000 | 1400000 | 6042513.75 | 42.98% | 2013-06-01 | 2015-12-01 | 0 | 0.07142 | 0.3448 | 8.0288 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 1A300 | MRN | 580 | REPLACE BRIDGE RAILS | 2.3015 | SHOPP PA |  |  |  | X | X
04 | SHOPP | 1A320 | CC | 580 | BRIDGE DECK REPLACEMENT | 18.3716 | SHOPP | 2010 | 0229B |  |  |  | X |  | 17971000 | 6200000 | 800000 | 2100000 | 100000 | 3200000 | 4581763.44 | 34.5% | 2013-01-15 | 2014-02-01 | 0 | 0 | 0.31734 | 18.0542 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 1A340 | SCL | 009 | REPLACE THE DEFICIENT AND DAMAGED BRIDGE RAILING, MBGR, FENCE AND | 4.6528 | SHOPP | 2012 | 0385C | X |  |  |  |  | 1200000 | 1170000 | 450000 | 540000 | 54000 | 126000 | 0 | 97.5% | 2013-08-01 | 2016-06-24 | 2.7181 | 1.6839 | 0.01659 | 0.23428 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 1A551 | SF | 280 | REPLACE BRIDGE RAILS | 6.0905 | SHOPP | 2012 | 0268P |  | X | X |  |  | 17819000 | 5165000 | 200000 | 2035000 | 320000 | 2610000 | 834413.18 | 28.99% | 2014-04-01 | 2015-09-01 | 0 | 1.812 | 0.14891 | 4.1296 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 1A620 | SON | 012 | INST SIGNAL & RALIGN THE RTE 12 APPROACH AT THE JCT OF ST RTE 12 & | 0.90233 | SHOPP | 2010 | 0268Q | [5 empty] | 5850000 | 3027000 | 827000 | 1100000 | 300000 | 800000 | 3730945.77 | 51.74% | 2011-10-05 | 2012-12-31 | 0 | 0 | 0.44404 | 0.45829 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 1A671 | ALA | 580 | REHABILITATE BRIDGE DECK | 15.4067 | SHOPP | 2010 | 0159K | [5 empty] | 49390000 | 13605000 | 5000 | 5800000 | 100000 | 7700000 | 1916909.2258 | 27.55% | 2013-12-01 | 2016-01-15 | 0 | 0.2979 | 0.25764 | 14.8512 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 1A672 | ALA | 580 | REHABILITATE BRIDGE STRUCTURAL, STEEL PAINTING, REPAIR OF ELETRICAL | 9.3323 | SHOPP | 2012 | 0159Q | [5 empty] | 16320000 | 6055000 | 5000 | 2800000 | 250000 | 3000000 | 525007.7542 | 37.1% | 2015-06-30 | 2017-01-15 | 0 | 9.2961 | 0.03619 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 1A682 | ALA | 880 | ROADWAY REHAB. | 4.2199 | SHOPP | 2010 | 0042 |  |  |  | X |  | 22100000 | 4860000 | 10000 | 2200000 | 10000 | 2640000 | 3040865.19 | 21.99% | 2011-12-02 | 2013-10-01 | 0 | 0 | 0.1364 | 4.0835 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 1A683 | ALA | 880 | CRACK, SEAL AND HMA METERING | 2.8314 | SHOPP | 2012 | 0044Q | [5 empty] | 10000000 | 4950000 | 10000 | 2200000 | 100000 | 2640000 | 0 | 49.5% | 2015-03-15 | 2016-04-01 | 0 | 2.7778 | 0.05359 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 1A770 | SM | 280 | SEISMIC RESTORATION | 0.17277 | SHOPP | 2008 | 0733F | [5 empty] | 9333000 | 3399000 | E | 2156000 | 72000 | 1171000 | 4668351.02 | 36.42% | 2011-05-11 | 2012-10-23 | 0 | 0 | 0.03873 | 0.13404 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 1A902 | SF | 001 | WATER QUALITY IMPROVEMENTS | 0.005 | SHOPP | 2010 | 1067A | [5 empty] | 3570000 | 2499000 | 84000 | 1120000 | 35000 | 1260000 | 755202.09 | 70% | 2012-06-15 | 2012-11-15 | 0 | 0 | 0.0009 | 0.0041 | Local | Caltrans | Caltrans | Caltrans
04 | SHOPP | 1A903 | SF | 001 | CONSTRUCT DRAINAGE | 4.249 | SHOPP | 2012 | 1067B | [5 empty] | 2430000 | 1071000 | 36000 | 480000 | 15000 | 540000 | 0 | 44.07% | 2015-06-15 | 2015-11-15 | 1.8954 | 1.04 | 1.3136 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 1G020 | SM | 082 | INSTALL LEFT TURN CHANNELIZATION | 10.5716 | SHOPP | 2012 | 0686 | [5 empty] | 3605000 | 2232000 | 846000 | 810000 | 360000 | 216000 | 0 | 61.91% | 2016-09-01 | 2017-09-30 | 10.5716 | 0 | 0 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 1G070 | SCL | 009 | SHOULDER WIDENING | 4.6489 | SHOPP | 2012 | 0882 |  |  |  | X |  | 2643000 | 1302000 | E | 620000 | 32000 | 650000 | 340462.63 | 49.26% | 2013-05-15 | 2014-05-01 | 0 | 0 | 0.12535 | 4.5235 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 1G200 | ALA | 880 | RESURFACE THE EXISTING NB & SB OFF-RAMPS WITH OGAC | 0.12793 | SHOPP | 2010 | 0025 | [5 empty] | 745000 | 300000 | E | 154000 | 10000 | 136000 | 311892.21 | 40.27% | 2012-06-11 | 2013-06-28 | 0 | 0 | 0.02942 | 0.09851 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 1G240 | SON | 116 | LEFT TURN CHANNELIZATION | 2.2522 | SHOPP | 2010 | 0788 |  |  |  | X |  | 1155000 | 405000 | E | 180000 | 45000 | 180000 | 972632.15 | 35.06% | 2012-12-01 | 2013-12-01 | 0 | 0 | 0.36021 | 1.892 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 1G310 | ALA | 080 | REHABILITATE PAVEMENT | 1.006 | SHOPP | 2010 | 0054U |  |  |  | X |  | 17010000 | 2820000 | 10000 | 1000000 | 10000 | 1800000 | 2282638.27 | 16.58% | 2011-02-17 | 2013-12-15 | 0 | 0 | 0.22764 | 0.7784 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 1G420 | SON | 116 | CONSTRUCT RETAINING WALL, PLACE ROCK PROTECTION, MODIFY DRAINAGE, | 4.4232 | SHOPP | 2012 | 0816K |  |  |  | X |  | 910000 | 997000 | 314000 | 353000 | 50000 | 280000 | 600825.83 | 109.6% | 2013-09-22 | 2014-04-01 | 0 | 0.41182 | 0.13388 | 3.8775 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 1G430 | NAP | 128 | OVERLAY (DUMBARTON BRIDGE) | 1.2401 | SHOPP | 2012 | 0587H | [5 empty] | 6209000 | 2200000 | E | 1050000 | 150000 | 1000000 | 0 | 35.43% | 2017-08-02 | 2019-11-01 | 0.30667 | 0.93341 | 0 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 1G490 | VAR | VAR | STATEWIDE RELOCATE OF ARCHAELOGICAL REBURIAL LOCATIONS & CREATION OF | 1.4628 | STIP | 2012 | 2127N | [5 empty] | 575000 | 575000 | 575000 | D | D | D | 3681.52 | 100% | 2011-03-12 | 2011-11-27 | 1.4628 | 0 | 0 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 1G550 | CC | 080 | INSTALL EMBANKMENT MBGR AT HWY 80 AND HWY 4 LOCATIONS. RESURFACE PAV | 2.1626 | SHOPP | 2010 | 0026 |  |  |  | X |  | 1340000 | 730000 | 280000 | 233000 | 17000 | 200000 | 667586.75 | 54.48% | 2012-11-16 | 2014-01-15 | 0 | 0 | 0.08968 | 2.0729 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 1G560 | ALA | 880 | REMOVE EXISTING MEDIAN DOUBLE METAL BEAM BARRIER AND INSTALL TYPE 60A | 4.638 | SHOPP | 2010 | 0066 |  |  |  | X |  | 3174000 | 600000 | 150000 | 225000 | 20000 | 205000 | 1183216.15 | 18.9% | 2012-12-12 | 2013-12-01 | 0 | 0 | 0.08587 | 4.5521 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 1G830 | SM | 280 | UPGRADE TO STANDARD THE EXISTING METAL BEAM GUARD RAIL CONNECTIONS | 2.346 | SHOPP | 2012 | 0730B | X | X | X |  |  | 2266000 | 2078000 | 297000 | 594000 | 297000 | 890000 | 0 | 91.7% | 2014-10-15 | 2015-04-01 | 0.00352 | 2.2828 | 0.05974 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 1G850 | SM | 092 | INSTALL OR MODIFY METAL BEAM GUARD RAILS | 2.1416 | SHOPP | 2012 | 0730G |  | X | X |  |  | 1270000 | 847000 | 121000 | 242000 | 121000 | 363000 | 0 | 66.69% | 2014-07-01 | 2014-11-01 | 0 | 2.062 | 0.07964 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 1SS02 | ALA | 013 | INSTALL TIEBACK RETAINING WALL | 2.9187 | SHOPP | 2012 | 0143A |  | X | X |  |  | 3030000 | 1642000 | 609000 | 533000 | 50000 | 450000 | 286209.09 | 54.19% | 2014-10-01 | 2015-08-25 | 0 | 2.4858 | 0.43287 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 1SS03 | ALA | 580 | CONSTRUCT SOLDIER PILE WALL | 5.4202 | SHOPP | 2012 | 0105A | X |  |  |  |  | 10650000 | 1667000 | 765000 | 669000 | 50000 | 183000 | 142992.14 | 15.65% | 2014-09-29 | 2015-09-28 | 1.5523 | 3.5245 | 0.34347 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 1SS04 | ALA | 580 | INSTALL TIEBACK RETAINING WALL | 3.3186 | SHOPP | 2012 | 0123A | X | X | X |  |  | 1710000 | 1950000 | 650000 | 700000 | 50000 | 550000 | 245161.18 | 114% | 2014-01-23 | 2015-07-24 | 0.02858 | 3.1084 | 0.18158 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 1SS05 | ALA | 580 | CONSTRUCT SOLDIER BEAM TIEBACK WALL | 3.251 | SHOPP | 2012 | 0123B | X | X | X |  |  | 3450000 | 2112000 | 862000 | 600000 | 150000 | 500000 | 234570.85 | 61.22% | 2014-10-21 | 2015-10-20 | 0.05583 | 2.8835 | 0.3116 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 1SS22 | SON | 128 | CONSTRUCT LAUNCHED SOIL NAIL WALL | 1.7189 | SHOPP | 2012 | 0824B |  | X | X |  |  | 560000 | 611000 | 228000 | 260000 | 40000 | 83000 | 171219.5 | 109.1% | 2014-10-02 | 2015-10-13 | 0 | 1.4347 | 0.28422 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 1SS37 | SON | 121 | CONSTRUCT CIDH PILE WALL | 1.1004 | SHOPP | 2012 | 0815C | X |  |  |  |  | 1125000 | 925000 | 200000 | 300000 | 25000 | 400000 | 0 | 82.22% | 2015-02-11 | 2015-12-01 | 0.18305 | 0.91736 | 0 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 1SS43 | ALA | 880 | INSTALL PRESSURE GROUTING | 2.6186 | SHOPP | 2012 | 0070A | X |  | X |  |  | 3075000 | 2483000 | 762000 | 762000 | 64000 | 895000 | 0 | 80.75% | 2014-10-01 | 2015-10-19 | 0.01017 | 2.575 | 0.03348 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 1SS46 | CC | 680 | INSTALL COMPACTION GROUTING | 0.86604 | SHOPP | 2012 | 0294D | X |  |  |  |  | 765000 | 913000 | 333000 | 333000 | 27000 | 220000 | 0 | 119.3% | 2015-08-03 | 2016-09-01 | 0.32004 | 0.546 | 0 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 1SS47 | CC | 680 | RECONSTRUCT ROADWAY AND INSTALL ROCK SLOPE PROTECTION | 0.89854 | SHOPP | 2012 | 0277Q | X |  |  |  |  | 575000 | 677000 | 246000 | 246000 | 20000 | 165000 | 0 | 117.7% | 2015-08-03 | 2016-09-01 | 0.34564 | 0.5529 | 0 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 1SS57 | SOL | 080 | REPAIR DRAINAGE SYSTEM | 1.0554 | SHOPP | 2012 | 5303Q | X |  |  |  |  | 422000 | 509000 | 197000 | 132000 | 20000 | 160000 | 0 | 120.6% | 2015-05-11 | 2016-12-01 | 0.56752 | 0.48146 | 0.00639 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 1SS58 | MRN | 001 | PROVIDE DRAINAGE SYSTEM AND INSTALL ROCK SLOPE PROTECTION | 1.3076 | SHOPP | 2012 | 0312T | X |  |  |  |  | 540000 | 746000 | 200000 | 300000 | 50000 | 196000 | 0 | 138.1% | 2015-09-01 | 2016-10-15 | 0.49433 | 0.80845 | 0.00483 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 1SS59 | MRN | 580 | RE-GRADE SLOPE AND REPAIR DOWN DRAIN | 1.8214 | SHOPP | 2012 | 0327Q | X |  |  |  |  | 986000 | 870000 | 150000 | 427000 | 50000 | 243000 | 0 | 88.24% | 2015-09-01 | 2016-07-04 | 0.81526 | 0.95321 | 0.0529 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 2708U | SM | 092 | REPLACEMENT HIGHWAY PLANTING | 3.7043 | SHOPP | 2006 | 0681D | [5 empty] | 3986859.1585 | 1749999.9999 | 644999.9999 | 503000 | 70000 | 532000 | 235675.949 | 43.89% | 2012-06-01 | 2015-09-01 | 0 | 0 | 0.03535 | 3.6689 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 2937U | MRN | 101 | WIDENING OFF RAMP | 0.02815 | SHOPP | 2006 | 0338E | [5 empty] | 4089000 | 997000 | 997000 | F | F | F | 5523774.92 | 24.38% | 2007-02-15 | 2009-09-01 | 0 | 0 | 0.01099 | 0.01716 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 2A040 | MRN | 101 | REPLACE BRIDGE RAILS | 1.5286 | SHOPP PA |  |  |  | X | X
04 | SHOPP | 2A110 | NAP | 121 | REPLACE BRIDGE (SCOUR) | 10.4888 | SHOPP | 2012 | 0384G | [5 empty] | 6780000 | 4100000 | 1700000 | 1100000 | 200000 | 1100000 | 3128668.94 | 60.47% | 2013-08-20 | 2015-08-01 | 0 | 0.34377 | 0.09551 | 10.0495 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 2A140 | SF | 101 | REPLACE DRAINAGE SYSTEMS | 3.9637 | SHOPP | 2008 | 0269K |  |  |  | X |  | 10797000 | 5742000 | 122000 | 2713000 | 198000 | 2709000 | 4815841.01 | 53.18% | 2010-10-26 | 2013-08-31 | 0 | 0 | 0.20188 | 3.7618 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 2A250 | SCL | 152 | IMPROVE SIGHT DISTANCE, UPGRADE SHOULDERS, MINOR REALIGNMENT, TURN- | 11.9254 | SHOPP | 2012 | 0483J | [5 empty] | 26019000 | 11122000 | 3822000 | 2980000 | 850000 | 3470000 | 7574584.34 | 42.75% | 2013-09-24 | 2015-11-17 | 0 | 1.6503 | 0.60433 | 9.6707 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 2A260 | SCL | 152 | NEAR GILROY, AT FERGUSON ROAD, REA LIGN AND SIGNALIZE INTERSECTION | 3.7973 | SHOPP | 2010 | 0483K |  |  |  | X |  | 4900000 | 2876000 | 1024000 | 868000 | 300000 | 684000 | 3439897.72 | 58.69% | 2012-03-14 | 2013-12-08 | 0 | 0 | 0.32454 | 3.4727 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 2A320 | NAP | 121 | BRIDGE REPLACEMENT (SCOUR) | 10.6557 | SHOPP | 2012 | 0380L |  | X | X |  |  | 9700000 | 6275000 | 1800000 | 2100000 | 275000 | 2100000 | 1888656.4 | 64.69% | 2014-10-01 | 2018-12-04 | 0 | 8.6754 | 1.9802 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 2A330 | ALA | 084 | IMPROVE SIGHT DISTANCE, UPGRADE SHOULDERS AND PROVIDE CURVE CORRECT | 8.2934 | SHOPP | 2012 | 0076A | X |  |  |  |  | 36060000 | 17455000 | 8622000 | 3358000 | 850000 | 4625000 | 9068580.32 | 48.41% | 2016-08-01 | 2018-12-01 | 0.63891 | 6.6544 | 1 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 2A430 | SCL | 009 | IMPROVE SIGHT DISTANCE, UPGRADE SHOULDERS, AND PROVIDE MINOR | 9.6758 | SHOPP | 2012 | 0385F | [5 empty] | 8977000 | 4900000 | 2000000 | 1500000 | 200000 | 1200000 | 3361109.07 | 54.58% | 2013-08-15 | 2014-12-31 | 0 | 0.40894 | 0.92016 | 8.3467 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 2A440 | SCL | 152 | IMPROVE SIGHT DISTANCE, UPGRADE SHOULDERS AND PROVIDE | 12.6784 | SHOPP | 2010 | 0485K |  |  |  | X |  | 16343000 | 6429000 | 1980000 | 2000000 | 341000 | 2108000 | 5806216.52 | 39.34% | 2013-02-01 | 2014-06-05 | 0 | 0.3675 | 0.37819 | 11.9328 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 2A441 | SCL | 152 | IMPROVE SIGHT DISTANCE, UPGRADE SHOULDERS AND PROVIDE | 2.4589 | SHOPP | 2012 | 0485U | [5 empty] | 950000 | 445000 | H | 200000 | 50000 | 195000 | 0 | 46.84% | 2015-04-09 | 2017-01-07 | 0.84666 | 1.0989 | 0.51339 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 2A442 | SCL | 152 | ENVIRONMENTAL SPECIES MITIGATION | 1.162 | SHOPP | 2012 | 0485Q | X |  |  |  |  | 3349000 | 600000 | H | 350000 | 50000 | 200000 | 0 | 17.92% | 2015-04-09 | 2017-01-07 | 0.59769 | 0.0501 | 0.51425 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 2A460 | MRN | 037 | INSTALL DOUBLE THRIE BEAM BARRIER IN THE MEDIAN | 0.00713 | SHOPP | 2006 | 0768C | [5 empty] | 1405000 | 412000 | 412000 | F | F | F | 808648.78 | 29.32% | 2008-01-18 | 2008-06-15 | 0 | 0 | 0.00157 | 0.00556 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 2A490 | SF | 280 | BRIDGE REHABILITATION REPAIR FOR DRAINAGE & PONDING | 7.7277 | SHOPP | 2012 | 0608K |  | X | X |  |  | 9415000 | 5049000 | 605000 | 2247000 | 465000 | 1732000 | 530116.68 | 53.63% | 2014-12-01 | 2016-04-01 | 0 | 4.9385 | 2.7892 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 2A542 | SM | 280 | UPGRADE VISTA POINTS | 0.12135 | SHOPP | 2008 | 0387F | [5 empty] | 1255000 | 1456000 | 250000 | 800000 | 6000 | 400000 | 1577640.5723 | 116% | 2010-08-02 | 2012-04-18 | 0 | 0 | 0.02496 | 0.09639 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 2A543 | SM | 280 | CONSTRUCT RETAINING WALL AND ADA COMPLIANT SIDEWALK | 0.00777 | SHOPP | 2008 | 0387G | [5 empty] | 1301000 | 581000 | 80000 | 400000 | 1000 | 100000 | 804856.6915 | 44.66% | 2010-08-06 | 2011-09-30 | 0 | 0 | 0.00777 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 2A620 | SOL | 012 | INSTALL LEFT TURN POCKETS, FROM AZAVEDO RD TO LIBERTY ISLAND RD | 8.0028 | SHOPP | 2012 | 8085A | [5 empty] | 11088000 | 5733000 | 2720000 | 1370000 | 273000 | 1370000 | 4735319.01 | 51.7% | 2013-06-07 | 2015-10-01 | 0 | 0.29026 | 1.3273 | 6.3853 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 2A790 | SM | 101 | INSTALL NEW RAMP METERING AND UP GRADE PARTIALLY INSTALLED RM | 1.0424 | SHOPP | 2010 | 0618F |  |  |  | X |  | 11500000 | 2903000 | 454000 | 907000 | 181000 | 1361000 | 4114262.42 | 25.24% | 2011-11-29 | 2013-08-15 | 0 | 0 | 0.14844 | 0.89392 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 2A920 | SON | 116 | INSTALL TRAFFIC SIGNALS, WIDEN SHOULDER AND EXTEND LEFT TURN | 0.08567 | SHOPP | 2008 | 0813B | [5 empty] | 1269000 | 1202000 | 300000 | 430000 | 42000 | 430000 | 1749671.53 | 94.72% | 2011-02-07 | 2011-12-29 | 0 | 0 | 0.01784 | 0.06783 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 2G410 | ALA | 680 | REPLACE MBGR WITH CONCRETE BARRIER | 0.87746 | SHOPP | 2012 | 0272K | [5 empty] | 1075000 | 373000 | 75000 | 117000 | 32000 | 149000 | 0 | 34.7% | 2015-05-01 | 2015-12-01 | 0 | 0.87746 | 0 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 2G440 | CC | 080 | UPGRADE TYPE W BEAM OR SINGLE THRIE BEAM (STB) TRANSITION RAILING | 3.6463 | SHOPP | 2012 | 0026D | X |  |  |  |  | 2206000 | 1448000 | 207000 | 414000 | 207000 | 620000 | 0 | 65.64% | 2015-11-02 | 2017-02-01 | 0.89234 | 2.7268 | 0.0272 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 2G450 | CC | 680 | UPGRADE TO TYPE W BEAM (WB) OR GLE SINGLE THRIE BEAM (STB) TRANSITION | 2.083 | SHOPP | 2012 | 0277E | X |  |  |  |  | 2214000 | 1178000 | 196000 | 491000 | 20000 | 471000 | 0 | 53.21% | 2015-11-02 | 2017-02-01 | 0.47561 | 1.5847 | 0.02265 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 2G500 | ALA | 013 | INSTAL W BEAM (WB) OR SINGLE THRIE BEAM (STB) TRANSITION RAILING AT | 3.72 | SHOPP | 2012 | 0107G | X |  |  |  |  | 4682000 | 1155000 | 231000 | 363000 | 99000 | 462000 | 0 | 24.67% | 2015-05-01 | 2016-06-01 | 0.85 | 2.87 | 0 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 2G520 | ALA | 580 | UPGRADE TYPE W BEAM (WB) OR SINGLE THRIE BEAM (STB) TRANSITION RAILING | 4.2873 | SHOPP | 2012 | 0107H | X |  |  |  |  | 6991000 | 4583000 | 655000 | 1309000 | 655000 | 1964000 | 0 | 65.56% | - - | 2017-10-01 | 1.2545 | 3.0315 | 0.00124 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 2G830 | ALA | 013 | REPAIR SLOPE SLIDE WITH SOLDIER BEAM TIE BACK RETAINING WALL | 3.5171 | SHOPP | 2012 | 0144R | X |  |  |  |  | 1340000 | 980000 | 50000 | 480000 | 80000 | 370000 | 309367.92 | 73.13% | 2015-12-15 | 2016-09-01 | 1.2918 | 2.095 | 0.13029 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 2G850 | ALA | 580 | INSTALL RAMMED AGGREGATE PIERS (RAP) | 2.3316 | SHOPP | 2012 | 0102R | X | X |  |  |  | 6100120 | 2055000 | 750000 | 575000 | 80000 | 650000 | 204699.95 | 33.69% | 2014-09-29 | 2015-09-28 | 0.9179 | 1.3279 | 0.08579 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 2G860 | ALA | 580 | REBUILD EMBANKMENT | 1.5331 | SHOPP | 2012 | 0133A |  | X | X |  |  | 2000010 | 1550000 | 300000 | 700000 | 50000 | 500000 | 109348.06 | 77.5% | 2014-09-29 | 2015-09-28 | 0 | 1.4016 | 0.1315 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 2G870 | MRN | 001 | PLACE ROCK SLOPE PROTECTION | 2.524 | SHOPP | 2012 | 0312R |  | X | X |  |  | 515000 | 405000 | 100000 | 150000 | 20000 | 135000 | 74038.74 | 78.64% | 2014-10-01 | 2015-12-31 | 0 | 2.1713 | 0.35269 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 2G890 | MRN | 001 | CONSTRUCT SOLDIER PILE WALL | 3.3785 | SHOPP | 2012 | 0209R | X |  |  |  |  | 8087000 | 4700000 | 550000 | 1800000 | 400000 | 1950000 | 0 | 58.12% | 2016-04-02 | 2016-10-31 | 0.69831 | 2.2301 | 0.45012 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 2G940 | NAP | 128 | CONSTRUCT ROADWAY RETAINING SYSTEM | 2.5663 | SHOPP | 2012 | 0522R | X |  |  |  |  | 1022000 | 860000 | 270000 | 270000 | 80000 | 240000 | 48158.39 | 84.15% | 2016-01-31 | 2020-11-02 | 1.7716 | 0.74715 | 0.04753 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 2G950 | NAP | 128 | CONSTRUCT ROADWAY RETAINING SYSTEM | 4.7632 | SHOPP | 2012 | 0640B | [5 empty] | 1666000 | 790000 | 190000 | 190000 | 80000 | 330000 | 0 | 47.42% | 2015-08-05 | 2019-04-30 | 1e-05 | 4.4388 | 0.32441 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 2G960 | SCL | 009 | CONSTRUCT SOLDIER PILE WALL | 6.4699 | SHOPP | 2012 | 0387R | X | X |  |  |  | 2250000 | 1510000 | 168000 | 672000 | 70000 | 600000 | 0 | 67.11% | 2014-08-16 | 2015-09-06 | 1.5461 | 3.4323 | 0.73006 | 0.76142 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 2G990 | SCL | 130 | CONSTRUCT SEGMENTED PILE WALL | 4.402 | SHOPP | 2012 | 0500C | X | X | X |  |  | 1727000 | 1244000 | 138000 | 550000 | 70000 | 486000 | 0 | 72.03% | 2014-06-09 | 2015-06-20 | 0.98581 | 2.746 | 0.67024 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 2S370 | NAP | 128 | STORM DAMAGE REPAIR | 0.13209 | SHOPP | 2008 | 0383D | [5 empty] | 1570000 | 905000 | E | 625000 | 80000 | 200000 | 1290296.73 | 57.64% | 2009-09-30 | 2012-01-27 | 0 | 0 | 0.01575 | 0.11634 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 2S600 | SON | 001 | MITIGATION AND EROSION CONTROL | 0.09599 | SHOPP | 2008 | 0748K | [5 empty] | 1350000 | 352000 | 352000 | D | D | D | 152412.57 | 26.07% | - - | - - | 0 | 0 | 0.09599 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 2S620 | SM | 001 | ROCK SLOPE PROTECTION | 0.0322 | SHOPP | 2008 | 0630C | [5 empty] | 479000 | 650000 | 130000 | 357000 | 33000 | 130000 | 1459281.04 | 135.7% | 2009-06-08 | 2012-02-01 | 0 | 0 | 0.0322 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 2S940 | SON | 128 | REPLACE STORM DAMAGED BRIDGE | 0.16158 | SHOPP | 2004 | 0823D | [5 empty] | 24500000 | 7400000 | 7400000 | F | F | F | 2220874.08 | 30.2% | 2006-04-11 | 2007-03-12 | 0 | 0 | 0.16158 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 2S941 | SON | 128 | RESTORE HIGHWAY PLANTING | 0.43105 | SHOPP | 2008 | 0829H | [5 empty] | 1221000 | 552000 | N | 300000 | 2000 | 250000 | 517799.22 | 45.21% | 2010-03-25 | 2015-07-28 | 0 | 0 | 0.00374 | 0.42731 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 3A090 | ALA | 024 | REPLACE UNDERGROUND STORAGE TANKS | 0.55075 | SHOPP | 2010 | 0056H | [5 empty] | 4655000 | 2080000 | 10000 | 1100000 | 50000 | 920000 | 2606888.2 | 44.68% | 2011-07-15 | 2013-01-02 | 0 | 0 | 0.08322 | 0.46753 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 3A300 | SOL | 080 | REPLACE APPROACH SLAB | 0.05265 | SHOPP | 2008 | 5401A | [5 empty] | 16721000 | 2800000 | B | 750000 | 50000 | 2000000 | 1271879.56 | 16.75% | 2010-07-06 | 2010-12-01 | 0 | 0 | 0.00344 | 0.04921 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 3A330 | SON | 012 | INSTALL TRAFFIC SIGNALS AND WIDEN ROADWAY AT THE INTERSECTION | 2.705 | SHOPP | 2010 | 0762Y |  |  |  | X |  | 1344000 | 2253000 | 303000 | 1250000 | 250000 | 450000 | 2167826.07 | 167.6% | 2012-12-14 | 2013-12-30 | 0 | 0 | 1.0228 | 1.6822 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 3A400 | SCL | 152 | CONSTRUCT LEFT TURN POCKET | 0.44568 | SHOPP | 2008 | 0486J | [5 empty] | 2275000 | 2467000 | 297000 | 1470000 | 300000 | 400000 | 2358449.17 | 108.4% | 2011-04-07 | 2011-09-02 | 0 | 0.01534 | 0.43034 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 3A530 | ALA | 580 | REPAIR PAVEMENT | 0.17224 | SHOPP | 2010 | 0119H | [5 empty] | 1979000 | 540000 | 4000 | 328000 | 4000 | 204000 | 1031367.99 | 27.29% | 2011-07-22 | 2012-02-03 | 0 | 0 | 0.05014 | 0.1221 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 3A773 | ALA | 080 | CONST. TRAFFIC MANAGEMENT SYSTEMS | 0.24403 | PARTNERSHIP
04 | SHOPP | 3A820 | MRN | 001 | RECONSTRUCT SIDEWALK AND WALKWAY RESURFACE ACCESSIBLE PARKING AREAS | 0.07986 | SHOPP | 2008 | 0338H | [5 empty] | 505000 | 983000 | 216000 | 498000 | 20000 | 249000 | 954794.34 | 194.7% | 2010-05-03 | 2011-05-13 | 0 | 0 | 0.01016 | 0.0697 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 3A870 | CC | 680 | BRIDGE REHABILITATION | 6.9423 | SHOPP | 2012 | 0303B | [5 empty] | 15370000 | 6000000 | 1300000 | 2250000 | 50000 | 2400000 | 4052686.21 | 39.04% | 2013-11-01 | 2014-12-31 | 0 | 0.65459 | 0.51335 | 5.7743 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 3A950 | ALA | 680 | REPLACE ROOF AT MISSION GRADE STATION | 0.00506 | SHOPP | 2008 | 0165H | [5 empty] | 469000 | 257000 | 67000 | 83000 | 17000 | 90000 | 346261.9 | 54.8% | 2010-11-24 | 2011-12-01 | 0 | 0 | 0.00506 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 3A960 | ALA | 580 | REPAIR AND EXTEND PAVEMENT | 0.20654 | SHOPP | 2010 | 0111D | [5 empty] | 1810000 | 720000 | 25000 | 318000 | 17000 | 360000 | 339734.1 | 39.78% | 2012-06-07 | 2013-06-03 | 0 | 0 | 0.05499 | 0.15155 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 3A980 | SCL | 101 | BRIDGE RAIL REPLACEMENT/UPGRADE | 0.04736 | SHOPP | 2010 | 0485M | [5 empty] | 1630000 | 437000 | 128000 | 128000 | 10000 | 171000 | 1270657.77 | 26.81% | 2011-07-28 | 2012-05-08 | 0 | 0 | 0.00833 | 0.03903 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 3A990 | SON | 116 | RECONSTRUCT CURB RAMPS | 0.01789 | SHOPP | 2008 | 0816B | [5 empty] | 923000 | 1065000 | 520000 | 250000 | 45000 | 250000 | 1307080.99 | 115.4% | 2010-08-12 | 2011-08-11 | 0 | 0 | 0.01789 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 3G020 | SM | 035 | CONSTRUCT SOLDIER PILE WALL | 3.7061 | SHOPP | 2012 | 0636R |  | X | X |  |  | 1163000 | 812000 | 180000 | 390000 | 25000 | 217000 | 63538.9 | 69.82% | 2014-09-01 | 2014-10-01 | 0.28194 | 3.3216 | 0.10264 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 3G060 | SOL | 680 | CONSTRUCT RAMMED AGGREGATE PIERS | 3.5152 | SHOPP | 2012 | 0384R | X |  |  |  |  | 1199000 | 1023000 | 300000 | 370000 | 50000 | 303000 | 0 | 85.32% | 2014-12-03 | 2016-07-09 | 1.0857 | 2.1196 | 0.31 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 3G070 | SON | 001 | PLACE ROCK SLOPE PROTECTION | 3.3015 | SHOPP | 2012 | 0330H |  | X | X |  |  | 540000 | 476000 | 120000 | 140000 | 60000 | 156000 | 26383.04 | 88.15% | 2014-11-06 | 2015-06-11 | 0 | 2.4617 | 0.83981 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 3G080 | SON | 001 | CONSTRUCT SOIL NAIL WALLS | 8.422 | SHOPP | 2012 | 0753R | X | X | X |  |  | 7340000 | 3600000 | 1000000 | 1000000 | 100000 | 1500000 | 34534.64 | 49.05% | 2014-10-02 | 2015-12-01 | 0.31324 | 7.7359 | 0.37283 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 3G090 | SON | 001 | PLACE ROCK SLOPE PROTECTION | 3.1818 | SHOPP | 2012 | 0753Q | X | X | X |  |  | 830000 | 661000 | 200000 | 200000 | 75000 | 186000 | 24825.74 | 79.64% | 2014-10-02 | 2015-12-01 | 0.16587 | 2.6895 | 0.32637 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 3G110 | SON | 116 | PLACE ROCK SLOPE PROTECTION | 3.1277 | SHOPP | 2012 | 0819Q |  | X | X |  |  | 720000 | 560000 | 150000 | 202000 | 50000 | 158000 | 9365.26 | 77.78% | 2014-11-06 | 2015-06-11 | 0 | 2.6204 | 0.50728 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 3G120 | SON | 128 | CONSTRUCT CIDH PILE WALL AND REPLACE CULVERT | 3.0925 | SHOPP | 2012 | 8315T |  | X | X |  |  | 1530000 | 1317000 | 350000 | 525000 | 70000 | 372000 | 63419.8 | 86.08% | 2014-11-26 | 2015-11-11 | 0 | 3.0098 | 0.08273 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 3G160 | CC | 024 | REPAIR SLOPE SLIDE BY TIE BACK RETAINING WALL | 4.417 | SHOPP | 2012 | 0225H | X | X | X |  |  | 5035000 | 3556000 | 125000 | 1900000 | 100000 | 1431000 | 165621.5 | 70.63% | 2014-11-15 | 2016-01-01 | 0.00236 | 4.1647 | 0.24989 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 3G170 | SF | 101 | RECONSTRUCT SLOPE WITH ROCK SLOPE PROTECTION | 1.9535 | SHOPP | 2012 | 0600H |  | X | X |  |  | 402000 | 581000 | 80000 | 274000 | 55000 | 172000 | 0 | 144.5% | 2014-11-15 | 2015-05-15 | 0 | 1.6355 | 0.31801 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 3G590 | ALA | 580 | ROADWAY REHABILITATION (2R) | 4.1616 | SHOPP | 2012 | 8315V | X |  |  |  |  | 58531000 | 15932000 | 538000 | 7697000 | 179000 | 7518000 | 0 | 27.22% | 2016-05-02 | 2018-08-01 | 2.1605 | 2 | 0.00113 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 3G620 | SF | 101 | BRIDGE REHABILITATION | 2.811 | SHOPP | 2012 | 0587D | X |  |  |  |  | 18172000 | 5320000 | 330000 | 2350000 | 20000 | 2620000 | 0 | 29.28% | 2016-04-01 | 2018-04-01 | 0.06829 | 2.5598 | 0.1829 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 3G640 | NAP | 029 | SCOUR REPLACE BRIDGE | 4.551 | SHOPP | 2012 | 0587G | X |  |  |  |  | 8244000 | 3570000 | 1090000 | 980000 | 400000 | 1100000 | 0 | 43.3% | 2016-05-01 | 2017-12-01 | 3.4237 | 1.1273 | 0 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 3G650 | SOL | 680 | OVERLAY EXISTING PAVEMENT | 2.3711 | SHOPP | 2012 | 8315P | X |  |  |  |  | 11088000 | 5865000 | 1360000 | 2040000 | 425000 | 2040000 | 0 | 52.9% | 2015-09-09 | 2018-07-09 | 0.89724 | 1 | 0.4739 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 3G670 | SM | 101 | CONSTRUCT ROADSIDE PAVEMENT | 1.3558 | SHOPP | 2012 | 8315R | [5 empty] | 1555000 | 510000 | 110000 | 150000 | 40000 | 210000 | 0 | 32.8% | 2016-11-01 | 2017-11-30 | 0.01308 | 1.3427 | 0 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 3G680 | SM | 101 | CONSTRUCT ROADSIDE PAVEMENT, MVP'S AND ACCESS GATES | 3.1363 | SHOPP | 2012 | 8315Q | X |  |  |  |  | 1505000 | 500000 | 100000 | 150000 | 40000 | 210000 | 0 | 33.22% | 2015-09-01 | 2016-09-01 | 0.58748 | 2.5277 | 0.02111 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 3G700 | SF | 101 | ROADSIDE SAFETY IMPROVEMENTS | 4.3518 | SHOPP | 2012 | 8315U | X |  |  |  |  | 2005000 | 680000 | 140000 | 200000 | 40000 | 300000 | 0 | 33.92% | 2015-04-01 | 2016-05-01 | 0.40122 | 3.9208 | 0.02977 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 3G710 | ALA | 580 | ROADSIDE SAFETY IMPROVEMENTS | 4.2503 | SHOPP | 2012 | 8315W | X |  |  |  |  | 2205000 | 700000 | 150000 | 220000 | 30000 | 300000 | 0 | 31.75% | 2015-04-01 | 2016-04-01 | 0.37724 | 3.8435 | 0.02949 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 3G720 | SON | 101 | ROADSIDE SAFETY IMPROVEMENTS | 1.9937 | SHOPP | 2012 | 8315S | [5 empty] | 1485000 | 517000 | 100000 | 150000 | 44000 | 223000 | 0 | 34.81% | 2016-02-01 | 2017-04-01 | 1.9937 | 0 | 0 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 3G740 | SON | 001 | REPLACE CULVERT | 0.15892 | SHOPP | 2012 | 0755Q | [5 empty] | 1755000 | 520000 | N | 150000 | 20000 | 350000 | 0 | 29.63% | 2013-08-18 | 2014-12-01 | 0 | 0.0558 | 0 | 0.10312 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 3G750 | SM | 092 | CONSTRUCT RSP AND INSTALL DRAINAGE | 1.4478 | SHOPP | 2012 | 0653Q |  | X | X |  |  | 321000 | 590000 | 193000 | 207000 | 100000 | 90000 | 116874.56 | 183.8% | 2014-12-19 | 2015-12-18 | 0 | 1.1414 | 0.30636 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 3G760 | NAP | 128 | INSTALL SLOPE INDICATORS,INSTALL NEW HORIZONTAL DRAINS AND CLEAN | 2.0171 | SHOPP | 2012 | 0829Q |  | X | X |  |  | 655000 | 750000 | 250000 | 250000 | 50000 | 200000 | 50777.49 | 114.5% | 2014-12-09 | 2015-12-22 | 0 | 1.7265 | 0.29059 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 3S562 | MRN | 001 | REBUILD SLOPE, INSTALL ROCK SLOPE PROTECTION, RECONNECT DOWNDRAIN, | 0.05865 | SHOPP | 2008 | 0713H | [5 empty] | 904000 | 350000 | E | 150000 | 50000 | 150000 | 752443.4751 | 38.72% | 2010-07-15 | 2011-01-06 | 0 | 0 | 0 | 0.05865 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 3S563 | MRN | 001 | INSTALL ROCK SLOPE PROTECTION. | 0.16556 | SHOPP | 2008 | 0713J | [5 empty] | 902000 | 550000 | E | 300000 | 50000 | 200000 | 635104.8898 | 60.98% | 2008-12-11 | 2009-02-11 | 0 | 0 | 0.16556 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 3S570 | MRN | 001 | REPLACE CULVERT AND INSTALL ROCK SLOPE PROTECTION | 2.2713 | SHOPP | 2012 | 0321B | [5 empty] | 1090000 | 1730000 | 400000 | 1000000 | 100000 | 230000 | 1123299.64 | 158.7% | 2012-11-02 | 2014-07-01 | 0 | 0.0011 | 0.00681 | 2.2633 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 3S580 | MRN | 037 | TRAFFIC CONROL, DEWATERING, CLEANUP REBUILD LEVEE UNDER THE BRIDGE | 2.2777 | SHOPP | 2010 | 0768D |  |  |  | X |  | 1298000 | 1010000 | 300000 | 400000 | 10000 | 300000 | 949722.79 | 77.81% | 2011-12-21 | 2014-01-02 | 0 | 0 | 0.11893 | 2.1587 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 3S620 | SCL | 009 | EROSION CONTROL, DRAINAGE, CONSTRUCT V-DITCH | 0.40003 | SHOPP | 2010 | 0385K | [5 empty] | 1073000 | 1450000 | E | 1100000 | 150000 | 200000 | 1632683.37 | 135.1% | 2011-10-06 | 2012-11-02 | 0 | 0 | 0.18103 | 0.219 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 3S752 | SON | 001 | REPLACE CULVERT AND ROCK SLOPE PROTECTION | 4.246 | SHOPP | 2012 | 0753L |  |  |  | X |  | 474000 | 1600000 | E | 1300000 | 50000 | 250000 | 1370110.61 | 337.6% | 2013-05-01 | 2013-12-01 | 0 | 1.4166 | 0.20227 | 2.6271 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 3S830 | SCL | 017 | CONSTRUCT HEADWALL AND SOIL WALL, DRAINAGE SYSTEM | 3.1929 | SHOPP | 2012 | 0392B |  |  |  | X |  | 2023000 | 340000 | E | 132000 | 10000 | 198000 | 1355596.87 | 16.81% | 2013-05-13 | 2013-12-13 | 0 | 0 | 0.16188 | 3.0311 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 3S900 | MRN | 001 | CONSTRUCT TIE-BACK WALL | 1.7204 | SHOPP | 2012 | 0713F | X |  |  |  |  | 6085000 | 2850000 | E | 1700000 | 150000 | 1000000 | 1391523.66 | 46.84% | 2016-05-01 | 2016-10-08 | 0.14233 | 1.2748 | 0.30325 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 3S910 | MRN | 001 | CONSTRUCT TIE-BACK WALL | 2.0304 | SHOPP | 2012 | 0713G | [5 empty] | 6331000 | 2836000 | 168000 | 1518000 | 150000 | 1000000 | 1063666.73 | 44.8% | 2016-05-02 | 2016-10-31 | 0 | 1.539 | 0.4914 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 4442A | NAP | 121 | PERFORM HIGHWAY PLANTING | 4.5751 | SHOPP | 2010 | 0380R | [5 empty] | 925000 | 680000 | 18000 | 310000 | 80000 | 272000 | 819863.63 | 73.51% | 2011-09-30 | 2015-06-30 | 0 | 0 | 0.39719 | 4.178 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 4470U | CC | 680 | REHABILITATE ROADWAY WITH CONCRETE AND HOT MIX ASPHALT | 0.59038 | SHOPP | 2008 | 0277C | [5 empty] | 72250000 | 26250000 | 6000000 | 7500000 | 1500000 | 11250000 | 16883787.72 | 36.33% | 2010-11-18 | 2012-10-15 | 0 | 0 | 0.10472 | 0.48566 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 4A000 | MRN | 101 | BRIDGE RAIL REPLACEMENT AT THREE LOCATIONS | 2.4459 | SHOPP | 2012 | 0355A | X |  |  |  |  | 1790000 | 990000 | 360000 | 270000 | 90000 | 270000 | 0 | 55.31% | 2015-07-01 | 2016-07-01 | 0.58208 | 1.7507 | 0.11312 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 4A07U | ALA | 580 | CONSTR. TRUCK CLIMBING LANE, REHAB. PAVEMENT, CONSTR. RETAINING WALLS | 16.8912 | SHOPP | 2010 | 0104 | [5 empty] | 76190000 | 17307000 | 2713000 | 5204000 | 15000 | 9375000 | 7987096.32 | 22.72% | 2012-06-18 | 2015-08-01 | 0 | 0 | 0 | 16.8912 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 4A090 | NAP | 029 | REPLACEMENT OF TROUTDAL CREEK BRIDGE ON A NEW ALLIGNMENT | 3.793 | SHOPP | 2012 | 0382D |  | X | X |  |  | 17000000 | 4475000 | 1300000 | 1275000 | 370000 | 1530000 | 1005506.47 | 26.32% | 2014-10-30 | 2016-04-30 | 0 | 3.793 | 0 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 4A250 | SOL | 080 | INSTALL METAL BEAM GUARDRAIL | 1.909 | SHOPP | 2010 | 0263L |  |  |  | X |  | 5425000 | 1550000 | 420000 | 510000 | 20000 | 600000 | 1194926.19 | 28.57% | 2013-01-11 | 2013-11-01 | 0 | 0 | 0.00241 | 1.9066 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 4A260 | ALA | 580 | INSTALL METAL BEAM GUARDRAIL | 2.765 | SHOPP | 2012 | 0107F | [5 empty] | 4565000 | 1320000 | 450000 | 330000 | 20000 | 520000 | 1038698.24 | 28.92% | 2013-05-21 | 2014-12-30 | 0 | 0.21295 | 0.0657 | 2.4864 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 4A320 | SM | 280 | INSTALL METAL BEAM GUARDRAILING | 0.31028 | SHOPP | 2012 | 0716F |  |  |  | X |  | 4550000 | 1320000 | 450000 | 330000 | 20000 | 520000 | 775700.54 | 29.01% | 2013-01-04 | 2013-07-01 | 0 | 0 | 0.04432 | 0.26596 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 4A340 | ALA | 013 | REMOVE GORE SIGNS AND REPLACE WITH OVERHEAD SIGNS - PHASE II | 5.2468 | SHOPP | 2012 | 0016W |  | X | X |  |  | 3650000 | 1103000 | 51000 | 501000 | 51000 | 500000 | 0 | 30.22% | 2014-09-21 | 2015-10-01 | 0 | 5.218 | 0.02886 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 4A360 | SM | VAR | REPLACE METAL BEAM GUARDRAIL WITH CONCRETE GUARDRAIL | 3.185 | SHOPP | 2012 | 1066A | X |  |  |  |  | 8083000 | 2606000 | 500000 | 842000 | 211000 | 1053000 | 39477.43 | 32.24% | 2015-05-01 | 2017-07-31 | 0.80679 | 2 | 0.37822 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 4A480 | ALA | 260 | REPAIR HANDRAIL AND SIDEWALK ALONG POSEY AND WEBSTER TUBES AND OTHER | 7.1898 | SHOPP | 2012 | 0098L | X | X | X |  |  | 8721000 | 3075000 | 1000000 | 970000 | 130000 | 975000 | 132919.74 | 35.26% | 2014-08-01 | 2015-12-01 | 0.04845 | 6.3147 | 0.82662 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 4A510 | SF | 280 | REPLACE BRIDGE HINGES | 1.5255 | SHOPP | 2012 | 0609K | [5 empty] | 12574000 | 4872000 | 253000 | 2075000 | 410000 | 2134000 | 1241574.8 | 38.75% | 2014-01-06 | 2015-01-01 | 0 | 0.45148 | 0.74294 | 0.3311 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 4A630 | VAR | VAR | CONSTRUCT WHEELCHAIR RAMPS | 4.1209 | SHOPP | 2012 | 0273M | [5 empty] | 12000000 | 3500000 | 800000 | 1500000 | 400000 | 800000 | 792078.1 | 29.17% | 2013-09-19 | 2014-12-01 | 0 | 1.6056 | 0.44168 | 2.0736 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 4A800 | ALA | 880 | RELOCATION OF RAILROAD BRIDGE | 4.3235 | SHOPP | 2012 | 0050N | X |  |  |  |  | 6754000 | 1900000 | 500000 | 750000 | 150000 | 500000 | 0 | 28.13% | 2015-09-15 | 2016-11-30 | 2.5916 | 1.7316 | 0.00033 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 4A870 | SON | 128 | REPLACE BRIDGES | 0.18277 | SHOPP | 2008 | 0829D | [5 empty] | 10380000 | 1960000 | F | 800000 | 110000 | 1050000 | 6288043.5184 | 18.88% | 2009-09-09 | 2012-01-10 | 0 | 0 | 0.18277 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 4A881 | SON | 128 | MITIGATION PLANTING | 2.0055 | SHOPP | 2008 | 0829E |  |  |  | X |  | 560000 | 300000 | F | 90000 | 10000 | 200000 | 1387637.6016 | 53.57% | 2010-05-26 | 2013-12-01 | 0 | 0 | 0.01572 | 1.9897 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 4A882 | SON | 128 | ENVIRONMENTAL MITIGATION | 1.3773 | SHOPP | 2010 | 0829J | [5 empty] | 350000 | 154000 | F | 44000 | 10000 | 100000 | 350831.66 | 44% | 2012-02-27 | 2017-12-01 | 0 | 0.37069 | 0.0052 | 1.0014 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 4A921 | SM | 082 | INSTALL TOS | 0.02127 | PARTNERSHIP | 2010 | 2140P |  |  |  |  | O
04 | SHOPP | 4G160 | SF | 101 | RECONSTRUCT BRIDGE RAILING AND DECK | 0.24214 | SHOPP | 2012 | 0589Q |  |  |  | X |  | 575000 | 367000 | 40000 | 144000 | 10000 | 173000 | 126772.28 | 63.83% | 2012-11-16 | 2014-05-16 | 0 | 0 | 0.0091 | 0.23304 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 4G450 | SOL | 780 | REPLACE BRIDGE | 3.583 | SHOPP | 2012 | 0832D | X |  |  |  |  | 6250000 | 3600000 | 504000 | 1008000 | 504000 | 1584000 | 0 | 57.6% | 2016-08-18 | 2017-10-01 | 2.4019 | 1.1391 | 0.04203 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 4G460 | MRN | 101 | UPGRADE BRIDGE RAILS | 6.4542 | SHOPP | 2012 | 0832E | X |  |  |  |  | 6485000 | 2249000 | 1210000 | 689000 | 63000 | 287000 | 0 | 34.68% | 2015-07-01 | 2016-12-01 | 0.00374 | 6.3894 | 0.061 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 4G470 | MRN | 580 | UPGRADE BRIDGE RAIL | 4.323 | SHOPP | 2012 | 0832F | X |  |  |  |  | 2045000 | 1339000 | 357000 | 692000 | 59000 | 231000 | 0 | 65.48% | 2015-07-01 | 2016-12-01 | 0.00323 | 4.3111 | 0.00868 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 4G510 | SOL | 080 | SEISMIC RESTORATION AND BRIDGE REPLACEMENT | 7.5275 | SHOPP | 2012 | 0832G | X |  |  |  |  | 11510000 | 4560000 | 1040000 | 1460000 | 240000 | 1820000 | 0 | 39.62% | 2016-02-16 | 2017-06-01 | 4.0519 | 3.4477 | 0.02792 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 4G590 | SM | 280 | JACK PIPE AND BACKFILL SINKHOLE | 0.29128 | SHOPP | 2012 | 0729Q | X | X | X |  |  | 1300000 | 953000 | 317000 | 212000 | 50000 | 374000 | 0 | 73.31% | 2014-08-01 | 2014-10-01 | 0.02969 | 0.26159 | 0 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 4S020 | NAP | 029 | RECONSTRUCT SLOPE AND REPLACE CULVERTS | 5.472 | SHOPP | 2010 | 0379Q | [5 empty] | 2416000 | 2831000 | 763000 | 890000 | 117000 | 1061000 | 2026636.35 | 117.2% | 2013-04-03 | 2018-11-01 | 0 | 0 | 0.16885 | 5.3032 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 4S030 | NAP | 128 | CONSTRUCT SHEET PILE WALL | 6.259 | SHOPP | 2010 | 0829F | [5 empty] | 1339000 | 2665000 | 1064000 | 480000 | 84000 | 1037000 | 1399040.23 | 199% | 2012-12-28 | 2017-10-02 | 0 | 0.11712 | 0.17153 | 5.9704 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 4S050 | SCL | 009 | CONSTRUCT TIE-BACK WALL | 4.3158 | SHOPP | 2012 | 0392C | [5 empty] | 2927000 | 801000 | 110000 | 345000 | 20000 | 326000 | 1089568.28 | 27.37% | 2013-07-17 | 2014-08-16 | 0 | 0.2308 | 0.31841 | 3.7665 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 4S060 | SCL | 085 | HEAVING PAVEMENT AC LEVELING AND GRINDING | 1.6571 | SHOPP | 2012 | 0048E |  |  |  | X |  | 286000 | 89000 | 20000 | 26000 | 5000 | 38000 | 514462.88 | 31.12% | 2012-11-13 | 2013-12-13 | 0 | 0 | 0.07309 | 1.584 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 4S070 | SCL | 101 | INSTALL RSP | 3.0604 | SHOPP | 2012 | 0485L | [5 empty] | 1596000 | 428000 | 95000 | 135000 | 10000 | 188000 | 410463.93 | 26.82% | 2013-05-13 | 2014-08-25 | 0 | 0 | 0.03465 | 3.0257 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 4S080 | SCL | 101 | RECONSTRUCT SLOPE WITH GEOGRID AND SEAL CRACKED WINGWALL | 3.2267 | SHOPP | 2012 | 0485J | [5 empty] | 996000 | 317000 | 80000 | 110000 | 10000 | 117000 | 618619.63 | 31.83% | 2013-05-13 | 2014-07-10 | 0 | 0 | 0.01088 | 3.2158 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 4S090 | SM | 001 | REPLACE FAILED CULVERT AND INSTALL RSP | 0.07982 | SHOPP | 2010 | 0045D | [5 empty] | 319000 | 535000 | 225000 | 225000 | 5000 | 80000 | 525143.78 | 167.7% | 2012-02-15 | 2012-06-15 | 0 | 0 | 0.05065 | 0.02917 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 4S110 | SM | 001 | INSTALL RSP | 0.01411 | SHOPP | 2010 | 0045E | [5 empty] | 372000 | 330000 | E | 250000 | 10000 | 70000 | 334525.9 | 88.71% | 2011-09-13 | 2012-08-15 | 0 | 0 | 0.01411 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 4S120 | SM | 035 | GABION EMBANKMENT REPAIR | 0.63588 | SHOPP | 2012 | 0639G |  |  |  | X |  | 626000 | 460000 | 20000 | 300000 | 10000 | 130000 | 560792.5 | 73.48% | 2012-10-13 | 2013-10-15 | 0 | 0 | 0.07393 | 0.56195 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 4S140 | SM | 092 | RECONSTRUCT SOUNDWALL AND UNDERPIN FOUNDATION | 0.01673 | SHOPP | 2010 | 0653K | [5 empty] | 275000 | 395000 | E | 300000 | 25000 | 70000 | 503861.89 | 143.6% | 2011-06-10 | 2011-09-08 | 0 | 0 | 0.01673 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 4S160 | SON | 001 | REMOVE DEBRIS, INSTALL SUB-DRAINAGE SYSTEM, RECONSTRUCT EMBANKMENT | 2.1088 | SHOPP | 2012 | 0753M | [5 empty] | 1544000 | 1505000 | 340000 | 760000 | 140000 | 265000 | 959719.97 | 97.47% | 2013-08-13 | 2014-08-26 | 0 | 0.09372 | 0.01502 | 2 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 4S190 | SON | 116 | CONSTRUCT SOLDIER PILE WALL | 3.9886 | SHOPP | 2012 | 0816G | X |  |  |  |  | 3266000 | 2650000 | 1000000 | 1200000 | 100000 | 350000 | 761012.32 | 81.14% | 2015-02-01 | 2015-12-01 | 1.0097 | 2.2831 | 0.69581 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 4S220 | MRN | 001 | CONSTRUCT SOLDIER PILE/TIE BACK RETAINING WALL | 1.3795 | SHOPP | 2012 | 0313E |  | X | X |  |  | 1550000 | 1690000 | 440000 | 700000 | 100000 | 450000 | 1135154.37 | 109% | 2014-10-24 | 2015-11-06 | 0 | 1.2968 | 0.08274 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 4S270 | CC | 024 | INSTALL DOWNDRAIN, GRADING AND REPLACE FAILED CULVERT | 0.93899 | SHOPP | 2012 | 0247D |  |  |  | X |  | 881000 | 280000 | 5000 | 180000 | 5000 | 90000 | 1007225.24 | 31.78% | 2012-11-19 | 2013-12-11 | 0 | 0 | 0 | 0.93899 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 4S370 | ALA | 580 | INSTALL ROCK SLOPE PROTECTION AND ROCK SLOPE PROTECTION FABRIC, RE- | 0.84928 | SHOPP | 2012 | 0114E |  |  |  | X |  | 766000 | 330000 | 5000 | 180000 | 5000 | 140000 | 978591.66 | 43.08% | 2012-11-05 | 2013-12-10 | 0 | 0 | 0.00606 | 0.84322 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 4S430 | SM | 001 | EROSION CONTROL | 1.0049 | SHOPP | 2010 | 0623H | [5 empty] | 787000 | 632000 | 3000 | 356000 | 19000 | 254000 | 671079.18 | 80.3% | 2011-06-23 | 2014-11-30 | 0 | 0 | 0.00867 | 0.99624 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 4S450 | MRN | 001 | REPAIR WASH OUT BY REMOVING TEMP RSP AND RECONSTRUCT EMBANKMENT | 2.1139 | SHOPP | 2012 | 0322C | [5 empty] | 1150000 | 1170000 | 575000 | 250000 | 25000 | 320000 | 796994.16 | 101.7% | 2013-10-15 | 2014-10-28 | 0 | 0.15499 | 0.0105 | 1.9484 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 4S490 | CC | 004 | REGRADE EXISTING SLOPE, INSTALL PERMEABLE BLANKET, AND PAVE SLOPE | 0.00732 | SHOPP | 2010 | 0187D | [5 empty] | 155000 | 320000 | 5000 | 200000 | 5000 | 110000 | 477581.17 | 206.5% | 2011-11-07 | 2012-02-17 | 0 | 0 | 0.00017 | 0.00715 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 4S500 | CC | 680 | INSTALL NEW DRAINAGE PIPE, MANHOLES AND INLET, REPLACE LANDSCAPE | 0.00613 | SHOPP | 2010 | 0305C | [5 empty] | 180000 | 303000 | 3000 | 190000 | 10000 | 100000 | 453917.16 | 168.3% | 2011-11-07 | 2012-01-20 | 0 | 0 | 0.00035 | 0.00578 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 4S530 | MRN | 001 | CONSTRUCT A SOIL NAIL WALL AND PLACE ROCK SLOPE PROTECTION | 2.2433 | SHOPP | 2010 | 0303H |  |  |  | X |  | 1200000 | 428000 | 12000 | 174000 | 10000 | 232000 | 773774.33 | 35.67% | 2012-10-01 | 2013-10-15 | 0 | 0 | 0.1066 | 2.1367 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 4S540 | MRN | 001 | DRAINAGE SYSTEM REHABILITATION | 0.19155 | SHOPP | 2010 | 0713M | [5 empty] | 3050000 | 1090000 | 30000 | 450000 | 10000 | 600000 | 1159393.19 | 35.74% | 2011-04-14 | 2012-02-23 | 0 | 0 | 0.08388 | 0.10767 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 4S550 | MRN | 101 | REPLACE EXISTING FILL WITH LIGHWEIGHT FILL ENCAPSULATED IN | 0.32441 | SHOPP | 2010 | 0268R | [5 empty] | 2274000 | 812000 | 23000 | 334000 | 10000 | 445000 | 1138182.57 | 35.71% | 2012-04-20 | 2013-05-03 | 0 | 0 | 0.02072 | 0.30369 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 4S580 | SM | 001 | CONSTRUCT LINED DITCH AND PLACE SLOPE PROTECTION | 1.064 | SHOPP | 2012 | 0624G |  |  |  | X |  | 409000 | 142000 | 4000 | 57000 | 5000 | 76000 | 483096.54 | 34.72% | 2012-11-30 | 2013-12-11 | 0 | 0 | 0.05146 | 1.0125 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 4S590 | SM | 084 | CONSTRUCT A SECANT WALL, REPAIR AC PAVEMENT AND REPAIR DRAINAGE DIKES | 0.13994 | SHOPP | 2010 | 0653N | [5 empty] | 2356000 | 746000 | 54000 | 330000 | 30000 | 332000 | 855646.5 | 31.66% | 2012-04-25 | 2013-06-07 | 0 | 0 | 0.01367 | 0.12627 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 4S620 | SON | 001 | CONSTRUCT A SOLDIER PILE TIE-BACK WALL | 2.1527 | SHOPP | 2010 | 0748L | [5 empty] | 2110000 | 756000 | 20000 | 294000 | 50000 | 392000 | 900269.12 | 35.83% | 2014-01-03 | 2015-01-02 | 0 | 0.40907 | 0.395 | 1.3486 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 4S630 | SON | 001 | REPAIR SLIPOUT | 0.23269 | SHOPP | 2010 | 0756H | [5 empty] | 437000 | 400000 | E | 281000 | 10000 | 109000 | 420153.46 | 91.53% | 2011-02-15 | 2011-10-18 | 0 | 0 | 0.05041 | 0.18228 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 4S640 | SON | 101 | INSTALL ROCK SLOPE PROTECTION | 0.12332 | SHOPP | 2010 | 0116P | [5 empty] | 605000 | 444000 | 230000 | 79000 | 10000 | 125000 | 587112.48 | 73.39% | 2011-11-18 | 2012-10-05 | 0 | 0 | 0.00246 | 0.12086 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 4S650 | SON | 101 | CONSTRUCT A TIE-BACK RETAINING WALL | 0.19029 | SHOPP | 2010 | 0303J | [5 empty] | 3105000 | 779000 | 24000 | 270000 | 10000 | 475000 | 1171639.13 | 25.09% | 2011-11-16 | 2013-06-30 | 0 | 0 | 0.03228 | 0.15801 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 4S660 | MRN | 001 | PERMANENT RESTORATION & TO REPLACE EMERGENCY REPAIR WALL | 3.1488 | SHOPP | 2012 | 0308J | X |  |  |  |  | 1775000 | 1235000 | 450000 | 400000 | 50000 | 335000 | 523691 | 69.58% | 2015-08-22 | 2016-10-01 | 0.01397 | 2.9487 | 0.18613 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 4S770 | MRN | 001 | REPLACE FAILED CULVERT AND EXTEND ANOTHER CULVERT IN ANOTHER | 1.5855 | SHOPP | 2012 | 0312L | [5 empty] | 1040000 | 680000 | 160000 | 150000 | 180000 | 190000 | 338842.75 | 65.38% | 2013-09-04 | 2014-09-04 | 0 | 0.14794 | 0.0557 | 1.3819 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 4S780 | MRN | 001 | REPLACE FAILED CULVERT AND RECONSTRUCT THE EMBANKMENT. | 2.6621 | SHOPP | 2012 | 0315D |  | X | X |  |  | 1295000 | 735000 | 400000 | 95000 | 100000 | 140000 | 231644.81 | 56.76% | 2014-07-01 | 2015-02-02 | 0 | 2.0955 | 0.56659 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 4S920 | SON | 001 | CONSTRUCT SOLDIER PILE WALL | 1.6662 | SHOPP | 2012 | 0752Z |  | X | X |  |  | 1650000 | 835000 | 210000 | 155000 | 200000 | 270000 | 332514.79 | 50.61% | 2014-09-04 | 2015-10-03 | 0 | 1.5817 | 0.08445 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | 4S960 | SON | 001 | REPLACE CULVERT | 1.0068 | SHOPP | 2010 | 0748M |  |  |  | X |  | 815000 | 440000 | 110000 | 200000 | 10000 | 120000 | 336980.06 | 53.99% | 2012-07-01 | 2013-09-01 | 0 | 0 | 0.02171 | 0.98508 | Caltrans | Caltrans | Caltrans | Caltrans
04 | SHOPP | MINOR |  |  | SHOPP MINOR | 32.5169 | MINOR
05 | SHOPP | 39610 | SB | 192 | REPLACE BRIDGE (SCOUR) | 4.4578 | SHOPP | 2012 | 0335 |  | X | X |  |  | 6379000 | 4829000 | 960000 | 2715000 | 420000 | 734000 | 3095190.93 | 75.7% | 2014-07-10 | 2019-03-01 | 0 | 3.8765 | 0.48803 | 0.09326 | Caltrans | Caltrans | Caltrans | Caltrans
05 | SHOPP | 46250 | SB | 101 | RESTORE HIGHWAY PLANTING | 0.3332 | SHOPP | 2008 | 4625 |  |  |  | X |  | 3286000 | 1562000 | 159000 | 598000 | 4000 | 801000 | 1075899.83 | 47.53% | 2009-08-31 | 2014-04-01 | 0 | 0 | 0.00495 | 0.32825 | Caltrans | Caltrans | Caltrans | Caltrans
05 | SHOPP | 49280 | SLO | 001 | REALIGN ROADWAY | 6.1182 | SHOPP | 2012 | 4928 |  | X | X |  |  | 57770000 | 13769000 | 3570000 | 4257000 | 806000 | 5136000 | 6337935.62 | 23.83% | 2014-03-06 | 2019-03-14 | 0 | 3.0061 | 1.162 | 1.9502 | Caltrans | Caltrans | Caltrans | Caltrans
05 | SHOPP | 1E060 | MON | 101 | CONCRETE MEDIAN BARRIER, INSIDE SHOULDER WIDENING AND RUMBLE STRIP | 2.8121 | SHOPP PA
05 | SHOPP | 0A050 | SB | 001 | CONSTRUCT SOIL NAIL/TIEBACK RETAINING WALL | 3.2497 | SHOPP | 2012 | 1501 | [5 empty] | 3023000 | 3483000 | 1402000 | 1109000 | 122000 | 850000 | 967628.72 | 115.2% | 2017-06-01 | 2018-09-01 | 3.2497 | 0 | 0 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
05 | SHOPP | 0C901 | SCR | 001 | INSTALL CCTV AND SIGNS | 1.6921 | SHOPP | 2012 | 9000 | [5 empty] | 2969000 | 1821000 | 412000 | 550000 | 47000 | 812000 | 610739.58 | 61.33% | 2013-10-01 | 2014-12-01 | 0 | 0.10454 | 0.11857 | 1.469 | Caltrans | Caltrans | Caltrans | Caltrans
05 | SHOPP | 0E960 | MON | 001 | CONSTRUCT BRIDGE AND ROCK SHED | 2.8767 | SHOPP | 2008 | 5960 |  |  |  | X |  | 38967000 | 10854000 | 2880000 | 3330000 | 88000 | 4556000 | 9378828.54 | 27.85% | 2009-10-01 | 2013-09-23 | 0 | 0 | 0.0723 | 2.8044 | Caltrans | Caltrans | Caltrans | Caltrans
05 | SHOPP | 0F700 | MON | 068 | BRIDGE WIDENING | 6.945 | SHOPP | 2012 | 7000 | [5 empty] | 15342000 | 6956000 | 1229000 | 2751000 | 243000 | 2733000 | 1542402.53 | 45.34% | 2015-02-10 | 2016-10-10 | 0 | 6.3247 | 0.62024 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
05 | SHOPP | 0F990 | SCR | 001 | BRIDGE REPLACEMENT | 3.6807 | SHOPP | 2012 | 9900 | [5 empty] | 20709000 | 8099000 | 2118000 | 2960000 | 121000 | 2900000 | 1404348.21 | 39.11% | 2016-01-11 | 2018-04-01 | 0.90313 | 1.983 | 0.00655 | 0.78798 | Caltrans | Caltrans | Caltrans | Caltrans
05 | SHOPP | 0G040 | SLO | 101 | HIGHWAY REHAB | 11.5816 | SHOPP | 2012 | 0040B | X |  |  |  |  | 47065000 | 13139000 | 2897000 | 5214000 | 430000 | 4598000 | 2095542.42 | 27.92% | 2016-03-01 | 2018-05-16 | 0.00477 | 11.0691 | 0.50772 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
05 | SHOPP | 0G070 | SB | 101 | UPGRADE EXISTING DRAINAGE CULVERTS | 4.6072 | SHOPP | 2012 | 0707 | [5 empty] | 17245000 | 6442000 | 2537000 | 1093000 | 119000 | 2693000 | 4654787.87 | 37.36% | 2013-11-15 | 2016-06-01 | 0 | 0.47478 | 0.102 | 4.0304 | Local | Caltrans | Caltrans | Caltrans
05 | SHOPP | 0G160 | SB | 166 | RELOCATE DRAINAGE DITCHES | 4.0191 | SHOPP | 2012 | 1850 | [5 empty] | 5276000 | 3847000 | 820000 | 1133000 | 680000 | 1214000 | 2176664.55 | 72.92% | 2013-03-27 | 2014-08-01 | 0 | 0 | 0.58581 | 3.4333 | Caltrans | Caltrans | Caltrans | Caltrans
05 | SHOPP | 0G400 | SCR | 017 | CONSTRUCT CONCRETE BARRIER AND RETAINING WALLS | 0.62695 | SHOPP | 2008 | 4001 | [5 empty] | 4567000 | 5128000 | 1228000 | 1691000 | 126000 | 2083000 | 2904482 | 112.3% | 2011-01-11 | 2013-03-01 | 0 | 0 | 0.05782 | 0.56913 | Caltrans | Caltrans | Caltrans | Caltrans
05 | SHOPP | 0H330 | MON | 101 | UPGRADE EXISTING EXPRESWAY TO A FREEWAY, INTERCHANGES & FRONTAGE RD | 4.9771 | STIP | 2012 | 3300 | [5 empty] | 145243000 | 8600000 | 8600000 | A | A | A | 0 | 5.921% | - - | - - | 4.9771 | 0 | 0 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
05 | SHOPP | 0K230 | SCR | 009 | GUARDRAIL UPGRADE & SHOULDER WIDENING | 0.91921 | SHOPP | 2010 | 1937 |  |  |  | X |  | 3097000 | 2467000 | 796000 | 1013000 | 38000 | 620000 | 2010678.11 | 79.66% | 2012-05-23 | 2014-01-16 | 0 | 0 | 0 | 0.91921 | Caltrans | Caltrans | Caltrans | Caltrans
05 | SHOPP | 0L701 | SCR | 017 | UPGRADE GUARD RAIL | 9.7851 | SHOPP | 2008 | 7007 |  |  |  | X |  | 10000000 | 7253000 | 972000 | 2990000 | 178000 | 3113000 | 0 | 72.53% | 2013-02-20 | 2014-02-03 | 0 | 0 | 0.06077 | 9.7244 | Caltrans | Caltrans | Caltrans | Caltrans
05 | SHOPP | 0L720 | SLO | 001 | BRIDGE RAIL REPLACEMENT | 4.5534 | SHOPP | 2012 | 0072 | [5 empty] | 8081000 | 3748000 | 448000 | 1769000 | 68000 | 1463000 | 0 | 46.38% | 2016-09-01 | 2017-12-01 | 3.3622 | 1.1911 | 0 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
05 | SHOPP | 0M14V | SB | 101 | LANDSCAPE MITIGATION PLANTING AT THE CATHEDRAL OAKS OC AND OH | 0.07025 | SHOPP | 2010 | 1840Y | [5 empty] | 897000 | 295000 | H | 167000 | C | 128000 | 361724.1 | 32.89% | 2011-10-26 | 2015-04-17 | 0 | 0 | 0.00337 | 0.06688 | Caltrans | Caltrans | Caltrans | Caltrans
05 | SHOPP | 0M750 | SCR | 001 | PAVEMENT REHABILITATION | 0.03062 | SHOPP | 2010 | 0075 | [5 empty] | 24775000 | 3763000 | E | 1110000 | 30000 | 2623000 | 1266305.01 | 15.19% | 2012-01-05 | 2012-11-01 | 0 | 0 | 0.00065 | 0.02997 | Caltrans | Caltrans | Caltrans | Caltrans
05 | SHOPP | 0M970 | SCR | 001 | GUARDRAIL AND CRASH CUSHIONS | 0.50151 | SHOPP | 2010 | 1963 |  |  |  | X |  | 2783000 | 1140000 | E | 739000 | 117000 | 284000 | 642643.07 | 40.96% | 2012-09-12 | 2013-07-01 | 0 | 0 | 0.02088 | 0.48063 | Caltrans | Caltrans | Caltrans | Caltrans
05 | SHOPP | 0M980 | SCR | 001 | GUARDRAIL UPGRADE | 1.2744 | SHOPP | 2012 | 1964 |  |  |  | X |  | 2451000 | 857000 | E | 435000 | 14000 | 408000 | 542849.51 | 34.97% | 2013-02-18 | 2013-09-04 | 0 | 0.0691 | 0.0848 | 1.1205 | Caltrans | Caltrans | Caltrans | Caltrans
05 | SHOPP | 0N060 | SLO | 101 | PLACE HOT MIX ASPHALT | 0.50417 | SHOPP | 2008 | 0606 | [5 empty] | 12646000 | 1810000 | E | 777000 | 30000 | 1003000 | 1353863.3 | 14.31% | 2010-09-15 | 2013-04-01 | 0 | 0 | 0 | 0.50417 | Caltrans | Caltrans | Caltrans | Caltrans
05 | SHOPP | 0N831 | MON | 101 | PLANTING AND IRRIGATION | 0.04996 | SHOPP | 2008 | 8300Y | [5 empty] | 193000 | 323000 | H | 200000 | 3000 | 120000 | 221771.06 | 167.4% | 2009-10-27 | 2012-10-03 | 0 | 0 | 0 | 0.04996 | Caltrans | Caltrans | Caltrans | Caltrans
05 | SHOPP | 0N890 | SLO | 101 | CONSTRUCT RETAINING WALL | 0.3795 | SHOPP | 2010 | 8900 | [5 empty] | 7010000 | 1704000 | 86000 | 667000 | 6000 | 945000 | 1459401 | 24.31% | 2011-08-24 | 2012-11-14 | 0 | 0 | 0.0047 | 0.3748 | Caltrans | Caltrans | Caltrans | Caltrans
05 | SHOPP | 0P250 | MON | 001 | MBGR AND CONCRETE BARRIER IMPROVE- MENTS AT VARIOUS LOCATIONS | 0.0062 | SHOPP | 2010 | 2278 | [5 empty] | 4216000 | 1532000 | 42000 | 837000 | 9000 | 644000 | 608402.01 | 36.34% | 2011-09-26 | 2012-03-21 | 0 | 0 | 0.00048 | 0.00572 | Caltrans | Caltrans | Caltrans | Caltrans
05 | SHOPP | 0Q570 | MON | 101 | INSTALL MEDIAN BARRIER | 4.0683 | SHOPP | 2012 | 1991 | [5 empty] | 10860000 | 1822000 | E | 672000 | 9000 | 1141000 | 940484.2 | 16.78% | 2013-04-22 | 2014-07-21 | 0 | 0.13624 | 0.01218 | 3.9199 | Caltrans | Caltrans | Caltrans | Caltrans
05 | SHOPP | 0Q590 | SCR | 009 | STORM WATER MITIGATION | 2.5548 | SHOPP | 2012 | 1988 |  | X | X |  |  | 4805000 | 2226000 | 334000 | 668000 | 111000 | 1113000 | 1042410.29 | 46.33% | 2014-04-21 | 2015-05-04 | 0 | 1.0199 | 0.28474 | 1.2501 | Caltrans | Caltrans | Caltrans | Caltrans
05 | SHOPP | 0Q600 | SCR | 017 | STORM WATER MITIGATION | 2.7521 | SHOPP | 2012 | 1989 | [5 empty] | 11012000 | 3573000 | 1273000 | 991000 | 196000 | 1113000 | 0 | 32.45% | 2016-07-25 | 2017-05-08 | 2.7521 | 0 | 0 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
05 | SHOPP | 0Q620 | SLO | 101 | CONSTRUCT MEDIAN BARRIER | 0.54504 | SHOPP | 2010 | 1993 |  |  |  | X |  | 5492000 | 2090000 | 176000 | 929000 | 26000 | 959000 | 614576.77 | 38.06% | 2012-07-25 | 2013-07-01 | 0 | 0 | 0.04295 | 0.50209 | Caltrans | Caltrans | Caltrans | Caltrans
05 | SHOPP | 0Q630 | SLO | 101 | CONSTRUCT MEDIAN BARRIER | 0.6112 | SHOPP | 2010 | 1994 | [5 empty] | 4911000 | 2077000 | 556000 | 788000 | 18000 | 715000 | 919809.98 | 42.29% | 2012-08-02 | 2013-06-30 | 0 | 0.00027 | 0.04001 | 0.57092 | Caltrans | Caltrans | Caltrans | Caltrans
05 | SHOPP | 0Q631 | SLO | 101 | MITIGATION PLANTING AND IRRIGATION | 0.62716 | SHOPP | 2012 | 1994Y | [5 empty] | 200000 | 563000 | H | 150000 | 2000 | 411000 | 18527.75 | 281.5% | 2013-04-15 | 2016-09-15 | 0 | 0 | 0.00157 | 0.62559 | Caltrans | Caltrans | Caltrans | Caltrans
05 | SHOPP | 0R300 | SLO | 166 | CURVE CORRECTION, CULVERT, PAVING AND EARTHWORK | 2.8503 | SHOPP | 2010 | 2243 | [5 empty] | 3600000 | 2877000 | 780000 | 1172000 | 112000 | 813000 | 961128.71 | 79.92% | 2012-10-25 | 2014-07-01 | 0 | 0 | 0.10579 | 2.7446 | Caltrans | Caltrans | Caltrans | Caltrans
05 | SHOPP | 0R510 | SCR | 001 | ADA CURB RAMPS AND MINOR SIDEWALKS | 10.5549 | SHOPP | 2012 | 2235 | [5 empty] | 4936000 | 3350000 | 485000 | 983000 | 1189000 | 693000 | 1125720.63 | 67.87% | 2015-09-04 | 2016-07-01 | 0 | 8.4003 | 2.1546 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
05 | SHOPP | 0R530 | SLO | 001 | ADA CURB RAMPS | 3.1029 | SHOPP | 2012 | 2232 |  | X | X |  |  | 1743000 | 2227000 | 259000 | 706000 | 775000 | 487000 | 703741.43 | 127.8% | 2014-04-01 | 2014-12-01 | 0 | 2.2387 | 0.86424 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
05 | SHOPP | 0R750 | SB | 246 | INTERSECTION IMPROVEMENTS | 0.51815 | SHOPP | 2010 | 2229 |  |  |  | X |  | 3500000 | 1639000 | E | 799000 | 241000 | 599000 | 1062353.53 | 46.83% | 2011-08-26 | 2013-07-01 | 0 | 0 | 0.26485 | 0.2533 | Caltrans | Caltrans | Caltrans | Caltrans
05 | SHOPP | 0R830 | SB | 001 | ADA CURB RAMPS AND MINOR SIDEWALKS | 4.0094 | SHOPP | 2012 | 2231 |  | X | X |  |  | 1842000 | 1910000 | 330000 | 530000 | 550000 | 500000 | 990197.77 | 103.7% | 2014-09-01 | 2015-07-15 | 0 | 2.4955 | 1.5139 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
05 | SHOPP | 0R840 | SBT | 025 | ADA CURB RAMPS AND MINOR SIDEWALKS | 0.17094 | SHOPP | 2010 | 2233 | [5 empty] | 1076000 | 1328000 | 190000 | 477000 | 371000 | 290000 | 1188193.41 | 123.4% | 2012-09-13 | 2013-03-29 | 0 | 0 | 0.07771 | 0.09323 | Caltrans | Caltrans | Caltrans | Caltrans
05 | SHOPP | 0R910 | SCR | 001 | UPGRADE MBGR, CONSTRUCT CONCRETE BARRIER & RETAINING WALLS & GUARD | 3.3209 | SHOPP | 2012 | 2271 | [5 empty] | 2544000 | 1856000 | 601000 | 639000 | 166000 | 450000 | 1148412.86 | 72.96% | 2013-07-10 | 2014-07-01 | 0 | 0.02208 | 0.09943 | 3.1993 | Caltrans | Caltrans | Caltrans | Caltrans
05 | SHOPP | 0S030 | SB | 001 | CURB RAMPS AND MINOR SIDEWALK EXTENSIONS | 3.6433 | SHOPP | 2012 | 2241 |  | X | X |  |  | 2522000 | 2324000 | 299000 | 797000 | 754000 | 474000 | 514413.39 | 92.15% | 2014-09-15 | 2015-07-01 | 0 | 2.7796 | 0.77388 | 0.08981 | Caltrans | Caltrans | Caltrans | Caltrans
05 | SHOPP | 0S250 | SB | 101 | ROADSIDE SAFETY IMPROVEMENTS | 1.6386 | SHOPP | 2012 | 2256 | X |  |  |  |  | 1991000 | 1338000 | 250000 | 415000 | 3000 | 670000 | 3797.62 | 67.2% | 2015-04-15 | 2015-08-01 | 0.12873 | 1.5029 | 0.00704 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
05 | SHOPP | 0S310 | SCR | 001 | CONCRETE MEDIAN BARRIER | 0.05506 | SHOPP | 2010 | 2246 | [5 empty] | 1607000 | 749000 | E | 486000 | 6000 | 257000 | 622097.15 | 46.61% | 2012-02-03 | 2012-10-21 | 0 | 0 | 0 | 0.05506 | Caltrans | Caltrans | Caltrans | Caltrans
05 | SHOPP | 0S780 | MON | 101 | ROADWAY REHABILITATION | 1.9953 | SHOPP | 2012 | 2261 | X |  |  |  |  | 8551000 | 1915000 | 277000 | 890000 | 7000 | 741000 | 2105.01 | 22.4% | 2016-01-11 | 2016-10-03 | 0.14063 | 1.8401 | 0.01459 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
05 | SHOPP | 0S790 | SLO | 101 | PAVEMENT PRESERVATION | 0.51202 | SHOPP | 2012 | 2262 | [5 empty] | 3802000 | 1232000 | 179000 | 691000 | 9000 | 353000 | 87231.04 | 32.4% | 2016-01-11 | 2016-10-03 | 0 | 0.44124 | 0.0194 | 0.05138 | Caltrans | Caltrans | Caltrans | Caltrans
05 | SHOPP | 0T000 | SB | 154 | INTERSECTION IMPROVEMENTS | 1.8323 | SHOPP | 2012 | 2267 |  | X | X |  |  | 3486000 | 2153000 | 250000 | 851000 | 209000 | 843000 | 485750.62 | 61.76% | 2014-02-24 | 2015-10-02 | 0 | 0.87192 | 0.1609 | 0.79944 | Caltrans | Caltrans | Caltrans | Caltrans
05 | SHOPP | 0T270 | MON | 068 | INSTALL TRAFFIC SIGNAL | 1.2393 | SHOPP | 2012 | 2303 | [5 empty] | 1169000 | 785000 | E | 387000 | 94000 | 304000 | 0 | 67.15% | 2015-05-15 | 2016-02-01 | 0 | 0.99699 | 0.24236 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
05 | SHOPP | 0T540 | SCR | 129 | CURVE REALIGNMENT | 5.0387 | SHOPP | 2012 | 2285 |  | X | X |  |  | 12628000 | 4010000 | 641000 | 1497000 | 155000 | 1717000 | 417074.8 | 31.75% | 2014-11-03 | 2016-10-01 | 0 | 4.5918 | 0.4469 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
05 | SHOPP | 0T560 | MON | 001 | CONSTRUCT RETAINING WALL | 0.30394 | SHOPP | 2010 | 2294 | [5 empty] | 18700000 | 5800000 | 1700000 | 1200000 | 200000 | 2700000 | 2013809.65 | 31.02% | 2010-09-16 | 2012-11-16 | 0 | 0 | 0.09494 | 0.209 | Caltrans | Caltrans | Caltrans | Caltrans
05 | SHOPP | 0T630 | SB | 101 | CURVE REALIGNMENT | 3.1602 | SHOPP | 2012 | 2292 | X |  |  |  |  | 6906000 | 4246000 | 1509000 | 1401000 | 52000 | 1284000 | 614918.7 | 61.48% | 2016-04-01 | 2017-08-01 | 0.06382 | 2.9371 | 0.15919 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
05 | SHOPP | 0T640 | SBT | 025 | CURVE CORRECTION | 3.7004 | SHOPP | 2012 | 2293 |  | X | X |  |  | 1315000 | 2095000 | 605000 | 675000 | 250000 | 565000 | 735492.97 | 159.3% | 2014-09-17 | 2015-07-21 | 0 | 2.8739 | 0.82647 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
05 | SHOPP | 0T760 | MON | 001 | WET WEATHER IMPROVEMENT | 1.3112 | SHOPP PA |  |  |  | X | X
05 | SHOPP | 0T850 | MON | 001 | CONSTRUCT VIADUCT | 2.575 | SHOPP | 2012 | 2314 | [5 empty] | 39620000 | 15454000 | 4500000 | 3821000 | 793000 | 6340000 | 1341377.11 | 39.01% | 2016-01-02 | 2018-02-01 | 2.2626 | 0.26236 | 0.05005 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
05 | SHOPP | 0T970 | SB | 246 | LEFT-TURN CHANNELIZATION | 1.5691 | SHOPP | 2012 | 2308 |  | X |  | X |  | 869000 | 576000 | E | 280000 | 56000 | 240000 | 116020.7 | 66.28% | 2013-11-21 | 2014-04-01 | 0 | 0.0923 | 0.09446 | 1.3823 | Caltrans | Caltrans | Caltrans | Caltrans
05 | SHOPP | 0T980 | SCR | 017 | SHOULDER WIDENING AND CONCRETE GUARDRAIL | 6.447 | SHOPP | 2012 | 2311 | [5 empty] | 7043000 | 3302000 | E | 1625000 | 109000 | 1568000 | 11219.65 | 46.88% | 2015-06-10 | 2017-10-01 | 0 | 6.1283 | 0.31872 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
05 | SHOPP | 0T990 | MON | 101 | HIGHWAY PLANTING REHABILITATION | 1.3775 | SHOPP | 2012 | 2312 | [5 empty] | 6025000 | 1920000 | 553000 | 671000 | 69000 | 627000 | 10575.36 | 31.87% | 2016-04-01 | 2019-10-01 | 1.3729 | 0 | 0.0046 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
05 | SHOPP | 1A270 | MON | 001 | STABILIZE ROADWAY AND INSTALL TEMPORARY TRAFFIC SIGNAL | 0.11834 | SHOPP | 2010 | 2318 | [5 empty] | 2525000 | 835000 | 75000 | 285000 | 15000 | 460000 | 982640.27 | 33.07% | 2011-04-15 | 2012-11-28 | 0 | 0 | 0 | 0.11834 | Caltrans | Caltrans | Caltrans | Caltrans
05 | SHOPP | 1A570 | MON | 001 | CONSTRUCT SOLDIER PILE TIE-BACK RETAINING WALL AND RECONSTRUCT LANE | 0.20547 | SHOPP | 2010 | 2325 |  |  |  | X |  | 5505000 | 1363000 | 100000 | 420000 | 25000 | 818000 | 395029.35 | 24.76% | 2011-06-29 | 2013-07-01 | 0.00046 | 0.00207 | 0.00278 | 0.20016 | Caltrans | Caltrans | Caltrans | Caltrans
05 | SHOPP | 1A690 | MON | 001 | CONSTRUCT VIADUCT 600' X 43.5' | 5.7312 | SHOPP | 2010 | 2330 | [5 empty] | 18845000 | 6955000 | 2000000 | 2000000 | 135000 | 2820000 | 907086.03 | 36.91% | 2012-07-26 | 2014-09-30 | 0 | 0 | 0.01253 | 5.7187 | Caltrans | Caltrans | Caltrans | Caltrans
05 | SHOPP | 1A700 | SLO | 001 | CONSTRUCT 50' HIGH X 850' LONG SOLDIER PILE WALL WITH TIEBACKS | 4.9964 | SHOPP | 2012 | 2331 |  | X | X |  |  | 13715000 | 3425000 | 500000 | 770000 | 100000 | 2055000 | 302438.74 | 24.97% | 2014-08-15 | 2016-08-15 | 0 | 4.7396 | 0.25672 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
05 | SHOPP | 1A710 | SCR | 017 | CONSTRUCT SOLDIER PILE WALL WITH TIE-BACKS 350' X 30' | 0.58723 | SHOPP | 2010 | 2332 |  |  |  | X |  | 4925000 | 1225000 | 150000 | 290000 | 50000 | 735000 | 239267.12 | 24.87% | 2012-07-24 | 2013-07-01 | 0 | 0 | 0.03695 | 0.55028 | Caltrans | Caltrans | Caltrans | Caltrans
05 | SHOPP | 1A720 | SB | 101 | PAVEMENT PRESERVATION | 2.8695 | SHOPP | 2012 | 2333 |  |  | X |  |  | 10476000 | 2160000 | 193000 | 990000 | 11000 | 966000 | 2570.58 | 20.62% | 2015-08-10 | 2016-02-23 | 0 | 2.7642 | 0.05963 | 0.04567 | Caltrans | Caltrans | Caltrans | Caltrans
05 | SHOPP | 1A730 | MON | 101 | PAVEMENT PRESERVATION | 1.5019 | SHOPP | 2012 | 2334 | X |  |  |  |  | 6513000 | 1590000 | 167000 | 841000 | 6000 | 576000 | 770.42 | 24.41% | 2016-02-03 | 2016-10-13 | 0.15508 | 1.3334 | 0.01348 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
05 | SHOPP | 1A750 | SB | 246 | PAVEMENT PRESERVATION | 2.1544 | SHOPP | 2012 | 2336 | [5 empty] | 9868000 | 1656000 | 285000 | 581000 | 54000 | 736000 | 21943.03 | 16.78% | 2016-01-11 | 2016-10-03 | 0.11468 | 1.9455 | 0.0943 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
05 | SHOPP | 1A760 | MON | 001 | PAVEMENT PRESERVATION | 3.1801 | SHOPP | 2012 | 2355 | X |  |  |  |  | 9219000 | 2125000 | 257000 | 921000 | 7000 | 940000 | 6576.12 | 23.05% | 2016-01-11 | 2016-10-03 | 0.13668 | 3.0346 | 0.00886 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
05 | SHOPP | 1A870 | SCR | 001 | RE-STRIPING AND SHOULDER WIDENING | 4.0979 | SHOPP PA |  |  | X
05 | SHOPP | 1A970 | SB | 101 | REPLACE DAMAGED BRIDGE RAILING | 0.32551 | SHOPP | 2010 | 2350 | [5 empty] | 1395000 | 510000 | 50000 | 150000 | 10000 | 300000 | 307118.04 | 36.56% | 2012-07-26 | 2013-01-12 | 0 | 0 | 0.00061 | 0.3249 | Caltrans | Caltrans | Caltrans | Caltrans
05 | SHOPP | 1C080 | SLO | 101 | ROADSIDE SAFETY IMPROVEMENTS | 1.4376 | SHOPP | 2012 | 2356 | X |  |  |  |  | 2146000 | 1135000 | 239000 | 451000 | 5000 | 440000 | 0 | 52.89% | 2015-04-22 | 2016-03-01 | 0.00206 | 1.4096 | 0.02595 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
05 | SHOPP | 1C090 | MON | 068 | ROADSIDE SAFETY IMPROVEMENTS | 1.1666 | SHOPP | 2012 | 2357 | X |  |  |  |  | 2214000 | 1405000 | 245000 | 450000 | 5000 | 705000 | 10934.98 | 63.46% | 2015-08-22 | 2016-07-01 | 0.0025 | 1.1408 | 0.02334 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
05 | SHOPP | 1C100 | SCR | 001 | ROADSIDE SAFETY IMPROVEMENTS | 0.71713 | SHOPP | 2012 | 2358 | X |  |  |  |  | 1227000 | 1119000 | 211000 | 421000 | 5000 | 482000 | 5117.73 | 91.2% | 2016-04-22 | 2017-03-01 | 0.00364 | 0.69676 | 0.01673 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
05 | SHOPP | 1C110 | SLO | 101 | ROADSIDE SAFETY IMPROVEMENTS | 0.91891 | SHOPP | 2012 | 2359 | X |  |  |  |  | 2552000 | 1318000 | 281000 | 520000 | 5000 | 512000 | 3966.06 | 51.65% | 2016-04-22 | 2017-03-01 | 0.00429 | 0.89655 | 0.01807 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
05 | SHOPP | 1C120 | SB | 101 | ROADSIDE SAFETY IMPROVEMENTS | 0.99081 | SHOPP | 2012 | 2360 | X |  |  |  |  | 2429000 | 1265000 | 247000 | 507000 | 5000 | 506000 | 5837.08 | 52.08% | 2016-04-22 | 2017-03-01 | 0.66076 | 0.31969 | 0.01036 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
05 | SHOPP | 1C130 | SLO | 001 | CURB RAMPS AND SIDEWALK | 2.0577 | SHOPP | 2012 | 2382 | X |  |  |  |  | 1320000 | 1275000 | 270000 | 480000 | 95000 | 430000 | 4504.5 | 96.59% | 2015-05-01 | 2016-07-15 | 0.05264 | 1.7269 | 0.27821 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
05 | SHOPP | 1C180 | SCR | 017 | SHOULDER WIDENING AND CONCRETE GUARDRAIL | 1.831 | SHOPP | 2012 | 2361 |  | X | X |  |  | 3558000 | 1693000 | E | 960000 | 3000 | 730000 | 143137 | 47.58% | 2014-05-26 | 2014-10-08 | 0 | 1.0239 | 0.02705 | 0.78008 | Caltrans | Caltrans | Caltrans | Caltrans
05 | SHOPP | 1C240 | SLO | 001 | INSTALL RUMBLE STRIP | 1.9395 | SHOPP | 2012 | 2377 | X |  |  |  |  | 2382000 | 1192000 | 281000 | 470000 | 3000 | 438000 | 0 | 50.04% | 2015-11-01 | 2016-06-01 | 0.99298 | 0.94272 | 0.00383 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
05 | SHOPP | 1C300 | MON | 001 | INSTALL RUMBLE STRIP | 1.5365 | SHOPP PA |  |  |  | X
05 | SHOPP | 1C310 | SCR | 001 | INSTALL RUMBLE STRIPS | 1.9856 | SHOPP | 2012 | 2381 | X |  | X |  |  | 607000 | 483000 | 110000 | 225000 | 3000 | 145000 | 0 | 79.57% | 2014-10-22 | 2015-04-01 | 0.3666 | 1.6007 | 0.01838 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
05 | SHOPP | 1C320 | SLO | 046 | INSTALL RUMBLE STRIPS | 0.49095 | SHOPP | 2012 | 2383 |  | X |  | X |  | 428000 | 292000 | 64000 | 154000 | 4000 | 70000 | 35195.17 | 68.22% | 2013-09-18 | 2013-12-02 | 0 | 0.06794 | 0.00788 | 0.41513 | Caltrans | Caltrans | Caltrans | Caltrans
05 | SHOPP | 1C330 | MON | 101 | CONSTRUCT MEDIAN BARRIER AND RUMBLE STRIPS | 2.6404 | SHOPP | 2012 | 2384 |  | X | X |  |  | 3150000 | 1267000 | 315000 | 460000 | 7000 | 485000 | 0 | 40.22% | 2014-05-07 | 2014-12-01 | 0 | 2.0841 | 0.03346 | 0.52285 | Caltrans | Caltrans | Caltrans | Caltrans
05 | SHOPP | 1C340 | SB | 101 | CONSTRUCT MEDIAN BARRIER AND RUMBLE STRIPS | 2.5878 | SHOPP | 2012 | 2385 |  | X | X |  |  | 1205000 | 955000 | 150000 | 400000 | 5000 | 400000 | 0 | 79.25% | 2014-04-14 | 2015-07-01 | 0 | 2.0785 | 0.02644 | 0.48292 | Caltrans | Caltrans | Caltrans | Caltrans
05 | SHOPP | 1C660 | MON | 198 | WIDEN SHOULDERS AND CORRECT SUPERELEVATION | 4.3416 | SHOPP PA
05 | SHOPP | 1C670 | SCR | 017 | SHOULDER WIDENING AND SOIL NAIL WALL | 4.0979 | SHOPP PA |  |  | X
05 | SHOPP | 1F030 | SCR | 129 | OVERLAY AND MBGR UPGRADES | 3.306 | SHOPP PA |  |  | X
05 | SHOPP | 1F080 | MON | 001 | CULVERT REHABILITATION OR REPLACEMENT | 2.3195 | SHOPP PA
05 | SHOPP | MINOR |  |  | SHOPP MINOR | 24.686 | MINOR
06 | SHOPP | 0E070 | TUL | 099 | PAVEMENT REHABILITATION | 1.3844 | SHOPP | 2010 | 6377 |  |  |  | X |  | 10517000 | 3403000 | E | 1550000 | 23000 | 1830000 | 1640760.64 | 32.36% | 2011-12-21 | 2013-07-07 | 0 | 0 | 0 | 1.3844 | Caltrans | Caltrans | Caltrans | Caltrans
06 | SHOPP | 0E040 | MAD | 099 | PAVEMENT REHABILITATION | 5.4866 | SHOPP | 2010 | 4326 |  |  |  | X |  | 33523000 | 3869000 | 304000 | 1695000 | 88000 | 1782000 | 2822547.19 | 11.54% | 2011-06-28 | 2013-12-03 | 0 | 0 | 0 | 5.4866 | Caltrans | Caltrans | Caltrans | Caltrans
06 | SHOPP | 33741 | TUL | 190 | PAVEMENT REHABILITATION | 0.11792 | SHOPP | 2010 | 6544 |  |  |  | X |  | N | 1482000 | N | 742000 | 47000 | 693000 | 1377693.19 | NA | 2012-06-20 | 2013-07-01 | 0 | 0 | 0 | 0.11792 | Caltrans | Caltrans | Caltrans | Caltrans
06 | SHOPP | 39460 | FRE | 269 | CONSTRUCT NEW BRIDGE & RAISE GRADE | 4.4565 | SHOPP | 2012 | 2184 | [5 empty] | 16295000 | 9000000 | 1700000 | 3000000 | 300000 | 4000000 | 96866.63 | 55.23% | 2017-01-15 | 2019-08-01 | 4.0095 | 0.41058 | 0.03635 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
06 | SHOPP | 41590 | KIN | 041 | AC OVERLAY AND WIDEN SHOULDER | 0.06877 | SHOPP | 2010 | 4248 | [5 empty] | 25627000 | 5988000 | 1128000 | 2038000 | 496000 | 2326000 | 6491662.52 | 23.37% | 2011-05-09 | 2012-07-11 | 0 | 0 | 0.03718 | 0.03159 | Caltrans | Caltrans | Caltrans | Caltrans
06 | SHOPP | 41600 | KIN | 041 | REHAB ROADWAY AND WIDEN SHOULDERS | 7.8325 | SHOPP | 2010 | 4275 | [5 empty] | 22705000 | 6916000 | 1293000 | 2074000 | 1092000 | 2457000 | 4901352.69 | 30.46% | 2012-04-06 | 2014-07-01 | 0 | 0 | 0.23104 | 7.6015 | Caltrans | Caltrans | Caltrans | Caltrans
06 | SHOPP | 43260 | FRE | 033 | BRIDGE REPLACEMENT | 2.5439 | SHOPP | 2012 | 1280 | X | X |  |  |  | 7265000 | 3070000 | 1132000 | 926000 | 169000 | 843000 | 1278763.95 | 42.26% | 2014-12-01 | 2016-04-01 | 0.00632 | 2.1999 | 0.32861 | 0.00916 | Caltrans | Caltrans | Caltrans | Caltrans
06 | SHOPP | 46060 | KER | 005 | REHABILITATE PAVEMENT | 0.17946 | SHOPP | 2008 | 3084 | [5 empty] | 16291000 | 3680000 | E | 700000 | 80000 | 2900000 | 1267896.52 | 22.59% | 2011-02-03 | 2013-04-01 | 0 | 0 | 0 | 0.17946 | Caltrans | Caltrans | Caltrans | Caltrans
06 | SHOPP | 46150 | TUL | 190 | AC OVERLAY, SHOULDER WIDENING, LEFT TURN CHANNELIZATION & UTIL RELOCAT | 7.8075 | SHOPP | 2012 | 6508 | X | X | X |  |  | 20000000 | 5462000 | 1211000 | 1378000 | 1391000 | 1482000 | 1192162.1 | 27.31% | 2014-09-01 | 2016-11-01 | 0.02456 | 4.3399 | 3.4069 | 0.03614 | Caltrans | Caltrans | Caltrans | Caltrans
06 | SHOPP | 46220 | KIN | 198 | REHAB 3 BRIDGE DECKS | 7.2223 | SHOPP | 2012 | 4340 | [5 empty] | 9743000 | 2395000 | 205000 | 1145000 | 17000 | 1028000 | 1035745.59 | 24.58% | 2013-06-03 | 2014-07-01 | 0 | 0.05654 | 0 | 7.1658 | Caltrans | Caltrans | Caltrans | Caltrans
06 | SHOPP | 47090 | MAD | 099 | 4F TO 6F | 8.5514 | STIP | 2012 | 5335 | X |  |  |  |  | 110000000 | 21150000 | 3150000 | 6000000 | 2000000 | 10000000 | 0 | 19.23% | 2016-05-01 | 2018-07-01 | 5.3586 | 3.1228 | 0.07003 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
06 | SHOPP | 47230 | FRE | 180 | REPLACE BRIDGE AND WIDEN SHOULDER | 0.06126 | SHOPP | 2008 | 2055 | [5 empty] | 3575000 | 2857000 | 409000 | 1412000 | 258000 | 778000 | 3357676.32 | 79.92% | 2010-10-12 | 2011-10-19 | 0 | 0 | 0.01592 | 0.04534 | Caltrans | Caltrans | Caltrans | Caltrans
06 | SHOPP | 0A970 | TUL | 099 | CONSTRUCT NEW FACILITES REST AREA | 0.70222 | SHOPP | 2010 | 6370 |  |  |  | X |  | 8961000 | 4160000 | 440000 | 2060000 | 2000 | 1658000 | 5308028.18 | 46.42% | 2011-04-06 | 2013-12-17 | 0 | 0 | 0 | 0.70222 | Caltrans | Caltrans | Caltrans | Caltrans
06 | SHOPP | 0A990 | KER | 005 | RESTORE SAFETY ROADSIDE REST AREA | 0.46565 | SHOPP | 2008 | 3093 | [5 empty] | 8150000 | 4172000 | 280000 | 2388000 | 33000 | 1471000 | 3212901.95 | 51.19% | 2010-10-11 | 2013-03-30 | 0 | 0 | 0 | 0.46565 | Caltrans | Caltrans | Caltrans | Caltrans
06 | SHOPP | 0C110 | FRE | 180 | BRAIDED RAMPS | 6.7423 | SHOPP | 2010 | 6276A |  |  |  | X |  | 51000000 | 10513000 | 1804000 | 5606000 | 103000 | 3000000 | 2906870.4 | 20.61% | 2012-01-12 | 2014-06-01 | 0 | 0.10296 | 0 | 6.6394 | Caltrans | Caltrans | Caltrans | Caltrans
06 | SHOPP | 0C130 | FRE | 033 | SEISMIC RESTORATION | 3.5991 | SHOPP | 2012 | 1243 | [5 empty] | 3455000 | 1399000 | 420000 | 519000 | 6000 | 454000 | 1433745.63 | 40.49% | 2013-01-15 | 2014-08-15 | 0 | 0 | 0.02246 | 3.5766 | Caltrans | Caltrans | Caltrans | Caltrans
06 | SHOPP | 0E310 | FRE | 041 | FREEWAY MAINTENANCE ACCESS | 0.01722 | SHOPP | 2010 | 1302 | [5 empty] | 2510000 | 635000 | 104000 | 266000 | 19000 | 246000 | 775158.17 | 25.3% | 2011-07-15 | 2012-06-08 | 0 | 0 | 0 | 0.01722 | Caltrans | Caltrans | Caltrans | Caltrans
06 | SHOPP | 0E330 | KER | 058 | FREEWAY MAINTENANCE ACCESS | 1.0771 | SHOPP | 2012 | 3440 | X |  |  |  |  | 1077000 | 610000 | 130000 | 275000 | 5000 | 200000 | 2064.18 | 56.64% | 2015-06-15 | 2016-07-15 | 0.10599 | 0.93885 | 0.03222 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
06 | SHOPP | 0E340 | KER | 099 | FREEWAY MAINTENANCE ACCESS | 1.2417 | SHOPP | 2012 | 3541 | X |  |  |  |  | 1287000 | 772000 | 167000 | 350000 | 5000 | 250000 | 1712.78 | 59.98% | 2015-06-15 | 2016-07-15 | 0.10972 | 1.0997 | 0.03222 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
06 | SHOPP | 0E971 | FRE | 041 | REPLACEMENT PLANTING | 0.26845 | SHOPP | 2010 | 2057A | [5 empty] | 355000 | 306000 | 20000 | 114000 | 2000 | 170000 | 392693.92 | 86.2% | 2012-03-19 | 2016-07-01 | 0 | 0 | 0 | 0.26845 | Caltrans | Caltrans | Caltrans | Caltrans
06 | SHOPP | 0F000 | TUL | 198 | WIDEN OFF RAMP AND CONSTRUCT RETAINING WALL | 0.05077 | SHOPP | 2010 | 6403 | [5 empty] | 1147000 | 709000 | 203000 | 221000 | 48000 | 237000 | 987045.25 | 61.81% | 2011-05-25 | 2012-12-03 | 0 | 0 | 0 | 0.05077 | Caltrans | Caltrans | Caltrans | Caltrans
06 | SHOPP | 0G270 | KER | 058 | INSTALL WINDSCREEN | 0.35956 | SHOPP | 2010 | 6332 |  |  |  | X |  | 3617000 | 1398000 | 171000 | 693000 | 7000 | 527000 | 385937.01 | 38.65% | 2012-08-14 | 2013-07-01 | 0 | 0 | 0 | 0.35956 | Caltrans | Caltrans | Caltrans | Caltrans
06 | SHOPP | 0G960 | FRE | 099 | CONSTRUCT CONCRETE CURB RAMPS | 0.01178 | SHOPP | 2010 | 6304 | [5 empty] | 1681000 | 783000 | 113000 | 409000 | 26000 | 235000 | 1143043.4 | 46.58% | 2011-03-07 | 2011-12-21 | 0 | 0 | 0.01178 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
06 | SHOPP | 0H100 | FRE | 168 | AC OVERLAY | 0.96616 | SHOPP | 2012 | 6311 |  |  |  | X |  | 3710000 | 662000 | 205000 | 231000 | 10000 | 216000 | 466062.79 | 17.84% | 2013-02-12 | 2014-01-02 | 0 | 0 | 0 | 0.96616 | Caltrans | Caltrans | Caltrans | Caltrans
06 | SHOPP | 0H170 | FRE | 180 | BRIDGE REPLACEMENT | 3.3772 | SHOPP | 2012 | 6328 | [5 empty] | 3754000 | 2649000 | 761000 | 1070000 | 107000 | 711000 | 1489527.7 | 70.56% | 2013-02-01 | 2014-08-15 | 0 | 0 | 0.02412 | 3.353 | Caltrans | Caltrans | Caltrans | Caltrans
06 | SHOPP | 0H180 | KER | 014 | BRIDGE REPLACEMENT (SCOUR) | 7.2058 | SHOPP | 2012 | 6330 | [5 empty] | 14693000 | 4792000 | 623000 | 1547000 | 36000 | 2586000 | 1937572.11 | 32.61% | 2013-08-01 | 2015-05-01 | 0 | 0.21525 | 0 | 6.9906 | Caltrans | Caltrans | Caltrans | Caltrans
06 | SHOPP | 0H200 | TUL | 201 | BRIDGE RAIL REPLACMENT | 3.6505 | SHOPP | 2012 | 6521 | [5 empty] | 9100000 | 6198000 | 1268000 | 2498000 | 516000 | 1916000 | 0 | 68.11% | 2016-07-26 | 2017-11-11 | 3.6505 | 0 | 0 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
06 | SHOPP | 0H630 | TUL | 198 | ADA COMPLIANCE UPGRADES | 6.0121 | SHOPP | 2012 | 6468 |  | X | X |  |  | 7248000 | 3643000 | 589000 | 1636000 | 244000 | 1174000 | 636313.51 | 50.26% | 2014-11-15 | 2016-06-01 | 0 | 5.3302 | 0.68183 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
06 | SHOPP | 0H640 | KER | 099 | ADA COMPLIANCE UPGRADES | 5.6898 | SHOPP | 2012 | 6485 |  | X | X |  |  | 12203000 | 3995000 | 479000 | 1888000 | 278000 | 1350000 | 524354.87 | 32.74% | 2014-11-15 | 2016-06-01 | 0 | 5.0981 | 0.5917 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
06 | SHOPP | 0H940 | FRE | 168 | REALIGN THE HORIZONTAL CURVE | 0.41166 | SHOPP | 2010 | 6359 |  |  |  | X |  | 3656000 | 1452000 | 424000 | 555000 | 144000 | 329000 | 1230154.37 | 39.72% | 2012-08-14 | 2013-08-01 | 0 | 0 | 0.12664 | 0.28502 | Caltrans | Caltrans | Caltrans | Caltrans
06 | SHOPP | 0J040 | KIN | 041 | CONSTRUCT LEFT-TURN LANES | 0.66875 | SHOPP | 2010 | 6456 |  |  |  | X |  | 1687000 | 1066000 | 403000 | 573000 | 10000 | 80000 | 1334860.7 | 63.19% | 2012-10-29 | 2013-08-01 | 0 | 0 | 0 | 0.66875 | Caltrans | Caltrans | Caltrans | Caltrans
06 | SHOPP | 0J050 | KIN | 043 | CHANNELIZE WITH SIGNALS | 0.40308 | SHOPP | 2010 | 6367 |  |  |  | X |  | 2298000 | 792000 | 263000 | 244000 | 114000 | 171000 | 735503.08 | 34.46% | 2012-05-17 | 2013-07-31 | 0 | 0 | 0.11529 | 0.28779 | Caltrans | Caltrans | Caltrans | Caltrans
06 | SHOPP | 0J520 | KER | 119 | WIDEN SHOULDERS | 0.08521 | SHOPP | 2010 | 6429 | [5 empty] | 4434000 | 1173000 | 224000 | 485000 | 180000 | 284000 | 1446852.99 | 26.45% | 2012-01-26 | 2013-02-01 | 0 | 0 | 0.00647 | 0.07874 | Caltrans | Caltrans | Caltrans | Caltrans
06 | SHOPP | 0J530 | TUL | 190 | INTERSECTION IMPROVEMENTS | 2.5671 | SHOPP | 2012 | 6428 |  | X | X |  |  | 1870000 | 830000 | 300000 | 250000 | 100000 | 180000 | 502278.93 | 44.39% | 2014-08-01 | 2015-10-01 | 0 | 1.7135 | 0.1649 | 0.68865 | Caltrans | Caltrans | Caltrans | Caltrans
06 | SHOPP | 0J920 | FRE | 145 | CONSTRUCT ROUNDABOUT | 1.9647 | SHOPP | 2012 | 6441 |  | X | X |  |  | 1602000 | 1301000 | 493000 | 407000 | 115000 | 286000 | 956922.21 | 81.21% | 2014-02-01 | 2014-09-01 | 0 | 0.88417 | 0.05881 | 1.0217 | Caltrans | Caltrans | Caltrans | Caltrans
06 | SHOPP | 0J930 | KER | 119 | INSTALL GUARDRAIL AND EXTEND CULVERTS | 1.7939 | SHOPP | 2012 | 6462 | [5 empty] | 2283000 | 2082000 | 474000 | 662000 | 227000 | 719000 | 602102.04 | 91.2% | 2013-10-15 | 2015-03-01 | 0 | 0.47751 | 0.11391 | 1.2025 | Caltrans | Caltrans | Caltrans | Caltrans
06 | SHOPP | 0K390 | KER | 058 | BRIDGE REPLACEMENT | 2.1661 | SHOPP | 2010 | 6459 |  |  |  | X |  | 3202000 | 1125000 | 243000 | 487000 | 5000 | 390000 | 811493.61 | 35.13% | 2012-12-20 | 2014-04-01 | 0 | 0 | 0.00136 | 2.1648 | Caltrans | Caltrans | Caltrans | Caltrans
06 | SHOPP | 0K460 | KER | 099 | BRIDGE REPLACEMENT | 4.5927 | SHOPP | 2012 | 6601 | X |  |  |  |  | 13822000 | 4884000 | 701000 | 2444000 | 113000 | 1626000 | 427.03 | 35.33% | 2016-06-01 | 2017-10-01 | 2.0577 | 2.4693 | 0.06576 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
06 | SHOPP | 0K540 | TUL | 063 | REALIGN INTERSECTION AND INSTALL SIGNAL | 0.32677 | SHOPP | 2010 | 6457 |  |  |  | X |  | 1701000 | 966000 | E | 531000 | 128000 | 307000 | 706891.24 | 56.79% | 2012-11-26 | 2013-09-01 | 0 | 0 | 0.05688 | 0.26989 | Caltrans | Caltrans | Caltrans | Caltrans
06 | SHOPP | 0K800 | FRE | 041 | SEISMIC RESTORATION | 1.4042 | SHOPP | 2012 | 6596 | [5 empty] | 4825000 | 4195000 | 456000 | 1589000 | 18000 | 2132000 | 6649.43 | 86.94% | 2016-11-01 | 2017-12-01 | 1.4042 | 0 | 0 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
06 | SHOPP | 0K810 | KER | 099 | SEISMIC RESTORATION | 1.87 | SHOPP | 2012 | 6605 | X |  |  |  |  | 7025000 | 3114000 | 280000 | 1314000 | 20000 | 1500000 | 3912.21 | 44.33% | 2016-10-12 | 2018-08-01 | 1.3108 | 0.54341 | 0.0158 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
06 | SHOPP | 0L180 | KER | 005 | INSTALL MEDIAN BARRIER | 0.26818 | SHOPP | 2010 | 6461 |  |  |  | X |  | 1492000 | 913000 | 152000 | 405000 | 19000 | 337000 | 681747.25 | 61.19% | 2011-10-26 | 2013-07-01 | 0 | 0 | 0 | 0.26818 | Caltrans | Caltrans | Caltrans | Caltrans
06 | SHOPP | 0L200 | MAD | 099 | INSTALL MEDIAN BARRIER | 0.02591 | SHOPP | 2010 | 6458 | [5 empty] | 1638000 | 1011000 | E | 543000 | 16000 | 452000 | 546459.49 | 61.72% | 2012-04-12 | 2012-07-24 | 0 | 0 | 0 | 0.02591 | Caltrans | Caltrans | Caltrans | Caltrans
06 | SHOPP | 0L220 | KER | 005 | INSTALL MEDIAN BARRIER | 0.12508 | SHOPP | 2010 | 6463 | [5 empty] | 1663000 | 873000 | 236000 | 424000 | 18000 | 195000 | 454194.23 | 52.5% | 2012-01-30 | 2012-06-19 | 0 | 0 | 0 | 0.12508 | Caltrans | Caltrans | Caltrans | Caltrans
06 | SHOPP | 0L340 | FRE | 168 | INTERSECTION IMPROVEMENT | 0.93697 | SHOPP | 2012 | 6623 | X |  |  |  |  | 2280000 | 1619000 | 542000 | 558000 | 181000 | 338000 | 53909.76 | 71.01% | 2016-01-15 | 2017-02-01 | 0.68344 | 0.20031 | 0.05322 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
06 | SHOPP | 0L390 | KER | 099 | RELOCATE RIGHT TURN LANE OF THE SB ONRAMP TO SR 99 | 2.0942 | SHOPP | 2012 | 6486 | [5 empty] | 1217000 | 1492000 | 428000 | 654000 | 3000 | 407000 | 507774.04 | 122.6% | 2013-07-01 | 2014-07-01 | 0 | 0.00777 | 0.00029 | 2.0861 | Caltrans | Caltrans | Caltrans | Caltrans
06 | SHOPP | 0L640 | KER | 099 | REPLACE EXISTING #2 & #3 LANE WITH CRCP & PLACE 10 FT PCC OUTSIDE | 7.9705 | SHOPP | 2010 | 6506 | [5 empty] | 80025000 | 5104000 | E | 1100000 | 4000 | 4000000 | 2098841.94 | 6.378% | 2012-01-18 | 2014-08-05 | 0 | 0 | 0 | 7.9705 | Caltrans | Caltrans | Caltrans | Caltrans
06 | SHOPP | 0L720 | KER | 058 | INSTALL CONCRETE MEDIAN BARRIER | 0.07459 | SHOPP | 2010 | 6499 | [5 empty] | 1455000 | 691000 | E | 504000 | 2000 | 185000 | 448382.31 | 47.49% | 2012-04-10 | 2012-09-05 | 0 | 0 | 0 | 0.07459 | Caltrans | Caltrans | Caltrans | Caltrans
06 | SHOPP | 0L900 | KER | 184 | VERTICAL CURVE IMPROVEMENTS | 0.04 | SHOPP | 2010 | 6604 | [5 empty] | 806000 | 475000 | E | 365000 | 9000 | 101000 | 105603.36 | 58.93% | 2012-05-09 | 2013-01-15 | 0 | 0 | 0.01111 | 0.02889 | Caltrans | Caltrans | Caltrans | Caltrans
06 | SHOPP | 0M050 | FRE | 168 | REALIGN CURVE | 3.5777 | SHOPP | 2012 | 6502 |  | X | X |  |  | 2900000 | 2270000 | 690000 | 880000 | 160000 | 540000 | 351450.63 | 78.28% | 2015-01-01 | 2015-07-15 | 0 | 3.064 | 0.51378 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
06 | SHOPP | 0M250 | FRE | 198 | BRIDGE DECK REPLACEMENT | 1.2169 | SHOPP | 2012 | 6574 | X |  |  |  |  | 2115000 | 1645000 | 245000 | 617000 | 17000 | 766000 | 11646.07 | 77.78% | 2016-03-01 | 2017-02-01 | 0.46265 | 0.74166 | 0.01256 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
06 | SHOPP | 0M260 | KER | 058 | REPLACE DECK | 1.8513 | SHOPP | 2012 | 6588 | [5 empty] | 3002000 | 1275000 | E | 752000 | 6000 | 517000 | 9923.8 | 42.47% | 2015-10-01 | 2016-07-01 | 0 | 1.8202 | 0.0311 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
06 | SHOPP | 0M370 | KIN | 043 | ROUNDABOUT | 3.0071 | SHOPP | 2012 | 6619 | [5 empty] | 2371000 | 1843000 | 609000 | 527000 | 166000 | 541000 | 0 | 77.73% | 2016-07-01 | 2017-10-01 | 2.7638 | 0.15642 | 0.08689 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
06 | SHOPP | 0M420 | FRE | 180 | CONSTRUCT CONCRETE GUARD RAIL | 1.4693 | SHOPP | 2012 | 6547 |  |  |  | X |  | 1101000 | 604200 | 89000 | 240000 | 4200 | 271000 | 514063.46 | 54.88% | 2013-04-04 | 2014-04-04 | 0 | 0 | 0.02067 | 1.4487 | Caltrans | Caltrans | Caltrans | Caltrans
06 | SHOPP | 0M510 | KER | VAR | PLACE HMA ON PAVEMENT | 0.01459 | SHOPP | 2010 | 6484 | [5 empty] | 4620000 | 750000 | 15000 | 291000 | 4000 | 440000 | 618295.95 | 16.23% | 2011-03-29 | 2012-07-23 | 0 | 0 | 0 | 0.01459 | Caltrans | Caltrans | Caltrans | Caltrans
06 | SHOPP | 0M730 | FRE | 005 | INSTALL MEDIAN BARRIER | 0.42704 | SHOPP | 2010 | 6507 |  |  |  | X |  | 2803000 | 679000 | E | 363000 | 58000 | 258000 | 342055.47 | 24.22% | 2012-07-12 | 2013-08-01 | 0 | 0 | 0.08849 | 0.33855 | Caltrans | Caltrans | Caltrans | Caltrans
06 | SHOPP | 0M800 | MAD | 099 | INSTALL MEDIAN BARRIER | 0.71676 | SHOPP | 2012 | 6522 | [5 empty] | 680000 | 638000 | E | 360000 | 8000 | 270000 | 240938.33 | 93.82% | 2013-02-08 | 2013-05-03 | 0 | 0 | 0.01714 | 0.69962 | Caltrans | Caltrans | Caltrans | Caltrans
06 | SHOPP | 0M820 | FRE | 041 | WET WEATHER IMPROVEMENTS W/CONCRETE BARRIERS | 1.273 | SHOPP | 2012 | 6573 |  | X | X |  |  | 1446000 | 742000 | 138000 | 322000 | 2000 | 280000 | 174572.32 | 51.31% | 2014-07-15 | 2015-07-15 | 0 | 1.2638 | 0.00913 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
06 | SHOPP | 0N070 | KER | 005 | MAINTENANCE | 0.44922 | SHOPP | 2010 | 6602 |  |  |  | X |  | 2402000 | 532000 | 4000 | 150000 | 3000 | 375000 | 64676.31 | 22.15% | 2012-04-23 | 2013-08-01 | 0 | 0 | 0 | 0.44922 | Caltrans | Caltrans | Caltrans | Caltrans
06 | SHOPP | 0N180 | KIN | 198 | INSTALL MEDIAN BARRIER | 1.007 | SHOPP | 2012 | 6622 | [5 empty] | 3400000 | 975000 | 224000 | 433000 | 13000 | 305000 | 0 | 28.68% | 2016-01-15 | 2016-07-15 | 1.007 | 0 | 0 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
06 | SHOPP | 0N200 | MAD | 099 | INSTALL MEDIAN BARRIER | 2.3986 | SHOPP | 2012 | 6603 |  | X |  | X |  | 2200000 | 855000 | E | 530000 | 10000 | 315000 | 63178.65 | 38.86% | 2013-12-15 | 2014-05-16 | 0 | 0.79999 | 0.00261 | 1.596 | Caltrans | Caltrans | Caltrans | Caltrans
06 | SHOPP | 0N360 | KER | 005 | REPLACE AC PANELS WITH PCC | 1.0149 | SHOPP | 2012 | 6571 |  | X |  |  |  | 1764000 | 735000 | 18000 | 314000 | 3000 | 400000 | 76267.27 | 41.67% | 2013-12-04 | 2015-07-01 | 0 | 0.30575 | 0.02226 | 0.68685 | Caltrans | Caltrans | Caltrans | Caltrans
06 | SHOPP | 0N380 | KER | 178 | CONSTRUCT RETAINING STRUCTURES | 0.84253 | SHOPP | 2012 | 6551 |  |  |  | X |  | 1182000 | 495000 | 48000 | 276000 | 9000 | 162000 | 178541.16 | 41.88% | 2013-07-01 | 2013-11-01 | 0 | 0.04136 | 0.04413 | 0.75704 | Caltrans | Caltrans | Caltrans | Caltrans
06 | SHOPP | 0N390 | TUL | 245 | CONSTRUCT ROCK GABION WALL | 0.62234 | SHOPP | 2012 | 6569 | [5 empty] | 426000 | 576000 | 128000 | 211000 | 127000 | 110000 | 268952.06 | 135.2% | 2013-08-15 | 2014-07-15 | 0 | 0.09167 | 0.03507 | 0.4956 | Caltrans | Caltrans | Caltrans | Caltrans
06 | SHOPP | 0N401 | KER | 058 | CONSTRUCT ROCK SLOPE PROTECTION | 0.45426 | SHOPP | 2012 | 6647 |  |  |  | X |  | 489000 | 118000 | 4000 | 41000 | 1000 | 72000 | 0 | 24.13% | 2013-07-01 | 2014-01-02 | 0 | 0.01281 | 0 | 0.44145 | Caltrans | Caltrans | Caltrans | Caltrans
06 | SHOPP | 0N850 | TUL | 099 | PAVEMENT REHAB / AC OVERLAY (RAC) | 0.48071 | SHOPP | 2010 | 6572 |  |  |  | X |  | 905000 | 353000 | E | 150000 | 3000 | 200000 | 168327.23 | 39.01% | 2012-10-12 | 2013-11-01 | 0 | 0 | 0 | 0.48071 | Caltrans | Caltrans | Caltrans | Caltrans
06 | SHOPP | 0N960 | KER | 204 | BRIDGE DECK REHAB, JOINT SEAL REPLACEMENTS, PAINTING | 2.1652 | SHOPP | 2012 | 6587 | X |  |  |  |  | 8656000 | 1554000 | 145000 | 628000 | 5000 | 776000 | 2553.69 | 17.95% | 2015-07-01 | 2016-07-01 | 0.53058 | 1.6126 | 0.02203 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
06 | SHOPP | 0N990 | FRE | 041 | BRIDGE SCOUR | 4.739 | SHOPP | 2012 | 6598 | X |  |  |  |  | 2390000 | 1065000 | 164000 | 500000 | 19000 | 382000 | 4648.59 | 44.56% | 2015-12-01 | 2017-05-01 | 2.6521 | 1.9363 | 0.03441 | 0.11616 | Caltrans | Caltrans | Caltrans | Caltrans
06 | SHOPP | 0P140 | KER | 005 | GRIND PAVEMENT & OVERLAY CAPM | 1.3311 | SHOPP | 2012 | 6589 |  | X | X |  |  | 5199000 | 1184000 | E | 487000 | 14000 | 683000 | 20157.06 | 22.77% | 2014-05-01 | 2014-12-01 | 0 | 0.58436 | 0.03562 | 0.71109 | Caltrans | Caltrans | Caltrans | Caltrans
06 | SHOPP | 0P150 | KIN | 198 | OVERLAY 2R | 3.8086 | SHOPP | 2012 | 6590 | [5 empty] | 11337000 | 2556000 | E | 1062000 | 4000 | 1490000 | 0 | 22.55% | 2015-01-15 | 2015-09-01 | 0 | 3.795 | 0.01362 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
06 | SHOPP | 0P160 | KIN | 198 | OVERLAY CAPM | 2.8831 | SHOPP | 2012 | 6592 |  | X | X |  |  | 7544000 | 2112000 | E | 804000 | 4000 | 1304000 | 0 | 28% | 2014-03-15 | 2015-02-01 | 0 | 1.4905 | 0 | 1.3926 | Caltrans | Caltrans | Caltrans | Caltrans
06 | SHOPP | 0P170 | TUL | 099 | OVERLAY 2R | 2.2795 | SHOPP | 2012 | 6593 |  | X | X |  |  | 6734000 | 1243000 | E | 647000 | 15000 | 581000 | 0 | 18.46% | 2014-08-01 | 2015-03-02 | 0 | 2.2005 | 0.07895 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
06 | SHOPP | 0P270 | KER | 043 | ADA CURB RAMPS | 1.9741 | SHOPP | 2012 | 6645 |  | X | X |  |  | 1461000 | 922000 | Q | 571000 | 80000 | 271000 | 227893.93 | 63.11% | 2014-08-01 | 2015-02-01 | 0 | 1.816 | 0.11609 | 0.04203 | Caltrans | Caltrans | Caltrans | Caltrans
06 | SHOPP | 0P290 | KER | 155 | CONSTRUCT ROUNDABOUT | 1.248 | SHOPP PA
06 | SHOPP | 0P300 | KER | 099 | WIDEN N/B INSIDE SHOULDER & INSTALL RUMBLE STRIP | 1.1099 | SHOPP | 2012 | 6637 |  | X | X |  |  | 1444000 | 689000 | E | 427000 | 13000 | 249000 | 18485.97 | 47.71% | 2014-06-10 | 2014-12-01 | 0 | 1.0537 | 0.05619 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
06 | SHOPP | 0P560 | KER | 058 | WIDEN SHOULDERS & INSTALL RUMBLE STRIPS | 3.068 | SHOPP | 2012 | 6638 |  | X | X |  |  | 2255000 | 1320000 | E | 680000 | 143000 | 497000 | 0 | 58.54% | 2014-08-01 | 2015-09-01 | 0 | 2.9034 | 0.16466 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
06 | SHOPP | 0P590 | TUL | 190 | CONSTRUCT ROUNDABOUT | 3.19 | SHOPP PA
06 | SHOPP | 0P840 | KER | 223 | WIDEN SHOULDERS & INSTALL RUMBLE STRIPS | 2.3588 | SHOPP | 2012 | 6646 |  | X | X |  |  | 3656000 | 1261000 | E | 737000 | 27000 | 497000 | 0 | 34.49% | 2014-08-01 | 2015-09-15 | 0 | 2.2768 | 0.08208 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
06 | SHOPP | 0P980 | FRE | 168 | CONSTRUCT MEDIAN BARRIER | 1.31 | SHOPP PA |  |  |  | X | X
06 | SHOPP | MINOR |  |  | SHOPP MINOR | 34.3269 | MINOR
07 | SHOPP | 12093 | LA | 710 | INSTALL COMMUNICATION SYSTEM | 0.78468 | SHOPP | 2004 | 3244 | [5 empty] | 3541000 | 1500000 | 1500000 | F | F | F | 2035022.565 | 42.36% | 2005-11-23 | 2007-07-30 | 0 | 0 | 0 | 0.78468 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 12993 | LA | 210 | CLOSED CIRCUIT TELEVISION SYSTEM | 0.02484 | SHOPP | 2006 | 0760A | [5 empty] | 10322000 | 1636000 | 1636000 | F | F | F | 5752200.5367 | 15.85% | 2007-07-06 | 2010-02-04 | 0 | 0 | 0 | 0.02484 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 13820 | LA | 047 | REPLACE STEEL BRIDGE WITH CIP | 30.5726 | SHOPP | 2010 | 0444E | [5 empty] | 307200000 | 32567000 | 7150000 | 14390000 | 2234000 | 8793000 | 21098207.24 | 10.6% | 2011-06-30 | 2016-10-20 | 0 | 0.09188 | 0.67354 | 29.8072 | Caltrans | Local | Local | Caltrans
07 | SHOPP | 16681 | LA | 010 | REHABILITATE ROADWAY AND RAMPS *INCL= 166801 & 212201; POR 1668U1 | 0.46204 | SHOPP | 2006 | 0262P | [5 empty] | 186718000 | 3589000 | 3589000 | F | F | F | 31408919.3 | 1.922% | 2008-10-06 | 2013-04-30 | 0 | 0 | 0 | 0.46204 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 17970 | LA | 710 | HIGHWAY PLANTING AND IRRIGATION | 0.37613 | SHOPP | 2008 | 2131 | [5 empty] | 1901000 | 955000 | 20000 | 450000 | 5000 | 480000 | 787562.13 | 50.24% | 2009-07-09 | 2015-02-18 | 0 | 0 | 0 | 0.37613 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 18270 | LA | 134 | PLANTING AND IRRIGATION | 0.13944 | SHOPP | 2006 | 2158 | [5 empty] | 2514000 | 1146000 | 1146000 | F | F | F | 1221197.31 | 45.58% | 2007-08-07 | 2012-08-27 | 0 | 0 | 0 | 0.13944 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 18312 | LA | 710 | LANDSCAPE | 1.2425 | SHOPP | 2012 | 2163A |  | X | X |  |  | 1934000 | 803000 | 1000 | 400000 | 2000 | 400000 | 298687.3007 | 41.52% | 2015-03-27 | 2016-07-14 | 0 | 0.48008 | 0.0058 | 0.75665 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 18410 | LA | 005 | UPGRADE MEDIAN CONCRETE BARRIER | 0.19978 | SHOPP | 2008 | 2172 |  |  |  | X |  | 6753000 | 2668000 | 10000 | 1424000 | 59000 | 1175000 | 3742720.89 | 39.51% | 2011-02-08 | 2013-10-31 | 0 | 0 | 0 | 0.19978 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 19310 | LA | 005 | REHABILITATE PAVEMENT | 0.07871 | SHOPP | 2004 | 2269 | [5 empty] | 49556000 | 5343000 | 5343000 | F | F | F | 11171699.05 | 10.78% | 2005-11-08 | 2011-06-28 | 0 | 0 | 0 | 0.07871 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 20211 | LA | 710 | LONG LIFE PAVEMENT & WIDEN BRIDGES | 35.2673 | SHOPP | 2010 | 4137 | [5 empty] | 220000000 | 31200000 | 5500000 | 14700000 | 200000 | 10800000 | 20115095.66 | 14.18% | 2012-04-04 | 2015-09-29 | 0 | 0 | 1.017 | 34.2503 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 20212 | LA | 710 | LONG LIFE PAVEMENT & WIDEN BRIDGES | 12.4366 | SHOPP | 2012 | 4137A |  | X | X |  |  | 124200000 | 26500000 | 500000 | 11700000 | 2600000 | 11700000 | 10438074.34 | 21.34% | 2014-10-29 | 2017-11-27 | 0 | 6.8567 | 5.58 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 21592 | LA | 005 | ROADWAY WIDENING (SEG 2) | 10.6439 | STIP | 2012 | 2808 |  | X | X |  |  | 381859000 | 67402000 | 7209000 | 32417000 | 8086000 | 19690000 | 30244789.3096 | 17.65% | 2014-08-06 | 2017-03-21 | 0 | 5.5838 | 5.0602 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 21595 | LA | 005 | ROADWAY WIDENING & STRIPING (SEG 5) | 22.5425 | STIP | 2012 | 4156 | [5 empty] | 177572000 | 37820000 | 1924000 | 14784000 | 5137000 | 15975000 | 13397692.9239 | 21.3% | 2013-09-17 | 2016-12-30 | 0 | 0.79834 | 3.3102 | 18.434 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 21740 | LA | 005 | WIDEN RAMP | 0.84143 | SHOPP | 2006 | 2827 | [5 empty] | 7426000 | 1327000 | 1327000 | F | F | F | 4184145.58 | 17.87% | 2008-08-14 | 2010-07-01 | 0 | 0 | 0 | 0.84143 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 22222 | LA | 010 | BRIDGE RESTORATION COLLECTORS AND ON/OFF RAMPS | 0.22515 | SHOPP | 2006 | 2959A | [5 empty] | 29210000 | 5126000 | 5126000 | F | F | F | 7942867.96 | 17.55% | 2007-04-27 | 2009-09-17 | 0 | 0 | 0 | 0.22515 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 22820 | VEN | 001 | STRUCTURE (SEAWALL) RESTORATION | 6.2768 | SHOPP | 2010 | 3036 |  |  |  | X |  | 14330000 | 4577000 | E | 2134000 | 129000 | 2314000 | 2470950.28 | 31.94% | 2013-01-07 | 2014-03-04 | 0 | 0 | 0.07156 | 6.2052 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 23961 | LA | 138 | RECONSTRUCT INTERSECTION | 0.57459 | SHOPP | 2006 | 4058 | [5 empty] | 15435000 | 4132000 | 4132000 | F | F | F | 6659794.78 | 26.77% | 2008-01-15 | 2010-08-19 | 0 | 0 | 0.37349 | 0.2011 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 24060 | LA | 105 | GROUNDWATER PIPING | 2.1769 | PARTNERSHIP |  |  | X
07 | SHOPP | 24130 | LA | 405 | WIDEN RC SLAB | 4.3528 | SHOPP | 2008 | 3348 |  |  |  | X |  | 25211000 | 13500000 | 742000 | 6015000 | 424000 | 6319000 | 10375783.04 | 53.55% | 2011-05-31 | 2013-10-25 | 0 | 0 | 0.3427 | 4.0101 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 24540 | LA | 010 | INTERCHANGE IMPROVEMENTS | 17.2085 | SHOPP | 2010 | 3529 |  |  |  | X |  | 66000000 | 12760000 | 1430000 | 5060000 | 1210000 | 5060000 | 3125991.2 | 19.33% | 2012-02-28 | 2014-06-20 | 0 | 0 | 2.2997 | 14.9088 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 25050 | LA | 605 | INST MET BEAM GUARDRAIL | 2.1755 | SHOPP | 2010 | 3661 | [5 empty] | 3966000 | 2098000 | 52000 | 818000 | 33000 | 1195000 | 755711.96 | 52.9% | 2012-07-05 | 2014-10-14 | 0 | 0 | 0.00179 | 2.1737 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 25130 | LA | 060 | GRIND AND REPLACE CONCRETE PAVEMENT | 0.13886 | SHOPP | 2010 | 3752 | [5 empty] | 27000000 | 4010000 | E | 1000000 | 10000 | 3000000 | 1103517.62 | 14.85% | 2011-05-02 | 2013-02-15 | 0 | 0.00464 | 0.00109 | 0.13313 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 25150 | VEN | 101 | REPLACE PCC SLABS COLD PLANE AC PAVEMENT AND REPLACE WITH | 0.08342 | SHOPP | 2010 | 3706 | [5 empty] | 57000000 | 6710000 | E | 1000000 | 10000 | 5700000 | 3348443.12 | 11.77% | 2011-02-02 | 2012-06-22 | 0 | 0 | 0.0015 | 0.08192 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 25180 | VEN | 101 | PLACE HOT MIX ASPHALT | 0.37297 | SHOPP | 2010 | 3710 | [5 empty] | 55000000 | 5279000 | E | 1000000 | 34000 | 4245000 | 3909694.99 | 9.598% | 2011-02-24 | 2013-03-20 | 0 | 0 | 0.00299 | 0.36998 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 25190 | VEN | 101 | PAVEMENT REHABILITATION | 5.5338 | SHOPP | 2012 | 3711 |  | X | X |  |  | 10720000 | 2496000 | 240000 | 1123000 | 10000 | 1123000 | 20330.58 | 23.28% | 2014-02-06 | 2015-03-27 | 0 | 3.0809 | 0.02696 | 2.4259 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 25200 | LA | 405 | SLAB REPLACEMENT. GRINDING, OVERLAY | 9.5174 | SHOPP | 2010 | 3712 | [5 empty] | 42800000 | 5520000 | E | 1000000 | 20000 | 4500000 | 1180960.53 | 12.9% | 2013-05-31 | 2015-07-21 | 0 | 0 | 0 | 9.5174 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 25230 | LA | 057 | PAVEMENT REHABILITATION | 0.71086 | SHOPP | 2010 | 3722 | [5 empty] | 20000000 | 3510000 | E | 1000000 | 10000 | 2500000 | 1201235.35 | 17.55% | 2011-01-11 | 2011-08-22 | 0 | 0.05477 | 0.02804 | 0.62805 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 25250 | LA | 005 | PLACE RUBBERIZED HMA TYPE G AND REPLACE CONCRETE PAVEMENT | 0.51303 | SHOPP | 2008 | 3724 | [5 empty] | 22100000 | 7020000 | E | 1500000 | 10000 | 5510000 | 1631414.29 | 31.76% | 2011-01-19 | 2013-02-28 | 0 | 0 | 0.01658 | 0.49645 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 25261 | LA | 005 | ROADWAY REHABILITATION *SPLIT FR 252601 | 4.1945 | SHOPP | 2010 | 3725A |  |  |  | X |  | 12100000 | 2420000 | E | 810000 | 10000 | 1600000 | 928427.4555 | 20% | 2012-12-12 | 2014-01-21 | 0 | 0 | 0.02275 | 4.1717 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 25262 | LA | 005 | ROADWAY REHABILITATION *SPLIT FR 252601 | 7.6636 | SHOPP | 2012 | 3725B |  | X | X |  |  | 78200000 | 15568000 | E | 6410000 | 20000 | 9138000 | 1246598.4678 | 19.91% | 2015-06-30 | 2016-09-27 | 0 | 7.635 | 0.02861 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 25263 | LA | 005 | ROADWAY REHABILITATION *SPLIT FR 252601 | 7.309 | SHOPP | 2010 | 3725C |  |  |  | X |  | 12000000 | 2440000 | E | 906000 | 34000 | 1500000 | 683145.4267 | 20.33% | 2013-05-16 | 2014-06-18 | 0 | 0 | 0.02544 | 7.2836 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 25280 | LA | 005 | REHABILITATE PAVEMENT | 24.9986 | SHOPP | 2010 | 3730 | [5 empty] | 130110000 | 13520000 | 20000 | 3300000 | 200000 | 10000000 | 3086300.27 | 10.39% | 2012-01-12 | 2014-07-16 | 0 | 0 | 0.41563 | 24.583 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 25330 | LA | 060 | REPLACE PAVEMENT | 0.18912 | SHOPP | 2008 | 3736 | [5 empty] | 25999000 | 5553000 | E | 2667000 | 30000 | 2856000 | 4176964.82 | 21.36% | 2010-10-14 | 2012-11-14 | 0 | 0 | 0 | 0.18912 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 25350 | LA | 005 | UPGRADE MEDIAN BARRIER | 1.2452 | SHOPP | 2010 | 3738 |  |  |  | X |  | 11005000 | 5535000 | E | 3000000 | 35000 | 2500000 | 3248737.36 | 50.3% | 2011-12-23 | 2013-07-23 | 0 | 0.00803 | 0.02902 | 1.2081 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 25380 | LA | 210 | REHABILITATE CONCRETE | 0.09108 | SHOPP | 2008 | 3740 | [5 empty] | 46918000 | 10160000 | E | 2000000 | 10000 | 8150000 | 3546697.12 | 21.65% | 2010-11-18 | 2012-09-06 | 0 | 0 | 0.09108 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 25490 | LA | 014 | PCC REPLACE, GRIND, COLD PLANE | 1.3365 | SHOPP | 2010 | 3756 | [5 empty] | 19320000 | 3120000 | E | 600000 | 20000 | 2500000 | 712497.83 | 16.15% | 2012-02-10 | 2013-06-21 | 0 | 0 | 0.01383 | 1.3227 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 25610 | LA | 110 | INSTALL METAL BEAM GUARD RAIL | 0.23568 | SHOPP | 2008 | 3780 | [5 empty] | 3377000 | 1455000 | 2000 | 937000 | 9000 | 507000 | 2220701.32 | 43.09% | 2010-11-10 | 2013-02-15 | 0 | 0 | 0.00147 | 0.23421 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 25840 | LA | 005 | STORM WATER MITIGATION (TRASH TMDL) | 5.4244 | SHOPP | 2012 | 3858 |  | X | X |  |  | 12125000 | 3638000 | 897000 | 1310000 | 121000 | 1310000 | 0 | 30% | 2014-03-14 | 2014-12-16 | 0 | 3.6269 | 0.0247 | 1.7728 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 25870 | LA | 010 | SOIL STABILIZATION & REVEGETATION | 1.1205 | SHOPP | 2012 | 3865 |  |  |  | X |  | 500000 | 653000 | 93000 | 200000 | 10000 | 350000 | 374225.69 | 130.6% | 2013-03-08 | 2014-02-07 | 0 | 0 | 0 | 1.1205 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 25880 | LA | 005 | SOIL STABILIZATION & REVEGETATION | 2.035 | SHOPP | 2012 | 3866 |  |  |  | X |  | 2600000 | 1375000 | 246000 | 495000 | 15000 | 619000 | 455832.64 | 52.88% | 2013-04-26 | 2014-02-27 | 0 | 0 | 0 | 2.035 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 25892 | LA | 060 | CONSTRUCT AUSTIN VAULT SAND FILTERS | 0.17403 | SHOPP | 2008 | 3867B | [5 empty] | 4999000 | 1406000 | 45000 | 604000 | 2000 | 755000 | 1424948.4532 | 28.13% | 2009-11-25 | 2012-11-27 | 0 | 0 | 0 | 0.17403 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 25893 | LA | 101 | SAND FILTERS & INFILTRATION DEVICES | 5.2079 | SHOPP | 2010 | 3867 | [5 empty] | 15000000 | 7269000 | 210000 | 3527000 | 7000 | 3525000 | 2459323.4436 | 48.46% | 2013-03-05 | 2015-07-31 | 0 | 0 | 0 | 5.2079 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 25901 | LA | 710 | CONSTUCTION OF SAND FILTERS AND SINFILTRATION DEVICES | 6.1369 | SHOPP | 2012 | 3868 | [5 empty] | 10950000 | 3205200 | 302100 | 1356000 | 36600 | 1510500 | 385706.476 | 29.27% | 2013-09-30 | 2014-08-01 | 0 | 0.52637 | 0.02704 | 5.5835 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 25902 | LA | 005 | CONSTUCTION OF SAND FILTERS AND SINFILTRATION DEVICES | 6.187 | SHOPP | 2012 | 3868 |  | X | X |  |  | 25450000 | 7478800 | 704900 | 3164000 | 85400 | 3524500 | 790606.384 | 29.39% | 2014-09-19 | 2015-07-23 | 0 | 6.1624 | 0.02457 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 25910 | LA | 090 | SAND FILTERS & INFILTRATION DEVICES | 1.7653 | SHOPP | 2010 | 3869 | [5 empty] | 5385000 | 1576000 | 157000 | 626000 | 10000 | 783000 | 777444.83 | 29.27% | 2012-12-12 | 2014-11-24 | 0 | 0 | 0 | 1.7653 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 25920 | LA | 010 | SAND FILTERS & INFILTRATION DEVICES | 2.6313 | SHOPP | 2012 | 3870 | [5 empty] | 5654000 | 1409000 | 109000 | 640000 | 10000 | 650000 | 101634.34 | 24.92% | 2013-09-06 | 2014-08-07 | 0 | 0.09483 | 0.00512 | 2.5313 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 26010 | LA | 091 | REPLACE BRIDGE RAIL | 0.13946 | SHOPP | 2010 | 3913 | [5 empty] | 2101000 | 1143000 | E | 492000 | 5000 | 646000 | 901500.65 | 54.4% | 2011-11-30 | 2012-11-21 | 0 | 0 | 0 | 0.13946 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 26040 | LA | 039 | BRIDGE SCOUR MITIGATION | 3.0387 | SHOPP | 2012 | 3917 | [5 empty] | 6315000 | 3360000 | 300000 | 1850000 | 10000 | 1200000 | 1088461.5 | 53.21% | 2016-04-26 | 2018-10-15 | 0 | 3.0245 | 0.01411 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 26050 | LA | 091 | STRUCTURE REHABILITATION | 1.3812 | SHOPP | 2010 | 3922 |  |  |  | X |  | 4849000 | 1440000 | E | 700000 | 10000 | 730000 | 633896.95 | 29.7% | 2012-02-02 | 2013-07-15 | 0 | 0 | 0 | 1.3812 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 26110 | LA | 001 | SEISMIC RETROFIT BRIDGE COLUMN | 0.32951 | SHOPP | 2010 | 3927 | [5 empty] | 3473000 | 1560000 | E | 764000 | 16000 | 780000 | 1352306.45 | 44.92% | 2011-08-04 | 2012-05-16 | 0 | 0 | 0 | 0.32951 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 26470 | LA | 105 | REPLACE JOINT SEALS | 1.5914 | SHOPP | 2010 | 3965 |  |  |  | X |  | 5032000 | 2105000 | E | 1261000 | 10000 | 834000 | 1195443.56 | 41.83% | 2011-06-28 | 2014-03-12 | 0 | 0 | 0 | 1.5914 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 26560 | LA | 138 | WIDEN ROADWAY AND PAVE SHOULDERS | 6.3851 | SHOPP | 2012 | 3978 |  | X | X |  |  | 21900000 | 8400000 | 900000 | 3700000 | 500000 | 3300000 | 656738.91 | 38.36% | 2014-08-21 | 2016-09-01 | 0 | 3.7553 | 2.6298 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 26590 | LA | 101 | UPGRADE BRIDGE RAILS | 2.0711 | SHOPP | 2012 | 3981 |  |  |  | X |  | 3241000 | 2116000 | 632000 | 970000 | 4000 | 510000 | 1632829.68 | 65.29% | 2013-06-20 | 2014-01-22 | 0 | 0 | 0 | 2.0711 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 26610 | LA | 134 | INSTALL MBGR | 3.7961 | SHOPP | 2010 | 3984 |  |  |  | X |  | 5098000 | 2210000 | E | 1000000 | 10000 | 1200000 | 1066057.5 | 43.35% | 2013-01-22 | 2014-03-28 | 0 | 0.01219 | 0.01123 | 3.7727 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 26690 | LA | 002 | GORE AREA CLEAN-UP/UPGRADES (CURE) | 1.0157 | SHOPP | 2010 | 4009 |  |  |  | X |  | 3815000 | 1334000 | E | 547000 | 27000 | 760000 | 978309.07 | 34.97% | 2012-04-19 | 2013-11-14 | 0 | 0 | 0.03648 | 0.97923 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 26700 | LA | 210 | FREEWAY MAINTENANCE ACCESS | 1.1159 | SHOPP | 2010 | 4010 |  |  |  | X |  | 1502000 | 1000000 | 30000 | 400000 | 30000 | 540000 | 522660.31 | 66.58% | 2012-03-27 | 2013-08-30 | 0 | 0 | 0 | 1.1159 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 26750 | LA | 010 | INSTALL NEW MBGR/CONCRETE RAILING | 4.4678 | SHOPP | 2010 | 4018 |  |  |  | X |  | 11379000 | 3315000 | E | 1591000 | 67000 | 1657000 | 1236640.26 | 29.13% | 2012-12-21 | 2013-11-08 | 0 | 0 | 0.06934 | 4.3984 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 27240 | LA | 005 | STORM WATER SOURCE CONTROL | 1.1556 | SHOPP | 2012 | 4060 | [5 empty] | 2033000 | 925000 | 75000 | 390000 | C | 460000 | 174252.25 | 45.5% | 2013-11-13 | 2017-11-22 | 0 | 0.32931 | 0 | 0.82628 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 27310 | LA | 110 | STRUCTURE REHABILITATION | 1.2811 | SHOPP | 2012 | 4074 |  | X | X |  |  | 9135000 | 3239000 | E | 1750000 | 60000 | 1429000 | 606205.65 | 35.46% | 2015-02-25 | 2016-11-08 | 0 | 1.2638 | 0.01732 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 27340 | LA | 134 | BRIDGE RAIL REPLACEMENT *NOT PROGRAMMED | 2.4346 | SHOPP | 2010 | 4103 |  |  |  | X |  | 4000000 | 2475000 | E | 1200000 | 34000 | 1241000 | 841311.41 | 61.88% | 2012-09-13 | 2014-01-10 | 0 | 0.03889 | 0 | 2.3957 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 27360 | VEN | 126 | INSTALL CONCRETE MEDIAN BARRIER | 10.3043 | SHOPP | 2012 | 4107 | X |  |  |  |  | 62300000 | 14200000 | 1600000 | 5950000 | 650000 | 6000000 | 0 | 22.79% | 2016-10-07 | 2018-10-03 | 6.0888 | 4.1852 | 0.03032 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 27400 | LA | 014 | INSTALL MBGR | 0.35914 | SHOPP | 2010 | 4124 |  |  |  | X |  | 3778000 | 1750000 | E | 950000 | 100000 | 700000 | 800576.64 | 46.32% | 2012-03-26 | 2014-04-18 | 0 | 0 | 0 | 0.35914 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 27430 | LA | 091 | UPGRADE MBGR, TRTMNTS & CRSH CUSHNS | 0.91759 | SHOPP | 2010 | 4133 | [5 empty] | 3115000 | 1414000 | E | 580000 | 30000 | 804000 | 483470.75 | 45.39% | 2012-12-17 | 2016-06-01 | 0 | 0.04742 | 0.00216 | 0.86801 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 27450 | LA | 005 | UPDGRADE MBGR & CRASH CUSHIONS | 3.2869 | SHOPP | 2010 | 4136 | [5 empty] | 3167000 | 1630000 | E | 700000 | 30000 | 900000 | 684202.18 | 51.47% | 2013-10-01 | 2014-09-30 | 0 | 0 | 0.05157 | 3.2354 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 27480 | LA | 018 | REPALCE BRIDGE DECK AND RAIL | 2.8602 | SHOPP | 2012 | 4147 |  | X | X |  |  | 2700000 | 1310000 | E | 675000 | 35000 | 600000 | 255343.9 | 48.52% | 2013-12-27 | 2015-01-06 | 0 | 0.77725 | 0.06716 | 2.0158 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 27500 | VEN | 033 | INSTALL BMP | 1.1296 | SHOPP | 2012 | 4157 |  | X | X |  |  | 26300000 | 7770000 | 345000 | 3500000 | 425000 | 3500000 | 0 | 29.54% | 2014-06-16 | 2015-12-30 | 0 | 1.103 | 0.02666 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 27510 | LA | 001 | CONST SHOULDERS/UPGRADE GUARDRAIL | 2.3352 | SHOPP | 2012 | 4159 | [5 empty] | 7500000 | 3208000 | 744000 | 1089000 | 280000 | 1095000 | 0 | 42.77% | 2017-02-27 | 2018-02-26 | 2.3352 | 0 | 0 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 27540 | LA | 001 | SEISMC RETROFIT (BRIDGE 53-0064) | 2.5137 | SHOPP | 2012 | 4165 | X |  |  |  |  | 17528000 | 5398000 | 1075000 | 1551000 | C | 2772000 | 2047.62 | 30.8% | 2016-08-19 | 2018-06-07 | 2.0301 | 0.47305 | 0.0105 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 27570 | LA | 103 | PAINT STEEL PORTION OF STRUCTURE | 2.6109 | SHOPP | 2012 | 4170 |  | X | X |  |  | 7710000 | 2700000 | E | 1320000 | 60000 | 1320000 | 174802.71 | 35.02% | 2014-11-18 | 2017-09-15 | 0 | 2.1357 | 0.02975 | 0.44536 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 27580 | LA | 090 | INSTALL CONCRETE GUARDRAIL | 0.85406 | SHOPP | 2010 | 4171 |  |  |  | X |  | 2426000 | 1066000 | E | 470000 | 50000 | 546000 | 647658.99 | 43.94% | 2012-06-27 | 2013-09-20 | 0 | 0 | 0.00046 | 0.8536 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 27600 | VEN | 101 | PSSR FOR BMP'S IN VEN TRASH TMDL | 6.0734 | SHOPP | 2012 | 4173 | [5 empty] | 15512000 | 4654000 | 475000 | 2000000 | 179000 | 2000000 | 0 | 30% | 2015-06-25 | 2016-08-12 | 0 | 5.9492 | 0.02311 | 0.10116 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 27670 | VEN | 001 | INSTALL ADA CURB RAMPS | 1.1338 | SHOPP | 2012 | 4182 | [5 empty] | 499000 | 485000 | E | 280000 | 5000 | 200000 | 510202.52 | 97.19% | 2013-02-19 | 2013-06-28 | 0 | 0 | 0 | 1.1338 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 27780 | LA | 001 | INSTALL ADA CURB RAMPS | 0.40403 | SHOPP | 2010 | 4200 | [5 empty] | 1650000 | 800000 | E | 385000 | 15000 | 400000 | 1214146.81 | 48.48% | 2011-11-10 | 2013-01-31 | 0 | 0 | 0.00128 | 0.40275 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 27820 | LA | 010 | INSTALL ADA CURB RAMPS | 1.4902 | SHOPP | 2012 | 4207 | [5 empty] | 3000000 | 1265000 | E | 645000 | 20000 | 600000 | 1330985.99 | 42.17% | 2014-01-17 | 2015-04-28 | 0 | 0.34881 | 0.00547 | 1.1359 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 27830 | LA | 405 | BRIDGE REHAB | 2.7758 | SHOPP | 2012 | 4211 | [5 empty] | 9200000 | 3500000 | E | 1600000 | 100000 | 1800000 | 1490536.37 | 38.04% | 2013-05-31 | 2017-08-08 | 0 | 0 | 0.02735 | 2.7484 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 27880 | LA | 005 | UPGRADE WEIGH STATION | 1.4612 | SHOPP | 2012 | 4219 |  |  |  | X |  | 1931000 | 1011000 | E | 764000 | C | 247000 | 674558.4 | 52.36% | 2013-09-10 | 2014-01-08 | 0 | 0.09061 | 0 | 1.3706 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 27890 | VEN | 101 | UPGRADE WEIGH STATION | 0.27098 | SHOPP | 2010 | 4222 | [5 empty] | 544000 | 953000 | E | 633000 | 3000 | 317000 | 541365.63 | 175.2% | 2012-12-19 | 2013-05-23 | 0 | 0.0706 | 0 | 0.20038 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 27980 | LA | 010 | CONST MAINTENANCE VEHICLE PULLOUTS AADD | 0.82323 | SHOPP | 2010 | 4233 |  |  |  | X |  | 1500000 | 750000 | E | 370000 | 10000 | 370000 | 179938.85 | 50% | 2012-03-21 | 2013-12-02 | 0 | 0 | 0 | 0.82323 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 28150 | LA | 101 | GSRD'S OR OTHER TREATMENT BMP | 12.0434 | SHOPP | 2012 | 4279 | [5 empty] | 42952000 | 10850000 | 350000 | 5000000 | 500000 | 5000000 | 0 | 25.26% | 2016-05-12 | 2018-01-02 | 0 | 12.0275 | 0.01589 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 28270 | LA | 101 | INST MBGR-GAP CLOSURES (COLLISION | 4.5129 | SHOPP | 2012 | 4293 | [5 empty] | 11830000 | 3400000 | 10000 | 1640000 | 50000 | 1700000 | 0 | 28.74% | 2015-08-31 | 2017-04-20 | 0 | 4.4007 | 0.11218 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 28500 | LA | 005 | INSTALL AND UPGRADE SIGNAL | 0.2227 | SHOPP | 2010 | 4339 |  |  |  | X |  | 520000 | 373000 | 70000 | 150000 | 3000 | 150000 | 529568.63 | 71.73% | 2012-11-05 | 2013-09-30 | 0 | 0 | 0.03311 | 0.18959 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 28690 | LA | 060 | REHABILITATE PAVEMENT | 15.6024 | SHOPP | 2010 | 4388 | [5 empty] | 110000000 | 11500000 | E | 2400000 | 100000 | 9000000 | 1669430.26 | 10.45% | 2011-12-22 | 2014-10-24 | 0 | 0.02198 | 0.02623 | 15.5542 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 28710 | LA | 101 | INSTALL CONCRETE BARRIER | 3.3975 | SHOPP | 2012 | 4391 | [5 empty] | 4400000 | 1810000 | 100000 | 850000 | 10000 | 850000 | 0 | 41.14% | 2015-08-07 | 2016-06-15 | 0 | 3.3947 | 0.00277 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 28720 | LA | 134 | STORM WATER SOURCE CONTROL | 1.2241 | SHOPP | 2012 | 4405 | [5 empty] | 2000000 | 875000 | 70000 | 400000 | 5000 | 400000 | 0 | 43.75% | 2015-03-03 | 2019-03-12 | 0 | 1.2105 | 0.01365 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 28730 | LA | 210 | STORM WATER SOURCE CONTROL | 1.3307 | SHOPP | 2012 | 4406 | [5 empty] | 2000000 | 875000 | 70000 | 400000 | 5000 | 400000 | 0 | 43.75% | 2015-03-06 | 2019-03-15 | 0 | 1.2977 | 0.03299 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 28740 | LA | 405 | INSTALL CONCRETE/METAL BARRIERS | 4.3706 | SHOPP | 2012 | 4414 | [5 empty] | 6720000 | 2134000 | E | 900000 | 100000 | 1134000 | 0 | 31.76% | 2015-04-28 | 2016-08-24 | 0 | 4.3023 | 0.06832 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 28750 | VEN | 118 | WILDLIFE CORRIDOR STUDY | 0.05065 | PARTNERSHIP |  |  | X
07 | SHOPP | 28760 | LA | 101 | INSTALL SAFETY LIGHT & MBGR BARRIER | 1.692 | SHOPP | 2012 | 4409 | [5 empty] | 2703000 | 1080000 | E | 500000 | 80000 | 500000 | 0 | 39.96% | 2015-09-15 | 2016-07-18 | 0 | 1.6116 | 0.08037 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 28800 | LA | 210 | ROADWAY REHABILITATION | 8.0226 | SHOPP | 2012 | 4413 | [5 empty] | 61201000 | 10200000 | E | 2550000 | C | 7650000 | 163994.53 | 16.67% | 2013-11-01 | 2016-04-05 | 0 | 0.68224 | 0 | 7.3403 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 28820 | LA | 060 | STORM WATER SOURCE CONTROL | 0.89631 | SHOPP | 2012 | 4419 | X |  |  |  |  | 3200000 | 1012000 | 77000 | 450000 | 5000 | 480000 | 0 | 31.62% | 2015-06-12 | 2019-06-21 | 0.01655 | 0.87976 | 0 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 28850 | LA | 405 | PAVE AREA,CONSTRUCT SCALE HOUSE | 2.3066 | SHOPP | 2012 | 4423 |  | X | X |  |  | 3924000 | 1191000 | 70000 | 816000 | 5000 | 300000 | 208950.2 | 30.35% | 2014-05-15 | 2014-12-19 | 0 | 1.9893 | 0 | 0.31728 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 28860 | LA | 710 | BRIDGE REPLACEMENT | 26.7041 | PARTNERSHIP
07 | SHOPP | 28920 | LA | 710 | SOURCE CONTROL | 0.74276 | SHOPP | 2012 | 4458 | X |  |  |  |  | 3000000 | 1000000 | 70000 | 450000 | 5000 | 475000 | 0 | 33.33% | 2015-06-12 | 2019-06-21 | 0.01686 | 0.7259 | 0 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 29000 | LA | 002 | SIGNALS & LIGHTING | 3.6504 | SHOPP | 2012 | 4486 | [5 empty] | 11210000 | 3480000 | E | 1700000 | 80000 | 1700000 | 0 | 31.04% | 2015-08-18 | 2018-07-02 | 0 | 3.4177 | 0.2327 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 29010 | LA | 091 | CONC BARRIER & RECONSTRUCT MBGR | 3.5071 | SHOPP | 2012 | 4489 |  |  | X |  |  | 11325000 | 3250000 | E | 1600000 | 50000 | 1600000 | 0 | 28.7% | 2015-06-10 | 2016-06-01 | 0 | 3.4185 | 0.08864 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 29070 | LA | 110 | MULTILANE FREEWAY | 10.1764 | SHOPP | 2012 | 4497 | [5 empty] | 28750000 | 9010000 | E | 4000000 | 10000 | 5000000 | 33601.41 | 31.34% | 2015-11-03 | 2018-07-05 | 0.11547 | 9.9026 | 0.1584 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 29080 | LA | 001 | ADA IMPROVEMENTS (010.378) | 2.6348 | SHOPP | 2012 | 4491 | X |  |  |  |  | 5300000 | 3500000 | 1000000 | 1500000 | C | 1000000 | 0 | 66.04% | 2015-11-09 | 2016-09-12 | 0.60532 | 2.0146 | 0.01495 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 29090 | LA | 210 | REPLACE MBGR TO CONCRETE BARRIER | 1.3242 | SHOPP | 2012 | 4495 | [5 empty] | 1500000 | 736000 | 50000 | 405000 | 5000 | 276000 | 24377.32 | 49.07% | 2013-10-18 | 2014-12-03 | 0 | 0.26065 | 0.00391 | 1.0596 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 29210 | LA | 101 | MAINTENANCE SAFETY | 0.92949 | SHOPP | 2012 | 4503 | [5 empty] | 2215000 | 812000 | 73000 | 371000 | 1000 | 367000 | 235.14 | 36.66% | 2015-06-16 | 2019-06-25 | 0 | 0.91584 | 0.01365 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 29220 | LA | 002 | MAINTENANCE SAFETY | 1.1962 | SHOPP | 2012 | 4504 | [5 empty] | 2220000 | 1200000 | 100000 | 500000 | 5000 | 595000 | 0 | 54.05% | 2015-06-16 | 2019-06-25 | 0 | 1.1826 | 0.01365 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 29250 | VEN | 101 | MODIFY TRAFFIC SIGNAL | 1.3574 | SHOPP | 2012 | 4506 |  | X | X |  |  | 525000 | 538000 | 77000 | 294000 | 5000 | 162000 | 21725.23 | 102.5% | 2015-05-22 | 2015-08-25 | 0 | 0.28627 | 0 | 1.0711 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 29340 | LA | 005 | MEDIAN BARRIER/CURVE CORRECTION | 3.29 | SHOPP | 2012 | 4550 | [5 empty] | 2900000 | 1200000 | E | 500000 | 50000 | 650000 | 0 | 41.38% | 2015-08-03 | 2017-03-01 | 0 | 3.29 | 0 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 29460 | LA | 101 | ROADSIDE SAFETY IMPROVEMENTS | 0.60242 | SHOPP | 2012 | 4584 | X |  |  |  |  | 2060000 | 927000 | 122000 | 330000 | 1000 | 474000 | 0 | 45% | 2015-07-23 | 2016-08-04 | 0.01649 | 0.58593 | 0 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 29720 | LA | 105 | INSTALL SAFETY LIGHTING/SIGNING | 0.16 | SHOPP PA
07 | SHOPP | 29740 | LA | 105 | INSTALL SAFETY LIGHTING AT INTRCHNG | 0.16 | SHOPP PA
07 | SHOPP | 29770 | LA | 110 | INSTALL SAFETY LIGHTING | 0.8 | SHOPP PA |  |  | X
07 | SHOPP | 29840 | LA | 005 | ENVIRONMENTAL MONITORING | 0.52609 | SHOPP PA
07 | SHOPP | 29850 | LA | 405 | RECONFIGURE RAMPS | 0.58 | SHOPP PA |  |  | X
07 | SHOPP | 0607U | VEN | 101 | WIDEN ROADWAY AND BRIDGES | 0.60659 | STIP | 2000 | 1213M | [5 empty] | 121875000 | 16788000 | 7638000 | 3542000 | 1569000 | 4039000 | 28792652.33 | 13.77% | 2002-05-08 | 2007-10-30 | 0 | 0 | 0 | 0.60659 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 1189F | VEN | 150 | WIDEN BRIDGE AND UPGRADE RAILING | 0.04627 | SHOPP | 2006 | 1231V | [5 empty] | 3617000 | 2216000 | 2216000 | F | F | F | 4547959.1186 | 61.27% | 2008-01-18 | 2010-06-14 | 0 | 0 | 0.04627 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 1760U | LA | 005 | RECONSTRUCT INTERCHANGE AND BRIDGES | 0.37346 | SHOPP | 2000 | 2087 | [5 empty] | 29476000 | 2663000 | 2663000 | F | F | F | 12379938.85 | 9.034% | 2002-01-22 | 2006-04-03 | 0 | 0.11021 | 0 | 0.26325 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 1W240 | LA | 005 | PAINT BRIDGE | 3.2 | SHOPP PA |  |  | X
07 | SHOPP | 1W320 | LA | 405 | ADA UPGRADE | 1.1422 | SHOPP | 2012 | 4561 | [5 empty] | 440000 | 545000 | 102000 | 210000 | 23000 | 210000 | 102417.55 | 123.9% | 2013-11-08 | 2014-09-29 | 0 | 0.11372 | 0.0838 | 0.94471 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 1X321 | LA | 039 | CONSTRUCT RETAINING WALL | 0.09084 | SHOPP | 2008 | 3832 | [5 empty] | 5000000 | 1555000 | 60000 | 565000 | 30000 | 900000 | 3086395.6664 | 31.1% | 2009-10-05 | 2011-12-15 | 0 | 0.03162 | 0.02005 | 0.03917 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 1X322 | LA | 039 | CONSTRUCT RETAINING WALL | 0.40645 | SHOPP | 2008 | 3832A | [5 empty] | 3000000 | 884000 | 48000 | 366000 | 20000 | 450000 | 1216981.7136 | 29.47% | 2009-09-29 | 2011-03-18 | 0 | 0.09736 | 0.006 | 0.30309 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 1X570 | VEN | 150 | STORM DAMAGE REPAIR | 0.19438 | SHOPP | 2010 | 4030 | [5 empty] | 753000 | 189000 | E | 76000 | C | 113000 | 60699.57 | 25.1% | 2012-01-04 | 2017-10-10 | 0 | 0 | 0 | 0.19438 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 1X650 | LA | 005 | RESTORE ROADWAY ALIGNMENT *NOT PROGRAMMED | 1.0783 | SHOPP | 2008 | 4029 | [5 empty] | 21000000 | 5300000 | E | 2500000 | 36000 | 2764000 | 5508390.62 | 25.24% | 2009-08-28 | 2015-02-04 | 0 | 0 | 0.01127 | 1.067 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 2332A | LA | 005 | CONSTRUCT TRUCK LANE | 24.8216 | SHOPP | 2010 | 3189 |  |  |  | X |  | 47726000 | 27274000 | H | 12308000 | 10000 | 14956000 | 6481708.06 | 57.15% | 2012-02-27 | 2014-03-06 | 0 | 0 | 0.10054 | 24.721 | Local | Caltrans | Caltrans | Caltrans
07 | SHOPP | 2395U | LA | 110 | CONSTRUCT CONCRETE BARRIER | 0.3513 | SHOPP | 2006 | 3290 | [5 empty] | 16557000 | 4040000 | 3300000 | 540000 | C | 200000 | 6629802.15 | 24.4% | 2009-07-22 | 2011-08-03 | 0 | 0 | 0.00382 | 0.34748 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 2411U | LA | 110 | CONSTRUCT AUXILIARY LANES | 6.1846 | SHOPP | 2008 | 3343 |  |  |  | X |  | 40567000 | 14365000 | E | 5825000 | 483000 | 8057000 | 17192880.66 | 35.41% | 2009-11-12 | 2014-04-24 | 0 | 0 | 0.18208 | 6.0025 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 2759U | LA | 110 | INSTALL PLANTS FOR EROSION CONTROL | 1.8023 | SHOPP | 2012 | 4172 | [5 empty] | 2550000 | 1182000 | 96000 | 436000 | 50000 | 600000 | 0 | 46.35% | 2013-10-15 | 2015-11-10 | 0 | 0.29709 | 0 | 1.5052 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 2768U | LA | 210 | EROSION CONTROL | 1.9472 | SHOPP | 2012 | 4186 | [5 empty] | 2400000 | 1200000 | 96000 | 454000 | 50000 | 600000 | 154334.48 | 50% | 2013-08-07 | 2015-09-02 | 0 | 0.20132 | 0 | 1.7459 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 2769U | LA | 170 | EROSION CONTROL | 1.1244 | SHOPP | 2012 | 4187 | [5 empty] | 2300000 | 1200000 | 96000 | 454000 | 50000 | 600000 | 318161.7 | 52.17% | 2012-12-11 | 2016-12-23 | 0 | 0 | 0 | 1.1244 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 2770U | LA | 118 | EROSION CONTROL | 1.2167 | SHOPP | 2012 | 4196 | [5 empty] | 2400000 | 1200000 | 96000 | 454000 | 50000 | 600000 | 320726.78 | 50% | 2012-12-12 | 2016-12-29 | 0 | 0 | 0 | 1.2167 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 2777U | LA | 005 | EROSION CONTROL | 2.5985 | SHOPP | 2012 | 4197 | [5 empty] | 3500000 | 1800000 | 144000 | 681000 | 75000 | 900000 | 335669.8 | 51.43% | 2014-02-28 | 2016-03-25 | 0 | 1.8771 | 0 | 0.72136 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 2X370 | LA | 014 | CONVERT LIGHTING | 0.13881 | SHOPP | 2010 | 4277 | [5 empty] | 1500000 | 533000 | E | 300000 | C | 233000 | 284207.54 | 35.53% | 2011-08-15 | 2012-05-03 | 0 | 0 | 0.0615 | 0.07731 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 2X720 | LA | 002 | CLEAR, PROTECT & REPAIR ROADWAY *DIR | 0.19302 | SHOPP | 2008 | 4333 | [5 empty] | 7500000 | 2625000 | L | L | L | 2625000 | 1500525.81 | 35% | 2010-06-24 | 2011-06-08 | 0 | 0 | 0 | 0.19302 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 2X840 | LA | 210 | REPLACE PCC FLUME PROTECTIVE LINER | 0.42127 | SHOPP | 2010 | 4401 |  |  |  | X |  | 1100000 | 495000 | 15000 | 150000 | C | 330000 | 260279.1 | 45% | 2012-09-17 | 2014-01-10 | 0 | 0.00334 | 0.00014 | 0.41779 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 2X870 | LA | 002 | BUILD RETAINING WALLS FOR RDWY SECT *DIR | 0.05171 | SHOPP | 2008 | 4376 | [5 empty] | 9000000 | 1350000 | L | L | L | 1350000 | 991808.8 | 15% | 2010-06-24 | 2012-01-13 | 0 | 0 | 0 | 0.05171 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 2X920 | LA | 091 | REPAIR SLOPE EROSIONS | 0.89006 | SHOPP | 2010 | 4392 | [5 empty] | 2040000 | 918000 | 28000 | 380000 | C | 510000 | 379214.44 | 45% | 2012-06-12 | 2014-09-30 | 0 | 0 | 0.01614 | 0.87392 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 2X930 | LA | 105 | REPAIR SLOPE EROSIONS | 1.6443 | SHOPP | 2010 | 4393 | [5 empty] | 1100000 | 395000 | 20000 | 200000 | C | 175000 | 354209.75 | 35.91% | 2013-07-15 | 2014-08-13 | 0 | 0.06108 | 0.0002 | 1.5831 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 2X940 | LA | 110 | REPAIR SLOPE EROSIONS | 1.0423 | SHOPP | 2010 | 4394 | [5 empty] | 2300000 | 1035000 | 30000 | 430000 | C | 575000 | 417489.18 | 45% | 2013-03-05 | 2016-05-20 | 0 | 0 | 0.00487 | 1.0375 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 2X950 | LA | 405 | REPAIR SLOPE EROSIONS | 2.3538 | SHOPP | 2010 | 4395 |  |  |  | X |  | 3270000 | 1472000 | 54000 | 600000 | C | 818000 | 519582.16 | 45.02% | 2012-11-07 | 2014-02-06 | 0 | 0 | 0 | 2.3538 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 2X960 | LA | 710 | RECONSTRUCT ERODED SLOPE | 2.5366 | SHOPP | 2010 | 4400 |  |  |  | X |  | 1750000 | 736000 | 50000 | 300000 | C | 386000 | 648429.84 | 42.06% | 2013-08-28 | 2014-05-13 | 0 | 0.0642 | 0.00132 | 2.4711 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 2X980 | LA | 014 | REPAIR SLOPE | 1.2718 | SHOPP | 2010 | 4397 |  |  |  | X |  | 4500000 | 2075000 | 50000 | 885000 | 15000 | 1125000 | 699113.35 | 46.11% | 2013-01-02 | 2013-10-24 | 0 | 0 | 0 | 1.2718 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 3X000 | VEN | 033 | CONSTRUCT SOLDIER PILE WALL | 1.0198 | SHOPP | 2012 | 4402 |  |  |  | X |  | 2500000 | 1425000 | E | 500000 | C | 925000 | 1174865.95 | 57% | 2012-10-26 | 2014-06-02 | 0 | 0 | 0 | 1.0198 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 3X010 | LA | 010 | GEOTECHNICAL INVESTIGATION | 0.2466 | SHOPP | 2010 | 4403 |  |  |  | X |  | 575000 | 275000 | E | 90000 | 10000 | 175000 | 307967.64 | 47.83% | 2013-01-02 | 2013-12-09 | 0 | 0.04015 | 0 | 0.20645 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 3X020 | VEN | 150 | CONSTRUCT SOLDIER PILE WALLS | 4.3295 | SHOPP | 2012 | 4404 | [5 empty] | 4150000 | 2000000 | 10000 | 740000 | 50000 | 1200000 | 1333026.03 | 48.19% | 2013-05-23 | 2014-11-26 | 0 | 0 | 0 | 4.3295 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 3X180 | LA | 047 | STORM DAMAGE REPAIRS | 0.70407 | SHOPP | 2012 | 4417 |  |  |  | X |  | 460000 | 400000 | E | 205000 | 10000 | 185000 | 117757.93 | 86.96% | 2013-05-01 | 2014-01-14 | 0 | 0 | 0 | 0.70407 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 3X300 | LA | 010 | RECONST FAILED SLOPE INST RETAIN WA | 0.62617 | SHOPP | 2010 | 4462 |  |  |  | X |  | 1250000 | 563000 | E | 245000 | 5000 | 313000 | 455732.92 | 45.04% | 2012-10-31 | 2013-12-20 | 0 | 0 | 0 | 0.62617 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 3X320 | LA | 010 | CONST DEBRIS BARRIER SYSTEM | 0.5552 | SHOPP | 2010 | 4463 |  |  |  | X |  | 500000 | 225000 | E | 100000 | C | 125000 | 166879.99 | 45% | 2012-11-14 | 2013-10-08 | 0 | 0 | 0 | 0.5552 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 3X350 | LA | 105 | RECONSTRUCT THE FAILED SLOPE *DIR | 0.97786 | SHOPP | 2012 | 4433 | [5 empty] | 550000 | 225000 | 5000 | 75000 | 20000 | 125000 | 34984.28 | 40.91% | 2013-11-01 | 2014-12-05 | 0 | 0.06247 | 0 | 0.91539 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 3X390 | LA | 001 | REPLACE ENTIRE CRIB WALL SYSTEM | 3.2764 | SHOPP | 2012 | 4437 | [5 empty] | 3650000 | 1450000 | 50000 | 400000 | 50000 | 950000 | 234753.04 | 39.73% | 2013-11-12 | 2014-11-03 | 0 | 0.31353 | 0.02164 | 2.9413 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 3X410 | LA | 002 | GRADE SLOPE,PLACE EROSION CONTROL | 1.9966 | SHOPP | 2012 | 4442 | [5 empty] | 3525000 | 1365000 | 20000 | 450000 | 20000 | 875000 | 147132.27 | 38.72% | 2013-11-13 | 2014-10-31 | 0 | 0.32815 | 0.03232 | 1.6361 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 3X450 | LA | 001 | REPAIR FAILED DRAINAGE | 2.8837 | SHOPP | 2012 | 4446 | [5 empty] | 3675000 | 1365000 | 10000 | 465000 | 50000 | 840000 | 0 | 37.14% | 2013-11-06 | 2014-09-10 | 0 | 0.64708 | 0.05156 | 2.1851 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 3X660 | LA | 010 | CONSTRUCT SOIL NAILS | 0.80486 | SHOPP | 2012 | 4480 |  |  |  | X |  | 1500000 | 600000 | 5000 | 260000 | 5000 | 330000 | 30565.67 | 40% | 2013-08-16 | 2014-04-24 | 0 | 0.13969 | 0.00316 | 0.66201 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 3X670 | LA | 047 | REPAIR BRIDGE DAMAGE | 1.4267 | SHOPP | 2010 | 4481 |  |  |  | X |  | 10985000 | 3275000 | L | L | 25000 | 3250000 | 407247.06 | 29.81% | 2011-11-22 | 2013-07-08 | 0 | 0 | 0 | 1.4267 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 3X710 | LA | 060 | REALIGN RAMP & APPROACHES TO NEW BR *DIR | 7.198 | SHOPP | 2012 | 4511 |  | X | X |  |  | 1375000 | 500000 | 5000 | 150000 | 45000 | 300000 | 103973.55 | 36.36% | 2014-09-11 | 2015-09-24 | 0 | 6.9351 | 0.2629 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 3X820 | LA | 039 | REPAIR SLOP FAILURE *DIR | 0.7162 | SHOPP | 2012 | 4619 |  | X |  |  |  | 2000000 | 1200000 | 10000 | 585000 | 5000 | 600000 | 0 | 60% | 2014-02-27 | 2014-12-15 | 0 | 0.17065 | 0.00307 | 0.54248 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 3Y620 | LA | 210 | TREAT DECKS AND REPLACE SEALS | 0.46933 | SHOPP | 2010 | 4269 | [5 empty] | 1371000 | 695000 | E | 250000 | C | 445000 | 312277 | 50.69% | 2011-08-15 | 2012-03-28 | 0 | 0 | 0.05998 | 0.40935 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 4H900 | LA | 060 | WINDEN OFF-RAMP | 4.1803 | SHOPP | 2012 | 3592 | [5 empty] | 2606000 | 1537000 | 20000 | 613000 | 13000 | 891000 | 999547.38 | 58.98% | 2013-08-26 | 2014-08-25 | 0 | 0.1825 | 0.03113 | 3.9667 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 4L221 | LA | 001 | ROADWAY STABILIZATION | 4.0297 | SHOPP | 2010 | 3732A | [5 empty] | 7776000 | 3555000 | 11000 | 1827000 | 690000 | 1027000 | 2537264.55 | 45.72% | 2012-12-14 | 2014-12-02 | 0 | 0.00744 | 1.1619 | 2.8603 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 4L430 | VEN | 150 | REPAIR SLOPE | 0.24045 | SHOPP | 2006 | 3862 | [5 empty] | 2625000 | 525000 | 525000 | F | F | F | 1023875.34 | 20% | 2008-09-15 | 2010-01-07 | 0 | 0 | 0 | 0.24045 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 4L570 | VEN | 150 | CONSTRUCT ROCK WEIR SYSTEM | 1.1864 | SHOPP | 2010 | 4110 | [5 empty] | 6500000 | 1625000 | E | 650000 | C | 975000 | 1620469.8 | 25% | 2010-12-06 | 2014-11-05 | 0 | 0 | 0.00504 | 1.1813 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 4T490 | LA | 001 | CONSTRUCT CURB RAMPS & SIDEWALK REP | 1.5506 | SHOPP | 2012 | 4559 |  |  |  | X |  | 595000 | 624000 | 150000 | 225000 | 24000 | 225000 | 146861.47 | 104.9% | 2013-09-16 | 2014-03-28 | 0 | 0.05832 | 0.09603 | 1.3962 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 4T560 | LA | 107 | SIGNALS | 0.92968 | SHOPP | 2012 | 4507 |  |  |  | X |  | 408000 | 498000 | 87000 | 201000 | 10000 | 200000 | 155474 | 122.1% | 2013-08-01 | 2014-06-04 | 0 | 0 | 0.03333 | 0.89635 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 4T570 | LA | 105 | RDWRK/FLSHNG BCN/LGTHNG DRNG,STRPNG | 1.1782 | SHOPP | 2012 | 4508 |  |  |  | X |  | 985000 | 505000 | 50000 | 200000 | 5000 | 250000 | 191469.76 | 51.27% | 2013-08-22 | 2014-03-18 | 0 | 0 | 0.00753 | 1.1707 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 4T580 | LA | 210 | INSTALL TRAFFIC SIGNAL | 0.65101 | SHOPP | 2012 | 4509 | [5 empty] | 565000 | 348000 | 70000 | 160000 | 5000 | 113000 | 51413.55 | 61.59% | 2013-11-07 | 2014-07-18 | 0 | 0.11149 | 0.01312 | 0.5264 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 4Y150 | LA | 001 | BRIDGE PRESERVATION | 1.1722 | SHOPP | 2010 | 4384 | [5 empty] | 3191000 | 1425000 | E | 700000 | 25000 | 700000 | 571749.87 | 44.66% | 2012-07-13 | 2016-02-23 | 0 | 0 | 0.00477 | 1.1675 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 4Y180 | LA | 605 | BRIDGE PRESERVATION | 0.13865 | SHOPP | 2010 | 4270 |  |  |  | X |  | 1708000 | 680000 | E | 250000 | C | 430000 | 505656.4 | 39.81% | 2011-12-06 | 2013-07-15 | 0 | 0 | 0 | 0.13865 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 4Y230 | LA | 005 | REPLACE JOINT SEAL | 0.26943 | SHOPP | 2010 | 4271 |  |  |  | X |  | 890000 | 457000 | E | 150000 | C | 307000 | 424796.79 | 51.35% | 2011-06-10 | 2013-07-16 | 0 | 0.01818 | 0 | 0.25125 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 4Y240 | LA | 110 | BRIDGE PRESERVATION | 0.51304 | SHOPP | 2010 | 4268 | [5 empty] | 2162000 | 868000 | E | 350000 | C | 518000 | 491878.37 | 40.15% | 2011-12-23 | 2012-09-19 | 0 | 0 | 0.00045 | 0.51259 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 4Y700 | LA | 405 | FULL REMOVAL & PAINT STEEL GIRDERS | 2.4335 | SHOPP | 2012 | 4386 | [5 empty] | 8129000 | 3050000 | E | 1500000 | 350000 | 1200000 | 206754.63 | 37.52% | 2015-11-10 | 2017-09-26 | 0 | 1.9484 | 0.48511 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 4Y750 | LA | 019 | METH DECK,JOINT SEALS,RAIL REPAIR,S | 0.70339 | SHOPP | 2010 | 4385 |  |  |  | X |  | 1120000 | 560000 | E | 260000 | 40000 | 260000 | 353549.38 | 50% | 2012-12-31 | 2013-11-06 | 0 | 0 | 0 | 0.70339 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | 4Y850 | LA | 103 | SPOT PROP AND PAINT | 4.5732 | SHOPP | 2012 | 4383 |  | X | X |  |  | 4872000 | 2442000 | E | 800000 | 800000 | 842000 | 163506.65 | 50.12% | 2014-07-01 | 2018-08-17 | 0 | 1.9028 | 2.6704 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
07 | SHOPP | MINOR |  |  | SHOPP MINOR | 35.3718 | MINOR
08 | SHOPP | 20430 | SBD | 030 | FREEWAY, INTERCHANGE AND STRUCTURES | 0.43255 | STIP | 2010 | 0193D | [5 empty] | 125329000 | D | D | D | D | D | 11427609.4 | NA | 1998-03-19 | 2002-07-01 | 0 | 0 | 0.19422 | 0.23833 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 22700 | SBD | 018 | REPLACE BRIDGE & REALIGN ROADWAY | 0.39789 | SHOPP | 2006 | 0186 | [5 empty] | 58015000 | 16074000 | 5592000 | 4034000 | 182000 | 6266000 | 16798027.23 | 27.71% | 2008-12-02 | 2012-11-21 | 0 | 0 | 0.34091 | 0.05698 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 33630 | SBD | 038 | REPLACE BRIDGE DECK, UPGRADE BRIDGE RAIL, APPROACH GUARD RAIL AND | 1.7485 | SHOPP | 2012 | 0204K |  | X | X |  |  | 1631000 | 2183000 | 930000 | 770000 | 51000 | 432000 | 1187552.77 | 133.8% | 2014-06-26 | 2016-02-16 | 0 | 1.6935 | 0.054957 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 35902 | SBD | 062 | REHABILITATE ROADWAY | 0.38098 | SHOPP | 2004 | 0224K | [5 empty] | 9466000 | 4260000 | 488000 | 1211000 | 963000 | 1598000 | 7195925.4378 | 45% | 2005-09-23 | 2006-11-02 | 0 | 0 | 0.28741 | 0.09357 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 36850 | SBD | 015 | CONST COMM VEH ENFORCEMENT FACILITY (CVEF)& AGRIC INSPEC FACILITY (AIF | 25.9061 | SHOPP | 2012 | 0179B | [5 empty] | 41660000 | 24083000 | 1385000 | 13000000 | 604000 | 9094000 | 19965832.68 | 57.81% | 2013-07-01 | 2014-09-15 | 0 | 0.16066 | 0.23444 | 25.511 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 37704 | SBD | L5506 | CONSTRUCT INLAND EMPIRE TRANSPORTATION MANAGEMENT CENTER | 0.53201 | SHOPP | 2006 | 0410X | [5 empty] | 22188000 | 3087999.9997 | 87999.9999 | 1164000 | 51999.9999 | 1784000 | 1369371.415 | 13.92% | 2008-01-14 | 2012-07-02 | 0 | 0 | 0 | 0.53201 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 37870 | SBD | 062 | BRIDGE TO BE REPLACED | 4.8582 | SHOPP | 2008 | 0227F |  |  |  | X |  | 19157000 | 10470000 | 4700000 | 3540000 | 1012000 | 1218000 | 13019351.69 | 54.65% | 2011-02-15 | 2013-11-12 | 0 | 0 | 0.91817 | 3.94 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 38350 | RIV | 074 | REPLACE BRIDGE | 1.9805 | SHOPP | 2012 | 0062N |  | X | X |  |  | 2881000 | 3162000 | 1570000 | 1100000 | 55000 | 437000 | 1651059.36 | 109.8% | 2014-05-22 | 2015-07-02 | 0 | 1.9582 | 0.022298 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 39471 | SBD | 018 | 4-YR PLANT ESTABLISHMENT | 0.0608 | SHOPP | 2010 | 0188Y | [5 empty] | 100000 | 88000 | H | 40000 | 10000 | 38000 | 46335.61 | 88% | 2012-06-25 | 2016-08-08 | 0 | 0 | 0 | 0.0608 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 43541 | SBD | 040 | PLACE ROCK SLOPE PROTECTION | 1.1523 | SHOPP | 2012 | 0207H | [5 empty] | 504000 | 714000 | 138000 | 325000 | 14000 | 237000 | 185967.38 | 141.7% | 2013-09-05 | 2014-10-20 | 0 | 0.14753 | 0.014902 | 0.98983 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 43890 | SBD | 178 | DRAINAGE IMPROVEMENTS | 0.11333 | SHOPP | 2010 | 0449A | [5 empty] | 2543000 | 3104000 | 1700000 | 965000 | 4000 | 435000 | 2584519.04 | 122.1% | 2012-06-04 | 2013-01-02 | 0 | 0 | 0.010113 | 0.10322 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 44830 | RIV | 015 | REHABILATATE ROADWAY & WIDEN MEDIAN SHOULDER | 9.282 | SHOPP | 2010 | 0024X |  |  |  | X |  | 31911000 | 6667000 | 140000 | 3227000 | 20000 | 3280000 | 1874199.27 | 20.89% | 2012-11-19 | 2014-03-21 | 0 | 0 | 0.01843 | 9.2636 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 44910 | RIV | 111 | REPLACE BRIDGE | 1.5348 | SHOPP | 2012 | 0086A | [5 empty] | 7408000 | 3647000 | 1287000 | 1255000 | 30000 | 1075000 | 1239948.03 | 49.23% | 2013-12-20 | 2015-06-30 | 0 | 0.44873 | 0.018255 | 1.0678 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 47221 | SBD | 015 | REHABILITATE PAVEMENT | 0.29166 | SHOPP | 2008 | 0167J | [5 empty] | 81343000 | 12519000 | 288000 | 3377000 | 98000 | 8756000 | 13142909.67 | 15.39% | 2009-01-16 | 2011-05-11 | 0 | 0 | 0.012765 | 0.2789 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 47222 | SBD | 015 | PAVEMENT REHABILITATION, SLAB REPLACEMENT. REPLACE BRIDGE RAILING | 7.5545 | SHOPP | 2010 | 0167K | [5 empty] | 110050000 | 15030000 | 379000 | 5800000 | 151000 | 8700000 | 4511304.6 | 13.66% | 2012-02-16 | 2014-10-22 | 0 | 0 | 0.092102 | 7.4624 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 47230 | RIV | 010 | CONSTRUCT BRIDGE | 0.07988 | SHOPP | 2006 | 0003A | [5 empty] | 52883000 | 8058000 | 207000 | 3585000 | 159000 | 4107000 | 15058108.46 | 15.24% | 2008-11-21 | 2011-07-01 | 0 | 0 | 0 | 0.07988 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 47810 | RIV | 010 | UPGRADE METAL BEAM GUARD RAIL | 0.15447 | SHOPP | 2010 | 0014F | [5 empty] | 1957000 | 1910000 | 38000 | 1112000 | 23000 | 737000 | 1759015.08 | 97.6% | 2011-06-24 | 2012-10-23 | 0 | 0 | 0.036647 | 0.11782 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 47830 | RIV | 010 | UPGRADE METAL BEAM GUARDRAILING AND BRIDGE ANCHOR BLOCKS | 0.092706 | SHOPP | 2008 | 0067C | [5 empty] | 7756000 | 1837000 | 1000 | 1013000 | 17000 | 806000 | 1970306.62 | 23.68% | 2011-01-14 | 2012-07-13 | 0 | 0 | 0.0087958 | 0.08391 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 47860 | RIV | 086 | CONSTRUCT NEW INTERCHANGE | 0.77509 | SHOPP | 2008 | 0078L | [5 empty] | 27213000 | 8397000 | 1744000 | 2200000 | 770000 | 3683000 | 7955261.66 | 30.86% | 2011-01-11 | 2012-07-02 | 0 | 0 | 0.52825 | 0.24684 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 48930 | SBD | 040 | PAVEMENT REHAB & SHOULDER WIDENING WIDENNING | 0.30132 | SHOPP | 2010 | 0212E | [5 empty] | 20872000 | 4083000 | 581000 | 1663000 | 254000 | 1585000 | 2484669.31 | 19.56% | 2011-04-18 | 2012-03-09 | 0 | 0 | 0.10812 | 0.1932 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 49180 | RIV | 062 | PAVEMENT REHAB INCLUDING SHOULDERS, | 8.4066 | SHOPP | 2012 | 0048S |  |  |  | X |  | 15317000 | 4120000 | 47000 | 1989000 | 158000 | 1926000 | 901522.24 | 26.9% | 2013-08-15 | 2014-06-18 | 0 | 0.36544 | 0.044688 | 7.9965 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 49751 | SBD | 010 | 3-YR PLANT ESTABLISHMENT | 0.20186 | SHOPP | 2010 | 0133L | [5 empty] | 200000 | 100000 | H | H | H | 100000 | 50505.79 | 50% | 2012-09-14 | 2016-01-25 | 0 | 0 | 0 | 0.20186 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 0A423 | SBD | 015 | PAVEMENT REHABILITATION | 0.5106 | SHOPP | 2004 | 0069H | [5 empty] | 21494000 | 3847000 | 70000 | 1010000 | 64000 | 2703000 | 6264149.6936 | 17.9% | 2006-07-14 | 2007-03-26 | 0 | 0.12559 | 0.053475 | 0.33154 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 0C020 | SBD | 002 | CONSTRUCT LEFT TURN POCKET | 0.070009 | SHOPP | 2008 | 0127D | [5 empty] | 2901000 | 5111000 | 2834000 | 1094000 | 348000 | 835000 | 5338168.61 | 176.2% | 2010-09-29 | 2012-10-30 | 0 | 0 | 0.056339 | 0.01367 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 0C121 | SBD | 395 | WIDEN MEDIAN & SHOULDER, INSTALL MEDIAN & SHOULDER RUMBLE STRIPS & | 13.8341 | SHOPP | 2010 | 0259K | [5 empty] | 44360000 | 11100000 | 1250000 | 1750000 | 3700000 | 4400000 | 4813430.57 | 25.02% | 2012-10-31 | 2014-12-29 | 0 | 0 | 1.6863 | 12.1479 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 0E410 | RIV | 010 | WIDENING, REPAIR BRIDGE DECK AND UPGRADE BRIDGE RAILING. | 1.4512 | SHOPP | 2010 | 0010A |  |  |  | X |  | 2660000 | 1905000 | 271000 | 772000 | 24000 | 838000 | 1193478.67 | 71.62% | 2012-01-12 | 2013-09-20 | 0 | 0 | 0 | 1.4512 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 0E500 | SBD | 010 | CONSTRUCT CURB RAMPS | 0.021153 | SHOPP | 2008 | 0137P | [5 empty] | 1475000 | 1126000 | 173000 | 655000 | 67000 | 231000 | 1680002.44 | 76.34% | 2009-02-11 | 2009-11-24 | 0 | 0 | 0.016753 | 0.0044 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 0E850 | SBD | 058 | WIDEN ROADWAY CONSTRUCT MEDIAN | 0.37649 | SHOPP | 2008 | 0216K | [5 empty] | 24820000 | 7423000 | 1626000 | 1640000 | 1431000 | 2726000 | 5794990.71 | 29.91% | 2011-01-04 | 2011-08-22 | 0 | 0 | 0.25074 | 0.12575 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 0F660 | SBD | 247 | CONSTRUCT SHOULDERS @ VARIOUS LOC | 7.5477 | SHOPP | 2012 | 0253E |  | X | X |  |  | 18015000 | 6971000 | 788000 | 1355000 | 3301000 | 1527000 | 2570133.96 | 38.7% | 2014-03-31 | 2015-01-30 | 0 | 1.1366 | 5.0003 | 1.4107 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 0G290 | SBD | 015 | INSTALL SIGNALS ON EXISTING SB & NB RAMP INTERSECTIONS | 3.8055 | PARTNERSHIP | [5 empty] | X
08 | SHOPP | 0G350 | RIV | 010 | METHACRYLATE AND POLYESTER CONCRETE OVERLAY ON BRIDGE DECK | 0.09245 | SHOPP | 2010 | 0067E | [5 empty] | 1317000 | 942000 | 40000 | 400000 | 11000 | 491000 | 577727.41 | 71.53% | 2011-05-25 | 2011-12-19 | 0 | 0 | 0 | 0.09245 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 0G480 | SBD | 015 | SEISMIC RETROFIT BRIDGES(3) | 0.12364 | SHOPP | 2010 | 0177C | [5 empty] | 2132000 | 2852000 | 409000 | 1334000 | 29000 | 1080000 | 1438960.03 | 133.8% | 2011-11-10 | 2012-06-15 | 0 | 0 | 0.021718 | 0.10192 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 0G620 | SBD | 038 | GRIND 30MM & OVERLAY 45MM DGAC TYPE A | 1.8924 | SHOPP | 2012 | 0204J | [5 empty] | 13155000 | 2432000 | E | 1288000 | 43000 | 1101000 | 618648.57 | 18.49% | 2014-02-28 | 2014-12-19 | 0 | 0.35406 | 0.012867 | 1.5255 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 0G840 | SBD | 015 | UPGRADE SRRA | 8.3085 | SHOPP | 2012 | 0176F | [5 empty] | 11377000 | 5584000 | 576000 | 3000000 | 50000 | 1958000 | 3426164.05 | 49.08% | 2013-04-01 | 2014-07-10 | 0 | 0 | 0.0017407 | 8.3068 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 0G900 | SBD | 247 | CONSTRUCT STANDARD PAVED SHOULDER | 15.0673 | SHOPP | 2012 | 0253F |  | X | X |  |  | 19590000 | 9691000 | 1337000 | 2400000 | 3300000 | 2654000 | 1000889.75 | 49.47% | 2014-12-10 | 2015-11-04 | 0 | 4.0151 | 11.0523 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 0H282 | SBD | L5730 | CONSTRUCT NEW MATERIAL LABORATORY | 0.17661 | SHOPP | 2000 | 2108 | [5 empty] | 27293000 | 5956000 | 133000 | 3219000 | 57000 | 2547000 | 15544268.2575 | 21.82% | 2008-03-03 | 2011-11-01 | 0 | 0 | 0 | 0.17661 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 0H310 | RIV | 010 | RUBBERIZED HOT MIX ASPHALT OVERLAY | 0.12838 | SHOPP | 2010 | 0015H | [5 empty] | 26383000 | 1510000 | E | 300000 | 10000 | 1200000 | 1099903.47 | 5.723% | 2011-01-03 | 2011-11-03 | 0 | 0 | 0 | 0.12838 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 0H330 | RIV | 215 | GRIND 45, OVERLAY 60 MM RUBBERIZED AC | 0.043021 | SHOPP | 2010 | 0252T | [5 empty] | 15392000 | 1674000 | 44000 | 800000 | 30000 | 800000 | 498760.38 | 10.88% | 2012-12-03 | - - | 0 | 0 | 0.043021 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 0J010 | SBD | 018 | COSNTRCUT LEFT TURN IN BOTH DIRECTION WIDEN SHOULDER WEST BOUND | 1.5225 | SHOPP | 2012 | 0188C |  |  |  | X |  | 1327000 | 1451000 | 350000 | 299000 | 430000 | 372000 | 1736602.86 | 109.3% | 2013-03-15 | 2014-06-16 | 0 | 0 | 0.42849 | 1.094 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 0J140 | RIV | 074 | WIDEN SR74,EXTEND LEFT-TURN POCKET AND CONSTRUCT CURB RAMPS | 0.23292 | SHOPP | 2010 | 0055C |  |  |  | X |  | 1341000 | 1145000 | 239000 | 441000 | 109000 | 356000 | 1081055.46 | 85.38% | 2012-08-20 | 2013-07-08 | 0 | 0 | 0.041207 | 0.19171 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 0J850 | SBD | 138 | REHABILITATE BRIDGE | 2.3414 | SHOPP | 2012 | 0237R |  | X | X |  |  | 5159000 | 3409000 | 750000 | 1514000 | 69000 | 1076000 | 1316713.85 | 66.08% | 2014-06-11 | 2015-12-18 | 0 | 2.3144 | 0.027023 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 0J930 | SBD | 015 | REHABILITATE BRIDGE | 2.5104 | SHOPP | 2012 | 0178L | X | X | X |  |  | 1510000 | 1147000 | 159000 | 510000 | 12000 | 466000 | 107145.73 | 75.96% | 2014-08-21 | 2014-12-26 | 0.014015 | 2.4601 | 0.03627 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 0J990 | SBD | 018 | REPLACE AND REPAIR DAMAGED SIDEWALK AND CURBS | 6.7761 | SHOPP | 2012 | 0187G | [5 empty] | 3731000 | 3122000 | 650000 | 831000 | 1188000 | 453000 | 473921.82 | 83.68% | 2015-12-02 | 2016-12-23 | 0 | 1.25 | 5.5261 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 0K150 | SBD | 015 | COLD PLANE AND OVERLAY | 3.2084 | SHOPP | 2010 | 0175R |  |  |  | X |  | 9765000 | 3623000 | 146000 | 1700000 | 216000 | 1561000 | 1000804.05 | 37.1% | 2012-01-05 | 2013-10-24 | 0 | 0 | 0.14706 | 3.0614 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 0K200 | SBD | 018 | INSTALL LEFT-TURN LANE | 0.37623 | SHOPP | 2010 | 0190F | [5 empty] | 1186000 | 1186000 | 179000 | 279000 | 274000 | 454000 | 988537.6 | 100% | 2012-04-24 | 2012-08-15 | 0 | 0 | 0.3249 | 0.05133 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 0K230 | RIV | 010 | PCC GRINDING AND SLABS REPLACEMENT | 3.0735 | SHOPP | 2012 | 0015K | [5 empty] | 6778000 | 1292000 | E | 665000 | 21000 | 606000 | 623485.9 | 19.06% | 2013-12-05 | 2014-07-28 | 0 | 0.18107 | 0.0105 | 2.8819 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 0K240 | SBD | 040 | PAVEMENT REHABILITATION | 2.5762 | SHOPP | 2010 | 0208G |  |  |  | X |  | 36198000 | 6000000 | 750000 | 1400000 | 250000 | 3600000 | 982859.22 | 16.58% | 2012-02-10 | 2013-08-13 | 0 | 0 | 0.33475 | 2.2414 | Caltrans | Local | Caltrans | Caltrans
08 | SHOPP | 0K250 | SBD | 040 | MILL & OVERLAY THE EXISTING ASPHALT CONCRETE PAVEMENT | 8.4581 | SHOPP | 2010 | 0207A |  |  |  | X |  | 25570000 | 3370000 | 250000 | 600000 | 20000 | 2500000 | 751209.78 | 13.18% | 2012-12-06 | 2014-05-19 | 0 | 0 | 0.0073958 | 8.4507 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 0K260 | SBD | 040 | MILL & OVERLAY THE EXISTING ASPHALT CONCRETE PAVEMENT | 9.3342 | SHOPP | 2010 | 0211R |  |  |  | X |  | 23931000 | 3520000 | 300000 | 600000 | 20000 | 2600000 | 432949.57 | 14.71% | 2012-12-19 | 2014-06-11 | 0 | 0 | 0.015289 | 9.3189 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 0K270 | SBD | 040 | PAVEMENT REHABILITATION | 11.3609 | SHOPP | 2010 | 0212H |  |  |  | X |  | 32782000 | 4240000 | 320000 | 600000 | 20000 | 3300000 | 381703.58 | 12.93% | 2012-12-21 | 2014-06-11 | 0 | 0 | 0.016624 | 11.3443 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 0K280 | SBD | 040 | GRIND 45 MM AND OVERLAY 60 MM AC | 9.8572 | SHOPP | 2012 | 0210J | [5 empty] | 23218000 | 4313000 | 416000 | 974000 | 221000 | 2702000 | 729183.23 | 18.58% | 2013-10-31 | 2014-08-28 | 0 | 0.23736 | 0.0092102 | 9.6106 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 0K292 | SBD | 010 | LANE REPLACEMENT | 2.1559 | SHOPP | 2012 | 0151J |  | X | X |  |  | 29560000 | 5373000 | H | 1920000 | 268000 | 3185000 | 5339.77 | 18.18% | 2014-08-07 | 2016-04-14 | 0 | 1.8691 | 0.28682 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 0K300 | RIV | 015 | REPLACE PCC PAVEMENT | 0.09223 | SHOPP | 2010 | 0016H | [5 empty] | 6272000 | 1701000 | 292000 | 790000 | 46000 | 573000 | 999892.49 | 27.12% | 2011-05-11 | 2012-03-08 | 0 | 0 | 0 | 0.09223 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 0K310 | SBD | 095 | VERICAL CURVE ALIGNMENT | 3.1501 | SHOPP | 2012 | 0238L | [5 empty] | 3896000 | 1839000 | 446000 | 539000 | 163000 | 691000 | 1034179.21 | 47.2% | 2013-06-20 | 2014-07-22 | 0 | 0.016434 | 0.029049 | 3.1046 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 0K681 | RIV | 010 | REMOVE AC OVERLAY CLEAN DECK,REMOVE REPAIR JOINT SEAL,SEAL COAT METHAC | 0.03626 | SHOPP | 2008 | 0057T | [5 empty] | 2800000 | 538000 | E | 124000 | 3000 | 411000 | 592815.08 | 19.21% | 2010-11-23 | 2012-02-13 | 0 | 0 | 0 | 0.03626 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 0K710 | SBD | 015 | REALIGN AND RECONFIGURE CONNECTORS | 32.331 | SHOPP | 2010 | 0170M | [5 empty] | 284692000 | 45267000 | 10295000 | 6385000 | 2036000 | 26551000 | 6809651.38 | 15.9% | 2012-11-13 | 2016-09-30 | 0 | 0 | 1.4798 | 30.8513 | Caltrans | Caltrans | Local | Caltrans
08 | SHOPP | 0K771 | SBD | 015 | REPLACE THE EXISTING GUARDRAIL WITH CONCRETE GUARDRAIL PLACE RUMBLE | 1.1952 | SHOPP PA |  |  |  | X | X
08 | SHOPP | 0L790 | RIV | 010 | INSTALL VEHICLE DETECTION SYSTEMS (VDS'S) | 0.1244 | SHOPP | 2010 | 0005M | [5 empty] | 7000000 | 1460000 | 100000 | 300000 | 10000 | 1050000 | 949552.3 | 20.86% | 2011-04-07 | 2013-05-31 | 0 | 0 | 0 | 0.1244 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 0L820 | SBD | 210 | GROOVE EXISTING PCC PAVEMENT IN ALL 3 LANES | 0.010489 | SHOPP | 2010 | 0194V | [5 empty] | 880000 | 540000 | 10000 | 238000 | 31000 | 261000 | 386856.84 | 61.36% | 2011-09-12 | 2012-01-26 | 0 | 0 | 0.0058393 | 0.00465 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 0L930 | RIV | 010 | BUILD A NEW ADMISTRATIVE BLDG & INSTALL A NEW SEPTIC TANK & | 2.2457 | SHOPP | 2010 | 0009L |  |  |  | X |  | 1960000 | 1612000 | 210000 | 850000 | 32000 | 520000 | 1673082.85 | 82.24% | 2012-11-09 | 2014-01-15 | 0 | 0 | 0.0049919 | 2.2407 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 0L950 | RIV | 010 | REPLACE CONCRETE SLABS | 0.11041 | SHOPP | 2008 | 0009M | [5 empty] | 7077000 | 1303000 | E | 709000 | 18000 | 576000 | 747566.14 | 18.41% | 2011-01-21 | 2011-11-29 | 0 | 0 | 0.020751 | 0.08966 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 0M200 | RIV | 371 | CONSTRUCT SHOULDER | 1.956 | SHOPP | 2012 | 0258N |  | X | X |  |  | 7758000 | 3347000 | 732000 | 665000 | 200000 | 1750000 | 476202.09 | 43.14% | 2014-11-20 | 2016-07-18 | 0 | 1.7979 | 0.15811 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 0M210 | RIV | 074 | INSTALL TRAFFIC SIGNALS | 0.7795 | SHOPP | 2010 | 0058A |  |  |  | X |  | 590000 | 652000 | 12000 | 240000 | 110000 | 290000 | 507919.52 | 110.5% | 2013-01-10 | 2013-10-31 | 0 | 0 | 0.12146 | 0.65804 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 0M280 | SBD | 015 | REPLACE 2 BRIDGES | 4.0479 | SHOPP | 2012 | 0172X |  | X | X |  |  | 14552000 | 5366000 | 634000 | 2421000 | 40000 | 2271000 | 695787.9 | 36.87% | 2014-10-01 | 2016-03-07 | 0 | 4.0027 | 0.045148 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 0M310 | RIV | 060 | UPGRADE PEDESTRIAN FACILITIES ADA RAMPS 37 CURB RAMPS | 0.99829 | SHOPP | 2012 | 0044K | [5 empty] | 760000 | 980000 | 189000 | 386000 | 175000 | 230000 | 523719.17 | 128.9% | 2013-10-25 | 2014-10-27 | 0 | 0.15952 | 0.11813 | 0.72064 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 0M350 | SBD | 010 | GRIND PCC PAVEMENT RECONSTRUCT G R | 0.093886 | SHOPP | 2010 | 0146G | [5 empty] | 3176000 | 796000 | E | 280000 | 35000 | 481000 | 420576.62 | 25.06% | 2011-06-24 | 2012-07-31 | 0 | 0 | 0.036896 | 0.05699 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 0M420 | RIV | 074 | INSTALL METAL BEAM GUARDRAIL | 0.94121 | SHOPP | 2012 | 0050K | [5 empty] | 576000 | 953000 | 160000 | 482000 | 16000 | 295000 | 418650.8 | 165.5% | 2013-09-05 | 2014-09-05 | 0 | 0.12131 | 0.011909 | 0.80799 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 0M440 | SBD | 062 | INSTALL TRAFFIC SIGNALS | 0.025811 | SHOPP | 2010 | 0225F | [5 empty] | 751000 | 645000 | 137000 | 222000 | 68000 | 218000 | 606304.61 | 85.89% | 2011-06-20 | 2012-03-06 | 0 | 0 | 0.0094313 | 0.01638 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 0M450 | SBD | 038 | ADD LEFT TURN POCKETS | 1.0905 | SHOPP | 2012 | 0204V | [5 empty] | 1113000 | 1132000 | 240000 | 413000 | 190000 | 289000 | 764526.91 | 101.7% | 2013-10-28 | 2014-12-15 | 0 | 0.21128 | 0.15983 | 0.71937 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 0M690 | SBD | 095 | CONSTRUCT SIDEWALKS &18 CRUB RAMPS | 0.69235 | SHOPP | 2012 | 0238M | [5 empty] | 855000 | 689000 | 157000 | 346000 | 20000 | 166000 | 485630.35 | 80.58% | 2013-07-29 | 2014-07-28 | 0 | 0.06966 | 0.011623 | 0.61107 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 0M720 | SBD | 018 | INSTALL GROUND-IN MEDIAN RUMBLE STRIP | 0.0092177 | SHOPP | 2010 | 0183E | [5 empty] | 263000 | 341000 | E | 140000 | 21000 | 180000 | 216160.53 | 129.7% | 2011-10-25 | 2012-05-24 | 0 | 0 | 0.0044577 | 0.00476 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 0M770 | SBD | 015 | RETROFIT CHANGEABLE MESSAGE SIGNS | 0.09906 | SHOPP | 2010 | 0019M | [5 empty] | 4000000 | 1010000 | 100000 | 300000 | 10000 | 600000 | 436680.98 | 25.25% | 2011-01-20 | 2012-08-09 | 0 | 0 | 0 | 0.09906 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 0M870 | RIV | 074 | INSTALL TRAFFIC SIGNALS | 0.13261 | SHOPP | 2010 | 0054J | [5 empty] | 698000 | 702000 | 198000 | 240000 | 46000 | 218000 | 626359.76 | 100.6% | 2012-06-19 | 2013-04-23 | 0 | 0 | 0.054055 | 0.07856 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 0M880 | SBD | 015 | INSTALL TRAFFIC SIGNALS | 0.72046 | SHOPP | 2010 | 0069G |  |  |  | X |  | 583000 | 676000 | 190000 | 230000 | 46000 | 210000 | 513343.5 | 116% | 2013-02-11 | 2013-12-10 | 0 | 0 | 0.1031 | 0.61736 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 0N240 | SBD | 010 | INSTALL OUTER SEPERATION CONCRETE BARRIER TYPE 60G | 0.089037 | SHOPP | 2010 | 0164A | [5 empty] | 762000 | 639000 | 190000 | 212000 | 27000 | 210000 | 410540.19 | 83.86% | 2012-08-20 | 2013-04-16 | 0 | 0 | 0.032687 | 0.05635 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 0N260 | RIV | 015 | INSTALL OUTER SEPARATION BARRIER | 0.053921 | SHOPP | 2010 | 0022H | [5 empty] | 681000 | 638000 | 185000 | 203000 | 30000 | 220000 | 521653.51 | 93.69% | 2012-07-16 | 2012-11-02 | 0 | 0 | 0.039521 | 0.0144 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 0N410 | SBD | 210 | REPLACE K-RAIL BARRIER W/ CONCRETE BARRIER | 1.0453 | SHOPP | 2010 | 0195K |  |  |  | X |  | 3754000 | 1280000 | E | 650000 | 30000 | 600000 | 506636.95 | 34.1% | 2012-11-27 | 2013-09-18 | 0 | 0 | 0.036224 | 1.009 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 0N510 | RIV | 015 | REPLACE EXISTING GUARDRAIL WITH CONCRETE BARRIER | 2.1694 | SHOPP | 2012 | 0030G |  |  |  | X |  | 2835000 | 1248000 | 230000 | 530000 | 28000 | 460000 | 640063.67 | 44.02% | 2013-09-30 | 2014-06-30 | 0 | 0.12777 | 0.0059498 | 2.0356 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 0N550 | SBD | 040 | BRIDGE REPLACEMENT | 5.4357 | SHOPP | 2012 | 0206T | X |  |  |  |  | 9537000 | 3936000 | 755000 | 1701000 | 70000 | 1410000 | 12351.94 | 41.27% | 2015-09-03 | 2016-11-03 | 1.1298 | 4.1952 | 0.11068 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 0N560 | SBD | 040 | BRIDGE REPLACEMENT | 9.5433 | SHOPP | 2012 | 0211S |  | X | X |  |  | 34105000 | 9014000 | 816000 | 3189000 | 143000 | 4866000 | 441155.76 | 26.43% | 2014-10-06 | 2016-05-02 | 0 | 9.3414 | 0.20189 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 0N570 | SBD | 040 | BRIDGE SIESMIC RETROFIT | 1.5683 | SHOPP | 2012 | 0213C | [5 empty] | 1185000 | 1094000 | 141000 | 469000 | 22000 | 462000 | 155833 | 92.32% | 2013-10-07 | 2014-12-08 | 0 | 0.21808 | 0.02251 | 1.3278 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 0N590 | SBD | 040 | BRIDGE REPLACEMENT | 7.4734 | SHOPP | 2010 | 0206S |  |  |  | X |  | 16100000 | 5597000 | 750000 | 2513000 | 52000 | 2282000 | 2100303.89 | 34.76% | 2013-02-25 | 2014-02-21 | 0 | 0 | 0.083822 | 7.3895 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 0N591 | SBD | 040 | BRIDGE REPLACEMENT | 2.7283 | SHOPP | 2012 | 0210K |  | X | X |  |  | 9143000 | 3892000 | 692000 | 1298000 | 51000 | 1851000 | 294047.94 | 42.57% | 2014-07-07 | 2016-02-05 | 0 | 2.7014 | 0.026875 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 0N780 | RIV | 015 | NATIVE TREE PLANTING & PLACE INERT MATERIAL (CCC DIRECTED) | 0.24309 | STIP | 2008 | 0016L | [5 empty] | 1150000 | 230000 | J | J | J | 230000 | 166044.92 | 20% | - - | 2014-12-30 | 0 | 0 | 0 | 0.24309 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 0N790 | RIV | 015 | NATIVE TREE PLANTING & PLACE INVERT MATERIAL (CCC DIRECTED) | 0.12538 | STIP | 2008 | 0016J | [5 empty] | 700000 | 140000 | J | J | J | 140000 | 95979.44 | 20% | - - | 2014-12-30 | 0 | 0 | 0 | 0.12538 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 0N800 | SBD | 015 | NATIVE TREE PLANTING & PLACE INERT MATERIAL (CCC DIRECTED) | 0.46556 | STIP | 2008 | 0168P | [5 empty] | 1350000 | 270000 | J | J | J | 270000 | 110572.31 | 20% | - - | 2014-12-30 | 0 | 0 | 0 | 0.46556 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 0N810 | SBD | 015 | NATIVE TREE PLANTING & PLACE INVERT MATERIAL (CCC DIRECTED) | 0.19909 | STIP | 2008 | 0168N | [5 empty] | 425000 | 85000 | J | J | J | 85000 | 18878.25 | 20% | - - | 2014-12-30 | 0 | 0 | 0 | 0.19909 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 0N820 | RIV | 091 | NATIVE TREE PLANTING & PLACE INERT MATERIAL (CCC DIRECTED) | 0.2313 | STIP | 2008 | 0049W | [5 empty] | 500000 | 100000 | J | J | J | 100000 | 21842.13 | 20% | - - | 2014-12-30 | 0 | 0 | 0 | 0.2313 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 0N830 | RIV | 015 | NATIVE TREE PLANTING & PLACE INERT MATERIAL (CCC DIRECTED) | 0.09583 | STIP | 2008 | 0016K | [5 empty] | 325000 | 65000 | J | J | J | 65000 | 32947.02 | 20% | - - | 2014-12-30 | 0 | 0 | 0 | 0.09583 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 0N870 | RIV | 010 | TRIM REMOVE AND HAUL BURNT PLANT MATERIAL & REPAIR IRRIGATION SYSTEM | 0.06336 | SHOPP | 2010 | 0012G | [5 empty] | 1200000 | 720000 | 80000 | 330000 | 20000 | 290000 | 463179.66 | 60% | 2011-07-01 | 2012-06-08 | 0 | 0 | 0 | 0.06336 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 0N910 | RIV | 062 | INSTALL TRAFFIC SIGNALS | 0.95812 | SHOPP | 2010 | 0050H |  |  |  | X |  | 994000 | 925000 | 254000 | 370000 | 20000 | 281000 | 785530.14 | 93.06% | 2013-01-28 | 2013-12-23 | 0 | 0 | 0.044025 | 0.9141 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 0N970 | SBD | 395 | CONSTRUCT 4' MEDIAN BUFFER & WIDEN EXISTING SHOULDER TO 5'. CONSTRUCT | 7.6439 | SHOPP | 2012 | 0258P | X |  |  |  |  | 36138000 | 7518000 | 1478000 | 1352000 | 665000 | 4023000 | 696626.8 | 20.8% | 2015-11-02 | 2016-11-15 | 0.29767 | 5.0607 | 2.2856 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 0P160 | SBD | 010 | TREAT DECKS W/METHACRYLATE, REPLACE JOINT SEALS | 0.04702 | SHOPP | 2010 | 0133K | [5 empty] | 1124000 | 643000 | 36000 | 265000 | 7000 | 335000 | 430203.6 | 57.21% | 2012-02-03 | 2012-05-29 | 0 | 0 | 0 | 0.04702 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 0P180 | SBD | 040 | PLACE OVERLAY, METHACRYLATE DECK AND REPLACE JOINT SEAL | 0.15649 | SHOPP | 2010 | 0206Q | [5 empty] | 2136000 | 1120000 | 108000 | 319000 | 13000 | 680000 | 476905.59 | 52.43% | 2011-12-23 | 2012-05-29 | 0 | 0 | 0.039733 | 0.11676 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 0P280 | RIV | 060 | INSTALL TRAFFIC SIGNAL. CONSTRUCT DOUBLE LEFT-TURN LANE | 0.98356 | SHOPP | 2012 | 0033K |  | X | X |  |  | 1059000 | 627000 | E | 270000 | 7000 | 350000 | 169.14 | 59.21% | 2014-07-31 | 2015-08-13 | 0 | 0.95306 | 0.030504 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 0P310 | SBD | 395 | INSTALL LEFT-TURN PHASING | 0.7383 | SHOPP | 2012 | 0258Q |  | X | X |  |  | 416000 | 781000 | 286000 | 274000 | 23000 | 198000 | 172623.18 | 187.7% | 2014-01-20 | 2015-02-20 | 0 | 0.37237 | 0.02565 | 0.34028 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 0P390 | SBD | 018 | WIDEN EXISTING SHOULDER TO 8' AND CONSTRUCT CENTERLINE AND SHOULDER | 5.026 | SHOPP | 2012 | 0191G | X |  |  |  |  | 25654000 | 7772000 | 2168000 | 1788000 | 394000 | 3422000 | 0 | 30.3% | 2016-04-21 | 2018-04-20 | 1.8826 | 2.7824 | 0.36107 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 0P560 | SBD | 095 | INSTALL CENTERLINE GROUND IN RUMBLE STRIPS | 0.082386 | SHOPP | 2010 | 0236L | [5 empty] | 299000 | 400000 | 90000 | 149000 | 11000 | 150000 | 253462.51 | 133.8% | 2012-11-01 | 2013-06-28 | 0 | 0 | 0.027806 | 0.05458 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 0P620 | RIV | 015 | UPGRADE CONTROLLERS, SYSTEM DETECTION, VEHICLE DETECTION | 0.06325 | SHOPP | 2010 | 0018E | [5 empty] | 4510000 | 1385000 | 300000 | 400000 | 10000 | 675000 | 1216687.36 | 30.71% | 2011-04-21 | 2013-05-01 | 0 | 0 | 0 | 0.06325 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 0P630 | RIV | 091 | UPGRADE TELEVISION CAMERA SYSTEMS | 0.15744 | SHOPP | 2010 | 0081J | [5 empty] | 7710000 | 2155000 | 460000 | 685000 | 10000 | 1000000 | 707730.33 | 27.95% | 2011-04-07 | 2013-05-10 | 0 | 0 | 0.020907 | 0.13653 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 0P960 | RIV | 079 | INSTALL MARKERS AND RUMBLE STRIPS | 0.10477 | SHOPP | 2010 | 0068J | [5 empty] | 381000 | 542000 | 157000 | 220000 | 7000 | 158000 | 384081.68 | 142.3% | 2012-10-15 | 2012-12-18 | 0 | 0 | 0.02158 | 0.08319 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 0P980 | SBD | 018 | SIGNALIZE INTERSECTION. ADA REQUIREMENTS | 1.0759 | SHOPP | 2012 | 0191H | [5 empty] | 675000 | 1091000 | 253000 | 412000 | 70000 | 356000 | 0 | 161.6% | 2015-06-16 | 2016-05-13 | 0 | 0.90108 | 0.17487 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 0Q110 | RIV | 010 | REPLACE CHAIN LINK FENCE & BARBED WIRE FENCE WITH AN OUTER- | 3.601 | SHOPP | 2012 | 0015M |  |  |  | X |  | 3570000 | 1222000 | 280000 | 310000 | 5000 | 627000 | 494216.26 | 34.23% | 2013-07-12 | 2014-06-10 | 0 | 0.013906 | 0.0009947 | 3.5861 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 0Q180 | RIV | 060 | CONSTRUCT SHOULDERS | 10.097 | SHOPP | 2012 | 0045G | [5 empty] | 25250000 | 20402000 | 4516000 | 11986000 | 200000 | 3700000 | 3354.23 | 80.8% | 2016-10-31 | 2018-12-03 | 10.097 | 0 | 0 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 0Q230 | SBD | 018 | SIGNALIZE INTERSECTION. PLUS CURB RAMPS, ADA REQUIREMENT. | 1.3164 | SHOPP | 2012 | 0191K |  | X | X |  |  | 1133000 | 1252000 | 299000 | 481000 | 174000 | 298000 | 188099.45 | 110.5% | 2014-08-04 | 2015-07-01 | 0 | 0.8369 | 0.47945 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 0Q240 | SBD | 138 | REPAIR/REPLACE 42" CULVERTS | 0.60204 | SHOPP | 2010 | 0236K |  |  |  | X |  | 1107000 | 406000 | 34000 | 168000 | 6000 | 198000 | 541903.27 | 36.68% | 2013-02-04 | 2014-03-04 | 0 | 0 | 0.0052222 | 0.59681 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 0Q300 | SBD | 138 | CONSTRUCT TWO LANE CONVENTIONAL HWY | 17.6772 | SHOPP | 2012 | 0237P | X | X | X |  |  | 23717000 | 9116000 | 1257000 | 3248000 | 677000 | 3934000 | 1043069.21 | 38.44% | 2014-10-30 | 2016-11-30 | 0.1452 | 14.7394 | 2.7926 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 0Q600 | SBD | 002 | MODIFY DIKE AND PLACE CONCRETE SLOPE | 0.62619 | SHOPP | 2012 | 0127H |  | X | X | X |  | 305000 | 405000 | 100000 | 180000 | 15000 | 110000 | 151925.28 | 132.8% | 2014-01-03 | 2014-06-02 | 0 | 0.10735 | 0.025918 | 0.49293 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 0Q730 | SBD | 062 | PAVEMENT REHABILITATION | 9.58 | SHOPP | 2010 | 0224M |  |  |  | X |  | 22093000 | 3240000 | E | 600000 | 40000 | 2600000 | 504795.91 | 14.67% | 2013-01-03 | 2014-06-23 | 0 | 0 | 0.024287 | 9.5557 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 0Q740 | SBD | 015 | PAVEMENT REHABILITATION AND SLAB REPLACEMENT | 11.5153 | SHOPP | 2012 | 0169K | [5 empty] | 129881000 | 43069000 | 2468000 | 14480000 | 1646000 | 24475000 | 35904.9 | 33.16% | 2013-09-02 | 2015-12-11 | 0 | 2.8625 | 0.11323 | 8.5395 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 0Q790 | SBD | 040 | BRIDGE REPLACEMENT | 2.0894 | SHOPP | 2012 | 0206X | X |  |  |  |  | 8854000 | 3711000 | 404000 | 1281000 | 92000 | 1934000 | 2468.88 | 41.91% | 2015-12-01 | 2017-06-08 | 1.6317 | 0.45774 | 0 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 0Q830 | SBD | 210 | GRIND/RECONSTRUCT PCC PAVEMENT. CONSTRUCT/RECONSTRUCT DRAINAGE | 2.4717 | SHOPP | 2012 | 0195L | X |  | X |  |  | 2306000 | 936000 | 221000 | 430000 | 8000 | 277000 | 10845.26 | 40.59% | 2014-12-29 | 2015-09-02 | 0.079197 | 2.3748 | 0.017757 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 0Q860 | SBD | 015 | REPLACE OVERHEAD SIGN STRUCTURE | 0.13257 | SHOPP | 2012 | 0175U | [5 empty] | 176000 | 256000 | 76000 | 150000 | C | 30000 | 179329.5 | 145.5% | 2013-02-07 | 2013-04-23 | 0 | 0 | 0.029473 | 0.1031 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 0Q980 | RIV | 091 | REPLACE ALUMINUM JOINT SEALS | 0.00586 | SHOPP | 2010 | 0078P | [5 empty] | 800000 | 120000 | 10000 | 20000 | C | 90000 | 54168.78 | 15% | 2011-07-08 | 2011-12-22 | 0 | 0 | 0 | 0.00586 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 0R120 | SBD | 040 | REGRADE MEDIAN CROSS SLOPE | 1.0304 | SHOPP | 2012 | 0207J | [5 empty] | 19500000 | 6222000 | 1537000 | 2157000 | 183000 | 2345000 | 0 | 31.91% | 2016-10-31 | 2018-11-30 | 1.0304 | 0 | 0 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 0R160 | SBD | 040 | REGRADE MEDIAN CROSS SLOPE | 3.1512 | SHOPP | 2012 | 0206Y | [5 empty] | 19665000 | 6302000 | 1537000 | 2157000 | 190000 | 2418000 | 0 | 32.05% | 2016-08-31 | 2018-09-28 | 3.1512 | 0 | 0 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 0R440 | SBD | 015 | INSTALL VEGETATION CONTROL UNDER- NEATH METAL BEAM GUARD RAIL | 0.49902 | SHOPP | 2012 | 0171G | [5 empty] | 1300000 | 600000 | 120000 | 240000 | 20000 | 220000 | 0 | 46.15% | 2016-03-31 | 2017-02-28 | 0.49902 | 0 | 0 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 0R450 | SBD | 015 | INSTALL VEGETATION CONTROL UNDER- NEATH METAL BEAM GUARDRAIL. | 0.77434 | SHOPP | 2012 | 0170S | [5 empty] | 1300000 | 720000 | 150000 | 250000 | 30000 | 290000 | 0 | 55.38% | 2016-02-19 | 2017-01-20 | 0.77434 | 0 | 0 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 0R460 | RIV | 091 | IMPROVE WORKER SAFETY CONDITIONS. UPGRADE GUARDRAIL AND ROADSIDE | 1.5545 | SHOPP | 2012 | 0080J | X |  |  |  |  | 1325000 | 730000 | 160000 | 320000 | 30000 | 220000 | 0 | 55.09% | 2015-07-31 | 2016-06-30 | 0.57116 | 0.96795 | 0.015353 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 0R470 | SBD | 215 | UPGRADE PEDESTRIAN FACILITIES, REMOVE MBGR AND PAVE WALKWAY | 1.6641 | SHOPP | 2012 | 0244G | X |  |  |  |  | 1938000 | 975000 | 200000 | 400000 | 40000 | 335000 | 0 | 50.31% | 2015-09-30 | 2016-08-31 | 0.83353 | 0.8211 | 0.0094681 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 0R480 | SBD | 060 | IMPROVE WORKER SAFETY CONDITIONS. UPGRADE GUARDRAIL AND ROADSIDE | 0.29368 | SHOPP | 2012 | 0220F | [5 empty] | 1780000 | 910000 | 180000 | 360000 | 40000 | 330000 | 0 | 51.12% | 2016-07-29 | 2017-08-31 | 0.29368 | 0 | 0 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 0R490 | RIV | 091 | IMPROVE WORKER SAFETY CONDITIONS. UPGRADE GUARDRAIL AND ROADSIDE | 1.7186 | SHOPP | 2012 | 0076G | X |  |  |  |  | 1486000 | 795000 | 165000 | 340000 | 30000 | 260000 | 0 | 53.5% | 2015-05-29 | 2016-04-29 | 0.41428 | 1.2811 | 0.023191 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 0R500 | SBD | 015 | BUID DEBRIS RACKS, CLEAN DEBRIS, CULVERT REPAIR. STABILIZE SLOPE. | 0.00872 | SHOPP | 2010 | 0069M | [5 empty] | 275000 | 55000 | 5000 | J | C | 50000 | 85970.51 | 20% | 2011-09-26 | 2012-03-02 | 0 | 0 | 0 | 0.00872 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 0R510 | SBD | 015 | INSTALL VEGETATION CONTROL UNDER- NEATH METAL BEAM GUARDRAIL. | 0.75721 | SHOPP | 2012 | 0168S | X |  |  |  |  | 1200000 | 680000 | 140000 | 275000 | 25000 | 240000 | 0 | 56.67% | 2016-01-29 | 2016-12-23 | 0.75721 | 0 | 0 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 0R540 | SBD | 010 | INSTALL ROCK BLANKET AND TWO SIGN EXIT IN THE GORE AREA OF FWY EXITS. | 0.42116 | SHOPP | 2012 | 0160G | [5 empty] | 1000000 | 720000 | 150000 | 250000 | 30000 | 290000 | 0 | 72% | 2016-05-20 | 2017-04-28 | 0.42116 | 0 | 0 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 0R670 | SBD | 018 | INSTALL CENTERLINE GROUND-IN RUMBLE STRIPS | 1.1105 | SHOPP | 2012 | 0181L | X | X | X |  |  | 452000 | 458000 | 126000 | 189000 | 6000 | 137000 | 16560.09 | 101.3% | 2014-11-20 | 2015-05-26 | 0.017013 | 1.057 | 0.036491 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 0R740 | RIV | 371 | INSTALL CENTERLINE GROUND-IN RUMBLE STRIPS AND OBJECT MARKERS TYPE | 0.66769 | SHOPP | 2012 | 0259R | [5 empty] | 325000 | 481000 | 174000 | 207000 | 3000 | 97000 | 0 | 148% | 2015-01-15 | 2016-01-15 | 0 | 0.66519 | 0.0025052 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 0R750 | RIV | 062 | INSTALL MEDIAN BARRIER MARKERS AND RUMBLE STRIPS | 0.8873 | SHOPP | 2012 | 0023A | X |  |  |  |  | 457000 | 580000 | 207000 | 249000 | 3000 | 121000 | 0 | 126.9% | 2015-04-15 | 2016-04-15 | 0.1776 | 0.70863 | 0.0010684 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 0R840 | SBD | 015 | REPAIR CULVERT BY COMPACTION GROUTING THE VOIDS BENEATH THE | 0.52329 | SHOPP | 2012 | 0069N | [5 empty] | 2306000 | 975000 | 200000 | 300000 | 75000 | 400000 | 4065.57 | 42.28% | 2012-10-29 | 2013-02-01 | 0 | 0 | 0.2137 | 0.30959 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 0R920 | RIV | 010 | REPLACE/REPAIR ELECTRICAL SYSTEMS | 0.01954 | SHOPP | 2010 | 0007M | [5 empty] | 700000 | 70000 | 10000 | L | C | 60000 | 162542.42 | 10% | 2012-02-01 | 2012-08-28 | 0 | 0 | 0 | 0.01954 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 0R930 | SBD | 010 | REMOVE/REPLACE TWO CLOSURE POURS | 0.00532 | SHOPP | 2010 | 0133M | [5 empty] | 800000 | 60000 | 10000 | 10000 | C | 40000 | 70687.11 | 7.5% | 2012-02-01 | 2012-04-18 | 0 | 0 | 0 | 0.00532 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 0R950 | RIV | 371 | CONSTRUCT LEFT TURN LANE | 2.0182 | SHOPP | 2012 | 0259S | X |  |  |  |  | 636000 | 1125000 | 330000 | 484000 | 26000 | 285000 | 0 | 176.9% | 2015-02-16 | 2015-08-27 | 0.0069492 | 1.9765 | 0.034686 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 1C780 | RIV | 111 | BACKFILL AND STABILIZE SLOPE, REPAIR SHOULDERS, REPLACE GUARDRAIL | 0.01187 | SHOPP | 2012 | 0087A | [5 empty] | 300000 | 115000 | 10000 | 15000 | C | 90000 | 0 | 38.33% | 2012-09-14 | 2012-12-03 | 0 | 0 | 0 | 0.01187 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 1C820 | SBD | 062 | REPAIR PAVEMENT AND SHOULDERS. | 0.00767 | SHOPP | 2012 | 0227N | [5 empty] | 750000 | 125000 | 10000 | 20000 | C | 95000 | 0 | 16.67% | 2012-08-31 | 2012-09-28 | 0 | 0 | 0 | 0.00767 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 3564U | RIV | 071 | WIDEN BRIDGE | 0.013824 | SHOPP | 2000 | 0048Q | [5 empty] | 3075000 | 3621000 | 93000 | 1023000 | 131000 | 2374000 | 5755768.08 | 117.8% | 2000-06-08 | 2003-07-17 | 0 | 0 | 6.4472e-05 | 0.01376 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 4353U | RIV | 091 | WIDEN EXISTING HIGHWAY AND BRIDGES | 0.06925 | SHOPP | 2000 | 0080F | [5 empty] | 20390000 | 1900000 | 7000 | 107000 | 25000 | 1761000 | 6227690.8733 | 9.318% | 2001-05-31 | 2007-03-09 | 0 | 0 | 0 | 0.06925 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | 4437U | SBD | 210 | CONSTRUCT SIX LANE FREEWAY | 0.036809 | STIP | 2002 | 0194B | [5 empty] | 39067000 | 3591000 | N | N | N | 3591000 | 12150193.6216 | 9.192% | 2003-06-03 | 2005-03-11 | 0 | 0 | 0.022749 | 0.01406 | Caltrans | Caltrans | Caltrans | Caltrans
08 | SHOPP | MINOR |  |  | SHOPP MINOR | 32.4379 | MINOR
09 | SHOPP | 23770 | MNO | 395 | REALIGN & CURVE CORRECTION | 0.82703 | SHOPP | 2010 | 0601 | [5 empty] | 18398000 | 3760000 | E | 1770000 | 190000 | 1800000 | 3631774.02 | 20.44% | 2012-03-06 | 2012-12-01 | 0 | 0 | 0.0522 | 0.77483 | Caltrans | Caltrans | Caltrans | Caltrans
09 | SHOPP | 28750 | INY | 190 | ROCKFALL MITIGATION | 3.1755 | SHOPP | 2010 | 0388 |  |  |  | X |  | 8923000 | 2498000 | 680000 | 765000 | 80000 | 973000 | 1595594.29 | 28% | 2012-07-27 | 2014-03-15 | 0 | 0 | 0.00022 | 3.1752 | Caltrans | Caltrans | Caltrans | Caltrans
09 | SHOPP | 31660 | INY | 395 | ROADWAY REHABILITATION | 0.02547 | SHOPP | 2006 | 0442A | [5 empty] | 8478000 | 2468000 | 2468000 | F | F | F | 2537886.64 | 29.11% | 2008-09-10 | 2009-07-22 | 0 | 0 | 0.02354 | 0.00193 | Caltrans | Caltrans | Caltrans | Caltrans
09 | SHOPP | 33500 | MNO | 395 | MITIGATE MONO LAKE ROCKFALL | 1.7578 | SHOPP | 2012 | 0566 |  | X | X |  |  | 6058000 | 2820000 | 1120000 | 840000 | 90000 | 770000 | 661011.6 | 46.55% | 2014-06-15 | 2015-04-01 | 0 | 1.5523 | 0.20551 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
09 | SHOPP | 34090 | MNO | 395 | REHAB/REPLACE CULVERTS *MONO CULVERTS* | 2.7549 | SHOPP | 2012 | 0587 | X |  |  |  |  | 1375000 | 1610000 | 519000 | 498000 | 219000 | 374000 | 189036.38 | 117.1% | 2015-09-15 | 2016-05-17 | 1.81 | 0.84058 | 0.10428 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
09 | SHOPP | 34650 | MNO | 266 | CURVE CORRECTION/COLLISION SEVERITY REDUCTION | 0.85767 | SHOPP | 2012 | 0603 |  | X | X |  |  | 1560000 | 1220000 | 285000 | 370000 | 105000 | 460000 | 218102.58 | 78.21% | 2014-07-15 | 2014-12-01 | 0 | 0.47187 | 0.1936 | 0.1922 | Caltrans | Caltrans | Caltrans | Caltrans
09 | SHOPP | 34940 | MNO | 395 | CONSTRUCT 8 FOOT SHOULDERS | 3.22 | SHOPP PA
09 | SHOPP | 35080 | MON | 395 | SHOULDER WIDENING AND CONSTRUCT RUMBLE STRIP | 5.1747 | SHOPP | 2012 | 0604 | [5 empty] | 4406000 | 2390000 | 660000 | 850000 | 130000 | 750000 | 160993.08 | 54.24% | 2016-11-01 | 2017-11-01 | 4.0872 | 1.0791 | 0.00832 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
09 | SHOPP | 35120 | INY | 395 | SHOULDER WIDENING AND CONSTRUCT RUMBLE STRIP | 2.6902 | SHOPP | 2012 | 0605 | [5 empty] | 1866000 | 2001000 | 585000 | 670000 | 147000 | 599000 | 364314.39 | 107.2% | 2015-04-01 | 2015-12-01 | 0 | 2.2269 | 0.46329 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
09 | SHOPP | 35160 | INY | 395 | COLD IN-PLACE RECYCLE CAPM | 1.0909 | SHOPP | 2012 | 0609 | [5 empty] | 5573000 | 780000 | 130000 | 300000 | 5000 | 345000 | 0 | 14% | 2013-07-15 | 2014-09-01 | 0 | 0.6601 | 0.00959 | 0.42119 | Caltrans | Caltrans | Caltrans | Caltrans
09 | SHOPP | 35310 | MNO | 395 | CAP M | 0.97908 | SHOPP | 2012 | 0608 |  | X | X |  |  | 3466000 | 611000 | 45000 | 273000 | 6000 | 287000 | 0 | 17.63% | 2014-04-01 | 2014-12-01 | 0 | 0.59321 | 0.01319 | 0.37268 | Caltrans | Caltrans | Caltrans | Caltrans
09 | SHOPP | 35410 | MNO | 395 | CAP M | 1.1054 | SHOPP | 2012 | 0607 | [5 empty] | 2045000 | 441000 | E | 151000 | 5000 | 285000 | 0 | 21.56% | 2013-09-01 | 2014-12-01 | 0 | 0.18074 | 0 | 0.92462 | Caltrans | Caltrans | Caltrans | Caltrans
09 | SHOPP | 35690 | MNO | 108 | UPGRADE BARRIER APPROACH RAIL | 1.5682 | SHOPP | 2012 | 0612 | X |  |  |  |  | 3650000 | 1314000 | 180000 | 450000 | 9000 | 675000 | 0 | 36% | 2016-01-15 | 2017-01-15 | 0.51352 | 0.98997 | 0.06471 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
09 | SHOPP | MINOR |  |  | SHOPP MINOR | 15.7644 | MINOR
10 | SHOPP | 26444 | AMA | 088 | ROADWAY REHABILITATION. | 5.0602 | SHOPP | 2010 | 2300 | [5 empty] | 22531000 | 7615000 | 905000 | 3493000 | 974000 | 2243000 | 7497097 | 33.8% | 2012-04-10 | 2014-11-17 | 0 | 0 | 0.79413 | 4.266 | Caltrans | Caltrans | Caltrans | Caltrans
10 | SHOPP | 27980 | MER | 165 | HOT MIX ASPHALT OVERLAY TYPE B | 0.28617 | SHOPP | 2008 | 5858 | [5 empty] | 18101000 | 7672000 | 1898000 | 2900000 | 286000 | 2588000 | 6637535.56 | 42.38% | 2011-05-27 | 2012-03-07 | 0 | 0 | 0.09715 | 0.18902 | Caltrans | Caltrans | Caltrans | Caltrans
10 | SHOPP | 37930 | CAL | 012 | PAVEMENT REHABILITATION | 0.00986 | SHOPP | 2008 | 3387 | [5 empty] | 7189000 | 3866000 | 491000 | 1816000 | 365000 | 1194000 | 4133958.26 | 53.78% | 2010-05-05 | 2011-02-11 | 0 | 0 | 0 | 0.00986 | Caltrans | Caltrans | Caltrans | Caltrans
10 | SHOPP | 38151 | MER | 165 | AC OVERLAY, DIGOUTS, INTERSECTION IMPROVEMENTS & SHOULDER WIDENING | 4.415 | SHOPP | 2012 | 5917A |  | X | X |  |  | 9114000 | 4871000 | 818000 | 1753000 | 1475000 | 825000 | 3180.71 | 53.45% | 2014-02-05 | 2014-12-31 | 0 | 1.2038 | 1.1957 | 2.0155 | Caltrans | Caltrans | Caltrans | Caltrans
10 | SHOPP | 48100 | MER | 099 | WIDEN 15TH ST UC AND REPLACE EAST MERCED OH | 8.6948 | SHOPP | 2010 | 5415 | [5 empty] | 40352000 | 7845000 | 173000 | 3171000 | 249000 | 4252000 | 4390865.07 | 19.44% | 2012-01-19 | 2015-03-30 | 0 | 0 | 0.21106 | 8.4838 | Caltrans | Caltrans | Caltrans | Caltrans
10 | SHOPP | 49980 | AMA | 088 | WIDEN ROADWAY | 0.41707 | SHOPP | 2006 | 2505 | [5 empty] | 2329000 | 2245000 | 2245000 | F | F | F | 3336966.13 | 96.39% | 2008-04-23 | 2009-09-10 | 0 | 0 | 0.41707 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
10 | SHOPP | 0A010 | CAL | 004 | REALIGN AND WIDEN HIGHWAY WITH RHMA HMA AND AB | 0.43747 | SHOPP | 2008 | 3090 | [5 empty] | 3296000 | 1946000 | 567000 | 650000 | 270000 | 459000 | 2024718.52 | 59.04% | 2010-12-21 | 2012-11-02 | 0 | 0 | 0.24391 | 0.19356 | Caltrans | Caltrans | Caltrans | Caltrans
10 | SHOPP | 0A830 | SJ | 088 | UPGRADE BRIDGE APPROACH GUARDRAIL AND EXTEND CULVERTS 4 LOC. | 2.0827 | SHOPP | 2012 | 7550 |  | X | X |  |  | 2404000 | 1002000 | 178000 | 311000 | 102000 | 411000 | 1710457.67 | 41.68% | 2014-02-04 | 2014-10-01 | 0 | 0.28299 | 0.62494 | 1.1747 | Caltrans | Caltrans | Caltrans | Caltrans
10 | SHOPP | 0E930 | SJ | 026 | WIDEN, COLD PLANE AND OVERLAY | 0.35 | SHOPP | 2008 | 7453 | [5 empty] | 8629000 | 5101000 | 1917000 | 1389000 | 978000 | 817000 | 3199535.76 | 59.11% | 2011-05-13 | 2012-06-28 | 0.05 | 0.1 | 0.1 | 0.1 | Caltrans | Caltrans | Caltrans | Caltrans
10 | SHOPP | 0E940 | MER | 033 | OVERLAY AND REPLACE AC SURFACING | 0.06621 | SHOPP | 2010 | 5176 | [5 empty] | 2800000 | 1074000 | 225000 | 502000 | 24000 | 323000 | 651535.94 | 38.36% | 2010-12-13 | 2011-09-15 | 0 | 0 | 0.02244 | 0.04377 | Caltrans | Caltrans | Caltrans | Caltrans
10 | SHOPP | 0F280 | CAL | 004 | CONSTRUCT WALL FOR SEDIMENT CONTROL | 5.939 | SHOPP | 2012 | 3248 | X | X | X |  |  | 4437000 | 1941000 | 367000 | 605000 | 198000 | 771000 | 1150544.9 | 43.75% | 2014-11-26 | 2015-12-10 | 1.6597 | 2.2535 | 0.41835 | 1.6075 | Caltrans | Caltrans | Caltrans | Caltrans
10 | SHOPP | 0F740 | MER | 005 | GIRDER DIAPHRAGM RETROFIT | 1.7714 | SHOPP | 2012 | 0033 |  | X | X |  |  | 3500000 | 1148000 | 137000 | 428000 | 5000 | 578000 | 374548.84 | 32.8% | 2014-06-11 | 2016-02-01 | 0 | 1.5449 | 0.0145 | 0.21205 | Caltrans | Caltrans | Caltrans | Caltrans
10 | SHOPP | 0G350 | SJ | 012 | REPLACE BEARING PADS, JOINT SEALS | 1.2043 | SHOPP | 2012 | 7364 | [5 empty] | 2754000 | 1831000 | 801000 | 541000 | C | 489000 | 927089.71 | 66.49% | 2013-10-14 | 2014-08-01 | 0 | 0 | 0.01424 | 1.1901 | Caltrans | Caltrans | Caltrans | Caltrans
10 | SHOPP | 0G800 | SJ | 012 | ROADWAY REHABILITATION BY WIDENING THE SHOULDERS | 9.1976 | SHOPP | 2012 | 7352 | [5 empty] | 37047000 | 10244000 | 1391000 | 2310000 | 282000 | 6261000 | 3304291.22 | 27.65% | 2013-07-03 | 2017-05-25 | 0 | 0 | 0.12871 | 9.0689 | Caltrans | Caltrans | Caltrans | Caltrans
10 | SHOPP | 0G810 | SJ | 580 | PAVEMENT REPAIR & SHOULDER WIDENING | 2.1464 | SHOPP | 2012 | 7901 | [5 empty] | 15449000 | 2637000 | 17000 | 805000 | 9000 | 1806000 | 10322.9 | 17.07% | 2016-03-16 | 2018-08-01 | 0 | 2.1464 | 0 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
10 | SHOPP | 0J920 | SJ | 012 | REPLACE DAMAGED BEAM AND CONTROL HOUSE | 2.7121 | SHOPP | 2012 | 7353 |  | X |  |  |  | 3966000 | 1459000 | 410000 | 704000 | 1000 | 344000 | 990427.13 | 36.79% | 2014-04-09 | 2015-06-01 | 0 | 2.1576 | 0.00605 | 0.54841 | Caltrans | Caltrans | Caltrans | Caltrans
10 | SHOPP | 0K021 | MER | 099 | INSTALL ABOUT 220 TREES AND 800 GROUNDCOVER SHRUBS AND IRRIGATION | 2.174 | SHOPP | 2012 | 5423Y |  | X | X |  |  | 831000 | 979000 | 104000 | 563000 | 6000 | 306000 | 103860.03 | 117.8% | 2014-06-01 | 2018-08-01 | 0 | 2.1562 | 0.00174 | 0.01597 | Caltrans | Caltrans | Caltrans | Caltrans
10 | SHOPP | 0K330 | SJ | 005 | INSTALL TRAFFIC MONITORING STATIONS (TMS) AT VARIOUS LOCATIONS | 1.7809 | SHOPP | 2012 | 7161B |  |  |  | X |  | 3494000 | 995000 | 1000 | 370000 | 47000 | 577000 | 1383907.24 | 28.48% | 2013-02-20 | 2013-11-01 | 0 | 0 | 0.02302 | 1.7579 | Caltrans | Caltrans | Caltrans | Caltrans
10 | SHOPP | 0L970 | TUO | 120 | BRIDGE REHABILITATION | 5.9265 | SHOPP | 2012 | 0031 | [5 empty] | 13700000 | 2101000 | E | 1629000 | 4000 | 468000 | 34713.09 | 15.34% | 2015-06-01 | 2016-10-01 | 0 | 5.9244 | 0.00204 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
10 | SHOPP | 0M780 | SJ | 005 | ROADWAY REHABILITATION | 12.4876 | SHOPP | 2010 | 0268 | [5 empty] | 44497000 | 7924000 | 373000 | 2160000 | 91000 | 5300000 | 2601487.93 | 17.81% | 2012-12-10 | 2016-02-01 | 0 | 0 | 0.00198 | 12.4856 | Caltrans | Caltrans | Caltrans | Caltrans
10 | SHOPP | 0M800 | STA | 099 | HIGHWAY REHABILITATION | 4.0769 | SHOPP | 2010 | 0283 |  |  |  | X |  | 91400000 | 4571000 | 35000 | 724000 | 12000 | 3800000 | 1777790.72 | 5.001% | 2012-02-13 | 2014-05-16 | 0 | 0 | 0 | 4.0769 | Caltrans | Caltrans | Caltrans | Caltrans
10 | SHOPP | 0N830 | SJ | L5721 | INSTALL DESIGNED SOIL REMEDIATION | 0.21223 | SHOPP | 2012 | 0123 | [5 empty] | 430000 | 280000 | E | 184000 | 3000 | 93000 | 133990.71 | 65.12% | 2013-05-10 | 2015-05-24 | 0 | 0 | 0.0095 | 0.20273 | Caltrans | Caltrans | Caltrans | Caltrans
10 | SHOPP | 0N910 | SJ | 099 | REPLACE HIGHWAY PLANTING | 0.06953 | SHOPP | 2008 | 0122 | [5 empty] | 662000 | 726000 | 156000 | 307000 | 79000 | 184000 | 525898.56 | 109.7% | 2009-01-28 | 2012-06-01 | 0 | 0 | 0.01094 | 0.05859 | Caltrans | Caltrans | Caltrans | Caltrans
10 | SHOPP | 0P600 | SJ | 088 | RHMA OVERLAY AND MODIFY SIGNALS | 0.25823 | SHOPP | 2010 | 0152 | [5 empty] | 3693000 | 1104000 | 273000 | 380000 | 10000 | 441000 | 298859.09 | 29.89% | 2011-11-22 | 2012-10-30 | 0 | 0 | 0.09762 | 0.16061 | Caltrans | Caltrans | Caltrans | Caltrans
10 | SHOPP | 0P670 | TUO | L5724 | EVALUATE CONTAMINATION & CLEANUP OF SOIL AND GROUNDWATER | 0.63093 | SHOPP | 2012 | 0155 |  | X | X |  |  | 205000 | 349000 | 87000 | 199000 | 7000 | 56000 | 101233.32 | 170.2% | 2014-01-13 | 2014-10-01 | 0 | 0.39652 | 0.00181 | 0.2326 | Caltrans | Caltrans | Caltrans | Caltrans
10 | SHOPP | 0P800 | MER | 140 | BRIDGE SCOUR MITIGATION | 1.5887 | SHOPP | 2012 | 0330 | X |  |  |  |  | 1200000 | 1256000 | 430000 | 380000 | 6000 | 440000 | 11390.36 | 104.7% | 2015-07-08 | 2016-09-05 | 0.40599 | 1.1618 | 0.02089 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
10 | SHOPP | 0P920 | MPA | 140 | CLEAR LANDSLIDE | 17.9156 | SHOPP | 2012 | 0280 | X |  |  |  |  | 110300000 | 18800000 | 5600000 | 5400000 | 200000 | 7600000 | 6641158.57 | 17.04% | 2015-12-09 | 2019-01-02 | 0.90869 | 16.5889 | 0.41809 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
10 | SHOPP | 0Q170 | SJ | 580 | DIGOUT AND REPAIR OF LOCALIZED FAILURES/AC OVERLAY | 2.0092 | SHOPP | 2012 | 0164 | [5 empty] | 19907000 | 1706000 | 41000 | 501000 | 13000 | 1151000 | 0 | 8.57% | 2015-04-01 | 2016-08-01 | 0 | 2.0069 | 0.00232 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
10 | SHOPP | 0Q220 | AMA | 088 | AC OVERLAY AND DIGOUTS | 0.93302 | SHOPP | 2012 | 0168 | X |  |  |  |  | 8775000 | 1161000 | 133000 | 499000 | 13000 | 516000 | 0 | 13.23% | 2015-05-25 | 2017-03-01 | 0.00175 | 0.93091 | 0.00036 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
10 | SHOPP | 0Q290 | MER | 165 | IMPROVE CURVE RADIUS, SUPERELEVATION, WIDEN SHOULDER, | 6.0658 | SHOPP | 2012 | 0262 | X |  |  |  |  | 3395000 | 2431000 | 528000 | 871000 | 285000 | 747000 | 171327.66 | 71.61% | 2016-04-07 | 2016-12-15 | 1.9953 | 3.852 | 0.21856 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
10 | SHOPP | 0Q610 | MPA | 049 | WIDEN ROADWAY FOR LEFT TURN CHANNELIZATION | 0.06899 | SHOPP | 2010 | 0263 | [5 empty] | 1973000 | 859000 | E | 513000 | 1000 | 345000 | 730240.34 | 43.54% | 2012-01-05 | 2012-07-30 | 0 | 0 | 0 | 0.06899 | Caltrans | Caltrans | Caltrans | Caltrans
10 | SHOPP | 0S190 | MER | 005 | WEIGH STATION IMPROVEMENTS | 0.79696 | SHOPP | 2010 | 0246 |  |  |  | X |  | 1723000 | 1279000 | 209000 | 697000 | 2000 | 371000 | 1178191.66 | 74.23% | 2012-02-27 | 2013-07-24 | 0 | 0 | 0 | 0.79696 | Caltrans | Caltrans | Caltrans | Caltrans
10 | SHOPP | 0S720 | AMA | 049 | ASPHALT CONCRETE OVERLAY | 2.1284 | SHOPP | 2012 | 0339 |  |  | X |  |  | 4094000 | 795000 | 40000 | 381000 | 7000 | 367000 | 0 | 19.42% | 2015-02-04 | 2016-02-18 | 0 | 2.1079 | 0.02047 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
10 | SHOPP | 0S790 | SJ | 132 | CONSTRUCT LEFT TURN CHANNELIZATION | 0.1086 | SHOPP | 2010 | 0241 | [5 empty] | 1225000 | 789000 | E | 407000 | 6000 | 376000 | 482666.25 | 64.41% | 2011-11-30 | 2012-10-02 | 0 | 0 | 0.02384 | 0.08476 | Caltrans | Caltrans | Caltrans | Caltrans
10 | SHOPP | 0S800 | STA | 108 | EXPRESSWAY ON NEW ALIGNMENT | 7.5912 | PARTNERSHIP
10 | SHOPP | 0S860 | SJ | 099 | HOTMIX ASPHALT OVERLAY | 0.2716 | SHOPP | 2010 | 0289 | [5 empty] | 1000000 | 671000 | 92000 | 317000 | 6000 | 256000 | 436120.95 | 67.1% | 2012-08-22 | 2013-06-30 | 0 | 0 | 0.07016 | 0.20144 | Caltrans | Caltrans | Caltrans | Caltrans
10 | SHOPP | 0S870 | STA | 004 | SHOULDER WIDENING WITH RUMBLE STRIPS | 2.2699 | SHOPP | 2012 | 0287 |  | X | X |  |  | 624000 | 977000 | 367000 | 408000 | 7000 | 195000 | 182452.74 | 156.6% | 2014-05-19 | 2015-04-22 | 0 | 2.2381 | 0.03177 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
10 | SHOPP | 0S940 | MER | 152 | INSTALL DOUBLE THRIE BEAM BARRIER IN CENTER MEDIAN | 0.92638 | SHOPP | 2010 | 0261 |  |  |  | X |  | 4250000 | 2228000 | 150000 | 773000 | 10000 | 1295000 | 603469.54 | 52.42% | 2012-10-03 | 2013-10-01 | 0 | 0 | 0.00078 | 0.9256 | Caltrans | Caltrans | Caltrans | Caltrans
10 | SHOPP | 0T040 | AMA | 104 | HIGHWAY RAIL GRADE CROSSING WARNING DEVICE | 0.81318 | SHOPP | 2012 | 0269 |  |  |  | X |  | 433000 | 325000 | E | 188000 | 28000 | 109000 | 46603.38 | 75.06% | 2013-05-01 | 2013-11-01 | 0 | 0 | 0.10707 | 0.70611 | Caltrans | Caltrans | Caltrans | Caltrans
10 | SHOPP | 0T140 | AMA | 049 | INSTALL NEW SIGNAL | 0.83193 | SHOPP | 2012 | 0343 |  |  |  | X |  | 579000 | 730000 | E | 428000 | 48000 | 254000 | 445198.1 | 126.1% | 2013-01-18 | 2013-12-16 | 0 | 0 | 0.09532 | 0.73661 | Caltrans | Caltrans | Caltrans | Caltrans
10 | SHOPP | 0T160 | SJ | 026 | HORIZONTAL CURVE REALIGNMENT | 4.8193 | SHOPP | 2012 | 0264 | [5 empty] | 3620000 | 2429000 | 576000 | 904000 | 145000 | 804000 | 990758.77 | 67.1% | 2013-11-06 | 2014-09-23 | 0 | 0 | 0.37995 | 4.4393 | Caltrans | Caltrans | Caltrans | Caltrans
10 | SHOPP | 0T230 | SJ | 004 | TRAFFIC CONTROL INSTALLATION AND WIDENING SHOULDER | 3.2125 | SHOPP | 2012 | 0255 |  |  |  | X |  | 748000 | 1128000 | E | 763000 | C | 365000 | 268129.49 | 150.8% | 2013-09-04 | 2014-02-02 | 0 | 0.34477 | 0 | 2.8678 | Caltrans | Caltrans | Caltrans | Caltrans
10 | SHOPP | 0T780 | STA | 132 | INSTALL TRAFFIC SIGNALS AND ROADWAY WIDENING | 3.5229 | SHOPP | 2012 | 0348 | X |  |  |  |  | 3753000 | 2455000 | 464000 | 1190000 | 280000 | 521000 | 10167.41 | 65.41% | 2015-10-15 | 2016-12-01 | 0.04441 | 2.9916 | 0.45526 | 0.0316 | Caltrans | Caltrans | Caltrans | Caltrans
10 | SHOPP | 0T800 | AMA | 012 | INSTALL ADA CURB RAMPS | 1.3126 | SHOPP | 2012 | 0267 | [5 empty] | 805000 | 1496000 | E | 722000 | 371000 | 403000 | 689505.48 | 185.8% | 2012-07-04 | 2014-07-18 | 0 | 0 | 0.37793 | 0.93464 | Caltrans | Caltrans | Caltrans | Caltrans
10 | SHOPP | 0T820 | SJ | 005 | INSTALL ADA CURB RAMPS | 1.799 | SHOPP | 2012 | 0266 | [5 empty] | 1121000 | 795000 | E | 336000 | 175000 | 284000 | 232458.91 | 70.92% | 2014-11-01 | 2015-12-01 | 0 | 1.2957 | 0.50332 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
10 | SHOPP | 0U280 | AMA | 088 | INSTALL CENTERLINE RUMBLE STRIPS | 0.62455 | SHOPP | 2012 | 0344 | [5 empty] | 652000 | 413000 | E | 280000 | 2000 | 131000 | 102471.1 | 63.34% | 2013-09-01 | 2014-07-01 | 0 | 0 | 0 | 0.62455 | Caltrans | Caltrans | Caltrans | Caltrans
10 | SHOPP | 0U290 | MER | 165 | INSTALL LEFT TURN CHANNELIZATION | 1.5047 | SHOPP | 2012 | 3006 | [5 empty] | 1263000 | 1393000 | 308000 | 611000 | 135000 | 339000 | 317236.57 | 110.3% | 2015-07-01 | 2016-02-01 | 0 | 1.2068 | 0.20707 | 0.09089 | Caltrans | Caltrans | Caltrans | Caltrans
10 | SHOPP | 0U360 | CAL | 004 | HIGHWAY PLANTING | 0.40739 | STIP | 2008 | 0253 |  |  |  | X |  | 845000 | 200000 | H | H | H | 200000 | 79483.95 | 23.67% | 2010-06-29 | 2014-05-14 | 0 | 0 | 0 | 0.40739 | Caltrans | Caltrans | Caltrans | Caltrans
10 | SHOPP | 0U500 | MER | 005 | INSTALL DOUBLE BEAM BARRIER (DTBB) IN THE CENTER MEDIAN | 1.4627 | SHOPP | 2012 | 0347 |  |  |  | X |  | 654000 | 605000 | E | 370000 | 3000 | 232000 | 184818.49 | 92.51% | 2013-04-15 | 2013-12-01 | 0 | 0.00184 | 0.00853 | 1.4523 | Caltrans | Caltrans | Caltrans | Caltrans
10 | SHOPP | 0U520 | MER | 059 | INSTALL LEFT TURN CHANNELIZATION | 3.2507 | SHOPP | 2012 | 3005 | X |  |  |  |  | 2318000 | 2393000 | 699000 | 727000 | 598000 | 369000 | 7302.82 | 103.2% | 2016-06-15 | 2017-06-29 | 2.5497 | 0.54318 | 0.15783 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
10 | SHOPP | 0U610 | SJ | 012 | REMOVE & REPLACE EXISTING CONCRETE BRIDGE DECK & REPLACE JOINT SEALS | 2.3954 | SHOPP | 2012 | 0295 | [5 empty] | 2200000 | 1173000 | 172000 | 352000 | 81000 | 568000 | 34068.61 | 53.32% | 2013-08-07 | 2014-12-31 | 0 | 0.28384 | 0.03368 | 2.0778 | Caltrans | Caltrans | Caltrans | Caltrans
10 | SHOPP | 0V170 | SJ | 005 | HOT MIX ASPHALT OVERLAY | 0.52685 | SHOPP | 2008 | 0271 | [5 empty] | 32000000 | 2597000 | 25000 | 500000 | 10000 | 2062000 | 2207808.78 | 8.116% | 2010-12-03 | 2012-09-25 | 0 | 0 | 0 | 0.52685 | Caltrans | Caltrans | Caltrans | Caltrans
10 | SHOPP | 0V290 | CAL | 026 | INSTALL A TWO-WAY LEFT-TURN LANE | 2.4087 | SHOPP | 2012 | 3000 | X |  |  |  |  | 1646000 | 1950000 | 442000 | 554000 | 531000 | 423000 | 62483.52 | 118.5% | 2015-07-13 | 2015-12-31 | 0.04724 | 1.2493 | 1.1121 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
10 | SHOPP | 0V300 | CAL | 004 | PEDESTRIAN ACCESSIBILITY IMPROVEMENTS | 2.0992 | SHOPP | 2012 | 0332 | X |  |  |  |  | 1780000 | 1257000 | 240000 | 540000 | 126000 | 351000 | 0 | 70.62% | 2015-11-12 | 2016-12-30 | 1.5245 | 0.53396 | 0.03675 | 0.00395 | Caltrans | Caltrans | Caltrans | Caltrans
10 | SHOPP | 0V490 | TUO | 108 | STORM WATER MITIGATION | 2.5777 | SHOPP | 2012 | 0334 |  | X | X |  |  | 1200000 | 998000 | E | 694000 | 2000 | 302000 | 2702.27 | 83.17% | 2014-04-01 | 2014-12-01 | 0 | 2.1264 | 0.00276 | 0.44856 | Caltrans | Caltrans | Caltrans | Caltrans
10 | SHOPP | 0V620 | CAL | 026 | SIGNALIZATION AND CHANNELIZATION | 3.021 | SHOPP | 2012 | 3004 | X |  |  |  |  | 1633000 | 1951000 | 577000 | 709000 | 314000 | 351000 | 44415.04 | 119.5% | 2016-05-20 | 2017-06-30 | 1.9683 | 0.99429 | 0.05844 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
10 | SHOPP | 0V680 | STA | 120 | CAP M | 2.9358 | SHOPP | 2012 | 0341 |  | X |  |  |  | 4997000 | 1228000 | E | 772000 | 2000 | 454000 | 2456.55 | 24.57% | 2014-04-01 | 2014-12-01 | 0 | 2.244 | 0.00262 | 0.68913 | Caltrans | Caltrans | Caltrans | Caltrans
10 | SHOPP | 0V870 | SJ | 099 | PCC GRIND AND OVERLAY | 0.04497 | SHOPP | 2010 | 0294 | [5 empty] | 2505000 | 529000 | 42000 | 311000 | 5000 | 171000 | 455771 | 21.12% | 2011-11-17 | 2012-12-20 | 0 | 0 | 0.00166 | 0.04331 | Caltrans | Caltrans | Caltrans | Caltrans
10 | SHOPP | 0W070 | TUO | 120 | REPLACE BRIDGE DECK | 1.3533 | SHOPP | 2012 | 0301 | [5 empty] | 2885000 | 1196000 | 276000 | 438000 | 14000 | 468000 | 211724.57 | 41.46% | 2012-12-31 | 2014-12-30 | 0 | 0 | 0.0393 | 1.314 | Caltrans | Caltrans | Caltrans | Caltrans
10 | SHOPP | 0W120 | SJ | 004 | REHABILITATE EXISTING ASPHALT CONCRETE PAVEMENT (HMA OVERLAY) | 4.0549 | SHOPP | 2012 | 0302 | [5 empty] | 7738000 | 2236000 | H | 236000 | 454000 | 1546000 | 96849.46 | 28.9% | 2013-10-23 | 2015-11-06 | 0 | 0.31676 | 0.37056 | 3.3675 | Caltrans | Caltrans | Caltrans | Caltrans
10 | SHOPP | 0W360 | AMA | 049 | INSTALL TRAFFIC SIGNALS INTERSECTION IMPROVEMENTS | 2.326 | SHOPP | 2012 | 0331 |  | X | X |  |  | 658000 | 896000 | 238000 | 434000 | 9000 | 215000 | 2634.05 | 136.2% | 2014-09-22 | 2015-10-28 | 0.13474 | 2.1632 | 0.02808 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
10 | SHOPP | 0W560 | SJ | 012 | REPAIR STRUCTURAL SECTION | 1.6186 | SHOPP | 2012 | 0323 | [5 empty] | 7779000 | 1454000 | 36000 | 670000 | 9000 | 739000 | 6425.24 | 18.69% | 2015-07-22 | 2017-08-15 | 0 | 1.6182 | 0.00044 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
10 | SHOPP | 0W690 | SJ | 004 | REPLACE JOINT SEALS, BEARING PADS & TREAT BRIDGE DECKS | 1.9239 | SHOPP | 2012 | 0346 | X | X | X |  |  | 3047000 | 1061075 | 137000 | 354000 | 1075 | 569000 | 0 | 34.82% | 2014-06-09 | 2014-12-31 | 0.32435 | 1.5963 | 0.00321 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
10 | SHOPP | 0X300 | MER | 140 | INSTALL FLASHING BEACONS | 2 | SHOPP PA
10 | SHOPP | 0X320 | MER | 165 | INSTALL RUMBLE STRIPS | 2 | SHOPP PA
10 | SHOPP | 2A290 | STA | 033 | REPLACE BRIDGE | 0.12699 | SHOPP | 2008 | 0032 | [5 empty] | 2011000 | 1964000 | 172000 | 1003000 | 159000 | 630000 | 2146566.49 | 97.66% | 2010-12-09 | 2012-02-07 | 0 | 0 | 0.00057 | 0.12642 | Caltrans | Caltrans | Caltrans | Caltrans
10 | SHOPP | 2A420 | CAL | 026 | PLACE HMA, AB AND WIDEN ROADWAY | 1.5734 | SHOPP | 2010 | 7498 |  |  |  | X |  | 19089000 | 5715000 | 845000 | 1805000 | 1433000 | 1632000 | 5685551.52 | 29.94% | 2011-06-27 | 2013-10-01 | 0 | 0 | 1.2313 | 0.34207 | Caltrans | Caltrans | Caltrans | Caltrans
10 | SHOPP | MINOR |  |  | SHOPP MINOR | 23.9109 | MINOR
11 | SHOPP | 00270 | SD | 005 | CONSTRUCT AUXILIARY LANES/ WIDEN CONNECTOR | 7.579 | SHOPP | 2012 | 0778 |  | X |  |  |  | 9468000 | 7452000 | 2452000 | 2700000 | 200000 | 2100000 | 4183960.91 | 78.71% | 2013-11-16 | 2015-08-24 | 0 | 1.1272 | 0.09345 | 6.3583 | Caltrans | Caltrans | Caltrans | Caltrans
11 | SHOPP | 06381 | SD | 008 | HIGHWAY PLANTING/IRRIGATION SYSTEM FOR PPNO 0187P | 0.758 | SHOPP | 2012 | 0187Y | [5 empty] | 1697000 | 544000 | H | 305000 | 10000 | 229000 | 300951.03 | 32.06% | 2013-04-14 | 2017-07-07 | 0 | 0 | 0 | 0.758 | Caltrans | Caltrans | Caltrans | Caltrans
11 | SHOPP | 07040 | SD | 015 | PLANTING AND IRRIGATION | 0.10045 | SHOPP | 2006 | 0425L | [5 empty] | 5665000 | 1091000 | 1091000 | F | F | F | 1195923.57 | 19.26% | 2007-09-10 | 2012-04-11 | 0 | 0 | 0 | 0.10045 | Caltrans | Caltrans | Caltrans | Caltrans
11 | SHOPP | 07670 | IMP | M5708 | CONSTRUCT MAINTENANCE STATION | 2.9599 | SHOPP | 2012 | 0972 | [5 empty] | 11783000 | 5847000 | 1090000 | 2858000 | 321000 | 1578000 | 4352183.89 | 49.62% | 2013-08-08 | 2016-11-06 | 0 | 0.12468 | 0 | 2.8353 | Caltrans | Caltrans | Caltrans | Caltrans
11 | SHOPP | 08023 | IMP | 098 | WIDEN HIGHWAY | 4.0636 | STIP | 2012 | 0549A | [5 empty] | 6605000 | 2752000 | H | 728000 | 650000 | 1374000 | 2481786.3603 | 41.67% | 2015-04-16 | 2017-01-05 | 0 | 2.0488 | 2.0148 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
11 | SHOPP | 08165 | SD | 805 | LANDSCAPE AND INSTALL IRRIGATION | 0.22782 | SHOPP | 2010 | 0948Y | [5 empty] | 700000 | 513359 | H | 219235 | 10000 | 284124 | 408924.18 | 73.34% | 2011-06-24 | 2015-10-01 | 0 | 0 | 0 | 0.22782 | Caltrans | Caltrans | Caltrans | Caltrans
11 | SHOPP | 23640 | SD | 008 | HOT MIX ASPHALT PAVEMENT REHABILITATION | 0.29258 | SHOPP | 2010 | 0635 | [5 empty] | 5200000 | 1336000 | 104000 | 510000 | 2000 | 720000 | 552499.42 | 25.69% | 2010-12-07 | 2013-03-29 | 0 | 0 | 0 | 0.29258 | Caltrans | Caltrans | Caltrans | Caltrans
11 | SHOPP | 23840 | IMP | 007 | PAVEMENT REHABILITATION | 0.55464 | SHOPP | 2012 | 0500 |  | X |  |  |  | 11397000 | 3832000 | E | 1474000 | 7000 | 2351000 | 48225.51 | 33.62% | 2014-09-04 | 2015-09-03 | 0 | 0.55464 | 0 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
11 | SHOPP | 23860 | SD | 052 | PAVEMENT REHABILITATION | 5.524 | SHOPP | 2010 | 0696 | [5 empty] | 14953000 | 3231000 | E | 1093000 | 4000 | 2134000 | 867004.48 | 21.61% | 2012-10-25 | 2015-01-03 | 0 | 0 | 0 | 5.524 | Caltrans | Caltrans | Caltrans | Caltrans
11 | SHOPP | 23960 | SD | 005 | HIGHWAY PLANTING RESTORATION | 0.08064 | SHOPP | 2006 | 0605 |  |  |  | X |  | 2575000 | 1012000 | 1012000 | F | F | F | 1175306.46 | 39.3% | 2007-10-12 | 2013-07-15 | 0 | 0 | 0 | 0.08064 | Caltrans | Caltrans | Caltrans | Caltrans
11 | SHOPP | 24010 | SD | 005 | PAVEMENT REHABILITATION | 0.07088 | SHOPP | 2010 | 0624 | [5 empty] | 23555000 | 3613000 | 471000 | 1177000 | 5000 | 1960000 | 2387085.94 | 15.34% | 2011-01-10 | 2012-01-05 | 0 | 0 | 0 | 0.07088 | Caltrans | Caltrans | Caltrans | Caltrans
11 | SHOPP | 24320 | SD | 008 | RESTORE SAFETY ROADSIDE REST | 0.01217 | SHOPP | 2008 | 0643 | [5 empty] | 3028000 | 1050000 | 144000 | 435000 | 6000 | 465000 | 3436607.45 | 34.68% | 2010-01-12 | 2012-06-04 | 0 | 0 | 0 | 0.01217 | Caltrans | Caltrans | Caltrans | Caltrans
11 | SHOPP | 26041 | SD | 008 | DRAINAGE IMPROVEMENTS | 2.4989 | SHOPP | 2012 | 0651 |  | X | X |  |  | 5433000 | 1728000 | 262000 | 523000 | 2000 | 941000 | 107940.7177 | 31.81% | 2014-07-24 | 2015-11-11 | 0 | 2.492 | 0.00684 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
11 | SHOPP | 26042 | SD | 008 | DRAINAGE IMPROVEMENTS | 0.00834 | SHOPP | 2010 | 0651A | [5 empty] | 591000 | 240000 | 106000 | 50000 | 2000 | 82000 | 390718.6923 | 40.61% | 2012-06-27 | 2012-12-03 | 0 | 0 | 0 | 0.00834 | Caltrans | Caltrans | Caltrans | Caltrans
11 | SHOPP | 26140 | SD | 005 | REPLACE BUILDINGS | 1.7689 | SHOPP | 2008 | 0897 |  |  |  | X |  | 7247000 | 3519000 | 236000 | 2516000 | 12000 | 755000 | 5440738.18 | 48.56% | 2011-04-27 | 2013-12-08 | 0 | 0 | 0 | 1.7689 | Caltrans | Caltrans | Caltrans | Caltrans
11 | SHOPP | 26160 | SD | 005 | FREEWAY MAINTENANCE ACCESS | 4.3088 | SHOPP | 2012 | 0877 |  | X | X |  |  | 5110000 | 1850000 | 450000 | 650000 | 25000 | 725000 | 50533.05 | 36.2% | 2014-10-18 | 2016-04-20 | 0 | 4.1735 | 0.13524 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
11 | SHOPP | 26170 | SD | 008 | FREEWAY MAINTENANCE ACCESS PAVING | 0.04322 | SHOPP | 2008 | 0648 | [5 empty] | 1320000 | 470000 | 66000 | 185000 | 4000 | 215000 | 524229.52 | 35.61% | 2010-08-10 | 2013-03-15 | 0 | 0 | 0 | 0.04322 | Caltrans | Caltrans | Caltrans | Caltrans
11 | SHOPP | 26200 | SD | 075 | PAVEMENT REHABILITATION OF MAINLINE AND SHOULDERS | 0.12162 | SHOPP | 2010 | 0752 | [5 empty] | 1800000 | 826000 | E | 410000 | C | 416000 | 895264.7 | 45.89% | 2012-01-05 | 2013-06-07 | 0 | 0 | 0 | 0.12162 | Caltrans | Caltrans | Caltrans | Caltrans
11 | SHOPP | 26400 | IMP | 008 | REHABILITATE BRIDGE | 0.09453 | SHOPP | 2008 | 0521 | [5 empty] | 7485000 | 1151000 | 208000 | 240000 | 27000 | 676000 | 2509197.82 | 15.38% | 2010-10-12 | 2012-08-10 | 0 | 0 | 0 | 0.09453 | Caltrans | Caltrans | Caltrans | Caltrans
11 | SHOPP | 26530 | SD | 015 | PAVEMENT REHABILITATION | 0.18091 | SHOPP | 2010 | 0691 | [5 empty] | 7156000 | 2196000 | E | 951000 | 8000 | 1237000 | 1392767.89 | 30.69% | 2012-02-03 | 2012-11-27 | 0 | 0 | 0 | 0.18091 | Caltrans | Caltrans | Caltrans | Caltrans
11 | SHOPP | 26610 | IMP | 008 | PAVEMENT REHABILITATION OF MAINLINE, SHOULDERS, AND RAMPS | 0.74676 | SHOPP | 2010 | 0522 |  |  |  | X |  | 13442000 | 2068000 | E | 669000 | 1000 | 1398000 | 1027177.32 | 15.38% | 2011-12-14 | 2013-07-18 | 0 | 0 | 0 | 0.74676 | Caltrans | Caltrans | Caltrans | Caltrans
11 | SHOPP | 26930 | SD | 056 | INSTALL RAMP METERS,CCTV'S,LOOPS, CMS AND OTHER TSM EQUIPMENT. | 4.4992 | SHOPP | 2010 | 0725 |  |  |  | X |  | 8473000 | 3102000 | 435000 | 1105000 | 7000 | 1555000 | 1731033.58 | 36.61% | 2012-12-19 | 2014-03-21 | 0 | 0 | 0.00028 | 4.4989 | Caltrans | Caltrans | Caltrans | Caltrans
11 | SHOPP | 27030 | SD | 079 | INSTALL NEW CULVERTS | 0.2032 | SHOPP | 2006 | 0806 | [5 empty] | 552098 | 1149874 | S | 841204 | S | 308670 | 1150124.4 | 208.3% | 2008-02-04 | 2008-10-09 | 0 | 0 | 0 | 0.2032 | Caltrans | Caltrans | Caltrans | Caltrans
11 | SHOPP | 27080 | SD | 005 | CULVERT REHABILITATION | 0.68509 | SHOPP | 2010 | 0876 |  |  |  | X |  | 4571000 | 2783000 | 666000 | 751000 | 481000 | 885000 | 1531025.19 | 60.88% | 2012-09-27 | 2014-01-29 | 0 | 0 | 0 | 0.68509 | Caltrans | Caltrans | Caltrans | Caltrans
11 | SHOPP | 27340 | SD | 076 | BRIDGE REPLACEMENT (SCOUR) | 0.3216 | SHOPP | 2008 | 0762 |  |  |  | X |  | 6888000 | 3235000 | 717000 | 1435000 | 133000 | 950000 | 4104404.33 | 46.97% | 2010-12-28 | 2013-08-22 | 0 | 0 | 0.03139 | 0.29021 | Caltrans | Caltrans | Caltrans | Caltrans
11 | SHOPP | 27520 | IMP | 098 | PAVEMENT REHABILITATION (AC OVERLAY | 0.70991 | SHOPP | 2012 | 0552 |  |  |  | X |  | 5440000 | 2160000 | E | 1050000 | 10000 | 1100000 | 329359.46 | 39.71% | 2013-03-09 | 2013-07-17 | 0 | 0 | 0 | 0.70991 | Caltrans | Caltrans | Caltrans | Caltrans
11 | SHOPP | 27550 | SD | 067 | PAVEMENT REHABILITATION OF MAINLINE SHOULDERS, AND RAMPS. | 3.9002 | SHOPP | 2012 | 0744 |  | X |  |  |  | 22005000 | 2456000 | E | 804000 | 5000 | 1647000 | 298816.74 | 11.16% | 2014-04-24 | 2015-03-29 | 0 | 2.4235 | 0 | 1.4766 | Caltrans | Caltrans | Caltrans | Caltrans
11 | SHOPP | 27560 | SD | 015 | UPGRADE ELECTRICAL AND MODIFY OFFICE | 0.84225 | SHOPP | 2012 | 0853 |  | X |  |  |  | 645000 | 709000 | 180000 | 355000 | 1000 | 173000 | 199753.81 | 109.9% | 2014-01-04 | 2014-07-29 | 0 | 0.37527 | 0 | 0.46698 | Caltrans | Caltrans | Caltrans | Caltrans
11 | SHOPP | 28080 | SD | 078 | INSTALL RUMBLE STRIPS AND UPGRADE END TREATMENTS | 0.01582 | SHOPP | 2010 | 0837 | [5 empty] | 2200000 | 612000 | E | 350000 | 10000 | 252000 | 658722.49 | 27.82% | 2011-12-06 | 2012-05-14 | 0 | 0 | 0 | 0.01582 | Caltrans | Caltrans | Caltrans | Caltrans
11 | SHOPP | 28101 | SD | 076 | INSTALL RUMBLE STRIP,REPLACE MBGR AND UPGRADE END TREATMENTS | 0.0105 | SHOPP | 2010 | 0727 | [5 empty] | 1012000 | 233000 | E | 110000 | 8000 | 115000 | 442573.07 | 23.02% | 2011-05-05 | 2012-04-06 | 0 | 0 | 0 | 0.0105 | Caltrans | Caltrans | Caltrans | Caltrans
11 | SHOPP | 28230 | SD | 005 | STORM WATER DETENTION BASINS RETROFIT | 1.8151 | SHOPP | 2012 | 0909 | X |  |  |  |  | 1303000 | 820000 | 241000 | 260000 | 31000 | 288000 | 34096.09 | 62.93% | 2015-06-03 | 2016-08-31 | 1.2731 | 0.49655 | 0.04551 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
11 | SHOPP | 28240 | SD | 015 | STORM WATER MITIGATION - CONSTRUCT SAND FILTERS AND INFILTRATION | 4.8779 | SHOPP | 2012 | 0943 | [5 empty] | 13985000 | 3924000 | 525000 | 1301000 | 39000 | 2059000 | 503572.36 | 28.06% | 2013-08-21 | 2014-12-09 | 0 | 0.31186 | 0 | 4.566 | Caltrans | Caltrans | Caltrans | Caltrans
11 | SHOPP | 28250 | SD | 005 | STORM WATER MITIGATION STORM WATER MITIGATION, CONSTRUCT SAND FILTERS | 4.0525 | SHOPP | 2012 | 0944 |  | X | X |  |  | 16690000 | 4491000 | 258000 | 1591000 | 127000 | 2515000 | 30393.7 | 26.91% | 2014-06-07 | 2015-09-25 | 0 | 3.8363 | 0.21616 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
11 | SHOPP | 28340 | SD | 005 | CONSTRUCT CURB RAMPS | 0.02014 | SHOPP | 2008 | 0843 | [5 empty] | 3150000 | 1377000 | 300000 | 468000 | 9000 | 600000 | 2177535.38 | 43.71% | 2010-07-15 | 2011-06-30 | 0 | 0 | 0 | 0.02014 | Caltrans | Caltrans | Caltrans | Caltrans
11 | SHOPP | 28460 | SD | 005 | UPGRADE MEDIAN GUARD RAIL | 0.26156 | SHOPP | 2008 | 0658 | [5 empty] | 10000000 | 3059000 | E | 1530000 | 4000 | 1525000 | 2755010.06 | 30.59% | 2010-10-11 | 2012-05-02 | 0 | 0 | 0 | 0.26156 | Caltrans | Caltrans | Caltrans | Caltrans
11 | SHOPP | 28620 | IMP | 111 | ROADWAY WIDENING AND INSTALLATION OF TRAFFIC SIGNALS | 0.0066 | PARTNERSHIP | [6 empty] | O
11 | SHOPP | 28770 | SD | L5506 | UPGRADE MATERIALS LAB FACILITY | 3.9753 | SHOPP | 2012 | 0729 | [5 empty] | 3248000 | 1727000 | 242000 | 850000 | 5000 | 630000 | 1144026.01 | 53.17% | 2013-08-08 | 2014-09-18 | 0 | 0.11959 | 0.00411 | 3.8516 | Caltrans | Caltrans | Caltrans | Caltrans
11 | SHOPP | 28790 | SD | 094 | RECONSTRUCT METAL BEAM GUARD RAIL AND END TREATMENT | 1.2465 | SHOPP | 2012 | 0659 |  | X |  | X |  | 1351000 | 584000 | 51000 | 350000 | 3000 | 180000 | 93607.53 | 43.23% | 2013-11-01 | 2014-03-01 | 0 | 0.1534 | 0.00504 | 1.0881 | Caltrans | Caltrans | Caltrans | Caltrans
11 | SHOPP | 28890 | SD | 805 | REPLACE EXISTING CULVERT | 0.00887 | SHOPP | 2010 | 1004 | [5 empty] | 735000 | 288000 | 50000 | 108000 | 10000 | 120000 | 410346.98 | 39.18% | 2011-01-25 | 2012-12-04 | 0 | 0 | 0 | 0.00887 | Caltrans | Caltrans | Caltrans | Caltrans
11 | SHOPP | 28960 | IMP | 086 | SCOUR MITIGATION | 0.7376 | SHOPP | 2010 | 0842 | [5 empty] | 9274000 | 3383000 | 1181000 | 1131000 | 2000 | 1069000 | 1570616.01 | 36.48% | 2013-02-09 | 2013-05-15 | 0 | 0 | 0.02995 | 0.70765 | Caltrans | Caltrans | Caltrans | Caltrans
11 | SHOPP | 29030 | SD | 005 | SEISMIC RETROFIT AND STRUCTURE REHABILITATION | 4.6979 | SHOPP | 2010 | 0840 | [5 empty] | 3913000 | 3136000 | 479000 | 1535000 | 33000 | 1089000 | 1412498.15 | 80.14% | 2013-07-08 | 2015-04-19 | 0 | 0.06896 | 0 | 4.629 | Caltrans | Caltrans | Caltrans | Caltrans
11 | SHOPP | 29040 | SD | 094 | PAVEMENT REHABILITATION | 10.4785 | SHOPP | 2012 | 0836 |  |  |  | X |  | 14528000 | 4513000 | 601000 | 1565000 | 59000 | 2288000 | 914034.38 | 31.06% | 2013-08-23 | 2014-03-01 | 0 | 0.10145 | 0 | 10.377 | Caltrans | Caltrans | Caltrans | Caltrans
11 | SHOPP | 29170 | SD | 005 | REPLACE OVERHEAD AND ROADSIDE SIGNS ON FORMER RTES SR-209 & SR-274 | 0.20589 | SHOPP | 2010 | 0765 | [5 empty] | 2239000 | 1028000 | 21000 | 750000 | 4000 | 253000 | 485156.19 | 45.91% | 2012-03-20 | 2013-02-25 | 0 | 0 | 0 | 0.20589 | Caltrans | Caltrans | Caltrans | Caltrans
11 | SHOPP | 29190 | SD | 015 | CONCRETE SLOPE PAVING AND PLANTING | 0.17742 | SHOPP | 2008 | 0911 | [5 empty] | 2697000 | 1087000 | 145000 | 425000 | 7000 | 510000 | 822404.42 | 40.3% | 2010-11-23 | 2012-09-11 | 0 | 0 | 0 | 0.17742 | Caltrans | Caltrans | Caltrans | Caltrans
11 | SHOPP | 29230 | SD | 805 | STORM WATER MITIGATION SLOPE EROSION REPAIR | 0.96378 | SHOPP | 2012 | 0916 |  | X |  |  |  | 1786000 | 577000 | 80000 | 232000 | 5000 | 260000 | 114873.03 | 32.31% | 2014-03-31 | 2018-06-14 | 0 | 0.89438 | 0 | 0.0694 | Caltrans | Caltrans | Caltrans | Caltrans
11 | SHOPP | 29240 | SD | 005 | REPAIR SLOPE AND EROSION CONTROL WORK | 0.01223 | SHOPP | 2008 | 0917 | [5 empty] | 1699000 | 670000 | 90000 | 270000 | 5000 | 305000 | 824751.98 | 39.43% | 2010-12-23 | 2012-06-25 | 0 | 0 | 0 | 0.01223 | Caltrans | Caltrans | Caltrans | Caltrans
11 | SHOPP | 29450 | SD | 078 | INSTALL OUTER SEPARATION BARRIER | 0.29701 | SHOPP | 2010 | 0950 | [5 empty] | 6131000 | 1499000 | 21000 | 714000 | 27000 | 737000 | 1318971.74 | 24.45% | 2011-09-28 | 2012-11-05 | 0 | 0 | 0 | 0.29701 | Caltrans | Caltrans | Caltrans | Caltrans
11 | SHOPP | 29520 | SD | 094 | CURVE REALIGNMENT | 6.0405 | SHOPP PA |  |  | X
11 | SHOPP | 29780 | SD | 076 | INSTALL TRAFFIC SIGNAL & WIDENING | 0.09684 | SHOPP | 2010 | 0904 | [5 empty] | 1303000 | 1507000 | E | 862000 | 435000 | 210000 | 1577908.83 | 115.7% | 2011-10-27 | 2013-04-10 | 0 | 0 | 0.02656 | 0.07028 | Caltrans | Caltrans | Caltrans | Caltrans
11 | SHOPP | 29800 | SD | 094 | INSTALL CONCRETE MEDIAN BARRIER | 0.07872 | SHOPP | 2010 | 1021 | [5 empty] | 2400000 | 590000 | E | 250000 | 40000 | 300000 | 336894.07 | 24.58% | 2012-06-27 | 2013-02-06 | 0 | 0 | 0 | 0.07872 | Caltrans | Caltrans | Caltrans | Caltrans
11 | SHOPP | 29840 | SD | 054 | INSTALL MEDIAN BARRIER | 0.18461 | SHOPP | 2010 | 0884 | [5 empty] | 3065000 | 1278000 | 7000 | 580000 | 6000 | 685000 | 726732.33 | 41.7% | 2012-03-12 | 2012-11-01 | 0 | 0 | 0 | 0.18461 | Caltrans | Caltrans | Caltrans | Caltrans
11 | SHOPP | 29860 | SD | 008 | UPGRADE END TREATMENTS,ADD MBGR AND CONCRETE BARRIER. | 0.07703 | SHOPP | 2010 | 0906 |  |  |  | X |  | 2500000 | 1087000 | 199000 | 510000 | 3000 | 375000 | 604874.83 | 43.48% | 2012-12-18 | 2014-06-19 | 0 | 0 | 0.00012 | 0.07691 | Caltrans | Caltrans | Caltrans | Caltrans
11 | SHOPP | 29870 | SD | 079 | CENTERLINE RUMBLE STRIPS AND SHOULDER UPGRADE | 0.03731 | SHOPP | 2010 | 0914 | [5 empty] | 601000 | 462000 | 37000 | 280000 | 8000 | 137000 | 421863.42 | 76.87% | 2012-01-11 | 2012-06-22 | 0 | 0 | 0 | 0.03731 | Caltrans | Caltrans | Caltrans | Caltrans
11 | SHOPP | 29920 | SD | 005 | SEISMIC RESTORATION AND BRIDGE RAIL UPGRADES | 5.5149 | SHOPP | 2012 | 1053 |  |  | X |  |  | 9023000 | 3200000 | E | 1707000 | 14000 | 1479000 | 0 | 35.46% | 2015-04-02 | 2017-09-06 | 0 | 5.4633 | 0.05159 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
11 | SHOPP | 40140 | SD | 005 | REMOVE EXISTING MBGR AND REPLACE WITH CONCRETE BARRIER AND UPGRADE | 7.9568 | SHOPP | 2012 | 1024 | [5 empty] | 8450000 | 3680000 | 124000 | 1324000 | 14000 | 2218000 | 971989.09 | 43.55% | 2013-07-08 | 2014-10-26 | 0 | 0.08185 | 0.00143 | 7.8735 | Caltrans | Caltrans | Caltrans | Caltrans
11 | SHOPP | 40280 | SD | 052 | PAVEMENT REHABILITATION | 2.4975 | SHOPP | 2012 | 1031 |  |  |  | X |  | 3260000 | 980000 | E | 490000 | 10000 | 480000 | 637101.03 | 30.06% | 2013-06-06 | 2013-12-17 | 0 | 0 | 0.00558 | 2.4919 | Caltrans | Caltrans | Caltrans | Caltrans
11 | SHOPP | 40320 | SD | 067 | INSTALL MEDIAN BARRIER | 2.9698 | SHOPP | 2012 | 0670 | [5 empty] | 43033000 | 6150000 | 1800000 | 1500000 | 50000 | 2800000 | 450483.7 | 14.29% | 2016-08-07 | 2017-08-23 | 2.9698 | 0 | 0 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
11 | SHOPP | 40370 | SD | 163 | INSTALL OUTER SEPARATION BARRIER | 1.0156 | SHOPP | 2012 | 1025 | [5 empty] | 2605000 | 957000 | E | 443000 | 18000 | 496000 | 428971.94 | 36.74% | 2013-03-23 | 2015-07-22 | 0 | 0 | 0 | 1.0156 | Caltrans | Caltrans | Caltrans | Caltrans
11 | SHOPP | 40430 | SD | 005 | OUTER SEPARATION BARRIER | 2.8635 | SHOPP | 2012 | 1040 | [5 empty] | 3971000 | 2031000 | E | 800000 | 11000 | 1220000 | 539647.86 | 51.15% | 2013-07-19 | 2015-12-23 | 0 | 0.06894 | 0 | 2.7946 | Caltrans | Caltrans | Caltrans | Caltrans
11 | SHOPP | 40450 | SD | 078 | CONSTRUCT AUXILIARY LANES | 0.28942 | PARTNERSHIP | [6 empty] | O
11 | SHOPP | 40550 | SD | 008 | CONSTRUCT MEDIAN BARRIER | 1.4406 | SHOPP | 2012 | 1044 | [5 empty] | 12643000 | 3597000 | E | 1529000 | 25000 | 2043000 | 0 | 28.45% | 2015-08-28 | 2017-08-24 | 0 | 1.4406 | 0 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
11 | SHOPP | 40570 | SD | 076 | INSTALL ROUNDABOUT AND REALIGN CURVE | 3.2747 | SHOPP | 2012 | 1020 | X |  |  |  |  | 7084000 | 4213000 | 1205000 | 1163000 | 815000 | 1030000 | 35223.88 | 59.47% | 2016-12-05 | 2018-08-05 | 2.9797 | 0.15459 | 0.14044 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
11 | SHOPP | 40640 | SD | 078 | UPGRADE BRIDGE RAIL ENDTREATMENTS TYPE 8 | 1.6477 | SHOPP | 2012 | 1029 | X |  |  |  |  | 5587000 | 1840000 | 465000 | 575000 | 45000 | 755000 | 6647.65 | 32.93% | 2016-03-17 | 2016-11-02 | 1.6283 | 0.0162 | 0.0032 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
11 | SHOPP | 40650 | SD | 015 | MEDIAN BARRIER | 2.9803 | SHOPP | 2012 | 1028 |  | X | X | X |  | 3616000 | 984000 | E | 480000 | 3000 | 501000 | 14746.34 | 27.21% | 2014-02-01 | 2014-06-10 | 0 | 0.33927 | 0.00665 | 2.6344 | Caltrans | Caltrans | Caltrans | Caltrans
11 | SHOPP | 40660 | SD | 076 | REDUCE CROSS MEDIAN ACCIDENTS | 3.4431 | SHOPP | 2012 | 1030 |  | X | X |  |  | 10209000 | 2490000 | E | 1022000 | 7000 | 1461000 | 23599.26 | 24.39% | 2014-09-26 | 2015-12-23 | 0 | 3.4242 | 0.01889 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
11 | SHOPP | 40670 | SD | 005 | PAVEMENT REHABILITATION | 11.6975 | SHOPP | 2012 | 1032 | [5 empty] | 53335000 | 8605000 | 1520000 | 2182000 | 13000 | 4890000 | 1224781.17 | 16.13% | 2013-09-26 | 2015-07-08 | 0 | 0.28532 | 0.00835 | 11.4038 | Caltrans | Caltrans | Caltrans | Caltrans
11 | SHOPP | 40690 | SD | 008 | PAVEMENT REHABILITATION | 4.9275 | SHOPP | 2012 | 1038 | [5 empty] | 17117000 | 3800000 | E | 1350000 | 50000 | 2400000 | 0 | 22.2% | 2015-03-29 | 2016-04-17 | 0 | 4.886 | 0.04154 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
11 | SHOPP | 40700 | SD | 008 | PAVEMENT REABILITATION | 4.5256 | SHOPP | 2012 | 1039 | [5 empty] | 35350000 | 7800000 | E | 3500000 | 100000 | 4200000 | 0 | 22.07% | 2015-04-16 | 2016-05-05 | 0 | 4.4968 | 0.0288 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
11 | SHOPP | 40760 | SD | 052 | UPGRADE BRIDGE RAIL END TREATMENTS | 1.7241 | SHOPP | 2012 | 1045 | X |  |  |  |  | 5440000 | 1775000 | 465000 | 575000 | 45000 | 690000 | 2769.03 | 32.63% | 2015-10-05 | 2016-06-09 | 0.43298 | 1.278 | 0 | 0.01315 | Caltrans | Caltrans | Caltrans | Caltrans
11 | SHOPP | 40800 | SD | 008 | BRIDE RAIL UPGRADES, REPLACEMENTS AND SEISMIC RETROFIT | 2.065 | SHOPP | 2012 | 1066 | [5 empty] | 1287000 | 857000 | E | 546000 | 2000 | 309000 | 0 | 66.59% | 2015-05-11 | 2015-09-27 | 0 | 2.0561 | 0.00888 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
11 | SHOPP | 40850 | SD | 125 | INSTALL MEDIAN BARRIER | 2.1884 | SHOPP | 2012 | 1043 |  | X | X |  |  | 1330000 | 1410000 | 450000 | 580000 | 30000 | 350000 | 213117.72 | 106% | 2014-08-21 | 2015-12-28 | 0 | 2.1884 | 0 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
11 | SHOPP | 40890 | SD | 005 | CLEAN AND TREAT BRIDGE DECK WITH METHACRYLATE AND REPLACE JOINT | 1.3393 | SHOPP | 2012 | 1046 |  |  |  | X |  | 1950000 | 562000 | H | 350000 | 2000 | 210000 | 202875.08 | 28.82% | 2013-05-16 | 2013-12-11 | 0 | 0 | 0 | 1.3393 | Caltrans | Caltrans | Caltrans | Caltrans
11 | SHOPP | 40930 | SD | 075 | BRIDGE REHABILITATION | 3.2854 | SHOPP | 2012 | 1059 |  |  | X |  |  | 16108000 | 2152000 | 368000 | 691000 | 2000 | 1091000 | 13089.12 | 13.36% | 2015-03-19 | 2016-02-01 | 0 | 3.2513 | 0.03412 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
11 | SHOPP | 40950 | SD | 075 | PAINT CORONADO BRIDGE SPANS 26-29 | 2.233 | SHOPP | 2010 | 1047 |  |  |  | X |  | 4000000 | 644000 | 2000 | 260000 | 2000 | 380000 | 313358.06 | 16.1% | 2012-12-13 | 2014-03-14 | 0 | 0 | 0 | 2.233 | Caltrans | Caltrans | Caltrans | Caltrans
11 | SHOPP | 40960 | SD | 054 | ROADSIDE SAFETY IMPROVEMENTS | 1.0165 | SHOPP PA
11 | SHOPP | 40970 | SD | 008 | ROADSIDE SAFETY IMPROVEMENTS | 0.969 | SHOPP PA
11 | SHOPP | 40980 | SD | 078 | ROADSIDE SAFETY IMPROVEMENT | 1.8687 | SHOPP PA |  |  | X
11 | SHOPP | 41060 | SD | 005 | INSTALL AND UPGRADE CURB RAMPS | 3.6955 | SHOPP | 2012 | 1060 |  | X | X |  |  | 2302000 | 1998000 | 252000 | 1112000 | 94000 | 540000 | 3725.6 | 86.79% | 2014-07-06 | 2015-05-01 | 0 | 3.1638 | 0.53172 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
11 | SHOPP | 41470 | SD | 067 | DRAINAGE IMPROVEMENTS AND HIGH FRICTION SURFACE TREATMENT | 2.6626 | SHOPP | 2012 | 1094 | X |  |  |  |  | 3355000 | 1745000 | 476000 | 746000 | 9000 | 514000 | 0 | 52.01% | 2016-01-31 | 2016-10-16 | 2.2442 | 0.36356 | 0 | 0.05488 | Caltrans | Caltrans | Caltrans | Caltrans
11 | SHOPP | 41480 | SD | 008 | SAFETY IMPROVEMENT WESTBOUND I-8 | 3.1707 | SHOPP PA |  |  |  |  | X
11 | SHOPP | 41540 | SD | 008 | ENHANCE STRIPING, LIGHTING, AND UPGRADE BRIDGE END TREATMENTS | 2.398 | SHOPP PA |  |  | X
11 | SHOPP | 41570 | SD | 078 | INSTALL ENHANCED LIGHTING AND REPLACE STRIPING | 2.2382 | SHOPP PA |  |  | X
11 | SHOPP | MINOR |  |  | SHOPP MINOR | 21.1141 | MINOR
12 | SHOPP | 0E030 | ORA | 005 | REHABILITATE PAVEMENT. | 2.8255 | SHOPP | 2010 | 2599A | [5 empty] | 21506000 | 6432000 | E | 2721000 | 10000 | 3701000 | 3552929.81 | 29.91% | 2011-10-18 | 2013-02-01 | 0 | 0 | 0 | 2.8255 | Caltrans | Caltrans | Caltrans | Caltrans
12 | SHOPP | 04321 | ORA | 074 | WIDEN ROADWAY AND BRIDGES | 0.65151 | SHOPP | 2004 | 4228 | [5 empty] | 26662000 | 13880000 | 13880000 | F | F | F | 16214941.86 | 52.06% | 2006-12-22 | 2009-05-05 | 0 | 0 | 0.00123 | 0.65028 | Caltrans | Caltrans | Caltrans | Caltrans
12 | SHOPP | 04322 | ORA | 074 | ESTABLISH PLANTING AND INSTALL IRRIGATION SYSTEM | 0.20099 | SHOPP | 2008 | 4228A | [5 empty] | 1048000 | 879000 | 8000 | 356000 | 26000 | 489000 | 556412.18 | 83.87% | 2010-04-29 | 2015-12-01 | 0 | 0 | 0 | 0.20099 | Caltrans | Caltrans | Caltrans | Caltrans
12 | SHOPP | 0E970 | ORA | L5730 | PURCHASE LAND & CONSTRUCT DISTRICT 12 EQUIPMENT SERVICE CENTER | 0.02996 | SHOPP | 2004 | 2109 | [5 empty] | 8900000 | 2418000 | 2418000 | A | A | A | 909024.44 | 27.17% | - - | - - | 0 | 0 | 0.02996 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
12 | SHOPP | 0F060 | ORA | 005 | WIDEN S/B OFF-RAMP AND BRIDGE OC @ CAMINO DE ESTRELLA | 2.3415 | SHOPP | 2010 | 2587 | [5 empty] | 7487000 | 5247000 | 746000 | 2283000 | 558000 | 1660000 | 3434751.8 | 70.08% | 2012-02-24 | 2014-10-31 | 0 | 0 | 0.96262 | 1.3788 | Caltrans | Caltrans | Caltrans | Caltrans
12 | SHOPP | 0F920 | ORA | 005 | PLANTING AND IRRIGATION | 0.05617 | SHOPP | 2008 | 2638 | [5 empty] | 2718000 | 1041000 | 89000 | 596000 | 12000 | 344000 | 1135418.86 | 38.3% | 2010-05-01 | 2014-12-01 | 0 | 0 | 0 | 0.05617 | Caltrans | Caltrans | Caltrans | Caltrans
12 | SHOPP | 0G370 | ORA | 241 | REPLACE METAL BLOCKS WITH WOOD | 0.43317 | SHOPP | 2010 | 5483 | [5 empty] | 3170000 | 2553000 | 193000 | 1230000 | 40000 | 1090000 | 1873798.16 | 80.54% | 2011-08-24 | 2012-07-24 | 0 | 0 | 0.00855 | 0.42462 | Caltrans | Caltrans | Caltrans | Caltrans
12 | SHOPP | 0G960 | ORA | 055 | WIDEN FREEWAY AND BRIDGE | 1.3657 | SHOPP | 2010 | 3483A | [5 empty] | 10222000 | 7874000 | 1312000 | 3372000 | 690000 | 2500000 | 6899423.62 | 77.03% | 2011-08-02 | 2013-06-11 | 0 | 0 | 0.05969 | 1.306 | Caltrans | Caltrans | Caltrans | Caltrans
12 | SHOPP | 0H029 | ORA | 091 | RESURFACE TRAVELED WAYS OF MAINLINE AND RAMPS. RESURFACE DETERIORATED | 4.413 | SHOPP | 2010 | 4506B |  |  |  | X |  | 28653000 | 9536000 | E | 4584000 | 81000 | 4871000 | 3165906.34 | 33.28% | 2012-03-26 | 2013-10-01 | 0 | 0 | 0 | 4.413 | Caltrans | Caltrans | Caltrans | Caltrans
12 | SHOPP | 0H030 | ORA | 142 | CAPITAL PREVENTIVE MAINTENANCE | 0.13415 | SHOPP | 2010 | 5363A | [5 empty] | 4000000 | 1453000 | E | 700000 | 3000 | 750000 | 808107.41 | 36.33% | 2011-12-14 | 2013-02-01 | 0 | 0 | 0 | 0.13415 | Caltrans | Caltrans | Caltrans | Caltrans
12 | SHOPP | 0H034 | ORA | 073 | NB/SB SLAB REPLACEMENT. ON/OFF RAMPS RESURFACING, SHOULDER REHAB & | 2.7227 | SHOPP | 2012 | 4096F | [5 empty] | 4861000 | 1645000 | 34000 | 800000 | 11000 | 800000 | 422866.7 | 33.84% | 2013-10-01 | 2016-03-04 | 0 | 0.62 | 0.01986 | 2.0828 | Caltrans | Caltrans | Caltrans | Caltrans
12 | SHOPP | 0H160 | ORA | 001 | CAPITAL PREVENTIVE MAINTENANCE - RESURFACE THE PAVEMENTS | 2.6049 | SHOPP | 2012 | 2459A |  | X | X |  |  | 4609000 | 2050000 | E | 990000 | 100000 | 960000 | 3282.34 | 44.48% | 2014-02-01 | 2015-12-01 | 0 | 1.6645 | 0.03262 | 0.90773 | Caltrans | Caltrans | Caltrans | Caltrans
12 | SHOPP | 0H208 | ORA | 055 | FLATTEN THE SLOPE ABOVE THE MAINTENANCE ACCESS ROAD | 5.6903 | SHOPP | 2012 | 3577A | [5 empty] | 16128000 | 4700000 | 700000 | 1600000 | 600000 | 1800000 | 2078919.66 | 29.14% | 2013-10-14 | 2015-11-02 | 0 | 1.0766 | 0.06469 | 4.549 | Caltrans | Caltrans | Caltrans | Caltrans
12 | SHOPP | 0H20U | ORA | 055 | REMOVE DISEASED TREES AND UPGRADE HIGHWAY PLANTING | 1.3564 | SHOPP | 2012 | 3448 |  | X | X |  |  | 4581000 | 928000 | 145000 | 348000 | 58000 | 377000 | 72374.46 | 20.26% | 2014-08-05 | 2018-11-01 | 0 | 1.1927 | 0.16362 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
12 | SHOPP | 0H232 | ORA | 005 | INSTALL CMS AT VARIOUS FREEWAY INTERCHANGE | 0.31219 | SHOPP | 2010 | 2350A | [5 empty] | 2738000 | 1939000 | 306000 | 990000 | 133000 | 510000 | 1419591.66 | 70.82% | 2011-11-30 | 2013-06-01 | 0 | 0 | 0.00051 | 0.31168 | Caltrans | Caltrans | Caltrans | Caltrans
12 | SHOPP | 0H440 | ORA | 073 | STORM WATER MITIGATION & SLOPE STABILITY | 2.5655 | SHOPP | 2012 | 4051 | [5 empty] | 18044000 | 6180000 | 1850000 | 2000000 | 250000 | 2080000 | 3315100.08 | 34.25% | 2013-09-08 | 2017-10-01 | 0 | 0.23866 | 0 | 2.3269 | Caltrans | Caltrans | Caltrans | Caltrans
12 | SHOPP | 0H450 | ORA | 261 | SELENIUM TREATMENT FACILITY | 6.5005 | SHOPP | 2012 | 4926B | X | X | X |  |  | 15000000 | 4843000 | 1058000 | 1500000 | 442000 | 1843000 | 384955.17 | 32.29% | 2014-12-01 | 2016-02-01 | 0.00048 | 5.5 | 1 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
12 | SHOPP | 0H890 | ORA | 055 | REPAIR EXISTING ROCK BLANKET, UPGRADE EXIST IRRIGATION, PROVIDE | 0.72609 | SHOPP | 2012 | 3449 | X |  |  |  |  | 1200000 | 360000 | 70000 | 140000 | 20000 | 130000 | 0 | 30% | 2015-08-16 | 2016-09-03 | 0.38111 | 0.25206 | 0.09292 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
12 | SHOPP | 0H900 | ORA | 055 | REMOVE DISEASED EUC. TREES, UPGRADE EXIST IRRIGATION, PROVIDE MTNC | 0.76274 | SHOPP | 2012 | 3449A |  | X | X |  |  | 1200000 | 480000 | 75000 | 185000 | 20000 | 200000 | 42639.77 | 40% | 2014-07-15 | 2015-08-01 | 0 | 0.71756 | 0.04518 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
12 | SHOPP | 0J430 | ORA | 074 | PAVEMENT REHABILITATION | 0.97194 | SHOPP | 2010 | 4097A | [5 empty] | 9783000 | 3424000 | E | 1722000 | 10000 | 1692000 | 2138438.73 | 35% | 2011-12-14 | 2013-01-05 | 0 | 0 | 0 | 0.97194 | Caltrans | Caltrans | Caltrans | Caltrans
12 | SHOPP | 0J61U | ORA | 005 | REVEGETATION OF EXPOSED SLOPES FOR NPDES CONCERNS AND SOURCE CONTROL | 1.4206 | SHOPP | 2012 | 2723A |  | X | X |  |  | 6348000 | 1778000 | 278000 | 666000 | 112000 | 722000 | 163359.2 | 28.01% | 2014-06-07 | 2018-09-01 | 0 | 1.2752 | 0.1454 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
12 | SHOPP | 0J640 | ORA | 055 | REVEGETATION OF EXPOSED SLOPES FOR NPDES CONCERNS AND SOURCE CONTROL | 2.9717 | SHOPP | 2012 | 3479C | X |  |  |  |  | 2100000 | 1400000 | 250000 | 500000 | 50000 | 600000 | 0 | 66.67% | 2015-09-09 | 2019-09-23 | 1.5017 | 1.2913 | 0.17868 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
12 | SHOPP | 0J650 | ORA | 261 | REVEGETATION OF EXPOSED SLOPES FOR NPDES CONCERNS AND SOURCE CONTROL | 1.4579 | SHOPP | 2012 | 4926D | [5 empty] | 2200000 | 1500000 | 250000 | 550000 | 50000 | 650000 | 0 | 68.18% | 2016-01-16 | 2020-01-31 | 1.3318 | 0 | 0.12613 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
12 | SHOPP | 0J660 | ORA | 241 | REVEGETATION OF EXPOSED SLOPES FOR NPDES CONCERNS AND SOURCE CONTROL | 0.9608 | SHOPP | 2012 | 5490A | [5 empty] | 2200000 | 1400000 | 250000 | 500000 | 50000 | 600000 | 0 | 63.64% | 2016-05-12 | 2020-06-02 | 0.89038 | 0 | 0.07042 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
12 | SHOPP | 0J670 | ORA | 241 | REVEGETATION OF EXPOSED SLOPES FOR NPDES CONCERNS AND SOURCE CONTROL | 0.93811 | SHOPP | 2010 | 5504A |  |  |  | X |  | 1507000 | 814000 | 82000 | 498000 | 33000 | 201000 | 811905.91 | 54.01% | 2013-03-18 | 2014-04-01 | 0 | 0 | 0 | 0.93811 | Caltrans | Caltrans | Caltrans | Caltrans
12 | SHOPP | 0K520 | ORA | 091 | OGAC OVERLAY, GROOVING, SAFETY LIGHTING, & UPGRADE ADA & GUARDRAIL | 0.10161 | SHOPP | 2010 | 5486 |  |  |  | X |  | 1000000 | 596000 | E | 360000 | 10000 | 226000 | 417600.9 | 59.6% | 2012-06-11 | 2013-07-01 | 0 | 0 | 0 | 0.10161 | Caltrans | Caltrans | Caltrans | Caltrans
12 | SHOPP | 0K530 | ORA | 091 | RESURFACE ALL LANES WITH RUBBERIZED DENSE AC | 1.3821 | SHOPP | 2012 | 4528A |  |  |  | X |  | 2520000 | 1049000 | E | 540000 | 20000 | 489000 | 676630.75 | 41.63% | 2013-01-07 | 2013-11-01 | 0 | 0 | 0 | 1.3821 | Caltrans | Caltrans | Caltrans | Caltrans
12 | SHOPP | 0K620 | ORA | 005 | GROOVE MAINLINE & OVERLAY W/OGAC NB & SB I-5. ALSO MODIFY TRAFFIC | 0.14028 | SHOPP | 2010 | 2702 | [5 empty] | 1791000 | 719000 | E | 299000 | 5000 | 415000 | 520597.06 | 40.15% | 2011-11-30 | 2013-04-01 | 0 | 0 | 0 | 0.14028 | Caltrans | Caltrans | Caltrans | Caltrans
12 | SHOPP | 0K690 | ORA | 057 | OVERLAY CONNECTOR | 0.01585 | SHOPP | 2010 | 3792A | [5 empty] | 307000 | 268000 | E | 132000 | 4000 | 132000 | 226663.26 | 87.3% | 2011-05-17 | 2012-11-20 | 0 | 0 | 0 | 0.01585 | Caltrans | Caltrans | Caltrans | Caltrans
12 | SHOPP | 0L020 | ORA | 057 | CONSTRUCT CONCRETE MEDIAN BARRIER | 0.13557 | SHOPP | 2008 | 3798 | [5 empty] | 513000 | 138000 | 69000 | N | N | 69000 | 22032.82 | 26.9% | 2010-11-01 | 2014-07-01 | 0 | 0 | 0 | 0.13557 | Caltrans | Caltrans | Caltrans | Caltrans
12 | SHOPP | 0L380 | ORA | 039 | INSTALL NEW & UPGRADE CURB RAMPS AT VARIOUS LOCATIONS | 2.3125 | SHOPP | 2012 | 3097A | [5 empty] | 3090000 | 1917000 | E | 864000 | 35000 | 1018000 | 823662.33 | 62.04% | 2013-08-25 | 2015-05-25 | 0 | 0.06609 | 0.06135 | 2.185 | Caltrans | Caltrans | Caltrans | Caltrans
12 | SHOPP | 0L480 | ORA | 074 | BUILD AND PLACE CULVERT DRAINAGE SYSTEMS TO STABLILIZE ROADWAY | 0.2687 | SHOPP | 2008 | 4155 | [5 empty] | 700000 | 260000 | E | 60000 | 100000 | 100000 | 321481.41 | 37.14% | 2010-03-30 | 2010-05-01 | 0 | 0 | 0.2687 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
12 | SHOPP | 0L720 | ORA | 074 | CONSTRUCT 4-FOOT RIGHT SHOULDER, PAVE TURNOUTS, REPLACE/ADD MBGR | 14.0937 | SHOPP | 2012 | 4124 | X |  |  |  |  | 10000000 | 8350000 | 1300000 | 2800000 | 1250000 | 3000000 | 0 | 83.5% | 2015-11-12 | 2018-03-01 | 0.00774 | 11.1161 | 2.9699 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
12 | SHOPP | 0L730 | ORA | 005 | EXTEND SHORT SEAT HINGES & ADDRESS SEISMIC VULNERABILITY CONCERNS. | 7.3178 | SHOPP PA
12 | SHOPP | 0L74U | ORA | 055 | REHABILITATE PAVEMENT & CONSTRUCT PERMANENT CONCRETE MEDIAN BARRIER. | 9.3942 | SHOPP | 2012 | 3421D | [5 empty] | 20482000 | 6500000 | E | 3190000 | 50000 | 3260000 | 0 | 31.74% | 2013-09-10 | 2016-02-01 | 0 | 0 | 0 | 9.3942 | Caltrans | Caltrans | Caltrans | Caltrans
12 | SHOPP | 0L750 | ORA | 091 | SHOULDER WIDENING, SIGNING, STRIPING AND GURDRAIL MODIFICATION | 1.0129 | SHOPP | 2012 | 4509Z |  |  |  | X |  | 753000 | 493000 | 104000 | 215000 | 10000 | 164000 | 289462.39 | 65.47% | 2013-07-15 | 2014-03-01 | 0 | 0.05416 | 0 | 0.95872 | Caltrans | Caltrans | Caltrans | Caltrans
12 | SHOPP | 0L77U | ORA | 039 | INSTALL ADDITIONAL SAFETY LIGHTING AND MODIFY SIGNALS. | 1.7226 | SHOPP | 2012 | 3157 | [5 empty] | 562000 | 965000 | 155000 | 450000 | 10000 | 350000 | 396152.54 | 171.7% | 2013-04-24 | 2014-09-01 | 0 | 0.00212 | 0 | 1.7205 | Caltrans | Caltrans | Caltrans | Caltrans
12 | SHOPP | 0L870 | ORA | 005 | SIGNAL MODIFICATION SAFETY/TRAFFIC OPERATION | 1.0341 | SHOPP | 2012 | 2726 | [5 empty] | 580000 | 775000 | 120000 | 359000 | 5000 | 291000 | 375725.69 | 133.6% | 2013-08-01 | 2014-12-01 | 0 | 0.01886 | 0.00072 | 1.0145 | Caltrans | Caltrans | Caltrans | Caltrans
12 | SHOPP | 0L920 | ORA | 005 | UPGRADE PEDESTRIAN FACILITIES W/IN CT R/W TO CURRENT ADA STANDARDS. | 6.5347 | SHOPP | 2012 | 2531G | X |  |  |  |  | 1762000 | 1400000 | 190000 | 580000 | 20000 | 610000 | 0 | 79.46% | 2015-03-13 | 2016-04-12 | 0.42329 | 6.0955 | 0.01593 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
12 | SHOPP | 0L970 | ORA | 039 | ADD SAFETY LIGHTING, MODIFY SIGNALS AND PAVEMENT MARKING, ADA UPDATE. | 1.4214 | SHOPP | 2012 | 3107 | [5 empty] | 934000 | 1040000 | 155000 | 450000 | 10000 | 425000 | 157906.79 | 111.3% | 2014-01-01 | 2015-03-01 | 0 | 0.56353 | 0.00235 | 0.85555 | Caltrans | Caltrans | Caltrans | Caltrans
12 | SHOPP | 0M000 | ORA | 055 | OVERLAY THE CONNECTOR WITH OCGA, MODIFY DRAINAGE, UPGRADE METAL BEAM | 0.34883 | SHOPP | 2012 | 3530E |  |  |  | X |  | 400000 | 400000 | 50000 | 250000 | C | 100000 | 415707.69 | 100% | 2012-11-30 | 2013-08-30 | 0 | 0 | 0 | 0.34883 | Caltrans | Caltrans | Caltrans | Caltrans
12 | SHOPP | 0M110 | ORA | 073 | ADJUST FWY CROSS-SLOPE A, ADD DRAINAGE INLETS, RESURFACE RWY WITH | 2.6097 | SHOPP PA | 2012 | 4096D | X |  | X |  |  | 2200000 | 1197000 | H | 598000 | 27000 | 572000 | 0 | 0% | 2015-02-01 | 2016-05-01 | 0 | 2.6034 | 0.00629 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
12 | SHOPP | 0M340 | ORA | 073 | WIDEN RDWY TO IMPROVE CHANNELIZA- TION AT GORE AREA & WIDEN RAMP, | 2.0013 | SHOPP PA |  |  |  |  | X
12 | SHOPP | 0M350 | ORA | 405 | WIDEN RDWY TO IMPROVE CHANNELIZA- TION AT GORE AREA & WIDEN RAMP, | 12.0499 | SHOPP PA
12 | SHOPP | 0M400 | ORA | 091 | IMPROVE MAINTENANCE ACCESS & PAVING FOR ROADSIDE WORKER SAFETY. | 0.40711 | SHOPP | 2012 | 4507A | [5 empty] | 1200000 | 360000 | 70000 | 140000 | 20000 | 130000 | 0 | 30% | 2016-04-14 | 2017-05-01 | 0.35188 | 0 | 0.05523 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
12 | SHOPP | 0M470 | ORA | 001 | MODIFY SIGNALS, STRIPING, ADD'T SAFETY LIGHTNING, ADA IMPROVEMENTS. | 2.306 | SHOPP PA
12 | SHOPP | 0M490 | ORA | 005 | ENHANCE CURVE, BUILD UP THE APPROACH & DEPT FROM THE BRIDGE AND | 7.6531 | SHOPP PA |  |  | X
12 | SHOPP | 0M500 | ORA | 055 | UPGRADE METAL BEAM GUARDRAIL. | 5.9787 | SHOPP PA
12 | SHOPP | 0M520 | ORA | 039 | MODIFY SIGNALS, ADD SAFETY LIGHTING REFRESH PAVEMENT & ADA UPGRADES. | 2.18 | SHOPP PA |  |  | X
12 | SHOPP | 0M550 | ORA | 073 | BUILD SHEAR PILE WALLS WITH TIEBACKS. | 2.4634 | SHOPP | 2010 | 4057 | [5 empty] | 20808000 | 5202000 | 612000 | 2040000 | 102000 | 2448000 | 1477325.2 | 25% | 2012-07-09 | 2014-09-02 | 0 | 0 | 0.75528 | 1.7082 | Caltrans | Caltrans | Caltrans | Caltrans
12 | SHOPP | 0M610 | ORA | 091 | INSTALL ADDITIONAL LIGHTING AT INTERCHANGE. | 2.7507 | SHOPP PA |  |  |  | X
12 | SHOPP | 0M720 | ORA | 091 | SEISMIC RETROFIT FOUR (4) BRIDGES. | 4.4 | SHOPP PA |  |  | X
12 | SHOPP | 0M900 | ORA | 022 | IMPROVE/CONFIGURE CHANNELIZATION REMOVE APPROX 2/3 OF CONC BARRIER | 0.41519 | SHOPP PA |  |  | X
12 | SHOPP | 0M910 | ORA | 090 | CONSTRUCTION OR MODIFY CURBS, SIDEWALKS, OR WHEELCHAIR RAMPS. | 2.8415 | SHOPP PA
12 | SHOPP | 0N070 | ORA | VAR | GROOVING, OGAC, POLYESTER CONCRETE, RESTRIPING, AND MBGR UPGRADE. | 3.8917 | SHOPP PA
12 | SHOPP | 0N110 | ORA | 133 | DEEP INJECTION GROUTING AT THREE LOCATIONS AT THE CONNETOR | 7.8009 | SHOPP PA |  |  | X
12 | SHOPP | MINOR |  |  | SHOPP MINOR | 15.3846 | MINOR
01 | STIP | 26200 | MEN | 101 | CONSTRUCT 4-LANE FREEWAY, PHASE 1 | 21.926 | STIP | 2010 | 0125F | [5 empty] | 153071000 | 69981000 | 9865000 | 35398000 | 4700000 | 20018000 | 50837048.55 | 45.72% | 2012-07-26 | 2018-04-01 | 0 | 0.00084759 | 0.49 | 21.4351 | Caltrans | Caltrans | Caltrans | Caltrans
01 | STIP | 26201 | MEN | 101 | RYAN CREEK FISH PASSAGE - COHO SALMON MITIGATION | 4.87 | STIP | 2010 | 0125F | X | X | X |  |  | 2300000 | 1135000 | 245000 | 500000 | 90000 | 300000 | 68503.31 | 49.35% | 2014-05-01 | 2014-10-01 | 1.9529 | 2.0536 | 0.46989 | 0.39355 | Caltrans | Caltrans | Caltrans | Caltrans
01 | STIP | 26202 | MEN | 101 | WETLAND/RIPARIAN MITIGATION | 7.11 | STIP | 2010 | 0125F | [5 empty] | 47820000 | 2964000 | H | 400000 | 314000 | 2250000 | 124421.7 | 6.198% | 2013-05-01 | 2017-04-01 | 0 | 0.27052 | 0.34229 | 6.4972 | Caltrans | Caltrans | Caltrans | Caltrans
01 | STIP | 26203 | MEN | 101 | WILLITS BYPASS RELINQUISHMENT | 1.52 | STIP | 2010 | 0125F | [5 empty] | 3642000 | 2170000 | H | 1000000 | 320000 | 850000 | 0 | 59.58% | 2016-03-01 | 2018-04-01 | 0 | 1.4939 | 0.026102 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
01 | STIP | 26204 | MEN | 101 | SHERWOOD ROAD GEOMETRIC UPGRADES - WILLITS BYPASS | 2.86 | STIP | 2010 | 0125F | X |  |  |  |  | 3700000 | 2550000 | 800000 | 800000 | 200000 | 750000 | 1390.26 | 68.92% | 2016-03-01 | 2018-04-01 | 0.82548 | 1.5814 | 0.45316 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
01 | STIP | 36600 | HUM | 101 | UPGRADE 4-LANE FACILITY | 8.3308 | STIP | 2012 | 0072 | X |  |  |  |  | 17160000 | 8108000 | 3063000 | 2656000 | 399000 | 1990000 | 2783558.01 | 47.25% | 2016-03-01 | 2018-05-01 | 0.051599 | 0 | 0.16731 | 8.1119 | Caltrans | Caltrans | Caltrans | Caltrans
01 | STIP | 46530 | DN | 101 | YUROK TRIBE TRANSPORTATION CORRIDOR | 0.04 | STIP | 2010 | 2015 |  |  |  | X |  | 257000 | 260000 | 100000 | 80000 | 5000 | 75000 | 237266.88 | 101.2% | 2012-06-20 | 2013-11-01 | 0 | 0 | 0.019492 | 0.020508 | Caltrans | Caltrans | Caltrans | Caltrans
01 | STIP | 46580 | MEN | 001 | PACIFIC COAST BIKE ROUTE PHASE II AND III | 0.3 | STIP | 2010 | 4418 |  |  |  | X |  | 605000 | 387000 | 152000 | 75000 | 10000 | 150000 | 249177.14 | 63.97% | 2012-09-19 | 2013-07-15 | 0 | 0 | 0.073174 | 0.22683 | Caltrans | Caltrans | Caltrans | Caltrans
01 | STIP | 46590 | MEN | 001 | PACIFIC COAST BIKE ROUTE PHASE III | 0.68 | STIP | 2012 | 4419 | X |  |  |  |  | 839000 | 355000 | 95000 | 75000 | 45000 | 140000 | 0 | 42.31% | 2015-01-01 | 2016-01-15 | 0.20081 | 0.36718 | 0.112 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
01 | STIP | 46680 | LAK | 020 | CONSTRUCT HISTORIC INTERPRETIVE CENTER | 0.09 | STIP | 2010 | 4421 | [5 empty] | 125000 | 246000 | 88000 | 80000 | 18000 | 60000 | 243876.59 | 196.8% | 2011-08-26 | 2012-11-01 | 0 | 0 | 0.046208 | 0.043792 | Caltrans | Caltrans | Caltrans | Caltrans
01 | STIP | 47940 | DN | 199 | SHOULDER WIDENING & BRIDGE WIDENING /REPLACEMENT | 1.5304 | STIP | 2012 | 1047 | [5 empty] | 15181000 | 6121000 | 1337000 | 2433000 | 461000 | 1890000 | 2873415.34 | 40.32% | 2013-11-01 | 2017-05-01 | 0 | 0.81794 | 0.10297 | 0.60948 | Caltrans | Caltrans | Caltrans | Caltrans
01 | STIP | 2981U | LAK | 029 | UPGRADE TO 4 LANE EXPRESSWAY | 8.18 | STIP | 2012 | 0122C | [5 empty] | 151409000 | 28739000 | 10828000 | 4116000 | 3295000 | 10500000 | 9633203.42 | 18.98% | 2017-08-01 | 2018-09-01 | 8.0535 | 0 | 0.12655 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
02 | STIP | 0E240 | PLU | 089 | GREENVILLE STREETSCAPE | 1.2087 | STIP | 2012 | 3355 |  |  | X |  |  | 5250000 | 1546000 | 350000 | 253000 | 405000 | 538000 | 322299.81 | 29.45% | 2015-03-21 | 2017-01-24 | 0 | 0.86483 | 0.34388 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
02 | STIP | 28853 | TRI | 299 | WIDEN EXISTING ROADWAY | 0.40059 | STIP | 2004 | 0320 | [5 empty] | 4201000 | 1075000 | 400000 | 250000 | 75000 | 350000 | 1379539.19 | 25.59% | 2005-10-28 | 2006-11-15 | 0 | 0 | 0 | 0.40059 | Caltrans | Caltrans | Caltrans | Caltrans
02 | STIP | 29971 | MOD | 299 | WIDEN TO THREE LANES | 4.9037 | STIP | 2012 | 3368 |  | X | X |  |  | 3160000 | 1113000 | 206000 | 362000 | 89000 | 456000 | 216991.26 | 35.22% | 2014-02-05 | 2015-07-10 | 0 | 2.66 | 0.85 | 1.3937 | Caltrans | Caltrans | Caltrans | Caltrans
02 | STIP | 32760 | PLU | 089 | REALIGN CURVES | 0.33445 | STIP | 2002 | 5800 | [5 empty] | 1972000 | 465000 | 100000 | 125000 | 75000 | 165000 | 999943.25 | 23.58% | 2003-07-16 | 2004-12-10 | 0 | 0 | 0 | 0.33445 | Caltrans | Caltrans | Caltrans | Caltrans
02 | STIP | 32804 | SHA | 044 | INSTALL LANDSCAPING AND IRRIGATION | 0.03877 | STIP | 2010 | 6650Y | [5 empty] | 500000 | 144000 | 4000 | 80000 | C | 60000 | 254615.9267 | 28.8% | 2011-04-07 | 2015-11-01 | 0 | 0 | 0 | 0.03877 | Caltrans | Caltrans | Caltrans | Caltrans
02 | STIP | 1E060 | MOD | 139 | INSTALL CCTV AND RWIS | 0.51643 | STIP | 2012 | 3383 |  | X | X |  |  | 502000 | 312000 | 65000 | 96000 | 45000 | 106000 | 70958.39 | 62.15% | 2013-12-03 | 2015-07-15 | 0 | 0.17602 | 0.0458 | 0.29461 | Caltrans | Caltrans | Caltrans | Caltrans
02 | STIP | 0E400 | SHA | 005 | UPGRADE VISTA POINT | 0.2125 | STIP | 2012 | 3369 |  |  |  | X |  | 373000 | 332000 | 57000 | 184000 | 6000 | 85000 | 227680.34 | 89.01% | 2012-08-30 | 2014-01-17 | 0 | 0 | 0.00827 | 0.20423 | Caltrans | Caltrans | Caltrans | Caltrans
02 | STIP | 0E440 | SIS | 097 | TURN LANE | 0.31245 | STIP | 2012 | 3371 |  |  |  | X |  | 747000 | 390000 | 107000 | 118000 | 14000 | 151000 | 275057.08 | 52.21% | 2012-10-17 | 2014-01-17 | 0 | 0 | 0.01066 | 0.30179 | Caltrans | Caltrans | Caltrans | Caltrans
02 | STIP | 0E450 | TEH | 005 | INSTALL NATIVE LANDSCAPING | 2.2951 | STIP | 2012 | 3256 |  |  |  | X |  | 1400000 | 688000 | 80000 | 300000 | 8000 | 300000 | 288954.97 | 49.14% | 2012-10-15 | 2014-01-16 | 0 | 0.03066 | 1.4666 | 0.79782 | Caltrans | Caltrans | Caltrans | Caltrans
02 | STIP | 0E840 | SIS | 003 | INSTALL LEFT TURN LANE AT JUNIPER DRIVE | 0.32834 | STIP | 2012 | 3377 |  |  |  | X |  | 747000 | 390000 | 107000 | 118000 | 14000 | 151000 | 283220.28 | 52.21% | 2012-11-14 | 2014-01-17 | 0 | 0 | 0.04106 | 0.28728 | Caltrans | Caltrans | Caltrans | Caltrans
02 | STIP | 2618U | TEH | 005 | CONSTRUCT TWO RAMPS AT ADOBE ROAD (PHASE 1) | 0.13818 | STIP | 2000 | 0266C | [5 empty] | 6030000 | 3109000 | 205000 | 724000 | 377000 | 1803000 | 3108123.35 | 51.56% | 2001-08-14 | 2003-09-26 | 0 | 0 | 0.02281 | 0.11537 | Caltrans | Caltrans | Caltrans | Caltrans
02 | STIP | 4C960 | TRI | 003 | HAYFORK II TE | 0.43576 | STIP | 2012 | 2399A | [5 empty] | 973000 | 440000 | 139000 | 168000 | 13000 | 120000 | 327346.05 | 45.22% | 2012-10-17 | 2014-10-13 | 0 | 0 | 0.005 | 0.43076 | Caltrans | Caltrans | Caltrans | Caltrans
03 | STIP | 29101 | NEV | 267 | PLANTING AND IRRIGATION | 0.46299 | STIP | 2004 | 0140Y | [5 empty] | 900000 | 605000 | 32000 | 260000 | 2000 | 311000 | 623255.86 | 67.22% | 2005-05-31 | 2007-11-16 | 0 | 0 | 0 | 0.46299 | Caltrans | Caltrans | Caltrans | Caltrans
03 | STIP | 35553 | ED | 050 | HIGHWAY PLANTING | 0.42385 | STIP | 2008 | 3209Y | [5 empty] | 425000 | 398000 | H | 138000 | 10000 | 250000 | 239672.14 | 93.65% | 2010-11-03 | 2015-03-01 | 0 | 0 | 0.00617 | 0.41768 | Caltrans | Caltrans | Caltrans | Caltrans
03 | STIP | 36781 | PLA | 080 | CONSTRUCT BYPASS LANE | 0.177 | STIP | 2006 | 0146B | [5 empty] | 5932000 | 3502000 | 110000 | 2300000 | 32000 | 1060000 | 2605912.6533 | 59.04% | 2006-11-07 | 2008-09-11 | 0 | 0 | 0 | 0.177 | Caltrans | Caltrans | Caltrans | Caltrans
03 | STIP | 37120 | SAC | 050 | EXPAND OC TO 6-LANES & MODIFY RAMPS | 2.68 | PARTNERSHIP | [6 empty] | O
03 | STIP | 37280 | ED | 050 | REVISE INTERCHANGES FORNI RD/PLACERVILLE DR I/C | 2.89 | PARTNERSHIP
03 | STIP | 37422 | YOL | 005 | CONSTR N/B I5 TO S/B 113 CONNECTOR | 0.59871 | STIP | 2012 | 0301X | [5 empty] | 56730000 | 11300000 | 650000 | 4750000 | 1000000 | 4900000 | 5917099.3959 | 19.92% | 2018-03-01 | 2022-11-01 | 0 | 0.23 | 0.36 | 0.0087147 | Caltrans | Caltrans | Caltrans | Caltrans
03 | STIP | 37610 | YUB | 070 | CONSTRUCT 4-LANE EXPRESSWAY | 0.94797 | STIP | 2002 | 0366C | [5 empty] | 32730000 | 7566000 | 1123000 | 1731000 | 1185000 | 3527000 | 7644153.19 | 23.12% | 2002-10-01 | 2004-12-17 | 0 | 0 | 0.496 | 0.45197 | Caltrans | Caltrans | Caltrans | Caltrans
03 | STIP | 40230 | GLE | 032 | BRIDGE REPLACEMENT REPLACE STONY CREEK BR #11-29 | 0.02478 | STIP | 2002 | 3775 | [5 empty] | 13392000 | 2193000 | 163596 | 1303003 | 328454 | 397947 | 5510277.11 | 16.38% | 2002-08-29 | 2005-09-30 | 0 | 0 | 0 | 0.02478 | Caltrans | Caltrans | Caltrans | Caltrans
03 | STIP | 41240 | NEV | 020 | CONST NEW INTERCHG & AUX LANES (MSF-ACM) | 3.5859 | STIP | 2012 | 3976 | [5 empty] | 18790000 | 6660000 | 1250000 | 3000000 | 1200000 | 1210000 | 5554611.78 | 35.44% | 2012-11-01 | 2014-12-01 | 0 | 0 | 0.20204 | 3.3839 | Caltrans | Caltrans | Caltrans | Local
03 | STIP | 2E040 | ED | 050 | CONSTRUCT WILDLIFE CROSSING | 0.11099 | STIP | 2010 | 3263 | [5 empty] | 1105000 | 521000 | 153000 | 175000 | 6000 | 187000 | 556167.2 | 47.15% | 2011-05-16 | 2012-08-31 | 0 | 0 | 0.03152 | 0.07947 | Caltrans | Caltrans | Caltrans | Caltrans
03 | STIP | 0A410 | PLA | 049 | WIDEN ROADWAY | 0.40133 | STIP | 2006 | 4776 | [5 empty] | 7815000 | 5010000 | 540000 | 2380000 | 850000 | 1240000 | 7594666.25 | 64.11% | 2006-11-21 | 2008-12-12 | 0 | 0 | 0.18 | 0.22133 | Caltrans | Caltrans | Caltrans | Caltrans
03 | STIP | 0C930 | PLA | 028 | INSTL CURB,GTRS,SDWLK,SGNL & DRAIN | 1.353 | PARTNERSHIP
03 | STIP | 0E770 | SIE | 089 | INSTALL WILDLIFE CROSSING (CULVERT) CULVERT WILL ACT AS A WILDLIFE XIN | 0.03067 | STIP | 2006 | 8003 | [5 empty] | 343000 | 336000 | 121000 | 125000 | 2000 | 88000 | 503016.51 | 97.96% | 2008-04-21 | 2008-12-04 | 0 | 0 | 0 | 0.03067 | Caltrans | Caltrans | Caltrans | Caltrans
03 | STIP | 0E800 | ED | 050 | PLANT ESTABLISHMENT AND PROTECTION | 0.0095 | STIP | 2004 | 3261 | [5 empty] | 549000 | 161000 | 20000 | 31000 | 10000 | 100000 | 162055.13 | 29.33% | 2006-04-01 | 2011-06-30 | 0 | 0 | 0 | 0.0095 | Caltrans | Caltrans | Caltrans | Caltrans
03 | STIP | 0E810 | ED | 089 | PLANT ESTABLISHMENT AND PROTECTION | 0.10024 | STIP | 2006 | 3457 |  |  |  | X |  | 500000 | 182000 | 20000 | 52000 | 10000 | 100000 | 116535.63 | 36.4% | 2006-05-01 | 2014-01-15 | 0 | 0 | 0 | 0.10024 | Caltrans | Caltrans | Caltrans | Caltrans
03 | STIP | 0E830 | PLA | 267 | PLANT ESTABLISHMENT AND PROTECTION | 0.03882 | STIP | 2008 | 5705 | [5 empty] | 500000 | 205000 | 75000 | 60000 | 5000 | 65000 | 158811.5 | 41% | 2009-05-15 | 2012-10-30 | 0 | 0 | 0.01 | 0.02882 | Caltrans | Caltrans | Caltrans | Caltrans
03 | STIP | 0E840 | SAC | 050 | PLANTING AND IRRIGATION | 0.01065 | STIP | 2006 | 6210 | [5 empty] | 500000 | 201000 | 20000 | 80000 | 1000 | 100000 | 238783.27 | 40.2% | 2007-04-16 | 2010-01-04 | 0 | 0 | 0 | 0.01065 | Caltrans | Caltrans | Caltrans | Caltrans
03 | STIP | 0E860 | YOL | 080 | PLANT ESTABLISHMENT AND PROTECTION | 0.08278 | STIP | 2004 | 8914 | [5 empty] | 500000 | 182000 | 20000 | 57000 | 5000 | 100000 | 139430.8 | 36.4% | 2005-07-15 | 2009-06-19 | 0 | 0 | 0 | 0.08278 | Caltrans | Caltrans | Caltrans | Caltrans
03 | STIP | 0E870 | YOL | 005 | PLANT ESTABLISHMENT AND PROTECTION | 0.23625 | STIP | 2008 | 8557 |  |  |  | X |  | 500000 | 158000 | 50000 | 25000 | 3000 | 80000 | 141212.99 | 31.6% | 2009-09-10 | 2014-03-01 | 0 | 0 | 0.02807 | 0.20818 | Caltrans | Caltrans | Caltrans | Caltrans
03 | STIP | 1A431 | SUT | 099 | WIDEN HIGHWAY | 0.23028 | STIP | 2006 | 8361A | [5 empty] | 9995000 | 3902000 | 423000 | 1601000 | 678000 | 1200000 | 4091843.13 | 39.04% | 2006-06-28 | 2007-08-24 | 0 | 0 | 0 | 0.23028 | Caltrans | Caltrans | Caltrans | Caltrans
03 | STIP | 1A46U | SUT | 099 | WIDEN EXISTING ROADWAY | 0.6688 | SHOPP | 2002 | 8351 | [5 empty] | 18072000 | 4627000 | 1382000 | 1801000 | 365000 | 1079000 | 5946463.22 | 25.6% | 2003-02-01 | 2005-10-11 | 0 | 0 | 0.27426 | 0.39454 | Caltrans | Caltrans | Caltrans | Caltrans
03 | STIP | 1C520 | SAC | 005 | CONSTRUCT NEW INTERCHANGE | 4.04 | PARTNERSHIP
03 | STIP | 1C950 | SAC | 050 | CONSTRUCT INTERCHANGE | 1.21 | PARTNERSHIP | [6 empty] | O
03 | STIP | 1F260 | SIE | 089 | CONSTRUCT TWO WILDLIFE UNDERCROSSINGS AND WILDLIFE | 1.0531 | STIP | 2012 | 8005 |  | X | X |  |  | 2055000 | 655000 | 150000 | 175000 | 5000 | 325000 | 17251.12 | 31.87% | 2014-06-01 | 2015-07-01 | 0 | 0.99311 | 0.06 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
03 | STIP | 1F270 | PLA | 020 | WILDLIFE MOVEMENT STUDIES USING TRACKING AND MOVEMENT DEVICES | 0.11 | STIP | 2012 | 4625 | [5 empty] | 502000 | 150000 | 20000 | A | C | 130000 | 0 | 29.88% | - - | - - | 0.11 | 0 | 0 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
03 | STIP | 1F280 | GLE | 005 | NATIVE PLANTING | 1.2339 | STIP | 2012 | 3708 |  | X |  |  |  | 640000 | 210000 | 40000 | 80000 | 5000 | 85000 | 27536.93 | 32.81% | 2014-03-03 | 2017-04-03 | 0 | 0.69 | 0.5 | 0.04394 | Caltrans | Caltrans | Caltrans | Caltrans
03 | STIP | 1F290 | COL | 005 | NATIVE PLANTING | 0.34 | STIP | 2012 | 2788 |  | X |  |  |  | 640000 | 210000 | 40000 | 80000 | 5000 | 85000 | 20426.08 | 32.81% | 2014-02-15 | 2017-04-01 | 0 | 0.21 | 0.03 | 0.1 | Caltrans | Caltrans | Caltrans | Caltrans
03 | STIP | 2E470 | ED | 050 | CONSTRUCT PEDESTRIAN OVERCROSSING | 0.62507 | PARTNERSHIP | [6 empty] | O
03 | STIP | 3555U | ED | 050 | WIDEN HIGHWAY AND BRIDGES | 0.30347 | STIP | 2012 | 3209 | [5 empty] | 42754000 | 22254000 | 2533000 | 8082000 | 2076000 | 9563000 | 22926925.68 | 52.05% | 2006-03-22 | 2009-09-30 | 0 | 0 | 0.16 | 0.14347 | Caltrans | Caltrans | Caltrans | Caltrans
03 | STIP | 3822V | BUT | 149 | CONSTRUCT 4 LANE EXPRESSWAY | 0.72373 | STIP | 2004 | 0016W | [5 empty] | 111884000 | 22295000 | 5666000 | 5000000 | 1000000 | 10629000 | 28559718.8 | 19.93% | 2006-01-31 | 2009-01-20 | 0 | 0 | 0.17 | 0.55373 | Caltrans | Caltrans | Caltrans | Caltrans
03 | STIP | 3864U | SUT | 070 | WIDEN AND REALIGN ROADWAY | 1.2904 | STIP | 2008 | 0289P | [5 empty] | 108430000 | 29600000 | 2000000 | 10000000 | 4600000 | 13000000 | 31313867.68 | 27.3% | 2007-12-06 | 2011-06-28 | 0 | 0 | 0.70038 | 0.59 | Caltrans | Caltrans | Caltrans | Caltrans
03 | STIP | 3A040 | BUT | 099 | CONSTRUCT AUX LANES, IMPROVE RAMPS | 0.15985 | PARTNERSHIP
03 | STIP | 3A270 | BUT | 099 | WIDEN TO 5 LNS, INST SIGNAL, CURB SIDEWALK, GUTTER, STORM DRAIN SYS | 0.40367 | STIP | 2008 | 2411 | [5 empty] | 5451000 | 953000 | 192000 | 450000 | 311000 | G | 1819351.26 | 17.48% | 2009-05-29 | 2010-03-26 | 0 | 0 | 0.12703 | 0.27664 | Local | Local | Caltrans | Local
03 | STIP | 3A760 | PLA | 089 | OPERATIONAL IMPROVEMENTS REALIGNMENT, BIKE/PED IMPROVEMENTS | 0.92297 | PARTNERSHIP
03 | STIP | 3C200 | BUT | 099 | INSTALL TRAFFIC SIGNALS | 0.0297 | STIP | 2004 | 2420 | [5 empty] | 713000 | 433000 | 67000 | 197000 | 11000 | 158000 | 751672.1 | 60.73% | 2006-08-21 | 2007-07-19 | 0 | 0 | 0 | 0.0297 | Caltrans | Caltrans | Caltrans | Caltrans
03 | STIP | 3C630 | SAC | 099 | RECONSTRUCT INTERCHANGE | 0.55 | PARTNERSHIP
03 | STIP | 4E28U | ED | 050 | CONSTR AUX LANES, WIDEN BRIDGES, AND RECONSTRUCT RAMPS | 1.1873 | PARTNERSHIP
03 | STIP | 4E480 | SAC | 099 | INSTALL NATIVE PLANTING | 0.67 | STIP | 2012 | 6911 | [5 empty] | 750000 | 447000 | 30000 | 120000 | 10000 | 287000 | 53361.08 | 59.6% | 2013-03-15 | 2016-11-01 | 0 | 0 | 0.06 | 0.61 | Caltrans | Caltrans | Caltrans | Caltrans
03 | STIP | 4E500 | SIE | 089 | CONSTRUCT WILDLIFE CROSSING | 0.9 | STIP | 2012 | 8004 |  |  |  | X |  | 460000 | 390000 | 80000 | 170000 | 10000 | 130000 | 148642.57 | 84.78% | 2013-06-01 | 2014-01-02 | 0 | 0 | 0.07 | 0.83 | Caltrans | Caltrans | Caltrans | Caltrans
04 | STIP | 12061 | NAP | 029 | CONSTRUCT INTERCHANGE X | 0.10842 | STIP | 2004 | 0377A | [5 empty] | 43709000 | 24767000 | 851000 | 11187000 | 1729000 | 11000000 | 19281346.93 | 56.66% | 2002-01-22 | 2005-06-16 | 0 | 0 | 0.10842 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
04 | STIP | 17493 | SCL | 152 | CONSTRUCT TRUCK CLIMBING LANE SOFT MEDIAN BARRIER | 0.00759 | STIP | 2006 | 0486G | [5 empty] | 11775000 | 6999000 | 836000 | 3047000 | 412000 | 2704000 | 6882009.195 | 59.44% | 2007-06-21 | 2008-05-13 | 0 | 0 | 0.00759 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
04 | STIP | 22613 | MRN | 101 | CONSTRUCT HOV LANES | 0.11251 | STIP | 2002 | 342L3 | [5 empty] | 8803000 | 12769000 | 1200000 | 6099000 | 438000 | 5032000 | 11454203.58 | 145.1% | 2004-02-17 | 2006-12-01 | 0 | 0 | 0.03042 | 0.08209 | Caltrans | Caltrans | Caltrans | Caltrans
04 | STIP | 22859 | CC | 004 | WIDEN HIGHWAY AND BRIDGE | 17.9906 | STIP | 2008 | 0192E | [5 empty] | 74016445 | 17486000 | H | 11050000 | 2186000 | 15300000 | 14087244.732 | 23.62% | 2010-04-15 | 2014-07-01 | 0 | 0 | 1.0006 | 16.99 | Local | Local | Caltrans | Caltrans
04 | STIP | 22910 | CC | 680 | MODIFY INTERCHANGE | 7.6096 | PARTNERSHIP | [6 empty] | O
04 | STIP | 23303 | ALA | 084 | CONSTRUCT 4 LANE HIGHWAY | 1.1925 | PARTNERSHIP
04 | STIP | 23565 | SM | 101 | RECONSTRUCT INTERCHANGE | 8.9033 | STIP | 2012 | 0690A | X |  |  |  |  | 16791000 | 14689000 | 5534000 | 5475000 | G | 3680000 | 1896910.91 | 87.48% | 2016-01-01 | 2018-01-01 | 1.962 | 6.4714 | 0.46987 | 0 | Caltrans | Local | Local | Caltrans
04 | STIP | 23584 | SM | 101 | RECONSTRUCT INTERCHANGE | 9.8415 | PARTNERSHIP
04 | STIP | 24541 | SON | 101 | WIDEN FREEWAY 4 TO 6 LANES (HOV) | 0.75528 | STIP | 2004 | 0789A | [5 empty] | 62955000 | 18480000 | 4063000 | 7465000 | 800000 | 6152000 | 30569414.9 | 29.35% | 2006-03-30 | 2009-04-21 | 0 | 0 | 0.75528 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
04 | STIP | 24543 | SON | 101 | FOLLOW UP LANDSCAPING | 3.4975 | STIP | 2012 | 0789F | [5 empty] | 1880000 | 550000 | H | 250000 | H | 300000 | 90115.17 | 29.26% | 2015-03-01 | 2019-03-01 | 0 | 3.3897 | 0.10789 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
04 | STIP | 24544 | SON | 101 | COLLEGE AVENUE IMPROVEMENT | 5.0871 | STIP | 2012 | 0789E | [5 empty] | 6880000 | 1750000 | H | 750000 | 550000 | 450000 | 1333170.33 | 25.44% | 2013-10-16 | 2014-11-06 | 0 | 0.33637 | 0.00883 | 4.7419 | Caltrans | Caltrans | Caltrans | Caltrans
04 | STIP | 25376 | ALA | 680 | HIGHWAY PLANTING AND IRRIGATION | 0.36853 | STIP | 2008 | A0157D | [5 empty] | 2000000 | 1661000 | E | 1041000 | 20000 | 600000 | 1793966.71 | 83.05% | 2010-07-07 | 2015-01-30 | 0 | 0.016 | 0.01162 | 0.34091 | Caltrans | Caltrans | Caltrans | Caltrans
04 | STIP | 25460 | SM | 001 | WIDEN FOR OPERATIONAL IMPROVEMENTS | 3.77 | STIP | 2012 | 0632C | [5 empty] | 5400000 | 7073000 | 4000000 | 1573000 | G | 1500000 | 1455120.12 | 131% | 2015-02-01 | 2016-06-01 | 0 | 2.7163 | 1.0537 | 0 | Local | Local | Local | Caltrans
04 | STIP | 26404 | SON | 101 | CONSTRUCT NEW NORTH BOUND ON RAMP TO ROUTE 101 FROM E WASHINGTON AVE | 0.4432 | STIP | 2008 | T0181 | [5 empty] | 17480000 | 5470000 | H | 3300000 | G | 2170000 | 1847039.79 | 31.29% | 2011-11-01 | 2013-06-30 | 0 | 0 | 0.18388 | 0.25932 | Caltrans | Local | Local | Caltrans
04 | STIP | 26409 | MRN | 101 | REALIGN ROUTE 101 AT SAN ANTONIO CURVE | 3.5031 | STIP | 2012 | 0360G |  |  | X |  |  | 57315000 | 13525000 | 668000 | 4932000 | 265000 | 7660000 | 2147411.49 | 23.6% | 2014-11-01 | 2016-12-02 | 0 | 2.0532 | 1.4499 | 0 | Caltrans | Local | Caltrans | Caltrans
04 | STIP | 28120 | NAP | 029 | CONSTRUCT SOUTHBOUND FLYOVER FROM RTE 221 TO RTE 29/12 | 7.1562 | STIP | 2012 | 0376 | [5 empty] | 37250000 | 10990000 | 3700000 | 5700000 | 70000 | 1520000 | 4731184.76 | 29.5% | 2019-03-15 | 2020-12-15 | 6.2909 | 0.86525 | 0 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
04 | STIP | 28552 | SCL | 880 | BRIDGE WIDENING AND RECONSTRUCTION | 0.02337 | STIP | 2000 | 0017B | [5 empty] | 60361000 | 21143000 | 4560000 | 3006000 | 3180000 | 10397000 | 15187922.5905 | 35.03% | 2001-07-26 | 2007-04-20 | 0 | 0.01599 | 0.00738 | 0 | Caltrans | Caltrans | Local | Caltrans
04 | STIP | 28600 | ALA | 680 | CONST NB HOV LANE, AUXILIARY LANES, INSTALL RAMP METERING AND WIDEN | 20.6975 | STIP | 2010 | 0177 | [5 empty] | 401100000 | 4000000 | 4000000 | Q | Q | Q | 4758025.33 | 0.9973% | 2015-05-01 | 2018-05-01 | 0 | 18.7947 | 1.9028 | 0 | Caltrans | Local | Local | Caltrans
04 | STIP | 29494 | ALA | 024 | ROADWAY PLANTING | 3.1294 | STIP | 2012 | 0057J |  | X | X |  |  | 3700000 | 1510000 | 410000 | F | F | 1100000 | 7226.0648 | 40.81% | 2014-04-30 | 2018-07-13 | 0 | 2.4755 | 0.03412 | 0.61978 | Caltrans | Caltrans | Caltrans | Caltrans
04 | STIP | 43830 | SCL | 085 | CONSTRUCT HOV DIRECT CONNECTORS & ONE CONNECTOR | 0.005 | PARTNERSHIP | [6 empty] | O
04 | STIP | 0A271 | SCL | 087 | HIGHWAY PLANTING | 1.0875 | STIP | 2008 | 2204G | [5 empty] | 1200000 | 1400000 | 201000 | 442000 | 32000 | 725000 | 1001082.8943 | 116.7% | 2009-01-16 | 2014-12-01 | 0 | 0 | 0.00671 | 1.0807 | Caltrans | Caltrans | Caltrans | Caltrans
04 | STIP | 0A530 | SOL | 080 | I-80/I-680/SR-12 I/C IMPROVEMENTS, WIDEN EXIST FREEWAY, CONSTRUCT NEW | 11.0664 | PARTNERSHIP
04 | STIP | 0G230 | SCL | 152 | RTE 152 NEW ALIGNMENT FR RTE 101 TO RTE 156. REALIGN H/W & EVAL CORRID | 4.4823 | PARTNERSHIP
04 | STIP | 0G500 | VAR | VAR | STATEWIDE DIGITAL SCANNING OF PAPER COPIES OF CULTURAL RESOURCES FILES | 2.8893 | STIP | 2012 | 2127J | [5 empty] | 1630000 | 1630000 | 1630000 | D | D | D | 5709.37 | 100% | 2014-11-01 | 2014-11-01 | 2.8893 | 0 | 0 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
04 | STIP | 0G510 | MRN | VAR | DEVELOP AN INTERPRETATIVE INVENTORY OF CULTURE SITES, WATERCOURSE, AND | 0.29591 | STIP | 2012 | 2127K | X |  |  |  |  | A | 1494000 | 1494000 | A | A | A | 20561.97 | NA | - - | - - | 0.15938 | 0.13653 | 0 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
04 | STIP | 0T145 | SOL | 037 | PLANTING AND IRRIGATION | 1.6018 | STIP | 2008 | 5201F |  |  |  | X |  | 1579000 | 1527000 | H | 758000 | C | 769000 | 922152.65 | 96.71% | 2010-01-15 | 2014-03-03 | 0 | 0 | 0.01428 | 1.5875 | Caltrans | Caltrans | Caltrans | Caltrans
04 | STIP | 0T163 | SOL | 080 | HIGHWAY PLANTING | 3.3568 | STIP | 2012 | 8273B | [5 empty] | 1086000 | 1458000 | H | 700000 | 50000 | 708000 | 0 | 134.3% | 2016-01-02 | 2018-02-01 | 0 | 3.1924 | 0.16437 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
04 | STIP | 1123J | SM | 001 | POND REPAIR AND REVEGETATION | 13.4499 | ER
04 | STIP | 1123U | SM | 001 | CONSTRUCT TUNNELS, APPROACH ROADS AND OMC BUILDING | 12.7345 | ER
04 | STIP | 2261V | MRN | 101 | WIDEN FREEWAY | 0.3136 | STIP | 2004 | 342LV | [5 empty] | 73353000 | 26038000 | 1500000 | 10533000 | 1869000 | 12136000 | 23840769.25 | 35.5% | 2006-04-01 | 2009-05-04 | 0 | 0 | 0.11889 | 0.19471 | Caltrans | Caltrans | Caltrans | Caltrans
04 | STIP | 2332C | ALA | 262 | UPPR,WIDENING OF ROUTE 262,AND COMP CONST. OF KATO RD ON AND OFF RAMP. | 7.8508 | PARTNERSHIP
04 | STIP | 2332G | ALA | 880 | REQUIRED MITIGATION REPLACEMENT HIGHWAY PLANTING ON RTE 880 AND 262 | 2.7423 | STIP | 2004 | 0016F |  |  | X |  |  | 4110000 | 1070176.7442 | H | 560000 | 10176.7442 | 500000 | 62499.81 | 26.04% | 2015-01-01 | 2016-01-28 | 0 | 2.5942 | 0.14807 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
04 | STIP | 2332U | ALA | 880 | WIDEN EXISITING FREEWAY | 0.33044 | STIP | 2004 | 0016F | [5 empty] | 133780000 | 38390066.2867 | 6974000 | 12523419.7751 | 1262646.5116 | 17630000 | 26523537.5 | 28.7% | 2004-12-22 | 2009-11-18 | 0 | 0 | 0.30804 | 0.0224 | Local | Caltrans | Local | Caltrans
04 | STIP | 2490A | ALA | 238 | HIGHWAY PLANTING AND IRRIGATION | 0.42393 | PARTNERSHIP
04 | STIP | 2642A | SM | 101 | TWO YEAR PLANT ESTABLISHMENT LANDSCAPE PROJECT | 0.40137 | STIP | 2012 | 0700C |  |  |  | X |  | 220000 | 126000 | H | 33000 | H | 93000 | 154310.51 | 57.27% | 2011-10-14 | 2014-03-01 | 0 | 0 | 0.0635 | 0.33787 | Local | Caltrans | Local | Caltrans
04 | STIP | 2A910 | MRN | 101 | INSTALL MISSION BELL MARKERS IN MARIN AND SONOMA COUNTIES | 0.01178 | STIP | 2010 | 0338G | [5 empty] | 161000 | 141000 | 98000 | 18000 | 5000 | 20000 | 144027.39 | 87.58% | 2012-01-31 | 2013-02-15 | 0 | 0 | 0.01178 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
04 | STIP | 2A930 | MRN | 101 | VEGETATION MANAGEMENT PHASE II | 3.1498 | STIP | 2008 | 0343D | [5 empty] | 465000 | 74000 | 8000 | 40000 | 6000 | 20000 | 364167.2 | 15.91% | 2010-05-15 | 2014-06-01 | 0 | 0 | 0.1773 | 2.9725 | Caltrans | Caltrans | Caltrans | Local
04 | STIP | 3A100 | SON | 001 | KASHAYA POMO CULTURAL LANDSCAPE PROJECT | 1.2952 | STIP | 2006 | 0748I |  |  |  | X |  | 573000 | 107000 | 107000 | J | J | J | 299835.39 | 18.67% | 2008-05-28 | 2014-06-28 | 0 | 0 | 0 | 1.2952 | Caltrans | Caltrans | Caltrans | Caltrans
04 | STIP | 3G580 | SF | 101 | CONSTRUCT MOVEABLE MEDIAN BARRIER | 0.88607 | PARTNERSHIP | [6 empty] | O
04 | STIP | 4396U | SCL | 087 | WIDEN ROADWAY AND BRIDGE REPAIR | 0.91113 | PARTNERSHIP
04 | STIP | 4876A | SCL | 101 | REPLACEMENT HIGHWAY PLANTING | 1.3351 | STIP | 2010 | 0468F | [5 empty] | 675000 | 786000 | H | 424000 | H | 362000 | 575219.71 | 116.4% | 2010-12-15 | 2015-06-01 | 0 | 0 | 0.00366 | 1.3315 | Caltrans | Caltrans | Caltrans | Caltrans
04 | STIP | 4A925 | SM | 101 | INSTALL INTELLIGENT TRANSPORTATION SYSTEM ELEMENTS | 1.4214 | STIP | 2012 | 2140T |  |  |  | X |  | 6980000 | 1735000 | H | 670000 | 20000 | 1045000 | 0 | 24.86% | 2012-12-19 | 2013-12-01 | 0 | 0 | 0 | 1.4214 | Local | Caltrans | Caltrans | Caltrans
04 | STIP | 4G100 | ALA | 680 | WIDEN RAMPS AND CONSTRUCT RAMP METERING FACILITIES ON ROUTE 680 | 6.517 | STIP | 2012 | 0521J |  |  |  | X |  | 5693000 | 3100000 | 1400000 | 700000 | D | 1000000 | 0 | 54.45% | 2012-09-29 | 2013-11-15 | 0 | 0 | 0.06832 | 6.4487 | Caltrans | Caltrans | Caltrans | Caltrans
04 | STIP | 4G111 | ALA | 680 | WIDEN RAMPS AND CONSTRUCT RAMP METERING FACILITIES ON ROUTE 680 | 6.249 | STIP | 2012 | 0521K | X |  | X |  |  | 22050000 | 6500000 | 1500000 | 1700000 | H | 3300000 | 0 | 29.48% | 2015-01-15 | 2017-03-15 | 1.9273 | 4.3217 | 0 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
05 | STIP | 12911 | SCR | 001 | HIGHWAY PLANTING | 0.19991 | STIP | 2008 | 0542H |  |  |  | X |  | 944000 | 853000 | H | 325000 | C | 528000 | 711579.51 | 90.36% | 2010-02-11 | 2013-11-01 | 0 | 0 | 0.00171 | 0.1982 | Caltrans | Caltrans | Caltrans | Caltrans
05 | STIP | 31600 | MON | 156 | WIDEN TO 4-LN DIVIDED EXPRESSWAY AND BUILD INTERCHANGES | 21.1149 | STIP | 2012 | 0057C | [5 empty] | 352000000 | 45859000 | 10194000 | 16265000 | 3000000 | 16400000 | 9697022.85 | 13.03% | 2018-01-19 | 2022-02-11 | 0 | 14.7344 | 6.3805 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
05 | STIP | 33074 | SLO | 046 | PERFORM HIGHWAY PLANTING AND INSTALL IRRIGATION SYSTEM | 0.20972 | STIP | 2008 | 0226Y | [5 empty] | 346000 | 239000 | H | 177000 | C | 62000 | 393904.16 | 69.08% | 2010-12-07 | 2015-03-01 | 0 | 0 | 0 | 0.20972 | Caltrans | Caltrans | Caltrans | Caltrans
05 | STIP | 33075 | SLO | 046 | BRIDGE REPLACEMENT | 4.9213 | STIP | 2012 | 0226E | [5 empty] | 4400000 | 1774000 | H | 1000000 | 24000 | 750000 | 1141710.52 | 40.32% | 2013-05-01 | 2014-09-01 | 0 | 0.11229 | 0.02395 | 4.7851 | Caltrans | Caltrans | Caltrans | Caltrans
05 | STIP | 33076 | SLO | 046 | LANDSCAPE MITIGATION | 0.94363 | STIP | 2012 | 0226F |  | X | X |  |  | 1250000 | 660000 | H | 400000 | 10000 | 250000 | 822.96 | 52.8% | 2014-06-06 | 2017-12-01 | 0 | 0.93852 | 0.00326 | 0.00185 | Caltrans | Caltrans | Caltrans | Caltrans
05 | STIP | 33078 | SLO | 046 | CONVERT TO 4-LANE EXPRESSWAY | 15.4755 | STIP | 2012 | 0226H | [5 empty] | 71000000 | 16500000 | H | 7000000 | 2500000 | 7000000 | 1860774.2256 | 23.24% | 2016-03-01 | 2018-04-01 | 0 | 12.7312 | 2.7443 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
05 | STIP | 34490 | SBT | 156 | WIDEN 2 TO 4 LANES | 8.8962 | STIP | 2012 | 0297 | [5 empty] | 58591000 | 12120000 | 3936000 | 3778000 | 1183000 | 3223000 | 7442034.16 | 20.69% | 2015-09-17 | 2017-10-01 | 0 | 6.6508 | 2.2454 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
05 | STIP | 34951 | MON | 101 | LANDSCAPE | 0.15861 | STIP | 2010 | 0318Y | [5 empty] | 687000 | 573000 | H | 291000 | 2000 | 280000 | 366197.59 | 83.41% | 2012-02-28 | 2015-09-01 | 0 | 0 | 0.00417 | 0.15444 | Caltrans | Caltrans | Caltrans | Caltrans
05 | STIP | 36150 | SLO | 101 | CONSTRUCT NEW ON-RAMP & WIDEN AND MODIFY RAMPS & STRIPING | 0.19266 | PARTNERSHIP | [6 empty] | O
05 | STIP | 40282 | SLO | 101 | LANDSCAPE | 0.04808 | STIP | 2010 | 0520Y | [5 empty] | 586000 | 457000 | H | 232000 | C | 225000 | 486704.9 | 77.99% | 2011-11-09 | 2015-06-15 | 0 | 0 | 0 | 0.04808 | Caltrans | Caltrans | Caltrans | Caltrans
05 | STIP | 44130 | SCR | 001 | REVISE INTERCHANGE | 2.198 | PARTNERSHIP | [6 empty] | O
05 | STIP | 44781 | SB | 101 | PLANTING AND IRRIGATION | 0.34602 | STIP | 2010 | 0478Y | [5 empty] | 1386000 | 1105000 | H | 300000 | 5000 | 800000 | 786405.81 | 79.73% | 2010-06-16 | 2015-03-02 | 0 | 0 | 0.00071 | 0.34531 | Caltrans | Caltrans | Caltrans | Caltrans
05 | STIP | 44800 | MON | 068 | WIDENING & INTERSECTION IMPROVEMENTS (OVERSIGHT) | 0.96116 | PARTNERSHIP
05 | STIP | 46380 | SB | 101 | CONSTRUCT INTERCHANGE | 5.7045 | STIP | 2012 | 4638 |  |  |  | X |  | 17358000 | 7172000 | 2486000 | 2446000 | 340000 | 1900000 | 5623311.06 | 41.32% | 2012-07-26 | 2013-12-31 | 0 | 0.0264 | 0.29119 | 5.3869 | Caltrans | Caltrans | Caltrans | Caltrans
05 | STIP | 46381 | SB | 101 | UVP MITIGATION PLANTING | 0.48894 | STIP | 2012 | 4638Y |  | X | X |  |  | 650000 | 710000 | H | 305000 | 5000 | 400000 | 0 | 109.2% | 2014-01-01 | 2017-10-01 | 0 | 0.29612 | 0.00086 | 0.19196 | Caltrans | Caltrans | Caltrans | Caltrans
05 | STIP | 47450 | SLO | 101 | CONSTRUCT NEW INTERCHANGE (WILLOW RD) | 0.05471 | PARTNERSHIP
05 | STIP | 0161E | MON | 101 | CONSTRUCT INTERCHANGES AND OPERATIONAL IMPROVEMENTS | 26.8701 | STIP | 2010 | 0058G | [5 empty] | 156588000 | 69321000 | 19600000 | 26300000 | 8821000 | 14600000 | 59876296.75 | 44.27% | 2011-01-25 | 2015-06-01 | 0 | 0 | 4.0289 | 22.8412 | Caltrans | Caltrans | Caltrans | Caltrans
05 | STIP | 0161H | MON | 101 | LANDSCAPE MITIGATION | 0.96096 | STIP | 2012 | 0058Y | [5 empty] | 5300000 | 1560000 | H | 500000 | 10000 | 1050000 | 0 | 29.43% | 2015-07-22 | 2019-08-19 | 0 | 0.95271 | 0.00825 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
05 | STIP | 0A381 | SLO | 001 | LANDSCAPE MITIGATION | 0.01045 | PARTNERSHIP
05 | STIP | 0C640 | SB | 246 | PASSING LANES AND OPERATIONAL IMPROVEMENTS | 4.0022 | STIP | 2012 | 6400 |  | X | X |  |  | 20500000 | 10124000 | 3994000 | 2300000 | 720000 | 3110000 | 5035785.63 | 49.39% | 2013-11-25 | 2015-12-31 | 0 | 3.3371 | 0.53543 | 0.12958 | Caltrans | Caltrans | Caltrans | Caltrans
05 | STIP | 0C730 | SCR | 001 | ADDITION OF HOV OR HOT LANE IN EACH DIRECTION | 3.5927 | PARTNERSHIP | [6 empty] | O
05 | STIP | 0G820 | SB | 225 | INTERSECTION IMPROVEMENTS | 0.65132 | PARTNERSHIP | [6 empty] | O
05 | STIP | 0H730 | SLO | 101 | PSR-PDS RECONSTRUCT INTERCHANGE | 0.83528 | PARTNERSHIP
05 | STIP | 0H823 | MON | 068 | CONSTRUCT DUAL WB LEFT TURN LANES | 0.14903 | PARTNERSHIP
05 | STIP | 0L570 | MON | 001 | OPERATIONAL IMPROVEMENTS | 0.35928 | PARTNERSHIP | [6 empty] | O
05 | STIP | 0M14U | SB | 101 | REPLACE EXISTING BRIDGES | 0.02379 | STIP | 2008 | 1840 | [5 empty] | 11174000 | 7129000 | 1049000 | 3051000 | 559000 | 2470000 | 7863501.88 | 63.8% | 2009-12-22 | 2011-12-02 | 0 | 0 | 0 | 0.02379 | Caltrans | Caltrans | Caltrans | Caltrans
05 | STIP | 0N400 | SLO | 001 | TRANSPORTATION ENHANCEMENT COASTAL ACCESS AND PROTECTION | 0.52302 | STIP | 2012 | 1845 | [5 empty] | 2650000 | 1483000 | 500000 | 417000 | 150000 | 416000 | 1239654.8 | 55.96% | 2012-10-22 | 2017-03-01 | 0 | 0 | 0.03983 | 0.48319 | Caltrans | Caltrans | Caltrans | Caltrans
05 | STIP | 0N700 | SB | 101 | CONSTRUCT HOV LANES | 15.7609 | STIP | 2012 | 7101 | X |  |  |  |  | 547300000 | 67935000 | 9450000 | 12585000 | 900000 | 45000000 | 10933977.83 | 12.41% | 2017-05-01 | 2021-07-01 | 2.099 | 12.9322 | 0.72963 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
05 | STIP | 0T070 | SB | 101 | INSTALL NEW NATIVE DROUGHT TOLERANT TREES, SHRUBS AND MULCHING | 0.96604 | STIP | 2012 | 2266 |  | X | X |  |  | 1250000 | 595000 | 110000 | 250000 | 5000 | 230000 | 113854.91 | 47.6% | 2014-07-15 | 2018-07-15 | 0 | 0.96071 | 0.00533 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
05 | STIP | 0T500 | SCR | VAR | VISTA POINT INTERPRETIVE DISPLAYS | 2.524 | STIP | 2012 | 2272 |  | X | X |  |  | 703000 | 1330000 | 390000 | 540000 | 10000 | 390000 | 84546.68 | 189.2% | 2014-06-15 | 2015-07-15 | 0 | 2.509 | 0.01497 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
05 | STIP | 0T510 | SLO | VAR | CORRIDOR MASTER PLAN | 0.93932 | STIP | 2012 | 2273 | [5 empty] | 275000 | 430000 | 430000 | A | A | A | 9898.05 | 156.4% | - - | - - | 0.93932 | 0 | 0 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
05 | STIP | 1A880 | SB | 166 | TRANSPORTATION ACCHAELOGICAL COLLECTIONS | 5.7912 | STIP | 2012 | 2342 | [5 empty] | A | 1383000 | 1383000 | A | A | A | 125.78 | NA | - - | - - | 5.7912 | 0 | 0 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
05 | STIP | 4482U | SB | 101 | RECONSTRUCT INTERCHANGES | 12.9472 | STIP | 2012 | 0482 | [5 empty] | 82341000 | 29170000 | 6770000 | 8000000 | 2400000 | 12000000 | 12332237.67 | 35.43% | 2014-12-01 | 2018-12-01 | 0 | 9.264 | 3.6832 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
05 | STIP | 4611U | SB | 217 | CONSTRUCT NEW INTERCHANGE | 1.3037 | PARTNERSHIP | [6 empty] | O
06 | STIP | 32550 | KIN | 198 | CONSTRUCT INTERCHANGE | 7.2469 | STIP | 2012 | 4330 | [5 empty] | 32104000 | 6322000 | 1471000 | 1630000 | 451000 | 2770000 | 6946489.93 | 19.69% | 2012-10-24 | 2015-09-30 | 0 | 0 | 0.22695 | 7.0199 | Caltrans | Caltrans | Caltrans | Caltrans
06 | STIP | 32551 | KIN | 198 | LANDSCAPING AND PLANT ESTABLISHMENT | 1.2031 | STIP | 2012 | 4330Y |  | X | X |  |  | 1022000 | 102000 | H | H | H | 102000 | 0 | 9.98% | 2014-09-15 | 2016-10-15 | 0 | 1.2031 | 0 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
06 | STIP | 34235 | FRE | 180 | HIGHWAY PLANTING | 1.0349 | STIP | 2012 | 6489 | X |  |  |  |  | 4110000 | 1012000 | 166000 | 374000 | 10000 | 462000 | 0 | 24.62% | 2016-04-01 | 2020-09-01 | 0.45624 | 0.5787 | 0 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
06 | STIP | 34251 | FRE | 180 | CONSTRUCT FOUR LANE EXPRESSWAY | 0.3793 | PARTNERSHIP | [7 empty] | 64644000 | 13609000 | H | 4412000 | 5597000 | 3600000 | 13488002.23 | 21.05% | 2009-09-10 | 2011-11-28 | 0 | 0 | 0.16418 | 0.21512 | Caltrans | Caltrans | Caltrans | Caltrans
06 | STIP | 34252 | FRE | 180 | 2C TO 4E ON EXISTING ALIGNMENT | 8.1515 | STIP | 2012 | 0091B | [5 empty] | 37851000 | 13249000 | H | 5400000 | 3849000 | 4000000 | 7871354.55 | 35% | 2013-06-01 | 2015-09-01 | 0 | 0.00418 | 1.4083 | 6.739 | Caltrans | Caltrans | Caltrans | Caltrans
06 | STIP | 34253 | FRE | 180 | 2C TO 4E ON NEW ALIGNMENT | 15.3389 | STIP | 2012 | 0091C | [5 empty] | 75154000 | 14896000 | H | 5167000 | 3229000 | 6500000 | 3822647.7 | 19.82% | 2015-05-01 | 2018-08-01 | 0 | 7.977 | 7.3618 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
06 | STIP | 34256 | FRE | 180 | HIGHWAY PLANTING AND IRRIGATION ON NEW FREEWAY | 0.94244 | STIP | 2010 | 6434 | [5 empty] | 5640000 | 1305000 | 93000 | 504000 | 8000 | 700000 | 619386.49 | 23.14% | 2012-08-23 | 2016-11-01 | 0 | 0 | 0 | 0.94244 | Caltrans | Caltrans | Caltrans | Caltrans
06 | STIP | 35071 | FRE | 099 | PERFORM HIGHWAY PLANTING | 0.17883 | STIP | 2008 | 1530Y | [5 empty] | 1061000 | 669000 | 44000 | 300000 | C | 325000 | 776405.62 | 63.05% | 2009-12-23 | 2014-12-01 | 0 | 0 | 0 | 0.17883 | Caltrans | Caltrans | Caltrans | Caltrans
06 | STIP | 35341 | KER | 046 | WIDEN HIGHWAY WITH HOT MIX ASPHALT ON AGGREGATE BASE | 0.0598 | STIP | 2008 | 3380A | [5 empty] | 59440000 | 12254000 | 2421000 | 3801000 | 1400000 | 4632000 | 10369310.33 | 20.62% | 2010-05-19 | 2011-10-27 | 0 | 0 | 0.04074 | 0.01906 | Caltrans | Caltrans | Caltrans | Caltrans
06 | STIP | 36021 | TUL | 099 | 4-LN FWY TO 6-LN FWY | 15.2155 | STIP | 2012 | 6400A | [5 empty] | 42000000 | 10900000 | H | 4000000 | 300000 | 6600000 | 2852701.87 | 25.95% | 2012-12-07 | 2015-07-01 | 0 | 0 | 0.07038 | 15.1451 | Caltrans | Caltrans | Caltrans | Caltrans
06 | STIP | 36024 | TUL | 099 | 4F TO 6F | 9.1786 | STIP | 2012 | 6400D | [5 empty] | 115600000 | 20113000 | H | 2450000 | 1663000 | 16000000 | 6942.87 | 17.4% | 2017-07-01 | 2020-12-01 | 0.0201 | 7.1221 | 2.0364 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
06 | STIP | 39520 | KER | 178 | CONSTRUCT INTERCHANGE | 0.13411 | PARTNERSHIP | [6 empty] | O
06 | STIP | 42371 | TUL | 198 | REPLACEMENT PLANTING | 0.13193 | PARTNERSHIP | 2012 | 0105Y |  |  |  |  | O
06 | STIP | 42470 | KER | 119 | WIDEN FROM 2-LANE CONV TO 4-LANE EXPRESSWAY | 10.3143 | STIP | 2012 | 3645 | [5 empty] | 52751000 | 15965000 | 3687000 | 5330000 | 1962000 | 4986000 | 4162035.36 | 30.26% | 2014-12-01 | 2015-10-01 | 0 | 6.2508 | 4.0635 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
06 | STIP | 43070 | TUL | 216 | WIDEN AND REALIGNMENT OF HOUSTON AVENUE (SR 216) | 4.6846 | STIP | 2012 | 0106 | [5 empty] | 7707000 | 5103000 | 2087000 | 1635000 | 851000 | 530000 | 4343519.35 | 66.21% | 2013-03-01 | 2014-07-16 | 0 | 0.13027 | 1.7863 | 2.7681 | Caltrans | Caltrans | Caltrans | Caltrans
06 | STIP | 43071 | TUL | 216 | INSTALL LANDSCAPING | 0.63538 | STIP | 2012 | 0106Y | [5 empty] | 580000 | 100000 | H | 50000 | H | 50000 | 0 | 17.24% | 2015-01-15 | 2017-07-01 | 0 | 0.63538 | 0 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
06 | STIP | 43080 | TUL | 065 | CONSTRUCT 4-L EXPRESSWAY ALONG AN EXISTING 2-LANE COUNTY ROAD | 1.9339 | STIP | 2012 | 0104 | X |  |  |  |  | 82935000 | 19776000 | 3150000 | 1557000 | 2629000 | 12440000 | 3706235.78 | 23.85% | 2018-05-15 | 2020-07-01 | 1.4071 | 0.47437 | 0.05247 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
06 | STIP | 43350 | KER | 099 | MODIFY INTERCHANGE | 0.07487 | PARTNERSHIP | [6 empty] | O
06 | STIP | 43401 | TUL | 065 | WIDEN 2 LANE CONVENTIONAL HIGHWAY TO 4 LANE EXPRESSWAY | 1.8939 | STIP | 2012 | 8650A | [5 empty] | 22630000 | 7823000 | 684000 | 3339000 | 2000000 | 1800000 | 4976631.3275 | 34.57% | 2016-02-15 | 2017-10-01 | 0 | 0.88383 | 1.0101 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
06 | STIP | 44254 | KER | 046 | 2-LN CONVENTIONAL HIGHWAY TO 4-LN CONVENTIONAL HIGHWAY | 8.093 | STIP | 2012 | 3386C | [5 empty] | 22000000 | 8880000 | H | 4030000 | 1500000 | 3350000 | 0 | 40.36% | 2016-02-20 | 2019-03-03 | 0 | 6.5577 | 1.5352 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
06 | STIP | 45130 | FRE | 043 | 2C TO 4 LN DIVIDED HIGHWAY | 0.09738 | STIP | 2008 | 1490 | [5 empty] | 80000000 | 5000000 | 5000000 | A | A | A | 467799.57 | 6.25% | 2020-12-01 | 2021-07-01 | 0 | 0.09044 | 0.00694 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
06 | STIP | 45140 | FRE | 180 | RTE ADOPTION STUDY FOR A NEW ROADWAY SEGMENT | 0.03286 | STIP | 2008 | T0930 | [5 empty] | P | 7000000 | 7000000 | D | D | D | 6551331.27 | NA | - - | - - | 0.03286 | 0 | 0 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
06 | STIP | 45711 | KER | 014 | CONVERT EXISTING 2-LANE TO 4-LANE EXPRESSWAY | 7.782 | STIP | 2012 | 8042A | [5 empty] | 37488000 | 7400000 | E | 2500000 | 1800000 | 3100000 | 630985.65 | 19.74% | 2015-07-01 | 2017-01-02 | 0 | 5.5048 | 2.2772 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
06 | STIP | 45712 | KER | 014 | CONVERT EXISTING 2-LANE TO 4-LANE EXPRESSWAY | 5.0202 | STIP | 2012 | 8042B | [5 empty] | 38437000 | 5350000 | H | 3250000 | 2100000 | B | 0 | 13.92% | 2017-06-01 | 2018-11-01 | 0 | 4.7014 | 0.31881 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
06 | STIP | 47150 | TUL | 099 | RECONSTRUCT INTERCHANGE | 8.1037 | STIP | 2012 | 6423 | [5 empty] | 56000000 | 11220000 | 2120000 | 3108000 | 492000 | 5500000 | 2212173.09 | 20.04% | 2016-08-01 | 2019-01-02 | 0 | 7.3842 | 0.71953 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
06 | STIP | 48750 | KIN | 198 | RECONSTRUCT INTERCHANGE | 8.1975 | STIP | 2012 | 4348 | [5 empty] | 18818000 | 6275000 | 1890000 | 1825000 | 281000 | 2279000 | 4995859.39 | 33.35% | 2013-05-15 | 2015-07-15 | 0 | 0.06688 | 0.53251 | 7.5981 | Caltrans | Caltrans | Caltrans | Caltrans
06 | STIP | 0A490 | FRE | 041 | CORRIDOR ENHANCEMENT | 0.18669 | STIP | 2008 | 1477 |  |  |  | X |  | 1166000 | 579000 | 47000 | 254000 | C | 278000 | 569674.08 | 49.66% | 2010-05-24 | 2013-12-04 | 0 | 0 | 0 | 0.18669 | Caltrans | Caltrans | Caltrans | Caltrans
06 | STIP | 0E660 | KER | 099 | 99 CORRIDOR-BRIDGE ENHANCEMENT | 1.2035 | STIP | 2012 | 6414 |  |  |  | X |  | 1126000 | 514000 | 130000 | 170000 | 4000 | 210000 | 213801.76 | 45.65% | 2013-08-02 | 2014-02-14 | 0 | 0.03225 | 0.00815 | 1.1631 | Caltrans | Caltrans | Caltrans | Caltrans
06 | STIP | 0E670 | TUL | 099 | 99 CORRIDOR-BRIDGE ENHANCEMENT | 0.74189 | STIP | 2012 | 6348 |  |  |  | X |  | 534000 | 343000 | 120000 | 110000 | 3000 | 110000 | 338677.93 | 64.23% | 2013-08-02 | 2014-02-14 | 0 | 0.03386 | 0.00307 | 0.70496 | Caltrans | Caltrans | Caltrans | Caltrans
06 | STIP | 0E680 | MAD | 099 | 99 CORRIDOR-BRIDGE ENHANCEMENT | 0.88606 | STIP | 2012 | 4328 |  | X | X |  |  | 500000 | 252000 | 60000 | 90000 | 2000 | 100000 | 53039.54 | 50.4% | 2014-07-18 | 2015-02-14 | 0 | 0.87666 | 0.00454 | 0.00486 | Caltrans | Caltrans | Caltrans | Caltrans
06 | STIP | 0G830 | KER | 099 | WIDEN FREEWAY FROM 6 TO 8 LANES | 8.4841 | STIP | 2012 | 6268 | [5 empty] | 22872000 | 6500000 | 1600000 | 1100000 | G | 3800000 | 2278827.07 | 28.42% | 2012-10-24 | 2014-09-01 | 0 | 0 | 0.00076 | 8.4833 | Caltrans | Caltrans | Caltrans | Caltrans
06 | STIP | 0G840 | KER | 099 | WIDEN FREEWAY FROM 6 TO 8 LANES | 7.0967 | STIP | 2012 | 6267 |  |  |  | X |  | 9600000 | 2900000 | 515000 | 685000 | G | 1700000 | 1156558.54 | 30.21% | 2013-03-01 | 2014-03-01 | 0 | 0 | 0.05354 | 7.0432 | Caltrans | Caltrans | Caltrans | Caltrans
06 | STIP | 0J320 | MAD | 099 | WIDEN STRUCTURE | 0.67808 | PARTNERSHIP
06 | STIP | 0M020 | FRE | 168 | ENHANCE VISTA POINT | 1.5859 | STIP | 2012 | 6465 |  | X | X |  |  | 1553000 | 954000 | 166000 | 521000 | 16000 | 251000 | 278416.73 | 61.43% | 2014-04-01 | 2015-09-01 | 0 | 1.1907 | 0.00626 | 0.38898 | Caltrans | Caltrans | Caltrans | Caltrans
06 | STIP | 0N680 | KER | 043 | LANDSCAPE IMPROVEMENTS (TE) | 0.05429 | PARTNERSHIP | 2012 | 6559 |  |  |  |  | O
06 | STIP | 0P800 | KER | 043 | WASCO'S HIGHWAY 43 CORRIDOR BEAUTIFICATION - PHASE 2 | 0.30034 | PARTNERSHIP | 2012 | 6618 |  |  |  |  | O
07 | STIP | 00234 | LA | 710 | CONSTRUCT SOUND WALL | 0.73496 | RETROFIT SOUNDWALL
07 | STIP | 12200 | LA | 005 | WIDEN FREEWAY AND STRUCTURES | 0.13352 | STIP | 2006 | 0162P | [5 empty] | 46720000 | 11595000 | 205000 | 7440000 | 200000 | 3750000 | 14601989.6 | 24.82% | 2005-04-12 | 2008-05-20 | 0 | 0 | 0.00257 | 0.13095 | Caltrans | Caltrans | Caltrans | Caltrans
07 | STIP | 12721 | LA | 138 | WIDEN CONVENTIONAL HIGHWAY (SEG 2) | 0.30804 | STIP | 2010 | 3325 | [5 empty] | 9415000 | 829000 | 16000 | 179000 | 139000 | 495000 | 4849733.976 | 8.805% | 2008-06-09 | 2009-08-18 | 0 | 0.04148 | 0.16508 | 0.10148 | Caltrans | Caltrans | Caltrans | Caltrans
07 | STIP | 12722 | LA | 138 | WIDEN HIGHWAY WITH HMA OVER AB | 1.0923 | STIP | 2010 | 3326 |  |  |  | X |  | 8548000 | 9461000 | 462000 | 4200000 | 2399000 | 2400000 | 7073134.126 | 110.7% | 2011-10-26 | 2013-08-14 | 0 | 0.05366 | 0.61049 | 0.42819 | Caltrans | Caltrans | Caltrans | Caltrans
07 | STIP | 12723 | LA | 138 | WIDEN CONVENTIONAL HIGHWAY (SEG 7) | 0.32923 | STIP | 2010 | 3327 | [5 empty] | 10845000 | 1311000 | 24000 | 299000 | 232000 | 756000 | 3833958.896 | 12.09% | 2008-03-03 | 2009-08-18 | 0 | 0.07336 | 0.17613 | 0.07974 | Caltrans | Caltrans | Caltrans | Caltrans
07 | STIP | 12726 | LA | 138 | WIDEN HIGHWAY AND CONSTRUCT BRIDGE | 0.24764 | SHOPP | 2004 | 3082 | [5 empty] | 17944000 | 7059000 | 5729000 | 350000 | 200000 | 780000 | 10068309.742 | 39.34% | 2005-10-20 | 2008-05-09 | 0 | 0 | 0.24764 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
07 | STIP | 12727 | LA | 138 | WIDEN CONVENTIONAL HIGHWAY (SEG 12) | 1.9347 | STIP | 2010 | 0694Q | [5 empty] | 24238000 | 12205000 | 1003000 | 3659000 | 3191000 | 4352000 | 8149814.212 | 50.35% | 2011-12-15 | 2014-07-25 | 0 | 0 | 1.0227 | 0.912 | Caltrans | Caltrans | Caltrans | Caltrans
07 | STIP | 14551 | LA | 001 | CONSTRUCT R/R GRADE SEP & UNDRCSSG *FOR OVERSIGHT ONLY | 1 | PARTNERSHIP | [6 empty] | O
07 | STIP | 16800 | LA | 005 | CONSTRUCT HOV LANES AND CONNECTORS | 5.0066 | STIP | 2006 | 0168M |  |  |  | X |  | 145228000 | 30572000 | 722000 | 9394000 | 250000 | 20206000 | 36590886.12 | 21.05% | 2008-03-27 | 2013-07-29 | 0 | 0 | 0.60402 | 4.4025 | Caltrans | Caltrans | Caltrans | Caltrans
07 | STIP | 17215 | LA | 030 | FREEWAY CONSTRUCTION | 0.38897 | STIP | 1998 | 2022C | [5 empty] | 108593000 | 12785000 | H | 2463000 | 2969000 | 7353000 | 13775951.442 | 11.77% | 2001-01-26 | 2003-03-19 | 0 | 0 | 0.35179 | 0.03718 | Caltrans | Caltrans | Caltrans | Caltrans
07 | STIP | 17850 | LA | 105 | WIDEN OFF RAMP | 1.1393 | STIP | 2006 | 2119 | [5 empty] | 18639000 | 7593000 | 467000 | 2788000 | 732000 | 3606000 | 7468343.94 | 40.74% | 2008-06-24 | 2010-05-28 | 0 | 0 | 1.0065 | 0.13281 | Caltrans | Caltrans | Caltrans | Caltrans
07 | STIP | 18720 | LA | 126 | WIDEN HIGHWAY | 0.1872 | STIP | 2006 | 2209 | [5 empty] | 19145000 | 5352000 | 273000 | 1594000 | 190000 | 3295000 | 8300765.22 | 27.96% | 2003-02-18 | 2005-11-28 | 0 | 0 | 0.08555 | 0.10165 | Caltrans | Caltrans | Caltrans | Caltrans
07 | STIP | 18790 | LA | 710 | CONSTRUCT FREEWAY | 10.3586 | PARTNERSHIP
07 | STIP | 18850 | LA | 134 | MODIFY INTERCHANGE AND ON RAMP | 1.3914 | STIP | 2006 | 2223 | [5 empty] | 40023000 | 7008000 | 1054000 | 3712000 | 922000 | 1320000 | 13963450.29 | 17.51% | 2007-03-12 | 2012-05-25 | 0 | 0.06481 | 1.057 | 0.26954 | Caltrans | Caltrans | Caltrans | Caltrans
07 | STIP | 19963 | LA | 101 | WIDEN OFF RAMPS | 1.3299 | STIP | 2010 | 2789 |  |  |  | X |  | 6549000 | 3683000 | 497000 | 1674000 | 12000 | 1500000 | 3840744.06 | 56.24% | 2011-01-13 | 2013-08-22 | 0 | 0 | 0.01487 | 1.3151 | Caltrans | Caltrans | Caltrans | Caltrans
07 | STIP | 20120 | LA | 405 | REALIGN AND WIDEN EXISTING HIGHWAY *RELINQUISHED # 1237A TO LA 1/27/10 | 0.01732 | STIP | 2006 | 2336 | [5 empty] | 43149000 | 7925000 | 378000 | 3547000 | C | 4000000 | 14961449.93 | 18.37% | 2005-03-18 | 2008-10-09 | 0 | 0 | 0.01732 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
07 | STIP | 21060 | LA | 071 | RECONSTRUCTION-ADD LANES | 3.2078 | STIP | 2012 | 2741 | [5 empty] | 324353000 | 13925000 | 4582000 | 9343000 | C | B | 5054300.45 | 4.293% | 2018-05-30 | 2021-01-12 | 0 | 2.6836 | 0.52418 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
07 | STIP | 21070 | VEN | 101 | OFF-RAMP MODIFICATION | 0.10451 | PARTNERSHIP |  |  |  | X | X
07 | STIP | 21593 | LA | 005 | ROADWAY WIDENING (SEG 3) | 27.4784 | STIP | 2012 | 4154 | [5 empty] | 139034000 | 40969000 | 3646000 | 15716000 | 4926000 | 16681000 | 21838794.9185 | 29.47% | 2012-08-14 | 2017-10-04 | 0 | 0 | 4.0255 | 23.4529 | Caltrans | Caltrans | Caltrans | Caltrans
07 | STIP | 21594 | LA | 005 | ROADWAY WIDENING (SEG 4) | 26.2162 | STIP | 2012 | 4155 | [5 empty] | 322781000 | 47489000 | 4797000 | 17493000 | 8187000 | 17012000 | 26465820.2832 | 14.71% | 2012-08-23 | 2017-10-16 | 0 | 0 | 3.544 | 22.6722 | Caltrans | Caltrans | Caltrans | Caltrans
07 | STIP | 24640 | LA | 005 | HIGHWAY PLANTING AND IRRIGATION | 0.71689 | STIP | 2008 | 3547 | [5 empty] | 1435000 | 906000 | 44000 | 436000 | C | 426000 | 644867.62 | 63.14% | 2010-01-14 | 2015-12-31 | 0 | 0 | 0 | 0.71689 | Caltrans | Caltrans | Caltrans | Caltrans
07 | STIP | 24650 | LA | 010 | GORE & SLOPE PAVING AND NATIVE TREE | 0.07046 | STIP | 2008 | 3548 |  |  |  | X |  | 1250000 | 564000 | 84000 | 230000 | C | 250000 | 574705.45 | 45.12% | 2009-06-29 | 2014-05-30 | 0 | 0 | 0 | 0.07046 | Caltrans | Caltrans | Caltrans | Caltrans
07 | STIP | 24990 | LA | 710 | I-710 SOUTH EXPANSION | 10.5036 | PARTNERSHIP
07 | STIP | 28380 | LA | 101 | VINE PLANTING TRANS ENHANCEMENT *ITIP TE FUND | 0.94817 | STIP | 2012 | 4328 | [5 empty] | 1738000 | 608000 | 87000 | 226000 | C | 295000 | 3224.37 | 34.98% | 2015-06-25 | 2020-05-13 | 0 | 0.94817 | 0 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
07 | STIP | 28390 | LA | 210 | TRANSPORTATION ENHANCEMENT | 0.2029 | STIP | 2012 | 4329 | X |  | X |  |  | 428000 | 151000 | 22000 | 56000 | C | 73000 | 3086.78 | 35.28% | 2014-11-24 | 2018-07-24 | 0 | 0.19721 | 0.00569 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
07 | STIP | 28420 | LA | 005 | TRANSPORTATION ENHANCEMENT | 0.90611 | STIP | 2012 | 4331 |  | X | X |  |  | 1054000 | 370000 | 53000 | 138000 | C | 179000 | 61581.3 | 35.1% | 2013-11-22 | 2017-07-18 | 0 | 0.62435 | 0 | 0.28176 | Caltrans | Caltrans | Caltrans | Local
07 | STIP | 28430 | LA | 002 | TRANSPORTATION ENHANCEMENT | 0.31368 | STIP | 2012 | 4332 | X |  | X |  |  | 1105000 | 387000 | 55000 | 144000 | C | 188000 | 7484.16 | 35.02% | 2014-11-24 | 2018-07-24 | 0 | 0.31368 | 0 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
07 | STIP | 28450 | LA | 014 | TRANSPORTATION ENHANCEMENT | 1.6502 | STIP | 2012 | 4325 |  | X | X |  |  | 2544000 | 891000 | 127000 | 331000 | C | 433000 | 75598.27 | 35.02% | 2014-01-29 | 2018-02-19 | 0 | 1.2483 | 0 | 0.4019 | Caltrans | Caltrans | Caltrans | Caltrans
07 | STIP | 28480 | LA | 710 | CORRIDOR MASTER PLAN | 0.59997 | STIP | 2012 | 4336 | X |  |  |  |  | P | 480000 | 480000 | P | P | P | 0 | NA | 2016-12-22 | 2019-08-05 | 0.59521 | 0.00476 | 0 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
07 | STIP | 28620 | LA | 138 | WIDEN CONVENTIONAL HIGHWAY (SEG 6) | 7.2435 | STIP | 2012 | 4356 | [5 empty] | 23800000 | 8100000 | E | 3500000 | 1600000 | 3000000 | 0 | 34.03% | 2016-08-03 | 2017-11-09 | 0 | 5.5435 | 1.7 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
07 | STIP | 28630 | LA | 138 | WIDEN CONVENTIONAL HIGHWAY (SEG 13) | 26.2002 | STIP | 2012 | 4357 | [5 empty] | 43000000 | 19000000 | E | 6000000 | 6500000 | 6500000 | 0 | 44.19% | 2016-04-11 | 2018-11-08 | 0 | 14.0002 | 12.2 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
07 | STIP | 29350 | LA | 138 | WIDEN (SEG 9)FR 2 TO 4 LN W MEDIAN | 18.5661 | STIP | 2012 | 4560 | [5 empty] | 13200000 | 7000000 | E | 2100000 | 3000000 | 1900000 | 0 | 53.03% | 2015-04-29 | 2016-11-22 | 0 | 8.3461 | 10.22 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
07 | STIP | 29450 | LA | 005 | NATIVE PLANTING AND ENHANCEMENTS | 0.62 | STIP | 2012 | 4549 | X |  |  |  |  | 1742000 | 609000 | 87000 | 221000 | 5000 | 296000 | 0 | 34.96% | 2017-06-22 | 2021-07-28 | 0.05 | 0.57 | 0 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
07 | STIP | 1170U | LA | 010 | CONSTRUCT HOV LANES & SOUNDWALLS | 15.4688 | STIP | 2012 | 0309S | [5 empty] | 160354000 | 35226000 | 846000 | 18469000 | 2338000 | 13573000 | 20288269.02 | 21.97% | 2013-10-31 | 2018-09-13 | 0 | 1.239 | 1.2676 | 12.9623 | Caltrans | Caltrans | Caltrans | Caltrans
07 | STIP | 1178U | LA | 405 | CONSTRUCT HOV LANES | 0.01855 | STIP | 2010 | 0837A | [5 empty] | 168771000 | 21830000 | 400000 | 9460000 | 2788000 | 9182000 | 61073179.43 | 12.93% | 2004-10-06 | 2010-06-10 | 0 | 0 | 0.01855 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
07 | STIP | 1294V | LA | 060 | CONSTRUCT HOV LANE AND SOUNDWALLS | 0.10723 | STIP | 2006 | 0482R | [5 empty] | 126793000 | 29192000 | H | 15792000 | 1000000 | 12400000 | 35664397.5744 | 23.02% | 2007-04-18 | 2011-05-02 | 0 | 0 | 0.00518 | 0.10205 | Caltrans | Caltrans | Caltrans | Caltrans
07 | STIP | 1660U | LA | 001 | WIDEN AND REALIGN ROADWAY | 0.21848 | STIP | 2010 | 0027J | [5 empty] | 12241000 | 8972000 | 87000 | 1937000 | 131000 | 6817000 | 8092546.4 | 73.29% | 2005-07-12 | 2010-08-31 | 0 | 0 | 0 | 0.21848 | Caltrans | Caltrans | Caltrans | Caltrans
07 | STIP | 1661C | LA | 001 | WIDEN,REPLACE OC & CONTR NEW BRIDGE | 0.85277 | STIP | 2010 | 0027Q | [5 empty] | 23168000 | 3387051.6854 | 707000 | 2507051.6854 | 173000 | B | 1949265.1196 | 14.62% | 2017-05-10 | 2019-11-18 | 0.85277 | 0 | 0 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
07 | STIP | 1786A | LA | 005 | MODIFY INTERCHANGE | 1.1162 | STIP | 2008 | 2120 |  |  |  | X |  | 25585000 | 9322000 | 359000 | 4847000 | 1145000 | 2971000 | 8510174.18 | 36.44% | 2010-10-11 | 2013-07-19 | 0 | 0.02498 | 0.58711 | 0.5041 | Caltrans | Caltrans | Caltrans | Caltrans
07 | STIP | 2159C | LA | 005 | WIDEN AND REALIGH FREEWAY WITH PCC | 31.1997 | STIP | 2010 | 2808A | [5 empty] | 340260000 | 54907000 | 3100000 | 28407000 | 7200000 | 16200000 | 45117026.97 | 16.14% | 2011-08-19 | 2016-09-06 | 0 | 0.73256 | 4.7089 | 25.7582 | Caltrans | Caltrans | Caltrans | Caltrans
07 | STIP | 2159E | LA | 005 | RECONSTRUCT I/C (RTE 5/710) | 12.6202 | STIP | 2012 | 2808D | [5 empty] | 1100000000 | 2400000 | 2400000 | A | A | A | 1824351.68 | 0.2182% | 2020-03-12 | 2022-12-07 | 12.6202 | 0 | 0 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
07 | STIP | 2159F | LA | 005 | FREEWAY WIDENING (PHASE II) | 12.7917 | STIP | 2012 | 2808C | [5 empty] | 1100000000 | 2592000 | 2592000 | A | A | A | 2266613.31 | 0.2356% | 2020-08-03 | 2023-12-22 | 12.7917 | 0 | 0 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
07 | STIP | 2844U | LA | 110 | CONSTRUCT BICYCLE/PEDESTRIAN TRAIL | 1.5022 | STIP | 2012 | 4324 | X |  | X |  |  | 1852000 | 839000 | 52000 | 349000 | 5000 | 433000 | 0 | 45.3% | 2014-12-03 | 2016-03-24 | 0.03326 | 1.4689 | 0 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
07 | STIP | 4S300 | LA | 101 | PEDESTRIAN LINKAGE (PHASE 2) | 0.56052 | PARTNERSHIP
08 | STIP | 00711 | SBD | 215 | WIDEN BRIDGES AND HIGHWAY | 0.04337 | STIP | 1998 | 0247C | [5 empty] | 9117000 | D | N | N | N | N | 2110473.01 | NA | 1998-11-13 | 2001-03-22 | 0 | 0 | 0 | 0.04337 | Caltrans | Caltrans | Caltrans | Caltrans
08 | STIP | 00717 | SBD | 215 | WIDEN FREEWAY AND CONSTRUCT NEW OVERPASSES | 0.52701 | STIP | 2006 | 0247L | [5 empty] | 159163000 | 27602000 | H | 8323000 | 4676000 | 14603000 | 41953030.3544 | 17.34% | 2007-11-21 | 2011-07-29 | 0 | 0 | 0.43411 | 0.0929 | Caltrans | Caltrans | Caltrans | Caltrans
08 | STIP | 04351 | SBD | 058 | REALIGN & WIDEN 2 TO 4 LANE EXPWY | 42.2358 | STIP | 2012 | 0217F |  | X | X |  |  | 160648000 | 34277000 | 9640000 | 7556000 | 3101000 | 13980000 | 9386648.4153 | 21.34% | 2014-11-20 | 2016-08-19 | 0 | 23.8153 | 18.4204 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
08 | STIP | 20320 | RIV | 091 | MODIFY IC; NEW OC; AUX LANES | 0.41789 | PARTNERSHIP | [6 empty] | O
08 | STIP | 20432 | SBD | 210 | MITIGATION PLANTING | 0.014322 | STIP | 2006 | 0194T | [5 empty] | 935000 | 867000 | 289000 | 150000 | 60000 | 368000 | 1203175.29 | 92.73% | 2007-09-21 | 2012-04-06 | 0 | 0 | 0.010002 | 0.00432 | Caltrans | Caltrans | Caltrans | Caltrans
08 | STIP | 33483 | RIV | 091 | WIDEN BRIDGES | 0.080148 | STIP | 2006 | 0121D | [5 empty] | 16890000 | 7310689 | H | 939367 | 971239 | 5400083 | 7929121.6403 | 43.28% | 2002-10-11 | 2004-12-31 | 0 | 0 | 0.073848 | 0.0063 | Caltrans | Caltrans | Caltrans | Caltrans
08 | STIP | 33484 | RIV | 215 | WIDEN EXISTING FREEWAY | 1.1035 | STIP | 2006 | 0121D | [5 empty] | 367821383.2197 | 154040399.3491 | H | 43375262.7931 | 23537220.9295 | 87127915.6265 | 148456689.5436 | 41.88% | 2004-02-06 | 2008-12-31 | 0 | 0 | 1.1035 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
08 | STIP | 33486 | RIV | 215 | REPLACE HIGHWAY PLANTING | 0.1722 | STIP | 2004 | 0126E | [5 empty] | 4240000 | 1793000 | 157000 | 810000 | 6000 | 820000 | 1591112.98 | 42.29% | 2011-04-01 | 2015-04-30 | 0 | 0 | 0.0010223 | 0.17118 | Caltrans | Caltrans | Caltrans | Caltrans
08 | STIP | 33487 | RIV | 215 | FACILITATE MANAGING LANDSCAPE DESIGN. PLANT ESTABLISHMENT FOR THE | 0.51907 | STIP | 2004 | 0122C | [5 empty] | 2002000 | 1350000 | 215000 | 660000 | 5000 | 470000 | 953939.24 | 67.43% | 2012-03-21 | 2016-09-23 | 0 | 0 | 0 | 0.51907 | Caltrans | Caltrans | Caltrans | Caltrans
08 | STIP | 33488 | RIV | 215 | FACILITATE MANAGING LANDSCAPE DESIGN. PLANT ESTABLISHMENT FOR | 0.58836 | STIP | 2004 | 0121J | [5 empty] | 1500000 | 978000 | 103000 | 445000 | 5000 | 425000 | 539621.4 | 65.2% | 2012-06-28 | 2016-06-29 | 0 | 0 | 0.00058945 | 0.58777 | Caltrans | Caltrans | Caltrans | Caltrans
08 | STIP | 34040 | SBD | 395 | REALIGN &/OR WDN TO 4/6 LN FWY OR EXPWY & CONST/MODIFY NEW IC | 10.8125 | STIP | 2012 | 0260B | [5 empty] | A | 14000000 | 14000000 | A | A | A | 2155074.14 | NA | - - | - - | 10.8125 | 0 | 0 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
08 | STIP | 34160 | SBD | 015 | CONSTRUCT NEW INTERCHANGE | 2.6234 | PARTNERSHIP | 2012 | 0172I |  |  |  |  | O
08 | STIP | 34770 | SBD | 058 | CONSTRUCT 4-LANE EXPWY ON NEW ALIGN | 11.9608 | STIP | 2012 | 0215C | X |  |  |  |  | 162085000 | 37424000 | 8800000 | 8200000 | 4756000 | 15668000 | 6374184.26 | 23.09% | 2017-04-17 | 2020-05-01 | 7.7019 | 4.2589 | 0 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
08 | STIP | 35556 | SBD | 015 | ADD N/B MIXED FLOW LANE W/AUX LANE. RECON "D" & "E" ST ICS & STODDARD | 8.7308 | STIP | 2012 | 0174L |  | X | X |  |  | 78826000 | 29293000 | 5420000 | 10727000 | 4448000 | 8698000 | 14885551.6991 | 37.16% | 2014-10-23 | 2017-03-24 | 0 | 5.6421 | 3.0886 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
08 | STIP | 35558 | SBD | 015 | BEAUTIFICATION LAND MODERNIZATION | 0.80972 | STIP | 2012 | 0175N |  | X | X |  |  | 1446000 | 1000000 | H | 600000 | C | 400000 | 140971.55 | 69.16% | 2014-08-07 | 2017-01-06 | 0 | 0.80933 | 0.00038683 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
08 | STIP | 37020 | SBD | 015 | RECONSTRUCT EXISTING FREEWAY | 0.23259 | STIP | 2002 | 0172K | [5 empty] | 13112000 | 5812382 | 37938 | 543418 | 1526546 | 3704480 | 5801928.65 | 44.33% | 2003-08-25 | 2005-12-23 | 0 | 0 | 0.1801 | 0.05249 | Local | Local | Caltrans | Caltrans
08 | STIP | 43272 | RIV | 015 | CONSTRUCT NEW IC | 4.1395 | STIP | 2012 | 0021K | [5 empty] | 137903000 | 34702000 | 2237000 | 15165000 | G | 17300000 | 2500386.757 | 25.16% | 2015-06-18 | 2018-01-15 | 0 | 3.7553 | 0.38429 | 0 | Local | Local | Local | Caltrans
08 | STIP | 43321 | SBD | 010 | ADD HARD-SCAPE, ENTRY MONUMENTS, FREEWAY MONUMENTS AND ADDITIONAL | 0.34998 | PARTNERSHIP
08 | STIP | 44372 | SBD | 210 | CONSTRUCT NEW FRONTAGE ROAD | 0.40499 | STIP | 2000 | 0194J | [5 empty] | 2181000 | 2010007 | H | 316565 | 1315416 | 378026 | 2832022.9412 | 92.16% | 2002-08-26 | 2003-01-07 | 0 | 0 | 0.30287 | 0.10212 | Caltrans | Caltrans | Caltrans | Caltrans
08 | STIP | 44381 | SBD | 210 | CONST NEW FWY: 6 MF LANES & 2 HOV LANES; CACTUS AVE OC; LILAC PED OC | 1.103 | STIP | 2002 | 0195D | [5 empty] | 15018000 | 5711429 | H | 2577607 | 1191163 | 1942659 | 6124489.0466 | 38.03% | 2004-11-19 | 2008-07-01 | 0 | 0 | 0.80042 | 0.30254 | Caltrans | Caltrans | Caltrans | Local
08 | STIP | 44382 | SBD | 210 | CONSTRUCT NEW FRONTAGE ROADS | 0.20414 | STIP | 2000 | 0195E | [5 empty] | 3407000 | 2277724 | H | 215937 | 1316945 | 744842 | 2657018.8593 | 66.85% | 2002-08-21 | 2003-03-04 | 0 | 0 | 0.20414 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
08 | STIP | 44383 | SBD | 210 | CONST AYALA AVE OC | 0.026606 | STIP | 2002 | 0195F | [5 empty] | 2117000 | 1070815 | H | 696992 | 181943 | 191880 | 1453100.4059 | 50.58% | 2003-05-23 | 2005-02-08 | 0 | 0 | 0.018706 | 0.0079 | Caltrans | Caltrans | Caltrans | Caltrans
08 | STIP | 44384 | SBD | 210 | CONSTRUCT CACTUS CHANNEL | 0.12822 | STIP | 2002 | 0195H | [5 empty] | 8920000 | 1085819 | H | 855997 | 205486 | 24336 | 1475812.9791 | 12.17% | 2003-05-26 | 2005-02-08 | 0 | 0 | 0.11089 | 0.01733 | Caltrans | Caltrans | Caltrans | Local
08 | STIP | 44385 | SBD | 210 | CONSTRUCT SOUNDWALLS | 0.062676 | STIP | 2002 | 0195G | [5 empty] | 1316000 | 567137 | H | 210451 | 341351 | 15335 | 946331.0565 | 43.1% | 2003-05-23 | 2005-02-08 | 0 | 0 | 0.048206 | 0.01447 | Caltrans | Caltrans | Caltrans | Local
08 | STIP | 44391 | SBD | 210 | CONST NEW FWY - 6 MF LANES & 2 HOV LANES | 0.61317 | STIP | 2002 | 0196B | [5 empty] | 31000000 | 3656681 | H | 938841 | 2717840 | G | 3920754.2068 | 11.8% | 2005-01-11 | 2008-07-01 | 0 | 0 | 0.47613 | 0.13704 | Caltrans | Local | Caltrans | Local
08 | STIP | 44392 | SBD | 210 | CONST LOCAL STREET IMPROVEMENTS, EARLY BRIDGES & OTHER MISC IMPROV- | 0.037896 | STIP | 2002 | 0196E | [5 empty] | 6600000 | 1810255 | H | 245003 | 1216566 | 348686 | 2064342.0263 | 27.43% | 2003-07-01 | 2005-03-21 | 0 | 0 | 0.014976 | 0.02292 | Caltrans | Local | Caltrans | Local
08 | STIP | 44395 | SBD | 210 | CONSTRUCT SOUNDWALLS-PORTIONS OF SEGMENT 10 | 0.0074838 | STIP | 2002 | 0196G | [5 empty] | 600000 | 359865 | H | 30497 | 299303 | 30065 | 611781.6497 | 59.98% | 2003-07-01 | 2005-03-21 | 0 | 0 | 0.0052038 | 0.00228 | Caltrans | Local | Caltrans | Local
08 | STIP | 44402 | SBD | 210 | LOCAL STREET IMPROVEMENTS, EARLY BRIDGES, DRAINAGE IMPROVEMENTS AND | 0.074462 | STIP | 2002 | 0194L | [5 empty] | 9725000 | 3587501 | H | 337775 | 2627367 | 622359 | 3791394.5718 | 36.89% | 2004-12-28 | 2008-07-01 | 0 | 0 | 0.034759 | 0.039702 | Caltrans | Local | Caltrans | Local
08 | STIP | 44812 | SBD | 010 | MODIFY/CONSTRUCT WB RAMPS, WIDEN TIPPPECANOE AVE & TEA 21 DEMO | 5.8937 | STIP | 2012 | 0154D |  |  | X |  |  | 49146000 | 2500000 | H | H | 2500000 | G | 3207476.27 | 5.087% | 2013-11-01 | 2015-07-01 | 0 | 0.31583 | 3.5885 | 1.9894 | Local | Local | Caltrans | Local
08 | STIP | 44931 | RIV | 215 | CONSTRUCT HOV IN EACH DIRECTION | 10.3987 | STIP | 2008 | 0116F |  |  |  | X |  | 36843000 | 11300000 | H | 4400000 | G | 6900000 | 4870089.46 | 30.67% | 2011-04-11 | 2014-03-03 | 0 | 0 | 0.093557 | 10.3051 | Local | Local | Local | Caltrans
08 | STIP | 45570 | RIV | 010 | MODIFY OR RECONSTRUCT IC | 1.7532 | PARTNERSHIP | [6 empty] | O
08 | STIP | 45580 | RIV | 010 | MODIFY IC | 1.1901 | PARTNERSHIP | [6 empty] | O
08 | STIP | 45590 | RIV | 010 | MODIFY IC | 0.78767 | PARTNERSHIP | [6 empty] | O
08 | STIP | 45600 | RIV | 010 | CONSTRUCT INTERCHANGE | 0.36719 | STIP | 2010 | 0007D | [5 empty] | 36272000 | 14379000 | 1694000 | 6140000 | 1116000 | 5429000 | 14221528.31 | 39.64% | 2009-11-16 | 2012-02-09 | 0 | 0 | 0.36719 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
08 | STIP | 45662 | RIV | 091 | PLANTS AND MULCH WITH IRRIGATION | 0.14211 | STIP | 2010 | 0072G | [5 empty] | 1072000 | 760000 | 31000 | 285000 | 4000 | 440000 | 528385.16 | 70.9% | 2011-07-20 | 2015-05-26 | 0 | 0 | 0 | 0.14211 | Caltrans | Caltrans | Caltrans | Caltrans
08 | STIP | 47520 | RIV | 010 | MODIFY/WIDEN IC FROM 2 TO 6 LANES | 5.2989 | PARTNERSHIP | [6 empty] | O
08 | STIP | 0071C | SBD | 215 | BRIDGE REPLACEMENT | 0.0077912 | PARTNERSHIP
08 | STIP | 0A450 | SBD | 015 | CONSTRUCT INTERCHANGE | 0.52817 | PARTNERSHIP | [6 empty] | O
08 | STIP | 0A490 | RIV | 015 | IC & RAMP RECONFIGURATION | 0.35483 | PARTNERSHIP | [6 empty] | O
08 | STIP | 0A791 | SBD | 018 | PLANTING AND IRRIGATION | 0.14494 | STIP | 2008 | 0180F |  |  |  | X |  | 1240000 | 1020000 | 95000 | 559000 | C | 366000 | 1249537.76 | 82.26% | 2009-10-22 | 2013-12-02 | 0 | 0 | 0.0012894 | 0.14365 | Caltrans | Caltrans | Caltrans | Caltrans
08 | STIP | 0C250 | SBD | 010 | ADD HOV LANE IN EACH DIRECTION, RECONSTRUCT RAMPS & WIDEN UCS | 9.2735 | PARTNERSHIP | [6 empty] | O
08 | STIP | 0F100 | SBD | 071 | HIGHWAY PLANTING AND IRRIGATION | 0.1822 | STIP | 2008 | 0234P | [5 empty] | 992000 | 982000 | 117000 | 329000 | C | 536000 | 641705.56 | 98.99% | 2011-01-26 | 2015-08-25 | 0 | 0 | 0 | 0.1822 | Caltrans | Caltrans | Caltrans | Caltrans
08 | STIP | 0F162 | RIV | 215 | ADD ONE MIXED FLOW LANE IN EACH DIRECTION | 2.9849 | PARTNERSHIP | [6 empty] | O
08 | STIP | 0G841 | SBD | 015 | INTERPRETIVE DISPLAYS ON NB & SB | 0.091043 | STIP | 2012 | 0177F | X | X | X |  |  | 151000 | 109000 | 21000 | 37000 | 3000 | 48000 | 701.93 | 72.19% | 2014-07-03 | 2014-10-14 | 0.0096155 | 0.079549 | 0.0018789 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
08 | STIP | 0J070 | SBD | 215 | RECONSTRUCT INTERCHANGE | 18.4466 | PARTNERSHIP | [6 empty] | O
08 | STIP | 0L350 | SBD | 062 | RURAL ROADSIDE ARCHEOLOGICAL INVENTORY | 0.10136 | STIP | 2008 | 0227J | [5 empty] | 1269000 | 136000 | L | L | L | 136000 | 12358.28 | 10.72% | 2010-05-13 | 2013-06-28 | 0 | 0 | 0 | 0.10136 | Caltrans | Caltrans | Caltrans | Caltrans
08 | STIP | 0M94U | RIV | 215 | HOV LANE IN EACH DIRECTION | 29.0626 | SHOPP | 2010 | 0252T | [5 empty] | 154409000 | 17431000 | N | N | N | 17431000 | 16299171.02 | 11.29% | 2012-12-03 | 2016-07-20 | 0 | 0 | 0 | 29.0626 | Local | Caltrans | Local | Caltrans
08 | STIP | 0N450 | RIV | 215 | CORRIDOR MASTERPLAN | 0.50826 | STIP | 2012 | 0247R | [5 empty] | A | 279000 | 279000 | A | A | A | 2929.49 | NA | - - | - - | 0.50826 | 0 | 0 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
08 | STIP | 0N720 | SBD | 210 | NATIVE TREE PLANTING & APPLY ORGANIC MULCH (CCC DIRECTED) | 0.21125 | STIP | 2008 | 0192M | [5 empty] | 600000 | 100000 | J | J | J | 100000 | 20710.83 | 16.67% | 2011-01-12 | 2014-12-30 | 0 | 0 | 0 | 0.21125 | Caltrans | Caltrans | Caltrans | Caltrans
08 | STIP | 3348V | RIV | 215 | REPLACEMENT HIGHWAY PLANTING | 1.6093 | STIP | 2006 | 0121V |  | X | X |  |  | 1500000 | 1520000 | 180000 | 640000 | 10000 | 690000 | 0 | 101.3% | 2014-05-15 | 2017-11-15 | 0 | 1.5589 | 0.0072945 | 0.04308 | Caltrans | Caltrans | Caltrans | Caltrans
08 | STIP | 3401U | SBD | 138 | WIDEN TO 4 LNS FR BEEKLEY RD TO JCT 15, ADD 1 LN EB FR PHELAN RD TO | 11.0958 | STIP | 2012 | 0239D |  | X | X |  |  | 60413000 | 25084000 | 7538000 | 6341000 | 2960000 | 8245000 | 13428953.97 | 41.52% | 2014-07-10 | 2016-06-16 | 0 | 5.2012 | 5.8945 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
08 | STIP | 3555U | SBD | 015 | ADD MIXED FLOW LANE WITH AUXILIARY LANES AND REHABILIATION | 0.66775 | STIP | 2000 | 0174H | [5 empty] | 120147000 | 16255000 | 1155000 | 8231000 | 1567000 | 5302000 | 33595988.1909 | 13.53% | 2002-04-05 | 2005-07-01 | 0 | 0 | 0.61175 | 0.056 | Caltrans | Caltrans | Caltrans | Caltrans
09 | STIP | 21340 | INY | 395 | CONSTRUCT 4 LANE EXPRESSWAY | 14.2049 | STIP | 2012 | 0170 | X |  |  |  |  | 132107000 | 15032000 | 6872000 | 5128000 | 3032000 | B | 6990352.36 | 11.38% | 2017-03-01 | 2019-03-01 | 4.4512 | 6.0655 | 3.0541 | 0.63419 | Caltrans | Caltrans | Caltrans | Caltrans
09 | STIP | 35060 | INY | 168 | CONSTRUCT SIDEWALKS | 1.6597 | STIP | 2012 | 2585 | X |  |  |  |  | 754000 | 622000 | 143000 | 260000 | 48000 | 171000 | 82802.59 | 82.49% | 2015-06-23 | 2015-12-01 | 0.10014 | 1.0216 | 0.52887 | 0.00906 | Caltrans | Caltrans | Caltrans | Caltrans
10 | STIP | 34540 | STA | 120 | CONSTRUCT 2-LANE EXPRESSWAY WITH R/W PURCHASE FOR 4-LANE ULTIMATE. | 1.15 | STIP PA
10 | STIP | 36312 | MER | 099 | HIGHWAY PLANTING AND IRRIGATION | 0.06167 | STIP | 2008 | 0528Y | [5 empty] | 2886000 | 1350000 | H | 500000 | C | 850000 | 836569.81 | 46.78% | 2010-01-26 | 2015-03-12 | 0 | 0 | 0.00965 | 0.05202 | Caltrans | Caltrans | Caltrans | Caltrans
10 | STIP | 40350 | STA | 132 | CONSTRUCT 4 LANE EXPRESSWAY ON NEW ALIGNMENT AND SOUNDWALL | 11.3286 | PARTNERSHIP
10 | STIP | 41482 | MER | 099 | HIGHWAY PLANTING AND IRRIGATION | 0.71561 | STIP | 2010 | 5479Y | [5 empty] | 880000 | 350000 | 30000 | 120000 | C | 200000 | 465157.22 | 39.77% | 2011-11-09 | 2016-06-07 | 0 | 0 | 0 | 0.71561 | Caltrans | Caltrans | Caltrans | Caltrans
10 | STIP | 41911 | MER | 152 | FOUR LANE FREEWAY. SEGMENT I | 4.5304 | STIP | 2008 | 5707 |  | X | X |  |  | 74174000 | 15335999.9999 | 1109999.9999 | 6086000 | 540000 | 7600000 | 4576137.583 | 20.68% | 2014-12-17 | 2016-09-01 | 0 | 3.5469 | 0.94071 | 0.042853 | Caltrans | Caltrans | Caltrans | Caltrans
10 | STIP | 0A840 | SJ | 012 | OPERATIONAL IMPROVEMENTS AT GLASSCOCK ROAD AND SMART CORRIDOR | 3.2572 | STIP | 2010 | 7350 |  |  |  | X |  | 13000000 | 7513000 | 2400000 | 1852000 | 643000 | 2618000 | 5570765.24 | 57.79% | 2012-02-08 | 2013-12-17 | 0 | 0 | 0.26846 | 2.9887 | Caltrans | Caltrans | Caltrans | Caltrans
10 | STIP | 0E490 | SJ | 005 | MODIFY/RECONSTRUCT | 3.949 | PARTNERSHIP | [6 empty] | O
10 | STIP | 0E530 | CAL | 004 | TWO LANE EXPRESSWAY | 2.6262 | PARTNERSHIP
10 | STIP | 0G550 | AMA | 088 | IMPROVE OPERATION/BYPASS | 2.2338 | PARTNERSHIP
10 | STIP | 0L590 | STA | 099 | HIGHWAY PLANTING | 0.10929 | STIP | 2008 | 0003 |  |  |  | X |  | 966000 | 519000 | 57000 | 261000 | 1000 | 200000 | 574960.56 | 53.73% | 2010-02-09 | 2013-07-25 | 0 | 0 | 0.00287 | 0.10642 | Caltrans | Caltrans | Caltrans | Caltrans
10 | STIP | 0S780 | STA | 099 | BRIDGE ENHANCEMENT, 16 STRUCTURES | 1.9662 | STIP | 2012 | 0195 |  |  |  | X |  | 1075000 | 1081000 | 96000 | 474000 | 2000 | 509000 | 517734.4 | 100.6% | 2012-12-27 | 2014-02-10 | 0 | 0 | 0.00533 | 1.9608 | Caltrans | Caltrans | Caltrans | Caltrans
10 | STIP | 0S950 | MER | 099 | CORRIDOR BRIDGE ENHANCEMENT | 0.841 | STIP | 2012 | 0196 | [5 empty] | 900000 | 324000 | 81000 | 100000 | 2000 | 141000 | 147910.38 | 36% | 2013-06-21 | 2014-12-14 | 0 | 0 | 0.00481 | 0.83619 | Caltrans | Caltrans | Caltrans | Caltrans
10 | STIP | 0W450 | ALP | 004 | SIGNAGE AND STRIPING | 0.08529 | PARTNERSHIP | [6 empty] | O
10 | STIP | 3169C | MER | 099 | HIGHWAY PLANTING AND IRRIGATION | 0.19623 | STIP | 2008 | 0546Y | [5 empty] | 521000 | 718000 | 122000 | 265000 | 1000 | 330000 | 729255.56 | 137.8% | 2010-02-11 | 2014-09-05 | 0 | 0 | 0 | 0.19623 | Caltrans | Caltrans | Caltrans | Caltrans
10 | STIP | 3404A | TUO | 108 | ENVIRONMENTAL MITIGATION AND MONITORING. | 0.05715 | STIP | 2008 | 0021A | [5 empty] | 6647315 | 1071854 | 6792 | 529132 | 35420 | 500510 | 2597936.51 | 16.12% | - - | 2009-03-12 | 0 | 0 | 0 | 0.05715 | Caltrans | Caltrans | Caltrans | Caltrans
10 | STIP | 3404U | TUO | 108 | WIDEN EXISTING HIGHWAY | 4.2569 | STIP | 2008 | 0021A | [5 empty] | D | 238236 | D | D | 238236 | D | 18648999.96 | NA | 2001-06-21 | 2007-08-28 | 0 | 0 | 4.2569 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
10 | STIP | 3A66U | MER | 140 | REPLACE BRIDGE AND WIDEN ROADWAY | 12.8616 | STIP | 2010 | 5645 | [5 empty] | 33706000 | 10756000 | 1651000 | 3781000 | 1539000 | 3785000 | 10419490.87 | 31.91% | 2010-10-11 | 2015-04-03 | 0 | 0 | 0 | 12.8616 | Caltrans | Caltrans | Caltrans | Caltrans
10 | STIP | 4454U | SJ | 099 | WIDEN TO SIX LANES, MODIFY INTERCHANGES | 0.75526 | PARTNERSHIP | [6 empty] | O
11 | STIP | 05633 | SD | 011 | CONSTRUCT NEW 4 LANE HIGHWAY AND COMMERCIAL VEHICLE ENFORCEMENT | 44.22 | STIP | 2010 | 1000 | [5 empty] | 205700000 | 39700000 | N | 17500000 | 2100000 | 20100000 | 7409328.6775 | 19.3% | 2015-04-01 | 2017-04-03 | 0 | 36.54 | 7.68 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
11 | STIP | 05634 | SD | 011 | CONSTRUCT LAND PORT OF ENTRY | 29.98 | STIP | 2010 | 1000 | [5 empty] | 292800000 | 48500000 | N | 14400000 | 2100000 | 32000000 | 7280146.0875 | 16.56% | 2015-04-01 | 2017-03-01 | 0 | 23.91 | 6.07 | 0 | Caltrans | Caltrans | Caltrans | Local
11 | STIP | 06510 | SD | 005 | PLANTING AND IRRIGATION | 0.02338 | STIP | 2004 | 0135G | [5 empty] | 813000 | 1093000 | 126000 | 964000 | 3000 | I | 1624181.5 | 134.4% | 2004-08-20 | 2010-04-19 | 0 | 0 | 0 | 0.02338 | Caltrans | Caltrans | Caltrans | Caltrans
11 | STIP | 06802 | IMP | 007 | HIGHWAY PLANTING AND IRRIGATION | 0.73338 | STIP | 2006 | 0051Y |  |  |  | X |  | 2000000 | 494000 | H | 190000 | 10000 | 294000 | 880190.86 | 24.7% | 2007-11-16 | 2013-08-02 | 0 | 0 | 0 | 0.73338 | Caltrans | Caltrans | Caltrans | Caltrans
11 | STIP | 08092 | SD | 015 | CONSTRUCT MANAGED LANES MIDDLE UNIT 3 | 0.0739 | STIP | 2006 | 0672 | [5 empty] | 104516000 | 25288804 | H | 8968044 | 320760 | 16000000 | 26902010.096 | 24.2% | 2004-09-22 | 2009-11-03 | 0 | 0 | 0 | 0.0739 | Caltrans | Caltrans | Caltrans | Caltrans
11 | STIP | 08093 | SD | 015 | CONSTRUCT MANAGED LANES UNIT 4 | 0.03496 | STIP | 2006 | 0672 | [5 empty] | 40081000 | 13385000 | H | 5349000 | 133000 | 7903000 | 14665571.556 | 33.39% | 2005-04-27 | 2008-07-15 | 0 | 0 | 0 | 0.03496 | Caltrans | Caltrans | Caltrans | Caltrans
11 | STIP | 09183 | SD | 905 | CONSTRUCT NEW FREEWAY (PHASE 2) | 0.90526 | TIGER
11 | STIP | 14665 | SD | 094 | OUTSIDE LANE WIDENING/CONST FWY TO FWY CONNNECTORS | 7.1966 | STIP | 2006 | 0356 | X |  |  |  |  | 176000000 | 12000000 | 6000000 | 6000000 | C | D | 4697610.65 | 6.818% | 2016-12-15 | 2019-01-09 | 5.9448 | 1.2518 | 0 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
11 | STIP | 16789 | IMP | 078 | CONSTRUCT FOUR LANE EXPRESSWAY | 2.7152 | STIP | 2010 | 0021 | [5 empty] | 63404760 | 19120800 | 2260440 | 6644720 | 3215640 | 7000000 | 13919455.3603 | 30.16% | 2010-11-30 | 2012-12-10 | 0 | 0 | 1.1399 | 1.5753 | Caltrans | Caltrans | Caltrans | Caltrans
11 | STIP | 17520 | IMP | 098 | WIDEN TO 4-LANE CONVENTIONAL HWY | 0.07515 | STIP | 2010 | 0042A | [5 empty] | 52800000 | 9000000 | A | 9000000 | A | A | 2435419.3 | 17.05% | 2025-05-02 | 2027-06-23 | 0.05695 | 0.01093 | 0 | 0.00727 | Caltrans | Caltrans | Caltrans | Caltrans
11 | STIP | 23580 | SD | 005 | CONST HOV/GENERAL PURPOSE/AUX LANES | 14.4333 | STIP | 2012 | 0615 | [5 empty] | A | 66513000 | 65018000 | N | 1495000 | N | 45014086.58 | NA | - - | - - | 14.4333 | 0 | 0 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
11 | STIP | 26330 | IMP | 008 | REVISED INTERCHANGE | 9.8448 | STIP | 2012 | 0523 | [5 empty] | 24800000 | 8320000 | 1500000 | 3100000 | 300000 | 3420000 | 1798481.48 | 33.55% | 2013-12-11 | 2015-05-26 | 0 | 1.8862 | 0.67126 | 7.2873 | Caltrans | Caltrans | Caltrans | Caltrans
11 | STIP | 26500 | SD | 163 | PLANTING AND IRRIGATION | 0.44078 | STIP | 2008 | 0867 | [5 empty] | 2700000 | 1196000 | 95000 | 573000 | C | 528000 | 1120020.76 | 44.3% | 2009-10-08 | 2015-12-15 | 0 | 0 | 0 | 0.44078 | Caltrans | Caltrans | Caltrans | Caltrans
11 | STIP | 26501 | SD | 163 | SCENIC/HISTORIC HIGHWAY PRESERVATION | 2.1949 | STIP | 2012 | 1008 | [5 empty] | 3976000 | 1270000 | 125000 | 525000 | 20000 | 600000 | 319093.85 | 31.94% | 2013-07-30 | 2017-10-04 | 0 | 0.16296 | 0 | 2.032 | Caltrans | Caltrans | Caltrans | Caltrans
11 | STIP | 28710 | SD | 094 | CONSTRUCT 2 HOV LANES LANES | 15.3617 | STIP | 2012 | T0770 | [5 empty] | 465000000 | 12936000 | 12936000 | A | A | A | 10282008.63 | 2.782% | 2017-11-14 | 2020-11-28 | 15.3617 | 0 | 0 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
11 | STIP | 29480 | IMP | 186 | PEDESTRIAN/TRANSIT FACILITIES | 1.416 | STIP | 2012 | 0505 | [5 empty] | 1730000 | 1450000 | 185000 | 836000 | 10000 | 419000 | 613358.8 | 83.82% | 2013-08-04 | 2017-08-24 | 0 | 0.10415 | 0.00526 | 1.3066 | Caltrans | Caltrans | Caltrans | Caltrans
11 | STIP | 29490 | SD | 188 | PEDESTRIAN/TRANSIT FACILITIES | 0.27085 | STIP | 2012 | 0743 | [5 empty] | 1550000 | 832000 | 109000 | 341000 | 10000 | 372000 | 720.62 | 53.68% | 2016-01-09 | 2018-01-29 | 0.27085 | 0 | 0 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
11 | STIP | 40290 | SD | 015 | CONSERVATION CORPS - FALLBROOK TREE PLANTING | 0.24694 | PARTNERSHIP
11 | STIP | 40400 | SD | 005 | AESTHETIC COORIDOR MASTER PLAN - TRANSPORTATION ENHANCEMENT (TE) | 0.63181 | STIP | 2012 | 1007 | [5 empty] | A | 216000 | 216000 | A | A | A | 0 | NA | - - | - - | 0.63181 | 0 | 0 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
11 | STIP | 40410 | SD | 005 | BIKE/PED EAST TO WEST CONNECTION UNDER I-5 | 0.63435 | STIP | 2012 | 1009 | [5 empty] | 1883000 | 1160000 | 120000 | 440000 | 20000 | 580000 | 0 | 61.6% | 2016-08-22 | 2018-02-03 | 0.57103 | 0.02686 | 0.03646 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
11 | STIP | 40420 | SD | 079 | HISTORIC HIGHWAY 80 INTERPRETIVE PROJECT | 0.35942 | STIP | 2012 | 1010 | X |  | X |  |  | 350000 | 180000 | 35000 | 70000 | 5000 | 70000 | 1148.79 | 51.43% | 2014-12-10 | 2019-02-23 | 0.02412 | 0.30858 | 0.02672 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
11 | STIP | 40440 | IMP | 078 | LANDSCAPE MITIGATION FOR BRAWLEY BYPASS (STAGE 3) | 1.0587 | STIP | 2012 | 0021Y |  | X | X |  |  | 1400000 | 541000 | H | 200000 | H | 341000 | 20806.19 | 38.64% | 2014-02-28 | 2018-04-16 | 0 | 0.83825 | 0 | 0.22049 | Caltrans | Caltrans | Caltrans | Caltrans
11 | STIP | 0301U | SD | 005 | WIDEN FREEWAY AND BRIDGES | 0.25603 | STIP | 2000 | 0129X | [5 empty] | 163579000 | 26005000 | 58000 | 10613000 | 2097000 | 13237000 | 49452772.85 | 15.9% | 2002-03-12 | 2008-08-07 | 0 | 0 | 0.10978 | 0.14625 | Caltrans | Caltrans | Caltrans | Caltrans
11 | STIP | 1993U | IMP | 111 | CONSTRUCT 4 LANE EXPRESSWAY | 0.029 | STIP | 2010 | 0043H | [5 empty] | 41486000 | 8623000 | 16000 | 1453000 | 3803000 | 3351000 | 9070811.83 | 20.79% | 2000-09-21 | 2002-12-10 | 0 | 0 | 0.029 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
12 | STIP | 0E070 | ORA | 005 | WIDEN FREEWAY AND OVERHEAD | 0.18031 | STIP | 2008 | 2671A | [5 empty] | 16861000 | 5942000 | 306000 | 1814000 | 650000 | 3172000 | 6846624.11 | 35.24% | 2008-07-22 | 2011-09-19 | 0 | 0 | 0.05319 | 0.12712 | Local | Local | Caltrans | Caltrans
12 | STIP | 05622 | ORA | 090 | HIGHWAY PLANTING & LANDSCAPING | 0.08379 | STIP | 2010 | 4434B | [5 empty] | 1280000 | 461000 | 30000 | 262000 | 9000 | 160000 | 337608.42 | 36.02% | 2011-09-29 | 2016-02-01 | 0 | 0 | 0 | 0.08379 | Caltrans | Caltrans | Caltrans | Caltrans
12 | STIP | 07161 | ORA | 022 | CONSTRUCT HOV LANES | 2.3246 | STIP | 2006 | T0702 | [5 empty] | 508115000 | 52269000 | 1869000 | 50400000 | M | M | 26804266.68 | 10.29% | 2004-09-22 | 2011-03-16 | 0 | 0 | 0 | 2.3246 | Caltrans | Local | Local | Local
12 | STIP | 08691 | ORA | 074 | WIDEN FROM 2 LANES TO 4 LANES | 0.10029 | PARTNERSHIP
12 | STIP | 10167 | ORA | 005 | RECONSTRUCT AND WIDEN FREEWAY | 0.2772 | STIP | 2004 | 0978T | [5 empty] | 198721000 | 49118000 | 1066000 | 13800000 | 12469000 | 21783000 | 32131605.32 | 24.72% | 2006-04-15 | 2011-01-18 | 0 | 0 | 0.10215 | 0.17505 | Caltrans | Caltrans | Caltrans | Caltrans
12 | STIP | 0C560 | ORA | 091 | PROVIDE AN AUXILIARY LANE FROM NB SR-55 TO TUSTIN AVE OFF-RAMP | 8.8362 | STIP | 2012 | 4587A | [5 empty] | 23100000 | 15630000 | 3800000 | 5000000 | 1930000 | 4900000 | 7072014.36 | 67.66% | 2013-10-10 | 2015-10-01 | 0 | 0.23485 | 0.11117 | 8.4902 | Caltrans | Caltrans | Caltrans | Caltrans
12 | STIP | 0E310 | ORA | 074 | RECONSTRUCT IC AT SR-74 | 16.9142 | STIP | 2012 | 4102 | [5 empty] | 67567000 | 18647000 | 1700000 | 7373000 | 3000000 | 6574000 | 9407132.93 | 27.6% | 2012-08-22 | 2016-03-01 | 0 | 0 | 1.8415 | 15.0727 | Local | Caltrans | Caltrans | Caltrans
12 | STIP | 0E31A | ORA | 074 | HIGHWAY REPLACEMMENT PLANTING | 0.54116 | STIP | 2010 | 4102A | [5 empty] | 1000000 | 420000 | E | 210000 | C | 210000 | 0 | 42% | 2015-02-01 | 2019-03-01 | 0 | 0.53736 | 0.0038 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
12 | STIP | 0E570 | ORA | 005 | WIDEN ROADWAY AND BRIDGES AND CONSTRUCT RETAINING WALLS | 1.0626 | STIP | 2008 | 2615 |  |  |  | X |  | 13106000 | 6045000 | 363000 | 2940000 | 297000 | 2445000 | 5651410.74 | 46.12% | 2010-06-22 | 2014-02-22 | 0 | 0 | 0.4417 | 0.62093 | Local | Caltrans | Caltrans | Caltrans
12 | STIP | 0G730 | ORA | 005 | REMOVE AND PRUNE TREES | 0.04799 | STIP | 2008 | 2592 | [5 empty] | 1332000 | 528000 | 96000 | 265000 | C | 167000 | 517710.64 | 39.64% | 2010-04-14 | 2014-09-01 | 0 | 0 | 0 | 0.04799 | Caltrans | Caltrans | Caltrans | Caltrans
12 | STIP | 0G940 | ORA | 005 | CONSTRUCT SOUNDWALLS AND WIDEN BRIDGE | 0.41869 | STIP | 2010 | 2544B |  |  |  | X |  | 3575000 | 1420000 | E | 646000 | 86000 | 688000 | 1312394.8 | 39.72% | 2010-12-20 | 2013-07-01 | 0 | 0 | 0 | 0.41869 | Local | Local | Caltrans | Caltrans
12 | STIP | 0G990 | ORA | 005 | WIDEN AND CONSTRUCT RETAINING WALL | 0.45465 | STIP | 2010 | 2806B |  |  |  | X |  | 3983000 | 2367000 | 435000 | 917000 | 56000 | 959000 | 2364937.44 | 59.43% | 2011-03-15 | 2013-12-01 | 0 | 0 | 0 | 0.45465 | Caltrans | Caltrans | Caltrans | Caltrans
12 | STIP | 0H045 | ORA | 405 | ADD AUXILIARY LANE | 0.09951 | STIP | 2012 | 4956 | [5 empty] | 5450000 | 2087000 | 224000 | 900000 | 44000 | 919000 | 0 | 38.29% | 2017-05-01 | 2018-12-01 | 0.09951 | 0 | 0 | 0 | Caltrans | Caltrans | Caltrans | Caltrans
12 | STIP | 0J420 | ORA | 057 | REMOVE EXST HOV BUFFER. RESTRIPE FREEWAY TO PROVIDE A CONTINUOUS HOV | 1.8123 | STIP PA | 2012 | 3636A
12 | STIP | 0K330 | ORA | 091 | WILDLIFE CORRIDOR CONNECTIVITY ENHANCEMENT | 0.17696 | STIP | 2012 | 2140 | [5 empty] | 607000 | 195000 | 37000 | 67000 | 12000 | 79000 | 196575.45 | 32.13% | 2013-02-12 | 2017-04-01 | 0 | 0 | 0 | 0.17696 | Caltrans | Caltrans | Caltrans | Caltrans
12 | STIP | 0L180 | ORA | 142 | NATIVE PLANTING ENHANCEMENT | 0.0367 | STIP | 2008 | 5357 | [5 empty] | 450000 | 75000 | L | L | C | 75000 | 132264.66 | 16.67% | 2010-10-11 | 2015-05-02 | 0 | 0 | 0 | 0.0367 | Caltrans | Caltrans | Caltrans | Caltrans
Notes
DB - Design Build project.
ER - Funded with Federal Emergency Relief funds.
MINOR - SHOPP Minor lump sum FTE allocated to each District.
OTS - Funded with Office of Traffic Safety Federal grants. Formerly SHOPP.
PARTNERSHIP - Measure or local funded support. Not programmed in STIP or SHOPP.
P3 - Public Private Partnership.
RETROFIT SOUNDWALL - Project authorized by AB 1740. Not programmed in STIP or SHOPP.
SHOPP FCO - SHOPP Funding Contribution Only - oversight only
SHOPP PA - Pending ammendment in 2012 SHOPP.
STIP PA - Pending ammendment in 2012 STIP.
TIGER - Former STIP, now funded with Federal TIGER grants.
*Some project budgets include unfunded need reported in CTIPS.
** Construction start date estimated as Award Date Milestone 495 or Approved Contract Milestone 500.
** *Construction end date estimated as Construction Contract Acceptance Date Milestone 600. Source is XPM or PMCS.
A - PAED only project. Project programmed for PAED only.
B - PSE only project. ROW support may or may not be programmed. No construction support programmed.
C - No ROW support needed or programmed.
D - Non Traditional Capital Outlay Support project.
E - PAED completed during Planning phase.
F - All support component budgets included under PAED component in pre 2008 SHOPP
G - Local Agency implementing Right of Way and/or Construction. Right of Way and/or Construction support budget combined with Right of Way and/or Construction Capital budget.
H - Component completed under master project.
I - Project deleted from STIP or SHOPP. May have been split or combined.
J - Service contract. Project programmed for construction capital and construction support only.
K - ROW support only for corridor.
L - All support programmed under construction support.
M - Design-Build project.
N - Component completed under another project.
O - Full oversight project only. Caltrans only responsible for QA/QC
P - Corridor Project or Corridor Master Plan.
Q - PAED completed under SHOPP Minor program
R - Emergency Opening (201.130) project with programmed ROW & CON Support Only
S - Emergency Opening (201.130) project with programmed for Design and CON Support Only