## Instructions
INSTRUCTIONS Exhibit 25-P: ATP Plan Scope of Work
Plan Components
The CTC ATP Guidelines require that a plan must include, but not be limited to, the specified plan components or explain why the component is not applicable. On the Tab for 'Plan Components', please check the box for the components the plan will include, and if not included, explain why the component is not applicable.
Scope of Work (SOW) Template
The SOW defines the scope, cost, and deliverables of the plan. It also provides the details as to how the required plan components will be included throughout the development of the plan and in the final plan. On the Tab for 'SOW Template', please input the process for how you will execute completing the plan. Insert additional rows as needed. Include the Agency Name, the Project Name, and the Start and End Dates. Include in each row: • A task title • A task description • The start and end dates of the task • The cost per task (both ATP and Non-ATP) In the column for 'Required Plan Component the Task will Address', select the component that tasks addresses from drop down menu. Multiple components can be included in one task.
Example SOW
On the TAB for 'Example SOW', a sample SOW is provided for your reference. Do not directly copy the Example SOW. Your project is unique.
Form Updated: February 10, 2026

## Plan Components
Plan Requirements per ATP Guidelines
| The Active Transportation Guidelines require that an active transportation plan must include, but not be limited to, the following components or explain why the component is not applicable. | Check if included in SOW | If not, explain why not applicable.
A | Mode Share: The estimated number of existing bicycle trips and pedestrian trips in the plan area, both in absolute numbers and as a percentage of all trips, and the estimated increase in the number of bicycle trips and pedestrian trips resulting from implementation of the plan.
B | Description of Land Use/Destinations: A map and description of existing and proposed land uses which must include, but not be limited to, locations of residential neighborhoods, schools, shopping centers, public buildings, major employment centers, major transit hubs, and other destinations. Major transit hubs must include, but are not limited to, rail and transit terminals, and ferry docks and landings.
C | Pedestrian Facilities: A map and description of existing and proposed pedestrian facilities, including those at major transit hubs and those that serve public and private schools.
D | Bicycle Facilities: A map and description of existing and proposed bicycle transportation facilities, including those at major transit hubs and those that serve public and private schools.
E | Bicycle Parking: A map and description of existing and proposed end-of-trip bicycle parking facilities. Include a description of any existing and proposed policies related to bicycle parking in public locations, private parking garages and parking lots and in new commercial and residential developments. Also include a map and description of existing and proposed bicycle transport and parking facilities for connections with and use of other transportation modes. These must include, but not be limited to, bicycle parking facilities at transit stops, rail and transit terminals, ferry docks and landings, park and ride lots, and provisions for transporting bicyclists and bicycles on transit or rail vehicles or ferry vessels.
F | Wayfinding: A description of existing and proposed signage providing wayfinding along bicycle and pedestrian networks to designated destinations.
G | Non-Infrastructure Programs: A description of existing and proposed bicycle and pedestrian education, encouragement, enforcement programs conducted in the area included within the plan. Include efforts by the law enforcement agency having primary traffic law enforcement responsibility in the area to enforce provisions of the law impacting bicycle and pedestrian safety, and the resulting effect on collisions involving bicyclists and pedestrians.
H | Collision Analysis: The number and location of collisions, serious injuries, and fatalities suffered by bicyclists and pedestrians in the plan area, both in absolute numbers and as a percentage of all collisions and injuries, and a goal for collision, serious injury, and fatality reduction after implementation of the plan.
I | Equity Analysis: Identify census tracts that are considered to be disadvantaged or low-income and identify the bicycle and pedestrian needs of those disadvantaged or low-income residents.
J | Community Engagement: A description of the extent of community involvement in development of the plan, including disadvantaged and underserved communities.
K | Coordination: A description of how the plan has been coordinated with neighboring jurisdictions, including school districts within the plan area, and is consistent with other local or regional transportation, air quality, or energy conservation plans, including, but not limited to, General Plans and a Sustainable Community Strategy in a Regional Transportation Plan.
L | Prioritization: A description of the projects and programs proposed in the plan and a listing of their priorities for implementation, including the methodology for project prioritization and a proposed timeline for implementation.
M | Funding: A description of future financial needs for projects and programs that improve safety and convenience for bicyclists and pedestrians in the plan area. Include anticipated cost, revenue sources and potential grant funding for bicycle and pedestrian uses.
N | Implementation: A description of steps necessary to implement the plan and the reporting process that will be used to keep the adopting agency and community informed of the progress being made in implementing the plan.
O | Maintenance: A description of the policies and procedures for maintaining existing and proposed bicycle and pedestrian facilities, including, but not limited to, the maintenance of smooth pavement, ADA level surfaces, freedom from encroaching vegetation, maintenance of traffic control devices including striping and other pavement markings, and lighting.
P | Resolution: A resolution showing adoption of the plan by the city, county or district. If the active transportation plan was prepared by a county transportation commission, regional transportation planning agency, MPO, school district or transit district, the plan should indicate the support via resolution of the city(s) or county(s) in which the proposed facilities would be located.

## SOW Template
Exhibit 25-PLAN Plan Scope of Work
Agency:
Project Name: | [5 empty] | Project Start Date: | [6 empty] | Project End Date:
Task Number | Task | Task Description | Start Date | End Date | ATP Cost | Non-ATP Cost | Required Plan Component the Task will Address
[7 empty] | A | B | C | D | E | F | G | H | I | J | K | L | M | N | O | P
Task Title
1
2
3
Task Title
4
5
6
7
Task Title
8
9
10
11
12
Task Title
13
14
15
16
Task Title
17
18
19
|  |  |  | Total Cost: | 0 | 0

## Example SOW
Exhibit 25-PLAN Plan Scope of Work
Agency: | City of Can-Do
Project Name: | City of Can-Do Active Transportation Plan |  |  |  |  | Project Start Date: | Jan-2026 | [5 empty] | Project End Date: |  |  |  |  | June-2028
Task Number | Task | Task Description | Start Date | End Date | ATP Cost | Non-ATP Cost | Required Plan Component the Task will Address
[7 empty] | A | B | C | D | E | F | G | H | I | J | K | L | M | N | O | P
Project Administration
1 | RFP for Consultant Services | Prepare the RFP for consultant services and execute a contract. | Jan-2026 | Apr-2026 | 4000 | 0 | Required Plan Component the Task will Address A: n/a
2 | Coordination Meetings | Hold monthly coordination meetings with the project team (consultant and city staff). | Apr-2026 | June-2028 | 6000 | 0 | Required Plan Component the Task will Address A: n/a
3 | Invoicing and Reporting | Prepare and submit timely invoices and reports to Caltrans. | Jan-2026 | June-2028 | 4000 | 0 | Required Plan Component the Task will Address A: n/a
Existing Conditions and Analysis
4 | Existing Conditions | Gather existing condition information that includes current mode share, description of land use and destinations, existing bicycle parking, existing wayfinding, and existing non-infrastructure programs. | Apr-2026 | Jul-2026 | 15000 | 0 | Required Plan Component the Task will Address A: A,; Required Plan Component the Task will Address B: B,; Required Plan Component the Task will Address C: E,; Required Plan Component the Task will Address D: F,; Required Plan Component the Task will Address E: G,
5 | Existing Bicycle and Pedestrian Facilities Map | Develop a map of existing pedestrian facilities and existing bicycle facilities within the city. | Apr-2026 | Jul-2026 | 10000 | 0 | bar: Required Plan Component the Task will Address A to Required Plan Component the Task will Address B
6 | Collision Data and Analysis | Gather collision data for bicyclists and pedestrians both in absolute numbers and as a percentage of all collisions and injuries. Perform analysis and set a goal for collision, serious injury, and fatality reduction after implementation of the plan. | June-2026 | Aug-2026 | 7000 | 0 | bar: Required Plan Component the Task will Address A
7 | Equity Data and Analysis | Identify census tracts that are considered to be disadvantaged or low-income and identify the bicycle and pedestrian needs. | June-2026 | Aug-2026 | 5000 | 0 | bar: Required Plan Component the Task will Address A
Outreach and Engagement
8 | Technical Advisory Committee Meetings | Form an advisory committee of identified stakeholders to meet quarterly to guide the plan development. | Apr-2026 | June-2028 | 7000 | 0 | bar: Required Plan Component the Task will Address A to Required Plan Component the Task will Address B
9 | Website and Social Media Page | Create a website and social media page for plan announcements and documents to be posted. This task also include graphic design for these media outlets. | May-2026 | June-2028 | 20000 | 0 | bar: Required Plan Component the Task will Address A
10 | Community Workshop | Host three community workshops (charrettes) in various parts of the city and varying times to gain community input on new bicycle and pedestrian facilities. The community meetings will include a translator. | Sep-2026 | Jan-2028 | 20000 | 0 | bar: Required Plan Component the Task will Address A
11 | Attend Community Events | Attend at least 10 different community events to gather public input. Events will include farmers markets, school events, neighborhood gatherings, etc. | Sep-2026 | Jan-2028 | 15000 | 0 | bar: Required Plan Component the Task will Address A
12 | Coordination Meetings with Neighboring Jurisdictions | Hold bi-annual Coordination Meeting with Neighboring Jurisdictions. | June-2026 | June-2028 | 2500 | 0 | bar: Required Plan Component the Task will Address A
Implementation
13 | Proposed Pedestrian Facilities, Bicycle Facilities, and Non-Infrastructure Programs | Create maps of the proposed pedestrian and bicycle facilities, and NI programs based on the community and stakeholder input and the TAC. Description will include estimate mode shift from identified projects and programs. | Jan-2027 | May-2027 | 10000 | 0 | Required Plan Component the Task will Address A: A,; Required Plan Component the Task will Address B: C,; Required Plan Component the Task will Address C: D,; Required Plan Component the Task will Address D: G,
14 | Project Prioritization Methodology | Develop a methodology for project prioritization and a proposed timeline for implementation. | Feb-2027 | June-2027 | 12000 | 0 | bar: Required Plan Component the Task will Address A
15 | Identify Financial Needs | Include the financial needs for future projects and programs by listing anticipated cost, revenue sources and potential grant funding. | June-2027 | Sep-2027 | 7000 | 0 | bar: Required Plan Component the Task will Address A
16 | Create an Implementation Strategy | A description of steps necessary to implement the plan and the reporting process that will be used to keep the adopting agency and community informed of the progress being made in implementing the plan. This strategy includes maintenance considerations. | Sep-2027 | Dec-2027 | 10000 | 0 | bar: Required Plan Component the Task will Address A to Required Plan Component the Task will Address B
Final Plan
17 | Draft Plan | Prepare draft plan and receive comments. | Mar-2027 | Dec-2027 | 20000 | 0 | A, | B, | C, | D, | E, | F, | G, | H, | I, | J, | K, | L, | M, | N, | O,
18 | Final Plan | Prepare final plan. | Jan-2028 | June-2028 | 25000 | 0 | A, | B, | C, | D, | E, | F, | G, | H, | I, | J, | K, | L, | M, | N, | O,
19 | Resolution | Present final plan to the city council for resolution approval. | June-2028 | June-2028 | 500 | 0 | bar: Required Plan Component the Task will Address A
|  |  |  | Total Cost: | 200000 | 0

## Data (hidden)
n/a
A,
B,
C,
D,
E,
F,
G,
H,
I,
J,
K,
L,
M,
N,
O,
P