## TCEP SB1
Trade Corridor Enhancement Account Projects with Lapsing Senate Bill 1 Funds
Reversion Date: | 2026-06-30
Appropriation/Item Number | 2660-101-3291
Year of Appropriation: | 2019-20
Appropriation Unit: | 20101
Program Code: | 20.30
District | Parties to Agreement (Agency) | Purpose of Project (Work Description) | Scope (Location) | Prefix | Project Id | Advantage Project Id | PPNO | Federal Program Code | Budgeted Amount | Expenditure Amount | Remaining Balance | CTC TUF Deadline | Is Project Consistent with Original Scope and Purpose of the Appropriation? If No, Please Explain: | Are You Requesting a CWA (Yes or No)? If No, provide an anticipated date the agency plans to submit invoice for the remaining balance | Reason for Delay | Please Provide a 2-3 Sentence Explanation Identifying Any Impediments to Completion | What are the Consequences if CWA is Not Approved? (Please Provide a 2-3 Sentence Explanation) | Local Agency Contact Name | Local Agency Contact Phone Number | Local Agency Contact Email | Approved by DOF (Yes or No)? | Revised Reversion Date
08 | Corona | Grade Separation | In Corona on existing Mckinley Street from Griffin Way to Magnolia Avenue. | SB1TCEP | 5104(044) | 0814000127 | 1272 |  | 10300000 | 0 | 10300000 | 2026-07-31 | YES | YES | Contract Dispute/Litigation: Formal litigation proceeding. | While the project is substantially complete, there are active litigation matters associated with the contract that are still in process. A contract extension is necessary to accommodate the resolution of these issues and ensure proper administrative closeout. | If the CWA is not approved, the project may not be able to be completed which will not provide relief from congestion, improve mobility and safety for both motorists and pedestrians, and improve air quality and noise. | Sarah Arce | (951) 736-2278 | sarah.arce@coronaca.gov | Yes | 2028-06-30
11 | San Diego | To widen and improve La Media Road from State Route 905 to Siempre Viva Road. | Located in the City of San Diego. South of State Route 905 (SR-905), North of Siempre Viva Road, East of Britannia Road and West of Otay Mesa. | TCEPSB1L | 5004(212) | 1121000186 | 1435 |  | 22700000 | 22246000 | 454000 | 2025-12-31 | YES | YES | OTHER (explain): Remaining balance due to Caltrans required retention. | Remaining balance will be sought for reimbursement by the final invoice. | The work is completed by the contractor, and they need to get paid for the performed work per the construction contract otherwise Caltrans will be out of compliance with the contract. | Ramin Nasrabadi | (619) 533-4189 | rnasrabadi@sandiego.gov | Yes | 2028-06-30
[8 empty] | Total | 33000000 | 22246000 | 10754000

## Drop-down Reference Tables
Within Scope? | Need a CWA? | Primary Reason For Delay:
YES | YES | Design: Change in scope.
NO | NO | Design: Change in specifications.
Design: Change in site conditions.
Environmental: Change in scope requires additional studies/permits.
Environmental: Excessive study or opinion review time by external agencies.
Environmental: Permits expired.
Environmental: Environmental document determination revalidation required.
Environmental: Mitigation for project impacts period.
Right of Way and Utility Relocation: Change in scope/number of parcels/utility relocations required.
Right of Way and Utility Relocation: Condemnation/eminent domain proceedings.
Right of Way and Utility Relocation: Utility owner dispute.
Right of Way and Utility Relocation: Qualified Buy America purchase/delivery delays.
Construction: Contract award disputed/cancelled, rebid or complete under force account.
Construction: Change in site conditions.
Construction: Qualified Buy America purchase/delivery delays.
Construction: Extended winter suspension affecting delivery schedule.
Contract Dispute/Litigation: Post-construction claim. Informal settlement.
Contract Dispute/Litigation: Formal litigation proceeding.
Finance: CTC approved Time Extension conflicts with reversion date.
Finance: Indirect Cost Rate Proposal (ICRP) request package returned with errors.
Finance: Change in dedicated/programmed funding.
Finance: Pending programming.
OTHER-declared disaster:
OTHER (explain):