## ATP Federal
ATP Projects with Lapsing Federal Funds
Reversion Date: | 2026-06-30
Appropriation/Item Number: | 2660-108-0890
Year of Appropriation: | 2020-21
Appropriation Unit: | 21108F
Program Code: | 20.30
District | Parties to Agreement (Agency) | Purpose of Project (Work Description) | Scope (Location) | Prefix | Federal Project Id | Advantage Project Id | PPNO | Federal Program Code | Budgeted Amount | Expenditure Amount | Remaining Balance | CTC TUF Deadline | Is Project Consistent with Original Scope and Purpose of the Appropriation? If No, Please Explain: | Are You Requesting a CWA (Yes or No)? If No, provide an anticipated date the agency plans to submit invoice for the remaining balance | Reason for Delay | Please Provide a 2-3 Sentence Explanation Identifying Any Impediments to Completion | What are the Consequences if CWA is Not Approved? (Please Provide a 2-3 Sentence Explanation) | Local Agency Contact Name | Local Agency Contact Phone Number | Local Agency Contact Email | Approved by DOF (Yes or No)? | Revised Reversion Date
07 | Los Angeles | Pedestrian and Bike Path | 7 miles of pedestrian and cyclist improvements within the heart of the Canoga Park community connecting Disadvantaged Communities (DAC) residents with local destination. | ATPL | 5006(918) | 721000261 | 5862 | Z3E1 | 3567000 | 2251929.68 | 1315070.32 | 2026-06-30 | YES | YES | OTHER-declared disaster (explain): | Due to the Palisades Fire in 2025 in the City of Los Angeles (City), the City has experienced delays in the delivery of existing Active Transportation Program (ATP) projects. The delays are encountered from staff resources that had been diverted to the emergency response and recovery efforts. | The project could lose federal funding and potentially halt the Preliminary Engineering (PE) phase prior to project completion. The project will not be able to provide safety features for the Community. | Brian Ahn | (213) 887-1037 | Brian.Ahn@lacity.org | Yes | 2028-06-30
07 | Los Angeles | Pedestrian & Cyclist Safety Project | 2nd Street on the North; Los Angeles River to the East; 7th Street to the South; Alameda Street to the West, and Los Angeles River on the west. | ATPL | 5006(864) | 0717000302 | 5286 | Y301 | 837132 | 820389.36 | 16742.64 | 2026-09-30 | YES | YES | Construction: Change in site conditions. | Construction is anticipated to be completed by September 2026. The City of Los Angeles (City) would like to request additional time to complete the remaining construction work, conduct final inspection, issue notice of completion, negotiate and reconcile final contract and extra work costs, and submit final closeout package and invoice. | If the CWA is not approved, the loss of the federal Active Transportation Program (ATP) funds would negatively affect the City's finances and halt the remaining stages of construction work. The project will not be able to send the contractor final payment and satisfy all close out inspection and compliance requirements per standard federal funding procedures. Reverting funds to this project would negatively impact the City's available funding and cash flow to deliver all other safety capital projects in the City. | George Huang | (213) 485-1159 | george.huang@lacity.org | Yes | 2028-06-30
07 | Los Angeles | Pedestrian & Cyclist Safety Project | 2nd Street on the North; Los Angeles River to the East; 7th Street to the South; Alameda Street to the West, and Los Angeles River on the West. | ATPL | 5006(864) | 0717000302 | 5286 | Y301 | 11462868 | 3849577.42 | 7613290.58 | 2026-09-30 | YES | YES | Construction: Change in site conditions. | Construction is anticipated to be completed by September 2026. The City of Los Angeles (City) would like to request additional time to complete the remaining construction work, conduct final inspection, issue notice of completion, negotiate and reconcile final contract and extra work costs, and submit final closeout package and invoice. | If the CWA is not approved, the loss of the federal Active Transportation Program (ATP) funds would negatively affect the City's finances and halt the remaining stages of construction work. The project will not be able to send the contractor final payment and satisfy all close out inspection and compliance requirements per standard federal funding procedures. Reverting funds to this project would negatively impact the City's available funding and cash flow to deliver all other safety capital projects in the City. | George Huang | (213) 485-1159 | george.huang@lacity.org | Yes | 2028-06-30
07 | San Fernando | 12-foot wide, 1.34 mile long class 1 Bike/Pedestrian path, at grade crossings, lighting, fencing, signal. | At Pacoima Wash access Road from Fourth Street (Bradley) Avenue to English Street (Eight Street) National Park. | ATPL | 5202(020) | 0721000072 | 5334 | Z300 | 1000 | 391.5 | 608.5 | 2026-09-30 | YES | YES | Construction: Change in site conditions. | As a result of missing details on the plans and significant discrepancies between the elevations indicated on the plans and the actual elevations in the field, the project encountered delays while the plans were revised. In addition, project construction was nearly completed in December 2024, but repeated acts of vandalism have delayed the final completion. To mitigate and prevent future acts of vandalism from damaging the project and compromising the safety of the bicyclist and pedestrians using the path, the City of San Fernando is working with the project contractor to install bollards at all of the entry points to prevent cars from driving on the bike path. | If the CWA is not approved, the project will not be completed. Modifications to mitigate and prevent future acts of vandalism will not be completed to ensure the safety of bicyclist and pedestrians using the path. | Patsy Orozco | (818) 898-1224 | POrozco@sanfernando.gov | Yes | 2028-06-30
07 | San Fernando | 12-foot wide, 1.34 mile long class 1 Bike/Pedestrian path, at grade crossings, lighting, fencing, signal. | At Pacoima Wash access Road from Fourth Street (Bradley) Avenue to English Street (Eight Street) National Park. | ATPL | 5202(020) | 0721000072 | 5334 | Z300 | 972000 | 923232.6 | 48767.4 | 2026-09-30 | YES | YES | Construction: Change in site conditions. | As a result of missing details on the plans and significant discrepancies between the elevations indicated on the plans and the actual elevations in the field, the project encountered delays while the plans were revised. In addition, project construction was nearly completed in December 2024, but repeated acts of vandalism have delayed the final completion. To mitigate and prevent future acts of vandalism from damaging the project and compromising the safety of the bicyclist and pedestrians using the path, the City of San Fernando is working with the project contractor to install bollards at all of the entry points to prevent cars from driving on the bike path. | If the CWA is not approved, the project will not be completed. Modifications to mitigate and prevent future acts of vandalism will not be completed to ensure the safety of bicyclists and pedestrians using the path. | Patsy Orozco | (818) 898-1224 | POrozco@sanfernando.gov | Yes | 2028-06-30
08 | San Bernardino County | Class 1 bike path | Santa Ana River Trail from Waterman Avenue in San Bernardino to the California Street alignment, Phase III. | STPLER | 5954(083) | 0800000818 | 1278 | Z301 | 1105000 | 1020775.63 | 84224.37 | 2026-10-31 | YES | YES | Contract Dispute/Litigation: Post-construction claim. Informal settlement. | County is currently negotiating with contractor and needs additional time to resolve claims and release retention. Additionally, San Bernardino County (County) still requires time to submit Final Report of Expenditures, project completion, and Active Transportation Program (ATP) final delivery reports. | Project construction is complete and County is working with the contractor to finalize outstanding claims. If not approved, County would lose remaining federal ATP funding. | Jeremy Johnson, P.E. | (909) 387-8165 | jeremy.johnson@dpw.sbcounty.gov | Yes | 2028-06-30
[8 empty] | Total | 17945000 | 8866296.19 | 9078703.81

## Drop-down Reference Tables
Within Scope? | Need a CWA? | Primary Reason For Delay:
YES | YES | Design: Change in scope.
NO | NO | Design: Change in specifications.
Design: Change in site conditions.
Environmental: Change in scope requires additional studies/permits.
Environmental: Excessive study or opinion review time by external agencies.
Environmental: Permits expired.
Environmental: Environmental document determination revalidation required.
Environmental: Mitigation for project impacts period.
Right of Way and Utility Relocation: Change in scope/number of parcels/utility relocations required.
Right of Way and Utility Relocation: Condemnation/eminent domain proceedings.
Right of Way and Utility Relocation: Utility owner dispute.
Right of Way and Utility Relocation: Qualified Buy America purchase/delivery delays.
Construction: Contract award disputed/cancelled, rebid or complete under force account.
Construction: Change in site conditions.
Construction: Qualified Buy America purchase/delivery delays.
Construction: Extended winter suspension affecting delivery schedule.
Contract Dispute/Litigation: Post-construction claim. Informal settlement.
Contract Dispute/Litigation: Formal litigation proceeding.
Finance: CTC approved Time Extension conflicts with reversion date.
Finance: Indirect Cost Rate Proposal (ICRP) request package returned with errors.
Finance: Change in dedicated/programmed funding.
Finance: Pending programming.
OTHER-declared disaster (explain):
OTHER (explain):