## District 6
ATP Projects with Lapsing Federal Funds
Reversion Date: | 2026-06-30
Appropriation/Item Number: | 2660-108-0890
Year of Appropriation: | 2021
Appropriation Unit: | 21108F
District | Parties to Agreement (Agency) | Purpose of Project (Work Description) | Scope (Location) | Prefix | Federal Project Id | Advantage Project Id | PPNO | Federal Program Code | Budgeted Amount | Expenditure Amount | Remaining Balance | CTC TUF Deadline | Is Project Consistent with Original Scope and Purpose of the Appropriation? If No, Please Explain: | Are You Requesting a CWA (Yes or No)? If No, provide an anticipated date the agency plans to submit invoice for the remaining balance | Reason for Delay | Please Provide a 2-3 Sentence Explanation Identifying Any Impediments to Completion | What are the Consequences if CWA is Not Approved? (Please Provide a 2-3 Sentence Explanation) | Local Agency Contact Name | Local Agency Contact Phone Number | Local Agency Contact Email | Approved by DOF (Yes or No)? | Revised Reversion Date
06 | Fresno | New Signals, pedestrian countdown equipment, sidewalks, curb ramps, signing and striping | Intersection of Butler and 8th Streets, intersection of Orange and Lowe Avenues, and various locations near both intersections | ATPSB1L | 5060(367) | 0620000026 | Z300 | Z3E1 | 130581 | 120237.5 | 10343.5 | 2026-10-31
06 | Fresno | New Signals, pedestrian countdown equipment, sidewalks, curb ramps, signing and striping | Intersection of Butler and 8th Streets, intersection of Orange and Lowe Avenues, and various locations near both intersections | ATPSB1L | 5060(367) | 0620000026 | Z300 | Y301 | 859419 | 819419 | 40000 | 2026-10-31

## District 7
ATP Projects with Lapsing Federal Funds
Reversion Date: | 2026-06-30
Appropriation/Item Number: | 2660-108-0890
Year of Appropriation: | 2021
Appropriation Unit: | 21108F
District | Parties to Agreement (Agency) | Purpose of Project (Work Description) | Scope (Location) | Prefix | Federal Project Id | Advantage Project Id | PPNO | Federal Program Code | Budgeted Amount | Expenditure Amount | Remaining Balance | CTC TUF Deadline | Is Project Consistent with Original Scope and Purpose of the Appropriation? If No, Please Explain: | Are You Requesting a CWA (Yes or No)? If No, provide an anticipated date the agency plans to submit invoice for the remaining balance | Reason for Delay | Please Provide a 2-3 Sentence Explanation Identifying Any Impediments to Completion | What are the Consequences if CWA is Not Approved? (Please Provide a 2-3 Sentence Explanation) | Local Agency Contact Name | Local Agency Contact Phone Number | Local Agency Contact Email | Approved by DOF (Yes or No)? | Revised Reversion Date
07 | Los Angeles | Pedestrian and Bike Path | 7 miles of pedestrian and cyclist improvements within the heart of the Canoga Park community connecting DAC residents with local destination | ATPL | 5006(918) | 0721000261 | 5862 | Z3E1 | 3567000 | 2251929.68 | 1315070.32 | 2026-06-30
07 | Los Angeles | Pedestrian & Cyclist Safety Project | 2nd St on the North; Los Angeles River to the East; 7th St to the South; Alameda St to the West.and LA River on the west. | ATPL | 5006(864) | 0717000302 | 5286 | Y301 | 837132 | 820389.36 | 16742.64 | 2026-09-30
07 | Los Angeles | Pedestrian & Cyclist Safety Project | 2nd St on the North; Los Angeles River to the East; 7th St to the South; Alameda St to the West.and LA River on the west. | ATPL | 5006(864) | 0717000302 | 5286 | Y301 | 11462868 | 3849577.42 | 7613290.58 | 2026-09-30
07 | San Fernando | 12-foot wide, 1.34 mile long class 1 Bike/Pedestrian path, at grade crossings, lighting,fencing,sig | At Pacoima Wash access Road from Fourth Street (Bradley) Avenue to English Street (Eight Street) National Park. | ATPL | 5202(020) | 0721000072 | 5334 | Z300 | 1000 | 391.5 | 608.5 | 2026-09-30
07 | San Fernando | 12-foot wide, 1.34 mile long class 1 Bike/Pedestrian path, at grade crossings, lighting,fencing,sig | At Pacoima Wash access Road from Fourth Street (Bradley) Avenue to English Street (Eight Street) National Park. | ATPL | 5202(020) | 0721000072 | 5334 | Z300 | 972000 | 923232.6 | 48767.4 | 2026-09-30

## District 8
ATP Projects with Lapsing Federal Funds
Reversion Date: | 2026-06-30
Appropriation/Item Number: | 2660-108-0890
Year of Appropriation: | 2021
Appropriation Unit: | 21108F
District | Parties to Agreement (Agency) | Purpose of Project (Work Description) | Scope (Location) | Prefix | Federal Project Id | Advantage Project Id | PPNO | Federal Program Code | Budgeted Amount | Expenditure Amount | Remaining Balance | CTC TUF Deadline | Is Project Consistent with Original Scope and Purpose of the Appropriation? If No, Please Explain: | Are You Requesting a CWA (Yes or No)? If No, provide an anticipated date the agency plans to submit invoice for the remaining balance | Reason for Delay | Please Provide a 2-3 Sentence Explanation Identifying Any Impediments to Completion | What are the Consequences if CWA is Not Approved? (Please Provide a 2-3 Sentence Explanation) | Local Agency Contact Name | Local Agency Contact Phone Number | Local Agency Contact Email | Approved by DOF (Yes or No)? | Revised Reversion Date
08 | San Bernardino County | Class 1 bike path | Santa Ana River Trail from Waterman Avenue in San Bernardino to the California Street alignment, Phase III | STPLER | 5954(083) | 0800000818 | 1278 | Z301 | 1105000 | 1020775.63 | 84224.37 | 2026-10-31
08 | Hemet | Bike Path | Palm Ave, Whittier Ave, Johnston Ave, Gilbert St, Chambers St, and State St. | ATPSB1L | 5186(018) | 819000032 | 1212A | Y300 | 176175 | 159246.65 | 16928.35 | 2026-12-14
08 | Hemet | Bike Path | Palm Ave, Whittier Ave, Johnston Ave, Gilbert St, Chambers St, and State St. | ATPSB1L | 5186(018) | 0819000032 | 1212A | Y300 | 1813825 | 1790753.35 | 23071.65 | 2026-12-14
Note on J9: Leslie Avila ¦ DLA OSP Program Support-TUF Branch: Per LP2000 finance letter approved 07/31/25: Y300: $159,246.65 (CE)
Note on J10: Leslie Avila ¦ DLA OSP Program Support-TUF Branch: Budget (40) has not been updated to capture current finance letter. Per LP2000 finance letter approved 07/31/25: Y300: $1,830,753.35 (CON)

## District 12
ATP Projects with Lapsing Federal Funds
Reversion Date: | 2026-06-30
Appropriation/Item Number: | 2660-108-0890
Year of Appropriation: | 2021
Appropriation Unit: | 21108F
District | Parties to Agreement (Agency) | Purpose of Project (Work Description) | Scope (Location) | Prefix | Federal Project Id | Advantage Project Id | PPNO | Federal Program Code | Budgeted Amount | Expenditure Amount | Remaining Balance | CTC TUF Deadline | Is Project Consistent with Original Scope and Purpose of the Appropriation? If No, Please Explain: | Are You Requesting a CWA (Yes or No)? If No, provide an anticipated date the agency plans to submit invoice for the remaining balance | Reason for Delay | Please Provide a 2-3 Sentence Explanation Identifying Any Impediments to Completion | What are the Consequences if CWA is Not Approved? (Please Provide a 2-3 Sentence Explanation) | Local Agency Contact Name | Local Agency Contact Phone Number | Local Agency Contact Email | Approved by DOF (Yes or No)? | Revised Reversion Date
12 | Santa Ana | Bulb-outs and reconstruct ADA-compliant curb ramps, sidewalk, and driveways | Along neighborhood streets adjacent to Davis Elementary School; 14th, 15th, French, and Poinsettia Streets and Penn Way | ATPSB1L | 5063(193) | 1219000021 | 2190 | Y301 | 580000 | 316823.68 | 263176.32 | 2025-12-31
12 | Santa Ana | Bulb-outs and reconstruct ADA-compliant curb ramps, sidewalk, and driveways | Along neighborhood streets adjacent to Davis Elementary School; 14th, 15th, French, and Poinsettia Streets and Penn Way | ATPSB1L | 5063(193) | 1219000021 | 2190 | Z30E | 4254000 | 3932453.22 | 321546.78 | 2025-12-31
12 | Santa Ana | Install median, parking-protected bicycle lanes, and dedicated bicycle signal heads | Willits Street from Fairview Street to E/S of Raitt Street | ATPSB1L | 5063(195) | 1219000022 | 2189 | Y301 | 2007000 | 1912050 | 94950 | 2026-03-31

## Drop-down Reference Tables
Within Scope? | Need a CWA? | Primary Reason For Delay:
YES | YES | Design: Change in scope.
NO | NO | Design: Change in specifications.
Design: Change in site conditions.
Environmental: Change in scope requires additional studies/permits.
Environmental: Excessive study or opinion review time by external agencies.
Environmental: Permits expired.
Environmental: Environmental document determination revalidation required.
Environmental: Mitigation for project impacts period.
Right of Way and Utility Relocation: Change in scope/number of parcels/utility relocations required.
Right of Way and Utility Relocation: Condemnation/eminent domain proceedings.
Right of Way and Utility Relocation: Utility owner dispute.
Right of Way and Utility Relocation: Qualified Buy America purchase/delivery delays.
Construction: Contract award disputed/cancelled, rebid or complete under force account.
Construction: Change in site conditions.
Construction: Qualified Buy America purchase/delivery delays.
Construction: Extended winter suspension affecting delivery schedule.
Contract Dispute/Litigation: Post-construction claim. Informal settlement.
Contract Dispute/Litigation: Formal litigation proceeding.
Finance: CTC approved Time Extension conflicts with reversion date.
Finance: Indirect Cost Rate Proposal (ICRP) request package returned with errors.
Finance: Change in dedicated/programmed funding.
Finance: Pending programming.
OTHER-declared disaster (explain):
OTHER (explain):