## District 1
Projects with Lapsing Federal Funds
Reversion Date: | 2026-06-30
Appropriation/Item Number | 2660-102-0890
Year of Appropriation: | 2021
Appropriation Unit: | 21102F
District | Parties to Agreement (Agency) | Purpose of Project (Work Description) | Scope (Location) | Prefix | Federal Id | Advantage Project Id | Federal Program Code | Budgeted Amount | Expenditure Amount | Remaining Balance | Federal Financial Deadline. This deadline will supercede the CWA deadline if approved. Invoices due 8/15/2026. | Is Project Consistent with Original Scope and Purpose of the Appropriation? If No, Please Explain: | Are You Requesting a CWA (Yes or No)? If No, provide an anticipated date the agency plans to submit invoice for the remaining balance | Reason for Delay | Please Provide a 2-3 Sentence Explanation Identifying Any Impediments to Completion | What are the Consequences if CWA is Not Approved? (Please Provide a 2-3 Sentence Explanation) | Local Agency Contact Name | Local Agency Contact Phone Number | Local Agency Contact Email | Approved by DOF (Yes or No)? | Revised Reversion Date
01 | Lake County | Restoration | On Hill Road PM 7.70 to 7.80 PR | ER | 28C1(003) | 0118000084 | ER11 | 141648 | 29970.35 | 111677.65
01 | Del Norte County | Restoration | Pebble Beach Dr | ER | 32D0(009) | 0117000125 | ER11 | 448762.54 | 355150.25 | 93612.29
01 | Humboldt County | Restoration | Bell Springs Rd PM 2.20 | ER | 32L0(127) | 0117000303 | ER12 | 117685.73 | 0 | 117685.73
01 | Humboldt County | Restoration | Bell Springs Rd PM 2.20 | ER | 32L0(127) | 0117000303 | ER14 | 50813.42 | 896.06 | 49917.36
01 | Humboldt County | Restoration | Elk Creek Road PM 0.95/2.42 | ER | 32L0(237) | 0117000314 | ER12 | 317716.46 | 315110.77 | 2605.69
01 | Humboldt County | Restoration | Mattole Road PM 13.66/13.68 | ER | 32L0(252) | 0117000329 | ER12 | 227318.48 | 189333.08 | 37985.4
01 | Del Norte County | Bridge Replacement | Hunter Creek Bridge on Requa Road 0.1 mile west of SR-101 near Klamath, CA | BRLO | 5901(044) | 0100020389 | Z2E3 | 220000 | 45689.39 | 174310.61
01 | Mendocino County | Seismic Retrofit, Bridge Rehablitation | Eureka Hill Road, CR505, MP 4.92, Br,.No. 10C-0034 | BRLRT | 5910(041) | 0100000010 | Z2E3 | 35000 | 31604.08 | 3395.92
01 | Mendocino County | Bridge Replacement | Hill Road Bridge over Mill Creek (Bridge # 10C0111) | BRLO | 5910(084) | 0100020405 | M2E3 | 95000 | 66003.22 | 28996.78
01 | Lake County | AC Overlay / Roadway Rehabilitation and bike lanes construction project | South Main Street from the Lakeport City Limits to the SR 175 extension. | RPSTPLE | 5914(042) | 0100000054 | LY10 | 811770.08 | 562483.48 | 249286.6
01 | Lake County | AC Overlay / Roadway Rehabilitation and bike lanes construction project | South Main Street from the Lakeport City Limits to the SR 175 extension. | RPSTPLE | 5914(042) | 0100000054 | Z906 | 34298 | 1225.41 | 33072.59 | 9/30/2027
01 | Lake County | AC Overlay / Road Rehabilitation and construct bike lanes project | Soda Bay Road from the SR 175 extension to Manning Creek. | RPSTPLE | 5914(043) | 0100000055 | LY10 | 298189.59 | 123523.22 | 174666.37
01 | Lake County | Bridge Replacement | Chalk Mountain Road Bridge over North Fork Cache Creek, in spring Valley Lake Dev. (Bridge # 14C0048) | BRLO | 5914(094) | 0114000023 | Z2E3 | 90000 | 12808.34 | 77191.66
01 | Lake County | Bridge Replacement | Wolf Creek Road over Wolf Creek | BRLO | 5914(095) | 0114000024 | Z233 | 50000 | 23204.97 | 26795.03
01 | Lake County | Bridge Replacement | Bartlett Springs Road Bridge over Bartlett Creek (Bridge No. 14C0099) | BRLO | 5914(111) | 0117000017 | Z2E3 | 20000 | 11294.39 | 8705.61

## District 2
Projects with Lapsing Federal Funds
Reversion Date: | 2026-06-30
Appropriation/Item Number | 2660-102-0890
Year of Appropriation: | 2021
Appropriation Unit: | 21102F
District | Parties to Agreement (Agency) | Purpose of Project (Work Description) | Scope (Location) | Prefix | Federal Id | Advantage Project Id | Federal Program Code | Budgeted Amount | Expenditure Amount | Remaining Balance | Federal Financial Deadline. This deadline will supercede the CWA deadline if approved. Invoices due 8/15/2026. | Is Project Consistent with Original Scope and Purpose of the Appropriation? If No, Please Explain: | Are You Requesting a CWA (Yes or No)? If No, provide an anticipated date the agency plans to submit invoice for the remaining balance | Reason for Delay | Please Provide a 2-3 Sentence Explanation Identifying Any Impediments to Completion | What are the Consequences if CWA is Not Approved? (Please Provide a 2-3 Sentence Explanation) | Local Agency Contact Name | Local Agency Contact Phone Number | Local Agency Contact Email | Approved by DOF (Yes or No)? | Revised Reversion Date
02 | Modoc County | Road Rehabilitation | County Road 111 in Modoc County from SR139 Northward to County Road 108 (State Line Road), East of Tulelake | RPSTPL | 5903(063) | 0219000160 | Z907 | 35401 | 1691.51 | 33709.49 | 9/30/2027
02 | Modoc County | Road Rehabilitation | County Road 111 in Modoc County from SR139 Northward to County Road 108 (State Line Road), East of Tulelake | RPSTPL | 5903(063) | 0219000160 | Z912 | 10278 | 0 | 10278 | 9/30/2028
02 | Modoc County | Road Rehabilitation | County Road 111 in Modoc County from SR139 Northward to County Road 108 (State Line Road), East of Tulelake | RPSTPL | 5903(063) | 0219000160 | Z921 | 8377 | 0 | 8377 | 9/30/2029
02 | Shasta County | Bridge Rehabilitation | Parkville Road over Ash Creek, 3.4 mi. south of Dersch Road. Bridge No. 06C0220. | BRLO | 5906(117) | 0214000046 | M233 | 40000 | 25000 | 15000
02 | Plumas County | Bridge Painting | Belden Town Road Bridge (09C-0042), C.R. 303, 0.05 miles s/o SR 70 at Belden in the Feather River Canyon. | BRLO | 5909(092) | 0200020311 | Z2E3 | 48000 | 7920.91 | 40079.09
02 | Plumas County | Bridge Replacement | Chester-Warner Valley Rd., CR 312 (Bridge 09C0067) over Warner Creek, 13.4 mi, n/o SR 36 in Chester | BRLO | 5909(097) | 0200020249 | Z2E3 | 40000 | 36321.63 | 3678.37

## District 3
Projects with Lapsing Federal Funds
Reversion Date: | 2026-06-30
Appropriation/Item Number | 2660-102-0890
Year of Appropriation: | 2021
Appropriation Unit: | 21102F
District | Parties to Agreement (Agency) | Purpose of Project (Work Description) | Scope (Location) | Prefix | Federal Id | Advantage Project Id | Federal Program Code | Budgeted Amount | Expenditure Amount | Remaining Balance | Federal Financial Deadline. This deadline will supercede the CWA deadline if approved. Invoices due 8/15/2026. | Is Project Consistent with Original Scope and Purpose of the Appropriation? If No, Please Explain: | Are You Requesting a CWA (Yes or No)? If No, provide an anticipated date the agency plans to submit invoice for the remaining balance | Reason for Delay | Please Provide a 2-3 Sentence Explanation Identifying Any Impediments to Completion | What are the Consequences if CWA is Not Approved? (Please Provide a 2-3 Sentence Explanation) | Local Agency Contact Name | Local Agency Contact Phone Number | Local Agency Contact Email | Approved by DOF (Yes or No)? | Revised Reversion Date
03 | Paradise | Restoration | Neal Rd within limits of the Town of Paradise. DAF 009 replaces ineligible DAF 008. | ER | 38Y0(025) | 0320000105 | ER12 | 107607.5 | 106935.1 | 672.4
03 | Sacramento | Replace existing five lane bridge with a new five lane bridge | Auburn Bl over Arcade Creek at Winding Way | BRLS | 5002(168) | 0313000315 | Z0E1 | 404624 | 337126.65 | 67497.35
03 | Sacramento | Restripe and realign approaches, install pedestrian refuge island and enhanced pedestrian crossings | Intersection of Lampasas Boulevard and Rio Linda Avenue. | HSIPL | 5002(212) | 0319000104 | Z23E | 424000 | 211263.64 | 212736.36
03 | Sacramento | Bridge Related - Long Term Mitigation | Rio Linda Boulevard at Magpie Creek ~1.0 north of I80 | BRLS | 5002(220) | 0321000051 | Z001 | 132795 | 73382.45 | 59412.55
03 | Sacramento | New Signals | In Sacramento, (1) 16th St. at D St. (2) Franklin Blvd. at 36th Ave. (3) Freeport Blvd. at Kitchner Rd. (4) Fruitridge Rd. at 60th St. (5) Rio Linda Blvd. at Harris Ave. (6) Stockon Blvd. at 11th Ave. (7) 24th St. at 25th St. (8) Munroe St. at Latham Dr. (9) Rio Linda Blvd. at Roanoke Ave.: Install traffic signals. | STPL | 5002(221) | 0321000081 | Z23E | 796000 | 768464.31 | 27535.69
03 | Sacramento | Build a multi-use trail to close the gap in the existing trail | In Sacramento, adjacent to the Sacramento River, on top of the levee from Garcia Bend Park to Arabella Way (Phase 1) | STPCML | 5002(222) | 0321000089 | Z40E | 1550000 | 907397.95 | 642602.05
03 | Sacramento | Signalize both intersections,construct bulb-outs, interconnect the signals with light rail operation | In Sacramento, on R Street at the 29th Street and 30th Street intersections | STPL | 5002(224) | 0321000112 | Z24E | 561677 | 253599.28 | 308077.72
03 | Chico | Synchronizing four roundabouts, bike & ped improvements | Hegan Lane Business Park District. Park Ave. & Midway, Park Ave. & Fair St., Hegan Lane & Midway, Hagan & Otterson Dr. | HIPCML | 5037(040) | 0321000153 | Z006 | 570696 | 81606.52 | 489089.48 | 9/30/2026
03 | Chico | Synchronizing four roundabouts, bike & ped improvements | Hegan Lane Business Park District. Park Ave. & Midway, Park Ave. & Fair St., Hegan Lane & Midway, Hagan & Otterson Dr. | HIPCML | 5037(040) | 0321000153 | Z40E | 791791 | 113151.88 | 678639.12
03 | Chico | Synchronizing four roundabouts, bike & ped improvements | Hegan Lane Business Park District. Park Ave. & Midway, Park Ave. & Fair St., Hegan Lane & Midway, Hagan & Otterson Dr. | HIPCML | 5037(040) | 0321000153 | Z906 | 804070 | 114866.3 | 689203.7 | 9/30/2027
03 | Chico | Synchronizing four roundabouts, bike & ped improvements | Hegan Lane Business Park District. Park Ave. & Midway, Park Ave. & Fair St., Hegan Lane & Midway, Hagan & Otterson Dr. | HIPCML | 5037(040) | 0321000153 | Z911 | 233443 | 33259.8 | 200183.2 | 9/30/2028
03 | Woodland | Road diet, buffered bike lanes, ADA upgrades, transit and traffic signal improvements project | West Gibson Road, from West Street to County Road 98. | ATPSB1L | 5046(046) | 0320000038 | Z23E | 1765293 | 1654111.66 | 111181.34
03 | Woodland | Road diet, buffered bike lanes, ADA upgrades, transit and traffic signal improvements project | West Gibson Road, from West Street to County Road 98. | ATPSB1L | 5046(046) | 0320000038 | Z40E | 1234707 | 866850.49 | 367856.51
03 | Woodland | Road diet, buffered bike lanes, ADA upgrades, transit and traffic signal improvements project | West Gibson Road, from West Street to County Road 98. | ATPSB1L | 5046(046) | 0320000038 | ZS3E | 216000 | 154034.11 | 61965.89
03 | Orland | Install pedestrian countdown signal heads w/accessible pedestrian system buttons, pavement markings | On Walker Street/SR32 at various intersections | HSIPL | 5185(008) | 0319000097 | ZS3E | 202400 | 124153.45 | 78246.55
03 | Folsom | Construct 4 Lane Interchange | US-50 at Empire Ranch Road | HPLULN | 5288(043) | 0318000300 | Z007 | 140513 | 0 | 140513 | 9/30/2026
03 | Folsom | Construct 4 Lane Interchange | US-50 at Empire Ranch Road | HPLULN | 5288(043) | 0318000300 | Z24E | 844596 | 48835.9 | 795760.1
03 | Folsom | Construct 4 Lane Interchange | US-50 at Empire Ranch Road | HPLULN | 5288(043) | 0318000300 | Z906 | 1176179 | 0 | 1176179 | 9/30/2027
03 | Folsom | Construct 4 Lane Interchange | US-50 at Empire Ranch Road | HPLULN | 5288(043) | 0318000300 | Z910 | 246105 | 0 | 246105 | 9/30/2028
03 | Folsom | Construct 4 Lane Interchange | US-50 at Empire Ranch Road | HPLULN | 5288(043) | 0318000300 | Z911 | 57477 | 0 | 57477 | 9/30/2028
03 | Folsom | Construct 4 Lane Interchange | US-50 at Empire Ranch Road | HPLULN | 5288(043) | 0318000300 | Z920 | 35130 | 0 | 35130 | 9/30/2029
03 | Glenn County | Bridge Replacement | County Road 200A at Stony Creek Brd. #11C-245 | BHLO | 5911(031) | 0300000794 | Z233 | 300000 | 182212.06 | 117787.94
03 | Glenn County | Bridge Replacement | Co.Rd. 305 at Watson Creek near Grindstone Br. No. 11C-91 | BRLO | 5911(056) | 0313000286 | Z007 | 72950 | 1229.08 | 71720.92 | 9/30/2026
03 | Butte County | Bridge Replacement | East Rio Bonito Road at Hamilton Slough ~0.2 miles East of SR 99 | BRLS | 5912(091) | 0300020628 | Z2E3 | 50000 | 10953.89 | 39046.11
03 | Butte County | Bridge Replacement | East Rio Bonito Road at Sutter Buttes Slough ~0.8 miles East of SR 99 | BRLO | 5912(093) | 0300020679 | Z2E3 | 190000 | 161685.06 | 28314.94
03 | Yuba County | Bridge Replacement | Waldo Road at Dry Creek 1.9 miles South of Smartville Road | BRLO | 5916(092) | 0300020705 | Z2E3 | 71000 | 31000 | 40000
03 | Placer County | Construct new roundabout | SR 267 / SR 28 Intersection, Kings Beach Western Approach | STPL | 5919(136) | 0318000149 | Z23E | 675000 | 438233.03 | 236766.97
03 | Yolo County | Replace existing structurally deficient 2-lane bridge with a new 2-lane bridge | County Road 41 at Cache Creek (Rumsey Bridge) ~0.1 miles East of State Highway 16 | BRLO | 5922(077) | 0300020702 | M233 | 105000 | 35987.23 | 69012.77
03 | Sacramento County | Bridge Replacement | Michigan Bar Road at Consumnes River 1.2 Miles North of S.R. 16. | BRLO | 5924(175) | 0300020692 | Z2E3 | 360000 | 55167.52 | 304832.48
03 | Sacramento County | Road widening with bike/ped facilities | Madison Ave from Sunrise to Hazel | CML | 5924(252) | 0319000250 | Z23E | 358776 | 258613.37 | 100162.63
03 | El Dorado County | Replace existing functionally obsolete 2-lane bridge with a new 2-lane bridge | Green Valley Rd over Indian Creek 0.9 miles north of Greenstone Rd | BRLS | 5925(096) | 0300020724 | Z0E1 | 192995 | 156995 | 36000
03 | El Dorado County | Bridge Replacement | Green Valley Road at Mounds Springs Creek ~0.8 miles West of Missouri Flat Road | BRLS | 5925(112) | 0312000205 | Z0E1 | 192995 | 154995 | 38000

## District 4
Projects with Lapsing Federal Funds
Reversion Date: | 2026-06-30
Appropriation/Item Number | 2660-102-0890
Year of Appropriation: | 2021
Appropriation Unit: | 21102F
District | Parties to Agreement (Agency) | Purpose of Project (Work Description) | Scope (Location) | Prefix | Federal Id | Advantage Project Id | Federal Program Code | Budgeted Amount | Expenditure Amount | Remaining Balance | Federal Financial Deadline. This deadline will supercede the CWA deadline if approved. Invoices due 8/15/2026. | Is Project Consistent with Original Scope and Purpose of the Appropriation? If No, Please Explain: | Are You Requesting a CWA (Yes or No)? If No, provide an anticipated date the agency plans to submit invoice for the remaining balance | Reason for Delay | Please Provide a 2-3 Sentence Explanation Identifying Any Impediments to Completion | What are the Consequences if CWA is Not Approved? (Please Provide a 2-3 Sentence Explanation) | Local Agency Contact Name | Local Agency Contact Phone Number | Local Agency Contact Email | Approved by DOF (Yes or No)? | Revised Reversion Date
04 | San Jose | Implement Safety Elements | Tully Road between Monterey Road and Swift Lane | CML | 5005(155) | 0419000080 | Z23E | 6975360 | 5949723.82 | 1025636.18
04 | San Jose | Implement Safety Improvements | West San Carlos Street between I-880 and McEvoy Street | CML | 5005(162) | 0420000042 | Z003 | 2618000 | 1198472.77 | 1419527.23
04 | Santa Rosa | Bicycle and Pedestrian Bridge | Over Highway 101 in the vicinity of the Santa Rosa Junior College and the Coddingtown Mall | CML | 5028(083) | 0420000357 | Z0E3 | 1782000 | 1746000 | 36000
04 | Vacaville | Bridge Replacement | Aldridge Rd. Bridge over Putah South Canal, Br. No. 23C0236 | BRLO | 5094(065) | 0416000110 | Z2E3 | 223188 | 61409.56 | 161778.44
04 | Palo Alto | Replace existing two-lane bridge with new two-lane bridge to current standards. | Bridge 37C0223 Newell Road over San Francisquito Creek | BRLS | 5100(017) | 0400020982 | Z0E1 | 608330 | 602759.47 | 5570.53
04 | Pittsburg | Improve Signal Hardware (Heads, Backplates, Controllers, Modems, Cabinets, Etc) and Improve Timing | Various Locations Throughout the City of Pittsburg | HSIPL | 5127(037) | 0420000011 | ZS3E | 878400 | 730959.44 | 147440.56
04 | San Anselmo | Bridge Replacement | Nokomis Avenue Bridge over San Anselmo Creek in the Town of San Anselmo | BRLO | 5159(017) | 0412000653 | Z2E3 | 95400 | 75201.46 | 20198.54
04 | San Anselmo | Bridge Replacement | Madrone Ave Bridge over San Anselmo Creek in the Town of San Anselmo | BRLO | 5159(018) | 0412000654 | Z0E1 | 84457.62 | 67366.93 | 17090.69
04 | Larkspur | Bridge Rehabilitation | Bon Air Bridge; bet Eliseo/Bon Air intersection and magnolia/Bon Air intersection. Bon Air bridge spans Corte Madera Creek. | BHLS | 5166(015) | 0400001287 | Z0E1 | 3874156.35 | 3679643.34 | 194513.01
04 | Moraga | Bridge Replacement | Canyon Road Bridge (Br. No. 28C0137) over West Branch San Leandro Creek | BRLS | 5415(011) | 0414000270 | Q100 | 170862.25 | 0 | 170862.25
04 | Moraga | Bridge Replacement | Canyon Road Bridge (Br. No. 28C0137) over West Branch San Leandro Creek | BRLS | 5415(011) | 0414000270 | Z0E1 | 133676.75 | 0 | 133676.75
04 | Sonoma County | Bridge Replacement | Bridge No.# 20C0005, Geysers Road Bridge | STPLZ | 5920(111) | 0400002058 | Z2E3 | 541303 | 418310.42 | 122992.58
04 | Sonoma County | Mitigation Planting | Hauser Br. Rd (Br. 20C0240) Replacement (BRLO-5920(125)) | BRLO | 5920(177) | 0421000049 | Z233 | 320653 | 198894.1 | 121758.9
04 | Sonoma County | Environmental Mitigation Child Project for Parent Bridge Replacement Project STPLZ-5920(059) | Boyes Blvd over Sonoma Creek Bridge 20C0262 | STPLZ | 5920(178) | 0421000206 | L1CE | 124650 | 3299.01 | 121350.99
04 | Solano County | Interchange Improvements | I-80/Redwood Rd.and SR 37/Fairgrounds Drive Interchanges, Phase 1 | HPLUL | 5923(122) | 0419000146 | RPS3 | 427693 | 328475.53 | 99217.47
04 | Contra Costa County | Construct new 2-ln Bridge adjacent to existing bridge and demolish existing bridge | 14102F replenished, not eligible for a CWA. DB Byron Hwy 1.4 miles Northwest of Alameda County Line | BRLS | 5928(104) | 0400020300 | Z0E1 | 3828923 | 1223701.49 | 2605221.51
04 | San Francisco County | Roadway Improvements | Market Street between 5th Street and 8th Street | BUILDL | 5934(185) | 0420000265 | Z23E | 3366000 | 2946803.57 | 419196.43
04 | Santa Clara County | Bridge Replacement | Llagas Creek Bridge (#37C-0096) on Uvas Road | BRLO | 5937(106) | 0400001407 | Z0E1 | 407238 | 370580.04 | 36657.96
04 | Golden Gate Bridge, Highway And Transportation | Bridge Rehabilitation - Construct Physical Suicide Deterrent System | Bridge Rehabilitation - Construct Physical Suicide Deterrent System | BRLS | 6003(051) | 0415000067 | Z230 | 231855 | 231854.99 | 0.01
04 | Metropolitan Transportation Commission | Planning and implementation of various multi-modal operational policies | SF Bay Area: Regionwide | STPLNI | 6084(226) | 0418000246 | Z23E | 9687000 | 8021746.14 | 1665253.86
04 | Metropolitan Transportation Commission | Corridor Operational Performance Study (Before and After) | I-880 Express Lanes in Alameda County | STPL | 6084(273) | 0422000013 | Z23E | 900000 | 788837.07 | 111162.93
04 | San Francisco County Transportation Authority | Build new two-way Class I ADA compliant pedestrian and bicycle connections | On Yerba Buena Island along Hillcrest Rd and Treasure Island Rd. | STPL | 6272(053) | 0422000027 | Z23E | 1000000 | 833407.52 | 166592.48

## District 5
Projects with Lapsing Federal Funds
Reversion Date: | 2026-06-30
Appropriation/Item Number | 2660-102-0890
Year of Appropriation: | 2021
Appropriation Unit: | 21102F
District | Parties to Agreement (Agency) | Purpose of Project (Work Description) | Scope (Location) | Prefix | Federal Id | Advantage Project Id | Federal Program Code | Budgeted Amount | Expenditure Amount | Remaining Balance | Federal Financial Deadline. This deadline will supercede the CWA deadline if approved. Invoices due 8/15/2026. | Is Project Consistent with Original Scope and Purpose of the Appropriation? If No, Please Explain: | Are You Requesting a CWA (Yes or No)? If No, provide an anticipated date the agency plans to submit invoice for the remaining balance | Reason for Delay | Please Provide a 2-3 Sentence Explanation Identifying Any Impediments to Completion | What are the Consequences if CWA is Not Approved? (Please Provide a 2-3 Sentence Explanation) | Local Agency Contact Name | Local Agency Contact Phone Number | Local Agency Contact Email | Approved by DOF (Yes or No)? | Revised Reversion Date
05 | Pismo Beach | Emergency Opening and Restoration | Ocean Boulevard between Morro and Cuyama Ave | ER | 32L0(040) | 0517000129 | ER11 | 2278121 | 2258270.4 | 19850.6
05 | Santa Barbara | Add Segment Lighting & Install Protected Left Turn Phase | Carillo St (between Miramonte Dr to Bath St) & Miramonte St ( between Carrillo St and Bel Monte Dr) in the City of Santa Barbara | HSIPL | 5007(077) | 0517000149 | ZS3E | 1684800 | 1523795.27 | 161004.73
05 | Santa Barbara | Mitigation and Monitoring | Quinientos Bridge 51C0285 over Sycamore Creek in Santa Barbara | BRLS | 5007(091) | 0520000085 | Z2E3 | 130000 | 3982.37 | 126017.63
05 | El Paso De Robles | Bridge Replacement | 24th St Bridge - Br. No. 49C-0357 | BHLS | 5084(017) | 0516000068 | Z0E1 | 982636 | 218432.36 | 764203.64
05 | Arroyo Grande | Plant Establishment (Long-Term Post-Construction Environmental Mitigation & Monitoring) | Bridge St bridge (Br. No. 49C-0196) | BHLO | 5199(032) | 0520000017 | Z23E | 176000 | 117720.32 | 58279.68
05 | Santa Cruz County | Bridge Replacement 36C-0085 replace a one lane- off system low volume road | San Lorenzo Way over San Lorenzo River 36c-0087 | BRLO | 5936(086) | 0500020120 | Z2E3 | 500000 | 480779.43 | 19220.57
05 | Santa Cruz County | Guardrail | La Madrona, El Rancho and Swanton roads | HSIPL | 5936(135) | 0518000145 | ZS3E | 977113 | 40183.41 | 936929.59
05 | Santa Cruz County | Emergency Opening and Restoration | Glenwood Cutoff PM 0.02 | ER | 32L0(005) | 0517000103 | ER12 | 102851 | 92274.15 | 10576.85
05 | Santa Cruz County | Emergency Opening and Restoration | Bear Creek PM 2.12 | ER | 32L0(050) | 0517000139 | ER12 | 489951 | 439667.27 | 50283.73
05 | Santa Cruz County | Emergency Opening and Restoration | Hazel Dell Road PM 2.16 | ER | 32L0(067) | 0517000158 | ER12 | 236352.53 | 9216.04 | 227136.49
05 | Santa Cruz County | Emergency Opening and Restoration | Hazel Dell Road PM 2.16 | ER | 32L0(067) | 0517000158 | ER14 | 74333.39 | 0 | 74333.39
05 | Santa Cruz County | Emergency Opening and Restoration | Hazel Dell Road PM 2.16 | ER | 32L0(067) | 0517000158 | Z9W0 | 1624.78 | 0 | 1624.78
05 | Santa Cruz County | Emergency Opening and Restoration | Hazel Dell Road PM 2.21 | ER | 32L0(069) | 0517000160 | ER12 | 1138747 | 788375.39 | 350371.61
05 | Santa Cruz County | Emergency Opening and Restoration | Granite Creek Road PM 0.47 | ER | 32L0(071) | 0517000162 | ER12 | 50283 | 860.59 | 49422.41
05 | Santa Cruz County | Emergency Opening and Restoration | Browns Valley Rd pm 2.14 | ER | 32L0(081) | 0517000180 | ER14 | 0.32 | 0 | 0.32
05 | Santa Cruz County | Emergency Opening and Restoration | Hazel Dell Rd PM 2.08 | ER | 32L0(097) | 0517000199 | ER14 | 1370819 | 1222779.41 | 148039.59
05 | Santa Cruz County | Emergency Opening and Restoration | Hazel Dell PM 2.37 | ER | 32L0(106) | 0517000211 | ER10 | 155173.43 | 85047.96 | 70125.47
05 | Santa Cruz County | Emergency Opening and Restoration | Hazel Dell PM 2.37 | ER | 32L0(106) | 0517000211 | ER11 | 154929.47 | 154586.93 | 342.54
05 | Santa Cruz County | Emergency Opening and Restoration | Hazel Dell PM 2.37 | ER | 32L0(106) | 0517000211 | ER12 | 666481.8 | 282519.69 | 383962.11
05 | Santa Cruz County | Emergency Opening and Restoration | Hazel Dell PM 2.37 | ER | 32L0(106) | 0517000211 | ER14 | 186.67 | 0 | 186.67
05 | Santa Cruz County | Emergency Opening and Restoration | Hazel Dell PM 2.37 | ER | 32L0(106) | 0517000211 | Z9W0 | 39656.05 | 0 | 39656.05
05 | Santa Cruz County | Emergency Opening and Restoration | Hazel Dell Road PM 2.13 | ER | 32L0(149) | 0517000212 | ER12 | 511831 | 355576.4 | 156254.6
05 | Santa Cruz County | Emergency Opening and Restoration | Mt Madonna Rd Pm 0.96 | ER | 32L0(263) | 0517000238 | ER14 | 28940 | 25753.56 | 3186.44
05 | Santa Cruz County | Emergency Opening and Restoration | Hazel Dell Road PM 2.58 | ER | 32L0(337) | 0518000016 | ER12 | 424944 | 398137.98 | 26806.02
05 | Santa Cruz County | Emergency Opening and Restoration | Hazel Dell Road PM 2.58 | ER | 32L0(337) | 0518000016 | ER14 | 359344 | 280159.06 | 79184.94
05 | Monterey County | Bridge Replacement | Hartnell Road Bridge over Alisal Creek, 0.15mi south of Alisal Road. | BHLO | 5944(103) | 0500020138 | Z2E3 | 230500 | 225461.99 | 5038.01
05 | Santa Barbara County | Road Reconstruction | Hollister Ave in Santa Barbara County | HPLUL | 5951(158) | 0516000083 | LY10 | 101787.34 | 42856.25 | 58931.09

## District 6
Projects with Lapsing Federal Funds
Reversion Date: | 2026-06-30
Appropriation/Item Number | 2660-102-0890
Year of Appropriation: | 2021
Appropriation Unit: | 21102F
District | Parties to Agreement (Agency) | Purpose of Project (Work Description) | Scope (Location) | Prefix | Federal Id | Advantage Project Id | Federal Program Code | Budgeted Amount | Expenditure Amount | Remaining Balance | Federal Financial Deadline. This deadline will supercede the CWA deadline if approved. Invoices due 8/15/2026. | Is Project Consistent with Original Scope and Purpose of the Appropriation? If No, Please Explain: | Are You Requesting a CWA (Yes or No)? If No, provide an anticipated date the agency plans to submit invoice for the remaining balance | Reason for Delay | Please Provide a 2-3 Sentence Explanation Identifying Any Impediments to Completion | What are the Consequences if CWA is Not Approved? (Please Provide a 2-3 Sentence Explanation) | Local Agency Contact Name | Local Agency Contact Phone Number | Local Agency Contact Email | Approved by DOF (Yes or No)? | Revised Reversion Date
06 | Visalia | Reconstruct roadway install traffic signal interconnect, curb and gutter, and drain inlet | In City of Visalia, on Tulare Avenue from Demaree Street to Cotta Street | STPHIPL | 5044(134) | 0621000129 | M230 | 739386.94 | 247379.05 | 492007.89
06 | Visalia | Reconstruct roadway install traffic signal interconnect, curb and gutter, and drain inlet | In City of Visalia, on Tulare Avenue from Demaree Street to Cotta Street | STPHIPL | 5044(134) | 0621000129 | M23E | 500737.5 | 0 | 500737.5
06 | Visalia | Reconstruct roadway install traffic signal interconnect, curb and gutter, and drain inlet | In City of Visalia, on Tulare Avenue from Demaree Street to Cotta Street | STPHIPL | 5044(134) | 0621000129 | Z005 | 577501 | 0 | 577501 | 9/30/2026
06 | Visalia | Reconstruct roadway install traffic signal interconnect, curb and gutter, and drain inlet | In City of Visalia, on Tulare Avenue from Demaree Street to Cotta Street | STPHIPL | 5044(134) | 0621000129 | Z007 | 577765 | 0 | 577765 | 9/30/2026
06 | Visalia | Reconstruct roadway install traffic signal interconnect, curb and gutter, and drain inlet | In City of Visalia, on Tulare Avenue from Demaree Street to Cotta Street | STPHIPL | 5044(134) | 0621000129 | Z230 | 593609.56 | 39815.56 | 553794
06 | Fresno | Signal Synchronization, wireless communications, controllers, and cameras | Ashlan Avenue from Cornelia and Blackstone Avenues | CML | 5060(359) | 0619000127 | Z40E | 2037800 | 1351062.53 | 686737.47
06 | Fresno | Install adaptive ITS system, upgrade detection, and synchronize corridor | Friant Road from Shepherd Avenue to Copper River Drive | CML | 5060(379) | 0621000059 | Z40E | 220400 | 189222.53 | 31177.47
06 | Fresno | New Road | Veterans Blvd./SR99 Interchange (Phase 3) | BGFL | 5060(384) | 0621000108 | BDG3 | 10540582 | 9652671.98 | 887910.02 | 9/30/2026
06 | Selma | New Signals | Intersection of McCall Ave and Dinuba Ave | CML | 5096(040) | 0621000061 | Z40E | 105200 | 81793 | 23407
06 | Bakersfield | Road Related - Freeway Connector | Rt 58 / 99 Bakersfield Freeway Connector | PRNSL | 5109(245) | 0618000219 | LY40 | 2964439.38 | 2923439.1 | 41000.28
06 | Bakersfield | New Road: Construct new Centennial Corridor mainline and interchange and misc. related work. | Centennial Corridor connector: westside Parkway(WSP) at Kern River Br. to SR58 SR99 | NCIIPL | 5109(251) | 0619000038 | LY50 | 1671281.26 | 0 | 1671281.26
06 | Bakersfield | New Road: Construct new Centennial Corridor mainline and interchange and misc. related work. | Centennial Corridor connector: westside Parkway(WSP) at Kern River Br. to SR58 SR99 | NCIIPL | 5109(251) | 0619000038 | RPE3 | 381 | 0 | 381
06 | Bakersfield | New Road: Construct new Centennial Corridor mainline and interchange and misc. related work. | Centennial Corridor connector: westside Parkway(WSP) at Kern River Br. to SR58 SR99 | NCIIPL | 5109(251) | 0619000038 | Z24E | 44068.32 | 0 | 44068.32
06 | Bakersfield | Interconnect Signals and synchronization | Signal Coordination Part1: Along Truxtun Ave, H St, Oak St, Ming Ave, Hageman Rd, Coffee Rd, Chester Ave, 23rd St, and 24th St | CML | 5109(268) | 0621000098 | Z40E | 1593539 | 1304006.99 | 289532.01
06 | Bakersfield | Traffic signals communication | New Stine Rd between Panama Lane and Mohawk St & Calloway Dr between White Ln and Brimhall Rd | CML | 5109(269) | 0621000100 | Z400 | 531180 | 393413.12 | 137766.88
06 | Coalinga | Construct Class I paved multi-use trail | Phelps Ave. from Posa Chanet to Gregory Way, Southside of Los Gatos Creek from Elm Ave to former railroad corridor, Northside of Cambridge Avenue. from Monterey Ave to E/O Sunset St., and Northside of Coalinga Sports Complex fro E/O Sunset St. to Elm Ave. | CML | 5146(026) | 0620000109 | Z40E | 192287 | 186846.35 | 5440.65
06 | Madera | Bridge Preventative Maintenance Program | PM00133 Citywide BPMP Project Locations. BPMP work on bridges 41C0009 and 41C0043 (& 41C0155 for initial PE then stand alone) | BPMP | 5157(104) | 0616000081 | Z0E1 | 24788 | 23604.02 | 1183.98
06 | Madera | Pave unpaved alleys | Alley Paving Various Locations in the City of Madera | CML | 5157(122) | 0621000123 | Z400 | 66873.54 | 66869.77 | 3.77
06 | Fowler | Pavement and Pedestrian Facilities Rehabilitation | Manning Ave. from Golden State Blvd. to Fowler E. City limits | STPL | 5173(036) | 0619000138 | Z24E | 846847 | 800172.43 | 46674.57
06 | Sanger | Bike Lanes and trail | Bethel Ave from Jensen Ave to 480' n/o Florence Ave, and Church Ave from Indianila Ave to Bethel Ave. Fowler Switch Canal between Bethel Avenue and Jensen Avenue. | CML | 5197(042) | 0621000043 | Z40E | 99000 | 52235.5 | 46764.5
06 | Clovis | New Signals | At the Intersection of Shepherd and Peach Avenue | CML | 5208(169) | 0620000054 | Z400 | 48692 | 48691.98 | 0.02
06 | Corcoran | Construct sidewalk, ADA ramps, lighted crosswalks, and CL III bike routes | Phase 2 includes various improvements on several corridors: North Ave, Otis Ave, Norbe Ave, Van Dorsten Ave, Flory Ave, King Ave, Bainum Ave. | CML | 5223(023) | 0622000009 | Z40E | 56030 | 56026.61 | 3.39
06 | Firebaugh | Pave unpaved alley ways | Saipan Alley from Saipan Ave to 15th St, Soars Alley between 8th St to 7th St, and Beehive Alley from Saipan Ave to Corregidor Ave and Police Station Alley from 13th to 14th Street | CML | 5224(026) | 0621000048 | Z40E | 70804 | 68248.18 | 2555.82
06 | Chowchilla | Alley Paving | Alley Paving. City of Chowchilla: Robertson to Kings from 13th ST to 7th ST and Robertson to Trinity from 11th ST to 6th ST. | CML | 5258(041) | 0621000041 | Z400 | 50000 | 49985.54 | 14.46
06 | Shafter | Grade Separation and Widening | SEVENTH STANDARD ROAD FROM EAST OF GALPIN STREET TO WEST OF SR43 | DEMO17L | 5281(022) | 0617000110 | Z230 | 349649 | 113795.71 | 235853.29
06 | Mendota | Improve railroad corridor by adding concrete panels, installing medians, or channelizers | SR33 RRXG btwn Bass Ave and SR 180 Intersection, 9th St RRXG btwn Marie St and Naples St, & W. Belmont Ave RRXG btwn Marie St and SR 180/N San Benito Ave | STPL | 5285(020) | 0619000235 | Z240 | 27444.3 | 412.82 | 27031.48
06 | Kerman | Road Rehabilitation, replace curb and gutter, sidewalks, ADA curb ramps, signing and striping | Kearny Blvd from Park Ave to Del Norte Ave | STPL | 5291(030) | 0621000104 | Z24E | 39838 | 35378.31 | 4459.69
06 | Huron | Pave unpaved dirt alley ways. | Alley 1 between 11th and 12th Streets from Lassen Ave.(SR269) to M St., Alley 2 between 10th and 11th Streets from Lassen Ave.(SR269) to L St., and Alley 3 between Myrtle St. and Apple Ave. from parking lot w/o Lassen Ave.(SR269) to Orange St. | CML | 5305(020) | 0621000111 | Z400 | 38580 | 32404.55 | 6175.45
06 | Madera County | Replace 2 lane bridge with 2 lane bridge | Bridge 41C0123 on Road 427 over Oak Creek | BRLO | 5941(081) | 0600020246 | Z2E3 | 170000 | 84227.82 | 85772.18
06 | Madera County | Replace 2 Lane Bridge with 2 Lane Bridge | Bridge 41C0149 on Avenue 16 1/2 over Dry Creek | BRLO | 5941(089) | 0612000006 | Z233 | 126000 | 122462.57 | 3537.43
06 | Madera County | Construct Pedestrian and Bike Path | Road 225 from Willow Creek Drive to Road 228 | CML | 5941(102) | 0615000083 | Z006 | 391355 | 253293.03 | 138061.97 | 9/30/2026
06 | Madera County | Install 4 foot paved shoulders | Six roadway segments in Madera County, including: Road 16, Avenue 9, Avenue 7, Avenue 12, Avenue 18 1/2, and Robertson Blvd. | CML | 5941(131) | 0621000141 | Z400 | 457000 | 390950.68 | 66049.32
06 | Fresno County | Bridge Replacement | Bridge 42C0413 on Lincoln Avenue over Travers Creek | BRLO | 5942(226) | 0613000281 | Z2E3 | 160000 | 159980.61 | 19.39
06 | Fresno County | Bridge Replacement | Bridge 42C0413 on Lincoln Avenue over Travers Creek | BRLO | 5942(226) | 0613000281 | Z2E3 | 40000 | 5195 | 34805
06 | Fresno County | Replace two lane bridge with two lane bridge | Bridge 42C0276 on South Englehart Avenue over Reedley Main Canal | BRLO | 5942(239) | 0614000160 | M233 | 85000 | 73682.57 | 11317.43
06 | Fresno County | Shoulder improvements: construct 8-foot wide paved shoulders on each side of existing travel way | Mountain View Ave from Fowler Ave to McCall Ave | CML | 5942(297) | 0619000181 | Z40E | 842185 | 71508.13 | 770676.87
06 | Fresno County | Shoulder improvements, construct 8-foot wide paved shoulders on each side of existing travel way | Goodfellow Ave from 0.71mi E/O of Channel Rd to Reed Ave. | CML | 5942(298) | 0619000196 | Z40E | 275948 | 28632.31 | 247315.69
06 | Tulare County | Replace 2 Lane Bridge with 2 Lane Bridge | Bridge 46C0263 on Avenue 174 over Friant-Kern Canal | BRLO | 5946(140) | 0614000079 | Z2E3 | 14358 | 14273.03 | 84.97
06 | Tulare County | Replace 2 Lane Bridge with 2 Lane Bridge | Bridge 46C0263 on Avenue 174 over Friant-Kern Canal | BRLO | 5946(140) | 0614000079 | Z2E3 | 85642 | 4000 | 81642
06 | Tulare County | Replace 2 Lane Bridge with 2 Lane Bridge | Bridge 46C0340 on Avenue 428 over Sand Creek | BRLO | 5946(142) | 0614000082 | Z2E3 | 25000 | 0 | 25000
06 | Tulare County | Revegetation required by NEPA | Bridge 46C0195 on Road M348 over South Fork of Kaweah River | BRLO | 5946(189) | 0620000021 | Z233 | 137500 | 39068.85 | 98431.15

## District 7
Projects with Lapsing Federal Funds
Reversion Date: | 2026-06-30
Appropriation/Item Number | 2660-102-0890
Year of Appropriation: | 2021
Appropriation Unit: | 21102F
District | Parties to Agreement (Agency) | Purpose of Project (Work Description) | Scope (Location) | Prefix | Federal Id | Advantage Project Id | Federal Program Code | Budgeted Amount | Expenditure Amount | Remaining Balance | Federal Financial Deadline. This deadline will supercede the CWA deadline if approved. Invoices due 8/15/2026. | Is Project Consistent with Original Scope and Purpose of the Appropriation? If No, Please Explain: | Are You Requesting a CWA (Yes or No)? If No, provide an anticipated date the agency plans to submit invoice for the remaining balance | Reason for Delay | Please Provide a 2-3 Sentence Explanation Identifying Any Impediments to Completion | What are the Consequences if CWA is Not Approved? (Please Provide a 2-3 Sentence Explanation) | Local Agency Contact Name | Local Agency Contact Phone Number | Local Agency Contact Email | Approved by DOF (Yes or No)? | Revised Reversion Date
07 | Los Angeles | Bridge Rehabilitation | Hyperion Viaduct over Los Angeles River, Bridge #53C1881 | BHLS | 5006(181) | 0700001141 | Z001 | 719819 | 716130.67 | 3688.33
07 | Los Angeles | Roadway Widening(Install right turn lane , etc) | West side of San Fernando Road at Balboa Road | CML | 5006(639) | 0700001968 | Z400 | 849000 | 1000 | 848000
07 | Los Angeles | Transit Related | Transit Plazas at Normandie and Pico, and Hoover and Pico DEMO ID: CA513 | HPLUL | 5006(641) | 0700001971 | LY10 | 279960 | 21061.13 | 258898.87
07 | Los Angeles | Traffic Intersection Island Improvements | North side of Olympic Blvd at Irolo St and Normandy Ave | HPLUL | 5006(642) | 0700001972 | LY10 | 111994.92 | 9307.5 | 102687.42
07 | Los Angeles | Location of dedicated bike paths, lanes and routes, destinations, and transit hubs | Los Angeles | CML | 5006(690) | 0712000141 | Z400 | 283000 | 5952.02 | 277047.98
07 | Los Angeles | Roadway Widening | Balboa Widening at Devonshtire Street | STPL | 5006(840) | 0716000300 | M230 | 1001000 | 546082.27 | 454917.73
07 | Los Angeles | Pedestrian Improvement | Westlake MacArthur Park | CML | 5006(841) | 0716000310 | Z400 | 915000 | 718840.27 | 196159.73
07 | Los Angeles | Install RRFBs at uncontrolled locations. | Citywide list of 28 locations; Adams Bl & West View St., Avalon Bl and 90th St; Avalon Bl and 97th St, et | HSIPL | 5006(843) | 0716000354 | ZS3E | 2981340 | 1066101.43 | 1915238.57
07 | Los Angeles | Modify traffic signals: install turn phasing, upgrade indication sizes,install audible ped devices | 17 locations Citywide; Manchester Ave at Normandie Ave , etc. (Hoover, Vermont and Broadway. Imperial and Figueroa, Carson and Western. Victory @ Laurel Cyn and Coldwater Cyn, etc) | HSIPL | 5006(844) | 0716000352 | ZS3E | 3693900 | 1531103.88 | 2162796.12
07 | Los Angeles | Street Lighting(Replace existing high volt lighting system with low volt.) | Ventura Blvd: Amigo Ave to Calhoun Ave Amigo /white Oak ave. Densmore Ave / Calhoun | STPL | 5006(860) | 0717000241 | Z230 | 349966 | 307013.16 | 42952.84
07 | Los Angeles | Addition of five staging/storage tracks (approximately 31,000 lineal feet) to the existing Pier 400 rail yard | In the Port of Los Angeles on Terminal Island. | TCEPSB1 | 5006(882) | 0719000121 | Z460 | 21643000 | 21210140 | 432860
07 | Los Angeles | Street Lighting | Project locations are scattered throughout the city of LA in the proximity of Downtown LA and Westlake areas; area bounded by Ronald Reagan FWY(118), Ventura FWY(101): & Eagle Rock | STPL | 5006(900) | 0720000160 | Z230 | 1622600 | 946438.88 | 676161.12
07 | Los Angeles | High Voltage Conversion FED Program Unit 3 | Projects are in the proximity to the Down Town areas | STPL | 5006(902) | 0721000119 | Z230 | 1498500 | 971856.28 | 526643.72
07 | Los Angeles | Citywide re-surface, construct ADA compliant access ramps, and trucated domes, as needed | City of Los Angeles - city wide | STPL | 5006(917) | 0721000229 | Z230 | 11500000 | 9292297.17 | 2207702.83
07 | San Buenaventura | REPLACE EXISTING TWO LANE BRIDGE (BRIDGE NO. 52C0061) | MAIN ST OVER VENTURA RIVER AND RIVER TRAILS BOTH SIDES OF THE VENTURA RIVER (0.5 MILES W/O VENTURA AVE) | BRHIPL | 5026(065) | 0722000003 | Z913 | 2887678 | 1038480.85 | 1849197.15 | 9/30/2028
07 | Oxnard | UPGRADE EXISTING SIGNAL STANDARDS & ACCESS RAMPS, INSTALL LED LIGHTS, CONVERT SIGNALTO MAST ARMS | FIFTH ST. & OXNARD BLVD, SAVIERS RD. & ELM ST., SAVIERS RD & BRYCE CANYON, SAVIERS RD 7 BARD RD., SAVIERS RD & PLEASANT VALLEY ROAD. | HSIPL | 5129(093) | 0716000405 | ZS3E | 1227615 | 1208198.88 | 19416.12
07 | Torrance | Rehabilitate asphalt pavement, repair damaged sidwalk, curb and gutter, traffic signal improvments | Anza Ave from Del Amo Blvd to Sepulveda Blvd | STPL | 5249(032) | 0721000202 | Z230 | 2247000 | 2208950.02 | 38049.98
07 | Baldwin Park | Install traffic signals and raised medians | Maine-Pacific Ave. between Ramona Blvd. and Bogart Ave | HSIPL | 5323(032) | 0713000433 | Z230 | 304796 | 0 | 304796
07 | Baldwin Park | Install traffic signals and raised medians | Maine-Pacific Ave. between Ramona Blvd. and Bogart Ave | HSIPL | 5323(032) | 0713000433 | ZS3E | 344600 | 81661.01 | 262938.99
07 | Pico Rivera | Demolish exiist. four lane bridge; construct 2 parallel 3-lane structures w/ CIP | Telegraph Road over San Gabriel River. Bridge No. 53C0057 | BRLS | 5351(038) | 0721000123 | Z0E1 | 1155316 | 759706.15 | 395609.85
07 | Simi Valley | BRIDGE REHABILITATION | LOS ANGELES AVENUE BRIDGE OVER ARROYO SIMI, 0.1 MILE WEST OF FIRST STREET. STATE BRIDGE # 52C-0206 | BHLS | 5405(076) | 0713000358 | Z0E1 | 132795 | 1207.7 | 131587.3
07 | Santa Clarita | Post Construction Environmental Mitigation | Newhall Ranch Road | BHLS | 5450(101) | 0721000166 | M240 | 559479.86 | 194737.37 | 364742.49
07 | Santa Clarita | Post Construction Environmental Mitigation | Newhall Ranch Road | BHLS | 5450(101) | 0721000166 | Z001 | 586758.14 | 481149.05 | 105609.09
07 | Los Angeles County | Bridge Preventive Maintenance Program | 25 Bridges in the Unincorporated Areas of LA County | BPMPL | 5953(708) | 0715000145 | Z230 | 190243.43 | 185243.43 | 5000
07 | Los Angeles County | Bridge Preventive Maintenance Program | Six bridges in the cities of Baldwin Park, Cerritos, Downey, Pico Rivera, and Pasadena | BPMPL | 5953(726) | 0722000025 | Z230 | 138434.16 | 97434.16 | 41000
07 | Los Angeles County Metropolitan Transportation Authority | Sound Wall | I-210 FWY FROM 0.2 MILES WEST OF MARENGO AVE TO W ILSON AVE IN THE CITY OF PASADENA AND APPROX. 1.5 MILES OF SOUNDWALLS FROM BALDWIN AVE TO SANTA ANITA AVE IN THE CITY OF ARCADIA. | HIPL | 6065(251) | 0722000015 | Z005 | 25640775 | 24621854.38 | 1018920.62 | 9/30/2026
07 | Los Angeles County Metropolitan Transportation Authority | Sound Wall | I-210 FWY FROM 0.2 MILES WEST OF MARENGO AVE TO W ILSON AVE IN THE CITY OF PASADENA AND APPROX. 1.5 MILES OF SOUNDWALLS FROM BALDWIN AVE TO SANTA ANITA AVE IN THE CITY OF ARCADIA. | HIPL | 6065(251) | 0722000015 | Z007 | 194439 | 0 | 194439 | 9/30/2026
07 | San Gabriel Valley Council of Governments | New Bridge( grade separation) | Durfee Avenue at the UPRR in the City of Pico Rivera | PNRS | 6303(039) | 0713000055 | LY40 | 2814794.85 | 161898.11 | 2652896.74

## District 8
Projects with Lapsing Federal Funds
Reversion Date: | 2026-06-30
Appropriation/Item Number | 2660-102-0890
Year of Appropriation: | 2021
Appropriation Unit: | 21102F
District | Parties to Agreement (Agency) | Purpose of Project (Work Description) | Scope (Location) | Prefix | Federal Id | Advantage Project Id | Federal Program Code | Budgeted Amount | Expenditure Amount | Remaining Balance | Federal Financial Deadline. This deadline will supercede the CWA deadline if approved. Invoices due 8/15/2026. | Is Project Consistent with Original Scope and Purpose of the Appropriation? If No, Please Explain: | Are You Requesting a CWA (Yes or No)? If No, provide an anticipated date the agency plans to submit invoice for the remaining balance | Reason for Delay | Please Provide a 2-3 Sentence Explanation Identifying Any Impediments to Completion | What are the Consequences if CWA is Not Approved? (Please Provide a 2-3 Sentence Explanation) | Local Agency Contact Name | Local Agency Contact Phone Number | Local Agency Contact Email | Approved by DOF (Yes or No)? | Revised Reversion Date
08 | San Bernardino | Upgrade traffic signal hardware | Two hundred and twenty-four (224) signalized intersections on various arterials in the City of San Bernardino | HSIPL | 5033(056) | 0819000060 | ZS3E | 4432265 | 4124927.37 | 307337.63
08 | Chino | Roadway widening and extension | Pine Avenue from State Route 71 to Euclid Avenue (State Route 83) | HPLUL | 5188(018) | 0800000944 | LY10 | 1254920.4 | 0 | 1254920.4
08 | Palm Springs | Bridge rehabilitation and widening from four to six lanes | Ramon Road from San Luis Rey Drive to Landau Boulevard, Br. No. 56C-0287 | BHLS | 5282(040) | 0800020453 | Z0E1 | 362088 | 273664.24 | 88423.76
08 | Palm Springs | Bridge rehabilitation | East Palm Canyon Drive over Palm Canyon Wash, Br. No. 56C-0409 | BHLS | 5282(041) | 0813000143 | Z0E1 | 803852 | 438102.41 | 365749.59
08 | Palm Springs | Bridge replacement | South Palm Canyon Drive over Tahquitz Creek, Br. No. 56C-0408 | BRLS | 5282(042) | 0814000037 | Z0E1 | 299231 | 90845.28 | 208385.72
08 | Barstow | Bridge replacement | North First Avenue bridge over the BNSF Railroad, from 0.2 miles north of Main Street to Crooks Street, Br. No. 54C-0088 | BRLS | 5298(030) | 0813000018 | L1C0 | 1350083 | 419236.68 | 930846.32
08 | Barstow | Bridge replacement | North First Avenue bridge over the BNSF Railroad, from 0.2 miles north of Main Street to Crooks Street, Br. No. 54C-0088 | BRLS | 5298(030) | 0813000018 | Z0E1 | 4005581 | 3198099.24 | 807481.76
08 | Barstow | Bridge replacement | North First Avenue bridge over the Mojave River, Br. No. 54C-0089 | BRLS | 5298(031) | 0814000091 | Z001 | 708240 | 0 | 708240
08 | Barstow | Bridge replacement | North First Avenue bridge over the Mojave River, Br. No. 54C-0089 | BRLS | 5298(031) | 0814000091 | Z0E1 | 1897054 | 353276.53 | 1543777.47
08 | Riverside County | Replace existing 2-lane bridge with new 4-lane bridge | Market Street over the Santa Ana River in Jurupa Valley, Br. No. 56C-0024 | BRLS | 5956(200) | 0812000213 | Z0E1 | 354120 | 334542.46 | 19577.54
08 | Riverside County | Bridge replacement | Chuckwalla Valley Road over Acari Ditch, Br. No. 56C-0108 | BRLO | 5956(225) | 0814000007 | Z2E3 | 210000 | 167722.45 | 42277.55
08 | Riverside County | Bridge replacement | Chuckwalla Valley Road over Sutro Ditch, Br. No. 56C-0104 | BRLO | 5956(226) | 0814000008 | Z2E3 | 220000 | 182006.11 | 37993.89
08 | Riverside County | Bridge replacement | Chuckwalla Valley Road over Tarantula Ditch, Br. No. 56C-0103 | BRLO | 5956(227) | 0814000009 | Z2E3 | 220000 | 175433.49 | 44566.51
08 | Riverside County | Bridge replacement | Railroad Avenue over Fornat Wash, Br. No. 56C-0099 | BRLO | 5956(228) | 0814000010 | Z2E3 | 250000 | 217957.38 | 32042.62
08 | Riverside County | Bridge replacement | Railroad Avenue over east channel of Stubbe Wash, Br. No. 56C-0101 | BRLO | 5956(229) | 0814000011 | Z2E3 | 250000 | 217091.61 | 32908.39
08 | Riverside County | Bridge replacement from two to six lanes | IN WESTERN RIVERSIDE COUNTY IN THE CITY OF NORCO - ON HAMNER AVE OVER SANTA ANA RIVER .5 MILES N/O OF SIXTH STREET, (BRIDGE NO.56C0446). | BRLS | 5956(230) | 0814000014 | Z0E1 | 15300000 | 15299999.98 | 0.02
08 | Riverside County | Bridge replacement | Chuckwalla Valley Road over Aztec Ditch, Br. No. 56C-0102 | BRLO | 5956(239) | 0814000262 | Z2E3 | 210000 | 175000 | 35000
08 | San Bernardino Associated Governments | Widen highway to four lanes with left-turn channelization | US 395 from Palmdale Road (State Route 18) in the City of Victorville to Chamberlaine Way in the City of Adelanto, Phase 1 | STPLULN | 6053(122) | 0815000196 | M23E | 3447905.09 | 670777.8 | 2777127.29
08 | San Bernardino Associated Governments | Add toll express lanes in each direction | I-10 corridor express lane widening, Phase I, from San Antonio Avenue in the City of Pomona to the I-10/I-15 interchange in the City of Ontario | CMSTPLN | 6053(130) | 0817000021 | Z40E | 7963191 | 6197067.71 | 1766123.29
08 | Riverside County Transportation Commission | Reconstruct interchange | SR 91/ SR 71 interchange | HP21LN | 6054(066) | 0800020578 | Z230 | 2661000 | 0 | 2661000
08 | Riverside County Transportation Commission | Eastbound truck-climbing and westbound truck-descending lanes | State Route 60 from Gilman Springs Road to 1.37 miles west of Jack Rabbit Trail | CMLN | 6054(090) | 0819000010 | Z400 | 8005000 | 5829296.46 | 2175703.54
08 | Riverside County Transportation Commission | Smart Freeways Demonstration Project. | City of Temecula on I-15 NB from San Diego County line to I-15/I-215 split on Rancho California Road, Temecula Parkway, and Winchester Road ramps | CMLN | 6054(103) | 0821000100 | Z400 | 4000000 | 3100674.82 | 899325.18
08 | San Bernardino County Transportation Authority | Bridge replacement | Mount Vernon Avenue overhead at the Burlington Northern Santa Fe Railroad yard from King Street to 5th Street, Br. No. 54C-0066 | BRLS | 6507(003) | 0817000123 | Z0E1 | 18017241.54 | 17483968.08 | 533273.46
08 | San Bernardino County Transportation Authority | Develop, promote, and implement a 3-year rideshare program | Throughout the South Coast Air Basin within San Bernardino County | CML | 6507(029) | 0821000098 | M400 | 1950000 | 1752110.63 | 197889.37
08 | Palm Springs | Replace low water crossing with a 4-lane bridge | Vista Chino Road at Whitewater River east of Gene Autry Trail in the City of Palm Springs, LWC #00L0052 | BR | NBIL(513) | 0800020452 | Z0E1 | 779064 | 225405.24 | 553658.76
08 | La Quinta | Eliminate low water crossing with 4-lane bridge | Dune Palms Road over the Coachella Valley Stormwater Channel (Whitewater River) in the City of La Quinta, LWC 00L0070 | BR | NBIL(537) | 0815000208 | Z0E1 | 684337 | 417956.51 | 266380.49

## District 9
Projects with Lapsing Federal Funds
Reversion Date: | 2026-06-30
Appropriation/Item Number | 2660-102-0890
Year of Appropriation: | 2021
Appropriation Unit: | 21102F
District | Parties to Agreement (Agency) | Purpose of Project (Work Description) | Scope (Location) | Prefix | Federal Id | Advantage Project Id | Federal Program Code | Budgeted Amount | Expenditure Amount | Remaining Balance | Federal Financial Deadline. This deadline will supercede the CWA deadline if approved. Invoices due 8/15/2026. | Is Project Consistent with Original Scope and Purpose of the Appropriation? If No, Please Explain: | Are You Requesting a CWA (Yes or No)? If No, provide an anticipated date the agency plans to submit invoice for the remaining balance | Reason for Delay | Please Provide a 2-3 Sentence Explanation Identifying Any Impediments to Completion | What are the Consequences if CWA is Not Approved? (Please Provide a 2-3 Sentence Explanation) | Local Agency Contact Name | Local Agency Contact Phone Number | Local Agency Contact Email | Approved by DOF (Yes or No)? | Revised Reversion Date
09 | Ridgecrest | Install Electric Vehicle Charging Station and Solar Photovoltaic System | City corporation Yard located at 636 W Ridgecrest Blvd | CML | 5385(069) | 0921000015 | Z40E | 556457 | 520354.91 | 36102.09

## District 10
Projects with Lapsing Federal Funds
Reversion Date: | 2026-06-30
Appropriation/Item Number | 2660-102-0890
Year of Appropriation: | 2021
Appropriation Unit: | 21102F
District | Parties to Agreement (Agency) | Purpose of Project (Work Description) | Scope (Location) | Prefix | Federal Id | Advantage Project Id | Federal Program Code | Budgeted Amount | Expenditure Amount | Remaining Balance | Federal Financial Deadline. This deadline will supercede the CWA deadline if approved. Invoices due 8/15/2026. | Is Project Consistent with Original Scope and Purpose of the Appropriation? If No, Please Explain: | Are You Requesting a CWA (Yes or No)? If No, provide an anticipated date the agency plans to submit invoice for the remaining balance | Reason for Delay | Please Provide a 2-3 Sentence Explanation Identifying Any Impediments to Completion | What are the Consequences if CWA is Not Approved? (Please Provide a 2-3 Sentence Explanation) | Local Agency Contact Name | Local Agency Contact Phone Number | Local Agency Contact Email | Approved by DOF (Yes or No)? | Revised Reversion Date
10 | Modesto | Interconnect Signals (Signal Coordination) | Claus Road Between Briggsmore and Creekwood Drive | CML | 5059(245) | 1021000103 | Z400 | 47250 | 46584.48 | 665.52
10 | Modesto | Interconnect Signals (Signal Coordination) | Scenic Drive between Bodem Street and Oakdale Road | CML | 5059(246) | 1021000116 | Z40E | 63000 | 39151.5 | 23848.5
10 | Modesto | Traffic Control Devices / Radio Communication Upgrades (Purchase Radio Communication Units) | City of Modesto | CMLNI | 5059(247) | 1021000117 | Z003 | 122500 | 4900 | 117600
10 | Modesto | Purchase of Travel Time Bluetooth Devices | City of Modesto | CMLNI | 5059(249) | 1021000119 | Z400 | 150000 | 74900 | 75100
10 | Modesto | Roadway Widening, Reconstruct to 8 Lane Interchange | SR99 at Briggsmore/Carpenter Road | STPL | 5059(250) | 1021000128 | Z230 | 2298879 | 1852351 | 446528
10 | Los Banos | Complete Streets | Pioneer Road in the City of Los Banos | HIPLPPSB | 5160(029) | 1021000081 | Z006 | 663545 | 420107.12 | 243437.88 | 9/30/2026
10 | Turlock | Signal Synchronization. | E. Monte Vista Ave between Geer Road. and Berkeley Avenue | CML | 5165(097) | 1021000056 | M400 | 13448 | 10080.96 | 3367.04
10 | Gustine | Construct Roundabout on SR-140/33 | On SR-140/33 at Fourth Street and Sixth Avenue. | CML | 5230(003) | 1000020514 | Z003 | 2036190 | 1986383.82 | 49806.18
10 | Gustine | Pedestrian Improvements | 3rd Ave (3rd St to East Ave), East Ave (3rd Ave to South Ave), and South Ave (Railroad to East Ave) | CML | 5230(013) | 1021000030 | Z003 | 87367 | 84552.84 | 2814.16
10 | Atwater | Pedestrian and Bike Path | Atwater Ph 3 Ped Improvmnts to Connect w/Dntwn. Oak Ave and Mulberry Ave btwn Third St and Linden St; Laurel Ave, Kadota Ave and Juniper Ave btwn Third St and First St; Third St... | CML | 5254(032) | 1021000028 | Z003 | 116780 | 115780 | 1000
10 | Riverbank | Pavement Reconstruction along with Bike and Pedestrian Improvements. | Callander Avenue from just North of Topeka Street to just South of Santa Fe Street. | STPCML | 5255(061) | 1021000062 | Z003 | 196870.5 | 0 | 196870.5
10 | Riverbank | Pavement Reconstruction along with Bike and Pedestrian Improvements. | Callander Avenue from just North of Topeka Street to just South of Santa Fe Street. | STPCML | 5255(061) | 1021000062 | Z230 | 257641.5 | 92503.09 | 165138.41
10 | Livingston | Construct Multi-use Path Improvements (Phase 1) | At Max Foster Sports Complex Area in Livingston | CML | 5256(020) | 1021000031 | Z0E3 | 59315 | 55747.81 | 3567.19
10 | Amador County | Construct Safety and Operational Improvements | Pine Grove at SR 88 from Climax Road to Mount Zion. | HIPL | 5926(066) | 1021000187 | Z007 | 98811 | 0 | 98811 | 9/30/2026
10 | San Joaquin County | Replace existing one-lane timber bridge with a wider one-lane bridge | Buckman Road over Duck Creek, Bridge 29C0307. | BRLO | 5929(241) | 1012000116 | Z233 | 346500 | 286887.1 | 59612.9
10 | Tuolumne County | Rehabilitate existing two-lane bridge | Algerine Road over Algerine Creek (Bridge 32C0073) | BRLO | 5932(096) | 1018000099 | Z233 | 204100 | 176643.02 | 27456.98
10 | Stanislaus County | Replace existing historic 2-lane bridge with a standard 4-lane bridge, including a median. | Seventh Street over Tuolumne River, Bridge 38C0023. | BRLS | 5938(167) | 1000020320 | Z0E1 | 3801478 | 3178933.29 | 622544.71
10 | Stanislaus County | Replace 2-lane bridge with a standard 2-lane bridge (seismic retrofit) | Hickman Rd. over Tuolumne River, Bridge 38C0004A | BRLS | 5938(199) | 1012000221 | Z0E1 | 287607 | 37552 | 250055
10 | Stanislaus County | Install Traffic Signal System | Intersection of Crows Landing Road and 7th Street | CML | 5938(254) | 1020000010 | Z003 | 400000 | 399282.21 | 717.79
10 | Mariposa County | Rehabilitate existing two-lane bridge; Widen to standard two-lane width (No Added Lane Capacity) | School House Road Bridge (40C0053) over Owens Creek. | BRLO | 5940(113) | 1014000188 | Z2E3 | 100000 | 97845.55 | 2154.45
10 | Mariposa County | Install centerline /edgeline striping | 1) MERCED FALLS RD: COUNTYLINE (PM 10) - COUNTYLINE (PM 19.04); 2) E. WHITLOCK RD: SR140 - COLORADO RD; 3) MT. BULLION CUTOFF (PM10.00): SR140 - SR49), 4) BEN HUR RD: COUNTYLINE (PM 10.00) - PM 15.00 AND PM 18.50; 5) TRIANGLE RD: SR140 - E. WESTFALL RD ; 6)SUMMIT RD: SR41-END OF PAVEMENT | HIPL | 5940(139) | 1021000131 | Z007 | 26972 | 18374.5 | 8597.5 | 9/30/2026
10 | Mariposa County | Install centerline /edgeline striping | 1) MERCED FALLS RD: COUNTYLINE (PM 10) - COUNTYLINE (PM 19.04); 2) E. WHITLOCK RD: SR140 - COLORADO RD; 3) MT. BULLION CUTOFF (PM10.00): SR140 - SR49), 4) BEN HUR RD: COUNTYLINE (PM 10.00) - PM 15.00 AND PM 18.50; 5) TRIANGLE RD: SR140 - E. WESTFALL RD ; 6)SUMMIT RD: SR41-END OF PAVEMENT | HIPL | 5940(139) | 1021000131 | Z906 | 66705 | 0 | 66705 | 9/30/2027
10 | Mariposa County | Install centerline /edgeline striping | 1) MERCED FALLS RD: COUNTYLINE (PM 10) - COUNTYLINE (PM 19.04); 2) E. WHITLOCK RD: SR140 - COLORADO RD; 3) MT. BULLION CUTOFF (PM10.00): SR140 - SR49), 4) BEN HUR RD: COUNTYLINE (PM 10.00) - PM 15.00 AND PM 18.50; 5) TRIANGLE RD: SR140 - E. WESTFALL RD ; 6)SUMMIT RD: SR41-END OF PAVEMENT | HIPL | 5940(139) | 1021000131 | Z911 | 18951 | 0 | 18951 | 9/30/2028
10 | Mariposa County | Surface unpaved road, shoulder backing, ditch excavating | Leonard Rd PM 10.63(Harvest Dr) to PM11.45(Mobilehome Park) | CML | 5940(141) | 1021000151 | Z40E | 150000 | 68977.22 | 81022.78
10 | San Joaquin Council of Governments | Widen from 6 to 8 lanes with managed lanes including sound walls and eleven joined bridges | Near Tracy, I-205 from the Alameda County line to Interstate 5 | RPSTCML | 6088(068) | 1019000197 | Z006 | 641347 | 0 | 641347 | 9/30/2026
10 | Stanislaus Council of Governments | Transit Related - (Regional Rideshare ProgramThe Regional Rideshare Program consists of regional rideshare marketing services. These services include, but are not limited to, supporting existing and expanded activities designated to increase the use of carpools and vanpools. The program also supports the purchase and use of computerized matching software and outreach materials to employers. A guaranteed ride home program is also included as part of the project. | Within Stanislaus county (Regional Rideshare Program) | CMLNI | 6089(087) | 1021000109 | Z0E3 | 807615 | 763023.86 | 44591.14

## District 11
Projects with Lapsing Federal Funds
Reversion Date: | 2026-06-30
Appropriation/Item Number | 2660-102-0890
Year of Appropriation: | 2021
Appropriation Unit: | 21102F
District | Parties to Agreement (Agency) | Purpose of Project (Work Description) | Scope (Location) | Prefix | Federal Id | Advantage Project Id | Federal Program Code | Budgeted Amount | Expenditure Amount | Remaining Balance | Federal Financial Deadline. This deadline will supercede the CWA deadline if approved. Invoices due 8/15/2026. | Is Project Consistent with Original Scope and Purpose of the Appropriation? If No, Please Explain: | Are You Requesting a CWA (Yes or No)? If No, provide an anticipated date the agency plans to submit invoice for the remaining balance | Reason for Delay | Please Provide a 2-3 Sentence Explanation Identifying Any Impediments to Completion | What are the Consequences if CWA is Not Approved? (Please Provide a 2-3 Sentence Explanation) | Local Agency Contact Name | Local Agency Contact Phone Number | Local Agency Contact Email | Approved by DOF (Yes or No)? | Revised Reversion Date
11 | San Diego | Bridge Replacement | In the City of San Diego on El Camino Real Bridge over the San Dieguito River, Brd # 57C-0042 | BHLO | 5004(068) | 1100000556 | Z0E1 | 1992000 | 378213.24 | 1613786.76
11 | San Diego | Bridge Replacement | Fairmount Ave Overcrossing Aldine Dr. (57C0420R) Right Bridge | BRLS | 5004(198) | 1116000090 | Z0E1 | 103580 | 102580 | 1000
11 | San Diego | Bridge rehabilitation of two lane bridge | Fairmount Ave Overcrossing Aldine Ave (57C0420L) Left Bridge | BRLS | 5004(200) | 1116000092 | Z0E1 | 188568 | 151503.7 | 37064.3
11 | San Diego | Installation of roundabouts and other traffic control measures to improve pedestrian safety. | University Avenue between Fairmount Avenue and Euclid Avenue | HSIPL | 5004(207) | 1117000121 | ZS3E | 4469580 | 3872150.17 | 597429.83
11 | La Mesa | Bridge Rehabilitation. Widen bridge to accomodate wider lanes, shoulders, and sidewalks. | Bridge No.57C0467, Grossmont Center Drive over MTDB LRT & SDIV RR. 0.04 mile south of Fletcher Parkway. | BRLS | 5207(036) | 1113000119 | Z0E1 | 553313 | 406648.38 | 146664.62
11 | San Diego County | Bridge Replacement | Sycamore Drive over North Fork San Marcos Creek 57C-0358 | BRLS | 5957(118) | 1114000095 | Z0E1 | 265590 | 211858.37 | 53731.63

## District 12
Projects with Lapsing Federal Funds
Reversion Date: | 2026-06-30
Appropriation/Item Number | 2660-102-0890
Year of Appropriation: | 2021
Appropriation Unit: | 21102F
District | Parties to Agreement (Agency) | Purpose of Project (Work Description) | Scope (Location) | Prefix | Federal Id | Advantage Project Id | Federal Program Code | Budgeted Amount | Expenditure Amount | Remaining Balance | Federal Financial Deadline. This deadline will supercede the CWA deadline if approved. Invoices due 8/15/2026. | Is Project Consistent with Original Scope and Purpose of the Appropriation? If No, Please Explain: | Are You Requesting a CWA (Yes or No)? If No, provide an anticipated date the agency plans to submit invoice for the remaining balance | Reason for Delay | Please Provide a 2-3 Sentence Explanation Identifying Any Impediments to Completion | What are the Consequences if CWA is Not Approved? (Please Provide a 2-3 Sentence Explanation) | Local Agency Contact Name | Local Agency Contact Phone Number | Local Agency Contact Email | Approved by DOF (Yes or No)? | Revised Reversion Date
12 | Anaheim | Nohl Ranch Open Space Trail project will construct a 10' wide Class I bikeway in compliance with Caltrans standards. Ancillary features of the project include lighting, shared lane markings, signs to indicate directions and distances to nearby destinations, bicycle parking, and bicycle detection at the Imperial Highway signal in Alternative 1. The project will also include construction of a pedestrian traffic signal. | Various locations in Anaheim | CMLN | 5055(188) | 1218000016 | L40R | 9161 | 0 | 9161
12 | Anaheim | Nohl Ranch Open Space Trail project will construct a 10' wide Class I bikeway in compliance with Caltrans standards. Ancillary features of the project include lighting, shared lane markings, signs to indicate directions and distances to nearby destinations, bicycle parking, and bicycle detection at the Imperial Highway signal in Alternative 1. The project will also include construction of a pedestrian traffic signal. | Various locations in Anaheim | CMLN | 5055(188) | 1218000016 | Z40E | 430039 | 180136.4 | 249902.6
12 | Santa Ana | Install bicycle racks and construct bicycle center | Throughout the City of Santa Ana and at the Santa Ana Regional Transportation Center | CML | 5063(181) | 1217000066 | Z400 | 937200 | 1509.75 | 935690.25
12 | Santa Ana | Protected left-turn signal phasing | Intersections of 1st Street at Jackson Street and 5th Street at Euclid Street | HSIPL | 5063(190) | 1218000033 | ZS3E | 596328 | 375398.46 | 220929.54
12 | Santa Ana | Protective 6' Bike Lane, raised median, road narrowing, signage, striping, ADA, bike detection | Warner Ave. from Oak St. to Grand Ave. | CML | 5063(200) | 1220000033 | Z400 | 94010 | 87907.97 | 6102.03
12 | Orange | Protected left-turn signal phasing on Batavia Street | Intersection of Chapman Avenue and Batavia Street | HSIPL | 5073(090) | 1218000051 | ZS30 | 359800 | 310264.04 | 49535.96
12 | Orange | Class I Bicycle Lane/Multipurpose Trail including 2 bridges, signage, rest areas, & trash receptacle | Along Cannon St., 800' N/O Santiago Canyon Rd., connecting to existing bike trail & continuing along the north bank of Santiago Creek from Cannon St. to Santiago Oaks Regional Park | CML | 5073(094) | 1220000067 | Z400 | 345794 | 306370.6 | 39423.4
12 | Orange County Transportation Authority | Project study reports for HOV lanes | I-5 from the Orange/San Diego County Line to Avenida Pico in the City of San Clemente | CMLN | 6071(112) | 1215000130 | Z23E | 5500000 | 4787099.18 | 712900.82
12 | Orange County Transportation Authority | HOV and mixed-flow lanes in each direction | State Route 55 from Interstate 405 to Interstate 5 | CMSTPLN | 6071(129) | 1217000111 | Z230 | 8000000 | 0 | 8000000
12 | Orange County Transportation Authority | Roadway Widening | I-5 Improvement, Yale Ave. to SR-55 (segment 2) | STPLN | 6071(154) | 1220000101 | Z23E | 10900000 | 10587732.54 | 312267.46

## Drop-down Reference Tables
Within Scope? | Need a CWA? | Primary Reason For Delay:
YES | YES | Design: Change in scope.
NO | NO | Design: Change in specifications.
Design: Change in site conditions.
Environmental: Change in scope requires additional studies/permits.
Environmental: Excessive study or opinion review time by external agencies.
Environmental: Permits expired.
Environmental: Environmental document determination revalidation required.
Environmental: Mitigation for project impacts period.
Right of Way and Utility Relocation: Change in scope/number of parcels/utility relocations required.
Right of Way and Utility Relocation: Condemnation/eminent domain proceedings.
Right of Way and Utility Relocation: Utility owner dispute.
Right of Way and Utility Relocation: Qualified Buy America purchase/delivery delays.
Construction: Contract award disputed/cancelled, rebid, or complete under force account.
Construction: Change in site conditions.
Construction: Qualified Buy America purchase/delivery delays.
Construction: Extended winter suspension affecting delivery schedule.
Contract Dispute/Litigation: Post-construction claim. Informal settlement.
Contract Dispute/Litigation: Formal litigation proceeding.
Finance: CTC approved Time Extension conflicts with reversion date.
Finance: Indirect Cost Rate Proposal (ICRP) request package returned with errors.
Finance: Change in dedicated/programmed funding.
Finance: Pending programming.
OTHER-declared disaster:
OTHER (explain):