## District 2
STIP Projects with Lapsing Federal Funds
Reversion Date: | 2026-06-30
Appropriation/Item Number: | 2660-101-0890
Year of Appropriation: | 2020-21
Appropriation Unit: | 21101F
Program Code: | 20.30
District | Parties to Agreement (Agency) | Purpose of Project (Work Description) | Scope (Location) | Prefix | Project Id | Advantage Project Id | PPNO | Federal Program Code | Budgeted Amount | Expenditure Amount | Remaining Balance | CTC TUF Deadline | Is Project Consistent with Original Scope and Purpose of the Appropriation? If No, Please Explain: | Are You Requesting a CWA (Yes or No)? If No, provide an anticipated date the agency plans to submit invoice for the remaining balance | Reason for Delay | Please Provide a 2-3 Sentence Explanation Identifying Any Impediments to Completion | What are the Consequences if CWA is Not Approved? (Please Provide a 2-3 Sentence Explanation) | Local Agency Contact Name | Local Agency Contact Phone Number | Local Agency Contact Email | Approved by DOF (Yes or No)? | Revised Reversion Date
02 | Tehama County | Pavement Rehabilitation | Old Highway 99W (formerly Highway 99) from Tehama-Glenn county line and extends North to Corning city limits at South Avenue. | RPSTPL | 5908(102) | 0219000024 | 2567 | Z240 | 150000 | 37579.26 | 112420.74 | 2026-02-28 | NO. Tehama Regional Transportation Planning Agency (RTPA) paused the 5908(102) to re-scope the project as part of a new South County corridor planning effort. These efforts may include interchange and other improvements to better facilitate other stakeholders interests in the corridor. | YES | OTHER (explain): The majority of the funding for 5908(102) was transferred to provide full funding for the Construction (CON) phase of 5908(100). Construction of 5908(100) is complete, and the County’s focus is now on the remainder of the corridor and 5908(102). | Multiple stakeholders are involved in the scope of the improvements needed in the corridor, including Caltrans, Tehama County, City of Corning, and the Paskenta Band of Nomlaki Indians. Tehama RTPA will coordinate the programming of future funding based on input from the other stakeholders. | If the CWA is not approved, the remaining funding will expire, and current efforts to determine the condition of the existing roadway facility, development of current accident and traffic data, and coordination of stakeholder input will be discontinued. | Danielle Peterson, Blake Rampey, Shad Jacobe | (530) 385-1462, x3017 (530) 385-1462, x3043 (530) 385-1462, x3013 | dpeterson@tcpw.ca.gov rrampey@tcpw.ca.gov sjacobe@tcpw.ca.gov | Yes | 2028-06-30
02 | Modoc County | Rehabilitate 3.656 miles of roadway utilizing Cold in Place Recycle Method with HMA overlay. | On County Road 55 North of Alturas from United States Route 395 to County Road 247A. | RPSTPL | 5903(067) | 0222000017 | 2438 | Z970 | 35000 | 14966.51 | 20033.49 | 2024-06-30 | YES | YES | OTHER (explain): Need to process the invoices. | To avoid any unforseen events that would delay processing invoices. | If the CWA is not approved, Modoc County would need to pay for the invoices which would negatively affect the County's finances and other planned projects. | Dale Merrick | (530) 233-6423 | dalemerrick@co.modoc.ca.us | Yes | 2028-06-30
[8 empty] | Total | 185000 | 52545.77 | 132454.23

## Drop-down Reference Tables
Within Scope? | Need a CWA? | Primary Reason For Delay:
YES | YES | Design: Change in scope.
NO | NO | Design: Change in specifications.
Design: Change in site conditions.
Environmental: Change in scope requires additional studies/permits.
Environmental: Excessive study or opinion review time by external agencies.
Environmental: Permits expired.
Environmental: Environmental document determination revalidation required.
Environmental: Mitigation for project impacts period.
Right of Way and Utility Relocation: Change in scope/number of parcels/utility relocations required.
Right of Way and Utility Relocation: Condemnation/eminent domain proceedings.
Right of Way and Utility Relocation: Utility owner dispute.
Right of Way and Utility Relocation: Qualified Buy America purchase/delivery delays.
Construction: Contract award disputed/cancelled, rebid or complete under force account.
Construction: Change in site conditions.
Construction: Qualified Buy America purchase/delivery delays.
Construction: Extended winter suspension affecting delivery schedule.
Contract Dispute/Litigation: Post-construction claim. Informal settlement.
Contract Dispute/Litigation: Formal litigation proceeding.
Finance: CTC approved Time Extension conflicts with reversion date.
Finance: Indirect Cost Rate Proposal (ICRP) request package returned with errors.
Finance: Change in dedicated/programmed funding.
Finance: Pending programming.
OTHER-declared disaster (explain):
OTHER (explain):