## ATP SB1
ATP Projects with Lapsing Senate Bill 1 Funds
Reversion Date: | 2026-06-30
Appropriation/Item Number: | 2660-108-3290
Year of Appropriation: | 2020-21
Appropriation Unit: | 21108
Program Code | 20.30
District | Parties to Agreement (Agency) | Purpose of Project (Work Description) | Scope (Location) | Prefix | Project Id | Advantage Project Id | PPNO | Federal Program Code | Budgeted Amount | Expenditure Amount | Remaining Balance | CTC TUF Deadline | Is Project Consistent with Original Scope and Purpose of the Appropriation? If No, Please Explain: | Are You Requesting a CWA (Yes or No)? If No, provide an anticipated date the agency plans to submit invoice for the remaining balance | Reason for Delay | Please Provide a 2-3 Sentence Explanation Identifying Any Impediments to Completion | What are the Consequences if CWA is Not Approved? (Please Provide a 2-3 Sentence Explanation) | Local Agency Contact Name | Local Agency Contact Phone Number | Local Agency Contact Email | Approved by DOF (Yes or No)? | Revised Reversion Date
03 | West Sacramento | Pedestrian and Bike Overpass | 1500 foot overpass: Sycamore Park from Westmore Oaks School over United State Route 50 connecting Joey Lopes Park Phase 2 | CML | 5447(044) | 317000002 | 2215 |  | 3500000 | 3196524.2 | 303475.8 | 2026-02-03 | YES | YES | Contract Dispute/Litigation: Post-construction claim. Informal settlement. | During construction, disputes over the cause of delays to project completion, Pacific Gas and Electric (PG&E) utility delay, adjacent construction project work accessibility, and changes to hinge gap fill material resulted in completion schedule beyond the original scheduled date. Several meetings required to informally settle the dispute. | Construction funding would lapse and unable to submit final invoice for reimbursement which would make the City of West Sacramento (City) out of compliance and negatively impact the City's finances and other planned projects. | Ryan Teves | (916) 617-4665 | ryant@cityofwestsacramento.org | Yes | 2028-06-30
07 | Southern California Association of Governments | Sustainable Communities Program. Pedestrian Safety Program | In the Cities of Los Angeles, Pomona, Banning and Lynwood, County of Los Angeles, and Orange County Transportation Authority (OCTA) service area. | ATPLNI | 6049(025) | 0722000041 | 5899 |  | 1880000 | 1306545.56 | 573454.44 | 2026-08-31 | YES | YES | Finance: California Transportation Commission (CTC) approved Time Extension conflicts with reversion date. Reason for Delay: The consultant originally selected, in September 2022, to deliver the Pomona plan did not provide satisfactory performance. Approximately 20 percent of the project scope was completed. As a result, in July 2023, the contract was canceled. A new Request for Proposal (RFP) to complete the remainder of the project was due September 2024, but due to a lack of proposals, the RFP deadline was extended to October 2024. A new contract was executed in April 2025. The Pomona Plan had one year remaining and needed the time extension to complete. Additionally, the OCTA and Los Angeles County plans were intended to be a joint project effort anticipated to begin the summer of 2023. However, the joint RFP was cancelled and separate RFPs were issued to complete the OCTA and LA County plans. These plans also needed a time extension to complete work by July 2026. | Given the reasons for delay described in cell P9, the project received a time extension for project completion from CTC, and with this time extension, the project does not anticipate any further impediments to completion. | Plans for Pomona, County of Los Angeles and Orange County Transportation Authority (OCTA) service areas will not be able to be completed despite receiving a time extension from the CTC and would negatively affect the traveling public. | Rachel Om | (213) 630-1550 | om@scag.ca.gov | Yes | 2028-06-30
07 | Southern California Association of Governments | Pomona Citywide Complete Streets Ordinance - Education, Evaluation & Engagement | City of Pomona | ATPLNI | 6049(026) | 0722000211 | 5958 |  | 176000 | 92323.92 | 83676.08 | 2026-09-30 | YES | YES | Finance: California Transportation Commission (CTC) approved Time Extension conflicts with reversion date. Reason for Delay: This non-infrastructure project was bundled with the Pomona plan component of ATPLNI 6049(025). The consultant originally selected, in September 2022, to deliver the Pomona plan did not provide satisfactory performance. Approximately 20 percent of the project scope was completed. As a result, in July 2023, the contract was canceled. A new Request for Proposal (RFP) to complete the remainder of the project was due September 2024, but due to a lack of proposals, the RFP deadline was extended to October 2024. A new contract was executed in April 2025. The Pomona Plan had one year remaining and needed the time extension to complete. | Given the reasons for delay described in cell P10, the project received a time extension for project completion from CTC, and with this time extension, the project does not anticipate any further impediments to completion. | Engagement for Pomona will not be able to be completed despite receiving a time extension from the CTC which would negatively affect the traveling public. | Rachel Om | (213) 630-1550 | om@scag.ca.gov | Yes | 2028-06-30
07 | Paramount | Bike Path | West Santa Ana Branch Bikeway Phase 2 in City of Paramount. | ATPSB1L | 5336(021) | 0718000231 | 5333 |  | 3078000 | 395997.38 | 2682002.62 | 2026-10-31 | YES | YES | Construction: Change in site conditions. | Contractor encountered contaminated soil during construction which delayed construction, required testing and removal of contaminated soil. | If CWA is not approved, the project's remaining bike path segment may not be constructed, creating a gap in the West Santa Ana Branch bike path which when completed will connect the city to it's neighboring cities as part of the cities' bicycle master plan. | Adriana Figueroa | (562) 220-2106 | afigueroa@paramountcity.gov | Yes | 2028-06-30
07 | Los Angeles | Implementation of Class I and Class IV bike facilities, pedestrian improvements, transit connections and traffic calming measures. | This project is located on Sepulveda Boulevard between Rinaldi Street and Rayan Street and on Brand Boulevard between Sepulveda Boulevard and Memory Park in the San Fernando Valley community. | ATPSB1L | 5006(920) | 0722000024 | 5896 |  | 2959969 | 0 | 2959969 | 2026-02-28 | YES | YES | Finance: California Transportation Commission (CTC) approved Time Extension conflicts with reversion date. The City has experienced delays due to the 2025 fires in Southern California. On January 7, 2025, a State of Emergency was declared by Governor Gavin Newsom in response to the devastating fires in Southern California. Following this declaration, on January 8, 2025, the Federal Emergency Management Agency approved a major disaster declaration of the affected areas. In April 2025, the unused balance of the Project Approval and Environmental Document (PA&ED) phase was transferred to the Plans, Specifications, and Estimate phase. As a result of the fires, a significant portion of City staff and utility partners were deployed as disaster service workers to support emergency operations at disaster recovery centers. The support and coordination for fire relief and recovery efforts due to the extraordinary and unforeseen circumstances caused by this natural disaster, has delayed project delivery. The City needs additional time to complete project activities. Therefore, the City is requested an additional 8-month project development expenditure time extension to allow sufficient time to process and finalize the PA&ED phase from June 30, 2025 to February 28, 2026. | Given the reasons for delay described in cell P12, the project received a time extension for project completion from CTC, and with this time extension, the project does not anticipate any further impediments to completion. | The allocated funds won’t be fully expended and the Mission Mile Sepulveda project will not transform Sepulveda Boulevard into a complete street that provides a safer environment for pedestrians and bicyclists, connects to future Metro transit corridors, elevates connections to community assets and cultural landmarks, and improves public health and environmental quality by potentially providing up to 21 acres of green space. | Ava Majidi | (213) 543-9267 | ava.majidi@lacity.org | Yes | 2028-06-30
[8 empty] | Total | 11593969 | 4991391.06 | 6602577.94

## Drop-down Reference Tables
Within Scope? | Need a CWA? | Primary Reason For Delay:
YES | YES | Design: Change in scope.
NO | NO | Design: Change in specifications.
Design: Change in site conditions.
Environmental: Change in scope requires additional studies/permits.
Environmental: Excessive study or opinion review time by external agencies.
Environmental: Permits expired.
Environmental: Environmental document determination revalidation required.
Environmental: Mitigation for project impacts period.
Right of Way and Utility Relocation: Change in scope/number of parcels/utility relocations required.
Right of Way and Utility Relocation: Condemnation/eminent domain proceedings.
Right of Way and Utility Relocation: Utility owner dispute.
Right of Way and Utility Relocation: Qualified Buy America purchase/delivery delays.
Construction: Contract award disputed/cancelled, rebid or complete under force account.
Construction: Change in site conditions.
Construction: Qualified Buy America purchase/delivery delays.
Construction: Extended winter suspension affecting delivery schedule.
Contract Dispute/Litigation: Post-construction claim. Informal settlement.
Contract Dispute/Litigation: Formal litigation proceeding.
Finance: CTC approved Time Extension conflicts with reversion date.
Finance: Indirect Cost Rate Proposal (ICRP) request package returned with errors.
Finance: Change in dedicated/programmed funding.
Finance: Pending programming.
OTHER-declared disaster (explain):
OTHER (explain):