## District 3
ATP Projects with Lapsing Senate Bill 1 Funds
Reversion Date: | 2026-06-30
Appropriation/Item Number: | 2660-108-3290
Year of Appropriation: | 2021
Appropriation Unit: | 21108
District | Parties to Agreement (Agency) | Purpose of Project (Work Description) | Scope (Location) | Prefix | Project Id | Advantage Project Id | PPNO | Federal Program Code | Budgeted Amount | Expenditure Amount | Remaining Balance | CTC TUF Deadline | Is Project Consistent with Original Scope and Purpose of the Appropriation? If No, Please Explain: | Are You Requesting a CWA (Yes or No)? If No, provide an anticipated date the agency plans to submit invoice for the remaining balance | Reason for Delay | Please Provide a 2-3 Sentence Explanation Identifying Any Impediments to Completion | What are the Consequences if CWA is Not Approved? (Please Provide a 2-3 Sentence Explanation) | Local Agency Contact Name | Local Agency Contact Phone Number | Local Agency Contact Email | Approved by DOF (Yes or No)? | Revised Reversion Date
03 | West Sacramento | Pedestrian and Bike Overpass | 1500' overpass: Sycamore Park from Westmore Oaks School over US 50 connecting Joey Lopes Park Phase 2 | CML | 5447(044) | 0317000002 | 2215 |  | 3500000 | 3196524.2 | 303475.8 | 2026-02-03

## District 7
ATP Projects with Lapsing Senate Bill 1 Funds
Reversion Date: | 2026-06-30
Appropriation/Item Number: | 2660-108-3290
Year of Appropriation: | 2021
Appropriation Unit: | 21108
District | Parties to Agreement (Agency) | Purpose of Project (Work Description) | Scope (Location) | Prefix | Project Id | Advantage Project Id | PPNO | Federal Program Code | Budgeted Amount | Expenditure Amount | Remaining Balance | CTC TUF Deadline | Is Project Consistent with Original Scope and Purpose of the Appropriation? If No, Please Explain: | Are You Requesting a CWA (Yes or No)? If No, provide an anticipated date the agency plans to submit invoice for the remaining balance | Reason for Delay | Please Provide a 2-3 Sentence Explanation Identifying Any Impediments to Completion | What are the Consequences if CWA is Not Approved? (Please Provide a 2-3 Sentence Explanation) | Local Agency Contact Name | Local Agency Contact Phone Number | Local Agency Contact Email | Approved by DOF (Yes or No)? | Revised Reversion Date
07 | Southern California Association of Governments | Sustainable Communities Program. Pedestrian Safety Program | In the Cities of Los Angeles, Pomona, Banning and Lynwood, County of Los Angeles, and OCTA service area. | ATPLNI | 6049(025) | 0722000041 | 5899 |  | 1880000 | 1306545.56 | 573454.44 | 2026-08-31
07 | Southern California Association of Governments | Pomona Citywide Complete Streets Ordinance - Education, Evaluation & Engagement | City of Pomona | ATPLNI | 6049(026) | 0722000211 | 5958 |  | 176000 | 92323.92 | 83676.08 | 2026-09-30
07 | Paramount | Bike Path | West Santa Ana Branch Bikeway Phase 2 in City of Paramount. | ATPSB1L | 5336(021) | 0718000231 | 5333 |  | 3078000 | 395997.38 | 2682002.62 | 2026-10-31
07 | Los Angeles | Implementation of Class I and Class IV bike facilities, pedestrian improvements, transit connections and traffic calming measures. | This project is located on Sepulveda Blvd. between Rinaldi St and Rayan St. and on Brand Blvd. between Sepulveda Blvd and Memory Park in the San Fernando Valley community. | ATPSB1L | 5006(920) | 722000024 | 5896 |  | 2959969 | 0 | 2959969 | 2026-02-28

## District 8
ATP Projects with Lapsing Senate Bill 1 Funds
Reversion Date: | 2026-06-30
Appropriation/Item Number: | 2660-108-3290
Year of Appropriation: | 2021
Appropriation Unit: | 21108
District | Parties to Agreement (Agency) | Purpose of Project (Work Description) | Scope (Location) | Prefix | Project Id | Advantage Project Id | PPNO | Federal Program Code | Budgeted Amount | Expenditure Amount | Remaining Balance | CTC TUF Deadline | Is Project Consistent with Original Scope and Purpose of the Appropriation? If No, Please Explain: | Are You Requesting a CWA (Yes or No)? If No, provide an anticipated date the agency plans to submit invoice for the remaining balance | Reason for Delay | Please Provide a 2-3 Sentence Explanation Identifying Any Impediments to Completion | What are the Consequences if CWA is Not Approved? (Please Provide a 2-3 Sentence Explanation) | Local Agency Contact Name | Local Agency Contact Phone Number | Local Agency Contact Email | Approved by DOF (Yes or No)? | Revised Reversion Date
08 | Moreno Valley | Class 1 pedestrian and bicycle trail | Juan Bautista de Anza Trail from Moreno Valley Mall (Eucalytpus Avenue) to Iris Avenue | ATPSB1L | 5441(076) | 0820000008 | 1258 |  | 7393000 | 0 | 7393000 | 2025-12-31

## District 9
ATP Projects with Lapsing Senate Bill 1 Funds
Reversion Date: | 2026-06-30
Appropriation/Item Number: | 2660-108-3290
Year of Appropriation: | 2021
Appropriation Unit: | 21108
District | Parties to Agreement (Agency) | Purpose of Project (Work Description) | Scope (Location) | Prefix | Project Id | Advantage Project Id | PPNO | Federal Program Code | Budgeted Amount | Expenditure Amount | Remaining Balance | CTC TUF Deadline | Is Project Consistent with Original Scope and Purpose of the Appropriation? If No, Please Explain: | Are You Requesting a CWA (Yes or No)? If No, provide an anticipated date the agency plans to submit invoice for the remaining balance | Reason for Delay | Please Provide a 2-3 Sentence Explanation Identifying Any Impediments to Completion | What are the Consequences if CWA is Not Approved? (Please Provide a 2-3 Sentence Explanation) | Local Agency Contact Name | Local Agency Contact Phone Number | Local Agency Contact Email | Approved by DOF (Yes or No)? | Revised Reversion Date
09 | Tehachapi | Pedestrian and Bike Path | On Dennison Rd between Tehachapi Blvd and Pinon St | ATP | 5184(040) | 0922000012 | 2684 |  | 24000 | 14824.28 | 9175.72 | 2027-08-05

## District 10
ATP Projects with Lapsing Senate Bill 1 Funds
Reversion Date: | 2026-06-30
Appropriation/Item Number: | 2660-108-3290
Year of Appropriation: | 2021
Appropriation Unit: | 21108
District | Parties to Agreement (Agency) | Purpose of Project (Work Description) | Scope (Location) | Prefix | Project Id | Advantage Project Id | PPNO | Federal Program Code | Budgeted Amount | Expenditure Amount | Remaining Balance | CTC TUF Deadline | Is Project Consistent with Original Scope and Purpose of the Appropriation? If No, Please Explain: | Are You Requesting a CWA (Yes or No)? If No, provide an anticipated date the agency plans to submit invoice for the remaining balance | Reason for Delay | Please Provide a 2-3 Sentence Explanation Identifying Any Impediments to Completion | What are the Consequences if CWA is Not Approved? (Please Provide a 2-3 Sentence Explanation) | Local Agency Contact Name | Local Agency Contact Phone Number | Local Agency Contact Email | Approved by DOF (Yes or No)? | Revised Reversion Date
10 | Stockton | Construct 5.4 miles of bicycle facilities, new and reconstructed curb ramps, speed cushions, RRFBs, and over 70 crosswalk installations/enhancements | Greater Downtown Stockton | ATPSB1L | 5008(200) | 1022000200 | 3538 |  | 30066.14 | 16346.83 | 13719.31 | 2026-02-28

## Drop-down Reference Tables
Within Scope? | Need a CWA? | Primary Reason For Delay:
YES | YES | Design: Change in scope.
NO | NO | Design: Change in specifications.
Design: Change in site conditions.
Environmental: Change in scope requires additional studies/permits.
Environmental: Excessive study or opinion review time by external agencies.
Environmental: Permits expired.
Environmental: Environmental document determination revalidation required.
Environmental: Mitigation for project impacts period.
Right of Way and Utility Relocation: Change in scope/number of parcels/utility relocations required.
Right of Way and Utility Relocation: Condemnation/eminent domain proceedings.
Right of Way and Utility Relocation: Utility owner dispute.
Right of Way and Utility Relocation: Qualified Buy America purchase/delivery delays.
Construction: Contract award disputed/cancelled, rebid or complete under force account.
Construction: Change in site conditions.
Construction: Qualified Buy America purchase/delivery delays.
Construction: Extended winter suspension affecting delivery schedule.
Contract Dispute/Litigation: Post-construction claim. Informal settlement.
Contract Dispute/Litigation: Formal litigation proceeding.
Finance: CTC approved Time Extension conflicts with reversion date.
Finance: Indirect Cost Rate Proposal (ICRP) request package returned with errors.
Finance: Change in dedicated/programmed funding.
Finance: Pending programming.
OTHER-declared disaster (explain):
OTHER (explain):