## District
Congested Corridors Program Projects with Lapsing Senate Bill 1 Funds
Reversion Date: | 2026-06-30
Appropriation/Item Number: | 2660-109-0042
Year of Appropriation: | 2020-21
Appropriation Unit: | 21109
Program Code | 30.10
District | Parties to Agreement (Agency) | Purpose of Project (Work Description) | Scope (Location) | Prefix | Advantage Project Id | Budgeted Amount | Expenditure Amount | Remaining Balance | Is Project Consistent with Original Scope and Purpose of the Appropriation? If No, Please Explain: | Are You Requesting a CWA (Yes or No)? If No, provide an anticipated date the agency plans to submit invoice for the remaining balance | Reason for Delay | Please Provide a 2-3 Sentence Explanation Identifying Any Impediments to Completion | What are the Consequences if CWA is Not Approved? (Please Provide a 2-3 Sentence Explanation) | Local Agency Contact Name | Local Agency Contact Phone Number | Local Agency Contact Email | Approved by DOF (Yes or No)? | Revised Reversion Date
03 | Roseville | South Placer Transit - Five new electric buses | In Placer and Sacramento counties. The Lincoln to Sacramento express bus service will begin in the City of Lincoln and then continue along the Highway 65 corridor with stops at the Galleria Mall, Sutter Hospital and Kaiser Hospital. The express bus service would then travel down Interstate 80 into Sacramento County and terminate at Sacramento Regional Transits Watt/Interstate 80 light rail station. The light rail service would then enable passengers to travel to and from downtown Sacramento, the Railyards and other key destinations within Sacramento County. This new express bus service is expected to operate on weekdays every 30 minutes between approximately 6 a.m. and 9 p.m. The service will be provided using five (5) new 40 foot battery electric buses (4 buses and 1 spare). | SCCP | 0322000207 | 4705000 | 0 | 4705000 | YES | YES | OTHER (explain): The original bus manufacturer (Proterra) went through a bankruptcy, which created a delay in the production of the buses. | The original bus manufacturer (Proterra) went through a bankruptcy, which created a delay in the production of the buses. Phoenix Motor Cars purchased Proterra and is currently building the buses. | If the CWA extension is not approved, the City of Roseville may not be able to get all of the project invoices submitted prior to original reversion date which would make the city out of compliance for the contract and negatively affect the city's finances and other planned projects. There are still invoices pending to get the buses into service, such as registration, inspection, service testing, and final supplier payments. | Ed Scofield | (916) 774-5449 | ecscofield@roseville.ca.us | Yes | 2028-06-30
12 | Orange County Transportation Authority | The project will install real-time display and signage at up to 23 bus stops along the Bravo! Main Street Rapid Bus and Orange County Bus Route 53/53X corridor. Additionally, the project includes performance testing and support services for the real-time displays and signage following project implementation. | Route 53/53X operates from Anaheim through Orange and Santa Ana to Irvine via Main Street and Bravo! Main Street Rapid Bus (Route 533) operates on Main Street from Anaheim Regional Transportation Intermodal Center to MacArthur Boulevard in Santa Ana. | SCCP | 1221000006 | 230000 | 142465.18 | 87534.82 | YES | YES | Finance: California Transportation Commission (CTC) approved Time Extension conflicts with reversion date. At allocation in June 2021 the CTC approved an additional 36-months beyond the normal 36-month deadline for project expenditure/completion due to project needs attributing to licensing, software, and testing. The approved project expenditure/completion period for reimbursement of eligible expenditures is through 12/21/2027 and guidelines allow agencies an additional six months to reconcile, close-out, and request final reimbursement. | CTC approved Time Extension conflicts with reversion date. At allocation in June 2021 the CTC approved an additional 36-months beyond the normal 36-month deadline for project expenditure/completion due to project needs attributing to licensing, software, and testing. The approved project expenditure/completion period for reimbursement of eligible expenditures is through 12/21/2027 and guidelines allow agencies an additional six months to reconcile, close-out, and request final reimbursement. Remaining expenses include Operations and Management costs to be completed by December 2026. Given the reasons for delay, the project received a time extension for project completion from CTC, and with this time extension, the project does not anticipate any further impediments to completion. | Without approval of CWA, completion of the project will not be possible which will negatively affect the traveling public. Orange County Transportation Authority (OCTA) will not be reimbursed for awarded and expended which would negatively effect the city's finances and other planned projects. | Louis Zhao | (714) 560-5494 | lzhao@octa.net | Yes | 2028-06-30
[5 empty] | Total | 4935000 | 142465.18 | 4792534.82

## Drop-down Reference Tables
Within Scope? | Need a CWA? | Primary Reason For Delay:
YES | YES | Design: Change in scope.
NO | NO | Design: Change in specifications.
Design: Change in site conditions.
Environmental: Change in scope requires additional studies/permits.
Environmental: Excessive study or opinion review time by external agencies.
Environmental: Permits expired.
Environmental: Environmental document determination revalidation required.
Environmental: Mitigation for project impacts period.
Right of Way and Utility Relocation: Change in scope/number of parcels/utility relocations required.
Right of Way and Utility Relocation: Condemnation/eminent domain proceedings.
Right of Way and Utility Relocation: Utility owner dispute.
Right of Way and Utility Relocation: Qualified Buy America purchase/delivery delays.
Construction: Contract award disputed/cancelled, rebid or complete under force account.
Construction: Change in site conditions.
Construction: Qualified Buy America purchase/delivery delays.
Construction: Extended winter suspension affecting delivery schedule.
Contract Dispute/Litigation: Post-construction claim. Informal settlement.
Contract Dispute/Litigation: Formal litigation proceeding.
Finance: CTC approved Time Extension conflicts with reversion date.
Finance: Indirect Cost Rate Proposal (ICRP) request package returned with errors.
Finance: Change in dedicated/programmed funding.
Finance: Pending programming.
OTHER-declared disaster (explain):
OTHER (explain):