## District 4
ATP Projects with Lapsing State Funds
Reversion Date: | 2026-06-30
Appropriation/Item Number: | 2660-108-0042
Year of Appropriation: | 2021
Appropriation Unit: | 21108
District | Parties to Agreement (Agency) | Purpose of Project (Work Description) | Scope (Location) | Prefix | Project Number | Advantage Project Id | PPNO | Phase | Federal Program Code | Budgeted Amount | Expenditure Amount | Remaining Balance | CTC TUF Deadline | Is Project Consistent with Original Scope and Purpose of the Appropriation? If No, Please Explain: | Are You Requesting a CWA (Yes or No)? If No, provide an anticipated date the agency plans to submit invoice for the remaining balance | Reason for Delay | Please Provide a 2-3 Sentence Explanation Identifying Any Impediments to Completion | What are the Consequences if CWA is Not Approved? (Please Provide a 2-3 Sentence Explanation) | Local Agency Contact Name | Local Agency Contact Phone Number | Local Agency Contact Email | Approved by DOF (Yes or No)? | Revised Reversion Date
04 | Vallejo | Bike Path | The project will construct Class I and II gap closures on the Bay Trail/Vine Trail networks in Vallejo from the Vallejo Ferry Terminal north to the City of American Canyon. | ATPL | 5030(063) | 0418000099 | 2317 | 4 |  | 4216000 | 4005200 | 210800 | 2026-07-11

## District 7
ATP Projects with Lapsing State Funds
Reversion Date: | 2026-06-30
Appropriation/Item Number: | 2660-108-0042
Year of Appropriation: | 2021
Appropriation Unit: | 21108
District | Parties to Agreement (Agency) | Purpose of Project (Work Description) | Scope (Location) | Prefix | Project Number | Advantage Project Id | PPNO | Phase | Federal Program Code | Budgeted Amount | Expenditure Amount | Remaining Balance | CTC TUF Deadline | Is Project Consistent with Original Scope and Purpose of the Appropriation? If No, Please Explain: | Are You Requesting a CWA (Yes or No)? If No, provide an anticipated date the agency plans to submit invoice for the remaining balance | Reason for Delay | Please Provide a 2-3 Sentence Explanation Identifying Any Impediments to Completion | What are the Consequences if CWA is Not Approved? (Please Provide a 2-3 Sentence Explanation) | Local Agency Contact Name | Local Agency Contact Phone Number | Local Agency Contact Email | Approved by DOF (Yes or No)? | Revised Reversion Date
07 | Los Angeles | Pedestrian and Bike Path | The one-quarter mile radius around the Panorama City Elementary School in the San Fernando Valley in the City of Los Angeles. | ATPL | 5006(921) | 0722000034 | 5866 | 0 |  | 756000 | 73495.45 | 682504.55 | 2026-07-11
07 | Baldwin Park | Construct 2.3m of CL I shared-use path. Develop designs for 6.8m CL I trail & 15.3m of on-street CL II & III bikeways. Administer education. | Walnut Creek-San Gabriel River East Bank Greenway and Neighborhood Connections | ATPL | 5323(039) | 0721000068 | 5427A | 4 |  | 573000 | 0 | 573000 | 2026-09-30
07 | Baldwin Park | Non-Infrastructure project. Supportive education, encouragement, and evaluation programs administered thru-out the project area | City of Baldwin Park | ATPLNI | 5323(038) | 0720000125 | 5427B | 4 |  | 104000 | 0 | 104000 | 2026-09-30

## District 10
ATP Projects with Lapsing State Funds
Reversion Date: | 2026-06-30
Appropriation/Item Number: | 2660-108-0042
Year of Appropriation: | 2021
Appropriation Unit: | 21108
District | Parties to Agreement (Agency) | Purpose of Project (Work Description) | Scope (Location) | Prefix | Project Number | Advantage Project Id | PPNO | Phase | Federal Program Code | Budgeted Amount | Expenditure Amount | Remaining Balance | CTC TUF Deadline | Is Project Consistent with Original Scope and Purpose of the Appropriation? If No, Please Explain: | Are You Requesting a CWA (Yes or No)? If No, provide an anticipated date the agency plans to submit invoice for the remaining balance | Reason for Delay | Please Provide a 2-3 Sentence Explanation Identifying Any Impediments to Completion | What are the Consequences if CWA is Not Approved? (Please Provide a 2-3 Sentence Explanation) | Local Agency Contact Name | Local Agency Contact Phone Number | Local Agency Contact Email | Approved by DOF (Yes or No)? | Revised Reversion Date
10 | Waterford | Non-infrastructure component of Waterford's SR2S Crosswalks Safety Project | Throughout the City of Waterford | ATPLNI | 5406(031) | 1021000189 | 3272B | 4 |  | 12000 | 0 | 12000 | 2025-12-31

## Drop-down Reference Tables
Within Scope? | Need a CWA? | Primary Reason For Delay:
YES | YES | Design: Change in scope.
NO | NO | Design: Change in specifications.
Design: Change in site conditions.
Environmental: Change in scope requires additional studies/permits.
Environmental: Excessive study or opinion review time by external agencies.
Environmental: Permits expired.
Environmental: Environmental document determination revalidation required.
Environmental: Mitigation for project impacts period.
Right of Way and Utility Relocation: Change in scope/number of parcels/utility relocations required.
Right of Way and Utility Relocation: Condemnation/eminent domain proceedings.
Right of Way and Utility Relocation: Utility owner dispute.
Right of Way and Utility Relocation: Qualified Buy America purchase/delivery delays.
Construction: Contract award disputed/cancelled, rebid or complete under force account.
Construction: Change in site conditions.
Construction: Qualified Buy America purchase/delivery delays.
Construction: Extended winter suspension affecting delivery schedule.
Contract Dispute/Litigation: Post-construction claim. Informal settlement.
Contract Dispute/Litigation: Formal litigation proceeding.
Finance: CTC approved Time Extension conflicts with reversion date.
Finance: Indirect Cost Rate Proposal (ICRP) request package returned with errors.
Finance: Change in dedicated/programmed funding.
Finance: Pending programming.
OTHER-declared disaster (explain):
OTHER (explain):