## STIP State
STIP Projects with Lapsing State Funds
Reversion Date: | 2026-06-30
Appropriation/Item Number: | 2660-101-0042
Year of Appropriation: | 2020-21
Appropriation Unit: | 21101
Program Code: | 20.30
District | Parties to Agreement (Agency) | Purpose of Project (Work Description) | Scope (Location) | Prefix | Project Id | Advantage Project Id | PPNO | Federal Program Code | Budgeted Amount | Expenditure Amount | Remaining Balance | CTC TUF Deadline | Is Project Consistent with Original Scope and Purpose of the Appropriation? If No, Please Explain: | Are You Requesting a CWA (Yes or No)? If No, provide an anticipated date the agency plans to submit invoice for the remaining balance | Reason for Delay | Please Provide a 2-3 Sentence Explanation Identifying Any Impediments to Completion | What are the Consequences if CWA is Not Approved? (Please Provide a 2-3 Sentence Explanation) | Local Agency Contact Name | Local Agency Contact Phone Number | Local Agency Contact Email | Approved by DOF (Yes or No)? | Revised Reversion Date
02 | Tehama County | Bridge Replacement. | In Tehama County on South Fork Cottonwood Creek Bridge at Evergreen Road (Br #08C-008). | BRLOZB | 5908(025) | 0200000352 | 2379 |  | 999370 | 834370 | 165000 | 2026-12-31 | YES | YES | Environmental: Mitigation for project impacts period. | The project has not been delayed. The project required Limited Treatment Conditioning, and Erosion Control (LTEC) that prolonged the project closeout project timeline longer than estimated. | If the CWA is not approved the goal for the project closeout will be paused until CWA date is extended. As well, if the funding is lost, it will negatively affect the County's finances and other planned safety projects. | Danielle Peterson Blake Rampey Shad Jacobe | (530)385-1462, x3017 (530)385-1462, x3043 (530)385-1462 x3013 | dpeterson@tcpw.ca.gov rrampey@tcpw.ca.gov sjacobe@tcpw.ca.gov | Yes | 2028-06-30
02 | Tehama County | Bridge Replacement. | In Tehama County on South Fork Cottonwood Creek Bridge at Evergreen Road (Br #08C-008). | BRLOZB | 5908(025) | 0200000352 | 2379 |  | 2685630 | 2286609.81 | 399020.19 | 2026-12-31 | YES | YES | Environmental: Mitigation for project impacts period. | The project has not been delayed. The project required Limited Treatment Conditioning, and Erosion Control (LTEC) that prolonged the project closeout project timeline longer than estimated. | If the CWA is not approved the goal for the project closeout will be paused until CWA date is extended. As well, if the funding is lost, it will negatively affect the County's finances and other planned safety projects. | Danielle Peterson Blake Rampey Shad Jacobe | (530)385-1462, x3017 (530)385-1462, x3043 (530)385-1462 x3013 | dpeterson@tcpw.ca.gov rrampey@tcpw.ca.gov sjacobe@tcpw.ca.gov | Yes | 2028-06-30
02 | Siskiyou County | Road Rehabilitation. | In Siskiyou County near Weed on Jackson Ranch Road for the entire 5 mile length. | RPL | 5902(087) | 0220000131 | 2603 |  | 25000 | 24912.94 | 87.06 | 2024-06-30 | YES | YES | Finance: Change in dedicated/programmed funding. | The remaining funds would need to be moved to Plans, Specifications, and Estimates (PS&E) to utilize them. | Loss of $87.06 in project funding that could be utilized in PS&E which would help assist with the road rehabilitation to provide a safer roadway for its users. | Teresa Lemos | (530) 842-8258 | tlemos@co.siskiyou.ca.us | Yes | 2028-06-30
10 | Stanislaus Council of Governments | Planning, Programming and Monitoring. | Throughout Stanislaus County. | BRLOZB | 6089(091) | 1022000197 | 9953 |  | 214000 | 0 | 214000 | 2024-06-30 | YES | YES | OTHER (explain): Stanislaus Council of Governments is in the middle of multiple audits. Trying to complete an application for Indirect Cost Allocation Plan (ICAP) to be approved. Complete an amendment on the Overall Work Program (OWP) Fiscal Year 25-26. Prepare and complete the 26-27 OWP. | Stanislaus Council of Governments is in the middle of multiple audits. Trying to complete an application for Indirect Cost Allocation Plan (ICAP) to be approved. Complete an amendment on the Overall Work Program (OWP) Fiscal Year 25-26. Prepare and complete the 26-27 OWP. | The consequence would be losing the availability to the funds and Stanislaus Council of Governments would not be able to create a project development cost. | Jennifer Graham | (209) 525-4643 | jgraham@stancog.org | Yes | 2028-06-30
[8 empty] | Total | 3924000 | 3145892.75 | 778107.25

## Drop-down Reference Tables
Within Scope? | Need a CWA? | Primary Reason For Delay:
YES | YES | Design: Change in scope.
NO | NO | Design: Change in specifications.
Design: Change in site conditions.
Environmental: Change in scope requires additional studies/permits.
Environmental: Excessive study or opinion review time by external agencies.
Environmental: Permits expired.
Environmental: Environmental document determination revalidation required.
Environmental: Mitigation for project impacts period.
Right of Way and Utility Relocation: Change in scope/number of parcels/utility relocations required.
Right of Way and Utility Relocation: Condemnation/eminent domain proceedings.
Right of Way and Utility Relocation: Utility owner dispute.
Right of Way and Utility Relocation: Qualified Buy America purchase/delivery delays.
Construction: Contract award disputed/cancelled, rebid or complete under force account.
Construction: Change in site conditions.
Construction: Qualified Buy America purchase/delivery delays.
Construction: Extended winter suspension affecting delivery schedule.
Contract Dispute/Litigation: Post-construction claim. Informal settlement.
Contract Dispute/Litigation: Formal litigation proceeding.
Finance: CTC approved Time Extension conflicts with reversion date.
Finance: Indirect Cost Rate Proposal (ICRP) request package returned with errors.
Finance: Change in dedicated/programmed funding.
Finance: Pending programming.
OTHER-declared disaster (explain):
OTHER (explain):