## District 2
STIP Projects with Lapsing State Funds
Reversion Date: | 2025-06-30
Appropriation/Item Number: | 2660-101-0042
Year of Appropriation: | 1920
Appropriation Unit: | 20101
District | Parties to Agreement (Agency) | Purpose of Project (Work Description) | Scope (Location) | Prefix | Project Id | Advantage Project Id | PPNO | Federal Program Code | Budgeted Amount | Expenditure Amount | Remaining Balance | CTC TUF Deadline | Is Project Consistent with Original Scope and Purpose of the Appropriation? If No, Please Explain: | Are You Requesting a CWA (Yes or No)? If No, provide an anticipated date the agency plans to submit invoice for the remaining balance | Reason for Delay | Please Provide a 2-3 Sentence Explanation Identifying Any Impediments to Completion | What are the Consequences if CWA is Not Approved? (Please Provide a 2-3 Sentence Explanation) | Local Agency Contact Name | Local Agency Contact Phone Number | Local Agency Contact Email | Approved by DOF (Yes or No)? | Revised Reversion Date
02 | Tehama County | Bridge Replacement | In Tehama County on SF Cottonwood Creek Bridge @ Evergreen Road (Br #08C-008) | BRLOZB | 5908(025) | 0200000352 | 2379 |  | 999370 | 834370 | 165000 | 2026-12-31
02 | Tehama County | Bridge Replacement | In Tehama County on SF Cottonwood Creek Bridge @ Evergreen Road (Br #08C-008) | BRLOZB | 5908(025) | 0200000352 | 2379 |  | 2685630 | 2286609.81 | 399020.19 | 2026-12-31
02 | Alturas | Road Rehabilitation | West 8th Street Rehab between Warner Street and West C Street | RPL | 5120(009) | 0222000027 | 2584 |  | 1000 | 0 | 1000 | 2024-06-30
02 | Alturas | Road Rehabilitation | West 8th Street Rehab between Warner Street and West C Street | RPL | 5120(009) | 0222000027 | 2584 |  | 99000 | 96309.68 | 2690.32 | 2024-06-30
02 | Alturas | Road Rehabilitation | West 8th Street Rehab between Warner Street and West C Street | RPL | 5120(009) | 0222000027 | 2584 |  | 5000 | 0 | 5000 | 2024-06-30
02 | Alturas | Road Rehabilitation | Court Street Phase 1 Rehab from 1st Street to 4th Street | RPL | 5120(010) | 0222000028 | 2591 |  | 1000 | 0 | 1000 | 2024-06-30
02 | Alturas | Road Rehabilitation | Court Street Phase 1 Rehab from 1st Street to 4th Street | RPL | 5120(010) | 0222000028 | 2591 |  | 39000 | 11240.47 | 27759.53 | 2024-06-30
02 | Alturas | Road Rehabilitation | Court Street Phase 1 Rehab from 1st Street to 4th Street | RPL | 5136(010) | 0220000139 | 2594 |  | 5000 | 3665.88 | 1334.12 | 2024-06-30
02 | Siskiyou County | Road Rehabilitation | In Siskiyou county near Weed on Jackson Ranch Road for the entire 5 mile length. | RPL | 5902(087) | 0220000131 | 2603 |  | 25000 | 24912.94 | 87.06 | 2024-06-30
02 | Susanville | Pedestrian and Bike Path | Riverside Drive in City of Susanville. | RPSTPLE | 5116(014) | 0212000166 | 2480 |  | 50000 | 0 | 50000 | 2024-12-31

## District 10
STIP Projects with Lapsing State Funds
Reversion Date: | 2025-06-30
Appropriation/Item Number: | 2660-101-0042
Year of Appropriation: | 1920
Appropriation Unit: | 20101
District | Parties to Agreement (Agency) | Purpose of Project (Work Description) | Scope (Location) | Prefix | Project Id | Advantage Project Id | PPNO | Federal Program Code | Budgeted Amount | Expenditure Amount | Remaining Balance | CTC TUF Deadline | Is Project Consistent with Original Scope and Purpose of the Appropriation? If No, Please Explain: | Are You Requesting a CWA (Yes or No)? If No, provide an anticipated date the agency plans to submit invoice for the remaining balance | Reason for Delay | Please Provide a 2-3 Sentence Explanation Identifying Any Impediments to Completion | What are the Consequences if CWA is Not Approved? (Please Provide a 2-3 Sentence Explanation) | Local Agency Contact Name | Local Agency Contact Phone Number | Local Agency Contact Email | Approved by DOF (Yes or No)? | Revised Reversion Date
10 | Stanislaus Council of Governments | Planning,Programming and Monitoring | Throughout Stanislaus County | BRLOZB | 6089(091) | 1022000197 | 9953 |  | 214000 | 0 | 214000 | 2024-06-30

## Drop-down Reference Tables
Within Scope? | Need a CWA? | Primary Reason For Delay:
YES | YES | Design: Change in scope.
NO | NO | Design: Change in specifications.
Design: Change in site conditions.
Environmental: Change in scope requires additional studies/permits.
Environmental: Excessive study or opinion review time by external agencies.
Environmental: Permits expired.
Environmental: Environmental document determination revalidation required.
Environmental: Mitigation for project impacts period.
Right of Way and Utility Relocation: Change in scope/number of parcels/utility relocations required.
Right of Way and Utility Relocation: Condemnation/eminent domain proceedings.
Right of Way and Utility Relocation: Utility owner dispute.
Right of Way and Utility Relocation: Qualified Buy America purchase/delivery delays.
Construction: Contract award disputed/cancelled, rebid or complete under force account.
Construction: Change in site conditions.
Construction: Qualified Buy America purchase/delivery delays.
Construction: Extended winter suspension affecting delivery schedule.
Contract Dispute/Litigation: Post-construction claim. Informal settlement.
Contract Dispute/Litigation: Formal litigation proceeding.
Finance: CTC approved Time Extension conflicts with reversion date.
Finance: Indirect Cost Rate Proposal (ICRP) request package returned with errors.
Finance: Change in dedicated/programmed funding.
Finance: Pending programming.
OTHER-declared disaster (explain):
OTHER (explain):