## District
ATP Projects with Lapsing Federal Funds
Reversion Date: | 2027-06-30
Appropriation/Item Number: | 2660-108-0890
Year of Appropriation: | 2122
Appropriation Unit: | 22108F
Program: | 2030
District | Parties to Agreement (Agency) | Purpose of Project (Work Description) | Scope (Location) | Prefix | Project Id | Advantage Project Id | PPNO | Advantage Phase | Phase | Federal Program Code | Budgeted Amount | Expenditure Amount | Remaining Balance | CTC TUF Deadline | Is Project Consistent with Original Scope and Purpose of the Appropriation? If No, Please Explain: | Are You Requesting a CWA (Yes or No)? If No, provide an anticipated date the agency plans to submit invoice for the remaining balance | Reason for Delay | If Other for Reason for Delay, Provide Explanation | Please Provide a 2-3 Sentence Explanation Identifying Any Impediments to Completion | What are the Consequences if CWA is Not Approved? (Please Provide a 2-3 Sentence Explanation) | Local Agency Contact Name | Local Agency Contact Phone Number | Local Agency Contact Email | Approved by DOF (Yes or No)? | Revised Reversion Date
04 | Oakland | Reduce Roadway from four (4) to two (2) Lanes, Install Class IV Bike Lanes | 14th Street from Brush Street to Oak Street | ATPL | 5012(154) | 0419000007 | 2307 | 4E3 | CON | Z301 | 260915.57 | 260915.56 | 0.01 | 2026-07-18
04 | Oakland | Reduce Roadway from four (4) to two (2) Lanes, Install Class IV Bike Lanes | 14th Street from Brush Street to Oak Street | ATPL | 5012(154) | 0419000007 | 2307 | 4E4 | CON | Z3E1 | 2106325 | 1841628.91 | 264696.09 | 2026-07-18
06 | Fresno | Paved path, lighting, benches, fencing, irrigation, signing and striping | Eastbound McKinley from Millbrook Avenue to Clovis Avenue along the north bank of the Mill Ditch canal | ATPL | 5060(380) | 0621000064 | 6907 | 3 | CON | Y300 | 180954 | 177454 | 3500 | 2026-12-14
06 | Fresno | Paved path, lighting, benches, fencing, irrigation, signing and striping | Eastbound McKinley from Millbrook Avenue to Clovis Avenue along the north bank of the Mill Ditch canal | ATPL | 5060(380) | 0621000064 | 6907 | 4 | CON | Y300 | 1375046 | 1335046 | 40000 | 2026-12-14
07 | Los Angeles | Pedestrian Walkway | Downtown Los Angeles Broadway Historic Theater District Pedestrian Improvements between 4th-6th Streets | ATPL | 5006(855) | 0717000120 | 5135 | 3 | CON | Y300 | 679791 | 276359.53 | 403431.47 | 2026-07-12
07 | Los Angeles | Pedestrian Walkway | Downtown Los Angeles Broadway Historic Theater District Pedestrian Improvements between 4th-6th Streets | ATPL | 5006(855) | 0717000120 | 5135 | 4 | CON | Y300 | 4982209 | 122637.59 | 4859571.41 | 2026-07-12
11 | San Diego Association of Governments | Bike Path | In the City of San Diego along Imperial Avenue from 21st to 47th Street 3.1 mile facility with buffered and protected bikeways, pedestrian improvements, and traffic calming improvements | ATPL | 6066(137) | 1118000175 | 1288 | 4 | CON | Y301 | 4450000 | 4268528.51 | 181471.49 | 2026-12-08

## Drop-down Reference Tables
Within Scope? | Need a CWA? | Primary Reason For Delay:
YES | YES | Design: Change in scope.
NO | NO | Design: Change in specifications.
Design: Change in site conditions.
Environmental: Change in scope requires additional studies/permits.
Environmental: Excessive study or opinion review time by external agencies.
Environmental: Permits expired.
Environmental: Environmental document determination revalidation required.
Environmental: Mitigation for project impacts period.
Right of Way and Utility Relocation: Change in scope/number of parcels/utility relocations required.
Right of Way and Utility Relocation: Condemnation/eminent domain proceedings.
Right of Way and Utility Relocation: Utility owner dispute.
Right of Way and Utility Relocation: Qualified Buy America purchase/delivery delays.
Construction: Contract award disputed/cancelled, rebid or complete under force account.
Construction: Change in site conditions.
Construction: Qualified Buy America purchase/delivery delays.
Construction: Extended winter suspension affecting delivery schedule.
Contract Dispute/Litigation: Post-construction claim. Informal settlement.
Contract Dispute/Litigation: Formal litigation proceeding.
Finance: CTC approved Time Extension conflicts with reversion date.
Finance: Indirect Cost Rate Proposal (ICRP) request package returned with errors.
Finance: Change in dedicated/programmed funding.
Finance: Pending programming.
OTHER-declared disaster (explain):
OTHER (explain):