## District 0
Projects with Lapsing Federal Funds
Reversion Date: | 2027-06-30
Appropriation/Item Number: | 2660-102-0890
Year of Appropriation: | 2122
Appropriation Unit: | 22102F
Program: | 2030
District | Parties to Agreement (Agency) | Purpose of Project (Work Description) | Scope (Location) | Prefix | Project Id | Advantage Project Id | Advantage Phase | Federal Program Code | Budgeted Amount | Expenditure Amount | Remaining Balance | Federal Financial Constraint Date if Applicable within the CWA Timeline | Is Project Consistent with Original Scope and Purpose of the Appropriation? If No, Please Explain: | Are You Requesting a CWA (Yes or No)? If No, provide an anticipated date the agency plans to submit invoice for the remaining balance | Reason for Delay | If Other for Reason for Delay, Provide Explanation | Please Provide a 2-3 Sentence Explanation Identifying Any Impediments to Completion | What are the Consequences if CWA is Not Approved? (Please Provide a 2-3 Sentence Explanation) | Local Agency Contact Name | Local Agency Contact Phone Number | Local Agency Contact Email | Approved by DOF (Yes or No)? | Revised Reversion Date
0 | Caltrans | Discretionary Safety Grant Training | Statewide | N/A | N/A | 0024000012 | SE1 | Z442 | 117743.5 | 0 | 117743.5

## District 1
Projects with Lapsing Federal Funds
Reversion Date: | 2027-06-30
Appropriation/Item Number: | 2660-102-0890
Year of Appropriation: | 2122
Appropriation Unit: | 22102F
Program: | 2030
District | Parties to Agreement (Agency) | Purpose of Project (Work Description) | Scope (Location) | Prefix | Project Id | Advantage Project Id | Advantage Phase | Federal Program Code | Budgeted Amount | Expenditure Amount | Remaining Balance | Federal Financial Constraint Date if Applicable within the CWA Timeline | Is Project Consistent with Original Scope and Purpose of the Appropriation? If No, Please Explain: | Are You Requesting a CWA (Yes or No)? If No, provide an anticipated date the agency plans to submit invoice for the remaining balance | Reason for Delay | If Other for Reason for Delay, Provide Explanation | Please Provide a 2-3 Sentence Explanation Identifying Any Impediments to Completion | What are the Consequences if CWA is Not Approved? (Please Provide a 2-3 Sentence Explanation) | Local Agency Contact Name | Local Agency Contact Phone Number | Local Agency Contact Email | Approved by DOF (Yes or No)? | Revised Reversion Date
01 | Humboldt County | Restoration | Alderpoint Road Post Mile 5.00 | ER | 32L0(273) | 0118000007 | S | ER12 | 487041.9 | 477041.9 | 10000
01 | Humboldt County | Restoration | Alderpoint Road Post Mile 5.00 | ER | 32L0(273) | 0118000007 | SE4 | ER01 | 322777.55 | 285732.02 | 37045.53
01 | Humboldt County | Restoration | Alderpoint Road Post Mile 6.98/6.99 | ER | 32L0(278) | 0118000012 | SE1 | ER01 | 1014216.54 | 959080.2 | 55136.34
01 | Humboldt County | Restoration | Alderpoint Road Post Mile 7.25 | ER | 32L0(279) | 0118000013 | SE2 | ER01 | 1021704.23 | 890803.28 | 130900.95
01 | Humboldt County | Restoration | Alderpoint Road Post Mile 7.37 | ER | 32L0(280) | 0118000014 | SE2 | ER01 | 1116912.19 | 916856.26 | 200055.93
01 | Humboldt County | Restoration | Alderpoint Road Post Mile 7.37 | ER | 32L0(280) | 0118000014 | SE1 | ER11 | 149166.85 | 148747.93 | 418.92
01 | Humboldt County | Restoration | Mattole Road Post Mile 35.7 | ER | 40A0(015) | 0120000023 | SE1 | ER01 | 70758.47 | 70509.72 | 248.75
01 | Humboldt County | Restoration | Kneeland Road Post Mile 37.09 | ACSTP | 40A0(057) | 0120000012 | S | ER14 | 94288.94 | 93902.25 | 386.69
01 | Humboldt County | Restoration | Central Avenue Post Mile 4.30 | ER | 40A0(058) | 0120000015 | SE1 | ER01 | 59010.55 | 58589.12 | 421.43
01 | Humboldt County | Restoration | Mattole Road Post Mile 11.73 to 11.76 | ER | 40A0(059) | 0120000017 | S | ER01 | 512368.91 | 286002.66 | 226366.25
01 | Humboldt County | At seven sites excavate and place needed stabilization materials, replace culvert, and reconstruct roadbed and shoulder to former grade line and place surfacing | Alderpoint Road Post Mile 40.21 to 40.70, in Humboldt County Damage Assessment Form (DAF) Number KBT-HUM-069-0 | ER | 4400(046) | 0100000549 | SE6 | ER01 | 131198.07 | 94198.07 | 37000
01 | Mendocino County | Emergency Opening and Restoration | Mountain View Road Post Mile 1.65 | ER | 40A0(038) | 0120000063 | SE1 | ER01 | 70823 | 30586.76 | 40236.24
01 | Mendocino County | Revegetation and Mitigation Monitoring for Bridge Replacement Project BRLO-5910(077) | East Hill Road over Davis Creek; Bridge Number 10C0113 | BRLO | 5910(112) | 0117000002 | SE1 | L11E | 71000 | 59135.29 | 11864.71
01 | Mendocino County | Seismic Retrofit | Eureka Hill Road Bridge over Garcia River 10C0034 Daughter project for BRLRT-5910(041) | BRLRT | 5910(114) | 0117000005 | S | L110 | 20000 | 0 | 20000
01 | Mendocino County | Seismic Retrofit | Eureka Hill Road Bridge over Garcia River 10C0034 Daughter project for BRLRT-5910(041) | BRLRT | 5910(114) | 0117000005 | SE1 | M233 | 109709.01 | 94789.06 | 14919.95
01 | Mendocino County | Seismic Retrofit | Eureka Hill Road Bridge over Garcia River 10C0034 Daughter project for BRLRT-5910(041) | BRLRT | 5910(114) | 0117000005 | SE2 | M2E3 | 10927.42 | 0 | 10927.42
01 | Mendocino County | Seismic Retrofit | Eureka Hill Road Bridge over Garcia River 10C0034 Daughter project for BRLRT-5910(041) | BRLRT | 5910(114) | 0117000005 | SE3 | Z233 | 213483.57 | 0 | 213483.57
01 | Lake County | Bridge Replacement | Cooper Creek Bridge at Witter Springs Road in Lake County, Bridge Number 14C-0119 | BRLO | 5914(078) | 0100020461 | SE4 | Y233 | 1615000 | 1580000 | 35000

## District 2
Projects with Lapsing Federal Funds
Reversion Date: | 2027-06-30
Appropriation/Item Number: | 2660-102-0890
Year of Appropriation: | 2122
Appropriation Unit: | 22102F
Program: | 2030
District | Parties to Agreement (Agency) | Purpose of Project (Work Description) | Scope (Location) | Prefix | Project Id | Advantage Project Id | Advantage Phase | Federal Program Code | Budgeted Amount | Expenditure Amount | Remaining Balance | Federal Financial Constraint Date if Applicable within the CWA Timeline | Is Project Consistent with Original Scope and Purpose of the Appropriation? If No, Please Explain: | Are You Requesting a CWA (Yes or No)? If No, provide an anticipated date the agency plans to submit invoice for the remaining balance | Reason for Delay | If Other for Reason for Delay, Provide Explanation | Please Provide a 2-3 Sentence Explanation Identifying Any Impediments to Completion | What are the Consequences if CWA is Not Approved? (Please Provide a 2-3 Sentence Explanation) | Local Agency Contact Name | Local Agency Contact Phone Number | Local Agency Contact Email | Approved by DOF (Yes or No)? | Revised Reversion Date
02 | Tehama County | Permanent Restoration | Corning Road at Bridge 08C0153: East Houghton Creek | ER | 40A0(066) | 0220000026 | S | ER01 | 74365.2 | 57689.08 | 16676.12
02 | Trinity County | Update guardrail at bridge approach with terminal end systems at 19 locations within Trinity County | Various Locations throughout Trinity County | HRRRL | 5905(118) | 0217000038 | SE1 | YS30 | 811869 | 52072.67 | 759796.33
02 | Lassen County | Bridge Replacement | Punkin Center Road (Bridge 07C0088) over Muddy Slough Number 1, about four (4) miles Southeast of Bieber | BRLO | 5907(061) | 0212000105 | SE3 | Z906 | 63768 | 55355.71 | 8412.29 | 9/30/2027 with Invoices due 7/1/2027
02 | Tehama County | Bridge Replacement with a portion of the funding coming from Seismic Funds, Proposition 1B | In Tehama County on South Fork Cottonwood Creek Bridge at Evergreen Road (Bridge #08C-008) | BRLOZB | 5908(025) | 0200000352 | 9 | M2E3 | 34329 | 0 | 34329
02 | Tehama County | Bridge Replacement on New Alignment | North of Red Bluff, On Jelly's Ferry Road at the Sacramento River (Bridge Number 08C-0043) | BRLSZD | 5908(031) | 0200000353 | SE5 | Z0E1 | 9426766 | 9426765.66 | 0.34

## District 3
Projects with Lapsing Federal Funds
Reversion Date: | 2027-06-30
Appropriation/Item Number: | 2660-102-0890
Year of Appropriation: | 2122
Appropriation Unit: | 22102F
Program: | 2030
District | Parties to Agreement (Agency) | Purpose of Project (Work Description) | Scope (Location) | Prefix | Project Id | Advantage Project Id | Advantage Phase | Federal Program Code | Budgeted Amount | Expenditure Amount | Remaining Balance | Federal Financial Constraint Date if Applicable within the CWA Timeline | Is Project Consistent with Original Scope and Purpose of the Appropriation? If No, Please Explain: | Are You Requesting a CWA (Yes or No)? If No, provide an anticipated date the agency plans to submit invoice for the remaining balance | Reason for Delay | If Other for Reason for Delay, Provide Explanation | Please Provide a 2-3 Sentence Explanation Identifying Any Impediments to Completion | What are the Consequences if CWA is Not Approved? (Please Provide a 2-3 Sentence Explanation) | Local Agency Contact Name | Local Agency Contact Phone Number | Local Agency Contact Email | Approved by DOF (Yes or No)? | Revised Reversion Date
03 | Butte County | Emergency Opening and Restoration | Oro Quincy Highway - Culverts 20-2 Damage Assessment Form (DAF) Number: LTP-BUTCO-003-0 | ER | 15A5(035) | 0322000008 | S | ER01 | 9426.5 | 5334.78 | 4091.72
03 | Glenn County | Restoration | Glenn County Retaining Walls - Forest Highway 7 (FH-7) 20-2 Damage Assessment Form (DAF) LTP-GLECO-001-0 | ER | 15A5(037) | 0322000066 | S | ER01 | 33389.08 | 11822.81 | 21566.27
03 | Sacramento | Rails to trails project | Along the unused rail corridor near Freeport Boulevard from Sutterville Road to South of Meadowview/Pocket Road (4.5 miles) | ATPL | 5002(189) | 0316000158 | SE2 | Y400 | 4359000 | 4096940 | 262060
03 | Sacramento | Bike Lane | In Sacramento, on Broadway, from State Route 99 to Martin Luther King Jr Boulevard | STPL | 5002(225) | 0321000113 | S | Z23E | 713000 | 673000 | 40000
03 | Sacramento | Road Rehabilitation | In the City of Sacramento - On Florin Road from 24th Street to Munson Way | LPPSTPL | 5002(226) | 0321000173 | S | Y230 | 500000 | 447423.72 | 52576.28
03 | Roseville | Construct roundabout | Washington Boulevard and All American City roundabout | CML | 5182(079) | 0320000053 | SE1 | Y400 | 3270426 | 2973873.38 | 296552.62
03 | Folsom | Construct four (4) lane Interchange | United States 50 at Empire Ranch Road | HPLULN | 5288(043) | 0318000300 | SE8 | Y230 | 2500000 | 0 | 2500000
03 | Folsom | Signal Synchronization | Throughout the City of Folsom | STPL | 5288(052) | 0322000204 | SE1 | Y230 | 485493 | 387291.61 | 98201.39
03 | Galt | Road Reconstruction | On Kost Road in the City of Galt West of Joy Drive and East of Maria Way | STPL | 5293(021) | 0323000014 | S | Y230 | 275000 | 147445.7 | 127554.3
03 | Galt | Pedestrian and Bike Path | In Galt on Walnut Avenue from Carillion to Elk HIlls Drive | STPL | 5293(022) | 0323000015 | S | Y230 | 216000 | 158375.64 | 57624.36
03 | Live Oak | Reconstruct roadway and restripe existing bicycle lanes | Pennington Road, from Connecticut Avenue to Broadway | STPL | 5297(007) | 0313000035 | SE1 | Y230 | 899357 | 813620 | 85737
03 | South Lake Tahoe | Pedestrian and Bike Path | Pioneer Trail from intersection of Larch Avenue to intersection of Ski Run Boulevard | STPL | 5398(014) | 0319000017 | SE1 | M400 | 300000 | 50724.05 | 249275.95
03 | Paradise | Construct a grade separated Class I bike-pedestrian facility | Oliver Road between Skyway and Valley View Road | CML | 5425(044) | 0319000247 | S | Z400 | 201712 | 95367.46 | 106344.54
03 | West Sacramento | Bike Path | Project spans Sacramento River from 2nd/D Street in West Sacramento, up to the top deck of the I Street Bridge to the Jibboom/I Street viaduct and into the Sacramento Valley Station | CML | 5447(055) | 0323000032 | S | Y400 | 2429000 | 401663.54 | 2027336.46
03 | Glenn County | Bridge Replacement (Bridge Number 11C-0011) | County Road R over the Glenn-Colusa Irrigation District (GCID) Canal 0.3 miles North of County Road 39 | BRLO | 5911(057) | 0313000290 | SE2 | Z907 | 102782 | 93202.85 | 9579.15 | 9/30/2027 with Invoices due 7/1/2027
03 | Butte County | Bridge Replacement | East Rio Bonito Road at Sutter Buttes Slough around 0.8 miles East of State Route 99 | BRLO | 5912(093) | 0300020679 | SE2 | Y233 | 244000 | 75948.35 | 168051.65
03 | Sierra County | Bridge Replacement | Plumbago Road at Kanaka Creek around 1.6 miles South of Alleghany | BRLO | 5913(058) | 0314000095 | S | M233 | 10000 | 4068.01 | 5931.99
03 | Sierra County | Bridge Replacement | Plumbago Road at Kanaka Creek around 1.6 miles South of Alleghany | BRLO | 5913(058) | 0314000095 | SE3 | Z906 | 11842 | 7123.96 | 4718.04 | 9/30/2027 with Invoices due 7/1/2027
03 | Colusa County | Bridge Replacement | Danley Road at Glenn-Colusa Canal, 0.7 miles North of Freshwater Road, Bridge 15C-57 | BRLO | 5915(054) | 0300000900 | S | L110 | 22133 | 0 | 22133
03 | Nevada County | Bridge Replacement | Hirschdale Road over Truckee River at Hinton | BRLO | 5917(092) | 0316000090 | SE2 | Z907 | 77343 | 32043 | 45300 | 9/30/2027 with Invoices due 7/1/2027
03 | Placer County | Roundabouts | Bell Road Interstate 80 Roundabouts | STPCML | 5919(135) | 0318000088 | SE2 | L400 | 427068 | 388068 | 39000
03 | Placer County | Construct new roundabout | State Route 267 / State Route 28 Intersection, Kings Beach Western Approach | STPL | 5919(136) | 0318000149 | SE2 | Y230 | 648000 | 514613.76 | 133386.24
03 | Sacramento County | Bridge Rehabilitation | Elverta Road at North Channel Dry Creek | BRLS | 5924(119) | 0300020799 | S | M230 | 300000 | 266000 | 34000
03 | Sacramento County | Bridge Replacement | Franklin Road at Mokelumne River Overflow around 1.8 miles North of San Joaquin County line | BRLS | 5924(155) | 0300020416 | SE3 | Y230 | 7844155 | 7844154.99 | 0.01
03 | Sacramento County | Bridge Replacement | New Hope Road over Grizzly Slough 0.5 miles North of the San Joaquin County Line | BRLS | 5924(190) | 0312000217 | SE1 | L1CE | 71866.95 | 54264.79 | 17602.16
03 | Sacramento County | Bridge Replacement | New Hope Road over Grizzly Slough 0.5 miles North of the San Joaquin County Line | BRLS | 5924(190) | 0312000217 | SE2 | Z001 | 98830.62 | 0 | 98830.62
03 | Sacramento County | Install Bicycle lanes, upgrade signals, Americans with Disability Act (ADA) improvements, install lighting | Florin Road between Franklin Boulevard and Power Inn Road (excluding the segment at the State Route 99 interchange). | HSIPL | 5924(235) | 0317000135 | SE2 | Z230 | 542955 | 461937.9 | 81017.1
03 | Sacramento County | Construct sidewalk gap closures, including crossing upgrades and Americans with Disability Act (ADA) curb ramp upgrades, Streetlight | Various locations in the South Sacramento area of Sacramento County, along Power Inn Road, Stevenson Avenue, Elsie Avenue, and Cottonwood Lane | RPSTPL | 5924(268) | 0322000181 | SE1 | L23E | 18319.95 | 18319.85 | 0.1
03 | Placer County Transportation Planning Agency | Pedestrian Improvements | Along State Route 49 from Interstate 80 to Dry Creek Road | HIPCML | 6158(082) | 0318000089 | SE4 | Z40E | 1690000 | 708568.32 | 981431.68
03 | Caltrans | Widen and construct bus/carpool lanes, transition/auxiliary & Northbound Class I bike path | State Route 51 (Capital City) Managed Lanes Project: N Street to El Camino Avenue | STPLN | 6203(056) | 0316000113 | 0SBVE1 | Y400 | 1000000 | 8828.46 | 991171.54
03 | Caltrans | Widen and construct bus/carpool lanes, transition/auxiliary & Northbound Class I bike path | State Route 51 (Capital City) Managed Lanes Project: N Street to El Camino Avenue | STPLN | 6203(056) | 0316000113 | 1SBV | Y400 | 1000000 | 0 | 1000000
03 | Caltrans | Improvements consisting of managed lanes in each direction, auxiliary lanes and Intelligent Transportation System (ITS) elements (Preliminary Engineering (PE) only) | Interstate 5 from just North of Sutterville Road to Yolo County line - Post Mile 22.0/34.2 | CMLN | 6203(061) | 0318000336 | 0SBV | Z230 | 2941000 | 2931063.21 | 9936.79
03 | Caltrans | Construct Intelligent Transportation System (ITS) infrastructure, acceleration/deceleration and auxiliary lanes | On Interstate 5 in Sacramento County, from 0.2 mile South of Arena Boulevard interchange to 0.4 mile South of Yolo County line | CML | 6203(063) | 0320000240 | 2SBV | Z40E | 26000 | 9680.47 | 16319.53
03 | Caltrans | Roadway Widening, Auxiliary Lane | In Roseville and Rocklin: Between State Route 65 and Rocklin Road on eastbound Interstate 80, and east of Douglas Boulevard to west of Riverside Avenue on westbound Interstate 80. | STPCRAL | STPCRAL-6203(067) | 0322000243 | 3SBV | Z972 | 275000 | 238971.25 | 36028.75 | 9/30/2029 with Invoices due 7/1/2029

## District 4
Projects with Lapsing Federal Funds
Reversion Date: | 2027-06-30
Appropriation/Item Number: | 2660-102-0890
Year of Appropriation: | 2122
Appropriation Unit: | 22102F
Program: | 2030
District | Parties to Agreement (Agency) | Purpose of Project (Work Description) | Scope (Location) | Prefix | Project Id | Advantage Project Id | Advantage Phase | Federal Program Code | Budgeted Amount | Expenditure Amount | Remaining Balance | Federal Financial Constraint Date if Applicable within the CWA Timeline | Is Project Consistent with Original Scope and Purpose of the Appropriation? If No, Please Explain: | Are You Requesting a CWA (Yes or No)? If No, provide an anticipated date the agency plans to submit invoice for the remaining balance | Reason for Delay | If Other for Reason for Delay, Provide Explanation | Please Provide a 2-3 Sentence Explanation Identifying Any Impediments to Completion | What are the Consequences if CWA is Not Approved? (Please Provide a 2-3 Sentence Explanation) | Local Agency Contact Name | Local Agency Contact Phone Number | Local Agency Contact Email | Approved by DOF (Yes or No)? | Revised Reversion Date
04 | San Jose | Bicycle Related - Other | In San Jose: From the existing San Francisco Bay Trail/Highway 237 Bikeway Trail to the Bay Trail designated parking spaces (adjacent to the publicly accessible Marriott Hotel) | HPLUL | 5005(086) | 0400001490 | SE1 | LY10 | 100000 | 40150.29 | 59849.71
04 | San Jose | Implement Safety Improvements including Median Islands, Americans with Disability Act (ADA) Curb Ramps, Speed Radar Signs, et cetera | San Jose: On McKee Road between Route 101 and Toyon Avenue | STPL | 5005(154) | 0419000079 | SE1 | Y230 | 6994933 | 6568779.81 | 426153.19
04 | Oakland | Bridge Rehabilitation | Leimert Boulevard Bridge over Sausal Creek Bridge Number 33C0215 | STPLZ | 5012(124) | 0414000358 | SE4 | Y001 | 3753672 | 3713724.29 | 39947.71
04 | Oakland | Reduce Roadway from four (4) to two (2) Lanes, Install Class IV Bike Lanes | 14th Street from Brush Street to Oak Street | ATPL | 5012(154) | 0419000007 | S | Z972 | 1000000 | 999613.65 | 386.35 | 9/30/2029 with Invoices due 7/1/2029
04 | Healdsburg | Complete Street Improvements | On Healdsburg Avenue from Powell Avenue to Passalaqua Road | STPL | 5027(023) | 0422000486 | SE1 | Y240 | 600000 | 512365.08 | 87634.92
04 | Vallejo | Install High-Intensity activated crosswalk beacon (High-Intensity Activated Crosswalk (HAWK)) at unsignalized intersections | Spring at Tregaskis, Broadway at Illinois, Springs at Heartwood, Springs at Lassan/Hilton and Broadway at Hampshire | HSIPL | 5030(065) | 0419000564 | SE1 | YS30 | 1155800 | 1115857.45 | 39942.55
04 | Pinole | Safety Improvements: Installation of traffic signals and signs | Intersection of Appian Way and Marlesta Road | STPL | 5126(019) | 0422000116 | S | Y230 | 350000 | 309999.99 | 40000.01
04 | Larkspur | Bridge Rehabilitation | Bon Air Bridge; between Eliseo/Bon Air intersection and Magnolia/Bon Air intersection Bon Air Bridge spans Corte Madera Creek | BHLS | 5166(015) | 0400001287 | SE5 | Y001 | 1574471.14 | 1574407.52 | 63.62
04 | Larkspur | Offsite mitigation work: restoration of tidal marsh and Americans with Disability Act (ADA) upgrades and improvements | Environmental mitigations for Bon Air Bridge (Bridge Number 27C0028) replacement | BHLS | 5166(025) | 0416000393 | S | Y001 | 2988240.35 | 2433464.09 | 554776.26
04 | South San Francisco | Complete Street Improvements Phase III | El Camino Real from Arroyo Drive to Kaiser Way | CML | 5177(040) | 0419000112 | SE1 | Y003 | 2995000 | 2944595.97 | 50404.03
04 | Sonoma County | Seismic Retrofit | Wohler Road Bridge over the Russian River Bridge Number 20C0155 | STPLZ | 5920(137) | 0413000089 | S | M233 | 350000 | 227796.09 | 122203.91
04 | Marin County | Bridge Replacement | San Geronimo Creek Bridge on Mountain View Road 0.01 miles South of Sir Francis Drake Boulevard | BRLO | 5927(094) | 0412000657 | SE2 | Z233 | 294624.52 | 102298.8 | 192325.72
04 | Marin County | Miscellaneous - Other | Various locations throughout Marin County | HSIPL | 5927(115) | 0417000043 | S | ZS30 | 191306.25 | 166306.25 | 25000
04 | Contra Costa County | Construct new two (2)-lane Bridge adjacent to existing bridge and demolish existing bridge | Byron Highway 1.4 miles Northwest of Alameda County Line | BRLS | 5928(104) | 0400020300 | SE3 | Z001 | 610857 | 14466.87 | 596390.13
04 | Santa Clara County | Bridge Replacement | 1.7 Miles South of Alma Bridge Road and 2.12 Miles South of Old Santa Cruz Highway in Los Gatos | BRLO | 5937(205) | 0416000438 | SE2 | Y233 | 471999.2 | 379566.67 | 92432.53
04 | Santa Clara County | Bridge Replacement | Aldercroft Heights Road over Los Gatos Creek, 2.12 mile South of Los Gatos Santa Cruz Road | BRLO | 5937(206) | 0417000076 | SE1 | Y233 | 326652.62 | 229513.78 | 97138.84
04 | Santa Clara County | Bridge Replacement | Aldercroft Heights Road over Los Gatos Creek, 2.12 miles South of Los Gatos Santa Cruz Road | BRLO | 5937(206) | 0417000076 | S | Z233 | 173347.38 | 131263.32 | 42084.06
04 | Santa Clara County | Bridge Replacement | Los Gatos Creek Bridge on Aldercroft Height Road 1.9 miles South of Alma Bridge Road and 2.32 miles South of Old Santa Cruz Highway | BRLS | 5937(207) | 0417000077 | SE1 | M233 | 144251.03 | 127715.85 | 16535.18
04 | Santa Clara County | Bridge Replacement | Los Gatos Creek Bridge on Aldercroft Height Road 1.9 miles South of Alma Bridge Road and 2.32 miles South of Old Santa Cruz Highway | BRLS | 5937(207) | 0417000077 | SE2 | Q110 | 25269.44 | 3879.81 | 21389.63
04 | Santa Clara County | Bridge Replacement | Los Gatos Creek Bridge on Aldercroft Height Road 1.9 miles South of Alma Bridge Road and 2.32 miles South of Old Santa Cruz Highway | BRLS | 5937(207) | 0417000077 | SE3 | Y233 | 330479.53 | 276260.37 | 54219.16
04 | Golden Gate Bridge, Highway And Transportation District | Bridge Rehabilitation - Construct Physical Suicide Deterrent System | Golden Gate Bridge Suicide Deterrent System | BRLS | 6003(051) | 0415000067 | SE8 | Z0E1 | 6057114 | 3963114 | 2094000
04 | Metropolitan Transportation Commission | Non-Infrastructure: Implement Priority Development Area (PDA) | San Francisco Bay Area: Regionwide: Planning Assistance to support transportation investments and improve their performance in priority development areas | STPLNI | 6084(232) | 0418000299 | SE1 | Z23E | 8950000 | 8576882.26 | 373117.74
04 | Metropolitan Transportation Commission | Provide safety and operational improvements for multimodal corridor | Napa County : State Route 29 Up Valley Corridor | STPL | 6084(268) | 0421000156 | S | Z24E | 2700000 | 1910385.47 | 789614.53
04 | Metropolitan Transportation Commission | Bike Share Capital Program | Fremont, Richmond, and Marin and Sonoma Counties, along the Safety, Mobility, Automated Real-time Traffic Management (SMART) Corridor: Various Locations | STPLNI | 6084(275) | 0422000280 | S | Y230 | 700000 | 498031.82 | 201968.18
04 | Metropolitan Transportation Commission | The regional mapping data services system will expose a set of predefined mapping related data Application Programming Interfaces (API) | Regionwide - Nine (9) county San Francisco Bay Area | STPLNI | 6084(277) | 0422000334 | S | Y230 | 1800000 | 1045623.97 | 754376.03
04 | Metropolitan Transportation Commission | Conduct preliminary engineering and planning studies | Various bridge corridors and corridor approaches | CML | 6084(282) | 0422000469 | S | Y003 | 12000000 | 4488127.88 | 7511872.12
04 | Metropolitan Transportation Commission | Regionwide Planning Activities and Plans Preparation Manual (PPM) | Multi Counties | STPLNI | 6084(284) | 0422000493 | SE2 | Z972 | 16727000 | 15137560.09 | 1589439.91 | 9/30/2029 with Invoices due 7/1/2029
04 | Metropolitan Transportation Commission | Regionwide Planning Activities and Planning, Programming and Monitoring | San Francisco Bay Area, Regionwide | STPLNI | 6084(285) | 0422000500 | S | Y230 | 49500000 | 25371869.97 | 24128130.03
04 | Metropolitan Transportation Commission | Non-Infrastructure Metropolitan Transportation Commission (MTC) Regional Streets and Roads Program | San Francisco Bay Area | STPLNI | 6084(288) | 0423000020 | S | Y240 | 10000000 | 6755797.57 | 3244202.43
04 | Caltrans | Enhance communication infrastructure | Along the Interstate 880 corridor | STPL | 6204(134) | 0419000044 | 1SBV | Y230 | 1740000 | 1430505.7 | 309494.3
04 | Solano Transportation Authority | Develop a countywide Connected Mobility Implementation Plan | Solano Countywide | STPL | 6249(052) | 0422000410 | S | Y230 | 500000 | 351647.65 | 148352.35
04 | City & County of San Francisco, MTA/Parking & Traffic | Safety Improvements | Folsom Street, between 2nd and 11th Street | CRAATPL | 6328(098) | 0421000359 | S | Z972 | 5000000 | 2108377.29 | 2891622.71 | 9/30/2029 with Invoices due 7/1/2029

## District 5
Projects with Lapsing Federal Funds
Reversion Date: | 2027-06-30
Appropriation/Item Number: | 2660-102-0890
Year of Appropriation: | 2122
Appropriation Unit: | 22102F
Program: | 2030
District | Parties to Agreement (Agency) | Purpose of Project (Work Description) | Scope (Location) | Prefix | Project Id | Advantage Project Id | Advantage Phase | Federal Program Code | Budgeted Amount | Expenditure Amount | Remaining Balance | Federal Financial Constraint Date if Applicable within the CWA Timeline | Is Project Consistent with Original Scope and Purpose of the Appropriation? If No, Please Explain: | Are You Requesting a CWA (Yes or No)? If No, provide an anticipated date the agency plans to submit invoice for the remaining balance | Reason for Delay | If Other for Reason for Delay, Provide Explanation | Please Provide a 2-3 Sentence Explanation Identifying Any Impediments to Completion | What are the Consequences if CWA is Not Approved? (Please Provide a 2-3 Sentence Explanation) | Local Agency Contact Name | Local Agency Contact Phone Number | Local Agency Contact Email | Approved by DOF (Yes or No)? | Revised Reversion Date
05 | Santa Cruz County | Emergency Opening and Restoration | Jamison Creek Road Post Mile 1.61 | ER | 32D0(004) | 0517000126 | SE1 | ER01 | 248955 | 19991.11 | 228963.89
05 | Santa Cruz County | Emergency Opening and Restoration | Smith Grade Post Mile 4.06 | ER | 32L0(020) | 0517000135 | SE1 | ER14 | 235576 | 11301.59 | 224274.41
05 | Santa Cruz County | Emergency Opening and Restoration | Hazel Dell Road Post Mile 2.0 | ER | 32L0(065) | 0517000156 | S | ER12 | 677196.21 | 617991.14 | 59205.07
05 | Santa Cruz County | Emergency Opening and Restoration | Browns Valley Road Post Mile 2.14 | ER | 32L0(081) | 0517000180 | SE2 | ER01 | 70014.4 | 56722.04 | 13292.36
05 | Santa Cruz County | Emergency Opening and Restoration | East Zayante Road Post Mile 0.59 | ER | 32L0(201) | 0517000220 | SE1 | ER01 | 32666 | 27666 | 5000
05 | Santa Cruz County | Emergency Opening and Restoration | North Rodeo Gluch Post Mile 4.31 | ER | 32L0(202) | 0517000219 | SE1 | ER14 | 428240.24 | 413240.24 | 15000
05 | Santa Cruz County | Emergency Opening and Restoration | Paulsen Road Post Mile 0.43 | ER | 32L0(222) | 0517000229 | S | ER12 | 191506 | 186506 | 5000
05 | Santa Cruz County | Emergency Opening and Restoration | Lompico Road Post Mile 1.22 | ER | 32L0(259) | 0517000236 | SE1 | ER14 | 288622 | 13137.06 | 275484.94
05 | Santa Cruz County | Restoration | Glenwood Drive Post Mile 2.02 | ER | 32L0(336) | 0518000014 | SE1 | ER10 | 8393.8 | 1585.33 | 6808.47
05 | Santa Cruz County | Restoration | Glenwood Drive Post Mile 2.02 | ER | 32L0(336) | 0518000014 | SE2 | ER11 | 6065.58 | 0 | 6065.58
05 | Santa Cruz County | Restoration | Glenwood Drive Post Mile 2.02 | ER | 32L0(336) | 0518000014 | S | ER12 | 22381.85 | 0 | 22381.85
05 | Santa Cruz County | Restoration | Glenwood Drive Post Mile 2.02 | ER | 32L0(336) | 0518000014 | SE3 | Z9W0 | 22702.77 | 0 | 22702.77
05 | Santa Cruz County | Restoration | Lompico Road Post Mile 0.80 | ER | 32L0(341) | 0518000021 | SE1 | ER11 | 72619 | 6816 | 65803
05 | Santa Cruz County | Emergency Opening and Restoration | Soquel -San Jose Road Post Mile 1.25 | ER | 40A0(002) | 0519000144 | S | ER01 | 369643.76 | 336657.59 | 32986.17
05 | Santa Barbara | Bridge Replacement - Environmental Mitigation & Monitoring | De Los Angeles Guerra Street at Mission Creek in Santa Barbara | BRLS | 5007(098) | 0522000081 | S | Y001 | 115089 | 22659.16 | 92429.84
05 | Monterey County | Bridge Rehabilitation | Bradley Road Bridge | BHLO | 5944(100) | 0500020201 | S | L11E | 340394.75 | 0 | 340394.75
05 | Monterey County | Bridge Rehabilitation | Bradley Road Bridge | BHLO | 5944(100) | 0500020201 | SE2 | Z233 | 100157.83 | 0 | 100157.83
05 | Monterey County | Bridge Rehabilitation | Bradley Road Bridge | BHLO | 5944(100) | 0500020201 | SE3 | Z2E3 | 307126 | 245917.56 | 61208.44
05 | Santa Barbara County | Bridge Replacement - Replace 2-lane bridge with 2-lane bridge | Bonita School Road over Santa Maria River, 0.3 miles North State Route 166 (Bridge 51C0230). | BRLO | 5951(151) | 0513000105 | SE3 | Z2E3 | 1850000 | 1656671 | 193329
05 | Santa Barbara County | Upgrade 3073 feet of rail to current standards at nine (9) locations | Various locations in the unincorporated areas of Santa Barbara County | HSIPL | 5951(169) | 0520000141 | S | ZS30 | 215800 | 215749.15 | 50.85
05 | Santa Barbara County | Mitigation and Monitoring of Replacement of existing two (2)-Lane bridge with new two (2)-Lane bridge | Fernald Point Lane at Romero Creek | BRLO | 5951(171) | 0520000164 | S | M233 | 85000 | 45259.03 | 39740.97
05 | Santa Barbara County | Bridge Replacement for low-water crossing (LWC) | Foothill Road at Cuyama River in Santa Barbara County low-water crossing (LWC) 00L0047 | BRLO | NBIL(512) | 0500020372 | SE3 | Y233 | 20100000 | 18819316.13 | 1280683.87
05 | Caltrans | High-Occupancy Vehicle (HOV) Lane | In Santa Barbara County on Route 101, 0.1 miles South of the San Ysidro Avenue Overcrossing to 0.1 miles North of the Olive Mill Overcrossing Construct High-Occupancy Vehicle (HOV) Lanes | CRAL | 6205(032) | 0522000025 | 4SBVE1 | Z970 | 2045098 | 1891612.06 | 153485.94 | 9/30/2029 with Invoices due 7/1/2029

## District 6
Projects with Lapsing Federal Funds
Reversion Date: | 2027-06-30
Appropriation/Item Number: | 2660-102-0890
Year of Appropriation: | 2122
Appropriation Unit: | 22102F
Program: | 2030
District | Parties to Agreement (Agency) | Purpose of Project (Work Description) | Scope (Location) | Prefix | Project Id | Advantage Project Id | Advantage Phase | Federal Program Code | Budgeted Amount | Expenditure Amount | Remaining Balance | Federal Financial Constraint Date if Applicable within the CWA Timeline | Is Project Consistent with Original Scope and Purpose of the Appropriation? If No, Please Explain: | Are You Requesting a CWA (Yes or No)? If No, provide an anticipated date the agency plans to submit invoice for the remaining balance | Reason for Delay | If Other for Reason for Delay, Provide Explanation | Please Provide a 2-3 Sentence Explanation Identifying Any Impediments to Completion | What are the Consequences if CWA is Not Approved? (Please Provide a 2-3 Sentence Explanation) | Local Agency Contact Name | Local Agency Contact Phone Number | Local Agency Contact Email | Approved by DOF (Yes or No)? | Revised Reversion Date
06 | Visalia | Roadway Widening: from an undivided two (2)-lane road to a four (4)-lane divided roadway | Riggin Avenue between Mooney Boulevard and Conyer Street | HIPL | 5044(140) | 0622000021 | S | Z905 | 813659 | 752489.17 | 61169.83 | 9/30/2027 with Invoices due 7/1/2027
06 | Visalia | Roadway Widening: from an undivided two (2)-lane road to a four (4)-lane divided roadway | Riggin Avenue between Mooney Boulevard and Conyer Street | HIPL | 5044(140) | 0622000021 | SE4 | Z919 | 192531 | 47663.98 | 144867.02 | 9/30/2029 with Invoices due 7/1/2029
06 | Visalia | Roadway Widening: from an undivided two (2)-lane road to a four (4)-lane divided roadway | Riggin Avenue between Mooney Boulevard and Conyer Street | HIPL | 5044(140) | 0622000021 | SE5 | Z921 | 192219.17 | 0 | 192219.17 | 9/30/2029 with Invoices due 7/1/2029
06 | Fresno | Asphalt concrete overlay and install curb and gutter, signal loop detectors, streetlights, and High-Intensity Activated CrossWalk (HAWK) | Polk Avenue from Gettysburg to Shaw Avenues | STPL | 5060(352) | 0619000056 | S | Z905 | 1376270 | 732694.77 | 643575.23 | 9/30/2027 with Invoices due 7/1/2027
06 | Fresno | Asphalt concrete overlay and install curb and gutter, signal loop detectors, streetlights, and High-Intensity Activated CrossWalk (HAWK) | Polk Avenue from Gettysburg to Shaw Avenues | STPL | 5060(352) | 0619000056 | SE1 | Z906 | 568630 | 0 | 568630 | 9/30/2027 with Invoices due 7/1/2027
06 | Fresno | Install two High-Intensity Activated CrossWalk (HAWK) signals, two (2) protected left turn signals and upgrade pedestrian countdown equipment | Fresno Street crossings at Thomas and San Jose Aves, Fresno & R Streets Intersection, Fresno Street and Clinton Avenue Intersection, and various intersections along Fresno Street from B Street to Friant Road | HSIPL | 5060(357) | 0619000125 | SE2 | YS30 | 2014500 | 2014400 | 100
06 | Fresno | Pedestrian and Bike Path | Herndon Canal from McKinley to Shields Avenues | CML | 5060(364) | 0619000170 | SE1 | Z0E3 | 3415300 | 99429.66 | 3315870.34
06 | Fresno | Install traffic signals, bike lane, streetlights, storm drain, sidewalk, curb ramp and turn pockets | McKinley and Blythe Avenues Intersection; McKinely Avenue (Northside) from Cecelia Avenue to 400 feet East of Blythe Avenue | CML | 5060(385) | 0621000109 | SE1 | Y400 | 265000 | 117524.29 | 147475.71
06 | Hanford | New Signal, including Americans with Disability Act (ADA) ramps and traffic channelization | In Hanford, at the Intersection of 12th Avenue and Hume Avenue | CML | 5091(065) | 0620000121 | S | Z400 | 44200 | 36707.6 | 7492.4
06 | Hanford | Install sidewalk and Americans with Disability Act (ADA) ramps | East Lacy Boulevard from 10th Avenue to State Route 43 | CML | 5091(066) | 0620000122 | SE1 | Y400 | 500000 | 460000 | 40000
06 | Bakersfield | Construct roadway and a Flyover | In Bakersfield Extend Hagemen Road easterly across State Route 99 and connect to State Route 204 | NCIIPL | 5109(201) | 0614000033 | S | Z972 | 2565000 | 181974.83 | 2383025.17 | 9/30/2029 with Invoices due 7/1/2029
06 | Bakersfield | Construct multi-use path across State Route 99 | Hageman Road Multi-use Path: connecting Standard Street easterly across State Route 99 to Buck Owens Boulevard | CML | 5109(271) | 0622000102 | S | Z0E3 | 5247756 | 8670.76 | 5239085.24
06 | Bakersfield | Signal Synchronization/Interconnect | California Avenue between Mohawk Street and Oak Street; Stockdale Highway between Coffee Road and H Street; Brundage Lane between Oak Street and Hughes Lane | CML | 5109(275) | 0622000204 | S | Z0E3 | 1239420 | 786682.56 | 452737.44
06 | Taft | Reconstruct and resurface the roadway, upgrade curb ramps, and replace striping | Taft - 10th Street from A Street to Crosswalk at Bike/pedestrian Path (approximately 250 feet North of Suppy Road). | RSTPL | 5193(043) | 0622000001 | S | Z240 | 288408 | 169992.57 | 118415.43
06 | Taft | Reconstruct and resurface the roadway, upgrade curb ramps, and replace striping | Taft - 10th Street from A Street to Crosswalk at Bike/pedestrian Path (approximately 250 feet North of Suppy Road). | RSTPL | 5193(043) | 0622000001 | SE1 | Z906 | 32000 | 1000 | 31000 | 9/30/2027 with Invoices due 7/1/2027
06 | Sanger | Bike Lanes and trail | Bethel Avenue from Jensen Avenue to 480 feet North of Florence Avenue, and Church Avenue from Indianila Avenue to Bethel Avenue Fowler Switch Canal between Bethel Avenue and Jensen Avenue | CML | 5197(042) | 0621000043 | S | Z40E | 190000 | 6300 | 183700
06 | Clovis | Interconnect Signals | Shepherd Avenue from Peach Avenue to DeWolf Avenue | CML | 5208(181) | 0622000090 | S | Z40E | 115089 | 70341.47 | 44747.53
06 | Wasco | Road Rehabilitation and striping | Central Avenue from Filburn Street to State Route 46 | STPL | 5287(061) | 0622000232 | S | Z230 | 68796 | 40990.6 | 27805.4
06 | Madera County | Replace two (2) lane Bridge with two (2) lane Bridge | Bridge 41C0149 on Avenue 16 1/2 over Dry Creek | BRLO | 5941(089) | 0612000006 | SE2 | Z906 | 482746 | 475558.63 | 7187.37 | 9/30/2027 with Invoices due 7/1/2027
06 | Madera County | County wide shoulder paving at various locations | Various Locations in Madera County | CML | 5941(122) | 0619000143 | S | Z400 | 48385 | 44180.23 | 4204.77
06 | Fresno County | Bridge Replacement , two (2) lane bridge to new four (4) lane bridge | Bridge 42C0175 on East Manning Avenue over Travers Creek | BRLS | 5942(198) | 0600020576 | SE4 | Y001 | 398385 | 202407.7 | 195977.3
06 | Fresno County | Roadway Widening | Millerton Road from Friant Road to Marina Drive | STPL | 5942(273) | 0616000166 | SE1 | Y230 | 146867 | 100900.42 | 45966.58
06 | Fresno County | Replace two (2) lane bridge with two (2) lane bridge | Bridge 42C0270 on Millerton Road over Little Dry Creek | BRLO | 5942(287) | 0618000119 | SE1 | L110 | 55112.22 | 0 | 55112.22
06 | Fresno County | Replace two (2) lane bridge with two (2) lane bridge | Bridge 42C0270 on Millerton Road over Little Dry Creek | BRLO | 5942(287) | 0618000119 | SE2 | M233 | 14923.78 | 0 | 14923.78
06 | Fresno County | Replace two (2) lane bridge with two (2) lane bridge | Bridge 42C0270 on Millerton Road over Little Dry Creek | BRLO | 5942(287) | 0618000119 | S | Y233 | 100000 | 91737.68 | 8262.32
06 | Fresno County | Road Rehabilitation/ Reconstruction, curb, gutter, sidewalk, and storm drainage | Mount Whitney Avenue from Marks Avenue to Blythe Avenue | STBG | 5942(308) | 0622000192 | S | Z23E | 822610 | 736760.34 | 85849.66
06 | Fresno County | Install traffic signals and related intersection improvements | Intersection of Millerton Road and Marina Drive | STPL | 5942(311) | 0622000227 | S | Z230 | 354120 | 289269.37 | 64850.63
06 | Fresno County | Construct eight (8)-feet and four (4)-feet wide paved shoulders on each side of new 24-feet travel way | American Avenue from Peach Avenue to Temperance Avenue | CML | 5942(312) | 0623000013 | S | Z0E3 | 302283 | 182637.56 | 119645.44
06 | Fresno County | Construct four (4)-foot and six (6)-foot shoulders and place Asphalt Concrete (AC) overlay | Adams Avenue from Locan Avenue to Academy Avenue | CML | 5942(313) | 0623000014 | S | Z0E3 | 692684 | 253994.03 | 438689.97
06 | Kings County | Install advance warning flashing beacons, flashing beacons at stop signs and a roundabout | Various Locations in Kings County | HSIPL | 5945(110) | 0619000131 | S | ZS30 | 97800 | 46745.86 | 51054.14
06 | Tulare County | Replace two (2) lane bridge with two (2) lane bridge | Bridge 46C0196 on M375A Mineral King Road over East Fork Kaweah River, | BRLO | 5946(106) | 0600020683 | SE4 | Y233 | 499900 | 490268.11 | 9631.89
06 | Tulare County | Replace two (2) lane bridge with two (2) lane bridge | Bridge 46C0263 on Avenue 174 over Friant-Kern Canal | BRLO | 5946(140) | 0614000079 | SE3 | L11E | 144000 | 20882 | 123118
06 | Kern County | Construct 0.25 miles of sidewalk and shoulders | Kern County (Metro Bakersfield): Northside of Casa Loma Drive (South Union Avenue to Pogososo Street) | CML | 5950(503) | 0622000136 | S | Z40E | 421690 | 421689.31 | 0.69
06 | Caltrans | Construct New Interchange and Construct North and Southbound Auxiliary Lanes | On State Route-99 at Commercial Avenue: between 0.9 miles North of Avenue 200 Overcrossing (OC) and Paige Avenue Overcrossing | BUILDL | 6206(033) | 0616000074 | 4SBV | BDG6 | 16000000 | 14210010.88 | 1789989.12 | 9/30/2027 with Invoices due 7/1/2027

## District 7
Projects with Lapsing Federal Funds
Reversion Date: | 2027-06-30
Appropriation/Item Number: | 2660-102-0890
Year of Appropriation: | 2122
Appropriation Unit: | 22102F
Program: | 2030
District | Parties to Agreement (Agency) | Purpose of Project (Work Description) | Scope (Location) | Prefix | Project Id | Advantage Project Id | Advantage Phase | Federal Program Code | Budgeted Amount | Expenditure Amount | Remaining Balance | Federal Financial Constraint Date if Applicable within the CWA Timeline | Is Project Consistent with Original Scope and Purpose of the Appropriation? If No, Please Explain: | Are You Requesting a CWA (Yes or No)? If No, provide an anticipated date the agency plans to submit invoice for the remaining balance | Reason for Delay | If Other for Reason for Delay, Provide Explanation | Please Provide a 2-3 Sentence Explanation Identifying Any Impediments to Completion | What are the Consequences if CWA is Not Approved? (Please Provide a 2-3 Sentence Explanation) | Local Agency Contact Name | Local Agency Contact Phone Number | Local Agency Contact Email | Approved by DOF (Yes or No)? | Revised Reversion Date
07 | Los Angeles County | Pavement Removal (PR) -- remove roadway and pavement to restore 180 feet of slope using 5 percent soil cement mixture | Mulholland Highway at Mile Marker 14.74 | ER | 40A0(084) | 0720000250 | S | ER01 | 1604606.25 | 1522752.14 | 81854.11
07 | Los Angeles | Modification of Median Island and widening the road | Near El Segundo, on the Imperial Highway between Pershing Drive and 1,000 feet East of Pershing Drive Modify the median island and widen Imperial | RPSTPLE | 5006(654) | 0700020733 | S | L400 | 1506000 | 1385129.82 | 120870.18
07 | Los Angeles | Construct road diet with bike lanes, crosswalks, and median refuge islands and bulb | The area bordered/bounded by Martin Luther King Junior Boulevard, Hoover Street, Vernon Avenue, and Vermont Avenue | SRTSL | 5006(732) | 0712000317 | SE1 | LU2E | 71156.57 | 32596.65 | 38559.92
07 | Los Angeles | Construct raised medians and curb extensions, install rectangular rapid flashing beacons, modify sign | Crenshaw Boulevard: Florence Avenue to 79th Street | HSIPL | 5006(845) | 0716000353 | S | ZS30 | 1358780 | 92465.52 | 1266314.48
07 | Los Angeles | Install new sidewalks, access ramps, median island, bike signals, wayfinding signage, lighting et cetera | Pico Boulevard: Between Interstate 405 Freeway to Patricia Avenue; and the intersection of Westwood Boulevard and Tennessee Avenue | CML | 5006(862) | 0717000279 | SE1 | L40E | 1619000 | 916917.3 | 702082.7
07 | Los Angeles | Install new signals to partially stop controlled intersections | Fifteen intersections: 42nd Place/Central Avenue and others | HSIPL | 5006(867) | 0718000001 | SE1 | YS30 | 3804480 | 3194849.27 | 609630.73
07 | Los Angeles | Roadway Widening | To widen Anaheim street, Farragut Avenue to Dominguez Channel, from two (2)- three (3) lanes | STPL | 5006(885) | 0719000160 | S | M230 | 642000 | 300040.06 | 341959.94
07 | Los Angeles | Pedestrian Walkway | Westlake Transit Improvement Demonstration Identification (DEMO ID) CA868 | DEMOL | 5006(919) | 0722000004 | S | 56C0 | 99982 | 84008.65 | 15973.35
07 | Los Angeles | Asphalt Concrete Overlay | Project XXI Citywide resurfacing and construction of Americans with Disability Act (ADA) compliant access ramps and truncated domes as needed, within the city limits of Los Angeles | STPCRAL | 5006(929) | 0723000002 | S | Y230 | 11500000 | 7503050.92 | 3996949.08
07 | Los Angeles | Asphalt Concrete Overlay | Project XXI Citywide resurfacing and construction of Americans with Disability Act (ADA) compliant access ramps and truncated domes as needed, within the city limits of Los Angeles | STPCRAL | 5006(929) | 0723000002 | SE1 | Z972 | 6000000 | 3914635.26 | 2085364.74 | 9/30/2029 with Invoices due 7/1/2029
07 | Los Angeles | Pedestrian Walkway | Slauson Avenue- Western Avenue to Crenshaw Boulevard | CML | 5006(931) | 0722000265 | S | L400 | 730000 | 458438.57 | 271561.43
07 | Long Beach | Install controlled-access medians, signal upgrades and pedestrian refuges | Various Location on Anaheim Street between Los Angeles River and Pacific Coast Highway, | HSIPL | 5108(178) | 0718000126 | SE2 | Z972 | 2209296 | 33199.16 | 2176096.84 | 9/30/2029 with Invoices due 7/1/2029
07 | Oxnard | Traffic Operations / Maintenance-Labor / Consulting services for speed surveys, volume count | Citywide | CRALNI | 5129(109) | 0723000267 | S | Z972 | 866460 | 3000 | 863460 | 9/30/2029 with Invoices due 7/1/2029
07 | San Fernando | Twelve-foot wide, 1.34 mile long Class 1 Bike/Pedestrian path, at grade crossings, lighting, fencing, and sign | At Pacoima Wash access Road from Fourth Street (Bradley) Avenue to English Street (Eight Street) National Park | ATPL | 5202(020) | 0721000072 | S | Z0E3 | 1513000 | 1433490.4 | 79509.6
07 | Paramount | Bridge Rehabilitation | Bridge Number: 53C0190L: On Rosecrans Avenue (West) at the Los Angeles River crossing from 0.1 mile West of the Los Angeles River to 0.1 mile East of Los Angeles River | BRLS | 5336(018) | 0717000268 | SE1 | M001 | 83141.32 | 18412.08 | 64729.24
07 | Paramount | Bridge Rehabilitation | Bridge Number: 53C0190R: On Rosecrans Avenue (East) at the Los Angeles River crossing from 0.1 mile West of the Los Angeles River to 0.1 mile East of Los Angeles River | BRLS | 5336(019) | 0717000269 | SE1 | M001 | 69786.4 | 15684.35 | 54102.05
07 | Norwalk | Traffic Signal Upgrades, Fiber Optic Cable, New Controllers, Pedestrian Countdown Signal Heads | Alondra Boulevard between Piuma Avenue and Shoemaker Avenue | HSIPL | 5347(042) | 0717000123 | SE1 | ZS3E | 981750 | 931874.6 | 49875.4
07 | Norwalk | Traffic Signal Upgrades, Fiber Optic Cable, New Controllers, Pedestrian Countdown Signal Heads | Firestone Boulevard: Interstate-605 to Rosecrans Avenue | HSIPL | 5347(043) | 0717000122 | SE1 | MS3E | 1276870 | 942729.78 | 334140.22
07 | Norwalk | Traffic signal upgrades, fiber optic cable, new controllers, pedestrian countdown signal heads | Studebaker Road from Rosecrans Avenue to Cecilia Street | HSIPL | 5347(044) | 0718000041 | S | ZS30 | 956505 | 893349.55 | 63155.45
07 | Palmdale | Bike Path | Avenue R Complete Streets and Safe Routes Project Avenue R between Sierra Highway and 25th Street East, in southeastern Palmdale | ATPL | 5378(049) | 0722000002 | S | Z230 | 1799459 | 1774251.66 | 25207.34
07 | Lancaster | Rehabilitate existing pavement, reconstruct existing curb and gutter, sidewalk, curb ramps, traffic restripe | 35th Street West from Avenue K through 8 to Avenue L | STPL | 5419(062) | 0722000362 | S | Q230 | 911325 | 870158.55 | 41166.45
07 | Ventura County | Widening Hueneme Road from two lanes to four lanes | Hueneme Road from Edison Drive (Oxnard City Limits) to 1200 feet East of Rice Avenue in the Oxnard Plain Area in Unincorporated Ventura County | HIPL | 5952(215) | 0722000239 | S | Z905 | 1172000 | 1110829.3 | 61170.7 | 9/30/2027 with Invoices due 7/1/2027
07 | Los Angeles County | Upgrade Signals | Intersections of 120th Street at Normandie Avenue and 120th Street at Compton Avenue, located in the unincorporated County areas of West Athens and Willowbrook | HSIPL | 5953(755) | 0717000326 | SE1 | YS30 | 786800 | 668840.49 | 117959.51
07 | Los Angeles County | Upgrade Signals: Install various traffic signal improvements, including upgrading standards. | Intersections of Olympic Boulevard at Garfield Avenue and Whittier Boulevard at Eastern Avenue, located in the unincorporated County area of East Los Angeles | HSIPL | 5953(756) | 0717000287 | SE1 | YS30 | 626800 | 481593.9 | 145206.1
07 | Los Angeles County Metropolitan Transportation Authority | Interstate 605 Widening and Re-aligning Southbound off-ramp to South Street | Southbound Interstate 605 at South Street Improvement Project located in the City of Cerritos | HIPL | 6065(253) | 0722000190 | SE2 | Z910 | 2204795 | 2055211.33 | 149583.67 | 9/30/2028 with Invoices due 7/1/2028
07 | Southern California Regional Rail Authority | Railroad Safety and Signal Work | Crossings at Tyler Avenue and Cogswell Road in the City of El Monte | CARSI | 6187(009) | 0722000224 | S | Z915 | 2584000 | 167321.48 | 2416678.52
07 | Caltrans | Construct one High-Occupancy Vehicle (HOV) lane in each direction on Route 10 and pavement rehab | Route 10 High-Occupancy Vehicle (HOV) Lane from Citrus Avenue to Route 57 | CMLN | 6207(070) | 0713000007 | 3SBVE1 | Y400 | 517910 | 98416.34 | 419493.66
07 | Caltrans | Construct one High-Occupancy Vehicle (HOV) lane in each direction on Route 10 and pavement rehab | Route 10 High-Occupancy Vehicle (HOV) Lane from Citrus Avenue to Route 57 | CMLN | 6207(070) | 0713000007 | 4SBVE2 | Y400 | 7647110 | 3376784.32 | 4270325.68

## District 8
Projects with Lapsing Federal Funds
Reversion Date: | 2027-06-30
Appropriation/Item Number: | 2660-102-0890
Year of Appropriation: | 2122
Appropriation Unit: | 22102F
Program: | 2030
District | Parties to Agreement (Agency) | Purpose of Project (Work Description) | Scope (Location) | Prefix | Project Id | Advantage Project Id | Advantage Phase | Federal Program Code | Budgeted Amount | Expenditure Amount | Remaining Balance | Federal Financial Constraint Date if Applicable within the CWA Timeline | Is Project Consistent with Original Scope and Purpose of the Appropriation? If No, Please Explain: | Are You Requesting a CWA (Yes or No)? If No, provide an anticipated date the agency plans to submit invoice for the remaining balance | Reason for Delay | If Other for Reason for Delay, Provide Explanation | Please Provide a 2-3 Sentence Explanation Identifying Any Impediments to Completion | What are the Consequences if CWA is Not Approved? (Please Provide a 2-3 Sentence Explanation) | Local Agency Contact Name | Local Agency Contact Phone Number | Local Agency Contact Email | Approved by DOF (Yes or No)? | Revised Reversion Date
08 | San Bernardino | Upgrade traffic signal hardware | 224 signalized intersections on various arterials in the City of San Bernardino | HSIPL | 5033(056) | 0819000060 | SE2 | YS30 | 80000 | 63350.88 | 16649.12
08 | San Bernardino | Install advanced dilemma zone detection system | 49 signalized intersections on Mount Vernon Avenue: Highland Avenue to Johnson Street; Baseline Street: Del Rosa Avenue to California Street; and Highland Avenue: Medical Center Drive to Victoria Avenue | HSIPL | 5033(057) | 0819000059 | SE1 | YS30 | 4024722 | 3323637.2 | 701084.8
08 | Riverside | Construct a railroad underpass at the existing at-grade crossing of Third Street and the railroad | On Third Street from Vine Street to Park Avenue | CML | 5058(081) | 0812000280 | S | Z40E | 18000000 | 17566942.65 | 433057.35
08 | Colton | Bridge rehabilitation including seismic retrofit and widening of the bridge from two lanes to four lanes | Mount Vernon Avenue over the Santa Ana River near M Street, Bridge Number 54C-0100 | BRLSZ | 5065(017) | 0800020284 | SE3 | Z0E1 | 110751 | 71751 | 39000
08 | Colton | Replace overhead with two-lane road across discontinued railroad right of way | Barton Road overhead at Union Pacific Railroad, 0.25 mile West of Interstate-215, Bridge Number 54C-0379 | BRLS | 5065(024) | 0812000141 | SE1 | Y001 | 824834 | 304274.98 | 520559.02
08 | Lake Elsinore | Replace two-lane bridge with a four-lane bridge | Temescal Canyon Road over Temescal Wash approximately 0.2 miles West of Lake Street, Bridge Number 56C-0050 | BRLS | 5074(015) | 0812000240 | SE2 | Y001 | 1008357 | 998610.34 | 9746.66
08 | Barstow | Bridge replacement | North First Avenue bridge over the Burlington Northern Santa Fe Railway (BNSF) Railroad, from 0.2 miles North of Main Street to Crooks Street, Bridge Number 54C-0088 | BRLS | 5298(030) | 0813000018 | SE7 | Y001 | 1770600 | 0 | 1770600
08 | Rancho Mirage | Pork chop island to create right-turn lane and four (4)-foot high sand fencing | Northwest intersection quadrant of Bob Hope Drive and Ramon Road, Ramon Road from Los Alamos Road to Bob Hope Drive, and Dinah Shore Drive from Bob Hope Drive to Miriam Way | CML | 5412(016) | 0815000152 | SE1 | Z400 | 15332 | 0 | 15332
08 | Highland | Replace existing two-lane bridge with four-lane bridge | Orange Street over Plunge Creek Overflow, 1.5 miles North of Pioneer Avenue from the City of Redlands, Bridge Number 54C-0592 | BRLSN | 5449(034) | 0815000115 | SE1 | Z0E1 | 177060 | 87719.69 | 89340.31
08 | Temecula | Construct New Lane Collector/Distributor system | French Valley Parkway Interchange/Arterial Phases: Phase 2 | INFRALUL | 5459(031) | 0821000008 | S | Z430 | 47670828.09 | 43365168.05 | 4305660.04
08 | Calimesa | Roadway widening and improvements | County Line Road from Interstate 10 to 600 feet East of Calimesa Boulevard and Southbound Calimesa Boulevard from County Line Road to 125 feet South | HPLUL | 5460(006) | 0815000158 | SE1 | LY10 | 933839.5 | 324852.05 | 608987.45
08 | Riverside County Transportation Commission | Reconstruct interchange | State Route 91/ State Route 71 interchange | HP21LN | 6054(066) | 0800020578 | SE9 | Y230 | 5461212.65 | 4260050.76 | 1201161.89
08 | Riverside County Transportation Commission | Reconstruct interchange | State Route 91/ State Route 71 interchange | HP21LN | 6054(066) | 0800020578 | SE7 | Z23E | 9853000 | 8654397.16 | 1198602.84
08 | Riverside County Transportation Commission | Extend toll express lanes in each travel direction | Interstate 15 from State Route 74 in the City of Lake Elsinore to Cajalco Road in the City of Corona | CMLN | 6054(094) | 0819000062 | SE6 | Z970 | 2513378 | 0 | 2513378 | 9/30/2029 with Invoices due 7/1/2029
08 | Riverside County Transportation Commission | Extend toll express lanes in each travel direction | Interstate 15 from State Route 74 in the City of Lake Elsinore to Cajalco Road in the City of Corona | CMLN | 6054(094) | 0819000062 | SE7 | Z972 | 3800622 | 0 | 3800622 | 9/30/2029 with Invoices due 7/1/2029
08 | Caltrans | Interstate 10 Corridor Contract 2: Add one (1) Corridor Express Lane in each direction | Just East of Interstate 15 to Pepper Avenue in Colton, connecting to the Interstate 10 Corridor Contract 1 express lanes currently under construction | STPLN | 6208(035) | 0820000147 | 1SBV | Y230 | 6000000 | 5996650.6 | 0
08 | San Bernardino County | Widen from two to four lanes and add left turn channelization at Intersections | United States 395 Phase 2 (Hesperia, Victorville, & Adelanto) From 0.16 Miles North of Interstate Route 15 Junction so State Route 18 | STPCRALN | 6507(034) | 0822000167 | S | Y230 | 9140311 | 4475595.26 | 4664715.74
08 | San Bernardino County | Widen from two to four lanes and add left turn channelization at Intersections | United States 395 Phase 2 (Hesperia, Victorville, & Adelanto) From 0.16 Miles North of Interstate Route 15 Junction so State Route 18 | STPCRALN | 6507(034) | 0822000167 | SE1 | Z23E | 2648015 | 1533469.91 | 1114545.09
08 | San Bernardino County | Widen from two to four lanes and add left turn channelization at Intersections | United States 395 Phase 2 (Hesperia, Victorville, & Adelanto) From 0.16 Miles North of Interstate Route 15 Junction so State Route 18 | STPCRALN | 6507(034) | 0822000167 | SE2 | Z972 | 500000 | 497273.22 | 2726.78 | 9/30/2029 with Invoices due 7/1/2029
08 | San Bernardino County | Interstate 10 Corridor Contract 2: Add one (1) Corridor Express Lane in each direction | Just East of Interstate 15 to Pepper Avenue in Colton, connecting to the Interstate 10 Corridor Contract 1 express lanes currently under construction | STPCRALN | 6507(035) | 0822000183 | SE1 | Y230 | 5000000 | 4244255.51 | 755744.49
08 | San Bernardino County | Rideshare | South Coast Air Basin Rideshare Program | CMLNI | 6507(037) | 0823000012 | S | Z0E3 | 1950000 | 1063490.62 | 886509.38
08 | Yucaipa | Replace low water crossing with two (2)-lane bridge | Pendleton Avenue over Oak Glen Creek, low-water crossing (LWC) Number 00L0034 | BR | NBIL(506) | 0800020114 | SE1 | Z0E1 | 86759.4 | 46759.4 | 40000

## District 10
Projects with Lapsing Federal Funds
Reversion Date: | 2027-06-30
Appropriation/Item Number: | 2660-102-0890
Year of Appropriation: | 2122
Appropriation Unit: | 22102F
Program: | 2030
District | Parties to Agreement (Agency) | Purpose of Project (Work Description) | Scope (Location) | Prefix | Project Id | Advantage Project Id | Advantage Phase | Federal Program Code | Budgeted Amount | Expenditure Amount | Remaining Balance | Federal Financial Constraint Date if Applicable within the CWA Timeline | Is Project Consistent with Original Scope and Purpose of the Appropriation? If No, Please Explain: | Are You Requesting a CWA (Yes or No)? If No, provide an anticipated date the agency plans to submit invoice for the remaining balance | Reason for Delay | If Other for Reason for Delay, Provide Explanation | Please Provide a 2-3 Sentence Explanation Identifying Any Impediments to Completion | What are the Consequences if CWA is Not Approved? (Please Provide a 2-3 Sentence Explanation) | Local Agency Contact Name | Local Agency Contact Phone Number | Local Agency Contact Email | Approved by DOF (Yes or No)? | Revised Reversion Date
10 | Calaveras County | Realign 460 feet of road 12 feet to East and reconstruct State Route 26 Interchange Construct 5 feet debris barrier wall | Rail Road Flat Road Mile Post 0.0 at Highway 26 | ER | 40A0(082) | 1020000122 | S | ER01 | 253306 | 165553.44 | 87752.56
10 | Stockton | Traffic Related - Other | In Stockton, at intersection of Pacific Avenue and March Lane | CML | 5008(181) | 1018000249 | SE1 | Y400 | 460455 | 350002.41 | 110452.59
10 | Stockton | Bridge Preventive Maintenance - multiple locations | Bridges: 29C0093L; 29COO93R; 29C0237; 29C0242; 29C0400 | BPMP | 5008(201) | 1022000248 | S | Y001 | 270920 | 59475.9 | 211444.1
10 | Modesto | Roadway widening, reconstruct to eight (8) lane interchange | State Route 99 at Briggsmore/Carpenter Road | STPL | 5059(250) | 1021000128 | S | Z230 | 516650 | 71945.07 | 444704.93
10 | Modesto | Roadway widening, reconstruct to eight (8) lane interchange | State Route 99 at Briggsmore/Carpenter Road | STPL | 5059(250) | 1021000128 | SE1 | Z23E | 2297953 | 0 | 2297953
10 | Los Banos | Pioneer Road Improvements - Complete Streets Widening, bicycle/pedestrian improvements) | Pioneer Road in the City of Los Banos | HIPLPPSB | 5160(029) | 1021000081 | SE1 | RPS2 | 490000 | 103558.01 | 386441.99
10 | Turlock | Intersection Improvements - install traffic signal, pedestrian ramps, striping and various improvement | Taylor Road and Walnut Road Intersection | CML | 5165(079) | 1014000184 | S | L40E | 85000 | 26604.3 | 58395.7
10 | Turlock | New Signals Install traffic signal controllers and signal timing plan | Monte Vista - Tegner Road and Golden State Boulevard; Golden State Boulevard - Olive Avenue to East Avenue; Geer Road - Monte Vista Avenue to Hawkeye Avenue | CML | 5165(096) | 1021000055 | S | Z400 | 234025 | 222171.43 | 11853.57
10 | Turlock | Road Rehabilitation | Pedras Road between Geer Road and Golden State Boulevard | STPL | 5165(099) | 1022000057 | S | Z230 | 873883 | 833882.99 | 40000.01
10 | Tracy | Construct Interchange improvements, freeway auxiliary lanes and connecting roadways | On Interstate Route 205 at Eleventh Street | DEM03LN | 5192(021) | 1000000067 | SE2 | HY10 | 136876 | 0 | 136876
10 | Tracy | Construct Interchange improvements, freeway auxiliary lanes and connecting roadways | On Interstate Route 205 at Eleventh Street | DEM03LN | 5192(021) | 1000000067 | SE3 | LY10 | 583044.75 | 2514.33 | 580530.42
10 | Angels | Conduct a Roadway Safety Signing Audit (RSSA) and Implement Based on the Results | Various Locations Throughout the City of Angels Camp | HSIPL | 5206(018) | 1019000191 | SE1 | YS30 | 122475 | 111612.84 | 10862.16
10 | Gustine | Construct Roundabout | At 5th Street and 4th Avenue | CML | 5230(008) | 1016000158 | SE1 | Z0E3 | 487888 | 12336.62 | 475551.38
10 | Gustine | Pedestrian Walkway, Meredeth Avenue Phase 3 | In Gustine, On Meredith Avenue and Railroad Avenue (South Avenue to Meredith Avenue) | CML | 5230(015) | 1022000153 | S | Z0E3 | 64881 | 36087.22 | 28793.78
10 | Atwater | Phase 4: pedestrian improvement to connect with Downtown | Phase 4: North of downtown (Holly Avenue, Hemlock Avenue, Grove Avenue, Fire Avenue, Elm Avenue, Eucalyptus Street, Packers Street and High Street) | CML | 5254(033) | 1022000091 | S | Z0E3 | 180026 | 178130.5 | 1895.5
10 | Riverbank | New Signals | Patterson and Roselle Avenue Intersection | CML | 5255(052) | 1015000074 | SE2 | Z240 | 483628 | 0 | 483628
10 | Riverbank | New Signals | Patterson and Roselle Avenue Intersection | CML | 5255(052) | 1015000074 | SE3 | Z40E | 190610 | 33047.18 | 157562.82
10 | Amador County | Construct Safety and Operational Improvements | Pine Grove at State Route 88 from Climax Road to Mount Zion | HIPCML | 5926(066) | 1021000187 | SE1 | Z907 | 139000 | 10372 | 128628 | 9/30/2027 with Invoices due 7/1/2027
10 | Livingston | Construct Multi-use Path Improvements (Phase 1) | At Max Foster Sports Complex Area in Livingston | CML | 5256(020) | 1021000031 | SE1 | Y400 | 454763 | 397526.61 | 57236.39
10 | Livingston | Construct a concrete multiuse path, drive approaches and ancillary improvements | Max Foster Multiuse Path (Phase 2) - Along Dwight Way, between North of Trigger Lane and Tehama Drive | CML | 5256(021) | 1022000098 | S | M400 | 59682 | 49858.3 | 9823.7
10 | Livingston | Construct a concrete multiuse path, drive approaches and ancillary improvements | Max Foster Multiuse Path (Phase 2) - Along Dwight Way, between North of Trigger Lane and Tehama Drive | CML | 5256(021) | 1022000098 | SE1 | Y003 | 428968 | 302889.4 | 126078.6
10 | Calaveras County | Rehabilitation of historic one (1)-lane bridge: Strengthen structural members | Calaveritas Road over Calaveritas Creek | BRLO | 5930(060) | 1000020523 | SE2 | Z233 | 250000 | 210000.58 | 39999.42
10 | Calaveras County | Replace existing one (1)-lane bridge with a standard two (2)-lane bridge | Whiskey Slide Road over Jesus Maria Creek | BRLO | 5930(064) | 1000020530 | SE2 | M233 | 270513 | 113400.56 | 157112.44
10 | Calaveras County | Replace existing one (1)-lane bridge with a standard two (2)-lane bridge | Dogtown Road over Indian Creek; Bridge 30C0051 | BRLO | 5930(074) | 1012000213 | SE2 | Y233 | 250000 | 81631.9 | 168368.1
10 | Stanislaus County | Bridge Scour Countermeasures | Sonora Road (Bridge 38C0272) Over Martells Creek, .1 miles East of Frankenheimer Road | BRLO | 5938(203) | 1012000225 | SE3 | Y233 | 405000 | 314835.87 | 90164.13
10 | Merced County | Replace existing two (2)-lane timber bridge with a standard two (2)-lane bridge | Burchell Avenue over Duck Slough (Mariposa Creek) | BRLO | 5939(077) | 1000020508 | SE3 | Z2E3 | 170000 | 148847.75 | 21152.25
10 | Mariposa County | Replace existing one (1)-lane bridge with a standard two (2)-lane bridge | Dogtown Road over Maxwell Creek, 1.6 miles East of Greely Hill Road, Bridge Number 40C0038 | BRLO | 5940(099) | 1012000240 | SE2 | Y233 | 50000 | 9544.03 | 40455.97
10 | Mariposa County | Replace existing one-lane timber bridge with a standard two-lane bridge | Dogtown Road over Maxwell Creek | BRLO | 5940(106) | 1013000137 | SE3 | Y233 | 50000 | 11728.68 | 38271.32
10 | Mariposa County | Replace one-lane timber bridge with a wider one-lane bridge | Incline Road over Moss Canyon | BRLO | 5940(114) | 1014000198 | SE2 | L110 | 25000 | 5405.61 | 19594.39

## District 11
Projects with Lapsing Federal Funds
Reversion Date: | 2027-06-30
Appropriation/Item Number: | 2660-102-0890
Year of Appropriation: | 2122
Appropriation Unit: | 22102F
Program: | 2030
District | Parties to Agreement (Agency) | Purpose of Project (Work Description) | Scope (Location) | Prefix | Project Id | Advantage Project Id | Advantage Phase | Federal Program Code | Budgeted Amount | Expenditure Amount | Remaining Balance | Federal Financial Constraint Date if Applicable within the CWA Timeline | Is Project Consistent with Original Scope and Purpose of the Appropriation? If No, Please Explain: | Are You Requesting a CWA (Yes or No)? If No, provide an anticipated date the agency plans to submit invoice for the remaining balance | Reason for Delay | If Other for Reason for Delay, Provide Explanation | Please Provide a 2-3 Sentence Explanation Identifying Any Impediments to Completion | What are the Consequences if CWA is Not Approved? (Please Provide a 2-3 Sentence Explanation) | Local Agency Contact Name | Local Agency Contact Phone Number | Local Agency Contact Email | Approved by DOF (Yes or No)? | Revised Reversion Date
11 | Brawley | Construct new road | Western Avenue from Legion Street to Wildcat Drive | CML | 5167(045) | 1120000126 | S | Z400 | 784000 | 765195.12 | 18804.88
11 | Chula Vista | Install lead pedestrian interval operations | Various locations citywide | HSIPL | 5203(052) | 1120000003 | SE1 | ZS30 | 2146400 | 1904816.18 | 241583.82
11 | El Cajon | Pedestrian and Bike Path | Jamacha Road and 2nd Street, from Washington Avenue to Broadway | HSIPL | 5211(040) | 1119000211 | SE1 | YS30 | 2012270 | 1631743.79 | 380526.21
11 | San Marcos | Bridge Replacement | Via Vera Cruz bridge (57C-0780) over San Marcos Creek | BRLS | 5381(033) | 1100020414 | SE4 | Y001 | 21689142 | 21411479.14 | 277662.86
11 | San Diego County | Construct Sidewalks, Bike lanes, Advanced Dilemma Zone | Woodside Avenue from Marilla Drive to Chesnut Street | HSIPL | 5957(129) | 1117000222 | S | ZS30 | 90000 | 82000 | 8000
11 | San Diego Association of Governments | Construct 8.5 miles of continuous bikeway, intersection treatments, and traffic calming devices | In San Diego, just North of San Ysidro Land Port of Entry to Ingrid Avenue and Saturn Boulevard in Imperial Beach | ATPL | 6066(130) | 1116000161 | SE2 | Z972 | 1695000 | 910044.4 | 784955.6 | 9/30/2029 with Invoices due 7/1/2029
11 | San Diego Association of Governments | Bike Path | In the City of San Diego along Imperial Avenue from 21st to 47th Street 3.1 mile facility with buffered and protected bikeways, pedestrian improvements, and traffic calming improvements | ATPL | 6066(137) | 1118000175 | SE2 | Z972 | 4100158 | 3860098.65 | 240059.35 | 9/30/2029 with Invoices due 7/1/2029
11 | Caltrans | Landscape | In San Diego County in San Diego on State Route 905 from 0.3 miles West of Caliente Avenue overcrossing to 0.4 miles East of Los Angeles Media Road undercrossing | HPLULN | 6211(140) | 1120000088 | 3SBV | LY10 | 360637.2 | 360652.03 | 14.83
11 | Caltrans | High-Occupancy Vehicle (HOV) Lane | Interstate 5 in San Diego County | CML | 6211(151) | 1122000246 | 1SBV | Z0E3 | 1700000 | 1690885.93 | 9114.07

## District 12
Projects with Lapsing Federal Funds
Reversion Date: | 2027-06-30
Appropriation/Item Number: | 2660-102-0890
Year of Appropriation: | 2122
Appropriation Unit: | 22102F
Program: | 2030
District | Parties to Agreement (Agency) | Purpose of Project (Work Description) | Scope (Location) | Prefix | Project Id | Advantage Project Id | Advantage Phase | Federal Program Code | Budgeted Amount | Expenditure Amount | Remaining Balance | Federal Financial Constraint Date if Applicable within the CWA Timeline | Is Project Consistent with Original Scope and Purpose of the Appropriation? If No, Please Explain: | Are You Requesting a CWA (Yes or No)? If No, provide an anticipated date the agency plans to submit invoice for the remaining balance | Reason for Delay | If Other for Reason for Delay, Provide Explanation | Please Provide a 2-3 Sentence Explanation Identifying Any Impediments to Completion | What are the Consequences if CWA is Not Approved? (Please Provide a 2-3 Sentence Explanation) | Local Agency Contact Name | Local Agency Contact Phone Number | Local Agency Contact Email | Approved by DOF (Yes or No)? | Revised Reversion Date
12 | Anaheim | Median island and modify signals | Euclid Street from Crescent Avenue to Glenoaks Avenue | HSIPL | 5055(187) | 1217000072 | SE1 | MS3E | 816030 | 352570.74 | 463459.26
12 | Anaheim | Median island and modify signals | Euclid Street from Crescent Avenue to Glenoaks Avenue | HSIPL | 5055(187) | 1217000072 | S | ZS30 | 106470 | 99990 | 6480
12 | Rancho Santa Margarita | Bridge Related - Other | Antonio Parkway Bridge and Eastbound Santa Margarita Parkway Bridge in the City of Rancho Santa Margarita (Bridge Number 55C0520R and 55C0605) | BPMPL | 5478(017) | 1222000033 | S | Y001 | 178830 | 175150.29 | 3679.71
12 | Orange County Transportation Authority | Project study reports for HOV lanes | Interstate 5 from the Orange/San Diego County Line to Avenida Pico in the City of San Clemente | CMLN | 6071(112) | 1215000130 | SE2 | M230 | 907000 | 0 | 907000
12 | Orange County Transportation Authority | High-Occupancy Vehicle (HOV) and mixed-flow lanes in each direction | State Route 55 from Interstate 405 to Interstate 5 | CMSTPLN | 6071(129) | 1217000111 | SE14 | Y230 | 29786407 | 0 | 29786407
12 | Orange County Transportation Authority | High-Occupancy Vehicle (HOV) and mixed-flow lanes in each direction | State Route 55 from Interstate 405 to Interstate 5 | CMSTPLN | 6071(129) | 1217000111 | SE15 | Y400 | 3411006 | 0 | 3411006
12 | Orange County Transportation Authority | High-Occupancy Vehicle (HOV) and mixed-flow lanes in each direction | State Route 55 from Interstate 405 to Interstate 5 | CMSTPLN | 6071(129) | 1217000111 | SE13 | Z40E | 16097994 | 5273307.38 | 10824686.62
12 | Caltrans | Ramp improvements | Interstate 5 interchange at El Toro Road from Los Alisos Boulevard Overcrossing to Ridge Route Drive alignment | STPLN | 6212(023) | 1213000084 | 0SBVE1 | Y230 | 4813000 | 4547715.1 | 265284.9
12 | Caltrans | Add mixed-flow lane | Northbound State Route 57 from Orangewood in Orange to Katella Avenue in Anaheim | STPLN | 6212(027) | 1213000099 | 1SBV | Z910 | 450000 | 435425.61 | 14574.39 | 9/30/2028 with Invoices due 7/1/2028
12 | Caltrans | Roadway Widening | On Interstate 5 from Yale Avenue to State Route 55 | STPLN | 6212(028) | 1220000035 | 1SBV | L230 | 600000 | 599823.17 | 176.83

## Drop-down Reference Tables
Within Scope? | Need a CWA? | Primary Reason For Delay:
YES | YES | Design: Change in scope.
NO | NO | Design: Change in specifications.
Design: Change in site conditions.
Environmental: Change in scope requires additional studies/permits.
Environmental: Excessive study or opinion review time by external agencies.
Environmental: Permits expired.
Environmental: Environmental document determination revalidation required.
Environmental: Mitigation for project impacts period.
Right of Way and Utility Relocation: Change in scope/number of parcels/utility relocations required.
Right of Way and Utility Relocation: Condemnation/eminent domain proceedings.
Right of Way and Utility Relocation: Utility owner dispute.
Right of Way and Utility Relocation: Qualified Buy America purchase/delivery delays.
Construction: Contract award disputed/cancelled, rebid or complete under force account.
Construction: Change in site conditions.
Construction: Qualified Buy America purchase/delivery delays.
Construction: Extended winter suspension affecting delivery schedule.
Contract Dispute/Litigation: Post-construction claim. Informal settlement.
Contract Dispute/Litigation: Formal litigation proceeding.
Finance: CTC approved Time Extension conflicts with reversion date.
Finance: Indirect Cost Rate Proposal (ICRP) request package returned with errors.
Finance: Change in dedicated/programmed funding.
Finance: Pending programming.
OTHER-declared disaster (explain):
OTHER (explain):