## Rail
Rail Projects with Lapsing Federal Funds
Reversion Date: | 2027-06-30
Appropriation/Item Number: | 2660-102-0890
Year of Appropriation: | 2122
Appropriation Unit: | 22102F
Program: | 2030
District | Parties to Agreement (Agency) | Purpose of Project (Work Description) | Scope (Location) | Prefix | Project Id | Advantage Project Id | Advantage Phase | Federal Program Code | Budgeted Amount | Expenditure Amount | Remaining Balance | Federal Financial Constraint Date if Applicable within the CWA Timeline | Is Project Consistent with Original Scope and Purpose of the Appropriation? If No, Please Explain: | Are You Requesting a CWA (Yes or No)? If No, provide an anticipated date the agency plans to submit invoice for the remaining balance | Reason for Delay | If Other for Reason for Delay, Provide Explanation | Please Provide a 2-3 Sentence Explanation Identifying Any Impediments to Completion | What are the Consequences if CWA is Not Approved? (Please Provide a 2-3 Sentence Explanation) | Local Agency Contact Name | Local Agency Contact Phone Number | Local Agency Contact Email | Approved by DOF (Yes or No)? | Revised Reversion Date
50 | 1. City of Oakland, 2. Union Pacific Railroad (UPRR) | Safety improvements for the elimination of hazards at a railway-highway grade crossing | In the City of Oakland, the 29th Avenue and Union Pacific Railroad (UPRR) | STPLR | 7500(226) | 0015150311 | SE2 | ZS40 | 743035 | 0 | 743035 | N/A
50 | 1. City of Sacramento 2. Union Pacific Railraod (UPRR) | Safety improvements for the elimination of hazards at a railway-highway grade crossing | Power Inn Road in City of Sacramento | STPLR | 7500(260) | 0018000012 | SE1 | ZS50 | 645700 | 67728.82 | 577971.18 | N/A
50 | 1. Merced County 2. Burlington Northern Santa Fe (BNSF) | Safety improvements for the elimination of hazards at a railway-highway grade crossing | Olive Street in Merced County | STPLR | 7500(273) | 0019000408 | S | ZS40 | 48000 | 0 | 48000 | N/A
50 | 1. City of Chico 2. Union Pacific Railroad (UPRR) | Safety improvements for the elimination of hazards at a railway-highway grade crossing | At the grade crossing and intersection of West Sacramento Avenue and the Union Pacific Railroad track | STPLR | 130R(292) | 0323000012 | S | ZS4E | 149018.05 | 36106.33 | 112911.72 | N/A
50 | 1. City of Chico 2. Union Pacific Railroad (UPRR) | Safety improvements for the elimination of hazards at a railway-highway grade crossing | At the grade crossing and intersection of West Sacramento Avenue and the Union Pacific Railroad track | STPLR | 130R(292) | 0323000012 | SE1 | ZS50 | 1133481.95 | 0 | 1133481.95 | N/A
50 | 1. City of Chico 2. Union Pacific Railroad (UPRR) | Safety improvements for the elimination of hazards at a railway-highway grade crossing | At the grade crossing and intersection of West Sacramento Avenue and the Union Pacific Railroad track | STPLR | 130L(292) | 0323000013 | S | MS5E | 516162.38 | 283594.7 | 232567.68 | N/A
50 | 1. City of Chico 2. Union Pacific Railroad (UPRR) | Safety improvements for the elimination of hazards at a railway-highway grade crossing | At the grade crossing and intersection of West Sacramento Avenue and the Union Pacific Railroad track | STPLR | 130L(292) | 0323000013 | SE1 | ZS4E | 153837.62 | 0 | 153837.62 | N/A
50 | Peninsula Corridor Joints Powers Board (Caltrain) | Safety improvements for the elimination of hazards at a railway-highway grade crossing | At the grade crossings located at the intersection of 4th Avenue and the rail lines managed by Peninsula Corridor Joint Powers Board in City of San Mateo | STPLR | 7500(280) | 0420000270 | SE1 | ZS4E | 2030160 | 1861670.72 | 168489.28 | N/A
50 | Peninsula Corridor Joints Powers Board (Caltrain) | Safety improvements for the elimination of hazards at a railway-highway grade crossing | At the grade crossings located at the intersection of 4th Avenue and the rail lines managed by Peninsula Corridor Joint Powers Board in City of San Mateo | STPLR | 7500(281) | 0421000022 | SE3 | ZS4E | 882500 | 812946 | 69554 | N/A
50 | 1. City of Richmond 2. Burlington Northern Santa Fe (BNSF) | Safety improvements for the elimination of hazards at a railway-highway grade crossing | Location is at the grade crossing and intersection of Harbour and Wright and the BNSF Railroad tracks | STPLR | 7500(282) | 0421000023 | SE1 | ZS40 | 461784 | 5844.39 | 455939.61 | N/A
50 | Union Pacific Railroad (UPPR) | Safety improvements for the elimination of hazards at a railway-highway grade crossing | 29th Avenue in City of Oakland | STPLR | 130L(296) | 0423000039 | S | ZS4E | 500000 | 462583.05 | 37416.95 | N/A
50 | Union Pacific Railroad (UPPR) | Safety improvements for the elimination of hazards at a railway-highway grade crossing | 29th Avenue in City of Oakland | STPLR | 130R(296) | 0423000040 | S | ZS4E | 496118.05 | 8960.39 | 487157.66 | N/A
50 | Union Pacific Railroad (UPPR) | Safety improvements for the elimination of hazards at a railway-highway grade crossing | 29th Avenue in City of Oakland | STPLR | 130R(296) | 0423000040 | SE1 | ZS5E | 1133481.95 | 12674.19 | 1120807.76 | N/A
50 | Burlington Northern Santa Fe (BNSF) | Safety improvements for the elimination of hazards at a railway-highway grade crossing | Shields Avenue in City of Fresno | STPLR | 130R(293) | 0623000018 | S | LS40 | 54315.75 | 21569.6 | 32746.15 | N/A
50 | Burlington Northern Santa Fe (BNSF) | Safety improvements for the elimination of hazards at a railway-highway grade crossing | Shields Avenue in City of Fresno | STPLR | 130R(293) | 0623000018 | SE1 | ZS5E | 2913684.25 | 0 | 2913684.25 | N/A
50 | Burlington Northern Santa Fe (BNSF) | Safety improvements for the elimination of hazards at a railway-highway grade crossing | Shields Avenue in City of Fresno | STPLR | 130L(293) | 0623000019 | SE1 | ZS5E | 872300.57 | 62814.58 | 809485.99 | N/A
50 | 1. Ventura County Public Works 2. Union Pacific Railroad (UPRR) | Safety improvements for the elimination of hazards at a railway-highway grade crossing | Las Posas Road and State Route 34 | STPLR | 7500(290) | 0721000040 | S | ZS50 | 1002250 | 285661.02 | 716588.98 | N/A
50 | City of Palmdale | Safety improvements for the elimination of hazards at a railway-highway grade crossing | Avenue R in City of Palmdale | STPLR | 130L(297) | 0723000007 | S | ZS4E | 550000 | 449717.25 | 100282.75 | N/A
50 | Metrolink (SCRRA) | Safety improvements for the elimination of hazards at a railway-highway grade crossing | Avenue R in City of Palmdale | STPLR | 130X(297) | 0723000012 | S | ZS4E | 540000 | 89219.3 | 450780.7 | N/A
50 | Union Pacific Railroad (UPPR) | Safety improvements for the elimination of hazards at a railway-highway grade crossing | Avenue R in City of Palmdale | STPLR | 130R(297) | 0723000013 | S | ZS4E | 2655000 | 30566.62 | 2624433.38 | N/A
50 | City of Ontario | Safety improvements for the elimination of hazards at a railway-highway grade crossing | Campus Avenue in City of Ontario | STPLR | 130L(294) | 0823000006 | S | LS5E | 59800.8 | 33526.68 | 26274.12 | N/A
50 | City of Ontario | Safety improvements for the elimination of hazards at a railway-highway grade crossing | Campus Avenue in City of Ontario | STPLR | 130L(294) | 0823000006 | SE1 | ZS5E | 440199.2 | 246796.75 | 193402.45 | N/A
50 | City of Corona | Safety improvements for the elimination of hazards at a railway-highway grade crossing | Radio Road in City of Corona | STPLR | 130L(295) | 0823000007 | S | MS40 | 171962.99 | 145035.94 | 26927.05 | N/A
50 | City of Corona | Safety improvements for the elimination of hazards at a railway-highway grade crossing | Radio Road in City of Corona | STPLR | 130L(295) | 0823000007 | SE1 | ZS5E | 328037.01 | 0 | 328037.01 | N/A
50 | Union Pacific Railroad (UPPR) | Safety improvements for the elimination of hazards at a railway-highway grade crossing | Campus Avenue in City of Ontario | STPLR | 130R(294) | 0823000008 | S | ZS40 | 653766.62 | 46099.07 | 607667.55 | N/A
50 | Union Pacific Railroad (UPPR) | Safety improvements for the elimination of hazards at a railway-highway grade crossing | Campus Avenue in City of Ontario | STPLR | 130R(294) | 0823000008 | SE1 | ZS5E | 1009433.38 | 0 | 1009433.38 | N/A
50 | Burlington Northern Santa Fe (BNSF) | Safety improvements for the elimination of hazards at a railway-highway grade crossing | Radio Road in City of Corona | STPLR | 130R(295) | 0823000009 | S | MS50 | 95775.36 | 24870.64 | 70904.72 | N/A
50 | Burlington Northern Santa Fe (BNSF) | Safety improvements for the elimination of hazards at a railway-highway grade crossing | Radio Road in City of Corona | STPLR | 130R(295) | 0823000009 | SE1 | ZS5E | 1664224.64 | 0 | 1664224.64 | N/A

## Drop-down Reference Tables
Within Scope? | Need a CWA? | Primary Reason For Delay:
YES | YES | Design: Change in scope.
NO | NO | Design: Change in specifications.
Design: Change in site conditions.
Environmental: Change in scope requires additional studies/permits.
Environmental: Excessive study or opinion review time by external agencies.
Environmental: Permits expired.
Environmental: Environmental document determination revalidation required.
Environmental: Mitigation for project impacts period.
Right of Way and Utility Relocation: Change in scope/number of parcels/utility relocations required.
Right of Way and Utility Relocation: Condemnation/eminent domain proceedings.
Right of Way and Utility Relocation: Utility owner dispute.
Right of Way and Utility Relocation: Qualified Buy America purchase/delivery delays.
Construction: Contract award disputed/cancelled, rebid or complete under force account.
Construction: Change in site conditions.
Construction: Qualified Buy America purchase/delivery delays.
Construction: Extended winter suspension affecting delivery schedule.
Contract Dispute/Litigation: Post-construction claim. Informal settlement.
Contract Dispute/Litigation: Formal litigation proceeding.
Finance: CTC approved Time Extension conflicts with reversion date.
Finance: Indirect Cost Rate Proposal (ICRP) request package returned with errors.
Finance: Change in dedicated/programmed funding.
Finance: Pending programming.
OTHER-declared disaster (explain):
OTHER (explain):