## District
STIP Projects with Lapsing Federal Funds
Reversion Date: | 2027-06-30
Appropriation/Item Number: | 2660-101-0890
Year of Appropriation: | 2122
Appropriation Unit: | 22101
Program: | 2030
District | Parties to Agreement (Agency) | Purpose of Project (Work Description) | Scope (Location) | Prefix | Project Id | Advantage Project Id | PPNO | Advantage Phase | Phase | Federal Program Code | Budgeted Amount | Expenditure Amount | Remaining Balance | CTC TUF Deadline | Is Project Consistent with Original Scope and Purpose of the Appropriation? If No, Please Explain: | Are You Requesting a CWA (Yes or No)? If No, provide an anticipated date the agency plans to submit invoice for the remaining balance | Reason for Delay | If Other for Reason for Delay, Provide Explanation | Please Provide a 2-3 Sentence Explanation Identifying Any Impediments to Completion | What are the Consequences if CWA is Not Approved? (Please Provide a 2-3 Sentence Explanation) | Local Agency Contact Name | Local Agency Contact Phone Number | Local Agency Contact Email | Approved by DOF (Yes or No)? | Revised Reversion Date
02 | Susanville | Pedestrian and Bike Path | Riverside Drive in City of Susanville | RPSTPLE | 5116(014) | 0212000166 | 2480 | 1 | PS&E | N/A | 300000 | 8736.89 | 291263.11 | 2026-06-30
04 | San Jose | Implement Safety Improvements | West San Carlos Street between Interstate-880 and McEvoy Street | CML | 5005(162) | 0420000042 | 9035N | 4 | CON | N/A | 4350000 | 0 | 4350000 | 2026-06-28
04 | Richmond | Road Reconstruction | Interstate-80 Central Avenue in Richmond and El Cerrito | RPSTPL | 5137(050) | 0418000420 | 2025H | S | RW | N/A | 3983000 | 390799.98 | 3592200.02 | 2025-06-30

## Drop-down Reference Tables
Within Scope? | Need a CWA? | Primary Reason For Delay:
YES | YES | Design: Change in scope.
NO | NO | Design: Change in specifications.
Design: Change in site conditions.
Environmental: Change in scope requires additional studies/permits.
Environmental: Excessive study or opinion review time by external agencies.
Environmental: Permits expired.
Environmental: Environmental document determination revalidation required.
Environmental: Mitigation for project impacts period.
Right of Way and Utility Relocation: Change in scope/number of parcels/utility relocations required.
Right of Way and Utility Relocation: Condemnation/eminent domain proceedings.
Right of Way and Utility Relocation: Utility owner dispute.
Right of Way and Utility Relocation: Qualified Buy America purchase/delivery delays.
Construction: Contract award disputed/cancelled, rebid or complete under force account.
Construction: Change in site conditions.
Construction: Qualified Buy America purchase/delivery delays.
Construction: Extended winter suspension affecting delivery schedule.
Contract Dispute/Litigation: Post-construction claim. Informal settlement.
Contract Dispute/Litigation: Formal litigation proceeding.
Finance: CTC approved Time Extension conflicts with reversion date.
Finance: Indirect Cost Rate Proposal (ICRP) request package returned with errors.
Finance: Change in dedicated/programmed funding.
Finance: Pending programming.
OTHER-declared disaster (explain):
OTHER (explain):