## District 1
ATP Projects with Lapsing General Funds
Reversion Date: | 2027-06-30
Appropriation/Item Number: | 2660-102-0001
Year of Appropriation: | 2122
Appropriation Unit: | 22102
Program: | 2030
District | Parties to Agreement (Agency) | Purpose of Project (Work Description) | Scope (Location) | Prefix | Project Id | Advantage Project Id | PPNO | Advantage Phase | Phase | Federal Program Code | Budgeted Amount | Expenditure Amount | Remaining Balance | CTC TUF Deadline | Is Project Consistent with Original Scope and Purpose of the Appropriation? If No, Please Explain: | Are You Requesting a CWA (Yes or No)? If No, provide an anticipated date the agency plans to submit invoice for the remaining balance | Reason for Delay | If Other for Reason for Delay, Provide Explanation | Please Provide a 2-3 Sentence Explanation Identifying Any Impediments to Completion | What are the Consequences if CWA is Not Approved? (Please Provide a 2-3 Sentence Explanation) | Local Agency Contact Name | Local Agency Contact Phone Number | Local Agency Contact Email | Approved by DOF (Yes or No)? | Revised Reversion Date
01 | Mendocino Council of Governments | Pedestrian and Bike Path | Covelo Trail Phase 1. On Mendocino-162 Between Howard Street & Biggar Lane & from East end of Henderson Lane to Mendocino-162 | ATP | 6140(046) | 0116000072 | 4634 | 3 | CON | N/A | 261157.58 | 251157.58 | 10000 | 2027-04-30
01 | Mendocino Council of Governments | Pedestrian and Bike Path | Covelo Trail Phase 1. On Mendocino-162 Between Howard Street & Biggar Lane & from East end of Henderson Lane to Mendocino-162 | ATP | 6140(046) | 0116000072 | 4634 | 4E1 | CON | N/A | 1458842.42 | 1408842.42 | 50000 | 2027-04-30
01 | Mendocino Council of Governments | Pedestrian and Bike Path | Covelo Trail Phase 2. On Mendocino-162 between Biggar Lane and Hurt Road | ATPL | 6140(045) | 0116000079 | 4632 | 3 | CON | N/A | 347243.83 | 296963.83 | 50280 | 2027-04-30

## District 3
ATP Projects with Lapsing General Funds
Reversion Date: | 2027-06-30
Appropriation/Item Number: | 2660-102-0001
Year of Appropriation: | 2122
Appropriation Unit: | 22102
Program: | 2030
District | Parties to Agreement (Agency) | Purpose of Project (Work Description) | Scope (Location) | Prefix | Project Id | Advantage Project Id | PPNO | Advantage Phase | Phase | Federal Program Code | Budgeted Amount | Expenditure Amount | Remaining Balance | CTC TUF Deadline | Is Project Consistent with Original Scope and Purpose of the Appropriation? If No, Please Explain: | Are You Requesting a CWA (Yes or No)? If No, provide an anticipated date the agency plans to submit invoice for the remaining balance | Reason for Delay | If Other for Reason for Delay, Provide Explanation | Please Provide a 2-3 Sentence Explanation Identifying Any Impediments to Completion | What are the Consequences if CWA is Not Approved? (Please Provide a 2-3 Sentence Explanation) | Local Agency Contact Name | Local Agency Contact Phone Number | Local Agency Contact Email | Approved by DOF (Yes or No)? | Revised Reversion Date
03 | Sacramento | Two Rivers Bike Trail Phase II | South side of the American River between State Route 160 and H Street | CML | 5002(155) | 0312000138 | 1768 | 3 | CON | N/A | 967770 | 400064.66 | 567705.34 | 2026-12-12
03 | Paradise | Construct a grade separated Class I bike-pedestrian facility along the west side of Pentz Road | Along Pentz Road between Pearson Road and Bille Road, and from Wagstaff Road and Skyway | CML | 5425(042) | 0319000245 | 6123 | 1 | PS&E | N/A | 150000 | 28205.83 | 121794.17 | 2027-06-30
03 | Paradise | Construct a grade separated Class I bike-pedestrian facility along the west side of Pentz Road | Along Pentz Road between Pearson Road and Bille Road, and from Wagstaff Road and Skyway | CML | 5425(042) | 0319000245 | 6123 | SE1 | PS&E | N/A | 1948000 | 572830.62 | 1375169.38 | 2027-06-30
03 | Butte County | Noninfrastructure Component of South Oroville Bike and Pedestrian Connectivity Project | Monte Vista Avenue from Lincoln Boulevard to Lower Wyandotte Road, Autry Lane from Monte Vista Avenue to Las Plumas Avenue, the west side of Lower Wyandotte Road from Monte Vista Avenue to Las Plumas Avenue | ATPLNI | 5912(132) | 0323000307 | 6126B | 4 | CON-NI | N/A | 882000 | 462001.81 | 419998.19 | 2026-08-31
03 | Paradise | Five segments of sidewalk infill of which will close gaps in the existing Active Transportation Program (ATP) infrastructure | The Project is located on the east and west sides of Skyway between Bille Road and Wagstaff Road, and it is in the Town of Paradise in Butte County, California | ATPL | 5425(048) | 0323000308 | 6129 | 0 | PA&ED | N/A | 424000 | 177462.02 | 246537.98 | 2027-03-31

## District 4
ATP Projects with Lapsing General Funds
Reversion Date: | 2027-06-30
Appropriation/Item Number: | 2660-102-0001
Year of Appropriation: | 2122
Appropriation Unit: | 22102
Program: | 2030
District | Parties to Agreement (Agency) | Purpose of Project (Work Description) | Scope (Location) | Prefix | Project Id | Advantage Project Id | PPNO | Advantage Phase | Phase | Federal Program Code | Budgeted Amount | Expenditure Amount | Remaining Balance | CTC TUF Deadline | Is Project Consistent with Original Scope and Purpose of the Appropriation? If No, Please Explain: | Are You Requesting a CWA (Yes or No)? If No, provide an anticipated date the agency plans to submit invoice for the remaining balance | Reason for Delay | If Other for Reason for Delay, Provide Explanation | Please Provide a 2-3 Sentence Explanation Identifying Any Impediments to Completion | What are the Consequences if CWA is Not Approved? (Please Provide a 2-3 Sentence Explanation) | Local Agency Contact Name | Local Agency Contact Phone Number | Local Agency Contact Email | Approved by DOF (Yes or No)? | Revised Reversion Date
04 | Sonoma Marin Area Rail Transit District | Construct 5.7 miles of Class 1 pathway within the railroad right of way | Within publicly owed railroad r/w between Southpoint/McDowell in Petaluma to Main St in Penngrove and between Golf Course Drive in Rohnert Park to Bellevue Avenue in Santa Rosa | ATPSB1L | 6411(014) | 0421000027 | 2337 | 4 | CON | N/A | 9860583 | 9860522.3 | 60.7 | 2026-10-18
04 | Sonoma Marin Area Rail Transit District | Construct 5.7 miles of Class 1 pathway within the railroad right of way | Within publicly owed railroad r/w between Southpoint/McDowell in Petaluma to Main St in Penngrove and between Golf Course Drive in Rohnert Park to Bellevue Avenue in Santa Rosa | ATPSB1L | 6411(014) | 0421000027 | 2337 | 3 | CON | N/A | 896417 | 738433.44 | 157983.56 | 2026-10-18
04 | City & County of San Francisco, MTA/Parking & Traffic | Sidewalk | Project will improve three (3) blocks of Powell Street and will improve pedestrian safety and reduce sidewalk crowding | ATPL | 6328(096) | 0421000065 | 2313 | 3 | CON | N/A | 1250000 | 1147884.72 | 102115.28 | 2027-07-22
04 | City & County of San Francisco, MTA/Parking & Traffic | Sidewalk | Project will improve three (3) blocks of Powell Street and will improve pedestrian safety and reduce sidewalk crowding | ATPL | 6328(096) | 0421000065 | 2313 | 4 | CON | N/A | 3150000 | 808944.62 | 2341055.38 | 2027-07-22

## District 5
ATP Projects with Lapsing General Funds
Reversion Date: | 2027-06-30
Appropriation/Item Number: | 2660-102-0001
Year of Appropriation: | 2122
Appropriation Unit: | 22102
Program: | 2030
District | Parties to Agreement (Agency) | Purpose of Project (Work Description) | Scope (Location) | Prefix | Project Id | Advantage Project Id | PPNO | Advantage Phase | Phase | Federal Program Code | Budgeted Amount | Expenditure Amount | Remaining Balance | CTC TUF Deadline | Is Project Consistent with Original Scope and Purpose of the Appropriation? If No, Please Explain: | Are You Requesting a CWA (Yes or No)? If No, provide an anticipated date the agency plans to submit invoice for the remaining balance | Reason for Delay | If Other for Reason for Delay, Provide Explanation | Please Provide a 2-3 Sentence Explanation Identifying Any Impediments to Completion | What are the Consequences if CWA is Not Approved? (Please Provide a 2-3 Sentence Explanation) | Local Agency Contact Name | Local Agency Contact Phone Number | Local Agency Contact Email | Approved by DOF (Yes or No)? | Revised Reversion Date
05 | Santa Barbara County | Modoc Road Multimodal Path Gap Closure - Segment 2 | Construct 0.6 miles of path from Via Senda to the Obern Trail (Encore Drive) | ATPSB1L | 5951(165) | 0519000128 | 2992 | 4 | PS&E | N/A | 108600 | 0 | 108600 | 2026-06-30
05 | Watsonville | Bicycle Related - Other | Non-infrastructure to 3116A Safe Routes to Downtown Watsonville | ATPSB1NI | 5031(043) | 0523000083 | 3116B | 4 | CON-NI | N/A | 616000 | 285813.02 | 330186.98 | 2027-08-31
05 | Santa Cruz County | Bicycle Related - Other | Non-infrastructure to 3115A Coastal Rail Trail Segments 10 and 11 | ATPSB1NI | 5936(156) | 0523000084 | 3115B | 4 | CON-NI | N/A | 995000 | 633996.61 | 361003.39 | 2026-10-17
05 | Santa Cruz County Health Services Agency | Bicycle Related - Other | Provide a variety of Safe Routes to School (SRTS) programs to students and families as well as community active transportation programs | ATPSB1NI | 6448(004) | 0523000085 | 3129 | 4 | CON-NI | N/A | 1881000 | 992027.06 | 888972.94 | 2027-12-31
05 | University of California - Santa Cruz | Bicycle Related - Other | Further develop a robust and culturally inclusive bike safety, education, and encouragement program to suit the campus needs | ATPSB1NI | 6171(013) | 0523000086 | 3132 | 4 | CON-NI | N/A | 712000 | 283380.87 | 428619.13 | 2028-04-30
05 | Salinas | Alisal Safe Routes to School Project | Alisal Safe Routes to School Project | ATPSL | 5045(040) | 0523000091 | 3127A | 3 | CON | N/A | 119204 | 45714.73 | 73489.27 | 2027-10-31
05 | Lompoc | Walkability, Community Safety and School Investments Project | The City of Lompoc | ATPNIL | 5080(035) | 0523000183 | 3112B | 4 | CON-NI | N/A | 707000 | 332589.7 | 374410.3 | 2026-12-31
05 | Santa Cruz | Bicycle Related - Other | Cyc 6: Rail Trail Segments 8 & 9 NI-Component | ATPSB1NI | 5025(086) | 0523000259 | 2835C | 4 | CON-NI | N/A | 992000 | 590988.43 | 401011.57 | 2026-11-18
05 | King City | Pedestrian and Bike Path | San Antonio Drive Path & Safe Routes to Schools | ATP | 5194(008) | 0523000338 | 3131A | 0 | PA&ED | N/A | 350000 | 232380.28 | 117619.72 | 2027-02-28
05 | Arroyo Grande | Pedestrian and Bike facilities, roundabout, and road diet | Within the City of Arroyo Grande, along North Halcyon Road and South Halcyon Road between United States 101 and the southern city limits at The Pike | ATPSB1 | 5199(035) | 0524000094 | 3123A | 1 | PS&E | N/A | 777600 | 522548.9 | 255051.1 | 2027-06-30
05 | Arroyo Grande | Pedestrian and Bike facilities, roundabout, and road diet | Within the City of Arroyo Grande, along North Halcyon Road and South Halcyon Road between United States 101 and the southern city limits at The Pike | ATPSB1 | 5199(035) | 0524000094 | 3123A | S | PS&E | N/A | 526400 | 8335.12 | 518064.88 | 2027-06-30

## District 6
ATP Projects with Lapsing General Funds
Reversion Date: | 2027-06-30
Appropriation/Item Number: | 2660-102-0001
Year of Appropriation: | 2122
Appropriation Unit: | 22102
Program: | 2030
District | Parties to Agreement (Agency) | Purpose of Project (Work Description) | Scope (Location) | Prefix | Project Id | Advantage Project Id | PPNO | Advantage Phase | Phase | Federal Program Code | Budgeted Amount | Expenditure Amount | Remaining Balance | CTC TUF Deadline | Is Project Consistent with Original Scope and Purpose of the Appropriation? If No, Please Explain: | Are You Requesting a CWA (Yes or No)? If No, provide an anticipated date the agency plans to submit invoice for the remaining balance | Reason for Delay | If Other for Reason for Delay, Provide Explanation | Please Provide a 2-3 Sentence Explanation Identifying Any Impediments to Completion | What are the Consequences if CWA is Not Approved? (Please Provide a 2-3 Sentence Explanation) | Local Agency Contact Name | Local Agency Contact Phone Number | Local Agency Contact Email | Approved by DOF (Yes or No)? | Revised Reversion Date
06 | Huron | Add Class II, III, IV bike lanes and six (6) new crosswalks with safety features | Lassen Avenue, Palmer Avenue, M Street and 4th Street in Huron | ATPL | 5305(021) | 0621000222 | 7079 | 4 | CON | N/A | 1351082.7 | 1313269.81 | 37812.89 | 2027-01-25
06 | Huron | Add Class II, III, IV bike lanes and six (6) new crosswalks with safety features | Lassen Avenue, Palmer Avenue, M Street and 4th Street in Huron | ATPL | 5305(021) | 0621000222 | 7079 | 3 | CON | N/A | 292917.3 | 95103.94 | 197813.36 | 2027-01-25
06 | Fresno | Install two traffic signals, two curb ramps, and SRTS education | Amador & Trinity and Church & Waldby intersections | ATPSB1L | 5060(391) | 0622000045 | 7074A | 3 | CON | N/A | 188400 | 186400 | 2000 | 2027-06-25
06 | Fresno | Install two traffic signals, two curb ramps, and SRTS education | Amador & Trinity and Church & Waldby intersections | ATPSB1L | 5060(391) | 0622000045 | 7074A | 4 | CON | N/A | 40000 | 0 | 40000 | 2027-06-25
06 | Fresno | Install two traffic signals, two curb ramps, and SRTS education | Amador & Trinity and Church & Waldby intersections | ATPSB1L | 5060(391) | 0622000045 | 7074A | 4E1 | CON | N/A | 1252600 | 1212600 | 40000 | 2027-06-25
06 | Madera County | Install bike lanes, sidewalk, Americans with Disability Act (ADA) ramps, crosswalks, flashing beacon, street lights, curb and gutter | In Madera County, unincorporated community of La Vina beginning at the Avenue 9 and Road 24, West along both sides of Avenue 9 to Road 23 1/2 | ATPL | 5941(136) | 0623000205 | 8017 | 1 | PS&E | N/A | 300000 | 250098.91 | 49901.09 | 2026-06-30
06 | Madera County | Install bike lanes, sidewalk, Americans with Disability Act (ADA) ramps, crosswalks, flashing beacon, street lights, curb and gutter | In Madera County, unincorporated community of La Vina beginning at the Avenue 9 and Road 24, West along both sides of Avenue 9 to Road 23 1/2 | ATPL | 5941(136) | 0623000205 | 8017 | S | PS&E | N/A | 95000 | 0 | 95000 | 2026-06-30

## District 7
ATP Projects with Lapsing General Funds
Reversion Date: | 2027-06-30
Appropriation/Item Number: | 2660-102-0001
Year of Appropriation: | 2122
Appropriation Unit: | 22102
Program: | 2030
District | Parties to Agreement (Agency) | Purpose of Project (Work Description) | Scope (Location) | Prefix | Project Id | Advantage Project Id | PPNO | Advantage Phase | Phase | Federal Program Code | Budgeted Amount | Expenditure Amount | Remaining Balance | CTC TUF Deadline | Is Project Consistent with Original Scope and Purpose of the Appropriation? If No, Please Explain: | Are You Requesting a CWA (Yes or No)? If No, provide an anticipated date the agency plans to submit invoice for the remaining balance | Reason for Delay | If Other for Reason for Delay, Provide Explanation | Please Provide a 2-3 Sentence Explanation Identifying Any Impediments to Completion | What are the Consequences if CWA is Not Approved? (Please Provide a 2-3 Sentence Explanation) | Local Agency Contact Name | Local Agency Contact Phone Number | Local Agency Contact Email | Approved by DOF (Yes or No)? | Revised Reversion Date
07 | Oxnard | Install Sidewalk, Curb/Gutter, Access Ramps, Bike Lanes, Crosswalk, Flashing Beacons, Signage and Strip | Etting Road Between Pleasant Valley Road And City Of Oxnard boundary | ATPL | 5129(098) | 0720000225 | 5532 | 4 | CON | N/A | 871000 | 212228.57 | 658771.43 | 2026-10-17
07 | Oxnard | Provide Safe Routes To Six Schools In Oxnard By Installing Enhanced Safety Crossing Improvements | Provide safe routes to six (6) schools in Oxnard by installing enhanced safety crossing improvements and implementing a Citywide non-infrastructure program for all 26 schools | ATPSB1L | 5129(102) | 0722000026 | 5897A | 3 | CON | N/A | 20000 | 0 | 20000 | 2027-06-04
07 | Oxnard | Provide Safe Routes To Six Schools In Oxnard By Installing Enhanced Safety Crossing Improvements | Provide safe routes to six (6) schools in Oxnard by installing enhanced safety crossing improvements and implementing a Citywide non-infrastructure program for all 26 schools | ATPSB1L | 5129(102) | 0722000026 | 5897A | 4 | CON | N/A | 1460000 | 1420000 | 40000 | 2027-06-04
07 | Southern California Association of Governments | Pomona and Wilshire Center Quick Build Implementation | Design and install a quick build projects in various locations in the City of Los Angeles and the City of Pomona | ATPL | 6049(029) | 0723000203 | 5979Q | 3 | CON | N/A | 892878 | 769633.24 | 123244.76 | 2026-12-13
07 | Southern California Association of Governments | Pomona and Wilshire Center Quick Build Implementation | Design and install a quick build projects in various locations in the City of Los Angeles and the City of Pomona | ATPL | 6049(029) | 0723000203 | 5979Q | 4 | CON | N/A | 264122 | 0 | 264122 | 2026-12-13
07 | Lancaster | Rebuild Lancaster's SRTS Education and Encouragement Programs after 2022 update | This non-infrastructure education/encouragement Project will be implemented throughout the City of Lancaster with a special emphasis on programs at ten (10) Focus Schools in three (3) different school districts | ATPL | 5419(066) | 0723000210 | 6047 | 4 | CON-NI | N/A | 796000 | 290151.62 | 505848.38 | 2027-10-31
07 | Los Angeles County | Sidewalk | Various locations near the Firestone, Willowbrook/Rosa Parks, and Del Amo Metro A line stations in the unincorporated areas of Los Angeles County | ATPL | 5953(797) | 0723000256 | 6039 | 0 | PA&ED | N/A | 810000 | 199173.93 | 610826.07 | 2027-06-30
07 | Los Angeles | Pedestrian and Bike Path | Pedestrian and bike safety improvements including enhanced pedestrian crossings, traffic signal modifications and low-stress bicycle facilities to address community-identified mobility barriers | ATPL | 5006(948) | 0723000279 | 6049 | 0 | PA&ED | N/A | 2740000 | 1394215.76 | 1345784.24 | 2028-06-30
07 | Santa Monica | Non-infrastructure - cycling classes and a safety campaign to educate road users on safety hazards | Stewart-Pennsylvania Safety Enhancement Project - Non-Infrastructure Component | ATPLNI | 5107(055) | 0724000048 | 5861B | 4 | CON-NI | N/A | 25000 | 0 | 25000 | 2027-04-30
07 | Los Angeles County | Road Rehabilitation | On El Segundo Boulevard between Figueroa Street and Avalon Boulevard, and on San Pedro Street between El Segundo Boulevard and Rosecrans Avenue in the Unincorporated Community of Rosewood in Los Angeles County | ATPL | 5953(799) | 0724000057 | 6157 | 0 | PA&ED | N/A | 766000 | 439018.92 | 326981.08 | 2027-06-30
07 | Los Angeles County | Five Community Pedestrian Plans for high-collision disadvantaged communities in Los Angeles County | Unincorporated Los Angeles County: Alondra Park, Del Aire, Rancho Dominguez, West Carson, West Puente Valley, Valinda, South San Jose Hills | ATPL | 5953(802) | 0724000100 | 6178 | 4 | CON-NI | N/A | 1968000 | 801045.62 | 1166954.38 | 2027-06-05
07 | Long Beach | Non-Infrastructure | Pine Avenue Bicycle Boulevard - Non-Infrastructure Conduct pedestrian safety education, targeted messaging, and interactive activities that model desired safety behaviors | ATPLNI | 5108(216) | 0724000101 | 5895B | 4 | CON-NI | N/A | 514000 | 0 | 514000 | 2026-12-07

## District 8
ATP Projects with Lapsing General Funds
Reversion Date: | 2027-06-30
Appropriation/Item Number: | 2660-102-0001
Year of Appropriation: | 2122
Appropriation Unit: | 22102
Program: | 2030
District | Parties to Agreement (Agency) | Purpose of Project (Work Description) | Scope (Location) | Prefix | Project Id | Advantage Project Id | PPNO | Advantage Phase | Phase | Federal Program Code | Budgeted Amount | Expenditure Amount | Remaining Balance | CTC TUF Deadline | Is Project Consistent with Original Scope and Purpose of the Appropriation? If No, Please Explain: | Are You Requesting a CWA (Yes or No)? If No, provide an anticipated date the agency plans to submit invoice for the remaining balance | Reason for Delay | If Other for Reason for Delay, Provide Explanation | Please Provide a 2-3 Sentence Explanation Identifying Any Impediments to Completion | What are the Consequences if CWA is Not Approved? (Please Provide a 2-3 Sentence Explanation) | Local Agency Contact Name | Local Agency Contact Phone Number | Local Agency Contact Email | Approved by DOF (Yes or No)? | Revised Reversion Date
08 | Riverside County | Safe Route for All - City of Moreno Valley Non-Infrastructure | Riverside County Safe Route for All - City of Moreno Valley non-infrastructure | ATPL | 5956(292) | 0824000011 | 1298 | 4 | CON-NI | N/A | 442000 | 129050.98 | 312949.02 | 2026-12-07
08 | Montclair | Install and/or enhance sidewalks, bike lanes/routes, crosswalks, Americans with Disability Act (ADA) curbs, signage near three (3) schools | The project is located in the City of Montclair (population 40,041) at adjacent public schools: 1) Montclair High School; 2) Montera Elementary; and 3) Monte Vista Elementary | ATPL | 5326(025) | 0824000043 | 1305A | 0 | PA&ED | N/A | 130000 | 14914.37 | 115085.63 | 2026-06-30

## District 10
ATP Projects with Lapsing General Funds
Reversion Date: | 2027-06-30
Appropriation/Item Number: | 2660-102-0001
Year of Appropriation: | 2122
Appropriation Unit: | 22102
Program: | 2030
District | Parties to Agreement (Agency) | Purpose of Project (Work Description) | Scope (Location) | Prefix | Project Id | Advantage Project Id | PPNO | Advantage Phase | Phase | Federal Program Code | Budgeted Amount | Expenditure Amount | Remaining Balance | CTC TUF Deadline | Is Project Consistent with Original Scope and Purpose of the Appropriation? If No, Please Explain: | Are You Requesting a CWA (Yes or No)? If No, provide an anticipated date the agency plans to submit invoice for the remaining balance | Reason for Delay | If Other for Reason for Delay, Provide Explanation | Please Provide a 2-3 Sentence Explanation Identifying Any Impediments to Completion | What are the Consequences if CWA is Not Approved? (Please Provide a 2-3 Sentence Explanation) | Local Agency Contact Name | Local Agency Contact Phone Number | Local Agency Contact Email | Approved by DOF (Yes or No)? | Revised Reversion Date
10 | Tuolumne County | Pedestrian Walkway | Vicinity of Jamestown Elementary School- approximately 4,200 linear feet of new sidewalk, separated paths, curb and gutter, Americans with Disability Act (ADA) improvements, and crosswalks | ATPL | 5932(102) | 1022000028 | 3512 | 1 | PS&E | N/A | 147000 | 118597.25 | 28402.75 | 2027-02-28
10 | Stockton | Pedestrian and Bike Path | On Alpine Avenue from Ryde Avenue to Pershing Avenue, Pershing Avenue from Alpine Avenue to Mendocino Avenue, and Medocino Avenue from Pershing Avenue to Kensington Way | ATPSB1L | 5008(205) | 1023000260 | 3565 | 0 | PA&ED | N/A | 389000 | 255208.16 | 133791.84 | 2027-06-30

## District 11
ATP Projects with Lapsing General Funds
Reversion Date: | 2027-06-30
Appropriation/Item Number: | 2660-102-0001
Year of Appropriation: | 2122
Appropriation Unit: | 22102
Program: | 2030
District | Parties to Agreement (Agency) | Purpose of Project (Work Description) | Scope (Location) | Prefix | Project Id | Advantage Project Id | PPNO | Advantage Phase | Phase | Federal Program Code | Budgeted Amount | Expenditure Amount | Remaining Balance | CTC TUF Deadline | Is Project Consistent with Original Scope and Purpose of the Appropriation? If No, Please Explain: | Are You Requesting a CWA (Yes or No)? If No, provide an anticipated date the agency plans to submit invoice for the remaining balance | Reason for Delay | If Other for Reason for Delay, Provide Explanation | Please Provide a 2-3 Sentence Explanation Identifying Any Impediments to Completion | What are the Consequences if CWA is Not Approved? (Please Provide a 2-3 Sentence Explanation) | Local Agency Contact Name | Local Agency Contact Phone Number | Local Agency Contact Email | Approved by DOF (Yes or No)? | Revised Reversion Date
11 | Encinitas | Bike and Pedestrian Improvements | In Encinitas along North & South of Santa Fe Drive between Windsor Road and El Camino Real, in vicinity of San Dieguito Academy High, Ocean Knoll Elementary School, Oak Crest Middle School and Alta Harris | ATPSB1L | 5446(025) | 1118000207 | 1299A | 4 | CON | N/A | 742000 | 0 | 742000 | 2027-09-26
11 | San Diego Association of Governments | Bike Path | One mile of Class 1 bikeway, in railroad Right of Way (ROW), extending the Inland Rail Trail Corridor, including improvements at roadway crossings and fencing | ATPSB1L | 6066(140) | 1118000226 | 1328 | 4 | CON | N/A | 1517793 | 1447000.63 | 70792.37 | 2027-02-14
11 | National City | Bicycle Related - Other | The project will install more than 100 bicycle wayfinding signs at decision points throughout the City's recently constructed bicycle network | ATPSB1L | 5066(047) | 1120000087 | 1362 | 3 | CON | N/A | 110000 | 47147.23 | 62852.77 | 2027-03-19
11 | National City | Bicycle Related - Other | The project will install more than 100 bicycle wayfinding signs at decision points throughout the City's recently constructed bicycle network | ATPSB1L | 5066(047) | 1120000087 | 1362 | 4 | CON | N/A | 722000 | 20263.5 | 701736.5 | 2027-03-19
11 | National City | Pedestrian and Bike Path | Implement a North-South bicycle boulevard, close a sidewalk gap, and provide pedestrian enhancements in National City along M, N, and L Avenues, between 4th Street and 30th Street | ATPSB1L | 5066(048) | 1120000089 | 1360 | 4 | CON | N/A | 1095000 | 738087.08 | 356912.92 | 2027-10-15
11 | Encinitas | Bicycle Related - Other | Non-infrastructure portion of Santa Fe Drive Improvements | ATPLNI | 5446(035) | 1123000126 | 1299B | 4 | CON-NI | N/A | 40000 | 0 | 40000 | 2027-01-17
11 | Lemon Grove | Road Related - Other | Connect Main Street is an active transportation corridor project including Class 1 multi-use paths, DG pedestrian trails, and bike boulevard | ATPL | 5418(023) | 1124000078 | 1524 | 1 | PS&E | N/A | 374000 | 0 | 374000 | 2027-06-30
11 | Lemon Grove | Pedestrian and Bike Path | Lemon Grove, CA Main Street between Mount Vernon Street and Massachusetts Avenue | ATPL | 5418(024) | 1124000079 | 1525 | 0 | PA&ED | N/A | 115000 | 0 | 115000 | 2027-03-31
11 | San Diego | Accessibility Safety Plan for Individuals with Disabilities in Disadvantaged Communities | In the City of San Diego: South of Interstate--8 and east of Interstate-5 between Interstate-8 and Laurel Street | ATPLNI | 5004(222) | 1124000084 | 1535 | 4 | CON-NI | N/A | 1239000 | 578644.53 | 660355.47 | 2027-05-29

## District 12
ATP Projects with Lapsing General Funds
Reversion Date: | 2027-06-30
Appropriation/Item Number: | 2660-102-0001
Year of Appropriation: | 2122
Appropriation Unit: | 22102
Program: | 2030
District | Parties to Agreement (Agency) | Purpose of Project (Work Description) | Scope (Location) | Prefix | Project Id | Advantage Project Id | PPNO | Advantage Phase | Phase | Federal Program Code | Budgeted Amount | Expenditure Amount | Remaining Balance | CTC TUF Deadline | Is Project Consistent with Original Scope and Purpose of the Appropriation? If No, Please Explain: | Are You Requesting a CWA (Yes or No)? If No, provide an anticipated date the agency plans to submit invoice for the remaining balance | Reason for Delay | If Other for Reason for Delay, Provide Explanation | Please Provide a 2-3 Sentence Explanation Identifying Any Impediments to Completion | What are the Consequences if CWA is Not Approved? (Please Provide a 2-3 Sentence Explanation) | Local Agency Contact Name | Local Agency Contact Phone Number | Local Agency Contact Email | Approved by DOF (Yes or No)? | Revised Reversion Date
12 | Santa Ana | Bike lane and protected intersection | Standard Avenue from 3rd Street to Warner Avenue in the City of Santa Ana | ATPSB1L | 5063(196) | 1220000016 | 2199 | 4 | CON | N/A | 4771305 | 4522145.76 | 249159.24 | 2027-09-23
12 | Santa Ana | Bike lane and protected intersection | Standard Avenue from 3rd Street to Warner Avenue in the City of Santa Ana | ATPSB1L | 5063(196) | 1220000016 | 2199 | 3 | CON | N/A | 672695 | 312583.13 | 360111.87 | 2027-09-23
12 | Santa Ana | Class 4 Protected Bike Lane and Class 3 Bike Boulevard including signing, striping, bike detection | McFadden Avenue from Harbor Boulevard to Grand Avenue in the City of Santa Ana | ATPSB1L | 5063(198) | 1220000018 | 2198 | 3 | CON | N/A | 647634 | 475242.89 | 172391.11 | 2027-09-23
12 | Santa Ana | Class 4 Protected Bike Lane and Class 3 Bike Boulevard including signing, striping, bike detection | McFadden Avenue from Harbor Boulevard to Grand Avenue in the City of Santa Ana | ATPSB1L | 5063(198) | 1220000018 | 2198 | 4 | CON | N/A | 5227366 | 1554241.01 | 3673124.99 | 2027-09-23
12 | Santa Ana | Bike Path | Orange Avenue from 1st Street to Warner Avenue in the City of Santa Ana | ATPL | 5063(212) | 1223000100 | 1310 | 1E1 | PS&E | N/A | 82153.21 | 0 | 82153.21 | 2027-06-30
12 | Orange County Transportation Authority | Traffic Related - Other | Non-Infrastructure Next Safe Travels Education Program (STEP) provides education and encouragement activities as well as infrastructure recommendation for safer travel to schools | ATPLNI | 6071(190) | 1224000021 | 1311 | 4 | CON-NI | N/A | 850000 | 69500 | 780500 | 2027-06-10

## Drop-down Reference Tables
Within Scope? | Need a CWA? | Primary Reason For Delay:
YES | YES | Design: Change in scope.
NO | NO | Design: Change in specifications.
Design: Change in site conditions.
Environmental: Change in scope requires additional studies/permits.
Environmental: Excessive study or opinion review time by external agencies.
Environmental: Permits expired.
Environmental: Environmental document determination revalidation required.
Environmental: Mitigation for project impacts period.
Right of Way and Utility Relocation: Change in scope/number of parcels/utility relocations required.
Right of Way and Utility Relocation: Condemnation/eminent domain proceedings.
Right of Way and Utility Relocation: Utility owner dispute.
Right of Way and Utility Relocation: Qualified Buy America purchase/delivery delays.
Construction: Contract award disputed/cancelled, rebid or complete under force account.
Construction: Change in site conditions.
Construction: Qualified Buy America purchase/delivery delays.
Construction: Extended winter suspension affecting delivery schedule.
Contract Dispute/Litigation: Post-construction claim. Informal settlement.
Contract Dispute/Litigation: Formal litigation proceeding.
Finance: CTC approved Time Extension conflicts with reversion date.
Finance: Indirect Cost Rate Proposal (ICRP) request package returned with errors.
Finance: Change in dedicated/programmed funding.
Finance: Pending programming.
OTHER-declared disaster (explain):
OTHER (explain):