## District
ATP Projects with Lapsing State Funds
Reversion Date: | 2027-06-30
Appropriation/Item Number: | 2660-108-0042
Year of Appropriation: | 2122
Appropriation Unit: | 22108
Program: | 2030
District | Parties to Agreement (Agency) | Purpose of Project (Work Description) | Scope (Location) | Prefix | Project Id | Advantage Project Id | PPNO | Advantage Phase | Phase | Federal Program Code | Budgeted Amount | Expenditure Amount | Remaining Balance | CTC TUF Deadline | Is Project Consistent with Original Scope and Purpose of the Appropriation? If No, Please Explain: | Are You Requesting a CWA (Yes or No)? If No, provide an anticipated date the agency plans to submit invoice for the remaining balance | Reason for Delay | If Other for Reason for Delay, Provide Explanation | Please Provide a 2-3 Sentence Explanation Identifying Any Impediments to Completion | What are the Consequences if CWA is Not Approved? (Please Provide a 2-3 Sentence Explanation) | Local Agency Contact Name | Local Agency Contact Phone Number | Local Agency Contact Email | Approved by DOF (Yes or No)? | Revised Reversion Date
00 | Caltrans | Active Transportation Resource Center (ATRC). The Active Transportation Resource Center mission is to provide resources, technical assistance, and training to partners across CA. | Statewide | ATPLNI | 6200(041) | 0022000323 | 0776 | S | CON-NI | N/A | 2310000 | 1053359.25 | 1256640.75
07 | Southern California Association of Governments | Santa Monica East Pico Quick Build | Design and install a quick build project on East Pico Boulevard between 28th Street and 34th Street in the City of Santa Monica | ATPL | 6049(027) | 0722000256 | 5978Q | 3 | CON | N/A | 437466 | 426223.73 | 11242.27 | 2026-08-31
07 | Southern California Association of Governments | Santa Monica East Pico Quick Build | Design and install a quick build project on East Pico Boulevard between 28th Street and 34th Street in the City of Santa Monica | ATPL | 6049(027) | 0722000256 | 5978Q | 4 | CON | N/A | 362534 | 322534 | 40000 | 2026-08-31
08 | San Bernardino County | Safe Route to Schools | San Bernardino County Transportation Authority (SBCTA) is partnering with San Bernardino County Department of Public Health (SBC DPH) to extend the county-wide Safe Routes to School (SRTS) Education, Encouragement, Evaluation and Enforcement Program | ATPSB1NI | 6507(021) | 0820000125 | 1269 | 4 | SN | N/A | 500000 | 277919.69 | 222080.31 | 2027-07-31

## Drop-down Reference Tables
Within Scope? | Need a CWA? | Primary Reason For Delay:
YES | YES | Design: Change in scope.
NO | NO | Design: Change in specifications.
Design: Change in site conditions.
Environmental: Change in scope requires additional studies/permits.
Environmental: Excessive study or opinion review time by external agencies.
Environmental: Permits expired.
Environmental: Environmental document determination revalidation required.
Environmental: Mitigation for project impacts period.
Right of Way and Utility Relocation: Change in scope/number of parcels/utility relocations required.
Right of Way and Utility Relocation: Condemnation/eminent domain proceedings.
Right of Way and Utility Relocation: Utility owner dispute.
Right of Way and Utility Relocation: Qualified Buy America purchase/delivery delays.
Construction: Contract award disputed/cancelled, rebid or complete under force account.
Construction: Change in site conditions.
Construction: Qualified Buy America purchase/delivery delays.
Construction: Extended winter suspension affecting delivery schedule.
Contract Dispute/Litigation: Post-construction claim. Informal settlement.
Contract Dispute/Litigation: Formal litigation proceeding.
Finance: CTC approved Time Extension conflicts with reversion date.
Finance: Indirect Cost Rate Proposal (ICRP) request package returned with errors.
Finance: Change in dedicated/programmed funding.
Finance: Pending programming.
OTHER-declared disaster (explain):
OTHER (explain):