## District 0
Projects with Lapsing State Funds
Reversion Date: | 2027-06-30
Appropriation/Item Number: | 2660-102-0042
Year of Appropriation: | 2122
Appropriation Unit: | 22102
Program: | 2030
District | Parties to Agreement (Agency) | Purpose of Project (Work Description) | Scope (Location) | Prefix | Project Id | Advantage Project Id | Advantage Phase | Budgeted Amount | Expenditure Amount | Remaining Balance | Is Project Consistent with Original Scope and Purpose of the Appropriation? If No, Please Explain: | Are You Requesting a CWA (Yes or No)? If No, provide an anticipated date the agency plans to submit invoice for the remaining balance | Reason for Delay | If Other for Reason for Delay, Provide Explanation | Please Provide a 2-3 Sentence Explanation Identifying Any Impediments to Completion | What are the Consequences if CWA is Not Approved? (Please Provide a 2-3 Sentence Explanation) | Local Agency Contact Name | Local Agency Contact Phone Number | Local Agency Contact Email | Approved by DOF (Yes or No)? | Revised Reversion Date
0 | Caltrans | Discretionary Safety Grant Training | Statewide | N/A | N/A | 0024000012 | SE1 | 117743.5 | 0 | 117743.5

## District 1
Projects with Lapsing State Funds
Reversion Date: | 2027-06-30
Appropriation/Item Number: | 2660-102-0042
Year of Appropriation: | 2122
Appropriation Unit: | 22102
Program: | 2030
District | Parties to Agreement (Agency) | Purpose of Project (Work Description) | Scope (Location) | Prefix | Project Id | Advantage Project Id | Advantage Phase | Budgeted Amount | Expenditure Amount | Remaining Balance | Is Project Consistent with Original Scope and Purpose of the Appropriation? If No, Please Explain: | Are You Requesting a CWA (Yes or No)? If No, provide an anticipated date the agency plans to submit invoice for the remaining balance | Reason for Delay | If Other for Reason for Delay, Provide Explanation | Please Provide a 2-3 Sentence Explanation Identifying Any Impediments to Completion | What are the Consequences if CWA is Not Approved? (Please Provide a 2-3 Sentence Explanation) | Local Agency Contact Name | Local Agency Contact Phone Number | Local Agency Contact Email | Approved by DOF (Yes or No)? | Revised Reversion Date
01 | Humboldt County | Road Related - Edge Lines | Various County, Tribal and Bureau of Indian Affairs roads within Humboldt County Tribal Indian Reservation Roads system Hoopa, Karuk and Yurok tribes are participating agencies | HSIPSL | 5904(192) | 0123000126 | S | 36000 | 23435.11 | 12564.89

## District 3
Projects with Lapsing State Funds
Reversion Date: | 2027-06-30
Appropriation/Item Number: | 2660-102-0042
Year of Appropriation: | 2122
Appropriation Unit: | 22102
Program: | 2030
District | Parties to Agreement (Agency) | Purpose of Project (Work Description) | Scope (Location) | Prefix | Project Id | Advantage Project Id | Advantage Phase | Budgeted Amount | Expenditure Amount | Remaining Balance | Is Project Consistent with Original Scope and Purpose of the Appropriation? If No, Please Explain: | Are You Requesting a CWA (Yes or No)? If No, provide an anticipated date the agency plans to submit invoice for the remaining balance | Reason for Delay | If Other for Reason for Delay, Provide Explanation | Please Provide a 2-3 Sentence Explanation Identifying Any Impediments to Completion | What are the Consequences if CWA is Not Approved? (Please Provide a 2-3 Sentence Explanation) | Local Agency Contact Name | Local Agency Contact Phone Number | Local Agency Contact Email | Approved by DOF (Yes or No)? | Revised Reversion Date
03 | Isleton | Systemic Improvements at Unsignalized Intersections | Various intersections throughout the city: H Street/Main Street, 2nd Street/A Street/State Route-160, State Route-160/H Street, and Union Street/D Street | HSIPSL | 5260(002) | 0323000281 | S | 6840 | 0 | 6840
03 | Elk Grove | Install Advanced dilemma zone detectors | 76 locations in City of Elk Grove | HSIPSL | 5479(073) | 0322000240 | S | 8810200 | 6902273.87 | 1907926.13
03 | Butte County | High Friction Surface Treatment | Various locations within Butte County | HSIPSL | 5912(129) | 0323000253 | S | 90000 | 59695.61 | 30304.39
03 | Butte County | Butte County Road Safety Signing Audit | Various road sections throughout Butte County | HSIPSL | 5912(130) | 0323000254 | S | 153000 | 146699.77 | 6300.23
03 | Butte County | Guardrail | East Gridley Road, La Porte Road, Lower Wyandotte Road, and River Road | HSIPSL | 5912(133) | 0324000068 | S | 40500 | 35554.61 | 4945.39
03 | El Dorado County | Install approximately 65,000 feet of recessed edge lines | Sly Park Road, Carson Road, and Pony Express Trail | HSIPSL | 5925(186) | 0322000015 | S | 67192.56 | 59741.61 | 7450.95
03 | Butte County Association of Governments | Planning, Programming and Monitoring | Butte County | CRRSAA | 6092(085) | 0323000023 | S | 900000 | 590322.24 | 309677.76

## District 4
Projects with Lapsing State Funds
Reversion Date: | 2027-06-30
Appropriation/Item Number: | 2660-102-0042
Year of Appropriation: | 2122
Appropriation Unit: | 22102
Program: | 2030
District | Parties to Agreement (Agency) | Purpose of Project (Work Description) | Scope (Location) | Prefix | Project Id | Advantage Project Id | Advantage Phase | Budgeted Amount | Expenditure Amount | Remaining Balance | Is Project Consistent with Original Scope and Purpose of the Appropriation? If No, Please Explain: | Are You Requesting a CWA (Yes or No)? If No, provide an anticipated date the agency plans to submit invoice for the remaining balance | Reason for Delay | If Other for Reason for Delay, Provide Explanation | Please Provide a 2-3 Sentence Explanation Identifying Any Impediments to Completion | What are the Consequences if CWA is Not Approved? (Please Provide a 2-3 Sentence Explanation) | Local Agency Contact Name | Local Agency Contact Phone Number | Local Agency Contact Email | Approved by DOF (Yes or No)? | Revised Reversion Date
04 | Oakland | Pedestrian Walkway | MacArthur Boulevard/90th Avenue and Bancroft Avenue/90th Avenue. These are two signalized intersections in Oakland's priority equity census tracts | HSIPSL | 5012(171) | 0423000470 | S | 193500 | 0 | 193500
04 | Suisun City | Improve pedestrian crossing with upgrade, install Rectangular Rapid Flashing Beacon (RRFB) devices, bulbouts, high visibility crosswalks | Intersection of Marina Boulevard and Lotz Way and Pintail Drive and Cackling Drive | HSIPSL | 5032(038) | 0424000016 | S | 39240 | 35896.54 | 3343.46
04 | Suisun City | Install raised median to address left turn conflict | T-intersections: Walters Road and McClellan Drive, Railroad Avenue and Village Drive, and Railroad Avenue and Birchwood Drive | HSIPSL | 5032(039) | 0424000017 | S | 67050 | 62208 | 4842
04 | Dixon | Install high-visibility crosswalks, striping, signage, Rectangular Rapid Flashing Beacon (RRFB) system, Americans with Disability Act (ADA) ramps, and bulb-outs | East Mayes Street and South 3rd Street/ 4th Street, East A Street and North 4th Street, North 4th Street and East B Street and South 7th Street and East A Street | HSIPSL | 5056(021) | 0422000029 | S | 230800 | 0 | 230800
04 | Mill Valley | Upgrade existing timber and post guard rail | Four (4) locations between 700 and 759 East Blithedale Avenue Project location is a major arterial in Mill Valley and within Marin County | HSIPSL | 5113(022) | 0424000023 | S | 143550 | 86998 | 56552
04 | Concord | Improve traffic signal hardware, install pedestrian countdown signal heads | Various locations throughout the City of Concord | HSIPSL | 5135(060) | 0421000336 | S | 1748000 | 1516848.98 | 231151.02
04 | Cupertino | Install dynamic / variable speed warning signs along curves, improve pavement friction (High Friction Surface Treatments (HFST)) | De Anza Boulevard; Bollinger Road; Wolfe Road; McClellan Road; Bubb Road; Mariani Avenue; Tantau Avenue; Blaney Avenue; Rainbow Drive; Miller Avenue; Stelling Road; Valley Green Drive; Calvert Drive; and Mary Avenue | HSIPSL | 5318(034) | 0423000304 | S | 360000 | 86337.8 | 273662.2
04 | Contra Costa County | Install centerline rumble strips | Franklin Canyon Road between Cummings Skyway and Dutra Road | HSIPSL | 5928(161) | 0421000304 | S | 462400 | 297154.4 | 165245.6
04 | Contra Costa County | lighting, dynamic/variable speed warning signs, and rumble stripes | Byron Highway from Clifton Court Road to Bruns Road | HSIPSL | 5928(167) | 0423000291 | S | 207000 | 167000 | 40000
04 | San Mateo County | Pedestrian Walkway | Bunker Hill Drive from Brandywine Way to Yorktown Drive,-Highlands, Elementary South Park Plaza Drive -Garden, Village Elementary and Benjamin Franklin School, Alhambra Coronado to The Alameda | HSIPSL | 5935(086) | 0421000255 | S | 209500 | 0 | 209500

## District 5
Projects with Lapsing State Funds
Reversion Date: | 2027-06-30
Appropriation/Item Number: | 2660-102-0042
Year of Appropriation: | 2122
Appropriation Unit: | 22102
Program: | 2030
District | Parties to Agreement (Agency) | Purpose of Project (Work Description) | Scope (Location) | Prefix | Project Id | Advantage Project Id | Advantage Phase | Budgeted Amount | Expenditure Amount | Remaining Balance | Is Project Consistent with Original Scope and Purpose of the Appropriation? If No, Please Explain: | Are You Requesting a CWA (Yes or No)? If No, provide an anticipated date the agency plans to submit invoice for the remaining balance | Reason for Delay | If Other for Reason for Delay, Provide Explanation | Please Provide a 2-3 Sentence Explanation Identifying Any Impediments to Completion | What are the Consequences if CWA is Not Approved? (Please Provide a 2-3 Sentence Explanation) | Local Agency Contact Name | Local Agency Contact Phone Number | Local Agency Contact Email | Approved by DOF (Yes or No)? | Revised Reversion Date
05 | Santa Barbara | Curb Extensions, Signs and Markings to increase pedestrian Visibility | De La Vina and Valerio in the City of Santa Barbara | HSIPSL | 5007(103) | 0523000182 | S | 13500 | 6808.31 | 6691.69
05 | Salinas | Pedestrian Walkway | Main Street at Lamar Street. Pedestrian Enhancements | HSIPL | 5045(041) | 0523000195 | S | 22500 | 0 | 22500
05 | Salinas | Pedestrian Walkway | San Juan Grade Road Sidewalk and Street Light Improvements Project | HSIPSL | 5045(042) | 0523000196 | S | 63000 | 0 | 63000
05 | Soledad | Install Rectangular Rapid Flashing Beacon (RRFB) devices, beacons, bulb outs, crosswalks, bike boxes, streetlights, pavement markings | Various locations throughout the City | HSIPSL | 5248(010) | 0523000193 | S | 137700 | 0 | 137700
05 | Marina | New Traffic Signal and Safety Improvements | Imjin Parkway and 3rd Avenue Traffic Signal and Safety Improvements | HSIPSL | 5416(014) | 0523000194 | S | 137340 | 0 | 137340
05 | Santa Cruz County | Road Rehabilitation | Emergency Routes Resurfacing Project: Alba and Jamison Creek Roads | HIPL | 5936(150) | 0522000132 | SE2 | 1266120 | 1231120 | 35000
05 | Santa Barbara County | Install Rectangular Rapid Flashing Beacons | Lillie Avenue in Summerland, Hot Springs Road in Montecito, and Embarcadero del Mar/Embarcadero del Norte/Camino Pescadero/Camino del Sol in Isla Vista | HSIPSL | 5951(183) | 0523000342 | S | 13500 | 0 | 13500
05 | Transportation Agency for Monterey County |  | Transportation Agency for Monterey County 2021/2022 | FSP22SB1 | 6143(096) | 0522000020 | S | 191996 | 35834.55 | 156161.45
05 | Transportation Agency for Monterey County | Rail Extension to Monterey County | Rail extension to Monterey County, Package two (2) includes a layover facility and track improvements in Salinas | CRRSAASL | 6143(106) | 0524000140 | S | 2002850 | 1271504.67 | 731345.33

## District 6
Projects with Lapsing State Funds
Reversion Date: | 2027-06-30
Appropriation/Item Number: | 2660-102-0042
Year of Appropriation: | 2122
Appropriation Unit: | 22102
Program: | 2030
District | Parties to Agreement (Agency) | Purpose of Project (Work Description) | Scope (Location) | Prefix | Project Id | Advantage Project Id | Advantage Phase | Budgeted Amount | Expenditure Amount | Remaining Balance | Is Project Consistent with Original Scope and Purpose of the Appropriation? If No, Please Explain: | Are You Requesting a CWA (Yes or No)? If No, provide an anticipated date the agency plans to submit invoice for the remaining balance | Reason for Delay | If Other for Reason for Delay, Provide Explanation | Please Provide a 2-3 Sentence Explanation Identifying Any Impediments to Completion | What are the Consequences if CWA is Not Approved? (Please Provide a 2-3 Sentence Explanation) | Local Agency Contact Name | Local Agency Contact Phone Number | Local Agency Contact Email | Approved by DOF (Yes or No)? | Revised Reversion Date
06 | Hanford | Road reconstruction, install water and storm main, lift pump, sidewalk, curb and gutter | Emma Lee Lane from Grangeville Boulevard to Jana Way | CRRSAASL | 5091(068) | 0623000210 | S | 243020 | 0 | 243020
06 | Bakersfield | Install Traffic Signal Poles, controller, and other traffic signal equipment | Intersection of Beale Avenue and Monterey Street and intersection of Beale Avenue and Niles Street | HSIPSL | 5109(280) | 0623000134 | S | 586000 | 546000 | 40000
06 | Bakersfield | Install flashing yellow beacons near existing crosswalks | At Norris Elementary School and at Stiern Middle School | HSIPSL | 5109(292) | 0624000219 | S | 188370 | 148370 | 40000
06 | Porterville | Replace existing signal, add protected left turn phasing for all intersection legs, curb ramps, signs | Intersection of Olive Avenue and Porter Road/Cloverleaf Street | HSIPL | 5122(092) | 0622000211 | S | 69600 | 0 | 69600
06 | Wasco | Install High-Intensity Activated CrossWalk (HAWK) pedestrian hybrid beacon system, signs, striping and pavement markings | Intersection of Highway 46 and Poplar Avenue | HSIPSL | 5287(064) | 0623000231 | S | 58387.5 | 54427.5 | 3960

## District 7
Projects with Lapsing State Funds
Reversion Date: | 2027-06-30
Appropriation/Item Number: | 2660-102-0042
Year of Appropriation: | 2122
Appropriation Unit: | 22102
Program: | 2030
District | Parties to Agreement (Agency) | Purpose of Project (Work Description) | Scope (Location) | Prefix | Project Id | Advantage Project Id | Advantage Phase | Budgeted Amount | Expenditure Amount | Remaining Balance | Is Project Consistent with Original Scope and Purpose of the Appropriation? If No, Please Explain: | Are You Requesting a CWA (Yes or No)? If No, provide an anticipated date the agency plans to submit invoice for the remaining balance | Reason for Delay | If Other for Reason for Delay, Provide Explanation | Please Provide a 2-3 Sentence Explanation Identifying Any Impediments to Completion | What are the Consequences if CWA is Not Approved? (Please Provide a 2-3 Sentence Explanation) | Local Agency Contact Name | Local Agency Contact Phone Number | Local Agency Contact Email | Approved by DOF (Yes or No)? | Revised Reversion Date
07 | Pasadena | Installation of reflective backplate and near side signal heads | Fair Oaks Avenue, Walnut Street, Lake Avenue, Glenarm Street, California Boulevard, and Washington Boulevard corridors and selected intersections | HSIPSL | 5064(099) | 0724000068 | S | 37800 | 35432.78 | 2367.22
07 | Long Beach | Install new traffic signals | Two (2) Intersections: Atlantic Avenue and Atlantic Place; and Pacific Avenue and Burnett Street | HSIPSL | 5108(209) | 0724000011 | S | 76500 | 33060.42 | 43439.58
07 | Manhattan Beach | Install new pedestrian crosswalk with Americans with Disabilities Act (ADA) ramps | Manhattan Avenue and 36th Street, Valley Drive and Flournoy Road Highland Avenue and 40th Street | HSIPSL | 5212(015) | 0723000284 | S | 36000 | 0 | 36000
07 | Maywood | Improve signal hardware, install pedestrian countdown signal heads and modify signal phasing | 21 traffic signals on the Slauson Avenue corridor (East-West) between Alamo Avenue to Maywood Avenue; and the Atlantic Avenue Corridor (North-South) between East 52nd Street to Randolph Avenue | HSIPSL | 5265(018) | 0723000217 | S | 134100 | 105225.56 | 28874.44
07 | Downey | Upgrade uncontrolled marked pedestrian crosswalks to include Rectangular Rapid Flashing Beacon (RRFB) and Hi Vis signing and lighting | Uncontrolled marked pedestrian crossings at: Our Lady of Perpetual Help School on Downey Avenue; Street Pius X - Street Matthias Academy East crosswalk on Gardendale Street; and Street Pius | HSIPSL | 5334(070) | 0724000015 | S | 40050 | 35406.71 | 4643.29
07 | Pico Rivera | Conduct a Roadway Safety and Signing Audit (RSSA) | All streets and roadways throughout the City of Pico Rivera | HSIPSL | 5351(043) | 0724000052 | S | 360000 | 229465.35 | 130534.65
07 | South El Monte | Install left turn phasing at signalized locations with existing left turn pockets, | Various signalized intersections throughout the City | HSIPSL | 5352(021) | 0722000078 | S | 553299 | 453664.18 | 99634.82
07 | Lancaster | Upgrade existing crosswalks to high-visibility continental-style crosswalks using thermoplastic | 53 signalized intersections within the city limits of Lancaster | HSIPSL | 5419(064) | 0723000184 | S | 250000 | 5256.53 | 244743.47
07 | Lancaster | Enhance visibility of stop signs, pavement markings and advanced warning beacons and stop controlled | 223 unsignalized intersections in the City of Lancaster | HSIPSL | 5419(067) | 0724000016 | S | 202950 | 13577.65 | 189372.35
07 | Calabasas | Improve signal hardware, install intersection striping, install additional indications, upgrade pedestrian | Various signalized intersections throughout Calabasas | HSIPSL | 5463(022) | 0723000214 | S | 20250 | 0 | 20250

## District 8
Projects with Lapsing State Funds
Reversion Date: | 2027-06-30
Appropriation/Item Number: | 2660-102-0042
Year of Appropriation: | 2122
Appropriation Unit: | 22102
Program: | 2030
District | Parties to Agreement (Agency) | Purpose of Project (Work Description) | Scope (Location) | Prefix | Project Id | Advantage Project Id | Advantage Phase | Budgeted Amount | Expenditure Amount | Remaining Balance | Is Project Consistent with Original Scope and Purpose of the Appropriation? If No, Please Explain: | Are You Requesting a CWA (Yes or No)? If No, provide an anticipated date the agency plans to submit invoice for the remaining balance | Reason for Delay | If Other for Reason for Delay, Provide Explanation | Please Provide a 2-3 Sentence Explanation Identifying Any Impediments to Completion | What are the Consequences if CWA is Not Approved? (Please Provide a 2-3 Sentence Explanation) | Local Agency Contact Name | Local Agency Contact Phone Number | Local Agency Contact Email | Approved by DOF (Yes or No)? | Revised Reversion Date
08 | Colton | Bike Path | Intersection of La Cadena Drive/ Fogg Street, Valley Boulevard/ 4th Street, Valley Boulevard/ Pennsylvania Avenue, and Rancho Avenue/ B Street | HSIPSL | 5065(033) | 0824000073 | S | 20250 | 0 | 20250
08 | Banning | Upgrade Signals | 17 signalized intersections throughout the City of Banning | HSIPSL | 5214(016) | 0824000001 | S | 54000 | 40729.5 | 13270.5
08 | Banning | Pedestrian Walkway | 19 intersections throughout the City of Banning | HSIPSL | 5214(017) | 0824000002 | S | 76500 | 0 | 76500
08 | Banning | Pedestrian Walkway | The intersection of Wilson Street with 12th Street | HSIPSL | 5214(018) | 0824000003 | S | 44460 | 0 | 44460
08 | Fontana | Signal Synchronization | 118 Signalized Locations throughout the City of Fontana | HSIPSL | 5307(037) | 0824000056 | S | 19050 | 12852.72 | 6197.28
08 | Victorville | Upgrade Signals | All 96 city-owned traffic signals | HSIPSL | 5380(042) | 0824000072 | S | 100440 | 0 | 100440
08 | Desert Hot Springs | Upgrade Signals | 17 intersections (ten (10) along Palm Drive, Hacienda Avenue and Mountain View Road, 5 intersections along Pierson Bl, and Mission Lakes Boulevard and Indian Canyon Drive). | HSIPSL | 5384(019) | 0817000049 | S | 64170 | 56032.2 | 8137.8
08 | Cathedral City | Install intersection lighting, light-emitting diode (LED) flashing stop signs, curb ramps, and pedestrian safety features | Citywide pedestrian crosswalk upgrades at 18 unsignalized intersections | HSIPSL | 5430(039) | 0824000159 | S | 202500 | 162500 | 40000
08 | Cathedral City | Install pedestrian signal, curb bulb-outs, Americans with Disability Act (ADA) curb ramps, safety lighting, crosswalk, and signs | Intersection of 30th Avenue and Avenida La Paz and Intersection Cathedral Canyon Drive and Ortega Road | HSIPSL | 5430(040) | 0824000160 | S | 94500 | 92041.01 | 2458.99
08 | Cathedral City | Install Pedestrian School Crossing Enhancements | Intersection of 30th Avenue with San Eljay Avenue | HSIPSL | 5430(042) | 0824000162 | S | 42750 | 40435.91 | 2314.09
08 | Moreno Valley | Street Lighting | 15 signalized intersections on high speed roads with overnight collision trends | HSIPSL | 5441(081) | 0823000113 | S | 135000 | 97675.28 | 37324.72
08 | Riverside County | Upgrade existing guardrail/end treatments to meet current Caltrans standards - State/Special Authority (SA) Guardrail | Cajalco Road and Lake Mathews Drive | HSIPSL | 5956(281) | 0821000124 | S | 15000 | 37.46 | 14962.54

## District 10
Projects with Lapsing State Funds
Reversion Date: | 2027-06-30
Appropriation/Item Number: | 2660-102-0042
Year of Appropriation: | 2122
Appropriation Unit: | 22102
Program: | 2030
District | Parties to Agreement (Agency) | Purpose of Project (Work Description) | Scope (Location) | Prefix | Project Id | Advantage Project Id | Advantage Phase | Budgeted Amount | Expenditure Amount | Remaining Balance | Is Project Consistent with Original Scope and Purpose of the Appropriation? If No, Please Explain: | Are You Requesting a CWA (Yes or No)? If No, provide an anticipated date the agency plans to submit invoice for the remaining balance | Reason for Delay | If Other for Reason for Delay, Provide Explanation | Please Provide a 2-3 Sentence Explanation Identifying Any Impediments to Completion | What are the Consequences if CWA is Not Approved? (Please Provide a 2-3 Sentence Explanation) | Local Agency Contact Name | Local Agency Contact Phone Number | Local Agency Contact Email | Approved by DOF (Yes or No)? | Revised Reversion Date
10 | Stockton | Road Related - Install High-visibility crosswalks, pavement markings, sight triangles and rapid-flash | Intersections of Madison Street with Willow Street, Vine Street, Rose Street, Magnolia Street, Acacia Street, Poplar Street, and Flora Street | HSIPSL | 5008(202) | 1022000264 | S | 115200 | 110150.55 | 5049.45
10 | Angels | Public Work Personnel Cost | City of Angels | CRRSAA | 5206(020) | 1022000086 | S | 100000 | 0 | 100000
10 | Patterson | Traffic Related - Other | Intersection at Sperry Avenue and Highway 33 | HSIPL | 5244(042) | 1023000247 | S | 175500 | 0 | 175500
10 | Stanislaus County | Replace existing two (2)-lane bridge with a standard two (2)-lane bridge in lieu of seismic retrofit | River Road over San Joaquin River at Stanislaus/Merced County line; Bridge Number 39C0001 | BRLSZ | 5938(176) | 1000020163 | SE7 | 31657 | 5783.55 | 25873.45
10 | San Joaquin Council of Governments |  | San Joaquin Council of Governments 2021/2022 | FSP22SB1 | 6088(077) | 1022000031 | S | 467644 | 0 | 467644

## District 11
Projects with Lapsing State Funds
Reversion Date: | 2027-06-30
Appropriation/Item Number: | 2660-102-0042
Year of Appropriation: | 2122
Appropriation Unit: | 22102
Program: | 2030
District | Parties to Agreement (Agency) | Purpose of Project (Work Description) | Scope (Location) | Prefix | Project Id | Advantage Project Id | Advantage Phase | Budgeted Amount | Expenditure Amount | Remaining Balance | Is Project Consistent with Original Scope and Purpose of the Appropriation? If No, Please Explain: | Are You Requesting a CWA (Yes or No)? If No, provide an anticipated date the agency plans to submit invoice for the remaining balance | Reason for Delay | If Other for Reason for Delay, Provide Explanation | Please Provide a 2-3 Sentence Explanation Identifying Any Impediments to Completion | What are the Consequences if CWA is Not Approved? (Please Provide a 2-3 Sentence Explanation) | Local Agency Contact Name | Local Agency Contact Phone Number | Local Agency Contact Email | Approved by DOF (Yes or No)? | Revised Reversion Date
11 | Brawley | Road Rehabilitation | C Street, from 1st Street to Imperial Avenue | CRASL | 5167(047) | 1123000170 | S | 93633 | 0 | 93633
11 | Holtville | Miscellaneous - Other | City of Holtville | CRRSAASL | 5174(037) | 1123000307 | S | 15000 | 0 | 15000
11 | Holtville | Railroad Related - Other | City of Holtville at the Holton Interurban Railway bridge | CRRSAASL | 5174(038) | 1123000308 | S | 35000 | 0 | 35000
11 | La Mesa | Install edgeline striping | Various roadways throughout the City of La Mesa | HSIPSL | 5207(051) | 1122000030 | S | 137000 | 35730.06 | 101269.94
11 | Carlsbad | Bike Path | Paseo Del Norte between Palomar Airport Road and Camino Del Parque | HSIPSL | 5308(026) | 1124000022 | S | 97200 | 0 | 97200
11 | San Diego Association of Governments | Freeway Service Patrol | San Diego Association of Governments 2021/2022 | FSP22SB1 | 6066(186) | 1122000020 | S | 2176746 | 1919861.79 | 256884.21

## District 12
Projects with Lapsing State Funds
Reversion Date: | 2027-06-30
Appropriation/Item Number: | 2660-102-0042
Year of Appropriation: | 2122
Appropriation Unit: | 22102
Program: | 2030
District | Parties to Agreement (Agency) | Purpose of Project (Work Description) | Scope (Location) | Prefix | Project Id | Advantage Project Id | Advantage Phase | Budgeted Amount | Expenditure Amount | Remaining Balance | Is Project Consistent with Original Scope and Purpose of the Appropriation? If No, Please Explain: | Are You Requesting a CWA (Yes or No)? If No, provide an anticipated date the agency plans to submit invoice for the remaining balance | Reason for Delay | If Other for Reason for Delay, Provide Explanation | Please Provide a 2-3 Sentence Explanation Identifying Any Impediments to Completion | What are the Consequences if CWA is Not Approved? (Please Provide a 2-3 Sentence Explanation) | Local Agency Contact Name | Local Agency Contact Phone Number | Local Agency Contact Email | Approved by DOF (Yes or No)? | Revised Reversion Date
12 | Anaheim | Upgrade Signals | Three (3) Signalized Intersections in the City of Anaheim: Walnut Street at Ball Road; Anaheim Boulevard at Santa Ana Street; and Acacia Street/Anna Drive at La Palma Avenue | HSIPSL | 5055(200) | 1224000007 | S | 702100 | 0 | 702100
12 | Anaheim | Install edgelines on ten (10) local roadway segments | Ten (10) local roadway segments to implement traffic calming measures through edgeline striping at various locations within City limits | HSIPSL | 5055(201) | 1224000008 | S | 10980 | 0 | 10980
12 | Santa Ana | Upgrade Signals | Bristol Street and Santa Clara Avenue | HSIPSL | 5063(204) | 1221000089 | S | 297100 | 255988.79 | 41111.21
12 | Buena Park | Upgrade Signals | 13 signalized intersections citywide | HSIPSL | 5310(044) | 1223000103 | S | 153000 | 119489.41 | 33510.59

## Drop-down Reference Tables
Within Scope? | Need a CWA? | Primary Reason For Delay:
YES | YES | Design: Change in scope.
NO | NO | Design: Change in specifications.
Design: Change in site conditions.
Environmental: Change in scope requires additional studies/permits.
Environmental: Excessive study or opinion review time by external agencies.
Environmental: Permits expired.
Environmental: Environmental document determination revalidation required.
Environmental: Mitigation for project impacts period.
Right of Way and Utility Relocation: Change in scope/number of parcels/utility relocations required.
Right of Way and Utility Relocation: Condemnation/eminent domain proceedings.
Right of Way and Utility Relocation: Utility owner dispute.
Right of Way and Utility Relocation: Qualified Buy America purchase/delivery delays.
Construction: Contract award disputed/cancelled, rebid or complete under force account.
Construction: Change in site conditions.
Construction: Qualified Buy America purchase/delivery delays.
Construction: Extended winter suspension affecting delivery schedule.
Contract Dispute/Litigation: Post-construction claim. Informal settlement.
Contract Dispute/Litigation: Formal litigation proceeding.
Finance: CTC approved Time Extension conflicts with reversion date.
Finance: Indirect Cost Rate Proposal (ICRP) request package returned with errors.
Finance: Change in dedicated/programmed funding.
Finance: Pending programming.
OTHER-declared disaster (explain):
OTHER (explain):