## All Districts
STIP Projects with Lapsing State Funds
Reversion Date: | 2027-06-30
Appropriation/Item Number: | 2660-101-0042
Year of Appropriation: | 2122
Appropriation Unit: | 22101
Program: | 2030
District | Parties to Agreement (Agency) | Purpose of Project (Work Description) | Scope (Location) | Prefix | Project Id | Advantage Project Id | PPNO | Advantage Phase | Phase | Federal Program Code | Budgeted Amount | Expenditure Amount | Remaining Balance | CTC TUF Deadline | Is Project Consistent with Original Scope and Purpose of the Appropriation? If No, Please Explain: | Are You Requesting a CWA (Yes or No)? If No, provide an anticipated date the agency plans to submit invoice for the remaining balance | Reason for Delay | If Other for Reason for Delay, Provide Explanation | Please Provide a 2-3 Sentence Explanation Identifying Any Impediments to Completion | What are the Consequences if CWA is Not Approved? (Please Provide a 2-3 Sentence Explanation) | Local Agency Contact Name | Local Agency Contact Phone Number | Local Agency Contact Email | Approved by DOF (Yes or No)? | Revised Reversion Date
01 | Ukiah | Construct Roundabout, replacing all way stop signs | In Ukiah, Intersection of Low Gap Road and North Bush Street | RPL | 5049(024) | 0112000224 | 4562 | 1 | PS&E | N/A | 263000 | 267.8 | 262732.2 | 2025-03-30
01 | Ukiah | Streetscape Improvements | In Ukiah, on State Street from Norton Street to Henry Street and from Mill Street to Gobbi Street | RPSTPL | 5049(030) | 0122000107 | 4591 | 4E1 | CON | N/A | 233000 | 226490 | 6510
01 | Ukiah | Streetscape Improvements | In Ukiah, on State Street from Norton Street to Henry Street and from Mill Street to Gobbi Street | RPSTPL | 5049(030) | 0122000107 | 4591 | 4 | CON | N/A | 1369000 | 1335510 | 33490
01 | Clearlake | Road Related - Other | In the City of Clearlake at the intersection of Dam Road Extension about 400 feet from and connected to State Route 53 at Post Mile 1.10 | RPL | 5427(028) | 0119000038 | 3125 | S | RW | N/A | 570000 | 23231.88 | 546768.12 | 2026-06-30
01 | Mendocino County | Install Medians, Landscape and Aesthetic Features | Along North State Street (County Road 104), from Ford Road/Empire Drive to the Northbound on/off-ramps of United States 101 | HIPRPL | 5910(134) | 0120000133 | 4590 | 1 | PS&E | N/A | 1800000 | 1781172.14 | 18827.86 | 2027-02-28
02 | Yreka City | Road Rehabilitation | Oregon Street from 4H Way to Oberlin Road and 4H Way from Route 3 to Campus Drive | RPL | 5020(021) | 0219000033 | 2500 | 3 | CON | N/A | 10800 | 1562.1 | 9237.9 | 2026-03-22
02 | Yreka City | Road Rehabilitation | Oregon Street from 4H Way to Oberlin Road and 4H Way from Route 3 to Campus Drive | RPL | 5020(021) | 0219000033 | 2500 | 4 | CON | N/A | 915200 | 875200 | 40000 | 2026-03-22
02 | Mt Shasta | Road Rehabilitation | In Mount Shasta, on Lake Street between Mount Shasta Boulevard and Rockfellow Drive. Reconstruct roadway | RPL | 5136(010) | 0220000139 | 2594 | 1 | PS&E | N/A | 100000 | 3334.5 | 96665.5 | 2026-03-31
02 | Siskiyou County | Road Rehabilitation | In Siskiyou county near Weed on Jackson Ranch Road for the entire 5 mile length | RPL | 5902(087) | 0220000131 | 2603 | 1 | PS&E | N/A | 75000 | 30591.09 | 44408.91 | 2025-12-31
04 | Richmond | Road Reconstruction | Interstate-80 Central Avenue in Richmond and El Cerrito | RPSTPL | 5137(050) | 0418000420 | 2025H | SE1 | RW | N/A | 517000 | 50747.17 | 466252.83 | 2025-06-30
05 | Santa Cruz County | Road Rehabilitation | Near Los Angeles Selva Beach and Watsonville on San Andreas Road from 365 feet South of Manresa State Beach to Sunset Beach Road (approximately three (3) miles). Resurfacing Roadway | RPL | 5936(155) | 0523000052 | 3088 | 4 | CON | N/A | 1645000 | 0 | 1645000 | 2026-03-22
10 | Mariposa County | Replace Substandard Bridge - Harris Road Bridge | Mariposa County Harris Road Bridge Post Mile 12.75 | CRASL | 5940(150) | 1022000273 | 3552 | 0 | PA&ED | N/A | 75000 | 0 | 75000 | 2028-02-29
10 | Mariposa County | Replace existing bridge | In the Southeast portion of unincorporated Mariposa County, replace an existing single-lane, structurally deficient structure, Indian Peak Road bridge Post Mile 15.35, with a new bridge | CRASL | 5940(152) | 1023000133 | 3553 | 0 | PA&ED | N/A | 25000 | 0 | 25000 | 2025-06-30
11 | San Diego Association of Governments | Construction of 3.2 miles of bikeways, traffic calming, safety and pedestrian improvements | Within the City of San Diego primarily along Washington Street, Third Avenue, Bachman Place, and Hotel Circle | LPPSB1L | 6066(188) | 1122000089 | 1432 | 3E1 | CON | N/A | 2480000 | 1373771.2 | 1106228.8 | 2026-06-28
11 | San Diego Association of Governments | Construction of 3.2 miles of bikeways, traffic calming, safety and pedestrian improvements | Within the City of San Diego primarily along Washington Street, Third Avenue, Bachman Place, and Hotel Circle | LPPSB1L | 6066(188) | 1122000089 | 1432 | 4E1 | CON | N/A | 4520000 | 1304808.16 | 3215191.84 | 2026-06-28

## Drop-down Reference Tables
Within Scope? | Need a CWA? | Primary Reason For Delay:
YES | YES | Design: Change in scope.
NO | NO | Design: Change in specifications.
Design: Change in site conditions.
Environmental: Change in scope requires additional studies/permits.
Environmental: Excessive study or opinion review time by external agencies.
Environmental: Permits expired.
Environmental: Environmental document determination revalidation required.
Environmental: Mitigation for project impacts period.
Right of Way and Utility Relocation: Change in scope/number of parcels/utility relocations required.
Right of Way and Utility Relocation: Condemnation/eminent domain proceedings.
Right of Way and Utility Relocation: Utility owner dispute.
Right of Way and Utility Relocation: Qualified Buy America purchase/delivery delays.
Construction: Contract award disputed/cancelled, rebid or complete under force account.
Construction: Change in site conditions.
Construction: Qualified Buy America purchase/delivery delays.
Construction: Extended winter suspension affecting delivery schedule.
Contract Dispute/Litigation: Post-construction claim. Informal settlement.
Contract Dispute/Litigation: Formal litigation proceeding.
Finance: CTC approved Time Extension conflicts with reversion date.
Finance: Indirect Cost Rate Proposal (ICRP) request package returned with errors.
Finance: Change in dedicated/programmed funding.
Finance: Pending programming.
OTHER-declared disaster (explain):
OTHER (explain):