## All Districts
Fund Source | District | Agency | Work Performed and Location | Federal Project ID | Advantage Project ID | Current Budget | Expenditure Amt | Unliquidated Encumbrance Balance | CTC TUF Deadline | Delay Code | Reason for Delay | Obstacles for Future Completion | Consequences if CWA is not approved | Date funding expended if CWA approved | Contact Name | Comments | Approved by DOF (Yes/No) | Revised Lapsing Date
State | 3 | Paradise | Pedestrian Walkway project to include curb, gutter, sidewalk, ADA, lighting, signing and striping/On Almond Street between Pearson and Elliott Road. | ATPL-5425(031) | 0316000095 | 83000 | 62494.91 | 20505.09 | 2018-06-30 | 8 | The agency was unexpectedly delayed due to COVID 19 impacts. CTC adopted an interim policy that moved deadlines out by a minimum of 6 months. | None | The project phase will not be completed and will lead to project delivery delays. | PAED phase will be fully completed by June 2021. | Desiree Fox |  | Yes | 2022-06-30
State | 3 | Paradise | Sidewalk, curb, gutter and Class II bicycle lanes/Ponderosa Elementary School project along Pentz Road between Billie and 300ft north of Wagstaff Road. | ATPL-5425(033) | 0316000099 | 66000 | 55211.87 | 10788.13 | 2018-06-30 | 8 | The agency was unexpectedly delayed due to COVID 19 impacts. CTC adopted an interim policy that moved deadlines out by a minimum of 6 months. | None | The project phase will not be completed and will lead to project delivery delays. | PAED phase will be fully completed by June 2021. | Desiree Fox |  | Yes | 2022-06-30
State | 4 | Alameda County | Promoting Walking and Biking Safety in the Alameda County Unincorporated Area Schools/Unincorporated Alameda County. | ATPLNI-5933(134) | 0416000281 | 668000 | 645920.15 | 22080 | 2021-02-28 | 8 | The agency was unexpectedly delayed due to COVID 19 impacts. CTC adopted an interim policy that moved deadlines out by a minimum of 6 months. | None | Project completion activities including reporting will not be completed leading to project delivery delays and non-compliance with Accountability and Transparency requirements of SB1. | Project Completion by 6/30/22. | Desiree Fox |  | Yes | 2022-06-30
State | 4 | City& County of San Francisco, MTA/Parking & Traffic | Bicycle Related - Other/Various locations in San Francisco | ATPL-6328(079) | 0416000167 | 792000 | 275663.16 | 516336.84 | 2020-08-31 | 8 | The agency was unexpectedly delayed due to COVID 19 impacts. CTC adopted an interim policy that moved deadlines out by a minimum of 6 months. | None | Project completion activities including reporting will not be completed leading to project delivery delays and non-compliance with Accountability and Transparency requirements of SB1. | Project Completion by 6/30/22. | Desiree Fox |  | Yes | 2022-06-30
State | 5 | Goleta | Bike Path/In the City of Goleta along Hollister Avenue - Class I Bike Path. | ATPL-5481(016) | 0515000073 | 1454734 | 1414734 | 40000 | 2021-03-21 | 8 | The agency was unexpectedly delayed due to COVID 19 impacts. CTC adopted an interim policy that moved deadlines out by a minimum of 6 months. | None | Project completion activities including reporting will not be completed leading to project delivery delays and non-compliance with Accountability and Transparency requirements of SB1. | Project Completion by 6/30/22. | Desiree Fox |  | Yes | 2022-06-30
State | 7 | Compton | Wilminton Ave Safe St Ped/Bike Imp/ Const.of wider Xwalks& high visibility, countdown pedest signals/Wilmington Ave from El Segundo Blvd and Rosecrans Ave Rosecrans Avenue between Wilmington and Compton Creek | ATPL-5078(034) | 0715000288 | 949000 | 210338.07 | 738661.93 | 2020-07-31 | 8 | Based upon Caltrans audit, the reimbursed project costs of $257,333 were not in compliance with the Agreement, state and federal regulations, ATP application, and CTC program guidelines. | None anticipated. | If the CWA is not approved, the City would be unable to complete the project in compliance with the Agreement, state and federal regulations, the ATP application, and CTC program guidelines and would be forced to use its funding which would be a significant hardship to the City. | 2020-07-31 | Michael L.Antwine; mantwine@comptonicity.org; 310-605-5585 |  | Yes | 2022-06-30
State | 7 | Los Angeles County Metropolitan Transportation Authority | Infrastructure CON: Install a network of Share Kiosks with a fleet of bicycles in the project, the area is a dense neighborhood along the Metro Expo Line (5 stations), from the edge of downtown Los Angeles to Exposition Park. | ATPL-6065(221) | 0718000274 | 2287000 | 1143452 | 1143548 | 2021-12-19 | 8 | The Construction phase was programmed in 17/18. The Pre-construction phases took longer than anticipated and delayed the project's start of construction. | None | The project can't be completed. | 2022-06-30 | Teresa McWilliam |  | Yes | 2022-06-30
State | 7 | Los Angeles County Metropolitan Transportation Authority | Non-Infrastructure CON: Provide maps & postcards informing public on bike share & safety etiquette, the area is a dense neighborhood along the Metro Expo Line (5 Stations), from the edge of downtown Los Angeles to Exposition Park. | ATPLNI-6065(222) | 0718000275 | 259000 | 0 | 259000 | 2021-06-26 | 8 | The Construction phase was programmed in 17/18. The Pre-construction phases took longer than anticipated and delayed the project's start of construction. | None | The project can't be completed. | 2022-06-30 | Teresa McWilliam |  | Yes | 2022-06-30
State | 7 | San Gabriel Valley Council of Governments | Expand Metro Bike Share System - Expand the Metro Bike Share system by extending the service from Downtown Los Angeles to the San Gabriel Valley. Includes 840 bikes at 84 bike stations in 15 cities. | ATPL-6303(044) | 0718000331 | 4554000 | 1296035.84 | 3257964.16 | 2021-12-17 | 8 | The Construction phase was programmed in 17/18. The Pre-construction phases took longer than anticipated and delayed the project's start of construction. | None | The project can't be completed. | 2022-06-30 | Teresa McWilliam |  | Yes | 2022-06-30
State | 7 | Santa Monica | non infrastructure: SRTS Pilot program:providecomprehensive educational and encoragement activities/School Include: Edison Language Academy, SMASH, John Muir, McKinley, Grant and Franklin Elementary. | ATPL-5107(041) | 0716000245 | 450000 | 109001.95 | 340998.05 | 2020-11-30 | 8 | Unanticipated challenges collaborating with local schools. | None | There is not sufficient time to expend the remaining grant fund. Agency is currently implementing new promotions at local schools that provide the school administrator, teachers, and students the tools and information to increase and improve safety while traveling to school. | 2020-12-31 | Cory Keen (310) 458-2201 ext. 2120 cory.keen@smgov.net |  | Yes | 2022-06-30
State | 08 | Perris | Class 1 pedestrian and bicycle trail/West side of the Perris Valley Storm Drain Channel Trail from Nuevo Road to the north city limits | ATPL-5198(015) | 0815000079 | 1202000 | 844554.94 | 357445.06 | 2020-10-30 | 8 | Completion of over a half-mile segment of the trail by the developer. The developer is working out an elevation discrepancy with Riv. Co. Flood Control as the trail is in Riv Co. Flood Control jurisdiction. The CTC approved a 12-mo. Extension to complete construction at the Dec. 5, 2019 meeting. The new deadline for project completion is Oct. 31, 2020. | None | The City of Perris will not be able to comply with the State funding requirements for project development, including project completion. Failure of the City of Perris to submit a final report of expenditures within 180 days of project completion will result in State imposing sanctions upon the City of Perris under the current LAPM and the ATP Guidelines. | 2020-10-31 | Grace Alvarez | The City of Perris has already expended its local funds to fund the construction of two miles out of the 4.32 miles of trail (2 miles completed by city and 2.32 miles by development community). The remaining $57,445.06 needs to be reimbursed to the City upon successful completion of the remaining over a half-mile segment of the trail by Developer. The city will be ready to submit the final report of expenditures upon completion of the remaining trail segment by the developer - milestone is October 31, 2020, or sooner. | Yes | 2022-06-30
State | 10 | Stockton | Bike Path/Class I Bike Path between Brookside Rd and Cherokee Rd. | ATPL-5008(143) | 1015000143 | 42553.41 | 40162.92 | 2390.49 | 2021-06-06 | 8 | The agency was unexpectedly delayed due to COVID 19 impacts. CTC adopted an interim policy that moved deadlines out by a minimum of 6 months. | CON funds expire 6/6/2020. | Project completion activities including reporting will not be completed leading to project delivery delays and non-compliance with Accountability and Transparency requirements of SB1. | Project Completion by 6/30/22. | Desiree Fox |  | Yes | 2022-06-30
State | 10 | Stockton | Bike Path/Class I Bike Path between Brookside Rd and Cherokee Rd. | ATPL-5008(143) | 1015000143 | 548446.59 | 520050 | 28396.59 | 2021-06-06 | 8 | The agency was unexpectedly delayed due to COVID 19 impacts. CTC adopted an interim policy that moved deadlines out by a minimum of 6 months. | CON funds expire 6/6/2020. | Project completion activities including reporting will not be completed leading to project delivery delays and non-compliance with Accountability and Transparency requirements of SB1. | Project Completion by 6/30/22. | Desiree Fox |  | Yes | 2022-06-30
[5 empty] | Total | 13355734 | 6617619.81 | 6738114.34