## District 4
State Administered Projects with Lapsing Federal Funds
Reversion Date: | 2021-06-30
Appropriation/Item Number: | 2660-102-0890
Year of Appropriation: | 1516
Appropriation Unit: | 16102F
District | Parties to Agreement (Agency) | Purpose of Project (Work Description) | Scope (Location) | Federal Project Id with Prefix | Advantage Project Id | Federal Program Code | Budgeted Amount | Expenditure Amount | Remaining Balance | CTC TUF Deadline | Is Project Consistent with Original Scope and Purpose of the Appropriation? If No, Please Explain: | Are You Requesting a CWA (Yes or No)? | Reason for Delay | Please Provide a 2-3 Sentence Explanation Identifying Any Impediments to Completion (including if the extension is not approved). | Local Agency Contact Name ¦ Phone¦ Email | Approved by DOF (Yes or No)? | Revised Reversion Date
04 | Caltrans | Design, implement and maintain ramp metering, traffic operating systems. | Major congested freeways. | CML-6204(095) | 0414000446 | Z400 | 197020.2 | 173990.44 | 23029.76

## District 7
State Administered Projects with Lapsing Federal Funds
Reversion Date: | 2021-06-30
Appropriation/Item Number: | 2660-102-0890
Year of Appropriation: | 1516
Appropriation Unit: | 16102F
District | Parties to Agreement (Agency) | Purpose of Project (Work Description) | Scope (Location) | Federal Project Id with Prefix | Advantage Project Id | Federal Program Code | Budgeted Amount | Expenditure Amount | Remaining Balance | CTC TUF Deadline | Is Project Consistent with Original Scope and Purpose of the Appropriation? If No, Please Explain: | Are You Requesting a CWA (Yes or No)? | Reason for Delay | Please Provide a 2-3 Sentence Explanation Identifying Any Impediments to Completion (including if the extension is not approved). | Local Agency Contact Name ¦ Phone¦ Email | Approved by DOF (Yes or No)? | Revised Reversion Date
07 | Caltrans | HOV Lane, one in each direction including reconstruction of I-5/SR-170 mixed flow & HOV connector. | I-5 HOV Lane: From route 170 to route 118. | STPL-6207(054) | 0700001829 | Z230 | 2527000 | 1382983.61 | 1144016.39
07 | Caltrans | Add one lane in each direction, widen ramps, sound walls, and widen three bridges. | LA County Line to Moorpark Rd. in Thousand Oaks. | RSTPL-6207(067) | 0700000201 | M23E | 955000 | 951945.39 | 3054.61
07 | Caltrans | Sound wall, landscape, and sidewalk lighting. | LA002: Allesandro Street to I-5/SR2 interchange. | HP21L-6207(071) | 0714000277 | Q920 | 323000 | 201551.34 | 121448.66

## District 8
State Administered Projects with Lapsing Federal Funds
Reversion Date: | 2021-06-30
Appropriation/Item Number: | 2660-102-0890
Year of Appropriation: | 1516
Appropriation Unit: | 16102F
District | Parties to Agreement (Agency) | Purpose of Project (Work Description) | Scope (Location) | Federal Project Id with Prefix | Advantage Project Id | Federal Program Code | Budgeted Amount | Expenditure Amount | Remaining Balance | CTC TUF Deadline | Is Project Consistent with Original Scope and Purpose of the Appropriation? If No, Please Explain: | Are You Requesting a CWA (Yes or No)? | Reason for Delay | Please Provide a 2-3 Sentence Explanation Identifying Any Impediments to Completion (including if the extension is not approved). | Local Agency Contact Name ¦ Phone¦ Email | Approved by DOF (Yes or No)? | Revised Reversion Date
08 | Caltrans | Reconstruct interchange. | I-215 interchange at Barton Road from the I-215/Iowa Avenue interchange to I-215/Washington Street interchange. | DEMO4LN-6208(023) | 0800000282 | LY10 | 557000 | 33646.23 | 523353.77
08 | Caltrans | Construct toll express lanes in each direction. | I-15 from Cajalco Road in the City of Coronato State Route 60 in the Cities of Eastvale and Jurupa Valley. | STPLN-6208(025) | 0800000283 | M230 | 1104847 | 1101103.4 | 3743.6

## District 11
State Administered Projects with Lapsing Federal Funds
Reversion Date: | 2021-06-30
Appropriation/Item Number: | 2660-102-0890
Year of Appropriation: | 1516
Appropriation Unit: | 16102F
District | Parties to Agreement (Agency) | Purpose of Project (Work Description) | Scope (Location) | Federal Project Id with Prefix | Advantage Project Id | Federal Program Code | Budgeted Amount | Expenditure Amount | Remaining Balance | CTC TUF Deadline | Is Project Consistent with Original Scope and Purpose of the Appropriation? If No, Please Explain: | Are You Requesting a CWA (Yes or No)? | Reason for Delay | Please Provide a 2-3 Sentence Explanation Identifying Any Impediments to Completion (including if the extension is not approved). | Local Agency Contact Name ¦ Phone¦ Email | Approved by DOF (Yes or No)? | Revised Reversion Date
11 | Caltrans | Land Acquisition. | SR 905. | HP21L-6211(043) | 1100000068 | Q930 | 3689674 | 0 | 3689674
11 | Caltrans | New Road. | I-5/SR-56 interchange. | DEM05L-6211(093) | 1100000092 | LY10 | 3198085.74 | 111032.08 | 3087053.66
11 | Caltrans | New Road. | I-5/SR-56 interchange. | DEM05L-6211(093) | 1100000092 | HY10 | 855247.67 | 26162.8 | 829084.87
11 | Caltrans | Roadway Widening. | In Imperial County, SR-98 from VV Williams Avenue to Ollie Avenue widen Hwy from 2 to 4 lanes. | DEM05-6211(113) | 1100020357 | LY10 | 815000 | 814713.91 | 286.09
11 | Caltrans | Roadway Widening. | In Imperial County, SR-98 from VV Williams Avenue to Ollie Avenue widen Hwy from 2 to 4 lanes. | DEM05-6211(113) | 1100020357 | ZS30 | 1400000 | 1377474.61 | 22525.39
11 | Caltrans | Construct noise wall. | I-805 south of Palomar to SR-54. | CMSTPLN-6211(121) | 1112000217 | Z240 | 336000 | 268674.31 | 67325.69
11 | Caltrans | Interstate 5- HOV/ Managed Lanes. | San Diego County in Solana Beach from Lomas Santa Fe UC to SR-78 overcrossing in Oceanside. | CMSTPLN-6211(130) | 1100020362 | Z240 | 600000 | 550439.38 | 49560.62
11 | Caltrans | Interstate 5- HOV/ Managed Lanes. | San Diego County in Solana Beach from Lomas Santa Fe UC to SR-78 overcrossing in Oceanside. | CMSTPLN-6211(130) | 1100020362 | Z400 | 17346438 | 16692407.63 | 654030.37
11 | Caltrans | Interstate 5- HOV/ Managed Lanes. | San Diego County in Solana Beach from Lomas Santa Fe UC to SR-78 overcrossing in Oceanside. | CMSTPLN-6211(130) | 1100020362 | Z400 | 4861766 | 600000 | 4261766
11 | Caltrans | Interstate 5- HOV/ Managed Lanes. | San Diego County in Solana Beach from Lomas Santa Fe UC to SR-78 overcrossing in Oceanside. | CMSTPLN-6211(130) | 1114000059 | Z400 | 485000 | 165500 | 319500
11 | Caltrans | Interstate 5- HOV/ Managed Lanes. | San Diego County in Solana Beach from Lomas Santa Fe UC to SR-78 overcrossing in Oceanside. | CMSTPLN-6211(130) | 1114000060 | Z400 | 985000 | 0 | 985000

## District 12
State Administered Projects with Lapsing Federal Funds
Reversion Date: | 2021-06-30
Appropriation/Item Number: | 2660-102-0890
Year of Appropriation: | 1516
Appropriation Unit: | 16102F
District | Parties to Agreement (Agency) | Purpose of Project (Work Description) | Scope (Location) | Federal Project Id with Prefix | Advantage Project Id | Federal Program Code | Budgeted Amount | Expenditure Amount | Remaining Balance | CTC TUF Deadline | Is Project Consistent with Original Scope and Purpose of the Appropriation? If No, Please Explain: | Are You Requesting a CWA (Yes or No)? | Reason for Delay | Please Provide a 2-3 Sentence Explanation Identifying Any Impediments to Completion (including if the extension is not approved). | Local Agency Contact Name ¦ Phone¦ Email | Approved by DOF (Yes or No)? | Revised Reversion Date
12 | Caltrans | Add mix-flow and toll express lanes in each direction and associated improvements. | Interstate 405 from State Route 73 to Interstate 605. | STPLN-6212(018) | 1200000180 | Z230 | 8353200 | 8346515.49 | 6684.51

## Drop-down Reference Tables
Within Scope? | Need a CWA? | Primary Reason For Delay:
YES | YES | Design: Change in scope.
NO | NO | Design: Change in specifications.
Design: Change in site conditions.
Environmental: Change in scope requires additional studies/permits.
Environmental: Excessive study or opinion review time by external agencies.
Environmental: Permits expired.
Environmental: Environmental document determination revalidation required.
Environmental: Mitigation for project impacts period.
Right of Way and Utility Relocation: Change in scope/number of parcels/utility relocations required.
Right of Way and Utility Relocation: Condemnation/eminent domain proceedings.
Right of Way and Utility Relocation: Utility owner dispute.
Right of Way and Utility Relocation: Qualified Buy America purchase/delivery delays.
Construction: Contract award disputed/cancelled, rebid or complete under force account.
Construction: Change in site conditions.
Construction: Qualified Buy America purchase/delivery delays.
Construction: Extended winter suspension affecting delivery schedule.
Contract Dispute/Litigation: Post-construction claim. Informal settlement.
Contract Dispute/Litigation: Formal litigation proceeding.
Finance: CTC approved Time Extension conflicts with reversion date.
Finance: Indirect Cost Rate Proposal (ICRP) request package returned with errors.
Finance: Change in dedicated/programmed funding.
Finance: Pending programming.
OTHER-declared disaster (explain):
OTHER (explain):