## District 3
ATP Projects with Lapsing State Funds
Reversion Date: | 2021-06-30
Appropriation/Item Number: | 2660-108-0042
Year of Appropriation: | 1516
Appropriation Unit: | 16108
District | Parties to Agreement (Agency) | Purpose of Project (Work Description) | Scope (Location) | Federal Project Id with Prefix | Advantage Project Id | Federal Program Code | Budgeted Amount | Expenditure Amount | Remaining Balance | CTC TUF Deadline | Is Project Consistent with Original Scope and Purpose of the Appropriation? If No, Please Explain: | Are You Requesting a CWA (Yes or No)? | Reason for Delay | Please Provide a 2-3 Sentence Explanation Identifying Any Impediments to Completion (including if the extension is not approved). | Local Agency Contact Name ¦ Phone¦ Email | Approved by DOF (Yes or No)? | Revised Reversion Date
03 | Paradise | Pedestrian Walkway project to include curb, gutter, sidewalk, ADA, lighting, signing, and striping. | Almond Street between Pearson and Elliott Road. | ATPL-5425(031) | 0316000095 |  | 175200 | 144698.54 | 30501.46
03 | Paradise | Sidewalk, curb, gutter, and Class II bicycle lanes. | Ponderosa Elementary School project along Pentz Road between Billie and 300ft north of Wagstaff Road. | ATPL-5425(033) | 0316000099 |  | 155000 | 107830.32 | 47169.68

## District 50
ATP Projects with Lapsing State Funds
Reversion Date: | 2021-06-30
Appropriation/Item Number: | 2660-108-0042
Year of Appropriation: | 1516
Appropriation Unit: | 16108
District | Parties to Agreement (Agency) | Purpose of Project (Work Description) | Scope (Location) | Federal Project Id with Prefix | Advantage Project Id | Federal Program Code | Budgeted Amount | Expenditure Amount | Remaining Balance | CTC TUF Deadline | Is Project Consistent with Original Scope and Purpose of the Appropriation? If No, Please Explain: | Are You Requesting a CWA (Yes or No)? | Reason for Delay | Please Provide a 2-3 Sentence Explanation Identifying Any Impediments to Completion (including if the extension is not approved). | Local Agency Contact Name ¦ Phone¦ Email | Approved by DOF (Yes or No)? | Revised Reversion Date
50 | Caltrans | State Technical Assistance Resource Center. | Caltrans Statewide(Project ID 2014 ATP LIST#0773). | ATPLNI-6200(029) | 0015000079 |  | 1250000 | 1238466.68 | 11533.32
50 | Caltrans | State Transportation Resource Center. | Statewide. | ATPLNI-6200(031) | 0017000034 |  | 2380000 | 1598100.79 | 781899.21

## Drop-down Reference Tables
Within Scope? | Need a CWA? | Primary Reason For Delay:
YES | YES | Design: Change in scope.
NO | NO | Design: Change in specifications.
Design: Change in site conditions.
Environmental: Change in scope requires additional studies/permits.
Environmental: Excessive study or opinion review time by external agencies.
Environmental: Permits expired.
Environmental: Environmental document determination revalidation required.
Environmental: Mitigation for project impacts period.
Right of Way and Utility Relocation: Change in scope/number of parcels/utility relocations required.
Right of Way and Utility Relocation: Condemnation/eminent domain proceedings.
Right of Way and Utility Relocation: Utility owner dispute.
Right of Way and Utility Relocation: Qualified Buy America purchase/delivery delays.
Construction: Contract award disputed/cancelled, rebid or complete under force account.
Construction: Change in site conditions.
Construction: Qualified Buy America purchase/delivery delays.
Construction: Extended winter suspension affecting delivery schedule.
Contract Dispute/Litigation: Post-construction claim. Informal settlement.
Contract Dispute/Litigation: Formal litigation proceeding.
Finance: CTC approved Time Extension conflicts with reversion date.
Finance: Indirect Cost Rate Proposal (ICRP) request package returned with errors.
Finance: Change in dedicated/programmed funding.
Finance: Pending programming.
OTHER-declared disaster (explain):
OTHER (explain):