## 18101F
STIP Projects with Lapsing Federal Funds
Reversion Date: | 2023-06-30
Appropriation/Item Number: | 2660-101-0890
Year of Appropriation: | 1718
Appropriation Unit: | 18101F
District | Parties to Agreement (Agency) | Purpose of Project (Work Description) | Scope (Location) | Federal Project Id with Prefix | Advantage Project Id | Budgeted Amount | Expenditure Amount | Remaining Balance | CTC TUF Deadline | Is Project Consistent with Original Scope and Purpose of the Appropriation? If No, Please Explain: | Are You Requesting a CWA (Yes or No)? If No, provide an anticipated date the agency plans to submit invoice for the remaining balance | Reason for Delay | Please Provide a 2-3 Sentence Explanation Identifying Any Impediments to Completion | What are the Consequences if CWA is Not Approved? (Please Provide a 2-3 Sentence Explanation) | Local Agency Contact Name ¦ Phone¦ Email | Approved by DOF (Yes or No)? | Revised Reversion Date
02 | Plumas County | Road rehabilitation/reconstruction, including drainage improvements, erosion control, and guardrail | Within the community of Johnsville and on Graeagle-Johnsville Road, Polar Valley Road, the Plumas Eureka State Park, and the Plumas National Forest | RPSTPL-5909(116) | 0219000074 | 250000 | 220940.05 | 29059.95 | 2021-06-30 | YES | YES | OTHER-declared disaster (explain): The Dixie Fire from July 2021 thru October 2021 and the subsequent Disaster Recovery efforts in cooperation with FEMA/CalOES diverted staff time. Subsequently, the County missed the invoice deadline 180 days after the TUF. | No impediments are expected for completion. | Plumas County (a small, rural, disadvantaged Agency) will have to pull funding from other areas to cover these costs, resulting in additional hardship for the County if CWA is not approved. | John Mannle 530.283.6498 johnmannle@countyofplumas.com | Yes | 2025-06-30
02 | Tehama County | Pavement rehabilitation | Old Highway 99W (formerly Highway 99) from Tehama-Glenn County line and extends North to Corning City limits at South Avenue | RPSTPL-5908(102) | 0219000024 | 200000 | 42930.18 | 157069.82 | 2021-06-30 | YES | YES | OTHER (explain): Direct charges have been invoiced. The County is currently working to obtain an Indirect Cost Rate for FY 21 and 22 to complete invoicing for the phase. | Tehama County is contracted with a consultant to prepare Indirect Cost Rate Proposals and the FY 21 proposal has been submitted. The FY 22 proposal is being prepared. Final invoicing is pending approval of the proposals by Caltrans. | If CWA is not approved, loss of funds will delay improvements to Local Route 99W, which is a well-traveled thoroughfare between the Glenn County line and Corning city limits. 99W is in need of rehabilitation due to numerous hazards, such as rutting and delamination. This project will improve vehicle/public safety. | Jessica Pecha 530.385.1462 ext. 3026 jpecha@tcpw.ca.gov | Yes | 2025-06-30
03 | Folsom | Widen from 2-lane to 4-lane and add Class II bicycle path | Green Valley Road from the East Natoma Street (Sacramento County) to the Sophia Parkway (El Dorado County) | LPPSB1L-5288(040) | 0314000274 | 2900000 | 0 | 2900000 | 2021-11-27 | YES | YES | OTHER (explain): The original Contractor went out of business at the start of the contract. The City of Folsom executed the Performance Bond and the Bond company provided a replacement Contractor. | Construction is complete and the City has submitted several iterations of the Final Report of Expenditures. Caltrans District 3 Local Assistance has been working with the City to balance the Performance Bond issues with Exhibit 3A-Cost Adjustment and Final Invoice. Resubmittal of the Final Report of Expenditures is anticipated in January 2023. | If the CWA is not approved, the City will lose the $2.9 million that it has expended for a regional project should the Final Report of Expenditures not be approved by the Reversion Date. | Brian Reed 916.461.6707 breed@folsom.ca.us | Yes | 2025-06-30
[5 empty] | Total | 3350000 | 263870.23 | 3086129.77

## Drop-down Reference Tables
Within Scope? | Need a CWA? | Primary Reason For Delay:
YES | YES | Design: Change in scope.
NO | NO | Design: Change in specifications.
Design: Change in site conditions.
Environmental: Change in scope requires additional studies/permits.
Environmental: Excessive study or opinion review time by external agencies.
Environmental: Permits expired.
Environmental: Environmental document determination revalidation required.
Environmental: Mitigation for project impacts period.
Right of Way and Utility Relocation: Change in scope/number of parcels/utility relocations required.
Right of Way and Utility Relocation: Condemnation/eminent domain proceedings.
Right of Way and Utility Relocation: Utility owner dispute.
Right of Way and Utility Relocation: Qualified Buy America purchase/delivery delays.
Construction: Contract award disputed/cancelled, rebid or complete under force account.
Construction: Change in site conditions.
Construction: Qualified Buy America purchase/delivery delays.
Construction: Extended winter suspension affecting delivery schedule.
Contract Dispute/Litigation: Post-construction claim. Informal settlement.
Contract Dispute/Litigation: Formal litigation proceeding.
Finance: CTC approved Time Extension conflicts with reversion date.
Finance: Indirect Cost Rate Proposal (ICRP) request package returned with errors.
Finance: Change in dedicated/programmed funding.
Finance: Pending programming.
OTHER-declared disaster (explain):
OTHER (explain):