## Rail-20102F
Rail Projects with Lapsing Federal Funds
Reversion Date: | 2023-06-30
Rail Projects with Lapsing Federal Funds
Reversion Date: | 2026-06-30
Appropriation/Item Number: | 2660-102-0890
Year of Appropriation: | 2021
Appropriation Unit: | 21102F
District | Parties to Agreement (Agency) | Purpose of Project (Work Description) | Scope (Location) | Prefix | Federal Project Id | Advantage Project Id | Federal Program Code | Budgeted Amount | Expenditure Amount | Remaining Balance | Is Project Consistent with Original Scope and Purpose of the Appropriation? If No, Please Explain: | Are You Requesting a CWA (Yes or No)? If No, provide an anticipated date the agency plans to submit invoice for the remaining balance | Reason for Delay | Please Provide a 2-3 Sentence Explanation Identifying Any Impediments to Completion | What are the Consequences if CWA is Not Approved? (Please Provide a 2-3 Sentence Explanation) | Local Agency Contact Name | Local Agency Contact Phone Number | Local Agency Contact Email | Approved by DOF (Yes or No)? | Revised Reversion Date
03 | 1. Sutter County, 2. Union Pacific Railroad (UPRR) | Safety improvements for the elimination of hazards at a railway-highway grade crossing | In the County of Sutter, the Keys Road and Union Pacific Railroad (UPRR) Crossing | STPLR | 7500(279) | 0320000201 | LS5E | 366000 | 0 | 366000
05 | 1. City of San Luis Obispo, 2. Union Pacific Railroad (UPRR) | Safety improvements for the elimination of hazards at a railway-highway grade crossing | In the City of San Luis Obispo, the Foothill Boulevard and Union Pacific Railroad (UPRR) | STPLR | 7500(291) | 0521000061 | ZS40 | 1572000 | 0 | 1572000
05 | 1. City of San Luis Obispo, 2. Union Pacific Railroad (UPRR) | Safety improvements for the elimination of hazards at a railway-highway grade crossing | In the City of San Luis Obispo, the Foothill Boulevard and Union Pacific Railroad (UPRR) | STPLR | 7500(291) | 0521000061 | ZS50 | 2000000 | 208526.86 | 1791473.14
06 | 1. City of Fowler, 2. Union Pacific Railroad (UPRR) | Safety improvements for the elimination of hazards at a railway-highway grade crossing | In the City of Fowler, the Manning Avenue and Union Pacific Railroad (UPRR) | STPLR | 7500(283) | 0621000019 | MS40 | 207492.34 | 0 | 207492.34
06 | 1. City of Fowler, 2. Union Pacific Railroad (UPRR) | Safety improvements for the elimination of hazards at a railway-highway grade crossing | In the City of Fowler, the Manning Avenue and Union Pacific Railroad (UPRR) | STPLR | 7500(283) | 0621000019 | ZS40 | 2354507.66 | 41713.09 | 2312794.57
07 | 1. City of Lancaster, 2. Union Pacific Railroad (UPRR), 3. Metrolink | Safety improvements for the elimination of hazards at a railway-highway grade crossing | In the City of Lancaster, the Avenue K and Union Pacific Railroad (UPRR) | STPLR | 7500(276) | 0720000253 | LS4R | 3963.07 | 0 | 3963.07
07 | 1. City of Lancaster, 2. Union Pacific Railroad (UPRR), 3. Metrolink | Safety improvements for the elimination of hazards at a railway-highway grade crossing | In the City of Lancaster, the Avenue K and Union Pacific Railroad (UPRR) | STPLR | 7500(276) | 0720000253 | ZS40 | 1546036.93 | 0 | 1546036.93
07 | 1. City of Lancaster, 2. Union Pacific Railroad (UPRR) 3. Metrolink | Safety improvements for the elimination of hazards at a railway-highway grade crossing | In the City of Lancaster, the Avenue M and Union Pacific Railroad (UPRR) | STPLR | 7500(277) | 0720000254 | LS5E | 16831.63 | 0 | 16831.63
07 | 1. City of Lancaster, 2. Union Pacific Railroad (UPRR) 3. Metrolink | Safety improvements for the elimination of hazards at a railway-highway grade crossing | In the City of Lancaster, the Avenue M and Union Pacific Railroad (UPRR) | STPLR | 7500(277) | 0720000254 | ZS40 | 1410568.37 | 0 | 1410568.37
07 | 1. City of Pomona/San Gabriel Valley Council of Governments (SGVCOG), 2. Union Pacific Railroad (UPRR) | Safety improvements for the elimination of hazards at a railway-highway grade crossing | In the City of Pomona/SGVCOG, the San Antonio Avenue and Union Pacific Railroad (UPRR) | STPLR | 7500(286) | 0721000024 | MS50 | 71864.98 | 0 | 71864.98
07 | 1. City of Pomona/San Gabriel Valley Council of Governments (SGVCOG), 2. Union Pacific Railroad (UPRR) | Safety improvements for the elimination of hazards at a railway-highway grade crossing | In the City of Pomona/SGVCOG, the San Antonio Avenue and Union Pacific Railroad (UPRR) | STPLR | 7500(286) | 0721000024 | ZS40 | 1536135.02 | 0 | 1536135.02
07 | 1. City of Palmdale, 2. Union Pacific Railroad (UPRR), 3. Metrolink | Safety improvements for the elimination of hazards at a railway-highway grade crossing | In the City of Palmdale, the Avenue P and Union Pacific Railroad (UPRR) | STPLR | 7500(285) | 0721000025 | MS40 | 1020500 | 0 | 1020500
07 | 1. City of Lancaster, 2. Union Pacific Railroad (UPRR) 3. Metrolink | Safety improvements for the elimination of hazards at a railway-highway grade crossing | In the City of Lancaster, the Avenue J and Union Pacific Railroad (UPRR) | STPLR | 7500(287) | 0721000027 | ZS40 | 1179375 | 0 | 1179375
08 | 1. City of Banning, 2. Union Pacific Railroad (UPRR) | Safety improvements for the elimination of hazards at a railway-highway grade crossing | In the City of Banning, the San Gorgonio Avenue and Union Pacific Railroad (UPRR) | STPLR | 7500(288) | 0821000010 | LS5E | 257261.33 | 0 | 257261.33
08 | 1. City of Banning, 2. Union Pacific Railroad (UPRR) | Safety improvements for the elimination of hazards at a railway-highway grade crossing | In the City of Banning, the San Gorgonio Avenue and Union Pacific Railroad (UPRR) | STPLR | 7500(288) | 0821000010 | MS5E | 345038.67 | 0 | 345038.67
10 | 1. City of Stockton, 2. Union Pacific Railroad (UPRR) | Safety improvements for the elimination of hazards at a railway-highway grade crossing | In the City of Stockton, the West Lane and Union Pacific Railroad (UPRR) | STPLR | 7500(289) | 1021000019 | ZS40 | 3198900 | 205314.36 | 2993585.64
50 | 1. City of Oakland, 2. Union Pacific Railroad (UPRR) | Safety improvements for the elimination of hazards at a railway-highway grade crossing | In the City of Oakland, the 29th Avenue and Union Pacific Railroad (UPRR) | STPLR | 7500(226) | 0015150311 | LS4E | 109994.12 | 27388.11 | 82606.01
50 | 1. County of Tulare, 2. San Joaquin Valley Railroad (SJVR) | Safety improvements for the elimination of hazards at a railway-highway grade crossing | In the County of Tulare, the Avenue 336 and SJVR Crossing | STPLR | 7500(268) | 0019000290 | ZS40 | 40000 | 32481.79 | 7518.21

## Drop-down Reference Tables
Within Scope? | Need a CWA? | Primary Reason For Delay:
YES | YES | Design: Change in scope.
NO | NO | Design: Change in specifications.
Design: Change in site conditions.
Environmental: Change in scope requires additional studies/permits.
Environmental: Excessive study or opinion review time by external agencies.
Environmental: Permits expired.
Environmental: Environmental document determination revalidation required.
Environmental: Mitigation for project impacts period.
Right of Way and Utility Relocation: Change in scope/number of parcels/utility relocations required.
Right of Way and Utility Relocation: Condemnation/eminent domain proceedings.
Right of Way and Utility Relocation: Utility owner dispute.
Right of Way and Utility Relocation: Qualified Buy America purchase/delivery delays.
Construction: Contract award disputed/cancelled, rebid or complete under force account.
Construction: Change in site conditions.
Construction: Qualified Buy America purchase/delivery delays.
Construction: Extended winter suspension affecting delivery schedule.
Contract Dispute/Litigation: Post-construction claim. Informal settlement.
Contract Dispute/Litigation: Formal litigation proceeding.
Finance: CTC approved Time Extension conflicts with reversion date.
Finance: Indirect Cost Rate Proposal (ICRP) request package returned with errors.
Finance: Change in dedicated/programmed funding.
Finance: Pending programming.
OTHER-declared disaster (explain):
OTHER (explain):