## District 2
STIP Projects with Lapsing Federal Funds
Reversion Date: | 2022-06-30
Appropriation/Item Number: | 2660-101-0890
Year of Appropriation: | 1617
Appropriation Unit: | 17101F
District | Parties to Agreement (Agency) | Purpose of Project (Work Description) | Scope (Location) | Federal Project Id with Prefix | Advantage Project Id | Federal Program Code | Budgeted Amount | Expenditure Amount | Remaining Balance | CTC TUF Deadline | Is Project Consistent with Original Scope and Purpose of the Appropriation? If No, Please Explain: | Are You Requesting a CWA (Yes or No)? | Reason for Delay | Please Provide a 2-3 Sentence Explanation Identifying Any Impediments to Completion | What are the Consequences if CWA is Not Approved? (Please Provide a 2-3 Sentence Explanation) | Local Agency Contact Name ¦ Phone¦ Email | Approved by DOF (Yes or No)? | Revised Reversion Date
02 | Susanville | Road rehabilitation | In Susanville at various locations. Project FC. Rehabilitate roadway, construct drainage improvements and pedestrian facilities | RPSTPL-5116(016) | 0214000125 | M240 | 146932.07 | 81000 | 65932.07 | 2021-04-18

## Drop-down Reference Tables
Within Scope? | Need a CWA? | Primary Reason For Delay:
YES | YES | Design: Change in scope.
NO | NO | Design: Change in specifications.
Design: Change in site conditions.
Environmental: Change in scope requires additional studies/permits.
Environmental: Excessive study or opinion review time by external agencies.
Environmental: Permits expired.
Environmental: Environmental document determination revalidation required.
Environmental: Mitigation for project impacts period.
Right of Way and Utility Relocation: Change in scope/number of parcels/utility relocations required.
Right of Way and Utility Relocation: Condemnation/eminent domain proceedings.
Right of Way and Utility Relocation: Utility owner dispute.
Right of Way and Utility Relocation: Qualified Buy America purchase/delivery delays.
Construction: Contract award disputed/cancelled, rebid or complete under force account.
Construction: Change in site conditions.
Construction: Qualified Buy America purchase/delivery delays.
Construction: Extended winter suspension affecting delivery schedule.
Contract Dispute/Litigation: Post-construction claim. Informal settlement.
Contract Dispute/Litigation: Formal litigation proceeding.
Finance: CTC approved Time Extension conflicts with reversion date.
Finance: Indirect Cost Rate Proposal (ICRP) request package returned with errors.
Finance: Change in dedicated/programmed funding.
Finance: Pending programming.
OTHER-declared disaster (explain):
OTHER (explain):