## DAF Log 01-06-2026
HQ DAF Review Log
Date Updated: |  | 2026-01-06 | *Grey filled cells are cuto filled/calculated
DAF Information | [6 empty] | Auto Filled | (HQ) Review |  |  |  | Auto Filled | FHWA Review |  |  |  | (HQ) Post-Review | Other
Caltrans District | DAF No. | Disaster No. | Project Name | Local Agency | Total Project Cost | Date Rec'd from District | Under HQ Review | Ineligible - Rejected | Returned -w- Comments | Forwarded to FHWA | Date Rejected or Sent to FHWA | Under FHWA Review | Ineligible - Rejected | Returned -w- Comments | FHWA Approved | FHWA Signature Date (eligible Y/N box marked) | FHWA Signed Copy e-filed in Disaster Event "DAF" folder? | Proj. Dropped-Withdrawn by Local Agency | Review Status
4 | LTP-ALACO-006-0 | CA23-1 | Redwood Road (MM 7.00 to 8.15) | Alameda Co. | 7347707 | 2023-07-18 |  |  |  | x | 2025-08-13 |  |  | x |  |  |  |  | Returned to local agency
6 | THD-KERCO-001-0 | CA23-3 | Garlock Rd | Kern Co. | 5533 | 2023-08-31 |  |  | x | [9 empty] | Returned to local agency
4 | LTP-ALACO-007-0 | CA23-1 | Foothill Rd | Alameda Co. | 2399265 | 2023-10-16 |  |  | x | [9 empty] | Returned to local agency
8 | EMK-INDW-001-0 | CA23-4 | Fred Waring Dr. | Indian Wells | 283791 | 2023-11-09 |  |  | x | [9 empty] | Returned to local agency
4 | LTP-SF-001-0 | CA23-3 | 3rd Street Bridge | San Francisco | 7116185 | 2023-12-07 |  |  |  | x | 2023-12-07 |  |  | x |  |  |  |  | Returned to local agency
8 | EMK-RMIR-005-0 | CA23-4 | Country Club Drive Storm Drain | Rancho Mirage | 68880 | 2024-02-22 |  |  | x | [9 empty] | Returned to local agency
8 | EMK-YUCP-002-0 | CA23-4 | Bryant Street | Yucaipa | 1104985 | 2024-07-18 |  |  |  | x | 2025-07-31 |  |  | x |  |  |  |  | Returned to local agency
5 | LTP-MONCO-013-0 | CA23-1 | Metz Road | Monterey Co. | 11922 | 2025-03-19 |  |  |  | x | 2025-03-19 | x | [6 empty] | Under FHWA Review
8 | EMK-SBDCO-010-0 | CA23-4 | Oak Glen | San Bernardino Co. | 181930 | 2025-04-08 |  |  | x | [9 empty] | Returned to local agency
8 | EMK-SBDCO-008-1 | CA23-4 | Seven Oaks Rd | San Bernardino Co. | 10806526 | 2025-05-12 |  |  | x | [9 empty] | Returned to local agency
5 | LTP-MONCO-009-0 | CA24-3 | Carmel Valley Road at Garland Park | Monterey Co. | 19486 | 2025-07-01 |  |  |  | x | 2025-07-02 | x | [6 empty] | Under FHWA Review
7 | EMK-LACO-002-0 | CA25-2 | Allen Ave | Los Angeles Co. | 544000 | 2025-07-08 |  |  |  | x | 2025-09-05 | x | [6 empty] | Under FHWA Review
7 | EMK-LACO-003-0 | CA25-2 | Altadena Drive | Los Angeles Co. | 7030000 | 2025-07-08 |  |  |  | x | 2025-09-16 | x | [6 empty] | Under FHWA Review
7 | EMK-LACO-006-0 | CA25-2 | Lincoln Ave | Los Angeles Co. | 2375000 | 2025-07-08 |  |  |  | x | 2025-09-05 | x | [6 empty] | Under FHWA Review
7 | EMK-LACO-011-0 | CA25-2 | Woodbury Road | Los Angeles Co. | 2566000 | 2025-07-08 |  |  |  | x | 2025-09-05 | x | [6 empty] | Under FHWA Review
7 | EMK-LACO-012-0 | CA25-2 | Parkway and Roadway Repairs | Los Angeles Co. | 1470000 | 2025-07-08 |  |  |  | x | 2025-09-05 | x | [6 empty] | Under FHWA Review
7 | EMK-LACO-014-0 | CA25-2 | Valaveras Street | Los Angeles Co. | 969000 | 2025-07-08 |  |  |  | x | 2025-09-16 | x | [6 empty] | Under FHWA Review
5 | DVH-SBCO-001-2 | CA18-3 | North Jameson Lane (1E27) | Santa Barbara Co. | 582228 | 2025-09-17 |  |  |  | x | 2025-09-26 | x | [6 empty] | Under FHWA Review
4 | LTP-CCCO-002-1 | CA23-3 | San Pablo Dam Rd | Contra Costa Co. | 7250000 | 2025-10-14 |  |  |  | x | 2025-12-01 | x | [6 empty] | Under FHWA Review
4 | LTP-ANT-001-0 | CA23-1 | Delta Fair Blvd | Contra Costa Co. | 349403 | 2025-12-09 |  |  | x | [9 empty] | Returned to local agency
2 | PMP-RBL-001-0 | CA23-1 | Walnut Street @ Brickyard Creek Bridge | Tehama | 60817 | 2025-12-04 |  |  | x | [9 empty] | Returned to local agency
5 | DVH-SCRCO-068-1 | CA17-2 | Glenwood Drive PM 2.02 | Santa Cruz Co. | 175700 | 2025-12-03 |  |  |  | x | 2025-12-19 | [7 empty] | Under FHWA Review
5 | LTP-SLO-009-0 | CA23-1 | Pismo Street | San Luis Obispo | 976675 | 2025-11-12 |  |  |  | x | 2025-12-11 | [7 empty] | Under FHWA Review
5 | LTP-SCRCO-011-1 | CA23-1 | Eureka Canyon Road | Santa Cruz Co. | 428096.2 | 2025-12-13 |  |  |  | x | 2025-12-19 | [7 empty] | Under FHWA Review
6 | PMP-TULCO-003-1 | CA23-3 | Mountain Road 109 Bridge over Deer Creek | Tulare County | 1345410 | 2025-12-16 |  |  |  | x | 2025-12-19 | [7 empty] | Under FHWA Review
6 | PMP-TULCO-024-1 | CA23-3 | Road 96/Pratt St. over Tule River | Tulare County | 604990 | 2025-12-16 |  |  |  | x | 2025-12-19 | [7 empty] | Under FHWA Review
5 | LTP-SCRCO-101-1 | CA23-3 | Laurel Glen Road | Santa Cruz Co. | 5140568 | 2025-12-16 |  |  |  | x | 2025-12-19 | [7 empty] | Under FHWA Review
5 | LTP-SLO-010-1 | CA23-1 | 3288 Bullock Lane | San Luis Obispo | 36412 | 2025-12-17 |  |  |  | x | 2025-12-19 | [7 empty] | Under FHWA Review
4 | LTP-MRGA-001-1 | CA23-3 | Canyon Rd | Town of Moraga | 965537 | 2025-12-31 |  |  | x | [9 empty] | Returned to local agency
4 | ATB-SONCO-001 | CA25-5 | Westside Rd | Sonoma County | 3406401 | 2026-01-05 |  |  | x