## DAF log 06-09-2026
HQ DAF Review Log
Date Updated: |  | 2026-06-09 | *Grey filled cells are cuto filled/calculated
DAF Information | [6 empty] | Auto Filled | (HQ) Review |  |  |  | Auto Filled | FHWA Review |  |  |  | (HQ) Post-Review | Other
Caltrans District | DAF No. | Disaster No. | Project Name | Local Agency | Total Project Cost | Date Rec'd from District | Under HQ Review | Ineligible - Rejected | Returned -w- Comments | Forwarded to FHWA | Date Rejected or Sent to FHWA | Under FHWA Review | Ineligible - Rejected | Returned -w- Comments | FHWA Approved | FHWA Signature Date (eligible Y/N box marked) | FHWA Signed Copy e-filed in Disaster Event "DAF" folder? | Proj. Dropped-Withdrawn by Local Agency | Review Status
4 | LTP-ALACO-006-0 | CA23-1 | Redwood Road (MM 7.00 to 8.15) | Alameda Co. | 7347707 | 2023-07-18 |  |  |  | x | 2025-08-13 |  |  | x |  |  |  |  | Returned to local agency
6 | THD-KERCO-001-0 | CA23-3 | Garlock Rd | Kern Co. | 5533 | 2023-08-31 |  |  | x | [9 empty] | Returned to local agency
4 | LTP-ALACO-007-0 | CA23-1 | Foothill Rd | Alameda Co. | 2399265 | 2023-10-16 | [7 empty] | x |  |  |  |  | Returned to local agency
8 | EMK-INDW-001-0 | CA23-4 | Fred Waring Dr. | Indian Wells | 283791 | 2023-11-09 |  |  | x | [9 empty] | Returned to local agency
4 | LTP-SF-001-0 | CA23-3 | 3rd Street Bridge | San Francisco | 7116185 | 2023-12-07 |  |  |  | x | 2023-12-07 |  |  | x |  |  |  |  | Returned to local agency
5 | LTP-MONCO-013-0 | CA23-1 | Metz Road | Monterey Co. | 11922 | 2025-03-19 |  |  |  | x | 2025-03-19 | x | [6 empty] | Under FHWA Review
5 | LTP-MONCO-009-0 | CA24-3 | Carmel Valley Road at Garland Park | Monterey Co. | 19486 | 2025-07-01 |  |  |  | x | 2025-07-02 | x | [6 empty] | Under FHWA Review
7 | EMK-LACO-002-0 | CA25-2 | Allen Ave | Los Angeles Co. | 544000 | 2025-07-08 |  |  |  | x | 2025-09-05 | x | [6 empty] | Under FHWA Review
7 | EMK-LACO-003-0 | CA25-2 | Altadena Drive | Los Angeles Co. | 7030000 | 2025-07-08 |  |  |  | x | 2025-09-16 | x | [6 empty] | Under FHWA Review
7 | EMK-LACO-006-0 | CA25-2 | Lincoln Ave | Los Angeles Co. | 2375000 | 2025-07-08 |  |  |  | x | 2025-09-05 | x | [6 empty] | Under FHWA Review
7 | EMK-LACO-011-0 | CA25-2 | Woodbury Road | Los Angeles Co. | 2566000 | 2025-07-08 |  |  |  | x | 2025-09-05 | x | [6 empty] | Under FHWA Review
7 | EMK-LACO-012-0 | CA25-2 | Parkway and Roadway Repairs | Los Angeles Co. | 1470000 | 2025-07-08 |  |  |  | x | 2025-09-05 | x | [6 empty] | Under FHWA Review
7 | EMK-LACO-014-0 | CA25-2 | Valaveras Street | Los Angeles Co. | 969000 | 2025-07-08 |  |  |  | x | 2025-09-16 | x | [6 empty] | Under FHWA Review
5 | DVH-SBCO-001-2 | CA18-3 | North Jameson Lane (1E27) | Santa Barbara Co. | 582228 | 2025-09-17 |  |  |  | x | 2025-09-26 | x | [6 empty] | Under FHWA Review
5 | DVH-SCRCO-068-1 | CA17-2 | Glenwood Drive PM 2.02 | Santa Cruz Co. | 175700 | 2025-12-03 |  |  |  | x | 2025-12-19 | x | [6 empty] | Under FHWA Review
7 | EMK-LACO-001-0 | CA25-4 | Malibu Canon Road | Los Angeles | 970000 | 2026-01-23 |  |  |  | x | 2026-01-29 | x | [6 empty] | Under FHWA Review
4 | LTP-CCCO-003-1 | CA23-1 | Highland Rd | Contra Costa Co. | 1443000 | 2026-02-05 |  |  | x | [9 empty] | Returned to local agency
5 | LTP-SCRCO-091-1 | CA23-3 | Eureka Canyon Road | Santa Cruz Co. | 683864 | 2025-12-31 |  |  |  | x | 2026-02-10 | x | [6 empty] | Under FHWA Review
2 | PMP-TRICO-001-0 | CA25-6 | Hyampom Rd | Trinity Co. | 2090955 | 2026-02-12 |  |  |  | x | 2026-05-14 | x | [6 empty] | Under FHWA Review
10 | PMP-ALPCO-001-0 | CA23-1 | Hot Springs Road | Alpine Co. | 221199 | 2023-07-24 |  |  |  | x | 2026-04-01 | x | [6 empty] | Under FHWA Review
6 | PMP-TULCO-040-1 | CA23-3 | Road 256 (County Location #355) | Tulare County | 14917 | 2026-02-05 |  |  |  | x | 2026-04-01 | x | [6 empty] | Under FHWA Review
5 | DVH-SCRCO-078-2 | CA17-2 | Redwood Lodge Rd PM 1.80 | Santa Cruz Co. | 415976 | 2026-04-27 |  |  |  |  | 2026-04-28 | x | [6 empty] | Under FHWA Review
5 | LTP-SCRCO-088-1 | CA23-3 | Granite Creek Rd | Santa Cruz Co. | 419113 | 2026-04-28 |  |  |  |  | 2026-04-28 | x | [6 empty] | Under FHWA Review
2 | PMP-TRICO-002-0 | CA25-6 | Hyampom Rd | Trinity Co. | 1875000 | 2026-02-12 |  |  |  | x | 2026-05-14 | x | [6 empty] | Under FHWA Review
2 | PMP-TRICO-002-2 | CA17-2 | Trinity Dam Blvd | Trinity Co. | 398437 | 2026-03-10 |  |  | x |  | 2026-05-14 | [7 empty] | Returned to local agency
2 | PMP-SHACO-002-3 | CA17-2 | Big Bend Road | Shasta Co. | 6808306 | 2026-03-05 |  |  |  | x | 2026-06-05 | [7 empty] | Under FHWA Review
2 | PMP-TRICO-001-1 | CA25-3 | Van Duzen Road | Trinity Co. | 1518339 | 2026-03-20 |  |  |  | x | 2026-06-05 | [7 empty] | Under FHWA Review
2 | PMP-TEHCO-006-2 | CA23-1 | 99W@Truckee Creek | Tehama Co. | 186774 | 2026-04-09 |  |  |  | x | 2026-06-05 | x | [6 empty] | Under FHWA Review
1 | PMP-HUMCO-015-1 | CA23-3 | Mattole Road | Humboldt Co. | 3538526 | 2026-05-04 |  |  |  | x | 2026-06-05 | x | [6 empty] | Under FHWA Review
5 | DVH-SCRCO-029-2 | CA17-2 | Hazel Dell Road | Santa Cruz Co. | 840907 | 2026-05-14 |  |  |  | x | 2026-05-30 | x | [6 empty] | Under FHWA Review
5 | LTP-SCRCO-102-1 | CA24-2 | Day Valley Road | Santa Cruz Co. | 227400 | 2026-05-19 |  |  |  | x | 2026-05-30 | x | [6 empty] | Under FHWA Review
5 | LTP-SCRCO-105-1 | CA24-2 | East Zayante Road | Santa Cruz Co. | 550145 | 2026-05-19 |  |  |  | x | 2026-05-30 | x | [6 empty] | Under FHWA Review
5 | LTP-SCRCO-103-1 | CA24-3 | North Rodeo Gulch Road | Santa Cruz Co. | 636550 | 2026-05-19 |  |  |  | x | 2026-05-30 | x | [6 empty] | Under FHWA Review
5 | LTP-SCRCO-110-1 | CA24-4 | Bear Creek Road | Santa Cruz Co. | 747995 | 2026-05-19 |  |  |  | x | 2026-05-30 | x | [6 empty] | Under FHWA Review
5 | LTP-SCRCO-110-1 | CA24-4 | North Rodeo Gulch Road | Santa Cruz Co. | 175520 | 2026-05-19 |  |  |  | x | 2026-05-30 | x | [6 empty] | Under FHWA Review
5 | PMP-SCRCO-003-1 | CA22-3 | Soquel San Jose Road | Santa Cruz Co. | 761650 | 2026-05-20 |  |  |  | x | 2026-05-30 | x | [6 empty] | Under FHWA Review
5 | LTP-SCRCO-113-1 | CA24-4 | Mountain View Road | Santa Cruz Co. | 332700 | 2025-05-26 |  |  |  | x | 2026-05-30 | x | [6 empty] | Under FHWA Review
5 | LTP-SBCO-028-1 | CA23-1 | Palmer Road MP 4.01 | Santa Barbara Co. | 229453 | 2025-05-26 |  |  |  | x | 2026-05-30 | x | [6 empty] | Under FHWA Review
5 | DVH-SCRCO-016-2 | CA17-2 | Eureka Canyon Road PM 3.16 | Santa Cruz Co. | 838234 | 2026-05-29 |  |  |  | x | 2026-05-30 | x | [6 empty] | Under FHWA Review
5 | LTP-SCRCO-091-1 | CA23-3 | Eureka Canyon Road | Santa Cruz Co. | 683864 | 2026-05-29 |  |  |  | x | 2026-05-30 | x | [6 empty] | Under FHWA Review
1 | PMP-HUMCO-002-1 | CA23-2 | Blue Slide Road | Humboldt Co. | 1188536 | 2026-06-04 |  |  |  | x | 2026-06-05 | x | [6 empty] | Under FHWA Review