## DAF Log 10-07-2026
HQ DAF Review Log
Date Updated: |  | 2026-10-07 | *Grey filled cells are cuto filled/calculated
DAF Information | [6 empty] | Auto Filled | (HQ) Review |  |  |  | Auto Filled | FHWA Review |  |  |  | (HQ) Post-Review | Other
Caltrans District | DAF No. | Disaster No. | Project Name | Local Agency | Total Project Cost | Date Rec'd from District | Under HQ Review | Ineligible - Rejected | Returned -w- Comments | Forwarded to FHWA | Date Rejected or Sent to FHWA | Under FHWA Review | Ineligible - Rejected | Returned -w- Comments | FHWA Approved | FHWA Signature Date (eligible Y/N box marked) | FHWA Signed Copy e-filed in Disaster Event "DAF" folder? | Proj. Dropped-Withdrawn by Local Agency | Review Status
4 | LTP-ALACO-006-0 | CA23-1 | Redwood Road (MM 7.00 to 8.15) | Alameda Co. | 7347707 | 2023-07-18 |  |  |  | x | 2025-08-13 |  |  | x |  |  |  |  | Returned to local agency
6 | THD-KERCO-001-0 | CA23-3 | Garlock Rd | Kern Co. | 5533 | 2023-08-31 |  |  | x | [9 empty] | Returned to local agency
4 | LTP-ALACO-007-0 | CA23-1 | Foothill Rd | Alameda Co. | 2399265 | 2023-10-16 |  |  |  | x |  |  |  | x |  |  |  |  | Returned to local agency
4 | LTP-SF-001-0 | CA23-3 | 3rd Street Bridge | San Francisco | 7116185 | 2023-12-07 |  |  |  | x | 2023-12-07 |  |  | x |  |  |  |  | Returned to local agency
5 | LTP-MONCO-009-0 | CA24-3 | Carmel Valley Road at Garland Park | Monterey Co. | 19486 | 2025-07-01 |  |  |  | x | 2025-07-02 | x | [6 empty] | Under FHWA Review
7 | EMK-LACO-002-0 | CA25-2 | Allen Ave | Los Angeles Co. | 544000 | 2025-07-08 |  |  |  | x | 2025-09-05 | x | [6 empty] | Under FHWA Review
7 | EMK-LACO-003-0 | CA25-2 | Altadena Drive | Los Angeles Co. | 7030000 | 2025-07-08 |  |  |  | x | 2025-09-16 | x | [6 empty] | Under FHWA Review
7 | EMK-LACO-006-0 | CA25-2 | Lincoln Ave | Los Angeles Co. | 2375000 | 2025-07-08 |  |  |  | x | 2025-09-05 | x | [6 empty] | Under FHWA Review
7 | EMK-LACO-011-0 | CA25-2 | Woodbury Road | Los Angeles Co. | 2566000 | 2025-07-08 |  |  |  | x | 2025-09-05 | x | [6 empty] | Under FHWA Review
7 | EMK-LACO-012-0 | CA25-2 | Parkway and Roadway Repairs | Los Angeles Co. | 1470000 | 2025-07-08 |  |  |  | x | 2025-09-05 | x | [6 empty] | Under FHWA Review
7 | EMK-LACO-014-0 | CA25-2 | Valaveras Street | Los Angeles Co. | 969000 | 2025-07-08 |  |  |  | x | 2025-09-16 | x | [6 empty] | Under FHWA Review
5 | DVH-SCRCO-068-1 | CA17-2 | Glenwood Drive PM 2.02 | Santa Cruz Co. | 175700 | 2025-12-03 |  |  |  | x | 2025-12-19 | x | [6 empty] | Under FHWA Review
7 | EMK-LACO-001-0 | CA25-4 | Malibu Canon Road | Los Angeles | 970000 | 2026-01-23 |  |  |  | x | 2026-01-29 |  |  | x |  |  |  |  | Returned to local agency
4 | LTP-CCCO-003-1 | CA23-1 | Highland Rd | Contra Costa Co. | 1443000 | 2026-02-05 |  |  | x | [9 empty] | Returned to local agency
10 | PMP-ALPCO-001-0 | CA23-1 | Hot Springs Road | Alpine Co. | 221199 | 2023-07-24 |  |  |  | x | 2026-04-01 | x | [6 empty] | Under FHWA Review
6 | PMP-TULCO-040-1 | CA23-3 | Road 256 (County Location #355) | Tulare County | 14917 | 2026-02-05 |  |  |  | x | 2026-04-01 | x | [6 empty] | Under FHWA Review
2 | PMP-TRICO-002-2 | CA17-2 | Trinity Dam Blvd | Trinity Co. | 398437 | 2026-03-10 |  |  |  | x | 2026-06-11 | x | [6 empty] | Under FHWA Review
5 | LTP-SBCO-028-1 | CA23-1 | Palmer Road MP 4.01 | Santa Barbara Co. | 229453 | 2025-05-26 |  |  |  | x | 2026-05-30 | x | [6 empty] | Under FHWA Review
2 | PMP-TRICO-003-0 | CA25-5 | Ruth Zenia Road | Trinity Co. | 1330950 | 2026-01-31 |  |  |  | x | 2026-02-02 | x | [6 empty] | Under FHWA Review
7 | CHF-LACO-002 | CA26-1 | Sand Canyon Road | Los Angeles | 2395000 | 2026-08-05 |  |  |  | x | 2026-08-06 |  |  | x |  |  |  |  | Returned to local agency
7 | CHF-LACO-003 | CA26-1 | Sand Canyon Road | Los Angeles | 2740000 | 2026-08-05 |  |  |  | x | 2026-08-06 |  |  | x |  |  |  |  | Returned to local agency
7 | CHF-LACO-005 | CA26-1 | Mount Emme Road | Los Angeles | 1250000 | 2026-06-25 |  |  | x |  | 2026-07-01 | [7 empty] | Returned to local agency
7 | CHF-LACO-006 | CA26-1 | Largo Vista Road | Los Angeles | 600000 | 2026-08-05 |  |  |  | x | 2026-08-06 |  |  | x |  |  |  |  | Returned to local agency
7 | CHF-LACO-010 | CA26-1 | Mt. Baldy Road | Los Angeles | 535000 | 2026-08-05 |  |  |  | x | 2026-08-06 |  |  | x |  |  |  |  | Returned to local agency
7 | CHF-LACO-011 | CA26-1 | Little Tujunga | Los Angeles | 732000 | 2026-08-05 |  |  |  | x | 2026-08-06 |  |  | x |  |  |  |  | Returned to local agency
6 | PMP-TULCO-025-1 | CA23-3 | M296-MP4 Yokohl Mt Rd (County Location 186) | Tulare County | 444276 | 2026-07-27 |  |  |  | x | 2026-10-06 | x | [6 empty] | Under FHWA Review
2 | PMP-TRICO-004-0 | CA24-4 | Ruth-Zenia Road | Trinity Co. | 1463236 | 2026-08-14 |  |  | x | [9 empty] | Returned to local agency
2 | PMP-TRICO-005-0 | CA24-4 | Ruth-Zenia Road | Trinity Co. | 1476819 | 2026-08-14 |  |  | x | [9 empty] | Returned to local agency
2 | PMP-TRICO-006-0 | CA24-4 | Ruth-Zenia Road | Trinity Co. | 1089514 | 2026-08-14 |  |  | x | [9 empty] | Returned to local agency
2 | PMP-TRICO-007-0 | CA24-4 | Ruth-Zenia Road | Trinity Co. | 985486 | 2026-08-14 |  |  | x | [9 empty] | Returned to local agency
2 | PMP-TRICO-009-0 | CA24-4 | Ruth-Zenia Road | Trinity Co. | 498333 | 2026-08-14 |  |  | x | [9 empty] | Returned to local agency
2 | PMP-TRICO-010-0 | CA24-4 | Ruth-Zenia Road | Trinity Co. | 713264 | 2026-08-14 |  |  | x | [9 empty] | Returned to local agency
2 | PMP-TRICO-012-0 | CA24-4 | Ruth-Zenia Road | Trinity Co. | 850764 | 2026-08-14 |  |  | x | [9 empty] | Returned to local agency
2 | PMP-TRICO-008-0 | CA24-4 | Ruth-Zenia Road | Trinity Co. | 791597 | 2026-08-27 |  |  | x | [9 empty] | Returned to local agency
5 | LTP-SBCO-010-0 | CA24-3 | Jalama Road | Santa Barbara Co. | 1890020 | 2026-08-04 |  |  |  | x | 2026-09-29 | x | [6 empty] | Under FHWA Review
5 | LTP-SCRCO-118-0 | CA23-1 | Smith Grade Road PM 0.52 | Santa Cruz Co. | 91249 | 2026-08-10 |  |  |  | x | 2026-09-29 | x | [6 empty] | Under FHWA Review
5 | LTP-SLOCO-019-1 | CA23-3 | Price Canyon Road | San Luis Obispo | 552925 | 2026-08-19 |  |  |  | x | 2026-09-29 | x | [6 empty] | Under FHWA Review
5 | ATB-SCRCO-001-0 | CA26-2 | Alba Road | Santa Cruz Co. | 508425 | 2026-09-18 |  |  |  | x | 2026-09-29 | x | [6 empty] | Under FHWA Review