# 2020/21-2025/26 Highway Bridge Program

## See the appropriate FTIP/FSTIP for current funding commitments. This listing includes projects that should be individually listed in the FTIP/FSTIP. (Line item projects only)

10/24/2022, 2:28 PM

## Notes:

1. The purpose of this list is to show which projects being advanced by local agencies have met the eligibility requirements of the federal Highway Bridge Program and have been prioritized for funding by the Department in cooperation with local agencies for funding.
2. Please see the Local Assistance web site for the most current listings: <http://www.dot.ca.gov/hq/LocalPrograms/hbrr99/HBP_FSTIP.html>
3. Contractual funding levels are determined at time of federal authorization/obligation for given phase of work. For details see Chapter 3 of the Local Assistance Procedures Manual.
4. For FTIP/FSTIP purposes, Federal Highway Bridge Program (HBP) funding constraint is managed by Caltrans.
5. Prop 1B bond funds (Local Seismic Safety Retrofit Program (LSSRP)) used for matching federal funds are also managed by Caltrans.
6. Financial constraint of LOCAL matching funds (including regional STIP funds) and LOCAL Advance Construction (AC) is the responsibility of the MPOs and their local agencies.
7. Some projects show that they are programmed using State STP funds. These funds are HBP funds transferred to the STP for bridge work that is not ordinarily eligible for HBP funds. See the HB Program Guidelines for details. Do not confuse these STP funds with Regional STP funds.
8. Corrections to this report should be addressed to the District Local Assistance Engineer: <http://www.dot.ca.gov/hq/LocalPrograms/dlae.htm>

## Note id: 12

Butte County BRIDGE NO. 12C0111, CENTRAL HOUSE RD, OVER WYMAN RAVINE, 0.2 MI E OF SH70. Replace the existing 1 lane structurally deficient bridge with a new 2 lane bridge. 11/2/2010: Toll Credits programmed for PE, R/W, & CON.

Fed Proj: BRLO-5912(092)

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Phase Summary:** | Prior | 20/21 | 21/22 | 22/23 | 23/24 | 24/25 | 25/26 | Beyond | Total |
| PE | 650,000 |  |  |  |  |  |  |  | 650,000 |
| R/W | 65,000 |  |  |  |  |  |  |  | 65,000 |
| CON |  |  |  |  |  |  |  | 3,325,000 | 3,325,000 |
| Total | 715,000 |  |  |  |  |  |  | 3,325,000 | 4,040,000 |
| **Fund Source Summary:** | Prior | 20/21 | 21/22 | 22/23 | 23/24 | 24/25 | 25/26 | Beyond | Total |
| Fed $ | 715,000 |  |  |  |  |  |  | 3,325,000 | 4,040,000 |
| Local Match |  |  |  |  |  |  |  |  |  |
| LSSRP Bond |  |  |  |  |  |  |  |  |  |
| Local AC |  |  |  |  |  |  |  |  |  |
| Total | 715,000 |  |  |  |  |  |  | 3,325,000 | 4,040,000 |
| **PE Summary:** | Prior | 20/21 | 21/22 | 22/23 | 23/24 | 24/25 | 25/26 | Beyond | Total |
| Fed $ | 650,000 |  |  |  |  |  |  |  | 650,000 |
| Local Match |  |  |  |  |  |  |  |  |  |
| LSSRP Bond |  |  |  |  |  |  |  |  |  |
| Local AC |  |  |  |  |  |  |  |  |  |
| Total | 650,000 |  |  |  |  |  |  |  | 650,000 |

Phase Funding Details:

Proj id

Funds Src

Phase

Prior

20/21

21/22

22/23

23/24

24/25

25/26

Beyond

Total

#### 3745 HBP

Local Match

#### PE 310,000

310,000

Fed. Reimb. Rate: 100.00% 6/15/2016 Michael McCollum: Revise programmed amount per Exhibit 6-D

Total: 310,000

#### 3745 HBP

Local Match

#### PE 340,000

340,000

Fed. Reimb. Rate: 100.00% 11/2/2010 Michael McCollum: Reimbursement changed to 100% (Toll Credits).

11/2/2010 Michael McCollum: New Project - Program funds for PE.

Total: 340,000

|  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | **R/W Summary:** | Prior | 20/21 | 21/22 | 22/23 | 23/24 | 24/25 | 25/26 | Beyond | Total |
| Fed $ | 65,000 |  |  |  |  |  |  |  | 65,000 |
| Local Match |  |  |  |  |  |  |  |  |  |
| LSSRP Bond |  |  |  |  |  |  |  |  |  |
| Local AC |  |  |  |  |  |  |  |  |  |
| Total | 65,000 |  |  |  |  |  |  |  | 65,000 |

Phase Funding Details:

Proj id

Funds Src

Phase

Prior

20/21

21/22

22/23

23/24

24/25

25/26

Beyond

Total

#### 3745 HBP

Local Match

#### R/W 65,000

-65,000

Fed. Reimb. Rate: 100.00% 9/16/2019 Vlad Popko: Not ready to ad within 6 months. RW funds moved from FFY 21/22 to 19/20. As requested in September 2019 Survey.

Total:

#### 3745 HBP

Local Match

#### R/W -65,000

65,000

Fed. Reimb. Rate: 100.00% 10/16/2018 DLA-Admin: Not ready to ad within 6 months. RW funds moved from FFY 19/20 to 21/22. NEPA not yet clear.

#### 3745 HBP R/W

Local Match

Fed. Reimb. Rate: 100.00% 10/10/2017 DLA-Admin: Not ready to ad within 6 months. RW funds moved from FFY 18/19 to 19/20. NEPA not yet clear. 7/27/2021 DLA-Admin: Fundline zeroed out due to FTIP cycle migration: 2018/19-23/24 to 2020/21-25/26. This does not impact funds in the current FTIP cycle.

Total:

Total:

#### 3745 HBP R/W

Local Match

Fed. Reimb. Rate: 100.00% 8/30/2017 Darlene Wulff: Not ready to ad within 6 months. RW funds moved from FFY 19/20 to 18/19. As requested in September 2017 Survey. 7/27/2021 DLA-Admin: Fundline zeroed out due to FTIP cycle migration: 2018/19-23/24 to 2020/21-25/26. This does not impact funds in the current FTIP cycle.

Total:

#### 3745 HBP R/W

Local Match

Fed. Reimb. Rate: 100.00% 10/9/2016 DLA-Admin: Not ready to ad within 6 months. RW funds moved from FFY 17/18 to 19/20. NEPA not yet clear. 7/27/2021 DLA-Admin: Fundline zeroed out due to FTIP cycle migration: 2018/19-23/24 to 2020/21-25/26. This does not impact funds in the current FTIP cycle.

Total:

#### 3745 HBP R/W

Local Match

Fed. Reimb. Rate: 100.00% 10/23/2014 DLA-Admin: Not ready to ad within 6 months. RW funds moved from FFY 15/16 to 17/18. NEPA not yet clear. 8/25/2019 DLA-Admin: Fundline zeroed out due to FTIP cycle migration: 2016/17-21/22 to 2018/19-23/24. This does not impact funds in the current FTIP cycle.

Total:

#### 3745 HBP R/W

Local Match

Fed. Reimb. Rate: 100.00% 3/25/2014 DLA-Admin: Not ready to ad within 6 months. RW funds moved from FFY 14/15 to 15/16. NEPA not yet clear. 8/17/2017 DLA-Admin: Fundline zeroed out due to FTIP cycle migration: 2014/15-19/20 to 2016/17-21/22. This does not impact funds in the current FTIP cycle.

Total:

#### 3745 HBP R/W

Local Match

Fed. Reimb. Rate: 100.00% 10/8/2013 Michael McCollum: Reimbursement changed to 100% (Toll Credits).

10/8/2013 Michael McCollum: Move R/W funds to the 14/15 fiscal year per the fall survey. 8/17/2017 DLA-Admin: Fundline zeroed out due to FTIP cycle migration: 2014/15-19/20 to 2016/17-21/22. This does not impact funds in the current FTIP cycle.

Total:

#### 3745 HBP

Local Match

#### R/W 65,000

65,000

Fed. Reimb. Rate: 100.00% 11/2/2010 Michael McCollum: Reimbursement changed to 100% (Toll Credits).

11/2/2010 Michael McCollum: New Project - Program funds for R/W.

Total: 65,000

|  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | **CON Summary:** | Prior | 20/21 | 21/22 | 22/23 | 23/24 | 24/25 | 25/26 | Beyond | Total |
| Fed $ |  |  |  |  |  |  |  | 3,325,000 | 3,325,000 |
| Local Match |  |  |  |  |  |  |  |  |  |
| LSSRP Bond |  |  |  |  |  |  |  |  |  |
| Local AC |  |  |  |  |  |  |  |  |  |
| Total |  |  |  |  |  |  |  | 3,325,000 | 3,325,000 |

Phase Funding Details:

Proj id

Funds Src

Phase

Prior

20/21

21/22

22/23

23/24

24/25

25/26

Beyond

Total

#### 3745 HBP CON -3,325,000

Local Match

Fed. Reimb. Rate: 100.00% 11/2/2020 DLA-Admin: Not ready to ad within 6 months. CON funds moved from FFY 23/24 to Beyond. Action taken to financially constrain the FTIP (PUSH). Attempt will be made to program this project in year shown.

3,325,000

Total:

#### 3745 HBP

Local Match

CON

-3,325,000

3,325,000

Fed. Reimb. Rate: 100.00% 11/2/2020 DLA-Admin: Not ready to ad within 6 months. CON funds moved from FFY 22/23 to 23/24. Action taken to financially constrain the FTIP (PUSH). Attempt will be made to program this project in year shown.

Total:

#### 3745 HBP

Local Match

CON

-3,325,000 3,325,000

Fed. Reimb. Rate: 100.00% 11/2/2020 DLA-Admin: Not ready to ad within 6 months. CON funds moved from FFY 21/22 to 22/23. Action taken to financially constrain the FTIP (PUSH). Attempt will be made to program this project in year shown.

Total:

#### 3745 HBP

Local Match

CON

3,325,000

-3,325,000

Fed. Reimb. Rate: 100.00% 10/24/2020 DLA-Admin: Not ready to ad within 6 months. CON funds moved from FFY Beyond to 21/22. As requested in September 2020 Survey.

Total:

## Responsible Agency

3745 Local AC (HBP)

Local Match

#### CON

-3,325,000

Prior 20/21 21/22 22/23 23/24 24/25 25/26 Beyond Total

3,325,000

Fed. Reimb. Rate: 100.00% 10/24/2020 DLA-Admin: AC removed from project as requested in 2020 HBP Survey.

Total:

3745 Local AC (HBP)

Local Match

CON

3,325,000

-3,325,000

Fed. Reimb. Rate: 100.00% 10/9/2019 Linda Newton: Add AC to CON in FFY 21/22. Not ready to ad within 6 months.

Total:

#### 3745 HBP

Local Match

CON

1,625,000

1,625,000

Fed. Reimb. Rate: 100.00% 6/15/2016 Michael McCollum: Revise programming per Exhibit 6-D.

Total: 1,625,000

#### 3745 HBP

Local Match

CON

1,700,000

1,700,000

Fed. Reimb. Rate: 100.00% 11/2/2010 Michael McCollum: Reimbursement changed to 100% (Toll Credits). 11/2/2010 Michael McCollum: New Project - Program funds for Construction.

Total: 1,700,000

Chico BRIDGE NO. 12C0066, GUYNN RD, OVER LINDO CHANNEL, JUST N OF W LINDO AVE. Replace the existing 1 lane structurally deficient bridge with a new 2 lane bridge. 11/2/2010: Toll Credits programmed for PE, R/W, & CON.

Fed Proj: BRLO-5037(023)

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Phase Summary:** | Prior | 20/21 | 21/22 | 22/23 | 23/24 | 24/25 | 25/26 | Beyond | Total |
| PE | 978,000 |  |  |  |  |  |  |  | 978,000 |
| R/W |  |  |  |  | 150,000 |  |  |  | 150,000 |
| CON |  |  |  |  |  |  |  | 4,226,000 | 4,226,000 |
| Total | 978,000 |  |  |  | 150,000 |  |  | 4,226,000 | 5,354,000 |
| **Fund Source Summary:** | Prior | 20/21 | 21/22 | 22/23 | 23/24 | 24/25 | 25/26 | Beyond | Total |
| Fed $ | 978,000 |  |  |  | 150,000 |  |  | 4,226,000 | 5,354,000 |
| Local Match |  |  |  |  |  |  |  |  |  |
| LSSRP Bond |  |  |  |  |  |  |  |  |  |
| Local AC |  |  |  |  |  |  |  |  |  |
| Total | 978,000 |  |  |  | 150,000 |  |  | 4,226,000 | 5,354,000 |
| **PE Summary:** | Prior | 20/21 | 21/22 | 22/23 | 23/24 | 24/25 | 25/26 | Beyond | Total |
| Fed $ | 978,000 |  |  |  |  |  |  |  | 978,000 |
| Local Match |  |  |  |  |  |  |  |  |  |
| LSSRP Bond |  |  |  |  |  |  |  |  |  |
| Local AC |  |  |  |  |  |  |  |  |  |
| Total | 978,000 |  |  |  |  |  |  |  | 978,000 |

Phase Funding Details:

Proj id

Funds Src

Phase

Prior

20/21

21/22

22/23

23/24

24/25

25/26

Beyond

Total

#### 3743 HBP

Local Match

#### PE 501,000

501,000

Fed. Reimb. Rate: 100.00% 9/22/2016 Michael McCollum: Revise PE funds per fall survey and Ex. 6-D submitted by agency.

Total: 501,000

#### 3743 HBP

Local Match

#### PE 477,000

477,000

Fed. Reimb. Rate: 100.00% 11/2/2010 Michael McCollum: Reimbursement changed to 100% (Toll Credits).

11/1/2010 Michael McCollum: New Project - Program funds for PE.

Total: 477,000

|  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | **R/W Summary:** | Prior | 20/21 | 21/22 | 22/23 | 23/24 | 24/25 | 25/26 | Beyond | Total |
| Fed $ |  |  |  |  | 150,000 |  |  |  | 150,000 |
| Local Match |  |  |  |  |  |  |  |  |  |
| LSSRP Bond |  |  |  |  |  |  |  |  |  |
| Local AC |  |  |  |  |  |  |  |  |  |
| Total |  |  |  |  | 150,000 |  |  |  | 150,000 |

Phase Funding Details:

Proj id

Funds Src

Phase

Prior

20/21

21/22

22/23

23/24

24/25

25/26

Beyond

Total

#### 3743 HBP

Local Match

R/W

-150,000

150,000

### New!

Fed. Reimb. Rate: 100.00%

10/5/2022 DLA-Admin: Not ready to ad within 6 months. RW funds moved from FFY 22/23 to 23/24. NEPA not yet clear.

Total:

#### 3743 HBP

Local Match

R/W

150,000

-150,000

### New!

Fed. Reimb. Rate: 100.00%

8/29/2022 Robert Brown: Not ready to ad within 6 months. RW funds moved from FFY 23/24 to 22/23. As requested in August 2022 Status.

vvv

Total:

#### 3743 HBP

Local Match

R/W

-150,000

150,000

Fed. Reimb. Rate: 100.00% 10/11/2021 DLA-Admin: Not ready to ad within 6 months. RW funds moved from FFY 21/22 to 23/24. NEPA not clear.

Total:

#### 3743 HBP

Local Match

R/W

-150,000 150,000

Fed. Reimb. Rate: 100.00% 10/22/2019 DLA-Admin: Not ready to ad within 6 months. RW funds moved from FFY 20/21 to 21/22. NEPA not yet clear.

Total:

#### 3743 HBP

Local Match

R/W

150,000 -150,000

Fed. Reimb. Rate: 100.00% 9/10/2019 Vlad Popko: Not ready to ad within 6 months. RW funds moved from FFY 21/22 to 20/21. As requested in September 2019 Survey.

Total:

#### 3743 HBP

Local Match

#### R/W -150,000

150,000

Fed. Reimb. Rate: 100.00% 10/16/2018 DLA-Admin: Not ready to ad within 6 months. RW funds moved from FFY 19/20 to 21/22. NEPA not yet clear.

#### 3743 HBP R/W

Local Match

Fed. Reimb. Rate: 100.00% 10/10/2017 DLA-Admin: Not ready to ad within 6 months. RW funds moved from FFY 18/19 to 19/20. NEPA not yet clear. 7/27/2021 DLA-Admin: Fundline zeroed out due to FTIP cycle migration: 2018/19-23/24 to 2020/21-25/26. This does not impact funds in the current FTIP cycle.

Total:

Total:

#### 3743 HBP R/W

Local Match

Fed. Reimb. Rate: 100.00% 9/6/2017 Darlene Wulff: Not ready to ad within 6 months. RW funds moved from FFY 19/20 to 18/19. As requested in September 2017 Survey. 7/27/2021 DLA-Admin: Fundline zeroed out due to FTIP cycle migration: 2018/19-23/24 to 2020/21-25/26. This does not impact funds in the current FTIP cycle.

Total:

#### 3743 HBP R/W

Local Match

Fed. Reimb. Rate: 100.00% 10/9/2016 DLA-Admin: Not ready to ad within 6 months. RW funds moved from FFY 17/18 to 19/20. NEPA not yet clear. 7/27/2021 DLA-Admin: Fundline zeroed out due to FTIP cycle migration: 2018/19-23/24 to 2020/21-25/26. This does not impact funds in the current FTIP cycle.

Total:

#### 3743 HBP

Local Match

#### R/W 50,000

50,000

Fed. Reimb. Rate: 100.00% 9/30/2016 Michael McCollum: Adjust funds per the fall survey and Ex. 6-D.

#### 3743 HBP R/W

Local Match

Fed. Reimb. Rate: 100.00% 10/19/2015 DLA-Admin: Not ready to ad within 6 months. RW funds moved from FFY 15/16 to 17/18. NEPA not yet clear. 8/25/2019 DLA-Admin: Fundline zeroed out due to FTIP cycle migration: 2016/17-21/22 to 2018/19-23/24. This does not impact funds in the current FTIP cycle.

Total: 50,000

Total:

#### 3743 HBP R/W

Local Match

Fed. Reimb. Rate: 100.00% 9/18/2015 Michael McCollum: Move R/W funds to the current year per the fall survey. 8/25/2019 DLA-Admin: Fundline zeroed out due to FTIP cycle migration: 2016/17-21/22 to 2018/19-23/24. This does not impact funds in the current FTIP cycle.

Total:

#### 3743 HBP R/W

Local Match

Fed. Reimb. Rate: 100.00% 3/18/2015 DLA-Admin: Not ready to ad within 6 months. RW funds moved from FFY 15/16 to 17/18. NEPA not yet clear. 8/25/2019 DLA-Admin: Fundline zeroed out due to FTIP cycle migration: 2016/17-21/22 to 2018/19-23/24. This does not impact funds in the current FTIP cycle.

Total:

#### 3743 HBP R/W

Local Match

Fed. Reimb. Rate: 100.00% 3/25/2014 DLA-Admin: Not ready to ad within 6 months. RW funds moved from FFY 13/14 to 15/16. NEPA not yet clear. 8/17/2017 DLA-Admin: Fundline zeroed out due to FTIP cycle migration: 2014/15-19/20 to 2016/17-21/22. This does not impact funds in the current FTIP cycle.

Total:

#### 3743 HBP R/W

Local Match

Fed. Reimb. Rate: 100.00% 10/8/2013 Michael McCollum: Reimbursement changed to 100% (Toll Credits).

10/8/2013 Michael McCollum: Move R/W to this fiscal year per fall survey. 8/21/2015 DLA-Admin: Fundline zeroed out due to FTIP cycle migration: 2012/13-17/18 to 2014/15-19/20. This does not impact funds in the current FTIP cycle.

Total:

## Responsible Agency

#### 3743 HBP

Local Match

#### R/W

100,000

Prior 20/21 21/22 22/23 23/24 24/25 25/26 Beyond Total

100,000

Fed. Reimb. Rate: 100.00% 11/2/2010 Michael McCollum: Reimbursement changed to 100% (Toll Credits).

11/1/2010 Michael McCollum: New Project - Program funds for R/W.

Total: 100,000

|  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | **CON Summary:** | Prior | 20/21 | 21/22 | 22/23 | 23/24 | 24/25 | 25/26 | Beyond | Total |
| Fed $ |  |  |  |  |  |  |  | 4,226,000 | 4,226,000 |
| Local Match |  |  |  |  |  |  |  |  |  |
| LSSRP Bond |  |  |  |  |  |  |  |  |  |
| Local AC |  |  |  |  |  |  |  |  |  |
| Total |  |  |  |  |  |  |  | 4,226,000 | 4,226,000 |

Phase Funding Details:

Proj id

Funds Src

Phase

Prior

20/21

21/22

22/23

23/24

24/25

25/26

Beyond

Total

#### 3743 HBP CON -4,226,000

Local Match

Fed. Reimb. Rate: 100.00% 11/2/2020 DLA-Admin: Not ready to ad within 6 months. CON funds moved from FFY 23/24 to Beyond. Action taken to financially constrain the FTIP (PUSH). Attempt will be made to program this project in year shown.

4,226,000

Total:

#### 3743 HBP

Local Match

CON

-4,226,000

4,226,000

Fed. Reimb. Rate: 100.00% 11/2/2020 DLA-Admin: Not ready to ad within 6 months. CON funds moved from FFY 22/23 to 23/24. Action taken to financially constrain the FTIP (PUSH). Attempt will be made to program this project in year shown.

Total:

#### 3743 HBP

Local Match

CON

4,226,000

-4,226,000

Fed. Reimb. Rate: 100.00% 9/9/2020 Vlad Popko: Not ready to ad within 6 months. CON funds moved from FFY Beyond to 22/23. As requested in September 2020 Survey.

Total:

#### 3743 HBP

Local Match

CON

-4,226,000

4,226,000

Fed. Reimb. Rate: 100.00% 10/25/2018 DLA-Admin: Not ready to ad within 6 months. CON funds moved from FFY 21/22 to Beyond. Action taken to financially constrain the FTIP (PUSH). Attempt will be made to program this project in year shown.

Total:

#### 3743 HBP

Local Match

CON

-4,226,000 4,226,000

Fed. Reimb. Rate: 100.00% 10/24/2018 DLA-Admin: Not ready to ad within 6 months. CON funds moved from FFY 20/21 to 21/22. Action taken to financially constrain the FTIP (PUSH). Attempt will be made to program this project in year shown.

Total:

#### 3743 HBP

Local Match

CON

4,226,000

-4,226,000

Fed. Reimb. Rate: 100.00% 9/28/2018 Tou Vang: Not ready to ad within 6 months. CON funds moved from FFY Beyond to 20/21. As requested in September 2018 Survey.

Total:

## Responsible Agency

#### 3743 HBP

Local Match

#### CON

-4,226,000

Prior 20/21 21/22 22/23 23/24 24/25 25/26 Beyond Total

4,226,000

Fed. Reimb. Rate: 100.00% 3/28/2018 DLA-Admin: Not ready to ad within 6 months. CON funds moved from FFY 21/22 to Beyond. Action taken to financially constrain the FTIP (PUSH). Attempt will be made to program this project in year shown.

v

Total:

#### 3743 HBP

Local Match

CON

-4,226,000 4,226,000

Fed. Reimb. Rate: 100.00% 10/24/2017 DLA-Admin: Not ready to ad within 6 months. CON funds moved from FFY 20/21 to 21/22. Action taken to financially constrain the FTIP (PUSH). Attempt will be made to program this project in year shown.

Total:

#### 3743 HBP

Local Match

#### CON -4,226,000

4,226,000

Fed. Reimb. Rate: 100.00% 10/24/2017 DLA-Admin: Not ready to ad within 6 months. CON funds moved from FFY 19/20 to 20/21. Action taken to financially constrain the FTIP (PUSH). Attempt will be made to program this project in year shown.

Total:

#### 3743 HBP CON

Local Match

Fed. Reimb. Rate: 100.00% 10/25/2016 DLA-Admin:Not ready to ad within 6 months. CON funds moved from FFY 17/18 to 18/19. Action taken to financially constrain the FTIP (PUSH). Attempt will be made to program this project in year shown. 7/27/2021 DLA-Admin: Fundline zeroed out due to FTIP cycle migration: 2018/19-23/24 to 2020/21-25/26. This does not impact funds in the current FTIP cycle.

Total:

#### 3743 HBP

Local Match

#### CON 1,555,000

1,555,000

Fed. Reimb. Rate: 100.00% 9/30/2016 Michael McCollum: Adjust funds per the fall survey and Ex. 6-D.

#### 3743 HBP CON

Local Match

Fed. Reimb. Rate: 100.00% 10/29/2015 DLA-Admin: Not ready to ad within 6 months. CON funds moved from FFY 17/18 to 18/19. Action taken to financially constrain the FTIP (PUSH). Attempt will be made to program this project in year shown. 7/27/2021 DLA-Admin: Fundline zeroed out due to FTIP cycle migration: 2018/19-23/24 to 2020/21-25/26. This does not impact funds in the current FTIP cycle.

#### 3743 HBP CON 2,671,000

Local Match

Fed. Reimb. Rate: 100.00% 9/18/2015 Michael McCollum: Move Construction to 17/18 per fall survey.

#### 3743 HBP CON -2,671,000

Local Match

Fed. Reimb. Rate: 100.00% 10/28/2014 DLA-Admin: Not ready to ad within 6 months. CON funds moved from FFY 16/17 to Beyond. Action taken to financially constrain the FTIP (PUSH). Attempt will be made to program this project in year shown.

#### 3743 HBP CON 2,671,000

Local Match

Fed. Reimb. Rate: 100.00% 10/13/2014 Wesley Zinke: Revised CON funding as requested in September 2014 Survey.

Total: 1,555,000

Total:

-2,671,000

Total: 2,671,000

Total:

-2,671,000

Total:

#### 3743 HBP

Local Match

CON

2,671,000

2,671,000

Fed. Reimb. Rate: 100.00% 11/2/2010 Michael McCollum: Reimbursement changed to 100% (Toll Credits). 11/2/2010 Michael McCollum: New Project - Program funds for Construction.

Total: 2,671,000

**MPO Summary:** Butte County Association Of Governments

## Number of Projects: 2

**Total Costs:**

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Prior | 20/21 | 21/22 | 22/23 | 23/24 | 24/25 | 25/26 | Beyond | Total |
| Fed $ | 1,693,000 |  |  |  | 150,000 |  |  | 7,551,000 | 9,394,000 |
| Local Match |  |  |  |  |  |  |  |  |  |
| LSSRP Bond |  |  |  |  |  |  |  |  |  |
| Local AC |  |  |  |  |  |  |  |  |  |
| Total for all Phases | 1,693,000 |  |  |  | 150,000 |  |  | 7,551,000 | 9,394,000 |