## Introduction
DLAE contact info: | https://dot.ca.gov/programs/local-assistance/other-important-issues/local-assistance-contacts
Highway Bridge Program (HBP), FFY 24/25 Programmed Projects Reports
If you have questions about the projects in this workbook, please contact your District Local Assistance Engineer from the below web link. If you have questions or comments to improve this workbook, please contact Andy Chou at andy.chou@dot.ca.gov or (279) 599-8855.

## Project Status
District | County | MPO/RTPA | Responsible Agency | Off Federal Aid Highways? (Yes, No, or NHS) | Seismic Bond Funds | Project Description | Federal Aid Project | FFY 24/25 Federal Funds Programmed | Current FFY Funds Obligated | Unobligated Balance | Shaded Means Needs Action | PE Auth Date | R/W Auth Date | CON Auth Date | Date of Last Payment | Comments
01 | Humboldt | Statewide Planning and Non MPO Regions | Cal Fire | Yes | No | BRIDGE NO. 04F0001, FOREST ROAD, OVER SOUTH FORK EEL RIVER, 0.1 MI W/O REDWOOD DR. Standalone Scour Countermeasure Project. |  | 82332.9 |  | 82332.9 | Not Obligated
01 | Humboldt | Statewide Planning and Non MPO Regions | Humboldt County | Yes | No | BRIDGE NO. 04C0173, PINE HILL RD OVER SWAIN SLOUGH, 0.2 MI E/O ELK RIVER RD. Replace existing 2-lane bridge with 2-lane bridge widened to accommodate 11’ lanes and 5’ shoulders. 10/7/2010: Toll Credits programmed for PE, R/W, & CON. | 5904(167) | 48978 | 0 | 48978 | Not Obligated |  |  | 2023-08-03 | 2025-06-13 | 2/4/2025 DLA-Admin: E76 process complete.
01 | Humboldt | Statewide Planning and Non MPO Regions | Humboldt County | No | No | BRIDGE NO. PM00228, Bridge Preventive Maintenance Program (BPMP), various bridges in the County of Humboldt. See Caltrans Local Assistance HBP website for backup list of projects. | 5904(207) | 616660.8 | 616661 | -0.2 | OK | 2025-05-08 |  |  |  | 6/2/2025 DLA-Admin: E76 process complete.
01 | Lake | Statewide Planning and Non MPO Regions | Lake County | Yes | No | BRIDGE NO. 14C0015, FIRST STREET OVER CLOVER CREEK, 0.1 MI E MAIN ST UPER LK. Replace existing two lane bridge with new two lane bridge wide enough to accommodate traffic lanes, shoulders and sidewalks. No added capacity. 1/17/2012: Toll Credits programmed for PE, R/W, & CON. | 5914(079) | 256000 | 256000 | 0 | OK | 2012-04-20 | 2018-07-19 |  | 2025-04-11 | 6/2/2025 DLA-Admin: E76 process complete.
01 | Lake | Statewide Planning and Non MPO Regions | Lake County | Yes | No | BRIDGE NO. 14C0022, BRIDGE ARBOR N RD OVER CLOVER CREEK, SOUTH OF SR 20 IN UPER LK. Bridge replacement, no added lanes. 6/16/2011: Toll Credits programmed for PE, R/W, & CON. | 5914(076) | 411000 | 411000 | 0 | OK | 2012-01-05 | 2016-07-20 |  | 2025-05-16 | 7/1/2025 DLA-Admin: E76 process complete.
01 | Lake | Statewide Planning and Non MPO Regions | Lake County | Yes | No | BRIDGE NO. 14C0035, WARDLAW ST OVER SAINT HELENA CREEK, 0.15 MI E SR 29 IN MIDLTN. Replace bridge. Replace existing one lane bridge with two lane bridge. 8/16/2013: Toll Credits programmed for PE, R/W, & CON. | 5914(088) | 324000 | 324000 | 0 | OK | 2014-07-14 |  |  | 2025-03-21 | 8/1/2025 DLA-Admin: E76 process complete.
01 | Lake | Statewide Planning and Non MPO Regions | Lake County | Yes | No | BRIDGE NO. 14C0036, RANCHERIA ROAD OVER MIDDLE CREEK, 0.5 MI W ELK MOUNTAIN RD. Bridge rehabilitation, no lanes added. 6/16/2011: Toll Credits programmed for PE, R/W, & CON. | 5914(075) | 184000 | 184000 | 0 | OK | 2012-01-05 |  |  | 2025-03-14 | 6/2/2025 DLA-Admin: E76 process complete.
01 | Lake | Statewide Planning and Non MPO Regions | Lake County | Yes | No | BRIDGE NO. 14C0048, CHALK MTN RD OVER NORTH FORK CACHE CREEK, IN SPRING VALLEY LAKE DEV. Bridge Replacement 1-lane bridge to 2-lane. 11/4/2013: Toll Credits programmed for PE, R/W, & CON. | 5914(135) | 500000 | 500000 | 0 | OK | 2014-07-14 | 2021-03-12 | 2025-08-28 | 2025-08-27 | 9/2/2025 DLA-Admin: E76 process complete.
01 | Lake | Statewide Planning and Non MPO Regions | Lake County | Yes | No | BRIDGE NO. 14C0106, BARTLETT SPR RD OVER BARTLETT CREEK, 19 MI E OF RTE 20. Bridge Replacement. Replace one lane bridge to two lane bridge (no added capacity). 11/4/2013: Toll Credits programmed for PE, R/W, & CON. | 5914(091) | 734000 | 734000 | 0 | OK | 2014-07-14 |  |  | 2025-04-28 | 6/3/2025 DLA-Admin: E76 process complete.
01 | Lake | Statewide Planning and Non MPO Regions | Lake County | Yes | No | BRIDGE NO. 14C0114, BIG CANYON ROAD OVER BIG CANYON CREEK, 8 MI N OF SR 175. Standalone Scour Countermeasure Project. | 5914(136) | 16820.7 | 16821 | -0.3 | OK | 2025-03-20 |  |  |  | 4/1/2025 DLA-Admin: E76 process complete.
01 | Mendocino | Statewide Planning and Non MPO Regions | Cal Fire | Yes | No | BRIDGE NO. 10F0011, FOREST ROAD 320 OVER SOUTH FORK NOYO RIVER, PARLIN FORK CONSERVATION. Replace 1-lane timber bridge with 1-lane bridge. |  | 70824 |  | 70824 | Not Obligated
01 | Mendocino | Statewide Planning and Non MPO Regions | Cal Fire | Yes | No | BRIDGE NO. 10F0019, FOREST ROAD 601, OVER SOUTH FORK CASPAR CREEK, N OF INT OF FOREST RD 600. Replace 1-lane timber bridge with 1-lane bridge. |  | 88530 |  | 88530 | Not Obligated
01 | Mendocino | Statewide Planning and Non MPO Regions | Cal Fire | Yes | No | BRIDGE NO. 10F0022, FOREST ROAD 100 OVER JAMES CREEK, 0.4 MI N JCT SR 20. Standalone Scour Countermeasure Project. |  | 54888.6 |  | 54888.6 | Not Obligated
01 | Mendocino | Statewide Planning and Non MPO Regions | Cal Fire | Yes | No | BRIDGE NO. 10F0037, FOREST ROAD 400 EAST OF JUNCTION ROAD 440, OVER BUNKER GULCH. Replace 1-lane bridge with 1-lane bridge. |  | 80562.3 |  | 80562.3 | Not Obligated
01 | Mendocino | Statewide Planning and Non MPO Regions | Cal Fire | Yes | No | BRIDGE NO. 10F0051, FOREST ROAD 900 OVER JAMES CREEK, S OF SR 20, N OF RD 910. Standalone Scour Countermeasure Project. |  | 54888.6 |  | 54888.6 | Not Obligated
01 | Mendocino | Statewide Planning and Non MPO Regions | Cal Fire | Yes | No | BRIDGE NO. 10F0056, FOREST ROAD 330 AT PARLIN FORK CONSERVATION OVER PARLIN CREEK. Replace 1-lane bridge with 1-lane bridge. |  | 91185.9 |  | 91185.9 | Not Obligated
01 | Mendocino | Statewide Planning and Non MPO Regions | Cal Fire | Yes | No | BRIDGE NO. 10F0057, FOREST ROAD 452 WEST OF JUNCTION FOREST RD 30 OVER HARE CREEK. Replace 1-lane bridge with 1-lane bridge. |  | 100038.9 |  | 100038.9 | Not Obligated
01 | Mendocino | Statewide Planning and Non MPO Regions | Mendocino County | Yes | No | BRIDGE NO. 10C0032, PHILO GREENWOOD RD OVER NAVARRO RIVER, 0.4 MI W OF SR 128. Bridge rehabilitation. Widen existing arch and replace trestle of approach span to current standards. 9/1/2010: Toll Credits programmed for PE, R/W, & CON. | 5910(121) | 407000 | 407000 | 0 | OK | 2016-07-20 | 2024-08-02 |  | 2025-04-04 | 7/1/2025 DLA-Admin: E76 process complete.
01 | Mendocino | Statewide Planning and Non MPO Regions | Mendocino County | No | No | BRIDGE NO. 10C0065, N STATE ST OVER ACKERMAN CREEK, 0.2 MI N ORR SPRINGS RD. Replace existing 2 lane bridge to a 3 lane bridge, to accommodate a center turn lane and sidewalks. | 5910(117) | 132795 | 132794 | 1 | OK | 2011-03-27 | 2016-07-26 | 2025-06-02 | 2025-07-09 | 7/1/2025 DLA-Admin: E76 process complete.
01 | Mendocino | Statewide Planning and Non MPO Regions | Mendocino County | Yes | No | BRIDGE NO. 10C0073, WILDERNESS LDGE RD OVER DUTCH CHARLIE CREEK, 0.7 MI N OF BRANSCOMB RD. Replace existing one lane bridge with two lane bridge. 11/6/2013: Toll Credits programmed for PE, R/W, & CON. | 5910(122) | 175000 | 175000 | 0 | OK | 2014-01-29 | 2024-08-28 |  | 2025-05-02 | 7/7/2025 Andy Chou: E76 process complete.
01 | Mendocino | Statewide Planning and Non MPO Regions | Mendocino County | Yes | No | BRIDGE NO. 10C0139, USAL ROAD OVER USAL CREEK, 5.9 MI N JCT SR 1. Replace 1 lane bridge with a 1 lane bridge. 10/15/2014: Toll Credits programmed for PE, R/W, & CON. | 5910(126) | 190500 | 190500 | 0 | OK | 2016-01-08 |  |  | 2024-12-13 | 1/2/2025 DLA-Admin: E76 process complete.
01 | Mendocino | Statewide Planning and Non MPO Regions | Mendocino County | Yes | No | BRIDGE NO. 10C0146, LAMBERT LANE OVER ROBINSON CREEK, 0.1 MI W OF S.H. 128. Replace 2 lane bridge with 2 lane bridge. 10/16/2014: Toll Credits programmed for PE, R/W, & CON. | 5910(127) | 6772250 | 6772250 | 0 | OK | 2015-05-14 | 2022-06-29 | 2025-03-20 | 2025-05-14 | 6/3/2025 DLA-Admin: E76 process complete.
01 | Mendocino | Statewide Planning and Non MPO Regions | Willits | No | No | BRIDGE NO. 10C0198, E VALLEY ST, OVER BROADDUS CREEK, 0.1 MI E US 101. Replace 2-lane bridge with 2-lane bridge. | 5082(068) | 690400 | 690400 | 0 | OK | 2025-07-22 |  |  |  | 8/1/2025 DLA-Admin: E76 process complete.
02 | Lassen | Statewide Planning and Non MPO Regions | Lassen County | Yes | No | BRIDGE NO. 07C0040, CR 305 (MAPES RD) OVER HARTSON SLOUGH, 0.4 MI E/O RD 303. Replace timber 2-lane bridge with 2-lane bridge. | 5907(086) | 123942 |  | 123942 | Not Obligated
02 | Lassen | Statewide Planning and Non MPO Regions | Lassen County | Yes | No | BRIDGE NO. 07C0041, CR 305 (MAPES RD) OVER WHITEHEAD SLOUGH, 0.6 MI S/O RD 306. Replace timber 2-lane bridge with 2-lane bridge. | 5907(087) | 123942 |  | 123942 | Not Obligated |  |  |  |  | 3/18/2025 Jessica Pecha: E76 pending additional information from local agency.
02 | Shasta | Shasta County Regional Transportation Planning Agency | Cal Fire | Yes | No | BRIDGE NO. 06F0030, MIDDLE BR RD OVER BULLHOCK CREEK, LATOUR STATE FOREST IN SHASTA COUNTY. Standalone Paint Bridge. |  | 175289.4 |  | 175289.4 | Not Obligated
02 | Shasta | Shasta County Regional Transportation Planning Agency | Redding | No | No | BRIDGE NO. 06C0071, RAILROAD AVE OVER CANYON HOLLOW CREEK, 0.1 MI S CANYON CREEK RD. Replace two-lane bridge with two-lane bridge. (No added lane capacity). | 5068(038) | 267360.6 | 267360 | 0.6 | OK | 2011-04-15 | 2021-06-23 | 2024-01-04 | 2025-05-14 | 7/1/2025 DLA-Admin: E76 process complete.
02 | Shasta | Shasta County Regional Transportation Planning Agency | Redding | No | No | BRIDGE NO. 06C0085, EASTSIDE RD OVER CANYON HOLLOW CREEK, 0.2 MI N HOSPITAL LANE. Replace bridge two-lane bridge with two-lane bridge. (No added lane capacity). | 5068(035) | 110662.5 | 110662 | 0.5 | OK | 2011-04-15 | 2021-06-22 |  | 2025-07-24 | 7/1/2025 DLA-Admin: E76 process complete.
02 | Shasta | Shasta County Regional Transportation Planning Agency | Redding | No | No | BRIDGE NO. 06C0307, CANYON RD OVER A.C.I.D. CANAL, 0.2 MI SW OF SR 273. Bridge rehabilitation and widening. (No added capacity) | 5068(037) | 162949.2033 | 162949 | 0.2033 | OK | 2011-04-15 | 2022-06-06 |  | 2025-07-11 | 12/4/2024 DLA-Admin: E76 process complete.
02 | Shasta | Shasta County Regional Transportation Planning Agency | Redding | No | No | BRIDGE NO. 06C0341, GIRVAN RD OVER OLNEY CREEK, 0.6 MI E OF SH 273. Replace two-lane bridge with two-lane bridge. No added lane capacity. | 5068(039) | 296575.5 | 296575 | 0.5 | OK | 2011-11-04 |  |  | 2025-02-05 | 2/4/2025 DLA-Admin: E76 process complete.
02 | Shasta | Shasta County Regional Transportation Planning Agency | Shasta County | No | No | BRIDGE NO. 06C0192, DRY CREEK ROAD OVER DRY CREEK, 2.2 MI N SR 299. Stand alone Bridge Preventive Maintenance. | 5906(146) | 21600 | 21600 | 0 | OK | 2025-01-30 |  |  | 2025-08-13 | 2/4/2025 DLA-Admin: E76 process complete.
02 | Shasta | Shasta County Regional Transportation Planning Agency | Shasta County | Yes | No | BRIDGE NO. 06C0297, MIDDLE CREEK RD OVER MIDDLE CREEK, 0.7 MI E OF IRON MTN RD. Replace 1-lane bridge with 2-lane bridge. | 5906(148) | 212472 | 212472 | 0 | OK | 2025-03-04 |  |  | 2025-08-15 | 4/1/2025 DLA-Admin: E76 process complete.
02 | Shasta | Shasta County Regional Transportation Planning Agency | Shasta County | No | No | BRIDGE NO. PM00213, Bridge Preventive Maintenance Program (BPMP), various bridges in Shasta County. See Caltrans Local Assistance HBP website for backup list of projects. | 5906(147) | 79568.8 | 79569 | -0.2 | OK | 2025-01-30 |  |  | 2025-08-13 | 2/4/2025 DLA-Admin: E76 process complete.
02 | Siskiyou | Statewide Planning and Non MPO Regions | Dunsmuir | Yes | No | BRIDGE NO. 02C0076, BUTTERFLY AVE, OVER SACRAMENTO RIVER, JUST E SACRAMENTO AVE. Replace Bridge. 4/5/2010: Toll Credits programmed for PE, RW & Con. 10/17/2016: Toll credits used for R/W and Con. | 5183(007) | 44500 | 44500 | 0 | OK | 2017-12-15 | 2023-11-28 |  | 2025-05-07 | 9/2/2025 DLA-Admin: E76 process complete.
02 | Tehama | Statewide Planning and Non MPO Regions | Tehama County | No | No | BRIDGE NO. 00L0004, MC COY RD, OVER DIBBLE CR. Replace 1 lane low water crossing with 2 lane bridge. | 5908(029) | 280631.9441 | 280632 | -0.0559 | OK | 2001-03-01 | 2007-05-25 |  | 2025-07-28 | 4/1/2025 DLA-Admin: E76 process complete.
02 | Tehama | Statewide Planning and Non MPO Regions | Tehama County | Yes | No | BRIDGE NO. 08C0008, EVERGREEN RD, OVER S FORK COTTONWOOD CREEK, 0.3 MI N BOWMAN RD. Replace 1 lane bridge with 2 lane bridge. 4/5/2010: Toll Credits programmed for R/W & Con. Other Federal funds on project, must be programmed in FTIP. | 5908(121) | 896000 | 0 | 896000 | Not Obligated | 1999-04-14 | 2015-05-27 | 2022-07-06 | 2025-09-02
02 | Tehama | Statewide Planning and Non MPO Regions | Tehama County | No | No | BRIDGE NO. PM00200, Bridge Preventive Maintenance Program (BPMP), various bridges in Tehama County. See Caltrans Local Assistance HBP website for backup list of projects. | 5908(118) | 170862.9 | 170863 | -0.1 | OK | 2025-03-04 |  |  |  | 4/1/2025 DLA-Admin: E76 process complete.
02 | Trinity | Statewide Planning and Non MPO Regions | Trinity County | No | No | BRIDGE NO. 05C0039, HYAMPOM ROAD OVER LITTLE CREEK, 6.0 MI W OF SR 3. Replace 2-lane bridge with 2-lane bridge. | 5905(131) | 357776.8 | 357777 | -0.2 | OK | 2025-03-06 |  |  |  | 4/1/2025 DLA-Admin: E76 process complete.
02 | Trinity | Statewide Planning and Non MPO Regions | Trinity County | Yes | No | BRIDGE NO. 05C0122, SOUTH FORK ROAD OVER KERLIN CREEK, 3.8 MI N HYAMPOM RD. Standalone Paint Bridge. | 5905(129) | 110662.5 | 110662 | 0.5 | OK | 2025-03-11 |  |  |  | 4/1/2025 DLA-Admin: E76 process complete.
02 | Trinity | Statewide Planning and Non MPO Regions | Trinity County | Yes | No | BRIDGE NO. 05C0144, PRICE CREEK RD, OVER PRICE CREEK, 0.7 MI SOUTH OF SR 299. Replace 1-lane bridge with 2-lane bridge. | 5905(138) | 354120 | 354120 | 0 | OK | 2025-03-06 |  |  |  | 4/1/2025 DLA-Admin: E76 process complete.
02 | Trinity | Statewide Planning and Non MPO Regions | Trinity County | Yes | No | BRIDGE NO. 05C0147, LONG RIDGE ROAD OVER SALT CREEK, 2 MI E JCT HOAGLIN RD. Standalone Paint Bridge and Scour Countermeasure Project. | 5905(130) | 354120 | 354120 | 0 | OK | 2025-03-04 |  |  |  | 4/1/2025 DLA-Admin: E76 process complete.
03 | Butte | Butte County Association Of Governments | Butte County | No | No | BRIDGE NO. 12C0009L, SKYWAY RD WB, OVER BUTTE CREEK, 0.5 MI SE OF HUMBUG RD. Replace 2-lane bridge with 2-lane bridge, | 5912(140) | 880000 | 880000 | 0 | OK | 2025-05-27 |  |  |  | 6/2/2025 DLA-Admin: E76 process complete.
03 | Butte | Butte County Association Of Governments | Butte County | No | No | BRIDGE NO. 12C0242, ORD FERRY ROAD, OVER LITTLE CHICO CREEK, 1 MI EAST OF RIVER ROAD. Replace the existing 2 lane structurally deficient bridge with a new 2 lane bridge. | 5912(103) | 5589120.225 | 5589118 | 2.225 | OK | 2014-07-21 | 2020-03-04 | 2023-06-27 | 2025-07-09 | 6/3/2025 DLA-Admin: E76 process complete.
03 | Butte | Butte County Association Of Governments | Butte County | Yes | No | BRIDGE NO. 12C0301, CANA HWY OVER PINE CREEK, 4 MI W/O S R 99. Standalone Scour Countermeasure Project. | 5912(141) | 112433.1 | 112433 | 0.1 | OK | 2025-07-24 |  |  |  | 8/1/2025 DLA-Admin: E76 process complete.
03 | Butte | Butte County Association Of Governments | Chico | Yes | No | BRIDGE NO. 12C0328, POMONA ROAD OVER LITTLE CHICO CREEK, 0.4 MI SE/O MILLER AVE. Replace the existing 2 lane bridge, without adding lane capacity. 11/2/2010: Toll Credits programmed for PE, R/W, & CON., | 5037(036) | 3295000 | 3294997 | 3 | OK | 2017-05-18 | 2022-03-09 | 2025-03-03 | 2025-08-15 | 4/1/2025 DLA-Admin: E76 process complete.
03 | Butte | Butte County Association Of Governments | Department of Water Resources | No | No | BRIDGE NO. 12 0184, STATE ROUTE 162 OVER CANYON CREEK, 03-BUT-162-29.96. Standalone Bridge Preventive Maintenance. | 6248(033) | 1400000 | 1400000 | 0 | OK | 2025-08-18 |  |  |  | 9/2/2025 DLA-Admin: E76 process complete.
03 | El Dorado | Sacramento Area Council Of Governments | El Dorado County | No | No | BRIDGE NO. 25C0003, BUCKS BAR RD, OVER N FORK COSUMNES RIVER, 1.2 MI N MT AUKUM RD. Replace existing 1 lane structure with new 2 lane structure. Not capacity increasing. | 5925(051) | 179715.9 | 0 | 179715.9 | Not Obligated | 2007-11-28 |  |  | 2025-02-14 | 8/18/2025 Roberta Jensen: Funds Reserved, waiting for transmittal to FHWA.
03 | El Dorado | Sacramento Area Council Of Governments | El Dorado County | No | No | BRIDGE NO. 25C0033, NEWTOWN RD, OVER S FK WEBER CR, 0.7 MI W OF SNOWS RD. Replace existing 2 lane bridge. No added lane capacity. | 5925(086) | 1432415.4 | 1432416 | -0.6 | OK | 2010-08-12 | 2020-02-12 | 2024-07-15 | 2025-07-03 | 9/2/2025 DLA-Admin: E76 process complete.
03 | El Dorado | Sacramento Area Council Of Governments | El Dorado County | Yes | No | BRIDGE NO. 25C0061, MOSQUITO RD, OVER SOUTH FK AMERICAN RIVER, 5.7 MI NORTH OF US 50. Replace the existing structurally deficient 1 lane bridge with a new 2 lane bridge. 11/2/2010: Toll Credits programmed for PE, R/W, & CON. High Cost Project agreement required. | 5925(098) | 191000 | 191000 | 0 | OK | 2011-04-26 | 2018-01-26 | 2021-09-01 | 2025-07-09 | 5/2/2025 DLA-Admin: E76 process complete.
03 | El Dorado | Sacramento Area Council Of Governments | El Dorado County | Yes | No | BRIDGE NO. 25C0078, BREEDLOVE ROAD OVER CANYON CREEK, 1.0 MI N/O WENTWORTH S RD. Replace 1-lane timber bridge with 2-lane bridge. Not capacity increasing. |  | 407238 |  | 407238 | Not Obligated
03 | El Dorado | Sacramento Area Council Of Governments | Placerville | No | No | BRIDGE NO. 25C0029, PLACERVILLE DR, OVER HANGTOWN CREEK, 0.3 MI W COLD SPRINGS RD. Replace existing functionally obsolete 2-lane bridge with a new 2-lane bridge. | 5015(024) | 8154055.65 | 1161514 | 6992541.65 | Not Obligated | 2013-05-07 | 2023-02-21 |  | 2025-08-08 | 12/4/2024 DLA-Admin: E76 process complete.
03 | Glenn | Statewide Planning and Non MPO Regions | Glenn County | Yes | No | BRIDGE NO. 00L0053, COUNTY ROAD 35, OVER WALKER CREEK. Build a new 2 lane bridge to replace an existing low water crossing. 1/20/2011: Toll Credits programmed for PE, R/W & CON. | NBIL(510) | 3024000 | 0 | 3024000 | Not Obligated | 2011-07-21 |  |  | 2025-03-28 | 8/18/2025 Roberta Jensen: Funds Reserved, waiting for transmittal to FHWA.
03 | Glenn | Statewide Planning and Non MPO Regions | Glenn County | Yes | No | BRIDGE NO. 00L0054, County Road 35 OVER Wilson Creek , Replace the existing 2 lane Low Water Crossing with a new 2 lane bridge. 1/20/2011: Toll Credits programmed for PE, R/W, & CON. | NBIL(519) | 3500000 | 0 | 3500000 | Not Obligated | 2011-07-21 | 2017-09-11 |  | 2023-04-26
03 | Glenn | Statewide Planning and Non MPO Regions | Glenn County | Yes | No | BRIDGE NO. 11C0015, ROAD 67, OVER BRANCH HOWARD SLOUGH, 1.3 MI EAST OF ROAD Z. Replace this 2 lane structurally deficient bridge with a new 2 lane bridge. 11/2/2010: Toll Credits programmed for PE & CON. 10/8/2013: Toll credits used for R/W. | 5911(048) | 826000 | 826000 | 0 | OK | 2011-08-04 | 2017-08-03 | 2023-07-31 | 2025-08-15 | 6/2/2025 DLA-Admin: E76 process complete.
03 | Glenn | Statewide Planning and Non MPO Regions | Glenn County | Yes | No | BRIDGE NO. 11C0016, ROAD 67, OVER HOWARD SLOUGH, 1.7 MI E RD Z. Replace the existing 2 lane Structurally deficient bridge with a new 2 lane bridge. 11/2/2010: Toll Credits programmed for PE, R/W & CON. 6/19/2014: | 5911(047) | 404500 | 404500 | 0 | OK | 2011-07-19 | 2017-08-02 | 2023-07-28 | 2025-08-13 | 7/1/2025 DLA-Admin: E76 process complete.
03 | Glenn | Statewide Planning and Non MPO Regions | Glenn County | Yes | No | BRIDGE NO. 11C0017, COUNTY RD 67, OVER HOWARD SLOUGH, 1.8 MI E OF RD 'Z'. Replace the 2 lane functionally obsolete bridge with a new 2 lane bridge. 11/2/2010: Toll Credits programmed for PE, R/W & CON. | 5911(049) | 226750 | 226750 | 0 | OK | 2011-07-19 | 2017-08-03 | 2023-07-31 | 2025-08-20 | 6/2/2025 DLA-Admin: E76 process complete.
03 | Glenn | Statewide Planning and Non MPO Regions | Glenn County | Yes | No | BRIDGE NO. 11C0179, COUNTY ROAD #67, OVER BRANCH HOWARD SLOUGH, 1.9 MI E OF RD Z. Replace the existing 2 lane structurally deficient bridge with a new 2 lane bridge. 11/2/2010: Toll Credits programmed for PE, R/W & CON. | 5911(050) | 621250 | 621250 | 0 | OK | 2011-07-19 | 2017-08-03 | 2023-08-10 | 2025-08-20 | 6/2/2025 DLA-Admin: E76 process complete.
03 | Nevada | Statewide Planning and Non MPO Regions | Nevada County | Yes | No | BRIDGE NO 17C0046 Hirschdale Rd over UPRR. Rehabilitate and seismic retrofit the existing bridge. No added capacity. 4/25/2013 Revised 9/25/15: Toll Credits programmed for PE, R/W, & CON. | 5917(097) | 2565760 | 2565760 | 0 | OK | 2016-05-04 | 2019-12-13 | 2024-03-11 | 2025-08-13 | 7/1/2025 DLA-Admin: E76 process complete.
03 | Nevada | Statewide Planning and Non MPO Regions | Nevada County | Yes | No | BRIDGE NO. 17C0010, SODA SPRINGS RD, OVER SOUTH YUBA RIVER, NEAR VAN NORDEN LAKE RD. Replace the existing 2 lane structurally deficient bridge with a new 2 lane bridge. 10/21/2013: Toll Credits programmed for PE, R/W, & CON. | 5917(079) | 12042 |  | 12042 | Not Obligated |  |  |  |  | 1/2/2025 DLA-Admin: E76 process complete.
03 | Nevada | Statewide Planning and Non MPO Regions | Nevada County | Yes | No | BRIDGE NO. 17C0028, RELIEF HILL RD OVER HUMBUG CREEK, NEAR GRANITEVILLE RD. Replace 1-lane bridge with 1-lane bridge. | 5917(122) | 309855 | 309855 | 0 | OK | 2025-04-08 |  |  |  | 5/2/2025 DLA-Admin: E76 process complete.
03 | Nevada | Statewide Planning and Non MPO Regions | Nevada County | Yes | No | BRIDGE NO. 17C0031, DOG BAR ROAD, OVER BEAR RIVER, AT NEVADA-PLACER CO LINE. Replace the existing 1 lane functionally obsolete bridge with a new 2 lane bridge. 10/21/2013: Toll Credits programmed for PE, R/W, & CON. | 5917(084) | 8147000 | 8147000 | 0 | OK | 2014-04-09 | 2022-02-16 | 2024-02-08 | 2025-08-13 | 4/1/2025 DLA-Admin: E76 process complete.
03 | Nevada | Statewide Planning and Non MPO Regions | Nevada County | Yes | No | BRIDGE NO. 17C0045, HIRSCHDALE RD, OVER TRUCKEE RIVER, AT HINTON. Replace Bridge. Replace existing one lane bridge with one lane bridge. 10/9/2015: Toll Credits programmed for PE & CON. 9/2/2016: Toll credits used for R/W. Other federal funds on project (HIP) must be programmed in the FTIP. | 5917(092) | 7921000 | 7921000 | 0 | OK | 2016-02-18 | 2019-12-16 | 2024-03-12 | 2025-08-08 | 7/1/2025 DLA-Admin: E76 process complete.
03 | Placer | Sacramento Area Council Of Governments | Lincoln | No | No | BRIDGE NO. 19 0059, McBEAN PARK DR OVER AUBURN RAVINE, E of EAST AVE. Replace existing 2 lane bridge. with a three lane bridge. Toll Credits programmed for RW utilizing BIC credit earned. | 5089(021) | 569247.9 | 569248 | -0.1 | OK | 2013-05-09 |  |  | 2023-04-13 | 6/2/2025 DLA-Admin: E76 process complete.
03 | Placer | Sacramento Area Council Of Governments | Placer County | Yes | No | BRIDGE NO. 19C0002, YANKEE JIMS RD., OVER NORTH FORK AMERICAN RIV, 1.5 MI W SHIRTTAIL CAN.RD. Replace the existing one lane structurally deficient bridge with a new 2 lane bridge. 6/6/2011: Toll Credits programmed for PE, R/W & CON. High Cost Project Agreement required. | 5919(099) | 21798032 | 20300000 | 1498032 | Not Obligated | 2011-08-05 | 2025-02-05 | 2025-04-21 | 2025-05-28 | 8/28/2025 Andy Chou: Funds Reserved, waiting for transmittal to FHWA.
03 | Placer | Sacramento Area Council Of Governments | Placer County | No | No | BRIDGE NO. 19C0060, AUBURN-FRSTHILL RD OVER N FK AMERICAN RIVER, EAST OF I-80. Standalone Bridge Preventive Maintenance. | 5919(164) | 6457600 | 6457600 | 0 | OK | 2024-03-12 |  |  | 2025-08-01 | 5/2/2025 DLA-Admin: E76 process complete.
03 | Sacramento | Sacramento Area Council Of Governments | Sacramento | NHS | No | BRIDGE NO. 24C0081, AUBURN BLVD OVER ARCADE CREEK, AT WINDING WAY. Replace existing five lane bridge with a new six lane bridge. Toll Credits programmed for CON utilizing BIC credit earned. | 5002(168) | 9229500 | 9229500 | 0 | OK | 2013-09-12 | 2021-03-23 | 2025-01-22 | 2025-06-11 | 2/4/2025 DLA-Admin: E76 process complete.
03 | Sacramento | Sacramento Area Council Of Governments | Sacramento County | No | No | BRIDGE NO. 24C0005, WALNUT GROVE XING OVER SACRAMENTO RIVER, IN WALNUT GROVE. Standalone Bridge Preventive Maintenance. | 5924(288) | 1000000 | 1000000 | 0 | OK | 2025-02-11 |  |  |  | 3/3/2025 DLA-Admin: E76 process complete.
03 | Sacramento | Sacramento Area Council Of Governments | Sacramento County | Yes | No | BRIDGE NO. 24C0042, TYLER IS BR RD, OVER GEORGIANA SLOUGH, 1.5 MI E ISLETON. Replace the existing 2 lane bridge with a new 2 lane bridge. 5/29/2014 1:33:43 PM. 10/21/2014: Toll Credits programmed for PE & CON. 10/8/2021: Toll credits for PE & CON deleted. Scope not clear. 7/21/2022: Toll Credits programmed for PE & CON. | 5924(209) | 350000 | 350000 | 0 | OK | 2024-02-01 |  |  | 2025-04-04 | 7/1/2025 DLA-Admin: E76 process complete.
03 | Sacramento | Sacramento Area Council Of Governments | Sacramento County | No | No | BRIDGE NO. 24C0155, FRANKLIN BLVD, OVER MOKELUMNE RIVER OVERFLOW, 1.8 MI N SAN JQUIN CO LIN. Replace the existing structurally deficient 2 lane bridge with a new 2 lane bridge. | 5924(155) | 2596584.9 | 2596585 | -0.1 | OK | 2010-08-31 | 2017-05-30 | 2020-03-02 | 2025-03-07 | 5/2/2025 DLA-Admin: E76 process complete.
03 | Sierra | Statewide Planning and Non MPO Regions | Sierra County | Yes | No | BRIDGE NO. 13C0051, PLUMBAGO ROAD, OVER KANAKA CREEK, 1.6 MI SOUTH OF ALLEGHANY. Replace the existing Functionally obsolete bridge with a new one lane bridge, 11/6/2013: Toll Credits programmed for PE, R/W, & CON. | 5913(058) | 1690000 | 1690000 | 0 | OK | 2014-05-22 | 2022-04-14 | 2024-06-24 | 2024-07-03 | 8/1/2025 DLA-Admin: E76 process complete.
03 | Sutter | Sacramento Area Council Of Governments | Sutter County | Yes | No | BRIDGE NO. 18C0057, TISDALE RD, OVER WESTSIDE CANAL, 100 E CRANMORE RD. Replace the existing structurally deficient 2 lane bridge with a new 2 lane bridge, Toll Credits programmed for PE, R/W, & CON. | 5918(087) | 2265000 | 0 | 2265000 | Not Obligated | 2014-11-26 | 2019-04-23 |  | 2025-08-01
03 | Sutter | Sacramento Area Council Of Governments | Sutter County | No | No | BRIDGE NO. 18C0074, NICOLAUS AVE, OVER COON CREEK, 1 MI W/O PLEASANT GROVE R. Replace the existing 2 lane bridge with a new 2 lane bridge. | 5918(080) | 212472 | 212472 | 0 | OK | 2012-07-06 | 2017-04-17 |  | 2025-04-04 | 12/4/2024 DLA-Admin: E76 process complete.
03 | Sutter | Sacramento Area Council Of Governments | Sutter County | No | No | BRIDGE NO. 18C0105, LARKIN RD OVER S BRCH SUTTR-BUTTE CANAL, 0.2 MI N OF ENCINAL RD. Replace the existing 2 lane bridge with a new 2 lane bridge. | 5918(079) | 123942 | 123942 | 0 | OK | 2012-06-01 | 2017-04-17 |  | 2025-03-28 | 12/4/2024 DLA-Admin: E76 process complete.
03 | Sutter | Sacramento Area Council Of Governments | Sutter County | No | No | BRIDGE NO. 18C0113, HOWSLEY RD, OVER PLEASANT GROVE CRK CANAL, AT NATOMAS RD. Replace 2 lane bridge. No added capacity. Other Federal Funds must be programmed in FTIP. | 5918(101) | 212029.35 | 0 | 212029.35 | Not Obligated | 2015-05-19 |  |  | 2024-04-12
03 | Sutter | Sacramento Area Council Of Governments | Sutter County | No | No | PM00014, Bridge Preventive Maintenance Program, Sutter County, various locations. See Caltrans Local Assistance HBP web site for backup list of bridges. | 5918(086) | 489771.8631 | 0 | 489771.8631 | Not Obligated | 2013-09-10 | 2019-05-17 |  | 2024-02-02 | 4/24/2025 Andy Chou: Funds Reserved, waiting for transmittal to FHWA.
03 | Yolo | Sacramento Area Council Of Governments | Yolo County | Yes | No | BRIDGE NO. 22C0003, C. R. 41, OVER CACHE CREEK, 500' E SH 16. Replace existing 2 lane bridge with a new 2 lane bridge: Toll Credits programmed for PE, R/W, & CON. | 5922(077) | 9724750 | 9724750 | 0 | OK | 2011-04-22 | 2021-03-11 | 2025-07-18 | 2025-05-07 | 8/1/2025 DLA-Admin: E76 process complete.
03 | Yolo | Sacramento Area Council Of Governments | Yolo County | Yes | No | BRIDGE NO. 22C0117, COUNTY ROAD 29 OVER DRY SLOUGH, 0.77 MI W OF C.R. #98. Replace an existing 2 lane bridge with a new 2 lane bridge. 10/5/2012: Toll Credits programmed for PE, R/W, & CON. | 5922(099) | 2595924 | 0 | 2595924 | Not Obligated | 2014-04-14 | 2017-05-30 |  | 2025-08-13
03 | Yolo | Sacramento Area Council Of Governments | Yolo County | Yes | No | BRIDGE NO. 22C0126, COUNTY ROAD 96 OVER UNION SCHOOL SLOUGH, 1.38 MI S OF C.R. #27. Replace two lane bridge with two lane bridge. Toll Credits programmed for PE, R/W, & CON. | 5922(103) | 534080 | 534080 | 0 | OK | 2016-03-30 | 2025-05-01 |  | 2025-07-11 | 6/2/2025 DLA-Admin: E76 process complete.
03 | Yuba | Sacramento Area Council Of Governments | Yuba County | Yes | No | BRIDGE NO. 16C0075, ELLIS RD OVER SIMMERLY SLOUGH, 1.0 MI E OF SH 70. Replace existing 2 lane bridge with a 2 lane bridge. Darlene Wulff, 10/16/2017 7:52:28 AM. 3/18/2018: Toll Credits programmed for PE, R/W, & CON. | 5916(131) | 118625 | 118625 | 0 | OK | 2019-11-25 |  |  | 2025-05-07 | 5/2/2025 DLA-Admin: E76 process complete.
03 | Yuba | Sacramento Area Council Of Governments | Yuba County | Yes | No | BRIDGE NO. 16C0077, IOWA CITY RD OVER JACK SLOUGH, 0.35 MI E OF FRUITLAND RD. Replace existing 2 lane bridge with a new 2 lane bridge, 3/25/2013: Toll Credits programmed for PE, R/W, & CON. | 5916(105) | 53931 | 0 | 53931 | Not Obligated | 2013-08-30 |  | 2022-04-15 | 2024-01-25
03 | Yuba | Sacramento Area Council Of Governments | Yuba County | No | No | BRIDGE NO. PM00129, Bridge Preventive Maintenance Program (BPMP), various bridges in the County of Yuba. See Caltrans Local Assistance HBP web site for backup list of bridges. | 5916(126) | 15315.69 | 0 | 15315.69 | Not Obligated | 2018-04-20 |  | 2023-06-26 | 2025-08-01 | 7/1/2025 DLA-Admin: E76 process complete.
04 | Alameda | Metropolitan Transportation Commission | Oakland | No | No | PM00002, Bridge Preventive Maintenance Program (BPMP), various bridges in the City of Oakland. See Caltrans Local Assistance HBP web site for backup list of bridges. | 5012(137) | 2004899.9568 | 0 | 2004899.9568 | Not Obligated | 2017-01-31 |  |  | 2020-09-01
04 | Contra Costa | Metropolitan Transportation Commission | Contra Costa County | Yes | No | BRIDGE NO. 28C0207, DEL MONTE DR, OVER BNSF RY, 0.1 MI N SAN PABLO AVE. Standalone Bridge Preventive Maintenance. | 5928(158) | 137221.5 | 137222 | -0.5 | OK | 2025-08-13 |  |  |  | 9/2/2025 DLA-Admin: E76 process complete.
04 | Contra Costa | Metropolitan Transportation Commission | Contra Costa County | Yes | No | BRIDGE NO. 28C0389, FREEMAN ROAD OVER LAS TRAMPAS CREEK, 0.1 MI WEST OF STANLEY CT. Standalone Paint Bridge. | 5928(180) | 82332.9 | 82333 | -0.1 | OK | 2025-06-27 |  |  |  | 7/1/2025 DLA-Admin: E76 process complete.
04 | Contra Costa | Metropolitan Transportation Commission | Contra Costa County | No | No | BRIDGE NO. PM00159,Bridge Preventive Maintenance Program (BPMP) various bridges in Contra Costa County. See Caltrans Local Assistance HBP website for backup list of projects. | 5928(155) | 476515.3809 | 15607 | 460908.3809 | Not Obligated | 2019-12-06 |  |  | 2022-03-08 | 9/2/2025 DLA-Admin: E76 process complete.
04 | Contra Costa | Metropolitan Transportation Commission | Pinole | NHS | No | BRIDGE NO. 28C0062, SAN PABLO AVE, OVER BNSF RY AND AMTRAK, JUST W/O HERCULES AVE. Replace existing four-lane bridge with a new four-lane bridge, Chien Wu, 12/24/2015 9:57:52 AM. | 5126(015) | 177060 | 177060 | 0 | OK | 2018-03-05 |  |  | 2025-04-28 | 7/1/2025 DLA-Admin: E76 process complete.
04 | Contra Costa | Metropolitan Transportation Commission | San Pablo | No | No | BRIDGE NO. 28C0326, GIANT HWY OVER SAN PABLO CREEK, AT PARR BLVD. Preventive maintenance to include deck polyester concrete overlay and joint replacement work, Chien Wu, 3/22/2016 10:16:46 AM. | 5303(019) | 342965.22 | 342965 | 0.22 | OK | 2018-07-19 |  | 2025-08-19 | 2025-07-03 | 9/2/2025 DLA-Admin: E76 process complete.
04 | Marin | Metropolitan Transportation Commission | Fairfax | Yes | No | BRIDGE NO. 27C0008, MEADOW WAY, OVER SAN ANSELMO CREEK, IN FAIRFAX. Replace FO 1 lane timber bridge with wider 1 lane bridge. 4/5/2010: Toll Credits programmed for Con. 3/8/2019: Toll credits used for R/W. | 5277(025) | 870559.82 | 870560 | -0.18 | OK | 2009-07-16 | 2020-07-31 |  | 2025-06-04 | 2/4/2025 DLA-Admin: E76 process complete.
04 | Marin | Metropolitan Transportation Commission | Golden Gate Bridge Highway And Transportation Distri | NHS | No | GOLDEN GATE BRIDGE, Seismic Retrofit Phase 3B, Suspension bridge seismic retrofit. GGBHTD must provide MTC other funding sources for a fully funded project for FTIP purposes. | 6003(029) | 70000000 | 4270016 | 65729984 | Not Obligated | 2019-03-22 |  |  | 2025-06-23
04 | Marin | Metropolitan Transportation Commission | Novato | No | No | BRIDGE NO. 27C0021, GRANT AVE OVER NOVATO CREEK, IN NOVATO. Bridge rehabilitation no additional lanes added. | 5361(023) | 73313.4636 | 73313 | 0.4636 | OK | 2010-04-13 |  | 2023-05-02 | 2025-09-02 | 9/2/2025 DLA-Admin: E76 process complete.
04 | Marin | Metropolitan Transportation Commission | Novato | No | No | BRIDGE NO. PM00205, Bridge Preventive Maintenance Program (BPMP), various bridges in the City of Novato. See Caltrans Local Assistance HBP website for backup list of projects. | 5361(032) | 42112 | 42112 | 0 | OK | 2025-05-23 |  |  |  | 6/2/2025 DLA-Admin: E76 process complete.
04 | Marin | Metropolitan Transportation Commission | San Rafael | Yes | No | BRIDGE NO. 27C0148, SOUTHRN HEIGHTS BL, OVER HILLSIDE, JCT MEYER RD IN SAN RAFEL. Replace existing one-lane bridge with a new one-lane bridge. 3/4/2015: Toll Credits programmed for PE, R/W, & CON. | 5043(038) | 122992 | 122990 | 2 | OK | 2016-02-16 | 2018-04-18 | 2020-05-27 | 2025-08-25 | 1/2/2025 DLA-Admin: E76 process complete.
04 | Napa | Metropolitan Transportation Commission | Napa County | No | No | BRIDGE NO. 21C0075, CHILES-POPE VLY RD OVER CHILES CREEK, 2.1 MI N OF S.R. 128. Replace existing 2-lane bridge with new 2-lane bridge. | 5921(096) | 3995217.3405 | 3955376 | 39841.3405 | Not Obligated | 2016-06-30 | 2021-12-21 | 2025-06-27 | 2025-04-23 | 7/1/2025 DLA-Admin: E76 process complete.
04 | San Francisco | Metropolitan Transportation Commission | San Francisco | NHS | No | BRIDGE NO. 34C0024, THIRD STREET OVER ISLAIS CREEK, JUST N/O CARGO WAY. Rehabilitate bridge. No added lane capacity. (High Cost Project agreement required) Scope not clear. | 5934(168) | 442650 | 442650 | 0 | OK | 2013-08-30 |  |  | 2025-09-02 | 8/1/2025 DLA-Admin: E76 process complete.
04 | San Francisco | Metropolitan Transportation Commission | San Francisco County Transportation Authority | NHS | Yes | Starting on the westbound I-80 on-ramp from entrance to SFOBB to 2,000’ north of SFOBB. BRIDGE NO. 01CA0002, 01CA0006 replace with retaining walls, 01CA0003 to be replaced; and 01CA0001, 01CA0004, 01CA0007A, 01CA0007B, and 01CA0008 to be seismically retrofitted, High cost project agreement must be signed. Other Federal Funds must be shown in FTIP. | 6272(046) | 19135737.3675 | 19135737 | 0.3675 | OK | 2018-11-29 | 2020-07-29 | 2023-04-07 | 2025-08-13 | 2/4/2025 DLA-Admin: E76 process complete.
04 | San Mateo | Metropolitan Transportation Commission | South San Francisco | No | No | BRIDGE NO. PM00153, Bridge Preventive Maintenance Program (BPMP) various bridges in the City of South San Francisco. See Caltrans Local Assistance HBP website for backup list of projects. | 5177(039) | 196205.4978 | 196205 | 0.4978 | OK | 2019-11-19 |  |  | 2024-11-12 | 9/2/2025 DLA-Admin: E76 process complete.
04 | Santa Clara | Metropolitan Transportation Commission | Cupertino | No | No | BRIDGE NO. PM00132, Bridge Preventive Maintenance Program (BPMP), various bridges in the City of Cupertino. See Caltrans Local Assistance HBP web site for backup list of bridges. | 5318(029) | 605739.966 | 605740 | -0.034 | OK | 2016-09-08 |  | 2023-04-28 | 2025-05-23 | 6/2/2025 DLA-Admin: E76 process complete.
04 | Santa Clara | Metropolitan Transportation Commission | Palo Alto | No | No | BRIDGE NO. 37C0223, NEWELL RD OVER SAN FRANCISQUITO CR, NEAR WOODLAND AVE. Replace existing two-lane bridge with a new two-lane bridge conforming to current standards. | 5100(017) | 11693082.2385 | 0 | 11693082.2385 | Not Obligated | 2011-04-13 | 2020-12-17 | 2025-04-10 | 2025-04-16 | 8/27/2025 Andy Chou: Funds Reserved, waiting for transmittal to FHWA.
04 | Santa Clara | Metropolitan Transportation Commission | Santa Clara | No | No | BRIDGE NO. PM00199, Bridge Preventive Maintenance Program (BPMP), various bridges in the City of Santa Clara. See Caltrans Local Assistance HBP website for backup list of projects. | 5019(039) | 262360 | 262360 | 0 | OK | 2025-01-07 |  |  | 2025-07-28 | 2/4/2025 DLA-Admin: E76 process complete.
04 | Santa Clara | Metropolitan Transportation Commission | Santa Clara County | No | No | BRIDGE NO. 37C0094, UVAS RD, OVER UVAS CREEK, 0.6 MI S/O CROY RD. Replace 2 lane bridge with new 2 lane bridge. | 5937(123) | 385169.2416 | 385169 | 0.2416 | OK | 2009-06-03 | 2015-11-13 | 2023-01-25 | 2025-08-25 | 3/3/2025 DLA-Admin: E76 process complete.
04 | Santa Clara | Metropolitan Transportation Commission | Santa Clara County | No | No | BRIDGE NO. 37C0095, UVAS RD, OVER LITTLE UVAS CREEK, 0.2 MI N/O CROY RD. Replace 2 lane bridge with new 2 lane bridge. | 5937(124) | 460956.2334 | 460956 | 0.2334 | OK | 2009-06-16 | 2016-04-11 | 2022-06-28 | 2025-08-08 | 4/1/2025 DLA-Admin: E76 process complete.
04 | Santa Clara | Metropolitan Transportation Commission | Santa Clara County | No | No | BRIDGE NO. 37C0096, UVAS RD, OVER LLAGAS CREEK, 1.0 MI N/O OAK GLEN AV. Replace 2 lane bridge with new 2 lane bridge. | 5937(106) | 1739901.3372 | 1739901 | 0.3372 | OK | 2006-11-16 | 2015-09-16 | 2024-04-22 | 2025-08-15 | 3/3/2025 DLA-Admin: E76 process complete.
04 | Santa Clara | Metropolitan Transportation Commission | Santa Clara County | Yes | No | BRIDGE NO. 37C0159, ALAMITOS RD, OVER ALAMITOS CREEK, 0.8 MI S OF ALMADEN. Replace 2 lane bridge with new 2 lane bridge. 4/5/2010: Toll Credits programmed for R/W & Con. | 5937(228) | 1789621 | 1789621 | 0 | OK | 1999-10-01 |  | 2023-07-11 | 2025-08-01 | 7/1/2025 DLA-Admin: E76 process complete.
04 | Santa Clara | Metropolitan Transportation Commission | Santa Clara County | Yes | No | BRIDGE NO. 37C0172, NEW AVE, OVER RED FOX CREEK, 1.6 MI N LEAVESLY ROAD. Bridge Replacement 4/5/2010: Toll Credits programmed for PE & Con. 10/3/2011: Toll credits used for R/W. Replace two-lane with two-lane bridge. | 5937(182) | 200000 | 200000 | 0 | OK | 2012-03-16 | 2019-09-16 |  | 2025-08-08 | 1/2/2025 DLA-Admin: E76 process complete.
04 | Santa Clara | Metropolitan Transportation Commission | Sunnyvale | No | No | BRIDGE NO. PM00204, Bridge Preventive Maintenance Program (BPMP), various bridges in the City of Sunnyvale. See Caltrans Local Assistance HBP website for backup list of projects. | 5213(077) | 446100 | 446100 | 0 | OK | 2024-12-27 |  |  | 2025-07-03 | 1/2/2025 DLA-Admin: E76 process complete.
04 | Solano | Metropolitan Transportation Commission | Solano County | No | No | BRIDGE NO. 23C0092, STEVENSON BR RD, OVER PUTAH CREEK, SOL/YOL CO LINE. Bridge rehabilitation. No adding lane capacity. Other Federal Funds must be programmed in FTIP. | 5923(059) | 5385102.84 | 0 | 5385102.84 | Not Obligated | 2001-05-03 | 2016-12-23 |  | 2025-05-16 | 8/18/2025 Roberta Jensen: Funds Reserved, waiting for transmittal to FHWA.
04 | Solano | Metropolitan Transportation Commission | Vallejo | NHS | No | BRIDGE NO. 23C0248, G STREET, OVER NAPA RIVER, 1 MILE WEST OF SR 29. Bridge Preventive Maintenance (Painting, applying Methacrylate, piles and boards of fender system repairs, replacing anodes at Piers 26 and 27). | 5030(060) | 10936110.9 | 10936111 | -0.1 | OK | 2016-02-18 |  | 2024-06-17 | 2025-02-14 | 8/1/2025 DLA-Admin: E76 process complete.
04 | Sonoma | Metropolitan Transportation Commission | Sonoma County | No | Yes | BRIDGE NO. 20C0017, WATMAUGH ROAD, OVER SONOMA CREEK, 0.3 MI W HWY 12. Replace 2 lane bridge with new 2 lane bridge. (minor seismic contribution) | 5920(092) | 8677710.6 | 8677711 | -0.4 | OK | 2009-07-09 | 2020-10-14 | 2025-04-11 | 2025-07-28 | 5/2/2025 DLA-Admin: E76 process complete.
04 | Sonoma | Metropolitan Transportation Commission | Sonoma County | Yes | Yes | BRIDGE NO. 20C0155, WOHLER RD, OVER RUSSIAN RIVER, 1.5 MI FROM RIVER RD. LSSRP Seismic Retrofit. 11/13/2012: Toll credits used for PE. 10/18/2017: Toll credits used for R/W. | 5920(137) | 3778246.1574 | 3778246 | 0.1574 | OK | 2013-04-08 | 2019-09-09 | 2023-09-06 | 2025-07-28 | 5/2/2025 DLA-Admin: E76 process complete.
04 | Sonoma | Metropolitan Transportation Commission | Sonoma County | Yes | No | BRIDGE NO. 20C0227, GEYSERS RD, OVER FRASIER CREEK, 20.4 MI N OF ST HWY 128. Replace deficient 2-lane bridge with new 2-lane bridge meeting current geometrics standards. 9/14/2010: Toll credits for all phases. | 5920(129) | 9099750 | 9099750 | 0 | OK | 2011-06-14 | 2023-12-27 | 2025-01-30 | 2025-07-28 | 6/2/2025 DLA-Admin: E76 process complete.
04 | Sonoma | Metropolitan Transportation Commission | Sonoma County | Yes | No | BRIDGE NO. 20C0406, RIVER ROAD OVER GILL CREEK, 2.0 MI NW OF SR 128. Replace existing two-lane bridge with new two-lane bridge. Chien Wu, 3/14/2014 2:55:46 PM. 3/20/2014: Toll Credits programmed for PE, R/W, & CON. | 5920(144) | 7245400 | 391000 | 6854400 | Not Obligated | 2014-07-31 | 2022-09-22 |  | 2025-08-13 | 6/2/2025 DLA-Admin: E76 process complete.
04 | Sonoma | Metropolitan Transportation Commission | Sonoma County | Yes | No | BRIDGE NO. 20C0407, WEST DRY CREEK RD, OVER PENA CREEK, 0.7 MI NW YOAKIM BR RD. Replace one-lane bridge with two-lane bridge. Formerly LSSRP Seismic Retrofit 4/26/2010: Toll Credits programmed for PE, R/W & Con. | 5920(139) | 280500 | 280500 | 0 | OK | 2013-04-29 |  |  | 2025-07-28 | 1/2/2025 DLA-Admin: E76 process complete.
04 | Sonoma | Metropolitan Transportation Commission | Sonoma County | Yes | No | BRIDGE NO. 20C0433, KING RIDGE RD, OVER BIG AUSTIN CREEK, 2.3 MI N FORT ROSS RD. Replace one lane bridge to two-lane bridge 4/1/2010: Toll Credits programmed for PE, R/W, & Con. | 5920(146) | 350000 | 350000 | 0 | OK | 2014-09-16 | 2025-06-16 |  | 2025-07-28 | 7/1/2025 DLA-Admin: E76 process complete.
04 | Sonoma | Metropolitan Transportation Commission | Sonoma County | Yes | No | BRIDGE NO. 20C0440, FREESTONE FLAT RD OVER SALMON CREEK, 0.2 MI E BOHEMIAN HWY. Replace existing one-lane bridge with new two-lane bridge. 10/4/2010: Toll credits used for PE, RW and CON. | 5920(127) | 4425000 | 4425000 | 0 | OK | 2011-04-13 | 2021-06-07 | 2025-06-16 | 2025-08-15 | 7/1/2025 DLA-Admin: E76 process complete.
04 | Sonoma | Metropolitan Transportation Commission | Sonoma County | No | No | BRIDGE NO. PM00101, Bridge Preventive Maintenance Program (BPMP) for various bridges in the County of Sonoma. See Caltrans Local Assistance HBP website for backup list of projects. | 5920(163) | 786493.4376 | 786493 | 0.4376 | OK | 2018-05-18 |  | 2024-02-02 | 2025-08-06 | 7/1/2025 DLA-Admin: E76 process complete.
05 | Monterey | Association of Monterey Bay Area Governments | Monterey County | Yes | No | BRIDGE NO. 44C0093, MONTE RD, OVER SALINAS RIVER, 0.75 MI N DEL MONTE BLVD. Standalone Paint Project. | 5944(158) | 376252.5 | 376253 | -0.5 | OK | 2025-07-30 |  |  |  | 8/1/2025 DLA-Admin: E76 process complete.
05 | San Benito | Association of Monterey Bay Area Governments | San Benito County | No | No | BRIDGE NO. 43C0027, PANOCHE ROAD, OVER TRES PINOS CREEK, 12 MI W LITTLE PANOCHE RD. Replace 1-lane Bridge with 2-lane Bridge (satisfies seismic requirement). | 5943(056) | 572789.1 | 572789 | 0.1 | OK | 2010-09-01 | 2023-05-09 |  | 2025-08-25 | 8/1/2025 DLA-Admin: E76 process complete.
05 | San Luis Obispo | San Luis Obispo Council Of Governments | Arroyo Grande | No | No | BRIDGE NO. 49C0318, TRAFFIC WAY OVER ARROYO GRANDE CREEK, ARROYO GRANDE. Replace 3 lane bridge with 3 lane bridge | 5199(037) | 3150251.52 | 3150251 | 0.52 | OK | 2018-03-09 | 2023-01-25 | 2025-02-18 | 2025-08-25 | 5/2/2025 DLA-Admin: E76 process complete.
05 | San Luis Obispo | San Luis Obispo Council Of Governments | Atascadero | No | No | BRIDGE NO. 49C0158, VIA AVE OVER ATASCADERO CREEK, 0.12 MI E/O TRAFFIC WAY. Replacement of 2-Lane Bridge (No added lane capacity) | 5423(032) | 8853 | 0 | 8853 | Not Obligated | 2017-05-11 | 2018-11-08 | 2023-02-02 | 2025-04-11 | 3/3/2025 DLA-Admin: E76 process complete.
05 | San Luis Obispo | San Luis Obispo Council Of Governments | Atascadero | Yes | No | BRIDGE NO. 49C0164, SANTA LUCIA ROAD OVER GRAVES CREEK, LIANO RD. Replace 2-lane bridge with 2-lane bridge (no added capacity) 3/20/2014: Toll Credits programmed for PE, R/W, & CON. | 5423(029) | 144000 | 0 | 144000 | Not Obligated | 2015-03-09 | 2018-11-08 | 2022-08-08 | 2025-04-11 | 3/3/2025 DLA-Admin: E76 process complete.
05 | San Luis Obispo | San Luis Obispo Council Of Governments | El Paso De Robles | No | No | BRIDGE NO. PM00161,Bridge Preventive Maintenance Program (BPMP) various bridges in the City of Paso Robles. See Caltrans Local Assistance HBP website for backup list of projects. | 5084(019) | 80000 | 80000 | 0 | OK | 2023-11-22 |  |  | 2025-01-24 | 12/4/2024 DLA-Admin: E76 process complete.
05 | San Luis Obispo | San Luis Obispo Council Of Governments | San Luis Obispo County | Yes | No | BRIDGE NO. 49C0093, SANTA RITA OLD CR RD OVER OLD CREEK, 0.3 MI E CYPRESS MTN DR. Replace 2-lane timber bridge with 2-lane bridge. | 5949(201) | 619710 | 619710 | 0 | OK | 2025-06-13 |  |  |  | 7/1/2025 DLA-Admin: E76 process complete.
05 | San Luis Obispo | San Luis Obispo Council Of Governments | San Luis Obispo County | Yes | No | BRIDGE NO. 49C0261, MONTE RD OVER SQUIRE CREEK, 0.25 MI S/O SAN LUIS B DR. Replace 1 lane bridge with 2 lane bridge. 9/13/2016: Toll Credits programmed for PE, R/W, & CON. 10/19/2021: Toll credits for PE,R/W, and CON deleted. 7/21/2022: Toll Credits programmed for PE, R/W, & CON. | 5949(182) | 457000 | 457000 | 0 | OK | 2023-01-25 |  |  | 2025-08-13 | 8/1/2025 DLA-Admin: E76 process complete.
05 | San Luis Obispo | San Luis Obispo Council Of Governments | San Luis Obispo County | Yes | No | BRIDGE NO. 49C0342, JACK CREEK RD, OVER PASO ROBLES CREEK, 0.2 MI N STATE RTE 46. Replace 2-lane bridge with 2-lane bridge 9/28/2012: Toll Credits programmed for PE, R/W, & CON. | 5949(156) | 425000 | 425000 | 0 | OK | 2015-08-25 | 2022-03-07 | 2023-11-22 | 2025-08-08 | 4/1/2025 DLA-Admin: E76 process complete.
05 | San Luis Obispo | San Luis Obispo Council Of Governments | San Luis Obispo County | No | No | BRIDGE NO. 49C0351, SOUTH BAY BLVD OVER LOS OSOS CREEK, 2.15 MI SOUTH OF SR 1. Replacement of 2-lane bridge. No added lane capacity. | 5949(196) | 27905541.3 | 27905541 | 0.3 | OK | 2012-07-12 | 2023-01-23 | 2025-02-12 | 2025-08-06 | 5/2/2025 DLA-Admin: E76 process complete.
05 | Santa Barbara | Santa Barbara County Association Of Governments | Santa Barbara | NHS | No | BRIDGE NO. 51C0244, DE LA VINA ST, OVER MISSION CREEK, 0.1 MI N ALAMAR ST. Replace 3-lane bridge with 3-lane bridge | 5007(096) | 15354643.2 | 15354643 | 0.2 | OK | 2016-03-11 | 2021-01-21 | 2025-01-31 | 2025-02-12 | 8/1/2025 DLA-Admin: E76 process complete.
05 | Santa Barbara | Santa Barbara County Association Of Governments | Santa Barbara | Yes | No | BRIDGE NO. 51C0289, ISLAY ST OVER MISSION CREEK, AT CASTILLO ST. Replace 2-lane bridge with 2-lane bridge. | 5007(105) | 1327950 | 1327950 | 0 | OK | 2025-01-31 |  |  |  | 2/4/2025 DLA-Admin: E76 process complete.
05 | Santa Barbara | Santa Barbara County Association Of Governments | Santa Barbara | No | No | BRIDGE NO. PM00154, Bridge Preventive Maintenance Program (BPMP) various bridges in the City of Santa Barbara. See Caltrans Local Assistance HBP website for backup list of projects. | 5007(075) | 110589.9054 | 110588 | 1.9054 | OK | 2019-11-19 |  | 2024-07-01 | 2025-01-23 | 9/3/2025 DLA-Admin: E76 process complete.
05 | Santa Cruz | Association of Monterey Bay Area Governments | Santa Cruz | No | Yes | BRIDGE NO. 36C0108, MURRAY AVE, OVER WOODS LAGOON, W/O INT/O LAKE AVE. LSSRP seismic retrofit. Replace bridge rail and associated roadway improvements. (Mixed Funds.) | 5025(084) | 26297665.6371 | 26297666 | -0.3629 | OK | 2023-02-21 | 2023-02-21 | 2023-08-14 | 2024-11-12 | 8/1/2025 DLA-Admin: E76 process complete.
05 | Santa Cruz | Association of Monterey Bay Area Governments | Santa Cruz County | Yes | No | BRIDGE NO. 36C0128, RANCHO RIO AVENUE OVER NEWELL CREEK, 0.1 MI E NEWELL CREEK RD. Replace 1-lane bridge with 2-lane bridge. 6/8/2011: Toll Credits programmed for PE, R/W, & CON. | 5936(096) | 100000 | 100000 | 0 | OK | 2012-01-13 |  |  | 2024-04-25 | 3/3/2025 DLA-Admin: E76 process complete.
06 | Fresno | Council Of Fresno County Goverments | Fresno | No | No | BRIDGE NO. PM00116, Bridge Preventive Maintenance Program (BPMP), various bridges in the City of Fresno. See Caltrans Local Assistance HBP web site for backup list of bridges | 5060(372) | 498955.08 | 498955 | 0.08 | OK | 2024-08-05 |  | 2023-05-09 | 2025-06-13 | 3/3/2025 DLA-Admin: E76 process complete.
06 | Fresno | Council Of Fresno County Goverments | Fresno County | No | No | BRIDGE NO. 42C0001, NORTH FORK ROAD, OVER SAN JOAQUIN RIVER, 0.1 MI W/O FRIANT RD. Replace 2 Lane Bridge with 2 Lane Bridge | 5942(279) | 265590 | 265590 | 0 | OK | 2017-09-13 |  |  | 2025-08-08 | 8/1/2025 DLA-Admin: E76 process complete.
06 | Fresno | Council Of Fresno County Goverments | Fresno County | No | No | BRIDGE NO. 42C0067, W MANNING AVE, OVER JAMES BYPASS OVERFLOW, 3.2 MI EAST OF COLORADO. Replace 2 Lane Bridge with 2 Lane Bridge | 5942(233) | 108726.3489 |  | 108726.3489 | Not Obligated |  |  |  |  | 7/1/2025 DLA-Admin: E76 process complete.
06 | Fresno | Council Of Fresno County Goverments | Fresno County | Yes | No | BRIDGE NO. 42C0078, LOST HILLS AVE, OVER JACALITOS CREEK, JACALITOS CREEK RD. Replace 2 Lane Bridge with 2 Lane Bridge 10/14/2013: Toll Credits programmed for PE, R/W, & CON. | 5942(234) | 4930000 | 4930000 | 0 | OK | 2014-05-05 | 2018-04-13 | 2024-09-23 | 2025-07-03 | 4/1/2025 DLA-Admin: E76 process complete.
06 | Fresno | Council Of Fresno County Goverments | Fresno County | Yes | No | BRIDGE NO. 42C0097, S EL DORADO AVE, OVER ARROYO PASAJERO, 2.0 MI NORTH OF JAYNE AVE. Replace 2 lane bridge with 2 lane bridge. 9/15/2015: Toll Credits programmed for PE, R/W, & CON. | 5942(271) | 285000 | 285000 | 0 | OK | 2016-06-23 | 2024-05-13 |  | 2025-03-14 | 5/2/2025 DLA-Admin: E76 process complete.
06 | Fresno | Council Of Fresno County Goverments | Fresno County | Yes | No | BRIDGE NO. 42C0413, E LINCOLN AVE, OVER TRAVERS CREEK, 0.5 MI EAST OF ALTA AVE. Replace 2 lane bridge with 2 lane bridge. Toll Credits programmed for PE, R/W, & Con. | 5942(226) | 438784 | 438784 | 0 | OK | 2013-06-28 | 2015-06-30 | 2024-06-03 | 2025-09-02 | 2/4/2025 DLA-Admin: E76 process complete.
06 | Fresno | Council Of Fresno County Goverments | Fresno County | Yes | No | BRIDGE NO. 42C0417, E PARLIER AVE, OVER TRAVERS CREEK, 0.2 MI E ENGLEHART AVE. Replace 2 lane bridge with 2 lane bridge. 4/1/2010: Toll Credits programmed for PE, R/W, & Con. | 5942(227) | 193832 | 193832 | 0 | OK | 2013-07-02 | 2017-03-17 | 2024-06-03 | 2025-08-25 | 8/1/2025 DLA-Admin: E76 process complete.
06 | Fresno | Council Of Fresno County Goverments | Fresno County | Yes | No | BRIDGE NO. 42C0486, N CHATEAU FRESNO OVER HOUGHTON CANAL, 0.5 MI SOUTH OF BELMONT. Replace 2 lane bridge with 2 lane bridge 3/4/2014: Toll Credits programmed for PE, R/W, & CON. | 5942(237) | 4303081 | 4303081 | 0 | OK | 2014-07-21 | 2015-07-28 | 2025-03-05 | 2025-05-21 | 8/1/2025 DLA-Admin: E76 process complete.
06 | Kern | Kern County Council Of Governments | Bakersfield | NHS | Yes | BRIDGE NO. 50C0021 L & R, MANOR ST, OVER KERN RIVER, 0.2 MI S ROBERTS LANE. Rehabilitate 2 lane bridge as 2 lane bridge. No added lane capacity. Including LSSRP retrofit funds. | 5109(166) | 6110584.0575 | 6110584 | 0.0575 | OK | 2011-08-03 |  | 2018-06-27 | 2025-09-02 | 7/1/2025 DLA-Admin: E76 process complete.
06 | Madera | Madera County Transportation Commission | Madera County | Yes | No | BRIDGE NO. 41C0123, SCHOOL RD 427, OVER OAK CREEK, 0.1 MI E RD 418. Replace 2 lane bridge with 2 lane bridge. Toll Credits programmed for PE, R/W. & Con. Other Federal Funds (HIP) must be shown in FTIP. | 5941(081) | 7822170 | 7822170 | 0 | OK | 2010-09-14 | 2021-03-25 | 2025-01-22 | 2025-04-23 | 9/2/2025 DLA-Admin: E76 process complete.
06 | Madera | Madera County Transportation Commission | Madera County | Yes | No | BRIDGE NO. 41C0149, AVENUE 16.5 OVER DRY CREEK, AT ROAD 19. Replace 2 lane bridge with 2 lane bridge - Toll Credits programmed for PE, R/W & CON. Other Federal Funds (HIP) must be shown in the FTIP. | 5941(089) | 2932335 | 2932335 | 0 | OK | 2011-08-22 | 2019-03-11 | 2025-08-11 | 2025-06-23 | 9/2/2025 DLA-Admin: E76 process complete.
06 | Madera | Madera County Transportation Commission | Madera County | Yes | No | BRIDGE NO. 41C0162, C.R. 210 OVER RYAN CREEK, 4.0 MI E OF CR 211. Replace 1 lane bridge with 2 lane bridge. Not capacity increasing project. 10/24/2014: Toll Credits programmed for PE & CON. 8/3/2021: Toll credits used for R/W. | 5941(103) | 297500 | 297500 | 0 | OK | 2015-04-01 |  |  | 2025-04-23 | 4/1/2025 DLA-Admin: E76 process complete.
06 | Tulare | Tulare County Association Of Governments | Tulare County | Yes | No | BRIDGE NO. 46C0004, CO RD D112, OVER NORTH BRANCH TULE RIVER, 1.1 MI N OF AVE 160. Replace 2 Lane Bridge with a 2 Lane Bridge 3/12/2012: Toll Credits programmed for PE, R/W, & CON. | 5946(138) | 41093 |  | 41093 | Not Obligated |  |  |  |  | 1/2/2025 DLA-Admin: E76 process complete.
06 | Tulare | Tulare County Association Of Governments | Tulare County | No | No | BRIDGE NO. 46C0013, ROAD D112, OVER BATES SLOUGH, SOUTH OF AVE 196. Replace 2 Lane Bridge with 2 Lane Bridge | 5946(139) | 36039.6777 |  | 36039.6777 | Not Obligated |  |  |  |  | 1/2/2025 DLA-Admin: E76 process complete.
06 | Tulare | Tulare County Association Of Governments | Tulare County | No | No | BRIDGE NO. 46C0025, AVE 152, OVER TULE RIVER, 1.25 MI W OF RD 224. Replace 2 Lane Bridge with 4 Lane Bridge. | 5946(180) | 306400 | 306400 | 0 | OK | 2022-01-24 |  |  | 2025-09-02 | 8/1/2025 DLA-Admin: E76 process complete.
06 | Tulare | Tulare County Association Of Governments | Tulare County | Yes | No | BRIDGE NO. 46C0300, AVE 108, OVER LAKELAND CANAL, 0.5 MI E OF SR 43. Replace 1 Lane Bridge with 2 Lane Bridge 3/12/2012: Toll Credits programmed for PE, R/W, & CON. | 5946(141) | 229848 |  | 229848 | Not Obligated |  |  |  |  | 4/1/2025 DLA-Admin: E76 process complete.
06 | Tulare | Tulare County Association Of Governments | Tulare County | Yes | No | BRIDGE NO. 46C0340, AVE 428, OVER SAND CREEK, 0.25 MI E OF SR 63. Replace 2 Lane Bridge with 2 Lane Bridge 3/12/2012: Toll Credits programmed for PE, R/W, & CON. | 5946(142) | 2400000 | 2400000 | 0 | OK | 2016-05-13 | 2022-07-01 | 2025-03-27 | 2025-08-01 | 7/1/2025 DLA-Admin: E76 process complete.
07 | Los Angeles | Los Angeles County Metropolitan Transportation Auth. | Long Beach | NHS | No | BRIDGE NO. 53C0209, 2ND ST OVER MARINE STADIUM & APPIAN, 0.3 MI W/O PACFC CST HWY. Bridge Rehabilitation. Rehabilitation, replace concrete deck and barrier rail. (No added capacity) | 5108(197) | 1239420 | 1239420 | 0 | OK | 2020-12-28 |  |  | 2025-02-21 | 2/4/2025 DLA-Admin: E76 process complete.
07 | Los Angeles | Los Angeles County Metropolitan Transportation Auth. | Los Angeles | NHS | No | BRIDGE NO. 53C0011, SOTO STREET, OVER VALLEY BLVD/SPTCO, 0.6 MI NORTH OF I-10. Rehabilitate 4-lane bridge & widen to include shoulders, add sidewalk, and upgrade bridge railings. No added lane capacity. | 5006(193) | 301002 | 301002 | 0 | OK | 2000-11-14 | 2002-08-25 | 2017-08-23 | 2025-08-25 | 3/3/2025 DLA-Admin: E76 process complete.
07 | Los Angeles | Los Angeles County Metropolitan Transportation Auth. | Los Angeles | No | No | BRIDGE NO. PM00123, Bridge Preventive Maintenance Program (BPMP), various bridges in the City of Los Angeles. See Caltrans Local Assistance HBP web site for backup list of bridges | 5006(838) | 948147.447 | 948147 | 0.447 | OK | 2016-06-09 |  | 2025-06-13 | 2021-09-14 | 7/1/2025 DLA-Admin: E76 process complete.
07 | Los Angeles | Los Angeles County Metropolitan Transportation Auth. | Los Angeles | NHS | Yes | Glendale Blvd.- Hyperion Ave complex of bridges over LA River, I-5 and Riverside Drive, rehabilitation / seismic retrofit; upgrade bridge railing; includes bridges 53C1881, 53C1882, 53C1883, 53C1884. No additional lanes. Realign I-5 north bound off ramp. High cost project agreement required. | 5006(337) | 19999999.9836 | 0 | 19999999.9836 | Not Obligated | 2002-09-05 | 2015-05-28 | 2022-09-13 | 2025-05-23
07 | Los Angeles | Los Angeles County Metropolitan Transportation Auth. | Los Angeles County | No | No | Federally mandated Inspection Program. Los Angeles County inspection of local agency owned bridges withing LA County (except LA City bridges). State pays match. | 5953(811) | 2965249.4937 | 2965249 | 0.4937 | OK |  |  |  | 2025-08-08 | 7/1/2025 DLA-Admin: E76 process complete.
07 | Los Angeles | Los Angeles County Metropolitan Transportation Auth. | Pasadena | Yes | No | BRIDGE NO. 53C0757, SAN RAFAEL AVE OVER ARROYO SECO CHANNEL, 100FT W/O ARROYO BLVD. Voluntary seismic retrofit. | 5064(101) | 639186.6 | 639186 | 0.6 | OK | 2024-11-26 |  |  | 2025-05-02 | 7/1/2025 DLA-Admin: E76 process complete.
07 | Los Angeles | Los Angeles County Metropolitan Transportation Auth. | Santa Monica | Yes | No | BRIDGE NO. 53C1900, COLORADO AVE OVER APPIAN WAY/PROMENDAE, 0.6 MI W/O LINCOLN BLVD. Replace existing 2 lane bridge with new 2 lane bridge. 3/14/2011: Toll Credits programmed for PE & CON. 10/25/2016: Toll credits used for R/W. | 5107(033) | 25721250 | 25721250 | 0 | OK | 2012-03-16 |  | 2025-04-04 | 2025-08-27 | 7/1/2025 DLA-Admin: E76 process complete.
07 | Ventura | Ventura County Transportation Commission | San Buena Ventura | NHS | No | BRIDGE NO. 52C0064, VICTORIA AVE OVER UP RR & AMTRAK, 0.2 MI S OF ROUTE 101. Voluntary seismic retrofit. | 5026(075) | 280800 | 280800 | 0 | OK | 2025-07-30 |  |  |  | 8/1/2025 DLA-Admin: E76 process complete.
07 | Ventura | Ventura County Transportation Commission | San Buena Ventura | NHS | No | BRIDGE NO. 52C0248, TELEPHONE RD, OVER UP RR & AMTRAK, 0.8 MI S OF MAIN ST. Voluntary seismic retrofit. | 5026(074) | 169600 | 169600 | 0 | OK | 2025-07-30 |  |  |  | 8/1/2025 DLA-Admin: E76 process complete.
07 | Ventura | Ventura County Transportation Commission | San Buena Ventura | No | No | BRIDGE NO. PM00202, Bridge Preventive Maintenance Program (BPMP), various bridges in the City of Ventura. See Caltrans Local Assistance HBP website for backup list of projects. | 5026(076) | 473414.175 | 473414 | 0.175 | OK | 2025-08-15 |  |  |  | 9/2/2025 DLA-Admin: E76 process complete.
08 | Riverside | Riverside County Transportation Commission | Coachella | NHS | No | BRIDGE NO. 00L0055, AVENUE 50 OVER COACHELLA STORMWATER CHANNEL, (aka Whitewater River). Replace existing 2 lane low water crossing with 6 lane bridge. (Capacity increasing). High Cost project agreement required. | NBIL(536) | 3780673.65 | 0 | 3780673.65 | Not Obligated | 2014-09-19 | 2022-07-14 |  | 2025-08-13
08 | Riverside | Riverside County Transportation Commission | Indio | No | No | BRIDGE NO. 00L0056, AVENUE 44 low water crossing OVER the Coachella Valley Stormwater Channel. Replace existing two lane low water crossing with a four lane bridge. Capacity increasing project. | 5275(024) | 16363110.5625 | 16363111 | -0.4375 | OK | 2013-03-26 | 2017-08-24 | 2023-09-15 | 2025-06-13 | 3/3/2025 DLA-Admin: E76 process complete.
08 | Riverside | Riverside County Transportation Commission | La Quinta | No | No | BRIDGE NO. PM00201 Bridge Preventive Maintenance Program (BPMP), various bridges in the City of La Quinta. See Caltrans Local Assistance HBP website for backup list of projects. | 5433(022) | 560800 | 560800 | 0 | OK | 2025-01-22 |  |  | 2025-09-02 | 2/4/2025 DLA-Admin: E76 process complete.
08 | Riverside | Riverside County Transportation Commission | Palm Springs | No | No | BRIDGE NO. 56C0025, INDIAN CANYON DRIVE, OVER UP RR & AMTRAK, 0.6 MI S OF I-10. Replace 2 lane bridge with new 6 lane bridge. Other federal funds must be programed in the SCAG FTIP. | 5282(017) | 13173772.1622 | 13173772 | 0.1622 | OK | 2001-05-01 | 2014-04-22 | 2020-06-09 | 2025-08-01 | 5/2/2025 DLA-Admin: E76 process complete.
08 | Riverside | Riverside County Transportation Commission | Riverside County | No | No | BRIDGE NO. 56C0020, AIRPORT BOULEVARD OVER WHITEWATER RIVER, 0.21 MI. E/O RTE. 111 HWY. Replace existing two lane bridge with two lane bridge, with a center turn lane, not capacity increasing. | 5956(231) | 12745664.1 | 0 | 12745664.1 | Not Obligated | 2013-08-30 | 2024-02-14 |  | 2025-08-13
08 | Riverside | Riverside County Transportation Commission | Riverside County | NHS | No | BRIDGE NO. 56C0024, MARKET STREET OVER SANTA ANA RIVER, 0.4 MI NW OF SR 60. Replace existing 2 lane bridge with 4 lane bridge, capacity increasing. (High cost project agreement required) | 5956(200) | 912744.3 | 0 | 912744.3 | Not Obligated | 2012-03-26 | 2021-03-25 |  | 2025-07-16
08 | Riverside | Riverside County Transportation Commission | Riverside County | No | Yes | BRIDGE NO. 56C0071, MSSN BL/BUENA VST, OVER SANTA ANA RIVER, 1.47 MI W/O SH 91 ON 7TH. Combined funding of LSSRP Seismic Retrofit and HBP funds for the replacement project (High cost project agreement required). Replace existing 4 lane bridge with 4 lane bridge. | 5956(192) | 23368566.4836 | 23368567 | -0.5164 | OK | 2010-07-07 | 2019-09-13 | 2025-08-07 | 2025-07-16 | 8/1/2025 DLA-Admin: E76 process complete.
08 | Riverside | Riverside County Transportation Commission | Riverside County | No | No | BRIDGE NO. PM00076, Bridge Preventive Maintenance Program, various locations in Riverside County. See Caltrans Local Assistance HBP web site for backup list of bridges. | 5956(224) | 4899037.728 | 4899037 | 0.728 | OK | 2013-08-30 |  | 2025-07-28 | 2025-06-18 | 8/1/2025 DLA-Admin: E76 process complete.
08 | Riverside | Riverside County Transportation Commission | Twenty-Nine Palms Band of Mission Indians | NHS | No | BRIDGE NO. 56C0318, DILLON ROAD OVER WHITEWATER RIVER, 0.12 MI. SE/O SR 86S. Replace 2-lane bridge with 6-lane bridge. Capacity increasing and high cost bridge project. RTP ID 2016A319. Other Federal funds must be programmed in FTIP. High cost agreement required. Scope not clear. | 7302(001) | 1200000 |  | 1200000 | Not Obligated |  |  |  |  | 8/27/2025 Andy Chou: Funds Reserved, waiting for transmittal to FHWA.
08 | San Bernardino | San Bernardino Associated Governments | Apple Valley | NHS | No | BRIDGE NO. 54C0086, BEAR VALLEY RD OVER MOJAVE RIVER, 5 MI E RTE I-15. Bridge Rehabilitation, no added capacity. High Cost project agreement required. Other Federal Funds must be shown in the FTIP. | 5453(018) | 19999999.9836 | 19999999.9836 | 0 | OK | 2013-06-12 | 2018-08-11 | 2025-05-29 | 2025-05-14 | 6/3/2025 DLA-Admin: E76 process complete.
08 | San Bernardino | San Bernardino Associated Governments | Barstow | No | Yes | BRIDGE NO. 54C0089 & 54C0090, N 1ST AVENUE OVER MOJAVE RIVER AND MOJAVE OVERFLOW, 1.4 MI N/O RTE 15. Replace existing 2 lane bridges with 2 lane bridges, existing bridges to be removed. (minor seismic retrofit funds for 54C0089 only), High Cost project agreement required. | 5298(031) | 6074187.6039 | 6074188 | -0.3961 | OK | 2014-08-15 | 2021-06-15 |  | 2024-11-22 | 9/2/2025 DLA-Admin: E76 process complete.
08 | San Bernardino | San Bernardino Associated Governments | Colton | No | Yes | BRIDGE NO. 54C0077, LA CADENA DR OVER SANTA ANA RIVER, 1.5 MI SOUTH OF I-10. Replace existing 4-lane bridge with 4-lane bridge with minor seismic funds. | 5065(014) | 12729657.876 | 0 | 12729657.876 | Not Obligated | 2012-04-13 | 2018-12-10 |  | 2025-08-15
08 | San Bernardino | San Bernardino Associated Governments | Colton | NHS | Yes | BRIDGE NO. 54C0100, MT VERNON AVE, OVER SANTA ANA RIVER, 0.6 MI S'LY OF RTE I-10. LSSRP Seismic Retrofit | 5065(017) | 361999.17 | 361999 | 0.17 | OK | 2012-03-13 |  |  | 2024-11-19 | 5/2/2025 DLA-Admin: E76 process complete.
08 | San Bernardino | San Bernardino Associated Governments | Colton | NHS | Yes | BRIDGE NO. 54C0101, MT VERNON AVE OVER UP RR & AMTRAK, 0.1 MI S/O I-10. Bridge Rehabilitation, widen from two lanes to four lanes with shoulders and sidewalk (Mixed funding with LSSRP) (Capacity increasing must be in RTP). | 5065(023) | 10616074.95 | 1193385 | 9422689.95 | Not Obligated | 2012-05-08 | 2019-05-24 |  | 2024-11-22 | 8/1/2025 DLA-Admin: E76 process complete.
08 | San Bernardino | San Bernardino Associated Governments | Highland | NHS | No | BRIDGE NO. 54C0592, ORANGE ST OVER PLUNGE CREEK OVERFLOW, 1.5 MI N OF PIONEER AVE. Replace existing two lane bridge with four lane bridge. | 5449(034) | 239031 | 239031 | 0 | OK | 2015-05-08 |  |  | 2025-04-11 | 8/1/2025 DLA-Admin: E76 process complete.
08 | San Bernardino | San Bernardino Associated Governments | San Bernardino County | No | No | BRIDGE NO. 54C0025, GLEN HELEN PKWY, OVER CAJON WASH, .6 MI S OF ROUTE I-215. Replace 2 lane bridge with 4 lane bridge. High cost agreement required, | 5954(108) | 19999999.9836 | 20000000 | -0.0164 | OK | 2012-09-12 | 2012-09-12 | 2024-09-10 | 2025-05-23 | 8/1/2025 DLA-Admin: E76 process complete.
08 | San Bernardino | San Bernardino Associated Governments | San Bernardino County | No | No | BRIDGE NO. 54C0272, NAT TRAILS HWY OVER BRISTOL DITCH, 26.7 MI E CRUCERO RD. Replace existing 2-lane bridge with 2-lane bridge. | 5954(147) | 2948934.3 | 2948934 | 0.3 | OK | 2017-07-06 |  | 2025-04-16 | 2025-01-23 | 5/2/2025 DLA-Admin: E76 process complete.
08 | San Bernardino | San Bernardino Associated Governments | San Bernardino County | No | No | BRIDGE NO. 54C0275, NAT TRAILS HWY OVER CERRO DITCH, 1.3 MI E OF AMBOY RD. Replace existing 2-lane bridge with 2-lane bridge. | 5954(149) | 1511207.1 | 1511207 | 0.1 | OK | 2017-07-06 |  | 2025-04-17 | 2025-05-07 | 5/2/2025 DLA-Admin: E76 process complete.
08 | San Bernardino | San Bernardino Associated Governments | San Bernardino County | No | No | BRIDGE NO. 54C0276, NAT TRAILS HWY OVER GORDO DITCH, 1.8 MI E OF AMBOY RD. Replace existing 2-lane bridge with 2-lane bridge. | 5954(150) | 1535995.5 | 1535995 | 0.5 | OK | 2017-07-06 |  | 2025-04-17 | 2025-05-09 | 5/2/2025 DLA-Admin: E76 process complete.
08 | San Bernardino | San Bernardino Associated Governments | San Bernardino County | No | No | BRIDGE NO. 54C0277, NAT TRAILS HWY OVER CERULIA DITCH, 2.2 MI E OF AMBOY RD. Replace existing 2-lane bridge with new 2-lane bridge. | 5954(151) | 1515633.6 | 1515633 | 0.6 | OK | 2017-07-06 |  | 2025-04-11 | 2025-05-09 | 5/2/2025 DLA-Admin: E76 process complete.
08 | San Bernardino | San Bernardino Associated Governments | San Bernardino County | No | No | BRIDGE NO. 54C0279, NAT TRAILS HWY OVER LEITH DITCH, 3.1 MI E OF AMBOY RD. Replace the existing 2-lane bridge with new 2-lane bridge. | 5954(152) | 1523601.3 | 1523600 | 1.3 | OK | 2017-07-06 |  | 2025-04-17 | 2025-05-07 | 5/2/2025 DLA-Admin: E76 process complete.
08 | San Bernardino | San Bernardino Associated Governments | San Bernardino County | No | No | BRIDGE NO. 54C0280, NAT TRAILS HWY OVER TERRA DITCH, 3.6 MI E OF AMBOY RD. Replace existing 2-lane bridge with new 2-lane bridge. | 5954(153) | 2117637.6 | 2117637 | 0.6 | OK | 2017-07-06 |  | 2025-04-24 | 2025-05-07 | 5/2/2025 DLA-Admin: E76 process complete.
08 | San Bernardino | San Bernardino Associated Governments | San Bernardino County | No | No | BRIDGE NO. 54C0281, NAT TRAILS HWY OVER SOMBRA DITCH, 4.1 MI E OF AMBOY RD. Replace existing 2-lane bridge with 2-lane bridge. | 5954(154) | 3078188.1 | 3078188 | 0.1 | OK | 2017-07-06 | 2024-07-18 | 2025-04-21 | 2025-01-23 | 5/2/2025 DLA-Admin: E76 process complete.
08 | San Bernardino | San Bernardino Associated Governments | San Bernardino County | No | No | BRIDGE NO. 54C0282, NAT TRAILS HWY OVER BEACON DITCH, 6.2 MI E OF AMBOY RD. Replace existing 2-lane bridge with 2-lane bridge. | 5954(155) | 1816413.3897 | 1816413 | 0.3897 | OK | 2017-07-06 |  | 2025-04-21 | 2025-05-07 | 5/2/2025 DLA-Admin: E76 process complete.
08 | San Bernardino | San Bernardino Associated Governments | San Bernardino County | No | No | BRIDGE NO. 54C0284, NAT TRAILS HWY OVER LARISSA DITCH, 1.1 MI E KELBAKER RD. Replace existing 2-lane bridge with 2-lane bridge. | 5954(156) | 1821503.8647 | 1821504 | -0.1353 | OK | 2017-07-06 |  | 2025-04-21 | 2025-05-07 | 5/2/2025 DLA-Admin: E76 process complete.
08 | San Bernardino | San Bernardino Associated Governments | San Bernardino County | No | No | BRIDGE NO. 54C0315, NAT TRAILS HWY OVER ADENA DITCH, 21.9 MI E KELBAKER RD. Replace existing 2 lane bridge with new 2 lane bridge. | 5954(142) | 1987319.6694 | 1987320 | -0.3306 | OK | 2016-06-01 | 2024-06-27 | 2025-04-11 | 2025-08-15 | 5/2/2025 DLA-Admin: E76 process complete.
08 | San Bernardino | San Bernardino Associated Governments | San Bernardino County | No | No | BRIDGE NO. 54C0670, ROCK SPRINGS ROAD OVER MOJAVE RIVER, .9 MI E ARROWHEAD LK RD. Replace 2 lane bridge with 2 lane bridge. This project has limited HBP eligiblity. | 5954(135) | 8173532.25 | 8173532 | 0.25 | OK |  | 2019-09-19 | 2025-04-28 | 2025-08-08 | 5/2/2025 DLA-Admin: E76 process complete.
08 | San Bernardino | San Bernardino Associated Governments | Victorville | NHS | No | BRIDGE NO. 54C0547, BEAR VALLEY ROAD, OVER BNSF RY, AMTRAK, & UP RR, 3.8 MI E OF ROUTE I-15. Widen 6 lane bridge to 7 lanes (median turn lane) and seismically retrofitting existing bridge. | 5380(026) | 1430290.68 | 0 | 1430290.68 | Not Obligated | 2010-07-08 | 2016-04-26 | 2020-06-09 | 2025-06-23 | 8/27/2025 Andy Chou: Funds Reserved, waiting for transmittal to FHWA.
09 | Inyo | Statewide Planning and Non MPO Regions | Inyo County | Yes | No | BRIDGE NO. 48C0011, CARROLL CRK RD OVER LOS ANGELES AQUEDUCT, 0.4 MI W OF RTE 395 JCT. Bridge replacement. No adding lane capacity. 9/3/2010: Toll Credits programmed for PE & CON. 9/20/2012: Toll credits used for R/W. | 5948(074) | 2450000 | 0 | 2450000 | Not Obligated | 2011-05-23 | 2019-04-05 |  | 2025-08-01
09 | Inyo | Statewide Planning and Non MPO Regions | Inyo County | Yes | No | BRIDGE NO. 48C0039, WALKER CREEK RD OVER LOS ANGELES AQUEDUCT, 0.5 MI W OF RTE 395 JCT. Replace existing one lane bridge with two lane bridge. 9/8/2010: Toll Credits programmed for PE, R/W & CON. | 5948(076) | 742442 | 742442 | 0 | OK | 2011-05-17 | 2019-04-19 | 2023-06-29 | 2025-07-28 | 5/2/2025 DLA-Admin: E76 process complete.
10 | Calaveras | Statewide Planning and Non MPO Regions | Calaveras County | Yes | No | BRIDGE NO. 30C0050, DOGTOWN ROAD OVER INDIAN CREEK, 6.5 MI. N/O SR49. Replace one-lane bridge with a standard 2-lane bridge. No added lane capacity. 9/23/2010: Toll Credits programmed for PE, R/W, & CON. | 5930(063) | 2016000 | 0 | 2016000 | Not Obligated | 2011-05-18 | 2018-06-15 |  | 2025-04-23 | 8/25/2025 Jesus Serrano: E76 received and under eligibility review in District.
10 | Mariposa | Statewide Planning and Non MPO Regions | Mariposa County | Yes | No | BRIDGE NO. 40C0036, BUCKEYE ROAD OVER MARIPOSA CREEK, 2.3 MI S/O OLD HWY. Replace existing 2-lane bridge with standard 2-lane bridge width (No Added Lane Capacity). 7/25/2013: Toll Credits programmed for PE, R/W, & CON. | 5940(118) | 2380000 | 0 | 2380000 | Not Obligated | 2015-04-07 | 2019-05-07 |  | 2024-05-30 | 1/3/2025 Jesus Serrano: E76 received and under eligibility review in District.
10 | Merced | Merced County Association Of Goverments | Merced County | Yes | No | BRIDGE NO 39C0217, JORGENSEN RD OVER OUTSIDE CANAL, 0.5 MI W OF WHITWORTH RD. Replace 2-lane bridge with a standard 2-lane bridge. 9/7/2011: Toll Credits programmed for PE, R/W, & CON. | 5939(082) | 2263750 | 2263750 | 0 | OK | 2012-02-16 | 2018-04-26 | 2025-04-28 | 2025-07-03 | 5/2/2025 DLA-Admin: E76 process complete.
10 | Merced | Merced County Association Of Goverments | Merced County | Yes | No | BRIDGE NO. 39C0114, COTTONWOOD ROAD OVER OUTSIDE CANAL, 0.5 MI. E/O ORCHARD ROAD. Replace 2-lane bridge with a standard 2-lane bridge. 10/8/2013: Toll Credits programmed for PE, R/W, & CON. | 5939(100) | 514000 | 514000 | 0 | OK | 2014-05-05 | 2025-04-03 |  | 2025-08-01 | 5/2/2025 DLA-Admin: E76 process complete.
10 | Merced | Merced County Association Of Goverments | Merced County | Yes | No | BRIDGE NO. 39C0275, ARROYA AVENUE OVER WEST DELTA CANAL, 0.9 MI. N/O SR 152. Replace one-lane bridge with a standard 2-lane bridge. No added lane capacity. 10/8/2013: Toll Credits programmed for PE, R/W, & CON. | 5939(103) | 1891350 | 1891350 | 0 | OK | 2014-07-21 | 2022-05-06 | 2025-04-03 | 2025-08-01 | 5/2/2025 DLA-Admin: E76 process complete.
10 | Merced | Merced County Association Of Goverments | Merced County | Yes | No | BRIDGE NO. 39C0286, ATWATER JORDAN ROAD OVER ATWATER CANAL, 0.3 MI. W/O CENTRAL AVENUE. Replace existing 2-lane bridge. 10/8/2013: Toll Credits programmed for PE, R/W, & CON. | 5939(101) | 125000 | 125000 | 0 | OK | 2014-05-05 |  |  | 2025-08-01 | 2/4/2025 DLA-Admin: E76 process complete.
10 | Merced | Merced County Association Of Goverments | Merced County | Yes | No | BRIDGE NO.39C0319, QUINLEY AVENUE OVER BLACK RASCAL CREEK, 0.6 MI S/O SR 140. Replace 2-lane bridge with a new 2-lane bridge. 2/24/2015: Toll Credits programmed for PE, R/W, & CON. | 5939(107) | 7244000 | 7244000 | 0 | OK | 2015-06-03 | 2020-01-14 | 2025-04-11 | 2025-08-01 | 5/2/2025 DLA-Admin: E76 process complete.
10 | San Joaquin | San Joaquin County Council Of Goverments | Lathrop | No | No | BRIDGE NO. 29C0127, MANTHEY ROAD OVER SAN JOAQUIN RIVER, 0.3 MI NE OF STEWART RD. Replace 2-lane bridge with a standard 2-lane bridge wide enough to accommodate shoulders, bike lanes, and sidewalks. Caltrans/City High Cost Project Agreement is required to program CON federal funds within 4-year element of FTIP. | 5456(016) | 350000 | 350000 | 0 | OK | 2013-03-29 |  |  | 2022-09-01 | 6/2/2025 DLA-Admin: E76 process complete.
10 | San Joaquin | San Joaquin County Council Of Goverments | San Joaquin County | No | No | BRIDGE NO. 29C0131, WALNUT GROVE ROAD OVER MOKELUMNE RIVER, AT SJ AND SAC COUNTY LINE. Replace 2-lane bridge with a standard 2-lane bridge. High Cost Project Agreement required. | 5929(239) | 177060 | 136394 | 40666 | Not Obligated | 2011-11-21 |  |  | 2025-07-30 | 8/1/2025 DLA-Admin: E76 process complete.
10 | San Joaquin | San Joaquin County Council Of Goverments | San Joaquin County | Yes | No | BRIDGE NO. 29C0199, PEZZI ROAD OVER CALAVERAS RIVER, 0.8 MI S/O EIGHT MILE RD. Replace 2-lane bridge with a standard 2-lane bridge. 3/8/2011: Toll Credits programmed for PE & CON. | 5929(240) | 609000 | 609000 | 0 | OK | 2011-12-09 |  |  | 2025-07-03 | 9/2/2025 DLA-Admin: E76 process complete.
10 | San Joaquin | San Joaquin County Council Of Goverments | San Joaquin County | Yes | No | BRIDGE NO. 29C0274, MESSICK ROAD OVER MOSHER CREEK, 0.6 MI W/O CLEMENTS ROAD. Replace 2-lane timber bridge with a standard 2-lane bridge. 10/5/2012: Toll Credits programmed for PE & CON. | 5929(254) | 1064000 | 1064000 | 0 | OK | 2013-04-12 |  |  | 2025-06-23 | 7/1/2025 DLA-Admin: E76 process complete.
10 | San Joaquin | San Joaquin County Council Of Goverments | San Joaquin County | Yes | No | BRIDGE NO. 29C0292, COTTA ROAD OVER UPLAND CANAL, 1.0 MI W OF I-5. Replace 2-lane bridge with a standard 2-lane bridge. 3/8/2011: Toll Credits programmed for PE & CON. | 5929(234) | 1538750 | 1538750 | 0 | OK | 2011-11-09 |  | 2025-05-27 | 2025-05-09 | 6/2/2025 DLA-Admin: E76 process complete.
10 | San Joaquin | San Joaquin County Council Of Goverments | San Joaquin County | Yes | No | BRIDGE NO. 29C0319, SEXTON ROAD OVER S. SAN JOAQUIN IRRIGATION DISTRICT CANAL, 0.2 MI N/O RIVER ROAD. Replace 2-lane bridge with a new 2-lane bridge. 3/11/2011: Toll Credits programmed for PE & CON. | 5929(242) | 1241400 | 1241400 | 0 | OK | 2011-12-12 |  | 2023-03-14 | 2025-05-21 | 2/4/2025 DLA-Admin: E76 process complete.
10 | San Joaquin | San Joaquin County Council Of Goverments | San Joaquin County | Yes | No | BRIDGE NO. 29C0413, BOLLEA ROAD OVER BEAR CREEK, NEAR CALAVERAS COUNTY LINE. Replace 2-lane bridge with a standard 2-lane bridge. 3/11/2011: Toll Credits programmed for PE & CON. | 5929(236) | 3856541 | 3856541 | 0 | OK | 2011-11-09 |  | 2024-08-30 | 2025-08-15 | 7/1/2025 DLA-Admin: E76 process complete.
10 | San Joaquin | San Joaquin County Council Of Goverments | San Joaquin County | No | No | BRIDGE NO. PM00215, Bridge Preventive Maintenance Program (BPMP), various bridges in San Joaquin County. See Caltrans Local Assistance HBP website for backup list of projects. | 5929(340) | 952019.2 | 952019 | 0.2 | OK | 2025-02-03 |  |  | 2025-07-30 | 3/3/2025 DLA-Admin: E76 process complete.
10 | San Joaquin | San Joaquin County Council Of Goverments | San Joaquin County | No | No | PM00031, Bridge Preventive Maintenance Program, various locations within San Joaquin County. See Caltrans Local Assistance HBP web site for backup list of bridges. | 5929(292) | 5550864.6414 | 5550864 | 0.6414 | OK | 2013-05-24 |  | 2025-02-20 | 2025-07-30 | 8/1/2025 DLA-Admin: E76 process complete.
10 | San Joaquin | San Joaquin County Council Of Goverments | Stockton | No | No | PM00040, Bridge Preventive Maintenance Program, various locations within the City of Stockton. See Caltrans Local Assistance HBP website for backup list of bridges. | 5008(220) | 1750229.247 | 1750229 | 0.247 | OK | 2025-05-12 |  | 2025-05-29 | 2025-08-27 | 6/2/2025 DLA-Admin: E76 process complete.
10 | Stanislaus | Stanislaus Area Association Of Governments | Patterson | No | No | BRIDGE NO. 38C0214, ROGERS ROAD OVER DELTA-MENDOTA CANAL, 0.5 MI N/O SPERRY AVE. Replace existing 2-lane bridge with a wider 2-lane bridge (Not Capacity Increasing). | 5244(032) | 619931.325 | 619931 | 0.325 | OK | 2015-07-20 | 2023-04-26 |  | 2025-06-23 | 9/2/2025 DLA-Admin: E76 process complete.
10 | Stanislaus | Stanislaus Area Association Of Governments | Stanislaus County | No | Yes | BRIDGE NO. 38C0010, CROWS LANDING ROAD OVER SAN JOAQUIN RIVER, NEAR W. CARPENTER RD. Bridge replacement with limted LSSRP Seismic Retrofit funds. High cost agreement required. | 5938(076) | 4243905.9897 | 4243906 | -0.0103 | OK | 1998-04-01 | 2013-09-24 | 2019-12-12 | 2025-07-03 | 6/2/2025 DLA-Admin: E76 process complete.
10 | Stanislaus | Stanislaus Area Association Of Governments | Stanislaus County | No | No | BRIDGE NO. 38C0023, SEVENTH STREET OVER TUOLUMNE RIVER. Replace historic 2-lane bridge with a new 4-lane bridge with median (Added Lane Capacity). Caltrans/City High Cost Project Agreement is required to program CON federal funds within 4 year element of MTIP. Project must appear in 20 year RTP. Other Federal funds must be programmed in the FTIP for this project. | 5938(167) | 1018378.296 | 1018378 | 0.296 | OK | 2010-08-06 | 2020-09-16 | 2025-08-15 | 2025-09-02 | 9/2/2025 DLA-Admin: E76 process complete.
10 | Stanislaus | Stanislaus Area Association Of Governments | Stanislaus County | Yes | No | BRIDGE NO. 38C0073, TIM BELL ROAD OVER DRY CREEK, 0.8 MI. S/O CLARIBEL ROAD. Replace historic 2-lane bridge with a standard 2-lane bridge. 9/14/2010: Toll Credits programmed for PE & CON. 1/27/2016: Toll credits used for R/W. | 5938(189) | 18854692 | 18854692 | 0 | OK | 2011-07-08 | 2022-01-04 | 2024-08-22 | 2025-09-02 | 6/3/2025 DLA-Admin: E76 process complete.
10 | Stanislaus | Stanislaus Area Association Of Governments | Stanislaus County | Yes | No | BRIDGE NO. 38C0170, COOPERSTOWN ROAD OVER GALLUP CREEK, 2.8 MI. NW/O LA GRANGE ROAD. Replace 2-lane bridge with a standard 2-lane bridge. 9/21/2010: Toll Credits programmed for PE & CON. 7/23/2013: Toll credits used for R/W. | 5938(191) | 350000 | 132000 | 218000 | Not Obligated | 2011-07-13 | 2023-01-27 |  | 2025-07-24 | 8/22/2025 Roberta Jensen: Funds Reserved, waiting for transmittal to FHWA.
10 | Stanislaus | Stanislaus Area Association Of Governments | Stanislaus County | No | No | BRIDGE NO. 38C0231, MILTON ROAD OVER ROCK CREEK TRIBUTARY, 3.7 MI. N/O SR 4. Replace 2-lane bridge with a standard 2-lane bridge. | 5938(201) | 305428.5 | 305429 | -0.5 | OK | 2012-04-11 | 2023-09-12 |  | 2025-05-23 | 2/4/2025 DLA-Admin: E76 process complete.
10 | Stanislaus | Stanislaus Area Association Of Governments | Stanislaus County | No | No | BRIDGE NO. PM00185, Bridge Preventive Maintenance Program (BPMP) various bridges in Stanislaus County. See Caltrans Local Assistance HBP website for backup list of projects. | 5938(277) | 486411.2 | 486411 | 0.2 | OK | 2024-04-18 |  |  | 2025-07-28 | 7/1/2025 DLA-Admin: E76 process complete.
10 | Tuolumne | Statewide Planning and Non MPO Regions | Tuolumne County | Yes | No | BRIDGE NO. 32C0003, WARDS FERRY ROAD OVER DEER CREEK, 4.95 MI N OF GROVELAND. Replace one-lane bridge with a one-lane bridge. 2/21/2013: Toll Credits programmed for PE, R/W, & CON. | 5932(091) | 463837 | 0 | 463837 | Not Obligated | 2016-11-14 |  |  | 2025-08-01 | 8/27/2025 Andy Chou: Funds Reserved, waiting for transmittal to FHWA.
10 | Tuolumne | Statewide Planning and Non MPO Regions | Tuolumne County | Yes | No | BRIDGE NO. 32C0016, LIME KILN ROAD OVER CURTIS CREEK, 2.8 MI. S/O CAMPO SECO ROAD. Replace one-lane bridge with a standard 2-lane bridge. No added lane capacity. 9/27/2010: Toll Credits programmed for PE, RW & CON. | 5932(067) | 3406038 | 3406038 | 0 | OK | 2012-03-14 | 2017-11-20 | 2025-02-10 | 2025-08-13 | 3/3/2025 DLA-Admin: E76 process complete.
10 | Tuolumne | Statewide Planning and Non MPO Regions | Tuolumne County | Yes | No | BRIDGE NO. 32C0017, OLD WARDS FERRY ROAD OVER CURTIS CREEK, 3.3 MI S/O SANGUINETTI RD. Replace one-lane bridge with a standard 2-lane bridge. No added lane capacity. 10/5/2012: Toll Credits programmed for PE, R/W, & CON. | 5932(095) | 285675 | 50000 | 235675 | Not Obligated | 2017-11-27 |  |  | 2025-08-01 | 8/27/2025 Andy Chou: Funds Reserved, waiting for transmittal to FHWA.
10 | Tuolumne | Statewide Planning and Non MPO Regions | Tuolumne County | Yes | No | BRIDGE NO. 32C0037, ITALIAN BAR ROAD OVER ROSE CREEK, 10.7 MI. NE/O BIG HILL ROAD. Replace one-lane bridge with a wider one-lane bridge (No Added Lane Capacity). 9/27/2010: Toll Credits programmed for PE, R/W, & CON. | 5932(073) | 135860 | 135860 | 0 | OK | 2013-07-19 | 2019-09-11 |  | 2025-02-19 | 9/2/2025 DLA-Admin: E76 process complete.
10 | Tuolumne | Statewide Planning and Non MPO Regions | Tuolumne County | Yes | No | BRIDGE NO. 32C0073, ALGERINE ROAD OVER ALGERINE CREEK, 0.4 MI. N/O TWIST RD. Replace existing 2-lane bridge; Widen to standard 2-lane width (No Added Lane Capacity). 10/28/2013: Toll Credits programmed for PE, R/W, & CON. | 5932(096) | 285162 | 0 | 285162 | Not Obligated | 2017-11-27 |  |  | 2025-07-28 | 8/19/2025 Roberta Jensen: Funds Reserved, waiting for transmittal to FHWA.
11 | San Diego | San Diego Association Of Governments | Chula Vista | No | No | BRIDGE NO. 57C0670, HERITAGE ROAD, OVER OTAY RIVER, 1.9 MI E/O RTE I-805. Bridge Replacement. Replace 4 lane bridge to 6 lane bridge that accommodates shoulders, sidewalks and median. (Other federal funds on project, must also be programmed in FSTIP.) | 5203(039) | 21444281.9448 | 20999720 | 444561.9448 | Not Obligated | 2015-05-08 | 2017-11-17 | 2024-07-01 | 2025-06-23 | 7/1/2025 DLA-Admin: E76 process complete.
11 | San Diego | San Diego Association Of Governments | Del Mar | No | No | BRIDGE NO. 57C0209, CAMINO DEL MAR, OVER SAN DIEGUITO RIVER, 0.35 MI S VIA DE LA VALLE. Bridge replacement. No adding travelled lanes. High cost project agreement required. | 5356(008) | 885300 | 885300 | 0 | OK | 2017-05-30 | 2024-06-17 |  | 2025-06-18 | 7/1/2025 DLA-Admin: E76 process complete.
11 | San Diego | San Diego Association Of Governments | Escondido | Yes | No | BRIDGE NO. 57C0070, SUNSET DRIVE OVER BOLAS CREEK, 400FT S/O VIA RNCHO PKWY. Standalone Paint Bridge. |  | 17706 |  | 17706 | Not Obligated
11 | San Diego | San Diego Association Of Governments | Oceanside | No | Yes | BRIDGE NO. 57C0322, HILL ST, OVER SAN LUIS REY RIVER, 0.3 MI S OCNSIDE HRBOR DR Replace existing two lane bridge with two lane bridge. Originally LSSRP Seismic Retrofit. 7/23/2013: Toll credits used for PE and CON. 9/25/2014: Toll credits used for R/W. High cost project agreement needs to be signed for this project. 8/25/2021: Toll credits for R/W deleted. Toll credits for CON deleted. | 5079(030) | 2212795 | 0 | 2212795 | Not Obligated | 2013-09-17 |  |  | 2025-06-13
11 | San Diego | San Diego Association Of Governments | San Diego | No | No | BRIDGE NO. 57C0042, EL CAMINO REAL, OVER SAN DIEGUITO RIVER, 0.3 MI S VIA DE LA VALLE. Replace 2 lane bridge with 4 lane bridge. SANDAG to allocate Regional Surface Transportation funds in the FTIP. Funds shown are HBP only. High Cost Project Agreement is required to program CON federal funds within 4 year element of MTIP. | 5004(068) | 183412.8 | 183218 | 194.8 | OK | 1998-01-12 | 1998-01-12 |  | 2025-07-09 | 9/2/2025 DLA-Admin: E76 process complete.
11 | San Diego | San Diego Association Of Governments | San Diego | NHS | No | BRIDGE NO. 57C0420R, FAIRMOUNT AVE OVER ALDINE DRIVE, 1.2 MI S OF RTE 8. Rehabilitation of a two lane bridge. (no added capcity) | 5004(198) | 211586.7 | 211586 | 0.7 | OK | 2017-03-13 |  |  | 2025-05-07 | 8/1/2025 DLA-Admin: E76 process complete.
12 | Orange | Orange County Transportation Authority | Huntington Beach | Yes | No | BRIDGE NO. 55C0284, HUMBOLDT DRIVE OVER SHORT CHANNEL, 0.1 MI W/O SAYBROOK LN. Rehabilitate bridge. (no added lanes). 4/5/2010: Toll Credits programmed for PE & Con. 3/19/2019: Toll credits used for R/W. | 5181(175) | 2814000 | 2814000 | 0 | OK | 2012-05-09 |  | 2025-08-06 | 2023-04-20 | 9/2/2025 DLA-Admin: E76 process complete.
12 | Orange | Orange County Transportation Authority | Orange | No | No | BRIDGE NO. PM00086, Bridge Preventive Maintenance Program (BPMP) various bridges in the City of Orange. See Caltrans Local Assistance HBP website for backup list of projects. | 5073(077) | 1014625.5093 | 1014625 | 0.5093 | OK | 2014-05-01 |  | 2024-04-19 | 2025-02-14 | 6/2/2025 DLA-Admin: E76 process complete.
12 | Orange | Orange County Transportation Authority | Orange County | Yes | No | BRIDGE NO. 55C0174, SILVERADO CNYN RD. OVER SILVERADO CANYON CREEK, 1.6 MI E/O SANTIAGO ROAD. Replace existing two lane bridge with two lane bridge. 3/14/2013: Toll Credits programmed for PE & CON. FPN BRLO-5955 (095), Adv. Proj. ID 1215000151 | 5955(095) | 1622600 | 0 | 1622600 | Not Obligated | 2016-08-30 |  |  | 2024-01-19
12 | Orange | Orange County Transportation Authority | Orange County | Yes | No | BRIDGE NO. 55C0175, SILVERADO CANYN RD OVER LADD CANYON, 2.2 MI. E/O SANTIAGO ROAD. Bridge replacement project. Replace 2 lane bridge with 2 lane bridge (no added capacity). 2/14/2013: Toll Credits programmed for PE & CON. | 5955(087) | 264750 | 264750 | 0 | OK | 2014-03-04 |  |  | 2021-11-09 | 8/1/2025 DLA-Admin: E76 process complete.
12 | Orange | Orange County Transportation Authority | Placentia | No | No | BRIDGE NO. 55C0192, GOLDEN AVENUE OVER CARBON CANYON CHANNEL, 0.2 MI W/O ROSE DRIVE. Bridge Replacement. Replace existing 2 lane bridge with 2 lane bridge. Other Federal Funds must be shown in FTIP. | 5269(025) | 2647047 | 2647047 | 0 | OK | 2016-08-19 |  | 2025-07-17 | 2020-09-09 | 8/1/2025 DLA-Admin: E76 process complete.
12 | Orange | Orange County Transportation Authority | Santa Ana | No | No | BRIDGE NO. PM00187, Bridge Preventive Maintenance Program (BPMP), various bridges in the City of Santa Ana. See Caltrans Local Assistance HBP website for backup list of projects. | 5063(220) | 245600 | 245600 | 0 | OK | 2025-04-24 |  |  |  | 5/2/2025 DLA-Admin: E76 process complete.
|  | # of Projects: | 228 |  |  |  | Grand Totals: | 730197920.5106 | 539615258.9836 | 190582661.527

## Current Year Summary
District/MPO Summaries | Federal Funds Programmed | HBP Funds Obligated | Unobligated HBP Balance | % Obligated | # of Projects
| Sum of FFY 24/25 Federal Funds Programmed | HBP Funds Obligated | Unobligated HBP Balance | Sum of Percent Obligated | Count of District
01
Statewide Planning and Non MPO Regions | 12082655.7 | 11410426 | 672229.7 | 94.44% | 23
Total | 12082655.7 | 11410426 | 672229.7 | 94.44% | 23
02
Shasta County Regional Transportation Planning Agency | 1326478.0033 | 1151187 | 175291.0033 | 86.79% | 8
Statewide Planning and Non MPO Regions | 2816558.1441 | 1672674 | 1143884.1441 | 59.39% | 10
Total | 4143036.1474 | 2823861 | 1319175.1474 | 68.16% | 18
03
Statewide Planning and Non MPO Regions | 29248157 | 22712115 | 6536042 | 77.65% | 12
Butte County Association Of Governments | 11276553.325 | 11276548 | 5.325 | 100% | 5
Sacramento Area Council Of Governments | 68711230.6531 | 54001732 | 14709498.6531 | 78.59% | 23
Total | 109235940.9781 | 87990395 | 21245545.9781 | 80.55% | 40
04
Metropolitan Transportation Commission | 166647026.3988 | 74478804 | 92168222.3988 | 44.69% | 34
Total | 166647026.3988 | 74478804 | 92168222.3988 | 44.69% | 34
05
Association of Monterey Bay Area Governments | 27346707.2371 | 27346708 | -0.7629 | 100% | 4
San Luis Obispo Council Of Governments | 32790355.82 | 32637502 | 152853.82 | 99.53% | 8
Santa Barbara County Association Of Governments | 16793183.1054 | 16793181 | 2.1054 | 100% | 3
Total | 76930246.1625 | 76777391 | 152855.1625 | 99.8% | 15
06
Council Of Fresno County Goverments | 11023968.4289 | 10915242 | 108726.4289 | 99.01% | 8
Madera County Transportation Commission | 11052005 | 11052005 | 0 | 100% | 3
Tulare County Association Of Governments | 3013380.6777 | 2706400 | 306980.6777 | 89.81% | 5
Kern County Council Of Governments | 6110584.0575 | 6110584 | 0.0575 | 100% | 1
Total | 31199938.1641 | 30784231 | 415707.1641 | 98.67% | 17
07
Los Angeles County Metropolitan Transportation Auth. | 51814255.5243 | 31814254 | 20000001.5243 | 61.4% | 7
Ventura County Transportation Commission | 923814.175 | 923814 | 0.175 | 100% | 3
Total | 52738069.6993 | 32738068 | 20000001.6993 | 62.08% | 10
08
Riverside County Transportation Commission | 77004368.9863 | 58365287 | 18639081.9863 | 75.79% | 9
San Bernardino Associated Governments | 99481207.9209 | 75898565.9836 | 23582641.9373 | 76.29% | 19
Total | 176485576.9072 | 134263852.9836 | 42221723.9236 | 76.08% | 28
10
Statewide Planning and Non MPO Regions | 8972572 | 3591898 | 5380674 | 40.03% | 7
Merced County Association Of Goverments | 12038100 | 12038100 | 0 | 100% | 5
San Joaquin County Council Of Goverments | 17089864.0884 | 17049197 | 40667.0884 | 99.76% | 10
Stanislaus Area Association Of Governments | 25878747.3107 | 25660747 | 218000.3107 | 99.16% | 7
Total | 63979283.3991 | 58339942 | 5639341.3991 | 91.19% | 29
11
San Diego Association Of Governments | 24955082.4448 | 22279824 | 2675258.4448 | 89.28% | 6
Total | 24955082.4448 | 22279824 | 2675258.4448 | 89.28% | 6
12
Orange County Transportation Authority | 8608622.5093 | 6986022 | 1622600.5093 | 81.15% | 6
Total | 8608622.5093 | 6986022 | 1622600.5093 | 81.15% | 6
09
Statewide Planning and Non MPO Regions | 3192442 | 742442 | 2450000 | 23.26% | 2
Total | 3192442 | 742442 | 2450000 | 23.26% | 2
Grand Total | 730197920.5106 | 539615258.9836 | 190582661.527 | 73.9% | 228

## Off System Summary
District/MPO Summaries | Yes | HBP Funds Obligated | Unobligated HBP Balance | % Obligated | # of Projects
| Sum of FFY 24/25 Federal Funds Programmed | HBP Funds Obligated | Unobligated HBP Balance | Sum of Percent Obligated | Count of District
01
Statewide Planning and Non MPO Regions | 10642799.9 | 9970571 | 672228.9 | 93.68% | 20
Total | 10642799.9 | 9970571 | 672228.9 | 93.68% | 20
02
Shasta County Regional Transportation Planning Agency | 387761.4 | 212472 | 175289.4 | 54.79% | 2
Statewide Planning and Non MPO Regions | 2007286.5 | 863402 | 1143884.5 | 43.01% | 7
Total | 2395047.9 | 1075874 | 1319173.9 | 44.92% | 9
03
Sacramento Area Council Of Governments | 38038580 | 31218455 | 6820125 | 82.07% | 10
Statewide Planning and Non MPO Regions | 29248157 | 22712115 | 6536042 | 77.65% | 12
Butte County Association Of Governments | 3407433.1 | 3407430 | 3.1 | 100% | 2
Total | 70694170.1 | 57338000 | 13356170.1 | 81.11% | 24
04
Metropolitan Transportation Commission | 28381623.3774 | 21527222 | 6854401.3774 | 75.85% | 12
Total | 28381623.3774 | 21527222 | 6854401.3774 | 75.85% | 12
05
Association of Monterey Bay Area Governments | 476252.5 | 476253 | -0.5 | 100% | 2
San Luis Obispo Council Of Governments | 1645710 | 1501710 | 144000 | 91.25% | 4
Santa Barbara County Association Of Governments | 1327950 | 1327950 | 0 | 100% | 1
Total | 3449912.5 | 3305913 | 143999.5 | 95.83% | 7
06
Council Of Fresno County Goverments | 10150697 | 10150697 | 0 | 100% | 5
Madera County Transportation Commission | 11052005 | 11052005 | 0 | 100% | 3
Tulare County Association Of Governments | 2670941 | 2400000 | 270941 | 89.86% | 3
Total | 23873643 | 23602702 | 270941 | 98.87% | 11
07
Los Angeles County Metropolitan Transportation Auth. | 26360436.6 | 26360436 | 0.6 | 100% | 2
Total | 26360436.6 | 26360436 | 0.6 | 100% | 2
10
Statewide Planning and Non MPO Regions | 8972572 | 3591898 | 5380674 | 40.03% | 7
San Joaquin County Council Of Goverments | 8309691 | 8309691 | 0 | 100% | 5
Stanislaus Area Association Of Governments | 19204692 | 18986692 | 218000 | 98.86% | 2
Merced County Association Of Goverments | 12038100 | 12038100 | 0 | 100% | 5
Total | 48525055 | 42926381 | 5598674 | 88.46% | 19
11
San Diego Association Of Governments | 17706 |  | 17706 | 0% | 1
Total | 17706 |  | 17706 | 0% | 1
12
Orange County Transportation Authority | 4701350 | 3078750 | 1622600 | 65.49% | 3
Total | 4701350 | 3078750 | 1622600 | 65.49% | 3
09
Statewide Planning and Non MPO Regions | 3192442 | 742442 | 2450000 | 23.26% | 2
Total | 3192442 | 742442 | 2450000 | 23.26% | 2
Grand Total | 222234186.3774 | 189928291 | 32305895.3774 | 85.46% | 110

## NHS Summary
District/MPO Summaries | No | HBP Funds Obligated | Unobligated HBP Balance | % Obligated | # of Projects
| Sum of FFY 24/25 Federal Funds Programmed | HBP Funds Obligated | Unobligated HBP Balance | Sum of Percent Obligated | Count of District
01
Statewide Planning and Non MPO Regions | 1439855.8 | 1439855 | 0.8 | 100% | 3
Total | 1439855.8 | 1439855 | 0.8 | 100% | 3
02
Shasta County Regional Transportation Planning Agency | 938716.6033 | 938715 | 1.6033 | 100% | 6
Statewide Planning and Non MPO Regions | 809271.6441 | 809272 | -0.3559 | 100% | 3
Total | 1747988.2474 | 1747987 | 1.2474 | 100% | 9
03
Sacramento Area Council Of Governments | 21443150.6531 | 13553777 | 7889373.6531 | 63.21% | 12
Butte County Association Of Governments | 7869120.225 | 7869118 | 2.225 | 100% | 3
Total | 29312270.8781 | 21422895 | 7889375.8781 | 73.09% | 15
04
Metropolitan Transportation Commission | 37573844.7539 | 17990008 | 19583836.7539 | 47.88% | 17
Total | 37573844.7539 | 17990008 | 19583836.7539 | 47.88% | 17
05
Association of Monterey Bay Area Governments | 26870454.7371 | 26870455 | -0.2629 | 100% | 2
San Luis Obispo Council Of Governments | 31144645.82 | 31135792 | 8853.82 | 99.97% | 4
Santa Barbara County Association Of Governments | 110589.9054 | 110588 | 1.9054 | 100% | 1
Total | 58125690.4625 | 58116835 | 8855.4625 | 99.98% | 7
06
Council Of Fresno County Goverments | 873271.4289 | 764545 | 108726.4289 | 87.55% | 3
Tulare County Association Of Governments | 342439.6777 | 306400 | 36039.6777 | 89.48% | 2
Total | 1215711.1066 | 1070945 | 144766.1066 | 88.09% | 5
07
Los Angeles County Metropolitan Transportation Auth. | 3913396.9407 | 3913396 | 0.9407 | 100% | 2
Ventura County Transportation Commission | 473414.175 | 473414 | 0.175 | 100% | 1
Total | 4386811.1157 | 4386810 | 1.1157 | 100% | 3
08
Riverside County Transportation Commission | 71110951.0363 | 58365287 | 12745664.0363 | 82.08% | 6
San Bernardino Associated Governments | 66833812.1373 | 54104151 | 12729661.1373 | 80.95% | 14
Total | 137944763.1736 | 112469438 | 25475325.1736 | 81.53% | 20
10
San Joaquin County Council Of Goverments | 8780173.0884 | 8739506 | 40667.0884 | 99.54% | 5
Stanislaus Area Association Of Governments | 6674055.3107 | 6674055 | 0.3107 | 100% | 5
Total | 15454228.3991 | 15413561 | 40667.3991 | 99.74% | 10
11
San Diego Association Of Governments | 24725789.7448 | 22068238 | 2657551.7448 | 89.25% | 4
Total | 24725789.7448 | 22068238 | 2657551.7448 | 89.25% | 4
12
Orange County Transportation Authority | 3907272.5093 | 3907272 | 0.5093 | 100% | 3
Total | 3907272.5093 | 3907272 | 0.5093 | 100% | 3
Grand Total | 315834226.191 | 260033844 | 55800382.191 | 82.33% | 96