## LIST_HSIPdelayed
Highway Safety Improvement Program (HSIP) Delivery Status Report for Delayed Projects
Sorted by Caltrans District and Agency, Status as of 1/4/2022
Columns A to L are General Project Information, M to Q are Actual Project Delivery Information, and R to T are Delivery Milestone Status. Please see notes on the other spreadsheet of this file.
Unique Project ID | Cycle | Project Number | District | Agency | County | MPO | RTPA | Project Location | Description of Work | Total Cost ($) | HSIP Funds ($) | PE Auth Date | ROW Auth Date | CON Auth Date | Closed out Date | Obligated /Allocated Amt ($) | Milestone Status (PE) | Milestone Status (CON) | Delayed?
H9-02-001 | 9 | 0 | 2 | Lassen County | Lassen County | RURAL | Lassen LTC | On Janesville Grade, County Road 208, at eight (8) locations. | Upgrade heavily damaged W-Beam type guard railing with wood posts (mainly due to snowplowing activities and logging truck traffic) to Midwest Guardrail System with metal posts and mitigate exposed ends with proper termination ends. | 496300 | 456300 | 0 | 0 | 0 | 0 | 0 | No PE | Past due (due 12/31/2021) | Yes (CON)
H9-02-002 | 9 | 5068062 | 2 | Redding | Shasta County | SRTA | Shasta RTPA | Nine (9) intersections. | Install enhanced pedestrian crossings, including Rectangular Rapid Flashing Beacons (RRFBs), traffic signs, stripes, pavement markings, pedestrian refuge islands, and construct curb ramps. | 1273200 | 1273200 | 2019-09-10 | 0 | 0 | 0 | 216000 | Authorized | Past due (due 12/31/2021) | Yes (CON)
HSIP7-02-003 | 7 | 5906128 | 2 | Shasta County | Shasta County | SRTA | Shasta RTPA | Riverland Drive from Knighton Road to 2 miles south in the unincorporated area of Shasta County | Widen existing roadway by paving shoulders | 1163000 | 1046700 | 2016-01-26 | 0 | 0 | 0 | 121500 | Authorized | Past due (due 12/31/2021) | Yes (CON)
H8-02-004 | 8 | 5905118 | 2 | Trinity County | Trinity County | RURAL | Trinity LTC | Nineteen (19) locations throughout Trinity County. | Update Bridge Rail Approach Terminal End Systems (2,690 lineal feet of guardrail and 67 terminal end treatments). | 981000 | 981000 | 2017-10-13 | 0 | 0 | 0 | 169131 | Authorized | Past due (due 12/31/2021) | Yes (CON)
H8-02-005 | 8 | 5905119 | 2 | Trinity County | Trinity County | RURAL | Trinity LTC | Various locations on Rush Creek Road. | Install High Friction Surface Treatments | 1147900 | 1147900 | 2018-02-05 | 0 | 0 | 0 | 120000 | Authorized | Past due (due 12/31/2021) | Yes (CON)
H9-03-001 | 9 | 5912114 | 3 | Butte County | Butte County | BCAG | BCAG | Cohasset Rd between Nicalog Rd and end of existing guardrail near Jack Rabbit Flat Rd. | Update existing guardrail. | 1000000 | 1000000 | 2019-07-17 | 0 | 0 | 0 | 100000 | Authorized | Past due (due 12/31/2021) | Yes (CON)
H10-03-008 | 10 | 0 | 3 | Elk Grove | Sacramento County | SACOG | SACOG | 76 signalized intersections in the City of Elk Grove. | Provide advanced dilemma zone detection for signalized intersection approached with posted speeds of 40 MPH or higher. Replace 8 inch signal heads with 12 inch, and add retro-reflective borders to all signal heads. | 8830200 | 8830200 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2021) | Due by 9/30/2024 | Yes (PE)
HSIP7-03-010 | 7 | 5015028 | 3 | Placerville | El Dorado County | SACOG | El Dorado LTC | In El Dorado County, in the City of Placerville, along Broadway from the intersection at Main Street eastward to approximately 1500 Broadway. | Construct sidewalk | 1066470 | 959810 | 2016-07-11 | 0 | 0 | 0 | 226070 | Authorized | Past due (due 11/30/2021) | Yes (CON)
H10-03-020 | 10 | 0 | 3 | Rancho Cordova | Sacramento County | SACOG | SACOG | On Peter A Mccuen Boulevard adjacent to VA Northern Medical Center and four intersections along Zinfandel Dr and Cordova Lane adjacent to Cordova Lane Center School. | Improve pedestrian crossings with curb extensions, accessible curb ramps, high visibility crosswalks, and advanced pavement markings. | 242400 | 242400 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2021) | Due by 9/30/2024 | Yes (PE)
H9-03-020 | 9 | 5924245 | 3 | Sacramento County | Sacramento County | SACOG | SACOG | Coyle Avenue from Woodleigh Drive to Dewey Drive, Hillsdale Boulevard from Frizell Avenue to McCloud Drive, and Watt Avenue from Elkhorn Boulevard to 700' north of Elkhorn Boulevard. | Install street lighting. | 2510000 | 2510000 | 2019-06-10 | 0 | 0 | 0 | 418100 | Authorized | Past due (due 12/31/2021) | Yes (CON)
H9-03-023 | 9 | 5924248 | 3 | Sacramento County | Sacramento County | SACOG | SACOG | Intersection of Roseville Road with Diablo Drive/Stationers Way | Signalize the intersection. | 1180100 | 982700 | 2019-06-10 | 0 | 0 | 0 | 147100 | Authorized | Past due (due 12/31/2021) | Yes (CON)
H9-03-026 | 9 | 5447047 | 3 | West Sacramento | Yolo County | SACOG | SACOG | Various signalized and non-signalized intersections. | Install approach medians and medians to prohibit left turns. | 324000 | 291600 | 2019-10-11 | 0 | 0 | 0 | 50121 | Authorized | Past due (due 12/31/2021) | Yes (CON)
H9-03-029 | 9 | 5447050 | 3 | West Sacramento | Yolo County | SACOG | SACOG | Various locatoins including Reuter/Andrews, Poplar/Westfield Village ES, Carrie Street/Bryte Park, Quail-Columbus Shared Use Path, and Columbus/La Jolla at Stonegate ES. | Install striping for high-visibility crossings and stop bars, install RRFBs and signage, and construct ADA Curb Ramps, and curb extensions. | 187800 | 187800 | 2019-09-06 | 0 | 0 | 0 | 44980 | Authorized | Past due (due 12/31/2021) | Yes (CON)
H10-04-005 | 10 | 0 | 4 | Benicia | Solano County | MTC | MTC | Kearney Street at Rose Drive, Kearney Street at Mid-Block Crossing, Hastings Drive at Southhampton Road and Military West at W 3rd Street. | Install high-visibility crosswalks, advance yield limit lines, signage, RRFB systems, ADA compliant ramps, and bulb-outs. | 249900 | 249900 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2021) | Due by 9/30/2024 | Yes (PE)
H10-04-018 | 10 | 0 | 4 | Hayward | Alameda County | MTC | MTC | Intersections of Huntwood Avenue/Industrial Parkway and Huntwood Avenue/Sandoval Way. | Install protected left-turn phase at Huntwood/Industrial; install protected-permissive left-turn phase at Huntwood/Sandoval; install Hybrid Video Detection for bikes and queue cutters; and upgrade Peer-to-Peer Communication. | 861000 | 774900 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2021) | Due by 9/30/2024 | Yes (PE)
H9-04-027 | 9 | 0 | 4 | San Jose | Santa Clara County | MTC | MTC | Monterey Road from Cottle Road to Metcalf Road | Upgrade guardrails that are damaged and not up to current standards. | 1002800 | 1000000 | 0 | 0 | 0 | 0 | 0 | No PE | Past due (due 12/31/2021) | Yes (CON)
H10-04-039 | 10 | 0 | 4 | Santa Clara County | Santa Clara County | MTC | MTC | Foothill Expressway, Lawrence Expressway, and San Tomas Expressway. | Replace existing metal beam guardrail end treatments with modern variants and increase heights to meet current standards. | 999200 | 999200 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2021) | Due by 3/31/2024 | Yes (PE)
H10-04-040 | 10 | 0 | 4 | Solano County | Solano County | MTC | MTC | Suisun Valley Rd & Ledgewood Rd, Suisun Valley Rd & Rockville Rd, and Rockville Rd & Abernathy Rd (roundabout). | Install high-visibility crosswalks, truncated domes, dikes, advance warning signs, and ADA ramps. | 489800 | 250000 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2021) | Due by 9/30/2024 | Yes (PE)
H10-04-041 | 10 | 0 | 4 | South San Francisco | San Mateo County | MTC | MTC | 6 Unsignalized Intersections along Olive Avenue, Linden Avenue, and Walnut Avenue: Lux Ave & Walnut Ave, Linden Ave & 9th Ln, Linden Ave & 8th Ln, Olive Ave & Aspen Ave, Olive Ave & Pine Ave, Park Way & Walnut Ave. | Improve pedestrian safety by bringing the existing non-ADA compliant curb ramps up to current standards and installation of new high visibility crosswalks. | 249800 | 249800 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2021) | Due by 3/31/2024 | Yes (PE)
H10-04-048 | 10 | 0 | 4 | Windsor | Sonoma County | MTC | MTC | Intersection of Brooks Road South with Natalie Drive. | Install rectangular rapid flashing beacon (RRFB), construct pedestrian refuge median, curb extension, curb ramps, lane transition/traffic calming median, restripe bike lanes and vehicle lanes and slurry seal. | 240600 | 240600 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2021) | Due by 9/30/2024 | Yes (PE)
H9-05-009 | 9 | 5951169 | 5 | Santa Barbara County | Santa Barbara County | SBCAG | SBCAG | Various locations in the unincorporated areas of Santa Barbara County. | Upgrade a total of 3,073 feet "Tuthill" rail to current standard guardrail at 9 different locations on County of Santa Barbara roads. | 215800 | 215800 | 0 | 0 | 0 | 0 | 0 | No PE | Past due (due 12/31/2021) | Yes (CON)
HSIP2-05-011 | 2 | 6090059 | 5 | Santa Barbara County Association of Governments | Santa Barbara County | SBCAG | SBCAG | Cabrillo Blvd, 0.1 Mile South Of Highway 1 | Replace Existing Rr Bridge And Construct Roadway Improvements For Bicyclists And Pedestrians. | 7127700 | 900000 | 2014-11-18 | 0 | 0 | 0 | 900000 | Authorized | Past due (due 12/17/2020) | Yes (CON)
H9-06-002 | 9 | 0 | 6 | Bakersfield | Kern County | KCOG | KCOG | Calloway Drive in front of Norris Middle School at existing crosswalk near Manhattan Drive; Monitor Street in front of Palla Elementary School at existing crosswalk near Kyner Avenue. | Install flashing yellow beacons near crosswalks. | 246100 | 246100 | 0 | 0 | 0 | 0 | 0 | No PE | Past due (due 12/31/2021) | Yes (CON)
H10-06-001 | 10 | 0 | 6 | Bakersfield | Kern County | KCOG | KCOG | Old Farm Road in front of existing Veterans Elementary School at existing crosswalk near Cherry Valley Avenue, and Mountain Vista Drive in front of existing Earl Warren Junior High School at existing crosswalk near Mount Snow Lane. | Install flashing yellow beacons near existing crosswalks to enhance visibility and slow down vehicular traffic. | 246100 | 246100 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2021) | Due by 3/31/2024 | Yes (PE)
H10-06-002 | 10 | 0 | 6 | Bakersfield | Kern County | KCOG | KCOG | Intersection of Beale Avenue and Monterey Street and intersection of Beale Avenue and Niles Street. | Install signal poles/controller equipment. | 586000 | 586000 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2021) | Due by 3/31/2024 | Yes (PE)
H9-06-009 | 9 | 5942294 | 6 | Fresno County | Fresno County | FCOG | FCOG | The intersection of Ashlan Ave. and Palm Ave. | Upgrade existing 2-phase fixed timed traffic signal to 8-phase to include, but not limited to, left-turn phasing, larger vehicle heads, and new 2070 controller. | 956000 | 956000 | 2019-02-28 | 2021-01-15 | 0 | 0 | 216000 | Authorized | Past due (due 12/31/2021) | Yes (CON)
H8-06-011 | 8 | 5170061 | 6 | Kingsburg | Fresno County | FCOG | FCOG | Intersection of Sierra Street (Conejo Avenue) at Bethel Avenue. | Construct a single lane roundabout. | 1296900 | 1296900 | 2019-04-01 | 2020-11-30 | 0 | 0 | 254000 | Authorized | Past due (due 10/31/2021) | Yes (CON)
H10-06-016 | 10 | 0 | 6 | Lemoore | Kings County | KCAG | KCAG | Intersection at Bush Street and Champion Street. | Install Rectangular Rapid Flashing Beacon (RRFB) and pedestrian crossing at uncontrolled location with enhanced safety features. | 250000 | 250000 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2021) | Due by 9/30/2024 | Yes (PE)
H10-06-020 | 10 | 0 | 6 | Porterville | Tulare County | TCAG | TCAG | Olive Avenue & Porter Road/Cloverleaf Street Intersection. | Replace existing traffic signal, add protected left turn phasing for all intersection legs, provide accessible curb ramps at all corners, and add/modify signs. | 666000 | 579420 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2021) | Due by 9/30/2024 | Yes (PE)
H9-06-020 | 9 | 5946188 | 6 | Tulare County | Tulare County | TCAG | TCAG | Piedra Drive (D179) between Avenue 376 and Road 184. | Upgrade Existing Guardrail System. | 421200 | 421200 | 2019-05-17 | 0 | 0 | 0 | 0 | Authorized | Past due (due 12/31/2021) | Yes (CON)
H10-07-001 | 10 | 0 | 7 | Baldwin Park | Los Angeles County | SCAG | MTA | Intersection of Merced Ave and Vineland Ave. | Modify signal system to provide left-turn phasing; and improve signal hardware. | 381000 | 281940 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2021) | Due by 9/30/2024 | Yes (PE)
HSIP7-07-002 | 7 | 5403028 | 7 | Carson | Los Angeles County | SCAG | MTA | Intersection of 190th St/Victoria Ave and Figueroa St | Install Protected Left Turns, Upgrade Signal Hardware, Improve Curb Ramps, install countdown pedestrian heads, upgrade APS | 202400 | 202400 | 2018-03-08 | 0 | 0 | 0 | 35000 | Authorized | Past due (due 11/30/2021) | Yes (CON)
H8-07-003 | 8 | 5403030 | 7 | Carson | Los Angeles County | SCAG | MTA | Six (6) Intersections -Avalon Blvd at Victoria Street, Main Street at Sepulveda Blvd, Main Street at 220th Street, Main Street at 223rd Street, Figueroa Street at 223rd Street, and Figueroa Street at Torrance Blvd. | Construct intersection upgrades (new signal heads, ADA ramps, service upgrades, LED safety lighting, bike detection, audible pedestrian signals, signal poles, signal mast arms, signal cabinets, raised medians, signing, striping, and left-turn phasing) | 1912100 | 1720890 | 2020-05-11 | 0 | 0 | 0 | 198540 | Authorized | Past due (due 12/31/2021) | Yes (CON)
H8-07-004 | 8 | 0 | 7 | Commerce | Los Angeles County | SCAG | MTA | E Gage Avenue south of Slauson Ave and Washington Ave just west of the I-5 freeway. | Construct crosswalks, sidewalks and curb ramps, and install signage, pavement markings and pedestrian countdown heads. | 173700 | 156330 | 0 | 0 | 0 | 0 | 0 | No PE | Past due (due 12/31/2021) | Yes (CON)
HSIP7-07-005 | 7 | 0 | 7 | Compton | Los Angeles County | SCAG | MTA | Compton Boulevard, from Willowbrook Avenue to eastern City limits. | Installation of raised medians and Class II bicycle lanes | 1928400 | 1691098 | 0 | 0 | 0 | 0 | 0 | No PE | Past due (due 4/1/2021) | Yes (CON)
H8-07-005 | 8 | 0 | 7 | Compton | Los Angeles County | SCAG | MTA | The Compton Blvd. corridor between Willowbrook Avenue and Central Avenue. | Install bike lanes and lighting along the corridor, and enhance pedestrian crossings at fifteen (15) intersections. | 1298000 | 1168200 | 0 | 0 | 0 | 0 | 0 | No PE | Past due (due 4/1/2021) | Yes (CON)
H8-07-006 | 8 | 0 | 7 | Compton | Los Angeles County | SCAG | MTA | Twenty (20) intersections. | Install Pedestrian Countdown Heads. | 249800 | 249800 | 0 | 0 | 0 | 0 | 0 | No PE | Past due (due 4/1/2021) | Yes (CON)
H9-07-004 | 9 | 0 | 7 | El Segundo | Los Angeles County | SCAG | MTA | El Segundo Boulevard between Pacific Coast Highway and Isis Avenue. | Install pedestrian countdown signal heads, enhancing striping with high visibility crosswalks, and construction of ADA compliant curb ramps. | 241500 | 241500 | 0 | 0 | 0 | 0 | 0 | No PE | Past due (due 12/31/2021) | Yes (CON)
HSIP7-07-010 | 7 | 0 | 7 | Hawthorne | Los Angeles County | SCAG | MTA | 1.3 mile section of 120th Street from Prairie Avenue to Felton Avenue | Traffic signal upgrades (upgrade signals, controllers and detection) and coordination at eight signalized intersections and improve crossings and signage at spot locations in the corridor | 1500800 | 1305800 | 0 | 0 | 0 | 0 | 0 | No PE | Past due (due 11/30/2021) | Yes (CON)
H8-07-020 | 8 | 5108178 | 7 | Long Beach | Los Angeles County | SCAG | MTA | Various locations on Anaheim Street between the Los Angeles River and Pacific Coast Highway. | Install controlled-access medians, signal upgrades, and pedestrian refuges. | 3326300 | 2993670 | 2018-12-19 | 0 | 0 | 0 | 166500 | Authorized | Past due (due 11/30/2021) | Yes (CON)
H8-07-023 | 8 | 5006867 | 7 | Los Angeles | Los Angeles County | SCAG | MTA | 10 locations within the City of Los Angeles: 42nd Pl/Central Ave, Parthenia St/Willis Ave, SunnyslopeAve/Vanowen St, Olympic Blvd/Serrano Ave, 84th St/84th Pl/Figueroa St, and more. | Install new traffic signals at existing partially stop controlled intersections at 10 locations within the City of Los Angeles. | 5284000 | 4755600 | 2017-08-21 | 0 | 0 | 0 | 951120 | Authorized | Past due (due 9/30/2021) | Yes (CON)
H9-07-011 | 9 | 5006889 | 7 | Los Angeles | Los Angeles County | SCAG | MTA | Various locations throughout the City of Los Angeles. | Upgrade existing obsolete guardrail to modern metal beam guardrail. | 1000000 | 1000000 | 2019-09-13 | 0 | 0 | 0 | 62000 | Authorized | Past due (due 12/31/2021) | Yes (CON)
H8-07-026 | 8 | 5953756 | 7 | Los Angeles County | Los Angeles County | SCAG | MTA | Intersections of Olympic Boulevard at Garfield Avenue and Whittier Boulevard at Eastern Avenue, located in the unincorporated County area of East Los Angeles. | Install various traffic signal improvements, including upgrading standards, mastarms, vehicle heads, protected left-turn phasing, bicycle and vehicle detection, ADA access ramps, communication, and other associated equipment. | 763000 | 763000 | 2017-05-31 | 0 | 0 | 0 | 136200 | Authorized | Past due (due 12/31/2021) | Yes (CON)
H8-07-039 | 8 | 5378044 | 7 | Palmdale | Los Angeles County | SCAG | MTA | Intersection of Avenue S-8 at 40th Street East | Convert an existing two-way stop to a roundabout | 2910603 | 2910603 | 2017-03-21 | 2020-04-10 | 0 | 0 | 562703 | Authorized | Past due (due 1/1/2022) | Yes (CON)
HSIP7-07-033 | 7 | 5257035 | 7 | South Gate | Los Angeles County | SCAG | MTA | On Garfield Avenue between Southern Avenue and Howery Street | Construct raised center median | 1710700 | 1539630 | 2017-11-08 | 0 | 0 | 0 | 243000 | Authorized | Past due (due 12/31/2020) | Yes (CON)
H8-07-050 | 8 | 5257037 | 7 | South Gate | Los Angeles County | SCAG | MTA | Long Beach Boulevard between Santa Ana Street and Tweedy Boulevard. | Construct raised center median, re-stripe roadway corridor, and adjust utilities to grade. | 1650900 | 1485810 | 2018-03-26 | 0 | 0 | 0 | 247500 | Authorized | Past due (due 7/1/2021) | Yes (CON)
H9-07-028 | 9 | 5139014 | 7 | Vernon | Los Angeles County | SCAG | MTA | Various signalized intersections ( Santa Fe, Slauson, Soto, District, and Bandini Corridors). | Upgrade traffic signal housings, backplates, visors, and framework at various intersection; . Install dynamic speed warning signs along five corridors. | 305700 | 305700 | 2019-12-04 | 0 | 0 | 0 | 27600 | Authorized | Past due (due 12/31/2021) | Yes (CON)
H10-07-047 | 10 | 0 | 7 | West Covina | Los Angeles County | SCAG | MTA | Various signalized intersections throughout the City. | Install left turn phasing at signalized locations with existing left turn pockets, and install signal hardware improvements to the lenses, back-plates with retroreflective borders. | 3184700 | 3184700 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2021) | Due by 9/30/2024 | Yes (PE)
H8-07-055 | 8 | 0 | 7 | Whittier | Los Angeles County | SCAG | MTA | 7 various locations of guard rails within the City of Whittier. | Upgrade guardrails. | 363000 | 363000 | 0 | 0 | 0 | 0 | 0 | No PE | Past due (due 12/31/2021) | Yes (CON)
H10-08-005 | 10 | 0 | 8 | Colton | San Bernardino County | SCAG | SANBAG | Various locations citywide including Mt. Vernon Ave., La Cadena Dr. and Barton Rd. | Replace damaged guardrails and improve existing guardrails. | 110200 | 110200 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2021) | Due by 3/31/2024 | Yes (PE)
H10-08-008 | 10 | 0 | 8 | Hemet | Riverside County | SCAG | RCTC | Forty (40) signalized intersections throughout the City. | Replace the signal head backplates with backplates with retroreflective borders. | 299300 | 299300 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2021) | Due by 9/30/2024 | Yes (PE)
H10-08-009 | 10 | 0 | 8 | Highland | San Bernardino County | SCAG | SANBAG | 26 intersections within the City of Highland. | Install pedestrian countdown signal heads. | 250000 | 250000 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2021) | Due by 3/31/2024 | Yes (PE)
H8-08-016 | 8 | 5083020 | 8 | Redlands | San Bernardino County | SCAG | SANBAG | Various locations throughout the city. | Install emergency vehicle preemption at signalized intersections. | 1188000 | 1188000 | 2017-09-15 | 0 | 0 | 0 | 148500 | Authorized | Past due (due 12/31/2021) | Yes (CON)
H8-08-017 | 8 | 5083021 | 8 | Redlands | San Bernardino County | SCAG | SANBAG | Various locations throughout the City. | Install pedestrian countdown heads at signalized intersections. | 244400 | 244400 | 2017-09-13 | 0 | 0 | 0 | 11100 | Authorized | Past due (due 12/31/2021) | Yes (CON)
H10-08-018 | 10 | 0 | 8 | Redlands | San Bernardino County | SCAG | SANBAG | The intersection of Wabash Avenue with Highland Avenue. | Install pedestrian crossing with Rectangular Rapid Flashing Beacons (RRFBs). | 250000 | 250000 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2021) | Due by 3/31/2024 | Yes (PE)
H9-08-018 | 9 | 5956274 | 8 | Riverside County | Riverside County | SCAG | RCTC | Various high profile roadway corridors, including Cajalco Rd between Wood Rd and Temescal Canyon Rd, Gavilan Rd between Cajalco Rd and Lake Mathews Rd, and Sage Rd between Cactus Valley Rd and SH-79. | Review and upgrade horizontal alignment warning signs per the CA MUTCD mandate. | 250000 | 250000 | 2019-06-12 | 0 | 0 | 0 | 230000 | Authorized | Past due (due 12/31/2021) | Yes (CON)
H9-08-022 | 9 | 5954160 | 8 | San Bernardino County | San Bernardino County | SCAG | SANBAG | The intersections of Phelan Road with Arrowhead Rd, Sunny Vista Rd, Tumbleweed Rd and Sonora Rd, in the unincorporated community of Phelan. | Install left-turn and right-turn lanes with acceleration lanes. | 1250400 | 1125360 | 2019-04-15 | 0 | 0 | 0 | 281340 | Authorized | Past due (due 12/31/2021) | Yes (CON)
H9-08-023 | 9 | 0 | 8 | San Jacinto | Riverside County | SCAG | RCTC | The intersection of San Jacinto Ave and Shaver St. | Install traffic signal with protected left turn phasing, pedestrian push buttons and leading pedestrian intervals; construct ADA ramps; install sidewalk on the E/S of San Jacinto Ave. | 519200 | 467280 | 0 | 0 | 0 | 0 | 0 | No PE | Past due (due 12/31/2021) | Yes (CON)
H9-08-027 | 9 | 0 | 8 | Victorville | San Bernardino County | SCAG | SANBAG | The intersection of Mojave Dr and Condor Rd. | Upgrade from 2-way STOP control to actuated traffic signal. | 527000 | 478500 | 0 | 0 | 0 | 0 | 0 | No PE | Past due (due 12/31/2021) | Yes (CON)
H9-08-028 | 9 | 0 | 8 | Victorville | San Bernardino County | SCAG | SANBAG | Various locations along major roadways, including National Trails Highway, Amargosa Rd, Hesperia Rd, Outer Bear Valley Rd, Petaluma Rd, and Amethyst Rd. | Upgrade existing guardrails and terminal system end treatments to meet current standards. | 469890 | 469890 | 0 | 0 | 0 | 0 | 0 | No PE | Past due (due 5/15/2021) | Yes (CON)
H10-08-024 | 10 | 0 | 8 | Wildomar | Riverside County | SCAG | RCTC | Intersection of Bundy Canyon Road and Harvest Way (three-leg intersection). | Install new traffic signal. | 272900 | 272900 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2021) | Due by 9/30/2024 | Yes (PE)
H10-08-025 | 10 | 0 | 8 | Wildomar | Riverside County | SCAG | RCTC | Four signalized intersections: Bundy Canyon Road & Orange Street, Corydon Road & Mission Trail, Gruwell Street & Palomar Street, and Corydon Road & Grand Avenue. | Replace existing vehicle heads with LED vehicle heads with retro-reflective backing plates, provide advanced dilemma zone detection, and add a protected left-turn phase at two intersections. | 375200 | 375200 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2021) | Due by 9/30/2024 | Yes (PE)
H10-10-003 | 10 | 0 | 10 | Ceres | Stanislaus County | STANCOG | Stan COG | 3 unsignalized intersections on Mitchell Ave at Garrison St, Dale Ave, and Kay St. | Install raised medians on approaches, advanced pavement markings, and striping. | 514100 | 462690 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2021) | Due by 9/30/2024 | Yes (PE)
H10-10-004 | 10 | 0 | 10 | Ceres | Stanislaus County | STANCOG | Stan COG | Two signalized intersections: Fowler Road & Mitchell Road, and East Whitmore Avenue & Moffett Road. | Install raised medians on approaches; provide protected left-turn phasing; upgrade signal hardware on all approaches. | 740400 | 666360 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2021) | Due by 9/30/2024 | Yes (PE)
H8-10-005 | 8 | 5929288 | 10 | San Joaquin County | San Joaquin County | SJCOG | SJCOG | Intersection of Byron Road and Grant Line Road in Tracy. | Install a roundabout. | 1367300 | 1367300 | 2017-03-17 | 0 | 0 | 0 | 244000 | Authorized | Past due (due 12/31/2021) | Yes (CON)
H8-10-006 | 8 | 5929289 | 10 | San Joaquin County | San Joaquin County | SJCOG | SJCOG | Intersection of Duncan Road and Comstock Road in Linden. | Install a roundabout. | 1213900 | 1213900 | 2017-03-20 | 0 | 0 | 0 | 200000 | Authorized | Past due (due 12/31/2021) | Yes (CON)
H8-10-007 | 8 | 5929290 | 10 | San Joaquin County | San Joaquin County | SJCOG | SJCOG | Intersection of Liberty Road and Dustin Road in north San Joaquin County. | Install a roundabout. | 1279500 | 1279500 | 2017-04-06 | 0 | 0 | 0 | 213000 | Authorized | Past due (due 12/31/2021) | Yes (CON)
H10-10-018 | 10 | 0 | 10 | Stockton | San Joaquin County | SJCOG | SJCOG | Intersections of Madison Street with Willow Street, Vine Street, Rose Street, Magnolia Street, Acacia Street, Poplar Street, and Flora Street. | Install High-visibility crosswalks, pavement markings, ADA ramps, sight triangles and rapid-flashing beacons. | 721600 | 644940 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2021) | Due by 9/30/2024 | Yes (PE)
H10-11-004 | 10 | 0 | 11 | El Cajon | San Diego County | SANDAG | SANDAG | Washington Ave between Avocado Ave and Mollison Ave. | Install high visibility pedestrian crossings at signalized intersections, a Pedestrian Hybrid Beacon, and raised medians along the corridor. | 2235000 | 2134030 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2021) | Due by 9/30/2024 | Yes (PE)
H8-11-005 | 8 | 5446022 | 11 | Encinitas | San Diego County | SANDAG | SANDAG | Intersections of Encinitas Blvd and Vulcan Avenue, Leucadia Boulevard and Quail Gardens Drive, Santa Fe Drive and Scripps Driveway, and Leucadia Boulevard and North Vulcan Avenue. | Replace existing permissive left-turn phases and signal heads with protected left-turn phases and signal heads on existing and/or new traffic signal poles and mast arms. | 532200 | 532200 | 2017-09-13 | 0 | 0 | 0 | 45000 | Authorized | Past due (due 12/31/2021) | Yes (CON)
H8-11-007 | 8 | 5446024 | 11 | Encinitas | San Diego County | SANDAG | SANDAG | Corridors of 2nd St, Birmingham Dr, Coast Highway 101, El Camino Real, Encinitas Blvd, Garden View Rd, Leucadia Blvd, Mountain Vista Dr, Olivenhain Rd, Quail Garden Dr, Santa Fe Dr, Via Cantebria, Village Park Wy, and Vulcan Ave/San Elijo Ave. | Install LED luminaire safety lighting at signalized intersections and LED street lighting along project corridors. | 718000 | 718000 | 2017-09-13 | 0 | 0 | 0 | 50000 | Authorized | Past due (due 12/31/2021) | Yes (CON)
H10-11-006 | 10 | 0 | 11 | Encinitas | San Diego County | SANDAG | SANDAG | Coast Highway 101 from Swami's Pedestrian Crossing to Chesterfield Dr. | Install separated bike lanes. | 722100 | 649890 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2021) | Due by 9/30/2024 | Yes (PE)
H10-11-008 | 10 | 0 | 11 | Encinitas | San Diego County | SANDAG | SANDAG | 48 intersections throughout the City of Encinitas. | Install Leading Pedestrian (LPI), traffic signal system upgrades for LPI operations, and high visibility crosswalk striping. | 1234500 | 1234500 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2021) | Due by 9/30/2024 | Yes (PE)
H10-11-010 | 10 | 0 | 11 | Imperial County | Imperial County | SCAG | ICTC | Correll Rd between Dogwood Dr and Heber Ave; Rio Vista St between San Diego Ave and Haskell Rd; Shore Hawk Ave near intersection with Shore Gem St; and S. Marina Dr at intersection with Sea Palm Ave. | Install Rectangular Rapid Flashing Beacons (RRFBs) near schools. | 158000 | 158000 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2021) | Due by 9/30/2024 | Yes (PE)
H10-11-014 | 10 | 0 | 11 | National City | San Diego County | SANDAG | SANDAG | Signalized Intersections at Harbison Ave/E Plaza Blvd, Harbison Ave/E 8th St, E Plaza Blvd/Highland Ave, Highland Ave/E 8th St, Highland Ave/E 21st St, Highland Ave/E 18th St, National City Blvd/E 8th St and Highland Ave/E 30th St. | Install pedestrian countdown signal heads, advance stop bar before crosswalk (Bicycle Box), and modify signal phasing to implement a Leading Pedestrian Interval (LPI). | 427500 | 427500 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2021) | Due by 9/30/2024 | Yes (PE)
H10-11-015 | 10 | 0 | 11 | Poway | San Diego County | SANDAG | SANDAG | Various locations along Poway Road between Oak Knoll Road and Garden Road. | Provide advanced dilemma zone detection, implement leading pedestrian interval (LPI), create directional median openings, and install/upgrade intersection regulatory signs. | 604100 | 589980 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2021) | Due by 9/30/2024 | Yes (PE)
H9-11-016 | 9 | 5004209 | 11 | San Diego | San Diego County | SANDAG | SANDAG | Various locations, including Skyline Drive & S.Woodman Street, West Mission Bay Drive & Ingraham Street On-ramp, North Torrey Pines Road N/O Callan Road, Via de la Melodia & Smythe Avenue, Sabre Springs Parkway S/O Evening Creek Drive South. | This project involves extending existing guardrails, installing end terminals or crash cushions and widening sidewalks to provide adequate access. | 998200 | 998200 | 2019-09-13 | 0 | 0 | 0 | 178300 | Authorized | Past due (due 12/31/2021) | Yes (CON)
H9-12-007 | 9 | 5266029 | 12 | La Habra | Orange County | SCAG | OCTA | Six (6) intersections, including La Habra Blvd & Monte Vista St, La Habra Blvd & Cypress St, Harbor Blvd & Sterns Ave, Lambert Rd & Idaho St, Idaho St & Las Lomas Ave, and La Habra Blvd & Euclid St. | Add left-turn storage and left-turn protected signal phasing at one intersection; add left-turn protected signal phasing at four intersections; and upgrade existing signals at all six intersections. | 784600 | 706140 | 2019-06-12 | 0 | 0 | 0 | 81000 | Authorized | Past due (due 12/31/2021) | Yes (CON)
H9-12-008 | 9 | 5266030 | 12 | La Habra | Orange County | SCAG | OCTA | Eight (8) intersections, including La Habra & Monte Vista, La Habra & Cypress, Harbor & Sterns, Lambert & Idaho, Las Lomas & Idaho, La Habra & Euclid, La Habra & Harbor, and Lambert & Harbor. | Upgrade existing pedestrian signal heads with new pedestrian countdown signal heads. | 115400 | 115400 | 2019-06-12 | 0 | 0 | 0 | 10000 | Authorized | Past due (due 12/31/2021) | Yes (CON)

## Notes
Notes:
1. | The project delivery requirements for local safety programs are as follows: • The PE milestone is met within 9 months; and • The CON milestone is met within 36 months (3 years). Exceptions are: a. The PE milestone does not apply if the project does not need HSIP funding in PE. b. For a project that a consultant is used for the PE work, an additional time of 6 months is allowed for meeting the CON milestone. The additional time is for the agency to advertise and select the consultant for the work of the PE phase.
2. | The project delivery information ("PE Auth Date", "ROW Auth Date", "CON Auth Date", "Closed out Date", etc) in this report is based on the offical approvals. If a request for authorization/allocation has been submitted but not yet approved, the information is not reflected in this report.
3. | Values under "Milestone Status (PE)" and "Milestone Status (CON)"
Value | Meaning
Authorzied | This phase has been authorized.
Due by x/xx/xxxx | The milestone will be due on this date pur the HSIP Delivery Requirements.
Past due (due x/xx/xxxx) | The milestone was due on this past date. This project is considered "delayed".
RFA received x/xx/xxxx | Caltrans received Request for Authorization/Allocation (RFA) package though there is still no official approval. The milestone is considered "met" if the request can be approved within 3 months from this request date.
No PE (or No CON) | HSIP funds will not used in PE phase (or CON phase) so the milestone is not applicable. Example 1: only local funds is used for PE - "No PE"; Example 2: the construction of the project has been combined with another project so no construction authorization is needed under this project - "No CON".
Not tracked | The milestone is not tracked. Example: Caltrans takes the lead in delivering the project. The local agency has no full control over the schedule.
For more information on HSIP Delivery Requirements, please go to the below webpage:
https://dot.ca.gov/programs/local-assistance/fed-and-state-programs/highway-safety-improvement-program/delivery-requirements-status-approved-projects