## LIST_HSIP
Highway Safety Improvement Program (HSIP) Delivery Status Report for All Projects
Sorted by Caltrans District and Agency, Status as of 04/07/2025
Projects with gray background are Closed (Completed); Projects with red fonts are red-flagged as having delays per HSIP delivery requirements
Columns A to L are General Project Information, M to Q are Actual Project Delivery Information, and R to T are Delivery Milestone Status. Please see notes on the other spreadsheet of this file.
(Rows 5, 6 and 7 to be deleted for online reports; column U/V/W to be hidden) | [11 empty] | (need to sort) (need to double click to expand row to fit)
General Project Information | [11 empty] | Actual Project Delivery Information (Offical approval dates/amount. Not reflected if the request has not yet been approved.) |  |  |  |  | Delivery Milestone Status (see notes on the other spreadsheet)
| 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 33 | 34 | 35 | 23 | 36 | 37
Unique Project ID | Cycle | Project Number | District | Agency | County | MPO | RTPA | Project Location | Description of Work | Total Cost ($) | HSIP Funds ($) | PE Auth Date | ROW Auth Date | CON Auth Date | Closed out Date | Obligated /Allocated Amt ($) | Milestone Status (PE) | Milestone Status (CON) | Delayed? | Project Phase | FundingType | SpecialRule
H12-01-001&002&003 | 12 | 0 | 1 | Arcata | Humboldt County | RURAL | HCAG | Various locations throughout the City. | Stripe high visibility crossings, install bike lanes and buffered bike lanes, replaceg paint with thermoplastic striping, and install signs. Install rectangular rapid flashing beacons (RRFBs), raised pedestrian crossing speed tables, bulb-outs, enhanced visibility crosswalks, and LED stop signs. Install white and yellow reflective thermoplastic striping and retroreflective pavement marker. | 778400 | 700560 | 0 | 0 | 0 | 0 | 0 | No PE | Due by 3/31/2028 | No | Not Started | State | 0
HSIP2-01-003 | 2 | 5021014 | 1 | Arcata | Humboldt County | RURAL | HCAG | Fickle Hill Road | Install Signs And Pavement Markings; Construct Minor Shoulder Widening And Asphalt Berms | 120776.97 | 89715.33 | 2010-02-19 | 0 | 2014-04-14 | 2016-10-20 | 89715.33 | Authorized | Authorized | No | Closed | Federal | 0
HSIP6-01-001 | 6 | 5427026 | 1 | Clearlake | Lake County | RURAL | LC/CAPC | Lakeshore Dr between Olympic Dr and Old SR 53, and Olympic Dr between Lakeshore Dr and Old SR 53, Various roads throughout the City of Clearlake. | Install bike lanes, striping, and reflectors | 368642.51 | 331652.71 | 2014-02-18 | 0 | 2014-06-20 | 2015-10-28 | 331652.71 | Authorized | Authorized | No | Closed | Federal | 0
H11-01-001 | 11 | 5013017 | 1 | Crescent City | Del Norte County | RURAL | Del Norte LTC | Various locations throughout the City. | Install enhanced pedestrian crossings that include sidewalks with curb ramps, new road signs, and updated pavement markings. | 250000 | 225000 | 0 | 0 | 2024-05-15 | 0 | 225000 | No PE | Authorized | No | CON | State | 0
H12-01-004&005 | 12 | 5901070 | 1 | Del Norte County | Del Norte County | RURAL | Del Norte LTC | Williams Drive from US 101 to the end of the County maintained road, a distance of approximately 650 feet. | Construct a multi-use path accessing the Williams Drive Emergency Shelter and Micro Village and Williams Drive Youth Opportunity Center. | 2027000 | 441260 | 2025-07-29 | 0 | 0 | 0 | 88252 | Authorized | Due by 3/31/2028 | No | PE | State | 0
H12-01-006 | 12 | 5901071 | 1 | Del Norte County | Del Norte County | RURAL | Del Norte LTC | Del Norte County maintained road system. | Upgrade guardrail on the County maintained road system. | 1111100 | 999990 | 2025-07-22 | 0 | 0 | 0 | 185130 | Authorized | Due by 3/31/2028 | No | PE | Federal | 1
HSIP1-01-001 | 1 | 5901030 | 1 | Del Norte County | Del Norte County | RURAL | Del Norte LTC | On Northcrest Drive Between Pm .632 And Pm .674 And On Washington Blvd Between Pm 2.145 And Pm 2.279. | Construct Curb, Gutter And Sidewalk And Curb Ramps. | 361405 | 308458.26 | 2007-10-26 | 0 | 2008-07-21 | 2010-05-14 | 308458.26 | Authorized | Authorized | No | Closed | Federal | 0
HSIP1-01-002 | 1 | 5901031 | 1 | Del Norte County | Del Norte County | RURAL | Del Norte LTC | Intersections Of Old Mill Road And Northcrest Dr.; Lake Earl Dr. And Pine Grove Rd.; Washington Blvd And Northcrest Dr. | Install In-Pavement Lighted Crosswalks | 164047 | 129600 | 2007-10-26 | 0 | 2008-07-23 | 2010-05-06 | 129600 | Authorized | Authorized | No | Closed | Federal | 0
HSIP3-01-003 | 3 | 5901041 | 1 | Del Norte County | Del Norte County | RURAL | Del Norte LTC | Various locations within Crescent City | Install Rectangular Rapid Flashing Beacons (RRFB) and Construct Curb Ramps | 167905.47 | 151114.93 | 2010-08-26 | 0 | 2012-11-19 | 2014-04-08 | 151114.93 | Authorized | Authorized | No | Closed | Federal | 0
HSIP4-01-001 | 4 | 5901046 | 1 | Del Norte County | Del Norte County | RURAL | Del Norte LTC | Pebble Beach Dr. between Hemlock Ave. and the city limits of Crescent City | Resurface existing pavement and pave shoulders; remove right-turn lane; construct curb, gutter, and sidewalks | 763145.31 | 681321.62 | 2011-08-01 | 0 | 2013-10-24 | 2015-12-15 | 681321.62 | Authorized | Authorized | No | Closed | Federal | 0
HSIP6-01-002 | 6 | 5901051 | 1 | Del Norte County | Del Norte County | RURAL | Del Norte LTC | On Parkway Dr between SR 101 on the south end and SR 199 on the north end in Del Norte County. | Install center line rumble strips, delineators, signs, and striping | 318563.57 | 317028.99 | 2013-12-31 | 0 | 2016-07-21 | 2017-10-18 | 317028.99 | Authorized | Authorized | No | Closed | Federal | 0
H10-01-001 | 10 | 5017049 | 1 | Eureka | Humboldt County | RURAL | HCAG | H and I Streets, between 5th Street and Harris Street; 18 non-signalized intersections along the 6th and 7th Street corridors. | Reduce H & I St. from 3 lanes to 2 lanes, add buffered bike lanes, pedestrian upgrades to nonsignalized intersections such as curb extensions and RRFBs, and add other safety improvements such as signal re-timing and dynamic speed warning signs. Pedestrian crossing improvements at 18 non-signalized intersections throughout the 6th and 7th Street corridors within the City of Eureka including crosswalk markings, curb extensions and pedestrian crossing signage. | 4856300 | 4236420 | 2021-10-06 | 0 | 2023-04-10 | 2025-02-18 | 4236420 | Authorized | Authorized | No | Closed | State | 0
H11-01-002 | 11 | 5017054 | 1 | Eureka | Humboldt County | RURAL | HCAG | Buhne Street between Fairfield and Dean Streets. | Install enhanced pedestrian crossings that include sidewalks with curb ramps, RRFB systems, new road signs, and updated pavement markings. | 845200 | 760680 | 2023-09-15 | 0 | 2025-09-18 | 0 | 760680 | Authorized | Authorized | No | CON | State | 0
H12-01-007 | 12 | 0 | 1 | Eureka | Humboldt County | RURAL | HCAG | Various locations along the proposed Bay to Zoo Trail alignment, specifically the 2200 block of Buhne Street, 2200 block of Russ Street, and the intersection of Dolbeer and Harris Streets. | Implement pedestrian enhancements such as flashing beacons and crosswalk improvements along the Bay to Zoo Trail alignment at high traffic mid-block crossing and non-signalized intersection. | 433500 | 346800 | 0 | 0 | 0 | 0 | 0 | No PE | Due by 3/31/2028 | No | Not Started | State | 0
H12-01-008 | 12 | 5017057 | 1 | Eureka | Humboldt County | RURAL | HCAG | Six (6) signalized intersections. | Replace existing pedestal mounted signals with mast arm and overhead signals and implement leading pedestrian interval (LPI) at five locations, and install protected left turn and signal phasing at one location. | 983400 | 885060 | 2025-09-18 | 0 | 0 | 0 | 18000 | Authorized | Due by 3/31/2028 | No | PE | State | 0
H8-01-001 | 8 | 5017044 | 1 | Eureka | Humboldt County | RURAL | HCAG | Twenty-five (25) non-signalized crosswalk locations throughout Eureka. | Install high visibility crosswalk markings, thermoplastic markings, rapid flashing beacons, and remove raised curb barriers by installing ramps. | 250000 | 250000 | 2017-06-13 | 0 | 2018-05-18 | 2020-07-13 | 250000 | Authorized | Authorized | No | Closed | Federal | 0
H8-01-002 | 8 | 5017045 | 1 | Eureka | Humboldt County | RURAL | HCAG | Various locations throughout the City of Eureka. | Conduct regulatory and warning sign retro-reflectivity audit, remove and replace existing regulatory and warning signs that no longer meet CAMUTCD retro-reflectivity standards. | 312185.38 | 312185.38 | 2017-06-13 | 0 | 2019-04-12 | 2020-11-17 | 312185.38 | Authorized | Authorized | No | Closed | Federal | 0
H8-01-003 | 8 | 5017046 | 1 | Eureka | Humboldt County | RURAL | HCAG | Signalized intersections: H Street at 6th, 7th, 14th, Buhne, Henderson, and Harris; and I Street at 6th, 7th 14th, and Henderson. | Replace existing overhead poles (one signal head over one-way three lane roadway) with new poles with two signal heads; Add street lights. | 373844.98 | 347657.96 | 2017-06-13 | 0 | 2018-06-28 | 2020-10-07 | 347657.96 | Authorized | Authorized | No | Closed | Federal | 0
H9-01-001 | 9 | 5017047 | 1 | Eureka | Humboldt County | RURAL | HCAG | Thirty-five (35) intersections (29 nonsignalized and 6 signalized intersections). | Pedestrian & vehicle improvements including crosswalk markings, rapid flashing beacons, curb extensions, flashing beacons at stop signs, speed feedback signs, and audible pedestrian signals. | 1196660.84 | 1196400 | 2019-04-12 | 0 | 2021-01-07 | 2022-11-21 | 1196400 | Authorized | Authorized | No | Closed | Federal | 0
HSIP2-01-001 | 2 | 5017021 | 1 | Eureka | Humboldt County | RURAL | HCAG | Intersections Of Harris St. With E St. And F St. | Install Left Turn Lanes; Upgrade Traffic Signals | 189492.41 | 138600 | 2009-05-07 | 0 | 2011-05-11 | 2012-08-23 | 138600 | Authorized | Authorized | No | Closed | Federal | 0
HSIP2-01-002 | 2 | 5017022 | 1 | Eureka | Humboldt County | RURAL | HCAG | Compton Road Between Fern Drive South To City Limit | Install Guardrail | 54020.54 | 48617.49 | 2009-05-07 | 0 | 2010-07-19 | 2012-03-05 | 48617.49 | Authorized | Authorized | No | Closed | Federal | 0
HSIP3-01-001 | 3 | 5017033 | 1 | Eureka | Humboldt County | RURAL | HCAG | Citywide (All 25 Signalized Intersections) | Install Emergency Vehicle Pre-Emption Devices (Including Detectors, Wiring, And Phase Selectors) | 763380.32 | 687040.67 | 2010-09-14 | 0 | 2013-04-12 | 2015-06-19 | 687040.67 | Authorized | Authorized | No | Closed | Federal | 0
HSIP3-01-002 | 3 | 5017034 | 1 | Eureka | Humboldt County | RURAL | HCAG | Intersection Of Harris St. And "S" St. | Install Protected Left-Turn Signals For Eastbound And Westbound Harris St. | 160603.11 | 131715 | 2010-09-14 | 0 | 2012-06-13 | 2013-11-25 | 131715 | Authorized | Authorized | No | Closed | Federal | 0
HSIP4-01-003 | 4 | 5017035 | 1 | Eureka | Humboldt County | RURAL | HCAG | West Ave. between Myrtle Ave. and 6th St. | Construct bulb-outs and curb ramps; install in-pavement crosswalk lights, safety lighting, striping, pavement markings | 504263 | 441045.91 | 2011-08-29 | 0 | 2013-09-17 | 2015-12-02 | 441045.91 | Authorized | Authorized | No | Closed | Federal | 0
HSIP6-01-003 | 6 | 5017040 | 1 | Eureka | Humboldt County | RURAL | HCAG | 25 intersections throughout the City of Eureka | Install pedestrian countdown heads; ADA pedestrian pushbuttons | 140596.51 | 119771.69 | 2014-04-15 | 0 | 2014-09-03 | 2016-03-29 | 119771.69 | Authorized | Authorized | No | Closed | Federal | 0
H11-01-003 | 11 | 5088037 | 1 | Fort Bragg | Mendocino County | RURAL | Mendocino COG | Various intersections throughout the city: SR 20 at BoatYard, SR 1 at Pine, SR 1 at South, SR 1 at Pudding Creek, SR 1 at Noyo Point/Harbor, and Redwood Ave from West Terminus to North Whipple St. | Install or upgrade larger or additional stop signs or other intersection warning and regulatory signs, install or upgrade pedestrian crossings with enhanced safety features including RRFBs. | 91600 | 73890 | 0 | 0 | 0 | 0 | 0 | No PE | Due by 9/30/2026 | No | Not Started | State | 0
H11-01-004 | 11 | 5088038 | 1 | Fort Bragg | Mendocino County | RURAL | Mendocino COG | Nine intersections and connecting segments of Harold St between Fir St in the north and Maple St in the south. | Install high visibility crosswalks, bulb-outs, and warning signs along with ADA compliant curb ramps. | 297700 | 248130 | 0 | 0 | 2023-05-10 | 2025-12-15 | 248130 | No PE | Authorized | No | Closed | State | 0
H12-01-009 | 12 | 5088042 | 1 | Fort Bragg | Mendocino County | RURAL | Mendocino COG | Willow St. between S Harold St. and Florence St., containing four (4) intersections and one (1) mid-block crossing. | Install a pedestrian crossing island, high visibility crosswalks, and ADA compliant sidewalk, curb & gutter, curb ramps, and bulb-outs. | 397200 | 349677 | 2025-08-19 | 0 | 0 | 0 | 33507 | Authorized | Due by 3/31/2028 | No | PE | State | 0
H8-01-004 | 8 | 5145017 | 1 | Fortuna | Humboldt County | RURAL | HCAG | Various locations throughout the city of Fortuna. | Upgrading and installing pedestrian crosswalks, installing edge and centerlines. | 400100 | 400099.15 | 2017-08-18 | 0 | 2019-12-19 | 2021-03-25 | 400099.15 | Authorized | Authorized | No | Closed | Federal | 0
HSIP6-01-004 | 6 | 5145013 | 1 | Fortuna | Humboldt County | RURAL | HCAG | Rohnerville Rd/School St-Mills St, Rohnerville Rd/Jordan St, Rohnerville Rd/Newell Dr; on Rohnerville Rd between School St and Jordan St | Construct sidewalks, curbs, curb ramps and curb extensions; Upgrade striping; Install signs and flashing beacons | 694950.65 | 621004.68 | 2014-06-08 | 0 | 2015-08-20 | 2018-06-14 | 621004.68 | Authorized | Authorized | No | Closed | Federal | 0
H10-01-003 | 10 | 5904187 | 1 | Humboldt County | Humboldt County | RURAL | HCAG | Intersection of Hammond Trail with Hiller Road and mid-town trail crossing at intersection of Washington and Oakdale in McKinleyville and two uncontrolled crosswalks on Redwood Drive in Redway. | Install pedestrian rapid flashing beacons at Hammond Trail crossing of Hiller Road and at mid-town trail crossing of Washington at Oakdale in McKinleyville and two rectangular rapid flashing beacons with pedestrian refuges on Redwood Drive. | 250000 | 250000 | 2021-08-24 | 2024-05-15 | 2024-05-15 | 0 | 250000 | Authorized | Authorized | No | CON | State | 0
H11-01-005 | 11 | 5904198 | 1 | Humboldt County | Humboldt County | RURAL | HCAG | Various guardrails and bridges throughout Humboldt County. | Repair, replace and upgrade guardrails and end treatments to current safety standards. | 1107600 | 996840 | 2023-11-30 | 0 | 0 | 0 | 72000 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE | Federal | 1
H11-01-006 | 11 | 5904197 | 1 | Humboldt County | Humboldt County | RURAL | HCAG | Intersection of Country Club Road and The Terrace Road in Willow Creek California. | Install pedestrian activated flashing beacon at crosswalk from The Terrace Road across County Club Road with an advance warning flashing sign on Country Club. | 158400 | 142560 | 2023-11-20 | 0 | 0 | 0 | 10800 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE | Federal | 1
H11-01-007 | 11 | 5904192 | 1 | Humboldt County | Humboldt County | RURAL | HCAG | Various County, Tribal and Bureau of Indian Affairs roads within Humboldt County Tribal Indian Reservation Roads system. Hoopa, Karuk and Yurok tribes are participating agencies. | Place edge lines on numerous rural roads in Humboldt County that are within Indian Reservation Roads systems. This project bundles the requests from three tribes, The Hoopa Valley Tribe, the Karuk Tribe and the Yurok Tribe. | 832900 | 749610 | 2023-09-15 | 0 | 2026-01-13 | 0 | 749610 | Authorized | Authorized | No | CON | State | 0
H12-01-010 | 12 | 0 | 1 | Humboldt County | Humboldt County | RURAL | HCAG | Three locations: intersection of Oak and F Streets in unincorporated Eureka area, intersection of Kimtu Road and Country Club Drive in Willow Creek area, and school crossing for Loleta School on Loleta Drive. | Install pedestrian crossing enhancements. | 388800 | 349920 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2025) | Due by 3/31/2028 | Yes (PE) | Not Started | State | 0
H12-01-011 | 12 | 0 | 1 | Humboldt County | Humboldt County | RURAL | HCAG | Various guardrails and bridges throughout Humboldt County. | Repair, replace and upgrade guardrails and end treatments to current safety standards. | 1108300 | 997470 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2025) | Due by 3/31/2028 | Yes (PE) | Not Started | Federal | 1
H8-01-005 | 8 | 5904161 | 1 | Humboldt County | Humboldt County | RURAL | HCAG | Various guardrail and bridge locations (including locations in the cities of Blue Lake, Fortuna, Ferndale and Arcata for which the County is acting as lead agency). | Upgrade guardrails and guardrail end treatments. | 1234592.62 | 1200000 | 2017-02-07 | 0 | 2020-01-14 | 2023-07-11 | 1200000 | Authorized | Authorized | No | Closed | Federal | 0
H8-01-006 | 8 | 5904160 | 1 | Humboldt County | Humboldt County | RURAL | HCAG | Central and Myrtle Avenue signals in the towns of McKinleyville and Eureka. | Install pedestrian countdown signals at existing signalized intersections. | 162265.58 | 160883.41 | 2017-02-07 | 0 | 2017-12-19 | 2020-10-14 | 160883.41 | Authorized | Authorized | No | Closed | Federal | 0
H9-01-002 | 9 | 5904181 | 1 | Humboldt County | Humboldt County | RURAL | HCAG | Intersection of Redwood Dr and Redway Dr in the town of Redway. | Install enhanced pedestrian crossing with bulb outs to cross Redway Dr. Install pedestrian related warning signs and pavement markings. Restripe and realign lane lines, pavement markings and install new speed limit pavement markings. | 471372 | 419735 | 2019-10-18 | 2021-05-20 | 2022-06-23 | 0 | 415935.57 | Authorized | Authorized | No | CON | Federal | 1
HRRR1-01-002 | 1 | 5904089 | 1 | Humboldt County | Humboldt County | RURAL | HCAG | Briceland-Thorne Rd and Shelter Cove Rd. | Realign Roadway | 1133969.73 | 888655.6 | 2008-01-29 | 2011-04-06 | 2012-05-16 | 2016-11-04 | 888655.6 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-01-001 | 5 | 5904131 | 1 | Humboldt County | Humboldt County | RURAL | HCAG | Central Ave. from Anna Sparks Way to Hiller Rd. | Install buffered bike lanes, pedestrian refuge islands, and emergency vehicle pre-emption equipment | 1244386.96 | 975770.27 | 2013-08-11 | 0 | 2015-08-20 | 2019-01-14 | 975770.27 | Authorized | Authorized | No | Closed | Federal | 0
HSIP6-01-005 | 6 | 5904136 | 1 | Humboldt County | Humboldt County | RURAL | HCAG | Various rural major collectors throughout the County of Humboldt | Install striping | 240099.55 | 233916.1 | 2014-04-14 | 0 | 2016-09-13 | 2023-02-22 | 233916.1 | Authorized | Authorized | No | Closed | Federal | 0
HSIP7-01-001 | 7 | 5904150 | 1 | Humboldt County | Humboldt County | RURAL | HCAG | Three Locations in Myrtletown (Eureka): The intersection of Myrtle Avenue & Pennsylvania Avenue (Healthsport), the intersection of Harrison Avenue and Roane Avenue (Ramone's Bakery), and the midblock crossing on Harris Street at the Redwood Acres Fairgrounds. | Install Rectangular Rapid Flashing Beacons (RRFB's) at three un-signalized crosswalks in Myrtletown (Eureka). | 329037.53 | 329037.53 | 2016-09-08 | 0 | 2017-12-19 | 2021-01-07 | 329037.53 | Authorized | Authorized | No | Closed | Federal
H11-01-008 | 11 | 5914131 | 1 | Lake County | Lake County | RURAL | LC/CAPC | Eight (8) mid-block and non-signalized intersection pedestrian crossings throughout Lake County: Upper Lake (3 locations), Lucerne (1 location), Lower Lake (2 locations) and Middletown (2 locations) | Install solar powered RRFBs and crosswalk signs, install/upgrade pavement markings and advanced signage, install/reconstruct sidewalks, and install no parking signs at select locations. | 1217500 | 1077930 | 2023-07-21 | 0 | 0 | 0 | 189270 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE | Federal | 1
H11-01-009 | 11 | 5914132 | 1 | Lake County | Lake County | RURAL | LC/CAPC | Soda Bay Road, Butts Canyon Road, Nice-Lucerne Cutt-off Road, Lakeshore Boulevard, Morgan Valley Road, Sulphur Bank Drive, Bottle Rock Road, Scotts Valley Road, New Long Valley Road, Seigler Canyon Road, and Spruce Grove Road. | Install solar powered dynamic variable speed warning sign assemblies at 22 locations around Lake County. | 342000 | 307800 | 2023-07-26 | 0 | 0 | 0 | 49500 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE | Federal | 1
H8-01-007 | 8 | 5914113 | 1 | Lake County | Lake County | RURAL | LC/CAPC | Along the entire length of Big Valley Road, Hartmann Road, Highland Springs Road, Lakeshore Blvd., Morgan Valley Road, Point Lakeview Road, Riggs Road, Spruce Grove Road and Sulphur Bank Road. | Upgrade warning signs, centerlines, edge-lines, and install delineators. | 753706.27 | 752941.37 | 2017-06-13 | 0 | 2018-06-15 | 2023-10-19 | 752941.37 | Authorized | Authorized | No | Closed | Federal | 0
HSIP1-01-003 | 1 | 5914053 | 1 | Lake County | Lake County | RURAL | LC/CAPC | Various County-Maintained Roads. | Upgrade All County-Maintained Stop Signs And Street Name Signs Per Mutcd Standards. | 517000 | 465299.98 | 2007-10-24 | 0 | 2008-08-06 | 2012-01-18 | 465299.98 | Authorized | Authorized | No | Closed | Federal | 0
HSIP2-01-004 | 2 | 5914056 | 1 | Lake County | Lake County | RURAL | LC/CAPC | Bottle Rock Rd. From Harrington Flat Rd. To 1.0 Mile North Of Harrington Flat Rd. | Install Open-Graded Asphalt Skid-Resistant Overlay | 452344.66 | 407110.18 | 2009-02-09 | 0 | 2010-06-07 | 2012-11-01 | 407110.18 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-01-002 | 5 | 5914086 | 1 | Lake County | Lake County | RURAL | LC/CAPC | Butts Canyon Rd. and Soda Bay Rd. | Upgrade signs and pavement markings | 178483.78 | 159133.96 | 2013-01-22 | 0 | 2014-08-11 | 2017-02-22 | 159133.96 | Authorized | Authorized | No | Closed | Federal | 0
HSIP7-01-002 | 7 | 5914104 | 1 | Lake County | Lake County | RURAL | LC/CAPC | Along the entire length of Bottle Rock Road, Scotts Valley Road, Seigler Canyon Road and Loch Lomond Road. Along Elk Mountain Road from Main Street to Forest Highway 16N20. | Upgrade warning signs, centerlines, edge-lines and install delineators | 701723.19 | 629013.22 | 2016-10-14 | 2017-06-22 | 2018-02-23 | 2023-10-19 | 629013.22 | Authorized | Authorized | No | Closed | Federal
H10-01-004 | 10 | 5076016 | 1 | Lakeport | Lake County | RURAL | LC/CAPC | Various locations throughout the City. | Implement a street sign replacement program. Replace 719 signs in the City including warning, regulatory, guide and City specific signs. | 188400 | 188400 | 2021-11-29 | 0 | 2023-03-10 | 2025-01-06 | 188400 | Authorized | Authorized | No | Closed | State | 0
H8-01-008 | 8 | 5076012 | 1 | Lakeport | Lake County | RURAL | LC/CAPC | Arterial and collector streets | Install pavement markings. | 335228 | 335228 | 2017-04-17 | 0 | 2018-04-24 | 2019-08-02 | 335228 | Authorized | Authorized | No | Closed | Federal | 0
H11-01-010 | 11 | 5910139 | 1 | Mendocino County | Mendocino County | RURAL | Mendocino COG | Branscomb Rd/Willits Ave-Kenny Creek Rd, Eastside Calpella Rd/Marina Dr-SR20 on/off ramp, Comptche Ukiah Rd/Hwy1-Mendocino Headlands SP, Mountain View Rd/Btwn Manchester & Boonville, Crawford Rd/Biggar Ln-Foothill Blvd, and S State St/Laws Ave-Beacon Ln. | Installation of Advance Curve Warning Signs, installation of sidewalks/pathways, and installation/upgrade of Pedestrian Crossing. | 2864600 | 2578140 | 2023-07-26 | 0 | 0 | 0 | 343080 | Authorized | Due by 6/30/2027 | No | PE | Federal | 1
H11-01-011 | 11 | 5910140 | 1 | Mendocino County | Mendocino County | RURAL | Mendocino COG | Roadway Segments along: Branscomb Rd, Eastside Calpella Rd, North State St, Sherwood Rd, Comptche Ukiah Rd, Simpson Lane, Vichy Springs Rd, Valley Rd, South State St, Mountain View Rd, Pudding Creek Rd, Eel River Rd, and Henderson Lane. | Installation/upgrade of signs with new fluorescent sheeting (regulatory or warning) and the installation of chevron signs on horizontal curves, delineators, reflectors, and/or object markers. | 339200 | 305280 | 2023-07-26 | 0 | 2025-07-22 | 0 | 305258 | Authorized | Authorized | No | CON | Federal | 1
H11-01-012 | 11 | 5910141 | 1 | Mendocino County | Mendocino County | RURAL | Mendocino COG | Roadway segments along East Side Potter Valley Rd, MP 5.95 & 6.18; Point Cabrillo Dr, MP 2.64 & 2.88; Primrose Dr, MP 1.60; Comptche-Ukiah Rd, MP 7.30; Vichy Springs Rd, MP 1.01; & Old River Rd, MP 0.18, 1.17, 5.73, 5.92, & 10.08 | Upgrade existing guardrails and end treatments at areas with a high probability of vehicles unintentionally exiting the roadway. | 1111111 | 1000000 | 2023-07-26 | 0 | 2025-07-21 | 0 | 875520 | Authorized | Authorized | No | CON | Federal | 1
H11-01-013 | 11 | 0 | 1 | Robinson Rancheria | Lake County | RURAL | LC/CAPC | Various locations on Robinson Rancheria, Lake County. | Install new street signs, regulatory, warning and information with new sign posts. Also replace existing guardrail on Acorn Drive and enhance crosswalk on Pomo Way. | 63000 | 56700 | 0 | 0 | 0 | 0 | 0 | No PE | Past due (due 3/31/2026) | Yes (CON) | Not Started | Federal | 3
H10-01-005 | 10 | 5036016 | 1 | Trinidad | Humboldt County | RURAL | HCAG | 1. Three locations: Main Street at View Avenue; Edwards Street at Hector Street; and Edwards Street at Galindo Street. 2. Scenic Drive south of Langford Road and Patrick's Point Drive north of Ocean Avenue. 3. Trinidad Frontage Road from N. Westhaven Drive to End; Stagecoach Road from City Limits to Main Street; Westhaven Drive from City Limits to Trinidad Frontage Road; View Ave, Ocean Ave, Edwards Street, Galindo Street. | 1. Install Rectangular Rapid Flashing Beacons (RRFBs), curb/driveway extensions, ADA curb ramps, yield lines, traffic signs, striping and pavement markings. 2. Upgrade/replace existing guardrail systems and end treatments. 3. Install edgelines and improve striping. | 825800 | 825800 | 2021-10-29 | 2022-11-04 | 2023-08-24 | 0 | 825800 | Authorized | Authorized | No | CON | State | 0
HRRR1-01-001 | 1 | 5036009 | 1 | Trinidad | Humboldt County | RURAL | HCAG | Main and Trinity Streets | Widen or Improve Shoulder | 491772.25 | 442595 | 2008-01-06 | 0 | 2012-03-16 | 2013-04-30 | 442595 | Authorized | Authorized | No | Closed | Federal | 0
H11-01-014 | 11 | 0 | 1 | Ukiah | Mendocino County | RURAL | Mendocino COG | Various intersections throughout the city: State St at Talmage Rd, E. Gobbi St at S. Orchard Ave, Perkins St at Hospital Dr, Airport Park Blvd at Commerce Dr, and Airport Park Blvd at Talmage Rd. | Install traffic signal hardware, improve signal timing and coordination and provide protected left-turn phases. | 302900 | 151450 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2024) | Past due (due 3/31/2026) | Yes (PE & CON) | Not Started | State | 0
HSIP5-01-003 | 5 | 5049026 | 1 | Ukiah | Mendocino County | RURAL | Mendocino COG | State St. between Henry St. and Mill St. | Modify traffic signals; install "road diet" | 5794663.84 | 900000 | 2015-01-08 | 0 | 2019-09-04 | 2023-02-09 | 900000 | Authorized | Authorized | No | Closed | Federal | 0
H11-01-015 | 11 | 5082069 | 1 | Willits | Mendocino County | RURAL | Mendocino COG | Nine (9) roadway segments including N Main St entire segment; Sherwood Rd from Main St to city limit; E Commercial St from S Main St to 1000' E of S Lenore Ave; McKinley St; E San Francisco Ave from Railroad Ave to City Limit; Hazel St from Main Street to Locust St (School Zone). | Install or upgrade regulatory or warning signs with new fluorescent sheeting; install dynamic and variable speed warning signs and install edgelines and center lines. | 212300 | 191070 | 2024-05-15 | 0 | 0 | 0 | 14220 | Authorized | Due by 3/31/2027 | No | PE | State | 0
H11-01-016 | 11 | 5082070 | 1 | Willits | Mendocino County | RURAL | Mendocino COG | Main St & East San Francisco St, W Valley Rd & Main St, and Main St & Commercial St. | Upgrade the signal hardware, install or upgrade signs and pavement markings and crosswalks. Install APS Push buttons and upgrade controllers and ped signal head mounts. | 250000 | 225000 | 2024-05-15 | 0 | 0 | 0 | 17280 | Authorized | Due by 3/31/2027 | No | PE | State | 0
HSIP1-02-002 | 1 | 5321013 | 2 | Anderson | Shasta County | SRTA | Shasta RTPA | Intersection Of Sr 273 And Alexander Avenue/3Rd Street. | Cooperative Project With Caltrans. Install Traffic Signal And Improve Turning Lanes | 1470885.72 | 661794.2 | 2008-03-18 | 2010-05-12 | 2010-05-12 | 2013-02-26 | 661794.2 | Authorized | Authorized | No | Closed | Federal | 0
H11-02-001 | 11 | 5907085 | 2 | Lassen County | Lassen County | RURAL | Lassen LTC | 1.2 miles of CR A27 (Center Road) from 700ft west of Johnstonville Road to 1,500ft east of Cramer Lane in central unincorporated Lassen County. | Install edge rumble strips, centerline rumble strips and high friction surface treatment along length of corridor and advance curve warning and chevrons signs at two curves. | 323500 | 291150 | 0 | 0 | 0 | 0 | 0 | No PE | Due by 9/30/2026 | No | Not Started | State | 0
H9-02-001 | 9 | 5907073 | 2 | Lassen County | Lassen County | RURAL | Lassen LTC | On Janesville Grade, County Road 208, at eight (8) locations. | Upgrade heavily damaged W-Beam type guard railing with wood posts (mainly due to snowplowing activities and logging truck traffic) to Midwest Guardrail System with metal posts and mitigate exposed ends with proper termination ends. | 746700 | 706700 | 0 | 0 | 2022-02-24 | 0 | 706700 | No PE | Authorized | No | CON | Federal | 1
HRRR1-02-009 | 1 | 5907049 | 2 | Lassen County | Lassen County | RURAL | Lassen LTC | From the intersection of SR 44 and Mooney Rd. (CR A21) 3.92 miles to beginning of project and 4.44 miles to end of project | Realign Roadway | 1475823.94 | 1317888.81 | 2007-09-12 | 2012-12-11 | 2015-08-27 | 2020-10-14 | 1317888.81 | Authorized | Authorized | No | Closed | Federal | 0
HRRR1-02-003 | 1 | 5903041 | 2 | Modoc County | Modoc County | RURAL | Modoc LTC | CR 54, 4 miles Southwest of Alturas | Apply high friction surface treatment; widen shoulders; install rumble strips; install chevron signs | 588887.78 | 529998.97 | 2007-09-12 | 0 | 2016-03-08 | 2018-10-22 | 529998.97 | Authorized | Authorized | No | Closed | Federal | 0
HRRR2-02-004 | 2 | 5903047 | 2 | Modoc County | Modoc County | RURAL | Modoc LTC | County Road 55 North of Alturas | Widen shoulder; apply high friction surface treatment; install chevron signs; install delineation | 926176.38 | 832169.05 | 2009-03-26 | 0 | 2016-06-22 | 2018-12-21 | 832169.05 | Authorized | Authorized | No | Closed | Federal | 0
HSIP2-02-002 | 2 | 5903045 | 2 | Modoc County | Modoc County | RURAL | Modoc LTC | County Road 54 From Cr 71 To Alturas City Limits | Widen Shoulders | 222573.96 | 200316.55 | 2009-02-09 | 0 | 2014-07-09 | 2016-10-20 | 200316.55 | Authorized | Authorized | No | Closed | Federal | 0
H8-02-001 | 8 | 5909113 | 2 | Plumas County | Plumas County | RURAL | Plumas LTC | Gold Lake Forest Highway (CR 519) from the Sierra/Plumas County line north to the intersection with State Route 89 near Graeagle. | Upgrade existing guardrails. | 1430141.03 | 1379117.17 | 2017-09-05 | 0 | 2020-02-04 | 2023-05-26 | 1379117.17 | Authorized | Authorized | No | Closed | Federal | 0
HRRR1-02-012 | 1 | 5909084 | 2 | Plumas County | Plumas County | RURAL | Plumas LTC | Portola-McClears Rd. (CR 114), County Route A15, PM 0.7 to 5.8 | Reconstruction (combinations & miscellaneous) | 631219.44 | 530865.01 | 2007-09-12 | 0 | 2012-04-26 | 2016-06-22 | 530865.01 | Authorized | Authorized | No | Closed | Federal | 0
H10-02-001 | 10 | 5068065 | 2 | Redding | Shasta County | SRTA | Shasta RTPA | 4 Focus Areas including 6 Intersections: Continental St/Butte St; Placer St/Continental St; Placer St/East St Court St/Tehama St; South St/ California St; South St/ Market St. | Provide left turn lanes and left turn protected phasing where none exists at selected intersections. Install striping between intersections to facilitate intersection modifications. | 1201000 | 1080900 | 2021-09-20 | 0 | 2024-08-26 | 0 | 1080900 | Authorized | Authorized | No | CON | State | 0
H10-02-002 | 10 | 5068066 | 2 | Redding | Shasta County | SRTA | Shasta RTPA | 17 Intersections throughout the City. | Install new intersection safety lighting where none exists and correct deficient existing lighting at un-signalized intersections. | 849100 | 840609 | 2021-09-20 | 0 | 2024-07-17 | 0 | 840609 | Authorized | Authorized | No | CON | State | 0
H8-02-002 | 8 | 5068057 | 2 | Redding | Shasta County | SRTA | Shasta RTPA | Churn Creek Road between Hartnell Avenue and Cypress Avenue and Maraglia Street between Churn Creek Road and Hilltop Drive. | Complete sidewalk gaps, install ADA ramps, narrow travel lanes to provide standard bike lanes, and add street lighting along Churn Creek Rd. and Maraglia St. Install enhanced crosswalk on Churn Creek Rd with refuge island and RRFB. | 1881786.17 | 1692952.81 | 2018-01-10 | 0 | 2021-01-28 | 2023-10-25 | 1692952.81 | Authorized | Authorized | No | Closed | Federal | 0
H9-02-002 | 9 | 5068062 | 2 | Redding | Shasta County | SRTA | Shasta RTPA | Nine (9) intersections. | Install enhanced pedestrian crossings, including Rectangular Rapid Flashing Beacons (RRFBs), traffic signs, stripes, pavement markings, pedestrian refuge islands, and construct curb ramps. | 1225743.4 | 1211883.32 | 2019-09-10 | 0 | 2022-03-04 | 2024-05-06 | 1211883.32 | Authorized | Authorized | No | Closed | Federal | 0
HSIP1-02-001 | 1 | 5068019 | 2 | Redding | Shasta County | SRTA | Shasta RTPA | South Bonnyview Rd From The Sacramento River To Sr 273. | Install Street Safety Lighting; Widen Shoulder; Install Bike Lanes. | 17909242.07 | 810000 | 0 | 0 | 2007-09-12 | 2012-01-18 | 810000 | No PE | Authorized | No | Closed | Federal | 0
HSIP2-02-001 | 2 | 5068026 | 2 | Redding | Shasta County | SRTA | Shasta RTPA | Buenaventura Ave. From 400' West Of Railroad Ave. To Sr 273 | Construct Curb, Gutter And Sidewalk; Install Safety Lighting, Signing And Striping For Bike Lane; Widen Pavement And Shoulders. | 1056387.55 | 545678.82 | 2009-01-14 | 0 | 2010-06-02 | 2012-03-05 | 545678.82 | Authorized | Authorized | No | Closed | Federal | 0
HSIP3-02-001 | 3 | 5068030 | 2 | Redding | Shasta County | SRTA | Shasta RTPA | Intersection Of Old Oregon Trail And Oasis Rd. | Improve Left-Turn Storage And Sight Distance; Install Overhead Flashing Signal | 960400.36 | 857812.67 | 2010-09-01 | 0 | 2013-08-07 | 2022-06-07 | 857812.67 | Authorized | Authorized | No | Closed | Federal | 0
HSIP4-02-002 | 4 | 5068044 | 2 | Redding | Shasta County | SRTA | Shasta RTPA | Lake Blvd. between SR 299 and Northpoint Dr. | Construct raised median; install striping and pavement markings; reconfigure traffic lanes | 489794.84 | 399466.27 | 2011-08-30 | 0 | 2013-05-17 | 2016-12-12 | 399466.27 | Authorized | Authorized | No | Closed | Federal | 0
HSIP4-02-004 | 4 | 5068043 | 2 | Redding | Shasta County | SRTA | Shasta RTPA | Buenaventura Blvd. between Placer St. and Lakeside Dr. | Construct curb, gutter, sidewalk and street lighting on East side; Continuous center turn lane, one additional travel lane south bound on West side; Bike lanes on both sides | 1314357.55 | 461600 | 2011-08-30 | 0 | 2015-03-16 | 2017-07-24 | 461600 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-02-001 | 5 | 5068049 | 2 | Redding | Shasta County | SRTA | Shasta RTPA | East Cypress Ave. / Rosemary Ave. and East Cypress Ave. / Beverly Dr. | Install raised medians, rapid flashing beacons, and pavement markings | 369393.79 | 302660.64 | 2013-10-29 | 0 | 2015-07-01 | 2017-10-12 | 302660.64 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-02-002 | 5 | 5068050 | 2 | Redding | Shasta County | SRTA | Shasta RTPA | Churn Creek Rd. from Bodenhammer Blvd to the bridge over Boulder Creek | Widen roadway | 720000 | 647999.99 | 2013-10-29 | 0 | 2016-01-21 | 2017-10-13 | 647999.99 | Authorized | Authorized | No | Closed | Federal | 0
HSIP6-02-001 | 6 | 5068051 | 2 | Redding | Shasta County | SRTA | Shasta RTPA | Various locations along Victor Ave between Enterprise Park and Churn Creek | Road diet (reduce travel lanes); install raised median islands, pedestrian pathway, lighting, and installation of two roundabouts | 2486804.62 | 2418166.26 | 2014-07-31 | 0 | 2016-09-07 | 2021-09-27 | 2418166.26 | Authorized | Authorized | No | Closed | Federal | 0
HSIP6-02-002 | 6 | 5068052 | 2 | Redding | Shasta County | SRTA | Shasta RTPA | On Old Oregon Trail between Midland Dr and Bear Mountain Rd | Widen and pave shoulder, horizontal curve realignment and drainage improvements | 3174000 | 2603610 | 2014-07-21 | 2022-08-08 | 2024-06-10 | 0 | 2603610 | Authorized | Authorized | No | CON | Federal | 0
HSIP7-02-002 | 7 | 5068054 | 2 | Redding | Shasta County | SRTA | Shasta RTPA | On Hartnell Avenue between Churn Creek Road and Victor Avenue | Provide two mid-block enhanced crossing locations, buffered bike lanes, and provide accessible pedestrian facilities including tightening curb radius and completing sidewalk gaps, and pedestrian signal control equipment | 3544086.47 | 2389072 | 2016-06-20 | 0 | 2020-03-13 | 2023-09-18 | 2389072 | Authorized | Authorized | No | Closed | Federal
HRRR1-02-005 | 1 | 5906084 | 2 | Shasta County | Shasta County | SRTA | Shasta RTPA | Whitmore Road - 0.3 miles west of Fern Road to South Cow Creek Road | Widen or Improve Shoulder | 1444235.8 | 899999.93 | 2007-08-11 | 0 | 2012-07-25 | 2015-01-16 | 899999.93 | Authorized | Authorized | No | Closed | Federal | 0
HRRR2-02-006 | 2 | 5906091 | 2 | Shasta County | Shasta County | SRTA | Shasta RTPA | On Union School Road from Tierra Oaks Drive to Old Oregon Trail | Widen shoulders; improve bridge rail and install approach rail at the West Fork of Stillwater Creek; install guardrail at various locations | 924155.01 | 804482.15 | 2009-01-14 | 0 | 2011-07-06 | 2015-06-11 | 804482.15 | Authorized | Authorized | No | Closed | Federal | 0
HRRR2-02-007 | 2 | 5906092 | 2 | Shasta County | Shasta County | SRTA | Shasta RTPA | On Olinda Road from 0.3 miles west of the City of Anderson city limit to a location 2.1 miles west | Widen shoulders; install guardrail at various locations | 1365353.43 | 1112308.35 | 2009-01-15 | 2013-02-14 | 2013-11-20 | 2016-02-25 | 1112308.35 | Authorized | Authorized | No | Closed | Federal | 0
HRRR2-02-008 | 2 | 5906093 | 2 | Shasta County | Shasta County | SRTA | Shasta RTPA | Hawthorne Avenue from Happy Valley Road to Dixieland Lane. | Widen shoulders; install guard rail at various locations | 1526098.61 | 1141459.57 | 2009-01-14 | 2012-07-25 | 2013-11-08 | 2016-02-25 | 1141459.57 | Authorized | Authorized | No | Closed | Federal | 0
HSIP4-02-003 | 4 | 5906110 | 2 | Shasta County | Shasta County | SRTA | Shasta RTPA | Dry Creek Rd., from 800' S of Sagebrush Trail to 3000' N of Elk Trail East | Pave shoulders; replace guardrail | 989027.03 | 685800 | 2011-08-25 | 0 | 2014-02-03 | 2015-08-28 | 685800 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-02-003 | 5 | 5906118 | 2 | Shasta County | Shasta County | SRTA | Shasta RTPA | On Gas Point Road between Ludwig Gulch and Michael Street | Widen roadway (add two-way left-turn lane and paved shoulders) | 1662400.25 | 1270499 | 2014-03-12 | 2017-02-22 | 2018-05-28 | 2020-05-14 | 1270499 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-02-004 | 5 | 5906115 | 2 | Shasta County | Shasta County | SRTA | Shasta RTPA | Olinda Rd. between Sammy Ln. and Greenleaf Ln. | Widen and pave shoulders | 1576848.27 | 1095078.98 | 2013-05-28 | 2015-10-29 | 2018-06-14 | 2020-06-26 | 1095078.98 | Authorized | Authorized | No | Closed | Federal | 0
HSIP6-02-003 | 6 | 5906120 | 2 | Shasta County | Shasta County | SRTA | Shasta RTPA | On Deschutes Rd between Balls Ferry Rd and Beatie Rd | Widen and pave shoulders | 2435912.49 | 1788497.99 | 2014-04-09 | 0 | 2018-05-22 | 2020-06-26 | 1788497.99 | Authorized | Authorized | No | Closed | Federal | 0
HSIP6-02-004 | 6 | 5906122 | 2 | Shasta County | Shasta County | SRTA | Shasta RTPA | On Deschutes Rd between Beatie Rd and Brundage Rd | Widen and pave shoulders | 3605429.86 | 1647000 | 2014-04-01 | 2019-04-29 | 2021-04-01 | 2023-07-07 | 1647000 | Authorized | Authorized | No | Closed | Federal | 0
HSIP7-02-003 | 7 | 5906128 | 2 | Shasta County | Shasta County | SRTA | Shasta RTPA | Riverland Drive from Knighton Road to 2 miles south in the unincorporated area of Shasta County | Widen existing roadway by paving shoulders | 1947098 | 1046700 | 2016-01-26 | 2022-02-16 | 2022-05-12 | 2023-10-16 | 1046700 | Authorized | Authorized | No | Closed | Federal
H10-02-003 | 10 | 5474020 | 2 | Shasta Lake | Shasta County | SRTA | Shasta RTPA | Three locations: State Route 151 & Median Avenue; State Route 151 & Grand Coulee (Mid-Block); and State Route 151 & Shasta Way. | Install pedestrian activated rectangular rapid flashing beacons and other associated crosswalk enhancements. | 250000 | 250000 | 2021-09-14 | 0 | 2022-12-12 | 2024-10-08 | 250000 | Authorized | Authorized | No | Closed | State | 0
H8-02-003 | 8 | 5474018 | 2 | Shasta Lake | Shasta County | SRTA | Shasta RTPA | Various locations throughout the City of Shasta Lake, including Lake Boulevard, Vallecito Street, Ashby Road, Deer Creek Avenue, Main Street, Duval Road, Buckeye Street, and Pine Grove Avenue. | Upgrade existing guardrails. | 481192.36 | 481191.7 | 2018-01-10 | 0 | 2020-01-16 | 2021-02-18 | 481191.7 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-02-005 | 5 | 5902078 | 2 | Siskiyou County | Siskiyou County | RURAL | Siskiyou LTC | On Old Hwy 99 at Mile Post 17.04 (0.8 mile W NW of Grenada and 4.2 miles SW of Yreka) | Replace bridge (HBP funding); realign roadway | 670199.02 | 589554.97 | 0 | 0 | 2017-04-07 | 2020-10-14 | 589554.97 | No PE | Authorized | No | Closed | Federal | 0
H9-02-003 | 9 | 5908104 | 2 | Tehama County | Tehama County | RURAL | Tehama LTC | Five (5) intersections: South Avenue and Rowles Road, South Avenue and Marguerite Avenue, South Avenue and Woodson Avenue, Finnell Avenue and 99W, and Capay Road and 99W. | Install splitter-islands on minor road approaches, remove current pavement markings and upgrade intersection pavement markings including a slurry seal, and install flashing beacons as advanced warning on major road approaches. | 950400 | 855360 | 2019-05-31 | 0 | 2024-09-16 | 0 | 855317.3 | Authorized | Authorized | No | CON | Federal | 1
H9-02-004 | 9 | 5908105 | 2 | Tehama County | Tehama County | RURAL | Tehama LTC | Two intersections on Gallagher Avenue: Gallagher Avenue and Houghton Avenue, and Gallagher Avenue and Edith Avenue. | Install flashing beacons as advanced warning, convert to all way stop control, and install transverse rumble strips on major road approaches. | 337900 | 304110 | 2019-06-17 | 0 | 2024-09-16 | 0 | 303264.32 | Authorized | Authorized | No | CON | Federal | 1
H9-02-005 | 9 | 5908106 | 2 | Tehama County | Tehama County | RURAL | Tehama LTC | A 3.5 mile segment of Lake California Drive in Cottonwood, from 0.25 mile south of Main Street to Sawtooth Drive. | Rehabilitation and reconstruction. | 1669700 | 1502730 | 2019-06-18 | 2025-07-02 | 0 | 0 | 362790 | Authorized | Due by 6/30/2029 | No | ROW | Federal | 1
HRRR1-02-010 | 1 | 5908074 | 2 | Tehama County | Tehama County | RURAL | Tehama LTC | San Benito Avenue 0.7 miles South of Gerber | Realign Roadway; Superelevation Improvement | 1084186.21 | 889012.1 | 2007-09-12 | 2010-07-12 | 2014-01-14 | 2021-10-21 | 889012.1 | Authorized | Authorized | No | Closed | Federal | 0
HRRR1-02-011 | 1 | 5908075 | 2 | Tehama County | Tehama County | RURAL | Tehama LTC | On Rancho Tehama Rd. approximately 1.5 miles West of Paskenta Rd. | Realign Roadway | 509436.88 | 458493.07 | 2007-09-12 | 2010-03-26 | 2012-11-20 | 2015-11-04 | 458493.07 | Authorized | Authorized | No | Closed | Federal | 0
HSIP1-02-003 | 1 | 5908072 | 2 | Tehama County | Tehama County | RURAL | Tehama LTC | Old Hwy 99W From Gyle Road To Los Flores Avenue. | Install Rumble Strip On Both Sides Of Road. | 63927 | 57534.27 | 2007-09-12 | 0 | 2008-01-03 | 2010-04-02 | 57534.27 | Authorized | Authorized | No | Closed | Federal | 0
HSIP1-02-004 | 1 | 5908073 | 2 | Tehama County | Tehama County | RURAL | Tehama LTC | Orangewood Rd Approx 0.6 Miles West Of Hall Road At Tehama Colusa Canal Crossing | Improve Stopping Sight Distance With Vertical Alignment Correction And Tree Removal. | 969144.59 | 798726.49 | 2007-09-12 | 2010-04-06 | 2014-01-08 | 2021-10-21 | 798726.49 | Authorized | Authorized | No | Closed | Federal | 0
HSIP2-02-004 | 2 | 5908078 | 2 | Tehama County | Tehama County | RURAL | Tehama LTC | Intersections Of Gerber Rd. With Sr 99W And San Benito Ave. | Install Left Turn Lanes | 1941579.52 | 1368494.13 | 2009-01-14 | 2011-01-06 | 2016-02-22 | 2021-10-21 | 1368494.13 | Authorized | Authorized | No | Closed | Federal | 0
HSIP2-02-005 | 2 | 5908079 | 2 | Tehama County | Tehama County | RURAL | Tehama LTC | Intersection Of South Ave. And Hall Rd. | Install Left-Turn Lane & Acceleration Lane At Non-Signalized Intersection | 1026198.03 | 691197.16 | 2009-01-21 | 0 | 2013-05-16 | 2021-11-04 | 691197.16 | Authorized | Authorized | No | Closed | Federal | 0
HSIP2-02-006 | 2 | 5908080 | 2 | Tehama County | Tehama County | RURAL | Tehama LTC | Intersection Of Hall Rd. And Hoag Rd. | Construct New Left-Turn Lane; Realign Intersection | 844785.86 | 542287 | 2009-01-14 | 0 | 2012-12-17 | 2021-11-18 | 542287 | Authorized | Authorized | No | Closed | Federal | 0
HSIP4-02-001 | 4 | 5908089 | 2 | Tehama County | Tehama County | RURAL | Tehama LTC | South Ave. between Woodson Br. and SR 99 | Widen shoulders; upgrade striping and pavement markings | 1065466.31 | 917982.93 | 2011-06-09 | 0 | 2014-07-29 | 2018-09-06 | 917982.93 | Authorized | Authorized | No | Closed | Federal | 0
H12-02-001 | 12 | 5905140 | 2 | Trinity County | Trinity County | RURAL | Trinity LTC | Various locations throughout Trinity County. | Install stripes utilizing weather resistant paint and optical elements to achieve retroreflectivity at night. | 5933600 | 5340240 | 2026-01-20 | 0 | 0 | 0 | 243000 | Authorized | Due by 3/31/2028 | No | PE | Federal | 1
H8-02-004 | 8 | 5905118 | 2 | Trinity County | Trinity County | RURAL | Trinity LTC | Nineteen (19) locations throughout Trinity County. | Update Bridge Rail Approach Terminal End Systems (2,690 lineal feet of guardrail and 67 terminal end treatments). | 1480106 | 1480106 | 2017-10-13 | 0 | 2022-02-10 | 0 | 1480106 | Authorized | Authorized | No | CON | Federal | 1
H8-02-005 | 8 | 5905119 | 2 | Trinity County | Trinity County | RURAL | Trinity LTC | Various locations on Rush Creek Road. | Install High Friction Surface Treatments | 1037969.41 | 1037221.02 | 2018-02-05 | 0 | 2022-12-27 | 2026-03-26 | 1037221.02 | Authorized | Authorized | No | Closed | Federal | 0
HSIP2-02-003 | 2 | 5905078 | 2 | Trinity County | Trinity County | RURAL | Trinity LTC | Ruth Zenia Rd At Post Mile 3.4 | Install Guardrail | 200967.31 | 157903.33 | 2009-03-26 | 0 | 2012-05-18 | 2013-12-17 | 157903.33 | Authorized | Authorized | No | Closed | Federal | 0
HSIP3-02-002 | 3 | 5905088 | 2 | Trinity County | Trinity County | RURAL | Trinity LTC | County Rd. 105 (Trinity Dam Blvd.) 2.4 Miles North Of Rush Creek Rd. | Install Guardrail | 83675.07 | 65541 | 2010-07-20 | 0 | 2013-06-20 | 2015-11-04 | 65541 | Authorized | Authorized | No | Closed | Federal | 0
HSIP3-02-003 | 3 | 5905089 | 2 | Trinity County | Trinity County | RURAL | Trinity LTC | County Rd. 105 (Trinity Dam Blvd.) 0.1 To 1.3 Miles South Of Mtn. View Rd. | Install Warning Signs | 29652.45 | 20488.48 | 2010-07-22 | 0 | 2013-05-23 | 2014-11-12 | 20488.48 | Authorized | Authorized | No | Closed | Federal | 0
HSIP6-02-005 | 6 | 5905099 | 2 | Trinity County | Trinity County | RURAL | Trinity LTC | Various locations throughout Trinity County | Upgrade striping | 1203696.52 | 1152284.35 | 2014-06-08 | 0 | 2016-10-21 | 2025-01-15 | 1152284.35 | Authorized | Authorized | No | Closed | Federal | 0
HSIP6-02-006 | 6 | 5905100 | 2 | Trinity County | Trinity County | RURAL | Trinity LTC | Various locations throughout Trinity County | Upgrade striping | 1240496.1 | 1203368.48 | 2014-06-08 | 0 | 2016-11-01 | 2024-11-18 | 1203368.48 | Authorized | Authorized | No | Closed | Federal | 0
HSIP6-02-007 | 6 | 5905101 | 2 | Trinity County | Trinity County | RURAL | Trinity LTC | Various locations throughout Trinity County | Install signs | 358587.56 | 307949.2 | 2014-06-08 | 0 | 2018-07-13 | 2023-10-19 | 307949.2 | Authorized | Authorized | No | Closed | Federal | 0
H10-03-001 | 10 | 5912123 | 3 | Butte County | Butte County | BCAG | BCAG | Skyway from Toadtown Way to Humbug Summit Rd., Forbestown Rd from Rex Ln to Weiss Hill Rd, Lime Saddle Rd, Hurles Cir, Pentz Rd, Humboldt Rd, Stringtown Rd and Hurleton Sweeds Flat Rd. | Update existing guardrail. Upgrade post to metal. | 1040000 | 1040000 | 2021-06-24 | 0 | 2023-09-11 | 2025-08-15 | 1040000 | Authorized | Authorized | No | Closed | Mix | 1
H10-03-002 | 10 | 5912126 | 3 | Butte County | Butte County | BCAG | BCAG | Lincoln Blvd from Palermo Rd to Monte Vista Ave, Larkin Rd from E Rio Bonito Rd to Oroville City Limits, Dayton Rd, and E. Gridley Rd | Upgrade existing 4” painted edge lines to 6” thermoplastic stripe. | 280600 | 250000 | 2021-11-19 | 0 | 2022-09-01 | 2025-07-08 | 250000 | Authorized | Authorized | No | Closed | State | 0
H11-03-001 | 11 | 5912131 | 3 | Butte County | Butte County | BCAG | BCAG | Various locations along: Forbestown Road, Coutolenc Road, Skyway, Cohasset Road, Palermo Honcut Hwy, and Lwr Honcut Road. | Upgrading existing 4 inch painted edge lines to 6 inch thermoplastic edge lines. | 803246 | 722922 | 2023-09-14 | 0 | 2025-07-14 | 0 | 722922 | Authorized | Authorized | No | CON | Federal | 1
H11-03-002 | 11 | 5912129 | 3 | Butte County | Butte County | BCAG | BCAG | Various locations within designated road segments throughout Butte County: Forbestown Rd (2), Bald Rock Rd (2), W Biggs Gridley Rd (2), Cherokee Rd (2), Lower Wyandotte Rd, Dogtown Rd, Almond Ave, Colter Way, Skyway (2), Dalton Way, and Old Olive Hwy. | Install High Friction Surface Treatment (HFST) to identified high-risk bends and turns within designated roadway sections. | 1150000 | 1035000 | 2023-04-26 | 0 | 2026-02-27 | 0 | 1035000 | Authorized | Authorized | No | CON | State | 0
H11-03-003 | 11 | 5912130 | 3 | Butte County | Butte County | BCAG | BCAG | Various road sections throughout Butte County. | Road Safety Signing Audit (RSSA) Project. Audit existing sign types, locations, retroreflectivity and size per MUTCD, identify missing signs per MUTCD and modify signage accordingly. | 1440500 | 1296450 | 2023-05-02 | 0 | 0 | 0 | 153000 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE | State | 0
H11-03-004 | 11 | 5912133 | 3 | Butte County | Butte County | BCAG | BCAG | Various locations throughout Butte County: E Gridley Rd (at Kirk Rd), La Porte Rd (west of Loma Rica Rd), Lower Wyandotte Rd (west of Foothill Blvd), and River Rd (north of the Big Chico Creek Access), Pacific Heights Rd (at Ophir Rd), and Welsh Rd. | Upgrade Metal Beam Guardrails to Midwest Guardrail System. Upgrade wooden posts to metal in order to alleviate fire risk to guardrails. Upgrade end treatments to conform with current MUTCD standards. | 250000 | 225000 | 2023-08-29 | 0 | 2026-02-27 | 0 | 225000 | Authorized | Authorized | No | CON | State | 0
H12-03-001 | 12 | 5912124 | 3 | Butte County | Butte County | BCAG | BCAG | Ten road sections: Keefer Rd, Garner Ln, Chico River Rd, Dayton Rd, Durham Dayton Hwy, Ord Ferry Rd, Richvale Hwy, W. Biggs Gridley Rd, E. Gridley Rd, and Larkin Rd. | Upgrade existing 4 inch centerlines and edgelines to 6 inch thermoplastic striping. | 1359900 | 1223910 | 2026-03-02 | 0 | 0 | 0 | 27000 | Authorized | Due by 3/31/2028 | No | PE | Federal | 1
H12-03-002 | 12 | 5912145 | 3 | Butte County | Butte County | BCAG | BCAG | Various road sections throughout Butte County. | Peform road safety signing audit (RSSA) and modify signage. | 2606900 | 2346210 | 2026-03-02 | 0 | 0 | 0 | 432000 | Authorized | Due by 3/31/2028 | No | PE | Federal | 1
H12-03-003 | 12 | 5912143 | 3 | Butte County | Butte County | BCAG | BCAG | Various throughout Butte County: 10th St (at Feather Ave), Pacific Heights Rd (Oroville Wildlife Area), Pacific Heights Rd (N of Georgia Pacific Way), B St (E of Biggs), Richvale Hwy (E of Richvale), Lower Wyandotte Rd (between Country Oaks Dr). | Upgrade Metal Beam Guardrails (MBGR) to Midwest Guardrail System (MGS). | 500000 | 450000 | 2026-02-02 | 0 | 0 | 0 | 82350 | Authorized | Due by 3/31/2028 | No | PE | State | 0
H12-03-004 | 12 | 5912144 | 3 | Butte County | Butte County | BCAG | BCAG | Various locations within designated road segments throughout Butte County: Skyway (3), Columbine Rd, Steiffer Rd, Colter Way, Neal Road. | Add high friction surface treatment (HFST). | 600000 | 540000 | 2026-02-02 | 0 | 0 | 0 | 90000 | Authorized | Due by 3/31/2028 | No | PE | State | 0
H8-03-001 | 8 | 5912109 | 3 | Butte County | Butte County | BCAG | BCAG | Skyway between Chico City Limits and Paradise Town Limits and Cohasset Rd between Chico City Limits and end of existing guardrail near Jack Rabbit Flat Rd. | Upgrade existing guardrails. | 285430.73 | 285430.73 | 2017-05-08 | 2019-04-02 | 2019-10-28 | 2021-03-04 | 285430.73 | Authorized | Authorized | No | Closed | Federal | 0
H9-03-001 | 9 | 5912114 | 3 | Butte County | Butte County | BCAG | BCAG | Cohasset Rd between Nicalog Rd and end of existing guardrail near Jack Rabbit Flat Rd. | Update existing guardrail. | 597179.08 | 597179.08 | 2019-07-17 | 0 | 2022-04-14 | 2023-11-28 | 597179.08 | Authorized | Authorized | No | Closed | Federal | 1
HSIP2-03-002 | 2 | 5912079 | 3 | Butte County | Butte County | BCAG | BCAG | Lincoln Blvd. From Elgin St. To Arnold Ave. | Install Raised Concrete Medians With Curb Ramps And Left Turn Pockets; Construct Ped Refuge Area. | 1063978.4 | 787240.49 | 0 | 0 | 2010-10-14 | 2012-11-01 | 787240.49 | No PE | Authorized | No | Closed | Federal | 0
HSIP3-03-002 | 3 | 5912087 | 3 | Butte County | Butte County | BCAG | BCAG | Lincoln Blvd. from 50' North of Idora St. to 100' South of Arnold Ave. | Construct Curb, Gutter, Sidewalk, And Curb Ramps; Install Crosswalk Warning Signs With Integrated Flashing Beacons At All Three Midblock Crossings, And Class II Bike Lane Markings | 1913401.26 | 872196.98 | 0 | 0 | 2016-01-13 | 2018-03-16 | 872196.98 | No PE | Authorized | No | Closed | Federal | 0
HSIP4-03-002 | 4 | 5912094 | 3 | Butte County | Butte County | BCAG | BCAG | Skyway Rd. between the city limits of Chico and Paradise | Install rumble stripes and speed feedback signs | 1509954.11 | 616334.88 | 2011-12-11 | 0 | 2014-06-12 | 2016-05-31 | 616334.88 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-03-001 | 5 | 5912099 | 3 | Butte County | Butte County | BCAG | BCAG | Durham Pentz Rd. between SR 99 and SR 191 | Install rumble stripes, striping, and pavement markers | 416976.4 | 375278.74 | 2015-03-25 | 0 | 2015-07-01 | 2017-10-20 | 375278.74 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-03-002 | 5 | 5912100 | 3 | Butte County | Butte County | BCAG | BCAG | East Gridley Rd./Larkin Rd. | Install traffic signals | 1404906.28 | 1187778.76 | 0 | 0 | 2017-11-14 | 2019-11-06 | 1187778.76 | No PE | Authorized | No | Closed | Federal | 0
H12-03-005 | 12 | 5037047 | 3 | Chico | Butte County | BCAG | BCAG | Various intersections throughout the City of Chico. | Install leading pedestrian interval (LPI) and Audible Pedestrian System (APS). | 388700 | 349830 | 0 | 0 | 2025-05-06 | 0 | 349785 | No PE | Authorized | No | CON | State | 0
H8-03-002 | 8 | 5037034 | 3 | Chico | Butte County | BCAG | BCAG | Sixty (60) Intersections throughout the City Limits | Upgrading 60 intersections, with existing pedestrian signals, to include countdown heads. | 176871.07 | 175891.56 | 2017-07-01 | 0 | 2018-05-02 | 2023-03-23 | 175891.56 | Authorized | Authorized | No | Closed | Federal | 0
H8-03-003 | 8 | 5037035 | 3 | Chico | Butte County | BCAG | BCAG | The Intersection at SR-99 NB On-Off Ramps/ Eaton Road / Hicks Lane. | Construct a 5-leg roundabout intersection with adequate bike and pedestrian access. | 5841252.25 | 4069763 | 0 | 0 | 2021-03-30 | 2023-02-20 | 4069763 | No PE | Authorized | No | Closed | Federal | 0
HSIP7-03-001 | 7 | 5037029 | 3 | Chico | Butte County | BCAG | BCAG | City of Chico, at various locations throughout City Limits | Citywide systemic safety improvements including installation of improved signal hardware at signalized intersections, pedestrian crossings at uncontrolled locations, and upgraded intersection pavement markings at non-signalized intersections | 1389237.88 | 1250252.26 | 2016-04-11 | 0 | 2021-06-22 | 2024-04-03 | 1250252.26 | Authorized | Authorized | No | Closed | Federal
HSIP7-03-002 | 7 | 5037030 | 3 | Chico | Butte County | BCAG | BCAG | On Esplanade between Cohasset Rd and Memorial Way | Install emergency vehicles preemptive system along Esplanade. Construct ladder style crosswalks, ADA curb ramps, raised median, and rapid rectangular flashing beacons at W. 8th Ave and Esplanade intersection. | 392884.69 | 357699 | 2016-04-11 | 0 | 2018-03-22 | 2021-12-29 | 357699 | Authorized | Authorized | No | Closed | Federal
HSIP7-03-003 | 7 | 6203064 | 3 | Chico | Butte County | BCAG | BCAG | Intersections of Nord Ave. (SR-32) and West Sacramento Ave | Caltrans will construct two signal modifications on SR32 at the intersections of West Sacramento (west) and West Sacramento (East) in the City of Chico (at PM 7.6/7.9) | 3405425 | 1200000 | 0 | 0 | 2021-03-30 | 2025-08-07 | 1200000 | Not Tracked | Authorized | No | Closed | Federal
H11-03-005 | 11 | 5475050 | 3 | Citrus Heights | Sacramento County | SACOG | SACOG | Intersections throughout the City of Citrus Heights (36 Signalized Intersections) and Roseville Rd/Butternut Dr to Villaview (unsignalized). | Roseville Road/Butternut Drive intersection multi-modal safety improvements (pavement rehabilitation,bulbouts, left-turn lane, bike lanes, signage and striping) and retroreflective backplates at 36 signalized intersections throughout the City. | 1869700 | 1682730 | 2023-04-06 | 2025-03-18 | 2025-07-16 | 0 | 1682687 | Authorized | Authorized | No | CON | State | 0
H8-03-004 | 8 | 5475041 | 3 | Citrus Heights | Sacramento County | SACOG | SACOG | Various signalized intersections throughout the City of Citrus Heights. | Upgrade all existing 8" and combination vehicle signal indications to 12" indications. Retrofit all pedestrian signal heads to "count-down". Install a pedestrian median fence on three legs of the intersection of Greenback Ln/Auburn Blvd. | 1117820.71 | 199075 | 2017-03-24 | 0 | 2020-01-03 | 2024-03-11 | 199075 | Authorized | Authorized | No | Closed | Federal | 0
HSIP4-03-003 | 4 | 5475029 | 3 | Citrus Heights | Sacramento County | SACOG | SACOG | Sunrise Blvd./Sungarden Dr. | Install traffic signals and sidewalks | 1834600.93 | 899999.99 | 2011-12-06 | 0 | 2014-08-13 | 2017-03-06 | 899999.99 | Authorized | Authorized | No | Closed | Federal | 0
HSIP4-03-006 | 4 | 5475030 | 3 | Citrus Heights | Sacramento County | SACOG | SACOG | Old Auburn Rd. between Fair Oaks Blvd. and Wachtel Way | Widen shoulders; construct Class 1 multi-use trail; install Class II bike lanes | 1400271.66 | 644400 | 2011-06-22 | 0 | 2013-09-03 | 2016-02-25 | 644400 | Authorized | Authorized | No | Closed | Federal | 0
HSIP6-03-001 | 6 | 5475037 | 3 | Citrus Heights | Sacramento County | SACOG | SACOG | On Sunrise Blvd between Woodmore Oaks Dr and Sayonara Dr | Pavement overlay; Construct curb ramp, sidewalk, curb, gutter, drain inlet; Install lighting, traffic signals (interconnect), storm drain, striping, and pavement markings | 2250493 | 840799.99 | 2014-08-21 | 2016-08-19 | 2017-10-20 | 2019-12-10 | 840799.99 | Authorized | Authorized | No | Closed | Federal | 0
H12-03-006 | 12 | 5238079 | 3 | Davis | Yolo County | SACOG | SACOG | On Lake Blvd from Russell Blvd to Arlington Blvd. | Install buffered bike lanes. | 267200 | 240480 | 2026-01-26 | 0 | 0 | 0 | 42930 | Authorized | Due by 3/31/2028 | No | PE | State | 0
H12-03-007 | 12 | 5238080 | 3 | Davis | Yolo County | SACOG | SACOG | Three locations throughout the city. | Install rectangular rapid flashing Beacons; Install and upgrade high visibility pedestrian crossing markings. | 341900 | 307710 | 2026-02-12 | 0 | 0 | 0 | 54900 | Authorized | Due by 3/31/2028 | No | PE | State | 0
HSIP5-03-003 | 5 | 5238053 | 3 | Davis | Yolo County | SACOG | SACOG | Intersetions of Fifth St. with C, D, E, I, J and K Streets. | Install crosswalks and safety lighting | 313894.53 | 199999.99 | 2011-03-14 | 0 | 2013-07-18 | 2016-12-07 | 199999.99 | Authorized | Authorized | No | Closed | Federal | 0
H10-03-003 | 10 | 5925189 | 3 | El Dorado County | El Dorado County | SACOG | El Dorado LTC | Pleasant Valley Rd in El Dorado County excluding State Highway (HWY) 49 | Safety improvements along Pleasant Valley Rd which include HFST along high crash segments, centerline and edgeline striping along the entire length of Pleasant Valley Rd, and other safety improvements. This scope excludes construction within HWY 49. | 3623135 | 3062600 | 2021-11-12 | 2023-05-24 | 2024-04-17 | 0 | 3062600 | Authorized | Authorized | No | CON | State | 0
H10-03-004 | 10 | 5925188 | 3 | El Dorado County | El Dorado County | SACOG | El Dorado LTC | Multiple locations withinin Pollock Pines. | Replace out of compliance guardrail with new guardrail. | 802200 | 802200 | 2021-11-12 | 0 | 2023-05-26 | 2025-11-17 | 802200 | Authorized | Authorized | No | Closed | State | 0
H10-03-006 | 10 | 5925185 | 3 | El Dorado County | El Dorado County | SACOG | El Dorado LTC | Three locations: Sly Park Road at USFC / Sac County School / Sugarloaf Fine Arts Camp Crossing; Pioneer Trail at High Meadow Trail Crosswalk; and Silva Valley Parkway at New York Creek Trail. | Install high visibility crosswalks and rectangular rapid flashing beacons (RRFB). | 250000 | 250000 | 2021-07-14 | 0 | 2023-10-09 | 2026-01-12 | 250000 | Authorized | Authorized | No | Closed | State | 0
H10-03-007 | 10 | 5925186 | 3 | El Dorado County | El Dorado County | SACOG | El Dorado LTC | Pony Express Trail from Carson Road to Sanders Drive (Approx. 24,200 lineal feet of roadway) and on Sly Park Road from Highway 50 to approximately 6,900 lineal feet south (Approx. 6,900 lineal feet of roadway) on both sides of the roadways. | Install approx. 65,000 feet of recessed thermoplastic edge-lines on both sides of the roadways. | 250000 | 250000 | 2021-07-15 | 0 | 2022-07-22 | 0 | 250000 | Authorized | Authorized | No | CON | State | 0
H11-03-006 | 11 | 5925202 | 3 | El Dorado County | El Dorado County | SACOG | El Dorado LTC | Various Locations - Mount Aukum Road MP 0.22, MP 0.72, MP 1.31, and at Middle Fork Cosumnes River; Cameron Park Drive between El Dorado Royale and Oxford; Bass Lake Road at Bass Lake; and Salmon Falls Rd MP 3.72, MP7.15, MP 9.76. | Replace guardrail and end treatment systems at various locations on Mount Aukum Road (E16), Cameron Park Drive, Bass Lake Road, and Salmon Falls Road. | 977900 | 880110 | 2023-11-22 | 0 | 0 | 0 | 117000 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE | State | 0
H12-03-008 | 12 | 5925206 | 3 | El Dorado County | El Dorado County | SACOG | El Dorado LTC | Multiple locations along Lotus Road. | Replace out of compliance guardrail with new guardrail. | 1111100 | 999990 | 2025-07-15 | 0 | 0 | 0 | 90450 | Authorized | Due by 3/31/2028 | No | PE | State | 0
H12-03-009&010 | 12 | 5925175 | 3 | El Dorado County | El Dorado County | SACOG | El Dorado LTC | Ponderosa Road from Foxwood Lane to Mineshaft Lane. | Add a Class II Bike facility; Add a pedestrian sidewalk facility. | 1599000 | 697650 | 0 | 0 | 2025-04-22 | 0 | 697650 | No PE | Authorized | No | CON | State | 0
H8-03-005 | 8 | 5925147 | 3 | El Dorado County | El Dorado County | SACOG | El Dorado LTC | Various locations throughout El Dorado County. | Installation of high friction surface treatment, new thermoplastic striping with enhanced wet night visibility, Raised Pavement Markers (RPMs), and advance warning signs. | 1488147.52 | 1488147.52 | 2017-05-12 | 0 | 2018-10-15 | 2020-12-28 | 1488147.52 | Authorized | Authorized | No | Closed | Federal | 0
H8-03-006 | 8 | 5925148 | 3 | El Dorado County | El Dorado County | TMPO | El Dorado LTC | Intersection of US Highway 50 and Pioneer Trail (PM 71.48) in the community of Meyers in South Lake Tahoe. | Construct a roundabout with pedestrian and bicycle crossings, separated travel lane approaches, curb, gutter, sidewalk, traffic signs, stripes and pavement markings. | 3450400 | 3450400 | 0 | 0 | 2024-07-01 | 0 | 3450400 | No PE | Authorized | No | CON | Federal | 0
H9-03-002 | 9 | 5925169 | 3 | El Dorado County | El Dorado County | SACOG | El Dorado LTC | Intersections of Pleasant Valley Road with Oriental Street, Church Street and Racquet Way; Pleasant Valley Road between Toyan Drive and Pearl Place. | Improve pedestrian safety along Pleasant Valley Road, including enhanced pedestrian crossings at intersections and installation of speed feedback signs. | 492300 | 287500 | 2019-04-16 | 2020-03-25 | 2023-05-10 | 0 | 287500 | Authorized | Authorized | No | CON | Federal | 2
H9-03-003 | 9 | 5925170 | 3 | El Dorado County | El Dorado County | SACOG | El Dorado LTC | At intersections of Pleasant Valley Road with Hanks Exchange Road, Cedar Ravine Road, Zandonella West/Big Cut Road, and Newtown Road. | Clear sight triangle at intersections and install warning signs with flashing beacons near high crash intersections | 732713 | 555130 | 2019-04-16 | 2020-03-30 | 2023-05-10 | 0 | 555130 | Authorized | Authorized | No | CON | Federal | 0
H9-03-004 | 9 | 5925171 | 3 | El Dorado County | El Dorado County | SACOG | El Dorado LTC | Various locations throughout unincorporated El Dorado County. | Install high friction surface treatment, ancillary edge-lines, centerlines, and reflective pavement markers. | 1201374.58 | 1201374.58 | 2019-10-11 | 0 | 2021-04-05 | 2023-03-07 | 1201374.58 | Authorized | Authorized | No | Closed | Federal | 0
H9-03-005 | 9 | 5925172 | 3 | El Dorado County | El Dorado County | TMPO | El Dorado LTC | Multiple locations within the El Dorado County portion of the Tahoe Basin, near South Lake Tahoe. Includes areas along Lake Tahoe Blvd, Pioneer Trail, Black Bart, and View Circle. | Construct and/or reconstruct/upgrade metal beam Cor - 10 style guardrail. | 570602.66 | 570602.66 | 2019-03-27 | 0 | 2020-07-27 | 2022-02-22 | 570602.66 | Authorized | Authorized | No | Closed | Federal | 0
HRRR1-03-020 | 1 | 5925055 | 3 | El Dorado County | El Dorado County | SACOG | El Dorado LTC | Marshall Road, one (1) mile east of the intersection of Hwy 49 and Marshall Road. | Realign Roadway | 539521.48 | 485569.3 | 2007-08-15 | 0 | 2008-05-13 | 2012-07-09 | 485569.3 | Authorized | Authorized | No | Closed | Federal | 0
HRRR1-03-021 | 1 | 5925056 | 3 | El Dorado County | El Dorado County | SACOG | El Dorado LTC | Latrobe Rd., PM 7.0 to 7.35 | Realign Roadway | 1831058.01 | 1280770.73 | 2007-08-15 | 2007-11-02 | 2012-02-28 | 2015-01-27 | 1280770.73 | Authorized | Authorized | No | Closed | Federal | 0
HSIP2-03-015 | 2 | 5925060 | 3 | El Dorado County | El Dorado County | SACOG | El Dorado LTC | Intersection Of Green Valley Rd. And North Shingle Rd. To Tennessee Creek Bridge | Realign Roadway; Add 8 Foot Shoulders; Install Traffic Signal With Left And Right Turn Lanes | 3399428.38 | 707093.39 | 0 | 2009-02-09 | 2010-07-12 | 2015-01-27 | 707093.39 | No PE | Authorized | No | Closed | Federal | 0
HSIP2-03-018 | 2 | 5925061 | 3 | El Dorado County | El Dorado County | SACOG | El Dorado LTC | Intersection Of Pleasant Valley Rd. And Oak Hill Rd. | Widen Shoulders; Construct Left Turn Lane | 1243550.13 | 899485.2 | 2009-01-14 | 2010-05-25 | 2012-08-14 | 2016-10-20 | 899485.2 | Authorized | Authorized | No | Closed | Federal | 0
HSIP3-03-008 | 3 | 5925082 | 3 | El Dorado County | El Dorado County | SACOG | El Dorado LTC | Cold Springs Rd., At The Intersection With Mt. Shasta Ln. Between Pm 3.4 And 3.55 | Realign Roadway; Widen Shoulders; Construct Draininage Improvements; Install Flashing Beacon Warning Signs | 1222506.23 | 828647 | 2010-07-02 | 2013-03-07 | 2015-07-23 | 2018-07-04 | 828647 | Authorized | Authorized | No | Closed | Federal | 0
HSIP3-03-009 | 3 | 5925083 | 3 | El Dorado County | El Dorado County | SACOG | El Dorado LTC | Salmon Falls Rd., South Of The T-Intersection At Glenesk Ln. Between Pm 7.79 And 7.89 | Realign Roadway; Widen Shoulders; Construct Drainage Improvements; Install Flashing Beacon Warning Signs And Rumble Strips | 1715156.47 | 810000 | 2010-07-02 | 2012-09-04 | 2015-05-19 | 2018-01-31 | 810000 | Authorized | Authorized | No | Closed | Federal | 0
HSIP4-03-008 | 4 | 5925092 | 3 | El Dorado County | El Dorado County | SACOG | El Dorado LTC | Cold Springs Rd. between Fox Print Ct. and Skyview Ln. | Modify super-elevation; widen shoulders; install signs and striping | 809731.19 | 515853 | 2011-04-26 | 2013-08-21 | 2015-07-17 | 2018-07-04 | 515853 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-03-004 | 5 | 5925115 | 3 | El Dorado County | El Dorado County | SACOG | El Dorado LTC | Intersections of Green Valley Rd. with Francisco Dr., El Dorado Hills Blvd and Silva Valley Pkwy. | Upgrade traffic signals (interconnect) | 343193.44 | 242700 | 2013-03-07 | 0 | 2014-09-16 | 2016-11-02 | 242700 | Authorized | Authorized | No | Closed | Federal | 0
HSIP7-03-008 | 7 | 6203060 | 3 | El Dorado County | El Dorado County | SACOG | El Dorado LTC | State Route 50 in El Dorado County between Still Meadows Road and Upper Carson Road (from post mile 21.95 to 24.25). | Roadway widening, construction of a roundabout, upgrade intersections and restrict left turn crossing of center line turning movements at multiple intersections, upgrade drainage facilities. | 10498000 | 6342120 | 0 | 2019-02-22 | 2019-10-18 | 0 | 5141900 | Not Tracked | Authorized | No | CON | Federal
H10-03-008 | 10 | 5479073 | 3 | Elk Grove | Sacramento County | SACOG | SACOG | 76 signalized intersections in the City of Elk Grove. | Provide advanced dilemma zone detection for signalized intersection approached with posted speeds of 40 MPH or higher. Replace 8 inch signal heads with 12 inch, and add retro-reflective borders to all signal heads. | 8830200 | 8830200 | 2022-06-01 | 0 | 2024-02-09 | 0 | 8830200 | Authorized | Authorized | No | CON | State | 0
H11-03-007 | 11 | 5479081 | 3 | Elk Grove | Sacramento County | SACOG | SACOG | Uncontrolled crossings: 1. Maranello Drive at Roy Harburger Elementary 2. Gilliam Drive at Scoech Way/Franklin Elementary 3. Iris Meadow Way at Peters Ranch Way/Helen Carr Castello Elementary 4. Laguna Park Drive at Foulks Ranch Elementary | Install Rectangular Rapid Flashing Beacons at uncontrolled crossings at four elementary schools. All four streets have a speed limit of 30 mph and home fronting at least one side of the roadway. | 249700 | 224730 | 2023-10-18 | 0 | 2025-06-11 | 0 | 224730 | Authorized | Authorized | No | CON | State | 0
H11-03-008 | 11 | 5479082 | 3 | Elk Grove | Sacramento County | SACOG | SACOG | 1. Heritage Hill Drive; 2. Apple Mill Drive; 3. Emerald Vista Drive; 4. E. Park Drive; 5. E. Taron Drive; 6. Machado Ranch Drive; 7. Black Kite Drive | Install class II bike lanes at 7 locations: Heritage Hill Drive, Apple Mill Drive, Emerald Vista Drive, Park Drive, E. Taron Drive, Machado Ranch Drive, and Black Kite Drive. Improvements include striping, markings and signs. | 274500 | 247050 | 2023-10-19 | 0 | 2025-06-18 | 0 | 221506.51 | Authorized | Authorized | No | CON | State | 0
H11-03-009 | 11 | 5479083 | 3 | Elk Grove | Sacramento County | SACOG | SACOG | W. Stockton south of Wooded Brook, W. Stockton east of Laguna Springs, E. Stockton Blvd South of Cantwell Dr (4 Locations), and E. Stockton Blvd North of Calle Entrada Way (2 Locations). | Replace guardrail. | 1049100 | 944190 | 2023-10-19 | 0 | 2025-10-10 | 0 | 753425 | Authorized | Authorized | No | CON | State | 0
H12-03-011 | 12 | 5479091 | 3 | Elk Grove | Sacramento County | SACOG | SACOG | Auberry Dr at Monterey Trail High School, Bellaterra Dr at Valgrande Way, Elk Grove Florin Rd at Park Trail Dr, Elk Grove Florin Rd at Tralee Wy, Kyler Rd at Kammerer Park, Soaring Oaks Dr at Carrcroft Dr, and Vicino Dr at Laguna Creek High School. | Install rectangular rapid flashing beacons (RRFBs) at uncontrolled crossings. | 361700 | 311490 | 0 | 2025-09-19 | 0 | 0 | 23400 | No PE | Due by 3/31/2028 | No | ROW | State | 0
H8-03-007 | 8 | 5479055 | 3 | Elk Grove | Sacramento County | SACOG | SACOG | Three (3) uncontrolled pedestrian crossings at intersections of Harbour Point Dr at Buckminster Dr., Lakepoint Dr at Sunset Point Pl. and Whitelock Pkwy east of Knotts Dr. | Install pedestrian activated beacon systems and advanced yield lines. | 384070.02 | 249783 | 2017-05-24 | 0 | 2018-03-06 | 2019-08-15 | 249783 | Authorized | Authorized | No | Closed | Federal | 0
H9-03-006 | 9 | 5479062 | 3 | Elk Grove | Sacramento County | SACOG | SACOG | Four (4) locations: Bruceville Road at Laguna Creek Bridge, Sheldon Road at Laguna Creek Bridge, Waterman Road at Laguna Creek Bridge, and Grant Line Road at Deer Creek Tributary Bridge. | Upgrade outdated guardrail. | 535322.51 | 329200 | 2019-10-18 | 0 | 2023-06-27 | 2025-06-16 | 329200 | Authorized | Authorized | No | Closed | Federal | 0
H9-03-007 | 9 | 5479063 | 3 | Elk Grove | Sacramento County | SACOG | SACOG | Four (4) existing trail crossings of public roads: Laguna Park Drive, Adobe Springs Way, Bertwin Way, and Stonebroook Drive. | Install crosswalks, advance yield signs, Rapid Rectangular Flashing Beacons (RRFBs) and, associated advanced warning signs. | 678188.29 | 250000 | 2019-10-18 | 0 | 2023-06-27 | 2025-06-24 | 250000 | Authorized | Authorized | No | Closed | Federal | 2
HSIP5-03-005 | 5 | 5479042 | 3 | Elk Grove | Sacramento County | SACOG | SACOG | Various corridors throughout the City | Upgrade traffic signals (interconnect) | 150826.33 | 132061.11 | 2013-04-23 | 0 | 2015-06-02 | 2018-03-15 | 132061.11 | Authorized | Authorized | No | Closed | Federal | 0
HSIP6-03-002 | 6 | 5479046 | 3 | Elk Grove | Sacramento County | SACOG | SACOG | Various locations on Grant Line Rd , Bradshaw Rd., Kammerer Rd., and Waterman Rd. | Modify shoulders | 271225.79 | 129000 | 2014-06-08 | 0 | 2015-10-29 | 2018-03-28 | 129000 | Authorized | Authorized | No | Closed | Federal | 0
H10-03-009 | 10 | 5288050 | 3 | Folsom | Sacramento County | SACOG | SACOG | Folsom Bd/Natoma Stn Dr; Blue Ravine Rd/Flower Dr, Natoma Stn Dr; E Bidwell St/BlueRavine Rd, Oak Ave Pk, Broadstone Pk, Glenn Dr, Creekside Dr; FolsomAuburn Rd/Oak Ave Pk, Folsom Lake Cr; E Natoma St/Prison Rd, Green Valley Rd; Iron Pt Rd/Willard Dr. | Improve signal hardware and signal timing, and install raised pavement markers and striping. | 1584600 | 708067.37 | 2021-09-10 | 0 | 2023-05-05 | 2024-07-25 | 708067.37 | Authorized | Authorized | No | Closed | State | 0
H10-03-010 | 10 | 5288051 | 3 | Folsom | Sacramento County | SACOG | SACOG | American River Canyon Dr - Oak Canyon Wy and Canyon Rim Dr; Folsom Bd - US-50 and Iron Pt Rd; Glenn Dr - Sibley St and Folsom Bd; Blue Ravine Rd - Crossing Wy and Riley St; Folsom Auburn Rd; Prairie City Road; E Bidwell St - US-50 and Mangini Pk. | Install delineators, reflectors and object markers (with retro-reflectivity) on the sides of roads, and install rumble strip along the edges of the roadway segments. | 366600 | 366600 | 0 | 0 | 2024-03-15 | 0 | 184200 | No PE | Authorized | No | CON | State | 0
H10-03-011 | 10 | 5288049 | 3 | Folsom | Sacramento County | SACOG | SACOG | Folsom Lake Xing - Folsom Dam Rd and Johnny Cash Trail entrance; E Natoma St - Folsom Lake Xing and Gionata Wy; Folsom Auburn Rd - Pinebrook Rd and Folsom Dam Rd. | Construct median barrier, install dynamic/variable speed warning signs, and delineators, reflectors, and/or object markers (with retro-reflectivity). | 1031400 | 1031400 | 2021-08-17 | 0 | 2023-05-05 | 2024-07-11 | 1031400 | Authorized | Authorized | No | Closed | State | 0
H10-03-012 | 10 | 5911081 | 3 | Glenn County | Glenn County | RURAL | Glenn LTC | Forest Highway 7 (FH7) west of State Route 162 in western Glenn County. | The updated HSIP funded scope includes replacing 5,700 linear feet of fire damaged wood post guardrail, along a 2.3 mile segment of FH7 | 1000000 | 1000000 | 0 | 0 | 2024-06-12 | 0 | 1000000 | No PE | Authorized | No | CON | State | -1
H12-03-012 | 12 | 0 | 3 | Glenn County | Glenn County | RURAL | Glenn LTC | County Road 60 from west of Road P to east of Road SS (two segments approx. 1.41 miles combined). | Install centerline and edgeline rumble strips, and replace striping. | 361800 | 325620 | 0 | 0 | 0 | 0 | 0 | Due in no more than 4 months | Due by 3/31/2028 | No | Not Started | State | 0
H10-03-013 | 10 | 5023024 | 3 | Grass Valley | Nevada County | RURAL | Nevada LTC | Various locations throughout the City of Grass Valley. Areas include crossings adjacent to city schools, parks and commercial areas. | Install Rectangular Rapid Flashing Beacons (RRFBs), pavement striping and markings, pedestrian crossing signs, as well as a raised crosswalk and curb ramps. | 250000 | 250000 | 0 | 0 | 2021-07-02 | 2026-01-13 | 250000 | No PE | Authorized | No | Closed | State | 0
H11-03-010 | 11 | 5260002 | 3 | Isleton | Sacramento County | SACOG | SACOG | Various intersections throughout the city: H St/Main St, 2nd St/A St./SR-160, SR-160/H St, and Union St./D St. | Install/upgrade STOP or intersection warning/regulatory signs, upgrade intersection pavement markings, and improve sight distance to intersection. | 109800 | 98820 | 2023-05-31 | 0 | 0 | 0 | 6840 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE | State | 0
H11-03-011 | 11 | 5260004 | 3 | Isleton | Sacramento County | SACOG | SACOG | Various intersections throughout the city: H St/Main St; 2nd St/A St./SR-160; Union st/D St; and SR-160/C St. | Install pedestrian improvements (crossings, refuge island, and rectangular rapid flashing beacon) at unsignalized intersections. | 267500 | 240750 | 2023-09-18 | 0 | 0 | 0 | 17190 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE | Federal | 1
H11-03-012 | 11 | 5089031 | 3 | Lincoln | Placer County | SACOG | Placer TPA | McBean Park Dr/4th St & B St; McBean Park Dr/4th St & D St; D St & 3rd St; and East Ave & 11th St. | High visibility marked mid-block crosswalks; raised median refuge island; rectangular rapid flashing beacon (RRFB); curb ramps; signing/striping enhancements; and sight distance improvements. | 304600 | 274140 | 2023-11-03 | 0 | 0 | 0 | 36000 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE | State | 0
H8-03-008 | 8 | 5089026 | 3 | Lincoln | Placer County | SACOG | Placer TPA | Various locations throughout the City. | Install crosswalk enhancements at unsignalized locations. | 358223.83 | 249999 | 2017-02-28 | 0 | 2018-08-13 | 2020-10-07 | 249999 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-03-006 | 5 | 5089020 | 3 | Lincoln | Placer County | SACOG | Placer TPA | Lincoln Blvd. (SR 65) between Sterling Pkwy. and 7th St. | Upgrade traffic signals; install safety lighting and bike lanes | 3798498.38 | 1053899.94 | 2013-04-02 | 0 | 2017-04-07 | 2020-10-07 | 1053899.94 | Authorized | Authorized | No | Closed | Federal | 0
HSIP1-03-002 | 1 | 5297004 | 3 | Live Oak | Sutter County | SACOG | SACOG | Sr99 (Live Oak Blvd) At Elm Street. | Install New Traffic Signals With Interconnects To Union Pacific Rr Crossing And Existing Signal At Next Intersection. | 1038956.71 | 877859 | 2005-06-10 | 0 | 2011-09-20 | 2017-10-20 | 877859 | Authorized | Authorized | No | Closed | Federal | 0
H11-03-013 | 11 | 0 | 3 | Loomis | Placer County | SACOG | Placer TPA | Various locations in Town. | Three (3) rapid rectangular flashing beacons, one (1) pedestrian activated, Yield to Pedestrian sign, twenty (20) high visibility crosswalks, and five (5) pedestrian curb ramps to accompany RRFB crosswalks. | 209300 | 188370 | 0 | 0 | 0 | 0 | 0 | No PE | Past due (due 3/31/2026) | Yes (CON) | Not Started | State | 0
H10-03-014 | 10 | 5917109 | 3 | Nevada County | Nevada County | RURAL | Nevada LTC | Approximately 21.7 miles of road on: Burma Rd, Dog Bar Rd, Lower Colfax Rd, McCourtney Rd, Pleasant Valley Rd, Squirrel Creek Rd, Boulder St, Donner Pass Rd, Glenshire Dr, Gracie Rd, Hirschdale Rd, and Lake Vera Purdon Rd. | Provide thermoplastic striping and markings and pavement markers to lower elevation roads. Provide MMA striping and markings to higher elevation roads that are subject to frequent plowing and sanding. | 949100 | 949100 | 2021-04-15 | 0 | 2023-01-19 | 2025-01-06 | 949100 | Authorized | Authorized | No | Closed | State | 0
H10-03-015 | 10 | 5917110 | 3 | Nevada County | Nevada County | RURAL | Nevada LTC | Twenty curves throughout Nevada County. | Apply High Friction Surface Treatment (HFST). | 1889300 | 1819300 | 0 | 0 | 2022-02-28 | 2024-04-05 | 1819300 | No PE | Authorized | No | Closed | State | 0
H12-03-013 | 12 | 5917124 | 3 | Nevada County | Nevada County | RURAL | Nevada LTC | Fourteen (14) roadway curves throughout Nevada County. | Apply high friction surface treatment (HFST). | 1607000 | 1446300 | 2025-06-04 | 0 | 2026-02-13 | 0 | 1446300 | Authorized | Authorized | No | CON | Federal | 1
H8-03-009 | 8 | 5917098 | 3 | Nevada County | Nevada County | RURAL | Nevada LTC | Various road segments: Garden Bar Rd, Lime Kiln Rd, McCourtney Rd, N. Bloomfield-Graniteville Rd, Ridge Rd, Rough & Ready Hwy, Tyler-Foote Crossing, Wolf Rd, and You Bet Rd. | Provide thermoplastic striping and pavement markers along approx. 30 miles of rural Nevada County Roadways. | 410688.28 | 407172.1 | 0 | 0 | 2018-01-31 | 2019-10-31 | 407172.1 | No PE | Authorized | No | Closed | Federal | 0
H9-03-008 | 9 | 5917101 | 3 | Nevada County | Nevada County | RURAL | Nevada LTC | Various road segments: Banner Lava Cap, Indian Springs Rd, Magnolia Rd, McCourtney Rd, Mooney Flat Rd, Pleasant Valley Rd, Rough and Ready Highway, Tyler Foote Crossing Rd, Red Dog Road/Boulder St, and Wolf Rd. | Provide thermoplastic striping and pavement markers along approximately 28.6 miles of rural Nevada County Roadways. | 468624.43 | 468624.43 | 0 | 0 | 2019-05-08 | 2020-10-07 | 468624.43 | No PE | Authorized | No | Closed | Federal | 0
H9-03-009 | 9 | 5917102 | 3 | Nevada County | Nevada County | RURAL | Nevada LTC | Various road corridors in Western Nevada County. | Conduct a countywide guardrail safety audit, identify deficiencies, and repair or upgrade guardrail as necessary. | 1041288.47 | 1039354.29 | 2019-06-14 | 0 | 2022-03-21 | 2024-02-21 | 1039354.29 | Authorized | Authorized | No | Closed | Federal | 1
H9-03-010 | 9 | 5917103 | 3 | Nevada County | Nevada County | RURAL | Nevada LTC | Various curves along Greenhorn Rd, Dog Bar Rd, Red Dog Rd, Rough & Ready Hwy, Wolf Rd, Bitney Springs Rd, Old Tunnel Rd, Indian Springs Rd, McCourtney Rd, Auburn Rd, Lake Vera Purdon Rd, Pleasant Valley Rd. | Apply High Friction Surface Treatment (HFST) at various curves with high run-off road (hit object) accident rates. | 963206.02 | 963206.02 | 2019-10-11 | 0 | 2020-03-10 | 2021-11-23 | 963206.02 | Authorized | Authorized | No | Closed | Federal | 0
HRRR2-03-015A | 2 | 5917054 | 3 | Nevada County | Nevada County | RURAL | Nevada LTC | Wolf Road from SR 49 to Garden Bar Road | Widen shoulders; improve roadside drainage | 585956.98 | 433633.46 | 0 | 0 | 2010-07-07 | 2012-01-18 | 433633.46 | No PE | Authorized | No | Closed | Federal | 0
HSIP2-03-003 | 2 | 5917048 | 3 | Nevada County | Nevada County | RURAL | Nevada LTC | Mccourtney Road From Lime Kiln Rd. To Polaris Drive | Widen Shoulder And Construct Drainage Improvements | 663273.16 | 425513.78 | 0 | 0 | 2009-09-03 | 2012-03-05 | 425513.78 | No PE | Authorized | No | Closed | Federal | 0
HSIP2-03-004 | 2 | 5917049 | 3 | Nevada County | Nevada County | RURAL | Nevada LTC | Pasquale Rd. From Red Dog Rd. To Cascade Shores | Widen Shoulders And Construct Drainage Improvements At Spot Locations | 206203.01 | 173508.12 | 0 | 0 | 2009-07-09 | 2010-10-13 | 173508.12 | No PE | Authorized | No | Closed | Federal | 0
HSIP2-03-005 | 2 | 5917050 | 3 | Nevada County | Nevada County | RURAL | Nevada LTC | Intersection Of Mccourtney Rd. And Adair Ave. | Realign Roadway On Mccourtney Rd. | 373576.19 | 246977.22 | 0 | 0 | 2010-08-12 | 2014-06-27 | 246977.22 | No PE | Authorized | No | Closed | Federal | 0
HSIP2-03-006 | 2 | 5917051 | 3 | Nevada County | Nevada County | RURAL | Nevada LTC | Revised Project Location Is: Dog Bar Rd. From 400' North Of Wheeler Cross Rd. To 400' South Of Rogue House Place. Original Project Location: Intersection Of Dog Bar Rd. And Rogue House Place | Revised Project Scope Is: Widen Shoulders. Original Project Scope Was: Construct Left Turn Lane | 239797.76 | 171652.24 | 0 | 0 | 2009-04-15 | 2012-01-18 | 171652.24 | No PE | Authorized | No | Closed | Federal | 0
HSIP2-03-007 | 2 | 5917052 | 3 | Nevada County | Nevada County | RURAL | Nevada LTC | Lime Kiln Rd. From Sr 49 To Wolf Creek | Widen Shoulders And Construct Drainage Improvements | 358724.18 | 274183.95 | 2009-08-18 | 0 | 2011-03-15 | 2014-06-27 | 274183.95 | Authorized | Authorized | No | Closed | Federal | 0
HSIP4-03-005 | 4 | 5917071 | 3 | Nevada County | Nevada County | RURAL | Nevada LTC | Various locations throughout the county | Install striping and pavement markings | 424932.15 | 370592.67 | 0 | 0 | 2011-06-08 | 2014-06-27 | 370592.67 | No PE | Authorized | No | Closed | Federal | 0
HSIP5-03-007 | 5 | 5917074 | 3 | Nevada County | Nevada County | RURAL | Nevada LTC | Various locations along Alta Sierra Dr., Banner Lava Cap Rd., East Bennett St., Greenhorn Rd., Indian Springs Rd., La Barr Meadows Rd., Lime Kiln Rd., McCourtney Rd., and North Bloomfield Rd. | Install striping, signs and pavement markers | 269246.18 | 227978.95 | 0 | 0 | 2013-05-16 | 2014-03-28 | 227978.95 | No PE | Authorized | No | Closed | Federal | 0
HSIP5-03-008 | 5 | 5917075 | 3 | Nevada County | Nevada County | RURAL | Nevada LTC | Lime Kiln Rd. between McCourtney Rd. and Wolf Rd. | Widen shoulders; install striping and pavement markers | 341940.15 | 266769.03 | 2013-02-13 | 0 | 2014-05-01 | 2015-10-29 | 266769.03 | Authorized | Authorized | No | Closed | Federal | 0
HSIP6-03-003 | 6 | 5917086 | 3 | Nevada County | Nevada County | RURAL | Nevada LTC | Brunswick Rd/Loma Rica Dr | Install traffic signal, right turn pocket, and High Friction Surface Treatment | 1025655.09 | 521900 | 0 | 0 | 2014-06-27 | 2016-03-08 | 521900 | No PE | Authorized | No | Closed | Federal | 0
HSIP6-03-004 | 6 | 5917087 | 3 | Nevada County | Nevada County | RURAL | Nevada LTC | Various locations throughout Nevada County | Install striping and pavement markers | 184080.85 | 155121 | 0 | 0 | 2014-05-15 | 2015-09-02 | 155121 | No PE | Authorized | No | Closed | Federal | 0
HSIP6-03-005 | 6 | 5917088 | 3 | Nevada County | Nevada County | RURAL | Nevada LTC | 4 Corridors in Western Nevada County | Conduct a Roadway Safety Signing Audit and upgrade signs | 550340.18 | 456162.8 | 2014-02-04 | 0 | 2015-12-22 | 2020-10-15 | 456162.8 | Authorized | Authorized | No | Closed | Federal | 0
HSIP7-03-005 | 7 | 5917093 | 3 | Nevada County | Nevada County | RURAL | Nevada LTC | Various road corridors in Western Nevada County. This project includes approximately 130 miles of Major and Minor Collector roadways. | Road Safety and Signing Audit (RSSA) Project. This project proposes to evaluate: 1) the existing sign type, locations and sizes per MUTCD, 2) identify missing signs per MUTCD, 3) evaluate sign retroreflectivity, and 4) modify signage accordingly | 1211159.6 | 1204406.71 | 2016-07-27 | 0 | 2019-03-07 | 2020-09-04 | 1204406.71 | Authorized | Authorized | No | Closed | Federal
HSIP7-03-006 | 7 | 5917094 | 3 | Nevada County | Nevada County | RURAL | Nevada LTC | Various road segments: Alexandra Wy, Alta Sierra Dr, Ball Rd, Brewer Rd, Carrie Dr, Dog Bar Rd, E Bennett Rd, E Lime Kiln Rd, Francis Dr, Gary Wy, Karen Dr, La Barr Meadows Rd, Lawrence Wy, Newtown Rd, Norlene Wy, Rattlesnake Rd, Tammy Wy, Tippy Wy. | Provide thermoplastic striping and pavement markers along approximately 30 miles of rural Nevada County Roadways | 373646.83 | 361485.37 | 0 | 0 | 2017-01-28 | 2018-07-17 | 361485.37 | No PE | Authorized | No | Closed | Federal
HSIP7-03-007 | 7 | 5917095 | 3 | Nevada County | Nevada County | RURAL | Nevada LTC | Various curves along: Auburn Rd, Alta Sierra Rd, Bitney Springs Rd, Brunswick Rd, Dog Bar Rd, Greenhorn Rd, La Barr Meadows Rd, LIme Kiln Rd, Magnolia Rd, McCourtney Rd, Ridge Rd, Rough and Ready Rd, You Bet Rd. | Apply High Friction Surface Treatment (HFST) at various curves with high run-off road (hit object) accident rates | 756573.78 | 662909.55 | 0 | 0 | 2017-01-28 | 2018-07-04 | 662909.55 | No PE | Authorized | No | Closed | Federal
H9-03-011 | 9 | 5185008 | 3 | Orland | Glenn County | RURAL | Glenn LTC | On Walker Street/SR32 at the signalized intersections of Papst Avenue (1A), East Street (1B), Sixth Street (1C) & Eighth Street (1D) & South and Sixth Streets (1E), and non-signalized intersections of Fifth, Fourth, Third, Second, First, A & Woodward. | Install pedestrian countdown signal heads with accessible pedestrian system buttons and pavement markings for safety. | 227400 | 227400 | 2019-05-16 | 0 | 2021-04-19 | 0 | 227400 | Authorized | Authorized | No | CON | Federal | 0
HSIP2-03-019 | 2 | 6203042 | 3 | Oroville | Butte County | BCAG | BCAG | Intersection Of Sr 162 And Veatch St. | Install Traffic Signal; Cooperative Project With Caltrans Project Ea:03-3E850 | 229137.28 | 206223.55 | 0 | 0 | 2009-05-15 | 2013-03-22 | 206223.55 | No PE | Authorized | No | Closed | Federal | 0
HSIP5-03-009 | 5 | 5142034 | 3 | Oroville | Butte County | BCAG | BCAG | Oro Dam Blvd./Orange Ave./Acacia Ave. | Install traffic signals | 429487.52 | 345600 | 2013-02-20 | 0 | 2015-05-01 | 2016-06-22 | 345600 | Authorized | Authorized | No | Closed | Federal | 0
H9-03-012 | 9 | 5425041 | 3 | Paradise | Butte County | BCAG | BCAG | Thirteen stop-controlled intersections at various locations | Systemically improve minor street approaches with a combination of additional intersection warning/regulatory signs, improved pavement markings, and improved sight triangles. | 687400 | 618660 | 2019-05-24 | 0 | 2022-10-27 | 0 | 626889 | Authorized | Authorized | No | CON | Federal | 0
HSIP5-03-010 | 5 | 5425024 | 3 | Paradise | Butte County | BCAG | BCAG | Skyway Rd. between Vista Way and Elliot Rd. | Modify traffic signals; install crosswalks | 1246228.68 | 900000 | 2013-02-15 | 0 | 2014-05-01 | 2015-10-28 | 900000 | Authorized | Authorized | No | Closed | Federal | 0
HSIP6-03-006 | 6 | 5425025 | 3 | Paradise | Butte County | BCAG | BCAG | On Clark Rd between Adams Rd and Kimberly Lane | Improve vertical and horizontal alignments; improve drainage; widen shoulder | 1190339.35 | 1170687.9 | 2014-04-01 | 2015-08-20 | 2016-08-19 | 2018-05-18 | 1170687.9 | Authorized | Authorized | No | Closed | Federal | 0
HSIP6-03-007 | 6 | 5425026 | 3 | Paradise | Butte County | BCAG | BCAG | 15 intersections throughout Paradise | Upgrade traffic signals (battery back up system and Emergency Vehicle Pre-emption (EVP) system); install pedestrian countdown heads, ADA pedestrian pushbuttons | 307192.74 | 268114.25 | 2014-04-09 | 0 | 2014-08-08 | 2019-01-14 | 268114.25 | Authorized | Authorized | No | Closed | Federal | 0
HSIP6-03-008 | 6 | 5425027 | 3 | Paradise | Butte County | BCAG | BCAG | On Pearson Rd between Clark Rd and Pentz Rd | Widen shoulder; install bike lanes | 1217587.77 | 602399.35 | 2014-04-01 | 0 | 2016-02-16 | 2017-10-20 | 602399.35 | Authorized | Authorized | No | Closed | Federal | 0
HSIP6-03-009 | 6 | 5425028 | 3 | Paradise | Butte County | BCAG | BCAG | On Clark Rd between Billie Rd and Wagstaff Rd | Add Two-Way Left-Turn Lane (without reducing travel lanes) | 488054.43 | 485902.17 | 2014-04-01 | 0 | 2015-08-04 | 2017-02-08 | 485902.17 | Authorized | Authorized | No | Closed | Federal | 0
HSIP7-03-004 | 7 | 5425035 | 3 | Paradise | Butte County | BCAG | BCAG | Intersection of Skyway at Black Olive Drive | Install traffic signal | 769340.35 | 759519.35 | 2016-03-09 | 0 | 2018-11-07 | 2021-01-08 | 759519.35 | Authorized | Authorized | No | Closed | Federal
H10-03-016 | 10 | 5919151 | 3 | Placer County | Placer County | SACOG | Placer TPA | Hungry Hollow Rd. at Hardscrabble Dr., Lonestar Rd. (1 location 1/4 mile e of Bell Rd. and one w of View Wy.), McCourtney Rd. at Fleming Dr., Mt. Vernon Rd. north of Atwood Rd., and Placer Hills Rd. n of Pinewood Wy | Placer County, in order to reduce high-severity collisions along roadways, is applying for funding to perform high friction surface treatments along abrupt horizontal curves on several roadways primarily in the areas of Auburn and Lincoln. | 1201600 | 1201600 | 2021-06-01 | 0 | 2022-10-18 | 2024-10-04 | 1201600 | Authorized | Authorized | No | Closed | State | 0
H10-03-017 | 10 | 5919152 | 3 | Placer County | Placer County | SACOG | Placer TPA | Various locations in Placer County | Upgrade all signal backplates with new reflective backplates, replace old pedestrian heads with countdown type heads and replace old controllers along Douglas Blvd. with new 2070 controllers. | 351300 | 351300 | 2021-12-07 | 0 | 2023-07-31 | 0 | 351300 | Authorized | Authorized | No | CON | State | 0
H10-03-018 | 10 | 5919150 | 3 | Placer County | Placer County | SACOG | Placer TPA | Indian Hill Road, Ridge Road, and Rollins Lake Road. | Update guardrail to bring existing facilities up to current standards. | 995500 | 995500 | 2021-05-07 | 2022-05-02 | 2022-11-03 | 2024-07-10 | 995500 | Authorized | Authorized | No | Closed | State | 0
H11-03-014 | 11 | 5919159 | 3 | Placer County | Placer County | SACOG | Placer TPA | In Lincoln and Auburn, along a portion of Baxter Grade Road, Nelson Lane (Moore Road to Highway 65) and a portion of Wise Road (Garden Bar Road to Doty Creek); also Auburn, Foresthill, and Lincoln, Mt. Vernon Rd (Pleasant Hill Rd to Cold Stream Rd), Cavitt Stallman Road from 4360 to 6400, Swetzer Road from English Colony Way to Arabian Lane, Humphrey Road from English Colony Way to Citrus Colony Road, and Cowell Road from Humphrey Road to Swetzer Road. Wise Road (Doty Ravine to Wally Allen Dr). | Adding edgelines. | 244900 | 220410 | 2023-08-10 | 0 | 2024-01-04 | 0 | 97372.22 | Authorized | Authorized | No | CON | Federal | 1
H11-03-015 | 11 | 5919160 | 3 | Placer County | Placer County | SACOG | Placer TPA | Colfax/Gold Run and Dutch Flat/Alta. | Replace old guardrail with new guardrail and end treatments along Magra Road and Ridge Road. | 224523.13 | 202070.81 | 2023-08-10 | 0 | 2024-03-20 | 2025-03-10 | 202070.81 | Authorized | Authorized | No | Closed | Federal | 1
H11-03-016 | 11 | 5919161 | 3 | Placer County | Placer County | SACOG | Placer TPA | On Fuller Drive in Granite Bay. | Provide enhanced signing, markings, rectangular rapid flash beacon and street lighting on Fuller Drive. | 277778 | 215100 | 2023-07-28 | 0 | 2024-04-24 | 2025-04-21 | 215100 | Authorized | Authorized | No | Closed | State | 0
H11-03-017 | 11 | 5919162 | 3 | Placer County | Placer County | SACOG | Placer TPA | On Placer Hills Road in Meadow Vista, Dry Creek Road in Auburn and Auburn Folsom Road in Granite Bay. | Install Guardrail on short segments of road along Dry Creek Road and Auburn Folsom Road, and install recessed pavement markers, bike lane signage, and bike lane pavement markings along Placer Hills Road from Lake Arthur Road to Meadow Vista Road. | 625900 | 563310 | 2023-07-28 | 0 | 2024-03-06 | 2025-11-17 | 563310 | Authorized | Authorized | No | Closed | State | 0
H12-03-014 | 12 | 5919173 | 3 | Placer County | Placer County | SACOG | Placer TPA | Cavitt Stallman Road in Granite Bay, Applegate Road and Crother Road in Applegate, Dry Creek Road in Auburn, Giesendorfer Road in Weimar, Magra Road in Colfax and portions of McCourtney Road north of Lincoln. | Install edgeline striping. | 344400 | 309960 | 2025-06-04 | 0 | 2025-09-16 | 0 | 95625 | Authorized | Authorized | No | CON | State | 0
H12-03-015 | 12 | 5919168 | 3 | Placer County | Placer County | SACOG | Placer TPA | Auburn Folsom Road and Horseshoe Bar Road in Loomis. Portions of Wise/West Wise Road and Nicolaus Road in Lincoln. All of Lincoln-Sheridan Blvd in Lincoln. Mt. Vernon Road in Auburn. Taylor Road in Penryn/Loomis. | Install "Pass-3 Ft. Min" signs on various roadways; replace and install new "Bike Lane" signage and markings on Taylor, Auburn Folsom Road and Lincoln-Sheridan Blvd; and add conflict markings to Taylor Road. | 382300 | 344070 | 2025-03-21 | 0 | 0 | 0 | 58500 | Authorized | Due by 3/31/2028 | No | PE | State | 0
H12-03-016 | 12 | 5919172 | 3 | Placer County | Placer County | SACOG | Placer TPA | Auburn Folsom Road, Cabin Creek Road, Caperton Court, Indian Hill Road, Rippey Road, and Tahoe Park Heights Drive, located in Granite Bay, Loomis, Penryn, Newcastle, Dutch Flat, Truckee and Tahoe City. | Replace approximately 4,300 lineal feet of existing guardrail with new Midwest Guardrail System (MGS) guardrails and terminals. | 1107700 | 996930 | 2025-05-29 | 0 | 0 | 0 | 139500 | Authorized | Due by 3/31/2028 | No | PE | Federal | 1
H12-03-017 | 12 | 5919169 | 3 | Placer County | Placer County | SACOG | Placer TPA | H Street in Sheridan, Foresthill Road in the town of Foresthill, Auburn Folsom Road in Granite Bay north of Douglas Blvd and Wellington Way at Granite Bay High School in Granite Bay. | Install continental crosswalks in Sheridan on H Street, continental crosswalk, rectangular rapid flashing beacons (RRFBs) and one dynamic flashing speed limit sign in Foresthill and convert existing HAWK signal to pedestrian signal in Granite Bay. | 379800 | 341820 | 2025-03-21 | 0 | 0 | 0 | 54000 | Authorized | Due by 3/31/2028 | No | PE | State | 0
H12-03-018 | 12 | 5919170 | 3 | Placer County | Placer County | SACOG | Placer TPA | Several locations in western Placer County including Lincoln, Sheridan, Auburn and Newcastle. | Install high friction surface treatment (HFST) along curves. | 1841100 | 1656990 | 2025-05-19 | 0 | 2025-12-19 | 0 | 1656990 | Authorized | Authorized | No | CON | Federal | 1
H12-03-019 | 12 | 5919171 | 3 | Placer County | Placer County | SACOG | Placer TPA | 21 roadways in Placer County. | Perform roadway safety sign audit and sign upgrades, including yellow warning signs and regulatory speed limit signs. | 1110900 | 999810 | 2025-05-19 | 0 | 0 | 0 | 171000 | Authorized | Due by 3/31/2028 | No | PE | Federal | 1
H8-03-010 | 8 | 5919130 | 3 | Placer County | Placer County | SACOG | Placer TPA | Various locations throughout the county (Exact locations to be determined during the preliminary engineering of the project). | Install crosswalk enhancements to existing unprotected crosswalks. | 249700 | 249700 | 2017-02-15 | 0 | 2021-01-26 | 2023-06-21 | 249700 | Authorized | Authorized | No | Closed | Federal | 0
H9-03-013 | 9 | 5919140 | 3 | Placer County | Placer County | SACOG | Placer TPA | Foresthill Road between Old Auburn-Foresthill Road and Spring Garden Road. | Install high friction surface treatment, guardrail and warning signs. | 2599064.53 | 2530900 | 2019-10-11 | 0 | 2022-02-15 | 2024-07-09 | 2530900 | Authorized | Authorized | No | Closed | Federal | 1
HRRR2-03-017 | 2 | 5919081 | 3 | Placer County | Placer County | SACOG | Placer TPA | Foresthill Road from Lower Lake Clementine Road to Old Auburn Road | Increase sight distance; construct acceleration lane | 1301413.27 | 900000 | 2009-03-26 | 0 | 2012-04-18 | 2014-04-09 | 900000 | Authorized | Authorized | No | Closed | Federal | 0
HSIP3-03-005 | 3 | 5919092 | 3 | Placer County | Placer County | SACOG | Placer TPA | Rollins Lake Rd. For 2 Miles North Of Its Intersection With Sr 174, Including Its Intersection With Norton Grade Rd. | Construct Segments Of Shoulder Widening And Guardrail; Realign Roadway Intersection; Install Speed Limit And Curve Warning Signage | 952942.44 | 844473.68 | 2010-07-02 | 0 | 2013-02-20 | 2015-10-29 | 844473.68 | Authorized | Authorized | No | Closed | Federal | 0
HSIP3-03-006 | 3 | 5919093 | 3 | Placer County | Placer County | SACOG | Placer TPA | Foresthill Rd. 3.2 Miles East Of The Intersection Of Sr 80 And The "Auburn Ravine - Foresthill Exit" | Improve Horizontal Geometry Of 3 Curves; Repave And Apply A Micro-Surface Friction Course; Increase Sight Distance And Add Acceleration Lane. | 1261908.86 | 900000 | 2010-07-19 | 0 | 2012-04-10 | 2014-02-25 | 900000 | Authorized | Authorized | No | Closed | Federal | 0
HSIP4-03-007 | 4 | 5919096 | 3 | Placer County | Placer County | SACOG | Placer TPA | King Rd. between Auburn Folsom Rd. and Sudor Ln. | Widen traveled lanes; construct drainage improvements | 1099458.93 | 900000 | 2011-05-25 | 2014-08-22 | 2015-06-02 | 2018-03-15 | 900000 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-03-011 | 5 | 5919110 | 3 | Placer County | Placer County | SACOG | Placer TPA | Various locations throughout the county | Install pavement markings | 815022.37 | 730192.43 | 2013-05-17 | 0 | 2014-07-11 | 2019-10-11 | 730192.43 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-03-012 | 5 | 5919112 | 3 | Placer County | Placer County | SACOG | Placer TPA | Various locations throughout Placer County | Install pavement markers | 98016.11 | 80950.69 | 2013-05-17 | 0 | 2014-08-22 | 2016-10-20 | 80950.69 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-03-013 | 5 | 5919111 | 3 | Placer County | Placer County | SACOG | Placer TPA | Auburn Folsom Road from 60 feet North of Willow Lane to Robin Hood Lane, and Joe Rodgers Road from 450 feet west of Auburn Folsom Road to Auburn Folsom Road | Construct sidewalks, curb ramps, curb and gutter, mid-block crosswalks, traffic feedback sign, pedestrian warning beacon, guardrail replacements, and roadway surface treatment to improve friction | 689000 | 671500 | 2013-05-16 | 0 | 2015-07-23 | 2018-05-02 | 671500 | Authorized | Authorized | No | Closed | Federal | 0
HSIP6-03-010 | 6 | 5919118 | 3 | Placer County | Placer County | SACOG | Placer TPA | 18 various locations throughout Placer County | Install High Friction Surface Treatment | 1590421.86 | 1237009.54 | 2014-04-16 | 0 | 2014-07-23 | 2016-05-02 | 1237009.54 | Authorized | Authorized | No | Closed | Federal | 0
HSIP6-03-011 | 6 | 5919119 | 3 | Placer County | Placer County | SACOG | Placer TPA | Various corridors throughout Placer County | Conduct a Roadway Safety Signing Audit and upgrade signs | 2341182.3 | 2091750.66 | 2014-06-27 | 0 | 2018-10-15 | 2021-02-25 | 2091750.66 | Authorized | Authorized | No | Closed | Federal | 0
HSIP7-03-009 | 7 | 5919127 | 3 | Placer County | Placer County | SACOG | Placer TPA | At 19 intersections throughout southwest Placer County. | Installation of lighting, upgraded pavement markings, and flashing beacon improvements | 1377596.1 | 979928 | 2016-08-31 | 2018-09-10 | 2019-05-13 | 2021-12-28 | 979928 | Authorized | Authorized | No | Closed | Federal
H10-03-019 | 10 | 5015036 | 3 | Placerville | El Dorado County | SACOG | El Dorado LTC | US Highway 50, PM 16.7 to PM 18.8 (within the City limits of Placerville). | Enhance pedestrian crossing safety through the use of dynamic warning signs at various state highway and local road at grade pedestrian/school crossings. | 250000 | 250000 | 2021-11-12 | 0 | 0 | 0 | 21500 | Authorized | Past due (due 3/2/2026) | Yes (CON) | PE | State | 0
HSIP6-03-012 | 6 | 5015025 | 3 | Placerville | El Dorado County | SACOG | El Dorado LTC | On Broadway between Carson Rd and Schnell School Rd | Upgrade crosswalks, speed tables, signing and lighting | 354418.65 | 231288.69 | 2014-04-14 | 0 | 2015-07-01 | 2018-10-31 | 231288.69 | Authorized | Authorized | No | Closed | Federal | 0
HSIP7-03-010 | 7 | 5015028 | 3 | Placerville | El Dorado County | SACOG | El Dorado LTC | In El Dorado County, in the City of Placerville, along Broadway from the intersection at Main Street eastward to approximately 1500 Broadway. | Construct sidewalk | 3011197 | 1710305 | 2016-07-11 | 2022-07-01 | 2023-03-08 | 0 | 1946570.66 | Authorized | Authorized | No | CON | Federal
H10-03-020 | 10 | 5482048 | 3 | Rancho Cordova | Sacramento County | SACOG | SACOG | On Peter A Mccuen Boulevard adjacent to VA Northern Medical Center and four intersections along Zinfandel Dr and Cordova Lane adjacent to Cordova Lane Center School. | Improve pedestrian crossings with curb extensions, accessible curb ramps, high visibility crosswalks, and advanced pavement markings. | 242400 | 242400 | 0 | 0 | 2022-03-08 | 2023-12-15 | 242400 | No PE | Authorized | No | Closed | State | 0
H11-03-018 | 11 | 5482054 | 3 | Rancho Cordova | Sacramento County | SACOG | SACOG | The segment of Grant Line Road from Raymer Wy to White Rock Rd; various signals on International Dr between Mather Field Rd/Rockingham Dr and Kilgore Rd; and various signals on Coloma Road between Malaga Wy and Trinity River (19 signals total). | Install LED chevron curve warning signs, rumble strips, and high friction surface treatment along horizontal curve segment along Grant Line Rd. Signal hardware improvements include retroreflective border on backplates for improved visibility. | 910300 | 819270 | 0 | 0 | 2024-11-01 | 0 | 819270 | No PE | Authorized | No | CON | State | 0
H11-03-019 | 11 | 5482053 | 3 | Rancho Cordova | Sacramento County | SACOG | SACOG | Four school locations throughout the City: Zinfandel/Berrywood near Mitchell Middle, Kilgore Rd near Kinney High, Sophistry/Muldoon near Robert McGarvey Elementary, and Cobble Brook/Coratina near Sunrise Elementary. | Install Rectangular Rapid-Flashing Beacons, high visibility crosswalks, advanced yield markings, and curb ramps. | 290300 | 249470 | 0 | 0 | 2024-10-10 | 0 | 249470 | No PE | Authorized | No | CON | State | 0
H12-03-020 | 12 | 0 | 3 | Rancho Cordova | Sacramento County | SACOG | SACOG | 51 signals on the following corridors: Folsom Blvd, Zinfandel Dr, Sunrise Blvd, Bradshaw Rd, Old Placerville Rd, Douglas Rd, White Rock Rd, Rancho Cordova Pkwy, Data Dr, and Mather Field Rd. | Install signal hardware improvements including upgrading vehicle signal lenses from 8 inch to 12 inch and retroreflective border on backplates. | 1142100 | 975690 | 0 | 0 | 0 | 0 | 0 | No PE | Due by 3/31/2028 | No | Not Started | State | 0
H8-03-011 | 8 | 5482037 | 3 | Rancho Cordova | Sacramento County | SACOG | SACOG | Coloma Road from Ananda Lane to Dolecetto Drive, and Chase Drive from Daniel Way to Coloma Road. | Install new sidewalks along Coloma Rd. at the intersection of Chase Dr.; install new Chevron signage, pedestrian protection railing and improved lane delineation on Coloma Rd. | 843253.75 | 266514.66 | 0 | 0 | 2019-02-21 | 2020-11-03 | 266514.66 | No PE | Authorized | No | Closed | Federal | 0
H9-03-015 | 9 | 5482041 | 3 | Rancho Cordova | Sacramento County | SACOG | SACOG | Sunrise Boulevard from the American River Bridge to SR-16/Jackson Road; and Folsom Boulevard from Bradshaw Road to Hazel Avenue/Nimbus Road. | Install flashing beacons, dynamic/variable speed warning signs, and improve traffic signal hardware. | 2255891.52 | 1927699.82 | 2019-09-06 | 0 | 2022-10-27 | 2025-04-11 | 1927699.82 | Authorized | Authorized | No | Closed | Federal | 0
HSIP4-03-001 | 4 | 5482016 | 3 | Rancho Cordova | Sacramento County | SACOG | SACOG | White Rock Rd., W of Zinfandel Dr. | Install sidewalks, bike lanes, and crosswalks | 451287.38 | 358100 | 2011-08-01 | 0 | 2012-06-21 | 2014-03-27 | 358100 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-03-014 | 5 | 5482024 | 3 | Rancho Cordova | Sacramento County | SACOG | SACOG | Aramon Dr. (Studarus Dr.)/Coloma Rd. | Install traffic signals | 539628.19 | 429807.86 | 2013-02-13 | 0 | 2014-05-01 | 2016-10-20 | 429807.86 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-03-015 | 5 | 5482025 | 3 | Rancho Cordova | Sacramento County | SACOG | SACOG | Coloma Rd. between Folsom Blvd. and Sunrise Blvd. | Upgrade traffic signals (interconnect); install traffic cameras | 849712.53 | 721948.1 | 2013-02-13 | 0 | 2014-07-09 | 2016-10-20 | 721948.1 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-03-016 | 5 | 5482026 | 3 | Rancho Cordova | Sacramento County | SACOG | SACOG | Douglas Rd./Grant Line Rd. | Install traffic signal; widen roadway (to accommodate left-turn and right-turn pockets and bike lanes) | 984083.78 | 702399.99 | 0 | 0 | 2016-12-07 | 2018-06-01 | 702399.99 | No PE | Authorized | No | Closed | Federal | 0
HSIP6-03-013 | 6 | 5482028 | 3 | Rancho Cordova | Sacramento County | SACOG | SACOG | Various locations on Sunrise Blvd, Folsom Blvd, Zinfandel Dr, White Rock Rd, Mather Field Rd, and Rockingham Dr. | Install new traffic signal controllers, expand the existing coordinated signal system, and install fiber to connect to traffic operations center | 1887480.91 | 1625000 | 2014-08-21 | 0 | 2016-08-31 | 2019-06-13 | 1625000 | Authorized | Authorized | No | Closed | Federal | 0
H11-03-020 | 11 | 5182089 | 3 | Roseville | Placer County | SACOG | Placer TPA | Vernon Street and Atlantic Street segment between Lincoln Street and Yosemite Street. | Install raised median to restrict left-turn access at stop-controlled intersections; high visibility crosswalks; rectangular rapid flashing beacon (RRFB) at Jefferson Street; left-turn lanes; and additional signing and striping. | 2131360 | 486360 | 0 | 0 | 2025-07-07 | 0 | 486360 | No PE | Authorized | No | CON | State | 0
HSIP5-03-017 | 5 | 5182068 | 3 | Roseville | Placer County | SACOG | Placer TPA | Roseville Rd. from Cirby Way to the city limits | Realign roadway | 2377154.43 | 899999.99 | 0 | 0 | 2016-02-22 | 2018-04-20 | 899999.99 | No PE | Authorized | No | Closed | Federal | 0
H10-03-021 | 10 | 5002223 | 3 | Sacramento | Sacramento County | SACOG | SACOG | Various locations throughout the City of Sacramento | Upgrade pedestrian crossings at uncontrolled locations with the installation of Rectangular Rapid Flashing Beacons (RRFBs). | 248600 | 248600 | 2021-04-19 | 2024-10-03 | 2025-04-14 | 0 | 248600 | Authorized | Authorized | No | CON | State | 0
H12-03-021 | 12 | 0 | 3 | Sacramento | Sacramento County | SACOG | SACOG | Various signalized intersections throughout the City of Sacramento. | Install new traffic signal heads and modify existing signal heads to include retro-reflective tape. | 1005500 | 904950 | 0 | 0 | 0 | 0 | 0 | No PE | Due by 3/31/2028 | No | Not Started | State | 0
H8-03-012 | 8 | 5002198 | 3 | Sacramento | Sacramento County | SACOG | SACOG | Various locations throughout the City of Sacramento. | Replace pedestrian signal heads with countdown signal heads, install 12" vehicle heads, install emergency vehicle preemption equipment, and replace median island signals with mast arm signals. | 5763530.22 | 5205645.59 | 2017-11-30 | 2019-11-27 | 2021-05-17 | 2025-04-28 | 5205645.59 | Authorized | Authorized | No | Closed | Federal | 0
H8-03-013 | 8 | 5002199 | 3 | Sacramento | Sacramento County | SACOG | SACOG | Intersections of 65th St Expwy at 21st Ave, 65th St Expwy at Fruitridge Rd, Arden Way at Heritage Ln, Arden Way at Challenge Way, Howe Ave at Swarthmore Dr, Howe Ave at University Ave, and Stockton Blvd at Fruitridge Rd. | Replace pedestal mounted signals with mast arm signals. | 1984984.83 | 1880100 | 2017-11-30 | 2019-10-31 | 2022-02-08 | 2025-06-20 | 1880100 | Authorized | Authorized | No | Closed | Federal | 0
H8-03-014 | 8 | 5002200 | 3 | Sacramento | Sacramento County | SACOG | SACOG | Florin Road between Greenhaven Drive and Luther Drive. | Convert from pedestal mounted to mast arms at 7 intersections; Install advanced detection at Florin Rd/24th St, and Florin Rd/Freeport Blvd; Install communications fiber; Install Countdown Ped Heads; and Replace 8" with 12" LED 3 Section Heads. | 2555400 | 2555400 | 2017-11-30 | 0 | 2022-09-19 | 0 | 4237375.33 | Authorized | Authorized | No | CON | Federal | 0
H8-03-015 | 8 | 5002201 | 3 | Sacramento | Sacramento County | SACOG | SACOG | Various intersections in the Natomas and South Sacramento Area. | Replace pedestrian signal heads with countdown pedestrian heads. | 187246.1 | 184685.17 | 2017-11-30 | 0 | 2019-10-21 | 2021-08-18 | 184685.17 | Authorized | Authorized | No | Closed | Federal | 0
H9-03-016 | 9 | 5002209 | 3 | Sacramento | Sacramento County | SACOG | SACOG | Duckhorn Drive from Arena Boulevard to Far Niente Way. | Install curve warning signs and install raised medians. | 490210.79 | 441092.68 | 2019-10-11 | 0 | 2022-02-08 | 2024-10-30 | 441092.68 | Authorized | Authorized | No | Closed | Federal | 0
H9-03-017 | 9 | 5002210 | 3 | Sacramento | Sacramento County | SACOG | SACOG | Valley Hi Drive/La Mancha Way between Creek Centre Court and Wyndham Drive. | Install raised median to reduce access conflicts, install traffic signal, and add pedestrian fencing. | 2361900 | 1842940 | 2019-10-11 | 0 | 2026-03-10 | 0 | 1842940 | Authorized | Authorized | No | CON | Federal | 2
H9-03-018 | 9 | 5002211 | 3 | Sacramento | Sacramento County | SACOG | SACOG | Various segments along Florin Road. | Install raised median, install pedestrian signals, and add pedestrian fencing to encourage crossings at protected crossing locations | 1414200 | 1272780 | 2019-10-11 | 0 | 2022-09-19 | 0 | 1272780 | Authorized | Authorized | No | CON | Federal | 0
H9-03-019 | 9 | 5002212 | 3 | Sacramento | Sacramento County | SACOG | SACOG | Intersection of Lampasas Boulevard and Rio Linda Avenue. | Restripe and realign approaches to improve sight distance, install pedestrian refuge island on uncontrolled pedestrian crossing, and install enhanced pedestrian crossings across all legs. | 1286800 | 1158120 | 2019-10-11 | 2023-08-23 | 2026-03-10 | 0 | 1158120 | Authorized | Authorized | No | CON | Federal | 2
HSIP1-03-001 | 1 | 5002130 | 3 | Sacramento | Sacramento County | SACOG | SACOG | Intersection Of Rio Linda Blvd At Bell Avenue. | Upgrade Traffic Signals To Include Left Turn Phase. | 768200.07 | 364590 | 2008-07-21 | 0 | 2012-01-31 | 2014-04-24 | 364590 | Authorized | Authorized | No | Closed | Federal | 0
HSIP2-03-001 | 2 | 5002133 | 3 | Sacramento | Sacramento County | SACOG | SACOG | Intersection Of Alhambra Blvd. And Folsom Blvd. | Upgrade Traffic Signal With Protected/Split Phases; Add And Upgrade Pedestrian Improvements | 361818.04 | 251211.75 | 2009-12-03 | 0 | 2011-08-29 | 2014-04-03 | 251211.75 | Authorized | Authorized | No | Closed | Federal | 0
HSIP3-03-001 | 3 | 5002145 | 3 | Sacramento | Sacramento County | SACOG | SACOG | 12Th St. Between Richards Blvd. And "L" St. | Upgrade Traffic Signal System; Repair Conduit Infrastructure Between Signals; Provide Dynamic Train And Vehicle Signs; Improve Signing And Striping. | 1693673.39 | 899999.56 | 2010-08-17 | 0 | 2013-09-17 | 2017-02-28 | 899999.56 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-03-018 | 5 | 5002165 | 3 | Sacramento | Sacramento County | SACOG | SACOG | Mack Rd./Valley Hi Dr. (La Mancha Way) | Upgrade traffic signals; install right-turn lane | 968711.13 | 493800 | 2013-05-09 | 2014-04-24 | 2015-08-10 | 2018-03-06 | 493800 | Authorized | Authorized | No | Closed | Federal | 0
HSIP6-03-014 | 6 | 5002170 | 3 | Sacramento | Sacramento County | SACOG | SACOG | 9 locations throughout the City of Sacramento | Install flashing beacon | 1685952.08 | 1290554 | 2014-04-24 | 2016-01-29 | 2016-09-16 | 2018-07-20 | 1290554 | Authorized | Authorized | No | Closed | Federal | 0
HSIP6-03-015 | 6 | 5002171 | 3 | Sacramento | Sacramento County | SACOG | SACOG | On Carlson Dr between approx. 250' north of H St and 250' south of J St; On H ST between Camilla Ave and Carlson Dr | Upgrade traffic signals, signs, and striping; Construct curb ramps and crosswalks | 1836188.22 | 1276479 | 2014-04-15 | 0 | 2016-06-20 | 2018-10-31 | 1276479 | Authorized | Authorized | No | Closed | Federal | 0
HSIP7-03-011 | 7 | 5002183 | 3 | Sacramento | Sacramento County | SACOG | SACOG | 11 locations throughout the City of Sacramento. | Install pedestrian refuge islands and rectangular rapid flashing beacons(RRFB) at uncontrolled crosswalks on collector roadways | 1274139.82 | 1140941.68 | 2016-05-11 | 0 | 2019-05-07 | 2022-03-08 | 1140941.68 | Authorized | Authorized | No | Closed | Federal
HSIP7-03-012 | 7 | 5002184 | 3 | Sacramento | Sacramento County | SACOG | SACOG | Six locations throughout the City of Sacramento. | Install advanced dilemma zone loops for the high speed approaches at six existing signalized intersections | 456342.5 | 453495.13 | 2016-05-11 | 0 | 2019-03-27 | 2020-08-25 | 453495.13 | Authorized | Authorized | No | Closed | Federal
HSIP7-03-013 | 7 | 5002185 | 3 | Sacramento | Sacramento County | SACOG | SACOG | Various downtown corridors bounded by Interstate 5, Broadway, Alhambra Boulevard, and C Street, including the intersections of North 16th St/Sproule St-Basler St and North 16th Street/North B Street. | Install pedestrian countdown signal heads; replace 8" with 12" vehicle signal heads; install emergency vehicle preemption equipment | 2894524.94 | 2882082.65 | 2016-05-11 | 0 | 2019-03-27 | 2022-11-10 | 2882082.65 | Authorized | Authorized | No | Closed | Federal
HSIP7-03-014 | 7 | 5002186 | 3 | Sacramento | Sacramento County | SACOG | SACOG | Three corridors: On Freeport Bl from Meadowview Rd to Florin Rd, on Rio Linda Bl from North Ave to Claire Ave, and on Meadowview from Amherst to 24th St. | Install street lighting | 1731324.79 | 1627100.97 | 2016-05-11 | 0 | 2019-04-05 | 2021-08-18 | 1627100.97 | Authorized | Authorized | No | Closed | Federal
HSIP7-03-015 | 7 | 5002187 | 3 | Sacramento | Sacramento County | SACOG | SACOG | Nine locations throughout the City of Sacramento. | Install eight pedestrian hybrid beacons and one pedestrian signal(HAWK) at uncontrolled crosswalks | 2150477.89 | 2016630.08 | 2016-05-11 | 0 | 2019-06-21 | 2022-11-14 | 2016630.08 | Authorized | Authorized | No | Closed | Federal
HSIP7-03-016 | 7 | 5002188 | 3 | Sacramento | Sacramento County | SACOG | SACOG | Five signalized locations throughout the City of Sacramento. | Install mast arm traffic signals to replace traffic signal heads mounted on pedestals in median | 1727813.97 | 1346500 | 2016-05-11 | 0 | 2020-03-25 | 2023-12-04 | 1346500 | Authorized | Authorized | No | Closed | Federal
H10-03-022 | 10 | 5924263 | 3 | Sacramento County | Sacramento County | SACOG | SACOG | The Intersection of Fair Oaks Boulevard and Kenneth Avenue. | Signalization of intersection to mitigate collisions and improve safety. | 1674000 | 915800 | 2021-07-14 | 2022-05-24 | 2024-07-10 | 0 | 815800 | Authorized | Authorized | No | CON | State | 0
H10-03-023 | 10 | 5924262 | 3 | Sacramento County | Sacramento County | SACOG | SACOG | 15 locations within Sacramento County | The project will upgrade existing guardrails and their end treatment at 15 locations | 999900 | 999900 | 2021-07-09 | 0 | 2022-11-16 | 2025-07-08 | 999900 | Authorized | Authorized | No | Closed | State | 0
H11-03-021 | 11 | 5924278 | 3 | Sacramento County | Sacramento County | SACOG | SACOG | 167 signalized intersections throughout the unincorporated County. | Provide enhanced pedestrian safety and compliance at signalized intersections with existing pedestrian crossings by installing countdown pedestrian modules. | 220300 | 198270 | 2023-11-13 | 0 | 2025-10-07 | 0 | 198270 | Authorized | Authorized | No | CON | State | 0
H11-03-022 | 11 | 5924279 | 3 | Sacramento County | Sacramento County | SACOG | SACOG | 512 signalized intersections throughout the unincorporated County. | Provide enhanced visibility of traffic signal indications by upgrading signal backplates to include retro-reflective yellow boarders. | 896200 | 806580 | 2023-11-01 | 0 | 2025-11-03 | 0 | 806580 | Authorized | Authorized | No | CON | State | 0
H11-03-023 | 11 | 5924280 | 3 | Sacramento County | Sacramento County | SACOG | SACOG | Various roadways adjacent to 13 schools within unincorporated Sacramento County. | Install flashing beacons on school speed limit signs, school ahead signs, and school crosswalk signs. | 277600 | 249840 | 2023-10-31 | 0 | 2024-12-10 | 0 | 249840 | Authorized | Authorized | No | CON | State | 0
H12-03-022 | 12 | 5924295 | 3 | Sacramento County | Sacramento County | SACOG | SACOG | Intersection of Elkhorn Boulevard and 28th St. | Install traffic signal. | 1666000 | 1499400 | 2025-07-02 | 0 | 0 | 0 | 218700 | Authorized | Due by 3/31/2028 | No | PE | Federal | 0
H12-03-023 | 12 | 5924296 | 3 | Sacramento County | Sacramento County | SACOG | SACOG | Florin Rd at Power Inn Rd; Gerber Rd at Power Inn Rd; 47th Ave at MLK Jr Blvd; Lindale Dr at Stockton Blvd; 65th St at Sky Pkwy; French Rd at Gerber Rd; and 65th St Expressway at 53rd Ave. | Implement leading pedestrian interval (LPI) at 6 signals; install one new traffic signal with LPI at 65th St at 53rd Ave. | 1170000 | 1053000 | 2025-06-18 | 0 | 0 | 0 | 159570 | Authorized | Due by 3/31/2028 | No | PE | State | 0
H8-03-016 | 8 | 5924235 | 3 | Sacramento County | Sacramento County | SACOG | SACOG | Florin Rd between Franklin Blvd and Power Inn Rd (excluding the segment at the SR-99 interchange). | Install bicycle lanes, upgrade traffic signals to accommodate bicycles at all intersections, construct ADA improvements, install roadway lighting for a segment of Florin Rd. | 3637400 | 3273660 | 2017-07-01 | 2018-11-29 | 2021-12-08 | 0 | 3273660 | Authorized | Authorized | No | CON | Federal | 0
H8-03-017 | 8 | 5924236 | 3 | Sacramento County | Sacramento County | SACOG | SACOG | Power Inn Road from Elsie Avenue to about 400 feet north of Macfadden Drive. | Install curb, gutter, sidewalk infill and curb ramps; widen substandard bike lanes. | 4391269.3 | 3254860 | 2017-03-24 | 2019-02-27 | 2021-09-15 | 2025-11-05 | 3254860 | Authorized | Authorized | No | Closed | Federal | 0
H9-03-020 | 9 | 5924245 | 3 | Sacramento County | Sacramento County | SACOG | SACOG | Coyle Avenue from Woodleigh Drive to Dewey Drive, Hillsdale Boulevard from Frizell Avenue to McCloud Drive, and Watt Avenue from Elkhorn Boulevard to 700' north of Elkhorn Boulevard. | Install street lighting. | 2799046.91 | 2610000 | 2019-06-10 | 0 | 2022-02-08 | 2025-04-28 | 2610000 | Authorized | Authorized | No | Closed | Federal | 0
H9-03-021 | 9 | 5924246 | 3 | Sacramento County | Sacramento County | SACOG | SACOG | Various locations along Edison Avenue, El Camino Avenue, Hurley Way, Manzanita Avenue, and Marconi Avenue | Construct curb, gutter, sidewalk infill and curb ramps, and install street lighting. | 3729000 | 2511100 | 2019-06-10 | 2021-03-01 | 2023-08-04 | 0 | 2511100 | Authorized | Authorized | No | CON | Federal | 2
H9-03-022 | 9 | 5924247 | 3 | Sacramento County | Sacramento County | SACOG | SACOG | Morse Avenue between Hurley Way and Arden Way | Construct curb, gutter, sidewalk infill and curb ramps, and install street lighting. | 1540709.68 | 1471720 | 2019-06-10 | 2020-09-11 | 2021-09-15 | 2025-02-25 | 1471720 | Authorized | Authorized | No | Closed | Federal | 0
H9-03-023 | 9 | 5924248 | 3 | Sacramento County | Sacramento County | SACOG | SACOG | Intersection of Roseville Road with Diablo Drive/Stationers Way | Signalize the intersection. | 1196411.97 | 982700 | 2019-06-10 | 0 | 2022-02-28 | 2024-11-13 | 982700 | Authorized | Authorized | No | Closed | Federal | 0
HSIP1-03-007 | 1 | 5924148 | 3 | Sacramento County | Sacramento County | SACOG | SACOG | Intersection Of Cypress Ave. And Garfield Ave. | Install Traffic Signals With Minor Widening. | 653035.5 | 392325 | 2008-03-24 | 0 | 2008-03-26 | 2011-09-06 | 392325 | Authorized | Authorized | No | Closed | Federal | 0
HSIP2-03-014 | 2 | 5924153 | 3 | Sacramento County | Sacramento County | SACOG | SACOG | At Intersection Of Watt Ave. And Larchmont Dr. | Install Traffic Signal; Construct Sidewalks, Curb Ramps. Pedestrian Pads And Raised Median | 506657.91 | 378870.35 | 0 | 0 | 2011-03-24 | 2013-02-22 | 378870.35 | No PE | Authorized | No | Closed | Federal | 0
HSIP3-03-007 | 3 | 5924165 | 3 | Sacramento County | Sacramento County | SACOG | SACOG | Florin Rd. At East Southgate Dr.; Fruitridge Rd. At Mendocino Blvd. | Install Raised Median | 103034.76 | 73828.62 | 0 | 0 | 2011-08-15 | 2012-12-11 | 73828.62 | No PE | Authorized | No | Closed | Federal | 0
HSIP4-03-004 | 4 | 5924185 | 3 | Sacramento County | Sacramento County | SACOG | SACOG | Fair Oaks Blvd. between San Ramon Way and Eastern Ave. | Install median barrier | 812000.84 | 613108.15 | 2011-05-03 | 0 | 2011-10-18 | 2014-03-04 | 613108.15 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-03-019 | 5 | 5924196 | 3 | Sacramento County | Sacramento County | SACOG | SACOG | Fair Oaks Blvd. between Day Dr. and Arden Way | Install sidewalks, curb ramps, curb and gutter | 562599.38 | 369220.47 | 2013-04-02 | 0 | 2014-07-11 | 2019-06-13 | 369220.47 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-03-020 | 5 | 5924197 | 3 | Sacramento County | Sacramento County | SACOG | SACOG | Howe Ave. between El Camino Ave. and Shaw St. | Construct sidewalks, curb ramps, curb and gutter; install mid-block signalized crosswalk | 1407154.48 | 371689.65 | 2013-04-30 | 0 | 2014-11-26 | 2019-06-13 | 371689.65 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-03-021 | 5 | 5924198 | 3 | Sacramento County | Sacramento County | SACOG | SACOG | Ten (10) signalized intersections throughout the city | Provide advanced "dilemma zone" protection for the high speed main street approaches at ten existing signalized intersections. | 441516.26 | 280697.08 | 2013-08-01 | 0 | 2015-08-28 | 2019-06-13 | 280697.08 | Authorized | Authorized | No | Closed | Federal | 0
HSIP6-03-016 | 6 | 5924205 | 3 | Sacramento County | Sacramento County | SACOG | SACOG | On Cottage Way between Cortez Lane and Watt Ave | Install bike lanes, a "road diet" (reduce travel lanes from 4 to 3), and modify intersections | 1412093.51 | 673498.98 | 2014-04-24 | 0 | 2014-05-01 | 2019-06-13 | 673498.98 | Authorized | Authorized | No | Closed | Federal | 0
HSIP6-03-017 | 6 | 5924206 | 3 | Sacramento County | Sacramento County | SACOG | SACOG | Various locations throughout Sacramento County | Construct sidewalks, curb ramps, curbs and gutters | 1688302.31 | 1105198.68 | 2014-02-19 | 0 | 2017-01-06 | 2019-05-06 | 1105198.68 | Authorized | Authorized | No | Closed | Federal | 0
HSIP6-03-018 | 6 | 5924207 | 3 | Sacramento County | Sacramento County | SACOG | SACOG | Various locations throughout Sacramento County | Construct sidewalks, curb ramps, curbs and gutters; Upgrade traffic signals | 2037051.35 | 1474100.97 | 2014-02-19 | 2015-11-30 | 2016-11-14 | 2019-11-21 | 1474100.97 | Authorized | Authorized | No | Closed | Federal | 0
HSIP6-03-019 | 6 | 5924208 | 3 | Sacramento County | Sacramento County | SACOG | SACOG | 32 intersections throughout Sacramento County | Upgrade traffic signals | 1216451.8 | 1052289 | 2014-06-27 | 0 | 2016-08-17 | 2019-09-03 | 1052289 | Authorized | Authorized | No | Closed | Federal | 0
HSIP7-03-017 | 7 | 5924226 | 3 | Sacramento County | Sacramento County | SACOG | SACOG | On Auburn Blvd. beginning 200' west of Annadale Lane continuing eastward to Winding Way | Construct sidewalk infill, Class II bike lanes and install a pedestrian Hawk type signal, located near the intersection of Auburn and Annadale Lane | 3577560.79 | 2462700 | 2016-05-23 | 2017-11-13 | 2019-04-22 | 2021-11-18 | 2462700 | Authorized | Authorized | No | Closed | Federal
HSIP7-03-018 | 7 | 5924227 | 3 | Sacramento County | Sacramento County | SACOG | SACOG | 41 Signalized intersections on portions of Winding Way, Walnut Avenue, Marconi Avenue, El Camino Avenue, Elkhorn Boulevard, and Hazel Avenue. Forty-one (41) intersections total. | Provide enhanced signal coordination and monitoring forty-one existing signalized intersections by upgrading the signal control equipment and interconnect to allow for traffic responsive signal coordination on the new County central signal system. | 1579191.72 | 1536500 | 2016-09-15 | 0 | 2018-12-19 | 2021-03-11 | 1536500 | Authorized | Authorized | No | Closed | Federal
H10-03-024 | 10 | 5913078 | 3 | Sierra County | Sierra County | RURAL | Sierra LTC | On Pike City Road at 3 locations, on Brandy City Road at 9 locations, and on Upper Main Street at 3 locations. | Replace damaged guardrail with steel posts. | 539500 | 539500 | 2021-09-01 | 0 | 2023-02-10 | 2024-04-05 | 539500 | Authorized | Authorized | No | Closed | State | 0
H9-03-024 | 9 | 5398016 | 3 | South Lake Tahoe | El Dorado County | TMPO | Tahoe RPA | Intersection of Pioneer Trail with Edna Street. | Install dynamic speed feedback signs on Pioneer Trail on approaches. At intersection, install edge-lines and centerlines, intersection warning signs for minor streets, intersection lighting, upgrade pavement markings, and widen shoulder. | 170100 | 153090 | 2019-11-07 | 0 | 2024-08-30 | 0 | 153090 | Authorized | Authorized | No | CON | Federal | 0
HSIP2-03-010 | 2 | 5918070 | 3 | Sutter County | Sutter County | SACOG | SACOG | Butte House Rd. Between Humphrey Rd. And A Point 3500 Feet East Of East Butte House Rd. | Widen Shoulders | 584688.33 | 524407.56 | 2009-07-08 | 0 | 2011-12-11 | 2014-04-03 | 524407.56 | Authorized | Authorized | No | Closed | Federal | 0
HSIP6-03-020 | 6 | 5918089 | 3 | Sutter County | Sutter County | SACOG | SACOG | Various locations throughout Sutter County | Install stripping, pavement markers, and Raised pavement reflectors | 454464.83 | 415263.56 | 2014-12-15 | 0 | 2017-09-11 | 2019-12-11 | 415263.56 | Authorized | Authorized | No | Closed | Federal | 0
HSIP7-03-019 | 7 | 5918103 | 3 | Sutter County | Sutter County | SACOG | SACOG | Acacia Avenue and Pass Road from Butte House Road to Mawson Road. | Replace faded and missing painted edge lines, center lines and pavement markers with upgraded thermoplastic traffic striping and new pavement markers | 163140.81 | 160678.33 | 2016-11-02 | 0 | 2018-04-03 | 2019-12-11 | 160678.33 | Authorized | Authorized | No | Closed | Federal
H11-03-024 | 11 | 0 | 3 | Truckee | Nevada County | RURAL | Nevada LTC | The intersection of Bridge Street with Donner Pass Road and the intersection of Bridge Street with West River Street/ East River Street. | At each intersection, install traffic signals, sidewalks, curbs, curb ramps. Link signal phasing of both intersections with the railroad crossing. Install/ upgrade pedestrian crossings (with enhanced safety features). Add ped. gate at RR Xing. | 7009600 | 249648 | 0 | 0 | 0 | 0 | 0 | No PE | Due by 9/30/2026 | No | Not Started | State | -1
H12-03-024 | 12 | 0 | 3 | Truckee | Nevada County | RURAL | Nevada LTC | Various locations throughout the Town of Truckee. | Upgrade guardrails. | 932500 | 839250 | 0 | 0 | 0 | 0 | 0 | No PE | Due by 3/31/2028 | No | Not Started | State | 0
H9-03-025 | 9 | 5473023 | 3 | Truckee | Nevada County | RURAL | Nevada LTC | Various locations. | Upgrade guardrails. | 268365.07 | 230917.04 | 0 | 0 | 2020-03-10 | 2021-02-18 | 230917.04 | No PE | Authorized | No | Closed | Federal | 0
HSIP5-03-022 | 5 | 5473016 | 3 | Truckee | Nevada County | RURAL | Nevada LTC | Glenshire Dr. from 1,500' W of Highlands Ave. to 1,000' E of Highlands Ave. | Widen to include bike lanes on the shoulders and improve vertical and horizontal alignments or sight distance | 1043690.46 | 899816.02 | 2013-06-20 | 0 | 2015-07-01 | 2017-02-08 | 899816.02 | Authorized | Authorized | No | Closed | Federal | 0
HSIP6-03-021 | 6 | 5473019 | 3 | Truckee | Nevada County | RURAL | Nevada LTC | On Donner Pass Road (Lincoln Hwy)between Interstate 80-Coldstream Interchange and Frates Lane/SR 89 | Install raised medians, sidewalks | 6545878.26 | 1499999.95 | 2014-04-14 | 0 | 2017-08-22 | 2020-10-07 | 1499999.95 | Authorized | Authorized | No | Closed | Federal | 0
H9-03-026 | 9 | 5447047 | 3 | West Sacramento | Yolo County | SACOG | SACOG | Various signalized and non-signalized intersections. | Install approach medians and medians to prohibit left turns. | 581644 | 339895 | 2019-10-11 | 0 | 2024-02-06 | 0 | 339895 | Authorized | Authorized | No | CON | Federal | 0
H9-03-027 | 9 | 5447048 | 3 | West Sacramento | Yolo County | SACOG | SACOG | Various signalized intersections. | Improve signal hardware and install flashing beacons. | 1365497 | 876350 | 2019-09-06 | 0 | 2024-02-06 | 0 | 876350 | Authorized | Authorized | No | CON | Federal | 0
H9-03-028 | 9 | 5447049 | 3 | West Sacramento | Yolo County | SACOG | SACOG | Intersections of Jefferson Blvd & 11th St , C St & 6th St, Sacramento Ave & Solano St, and Sacramento Ave & Simon Terrace. | Install crossings with RRFBs and refuge islands, construct curb extensions, crosswalks, and other crossing improvements. | 757781 | 699013 | 2019-10-11 | 0 | 2024-02-14 | 0 | 699013 | Authorized | Authorized | No | CON | Federal | 2
H9-03-029 | 9 | 5447050 | 3 | West Sacramento | Yolo County | SACOG | SACOG | Various locatoins including Reuter/Andrews, Poplar/Westfield Village ES, Carrie Street/Bryte Park, Quail-Columbus Shared Use Path, and Columbus/La Jolla at Stonegate ES. | Install striping for high-visibility crossings and stop bars, install RRFBs and signage, and construct ADA Curb Ramps, and curb extensions. | 209919 | 209919 | 2019-09-06 | 0 | 2024-02-27 | 0 | 209919 | Authorized | Authorized | No | CON | Federal | 2
HSIP7-03-020 | 7 | 5447042 | 3 | West Sacramento | Yolo County | SACOG | SACOG | West Capitol Ave from Interstate 80 overpass to Jefferson Blvd and Jefferson Blvd from West Capitol Ave to Park Blvd. | Install bicycle lanes, enhanced crosswalks and lighting | 4244099.07 | 602100 | 2016-08-04 | 0 | 2019-12-13 | 2025-06-04 | 602100 | Authorized | Authorized | No | Closed | Federal
H11-03-025 | 11 | 5246009 | 3 | Williams | Colusa County | RURAL | Colusa LTC | Various intersections throughout the city: (1) I-5 and SR-20 NB Ramps, (2) SR-20 and Husted Rd., (3) E. St. and SR-20, (4) Old Hwy 99 and Crawford Rd., (5) Ruggeri Wy and Vann St., and (6) Abel Rd and Husted Rd. | Upgrade intersection pavement markings, install flashing beacons as advance warning (NS.I), and install transverse rumble strips on approaches. | 320000 | 288000 | 2023-11-07 | 0 | 0 | 0 | 16020 | Authorized | Due by 9/30/2026 | No | PE | State | 0
H11-03-026 | 11 | 5246010 | 3 | Williams | Colusa County | RURAL | Colusa LTC | 8th St. and F St. | Install raised medians (refuge islands), install/upgrade pedestrian crossings at uncontrolled locations (with enhanced safety features,) and install Rectangular Rapid Flashing Beacons (RRFBs). | 332700 | 299430 | 2023-11-07 | 0 | 0 | 0 | 20790 | Authorized | Due by 9/30/2026 | No | PE | State | 0
H10-03-025 | 10 | 5046050 | 3 | Woodland | Yolo County | SACOG | SACOG | Intersection of East Street and Main Street in the City of Woodland. | Intersection signal improvements. | 336900 | 158450 | 0 | 0 | 2025-02-04 | 0 | 158450 | No PE | Authorized | No | CON | State | 0
H10-03-026 | 10 | 5046049 | 3 | Woodland | Yolo County | SACOG | SACOG | Pedestrian Crossings at Dingle and Zamora Elementary Schools in Woodland. | Installation of Rectangular Rapid Flashing Beacons (RRFB) and AC Powered Speed Feedback Signs. | 354809 | 250000 | 0 | 0 | 2024-10-10 | 0 | 250000 | No PE | Authorized | No | CON | State | 0
H12-03-025 | 12 | 0 | 3 | Woodland | Yolo County | SACOG | SACOG | Intersection of West Street and Beamer Street. | Upgrade signal hardware, improve signal timing, and install left-turn lanes and ADA ramps. | 903500 | 451750 | 0 | 0 | 0 | 0 | 0 | No PE | Due by 3/31/2028 | No | Not Started | State | 0
H12-03-026 | 12 | 0 | 3 | Woodland | Yolo County | SACOG | SACOG | Pedestrian crossings at Freeman Elementary School, Tafoya Elementary School, Dignity Health Complex, and at the multi-use paths at Farmers Central and the Heritage Parkway. | Install rectangular rapid flashing beacons (RRFBs) and AC Powered speed feedback signs. | 388800 | 349920 | 0 | 0 | 0 | 0 | 0 | No PE | Due by 3/31/2028 | No | Not Started | State | 0
H9-03-030 | 9 | 5046046 | 3 | Woodland | Yolo County | SACOG | SACOG | The intersection of California Street and Gibson Road. | Install marked pedestrian crossing, install Rectangular Rapid Flashing Beacon (RRFB) and pedestrian refuge island. | 216000 | 216000 | 0 | 0 | 2021-04-19 | 0 | 216000 | No PE | Authorized | No | CON | Federal | 0
HSIP1-03-008 | 1 | 6203041 | 3 | Woodland | Yolo County | SACOG | SACOG | Intersection Of Sr16 At Kentucky Ave/County Road 20. | Cooperative Project With Caltrans. Install New Traffic Signals And Modify Intersection. Woodland Share 25% For Kentucky Avenue. | 689209.68 | 613854.96 | 0 | 0 | 2009-05-08 | 2013-09-06 | 613854.96 | No PE | Authorized | No | Closed | Federal | 0
HSIP4-03-009 | 4 | 5046034 | 3 | Woodland | Yolo County | SACOG | SACOG | Main St./Cleveland St. | Upgrade traffic signals | 334111.9 | 252200 | 2011-08-29 | 0 | 2016-04-11 | 2017-09-05 | 252200 | Authorized | Authorized | No | Closed | Federal | 0
H11-03-027 | 11 | 5922126 | 3 | Yolo County | Yolo County | SACOG | SACOG | In Yolo County along County Road (CR) 102 between CR 29(N) and Pole Line Rd (City of Davis Limit). | Widen the shoulders and install centerline rumble strips. | 870600 | 783540 | 2023-10-02 | 0 | 0 | 0 | 108000 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE | State | 0
H8-03-018 | 8 | 5922110 | 3 | Yolo County | Yolo County | SACOG | SACOG | Old River Road (south of County Road 124) and South River Road (south of Freeport Bridge). | Upgrade existing guardrails and end treatments. | 1134018.19 | 1134018.19 | 2017-08-14 | 0 | 2019-04-04 | 2021-10-18 | 1134018.19 | Authorized | Authorized | No | Closed | Federal | 0
H9-03-031 | 9 | 5922115 | 3 | Yolo County | Yolo County | SACOG | SACOG | Various locations on South River Road (north of Babel Slough Road, north of Freeport Bridge , and south of Freeport Bridge) | Upgrade existing guardrails and end treatments to meet current standards. | 690575.59 | 690575.59 | 2019-09-09 | 0 | 2021-04-15 | 2024-10-22 | 690575.59 | Authorized | Authorized | No | Closed | Federal | 1
HRRR1-03-018 | 1 | 5922075 | 3 | Yolo County | Yolo County | SACOG | SACOG | CR 140 between CR 141 and CR 142 | Widen or Improve Shoulder | 1483971.33 | 900000 | 2007-12-18 | 0 | 2010-04-30 | 2013-11-08 | 900000 | Authorized | Authorized | No | Closed | Federal | 0
HRRR1-03-019 | 1 | 5922076 | 3 | Yolo County | Yolo County | SACOG | SACOG | CR 23 between CR 86A and CR 86B | Widen or Improve Shoulder | 733963.57 | 612000 | 2007-12-18 | 2008-09-17 | 2010-07-15 | 2013-09-12 | 612000 | Authorized | Authorized | No | Closed | Federal | 0
HSIP2-03-011 | 2 | 5922081 | 3 | Yolo County | Yolo County | SACOG | SACOG | County Road 22 From Cr 26 To Cr 128A | Widen Shoulders; Rehab Roadway; Install Rumble Strips On Shoulders And Along Centerline | 2029588.16 | 686815 | 2009-03-04 | 0 | 2011-02-23 | 2014-02-25 | 686815 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-03-023 | 5 | 5922047 | 3 | Yolo County | Yolo County | SACOG | SACOG | County Road 98 between County Roads 25A and 27 | Widen and pave shoulders; remove fixed objects | 900000 | 900000 | 2001-10-18 | 2008-11-04 | 2013-04-30 | 2020-01-15 | 900000 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-03-024 | 5 | 5922094 | 3 | Yolo County | Yolo County | SACOG | SACOG | County Road 31/County Road 95 | Install left-turn lanes | 767015.04 | 623599 | 2013-08-22 | 0 | 2015-05-01 | 2018-02-28 | 623599 | Authorized | Authorized | No | Closed | Federal | 0
HSIP7-03-021 | 7 | 5922107 | 3 | Yolo County | Yolo County | SACOG | SACOG | Various locations throughout the County, a systemic application. | Perform Roadway Striping Audit to determine MUTCD compliance, install upgraded centerlines and edge-lines using thermoplastic striping with reflective beads | 3248416.01 | 3248416.01 | 2016-08-31 | 0 | 2018-04-20 | 2022-01-14 | 3248416.01 | Authorized | Authorized | No | Closed | Federal
H10-03-027 | 10 | 5163041 | 3 | Yuba City | Sutter County | SACOG | SACOG | Various signalized intersections throughout the City of Yuba City. | Improve signal hardware at 37 signalized intersections. Improvements include new backplates, replacing 8" bulbs with 12", adding/replacing LED IISNS, and installing reflective tape. | 818935 | 742754 | 2021-12-07 | 0 | 2024-10-16 | 0 | 742754 | Authorized | Authorized | No | CON | State | 0
H10-03-028 | 10 | 5163042 | 3 | Yuba City | Sutter County | SACOG | SACOG | Various arterial and collector roadways throughout the City of Yuba City. | Installation and/or upgrade signs with new fluorescent sheeting, as well as the completion of a Roadway Safety Signing Audit. | 1835400 | 1835400 | 2021-12-07 | 0 | 2024-11-01 | 0 | 1835400 | Authorized | Authorized | No | CON | State | 0
H10-03-029 | 10 | 5163043 | 3 | Yuba City | Sutter County | SACOG | SACOG | Various unsignalized intersections in Yuba City. | Crosswalk improvements at 15 unsignalized intersections, primarily near schools. Improvements include replacing standard crosswalks with high visibility striping, advance stop bars, yield lines, and ADA improvements. | 199100 | 199100 | 2021-12-07 | 0 | 2024-10-18 | 0 | 193862 | Authorized | Authorized | No | CON | State | 0
H10-03-030 | 10 | 5163044 | 3 | Yuba City | Sutter County | SACOG | SACOG | Various State Highway Signalized intersections within City of Yuba City limits. | Improve Signal Hardware at 17 State Highway Signalized Intersections. Improvements include new back plates, replacing 8" bulbs and lenses with 12", adding/replacing TYPE IX Street Name Signs, and installing reflective tape. | 510600 | 510600 | 2021-12-07 | 0 | 2024-10-09 | 0 | 328075 | Authorized | Authorized | No | CON | State | 0
H12-03-027 | 12 | 5163048 | 3 | Yuba City | Sutter County | SACOG | SACOG | The intersection of Market Street and Bird Street. | Install pedestrian hybrid beacons. | 230500 | 207450 | 0 | 0 | 2026-01-28 | 0 | 207450 | No PE | Authorized | No | CON | State | 0
HSIP5-03-025 | 5 | 5163030 | 3 | Yuba City | Sutter County | SACOG | SACOG | 14 intersections within the City limits | Upgrade bike lanes striping | 131169 | 115700 | 0 | 0 | 2015-08-13 | 2018-03-16 | 115700 | No PE | Authorized | No | Closed | Federal | 0
H10-03-031 | 10 | 5916139 | 3 | Yuba County | Yuba County | SACOG | SACOG | North Beale Road, starting at a point 300 feet SE of the intersection with Feather River Blvd. and extending 3,000 feet NW to the SR70 on-ramp. | Improve pavement friction by installing High Friction Surface Treatment, plus installing edge lines, centerlines, delineators, reflectors, and object markers. | 788418 | 788418 | 2021-04-23 | 0 | 2024-04-15 | 0 | 788418 | Authorized | Authorized | No | CON | State | 0
H10-03-032 | 10 | 5916138 | 3 | Yuba County | Yuba County | SACOG | SACOG | The entirety of Old Dobbins Road and on La Porte Road from Barton Hill Road to the Plumas County line. | Install edge lines, centerlines, reflectors, object markers, and improved reflective signs. | 374100 | 374100 | 2021-04-23 | 0 | 2024-04-16 | 2025-10-06 | 374100 | Authorized | Authorized | No | Closed | State | 0
H11-03-028 | 11 | 5916156 | 3 | Yuba County | Yuba County | SACOG | SACOG | Various locations throughout the Yuba County. | Install/upgrade signs with new fluorescent sheeting (regulatory or warning). | 4448000 | 4003200 | 2024-03-28 | 0 | 2026-03-23 | 0 | 4003200 | Authorized | Authorized | No | CON | State | 0
H11-03-029 | 11 | 5916148 | 3 | Yuba County | Yuba County | SACOG | SACOG | Nine (9) Signalized Intersections along multiple roadway segments within County of Yuba. | Improve signal hardware: lenses, back-plates with retro-reflective borders, mounting, size, and number; Install pedestrian countdown signal heads; and Implement Leading Pedestrian Intervals. | 768810 | 691930 | 2023-09-11 | 0 | 2025-06-02 | 0 | 691930 | Authorized | Authorized | No | CON | Federal | 1
H12-03-028 | 12 | 5916161 | 3 | Yuba County | Yuba County | SACOG | SACOG | Forty Mile Road between Rosser Road and the north entrance to the Hard Rock Hotel & Casino. | Construct shared-use path, install segment lighting, K-Rail barrier, traffic signs, and pavement markings. | 7036000 | 6332400 | 2025-05-05 | 0 | 0 | 0 | 291600 | Authorized | Due by 3/31/2028 | No | PE | Federal | 1
H8-03-019 | 8 | 5916119 | 3 | Yuba County | Yuba County | SACOG | SACOG | Four road segments: Loma Rica Road, Marysville Road, La Porte Road, and Willow Glen Road. | Upgrade traffic markings using "audible" thermoplastic striping with cookies to provide better visibility and tactile feedback. | 947961.71 | 947961.71 | 2017-06-15 | 0 | 2019-09-06 | 2021-08-20 | 947961.71 | Authorized | Authorized | No | Closed | Federal | 0
H9-03-032 | 9 | 5916128 | 3 | Yuba County | Yuba County | SACOG | SACOG | Multiple roadways including Simpson Lane, Hammonton-Smartsville Road, Olivehurst Avenue, Olive Avenue, Linda Avenue, and Arboga Road. | Install thermoplastic centerline and edge-line striping. | 143612.81 | 143612.81 | 0 | 0 | 2020-01-21 | 2021-10-18 | 143612.81 | No PE | Authorized | No | Closed | Federal | 0
HRRR1-03-013 | 1 | 5916073 | 3 | Yuba County | Yuba County | SACOG | SACOG | Intersection of Spenceville Rd. at Camp Far West/Monarch Trail | New left-turn lane at nonsignalized intersection | 448720.31 | 355499.98 | 2007-12-18 | 2009-03-04 | 2010-05-25 | 2013-08-01 | 355499.98 | Authorized | Authorized | No | Closed | Federal | 0
HRRR2-03-014 | 2 | 5916078 | 3 | Yuba County | Yuba County | SACOG | SACOG | Loma Rica Road from Verjeles Rd. to Marysville Rd. | Widen shoulders; extend culverts; improve drainage; install pavement markings and striping. | 2190371.02 | 899999.97 | 2009-03-04 | 2012-07-30 | 2013-08-22 | 2016-10-20 | 899999.97 | Authorized | Authorized | No | Closed | Federal | 0
HSIP1-03-004 | 1 | 5916076 | 3 | Yuba County | Yuba County | SACOG | SACOG | Intersection Of Hammonton-Smartville Road And Simpson Lane In Linda. | Install New 3-Phase Traffic Signal. | 359089.16 | 323180.11 | 2008-04-04 | 2009-07-22 | 2010-08-12 | 2013-01-02 | 323180.11 | Authorized | Authorized | No | Closed | Federal | 0
HSIP3-03-003 | 3 | 5916085 | 3 | Yuba County | Yuba County | SACOG | SACOG | Hammonton-Smartsville Rd. From 0.7 Miles West To 2 Miles West Of South Golden Parkway | Widen The Typical Shoulder Section To 4' Of Pavement With 3' Of Aggregate Base Rock | 947698.15 | 580499.96 | 2010-07-20 | 0 | 2013-02-20 | 2014-04-01 | 580499.96 | Authorized | Authorized | No | Closed | Federal | 0
HSIP3-03-004 | 3 | 5916086 | 3 | Yuba County | Yuba County | SACOG | SACOG | North Beale Rd. From Feather River Blvd. To Linda Ave. | Install Raised Median | 1222343.37 | 899200.2 | 2010-07-20 | 0 | 2012-09-18 | 2015-12-01 | 899200.2 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-03-026 | 5 | 5916100 | 3 | Yuba County | Yuba County | SACOG | SACOG | Hammonton-Smartsville Rd. from 0.18 mile E of Doolittle Gate Rd. to 2.28 miles E of Doolittle Gate Rd. | Widen and pave shoulders, curve corrections | 1446136.94 | 899999.96 | 2013-04-03 | 0 | 2016-05-04 | 2018-10-15 | 899999.96 | Authorized | Authorized | No | Closed | Federal | 0
HSIP6-03-022 | 6 | 5916109 | 3 | Yuba County | Yuba County | SACOG | SACOG | Hammonton Smartville Rd between S Golden Parkway and approx. 1 mile west | Widen and pave shoulder, including installation of safety edge | 943959.09 | 656499.98 | 2014-06-27 | 0 | 2016-05-31 | 2019-05-13 | 656499.98 | Authorized | Authorized | No | Closed | Federal | 0
HSIP6-03-023 | 6 | 5916110 | 3 | Yuba County | Yuba County | SACOG | SACOG | On Feather River Blvd between County Rd 512 and Algodon Rd | Improve horizontal alignments | 1390927.09 | 1204180.25 | 2014-07-03 | 2016-07-27 | 2018-02-22 | 2020-10-15 | 1204180.25 | Authorized | Authorized | No | Closed | Federal | 0
H10-04-001 | 10 | 5014049 | 4 | Alameda | Alameda County | MTC | MTC | four intersections: Santa Clara Avenue/Grand Street, Otis Drive/Willow Street, Otis Drive/Park Street, and Fernside Blvd./San Jose Avenue. | Provide upgraded traffic signal equipment, timing and striping to improve pedestrian safety. Upgraded equipment includes cabinets, controllers, video detection, audible pedestrian signals and signal heads. | 273100 | 249076 | 0 | 0 | 2023-09-14 | 2025-11-04 | 249076 | No PE | Authorized | No | Closed | State | 0
HSIP4-04-002 | 4 | 5014037 | 4 | Alameda | Alameda County | MTC | MTC | Shoreline Dr. between Westline Dr. and Broadway; Westline Dr. between Otis Dr. and Shoreline Dr.; Broadway between Shoreline Dr. and Bayview Dr. | Reduce traveled lanes from four to two; install bike lanes, bike racks, and crosswalks; construct bus pad, shelter, and drainage improvements | 961255.99 | 416400 | 2012-01-18 | 0 | 2014-03-05 | 2015-08-31 | 416400 | Authorized | Authorized | No | Closed | Federal | 0
HSIP4-04-010 | 4 | 5014038 | 4 | Alameda | Alameda County | MTC | MTC | Park St. between Park St. Draw Br. and Encinal Ave. (SR 61) | Install left-turn phasing and advance flashing beacons; upgrade signal operations | 948867.63 | 549911.1 | 2012-01-18 | 0 | 2015-05-13 | 2021-06-09 | 549911.1 | Authorized | Authorized | No | Closed | Federal | 0
H10-04-002 | 10 | 5933166 | 4 | Alameda County | Alameda County | MTC | MTC | Various unsignalized intersections in the unincorporated Alameda County: Meekland Ave. at Sunset Blvd., Hacienda Ave. at Ricardo Ave., Grove Way at Dolores St. | Install Rectangular Rapid Flash Beacons (RRFBs) and various crosswalk enhancements to unsignalized intersections to increase safety for pedestrians. | 529700 | 498980 | 2021-08-27 | 0 | 2026-03-27 | 0 | 498980 | Authorized | Authorized | No | CON | State | 0
H10-04-003 | 10 | 5933165 | 4 | Alameda County | Alameda County | MTC | MTC | Various locations along Crow Canyon Road in unincorporated Alameda County. | Upgrade existing guardrails at locations with damage and height below accepted tolerance. | 994600 | 994600 | 2021-05-28 | 0 | 2023-07-17 | 2025-07-08 | 994600 | Authorized | Authorized | No | Closed | State | 0
H10-04-004 | 10 | 5933167 | 4 | Alameda County | Alameda County | MTC | MTC | Three unsignalized intersections with existing marked crosswalks in suburban areas of Alameda County: Redwood Road and Modesto Street, Lake Chabot Road and Congress Way, and Lake Chabot Road and Keith Avenue. | Installation of Pedestrian Hybrid Beacons and raised medians; installation of accompanying signage, ADA Ramps, and pavement striping. | 821000 | 821000 | 2021-08-27 | 0 | 2026-02-17 | 0 | 821000 | Authorized | Authorized | No | CON | State | 0
H8-04-001&002 | 8 | 5933141 | 4 | Alameda County | Alameda County | MTC | MTC | Redwood Road between Marciel Rd and Camino Alta Mira in Castro Valley, and Palomares Rd between Palo Verde Rd and Highway 84. | Pave existing shoulders and provide law enforcement pullout areas to control vehicles speeding along the corridors. | 389202.89 | 247674.92 | 2017-08-02 | 0 | 2020-05-05 | 2022-06-28 | 247674.92 | Authorized | Authorized | No | Closed | Federal | 0
H8-04-003 | 8 | 5933142 | 4 | Alameda County | Alameda County | MTC | MTC | Fairmont Drive between Lake Chabot Road and 2700 Fairmont Drive in Castro Valley. | Install guardrails. | 1152793.92 | 815311.87 | 2017-07-28 | 0 | 2019-12-20 | 2022-05-06 | 815311.87 | Authorized | Authorized | No | Closed | Federal | 0
H9-04-001 | 9 | 5933152 | 4 | Alameda County | Alameda County | MTC | MTC | Various unsignalized intersections in unincorporated Alameda County. | Install/upgrade larger or additional stop signs or other warning/regulatory signs; add intersection lighting; add pedestrian crossing with enhanced safety features. | 1942400 | 1942400 | 2019-10-30 | 0 | 2023-06-28 | 0 | 1942400 | Authorized | Authorized | No | CON | Federal | 2
H9-04-002 | 9 | 5933153 | 4 | Alameda County | Alameda County | MTC | MTC | Various signalized intersections throughout Alameda County; urban and suburban contexts. | Install mast arms; install signal hardware improvements such as additional signal heads, reflective backplates; install leading pedestrian interval. | 2493900 | 2493900 | 2019-10-31 | 0 | 2023-07-06 | 0 | 2437980 | Authorized | Authorized | No | CON | Federal | 2
H9-04-003 | 9 | 5933154 | 4 | Alameda County | Alameda County | MTC | MTC | Crow Canyon Road, Palomares Road, North Vasco Road, and Altamont Pass Road in unincorporated Alameda County. | Widen paved shoulders, construct edgeline rumble strips, and install chevron signs and delineators. | 1812700 | 1631430 | 2019-11-19 | 0 | 2023-06-28 | 0 | 1631430 | Authorized | Authorized | No | CON | Federal | 0
H9-04-004 | 9 | 5933155 | 4 | Alameda County | Alameda County | MTC | MTC | Thirteen (13) locations along Tesla Road between Eagles Run Road and McLaughlin Road. | Upgrade guardrail. | 990238.88 | 471300 | 2019-10-31 | 0 | 2022-02-24 | 2024-11-14 | 471300 | Authorized | Authorized | No | Closed | Federal | 1
HRRR1-04-031 | 1 | 5933089 | 4 | Alameda County | Alameda County | MTC | MTC | Patterson Pass Rd. at PM 6.4 in unincorporated Alameda County | Widen or Improve Shoulder | 1929421.03 | 818099.95 | 2008-12-19 | 0 | 2015-09-15 | 2017-11-01 | 818099.95 | Authorized | Authorized | No | Closed | Federal | 0
HSIP2-04-024 | 2 | 5933096 | 4 | Alameda County | Alameda County | MTC | MTC | Castro Valley Blvd And Wisteria St. | Install Traffic Signal And Provide Frontage Improvements | 1278403.32 | 698385.81 | 2009-08-14 | 2011-02-15 | 2012-09-19 | 2015-10-28 | 698385.81 | Authorized | Authorized | No | Closed | Federal | 0
HSIP2-04-027 | 2 | 5933097 | 4 | Alameda County | Alameda County | MTC | MTC | Foothill Road Between Castlewood And Sunole Area And On Miner Rd. Between Del Valle Rd And The Vicinity Of Milepost 10 In Unincorporated County Line. | Remove Permanent Obstacle Along Shoulder | 555306.98 | 478065.25 | 2009-02-23 | 0 | 2015-05-12 | 2018-04-27 | 478065.25 | Authorized | Authorized | No | Closed | Federal | 0
HSIP6-04-001 | 6 | 5933129 | 4 | Alameda County | Alameda County | MTC | MTC | Various locations throughout unincorporated Alameda County | Construct sidewalks, curb ramps, curb extensions, curb and gutter; Restriping; Install flashing beacons | 1873347.58 | 1023333 | 2014-12-04 | 0 | 2016-01-11 | 2019-11-20 | 1023333 | Authorized | Authorized | No | Closed | Federal | 0
H11-04-002 | 11 | 5470017 | 4 | American Canyon | Napa County | MTC | MTC | On American Canyon Road approximately 400 feet east of Via Firenze. | Upgrade/replace existing guardrail systems. | 280500 | 252450 | 2024-01-24 | 0 | 2026-01-20 | 0 | 252450 | Authorized | Authorized | No | CON | State | 0
H11-04-003 | 11 | 5038028 | 4 | Antioch | Contra Costa County | MTC | MTC | 69 Signalized Intersections along Multiple Roadway Segments. | Improve signal hardware: lenses, back-plates with retroreflective borders, mounting, size, and number; Install pedestrian countdown signal heads; and Install advance stop bar before crosswalk (Bicycle Box). | 2800600 | 2520540 | 2024-08-08 | 0 | 0 | 0 | 369000 | Authorized | Due by 8/31/2026 | No | PE | Federal | 2
H11-04-004 | 11 | 5038029 | 4 | Antioch | Contra Costa County | MTC | MTC | Delta de Anza Trail Xing at James Donlan Boulevard; Delta de Anza Trail Xing at Lone Tree Way; and Canada Valley Trail Xing at Hillcrest Avenue. | Install Hawk Signals at Trail Crossings to enhance Pedestrian and Bicycle Safety. | 920000 | 828000 | 2024-07-01 | 0 | 0 | 0 | 63000 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE | State | 0
HSIP3-04-004 | 3 | 5261007 | 4 | Atherton | San Mateo County | MTC | MTC | Intersection Of Valparaiso Ave. And Hoover St. | Install In-Pavement Crosswalk Lights, Traffic Signs, Pavement Markings, And Striping | 70434 | 30600 | 2010-11-18 | 0 | 2011-06-30 | 2012-09-10 | 30600 | Authorized | Authorized | No | Closed | Federal | 0
H10-04-005 | 10 | 5003036 | 4 | Benicia | Solano County | MTC | MTC | Kearney Street at Rose Drive, Kearney Street at Mid-Block Crossing, Hastings Drive at Southhampton Road and Military West at W 3rd Street. | Install high-visibility crosswalks, advance yield limit lines, signage, RRFB systems, ADA compliant ramps, and bulb-outs. | 249900 | 249900 | 2022-12-27 | 0 | 2025-04-16 | 0 | 249900 | Authorized | Authorized | No | CON | State | 0
H11-04-005 | 11 | 5003037 | 4 | Benicia | Solano County | MTC | MTC | The intersection of Rose Drive and Panorama Drive. | Improve pedestrian crossing with the installation of bulb-outs (curb extensions) and high visibility crosswalks. Other safety measures include installing ADA curb ramps. | 266300 | 239670 | 2023-06-02 | 0 | 2024-03-04 | 2025-11-04 | 239670 | Authorized | Authorized | No | Closed | State | 0
H9-04-005 | 9 | 5003032 | 4 | Benicia | Solano County | MTC | MTC | Various locations throughout the City | Upgrade existing guardrails and end treatments at 21 locations in the City | 913899.55 | 913899.55 | 2019-09-06 | 0 | 2022-09-20 | 2025-05-12 | 913899.55 | Authorized | Authorized | No | Closed | Federal | 0
H9-04-006 | 9 | 5003033 | 4 | Benicia | Solano County | MTC | MTC | The intersections of West 5th St. with Military West and Hasting Dr. with London Dr. | Enhance pedestrian crossings by installing ADA curb ramp, RRFB system, median island, and sidewalk, and other relevant elements. | 396150.16 | 250000 | 2019-09-06 | 0 | 2022-09-20 | 2024-06-11 | 250000 | Authorized | Authorized | No | Closed | Federal | 0
HSIP7-04-001 | 7 | 5003030 | 4 | Benicia | Solano County | MTC | MTC | The intersection of East 5th Street and Vecino Street, and along East 5th Street between I-780 and Vecino Street | Construct a bulb-out and crosswalk with flashing beacons on East 5th Street @ Vecino Street and extend the eastern sidewalk of East 5th Street to I-780 along with adding two new roadway lights | 783084.58 | 545642.55 | 2017-01-24 | 0 | 2019-02-27 | 2023-01-23 | 545642.55 | Authorized | Authorized | No | Closed | Federal
HSIP7-04-002 | 7 | 5003029 | 4 | Benicia | Solano County | MTC | MTC | The intersection of Military West, West 7th Street, Carolina Drive, and Buena Vista | Replace traffic signal to add protected lefts on Military West; upgrade five (5) pedestrian crosswalks, and upgrade controller cabinet | 465558.04 | 346929.68 | 2016-11-29 | 0 | 2019-02-20 | 2023-03-27 | 346929.68 | Authorized | Authorized | No | Closed | Federal
H10-04-006 | 10 | 5057054 | 4 | Berkeley | Alameda County | MTC | MTC | Six intersections along Sacramento Street: Oregon Street, Julia Street, Tyler Street, Prince Street, Woolsey Street and Fairview Street. | Install RRFBs, warning signing, and raised median extensions at three intersections. Install advanced yield lines and warning signing at three other intersections. | 339800 | 250000 | 0 | 0 | 2023-12-21 | 0 | 250000 | No PE | Authorized | No | CON | State | 0
H9-04-007 | 9 | 5376015 | 4 | Brisbane | San Mateo County | MTC | MTC | Guadalupe Canyon Pkwy between Bayshore Blvd and western city limit. | Install edgeline rumble stripes, bike lane markings, and signage; restripe lane and median markings to widen median; install centerline rumble stripes; upgrade existing flashing beacons with solar-powered LED flashing warning signs. | 164491.33 | 108234 | 0 | 0 | 2020-03-26 | 2021-02-22 | 108234 | No PE | Authorized | No | Closed | Federal | 0
HSIP1-04-004 | 1 | 5306014 | 4 | Campbell | Santa Clara County | MTC | MTC | Intersection Of Hamilton Ave And Phoenix Dr. | Install Traffic Signal With Interconnect. | 283786.24 | 255407.6 | 2007-12-07 | 0 | 2008-09-12 | 2012-03-27 | 255407.6 | Authorized | Authorized | No | Closed | Federal | 0
HSIP2-04-016 | 2 | 5306015 | 4 | Campbell | Santa Clara County | MTC | MTC | Various Locations | Install Count Down Pedestrian Heads | 10894.46 | 8788.81 | 0 | 0 | 2009-08-25 | 2011-09-06 | 8788.81 | No PE | Authorized | No | Closed | Federal | 0
HSIP4-04-001 | 4 | 5306023 | 4 | Campbell | Santa Clara County | MTC | MTC | Apricot Ave.; Campbell Ave.; Hacienda Ave.; Harriet Ave.; Hazel Ave.; Leigh Ave.; San Tomas Aquino Rd.; Sunnyoaks Ave.; Union Ave.; Westmont Ave.; Winchester Blvd. | Install speed feedback signs | 192025.94 | 124576.55 | 2012-01-13 | 0 | 2012-04-12 | 2014-06-27 | 124576.55 | Authorized | Authorized | No | Closed | Federal | 0
HSIP6-04-002 | 6 | 5306027 | 4 | Campbell | Santa Clara County | MTC | MTC | Harriet Avenue between Westmont Avenue and north city limits | Install pedestrian hybrid beacon; construct curb, gutter, sidewalk, and curb ramps; widen sidewalk; install traffic signs, stripes, and pavement markings | 790461.19 | 504008.33 | 2014-07-11 | 0 | 2019-03-25 | 2021-06-24 | 504008.33 | Authorized | Authorized | No | Closed | Federal | 0
H12-04-001 | 12 | 0 | 4 | Clayton | Contra Costa County | MTC | MTC | Thirteen (13) signalized intersections. | Upgrade signal heads with retroreflective backplates. | 50700 | 45630 | 0 | 0 | 0 | 0 | 0 | No PE | Due by 3/31/2028 | No | Not Started | State | 0
H10-04-007 | 10 | 5135060 | 4 | Concord | Contra Costa County | MTC | MTC | Various locations throughout the City of Concord. | Improve traffic signal hardware, install pedestrian countdown signal heads, and modify phasing to provide a Lead Pedestrian Interval (LPI). | 2360000 | 2171200 | 2021-05-11 | 0 | 2022-07-01 | 0 | 2171200 | Authorized | Authorized | No | CON | State | 0
H10-04-008 | 10 | 5135061 | 4 | Concord | Contra Costa County | MTC | MTC | Citywide at 8 intersections | Modify 8 intersections with permissive left-turn phasing to provide protected left-turn phasing | 1254800 | 1254800 | 2021-05-12 | 0 | 2022-10-03 | 2024-10-08 | 1254800 | Authorized | Authorized | No | Closed | State | 0
H10-04-009 | 10 | 5135062 | 4 | Concord | Contra Costa County | MTC | MTC | Concord Boulevard at West Street, Salvio Street at Date Street, Ronald Way at Holbrook Elementary School Entrance and E. Olivera Road at Trail Crossing. | Install high-visibility crosswalks, concrete bulb-outs, advance warning signs, and ADA ramps. | 246600 | 246600 | 2021-05-12 | 0 | 2022-04-19 | 2023-07-31 | 246600 | Authorized | Authorized | No | Closed | State | 0
H11-04-006 | 11 | 5135064 | 4 | Concord | Contra Costa County | MTC | MTC | Various locations throughout the City of Concord. | Install new street lighting, upgrade existing street and intersection lighting, install pedestrian countdown signal heads, modify phasing to provide a Leading Pedestrian Interval (LPI), and install three new RRFBs and two HAWK Signals. | 8233300 | 7409970 | 2024-01-09 | 0 | 0 | 0 | 1240290 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE | Federal | 2
H11-04-007 | 11 | 5135065 | 4 | Concord | Contra Costa County | MTC | MTC | 9 intersection locations throughout the City of Concord. | Upgrade existing uncontrolled crossing locations to enhance pedestrian safety with flashing beacon systems. | 374672 | 300000 | 0 | 0 | 2024-05-22 | 0 | 249984 | No PE | Authorized | No | CON | State | 0
H11-04-008 | 11 | 5135065 | 4 | Concord | Contra Costa County | MTC | MTC | Various existing bike facilities throughout the City. | Install bike lane buffer delineators to provide physical separation between bicycles and vehicles and install bike boxes at intersection approaches. | 277200 | 249480 | 0 | 0 | 2024-05-22 | 0 | 249984 | No PE | Authorized | No | CON | State | 0
H12-04-002 | 12 | 5135069 | 4 | Concord | Contra Costa County | MTC | MTC | Various locations. | Install / upgrade signs with new fluorescent sheeting. | 7782500 | 7004250 | 2026-02-04 | 0 | 0 | 0 | 720000 | Authorized | Due by 3/31/2028 | No | PE | Federal | 0
H12-04-003 | 12 | 5135072 | 4 | Concord | Contra Costa County | MTC | MTC | Olivera Road & Grant Street-Northwood Drive. | Modify existing traffic signal system to eliminate permissive left-turn operations and improve intersection safety lighting. | 932500 | 839250 | 2026-01-12 | 0 | 0 | 0 | 45000 | Authorized | Due by 3/31/2028 | No | PE | State | 0
H12-04-004 | 12 | 5135071 | 4 | Concord | Contra Costa County | MTC | MTC | Various locations. | Install traffic signal backplates with yellow retroreflective border, install pedestrian countdown signal heads, accessible push button and associated ADA curb ramp upgrades and implement leading pedestrian interval (LPI). | 1117000 | 1005300 | 2025-12-15 | 0 | 0 | 0 | 94500 | Authorized | Due by 3/31/2028 | No | PE | State | 0
H9-04-008 | 9 | 5135056 | 4 | Concord | Contra Costa County | MTC | MTC | Various locations. | Improve signal hardware (lenses, backplates, mountings, size, number), upgrade cabinet equipment, controllers and modify phasing to provide a Lead Pedestrian Interval (LPI). | 3399596.82 | 2386976 | 2019-10-17 | 0 | 2022-02-10 | 2024-11-25 | 2386976 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-04-002 | 5 | 5135043 | 4 | Concord | Contra Costa County | MTC | MTC | Various locations in the City of Concord | Upgrade existing traffic signals, install new traffic signals, and related improvements including ADA upgrades | 2031355.21 | 1818628.59 | 2014-05-05 | 0 | 2015-12-15 | 2018-10-15 | 1818628.59 | Authorized | Authorized | No | Closed | Federal | 0
H10-04-010 | 10 | 5928173 | 4 | Contra Costa County | Contra Costa County | MTC | MTC | Various locations on arterial and major collector roadways in the Briones area of unincorporated Contra Costa County. | Replace sub-standard MBGR guardrails with MGS guardrails and end treatments on arterial and major collector roadways. Upgrade includes approximately 43 guardrails with a length of over 12,000 linear feet. | 1687800 | 992082 | 0 | 0 | 2024-02-28 | 2025-07-21 | 992082 | No PE | Authorized | No | Closed | State | 0
H10-04-011 | 10 | 5928161 | 4 | Contra Costa County | Contra Costa County | MTC | MTC | On Franklin Canyon Road in unincorporated Contra Costa County between Cummings Skyway and Dutra Road. | Install centerline rumble strips. | 562400 | 562400 | 2021-06-01 | 0 | 2023-05-04 | 0 | 562400 | Authorized | Authorized | No | CON | State | 0
H10-04-012 | 10 | 5928162 | 4 | Contra Costa County | Contra Costa County | MTC | MTC | San Pablo Dam Rd from El Portal Dr to Castro Ranch Rd; Bailey Rd from Willow Pass Rd to Canal Rd/ Via Delta De Anza Trail. | Improve safety by improving traffic signal hardware, with enlarged signal heads, video detection, advance dilemma zone detection, and install pedestrian countdown signal heads at 11 signalized intersections. | 1100100 | 1100100 | 2021-05-24 | 0 | 2023-04-25 | 2025-07-08 | 1100100 | Authorized | Authorized | No | Closed | State | 0
H11-04-009 | 11 | 5928189 | 4 | Contra Costa County | Contra Costa County | MTC | MTC | Various locations on arterials, collectors, and local roads throughout Contra Costa County. | Replace sub-standard MBGR guardrails with Caltrans standard MGS guardrails and end treatments. | 1493700 | 999990 | 0 | 0 | 2026-02-27 | 0 | 999990 | No PE | Authorized | No | CON | State | 0
H11-04-010 | 11 | 0 | 4 | Contra Costa County | Contra Costa County | MTC | MTC | The intersection of Appian Way and Fran Way in unincorporated El Sobrante. | Install Rectangular Rapid Flashing Beacons (RRFBs), bulb-outs and a median refuge island. | 510800 | 249840 | 0 | 0 | 0 | 0 | 0 | No PE | Due by 3/31/2027 | No | Not Started | State | 0
H11-04-011 | 11 | 5928172 | 4 | Contra Costa County | Contra Costa County | MTC | MTC | Walnut Boulevard between Marsh Creek Road and Vasco Road in unincorporated Brentwood. | Install bike lanes by widening and restriping the roadway and install a centerline rumble strip. | 1150000 | 249415 | 0 | 0 | 2024-03-04 | 2025-01-06 | 249415 | No PE | Authorized | No | Closed | State | 0
H11-04-012 | 11 | 5928167 | 4 | Contra Costa County | Contra Costa County | MTC | MTC | Byron Highway from Clifton Court Road to Bruns Road. | Add lighting, install dynamic/variable speed warning signs, and install edgeline rumble strips/stripes. | 1462800 | 1316520 | 2023-05-01 | 0 | 0 | 0 | 207000 | Authorized | Due by 3/31/2028 | No | PE | State | 0
H11-04-013 | 11 | 5928168 | 4 | Contra Costa County | Contra Costa County | MTC | MTC | Vasco Road from Walnut Boulevard to the Frisk Creek Bridge. | Install no-passing zone and centerline rumble strip and improve signal hardware at intersections. | 1232300 | 1109070 | 2023-05-04 | 0 | 2025-05-22 | 0 | 1109070 | Authorized | Authorized | No | CON | State | 0
H11-04-014 | 11 | 5928171 | 4 | Contra Costa County | Contra Costa County | MTC | MTC | Deer Valley Road between Deer Hill Lane and Marsh Creek Road in the unincorporated areas outside the cities of Antioch and Brentwood, in east Contra Costa County. | Install dynamic/variable speed feedback signs, guardrails, and curve shoulder widening. | 1250900 | 1125810 | 2023-07-26 | 2025-07-21 | 0 | 0 | 247500 | Authorized | Due by 3/31/2027 | No | ROW | State | 0
H12-04-005 | 12 | 0 | 4 | Contra Costa County | Contra Costa County | MTC | MTC | Various locations on arterials, collectors, and local roads within the Bay Point, Concord, and Martinez areas of unincorporated Contra Costa County. | Replace sub-standard Metal Beam Guardrails (MBGR) with Midwest Guardrail System (MGS) and end treatments. | 1787400 | 1000000 | 0 | 0 | 0 | 0 | 0 | No PE | Due by 3/31/2028 | No | Not Started | State | 0
H12-04-006 | 12 | 0 | 4 | Contra Costa County | Contra Costa County | MTC | MTC | Treat Boulevard in the City of Walnut Creek and unincorporated Contra Costa Centre area, from N Main St to Jones Rd. | Install Class IV bikeways between N Main St and Jones Rd, install a shared use path between Buskirk Ave and Oak Rd, eliminate free right turns, and modify traffic signals and pedestrian refuge islands. | 5106300 | 350000 | 0 | 0 | 0 | 0 | 0 | No PE | Due by 3/31/2028 | No | Not Started | State | 0
H12-04-007 | 12 | 0 | 4 | Contra Costa County | Contra Costa County | MTC | MTC | The intersections of Danville Blvd & South Ave in Alamo and Center Ave & Deodar Dr in Pacheco, unincorporated Contra Costa County. | Install pedestrian crossing improvements at two intersections such as rectangular rapid flashing beacons (RRFBs), curb ramps, continental crosswalk striping, and other safety features. | 629400 | 350000 | 0 | 0 | 0 | 0 | 0 | No PE | Due by 3/31/2028 | No | Not Started | State | 0
H12-04-008 | 12 | 5928181 | 4 | Contra Costa County | Contra Costa County | MTC | MTC | Camino Tassajara from Finley Road to Windemere Parkway. | Install centerline rumble strips, install segment and intersection lighting, and upgrade guardrails. | 1783100 | 1604790 | 2025-07-24 | 0 | 0 | 0 | 270000 | Authorized | Due by 3/31/2028 | No | PE | Federal | 0
H12-04-009 | 12 | 5928182 | 4 | Contra Costa County | Contra Costa County | MTC | MTC | At various locations along curves. | Install speed feedback signs and curve warning signs. | 2402300 | 2162070 | 2025-06-27 | 0 | 0 | 0 | 386100 | Authorized | Due by 3/31/2028 | No | PE | Federal | 0
H8-04-004 | 8 | 5928144 | 4 | Contra Costa County | Contra Costa County | MTC | MTC | Intersections of Olympic Boulevard at Bridgefield Road and Walden Road at Westcliffe Lane (unincorporated Walnut Creek area). | Construct ADA curb ramp, curb, gutter, and sidewalk; Install Rectangular Rapid Flashing Beacons (RRFBs). | 421727.79 | 213102.82 | 2017-07-28 | 0 | 2019-12-20 | 2022-03-04 | 213102.82 | Authorized | Authorized | No | Closed | Federal | 0
H8-04-005 | 8 | 5928145 | 4 | Contra Costa County | Contra Costa County | MTC | MTC | Marsh Creek Road from the City of Clayton limits to Camino Diablo, Vasco Road from Walnut Boulevard to the Alameda County line, and San Pablo Dam Road from City of Richmond limits to Bear Creek Road. | Upgrade existing guardrails. | 1455982.15 | 1293200 | 2017-08-02 | 0 | 2019-11-19 | 2021-09-02 | 1293200 | Authorized | Authorized | No | Closed | Federal | 0
H8-04-006 | 8 | 5928140 | 4 | Contra Costa County | Contra Costa County | MTC | MTC | Danville Boulevard between Stone Valley Road and Jackson Way in unincorporated Alamo of Contra Costa County. | Construct a roundabout at the intersection of Danville Boulevard and Orchard Court in addition to street improvements, such as sidewalk improvements and curb extensions. | 2978000 | 2718000 | 2017-07-28 | 0 | 2022-04-25 | 0 | 2718000 | Authorized | Authorized | No | CON | Federal | 0
H8-04-007 | 8 | 5928142 | 4 | Contra Costa County | Contra Costa County | MTC | MTC | San Pablo Dam Road between the Richmond City Limits and Bear Creek Road/Wildcat Canyon Road. | Install centerline rumble strips along 4.6 miles of two-lane, winding roadway; upgrade regulatory and warning signs; reconstruct median island curbs; install lane channelizers along the centerline. | 1696837.86 | 760076.58 | 2017-08-02 | 0 | 2019-12-12 | 2022-06-28 | 760076.58 | Authorized | Authorized | No | Closed | Federal | 0
H8-04-008 | 8 | 5928143 | 4 | Contra Costa County | Contra Costa County | MTC | MTC | Byron Highway approx. 350 feet south of Byer Road to Hoffman Lane, adjacent to Excelsior Middle School in unincorporated Byron. | Install southbound left-turn lane on Byron Highway on to Byer Road; Construct a two-way left turn lane to improve access at Excelsior Middle School; and widen roadway to provide paved shoulders. | 1634701.6 | 616730 | 2017-08-02 | 0 | 2021-11-10 | 2024-06-27 | 616730 | Authorized | Authorized | No | Closed | Federal | 0
H9-04-009 | 9 | 5928156 | 4 | Contra Costa County | Contra Costa County | MTC | MTC | Kirker Pass Road between the city limits of Concord and Pittsburg. | Install intersection lighting at two intersections, install protective guardrail along the top of embankment, and install delineators/reflectors along the K-rail median. | 942503.33 | 932887.34 | 2019-09-06 | 0 | 2021-04-01 | 2023-11-09 | 932887.34 | Authorized | Authorized | No | Closed | Federal | 0
H9-04-010 | 9 | 5928157 | 4 | Contra Costa County | Contra Costa County | MTC | MTC | Various locations on arterials and major collector roadways in the Crockett area. | Upgrade sub-standard MBGR guardrails to Caltrans standard MGS guardrails and end treatments on arterials and major collector roadways (approximately 41 guardrails with a length of over 12,000 linear feet including end treatments). | 1182997.47 | 999963 | 0 | 0 | 2021-10-28 | 2023-03-24 | 999963 | No PE | Authorized | No | Closed | Federal | 0
HRRR1-04-025 | 1 | 5928083 | 4 | Contra Costa County | Contra Costa County | MTC | MTC | Alhambra Valley Rd.: 4700' to 6350' East of Castro Ranch Rd. | Widen or Improve Shoulder | 1716219.85 | 900000 | 2008-01-03 | 0 | 2011-03-23 | 2012-10-25 | 900000 | Authorized | Authorized | No | Closed | Federal | 0
HRRR1-04-026 | 1 | 5928084 | 4 | Contra Costa County | Contra Costa County | MTC | MTC | Dear Valley Rd. from Marsh Creek Rd. to Briones Valley Rd. in East Contra Costa County | Widen or Improve Shoulder | 1638655.44 | 888164 | 2008-03-02 | 0 | 2014-03-18 | 2017-10-18 | 888164 | Authorized | Authorized | No | Closed | Federal | 0
HRRR1-04-027 | 1 | 5928085 | 4 | Contra Costa County | Contra Costa County | MTC | MTC | Marsh Creek Rd. - West of Round Valley Park to Lydia Ln. | Widen or Improve Shoulder | 1920961.49 | 900000 | 2008-02-24 | 0 | 2012-06-13 | 2014-06-20 | 900000 | Authorized | Authorized | No | Closed | Federal | 0
HRRR2-04-028 | 2 | 5928095 | 4 | Contra Costa County | Contra Costa County | MTC | MTC | Marsh Creek Road from 2.0 to 2.5 miles west of Deer Valley Road | Realign and widen roadway and shoulders; relocate utilities; improve highway signage and drainage | 2980535.16 | 1520000 | 2009-07-16 | 0 | 2015-04-01 | 2018-01-16 | 1520000 | Authorized | Authorized | No | Closed | Federal | 0
HRRR2-04-029 | 2 | 5928096 | 4 | Contra Costa County | Contra Costa County | MTC | MTC | On Marsh Creek Road from 1 mile east of Russelmann Park Road to 3/4 mile west of Morgan Territory Road | Widen roadway and shoulders; install guardrail; eliminate roadway obstacles; install signs, stripes and pavement markers | 1508108.46 | 816066.42 | 2012-06-22 | 0 | 2014-03-05 | 2017-10-13 | 816066.42 | Authorized | Authorized | No | Closed | Federal | 0
HRRR2-04-030 | 2 | 5928098 | 4 | Contra Costa County | Contra Costa County | MTC | MTC | Alhambra Valley Road from Bear Creek Road to approximately 2200 feet east | Realign and widen roadway | 2489509.75 | 1710000 | 2009-09-01 | 0 | 2014-11-21 | 2017-02-22 | 1710000 | Authorized | Authorized | No | Closed | Federal | 0
HSIP2-04-023 | 2 | 5928089 | 4 | Contra Costa County | Contra Costa County | MTC | MTC | Deer Valley Road, 1/4 Mile To 1/2 Mile South Of Chadbourne Rd. | Realign Horizontal Curve; Widen Travel Lanes, Shoulders, And Backing; Improve Signing And Striping | 1004330.26 | 532039.2 | 2009-02-09 | 0 | 2012-04-24 | 2014-02-25 | 532039.2 | Authorized | Authorized | No | Closed | Federal | 0
HSIP3-04-010 | 3 | 5928105 | 4 | Contra Costa County | Contra Costa County | MTC | MTC | Camino Tassajara From Approximately 2,000' East Of Blackhawk Dr. To 100' South Of Finley Rd. | Widen Travel Lanes; Add Paved Shoulders And Shoulder Backing; Install Signs And Stripes | 1676171.27 | 867158.32 | 2010-12-23 | 0 | 2014-02-20 | 2016-10-20 | 867158.32 | Authorized | Authorized | No | Closed | Federal | 0
HSIP4-04-008 | 4 | 5928110 | 4 | Contra Costa County | Contra Costa County | MTC | MTC | Camino Tassajara Rd., from approximately 1 mile S of Highland Rd. to 0.2 miles N of Windemere Pkwy. | Widen roadway and pave shoulders; install signs, striping, and curve warning flashers; relocate roadside obstacles; flatten side slopes | 1466825.86 | 889754 | 2011-12-28 | 0 | 2014-07-11 | 2018-01-18 | 889754 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-04-004 | 5 | 5928117 | 4 | Contra Costa County | Contra Costa County | MTC | MTC | Byron Hwy./Camino Diablo Rd. | Install traffic signal and turning lanes; upgrade railroad crossings and shoulders | 2304813.72 | 900000 | 0 | 0 | 2016-11-10 | 2019-06-12 | 900000 | No PE | Authorized | No | Closed | Federal | 0
HSIP5-04-005 | 5 | 5928118 | 4 | Contra Costa County | Contra Costa County | MTC | MTC | Alhambra Valley Rd. between Rancho La Boca Rd. and Ferndale Rd. | Remove guardrail, construct paved shoulders, flatten adjacent slope, install traffic calming measures, remove roadside obstacles, and install striping, pavement markings and warning signs. | 1242263.87 | 600000 | 2014-04-27 | 0 | 2016-11-01 | 2019-01-22 | 600000 | Authorized | Authorized | No | Closed | Federal | 0
HSIP7-04-004 | 7 | 5928132 | 4 | Contra Costa County | Contra Costa County | MTC | MTC | Various roadways located in the unincorporated Bay Point area | Bay Point Sign Upgrade Project: Replacement of existing regulatory and warning signs | 282025.48 | 261751.8 | 2016-11-01 | 0 | 2017-12-27 | 2019-07-19 | 261751.8 | Authorized | Authorized | No | Closed | Federal
HSIP7-04-005 | 7 | 5928133 | 4 | Contra Costa County | Contra Costa County | MTC | MTC | On San Pablo Dam Road between Appian Way and Clark Road, within the unincorporated El Sobrante area. | Construct curb, gutter, and sidewalk | 916783.4 | 606001.32 | 2016-10-31 | 0 | 2019-03-07 | 2021-04-15 | 606001.32 | Authorized | Authorized | No | Closed | Federal
HSIP7-04-006 | 7 | 5928131 | 4 | Contra Costa County | Contra Costa County | MTC | MTC | Byron Highway between Byron Hot Springs Road and Contra Costa/Alameda County Line, within the unincorporated Byron area. | Restripe centerline with double yellow no passing lines, install centerline rumble strips, and upgrade signs | 1878875.74 | 515000 | 2016-11-01 | 0 | 2019-01-29 | 2021-04-01 | 515000 | Authorized | Authorized | No | Closed | Federal
HSIP7-04-007 | 7 | 5928130 | 4 | Contra Costa County | Contra Costa County | MTC | MTC | Located on Marsh Creek Road between the city limits of Clayton and Brentwood. The project length is approximately 14 miles. | Install centerline rumble strips/stripes; Add lighting at Deer Valley Road and Marsh Creek Road intersection | 1078049.35 | 1049263.68 | 2016-11-01 | 0 | 2019-01-29 | 2021-04-21 | 1049263.68 | Authorized | Authorized | No | Closed | Federal
H11-04-015 | 11 | 5318034 | 4 | Cupertino | Santa Clara County | MTC | MTC | Sections of 17 corridors: De Anza Blvd; Homestead Rd; Bollinger Rd; Wolfe Rd; McClellan Rd; Bubb Rd; Mariani Ave; Tantau Ave; Blaney Ave; Rainbow Dr; Miller Ave; Stelling Rd; Valley Green Dr; Calvert Dr; and Mary Ave. | Implement countermeasures including dynamic/variable speed warning signs at the curves along the corridor and improving pavement friction (HFST). | 3561800 | 3205620 | 2023-05-04 | 0 | 0 | 0 | 360000 | Authorized | Due in no more than 4 months | No | PE | State | 0
H9-04-011 | 9 | 5318030 | 4 | Cupertino | Santa Clara County | MTC | MTC | The intersection of Homestead Rd and N De Anza Blvd. | Upgrade existing pedestal-mounted signal to signal on mast arm. | 316909.58 | 210452.06 | 2019-10-17 | 0 | 2021-11-26 | 2023-06-19 | 210452.06 | Authorized | Authorized | No | Closed | Federal | 0
H10-04-013 | 10 | 5196043 | 4 | Daly City | San Mateo County | MTC | MTC | The intersection of John Daly Boulevard and Skyline Boulevard in Daly City. | Upgrade intersection signal hardware and pedestrian countdown signal heads, convert traffic signal pole to pole with a mast arm, install raised pavement markers and striping and upgrade ADA curb ramps. | 380200 | 342180 | 2021-06-11 | 0 | 0 | 0 | 48600 | Authorized | Past due (due 2/28/2025) | Yes (CON) | PE | State | 0
HSIP3-04-008 | 3 | 5196034 | 4 | Daly City | San Mateo County | MTC | MTC | Gellert Blvd. Between Hickey Blvd. And King Dr. | Install Pavement Markings And Directional Signage For Class Ii Bike Lanes; Construct Pedestrian Refuge At Serra Vista Ave. | 86429.89 | 61885.14 | 0 | 0 | 2011-04-04 | 2012-11-07 | 61885.14 | No PE | Authorized | No | Closed | Federal | 0
HSIP4-04-017 | 4 | 5196037 | 4 | Daly City | San Mateo County | MTC | MTC | Hickey Blvd./Callan Blvd. | Install protected left-turn phasing; upgrade traffic signals; construct curb ramps | 228735.98 | 198589.64 | 2012-06-01 | 0 | 2012-12-13 | 2014-11-26 | 198589.64 | Authorized | Authorized | No | Closed | Federal | 0
H10-04-014 | 10 | 5434028 | 4 | Danville | Contra Costa County | MTC | MTC | Existing Class I path crossings along Iron Horse Regional Trail at Linda Mesa Avenue, Love Lane and Del Amigo Road (all local roads); and existing mid-block crossing on Stone Valley Road (minor arterial) at Monte Vista High School entry. | Install solar-powered Rectangular Rapid Flashing Beacon (RRFB) systems, LED crosswalk warning signage and illumination systems at four uncontrolled crosswalk locations. | 240000 | 240000 | 0 | 0 | 2024-11-07 | 0 | 240000 | No PE | Authorized | No | CON | State | 0
H11-04-017 | 11 | 5434034 | 4 | Danville | Contra Costa County | MTC | MTC | 20 signalized intersections along the arterial roadways of Sycamore Valley Road, Camino Tassjara and Diablo Road. | Improve signal hardware, install advance stop bar, and modify signal phasing to implement a leading pedestrian interval. | 590400 | 531360 | 0 | 0 | 2026-03-19 | 0 | 531360 | No PE | Authorized | No | CON | State | 0
H10-04-015 | 10 | 5056021 | 4 | Dixon | Solano County | MTC | MTC | E Mayes St & 4th St, E. A St & N. 4th St., N. 4th St & E. B St. and S. 7th St & E. A St. | Install high-visibility crosswalks, striping, signage, RRFB system, ADA ramps, and bulb-outs. | 250000 | 250000 | 2021-09-29 | 0 | 2023-09-12 | 0 | 250000 | Authorized | Authorized | No | CON | State | 0
H11-04-018 | 11 | 5056024 | 4 | Dixon | Solano County | MTC | MTC | Pedestrian crossing locations at 5th St & E A St and E A St & the Good Neighbor School. | Install RRFBs and other standard crossing treatments including signing, striping and curb enhancements. | 167800 | 151020 | 2024-05-31 | 0 | 0 | 0 | 27000 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE | State | 0
H12-04-010 | 12 | 5056026 | 4 | Dixon | Solano County | MTC | MTC | Nine pedestrian crossings: one at N 1st Street and E B Street, all four legs at Watson Ranch Way and Pitt School Road, and all four legs at Watson Ranch Way and N Lincoln Street. | Install rectangular rapid flashing beacons (RRFBs) and other standard crossing treatments including signing, striping, and curb enhancements. | 177100 | 159390 | 2025-09-08 | 0 | 0 | 0 | 26100 | Authorized | Due by 3/31/2028 | No | PE | State | 0
H12-04-011 | 12 | 5056025 | 4 | Dixon | Solano County | MTC | MTC | N Adams Street between W A Street and N 1st Street/SR 113. | Install buffered bike lanes, refresh bike lane striping and existing channelization, and add green conflict zone markings. | 160200 | 144180 | 2025-09-08 | 0 | 0 | 0 | 17100 | Authorized | Due by 3/31/2028 | No | PE | State | 0
H10-04-016 | 10 | 5438019 | 4 | East Palo Alto | San Mateo County | MTC | MTC | Intersection of Runnymede Street and University Ave | Traffic Signal Improvements to install protected left turn phase, upgrade equipment, and install bulbouts. | 1234400 | 1234400 | 2021-05-10 | 0 | 2024-03-22 | 0 | 1184294 | Authorized | Authorized | No | CON | State | 0
HSIP2-04-011 | 2 | 5239012 | 4 | El Cerrito | Contra Costa County | MTC | MTC | Fairmont Ave And Ashbury Ave Intersection | Upgrade Traffic Signals | 582383.86 | 522165.46 | 2009-01-29 | 0 | 2011-03-29 | 2015-10-29 | 522165.46 | Authorized | Authorized | No | Closed | Federal | 0
HSIP2-04-014C | 2 | 5239013 | 4 | El Cerrito | Contra Costa County | MTC | MTC | Portrero Ave. Between South 55Th St And 56 St | Upgrade Traffic Signals; Modify Channelization; Extend Left-Turn Lane; Remove Right-Turn Island | 787653.11 | 584277.12 | 2009-08-27 | 0 | 2012-05-02 | 2015-10-29 | 584277.12 | Authorized | Authorized | No | Closed | Federal | 0
HSIP2-04-015 | 2 | 5239015 | 4 | El Cerrito | Contra Costa County | MTC | MTC | Various Locations On The Ohlone Greenway Bike And Ped Path Between Fairmount Ave And Cutting Blvd. | Install In-Pavement Crosswalk Lights. | 552291.12 | 486547.23 | 2010-12-21 | 0 | 2012-09-18 | 2017-06-29 | 486547.23 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-04-006 | 5 | 5239023 | 4 | El Cerrito | Contra Costa County | MTC | MTC | Arlington Blvd./Brewster Dr. | Construct sidewalks, curb ramps, bulb-outs, curb and gutter, and shoulders; install speed feedback signs, sharrows, signs, striping, pavement markers | 266589.85 | 237509.62 | 2014-09-16 | 0 | 2015-11-06 | 2019-01-22 | 237509.62 | Authorized | Authorized | No | Closed | Federal | 0
H11-04-019 | 11 | 5132065 | 4 | Fairfield | Solano County | MTC | MTC | All city-owned signalized intersections in Fairfield. | Standardize signal heads to be 12" and have reflective backplates citywide. Relevant locations will also have advance intersection warning signs with flashing beacons, and larger intersections will get cat tracks as needed. | 2158700 | 1663200 | 0 | 0 | 2026-02-24 | 0 | 1663200 | No PE | Authorized | No | CON | State | 0
H11-04-020 | 11 | 5132063 | 4 | Fairfield | Solano County | MTC | MTC | High crash frequency and severity unsignalized intersection locations. | Improve/add signing along with striping and median installations to increase the visibility and safety of unsignalized intersections. | 690173 | 447570 | 0 | 0 | 2025-11-12 | 0 | 447570 | No PE | Authorized | No | CON | State | 0
H11-04-021 | 11 | 5132066 | 4 | Fairfield | Solano County | MTC | MTC | Three pedestrian crossings in Fairfield: Linear Park Trail & 2nd St, Linear Park Trail & 5th St and the I-80 EB Off Ramp & Travis Blvd. | Install RRFBs and other standard crossing treatments including signing, striping and curb enhancements. | 479300 | 248094 | 0 | 0 | 2026-03-04 | 0 | 248094 | No PE | Authorized | No | CON | State | 0
H11-04-022 | 11 | 5132060 | 4 | Fairfield | Solano County | MTC | MTC | Broadway St from Pennsylvania Ave to Union Ave; Kentucky St from Pennsylvania Ave to Union. | Install new bike lanes and re-stripe existing channelization. | 474700 | 249600 | 0 | 0 | 2025-03-14 | 0 | 249600 | No PE | Authorized | No | CON | State | 0
H12-04-012 | 12 | 0 | 4 | Fairfield | Solano County | MTC | MTC | Four pedestrian crossings: Linear Park Trail & Beck Avenue, Linear Park Trail & Fairfield Avenue, Linear Park Trail & Union Avenue, and Mankas Boulevard midblock crossing near Mankas Neighborhood Park. | Install rectangular rapid flashing beacons (RRFBs) and other standard crossing treatments including signing, striping, and curb enhancements. | 449300 | 342810 | 0 | 0 | 0 | 0 | 0 | No PE | Due by 3/31/2028 | No | Not Started | State | 0
H12-04-013 | 12 | 5132064 | 4 | Fairfield | Solano County | MTC | MTC | Texas Street/N Texas Street from Union Avenue to E Travis Boulevard. | Install new bike lanes and re-stripe existing channelization. | 283400 | 255060 | 2025-11-26 | 0 | 0 | 0 | 45450 | Authorized | Due by 3/31/2028 | No | PE | State | 0
H9-04-012 | 9 | 5132050 | 4 | Fairfield | Solano County | MTC | MTC | On Travis Boulevard between Oliver Road and N. Texas Street; On Oliver Road between Travis Boulevard and Woodcreek Drive; On N. Texas Street between Travis Boulevard and Walmart. | Install Adaptive Signal Timing and advanced dilemma-zone detection, and enhance the visibility of signals. | 3698978 | 1115726.5 | 0 | 0 | 2022-07-25 | 2025-10-27 | 1115726.5 | No PE | Authorized | No | Closed | Federal | 0
H9-04-013 | 9 | 5132052 | 4 | Fairfield | Solano County | MTC | MTC | Twenty-two (22) locations. | Upgrade existing guardrails and their end treatments. | 915295.94 | 902296.1 | 0 | 0 | 2022-06-26 | 2024-04-04 | 902296.1 | No PE | Authorized | No | Closed | Federal | 0
H9-04-014 | 9 | 5132051 | 4 | Fairfield | Solano County | MTC | MTC | Five non-signalized intersections, including: N Texas St at Oak St; Pennsylvania Ave at Empire St; N Texas St at Wisconsin St; Travis Blvd at Phoenix Dr; and Travis Blvd at Clay St. | Construct pedestrian crossing enhancements including HAWK installation accompanied by ADA curb ramp, and relevant signs and pavement markings. | 1939754.17 | 1220215.13 | 0 | 0 | 2022-05-23 | 2026-02-03 | 1220215.13 | No PE | Authorized | No | Closed | Federal | 0
HSIP6-04-004 | 6 | 5132044 | 4 | Fairfield | Solano County | MTC | MTC | N Texas St /Acacia St | Upgrade traffic signals and ramps; Install protected left-turn phasing | 178009.1 | 172852 | 0 | 0 | 2016-07-28 | 2019-06-14 | 172852 | No PE | Authorized | No | Closed | Federal | 0
HSIP6-04-005 | 6 | 5132043 | 4 | Fairfield | Solano County | MTC | MTC | On Travis Blvd between I-80 EB Off Ramp and Sunset Ave | Install pavement markings | 180461.8 | 162415.62 | 0 | 0 | 2015-12-23 | 2018-01-26 | 162415.62 | No PE | Authorized | No | Closed | Federal | 0
H10-04-017 | 10 | 5322062 | 4 | Fremont | Alameda County | MTC | MTC | Intersections of Fremont Boulevard & Papazian Way, Fremont Boulevard & Clough Ave, Fremont Boulevard & Adams Avenue, Fremont Boulevard & Michael Avenue, Fremont Boulevard & Crestwood Street, and Fremont Boulevard & Doane Street. | Adding intersection lighting on minor road approaches, installing RRFB with high-visibility crosswalks and adding median refuge islands on major road. Installing curb extensions with directional curb ramps. | 1849500 | 1664550 | 2021-09-30 | 0 | 2025-05-13 | 0 | 1664550 | Authorized | Authorized | No | CON | State | 0
H8-04-009 | 8 | 5322057 | 4 | Fremont | Alameda County | MTC | MTC | Fremont Blvd. at the intersections of Mowry Ave. and Stevenson Blvd. | Install 8 pedestrian and bicycle refuge areas (4 at each intersection); remove 8 right-turn slip lanes; relocate signals at intersections to accommodate new refuge areas. | 2609534.59 | 1296450 | 2017-06-06 | 0 | 2019-12-09 | 2022-08-03 | 1296450 | Authorized | Authorized | No | Closed | Federal | 0
HSIP1-04-005 | 1 | 5322030 | 4 | Fremont | Alameda County | MTC | MTC | Mowry Ave. East And West Of Overacker Ave. | Install Median Barrier; Install Raised Median; Improve Delineation. | 192998.17 | 169212.7 | 2007-11-28 | 0 | 2013-03-07 | 2015-10-29 | 169212.7 | Authorized | Authorized | No | Closed | Federal | 0
HSIP2-04-018 | 2 | 5322036 | 4 | Fremont | Alameda County | MTC | MTC | Paseo Padre Parkway From Decoto Rd. To Fremont Blvd. And From Thornton Ave. To Walnut Ave. | Replace Concrete Poles With Aluminum Poles Within Median | 213360.84 | 174736.77 | 2009-04-08 | 0 | 2011-04-19 | 2015-11-03 | 174736.77 | Authorized | Authorized | No | Closed | Federal | 0
HSIP3-04-005 | 3 | 5322041 | 4 | Fremont | Alameda County | MTC | MTC | Paseo Padre Parkway From Walnut Ave. To Washington Blvd. | Remove And Replace Existing Concrete Pole Electroliers In The Median With Aluminum Poles | 105682.19 | 95108.38 | 2010-11-18 | 0 | 2012-02-16 | 2015-10-29 | 95108.38 | Authorized | Authorized | No | Closed | Federal | 0
HSIP3-04-006 | 3 | 5322042 | 4 | Fremont | Alameda County | MTC | MTC | Walnut Ave. Between Fremont Blvd. And Parkhurst Dr. And Argonaut Way Between Parkhurst Dr. And Mowry Ave. | Construct Roundabout; Reduce Number Of Lanes From Four To Two; Install New Bicycle Lanes And Two-Way Left-Turn Lane | 1053054.76 | 517680 | 2010-11-22 | 0 | 2013-04-11 | 2015-12-14 | 517680 | Authorized | Authorized | No | Closed | Federal | 0
HSIP4-04-020 | 4 | 5322049 | 4 | Fremont | Alameda County | MTC | MTC | Fremont Blvd./Eggers Dr. | Upgrade traffic signals; install pedestrian countdown heads and safety lighting; widen sidewalks; construct bulb-outs | 461184.51 | 316200 | 2011-11-08 | 0 | 2014-01-24 | 2015-11-06 | 316200 | Authorized | Authorized | No | Closed | Federal | 0
HSIP4-04-022 | 4 | 5322048 | 4 | Fremont | Alameda County | MTC | MTC | Fremont Blvd./Alder Ave. | Remove free right-turn lanes; install pedestrian countdown heads; construct curb ramps and bulb-outs | 667781.24 | 391400 | 2011-11-08 | 0 | 2013-12-31 | 2016-05-26 | 391400 | Authorized | Authorized | No | Closed | Federal | 0
HSIP7-04-008 | 7 | 5322056 | 4 | Fremont | Alameda County | MTC | MTC | Washington Boulevard from Roberts Avenue to Meredith Drive | Construct curb bulb-out with rectangular rapid flashing beacons(RRFB), install buffered bike lane striping, radar feedback signs, and APS/countdown pedestrian signal heads | 647577.21 | 465820.63 | 2016-08-25 | 0 | 2018-09-10 | 2021-04-23 | 465820.63 | Authorized | Authorized | No | Closed | Federal
H12-04-014 | 12 | 5034032 | 4 | Gilroy | Santa Clara County | MTC | MTC | On the west side of Church Street, just north of its intersection with 1st Street. | Construct sidewalk and curb & gutter for a sidewalk gap closure, as well as two new driveway approaches to become ADA compliant. | 157900 | 142110 | 2025-05-28 | 0 | 0 | 0 | 19620 | Authorized | Due by 3/31/2028 | No | PE | State | 0
H12-04-015 | 12 | 0 | 4 | Gilroy | Santa Clara County | MTC | MTC | On the southeastern edge of the intersection of Santa Teresa Boulevard and Day Road East, diagonally across the intersection from Christopher High School. | Upgrade a guardrail and construct an ADA compliant access to the Lions Creek Trail along Santa Teresa Boulevard. | 959000 | 785375 | 0 | 0 | 0 | 0 | 0 | No PE | Due by 3/31/2028 | No | Not Started | State | 0
H10-04-018 | 10 | 5050049 | 4 | Hayward | Alameda County | MTC | MTC | Intersections of Huntwood Avenue/Industrial Parkway and Huntwood Avenue/Sandoval Way. | Install protected left-turn phase at Huntwood/Industrial; install protected-permissive left-turn phase at Huntwood/Sandoval; install Hybrid Video Detection for bikes and queue cutters; and upgrade Peer-to-Peer Communication. | 75000 | 67500 | 2022-01-20 | 0 | 0 | 2025-09-30 | 67500 | Authorized | No CON | No | Closed | State | 0
H12-04-016&018 | 12 | 5050051 | 4 | Hayward | Alameda County | MTC | MTC | The intersection of Industrial Parkway West/Industrial Parkway Southwest/Ruus Road. Ruus Rd between Folsom and Industrial, Amador St from Elmhurst St to Jackson St, and Soto Rd near Jackson St. | Install left turn phase traffic signals with pole and mast arm, convert pedestal mounted traffic signal to mast arm traffic signal, install raised pavement markings & striping through skewed intersection, and install pedestrian signals and APS pushbuttons. Install signage and striping changes to designate Class II bike lanes at Amador St and Soto Rd. Install mast arm traffic signals, raised pavement markings, pedestrian signals, and APS pushbuttons at Ruus Rd and Industrial Parkway W. | 934900 | 708654 | 2025-08-22 | 0 | 0 | 0 | 54614 | Authorized | Due by 3/31/2028 | No | PE | State | 0
H12-04-017 | 12 | 5050053 | 4 | Hayward | Alameda County | MTC | MTC | Various locations. | Improve traffic signal hardware, install pedestrian countdown signal heads, and improve intersection lighting. | 1755800 | 1580220 | 2025-11-24 | 0 | 0 | 0 | 139500 | Authorized | Due by 3/31/2028 | No | PE | Federal | 0
H12-04-019 | 12 | 5050052 | 4 | Hayward | Alameda County | MTC | MTC | Calaroga Ave/Eden Greenway; D St /5th St; Santa Clara St/El Dorado Ave; Santa Clara St/Ocie Way; Patrick Ave/St Bede Ln; Patrick Ave /Mid-Block Crossing at St Bede Catholic Church. | Install rectangular rapid flashing beacons (RRFBs), curb extensions, and pedestrian refuge islands. | 579100 | 349776 | 2025-08-22 | 0 | 0 | 0 | 26938 | Authorized | Due by 3/31/2028 | No | PE | State | 0
HSIP2-04-009 | 2 | 5050035 | 4 | Hayward | Alameda County | MTC | MTC | Carlos Bee Blvd. Between West Loop Rd. And Mission Blvd. | Realign Roadway | 1406561.17 | 724500 | 2009-02-23 | 0 | 2010-06-18 | 2013-02-13 | 724500 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-04-007 | 5 | 5050040 | 4 | Hayward | Alameda County | MTC | MTC | W "A" St. between Hathaway Ave. (Santa Clara St.) and S Garden Ave. | Construct medians; install flashing beacons | 317119.56 | 161000 | 2014-02-18 | 0 | 2014-06-08 | 2018-01-18 | 161000 | Authorized | Authorized | No | Closed | Federal | 0
HSIP6-04-006 | 6 | 5050043 | 4 | Hayward | Alameda County | MTC | MTC | Mission Blvd/Blanche St, Huntwood Way/Gading Rd | Install traffic signals; Install HAWK signal | 488888.88 | 439999.99 | 0 | 0 | 2016-04-05 | 2018-10-22 | 439999.99 | No PE | Authorized | No | Closed | Federal | 0
H11-04-023 | 11 | 5027024 | 4 | Healdsburg | Sonoma County | MTC | MTC | Powell Avenue at Johnson Street. | Install Rectangular Rapid Flashing Beacons (RRFBs), curb extensions, ADA curb ramps, yield lines, traffic signs, striping and pavement markings | 249800 | 224820 | 2023-10-16 | 0 | 2026-02-09 | 0 | 224820 | Authorized | Authorized | No | CON | State | 0
HSIP2-04-007 | 2 | 5027015 | 4 | Healdsburg | Sonoma County | MTC | MTC | Healdsburg Ave. Piper And Plaza St. | Install In-Pavement Crosswalk Lights. | 98900.06 | 83793 | 2010-04-27 | 0 | 2013-08-05 | 2013-11-15 | 83793 | Authorized | Authorized | No | Closed | Federal | 0
H12-04-020 | 12 | 0 | 4 | Hercules | Contra Costa County | MTC | MTC | Sycamore Avenue Corridor under I-80 and the BNSF railroad overcrossing. | Install a 10-ft multipurpose pathway and Class II bicycle lanes, improving safety and connectivity. | 1415600 | 350000 | 0 | 0 | 0 | 0 | 0 | No PE | Due by 3/31/2030 | No | Not Started | State | 0
HSIP1-04-008 | 1 | 5404017 | 4 | Lafayette | Contra Costa County | MTC | MTC | The Warner Court Curve. | Construct New Curb And Gutter And Regrade Side Slopes. | 86629.21 | 77814.17 | 2007-10-12 | 0 | 2009-03-09 | 2012-02-28 | 77814.17 | Authorized | Authorized | No | Closed | Federal | 0
HSIP1-04-009 | 1 | 5404018 | 4 | Lafayette | Contra Costa County | MTC | MTC | S-Curve Parallel To Reliez Valley Creek Near Lafayette High School | Install 250 Lf Of Guard Rail | 28876 | 25988 | 2008-03-08 | 0 | 2008-03-08 | 2009-07-09 | 25988 | Authorized | Authorized | No | Closed | Federal | 0
HSIP3-04-007 | 3 | 5404022 | 4 | Lafayette | Contra Costa County | MTC | MTC | T-Intersection Of St. Mary'S Rd. And Topper Ln. | Flatten Roadway Profile; Install 80' Of Guardrail; Shift Stop-Bar 15' South | 153889.21 | 136440 | 2010-11-22 | 0 | 2011-03-29 | 2012-07-09 | 136440 | Authorized | Authorized | No | Closed | Federal | 0
HSIP7-04-009 | 7 | 5404027 | 4 | Lafayette | Contra Costa County | MTC | MTC | On southbound Taylor Boulevard near Pleasant Hill Road | Install guard rail/median barrier and high-friction surface treatment | 148914 | 128950 | 0 | 0 | 2016-10-31 | 2018-03-28 | 128950 | No PE | Authorized | No | Closed | Federal
H12-04-021 | 12 | 5053033 | 4 | Livermore | Alameda County | MTC | MTC | Intersections of First St and Southfront Rd, E Stanley Blvd and Murrieta Blvd, Railroad Ave and S P St, First St and Maple St, Portola Ave and N L St , Northfront Road and North Vasco Road, Fenton St and E Stanley Blvd, and East Ave and Charlotte Way. | Improve pedestrian safety: install flashing beacons as advance warning, install advance stop bar before crosswalk (bicycle box), and modify signal phasing to implement a leading pedestrian interval (LPI). | 413200 | 371880 | 2025-04-22 | 0 | 0 | 0 | 66420 | Authorized | Due by 3/31/2028 | No | PE | State | 0
H12-04-022 | 12 | 5053034 | 4 | Livermore | Alameda County | MTC | MTC | Intersections of First St and Portola Ave, First St and Scott St, Jensen St and East Ave, Maple St and 5th St , Charlotte Way and Marcella St, and Charlotte Way and Arlene Way. | Install/upgrade larger or additional stop signs or other intersection warning/regulatory signs, install flashing beacons as advance warning and install rectangular rapid flashing beacons (RRFBs). | 452400 | 407160 | 2025-04-22 | 0 | 0 | 0 | 72720 | Authorized | Due by 3/31/2028 | No | PE | State | 0
H12-04-023 | 12 | 5053035 | 4 | Livermore | Alameda County | MTC | MTC | First St, Murrieta Blvd, Concannon Blvd, Las Positas Road, N Livermore Ave, S. Vasco Rd, W Jack London Blvd, Portola Ave, E Stanley Blvd and Patterson Pass Rd. | Install dynamic/variable speed warning signs. | 1248600 | 1123740 | 2025-04-22 | 0 | 0 | 0 | 200610 | Authorized | Due by 3/31/2028 | No | PE | State | 0
H12-04-024 | 12 | 5053036 | 4 | Livermore | Alameda County | MTC | MTC | College Ave and S Livermore Ave, Hansen Rd and Arroyo Rd, East Ave and Mitra St, Springtown Blvd and Rhododendron Dr. | Improve crossing signage and striping, and install rectangular rapid flashing beacons (RRFBs). | 380600 | 342540 | 2025-04-22 | 0 | 0 | 0 | 61200 | Authorized | Due by 3/31/2028 | No | PE | State | 0
HSIP4-04-025 | 4 | 5309015 | 4 | Los Altos | Santa Clara County | MTC | MTC | Homestead Rd. between Belleville Way and Foothill Expressway | Install traffic signals, crosswalks, turning islands, and pedestrian/bike pathway; construct drainage improvements | 1294056.63 | 608999.99 | 0 | 0 | 2012-08-02 | 2016-04-12 | 608999.99 | No PE | Authorized | No | Closed | Federal | 0
H9-04-015 | 9 | 5067022 | 4 | Los Gatos | Santa Clara County | MTC | MTC | Guardrail locatoins on Blossom Hill Road, Cleland Avenue, Los Gatos Boulevard, Miles Avenue, More Avenue, Reservoir Road, and Santa Rosa Drive. | Upgrade the existing non-conforming and/or damaged guardrails. | 876328.84 | 847854.58 | 2019-09-06 | 0 | 2021-02-03 | 2022-05-06 | 847854.58 | Authorized | Authorized | No | Closed | Federal | 0
HSIP3-04-012 | 3 | 5067017 | 4 | Los Gatos | Santa Clara County | MTC | MTC | Intersection Of Sr 9 And University Ave. | Reconstruct Intersection; Upgrade Signal Poles And Equipment; Relocate Utility Pole; Remove Porkchop Island; Extend Wb Left-Turn Lane; Close Median Opening 250' East Of Intersection | 905685.73 | 810864.66 | 0 | 0 | 2013-06-20 | 2018-06-14 | 810864.66 | No PE | Authorized | No | Closed | Federal | 0
H10-04-019 | 10 | 5927126 | 4 | Marin County | Marin County | MTC | MTC | Intersection of Pt Reyes Petaluma Rd and Nicasio Valley Rd in Nicasio, County of Marin. | At southbound Pt Reyes Petaluma Rd, add left turn lane and associated roadway widening, asphalt paving and improve intersection traffic safety. | 2017100 | 1815390 | 2021-05-14 | 2023-01-04 | 0 | 0 | 247500 | Authorized | Past due (due 3/30/2026) | Yes (CON) | ROW | State | 0
H10-04-020 | 10 | 5927127 | 4 | Marin County | Marin County | MTC | MTC | Three locatoins: Woodland Avenue and Auburn Street (new Pedestrian Crosswalk with RRFB) in San Rafael, North San Pedro Road and Schmidt Avenue (install RRFB only) in San Rafael area, and McAllister Avenue and Stadium Way (install RRFB only) in Kentfield area. | Construct curb, gutter, sidewalk, curb ramps, & curb extensions; bulb-out, Install RRFB, curve, Stripe crosswalks. | 270000 | 250000 | 2021-05-14 | 0 | 2022-04-05 | 2023-12-15 | 250000 | Authorized | Authorized | No | Closed | State | 0
H10-04-021 | 10 | 5927128 | 4 | Marin County | Marin County | MTC | MTC | A portion of Panoramic Highway between Mile post 4 to 8 in Marin County. | Install skid resistant pavement and widen the shoulder as need along the roadway. Provide a safety edge on the pavement edge where feasible. | 2069500 | 2069500 | 2021-05-14 | 0 | 2025-08-22 | 0 | 1910000 | Authorized | Authorized | No | CON | State | 0
H10-04-022 | 10 | 5927129 | 4 | Marin County | Marin County | MTC | MTC | Point San Pedro Rd (PSP) and Summit Ave crosswalk. | Install Pedestrian Hybrid Beacon (HAWK). | 461500 | 461500 | 2021-05-14 | 0 | 2025-04-28 | 0 | 362300 | Authorized | Authorized | No | CON | State | 0
H11-04-024 | 11 | 5927138 | 4 | Marin County | Marin County | MTC | MTC | Various locations throughout County of Marin: Los Ranchitos Rd (San Rafael), Vineyard Rd (Novato) and Auburn Street (San Rafael). | Install radar signs to improve traffic safety of bicyclist and pedestrians. | 227500 | 204750 | 2024-03-11 | 0 | 0 | 0 | 0 | Authorized | Due by 3/31/2027 | No | Withdrawn | Federal | 1
H11-04-025 | 11 | 5927135 | 4 | Marin County | Marin County | MTC | MTC | Las Gallinas Ave/Roundtree Blvd (San Rafael), and Panoramic Highway between Edgewood Ave and Pan Toll Rd. | Install Rectangular Rapid Flashing Beacon (RRFB) at Las Gallinas Ave/Roundtree Blvd, and Install RRFB and radar sign at Panoramic Highway between Edgewood Ave and Pan Toll Rd. | 412600 | 371340 | 2023-12-18 | 0 | 0 | 0 | 3600 | Authorized | Due by 3/31/2027 | No | PE | State | 0
H11-04-026 | 11 | 5927136 | 4 | Marin County | Marin County | MTC | MTC | Various locations along Sir Francis Drake Blvd, Tomales Petaluma Road and Panoramic Highway. | Install warning signs and High Friction Pavement treatment. | 1190500 | 1071450 | 2023-12-15 | 0 | 0 | 0 | 27000 | Authorized | Due by 3/31/2027 | No | PE | State | 0
H11-04-027 | 11 | 5927137 | 4 | Marin County | Marin County | MTC | MTC | Various Rural and arterial roadways in the County of Marin. | Replace/ upgrade existing guardrails and end treatments. Replace nonstandard guardrails that have nonstandard end treatments and lower than minimum guardrail height required. The guardrails are located along high traffic volume and speed. | 946700 | 852030 | 2024-02-02 | 0 | 0 | 0 | 0 | Authorized | Due by 3/31/2027 | No | Withdrawn | Federal | 1
H12-04-025 | 12 | 5927146 | 4 | Marin County | Marin County | MTC | MTC | Irving Drive and Butterfield Road (T-intersection) in unincorporated San Anselmo, Marin County. | Improve pedestrian crossing. | 349500 | 314550 | 2025-12-30 | 0 | 0 | 0 | 27000 | Authorized | Due by 3/31/2028 | No | PE | State | 0
H12-04-026 | 12 | 5927147 | 4 | Marin County | Marin County | MTC | MTC | North San Pedro Road in San Rafael, Pinehill Road in Mill Valley, and variable location for portable trailer. | Install radar feedback signs and deploy portable radar feedback trailer in various locations. | 232200 | 208980 | 2025-12-30 | 0 | 0 | 0 | 31500 | Authorized | Due by 3/31/2028 | No | PE | State | 0
H8-04-010 | 8 | 5927118 | 4 | Marin County | Marin County | MTC | MTC | Various rural arterial and collector roads. | Upgrade existing guardrails. | 777788.53 | 766093.18 | 2018-01-05 | 0 | 2020-02-28 | 2022-11-23 | 766093.18 | Authorized | Authorized | No | Closed | Federal | 0
H8-04-011 | 8 | 5927119 | 4 | Marin County | Marin County | MTC | MTC | Various rural arterial and collector roadways | Install guardrail system | 433778.4 | 312860.19 | 2017-12-05 | 0 | 2020-04-30 | 2021-04-01 | 312860.19 | Authorized | Authorized | No | Closed | Federal | 0
H9-04-016 | 9 | 5927122 | 4 | Marin County | Marin County | MTC | MTC | Fifty-eight (59) signalized intersections throughout Marin County, including unincorporated Marin County and within 11 incorporated cities and towns. | Upgrading signal heads to 12" LED signal heads, adding signal head backplates, adding pedestrian countdown heads, adding audible pedestrian signals (APS) at pedestrian push buttons, updating, signal hardware to incorporate Lead Pedestrian Intervals (LPI) at crosswalks, and adding video or advanced detection loops for advanced dilemma zone detections | 2000442.57 | 1981953.02 | 2019-06-14 | 0 | 2022-03-08 | 2026-03-27 | 1981953.02 | Authorized | Authorized | No | Closed | Federal | 0
H9-04-017 | 9 | 5927123 | 4 | Marin County | Marin County | MTC | MTC | Locations on Various rural arterials and major collector roadways in the County of Marin. | Upgrade nonstandard guardrails. | 2239266.82 | 2101779.42 | 2019-10-23 | 0 | 2023-04-05 | 2025-06-27 | 2101779.42 | Authorized | Authorized | No | Closed | Federal | 1
HRRR2-04-024C | 2 | 5927077 | 4 | Marin County | Marin County | MTC | MTC | Along Point Reyes Petaluma Road near Nicasio Road; Lucas Valley Road from Mile Post 4.7 to 4.8 | Upgrade guardrail; install guardrail | 233479.29 | 210131.36 | 2010-02-02 | 0 | 2011-03-28 | 2013-10-18 | 210131.36 | Authorized | Authorized | No | Closed | Federal | 0
HSIP1-04-012 | 1 | 5927060 | 4 | Marin County | Marin County | MTC | MTC | Point Reyes Petaluma Rd. South Of Platform Bridge, Mp 11.92 - Mp 12.03. | Install Approx. 200Ft Guardrail | 51081.38 | 39404.38 | 2008-10-28 | 0 | 2015-05-22 | 2015-12-04 | 39404.38 | Authorized | Authorized | No | Closed | Federal | 0
HSIP4-04-009 | 4 | 5927090 | 4 | Marin County | Marin County | MTC | MTC | Redwood Hwy. Frontage Rd./US 101 (DeSilva Island Dr.) | Install protected left-turn phasing; modify intersection channelization | 812533.17 | 359144.37 | 2011-12-15 | 0 | 2014-08-20 | 2017-10-13 | 359144.37 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-04-008 | 5 | 5927101 | 4 | Marin County | Marin County | MTC | MTC | East Sir Francis Drake Blvd. PM 0.05 to 0.60 | Install guardrail and speed feedback signs; pave shoulders | 202119.09 | 143667.6 | 2013-06-10 | 0 | 2014-08-13 | 2016-10-20 | 143667.6 | Authorized | Authorized | No | Closed | Federal | 0
HSIP7-04-010 | 7 | 5927112 | 4 | Marin County | Marin County | MTC | MTC | Lucas Valley Road at PM 5.08 | Improve roadway curve alignment at Mile Post 5.08 | 1978486.31 | 1207500 | 2016-07-22 | 0 | 2020-09-09 | 2022-11-10 | 1207500 | Authorized | Authorized | No | Closed | Federal
HSIP7-04-011 | 7 | 5927115 | 4 | Marin County | Marin County | MTC | MTC | Arterials and rural collector roadways | Sign inventory, roadway safety sign audit and signing upgrade project | 605000 | 544500 | 2016-09-14 | 0 | 2022-01-13 | 0 | 393806.25 | Authorized | Authorized | No | CON | Federal
HSIP7-04-012 | 7 | 5927113 | 4 | Marin County | Marin County | MTC | MTC | Panoramic Highway between Mile Post 6.7 and 8.8 | Install guardrail (1500 ft.)and install additional curve warning and chevron signs | 303522.33 | 273170.09 | 2016-08-19 | 0 | 2018-01-11 | 2019-07-12 | 273170.09 | Authorized | Authorized | No | Closed | Federal
HSIP7-04-013 | 7 | 5927114 | 4 | Marin County | Marin County | MTC | MTC | Sir Francis Drake Boulevard between Mile Post 8.60 and 9.53 | Install dynamic variable speed warning signs at two locations for the downhill traffic, additional curve warning signs and skid resistant pavement resurfacing | 2122240.08 | 1056824.39 | 2016-08-04 | 0 | 2018-11-29 | 2021-01-25 | 1056824.39 | Authorized | Authorized | No | Closed | Federal
HSIP4-04-023 | 4 | 5273022 | 4 | Menlo Park | San Mateo County | MTC | MTC | Oak Grove Ave./Merrill St. | Install in-pavement crosswalk lights | 64669.91 | 49500 | 2011-12-28 | 0 | 2013-09-03 | 2015-01-14 | 49500 | Authorized | Authorized | No | Closed | Federal | 0
H10-04-023 | 10 | 5113021 | 4 | Mill Valley | Marin County | MTC | MTC | Multiple locations along E. Blithdale Avenue, located at Sunnyside Avenue, Mountain View Avenue, Dell Street, and Hilarita/Mesa Avenue. | Construct pedestrian crossing improvements to improve pedestrian safety. | 410000 | 250000 | 0 | 0 | 2021-11-12 | 2024-10-08 | 250000 | No PE | Authorized | No | Closed | State | 0
H11-04-028 | 11 | 5113022 | 4 | Mill Valley | Marin County | MTC | MTC | Three locations between 700 and 759 E. Blithedale Ave. Project location is a major arterial in Mill Valley and within Marin County. | Upgrade existing timber and post guard rail. | 1111111 | 1000000 | 2023-07-31 | 0 | 2024-11-07 | 0 | 1000000 | Authorized | Authorized | No | CON | State | 0
H12-04-027 | 12 | 5113023 | 4 | Mill Valley | Marin County | MTC | MTC | Various locations. | Install pedestrian crossing; install sidewalk; install/upgrade pedestrian crossing; install rectangular rapid flashing beacons (RRFBs). | 388900 | 350000 | 2025-07-24 | 0 | 0 | 0 | 62460 | Authorized | Due by 3/31/2028 | No | PE | State | 0
HSIP1-04-002 | 1 | 5113008 | 4 | Mill Valley | Marin County | MTC | MTC | Bolsa Ave (Above 164 Hillside Ave), Camino Alto (950Ft N/O Azalea Dr) , 522 Cascade Ave, 312 Edgewood Ave, 160 Rose Ave, And 580 Edgewood Ave. | Install Guardrail At Various Locations. | 380981.55 | 300107.2 | 2009-06-02 | 0 | 2009-06-03 | 2012-01-18 | 300107.2 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-04-009 | 5 | 5113017 | 4 | Mill Valley | Marin County | MTC | MTC | Miller Ave. between Millwood St. and Sunnyside Ave. | Construct sidewalks; install bike lanes | 454867.13 | 391600 | 0 | 0 | 2016-02-16 | 2018-07-19 | 391600 | No PE | Authorized | No | Closed | Federal | 0
HSIP6-04-008 | 6 | 5113018 | 4 | Mill Valley | Marin County | MTC | MTC | On Camino Alto between Miller Ave and E. Blithedale Ave | Install bike lanes, striping, signs; upgrade traffic signal | 535246.16 | 356300 | 2014-12-30 | 0 | 2018-03-15 | 2021-02-22 | 356300 | Authorized | Authorized | No | Closed | Federal | 0
H12-04-028 | 12 | 5314016 | 4 | Milpitas | Santa Clara County | MTC | MTC | All city owned and maintained traffic signals (72); three (3) unsignalized intersections; and N McCarthy Blvd curve 500 feet south of the city boundary between Milpitas and Fremont. | Install retroreflective backplates and leading pedestrian interval (LPI), improve visibility with signage, daylighting and beacons, and improve horizontal curve. | 2293700 | 2064330 | 2025-11-05 | 0 | 0 | 0 | 343710 | Authorized | Due by 3/31/2028 | No | PE | Federal | 0
H10-04-024 | 10 | 5415016 | 4 | Moraga | Contra Costa County | MTC | MTC | Various locations within Town of Moraga | Install pedestrian improvements including signage and striping to improve crosswalk visibility and improve pedestrian safety. | 332100 | 276240 | 2021-06-30 | 0 | 2024-04-16 | 0 | 276240 | Authorized | Authorized | No | CON | State | 0
H11-04-029 | 11 | 5415018 | 4 | Moraga | Contra Costa County | MTC | MTC | Various non-signalized intersections including Moraga Road at Lucas and at Alta Mesa; Moraga Way at Moraga Valley Lane; Camino Pablo at Sanders Ranch Road; and Rheem Boulevard at St. Mary's Road. | Install/upgrade stop signs and other intersection warning/egulatory signs; install RRFB on Moraga Rd at Lucas Dr; install flashing beacons on Moraga Wy/Moraga Valley Ln, Moraga Rd/Alta Mesa Dr, St. Mary's Rd/Rheem Blvd and Moraga Rd/Corliss Dr. | 534100 | 480690 | 2024-05-06 | 0 | 2024-07-19 | 0 | 480690 | Authorized | Authorized | No | CON | State | 0
H11-04-057 | 11 | 5415019 | 4 | Moraga | Contra Costa County | MTC | MTC | Three primary corridors and two non-signalized intersections: Moraga Wy; Moraga Rd from Larch Ave to Town Limit north; Rheem Blvd from Moraga Rd to La Salle; Moraga Wy/Moraga Valley Ln; and Moraga Road/Corliss Drive. | Upgrade and/or install enhanced safety features at pedestrian crossings. At Moraga Road at Corliss Drive, install flashing beacon and larger warning and regulatory signs in advance of intersection. | 290200 | 261180 | 2024-05-06 | 0 | 2024-07-18 | 0 | 220500 | Authorized | Authorized | No | CON | State | 0
H12-04-029 | 12 | 5415020 | 4 | Moraga | Contra Costa County | MTC | MTC | The primary corridors connecting Moraga with adjacent communities and two non-signalized intersections: Moraga Wy, Canyon Rd, Rheem Blvd, St. Mary’s Rd, Moraga Rd at Lucas Dr (intersection), and Moraga Way at Moraga Valley Ln (intersection). | Apply high friction surface treatment (HFST), install intersection lighting, install/upgrade signs with new fluorescent sheeting (regulatory or warning), and install delineators, reflectors and/or object markers. | 1048700 | 943830 | 2025-12-12 | 0 | 0 | 0 | 97200 | Authorized | Due by 3/31/2028 | No | PE | State | 0
HSIP1-04-010 | 1 | 5415007 | 4 | Moraga | Contra Costa County | MTC | MTC | Intersection Of Moraga Rd And Ascot Dr. | Install Traffic Signal; Construct Raised Median; Install Ped/Bike Improvements. | 696946.95 | 601470 | 2007-09-12 | 0 | 2008-07-03 | 2013-12-20 | 601470 | Authorized | Authorized | No | Closed | Federal | 0
H8-04-012 | 8 | 5124034 | 4 | Mountain View | Santa Clara County | MTC | MTC | Intersection of Shoreline Blvd. at Villa St. | Upgrade existing traffic signal; add protected left turn phase on minor street approaches; install new pedestrian crosswalk; remove existing channelized free right turn and "pork chop" island; construct curb, gutter, sidewalk. | 996671.29 | 400725 | 0 | 0 | 2019-11-19 | 2024-09-16 | 400725 | No PE | Authorized | No | Closed | Federal | 0
HSIP4-04-014 | 4 | 5124029 | 4 | Mountain View | Santa Clara County | MTC | MTC | Middlefield Rd. between Easy St. and Shoreline Blvd. | Upgrade median islands; install striping and pavement markings | 579582.68 | 519455.4 | 0 | 0 | 2014-03-18 | 2017-10-16 | 519455.4 | No PE | Authorized | No | Closed | Federal | 0
H11-04-030 | 11 | 5042064 | 4 | Napa | Napa County | MTC | MTC | Various uncontrolled crossing locations throughout the City of Napa. | Install Rectangular Rapid Flashing Beacons, ADA curb ramps, curb extensions, signage, and striping. | 711000 | 639900 | 2023-12-11 | 0 | 0 | 0 | 68580 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE | State | 0
H11-04-031 | 11 | 5042065 | 4 | Napa | Napa County | MTC | MTC | 5 locations along the Lincoln Avenue corridor; 5 locations along the Browns Valley Road/First Street corridor. | Install High Friction Surface Treatments. | 516800 | 465120 | 2023-12-11 | 0 | 0 | 0 | 49860 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE | State | 0
H12-04-030 | 12 | 5042066 | 4 | Napa | Napa County | MTC | MTC | Sixteen (16) signalized intersections. | Provide one protected left-turn phase, install one pedestrian countdown signal head, and modify signal phasing for fourteen intersections to implement a leading pedestrian interval (LPI). | 424000 | 381600 | 2026-01-09 | 0 | 0 | 0 | 33750 | Authorized | Due by 3/31/2028 | No | PE | State | 0
H12-04-031 | 12 | 0 | 4 | Napa | Napa County | MTC | MTC | Non-signalized intersection: California Boulevard and Pueblo Avenue. | Install upgraded stop signs and intersection pavement markings. | 51100 | 45990 | 0 | 0 | 0 | 0 | 0 | No PE | Due by 3/31/2028 | No | Not Started | State | 0
H10-04-025 | 10 | 5921085 | 4 | Napa County | Napa County | MTC | MTC | 3 guardrail sections along Silverado Trail from Meadwood Lane to Fawn Park Road and 10 guardrail sections along Petrified Forest Rd from Franz Valley School Rd to Rancho Juan Inez Rd. | Upgrade guardrail segments and end treatments. | 1000000 | 995127 | 2021-05-10 | 0 | 2022-05-25 | 2023-12-27 | 995127 | Authorized | Authorized | No | Closed | State | 0
H10-04-026 | 10 | 5921086 | 4 | Napa County | Napa County | MTC | MTC | 52 roadway segments on the Valley Floor of Napa County. | Upgrade roadway striping with the following or a combination of wet reflective beading high visibility centerline, edge line, and class 2 bike lanes. | 2932100 | 2931226 | 2021-05-10 | 0 | 2022-06-02 | 2024-10-04 | 2931226 | Authorized | Authorized | No | Closed | State | 0
H11-04-032 | 11 | 5921089 | 4 | Napa County | Napa County | MTC | MTC | 1.1 miles of guardrail upgrades within Napa County, with 4 sections on Silverado Trail, 1 section on Petrified Forest Rd, 5 sections on Deer Park Rd, 1 section on Howell Mountain Rd, and 2 sections on Tubbs Ln. | Guardrail and end treatment upgrades. | 1198500 | 1000000 | 2023-08-08 | 0 | 0 | 0 | 79265 | Authorized | Due by 6/30/2027 | No | PE | Federal | 1
H11-04-033 | 11 | 5921090 | 4 | Napa County | Napa County | MTC | MTC | Intersections of Silverado Trail/Oak Knoll Ave and Silverado Trail/Zinfandel Ln. | Upgrade bike lane striping, incorporate street lighting, install advanced flashing beacons, and install right turn lane. | 1230200 | 1107180 | 2023-10-16 | 0 | 0 | 0 | 177930 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE | State | 0
H12-04-032 | 12 | 5921098 | 4 | Napa County | Napa County | MTC | MTC | 24 sections spread along Howell Mountain Rd (5), White Cottage Rd (2), Oakville Cross Rd (6), Silverado Trail (1), Oak Knoll Ave (6), and Larkmead Ln (3). | Upgrade guardrails and end treatments. | 1111100 | 999990 | 2025-11-06 | 0 | 0 | 0 | 81000 | Authorized | Due by 3/31/2028 | No | PE | Federal | 1
H9-04-018 | 9 | 5921079 | 4 | Napa County | Napa County | MTC | MTC | Silverado Trail, MM 00.00-11.00. | Upgrade existing guardrail on Silverado Trail to meet the current standards. | 579076.13 | 579076.13 | 2019-09-06 | 0 | 2022-09-20 | 2023-11-09 | 579076.13 | Authorized | Authorized | No | Closed | Federal | 1
H9-04-019 | 9 | 5921080 | 4 | Napa County | Napa County | MTC | MTC | Silverado Trail north of Trancas St and south of HWY 29, excluding portions within City of St. Helena, City of Calistoga, and Caltrans ROW. | Upgrade striping on Silverado Trail from Trancas Street to Highway 29. The striping upgrade will only occur within portions of the roadway under County jurisdiction. All work will occur within existing County right of way. | 929109.42 | 929109.42 | 2019-09-06 | 0 | 2022-07-25 | 2024-01-09 | 929109.42 | Authorized | Authorized | No | Closed | Federal | 1
HRRR2-04-035 | 2 | 5921055 | 4 | Napa County | Napa County | MTC | MTC | Wooden Valley Road from Solano County Line (PM 0.0) to Highway 121 (PM 6.7) | Install guardrail, pavement markers, and delineators | 184998.17 | 162228.55 | 0 | 0 | 2013-04-17 | 2014-04-27 | 162228.55 | No PE | Authorized | No | Closed | Federal | 0
HRRR2-04-036 | 2 | 5921056 | 4 | Napa County | Napa County | MTC | MTC | North Kelly Road at PM 1.50 | Upgrade guardrail; improve signs and delineation | 26175.67 | 19040.98 | 0 | 0 | 2013-03-26 | 2014-01-09 | 19040.98 | No PE | Authorized | No | Closed | Federal | 0
HSIP2-04-001 | 2 | 5921057 | 4 | Napa County | Napa County | MTC | MTC | Deer Park Road And Sunnyside Road | Install Solar Powered Speed Signs. | 25925.98 | 17369.94 | 0 | 0 | 2013-03-26 | 2014-11-12 | 17369.94 | No PE | Authorized | No | Closed | Federal | 0
HSIP6-04-009 | 6 | 5921064 | 4 | Napa County | Napa County | MTC | MTC | Various locations on Butts Canyon Rd, Hagen Rd/Old Sonoma Rd | Install High Friction Surface Treatment | 268033.32 | 268033.05 | 0 | 0 | 2016-03-23 | 2017-10-12 | 268033.05 | No PE | Authorized | No | Closed | Federal | 0
HSIP6-04-010 | 6 | 5921065 | 4 | Napa County | Napa County | MTC | MTC | Various locations on Silverado Trail, Deer Park Rd And Sanitarium Rd | Install guardrail | 284569.11 | 284569.11 | 0 | 0 | 2016-03-23 | 2017-10-12 | 284569.11 | No PE | Authorized | No | Closed | Federal | 0
H11-04-034 | 11 | 5317019 | 4 | Newark | Alameda County | MTC | MTC | Two unsignalized intersections: Thornton Ave & Magnolia St and Enterprise Dr & Aleppo Dr. | Install Rectangular Rapid Flashing Beacons with accompanying signage, curb cuts and pavement striping. | 192800 | 173520 | 2023-10-16 | 0 | 0 | 0 | 26280 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE | State | 0
H9-04-020 | 9 | 5361031 | 4 | Novato | Marin County | MTC | MTC | Diablo Avenue/De Long Avenue corridor between Novato Boulevard and Reichert Avenue. | Improve pedestrian crosswalks throughout the corridor, install advanced dilemma zone detection at two key intersections, and provide an advance flashing beacon at upstream of an intersection with an arterial roadway. | 1153554.69 | 1142994.29 | 2021-10-25 | 0 | 2023-04-20 | 2025-06-26 | 1142994.29 | Authorized | Authorized | No | Closed | Federal | 2
HSIP5-04-010 | 5 | 5361025 | 4 | Novato | Marin County | MTC | MTC | Olive Ave. from Samrose Dr. to the city limits | Widen roadway; apply slurry seal; install bike lanes | 568571.64 | 508791.09 | 2013-08-15 | 0 | 2015-11-02 | 2017-10-12 | 508791.09 | Authorized | Authorized | No | Closed | Federal | 0
H10-04-027 | 10 | 5012163 | 4 | Oakland | Alameda County | MTC | MTC | Six intersections throughout the City of Oakland: Alcatraz/Dana, Shattuck/56th, 18th/E.15th, 23rd/E.20th, 55th/Holland, & 69th/Brentford. | Install Rapid Rectangular Flashing Beacons (RRFBs) and Intersection Lighting at five intersection and a diagonal traffic diverter at 18th / E. 15th. | 2271100 | 2271100 | 2021-09-01 | 0 | 2024-03-26 | 0 | 2271000 | Authorized | Authorized | No | CON | State | 0
H10-04-028 | 10 | 5012164 | 4 | Oakland | Alameda County | MTC | MTC | Seven intersections along 98th Avenue between Pearmain Street and Birch Street. | Install side street signal mast arms, leading pedestrian intervals, RRFBs, pedestrian refuge islands, and left-turn-only phases. | 2242200 | 2182590 | 2021-09-01 | 0 | 2024-05-23 | 0 | 2182590 | Authorized | Authorized | No | CON | State | 0
H10-04-029 | 10 | 5012165 | 4 | Oakland | Alameda County | MTC | MTC | 14th Street in West Oakland between Mandela Parkway and Adeline Street with proposed corridor improvements between the extents as well as the original intersections of 14th Street and Mandela, Poplar, Magnolia, and Adeline. | The updated project will repurpose 2 of 4 total vehicle lanes to upgrade existing bicycle lanes to buffered bike lanes. There are existing left-turn lanes. Original proposed left-turn signal phasing, LPIs, RRFBs will still be installed. | 1693800 | 1570220 | 2021-09-01 | 0 | 2025-08-22 | 0 | 1570220 | Authorized | Authorized | No | CON | State | 0
H11-04-035 | 11 | 0 | 4 | Oakland | Alameda County | MTC | MTC | 51 signalized intersections within Oakland’s priority equity neighborhoods. | Enhance pedestrian safety and accessibility by adding leading pedestrian intervals, longer pedestrian clearance times and pedestrian countdown signal heads. | 1909000 | 1718100 | 0 | 0 | 0 | 0 | 0 | No PE | Due by 3/31/2028 | No | Not Started | State | 0
H11-04-036 | 11 | 5012171 | 4 | Oakland | Alameda County | MTC | MTC | MacArthur Blvd/90th Ave and Bancroft Ave/90th Ave. | Enhance ped/bike safety by adding leading pedestrian intervals, pedestrian countdown heads, protected left turns, raised medians, and other safety upgrades - primarily at Bancroft Ave/90th Ave. MacArthur will get raised medians. | 1206600 | 1085940 | 2023-06-28 | 0 | 0 | 0 | 193500 | Authorized | Due by 2/28/2028 | No | PE | State | 0
H11-04-037 | 11 | 0 | 4 | Oakland | Alameda County | MTC | MTC | Nine non-signalized intersections at arterial and collector streets within Oakland’s priority equity neighborhoods. | Enhance pedestrian and bicycle safety by installing Rectangular Rapid Flashing Beacons (RRFBs), refuge islands, and bulb-outs, and install/upgrade crosswalks and curb ramps. | 2579900 | 2321910 | 0 | 0 | 0 | 0 | 0 | No PE | Due by 12/31/2027 | No | Not Started | Federal | 2
H12-04-033 | 12 | 5012177 | 4 | Oakland | Alameda County | MTC | MTC | 4 intersections in Oakland neighborhoods: MLK Jr. Way & W Grand Ave; Orange St & Perkins St; Park Blvd & Leimert Blvd; and Fruitvale Ave & International Blvd. | Add a protected left-turn phase, add intersection mast-arms, install raised median/pedestrian refuge islands, and install/upgrade pedestrian crossings. | 2043800 | 1839420 | 2026-01-05 | 0 | 0 | 0 | 319500 | Authorized | Due by 3/31/2028 | No | PE | Federal | 2
H12-04-034 | 12 | 5012178 | 4 | Oakland | Alameda County | MTC | MTC | 13 non-signalized intersections at arterial and collector streets throughout Oakland. | Install rectangular rapid flashing beacons (RRFBs), install/upgrade pedestrian crossings at uncontrolled locations, and install raised medians/refuge islands. | 1220400 | 1098360 | 2025-09-17 | 0 | 0 | 0 | 162000 | Authorized | Due by 3/31/2028 | No | PE | State | 0
H8-04-013 | 8 | 5012147 | 4 | Oakland | Alameda County | MTC | MTC | On Bancroft Avenue in the City of Oakland between Havenscourt Boulevard and 98th Street | Install HAWKs and RRFBs at eleven locations along the corridor; install signal mast arms at three locations; and install a landscape at the northeast corner of Bancroft and 67th Street. | 4770700 | 3595300 | 2017-10-13 | 0 | 2020-01-08 | 0 | 3595300 | Authorized | Authorized | No | CON | Federal | 0
H8-04-014 | 8 | 5012149 | 4 | Oakland | Alameda County | MTC | MTC | Fruitvale Avenue from Ashbrook Court to E 10th Street. | Install new Class II bicycle lanes, enhanced safety features at pedestrian crossings, and a new protected left turn phase at Foothill Blvd. | 1008750.8 | 907743.6 | 2017-10-13 | 0 | 2020-01-08 | 2024-11-05 | 907743.6 | Authorized | Authorized | No | Closed | Federal | 0
H8-04-015 | 8 | 5012150 | 4 | Oakland | Alameda County | MTC | MTC | 35th Avenue from E 12th Street to I-580. | Construct crossing enhancements, a protected left turn phase at Foothill Blv, and Class II bicycle lanes between International Blvd and E 12th Street. | 2575234.68 | 2162759.4 | 2017-10-13 | 0 | 2019-04-05 | 2022-05-05 | 2162759.4 | Authorized | Authorized | No | Closed | Federal | 0
H8-04-016 | 8 | 5012152 | 4 | Oakland | Alameda County | MTC | MTC | High Street from San Leandro Street to I-580. | Construct crossing enhancements, signal placement improvements, and new pedestrian signal countdown heads. | 1534450.64 | 1409088.68 | 2017-10-13 | 0 | 2020-01-08 | 2025-12-03 | 1409088.68 | Authorized | Authorized | No | Closed | Federal | 0
H8-04-017 | 8 | 5012151 | 4 | Oakland | Alameda County | MTC | MTC | Intersections in Downtown Oakland in the area bounded by Broadway, 9th Street, Harrison Street, and 7th Street, and the intersection of 10th Street and Harrison Street. | Construct safety improvements at 13 intersections, including signal mast arms, vehicle/bicycle detection, accessible pedestrian signal upgrade, and other improvements. | 973354.18 | 527040 | 2017-10-13 | 0 | 2020-01-16 | 2024-11-20 | 527040 | Authorized | Authorized | No | Closed | Federal | 0
H8-04-018 | 8 | 5012148 | 4 | Oakland | Alameda County | MTC | MTC | Twenty-seven (27) existing guardrails on roadways in the Oakland hills. | Upgrade existing guardrails. | 549875.55 | 549846.42 | 2017-10-13 | 0 | 2020-01-08 | 2025-04-11 | 549846.42 | Authorized | Authorized | No | Closed | Federal | 0
H9-04-021 | 9 | 5012159 | 4 | Oakland | Alameda County | MTC | MTC | Foothill Blvd between Harrington Ave and Cole St, and MacArthur Blvd between 69th and 96th Ave. | Construct bulbouts, pedestrian median refuge islands, crosswalk enhancements, Rectangular Rapid Flashing Beacons (RRFBs), Speed Cushions, signs and striping | 2484284.81 | 1095930 | 2019-10-17 | 0 | 2021-12-08 | 2026-03-13 | 1095930 | Authorized | Authorized | No | Closed | Federal | 0
H9-04-022 | 9 | 5012158 | 4 | Oakland | Alameda County | MTC | MTC | Uncontrolled crosswalks along minor arterials at the following two intersections: Oakland Avenue & Moss Avenue; and 98th Avenue & C Street. | Install flashing beacons, pavement markings and signs; construct a median island, curb ramps and bulb outs. | 282300 | 250000 | 0 | 0 | 2024-08-29 | 0 | 250000 | No PE | Authorized | No | CON | Federal | 2
HSIP2-04-004 | 2 | 5012096 | 4 | Oakland | Alameda County | MTC | MTC | West Grand Ave. At Market St.; Macarthur Blvd. At Fruitvale Ave.; Market St. At 55Th St. | Install Protected Left-Turn Phase With New Left Turn Lane; Install Video And Pedestrian Detection | 254395 | 210740.81 | 0 | 0 | 2011-06-30 | 2015-10-28 | 210740.81 | No PE | Authorized | No | Closed | Federal | 0
HSIP2-04-005 | 2 | 5012097 | 4 | Oakland | Alameda County | MTC | MTC | Various Intersections | Install Count-Down Pedestrian Heads | 51296.02 | 35655.85 | 0 | 0 | 2011-07-08 | 2015-10-29 | 35655.85 | No PE | Authorized | No | Closed | Federal | 0
HSIP4-04-005 | 4 | 5012115 | 4 | Oakland | Alameda County | MTC | MTC | San Pablo Ave./West St.; San Pablo Ave./W Grand Ave. | Install protected left-turn phasing; modify intersection geometry | 602297.19 | 415800 | 2012-01-23 | 0 | 2014-02-20 | 2018-06-28 | 415800 | Authorized | Authorized | No | Closed | Federal | 0
HSIP4-04-011 | 4 | 5012114 | 4 | Oakland | Alameda County | MTC | MTC | Bancroft Ave./94th Ave. | Install traffic signals; construct curb ramps | 476845.63 | 429161.07 | 2012-01-23 | 0 | 2014-02-20 | 2018-07-02 | 429161.07 | Authorized | Authorized | No | Closed | Federal | 0
HSIP4-04-012 | 4 | 5012113 | 4 | Oakland | Alameda County | MTC | MTC | Hegenberger Rd./Edes Ave.; Hegenberger Rd./Baldwin St.; Hegenberger Rd./Hamilton St.; Hegenberger Rd./73rd Ave. | Upgrade traffic signal; install flashing beacons | 699507.14 | 613199.67 | 2012-01-25 | 0 | 2014-02-20 | 2018-07-02 | 613199.67 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-04-011 | 5 | 5012117 | 4 | Oakland | Alameda County | MTC | MTC | W. MacArthur Blvd. between Market St. and Telegraph Ave. | Modify traffic signals and striping; install protected left-turn phasing; construct left-turn lane (remove median islands) | 1280528.25 | 683559.05 | 2013-10-22 | 0 | 2015-07-07 | 2020-06-12 | 683559.05 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-04-012 | 5 | 5012118 | 4 | Oakland | Alameda County | MTC | MTC | 98th Ave. Corridor (including intersections with MacArthur Blvd., Bancroft Ave., Sunnyside St., Holly St., International Blvd., D St., E St., Medford Ave., San Leandro St., Pippin St., Walter Ave. and Edes Ave.) | Install advanced "dilemma zone" detection, crosswalks, speed feedback signs; construct bulb-outs | 725445.12 | 621091 | 2013-10-22 | 0 | 2015-08-11 | 2020-06-26 | 621091 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-04-013 | 5 | 5012119 | 4 | Oakland | Alameda County | MTC | MTC | Market St. between 45th St. and Arlington Ave. | Install bike lanes and striping; upgrade traffic signals; reconfigure intersection; construct sidewalks, curb and gutter | 1230796.26 | 606203.27 | 2013-10-22 | 0 | 2015-08-18 | 2020-01-08 | 606203.27 | Authorized | Authorized | No | Closed | Federal | 0
HSIP6-04-011 | 6 | 5012126 | 4 | Oakland | Alameda County | MTC | MTC | On Grand Ave between Park View Terrace and Euclid Ave | Upgrade crosswalks: signing, striping, pedestrian signals, bulb-outs, and raised medians | 1174104.96 | 636752.84 | 2014-08-27 | 0 | 2017-03-24 | 2021-05-20 | 636752.84 | Authorized | Authorized | No | Closed | Federal | 0
HSIP6-04-012 | 6 | 5012129 | 4 | Oakland | Alameda County | MTC | MTC | 9th St/Madison St, 8th St/Jackson St, 8th St/Madison St, 8th St/Oak St, 7th St/Madison St | Upgrade traffic signals | 1013912.56 | 606000 | 2014-09-02 | 0 | 2016-12-07 | 2020-05-13 | 606000 | Authorized | Authorized | No | Closed | Federal | 0
HSIP7-04-014 | 7 | 5012142 | 4 | Oakland | Alameda County | MTC | MTC | Telegraph Avenue corridor between 29th Street and 45th Street | Stripe and sign road diet with buffered bike lanes between 29th and 41st Sts; install signal modifications at 29th and 45th Sts; install uncontrolled crosswalk enhancements, painted bulb-outs, and painted median refuges | 1493900 | 1344510 | 2016-10-14 | 0 | 2019-10-17 | 0 | 1344510 | Authorized | Authorized | No | CON | Federal
HSIP7-04-015 | 7 | 5012141 | 4 | Oakland | Alameda County | MTC | MTC | Market Street between 4th and 7th Sts & 18 to 19 Sts; Intersections at Market St at 14, 16, 21 Sts; San Pablo Avenue at 32, Brockhurst, and 34 Sts | Stripe and sign bike improvements on Market between 4-7 Sts and 18-19 Sts; install uncontrolled crosswalk enhancements, such as RRFBs, ladder striping, raised bulb-outs, and raised median refuges at multiple locations | 2617276.97 | 1425870 | 2016-10-21 | 0 | 2019-12-20 | 2024-06-03 | 1425870 | Authorized | Authorized | No | Closed | Federal
HSIP7-04-016 | 7 | 5012140 | 4 | Oakland | Alameda County | MTC | MTC | Shattuck Avenue at 49 St, 51St, 59th St, Alactraz Ave; Claremont Avenue between Telegraph Avenue and Clifton Street | Sign and stripe road diet with bike lanes on Claremont; uncontrolled crosswalk enhancements with ladder crosswalk, RRFBs, bulb-out, and/or median refuges at multiple locations; protected left-turn at Shattuck/Alcatraz | 1523299.23 | 1258028 | 2016-12-15 | 0 | 2020-01-23 | 2022-11-23 | 1258028 | Authorized | Authorized | No | Closed | Federal
HSIP7-04-017 | 7 | 5012139 | 4 | Oakland | Alameda County | MTC | MTC | Signalized intersections in Downtown: 10th/Oak, 10th/Jackson, 10th/Harrison, 11th/Jackson, 11th/Harrison, 12th/Franklin, 12th Ped Signal, 13th/Franklin, 17th/Franklin, 19th/Franklin | Upgrade existing deficient signals for pedestrian safety to include countdown signals accessible pedestrian signals | 466887.79 | 420199 | 2016-10-14 | 0 | 2019-03-11 | 2021-07-09 | 420199 | Authorized | Authorized | No | Closed | Federal
H12-04-035 | 12 | 0 | 4 | Orinda | Contra Costa County | MTC | MTC | Five (5) stop-controlled intersections: Moraga Way and Orchard Rd; Moraga Way and Stein Way; Crestview Dr. and Richard Court and Valley View Dr; Miner Rd and Poppy Lane; and Lost Valley Dr and Valley View Dr and Don Gabriel Way. | Install flashing beacons at stop sign and flashing beacons as advance warning. | 130500 | 101250 | 0 | 0 | 0 | 0 | 0 | No PE | Due by 3/31/2028 | No | Not Started | State | 0
H12-04-036 | 12 | 0 | 4 | Orinda | Contra Costa County | MTC | MTC | Sections of Camino Pablo; Brookwood Rd; Crestview Dr; Lost Valley Dr, Miner Rd; and Orinda Wy. | Install speed warning signs, chevron signs, and rumble strips. | 174000 | 135000 | 0 | 0 | 0 | 0 | 0 | No PE | Due by 3/31/2028 | No | Not Started | State | 0
H12-04-037 | 12 | 0 | 4 | Orinda | Contra Costa County | MTC | MTC | Brookwood Rd from Moraga Wy to Spring Ct; Lost Valley Dr from Don Gabriel Wy; Orinda Wy from El Toyonal to Santa Maria Wy; and Valley View Dr from Crestview Dr to Don Gabriel Wy. | Install pedestrian crossing with enhanced safety features and rectangular rapid flashing beacons (RRFBs). | 505000 | 391680 | 0 | 0 | 0 | 0 | 0 | No PE | Due by 3/31/2028 | No | Not Started | State | 0
H12-04-038 | 12 | 0 | 4 | Orinda | Contra Costa County | MTC | MTC | All publiclly maintained streets within the City of Orinda, excluding those within the State right-of-way. | Assess and document all signs and pavement markers within the City of Orinda, excluding the limits within the State right-of-way. | 611900 | 474750 | 0 | 0 | 0 | 0 | 0 | No PE | Due by 3/31/2028 | No | Not Started | State | 0
H10-04-030 | 10 | 5350025 | 4 | Pacifica | San Mateo County | MTC | MTC | Gateway Dr. between Westcliff Ct. & Edgewood Dr.; Inverness Dr. between Hickey Blvd. & Heathcliff Dr.; Hickey Blvd between Inverness Dr. & Beachview Ave; and Glencourt Way between Inverness Dr. & Kavanaugh Way. | Install high-visibility crosswalks and ADA-compliant curb ramps. | 249200 | 249200 | 0 | 0 | 2022-02-23 | 0 | 249200 | No PE | Authorized | No | CON | State | 0
H8-04-019 | 8 | 5100029 | 4 | Palo Alto | Santa Clara County | MTC | MTC | Page Mill Road between the City Limits (Mile Marker 0.0 to Mile Marker 4.5). | Improve curve superelevations and install new guardrails along several turns. | 1925663.81 | 946169 | 0 | 0 | 2020-04-15 | 2022-04-12 | 946169 | No PE | Authorized | No | Closed | Federal | 0
HSIP2-04-002 | 2 | 5100015 | 4 | Palo Alto | Santa Clara County | MTC | MTC | San Antonio Rd. From Sr 101 To South City Limit | Reconstruct Median Channelization; Construct Curb Ramps; Upgrade Signals; Overlay And Restripe Rdwy; Lengthen Left-Turn Pockets | 1413660.48 | 851303.68 | 0 | 0 | 2011-12-27 | 2013-11-27 | 851303.68 | No PE | Authorized | No | Closed | Federal | 0
HSIP2-04-003 | 2 | 5100014 | 4 | Palo Alto | Santa Clara County | MTC | MTC | Alma St. From Colorado Ave. To City Limits At Mountain View | Remove, Replace, Repair Mbgr; Install Signs, Stripes, And Pavement Markings; Upgrade Pedestrian Facilities; Upgrade Traffic Signals; Lengthen Left-Turn Pockets; Restore Curb And Gutter | 1382756.74 | 899798.15 | 0 | 0 | 2012-03-23 | 2014-12-17 | 899798.15 | No PE | Authorized | No | Closed | Federal | 0
H12-04-039 | 12 | 5022066 | 4 | Petaluma | Sonoma County | MTC | MTC | 35 signalized intersections throughout the City of Petaluma. | Replace signal heads and install retroreflective borders to backplates, add mast arms and signal heads at intersections, and update signal timing to include leading pedestrian intervals (LPI). | 1237400 | 1113660 | 0 | 0 | 2026-02-25 | 0 | 1113660 | No PE | Authorized | No | CON | State | 0
H12-04-040 | 12 | 5022067 | 4 | Petaluma | Sonoma County | MTC | MTC | Various locations along Sonoma Mountain Parkway and Ely Road North. | Install rectangular rapid flashing beacons (RRFBs) and pedestrian refuge islands. | 387800 | 349020 | 0 | 0 | 2026-02-20 | 0 | 349020 | No PE | Authorized | No | CON | State | 0
H9-04-023 | 9 | 5022062 | 4 | Petaluma | Sonoma County | MTC | MTC | Various intersection throughout the City of Petaluma. | Install Rectangular Rapid Flashing Beacons (RRFBs) at various uncontrolled marked crosswalks. | 239970 | 239294.36 | 2019-09-06 | 0 | 2020-09-09 | 2024-03-07 | 239294.36 | Authorized | Authorized | No | Closed | Federal | 0
H9-04-024 | 9 | 5022063 | 4 | Petaluma | Sonoma County | MTC | MTC | Various intersections; and Petaluma Blvd North near Gossage Ave. | Install upgrades to signal hardware at various intersections; and install new guardrail along Petaluma Blvd North. | 226830 | 226830 | 2019-09-06 | 0 | 2020-09-09 | 2024-01-10 | 226830 | Authorized | Authorized | No | Closed | Federal | 0
HSIP2-04-006 | 2 | 5022043 | 4 | Petaluma | Sonoma County | MTC | MTC | East Washington St. And The Petaluma Ring Trail | Construct Pedestrian Crossing And Install Flashing Beacons | 409662.59 | 368696.3 | 2008-12-19 | 0 | 2010-06-17 | 2013-01-31 | 368696.3 | Authorized | Authorized | No | Closed | Federal | 0
HSIP3-04-001 | 3 | 5022047 | 4 | Petaluma | Sonoma County | MTC | MTC | 26 Signalized Intersections Within The City. | Upgrade Traffic Signals To Protected Left-Turn Only Operations; Install Signs And Stripes | 489270.7 | 439114.4 | 2010-07-16 | 0 | 2012-12-13 | 2016-03-21 | 439114.4 | Authorized | Authorized | No | Closed | Federal | 0
HSIP4-04-016 | 4 | 5022051 | 4 | Petaluma | Sonoma County | MTC | MTC | Crinella Dr./Casa Grande Rd.; Ely Blvd./Spoonbill Ave. | Install in-pavement crosswalk lights, curb ramps, signs, striping, and pavement markings | 181372.77 | 156786.52 | 2011-11-08 | 0 | 2012-11-20 | 2014-02-24 | 156786.52 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-04-014 | 5 | 5022054 | 4 | Petaluma | Sonoma County | MTC | MTC | Lakeville Hwy. (SR 116)/Pine View Way | Intersection channelization; install raised medians, signs, striping, and pavement markings | 327790.47 | 272400 | 2013-11-27 | 0 | 2018-04-03 | 2021-01-21 | 272400 | Authorized | Authorized | No | Closed | Federal | 0
H11-04-038 | 11 | 5126020 | 4 | Pinole | Contra Costa County | MTC | MTC | On San Pablo Avenue at the Third Ave. intersection and Quinan Street intersection. On Pinole Valley Road at the Savage Avenue intersection. | Install pedestrian crossing enhancements at three mid-block crossings on arterial roadways. The enhancements include continental markings, median refuge islands, advanced stop bars and Rectangular Rapid Flash Beacons. | 281133 | 250000 | ? | 0 | 0 | 0 | 30179 | Past due (due 5/31/2024) | Past due (due 3/31/2026) | Yes (PE & CON) | Not Started | State | 0
H10-04-031 | 10 | 5127039 | 4 | Pittsburg | Contra Costa County | MTC | MTC | Arterial roads - Railroad Ave, Kirker Pass Rd, Willow Pass Rd, Bailey Rd, Pittsburg-Antioch Hwy, E Leland Rd, Loveridge Rd, Buchanan Rd, W 10th St, E 10th St, Harbor St, N Parkside Dr, California Ave, Century Bl and E 14th St in the City of Pittsburg. | Complete City-wide roadway safety signing audit; install or upgrade signs with new fluorescent sheeting; and modify edge-line and centerline striping. | 2965700 | 2965700 | 2021-05-17 | 0 | 2024-06-18 | 2026-01-09 | 2965700 | Authorized | Authorized | No | Closed | State | 0
H10-04-032 | 10 | 5127040 | 4 | Pittsburg | Contra Costa County | MTC | MTC | 6 intersections: Crestview Drive and Nina Place; Crestview Drive and AltaVista Circle / Sunnyhill Way; Crestview Drive and Kingsberry Place; Crestview Drive and Atherton Avenue; Crestview Drive and William Way; Crestview Drive and Crestview Lane. | Upgrade intersection pavement markings, install raised medians and install/upgrade pedestrian crossings with enhanced safety features at various intersections along Crestview Drive. | 419400 | 378220 | 2021-05-18 | 0 | 2024-06-03 | 0 | 441350 | Authorized | Authorized | No | CON | State | 0
H12-04-041 | 12 | 5127045 | 4 | Pittsburg | Contra Costa County | MTC | MTC | Arterial Roadway of Harbor Street from Buchanan Road to East 3rd Street. | Improve signal hardware (cabinets, signal heads, signal pole, loops, backplate, controllers, backup battery systems, and camera), install light roadway segment improvements, and upgrade pedestrian crossing with enhanced safety features. | 2612700 | 2246922 | 2025-09-11 | 0 | 0 | 0 | 176300 | Authorized | Due by 3/31/2028 | No | PE | Federal | 0
H8-04-020 | 8 | 5127034 | 4 | Pittsburg | Contra Costa County | MTC | MTC | Stoneman Avenue from Harbor Street to Loveridge Road | Install pedestrian HAWK Signals, intersection striping/signage improvements, and two variable speed signs (at approaches to Stoneman Ave/Meadowbrook Ave). | 1107746.83 | 879999.97 | 2017-08-09 | 0 | 2020-07-07 | 2024-02-27 | 879999.97 | Authorized | Authorized | No | Closed | Federal | 0
H9-04-025 | 9 | 5127037 | 4 | Pittsburg | Contra Costa County | MTC | MTC | Various locations throughout the City of Pittsburg. | Improve signal hardware (signal heads, backplates, controllers, BBS, UPS, modems, cabinets, etc) and improve signal timing. | 1166933.94 | 1065600 | 2019-10-23 | 0 | 2021-09-09 | 2026-04-03 | 1065600 | Authorized | Authorized | No | Closed | Federal | 0
HSIP1-04-003 | 1 | 5127019 | 4 | Pittsburg | Contra Costa County | MTC | MTC | Power Ave., Approx. 700' West Of Andrew Ave.; Stoneman Ave At Meadowbrook Circle. | Install Pedestrian Activated Flashing Beacons; Install In-Pavement Crosswalk Lights And Associated Improvements. | 134658.99 | 108880 | 2008-05-22 | 0 | 2010-03-05 | 2013-08-01 | 108880 | Authorized | Authorized | No | Closed | Federal | 0
HSIP2-04-010 | 2 | 5127022 | 4 | Pittsburg | Contra Costa County | MTC | MTC | Willow Pass Road And Balclutha | Traffic Signal Improvement | 238696.87 | 186934.97 | 2009-03-19 | 0 | 2009-09-02 | 2012-01-18 | 186934.97 | Authorized | Authorized | No | Closed | Federal | 0
HSIP7-04-018&019&020 | 7 | 5127031 | 4 | Pittsburg | Contra Costa County | MTC | MTC | West Leland Road Corridor between Bailey Road and Montevideo Drive; Intersections of Railroad/California Ave and E. Leland/Loveridge Ave | Install dynamic/variable speed warning signs and centerline rumble strips; provide protected left turn and raised pavement markers and striping; and provide High Friction Surface Treatment | 1268061.33 | 1190618.92 | 2016-11-01 | 0 | 2019-10-23 | 2023-01-06 | 1190618.92 | Authorized | Authorized | No | Closed | Federal
HSIP1-04-007 | 1 | 5375017 | 4 | Pleasant Hill | Contra Costa County | MTC | MTC | Contra Costa Blvd. Between Taylor Blvd. And Harriet Dr. | Construct Sidewalk; Install Count Down Pedestrian Heads. | 125338 | 112804.2 | 0 | 0 | 2008-12-19 | 2012-01-18 | 112804.2 | No PE | Authorized | No | Closed | Federal | 0
HSIP2-04-019 | 2 | 5375020 | 4 | Pleasant Hill | Contra Costa County | MTC | MTC | Oak Park Blvd And Patterson Blvd | Upgrade Traffic Signal And Provide Left-Turn Lane. | 578764 | 292218.67 | 2009-04-14 | 0 | 2011-04-13 | 2013-11-05 | 292218.67 | Authorized | Authorized | No | Closed | Federal | 0
HSIP2-04-020 | 2 | 5375022 | 4 | Pleasant Hill | Contra Costa County | MTC | MTC | Pleasant Hill Road And Geary Road | Relocate Signal Pole And Construct Intersection Improvements. | 1015771.11 | 315269.91 | 2010-05-27 | 0 | 2014-07-09 | 2016-02-09 | 315269.91 | Authorized | Authorized | No | Closed | Federal | 0
HSIP3-04-013 | 3 | 5375026 | 4 | Pleasant Hill | Contra Costa County | MTC | MTC | Intersection Of Contra Costa Blvd. And Golf Club Rd. | Construct Additional Left-Turn Lane; Modify Intersection Geometry And Traffic Signals | 3171485.6 | 650000 | 0 | 0 | 2013-06-19 | 2016-04-22 | 650000 | No PE | Authorized | No | Closed | Federal | 0
HSIP4-04-018 | 4 | 5375027 | 4 | Pleasant Hill | Contra Costa County | MTC | MTC | Contra Costa Blvd./Viking Dr. | Upgrade traffic signals; install bike lanes; construct curb, gutter, sidewalks, and curb ramps; modify raised median | 3171485.6 | 532100 | 0 | 0 | 2013-07-02 | 2016-05-26 | 532100 | No PE | Authorized | No | Closed | Federal | 0
HSIP5-04-015 | 5 | 5375032 | 4 | Pleasant Hill | Contra Costa County | MTC | MTC | Contra Costa Blvd. between Harriet Dr. and Beth Dr. | Install bike lanes and safety lighting; construct sidewalks | 1153877.67 | 897048 | 0 | 0 | 2016-03-25 | 2018-10-15 | 897048 | No PE | Authorized | No | Closed | Federal | 0
H10-04-033 | 10 | 0 | 4 | Pleasanton | Alameda County | MTC | MTC | Various overcrossing on/off ramp locations along Interstate 580 between Hopyard Road, Hacienda Drive, and Santa Rita Road. | Install Rectangular Rapid Flashing Beacons and improve striping and pavement markings. | 321200 | 250000 | 0 | 0 | 0 | 0 | 0 | No PE | Past due (due 9/30/2024) | Yes (CON) | Not Started | State | 0
H11-04-039 | 11 | 5137059 | 4 | Richmond | Contra Costa County | MTC | MTC | Various intersections along MacDonald Avenue (15th Street and Nicholl Park). | Install Rectangular Rapid Flashing Beacons (RRFBs), curb extensions (bulb-outs), and added yield markings. Other safety measures include the installation of median refuge islands and red curb. | 371380 | 269568 | 2025-01-27 | 0 | 2025-08-26 | 0 | 269568 | Authorized | Authorized | No | CON | State | 0
H11-04-040 | 11 | 5137060 | 4 | Richmond | Contra Costa County | MTC | MTC | Barrett Avenue from Harbour Way to 24th Street. | Road diet including protected bike lanes, sidewalk widening, high visibility crosswalk enhancements, protected left-turn phasing, advanced stop bars, median refuge islands, and Rectangular Rapid Flashing Beacons (RRFBs). | 1563200 | 1406880 | 2025-01-27 | 0 | 0 | 0 | 251280 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE | State | 0
HSIP6-04-013 | 6 | 5137048 | 4 | Richmond | Contra Costa County | MTC | MTC | On 37th St between Cerrito Ave and Center Ave | Install bike lanes and pedestrian countdown head; Upgrade traffic signals; Road diet (reduce travel lanes) ; Install 12 ADA-Compliant Curb Ramps and 4 Bulb-outs | 925777.4 | 286600 | 0 | 0 | 2018-03-15 | 2025-02-28 | 286600 | No PE | Authorized | No | Closed | Federal | 0
H10-04-034 | 10 | 5099016 | 4 | Rio Vista | Solano County | MTC | MTC | Various non-signalized locations throughout the City of Rio Vista | Install high-visibility crosswalks, striping, advance warning signs, and ADA ramps. | 250000 | 250000 | 2021-12-21 | 0 | 2023-07-10 | 2024-07-16 | 250000 | Authorized | Authorized | No | Closed | State | 0
H11-04-041 | 11 | 5099018 | 4 | Rio Vista | Solano County | MTC | MTC | Norman Richards Drive from Airport Road to Poppy House Road; Airport Road from Norman Richards Drive to ASTA Minerals Driveway. | Construct Class IV bike facilities on Airport Road and Class II bike facilities on Norman Richards Drive which include new signing, striping, pavement markings and barriers. | 276900 | 249210 | 2023-11-13 | 0 | 0 | 0 | 20700 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE | State | 0
H11-04-042 | 11 | 5099019 | 4 | Rio Vista | Solano County | MTC | MTC | Three pedestrian crossings: Airport Road and Church Road; Airport Road and Norman Richard Drive; N Front Street and SR-84. | Install RRFBs and other standard crossing treatments including signing, striping and curb enhancements. | 268700 | 241830 | 2023-11-13 | 0 | 0 | 0 | 20430 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE | State | 0
H9-04-026 | 9 | 5099015 | 4 | Rio Vista | Solano County | MTC | MTC | Four (4) pedestrian crossings at the following intersections: S 2nd and Marina Dr (Riverview Junior High); DH White Elementary School and Thereza Way; DH White Elementary School and Laurel Way; and S 7th St and Main St. | Enhance pedestrian crossings by the addition of ADA curb ramp, curb extensions, advance yield signs and lines, Rectangular Rapid Flashing Beacons (RRFBs) and other relevant elements. | 228395.5 | 228395.5 | 2019-10-18 | 0 | 2021-11-18 | 2023-05-02 | 228395.5 | Authorized | Authorized | No | Closed | Federal | 0
H10-04-035 | 10 | 5379023 | 4 | Rohnert Park | Sonoma County | MTC | MTC | 40 Signalized intersections throughout the City of Rohnert Park. | Upgrade signal hardware (12" vehicle heads, reflective yellow tape,countdown pedestrian signal heads, accessible pedestrian signals), upgrade detection and emergency preemption equipment, update controllers, and add battery backup system. | 1712600 | 1712600 | 2021-07-30 | 0 | 2023-06-01 | 2026-01-20 | 1712600 | Authorized | Authorized | No | Closed | State | 0
HSIP3-04-002 | 3 | 5176006 | 4 | Ross | Marin County | MTC | MTC | Intersection Of Sir Francis Drake Blvd. And Lagunitas Rd. | Remove Corner Pedestrian Islands And Reconfigure Right Turning Lanes; Construct New Curbs, Sidewalks, Curb Ramps And Crosswalks; Upgrade Traffic And Pedestrian Signals; Install New Traffic Signs And Pavement Markings | 967439.73 | 442899.39 | 2011-01-04 | 0 | 2013-06-19 | 2016-03-08 | 442899.39 | Authorized | Authorized | No | Closed | Federal | 0
H12-04-042 | 12 | 5226027 | 4 | San Bruno | San Mateo County | MTC | MTC | Three unsignalized intersections along the San Bruno Avenue West corridor, between El Camino Real and Seventh Avenue. | Install rectangular rapid flashing beacons (RRFBs) at two intersections; install crosswalk striping/signage improvements at two intersections. | 349100 | 314190 | 2025-06-30 | 0 | 0 | 0 | 41400 | Authorized | Due by 3/31/2028 | No | PE | State | 0
HSIP3-04-014 | 3 | 5267017 | 4 | San Carlos | San Mateo County | MTC | MTC | Intersection Of El Camino Real And Belmont Ave. | Relocate Crosswalk And Bus Pad; Install Pedestrian Activated Overhead Flashing Beacon; Construct Pedestrian Refuge Area; Install Signs, Stripes And Crosswalk Pavement Markings | 241895.31 | 198000 | 2011-07-21 | 0 | 2012-06-01 | 2015-01-06 | 198000 | Authorized | Authorized | No | Closed | Federal | 0
H10-04-036 | 10 | 6328099 | 4 | San Francisco | San Francisco County | MTC | MTC | Up to 175 signalized intersections throughout San Francisco. | Enhance pedestrian safety by retiming to add leading pedestrian intervals. Where possible, update signal timing to set pedestrian clearance times using a 3 feet per second walking speed. | 2000000 | 2000000 | 2021-06-02 | 0 | 2023-02-07 | 2026-02-20 | 2000000 | Authorized | Authorized | No | Closed | State | 0
H11-04-043 | 11 | 6328110 | 4 | San Francisco | San Francisco County | MTC | MTC | Various intersections and streets throughout the entire City and County of San Francisco. | Enhance traffic and pedestrian safety by installing new and replacement signs with retro-reflectivity. | 2188400 | 1969560 | 0 | 0 | 2024-06-17 | 0 | 1969560 | No PE | Authorized | No | CON | Federal | 2
H12-04-043 | 12 | 6328129 | 4 | San Francisco | San Francisco County | MTC | MTC | Various locations. | Install new and replace existing signs (e.g., No Turn on Red, Speed Limit near schools, “Slow—School Xing”, and Yield/Ped Signs) to feature advanced high-visibility fluorescent sheeting. | 4412400 | 3971160 | 2025-09-11 | 0 | 0 | 0 | 54000 | Authorized | Due by 3/31/2028 | No | PE | Federal | 2
HSIP1-04-013 | 1 | 5934141 | 4 | San Francisco County | San Francisco County | MTC | MTC | Various Locations: Twin Peaks Blvd; O'Shaughnessy Blvd At Del Valle Ave; Portola Dr. North Of Burnett Ave. And West Of Burnett Ave. | Upgrade Guardrails And Install End Treatments. | 262136 | 235922.51 | 0 | 0 | 2008-03-02 | 2009-06-16 | 235922.51 | No PE | Authorized | No | Closed | Federal | 0
HSIP5-04-016A | 5 | 5934167 | 4 | San Francisco County | San Francisco County | MTC | MTC | Sloat Blvd. (SR 35)/Everglade Dr.; Sloat Blvd./23rd Ave. | Construct bulb-outs and curb ramps; install medians and flashing beacons | 919684.28 | 488421.69 | 2013-04-17 | 0 | 2014-11-26 | 2018-05-04 | 488421.69 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-04-016B | 5 | 5934170 | 4 | San Francisco County | San Francisco County | MTC | MTC | Sloat Blvd. (SR 35)/Forest View Dr. | Construct bulb-outs and curb ramps; install medians and flashing beacons | 1180505.71 | 301000 | 0 | 0 | 2013-07-18 | 2014-09-02 | 301000 | No PE | Authorized | No | Closed | Federal | 0
HSIP2-04-029 | 2 | 6328026 | 4 | San Francisco Municipal Transportation Agency (SFMTA) | San Francisco County | MTC | MTC | Fulton St. Between 8Th Ave And 25Th Ave. | Reconstruct Curb Ramps. | 105443.76 | 85468.89 | 2013-03-22 | 0 | 2013-03-22 | 2015-01-06 | 85468.89 | Authorized | Authorized | No | Closed | Federal | 0
HSIP2-04-030 | 2 | 6328028 | 4 | San Francisco Municipal Transportation Agency (SFMTA) | San Francisco County | MTC | MTC | Various Locations In The Tenderloin Area | Install Emergency Vehicle Priority System At Existing Traffic Signals | 850000 | 765000 | 0 | 0 | 2009-09-01 | 2013-09-06 | 765000 | No PE | Authorized | No | Closed | Federal | 0
HSIP2-04-031 | 2 | 6328031 | 4 | San Francisco Municipal Transportation Agency (SFMTA) | San Francisco County | MTC | MTC | Bayshore Blvd. And Paul Ave. Intersection | Upgrade Traffic Signal | 485798.82 | 305171.58 | 2009-08-25 | 0 | 2012-09-18 | 2016-10-20 | 305171.58 | Authorized | Authorized | No | Closed | Federal | 0
HSIP3-04-011 | 3 | 6328039 | 4 | San Francisco Municipal Transportation Agency (SFMTA) | San Francisco County | MTC | MTC | Sunset Blvd. At Its Intersections With Kirkham St., Santiago St., And Ulloa St. | Install Traffic Signals; Construct Curb Ramps; Install Signs And Stripes | 803879.1 | 723489.24 | 2010-11-22 | 0 | 2012-11-19 | 2015-11-06 | 723489.24 | Authorized | Authorized | No | Closed | Federal | 0
HSIP3-04-015 | 3 | 6328041 | 4 | San Francisco Municipal Transportation Agency (SFMTA) | San Francisco County | MTC | MTC | Intersections around San Francisco MUNI T-line Light-Rail Corridor - 3rd St. and Bayshore Blvd., from King St. to Geneva Ave. plus additional locations citywide | Replace Rail Traffic Signal Heads; Remove And/Or Modify Adjacent Vehicle Traffic Signals, Install Pavement Markings And Traffic Signs | 363064.87 | 326641.77 | 0 | 0 | 2013-08-15 | 2017-05-15 | 326641.77 | No PE | Authorized | No | Closed | Federal | 0
HSIP4-04-006 | 4 | 6328047 | 4 | San Francisco Municipal Transportation Agency (SFMTA) | San Francisco County | MTC | MTC | Various locations throughout the city | Install advance yield lines, warning signs, crosswalks, and No Parking zones | 407712.72 | 366085.85 | 2011-11-16 | 0 | 2014-09-18 | 2018-01-05 | 366085.85 | Authorized | Authorized | No | Closed | Federal | 0
HSIP4-04-019 | 4 | 6328048 | 4 | San Francisco Municipal Transportation Agency (SFMTA) | San Francisco County | MTC | MTC | Masonic Ave. between Geary Blvd. and Fell St. | Upgrade traffic signals (includes controllers and cabinets, mast arms, transit signal priority, pedestrian countdown heads, and larger signal heads) | 963300.91 | 763957.82 | 2011-11-16 | 0 | 2014-04-16 | 2017-02-02 | 763957.82 | Authorized | Authorized | No | Closed | Federal | 0
HSIP6-04-014 | 6 | 6328069 | 4 | San Francisco Municipal Transportation Agency (SFMTA) | San Francisco County | MTC | MTC | 7 instersections various locations on S Van Ness Ave | Upgrade traffic signals; Install pedestrian countdown heads; Construct curb ramps | 1767287.52 | 1391825.17 | 2014-06-08 | 0 | 2016-03-04 | 2020-03-26 | 1391825.17 | Authorized | Authorized | No | Closed | Federal | 0
HSIP6-04-015 | 6 | 6328068 | 4 | San Francisco Municipal Transportation Agency (SFMTA) | San Francisco County | MTC | MTC | 9 intersections various locations on Polk St | Upgrade traffic signals; install curb ramps and pedestrian countdown heads | 1606602.98 | 1373677.28 | 2014-04-27 | 0 | 2015-06-26 | 2020-10-22 | 1373677.28 | Authorized | Authorized | No | Closed | Federal | 0
HSIP7-04-021 | 7 | 6328080 | 4 | San Francisco Municipal Transportation Agency (SFMTA) | San Francisco County | MTC | MTC | Up to 345 intersections at various locations in the northeast quadrant of San Francisco. | The project will retime up to 345 traffic signals in the northeast quadrant of San Francisco, which includes 251 intersections in the North of Market (NOMA) area and 94 intersections in the South of Market (SOMA) area | 3803930.75 | 3741900 | 2016-07-08 | 0 | 0 | 2021-04-15 | 3741900 | Authorized | No CON | No | Closed | Federal
H10-04-037 | 10 | 5005170 | 4 | San Jose | Santa Clara County | MTC | MTC | I-280 SB Offramp & Moorpark Av. | Upgrade existing traffic signal from pedestal-mounted to mast-arm mounted; refresh striping, and add additional signal heads. | 402845 | 324200 | 0 | 0 | 2022-01-07 | 2024-12-10 | 324200 | No PE | Authorized | No | Closed | State | 0
H11-04-044 | 11 | 5005181 | 4 | San Jose | Santa Clara County | MTC | MTC | The intersections of: Park Avenue & Race Street, Auzerais Avenue & Race Street, and Blossom Ave & Calero Ave. | Upgrade the existing traffic signal, add protected left turns on the north and south approaches to Blossom & Calero and Auzerais & Race, and all four approaches of Park & Race. | 201600 | 181440 | 0 | 0 | 2024-11-15 | 0 | 181440 | No PE | Authorized | No | CON | State | 0
H11-04-045 | 11 | 5005182 | 4 | San Jose | Santa Clara County | MTC | MTC | Ninety-Eight (98) signalized intersections along the corridors of Brokaw Rd/Murphy Ave/Hostetter Rd, First St, King Rd/Lundy Ave, Meridian Ave, Santa Teresa Blvd, and Snell Ave. | Upgrade 8-inch traffic signal heads to 12-inch heads, apply retroreflective borders on traffic signal backplates, and install Accessible Pedestrian Signal hardware at signalized pedestrian crossings. | 1325700 | 1193130 | 0 | 0 | 2024-10-30 | 0 | 1193130 | No PE | Authorized | No | CON | State | 0
H11-04-046 | 11 | 5005176 | 4 | San Jose | Santa Clara County | MTC | MTC | Along Ocala Avenue between Everwood Court and Hillmont Avenue. | Construct a raised median island to replace the existing two-way left turn lane. | 501500 | 451350 | 2023-12-18 | 0 | 0 | 0 | 80460 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE | State | 0
H12-04-044 | 12 | 0 | 4 | San Jose | Santa Clara County | MTC | MTC | 52 signalized intersections along the corridors of Capitol Ave, First Street, Curtner, Camden Ave, Branham Ln, Barack Obama Bl, Moorpark Ave, Park Ave, McLaughlin Ave, Quimby Rd, and Tully Rd. | Upgrade 8 inch diameter traffic signal heads to 12 inch heads, apply retroreflective borders on traffic signal backplates, and install accessible pedestrian signal hardware. | 566300 | 509670 | 0 | 0 | 0 | 0 | 0 | No PE | Due by 3/31/2028 | No | Not Started | State | 0
H8-04-021 | 8 | 5005149 | 4 | San Jose | Santa Clara County | MTC | MTC | Senter Road between Story Road/Keyes Street and Singleton Road. | Install buffered bike lanes, a raised median island, and general improvements to enhance safety, visibility, and calm vehicle speeds along the corridor. | 3271329.1 | 2804629.46 | 2017-11-17 | 0 | 2020-01-08 | 2023-01-23 | 2804629.46 | Authorized | Authorized | No | Closed | Federal | 0
H8-04-022 | 8 | 5005150 | 4 | San Jose | Santa Clara County | MTC | MTC | White Road between Penitencia Creek Road and Rose Avenue. | Install buffered bike lanes, enhanced crosswalks, flashing beacons, additional streetlights, and general improvements to enhance safety, visibility, and calm vehicle speeds along the corridor. | 1214329.17 | 1068019.81 | 2017-10-18 | 0 | 2020-01-02 | 2023-02-24 | 1068019.81 | Authorized | Authorized | No | Closed | Federal | 0
H9-04-027 | 9 | 5005165 | 4 | San Jose | Santa Clara County | MTC | MTC | Monterey Road from Cottle Road to Metcalf Road | Upgrade guardrails that are damaged and not up to current standards. | 2097000.13 | 1000000 | 0 | 0 | 2022-02-10 | 2026-01-08 | 1000000 | No PE | Authorized | No | Closed | Federal | 0
HSIP5-04-017 | 5 | 5005123 | 4 | San Jose | Santa Clara County | MTC | MTC | North First St. between the bike path adjoining SR 237 and Brokaw Rd. | Install tubular markers (to demarcate bike lanes), green pavement surface treatment (to enhance bike lane visibility), pavement markings (stop bars and bike boxes) | 928149.02 | 798055.3 | 2013-10-22 | 0 | 2015-04-15 | 2020-03-24 | 798055.3 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-04-018 | 5 | 5005121 | 4 | San Jose | Santa Clara County | MTC | MTC | Park Ave. between Hedding St. and South Market St. | Install tubular markers (to demarcate bike lanes), pavement surface treatment (to enhance bike lane visibility), sharrows, pavement markings (stop bars and bike boxes) | 413226.67 | 371331.06 | 2013-08-11 | 0 | 2016-06-14 | 2019-06-14 | 371331.06 | Authorized | Authorized | No | Closed | Federal | 0
HSIP6-04-016 | 6 | 5005135 | 4 | San Jose | Santa Clara County | MTC | MTC | On Ocala Ave between Daytona Dr and E Capitol Expressway | Install traffic signals; Construct sidewalk and raised median | 2091159.61 | 1061342.7 | 2014-05-05 | 0 | 2016-04-11 | 2019-06-12 | 1061342.7 | Authorized | Authorized | No | Closed | Federal | 0
HSIP7-04-022 | 7 | 5005157 | 4 | San Jose | Santa Clara County | MTC | MTC | On McLaughlin Avenue between Interstate 280 and Capitol Expressway. | Install flashing beacons, bulb-outs, enhanced crosswalks, median island, additional streetlights, and general improvements | 2221730.07 | 1997401.36 | 0 | 0 | 2019-12-20 | 2023-01-06 | 1997401.36 | No PE | Authorized | No | Closed | Federal
H12-04-045 | 12 | 5041053 | 4 | San Leandro | Alameda County | MTC | MTC | (1) Manor Blvd/Crosby St, (2) Manor Blvd/Thoits St, (3) Dutton Ave/Arbor Dr, (4) Farnsworth St/Devonshire Ave, (5) 150th Ave/Lark St, (6) E. 14th St/Lorraine Dr, and (7) Farnsworth St/Chapel Ave. | Install rectangular rapid flashing beacons (RRFBs), pedestrian hybrid beacons, and crosswalk enhancements. | 2038400 | 1834560 | 2025-08-13 | 0 | 0 | 0 | 339570 | Authorized | Due by 3/31/2028 | No | PE | Federal | 2
H8-04-023 | 8 | 5041046 | 4 | San Leandro | Alameda County | MTC | MTC | The intersection of East 14th Street (SR 185) and Joaquin Avenue. | Upgrade the existing aged traffic signal equipment, including adding a scramble pedestrian crosswalk with a dedicated pedestrian signal phase, adding accessible pedestrian signals, and improving signing, striping, and curb ramps. | 544213.6 | 335250 | 2017-10-13 | 0 | 2020-06-25 | 2024-08-21 | 335250 | Authorized | Authorized | No | Closed | Federal | 0
H9-04-028 | 9 | 5041049 | 4 | San Leandro | Alameda County | MTC | MTC | The intersection of Wicks Blvd and Manor Blvd. | Install southbound and northbound left-turn signals; Upgrade signal heads and signal equipment; Install video detections for cars and bikes and advance detection; Install Accessible Pedestrian Signal (APS); Upgrade wheelchair Ramps. | 1280741 | 459900 | 2019-09-06 | 0 | 2022-07-28 | 0 | 459900 | Authorized | Authorized | No | CON | Federal | 0
HSIP1-04-001 | 1 | 5041031 | 4 | San Leandro | Alameda County | MTC | MTC | Intersection Of Washington Ave And Estabrook St. | Install Traffic Signals With Interconnect; Remove Pork Chop Island; Relocate Utility Pole; Install Curb Ramps. | 455628.39 | 409130 | 2008-03-02 | 0 | 2009-04-14 | 2012-03-28 | 409130 | Authorized | Authorized | No | Closed | Federal | 0
HSIP4-04-015 | 4 | 5041041 | 4 | San Leandro | Alameda County | MTC | MTC | Washington Ave./Monterey Blvd. (Bradrick Dr.) | Install protected left-turn phasing; upgrade traffic signals, signs and pavement markings | 404853.63 | 322367.39 | 2011-12-15 | 0 | 2014-04-14 | 2018-01-11 | 322367.39 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-04-019 | 5 | 5041042 | 4 | San Leandro | Alameda County | MTC | MTC | Bancroft Ave./Sybil Ave. | Upgrade traffic signals; install protected left-turn phasing; construct sidewalks, curb ramps, curb and gutter | 552041.64 | 448800 | 2013-07-16 | 0 | 2016-11-29 | 2019-07-08 | 448800 | Authorized | Authorized | No | Closed | Federal | 0
HSIP7-04-003 | 7 | 5041045 | 4 | San Leandro | Alameda County | MTC | MTC | The intersection of Davis Street with Carpentier Street | Install pedestrian activated or HAWK signal, accessible pedestrian signal equipment; improve street lighting features and signing & striping for crosswalks; and upgrade disabled curb ramps | 261050 | 254404.99 | 2017-04-21 | 0 | 2019-10-17 | 2023-03-27 | 254404.99 | Authorized | Authorized | No | Closed | Federal
H10-04-038 | 10 | 5935086 | 4 | San Mateo County | San Mateo County | MTC | MTC | Bunker Hill Drive: From Brandywine Way to Yorktown Drive - Highlands Elementary Avenue Alhambra: From Coronado Street to The Alameda - Wilkinson School | Improve two existing mid-block crosswalks. Locations to have high visibility ladder crossing, concrete bulb- outs, ADA ramps, rapid rectangular flashing beacons, speed reduction and advance pavement markings and signs. | 246500 | 246500 | 2021-04-22 | 0 | 2023-03-07 | 0 | 246500 | Authorized | Authorized | No | CON | State | 0
H12-04-046 | 12 | 5935094 | 4 | San Mateo County | San Mateo County | MTC | MTC | Various locations. | Construct 11 guardrails and 22 end treatments. | 1077500 | 969750 | 2025-11-28 | 0 | 0 | 0 | 99990 | Authorized | Due by 3/31/2028 | No | PE | Federal | 1
H12-04-047 | 12 | 5935093 | 4 | San Mateo County | San Mateo County | MTC | MTC | Various locations. | Construct edgeline for 16.5 miles of roadway. | 389800 | 350000 | 2025-09-17 | 0 | 0 | 0 | 36390 | Authorized | Due by 3/31/2028 | No | PE | State | 0
H9-04-029 | 9 | 5303020 | 4 | San Pablo | Contra Costa County | MTC | MTC | The Intersections of Church Lane and Willow Road and El Portal Drive and Mission Bell Road. | Install pedestrian crossing enhancements and illumination. | 934395.72 | 837153.2 | 2019-10-23 | 0 | 2021-12-09 | 2025-05-09 | 837153.2 | Authorized | Authorized | No | Closed | Federal | 0
H11-04-047 | 11 | 5043046 | 4 | San Rafael | Marin County | MTC | MTC | Lincoln Avenue at Brookdale Avenue and Wilson Court. | Add intersection safety improvements - install curb extensions and Rectangular Rapid Flashing Beacons (RRFBs). | 277700 | 250000 | 2024-03-22 | 0 | 2025-09-08 | 0 | 217483 | Authorized | Authorized | No | CON | State | 0
H12-04-048 | 12 | 5043050 | 4 | San Rafael | Marin County | MTC | MTC | The Lincoln Avenue corridor between Second Street and Paloma Avenue, including eight (8) intersections. | Install protected left turn lane striping and signal phases, add intersection safety improvements with traffic signal upgrades, intersection lighting, rectangular rapid flashing beacons (RRFBs), and pedestrian crossing upgrades. | 2839900 | 2555910 | 2025-12-17 | 0 | 0 | 0 | 180000 | Authorized | Due by 3/31/2028 | No | PE | Federal | 0
H8-04-025 | 8 | 5043040 | 4 | San Rafael | Marin County | MTC | MTC | The intersection of Third Street and Hetherton Street. | Install ADA compliant curb ramp; remove the existing crosswalk on the south leg & install a new crosswalk on the east leg; install new traffic signal poles and conduit; install roadway signage; change traffic signal timing. | 550972.99 | 531486.46 | 2017-05-01 | 0 | 2019-12-03 | 2021-05-06 | 531486.46 | Authorized | Authorized | No | Closed | Federal | 0
H9-04-030 | 9 | 5043043 | 4 | San Rafael | Marin County | MTC | MTC | Five (5) signalized intersections of Third Street at Lindaro Street, Lincoln Avenue, Tamalpais Avenue, Irwin Street and Grand Street. | Construct high-visibility crosswalks, install advanced stop bars, and install pedestrian countdown signals at five intersections; and add signal mast arms at three locations. | 2853655.51 | 1574993.48 | 2019-04-03 | 0 | 2022-02-10 | 2026-01-08 | 1574993.48 | Authorized | Authorized | No | Closed | Federal | 0
HSIP6-04-017 | 6 | 5043037 | 4 | San Rafael | Marin County | MTC | MTC | S Grand Ave/W 2nd St | Upgrade traffic signals, including: signal hardware, widen sidewalk, construct curb ramps and other safety improvements | 1060658.84 | 499906.95 | 2014-07-29 | 0 | 2017-04-21 | 2018-10-15 | 499906.95 | Authorized | Authorized | No | Closed | Federal | 0
HSIP1-04-011 | 1 | 5437016 | 4 | San Ramon | Contra Costa County | MTC | MTC | 4 Intersections With San Ramon Blvd: Montevideo Dr., Westside Dr., Talavera Dr., Woodborough Way. | Modify Existing Median; Install Refuge Lane; Extend Left-Turn Lane. | 507022.12 | 456319.9 | 2007-10-29 | 0 | 2008-04-27 | 2010-12-28 | 456319.9 | Authorized | Authorized | No | Closed | Federal | 0
HSIP2-04-021 | 2 | 5437021 | 4 | San Ramon | Contra Costa County | MTC | MTC | Alcosta Blvd And Davona Dr. Intersection | Upgrade Traffic Signal | 269654.77 | 238639.29 | 2009-08-25 | 0 | 2011-06-22 | 2022-04-26 | 238639.29 | Authorized | Authorized | No | Closed | Federal | 0
HSIP3-04-016 | 3 | 5437023 | 4 | San Ramon | Contra Costa County | MTC | MTC | Bollinger Canyon Rd. Between Canyon Lakes Dr. And Dougherty Rd. | Install Pedestrian Signal Improvements; Upgrade Signal Controller And Phasing | 344483.88 | 304607.49 | 0 | 0 | 2014-07-03 | 2016-10-20 | 304607.49 | No PE | Authorized | No | Closed | Federal | 0
HSIP3-04-017 | 3 | 5019026 | 4 | Santa Clara | Santa Clara County | MTC | MTC | Intersection Of Pomeroy Ave. And Benton St. | Upgrade Traffic Signal With Protected Left Turn Phasing, Interconnect, And Emergency Vehicle Preemption; Add Left-Turn Pockets; Install Bulb-Outs; Construct Curb, Gutter, Sidewalk, Curb Ramps | 711302.78 | 550050.03 | 0 | 0 | 2012-05-02 | 2016-04-27 | 550050.03 | No PE | Authorized | No | Closed | Federal | 0
H10-04-039 | 10 | 5937226 | 4 | Santa Clara County | Santa Clara County | MTC | MTC | Foothill Expressway, Lawrence Expressway, and San Tomas Expressway. | Replace existing metal beam guardrail end treatments with modern variants and increase heights to meet current standards. | 999200 | 999200 | 2022-01-27 | 0 | 0 | 0 | 175000 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE | State | 0
HRRR1-04-032 | 1 | 5937113 | 4 | Santa Clara County | Santa Clara County | MTC | MTC | Hicks Road from Shannon Road to Alamitos Road | Upgrade Guardrail (include new guardrail) | 194566.16 | 149861.59 | 2007-10-12 | 0 | 2009-03-19 | 2011-12-06 | 149861.59 | Authorized | Authorized | No | Closed | Federal | 0
HRRR1-04-033 | 1 | 5937114 | 4 | Santa Clara County | Santa Clara County | MTC | MTC | Sierra Rd. from Felter Rd. to 4.3 miles Southwest of Felter Rd. | Widen or Improve Shoulder | 789821.58 | 675808.69 | 2007-10-11 | 0 | 2010-01-12 | 2012-02-28 | 675808.69 | Authorized | Authorized | No | Closed | Federal | 0
HRRR2-04-034 | 2 | 5937129 | 4 | Santa Clara County | Santa Clara County | MTC | MTC | Felter Road between Calaveras Road and Sierra Road | Widen shoulders at spot locations; install guardrail, signs, stripes and pavement markers | 426280.45 | 304798.04 | 2009-04-03 | 0 | 2011-11-04 | 2013-11-15 | 304798.04 | Authorized | Authorized | No | Closed | Federal | 0
HSIP1-04-014 | 1 | 5937117 | 4 | Santa Clara County | Santa Clara County | MTC | MTC | Capital Expressway From Hwy 680 To Hwy 87. | Upgrade Traffic Control Signs, Pavement Markings And Delineation. | 248576.22 | 181396.4 | 2007-12-07 | 0 | 2009-01-12 | 2012-01-18 | 181396.4 | Authorized | Authorized | No | Closed | Federal | 0
HSIP1-04-015 | 1 | 5937118 | 4 | Santa Clara County | Santa Clara County | MTC | MTC | Quimby Rd From Deedham Dr. To Mt. Hamilton Rd (Sr130). | Install And Upgrade Metal Beam Guardrail; Upgrade Signing And Striping. | 204130.83 | 126949.49 | 2007-12-18 | 0 | 2009-03-30 | 2011-12-06 | 126949.49 | Authorized | Authorized | No | Closed | Federal | 0
HSIP2-04-028 | 2 | 5937138 | 4 | Santa Clara County | Santa Clara County | MTC | MTC | Black Rd. From Sr 17 To Skyline Blvd. | Construct Shoulder Improvement; Install Mbgr; Upgrade Striping And Signage | 534409.24 | 446808.46 | 2009-12-16 | 0 | 2011-11-04 | 2013-10-24 | 446808.46 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-04-021 | 5 | 5937190 | 4 | Santa Clara County | Santa Clara County | MTC | MTC | Uvas Rd. (County Road G8) from Croy Rd. to 0.7 miles N of Casa Loma Rd. | Widen shoulders; install guardrail | 1344314.93 | 855335.63 | 2013-09-13 | 0 | 2016-05-06 | 2019-04-19 | 855335.63 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-04-022 | 5 | 5937188 | 4 | Santa Clara County | Santa Clara County | MTC | MTC | Stevens Canyon Rd. from Mt. Eden Rd. to 0.68 miles S of Ricardo Rd. | Widen and pave shoulders; install guardrail | 800653.78 | 643020.16 | 2013-09-13 | 0 | 2016-10-31 | 2018-12-14 | 643020.16 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-04-023 | 5 | 5937189 | 4 | Santa Clara County | Santa Clara County | MTC | MTC | Clayton Rd. from 0.52 miles E of Fall Ave. to Mt. Hamilton Rd. (SR 130) | Widen shoulders | 570556.31 | 370795.84 | 2013-09-13 | 0 | 2016-09-06 | 2018-12-14 | 370795.84 | Authorized | Authorized | No | Closed | Federal | 0
HSIP6-04-018 | 6 | 5937199 | 4 | Santa Clara County | Santa Clara County | MTC | MTC | On Watsonville Rd between Uvas Rd and approx 0.18 miles south of Santa Teresa Blvd | Widen and pave shoulders | 1085582.87 | 872461.69 | 2014-08-20 | 0 | 2016-04-27 | 2019-05-09 | 872461.69 | Authorized | Authorized | No | Closed | Federal | 0
HSIP6-04-019 | 6 | 6264063 | 4 | Santa Clara Valley Transportation Authority | Santa Clara County | MTC | MTC | On Capitol Expressway between Eastridge Loop and Tully Rd, Capitol Expressway/Eastridge Loop | Install sidewalk, crosswalk and a median fence; upgrade traffic signal | 1231779.84 | 1027346.71 | 2014-08-20 | 0 | 2016-11-18 | 2018-12-14 | 1027346.71 | Authorized | Authorized | No | Closed | Federal | 0
H8-04-026 | 8 | 5028078 | 4 | Santa Rosa | Sonoma County | MTC | MTC | Thirty nine (39) signalized intersections. | Retrofit and upgrade thirty nine (39) Protected/Permissive signalized intersections with Flashing Yellow Left Turn Arrow displays to meet the current MUTCD/CAMUTCD Standards. | 629633.18 | 629633.18 | 2017-08-14 | 0 | 2019-05-08 | 2022-06-15 | 629633.18 | Authorized | Authorized | No | Closed | Federal | 0
HSIP2-04-008 | 2 | 5028059 | 4 | Santa Rosa | Sonoma County | MTC | MTC | Sonoma Ave Between Santa Rosa Ave And Hahman Dr. and Hahman Dr. from Sonoma Ave. to Montgomery Dr. | Reconfigure Roadways For Bike Lanes. | 403280 | 272118.3 | 0 | 0 | 2011-06-13 | 2012-10-25 | 272118.3 | No PE | Authorized | No | Closed | Federal | 0
HSIP6-04-020 | 6 | 5028073 | 4 | Santa Rosa | Sonoma County | MTC | MTC | 114 intersections throughout the City of Santa Rosa | Install crosswalks, signs, markings, and Rectangular Rapid Flashing Beacons (RRFB), Construct pedestrian refuge islands and curb ramps | 980689.97 | 790410.98 | 2014-03-14 | 0 | 2017-02-07 | 2019-06-17 | 790410.98 | Authorized | Authorized | No | Closed | Federal | 0
HSIP1-04-006 | 1 | 5332011 | 4 | Saratoga | Santa Clara County | MTC | MTC | Saratoga-Los Gatos Rd (Sr 9) Between Big Basin Way In Saratoga And Los Gatos Blvd In Los Gatos | Construct Sidewalks And Curb Ramps; Relocate Utility Pole; Signing And Striping; Construct Ped/Bike Bridge. | 1062430.22 | 899720.99 | 2008-03-31 | 0 | 2012-05-11 | 2016-03-04 | 899720.99 | Authorized | Authorized | No | Closed | Federal | 0
HSIP4-04-004 | 4 | 5332021 | 4 | Saratoga | Santa Clara County | MTC | MTC | SR 9 (Saratoga-Los Gatos Rd.) between Fruitvale Ave. and Lexington Dr. | Construct pedestrian pathway, curbs, and curb ramps; install crosswalks, signs, and striping | 1032777.53 | 899999.78 | 0 | 0 | 2016-03-24 | 2019-06-14 | 899999.78 | No PE | Authorized | No | Closed | Federal | 0
H11-04-048 | 11 | 5123019 | 4 | Sebastopol | Sonoma County | MTC | MTC | Bodega Ave, from approximately 50' east of existing bridge crossing over Atascadero Creek to Valley View Drive | Remove a short section of metal beam guardrail, install new Midwest Guardrail System, minor shoulder work, re-stripe paved surface, add new warning signage. | 347000 | 312300 | 2024-03-04 | 0 | 0 | 0 | 55800 | Authorized | Due by 3/31/2028 | No | PE | State | 0
H11-04-049 | 11 | 5123020 | 4 | Sebastopol | Sonoma County | MTC | MTC | Intersections of South Main Street/Burnett Street, North Main Street/Keating Avenue, Gravenstein Highway South/Hutchins Avenue, and Petaluma Avenue/Walker Avenue. | Install pedestrian-activated circular LED rapid flashing beacons replacing existing standard flashing beacons; install perimeter lighted pedestrian crossing signs; install pedestrian push buttons; remove existing in-roadway warning lights. | 239800 | 215820 | 0 | 0 | 0 | 0 | 0 | No PE | Due by 3/31/2028 | No | Not Started | State | 0
H12-04-049 | 12 | 5123021 | 4 | Sebastopol | Sonoma County | MTC | MTC | Intersection of Covert Lane and Zimpher Drive. | Install pedestrian-activated circular LED rapid flashing beacons, perimeter lighted pedestrian crossing signs, pedestrian pushbuttons, curb extensions, ADA ramps and refuge island, and restripe intersection approach. | 388400 | 349560 | 2026-01-16 | 0 | 0 | 0 | 53010 | Authorized | Due by 3/31/2028 | No | PE | State | 0
H10-04-040 | 10 | 5923130 | 4 | Solano County | Solano County | MTC | MTC | Suisun Valley Rd & Ledgewood Rd, Suisun Valley Rd & Rockville Rd, and Rockville Rd & Abernathy Rd (roundabout). | Install high-visibility crosswalks, truncated domes, dikes, advance warning signs, and ADA ramps. | 489800 | 250000 | 0 | 0 | 2022-09-14 | 2025-08-26 | 250000 | No PE | Authorized | No | Closed | State | 0
H11-04-050 | 11 | 5923145 | 4 | Solano County | Solano County | MTC | MTC | Lemon Street in Vallejo from Cypress Avenue to Benicia Road, and Benicia Road from Beach Street to Old Glenn Cove Parkway (Solano County right of way). | Improvement of pedestrian safety facilities including: Cross walk improvements, curb ramp improvements, addition of detectable warning surfaces, addition of bulb-outs, addition of flashing beacons, striping and markings. | 277700 | 249930 | 0 | 0 | 2025-09-30 | 0 | 249930 | No PE | Authorized | No | CON | State | 0
H11-04-051 | 11 | 5923133 | 4 | Solano County | Solano County | MTC | MTC | Multiple Rural Roads: 1) Lyon Road, 2) Vaca Valley, 3) Dixon Avenue, 4) Putah Creek Road, 5) Cordelia Road, 6) Fry Road, 7) Rockveille Road, 8) Pleasants Valley Road, 9) Meridian Road, 10) Holland Road, 11) Pedrick Road, and 12) Other Roads. | Install curve advance warning signs with flashing beacons, install delineators/reflectors/object markers and install/upgrade signs with new fluorescent sheeting. | 1192800 | 1073520 | 2023-08-17 | 0 | 0 | 0 | 191700 | Authorized | Due by 10/1/2026 | No | PE | Federal | 1
H11-04-052 | 11 | 5923136 | 4 | Solano County | Solano County | MTC | MTC | Various unsignalized intersections throughout the County. | Install street lights, place high friction surface treatment, restripe, and relocate various markings/utility poles/signs to correct sight distance. | 1684700 | 1516230 | 2023-08-17 | 0 | 0 | 0 | 225000 | Authorized | Due by 8/28/2026 | No | PE | Federal | 1
H11-04-053 | 11 | 5923135 | 4 | Solano County | Solano County | MTC | MTC | Five rural road corridors: (1) Putah Creek Rd, (2) Vaca Valley Rd, (3) Cordelia Rd, (4) Pleasants Valley Rd, and (5) Gibson Canyon Rd. | Install guardrail and/or high friction surface treatment at horizontal curves and spot locations. | 1868200 | 1681380 | 2023-08-17 | 0 | 0 | 0 | 202500 | Authorized | Due by 8/28/2026 | No | PE | Federal | 1
H12-04-050 | 12 | 5923148 | 4 | Solano County | Solano County | MTC | MTC | Various unsignalized intersections throughout the County. | Install additional signs or upgrade existing signs (intersection warning/regulatory signs, flashing beacons, and other advance warning signals). | 525500 | 472950 | 2025-11-26 | 0 | 0 | 0 | 81900 | Authorized | Due by 3/31/2028 | No | PE | State | 0
H12-04-051 | 12 | 5923141 | 4 | Solano County | Solano County | MTC | MTC | Multiple Rural Roads: 1) Pleasants Valley Rd 2) Suisun Valley Rd 3) Mankas Corner Rd 4) Putah Creek Rd 2 segments 5) Rockville Rd 6) Lopes Rd 7) Sievers Rd 8) Meridian Rd 9) Midway Rd 10) Pedrick Rd 2 segments 11) Cantelow Rd 12) and Other Roads. | Install/upgrade regulatory and warning signs with fluorescent sheeting, install chevron signs on curves, and install delineators, reflectors and/or object markers. | 1313600 | 1182240 | 2025-08-08 | 0 | 0 | 0 | 207000 | Authorized | Due by 3/31/2028 | No | PE | Federal | 1
H12-04-052 | 12 | 5923149 | 4 | Solano County | Solano County | MTC | MTC | Multiple rural road corridors: (1) Lopes Road, (2) Mankas Corner Road, and (3) Pleasants Valley Road and (4) other roads. | Install guardrails at horizontal curves and spot locations. | 580600 | 522540 | 2025-11-26 | 0 | 0 | 0 | 65700 | Authorized | Due by 3/31/2028 | No | PE | State | 0
H12-04-053 | 12 | 5923142 | 4 | Solano County | Solano County | MTC | MTC | Various roadway segments. | Install lighting and dynamic/variable speed warning signs. | 947800 | 853020 | 2025-08-08 | 0 | 0 | 0 | 76500 | Authorized | Due by 3/31/2028 | No | PE | Federal | 1
H12-04-054 | 12 | 5923147 | 4 | Solano County | Solano County | MTC | MTC | Tremont Road from Sparling Lane to Old Davis Road. | Widen existing graded dirt shoulders, pave and stripe bike lanes. | 1499200 | 349934 | 2025-11-25 | 0 | 0 | 0 | 39560 | Authorized | Due by 3/31/2028 | No | PE | State | 0
H8-04-027 | 8 | 5923119 | 4 | Solano County | Solano County | MTC | MTC | Various locations. | Upgrade existing painted edge lines and centerlines to thermoplastic with raised pavement markers(RPMs) and thermoplastic markings for stop signs. | 2216790.22 | 2029800 | 2017-04-19 | 0 | 2018-10-27 | 2022-07-25 | 2029800 | Authorized | Authorized | No | Closed | Federal | 0
H8-04-028 | 8 | 5923118 | 4 | Solano County | Solano County | MTC | MTC | Various locations. | Install new guardrail and upgrade existing guardrail. | 506907.66 | 490565.52 | 2017-04-19 | 0 | 2019-08-26 | 2022-10-21 | 490565.52 | Authorized | Authorized | No | Closed | Federal | 0
HRRR1-04-023 | 1 | 5923081 | 4 | Solano County | Solano County | MTC | MTC | Gibson Canyon Rd. 0.4 miles North of Pamela Ln. to 0.65 miles North of Pamela Ln. | Realign Roadway | 701999.29 | 421244.57 | 2007-12-05 | 2011-03-28 | 2012-06-01 | 2014-03-07 | 421244.57 | Authorized | Authorized | No | Closed | Federal | 0
HSIP2-04-022 | 2 | 5923087 | 4 | Solano County | Solano County | MTC | MTC | Various Locations Along Cantelow Rd, Dixon Ave, Halley Rd, Lyon Rd, & Rockville Rd. | Upgrade Guardrails | 277100.59 | 236827.74 | 2008-10-28 | 0 | 2009-07-07 | 2012-03-28 | 236827.74 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-04-024 | 5 | 5923104 | 4 | Solano County | Solano County | MTC | MTC | Midway Rd. between SR 80 and Porter Rd.; Sievers Rd. between Halley Rd. and Stevenson Bridge Rd. | Widen and pave shoulders | 1222270.12 | 899338.87 | 2013-07-25 | 0 | 2015-05-01 | 2017-05-15 | 899338.87 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-04-025 | 5 | 5923105 | 4 | Solano County | Solano County | MTC | MTC | Pleasants Valley Rd. between Foothill Rd. and Cantelow Rd. | Widen and pave shoulders | 2140306.36 | 897398.94 | 2013-07-25 | 0 | 2016-05-16 | 2019-04-19 | 897398.94 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-04-026 | 5 | 5923106 | 4 | Solano County | Solano County | MTC | MTC | Eighteen (17) curve locations in Solano County | Install guardrail | 357923.33 | 197949.24 | 2013-07-26 | 0 | 2016-01-26 | 2018-10-22 | 197949.24 | Authorized | Authorized | No | Closed | Federal | 0
HSIP6-04-021 | 6 | 5923114 | 4 | Solano County | Solano County | MTC | MTC | On Cordelia Rd between Thomasson Lane and Hale Ranch Rd, on Lake Herman Rd from 0.3 mile west of Sky Valley Rd to 0.7 mile east of Sky Valley Rd | Construct 4' paved shoulders | 774617.41 | 731581.33 | 2014-04-14 | 0 | 2016-10-24 | 2022-05-05 | 731581.33 | Authorized | Authorized | No | Closed | Federal | 0
HSIP6-04-022 | 6 | 5923113 | 4 | Solano County | Solano County | MTC | MTC | On Hartley Rd between Midway Rd and Allendale Rd, On Rockville Rd from Abernathy Rd to 1.0 mile east | Construct 4' paved shoulders | 1110428.69 | 1025424.83 | 2014-04-14 | 0 | 2016-05-13 | 2019-04-16 | 1025424.83 | Authorized | Authorized | No | Closed | Federal | 0
HSIP6-04-023 | 6 | 5923115 | 4 | Solano County | Solano County | MTC | MTC | On Putah Creek Rd. between Martinez Lane to 2.0 miles WEST, and on Dixon Ave. West from Jahn Rd. to 2.0 miles EAST | Construct 5-ft paved shoulders on Putah creek Rd. and 4-ft paved shoulders on Dixon Ave. West | 1312344.18 | 1072268.91 | 2014-04-14 | 0 | 2016-06-14 | 2018-11-07 | 1072268.91 | Authorized | Authorized | No | Closed | Federal | 0
HSIP3-04-018 | 3 | 5114015 | 4 | Sonoma | Sonoma County | MTC | MTC | Napa/Leveroni Rd. At Its Intersection With Broadway (Sr 12) | Install Protected Left-Turn Phasing In All Directions; Extend Eastbound Left-Turn Pocket Striping | 175984.43 | 129396.48 | 0 | 0 | 2013-03-29 | 2015-12-01 | 129396.48 | No PE | Authorized | No | Closed | Federal | 0
H8-04-029 | 8 | 5920156 | 4 | Sonoma County | Sonoma County | MTC | MTC | Lakeville Road between State Route 116 and State Route 37. | Install new longitudinal center line and edge line rumble strips; and upgrade existing striping for enhanced wet night visibility. | 717769.22 | 712109.52 | 2017-08-16 | 0 | 2018-11-16 | 2023-06-27 | 712109.52 | Authorized | Authorized | No | Closed | Federal | 0
HRRR2-04-022 | 2 | 5920113 | 4 | Sonoma County | Sonoma County | MTC | MTC | Adobe Road at East Washington Street | Install traffic signal; add turn lanes; widen roadway and shoulders | 2892856.69 | 899999.99 | 2008-12-19 | 0 | 2015-05-13 | 2018-06-01 | 899999.99 | Authorized | Authorized | No | Closed | Federal | 0
H10-04-041 | 10 | 5177046 | 4 | South San Francisco | San Mateo County | MTC | MTC | 6 Unsignalized Intersections along Olive Avenue, Linden Avenue, and Walnut Avenue: Lux Ave & Walnut Ave, Linden Ave & 9th Ln, Linden Ave & 8th Ln, Olive Ave & Aspen Ave, Olive Ave & Pine Ave, Park Way & Walnut Ave. | Improve pedestrian safety by bringing the existing non-ADA compliant curb ramps up to current standards and installation of new high visibility crosswalks. | 249800 | 249800 | 0 | 0 | 2023-08-10 | 2025-01-06 | 249800 | No PE | Authorized | No | Closed | State | 0
H11-04-054 | 11 | 5177052 | 4 | South San Francisco | San Mateo County | MTC | MTC | The intersection of Junipero Serra Blvd/Arroyo (new traffic signal); intersections of Grand Ave/Spruce Ave, Grand Ave/Maple, Grand Ave/Linden Ave (modified signals); and various signalized intersections throughout City. | Install new traffic signal including curb, gutter, sidewalk, curb ramp improvements; leading pedestrian interval (LPI) implementation (3 signals), and install retroreflective backplates (64 signals). | 1696800 | 1527120 | 0 | 0 | 2024-11-19 | 0 | 1527120 | No PE | Authorized | No | CON | State | 0
H8-04-030 | 8 | 5177041 | 4 | South San Francisco | San Mateo County | MTC | MTC | Intersection of Spruce Avenue at Commercial Avenue. | Install new traffic signal with pedestrian countdown timers and accompanying ADA curb ramps. | 696188.84 | 444000 | 0 | 0 | 2019-12-12 | 2022-11-23 | 444000 | No PE | Authorized | No | Closed | Federal | 0
H9-04-031 | 9 | 5177043 | 4 | South San Francisco | San Mateo County | MTC | MTC | Three (3) non-signalized intersections: W. Orange Ave at N. Canal St, W. Orange Ave at Myrtle Ave, and Hillside Blvd at Claremont Ave. | Construct pedestrian improvements including advanced pedestrian crosswalk, and ADA curb ramps. | 209613.33 | 204800 | 0 | 0 | 2021-11-15 | 2023-02-16 | 204800 | No PE | Authorized | No | Closed | Federal | 0
HSIP3-04-003 | 3 | 5177024 | 4 | South San Francisco | San Mateo County | MTC | MTC | Sister Cities Blvd. Between Hillside Blvd. And 1700' West Of Airport Blvd. | Install Guardrail | 200892.53 | 180097.76 | 2010-12-30 | 0 | 2012-03-16 | 2013-03-22 | 180097.76 | Authorized | Authorized | No | Closed | Federal | 0
HSIP4-04-024 | 4 | 5177028 | 4 | South San Francisco | San Mateo County | MTC | MTC | Grand Ave./Magnolia Ave. | Install traffic signals; construct curb ramps; improve drainage | 570478.01 | 366196.16 | 2011-10-24 | 0 | 2014-05-29 | 2018-10-22 | 366196.16 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-04-027 | 5 | 5177031 | 4 | South San Francisco | San Mateo County | MTC | MTC | Mission Rd./Evergreen Dr. | Install traffic signals | 574366.37 | 298469.55 | 2013-07-22 | 0 | 2015-02-06 | 2018-10-15 | 298469.55 | Authorized | Authorized | No | Closed | Federal | 0
HSIP6-04-024 | 6 | 5177034 | 4 | South San Francisco | San Mateo County | MTC | MTC | Junipero Serra Blvd/King Dr | Install/upgrade traffic signal mast arms, speed feedback sign, left turn phasing, turn pockets, curb ramps, sidewalks, striping and medians | 847147.12 | 759603.49 | 2014-11-07 | 0 | 2016-02-18 | 2019-01-28 | 759603.49 | Authorized | Authorized | No | Closed | Federal | 0
H9-04-032 | 9 | 5051005 | 4 | St Helena | Napa County | MTC | MTC | Silverado Trail, with the project limits bordering Napa County, beginning from approximately 175 feet north of Howell Mountain Road and ending at the southern City limits (1,475 feet total). | Replace 136 LF of guardrail, including terminal systems and associated striping. | 95509.43 | 95509.43 | 2019-12-03 | 0 | 2022-09-09 | 2024-01-24 | 95509.43 | Authorized | Authorized | No | Closed | Federal | 1
H10-04-042 | 10 | 5032036 | 4 | Suisun City | Solano County | MTC | MTC | 1 intersection on Main St at Lotz Wy; 5 intersections on Sunset Ave; and 5 intersections on Walters Rd. | Install protected left-turn phase & advanced dilemma zone detection and improve signal timing. | 2480600 | 1873935 | 2021-09-17 | 0 | 2023-10-02 | 0 | 1873935 | Authorized | Authorized | No | CON | State | 0
H10-04-043 | 10 | 5032037 | 4 | Suisun City | Solano County | MTC | MTC | Shoveller Dr & Golden Eye Wy, and Harrier Dr & Dan O. Root Elementary School Entrance. Additive alternate location: Pintail Dr & Crane Dr. | Install RRFB, high-visibility crosswalks, warning signs curb extensions, and ADA ramps. | 249800 | 249800 | 2021-08-12 | 0 | 2023-06-08 | 0 | 249800 | Authorized | Authorized | No | CON | State | 0
H11-04-055 | 11 | 5032039 | 4 | Suisun City | Solano County | MTC | MTC | Various T-intersections: Walters Road and McClellan Drive, Railroad Avenue and Village Drive, and Railroad Avenue and Birchwood Court. | Install raised medians to address left-turn conflicts. | 417100 | 375390 | 2023-07-31 | 0 | 2025-04-28 | 0 | 375390 | Authorized | Authorized | No | CON | State | 0
H11-04-056 | 11 | 5032038 | 4 | Suisun City | Solano County | MTC | MTC | Various non-signalized intersections throughout Suisun City. The intersections of Marina Boulevard and Lotz Way and Pintail Drive and Cackling Drive. | Improve pedestrian crossing with the upgrade and installation of Rectangular Rapid Flashing Beacon (RRFB) devices, bulb-outs (curb extensions), and high visibility crosswalks. | 244000 | 219600 | 2023-07-31 | 0 | 2024-10-25 | 0 | 219600 | Authorized | Authorized | No | CON | State | 0
H12-04-055 | 12 | 5032041 | 4 | Suisun City | Solano County | MTC | MTC | Non-signalized intersection on Pintail Drive at Crane Drive; Suisun City Fire Station, 621 Pintail Drive, between Cackling Drive and East Wigeon Way. | Install rectangular rapid flashing beacons (RRFBs), curb extensions, ADA ramps, warning signs and high visibility crosswalk; Replace and upgrade outdated emergency warning devices and install new advance warning beacons. | 388800 | 349920 | 2025-06-23 | 0 | 0 | 0 | 36000 | Authorized | Due by 3/31/2028 | No | PE | State | 0
H9-04-033 | 9 | 5032033 | 4 | Suisun City | Solano County | MTC | MTC | Three (3) pedestrian crossings, including: on Merganser Dr between Sunset Ave and Wigeon Way; the intersection of Pintail Dr. and Scoter Way; and on Lawler Ranch Pkwy between Fennie Way and Hillborn Way . | Enhance pedestrian crossings by the addition of ADA curb ramp, RRFB system, yield lines and signs, and other relevant elements. | 294013.31 | 248097.02 | 2019-09-06 | 0 | 2021-08-03 | 2024-05-01 | 248097.02 | Authorized | Authorized | No | Closed | Federal | 0
HSIP6-04-025 | 6 | 5032027 | 4 | Suisun City | Solano County | MTC | MTC | Walters Rd/Pintail Dr | Install traffic signals and protected left-turn phasing; upgrade curb ramps, striping, pavement markings, signs, lane reconfiguration, and landscaping & irrigation | 446595.57 | 389899.8 | 2014-04-27 | 0 | 2015-03-26 | 2017-04-03 | 389899.8 | Authorized | Authorized | No | Closed | Federal | 0
HSIP7-04-023 | 7 | 5032030 | 4 | Suisun City | Solano County | MTC | MTC | 1) Sunset Avenue between Highway 12 and a point approximately 300 feet north of Railroad Avenue East. 2) Walters Road between Highway 12 and E. Tabor Avenue. | Install traffic signal post with left turn arrow, and widen the Railroad Avenue East approach. Replace existing pedestrian head modules with pedestrian head modules that include walking countdown sequence. Install Signal Ahead advance warning signs | 210201.38 | 189181.24 | 2016-09-14 | 0 | 2018-12-13 | 2020-11-13 | 189181.24 | Authorized | Authorized | No | Closed | Federal
HSIP7-04-024 | 7 | 5032031 | 4 | Suisun City | Solano County | MTC | MTC | Eastbound State Route 12 between Pennsylvania Avenue and Marina Boulevard. | Installation of advance warning beacon system with controller and vehicle detection devices | 186939.83 | 162000 | 2016-09-06 | 0 | 2019-04-17 | 2022-03-07 | 162000 | Authorized | Authorized | No | Closed | Federal
H8-04-031 | 8 | 5213058 | 4 | Sunnyvale | Santa Clara County | MTC | MTC | Various locations. | Provide advance dilemma zone detection. | 638116.1 | 638116.1 | 2017-05-18 | 0 | 2019-09-06 | 2022-06-28 | 638116.1 | Authorized | Authorized | No | Closed | Federal | 0
H9-04-034 | 9 | 5213071 | 4 | Sunnyvale | Santa Clara County | MTC | MTC | Various locations throughout the City of Sunnyvale | Install video detection equipment to provide advance dilemma zone detection. | 1217000 | 1019453.21 | 2019-05-31 | 0 | 2022-06-13 | 2024-10-31 | 1019453.21 | Authorized | Authorized | No | Closed | Federal | 0
HSIP4-04-007 | 4 | 5213045 | 4 | Sunnyvale | Santa Clara County | MTC | MTC | Bernardo Ave./Remington Dr. | Install traffic signals, signs, striping, and curb ramps | 645269.99 | 579567.57 | 2012-01-18 | 0 | 2013-06-19 | 2015-10-29 | 579567.57 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-04-028 | 5 | 5213049 | 4 | Sunnyvale | Santa Clara County | MTC | MTC | Mathilda Ave./Maude Ave. | Upgrade traffic signals; install speed feedback sign | 291723 | 262550.64 | 2013-07-02 | 0 | 2015-02-11 | 2017-10-13 | 262550.64 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-04-029 | 5 | 5213048 | 4 | Sunnyvale | Santa Clara County | MTC | MTC | Sunnyvale-Saratoga Rd./Fremont Ave. | Upgrade traffic signals; install speed feedback sign | 277956.22 | 230100 | 2013-07-02 | 0 | 2015-02-17 | 2017-04-07 | 230100 | Authorized | Authorized | No | Closed | Federal | 0
HSIP7-04-025 | 7 | 5213056 | 4 | Sunnyvale | Santa Clara County | MTC | MTC | Intersection of Mathilda Avenue and Indio Way in the City of Sunnyvale. | Modify traffic signals to convert existing pedestal-mounted traffic signals to mast arm, installation of countdown pedestrian signals for all approaches and installation of left turn lanes and phase | 516752.18 | 450000 | 2016-06-22 | 0 | 2018-09-10 | 2021-06-07 | 450000 | Authorized | Authorized | No | Closed | Federal
HSIP7-04-026 | 7 | 5213055 | 4 | Sunnyvale | Santa Clara County | MTC | MTC | Iintersection of West Remington Drive at Michelangelo Drive | Install pedestrian crossing with enhanced safety features (In-Roadway Warning Lights Pedestrian System); upgrade warning and regulatory signs, and installation/upgrade intersection lighting | 308010.24 | 196498.74 | 2016-07-11 | 0 | 2018-11-28 | 2021-01-11 | 196498.74 | Authorized | Authorized | No | Closed | Federal
H8-04-032 | 8 | 5354040 | 4 | Union City | Alameda County | MTC | MTC | Two signalized intersections: Alvarado-Niles Road/Mann Ave/Union Square and Alvarado Blvd./Galaxy Drive. | Remove pedestal mounted signal heads, install new mast arms, install new street lights on the mast arm poles and related improvements. | 728599.45 | 524631.47 | 2017-06-13 | 0 | 2019-09-06 | 2023-02-21 | 524631.47 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-04-030 | 5 | 5354035 | 4 | Union City | Alameda County | MTC | MTC | Alvarado Rd. (Niles Rd.) between Decoto Rd. and Mann Ave. | Install crosswalks, flashing beacons, and median fencing | 380056.12 | 342050.11 | 2013-11-27 | 0 | 2015-03-26 | 2018-03-21 | 342050.11 | Authorized | Authorized | No | Closed | Federal | 0
HSIP6-04-026 | 6 | 5354038 | 4 | Union City | Alameda County | MTC | MTC | Alvarado-Niles Rd/Almaden Blvd, Alvarado-Niles Rd/Medallion Dr, Alvarado-Niles Rd/Central Av, Alvarado-Niles Rd/Royal Ann Dr, Alvarado-Niles Road/Western Av, and Alvarado Blvd/Dyer St | Upgrade traffic signals; Install lighting | 986464.39 | 886508.56 | 2015-01-06 | 0 | 2016-11-18 | 2019-04-29 | 886508.56 | Authorized | Authorized | No | Closed | Federal | 0
HSIP7-04-027 | 7 | 5354039 | 4 | Union City | Alameda County | MTC | MTC | Intersections of Whipple Road/Central Avenue and Decoto Road/Perry Road. | Upgrade visibility/safety of existing traffic signals by removal of pedestal mounted signal heads, install new mast arms to accommodate additional signal head installation, install new street lights on the mast arm poles and related improvements | 526998.94 | 437700 | 2016-10-21 | 0 | 2018-09-10 | 2021-04-01 | 437700 | Authorized | Authorized | No | Closed | Federal
H10-04-044 | 10 | 5094073 | 4 | Vacaville | Solano County | MTC | MTC | Segments among Monte Vista Ave, Elmira Road, Vaca Valley Pkwy, Browns Valley Rd, Midway Rd, Leisure Town Rd, Marshall Rd and Ulatis Dr. | Remove and replace edge-lines; remove and replace center line striping at various locations. | 188200 | 188200 | 2021-08-18 | 0 | 2022-10-25 | 2024-05-23 | 188200 | Authorized | Authorized | No | Closed | State | 0
H10-04-045 | 10 | 5094074 | 4 | Vacaville | Solano County | MTC | MTC | Alamo Drive between Grandview Drive and Walnut Drive and East Monte Vista Ave between Nut Tree Road and I-80 WB Ramp intersection. | Install high-visibility yellow crosswalk, advance crossing legends and markings, thermoplastic striping, signage, solar RRFBs system, and advance RRFBs. | 296200 | 250000 | 2021-09-16 | 0 | 2022-09-29 | 2024-04-05 | 250000 | Authorized | Authorized | No | Closed | State | 0
H11-04-058 | 11 | 0 | 4 | Vacaville | Solano County | MTC | MTC | The intersection of N. Orchard Ave and Valencia Lane; and the intersection of East Monte Vista Avenue and West Street. | Implement pedestrian crossing enhancements including high visibility crosswalks, advanced pedestrian warnings and signs, curb ramps, and Rectangular Rapid-Flashing Beacons (RRFBs). | 274700 | 247230 | 0 | 0 | 0 | 0 | 0 | No PE | Past due (due 3/31/2026) | Yes (CON) | Not Started | State | 0
H11-04-059 | 11 | 0 | 4 | Vacaville | Solano County | MTC | MTC | Segments along Allison Pkwy, Meridian Rd, Orange Dr, Peabody Rd, Ulatis Dr, and Vaca Valley Pkwy. | Remove and replace edge-lines that have faded away or deteriorated. Remove and replace center line striping at various locations. | 272900 | 245610 | 0 | 0 | 0 | 0 | 0 | No PE | Past due (due 3/31/2026) | Yes (CON) | Not Started | State | 0
H12-04-056 | 12 | 0 | 4 | Vacaville | Solano County | MTC | MTC | Orchard Ave from Walnut Ave to Peach Tree Ave, the intersections of Christine Dr and Oak Hollow Ave, Brown St and Bennett Hill Dr, Markham Ave and Alpine St, and Markham Ave and Meadows Dr. | Install pedestrian crossing enhancements such as radar feedback signs and rectangular rapid flashing beacons (RRFBs). | 388400 | 349560 | 0 | 0 | 0 | 0 | 0 | No PE | Due by 3/31/2028 | No | Not Started | State | 0
H9-04-035 | 9 | 5094071 | 4 | Vacaville | Solano County | MTC | MTC | Twenty-one (21) intersections in the City of Vacaville. | Improve signal hardware and timing ; install Advanced Dilemma-Zone Detection. | 2406387.25 | 2399903.54 | 2019-09-06 | 0 | 2022-07-18 | 2025-01-10 | 2399903.54 | Authorized | Authorized | No | Closed | Federal | 0
H9-04-036 | 9 | 5094072 | 4 | Vacaville | Solano County | MTC | MTC | The intersections of Browns Valley Rd with Waterford/Clarecastle Way and Marshall Rd. with Southside Bikeway. | Construct pedestrian crossing enhancements such as advanced pedestrian warnings and signs as well as Rectangular Rapid Flashing Beacons (RRFBs). | 224510.03 | 221540.92 | 2019-09-06 | 0 | 2020-04-30 | 2022-04-04 | 221540.92 | Authorized | Authorized | No | Closed | Federal | 0
H10-04-046 | 10 | 5030068 | 4 | Vallejo | Solano County | MTC | MTC | Springs Rd from Miller Ave/Humbolt St to Rollingwood Dr. | Reduce travel lanes from 4 to 3 and add two-way left-turn and bike lanes. Install crossing enhancements and RRFB system at various non signalized locations along roadway segment. | 1400400 | 1260360 | 2021-05-10 | 0 | 2025-01-13 | 0 | 1260360 | Authorized | Authorized | No | CON | State | 0
H10-04-047 | 10 | 5030069 | 4 | Vallejo | Solano County | MTC | MTC | Georgia at Rollingwood/Fernwood, Baywood at Rollingwood/Fernwood, Daniels at Rodgers/Selfridge, Mini at Whitney/Corcoran, Cocoran at Arrowhead, Ensign at Shasta/Highland Elm/Mariposa, Nebraska at Shasta/Mariposa/Mid Block, Porter at Magazine, Glen Cove at Regatta. | Install high-visibility crosswalks, advance warning signs, and ADA ramps. | 249700 | 249700 | 2021-05-10 | 0 | 2023-12-18 | 0 | 249700 | Authorized | Authorized | No | CON | State | 0
H11-04-060 | 11 | 5030075 | 4 | Vallejo | Solano County | MTC | MTC | Various locations throughout the city. 2 locations along Lincoln Road East, 1 at Admiral Callaghan Lane, 1 at the Whitney Avenue and Mini Drive intersection, and 1 at Virgina Street. | Upgrade guardrails, including the removal and replacement of existing guardrail. | 238900 | 215010 | 2024-04-18 | 0 | 0 | 0 | 25430 | Authorized | Due by 9/30/2026 | No | PE | State | 0
H12-04-057 | 12 | 0 | 4 | Vallejo | Solano County | MTC | MTC | Major collector streets including Admiral Callaghan Lane, Ascot Parkway, Benicia Road, Borges Lane, Camino Alto, Corcoran Avenue, Florida Street, Glen Cove Parkway, Nebraska Street, and Whitney Avenue. | Install edgelines. | 388870 | 350000 | 0 | 0 | 0 | 0 | 0 | No PE | Due by 3/31/2028 | No | Not Started | State | 0
H9-04-037 | 9 | 5030065 | 4 | Vallejo | Solano County | MTC | MTC | Five (5) pedestrian crossing at the intersection of Broadway at Illinois, Broadway at Hampshire, Springs at Tregaskis, Springs at Heartwood, and Springs at Lassen/Hilton. | Installation of High-Intensity Activated Crosswalk beacon (HAWK) at unsignalized intersections, installing high visible crosswalk, ADA curb ramps, Yield like with signage and Pedestrian Push Button | 1305800 | 1305800 | 2019-09-06 | 0 | 2022-06-28 | 0 | 1305800 | Authorized | Authorized | No | CON | Federal | 0
H9-04-038 | 9 | 5030066 | 4 | Vallejo | Solano County | MTC | MTC | Five (5) intersections including: Foothill Dr at Redwood Pkwy, Valle Vista Ave at Redwood St, Fairview Ave at Redwood St, Howard Ave at Redwood St, and Solano Ave at Tuolumne St. | Construct pedestrian crossing enhancements such as advanced pedestrian warnings and signs as well as Rectangular Rapid-Flashing Beacons (RRFBs). | 582570.44 | 246000 | 2019-09-06 | 0 | 2022-03-16 | 2024-03-19 | 246000 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-04-031 | 5 | 5030057 | 4 | Vallejo | Solano County | MTC | MTC | Sonoma Blvd. (SR 29) between York St. and Kentucky St. | Implement "road diet" (reduce travel lanes from 4 to 2, add a two-way left-turn lane or median, and add bike lanes) | 814219.46 | 365068 | 2013-11-08 | 0 | 2018-07-04 | 2021-04-07 | 365068 | Authorized | Authorized | No | Closed | Federal | 0
H12-04-058 | 12 | 5225036 | 4 | Walnut Creek | Contra Costa County | MTC | MTC | Signalized intersections along Ygnacio Valley Road at the Walnut Boulevard, Via Monte Drive, Wimbledon Road, and Wiget Lane. | Add protected-left-turn phasing. | 2134400 | 1920960 | 2025-11-05 | 0 | 0 | 0 | 163800 | Authorized | Due by 3/31/2028 | No | PE | Federal | 0
H10-04-048 | 10 | 5472023 | 4 | Windsor | Sonoma County | MTC | MTC | Intersection of Brooks Road South with Natalie Drive. | Install rectangular rapid flashing beacon (RRFB), construct pedestrian refuge median, curb extension, curb ramps, lane transition/traffic calming median, restripe bike lanes and vehicle lanes and slurry seal. | 240600 | 240600 | 0 | 0 | 2022-05-18 | 2024-01-04 | 240600 | No PE | Authorized | No | Closed | State | 0
H12-04-059 | 12 | 5472024 | 4 | Windsor | Sonoma County | MTC | MTC | Three locations: Arata Lane at Old Redwood Highway; Old Redwood Highway at U.S. 101 underpass; and Old Redwood Highway and Pool Creek. | Replace two damaged guardrails at Old Redwood Hwy/Arata Ln with Caltrans-approved inline crash cushions; replace two center crash cushions at Old Redwood Hwy Downtown Undercrossing; restore two damaged guardrails at Pool Creek to original design. | 221600 | 199440 | 2025-07-31 | 0 | 0 | 0 | 77490 | Authorized | Due by 3/31/2028 | No | PE | State | 0
HSIP4-04-021 | 4 | 5333015 | 4 | Woodside | San Mateo County | MTC | MTC | Woodside Rd. (SR 84), near Albion Way at Woodside Elementary School | Upgrade crosswalks, school area signs, and flashing beacons | 366211.66 | 194000 | 2012-07-06 | 0 | 2013-06-19 | 2015-06-19 | 194000 | Authorized | Authorized | No | Closed | Federal | 0
H10-05-001 | 10 | 5199033 | 5 | Arroyo Grande | San Luis Obispo County | SLOCOG | SLOCOG | Uncontrolled pedestrian crosswalk on the west leg of E Grand Ave at Alder St; School crosswalk across Farroll Ave at S. Halcyon Rd; and School crosswalk on the south leg of S Halcyon Rd at Sandalwood Ave. | Install Rectangular Rapid Flashing Beacons (RRFBs), curb extensions, ADA curb ramps, yield lines, and striping and pavement markings. | 250000 | 250000 | 2021-06-28 | 0 | 2022-08-04 | 2023-12-15 | 250000 | Authorized | Authorized | No | Closed | State | 0
H12-05-001 | 12 | 5199039 | 5 | Arroyo Grande | San Luis Obispo County | SLOCOG | SLOCOG | Locations along E. Branch east of Mason Street to Le Point Terrace and Huasna Road at Rosewood Lane near Strother Park. | Improve pedestrian access to schools and parks by constructing crosswalks with bulb-outs, rectangular rapid flashing beacons (RRFBs), signage and island refuge. Add bulb-outs at E. Branch. | 627600 | 340560 | 0 | 0 | 2025-11-14 | 0 | 340560 | No PE | Authorized | No | CON | State | 0
HSIP5-05-001 | 5 | 5199029 | 5 | Arroyo Grande | San Luis Obispo County | SLOCOG | SLOCOG | Oak Park Blvd./West Branch St./SR 101 on-ramp | Upgrade traffic signal; install protected left-turn phasing | 139721.85 | 98546.32 | 2013-08-16 | 0 | 2015-07-14 | 2017-04-10 | 98546.32 | Authorized | Authorized | No | Closed | Federal | 0
H12-05-002 | 12 | 5397012 | 5 | Carpinteria | Santa Barbara County | SBCAG | SBCAG | Carpinteria High School crosswalk. | Install a pedestrian hybrid beacon. | 380300 | 342270 | 0 | 0 | 2025-05-07 | 0 | 342270 | No PE | Authorized | No | CON | State | 0
H10-05-002 | 10 | 5084020 | 5 | El Paso De Robles | San Luis Obispo County | SLOCOG | SLOCOG | Intersection of Niblick Road and Appaloosa Drive | Install Rectangular Rapid Flashing Beacons (RRFBs), pedestrian refuge island & advanced yield markings, and restripe lanes. | 247970 | 247970 | 0 | 0 | 2022-09-26 | 2024-05-07 | 247970 | No PE | Authorized | No | Closed | State | 0
H11-05-001 | 11 | 5084024 | 5 | El Paso De Robles | San Luis Obispo County | SLOCOG | SLOCOG | Intersections for bicycle safety improvements: 12th St at Riverside Ave, 16th St at Riverside Ave, and 10th St at Riverside Ave. | Green bike lane upgrades intersection improvement. | 269300 | 242370 | 0 | 0 | 0 | 0 | 0 | No PE | Past due (due 3/31/2026) | Yes (CON) | Not Started | State | 0
H12-05-003 | 12 | 0 | 5 | El Paso De Robles | San Luis Obispo County | SLOCOG | SLOCOG | The intersections of Montebello Oaks Dr & Union Rd, 21st & Spring, 17th & Spring and Nickerson Dr at Centennial Trail crossing. | Install rectangular rapid flashing beacons (RRFBs) at crossings. | 311700 | 280530 | 0 | 0 | 0 | 0 | 0 | No PE | Due by 3/31/2028 | No | Not Started | State | 0
H12-05-004 | 12 | 5084026 | 5 | El Paso De Robles | San Luis Obispo County | SLOCOG | SLOCOG | The intersection of Creston & Golden Hill. | Modify/upgrade signal along with signage and striping. | 150000 | 135000 | 0 | 0 | 2025-06-02 | 0 | 135000 | No PE | Authorized | No | CON | State | 0
H10-05-003 | 10 | 5481024 | 5 | Goleta | Santa Barbara County | SBCAG | SBCAG | Various locations throughout the City. | Upgrade and modernize existing city traffic signals including retroreflective back plates, advanced dilemma zone detection, LPIs, controllers, and 12-inch LED lenses. | 3503300 | 3503300 | 2021-07-26 | 0 | 2025-07-02 | 0 | 3120100 | Authorized | Authorized | No | CON | State | 0
HSIP6-05-001 | 6 | 5481015 | 5 | Goleta | Santa Barbara County | SBCAG | SBCAG | On Hollister Ave between 340' ft east of Rutherford St | Install High Intensity Activated Crosswalk (HAWK) (remove flashing beacon); striping and signs | 228219.18 | 184629.33 | 2013-12-30 | 0 | 2016-05-04 | 2018-04-25 | 184629.33 | Authorized | Authorized | No | Closed | Federal | 0
HSIP7-05-007 | 7 | 5481019 | 5 | Goleta | Santa Barbara County | SBCAG | SBCAG | Uncontrolled pedestrian crossings at the intersections of Hollister Avenue and Chapel Street and Calle Real and Kingston Avenue | Installation of pedestrian crosswalk improvements consisting of Rectangular Rapid Flashing Beacons (RRFBs) at Hollister and Chapel and a Pedestrian Hybrid Beacon (HAWK signal) at Calle Real and Kingston Ave. | 621750.44 | 237780 | 2016-08-11 | 0 | 2020-01-09 | 2022-08-16 | 237780 | Authorized | Authorized | No | Closed | Federal
HSIP1-05-002 | 1 | 5080018 | 5 | Lompoc | Santa Barbara County | SBCAG | SBCAG | 300 Block Of South "U" Street At The San Miguelito Channel. | Construct Pedestrian Footbridge With Ada Accessible Approach Ramps And Sidewalk. | 290103.17 | 245778.13 | 2009-10-16 | 0 | 2012-03-16 | 2013-08-02 | 245778.13 | Authorized | Authorized | No | Closed | Federal | 0
HSIP3-05-002 | 3 | 5080025 | 5 | Lompoc | Santa Barbara County | SBCAG | SBCAG | Intersection Of "R" St. And Sr 246 | Install Traffic Signal And Upgrade Curb Ramps | 326411.94 | 176986.18 | 2011-05-12 | 0 | 2013-03-01 | 2015-01-20 | 176986.18 | Authorized | Authorized | No | Closed | Federal | 0
HSIP4-05-008 | 4 | 5080026 | 5 | Lompoc | Santa Barbara County | SBCAG | SBCAG | Chestnut Ave. between "G" St. and "O" St. | Construct sidewalk and curb ramps | 181338.72 | 134199.32 | 2011-11-04 | 0 | 2013-07-25 | 2016-01-13 | 134199.32 | Authorized | Authorized | No | Closed | Federal | 0
H11-05-002 | 11 | 5416013 | 5 | Marina | Monterey County | AMBAG | TAMC | Roundabout at the intersection of Del Monte Blvd and Beach Rd, and the NB Del Monte Blvd approach to the roundabout. | Implement road geometry improvements including bollards, striping improvements, a chicane, and speed feedback sign. | 493234 | 443910 | 2023-09-25 | 0 | 2026-04-02 | 0 | 443910 | Authorized | Authorized | No | CON | State | 0
H11-05-003 | 11 | 5416014 | 5 | Marina | Monterey County | AMBAG | TAMC | The intersection of Imjin Pkwy and 3rd Ave. | Install a traffic signal and pedestrian facility improvements. | 1458085 | 943650 | 2023-08-29 | 0 | 2025-12-05 | 0 | 943650 | Authorized | Authorized | No | CON | State | 0
HSIP5-05-002 | 5 | 5416010 | 5 | Marina | Monterey County | AMBAG | TAMC | Del Monte Blvd./Beach Rd. | Install traffic signals, left-turn and right-turn pockets, and bike lanes | 1861770 | 1340013.4 | 2013-11-05 | 0 | 2016-05-13 | 2019-10-21 | 1340013.4 | Authorized | Authorized | No | Closed | Federal | 0
H9-05-001 | 9 | 5086040 | 5 | Monterey | Monterey County | AMBAG | TAMC | The intersection of Del Monte Avenue and Casa Verde Way in City of Monterey and Casa Verde Recreational trail crossing just north of the intersection between Del Monte Avenue and Robertson Ave. | Intersection Improvements including: relocate of the Casa Verde Trail Crossing to the Int., protected left turn phase, shorten/restripe crosswalks, ADA Improvements, bike crosswalks/signals, median improvements, right turn lane and leading ped phase. | 1649000 | 1023560 | 2019-09-05 | 0 | 2023-07-07 | 0 | 923832 | Authorized | Authorized | No | CON | Federal | 2
HSIP3-05-006 | 3 | 5086032 | 5 | Monterey | Monterey County | AMBAG | TAMC | Intersection Of Pacific St. And Del Monte Ave. | Widen Wb Left & Right-Turn Lanes; Upgrade Traffic Signals; Reconstruct Curb Returns; Install Safety Lighting, Signs, Stripes And Pavement Markings | 838731.86 | 624127.86 | 0 | 0 | 2012-03-16 | 2015-01-05 | 624127.86 | No PE | Authorized | No | Closed | Federal | 0
H10-05-004 | 10 | 5944143 | 5 | Monterey County | Monterey County | AMBAG | TAMC | San Miguel Canyon Road and Castroville Boulevard in Prunedale. | Install a roundabout. | 2189600 | 2189600 | 2021-09-29 | 2025-09-11 | 0 | 0 | 511000 | Authorized | Due in no more than 4 months | No | ROW | State | -1
H10-05-005 | 10 | 5944144 | 5 | Monterey County | Monterey County | AMBAG | TAMC | Salinas Road from approximately 75 feet south of Railroad Avenue through the unincorporated community of Pajaro, terminating at the intersection of Porter Drive and San Juan Road. | Install Class II bike lane; class II bike lane and 3 ft buffer where feasible; install RRFB, install PCC sidewalks and curb ramps; install splitter-island on minor road approaches; dynamic speed warning signs. | 832400 | 749160 | 2021-09-29 | 2025-04-04 | 2025-05-30 | 0 | 721620 | Authorized | Authorized | No | CON | State | 0
H8-05-001 | 8 | 5944130 | 5 | Monterey County | Monterey County | AMBAG | TAMC | Various locations along Carmel Valley Road, Carpenteria Road, Outlook Drive, Laureles Grade, Old Stage Road, Reservation Road, and San Juan Road. | Upgrade existing guardrails. | 779605.85 | 760169.14 | 2017-09-13 | 0 | 2020-09-11 | 2022-11-03 | 760169.14 | Authorized | Authorized | No | Closed | Federal | 0
H8-05-002 | 8 | 5944132 | 5 | Monterey County | Monterey County | AMBAG | TAMC | Intersections of Castroville Boulevard at Elkhorn Road (in the community of Castroville) and Rio Road at Via Nona Marie (in the community of Carmel Valley). | Install Rectangular Rapid Flashing Beacons and luminaires at Castroville Blvd at Elk horn Rd and Rectangular Rapid Flashing Beacons Rio Rd at Via Nona Marie | 390630.9 | 244500 | 2017-09-13 | 0 | 2020-06-26 | 2022-12-07 | 244500 | Authorized | Authorized | No | Closed | Federal | 0
HRRR1-05-037 | 1 | 5944086 | 5 | Monterey County | Monterey County | AMBAG | TAMC | Unincorporated Monterey County between SRs 156 and 101 | Widen or Improve Shoulder | 264045.29 | 159000 | 2007-10-22 | 0 | 0 | 2013-08-23 | 159000 | Authorized | No CON | No | Closed | Federal | 0
HRRR2-05-038 | 2 | 5944091 | 5 | Monterey County | Monterey County | AMBAG | TAMC | Blackie Road between SR 183 and SR 101 | Widen roadway and shoulder; install signs, stripes and pavement markers | 259579.51 | 227708.99 | 2009-02-05 | 0 | 0 | 2013-05-06 | 227708.99 | Authorized | No CON | No | Closed | Federal | 0
HRRR2-05-039 | 2 | 5944092 | 5 | Monterey County | Monterey County | AMBAG | TAMC | San Juan Road from MP 2.38 to MP 5.0 | Install signs, stripes, pavement markings, and radar speed feedback sign | 4416097.82 | 360094.29 | 2009-02-05 | 0 | 2011-09-12 | 2014-10-09 | 360094.29 | Authorized | Authorized | No | Closed | Federal | 0
HRRR2-05-043 | 2 | 5944109 | 5 | Monterey County | Monterey County | AMBAG | TAMC | BLACKIE ROAD SAFETY IMPROVEMENTS | SAFETY WIDENING | 2283948 | 1413282 | 0 | 0 | 2012-03-08 | 2016-05-25 | 1413282 | No PE | Authorized | No | Closed | Federal | 0
HSIP2-05-006 | 2 | 5944090 | 5 | Monterey County | Monterey County | AMBAG | TAMC | Various Locations Throughout Monterey County | Install And Upgrade Guardrails | 485780.21 | 437202.14 | 2009-02-04 | 0 | 2009-08-20 | 2012-02-29 | 437202.14 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-05-003 | 5 | 5944114 | 5 | Monterey County | Monterey County | AMBAG | TAMC | Castroville Blvd. between SR 156 and San Miguel Canyon Rd. | Apply fog seal; install striping (center-line and edge-line) and pavement markers | 365534.24 | 309794.96 | 2013-02-14 | 0 | 2014-02-24 | 2017-02-15 | 309794.96 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-05-004 | 5 | 5944113 | 5 | Monterey County | Monterey County | AMBAG | TAMC | River Rd. between Chualar River Rd. and Parker Rd. | Apply fog seal; install striping (center-line and edge-line) and pavement markers; install 6 solar powered flashing beacons, road and curve warning signs. | 270134.46 | 221202.69 | 2013-02-14 | 0 | 2015-02-23 | 2017-02-21 | 221202.69 | Authorized | Authorized | No | Closed | Federal | 0
HSIP7-05-001 | 7 | 5944127 | 5 | Monterey County | Monterey County | AMBAG | TAMC | Various locations throughout the County. | Conduct a Roadway Safety Signing and Striping Audit on approximately 250 miles of County roads. Based on the the audit findings replace or relocate existing signs, install new signs, and replace existing striping with detail 22 where warranted | 2646725.96 | 2646725.96 | 2016-08-10 | 0 | 2021-01-22 | 2024-06-24 | 2646725.96 | Authorized | Authorized | No | Closed | Federal
HSIP7-05-012 | 7 | 5289014 | 5 | Pismo Beach | San Luis Obispo County | SLOCOG | SLOCOG | US 101 Southbound Ramps / Five Cities Drive | Install protected left turn phase; install traffic signal poles; LED signal hardware; LED ped. countdown signals; a crosswalk; & constructs new curb, gutter, sidewalk, & curb ramp | 188002.17 | 169201.95 | 0 | 0 | 2016-03-11 | 2017-10-16 | 169201.95 | No PE | Authorized | No | Closed | Federal
H11-05-004 | 11 | 5045041 | 5 | Salinas | Monterey County | AMBAG | TAMC | Main Street at Lamar Street. | Install overhead rectangular rapid flashing beacon system, signs, and striping. | 275000 | 247500 | 2023-04-14 | 0 | 2024-03-01 | 0 | 247500 | Authorized | Authorized | No | CON | State | 0
H11-05-005 | 11 | 5045042 | 5 | Salinas | Monterey County | AMBAG | TAMC | San Juan Grade Road between Boronda Road and 600 ft north of Van Buren Avenue | Install sidewalks and street lights, and install radar feedback signs at the road transitions from a rural highway to an urban arterial. | 1494100 | 1344690 | 2023-04-14 | 0 | 0 | 0 | 63000 | Authorized | Due by 3/31/2027 | No | PE | State | 0
H9-05-002 | 9 | 5045035 | 5 | Salinas | Monterey County | AMBAG | TAMC | Various uncontrolled pedestrian crossings within the City of Salinas. | Install pedestrian crossing enhancements. | 1134208.08 | 250000 | 2019-03-08 | 0 | 2020-09-21 | 2023-11-28 | 250000 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-05-005 | 5 | 5045026 | 5 | Salinas | Monterey County | AMBAG | TAMC | Sanborn Rd./John St. | Upgrade traffic signals; install left-turn phasing and a "dilemma zone" detection | 377971.95 | 340174.73 | 2013-05-15 | 0 | 2015-03-27 | 2017-10-19 | 340174.73 | Authorized | Authorized | No | Closed | Federal | 0
HSIP6-05-002 | 6 | 5045027 | 5 | Salinas | Monterey County | AMBAG | TAMC | Various locations on Sanborn Rd between East Alisal St and Freedom Parkway | Install signal coordination, pedestrian countdown heads and protected left-turn phasing | 1958676.52 | 1685199.97 | 2014-05-19 | 0 | 2017-03-15 | 2020-12-11 | 1685199.97 | Authorized | Authorized | No | Closed | Federal | 0
HSIP7-05-002 | 7 | 5045032 | 5 | Salinas | Monterey County | AMBAG | TAMC | Alisal St between Blonco St and Front St | Install left-turn lane and add turn phase at four intersections with no left-turn lane or left-turn phase, provide protected left-turn phase for three intersections with left-turn lane but no left-turn phase, and conduct road diet | 8220661.1 | 2340090 | 2016-07-20 | 0 | 2018-12-14 | 2022-04-07 | 2340090 | Authorized | Authorized | No | Closed | Federal
HSIP7-05-003 | 7 | 5045033 | 5 | Salinas | Monterey County | AMBAG | TAMC | N Main St between Chaparral St and Navajo Dr | Install a traffic signal, and a median opening to allow Main St and restrict Chaparral Left-turn | 674061.29 | 484766.02 | 2016-07-20 | 0 | 2019-10-18 | 2023-02-27 | 484766.02 | Authorized | Authorized | No | Closed | Federal
H10-05-006 | 10 | 5943079 | 5 | San Benito County | San Benito County | AMBAG | San Benito COG | 21 locations on 10 roads (Panoche Rd, Limekiln Rd, Cienega Rd, Southside Rd, Enterprise Rd, San Juan Hollister Rd, San Juan Canyon Rd, Salinas Rd, Cannon Rd and Prescott Rd). | Replace damaged/destroyed guardrails to current standards. | 1013600 | 1000000 | 2021-06-23 | 0 | 0 | 0 | 170000 | Authorized | Past due (due 9/30/2025) | Yes (CON) | PE | Mix | 1
HSIP2-05-004 | 2 | 5943058 | 5 | San Benito County | San Benito County | AMBAG | San Benito COG | Salinas Grade Rd At County Mile Post 2.91 And 3.85 | Upgrade Guardrail | 61146.2 | 52355.23 | 2010-09-01 | 0 | 2013-08-08 | 2015-11-16 | 52355.23 | Authorized | Authorized | No | Closed | Federal | 0
HSIP2-05-005 | 2 | 5943059 | 5 | San Benito County | San Benito County | AMBAG | San Benito COG | Fairview Rd. At Its Intersection With John Smith Rd. At Santa Ana Creek Crossing. | Install Guardrail | 42983.2 | 33448.61 | 2010-09-01 | 0 | 2013-07-29 | 2015-11-16 | 33448.61 | Authorized | Authorized | No | Closed | Federal | 0
HSIP3-05-005 | 3 | 5943060 | 5 | San Benito County | San Benito County | AMBAG | San Benito COG | Intersection Of Santa Ana Rd. And Fairview Rd. | Install Traffic Signal | 365678.31 | 229058.85 | 2010-09-01 | 0 | 2013-03-21 | 2015-10-30 | 229058.85 | Authorized | Authorized | No | Closed | Federal | 0
H12-05-005 | 12 | 5103006 | 5 | San Juan Bautista | San Benito County | AMBAG | San Benito COG | Along 2nd Street from Muckelemi St. to about 100 feet beyond the intersection at Washington St. | Install one and remove one pedestrian crossing, enhance visibility at existing crossings with pavement markings and ped yield signs, install curb ramps, ADA tactile pads, and painted curb extensions, and fill in gaps in the sidewalk network. | 514100 | 349588 | 2025-05-12 | 0 | 0 | 0 | 62764 | Authorized | Due by 3/31/2028 | No | PE | State | 0
HSIP1-05-001 | 1 | 5016045 | 5 | San Luis Obispo | San Luis Obispo County | SLOCOG | SLOCOG | Intersection Of Grand Avenue And The Nb Off Ramp Of State Route 101. | Cooperative Project With Caltrans. Install Traffic Signal. | 280051.48 | 251441.53 | 2009-07-10 | 0 | 2011-08-03 | 2013-05-09 | 251441.53 | Authorized | Authorized | No | Closed | Federal | 0
HSIP6-05-003 | 6 | 5016053 | 5 | San Luis Obispo | San Luis Obispo County | SLOCOG | SLOCOG | On Higuera St between Bridge St and Elks Lane | Widen a portion of roadway north of Bridge and install new curb, gutter and sidewalk; install "Two-Way Left Turn Lane", remove one NB travel lane, for the length of the segment. Install two left turn receiving lanes. | 498700 | 448800 | 2014-10-22 | 2017-07-06 | 0 | 0 | 406350 | Authorized | Due in no more than 4 months | No | ROW | Federal | -2
H10-05-007 | 10 | 5949185 | 5 | San Luis Obispo County | San Luis Obispo County | SLOCOG | SLOCOG | Various roads in County: Adelaida Rd from Chimney Rock Rd to Nacimiento Lake Dr, El Pomar Rd from Templeton Rd to Cripple Creek Rd, Geneseo Rd from Creston Rd to SR46, Linne Rd from City of Paso Robles to Geneseo Rd, Union Rd from City of Paso Robles to SR46. | Replace existing signage as needed for compliance with latest retroreflectivity standards, install new chevrons and advanced curve warning signs. | 314100 | 299986.23 | 2021-07-26 | 0 | 2024-02-09 | 2026-01-09 | 299986.23 | Authorized | Authorized | No | Closed | State | -1
H10-05-008 | 10 | 5949186 | 5 | San Luis Obispo County | San Luis Obispo County | SLOCOG | SLOCOG | Adelaida Rd from 1.2 mi W of Hidden Mountain Rd to 1.5 mi E of Adara Rd; Creston Rd from S El Pomar Rd to 4 Paws Wy; Old Creek Rd from 2 mi S of HWY 1 to .75 mi N of Cottontail Creek Rd; and Templeton Rd from Blue Bird Hill Ln to .25 mi N of River Rd. | Install guardrail improvements. | 1996200 | 1996200 | 2021-07-23 | 0 | 2025-10-31 | 0 | 1996200 | Authorized | Authorized | No | CON | Mix | 1
H10-05-009 | 10 | 5949187 | 5 | San Luis Obispo County | San Luis Obispo County | SLOCOG | SLOCOG | Various County roads: Adelaida Rd, El Pomar Rd, Geneseo Rd, La Panza Rd, Oso Flaco Lake Rd, Peachy Canyon Rd and Pomeroy Rd. | Install centerline striping and rumble strips. | 787005 | 787005 | 2021-07-26 | 0 | 2024-03-04 | 0 | 733268 | Authorized | Authorized | No | CON | Mix | 1
H11-05-006 | 11 | 5949192 | 5 | San Luis Obispo County | San Luis Obispo County | SLOCOG | SLOCOG | Turri Road (0.6 mi East of S Bay Boulevard and 1.75 mi East of S Bay Boulevard) and See Canyon Road (0.65 mi North of San Luis Bay Drive). | Install guardrails. | 391600 | 352440 | 2023-06-29 | 0 | 2025-12-01 | 0 | 352440 | Authorized | Authorized | No | CON | Federal | 1
H11-05-007 | 11 | 5949193 | 5 | San Luis Obispo County | San Luis Obispo County | SLOCOG | SLOCOG | S Higuera Street between Clover Ridge lane and Octagon way, and S El Pomar Road between Summit Road and Rancho Road. | Upgrade 1875 ft of existing guardrail in compliance with state and federal standards. | 651900 | 586710 | 2023-06-14 | 0 | 2026-02-09 | 0 | 586710 | Authorized | Authorized | No | CON | State | 0
H12-05-006 | 12 | 5949198 | 5 | San Luis Obispo County | San Luis Obispo County | SLOCOG | SLOCOG | Vineyard Drive from Bennett Way to Main Street. | Install sidewalk, signal optimization, signing & striping improvement including green bike lane and intersection lane extension markings. | 908400 | 817560 | 2025-04-01 | 0 | 0 | 0 | 76500 | Authorized | Due by 3/31/2028 | No | PE | State | 0
H12-05-007 | 12 | 5949199 | 5 | San Luis Obispo County | San Luis Obispo County | SLOCOG | SLOCOG | Cross Canyon Road (N of Vineyard Canyon Road), Ontario Road (NW Corner at San Luis Bay Dr), Cave Landing Road, Lopez Drive (E of Huasna Road), and South Bay Boulevard (At Yama ln). | Upgrade 1960 feet of existing guardrail; install an additional 200 feet of MBGR at the South Bay Blvd site. | 831700 | 748530 | 2025-04-01 | 0 | 0 | 0 | 81000 | Authorized | Due by 3/31/2028 | No | PE | State | 0
H8-05-003 | 8 | 5949167 | 5 | San Luis Obispo County | San Luis Obispo County | SLOCOG | SLOCOG | Los Osos Valley Rd between Doris Ave and Palisades Ave, Pomeroy Rd between Tefft St and Sandydale Dr, and Thompson Ave between Willow Rd and Leaf St. | Add segment lighting at intersections to complete gaps in existing lighting. | 635787.16 | 635787.16 | 2017-07-19 | 0 | 2019-12-19 | 2023-02-16 | 635787.16 | Authorized | Authorized | No | Closed | Federal | 0
H8-05-004 | 8 | 5949168 | 5 | San Luis Obispo County | San Luis Obispo County | SLOCOG | SLOCOG | Burton Drive and Main Street, Cambria; Price Canyon Road, Unincorporated San Luis Obispo County; and Division Street, Nipomo. | Upgrade the 1.33 miles of existing metal beam guardrail and end treatments. | 1196800 | 1196800 | 2017-07-19 | 0 | 2019-12-19 | 0 | 1182071.31 | Authorized | Authorized | No | CON | Federal | 0
H8-05-005 | 8 | 5949169 | 5 | San Luis Obispo County | San Luis Obispo County | SLOCOG | SLOCOG | Three (3) crosswalk locations: Ontario Road at the Bob Jones Trail in Avila Beach, North Ocean Avenue between Cayucos Drive and E Street in Cayucos and Tefft Street at Dana Elementary School in Nipomo. | Install an overhead flashing beacon on Ontario Road at the Bob Jones Trail in Avila Beach, with upgrades to existing advanced pedestrian beacons; Install Rectangular Rapid Flashing Beacons (RRFB’s) on North Ocean Avenue at the existing mid-block crossing, along with the installation of bulbouts in order to minimize the crossing distance; and Install RRFB’s on Tefft Street at Dana Elementary at the existing pedestrian crossing. | 427912.17 | 244700 | 2017-07-19 | 0 | 2019-12-27 | 2023-02-15 | 244700 | Authorized | Authorized | No | Closed | Federal | 0
H8-05-006 | 8 | 5949170 | 5 | San Luis Obispo County | San Luis Obispo County | SLOCOG | SLOCOG | Los Berros Road between Pomeroy Road and Quailwood Lane | Construct shoulder widening for six foot Class II bike lanes. | 2111201.01 | 698790 | 2017-06-29 | 0 | 2020-01-03 | 2022-07-27 | 698790 | Authorized | Authorized | No | Closed | Federal | 0
H9-05-003 | 9 | 5949176 | 5 | San Luis Obispo County | San Luis Obispo County | SLOCOG | SLOCOG | Various metal beam guardrail locations on Los Osos Valley Rd., South Bay Blvd., Ninth St., and Pecho Valley Rd. in Los Osos; Windsor Blvd., Moonstone Beach Dr., and Charing Ln St in Cambria | Upgrade 0.52 miles of existing meal beam guardrail and end treatments in compliance with state and federal standards. | 1140936.09 | 1059300 | 2019-09-05 | 0 | 2021-12-13 | 2023-09-14 | 1059300 | Authorized | Authorized | No | Closed | Federal | 0
H9-05-004 | 9 | 5949177 | 5 | San Luis Obispo County | San Luis Obispo County | SLOCOG | SLOCOG | Non-signalized intersections of Vineyard Dr at Santa Rita Rd, South Bay Blvd at Pismo Ave, South Bay Blvd at Los Olivos Ave, Noyes Rd at Printz Rd, and Price Canyon Rd at Ormonde Rd. | Install LED street lights. | 539733.51 | 515519.06 | 2019-09-05 | 0 | 2021-12-30 | 2026-03-26 | 515519.06 | Authorized | Authorized | No | Closed | Federal | 0
HRRR1-05-040 | 1 | 5949111 | 5 | San Luis Obispo County | San Luis Obispo County | SLOCOG | SLOCOG | Templeton Rd., from So El Pomar to SR 41 | Widen or Improve Shoulder | 996107.02 | 893388.53 | 0 | 0 | 2012-09-04 | 2015-09-16 | 893388.53 | No PE | Authorized | No | Closed | Federal | 0
HSIP1-05-005 | 1 | 5949108 | 5 | San Luis Obispo County | San Luis Obispo County | SLOCOG | SLOCOG | El Camino Real At Carmel Road. | Widen Existing Roadway To Construct Standard Left Turn Lanes At The Nb And Sb Approaches To The Intersection. | 783197.11 | 349999.98 | 0 | 0 | 2009-04-17 | 2012-01-20 | 349999.98 | No PE | Authorized | No | Closed | Federal | 0
HSIP2-05-007 | 2 | 5949112 | 5 | San Luis Obispo County | San Luis Obispo County | SLOCOG | SLOCOG | Hutton Rd. Between The Nipomo Creek Bridge And Sr 166 | Widen Shoulders; Stripe For Bicycle Lane. | 667570.48 | 512492.3 | 2009-03-13 | 0 | 2010-05-18 | 2012-01-20 | 512492.3 | Authorized | Authorized | No | Closed | Federal | 0
HSIP4-05-006 | 4 | 5949133 | 5 | San Luis Obispo County | San Luis Obispo County | SLOCOG | SLOCOG | La Panza Rd. between Ryan Rd. and Hord Valley Rd. | Widen roadway and pave shoulders; improve horizontal alignment; flatten side slopes | 1113722.11 | 900000 | 0 | 0 | 2013-11-15 | 2015-08-25 | 900000 | No PE | Authorized | No | Closed | Federal | 0
HSIP5-05-006 | 5 | 5949148 | 5 | San Luis Obispo County | San Luis Obispo County | SLOCOG | SLOCOG | Buckley Rd. from approximately 1000' W of Thread Ln. to 50' E of Thread Ln. | Install two-way left-turn lane; widen shoulders | 1031561.06 | 928405.18 | 2013-03-22 | 2013-12-30 | 2015-06-30 | 2018-03-28 | 928405.18 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-05-007 | 5 | 5949149 | 5 | San Luis Obispo County | San Luis Obispo County | SLOCOG | SLOCOG | River Rd. between Magdalena Dr. and Mission Ln. | Widen roadway and pave shoulders | 1188140.25 | 996206.2 | 2013-03-22 | 0 | 2015-03-25 | 2016-11-01 | 996206.2 | Authorized | Authorized | No | Closed | Federal | 0
HSIP6-05-004 | 6 | 5949154 | 5 | San Luis Obispo County | San Luis Obispo County | SLOCOG | SLOCOG | Various locations throughout San Luis Obispo County | Install center line rumble strips | 836788.13 | 832379.47 | 2014-09-16 | 0 | 2015-10-29 | 2018-03-28 | 832379.47 | Authorized | Authorized | No | Closed | Federal | 0
HSIP7-05-013 | 7 | 5949159 | 5 | San Luis Obispo County | San Luis Obispo County | SLOCOG | SLOCOG | Various curves throughout the unincorporated areas of San Luis Obispo County: Buckley Rd, Corbett Canyon Rd, Creston Rd, Division St, El Camino Real, El Pomar Dr, Higuera St, Hutton Rd, Los Berros Rd, Orchard Ave, Valley Rd, and Vineyard Dr. | Install 22 dynamic speed warning sign assemblies | 346289.61 | 346289.61 | 2016-07-26 | 0 | 2017-11-29 | 2019-06-12 | 346289.61 | Authorized | Authorized | No | Closed | Federal
H10-05-011n010 | 10 | 5007092 | 5 | Santa Barbara | Santa Barbara County | SBCAG | SBCAG | Intersections of De La Vina St at Los Olivos St and De La Vina at Pedregosa. | Provide enhanced crosswalk features. Enhancements include curb extensions, signs/markings, and intersection lighting. | 703300 | 703300 | 2021-09-02 | 2023-09-18 | 2024-03-25 | 0 | 703300 | Authorized | Authorized | No | CON | State | 0
H10-05-012 | 10 | 5007093 | 5 | Santa Barbara | Santa Barbara County | SBCAG | SBCAG | Uncontrolled crossing at San Andres St & Sola St. | Install rectangular rapid flashing beacons (RRFBs). | 65000 | 65000 | 2021-09-02 | 2023-09-18 | 0 | 0 | 65000 | Authorized | No CON | No | ROW | State | 0
H10-05-013 | 10 | 5007094 | 5 | Santa Barbara | Santa Barbara County | SBCAG | SBCAG | Mission Street from Gillespie Street to Anacapa Street, and State Street from Micheltorena Street to Mission Street. | Install lighting; install dedicated left turn lane on southbound State Street at Mission Street. | 2476541 | 2374800 | 2021-09-02 | 0 | 2024-03-06 | 0 | 2274800 | Authorized | Authorized | No | CON | State | 0
H10-05-014 | 10 | 5007095 | 5 | Santa Barbara | Santa Barbara County | SBCAG | SBCAG | Cliff Drive between Alan Road and Las Positas Road, and uncontrolled crossing at San Andres St & Sola St. | Install RRFB's, new and relocated ADA access ramps for improved sight lines, and 340 feet of sidewalk. | 1373300 | 1373300 | 2021-09-02 | 2023-09-18 | 2023-12-07 | 0 | 1373300 | Authorized | Authorized | No | CON | State | 0
H11-05-008 | 11 | 5007102 | 5 | Santa Barbara | Santa Barbara County | SBCAG | SBCAG | Las Positas Road at Stanley Drive. | Install rectangular rapid flashing beacons, intersection lighting, and a pedestrian refuge island at an uncontrolled crossing location. | 887400 | 798660 | 2023-03-28 | 0 | 2023-12-07 | 0 | 798660 | Authorized | Authorized | No | CON | State | 0
H11-05-009 | 11 | 5007103 | 5 | Santa Barbara | Santa Barbara County | SBCAG | SBCAG | Uncontrolled crossing location of De La Vina at Valerio. | Install curb extensions and signs/markings to increase pedestrian visibility and decrease crossing distances. | 276500 | 248850 | 2023-03-28 | 0 | 2024-05-15 | 0 | 248850 | Authorized | Authorized | No | CON | State | 0
H12-05-008 | 12 | 5007106 | 5 | Santa Barbara | Santa Barbara County | SBCAG | SBCAG | Three uncontrolled crossing locations: La Colina Rd at Hope Elementary, Hope Ave at Monte Vista Elementary, and Hope Ave At Pueblo Ave. | Install curb extensions, rectangular rapid flashing beacons (RRFBs), lighting, and markings. | 388800 | 349920 | 2025-06-10 | 0 | 2026-02-25 | 0 | 349920 | Authorized | Authorized | No | CON | State | 0
H12-05-009 | 12 | 5007107 | 5 | Santa Barbara | Santa Barbara County | SBCAG | SBCAG | Cota Street from Milpas Street to Santa Barbara Street. | Install a doweled concrete curb to provide a continuous physical separation between cyclists and motorists. | 388800 | 349920 | 2025-06-10 | 0 | 0 | 0 | 22860 | Authorized | Due by 3/31/2028 | No | PE | State | 0
H12-05-010 | 12 | 5007101 | 5 | Santa Barbara | Santa Barbara County | SBCAG | SBCAG | Cliff Drive between Mira Mesa Dr and Loma Alta Dr. | Install lighting. | 1050600 | 945540 | 0 | 0 | 0 | 0 | 0 | No PE | Due by 3/31/2028 | No | Not Started | State | 0
H12-05-011 | 12 | 5007109 | 5 | Santa Barbara | Santa Barbara County | SBCAG | SBCAG | Various traffic signal locations. | Install improved traffic signal hardware, intersection lighting, and install leading pedestrian intervals (LPIs). | 4134700 | 3721230 | 2025-11-12 | 0 | 0 | 0 | 202500 | Authorized | Due by 3/31/2028 | No | PE | Federal | 2
H12-05-012 | 12 | 5007110 | 5 | Santa Barbara | Santa Barbara County | SBCAG | SBCAG | Four (4) non-signalized intersections: Calle Cesar Chavez at Yanonali, Garden & Cota, Milpas Roundabout, and Yanonali at Helena. | Implement pedestrian crossing improvements, including intersection lighting, rectangular rapid flashing beacons (RRFBs), and curb extensions. | 2361200 | 2125080 | 2025-11-13 | 0 | 0 | 0 | 211500 | Authorized | Due by 3/31/2028 | No | PE | Federal | 2
H12-05-013 | 12 | 5007100 | 5 | Santa Barbara | Santa Barbara County | SBCAG | SBCAG | Eight (8) signalized intersections along Milpas Street. | Install reflective backplates and poles. | 430600 | 387540 | 0 | 0 | 0 | 0 | 0 | No PE | Due by 3/31/2028 | No | Not Started | State | 0
H8-05-007 | 8 | 5007076 | 5 | Santa Barbara | Santa Barbara County | SBCAG | SBCAG | Perimeter around downtown Santa Barbara, including parts of De La Vina Street, Chapala Street, Sola Street, Anacapa Street, and Gutierrez Street. | Install new corridor and crosswalk lighting, new marked pedestrian crosswalks, yield lines, and warning signs, and install new edgelines. | 1675438.79 | 1675438.79 | 2017-07-06 | 0 | 2020-07-13 | 2023-06-16 | 1675438.79 | Authorized | Authorized | No | Closed | Federal | 0
H8-05-008 | 8 | 5007077 | 5 | Santa Barbara | Santa Barbara County | SBCAG | SBCAG | Carrillo St between Miramonte Dr and Bath St and Miramonte St between Carrillo St and Bel Monte Dr. | Add segment lighting and install protected left-turn phase. | 1893600 | 1893600 | 2017-07-06 | 2020-02-10 | 2021-01-13 | 0 | 1793600 | Authorized | Authorized | No | CON | Federal | 0
H9-05-005 | 9 | 5007088 | 5 | Santa Barbara | Santa Barbara County | SBCAG | SBCAG | Intersections of Bath Street at Victoria Street and Bath Street & Sola Street. | Provide enhanced crosswalk features at two uncontrolled crossings, including curb extensions and intersection lighting. | 73993.94 | 73993.94 | 2019-09-05 | 2020-10-16 | 0 | 2022-06-09 | 73993.94 | Authorized | No CON | No | Closed | Federal | 0
H9-05-006 | 9 | 5007089 | 5 | Santa Barbara | Santa Barbara County | SBCAG | SBCAG | The intersection of Canon Perdido Street at Nopal Street. | Provide enhanced crosswalk features at an uncontrolled crossings adjacent to a high school. Enhancements include curb extensions and intersection lighting. | 26000 | 26000 | 2019-09-05 | 0 | 0 | 2023-02-10 | 26000 | Authorized | No CON | No | Closed | Federal | 0
H9-05-007 | 9 | 5007090 | 5 | Santa Barbara | Santa Barbara County | SBCAG | SBCAG | The intersection of Salinas Street and Old Coast Highway/Punta Gorda St. | Provide enhanced crosswalk features to improve pedestrian safety: curb extensions, pedestrian refuge island, and improved lighting. | 1429304.31 | 1429304.31 | 2019-09-05 | 2021-01-14 | 2022-04-04 | 2026-03-10 | 1429304.31 | Authorized | Authorized | No | Closed | Federal | 0
HSIP3-05-001 | 3 | 5007049 | 5 | Santa Barbara | Santa Barbara County | SBCAG | SBCAG | Intersection Of Carrillo St. And Anacapa St. | Install Mast Arms, Pedestrian Heads And Safety Lighting; Reconstruct Curb, Gutter, Sidewalk And Curb Ramps | 517128 | 400000 | 0 | 0 | 2011-08-17 | 2015-02-27 | 400000 | No PE | Authorized | No | Closed | Federal | 0
HSIP4-05-003 | 4 | 5007056 | 5 | Santa Barbara | Santa Barbara County | SBCAG | SBCAG | De La Vina St./Figueroa St. | Install pedestrian crossing and safety lighting | 382636.77 | 326079.58 | 0 | 0 | 2013-01-02 | 2015-12-08 | 326079.58 | No PE | Authorized | No | Closed | Federal | 0
HSIP5-05-008 | 5 | 5007057 | 5 | Santa Barbara | Santa Barbara County | SBCAG | SBCAG | Cabrillo Blvd./Anacapa St.; Cabrillo Blvd./Corona Del Mar; State St./Calle Palo Colorado; State St./Islay St.; State St./Pedregosa St. | Provide enhanced pedestrian crossing safety features | 998164.51 | 763490.2 | 0 | 0 | 2015-07-06 | 2018-05-01 | 763490.2 | No PE | Authorized | No | Closed | Federal | 0
HSIP5-05-009 | 5 | 5007058 | 5 | Santa Barbara | Santa Barbara County | SBCAG | SBCAG | 40 signalized intersections within the City | Install pedestrian countdown heads; modify traffic signals | 1292005.69 | 1162805.09 | 0 | 0 | 2015-06-16 | 2017-04-24 | 1162805.09 | No PE | Authorized | No | Closed | Federal | 0
HSIP6-05-005 | 6 | 5007064 | 5 | Santa Barbara | Santa Barbara County | SBCAG | SBCAG | De La Vina St/W Arrellaga St | Install traffic signal | 189116.14 | 141100 | 0 | 0 | 2014-07-23 | 2016-05-11 | 141100 | No PE | Authorized | No | Closed | Federal | 0
HSIP7-05-008 | 7 | 5007073 | 5 | Santa Barbara | Santa Barbara County | SBCAG | SBCAG | 23 signalized intersections within the City of Santa Barbara | Increasing head size from 8" to 12" | 226592.22 | 194270.93 | 2016-07-26 | 0 | 2017-08-16 | 2021-05-27 | 194270.93 | Authorized | Authorized | No | Closed | Federal
HSIP7-05-009 | 7 | 5007074 | 5 | Santa Barbara | Santa Barbara County | SBCAG | SBCAG | Two Intersections: 1) Alamar Avenue & Puesta Del Sol; & 2) La Cumbre Road & Calle Cita | Provide enhanced crosswalk features including curb extensions, street lighting, and rectangular rapid flashing beacons | 834160.53 | 726800 | 2016-08-22 | 0 | 2019-03-11 | 2020-11-02 | 726800 | Authorized | Authorized | No | Closed | Federal
H10-05-015 | 10 | 5951174 | 5 | Santa Barbara County | Santa Barbara County | SBCAG | SBCAG | Various locations in the unincorporated areas of Santa Barbara County. | Stripe new 6" edgeline on 2 lane roads with characteristics of systemic safety issue of roadway departures as identified in the Santa Barbara County Local Road Safety Plan. | 248000 | 248000 | 0 | 0 | 2023-03-22 | 2024-12-10 | 248000 | No PE | Authorized | No | Closed | State | 0
H10-05-016 | 10 | 5951175 | 5 | Santa Barbara County | Santa Barbara County | SBCAG | SBCAG | Gibraltar Road, 2.5 miles south of East Camino Cielo. | Install metal beam guardrail. | 177486 | 177486 | 2021-07-30 | 0 | 2023-10-07 | 2024-12-10 | 177486 | Authorized | Authorized | No | Closed | State | 0
H11-05-010 | 11 | 5951181 | 5 | Santa Barbara County | Santa Barbara County | SBCAG | SBCAG | Various locations on Harris Grade Rd. Location 1: between 3,168' and 3,696' south of SR-135; Location 2: between 6,364' and 6,864' south of SR-135; Location 3: approx. 16,770' south of SR-135; and Location 4: between 5,280' and 7,920' north of Rucker Rd. | Install new Midwest Guardrail System, chevrons, and object markers. | 243000 | 218700 | 2023-09-05 | 0 | 2025-11-20 | 0 | 218700 | Authorized | Authorized | No | CON | Federal | 1
H11-05-011 | 11 | 5951182 | 5 | Santa Barbara County | Santa Barbara County | SBCAG | SBCAG | Multiple locations across Santa Barbara County: Foxen Canyon Road, Harris Grade Road, Dominion Road, Las Palmas Drive, and Betteravia Road. | Upgrade existing Metal Beam Guardrail and end treatments to current Caltrans standards with Midwest Guardrail System. | 445470 | 400923 | 2023-09-05 | 0 | 2026-01-05 | 0 | 400923 | Authorized | Authorized | No | CON | Federal | 1
H11-05-012 | 11 | 5951183 | 5 | Santa Barbara County | Santa Barbara County | SBCAG | SBCAG | Lillie Avenue (Summerland); Hot Springs Rd (Montecito); Embarcadero del Mar / Embarcadero del Norte / Camino Pescadero / Camino del Sol (Isla Vista). | Install Rectangular Rapid Flashing Beacons. | 286561 | 250000 | 2023-07-05 | 0 | 2023-11-27 | 0 | 211500 | Authorized | Authorized | No | CON | State | 0
H12-05-014 | 12 | 5951188 | 5 | Santa Barbara County | Santa Barbara County | SBCAG | SBCAG | Various locations: Ray Rd, Brown Rd, Dominion Rd ,Palmer Rd, Foxen Canyon Rd, Santa Rosa Rd, Calzada Av, Central Av, and Glen Annie Rd. | Install edgelines. | 385000 | 346500 | 2025-05-08 | 0 | 0 | 0 | 13500 | Authorized | Due by 3/31/2028 | No | PE | State | 0
H12-05-015 | 12 | 5951189 | 5 | Santa Barbara County | Santa Barbara County | SBCAG | SBCAG | Locations include 1: Brown Rd; 2: Black Rd; 3: Lompoc Casmilia Rd; 4: Harris Grade Rd; 5/6: Harris Grade Rd; 7: Santos Rd; 8: Avenue of Flags Rd; 9: Ladan Dr; 10: Sagunto St; 11: Paradise Rd; 12-14: Stagecoach Rd; and 15: Roble Dr. | Upgrade existing Metal Beam Guardrail (MBGR) to Midwest Guardrail System (MGS). | 890000 | 801000 | 2025-05-05 | 0 | 0 | 0 | 35100 | Authorized | Due by 3/31/2028 | No | PE | Federal | 1
H12-05-016 | 12 | 5951190 | 5 | Santa Barbara County | Santa Barbara County | SBCAG | SBCAG | Eight (8) pedestrian crossings: Joe Nightingale Elementary (2); Patterson Elementary (2); Calzada Av & Pine St; Burton Mesa Blvd & Calle Quarta; Cathedral Oaks Rd & Camino del Retiro; and Cathedral Oaks Rd & Via Chaparral. | Install rectangular rapid flashing beacons (RRFBs); and install raised concrete Pedestrian Refuge Islands at two of the crosswalks. | 388000 | 349200 | 2025-05-07 | 0 | 0 | 0 | 22500 | Authorized | Due by 3/31/2028 | No | PE | State | 0
H12-05-017 | 12 | 5951191 | 5 | Santa Barbara County | Santa Barbara County | SBCAG | SBCAG | Unincorporated public roads: 1) El Colegio Road in Isla Vista; 2) Orcutt Road in Orcutt; and 3) Stillwell Road in Orcutt. | Install Class II bike lanes and close a bikeway gap (Stillwell Rd); install/upgrade existing buffered bike lanes to protected bike lanes (Orcutt Rd and El Colegio Rd). | 362000 | 325800 | 2025-04-25 | 0 | 0 | 0 | 15750 | Authorized | Due by 3/31/2028 | No | PE | State | 0
H9-05-008 | 9 | 5951168 | 5 | Santa Barbara County | Santa Barbara County | SBCAG | SBCAG | Various existing traffic signals and Various crosswalk locations in the unincorporated communities in Santa Barbara County. | Upgrade 206 pedestrian signal heads to new LED countdown signal head at 31 signalized locations; Improve pedestrian safety at uncontrolled crosswalk locations with RRFBs, medians, signs, striping. | 119516.76 | 119516.76 | 0 | 0 | 2021-05-26 | 2024-06-05 | 119516.76 | No PE | Authorized | No | Closed | Federal | 0
H9-05-009 | 9 | 5951169 | 5 | Santa Barbara County | Santa Barbara County | SBCAG | SBCAG | Various locations in the unincorporated areas of Santa Barbara County. | Upgrade existing Tuthill railing to current standard guardrail (Midwest Guardrail System). | 215800 | 215800 | 0 | 0 | 2022-01-20 | 0 | 215800 | No PE | Authorized | No | CON | Federal | 1
H9-05-010 | 9 | 5951170 | 5 | Santa Barbara County | Santa Barbara County | SBCAG | SBCAG | Various locations in the unincorporated areas of Santa Barbara County. | Install W1-8 or W1-6 at all locations with a existing horizontal alignment sign on County of Santa Barbara roads. | 29424.71 | 29424.71 | 0 | 0 | 2021-10-27 | 2024-06-25 | 29424.71 | No PE | Authorized | No | Closed | Federal | 0
HRRR1-05-041 | 1 | 5951115 | 5 | Santa Barbara County | Santa Barbara County | SBCAG | SBCAG | Harris Grade Rd., approximately 1 mile South of SR 135 | Superelevation Improvement; Flatten Side Slopes | 708938.79 | 611816.08 | 2007-12-28 | 2009-11-02 | 2010-05-25 | 2012-07-26 | 611816.08 | Authorized | Authorized | No | Closed | Federal | 0
HRRR2-05-042C | 2 | 5951116 | 5 | Santa Barbara County | Santa Barbara County | SBCAG | SBCAG | Tepusquet Road at MP 5.9 between Foxen Canyon Road and SR 166 | Widen and improve shoulder; widen travel lanes; reconstruct slope embankment and 400 LF of roadway | 500188.52 | 421040.3 | 2008-04-10 | 2009-04-09 | 2010-02-01 | 2012-03-29 | 421040.3 | Authorized | Authorized | No | Closed | Federal | 0
HSIP2-05-008 | 2 | 5951122 | 5 | Santa Barbara County | Santa Barbara County | SBCAG | SBCAG | Approx. 6 Miles East Of The City Of Santa Maria At The Intersection Of Foxen Cyn Rd., And Santa Maria Mesa Road. | Realignment Of Roadway | 364150.01 | 321364.19 | 2009-01-15 | 2010-04-28 | 2010-10-15 | 2012-04-13 | 321364.19 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-05-010 | 5 | 5951149 | 5 | Santa Barbara County | Santa Barbara County | SBCAG | SBCAG | Clark Ave./SR 101 NB on and off-ramps | Install traffic signals; realign roadway | 2196532 | 900000 | 0 | 0 | 2019-05-02 | 2021-09-16 | 900000 | No PE | Authorized | No | Closed | Federal | 0
HSIP5-05-011 | 5 | 5951150 | 5 | Santa Barbara County | Santa Barbara County | SBCAG | SBCAG | W Betteravia Rd. (Simas Rd.) between Black Rd. and W Main St. | Instal rumble strips and flashing beacons | 735315.13 | 661783.19 | 2013-06-21 | 0 | 2015-04-07 | 2016-11-21 | 661783.19 | Authorized | Authorized | No | Closed | Federal | 0
HSIP2-05-011 | 2 | 6090059 | 5 | Santa Barbara County Association of Governments | Santa Barbara County | SBCAG | SBCAG | Cabrillo Blvd, 0.1 Mile South Of Highway 1 | Replace Existing Rr Bridge And Construct Roadway Improvements For Bicyclists And Pedestrians. | 1000000 | 900000 | 2014-11-18 | 0 | 0 | 2023-12-01 | 900000 | Authorized | No CON | No | Closed | Federal | 0
H10-05-017 | 10 | 5025078 | 5 | Santa Cruz | Santa Cruz County | AMBAG | SCCRTC | Six locations at unsignalized locations throughout the City of Santa Cruz. | Install RRFBs at unsignalized locations to improve pedestrian safety, including pedestrian signs, advanced yield lines with associated signs, and high visibility crosswalk markings. | 250000 | 250000 | 2021-10-19 | 0 | 2022-10-19 | 2025-01-06 | 250000 | Authorized | Authorized | No | Closed | State | 0
H10-05-018 | 10 | 5025079 | 5 | Santa Cruz | Santa Cruz County | AMBAG | SCCRTC | Signalized intersections throughout the City of Santa Cruz. | Install Advanced Dilemma Zone Detection & Retroreflective Borders on Traffic Signal Backplates. | 1257600 | 1257600 | 2021-10-19 | 0 | 2024-09-09 | 0 | 1257600 | Authorized | Authorized | No | CON | State | 0
H11-05-013 | 11 | 5025087 | 5 | Santa Cruz | Santa Cruz County | AMBAG | SCCRTC | Various non-signalized intersections at five locations. | Install signage, striping, islands and RRFBs. | 276800 | 249120 | 2023-10-27 | 0 | 0 | 0 | 13500 | Authorized | Due by 9/30/2026 | No | PE | State | 0
H12-05-018 | 12 | 5025089 | 5 | Santa Cruz | Santa Cruz County | AMBAG | SCCRTC | Various non-signalized intersections. | Implement daylighting and pedestrian crossing improvements. | 2147000 | 1932300 | 2025-04-17 | 0 | 0 | 0 | 45000 | Authorized | Due by 3/31/2028 | No | PE | Federal | 2
H12-05-019 | 12 | 5025090 | 5 | Santa Cruz | Santa Cruz County | AMBAG | SCCRTC | Non-signalized intersections of High/Cardiff and Soquel/Poplar. | Install signage, striping, bulb-outs, islands and rectangular rapid flashing beacons (RRFBs). | 387900 | 349110 | 2025-04-09 | 0 | 0 | 0 | 54000 | Authorized | Due by 3/31/2028 | No | PE | State | 0
H12-05-020 | 12 | 5025091 | 5 | Santa Cruz | Santa Cruz County | AMBAG | SCCRTC | Water Street between North Branciforte Avenue and Poplar Avenue | Construct separated bike lanes on Water Street to fill a network gap and connect to existing separated bike infrastructure in a high active transportation use area. | 381000 | 342900 | 2025-04-17 | 0 | 0 | 0 | 54000 | Authorized | Due by 3/31/2028 | No | PE | State | 0
H8-05-010 | 8 | 5025068 | 5 | Santa Cruz | Santa Cruz County | AMBAG | SCCRTC | Various locations at unsignalized locations throughout the City of Santa Cruz. | Install crosswalk enhancements including pedestrian signs, advanced yield lines with associated signs, high visibility crosswalk markings, bulbouts and Rectangular Rapid Flashing Beacons (RRFBs). | 1150343.65 | 1150343.65 | 2017-12-15 | 0 | 2019-12-17 | 2021-11-21 | 1150343.65 | Authorized | Authorized | No | Closed | Federal | 0
HSIP2-05-001 | 2 | 5025043 | 5 | Santa Cruz | Santa Cruz County | AMBAG | SCCRTC | Soquel Ave. At Hageman Ave., In The City Of Santa Cruz | Install Left-Turn Lane. | 175567.53 | 158010.77 | 2009-07-10 | 0 | 2009-10-16 | 2012-01-20 | 158010.77 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-05-012 | 5 | 5025059 | 5 | Santa Cruz | Santa Cruz County | AMBAG | SCCRTC | Soquel Ave./Park Way (including approaches) | Widen roadway; install left-turn lanes; upgrade traffic signals | 553525.96 | 255000 | 0 | 0 | 2013-07-25 | 2015-12-08 | 255000 | No PE | Authorized | No | Closed | Federal | 0
HSIP6-05-006 | 6 | 5025062 | 5 | Santa Cruz | Santa Cruz County | AMBAG | SCCRTC | Various locations throughout Santa Cruz | Upgrade traffic signals; install pedestrian countdown heads | 533636.68 | 530905.27 | 2014-07-23 | 0 | 2015-07-23 | 2017-10-19 | 530905.27 | Authorized | Authorized | No | Closed | Federal | 0
HSIP7-05-004 | 7 | 5025066 | 5 | Santa Cruz | Santa Cruz County | AMBAG | SCCRTC | Bay Street between Escalona Drive and King Street | Sidewalk completion on the west side of Bay Street | 629504.96 | 566554.45 | 2016-08-06 | 0 | 2018-05-24 | 2020-03-30 | 566554.45 | Authorized | Authorized | No | Closed | Federal
HSIP7-05-005 | 7 | 5025067 | 5 | Santa Cruz | Santa Cruz County | AMBAG | SCCRTC | Bay Street between Escalona Drive and King Street | Protected left turn phase at Bay Street/King Street and segment lighting on Bay Street between Escalona Drive and King Street | 346841.82 | 346841.82 | 2016-08-06 | 0 | 2018-05-24 | 2020-03-26 | 346841.82 | Authorized | Authorized | No | Closed | Federal
H10-05-019 | 10 | 5936149 | 5 | Santa Cruz County | Santa Cruz County | AMBAG | SCCRTC | Empire Grade at Chinquapin Trail; Rio del Mar Blvd at Deer Park Marketplace; Summit Rd at Loma Prieta Elementary School; Trout Gulch at Valencia St; and Green Valley Rd at Pinto Lake County Park. | Install Rectangular Rapid Flashing Beacons (RRFBs) with ADA improvements. Install sign and pavement marking pedestrian crossing enhancements. | 250000 | 250000 | 2021-12-29 | 0 | 2025-03-28 | 0 | 250000 | Authorized | Authorized | No | CON | State | 0
H8-05-011 | 8 | 5936135 | 5 | Santa Cruz County | Santa Cruz County | AMBAG | SCCRTC | La Madrona Drive, El Rancho Drive, and Swanton Road. | Upgrade existing guardrails. | 1534859 | 1383200 | 2018-02-06 | 0 | 2021-01-22 | 0 | 1182113 | Authorized | Authorized | No | CON | Federal | 0
H9-05-011 | 9 | 5936140 | 5 | Santa Cruz County | Santa Cruz County | AMBAG | SCCRTC | Various locations on Old Santa Cruz Highway, Spreckels Drive, Buena Vista Drive, Mt. Madonna Road, and Lompico Road. | Upgrade single beam guardrail to w-beam guardrail. | 500000 | 500000 | 2019-09-05 | 0 | 2024-01-25 | 0 | 417538 | Authorized | Authorized | No | CON | Federal | 0
H9-05-012 | 9 | 5936139 | 5 | Santa Cruz County | Santa Cruz County | AMBAG | SCCRTC | Four (4) locations including Graham Hill Road near Covered Bridge Road, 7th Avenue at Bonnie St, Soquel Drive 1250 ft southeast of State Park Drive, and Green Valley Road at Amesti Road. | Install Rectangular Rapid Flashing Beacons (RRFBs) at four locations and four concrete landings with ramps. Install sign and pavement marking pedestrian crossing enhancements consistent with CA MUTCD. | 520000 | 520000 | 2019-09-05 | 0 | 2022-09-09 | 0 | 520000 | Authorized | Authorized | No | CON | Federal | 0
H9-05-014 | 9 | 6205025 | 5 | Santa Cruz County | Santa Cruz County | AMBAG | SCCRTC | Five (5) uncontrolled intersections on SR9 through San Lorenzo Valley, including SR9/Redwood Dr in Felton, SR9 crossing between Graham Hill Rd and Kirby St in Felton, SR9 crossing between Fall Creek Dr and Lazy Woods Rd at the SLV elementary school entrance in Felton, SR9/Lazy Woods Rd in Felton, and SR9/Clear Creek Rd in Brookdale | Install combinations of high visibility striping and signage, advance warning flashing beacons, and Rectangular Rapid Flashing Beacons (RRFBs). | 250000 | 250000 | 0 | 0 | 2020-02-03 | 2022-12-12 | 250000 | No PE | Authorized | No | Closed | Federal | 0
HSIP1-05-004 | 1 | 5936074 | 5 | Santa Cruz County | Santa Cruz County | AMBAG | SCCRTC | Intersection Of Graham Hill Road And Lockewood Lane. | Install Traffic Signal; Widen Shoulder And Lengthen Left Turn Lane On Graham Hill Road. | 556252.87 | 449999.7 | 0 | 0 | 2012-04-06 | 2014-03-31 | 449999.7 | No PE | Authorized | No | Closed | Federal | 0
HSIP2-05-003 | 2 | 5936080 | 5 | Santa Cruz County | Santa Cruz County | AMBAG | SCCRTC | Graham Hill Road, North Of Jewell Street | Upgrade Guardrail. | 123359.35 | 88535 | 2010-08-25 | 0 | 2013-04-12 | 2015-06-16 | 88535 | Authorized | Authorized | No | Closed | Federal | 0
HSIP3-05-007 | 3 | 5936100 | 5 | Santa Cruz County | Santa Cruz County | AMBAG | SCCRTC | Various Locations | Replace And Install Warning Signs And Guide Signs | 57615.28 | 51853.74 | 0 | 0 | 2013-07-25 | 2016-01-13 | 51853.74 | No PE | Authorized | No | Closed | Federal | 0
HSIP4-05-002 | 4 | 5936099 | 5 | Santa Cruz County | Santa Cruz County | AMBAG | SCCRTC | Granite Creek Rd., 0.2 mile S of Lauren Ct. | Install approximately 200' of guardrail | 123039.08 | 97951.7 | 2012-04-03 | 0 | 2015-03-13 | 2017-05-19 | 97951.7 | Authorized | Authorized | No | Closed | Federal | 0
HSIP4-05-005 | 4 | 5936098 | 5 | Santa Cruz County | Santa Cruz County | AMBAG | SCCRTC | Felton Empire Rd., 0.8 mile E of Empire Grade | Install approximately 200' of guardrail; stabilize embankment | 349525.92 | 299309.45 | 2012-04-03 | 0 | 2014-04-28 | 2018-05-01 | 299309.45 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-05-013 | 5 | 5936115 | 5 | Santa Cruz County | Santa Cruz County | AMBAG | SCCRTC | Alba Rd. 1.4 miles W of SR 9 | Install guardrail | 82597.02 | 74230.86 | 2013-08-02 | 0 | 2015-06-01 | 2018-07-05 | 74230.86 | Authorized | Authorized | No | Closed | Federal | 0
HSIP6-05-007 | 6 | 5936123 | 5 | Santa Cruz County | Santa Cruz County | AMBAG | SCCRTC | North Area of Santa Cruz County northwest of Highway 17 | Install guardrails and striping | 1089810.88 | 1086891.36 | 2015-04-01 | 0 | 2016-09-15 | 2021-07-26 | 1086891.36 | Authorized | Authorized | No | Closed | Federal | 0
HSIP6-05-008 | 6 | 5936122 | 5 | Santa Cruz County | Santa Cruz County | AMBAG | SCCRTC | Central Area of County | Install guardrails and striping | 1059252.28 | 1055357 | 2015-03-25 | 0 | 2016-09-15 | 2022-03-07 | 1055357 | Authorized | Authorized | No | Closed | Federal | 0
HSIP6-05-009 | 6 | 5936120 | 5 | Santa Cruz County | Santa Cruz County | AMBAG | SCCRTC | South Area of Santa Cruz County | Install striping | 312799.61 | 310152.37 | 2015-03-25 | 0 | 2016-09-01 | 2022-05-10 | 310152.37 | Authorized | Authorized | No | Closed | Federal | 0
HSIP7-05-006 | 7 | 5936129 | 5 | Santa Cruz County | Santa Cruz County | AMBAG | SCCRTC | On La Madrona Drive 0.2 miles south of Silverwood Drive (PM 1.82) and at La Madrona Drive near Via Vinca (PM 1.32). | Install guardrail | 267179.59 | 266259.19 | 2016-10-21 | 0 | 2019-03-26 | 2021-05-21 | 266259.19 | Authorized | Authorized | No | Closed | Federal
H10-05-020 | 10 | 5138056 | 5 | Santa Maria | Santa Barbara County | SBCAG | SBCAG | Various existing uncontrolled pedestrian crossing locations. | Enhance pedestrian crossings at uncontrolled locations using low-cost proven safety countermeasures to prevent vehicular/pedestrian collisions. | 505700 | 250000 | 0 | 0 | 2023-07-25 | 0 | 250000 | No PE | Authorized | No | CON | State | 0
H11-05-014 | 11 | 5138059 | 5 | Santa Maria | Santa Barbara County | SBCAG | SBCAG | Intersections of: Donovan Rd/Western Ave., Donovan Rd/Bay Ave, Alvin Ave/Palisade Dr., Battles Rd/Westgate Rd., and Miller Ave/Newlove Dr. | Construct/install pedestrian refuge islands, updated signage, road diets and Rectangular Rapid Flashing Beacons (RRFBs). | 275000 | 247500 | 2024-06-07 | 0 | 0 | 0 | 9000 | Authorized | Due by 8/31/2026 | No | PE | State | 0
H11-05-016 | 11 | 5138061 | 5 | Santa Maria | Santa Barbara County | SBCAG | SBCAG | Skyway Drive between Betteravia Road and State Route 135 (Broadway). | Improve 24,000 LF of existing Class II Bicycle Lanes to Class IV Bicycle Lanes through lane width reduction and installation of paint and flexible bollards. | 322200 | 249480 | 0 | 0 | 0 | 0 | 0 | No PE | Due by 8/31/2026 | No | Not Started | State | 0
H12-05-021 | 12 | 5138062 | 5 | Santa Maria | Santa Barbara County | SBCAG | SBCAG | Intersections of Cook Street and Depot Street, and Blosser Road and Boone Street. | Install compact roundabout and signalized intersection. | 1217200 | 1095480 | 2025-09-19 | 0 | 0 | 0 | 90000 | Authorized | Due by 3/31/2028 | No | PE | State | 0
H12-05-022 | 12 | 5138063 | 5 | Santa Maria | Santa Barbara County | SBCAG | SBCAG | Crossings at the intersections of Atlantic Pl./Bentley Ave., Mary Dr., Sonya Ln./Western Ave., Provance Ave./Ped.Trail, Morrison/Lincoln, and McCLelland St./ Newlove Dr. | Insall raised pedestrian crossings/speed tables, signage/striping, and rectangular rapid flashing beacons (RRFBs). | 357600 | 321840 | 2025-12-18 | 0 | 0 | 0 | 26100 | Authorized | Due by 3/31/2028 | No | PE | State | 0
H9-05-013 | 9 | 6205024 | 5 | Santa Maria | Santa Barbara County | SBCAG | SBCAG | Twenty-two (22) signalized intersections on State Route 135 (Broadway) in Santa Maria from Foster Road to Preisker Lane. | Increase visibility of traffic signal indications by installing additional traffic signal heads at the 22 intersections; and provide protected left turns at Broadway/Newlove Dr and Broadway/Morrison Drive intersections. | 3019200 | 3019200 | 0 | 0 | 2022-04-11 | 0 | 3019200 | Not Tracked | Authorized | No | CON | Federal | 0
HSIP2-05-002 | 2 | 5138039 | 5 | Santa Maria | Santa Barbara County | SBCAG | SBCAG | East Donovan Rd. And North Lynne Dr. | Install Concrete Median; Upgrade Existing Traffic Signal. | 114472.5 | 69300 | 0 | 0 | 2011-07-29 | 2013-02-14 | 69300 | No PE | Authorized | No | Closed | Federal | 0
HSIP3-05-003 | 3 | 5138043 | 5 | Santa Maria | Santa Barbara County | SBCAG | SBCAG | Intersection Of Battles Rd. And Depot St. | Widen Shoulder; Construct Curb, Gutter, Sidewalk And Curb Ramps; Relocate Street Lights | 165361.74 | 123683.92 | 0 | 0 | 2012-09-18 | 2015-02-27 | 123683.92 | No PE | Authorized | No | Closed | Federal | 0
HSIP4-05-001 | 4 | 5138044 | 5 | Santa Maria | Santa Barbara County | SBCAG | SBCAG | SR 135 (Broadway) between PM 10.93 and 17.79; SR 166 (Main St.) between PM 6.50 and 8.93 | Upgrade safety lighting | 371315.41 | 303934.66 | 0 | 0 | 2012-03-21 | 2016-01-13 | 303934.66 | No PE | Authorized | No | Closed | Federal | 0
HSIP5-05-014 | 5 | 5138049 | 5 | Santa Maria | Santa Barbara County | SBCAG | SBCAG | Depot St. from approximately 150' S of Main St. (SR 166) to approximately 150' N of Alvin Ave. | Modify traffic signal; construct sidewalks, curb ramps, predestrian refuge islands, curb and gutter; install signs, striping, and pavement markings | 579706.38 | 404800 | 2014-02-12 | 0 | 2015-07-27 | 2018-08-14 | 404800 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-05-015 | 5 | 5138050 | 5 | Santa Maria | Santa Barbara County | SBCAG | SBCAG | Stowell Rd./Entrada Way; Stowell Rd. between Broadway (SR 135) and Entrada Way | Relocate crosswalk and signs; install pedestrian refuge islands, crosswalk, flashing beacons, safety lighting, and signs | 281456.15 | 101300 | 2014-01-14 | 0 | 2015-07-14 | 2018-05-01 | 101300 | Authorized | Authorized | No | Closed | Federal | 0
HSIP7-05-010 | 7 | 5138052 | 5 | Santa Maria | Santa Barbara County | SBCAG | SBCAG | N. Blosser Rd (From W. Taylor St. to Atlantic Ave.) | Construct a central median barrier and complete the road diet feature at N. Blosser Rd. (between W. Taylor St. & Atlantic Ave) | 873592.01 | 667075.01 | 2016-08-06 | 0 | 2020-09-09 | 2023-05-01 | 667075.01 | Authorized | Authorized | No | Closed | Federal
HSIP7-05-011 | 7 | 5138053 | 5 | Santa Maria | Santa Barbara County | SBCAG | SBCAG | N. Broadway (SR-135) between Main St. (SR-166) and Mill St. | Remove part of existing median & replace with extended left turn lane, new striping and PCC median extension | 286663.63 | 212220 | 2016-08-06 | 0 | 2021-05-27 | 2024-02-15 | 212220 | Authorized | Authorized | No | Closed | Federal
H10-05-021 | 10 | 5248009 | 5 | Soledad | Monterey County | AMBAG | TAMC | Vicinity of 4 public schools: Main Street Middle School, Frank Ledesma Elementary School, Soledad High School, and Rose Ferrero Elementary School. | Install curb extensions, high-visibility crosswalks, enhanced crosswalk signage and pavement markings, Rectangular Rapid Flashing Beacons (RRFBs), and flashing beacons at stop signs. | 1126700 | 250000 | 0 | 0 | 2024-03-13 | 0 | 250000 | No PE | Authorized | No | CON | State | 0
H11-05-017 | 11 | 5248010 | 5 | Soledad | Monterey County | AMBAG | TAMC | Various locations throughout the City. | Install RRFB devices, beacons, bulb outs, crosswalks, bike boxes, streetlights, pavement markings, lead pedestrian interval timing, signage, construct median refuge islands, bike lane buffers, and roadway reconfiguration (one location). | 863600 | 777240 | 2023-05-15 | 0 | 0 | 0 | 137700 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE | State | -1
HSIP3-05-004 | 3 | 5443007 | 5 | Solvang | Santa Barbara County | SBCAG | SBCAG | Alisal Rd., Approximately 0.7 Miles South Of Santa Ynez River Bridge | Widen Shoulder; Install Warnings Signs And Edge Stripe | 287235.8 | 258160.31 | 2010-11-18 | 0 | 2012-05-17 | 2013-07-29 | 258160.31 | Authorized | Authorized | No | Closed | Federal | 0
H12-05-023 | 12 | 6171014 | 5 | University of California - Santa Cruz | Santa Cruz County | AMBAG | SCCRTC | Hagar Drive on the UCSC Campus from Coolidge Drive to East Remote Parking Lot (0.7 miles). | Install three compact roundabouts, add vertical reflectors on curves and add new delineators to create protected bike lanes. | 2309300 | 2078370 | 2025-06-13 | 0 | 0 | 0 | 180000 | Authorized | Due by 3/31/2028 | No | PE | Federal | 0
HSIP1-05-006 | 1 | 6171007 | 5 | University of California - Santa Cruz | Santa Cruz County | AMBAG | SCCRTC | Intersection Of Empire Grade Drive And Heller Drive At The West Entrance To Uc Santa Cruz. | Install Traffic Signal And Safety Lighting. | 408384 | 367545 | 2008-01-11 | 0 | 2009-12-14 | 2012-02-29 | 367545 | Authorized | Authorized | No | Closed | Federal | 0
H9-05-016 | 9 | 5031036 | 5 | Watsonville | Santa Cruz County | AMBAG | SCCRTC | The intersection of Airport Boulevard and Holm Road. | Install traffic signal, curb ramps, striping and signing. | 502664.15 | 495336.71 | 0 | 0 | 2020-03-05 | 2022-12-08 | 495336.71 | No PE | Authorized | No | Closed | Federal | 0
HSIP6-05-010 | 6 | 5031027 | 5 | Watsonville | Santa Cruz County | AMBAG | SCCRTC | On Airport Blvd between East of Watsonville City Limits to Freedom Blvd | Widen roadway; Upgrade curbs, curb ramps, gutter, and sidewalk; Construct refuge island; Install Rectangular flashing beacon and striping; Relocate bus stop and crosswalk | 529399.78 | 335662.94 | 2015-03-25 | 0 | 2017-10-20 | 2020-11-02 | 335662.94 | Authorized | Authorized | No | Closed | Federal | 0
HSIP6-06-001b | 6 | 6206029 | 6 | Arvin | Kern County | KCOG | KCOG | Bear Mountain Blvd (SR 223)/Derby St | Install traffic signals, railroad crossings, upgrade and install new pavement, striping and pavement markers | 2016000 | 498175 | 0 | 0 | 2020-11-03 | 0 | 498175 | No PE | Authorized | No | CON | Federal | 0
H12-06-001 | 12 | 5424013 | 6 | Avenal | Kings County | KCAG | KCAG | The intersection of San Joaquin St and Park Ave. | Upgrade pedestrian crossing with rectangular rapid flashing beacons (RRFBs), curb extensions, traffic signs, stripes and pavement markings. | 350000 | 315000 | 2025-09-23 | 0 | 0 | 0 | 54000 | Authorized | Due by 3/31/2028 | No | PE | State | 0
H12-06-002 | 12 | 5424014 | 6 | Avenal | Kings County | KCAG | KCAG | Along First Avenue from Kings Street to Reef-Sunset Middle School. | Install buffered Class II bicycle lanes. | 350000 | 315000 | 2025-09-24 | 0 | 0 | 0 | 51300 | Authorized | Due by 3/31/2028 | No | PE | State | 0
H12-06-003 | 12 | 5424015 | 6 | Avenal | Kings County | KCAG | KCAG | On Avenal Cutoff Road approximately 100 feet southwest of the California Aqueduct. | Upgrade existing guardrails and end treatments. | 600000 | 540000 | 2025-09-24 | 0 | 0 | 0 | 90000 | Authorized | Due by 3/31/2028 | No | PE | State | 0
H10-06-001 | 10 | 5109279 | 6 | Bakersfield | Kern County | KCOG | KCOG | Old Farm Road in front of existing Veterans Elementary School at existing crosswalk near Cherry Valley Avenue, and Mountain Vista Drive in front of existing Earl Warren Junior High School at existing crosswalk near Mount Snow Lane. | Install flashing yellow beacons near existing crosswalks to enhance visibility and slow down vehicular traffic. | 246100 | 246100 | 0 | 0 | 2023-08-14 | 2025-01-06 | 246100 | No PE | Authorized | No | Closed | State | 0
H10-06-002 | 10 | 5109280 | 6 | Bakersfield | Kern County | KCOG | KCOG | Intersection of Beale Avenue and Monterey Street and intersection of Beale Avenue and Niles Street. | Install signal poles/controller equipment. | 586000 | 586000 | 0 | 0 | 2023-08-18 | 0 | 586000 | No PE | Authorized | No | CON | State | 0
H11-06-001 | 11 | 5109289 | 6 | Bakersfield | Kern County | KCOG | KCOG | Various Locations at 14 street segments throughout the City of Bakersfield. | Install radar feedback speed signs at the entrances of each street in both directions. | 320500 | 288000 | 0 | 0 | 2023-11-21 | 2025-07-08 | 288000 | No PE | Authorized | No | Closed | State | 0
H11-06-002 | 11 | 5109294 | 6 | Bakersfield | Kern County | KCOG | KCOG | Jewetta Ave between Hageman Rd and Olive Dr; Camino Media between Gosford Rd and the canal to the west; Hosking Ave between Akers Rd and Hughes Ln; and several sections on Panama Ln. | Install raised street medians. | 1968000 | 1771200 | 0 | 0 | 2024-03-19 | 2025-11-04 | 1771200 | No PE | Authorized | No | Closed | State | 0
H11-06-003 | 11 | 5109292 | 6 | Bakersfield | Kern County | KCOG | KCOG | At Norris Elementary School and at Stiern Middle School. | Install flashing yellow beacons near existing crosswalks to enhance visibility and slow down vehicular traffic. | 209300 | 188370 | 0 | 0 | 2024-03-08 | 0 | 188370 | No PE | Authorized | No | CON | State | 0
H11-06-004 | 11 | 5109284 | 6 | Bakersfield | Kern County | KCOG | KCOG | Various intersections throughout the City. | Replace existing traffic signal backplates with high visibility reflective backplates. | 220600 | 198540 | 0 | 0 | 2024-01-18 | 2025-09-23 | 198540 | No PE | Authorized | No | Closed | State | 0
H12-06-004 | 12 | 0 | 6 | Bakersfield | Kern County | KCOG | KCOG | On Ashe Road between Ming Avenue and Stockdale Highway, and on Wible Road between McKee Road and Hosking Avenue. | Install raised medians. | 1397200 | 1257480 | 0 | 0 | 0 | 0 | 0 | No PE | Due by 3/31/2028 | No | Not Started | Federal | 0
H8-06-001 | 8 | 5109247 | 6 | Bakersfield | Kern County | KCOG | KCOG | Fifty-seven (57) signalized intersections within the north west portion of the City of Bakersfield. | Remove existing pedestrian walk/don't walk signal heads and install new pedestrian countdown timer modules for all pedestrian crossings. | 65429.03 | 58834.74 | 0 | 0 | 2018-11-23 | 2020-05-01 | 58834.74 | No PE | Authorized | No | Closed | Federal | 0
H8-06-002 | 8 | 5109248 | 6 | Bakersfield | Kern County | KCOG | KCOG | Eighty-eight (88) signalized intersections within the south west portion of the City of Bakersfield. | Remove existing pedestrian walk/don't walk signal heads and install new pedestrian countdown timer modules for all pedestrian crossings. | 150206.46 | 135134.42 | 0 | 0 | 2018-11-23 | 2020-05-20 | 135134.42 | No PE | Authorized | No | Closed | Federal | 0
H9-06-002 | 9 | 5109267 | 6 | Bakersfield | Kern County | KCOG | KCOG | Calloway Drive in front of Norris Middle School at existing crosswalk near Manhattan Drive; Monitor Street in front of Palla Elementary School at existing crosswalk near Kyner Avenue. | Install flashing yellow beacons near crosswalks. | 376282.3 | 246100 | 0 | 0 | 2022-11-08 | 2025-05-27 | 246100 | No PE | Authorized | No | Closed | Federal | 0
HSIP2-06-001 | 2 | 5109147 | 6 | Bakersfield | Kern County | KCOG | KCOG | Benton Street Between Ming Ave. And Wilson Rd. | Install Flashing Beacons And Curb Ramps. | 31894.38 | 28059 | 0 | 0 | 2013-02-22 | 2015-12-09 | 28059 | No PE | Authorized | No | Closed | Federal | 0
HSIP4-06-007 | 4 | 5109185 | 6 | Bakersfield | Kern County | KCOG | KCOG | Various locations throughout the city | Install pedestrian countdown heads | 41148.65 | 36961.2 | 0 | 0 | 2012-05-17 | 2014-09-02 | 36961.2 | No PE | Authorized | No | Closed | Federal | 0
HSIP5-06-001 | 5 | 5109202 | 6 | Bakersfield | Kern County | KCOG | KCOG | Twenty (20) intersections within the city | Install pedestrian countdown heads | 46319.28 | 37707.71 | 0 | 0 | 2013-11-06 | 2016-02-26 | 37707.71 | No PE | Authorized | No | Closed | Federal | 0
HSIP6-06-002 | 6 | 5109211 | 6 | Bakersfield | Kern County | KCOG | KCOG | 60 intersections throughout the City of Bakersfield | Install pedestrian countdown signal heads and timer modules | 81521.72 | 70920.65 | 0 | 0 | 2014-07-15 | 2016-11-21 | 70920.65 | No PE | Authorized | No | Closed | Federal | 0
HSIP7-06-004 | 7 | 5109232 | 6 | Bakersfield | Kern County | KCOG | KCOG | Various Locations - 62 signalized intersections within the north east portion of the City of Bakersfield | Install pedestrian countdown head at each signalized intersection | 113000.22 | 101700.2 | 0 | 0 | 2017-04-05 | 2019-10-18 | 101700.2 | No PE | Authorized | No | Closed | Federal
HSIP7-06-005 | 7 | 5109233 | 6 | Bakersfield | Kern County | KCOG | KCOG | Various Locations - 50 signalized intersections within the south east portion of the City of Bakersfield | Install pedestrian countdown head at each signalized intersection | 99456.25 | 89510.63 | 0 | 0 | 2017-06-27 | 2019-10-18 | 89510.63 | No PE | Authorized | No | Closed | Federal
H11-06-005 | 11 | 5258047 | 6 | Chowchilla | Madera County | MCTC | Madera LTC | Various locations throughout the City. Ave 24 1/2 & Rd 16; Robertson Blvd & 8th St; 7th & Robertson Blvd; Ave 24 1/2 & Chowchilla Blvd; S 3rd St & Colusa Ave; N 5th St & Riverside Ave; N 4th St & Ventura; Orange Ave & S 12th St; N 5th St & Ventura; Robertson Blvd & 13th St; Trinity Ave & South 3rd St; Orange St & S 11th St; Orange St & S 13th St; Trinity Ave & S 11th St; Trinity Ave & S 13th St; and Riverside Ave & N 13th St. | Add intersection lighting; install additional stop signs or other intersection warning/regulatory signs; add marked crosswalks and RRFBs; and install pedestrian crossing at uncontrolled locations (new signs and markings). | 697600 | 627840 | 2023-10-24 | 0 | 2025-05-16 | 0 | 627840 | Authorized | Authorized | No | CON | State | -1
H10-06-003 | 10 | 5208179 | 6 | Clovis | Fresno County | FCOG | FCOG | Along Shaw Avenue, at the intersections of Willow, Sylmar, Peach, Villa, Minnewawa, Dewitt, and Clovis; along Herndon Avenue, at the intersections of Helm, Peach, Villa, and Dewitt. | Install upgraded controllers, equipment and detection at 11 intersections. | 802400 | 802400 | 2021-11-15 | 0 | 2026-03-17 | 0 | 802400 | Authorized | Authorized | No | CON | State | 0
H11-06-006 | 11 | 5208190 | 6 | Clovis | Fresno County | FCOG | FCOG | The traffic circle located at Owen's Mountain Parkway and Temperance Avenue and at San Jose Avenue and Locan Avenue at the trail crossing. | Install solar powered rectangular rapid flashing beacons, posts, actuation push button stations, and striping and signage adjustments. | 275470 | 247700 | 2023-10-13 | 0 | 2024-10-21 | 2025-12-15 | 247700 | Authorized | Authorized | No | Closed | State | 0
H9-06-003 | 9 | 5208168 | 6 | Clovis | Fresno County | FCOG | FCOG | Twenty-nine (29) intersections throughout the City of Clovis | Install pedestrian push button systems and pedestrian countdown modules. | 557684.68 | 546142.64 | 2019-04-29 | 0 | 2021-07-02 | 2023-05-26 | 546142.64 | Authorized | Authorized | No | Closed | Federal | 0
HSIP2-06-009 | 2 | 5208096 | 6 | Clovis | Fresno County | FCOG | FCOG | Villa Ave. And Bullard Ave. Intersection | Lenghten Left Turn Pocket | 92473.99 | 53820 | 2010-01-14 | 0 | 2010-07-20 | 2011-12-08 | 53820 | Authorized | Authorized | No | Closed | Federal | 0
HSIP2-06-010 | 2 | 5208097 | 6 | Clovis | Fresno County | FCOG | FCOG | Clovis Ave. And Santa Ana Ave. Intersection | Upgrade Traffic Signals; Add Protective Left Turn Phase | 177263.88 | 143729.99 | 2009-12-17 | 2011-12-28 | 2012-07-06 | 2014-05-13 | 143729.99 | Authorized | Authorized | No | Closed | Federal | 0
HSIP3-06-001 | 3 | 5208102 | 6 | Clovis | Fresno County | FCOG | FCOG | Intersection Of Peach And Gettysburg | Upgrade Traffic Signal; Convert To Fully Actuated Operation With Protected Left-Turn Phases | 458066.33 | 299999.99 | 2010-07-09 | 2011-07-21 | 2013-05-06 | 2015-06-19 | 299999.99 | Authorized | Authorized | No | Closed | Federal | 0
HSIP3-06-002 | 3 | 5208103 | 6 | Clovis | Fresno County | FCOG | FCOG | Intersection of Fifth And Sunnyside | Upgrade Traffic Signal; Convert Two-Phase To Eight-Phase Operation With Protected Turning Movements; Install Audible Pedestrian System; Improve Curb Ramps | 238096.15 | 175180 | 2010-07-13 | 0 | 2011-07-21 | 2013-04-17 | 175180 | Authorized | Authorized | No | Closed | Federal | 0
HSIP3-06-003 | 3 | 5208104 | 6 | Clovis | Fresno County | FCOG | FCOG | Fowler Ave. Between Sierra Ave. And Herndon Ave. | Install Audible Pedestrian System And Signs; Construct Diverter/Median Islands And Curb Ramps | 174781.48 | 156597.21 | 2010-07-16 | 0 | 2011-07-21 | 2012-11-05 | 156597.21 | Authorized | Authorized | No | Closed | Federal | 0
HSIP4-06-009 | 4 | 5208121 | 6 | Clovis | Fresno County | FCOG | FCOG | Helm Ave./Gettysburg Ave.; Villa Ave./Gettysburg Ave. | Install solar-powered LED Stop signs | 31462.64 | 24500 | 2011-11-04 | 0 | 2012-04-11 | 2013-02-26 | 24500 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-06-002 | 5 | 5208144 | 6 | Clovis | Fresno County | FCOG | FCOG | East side of Willow Ave. along the Clovis Old Town Trail grade separated crossing | Install a concrete abutment | 103033.1 | 92695.97 | 2013-08-10 | 0 | 2014-07-31 | 2015-12-09 | 92695.97 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-06-003 | 5 | 5208145 | 6 | Clovis | Fresno County | FCOG | FCOG | Shaw Ave./Cole Ave. | Modify traffic signals and left-turn lane | 370626.26 | 157455.82 | 2013-08-02 | 0 | 2015-06-16 | 2017-04-24 | 157455.82 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-06-004 | 5 | 5208146 | 6 | Clovis | Fresno County | FCOG | FCOG | Shepherd Ave./North Fowler Ave. | Install traffic signal, raised medians and striping; construct sidewalks, curb ramps, curbs and gutters | 1206204.72 | 356099.99 | 2013-08-02 | 0 | 2015-08-14 | 2018-03-07 | 356099.99 | Authorized | Authorized | No | Closed | Federal | 0
HSIP4-06-001 | 4 | 5146011 | 6 | Coalinga | Fresno County | FCOG | FCOG | Elm Ave. (SR 33/SR 198) between Phelps Ave. and Gale Ave. | Install left-turn pocket, safety lighting, signs, and striping | 170062.42 | 152557.57 | 2012-08-31 | 0 | 2012-11-30 | 2015-02-27 | 152557.57 | Authorized | Authorized | No | Closed | Federal | 0
HSIP6-06-003 | 6 | 5146014 | 6 | Coalinga | Fresno County | FCOG | FCOG | SR 33 (Elm Ave)/Cambridge Ave | Install traffic signals, signs, striping, sidewalks, curb and gutter, curb ramps, widen pavement and other safety improvements | 690863.06 | 537000 | 2014-05-29 | 0 | 2020-03-03 | 2024-07-24 | 537000 | Authorized | Authorized | No | Closed | Federal | 0
H10-06-004 | 10 | 5223024 | 6 | Corcoran | Kings County | KCAG | KCAG | Intersection of Dairy Avenue and Bainum Avenue. | Install Rectangular Rapid Flashing Beacon (RRFB), update pedestrian crossing at uncontrolled location with enhanced safety features including in-roadway warning lights. | 250000 | 250000 | 2021-08-11 | 0 | 2022-05-17 | 2024-09-09 | 250000 | Authorized | Authorized | No | Closed | State | 0
H11-06-007 | 11 | 5223028 | 6 | Corcoran | Kings County | KCAG | KCAG | Intersection of Whitley Ave and Gardner Ave. | Install pedestrian crossing at an uncontrolled intersection with enhanced safety features. | 250000 | 225000 | 2023-07-27 | 0 | 0 | 0 | 39510 | Authorized | Due by 9/30/2026 | No | PE | State | 0
H11-06-008 | 11 | 5223034 | 6 | Corcoran | Kings County | KCAG | KCAG | Plymouth Avenue near 4th Avenue. | Upgrade existing guardrails and end treatments. | 255100 | 229590 | 2023-12-13 | 0 | 2025-10-07 | 0 | 229590 | Authorized | Authorized | No | CON | State | -1
H12-06-005 | 12 | 5223037 | 6 | Corcoran | Kings County | KCAG | KCAG | The intersection of Bainum Avenue and Letts Avenue. | Upgrade pedestrian crossing at uncontrolled intersection with enhanced safety features including flashing beacons and curb extensions. | 350000 | 315000 | 2025-12-04 | 0 | 0 | 0 | 56250 | Authorized | Due by 3/31/2028 | No | PE | State | 0
H12-06-006 | 12 | 5223038 | 6 | Corcoran | Kings County | KCAG | KCAG | On Paris Avenue at turn onto Plymouth Avenue. | Upgrade existing guardrails and end treatments. | 510000 | 459000 | 2025-12-04 | 0 | 0 | 0 | 63000 | Authorized | Due by 3/31/2028 | No | PE | State | 0
H11-06-009 | 11 | 5227072 | 6 | Delano | Kern County | KCOG | KCOG | County Line Road from Browning Road to Veneto Street; Browning Road from Garces Highway to 6th Ave.; Norwalk Street from Weaver Ave. to 18th Ave. | Install centerline and edgeline rumble strips/stripes. | 132500 | 119250 | 2023-10-23 | 0 | 2025-12-16 | 0 | 119250 | Authorized | Authorized | No | CON | State | 0
H9-06-004 | 9 | 5227064 | 6 | Delano | Kern County | KCOG | KCOG | Twenty-two (22) uncontrolled pedestrian crossing locations throughout the City of Delano. | Install pedestrian crossings at uncontrolled locations; Install/upgrade larger intersections warning/regulatory signs. | 386420.84 | 261173.06 | 0 | 0 | 2021-03-25 | 2023-10-19 | 261173.06 | No PE | Authorized | No | Closed | Federal | 0
HSIP2-06-011 | 2 | 5227035 | 6 | Delano | Kern County | KCOG | KCOG | Cecil Ave. And Hiett Ave. Intersection | Install Traffic Signal | 418107.17 | 366708.48 | 2009-03-19 | 0 | 2010-05-21 | 2013-03-01 | 366708.48 | Authorized | Authorized | No | Closed | Federal | 0
HSIP6-06-004 | 6 | 5227047 | 6 | Delano | Kern County | KCOG | KCOG | Cecil Ave/Albany St | Upgrade traffic signals; Install protected left-turn phasing | 216371.57 | 215036.07 | 2014-05-09 | 0 | 2016-03-11 | 2018-12-14 | 215036.07 | Authorized | Authorized | No | Closed | Federal | 0
HSIP7-06-006 | 7 | 5227054 | 6 | Delano | Kern County | KCOG | KCOG | 32 non-signalized crosswalk locations throughout the City of Delano. | Install pedestrian actuated warning systems; Install Advanced Yield Markings, and Install Pedestrian Crossing Signs | 511288.79 | 510593 | 2016-06-09 | 0 | 2017-08-16 | 2020-04-13 | 510593 | Authorized | Authorized | No | Closed | Federal
H11-06-010 | 11 | 5143042 | 6 | Dinuba | Tulare County | TCAG | TCAG | 5 Locations within the City of Dinuba: 1) El Monte Way/Palm Drive; 2) N Crawford Avenue/E Saginaw Avenue; 3) W Kern Street/S M Street; 4) El Monte Way/N I Street/Eaton Avenue; and 5) Avenue 416/Road 92. | Install/upgrade pedestrian crossings with enhanced safety features and install median refuge islands on minor road approaches. | 227900 | 205110 | 2023-12-28 | 0 | 0 | 0 | 36000 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE | State | -1
H11-06-011 | 11 | 5143043 | 6 | Dinuba | Tulare County | TCAG | TCAG | 3 Locations within the City of Dinuba: 1) El Monte Way between N Dickey Avenue and Palm Drive; 2) Crawford Avenue between Davis Drive and E Saginaw Avenue; and 3) S College Avenue between S M Street and Avenue 408. | Install/Upgrade Sidewalk Pathway along roadway segments. | 862100 | 775890 | 2023-12-28 | 0 | 0 | 0 | 117000 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE | State | 0
H11-06-012 | 11 | 5143041 | 6 | Dinuba | Tulare County | TCAG | TCAG | E. North Way and Hayes Ave, S. College Ave and Academy Way, Euclid Ave and Franklin Way, Monte Vista Dr and West Drive Entrance to Walmart, and E. Tulare St and H St. | Install Rectangular Rapid Flashing Beacon to enhance pedestrian safety. | 249000 | 224100 | 2023-12-29 | 0 | 0 | 0 | 27000 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE | State | -1
H8-06-003 | 8 | 5143032 | 6 | Dinuba | Tulare County | TCAG | TCAG | The intersection of Kamm Avenue at Greene Avenue. | Reduce the length of the existing crosswalk and narrow the street width to induce slower vehicle speeds; construct other crossing improvements. | 700614.58 | 623803.11 | 2017-09-13 | 0 | 2019-06-12 | 2021-05-05 | 623803.11 | Authorized | Authorized | No | Closed | Federal | 0
H9-06-005 | 9 | 5143034 | 6 | Dinuba | Tulare County | TCAG | TCAG | Various locations along Alta Avenue, Crawford Avenue, El Monte Way, Saginaw Avenue, Kamm Avenue, Kern Street, Nebraska Avenue, Englehart Avenue, Surabian Drive, and Sequoia Drive. | Install flush median, edgeline and centerline, and Class II and Class III bicycle facilities. | 2465232.8 | 1950011.99 | 2020-01-02 | 0 | 2023-03-03 | 2026-03-30 | 1950011.99 | Authorized | Authorized | No | Closed | Federal | 2
HSIP6-06-005 | 6 | 5195015 | 6 | Exeter | Tulare County | TCAG | TCAG | On SR 65 between Rocky Hill Dr and San Juan Ave | Install crosswalks, curb ramps, signs and pavement marking | 558255.57 | 558255.57 | 2015-05-12 | 0 | 2016-07-26 | 2021-05-05 | 558255.57 | Authorized | Authorized | No | Closed | Federal | 0
H12-06-007 | 12 | 5368018 | 6 | Farmersville | Tulare County | TCAG | TCAG | Intersection of N Magnolia Avenue and E Visalia Road; Intersection of S Farmersville Boulevard and E Oakland Street. | Install/upgrade pedestrian crossings with enhanced safety features for pedestrians, and install rectangular rapid flashing beacons (RRFBs). | 338000 | 304200 | 2025-08-22 | 0 | 0 | 0 | 49860 | Authorized | Due by 3/31/2028 | No | PE | State | 0
HSIP4-06-010 | 4 | 5368009 | 6 | Farmersville | Tulare County | TCAG | TCAG | Noble Ave./North Farmersville Blvd., near on/off-ramp connections from EB SR 198 | Construct roundabout | 897183.11 | 800000 | 0 | 0 | 2014-08-26 | 2019-04-18 | 800000 | No PE | Authorized | No | Closed | Federal | 0
H11-06-013 | 11 | 5224029 | 6 | Firebaugh | Fresno County | FCOG | FCOG | At nine intersections. | Install/upgrade pedestrian crosswalks with high visibility crossings, advanced yield lines, warning signs, curb ramps, and medians with pedestrian refuge islands. | 249300 | 224370 | 2023-10-24 | 0 | 0 | 0 | 23040 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE | State | 0
HSIP4-06-002 | 4 | 5173021 | 6 | Fowler | Fresno County | FCOG | FCOG | Adams Ave./Golden State Blvd.; Merced Ave./Golden State Blvd.; Manning Ave./Golden State Blvd.; Manning Ave./Vineyard Pl.; San Antonio Dr./Golden State Blvd. | Install battery back-up system at signalized intersections | 104464.24 | 93805.41 | 2012-02-21 | 0 | 2012-08-28 | 2014-02-24 | 93805.41 | Authorized | Authorized | No | Closed | Federal | 0
H10-06-005 | 10 | 5060392 | 6 | Fresno | Fresno County | FCOG | FCOG | Three school crossings, at the Intersections of Donner and Millbrook, Alluvial and Sierra Vista, and Browning and Maroa. | Install RRFBs. | 221284 | 221284 | 2021-12-13 | 0 | 2023-04-21 | 0 | 250079.66 | Authorized | Authorized | No | CON | State | 0
H10-06-006 | 10 | 5060393 | 6 | Fresno | Fresno County | FCOG | FCOG | 89 signalized intersections citywide on Cedar, West, Barstow, McKinley, Clovis, Butler, Elm, Ashlan, California, Ventura and Jensen. | Install pedestrian countdown signal head equipment. | 941200 | 921208 | 2021-12-13 | 0 | 2022-11-10 | 2025-03-03 | 921208 | Authorized | Authorized | No | Closed | State | 0
H11-06-014 | 11 | 5060406 | 6 | Fresno | Fresno County | FCOG | FCOG | Intersections of Cedar Avenue/Shields Avenue and Cedar Avenue/Fountain Way. | Cedar/Shields: install retroreflective back plates, advance stop bars, and leading pedestrian intervals. Cedar/Fountain: add intersection lighting; install high visibility crosswalks and pedestrian hybrid beacon. | 1021000 | 918900 | 2023-11-14 | 0 | 2026-03-17 | 0 | 918900 | Authorized | Authorized | No | CON | State | 0
H11-06-015 | 11 | 5060407 | 6 | Fresno | Fresno County | FCOG | FCOG | Various locations on Ashlan Avenue and Shields Avenue (23 signalized intersections). | Install pedestrian countdown signal head equipment. | 272300 | 245070 | 2023-11-14 | 0 | 2024-12-03 | 0 | 245070 | Authorized | Authorized | No | CON | State | 0
H12-06-008 | 12 | 5060423 | 6 | Fresno | Fresno County | FCOG | FCOG | Intersection of Blackstone Avenue and Sierra Avenue. | Install retroreflective back plates, intersection lighting, protected left-turn phase with an existing left turn lane. | 962000 | 865800 | 2025-11-18 | 0 | 0 | 0 | 92790 | Authorized | Due by 3/31/2028 | No | PE | State | 0
H12-06-009 | 12 | 5060424 | 6 | Fresno | Fresno County | FCOG | FCOG | Intersection of First Street and Gettysburg Avenue, and intersection of Fresno Street and Shields Avenue. | Install retroreflective back plates, intersection lighting, and advanced stop bars. | 766900 | 690210 | 2025-11-18 | 0 | 0 | 0 | 72810 | Authorized | Due by 3/31/2028 | No | PE | State | 0
H8-06-004 | 8 | 5060349 | 6 | Fresno | Fresno County | FCOG | FCOG | Herndon Ave. from Golden State Blvd. to Willow Ave. | Upgrade twenty-three (23) signalized intersections with pedestrian countdown head equipment along ten (10) miles of the Herndon Avenue corridor. | 115565.18 | 115565.18 | 2018-05-11 | 0 | 2019-04-30 | 2021-04-26 | 115565.18 | Authorized | Authorized | No | Closed | Federal | 0
H8-06-005 | 8 | 5060350 | 6 | Fresno | Fresno County | FCOG | FCOG | Shaw Avenue from West Avenue to Chestnut Avenue. | Upgrade fourteen (14) signalized intersections with pedestrian countdown head equipment along five (5) miles of the Shaw Avenue corridor. | 87170.26 | 87170.26 | 2018-05-11 | 0 | 2019-05-03 | 2021-05-26 | 87170.26 | Authorized | Authorized | No | Closed | Federal | 0
H8-06-006 | 8 | 5060343 | 6 | Fresno | Fresno County | FCOG | FCOG | Intersection of Dakota Avenue at West Avenue. | Install protected left turn phase. | 538718.61 | 538718.61 | 0 | 0 | 2019-01-22 | 2021-06-10 | 538718.61 | No PE | Authorized | No | Closed | Federal | 0
H9-06-006 | 9 | 5060355 | 6 | Fresno | Fresno County | FCOG | FCOG | Eighty-six (86) signalized intersections (on Belmont from Delno to Clovis, Olive from Fruit to Clovis, and various locations Downtown and in the Tower District). | Install pedestrian countdown equipment. | 393110.34 | 393110.34 | 2019-03-19 | 0 | 2019-11-27 | 2021-10-25 | 393110.34 | Authorized | Authorized | No | Closed | Federal | 0
H9-06-007 | 9 | 5060356 | 6 | Fresno | Fresno County | FCOG | FCOG | Twenty-two (22) signalized intersections along First Street from Ventura to Nees. | Upgrade pedestrian countdown equipment. | 115180.54 | 115180.54 | 2019-03-19 | 0 | 2019-12-17 | 2021-06-17 | 115180.54 | Authorized | Authorized | No | Closed | Federal | 0
H9-06-008 | 9 | 5060357 | 6 | Fresno | Fresno County | FCOG | FCOG | Twenty-five (25) signalized intersections (Fresno Street crossings at Thomas and San Jose; the intersection of Fresno and R Street (east/west), the intersection of Fresno and Clinton and various intersections along Fresno from B Street to Friant Road). | Install two HAWK signals, two protected left turn signals and upgrade pedestrian countdown equipment. | 2963602 | 2618160 | 2019-03-20 | 2021-01-04 | 2022-09-13 | 0 | 2618160 | Authorized | Authorized | No | CON | Federal | 0
HSIP1-06-001 | 1 | 5060076 | 6 | Fresno | Fresno County | FCOG | FCOG | Intersection Of Clinton Ave. And West Ave. | Upgrade Traffic Signals With Left-Turn Phasing. | 239218.38 | 211780 | 2001-03-06 | 2004-08-26 | 2007-07-24 | 2012-11-02 | 211780 | Authorized | Authorized | No | Closed | Federal | 0
HSIP1-06-002 | 1 | 5060154 | 6 | Fresno | Fresno County | FCOG | FCOG | Intersection Of Cedar Ave. And Barstow Ave. | Remove Valley Gutter Crossing. | 78477.13 | 70455.41 | 2008-04-15 | 0 | 2008-09-10 | 2012-02-21 | 70455.41 | Authorized | Authorized | No | Closed | Federal | 0
HSIP2-06-003 | 2 | 5060177 | 6 | Fresno | Fresno County | FCOG | FCOG | Olive Ave. At Both Sr99 Southbound And Northbound Off And On Ramps | Install Traffic Signal; Cooperative Project With Caltrans | 1687471.11 | 892181.71 | 0 | 0 | 2014-07-31 | 2018-02-21 | 892181.71 | No PE | Authorized | No | Closed | Federal | 0
HSIP2-06-004 | 2 | 5060173 | 6 | Fresno | Fresno County | FCOG | FCOG | Belmont Ave. And Maple Ave. Intersection | Install Left Turn Phasing For All Four Legs | 322822.53 | 290540.28 | 2009-04-10 | 0 | 2010-07-28 | 2012-05-14 | 290540.28 | Authorized | Authorized | No | Closed | Federal | 0
HSIP2-06-005 | 2 | 5060174 | 6 | Fresno | Fresno County | FCOG | FCOG | Hughes Ave. And Weber Ave. | Install Traffic Signals | 335558.68 | 297532.42 | 2009-04-10 | 0 | 2010-08-20 | 2013-03-01 | 297532.42 | Authorized | Authorized | No | Closed | Federal | 0
HSIP2-06-008 | 2 | 5060175 | 6 | Fresno | Fresno County | FCOG | FCOG | Dakota Ave. And First Ave. | Upgrade Traffic Signals | 320805.84 | 268113.02 | 2009-04-10 | 0 | 2010-08-06 | 2012-12-20 | 268113.02 | Authorized | Authorized | No | Closed | Federal | 0
HSIP4-06-014 | 4 | 5060249 | 6 | Fresno | Fresno County | FCOG | FCOG | Millbrook Ave./Shields Ave. | Install protected left-turn phasing | 399787.71 | 358959.85 | 2011-08-03 | 0 | 2012-08-24 | 2015-12-08 | 358959.85 | Authorized | Authorized | No | Closed | Federal | 0
HSIP4-06-015 | 4 | 5060248 | 6 | Fresno | Fresno County | FCOG | FCOG | Palm Ave./Sierra Ave. | Install protected left-turn phasing | 425656.99 | 383091.28 | 2011-08-03 | 0 | 2012-08-02 | 2015-12-22 | 383091.28 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-06-006 | 5 | 5060275 | 6 | Fresno | Fresno County | FCOG | FCOG | Cedar Ave./Bulldog Ln. | Install protected left-turn phasing | 418852.17 | 350024.02 | 2013-08-10 | 0 | 2014-09-12 | 2016-12-12 | 350024.02 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-06-007 | 5 | 5060282 | 6 | Fresno | Fresno County | FCOG | FCOG | Weber Ave./Shields Ave. | Install traffic signals and left-turn lane | 1013979.51 | 892642.56 | 2014-03-21 | 0 | 2015-07-02 | 2021-11-16 | 892642.56 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-06-008 | 5 | 5060274 | 6 | Fresno | Fresno County | FCOG | FCOG | McKinley Ave./Palm Ave. | Install protected left-turn phasing | 453452.22 | 399106.98 | 2013-07-25 | 0 | 2014-12-30 | 2018-02-06 | 399106.98 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-06-010 | 5 | 5060277 | 6 | Fresno | Fresno County | FCOG | FCOG | Tulare Ave./R St. | Install protected left-turn phasing | 553184.2 | 461068.99 | 2013-08-02 | 0 | 2015-06-22 | 2018-03-26 | 461068.99 | Authorized | Authorized | No | Closed | Federal | 0
HSIP6-06-006 | 6 | 5060286 | 6 | Fresno | Fresno County | FCOG | FCOG | N Palm Ave/Clinton Ave | Install protected left-turn phasing | 519083.53 | 511823 | 2014-07-11 | 2015-07-14 | 2016-09-01 | 2018-10-16 | 511823 | Authorized | Authorized | No | Closed | Federal | 0
HSIP7-06-001 | 7 | 5060332 | 6 | Fresno | Fresno County | FCOG | FCOG | Intersection of Chestnut Avenue and Shields Avenue | Installation of protected left-turn phasing at the intersection of Chestnut Avenue and Shields Avenue | 528766.52 | 526727.97 | 0 | 2017-04-05 | 2019-04-15 | 2022-05-17 | 526727.97 | No PE | Authorized | No | Closed | Federal
HSIP7-06-002 | 7 | 5060331 | 6 | Fresno | Fresno County | FCOG | FCOG | The intersection of Belmont Avenue and Fulton Street | Modification of the existing traffic signal including the installation of an additional mast arm, traffic signal and pedestrian heads, and equipment upgrades | 520148.73 | 480109.53 | 2016-11-16 | 0 | 2017-09-12 | 2020-05-01 | 480109.53 | Authorized | Authorized | No | Closed | Federal
H11-06-016 | 11 | 5942318 | 6 | Fresno County | Fresno County | FCOG | FCOG | Various locations in Fresno County. | Install edge line striping on 41.6 miles of roadway (83.2 miles of edge line) in various locations. | 298300 | 249975 | 0 | 0 | 2023-08-18 | 0 | 249975 | No PE | Authorized | No | CON | Federal | 1
H11-06-032 | 11 | 5942317 | 6 | Fresno County | Fresno County | FCOG | FCOG | Auberry Road and Frazier Road in eastern Fresno County. | Reconstruct the intersection and improve the horizontal alignment by flattening the curve. Install a right-turn pocket and a left-turn pocket. Widen the shoulders, and improve intersection sight distance. Install a painted median. | 2408200 | 2167380 | 2023-08-18 | 0 | 0 | 0 | 306900 | Authorized | Due by 6/30/2027 | No | PE | Federal | 1
H12-06-010 | 12 | 5942311 | 6 | Fresno County | Fresno County | FCOG | FCOG | Intersection of Millerton Road and Marina Drive near the unincorporated community of Friant. | Install roundabout. | 3659500 | 2957603 | 0 | 0 | 0 | 0 | 0 | Due by 12/31/2026 | Due by 3/31/2028 | No | Not Started | Federal | 1
H12-06-011 | 12 | 5942331 | 6 | Fresno County | Fresno County | FCOG | FCOG | Ten (10) two-way stop controlled intersections. | Improve sight distance to intersections, install left-turn lane and add intersection lighting. | 5054100 | 4295985 | 2025-07-14 | 0 | 0 | 0 | 446420 | Authorized | Due by 3/31/2028 | No | PE | Federal | 1
H12-06-012 | 12 | 5942324 | 6 | Fresno County | Fresno County | FCOG | FCOG | Intersection of Central Ave and Chestnut Ave just south of the unincorporated community of Malaga. | Provide protected left turn phasing and convert signal to mast arm. | 1024000 | 921600 | 0 | 0 | 0 | 0 | 0 | Due by 12/31/2026 | Due by 3/31/2028 | No | Not Started | State | 0
H9-06-009 | 9 | 5942294 | 6 | Fresno County | Fresno County | FCOG | FCOG | The intersection of Ashlan Ave. and Palm Ave. | Upgrade existing 2-phase fixed timed traffic signal to 8-phase to include, but not limited to, left-turn phasing, larger vehicle heads, and new 2070 controller. | 956000 | 956000 | 2019-02-28 | 2021-01-15 | 2022-07-01 | 0 | 956000 | Authorized | Authorized | No | CON | Federal | 0
HRRR1-06-043 | 1 | 5942170 | 6 | Fresno County | Fresno County | FCOG | FCOG | Manning from SR 99 to Crawford; Zediker from Dinuba to Rose; Rose from Zediker to Lac Jac; Clovis from SR 99 to Manning; Conejo from Clovis to Temperance; Lincoln from Brawley to Cornelia; Cornelia from Central to Lincoln; Shields from Del Norte to Butte | Pavement Markings and Delineation | 231628.54 | 166338.39 | 0 | 0 | 2008-07-17 | 2011-07-06 | 166338.39 | No PE | Authorized | No | Closed | Federal | 0
HSIP3-06-005 | 3 | 5942194 | 6 | Fresno County | Fresno County | FCOG | FCOG | Howard Ave. South Of Shaw Ave. | Realign Roadway | 193610.42 | 64482.79 | 2010-08-20 | 0 | 2011-07-08 | 2012-11-02 | 64482.79 | Authorized | Authorized | No | Closed | Federal | 0
HSIP4-06-003 | 4 | 5942203 | 6 | Fresno County | Fresno County | FCOG | FCOG | Alta Ave./Manning Ave. | Install left-turn phasing | 232684.4 | 180499.36 | 2011-08-01 | 0 | 2012-08-15 | 2014-10-24 | 180499.36 | Authorized | Authorized | No | Closed | Federal | 0
HSIP4-06-008 | 4 | 5942204 | 6 | Fresno County | Fresno County | FCOG | FCOG | Nees Ave./Washoe Ave. | Install turn lanes at intersection | 1049385.92 | 680374.99 | 2011-08-01 | 2012-08-31 | 2014-05-05 | 2018-05-01 | 680374.99 | Authorized | Authorized | No | Closed | Federal | 0
HSIP4-06-011 | 4 | 5942202 | 6 | Fresno County | Fresno County | FCOG | FCOG | Millerton Rd. (Friant Rd.)/North Fork Rd. (Mono St.) | Install traffic signals | 602982.66 | 454512.58 | 2011-07-08 | 0 | 2012-11-09 | 2015-12-11 | 454512.58 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-06-011 | 5 | 5942230 | 6 | Fresno County | Fresno County | FCOG | FCOG | S Bethel Ave./E Manning Ave. | Install traffic signals and left-turn pockets | 1406338.17 | 565500 | 2013-07-29 | 2015-06-30 | 2017-04-06 | 2018-12-17 | 565500 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-06-012 | 5 | 5942231 | 6 | Fresno County | Fresno County | FCOG | FCOG | Grantland Ave./Shaw Ave. | Install traffic signals and left-turn pocket; widen roadway | 1078181.12 | 649000 | 2013-08-02 | 2015-06-30 | 2016-05-25 | 2018-11-02 | 649000 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-06-013 | 5 | 5942229 | 6 | Fresno County | Fresno County | FCOG | FCOG | Jensen Ave./Temperance Ave. | Widen roadway; install traffic signals and left-turn pocket | 1594998.83 | 785500 | 2013-08-20 | 2015-06-30 | 2017-02-10 | 2019-01-17 | 785500 | Authorized | Authorized | No | Closed | Federal | 0
HSIP6-06-007 | 6 | 5942241 | 6 | Fresno County | Fresno County | FCOG | FCOG | Auberry Rd/Copper Ave | Install traffic signals, left turn phase and left turn lanes | 1580682.25 | 802195.08 | 2014-03-21 | 2015-07-23 | 2018-11-30 | 2024-11-13 | 802195.08 | Authorized | Authorized | No | Closed | Federal | 0
HSIP6-06-008 | 6 | 5942242 | 6 | Fresno County | Fresno County | FCOG | FCOG | Barstow Ave/Fruit Ave | Upgrade traffic signals; Install protected left-turn phasing | 734025.35 | 647500 | 2014-03-21 | 2015-10-28 | 2016-12-23 | 2020-01-09 | 647500 | Authorized | Authorized | No | Closed | Federal | 0
HSIP6-06-009 | 6 | 5942243 | 6 | Fresno County | Fresno County | FCOG | FCOG | Bethel Ave/Mountain View Ave | Upgrade traffic signals; Install protected left-turn phasing | 782284.9 | 702942.75 | 2014-05-09 | 2016-05-03 | 2017-08-16 | 2020-01-09 | 702942.75 | Authorized | Authorized | No | Closed | Federal | 0
HSIP6-06-010 | 6 | 5942244 | 6 | Fresno County | Fresno County | FCOG | FCOG | Various locations throughout the Fresno County | Install striping | 550951.97 | 503616.73 | 2014-04-29 | 0 | 2015-06-09 | 2018-03-23 | 503616.73 | Authorized | Authorized | No | Closed | Federal | 0
HSIP7-06-003 | 7 | 5942272 | 6 | Fresno County | Fresno County | FCOG | FCOG | Various roads in the area west of Interstate 5 and east of the Friant-Kern Canal | Install no passing striping in lieu of existing dashed striping to comply with MUTCD and upgrade other pavement markings and striping | 877435.1 | 785846.44 | 2016-02-08 | 0 | 2016-06-13 | 2018-03-23 | 785846.44 | Authorized | Authorized | No | Closed | Federal
HSIP4-06-012 | 4 | 5091049 | 6 | Hanford | Kings County | KCAG | KCAG | Fargo Ave./Fitzgerald Ln. | Install left-turn lane | 84181.08 | 72323.92 | 2011-12-28 | 0 | 2012-10-29 | 2016-02-10 | 72323.92 | Authorized | Authorized | No | Closed | Federal | 0
H11-06-017 | 11 | 5305026 | 6 | Huron | Fresno County | FCOG | FCOG | Six intersections: 4th St/Central Ave, 4th St/Azteca Blvd, Myrtle St/Los Angeles St, 12th St/N St, Giffen Dr/Mouren Dr, and Palmer Ave/R St. | Install/upgrade pedestrian crosswalks with high visibility crossings, advanced yield lines and warning signing. | 294564 | 250000 | 2023-12-26 | 0 | 2025-02-20 | 0 | 250000 | Authorized | Authorized | No | CON | State | -1
H11-06-018 | 11 | 5291036 | 6 | Kerman | Fresno County | FCOG | FCOG | Along Kearney Boulevard at the intersections of Siskiyou Avenue, Park Avenue, and 4th Street. | Pedestrian crossing improvements at new and existing crosswalks by installing high visibility crosswalks, RRFBs, pedestrian crossing signage, and bulb outs. | 277200 | 249480 | 2023-10-31 | 0 | 2025-08-26 | 0 | 249480 | Authorized | Authorized | No | CON | State | 0
H12-06-013 | 12 | 5291040 | 6 | Kerman | Fresno County | FCOG | FCOG | Kearney Boulevard and Del Norte Avenue, First Street and El Mar Avenue, and First Sreet and F Street. | Improve school pedestrian crossing and intersection safety by installing high visibility crosswalks, advance pedestrian crossing signs and concrete curb bulb-outs. | 350000 | 315000 | 2025-07-30 | 0 | 0 | 0 | 36360 | Authorized | Due by 3/31/2028 | No | PE | State | 0
H12-09-002 | 12 | 0 | 6 | Kern Council of Governments | Kern County | KCOG | KCOG | A 2 mile segment of SR 58 in Kern County near California City and Edwards AFB North Gate entrance, from the SR 58 Intersection of California City Blvd to existing SR 58 freeway interchange at 140th St. | Reduce left-turn conflict at intersection. | 4520000 | 2468000 | 0 | 0 | 0 | 0 | 0 | No PE | Due by 3/31/2028 | No | Not Started | Federal | 0
H10-06-007 | 10 | 5950500 | 6 | Kern County | Kern County | KCOG | KCOG | 6 uncontrolled multi-lane pedestrian crossings on arterial and collector roads in unincorporated areas of east Bakersfield, Mojave, Rosamond, & Wofford Heights. | Install lighting. | 24100 | 22172 | 2021-09-23 | 0 | 0 | 2023-12-15 | 22172 | Authorized | No CON | No | Closed | State | 0
H10-06-007n008 | 10 | 5950519 | 6 | Kern County | Kern County | KCOG | KCOG | Various multi-lane arterial and collector roads in unincorporated areas of Oildale, east Bakersfield & Mojave. Upgrade 6 existing uncontrolled pedestrian crossings in unincorporated areas. | Install lighting at 6 existing uncontrolled multi-lane pedestrian crossings, five of which include raised medians on the approaches, and ped-activated Rectangular Rapid Flashing Beacons (RRFBs) at all intersections. | 1563800 | 1087741 | 0 | 0 | 2023-03-23 | 2025-12-01 | 1087741 | No PE | Authorized | No | Closed | State | 0
H10-06-008 | 10 | 5950501 | 6 | Kern County | Kern County | KCOG | KCOG | Intersection approaches of 5 multi-lane arterial and collector roads in unincorporated areas of Oildale, east Bakersfield, & Mojave. | Install raised medians on the approaches. | 16100 | 13685 | 2021-09-23 | 0 | 0 | 2023-12-15 | 13685 | Authorized | No CON | No | Closed | State | 0
H10-06-009n010 | 10 | 5950520 | 6 | Kern County | Kern County | KCOG | KCOG | All Kern County-maintained multi-lane roads and Wheeler Ridge Road (single lane). | Upgrade striping of centerlines/edgelines, left or right turns, & lane drops. Improve safety of curve on Wheeler Ridge Rd with chevron signs. Add new raised pavement markers on all roads. 80 miles of roadway; 226 miles of striping. | 3472600 | 2355087 | 0 | 0 | 2023-04-11 | 2025-12-01 | 2355087 | No PE | Authorized | No | Closed | State | 0
H10-06-011 | 10 | 5950522 | 6 | Kern County | Kern County | KCOG | KCOG | Various locations throughout the County of Kern. | Upgrade guardrail. | 653700 | 626450 | 0 | 0 | 2023-04-06 | 2024-12-10 | 626450 | No PE | Authorized | No | Closed | State | 0
H10-06-012 | 10 | 5950502 | 6 | Kern County | Kern County | KCOG | KCOG | Intersection of Wofford Boulevard & Panorama Drive in the community of Wofford Heights. | Install flashing beacons, radar speed Feedback signs, sidewalk, curb & gutter, ADA ramps, thermoplastic markings and signs at the uncontrolled multi-lane crosswalk. | 712900 | 250000 | 2021-09-23 | 0 | 2023-04-06 | 2024-12-10 | 250000 | Authorized | Authorized | No | Closed | State | 0
H10-06-013 | 10 | 5950523 | 6 | Kern County | Kern County | KCOG | KCOG | Cuddy Valley Road between Ivins Road and Obrien Drive, near the community of Frazier Park. | Upgrade existing edgelines and install rumble stripes. Install recessed reflective pavement markers on the centerline. | 339800 | 250000 | 0 | 0 | 2023-04-06 | 2024-06-07 | 250000 | No PE | Authorized | No | Closed | State | 0
H11-06-019 | 11 | 5950550 | 6 | Kern County | Kern County | KCOG | KCOG | Various locations throughout the County of Kern. | Guardrail Upgrades. | 1067900 | 961110 | 0 | 0 | 2026-03-26 | 0 | 961110 | No PE | Authorized | No | CON | State | 0
H12-06-014 | 12 | 5950547 | 6 | Kern County | Kern County | KCOG | KCOG | Niles Street from 360 ft West of Virginia Avenue to Oswell Street, approximately 1.5 miles in unincorporated Bakersfield. | Install new raised median, remove existing medians, restrict left-turns and u-turns, and reduce left-turn conflict intersections. | 9672800 | 8705520 | 2025-12-04 | 0 | 0 | 0 | 605700 | Authorized | Due by 3/31/2028 | No | PE | Federal | 0
H12-06-015 | 12 | 5950546 | 6 | Kern County | Kern County | KCOG | KCOG | Various locations in unincorporated Bakersfield and Oildale; 4 signalized intersections at (Olive Drive & Airport Drive), (Eucalyptus Drive & Fairfax Road), (Brundage Lane & Fairfax Road), & (Fairfax Road & Pioneer Drive). | Install raised medians on approaches. | 1438000 | 1294200 | 2025-11-21 | 0 | 0 | 0 | 231120 | Authorized | Due by 3/31/2028 | No | PE | Federal | 0
H8-06-007 | 8 | 5950437 | 6 | Kern County | Kern County | KCOG | KCOG | Intersection of Mount Vernon Ave at Quincy St | Convert signal to mast arm for east/west bound traffic on Quincy St and install pedestrian countdown signal heads | 544328.1 | 334015.65 | 2017-10-19 | 2017-10-19 | 2019-04-19 | 2022-07-12 | 334015.65 | Authorized | Authorized | No | Closed | Federal | 0
H8-06-008 | 8 | 5950435 | 6 | Kern County | Kern County | KCOG | KCOG | Intersection of Airport Dr at Norris Rd | install additional signal heads at north, west and east bound directions on the near side of the intersection. | 295172.92 | 219100 | 2017-10-25 | 2017-10-25 | 2019-05-17 | 2021-09-16 | 219100 | Authorized | Authorized | No | Closed | Federal | 0
H8-06-009 | 8 | 5950436 | 6 | Kern County | Kern County | KCOG | KCOG | Various locations in unincorporated Bakersfield and Rosamond areas. | Installation of pedestrian countdown signal heads. | 135084.35 | 135084.35 | 0 | 0 | 2018-10-31 | 2020-05-01 | 135084.35 | No PE | Authorized | No | Closed | Federal | 0
H8-06-010 | 8 | 5950440 | 6 | Kern County | Kern County | KCOG | KCOG | Various locations throughout the County of Kern. | Upgrade existing guardrails. | 1480636.42 | 1200000 | 2017-11-02 | 2017-11-02 | 2018-11-30 | 2021-03-16 | 1200000 | Authorized | Authorized | No | Closed | Federal | 0
H9-06-010&013 | 9 | 5950470 | 6 | Kern County | Kern County | KCOG | KCOG | Eighty-two (82) crosswalk locations at 79 intersections throughout Kern County (H9-06-010); San Diego Street between Hall Road and Burgundy Avenue, in the unincorporated community of Lamont, Kern County(H9-06-013). | Install continental crosswalks, intersection warning signs, reflective signs, pedestrian crossing signs, ADA curb ramps, street lighting, cross drains, and AC tie-ins (H9-06-010); Install continental crosswalks and lighting at four existing uncontrolled pedestrian crossing areas (H9-06-013). | 4912309.95 | 4790190.47 | 2019-09-05 | 0 | 2021-12-09 | 2024-09-04 | 4790190.47 | Authorized | Authorized | No | Closed | Federal | 0
H9-06-011 | 9 | 5950469 | 6 | Kern County | Kern County | KCOG | KCOG | The intersections of Roberts Lane at Sequoia Drive, Norris at Manor, and Manor at China Grade Loop. | Upgrade signals from pedestal to overhead mast arms. | 1469812.35 | 1272599.99 | 2019-09-05 | 2020-09-11 | 2021-04-20 | 2024-01-22 | 1272599.99 | Authorized | Authorized | No | Closed | Federal | 0
H9-06-012 | 9 | 5950471 | 6 | Kern County | Kern County | KCOG | KCOG | Various signalized intersections throughout the unincorporated Bakersfield, Oildale, Wheeler Ridge, Lake Isabella, and Rosamond communities of Kern County. | Intersection improvements, including replacing signal hardware at 30 intersections, intersection striping at 22 locations, and upgrading existing ADA-accessible curb ramps. | 2758913.5 | 2694469.75 | 2019-09-05 | 2020-09-11 | 2021-12-06 | 2024-05-01 | 2694469.75 | Authorized | Authorized | No | Closed | Federal | 0
HSIP1-06-009 | 1 | 5950282 | 6 | Kern County | Kern County | KCOG | KCOG | Intersection Of Flower St. And Haley St. | Upgrade Traffic Signals; Remove Fixed Objects; Construct Curb Ramps. | 136536.21 | 122882.58 | 0 | 0 | 2008-04-23 | 2012-01-19 | 122882.58 | No PE | Authorized | No | Closed | Federal | 0
HSIP2-06-014 | 2 | 5950300 | 6 | Kern County | Kern County | KCOG | KCOG | South Union Avenue And Pacheco Rd.; South Union Avenue And Fairview Rd. | Upgrade Traffic Signals; Construct Curb Ramps | 492469.51 | 397800 | 2009-05-08 | 0 | 2010-03-22 | 2012-03-29 | 397800 | Authorized | Authorized | No | Closed | Federal | 0
HSIP2-06-015 | 2 | 5950311 | 6 | Kern County | Kern County | KCOG | KCOG | Bernard St. And Alta Vista Dr. Intersection | Upgrade Traffic Signals; Construct Curb Ramps | 133616.58 | 112748.57 | 2009-06-16 | 0 | 2010-03-22 | 2012-03-29 | 112748.57 | Authorized | Authorized | No | Closed | Federal | 0
HSIP4-06-013 | 4 | 5950343 | 6 | Kern County | Kern County | KCOG | KCOG | Mount Vernon Ave. between Kentucky St. and Niles Pt. | Modify raised medians; relocate crosswalk; construct curb ramps | 264445.37 | 187200 | 0 | 0 | 2012-04-06 | 2013-12-06 | 187200 | No PE | Authorized | No | Closed | Federal | 0
HSIP5-06-014 | 5 | 5950374 | 6 | Kern County | Kern County | KCOG | KCOG | Patton Way between Hageman Rd. and Snow Rd. | Modify traffic signals; install two-way left-turn lane | 181267.36 | 135390.29 | 0 | 0 | 2014-02-07 | 2015-10-30 | 135390.29 | No PE | Authorized | No | Closed | Federal | 0
HSIP5-06-015 | 5 | 5950375 | 6 | Kern County | Kern County | KCOG | KCOG | Roberts Ln./Oildale Dr. | Construct left-turn lanes; modify traffic signals; install pedestrian countdown heads | 239280.5 | 108999 | 0 | 0 | 2014-02-19 | 2015-09-08 | 108999 | No PE | Authorized | No | Closed | Federal | 0
HSIP7-06-007 | 7 | 5950424 | 6 | Kern County | Kern County | KCOG | KCOG | South Union Ave between Taft Highway and Ming Avenue. | Construct left turn channelization | 2143710.75 | 1020870 | 0 | 0 | 2017-02-01 | 2018-10-31 | 1020870 | No PE | Authorized | No | Closed | Federal
H10-06-014 | 10 | 5945116 | 6 | Kings County | Kings County | KCAG | KCAG | Arterial and Collector roadway segments within the County of Kings. | Evaluate roadway signing upgrades; install, upgrade and replace signs. | 4055600 | 4055600 | 2021-11-19 | 0 | 2024-06-18 | 0 | 2940275 | Authorized | Authorized | No | CON | Mix | 1
H10-06-015 | 10 | 5945117 | 6 | Kings County | Kings County | KCAG | KCAG | Intersections: 21st Ave & Fremont Ave, 14th Ave & Fargo Ave, 16th Ave & Hanford Armona Rd, 22nd Ave & Excelsior Ave, 18th Ave & Kansas Ave, 12 3/4 Ave & Excelsior Ave, Avenal-Cutoff Road & Jackson Ave, 17th Ave & Lacey Blvd. | Install advanced warning flashing beacons; install flashing beacons on stop signs. | 186635 | 227412 | 2021-11-22 | 0 | 2023-04-21 | 2025-08-12 | 227412 | Authorized | Authorized | No | Closed | State | 3
H11-06-020 | 11 | 5945122 | 6 | Kings County | Kings County | KCAG | KCAG | Intersections: Excelsior Avenue and 13 1/4th Avenue, Excelsior Avenue and 11th Avenue, Grangeville Avenue and 7th Avenue, Idaho Avenue and 17th Avenue, Jersey Avenue and 19th Avenue, and Jackson Avenue and 14th Avenue. | Install left-turn lane; upgrade intersection pavement markings; install flashing beacons at stop-controlled intersections; install flashing beacons as advance warning. | 552900 | 497610 | 2023-05-11 | 2025-07-22 | 2025-12-19 | 0 | 497610 | Authorized | Authorized | No | CON | Federal | 1
H9-06-014n015 | 9 | 5945110 | 6 | Kings County | Kings County | KCAG | KCAG | Intersections of 13th Avenue at Front Street, 16th Avenue at Flint Avenue, 6th Avenue at Excelsior Avenue, 16th Avenue at Grangeville Boulevard, 14th Avenue at Idaho Ave and 14th Avenue at Hanford Armona Road (H9-06-014). Intersection of 22nd Avenue and Grangeville Boulevard (H9-06-015). | Install advance warning flashing beacons; install flashing beacons on stop signs (H9-06-014). Install roundabout (H9-06-015). | 2034700 | 2034700 | 2019-03-26 | 2021-12-28 | 2025-09-08 | 0 | 2034700 | Authorized | Authorized | No | CON | Federal | 0
HSIP3-06-006 | 3 | 6206022 | 6 | Kings County | Kings County | KCAG | KCAG | Intersection Of Sr 43 With Sr 137 And Whitley Ave. | Install Traffic Signals With Left-Turn Phase For Sr 43 Or Construct Roundabout | 1136000 | 462000 | 2014-08-14 | 0 | 0 | 2021-04-14 | 462000 | Authorized | Not Tracked | No | Closed | Federal | 0
HSIP6-06-011 | 6 | 5945099 | 6 | Kings County | Kings County | KCAG | KCAG | Various locations along Avenal Cutoff Rd in Kings County | Install right turn lanes and acceleration lanes | 1560131.78 | 1421425.62 | 2014-11-13 | 0 | 2017-07-06 | 2019-08-09 | 1421425.62 | Authorized | Authorized | No | Closed | Federal | 0
HSIP6-06-012 | 6 | 5945100 | 6 | Kings County | Kings County | KCAG | KCAG | Various locations throughout Kings County | Install right turn lanes and flashing beacons | 710481.43 | 627799 | 2014-11-18 | 0 | 2017-07-06 | 2019-11-08 | 627799 | Authorized | Authorized | No | Closed | Federal | 0
H12-06-016 | 12 | 5170073 | 6 | Kingsburg | Fresno County | FCOG | FCOG | Intersection of 10th Ave & Kern St. | Install speed table, rectangular rapid flashing beacon (RRFBs), lighting, and new crosswalks. | 1184800 | 1066320 | 2025-10-28 | 0 | 0 | 0 | 90000 | Authorized | Due by 3/31/2028 | No | PE | State | 0
H8-06-011 | 8 | 5170061 | 6 | Kingsburg | Fresno County | FCOG | FCOG | Intersection of Sierra Street (Conejo Avenue) at Bethel Avenue. | Construct a single lane roundabout. | 1296680 | 1296680 | 2019-04-01 | 2020-11-30 | 2022-03-07 | 2023-10-19 | 1296680 | Authorized | Authorized | No | Closed | Federal | 0
H10-06-016 | 10 | 5115042 | 6 | Lemoore | Kings County | KCAG | KCAG | Intersection at Bush Street and Champion Street. | Install Rectangular Rapid Flashing Beacon (RRFB) and pedestrian crossing at uncontrolled location with enhanced safety features. | 250000 | 250000 | 0 | 0 | 2023-11-09 | 2025-10-20 | 250000 | No PE | Authorized | No | Closed | State | 0
H12-06-017 | 12 | 5115044 | 6 | Lemoore | Kings County | KCAG | KCAG | The intersection of 19th Ave and Freedom Dr. | Upgrade pedestrian crossing with enhanced safety features including in-roadway warning lights, bulb-outs, signs, stripes and pavement markings. | 350000 | 315000 | 2025-03-19 | 0 | 0 | 0 | 55980 | Authorized | Due by 3/31/2028 | No | PE | State | 0
H12-06-018 | 12 | 5115045 | 6 | Lemoore | Kings County | KCAG | KCAG | Cedar Lane from Bluejay Avenue to Vine Street. | Install buffered Class II bicycle lanes. | 350000 | 315000 | 2025-03-14 | 0 | 2025-09-26 | 0 | 315000 | Authorized | Authorized | No | CON | State | 0
H10-06-017 | 10 | 5157127 | 6 | Madera | Madera County | MCTC | Madera LTC | Granada Drive north of Industrial Avenue. | Install curb ramps, concrete median island refuge area, high visibility crosswalk, RRFBs and sidewalk. | 141500 | 113760 | 0 | 0 | 2024-04-15 | 0 | 113760 | No PE | Authorized | No | CON | State | 0
H12-06-019 | 12 | 5157142 | 6 | Madera | Madera County | MCTC | Madera LTC | At the signalized intersection of Ellis Street & Country Club Drive (Road 26). | Install left-turn lane and add turn phase, implement leading pedestrian interval (LPI), and install high visibility markings. | 411300 | 370170 | 2025-12-05 | 0 | 0 | 0 | 61560 | Authorized | Due by 3/31/2028 | No | PE | State | 0
HSIP4-06-004 | 4 | 5157084 | 6 | Madera | Madera County | MCTC | Madera LTC | 4th St./Flume St.; Sunset Ave./Liberty Ln.; Ave. 13/Barnett Ave.; Ellis Ave./Jericho Dr.; Olive Ave./Roosevelt St.; Olive Ave. between Martin St. and Santa Cruz St. | Install in-pavement crosswalk lights, flashing beacons, and barricades | 306888.4 | 275432.76 | 2011-12-12 | 0 | 2014-08-14 | 2017-02-15 | 275432.76 | Authorized | Authorized | No | Closed | Federal | 0
HSIP7-06-010 | 7 | 5157111 | 6 | Madera | Madera County | MCTC | Madera LTC | Sunset Avenue from Granada Avenue to Foster Avenue | The proposed project will install pedestrian medians and ADA compliant sidewalks | 541026 | 486924 | 2018-01-03 | 0 | 2019-02-21 | 2021-07-30 | 486924 | Authorized | Authorized | No | Closed | Federal
HSIP1-06-007 | 1 | 5941062 | 6 | Madera County | Madera County | MCTC | Madera LTC | Intersection Of Children'S Blvd. And Lanes Bridge. | Install Traffic Signals With Interconnect And Emergency Vehicle Pre-Emption. | 267499.37 | 181691.51 | 2008-03-03 | 0 | 2009-01-09 | 2012-06-18 | 181691.51 | Authorized | Authorized | No | Closed | Federal | 0
HSIP4-06-005 | 4 | 5941092 | 6 | Madera County | Madera County | MCTC | Madera LTC | Children's Blvd. between Crocket Way and Lanes Bridge Dr. | Install shoulder rumble strip | 17291.64 | 15562.47 | 0 | 0 | 2012-01-10 | 2013-10-15 | 15562.47 | No PE | Authorized | No | Closed | Federal | 0
HSIP6-06-013 | 6 | 5941105 | 6 | Madera County | Madera County | MCTC | Madera LTC | Throughout the County of Madera unincorporated area | Upgrade signs | 641751.64 | 641751.64 | 0 | 0 | 2015-03-25 | 2017-10-13 | 641751.64 | No PE | Authorized | No | Closed | Federal | 0
H10-06-018 | 10 | 5343018 | 6 | Mcfarland | Kern County | KCOG | KCOG | Uncontrolled crosswalks at the intersections of W Perkins Ave and 3rd Place, E Perkins Ave and San Lucas St, E Perkins Ave.and San Pedro St, E Sherwood Ave and Browning Rd, and W Kern Ave and 4th St. NOTE, there is no change in the project location. | Install warning signs and upgrade markings to high-visibility, install one curb ramp, and add enhanced safety features. | 249900 | 249900 | 2021-04-23 | 0 | 2023-04-04 | 0 | 249900 | Authorized | Authorized | No | CON | State | 0
H12-06-020 | 12 | 5343022 | 6 | Mcfarland | Kern County | KCOG | KCOG | Various locations throughout the city. | Install rectangular rapid flashing beacons (RRFBs), LED Flashing Stop signs, advanced yield lines/signs; re-stripe high visibility crosswalks; and install curb ramps. | 388800 | 349920 | 2025-05-23 | 0 | 0 | 0 | 41400 | Authorized | Due by 3/31/2028 | No | PE | State | 0
H8-06-012 | 8 | 5343012 | 6 | Mcfarland | Kern County | KCOG | KCOG | Various stop controlled intersections along Garzoli Avenue, and Perkins Ave and 5th Street. | Upgrade signing with new Solar flashing LED Stop signs, traffic striping and markings, solar Speed Limit warning flashing beacon signs with radar speed feedback, crosswalk with In Roadway warning lights and upgrade ADA curb ramps. | 193610.09 | 193610.09 | 2017-05-19 | 0 | 2018-08-16 | 2020-11-03 | 193610.09 | Authorized | Authorized | No | Closed | Federal | 0
H11-06-021 | 11 | 5301027 | 6 | Orange Cove | Fresno County | FCOG | FCOG | Seven intersections: 4th St/C St, Jacobs Ave/C St, Jacobs Ave/D St, Park Blvd/2nd St, J St/9th St, Adams Ave/4th St, and Adams Ave/5th St. | Install/upgrade pedestrian crosswalks with high visibility crossings, advanced yield lines and warning signing. | 277700 | 249930 | 2025-03-18 | 0 | 2025-11-03 | 0 | 249930 | Authorized | Authorized | No | CON | State | -1
H12-06-021 | 12 | 5301030 | 6 | Orange Cove | Fresno County | FCOG | FCOG | Various intersections throughout the city. | 1. Install/replace/re-paint pedestrian crossings with hi-visibility continental crossings; 2. Re-paint/install "SLOW SCHOOL XING"/other texts; and 3. Re-paint/relocate existing Stop Bars. | 388800 | 349920 | 2025-12-04 | 0 | 0 | 0 | 21510 | Authorized | Due by 3/31/2028 | No | PE | State | 0
H10-06-019 | 10 | 5252033 | 6 | Parlier | Fresno County | FCOG | FCOG | Intersection of Tuolumne Street and I Street. | Install pedestrian activated crosswalk lighting including Rectangular Rapid Flashing Beacon with LED pedestrian sign, and in-roadway warning lights. | 250000 | 250000 | 2021-09-23 | 0 | 2023-05-12 | 2025-07-14 | 250000 | Authorized | Authorized | No | Closed | State | 0
H11-06-022 | 11 | 5252036 | 6 | Parlier | Fresno County | FCOG | FCOG | At the intersection of Tuolumne Street and Ericka Avenue. | Upgrade pedestrian crossing at uncontrolled location with enhanced safety features. | 250000 | 225000 | 2023-12-11 | 0 | 2025-04-03 | 0 | 225000 | Authorized | Authorized | No | CON | State | -1
H11-06-023 | 11 | 5252037 | 6 | Parlier | Fresno County | FCOG | FCOG | On Academy Avenue approximately 0.4 miles south of the Academy Ave and Manning Ave intersection and on Academy Avenue near the Academy Ave and Sierra Ave intersection. | Upgrade existing guardrails and end treatments. | 215500 | 193950 | 2023-12-11 | 0 | 2026-03-17 | 0 | 193950 | Authorized | Authorized | No | CON | State | -1
H12-06-022 | 12 | 5252042 | 6 | Parlier | Fresno County | FCOG | FCOG | The intersection of Newmark Avenue and 1st Street. | Install raised pedestrian crossing and crossing enhancements including striping, signage and markings. | 350000 | 315000 | 2025-09-23 | 0 | 0 | 0 | 54000 | Authorized | Due by 3/31/2028 | No | PE | State | 0
H12-06-023 | 12 | 5252043 | 6 | Parlier | Fresno County | FCOG | FCOG | Manning Ave from Mendocino Ave to Madsen Ave. | Install separated bike lane. | 350000 | 315000 | 2025-09-24 | 0 | 0 | 0 | 55800 | Authorized | Due by 3/31/2028 | No | PE | State | 0
HSIP5-06-016 | 5 | 5252018 | 6 | Parlier | Fresno County | FCOG | FCOG | Zediker Ave. from 500' S of Manning Ave. to 750' N of Manning Ave.; Manning Ave. from Zediker Ave. to 400' E of Zediker Ave. | Widen roadway; install left-turn, two-way left-turn, and right-turn lanes, and bike lanes | 739697 | 663037.98 | 2013-07-08 | 2015-03-09 | 2018-05-07 | 2021-06-17 | 663037.98 | Authorized | Authorized | No | Closed | Federal | 0
H10-06-020 | 10 | 5122092 | 6 | Porterville | Tulare County | TCAG | TCAG | Olive Avenue & Porter Road/Cloverleaf Street Intersection. | Replace existing traffic signal, add protected left turn phasing for all intersection legs, provide accessible curb ramps at all corners, and add/modify signs. | 666000 | 579420 | 2022-09-15 | 2024-06-13 | 2025-04-29 | 0 | 579420 | Authorized | Authorized | No | CON | State | 0
HSIP5-06-017 | 5 | 5122080 | 6 | Porterville | Tulare County | TCAG | TCAG | Putnam St./D St. | Install protected left-turn phasing | 517418 | 346986.41 | 2013-08-02 | 0 | 2016-07-28 | 2018-11-02 | 346986.41 | Authorized | Authorized | No | Closed | Federal | 0
HSIP7-06-011 | 7 | 5122085 | 6 | Porterville | Tulare County | TCAG | TCAG | Olive Avenue & Newcomb Street Intersection | Replace existing traffic signal. Add NB/SB protected LT phasing; Add mast arm mounted LT heads for EB/WB. Modify median noses, add ADA ramps at all corners, add crosswalks on south and west legs, add/modify signs, install APS signal. | 688831.32 | 395973.81 | 2017-07-19 | 2020-03-18 | 2020-10-22 | 2023-10-23 | 395973.81 | Authorized | Authorized | No | Closed | Federal
H9-06-016 | 9 | 5216052 | 6 | Reedley | Fresno County | FCOG | FCOG | Minor Arterials and Arterial roadway segments (Reed Ave, Manning Ave, I St, 11th St, Dinuba Ave, Frankwood Ave, Olson Ave and Buttonwillow Ave). | Evaluate roadway signing upgrades through the process of a Roadway Safety Signing Audit (RSSA); install and/or upgrade signs. | 236460.95 | 236460.95 | 2019-05-07 | 0 | 2020-05-27 | 2022-04-07 | 236460.95 | Authorized | Authorized | No | Closed | Federal | 0
HSIP1-06-003 | 1 | 5216036 | 6 | Reedley | Fresno County | FCOG | FCOG | Intersection Of Reed Ave. And Manning Ave.; Reed Ave. Between "I" Street And Manning Ave.; Reed Ave. And North Ave. | Install Traffic Signals; Install Safety Street Lighting; Construct Roundabout; Install In-Pavement Crosswalk Lights. | 533056 | 479750 | 2008-09-18 | 0 | 2016-05-19 | 2019-06-12 | 479750 | Authorized | Authorized | No | Closed | Federal | 0
HSIP1-06-004 | 1 | 5216038 | 6 | Reedley | Fresno County | FCOG | FCOG | Parkway Trail Crossing at Manning Ave. | Install In-Pavement Crosswalk Lights | 132090.33 | 118881.29 | 0 | 0 | 2010-09-14 | 2013-10-15 | 118881.29 | No PE | Authorized | No | Closed | Federal | 0
H11-06-024 | 11 | 5245020 | 6 | San Joaquin | Fresno County | FCOG | FCOG | Three intersections: Colorado Ave/9th St, California Ave/5th St, and California Ave/6th St. | Install/upgrade pedestrian crosswalks with high visibility crossings, medians, and curb ramps. | 225500 | 202950 | 2023-10-25 | 0 | 0 | 0 | 36270 | Authorized | Due by 3/31/2027 | No | PE | State | 0
H11-06-025 | 11 | 5197047 | 6 | Sanger | Fresno County | FCOG | FCOG | Along Jensen Avenue at the Lyon Avenue, Tait Avenue, West Avenue, P Street, and N Street intersections. | Pedestrian crossing improvements at existing crosswalks by upgrading to high visibility crosswalks, installation of new RRFBs, pedestrian crossing signage, red curbing for no parking at improved crosswalks to improve pedestrian sight distances. | 275800 | 248220 | 2023-05-23 | 0 | 2026-01-29 | 0 | 248220 | Authorized | Authorized | No | CON | State | 0
H12-06-024 | 12 | 5096050 | 6 | Selma | Fresno County | FCOG | FCOG | Thompson Avenue and Lewis Street, various intersections along Wright Street, and various intersections along 2nd Street. | Install concrete curb bulb outs, rectangular rapid flashing beacons (RRFBs), solar LED flashing stop signs, new advance pedestrian crossing signs, and replace aging pedestrian crossing signs. | 1000400 | 900360 | 2025-11-19 | 0 | 0 | 0 | 85140 | Authorized | Due by 3/31/2028 | No | PE | State | 0
HSIP6-06-014 | 6 | 5096032 | 6 | Selma | Fresno County | FCOG | FCOG | On Thompson Ave between Dinuba Ave and Rose Ave | Install Rectangular Rapid Flashing Beacons, crosswalks, striping; Construct curb ramps and shoulders | 292886.22 | 266747.2 | 2014-11-26 | 0 | 2017-05-30 | 2021-01-22 | 266747.2 | Authorized | Authorized | No | Closed | Federal | 0
HSIP4-06-006 | 4 | 5281014 | 6 | Shafter | Kern County | KCOG | KCOG | Lerdo Hwy. between Cherry Ave. and Driver Rd. | Install median guardrail, signs, striping, and pavement markings | 1369225.11 | 899999.99 | 0 | 0 | 2012-06-27 | 2013-09-20 | 899999.99 | No PE | Authorized | No | Closed | Federal | 0
HSIP7-06-008 | 7 | 5281027 | 6 | Shafter | Kern County | KCOG | KCOG | Lerdo Highway between Cherry Ave. and Zerker Rd. | Install guardrail | 806826.18 | 806826.18 | 0 | 0 | 2019-09-05 | 2021-03-04 | 806826.18 | No PE | Authorized | No | Closed | Federal
H12-06-025 | 12 | 5193047 | 6 | Taft | Kern County | KCOG | KCOG | Various locations along 6th Street. | Install rectangular rapid flashing beacons (RRFBs), LED flashing stop signs, advanced yield lines/signs, and re-stripe high-visibility crosswalks. | 376000 | 338400 | 2025-10-08 | 0 | 0 | 0 | 40230 | Authorized | Due by 3/31/2028 | No | PE | State | 0
H12-06-026 | 12 | 5193048 | 6 | Taft | Kern County | KCOG | KCOG | Various locations throughout the City | Install enhanced safety features including rectangular rapid flashing beacons (RRFBs), LED flashing stop signs, advanced yield lines/signs, and re-stripe high visibility crosswalks. | 348100 | 313290 | 2025-10-08 | 0 | 0 | 0 | 37350 | Authorized | Due by 3/31/2028 | No | PE | State | 0
H8-06-013 | 8 | 5193040 | 6 | Taft | Kern County | KCOG | KCOG | Kern Street between 1st Street and Hillard Street. | Install twelve (12) Pedestrian Crossing flashing LED solar-powered signs; Install two (2) School Crossing flashing LED solar-powered signs; Install two (2) solar Radar Speed Feed Back Signs, re-paint existing pedestrian crosswalks and pavement markings. | 390935.73 | 386662.7 | 2017-05-11 | 0 | 2018-07-05 | 2020-04-13 | 386662.7 | Authorized | Authorized | No | Closed | Federal | 0
H12-06-027 | 12 | 5072064 | 6 | Tulare | Tulare County | TCAG | TCAG | Santa Fe Trail pedestrian crossings at Laspina Street, Tulare Drive, E Street, M Street, Cherry Street, and Blackstone Street. | Install rectangular rapid flashing beacons (RRFBs). | 388800 | 349920 | 2025-11-04 | 0 | 0 | 0 | 45000 | Authorized | Due by 3/31/2028 | No | PE | State | 0
HSIP2-06-002 | 2 | 5072056 | 6 | Tulare | Tulare County | TCAG | TCAG | Santa Fe Trail And Laspina Ave. | Install In-Pavement Crosswalk Lights. | 143185.06 | 51300 | 0 | 0 | 2014-07-15 | 2016-12-12 | 51300 | No PE | Authorized | No | Closed | Federal | 0
H10-06-021 | 10 | 5946197 | 6 | Tulare County | Tulare County | TCAG | TCAG | Sutter Avenue Pedestrian Crossing to Earlimart Middle School. | Relocate existing crosswalk along Sutter Avenue to the North Spring Road intersection; install Rectangular Rapid Flashing Beacon (RRFB) system with advance warning beacons; upgrade markings; and install curb ramps. | 286021 | 250000 | 2021-06-09 | 0 | 2023-03-13 | 2024-12-10 | 250000 | Authorized | Authorized | No | Closed | State | 0
H10-06-022 | 10 | 5946196 | 6 | Tulare County | Tulare County | TCAG | TCAG | Road 100 from Visalia City Limits to 0.50-mile south of Avenue 256 (3 miles); Road 140 from Avenue 256 to Avenue 280 (3 miles); and Road 192 from Avenue 120 to Avenue 144 (4 miles). | Install/Upgrade edgelines and centerlines stripe with thermoplastic stripe with enhanced wet night visibility. Upgrade pavement marking with thermoplastic pavement marking. | 308600 | 249966 | 2021-06-09 | 0 | 2022-06-28 | 2023-12-15 | 249966 | Authorized | Authorized | No | Closed | State | 0
H10-06-023 | 10 | 5946195 | 6 | Tulare County | Tulare County | TCAG | TCAG | Eight locations along Road 236, Avenue 144, Road 196 north and south of Lort Drive, Road 12, Road 228, and at Road 140/Avenue 272, and Burnett Road/Avenue 152. | Replace existing non-standard, damaged, or obsolete guardrails. | 1705600 | 1705600 | 2023-05-15 | 2024-02-26 | 2025-03-28 | 0 | 1700600 | Authorized | Authorized | No | CON | Mix | 1
H11-06-026 | 11 | 5946215 | 6 | Tulare County | Tulare County | TCAG | TCAG | Avenue 192 from Road 136 to Road 196 (7.5mi) and Avenue 384 from CA-99 (Diagonal 27) to CA-63 (Dinuba Blvd) (12.7mi). | Corridor improvements include installing or upgrading signs, installing centerline rumble strips, and installing edgeline rumble strips. | 679000 | 611100 | 2023-10-02 | 0 | 2026-02-27 | 0 | 610650 | Authorized | Authorized | No | CON | State | 0
H11-06-027 | 11 | 5946212 | 6 | Tulare County | Tulare County | TCAG | TCAG | Various Location throughout Tulare County. Segments include D238/Main St (2mi), Avenue 96 (2 mi), Avenue 304 (3 mi), Road 208 (2 mi), Avenue 144 (11mi), Avenue 120 (12mi), Avenue 264 (2mi) and Road 144 (4mi). | Install/Upgrade edgelines and centerlines stripe along eight corridors with 6 inch Paint Traffic Stripe (2-Coat). Upgrade pavement marking with thermoplastic pavement marking. | 277400 | 249660 | 2023-08-01 | 0 | 2024-11-18 | 0 | 249660 | Authorized | Authorized | No | CON | Federal | 1
H11-06-028 | 11 | 5946213 | 6 | Tulare County | Tulare County | TCAG | TCAG | Various Locations. 8 Locations on 6 roads (Road 192, Road 124, Road 196, Road 152, Avenue 368, and Drive 60). | Upgrade existing, damaged, outdated, and destroyed guardrail to current standards. | 1111100 | 999990 | 2023-08-01 | 2024-09-05 | 0 | 0 | 198450 | Authorized | Past due (due 3/31/2026) | Yes (CON) | ROW | Federal | 1
H11-06-029 | 11 | 5946216 | 6 | Tulare County | Tulare County | TCAG | TCAG | Avenue 308 Crossing at Goshen Elementary School. | Install ADA curb ramps, concrete islands, adjacent sidewalk (include curb&gutter), Rectangular Flashing Beacons with advanced Synchronized Flashing Beacons, upgrade pavement markings. | 277700 | 249930 | 2023-10-04 | 2024-08-13 | 2025-03-05 | 0 | 230805 | Authorized | Authorized | No | CON | State | 0
H12-06-028 | 12 | 5946231 | 6 | Tulare County | Tulare County | TCAG | TCAG | Avenue 184 at Orange Belt Drive. | Install left-turn lanes. | 1387700 | 1248930 | 2025-12-05 | 0 | 0 | 0 | 90000 | Authorized | Due by 3/31/2028 | No | PE | Federal | 0
H12-06-029 | 12 | 5946232 | 6 | Tulare County | Tulare County | TCAG | TCAG | Avenue 56 from E. Sutter Ave. (Earlimart) to Road 232 (Ducor) (12mi), Road 152 from Avenue 144 to Avenue 232 (11mi), Road 224 from Avenue 168 (Canal) to Avenue 192 (3mi), and Avenue 256 from Mooney Blvd. to Road 196 (SR 65) (10mi). | Upgrade and install signs, centerline and edgeline rumble strips, a left-turn lane, and flashing beacons. | 4535000 | 4081500 | 2025-12-05 | 0 | 0 | 0 | 270000 | Authorized | Due by 3/31/2028 | No | PE | Federal | 1
H12-06-030 | 12 | 5946233 | 6 | Tulare County | Tulare County | TCAG | TCAG | Various locations (4) (Diagonal 92B (DRV 92B), Road 68, Avenue 120, and Avenue 368). | Upgrade existing damaged /outdated / destroyed guardrail. | 1109400 | 998460 | 2025-12-05 | 0 | 0 | 0 | 117000 | Authorized | Due by 3/31/2028 | No | PE | Federal | 1
H12-06-031 | 12 | 5946234 | 6 | Tulare County | Tulare County | TCAG | TCAG | Various Locations. Road 126 crossing for Orosi High School, Road 28 crossing for Waukena Joint Union Elementary School, and Road 168 crossing for Woodville Elementary School. | Install rectangular rapid flashing beacons (RRFBs) with advanced synchronized flashing beacons, and upgrade pavement markings. | 388500 | 349650 | 2025-11-25 | 0 | 0 | 0 | 31050 | Authorized | Due by 3/31/2028 | No | PE | State | 0
H8-06-014 | 8 | 5946174 | 6 | Tulare County | Tulare County | TCAG | TCAG | Drive 134 (Spacer Drive) between Road 124 and Road 136 (approx. 2.5 miles). | Install edgeline rumble strips on both side of the roadway, and install advance warning flashing beacons at stop controlled intersections. | 324600.54 | 324600.54 | 2017-10-20 | 0 | 2018-07-13 | 2020-03-03 | 324600.54 | Authorized | Authorized | No | Closed | Federal | 0
H9-06-017 | 9 | 5946185 | 6 | Tulare County | Tulare County | TCAG | TCAG | The intersection of Avenue 144 and Road 96 (Tipton). | Convert intersection to roundabout. | 3587800 | 3587800 | 2019-05-17 | 2022-08-09 | 2024-08-06 | 0 | 3587800 | Authorized | Authorized | No | CON | Federal | 1
H9-06-018 | 9 | 5946186 | 6 | Tulare County | Tulare County | TCAG | TCAG | Two Intersections: Avenue 256 at Road 164 and Avenue 240 at Road 140. | Install overhead Red Flashing Beacons. | 291743.22 | 247278.24 | 2019-05-17 | 2021-04-12 | 2021-12-29 | 2024-01-18 | 247278.24 | Authorized | Authorized | No | Closed | Federal | 1
H9-06-019 | 9 | 5946187 | 6 | Tulare County | Tulare County | TCAG | TCAG | John J. Doyle Elementary School at East Orange Avenue (Porterville) | Install pedestrian crossing enhancements. | 191868.02 | 191583.02 | 2019-05-17 | 2020-02-11 | 2020-09-10 | 2022-06-06 | 191583.02 | Authorized | Authorized | No | Closed | Federal | 0
HRRR1-06-044 | 1 | 5946087 | 6 | Tulare County | Tulare County | TCAG | TCAG | Avenue 256 and Road 140 Intersection | New Traffic Signals | 236467.31 | 188399.7 | 0 | 0 | 2008-09-17 | 2012-01-20 | 188399.7 | No PE | Authorized | No | Closed | Federal | 0
HRRR2-06-045A | 2 | 5946120 | 6 | Tulare County | Tulare County | TCAG | TCAG | Intersection of Road 156 and Avenue 295 | Install traffic signals | 55587.81 | 24000 | 2012-10-31 | 0 | 0 | 2015-01-08 | 24000 | Authorized | No CON | No | Closed | Federal | 0
HRRR2-06-045B | 2 | 5946121 | 6 | Tulare County | Tulare County | TCAG | TCAG | Intersection of Road 156 and Avenue 295 | Install traffic signals | 424991.79 | 280000 | 0 | 0 | 2013-07-12 | 2017-02-08 | 280000 | No PE | Authorized | No | Closed | Federal | 0
HSIP1-06-008 | 1 | 5946079 | 6 | Tulare County | Tulare County | TCAG | TCAG | Intersection Of Avenue 280 And Road 156. | Install Traffic Signals. | 415651.79 | 327251.02 | 2008-06-06 | 0 | 2009-04-29 | 2012-03-05 | 327251.02 | Authorized | Authorized | No | Closed | Federal | 0
HSIP2-06-013 | 2 | 5946093 | 6 | Tulare County | Tulare County | TCAG | TCAG | Avenue 280 (Visalia Rd) And Road 180 (Anderson Rd) | Install Traffic Signal | 467191 | 410253.32 | 0 | 0 | 2010-07-16 | 2013-10-21 | 410253.32 | No PE | Authorized | No | Closed | Federal | 0
HSIP3-06-007 | 3 | 6206020 | 6 | Tulare County | Tulare County | TCAG | TCAG | Intersection Of Sr 63 And Ave. 256 | Install Traffic Signal And Upgrade Intersection; Upgrade Left-Turn Lanes; Realign The West Leg Of Ave. 256 To Correct The Offset | 640643.23 | 350000 | 0 | 0 | 2012-10-29 | 2020-01-14 | 350000 | No PE | Authorized | No | Closed | Federal | 0
HSIP3-06-008 | 3 | 5946128 | 6 | Tulare County | Tulare County | TCAG | TCAG | Intersection Of Ave. 148 And Rd. 256 | Install Traffic Signal | 517002.18 | 433508.24 | 2012-08-24 | 0 | 2013-06-10 | 2015-10-28 | 433508.24 | Authorized | Authorized | No | Closed | Federal | 0
HSIP3-06-009 | 3 | 6206023 | 6 | Tulare County | Tulare County | TCAG | TCAG | On SR190 (PM 20.9/21.3) at Road 284 in Tulare County | Install roundabout and traffic warning signs | 363676.92 | 321963.18 | 0 | 0 | 2015-03-25 | 2021-04-26 | 321963.18 | No PE | Authorized | No | Closed | Federal | 0
HSIP5-06-018 | 5 | 5946134 | 6 | Tulare County | Tulare County | TCAG | TCAG | Indian Reservation Rd. (M137) from Ave. 138 to the Tule River Indian Reservation | Install guardrail, signs, and pavement markings | 1131332.39 | 900000 | 2013-04-05 | 0 | 2015-03-09 | 2017-02-08 | 900000 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-06-019 | 5 | 5946135 | 6 | Tulare County | Tulare County | TCAG | TCAG | Fifty-two (52) stop controlled intersections | Upgrade signs and pavement markings; install flashing beacons | 897856.45 | 799889.03 | 2013-04-05 | 0 | 2015-06-19 | 2018-01-26 | 799889.03 | Authorized | Authorized | No | Closed | Federal | 0
HSIP6-06-015 | 6 | 5946146 | 6 | Tulare County | Tulare County | TCAG | TCAG | On Avenue 152 (Olive St) between SR 99 and Rd 222 (N Elderwood St) | Install traffic signals, left turn lanes and rumble stripes | 1916982.76 | 1749999.98 | 2014-07-31 | 2016-01-12 | 2018-04-05 | 2022-02-17 | 1749999.98 | Authorized | Authorized | No | Closed | Federal | 0
HSIP6-06-016 | 6 | 5946147 | 6 | Tulare County | Tulare County | TCAG | TCAG | Various locations throughout unincorporated Tulare County | Upgrade striping and markings; install flashing beacons and High Friction Surface treatment | 1462886.25 | 1389720.28 | 2014-07-31 | 0 | 2016-07-26 | 2022-11-09 | 1389720.28 | Authorized | Authorized | No | Closed | Federal | 0
HSIP7-06-012 | 7 | 5946161 | 6 | Tulare County | Tulare County | TCAG | TCAG | Worth Drive (M 146) between Road 278 and Road Road 284, located on the east side of the County near Porterville | Install guardrails, and centerline rumble strips/stripes, improve signs and striping | 305069 | 304646.59 | 2016-07-26 | 0 | 2019-01-10 | 2021-02-02 | 304646.59 | Authorized | Authorized | No | Closed | Federal
HSIP7-06-013 | 7 | 5946162 | 6 | Tulare County | Tulare County | TCAG | TCAG | Avenue 328 from Road 112 to Road 156 | Safety improvements along Avenue 328 between Road 112 and Road 156 consisting of the installation of left-turn pockets. | 1556020.11 | 1325057.75 | 2016-07-26 | 2020-01-09 | 2021-11-24 | 2024-02-01 | 1325057.75 | Authorized | Authorized | No | Closed | Federal
HSIP7-06-014 | 7 | 5946163 | 6 | Tulare County | Tulare County | TCAG | TCAG | On Avenue 232 from Road 36 to Road 76 (Palm St.) | Installation of three (3) left turn lanes in selected intersections; and install edge line rumble strips/stripes | 1155663.49 | 1033363.28 | 2016-07-26 | 2020-01-29 | 2021-01-22 | 2022-11-23 | 1033363.28 | Authorized | Authorized | No | Closed | Federal
HSIP3-06-010 | 3 | 5044065 | 6 | Visalia | Tulare County | TCAG | TCAG | Intersection Of Mooney Blvd. And Goshen Ave. | Install Traffic Signal; Construct Curb, Gutter, Sidewalk, And Curb Ramps; Improve Railroad Signs/Signals | 413999.37 | 298000 | 0 | 0 | 2013-01-09 | 2015-11-18 | 298000 | No PE | Authorized | No | Closed | Federal | 0
HSIP5-06-020 | 5 | 5044095 | 6 | Visalia | Tulare County | TCAG | TCAG | Ben Maddox Way/Douglas St. | Install traffic signals with vehicle/bicycle loops; construct curb ramps | 618501.07 | 309900 | 0 | 0 | 2015-08-28 | 2018-01-31 | 309900 | No PE | Authorized | No | Closed | Federal | 0
HSIP5-06-021 | 5 | 5044096 | 6 | Visalia | Tulare County | TCAG | TCAG | Main St./Giddings St.; Murray Ave./Jacob St.; Walnut Ave./Chinowth St.; Walnut Ave./County Center St.; Tulare Ave./Giddings St. | Install traffic signals, left-turn phasing, pedestrian improvements, bike detection loops, striping, and pavement markings; construct curb ramps | 1364052.47 | 878300 | 2013-08-02 | 0 | 2015-08-14 | 2017-12-06 | 878300 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-06-022 | 5 | 5044097 | 6 | Visalia | Tulare County | TCAG | TCAG | Area around Oval Park | Install bike lanes, crosswalks, signs and striping | 1442299.23 | 574500 | 0 | 0 | 2014-11-13 | 2018-02-21 | 574500 | No PE | Authorized | No | Closed | Federal | 0
H11-06-030 | 11 | 5287063 | 6 | Wasco | Kern County | KCOG | KCOG | The Intersection of Hwy 43 (known as F Street) and 8th Street. | Install Rectangular Rapid-Flashing Beacon (RRFB), bulb-outs, ADA ramps, Advance STOP or YIELD markings and traffic signs, crosswalk visibility enhancements, stripe and pavement markings at uncontrolled location with enhanced safety. | 317000 | 249990 | 2023-08-17 | 0 | 2025-06-16 | 0 | 249990 | Authorized | Authorized | No | CON | State | 0
H11-06-031 | 11 | 5287064 | 6 | Wasco | Kern County | KCOG | KCOG | The Intersection of Hwy 46 and Poplar Avenue. | Install High Intensity Activated Crosswalk "HAWK" pedestrian hybrid beacon system, traffic signs, stripe and pavement markings at uncontrolled location with enhanced safety. | 521200 | 469080 | 2023-08-17 | 0 | 2025-06-16 | 0 | 469080 | Authorized | Authorized | No | CON | State | 0
H8-06-015 | 8 | 5287051 | 6 | Wasco | Kern County | KCOG | KCOG | Various locations around Barker Park | Install Rectangular Rapid Flashing Beacons (RRFBs), high visibility crosswalks, infill sidewalk, and ADA curb ramps. | 195850.01 | 160920 | 2017-04-10 | 0 | 2018-07-19 | 2020-04-13 | 160920 | Authorized | Authorized | No | Closed | Federal | 0
H9-06-021 | 9 | 5287057 | 6 | Wasco | Kern County | KCOG | KCOG | Various locations on local roadways throughout Wasco. | Upgrade roadway signs and various intersections as recommended in 2017 City of Wasco Roadway Safety Signs Audit Project Report. | 56794.28 | 56794.28 | 2019-04-03 | 0 | 2021-07-23 | 2023-10-23 | 56794.28 | Authorized | Authorized | No | Closed | Federal | 0
HSIP1-06-006 | 1 | 5287023 | 6 | Wasco | Kern County | KCOG | KCOG | Mid-Block Crosswalk On Poso Drive Between Griffith Ave. And Poplar Ave.; Intersection Of Palm Ave. And 9Th Place. | Install In-Pavement Crosswalk Lights. | 186615.1 | 167818.58 | 2008-09-17 | 0 | 2009-08-18 | 2012-07-09 | 167818.58 | Authorized | Authorized | No | Closed | Federal | 0
HSIP2-06-012 | 2 | 5287025 | 6 | Wasco | Kern County | KCOG | KCOG | 7Th Street Between Broadway And Palm Avenues | Bicycle/Pedestrian Improvements | 174840.64 | 157356.56 | 2010-09-14 | 0 | 2013-01-18 | 2014-07-30 | 157356.56 | Authorized | Authorized | No | Closed | Federal | 0
HSIP3-06-004 | 3 | 5287029 | 6 | Wasco | Kern County | KCOG | KCOG | Palm Ave. Between Sr 46 And 9Th Place | Construct Ada Compliant Curb, Gutter, Sidewalk, And Curb Ramps | 265641.04 | 181090.35 | 2010-09-14 | 0 | 2015-02-06 | 2016-02-26 | 181090.35 | Authorized | Authorized | No | Closed | Federal | 0
HSIP7-06-009 | 7 | 5287046 | 6 | Wasco | Kern County | KCOG | KCOG | Various locations within the Wasco city limits | Roadway Safety Sign Audit and sign upgrade/installation project | 132776.99 | 126631.43 | 2016-03-11 | 0 | 2017-08-16 | 2019-09-19 | 126631.43 | Authorized | Authorized | No | Closed | Federal
H9-07-001 | 9 | 5130022 | 7 | Alhambra | Los Angeles County | SCAG | MTA | Various signalized intersections throughout the City of Alhambra. | Install pedestrian countdown signal head systems. | 876000 | 876000 | 2019-10-23 | 0 | 2023-07-06 | 0 | 876000 | Authorized | Authorized | No | CON | Federal | 2
HSIP2-07-001 | 2 | 5130021 | 7 | Alhambra | Los Angeles County | SCAG | MTA | Mission Rd. From Fremont Ave. To Atlantic Blvd. | Construct Raised Medians And 3 Left-Turn Lanes W/ Dedicated Left-Turn Phasing; Install Traffic Signals, Signs, Safety Lighting And Pavement Markings | 497000 | 389896.5 | 0 | 0 | 2016-09-23 | 2020-12-08 | 389896.5 | No PE | Authorized | No | Closed | Federal | 0
H11-07-001 | 11 | 5355033 | 7 | Artesia | Los Angeles County | SCAG | MTA | 10 unsignalized intersections, 3 signalized intersections, and one mid-block pedestrian enhancements. | Installation of Rapid Flashing Beacon at two locations, high visibility crosswalks, raised crosswalk at mid-block, red curbing, pavement markings, and signage for crosswalk enhancements. | 232700 | 209430 | 0 | 0 | 2026-03-27 | 0 | 209430 | No PE | Authorized | No | CON | State | 0
H11-07-002 | 11 | 5355032 | 7 | Artesia | Los Angeles County | SCAG | MTA | 166th from Pioneer To City Property West Line to Property East Line. | Installation of bike lanes. | 250000 | 225000 | 0 | 0 | 2023-05-16 | 2025-03-27 | 225000 | No PE | Authorized | No | Closed | State | 0
HSIP4-07-006 | 4 | 5355024 | 7 | Artesia | Los Angeles County | SCAG | MTA | 166th St.; 183rd St.; Gridley Rd.; Artesia Blvd.; Pioneer Blvd.; Norwalk Blvd.; South St. | Upgrade signs, sign supports, delineation, pavement markings and curb ramps; install speed feedback signs | 381034.98 | 342931.48 | 2012-02-14 | 0 | 2014-02-07 | 2016-03-11 | 342931.48 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-07-001 | 5 | 5355026 | 7 | Artesia | Los Angeles County | SCAG | MTA | Eight (8) intersections (Arteisa Blvd. with Pioneer Blvd., Roseton Ave., Gridley Rd. and Norwalk Blvd.; 183rd St. with Alburtis Ave., Pioneer Blvd. and Norwalk Blvd.; and South St. with Norwalk Blvd.) | Upgrade traffic signal visibility, synchronize traffic signals, install illuminated street signs, pedestrian countdown heads, and CCTV surveillance | 405905 | 322330.5 | 2013-06-03 | 0 | 2014-07-25 | 2016-11-15 | 322330.5 | Authorized | Authorized | No | Closed | Federal | 0
HSIP6-07-001 | 6 | 5355027 | 7 | Artesia | Los Angeles County | SCAG | MTA | Various locations on Pioneer Blvd, South St, Norwalk Blvd, and Artesia Blvd/Clarkdale Ave | Upgrade traffic signal, synchronize traffic signals, install illuminated street signs, pedestrian countdown heads, and CCTV surveillance | 267928 | 216155 | 2015-08-18 | 0 | 2017-11-08 | 2022-07-21 | 216155 | Authorized | Authorized | No | Closed | Federal | 0
HSIP6-07-002 | 6 | 5112019 | 7 | Azusa | Los Angeles County | SCAG | MTA | One-mile segment of Arrow Highway between Citrus Ave and approx. 500' west of Azusa Ave | Install raised medians | 593652.48 | 490585.46 | 2017-01-03 | 0 | 2021-08-24 | 2024-07-01 | 490585.46 | Authorized | Authorized | No | Closed | Federal | 0
H10-07-001 | 10 | 5323040 | 7 | Baldwin Park | Los Angeles County | SCAG | MTA | Intersection of Merced Ave and Vineland Ave. | Modify signal system to provide left-turn phasing; and improve signal hardware. | 381000 | 281940 | 0 | 0 | 2022-08-09 | 2024-09-11 | 281940 | No PE | Authorized | No | Closed | State | 0
HSIP2-07-035 | 2 | 5323022 | 7 | Baldwin Park | Los Angeles County | SCAG | MTA | Various Mid-Block Locations Citywide | Install Traffic Calming Roadway Devices | 142167.88 | 99090 | 0 | 0 | 2010-07-24 | 2012-10-26 | 99090 | No PE | Authorized | No | Closed | Federal | 0
HSIP5-07-002 | 5 | 5323032 | 7 | Baldwin Park | Los Angeles County | SCAG | MTA | Maine-Pacific Ave. between Ramona Blvd. and Bogart Ave. | Install traffic signals and raised medians | 383000 | 344600 | 2013-06-13 | 0 | 2021-04-16 | 0 | 344600 | Authorized | Authorized | No | CON | Federal | 0
H11-07-003 | 11 | 5272020 | 7 | Bell | Los Angeles County | SCAG | MTA | 28 signalized intersections throughout the City of Bell. | Upgrade traffic signal hardware with new lenses, back-plates, mounting, size, number, audible pedestrian push buttons, and pedestrian countdown signal heads. | 1237200 | 1113480 | 0 | 0 | 2024-04-18 | 0 | 1113480 | No PE | Authorized | No | CON | State | 0
HSIP7-07-001 | 7 | 5272015 | 7 | Bell | Los Angeles County | SCAG | MTA | Various intersections in the City of Bell, principally on Atlantic Avenue, Florence Avenue and Gage Avenue | Installation of pedestrian countdown signal heads and upgrading pedestrian ramps to ADA standards | 159070 | 144000 | 2017-01-17 | 0 | 2018-07-17 | 2020-03-30 | 144000 | Authorized | Authorized | No | Closed | Federal
H11-07-004 | 11 | 5373031 | 7 | Bell Gardens | Los Angeles County | SCAG | MTA | Intersections of Florence Ave/Garfield Ave and Eastern Ave/Gage Ave. | Install raised median on approaches, improve pavement friction, install pavement markings, improve signal timing, upgrade roadway signage and striping. | 483500 | 435150 | 2024-05-21 | 0 | 2025-09-12 | 0 | 435150 | Authorized | Authorized | No | CON | State | 0
H8-07-001&002 | 8 | 5373025 | 7 | Bell Gardens | Los Angeles County | SCAG | MTA | The intersection of Eastern Avenue and Lubec Street and the intersection of Garfield Avenue and Loveland Street | Install protected-permissive left-turn phases and signal heads on new poles where left turn lanes already exist for north/southbound directions. | 585153.14 | 544265.68 | 2018-01-12 | 0 | 2019-09-13 | 2022-11-16 | 544265.68 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-07-003 | 5 | 5373021 | 7 | Bell Gardens | Los Angeles County | SCAG | MTA | Six (6) intersections (Florence Ave. with Eastern Ave., Ajax Ave., El Selinda Ave., and S. Garfield Ave.; Eastern Ave. with Watcher St.; and E. Gage Avenue with Darwell Ave.) | Install Emergency Vehicle Pre-emption (EVP) systems | 133426.21 | 120082.99 | 2013-05-03 | 0 | 2014-05-08 | 2018-03-20 | 120082.99 | Authorized | Authorized | No | Closed | Federal | 0
H9-07-002 | 9 | 5348032 | 7 | Bellflower | Los Angeles County | SCAG | MTA | Bellflower Blvd from Artesia Blvd to south City Limits (350' south of Rose St). | Install Class Il bike lane, raised median, bulb-outs, and high visibility crosswalks. | 2087501.67 | 1360080 | 0 | 0 | 2022-07-06 | 2024-07-18 | 1360080 | No PE | Authorized | No | Closed | Federal | 0
HSIP3-07-017 | 3 | 5348029 | 7 | Bellflower | Los Angeles County | SCAG | MTA | Bellflower Blvd. From Walnut St. To Flora Vista St. | Install Traffic Signals; Construct Curb Extensions; Install In-Pavement Crosswalk Lights; Improve Signange And Visibility | 1325893.06 | 821700 | 0 | 0 | 2015-04-30 | 2017-04-06 | 821700 | No PE | Authorized | No | Closed | Federal | 0
HSIP3-07-011 | 3 | 5200038 | 7 | Burbank | Los Angeles County | SCAG | MTA | Intersections Of Verdugo Ave./Parish Place And Verdugo Ave./Keystone St. | Modify/Upgrade Two Existing Traffic Signals; Construct Bulb-Outs | 677307.1 | 587182.96 | 2010-09-02 | 0 | 2013-03-01 | 2017-10-24 | 587182.96 | Authorized | Authorized | No | Closed | Federal | 0
HSIP4-07-034 | 4 | 5200039 | 7 | Burbank | Los Angeles County | SCAG | MTA | Verdugo Ave. between Flower St. and Clybourn | Add protected left turn phasing; extend bike lanes; construct sidewalks | 1164176.39 | 724734.13 | 2011-06-21 | 0 | 2014-07-08 | 2018-07-09 | 724734.13 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-07-004 | 5 | 5200045 | 7 | Burbank | Los Angeles County | SCAG | MTA | North San Fernando Blvd. between Grismer Ave. and Walnut Ave. | Construct medians; install crosswalks and left-turn phasing | 1442769.52 | 775585.92 | 2013-05-10 | 0 | 2017-03-02 | 2019-11-19 | 775585.92 | Authorized | Authorized | No | Closed | Federal | 0
HSIP6-07-003 | 6 | 5200047 | 7 | Burbank | Los Angeles County | SCAG | MTA | On Buena Vista St between Glenoaks Blvd and Riverside Dr; On Magnolia Blvd between N Lima St and Lamer St | Upgrade traffic signals (interconnect); Install crosswalks | 266025.6 | 239370.11 | 2015-03-12 | 0 | 0 | 2018-07-17 | 239370.11 | Authorized | No CON | No | Closed | Federal | 0
H11-07-005 | 11 | 5463022 | 7 | Calabasas | Los Angeles County | SCAG | MTA | Various signalized intersections throughout Calabasas. | Improve signal hardware, install intersection striping, install additional indications, upgrade pedestrian push buttons, install reflective backplates, add pedestrian countdown timers, and install warning signs. | 265930 | 239337 | 2023-09-11 | 0 | 2026-04-03 | 0 | 239337 | Authorized | Authorized | No | CON | State | 0
H12-07-001 | 12 | 5463024 | 7 | Calabasas | Los Angeles County | SCAG | MTA | Various locations along Mulholland Hwy, Las Virgenes Rd, Dry Canyon Cold Creek Rd, Old Topanga Canyon Rd, Helmond Dr, De Berry Drive, and Canwood St. | Remove and replace / upgrade damaged guardrail system; install new guardrail at southeastern corner of Old Topanga Canyon Rd and Mulholland Hwy. | 520600 | 468540 | 2025-05-15 | 0 | 0 | 0 | 22500 | Authorized | Due by 3/31/2028 | No | PE | State | 0
H12-07-002 | 12 | 5463023 | 7 | Calabasas | Los Angeles County | SCAG | MTA | 22 traffic signals at various locations. | Install leading pedestrian interval (LPI) at 22 traffic signals, replace 10 pedestrian indications with countdown timers, and install Accessible Pedestrian Systems (APS) at 4 traffic signals. | 271800 | 244620 | 2025-05-15 | 0 | 0 | 0 | 16650 | Authorized | Due by 3/31/2028 | No | PE | State | 0
H12-07-003 | 12 | 0 | 7 | Carson | Los Angeles County | SCAG | MTA | The intersection of Dolores St and Sepuleda Blvd. | Improve intersection lighting, improve signal hardware, signing/striping for NB approach, implement split phasing, install protected left turn signal phasing, pedestrian countdown signal heads, high visibility crosswalks. | 709300 | 638370 | 0 | 0 | 0 | 0 | 0 | Due by 12/31/2026 | Due by 3/31/2028 | No | Not Started | State | 0
H12-07-004 | 12 | 0 | 7 | Carson | Los Angeles County | SCAG | MTA | The intersections of E. University Dr. at Avalon Blvd. and Avalon Blvd. at MLK Jr. St. | Install pedestrian crossings with enhanced safety features; install leading pedestrian interval (LPI). | 385000 | 346500 | 0 | 0 | 0 | 0 | 0 | No PE | Due by 3/31/2028 | No | Not Started | State | 0
H8-07-003 | 8 | 5403030 | 7 | Carson | Los Angeles County | SCAG | MTA | Six (6) Intersections - Avalon Blvd at Victoria Street, Main Street at Sepulveda Blvd, Main Street at 220th Street, Main Street at 223rd Street, Figueroa Street at 223rd Street, and Figueroa Street at Torrance Blvd. | Construct intersection upgrades (new signal heads, ADA ramps, service upgrades, LED safety lighting, bike detection, audible pedestrian signals, signal poles, signal mast arms, signal cabinets, raised medians, signing, striping, and left-turn phasing) | 1912100 | 1720890 | 2020-05-11 | 0 | 2025-02-18 | 0 | 1720890 | Authorized | Authorized | No | CON | Federal | 2
HSIP5-07-005 | 5 | 5403022 | 7 | Carson | Los Angeles County | SCAG | MTA | Avalon Blvd./Carson St. | Construct right-turn lanes; modify traffic signals; install pedestrial countdown heads | 734026 | 637596 | 2013-06-24 | 0 | 2016-03-16 | 0 | 0 | Authorized | Authorized | No | Withdrawn | Federal | 0
HSIP6-07-004R | 6 | 5403035 | 7 | Carson | Los Angeles County | SCAG | MTA | Various locations on Avalon, Central Ave, Del Amo Blvd, 223rd St, Main St, Victoria St, and Carson St in Carson. | Install bike lanes. | 1742000 | 1567800 | 0 | 0 | 2025-06-25 | 0 | 1567800 | No PE | Authorized | No | CON | Federal | 2
HSIP6-07-005R | 6 | 0 | 7 | Carson | Los Angeles County | SCAG | MTA | Various locations on Figueroa St, Main St, Victoria St, Avalon Blvd, University Dr, and Del Amo Blvd. | Install bike lanes. | 1124600 | 1012140 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2024) | Past due (due 6/30/2025) | Yes (PE & CON) | Not Started | State | -2
HSIP7-07-002 | 7 | 5403028 | 7 | Carson | Los Angeles County | SCAG | MTA | Intersection of 190th St/Victoria Ave and Figueroa St | Install Protected Left Turns, Upgrade Signal Hardware, Improve Curb Ramps, install countdown pedestrian heads, upgrade APS | 202400 | 202400 | 2018-03-08 | 0 | 2022-02-02 | 0 | 0 | Authorized | Authorized | No | Withdrawn | Federal
HSIP7-07-003 | 7 | 5325017 | 7 | Cerritos | Los Angeles County | SCAG | MTA | Bloomfield Avenue & 166th Street in the City of Cerritos | Modification of the existing traffic signal from a protective-permissive signal to a fully protected signal | 365017.9 | 350772.83 | 2017-11-08 | 0 | 2019-04-30 | 2021-10-26 | 350772.83 | Authorized | Authorized | No | Closed | Federal
HSIP3-07-026 | 3 | 5162023 | 7 | Claremont | Los Angeles County | SCAG | MTA | Indian Hill Blvd. Between American Ave. And Oak Park Dr. | Widen Turn Lane; Modify Intersection; Relocate Signal Pole; Upgrade Curb Ramps; Increase Turn Pocket Length; Remove Turn Pocket, Reconfigure/Extend Median | 1208378.08 | 900000 | 0 | 0 | 2012-05-25 | 2014-07-11 | 900000 | No PE | Authorized | No | Closed | Federal | 0
H10-07-002 | 10 | 5362028 | 7 | Commerce | Los Angeles County | SCAG | MTA | Various signalized intersections throughout the City. | Install left turn phasing at signalized locations with existing left turn pockets, and install signal hardware improvements to the lenses, back-plates with retroreflective borders. | 2055496 | 2055496 | 2021-10-01 | 0 | 2023-05-26 | 0 | 2055496 | Authorized | Authorized | No | CON | State | 0
H11-07-006 | 11 | 5362030 | 7 | Commerce | Los Angeles County | SCAG | MTA | 29 signalized intersections citywide. | Install Leading Pedestrian Interval (LPI), retro-reflective backplates, and nearside signals; upgrade signal heads and signal hardware; install other safety improvements including crosswalks. | 1707341 | 1223420 | 2023-04-21 | 0 | 2024-07-24 | 0 | 1223420 | Authorized | Authorized | No | CON | State | 0
HSIP4-07-051 | 4 | 5362021 | 7 | Commerce | Los Angeles County | SCAG | MTA | Washington Blvd./Garfield Ave.; Washington Blvd./Yates Ave.; Garfield Ave./ Yates Ave.; and Garfield Ave./Malt Ave. | Construct sidewalk with curb ramp Improvements and traffic signal modifications | 768540.81 | 575400 | 2015-01-20 | 0 | 2016-11-18 | 2020-04-21 | 575400 | Authorized | Authorized | No | Closed | Federal | 0
HSIP7-07-004 | 7 | 5362023 | 7 | Commerce | Los Angeles County | SCAG | MTA | Signalized Intersections on the following corridors: Eastern Ave from Randolf St to Stevens Pl: Telegraph Rd from Garfield to Atlantic Blvd; Atlantic from Ferguson Dr to Sheila St; Garfield from Flotilla to Randolph St; Slauson from Eastern to Gage. | Upgrade traffic interconnected system at 39 intersections | 1261423 | 1135280 | 0 | 0 | 2019-11-08 | 2023-07-11 | 1135280 | No PE | Authorized | No | Closed | Federal
H8-07-005 | 8 | 0 | 7 | Compton | Los Angeles County | SCAG | MTA | The Compton Blvd. corridor between Willowbrook Avenue and Central Avenue. | Install bike lanes and lighting along the corridor, and enhance pedestrian crossings at fifteen (15) intersections. | 1298000 | 1168200 | 0 | 0 | 0 | 0 | 0 | No PE | Past due (due 12/31/2022) | Yes (CON) | Not Started | Federal | 2
H8-07-006 | 8 | 0 | 7 | Compton | Los Angeles County | SCAG | MTA | Citywide | Install (20) Pedestrian Countdown Heads. | 249800 | 249800 | 0 | 0 | 0 | 0 | 0 | No PE | Past due (due 9/30/2022) | Yes (CON) | Not Started | Federal | 2
HSIP7-07-005 | 7 | 0 | 7 | Compton | Los Angeles County | SCAG | MTA | Compton Boulevard, from Willowbrook Avenue to eastern City limits. | Installation of raised medians and Class II bicycle lanes | 1928400 | 1691098 | 0 | 0 | 0 | 0 | 0 | No PE | Past due (due 12/31/2022) | Yes (CON) | Not Started | Federal
H10-07-003 | 10 | 0 | 7 | Covina | Los Angeles County | SCAG | MTA | Various uncontrolled crosswalk locations throughout the City of Covina. | Install inroad warning lights and/or rapid flashing beacons, signage, pavement markings, high visibility crosswalk and curb ramps. | 282500 | 250000 | 0 | 0 | 0 | 0 | 0 | No PE | Past due (due 3/31/2024) | Yes (CON) | Not Started | State | 0
H9-07-003 | 9 | 5118021 | 7 | Covina | Los Angeles County | SCAG | MTA | Various locations throughout the City of Covina. | Install inroad warning lights and/or rapid flashing beacons, signage, pavement markings, high visibility crosswalk and curb ramps at uncontrolled crosswalk locations. | 310331 | 250000 | 0 | 0 | 2020-09-10 | 2024-01-17 | 250000 | No PE | Authorized | No | Closed | Federal | 0
H11-07-007 | 11 | 5369016 | 7 | Cudahy | Los Angeles County | SCAG | MTA | 13 signalized intersections citywide. | Install retro-reflective backplates, other signal improvements, and implement Leading Pedestrian Interval (LPI) timing at all signals Citywide. Re-stripe crosswalks to implement high-visibility crosswalks at all signalized intersections. Furnish and install bulb outs. | 1353100 | 1217790 | 2023-10-11 | 0 | 0 | 0 | 180000 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE | State | 0
HSIP6-07-006 | 6 | 5369009 | 7 | Cudahy | Los Angeles County | SCAG | MTA | Various intersections on Atlantic Ave | Install pedestrian countdown heads and protected left-turn phasing | 528146.03 | 475331.12 | 2015-01-20 | 0 | 2017-06-20 | 2021-04-14 | 475331.12 | Authorized | Authorized | No | Closed | Federal | 0
HSIP7-07-006 | 7 | 5369012 | 7 | Cudahy | Los Angeles County | SCAG | MTA | Along Salt Lake Ave between Walnut St & Patata St/Atlantic Ave. | Installation of pedestrian safety enhancements (advisory signage, crossings) | 302169.89 | 259785.04 | 2016-11-18 | 0 | 2021-08-24 | 2026-01-05 | 259785.04 | Authorized | Authorized | No | Closed | Federal
H10-07-004 | 10 | 5240038 | 7 | Culver City | Los Angeles County | SCAG | MTA | Overland Avenue Corridor, Maytime Lane to Northgate Street. | Install High Friction Surface Treatment (HFST) pavement on curved segment of Overland Avenue Corridor, Maytime Lane to Northgate Street. | 786236 | 786236 | 2021-12-22 | 0 | 2024-10-02 | 0 | 676846 | Authorized | Authorized | No | CON | State | 0
H10-07-005 | 10 | 5240040 | 7 | Culver City | Los Angeles County | SCAG | MTA | 10 signalized intersections: Washington Blvd(4); Culver Blvd(1); Overland Ave(2); Jefferson Blvd(1);Centinela Ave(1); Sepulveda Blvd(1). | Improve signal hardware; provide protected left turn phase; and modify signal phasing to implement a Leading Pedestrian Interval (LPI). | 2766700 | 2766700 | 2021-12-22 | 0 | 2025-03-21 | 0 | 2766700 | Authorized | Authorized | No | CON | State | 0
H10-07-006 | 10 | 5240039 | 7 | Culver City | Los Angeles County | SCAG | MTA | 12 non-signalized intersections: 8 on Washington Blvd, 2 on Sepulveda Blvd, 1 on Washington Pl and 1 on Higuera St. | Add intersection lighting, install/upgrade stop signs and other warning and regulatory signs, and upgrade intersection pavement markings. | 1545700 | 1545700 | 2021-12-22 | 0 | 2024-05-16 | 0 | 1545700 | Authorized | Authorized | No | CON | State | 0
H12-07-005 | 12 | 0 | 7 | Culver City | Los Angeles County | SCAG | MTA | Green Valley Cir from Sepulveda Blvd to Centinela Ave, and Buckingham Pkwy from Green Valley Cir to Slauson Ave, in the Fox Hills neighborhood. | Install new bikeways (Class II/IV). | 388800 | 349920 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2025) | Due by 3/31/2028 | Yes (PE) | Not Started | State | 0
H12-07-006 | 12 | 0 | 7 | Culver City | Los Angeles County | SCAG | MTA | three (3) locations on Green Valley Cir between Sepulveda Blvd and Centinela Ave, in the Fox Hills Neighborhood. | Install pedestrian crossing enhancements. | 387900 | 349110 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2025) | Due by 3/31/2028 | Yes (PE) | Not Started | State | 0
HSIP6-07-007 | 6 | 5240032 | 7 | Culver City | Los Angeles County | SCAG | MTA | Centinela Ave/Washington Blvd, Centinela Ave/Washington Pl, Duquesne Ave/Jefferson Blvd, Jefferson Blvd/Jordan Way, Jefferson Blvd/Machado Rd, Sepulveda Blvd/Washington Blvd, Sepulveda Blvd/Washington Pl | Upgrade traffic signals; Install protected left-turn phasing | 1187641.72 | 1039389 | 2014-07-30 | 0 | 2016-02-12 | 2018-03-29 | 1039389 | Authorized | Authorized | No | Closed | Federal | 0
HSIP7-07-007 | 7 | 5240035 | 7 | Culver City | Los Angeles County | SCAG | MTA | Twelve signalized intersections on the arterial network throughout the city: 2 on Sepulveda Blvd; 7 on Washington Blvd; 1 on Washington Pl; 1 on Culver Blvd; and 1 on Green Valley Circle. | Replace existing permissive left-turn movements with protected/permissive left-turn phases (including new signal standards, mast arms, indications, detection, wiring, and controller upgrades) | 2140262.68 | 2125157.31 | 2018-05-21 | 0 | 2020-06-02 | 2023-11-01 | 2125157.31 | Authorized | Authorized | No | Closed | Federal
H11-07-008 | 11 | 5455018 | 7 | Diamond Bar | Los Angeles County | SCAG | MTA | On Diamond Bar Blvd at Golden Springs, Sunset Crossing, Grand Ave, Pathfinder, Brea Canyon. On Golden Springs at Brea Canyon, Carpio. Grand Ave/Summitridge. Brea Canyon/Pathfinder. | Install nearside supplemental traffic signals, install pedestrian countdown signal heads, and restripe crosswalks to high visibility crosswalks. | 336500 | 302850 | 2023-10-31 | 0 | 2024-08-15 | 0 | 299003.4 | Authorized | Authorized | No | CON | State | 0
HSIP2-07-002 | 2 | 0 | 7 | Diamond Bar | Los Angeles County | SCAG | MTA | Golden Springs Drive, Between Lemon Ave. And Brea Canyon Rd. | Install Frontage Road, Street Lightings, And Median Island Improvemts. | 476300 | 400000 | 0 | 0 | 0 | 0 | 0 | Not Tracked | Not Tracked | No | Not Started | Federal | 0
HSIP2-07-045 | 2 | 5455012 | 7 | Diamond Bar | Los Angeles County | SCAG | MTA | Pathfinder Rd. Between The Intersection Of South Brea Canyon Road/Fern Hollow Dr. And The Northbound State Route 57 (Sr-57) On And Off Ramps | Install Raised Concrete Median Islands. | 101630.43 | 74614.85 | 0 | 0 | 2010-02-17 | 2012-04-20 | 74614.85 | No PE | Authorized | No | Closed | Federal | 0
H11-07-009 | 11 | 5334070 | 7 | Downey | Los Angeles County | SCAG | MTA | Uncontrolled marked pedestrian crossings at: 1. Our Lady of Perpetual Help School on Downey Avenue; 2. St Pius X - St Matthias Academy east crosswalk on Gardendale St; and 3. St Pius X - St Matthias Academy west crosswalk on Gardendale St. | Upgrade uncontrolled marked pedestrian crosswalks to include rectangular rapid flashing beacon (RRFB) and high visibility signing and striping. | 249900 | 224910 | 2023-07-21 | 0 | 2026-02-26 | 0 | 224910 | Authorized | Authorized | No | CON | State | 0
H12-07-007 | 12 | 5334075 | 7 | Downey | Los Angeles County | SCAG | MTA | Fifteen (15) signalized intersections along the Firestone Boulevard corridor extending from Ryerson Avenue to Stewart and Gray Road, and the intersections of Downey Avenue at Alameda Street, and Brookshire Avenue at Alameda Street. | Upgrade existing traffic signal equipment including cabinets, controllers, vehicle indications, pedestrian countdown signal heads, APS pedestrian push buttons, and implementation of leading pedestrian intervals (LPIs). | 1573200 | 1415880 | 2026-01-05 | 0 | 0 | 0 | 198000 | Authorized | Due by 3/31/2028 | No | PE | Federal | 0
H12-07-008 | 12 | 5334076 | 7 | Downey | Los Angeles County | SCAG | MTA | Uncontrolled pedestrian crossings at intersections of Rives Ave & Adwen St and Conrad St & Montgomery St. | Upgrade crosswalks to include rectangular rapid flashing beacons (RRFBs), high visibility signing and striping. | 299700 | 269730 | 2025-12-18 | 0 | 0 | 0 | 35460 | Authorized | Due by 3/31/2028 | No | PE | State | 0
H12-07-009 | 12 | 5334077 | 7 | Downey | Los Angeles County | SCAG | MTA | Nine (9) signalized intersections citywide. | Upgrade existing traffic signal equipment including vehicle indications, pedestrian countdown signal heads, APS pedestrian push buttons, and implementation of leading pedestrian intervals (LPIs). | 650800 | 585720 | 2025-12-18 | 0 | 0 | 0 | 76500 | Authorized | Due by 3/31/2028 | No | PE | State | 0
H12-07-010 | 12 | 5334078 | 7 | Downey | Los Angeles County | SCAG | MTA | Florence Avenue from Vultee Avenue/Arrington Avenue to Woodruff Avenue. | Install raised median. | 608500 | 547650 | 2025-12-19 | 0 | 0 | 0 | 90000 | Authorized | Due by 3/31/2028 | No | PE | State | 0
H12-07-011 | 12 | 5334079 | 7 | Downey | Los Angeles County | SCAG | MTA | Klondike Avenue and Bixler Avenue between Century Boulevard and Downey Avenue. | Install sidewalk and ADA curb ramps on both sides of Klondike Avenue and Bixler Avenue. Convert Klondike Avenue to a Northbound one-way street and Bixler Avenue to a Southbound one-way street with appropriate signage. | 833500 | 750150 | 2025-12-19 | 0 | 0 | 0 | 127530 | Authorized | Due by 3/31/2028 | No | PE | State | 0
H8-07-007 | 8 | 5334064 | 7 | Downey | Los Angeles County | SCAG | MTA | Imperial Highway between Old River School Road and Woodruff Avenue. | Upgrade signals to provide separate left-turn phasing at 3 intersections and provide various safety improvements at other intersections. | 1406449.8 | 1342746.46 | 2018-03-20 | 0 | 2020-03-05 | 2023-10-23 | 1342746.46 | Authorized | Authorized | No | Closed | Federal | 0
HSIP1-07-010 | 1 | 5334031 | 7 | Downey | Los Angeles County | SCAG | MTA | 20+ Intersections Within The City Of Downey | Install Pedestrian Countdown Heads | 41113.04 | 37001.73 | 0 | 0 | 2010-06-01 | 2013-06-20 | 37001.73 | No PE | Authorized | No | Closed | Federal | 0
HSIP1-07-011 | 1 | 5334032 | 7 | Downey | Los Angeles County | SCAG | MTA | In The Vicinity Of 20 Schools | Various Modifications And Improvements To Existing School Traffic Warning Signs, Markings And Pavement Legends. | 101123.1 | 43560 | 0 | 0 | 2010-06-25 | 2014-06-26 | 43560 | No PE | Authorized | No | Closed | Federal | 0
HSIP2-07-037 | 2 | 5334039 | 7 | Downey | Los Angeles County | SCAG | MTA | Woodruff Ave. And Washburn Rd. | Upgrade Traffic Signal. | 185251.01 | 163879.72 | 0 | 0 | 2012-07-05 | 2014-12-22 | 163879.72 | No PE | Authorized | No | Closed | Federal | 0
HSIP3-07-016 | 3 | 5334040 | 7 | Downey | Los Angeles County | SCAG | MTA | On Barlin Ave., Dunrobin Ave., Chaney Ave., Pangborn Ave., Old River School Rd., Rives Ave., Smallwood Ave., Seventh St., Tweedy Ln., and Donovan St. (10 Locations) | Install Solar-Powered Variable Message Speed Feedback Sign In Each Direction | 200200 | 180180 | 0 | 0 | 2011-11-10 | 2013-11-15 | 180180 | No PE | Authorized | No | Closed | Federal | 0
HSIP3-07-027 | 3 | 5334041 | 7 | Downey | Los Angeles County | SCAG | MTA | Woodruff Ave. At Via Amorita | Install Pedestrian-Activated Signal | 179215.01 | 138010.27 | 0 | 0 | 2012-10-30 | 2015-12-23 | 138010.27 | No PE | Authorized | No | Closed | Federal | 0
HSIP4-07-024 | 4 | 5334042 | 7 | Downey | Los Angeles County | SCAG | MTA | Various locations throughout the city | Install pedestrian countdown heads | 92108.27 | 74994.24 | 0 | 0 | 2013-07-08 | 2015-12-22 | 74994.24 | No PE | Authorized | No | Closed | Federal | 0
HSIP4-07-038 | 4 | 5334043 | 7 | Downey | Los Angeles County | SCAG | MTA | Imperial Hwy./Columbia Way | Install left-turn phasing | 237865.89 | 181000 | 0 | 0 | 2013-02-14 | 2015-06-25 | 181000 | No PE | Authorized | No | Closed | Federal | 0
HSIP5-07-006 | 5 | 5334050 | 7 | Downey | Los Angeles County | SCAG | MTA | Imperial Hwy./Downey Ave. | Upgrade traffic signals; install left-turn phasing | 113891.02 | 99518.37 | 0 | 0 | 2016-01-25 | 2019-04-30 | 99518.37 | No PE | Authorized | No | Closed | Federal | 0
HSIP5-07-007 | 5 | 5334053 | 7 | Downey | Los Angeles County | SCAG | MTA | Lakewood Blvd./Florence Ave. | Install left-turn phasing | 155053.16 | 101781.32 | 0 | 0 | 2016-01-22 | 2019-03-21 | 101781.32 | No PE | Authorized | No | Closed | Federal | 0
HSIP5-07-008 | 5 | 5334054 | 7 | Downey | Los Angeles County | SCAG | MTA | Firestone Blvd./Woodruff Ave. | Upgrade traffic signals; install left-turn phasing | 272335.98 | 183172.87 | 0 | 0 | 2016-02-05 | 2019-03-19 | 183172.87 | No PE | Authorized | No | Closed | Federal | 0
HSIP5-07-009 | 5 | 5334048 | 7 | Downey | Los Angeles County | SCAG | MTA | Firestone Blvd. between Patton Rd. and Marbel Ave. | Install raised median islands, left-turn lanes, loop detectors, signs and striping | 949927.77 | 163753.9 | 0 | 0 | 2016-05-17 | 2020-04-21 | 163753.9 | No PE | Authorized | No | Closed | Federal | 0
HSIP5-07-010 | 5 | 5334051 | 7 | Downey | Los Angeles County | SCAG | MTA | Florence Ave./Old River School Rd. (Tecum Rd.) | Upgrade traffic signals; install left-turn phasing | 266324.53 | 186753.94 | 0 | 0 | 2016-01-19 | 2019-03-19 | 186753.94 | No PE | Authorized | No | Closed | Federal | 0
HSIP5-07-011 | 5 | 5334052 | 7 | Downey | Los Angeles County | SCAG | MTA | Bellflower Blvd./Foster Rd. | Upgrade traffic signals; install pedestrian countdown heads, safety lighting, and video detection | 235933.64 | 171746.93 | 0 | 0 | 2016-01-19 | 2019-03-22 | 171746.93 | No PE | Authorized | No | Closed | Federal | 0
HSIP5-07-012 | 5 | 5334049 | 7 | Downey | Los Angeles County | SCAG | MTA | Woodruff Ave. and Foster Rd. | Upgrade traffic signals; install pedestrian countdown heads and safety lighting | 264968.46 | 183913.68 | 0 | 0 | 2016-02-10 | 2019-03-19 | 183913.68 | No PE | Authorized | No | Closed | Federal | 0
HSIP5-07-013 | 5 | 5334056 | 7 | Downey | Los Angeles County | SCAG | MTA | Paramount Blvd. between Firestone Blvd. and Florence Ave. | Install raised median islands, left-turn lanes, signs and striping; replace traffic loop detectors | 404685.27 | 172599.88 | 0 | 0 | 2018-11-02 | 2021-02-10 | 172599.88 | No PE | Authorized | No | Closed | Federal | 0
HSIP5-07-014 | 5 | 5334055 | 7 | Downey | Los Angeles County | SCAG | MTA | Paramount Blvd. between Leeds St. and Firestone Blvd. | Install raised median islands, left-turn lanes, signs and striping; replace traffic loop detectors | 1816470.94 | 300299.82 | 0 | 0 | 2018-09-11 | 2021-06-01 | 300299.82 | No PE | Authorized | No | Closed | Federal | 0
HSIP6-07-008 | 6 | 5334058 | 7 | Downey | Los Angeles County | SCAG | MTA | Firestone Blvd between Westerly City Limits and Old River School Rd | Install raised median, left-turn lanes, signs, striping, and other safety improvements | 1752896.12 | 142988.99 | 0 | 0 | 2018-09-11 | 2021-06-17 | 142988.99 | No PE | Authorized | No | Closed | Federal | 0
HSIP6-07-009 | 6 | 5334057 | 7 | Downey | Los Angeles County | SCAG | MTA | Paramount Blvd/3rd St, Paramount Blvd/5th St, and Paramount Blvd/7th St | Upgrade traffic signals: install split phasing, pedestrian countdown heads, and video detection | 862912.34 | 524656.85 | 0 | 0 | 2016-02-10 | 2019-03-19 | 524656.85 | No PE | Authorized | No | Closed | Federal | 0
HSIP7-07-008 | 7 | 5334061 | 7 | Downey | Los Angeles County | SCAG | MTA | Paramount Boulevard - Gardendale Street to Telegraph Road | Traffic signal upgrades: Fiber optic cable, new controllers, signal hardware, equipment, intersection pedestrian countdown signal heads, safety lighting | 1777611.17 | 1777611.17 | 2017-07-06 | 0 | 2019-12-18 | 2023-05-09 | 1777611.17 | Authorized | Authorized | No | Closed | Federal
HSIP7-07-009 | 7 | 5334062 | 7 | Downey | Los Angeles County | SCAG | MTA | Stewart and Gray - Old River School Road to Firestone Boulevard | Traffic signal upgrades: Fiber optic cable, new controllers, appurtenant equipment, intersection pedestrian countdown signal heads, safety lighting | 2980708.63 | 2182005.32 | 2017-08-18 | 0 | 2019-11-19 | 2022-10-26 | 2182005.32 | Authorized | Authorized | No | Closed | Federal
H10-07-007 | 10 | 5210030 | 7 | El Monte | Los Angeles County | SCAG | MTA | 18 signalized intersections along Peck Road and 11 signalized intersections along Santa Anita Avenue. | Upgrade signal hardware and pedestrian countdown heads. | 1756000 | 1756000 | 2021-11-10 | 0 | 2025-08-01 | 0 | 1756000 | Authorized | Authorized | No | CON | State | 0
H10-07-008 | 10 | 5210031 | 7 | El Monte | Los Angeles County | SCAG | MTA | 7 signalized intersections along Garvey Avenue and 7 signalized intersections along Durfee Avenue. 4 uncontrolled crosswalks at Garvey Ave and Edwards Ave; Garvey Ave and Gage Ave; Garvey Ave and Nevada Ave; and Garvey Ave and Consol Ave. | Upgrade signal hardware and install pedestrian countdown heads. Install Rectangular Rapid Flashing Beacons (RRFB), high visibility signing and striping, and ADA curb ramps. | 1208300 | 1208300 | 2021-11-12 | 0 | 2025-08-01 | 0 | 1208300 | Authorized | Authorized | No | CON | State | 0
H11-07-010 | 11 | 5210036 | 7 | El Monte | Los Angeles County | SCAG | MTA | 4 signalized intersections along Tyler Ave and Valley Blvd. | Upgrade signal hardware and pedestrian countdown heads at three locations; convert signal to mast arm and install pedestrian countdown heads at one location. | 362400 | 326160 | 2024-05-16 | 0 | 0 | 0 | 58230 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE | State | 0
H11-07-011 | 11 | 5210035 | 7 | El Monte | Los Angeles County | SCAG | MTA | Santa Anita Avenue between Valley Boulevard and Tyler Avenue. | Install Class II bike lane striping and signs. | 277000 | 249300 | 2024-05-16 | 0 | 0 | 0 | 44550 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE | State | 0
H12-07-012 | 12 | 5210037 | 7 | El Monte | Los Angeles County | SCAG | MTA | 6 unsignalized intersections along Valley Blvd (El Monte Ave; Shirley Ave; Meeker Ave; La Madera Ave; Allgeyer Ave; Maxson Rd). | Install HAWK signals at 2 locations; install rectangular rapid flashing beacons (RRFBs) at 4 locations; upgrade crosswalks and curb ramps at 6 locations. | 779300 | 701370 | 2026-01-15 | 0 | 0 | 0 | 56610 | Authorized | Due by 3/31/2028 | No | PE | State | 0
H12-07-013 | 12 | 5210038 | 7 | El Monte | Los Angeles County | SCAG | MTA | 2 signalized intersections at Santa Anita Ave/Lower Azusa Rd & Santa Anita Ave/Kings Row; 1 signalized intersection at Valley Blvd/Gibson Rd. | Provide protected left turn phasing; convert signal to mast arm from pedestal-mounted; and implement leading pedestrian interval (LPI). | 308800 | 277920 | 2026-01-15 | 0 | 0 | 0 | 22410 | Authorized | Due by 3/31/2028 | No | PE | State | 0
H9-07-005 | 9 | 5276033 | 7 | Gardena | Los Angeles County | SCAG | MTA | Vermont Ave just North of 133rd St. | Install a pedestrian crosswalk with a Pedestrian Hybrid Beacon (PHB) or High-Intensity Activated Crosswalk Beacon (HAWK) Crossing System. | 167800 | 167800 | 0 | 0 | 2022-07-14 | 0 | 167800 | No PE | Authorized | No | CON | Federal | 0
HSIP4-07-018 | 4 | 5276026 | 7 | Gardena | Los Angeles County | SCAG | MTA | Rosecrans Ave./Purche Ave. | Install traffic signals, curb ramps, and safety lighting; modify striping and pavement markings | 371418.53 | 313680.7 | 2011-08-02 | 0 | 2013-02-21 | 2014-10-29 | 313680.7 | Authorized | Authorized | No | Closed | Federal | 0
H10-07-010 | 10 | 5144076 | 7 | Glendale | Los Angeles County | SCAG | MTA | Pedestrian crossing flashing beacons will be installed at three intersections in the City: Wilson at Belmont, Lincoln at Colorado, and Colorado at Porter. Each intersection has a minimum of three recent vehicle/pedestrian collisions. | Installation of pedestrian crossing flashing beacons at three high collision intersections throughout the City. | 376900 | 249975 | 0 | 0 | 2022-04-26 | 0 | 249975 | No PE | Authorized | No | CON | State | 0
H11-07-012 | 11 | 5144082 | 7 | Glendale | Los Angeles County | SCAG | MTA | Chevy Chase Dr & San Fernando Rd, Central Ave & Los Feliz Rd, Colorado St & Glendale Ave, Broadway & Brand Blvd, Verdugo Rd & Broadview Dr, San Fernando Rd & Los Feliz Rd, Chevy Chase Dr & Glendale Ave, Foothill Blvd & New York Ave | Proposed project would provide protected left turn phases, raised median on approaches and modify signal phasing to implement a Leading Pedestrian Interval (LPI) at eight signalized intersections. | 1127700 | 1014930 | 0 | 0 | 0 | 0 | 0 | No PE | Past due (due 3/31/2026) | Yes (CON) | Not Started | State | 0
H11-07-013 | 11 | 5144083 | 7 | Glendale | Los Angeles County | SCAG | MTA | Various locations throughout the City of Glendale. | Install/upgrade signs with new fluorescent sheeting (regulatory or warning). | 4121200 | 3709080 | 2023-12-27 | 0 | 0 | 0 | 0 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE | State | 0
H11-07-014 | 11 | 5144084 | 7 | Glendale | Los Angeles County | SCAG | MTA | S Glendale Ave: E Los Feliz-E Broadway, Verdugo Rd: E Colorado-N Glendale, W Colorado St: S Pacific-S Columbus, Montrose Ave: Pennsylvania-La Crescenta, Lexington Dr: N Pacific-N Verdugo, Western Ave: W Glenoaks -S Victory | Proposed projects would install edge-lines, centerlines, rectangular rapid flashing beacons and install/ upgrade pedestrian crossings (with enhanced safety features) along six roadway segments. | 1514300 | 1362870 | 0 | 0 | 0 | 0 | 0 | No PE | Past due (due 3/31/2026) | Yes (CON) | Not Started | State | 0
H11-07-015 | 11 | 0 | 7 | Glendale | Los Angeles County | SCAG | MTA | Three roadway segments throughout city: (1) San Fernando Rd: W California Ave to Fierro St, (2) W Glenoaks Blvd: Thompson Ave to Concord St., and (3) Montrose Ave: Pennsylvania Ave to Ramsdell Ave. | Install dynamic/variable speed warning signs, and install/upgrade pedestrian crossing (with enhanced safety features). | 277700 | 249930 | 0 | 0 | 0 | 0 | 0 | No PE | Past due (due 3/31/2026) | Yes (CON) | Not Started | State | 0
H12-07-014 | 12 | 0 | 7 | Glendale | Los Angeles County | SCAG | MTA | 120 Signalized Intersections citywide. | Improve signal hardware; install pedestrian countdown signal heads; install APS; and implement leading pedestrian interval (LPI). | 9168700 | 8251830 | 0 | 0 | 0 | 0 | 0 | No PE | Due by 3/31/2028 | No | Not Started | Federal | 2
H12-07-015 | 12 | 0 | 7 | Glendale | Los Angeles County | SCAG | MTA | Four (4) Unsignalized Intersections: San Fernando Road and Palmer Avenue, Sonora Avenue and Randall Street, Verdugo Road and Glencoe Way, Glendale Avenue and Elk Avenue. | Install flashing beacons at stop controlled intersections; install rectangular rapid flashing beacons (RRFBs), and install Pedestrian Hybrid Beacons. | 1942400 | 1748160 | 0 | 0 | 0 | 0 | 0 | No PE | Due by 3/31/2028 | No | Not Started | Federal | 2
H12-07-016 | 12 | 0 | 7 | Glendale | Los Angeles County | SCAG | MTA | Various intersections and mid block crossings. | Upgrade 11 pedestrian crosswalks and 8 school crosswalks with improved crossing striping, stop bars, yield lines, curb ramps and detectable warning surfaces. | 388000 | 349200 | 0 | 0 | 0 | 0 | 0 | No PE | Due by 3/31/2028 | No | Not Started | State | 0
H9-07-006 | 9 | 5144073 | 7 | Glendale | Los Angeles County | SCAG | MTA | Four (4) non-signalized intersections throughout Glendale. | Install solar-powered Rectangular Rapid Flashing Beacons (RRFBs) with Bulldog pedestrian push buttons, thermoplastic high visibility crosswalk striping & street markings, and retroreflective signing. | 1115714.28 | 322887.71 | 0 | 0 | 2020-04-27 | 2022-03-22 | 322887.71 | No PE | Authorized | No | Closed | Federal | 0
H9-07-007 | 9 | 5144074 | 7 | Glendale | Los Angeles County | SCAG | MTA | Thirty-four (34) roadway segments throughout Glendale. | Upgrade damaged, substandard or missing guardrails. | 897692.04 | 732464.81 | 0 | 0 | 2020-03-12 | 2021-12-06 | 732464.81 | No PE | Authorized | No | Closed | Federal | 0
HSIP2-07-027 | 2 | 5144053 | 7 | Glendale | Los Angeles County | SCAG | MTA | Wilson Ave. / Harvey Dr. And Broadway | Upgrade Traffice Signal And Provide Let-Turn Phases. | 391211.37 | 324469.29 | 2010-12-13 | 0 | 2014-05-06 | 2016-04-25 | 324469.29 | Authorized | Authorized | No | Closed | Federal | 0
HSIP2-07-028 | 2 | 5144054 | 7 | Glendale | Los Angeles County | SCAG | MTA | Verdugo Rd. / Honolulu Ave. And Montrose Bld./Verdugo Bld. | Upgrade Traffic Signal To Include Left Turn Phases. | 791992.36 | 309165.77 | 2010-12-13 | 0 | 2013-11-27 | 2016-10-21 | 309165.77 | Authorized | Authorized | No | Closed | Federal | 0
H11-07-016 | 11 | 5204026 | 7 | Glendora | Los Angeles County | SCAG | MTA | 8 intersections: Gladstone & Barranca, Gladstone & Sunflower, Baseline & Grand, Route 66 & Barranca, Juanita & Sunflower, Gladstone & Valley Center, Lone Hill & Kenoma, and Route 66 & Hunters Trail | Provide protected left turn phases at 6 intersections; convert signals from pedestal-mounted to mast arms at 2 intersections; and add high-visibility crosswalks. | 1926200 | 1733580 | 0 | 0 | 2025-04-29 | 0 | 1733580 | No PE | Authorized | No | CON | State | 0
H12-07-017 | 12 | 0 | 7 | Glendora | Los Angeles County | SCAG | MTA | 10 intersections: Route 66 at Grand, Lone Hill, Pasadena, Loraine, Elwood, Glendora, Amelia, and Vermont; Grand Ave at Gladstone; and Glendora Ave at Baseline. | Convert signals from pedestal-mounted to mast arms at 8 intersections; and impove signal hardware at 2 intersections. | 2305100 | 2074590 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2025) | Due by 3/31/2028 | Yes (PE) | Not Started | Federal | 0
H9-07-008 | 9 | 5204023 | 7 | Glendora | Los Angeles County | SCAG | MTA | The vicinity of five (5) public and private elementary schools, including Cullen Elementary, Sellers Elementary, La Fetra Elementary, Hope Lutheran School, and Stanton Elementary. | Install curb extensions, high-visibility crosswalks, enhanced crosswalk signage and pavement markings, street lighting, flashing beacons at stop signs, pedestrian countdown signals, lead ped intervals, and no-passing centerlines. | 395308 | 250000 | 0 | 0 | 2022-06-01 | 2026-01-05 | 250000 | No PE | Authorized | No | Closed | Federal | 0
HSIP2-07-030 | 2 | 5204013 | 7 | Glendora | Los Angeles County | SCAG | MTA | Gladstone St. North Of Nearglen Ave. | Install In-Pavement Crosswalk Lights, Bulb-Outs, Street Light, And School Signs. | 81210 | 73089 | 0 | 0 | 2009-11-05 | 2011-11-17 | 73089 | No PE | Authorized | No | Closed | Federal | 0
HSIP3-07-028 | 3 | 5204015 | 7 | Glendora | Los Angeles County | SCAG | MTA | Glendora Ave. And Gladstone St. | Install Protected Left-Turn Phasing | 139778.63 | 125800.76 | 0 | 0 | 2011-09-20 | 2013-04-11 | 125800.76 | No PE | Authorized | No | Closed | Federal | 0
HSIP4-07-039 | 4 | 5204016 | 7 | Glendora | Los Angeles County | SCAG | MTA | Amelia Ave./SR 66 | Install protected left-turn phasing | 71348 | 64213.2 | 0 | 0 | 2012-08-10 | 2013-10-22 | 64213.2 | No PE | Authorized | No | Closed | Federal | 0
HSIP5-07-015 | 5 | 5204020 | 7 | Glendora | Los Angeles County | SCAG | MTA | Foothill Blvd./Barranca Ave. | Install protected left-turn phasing | 242849.44 | 147911 | 0 | 0 | 2017-05-22 | 2020-03-17 | 147911 | No PE | Authorized | No | Closed | Federal | 0
H12-07-018 | 12 | 5387016 | 7 | Hawaiian Gardens | Los Angeles County | SCAG | MTA | Norwalk Blvd at 216th St. | Install a HAWK signal on Norwalk Blvd at 216th St and remove the two adjacent crosswalks on Norwalk Blvd at 215th St and Tilbury St. | 388900 | 350000 | 0 | 0 | 2025-04-29 | 0 | 350000 | No PE | Authorized | No | CON | State | 0
H8-07-009 | 8 | 5387012 | 7 | Hawaiian Gardens | Los Angeles County | SCAG | MTA | Various signalized intersections along Carson St. between Western City Limit (Pioneer Blvd) and Eastern City Limit (Bloomfield Ave). | Install traffic signal hardware improvements. | 805778 | 700000 | 0 | 0 | 2022-03-07 | 2025-12-18 | 700000 | No PE | Authorized | No | Closed | Federal | 0
H8-07-010 | 8 | 5387013 | 7 | Hawaiian Gardens | Los Angeles County | SCAG | MTA | Various intersections on Norwalk Blvd between 214th St and 226th St. | Install traffic signal improvements. | 516000 | 464399.5 | 0 | 0 | 2022-03-07 | 2026-01-05 | 464399.5 | No PE | Authorized | No | Closed | Federal | 0
HSIP1-07-008 | 1 | 5253016 | 7 | Hawthorne | Los Angeles County | SCAG | MTA | On Rosecrans Ave From Inglewood Ave To 250' West Of I-405 Sb Off-Ramp. | Upgrade And Construct Raised Median; Improve Existing Shoulders; Upgrade Pavement Markings And Delineation. | 2781550.86 | 762584.35 | 2010-02-12 | 0 | 2011-07-21 | 2013-05-15 | 762584.35 | Authorized | Authorized | No | Closed | Federal | 0
HSIP2-07-031 | 2 | 5253017 | 7 | Hawthorne | Los Angeles County | SCAG | MTA | Five Intersections: El Segundo Blvd. And Doty Ave., El Segundo Blvd. And Yukon Ave., 120Th St. And Wilkie Ave., Van Ness Ave. And 116Th St., 135Th St. And Doty Ave. | Upgrade Traffic Signals | 1268874.38 | 880500 | 2010-02-17 | 0 | 2011-06-08 | 2013-03-26 | 880500 | Authorized | Authorized | No | Closed | Federal | 0
HSIP4-07-027 | 4 | 5253019 | 7 | Hawthorne | Los Angeles County | SCAG | MTA | Inglewood Ave. between Imperial Hwy. and El Segundo Blvd. | Upgrade traffic signals and safety lighting | 868167.77 | 729999.99 | 2012-07-20 | 0 | 2015-06-18 | 2017-03-23 | 729999.99 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-07-016 | 5 | 5253020 | 7 | Hawthorne | Los Angeles County | SCAG | MTA | Prairie Ave. between 118th St. and Marine Ave. | Upgrade traffic signals; install safety lighting | 1014945 | 885500 | 2013-09-18 | 0 | 2017-11-15 | 2021-06-25 | 885500 | Authorized | Authorized | No | Closed | Federal | 0
HSIP7-07-010 | 7 | 5253021 | 7 | Hawthorne | Los Angeles County | SCAG | MTA | 1.3 mile section of 120th Street from Prairie Avenue to Felton Avenue | Traffic signal upgrades (upgrade signals, controllers and detection) and coordination at eight signalized intersections and improve crossings and signage at spot locations in the corridor | 4143966.3 | 1305800 | 0 | 0 | 2022-06-01 | 2025-04-17 | 1305800 | No PE | Authorized | No | Closed | Federal
HSIP3-07-029 | 3 | 5155010 | 7 | Hermosa Beach | Los Angeles County | SCAG | MTA | Intersection Of Valley Dr. And The Driveway For Valley School (A T-Intersection) | Upgrade Pedestrian Traffic Signal To Full Traffic Signal; Install Pedestrian Countdown Signals, Safety Lighting And Advance Warning Signs; Construct Sidewalks | 147207.3 | 96112.09 | 0 | 0 | 2011-08-23 | 2013-06-25 | 96112.09 | No PE | Authorized | No | Closed | Federal | 0
H8-07-011 | 8 | 5164033 | 7 | Inglewood | Los Angeles County | SCAG | MTA | Centinela Ave between La Cienega Blvd and La Brea Ave. | Construct raised center medians and install traffic signal improvements including protected left turn phasing at the intersections of Centinela at Beach, Centinela at Eucalyptus, and Centinela at La Brea. | 7520596 | 1096755.02 | 0 | 0 | 2020-09-11 | 2024-03-28 | 1096755.02 | No PE | Authorized | No | Closed | Federal | 0
H8-07-012 | 8 | 5164031 | 7 | Inglewood | Los Angeles County | SCAG | MTA | La Brea Avenue between 64th Street and Beach Avenue. | Install traffic signal improvements. | 98815.87 | 81158.01 | 0 | 0 | 2020-03-04 | 2023-12-18 | 81158.01 | No PE | Authorized | No | Closed | Federal | 0
H8-07-013 | 8 | 5164032 | 7 | Inglewood | Los Angeles County | SCAG | MTA | Prairie Avenue between Grace Avenue and 111th Street. | Install traffic signal improvements. | 875400 | 875400 | 0 | 0 | 2020-03-05 | 2023-11-09 | 875400 | No PE | Authorized | No | Closed | Federal | 0
H8-07-014 | 8 | 5164030 | 7 | Inglewood | Los Angeles County | SCAG | MTA | Various signalized intersections throughout the City of Inglewood. | Install pedestrian countdown signal heads. | 31011.8 | 27269.6 | 0 | 0 | 2019-09-13 | 2021-10-21 | 27269.6 | No PE | Authorized | No | Closed | Federal | 0
H9-07-009 | 9 | 5164035 | 7 | Inglewood | Los Angeles County | SCAG | MTA | Various uncontrolled crosswalks throughout the City of Inglewood, including Centinela Ave at Market St, Manchester Blvd at Cedar Ave, on Regent St between Grevillea Ave and La Brea Avenue, two midblock crosswalks on Market St between Regent St and Manchester Blvd. | Install high visibility crosswalk enhancements including pedestrian signals, signing and striping, and Rectangular Rapid Flashing Beacons (RRFBs). | 1119843.84 | 250000 | 0 | 0 | 2022-06-07 | 2025-05-14 | 250000 | No PE | Authorized | No | Closed | Federal | 0
HSIP3-07-010 | 3 | 5164025 | 7 | Inglewood | Los Angeles County | SCAG | MTA | Crenshaw Blvd. At 84Th Place East & 84Th Place West, Including The Intersection With South 8Th Ave. | Extend And Improve Raised Median For Sb Crenshaw; Modify Signal Operations; Install Right-Turn Lane, Signs, Pavement Markings And Speed Feedback Signs | 290688.55 | 245696.9 | 2011-03-03 | 0 | 2014-09-15 | 2019-06-19 | 245696.9 | Authorized | Authorized | No | Closed | Federal | 0
HSIP4-07-002 | 4 | 5164027 | 7 | Inglewood | Los Angeles County | SCAG | MTA | Various locations throughout the city | Upgrade signs | 194462.32 | 175016.08 | 2011-09-20 | 0 | 2013-09-18 | 2018-05-01 | 175016.08 | Authorized | Authorized | No | Closed | Federal | 0
HSIP1-07-012 | 1 | 5345004 | 7 | Irwindale | Los Angeles County | SCAG | MTA | Arrow Highway At The Santa Fe Dam. | Install Mid-Block Bike/Pedestrian Crossing With In-Roadway Warning Lights And Advance Warning Flashing Yellow Beacons. | 121558 | 109402.16 | 2008-09-17 | 0 | 2011-06-08 | 2013-10-15 | 109402.16 | Authorized | Authorized | No | Closed | Federal | 0
H10-07-011 | 10 | 5417025 | 7 | La Canada Flintridge | Los Angeles County | SCAG | MTA | 6 intersections total; 5 along Foothill Blvd: Lasheart Dr, La Canada Plaza Rd, Castle Rd, Ocean View Blvd and Union St; and 1 along Verdugo Blvd at La Tour Wy | Installation of pedestrian crossing enhancements including pedestrian signals and pedestrian push-buttons. Additionally upgrade the uncontrolled crosswalk on Foothill Blvd at Union St with overhead flashing beacons, bulb-outs and ADA curb ramps | 471100 | 250000 | 2021-11-19 | 0 | 2023-04-21 | 0 | 250000 | Authorized | Authorized | No | CON | State | 0
H12-07-019 | 12 | 5417029 | 7 | La Canada Flintridge | Los Angeles County | SCAG | MTA | Foothill Boulevard at Indiana Avenue. | Install a HAWK signal. | 389200 | 350000 | 2025-12-04 | 0 | 0 | 0 | 36900 | Authorized | Due by 3/31/2028 | No | PE | State | 0
H9-07-010 | 9 | 5417023 | 7 | La Canada Flintridge | Los Angeles County | SCAG | MTA | Various intersections along Foothill Blvd (Hillard Ave, Palm Dr, Gould Ave, Commonwealth Ave, and Hampton Rd). | Improve signal hardware, install pedestrian countdown heads, and add left turn phasing to two intersections (Hillard Ave and Foothill Blvd). | 462025.76 | 458697.82 | 2020-03-09 | 0 | 2021-12-22 | 2026-02-06 | 458697.82 | Authorized | Authorized | No | Closed | Federal | 0
H10-07-012 | 10 | 5422003 | 7 | La Habra Heights | Los Angeles County | SCAG | MTA | Various Locations Throughout the City | Replace damaged guardrail as well as those not meeting standards, and installation of new guardrails as needed to improve safety. | 880000 | 880000 | 2021-12-13 | 0 | 0 | 0 | 80000 | Authorized | Past due (due 9/30/2024) | Yes (CON) | PE | State | -1
H10-07-013 | 10 | 5422004 | 7 | La Habra Heights | Los Angeles County | SCAG | MTA | Hacienda Road within the City of La Habra Heights | Safety improvements along Hacienda road including signalization of Hacienda Road and Avocado Crest Road intersection, upgrading signage and striping on Hacienda Road including the installation of edge lines. | 1144612 | 1144612 | 2021-12-13 | 0 | 2024-02-05 | 0 | 1144612 | Authorized | Authorized | No | CON | State | -1
HSIP5-07-017 | 5 | 5364010 | 7 | La Mirada | Los Angeles County | SCAG | MTA | Valley View Ave./Adoree St. | Install traffic signal | 436978.84 | 393040.62 | 2013-11-13 | 0 | 2015-08-20 | 2018-03-14 | 393040.62 | Authorized | Authorized | No | Closed | Federal | 0
H8-07-015 | 8 | 5331021 | 7 | La Puente | Los Angeles County | SCAG | MTA | Eight (8) crosswalk locations throughout the City of La Puente. | Install Rectangular Rapid Flashing Beacons (RRFBs), curb extensions, advanced pavement markings, warning signs, and high visibility crosswalks. | 964695 | 783600 | 0 | 0 | 2022-06-14 | 2024-11-07 | 783600 | No PE | Authorized | No | Closed | Federal | 0
HSIP2-07-036 | 2 | 5331010 | 7 | La Puente | Los Angeles County | SCAG | MTA | Temple Ave. And Orange Ave.; Valley Blvd. And Ferrero Lane; Temple Ave. And Sunset Ave. | Upgrade Traffic Signal To Include Left-Turn Phasing; Install Protected-Permissive Left-Turn Phasing | 393248.87 | 296910 | 2009-12-04 | 0 | 2011-11-04 | 2014-01-14 | 296910 | Authorized | Authorized | No | Closed | Federal | 0
HSIP3-07-015 | 3 | 5331017 | 7 | La Puente | Los Angeles County | SCAG | MTA | Intersection Of Amar Rd. And Tonopah Ave. | Install School Crossing Signals For Nb And Sb Pedestrian Crossings | 229502.72 | 200790 | 2010-09-23 | 0 | 2011-11-04 | 2014-02-24 | 200790 | Authorized | Authorized | No | Closed | Federal | 0
HSIP6-07-010 | 6 | 5331020 | 7 | La Puente | Los Angeles County | SCAG | MTA | On Amar Rd between N Puente Ave and N Hacienda Blvd | Install traffic signals and pedestrian countdown heads | 976278.77 | 836023.07 | 2014-12-30 | 0 | 2017-01-07 | 2019-01-22 | 836023.07 | Authorized | Authorized | No | Closed | Federal | 0
H8-07-016 | 8 | 5149022 | 7 | La Verne | Los Angeles County | SCAG | MTA | Fruit Street between Baseline Road and Foothill Boulevard. | Install protected left turn phase improvements at Baseline Road, and install raised medians along Fruit Street from south of Interstate 210 Freeway to north of Foothill Boulevard. | 543131.84 | 239794.88 | 0 | 0 | 2020-07-15 | 2022-11-22 | 239794.88 | No PE | Authorized | No | Closed | Federal | 0
H8-07-017 | 8 | 5149021 | 7 | La Verne | Los Angeles County | SCAG | MTA | Intersection of Durward Way at White Avenue. | Install signals, lighting and raised medians. | 368352.86 | 252000 | 0 | 0 | 2020-01-29 | 2023-05-02 | 252000 | No PE | Authorized | No | Closed | Federal | 0
HSIP2-07-029 | 2 | 5149008 | 7 | La Verne | Los Angeles County | SCAG | MTA | Streets Surrounding Roynon Elementary School | Install Solar Powered Speed Feedback Signs | 220272 | 191565 | 0 | 0 | 2010-09-02 | 2012-02-22 | 191565 | No PE | Authorized | No | Closed | Federal | 0
HSIP6-07-011 | 6 | 5149017 | 7 | La Verne | Los Angeles County | SCAG | MTA | Bonita Ave/White Ave and Bonita Ave/B St | Install traffic signals and pedestrian countdown heads | 354853.52 | 354853.52 | 0 | 0 | 2016-01-19 | 2018-06-28 | 354853.52 | No PE | Authorized | No | Closed | Federal | 0
H10-07-014 | 10 | 5315015 | 7 | Lakewood | Los Angeles County | SCAG | MTA | 19 intersections: Del Amo/Downey, Del Amo/Graywood, Del Amo/Clark, Del Amo/Palo Verde, Paramount/Candlewood, Paramount/Cover, Centralia/Pioneer, Centralia/Norwalk, Centralia/Claretta, Centralia/Bloomfield, Paramount/Del Amo, Paramount/Carson, Candlewood/Bellflower, Del Amo/Bloomfield, Del Amo/Bellflower, Carson/Nectar, Candlewood/Clark, Hedda/Clark and Cark/Ashworth. | Provide advanced dilemma zone detection at 12 intersections, upgrade and improve signal hardware at 17 intersections and upgrade pedestal mounted median signals with mast arms at 2 intersections. | 2243900 | 2243900 | 2021-11-01 | 0 | 2023-11-09 | 0 | 2243900 | Authorized | Authorized | No | CON | State | 0
HSIP2-07-034 | 2 | 5315009 | 7 | Lakewood | Los Angeles County | SCAG | MTA | Various Intersections | Construct Left-Turn Lanes; Install Protected Permissive Left-Turn Phasing | 626236.14 | 479070 | 0 | 0 | 2010-01-13 | 2012-07-10 | 479070 | No PE | Authorized | No | Closed | Federal | 0
H10-07-015 | 10 | 5419061 | 7 | Lancaster | Los Angeles County | SCAG | MTA | 28 signalized intersections within the city limits of Lancaster. | Systemically upgrade vehicle detection to include advanced dilemma-zone detection, bike recognition and detection, as well as upgrading existing signal equipment. | 2908000 | 2908000 | 2021-11-30 | 0 | 0 | 0 | 335600 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE | State | 0
H10-07-016 | 10 | 5419058 | 7 | Lancaster | Los Angeles County | SCAG | MTA | 7 commercial driveways in the City of Lancaster. | Create directional median openings to restrict left-turns and u-turns. | 339500 | 305550 | 2021-11-01 | 0 | 2024-03-14 | 0 | 305550 | Authorized | Authorized | No | CON | State | 0
H10-07-017 | 10 | 5419059 | 7 | Lancaster | Los Angeles County | SCAG | MTA | Five (5) intersections: Avenue K-8 & Challenger Way, Valley Central Way & Central Court, Valley Central Way & Commercial Driveways (550 ft South of Lancaster Blvd), Avenue J & 25th Street East, and Avenue K & 25th Street East. | Install low-cost, quick build roundabouts. | 2129200 | 2129200 | 2021-11-01 | 0 | 0 | 0 | 280000 | Authorized | Past due (due 9/30/2024) | Yes (CON) | PE | State | 0
H10-07-018 | 10 | 5419064 | 7 | Lancaster | Los Angeles County | SCAG | MTA | 53 signalized intersections within the city limits of Lancaster. | Upgrade existing crosswalks to high-visibility continental-style crosswalks using thermoplastic material. | 646900 | 250000 | 0 | 0 | 2023-05-25 | 0 | 250000 | No PE | Authorized | No | CON | State | 0
H10-07-019 | 10 | 5419065 | 7 | Lancaster | Los Angeles County | SCAG | MTA | Ave I, 37th St E to 40th St E; Ave J, 32nd St E to 50th St E; Ave J, 50th St E to 85th St E; Ave K, 35th St E to 107th St E; 60th St W, Ave J to Ave E; Ave G, 70th St W to 50th St W; 40th St E, Lanc Blvd to Ave K-8; 80th St W, Ave K to Ave L; Ave F, 70 St W to 60th St W | Upgrade and refresh 48 miles of roadway edgelines with thermoplastic material. | 337300 | 250000 | 0 | 0 | 2023-05-30 | 0 | 250000 | No PE | Authorized | No | CON | State | 0
H10-07-020 | 10 | 5419060 | 7 | Lancaster | Los Angeles County | SCAG | MTA | 4 locations within Lancaster: 50th Street West and Avenue I; 60th Street West and Avenue I; Sierra Highway and Avenue L; and Sierra Highway and Avenue H. | Replace approx. 1,100 feet of existing damaged guardrail with new guardrail. | 226900 | 226900 | 2021-11-01 | 0 | 2023-07-13 | 0 | 226900 | Authorized | Authorized | No | CON | State | 0
H11-07-017 | 11 | 5419069 | 7 | Lancaster | Los Angeles County | SCAG | MTA | 101 signalized intersections in the City of Lancaster. | Upgrade all traffic signals at intersections to include reflective backplates. | 1515000 | 1363500 | 2023-11-21 | 0 | 0 | 0 | 163620 | Authorized | Due by 3/31/2027 | No | PE | State | 0
H11-07-018 | 11 | 5419067 | 7 | Lancaster | Los Angeles County | SCAG | MTA | 223 unsignalized intersections in the City of Lancaster. | Enhance visibility of stop signs, pavement markings, and advanced warning beacons at stop-controlled intersections. | 1878500 | 1690650 | 2023-08-16 | 0 | 0 | 0 | 202950 | Authorized | Due by 3/31/2027 | No | PE | State | -1
H11-07-019 | 11 | 5419070 | 7 | Lancaster | Los Angeles County | SCAG | MTA | 66 unsignalized intersections in the City of Lancaster. | Install additional intersection lighting at unsignalized intersections. | 2610000 | 2349000 | 2023-11-21 | 0 | 0 | 0 | 281880 | Authorized | Due by 3/31/2027 | No | PE | State | 0
H11-07-020 | 11 | 5419071 | 7 | Lancaster | Los Angeles County | SCAG | MTA | 10th St W/Avenue H-6, 17th St E/Avenue I, and 10th St W/Avenue H-12. | Install/upgrade rectangular rapid flashing beacons (RRFBs) at unsignalized intersections. | 419400 | 377460 | 2023-11-21 | 0 | 0 | 0 | 45360 | Authorized | Due by 3/31/2027 | No | PE | State | 0
H8-07-019 | 8 | 5419056 | 7 | Lancaster | Los Angeles County | SCAG | MTA | Intersection of Avenue I at 60th Street West. | Modify the existing traffic signal to provide east/west protected left turn phasing, and install advance "Signal Ahead" signs and flashing beacons. | 201600.22 | 201600.22 | 0 | 0 | 2020-01-15 | 2022-10-26 | 201600.22 | No PE | Authorized | No | Closed | Federal | 0
HSIP2-07-042 | 2 | 5419025 | 7 | Lancaster | Los Angeles County | SCAG | MTA | Ave. I And 40Th St. West | Construct Left-Turn Lane | 258973.69 | 233076.32 | 2009-09-01 | 0 | 2012-08-30 | 2014-02-24 | 233076.32 | Authorized | Authorized | No | Closed | Federal | 0
HSIP2-07-043 | 2 | 5419026 | 7 | Lancaster | Los Angeles County | SCAG | MTA | Five Intersectiosn: Ave. J-8 And 15Th St. West; Ave. L And 20Th St. West; Ave. J And 15Th St. East; Ave. J And 5Th St. East; Ave. I And 5Th St. East | Upgrade Traffic Signals | 461378.04 | 415240.24 | 0 | 0 | 2010-09-14 | 2012-12-20 | 415240.24 | No PE | Authorized | No | Closed | Federal | 0
HSIP3-07-030 | 3 | 5419032 | 7 | Lancaster | Los Angeles County | SCAG | MTA | Ave. "J" Between Challenger Way (10Th St. East) And 20Th St. East | Construct Raised Medians | 579024.07 | 248838.29 | 0 | 0 | 2012-10-26 | 2015-03-26 | 248838.29 | No PE | Authorized | No | Closed | Federal | 0
HSIP3-07-031 | 3 | 5419029 | 7 | Lancaster | Los Angeles County | SCAG | MTA | Citywide (Twenty-One Neighborhood Street Segments) | Install Speed Humps, Signs, And Stripes; Reduce Lane Widths To Add Bike Lanes | 333936.2 | 300542.57 | 0 | 0 | 2012-04-18 | 2014-11-18 | 300542.57 | No PE | Authorized | No | Closed | Federal | 0
HSIP4-07-005 | 4 | 5419035 | 7 | Lancaster | Los Angeles County | SCAG | MTA | Various locations throughout the city | Upgrade signs, striping, and pavement markings | 338139.59 | 285689.54 | 2012-01-11 | 0 | 2014-04-15 | 2016-10-21 | 285689.54 | Authorized | Authorized | No | Closed | Federal | 0
HSIP4-07-017 | 4 | 5419033 | 7 | Lancaster | Los Angeles County | SCAG | MTA | Ave. "L"/Challenger Way (10th St. East) | Convert traffic signal to roundabout | 1466576.17 | 690300 | 2011-10-25 | 0 | 2015-03-18 | 2018-03-23 | 690300 | Authorized | Authorized | No | Closed | Federal | 0
HSIP4-07-048 | 4 | 5419040 | 7 | Lancaster | Los Angeles County | SCAG | MTA | Various locations throughout the city | Install solar-powered LED Stop signs | 350941.31 | 284336.1 | 0 | 0 | 2014-04-29 | 2016-10-24 | 284336.1 | No PE | Authorized | No | Closed | Federal | 0
HSIP5-07-018 | 5 | 5419041 | 7 | Lancaster | Los Angeles County | SCAG | MTA | Ave. I/10th St. West; Ave. K/30th St. West | Modify traffic signals; upgrade crosswalks; install pedestrian countdown heads, pedestrian refuge islands, bulb-outs, and curb ramps | 1898305.73 | 213462.05 | 2013-07-11 | 0 | 2017-08-11 | 2021-11-23 | 213462.05 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-07-019 | 5 | 5419042 | 7 | Lancaster | Los Angeles County | SCAG | MTA | 15th Street East/Lancaster Blvd., and its four approach legs up to Kettering St., 20th St. East, Ave. J, and Challenger Way | Construct roundabout, bulb-outs; install " road diet" (reduce traffic lanes from 4 to 2) | 1390035 | 882800 | 2013-07-29 | 0 | 2018-01-05 | 2021-03-29 | 882800 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-07-020 | 5 | 5419043 | 7 | Lancaster | Los Angeles County | SCAG | MTA | 15th Street West between Jenner St. and Avenue J | Install roundabout and "road diet" (reduce traffic lanes from 4 to 2); construct bulb-outs and pedestrian refuge islands | 1564084 | 897800 | 2013-07-29 | 0 | 2018-04-30 | 2021-03-18 | 897800 | Authorized | Authorized | No | Closed | Federal | 0
HSIP6-07-012 | 6 | 5419047 | 7 | Lancaster | Los Angeles County | SCAG | MTA | On E Avenue I between Challenger Way and Price Lane | Install sidewalks and bike lanes, curb ramps, curb extension, and crosswalks; Upgrade signals | 1160636.6 | 792320.81 | 2015-05-26 | 0 | 2019-07-31 | 2022-02-08 | 792320.81 | Authorized | Authorized | No | Closed | Federal | 0
HSIP6-07-013 | 6 | 5419048 | 7 | Lancaster | Los Angeles County | SCAG | MTA | On E Avenue I between Price Lane and 35th St East | Install sidewalks and bike lanes, curb ramps, curb extension, and crosswalks; Upgrade signals | 1029639.58 | 765076.06 | 2015-05-26 | 0 | 2019-11-08 | 2022-11-05 | 765076.06 | Authorized | Authorized | No | Closed | Federal | 0
HSIP7-07-012 | 7 | 5419053 | 7 | Lancaster | Los Angeles County | SCAG | MTA | 10th Street West from Lancaster Boulevard to Avenue J, Avenue J from 10th Street West to Challenger Way | Construct sidewalk, curb and gutter and curb ramps, install new striping to accommodate new bike lanes and some on-street parking. Construct mid-block crossings and median refuge islands. | 3120908.94 | 2653345.82 | 2018-08-08 | 0 | 2020-11-30 | 2023-06-21 | 2653345.82 | Authorized | Authorized | No | Closed | Federal
HSIP1-07-013 | 1 | 5360006 | 7 | Lawndale | Los Angeles County | SCAG | MTA | Intersection Of Marine Avenue And Mansel Avenue. | Install Traffic Signal; Construct Left Turn Lanes; Enhance Pavement Markings. | 139310.7 | 125379.63 | 0 | 0 | 2009-03-26 | 2012-01-25 | 125379.63 | No PE | Authorized | No | Closed | Federal | 0
HSIP4-07-014 | 4 | 5360012 | 7 | Lawndale | Los Angeles County | SCAG | MTA | Manhattan Beach Blvd./Firmona Ave. | Modify traffic signals; upgrade curb ramps; install signs and pavement markings | 160990.16 | 144891.13 | 0 | 0 | 2013-04-19 | 2015-01-20 | 144891.13 | No PE | Authorized | No | Closed | Federal | 0
H10-07-021 | 10 | 5108203 | 7 | Long Beach | Los Angeles County | SCAG | MTA | 6 Intersections: South St & Downey Ave, Carson St & Orange Ave, Cherry Ave & Bixby Rd, Bellflower Blvd & Wardlow Rd, Willow Rd & Magnolia Ave, and Willow St & Easy Ave. | Provide protected left turn phase. | 927500 | 927500 | 2021-12-06 | 2025-06-12 | 2025-06-12 | 0 | 805500 | Authorized | Authorized | No | CON | State | 0
H11-07-021 | 11 | 5108209 | 7 | Long Beach | Los Angeles County | SCAG | MTA | 2 Intersections: Atlantic Ave & Atlantic Pl; and Pacific Ave & Burnett St. | Install new traffic signals. | 1107900 | 997110 | 2023-08-17 | 0 | 0 | 0 | 76500 | Authorized | Due by 6/30/2027 | No | PE | State | 0
H11-07-022 | 11 | 5108211 | 7 | Long Beach | Los Angeles County | SCAG | MTA | Approximately 140 signalized intersections throughout the City. | Install new signal back plates, retro-reflective tape, LED safety lighting, 12” signals heads, EVPs, and ped countdown heads. | 4679500 | 4211550 | 2025-07-17 | 0 | 0 | 0 | 94500 | Authorized | Due by 12/29/2027 | No | PE | Federal | 2
H11-07-023 | 11 | 5108212 | 7 | Long Beach | Los Angeles County | SCAG | MTA | 7th Street between I-710 and Park Avenue. | Install pedestrian refuge medians and restrict left turns at minor street crossings along the 7th Street Corridor. | 4502600 | 3151820 | 2025-07-17 | 0 | 0 | 0 | 563500 | Authorized | Due by 7/31/2028 | No | PE | Federal | 2
H11-07-024 | 11 | 0 | 7 | Long Beach | Los Angeles County | SCAG | MTA | 168 intersections near schools, Citywide. | Mark high-contrast thermoplastic continental crosswalks in place of faded or outdated parallel bar crosswalks. | 250000 | 225000 | 0 | 0 | 0 | 0 | 0 | No PE | Due by 12/31/2027 | No | Not Started | State | 0
H12-07-020 | 12 | 5108240 | 7 | Long Beach | Los Angeles County | SCAG | MTA | Various locations throughout the City of Long Beach. | Install/upgrade signs with new fluorescent sheeting. | 10796700 | 9717030 | 2025-11-14 | 0 | 0 | 0 | 270000 | Authorized | Due by 3/31/2028 | No | PE | Federal | 0
H12-07-021 | 12 | 0 | 7 | Long Beach | Los Angeles County | SCAG | MTA | Eight intersections in underserved areas of Long Beach. | Mark high-contrast thermoplastic continental crosswalks in place of faded or outdated parallel bar crosswalks. | 234000 | 210600 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2025) | Due by 3/31/2028 | Yes (PE) | Not Started | State | 0
H8-07-020 | 8 | 5108178 | 7 | Long Beach | Los Angeles County | SCAG | MTA | Various locations on Anaheim Street between the Los Angeles River and Pacific Coast Highway. | Install controlled-access medians, signal upgrades, and pedestrian refuges. | 3326300 | 2993670 | 2018-12-19 | 0 | 2023-01-10 | 0 | 2993670 | Authorized | Authorized | No | CON | Federal | 2
H8-07-021 | 8 | 5108190 | 7 | Long Beach | Los Angeles County | SCAG | MTA | Ten (10) signalized intersections on Los Coyotes Diagonal from Outer Traffic Circle to Carson Street. | Install new traffic signal poles, indications and related equipment to accommodate the protected left turn phasing. | 1470698.14 | 1320703.88 | 2018-12-04 | 0 | 2020-12-18 | 2025-01-22 | 1320703.88 | Authorized | Authorized | No | Closed | Federal | 0
H8-07-022 | 8 | 5108188 | 7 | Long Beach | Los Angeles County | SCAG | MTA | Eighteen (18) uncontrolled intersections. | Install enhanced pedestrian crossings, including high visibility crosswalks along with yield triangles, new pedestrian signs and solar powered warning flashers. | 18150.24 | 18150.24 | 2018-11-06 | 0 | 0 | 2025-10-16 | 18150.24 | Authorized | No CON | No | Closed | Federal | 0
HSIP4-07-035 | 4 | 5108151 | 7 | Long Beach | Los Angeles County | SCAG | MTA | Martin Luther King Jr. Ave. between Seventh St. and Sixth St.; Alamitos Ave./Seventh St. | Eliminate road segment; install channelizing island, construct curb extensions and curb ramps; install high visibility crosswalks; improve pedestrian signal timing; install protected left-turn lanes; and remove signals | 1961328 | 899970 | 0 | 0 | 2014-05-06 | 2018-05-01 | 899970 | No PE | Authorized | No | Closed | Federal | 0
H10-07-022 | 10 | 5006926 | 7 | Los Angeles | Los Angeles County | SCAG | MTA | Various locations througout the City of Los Angeles. | Upgrade existing obsolete guardrail with metal beam guardrail compliant with current standards and Method for Assessing Safety Hardware (MASH). | 1000000 | 1000000 | 2021-12-24 | 0 | 2024-11-01 | 0 | 1000000 | Authorized | Authorized | No | CON | State | 0
H10-07-023 | 10 | 5006928 | 7 | Los Angeles | Los Angeles County | SCAG | MTA | 200 locations across the City. | Upgrade backplates to retroreflective. | 1884000 | 1884000 | 2022-01-04 | 0 | 2025-02-19 | 0 | 2165602.22 | Authorized | Authorized | No | CON | State | 0
H11-07-054 | 11 | 0 | 7 | Los Angeles | Los Angeles County | SCAG | MTA | 7 Uncontrolled Crossing Locations on Figueroa Street between 56th Street and 106th St. | Systemic approach to increase traffic safety, combination of Curb Extensions, Pedestrian Signals and Pedestrian Hybrid Beacons at uncontrolled pedestrian crossing locations and visibility improvements at signalized intersections. | 2648700 | 2383830 | 0 | 0 | 0 | 0 | 0 | No PE | Due by 12/31/2026 | No | Not Started | State | 0
H8-07-023 | 8 | 5006867 | 7 | Los Angeles | Los Angeles County | SCAG | MTA | 10 locations within the City of Los Angeles: 42nd Pl/Central Ave, Parthenia St/Willis Ave, SunnyslopeAve/Vanowen St, Olympic Blvd/Serrano Ave, 84th St/84th Pl/Figueroa St, and more. | Install new traffic signals at existing partially stop controlled intersections at 10 locations within the City of Los Angeles. | 5284000 | 4755600 | 2017-08-21 | 0 | 2022-04-26 | 0 | 4755600 | Authorized | Authorized | No | CON | Federal | 0
H8-07-024 | 8 | 5006868 | 7 | Los Angeles | Los Angeles County | SCAG | MTA | Twenty (20) intersections: Lindley Av/Sherman Wy, Compton Av/Imperial Hwy, Foothill Bl/Osborne St, Lassen St/Sepulveda Bl, Florence Av/Van Ness Av, Balboa Bl/Parthenia St, Tampa Av/Victory Bl, Union Av/Washington Bl, and the other twelve (12) intersections. | Modify traffic signals to install protected phasing operations (19 locations for left-turn and 1 for pedestrian scramble); upgrade signal indication sizes, install APS devices, and install/upgrade curb ramps. | 9927111 | 5244400 | 2017-09-13 | 0 | 2023-05-15 | 0 | 5244400 | Authorized | Authorized | No | CON | Federal | 2
H9-07-011 | 9 | 5006889 | 7 | Los Angeles | Los Angeles County | SCAG | MTA | Various locations throughout the City of Los Angeles. | Upgrade existing obsolete guardrail to modern metal beam guardrail. | 698964.76 | 698964.76 | 2019-09-13 | 0 | 2022-02-03 | 2024-05-31 | 698964.76 | Authorized | Authorized | No | Closed | Federal | 0
HSIP1-07-001 | 1 | 5006529 | 7 | Los Angeles | Los Angeles County | SCAG | MTA | Throughout 113 Miles Of Designated Bikeways Within The City Of Los Angeles. | Upgrade Existing Roadway Grates To Bicycle Safety Grates. | 432000.26 | 388800.22 | 2008-01-03 | 0 | 2008-05-22 | 2012-03-20 | 388800.22 | Authorized | Authorized | No | Closed | Federal | 0
HSIP1-07-002 | 1 | 5006532 | 7 | Los Angeles | Los Angeles County | SCAG | MTA | Camarillo St, Riverside Dr. And Tujunga Ave; Victory Blvd At Woodman Ave.; Hazeltine Ave At Sherman Way, Van Nuys Blvd. At Victory Blvd, Martin Luther King Blvd At Normandie Ave. And Parthenia St. At Tampa Ave. | Upgrade Traffic Signals; Install Protected And/Or Protected-Permissive Left Turn Signal Phasing; Install Curb Ramps. | 888047.07 | 583462.81 | 2008-04-10 | 0 | 2010-11-11 | 2019-01-18 | 583462.81 | Authorized | Authorized | No | Closed | Federal | 0
HSIP1-07-005 | 1 | 5006533 | 7 | Los Angeles | Los Angeles County | SCAG | MTA | Woodley Avenue/ Raymer Street And De Soto Street/ Knapp Street At Metro Link'S Highway-Rail Grade Crossings. | Upgrade Traffic Signal Equipment, Roadway Medians And Other Traffic Control Devices; Railroad Preemption | 1017132.53 | 735792.89 | 2008-04-10 | 0 | 2012-09-12 | 2019-11-08 | 735792.89 | Authorized | Authorized | No | Closed | Federal | 0
HSIP2-07-013 | 2 | 5006551 | 7 | Los Angeles | Los Angeles County | SCAG | MTA | Roxford St. And I-5 (The Golden State Freeway) Southbound On And Off Ramps | Install Traffic Signals. | 220773.01 | 188099.92 | 2009-10-30 | 0 | 2012-07-30 | 2018-05-07 | 188099.92 | Authorized | Authorized | No | Closed | Federal | 0
HSIP2-07-014 | 2 | 5006553 | 7 | Los Angeles | Los Angeles County | SCAG | MTA | Intersection Of 11Th Ave. And Slauson Ave. | Install Traffic Signals | 212821.65 | 184729.87 | 2009-10-30 | 0 | 2011-07-25 | 2019-03-19 | 184729.87 | Authorized | Authorized | No | Closed | Federal | 0
HSIP2-07-015 | 2 | 5006554 | 7 | Los Angeles | Los Angeles County | SCAG | MTA | Crenshaw Blvd. And Jefferson Blvd. | Upgrade Traffic Signals; Install Protected And/Or Protected-Permissive Left Turn Phasing; Construct Curb Ramps | 118163.44 | 82149.34 | 2009-10-15 | 0 | 2012-05-31 | 2019-02-25 | 82149.34 | Authorized | Authorized | No | Closed | Federal | 0
HSIP2-07-016 | 2 | 5006648 | 7 | Los Angeles | Los Angeles County | SCAG | MTA | Oro Vista Ave. Between Foothill Blvd. And Hillrose St. | Install Frontage Improvements To Include Concrete Sidewalks, Curbs, Gutter, Ramps, Speed Feedback Signs, And Driveways. | 650000 | 207000 | 2010-11-10 | 0 | 2013-07-03 | 0 | 0 | Authorized | Authorized | No | Withdrawn | Federal | 0
HSIP2-07-017 | 2 | 5006649 | 7 | Los Angeles | Los Angeles County | SCAG | MTA | Devonshire St. Between Topanga Canyon Blvd. And Hanna Ave. | Construct Frontage Improvements To Include Concrete Sidewalks, Curbs, Gutters, Ramps, Speed Feedback Signs, And Driveways. | 266029.39 | 199862.31 | 2010-11-10 | 0 | 2013-07-03 | 2017-10-19 | 199862.31 | Authorized | Authorized | No | Closed | Federal | 0
HSIP2-07-018 | 2 | 5006650 | 7 | Los Angeles | Los Angeles County | SCAG | MTA | Anaheim St. From Vermont Ave. To Figueroa Pl. | Install Metal Beam Guardrail | 297435.8 | 266116.43 | 2010-11-10 | 0 | 2013-06-27 | 2016-04-25 | 266116.43 | Authorized | Authorized | No | Closed | Federal | 0
HSIP3-07-001 | 3 | 5006671 | 7 | Los Angeles | Los Angeles County | SCAG | MTA | Intersection Of Dearborn St. And Reseda Blvd. | Install Traffic Signal | 182334.85 | 154153.92 | 2010-08-18 | 0 | 2012-08-02 | 2018-05-14 | 154153.92 | Authorized | Authorized | No | Closed | Federal | 0
HSIP3-07-002 | 3 | 5006672 | 7 | Los Angeles | Los Angeles County | SCAG | MTA | Western Ave. And 37Th Place | Install Traffic Signal | 223564.94 | 160118.86 | 2010-08-17 | 0 | 2012-07-30 | 2018-05-07 | 160118.86 | Authorized | Authorized | No | Closed | Federal | 0
HSIP3-07-003 | 3 | 5006673 | 7 | Los Angeles | Los Angeles County | SCAG | MTA | Intersection Of Lankershim Blvd. And Valerio St. | Install Traffic Signal; Construct Curb Ramps | 227939.65 | 162000 | 2010-08-17 | 0 | 2012-07-30 | 2018-05-18 | 162000 | Authorized | Authorized | No | Closed | Federal | 0
HSIP3-07-005 | 3 | 5006687 | 7 | Los Angeles | Los Angeles County | SCAG | MTA | Intersection Of Broadway/Brazil St. And San Fernando Rd. At Metrolink'S Highway-Rail Grade Crossing | Construct New Medians; Upgrade Pedestrian Access And Curb Returns; Install Pavement Markings And Other Railroad Traffic Control Devices | 517967.17 | 466170.44 | 0 | 0 | 2013-07-23 | 2020-02-12 | 466170.44 | No PE | Authorized | No | Closed | Federal | 0
HSIP4-07-008 | 4 | 5006710 | 7 | Los Angeles | Los Angeles County | SCAG | MTA | 48th St. between Normandie Ave. and the W city limits of Los Angeles | Install traffic signals; upgrade and modify existing traffic signals; install left-turn and bike lanes | 573037.33 | 453735.82 | 2011-11-02 | 0 | 2013-02-22 | 2019-01-11 | 453735.82 | Authorized | Authorized | No | Closed | Federal | 0
HSIP4-07-033 | 4 | 5006711 | 7 | Los Angeles | Los Angeles County | SCAG | MTA | Gaffey St. between 11th St. and 15th St. | Install traffic signals | 406651.49 | 339417.47 | 2011-11-04 | 0 | 2012-11-09 | 2019-11-19 | 339417.47 | Authorized | Authorized | No | Closed | Federal | 0
HSIP4-07-043 | 4 | 5006721 | 7 | Los Angeles | Los Angeles County | SCAG | MTA | Entrada Ave. between Amalfi Ave. and Kingman Ave.; E. Channel Ave./Sage Ln. | Construct sidewalks and bulb-outs; improve crosswalks; install pedestrian warning device | 679848.11 | 551601.11 | 2012-01-06 | 0 | 2015-07-22 | 2019-02-26 | 551601.11 | Authorized | Authorized | No | Closed | Federal | 0
HSIP4-07-054 | 4 | 5006713 | 7 | Los Angeles | Los Angeles County | SCAG | MTA | Anaheim St., W of McFarland Ave. at the RR grade crossing | Construct medians and RR safety features; upgrade traffic control devices | 2694328.19 | 878027.48 | 2011-11-04 | 0 | 2015-09-16 | 2023-06-13 | 878027.48 | Authorized | Authorized | No | Closed | Federal | 0
HSIP4-07-055 | 4 | 5006703 | 7 | Los Angeles | Los Angeles County | SCAG | MTA | Roxford St./Foothill (I-210) on/off-ramps | Install traffic signals; modify signal operations; improve channelization | 307883.02 | 269042.41 | 2011-11-02 | 0 | 2015-08-10 | 2022-04-26 | 269042.41 | Authorized | Authorized | No | Closed | Federal | 0
HSIP4-07-056 | 4 | 5006707 | 7 | Los Angeles | Los Angeles County | SCAG | MTA | 64th St./Main St.; 49th St./Avalon Blvd.; Cohasset St./Tujunga Ave. | Install traffic signals | 726692.5 | 582186.39 | 2011-11-02 | 0 | 2012-11-16 | 2018-10-15 | 582186.39 | Authorized | Authorized | No | Closed | Federal | 0
HSIP4-07-057 | 4 | 5006708 | 7 | Los Angeles | Los Angeles County | SCAG | MTA | Pacific Ave./Santa Cruz St.; Hobart Blvd./Hollywood Blvd. | Install flashing beacon, left-turn lane, pedestrian-activated warning device | 321588.73 | 216332.88 | 2011-11-01 | 0 | 2012-11-16 | 2019-10-23 | 216332.88 | Authorized | Authorized | No | Closed | Federal | 0
HSIP4-07-058 | 4 | 5006709 | 7 | Los Angeles | Los Angeles County | SCAG | MTA | Various locations | Upgrade traffic signals; modify signal phasing; install curb ramps; construct left turn lanes. | 555845.7 | 500094.36 | 2011-11-04 | 0 | 2012-11-20 | 2018-12-13 | 500094.36 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-07-024 | 5 | 5006769 | 7 | Los Angeles | Los Angeles County | SCAG | MTA | Corbin Ave./Roscoe Blvd.; Glenoaks Blvd./Hubbard St.; Mason Ave./Roscoe Blvd.; Saticoy St./Winnetka Ave.; Sepulveda Blvd./Vose St.; Victory Blvd./White Oak Ave.; Victory Blvd./Whitsett Ave.; Laurelgrove Ave./Riverside Dr. | Install traffic signal and left-turn phasing | 1305046.92 | 857419.95 | 2013-06-28 | 0 | 2014-08-15 | 2019-11-19 | 857419.95 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-07-025 | 5 | 5006770 | 7 | Los Angeles | Los Angeles County | SCAG | MTA | 3rd St./Carondelet St.; Slauson Ave./6th Ave.; Slauson Ave./7th Ave.; Pico Blvd./Granville Ave. | Install traffic signal, flashing beacons, and raised median islands. | 641529.31 | 445962 | 2013-07-03 | 0 | 2015-07-22 | 2022-07-26 | 445962 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-07-026 | 5 | 5006771 | 7 | Los Angeles | Los Angeles County | SCAG | MTA | Cesar Chavez Ave./Forest Ave.; Temple St. between Patton Ave. and Bixel St. | Install rapid flashing beacons, speed feedback signs, and minor signing and striping. | 287314.51 | 257682.65 | 2013-07-09 | 0 | 2015-07-28 | 2022-10-26 | 257682.65 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-07-027 | 5 | 5006772 | 7 | Los Angeles | Los Angeles County | SCAG | MTA | Pacific Ave. between Windward Ave. and 18th Ave. | Install traffic signal, crosswalks, median islands, signs, and striping; construct sidewalks | 1272556 | 793800 | 2013-07-03 | 0 | 2015-09-16 | 0 | 0 | Authorized | Authorized | No | Withdrawn | Federal | 0
HSIP5-07-028 | 5 | 5006773 | 7 | Los Angeles | Los Angeles County | SCAG | MTA | Pico Blvd./Wooster St.; Pico Blvd./Bedford St. | Install traffic signals | 396928.79 | 350274.76 | 2013-07-03 | 0 | 2014-08-26 | 2019-11-27 | 350274.76 | Authorized | Authorized | No | Closed | Federal | 0
HSIP6-07-014 | 6 | 5006788 | 7 | Los Angeles | Los Angeles County | SCAG | MTA | Vineland Ave./Magnolia Blvd., Woodman Ave./Woodman Place, Vineland Ave./Riverside Dr., Van Nuys Blvd./Vanowen St., Nordhoff St./Van Nuys Blvd, S. Western Ave./W. Vernon Ave | Upgrade traffic signals; Install protected left-turn phasing | 856000 | 770300 | 2014-08-05 | 0 | 2018-12-18 | 0 | 730700 | Authorized | Authorized | No | CON | Federal | 0
HSIP6-07-015 | 6 | 5006789 | 7 | Los Angeles | Los Angeles County | SCAG | MTA | S. Crest Dr./W. Pico Blvd., Ventura Blvd./Calhoun Ave., Ventura Blvd./Columbus Ave., and Ventura Blvd./Lemona Ave. | Install traffic signals | 1123400 | 1010900 | 2014-07-31 | 0 | 2018-12-19 | 0 | 845800 | Authorized | Authorized | No | CON | Federal | 0
HSIP6-07-019 | 6 | 5006793 | 7 | Los Angeles | Los Angeles County | SCAG | MTA | W 3rd St/Hoover St, W Anaheim St/Bay View Ave, W Anaheim St/N Marine Ave, and E Century Blvd/Wadsworth Ave | Install traffic signals | 1200000 | 1080000 | 2014-08-05 | 0 | 2018-12-19 | 0 | 888200 | Authorized | Authorized | No | CON | Federal | 0
HSIP6-07-020 | 6 | 5006794 | 7 | Los Angeles | Los Angeles County | SCAG | MTA | The installation of Rapid Rectangular Flashing Beacons (RRFBs) to improve pedestrian crossing at 35 uncontrolled locations within the City of Los Angeles. | Install Rectangular Rapid Flashing Beacons | 1433600 | 1290200 | 2014-07-25 | 0 | 2019-03-19 | 0 | 1290200 | Authorized | Authorized | No | CON | Federal | 0
HSIP6-07-021 | 6 | 5006795 | 7 | Los Angeles | Los Angeles County | SCAG | MTA | 92nd St/Bandera St | Upgrade signs; Construct curb extensions; Install crosswalk and Rectangular Rapid Flashing Beacon | 217773.37 | 196052.41 | 2014-07-25 | 0 | 2016-07-26 | 2017-05-22 | 196052.41 | Authorized | Authorized | No | Closed | Federal | 0
HSIP7-07-013 | 7 | 5006843 | 7 | Los Angeles | Los Angeles County | SCAG | MTA | Citywide list of 24 locations starting with Avalon Bl & 90th St; Avalon Bl & 97th St; etc. | Install one HAWK at Grand View Ave, Meade Pl & Venice Blvd; Install rectangular rapid flashing beacons (RRFBs) at 23 other uncontrolled locations. | 4140800 | 3726720 | 2016-10-25 | 0 | 2021-01-06 | 0 | 3726720 | Authorized | Authorized | No | CON | Federal
HSIP7-07-014 | 7 | 5006844 | 7 | Los Angeles | Los Angeles County | SCAG | MTA | 9 intersections in City of Los Angeles | Modify traffic signals by installing turn phasing, upgrading signal indication sizes, install audible pedestrian devices | 4496900 | 4496900 | 2016-12-15 | 0 | 2021-01-13 | 0 | 4496900 | Authorized | Authorized | No | CON | Federal
HSIP7-07-015 | 7 | 5006845 | 7 | Los Angeles | Los Angeles County | SCAG | MTA | Crenshaw Boulevard from Florence Avenue to 79th Street | Construct raised medians, curb extensions, connecting curb ramps, and modify signals | 2320000 | 1776380 | 2016-06-13 | 0 | 2022-07-14 | 0 | 1776380 | Authorized | Authorized | No | CON | Federal
H8-07-026 | 8 | 5953756 | 7 | Los Angeles County | Los Angeles County | SCAG | MTA | Intersections of Olympic Boulevard at Garfield Avenue and Whittier Boulevard at Eastern Avenue, located in the unincorporated County area of East Los Angeles. | Install various traffic signal improvements, including upgrading standards, mastarms, vehicle heads, protected left-turn phasing, bicycle and vehicle detection, ADA access ramps, communication, and other associated equipment. | 763000 | 763000 | 2017-05-31 | 0 | 2022-09-08 | 0 | 763000 | Authorized | Authorized | No | CON | Federal | 0
H8-07-027 | 8 | 5953752 | 7 | Los Angeles County | Los Angeles County | SCAG | MTA | Intersections of Covina Boulevard at Hollenbeck Avenue, Cypress Street at Vincent Avenue, and Workman Mill Road at Lomitas Avenue, located in the unincorporated County area of San Gabriel Valley. | Install various traffic signal equipment upgrades, including upgrading standards, mastarms, vehicle heads, bicycle and vehicle detection, access ramps, communication, and other associated equipment. | 1252100 | 1252100 | 2017-06-16 | 0 | 2022-03-07 | 0 | 1252100 | Authorized | Authorized | No | CON | Federal | 0
H8-07-028 | 8 | 5953755 | 7 | Los Angeles County | Los Angeles County | SCAG | MTA | Intersections of 120th Street at Normandie Avenue and 120th Street at Compton Avenue, located in the unincorporated County areas of West Athens and Willowbrook. | Install various traffic signal equipment upgrades, including upgrading standards, mastarms, vehicle heads, bicycle and vehicle detection, protected-permissive left-turn phasing, access ramps, communication, and other associated equipment. | 957800 | 957800 | 2017-06-16 | 0 | 2022-06-07 | 0 | 957800 | Authorized | Authorized | No | CON | Federal | 0
H8-07-029 | 8 | 5953759 | 7 | Los Angeles County | Los Angeles County | SCAG | MTA | Intersections of Amar Rd at Baldwin Park Blvd, Badillo St at Irwindale Ave, Santa Anita Ave at Freer St, and Temple Ave at Azusa Ave, in various city/county shared-jurisdiction locations in the San Gabriel Valley area. | Install various traffic signal equipment upgrades, including upgrading standards, mastarms, vehicle heads, protected left-turn phasing, bicycle and vehicle detection, access ramps, communication, and other associated equipment. | 2635600 | 1460640 | 2017-06-20 | 0 | 2023-01-25 | 0 | 1217200 | Authorized | Authorized | No | CON | Federal | 2
H8-07-030 | 8 | 5953757 | 7 | Los Angeles County | Los Angeles County | SCAG | MTA | Intersections of Las Virgenes Road at Mulholland Highway and at Piuma Road, in Unincorporated County Area. | Install traffic signal improvements: upgrade 8" vehicle heads to 12"; install video detection, Battery Back-up and CCTV systems; and establish communications with LA County Traffic Management Center (TMC). | 183139.37 | 112400 | 2017-06-16 | 0 | 2019-11-27 | 2022-03-22 | 112400 | Authorized | Authorized | No | Closed | Federal | 0
H8-07-031 | 8 | 5953760 | 7 | Los Angeles County | Los Angeles County | SCAG | MTA | Glendora Mountain Road from Big Dalton Canyon Road to East Fork Road . | Remove existing centerline striping and install recessed thermoplastic striping and recessed pavement markers | 1203561.86 | 828000 | 2017-06-20 | 0 | 2020-01-10 | 2022-04-13 | 828000 | Authorized | Authorized | No | Closed | Federal | 0
H8-07-032 | 8 | 5953779 | 7 | Los Angeles County | Los Angeles County | SCAG | MTA | Bouquet Canyon Road between 640 ft North of M.M. 16.43 and 1145 ft North of M.M 3.52 | Install chevron signs, curve advance warning signs, and variable speed warning signs. | 475100 | 475100 | 0 | 0 | 2023-08-04 | 0 | 475100 | No PE | Authorized | No | CON | Federal | 1
H8-07-033 | 8 | 5953758 | 7 | Los Angeles County | Los Angeles County | SCAG | MTA | San Francisquito Canyon Road between 715 ft North of M.M. 0.42 to 530 ft North of M. M. 16.33. Lake Hughes Road between Elizabeth lake Road and 215 ft East of M.M. 20.58 | Install chevron signs and advance curve warning signs. | 1086500 | 1086500 | 2017-06-16 | 0 | 2024-03-19 | 0 | 1076518.5 | Authorized | Authorized | No | CON | Federal | 1
H9-07-012 | 9 | 5953776 | 7 | Los Angeles County | Los Angeles County | SCAG | MTA | City/County shared-jurisdiction locations in the Athens, Rancho Dominguez Hills, West Carson, Willowbrook areas (Broadway at El Segundo Blvd, Broadway at Rosecrans Ave, Normandie Ave at 104th St, Normandie Ave at 228th St, and Rosecrans Ave at Atlantic Ave). | Construct various traffic signal improvements, including upgrading standards, mastarms, protected-permissive left-turn phasing, vehicle heads, bicycle and vehicle detection, ADA access ramps, communication, and other associated equipment. | 2320500 | 2320500 | 2019-06-24 | 0 | 2025-03-04 | 0 | 2320500 | Authorized | Authorized | No | CON | Federal | 0
H9-07-014 | 9 | 5953791 | 7 | Los Angeles County | Los Angeles County | SCAG | MTA | The intersections of Avalon Blvd at 135th St and Avalon Blvd at Rosecrans Ave, in the unincorporated County area of Willowbrook. | Construct various traffic signal improvements, including upgrading standards, mastarms, vehicle heads, bicycle and vehicle detection, ADA access ramps, communication, and other associated equipment. | 749500 | 749500 | 0 | 0 | 2024-07-23 | 0 | 749500 | No PE | Authorized | No | CON | Federal | 0
HSIP2-07-047 | 2 | 5953462 | 7 | Los Angeles County | Los Angeles County | SCAG | MTA | Intersection Of Woodbury Rd. And Fair Oaks Ave. | Upgrade Traffic Signals, Signing, Striping And Pavement Markings; Construct Curb Ramps | 34721.1111 | 31249 | 0 | 0 | 2010-12-07 | 0 | 25243.29 | No PE | Authorized | No | CON | Federal | 0
HSIP2-07-048 | 2 | 5953476 | 7 | Los Angeles County | Los Angeles County | SCAG | MTA | Various Roads Within The Santa Monica Mountains Known As The "Mulholland Raceway" | Install Centerline Rumble Strips | 301033.82 | 229624.72 | 0 | 0 | 2010-08-18 | 2013-03-19 | 229624.72 | No PE | Authorized | No | Closed | Federal | 0
HSIP2-07-049 | 2 | 5953629 | 7 | Los Angeles County | Los Angeles County | SCAG | MTA | Hawes Street Over Leffingwell Creek And Other Drainage Canal Locations | Replace Existing Chain Link Fence And Existing Sidewalk With Concrete Barriers And Sidewalks. | 496555.54 | 310411 | 2009-05-21 | 0 | 2010-09-14 | 2012-12-27 | 310411 | Authorized | Authorized | No | Closed | Federal | 0
HSIP2-07-052 | 2 | 5953637 | 7 | Los Angeles County | Los Angeles County | SCAG | MTA | Intersection Of Ramona Blvd. And Campus Rd. | Upgrade Traffic Signals, Signing, Striping And Pavement Markings | 205051.89 | 88633 | 0 | 0 | 2010-09-14 | 2014-09-03 | 88633 | No PE | Authorized | No | Closed | Federal | 0
HSIP3-07-022 | 3 | 5953599 | 7 | Los Angeles County | Los Angeles County | SCAG | MTA | Colima Rd. Between Banida Ave. And Brea Canyon Cutoff; Olympic Blvd. Between Kern Ave. And Hillview Ave.; Valley Blvd. Between Santa Mariana Ave. And Bielec Ln. | Conduct Roadway Safety Audit Along Three Corridors | 114478.73 | 54000 | 0 | 0 | 2011-12-28 | 2019-10-10 | 54000 | No PE | Authorized | No | Closed | Federal | 0
HSIP3-07-023 | 3 | 5953651 | 7 | Los Angeles County | Los Angeles County | SCAG | MTA | Angeles Forest Hwy. | Install Guardrail, Advance Warning Signs, Delineators And Pavement Markings | 1993339.58 | 900000 | 2010-09-09 | 0 | 2012-11-20 | 2018-01-17 | 900000 | Authorized | Authorized | No | Closed | Federal | 0
HSIP3-07-024 | 3 | 5953653 | 7 | Los Angeles County | Los Angeles County | SCAG | MTA | Reis St. North Crossing Over Sorensen Drain 707-B3, Mills Ave. Over Sorensen Drain 707-D5, Gladstone St. Over Big Dalton Wash 599-C1 | Remove And Replace Steel Railing And Sidewalk | 925961.45 | 461070 | 2010-09-14 | 0 | 2012-08-31 | 2015-09-15 | 461070 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-07-031 | 5 | 5953669 | 7 | Los Angeles County | Los Angeles County | SCAG | MTA | Pacific Blvd./California St. | Construct bulb-outs | 903483.54 | 383900 | 2013-03-12 | 0 | 2016-02-25 | 2019-07-25 | 383900 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-07-033 | 5 | 5953709 | 7 | Los Angeles County | Los Angeles County | SCAG | MTA | Del Amo Blvd./Hamilton Ave. | Install traffic signal | 482679.63 | 260700 | 0 | 0 | 2016-10-25 | 2020-03-25 | 260700 | No PE | Authorized | No | Closed | Federal | 0
HSIP5-07-034 | 5 | 5953671 | 7 | Los Angeles County | Los Angeles County | SCAG | MTA | El Segundo Blvd./Willowbrook Ave.; El Segundo Blvd./Central Ave. | Upgrade traffic signals | 545875.31 | 205200 | 2013-03-12 | 0 | 2016-02-12 | 2019-09-20 | 205200 | Authorized | Authorized | No | Closed | Federal | 0
HSIP6-07-022 | 6 | 5953690 | 7 | Los Angeles County | Los Angeles County | SCAG | MTA | Hacienda Blvd/Newton St | Upgrade traffic signals; Install ADA pedestrian pushbuttons, and crosswalk; Construct curb ramps | 503469.42 | 187200 | 2014-06-17 | 0 | 2017-05-22 | 2020-03-30 | 187200 | Authorized | Authorized | No | Closed | Federal | 0
HSIP6-07-023 | 6 | 5953693 | 7 | Los Angeles County | Los Angeles County | SCAG | MTA | Colima Rd/Leffingwell Rd | Upgrade traffic signals; Construct curb ramps; Install ADA pedestrian pushbuttons | 340385.23 | 130700 | 2014-06-20 | 0 | 2017-05-15 | 2020-05-12 | 130700 | Authorized | Authorized | No | Closed | Federal | 0
HSIP6-07-024 | 6 | 5953694 | 7 | Los Angeles County | Los Angeles County | SCAG | MTA | San Pedro St/Rosecrans Ave | Upgrade traffic signals; Install ADA pedestrian pushbutton | 619631.65 | 140100 | 2014-06-27 | 0 | 2017-05-23 | 2020-09-18 | 140100 | Authorized | Authorized | No | Closed | Federal | 0
HSIP6-07-025 | 6 | 5953697 | 7 | Los Angeles County | Los Angeles County | SCAG | MTA | Atlantic Blvd/Olympic Blvd | Upgrade traffic signals; Install ADA pedestrian pushbutton, crosswalk; Construct curb ramps | 638640.5 | 167200 | 2014-07-08 | 0 | 2017-05-15 | 2020-09-23 | 167200 | Authorized | Authorized | No | Closed | Federal | 0
HSIP6-07-026 | 6 | 5953695 | 7 | Los Angeles County | Los Angeles County | SCAG | MTA | Eastern Ave/Olympic Blvd | Upgrade traffic signals; Install ADA pedestrian pushbutton, crosswalk; Construct curb ramps | 580677.62 | 180100 | 2014-06-20 | 0 | 2017-05-22 | 2020-09-23 | 180100 | Authorized | Authorized | No | Closed | Federal | 0
HSIP6-07-027 | 6 | 5953700 | 7 | Los Angeles County | Los Angeles County | SCAG | MTA | Various locations throughout unincorporated areas of Los Angeles County | Upgrade crosswalk; Install signs and pavement markings | 1242587.13 | 525200 | 2014-07-11 | 0 | 2018-06-28 | 2020-11-24 | 525200 | Authorized | Authorized | No | Closed | Federal | 0
HSIP6-07-028 | 6 | 5953691 | 7 | Los Angeles County | Los Angeles County | SCAG | MTA | Santa Gertrudes Ave/Silvergrove Dr, Leffingwell Rd/Arroyo Dr | Install traffic signals | 856603.89 | 652600 | 2014-06-17 | 0 | 2017-05-31 | 2020-05-12 | 652600 | Authorized | Authorized | No | Closed | Federal | 0
HSIP6-07-031 | 6 | 5953698 | 7 | Los Angeles County | Los Angeles County | SCAG | MTA | Various locations throughout the unincorporated Los Angeles Counties of Willbrook and West Rancho Dominguez | Install bike lanes; Road Diet (reduce travel lanes) | 1630600 | 1467400 | 2014-06-27 | 0 | 2018-11-30 | 0 | 0 | Authorized | Authorized | No | Withdrawn | Federal | 0
HSIP6-07-032 | 6 | 5953704 | 7 | Los Angeles County | Los Angeles County | SCAG | MTA | On Washington Blvd between Bellford Ave and N Altadena Dr, On N Altadena Dr between Canyon Close Rd and E Washington Blvd | Install bike lanes; Road Diet (reduce travel lanes) | 1956000 | 1492100 | 2014-07-16 | 0 | 2018-12-14 | 0 | 0 | Authorized | Authorized | No | Withdrawn | Federal | 0
HSIP6-07-033 | 6 | 5953699 | 7 | Los Angeles County | Los Angeles County | SCAG | MTA | Various locations throughout Charter Oaks community | Install bike lanes and striping; construct medians | 1831842.62 | 1013300 | 2014-07-08 | 0 | 2017-04-12 | 2019-06-20 | 1013300 | Authorized | Authorized | No | Closed | Federal | 0
HSIP6-07-034 | 6 | 5953702 | 7 | Los Angeles County | Los Angeles County | SCAG | MTA | On Lake Hughes Rd between Elizabeth Lake Rd and Mile Marker 17.2 | Install guardrails and pavement markers | 762097.67 | 364499.99 | 2014-07-23 | 0 | 2018-07-09 | 2021-05-18 | 364499.99 | Authorized | Authorized | No | Closed | Federal | 0
HSIP6-07-035 | 6 | 5953703 | 7 | Los Angeles County | Los Angeles County | SCAG | MTA | On Bouquet Canyon Rd between 1 mile south of Elizabeth Lake Rd and Blue Cloud Rd; On San Francisqutio Canyon Rd between Elizabeth Lake Rd and Copper Hill Dr | Install guardrails and centerline recessed pavement markers | 1520052.17 | 1012332.53 | 2014-07-11 | 0 | 2018-07-17 | 2022-12-09 | 1012332.53 | Authorized | Authorized | No | Closed | Federal | 0
HSIP6-07-036 | 6 | 5953701 | 7 | Los Angeles County | Los Angeles County | SCAG | MTA | 524 various County maintained locations within the unincorporated areas of Los Angeles County | Install pedestrian countdown heads | 896784.54 | 887922.31 | 2014-07-11 | 0 | 2016-03-16 | 2019-03-19 | 887922.31 | Authorized | Authorized | No | Closed | Federal | 0
H9-07-015 | 9 | 5250031 | 7 | Lynwood | Los Angeles County | SCAG | MTA | The intersection of Imperial Highway and Atlantic Avenue | Add left turn phases and modernize control equipment, detection and lighting, construct curb ramps and pertinent striping improvements. | 459645.41 | 459645.41 | 2019-12-11 | 0 | 2022-07-06 | 2024-11-15 | 459645.41 | Authorized | Authorized | No | Closed | Federal | 0
H9-07-016 | 9 | 5250030 | 7 | Lynwood | Los Angeles County | SCAG | MTA | Intersection of Alameda St at Martin Luther King, Jr. Blvd. | Add left turn phases, detection and lighting, upgrade ramps and striping improvements. | 460900 | 460900 | 2019-12-04 | 0 | 0 | 0 | 21000 | Authorized | Due in no more than 4 months | No | PE | Federal | 0
H9-07-017 | 9 | 5250029 | 7 | Lynwood | Los Angeles County | SCAG | MTA | Intersection of Atlantic Ave at Carlin Ave. | Install left turn phases, cabinet modifications, detection, lighting, upgrade ramps and striping improvements. | 522349 | 522348.33 | 2019-12-11 | 0 | 2022-06-16 | 2024-11-07 | 522348.33 | Authorized | Authorized | No | Closed | Federal | 0
HSIP3-07-032CON | 3 | 5250025 | 7 | Lynwood | Los Angeles County | SCAG | MTA | In The Vicinity Of Firebaugh High School, Will Rogers School, And J.P. Abbott School | Install In-Roadway Warning Light Systems And Radar Speed Feedback Signs; Construct Bulb Outs | 342852.78 | 308566.7 | 0 | 0 | 2015-09-16 | 2019-02-04 | 308566.7 | No PE | Authorized | No | Closed | Federal | 0
HSIP5-07-035 | 5 | 5250032 | 7 | Lynwood | Los Angeles County | SCAG | MTA | The St. Francis Hospital located at the southwest comer of Imperial Highway and Martin Luther Ki ng, Jr. Blvd. Improvements at Stockwell, Arvall , Benwell, and MLK Jr. Blvd. | City will install pedestrian crossings, signs, safety features, and pedestrian signals. | 342100 | 342099.86 | 0 | 0 | 2021-06-15 | 2025-05-29 | 342099.86 | No PE | Authorized | No | Closed | Federal | 0
HSIP3-07-020 | 3 | 5462017 | 7 | Malibu | Los Angeles County | SCAG | MTA | Pacifc Coast Highway (SR-l) from the intersection of Busch Drive westward to the City limits | Improve Existing Bike Route; Install Signs And Stripes; Widen Shoulders | 1077008.31 | 900000 | 2010-12-22 | 0 | 2013-09-18 | 2016-06-28 | 900000 | Authorized | Authorized | No | Closed | Federal | 0
H11-07-025 | 11 | 5212015 | 7 | Manhattan Beach | Los Angeles County | SCAG | MTA | Manhattan Avenue and 36th Street; Valley Drive and Flournoy Road; and Highland Avenue and 40th Street. | Install new pedestrian crosswalk with Americans with Disabilities Act (ADA) ramps. | 245000 | 220500 | 2023-06-30 | 0 | 0 | 0 | 36000 | Authorized | Due by 9/30/2026 | No | PE | State | 0
HSIP5-07-036 | 5 | 5212011 | 7 | Manhattan Beach | Los Angeles County | SCAG | MTA | Sepulveda Blvd./8th St. | Upgrade traffic signals; install protected left-turn phasing; construct curb ramps | 388666.68 | 344901 | 2014-05-20 | 0 | 2018-06-15 | 2021-10-14 | 344901 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-07-037 | 5 | 5212010 | 7 | Manhattan Beach | Los Angeles County | SCAG | MTA | Seventeen (17) intersections throughout the city | Install crosswalks, pedestrian countdown heads, flashing beacons, and signs; and construct curb ramps and bulb-outs | 531000 | 233699.99 | 2013-08-25 | 0 | 2018-04-30 | 2021-04-08 | 233699.99 | Authorized | Authorized | No | Closed | Federal | 0
H11-07-026 | 11 | 5265018 | 7 | Maywood | Los Angeles County | SCAG | MTA | 21 traffic signals on the Slauson Ave corridor (east-west) between Alamo Ave to Maywood Ave; and the Atlantic Ave Corridor (north-south) between E. 52nd St to Randolph Ave. | Improve signal hardware, install pedestrian countdown signal heads and modify signal phasing. | 1892350 | 1703115 | 2023-05-19 | 0 | 2024-09-06 | 0 | 1703115 | Authorized | Authorized | No | CON | State | 0
HSIP4-07-037 | 4 | 5069013 | 7 | Monrovia | Los Angeles County | SCAG | MTA | Huntinton Dr./5th Ave.; Duarte Rd./Peck Rd.; Foothill Blvd./Sunset Pl.; Foothill Blvd./California Ave. | Install pedestrian safety devices and crosswalk lighting system; upgrade traffic signals | 790014.86 | 623988.06 | 2013-12-16 | 0 | 2020-08-04 | 2026-02-06 | 623988.06 | Authorized | Authorized | No | Closed | Federal | 0
HSIP1-07-007 | 1 | 5247012 | 7 | Montebello | Los Angeles County | SCAG | MTA | Intersection Of Garfield Avenue And Via San Clemente. | Install Traffic Signal. | 138988.5 | 125089.65 | 0 | 0 | 2008-10-07 | 2011-03-06 | 125089.65 | No PE | Authorized | No | Closed | Federal | 0
HSIP2-07-012 | 2 | 5247020 | 7 | Montebello | Los Angeles County | SCAG | MTA | Montebello Blvd. from Mines Avenue to Roosevelt Avenue | Upgrade Traffic Signals; Left Turn Phasing, Ped and Vehicular Signage, Railroad Preemption, Safety Lighting, and Install Center Median | 567918.32 | 101185.68 | 0 | 0 | 2014-07-25 | 2022-03-09 | 101185.68 | No PE | Authorized | No | Closed | Federal | 0
HSIP7-07-016&017&018 | 7 | 5247024 | 7 | Montebello | Los Angeles County | SCAG | MTA | The intersections of Via Campo and Findlay Avenue; Garfield Avenue and Whittier Boulevard; and Garfield Avenue and Via Campo | Upgrade signal hardware, improve signal timing and operation | 747031.87 | 747031.87 | 2017-01-18 | 0 | 2019-09-13 | 2025-12-10 | 747031.87 | Authorized | Authorized | No | Closed | Federal
H9-07-018 | 9 | 5231018 | 7 | Monterey Park | Los Angeles County | SCAG | MTA | Vvarious signalized intersections along Garfield Avenue between the northern and southern city limits. | Install signal hardware improvements to the lenses, back-plates with retroreflective borders, mounting, size, and number, as well as installation of pedestrian countdown signal heads. | 511822.64 | 511822.64 | 2019-11-21 | 0 | 2023-02-23 | 2025-01-07 | 511822.64 | Authorized | Authorized | No | Closed | Federal | 0
HSIP7-07-019 | 7 | 5231016 | 7 | Monterey Park | Los Angeles County | SCAG | MTA | Three downtown intersections in Monterey Park; Garfield Ave & Hellman Ave, Garfield Ave & Emerson Ave, and Alhambra Ave & Hellman Ave with Almansor St | Improve signal timing at 3 downtown intersections. Add Left turn phase to 2 intersections. Add Left turn lane and phase at 1 intersection. Improve signal hardware at 2 of them and install pedestrian countdown signal heads at all 3 | 1036111 | 932500 | 0 | 0 | 2021-04-01 | 2024-11-07 | 932500 | No PE | Authorized | No | Closed | Federal
HSIP3-07-033 | 3 | 5436018 | 7 | Moorpark | Ventura County | SCAG | VCTC | Princeton Avenue East of Spring Road to the South of Condor Drive Improvements | Improve Existing Road For Class II Bikeway In Both Directions; Construct Curb And Gutter; Install 2-Way Left-Turn Lane, Signs, Stripes And Pavement Markings. Construct Retaining Walls. | 15217684.06 | 1000000 | 0 | 0 | 2021-11-18 | 2026-01-30 | 1000000 | No PE | Authorized | No | Closed | Federal | 0
H8-07-034 | 8 | 0 | 7 | Norwalk | Los Angeles County | SCAG | MTA | Pioneer Boulevard between 166th Street (South City Limits) and Lakeland Road (North City Limits). | Upgrade signals to provide separate left-turn phasing at eight (8) intersections and provide various safety improvements at adjacent intersections. | 2911000 | 2911000 | 0 | 0 | 0 | 0 | 0 | No PE | Past due (due 12/31/2023) | Yes (CON) | Not Started | Federal | 0
H8-07-035 | 8 | 0 | 7 | Norwalk | Los Angeles County | SCAG | MTA | Pioneer Boulevard between 166th Street (South City Limits) and Lakeland Avenue (North City Limits). | Update signal timing and coordinated operations of fifteen (15) signalized intersections, construct a fiber-optic communication network to integrate with the City's Traffic Management Center (TMC). | 1281700 | 640850 | 0 | 0 | 0 | 0 | 0 | No PE | Past due (due 12/31/2023) | Yes (CON) | Not Started | Federal | 0
H8-07-036 | 8 | 0 | 7 | Norwalk | Los Angeles County | SCAG | MTA | Norwalk Boulevard from 166th Street (South City Limits) to Rosecrans Avenue; and from Adoree Street to Lakeland Road (North City Limits). | Upgrade signals to provide separate left turn phasing at six (6) intersections and provide various safety improvements at adjacent intersections. | 2294500 | 2294500 | 0 | 0 | 0 | 0 | 0 | No PE | Past due (due 12/31/2023) | Yes (CON) | Not Started | Federal | 0
H8-07-037 | 8 | 0 | 7 | Norwalk | Los Angeles County | SCAG | MTA | Norwalk Boulevard from 166th Street (South City Limits) to Rosecrans Avenue; and from Adoree Street to Lakeland Road (North City Limits). | Update signal timing and coordinated operations of eleven (11) signalized intersections, construct a fiber-optic communication network to integrate with the City's Traffic Management Center (TMC). | 1135100 | 567550 | 0 | 0 | 0 | 0 | 0 | No PE | Past due (due 12/31/2023) | Yes (CON) | Not Started | Federal | 0
HSIP6-07-037 | 6 | 5347038 | 7 | Norwalk | Los Angeles County | SCAG | MTA | On Rosecrans Ave between Studebaker Rd and Carmenita Rd | Upgrade traffic signals (interconnect); Install pedestrian countdown heads | 2568400 | 2311560 | 2014-07-23 | 0 | 2019-04-30 | 0 | 2311560 | Authorized | Authorized | No | CON | Federal | 0
HSIP6-07-038 | 6 | 5347039 | 7 | Norwalk | Los Angeles County | SCAG | MTA | On Studebaker Rd between Alondra Blvd and Rosecrans Ave | Upgrade traffic signals (interconnect)and curb ramps; Install pedestrian countdown heads | 1026100 | 923490 | 2014-07-25 | 0 | 2018-12-19 | 0 | 923490 | Authorized | Authorized | No | CON | Federal | 0
HSIP6-07-039 | 6 | 5347040 | 7 | Norwalk | Los Angeles County | SCAG | MTA | On San Antonio Ave-Norwalk Blvd between Rosecrans Ave and Civic Center Dr, and On Civic Center Dr between Norwalk Blvd and Bloomfield Ave | Upgrade traffic signals (interconnect)and curb ramps; install pedestrian countdown signal heads | 1890700 | 1701630 | 2014-07-25 | 0 | 2019-04-30 | 0 | 1701630 | Authorized | Authorized | No | CON | Federal | 0
HSIP7-07-020 | 7 | 5347042 | 7 | Norwalk | Los Angeles County | SCAG | MTA | Alondra Boulevard between Piuma Avenue and Shoemaker Avenue | Traffic signal upgrades including fiber optic cable, new controllers, signal head upgrades, pedestrian countdown signal heads, and new traffic poles | 1850850 | 1850850 | 2017-11-08 | 0 | 2021-12-02 | 0 | 1850850 | Authorized | Authorized | No | CON | Federal
HSIP7-07-021 | 7 | 5347043 | 7 | Norwalk | Los Angeles County | SCAG | MTA | Firestone Boulevard between West City Limits (Interstate 605) and Rosecrans Ave (Interstate 5) | Traffic signal upgrades: fiber optic cable, new controllers, appurtenant equipment and intersection pedestrian countdown signal heads | 1603225 | 1603225 | 2017-11-08 | 0 | 2021-11-10 | 0 | 1603225 | Authorized | Authorized | No | CON | Federal
HSIP7-07-022 | 7 | 5347044 | 7 | Norwalk | Los Angeles County | SCAG | MTA | Studebaker Road between Rosecrans Avenue and Cecilia Street | Traffic signal upgrades: fiber optic cable, new controllers, appurtenant equipment and intersection pedestrian countdown signal heads | 1798564 | 1798564 | 2017-11-08 | 0 | 2021-11-10 | 0 | 1798564 | Authorized | Authorized | No | CON | Federal
H10-07-024 | 10 | 0 | 7 | Ojai | Ventura County | SCAG | VCTC | On State Route 150 (Ojai Ave.) at Canada, Blanche and Ventura Streets (post mile marker 17.3 to 17.5). | Install curb extensions at NW and NE corners and a median, and related striping (Canada St); install curb extension at NE corner and related striping (Blanche St); and install curb extensions at NE and SE corners and related striping (Ventura St). | 307500 | 242500 | 0 | 0 | 0 | 0 | 0 | No PE | Due by 9/30/2027 | No | Not Started | State | 0
H10-07-025 | 10 | 5129100 | 7 | Oxnard | Ventura County | SCAG | VCTC | Ten intersections including: Gonzales & Lombard, Gonzales & Solar, Rice & Camino Del Sol, Rose & Bard, Saviers & Hueneme, Ventura Rd & Doris, Vineyard & Esplanade, Pleasant Valley & C St, Harbor Blvd & 5th, and Saviers Rd & Laurel St. | Construct traffic signal improvements, including upgrading standards, mast arms, protected-left turn phasing, street lighting, emergency vehicle preemption, and accessible crossing. | 2998600 | 2998600 | 2021-06-28 | 0 | 0 | 0 | 297500 | Authorized | Past due (due 9/30/2024) | Yes (CON) | PE | State | 0
H10-07-026 | 10 | 5129101 | 7 | Oxnard | Ventura County | SCAG | VCTC | 4 intersection crossings adjacent to Ramona Elementary School, along Bonita Ave from 1st St to Cooper Rd and Cooper Rd from Bonita Ave to Juanita Ave. | Install Rectangular Rapid Flashing Beacons (RRFBs), curb extensions, high visilbility crosswalks, pedestrian signage and advance pavement markings. | 276600 | 249936 | 2021-06-29 | 0 | 2022-06-09 | 0 | 249936 | Authorized | Authorized | No | CON | State | 0
H11-07-027 | 11 | 5129110 | 7 | Oxnard | Ventura County | SCAG | VCTC | Intersections and roadway on Ventura Road from Second Street to Wooley Road. | Install class II bike lanes (with green conflict areas), leading pedestrian intervals, additional signal heads, retroreflective backplates, advance stop bars, high visibility crosswalks, and bike and pedestrian warning signs. | 821100 | 738990 | 2023-12-04 | 0 | 0 | 0 | 130500 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE | State | 0
H11-07-028 | 11 | 5129111 | 7 | Oxnard | Ventura County | SCAG | VCTC | Intersections and roadway on Bard Road from Saviers Road to Pleasant Valley Road. | Green bike conflict striping, leading pedestrian intervals, retroreflective backplates, advance stop bars, high visibility crosswalks, advance warning flashing beacons, upgraded signs, and movement restricting median improvements. | 775700 | 698130 | 2023-12-04 | 0 | 0 | 0 | 121500 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE | State | 0
H12-07-022 | 12 | 0 | 7 | Oxnard | Ventura County | SCAG | VCTC | Seven intersections: Ventura Road / Town Center Drive, Oxnard Boulevard / Town Center Drive, Oxnard / Wagon Wheel Road / Esplanade Drive, Oxnard / Vineyard Avenue, Oxnard / Gonzales Road, Oxnard / Cooper Road, and Rose Avenue / Fifth Street. | Install electronic blank-out signs at intersections to enhance pedestrian safety. | 388800 | 349920 | 0 | 0 | 0 | 0 | 0 | No PE | Due by 3/31/2028 | No | Not Started | State | 0
H8-07-038 | 8 | 5129095 | 7 | Oxnard | Ventura County | SCAG | VCTC | Intersections along Oxnard Blvd (at Fourth St, Seventh St & Date St) and Channel Islands Blvd (at J St, Statham Blvd & Gisler Ave) and the intersection of Ventura Rd at Seventh St. | Modify traffic signals. | 2901688.23 | 2451306.56 | 2018-04-19 | 0 | 2021-05-07 | 2024-05-09 | 2451306.56 | Authorized | Authorized | No | Closed | Federal | 0
HSIP2-07-025 | 2 | 5129059 | 7 | Oxnard | Ventura County | SCAG | VCTC | Intersection Of Rose Ave. And Emerson Ave. | Upgrade Traffic Signal; Add Protected Left-Turn Phase; Install Emergency Vehicle Detention And Battery Backup System | 148571.93 | 72540 | 2010-01-26 | 0 | 2010-07-24 | 2012-02-08 | 72540 | Authorized | Authorized | No | Closed | Federal | 0
HSIP3-07-008 | 3 | 5129064 | 7 | Oxnard | Ventura County | SCAG | VCTC | Intersection Of Saviers Rd. And Hill St. | Install New Traffic Signal | 138499.28 | 124475.62 | 2010-10-21 | 0 | 2011-08-05 | 2013-06-25 | 124475.62 | Authorized | Authorized | No | Closed | Federal | 0
HSIP3-07-009 | 3 | 5129065 | 7 | Oxnard | Ventura County | SCAG | VCTC | Intersection Of Ventura Rd. And Devonshire Dr. | Modify Existing Traffic Signal And Median | 195181.81 | 151560 | 2010-11-10 | 0 | 2012-11-01 | 2014-10-17 | 151560 | Authorized | Authorized | No | Closed | Federal | 0
HSIP4-07-030 | 4 | 5129072 | 7 | Oxnard | Ventura County | SCAG | VCTC | Ventura Rd./Ninth St. | Modify traffic signals | 210742.12 | 136712.08 | 2011-11-28 | 0 | 2013-04-05 | 2015-05-08 | 136712.08 | Authorized | Authorized | No | Closed | Federal | 0
HSIP4-07-050 | 4 | 5129071 | 7 | Oxnard | Ventura County | SCAG | VCTC | Pleasant Valley Rd./Rose Ave. | Modify median for left-turn lane; modify traffic signals | 349219.34 | 238096.32 | 2011-11-17 | 0 | 2013-07-22 | 2016-01-13 | 238096.32 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-07-038 | 5 | 5129082 | 7 | Oxnard | Ventura County | SCAG | VCTC | Rice Ave./Latigo Ave. | Upgrade traffic signals (battery back up system and Emergency Vehicle Pre-emption (EVP) system); install protective protected left-turn phasing and safety lighting | 266824.16 | 166500 | 2013-05-24 | 0 | 2014-05-06 | 2023-02-08 | 166500 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-07-039 | 5 | 5129083 | 7 | Oxnard | Ventura County | SCAG | VCTC | Victoria Ave. between Gonzales Rd. and Fifth St. | Construct raised medians; install safety lighting | 1309698.76 | 960994.35 | 2013-05-24 | 0 | 2015-07-22 | 2019-11-19 | 960994.35 | Authorized | Authorized | No | Closed | Federal | 0
HSIP7-07-023 | 7 | 5129093 | 7 | Oxnard | Ventura County | SCAG | VCTC | At 5 intersections along Saviers Road, and the intersection of Oxnard Boulevard and Fifth Street in the city of Oxnard. | Install intersection lighting and convert signal to mast arm | 2160800 | 1482390 | 2016-07-20 | 0 | 2021-03-24 | 0 | 1482390 | Authorized | Authorized | No | CON | Federal
H11-07-029 | 11 | 5378051 | 7 | Palmdale | Los Angeles County | SCAG | MTA | Various locations throughout the City of Palmdale. | Conduct a City-wide signal modernization and pedestrian infrastructure replacement. Replace signal-head displays with current standards and replace pedestrian crosswalks and pedestrian buttons at crosswalks. | 6508800 | 5857920 | 2024-04-12 | 0 | 0 | 0 | 450000 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE | Federal | 2
H8-07-039 | 8 | 5378044 | 7 | Palmdale | Los Angeles County | SCAG | MTA | Intersection of Avenue S-8 at 40th Street East | Convert an existing two-way stop to a roundabout | 5249060 | 3380183 | 2017-03-21 | 2020-04-10 | 2022-03-21 | 0 | 3380183 | Authorized | Authorized | No | CON | Federal | 0
H8-07-040 | 8 | 5378043 | 7 | Palmdale | Los Angeles County | SCAG | MTA | Various unsignalized crosswalk locations throughout the City of Palmdale. | Upgrade existing unsignalized crosswalk locations with high visibility ladder crosswalks, markings and signage, and curb ramp installation. | 381149.7 | 294637.47 | 2017-03-10 | 0 | 2018-08-16 | 2020-03-30 | 294637.47 | Authorized | Authorized | No | Closed | Federal | 0
H8-07-041 | 8 | 5378045 | 7 | Palmdale | Los Angeles County | SCAG | MTA | Various locations citywide. | Upgrade guardrail and end treatments. | 452485.19 | 452485.19 | 2017-07-26 | 0 | 2018-12-27 | 2020-04-13 | 452485.19 | Authorized | Authorized | No | Closed | Federal | 0
HSIP2-07-003 | 2 | 5378024 | 7 | Palmdale | Los Angeles County | SCAG | MTA | Intersection Of Ave. R And 10Th St. East | Widen Shoulder; Construct Left-Turn Lanes; Install Left-Turn Phasing | 689755.44 | 553083.77 | 0 | 0 | 2013-03-26 | 2020-04-21 | 553083.77 | No PE | Authorized | No | Closed | Federal | 0
HSIP2-07-004 | 2 | 5378021 | 7 | Palmdale | Los Angeles County | SCAG | MTA | Sierra Hwy From Ave. M To Ave. S; Pearblossom Hwy From City Limits West Of 25Th St. To Fort Tejon Rd./Ave. T | Install Striping And Pavement Markers | 373349.99 | 331101.6 | 0 | 0 | 2011-11-08 | 2015-07-22 | 331101.6 | No PE | Authorized | No | Closed | Federal | 0
HSIP5-07-040 | 5 | 5378033 | 7 | Palmdale | Los Angeles County | SCAG | MTA | Ave. "R"/55th St. East | Install traffic signal; construct curb ramps; provide shoulder area | 501220.13 | 432685.73 | 2013-03-19 | 0 | 2014-03-05 | 2018-03-23 | 432685.73 | Authorized | Authorized | No | Closed | Federal | 0
HSIP6-07-040 | 6 | 5378037 | 7 | Palmdale | Los Angeles County | SCAG | MTA | Avenue S /30th St East | Install protected left-turn phasing and non-motorized detection | 24930 | 24930 | 2015-06-18 | 0 | 0 | 2017-07-26 | 24930 | Authorized | No CON | No | Closed | Federal | 0
HSIP6-07-040con | 6 | 5378042 | 7 | Palmdale | Los Angeles County | SCAG | MTA | Avenue S /30th St East and Technology Dr/Trade Center Dr | Install protected left-turn phasing and non-motorized detection (Avenue S /30th St East); Install traffic signal & upgrade curb ramps (Technology Dr/Trade Center Dr) | 692009.42 | 589628.98 | 0 | 0 | 2016-09-20 | 2018-03-26 | 589628.98 | No PE | Authorized | No | Closed | Federal | 0
HSIP6-07-041 | 6 | 5378036 | 7 | Palmdale | Los Angeles County | SCAG | MTA | Technology Dr/Trade Center Dr | Install traffic signal; upgrade curb ramps | 31230 | 31230 | 2015-06-18 | 0 | 0 | 2017-07-26 | 31230 | Authorized | No CON | No | Closed | Federal | 0
H8-07-042 | 8 | 5283010 | 7 | Palos Verdes Estates | Los Angeles County | SCAG | MTA | Eleven (11) locations throughout the City. | Upgrade existing metal beam guardrails to Midwest Guardrail System (MGS) standards, including new end treatments and beam sections, and relocate guardrails to correct locations. | 525000 | 332727.66 | 0 | 0 | 2020-07-17 | 2023-02-16 | 332727.66 | No PE | Authorized | No | Closed | Federal | 0
H10-07-027 | 10 | 5336023 | 7 | Paramount | Los Angeles County | SCAG | MTA | Unsignalized intersection at Alondra Boulevard and Passage Avenue. | Install traffic signal. | 331900 | 331900 | 0 | 0 | 2022-05-09 | 2024-06-07 | 331900 | No PE | Authorized | No | Closed | State | 0
H10-07-028 | 10 | 5336024 | 7 | Paramount | Los Angeles County | SCAG | MTA | Four crosswalks citywide: San Mateo St, Myrrh & Orange Ave, Jackson St and Texaco Ave, and Flower St and Passage Ave. | Upgrade 3 uncontrolled crosswalks with Rectangular Rapid Flashing Beacons (RRFBs) and 1 at Myrrh & Orange Ave with a HAWK signal. Add High visibility signing and striping, and ADA accessible curb ramps at all locations and truncated domes to the ramps at Flower t at Passage Ave. | 250000 | 250000 | 0 | 0 | 2023-09-29 | 2025-06-23 | 250000 | No PE | Authorized | No | Closed | State | 0
H11-07-030 | 11 | 5336026 | 7 | Paramount | Los Angeles County | SCAG | MTA | 15 signalized intersections on Garfield Ave, Rosecrans Ave, Somerset Blvd, and Downey Ave. | Remove and replace existing traffic signal hardware with upgraded hardware and pedestrian countdown heads. At 2 of the intersections, implement a leading pedestrian interval. | 933777 | 840400 | 0 | 0 | 2024-07-30 | 0 | 840400 | No PE | Authorized | No | CON | State | 0
H11-07-031 | 11 | 0 | 7 | Paramount | Los Angeles County | SCAG | MTA | Hunsaker Avenue between Atlantic Place and Alondra Boulevard. Intersection of Hunsaker Avenue and Atlantic Place. | Re-stripe Hunsaker Avenue to include a buffered bike lane on each side. Reconfigure the Intersection of Hunsaker Avenue and Atlantic Place to be a painted roundabout. | 275900 | 248310 | 0 | 0 | 0 | 0 | 0 | No PE | Due by 3/31/2027 | No | Not Started | State | 0
H12-07-023 | 12 | 0 | 7 | Paramount | Los Angeles County | SCAG | MTA | Garfield Avenue at Motz Street/ Monroe Street and Alondra Boulevard at Minnesota Avenue. | Install traffic signals. | 1035000 | 931500 | 0 | 0 | 0 | 0 | 0 | No PE | Due by 3/31/2028 | No | Not Started | State | 0
HSIP2-07-038 | 2 | 5336011 | 7 | Paramount | Los Angeles County | SCAG | MTA | Garfield Ave. At Peterson Ln. | Install Traffic Signals To Provide Left Turns. | 144285.5 | 129856.95 | 0 | 0 | 2009-12-04 | 2011-11-21 | 129856.95 | No PE | Authorized | No | Closed | Federal | 0
H10-07-029 | 10 | 5064097 | 7 | Pasadena | Los Angeles County | SCAG | MTA | The project is at 3 locations: Glenarm St at Euclid Ave, Raymond Ave at Grandview St, and El Molino Ave and Buckeye St. | Install Rectangular Rapid Flashing Beacons (RRFBs), striping and signs. | 248700 | 248700 | 2021-11-17 | 0 | 2023-10-12 | 2025-09-16 | 248700 | Authorized | Authorized | No | Closed | State | 0
H10-07-030 | 10 | 5064096 | 7 | Pasadena | Los Angeles County | SCAG | MTA | Various intersections along 8 corridors Colorado Blvd, Lake Ave, Fair Oaks Ave, Los Robles Ave, Marengo Ave, Walnut St, Washington Blvd, and Lincoln Ave and selected intersections for a total of 70 Intersections | The project will involve the removal and replacement of existing ped push buttons with APS buttons and the implementation of leading pedestrian intervals. | 1357500 | 1357500 | 2021-11-16 | 0 | 2023-09-19 | 2025-09-16 | 1357500 | Authorized | Authorized | No | Closed | State | 0
H11-07-032 | 11 | 5064104 | 7 | Pasadena | Los Angeles County | SCAG | MTA | The intersection of Washington Blvd and Hudson Ave. | Installation of a crosswalk with High-intensity Activated Crosswalk (HAWK) with updated curb ramps, signage, lighting and striping. | 396900 | 357210 | 0 | 0 | 2025-04-10 | 0 | 357210 | No PE | Authorized | No | CON | State | 0
H11-07-033 | 11 | 5064098 | 7 | Pasadena | Los Angeles County | SCAG | MTA | Green St at Michigan Ave and Green St at Chester Ave intersections. | Installation of rapid rectangular flashing beacon with updated curb ramps, signage, lighting and striping. | 276800 | 249120 | 2023-09-12 | 0 | 0 | 0 | 18000 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE | State | 0
H11-07-034 | 11 | 5064099 | 7 | Pasadena | Los Angeles County | SCAG | MTA | Fair Oaks ave, Walnut St, Lake Ave, Glenarm St, California Blvd, and Washington Blvd corridors and selected intersections. | Installation of reflective backplate and near side signal heads. | 441900 | 397710 | 2023-09-12 | 0 | 0 | 0 | 37800 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE | State | 0
H12-07-024 | 12 | 5064107 | 7 | Pasadena | Los Angeles County | SCAG | MTA | Intersections of Villa St at Chester Ave, Arroyo Blvd at Seco St, and Bellefontaine St at Fairmount Ave. | Install rectangular rapid flashing beacons (RRFBs) with updated curb ramps, signage, lighting and striping. | 360700 | 324630 | 2025-12-19 | 0 | 0 | 0 | 34200 | Authorized | Due by 3/31/2028 | No | PE | State | 0
H12-07-025 | 12 | 5064106 | 7 | Pasadena | Los Angeles County | SCAG | MTA | Union Street between Arroyo Parkway and St John Avenue. | Install a new half mile east-west bike facility creating a new connection to the Old Pasadena business district. | 317200 | 285480 | 2025-12-18 | 0 | 0 | 0 | 52650 | Authorized | Due by 3/31/2028 | No | PE | State | 0
H8-07-043 | 8 | 5064084 | 7 | Pasadena | Los Angeles County | SCAG | MTA | Intersections of Lake Ave/Orange Grove Blvd, Mountain Street-Seco Street/Lincoln Avenue, and Lincoln Avenue/Forest Avenue. | Modify traffic signal to install Left-turn signals, install corner curb extension, install left-turn pockets, modify striping to simplify movements and minimize conflicts, install enhanced signage, and additional signal heads. | 789535.71 | 599040 | 2017-06-20 | 0 | 2018-11-06 | 2020-11-06 | 599040 | Authorized | Authorized | No | Closed | Federal | 0
H9-07-019 | 9 | 5064095 | 7 | Pasadena | Los Angeles County | SCAG | MTA | Various Locations throughout the west side of the City. | Repair existing damaged guardrail. | 348050.35 | 288999.99 | 0 | 0 | 2022-02-04 | 2023-10-26 | 288999.99 | No PE | Authorized | No | Closed | Federal | 0
HSIP2-07-019 | 2 | 5064063 | 7 | Pasadena | Los Angeles County | SCAG | MTA | Intersection Of Los Robles Ave. And Union St. | Install Protected/Permissive Left-Turn Traffic Signals | 112841.28 | 67956.52 | 2010-02-12 | 0 | 2011-08-23 | 2018-04-16 | 67956.52 | Authorized | Authorized | No | Closed | Federal | 0
HSIP2-07-020 | 2 | 5064064 | 7 | Pasadena | Los Angeles County | SCAG | MTA | Intersection Of Washington Blvd. And Hill St. | Install Protected/Permissive Left-Turn Traffic Signals | 160527.01 | 91274.53 | 2010-01-26 | 0 | 2011-08-23 | 2018-04-16 | 91274.53 | Authorized | Authorized | No | Closed | Federal | 0
HSIP4-07-003 | 4 | 5064075 | 7 | Pasadena | Los Angeles County | SCAG | MTA | Pasadena Ave./SR 210 WB on-ramp at Walnut St. | Upgrade traffic signals; install flashing beacons | 161821.96 | 97999.18 | 2012-12-18 | 0 | 2016-02-12 | 2018-03-26 | 97999.18 | Authorized | Authorized | No | Closed | Federal | 0
HSIP4-07-012 | 4 | 5064093 | 7 | Pasadena | Los Angeles County | SCAG | MTA | Fair Oaks Ave./Colorado Blvd.; Lake Ave./Mountain St. | Install pedestrian bulb-outs and curb ramps; enhance striping | 945384.59 | 602200 | 0 | 0 | 2020-01-27 | 2023-05-16 | 602200 | No PE | Authorized | No | Closed | Federal | 0
HSIP4-07-032 | 4 | 5064076 | 7 | Pasadena | Los Angeles County | SCAG | MTA | SR 134 on/off-ramp at Colorado Blvd./Orange Grove Blvd.; SR 210 on/off-ramp at Holly St./Orange Grove Blvd. | Modify traffic signal phasing | 489020.02 | 227687.84 | 2013-01-07 | 0 | 2016-06-09 | 2018-05-01 | 227687.84 | Authorized | Authorized | No | Closed | Federal | 0
H11-07-035 | 11 | 5351043 | 7 | Pico Rivera | Los Angeles County | SCAG | MTA | All streets and roadways throughout the City of Pico Rivera. | Conduct a roadway safety and signing audit (RSSA) and implement a roadway sign replacement project (per MUTCD standards) based on the results of the RSSA. | 2821300 | 2539170 | 2023-09-15 | 0 | 0 | 0 | 360000 | Authorized | Due by 3/31/2027 | No | PE | State | 0
H11-07-036 | 11 | 5351045 | 7 | Pico Rivera | Los Angeles County | SCAG | MTA | 47 Signalized Intersections along Multiple Roadway Segments. | Improve signal hardware, install pedestrian countdown signal heads, and install advance stop bar before crosswalk (Bicycle Box). | 2130800 | 1917720 | 2023-11-17 | 0 | 0 | 0 | 324000 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE | Federal | 2
H11-07-037 | 11 | 5351044 | 7 | Pico Rivera | Los Angeles County | SCAG | MTA | Various locations encompassing 18 pedestrian school crossings at 12 schools (17 locations at intersections and 1 mid-block location). | Improve 18 pedestrian school crossings with either improved school crossing signage, installation of rectangular rapid flashing beacons (RRFBs), or LED enhanced signage as well as adding advance limit lines and signage. | 275000 | 247500 | 2023-09-15 | 0 | 0 | 0 | 28800 | Authorized | Due by 3/31/2027 | No | PE | State | 0
H12-07-026 | 12 | 5351049 | 7 | Pico Rivera | Los Angeles County | SCAG | MTA | Eleven (11) signalized Intersections and one roadway segment: Paramount Blvd from Goodbee St to Unser St. | Add left turn phase, convert pedestal mounted signal head to mast arms, and install striping through intersection; for the roadway segment: install raised median. | 2110100 | 1899090 | 2026-01-13 | 0 | 0 | 0 | 269100 | Authorized | Due by 3/31/2028 | No | PE | Federal | 0
H12-07-027 | 12 | 5351048 | 7 | Pico Rivera | Los Angeles County | SCAG | MTA | Eight (8) school crossings: 1. Sideview Dr & Shade Ln; 2. Orange Ave & Shade Ln; 3. Orange Ave & Homestead; 4. Orange Ave & Maxine St; 5. Durfee Ave at North Park Acedemy of Arts Driveway; 6. Serapis Ave & Aero Dr; 7. Serapis Ave & La Docena; and 8. Serapis Ave & Terrradel St. | Install safety improvements including crossing signage & striping, rectangular rapid flashing beacons (RRFBs), LED enhanced signage, and ADA improvements. | 388800 | 349920 | 2025-12-16 | 0 | 0 | 0 | 61200 | Authorized | Due by 3/31/2028 | No | PE | State | 0
H8-07-044 | 8 | 5351035 | 7 | Pico Rivera | Los Angeles County | SCAG | MTA | Intersections of Washington Blvd/Crossway Drive, Paramount Blvd/Beverly Blvd, Whittier Blvd/Lindsey Ave, Rosemead Blvd/Gallatin Rd, and Paramount Blvd/Rex Road. | Install improved signal hardware (three intersections); and convert pedestal-mounted to signal mast arms (two intersections). | 1231380.16 | 696300 | 2018-01-29 | 0 | 2020-09-11 | 2024-03-28 | 696300 | Authorized | Authorized | No | Closed | Federal | 0
HSIP2-07-005 | 2 | 5351022 | 7 | Pico Rivera | Los Angeles County | SCAG | MTA | Downey Telegraph Rd. Between Lakewood Blvd. / Rosemead Blvd. And Passons Blvd. | Construct Raise Median. | 2272320.73 | 900000 | 0 | 0 | 2012-05-31 | 2015-01-09 | 900000 | No PE | Authorized | No | Closed | Federal | 0
HSIP4-07-045 | 4 | 5351023 | 7 | Pico Rivera | Los Angeles County | SCAG | MTA | Various locations throughout the city | Install left-turn phasing, pedestrian countdown heads, and speed feedback signs | 1983431.49 | 889100 | 2012-01-06 | 0 | 2014-04-29 | 2016-05-09 | 889100 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-07-041 | 5 | 5351031 | 7 | Pico Rivera | Los Angeles County | SCAG | MTA | Paramount Blvd. between Mines Ave. and Whittier Blvd. | Construct raised medians and bulb-outs | 1262839.17 | 832921.97 | 0 | 0 | 2016-04-27 | 2019-11-19 | 832921.97 | No PE | Authorized | No | Closed | Federal | 0
HSIP6-07-042 | 6 | 5351030 | 7 | Pico Rivera | Los Angeles County | SCAG | MTA | Whittier Blvd/Paramount Blvd, Paramount Blvd/Washington Blvd, Slauson Ave/Paramount Blvd, Rosemead Blvd/Slauson Ave; On Washington Blvd between Rio Hondo River and Paramount Blvd | Upgrade traffic signals; Construct sidewalks | 953153.17 | 841556 | 2015-03-26 | 0 | 2016-09-16 | 2020-02-20 | 841556 | Authorized | Authorized | No | Closed | Federal | 0
HSIP7-07-024 | 7 | 5351037 | 7 | Pico Rivera | Los Angeles County | SCAG | MTA | A total of 19 high capacity intersections located along Beverly Boulevard, Paramount Boulevard, Rosemead Boulevard, Slauson Avenue and Whittier Boulevard in the City of Pico Rivera | Install signal hardware (12" LED lenses, backplates, signal timing/emergency vehicle preemption upgrades) & pedestrian countdown signal heads | 1207003 | 853100 | 0 | 0 | 2020-09-18 | 2024-02-28 | 853100 | No PE | Authorized | No | Closed | Federal
H8-07-045 | 8 | 5070034 | 7 | Pomona | Los Angeles County | SCAG | MTA | Intersections of Towne Avenue and Philadelphia Street, Garey Avenue and Rio Rancho Road/Philadelphia Street. | Modify two existing traffic signals to provide protected left turn phases. | 569397.27 | 547857.97 | 2017-12-02 | 0 | 2020-12-21 | 2023-11-06 | 547857.97 | Authorized | Authorized | No | Closed | Federal | 0
H9-07-020 | 9 | 5070037 | 7 | Pomona | Los Angeles County | SCAG | MTA | Various signalized intersections throughout the City of Pomona. | Install pedestrian countdown heads. | 136437.1 | 136437.1 | 2020-01-27 | 0 | 2022-01-18 | 2025-01-07 | 136437.1 | Authorized | Authorized | No | Closed | Federal | 0
HSIP3-07-006 | 3 | 5070025 | 7 | Pomona | Los Angeles County | SCAG | MTA | Intersection Of Monroe St. And Orange Grove Ave. | Construct New Sidewalks | 134759.52 | 101868.23 | 2010-08-14 | 0 | 2012-04-13 | 2015-04-27 | 101868.23 | Authorized | Authorized | No | Closed | Federal | 0
HSIP4-07-042 | 4 | 5070027 | 7 | Pomona | Los Angeles County | SCAG | MTA | Phillips Blvd.; La Verne Ave.; Hamilton Blvd.; Lexington Ave. | Construct sidewalk; modify traffic signals; install crosswalk improvements and speed feedback signs | 1000493.42 | 900000 | 2011-11-29 | 0 | 2013-11-27 | 2016-03-15 | 900000 | Authorized | Authorized | No | Closed | Federal | 0
H10-07-031 | 10 | 5413018 | 7 | Rancho Palos Verdes | Los Angeles County | SCAG | MTA | Palos Verdes Drive East between Palos Verdes Drive South and Palos Verdes Drive North. | Upgrade approx. 4,400 linear feet of guardrails. | 1000000 | 1000000 | 2024-12-16 | 0 | 0 | 0 | 88100 | Authorized | Past due (due 3/30/2026) | Yes (CON) | PE | State | 0
HSIP1-07-014 | 1 | 5413008 | 7 | Rancho Palos Verdes | Los Angeles County | SCAG | MTA | Intersection Of Crenshaw Blvd. And Crestridge Road. | Upgrade Traffic Signal; Install Protected Left-Turn Phasing; Upgrade Pedestrian Facilities. | 188113.02 | 161888.25 | 2008-07-08 | 0 | 2010-05-06 | 2012-11-02 | 161888.25 | Authorized | Authorized | No | Closed | Federal | 0
HSIP2-07-041 | 2 | 5413011 | 7 | Rancho Palos Verdes | Los Angeles County | SCAG | MTA | Palos Verdes Drive East From Palos Verdes Drive South To North City Limit | Upgrade Guardrail And Install New Guardrail; Install Signs | 178974.65 | 143921.65 | 0 | 0 | 2012-10-26 | 2018-08-07 | 143921.65 | No PE | Authorized | No | Closed | Federal | 0
HSIP4-07-053 | 4 | 5413014 | 7 | Rancho Palos Verdes | Los Angeles County | SCAG | MTA | Hawthorne Blvd./Highridge Rd.; Hawthorne Blvd./Gran Via Altamira (Ridgegate Dr.); Hawthorne Blvd./Eddinghill (Seamount Dr.); Hawthorne Blvd./Crest Rd.; Hawthorne Blvd./Dupre Dr.; Hawthorne Blvd./Vallon Dr.; Hawthorne Blvd./Palos Verdes Dr. West | Install pedestrian countdown heads; synchronize traffic signals | 1072171.41 | 707000 | 2011-10-25 | 0 | 2015-08-10 | 2019-09-13 | 707000 | Authorized | Authorized | No | Closed | Federal | 0
H11-07-038 | 11 | 5349014 | 7 | Rolling Hills Estates | Los Angeles County | SCAG | MTA | Four pedestrian crosswalks on Drybank Drive and Deep Valley Drive. | Install bulb-outs, RRFBs, and high-visibility signing and striping. | 293500 | 250000 | 2023-11-27 | 0 | 2025-04-15 | 0 | 250000 | Authorized | Authorized | No | CON | State | 0
H11-07-039 | 11 | 5349015 | 7 | Rolling Hills Estates | Los Angeles County | SCAG | MTA | Rolling Hills Road between Palos Verdes Drive North and North City Limits. | Widen both sides of Rolling Hills Road to install bike lanes. | 450000 | 250000 | 0 | 0 | 0 | 0 | 0 | No PE | Due by 3/31/2027 | No | Not Started | State | 0
H11-07-040 | 11 | 5349016 | 7 | Rolling Hills Estates | Los Angeles County | SCAG | MTA | 7 guardrail segments: 2 sections on Silver Spur Road; 2 sections on Hawthorne Boulevard; 1 section on Ranchview Road; and 2 sections on Palos Verdes Drive East. | Guardrail and end treatment upgrades. | 1111400 | 1000000 | 2023-12-12 | 0 | 0 | 0 | 176153 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE | State | 0
H12-07-028 | 12 | 5358022 | 7 | Rosemead | Los Angeles County | SCAG | MTA | 40 signalized intersections citywide. | Install retro-reflective backplates, pedestrian countdown signal heads, and leading pedestrian interval (LPI). | 2858200 | 2572380 | 2026-01-02 | 0 | 0 | 0 | 182520 | Authorized | Due by 3/31/2028 | No | PE | Federal | 0
HSIP4-07-047 | 4 | 5358014 | 7 | Rosemead | Los Angeles County | SCAG | MTA | Garvey Blvd.; Walnut Grove Ave. between Hellman Ave. and Marshall St. | Install left-turn phasing, signs, and striping; upgrade traffic signals; construct raised medians | 545680.02 | 339499.97 | 2012-08-27 | 0 | 2015-04-06 | 2017-10-11 | 339499.97 | Authorized | Authorized | No | Closed | Federal | 0
HSIP7-07-025 | 7 | 5358019 | 7 | Rosemead | Los Angeles County | SCAG | MTA | At the intersection of Mission Dr/Ivar Ave. | Install pedestrian HAWK system | 116654 | 116654 | 0 | 0 | 2018-08-11 | 2020-11-06 | 116654 | No PE | Authorized | No | Closed | Federal
H8-07-046 | 8 | 5202019 | 7 | San Fernando | Los Angeles County | SCAG | MTA | Nine (9) intersections along the Metrolink rail corridor (1st St at Hubbard Ave & Maclay Avenue; San Fernando Rd at Brand Blvd, Hubbard Ave & Maclay Ave; and Truman St at Brand Blvd, Hubbard Ave, Maclay Ave & Wolfskill St). | Install larger signal heads, additional street lighting, and protected left turn phase signals where left turn lanes already exist. | 1721300 | 1549170 | 0 | 0 | 2023-06-26 | 0 | 1549104 | No PE | Authorized | No | CON | Federal | 0
HSIP2-07-007 | 2 | 5202017 | 7 | San Fernando | Los Angeles County | SCAG | MTA | Various Locations | Install Count Down Pedestrian Heads. | 66215.22 | 55710 | 0 | 0 | 2015-09-16 | 2018-03-29 | 55710 | No PE | Authorized | No | Closed | Federal | 0
HSIP7-07-026 | 7 | 5202018 | 7 | San Fernando | Los Angeles County | SCAG | MTA | Glen Oaks Boulevard, from Hubbard St. in the west (western city limit) and Arroyo St. in east (eastern city limit) | Install protective left turn phasing at intersections, installation of raised medians at approaches, and the improvement of signal hardware | 3035720 | 917328.06 | 0 | 0 | 2019-04-15 | 2022-03-09 | 917328.06 | No PE | Authorized | No | Closed | Federal
H12-07-029 | 12 | 0 | 7 | San Gabriel | Los Angeles County | SCAG | MTA | Five (5) intersections along the San Gabriel Blvd corridor and the Las Tunas Dr. corridor, including the intersection of San Gabriel and Las Tunas. | Install delineators, reflectors and/or object markers, improve signal hardware, install raised pavement markers and striping , and modify signal phasing for leading pedestrian interval (LPI). | 121100 | 108990 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2025) | Due by 3/31/2028 | Yes (PE) | Not Started | State | 0
H8-07-047 | 8 | 5217026 | 7 | San Gabriel | Los Angeles County | SCAG | MTA | Intersection of San Gabriel Blvd and Roses Road. | Install a pedestrian actuated overhead flashing beacon with pedestrian crossing signage, curb ramps, pedestrian ahead signage, etc. | 170804.12 | 170804.12 | 2018-09-11 | 0 | 2020-12-21 | 2023-02-22 | 170804.12 | Authorized | Authorized | No | Closed | Federal | 0
HSIP7-07-027 | 7 | 5217025 | 7 | San Gabriel | Los Angeles County | SCAG | MTA | Located in the City of San Gabriel, which included 4 spot location improvements at the intersections of Las Tunas Dr/Mission Drive, Las Tunas Dr/Del Mar Ave, Las Tunas Dr/Country Club Dr, & San Gabriel Blvd/Live Oak St. | Installation of safety enhancements (ex: left turn phasing, RRFB, at existing uncontrolled crosswalks) | 845497.76 | 764955.66 | 2018-06-15 | 0 | 2020-12-18 | 2023-06-29 | 764955.66 | Authorized | Authorized | No | Closed | Federal
H10-07-032 | 10 | 5450105 | 7 | Santa Clarita | Los Angeles County | SCAG | MTA | Nine intersections near Placerita Junior High School and William S. Hart High School in the Newhall area of Santa Clarita. | Install curb extensions at one intersection, school continental crosswalks at six intersections, and upgrade existing crosswalks to school continental at two intersections. | 274600 | 250000 | 0 | 0 | 2023-02-15 | 2024-05-24 | 250000 | No PE | Authorized | No | Closed | State | 0
H11-07-041 | 11 | 5450107 | 7 | Santa Clarita | Los Angeles County | SCAG | MTA | At the intersection of Whites Canyon Road and Via Princessa. | Install pedestrian camera detection system and electronic blank-out signs at the intersection's two uncontrolled channelized right-turn lanes. | 234300 | 210870 | 2023-08-03 | 0 | 2024-02-20 | 2025-06-25 | 210870 | Authorized | Authorized | No | Closed | State | 0
H11-07-042 | 11 | 5450106 | 7 | Santa Clarita | Los Angeles County | SCAG | MTA | Kelly Johnson Loop (Kelly Johnson, Hercules St, Constellation Rd, W Rye Canyon Rd) and Golden Valley Rd (between Claremore Way and Plum Canyon Rd) approximately 2.75 miles. | Install Class II bike lanes to enhance bicycle connectivity to surrounding neighborhoods, retail, and schools | 275580 | 239815 | 2023-08-03 | 0 | 2025-04-30 | 0 | 202590 | Authorized | Authorized | No | CON | State | 0
H12-07-030 | 12 | 5450113 | 7 | Santa Clarita | Los Angeles County | SCAG | MTA | Five (5) intersections: McBean Pkwy / Magic Mountain Pkwy, McBean Pkwy / Northpark Dr, McBean Pkwy / Sunset Hills Dr, Copper Hill Dr / Decoro Dr, and Golden Valley Rd / Newhall Ranch Rd. | Install electronic blank-out signs to enhance pedestrian visibility. | 388800 | 349920 | 2025-09-02 | 0 | 0 | 0 | 36000 | Authorized | Due by 3/31/2028 | No | PE | State | 0
H12-07-031 | 12 | 5450114 | 7 | Santa Clarita | Los Angeles County | SCAG | MTA | At seven intersections along the Golden Valley Road/ Newhall Ranch Road corridor. | Install bicycle detection system and signage on trail system at seven signalized intersections to enhance bicyclist safety. | 411900 | 350000 | 2025-09-25 | 0 | 0 | 0 | 31950 | Authorized | Due by 3/31/2028 | No | PE | State | 0
H8-07-048 | 8 | 5450093 | 7 | Santa Clarita | Los Angeles County | SCAG | MTA | Soledad Canyon Road at the intersections of Oak Springs Canyon Road, Rue Entree, Flowerpark Drive, Poppy Meadow Street, and Shadow Pines Boulevard. | Replace existing permissive and protected-permissive signal traffic controls with protected left-turn phases. | 716973.03 | 619699.99 | 2017-08-23 | 0 | 2019-12-12 | 2022-02-17 | 619699.99 | Authorized | Authorized | No | Closed | Federal | 0
H8-07-049 | 8 | 5450094 | 7 | Santa Clarita | Los Angeles County | SCAG | MTA | Various locations throughout the City. | Upgrade existing guardrail and end treatments. | 1178602 | 1178602 | 2017-08-02 | 0 | 2020-03-09 | 2024-09-24 | 1178602 | Authorized | Authorized | No | Closed | Federal | 0
H9-07-021 | 9 | 5450098 | 7 | Santa Clarita | Los Angeles County | SCAG | MTA | Seven (7) intersections: McBean Pkwy/ Magic Mountain Pkwy, McBean Pkwy/ Newhall Ranch Rd, Newhall Ranch Rd/ Rye Cyn Rd, Soledad Cyn Rd/ Valley Center Dr, Golden Valley Rd/ Valley Center Dr, Via Princessa/ Whites Cyn Rd, and Copper Hill Rd/ Decoro Dr. | Install new pedestrian traffic signs, advanced yield lines, continental crosswalks, and associated pavement striping; reconstruct curb ramps for enhanced visibility. | 162720.29 | 162720.29 | 2019-09-13 | 0 | 2021-01-06 | 2022-10-26 | 162720.29 | Authorized | Authorized | No | Closed | Federal | 0
HSIP1-07-015 | 1 | 5450035 | 7 | Santa Clarita | Los Angeles County | SCAG | MTA | Intersection Of Soledad Canyon Road And Crossglade Avenue | Upgrade Pedestrian Facilities; Remove Obstructions. | 160799 | 139055.1 | 0 | 0 | 2008-12-19 | 2011-03-06 | 139055.1 | No PE | Authorized | No | Closed | Federal | 0
HSIP1-07-016 | 1 | 5450036 | 7 | Santa Clarita | Los Angeles County | SCAG | MTA | Southeast Intersection Of Mcbean Parkway And Newhall Ranch Road. | Restripe Dual Right Turn Lane To Single Lane. Relocate Existing Signal Pole And Mast Arm. | 75476 | 67927.95 | 0 | 0 | 2008-12-19 | 2012-01-04 | 67927.95 | No PE | Authorized | No | Closed | Federal | 0
HSIP2-07-044 | 2 | 5450044 | 7 | Santa Clarita | Los Angeles County | SCAG | MTA | Lyons Ave. From I-5 Northbound Ramps To 800 Feet East | Construct Raised Median | 286674.47 | 224995.16 | 0 | 0 | 2009-07-16 | 2013-03-19 | 224995.16 | No PE | Authorized | No | Closed | Federal | 0
HSIP3-07-019 | 3 | 5450063 | 7 | Santa Clarita | Los Angeles County | SCAG | MTA | Intersection Of Railroad Ave. (Formerly San Fernando Rd.) And Drayton St. | Upgrade Traffic Signal; Add Protected Left-Turn Phasing; Construct Curb Ramps | 322807.39 | 290526.65 | 0 | 0 | 2012-05-02 | 2013-10-18 | 290526.65 | No PE | Authorized | No | Closed | Federal | 0
HSIP4-07-001 | 4 | 5450070 | 7 | Santa Clarita | Los Angeles County | SCAG | MTA | Sand Canyon Rd., within 400' N and S of Silver Saddles Dr. | Install guardrail | 59286.53 | 53357.87 | 2011-10-25 | 0 | 2012-08-16 | 2013-10-18 | 53357.87 | Authorized | Authorized | No | Closed | Federal | 0
HSIP4-07-049 | 4 | 5450071 | 7 | Santa Clarita | Los Angeles County | SCAG | MTA | Various locations throughout the city | Upgrade signs, crosswalks, and pavement markings | 138933.5 | 125040.15 | 2011-10-25 | 0 | 2012-08-15 | 2013-11-13 | 125040.15 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-07-043 | 5 | 5450079 | 7 | Santa Clarita | Los Angeles County | SCAG | MTA | Golden Valley Rd./Robert C. Lee Pkwy.; Via Princessa/Vista Del Canon; Bouquet Canyon Rd./Central Park | Install protected left-turn phasing | 591616.67 | 485499.65 | 0 | 0 | 2014-01-23 | 2016-04-11 | 485499.65 | No PE | Authorized | No | Closed | Federal | 0
HSIP5-07-044 | 5 | 5450081 | 7 | Santa Clarita | Los Angeles County | SCAG | MTA | Newhall Ave./8th St.; Newhall Ave./9th St.; Newhall Ave./Lyons Ave. | Construct bulb-outs; install crosswalks | 392092.72 | 324900 | 2013-04-17 | 0 | 2014-08-26 | 2016-11-15 | 324900 | Authorized | Authorized | No | Closed | Federal | 0
HSIP6-07-043 | 6 | 5450085 | 7 | Santa Clarita | Los Angeles County | SCAG | MTA | Orchard Village Rd/Wiley Canyon Rd, Seco Canyon Rd/Pamplico Dr, Soledad Canyon Rd/SR14 Southbound Ramps (Sand Canyon Rd. Exit 9) | Upgrade traffic signals; Install protected left-turn phasing | 1219875.23 | 763878 | 0 | 0 | 2017-01-13 | 2019-08-22 | 763878 | No PE | Authorized | No | Closed | Federal | 0
HSIP6-07-044 | 6 | 5450084 | 7 | Santa Clarita | Los Angeles County | SCAG | MTA | On Sand Canyon Rd south of Alamo Canyon Dr, On Via Princessa east of Whites Canyon Rd | Install guardrail | 132466.5 | 132466.5 | 0 | 0 | 2015-07-28 | 2018-01-18 | 132466.5 | No PE | Authorized | No | Closed | Federal | 0
HSIP7-07-028 | 7 | 5450091 | 7 | Santa Clarita | Los Angeles County | SCAG | MTA | Intersections of Copper Hill Drive/Copperstone Drive, Copper Hill Drive/Camino del Arte Drive, and Soledad Canyon Road/Gailxy Avenue in the City of Santa Clarita | Modify intersections, including revising existing raised medians on major streets to create directional openings to restrict left-turns from the minor street, and provide for circulation changes. | 243885.58 | 219493.78 | 0 | 0 | 2017-08-21 | 2021-04-16 | 219493.78 | No PE | Authorized | No | Closed | Federal
HSIP7-07-029 | 7 | 5450092 | 7 | Santa Clarita | Los Angeles County | SCAG | MTA | Intersection of Seco Canyon Road and Garzota Drive in the City of Santa Clarita | Modify existing signal traffic controls to provide protected left-turn phase for northbound and southbound left-turn movements. | 205680.1 | 200800 | 0 | 0 | 2017-08-02 | 2019-12-11 | 200800 | No PE | Authorized | No | Closed | Federal
H12-07-032 | 12 | 5107057 | 7 | Santa Monica | Los Angeles County | SCAG | MTA | At the intersection of Lincoln Boulevard and Hill Street (north approach). | Install pedestrian signal on the north approach of the intersection. | 421500 | 350000 | 2025-10-02 | 0 | 0 | 0 | 22712 | Authorized | Due by 3/31/2028 | No | PE | State | 0
H12-07-033 | 12 | 5107058 | 7 | Santa Monica | Los Angeles County | SCAG | MTA | All signalized intersections along Neilson Way from Ocean Park Boulevard to Pico Boulevard. | Install retroreflective backplates, leading pedestrian interval, and protected left turns. | 891300 | 802170 | 2025-10-02 | 0 | 0 | 0 | 51660 | Authorized | Due by 3/31/2028 | No | PE | State | 0
H12-07-035 | 12 | 5107059 | 7 | Santa Monica | Los Angeles County | SCAG | MTA | 23rd St & Hill Street and unsignalized intersections along Ocean Avenue and Colorado Avenue. | Install rectangular rapid flashing beacons (RRFBs), curb extensions and pedestrian crossing striping. | 1359600 | 1223640 | 2025-10-23 | 0 | 0 | 0 | 78480 | Authorized | Due by 3/31/2028 | No | PE | Federal | 2
H12-07-036 | 12 | 5262012 | 7 | Signal Hill | Los Angeles County | SCAG | MTA | 11 signalized intersections. | Upgrades signals to provide protected left turn phasing at 8 intersections, upgrade signal visibility at 3 signals, and provide pedestrian countdown heads. | 3022200 | 2719980 | 2025-07-25 | 0 | 0 | 0 | 180000 | Authorized | Due by 3/31/2028 | No | PE | Federal | 0
H12-07-037 | 12 | 5262013 | 7 | Signal Hill | Los Angeles County | SCAG | MTA | Willow Street from California Avenue to Temple Avenue and Cherry Avenue from Spring Street to 20th Street. | Install signal coordination, signal head improvements, pedestrian countdown heads and signs. | 2164900 | 1082450 | 2025-07-15 | 0 | 0 | 0 | 152500 | Authorized | Due by 3/31/2028 | No | PE | State | 0
HSIP4-07-046 | 4 | 5262007 | 7 | Signal Hill | Los Angeles County | SCAG | MTA | Cherry Ave./20th St. | Install traffic signals; construct curb ramps | 309524.23 | 278477.37 | 2011-08-02 | 0 | 2012-06-25 | 2016-03-04 | 278477.37 | Authorized | Authorized | No | Closed | Federal | 0
H10-07-033 | 10 | 5405092 | 7 | Simi Valley | Ventura County | SCAG | VCTC | 30 major signalized intersections on Alamo Street, Cochran Street, Easy Street, Los Angeles Avenue, Madera Road, Royal Avenue and Wood Ranch Parkway. | Replace seventy-eight (78) 8"-section signal heads with 12"-section signal heads and install high visibility retroreflective tape on 448 signal heads. | 486500 | 157700 | 0 | 0 | 2022-10-03 | 2025-03-12 | 157700 | No PE | Authorized | No | Closed | State | 0
H11-07-043 | 11 | 5405100 | 7 | Simi Valley | Ventura County | SCAG | VCTC | Cochran Street at Erringer Road, Royal Avenue at Erringer Road, Royal Avenue at First Street. | Install new Left-Turn Phasing and associated equipment with high-visibility signal head backplates and advanced traffic signal controllers. | 960000 | 864000 | 0 | 0 | 2023-12-19 | 0 | 864000 | No PE | Authorized | No | CON | State | 0
H12-07-038 | 12 | 5405106 | 7 | Simi Valley | Ventura County | SCAG | VCTC | At 91 signalized intersections citywide. | Install retroreflective yellow tape on signal heads. | 1098600 | 988740 | 0 | 0 | 2025-12-17 | 0 | 988740 | No PE | Authorized | No | CON | State | 0
HSIP2-07-008 | 2 | 5405059 | 7 | Simi Valley | Ventura County | SCAG | VCTC | Los Angeles Ave. At Erringer Rd., Sycamore Dr., Sequoia Ave., Tapo Canyon Rd., And Tapo St. | Install Illuminated "No Left Turn" And "No Right Turn" Signs For Railroad Preemption. | 42201 | 37980.9 | 0 | 0 | 2011-06-09 | 2013-11-07 | 37980.9 | No PE | Authorized | No | Closed | Federal | 0
HSIP4-07-010 | 4 | 5405069 | 7 | Simi Valley | Ventura County | SCAG | VCTC | Various locations throughout the city | Upgrade signs | 189345.7 | 170411.13 | 2012-07-18 | 0 | 2014-03-27 | 2016-03-29 | 170411.13 | Authorized | Authorized | No | Closed | Federal | 0
HSIP6-07-045 | 6 | 5405083 | 7 | Simi Valley | Ventura County | SCAG | VCTC | On the north side of Alamo St west of Gage Ave | Install bike lanes; Widen roadway; upgrade curb, gutter, sidewalk, curb ramp, driveway, street light, water valve, pavement and utilities | 368059.28 | 363666.69 | 2015-04-16 | 0 | 2016-06-14 | 2018-03-09 | 363666.69 | Authorized | Authorized | No | Closed | Federal | 0
H10-07-034 | 10 | 5352021 | 7 | South El Monte | Los Angeles County | SCAG | MTA | Various signalized intersections throughout the City. | Install left turn phasing at signalized locations with existing left turn pockets, and install signal hardware improvements to the lenses, back-plates with retroreflective borders. | 653000 | 653000 | 2021-11-10 | 0 | 2024-01-31 | 0 | 653000 | Authorized | Authorized | No | CON | State | 0
H11-07-044 | 11 | 5352025 | 7 | South El Monte | Los Angeles County | SCAG | MTA | 21 signalized intersections citywide. | Install raised pavements markers; install crosswalks; implement LPI. | 707800 | 637020 | 2024-02-22 | 0 | 2024-10-25 | 0 | 637020 | Authorized | Authorized | No | CON | State | 0
H9-07-022 | 9 | 5352020 | 7 | South El Monte | Los Angeles County | SCAG | MTA | various signalized intersections throughout the City. | Install signal hardware improvements to the lenses, back-plates with retroreflective borders, mounting, size, and number, as well as installation of pedestrian countdown signal heads. | 551300 | 515555.17 | 2019-10-23 | 0 | 2023-08-04 | 2025-06-13 | 515555.17 | Authorized | Authorized | No | Closed | Federal | 0
HSIP6-07-046 | 6 | 5352014 | 7 | South El Monte | Los Angeles County | SCAG | MTA | Thienes Ave/Tyler Ave | Install traffic signals | 399955.95 | 341276.69 | 2014-09-03 | 0 | 2017-02-27 | 2021-06-15 | 341276.69 | Authorized | Authorized | No | Closed | Federal | 0
HSIP6-07-047 | 6 | 5352015 | 7 | South El Monte | Los Angeles County | SCAG | MTA | Durfee Ave/Thienes Ave | Upgrade traffic signals and Install protected left-turn phasing | 335258.55 | 331258.55 | 2014-09-09 | 0 | 2016-09-19 | 2020-01-15 | 331258.55 | Authorized | Authorized | No | Closed | Federal
HSIP6-07-048 | 6 | 5352016 | 7 | South El Monte | Los Angeles County | SCAG | MTA | Santa Anita Ave/Fern St-Elliott Ave | Install traffic signals | 418362.69 | 325404 | 2014-09-03 | 0 | 2017-02-27 | 2021-08-26 | 325404 | Authorized | Authorized | No | Closed | Federal
HSIP6-07-049 | 6 | 5352017 | 7 | South El Monte | Los Angeles County | SCAG | MTA | Peck Rd/E Ruch St | Upgrade traffic signals; Install protected left-turn phasing | 697029.86 | 594157.74 | 2014-09-09 | 0 | 2017-05-22 | 2022-06-13 | 594157.74 | Authorized | Authorized | No | Closed | Federal
HSIP7-07-030&031&032 | 7 | 5352019 | 7 | South El Monte | Los Angeles County | SCAG | MTA | The intersections of Santa Anita Avenue with Klingerman Street, Rush Street, and Central Avenue | Provide protected left turn phases at all three intersections; convert signals to mast arms on the Klingerman Street approaches at the Santa Anita Avenue and Klingerman Street intersection. | 937116 | 843403.11 | 2017-02-27 | 0 | 2021-01-06 | 2023-06-28 | 843403.11 | Authorized | Authorized | No | Closed | Federal
H10-07-035 | 10 | 5257040 | 7 | South Gate | Los Angeles County | SCAG | MTA | 7 intersections including Southern Ave & Victoria Ave, Southern Ave & Elizabeth Ave, Southern Ave & Kauffman Ave, California Ave & Duane Way, California Ave & Michigan Ave, California Ave & Tenaya Ave, and California Ave & Santa Ana St. | Install enhanced crosswalk features at 6 uncontrolled crosswalks, and install protected left-turn phasing at 1 signalized intersection. | 1761300 | 1761300 | 2021-12-27 | 0 | 2025-10-10 | 0 | 1761300 | Authorized | Authorized | No | CON | State | 0
H10-07-036 | 10 | 0 | 7 | South Gate | Los Angeles County | SCAG | MTA | Four uncontrolled crosswalks at Tweedy Boulevard and Virginia Avenue, Tweedy Boulevard and San Antonio Avenue, Tweedy Boulevard and Washington Avenue, Tweedy Boulevard and Walnut Avenue. | Upgrade 4 uncontrolled crosswalks with enhanced crosswalk features including rectangular rapid flashing beacons, high visibility signing and striping, and ADA curb ramps. | 250000 | 250000 | 0 | 0 | 0 | 0 | 0 | No PE | Past due (due 9/30/2024) | Yes (CON) | Not Started | State | 0
H11-07-045 | 11 | 5257043 | 7 | South Gate | Los Angeles County | SCAG | MTA | Atlantic Ave & Southern Pl, Firestone Blvd & Alexander Ave, Firestone Blvd & Garfield Ave, Firestone Blvd & Santa Fe Ave, Firestone Blvd & San Juan Ave, Garfield Ave & El Paseo, and Garfield Ave & Garfield Pl (a total of 7 intersections). | Install safety countermeasures including upgrades to signal hardware, leading pedestrian intervals, raised median to restrict left turns, protected left turn phases, and high visibility crosswalks with advance limit line. | 1059000 | 953100 | 2023-11-16 | 0 | 0 | 0 | 153000 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE | State | 0
H12-07-039 | 12 | 0 | 7 | South Gate | Los Angeles County | SCAG | MTA | 8 signalized intersections on State Street between Tweedy Blvd and Santa Ana St, and Long Beach Blvd between Ardmore Ave and Kansas Ave. | Upgrade signal hardware, install mast arm, install leading pedestrian interval (LPI), and install raised median. | 1309900 | 1178910 | 0 | 0 | 0 | 0 | 0 | No PE | Due by 3/31/2028 | No | Not Started | State | 0
H12-07-040 | 12 | 0 | 7 | South Gate | Los Angeles County | SCAG | MTA | Tweedy Boulevard between Alameda Street and Victoria Avenue and California Avenue between Tweedy Boulevard and Firestone Boulevard. All 9 signalized intersections within project corridor limits. | Install fiber optic cable and conduit with communication signal gear at all 9 signalized intersections and implement leading pedestrian intervals (LPIs). | 958800 | 862920 | 0 | 0 | 0 | 0 | 0 | No PE | Due by 3/31/2028 | No | Not Started | State | 0
H8-07-050 | 8 | 5257037 | 7 | South Gate | Los Angeles County | SCAG | MTA | Long Beach Boulevard between Santa Ana Street and Tweedy Boulevard. | Construct raised center median, re-stripe roadway corridor, and adjust utilities to grade. | 1650900 | 1485810 | 2018-03-26 | 0 | 2022-05-13 | 2026-02-12 | 1485810 | Authorized | Authorized | No | Closed | Federal | 0
H9-07-023 | 9 | 5257042 | 7 | South Gate | Los Angeles County | SCAG | MTA | Various intersections throughout the City of South Gate (California Avenue and Missouri Avenue, State Street and Illinois Avenue, Southern Avenue and Madison Avenue, Otis Street and Missouri Avenue | Install crosswalk improvements including rectangular rapid flashing beacons, signing and striping upgrades to meet current standards, and upgrade pedestrian ramps to be ADA compliant. | 249780 | 249780 | 0 | 0 | 2024-05-08 | 0 | 249780 | No PE | Authorized | No | CON | Federal | 2
HSIP1-07-009 | 1 | 5257021 | 7 | South Gate | Los Angeles County | SCAG | MTA | Tweedy Blvd Between Alameda Street And Long Beach Blvd. | Construct Raised Center Medians; Modify Existing Traffic Signal; Install Ped Countdown Signals And Protected Left Turn Phasing. | 2040351.13 | 876150 | 2009-01-30 | 0 | 2011-08-30 | 2015-11-17 | 876150 | Authorized | Authorized | No | Closed | Federal | 0
HSIP2-07-032 | 2 | 5257025 | 7 | South Gate | Los Angeles County | SCAG | MTA | Firestone Blvd At Otis Str., California Ave., Long Beach Blvd. And Santa Fe. | Upgrade Traffic Signals To Include Left Turn Phases | 1063822.91 | 712798.09 | 2010-06-28 | 0 | 2013-08-14 | 2019-01-25 | 712798.09 | Authorized | Authorized | No | Closed | Federal | 0
HSIP4-07-036 | 4 | 5257029 | 7 | South Gate | Los Angeles County | SCAG | MTA | Firestone Blvd./State St.; Tweedy Blvd./California Ave. | Install protected left-turn signals, pedestrian countdown heads, curb ramps, signs, and striping | 838921.36 | 530999.99 | 2012-07-20 | 0 | 2015-03-18 | 2018-12-13 | 530999.99 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-07-045 | 5 | 5257032 | 7 | South Gate | Los Angeles County | SCAG | MTA | Imperial Hwy from LA River to the East City Limits, and the Intersection of Otis Street and Firestone Blvd | Construct raised center medians and right turn pocket/loading zone turn out | 1510426.01 | 887400 | 2015-02-06 | 0 | 2018-03-26 | 2023-04-17 | 887400 | Authorized | Authorized | No | Closed | Federal | 0
HSIP7-07-033 | 7 | 5257035 | 7 | South Gate | Los Angeles County | SCAG | MTA | On Garfield Avenue between Southern Avenue and Howery Street | Construct raised center median | 1710700 | 1539630 | 2017-11-08 | 0 | 2022-08-04 | 0 | 1539630 | Authorized | Authorized | No | CON | Federal
H11-07-046 | 11 | 0 | 7 | South Pasadena | Los Angeles County | SCAG | MTA | The intersection of Monterey Road and Fremont Avenue and the intersection of Fair Oaks Avenue and Grevelia Street south of the 110 Freeway on and off-ramps. | Improve traffic signal timing and hardware, add intersection lighting. | 64700 | 32350 | 0 | 0 | 0 | 0 | 0 | No PE | Due by 12/29/2028 | No | Not Started | State | 0
H11-07-047 | 11 | 0 | 7 | South Pasadena | Los Angeles County | SCAG | MTA | The intersection of Fremont Avenue and Huntington Drive. | Addition of bike lanes, installation of pedestrian countdown signals, and addition of lighting. | 55600 | 50040 | 0 | 0 | 0 | 0 | 0 | No PE | Due by 12/29/2028 | No | Not Started | State | 0
H11-07-048 | 11 | 0 | 7 | South Pasadena | Los Angeles County | SCAG | MTA | Fremont Avenue from Columbia Street to Monterey Road. | Add street lighting, install flashing beacons at stop-controlled intersection, install curve advance warning signs. | 307900 | 277110 | 0 | 0 | 0 | 0 | 0 | No PE | Due by 12/29/2028 | No | Not Started | State | 0
H11-07-049 | 11 | 0 | 7 | South Pasadena | Los Angeles County | SCAG | MTA | Huntington Drive from Leman Street to Maple Street. | Install bike lanes, and add street lighting. | 201400 | 181260 | 0 | 0 | 0 | 0 | 0 | No PE | Due by 12/29/2028 | No | Not Started | State | 0
HSIP6-07-050 | 6 | 5071019 | 7 | South Pasadena | Los Angeles County | SCAG | MTA | Mission St/Diamond Ave, Mission St/Fairview Ave, and Fremount Ave/Lyndon St | Upgrade crosswalks; Install in-roadway warning lights | 264962 | 238465 | 2015-05-08 | 0 | 2020-03-12 | 0 | 238465 | Authorized | Authorized | No | CON | Federal
HSIP7-07-034 | 7 | 5071020 | 7 | South Pasadena | Los Angeles County | SCAG | MTA | On Fair Oaks Avenue between Huntington Drive and Hope Street. | Improve signal timing on Fair Oaks Avenue between Huntington Drive and Hope Street. Provide software updates to existing signal controllers. Implement advance loop detection on Fair Oaks Avenue. | 594795.24 | 301020 | 2016-11-22 | 0 | 2020-09-15 | 2024-05-24 | 301020 | Authorized | Authorized | No | Closed | Federal
H12-07-041 | 12 | 5365012 | 7 | Temple City | Los Angeles County | SCAG | MTA | 27 signalized intersections citywide. | Install retro-reflective backplates, replace signal heads, and implement leading pedestrian interval (LPI). | 1568300 | 1411470 | 2025-11-13 | 0 | 0 | 0 | 113760 | Authorized | Due by 3/31/2028 | No | PE | Federal | 0
HSIP2-07-039 | 2 | 5365006 | 7 | Temple City | Los Angeles County | SCAG | MTA | Intersection Of Baldwin Ave. And Olive St.; Temple City Blvd At Las Tunas Drive. | Upgrade Traffic Signal; Install Left-Turn Phasing | 201440.84 | 181296.76 | 0 | 0 | 2010-02-10 | 2012-11-02 | 181296.76 | No PE | Authorized | No | Closed | Federal | 0
HSIP4-07-004 | 4 | 5365007 | 7 | Temple City | Los Angeles County | SCAG | MTA | Rosemead Blvd./Longden Ave.; Rosemead Blvd./Garibaldi Ave.; Rosemead Blvd./Las Tunas Dr.; Rosemead Blvd./Emperor Ave. | Install traffic signals and speed feedback signs | 613882 | 340000 | 0 | 0 | 2012-07-30 | 2016-01-19 | 340000 | No PE | Authorized | No | Closed | Federal | 0
HSIP6-07-051 | 6 | 5365010 | 7 | Temple City | Los Angeles County | SCAG | MTA | On Temple City Blvd between El Camino Real Ave and Ellis Lane, Various locations throughout Temple City | Upgrade traffic signals; signal hardware; Install pedestrian countdown heads, bike lanes, and other safety improvements | 798579.23 | 704239 | 2015-09-16 | 0 | 2016-09-19 | 2019-01-18 | 704239 | Authorized | Authorized | No | Closed | Federal
HSIP6-07-052 | 6 | 5365009 | 7 | Temple City | Los Angeles County | SCAG | MTA | Various locations throughout Temple City | Upgrade traffic signals; signs; and other safety improvements | 200836.98 | 186450.73 | 2014-09-09 | 0 | 2016-09-16 | 2018-12-11 | 186450.73 | Authorized | Authorized | No | Closed | Federal
H10-07-037 | 10 | 5392062 | 7 | Thousand Oaks | Ventura County | SCAG | VCTC | Thirty-five signalized intersections in the City of Thousand Oaks. | Install retroreflective backplates (yellow borders). | 143300 | 123300 | 0 | 0 | 2023-07-26 | 2024-12-17 | 123300 | No PE | Authorized | No | Closed | State | 0
H10-07-038 | 10 | 5392063 | 7 | Thousand Oaks | Ventura County | SCAG | VCTC | Ten intersections throughout the City. | Install RRFBs at nine existing marked crosswalks and include advanced flashing beacons; and upgrade an existing equestrian crossing equipped with flashing beacons to RRFBs, add a marked pedestrian crosswalk, and provide advanced warning beacons. | 260500 | 179000 | 0 | 0 | 2023-06-21 | 2024-12-18 | 179000 | No PE | Authorized | No | Closed | State | 0
H10-07-039 | 10 | 5392064 | 7 | Thousand Oaks | Ventura County | SCAG | VCTC | 9 segments of guardrail and their posts throughout the City. | Replace approx. 1,780 linear feet of guardrail and 88 anchor posts with new guardrail and new anchor posts. | 535500 | 512500 | 0 | 0 | 2023-04-17 | 2025-04-07 | 512500 | No PE | Authorized | No | Closed | State | 0
H11-07-050 | 11 | 5392068 | 7 | Thousand Oaks | Ventura County | SCAG | VCTC | On major arterial and collector streets throughout the City of Thousand Oaks. | Install 17 radar feedback signs. | 313300 | 258570 | 0 | 0 | 2026-02-26 | 0 | 258570 | No PE | Authorized | No | CON | State | 0
H12-07-042 | 12 | 0 | 7 | Thousand Oaks | Ventura County | SCAG | VCTC | Olsen Road at the State Route 23 undercrossing, including the State Route 23 northbound and southbound off-ramp intersections. | Install continuous bike lane striping, increase the visibility of bike conflict areas, and install eastbound bike signal phasing at the Route 23/Olsen Road northbound off-ramp. | 825800 | 653220 | 0 | 0 | 0 | 0 | 0 | No PE | Due by 3/31/2028 | No | Not Started | State | 0
H9-07-024 | 9 | 5392059 | 7 | Thousand Oaks | Ventura County | SCAG | VCTC | Thousand Oaks Blvd between Conejo School Rd and Skyline Dr. | Relocate and consolidate two existing crosswalks located on Thousand Oaks Blvd, at Live Oak St and Oakview Dr, to one single mid-block crosswalk between Live Oak St and Oakview Dr. | 1046717.5 | 704540 | 2019-11-08 | 0 | 2023-03-21 | 2026-02-26 | 704540 | Authorized | Authorized | No | Closed | Federal | 2
HSIP2-07-040 | 2 | 5392037 | 7 | Thousand Oaks | Ventura County | SCAG | VCTC | Moorpark Rd. North Of Calle Contento | Install Guardrail, Flashing Yellow Curve Warning Beacons And Signs | 168554.68 | 151699.2 | 0 | 0 | 2010-05-13 | 2014-11-26 | 151699.2 | No PE | Authorized | No | Closed | Federal | 0
HSIP5-07-047 | 5 | 5392052 | 7 | Thousand Oaks | Ventura County | SCAG | VCTC | Westlake Blvd./W Avenida de los Arboles | Extend left-turn lane; install signs and striping | 168774.77 | 151897.29 | 0 | 0 | 2015-03-18 | 2016-05-09 | 151897.29 | No PE | Authorized | No | Closed | Federal | 0
HSIP6-07-053 | 6 | 5392054 | 7 | Thousand Oaks | Ventura County | SCAG | VCTC | On Westlake Blvd (SR 23) between Ventura Freeway (SR 101) and Triunfo Rd, on SR 101 between postmile 0.70 and postmile 0.71 | Upgrade striping and curb ramps; install crosswalks; Remove trees; Construct sidewalks | 1391242.44 | 603597.46 | 2014-08-26 | 0 | 2017-12-15 | 2020-03-19 | 603597.46 | Authorized | Authorized | No | Closed | Federal
H10-07-040 | 10 | 5249033 | 7 | Torrance | Los Angeles County | SCAG | MTA | Intersection of Lomita Boulevard and Madison Street. | Install new traffic signal, including curb ramps, crosswalks, and all traffic signal equipment. | 707300 | 637800 | 0 | 0 | 2023-05-25 | 0 | 637800 | No PE | Authorized | No | CON | State | 0
H10-07-041 | 10 | 5026068 | 7 | Ventura | Ventura County | SCAG | VCTC | All signalized intersections in the City of Ventura. | Implement traffic signal coordination for 136 city-maintained intersections. Improvements include a new fiber-optic interconnect communications system that allows for consistent and reliable traffic signal coordination. | 6651310 | 4025650 | 0 | 0 | 2023-04-20 | 0 | 3325650 | No PE | Authorized | No | CON | State | 0
H10-07-042 | 10 | 5026069 | 7 | Ventura | Ventura County | SCAG | VCTC | All signalized intersections in the City of Ventura. | Install new traffic signal controllers and switches for implementation of Leading Pedestrian Intervals (LPIs). | 2270700 | 2270700 | 0 | 0 | 2023-04-21 | 0 | 1570700 | No PE | Authorized | No | CON | State | 0
H10-07-043 | 10 | 5952212 | 7 | Ventura County | Ventura County | SCAG | VCTC | Various Locations Throughout the County of Ventura. | Install Rectangular Rapid Flashing Beacons (RRFBs). | 250000 | 250000 | 0 | 0 | 2023-02-02 | 2024-05-24 | 250000 | No PE | Authorized | No | Closed | State | 0
H10-07-044 | 10 | 5952213 | 7 | Ventura County | Ventura County | SCAG | VCTC | Various Locations along Las Posas Road; Pleasant Valley Road; Potrero Road; Rose Avenue; Santa Clara Avenue; Telegraph Road; and Victoria Avenue. | Upgrade an Old Guardrail System to a Midwest Guardrail System. Upgrade the Guardrail, Terminals, and Transition railings, in addition to installing Butterfly Guardrail Reflectors. | 1000000 | 1000000 | 0 | 0 | 2022-03-09 | 2023-12-15 | 1000000 | No PE | Authorized | No | Closed | State | 0
H10-07-045 | 10 | 5952210 | 7 | Ventura County | Ventura County | SCAG | VCTC | All signalized intersection maintained by Ventura County. | Install Retroreflective Back-Plates to all signal heads, Install Advance Dilemma Zone Detection at all Intersection, and add High Friction Surface Treatment to 20 intersections with an approach speed over 35 MPH. | 7615000 | 5886360 | 2021-10-04 | 0 | 2024-03-28 | 0 | 4905300 | Authorized | Authorized | No | CON | State | 0
H10-07-046 | 10 | 5952211 | 7 | Ventura County | Ventura County | SCAG | VCTC | Balcom Canyon Road, Central Avenue, Creek Road, Foothill Road, Hueneme Road, Pleasant Valley Road, Potrero Road, Rose Avenue, and Telegraph Road. | Install edgeline and centerline rumble strips or High Friction Surface Treatment. | 3844700 | 3844700 | 2021-10-04 | 0 | 2022-06-23 | 2023-12-15 | 3844700 | Authorized | Authorized | No | Closed | State | 0
H11-07-051 | 11 | 5952230 | 7 | Ventura County | Ventura County | SCAG | VCTC | Various Locations along Center Street, Oak Hill Drive, Santa Ana Boulevard, Main Street, Violeta Street, Los Angeles Avenue, Roosevelt Boulevard, Dena Drive, Cortez Street, and North Street. | Installation of Rectangular Rapid Flashing Beacons (RRFB). | 277700 | 249930 | 0 | 0 | 2025-06-12 | 0 | 249930 | No PE | Authorized | No | CON | State | 0
H11-07-052 | 11 | 5952229 | 7 | Ventura County | Ventura County | SCAG | VCTC | Various Locations along Santa Rosa Road; Moorpark Road; Potrero Road; South Mountain Road; and Foothill Road. | Upgrade an Old Guardrail System to a Midwest Guardrail System. Upgrade the Guardrail, Terminals, and Transition railings, in addition to installing Butterfly Guardrail Reflectors. | 1111100 | 999990 | 0 | 0 | 2025-06-02 | 0 | 999990 | No PE | Authorized | No | CON | State | 0
H11-07-053 | 11 | 5952219 | 7 | Ventura County | Ventura County | SCAG | VCTC | Various rural locations (58 roads) throughout the County of Ventura. | Install edgeline and/or centerline rumble strips and/or curve warning signs, on mid-block segments of County Maintained Roadways. | 6710900 | 6039810 | 2023-08-01 | 0 | 2026-03-12 | 0 | 5387070.7 | Authorized | Authorized | No | CON | Federal | 1
H12-07-043 | 12 | 5952234 | 7 | Ventura County | Ventura County | SCAG | VCTC | The intersection of Santa Clara Avenue and Central Avenue. | Install protected left-turn signal heads/phases, relocate and install high visibility crosswalks, and convert all right-lanes to right-turn only lanes. | 555200 | 499680 | 2025-12-10 | 0 | 0 | 0 | 77400 | Authorized | Due by 3/31/2028 | No | PE | State | 0
H12-07-044 | 12 | 5952233 | 7 | Ventura County | Ventura County | SCAG | VCTC | The intersection of Las Posas Road and Laguna Road. | Install flashing beacons and daytime headlight section signage. | 110000 | 99000 | 2025-09-30 | 0 | 0 | 0 | 15030 | Authorized | Due by 3/31/2028 | No | PE | State | 0
H12-07-045 | 12 | 0 | 7 | Ventura County | Ventura County | SCAG | VCTC | Various locations throughout the County. | Install rectangular rapid flashing beacons (RRFBs) and high visibility crosswalks. | 386000 | 347400 | 0 | 0 | 0 | 0 | 0 | No PE | Due by 3/31/2028 | No | Not Started | State | 0
H8-07-051 | 8 | 5952190 | 7 | Ventura County | Ventura County | SCAG | VCTC | Pleasant Valley Road between Dodge Road and Hailes Road (East of the City of Oxnard and State Route 1). | Widen pavement and install striping to accommodate two-way left-turn lane. | 1653903.65 | 973692.17 | 2017-03-09 | 0 | 2019-12-27 | 2021-10-19 | 973692.17 | Authorized | Authorized | No | Closed | Federal | 0
H9-07-025 | 9 | 5952202 | 7 | Ventura County | Ventura County | SCAG | VCTC | The Intersection of Hueneme Road with Wood Road and the Intersection of Hueneme Road with Los Posas Road. | Installation of new traffic signals at the intersection of Hueneme Rd. & Wood Rd. & updating existing traffic signals to implement a protective left turn approach at the intersections of Hueneme Rd. & Los Posas Rd. with a traffic signal connection. | 1270705.82 | 872383 | 2019-10-22 | 0 | 2021-06-24 | 2024-04-30 | 872383 | Authorized | Authorized | No | Closed | Federal | 1
H9-07-026 | 9 | 5952200 | 7 | Ventura County | Ventura County | SCAG | VCTC | Various locations throughout the County of Ventura. | Install new and update the existing locations of horizontal alignment warning signs to meet the current standards. | 1160578.09 | 693200 | 2019-06-24 | 0 | 2021-06-24 | 2023-01-03 | 693200 | Authorized | Authorized | No | Closed | Federal | 0
H9-07-027 | 9 | 5952201 | 7 | Ventura County | Ventura County | SCAG | VCTC | Various locations throughout the County of Ventura. | Installat Rectangular Rapid Flashing Beacons (RRFBs) and pedestrian countdown signal heads. | 277103.06 | 246360 | 2019-06-24 | 0 | 2020-06-02 | 2021-10-26 | 246360 | Authorized | Authorized | No | Closed | Federal | 0
HSIP1-07-017 | 1 | 5952131 | 7 | Ventura County | Ventura County | SCAG | VCTC | West Potrero Road From Thousand Oaks City Limit To 3,500 West. | Upgrade Existing Guardrail; Reconstruct Ac Berm. | 159445 | 113385.1 | 0 | 0 | 2008-02-11 | 2010-07-24 | 113385.1 | No PE | Authorized | No | Closed | Federal | 0
HSIP2-07-046 | 2 | 5952134 | 7 | Ventura County | Ventura County | SCAG | VCTC | Intersection Of Rose Ave. And Central Ave. | Extend Left-Turn Lane; Upgrade Traffic Signal; Widen Roadway For Channelization Changes | 682150.22 | 580513.27 | 0 | 0 | 2009-04-24 | 2010-12-17 | 580513.27 | No PE | Authorized | No | Closed | Federal | 0
HSIP3-07-021 | 3 | 5952146 | 7 | Ventura County | Ventura County | SCAG | VCTC | South Lomita Ave. From Lomita Ave. To El Roblar Dr. | Construct Sidewalk And Curb Ramps | 506639.56 | 261131.04 | 0 | 0 | 2011-01-14 | 2013-01-09 | 261131.04 | No PE | Authorized | No | Closed | Federal | 0
HSIP3-07-035 | 3 | 5952150 | 7 | Ventura County | Ventura County | SCAG | VCTC | Santa Clara Ave. Between Central Ave. And Los Angeles Ave. (Sr 118) | Fill Existing Earthen Ditch; Widen Shoulder; Flatten Side Slopes | 314340.75 | 225000 | 0 | 0 | 2011-08-12 | 2013-03-26 | 225000 | No PE | Authorized | No | Closed | Federal | 0
HSIP4-07-040 | 4 | 5952158 | 7 | Ventura County | Ventura County | SCAG | VCTC | Rice Ave./Channel Islands Blvd. | Construct left-turn lane; lengthen right-turn lane and acceleration lanes; upgrade traffic signals | 458345.32 | 399275.07 | 0 | 0 | 2015-07-28 | 2017-10-18 | 399275.07 | No PE | Authorized | No | Closed | Federal | 0
HSIP4-07-052 | 4 | 5952163 | 7 | Ventura County | Ventura County | SCAG | VCTC | Rose Ave. and Central Ave. near Rio Mesa High School | Install new bus stop; construct sidewalk and curb ramps; install crosswalk | 308947.67 | 162000 | 2012-07-05 | 0 | 2012-08-25 | 2015-07-15 | 162000 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-07-048 | 5 | 5952169 | 7 | Ventura County | Ventura County | SCAG | VCTC | Santa Clara Ave./Eucalyptus Dr. | Install left-turn pocket | 184746.82 | 116950 | 2013-12-24 | 0 | 2016-08-10 | 2018-05-01 | 116950 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-07-049 | 5 | 5952175 | 7 | Ventura County | Ventura County | SCAG | VCTC | Pleasant Valley Rd./Sturgis Rd. | Install traffic signals and right-turn pocket | 517511.89 | 378000 | 0 | 0 | 2016-07-22 | 2018-03-29 | 378000 | No PE | Authorized | No | Closed | Federal | 0
HSIP6-07-054 | 6 | 5952174 | 7 | Ventura County | Ventura County | SCAG | VCTC | On Santa Clara Ave between Oxnard City limits and Friedrich Rd | Widen pavement; Construct sidewalk and curb ramps; Upgrade striping | 552321.29 | 492904.16 | 0 | 0 | 2016-09-20 | 2019-01-11 | 492904.16 | No PE | Authorized | No | Closed | Federal
HSIP6-07-055 | 6 | 5952184 | 7 | Ventura County | Ventura County | SCAG | VCTC | N Rose Ave/Simon Way | Install traffic signals | 285888.77 | 262818.55 | 0 | 0 | 2016-11-18 | 2019-03-19 | 262818.55 | No PE | Authorized | No | Closed | Federal
HSIP6-07-056 | 6 | 5952180 | 7 | Ventura County | Ventura County | SCAG | VCTC | On Santa Ana Rd between mile marker 3.81 and mile marker 5.80 | Widen and pave shoulders; install bike lanes | 842014.03 | 816800 | 0 | 0 | 2016-12-15 | 2019-04-26 | 816800 | No PE | Authorized | No | Closed | Federal
HSIP6-07-057 | 6 | 5952176 | 7 | Ventura County | Ventura County | SCAG | VCTC | N Wendy Dr/Gerald Dr | Install traffic signals | 427946.09 | 267670.76 | 0 | 0 | 2015-07-17 | 2017-02-14 | 267670.76 | No PE | Authorized | No | Closed | Federal
HSIP6-07-058 | 6 | 5952178 | 7 | Ventura County | Ventura County | SCAG | VCTC | On Santa Ana Rd between mile marker 0.19 and mile marker 1.70 | Widen and pave shoulders; install bike lanes | 875120.31 | 833075.85 | 0 | 0 | 2016-12-15 | 2019-06-20 | 833075.85 | No PE | Authorized | No | Closed | Federal
HSIP7-07-035 | 7 | 5952183 | 7 | Ventura County | Ventura County | SCAG | VCTC | The project is located in the unincorporated area of Ventura County known as the Yerba Buena Area on Yerba Buena Road, Deer Creek Road, Pacific View Road, and Cotharin Road. | Install 12,000 lf of guardrail at various locations on four roadways | 1036252.48 | 926705.93 | 2016-05-12 | 0 | 2018-12-06 | 2020-03-04 | 926705.93 | Authorized | Authorized | No | Closed | Federal
H9-07-028 | 9 | 5139014 | 7 | Vernon | Los Angeles County | SCAG | MTA | Various signalized intersections (Santa Fe, Slauson, Soto, District, and Bandini Corridors). | Upgrade traffic signal housings, backplates, visors, and framework at various intersection; Install dynamic speed warning signs along five corridors. | 251266.86 | 251266.86 | 2019-12-04 | 0 | 2023-07-11 | 2025-05-09 | 251266.86 | Authorized | Authorized | No | Closed | Federal | 0
HSIP4-07-028 | 4 | 5139012 | 7 | Vernon | Los Angeles County | SCAG | MTA | Various locations throughout the city | Install pedestrian countdown heads | 84116.68 | 75705 | 0 | 0 | 2013-01-07 | 2015-03-30 | 75705 | No PE | Authorized | No | Closed | Federal | 0
H10-07-047 | 10 | 5259030 | 7 | West Covina | Los Angeles County | SCAG | MTA | Various signalized intersections throughout the City. | Install left turn phasing at signalized locations with existing left turn pockets, and install signal hardware improvements to the lenses, back-plates with retroreflective borders. | 3184700 | 3184700 | 2022-10-04 | 0 | 2024-05-28 | 0 | 3184700 | Authorized | Authorized | No | CON | State | 0
H12-07-046 | 12 | 5259034 | 7 | West Covina | Los Angeles County | SCAG | MTA | 64 signalized intersections citywide. | Install retro-reflective backplates, replace signal heads, implement leading pedestrian interval (LPI) and provide protected left turn phasing. | 5259100 | 4733190 | 2025-10-29 | 0 | 0 | 0 | 362250 | Authorized | Due by 3/31/2028 | No | PE | Federal | 0
HSIP2-07-033 | 2 | 5259019 | 7 | West Covina | Los Angeles County | SCAG | MTA | Intersection Of Cameron Ave. And North Garvey Ave. | Install Traffic Signal With Interconnect | 203260.93 | 182934.83 | 2010-06-28 | 0 | 2011-08-29 | 2013-01-04 | 182934.83 | Authorized | Authorized | No | Closed | Federal | 0
HSIP3-07-012 | 3 | 5259020 | 7 | West Covina | Los Angeles County | SCAG | MTA | Workman Ave. At Phillips Ave. | Construct Sidewalk And Curb Ramps; Install In-Pavement Crosswalk Lights, Striping And Pavement Markings | 67450.24 | 60705.21 | 2010-06-01 | 0 | 2010-08-31 | 2012-02-28 | 60705.21 | Authorized | Authorized | No | Closed | Federal | 0
HSIP4-07-021 | 4 | 5259025 | 7 | West Covina | Los Angeles County | SCAG | MTA | Lark Ellen Ave./Puente Ave. | Install left-turn phasing | 52387.1 | 45612.95 | 0 | 0 | 2011-12-23 | 2014-03-27 | 45612.95 | No PE | Authorized | No | Closed | Federal | 0
HSIP6-07-059 | 6 | 5259027 | 7 | West Covina | Los Angeles County | SCAG | MTA | S Sunset Ave/W Francisquito Ave | Upgrade traffic signals; Install protected left-turn phasing, lighting, and pedestrian countdown head | 145228.42 | 132380.35 | 2016-02-10 | 0 | 2017-01-07 | 2019-01-15 | 132380.35 | Authorized | Authorized | No | Closed | Federal
H10-07-048 | 10 | 5440010 | 7 | West Hollywood | Los Angeles County | SCAG | MTA | Along Sunset Bl, Fountain Ave, Doheny Dr, La Cienega Bl, Harper Ave, Fairfax Ave, and La Brea Ave. | Update signal timing for 34 signalized intersections; install a fiber optic system loop to connect traffic signals along 7 corridors; implement LPI timing on 34 signalized intersections; and install retroreflective backplates on 34 signals. | 5849400 | 2924700 | 2021-05-14 | 0 | 2022-10-31 | 0 | 2924700 | Authorized | Authorized | No | CON | State | 0
HSIP2-07-010 | 2 | 5431007 | 7 | Westlake Village | Los Angeles County | SCAG | MTA | Citywide | Upgrade Pedestrian Heads To Count Down Pedestrian Heads And Provide Crosswalks. | 65071.04 | 58563.93 | 0 | 0 | 2013-12-16 | 2015-05-08 | 58563.93 | No PE | Authorized | No | Closed | Federal | 0
H8-07-053 | 8 | 5111067 | 7 | Whittier | Los Angeles County | SCAG | MTA | Forty (40) signalized intersections within the City of Whittier. | Install LED countdown pedestrian heads, Accessible Pedestrian Signals (APS) with ADA compliant push buttons. | 365427.16 | 325377.45 | 0 | 0 | 2018-12-14 | 2021-10-26 | 325377.45 | No PE | Authorized | No | Closed | Federal | 0
H8-07-054 | 8 | 5111068 | 7 | Whittier | Los Angeles County | SCAG | MTA | La Serna Drive from Whittier Boulevard (State Route 72) to Youngwood Drive adjacent to La Serna High School. | Construct new sidewalks and ADA compliant wheelchair access ramps; install new centerline striping, Class II Bike Lanes, Sharrow pavement markings & Signing. | 288621.66 | 220600 | 0 | 0 | 2020-09-14 | 2022-07-26 | 220600 | No PE | Authorized | No | Closed | Federal | 0
H8-07-055 | 8 | 5111069 | 7 | Whittier | Los Angeles County | SCAG | MTA | 7 various locations of guard rails within the City of Whittier. | Upgrade guardrails. | 450090 | 363000 | 0 | 0 | 2023-08-04 | 2025-12-30 | 363000 | No PE | Authorized | No | Closed | Federal | 0
HSIP1-07-006 | 1 | 5111040 | 7 | Whittier | Los Angeles County | SCAG | MTA | Intersection Of Lambert Road And Santa Gertrudes Ave. | Install Left Turn Phasing For East And Westbound Approaches. | 553809.1 | 186120 | 2008-03-17 | 0 | 2009-11-05 | 2013-05-01 | 186120 | Authorized | Authorized | No | Closed | Federal | 0
HSIP2-07-021 | 2 | 5111043 | 7 | Whittier | Los Angeles County | SCAG | MTA | Beverly Blvd. Curve Between Magnolia Ave. And Citrus Ave. | Groove Concrete Pavement | 6545.02 | 4829 | 2009-11-05 | 0 | 2012-06-25 | 2015-07-08 | 4829 | Authorized | Authorized | No | Closed | Federal | 0
HSIP2-07-022 | 2 | 5111044 | 7 | Whittier | Los Angeles County | SCAG | MTA | Colima Rd. From Mar Vista St. To North City Limits | Install Right Edge Line Rumble Strip Between Vehicle Travel And Class Ii Bike Lanes | 45729.38 | 41128.56 | 2009-11-05 | 0 | 2012-06-25 | 2014-02-24 | 41128.56 | Authorized | Authorized | No | Closed | Federal | 0
HSIP2-07-023 | 2 | 5111045 | 7 | Whittier | Los Angeles County | SCAG | MTA | Broadway From Whittier Blvd. To Magnolia Ave. | Install Two-Way Left-Turn Lane, Signs, Stripes And Pavement Markings | 172102.98 | 114229.81 | 2009-11-05 | 0 | 2012-06-29 | 2015-01-09 | 114229.81 | Authorized | Authorized | No | Closed | Federal | 0
HSIP2-07-024 | 2 | 5111046 | 7 | Whittier | Los Angeles County | SCAG | MTA | Greenleaf Ave. From Whittier Blvd. To South City Limits | Install Two-Way Left Turn Lane And Class Ii Bike Lanes | 24024 | 21621.6 | 0 | 0 | 2009-09-09 | 2011-11-08 | 21621.6 | No PE | Authorized | No | Closed | Federal | 0
HSIP3-07-007 | 3 | 5111059 | 7 | Whittier | Los Angeles County | SCAG | MTA | Beverly Blvd. From The West City Limits To Norwalk Blvd./Workman Mill Rd. | Construct Raised Medians And Curb Extensions; Install In-Roadway Warning Lights, Traffic Signs, Class Ii Bike Lane Striping, Pavement Markings, Bus Shelters And Safety Lighting | 2299546.69 | 1500000 | 2010-08-30 | 0 | 2016-07-06 | 2018-03-28 | 1500000 | Authorized | Authorized | No | Closed | Federal | 0
H11-08-001 | 11 | 5408009 | 8 | Adelanto | San Bernardino County | SCAG | SANBAG | Intersections of Bellflower St/Victor St, Verbena Rd/Victor St, Aster Rd/Victor St, Rancho Rd/Adelanto Rd, Air Expressway/Aster Rd, and Air Expressway /Raccoon Ave. | Install all-way stop control including the installation of stop signs, stop ahead signs and legends, crosswalks, and the construction and reconstruction of ADA ramps. | 365900 | 329310 | 2025-07-17 | 0 | 0 | 0 | 40500 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE | State | 0
H12-08-001 | 12 | 5408011 | 8 | Adelanto | San Bernardino County | SCAG | SANBAG | Bellflower Street from Cactus to Rancho Road. | Widen shoulders; install striping and rumble strips. | 1167800 | 1051020 | 2025-08-29 | 0 | 0 | 0 | 99000 | Authorized | Due by 3/31/2028 | No | PE | State | 0
H12-08-002 | 12 | 5408010 | 8 | Adelanto | San Bernardino County | SCAG | SANBAG | Intersection of Rancho Road at Bellflower Street. | Install a traffic signal, with advance signal ahead warning signs and legends, and reconstruct existing handicap ramps and crosswalk striping. | 980000 | 882000 | 2025-07-17 | 0 | 0 | 0 | 162000 | Authorized | Due by 3/31/2028 | No | PE | State | 0
HSIP6-08-001 | 6 | 5453021 | 8 | Apple Valley | San Bernardino County | SCAG | SANBAG | Various locations throughout the Town of Apple Valley | Upgrade bike lanes, striping, and paint | 680852.99 | 451000 | 0 | 0 | 2016-08-11 | 2021-03-29 | 451000 | No PE | Authorized | No | Closed | Federal
H10-08-001 | 10 | 5214013 | 8 | Banning | Riverside County | SCAG | RCTC | The intersection of Ramsey Street with Omar Street and 1,000 feet west of intersection along eastbound Ramsey St. | Install sidewalk, curb and gutter, curb ramps, signage and striping, modify existing median to limit left turns from eastbound Ramsey Street only, install left-turn pocket, and improve sight distance. | 601898 | 539458 | 2021-08-19 | 0 | 2024-12-04 | 2026-02-18 | 539458 | Authorized | Authorized | No | Closed | State | 0
H10-08-002 | 10 | 5214014 | 8 | Banning | Riverside County | SCAG | RCTC | Four non-signalized intersections on Ramsey Street at Martin Street, 2nd Street, 6th Street, and 16th Street. | Install/upgrade pedestrian crossings at uncontrolled locations; install Rectangular Rapid Flashing Beacon (RRFB). | 282900 | 250000 | 2021-08-19 | 0 | 2024-12-04 | 0 | 250000 | Authorized | Authorized | No | CON | State | 0
H11-08-002 | 11 | 5214016 | 8 | Banning | Riverside County | SCAG | RCTC | 17 signalized intersections throughout the City of Banning. | Upgrade traffic signal hardware including LED safety lighting, retro-reflective backplates, countdown pedestrian signal heads, ADA-compliant pedestrian push buttons, and emergency vehicle preemption systems. | 433900 | 390510 | 2023-09-07 | 0 | 0 | 0 | 54000 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE | State | 0
H11-08-003 | 11 | 5214017 | 8 | Banning | Riverside County | SCAG | RCTC | 19 intersections throughout the City of Banning. | Install curb extensions, ADA curb ramps, RRFBs, high visibility crosswalks, and advanced warning signs and pavement markings. | 585000 | 526500 | 2023-09-07 | 0 | 0 | 0 | 76500 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE | State | 0
H11-08-004 | 11 | 5214018 | 8 | Banning | Riverside County | SCAG | RCTC | The intersection of Wilson St with 12th St. | Install curb extensions, ADA curb ramps, median refuge island, RRFB, high visibility crosswalks, and advanced warning signs and pavement markings. | 277000 | 249300 | 2023-09-07 | 0 | 0 | 0 | 44460 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE | State | 0
HSIP6-08-002 | 6 | 5214010 | 8 | Banning | Riverside County | SCAG | RCTC | On Ramsey St between Hargrave St and Sunset Ave | Upgrade traffic signals, including: controllers, pedestrian pushbuttons, signals hardware, new mast arms, detection, and install Emergency Vehicle Pre-Emption Devices. | 453410.12 | 375700 | 0 | 0 | 2016-09-20 | 2020-07-17 | 375700 | No PE | Authorized | No | Closed | Federal
HSIP6-08-003 | 6 | 5298028 | 8 | Barstow | San Bernardino County | SCAG | SANBAG | Various locations throughout Barstow | Upgrade traffic signals; Install pedestrian countdown head | 892200 | 802900 | 2016-06-22 | 0 | 2020-07-17 | 0 | 802900 | Authorized | Authorized | No | CON | Federal
HSIP6-08-004 | 6 | 5298033 | 8 | Barstow | San Bernardino County | SCAG | SANBAG | Barstow Rd (SR 247)/E Rimrock Rd | Install protected left-turn phasing | 200000 | 180000 | 0 | 0 | 2018-09-19 | 0 | 180000 | No PE | Authorized | No | CON | Federal
HSIP3-08-004 | 3 | 5426008 | 8 | Big Bear Lake | San Bernardino County | SCAG | SANBAG | Lakeview Dr./Big Bear Blvd. (Sr 18) Between Pine Knot Ave. And Paine Rd. | Widen Roadway; Install Two-Way Left-Turn Lane And Paved Shoulder; Replace/Modify Signs And Pavement Markings | 196257 | 169650 | 0 | 0 | 2014-02-10 | 2016-04-26 | 169650 | No PE | Authorized | No | Closed | Federal | 0
HSIP4-08-009 | 4 | 5426009 | 8 | Big Bear Lake | San Bernardino County | SCAG | SANBAG | Big Bear Blvd. (SR 18) between Edgemoor Rd. and Talmadge Rd. | Construct curb, gutter, sidewalks and curb ramps | 890723.3 | 458600 | 2014-01-29 | 0 | 2016-06-22 | 2018-06-15 | 458600 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-08-001 | 5 | 5426011 | 8 | Big Bear Lake | San Bernardino County | SCAG | SANBAG | Big Bear Blvd. from Division St. to 1,000' W of Division St. | Widen roadway and pave shoulders, lengthen left-turn and acceleration lanes; install two-way left-turn lane | 596662 | 192097.51 | 2014-03-12 | 0 | 2016-08-11 | 2018-10-15 | 192097.51 | Authorized | Authorized | No | Closed | Federal | 0
H11-08-005 | 11 | 5461001 | 8 | Canyon Lake | Riverside County | SCAG | RCTC | Railroad Canyon Road within the City of Canyon Lake, from approximately 0.1 mile south of Skylink Drive to approximately 0.3 miles west of Goetz Road. | Install roadway lighting, retro-reflective signal plates, and roadway enhancements such as median barriers, chevron signs, and warning devices. Improve pedestrian crossing along the roadway by installing protected left-turn and a new crosswalk. | 2923700 | 2000000 | 0 | 0 | 2025-02-20 | 0 | 2000000 | No PE | Authorized | No | CON | State | 0
H10-08-003 | 10 | 5430037 | 8 | Cathedral City | Riverside County | SCAG | RCTC | Intersection of Ramon Road and Avenida La Paloma.test | Install a Pedestrian Hybrid Beacon with conventional signal operation (3-signal head with green, yellow, and red indications).test | 1454300 | 1228400 | 2021-10-25 | 0 | 2023-07-07 | 2026-02-09 | 1228400 | Authorized | Authorized | No | Closed | State | 0
H11-08-006 | 11 | 5430039 | 8 | Cathedral City | Riverside County | SCAG | RCTC | 18 unsignalized intersections throughout the City of Cathedral City. | Install intersection lighting, LED flashing stop signs, ADA curb ramps, crosswalks, RRFBs, and advanced school zone signs and pavement markings. | 1452100 | 1306890 | 2024-02-03 | 0 | 2025-11-05 | 0 | 1306890 | Authorized | Authorized | No | CON | State | 0
H11-08-007 | 11 | 5430040 | 8 | Cathedral City | Riverside County | SCAG | RCTC | Intersection of 30th Avenue & Avenida La Paz, and Intersection of Cathedral Canyon Drive & Ortega Road. | Install pedestrian signal, including curb bulb-outs, ADA curb ramps, LED safety lighting, high visibility crosswalks, pavement markings, advanced warning signs and flashing beacons. | 1066300 | 959670 | 2024-02-03 | 0 | 2025-08-06 | 0 | 959670 | Authorized | Authorized | No | CON | State | 0
H11-08-008 | 11 | 5430041 | 8 | Cathedral City | Riverside County | SCAG | RCTC | 49 signalized intersections throughout the City of Cathedral City. | Install LED safety lighting and traffic signal backplates with retroreflective borders. | 1415650 | 1274085 | 2024-02-03 | 0 | 2025-08-06 | 0 | 1007730 | Authorized | Authorized | No | CON | State | 0
H11-08-009 | 11 | 5430042 | 8 | Cathedral City | Riverside County | SCAG | RCTC | The intersection of 30th Avenue with San Eljay Avenue. | Pedestrian School Crossing Enhancements including curb bulb-outs, ADA curb ramps, flashing stop signs, school zone flashing beacons, and LED safety lighting. | 277600 | 249840 | 2024-02-03 | 0 | 2025-08-01 | 0 | 249840 | Authorized | Authorized | No | CON | State | 0
H12-08-003 | 12 | 5430043 | 8 | Cathedral City | Riverside County | SCAG | RCTC | Ortega Road & Via De Anza, Bella Vista Road & Calada Road, Century Park Drive & Foxborough Drive. | Implement pedestrian crossing enhancements including ADA-compliant curb ramps, rectangular rapid flashing beacons (RRFBs), high visibility continental crosswalks, and other signing and striping improvements. | 388800 | 349920 | 2025-09-18 | 0 | 0 | 0 | 54450 | Authorized | Due by 3/31/2028 | No | PE | State | 0
H12-08-004 | 12 | 5430044 | 8 | Cathedral City | Riverside County | SCAG | RCTC | San Eljay Avenue & Doral Way, Dinah Shore Drive & Corregidor Drive, San Luis Rey Drive N & San Gabriel Circle E, San Luis Rey Drive S & San Gabriel Circle E, Ramon Road & Neuma Drive, and Ramon Road & Avenida Alvera / Canyon Vista Road. | Install pedestrian crossing at uncontrolled locations (signs and markings only) including pedestrian ramp upgrades, signing and striping. | 302400 | 272160 | 2025-10-01 | 0 | 0 | 0 | 48600 | Authorized | Due by 3/31/2028 | No | PE | State | 0
H8-08-001 | 8 | 5430033 | 8 | Cathedral City | Riverside County | SCAG | RCTC | Twenty (20) intersections throughout the City of Cathedral City. | Install advanced dilemma zone detection and countdown pedestrian signal heads. | 1772793.72 | 1772793.72 | 2017-07-19 | 0 | 2020-01-29 | 2023-02-14 | 1772793.72 | Authorized | Authorized | No | Closed | Federal | 0
H9-08-001 | 9 | 5430034 | 8 | Cathedral City | Riverside County | SCAG | RCTC | Traffic Signal Safety Upgrades at 12 Intersections Throughout the City | Install advanced dilemma zone detection, protected left turn phases, and pedestrian countdown heads. | 1489100 | 1489100 | 2019-09-13 | 0 | 2024-04-29 | 0 | 1489100 | Authorized | Authorized | No | CON | Federal | 0
H9-08-002 | 9 | 5430035 | 8 | Cathedral City | Riverside County | SCAG | RCTC | Varner Road between Mountain View Road and City Limits to the East. | Construct centerline and edgeline rumble strips, install flashing stop signs, and install guardrail. | 1107110.51 | 1089700 | 2019-09-13 | 0 | 2024-04-18 | 2026-03-27 | 1089700 | Authorized | Authorized | No | Closed | Federal | 0
HSIP4-08-015 | 4 | 5430030 | 8 | Cathedral City | Riverside County | SCAG | RCTC | E Palm Canyon Dr. between Canyon Plaza Dr. and Perez Rd. | Widen roadway and add bike lanes; construct curb, gutter, and sidewalks; upgrade traffic signals; install signs and striping | 750444.83 | 657625.35 | 2012-02-01 | 0 | 2014-09-11 | 2015-12-23 | 657625.35 | Authorized | Authorized | No | Closed | Federal | 0
H12-08-005 | 12 | 5188024 | 8 | Chino | San Bernardino County | SCAG | SANBAG | 10 signalized intersections along a segment of Central Avenue from Riverside Drive to Phillips Boulevard. | Install yellow retroreflective borders on traffic signal back-plates and install new near-side signal heads. | 250500 | 225450 | 2026-02-04 | 0 | 0 | 0 | 13500 | Authorized | Due by 3/31/2028 | No | PE | State | 0
HSIP5-08-002 | 5 | 5188020 | 8 | Chino | San Bernardino County | SCAG | SANBAG | Chino Ave./Ramona Ave. | Install protected left-turn phasing | 164490.61 | 140805 | 0 | 0 | 2015-06-01 | 2019-04-18 | 140805 | No PE | Authorized | No | Closed | Federal | 0
HSIP6-08-005 | 6 | 5188021 | 8 | Chino | San Bernardino County | SCAG | SANBAG | Edison Ave/Ramona Avenue, Edison Ave/Yorba Ave, and Edison Ave/Monte Vista Ave | Upgrade traffic signals; Install protected left-turn phasing | 1718906.8 | 880225 | 2014-12-19 | 0 | 2018-05-11 | 2023-08-15 | 880225 | Authorized | Authorized | No | Closed | Federal
H10-08-004 | 10 | 5467015 | 8 | Chino Hills | San Bernardino County | SCAG | SANBAG | Chino Hills Parkway at Walnut Creek and at Eucalyptus Ave; Peyton at Rock Springs Drive and Beverly Glen Drive; Soquel Canyon at Butterfield Ranch Road, Pomona Rincon Ave, and Pinehurst Drive; Butterfield Ranch Road at Pine Ave and at Brookwood Lane. | Improve traffic signals with backplates that include retroreflective borders. | 122800 | 122800 | 2021-08-19 | 0 | 2024-03-28 | 2025-11-24 | 122800 | Authorized | Authorized | No | Closed | State | 0
H12-08-006 | 12 | 0 | 8 | Chino Hills | San Bernardino County | SCAG | SANBAG | Seventy-four (74) major intersections throughout the City of Chino Hills. | Install green bike lanes and bike lane markings on green background. | 395300 | 349470 | 0 | 0 | 0 | 0 | 0 | No PE | Due by 3/31/2028 | No | Not Started | State | 0
H8-08-002 | 8 | 5467013 | 8 | Chino Hills | San Bernardino County | SCAG | SANBAG | Forty-six (46) signalized intersections throughout the City of Chino Hills. | Install signalized timers and pedestrian countdown heads. | 30244.32 | 22915 | 0 | 0 | 2018-09-19 | 2019-12-19 | 22915 | No PE | Authorized | No | Closed | Federal | 0
HSIP6-08-006 | 6 | 5467011 | 8 | Chino Hills | San Bernardino County | SCAG | SANBAG | On Pipeline Ave between approx 190' north of Chino Hills Parkway and approx1,810' north of Chino Hills Parkway | Install raised median | 497875.59 | 334637 | 2014-08-11 | 0 | 2017-02-28 | 2019-05-07 | 334637 | Authorized | Authorized | No | Closed | Federal
H12-08-007 | 12 | 5294022 | 8 | Coachella | Riverside County | SCAG | RCTC | Cesar Chavez St roadway and all signalized intersections from Park Ln to Ave 53. Nearby intersections: Ave 52 at Douma St; Cesar Chavez St access road at Ave 53; Cesar Chavez St at Bagdad Ave; Cesar Chavez St at Cairo St; Date Ave at Araby Ave. | Install protected bike lanes, pedestrian countdown signal heads and ADA-compliant audible push buttons, leading pedestrian intervals (LPIs), crosswalks, ADA-compliant curb ramps, curb extensions, pedestrian hybrid beacons, and raised medians. | 2903300 | 2612970 | 2025-12-11 | 0 | 0 | 0 | 466560 | Authorized | Due by 3/31/2028 | No | PE | Federal | 2
H12-08-009 | 12 | 5294020 | 8 | Coachella | Riverside County | SCAG | RCTC | Cesar Chavez St from Park Lane to the south driveway of Coachella Shopping Center, and Cesar Chavez St from Avenue 53 to Avenue 54. | Install protected bike lanes. | 184800 | 166320 | 2025-04-08 | 0 | 0 | 0 | 29700 | Authorized | Due by 3/31/2028 | No | PE | State | 0
H12-08-010 | 12 | 5294021 | 8 | Coachella | Riverside County | SCAG | RCTC | Valley Rd from Jennifer Way to Las Palmas St. | Install raised crosswalks. | 335600 | 261768 | 2025-05-01 | 0 | 0 | 0 | 46722 | Authorized | Due by 3/31/2028 | No | PE | State | 0
HSIP2-08-007 | 2 | 5294006 | 8 | Coachella | Riverside County | SCAG | RCTC | Various Locations | Upgrade Traffic Signs. | 472703.24 | 425432.92 | 2009-05-07 | 0 | 2014-09-19 | 2015-01-28 | 425432.92 | Authorized | Authorized | No | Closed | Federal | 0
H10-08-005 | 10 | 5065032 | 8 | Colton | San Bernardino County | SCAG | SANBAG | Various locations citywide including Mt. Vernon Ave., La Cadena Dr. and Barton Rd. | Replace damaged guardrails and improve existing guardrails. | 172933 | 172933 | 2022-01-11 | 0 | 2022-10-04 | 2025-08-01 | 172933 | Authorized | Authorized | No | Closed | State | 0
H11-08-010 | 11 | 5065033 | 8 | Colton | San Bernardino County | SCAG | SANBAG | Intersections of: La Cadena Dr./Fogg St., Valley Blvd./4th St., Valley Blvd./Pennsylvania Ave., and Rancho Ave./B St. | Installation of push button activated, solar powered Rapid Rectangular Flashing Beacon (RRFB), installation of signs, pavement striping and markings, and instillation of ADA ramps. | 232375 | 209138 | 2023-09-11 | 0 | 2024-10-22 | 0 | 209138 | Authorized | Authorized | No | CON | State | 0
H12-08-011 | 12 | 5065035 | 8 | Colton | San Bernardino County | SCAG | SANBAG | Intersection of: La Cadena Dr./D St., La Cadena Dr./E St., La Cadena Dr./Hanna St., La Cadena Dr./B St., 9th Street/D Street and Washington St./RV Center Drive (west). | Install rectangular rapid flashing beacons (RRFBs), signs, striping and other safety measures. | 246600 | 221940 | 2025-07-17 | 0 | 0 | 0 | 22950 | Authorized | Due by 3/31/2028 | No | PE | State | 0
H9-08-003 | 9 | 5065029 | 8 | Colton | San Bernardino County | SCAG | SANBAG | Improvements to 13 selected crosswalks near five Colton public schools, each with a high proportion of students who bike or walk to school. | Install RRFBs (NS 19), R1-5 signs (NS5), high visibility crosswalk re-striping and yield lines (Ns6), and ADA-compliant curb ramps (NS18). | 345012.41 | 202563.58 | 2019-12-18 | 0 | 2021-06-28 | 2023-12-14 | 202563.58 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-08-003 | 5 | 5065026 | 8 | Colton | San Bernardino County | SCAG | SANBAG | Mount Vernon Ave./Olive St.; Mount Vernon Ave./Cooley Dr.; Mount Vernon Ave./Valley Blvd.; Mount Vernon Ave./Santo Antonio Dr.; Mount Vernon Ave./Centerpointe Dr.; Mount Vernon Ave./Colton Ave. | Upgrade traffic signals | 1012749 | 755999.04 | 2014-04-01 | 0 | 2017-04-05 | 2022-03-21 | 755999.04 | Authorized | Authorized | No | Closed | Federal | 0
HSIP1-08-007 | 1 | 5104036 | 8 | Corona | Riverside County | SCAG | RCTC | Intersection Of Rimpau Ave. And California Ave. | Install Traffic Signals, Left-Turn Lanes And Pedestrian Crosswalks. | 600804.74 | 402927.42 | 0 | 0 | 2011-09-14 | 2015-01-06 | 402927.42 | No PE | Authorized | No | Closed | Federal | 0
HSIP2-08-005 | 2 | 5104039 | 8 | Corona | Riverside County | SCAG | RCTC | Intersection Of East Sixth St. And El Camino Ave. | Install Traffic Signal, Right- And Left-Turn Lanes, Crosswalk And Signs; Construct Curb, Gutter And Curb Ramps | 262301.75 | 207977.58 | 0 | 0 | 2012-02-06 | 2014-12-19 | 207977.58 | No PE | Authorized | No | Closed | Federal | 0
H11-08-011 | 11 | 5384019 | 8 | Desert Hot Springs | Riverside County | SCAG | RCTC | 17 intersections (10 along Palm Dr, Hacienda Av & Mountain View Rd, 5 intersections along Pierson Bl, and Mission Lakes Bl & Indian Canyon Dr). | Install retroreflective signal back-plates and install signal phasing to implement Leading Pedestrian Interval system (all 17 intersections). Install high visibility thermoplastic crosswalks (8 intersections). | 623500 | 561150 | 2023-08-03 | 0 | 0 | 0 | 64170 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE | State | 0
H9-08-004 | 9 | 5384023 | 8 | Desert Hot Springs | Riverside County | SCAG | RCTC | Palm Drive from Dillon Road to Pierson Boulevard. | Upgrade standard pedestrian signal heads to countdown style pedestrian signal heads and pedestrian push buttons to accessible pedestrian signal (APS); construct continental style crosswalks with limit lines. | 286489.46 | 286489.46 | 0 | 0 | 2022-12-20 | 2025-08-13 | 286489.46 | No PE | Authorized | No | Closed | Federal | 2
H9-08-006 | 9 | 5384025 | 8 | Desert Hot Springs | Riverside County | SCAG | RCTC | The intersection of Palm Drive at 8th Street. | Construct median refuges and curb bulb outs, upgrade stop signs to LED bordered stop signs, and upgrade existing crosswalks to continental crosswalks. | 192790.3 | 173511.27 | 0 | 0 | 2022-11-29 | 2023-12-27 | 173511.27 | No PE | Authorized | No | Closed | Federal | 0
H10-08-006 | 10 | 5486010 | 8 | Eastvale | Riverside County | SCAG | RCTC | 16 signalized intersections along major corridors: Limonite Ave, Schleisman Rd, Hamner Ave and Archibald Ave. | Install advanced dilemma zone detection system and associated equipment in existing traffic signal cabinets, and modify signal timing to improve safety. | 1175700 | 902300 | 2021-05-17 | 0 | 2023-01-16 | 2026-01-27 | 902300 | Authorized | Authorized | No | Closed | State | 0
H10-08-007 | 10 | 5486009 | 8 | Eastvale | Riverside County | SCAG | RCTC | 39 signalized intersections along major corridors: Limonite Ave, Schleisman Rd, Hamner Ave, and Archibald Ave. | Install retroreflective borders along the backplates of traffic signal indicators. | 371179 | 371179 | 2021-05-13 | 0 | 2022-06-06 | 2024-07-01 | 371179 | Authorized | Authorized | No | Closed | State | 0
H12-08-012 | 12 | 5486014 | 8 | Eastvale | Riverside County | SCAG | RCTC | The intersection of Sumner Ave and 68th St. | Convert a 3-way stop controlled intersection to a signalized intersection. | 721800 | 642402 | 2025-05-26 | 0 | 0 | 0 | 53400 | Authorized | Due by 3/31/2028 | No | PE | State | 0
H8-08-003 | 8 | 5486005 | 8 | Eastvale | Riverside County | SCAG | RCTC | Forty-six (46) intersections throughout the City of Eastvale. | Retrofit existing traditional pedestrian crossings with Countdown Pedestrian Signals at forty-six (46) locations and install audible APS Controller Units at twenty-two (22) locations. | 492548.37 | 206500 | 0 | 0 | 2020-04-23 | 2021-09-17 | 206500 | No PE | Authorized | No | Closed | Federal | 0
H11-08-012 | 11 | 5307037 | 8 | Fontana | San Bernardino County | SCAG | SANBAG | 118 signalized intersections throughout the City of Fontana. | Install traffic management software to improve safety by adding the ability to synchronize signals along major corridors throughout the City. | 1331800 | 665900 | 2023-08-23 | 0 | 0 | 0 | 19050 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE | State | 0
HSIP1-08-009 | 1 | 5307016 | 8 | Fontana | San Bernardino County | SCAG | SANBAG | On Sierra Avenue Between Valley Boulevard And San Bernardino Avenue. | Construct Raised Concrete Median. | 1578081.47 | 828674.97 | 0 | 0 | 2010-05-19 | 2013-04-17 | 828674.97 | No PE | Authorized | No | Closed | Federal | 0
HSIP3-08-001 | 3 | 5307020 | 8 | Fontana | San Bernardino County | SCAG | SANBAG | Foothill Blvd. Between Sierra Ave. And Mango Ave. | Construct Raised Median; Resurface Existing Pavement; Modify Traffic Signal; Install Traffic Signs, Stripes And Pavement Markings | 922743.93 | 569670.65 | 2011-06-02 | 0 | 2013-09-18 | 2015-03-09 | 569670.65 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-08-004 | 5 | 5307021 | 8 | Fontana | San Bernardino County | SCAG | SANBAG | Foothill Blvd. from Oleander Ave. to approximately 600' E of Cypress Ave. | Install traffic signals, signs, and striping; resurface pavement; construct raised medians, sidewalks, curbs and gutters | 3006050.6 | 884627.19 | 2013-12-09 | 0 | 2018-06-15 | 2023-10-27 | 884627.19 | Authorized | Authorized | No | Closed | Federal | 0
HSIP6-08-007 | 6 | 5307023 | 8 | Fontana | San Bernardino County | SCAG | SANBAG | Randall Ave/Juniper Ave | Install traffic signals | 430625.94 | 375369.69 | 2014-09-11 | 0 | 2017-04-12 | 2019-01-18 | 375369.69 | Authorized | Authorized | No | Closed | Federal
HSIP7-08-003 | 7 | 5307025 | 8 | Fontana | San Bernardino County | SCAG | SANBAG | Ten signalized intersections along Sierra Avenue from Valley Blvd. to Arrow Blvd | Implementing an adaptive traffic management system "ATMS" along ten (10) signalized intersection arterial | 362322 | 362322 | 0 | 0 | 2017-05-01 | 2020-10-06 | 362322 | No PE | Authorized | No | Closed | Federal
H8-08-004 | 8 | 5421005 | 8 | Grand Terrace | San Bernardino County | SCAG | SANBAG | Three (3) uncontrolled four-way stop intersections and two (2) signalized intersections along Mt. Vernon Avenue. | Upgrade intersection and crosswalk pavement markings, install advanced speed feedback warning signs, and install segment lighting. | 571601 | 423256 | 2018-01-11 | 0 | 2020-01-02 | 2023-04-17 | 423256 | Authorized | Authorized | No | Closed | Federal | 0
H10-08-008 | 10 | 5186019 | 8 | Hemet | Riverside County | SCAG | RCTC | Forty (40) signalized intersections throughout the City. | Replace the signal head backplates with backplates with retroreflective borders. | 485800 | 485800 | 2022-01-06 | 0 | 2023-08-07 | 2025-06-23 | 485800 | Authorized | Authorized | No | Closed | State | 0
H8-08-005 | 8 | 5186017 | 8 | Hemet | Riverside County | SCAG | RCTC | Signalized intersections on the following corridors: Cawston Ave, Domenigoni Pkwy, Kirby St, Latham Ave, Lyon Ave, Sanderson Ave, State St, and Stetson St; Mountain Ave & Soboba St, Warren Rd & Mustang Wy. | Install LED luminaire safety lighting and pedestrian countdown signal heads. | 994738.05 | 928278.74 | 2017-11-30 | 0 | 2021-04-01 | 2025-06-24 | 928278.74 | Authorized | Authorized | No | Closed | Federal | 0
H9-08-008 | 9 | 5452020 | 8 | Hesperia | San Bernardino County | SCAG | SANBAG | The intersection of Main Street and Timberlane Avenue/Sultana Street. | Install a traffic signal; widen roadway to accommodate left turn pockets; install curb, gutter, sidewalk, curb ramps, crosswalks, and lighting; provide pedestrian phasing and countdown timers. | 1214300 | 899300 | 0 | 0 | 2024-02-28 | 0 | 899300 | No PE | Authorized | No | CON | Federal | 2
H10-08-009 | 10 | 5449040 | 8 | Highland | San Bernardino County | SCAG | SANBAG | 26 intersections within the City of Highland. | Install pedestrian countdown signal heads. | 250000 | 250000 | 2022-06-01 | 0 | 2023-12-18 | 0 | 250000 | Authorized | Authorized | No | CON | State | 0
H11-08-013 | 11 | 5449043 | 8 | Highland | San Bernardino County | SCAG | SANBAG | 5th Street from Del Rosa Drive to Victoria Avenue; Greenspot Road from SR210 to Greenspot Road Bridge; and Orange Street from Boulder Avenue to south City Limits. | Upgrade approximately 7 miles of roadway edge-line and centerline stripes to replace existing faded and worn roadway line delineation along the City of Highland's arterial roadway segments. | 155000 | 139500 | 2024-05-08 | 0 | 0 | 0 | 25650 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE | State | 0
H12-08-013 | 12 | 0 | 8 | Highland | San Bernardino County | SCAG | SANBAG | Thirty-five (35) signalized intersections throughout the city and Church Street at Glenheather Drive/Love Street intersection. | Install a new traffic signal, upgrade signal heads, and install retroreflective signal head backplates. | 1522300 | 1370070 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2025) | Due by 3/31/2028 | Yes (PE) | Not Started | Federal | 0
H8-08-006 | 8 | 5449036 | 8 | Highland | San Bernardino County | SCAG | SANBAG | Intersection of Palm Avenue and Cypress Street. | Install Traffic Signal. | 282810.76 | 229277.94 | 0 | 0 | 2017-07-14 | 2021-04-08 | 229277.94 | No PE | Authorized | No | Closed | Federal | 0
HSIP2-08-009 | 2 | 5449011 | 8 | Highland | San Bernardino County | SCAG | SANBAG | Base Line St. Between Sr210 And Boulder Ave. | Construct Raised Median. | 1371204.46 | 683500 | 2009-05-11 | 0 | 2015-09-01 | 2018-03-27 | 683500 | Authorized | Authorized | No | Closed | Federal | 0
HSIP4-08-002 | 4 | 5449025 | 8 | Highland | San Bernardino County | SCAG | SANBAG | 9th St. between Del Rosa Dr. and Palm Ave. | Restripe for bike lanes and two-way left-turn lane; install in-pavement crosswalk lights, advance warning lights and signs, and pedestrian countdown heads; construct curb ramps | 709138.82 | 490000 | 2012-08-13 | 0 | 2014-09-11 | 2016-11-16 | 490000 | Authorized | Authorized | No | Closed | Federal | 0
HSIP4-08-020 | 4 | 5449022 | 8 | Highland | San Bernardino County | SCAG | SANBAG | Base Line between Cole Ave. and SR 210 | Construct raised median; reconfigure driveway access; install in-pavement crosswalk lights and pedestrian countdown heads | 1159336.15 | 300000 | 0 | 0 | 2011-11-21 | 2022-09-20 | 300000 | No PE | Authorized | No | Closed | Federal | 0
H12-08-014 | 12 | 0 | 8 | Indian Wells | Riverside County | SCAG | RCTC | On Fairway Drive between Cielito Drive and El Dorado Drive. | Construct sidewalk, curb ramps, and pedestrian crosswalk. | 382800 | 344520 | 0 | 0 | 0 | 0 | 0 | No PE | Due by 3/31/2028 | No | Not Started | State | 0
H12-08-015 | 12 | 0 | 8 | Indian Wells | Riverside County | SCAG | RCTC | On Fairway Drive, Cook Street, Rancho Palmeras Drive, and El Dorado Drive. | Install three (3) two-way cycle tracks and one (1) bicycle route. | 353300 | 317970 | 0 | 0 | 0 | 0 | 0 | No PE | Due by 3/31/2028 | No | Not Started | State | 0
H8-08-007 | 8 | 5275033 | 8 | Indio | Riverside County | SCAG | RCTC | Twenty-one (21) intersections throughout the City of Indio. | Install signal timers and pedestrian countdown heads. | 250000 | 68746.6 | 0 | 0 | 2020-02-12 | 2021-11-24 | 68746.6 | No PE | Authorized | No | Closed | Federal | 0
H8-08-008 | 8 | 5275034 | 8 | Indio | Riverside County | SCAG | RCTC | Avenue 44 from Monroe Street to Palo Verde Avenue. | Construct Road Diet (reduce travel lanes from four to two with a two-way left turn lane, and install bike lanes and space for street parking). | 401802.63 | 330120 | 0 | 0 | 2020-02-12 | 2022-12-15 | 330120 | No PE | Authorized | No | Closed | Federal | 0
H9-08-009 | 9 | 5275036 | 8 | Indio | Riverside County | SCAG | RCTC | Fifteen (15) signalized intersections throughout the City of Indio. | Install advanced dilemma zone detection. | 1013152.32 | 537969.06 | 2019-11-27 | 0 | 2022-07-14 | 2025-12-01 | 537969.06 | Authorized | Authorized | No | Closed | Federal | 0
HSIP7-08-005&006 | 7 | 5275029 | 8 | Indio | Riverside County | SCAG | RCTC | Intersection of Doctor Carreon Boulevard and Oasis Street; On Monroe Street at 11 intersections from Oleander Avenue to Comet Lane. | Replace existing permissive left-turn phases and signal heads with protected left-turn phases and signal heads on existing poles with larger mast arms; Improve signal timing (coordination, phases, red, yellow, or operation) | 468800 | 468800 | 0 | 0 | 2018-09-19 | 2021-02-10 | 468800 | No PE | Authorized | No | Closed | Federal
H10-08-010 | 10 | 5487007 | 8 | Jurupa Valley | Riverside County | SCAG | RCTC | Eighty-nine (89) signalized intersections throughout the City. | Install a signal master controller with fiber interconnectivity or via radio; and install retroreflective signal head backplates. | 4707600 | 2353800 | 2021-11-29 | 0 | 2024-08-23 | 0 | 2353800 | Authorized | Authorized | No | CON | State | 0
H11-08-014 | 11 | 5487011 | 8 | Jurupa Valley | Riverside County | SCAG | RCTC | On Rubidoux Boulevard from just north of 26th Street to just north of 24th Street. | Install traffic signal at 24th street. Re-stripe the existing four lane section to five lanes between 26th Street and 24th Street. | 625600 | 563040 | 0 | 0 | 2025-11-19 | 0 | 563040 | No PE | Authorized | No | CON | State | 0
H9-08-010 | 9 | 5487006 | 8 | Jurupa Valley | Riverside County | SCAG | RCTC | Fourteen (14) locations throughout the City totaling twenty-one (21) guardrail segments. | Upgrade existing metal beam guardrails to current Caltrans Midwest Guardrail System (MGS) standards, including new end treatments and beam sections, and relocate guardrails to correct locations. | 579179.61 | 509168 | 0 | 0 | 2022-06-07 | 2025-04-07 | 509168 | No PE | Authorized | No | Closed | Federal | 0
HSIP7-08-007 | 7 | 5487002 | 8 | Jurupa Valley | Riverside County | SCAG | RCTC | Pedley Road from 60th St. to 0.2 miles north of Kim Lane. | Add left-turn lanes to 6 unsignalized intersections along Pedley Road and modify storm drain under-crossings by relocating headwalls away from the travel lanes and adding guardrails at the headwall abutments. | 1198296.95 | 1078467.24 | 2017-10-20 | 0 | 2020-06-16 | 2022-11-05 | 1078467.24 | Authorized | Authorized | No | Closed | Federal
HSIP7-08-008 | 7 | 5433017 | 8 | La Quinta | Riverside County | SCAG | RCTC | Various streets throughout the City of La Quinta | Upgrade traffic signal interconnect network including the installation of new fiber optic interconnect, replacing existing wired interconnect with fiber optic cables and all contingent work to improve signal timing and coordination. | 1884859.88 | 1871141.87 | 2016-07-29 | 0 | 2019-05-17 | 2021-10-13 | 1871141.87 | Authorized | Authorized | No | Closed | Federal
HSIP7-08-009 | 7 | 5433015 | 8 | La Quinta | Riverside County | SCAG | RCTC | Various Intersections throughout the City of La Quinta | Upgrade all intersection safety lighting and street name signs to more visible LED type and upgrade the traffic signal cabinet at 8 intersections and cabinet controller at 15 intersections. | 898295.38 | 797982.84 | 2016-07-27 | 0 | 2018-02-21 | 2020-11-06 | 797982.84 | Authorized | Authorized | No | Closed | Federal
H11-08-015 | 11 | 0 | 8 | Lake Elsinore | Riverside County | SCAG | RCTC | Various locations throughout the City. | Install Rectangular Rapid Flashing Beacon (RRFB) signs at existing pedestrian crossings at various locations throughout the City. Install advanced yield line pavement markings and signs. | 250000 | 225000 | 0 | 0 | 0 | 0 | 0 | No PE | Due by 9/30/2026 | No | Not Started | State | 0
H12-08-016 | 12 | 5074023 | 8 | Lake Elsinore | Riverside County | SCAG | RCTC | Railroad Canyon Road from Summerhill Drive/Grape Street to Eastern City Boundary. | Relocate utility poles and install guardrails near Church Rd. Install high friction surface treatment (HFST), LED/flashing beacon chevron and "Curve Ahead" signs, and additional reflectors along curved segments. Improve signal hardware and signal timing. | 4395000 | 3955500 | 2025-08-28 | 0 | 0 | 0 | 315000 | Authorized | Due by 3/31/2028 | No | PE | Federal | 0
H12-08-017 | 12 | 0 | 8 | Lake Elsinore | Riverside County | SCAG | RCTC | Thirty (30) signalized intersections. | Install retroreflective signal backplates, install pedestrian countdown heads, and leading pedestrian interval (LPI). | 846400 | 761760 | 0 | 0 | 0 | 0 | 0 | No PE | Due by 3/31/2028 | No | Not Started | State | 0
H8-08-009 | 8 | 5074019 | 8 | Lake Elsinore | Riverside County | SCAG | RCTC | Eight (8) intersections throughout the city. | Install advanced dilemma zone detection, flashing warning beacons, and left turn phasing. | 691252.57 | 691252.57 | 2018-06-15 | 0 | 2021-04-08 | 2023-12-27 | 691252.57 | Authorized | Authorized | No | Closed | Federal | 0
H9-08-011 | 9 | 5074020 | 8 | Lake Elsinore | Riverside County | SCAG | RCTC | Ten (10) intersections throughout the Cityof Lake Elsinore. | Install advanced dilemma zone detection, protected left turns, and pedestrian countdown heads. | 1920550.18 | 1611762.95 | 2020-03-12 | 0 | 2023-01-25 | 2025-05-19 | 1611762.95 | Authorized | Authorized | No | Closed | Federal | 0
H11-08-016 | 11 | 5483014 | 8 | Menifee | Riverside County | SCAG | RCTC | Signalized intersections throughout city. | Installation of retro-reflective backplates and leading pedestrian interval at signal locations throughout the city. | 2160700 | 1555704 | 2023-11-06 | 0 | 2026-03-27 | 0 | 1555704 | Authorized | Authorized | No | CON | Federal | 2
H12-08-018 | 12 | 5483016 | 8 | Menifee | Riverside County | SCAG | RCTC | Various locations. | Upgrade existing guardrails and end treatments. | 1110800 | 999720 | 2025-08-22 | 0 | 0 | 0 | 115380 | Authorized | Due by 3/31/2028 | No | PE | State | 0
H12-08-019 | 12 | 5483017 | 8 | Menifee | Riverside County | SCAG | RCTC | Haun Road from Scott to Holland Rd; Garbani Road from Haun Road to Briggs Road; and Scott Road from Ascot Way to Sunset Avenue. | Install upgraded edgeline striping. | 385800 | 347220 | 2025-08-22 | 0 | 0 | 0 | 51480 | Authorized | Due by 3/31/2028 | No | PE | State | 0
H12-08-020 | 12 | 5483018 | 8 | Menifee | Riverside County | SCAG | RCTC | Various unsignalized pedestrian crossings. | Install rectangular rapid flashing beacons (RRFBs), high visibility crosswalk striping, and construct curb ramps. | 373000 | 335700 | 2025-08-22 | 0 | 0 | 0 | 49770 | Authorized | Due by 3/31/2028 | No | PE | State | 0
H8-08-010 | 8 | 5483005 | 8 | Menifee | Riverside County | SCAG | RCTC | Signalized intersections on the following corridors: Murrieta Road, Menifee Road, Newport Road, Goetz Road, Haun Road, McCall Boulevard, La Piedra Road, Antelope Road, and Scott Road. | Install pedestrian countdown signal heads, APS push buttons, ADA-compliant curb ramps and crosswalk striping. | 817836.93 | 817836.93 | 2017-10-20 | 0 | 2019-11-27 | 2021-08-16 | 817836.93 | Authorized | Authorized | No | Closed | Federal | 0
H9-08-012 | 9 | 5483007 | 8 | Menifee | Riverside County | SCAG | RCTC | Antelope Road between Sunstream Drive and La Piedra Road. | Install raised median. | 671333.31 | 511475.27 | 2019-10-23 | 0 | 2021-02-12 | 2022-11-05 | 511475.27 | Authorized | Authorized | No | Closed | Federal | 0
HSIP7-08-010 | 7 | 5483003 | 8 | Menifee | Riverside County | SCAG | RCTC | Signalized intersections on the following corridors on the west side of Menifee: McCall Blvd, Murrieta Road, Newport Rd, Goetz Rd, La Piedra Rd, Haun Rd, Normandy Rd, and Sun City Blvd. | Install wireless interconnect system including radios, controllers, and related communication equipment upgrades to improve safety and operations via optimized traffic signal timing coordination. | 575036.12 | 493586.21 | 0 | 0 | 2019-12-27 | 2021-11-24 | 493586.21 | No PE | Authorized | No | Closed | Federal
HSIP7-08-011 | 7 | 5483004 | 8 | Menifee | Riverside County | SCAG | RCTC | Signalized intersections on the following corridors on the east side of Menifee: Menifee Rd, Briggs Rd, McCall Blvd, Newport Rd, Lindenberger Rd, Antelope Rd, Holland Rd, and Scott Rd. | Install wireless interconnect system including radios and related communication equipment upgrade to improve safety and operations via optimized traffic signal timing coordination. | 548967.17 | 494899.63 | 0 | 0 | 2019-05-20 | 2021-10-13 | 494899.63 | No PE | Authorized | No | Closed | Federal
H10-08-011 | 10 | 5326023 | 8 | Montclair | San Bernardino County | SCAG | SANBAG | The intersection of Ramona Avenue and Howard Street. | Construct roundabout and refuge island; install high visibility crosswalks and curb ramps; and add/upgrade lighting. | 771100 | 771100 | 2021-07-16 | 0 | 2025-08-05 | 0 | 771100 | Authorized | Authorized | No | CON | State | 0
H11-08-017 | 11 | 5326027 | 8 | Montclair | San Bernardino County | SCAG | SANBAG | Adjacent to Montera Elementary School at multiple locations along Monte Vista Avenue, Bandera Street, Helena Avenue, Kingsley Street, Fremont Avenue, and Canoga Street. | Enhance pedestrian safety by installing edgelines and high visibility and/or ladder crosswalks, constructing ADA-compliant curb ramps, adding pedestrian signage, solar-powered speed feedback signage, and other safety measures. | 277700 | 249930 | 2024-06-18 | 0 | 0 | 0 | 27000 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE | State | 0
H11-08-018 | 11 | 5326026 | 8 | Montclair | San Bernardino County | SCAG | SANBAG | 1.95 miles of Orchard Street at 10 signalized and non-signalized intersections: Mills Ave., Pradera Ave., Sunset Park entrances, Ramona Ave., Camulos Ave., Tudor Ave., Monte Vista Ave., Fremont Ave., Central Ave., and Benson Ave. | Install raised pavement markers and striping; Upgrade existing stop signs to flashing LED light stop signs; Install a HAWK system; Install/Upgrade pedestrian crossings at uncontrolled locations. | 402300 | 362070 | 2024-06-18 | 0 | 0 | 0 | 40500 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE | State | 0
H12-08-021 | 12 | 0 | 8 | Montclair | San Bernardino County | SCAG | SANBAG | Benson Avenue between Arrow Highway and Holt Boulevard. | Implement a road diet, install Class II bike lanes, right and left turn lanes, pedestrian countdown signal heads, and upgrade intersection pavement markings and pedestrian crossing at uncontrolled locations. | 3156900 | 2841210 | 0 | 0 | 0 | 0 | 0 | No PE | Due by 3/31/2028 | No | Not Started | Federal | 2
HSIP6-08-008 | 6 | 5326017 | 8 | Montclair | San Bernardino County | SCAG | SANBAG | Central Ave/San Bernardino St | Upgrade traffic signals; Install protected left-turn phasing | 209429.03 | 188485.96 | 0 | 0 | 2015-03-25 | 2016-11-21 | 188485.96 | No PE | Authorized | No | Closed | Federal
H11-08-019 | 11 | 5441078 | 8 | Moreno Valley | Riverside County | SCAG | RCTC | 50 intersections throughout the city. | Improve signal hardware including: lenses, back-plates with retro reflective borders, mounting, size and number. | 1091900 | 982710 | 2023-04-28 | 0 | 2024-04-03 | 0 | 982710 | Authorized | Authorized | No | CON | State | 0
H11-08-020 | 11 | 5441079 | 8 | Moreno Valley | Riverside County | SCAG | RCTC | 3-mile corridor along Iris Avenue, between the Iris Avenue/Heacock Street intersection to the west and the Iris Avenue/Nason Street intersection to the east. | Implement safety improvements including: retroreflective backplates, advanced stop bar and high-visibility crosswalk striping, leading pedestrian intervals, advanced warning signs, object markers, and edge-lines. | 499300 | 449370 | 2023-04-28 | 0 | 2025-03-25 | 0 | 449370 | Authorized | Authorized | No | CON | State | 0
H11-08-021 | 11 | 5441080 | 8 | Moreno Valley | Riverside County | SCAG | RCTC | 16 signalized intersections on Perris Boulevard. | Signalized intersection improvements including retroreflective backplates, LPIs and advanced stop bars with upgraded crosswalk markings. | 721000 | 648900 | 2023-05-01 | 0 | 2024-09-17 | 0 | 648900 | Authorized | Authorized | No | CON | State | 0
H11-08-022 | 11 | 5441081 | 8 | Moreno Valley | Riverside County | SCAG | RCTC | 15 signalized intersections on high speed roads. | Intersection visibility improvements including additional intersection lighting, advance stop bars and high-visibility striping, and retroreflective backplates. | 1438700 | 1294830 | 2023-04-28 | 0 | 2025-03-28 | 0 | 1223730 | Authorized | Authorized | No | CON | State | 0
H12-08-022 | 12 | 5441085 | 8 | Moreno Valley | Riverside County | SCAG | RCTC | 62 locations citywide. | Improve signal hardware, apply yellow retro-reflective tape, improve pavement friction and install leading pedestrian intervals (LPIs). | 1808000 | 1627200 | 2025-12-01 | 0 | 0 | 0 | 121500 | Authorized | Due by 3/31/2028 | No | PE | Federal | 0
H12-08-023 | 12 | 5441087 | 8 | Moreno Valley | Riverside County | SCAG | RCTC | 12 signalized intersections, 19 non-signalized intersections and two roadways along Iris Avenue and John F. Kennedy Drive. | Signalized intersections: improve signal hardware and install leading pedestrian interval (LPI); Non-signalized intersections: upgrade intersection pavement markings and install flashing beacons rectangular rapid flashing beacons (RRFBs); Road segments: Install delineators, reflectors, object markers and impact attenuators. | 1018100 | 916290 | 2025-10-22 | 0 | 0 | 0 | 161820 | Authorized | Due by 3/31/2028 | No | PE | State | 0
H12-08-024 | 12 | 5441086 | 8 | Moreno Valley | Riverside County | SCAG | RCTC | The intersection of Dracaea Avenue and Helmsdale Street. | Construct an enhanced crosswalk with pedestrian hybrid beacons and ADA compliant ramps. | 349600 | 314640 | 2025-10-22 | 0 | 0 | 0 | 51300 | Authorized | Due by 3/31/2028 | No | PE | State | 0
H8-08-011 | 8 | 5441070 | 8 | Moreno Valley | Riverside County | SCAG | RCTC | Citywide locations. | Upgrade existing guardrails. | 624655.53 | 624655.53 | 2017-06-15 | 0 | 2020-03-04 | 2021-10-13 | 624655.53 | Authorized | Authorized | No | Closed | Federal | 0
H8-08-012 | 8 | 5441071 | 8 | Moreno Valley | Riverside County | SCAG | RCTC | Seven locations citywide. | Upgrade existing marked crosswalks on arterials. | 368127 | 368127 | 2017-06-15 | 0 | 2020-02-04 | 2023-10-19 | 368127 | Authorized | Authorized | No | Closed | Federal | 0
H8-08-013 | 8 | 5441072 | 8 | Moreno Valley | Riverside County | SCAG | RCTC | Lasselle Street from south city limit to College Drive. | Install high-friction surface treatment at spot locations; install speed control system on seven (7) signalized intersections. | 645710.24 | 628588.86 | 2017-06-15 | 0 | 2020-09-10 | 2023-10-24 | 628588.86 | Authorized | Authorized | No | Closed | Federal | 0
HSIP2-08-008 | 2 | 5441046 | 8 | Moreno Valley | Riverside County | SCAG | RCTC | Various Locations | Install Emergency Vehicle Pre-Emption System. | 853006.9 | 691883.24 | 2010-04-06 | 0 | 2011-07-08 | 2016-01-12 | 691883.24 | Authorized | Authorized | No | Closed | Federal | 0
HSIP4-08-008 | 4 | 5441050 | 8 | Moreno Valley | Riverside County | SCAG | RCTC | Alessandro Blvd. from 500' E of Perris Blvd. to Indian St. | Construct raised median island with left-turn pockets; install new traffic signals (Covey Quail Ln.); modify traffic signals (Perris Blvd.); install signs and striping | 1448674.24 | 900000 | 2011-10-31 | 0 | 2013-12-09 | 2016-03-01 | 900000 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-08-005 | 5 | 5441056 | 8 | Moreno Valley | Riverside County | SCAG | RCTC | Elsworth St./Alessandro Blvd. | Convert signal to mast arm, improve vehicular head placement, remove steep cross gutters, implement advanced "dilemma zone" protection, and upgrading ADA access | 884808.98 | 760500 | 2013-12-13 | 0 | 2016-08-11 | 2019-05-07 | 760500 | Authorized | Authorized | No | Closed | Federal | 0
HSIP6-08-009 | 6 | 5441062 | 8 | Moreno Valley | Riverside County | SCAG | RCTC | Alessandro Blvd/Chagall Ct, Alessandro Blvd/Graham St | Upgrade raised median and ramps; Install "dilemma zone" detection; | 632224.1 | 569001.61 | 2015-02-05 | 0 | 2017-08-24 | 2020-05-12 | 569001.61 | Authorized | Authorized | No | Closed | Federal
HSIP6-08-010 | 6 | 5441061 | 8 | Moreno Valley | Riverside County | SCAG | RCTC | Various locations throughout the Moreno Valley | Install pedestrian countdown heads; ADA pedestrian pushbuttons | 624206.14 | 553334.21 | 2014-08-04 | 0 | 2015-09-10 | 2020-03-19 | 553334.21 | Authorized | Authorized | No | Closed | Federal
HSIP7-08-012 | 7 | 5441068 | 8 | Moreno Valley | Riverside County | SCAG | RCTC | 65 signalized intersections citywide | Install advanced dilemma zone detection systems | 2393875.77 | 2393875.77 | 2016-09-16 | 0 | 2020-03-25 | 2023-12-27 | 2393875.77 | Authorized | Authorized | No | Closed | Federal
HSIP7-08-013 | 7 | 5441067 | 8 | Moreno Valley | Riverside County | SCAG | RCTC | Kitching Street between Sunnymead Boulevard and Alessandro Boulevard | Conduct Road Safety Audit and implement eligible recommended improvements | 70261.67 | 69403.87 | 2016-09-16 | 0 | 2020-09-10 | 2023-11-27 | 69403.87 | Authorized | Authorized | No | Closed | Federal
HSIP7-08-014 | 7 | 5441066 | 8 | Moreno Valley | Riverside County | SCAG | RCTC | Ironwood Avenue from 500' west of Lasselle Street to Nason Street | Conduct Road Safety Audit and implement eligible recommended improvements | 119600.76 | 118742.96 | 2016-09-16 | 0 | 2020-09-10 | 2023-11-28 | 118742.96 | Authorized | Authorized | No | Closed | Federal
H10-08-012 | 10 | 0 | 8 | Murrieta | Riverside County | SCAG | RCTC | Various locations citywide. | Install adaptive timing program at all City signalized intersections, including new traffic signal controllers and loops, as well as the required software and hardware at City Hall Traffic Management Center. | 854700 | 422350 | 0 | 0 | 0 | 0 | 0 | No PE | Past due (due 3/31/2025) | Yes (CON) | Not Started | State | 0
H9-08-013 | 9 | 5464033 | 8 | Murrieta | Riverside County | SCAG | RCTC | Five uncontrolled mid-block crosswalk locations near four school sites. | Install in-pavement LED lighted crosswalks and curb ramps. | 291100 | 247435 | 0 | 0 | 2025-08-28 | 0 | 247435 | No PE | Authorized | No | CON | Federal | 2
HSIP1-08-010 | 1 | 5464026 | 8 | Murrieta | Riverside County | SCAG | RCTC | Murrieta Hot Springs Road Between Alta Murrieta Drive And Margarita Road. | Construct Raised Traffic Medians. | 728805.69 | 503999.99 | 2008-08-06 | 0 | 2015-09-01 | 2018-04-26 | 503999.99 | Authorized | Authorized | No | Closed | Federal | 0
HSIP1-08-005 | 1 | 5092023 | 8 | Ontario | San Bernardino County | SCAG | SANBAG | Intersection Of Vineyard Avenue At Francis Street. | Install Traffic Signals. | 322893.33 | 207309.99 | 0 | 0 | 2010-04-26 | 2012-07-12 | 207309.99 | No PE | Authorized | No | Closed | Federal | 0
HSIP1-08-006 | 1 | 5092024 | 8 | Ontario | San Bernardino County | SCAG | SANBAG | Intersection Of Grove Avenue And Princeton Street. | Install Traffic Signals. | 184368.76 | 165931.88 | 0 | 0 | 2010-04-26 | 2012-05-21 | 165931.88 | No PE | Authorized | No | Closed | Federal | 0
HSIP2-08-004 | 2 | 5092025 | 8 | Ontario | San Bernardino County | SCAG | SANBAG | Grove Ave. At Sixth St. | Upgrade Traffic Signals And Modify Intersection Geometry. | 357620.51 | 321858.44 | 0 | 0 | 2010-04-26 | 2012-07-12 | 321858.44 | No PE | Authorized | No | Closed | Federal | 0
HSIP5-08-007 | 5 | 5092031 | 8 | Ontario | San Bernardino County | SCAG | SANBAG | Mission Blvd./Mountain Ave.; San Antonio Ave./Vine Ave. | Upgrade traffic signals; install left-turn phasing | 575183.6 | 364900 | 2013-12-18 | 0 | 2015-07-28 | 2017-09-18 | 364900 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-08-008 | 5 | 5092030 | 8 | Ontario | San Bernardino County | SCAG | SANBAG | Philadelphia St. from 500' W of Cypress Ave. to 310' E of Cypress Ave. | Install traffic signal and left-turn lanes; construct sidewalks | 903723.73 | 739999.98 | 2013-12-18 | 2016-05-13 | 2018-02-21 | 2022-10-25 | 739999.98 | Authorized | Authorized | No | Closed | Federal | 0
HSIP6-08-011 | 6 | 5092032 | 8 | Ontario | San Bernardino County | SCAG | SANBAG | S Campus Ave/E Philadelphia St | Install traffic signals | 355088.46 | 330458.83 | 2014-09-11 | 0 | 2016-11-16 | 2019-10-10 | 330458.83 | Authorized | Authorized | No | Closed | Federal
HSIP6-08-012 | 6 | 5092033 | 8 | Ontario | San Bernardino County | SCAG | SANBAG | N Baker Ave/E 6th St | Install traffic signals | 346786.06 | 271000.27 | 2014-09-11 | 0 | 2016-09-20 | 2020-10-06 | 271000.27 | Authorized | Authorized | No | Closed | Federal
H10-08-013 | 10 | 5414017 | 8 | Palm Desert | Riverside County | SCAG | RCTC | Various locations throughout the City. | Enhance the visibility of crosswalks. | 247200 | 247200 | 2021-06-09 | 0 | 2023-09-15 | 0 | 247200 | Authorized | Authorized | No | CON | State | 0
H10-08-014 | 10 | 5414018 | 8 | Palm Desert | Riverside County | SCAG | RCTC | Signalized intersections throughout the City. | Install retroreflective backplates and replace pedestrian signal heads with pedestrian countdown signals. | 1912600 | 1912600 | 2021-06-07 | 0 | 2025-06-03 | 0 | 1912600 | Authorized | Authorized | No | CON | State | 0
HSIP4-08-003 | 4 | 5414011 | 8 | Palm Desert | Riverside County | SCAG | RCTC | Fred Waring Dr./San Pascual Ave. | Modify intersection geometry; upgrade traffic signals | 170988.1 | 153769.6 | 0 | 0 | 2012-02-06 | 2013-06-25 | 153769.6 | No PE | Authorized | No | Closed | Federal | 0
H11-08-023 | 11 | 5282051 | 8 | Palm Springs | Riverside County | SCAG | RCTC | Various signalized intersections in the City of Palm Springs. | Installing LED pedestrian countdown signal heads, intersection lighting, upgrading signal equipment, and installing Leading Pedestrian Interval (LPI). | 2335600 | 2102040 | 2023-11-27 | 0 | 0 | 0 | 270000 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE | Federal | 2
H8-08-014 | 8 | 5282047 | 8 | Palm Springs | Riverside County | SCAG | RCTC | Fourteen (14) intersections throughout the city. | Modify traffic signal for improved visibility, install advanced dilemma zone detection, and add protected left-turn phasing | 4379128.98 | 2686600 | 2017-04-05 | 0 | 2021-06-15 | 2025-12-01 | 2686600 | Authorized | Authorized | No | Closed | Federal | 0
H8-08-015 | 8 | 5282048 | 8 | Palm Springs | Riverside County | SCAG | RCTC | Gene Autry Trail from Salvia Road to 1600 ft south of Salvia Road. | Install flashing beacon/changeable message signs and delineators. | 457942.75 | 390805 | 2017-04-05 | 0 | 2020-09-10 | 2024-02-12 | 390805 | Authorized | Authorized | No | Closed | Federal | 0
H9-08-014 | 9 | 5282049 | 8 | Palm Springs | Riverside County | SCAG | RCTC | Seven (7) signalized intersections throughout the City of Palm Springs. | Install advanced dilemma zone detection, protected left turns and pedestrian countdown heads. | 1865600 | 1865600 | 2019-10-22 | 0 | 2023-11-30 | 0 | 1865600 | Authorized | Authorized | No | CON | Federal | 2
HSIP1-08-008 | 1 | 5282028 | 8 | Palm Springs | Riverside County | SCAG | RCTC | Intersection Of Indian Canyon Drive At Tamarisk Road. | Install Traffic Signal And Lighting System, Including Emergency Vehicle Preemption | 180717 | 156570.28 | 2008-09-16 | 0 | 2008-09-16 | 2010-04-06 | 156570.28 | Authorized | Authorized | No | Closed | Federal | 0
HSIP7-08-015 | 7 | 5282046 | 8 | Palm Springs | Riverside County | SCAG | RCTC | Various intersections (17) throughout the City of Palm Springs | Modify traffic signal for improved visibility and install advanced dilemma zone detection. | 3764240.11 | 3764240.11 | 2016-07-22 | 0 | 2019-09-13 | 2025-02-19 | 3764240.11 | Authorized | Authorized | No | Closed | Federal
H10-08-015 | 10 | 5198027 | 8 | Perris | Riverside County | SCAG | RCTC | Ramona Expwy from Webster Ave to E Rider St; Nuevo Rd from Frontage rd to Dunlap Dr; W 4th St from Navajo Rd to Redlands Ave; Ethanac Rd from Murietta Rd to Case Rd. | Improve signalized intersection safety with retroreflective backplates, advanced dilemma zone detection, and radar speed signage along segments of priority corridors. | 3200000 | 1573700 | 0 | 0 | 2024-05-08 | 0 | 1173700 | No PE | Authorized | No | CON | State | 0
H10-08-016 | 10 | 5198026 | 8 | Perris | Riverside County | SCAG | RCTC | Ramona Expressway from N. Webster Ave to Rider St. (12 intersections, except for the intersection of Evans and Ramona Exp.) | Install enhanced crosswalks along a priority corridor to improve safety of pedestrian and bicyclists. | 292000 | 250000 | 0 | 0 | 2024-05-08 | 2026-01-27 | 250000 | No PE | Authorized | No | Closed | State | 0
H11-08-025 | 11 | 5198029 | 8 | Perris | Riverside County | SCAG | RCTC | A Street from Nuevo Rd to Mapes Dr. | Installation of rectangular rapid flashing beacons. | 159400 | 143460 | 0 | 0 | 2026-02-23 | 0 | 143460 | No PE | Authorized | No | CON | State | 0
H9-08-015 | 9 | 5198021 | 8 | Perris | Riverside County | SCAG | RCTC | Perris Blvd. Corridor from Ramona Exp. to 4th Street. | Modify signal phasing to implement a Leading Pedestrian Interval (LPI), review/modify signal & pedestrian crossing timing, add audio detection, install louvers/PV lights, upgrade ramps & median per ADA, and add a 2nd signal head on mast arm. | 789902.63 | 789902.63 | 0 | 0 | 2021-06-15 | 2023-10-24 | 789902.63 | No PE | Authorized | No | Closed | Federal | 0
HSIP5-08-010 | 5 | 5198018 | 8 | Perris | Riverside County | SCAG | RCTC | Various intersections throughout the city | Install pedestrian countdown heads | 572440.41 | 455999.99 | 0 | 0 | 2017-02-01 | 2023-10-25 | 455999.99 | No PE | Authorized | No | Closed | Federal | 0
H9-08-016 | 9 | 0 | 8 | Ramona Band of Cahuilla | Riverside County | SCAG | RCTC | Hog Lake Road (6S18), also referred to as Hog Lake Truck Trail. A 1.6 mile alignment from near the intersection with Bautista Road to the Ramona Reservation. | Upgrade existing stop signs and install new traffic signs. | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | Not Tracked | Not Tracked | No | Not Started | Federal | 0
H10-08-017 | 10 | 5420025 | 8 | Rancho Cucamonga | San Bernardino County | SCAG | SANBAG | Banyan St/East Ave, Base line Rd/Mountain View Dr S, Millennium Ct/Milliken Ave, Vintage Dr/Milliken Ave, Church St/Milliken Ave, Terra Vista Pkwy West/Church St, and Base Line Rd/Beryl St. | Upgrade seven (7) signalized intersections by replacing 34 five section signal heads (doghouse) with four section flashing yellow arrow (FYA) signal heads for protected/permissive left-turn controls and improving signal timing. | 325200 | 162600 | 2021-12-22 | 0 | 2022-06-22 | 2024-05-24 | 162600 | Authorized | Authorized | No | Closed | State | 0
H12-08-025 | 12 | 0 | 8 | Rancho Cucamonga | San Bernardino County | SCAG | SANBAG | Fairmont from Kenyon Way to Victoria Park Ln, Kenyon Way from Fairmont Way to Woodruff Pl, Woodruff Pl from Highland Ave to Kenyon Way, Highland Ave from Woodruff Pl to Day Creek Blvd. | Install Class II buffered bike lanes, Class II unbuffered bike lanes, Class III bike routes, install continental crosswalk and refresh existing striping. | 486800 | 348816 | 0 | 0 | 0 | 0 | 0 | No PE | Due by 3/31/2028 | No | Not Started | State | 0
H12-08-026 | 12 | 0 | 8 | Rancho Cucamonga | San Bernardino County | SCAG | SANBAG | Civic Center Drive from Haven Avenue to Utica Avenue. | Install rectangular rapid flashing beacons (RRFBs) and relocate crosswalk, construct ADA compliant access ramps and refuge island, and install Class II buffered bike lane and curb extensions. | 652500 | 350000 | 0 | 0 | 0 | 0 | 0 | No PE | Due by 3/31/2028 | No | Not Started | State | 0
H12-08-027 | 12 | 5420028 | 8 | Rancho Cucamonga | San Bernardino County | SCAG | SANBAG | Ten (10) signalized intersections: Day Creek Blvd/Foothill Blvd, Archibald Ave/Foothill Blvd, Foothill Blvd/Hermosa Ave, Foothill Blvd/Vineyard Ave, 19th St/Carnelian, Foothill Blvd/Hellman Ave, Archibald Ave/Base Line Rd, Foothill Blvd/Haven Ave, Base Line Rd/East Ave, and Elm Ave/Foothill Blvd. | Install retroreflective borders on signal head backplates, continental crosswalks, new signal heads, type 1A signal pole and new pull box, and upgrade an ADA ramp. | 556500 | 500850 | 2025-10-17 | 0 | 0 | 0 | 41760 | Authorized | Due by 3/31/2028 | No | PE | State | 0
HSIP4-08-019 | 4 | 5412010 | 8 | Rancho Mirage | Riverside County | SCAG | RCTC | Frank Sinatra Dr./SR 111 | Upgrade traffic signals and safety lighting; add turn lanes; construct curb and gutter | 1309592.08 | 900000 | 0 | 0 | 2014-03-12 | 2016-06-24 | 900000 | No PE | Authorized | No | Closed | Federal | 0
HSIP6-08-013 | 6 | 5412014 | 8 | Rancho Mirage | Riverside County | SCAG | RCTC | 27 intersections throughout Rancho Mirage | Upgrade traffic signals (interconnect); install pedestrian countdown signal heads | 2438151.39 | 1486000 | 2014-08-06 | 0 | 2019-05-24 | 2022-03-03 | 1486000 | Authorized | Authorized | No | Closed | Federal
HSIP6-08-014 | 6 | 5412015 | 8 | Rancho Mirage | Riverside County | SCAG | RCTC | On Monterey Ave between Gran Via-Avenida Las Palmas and Dinah Shore Dr, On Dinah Shore Dr between Monterey Ave and Key Largo Ave | Upgrade traffic signals (interconnect); install pedestrian countdown signal heads | 666564.82 | 574200 | 2014-08-04 | 0 | 2019-07-05 | 2022-03-03 | 574200 | Authorized | Authorized | No | Closed | Federal
H10-08-018 | 10 | 5083027 | 8 | Redlands | San Bernardino County | SCAG | SANBAG | The intersections of Dearborn Street and Orange Blossom Trail crossing, Berkeley Drive and Colton Avenue, Wabash Avenue and Los Altos Drive, and Judson Street and Orange Blossom Trail crossing. | Install pedestrian crossing with Rectangular Rapid Flashing Beacons (RRFBs) at uncontrolled crosswalks | 250000 | 250000 | 2023-02-08 | 0 | 2024-09-19 | 0 | 250000 | Authorized | Authorized | No | CON | State | 0
H11-08-026 | 11 | 5083029 | 8 | Redlands | San Bernardino County | SCAG | SANBAG | The intersection of San Bernardino Avenue and Church Street. | Install traffic signal. | 653600 | 588240 | 2023-10-30 | 0 | 0 | 0 | 103500 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE | State | 0
H11-08-027 | 11 | 5083028 | 8 | Redlands | San Bernardino County | SCAG | SANBAG | Various signalized intersections citywide. | Install larger signal heads and back-plate with reflective border. | 245000 | 220500 | 2023-10-25 | 0 | 0 | 0 | 38700 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE | State | 0
H12-08-028 | 12 | 5083032 | 8 | Redlands | San Bernardino County | SCAG | SANBAG | The intersection of Cajon Street and Cypress Avenue. | Install traffic signal. | 900000 | 810000 | 0 | 0 | 2025-07-17 | 0 | 810000 | No PE | Authorized | No | CON | State | 0
H8-08-016 | 8 | 5083020 | 8 | Redlands | San Bernardino County | SCAG | SANBAG | Various locations throughout the city. | Install emergency vehicle preemption at signalized intersections. | 1114690.67 | 1114690.67 | 2017-09-15 | 0 | 2022-03-30 | 2023-12-27 | 1114690.67 | Authorized | Authorized | No | Closed | Federal | 0
H8-08-017 | 8 | 5083021 | 8 | Redlands | San Bernardino County | SCAG | SANBAG | Various locations throughout the City. | Install pedestrian countdown heads at signalized intersections. | 244400 | 244400 | 2017-09-13 | 0 | 2022-03-07 | 2024-01-17 | 244400 | Authorized | Authorized | No | Closed | Federal | 0
H9-08-017 | 9 | 5083024 | 8 | Redlands | San Bernardino County | SCAG | SANBAG | Orange Blossom Trail at Alabama Street and Tennessee Street. | Install pedestrian crossings with enhanced safety features. | 249400.01 | 249400.01 | 2020-01-27 | 0 | 2023-02-23 | 2024-11-06 | 249400.01 | Authorized | Authorized | No | Closed | Federal | 2
HSIP4-08-004 | 4 | 5083014 | 8 | Redlands | San Bernardino County | SCAG | SANBAG | Various locations throughout the city | Upgrade crosswalks; install advance warning lights and signs; modify striping to narrow traffic lanes | 370436.9 | 326513.98 | 2012-04-17 | 0 | 2014-03-12 | 2017-04-03 | 326513.98 | Authorized | Authorized | No | Closed | Federal | 0
HSIP4-08-021 | 4 | 5083018 | 8 | Redlands | San Bernardino County | SCAG | SANBAG | Various locations throughout the city | Green bike lane enhancements | 201864 | 181652.8 | 0 | 0 | 2016-09-20 | 2018-03-27 | 181652.8 | No PE | Authorized | No | Closed | Federal | 0
HSIP6-08-015 | 6 | 5083016 | 8 | Redlands | San Bernardino County | SCAG | SANBAG | Pioneer Ave/Orange St | Install traffic signal | 336193.13 | 333270.09 | 2015-01-28 | 0 | 2016-09-20 | 2020-08-11 | 333270.09 | Authorized | Authorized | No | Closed | Federal
HSIP6-08-016 | 6 | 5083017 | 8 | Redlands | San Bernardino County | SCAG | SANBAG | On E Citrus Ave between University St and Wabash Ave | Install bike lanes | 359746 | 359746 | 2015-01-28 | 0 | 2016-09-20 | 2019-04-02 | 359746 | Authorized | Authorized | No | Closed | Federal
HSIP7-08-016 | 7 | 5083019 | 8 | Redlands | San Bernardino County | SCAG | SANBAG | -Redlands Boulevard (At the intersections of State, Ninth , Seventh and Fifth) -Orange Street (Shoppers Lane) -Citrus Avenue (Central Avenue) | Install rectangular rapid flashing beacons | 350291.28 | 266190.48 | 0 | 0 | 2019-02-25 | 2022-05-05 | 266190.48 | No PE | Authorized | No | Closed | Federal
H11-08-029 | 11 | 5205032 | 8 | Rialto | San Bernardino County | SCAG | SANBAG | Cedar Avenue and Merrill Avenue | Install protected left-turn phase and video detection system. Install pedestrian countdown heads and implement Leading Pedestrian Interval (LPI). | 413200 | 371880 | 2023-09-05 | 0 | 2024-07-22 | 0 | 371880 | Authorized | Authorized | No | CON | State | 0
H12-08-029 | 12 | 5205036 | 8 | Rialto | San Bernardino County | SCAG | SANBAG | 108 signalized intersections citywide. | Install new signal heads and controllers and implement leading pedestrian intervals (LPIs). | 5418000 | 4876200 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2025) | Due by 3/31/2028 | Yes (PE) | Not Started | Federal | 0
H12-08-031 | 12 | 5205034 | 8 | Rialto | San Bernardino County | SCAG | SANBAG | Two school crossings and other various locations. | Install rectangular rapid flashing beacons (RRFBs) at two school crossings and pedestrian crossing upgrades at various locations. | 298600 | 268740 | 2025-09-03 | 0 | 0 | 0 | 27000 | Authorized | Due by 3/31/2028 | No | PE | State | 0
H8-08-018 | 8 | 5205026 | 8 | Rialto | San Bernardino County | SCAG | SANBAG | Four (4) intersections: Baseline Rd at Sycamore Ave, Baseline Rd at Eucalyptus Ave, Etiwanda Ave at Cedar Ave, and Riverside Ave at Alder Ave. | Provide protected left turn phase; Improve signal hardware. | 1247558.32 | 1247558.32 | 2017-11-03 | 0 | 2020-01-29 | 2024-11-06 | 1247558.32 | Authorized | Authorized | No | Closed | Federal | 0
H8-08-019 | 8 | 5205027 | 8 | Rialto | San Bernardino County | SCAG | SANBAG | In the City of Rialto along West Baseline Road, From Lilac Avenue to Meridian Avenue. | Construct new 12 foot wide medians along Baseline Avenue from approximately 300 feet west of Willow Avenue to Meridian Avenue as well as installing median fencing on the south side of Eisenhower High School. | 1742457.39 | 1568211.65 | 2017-10-25 | 0 | 2022-08-11 | 2025-11-13 | 1568211.65 | Authorized | Authorized | No | Closed | Federal | 0
HSIP2-08-006 | 2 | 5205022 | 8 | Rialto | San Bernardino County | SCAG | SANBAG | Ayala Dr. Between Baseline Rd. And Sr 210 | Widen Roadway And Shoulders; Construct Curb, Gutter, Sidewalks, Curb Ramps And Bike Lanes | 5829646.43 | 634524.29 | 0 | 0 | 2015-09-01 | 2019-01-25 | 634524.29 | No PE | Authorized | No | Closed | Federal | 0
HSIP4-08-005 | 4 | 5205017 | 8 | Rialto | San Bernardino County | SCAG | SANBAG | Various locations throughout the city | Install pedestrian countdown heads | 247968 | 223171.2 | 0 | 0 | 2013-09-09 | 2015-05-15 | 223171.2 | No PE | Authorized | No | Closed | Federal | 0
HSIP6-08-017 | 6 | 5205020 | 8 | Rialto | San Bernardino County | SCAG | SANBAG | N Acacia Ave/E Baseline Rd | Upgrade traffic signals; Install protected left-turn phasing | 221296.11 | 221296.11 | 0 | 0 | 2015-08-04 | 2019-02-25 | 221296.11 | No PE | Authorized | No | Closed | Federal
HSIP7-08-017 | 7 | 5205024 | 8 | Rialto | San Bernardino County | SCAG | SANBAG | On Merrill Avenue from west city limits to Riverside Avenue. | Install 0.5 miles of Class III bike lanes and 1.5 miles of Class II bike lanes | 204457.7 | 183087.38 | 2016-12-09 | 0 | 2021-05-05 | 2025-04-30 | 183087.38 | Authorized | Authorized | No | Closed | Federal
H11-08-030 | 11 | 5058110 | 8 | Riverside | Riverside County | SCAG | RCTC | Signalized intersections and Mission Inn Avenue from Redwood Dr to Scout Lane. | Install retro-reflective signal backplates, implement Leading Pedestrian Interval (LPI) timing at all signals citywide, and construct a raised median along Mission Inn Avenue from Redwood Drive to Scout Lane. | 9018200 | 7815420 | 2023-11-27 | 0 | 2025-08-11 | 0 | 7815420 | Authorized | Authorized | No | CON | Federal | -2
H12-08-032 | 12 | 5058115 | 8 | Riverside | Riverside County | SCAG | RCTC | 160 signalized Intersections citywide. | Replace existing antiquated signal controllers with new 2070 signal controllers with updated software. | 1597600 | 798800 | 2025-11-18 | 0 | 0 | 0 | 50000 | Authorized | Due by 3/31/2028 | No | PE | State | 0
H12-08-033 | 12 | 5058114 | 8 | Riverside | Riverside County | SCAG | RCTC | Various signalized intersections, roadway segments and nonsignalized multi-way stop-controlled intersections citywide. | Install pedestrian median fencing, upgrade pedestrian crossings with enhanced safety features, and upgrade multi-way stop controlled intersections. | 5664100 | 5097690 | 2025-11-03 | 0 | 0 | 0 | 225000 | Authorized | Due by 3/31/2028 | No | PE | Federal | 2
H12-08-034 | 12 | 5058116 | 8 | Riverside | Riverside County | SCAG | RCTC | Van Buren Boulevard between Arlington Avenue and Magnolia Avenue. | Install / convert existing Class II bike lane to Class II buffered bike lane, including striping removals, new striping installation, pavement legends, bicycle detection, and signage modifications. | 348200 | 313380 | 2025-11-18 | 0 | 0 | 0 | 28800 | Authorized | Due by 3/31/2028 | No | PE | State | 0
H8-08-020 | 8 | 5058107 | 8 | Riverside | Riverside County | SCAG | RCTC | All currently interconnected traffic signals within the city. | Install new model 2070 controllers, with an upgraded controller software and central system. | 1932536 | 840000 | 0 | 0 | 2021-06-01 | 2025-12-01 | 840000 | No PE | Authorized | No | Closed | Federal | 0
HSIP4-08-006 | 4 | 5058087 | 8 | Riverside | Riverside County | SCAG | RCTC | Third St. (Blaine St.) between Mulberry St. and Watkins Dr. | Widen roadway; restripe to narrow traffic lanes and widen Class II bike lanes; install detection systems, signs, and pavement markings | 255471.4 | 229898.71 | 0 | 0 | 2014-01-24 | 2016-11-07 | 229898.71 | No PE | Authorized | No | Closed | Federal | 0
HSIP4-08-013 | 4 | 5058088 | 8 | Riverside | Riverside County | SCAG | RCTC | Canyon Crest Dr./Ransom Rd.; Canyon Crest Dr./Via Vista Dr.; Canyon Crest Dr./Mission Grove Pkwy. | Install traffic signals, signs, and striping | 493886.95 | 411111.48 | 0 | 0 | 2014-01-29 | 2016-02-10 | 411111.48 | No PE | Authorized | No | Closed | Federal | 0
HSIP5-08-012 | 5 | 5058092 | 8 | Riverside | Riverside County | SCAG | RCTC | Arlington Ave. from Fairhaven Dr. to the city limits | Widen and pave shoulders; install rumble strips, guardrail, safety lighting, signs and striping; construct right-turn and left-turn lanes and retaining wall; curve correction | 897411.53 | 564159.1 | 2014-01-30 | 0 | 2017-04-05 | 2019-11-19 | 564159.1 | Authorized | Authorized | No | Closed | Federal | 0
HSIP7-08-002 | 7 | 5058106 | 8 | Riverside | Riverside County | SCAG | RCTC | Various Locations throughout the City | Install High Friction Surface Treatment at five Locations, Construct 2 HAWK Signals, deploy new signal timing plans for 35 traffic signals in the Downtown Area | 1874363.42 | 1439002.97 | 0 | 0 | 2020-09-10 | 2025-01-30 | 1439002.97 | No PE | Authorized | No | Closed | Federal
H10-08-019 | 10 | 5956281 | 8 | Riverside County | Riverside County | SCAG | RCTC | Cajalco Road between La Sierra Avenue and Kirkpatrick Road and between Harley John Road and Wood Rood; and Lake Mathews Drive between Capello Drive and Malta Place. | Upgrade existing guardrail / end treatments to meet current Caltrans standards. | 1267839 | 1000000 | 2021-07-20 | 2023-01-19 | 2025-03-11 | 0 | 1000000 | Authorized | Authorized | No | CON | Mix | 1
H10-08-027 | 10 | 5956282 | 8 | Riverside County | Riverside County | SCAG | RCTC | Highway 74 from 7th Street to Crumpton Road in the County of Riverside, including 5 traffic signals and 18 unsignalized intersections. | Install raised median along 6.15 miles of Highway 74 between 7th St. and Crumpton Road, with left-turn pockets at select intersections. Install advanced detection for high-speed approaches and upgrade existing equipment at 5 signalized intersections. | 11002200 | 9901980 | 2021-07-23 | 0 | 0 | 0 | 1327320 | Authorized | Due in no more than 4 months | No | PE | State | 0
H8-08-021 | 8 | 5956263 | 8 | Riverside County | Riverside County | SCAG | RCTC | Gilman Springs Road between approx. 8,900 ft S/O Alessandro Blvd and approx. 5,100 ft S/O Bridge St, in the Moreno Valley area. | Construct median and paved shoulders, centerline/edgeline rumble stripes and other incidental work. | 26873579 | 20315299.22 | 2017-06-15 | 0 | 2023-08-11 | 0 | 20315299 | Authorized | Authorized | No | CON | Federal | 1
H8-08-022 | 8 | 5956264 | 8 | Riverside County | Riverside County | SCAG | RCTC | Reche Vista Dr between City of Moreno Valley & Reche Canyon Rd, Reche Canyon Rd between Reche Vista Dr & approx. 500 ft north of Woodson Rd, and La Sierra Ave between El Sobrante Rd & Orchard View Ln. | Upgrade existing guardrail/end treatments. | 903243.48 | 875106.43 | 2017-06-15 | 0 | 2019-03-28 | 2020-10-14 | 875106.43 | Authorized | Authorized | No | Closed | Federal | 0
H9-08-018 | 9 | 5956274 | 8 | Riverside County | Riverside County | SCAG | RCTC | Various high profile roadway corridors, including Cajalco Rd between Wood Rd and Temescal Canyon Rd, Gavilan Rd between Cajalco Rd and Lake Matthews Rd, and Sage Rd between Cactus Valley Rd and SH 79 | Review horizontal alignment warning signs per the CA MUTCD mandate. Establish County procedures/ methodologies regarding horizontal alignment warning signs. | 230000 | 230000 | 2019-06-12 | 0 | 0 | 2024-11-13 | 230000 | Authorized | No CON | No | Closed | Federal | 0
H9-08-019 | 9 | 5956272 | 8 | Riverside County | Riverside County | SCAG | RCTC | Cajalco Road between La Sierra Avenue and Temescal Canyon Road. | Upgrade existing guardrail/end treatments to meet current standards. | 640139.95 | 615216.51 | 2019-06-12 | 0 | 2020-11-25 | 2022-11-16 | 615216.51 | Authorized | Authorized | No | Closed | Federal | 0
HRRR1-08-046 | 1 | 5956182 | 8 | Riverside County | Riverside County | SCAG | RCTC | El Sobrante Rd. - Segment 3 - (Mockingbird Canyon to Cajalco Roads) and Segment 1- (McAllister St. to 1 mile Easterly) | Widen or Improve Shoulder; Roadway Illumination (where no lighting exists) | 814245.69 | 703096.41 | 0 | 0 | 2010-08-02 | 2018-05-11 | 703096.41 | No PE | Authorized | No | Closed | Federal | 0
HRRR1-08-047 | 1 | 5956186 | 8 | Riverside County | Riverside County | SCAG | RCTC | Mountain View Rd. from Varner Rd. to 500ft North of Club House Dr. | Widen or Improve Shoulder; New left-turn lane at nonsignalized intersection | 655815.07 | 560647.3 | 0 | 0 | 2010-09-14 | 2013-05-01 | 560647.3 | No PE | Authorized | No | Closed | Federal | 0
HSIP1-08-011 | 1 | 5956174 | 8 | Riverside County | Riverside County | SCAG | RCTC | The Westerly Side Of Mountain View Road, Approx. 0.85 Miles North Of Dillon Road. | Install Approx. 600 Lf Of Metal Beam Guardrails. | 137492.02 | 90520.94 | 0 | 0 | 2008-08-11 | 2012-01-26 | 90520.94 | No PE | Authorized | No | Closed | Federal | 0
HSIP1-08-012 | 1 | 5956175 | 8 | Riverside County | Riverside County | SCAG | RCTC | The Intersection Of Bundy Canyon Rd. And The Farm Rd. | Install Traffic Signals. | 205561.02 | 162998.34 | 0 | 0 | 2008-06-27 | 2012-01-26 | 162998.34 | No PE | Authorized | No | Closed | Federal | 0
HSIP2-08-001 | 2 | 5956189 | 8 | Riverside County | Riverside County | SCAG | RCTC | Intersection Of Rubidoux Blvd. And 28Th St. | Install Traffic Signal, Left-Turn Lanes, Signs, Stripes, And Markings | 824769.16 | 716916.24 | 0 | 0 | 2012-08-13 | 2014-09-02 | 716916.24 | No PE | Authorized | No | Closed | Federal | 0
HSIP2-08-002 | 2 | 5956191 | 8 | Riverside County | Riverside County | SCAG | RCTC | Leon Rd. From Scott Rd. To Keller Rd. | Realign Verical Profile; Install Signs, Striping And Markings | 1876912.46 | 900000 | 0 | 0 | 2012-09-12 | 2016-02-08 | 900000 | No PE | Authorized | No | Closed | Federal | 0
HSIP2-08-003 | 2 | 5956190 | 8 | Riverside County | Riverside County | SCAG | RCTC | Intersection Of Market St. And Agua Mansa Rd. | Intall Traffic Signal, Raised Median, Signs, Stripes And Markings | 1216589.53 | 457380 | 0 | 0 | 2014-03-13 | 2019-01-17 | 457380 | No PE | Authorized | No | Closed | Federal | 0
HSIP3-08-005 | 3 | 5956202 | 8 | Riverside County | Riverside County | SCAG | RCTC | Sierra Ave. Between Karen Ln. And The Riverside/San Bernardino County Line | Install Two Solar-Powered Radar Speed Feedback Signs, Centerline And Edgeline Rumble Strips, Anti-Skid Pavement Overlay, Signs, Stripes And Pavement Markings | 398817.85 | 293580 | 0 | 0 | 2013-01-31 | 2014-10-17 | 293580 | No PE | Authorized | No | Closed | Federal | 0
HSIP3-08-006C | 3 | 5956204 | 8 | Riverside County | Riverside County | SCAG | RCTC | Gilman Springs Rd. Between Riverside County/Moreno Valley Limits To 2.26 Miles Southeasterly | Widen Shoulder; Install Centerline And Edgeline Rumble Strips | 5059800.96 | 1585800 | 0 | 0 | 2013-05-14 | 2015-12-11 | 1585800 | No PE | Authorized | No | Closed | Federal | 0
HSIP4-08-011 | 4 | 5956203 | 8 | Riverside County | Riverside County | SCAG | RCTC | Cajalco Rd./Alexander St. | Install traffic signals, signs, striping, and pavement markings; construct left-turn lanes | 519248.91 | 311400 | 0 | 0 | 2012-09-17 | 2015-04-27 | 311400 | No PE | Authorized | No | Closed | Federal | 0
HSIP5-08-013 | 5 | 5956219 | 8 | Riverside County | Riverside County | SCAG | RCTC | Thousand Palms Canyon Rd. from approximately 1.5 miles N of Ramon Rd. to approximately 2.5 miles S of Dillon Rd. | Widen roadway; install left-turn lane; resurface roadway | 1070025.85 | 662390.75 | 2013-04-19 | 0 | 2017-10-24 | 2019-10-10 | 662390.75 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-08-014 | 5 | 5956218 | 8 | Riverside County | Riverside County | SCAG | RCTC | El Sobrante Rd. N of Cajalco Rd.; Cajalco Rd. W of Hollis Ln.; San Timoteo Canyon Rd. between Live Oak Canyon Rd. and Redlands Blvd.; Soboba Rd. W of city limits; Van Buren Blvd. S of Mockingbird Canyon Rd. | Install solar-powered speed feedback signs | 511316.24 | 348823.6 | 2013-04-24 | 0 | 2015-08-07 | 2017-03-24 | 348823.6 | Authorized | Authorized | No | Closed | Federal | 0
HSIP6-08-018 | 6 | 5956237 | 8 | Riverside County | Riverside County | SCAG | RCTC | On Gilman Springs Rd-State St between approx. 1,000' NW of Gilman Springs Rd-State St/ Soboba Rd, and approx. 4,000' NW of Gilman Springs Rd-State St/ Soboba Rd | Improve horizontal and vertical alignments and other roadway safety features | 2362234.64 | 1324994.49 | 0 | 0 | 2016-06-16 | 2018-10-19 | 1324994.49 | No PE | Authorized | No | Closed | Federal
HSIP6-08-019 | 6 | 5956236 | 8 | Riverside County | Riverside County | SCAG | RCTC | Grapefruit Blvd (SR111)/62nd Ave | Install traffic signal; upgrade railroad crossing; widen roadway; and install other safety improvements | 2573992 | 1221800 | 2014-09-16 | 0 | 2018-08-16 | 2024-11-12 | 1221800 | Authorized | Authorized | No | Closed | Federal
HSIP7-08-018 | 7 | 5956253 | 8 | Riverside County | Riverside County | SCAG | RCTC | The proposed project is located on Cajalco Road, between a point approx. 1,000' west of Brown Street and a approx. point 1,000' east of Day Street, in the Perris area of Unincorporated Riverside County. | Roadway improvements to accommodate a two-way left-turn lane, traffic signal modifications | 5032088.83 | 3680460 | 0 | 0 | 2019-09-19 | 2024-12-03 | 3680460 | No PE | Authorized | No | Closed | Federal
HSIP7-08-019 | 7 | 5956260 | 8 | Riverside County | Riverside County | SCAG | RCTC | Project is located at 2 separate locations; Harrison St between 54th Ave and 81st Ave (Thermal area), and San Timoteo Canyon Rd between Redlands Blvd and the City of Beaumont limits (Moreno Valley area). | Conduct a Roadway Safety Audit, install centerline rumble stripe, upgrade painted edgeline with thermoplastic striping, and install/upgrade signs with new fluorescent sheeting (regulatory or warning) | 742733.71 | 668460.33 | 2016-09-26 | 0 | 2019-03-28 | 2023-11-07 | 668460.33 | Authorized | Authorized | No | Closed | Federal
H12-08-035 | 12 | 5033060 | 8 | San Bernardino | San Bernardino County | SCAG | SANBAG | E Street from Fairway Drive to 10th Street. | Install a hard median. | 3503000 | 3152700 | 2025-07-14 | 0 | 0 | 0 | 242550 | Authorized | Due by 3/31/2028 | No | PE | Federal | 0
H9-08-020 | 9 | 5033057 | 8 | San Bernardino | San Bernardino County | SCAG | SANBAG | Fourty-nine (49) signalized intersections along Mt. Vernon Avenue from Highland Avenue to Johnston Street, Baseline Street from Del Rosa Avenue to California Street, and Highland Avenue from Medical Center Drive to Victoria Avenue. | Implement advanced dilemma zone detection. | 4341400 | 4341400 | 2019-05-22 | 0 | 2022-03-07 | 0 | 4341400 | Authorized | Authorized | No | CON | Federal | 0
H9-08-021 | 9 | 5033056 | 8 | San Bernardino | San Bernardino County | SCAG | SANBAG | Two hundred twenty-four (224) signalized intersections on various arterials. | Upgrade various signal hardware components, including traffic signal heads, push buttons, and pedestrian signal heads. | 5490800 | 5490800 | 2019-05-22 | 0 | 2021-09-08 | 0 | 5164265 | Authorized | Authorized | No | CON | Federal | 0
HSIP1-08-001 | 1 | 5033046 | 8 | San Bernardino | San Bernardino County | SCAG | SANBAG | 10 High-Accident Locations Throughout City. | Install Radar Speed Feedback Signs. | 99385.76 | 89447.18 | 0 | 0 | 2013-06-12 | 2017-05-19 | 89447.18 | No PE | Authorized | No | Closed | Federal | 0
HSIP1-08-003 | 1 | 5033045 | 8 | San Bernardino | San Bernardino County | SCAG | SANBAG | Industrial Parkway Between Palm Avenue And Lexington Way. | Install Two-Way Left-Turn Lane; Restrict Parking. | 35963.35 | 32018.38 | 0 | 0 | 2014-08-15 | 2016-11-07 | 32018.38 | No PE | Authorized | No | Closed | Federal | 0
HSIP4-08-010 | 4 | 5033051 | 8 | San Bernardino | San Bernardino County | SCAG | SANBAG | Ninth St./Arrowhead Ave. | Upgrade traffic signals; install protected left-turn phasing | 328346.1 | 158699.51 | 0 | 0 | 2016-08-11 | 2021-05-18 | 158699.51 | No PE | Authorized | No | Closed | Federal | 0
HSIP4-08-016 | 4 | 5033050 | 8 | San Bernardino | San Bernardino County | SCAG | SANBAG | Ninth St./Sierra Way | Install protected/permissive left-turn phasing and pedestrian countdown heads; construct curb ramps | 394057.29 | 161038.29 | 0 | 0 | 2016-08-11 | 2021-10-13 | 161038.29 | No PE | Authorized | No | Closed | Federal | 0
H11-08-031 | 11 | 5954196 | 8 | San Bernardino County | San Bernardino County | SCAG | SANBAG | Nine rural roadway segments (Arrowhead Lake Road, Rock Springs Road/Roundup Way, Sheep Creek Road, Wilson Ranch Road, Santa Fe Avenue, Pioneertown Road, Pipes Canyon Road, Camp Rock Road and Parker Dam Road). | Install centerline and edgeline rumble stripes with raised pavement markers. | 5983300 | 4994830 | 2023-09-18 | 0 | 0 | 0 | 750600 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE | State | 0
H11-08-032 | 11 | 5954197 | 8 | San Bernardino County | San Bernardino County | SCAG | SANBAG | 50 rural intersections along high-speed roadways with no intersection lighting. | Install stop signs and flashing beacons in advance of the stop signs, W4-4P 'Cross Traffic Does Not Stop' signs, and transverse rumble strips on County-maintained minor stop-controlled approaches. | 1392000 | 1252800 | 2023-08-11 | 0 | 0 | 0 | 164700 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE | Federal | 1
H11-08-033 | 11 | 5954198 | 8 | San Bernardino County | San Bernardino County | SCAG | SANBAG | Cajon Boulevard from Cleghorn Road to Kenwood Avenue. | Install centerline and edgeline rumble stripes with raised pavement markers. Install a 2ft painted median, with flexible delineators where passing is not permitted. Install flashing beacon on "Stop Ahead" sign prior to Kenwood Avenue. | 1314500 | 1183050 | 2023-08-18 | 0 | 0 | 0 | 166500 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE | Federal | 1
H11-08-034 | 11 | 5954199 | 8 | San Bernardino County | San Bernardino County | SCAG | SANBAG | Oak Glen Road east of the City of Yucaipa, generally between Chagall Road and Pisgah Peak-Oak Glen Road; Lone Pine Canyon Road, between Heath Creek Drive and SR-138; Lytle Creek Road between 1500 feet west of Sycamore Drive and Glen Helen Parkway. | Install centerline and edgeline rumble stripes with raised pavement markers. Install chevron signs on curved roadway segments. | 2854800 | 2569320 | 2023-08-18 | 0 | 0 | 0 | 360000 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE | Federal | 1
H9-08-022 | 9 | 5954160 | 8 | San Bernardino County | San Bernardino County | SCAG | SANBAG | The intersections of Phelan Road with Arrowhead Rd, Sunny Vista Rd, Tumbleweed Rd and Sonora Rd, in the unincorporated community of Phelan. | Install left-turn and right-turn lanes with acceleration lanes. | 2425416.67 | 1885925 | 2019-04-15 | 0 | 2022-02-02 | 2024-05-01 | 1885925 | Authorized | Authorized | No | Closed | Federal | 1
HSIP3-08-002 | 3 | 5954117 | 8 | San Bernardino County | San Bernardino County | SCAG | SANBAG | Valley Blvd. Between Linden Ave. And Spruce Ave. | Construct Raised Median | 867105.39 | 715599.72 | 2010-09-09 | 0 | 2013-05-20 | 2015-05-15 | 715599.72 | Authorized | Authorized | No | Closed | Federal | 0
HSIP3-08-003 | 3 | 5954118 | 8 | San Bernardino County | San Bernardino County | SCAG | SANBAG | Cedar Ave. Between Jurupa Ave. And El Rivino Rd. | Construct Raised Median | 1034664.77 | 783921.31 | 2010-08-27 | 0 | 2013-05-24 | 2015-05-08 | 783921.31 | Authorized | Authorized | No | Closed | Federal | 0
HSIP4-08-012 | 4 | 5954125 | 8 | San Bernardino County | San Bernardino County | SCAG | SANBAG | Beech Ave., near Beech Ave. Elementary School | Install in-pavement crosswalk lights | 150023.29 | 46800 | 2012-01-11 | 0 | 2014-02-27 | 2015-12-21 | 46800 | Authorized | Authorized | No | Closed | Federal | 0
HSIP4-08-018 | 4 | 5954126 | 8 | San Bernardino County | San Bernardino County | SCAG | SANBAG | Valley Blvd. between Locust Ave. and Linden Ave. | Construct raised median | 698099.89 | 578845.92 | 2012-01-11 | 0 | 2013-05-20 | 2015-12-11 | 578845.92 | Authorized | Authorized | No | Closed | Federal | 0
H10-08-020 | 10 | 0 | 8 | San Jacinto | Riverside County | SCAG | RCTC | San Jacinto Ave. (formerly SR79) between Menlo Avenue and Commonwealth Ave. | Install Pedestrian Hybrid Beacon (PHB) with enhanced pedestrian refuge island mid-block; install sidewalk on west and east side of San Jacinto from Commonwealth to Menlo; install roadway lighting; and install additional signage. | 677100 | 440100 | 0 | 0 | 0 | 0 | 0 | No PE | Past due (due 3/31/2024) | Yes (CON) | Not Started | State | 0
H8-08-023 | 8 | 5075021 | 8 | San Jacinto | Riverside County | SCAG | RCTC | Sanderson Avenue between Ramona Expressway and Cottonwood Avenue. | Widen paved shoulders, install crash impact attenuators around fixed objects, install centerline rumble strips, add safety lighting, install radar speed limit signs and re-stripe roadway. | 872713.24 | 529315.66 | 0 | 0 | 2019-11-22 | 2021-11-24 | 529315.66 | No PE | Authorized | No | Closed | Federal | 0
H9-08-023 | 9 | 5075019 | 8 | San Jacinto | Riverside County | SCAG | RCTC | The intersection of San Jacinto Ave and Shaver St. | Install traffic signal with protected left turn phasing, pedestrian push buttons and leading pedestrian intervals; construct ADA ramps; install sidewalk on the E/S of San Jacinto Ave. | 840584.89 | 576581.23 | 0 | 0 | 2023-05-22 | 2025-10-20 | 576581.23 | No PE | Authorized | No | Closed | Federal | 2
HSIP5-08-016 | 5 | 5075015 | 8 | San Jacinto | Riverside County | SCAG | RCTC | Various intersections throughout the city | Install pedestrian countdown heads | 222942 | 200647.8 | 0 | 0 | 2016-08-11 | 2019-01-15 | 200647.8 | No PE | Authorized | No | Closed | Federal | 0
HSIP6-08-021 | 6 | 5075016 | 8 | San Jacinto | Riverside County | SCAG | RCTC | 33 intersections throughout the City of San Jacinto. | Install crosswalks and signs | 254550.87 | 206425.86 | 2015-01-28 | 0 | 2017-04-06 | 2018-07-17 | 206425.86 | Authorized | Authorized | No | Closed | Federal
H11-08-035 | 11 | 5459034 | 8 | Temecula | Riverside County | SCAG | RCTC | 54 intersections throughout the City of Temecula. | Install pedestrian countdown signal heads and upgrade traffic signal signal controllers for operations. | 547700 | 492930 | 0 | 0 | 2024-01-26 | 0 | 492930 | No PE | Authorized | No | CON | State | 0
H11-08-036 | 11 | 5459035 | 8 | Temecula | Riverside County | SCAG | RCTC | 127 intersections throughout the City of Temecula. | Upgrade traffic signal hardware including LED safety lighting, vehicle signal heads, retro-reflective backplates, signal wiring, and traffic signal cabinets; Upgrade signal timing and communications network equipment. | 3205900 | 2441310 | 2023-09-27 | 0 | 2025-08-28 | 0 | 2438101 | Authorized | Authorized | No | CON | State | 0
H11-08-037 | 11 | 5459036 | 8 | Temecula | Riverside County | SCAG | RCTC | Various school ramp locations citywide. | Citywide upgrade of school curb ramps prioritizing locations. | 250000 | 225000 | 0 | 0 | 2024-04-09 | 0 | 225000 | No PE | Authorized | No | CON | State | 0
H11-08-038 | 11 | 5459037 | 8 | Temecula | Riverside County | SCAG | RCTC | Major bicycle corridors in city including Jefferson Ave, Ynez Rd, Margarita Rd, Pechanga Pkwy, Winchester Rd, Rancho California Rd, and Temecula Pkwy. | Citywide installation of green bike lanes pavement markings to increase visibility of cyclists and identify potential areas of conflict with turning motorists. | 249500 | 224550 | 0 | 0 | 2025-03-04 | 0 | 224550 | No PE | Authorized | No | CON | State | 0
H12-08-036 | 12 | 0 | 8 | Temecula | Riverside County | SCAG | RCTC | 41 intersections throughout the City of Temecula. | Install traffic signal hardware and communication interconnect system upgrades to improve traffic signal timing and optimize operations. | 1105700 | 552850 | 0 | 0 | 0 | 0 | 0 | No PE | Due by 3/31/2028 | No | Not Started | State | 0
H9-08-024 | 9 | 5459029 | 8 | Temecula | Riverside County | SCAG | RCTC | Signalized locations on corridors, including Butterfield Stage Rd, Jefferson Ave, Margarita Rd, Pechanga Pkwy, Rancho California Rd, Redhawk Pkwy, Temecula Pkwy, and Ynez Rd. | Install pedestrian countdown signal heads, ADA-compliant pedestrian pushbuttons, and upgrade traffic signal controllers. | 804251 | 804250.99 | 0 | 0 | 2021-01-06 | 2024-10-31 | 804250.99 | No PE | Authorized | No | Closed | Federal | 0
H9-08-025 | 9 | 5459028 | 8 | Temecula | Riverside County | SCAG | RCTC | Signalized intersections of Margarita Road and Verdes Lane, Redhawk Parkway and Paseo Parallon/Overland Trail, and Winchester Road and Enterprise Circle. | Upgrade existing permissive left-turn phases and signal heads with protected left-turn phases on existing and/or new traffic signal poles and mast arms. | 546613.78 | 453252.14 | 0 | 0 | 2023-02-02 | 2025-10-20 | 453252.14 | No PE | Authorized | No | Closed | Federal | 0
HSIP7-08-020 | 7 | 5459026 | 8 | Temecula | Riverside County | SCAG | RCTC | Signalized intersections along the following corridors within the City Limits: Winchester Road, Rancho California Road, and Temecula Parkway. | Install fiber optic communication system upgrades including: conduit, cable, controllers and related communication equipment to improve safety and operations via optimized traffic signal timing coordination | 1390942.47 | 1207557.8 | 0 | 0 | 2021-02-03 | 2024-10-31 | 1207557.8 | No PE | Authorized | No | Closed | Federal
H10-08-021 | 10 | 5448011 | 8 | Twentynine Palms | San Bernardino County | SCAG | SANBAG | Six intersections along the arterial streets of Two Mile Road, Amboy Road and Utah Trail. | Install flashing beacons at stop controlled intersections and upgrade intersection intersection pavement markings. | 426600 | 400600 | 2021-05-06 | 0 | 2023-09-05 | 2025-11-24 | 400600 | Authorized | Authorized | No | Closed | State | 0
H9-08-026 | 9 | 5448009 | 8 | Twentynine Palms | San Bernardino County | SCAG | SANBAG | Residential area (high speed rural residential/local area) south of Two Mile Rd, North of Baseline Rd, East of Encelia Ave, and west of Elm Ave. | Upgrade intersection pavement markings and installing advance flashing beacons for advance warning. | 958607.74 | 958607.74 | 2019-09-13 | 0 | 2022-08-04 | 2024-11-04 | 958607.74 | Authorized | Authorized | No | Closed | Federal | 0
HSIP7-08-001 | 7 | 5448008 | 8 | Twentynine Palms | San Bernardino County | SCAG | SANBAG | State Route 62 between Encelia Avenue and Larrea Avenue (approximately 0.6 miles). | Install sidewalk infrastructure on the south side of the highway and across a culvert. Pedestrian crossing signage and high-visibility crosswalk pavement markings will be installed at Encelia and Larrea Avenues. | 1153139.92 | 778612 | 0 | 0 | 2019-05-22 | 2021-02-01 | 778612 | No PE | Authorized | No | Closed | Federal
H11-08-039 | 11 | 5147016 | 8 | Upland | San Bernardino County | SCAG | SANBAG | 54 signalized intersections in Upland. | Replace all existing signal heads with 12-inch signal heads and retro-reflective back plates; and install pedestrian countdown heads at key locations. | 2060000 | 1854000 | 2023-12-04 | 0 | 2025-11-05 | 0 | 1718820 | Authorized | Authorized | No | CON | State | 0
H10-08-022 | 10 | 5380043 | 8 | Victorville | San Bernardino County | SCAG | SANBAG | Seventh Street between Sage Street and C Street. | Implement a variety of safety improvements to existing signalized intersections, such as adding mast arms, lighting, enhancing video detection and upgrading PBS system. | 3164100 | 1320000 | 0 | 0 | 2023-10-20 | 0 | 1320000 | No PE | Authorized | No | CON | State | 0
H10-08-023 | 10 | 5380040 | 8 | Victorville | San Bernardino County | SCAG | SANBAG | Intersection of Village Dr and Tawney Ridge Ln. | Upgrade the intersection from 2-way STOP control to actuated Traffic Signal. | 569000 | 539000 | 0 | 0 | 2022-01-10 | 2024-08-20 | 539000 | No PE | Authorized | No | Closed | State | 0
H11-08-040 | 11 | 5380041 | 8 | Victorville | San Bernardino County | SCAG | SANBAG | Intersection of Village Dr and Puesta Del Sol Dr. | Upgrade intersection from 2-way stop control to actuated traffic signal. | 625000 | 526500 | 0 | 0 | 2023-10-25 | 0 | 526500 | No PE | Authorized | No | CON | State | 0
H11-08-041 | 11 | 5380044 | 8 | Victorville | San Bernardino County | SCAG | SANBAG | Nine (9) School Crossing locations. | Install Rectangular Rapid Flashing Beacon (RRFB). | 176900 | 149310 | 0 | 0 | 2025-08-06 | 0 | 149310 | No PE | Authorized | No | CON | State | 0
H11-08-042 | 11 | 5380042 | 8 | Victorville | San Bernardino County | SCAG | SANBAG | All 96 city-owned traffic signals. | Install retroreflective border to traffic signal backplates. | 111600 | 100440 | 0 | 0 | 2023-09-05 | 0 | 100440 | No PE | Authorized | No | CON | State | 0
H9-08-027 | 9 | 5380037 | 8 | Victorville | San Bernardino County | SCAG | SANBAG | The intersection of Mojave Dr and Condor Rd. | Upgrade from 2-way STOP control to actuated traffic signal. | 778318.25 | 762930 | 0 | 0 | 2023-05-16 | 2026-01-08 | 762930 | No PE | Authorized | No | Closed | Federal | 0
H9-08-028 | 9 | 5380038 | 8 | Victorville | San Bernardino County | SCAG | SANBAG | Various locations along major roadways, including National Trails Highway, Amargosa Rd, Hesperia Rd, Outer Bear Valley Rd, Petaluma Rd, and Amethyst Rd. | Upgrade existing guardrails and terminal system end treatments to meet current standards. | 669322 | 669322 | 0 | 0 | 2022-05-13 | 2024-03-04 | 669322 | No PE | Authorized | No | Closed | Federal | 0
HSIP4-08-007 | 4 | 5380029 | 8 | Victorville | San Bernardino County | SCAG | SANBAG | Amethyst Rd./Hook Blvd. | Install traffic signal, signs, striping, and pavement markings; construct curb ramp | 372098.13 | 334888.31 | 0 | 0 | 2015-07-15 | 2017-10-11 | 334888.31 | No PE | Authorized | No | Closed | Federal | 0
HSIP6-08-022 | 6 | 5380033 | 8 | Victorville | San Bernardino County | SCAG | SANBAG | On El Evado Rd 460' north of Hook Blvd and 800' south of Mojave Dr | Widen and pave shoulders | 173573.7 | 144297.46 | 0 | 0 | 2017-06-15 | 2020-04-23 | 144297.46 | No PE | Authorized | No | Closed | Federal
HSIP6-08-023 | 6 | 5380030 | 8 | Victorville | San Bernardino County | SCAG | SANBAG | Mojave Dr/E Trail | Install traffic signals | 417738.3 | 353798.57 | 0 | 0 | 2017-06-15 | 2020-04-27 | 353798.57 | No PE | Authorized | No | Closed | Federal
HSIP6-08-024 | 6 | 5380031 | 8 | Victorville | San Bernardino County | SCAG | SANBAG | Nisqualli Rd/1st Ave | Install traffic signals | 601951 | 368000 | 0 | 0 | 2016-07-15 | 2018-05-30 | 368000 | No PE | Authorized | No | Closed | Federal
H10-08-024 | 10 | 5484018 | 8 | Wildomar | Riverside County | SCAG | RCTC | Intersection of Bundy Canyon Road and Harvest Way (three-leg intersection). | Install new traffic signal. | 272900 | 272900 | 0 | 0 | 2025-01-02 | 0 | 272900 | No PE | Authorized | No | CON | State | 0
H10-08-025 | 10 | 5484015 | 8 | Wildomar | Riverside County | SCAG | RCTC | Two signalized intersections: Bundy Canyon Road & Orange Street, and Corydon Road & Grand Avenue. | Replace existing vehicle heads with LED vehicle heads with retro-reflective backing plates, provide advanced dilemma zone detection, and add a protected left-turn phases. | 527600 | 527600 | 2022-04-05 | 0 | 2025-07-10 | 0 | 527600 | Authorized | Authorized | No | CON | State | 0
H11-08-043 | 11 | 0 | 8 | Wildomar | Riverside County | SCAG | RCTC | Mission Trail from Malaga Road to Corydon Street, and Corydon Street from Grand Avenue to Mission Trail. | Install pedestrian countdown signal heads, pedestrian crosswalk enhancements, ADA Systems at signalized intersections, high visibility crosswalks, and pedestrian curb ramps. | 176100 | 158490 | 0 | 0 | 0 | 0 | 0 | No PE | Past due (due 3/31/2026) | Yes (CON) | Not Started | State | 0
H12-08-037 | 12 | 0 | 8 | Wildomar | Riverside County | SCAG | RCTC | Bundy Canyon Rd. at The Farm Rd., Bundy Canyon Rd. at Orange St., Mission Trl. at Bundy Canyon Rd., Mission Trl. at Canyon Dr., Wildomar Trl. at Cervera Rd., Wildomar Trl. at Palomar St., Palomar St. at Gruwell St., and other locations citywide. | Install leading pedestrian interval (LPI), audible push buttons and enhanced crosswalk striping at signalized intersections; install rectangular rapid flashing beacons (RRFBs) and mid block crossings for Class I trail. | 590000 | 346500 | 0 | 0 | 0 | 0 | 0 | No PE | Due by 3/31/2028 | No | Not Started | State | 0
H12-08-038 | 12 | 0 | 8 | Wildomar | Riverside County | SCAG | RCTC | Arterial and collector roadways Citywide. | Install edgelines. | 622000 | 348920 | 0 | 0 | 0 | 0 | 0 | No PE | Due by 3/31/2028 | No | Not Started | State | 0
H12-08-039 | 12 | 0 | 8 | Wildomar | Riverside County | SCAG | RCTC | Bundy Canyon Road from Mission Trail to Orange Street. | Install Class II buffered bike lanes. | 1503400 | 349600 | 0 | 0 | 0 | 0 | 0 | No PE | Due by 3/31/2028 | No | Not Started | State | 0
H8-08-024 | 8 | 5484013 | 8 | Wildomar | Riverside County | SCAG | RCTC | Various locations throughout the City of Wildomar. | Upgrade existing guardrails and associated improvements. | 353681.4 | 318313.26 | 0 | 0 | 2020-03-25 | 2021-10-13 | 318313.26 | No PE | Authorized | No | Closed | Federal | 0
H8-08-025 | 8 | 5484012 | 8 | Wildomar | Riverside County | SCAG | RCTC | Various locations throughout the City of Wildomar | Install pedestrian countdown heads, ADA compliant push buttons, and crosswalk striping and markings. | 252058.22 | 226852.39 | 2018-04-27 | 0 | 2020-03-25 | 2022-01-05 | 226852.39 | Authorized | Authorized | No | Closed | Federal | 0
HSIP4-08-001 | 4 | 5484003 | 8 | Wildomar | Riverside County | SCAG | RCTC | Clinton Keith Rd./Hidden Springs Rd. | Install protected left-turn phasing and pedestrian improvements | 64250.4 | 56803 | 2012-08-01 | 0 | 2015-07-15 | 2016-12-09 | 56803 | Authorized | Authorized | No | Closed | Federal | 0
H10-08-026 | 10 | 5457028 | 8 | Yucaipa | San Bernardino County | SCAG | SANBAG | Various Intersections in Yucaipa: Yucaipa Blvd/5th St, Avenue E/Oak Glen Road, Yucaipa Blvd/10th St, Oak Glen Road/Chapman Heights Road, and Yucaipa Blvd/Yucaipa Valley Cir. | Convert left-turn movements to protected left-turns. | 539100 | 539100 | 0 | 0 | 2021-05-20 | 0 | 539100 | No PE | Authorized | No | CON | State | 0
H12-08-040 | 12 | 5457031 | 8 | Yucaipa | San Bernardino County | SCAG | SANBAG | Yucaipa Blvd (15 locations), Oak Glen Rd (8 locations), Bryant St (1 location), Wildwood Canyon Rd (1 location), Sand Canyon Rd (3 locations), Avenue E (1 location) and County Line Rd (1 location). | Upgrade signal heads with reflective tape and new backplates. | 397200 | 357480 | 0 | 0 | 2025-09-29 | 0 | 357480 | No PE | Authorized | No | CON | State | 0
H9-08-029 | 9 | 5457025 | 8 | Yucaipa | San Bernardino County | SCAG | SANBAG | The intersection of Oak Glen Road and 2nd Street. | Install traffic signal, safety lighting and associated striping/pavement markings. | 370412.74 | 329731.09 | 0 | 0 | 2019-12-19 | 2023-10-25 | 329731.09 | No PE | Authorized | No | Closed | Federal | 0
HSIP5-08-017 | 5 | 5457020 | 8 | Yucaipa | San Bernardino County | SCAG | SANBAG | Yucaipa Blvd. between 15th St. and 16th St. | Install raised medians | 1824354.02 | 684315.19 | 0 | 0 | 2017-06-15 | 2021-11-05 | 684315.19 | No PE | Authorized | No | Closed | Federal | 0
H8-08-026 | 8 | 5466023 | 8 | Yucca Valley | San Bernardino County | SCAG | SANBAG | Intersections on Yucca Trail between Warren Vista and Avalon Avenue. | Widen Yucca Trail to construct left turn lanes along the roadway segment; and widen Warren Vista to construct left turn lanes at the intersection of Yucca Trail. | 1297446.04 | 1155911.81 | 2017-05-01 | 0 | 2020-07-31 | 2022-01-03 | 1155911.81 | Authorized | Authorized | No | Closed | Federal | 0
HSIP3-08-007 | 3 | 5466018 | 8 | Yucca Valley | San Bernardino County | SCAG | SANBAG | Sr 62, Sr 247, And Joshua Ln. | Install 1,425' Of Raised Median Island | 268709.6 | 185400 | 0 | 0 | 2012-02-22 | 2013-07-29 | 185400 | No PE | Authorized | No | Closed | Federal | 0
HSIP3-08-008 | 3 | 5466017 | 8 | Yucca Valley | San Bernardino County | SCAG | SANBAG | Sr 62 Between Lahonda Way And Dumosa Ave. | Install Raised Median Island | 1968503.78 | 900000 | 0 | 0 | 2013-05-21 | 2015-04-01 | 900000 | No PE | Authorized | No | Closed | Federal | 0
H9-09-001 | 9 | 0 | 9 | Bishop Paiute Tribe | Inyo County | RURAL | Inyo LTC | Various intersections and road segments in the Bishop Paiute Indian Reservation (east of the City of Bishop). | Install enhanced signs and striping at intersections, install midblock crosswalk signs, add centerline and edge striping, and warning signs. | 547900 | 250000 | 0 | 0 | 0 | 0 | 0 | Not Tracked | Not Tracked | No | Not Started | Federal | 0
H10-09-001 | 10 | 5399032 | 9 | California City | Kern County | KCOG | KCOG | California City Blvd. between Yerba Blvd and Neuralia Road. | Install speed radar, high visibility crosswalks markings, crosswalk flashing beacons, sidewalk repairs with ADA ramps, flashing LED Stop Sign, restriping and signage. | 587000 | 512000 | 2021-08-02 | 0 | 2023-03-13 | 2025-08-05 | 512000 | Authorized | Authorized | No | Closed | State | 0
HSIP4-09-002 | 4 | 5399017 | 9 | California City | Kern County | KCOG | KCOG | Redwood Blvd./Hacienda Blvd. | Reconfigure intersection; construct curb, gutter, and raised median islands; upgrade signs, striping, and pavement markings | 482153.53 | 431880.29 | 2011-10-25 | 0 | 2013-04-29 | 2016-03-11 | 431880.29 | Authorized | Authorized | No | Closed | Federal | 0
HSIP6-09-001 | 6 | 5399023 | 9 | California City | Kern County | KCOG | KCOG | On California City Blvd between Alona Rd and Mitchell Blvd | Install reflectors, rumble strips, and chip seal; Upgrade striping | 657961.9 | 627987.36 | 2014-04-29 | 0 | 2015-08-11 | 2017-10-16 | 627987.36 | Authorized | Authorized | No | Closed | Federal
H9-09-002 | 9 | 0 | 9 | Fort Independence Tribe | Inyo County | RURAL | Inyo LTC | Various intersections and road segments in the Fort Independence Indian Reservation (approximately two miles north of the city of Independence) | Install intersection signs, center and edge striping, and new warning and speed limit signs. | 276500 | 250000 | 0 | 0 | 0 | 0 | 0 | Not Tracked | Not Tracked | No | Not Started | Federal | 0
H10-09-002 | 10 | 5948102 | 9 | Inyo County | Inyo County | RURAL | Inyo LTC | Various locations where existing guardrail remains sub-standard along Onion Valley Road near Independence. | Remove existing sub-standard sections of Metal Beam Guardrail and replace with 31" Midwest Guardrail System (MGS) to meet current standards. | 997000 | 997000 | 2021-08-05 | 0 | 2023-03-20 | 2024-08-12 | 997000 | Authorized | Authorized | No | Closed | State | 0
H9-09-003 | 9 | 5948094 | 9 | Inyo County | Inyo County | RURAL | Inyo LTC | Multiple locations throughout the County. This project aims to freshen centerline pavement markings on County roads that are high speed rural routes. There are 18 roads in this project that combine for about 137 miles of centerline paint. | The emphasis of the project is to paint a center line meeting reflectivity standards on high speed rural roads maintained by the County. The project includes about 137 miles of center line and 8.8 miles of fog lines. | 460622.5 | 201349.05 | 2019-01-25 | 0 | 2021-06-17 | 2022-02-22 | 201349.05 | Authorized | Authorized | No | Closed | Federal | 0
HSIP3-09-002 | 3 | 5948073 | 9 | Inyo County | Inyo County | RURAL | Inyo LTC | Ninemile Canyon Rd. Approx. 7 Miles West Of U.S. 395 | Install 7,400' Of Guardrail | 337935.4 | 304141.81 | 2010-09-09 | 0 | 2012-03-29 | 2013-10-24 | 304141.81 | Authorized | Authorized | No | Closed | Federal | 0
HSIP7-09-001 | 7 | 5948090 | 9 | Inyo County | Inyo County | RURAL | Inyo LTC | Panamint Valley Rd, State Line Rd, Trona Wildrose Rd, and Old Spanish Trail Highway. | Installation of edge lines for 77.8 miles on 4 rural major collectors and installation of edge rumble strips on 5.2 miles of State Line Rd. | 197644.88 | 197644.88 | 2016-08-22 | 0 | 2018-02-08 | 2020-03-18 | 197644.88 | Authorized | Authorized | No | Closed | Federal
H10-09-003 | 10 | 5439038 | 9 | Mammoth Lakes | Mono County | RURAL | Mono LTC | SR 203 between Laurel Mountain Road and the U.S. Post Office. | The upgrading of 2 existing crosswalks to Rectangular Rapid Flashing Beacon (RRFB) with early warning flashing signage. | 210485.26 | 191400 | 2021-12-22 | 0 | 2022-12-29 | 2024-07-11 | 191400 | Authorized | Authorized | No | Closed | State | 0
H12-09-003 | 12 | 0 | 9 | Mammoth Lakes | Mono County | RURAL | Mono LTC | Intersection of State Route 203 and Mountain Boulevard. | Install new crosswalk including the reconstruction of the north ADA ramp, the construction of a new ADA ramp on the south landing, striping, and installation of new posts, mast arms, and Rectangular Rapid Flashing Beacon (RRFB) system. | 869500 | 350000 | 0 | 0 | 0 | 0 | 0 | No PE | Due by 3/31/2028 | No | Not Started | State | 0
HSIP1-09-001 | 1 | 5439021 | 9 | Mammoth Lakes | Mono County | RURAL | Mono LTC | Lakeview Road Between Lakeview Blvd And Lake Mary Rd. | Install Snowmelt System To Prevent Snow And Ice Buildup On Steep 15% Grade. | 953123.09 | 783899.95 | 2008-02-12 | 0 | 2012-03-08 | 2013-08-14 | 783899.95 | Authorized | Authorized | No | Closed | Federal | 0
H10-09-004 | 10 | 5947069 | 9 | Mono County | Mono County | RURAL | Mono LTC | Lower Rock Creek Road, Benton Crossing Road, Convict Lake Road, Twin Lakes Road, Eastside Lane, and Lundy Lake Road. | Implement systemic safety curve warning and chevron signage. Upgrade existing curve warning signs reflectivity. | 209500 | 198500 | 0 | 0 | 2024-03-12 | 2025-01-16 | 198500 | No PE | Authorized | No | Closed | State | 0
H10-09-005 | 10 | 5947064 | 9 | Mono County | Mono County | RURAL | Mono LTC | Benton Crossing Rd (3,200 LF), Lower Rock Creek Rd (4112.5 LF), Twin Lakes Rd (437.5 LF), Gull Lake Rd (100 LF) | Upgrade existing, damaged and deficient guardrail at locations throughout Mono County. | 1002000 | 1000000 | 2021-11-19 | 0 | 2024-03-27 | 0 | 1000000 | Authorized | Authorized | No | CON | State | -1
H10-09-006 | 10 | 5947070 | 9 | Mono County | Mono County | RURAL | Mono LTC | Twin Lakes Rd, Northshore Dr, Eastside Ln (Offal Rd to Cunningham Ln), Topaz Ln | Paint right edgeline striping on existing roads throughout Mono County. | 261000 | 250000 | 0 | 0 | 2024-03-06 | 2025-03-17 | 250000 | No PE | Authorized | No | Closed | State | 0
H10-09-007 | 10 | 5385072 | 9 | Ridgecrest | Kern County | KCOG | KCOG | Signalized Intersections on China Lake Blvd at California Av, Church Av, Upjohn Av, Rader Av, Bowman Rd and College Heights Blvd. | Update the controllers and signal timing for adaptive traffic signals with advanced dilemma zone detection and a leading pedestrian interval. | 26232.75 | 36300 | 2021-11-15 | 0 | 0 | 2023-07-31 | 36300 | Authorized | No CON | No | Closed | State | 0
H10-09-007n8n9 | 10 | 5385074 | 9 | Ridgecrest | Kern County | KCOG | KCOG | H10-09-007(PN 5385072), H10-09-008 (PN 5385071) and H10-09-009 (PN 5385070) combined in Construction. | H10-09-007(PN 5385072), H10-09-008 (PN 5385071) and H10-09-009 (PN 5385070) combined in Construction. | 849927.25 | 822800 | 0 | 0 | 2022-11-14 | 2025-08-25 | 822800 | No PE | Authorized | No | Closed | State | 0
H10-09-008 | 10 | 5385071 | 9 | Ridgecrest | Kern County | KCOG | KCOG | 25 stop controlled arterial intersections in the City of Ridgecrest. | Upgrade arterial intersections with larger flashing stop signs with wind bracing and install advance "stop ahead" pavement markings. | 37118 | 87700 | 2021-11-15 | 0 | 0 | 2023-07-31 | 87700 | Authorized | No CON | No | Closed | State | 0
H10-09-009 | 10 | 5385070 | 9 | Ridgecrest | Kern County | KCOG | KCOG | Three uncontrolled crosswalks at Ridgecrest Boulevard & Alvord Street, Ridgecrest Boulevard & Sanders Street, and midblock on Downs St between Church Ave & Upjohn Ave. | Upgrade uncontrolled crosswalks with enhanced crosswalk features including Rectangular Rapid Flashing Beacons (RRFBs) and high visibility signing and striping. | 30822 | 44600 | 2021-11-15 | 0 | 0 | 2023-12-22 | 44600 | Authorized | No CON | No | Closed | State | 0
H12-09-004 | 12 | 0 | 9 | Ridgecrest | Kern County | KCOG | KCOG | Las Flores Avenue at Sierra View Street. | Upgrade the uncontrolled crosswalk with a HAWK signal. | 388900 | 350000 | 0 | 0 | 0 | 0 | 0 | No PE | Due by 3/31/2028 | No | Not Started | State | 0
H12-09-005 | 12 | 0 | 9 | Ridgecrest | Kern County | KCOG | KCOG | Existing bike lanes along the following roadways: Ward Ave, Drummond Ave, Los Flores Ave, Ridgecrest Blvd, Upjohn Ave, Bowman Rd, Mahan St, Downs St, Norma St, China Lake Blvd, French Ave, Sunland St, Gateway Blvd, Richmond Rd, College Heights Blvd. | Upgrade bike lanes. | 1754600 | 1579140 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2025) | Due by 3/31/2028 | Yes (PE) | Not Started | Federal | 2
H12-09-007 | 12 | 0 | 9 | Ridgecrest | Kern County | KCOG | KCOG | 14 signalized intersections on Downs Street, Norma Street, Drummond Ave, Bowman Rd, and China Lake Blvd. | Upgrade the signal hardware back-plates with retroreflective border and replace signal heads. | 543500 | 489150 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2025) | Due by 3/31/2028 | Yes (PE) | Not Started | State | 0
H8-09-001 | 8 | 5385059 | 9 | Ridgecrest | Kern County | KCOG | KCOG | Intersection of Downs Street at Bowman Road. | Convert to all-way Stop control, modify Southbound left turn lane to meet standards, and stripe crosswalk with ADA ramps on north leg. | 145046.47 | 145046.47 | 2017-10-25 | 0 | 2018-12-21 | 2021-02-25 | 145046.47 | Authorized | Authorized | No | Closed | Federal | 0
H8-09-002 | 8 | 5385060 | 9 | Ridgecrest | Kern County | KCOG | KCOG | Thirteen (13) uncontrolled Crosswalk locations throughout the City of Ridgecrest. | Installing Rapid Reflective Flashing Beacons (RRFB's), update signing and striping, and update the crosswalks to ladder style. | 232989.77 | 232989.77 | 2017-10-19 | 0 | 2018-12-21 | 2021-02-11 | 232989.77 | Authorized | Authorized | No | Closed | Federal | 0
HSIP4-09-001 | 4 | 5385042 | 9 | Ridgecrest | Kern County | KCOG | KCOG | China Lake Blvd./Upjohn Ave.; China Lake Blvd. between Rader Ave. and Ridgecrest Blvd. | Install traffic signals and interconnect communications cable; construct curb ramps | 397528.8 | 357775.92 | 2011-08-29 | 0 | 2013-09-09 | 2015-11-16 | 357775.92 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-09-001 | 5 | 5385049 | 9 | Ridgecrest | Kern County | KCOG | KCOG | China Lake Blvd./Bowman Rd. | Install traffic signals (interconnect); construct curb ramps, curb and gutter | 440871.5 | 396000 | 2013-09-06 | 0 | 2015-05-08 | 2018-05-02 | 396000 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-09-002 | 5 | 5385050 | 9 | Ridgecrest | Kern County | KCOG | KCOG | Drummond Ave. between Downs St. and Inyo St. | Widen roadway; improve alignment | 623831.37 | 263700 | 2013-09-06 | 0 | 2016-03-31 | 2017-09-12 | 263700 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-09-003 | 5 | 5385051 | 9 | Ridgecrest | Kern County | KCOG | KCOG | Seven (7) intersections (Norma St./Ward Ave., Downs St./Drummond Ave., Norma St./Drummond Ave., Norma St./Las Flores Ave., China Lake Blvd./California Ave., French Ave./Drummond Ave., China Lake Blvd./College Heights Blvd.) | Upgrade traffic signals | 214995.91 | 193496.28 | 2013-09-06 | 0 | 2014-06-13 | 2017-10-19 | 193496.28 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-09-004 | 5 | 5385052 | 9 | Ridgecrest | Kern County | KCOG | KCOG | Twelve (12) intersections (on Norma St., Downs St., and Richmond Rd. ) | Install signs and pavement markings | 318701.25 | 285876 | 2013-09-06 | 0 | 2014-06-10 | 2016-09-01 | 285876 | Authorized | Authorized | No | Closed | Federal | 0
H10-09-010 | 10 | 5184039 | 9 | Tehachapi | Kern County | KCOG | KCOG | Various locations in the City of Tehachapi. | Install edgelines and centerlines. | 250000 | 250000 | 2023-08-09 | 0 | 2023-08-09 | 2024-04-05 | 250000 | Authorized | Authorized | No | Closed | State | 0
H9-09-004 | 9 | 5184033 | 9 | Tehachapi | Kern County | KCOG | KCOG | Two uncontrolled locations including the midblock crossing of Curry Street in front of Tompkins Elementary School and the intersection Valley Blvd and Mill Street. | Install enhanced pedestrian crossings including solar powered pedestrian activated perimeter lit pedestrian crossing signs, accessible curb ramps, signing, and striping. | 229288.86 | 219800 | 2019-04-15 | 0 | 2020-09-10 | 2022-02-01 | 219800 | Authorized | Authorized | No | Closed | Federal | 0
HSIP3-09-001 | 3 | 5184015 | 9 | Tehachapi | Kern County | KCOG | KCOG | Adjacent To And Around The Pedestrian Bridge On The Southside Of Valley Blvd. Between Tucker Rd. And Mountain Ave. | Widen Shoulder To Remove Existing Guardrail; Install Curb And Gutter; Extend Culverts | 97971.57 | 76050 | 2010-08-18 | 0 | 2012-02-21 | 2015-01-22 | 76050 | Authorized | Authorized | No | Closed | Federal | 0
HSIP6-09-002 | 6 | 5184023 | 9 | Tehachapi | Kern County | KCOG | KCOG | On Tehachapi between Steuber Rd and Monolith St | Install traffic signals, striping, and signs; Construct sidewalk, gutter, curb, curb ramps; Widen pavement | 1725383.46 | 1707908.86 | 2014-06-18 | 0 | 2015-08-18 | 2018-05-07 | 1707908.86 | Authorized | Authorized | No | Closed | Federal
HRRR2-10-048 | 2 | 5926040 | 10 | Amador County | Amador County | RURAL | Amador LTC | On Ridge Road at the New York Ranch Road intersection | Lengthen turn/merge lane and revise road profile; install delineation | 2103861.27 | 866209.3 | 2008-12-19 | 2013-01-18 | 2015-12-02 | 2019-10-31 | 866209.3 | Authorized | Authorized | No | Closed | Federal | 0
HRRR2-10-049 | 2 | 5926041 | 10 | Amador County | Amador County | RURAL | Amador LTC | Various locations on Fiddletown Road, Jackson Valley Road, Shakeridge Road and Shenandoah Road | Widen shoulders; construct turnouts | 818873.09 | 689248.92 | 2008-09-16 | 2013-08-25 | 2015-03-18 | 2017-10-19 | 689248.92 | Authorized | Authorized | No | Closed | Federal | 0
HSIP2-10-005 | 2 | 5926039 | 10 | Amador County | Amador County | RURAL | Amador LTC | Intersection Of Ridge Rd. And New York Ranch Rd. | Install Traffic Signal; Construct Left-Turn And Acceleration Lanes | 1944230.52 | 855823.36 | 2008-09-17 | 2013-01-18 | 2015-12-02 | 2019-10-10 | 855823.36 | Authorized | Authorized | No | Closed | Federal | 0
HSIP3-10-004 | 3 | 6127044 | 10 | Amador County Transportation Commission | Amador County | RURAL | Amador LTC | Eleven Signalized Intersections In Amador County | Install Emergency Vehicle Preemption Systems And Provide ‘Emitters’ For Participating Emergency Vehicles | 349875 | 314887.49 | 2010-07-15 | 0 | 2011-08-16 | 2013-10-25 | 314887.49 | Authorized | Authorized | No | Closed | Federal | 0
H9-10-001 | 9 | 5206018 | 10 | Angels Camp | Calaveras County | RURAL | Calaveras COG | Various locations throughout the city of Angels Camp. | Conduct a roadway safety signing audit (RSSA) and install/relocate/remove roadway signs (per MUTCD standards) based on the results of the RSSA. | 163300 | 163300 | 2019-09-10 | 0 | 2022-09-07 | 0 | 163300 | Authorized | Authorized | No | CON | Federal | 0
HSIP7-10-001 | 7 | 5254026 | 10 | Atwater | Merced County | MCAG | MCAG | The intersection of Shaffer Road with Juniper Avenue | Replace existing permissive left turn phasing for Juniper Avenue with protective left turn phasing (split phasing); install ADA complaint ramps, high visibility x-walks & ADA compliant ped push buttons; and modify the signing and striping | 150528.43 | 132486.4 | 2017-03-17 | 0 | 2021-01-05 | 2022-05-06 | 132486.4 | Authorized | Authorized | No | Closed | Federal
H10-10-001 | 10 | 5930099 | 10 | Calaveras County | Calaveras County | RURAL | Calaveras COG | Various curves along Burson Rd, Copper Cove Dr, Double Springs Rd, Milton Rd, Jenny Lind Rd, Mountain Ranch Rd, Murphys Grade Rd, Parrotts Ferry Rd, Rail Road Flat Rd, Ridge Rd, Sheep Ranch Rd and Winton Rd. | Apply High Friction Surface Treatment (HFST) at various curves. | 1837800 | 1837800 | 2021-07-07 | 0 | 2022-09-13 | 2025-01-16 | 1837800 | Authorized | Authorized | No | Closed | State | 0
H10-10-002 | 10 | 5930098 | 10 | Calaveras County | Calaveras County | RURAL | Calaveras COG | Various roads including: Camanche Pkwy South, Milton, Mountain Ranch, Olive Orchard, Pool Station, Rail Road Flat, Ridge, Southworth, French Gulch, Independence, Ospital, Paloma, Pattison, Pettinger, Sheep Ranch and Calaveritas. | Apply thermoplastic striping. | 2064100 | 2064027 | 2021-07-07 | 0 | 2021-12-23 | 2025-08-20 | 2064027 | Authorized | Authorized | No | Closed | State | 0
H12-10-001 | 12 | 0 | 10 | Calaveras County | Calaveras County | RURAL | Calaveras COG | SR 4 and Pennsylvania Gulch Road. | Install approximately 1050 feet of sidewalks, upgrade / install ADA curb ramps, and upgrade / install crosswalks. | 391800 | 350000 | 0 | 0 | 0 | 0 | 0 | No PE | Due by 3/31/2028 | No | Not Started | State | 0
H9-10-002 | 9 | 5930095 | 10 | Calaveras County | Calaveras County | RURAL | Calaveras COG | County Rd #'s: 162,322,251,73,36,173,55,42,57,59,134,147,590,11,960,420,362, 43A,312,43,77,12A,74,58,54,27,127,48A,31 A,12, 28,761, 125,133,53,37,14,31,48,551,801,61,35,571,402,126,10,13,358,353,22,51,161,174,32,802,75,403,124,554, 29,72,60,1318,135,24 | Conduct a roadway safety and signing audit (RSSA) and install/relocate/remove roadway signs (per MUTCD standards) based on the results of the RSSA. | 5824815 | 5824815 | 2019-04-29 | 0 | 2022-09-19 | 0 | 5759732 | Authorized | Authorized | No | CON | Federal | 1
H9-10-003 | 9 | 5930094 | 10 | Calaveras County | Calaveras County | RURAL | Calaveras COG | Murphys Grd 6.06-6.13R, O'Byrnes Ferry 0.04-0.06R, 0.04-0.06L, 0.70-0.75L, Copper Cove 1.06-1.0SR, 1.06-1.0SL, Pool Station 9.92-9.97R, Southworth 4.96-4.97R, 4.96-4.97L, 5.10-5.15R, 5.10-5.15L, Gold Strike 0.85-0.87R, 0. 85-0.87L, Garabaldi 0.00-0.05R | Upgrade existing guardrail, end caps/flared ends, and transition railing. | 568176.42 | 469657.42 | 2019-05-31 | 0 | 2022-09-19 | 2025-10-21 | 469657.42 | Authorized | Authorized | No | Closed | Federal | 1
HRRR1-10-055 | 1 | 5930033 | 10 | Calaveras County | Calaveras County | RURAL | Calaveras COG | On Mountain Ranch Rd. (No. 14), approximately 5 miles East of San Andreas, near its intersection with Rocky Rd. | Rumble Strip | 220339.01 | 151736.3 | 2007-08-21 | 0 | 2011-08-25 | 2014-02-24 | 151736.3 | Authorized | Authorized | No | Closed | Federal | 0
HRRR1-10-056 | 1 | 5930034 | 10 | Calaveras County | Calaveras County | RURAL | Calaveras COG | On Mountain Ranch Rd. (No. 14) approximately 6 miles East of San Andreas, just past the intersection of Lower Michel Rd. | Widen or Improve Shoulder | 401505.4 | 134986.15 | 2007-08-21 | 0 | 0 | 2013-12-06 | 134986.15 | Authorized | No CON | No | Closed | Federal | 0
HSIP2-10-006 | 2 | 5930048 | 10 | Calaveras County | Calaveras County | RURAL | Calaveras COG | Copper Cove Dr. From 0.6 Miles W. Of Sawmill Red. To 0.2 Miles E. Of Quiver St. | Construct 8- Foot Shoulder; Install Guardrail | 168584.95 | 83039.34 | 2009-08-11 | 0 | 2011-08-25 | 2014-03-31 | 83039.34 | Authorized | Authorized | No | Closed | Federal | 0
HSIP2-10-007 | 2 | 5930049 | 10 | Calaveras County | Calaveras County | RURAL | Calaveras COG | Intersection Of O'Byrnes Ferry Rd. And Duchess Dr. | Construct Left-Turn Lane; Widen Shoulders | 251418.22 | 208532.57 | 2009-09-03 | 0 | 0 | 2013-11-18 | 208532.57 | Authorized | No CON | No | Closed | Federal | 0
HSIP3-10-003 | 3 | 5930056 | 10 | Calaveras County | Calaveras County | RURAL | Calaveras COG | Mountain Ranch Rd. | Resurface Roadway; Install Centerline And Edgeline Rumble Strips, Guardrail And Striping | 1069615.59 | 845225.94 | 2010-08-02 | 0 | 2011-12-14 | 2014-11-17 | 845225.94 | Authorized | Authorized | No | Closed | Federal | 0
HSIP4-10-005 | 4 | 5930053 | 10 | Calaveras County | Calaveras County | RURAL | Calaveras COG | Murphys Grade Rd., approximately 4.5 miles E of SR 49 | Install guardrail | 579909.21 | 521918.3 | 0 | 0 | 2012-06-08 | 2015-02-20 | 521918.3 | No PE | Authorized | No | Closed | Federal | 0
HSIP7-10-004 | 7 | 5930084 | 10 | Calaveras County | Calaveras County | RURAL | Calaveras COG | County-wide on entire length or significant segments of various Major Collector Roads: Camanche Pkwy S., Jesus Maria Rd, Milton Rd, Mountain Ranch Rd, Murphys Grade Rd, O'Byrnes Ferry Rd, Parrots Ferry Rd, Pool Station Rd, Rail Road Flat Rd. | Install E-1 delineators on both sides of roadway | 218769.5 | 196892.53 | 2016-05-13 | 0 | 2019-05-31 | 2021-12-16 | 196892.53 | Authorized | Authorized | No | Closed | Federal
H10-10-003 | 10 | 5241076 | 10 | Ceres | Stanislaus County | STANCOG | Stan COG | 3 unsignalized intersections on Mitchell Ave at Garrison St, Dale Ave, and Kay St. | Install raised medians on approaches, advanced pavement markings, and striping. | 514100 | 462690 | 2022-01-19 | 0 | 0 | 0 | 71190 | Authorized | Past due (due 9/30/2024) | Yes (CON) | PE | State | 0
H10-10-004 | 10 | 5241077 | 10 | Ceres | Stanislaus County | STANCOG | Stan COG | Two signalized intersections: Fowler Road & Mitchell Road, and East Whitmore Avenue & Moffett Road. | Install raised medians on approaches; provide protected left-turn phasing; upgrade signal hardware on all approaches. | 740400 | 666360 | 2022-01-19 | 0 | 0 | 0 | 118980 | Authorized | Past due (due 9/30/2024) | Yes (CON) | PE | State | 0
H8-10-001 | 8 | 5241067 | 10 | Ceres | Stanislaus County | STANCOG | Stan COG | Various locations throughout the City of Ceres | Install pedestrian countdown heads, ADA compliant push buttons, and crosswalk striping and markings. | 142344.25 | 135261.89 | 2017-07-31 | 0 | 2020-02-19 | 2021-10-27 | 135261.89 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-10-001 | 5 | 5230005 | 10 | Gustine | Merced County | MCAG | MCAG | SR 33/140 between Meredith Ave. and Linden Ave. | Install flush and raised medians, delineators, signs, and striping | 192976.54 | 173678.86 | 2013-03-22 | 0 | 2015-07-10 | 2016-12-23 | 173678.86 | Authorized | Authorized | No | Closed | Federal | 0
H9-10-004 | 9 | 5141019 | 10 | Jackson | Amador County | RURAL | Amador LTC | State Route 49 from SR 88 (East) to Clinton Rd. | Add street lighting. | 475000 | 475000 | 2019-09-10 | 0 | 2023-07-28 | 0 | 475000 | Authorized | Authorized | No | CON | Federal | 0
HSIP1-10-005 | 1 | 5141011 | 10 | Jackson | Amador County | RURAL | Amador LTC | Intersection Of Sr 88 And Court Street. | Improve Traffic Channelization And Decel/Accel Lanes For Turning Lanes. | 607579.33 | 544670.21 | 2008-07-19 | 2012-03-16 | 2012-04-17 | 2014-04-11 | 544670.21 | Authorized | Authorized | No | Closed | Federal | 0
H12-10-002 | 12 | 5242039 | 10 | Manteca | San Joaquin County | SJCOG | SJCOG | Signalized intersections: 42 traffic signals; Cottage Ave & North St, Yosemite Ave & Fremont St.; Unsignalized intersection: Spreckels Ave & Norman Dr.; Roadway segments: Mission Ridge Dr (Syrah Ct to S Main St) and Yosemite Ave (Cottage to Commerce Ave). | Implement systemic signal improvements: retro-reflective backplates and leading pedestrian interval (LPI) at 42 signals; install protected left-turn phases at two signals; implement pedestrian crossing improvements at the unsignalized intersection; install roadway median and lighting improvements. | 2610500 | 2349450 | 2025-10-23 | 0 | 0 | 0 | 261000 | Authorized | Due by 3/31/2028 | No | PE | Federal | 0
H9-10-006 | 9 | 5242035 | 10 | Manteca | San Joaquin County | SJCOG | SJCOG | Main Street from Northgate Drive to Alameda Street | Install Class II bike lanes, raised medians, pedestrian median fencing, curb ramps, and enhanced pedestrian crossings, and modify traffic signal (detector loops) at Main St and Louise Ave. | 4072400 | 2784640 | 2019-10-31 | 0 | 2024-09-09 | 0 | 2784640 | Authorized | Authorized | No | CON | Federal | 2
H9-10-007 | 9 | 5242036 | 10 | Manteca | San Joaquin County | SJCOG | SJCOG | Yosemite Avenue from Walnut Avenue to Main Street | Install Class II bike lanes, improved curb ramps, and pedestrian crossing enhancements. | 1099129 | 989216 | 2019-10-31 | 0 | 2025-07-03 | 0 | 989216 | Authorized | Authorized | No | CON | Federal | 2
HSIP7-10-006 | 7 | 5242033 | 10 | Manteca | San Joaquin County | SJCOG | SJCOG | All streets and roadways throughout the city | Installation and/or upgrade signs with new fluorescent sheeting, as well as the completion of a city-wide Roadway Safety Signing Audit. | 2558289.74 | 2544538.02 | 2016-07-26 | 0 | 2019-09-11 | 2025-05-29 | 2544538.02 | Authorized | Authorized | No | Closed | Federal
HSIP7-10-007 | 7 | 5242034 | 10 | Manteca | San Joaquin County | SJCOG | SJCOG | Various 46 signalized locations throughout the city | Improve signal hardware (lenses, back-plates, mounting, size, and number) and improve signal timing. | 4614000 | 3503000 | 2016-07-26 | 0 | 2019-12-12 | 0 | 3503000 | Authorized | Authorized | No | CON | Federal
H10-10-005 | 10 | 5940143 | 10 | Mariposa County | Mariposa County | RURAL | Mariposa LTC | Triangle Road between SR140 and SR49 (11.7 mi). | Install two-component paint edgelines. | 250000 | 250000 | 2021-07-07 | 0 | 2024-05-08 | 0 | 250000 | Authorized | Authorized | No | CON | State | 0
HRRR1-10-061 | 1 | 5940056 | 10 | Mariposa County | Mariposa County | RURAL | Mariposa LTC | In Greeley Hill on Greeley Hill Rd., Fiske Rd., and Holtzel Rd. | Widen or Improve Shoulder | 406707.65 | 366036.87 | 2010-01-07 | 0 | 2010-04-29 | 2013-02-14 | 366036.87 | Authorized | Authorized | No | Closed | Federal | 0
HSIP1-10-002 | 1 | 5085017 | 10 | Merced | Merced County | MCAG | MCAG | Yosemite Ave. Between "G" Street And "M" Street At Stadium Lane. | Install Traffic Signal, Safety Lighting And Crosswalks. | 222864.18 | 163367.68 | 2007-09-12 | 0 | 2009-04-09 | 2011-12-30 | 163367.68 | Authorized | Authorized | No | Closed | Federal | 0
H10-10-006 | 10 | 5939134 | 10 | Merced County | Merced County | MCAG | MCAG | Streets and roadways North of State Route 140 throughout the County of Merced. | Inventory and replacement of regularity and warning signs. | 750000 | 750000 | 2021-09-16 | 0 | 2024-05-17 | 0 | 750000 | Authorized | Authorized | No | CON | State | 0
H11-10-001 | 11 | 5939142 | 10 | Merced County | Merced County | MCAG | MCAG | Streets and roadways south of State Route 140 throughout the County of Merced. | Inventory and replacement of regularity and warning signs. | 1400000 | 1260000 | 2023-07-31 | 0 | 0 | 0 | 225000 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE | Federal | 1
H8-10-002 | 8 | 5939116 | 10 | Merced County | Merced County | MCAG | MCAG | Stephens Street between El Capitan Way and Shell Street in the unicorporated community of Delhi. | Use striping to implement Road Diet, install two enhanced pedestrian crosswalks, and install segment lighting. | 892533.27 | 650699.55 | 2017-06-01 | 0 | 2020-02-03 | 2021-11-23 | 650699.55 | Authorized | Authorized | No | Closed | Federal | 0
H8-10-003 | 8 | 5939118 | 10 | Merced County | Merced County | MCAG | MCAG | Various unsignalized intersections near school areas in the unincorporated communities of Le Grand, South Dos Palos, and Santa Nella. | Enhance pedestrian crosswalks by installing ADA curb ramps, advanced warning road signs, high-visibility crosswalk marking patterns, advanced yield lines, and rectangular rapid flashing beacons (RRFBs). | 422149.02 | 250000 | 2017-07-19 | 0 | 2020-02-03 | 2022-01-14 | 250000 | Authorized | Authorized | No | Closed | Federal | 0
HRRR2-10-057 | 2 | 5939067 | 10 | Merced County | Merced County | MCAG | MCAG | Various Locations; Sandy Mush Road at Nickel Road; Turner Island Road at Sand Slough; Henry Miller Road at Ingomar Grade; Oakdale Road at Dry Creek | Install solar powered flashing beacons | 39146.01 | 35231.39 | 2009-08-25 | 0 | 2010-04-29 | 2012-02-29 | 35231.39 | Authorized | Authorized | No | Closed | Federal | 0
HRRR2-10-058 | 2 | 5939068 | 10 | Merced County | Merced County | MCAG | MCAG | Intersection of Ingomar Road and Cottonwood Road | Reconfigure and reconstruct intersection | 692434.84 | 561670.74 | 2009-09-02 | 2011-01-21 | 2012-03-05 | 2013-10-24 | 561670.74 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-10-002 | 5 | 5939089 | 10 | Merced County | Merced County | MCAG | MCAG | Lake Rd. between Bellevue Rd. and Yosemite Ave. | Widen and pave shoulders | 933900.9 | 840510.8 | 2013-03-29 | 0 | 2016-07-13 | 2018-07-02 | 840510.8 | Authorized | Authorized | No | Closed | Federal | 0
HSIP6-10-001 | 6 | 5939096 | 10 | Merced County | Merced County | MCAG | MCAG | Winton Way/Gertrude Ave | Install traffic signal, flashing beacon, striping and pavement markings | 515670.67 | 506286.57 | 2014-01-22 | 0 | 2015-05-27 | 2017-03-06 | 506286.57 | Authorized | Authorized | No | Closed | Federal
HSIP7-10-002 | 7 | 5939112 | 10 | Merced County | Merced County | MCAG | MCAG | Project is located in the unincorporated Community of Planada at the intersection of Santa Fe Avenue at Childs Avenue and the adjacent Childs Avenue crossing of the BNSF Railroad. | Install pedestrian exclusionary fence along the BNSF railroad tracks, sidewalk, an at-grade pedestrian crossing of the BNSF railroad at Childs Avenue, and a traffic signal at the intersection of Santa Fe Avenue at Childs Avenue | 3017085.8 | 1271339.97 | 2016-07-01 | 0 | 2021-07-13 | 2024-06-27 | 1271339.97 | Authorized | Authorized | No | Closed | Federal
HSIP7-10-003 | 7 | 5939111 | 10 | Merced County | Merced County | MCAG | MCAG | On Merced Falls Road, approximately 1 mile East of La Grange Road in the Snelling area | Install centerline rumble strips/stripes, widen shoulder (paved) and edgeline rumble strips/stripes | 1144266.77 | 656650 | 2016-06-13 | 0 | 2019-11-04 | 2021-02-02 | 656650 | Authorized | Authorized | No | Closed | Federal
H10-10-007 | 10 | 5059252 | 10 | Modesto | Stanislaus County | STANCOG | Stan COG | Sylvan Ave and Northampton Lane; Jefferson St and Vine St; Wylie Dr and Rose Ave; Rumble Rd and Carver Rd; and Poust Rd and Chapparal Pl. | Install RRFB at school Crossing at Sylvan Ave and Northampton Lane. Install LED flashing stop signs at the other 4 locations. | 249200 | 249200 | 2021-09-17 | 0 | 2025-05-28 | 0 | 249200 | Authorized | Authorized | No | CON | State | 0
H10-10-008 | 10 | 5059251 | 10 | Modesto | Stanislaus County | STANCOG | Stan COG | 7 Crossings : Granger at Florida; Morris at Auburn St; Tully Rd at Leonard; Lincoln at Poppypatch; Lincoln Ave at Penny; Tully Rd at MJC; and Stoddard at MJC. | Install Rectangular Rapid Flashing Beacons (RRFBs). | 908200 | 908200 | 2021-09-17 | 0 | 2025-05-27 | 0 | 908200 | Authorized | Authorized | No | CON | State | 0
H10-10-009 | 10 | 5059253 | 10 | Modesto | Stanislaus County | STANCOG | Stan COG | 37 signalized intersections within Downtown Modesto, and 33 intersections outside of Downtown. | Replace all existing signal heads with new ones that have retroreflective back-plates; and install advance limit lines at the intersections that do not have. | 2004500 | 2004500 | 2021-09-17 | 0 | 2025-05-28 | 0 | 2004500 | Authorized | Authorized | No | CON | State | 0
H10-10-010 | 10 | 5059254 | 10 | Modesto | Stanislaus County | STANCOG | Stan COG | The intersections of Standiford Ave. with Longbridge Dr. and Sylvan Ave. with Bridgeford Ln. | Install pedestrian refuge island with directional median openings, Pedestrian Hybrid Beacons and high visibility crosswalks with pedestrian signage. | 965800 | 919000 | 2021-12-22 | 0 | 0 | 0 | 100350 | Authorized | Past due (due 9/30/2024) | Yes (CON) | PE | State | 0
H10-10-011 | 10 | 5059255 | 10 | Modesto | Stanislaus County | STANCOG | Stan COG | Oakdale Road from Lancey Drive to Celeste Drive. | Install Pedestrian Hybrid Beacon, Leading Pedestrian Intervals, pedestrian signals, blank-out no right turn signals/signage, directional median, high visibility crosswalk, median refuge island, ADA ramps, reconstruct driveway, and coordinate signals. | 1105900 | 1039330 | 2021-12-22 | 0 | 0 | 0 | 147510 | Authorized | Past due (due 9/30/2024) | Yes (CON) | PE | State | 0
H11-10-002 | 11 | 5059267 | 10 | Modesto | Stanislaus County | STANCOG | Stan COG | Tokay Ave at La Cienega Dr, E Rumble Rd at Hampshire Ln, Robertson Rd at Hancock St, and Conant Ave at Budd St. | Install raised crosswalks. | 248200 | 223380 | 2025-06-26 | 0 | 0 | 0 | 39600 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE | State | 0
H8-10-004 | 8 | 5059237 | 10 | Modesto | Stanislaus County | STANCOG | Stan COG | Citywide locations | Install traffic signal backplates with 2-inch retroreflective borders; install marked crosswalks, stop bars and stop legends. | 434700 | 391230 | 2019-04-29 | 0 | 2020-01-16 | 0 | 391230 | Authorized | Authorized | No | CON | Federal | 0
HSIP1-10-001 | 1 | 5059155 | 10 | Modesto | Stanislaus County | STANCOG | Stan COG | Various Locations Throughout The City Of Modesto. | Upgrade School Zone Signs With Diamond Grade Reflective Lime Green Signs. | 53895.28 | 48505.73 | 2008-05-09 | 0 | 0 | 2012-03-29 | 48505.73 | Authorized | No CON | No | Closed | Federal | 0
HSIP5-10-003 | 5 | 5059204 | 10 | Modesto | Stanislaus County | STANCOG | Stan COG | Various intersections throughout the city | Install new Emergency Vehicle Pre-emption (EVP) systems; upgrade phase detectors for existing EVP systems | 614735.85 | 553214.75 | 2015-01-27 | 0 | 2016-08-06 | 2021-11-18 | 553214.75 | Authorized | Authorized | No | Closed | Federal | 0
HSIP6-10-002 | 6 | 5059221 | 10 | Modesto | Stanislaus County | STANCOG | Stan COG | On Scenic Drive between east of Bodem St and Orangeburg Ave | Install High Friction Surface Treatment | 252454.02 | 227127.46 | 2016-06-22 | 0 | 2017-07-20 | 2021-10-19 | 227127.46 | Authorized | Authorized | No | Closed | Federal
HSIP7-10-018 | 7 | 5059227 | 10 | Modesto | Stanislaus County | STANCOG | Stan COG | The intersection of Oakdale Road with Claratina Avenue. | Install a new traffic signal and traffic signs, stripes and pavement markings | 552404.4 | 552404.4 | 2017-06-22 | 0 | 2019-09-10 | 2024-11-14 | 552404.4 | Authorized | Authorized | No | Closed | Federal
H11-10-004 | 11 | 0 | 10 | Mountain House Community Services District | San Joaquin County | SJCOG | SJCOG | Great Valley Pkwy (from Byron Rd to Grant Line Rd); Arturo Blvd (from Great Valley Pkwy to Central Pkwy); and Main Street (from Great Valley Pkwy to Central Pkwy). | Convert one travel lane in each direction to accommodate for the implementation of Class IV bikeway facility in each direction as a retrofit based on the existing conditions and traffic patterns. | 662200 | 249930 | 0 | 0 | 0 | 0 | 0 | No PE | Due by 12/31/2026 | No | Not Started | State | 0
H11-10-005 | 11 | 0 | 10 | Mountain House Community Services District | San Joaquin County | SJCOG | SJCOG | The intersection of Central Parkway with Legacy Drive and the intersection of Central Parkway with Heritage Drive. | Enhance the existing RRFBs by installing additional RRFBs at the median, and modify signing and striping near the intersections in Central Parkway. | 151000 | 135900 | 0 | 0 | 0 | 0 | 0 | No PE | Due by 12/31/2026 | No | Not Started | State | 0
HSIP1-10-006 | 1 | 5153025 | 10 | Oakdale | Stanislaus County | STANCOG | Stan COG | Yosemite Avenue At "G" Street. | Upgrade Temporary Traffic Signal With Permanent Signal. | 192922.81 | 173630.52 | 0 | 0 | 2008-05-05 | 2011-08-18 | 173630.52 | No PE | Authorized | No | Closed | Federal | 0
HSIP1-10-007 | 1 | 5153026 | 10 | Oakdale | Stanislaus County | STANCOG | Stan COG | F Street (Sr 108) At First Street. | Upgrade Temporary Traffic Signal With Permanent Signal. | 187241.27 | 84258.57 | 0 | 0 | 2008-07-29 | 2010-12-28 | 84258.57 | No PE | Authorized | No | Closed | Federal | 0
H11-10-006 | 11 | 5244042 | 10 | Patterson | Stanislaus County | STANCOG | Stan COG | Intersection at Sperry Avenue and Highway 33. | Installation of traffic signal with paved shoulder widening. Install left turn lanes, roadway signing and striping. Railroad crossing improvements include at-grade railroad crossing on the side street approach less than 110 feet to the east. | 1283000 | 1154700 | 2023-06-13 | 0 | 0 | 0 | 175500 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE | State | 0
HSIP5-10-004 | 5 | 5236003 | 10 | Plymouth | Amador County | RURAL | Amador LTC | SR 49/Main St. | Install traffic signals or roundabout | 3682411.48 | 2205626.72 | 2007-01-31 | 2013-09-09 | 2017-03-10 | 2024-01-25 | 2205626.72 | Authorized | Authorized | No | Closed | Federal | 0
HSIP6-10-003 | 6 | 5236004 | 10 | Plymouth | Amador County | RURAL | Amador LTC | Shenandoah Road/Fiddletown Road | Realign roadway; Increase horizontal curve; Modify profile | 2357426.41 | 1965598.29 | 2014-07-14 | 2016-06-16 | 2017-07-19 | 2019-12-11 | 1965598.29 | Authorized | Authorized | No | Closed | Federal
H10-10-012 | 10 | 5929320 | 10 | San Joaquin County | San Joaquin County | SJCOG | SJCOG | Intersection of Benjamin Holt Drive and Leesburg Place | Install a high visibility pedestrian crosswalk across Benjamin Holt Drive with RRFBs and an added curb ramp on the northwest corner of the intersection | 107300 | 107300 | 2021-12-28 | 0 | 2024-05-10 | 2025-10-20 | 107300 | Authorized | Authorized | No | Closed | State | 0
H10-10-013 | 10 | 5929318 | 10 | San Joaquin County | San Joaquin County | SJCOG | SJCOG | Bridges at West Lane-Pixley Slough, West Lane-Woodbridge Canal, West Lane-Wind River Slough, Lower Sacramento Road-Overflow Channel, and Lower Sacramento Road-Mokelumne River. | Replace guardrails on bridges. | 304654 | 304654 | 2021-11-23 | 0 | 2023-11-06 | 0 | 304654 | Authorized | Authorized | No | CON | State | 0
H10-10-014 | 10 | 5929319 | 10 | San Joaquin County | San Joaquin County | SJCOG | SJCOG | Intersections of 11th with Chrisman, Banta and Bird. | Replace "Signal Ahead" signs with PREPARE TO STOP blank out signs to improve dilemma zone protection; replace median mounted poles with heads mounted on mast arms, and replace existing heads with 12" heads with retroreflective back-plates. | 1038800 | 1038800 | 2021-12-28 | 0 | 2025-06-12 | 0 | 1038800 | Authorized | Authorized | No | CON | State | 0
H11-10-013 | 11 | 5929333 | 10 | San Joaquin County | San Joaquin County | SJCOG | SJCOG | Install Bicycle Lane on Lower Sacramento Road (Eight Mile Road to Lodi City Limits). | Stripe existing paved shoulders as a Class II Bicycle Lane, place Bike Lane painted legends and signage as required. | 249600 | 224640 | 2024-05-29 | 0 | 2025-12-23 | 0 | 224640 | Authorized | Authorized | No | CON | State | 0
H12-10-003 | 12 | 5929348 | 10 | San Joaquin County | San Joaquin County | SJCOG | SJCOG | Seventeen (17) signalized intersections throughout unincorporated San Joaquin County. | Replace 203 existing signal heads, install 9 new signal heads on existing poles, and install 1 new signal head on a new pole. | 508900 | 458010 | 2026-02-12 | 0 | 0 | 0 | 68697 | Authorized | Due by 3/31/2028 | No | PE | State | 0
H12-10-004 | 12 | 5929343 | 10 | San Joaquin County | San Joaquin County | SJCOG | SJCOG | Roads at San Joaquin County bridges numbered: 29C-082, 29C-147, 29C-158, 29C-159, 29C-160, 29C-162, 29C-163, 29C-214, 29C-215 and 29C-231. | Upgrade guardrails, end treatments and terminal systems. | 1111000 | 999900 | 2025-07-09 | 0 | 0 | 0 | 121500 | Authorized | Due by 3/31/2028 | No | PE | Federal | 1
H12-10-005 | 12 | 5929347 | 10 | San Joaquin County | San Joaquin County | SJCOG | SJCOG | Fifteen (15) intersections in unincorporated San Joaquin County. | Install intersection lighting and advance warning flashing beacons. | 5430200 | 4887180 | 2026-01-07 | 0 | 0 | 0 | 840150 | Authorized | Due by 3/31/2028 | No | PE | Federal | 1
H8-10-005 | 8 | 5929288 | 10 | San Joaquin County | San Joaquin County | SJCOG | SJCOG | Intersection of Byron Road and Grant Line Road in Tracy. | Install a roundabout. | 3274237.95 | 3274237.95 | 2017-03-17 | 0 | 2022-04-14 | 2025-04-28 | 3274237.95 | Authorized | Authorized | No | Closed | Federal | 0
H8-10-006 | 8 | 5929289 | 10 | San Joaquin County | San Joaquin County | SJCOG | SJCOG | Intersection of Duncan Road and Comstock Road in Linden. | Install a roundabout. | 2764761 | 2390984.93 | 2017-03-20 | 0 | 2023-03-29 | 2025-04-28 | 2390984.93 | Authorized | Authorized | No | Closed | Federal | 1
H9-10-008 | 9 | 5929308 | 10 | San Joaquin County | San Joaquin County | SJCOG | SJCOG | River Road between 1000 ft west of Van Allen Road and 1000 ft east of Sexton Road (1.4 miles). | Install centerline and edgeline rumble strips. | 82244.25 | 73106.38 | 2019-09-10 | 0 | 2021-09-14 | 2023-12-01 | 73106.38 | Authorized | Authorized | No | Closed | Federal | 1
H9-10-009 | 9 | 5929309 | 10 | San Joaquin County | San Joaquin County | SJCOG | SJCOG | Lower Sac Road between Acampo Road and Woodbridge Road (one mile). | Install centerline and edgeline rumble strips. | 115211.33 | 90949.64 | 2019-09-06 | 0 | 2021-09-14 | 2023-11-08 | 90949.64 | Authorized | Authorized | No | Closed | Federal | 0
H9-10-010 | 9 | 5929310 | 10 | San Joaquin County | San Joaquin County | SJCOG | SJCOG | Six crosswalks, including Waterloo Road at Myran Avenue, Waterloo Road at Auto Avenue, Alpine Avenue at Franklin Avenue, Lilac Street at Indiana Street, B Street/12th Street, and Acampo Rd at Houston Elementary School. | Install Rectangular Rapid Flashing Beacons (RRFBs) at crosswalks. | 75252.36 | 75252.36 | 2019-09-10 | 0 | 2021-07-28 | 2023-12-11 | 75252.36 | Authorized | Authorized | No | Closed | Federal | 0
HRRR1-10-052 | 1 | 5929186 | 10 | San Joaquin County | San Joaquin County | SJCOG | SJCOG | Corral Hollow Road from Interstate 580 to Alamada County Line | Upgrade Guardrail (include new guardrail) | 304705.15 | 243509.12 | 2007-11-20 | 0 | 2008-07-18 | 2013-01-09 | 243509.12 | Authorized | Authorized | No | Closed | Federal | 0
HRRR2-10-053 | 2 | 5929207 | 10 | San Joaquin County | San Joaquin County | SJCOG | SJCOG | Intersection of Escalon-Bellota Road and Lone Tree Road | Install traffic signal | 1208027.47 | 873826.95 | 2009-08-18 | 0 | 2012-08-13 | 2015-11-18 | 873826.95 | Authorized | Authorized | No | Closed | Federal | 0
HRRR2-10-054 | 2 | 5929208 | 10 | San Joaquin County | San Joaquin County | SJCOG | SJCOG | Airport Way from Kasson Road to Division Avenue. | Install textured centerline and edgeline markings | 155843.17 | 71248.22 | 2009-07-20 | 0 | 2010-03-05 | 2012-12-11 | 71248.22 | Authorized | Authorized | No | Closed | Federal | 0
HSIP1-10-011 | 1 | 6210008 | 10 | San Joaquin County | San Joaquin County | SJCOG | SJCOG | Intersection Of Sr 88 And Alpine Road. | Install Traffic Signal. | 180000 | 180000 | 0 | 0 | 2008-08-17 | 2013-03-14 | 180000 | No PE | Authorized | No | Closed | Federal | 0
HSIP3-10-002 | 3 | 5929219 | 10 | San Joaquin County | San Joaquin County | SJCOG | SJCOG | North Lower Sacramento Rd. From 600' North Of Collier Rd. To 1000' South Of The Union Pacific Railroad Uc | Install Turning Lanes, Safety Lighting, Pavement Markings, And Speed Feedback Signs | 1059767.15 | 589229.49 | 2010-05-13 | 0 | 2012-12-20 | 2015-11-02 | 589229.49 | Authorized | Authorized | No | Closed | Federal | 0
HSIP4-10-00 | 4 | 5929232 | 10 | San Joaquin County | San Joaquin County | SJCOG | SJCOG | Wilson Way/Newton Rd. (McAllen Rd.) | Construct left-turn and right-turn lanes; install protected left-turn phasing and RR preemption | 1453392.71 | 1021306.06 | 2011-06-10 | 0 | 2015-01-05 | 2018-10-16 | 1021306.06 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-10-005 | 5 | 5929265 | 10 | San Joaquin County | San Joaquin County | SJCOG | SJCOG | Wilson Way, approximately 500' N of the diverting canal | Install raised medians, delineators, reflectors, and object markers | 164149.55 | 97644.83 | 2013-05-24 | 0 | 2014-02-11 | 2016-06-16 | 97644.83 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-10-006 | 5 | 5929264 | 10 | San Joaquin County | San Joaquin County | SJCOG | SJCOG | Alpine Ave./Wilson Way; Wilson Way/Sanguinetti Ln.; Waterloo Rd./Filbert St. | Install pedestrian countdown heads | 84821.37 | 66716.71 | 2013-05-31 | 0 | 2014-08-07 | 2016-06-22 | 66716.71 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-10-007 | 5 | 5929253 | 10 | San Joaquin County | San Joaquin County | SJCOG | SJCOG | Peltier Rd. from 300 ft. west of Bender Road to Lower Sacramento Road | Widen and pave shoulders; install rumble strips and striping (center-line and edge-lines) | 1072284.23 | 777737.72 | 2013-03-01 | 0 | 2015-01-13 | 2016-12-01 | 777737.72 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-10-008 | 5 | 5929266 | 10 | San Joaquin County | San Joaquin County | SJCOG | SJCOG | Cherokee Rd./Newton Rd. | Install left-turn lane and relocate right-turn lane | 809140.17 | 512758.66 | 2013-05-30 | 0 | 2016-01-11 | 2018-07-23 | 512758.66 | Authorized | Authorized | No | Closed | Federal | 0
HSIP6-10-004 | 6 | 5929273 | 10 | San Joaquin County | San Joaquin County | SJCOG | SJCOG | On Schulte Rd approx 1,500' west of Lammers Rd and on Corral Hollow Rd near Tracy city limit | Install High Friction Surface Treatment | 620567.64 | 556515.28 | 2014-06-26 | 0 | 2015-06-29 | 2016-12-07 | 556515.28 | Authorized | Authorized | No | Closed | Federal
HSIP7-10-008 | 7 | 5929283 | 10 | San Joaquin County | San Joaquin County | SJCOG | SJCOG | Union Road from Coelho Road to French Camp Road | Install centerline and edgeline rumble strips, install no passing zones. | 156434.5 | 106608.36 | 2016-06-27 | 0 | 2018-02-07 | 2020-10-08 | 106608.36 | Authorized | Authorized | No | Closed | Federal
HSIP7-10-009 | 7 | 5929284 | 10 | San Joaquin County | San Joaquin County | SJCOG | SJCOG | Bird Road from Union Pacific Railroad tracks (north) to Ahern Road | Install center line and edge line rumble strips, install no passing zones. | 219419.78 | 209581.29 | 2016-07-01 | 0 | 2018-01-26 | 2020-06-29 | 209581.29 | Authorized | Authorized | No | Closed | Federal
HSIP7-10-010 | 7 | 5929285 | 10 | San Joaquin County | San Joaquin County | SJCOG | SJCOG | Austin Road from Burnham Road to French Camp Road | Install High Friction Surface Treatment (HFST). Install center line and edge line rumble strips. | 701997.75 | 507758.35 | 2016-07-11 | 0 | 2018-01-11 | 2020-01-29 | 507758.35 | Authorized | Authorized | No | Closed | Federal
HSIP7-10-011 | 7 | 5929286 | 10 | San Joaquin County | San Joaquin County | SJCOG | SJCOG | French Camp Road from Jack Tone Road to Prescott Road | Install centerline and edgeline rumble strips. Apply High Friction Surface Treatment (HFST) | 531697.42 | 456722.38 | 2016-07-05 | 0 | 2018-02-07 | 2020-10-08 | 456722.38 | Authorized | Authorized | No | Closed | Federal
HSIP7-10-012 | 7 | 5929287 | 10 | San Joaquin County | San Joaquin County | SJCOG | SJCOG | 35 all-way stop controlled intersections | Install Red Flashing LED Beacons with solar panels | 229647.37 | 215964.35 | 2017-02-23 | 0 | 2018-01-12 | 2020-02-11 | 215964.35 | Authorized | Authorized | No | Closed | Federal
H10-10-015 | 10 | 5938271 | 10 | Stanislaus County | Stanislaus County | STANCOG | Stan COG | 84 miles of roadway segments throughout Stanislaus County. | Install wet-night edgelines and center lines and edgeline rumble strips/stripes (both sides). | 8542700 | 8542700 | 2021-12-20 | 0 | 2025-01-14 | 0 | 8542700 | Authorized | Authorized | No | CON | Mix | 1
H10-10-016 | 10 | 5938272 | 10 | Stanislaus County | Stanislaus County | STANCOG | Stan COG | 12 unsignalized intersections in various locations throughout Stanislaus County. | Implement systemic safety improvements for rural, unsignalized intersections by upgrading stop signs with flashing beacons, upgrading intersection pavement markings, and installing transverse rumble strips. Adding Left Turn Lane, on Grayson Road, in West Grayson Road and Cox Intersection. | 2682120 | 2413908 | 2021-12-20 | 0 | 2025-04-07 | 0 | 2413906.01 | Authorized | Authorized | No | CON | Mix | 1
H12-10-006 | 12 | 5938287 | 10 | Stanislaus County | Stanislaus County | STANCOG | Stan COG | Various locations. | Install retroreflective backplates. | 601000 | 540900 | 2025-09-23 | 0 | 0 | 0 | 40500 | Authorized | Due by 3/31/2028 | No | PE | State | 0
H8-10-008 | 8 | 5938245 | 10 | Stanislaus County | Stanislaus County | STANCOG | Stan COG | Various Roads. | Install fluorescent sign, and wet/dry enhanced thermoplastic striping upgrades. | 1556045.53 | 1400440.96 | 2017-09-13 | 0 | 2020-09-10 | 2023-12-01 | 1400440.96 | Authorized | Authorized | No | Closed | Federal | 1
H8-10-009 | 8 | 5938246 | 10 | Stanislaus County | Stanislaus County | STANCOG | Stan COG | Various Locations. | Install edge-lines and centerlines using enhanced wet/night thermoplastic striping. | 2070997.93 | 1863898.12 | 2017-09-13 | 0 | 2020-09-10 | 2023-10-24 | 1863898.12 | Authorized | Authorized | No | Closed | Federal | 1
H9-10-011 | 9 | 5938250 | 10 | Stanislaus County | Stanislaus County | STANCOG | Stan COG | Intersections of Paradise Rd at Vernon Ave and 9th Street at Stella Ave. | Install Rectangular Rapid Flashing Beacons (RRFBs) at uncontrolled crossings. | 387951 | 250000 | 2019-03-13 | 0 | 2021-05-05 | 2023-04-12 | 250000 | Authorized | Authorized | No | Closed | Federal | 0
HRRR2-10-063 | 2 | 5938171 | 10 | Stanislaus County | Stanislaus County | STANCOG | Stan COG | Tim Bell Road approximately 1.3 miles west of Hazeldean Road | Install guardrail | 13939.81 | 12545.83 | 0 | 0 | 2011-05-23 | 2012-07-09 | 12545.83 | No PE | Authorized | No | Closed | Federal | 0
HSIP2-10-009 | 2 | 5938160 | 10 | Stanislaus County | Stanislaus County | STANCOG | Stan COG | Intersection Of Hatch Rd. And Crows Landing Rd. | Construct Raised Concrete Median; Upgrade Traffic Signals | 622470.74 | 385365.66 | 2009-02-05 | 0 | 2010-02-22 | 2013-03-26 | 385365.66 | Authorized | Authorized | No | Closed | Federal | 0
HSIP2-10-012 | 2 | 5938161 | 10 | Stanislaus County | Stanislaus County | STANCOG | Stan COG | Intersection Of South Ninth St. And Latimer Ave. | Construct Concrete Median; Extend Left Turn Pocket; Install Signs, Stripes And Pavement Markings | 150734.97 | 108893 | 2009-03-04 | 0 | 2010-07-15 | 2012-02-28 | 108893 | Authorized | Authorized | No | Closed | Federal | 0
HSIP2-10-015 | 2 | 5938163 | 10 | Stanislaus County | Stanislaus County | STANCOG | Stan COG | Claribel Rd. At The Bnsf Railroad Crossing And Intersection Of Claribel Road And Terminal Ave. | Construct Raised Concrete Median; Widen Radius Return; Install Signs, Stripes And Pavement Markings | 42195.56 | 21110 | 2009-03-30 | 0 | 2011-05-09 | 2013-01-04 | 21110 | Authorized | Authorized | No | Closed | Federal | 0
HSIP4-10-003 | 4 | 5938197 | 10 | Stanislaus County | Stanislaus County | STANCOG | Stan COG | Central Ave., within 1,500' of W. Taylor Rd. | Widen shoulders; modify geometrics | 787256.36 | 632043.63 | 2011-07-21 | 0 | 2015-05-27 | 2016-05-06 | 632043.63 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-10-009 | 5 | 5938213 | 10 | Stanislaus County | Stanislaus County | STANCOG | Stan COG | Lake Rd. between Lampley Rd. and Denton Rd. | Widen and pave shoulders; install rumble strips | 1530930.1 | 659420.17 | 2013-08-10 | 0 | 2018-05-02 | 2021-10-20 | 659420.17 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-10-010 | 5 | 5938212 | 10 | Stanislaus County | Stanislaus County | STANCOG | Stan COG | River R. between Sawyer Ave. and Cleveland Ave. | Widen and pave shoulders; install rumble strips (edge-lines); modify roadway superelevation | 976494.99 | 828951.88 | 2013-08-10 | 0 | 2018-05-18 | 2021-10-26 | 828951.88 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-10-011 | 5 | 5938211 | 10 | Stanislaus County | Stanislaus County | STANCOG | Stan COG | West Main St. from the San Joaquin River to approximately 0.8 miles W of Carpenter Rd. | Widen and pave shoulders; install rumble strips (center-line and edge-lines) | 985613.48 | 499888.09 | 2013-07-29 | 0 | 2018-05-02 | 2021-10-20 | 499888.09 | Authorized | Authorized | No | Closed | Federal | 0
HSIP6-10-005 | 6 | 5938234 | 10 | Stanislaus County | Stanislaus County | STANCOG | Stan COG | Various locations in Stanislaus County | Install flashing beacon and lighting; widen shoulder | 478934.25 | 417246.95 | 2015-07-28 | 0 | 2017-03-17 | 2020-12-22 | 417246.95 | Authorized | Authorized | No | Closed | Federal
HSIP7-10-019 | 7 | 5938238 | 10 | Stanislaus County | Stanislaus County | STANCOG | Stan COG | Crows Landing Road - Hatch Rd to Whitmore Avenue | Install Raised Median, Street Lighting, and Buffered bike lanes. | 4024254.64 | 2476300 | 2016-05-31 | 0 | 2020-01-16 | 2022-05-02 | 2476300 | Authorized | Authorized | No | Closed | Federal
H10-10-017 | 10 | 5008195 | 10 | Stockton | San Joaquin County | SJCOG | SJCOG | Intersection of Harding Way and Lincoln Street and intersection of Harding Way and Pacific Avenue/Madison Street. | Install left turn pockets with left turn phasing, upgrade signals, cabinet & appurtenances, install pedestrian countdown signal heads, and install High Friction Surface Treatment (HFST) through approaches. | 2020107 | 1595840 | 2021-08-17 | 0 | 2025-06-12 | 0 | 1827180 | Authorized | Authorized | No | CON | State | 0
H10-10-018 | 10 | 5008202 | 10 | Stockton | San Joaquin County | SJCOG | SJCOG | Intersections of Madison Street with Willow Street, Vine Street, Rose Street, Magnolia Street, Acacia Street, Poplar Street, and Flora Street. | Install High-visibility crosswalks, pavement markings, ADA ramps, sight triangles and rapid-flashing beacons. | 721600 | 644940 | 2022-08-17 | 0 | 2026-03-10 | 0 | 644940 | Authorized | Authorized | No | CON | State | 0
H10-10-019 | 10 | 5008197 | 10 | Stockton | San Joaquin County | SJCOG | SJCOG | Two signalized intersections: North Pershing Avenue at Country Club Boulevard and North Pershing at Rosemarie Lane. | Install protected left phasing, lengthen an existing turn pocket and upgrade signal equipment. | 796800 | 796800 | 2021-10-15 | 0 | 2025-02-13 | 0 | 796800 | Authorized | Authorized | No | CON | State | 0
H10-10-020 | 10 | 5008219 | 10 | Stockton | San Joaquin County | SJCOG | SJCOG | Various locations on curve approaches throughout the City. | Place 3 speed trailers and 27 speed sentries at curve approaches that experience high rates of collisions. | 320000 | 320000 | 0 | 0 | 2025-05-05 | 0 | 320000 | No PE | Authorized | No | CON | State | 0
H10-10-021 | 10 | 5008196 | 10 | Stockton | San Joaquin County | SJCOG | SJCOG | Eight intersections throughout South Stockton. | Install pedestrian hybrid beacons, other crossing improvements, and intersection lighting. | 5861500 | 5861500 | 2021-09-16 | 0 | 2024-10-25 | 0 | 5861500 | Authorized | Authorized | No | CON | State | 0
H10-10-022 | 10 | 5008198 | 10 | Stockton | San Joaquin County | SJCOG | SJCOG | Frontage Road just South of the Stockton Soccer Complex, Lower Sacramento Road South of Bear Creek, and Manthey Road at the curve adjacent to I-5. | Rehabilitate/replace guardrail posts, sections, and end sections. | 374200 | 374200 | 2021-11-18 | 0 | 2024-04-26 | 2025-11-05 | 374200 | Authorized | Authorized | No | Closed | State | 0
H10-10-023 | 10 | 5008218 | 10 | Stockton | San Joaquin County | SJCOG | SJCOG | Various locations throughout the City. | Install reflective thermoplastic edgelines where existing striped edgelines have significantly faded and road departures exist. | 250000 | 250000 | 0 | 0 | 2025-07-18 | 0 | 250000 | No PE | Authorized | No | CON | State | 0
H11-10-008 | 11 | 5008204 | 10 | Stockton | San Joaquin County | SJCOG | SJCOG | On Wilson Way between Hazelton Ave. and Anderson St. | Install safety lighting in the median. | 1457000 | 1311300 | 2023-06-16 | 0 | 0 | 0 | 215820 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE | State | 0
H11-10-009 | 11 | 5008210 | 10 | Stockton | San Joaquin County | SJCOG | SJCOG | Various segments along South El Dorado Street between Clayton Avenue to Third Street. | Install RRFB devices, crosswalks, bulb outs, bike boxes, bicycle video detection at all intersections, install painted buffers, and cycle track; construct median refuge islands and sidewalks; and roadway reconfiguration within two segments. | 2350000 | 2115000 | 2023-11-28 | 0 | 0 | 0 | 355500 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE | Federal | 2
H11-10-010 | 11 | 5008211 | 10 | Stockton | San Joaquin County | SJCOG | SJCOG | Hammer Lane corridor, including five intersections at Lower Sacramento Road on the west, Etna Street, El Dorado Street, Lan Ark Drive, and Tam O'Shanter Drive on the east. | Add edgeline, lane striping, pavement markings, speed feedback signs and pedestrian-scale lighting, install reflective signal backplates, and convert the existing Class II bike lanes to 7-ft protected bike lanes. | 1927800 | 1735020 | 2024-04-02 | 0 | 0 | 0 | 256500 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE | State | 0
H11-10-011 | 11 | 5008209 | 10 | Stockton | San Joaquin County | SJCOG | SJCOG | Lorraine Avenue and Hammer Lane, Wilson Way and Park Street, Wilson Way and Waterloo Road. | Install a leading pedestrian interval, high visibility crosswalk, left-turn phasing, curb extensions, raised median, curb ramps, and left turn lanes. | 2877200 | 2589480 | 2023-11-24 | 0 | 0 | 0 | 461340 | Authorized | Due by 3/31/2027 | No | PE | Federal | 2
H12-10-007 | 12 | 5008223 | 10 | Stockton | San Joaquin County | SJCOG | SJCOG | Carolyn Weston Blvd at French Camp Slough, Arch Airport Overpass, Eight Mile Road at Pixley Slough Bridge, West Lane at Calaveras River, Eight Mile Road & Hwy 99 W Frontage Road, Myrtle St west of Hwy 99, and Hwy 99 W Frontage Road at Mosher Slough. | Remove existing guardrails and replace with Midwest Guardrail System (MGS) guardrails. | 930000 | 837000 | 2025-08-21 | 0 | 0 | 0 | 144000 | Authorized | Due by 3/31/2028 | No | PE | State | 0
H12-10-008 | 12 | 5008226 | 10 | Stockton | San Joaquin County | SJCOG | SJCOG | The intersections at Fred Russo Lane and March Lane, Precissi Lane and March Lane, and Montauban Avenue and Hammer Lane. | Install protected left-turn signal heads, larger signal lens, retro-reflective back-plates, high reflectivity lane and crosswalk markings, traffic video detection system, and accessible pedestrian signals & near side signal heads at select locations. | 2195100 | 1975590 | 2025-12-10 | 0 | 0 | 0 | 297000 | Authorized | Due by 3/31/2028 | No | PE | Federal | 0
H12-10-009 | 12 | 5008225 | 10 | Stockton | San Joaquin County | SJCOG | SJCOG | B Street intersections at Industrial Drive and Boeing Way. | Construct roundabouts. | 2857900 | 2572110 | 2025-11-04 | 0 | 0 | 0 | 459360 | Authorized | Due by 3/31/2028 | No | PE | Federal | 0
H8-10-010 | 8 | 5008166 | 10 | Stockton | San Joaquin County | SJCOG | SJCOG | Dr. Martin Luther King, Jr. Blvd. between N. El Dorado St. and S. Aurora St., at the intersections of S. San Joaquin St., California St. and S. Grant St. | Convert signals from pedestal-mounted to mast arms (at the intersections with San Joaquin St., California St. and Grant St.), and provide protected left-turns (at the intersections with San Joaquin St. and Grant St.). | 1683279.88 | 1601587.5 | 2017-07-19 | 0 | 2019-11-27 | 2024-11-20 | 1601587.5 | Authorized | Authorized | No | Closed | Federal | 0
H8-10-011 | 8 | 5008167 | 10 | Stockton | San Joaquin County | SJCOG | SJCOG | Dr. Martin Luther King, Jr. Blvd. between Bieghle Alley and Mariposa Rd. | Install raised median. | 687994.47 | 454995.65 | 2017-07-10 | 0 | 2020-01-16 | 2022-11-23 | 454995.65 | Authorized | Authorized | No | Closed | Federal | 0
H8-10-012 | 8 | 5008168 | 10 | Stockton | San Joaquin County | SJCOG | SJCOG | Sixteen (16) locations throughout the City of Stockton. | Upgrade the existing guardrails with new guardrails, transition rails and end treatments. | 1125388.32 | 1125388.32 | 2017-07-20 | 0 | 2019-09-11 | 2022-01-21 | 1125388.32 | Authorized | Authorized | No | Closed | Federal | 0
H8-10-013 | 8 | 5008161 | 10 | Stockton | San Joaquin County | SJCOG | SJCOG | Nine (9) intersectoins in the Weston Ranch subdivision in the southwestern corner of the City of Stockton, just west of the Interstate-5 freeway. | Install Pedestrian Crossings (with enhanced safety feature) at Nine Intersections, to include high visibility crosswalks, RRFBs, PHB, and lighting enhancements. | 2189771.17 | 1639700 | 2017-06-23 | 0 | 2019-11-04 | 2021-12-23 | 1639700 | Authorized | Authorized | No | Closed | Federal | 0
H8-10-014 | 8 | 5008162 | 10 | Stockton | San Joaquin County | SJCOG | SJCOG | N. Eldorado St. between Morada Lane and W. Hammer Lane. | Reduce the travel lanes from four to three (Road Diet), to accommodate a center two-way left turn lane and install new bike lanes. | 613505.15 | 552154.63 | 2017-06-27 | 0 | 2020-01-23 | 2023-11-08 | 552154.63 | Authorized | Authorized | No | Closed | Federal | 0
H8-10-015 | 8 | 5008163 | 10 | Stockton | San Joaquin County | SJCOG | SJCOG | N. El Dorado St. between Essex St. and the Calaveras River Trail (near E. Ingram St.). | Install a raised median with pedestrian median fencing to prevent J-walking. | 399613.6 | 359652.23 | 2017-06-23 | 0 | 2021-06-15 | 2023-11-02 | 359652.23 | Authorized | Authorized | No | Closed | Federal | 0
H8-10-016 | 8 | 5008164 | 10 | Stockton | San Joaquin County | SJCOG | SJCOG | Pacific Ave. between Calaveras River Trail and W. Hammer Ln. | Install raised median curb between the existing median limits at various locations. | 1631158.78 | 1344567 | 2017-06-23 | 0 | 2019-10-18 | 2023-11-08 | 1344567 | Authorized | Authorized | No | Closed | Federal | 0
H9-10-012 | 9 | 5008183 | 10 | Stockton | San Joaquin County | SJCOG | SJCOG | Intersections of El Dorado Street and Robinhood Drive, El Dorado Street and Benjamin Holt Drive, and March Lane and McGaw Street. | Add left-turn lanes, install left-turn phasing, and improve signal hardware at El Dorado Street intersections; install left-turn phasing and improve signal hardware at March Lane intersection. | 907843.76 | 817059.38 | 2019-04-19 | 0 | 2022-05-13 | 2025-04-25 | 817059.38 | Authorized | Authorized | No | Closed | Federal | 0
H9-10-013 | 9 | 5008184 | 10 | Stockton | San Joaquin County | SJCOG | SJCOG | Airport Way and Hazelton Avenue. | Add designated left-turn lanes to the intersection of Airport Way/Hazelton Avenue, combined with associated signal modifications and upgrades. Add sidewalk to close gaps and improve access for pedestrians on Airport Way along with other improvements. | 1869653.76 | 1682688.37 | 2019-06-06 | 0 | 2022-04-20 | 2025-10-21 | 1682688.37 | Authorized | Authorized | No | Closed | Federal | 0
H9-10-014 | 9 | 5008186 | 10 | Stockton | San Joaquin County | SJCOG | SJCOG | Dr. Martin Luther King, Jr. Blvd (E. Charter Way) and S. Aurora St. | Install pathway with bot dots/or other separation device (to avoid vehicles encroaching within the pedestrian walkway) along Dr. Martin Luther King, Jr. Boulevard (East Charter Way) at South Aurora Street, and install pedestrian median fencing on Dr. MLK Jr. Boulevard (East Charter Way) to avoid jaywalking and unsafe mid-block crossing. Add guardrail on N/S of Dr. MLK Jr. Boulevard, signage (regulatory and warning) at various locations, replace curb ramps, additional pavement markings, and additional lighting. | 729723.82 | 656751.43 | 2019-06-21 | 0 | 2022-03-25 | 2025-04-14 | 656751.43 | Authorized | Authorized | No | Closed | Federal | 0
H9-10-015 | 9 | 5008185 | 10 | Stockton | San Joaquin County | SJCOG | SJCOG | Four crossing locations, including Alpine Avenue at Sutter Street, Pacific Avenue at Elm Street, El Dorado Street at Iris Avenue and Hunter Street at Channel Street. | Install Rectangular Rapid Flashing Beacons (RRFBs), signing & pavement marking. | 250000 | 249992.45 | 2019-06-21 | 0 | 2021-06-28 | 2024-11-04 | 249992.45 | Authorized | Authorized | No | Closed | Federal | 0
HSIP2-10-001 | 2 | 5008093 | 10 | Stockton | San Joaquin County | SJCOG | SJCOG | Intersections Of Airport Way And Park St., Airport Way And Oak St., And Airport Way And Fremont St. | Install Audible And Countdown Signal Heads; Upgrade Traffic Signals And Curb Ramps; Install Left-Turn Lanes And Phasing; Install Priority Control System | 878387.3 | 790278.29 | 2010-02-12 | 0 | 2012-04-02 | 2014-12-17 | 790278.29 | Authorized | Authorized | No | Closed | Federal | 0
HSIP2-10-004 | 2 | 5008101 | 10 | Stockton | San Joaquin County | SJCOG | SJCOG | Intersection Of El Dorado St. And Charter Way | Install Audible And Countdown Signal Heads; Upgrade Traffic Signals And Curb Ramps | 239356.14 | 215420.52 | 2010-09-09 | 0 | 2012-04-26 | 2014-10-24 | 215420.52 | Authorized | Authorized | No | Closed | Federal | 0
HSIP3-10-001 | 3 | 5008102 | 10 | Stockton | San Joaquin County | SJCOG | SJCOG | Along The Curve Of Glacier Point Dr. In Front Of Ansel Adams Elementary And Near Matt Equinoa Park | Install Raised Curb Median | 74645.34 | 67103.24 | 2010-11-08 | 0 | 2012-06-08 | 2015-01-05 | 67103.24 | Authorized | Authorized | No | Closed | Federal | 0
HSIP4-10-001 | 4 | 5008108 | 10 | Stockton | San Joaquin County | SJCOG | SJCOG | Various locations throughout the city | Install speed feedback signs | 290791.36 | 261712.19 | 2011-08-01 | 0 | 2012-04-20 | 2014-11-24 | 261712.19 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-10-012 | 5 | 5008124 | 10 | Stockton | San Joaquin County | SJCOG | SJCOG | Various locations on Brookside Rd., Davis Rd., Wagner Heights Rd., Scott Creek Dr., Tam O' Shanter Dr., Alexandria Pl., Feather River Dr., and Carolyn Weston Blvd. | Install flashing beacons; upgrade crosswalks and signs | 539522.08 | 319936.82 | 2013-04-17 | 0 | 2016-07-13 | 2018-10-15 | 319936.82 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-10-013 | 5 | 5008128 | 10 | Stockton | San Joaquin County | SJCOG | SJCOG | Harding Way/El Dorado St.; Harding Way/Center St. | Upgrade traffic signals and curb ramps; modify protected left-turn phasing | 706933.22 | 636239.88 | 2013-06-21 | 0 | 2015-07-28 | 2019-07-24 | 636239.88 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-10-014 | 5 | 5008131 | 10 | Stockton | San Joaquin County | SJCOG | SJCOG | California St./Washington St.; California St./Lafayette St. | Upgrade traffic signals and curb ramps; install pedestrian countdown heads and audible signals | 671246.03 | 601800 | 2013-09-17 | 0 | 2015-08-28 | 2019-08-29 | 601800 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-10-015 | 5 | 5008125 | 10 | Stockton | San Joaquin County | SJCOG | SJCOG | Twenty-one (21) intersections throughout the city | Install Emergency Vehicle Pre-emption (EVP) systems | 1071991.31 | 729131.53 | 2013-06-12 | 0 | 2015-07-28 | 2020-03-17 | 729131.53 | Authorized | Authorized | No | Closed | Federal | 0
HSIP6-10-006 | 6 | 5008135 | 10 | Stockton | San Joaquin County | SJCOG | SJCOG | Arch Airport Rd/B St | Install traffic signals | 571121.44 | 496685.61 | 2014-11-17 | 0 | 2017-07-25 | 2020-02-10 | 496685.61 | Authorized | Authorized | No | Closed | Federal
HSIP6-10-007 | 6 | 5008136 | 10 | Stockton | San Joaquin County | SJCOG | SJCOG | On West Lane between Knickerbocker Dr and Morada Lane; On West Lane Frontage Rd between Knickerbocker Dr and Morada Lane | Construct curb, sidewalks, curb ramps, gutter; install drainage, striping and signs; modify electrical | 1064806.6 | 911758.5 | 2014-11-17 | 0 | 2017-07-10 | 2023-02-09 | 911758.5 | Authorized | Authorized | No | Closed | Federal
HSIP6-10-008 | 6 | 5008137 | 10 | Stockton | San Joaquin County | SJCOG | SJCOG | On El Dorado St between Duncan Ave and E Alpine Ave | Upgrade traffic signals (interconnect) ; Install detection | 268557.75 | 183716.5 | 2014-11-24 | 0 | 2017-07-17 | 2019-11-08 | 183716.5 | Authorized | Authorized | No | Closed | Federal
HSIP6-10-009 | 6 | 5008133 | 10 | Stockton | San Joaquin County | SJCOG | SJCOG | Various locations throughout Stockton | Install Rectangular Rapid Flashing Beacons; Upgrade signs and crosswalks | 657933.51 | 591605.89 | 2014-09-04 | 0 | 2016-08-05 | 2020-03-17 | 591605.89 | Authorized | Authorized | No | Closed | Federal
HSIP6-10-010 | 6 | 5008134 | 10 | Stockton | San Joaquin County | SJCOG | SJCOG | 28 intersections throughout Stockton | Upgrade traffic signals | 367073.71 | 367073.71 | 2014-10-24 | 0 | 2016-07-01 | 2018-07-03 | 367073.71 | Authorized | Authorized | No | Closed | Federal
HSIP7-10-013 | 7 | 5008153 | 10 | Stockton | San Joaquin County | SJCOG | SJCOG | Multiple locations on Manthey Rd., Brookside Rd., Feather River Dr., Bianchi Rd. | Install high friction surface treatments (HFST) and variable speed warning signs at certain horizontal curves | 1138978.23 | 841346.13 | 2016-05-13 | 0 | 2019-10-18 | 2023-01-25 | 841346.13 | Authorized | Authorized | No | Closed | Federal
HSIP7-10-014 | 7 | 5008151 | 10 | Stockton | San Joaquin County | SJCOG | SJCOG | Intersection of South Airport Way and East Sonora Street, south of the Crosstown Freeway (SR-4). | Pedestrian crossing improvements, install high-intensity activated crosswalk (HAWK) pedestrian crossing and install pedestrian crossing at uncontrolled locations (new signs and markings only). | 547649.07 | 544542.58 | 2016-04-29 | 0 | 2019-09-10 | 2023-12-01 | 544542.58 | Authorized | Authorized | No | Closed | Federal
HSIP7-10-015 | 7 | 5008154 | 10 | Stockton | San Joaquin County | SJCOG | SJCOG | Intersections of N. Filbert St. / E. Myrtle St. and N. Filbert St. / E. Market St., at the Filbert St. exits of the Crosstown Freeway (SR-4). | Install Emergency vehicle Premption | 173629.22 | 173629.22 | 2016-05-24 | 0 | 2017-07-10 | 2019-01-10 | 173629.22 | Authorized | Authorized | No | Closed | Federal
HSIP7-10-016 | 7 | 5008152 | 10 | Stockton | San Joaquin County | SJCOG | SJCOG | Along S. Airport Way and Industrial Dr. | Install guardrail, transition railing and crash cushions, re-striping of the roadway and other improvements. | 299918.98 | 276385.85 | 2016-05-13 | 0 | 2019-09-10 | 2024-06-03 | 276385.85 | Authorized | Authorized | No | Closed | Federal
HSIP7-10-017 | 7 | 5008155 | 10 | Stockton | San Joaquin County | SJCOG | SJCOG | On North Hunter Street between West Harding Way and East Miner Ave. | To reduce the travel lanes from four lanes to three (Road Diet), to accommodate a center two-way left turn lane and install new bike lanes. | 469198.55 | 404609.89 | 2016-06-22 | 0 | 2019-10-18 | 2023-10-30 | 404609.89 | Authorized | Authorized | No | Closed | Federal
HSIP1-10-008 | 1 | 5215009 | 10 | Sutter Creek | Amador County | RURAL | Amador LTC | Old Sutter Hill Road At Ridge Road Approximately 0.1 Miles East Of The Sr 104 Intersection With Sr 49. | Realign Old Sutter Hill Road Intersection With Ridge Road; Includes The Realignment Of Old Ridge Road. | 905159.63 | 814643.67 | 2008-03-19 | 2013-03-08 | 2015-08-04 | 2018-06-06 | 814643.67 | Authorized | Authorized | No | Closed | Federal | 0
H11-10-007 | 11 | 5192059 | 10 | Tracy | San Joaquin County | SJCOG | SJCOG | Various signalized intersections throughout the City of Tracy. | Installation of a combination of engineering countermeasures (backplates, LPI, etc.) and updating the current signal equipment. | 2620700 | 2358630 | 0 | 0 | 2026-03-27 | 0 | 2358630 | No PE | Authorized | No | CON | State | 0
H12-10-010 | 12 | 5192058 | 10 | Tracy | San Joaquin County | SJCOG | SJCOG | Multiple unsignalized intersections and 2 roadway segments throughout the City of Tracy. | Install larger stop signs, update intersection parking marking, and improve sight distance at identified unsignalized intersections throughout the city systematically. | 1153600 | 1038240 | 2025-10-21 | 0 | 0 | 0 | 185400 | Authorized | Due by 3/31/2028 | No | PE | State | 0
H11-10-012 | 11 | 5932108 | 10 | Tuolumne County | Tuolumne County | RURAL | TCTC | Various locations throughout the county. | Upgrade existing guardrails and end treatments. | 1111000 | 999900 | 2024-08-12 | 0 | 0 | 0 | 0 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE | Federal | 1
H12-10-011 | 12 | 0 | 10 | Tuolumne County | Tuolumne County | RURAL | TCTC | The non-signalized intersection at Tuolumne Road, Black Oak Road, and Woodhams Carne Road. | Add lighting, improve sight distance for vehicles, and install high-friction surface treatment (HFST) approaching and through the intersection. | 806500 | 725850 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2025) | Due by 3/31/2028 | Yes (PE) | Not Started | State | 0
H12-10-012 | 12 | 0 | 10 | Tuolumne County | Tuolumne County | RURAL | TCTC | Multiple guardrail locations on Bonds Flat Road, La Grange Road, O'Byrnes Ferry Road, Parrotts Ferry Road, Rawhide Road, Kewin Mill Road, and Longeway Road. | Remove and replace existing guardrail systems with upgraded steel-post Midwest Guardrail System (MGS) guardrails. | 1109400 | 998460 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2025) | Due by 3/31/2028 | Yes (PE) | Not Started | Federal | 1
H12-10-013 | 12 | 0 | 10 | Tuolumne County | Tuolumne County | RURAL | TCTC | Tuolumne Road from Mono Way in East Sonora to Tuolumne Road North in Tuolumne City. | Enhance the centerline striping with the addition of recessed retroreflective pavement markers. | 147200 | 132480 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2025) | Due by 3/31/2028 | Yes (PE) | Not Started | State | 0
H8-10-017 | 8 | 5932094 | 10 | Tuolumne County | Tuolumne County | RURAL | TCTC | Various locations including: O'Byrnes Ferry Road; Rawhide Road; Twain Harte Drive; Little Fuller Road; Old Priest Grade; Parrotts Ferry Road; Dodge Ridge Road. | Upgrade existing guardrails. | 271022.73 | 271022.73 | 2017-09-12 | 0 | 2019-09-16 | 2020-12-28 | 271022.73 | Authorized | Authorized | No | Closed | Federal | 0
H8-10-018 | 8 | 5932093 | 10 | Tuolumne County | Tuolumne County | RURAL | TCTC | Intersection of Shaws Flat Road at State Route 49. | Install upgraded LED-enhanced flashing stop and stop ahead signs; Install transverse rumble strips; and improve sight distance. | 99080 | 89171.99 | 2017-08-10 | 0 | 2020-07-13 | 2022-02-23 | 89171.99 | Authorized | Authorized | No | Closed | Federal | 0
HSIP1-10-009C | 1 | 5932062 | 10 | Tuolumne County | Tuolumne County | RURAL | TCTC | Entire Length Of La Grange Road; 13 Miles; 3 Miles Of Tuolumne Road Between Soulsbyville Road And Wards Ferry Road. | Install Centerline Rumble Strip And High Visibility Paint. | 138734.18 | 124860.74 | 0 | 0 | 2011-04-19 | 2013-11-05 | 124860.74 | No PE | Authorized | No | Closed | Federal | 0
HSIP2-10-008 | 2 | 5932045 | 10 | Tuolumne County | Tuolumne County | RURAL | TCTC | Two Locations On Old Priest Grade Road | Install 2500 Lf Of Guardrail; Widen Shoulders | 753105.92 | 525638.37 | 2008-12-19 | 2009-09-03 | 2010-03-08 | 2013-02-13 | 525638.37 | Authorized | Authorized | No | Closed | Federal | 0
HSIP4-10-002 | 4 | 5932066 | 10 | Tuolumne County | Tuolumne County | RURAL | TCTC | Various locations throughout the county | Upgrade regulatory and warning signs | 157286.31 | 141406.69 | 2011-06-11 | 0 | 2013-09-04 | 2016-10-21 | 141406.69 | Authorized | Authorized | No | Closed | Federal | 0
HSIP4-10-002con | 4 | 5932089 | 10 | Tuolumne County | Tuolumne County | RURAL | TCTC | Various locations throughout the county | Upgrade regulatory and warning signs | 433714.6 | 390343.11 | 0 | 0 | 2016-11-10 | 2019-10-31 | 390343.11 | No PE | Authorized | No | Closed | Federal | 0
HSIP6-10-011 | 6 | 5932083 | 10 | Tuolumne County | Tuolumne County | RURAL | TCTC | On Parrots Ferry Rd-Broadway St between SR 49 and Union Hill Rd | Widen roadway; upgrade right-turn lane; Install left-turn lane | 1777411.57 | 913202.68 | 2014-06-23 | 2017-10-30 | 2019-09-16 | 2024-08-22 | 913202.68 | Authorized | Authorized | No | Closed | Federal
HSIP6-10-013 | 6 | 5932082 | 10 | Tuolumne County | Tuolumne County | RURAL | TCTC | On Phoenix Lake Rd between Ridgewood Dr and Paseo De Los Portales Rd | Widen roadway; Construct shoulders; Upgrade drainage | 1081215.45 | 973093.9 | 2014-06-23 | 2019-11-27 | 2021-07-27 | 2025-03-24 | 973093.9 | Authorized | Authorized | No | Closed | Federal
HSIP7-10-005 | 7 | 5932090 | 10 | Tuolumne County | Tuolumne County | RURAL | TCTC | Various locations throughout Tuolumne County | Roadway Safety Signing Audit (RSSA) | 911972.02 | 905486.47 | 2016-11-07 | 0 | 2020-08-05 | 2024-02-27 | 905486.47 | Authorized | Authorized | No | Closed | Federal
H8-10-019 | 8 | 5165091 | 10 | Turlock | Stanislaus County | STANCOG | Stan COG | Intersections of North Ave. and Loyola Way, N. Johnson Rd. and Carrigan St., South Ave. and Martinez St., and Berkeley Ave. and Heathernoel Way. | Install pedestrian crossing enhancements, including pedestrian activated RRFB systems, accessible ramps, high-visibility crosswalk striping and various related improvements. | 391781.88 | 249800 | 2017-12-15 | 0 | 2019-12-19 | 2022-05-31 | 249800 | Authorized | Authorized | No | Closed | Federal | 0
HSIP6-10-014 | 6 | 5165077 | 10 | Turlock | Stanislaus County | STANCOG | Stan COG | N Olive Dr/Wayside Dr | Install traffic signals, signs, striping, and various NI components; Construct curb, gutter, sidewalk, and curb ramps; pavement overlay | 888129.41 | 338778.56 | 2014-02-03 | 2016-08-15 | 2018-04-16 | 2020-10-20 | 338778.56 | Authorized | Authorized | No | Closed | Federal
H9-11-001 | 9 | 0 | 11 | Barona Band of Mission Indians | San Diego County | SANDAG | SANDAG | The intersection of Ashwood Street/ Wildcat Canyon Road and Willow Road. | Install high visibility pedestrian crossings and advanced stop bars; install bike lane striping, edge-lines and centerlines; construct sidewalk and curb ramps; install pedestrian signal heads and safety lighting system. | 348300 | 248706 | 0 | 0 | 0 | 0 | 0 | Not Tracked | Not Tracked | No | Not Started | Federal | 0
H11-11-001 | 11 | 5167051 | 11 | Brawley | Imperial County | SCAG | ICTC | The intersection of Main Street with 8th Street. | Install traffic signal mast arm assembly, LED safety lighting, curb bulb out, median curb nose, ADA curb ramps, high visibility crosswalks, and pavement markings. | 277700 | 249930 | 2023-12-28 | 0 | 0 | 0 | 42210 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE | State | 0
H11-11-010 | 11 | 5167053 | 11 | Brawley | Imperial County | SCAG | ICTC | Dogwood Road from 550ft south of Mead Road to 750ft north of Mead Road. | Install roadway lighting, guardrails, chevron curve warning signs, rumble strips, roadway striping, pavement markings, and outside shoulder widening. | 940000 | 846000 | 2023-12-28 | 0 | 0 | 0 | 94500 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE | State | 0
HSIP1-11-001 | 1 | 5168018 | 11 | Calexico | Imperial County | SCAG | ICTC | Intersection Of Cole Road And Van De Graaff Ave.; Cole Rd. Between Sr 111 And Van De Graaff Avenue. | Install Traffic Signal; Construct Concrete Median. | 287442.39 | 253738.7 | 0 | 0 | 2010-08-23 | 2013-02-21 | 253738.7 | No PE | Authorized | No | Closed | Federal | 0
HSIP3-11-014 | 3 | 6211113 | 11 | Calexico | Imperial County | SCAG | ICTC | Cesar Chavez Blvd. And Sr 98/West Birch St. | Install Traffic Signal; Construct Ac Pavement, Curb, Gutter, Sidewalk And Curb Ramps; Install Traffic Signs, Stripes And Pavement Markings | 1569577 | 1377474.61 | 2012-07-10 | 2012-08-08 | 2016-07-27 | 2021-12-15 | 1377474.61 | Authorized | Authorized | No | Closed | Federal | 0
H10-11-001&002 | 10 | 5308024 | 11 | Carlsbad | San Diego County | SANDAG | SANDAG | Carlsbad Bl at Oak Avenue, Carlsbad Bl at Sycamore Avenue, Carlsbad Bl at Maple Avenue, Carlsbad Bl at Cherry Avenue, and Carlsbad Bl at Hemlock Avenue, and Carlsbad Bl between Mountain View Drive and Cypress Avenue. | Install pedestrian enhancements at existing intersection/mid block crosswalks. The improvements include curb extensions, pedestrian-activated in roadway warning lights, green bicycle lanes and ADA curb ramps. | 657600 | 591600 | 0 | 0 | 2022-03-10 | 2025-11-06 | 591600 | No PE | Authorized | No | Closed | State | 0
H11-11-002 | 11 | 5308026 | 11 | Carlsbad | San Diego County | SANDAG | SANDAG | Paseo Del Norte between Palomar Airport Road and Camino Del Parque. | Install wider separated bike lanes by restriping to add 8 foot buffers. Install an enhanced mid-block pedestrian crossing with curb extensions, refuge island, RRFB & street lights. | 593900 | 534510 | 2023-08-15 | 0 | 0 | 0 | 97200 | Authorized | Due by 6/30/2027 | No | PE | State | 0
H10-11-003 | 10 | 5203054 | 11 | Chula Vista | San Diego County | SANDAG | SANDAG | North Second Avenue between C Street and Bayview Way. | Upgrade existing guardrail on easterly frontage of North Second Avenue. | 227500 | 227500 | 2021-09-30 | 2022-06-13 | 2024-04-16 | 2025-10-16 | 227500 | Authorized | Authorized | No | Closed | State | 0
H12-11-001 | 12 | 0 | 11 | Chula Vista | San Diego County | SANDAG | SANDAG | Olympic Parkway from Brandywine Avenue to Eastlake Parkway. | Install separated bike lanes, variable speed feedback signs, and high-visibility crosswalks and signage. | 1955900 | 1760310 | 0 | 0 | 0 | 0 | 0 | RFA received 03/12/2026 | Due by 3/31/2028 | No | Not Started | Federal | 2
H8-11-001 | 8 | 5203046 | 11 | Chula Vista | San Diego County | SANDAG | SANDAG | Various locations citywide. | Install pedestrian countdown signals. | 1312477.08 | 1215900 | 2017-10-19 | 0 | 2019-06-24 | 2021-11-21 | 1215900 | Authorized | Authorized | No | Closed | Federal | 0
H8-11-002 | 8 | 5203047 | 11 | Chula Vista | San Diego County | SANDAG | SANDAG | Various locations west of I-805 and east of I-5 to City Limits and signals along Main St. | Retiming of traffic signals and installation of fiber optic/ethernet communication system. | 1346626.85 | 644679.77 | 2017-10-16 | 0 | 2019-10-24 | 2022-10-25 | 644679.77 | Authorized | Authorized | No | Closed | Federal | 0
H8-11-003 | 8 | 5203048 | 11 | Chula Vista | San Diego County | SANDAG | SANDAG | Five (5) intersections: Broadway and Anita Street; Third Avenue and Oxford Street; Fifth Avenue and “E” Street; Fifth Avenue and “F” Street; Fifth Avenue and “G” Street. | Provide for protected left turn movement at two intersections and install traffic signals on mast arms at three intersections. | 1736582.04 | 1157633 | 2017-10-19 | 0 | 2019-10-24 | 2022-11-23 | 1157633 | Authorized | Authorized | No | Closed | Federal | 0
H9-11-002 | 9 | 5203052 | 11 | Chula Vista | San Diego County | SANDAG | SANDAG | Various locations citywide. | Install Lead Pedestrian Interval Operations. | 2233900 | 2233900 | 2019-09-13 | 0 | 2022-03-29 | 0 | 2233900 | Authorized | Authorized | No | CON | Federal | 0
HSIP1-11-002 | 1 | 5203025 | 11 | Chula Vista | San Diego County | SANDAG | SANDAG | 31 High-Priority Intersections City-Wide | Upgrade Traffic Signals, Pavement Markings And Delineation; Make Improvements To Bicycle And Pedestrian Facilities City-Wide. | 1540655.2 | 899998 | 2007-11-09 | 0 | 2010-01-07 | 2013-11-07 | 899998 | Authorized | Authorized | No | Closed | Federal | 0
HSIP3-11-002 | 3 | 5203031 | 11 | Chula Vista | San Diego County | SANDAG | SANDAG | Intersection Of Fourth Ave. And "G" St. | Modify Traffic Signals To Provide Protected Left-Turn | 252928.32 | 227635 | 2010-11-08 | 0 | 2012-05-18 | 2013-09-20 | 227635 | Authorized | Authorized | No | Closed | Federal | 0
HSIP3-11-003 | 3 | 5203032 | 11 | Chula Vista | San Diego County | SANDAG | SANDAG | Naples St. Between Fifth Ave. And Broadway | Construct Curb, Gutter, Sidewalks, And Curb Ramps; Resurface Roadway; Modify Traffic Signal, Install Striping | 355724.9 | 289799.65 | 2010-11-08 | 0 | 2012-04-18 | 2013-09-20 | 289799.65 | Authorized | Authorized | No | Closed | Federal | 0
HSIP4-11-009 | 4 | 5203034 | 11 | Chula Vista | San Diego County | SANDAG | SANDAG | K St./Third Ave. | Upgrade traffic signals; install safety lighting and pavement markings; construct curb ramps | 326982.41 | 282200 | 2011-08-25 | 0 | 2012-11-09 | 2014-03-26 | 282200 | Authorized | Authorized | No | Closed | Federal | 0
HSIP4-11-011 | 4 | 5203035 | 11 | Chula Vista | San Diego County | SANDAG | SANDAG | Oxford St. between Broadway and Fifth Ave. | Construct curb, gutter, sidewalks, driveways, and curb ramps; install signs, striping, and pavement markings | 360057.99 | 290600 | 2011-08-25 | 0 | 2013-03-12 | 2014-06-26 | 290600 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-11-001 | 5 | 5203038 | 11 | Chula Vista | San Diego County | SANDAG | SANDAG | Third Ave./"J" St.; Third Ave./Naples St. | Upgrade traffic signals; modify protected left-turn phasing; install push buttons, signs, striping, and safety lighting; construct curb ramps | 406025.08 | 318500 | 2013-07-09 | 0 | 2013-11-25 | 2015-12-18 | 318500 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-11-002 | 5 | 5203037 | 11 | Chula Vista | San Diego County | SANDAG | SANDAG | Moss St. between Third Ave. and Fourth Ave. | Install protected left-turn phasing and pedestrian improvements; construct sidewalks | 443567.51 | 265551.59 | 2013-07-09 | 0 | 2014-07-31 | 2016-05-09 | 265551.59 | Authorized | Authorized | No | Closed | Federal | 0
HSIP6-11-001 | 6 | 5203040 | 11 | Chula Vista | San Diego County | SANDAG | SANDAG | Hilltop Dr/L St, Fourth Ave/J St, Third Ave/I St, and Third Ave/H St | Upgrade traffic signals; install pedestrian countdown heads; install protected left-turn phasing; upgrade ramps, lights, signs and striping | 1251093.49 | 715733.2 | 2015-06-18 | 0 | 2017-06-29 | 2020-11-24 | 715733.2 | Authorized | Authorized | No | Closed | Federal
HSIP6-11-002 | 6 | 5203041 | 11 | Chula Vista | San Diego County | SANDAG | SANDAG | Various locations on Otay Lakes Rd, Telegraph Canyon Rd, and East H St | Upgrade traffic signals | 1308086.76 | 592780.28 | 2015-06-18 | 0 | 2016-08-22 | 2020-01-30 | 592780.28 | Authorized | Authorized | No | Closed | Federal
HSIP7-11-001 | 7 | 5203045 | 11 | Chula Vista | San Diego County | SANDAG | SANDAG | At Broadway/F street and Broadway/G Street | Provide protected left-turn phases | 669012.87 | 481584.42 | 2016-08-25 | 0 | 2018-01-16 | 2021-07-14 | 481584.42 | Authorized | Authorized | No | Closed | Federal
HSIP7-11-002 | 7 | 5203043 | 11 | Chula Vista | San Diego County | SANDAG | SANDAG | At 4 intersections: H Street / Oaklawn Ave, Fourth Ave / Park Way, Fourth Ave / Davidson St, H Street / Woodlawn Ave | Install pedestrian crossing and protected left-turn phase | 794618.4 | 379771.02 | 2016-08-11 | 0 | 2017-08-09 | 2020-02-20 | 379771.02 | Authorized | Authorized | No | Closed | Federal
HSIP7-11-003 | 7 | 5203044 | 11 | Chula Vista | San Diego County | SANDAG | SANDAG | On Palomar St between Industrial Blvd to Broadway | InstallbBike Lanes and sidewalks | 489517.84 | 345999.44 | 2016-07-27 | 0 | 2017-10-19 | 2021-01-21 | 345999.44 | Authorized | Authorized | No | Closed | Federal
H10-11-004 | 10 | 5211043 | 11 | El Cajon | San Diego County | SANDAG | SANDAG | Washington Ave between Avocado Ave and Mollison Ave. | Install high visibility pedestrian crossings at signalized intersections, a Pedestrian Hybrid Beacon, and raised medians along the corridor. | 2404836 | 2134030 | 2022-01-24 | 0 | 2025-09-16 | 0 | 2134030 | Authorized | Authorized | No | CON | State | 0
H10-11-005 | 10 | 5211042 | 11 | El Cajon | San Diego County | SANDAG | SANDAG | 11 unsignalized pedestrian crossings citywide. | Install Rectangular Rapid Flashing Beacons (RRFBs) and High Visibility Crosswalks. | 245900 | 245900 | 0 | 0 | 2021-09-03 | 2024-05-23 | 245900 | No PE | Authorized | No | Closed | State | 0
H12-11-002 | 12 | 5211046 | 11 | El Cajon | San Diego County | SANDAG | SANDAG | On Washington Ave. between First St. and Jamacha Rd. | Install raised concrete medians throughout the corridor. Install a high visibility pedestrian crossing at the intersection of Washington Ave. at Dorothy St. | 3133500 | 2820150 | 2025-11-13 | 0 | 0 | 0 | 297000 | Authorized | Due by 3/31/2028 | No | PE | Federal | 0
H8-11-004 | 8 | 5211037 | 11 | El Cajon | San Diego County | SANDAG | SANDAG | Washington Avenue between Third Street and Dehesa Road. | Reconfigure lane geometry from four travel lanes to three, add a two-way left-turn lane, bicycle lanes, and install roadway segment lighting. | 515261.07 | 330461.88 | 2017-07-19 | 0 | 2018-04-20 | 2020-06-05 | 330461.88 | Authorized | Authorized | No | Closed | Federal | 0
H9-11-003 | 9 | 5211040 | 11 | El Cajon | San Diego County | SANDAG | SANDAG | Jamacha Road and 2nd Street, from Washington Avenue to Broadway. | Install raised medians, high visibility pedestrian crossings at signalized intersections, curb extensions, and pedestrian crossings at uncontrolled locations (with enhanced safety features). | 2712300 | 2386824 | 2019-10-22 | 0 | 2022-07-31 | 0 | 2298270 | Authorized | Authorized | No | CON | Federal | 0
H9-11-004 | 9 | 5211041 | 11 | El Cajon | San Diego County | SANDAG | SANDAG | Madison Avenue from N. Johnson Avenue to 670 ft east of N. 2nd Street. | Install Class 2 bike lanes, uncontrolled pedestrian crossings, and street lighting. | 2784144.72 | 2285369 | 2019-10-22 | 0 | 2021-09-16 | 2024-08-02 | 2285369 | Authorized | Authorized | No | Closed | Federal | 0
HSIP4-11-003 | 4 | 5211020 | 11 | El Cajon | San Diego County | SANDAG | SANDAG | Various locations throughout the city | Upgrade regulatory and warning signs | 258135.15 | 230461.09 | 2011-08-25 | 0 | 2012-06-22 | 2014-03-04 | 230461.09 | Authorized | Authorized | No | Closed | Federal | 0
HSIP4-11-010 | 4 | 5211021 | 11 | El Cajon | San Diego County | SANDAG | SANDAG | Broadway/Third St. | Upgrade traffic signals with protected left-turn phasing | 73510.64 | 66081.56 | 2011-08-25 | 0 | 2012-01-11 | 2013-03-19 | 66081.56 | Authorized | Authorized | No | Closed | Federal | 0
HSIP4-11-012 | 4 | 5211022 | 11 | El Cajon | San Diego County | SANDAG | SANDAG | Main St./Jamacha Rd. (2nd St.) | Upgrade traffic signals with protected left-turn phasing; remove shared left-through lane; improve channelization; install pedestrian countdown heads | 401023.77 | 214199 | 2011-08-25 | 0 | 2012-08-31 | 2015-01-09 | 214199 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-11-003 | 5 | 5211026 | 11 | El Cajon | San Diego County | SANDAG | SANDAG | Ninety-seven (97) intersections throughout the city | Install pedestrian countdown heads | 113014.26 | 101653.26 | 2013-05-22 | 0 | 2013-09-18 | 2016-02-10 | 101653.26 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-11-004 | 5 | 5211027 | 11 | El Cajon | San Diego County | SANDAG | SANDAG | Greenfield Dr./North Second St. | Install protected left-turn phasing | 128337.01 | 92152.43 | 2013-05-22 | 0 | 2013-09-18 | 2015-06-18 | 92152.43 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-11-005 | 5 | 5211028 | 11 | El Cajon | San Diego County | SANDAG | SANDAG | Second St. (Jamacha Rd.) between Gustavo Rd. and Oakdale Ave. | Upgrade traffic signals (interconnect) | 120729.48 | 106144.91 | 2013-05-22 | 0 | 2014-01-08 | 2016-06-21 | 106144.91 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-11-006 | 5 | 5211029 | 11 | El Cajon | San Diego County | SANDAG | SANDAG | Various locations throughout the city | Upgrade signs | 117711.86 | 101856.7 | 2013-05-22 | 0 | 2014-05-06 | 2016-01-14 | 101856.7 | Authorized | Authorized | No | Closed | Federal | 0
HSIP6-11-003 | 6 | 5211031 | 11 | El Cajon | San Diego County | SANDAG | SANDAG | Various locations throughout El Cajon | Upgrade traffic signals (interconnect); Install "dilemma zone" detection | 891428.06 | 765707.16 | 2014-08-19 | 0 | 2015-12-28 | 2018-05-31 | 765707.16 | Authorized | Authorized | No | Closed | Federal
HSIP6-11-004 | 6 | 5211030 | 11 | El Cajon | San Diego County | SANDAG | SANDAG | 57 intersections throughout the City of El Cajon | Upgrade traffic signals | 295691.05 | 295211.04 | 2014-07-23 | 0 | 2015-03-25 | 2017-02-14 | 295211.04 | Authorized | Authorized | No | Closed | Federal
HSIP6-11-005 | 6 | 5211032 | 11 | El Cajon | San Diego County | SANDAG | SANDAG | On Avocado Ave-Ballantyne St between Skywood Dr and Madison Ave | Upgrade traffic signals (interconnect); Install "dilemma zone" detection and lighting | 425870.46 | 385681.12 | 2014-07-30 | 0 | 2015-08-03 | 2017-04-18 | 385681.12 | Authorized | Authorized | No | Closed | Federal
HSIP7-11-004 | 7 | 5211035 | 11 | El Cajon | San Diego County | SANDAG | SANDAG | Washington Ave. between Jamacha Rd. and El Cajon Blvd.; Chase Ave. between Anza St. and Johnson Ave.; El Cajon Blvd. between Boulevard Pl. and Main St.; Main St. between Travelodge Dr. and Magnolia Ave. | Installation of a traffic signal interconnect fiberoptic cable system to implement coordination timing and the installation of street lighting | 1019351.5 | 972051.5 | 2016-09-16 | 0 | 2017-10-19 | 2019-07-31 | 972051.5 | Authorized | Authorized | No | Closed | Federal
HSIP6-11-006 | 6 | 5169043 | 11 | El Centro | Imperial County | SCAG | ICTC | On Main St between 4th St and 8th St, on Dogwood Rd between South City limit and Danenberg Ave, S Imperial Ave/Aurora Dr, Ocotillo Dr/22nd St, S Imperial Ave/Holt Ave, S 8th St/Vine St | Install crosswalks, sidewalks, and lighting | 1797516.97 | 867200 | 2014-10-24 | 0 | 2016-07-25 | 2019-12-11 | 867200 | Authorized | Authorized | No | Closed | Federal
H10-11-006 | 10 | 5446034 | 11 | Encinitas | San Diego County | SANDAG | SANDAG | Coast Highway 101 from Swami's Pedestrian Crossing to Chesterfield Dr. | Install separated bike lanes. | 1294954 | 780000 | 0 | 0 | 2022-09-20 | 2024-06-07 | 780000 | No PE | Authorized | No | Closed | State | 0
H10-11-007 | 10 | 5446031 | 11 | Encinitas | San Diego County | SANDAG | SANDAG | Coast Highway 101 from South Cardiff State Beach Parking Lot to City Limits. | Install new sidewalk and retaining wall. | 1045700 | 941032 | 2021-10-11 | 0 | 2023-11-06 | 2026-01-28 | 941032 | Authorized | Authorized | No | Closed | State | 0
H10-11-008 | 10 | 5446036 | 11 | Encinitas | San Diego County | SANDAG | SANDAG | 48 intersections throughout the City of Encinitas. | Install Leading Pedestrian (LPI), traffic signal system upgrades for LPI operations, and high visibility crosswalk striping. | 1757915 | 1434500 | 2023-03-28 | 0 | 2024-08-27 | 0 | 1434500 | Authorized | Authorized | No | CON | State | 0
H11-11-003 | 11 | 5446037 | 11 | Encinitas | San Diego County | SANDAG | SANDAG | 6 unsignalized intersections throughout the City of Encinitas. | Install intersection lighting, LED flashing stop signs, ADA curb ramps, curb extensions, high-visibility crosswalks, and advanced school zone signs. | 609800 | 548820 | 2023-12-06 | 0 | 2025-01-09 | 0 | 548820 | Authorized | Authorized | No | CON | State | 0
H12-11-003 | 12 | 5446040 | 11 | Encinitas | San Diego County | SANDAG | SANDAG | Encinitas Boulevard from Calle Magdalena to Via Cantebria. | Install separated bike lanes. | 890400 | 801360 | 2025-12-02 | 0 | 0 | 0 | 143100 | Authorized | Due by 3/31/2028 | No | PE | State | 0
H12-11-004 | 12 | 5446041 | 11 | Encinitas | San Diego County | SANDAG | SANDAG | El Camino Real from Willowspring Dr to Avenida De Las Adelsas. | Install protected bike lanes. | 492000 | 442800 | 2025-12-02 | 0 | 0 | 0 | 76500 | Authorized | Due by 3/31/2028 | No | PE | State | 0
H12-11-005 | 12 | 5446043 | 11 | Encinitas | San Diego County | SANDAG | SANDAG | South Coast Highway 101 from City Limits (Solana Beach) to the North Cardiff State Beach Driveway (north of Los Olas). | Install sidewalk and path along the east side of South Coast Highway 101. | 1862900 | 1676610 | 2026-01-26 | 0 | 0 | 0 | 279000 | Authorized | Due by 3/31/2028 | No | PE | Federal | 2
H12-11-006 | 12 | 5446042 | 11 | Encinitas | San Diego County | SANDAG | SANDAG | South Coast Highwy 101 at Harbaugh Seaside Trails. | Install a pedestrian crossing at Harbaugh Seaside Trails including refuge median island, rectangular rapid flashing beacons (RRFBs), high visibility continental crosswalks and other signing and striping improvements. | 388800 | 349920 | 2025-12-02 | 0 | 0 | 0 | 58500 | Authorized | Due by 3/31/2028 | No | PE | State | 0
H8-11-005 | 8 | 5446022 | 11 | Encinitas | San Diego County | SANDAG | SANDAG | Intersections of Encinitas Blvd and Vulcan Avenue, Leucadia Boulevard and Quail Gardens Drive, Santa Fe Drive and Scripps Driveway, and Leucadia Boulevard and North Vulcan Avenue. | Replace existing permissive left-turn phases and signal heads with protected left-turn phases and signal heads on existing and/or new traffic signal poles and mast arms. | 532200 | 532200 | 2017-09-13 | 0 | 2022-05-13 | 0 | 532200 | Authorized | Authorized | No | CON | Federal | 0
H8-11-006 | 8 | 5446023 | 11 | Encinitas | San Diego County | SANDAG | SANDAG | North Coast Highway 101 from Jasper Street to Phoebe Street. | Install full pedestrian signal | 344037.22 | 298854.06 | 2017-09-13 | 0 | 2021-03-08 | 2023-12-27 | 298854.06 | Authorized | Authorized | No | Closed | Federal | 0
H8-11-007 | 8 | 5446024 | 11 | Encinitas | San Diego County | SANDAG | SANDAG | Corridors of 2nd St, Birmingham Dr, Coast Highway 101, El Camino Real, Encinitas Blvd, Garden View Rd, Leucadia Blvd, Mountain Vista Dr, Olivenhain Rd, Quail Garden Dr, Santa Fe Dr, Via Cantebria, Village Park Wy, and Vulcan Ave/San Elijo Ave. | Install LED luminaire safety lighting at signalized intersections and LED street lighting along project corridors. | 722770 | 718000 | 2017-09-13 | 0 | 2022-06-09 | 2025-05-29 | 718000 | Authorized | Authorized | No | Closed | Federal | 0
H9-11-005 | 9 | 5446028 | 11 | Encinitas | San Diego County | SANDAG | SANDAG | North Coast Highway 101 corridor from Basil Street to El Portal Street. | Install full pedestrian signal | 451932.45 | 451932.45 | 0 | 0 | 2021-03-16 | 2023-12-27 | 451932.45 | No PE | Authorized | No | Closed | Federal | 0
H9-11-006 | 9 | 5446026 | 11 | Encinitas | San Diego County | SANDAG | SANDAG | Santa Fe Drive between Gardena and Evergreen Rd | Install sidewalk/pathway to avoid walking along roadway. | 2098909 | 640696.99 | 2019-10-22 | 0 | 2022-11-17 | 2026-02-27 | 640696.99 | Authorized | Authorized | No | Closed | Federal | 2
H9-11-007 | 9 | 5446030 | 11 | Encinitas | San Diego County | SANDAG | SANDAG | El Camino Real approximately 350 ft south of Via Molena between the shopping centers of Encinitas Market Place and Encinitas Village. | Install a pedestrian staggered mid block crosswalk (z-crossing) with pedestrian hybrid beacon to connect pedestrians and bicyclists to the east and west sides of El Camino Real. | 509557.12 | 509557.12 | 0 | 0 | 2022-07-12 | 2025-06-12 | 509557.12 | No PE | Authorized | No | Closed | Federal | 0
HSIP4-11-004 | 4 | 5446018 | 11 | Encinitas | San Diego County | SANDAG | SANDAG | Santa Fe Dr. between I-5 and Nardo Rd. (Mackinnon Ave.) | Construct curb, gutter, sidewalks, and curb ramps; install signs, striping, and pavement markings | 658616.64 | 509160.99 | 0 | 0 | 2014-03-19 | 2019-12-18 | 509160.99 | No PE | Authorized | No | Closed | Federal | 0
HSIP5-11-007 | 5 | 5446019 | 11 | Encinitas | San Diego County | SANDAG | SANDAG | El Camino Real between Santa Fe and Leucadia Blvd.; Encinitas Blvd. between El Camino Real and Manchester Ave. | Upgrade traffic signals (interconnect) | 384373.84 | 345917.45 | 2013-08-21 | 0 | 2015-08-10 | 2019-11-08 | 345917.45 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-11-008 | 5 | 5446020 | 11 | Encinitas | San Diego County | SANDAG | SANDAG | Traffic signal intersections on the following corridors: Leucadia Blvd., Encinitas Blvd., SR 101, Via Cantebria, and Vulcan Ave | Upgrade traffic signals (interconnect) | 508424 | 457581.6 | 2013-08-21 | 0 | 2015-08-10 | 2018-08-16 | 457581.6 | Authorized | Authorized | No | Closed | Federal | 0
H10-11-009 | 10 | 5081027 | 11 | Escondido | San Diego County | SANDAG | SANDAG | Citywide | Install traffic signal interconnect system (conduit, monitoring devices, controllers, software and related communications equipment) to allow for improved safety operations and optimized signal coordination along sixteen coordinated signal groups. | 2321700 | 1160850 | 2021-08-10 | 0 | 2026-03-26 | 0 | 1160850 | Authorized | Authorized | No | CON | State | 0
H11-11-004 | 11 | 5081030 | 11 | Escondido | San Diego County | SANDAG | SANDAG | 12 signalized intersections within the city of Escondido. | Improve signal hardware including lenses, back plates with retroreflective borders, mounting and number; install pedestrian countdown signal heads; and modify the signal phasing to implement a leading pedestrian interval. | 1473600 | 1326240 | 2023-11-05 | 0 | 0 | 0 | 192870 | Authorized | Due by 3/31/2027 | No | PE | State | 0
HSIP2-11-001 | 2 | 6211107 | 11 | Escondido | San Diego County | SANDAG | SANDAG | Sr 78 At The Nordahl Rd. Overcrossing | Reconsruct Roadway To Increase Vertical Clearance. | 919043.33 | 826560 | 0 | 0 | 2011-08-15 | 2015-07-16 | 826560 | No PE | Authorized | No | Closed | Federal | 0
HSIP5-11-009 | 5 | 5081020 | 11 | Escondido | San Diego County | SANDAG | SANDAG | East Valley Pkwy. from Beven Dr. to Northern City Limits | Install sidewalk/pathway; add lighting; and improve signal hardware | 1049044 | 674954.9 | 0 | 0 | 2016-09-20 | 2021-01-06 | 674954.9 | No PE | Authorized | No | Closed | Federal | 0
HSIP6-11-007 | 6 | 5081019 | 11 | Escondido | San Diego County | SANDAG | SANDAG | E El Norte Parkway/N Fig St, E Valley Parkway/N Date St | Install traffic signals | 709587.98 | 682333.97 | 2014-03-26 | 0 | 2017-04-12 | 2021-07-01 | 682333.97 | Authorized | Authorized | No | Closed | Federal
HSIP4-11-007 | 4 | 5134013 | 11 | Imperial | Imperial County | SCAG | ICTC | Neckel Rd./SR 86 | Install traffic signals; construct intersection improvements | 1542777.85 | 1186192.97 | 2011-08-24 | 2016-01-11 | 2016-04-22 | 2020-06-05 | 1186192.97 | Authorized | Authorized | No | Closed | Federal | 0
H10-11-010 | 10 | 0 | 11 | Imperial County | Imperial County | SCAG | ICTC | Correll Rd between Dogwood Dr and Heber Ave; Rio Vista St between San Diego Ave and Haskell Rd; Shore Hawk Ave near intersection with Shore Gem St; and S. Marina Dr at intersection with Sea Palm Ave. | Install Rectangular Rapid Flashing Beacons (RRFBs) near schools. | 158000 | 158000 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2021) | Past due (due 9/30/2024) | Yes (PE & CON) | Not Started | State | 0
HRRR1-11-066 | 1 | 5958048 | 11 | Imperial County | Imperial County | SCAG | ICTC | Forrester Road Intersection at Cady Road | Turning Lanes (except for new left-turn lane) and Traffic Channelization | 757069.21 | 638445.24 | 2008-04-10 | 0 | 2009-07-08 | 2014-11-26 | 638445.24 | Authorized | Authorized | No | Closed | Federal | 0
HRRR1-11-067 | 1 | 5958049 | 11 | Imperial County | Imperial County | SCAG | ICTC | Worthington Road Intersection at McConnell Road | New left-turn lane at nonsignalized intersection | 124398.48 | 67000 | 2008-04-10 | 0 | 2008-09-15 | 2011-11-21 | 67000 | Authorized | Authorized | No | Closed | Federal | 0
HRRR1-11-068 | 1 | 5958065 | 11 | Imperial County | Imperial County | SCAG | ICTC | Worthington Road Intersection at McConnell Road | New left-turn lane at nonsignalized intersection | 251768.41 | 226591.56 | 0 | 0 | 2009-09-10 | 2013-04-24 | 226591.56 | No PE | Authorized | No | Closed | Federal | 0
HSIP2-11-009 | 2 | 5958060 | 11 | Imperial County | Imperial County | SCAG | ICTC | Intersection Of Forrester Rd. And Aten Rd. | Construct Northbound Right Turn Lane | 288154.77 | 224655.03 | 2009-04-21 | 0 | 2010-05-11 | 2013-01-04 | 224655.03 | Authorized | Authorized | No | Closed | Federal | 0
HSIP2-11-010 | 2 | 5958061 | 11 | Imperial County | Imperial County | SCAG | ICTC | Worthington Rd And Cooley Rd. | Install Right-Turn Lane. | 350154.43 | 280056.83 | 2010-04-17 | 0 | 2010-06-24 | 2016-02-12 | 280056.83 | Authorized | Authorized | No | Closed | Federal | 0
HSIP2-11-011 | 2 | 5958062 | 11 | Imperial County | Imperial County | SCAG | ICTC | Forrester Rd. And Worthington Rd. | Construct Right-Turn Lanes. | 1270829.94 | 647430.33 | 2009-04-17 | 0 | 2010-07-07 | 2018-06-13 | 647430.33 | Authorized | Authorized | No | Closed | Federal | 0
HSIP4-11-015 | 4 | 5958076 | 11 | Imperial County | Imperial County | SCAG | ICTC | SR 78 (SR 86)/S Marina Dr. | Install traffic signals; extend turning lanes | 2080344.96 | 785793.72 | 2011-09-15 | 0 | 2014-05-08 | 2018-06-13 | 785793.72 | Authorized | Authorized | No | Closed | Federal | 0
HSIP7-11-013 | 7 | 5958100 | 11 | Imperial County | Imperial County | SCAG | ICTC | Intersection of Keystone Road at Austin Road in Imperial County | Intersection Improvements; install intersection lighting; paving of the intersection, including rumble strips; and flashing beacons at stop signs and intersection warning signs. | 228811 | 205930.15 | 2017-04-12 | 0 | 2020-07-21 | 2022-10-25 | 205930.15 | Authorized | Authorized | No | Closed | Federal
HSIP7-11-014 | 7 | 5958099 | 11 | Imperial County | Imperial County | SCAG | ICTC | Weiman Road at Cady Road in Imperial County. | Intersection lighting, advance curve warning signs (flashing beacons), flashing beacon stop sign, upgraded chevron signs with fluorescent sheeting and installation of rumble strips. | 278903.01 | 135450 | 2017-01-26 | 0 | 2018-05-11 | 2020-08-14 | 135450 | Authorized | Authorized | No | Closed | Federal
HSIP7-11-015 | 7 | 5958098 | 11 | Imperial County | Imperial County | SCAG | ICTC | Forrester Road, Evan Hewes Highway, Dogwood Road, Keystone Road, Marina Drive. Imperial County Major Corridor Sign Audit. | Traffic sign audit at five (5) Roadway Corridors in Imperial County. Replacement of approximately one hundred forty three (143) current traffic signs on Forrester Road with high visibility/high reflective signs. | 136500 | 132500 | 2016-11-14 | 0 | 2019-09-13 | 2023-02-21 | 132500 | Authorized | Authorized | No | Closed | Federal
H10-11-011 | 10 | 5207052 | 11 | La Mesa | San Diego County | SANDAG | SANDAG | Various existing guardrail locations throughout the City of La Mesa. | Upgrade existing guardrails and end treatments. | 499300 | 499300 | 2021-09-10 | 0 | 2022-11-30 | 2024-08-22 | 499300 | Authorized | Authorized | No | Closed | State | 0
H10-11-012 | 10 | 5207051 | 11 | La Mesa | San Diego County | SANDAG | SANDAG | Various roadways throughout the City of La Mesa. | Install edgeline striping. | 150000 | 150000 | 2021-09-15 | 0 | 2022-11-30 | 0 | 150000 | Authorized | Authorized | No | CON | State | 0
H8-11-009 | 8 | 5207044 | 11 | La Mesa | San Diego County | SANDAG | SANDAG | Various streets. | Install regulatory and warning signs. | 140307 | 140307 | 0 | 0 | 2017-07-07 | 2019-05-17 | 140307 | No PE | Authorized | No | Closed | Federal | 0
H9-11-008 | 9 | 5207046 | 11 | La Mesa | San Diego County | SANDAG | SANDAG | Various signalized intersections, including La Mesa Blvd/Glen St, Lemon Ave/Bancroft Dr, Spring St/La Mesa Blvd, 70th/University, Lake Murray/Dallas St, Lake Murray/Aztec Dr, Murray Dr/Hospital Ring, Fletcher Pkwy/Trolley Ct/Parks Ave. | Install pedestrian countdown signal heads, ADA-compliant pedestrian pushbuttons, and upgrade traffic signal controllers. | 148920 | 148920 | 0 | 0 | 2021-05-20 | 2023-10-25 | 148920 | No PE | Authorized | No | Closed | Federal | 0
H9-11-009 | 9 | 5207050 | 11 | La Mesa | San Diego County | SANDAG | SANDAG | El Cajon Boulevard from Jessie Avenue to Williams Avenue. | Install a HAWK signal and curb extensions. | 438000 | 438000 | 0 | 0 | 2021-12-06 | 2024-11-13 | 438000 | No PE | Authorized | No | Closed | Federal | 0
H9-11-010 | 9 | 5207048 | 11 | La Mesa | San Diego County | SANDAG | SANDAG | Various locations citywide. | Install Rectangular Rapid Flashing Beacons (RRFBs), high visibility crosswalks, and pedestrian curb ramps. | 520500 | 250000 | 0 | 0 | 2021-02-16 | 2023-12-14 | 250000 | No PE | Authorized | No | Closed | Federal | 0
H9-11-011 | 9 | 5207045 | 11 | La Mesa | San Diego County | SANDAG | SANDAG | Various intersections within the City of La Mesa. | Upgrade regulatory, warnings, and school signs and posts. | 91688 | 91688 | 0 | 0 | 2019-06-12 | 2021-03-04 | 91688 | No PE | Authorized | No | Closed | Federal | 0
HSIP1-11-003 | 1 | 5207028 | 11 | La Mesa | San Diego County | SANDAG | SANDAG | Intersection Of Lake Murray Blvd And Baltimore Dr. | Upgrade Traffic Signals; Upgrade Pedestrian And Bicycle Facilities. | 198380 | 178542.25 | 0 | 0 | 2009-04-10 | 2011-12-14 | 178542.25 | No PE | Authorized | No | Closed | Federal | 0
HSIP3-11-004 | 3 | 5207031 | 11 | La Mesa | San Diego County | SANDAG | SANDAG | University Ave. At Massachusetts Ave. | Modify Traffic Signal With Mast-Arm Mounted Left-Turn Indications; Install And Upgrade Pedestrian Signal Indicators And Actuators; Construct Curb Ramps | 316689.84 | 181350 | 2010-11-08 | 0 | 2012-08-31 | 2015-01-09 | 181350 | Authorized | Authorized | No | Closed | Federal | 0
HSIP4-11-013 | 4 | 5207033 | 11 | La Mesa | San Diego County | SANDAG | SANDAG | University Ave./Harbinson Ave. (Marian St.) | Install protected left-turn phasing and pedestrian countdown heads; upgrade pedestrian facilities | 448916.38 | 211297.15 | 2011-08-25 | 0 | 2014-08-11 | 2017-04-12 | 211297.15 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-11-011 | 5 | 5207037 | 11 | La Mesa | San Diego County | SANDAG | SANDAG | Amaya Dr./Amaya Ct.; Center Dr./Entrance #6; La Mesa Blvd./Glen St. | Modify traffic signals; install protected left-turn phasing; upgrade curb ramps | 811342.37 | 544605.95 | 2013-11-08 | 0 | 2015-08-14 | 2019-11-08 | 544605.95 | Authorized | Authorized | No | Closed | Federal | 0
HSIP6-11-008 | 6 | 5207038 | 11 | La Mesa | San Diego County | SANDAG | SANDAG | On Spring St between Center St and Lemon Ave, Various location on El Cajon Blvd | Construct sidewalk; Upgrade traffic signals (interconnect); Install pedestrian countdown heads | 1830189.57 | 1200149.99 | 2015-06-18 | 0 | 2017-10-19 | 2020-12-28 | 1200149.99 | Authorized | Authorized | No | Closed | Federal
HSIP6-11-009 | 6 | 5207040 | 11 | La Mesa | San Diego County | SANDAG | SANDAG | On Fletcher Parkway between Baltimore Dr and Dallas St, on Baltimore Dr between Fletcher Parkway and City Hall | Upgrade traffic signals (interconnect); install pedestrian countdown signal heads | 609350.33 | 533469.62 | 2015-06-18 | 0 | 2017-09-13 | 2020-02-12 | 533469.62 | Authorized | Authorized | No | Closed | Federal
HSIP7-11-005 | 7 | 5207043 | 11 | La Mesa | San Diego County | SANDAG | SANDAG | Signalized intersections on the following corridors: Amaya Dr, Baltimore Dr, Center Dr, El Cajon Blvd, Grossmont Center Dr, Jackson Dr, La Mesa Blvd, Lake Murray Blvd, Murray Dr, Spring St, and University Ave | Upgrade fiber optic traffic signal interconnect system including installation of: cable, controllers, BBS, monitoring devices, and related communication equipment to improve safety and operations via optimized traffic signal timing and coordination. | 905595.53 | 801483.63 | 2016-07-20 | 0 | 2019-10-24 | 2022-05-25 | 801483.63 | Authorized | Authorized | No | Closed | Federal
H10-11-013 | 10 | 5066061 | 11 | National City | San Diego County | SANDAG | SANDAG | Intersections of 16th St & E Ave. | Install high visibility pedestrian striping, curb extensions, pedestrian refuge islands, ADA curb ramps, pedestrian push button poles, and pedestrian lighting. | 250000 | 243000 | 0 | 0 | 2025-08-14 | 0 | 243000 | No PE | Authorized | No | CON | State | 0
H10-11-014 | 10 | 5066050 | 11 | National City | San Diego County | SANDAG | SANDAG | Signalized Intersections at Harbison Ave/E Plaza Blvd, Harbison Ave/E 8th St, E Plaza Blvd/Highland Ave, Highland Ave/E 8th St, Highland Ave/E 21st St, Highland Ave/E 18th St, National City Blvd/E 8th St and Highland Ave/E 30th St. | Install pedestrian countdown signal heads; modify signal phasing to implement a Leading Pedestrian Interval (LPI); and implement other miscellaneous safety improvements. | 427500 | 427500 | 2022-01-24 | 0 | 2024-07-02 | 0 | 427500 | Authorized | Authorized | No | CON | State | 0
H11-11-005 | 11 | 5066057 | 11 | National City | San Diego County | SANDAG | SANDAG | Signalized Intersections along Highland Avenue from Division Street to 30th Street (excluding 28th Street), along Plaza Boulevard from L Avenue to 8th Street and along National City Boulevard from 4th Street to 24th Street/Miles of Cars Way. | Improve signal hardware with back-plates with retroreflective borders, install an advance stop bar before crosswalk (Bicycle Box), and modify signal phasing to implement a Leading Pedestrian Interval (LPI). | 947700 | 852930 | 2023-08-08 | 0 | 0 | 0 | 92250 | Authorized | Due by 9/30/2026 | No | PE | State | 0
H12-11-007 | 12 | 5066064 | 11 | National City | San Diego County | SANDAG | SANDAG | Intersections of 8th Street & A Avenue, 8th Street & B Avenue, and 8th Street & C Avenue. | Install rectangular rapid flashing beacons (RRFBs) for 6 crosswalks. | 388700 | 349830 | 2026-03-09 | 0 | 0 | 0 | 32850 | Authorized | Due by 3/31/2028 | No | PE | State | 0
H12-11-008 | 12 | 5066065 | 11 | National City | San Diego County | SANDAG | SANDAG | Various corridors, including 16th Street, Palm Avenue, N Avenue, and Harbison Avenue. | Install edgeline striping. | 386400 | 347760 | 2026-03-09 | 0 | 0 | 0 | 62100 | Authorized | Due by 3/31/2028 | No | PE | State | 0
H12-11-009 | 12 | 5066066 | 11 | National City | San Diego County | SANDAG | SANDAG | 4th Street corridor at the intersections of B Avenue, F Avenue, Laurel Avenue, V Avenue, and Hill Drive. | Install low-cost compact/mini roundabouts/traffic circles along the 4th Street corridor. | 838200 | 754380 | 2026-03-09 | 0 | 0 | 0 | 134100 | Authorized | Due by 3/31/2028 | No | PE | State | 0
H8-11-010 | 8 | 5066043 | 11 | National City | San Diego County | SANDAG | SANDAG | Sweetwater Road from Plaza Bonita Road/Stockman to Plaza Bonita Centerway. | Install pinned raised median and street lighting. | 1326447.65 | 680940 | 0 | 0 | 2020-01-27 | 2022-11-29 | 680940 | No PE | Authorized | No | Closed | Federal | 0
H8-11-011 | 8 | 5066044 | 11 | National City | San Diego County | SANDAG | SANDAG | Signalized intersections on corridors: 8th St, 18th St, 30th St/Sweetwater Rd, Bay Marina Dr/Mile of Cars Wy, Division St, Euclid Ave, National City Blvd, Plaza Blvd/Paradise Valley Rd, Tidelands Ave;Plaza Bonita Ctrwy &Valley Rd, 16th St & Palm Ave. | Install pedestrian countdown signal heads and ADA-compliant pedestrian push buttons. | 398787.4 | 398787.4 | 0 | 0 | 2020-01-27 | 2022-12-28 | 398787.4 | No PE | Authorized | No | Closed | Federal | 0
H8-11-012 | 8 | 5066042 | 11 | National City | San Diego County | SANDAG | SANDAG | Signalized intersections of Palm Avenue and E. 4th Street and Euclid Ave at 4th St. | Replace existing permissive left-turn phases and signal heads with protected left-turn phases and signal heads on existing and/or new traffic signal poles and mast arms. | 128934.2 | 128934.2 | 0 | 0 | 2020-01-27 | 2023-01-09 | 128934.2 | No PE | Authorized | No | Closed | Federal | 0
H8-11-013 | 8 | 5066045 | 11 | National City | San Diego County | SANDAG | SANDAG | Thirty-two (32) signalized intersections - Tidelands Ave/19th St, Palm Ave/16th St, and on the following corridors: 8th St, 18th St, 30th St/Sweetwater Rd, Bay Marina Dr/Mile of Cars Wy/24th St, Division St, Euclid Ave, Plaza Blvd/Paradise Valley Rd. | Install LED luminaire safety lighting. | 93947.53 | 93947.53 | 0 | 0 | 2020-01-27 | 2023-01-09 | 93947.53 | No PE | Authorized | No | Closed | Federal | 0
H9-11-012 | 9 | 5066041 | 11 | National City | San Diego County | SANDAG | SANDAG | Signalized intersections at the following corridors: 8th Street, 18th Street, D Avenue, Euclid Avenue, Plaza Boulevard, Palm Avenue, Sweetwater Road, and Roosevelt Avenue. | Upgrade existing permissive left-turn phases and signal heads with protected left-turn phases on existing and/or new traffic signal poles and mast arms. Add left turn lane striping at project signalized intersections with no left turn pocket lanes. | 1545100 | 1390590 | 2019-10-23 | 0 | 2024-03-26 | 0 | 1390590 | Authorized | Authorized | No | CON | Federal | 0
HSIP2-11-002 | 2 | 5066016 | 11 | National City | San Diego County | SANDAG | SANDAG | E. 8Th Street Between K Ave. And Palm Ave. And At The Intersection Of E 8Th St. And L Ave. | Construct Medians, Turn Lanes, Roadway Widening, Traffic Signals And Beacons, And Sidewalks. | 1245809.68 | 900000 | 0 | 0 | 2012-09-12 | 2016-12-27 | 900000 | No PE | Authorized | No | Closed | Federal | 0
HSIP4-11-002 | 4 | 5066021 | 11 | National City | San Diego County | SANDAG | SANDAG | Highland Ave. between Division St. and E 8th St. | Construct bulb-outs, curb ramps, left-turn pockets, and raised medians; reduce travel lanes from four to two; install signs, striping, and pavement markings | 1341109.29 | 899999.99 | 0 | 0 | 2014-07-31 | 2018-05-07 | 899999.99 | No PE | Authorized | No | Closed | Federal | 0
HSIP6-11-010 | 6 | 5066027 | 11 | National City | San Diego County | SANDAG | SANDAG | Highland Ave/E 4th St, Highland Ave/Shopping Center Driveway, Highland Ave/E 16th St, Highland Ave/E 18th St, Highland Ave/E 21st St, Highland Ave/E 24th St | Upgrade traffic signals; Install protected left-turn phasing | 852979.47 | 729300 | 0 | 0 | 2017-09-13 | 2021-11-20 | 729300 | No PE | Authorized | No | Closed | Federal
HSIP6-11-011 | 6 | 5066028 | 11 | National City | San Diego County | SANDAG | SANDAG | Highland Ave/28th St | Install traffic signals | 239339.92 | 154000 | 0 | 0 | 2017-08-16 | 2020-01-10 | 154000 | No PE | Authorized | No | Closed | Federal
HSIP6-11-012 | 6 | 5066029 | 11 | National City | San Diego County | SANDAG | SANDAG | 9 intersections throughout National City | Install pedestrian crossings and related improvements | 927217.63 | 810650 | 0 | 0 | 2017-09-13 | 2021-11-23 | 810650 | No PE | Authorized | No | Closed | Federal
HSIP6-11-013 | 6 | 5066030 | 11 | National City | San Diego County | SANDAG | SANDAG | National City Blvd/30th St, National City Blvd/E Plaza Blvd, Sweetwater Rd/Euclid Ave | Upgrade traffic signals (interconnect) | 615516.46 | 501400 | 0 | 0 | 2017-08-16 | 2020-04-27 | 501400 | No PE | Authorized | No | Closed | Federal
HSIP6-11-014 | 6 | 5066031 | 11 | National City | San Diego County | SANDAG | SANDAG | On East 18th St between D Ave and Palm Ave | Install bicycle lanes and bike boxes | 253362.9 | 251231 | 0 | 0 | 2016-09-20 | 2019-04-19 | 251231 | No PE | Authorized | No | Closed | Federal
HSIP7-11-006 | 7 | 5066039 | 11 | National City | San Diego County | SANDAG | SANDAG | Signalized intersections along the following corridors within City limits: 8th Street, 18th Street, Division Road, Euclid Avenue, Mile of Cars Way, Palm Avenue, and Plaza Boulevard. | Upgrade fiber optic traffic signal communication system including installation of: conduit, cable, radios, controllers, and related communication equipment to improve safety and operations via optimized traffic signal timing and coordination. | 430256.71 | 430256.71 | 0 | 0 | 2019-09-13 | 2022-12-12 | 430256.71 | No PE | Authorized | No | Closed | Federal
HSIP7-11-007 | 7 | 5066034 | 11 | National City | San Diego County | SANDAG | SANDAG | Signalized Intersections on the following corridors: D Ave, Euclid Ave, Highland Ave, National City Blvd, Palm Ave, Plaza Blvd, Sweetwater Rd Midblock crosswalk locations citywide | Install LED luminaire safety lighting at signalized intersections and pedestrian level LED street lighting at midblock crosswalks with additional pedestrian safety enhancements at select midblock locations | 1230799.72 | 625230 | 0 | 0 | 2017-06-26 | 2020-01-10 | 625230 | No PE | Authorized | No | Closed | Federal
HSIP7-11-008 | 7 | 5066040 | 11 | National City | San Diego County | SANDAG | SANDAG | At the intersections of National City Blvd & 30th St, Plaza Blvd & N Ave, Plaza Blvd & Harbison Ave, Euclid Ave & 16th St, Euclid Ave & 18th St, 30th St & L Ave, Sweetwater Rd & Prospect St, Sweetwater Rd & Ring Rd. | Installing pedestrian crossings at signalized intersections and necessary related access and equipment improvements. | 234669.2 | 234669.2 | 0 | 0 | 2019-09-13 | 2022-11-16 | 234669.2 | No PE | Authorized | No | Closed | Federal
H9-11-013 | 9 | 5079032 | 11 | Oceanside | San Diego County | SANDAG | SANDAG | Signalized intersections along the corridors of Coast Hwy 101, El Camino Real, College Blvd, Oceanside Blvd Mission Ave, Douglas Dr, Vandegrift Blvd, Mesa Dr, North Santa Fe, Cannon Rd, Rancho Del Oro Rd, and Lake Blvd. | Install pedestrian countdown signal heads, ADA-compliant pedestrian pushbuttons, and upgrade traffic signal controllers. | 2271727.31 | 2271727.31 | 2019-11-27 | 0 | 2023-04-06 | 2025-10-22 | 2271727.31 | Authorized | Authorized | No | Closed | Federal | 2
HSIP7-11-009 | 7 | 5079031 | 11 | Oceanside | San Diego County | SANDAG | SANDAG | On Douglas Drive between approximately 300 feet south of Westport Drive and 250 feet north of Via Cibola. | Install a raised median from 300 ft. south of Westport Dr to 250 ft. north of Festival Dr, and raised median islands on the approaches of two non-signalized intersections along Douglas Dr at Corte Bocina and at Via Cibola. | 846070.57 | 698845.27 | 2016-09-20 | 0 | 2020-09-10 | 2022-11-22 | 698845.27 | Authorized | Authorized | No | Closed | Federal
H10-11-015 | 10 | 5428015 | 11 | Poway | San Diego County | SANDAG | SANDAG | Various locations along Poway Road between Oak Knoll Road and Garden Road. | Provide advanced dilemma zone detection, implement leading pedestrian interval (LPI), create directional median openings, and install/upgrade intersection regulatory signs. | 729692 | 656723 | 2022-03-14 | 0 | 2024-01-04 | 2025-08-25 | 656723 | Authorized | Authorized | No | Closed | State | 0
H10-11-021 | 10 | 5004213 | 11 | San Diego | San Diego County | SANDAG | SANDAG | Torrey Pines Rd between Prospect Pl & Coast Walk | This project will install approximately 420 FT of California ST-75B bridge rail, sidewalk, curb & gutter and AC pavement, and relocate water facilities. | 1857988 | 1000000 | 2021-12-23 | 0 | 2026-01-15 | 0 | 1000000 | Authorized | Authorized | No | CON | State | 0
H11-11-006 | 11 | 5004221 | 11 | San Diego | San Diego County | SANDAG | SANDAG | 31 Intersections throughout the City of San Diego. | Install activated blank-out signs for leading pedestrian intervals, pedestrian countdown timers, and high visibility crosswalks. | 997700 | 897930 | 2024-01-04 | 0 | 2025-11-18 | 0 | 897930 | Authorized | Authorized | No | CON | State | 0
H11-11-007 | 11 | 5004219 | 11 | San Diego | San Diego County | SANDAG | SANDAG | 93 signalized intersections in the City of San Diego. | Install traffic signal hardware and communications interconnect system upgrades to improve traffic signal timing and optimize operations. | 2005000 | 1002500 | 0 | 0 | 2023-10-18 | 0 | 1002500 | No PE | Authorized | No | CON | State | 0
H11-11-008 | 11 | 5004220 | 11 | San Diego | San Diego County | SANDAG | SANDAG | 101 signalized intersections in the City of San Diego. | Install traffic signal hardware and communication interconnect system upgrades to improve traffic signal timing and optimize operations. | 2036500 | 1018250 | 0 | 0 | 2024-01-08 | 0 | 1018250 | No PE | Authorized | No | CON | State | 0
H12-11-010 | 12 | 5004228 | 11 | San Diego | San Diego County | SANDAG | SANDAG | Hotel Circle South & Taylor St/Hotel Circle North. | Install a roundabout. | 218000 | 196200 | 2025-11-26 | 0 | 0 | 0 | 35100 | Authorized | Due by 3/31/2028 | No | PE | State | 0
H8-11-014 | 8 | 5004207 | 11 | San Diego | San Diego County | SANDAG | SANDAG | University Avenue between Fairmount Avenue and Euclid Avenue. | Implement Complete Street measures including raised medians with pedestrian refuges, roundabouts, and wider sidewalks. | 6045800 | 5441220 | 2017-06-22 | 0 | 2020-11-02 | 0 | 5441220 | Authorized | Authorized | No | CON | Federal | 0
H9-11-014 | 9 | 5004211 | 11 | San Diego | San Diego County | SANDAG | SANDAG | Sixty-six (66) intersections throughout the City of San Diego. | Install activated blank out signs with leading pedestrian intervals, pedestrian countdown timers, and high visibility crosswalks. | 239394.72 | 239394.71 | 0 | 0 | 2020-06-26 | 2024-10-21 | 239394.71 | No PE | Authorized | No | Closed | Federal | 0
H9-11-015 | 9 | 5004210 | 11 | San Diego | San Diego County | SANDAG | SANDAG | Two hundred fifteen (215) intersections throughout the City of San Diego. | Install pedestrian countdown signal heads. | 247197.81 | 247197.81 | 0 | 0 | 2020-04-13 | 2023-04-26 | 247197.81 | No PE | Authorized | No | Closed | Federal | 0
H9-11-016 | 9 | 5004209 | 11 | San Diego | San Diego County | SANDAG | SANDAG | Various locations, including Skyline Drive & S.Woodman Street, West Mission Bay Drive & Ingraham Street On-ramp, North Torrey Pines Road N/O Callan Road, Via de la Melodia & Smythe Avenue, Sabre Springs Parkway S/O Evening Creek Drive South. | This project involves extending existing guardrails, installing end terminals or crash cushions and widening sidewalks to provide adequate access. | 277268.57 | 277268.57 | 2019-09-13 | 0 | 2023-02-02 | 2025-01-24 | 277268.57 | Authorized | Authorized | No | Closed | Federal | 0
HSIP3-11-001 | 3 | 5004186 | 11 | San Diego | San Diego County | SANDAG | SANDAG | Florida Dr. Between Pershing Dr. And Bob Wilson Dr. | Construct Type 60 Concrete Median Barriers On Both Sides Of The New Center Median; Install Safety Lighting And Warning Signs; Restripe Roadway For Wider Bike Lanes | 937065.03 | 577349.5 | 2010-11-23 | 0 | 2013-08-09 | 2019-06-19 | 577349.5 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-11-012 | 5 | 5004194 | 11 | San Diego | San Diego County | SANDAG | SANDAG | Ulric St. between David St. and Fashion Hills Blvd. | Install median barrier and striping; construct sidewalks | 1070974.93 | 798128.25 | 2013-05-17 | 0 | 2016-06-22 | 2021-10-15 | 798128.25 | Authorized | Authorized | No | Closed | Federal | 0
H10-11-016 | 10 | 5957141 | 11 | San Diego County | San Diego County | SANDAG | SANDAG | 4 intersections in unincorporated San Diego County: Jamacha Rd/Elkelton Blvd; S. Mission Rd/Alvarado St; S. Mission Rd/Clemmens Ln; and Sweetwater Rd/Troy St. | Install Pedestrian Countdown Signal Heads, pushbuttons, curb ramps, and continental crosswalks. | 675700 | 608130 | 2021-10-14 | 0 | 2024-06-26 | 0 | 567630 | Authorized | Authorized | No | CON | State | 0
H10-11-017 | 10 | 5957143 | 11 | San Diego County | San Diego County | SANDAG | SANDAG | Various locations along Sunrise Highway (MP 14.5, MP 15.0, MP 15.5, and MP 17.0) in Unincorporated San Diego County. | Upgrade metal beam guardrail and end-treatment. | 1577700 | 1577700 | 2021-10-12 | 0 | 0 | 0 | 328900 | Authorized | Past due (due 10/10/2025) | Yes (CON) | PE | Mix | 1
H10-11-019 | 10 | 5957145 | 11 | San Diego County | San Diego County | SANDAG | SANDAG | 17 intersections in unincorporated San Diego County. | Install pedestrian countdown signal heads. | 249600 | 249600 | 2021-12-14 | 0 | 2024-07-09 | 0 | 249600 | Authorized | Authorized | No | CON | State | 0
H11-11-009 | 11 | 5957150 | 11 | San Diego County | San Diego County | SANDAG | SANDAG | Various Locations throughout San Diego County. | Metal Beam Guardrail and End-Treatment Upgrades. | 963600 | 751608 | 2023-12-01 | 0 | 0 | 0 | 116142 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE | Federal | 1
H12-11-011 | 12 | 5957153 | 11 | San Diego County | San Diego County | SANDAG | SANDAG | The intersection of W Aviation Road and S Main Avenue in the community of Fallbrook. | Convert intersection to all-way stop control; provide pedestrian connection and pedestrian ramps; and provide/enhance advanced warning signage and markings. | 307200 | 276480 | 2025-12-19 | 0 | 0 | 0 | 45000 | Authorized | Due by 3/31/2028 | No | PE | State | 0
H12-11-012 | 12 | 5957155 | 11 | San Diego County | San Diego County | SANDAG | SANDAG | The intersection of Jamacha Boulevard and Grand Avenue in the community of Spring Valley. | Provide protected left turn phasing and provide pedestrian enhancements such as marked crosswalks, curb extensions, dual pedestrian ramps, and leading pedestrian interval (LPI). | 1338100 | 1204290 | 2026-01-15 | 0 | 0 | 0 | 180000 | Authorized | Due by 3/31/2028 | No | PE | Federal | 2
H12-11-013 | 12 | 5957154 | 11 | San Diego County | San Diego County | SANDAG | SANDAG | Bonita Road from Central Avenue to the County Limits near Villas Drive. | Install Class II buffered bike lanes to complete the missing segment, green paint at conflict zones and through intersections, and 2 dynamic/variable speed warning signs. | 599200 | 539280 | 2025-12-19 | 0 | 0 | 0 | 96300 | Authorized | Due by 3/31/2028 | No | PE | State | 0
H8-11-015 | 8 | 5957128 | 11 | San Diego County | San Diego County | SANDAG | SANDAG | Jamacha Boulevard between Sweetwater Road and Gillespie Drive, adjacent the Spring Valley Shopping Center, in the unincorporated community of Spring Valley. | Construct raised median and install traffic signal with striping, raised pavement markers, signage, and continental crosswalk striping. | 892218.79 | 752063.4 | 2017-07-17 | 2019-03-22 | 2020-09-11 | 2025-05-20 | 752063.4 | Authorized | Authorized | No | Closed | Federal | 0
H8-11-016 | 8 | 5957129 | 11 | San Diego County | San Diego County | SANDAG | SANDAG | Woodside Ave from Marilla Dr to Chestnut St in the unincorporated community of Lakeside. | Construct sidewalks, bike lanes, and advanced dilemma zone detection with signal coordination. | 7724200 | 6951780 | 2017-07-17 | 2022-02-07 | 2024-09-23 | 0 | 1315620 | Authorized | Authorized | No | CON | Federal | 2
H9-11-017 | 9 | 5957142 | 11 | San Diego County | San Diego County | SANDAG | SANDAG | San Miguel Road at Sunnyside Elementary School in the unincorporated community of Bonita in San Diego County. | Install Pedestrian Hybrid Beacon (HAWK). | 464222.62 | 361500 | 0 | 0 | 2022-05-03 | 2025-04-30 | 361500 | No PE | Authorized | No | Closed | Federal | 0
H9-11-018 | 9 | 5957137 | 11 | San Diego County | San Diego County | SANDAG | SANDAG | Five (5) guardrails, located at Del Dios Hwy (at Date Lane) and Japatul Rd (at MP 14.5 and east of Tavern Rd, in unincorporated San Diego County. | Upgrade metal beam guardrail. | 426409.45 | 412020 | 2019-10-22 | 0 | 2021-11-16 | 2023-10-23 | 412020 | Authorized | Authorized | No | Closed | Federal | 0
HRRR1-11-065 | 1 | 5957079 | 11 | San Diego County | San Diego County | SANDAG | SANDAG | South Grade Road - From State Route 76 to Canfield Drive / East Grade Road on Mount Palomar | Rumble Strip | 133710 | 57842.66 | 2008-06-04 | 0 | 2009-05-15 | 2011-12-12 | 57842.66 | Authorized | Authorized | No | Closed | Federal | 0
HSIP3-11-008 | 3 | 5957097 | 11 | San Diego County | San Diego County | SANDAG | SANDAG | Jamacha Rd. Between Sweetwater Rd. And Grand Ave. | Upgrade Traffic Signals With Interconnect Cable | 254538.13 | 171530.81 | 2010-07-24 | 0 | 2011-03-03 | 2014-03-26 | 171530.81 | Authorized | Authorized | No | Closed | Federal | 0
HSIP3-11-011 | 3 | 5957098 | 11 | San Diego County | San Diego County | SANDAG | SANDAG | Intersection Of Jamacha Rd. And Helix St. | Install Traffic Signal | 283061.87 | 239400.1 | 2010-07-24 | 0 | 2011-03-03 | 2014-03-26 | 239400.1 | Authorized | Authorized | No | Closed | Federal | 0
HSIP4-11-014 | 4 | 5957107 | 11 | San Diego County | San Diego County | SANDAG | SANDAG | Mission Rd./Aviation Rd.; Mission Rd. between Ammunition Rd. and Fallbrook St. | Install traffic signals with interconnect communications cable | 1034123.55 | 620984 | 2011-08-31 | 0 | 2013-02-01 | 2016-02-12 | 620984 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-11-013 | 5 | 5957115 | 11 | San Diego County | San Diego County | SANDAG | SANDAG | 10th St. (San Vicente Rd.) between "D" St. and Warnock Dr. | Install traffic signal; upgrade traffic signals (interconnect) | 909418.98 | 770976.77 | 2013-04-09 | 0 | 2014-05-16 | 2017-02-14 | 770976.77 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-11-014 | 5 | 5957116 | 11 | San Diego County | San Diego County | SANDAG | SANDAG | Mission Rd. between SR 76 and SR 15; Olive Hill Rd. between Camino Del Rey and Mission Rd.; El Nopal between Aquilla Dr. and Riverford Rd.; Reche Rd. between Stage Coach Ln. and Old Hwy. 395; Buckman Springs Rd. between SR 94 and Old Hwy 80 | Install center-line rumble strips | 301876.09 | 248663.47 | 2013-04-09 | 0 | 2014-05-16 | 2016-06-21 | 248663.47 | Authorized | Authorized | No | Closed | Federal | 0
HSIP6-11-015 | 6 | 5957119 | 11 | San Diego County | San Diego County | SANDAG | SANDAG | On Winter Gardens Blvd between Woodside Ave and Pepper Dr | Install traffic signal; Install signal interconnect | 962682.58 | 947272.58 | 2014-05-13 | 2015-08-06 | 2016-05-13 | 2021-10-15 | 947272.58 | Authorized | Authorized | No | Closed | Federal
HSIP7-11-010 | 7 | 5957126 | 11 | San Diego County | San Diego County | SANDAG | SANDAG | Wintergardens Blvd. from Woodside Ave to Lemoncrest Dr in the unincorporated community of Lakeside in San Diego County. | Construct sidewalk, curb, gutter, curb ramps, driveways, bike lanes, stripes, pavement markings and a traffic signal modification | 697311.76 | 505752.86 | 2016-12-15 | 2018-07-16 | 2019-10-22 | 2024-02-01 | 505752.86 | Authorized | Authorized | No | Closed | Federal
H10-11-020 | 10 | 5381045 | 11 | San Marcos | San Diego County | SANDAG | SANDAG | 120 intersections throughout the City of San Marcos. | Upgrade existing traffic signal backplates to retroreflective backplates. | 724000 | 724000 | 2021-09-22 | 0 | 2024-12-17 | 0 | 724000 | Authorized | Authorized | No | CON | State | 0
HSIP1-11-004 | 1 | 5381022 | 11 | San Marcos | San Diego County | SANDAG | SANDAG | Alvin Dunn, Paloma, Knob Hill, Twin Oaks, San Marcos, And San Elijo Elementary Schools; San Marcos, Woodland Park, And San Elijo Middle Schools; Mission Hills And San Marcos High Schools. | Install Solar-Powered Dual-Flashing Beacon Lights And/Or Speed Radar Detectors Sign Assemblies. | 247412 | 222670.8 | 0 | 0 | 2008-04-16 | 2010-05-11 | 222670.8 | No PE | Authorized | No | Closed | Federal | 0
HSIP2-11-003 | 2 | 5381027 | 11 | San Marcos | San Diego County | SANDAG | SANDAG | Mulberry Dr. And Rose Ranch Rd.; Various Intersections Along San Marcos Blvd. And Along Rancho Santa Fe Rd.; Mission Rd. And Knoll Rd.; Mission Rd. From Pico Ave. To Bosstick Blvd. | Install Traffic Signal; Install Count-Down Pedestrian Heads; Modify Traffic Signal And Reconfigure Intersection; Install Signal Interconnect System, Fiber Optic Cable, Remote Television Cameras, Integrate With Traffic Management Center | 1181041.31 | 963720.16 | 2009-02-18 | 0 | 2010-10-14 | 2018-06-13 | 963720.16 | Authorized | Authorized | No | Closed | Federal | 0
HSIP3-11-005 | 3 | 5381030 | 11 | San Marcos | San Diego County | SANDAG | SANDAG | Citywide | Replace/Upgrade Regulatory Traffic Signs | 209941 | 187864.25 | 2010-10-14 | 0 | 2013-03-26 | 2018-06-13 | 187864.25 | Authorized | Authorized | No | Closed | Federal | 0
HSIP3-11-006 | 3 | 5381031 | 11 | San Marcos | San Diego County | SANDAG | SANDAG | Coronado Hills Dr. Between Via Del Campo And Washingtonia Dr. | Install/Upgrade Guardrail | 113908.14 | 102517.27 | 2010-10-14 | 0 | 2012-07-26 | 2015-01-23 | 102517.27 | Authorized | Authorized | No | Closed | Federal | 0
HSIP4-11-006 | 4 | 5381034 | 11 | San Marcos | San Diego County | SANDAG | SANDAG | Mission Rd. between San Marcos Blvd. and Nordahl Rd.; Woodland Pkwy. between Mission Rd. and Borden (El Norte Pkwy.); Nordahl Rd. between Mission Rd. and Montiel Rd. | Upgrade traffic signals; install interconnect communications cable and CCTV cameras | 631043.42 | 539722.66 | 2011-12-02 | 0 | 2014-07-31 | 2020-10-29 | 539722.66 | Authorized | Authorized | No | Closed | Federal | 0
HSIP4-11-008 | 4 | 5381035 | 11 | San Marcos | San Diego County | SANDAG | SANDAG | Various locations throughout the city | Upgrade regulatory and warning signs | 225722.5 | 200767.48 | 2011-12-02 | 0 | 2014-07-31 | 2018-06-28 | 200767.48 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-11-017 | 5 | 5381041 | 11 | San Marcos | San Diego County | SANDAG | SANDAG | Various locations throughout the city | Install safety lighting | 385014.64 | 340266.65 | 2013-09-18 | 0 | 2017-06-20 | 2019-12-12 | 340266.65 | Authorized | Authorized | No | Closed | Federal | 0
H9-11-019 | 9 | 7504001 | 11 | San Pasqual Band of Mission Indians | San Diego County | SANDAG | SANDAG | Various locations throughout the San Pasqual Band of Mission Indians Reservation, within the County of San Diego. | Upgrade existing guardrail from wood posts to steel posts. | 620000 | 620000 | 0 | 0 | 0 | 0 | 0 | Not Tracked | Not Tracked | No | Not Started | Federal | 0
H9-11-020 | 9 | 5429032 | 11 | Santee | San Diego County | SANDAG | SANDAG | All sixty-one (61) traffic signals citywide. | Install reflective tapes on traffic signal heads and paint faded signal back plates to improve visibility of traffic signals. | 234552.65 | 234552.65 | 2019-10-22 | 0 | 2020-09-11 | 2022-04-11 | 234552.65 | Authorized | Authorized | No | Closed | Federal | 0
HSIP1-11-006 | 1 | 5429011 | 11 | Santee | San Diego County | SANDAG | SANDAG | Prospect Ave. Undercrossing At Sr 125. | Install Roadway Safety Lighting. | 59728 | 47700 | 2008-04-11 | 0 | 2009-03-31 | 2010-12-28 | 47700 | Authorized | Authorized | No | Closed | Federal | 0
HSIP2-11-008 | 2 | 5429017 | 11 | Santee | San Diego County | SANDAG | SANDAG | Cuyamaca St. Between Prosapect Ave. And Mission Gorge Rd. And To Trolley Station . | Upgrade Trolley Signal Equipment. | 24606 | 22145.4 | 0 | 0 | 2009-09-03 | 2012-01-25 | 22145.4 | No PE | Authorized | No | Closed | Federal | 0
HSIP3-11-007 | 3 | 5429018 | 11 | Santee | San Diego County | SANDAG | SANDAG | Mission Gorge Rd. Between Magnolia Ave. And First Ave. | Install 440' Of Raised Median | 215753.01 | 166697.35 | 2010-11-08 | 0 | 2012-12-07 | 2015-12-18 | 166697.35 | Authorized | Authorized | No | Closed | Federal | 0
HSIP4-11-001 | 4 | 5429019 | 11 | Santee | San Diego County | SANDAG | SANDAG | Magnolia Ave. between the San Diego River and Prospect Ave.; Mast Blvd. between Carlton Hills Blvd. and Cuyamaca St. | Install speed feedback signs | 90716.49 | 81644.65 | 2011-08-22 | 0 | 2012-06-12 | 2014-02-21 | 81644.65 | Authorized | Authorized | No | Closed | Federal | 0
HSIP4-11-016 | 4 | 5429020 | 11 | Santee | San Diego County | SANDAG | SANDAG | Magnolia Ave./Palm Glen Dr. | Construct raised medians | 113211.1 | 83200 | 2011-08-16 | 0 | 2014-08-18 | 2016-01-13 | 83200 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-11-018 | 5 | 5429025 | 11 | Santee | San Diego County | SANDAG | SANDAG | Various locations throughout the city | Upgrade signs | 256488.87 | 230788.98 | 2013-10-30 | 0 | 2015-12-21 | 2020-03-04 | 230788.98 | Authorized | Authorized | No | Closed | Federal | 0
HSIP6-11-018 | 6 | 5429026 | 11 | Santee | San Diego County | SANDAG | SANDAG | On Mission Gorge Rd between Riverview Parkway and 1st Ave | Install raised median | 1585622.69 | 711700 | 2015-12-21 | 0 | 2017-09-13 | 2019-09-13 | 711700 | Authorized | Authorized | No | Closed | Federal
HSIP7-11-011 | 7 | 5429030 | 11 | Santee | San Diego County | SANDAG | SANDAG | Mission Gorge Road from SR 52 westbound on-ramp to Carlton Hills Boulevard | Install streetlights | 381469.88 | 381463.95 | 2017-02-09 | 0 | 2019-11-21 | 2022-11-03 | 381463.95 | Authorized | Authorized | No | Closed | Federal
HSIP7-11-012 | 7 | 5429031 | 11 | Santee | San Diego County | SANDAG | SANDAG | Around Santana High School on Mast Boulevard from Park Center Drive to Grand Teton Way, Magnolia Avenue from Mast Boulevard to 2nd Street, 2nd Street from Magnolia Avenue to Cleary Street | Install streetlights | 518032.42 | 518032.42 | 2017-02-09 | 0 | 2019-11-21 | 2022-03-21 | 518032.42 | Authorized | Authorized | No | Closed | Federal
H9-11-021 | 9 | 0 | 11 | Viejas Tribal Government | San Diego County | SANDAG | SANDAG | Entire length of Browns Road, Viejas Indian Reservation, San Diego County. | Install new signs, new dynamic/variable speed warning sign, new edge-lines, new centerlines and centerline and departure line rumble strips. | 73900 | 73900 | 0 | 0 | 0 | 0 | 0 | Not Tracked | Not Tracked | No | Not Started | Federal | 0
H12-11-014 | 12 | 5382040 | 11 | Vista | San Diego County | SANDAG | SANDAG | E. Vista Way from Williamston Street to Taylor Street. | Install a raised median with directional median openings, pedestrian fencing at key locations, new or upgraded signs with fluorescent sheeting, retro-reflective backplates at existing traffic signals. | 2893400 | 2604060 | 2025-09-17 | 0 | 0 | 0 | 315000 | Authorized | Due by 3/31/2028 | No | PE | Federal | 0
H8-11-017 | 8 | 5382037 | 11 | Vista | San Diego County | SANDAG | SANDAG | Signalized intersections on the following corridors: North Melrose Drive, Santa Fe Avenue, Civic Center Drive, Vista Way/Vista Village Drive, and Bobier Drive/Foothill Drive. | Install traffic signal interconnect system including: conduit, cable, monitoring devices, controllers, and related communication equipment. | 1508144.55 | 747192.18 | 2017-10-19 | 0 | 2020-03-05 | 2022-11-03 | 747192.18 | Authorized | Authorized | No | Closed | Federal | 0
HSIP2-11-006 | 2 | 5382029 | 11 | Vista | San Diego County | SANDAG | SANDAG | Eastbound Offramp From Sr78 Onto Sycamore Ave. | Construct Right-Turn Lane; Upgrade Traffic Signal; Construct Curb, Gutter, Sidewalk And Retaining Wall; Install Signs, Stripes And Safety Barriers | 1580881.69 | 1230668.7 | 2009-04-17 | 0 | 2012-09-17 | 2018-07-10 | 1230668.7 | Authorized | Authorized | No | Closed | Federal | 0
HSIP4-11-005 | 4 | 5382032 | 11 | Vista | San Diego County | SANDAG | SANDAG | E Vista Way/Taylor St. | Install traffic signals with interconnect, bike lanes, signs, striping, and pavement markings; construct curb, gutter, and sidewalks | 942735.01 | 848461.28 | 2011-12-02 | 0 | 2014-06-10 | 2016-11-01 | 848461.28 | Authorized | Authorized | No | Closed | Federal | 0
HSIP6-11-019 | 6 | 5382033 | 11 | Vista | San Diego County | SANDAG | SANDAG | On E Vista Way between Fire Station 6 and Williamston St | Install raised median; modify striping | 812103.19 | 476899.99 | 2014-07-11 | 0 | 2017-08-01 | 2019-12-12 | 476899.99 | Authorized | Authorized | No | Closed | Federal
HSIP6-11-020 | 6 | 5382034 | 11 | Vista | San Diego County | SANDAG | SANDAG | Varrious locations throughout Vista | Upgrade traffic signals (interconnect) | 1221457.87 | 866860 | 2014-07-11 | 0 | 2017-09-18 | 2020-06-16 | 866860 | Authorized | Authorized | No | Closed | Federal
HRRR2-11-064 | 2 | 5278008 | 11 | Westmorland | Imperial County | SCAG | ICTC | South Center St. from SR 86 to Baughman Rd. | Construct median island; install traffic calming devices; install in-pavement crosswalk lights and flashing school crossing signs | 1000773.73 | 899487.71 | 2009-07-08 | 0 | 2012-08-08 | 2018-05-07 | 899487.71 | Authorized | Authorized | No | Closed | Federal | 0
H10-12-001 | 10 | 5055200 | 12 | Anaheim | Orange County | SCAG | OCTA | 3 Signalized Intersections in the City of Anaheim: Walnut Street at Ball Road; Anaheim Boulevard at Santa Ana Street; and Acacia Street/Anna Drive at La Palma Avenue. | Install protected/protected-permissive left-turn phasing. | 1351068 | 802100 | 0 | 0 | 2023-07-26 | 0 | 702100 | No PE | Authorized | No | CON | State | 0
H10-12-002 | 10 | 5055196 | 12 | Anaheim | Orange County | SCAG | OCTA | 4 Signalized Intersections in the City of Anaheim: Western Avenue at Ball Road; Western Avenue at Orange Avenue; Dale Avenue at Orange Avenue; and Manchester Avenue at Broadway. | Install protected left-turn phasing. | 2521000 | 1316100 | 2021-08-09 | 0 | 2025-01-09 | 0 | 1216100 | Authorized | Authorized | No | CON | State | 0
H11-12-001 | 11 | 5055207 | 12 | Anaheim | Orange County | SCAG | OCTA | Twelve (12) uncontrolled crosswalks with high pedestrian volumes at various locations adjacent to schools, parks, and trails throughout the city. | Install solar-powered rectangular rapid flashing beacons (RRFBs) to improve pedestrian safety. | 249600 | 224640 | 0 | 0 | 2026-03-18 | 0 | 224640 | No PE | Authorized | No | CON | State | 0
H11-12-002 | 11 | 5055201 | 12 | Anaheim | Orange County | SCAG | OCTA | Ten (10) local roadway segments to implement traffic calming measures through edgeline striping at various locations within City limits. | Install edgelines on ten (10) local roadway segments as a safety countermeasure for traffic calming and mitigating vehicular crashes. | 88100 | 79290 | 2023-07-31 | 0 | 2025-11-25 | 0 | 79290 | Authorized | Authorized | No | CON | State | 0
H12-12-001 | 12 | 5055206 | 12 | Anaheim | Orange County | SCAG | OCTA | Brookhurst Street from Sequoia Avenue to Ball Road. | Install raised medians. | 5579000 | 5021100 | 2025-11-25 | 0 | 0 | 0 | 604800 | Authorized | Due by 3/31/2028 | No | PE | Federal | 0
H8-12-001 | 8 | 5055187 | 12 | Anaheim | Orange County | SCAG | OCTA | Euclid Street between Glenoaks Avenue and Crescent Avenue. | Construct new median island; and complete signal modifications at intersection of Euclid St. and Glenoaks Ave (new mast arms with left turn phasing, Emergency Vehicle Preemption systems, intersection lighting, new hardware). | 1242900 | 1118610 | 2017-07-18 | 2019-10-22 | 2021-12-17 | 0 | 1118610 | Authorized | Authorized | No | CON | Federal | 0
H8-12-002 | 8 | 5055191 | 12 | Anaheim | Orange County | SCAG | OCTA | Three high priority guardrail locations, including Santa Ana Canyon Rd. (2 locations) and Gerda St. | Upgrade existing guardrails. | 440269.36 | 428597.12 | 2018-11-06 | 0 | 2021-12-22 | 2024-10-30 | 428597.12 | Authorized | Authorized | No | Closed | Federal | 0
H8-12-003 | 8 | 5055189 | 12 | Anaheim | Orange County | SCAG | OCTA | Ten corridors including Anaheim Blvd., Ball Rd., Broadway, Cerritos Ave., Crescent St., East St., La Palma Ave., Lincoln Ave., State College Blvd., and Sunkist St. | Replace 672 existing pedestrian crossing heads with pedestrian countdown heads. | 116886 | 116886 | 0 | 0 | 2020-09-10 | 2022-10-21 | 116886 | No PE | Authorized | No | Closed | Federal | 0
H9-12-001 | 9 | 5055190 | 12 | Anaheim | Orange County | SCAG | OCTA | Seven (7) signalized intersection locations, including Brookhurst/La Palma, Euclid/Crescent, Harbor/Lincoln, Ball/State College, Ball/Brookhurst, Magnolia/Lincoln, Magnolia/Broadway, and Ball/Knott. | Provide Advanced Dilemma Zone Detection for high speed approaches and signal hardware updates at seven locations, and protected left turn phase at four intersections. | 2965125 | 2965125 | 2019-06-12 | 0 | 2023-08-01 | 0 | 2372100 | Authorized | Authorized | No | CON | Federal | 0
H9-12-002 | 9 | 5055193 | 12 | Anaheim | Orange County | SCAG | OCTA | Various intersections along the following corridors: Ball Rd, Broadway, Brookhurst St, Cerritos Ave, Euclid St, Harbor Blvd, La Palma Ave, Magnolia Ave, Nohl Ranch Rd, Santa Ana Canyon Rd, Serrano Ave and Miraloma Ave. | Upgrade 755 existing pedestrian crossings to pedestrian countdown signal heads at 123 intersections citywide. | 135457.31 | 135457.3 | 0 | 0 | 2021-07-29 | 2024-10-28 | 135457.3 | No PE | Authorized | No | Closed | Federal | 0
HSIP1-12-001 | 1 | 5055152 | 12 | Anaheim | Orange County | SCAG | OCTA | Ball Rd Between Knott Ave & Brookhurst St. | Upgrade Traffic Signals; Install Pavement Markings, Crosswalks And Delineation; Construct Ada Ramps; Lengthen Left Turn Pockets. | 596093.25 | 527290.43 | 2008-09-18 | 0 | 2012-09-12 | 2016-01-14 | 527290.43 | Authorized | Authorized | No | Closed | Federal | 0
HSIP4-12-009 | 4 | 5055179 | 12 | Anaheim | Orange County | SCAG | OCTA | S Douglass Rd., from S of E Katella Ave. to N of the RR grade crossing | Install dynamic message signs | 250780.77 | 81895.72 | 0 | 0 | 2014-09-16 | 2018-10-15 | 81895.72 | No PE | Authorized | No | Closed | Federal | 0
HSIP7-12-001 | 7 | 5055185 | 12 | Anaheim | Orange County | SCAG | OCTA | The intersection of East Katella Ave. and S. Douglass Rd | Modify signal on Douglass Rd. (northside of Katella Ave.) and Katella Ave. (eastside of Douglass Rd.), including installation of pole, foundation, mast arm signals, electronic sign guides, and new hardware. | 245000 | 208250 | 2016-08-09 | 0 | 2019-12-03 | 0 | 0 | Authorized | Authorized | No | Withdrawn | Federal
HSIP1-12-006 | 1 | 5237021 | 12 | Brea | Orange County | SCAG | OCTA | Carbon Canyon Rd At Olinda Place. | Install Traffic Signal; Construct Sidewalk And Minor Street Improvements. | 545247.02 | 490722.31 | 2008-09-18 | 0 | 2008-09-18 | 2012-02-24 | 490722.31 | Authorized | Authorized | No | Closed | Federal | 0
H11-12-003 | 11 | 5310044 | 12 | Buena Park | Orange County | SCAG | OCTA | 13 signalized intersections citywide. | Upgrade traffic signals for additional vehicle heads. Install new traffic signal controllers (Leading Pedestrian Interval) and countdown pedestrian head indications. | 1319900 | 1187910 | 2023-04-25 | 0 | 2026-02-20 | 0 | 1187910 | Authorized | Authorized | No | CON | State | 0
HSIP2-12-007 | 2 | 5310032 | 12 | Buena Park | Orange County | SCAG | OCTA | Malvern Ave. And Owens St. | Install New Traffic Signal. | 235214.8 | 211693.31 | 0 | 0 | 2010-09-01 | 2013-05-08 | 211693.31 | No PE | Authorized | No | Closed | Federal | 0
H11-12-004 | 11 | 5312107 | 12 | Costa Mesa | Orange County | SCAG | OCTA | 128 City-owned and maintained traffic signals throughout the City of Costa Mesa. | Install retroflective backplates and upgrade 8" signal heads to 12" (125 intersections), implement leading pedestrian intervals (44 intersections), install countdown pedestrian signal heads (36 intersections), install emergency vehicle preemption systems (29 intersections), and install battery backup systems (16 intersections). | 4340100 | 3906090 | 2023-12-26 | 0 | 2026-03-25 | 0 | 3294991.32 | Authorized | Authorized | No | CON | Federal | 2
H12-12-002 | 12 | 0 | 12 | Costa Mesa | Orange County | SCAG | OCTA | Junipero Drive from Arlington Drive to Presidio Drive, including the intersections of Junipero Drive at Arlington Drive and Junipero Drive at Presidio Drive. | Construct Class IV bicycle facility including slurry seal, signing, and striping, and construct a raised intersection at Junipero & Arlington. | 388800 | 349920 | 0 | 0 | 0 | 0 | 0 | No PE | Due by 3/31/2028 | No | Not Started | State | 0
HSIP2-12-008 | 2 | 5312073 | 12 | Costa Mesa | Orange County | SCAG | OCTA | Intersection Of Placentia Ave. And 17Th St. | Upgrade Traffic Signals; Install Safety Lighting, Count-Down Signal Heads, Radar Speed Feedback Signs, And Crosswalks | 104161 | 92616.3 | 0 | 0 | 2010-03-05 | 2012-07-17 | 92616.3 | No PE | Authorized | No | Closed | Federal | 0
HSIP3-12-022 | 3 | 5312084 | 12 | Costa Mesa | Orange County | SCAG | OCTA | Victoria St. At Valley | Upgrade Traffic Signal With Protected-Permissive Signal Phasing And Enhanced Safety Lighting; Install Various Bicycle/Pedestrian Improvements And Radar Speed Feedback Signs | 322416.32 | 218985.14 | 0 | 0 | 2013-02-01 | 2017-05-22 | 218985.14 | No PE | Authorized | No | Closed | Federal | 0
HSIP4-12-003 | 4 | 5312086 | 12 | Costa Mesa | Orange County | SCAG | OCTA | 19th St. between Harbor Blvd. and Placentia Ave. | Install crosswalks, pedestrian countdown heads, advance warning signs, speed feedback signs, and safety lighting | 437008.06 | 237000 | 0 | 0 | 2013-02-01 | 2018-08-14 | 237000 | No PE | Authorized | No | Closed | Federal | 0
HSIP4-12-006 | 4 | 5312085 | 12 | Costa Mesa | Orange County | SCAG | OCTA | Anton Blvd./Sunflower Ave. | Install protected left-turn phasing, pedestrian countdown heads, and CCTV; upgrade traffic signals | 277581.41 | 232379.99 | 0 | 0 | 2014-03-26 | 2017-02-27 | 232379.99 | No PE | Authorized | No | Closed | Federal | 0
HSIP5-12-002 | 5 | 5312092 | 12 | Costa Mesa | Orange County | SCAG | OCTA | Placentia Ave. between Adams Ave. and Wilson St. | Install raised median islands | 1811277.49 | 729700 | 2013-09-12 | 0 | 2017-02-16 | 2019-09-19 | 729700 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-12-003 | 5 | 5312093 | 12 | Costa Mesa | Orange County | SCAG | OCTA | Bristol St. between Baker St. and Newport Blvd. | Install raised medians | 1217895.14 | 492200 | 2013-09-12 | 0 | 2016-09-19 | 2020-10-29 | 492200 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-12-004 | 5 | 5312094 | 12 | Costa Mesa | Orange County | SCAG | OCTA | Red Hill Ave. between McCormick Ave. and Bristol St. | Install raised median islands and associated improvements | 1259413.79 | 778100 | 2013-09-12 | 0 | 2017-01-25 | 2020-11-24 | 778100 | Authorized | Authorized | No | Closed | Federal | 0
HSIP6-12-001 | 6 | 5312099 | 12 | Costa Mesa | Orange County | SCAG | OCTA | On Harbor Blvd between Wilson St and 19th St | Install raised medians | 1104691.12 | 538600 | 2015-09-08 | 0 | 2018-08-03 | 2021-05-28 | 538600 | Authorized | Authorized | No | Closed | Federal
HSIP7-12-002 | 7 | 5312102 | 12 | Costa Mesa | Orange County | SCAG | OCTA | Fairview Rd between Baker St and Adams Ave | Construct raised directional median to restrict left turns, construct new traffic signal. | 1276936.1 | 630540 | 2017-04-28 | 0 | 2020-05-12 | 2023-12-26 | 630540 | Authorized | Authorized | No | Closed | Federal
H9-12-003 | 9 | 5341033 | 12 | Fountain Valley | Orange County | SCAG | OCTA | Various intersections, including Edinger Ave at Ward St, Brookhurst St at Heil Ave, Harbor Blvd at Lilac Ave, Magnolia St at Slater Ave, Euclid St at Slater Ave, Warner Ave at Los Jardines West, Ellis Ave at Bushard St, Ellis Ave at Ward St. | Improve signal hardware: lenses, back-plates, mounting size and number; provide protected left-turn phase. | 2601741.6 | 2546601.31 | 2019-09-13 | 0 | 2021-08-16 | 2024-10-30 | 2546601.31 | Authorized | Authorized | No | Closed | Federal | 0
H12-12-003 | 12 | 0 | 12 | Fullerton | Orange County | SCAG | OCTA | Intersections of Orangethorpe Ave at Harbor Blvd, Orangethorpe Ave at Euclid St, Orangethorpe Ave at Brookhurst Rd, Orangethorpe Ave at Magnolia Ave, Harbor Blvd at Commonwealth Ave, and Harbor Blvd at Chapman Ave. | Improve signal hardware and install intersection lighting. Provide protected left turn phase. | 3576000 | 3218400 | 0 | 0 | 0 | 0 | 0 | Due in no more than 4 months | Due by 3/31/2028 | No | Not Started | Federal | 0
H8-12-004 | 8 | 5133045 | 12 | Fullerton | Orange County | SCAG | OCTA | Fourteen (14) select intersections citywide. | Install fourteen (14) pedestrian warning flashing beacons citywide. | 393266 | 264796.78 | 0 | 0 | 2022-07-14 | 2025-10-16 | 264796.78 | No PE | Authorized | No | Closed | Federal | 0
H8-12-005 | 8 | 5133046 | 12 | Fullerton | Orange County | SCAG | OCTA | Eighty-four (84) signalized intersections throughout the city. | Install 504 pedestrian countdown signal heads and 57 pedestrian countdown head housing units. | 140035 | 136600 | 0 | 0 | 2022-07-14 | 2026-03-16 | 136600 | No PE | Authorized | No | Closed | Federal | 0
H11-12-005 | 11 | 5328089 | 12 | Garden Grove | Orange County | SCAG | OCTA | The intersection of Garden Grove Blvd. & Nelson St. - Century Blvd. | Install protected left-turn phasing to all directions. Install additional vehicle signal heads and leading pesdetrian intervals. | 518000 | 466200 | 2023-04-20 | 0 | 2023-07-18 | 0 | 466200 | Authorized | Authorized | No | CON | State | 0
H11-12-006 | 11 | 5328090 | 12 | Garden Grove | Orange County | SCAG | OCTA | The intersection of Garden Grove Blvd and Newland St. | Install protective left-turn phasing to all directions. Install additional traffic signal heads and implement leading pedestrian intervals. | 413500 | 372150 | 2023-04-20 | 0 | 2023-07-18 | 0 | 372150 | Authorized | Authorized | No | CON | State | 0
H8-12-006 | 8 | 5328080 | 12 | Garden Grove | Orange County | SCAG | OCTA | Intersection of Garden Grove Boulevard and Ninth/Nina Street. | Install protected left-turn phasing to east/west approaches and install secondary traffic signal heads to east/west approaches to provide safe stopping space for vehicles crossing intersection. | 288182.58 | 194000 | 0 | 0 | 2018-01-17 | 2020-04-13 | 194000 | No PE | Authorized | No | Closed | Federal | 0
H8-12-007 | 8 | 5328081 | 12 | Garden Grove | Orange County | SCAG | OCTA | Intersection of Magnolia Street and Orangewood Avenue. | Install protected left-turn phasing. | 285912.89 | 217000 | 0 | 0 | 2018-01-17 | 2020-04-21 | 217000 | No PE | Authorized | No | Closed | Federal | 0
H8-12-008 | 8 | 5328082 | 12 | Garden Grove | Orange County | SCAG | OCTA | Ninety-nine (99) signalized intersections citywide. | Install 612 pedestrian countdown signal heads. | 186343 | 174104 | 0 | 0 | 2018-01-17 | 2020-04-21 | 174104 | No PE | Authorized | No | Closed | Federal | 0
H9-12-004 | 9 | 5328084 | 12 | Garden Grove | Orange County | SCAG | OCTA | The intersection of Trask Avenue and Roxey Drive. | Install a new traffic signal. | 358449.69 | 310000 | 2019-03-28 | 0 | 2020-05-11 | 2022-03-03 | 310000 | Authorized | Authorized | No | Closed | Federal | 0
H9-12-005 | 9 | 5328085 | 12 | Garden Grove | Orange County | SCAG | OCTA | The intersection of Trask Avenue and Newland Street. | Install protected left-turn phasing at all directions. | 350657.3 | 310000 | 2019-03-28 | 0 | 2020-05-11 | 2022-03-03 | 310000 | Authorized | Authorized | No | Closed | Federal | 0
H9-12-006 | 9 | 5328086 | 12 | Garden Grove | Orange County | SCAG | OCTA | Twenty-one (21) school crossing locations throughout the City of Garden Grove. | Install speed radar feedback signs. | 192000 | 192000 | 0 | 0 | 2020-05-11 | 2022-03-07 | 192000 | No PE | Authorized | No | Closed | Federal | 0
HSIP3-12-002 | 3 | 5328066 | 12 | Garden Grove | Orange County | SCAG | OCTA | Valley View St. From Sr 22 To North City Limit | Upgrade 5,700' Of Raised Median | 5203938.34 | 675000 | 2010-08-17 | 0 | 2013-01-24 | 2015-09-08 | 675000 | Authorized | Authorized | No | Closed | Federal | 0
HSIP3-12-003 | 3 | 5328067 | 12 | Garden Grove | Orange County | SCAG | OCTA | Harbor Blvd. From Trask Ave. To Westminster Ave. | Upgrade 2,250' Of Raised Median | 1018715.29 | 450000 | 2010-08-20 | 0 | 2013-01-24 | 2015-07-22 | 450000 | Authorized | Authorized | No | Closed | Federal | 0
HSIP3-12-004 | 3 | 5328065 | 12 | Garden Grove | Orange County | SCAG | OCTA | Euclid St. From Lampson Ave. To Garden Grove Blvd. | Upgrade 2,300' Of Raised Median | 5203938.34 | 456390 | 2010-08-18 | 0 | 2013-01-24 | 2015-11-19 | 456390 | Authorized | Authorized | No | Closed | Federal | 0
HSIP4-12-004 | 4 | 5328070 | 12 | Garden Grove | Orange County | SCAG | OCTA | Lampson Ave. between Manley St. and Knott St. | Construct raised median | 1445134.23 | 899999.99 | 2011-06-24 | 0 | 2012-05-23 | 2014-11-26 | 899999.99 | Authorized | Authorized | No | Closed | Federal | 0
HSIP7-12-003 | 7 | 5328078 | 12 | Garden Grove | Orange County | SCAG | OCTA | Intersection of Haster Street and Lampson Ave | Provide protected left-turn phase | 322551.53 | 220000 | 2017-01-24 | 0 | 2018-01-18 | 2020-04-21 | 220000 | Authorized | Authorized | No | Closed | Federal
H11-12-007 | 11 | 5181196 | 12 | Huntington Beach | Orange County | SCAG | OCTA | 18 intersections (10 on Edinger Avenue between Bolsa Chica Street and Parkside Lane, and 8 on Heil Avenue between Bolsa Chica Street and Gothard Street). | Install retro-reflective backplates, near-side vehicle heads and other signal upgrades at all locations. Add striping across intersections for bicycle lanes. Implement Leading Pedestrian Intervals at signalized intersections. | 826100 | 675090 | 0 | 0 | 2025-02-06 | 0 | 675090 | No PE | Authorized | No | CON | State | 0
HSIP5-12-005 | 5 | 5181177 | 12 | Huntington Beach | Orange County | SCAG | OCTA | Adams Ave./Bushard St.; Magnolia St./Yorktown Ave. | Install traffic signal (interconnect) and protected left-turn phasing | 696337.16 | 626703.42 | 2013-09-12 | 0 | 2014-09-15 | 2018-03-23 | 626703.42 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-12-006 | 5 | 5181178 | 12 | Huntington Beach | Orange County | SCAG | OCTA | Gothard St./Talbert Ave.; Gothard St./Heil Ave.; Springdale St./McFadden Ave. | Install protected left-turn phasing | 562243.28 | 504439.45 | 2013-09-12 | 0 | 2016-12-16 | 2019-04-30 | 504439.45 | Authorized | Authorized | No | Closed | Federal | 0
HSIP6-12-002 | 6 | 5181181 | 12 | Huntington Beach | Orange County | SCAG | OCTA | Main St/17th St, Main St/ Utica Ave, Bolsa Chica St/Pearce Dr | Upgrade traffic signals; Install protected left-turn phasing | 1036874.28 | 879699.77 | 2015-12-09 | 0 | 2018-08-03 | 2021-01-06 | 879699.77 | Authorized | Authorized | No | Closed | Federal
HSIP6-12-003 | 6 | 5181182 | 12 | Huntington Beach | Orange County | SCAG | OCTA | Gothard St/Center Ave | Upgrade traffic signals (interconnect); Install protected left-turn phasing | 455409.47 | 406737.08 | 2015-12-09 | 0 | 2018-08-03 | 2021-02-25 | 406737.08 | Authorized | Authorized | No | Closed | Federal
HSIP6-12-004 | 6 | 5181180 | 12 | Huntington Beach | Orange County | SCAG | OCTA | Newland St/Slater Ave | Upgrade traffic signals; Install protected left-turn phasing | 360884.21 | 324540.03 | 2015-12-28 | 0 | 2018-08-27 | 2022-01-13 | 324540.03 | Authorized | Authorized | No | Closed | Federal
HSIP6-12-005 | 6 | 5181183 | 12 | Huntington Beach | Orange County | SCAG | OCTA | Newland St/Ellis Ave and on Newland St between Ellis Ave and Garfield Ave | Upgrade traffic signals (interconnect); Install protected left-turn phasing | 429186.79 | 386279.24 | 2015-12-24 | 0 | 2018-08-03 | 2021-04-08 | 386279.24 | Authorized | Authorized | No | Closed | Federal
HSIP6-12-006 | 6 | 5181184 | 12 | Huntington Beach | Orange County | SCAG | OCTA | On Goldenwest St between Heil Ave and Warner Ave | Upgrade traffic signals (interconnect); Install protected left-turn phasing | 361363.2 | 326343.82 | 2015-12-21 | 0 | 2018-08-03 | 2021-10-22 | 326343.82 | Authorized | Authorized | No | Closed | Federal
HSIP6-12-007 | 6 | 5181185 | 12 | Huntington Beach | Orange County | SCAG | OCTA | Gothard St/Slater Ave | Upgrade traffic signals (interconnect); Install protected left-turn phasing | 405834.44 | 363613.54 | 2015-12-21 | 0 | 2018-08-03 | 2021-03-16 | 363613.54 | Authorized | Authorized | No | Closed | Federal
HSIP6-12-008 | 6 | 5181186 | 12 | Huntington Beach | Orange County | SCAG | OCTA | On Newland St between Warner Ave and Ellis Ave | Upgrade traffic signals (interconnect) | 327689.42 | 296070.6 | 2015-12-24 | 0 | 2018-07-17 | 2020-12-14 | 296070.6 | Authorized | Authorized | No | Closed | Federal
H10-12-003 | 10 | 5410086 | 12 | Irvine | Orange County | SCAG | OCTA | Seven locations throughout the City of Irvine. | Construct pedestrian crossing enhancements with Rectangular Rapid Flashing Beacons (RRFBs). | 210039 | 210039 | 0 | 0 | 2022-03-03 | 0 | 248162 | No PE | Authorized | No | CON | State | 0
HSIP1-12-008 | 1 | 5410066 | 12 | Irvine | Orange County | SCAG | OCTA | Intersection Of California Ave And Campus Dr. | Upgrade Traffic Signals; Add Protective Left-Turn Phasing. | 157477.38 | 97469.55 | 2008-05-27 | 0 | 2012-02-24 | 2014-01-14 | 97469.55 | Authorized | Authorized | No | Closed | Federal | 0
HSIP2-12-010 | 2 | 5410068 | 12 | Irvine | Orange County | SCAG | OCTA | Macarthur Blvd. South Of University Dr. And North Of Sr-73 | Upgrade Median Barrier And Construct Drainage Improvements. | 279684.44 | 247216 | 0 | 0 | 2010-05-20 | 2012-07-10 | 247216 | No PE | Authorized | No | Closed | Federal | 0
HSIP3-12-012 | 3 | 5410072 | 12 | Irvine | Orange County | SCAG | OCTA | Various Intersections | Construct Curb Ramps | 868781.35 | 781121.31 | 0 | 0 | 2012-03-27 | 2014-05-16 | 781121.31 | No PE | Authorized | No | Closed | Federal | 0
HSIP4-12-012 | 4 | 5410075 | 12 | Irvine | Orange County | SCAG | OCTA | Warner Ave./Jamboree Rd. NB on-ramp | Install traffic signals | 489261.95 | 440335.75 | 0 | 0 | 2013-12-16 | 2016-05-09 | 440335.75 | No PE | Authorized | No | Closed | Federal | 0
HSIP5-12-007 | 5 | 5410081 | 12 | Irvine | Orange County | SCAG | OCTA | Trabuco Rd./Monroe | Install traffic signals with modified intersection geometry | 1566672.32 | 900000 | 0 | 0 | 2014-02-12 | 2016-04-26 | 900000 | No PE | Authorized | No | Closed | Federal | 0
HSIP6-12-009 | 6 | 5410082 | 12 | Irvine | Orange County | SCAG | OCTA | Paseo Westpark/Warner Ave | Upgrade traffic signals; Install protected left-turn phasing | 467118.21 | 420098.05 | 2014-06-20 | 0 | 2016-08-10 | 2019-01-18 | 420098.05 | Authorized | Authorized | No | Closed | Federal
H9-12-007 | 9 | 5266029 | 12 | La Habra | Orange County | SCAG | OCTA | Six (6) intersections, including La Habra Blvd & Monte Vista St, La Habra Blvd & Cypress St, Harbor Blvd & Sterns Ave, Lambert Rd & Idaho St, Idaho St & Las Lomas Ave, and La Habra Blvd & Euclid St. | Add left-turn storage and left-turn protected signal phasing at one intersection; add left-turn protected signal phasing at four intersections; and upgrade existing signals at all six intersections. | 1634800 | 1471300 | 2019-06-12 | 0 | 2025-08-21 | 0 | 706140 | Authorized | Authorized | No | CON | Federal | 0
H9-12-008 | 9 | 5266030 | 12 | La Habra | Orange County | SCAG | OCTA | Eight (8) intersections, including La Habra & Monte Vista, La Habra & Cypress, Harbor & Sterns, Lambert & Idaho, Las Lomas & Idaho, La Habra & Euclid, La Habra & Harbor, and Lambert & Harbor. | Upgrade existing pedestrian signal heads with new pedestrian countdown signal heads. | 115400 | 115400 | 2019-06-12 | 0 | 2023-08-14 | 0 | 115400 | Authorized | Authorized | No | CON | Federal | 2
HSIP4-12-014 | 4 | 5266021 | 12 | La Habra | Orange County | SCAG | OCTA | In the School zones of: El Portal Dr., Cajon Dr. (Briercliff Dr.), Schoolwood Dr., Hillside St., and Brookdale Ave. | Install speed feedback signs | 97500 | 50840 | 2012-07-30 | 0 | 2013-09-19 | 0 | 0 | Authorized | Authorized | No | Withdrawn | Federal | 0
H11-12-008 | 11 | 5458018 | 12 | Laguna Niguel | Orange County | SCAG | OCTA | Heather Ridge between Pacific Park Drive and Avila Road. | Installation of Class II bike lanes. | 144400 | 129960 | 0 | 0 | 2023-09-21 | 0 | 129960 | No PE | Authorized | No | CON | State | 0
H12-12-004 | 12 | 0 | 12 | Laguna Niguel | Orange County | SCAG | OCTA | Golden Lantern from Crown Valley Parkway to Chapparosa Park Road, approximately 2 miles in length. | Install vertical element separators; implement green bike lane conflict zone striping; and implement white buffer striping. | 950000 | 346500 | 0 | 0 | 0 | 0 | 0 | No PE | Due by 3/31/2028 | No | Not Started | State | 0
H10-12-004 | 10 | 5451037 | 12 | Mission Viejo | Orange County | SCAG | OCTA | Twenty-Four (24) prioritized signalized intersection locations within the City of Mission Viejo. | Install audible pedestrian push button systems. | 248200 | 248200 | 0 | 0 | 2023-08-15 | 2026-01-27 | 248200 | No PE | Authorized | No | Closed | State | 0
H11-12-009 | 11 | 5451038 | 12 | Mission Viejo | Orange County | SCAG | OCTA | Various Locations throughout the city. | Installation of Rectangular Rapid Flashing Beacons (RRFB) with enhanced pedestrian safety features (high visibility crosswalk markings, advanced yield lines, curb ramps, and signage). | 277100 | 249390 | 0 | 0 | 2024-08-07 | 0 | 249390 | No PE | Authorized | No | CON | State | 0
H8-12-009 | 8 | 5451033 | 12 | Mission Viejo | Orange County | SCAG | OCTA | Thirty-nine (39) signalized intersection locations within the City of Mission Viejo. | Install pedestrian countdown signal heads. | 29000 | 29000 | 0 | 0 | 2018-06-14 | 2019-11-19 | 29000 | No PE | Authorized | No | Closed | Federal | 0
HSIP5-12-008 | 5 | 5451031 | 12 | Mission Viejo | Orange County | SCAG | OCTA | Various locations throughout the city | Install Emergency Vehicle Pre-emption (EVP) systems | 462642.73 | 416378.46 | 2013-03-26 | 0 | 2014-09-17 | 2018-03-06 | 416378.46 | Authorized | Authorized | No | Closed | Federal | 0
H11-12-010 | 11 | 5073097 | 12 | Orange | Orange County | SCAG | OCTA | Existing crossing at Collins Avenue at California Street/Lynn Drive, Jordan Avenue at Esplanade Street, and La Veta Avenue at Malena Drive. | Replace existing beacons with Rectangular Rapid Flashing Beacons near schools. | 277300 | 249570 | 2023-09-28 | 0 | 0 | 0 | 18900 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE | State | 0
H12-12-005 | 12 | 5073102 | 12 | Orange | Orange County | SCAG | OCTA | 28 signalized intersections citywide. | Install larger signal heads and yellow retroreflective backplates. | 734800 | 661320 | 2025-09-30 | 0 | 0 | 0 | 31500 | Authorized | Due by 3/31/2028 | No | PE | State | 0
H12-12-006 | 12 | 5073103 | 12 | Orange | Orange County | SCAG | OCTA | Four crossing locations: Shaffer St & Everett Pl; Walnut Ave & Harwood St; Shaffer St 130' N/o Almond Ave; and Rancho Santiago Blvd & Orange Grove Ave. | Install rectangular rapid flashing beacons (RRFBs). | 388600 | 349740 | 2025-09-30 | 0 | 0 | 0 | 42300 | Authorized | Due by 3/31/2028 | No | PE | State | 0
H12-12-007 | 12 | 5073104 | 12 | Orange | Orange County | SCAG | OCTA | Four (4) locations: Glassell Street from Riverdale Ave to Katella Ave; Fletcher Street from Batavia St to Glassell St; Main Street from Taft Ave to Collins Ave; and Canyon View Ave from Newport Blvd to Jamboree Rd. | Install bike lanes and green paint at conflict points throughout the city. | 388800 | 349920 | 2025-09-30 | 0 | 0 | 0 | 36000 | Authorized | Due by 3/31/2028 | No | PE | State | 0
H12-12-008 | 12 | 5073105 | 12 | Orange | Orange County | SCAG | OCTA | Twelve (12) street segments approximately 8.5 miles in length. | Install edgelines striping. | 297300 | 267570 | 2025-09-30 | 0 | 0 | 0 | 22500 | Authorized | Due by 3/31/2028 | No | PE | State | 0
H8-12-010 | 8 | 5073090 | 12 | Orange | Orange County | SCAG | OCTA | Intersection of Chapman Avenue at Batavia Street. | Install protected left-turn phasing for northbound and southbound approaches. | 581409.15 | 399800 | 2017-11-27 | 0 | 2021-04-28 | 2026-03-03 | 399800 | Authorized | Authorized | No | Closed | Federal | 0
H8-12-011 | 8 | 5073088 | 12 | Orange | Orange County | SCAG | OCTA | Intersection of Chapman Avenue at Feldner Street. | Install protected left-turn phasing for northbound and southbound approaches. | 248500 | 248500 | 2017-11-27 | 0 | 2020-11-06 | 2023-03-20 | 248500 | Authorized | Authorized | No | Closed | Federal | 0
H8-12-012 | 8 | 5073087 | 12 | Orange | Orange County | SCAG | OCTA | Intersection of Chapman Avenue at Flower Street. | Install protected left-turn phasing for northbound and southbound approaches. | 248500 | 248500 | 2017-12-18 | 0 | 2020-11-23 | 2022-08-11 | 248500 | Authorized | Authorized | No | Closed | Federal | 0
H8-12-013 | 8 | 5073089 | 12 | Orange | Orange County | SCAG | OCTA | Three arterial road segments: La Veta Avenue from Flower St. to Bedford St., Collins Avenue from Wanda Rd. to Bond Ave., and Chapman Avenue from Jamboree Rd. to Orange Park Blvd. | Install Radar Feedback Speed Signs at specific locations with a history of speed related accidents. | 249951.21 | 249951.21 | 2017-11-27 | 0 | 2020-09-10 | 2022-11-16 | 249951.21 | Authorized | Authorized | No | Closed | Federal | 0
HSIP1-12-004 | 1 | 5073060 | 12 | Orange | Orange County | SCAG | OCTA | Intersection Of La Veta Avenue And Parker St. | Add Protected Left-Turn Phasing | 128628 | 49500 | 0 | 0 | 2010-03-08 | 2012-04-20 | 49500 | No PE | Authorized | No | Closed | Federal | 0
HSIP2-12-005 | 2 | 5073059 | 12 | Orange | Orange County | SCAG | OCTA | Santiago Canyon Between Winds Dr And East Angel View Terrace | Construct Raised Median And Guard Rail. Install New Signs, Striping, And Pavement Markings. | 857162.17 | 698670 | 2009-02-09 | 0 | 2010-06-01 | 2012-04-03 | 698670 | Authorized | Authorized | No | Closed | Federal | 0
HSIP2-12-006 | 2 | 5073064 | 12 | Orange | Orange County | SCAG | OCTA | Chapman Ave. Between State College Blvd. And Yorba St. | Install Emergency Vehicle Preemption System. | 236033.5 | 212430.14 | 0 | 0 | 2010-02-26 | 2012-03-20 | 212430.14 | No PE | Authorized | No | Closed | Federal | 0
HSIP4-12-001 | 4 | 5073070 | 12 | Orange | Orange County | SCAG | OCTA | Cannon St. between Via Escola and Santiago Canyon Rd.; Santiago Canyon Rd. between Jamboree Rd. and SR 241; Collins Ave. between Tustin St. and Shaffer St.; Serrano Ave. between Cannon St. and Kendra Way | Install speed feedback signs | 247793.45 | 196500 | 2012-05-15 | 0 | 2012-11-13 | 2014-08-05 | 196500 | Authorized | Authorized | No | Closed | Federal | 0
HSIP4-12-002 | 4 | 5073071 | 12 | Orange | Orange County | SCAG | OCTA | Cannon St. between Santiago Canyon Rd. and Chapman Ave.; La Veta Ave. between Yorba St. and Esplanade St.; Chapman Ave. between Orange Park Blvd. and Cannon St. | Install speed feedback signs | 202480.81 | 176049.95 | 2012-05-15 | 0 | 2013-02-01 | 2014-12-22 | 176049.95 | Authorized | Authorized | No | Closed | Federal | 0
HSIP4-12-005 | 4 | 5073069 | 12 | Orange | Orange County | SCAG | OCTA | Tustin St./Palm Ave. | Install protected left-turn phasing | 220054.57 | 167598 | 2012-04-06 | 0 | 2013-02-01 | 2014-09-02 | 167598 | Authorized | Authorized | No | Closed | Federal | 0
HSIP4-12-016 | 4 | 5073068 | 12 | Orange | Orange County | SCAG | OCTA | Lincoln Ave. between Orange Olive Rd. and Orange Ave. | Construct sidewalk gap closure | 651000.56 | 569798.58 | 2012-05-23 | 2013-07-29 | 2015-09-16 | 2019-01-11 | 569798.58 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-12-009 | 5 | 5073073 | 12 | Orange | Orange County | SCAG | OCTA | Chapman Ave./Hewes St. | Install protected left-turn phasing | 258687.57 | 214545.22 | 2013-09-09 | 0 | 2015-03-10 | 2018-06-22 | 214545.22 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-12-010 | 5 | 5073074 | 12 | Orange | Orange County | SCAG | OCTA | Fourteen (14) intersections throughout the city | Upgrade crosswalks; install solar-powered flashing beacons | 285406.28 | 254828.44 | 2013-08-23 | 0 | 2017-01-25 | 2018-11-02 | 254828.44 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-12-011 | 5 | 5073076 | 12 | Orange | Orange County | SCAG | OCTA | Chapman Ave./Esplanade St. | Install protected left-turn phasing | 253879.11 | 187459.22 | 2013-08-23 | 0 | 2015-01-22 | 2018-06-22 | 187459.22 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-12-012 | 5 | 5073075 | 12 | Orange | Orange County | SCAG | OCTA | Tustin St./Mayfair Ave. | Install protected left-turn phasing | 265698.41 | 205199 | 2013-08-23 | 0 | 2015-01-23 | 2018-06-26 | 205199 | Authorized | Authorized | No | Closed | Federal | 0
HSIP6-12-010 | 6 | 5073078 | 12 | Orange | Orange County | SCAG | OCTA | Glassell St/Walnut Ave | Install protected left-turn phasing; install left-turn pockets | 484725.22 | 293186.04 | 2014-06-26 | 0 | 2017-11-27 | 2023-06-16 | 293186.04 | Authorized | Authorized | No | Closed | Federal
HSIP6-12-011 | 6 | 5073079 | 12 | Orange | Orange County | SCAG | OCTA | E Chapman Ave/S Cannon St-S Crawford Canyon Rd | Upgrade traffic signals; Install protected left-turn phasing | 345794.44 | 270704.51 | 2014-07-11 | 0 | 2017-08-23 | 2020-10-06 | 270704.51 | Authorized | Authorized | No | Closed | Federal
HSIP6-12-012 | 6 | 5073080 | 12 | Orange | Orange County | SCAG | OCTA | E Chapman Ave/S James St | Upgrade traffic signals; Install protected left-turn phasing | 355266.1 | 257244.54 | 2014-06-20 | 0 | 2017-11-09 | 2022-05-12 | 257244.54 | Authorized | Authorized | No | Closed | Federal
HSIP6-12-013 | 6 | 5073081 | 12 | Orange | Orange County | SCAG | OCTA | W Collins Ave/N Batavia St | Install protected left-turn phasing; install left-turn pockets | 349227.2 | 281177.96 | 2014-06-20 | 0 | 2017-08-29 | 2020-10-06 | 281177.96 | Authorized | Authorized | No | Closed | Federal
HSIP7-12-004 | 7 | 5073083 | 12 | Orange | Orange County | SCAG | OCTA | The intersection of Glassell St. and Meats Ave. | Install protected left-turn phasing for northbound and southbound approaches. | 249007.1 | 249007.1 | 2017-02-27 | 0 | 2020-06-05 | 2021-12-16 | 249007.1 | Authorized | Authorized | No | Closed | Federal
HSIP7-12-005 | 7 | 5073084 | 12 | Orange | Orange County | SCAG | OCTA | The intersection of Glassell St. and Collins Ave. | Install protected left-turn phasing for northbound and southbound approaches | 295059.48 | 281892.48 | 2017-02-03 | 0 | 2020-11-06 | 2022-08-16 | 281892.48 | Authorized | Authorized | No | Closed | Federal
HSIP7-12-006 | 7 | 5073085 | 12 | Orange | Orange County | SCAG | OCTA | At 33 signalized intersections within the City of Orange | Install pedestrian countdown signals (PCS), new crosswalk striping and battery back-ups | 187289.14 | 187289.14 | 2017-09-13 | 0 | 2019-11-20 | 2021-07-01 | 187289.14 | Authorized | Authorized | No | Closed | Federal
HSIP7-12-007 | 7 | 5073086 | 12 | Orange | Orange County | SCAG | OCTA | At 11 signalized intersections within the City of Orange | Upgrade the accessible pedestrian signals (APS) | 179033.76 | 177353.08 | 2017-02-27 | 0 | 2019-11-26 | 2021-10-21 | 177353.08 | Authorized | Authorized | No | Closed | Federal
H12-12-009 | 12 | 0 | 12 | Orange County | Orange County | SCAG | OCTA | Fifty-nine (59) signalized intersections. | Install retroreflective signal backplates and leading pedestrian interval (LPI). | 1326200 | 1193580 | 0 | 0 | 0 | 0 | 0 | No PE | Due by 3/31/2028 | No | Not Started | State | 0
H12-12-010 | 12 | 0 | 12 | Orange County | Orange County | SCAG | OCTA | Sixty-one (61) uncontrolled intersections and seven (7) pedestrian crossings across uncontrolled approaches at side-street stop-controlled intersections. | Install stop signs/bars/pavement markers and rectangular rapid flashing beacon (RRFB). | 829900 | 746910 | 0 | 0 | 0 | 0 | 0 | No PE | Due by 3/31/2028 | No | Not Started | State | 0
H12-12-011 | 12 | 5955126 | 12 | Orange County | Orange County | SCAG | OCTA | Two (2) curved rural roads: Brea Blvd/Brea Canyon Rd and Silverado Canyon Road. | Install centerline rumble stripes, chevron signs, speed reduction markings, and rectangular rapid flashing beacon (RRFB). | 960300 | 864270 | 2026-01-06 | 0 | 0 | 0 | 81000 | Authorized | Due by 3/31/2028 | No | PE | State | 0
HSIP5-12-013 | 5 | 5955086 | 12 | Orange County | Orange County | SCAG | OCTA | Gilbert St. between Katella Ave. and W. Ball Rd. | Reconfigure lanes, upgrade traffic signals; place utilities underground; install safety lighting, signs, striping, and pavemetn markings | 3034610.55 | 800676.01 | 0 | 0 | 2015-02-06 | 2018-10-17 | 800676.01 | No PE | Authorized | No | Closed | Federal | 0
HSIP6-12-014 | 6 | 5955093 | 12 | Orange County | Orange County | SCAG | OCTA | On Live Oak Canyon Rd between El Toro Rd-Santiago Canyon Rd and O'Neill Regional Park Entrance | Upgrade shoulder and signs; Install high friction surface, guardrail and rumble strips | 2661528.38 | 1500000 | 0 | 0 | 2018-02-02 | 2020-05-12 | 1500000 | No PE | Authorized | No | Closed | Federal
HSIP6-12-015 | 6 | 5955089 | 12 | Orange County | Orange County | SCAG | OCTA | On Trabuco Canyon Rd between O'Neill Regional Park Entrance and County/City Boundary | Upgrade shoulder and signs; Install high friction surface, guardrail and rumble strips | 1276885.74 | 942896 | 2014-09-16 | 0 | 2018-02-02 | 2020-04-28 | 942896 | Authorized | Authorized | No | Closed | Federal
HSIP7-12-008 | 7 | 5955101 | 12 | Orange County | Orange County | SCAG | OCTA | Santiage Canyon Rd between State Rte 241 and N. Live Oak | Install reflectors, and/or object markers. Improve pavement friction with High Friction Surface Treatments. Additional countermeasures such as left turn pockets, curve warning signs, metal beam guardrail reconstruction, as well as the bike lane striping improvements, may be incorporated | 3559813.82 | 1740342.51 | 2016-12-15 | 0 | 2020-03-12 | 2022-03-07 | 1740342.51 | Authorized | Authorized | No | Closed | Federal
H12-12-012 | 12 | 5269031 | 12 | Placentia | Orange County | SCAG | OCTA | Various Locations throughout the City, including 7 signalized intersections and 2 unsignalized intersections. | Install leading pedestrian intervals (LPIs) and install/upgrade pedestrian crossings. | 281100 | 252990 | 2025-07-08 | 0 | 0 | 0 | 34200 | Authorized | Due by 3/31/2028 | No | PE | State | 0
H9-12-010 | 9 | 5269028 | 12 | Placentia | Orange County | SCAG | OCTA | Five (5) intersections, including Bastanchury Rd/Valencia Ave, Yorba Linda Blvd/Kraemer Blvd, Yorba Linda Blvd/Palm Dr, Kraemer Bl/Madison Ave, and Chapman Ave/Bradford Ave. | Improve signal hardware and provide protected left-turn phase. | 1643916.58 | 1642057 | 2019-11-22 | 0 | 2021-05-13 | 2025-01-16 | 1642057 | Authorized | Authorized | No | Closed | Federal | 0
HSIP1-12-009 | 1 | 5478007 | 12 | Rancho Santa Margarita | Orange County | SCAG | OCTA | Santa Margarita Parkway Bridge. | Install 1,714 Lf Of Railing On Top Of Crash Barrier; Modify Railing On Opposite Side Of Bridge. | 197432 | 177688.8 | 2008-02-13 | 0 | 2008-02-13 | 2009-07-09 | 177688.8 | Authorized | Authorized | No | Closed | Federal | 0
HSIP4-12-017 | 4 | 5478015 | 12 | Rancho Santa Margarita | Orange County | SCAG | OCTA | Robinson Ranch Rd./Pennington Ln.; Robinson Ranch Rd./Winchester Dr.; Robinson Ranch Rd./Cimmaron Ln.; Robinson Ranch Rd./Shadow Rock Dr.; Robinson Ranch Rd./Morningside Dr. | Construct bulb-outs | 222661.34 | 191856.01 | 0 | 0 | 2012-07-10 | 2014-11-18 | 191856.01 | No PE | Authorized | No | Closed | Federal | 0
HSIP4-12-013 | 4 | 5274037 | 12 | San Clemente | Orange County | SCAG | OCTA | N El Camino Real between Camino Capistrano and Avenida Estacion | Contruct Class I bike path, K-rail barrier, sidewalk and curb ramps; upgrade traffic signals and striping | 1841150.3 | 607075.4 | 0 | 0 | 2016-08-12 | 2018-10-15 | 607075.4 | No PE | Authorized | No | Closed | Federal | 0
H10-12-005 | 10 | 5063204 | 12 | Santa Ana | Orange County | SCAG | OCTA | The intersection of Bristol Street at Santa Clara Avenue. | Install left turn phasing for north and south directions. | 320900 | 320900 | 2021-05-06 | 0 | 2022-08-11 | 0 | 320900 | Authorized | Authorized | No | CON | State | 0
H12-12-013 | 12 | 0 | 12 | Santa Ana | Orange County | SCAG | OCTA | On 1st Street between Downtown Plaza and Euclid Street, on Bristol Street from Riverglen Lane to Willits Avenue, and Broadway/Washington Avenue and Main Street/17th Street Intersections. | Install high visibility marked crosswalks. | 342300 | 308070 | 0 | 0 | 0 | 0 | 0 | No PE | Due by 3/31/2028 | No | Not Started | State | 0
H12-12-014 | 12 | 5063221 | 12 | Santa Ana | Orange County | SCAG | OCTA | First Street between Harbor Blvd to Susan Street and First Street between Fairview Street and Center Street. | Install street lights. | 2756000 | 2480400 | 2025-12-08 | 0 | 0 | 0 | 45000 | Authorized | Due by 3/31/2028 | No | PE | Federal | 0
H8-12-014 | 8 | 5063189 | 12 | Santa Ana | Orange County | SCAG | OCTA | Intersection of Main Street and 15th Street. | Install a new traffic signal. | 408800 | 408800 | 2017-11-03 | 0 | 2021-04-19 | 0 | 488140 | Authorized | Authorized | No | CON | Federal | 0
H8-12-015 | 8 | 5063190 | 12 | Santa Ana | Orange County | SCAG | OCTA | Intersections of 1st Street at Jackson Street and 5th Street at Euclid Street. | Install left turn phasing (east and west directions at 1st Street at Jackson Street and north and south directions at 5th Street and Euclid Street). | 1059487 | 845528 | 2017-11-03 | 0 | 2021-04-19 | 0 | 845528 | Authorized | Authorized | No | CON | Federal | 0
HSIP1-12-002 | 1 | 5063118 | 12 | Santa Ana | Orange County | SCAG | OCTA | Intersection Of Harbor Blvd And Kent Ave. | Install Traffic Signal. | 221440.29 | 199296.25 | 2008-02-06 | 0 | 2009-05-29 | 2012-07-20 | 199296.25 | Authorized | Authorized | No | Closed | Federal | 0
HSIP1-12-003 | 1 | 5063119 | 12 | Santa Ana | Orange County | SCAG | OCTA | Intersection Of Flower St. And Santa Ana Blvd. | Modify Traffic Signal; Install Left Turn Phasing. | 229886.75 | 190354 | 2008-02-06 | 0 | 2009-05-29 | 2012-12-18 | 190354 | Authorized | Authorized | No | Closed | Federal | 0
HSIP2-12-003 | 2 | 5063129 | 12 | Santa Ana | Orange County | SCAG | OCTA | 17Th St And King St | Install Traffic Signal. | 301586.82 | 265958.53 | 2010-03-08 | 0 | 2012-01-11 | 2014-03-04 | 265958.53 | Authorized | Authorized | No | Closed | Federal | 0
HSIP2-12-004 | 2 | 5063130 | 12 | Santa Ana | Orange County | SCAG | OCTA | Intersection Of Civic Center Dr. And Pacific Ave. | Install Traffic Signal | 256823.63 | 230467.7 | 2010-03-08 | 0 | 2011-08-15 | 2014-06-26 | 230467.7 | Authorized | Authorized | No | Closed | Federal | 0
HSIP4-12-007 | 4 | 5063141 | 12 | Santa Ana | Orange County | SCAG | OCTA | McFadden Ave./Lyon St. | Install left-turn phasing; upgrade signing | 378621.67 | 312297.01 | 2012-01-11 | 0 | 2013-01-24 | 2015-01-28 | 312297.01 | Authorized | Authorized | No | Closed | Federal | 0
HSIP4-12-008 | 4 | 5063142 | 12 | Santa Ana | Orange County | SCAG | OCTA | McFadden Ave./Euclid St. | Install left-turn phasing; upgrade signing | 367393.93 | 310330.85 | 2012-01-11 | 0 | 2012-08-15 | 2015-05-01 | 310330.85 | Authorized | Authorized | No | Closed | Federal | 0
HSIP4-12-010 | 4 | 5063139 | 12 | Santa Ana | Orange County | SCAG | OCTA | Fairview St./Edna Dr. | Install traffic signals; upgrade signing | 420826.88 | 308140.36 | 2012-01-11 | 0 | 2012-08-15 | 2015-05-01 | 308140.36 | Authorized | Authorized | No | Closed | Federal | 0
HSIP4-12-015 | 4 | 5063140 | 12 | Santa Ana | Orange County | SCAG | OCTA | Raitt St./Adams St. | Install traffic signals; upgrade signing | 551703.42 | 389908.8 | 2012-01-11 | 0 | 2013-09-23 | 2020-10-22 | 389908.8 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-12-014 | 5 | 5063152 | 12 | Santa Ana | Orange County | SCAG | OCTA | Newhope St./Camille St. | Install traffic signals | 265462.1 | 238825.48 | 2013-06-11 | 0 | 2014-09-17 | 2018-03-27 | 238825.48 | Authorized | Authorized | No | Closed | Federal | 0
HSIP5-12-015 | 5 | 5063151 | 12 | Santa Ana | Orange County | SCAG | OCTA | Segerstrom Ave./Bear St. | Install left-turn phasing | 182991.73 | 164576.38 | 2013-06-11 | 0 | 2015-03-10 | 2018-01-17 | 164576.38 | Authorized | Authorized | No | Closed | Federal | 0
HSIP6-12-016 | 6 | 5063154 | 12 | Santa Ana | Orange County | SCAG | OCTA | Various locations throughout Santa Ana | Install pedestrian countdown heads and ADA pedestrian pushbuttons | 791468.26 | 780601.65 | 2014-07-31 | 0 | 2015-09-09 | 2018-05-21 | 780601.65 | Authorized | Authorized | No | Closed | Federal
HSIP6-12-017 | 6 | 5063156 | 12 | Santa Ana | Orange County | SCAG | OCTA | Four intersections within Santa Ana | Install protected left-turn phasing | 1079699.51 | 977759.46 | 2014-07-31 | 0 | 2015-03-24 | 2018-10-19 | 977759.46 | Authorized | Authorized | No | Closed | Federal
HSIP6-12-021 | 6 | 5063155 | 12 | Santa Ana | Orange County | SCAG | OCTA | Various locations throughout the City of Santa Ana | Install crosswalk and rectangular rapid flashing beacons | 304877.48 | 209403.16 | 2014-07-31 | 0 | 2016-09-20 | 2019-11-19 | 209403.16 | Authorized | Authorized | No | Closed | Federal
HSIP6-12-022 | 6 | 5063157 | 12 | Santa Ana | Orange County | SCAG | OCTA | Various segments located throughout the City of Santa Ana | Upgrade signs | 207025.48 | 204854.02 | 2014-07-31 | 0 | 2016-06-28 | 2018-06-13 | 204854.02 | Authorized | Authorized | No | Closed | Federal
HSIP7-12-009 | 7 | 5063188 | 12 | Santa Ana | Orange County | SCAG | OCTA | At 74 intersections located within the City of Santa Ana | Upgrade non-standard 8 inch vehicle head with 12 inch vehicle head assembly and associated hardware | 418736.87 | 418736.87 | 2017-10-19 | 0 | 2019-09-13 | 2022-01-26 | 418736.87 | Authorized | Authorized | No | Closed | Federal
HSIP7-12-010 | 7 | 5063186 | 12 | Santa Ana | Orange County | SCAG | OCTA | At 14 uncontrolled crosswalks within the City of Santa Ana | Installation of rectangular rapid flashing beacons, advanced "yield" markings, additional striping and signage | 397252.64 | 397252.64 | 2017-08-23 | 0 | 2019-09-13 | 2022-01-13 | 397252.64 | Authorized | Authorized | No | Closed | Federal
HSIP7-12-011 | 7 | 5063171 | 12 | Santa Ana | Orange County | SCAG | OCTA | East and west directions at Euclid Street and Hazard Avenue. | Installation of left turn phasing for east and west directions | 318643.11 | 259600.11 | 2016-09-20 | 0 | 2019-09-06 | 2024-11-05 | 259600.11 | Authorized | Authorized | No | Closed | Federal
HSIP7-12-012 | 7 | 5063187 | 12 | Santa Ana | Orange County | SCAG | OCTA | Along Flower Street from Civic Center Drive to Warner Ave | Installation of bicycle lanes along 2.5 mile corridor of Flower Street and protected left turn phasing at two intersections | 852295.28 | 756170.74 | 2017-10-20 | 0 | 2020-02-12 | 2023-03-20 | 756170.74 | Authorized | Authorized | No | Closed | Federal
HSIP2-12-009 | 2 | 5338033 | 12 | Westminster | Orange County | SCAG | OCTA | Bolsa Chica Rd. From Westminster Blvd. To Rancho Rd.; Bolsa Chica Rd. From Old Bolsa Chica Rd. To Westminster Blvd. Note: This Project Combined With #6387 For Construction. #6387 Status Was Changed From 'Programmed' To 'Combined' In Lp2000. | Construct Raised Median | 1530468.61 | 1277801.89 | 0 | 0 | 2010-03-08 | 2012-12-31 | 1277801.89 | No PE | Authorized | No | Closed | Federal | 0
HSIP5-12-016 | 5 | 5338048 | 12 | Westminster | Orange County | SCAG | OCTA | Rancho Rd. from Westminster Blvd. to 250' S of Spa Dr. | Widen roadway; install two-way left-turn lane; construct catch basin, curb ramps, curb and gutter | 973927.7 | 874953.23 | 2013-09-12 | 0 | 2015-02-11 | 2018-04-04 | 874953.23 | Authorized | Authorized | No | Closed | Federal | 0
HSIP6-12-023 | 6 | 5338049 | 12 | Westminster | Orange County | SCAG | OCTA | Westminster Blvd/Olive St | Upgrade traffic signals | 206469.55 | 188500 | 2014-09-02 | 0 | 2016-08-10 | 2018-07-17 | 188500 | Authorized | Authorized | No | Closed | Federal
HSIP6-12-024 | 6 | 5338051 | 12 | Westminster | Orange County | SCAG | OCTA | Westminster Blvd/University St, Bushard St/Hazard Ave, Bushard St/McFadden Ave, Ward St/Bolsa Ave | Upgrade traffic signals; Install protected left-turn phasing | 626192.05 | 626192.05 | 0 | 0 | 2016-08-10 | 2018-10-15 | 626192.05 | No PE | Authorized | No | Closed | Federal
H8-12-016 | 8 | 5402031 | 12 | Yorba Linda | Orange County | SCAG | OCTA | Fifty-four (54) signalized intersections along various streets. Major streets include Imperial Highway, Bastanchury Road, Yorba Linda Avenue, Orangethorpe Avenue, Rose Drive, Prospect Avenue, and Fairmont Boulevard. | Update existing pedestrian signal heads to be ADA compliant. Update existing pedestrian heads with new countdown sequence modules and push buttons with large button activators. | 92230.5 | 92230.5 | 0 | 0 | 2018-11-15 | 2021-03-16 | 92230.5 | No PE | Authorized | No | Closed | Federal | 0

## Notes
Notes:
1. | The project delivery requirements for local safety programs are as follows: • The PE milestone is met within 9 months; and • The CON milestone is met within 36 months (3 years). Exceptions are: a. The PE milestone does not apply if the project does not need HSIP funding in PE. b. For a project that a consultant is used for the PE work, an additional time of 6 months is allowed for meeting the CON milestone. The additional time is for the agency to advertise and select the consultant for the work of the PE phase.
2. | The project delivery information ("PE Auth Date", "ROW Auth Date", "CON Auth Date", "Closed out Date", etc) in this report is based on the offical approvals. If a request for authorization/allocation has been submitted but not yet approved, the information is not reflected in this report.
3. | Values under "Milestone Status (PE)" and "Milestone Status (CON)"
Value | Meaning
Authorzied | This phase has been authorized.
Due by x/xx/xxxx | The milestone will be due on this date pur the HSIP Delivery Requirements.
Past due (due x/xx/xxxx) | The milestone was due on this past date. This project is considered "delayed".
RFA received x/xx/xxxx | Caltrans received Request for Authorization/Allocation (RFA) package though there is still no official approval. The milestone is considered "met" if the request can be approved within 3 months from this request date.
No PE (or No CON) | HSIP funds will not used in PE phase (or CON phase) so the milestone is not applicable. Example 1: only local funds is used for PE - "No PE"; Example 2: the construction of the project has been combined with another project so no construction authorization is needed under this project - "No CON".
Not tracked | The milestone is not tracked. Example: Caltrans takes the lead in delivering the project. The local agency has no full control over the schedule.
For more information on HSIP Delivery Requirements, please go to the below webpage:
https://dot.ca.gov/programs/local-assistance/fed-and-state-programs/highway-safety-improvement-program/delivery-requirements-status-approved-projects