## LIST_HSIPdelayed
Highway Safety Improvement Program (HSIP) Delivery Status Report for Delayed Projects
Sorted by Caltrans District and Agency, Status as of 1/06/2026
Columns A to L are General Project Information, M to Q are Actual Project Delivery Information, and R to T are Delivery Milestone Status. Please see notes on the other spreadsheet of this file.
(Rows 4,5, and 6 to be deleted for online reports; column u to be deleted) | [11 empty] | (need to delete and double click to expand row to fit)
General Project Information | [11 empty] | Actual Project Delivery Information (Offical approval dates/amount. Not reflected if the request has not yet been approved.) |  |  |  |  | Delivery Milestone Status (see notes on the other spreadsheet)
| 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 33 | 34 | 35 | 23
Unique Project ID | Cycle | Project Number | District | Agency | County | MPO | RTPA | Project Location | Description of Work | Total Cost ($) | HSIP Funds ($) | PE Auth Date | ROW Auth Date | CON Auth Date | Closed out Date | Obligated /Allocated Amt ($) | Milestone Status (PE) | Milestone Status (CON) | Delayed? | Project Phase
H12-01-010 | 12 | 0 | 1 | Humboldt County | Humboldt County | RURAL | HCAG | Three locations: intersection of Oak and F Streets in unincorporated Eureka area, intersection of Kimtu Road and Country Club Drive in Willow Creek area, and school crossing for Loleta School on Loleta Drive. | Install pedestrian crossing enhancements. | 388800 | 349920 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2025) | Due by 3/31/2028 | Yes (PE) | Not Started
H12-01-011 | 12 | 0 | 1 | Humboldt County | Humboldt County | RURAL | HCAG | Various guardrails and bridges throughout Humboldt County. | Repair, replace and upgrade guardrails and end treatments to current safety standards. | 1108300 | 997470 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2025) | Due by 3/31/2028 | Yes (PE) | Not Started
H11-01-014 | 11 | 0 | 1 | Ukiah | Mendocino County | RURAL | Mendocino COG | Various intersections throughout the city: State St at Talmage Rd, E. Gobbi St at S. Orchard Ave, Perkins St at Hospital Dr, Airport Park Blvd at Commerce Dr, and Airport Park Blvd at Talmage Rd. | Install traffic signal hardware, improve signal timing and coordination and provide protected left-turn phases. | 302900 | 151450 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2024) | Due in no more than 4 months | Yes (PE) | Not Started
H12-02-001 | 12 | 5905140 | 2 | Trinity County | Trinity County | RURAL | Trinity LTC | Various locations throughout Trinity County. | Install stripes utilizing weather resistant paint and optical elements to achieve retroreflectivity at night. | 5933600 | 5340240 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2025) | Due by 3/31/2028 | Yes (PE) | Not Started
H12-03-001 | 12 | 0 | 3 | Butte County | Butte County | BCAG | BCAG | Ten road sections: Keefer Rd, Garner Ln, Chico River Rd, Dayton Rd, Durham Dayton Hwy, Ord Ferry Rd, Richvale Hwy, W. Biggs Gridley Rd, E. Gridley Rd, and Larkin Rd. | Upgrade existing 4 inch centerlines and edgelines to 6 inch thermoplastic striping. | 1359900 | 1223910 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2025) | Due by 3/31/2028 | Yes (PE) | Not Started
H12-03-002 | 12 | 0 | 3 | Butte County | Butte County | BCAG | BCAG | Various road sections throughout Butte County. | Peform road safety signing audit (RSSA) and modify signage. | 2606900 | 2346210 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2025) | Due by 3/31/2028 | Yes (PE) | Not Started
H12-03-003 | 12 | 0 | 3 | Butte County | Butte County | BCAG | BCAG | Various throughout Butte County: 10th St (at Feather Ave), Pacific Heights Rd (Oroville Wildlife Area), Pacific Heights Rd (N of Georgia Pacific Way), B St (E of Biggs), Richvale Hwy (E of Richvale), Lower Wyandotte Rd (between Country Oaks Dr). | Upgrade Metal Beam Guardrails (MBGR) to Midwest Guardrail System (MGS). | 500000 | 450000 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2025) | Due by 3/31/2028 | Yes (PE) | Not Started
H12-03-004 | 12 | 0 | 3 | Butte County | Butte County | BCAG | BCAG | Various locations within designated road segments throughout Butte County: Skyway (3), Columbine Rd, Steiffer Rd, Colter Way, Neal Road. | Add high friction surface treatment (HFST). | 600000 | 540000 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2025) | Due by 3/31/2028 | Yes (PE) | Not Started
H12-03-006 | 12 | 0 | 3 | Davis | Yolo County | SACOG | SACOG | On Lake Blvd from Russell Blvd to Arlington Blvd. | Install buffered bike lanes. | 267200 | 240480 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2025) | Due by 3/31/2028 | Yes (PE) | Not Started
H12-03-007 | 12 | 0 | 3 | Davis | Yolo County | SACOG | SACOG | Three locations throughout the city. | Install rectangular rapid flashing Beacons; Install and upgrade high visibility pedestrian crossing markings. | 341900 | 307710 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2025) | Due by 3/31/2028 | Yes (PE) | Not Started
H12-03-012 | 12 | 0 | 3 | Glenn County | Glenn County | RURAL | Glenn LTC | County Road 60 from I-5 to SR 162. | Install centerline, edgelines and rumble strips, and replace striping. | 361800 | 325620 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2025) | Due by 3/31/2028 | Yes (PE) | Not Started
H9-03-017 | 9 | 5002210 | 3 | Sacramento | Sacramento County | SACOG | SACOG | Valley Hi Drive/La Mancha Way between Creek Centre Court and Wyndham Drive. | Install raised median to reduce access conflicts, install traffic signal, and add pedestrian fencing. | 2361900 | 1842940 | 2019-10-11 | 0 | 0 | 0 | 258210 | Authorized | Past due (due 4/30/2025) | Yes (CON) | PE
H9-03-019 | 9 | 5002212 | 3 | Sacramento | Sacramento County | SACOG | SACOG | Intersection of Lampasas Boulevard and Rio Linda Avenue. | Restripe and realign approaches to improve sight distance, install pedestrian refuge island on uncontrolled pedestrian crossing, and install enhanced pedestrian crossings across all legs. | 1286800 | 1158120 | 2019-10-11 | 2023-08-23 | 0 | 0 | 180900 | Authorized | Past due (due 12/31/2024) | Yes (CON) | ROW
H10-04-002 | 10 | 5933166 | 4 | Alameda County | Alameda County | MTC | MTC | Various unsignalized intersections in the unincorporated Alameda County: Meekland Ave. at Medford Ave., Meekland Ave. at Sunset Blvd., Hacienda Ave. at Ricardo Ave., Grove Way at Dolores St., D St. at Twin Creek CT, Ashland Ave. at Bertero Ave., 164th Ave. at Helo Drive, Castro Valley BART Station, and Grove Way at Haviland Ave. | Install Rectangular Rapid Flash Beacons (RRFBs) and various crosswalk enhancements to unsignalized intersections to increase safety for pedestrians. | 529700 | 498980 | 2021-08-27 | 0 | 0 | 0 | 21000 | Authorized | Past due (due 3/31/2024) | Yes (CON) | PE
H10-04-004 | 10 | 5933167 | 4 | Alameda County | Alameda County | MTC | MTC | Three unsignalized intersections with existing marked crosswalks in suburban areas of Alameda County: Redwood Road and Modesto Street, Lake Chabot Road and Congress Way, and Lake Chabot Road and Keith Avenue. | Installation of Pedestrian Hybrid Beacons and raised medians; installation of accompanying signage, ADA Ramps, and pavement striping. | 821000 | 821000 | 2021-08-27 | 0 | 0 | 0 | 130000 | Authorized | Past due (due 9/30/2024) | Yes (CON) | PE
H12-04-002 | 12 | 0 | 4 | Concord | Contra Costa County | MTC | MTC | Various locations. | Install / upgrade signs with new fluorescent sheeting. | 7782500 | 7004250 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2025) | Due by 3/31/2028 | Yes (PE) | Not Started
H12-04-003 | 12 | 0 | 4 | Concord | Contra Costa County | MTC | MTC | Olivera Road & Grant Street-Northwood Drive. | Modify existing traffic signal system to eliminate permissive left-turn operations and improve intersection safety lighting. | 932500 | 839250 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2025) | Due by 3/31/2028 | Yes (PE) | Not Started
H10-04-013 | 10 | 5196043 | 4 | Daly City | San Mateo County | MTC | MTC | The intersection of John Daly Boulevard and Skyline Boulevard in Daly City. | Upgrade intersection signal hardware and pedestrian countdown signal heads, convert traffic signal pole to pole with a mast arm, install raised pavement markers and striping and upgrade ADA curb ramps. | 380200 | 342180 | 2021-06-11 | 0 | 0 | 0 | 48600 | Authorized | Past due (due 2/28/2025) | Yes (CON) | PE
H11-04-038 | 11 | 5126020 | 4 | Pinole | Contra Costa County | MTC | MTC | On San Pablo Avenue at the Third Ave. intersection and Quinan Street intersection. On Pinole Valley Road at the Savage Avenue intersection. | Install pedestrian crossing enhancements at three mid-block crossings on arterial roadways. The enhancements include continental markings, median refuge islands, advanced stop bars and Rectangular Rapid Flash Beacons. | 281133 | 250000 | ? | 0 | 0 | 0 | 30179 | Past due (due 5/31/2024) | Due in no more than 4 months | Yes (PE) | Not Started
H10-04-033 | 10 | 0 | 4 | Pleasanton | Alameda County | MTC | MTC | Various overcrossing on/off ramp locations along Interstate 580 between Hopyard Road, Hacienda Drive, and Santa Rita Road. | Install Rectangular Rapid Flashing Beacons and improve striping and pavement markings. | 321200 | 250000 | 0 | 0 | 0 | 0 | 0 | No PE | Past due (due 9/30/2024) | Yes (CON) | Not Started
H12-04-049 | 12 | 0 | 4 | Sebastopol | Sonoma County | MTC | MTC | Intersection of Covert Lane and Zimpher Drive. | Install pedestrian-activated circular LED rapid flashing beacons, perimeter lighted pedestrian crossing signs, pedestrian pushbuttons, curb extensions, ADA ramps and refuge island, and restripe intersection approach. | 388400 | 349560 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2025) | Due by 3/31/2028 | Yes (PE) | Not Started
H10-05-006 | 10 | 5943079 | 5 | San Benito County | San Benito County | AMBAG | San Benito COG | 21 locations on 10 roads (Panoche Rd, Limekiln Rd, Cienega Rd, Southside Rd, Enterprise Rd, San Juan Hollister Rd, San Juan Canyon Rd, Salinas Rd, Cannon Rd and Prescott Rd). | Replace damaged/destroyed guardrails to current standards. | 1013600 | 1000000 | 2021-06-23 | 0 | 0 | 0 | 170000 | Authorized | Past due (due 9/30/2025) | Yes (CON) | PE
H12-06-005 | 12 | 522337 | 6 | Corcoran | Kings County | KCAG | KCAG | The intersection of Bainum Avenue and Letts Avenue. | Upgrade pedestrian crossing at uncontrolled intersection with enhanced safety features including flashing beacons and curb extensions. | 350000 | 315000 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2025) | Due by 3/31/2028 | Yes (PE) | Not Started
H12-06-010 | 12 | 0 | 6 | Fresno County | Fresno County | FCOG | FCOG | Intersection of Millerton Road and Marina Drive near the unincorporated community of Friant. | Install roundabout. | 3659500 | 2957603 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2025) | Due by 3/31/2028 | Yes (PE) | Not Started
H12-06-012 | 12 | 0 | 6 | Fresno County | Fresno County | FCOG | FCOG | Intersection of Central Ave and Chestnut Ave just south of the unincorporated community of Malaga. | Provide protected left turn phasing and convert signal to mast arm. | 1024000 | 921600 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2025) | Due by 3/31/2028 | Yes (PE) | Not Started
H11-07-001 | 11 | 0 | 7 | Artesia | Los Angeles County | SCAG | MTA | 9 unsignalized intersections and 2 signalized intersections. | Installation of a Rapid Flashing Beacon, and High Visibility Crosswalks. | 232700 | 209430 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2023) | Due in no more than 4 months | Yes (PE) | Not Started
HSIP6-07-005R | 6 | 0 | 7 | Carson | Los Angeles County | SCAG | MTA | Various locations on Figueroa St, Main St, Victoria St, Avalon Blvd, University Dr, and Del Amo Blvd. | Install bike lanes. | 1124600 | 1012140 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2024) | Past due (due 6/30/2025) | Yes (PE & CON) | Not Started
H8-07-005 | 8 | 0 | 7 | Compton | Los Angeles County | SCAG | MTA | The Compton Blvd. corridor between Willowbrook Avenue and Central Avenue. | Install bike lanes and lighting along the corridor, and enhance pedestrian crossings at fifteen (15) intersections. | 1298000 | 1168200 | 0 | 0 | 0 | 0 | 0 | No PE | Past due (due 12/31/2022) | Yes (CON) | Not Started
H8-07-006 | 8 | 0 | 7 | Compton | Los Angeles County | SCAG | MTA | Citywide | Install (20) Pedestrian Countdown Heads. | 249800 | 249800 | 0 | 0 | 0 | 0 | 0 | No PE | Past due (due 9/30/2022) | Yes (CON) | Not Started
H10-07-003 | 10 | 0 | 7 | Covina | Los Angeles County | SCAG | MTA | Various uncontrolled crosswalk locations throughout the City of Covina. | Install inroad warning lights and/or rapid flashing beacons, signage, pavement markings, high visibility crosswalk and curb ramps. | 282500 | 250000 | 0 | 0 | 0 | 0 | 0 | No PE | Past due (due 3/31/2024) | Yes (CON) | Not Started
H12-07-005 | 12 | 0 | 7 | Culver City | Los Angeles County | SCAG | MTA | Green Valley Cir from Sepulveda Blvd to Centinela Ave, and Buckingham Pkwy from Green Valley Cir to Slauson Ave, in the Fox Hills neighborhood. | Install new bikeways (Class II/IV). | 388800 | 349920 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2025) | Due by 3/31/2028 | Yes (PE) | Not Started
H12-07-006 | 12 | 0 | 7 | Culver City | Los Angeles County | SCAG | MTA | three (3) locations on Green Valley Cir between Sepulveda Blvd and Centinela Ave, in the Fox Hills Neighborhood. | Install pedestrian crossing enhancements. | 387900 | 349110 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2025) | Due by 3/31/2028 | Yes (PE) | Not Started
H12-07-012 | 12 | 0 | 7 | El Monte | Los Angeles County | SCAG | MTA | 6 unsignalized intersections along Valley Blvd (El Monte Ave; Shirley Ave; Meeker Ave; La Madera Ave; Allgeyer Ave; Maxson Rd). | Install HAWK signals at 2 locations; install rectangular rapid flashing beacons (RRFBs) at 4 locations; upgrade crosswalks and curb ramps at 6 locations. | 779300 | 701370 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2025) | Due by 3/31/2028 | Yes (PE) | Not Started
H12-07-013 | 12 | 0 | 7 | El Monte | Los Angeles County | SCAG | MTA | 2 signalized intersections at Santa Anita Ave/Lower Azusa Rd & Santa Anita Ave/Kings Row; 1 signalized intersection at Valley Blvd/Gibson Rd. | Provide protected left turn phasing; convert signal to mast arm from pedestal-mounted; and implement leading pedestrian interval (LPI). | 308800 | 277920 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2025) | Due by 3/31/2028 | Yes (PE) | Not Started
H12-07-014 | 12 | 0 | 7 | Glendale | Los Angeles County | SCAG | MTA | 120 Signalized Intersections citywide. | Improve signal hardware; install pedestrian countdown signal heads; install APS; and implement leading pedestrian interval (LPI). | 9168700 | 8251830 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2025) | Due by 3/31/2028 | Yes (PE) | Not Started
H12-07-015 | 12 | 0 | 7 | Glendale | Los Angeles County | SCAG | MTA | Four (4) Unsignalized Intersections: San Fernando Road and Palmer Avenue, Sonora Avenue and Randall Street, Verdugo Road and Glencoe Way, Glendale Avenue and Elk Avenue. | Install flashing beacons at stop controlled intersections; install rectangular rapid flashing beacons (RRFBs), and install Pedestrian Hybrid Beacons. | 1942400 | 1748160 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2025) | Due by 3/31/2028 | Yes (PE) | Not Started
H12-07-017 | 12 | 0 | 7 | Glendora | Los Angeles County | SCAG | MTA | 10 intersections: Route 66 at Grand, Lone Hill, Pasadena, Loraine, Elwood, Glendora, Amelia, and Vermont; Grand Ave at Gladstone; and Glendora Ave at Baseline. | Convert signals from pedestal-mounted to mast arms at 8 intersections; and impove signal hardware at 2 intersections. | 2305100 | 2074590 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2025) | Due by 3/31/2028 | Yes (PE) | Not Started
H10-07-012 | 10 | 5422003 | 7 | La Habra Heights | Los Angeles County | SCAG | MTA | Various Locations Throughout the City | Replace damaged guardrail as well as those not meeting standards, and installation of new guardrails as needed to improve safety. | 880000 | 880000 | 2021-12-13 | 0 | 0 | 0 | 80000 | Authorized | Past due (due 9/30/2024) | Yes (CON) | PE
H10-07-017 | 10 | 5419059 | 7 | Lancaster | Los Angeles County | SCAG | MTA | Five (5) intersections: Avenue K-8 & Challenger Way, Valley Central Way & Central Court, Valley Central Way & Commercial Driveways (550 ft South of Lancaster Blvd), Avenue J & 25th Street East, and Avenue K & 25th Street East. | Install low-cost, quick build roundabouts. | 2129200 | 2129200 | 2021-11-01 | 0 | 0 | 0 | 280000 | Authorized | Past due (due 9/30/2024) | Yes (CON) | PE
H12-07-021 | 12 | 0 | 7 | Long Beach | Los Angeles County | SCAG | MTA | Eight intersections in underserved areas of Long Beach. | Mark high-contrast thermoplastic continental crosswalks in place of faded or outdated parallel bar crosswalks. | 234000 | 210600 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2025) | Due by 3/31/2028 | Yes (PE) | Not Started
H8-07-034 | 8 | 0 | 7 | Norwalk | Los Angeles County | SCAG | MTA | Pioneer Boulevard between 166th Street (South City Limits) and Lakeland Road (North City Limits). | Upgrade signals to provide separate left-turn phasing at eight (8) intersections and provide various safety improvements at adjacent intersections. | 2911000 | 2911000 | 0 | 0 | 0 | 0 | 0 | No PE | Past due (due 12/31/2023) | Yes (CON) | Not Started
H8-07-035 | 8 | 0 | 7 | Norwalk | Los Angeles County | SCAG | MTA | Pioneer Boulevard between 166th Street (South City Limits) and Lakeland Avenue (North City Limits). | Update signal timing and coordinated operations of fifteen (15) signalized intersections, construct a fiber-optic communication network to integrate with the City's Traffic Management Center (TMC). | 1281700 | 640850 | 0 | 0 | 0 | 0 | 0 | No PE | Past due (due 12/31/2023) | Yes (CON) | Not Started
H8-07-036 | 8 | 0 | 7 | Norwalk | Los Angeles County | SCAG | MTA | Norwalk Boulevard from 166th Street (South City Limits) to Rosecrans Avenue; and from Adoree Street to Lakeland Road (North City Limits). | Upgrade signals to provide separate left turn phasing at six (6) intersections and provide various safety improvements at adjacent intersections. | 2294500 | 2294500 | 0 | 0 | 0 | 0 | 0 | No PE | Past due (due 12/31/2023) | Yes (CON) | Not Started
H8-07-037 | 8 | 0 | 7 | Norwalk | Los Angeles County | SCAG | MTA | Norwalk Boulevard from 166th Street (South City Limits) to Rosecrans Avenue; and from Adoree Street to Lakeland Road (North City Limits). | Update signal timing and coordinated operations of eleven (11) signalized intersections, construct a fiber-optic communication network to integrate with the City's Traffic Management Center (TMC). | 1135100 | 567550 | 0 | 0 | 0 | 0 | 0 | No PE | Past due (due 12/31/2023) | Yes (CON) | Not Started
H10-07-025 | 10 | 5129100 | 7 | Oxnard | Ventura County | SCAG | VCTC | Ten intersections including: Gonzales & Lombard, Gonzales & Solar, Rice & Camino Del Sol, Rose & Bard, Saviers & Hueneme, Ventura Rd & Doris, Vineyard & Esplanade, Pleasant Valley & C St, Harbor Blvd & 5th, and Saviers Rd & Laurel St. | Construct traffic signal improvements, including upgrading standards, mast arms, protected-left turn phasing, street lighting, emergency vehicle preemption, and accessible crossing. | 2998600 | 2998600 | 2021-06-28 | 0 | 0 | 0 | 297500 | Authorized | Past due (due 9/30/2024) | Yes (CON) | PE
H12-07-026 | 12 | 0 | 7 | Pico Rivera | Los Angeles County | SCAG | MTA | Eleven (11) signalized Intersections and one roadway segment: Paramount Blvd from Goodbee St to Unser St. | Add left turn phase, convert pedestal mounted signal head to mast arms, and install striping through intersection; for the roadway segment: install raised median. | 2110100 | 1899090 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2025) | Due by 3/31/2028 | Yes (PE) | Not Started
H12-07-029 | 12 | 0 | 7 | San Gabriel | Los Angeles County | SCAG | MTA | Five (5) intersections along the San Gabriel Blvd corridor and the Las Tunas Dr. corridor, including the intersection of San Gabriel and Las Tunas. | Install delineators, reflectors and/or object markers, improve signal hardware, install raised pavement markers and striping , and modify signal phasing for leading pedestrian interval (LPI). | 121100 | 108990 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2025) | Due by 3/31/2028 | Yes (PE) | Not Started
H10-07-036 | 10 | 0 | 7 | South Gate | Los Angeles County | SCAG | MTA | Four uncontrolled crosswalks at Tweedy Boulevard and Virginia Avenue, Tweedy Boulevard and San Antonio Avenue, Tweedy Boulevard and Washington Avenue, Tweedy Boulevard and Walnut Avenue. | Upgrade 4 uncontrolled crosswalks with enhanced crosswalk features including rectangular rapid flashing beacons, high visibility signing and striping, and ADA curb ramps. | 250000 | 250000 | 0 | 0 | 0 | 0 | 0 | No PE | Past due (due 9/30/2024) | Yes (CON) | Not Started
H12-08-005 | 12 | 0 | 8 | Chino | San Bernardino County | SCAG | SANBAG | 10 signalized intersections along a segment of Central Avenue from Riverside Drive to Phillips Boulevard. | Install yellow retroreflective borders on traffic signal back-plates and install new near-side signal heads. | 250500 | 225450 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2025) | Due by 3/31/2028 | Yes (PE) | Not Started
H12-08-013 | 12 | 0 | 8 | Highland | San Bernardino County | SCAG | SANBAG | Thirty-five (35) signalized intersections throughout the city and Church Street at Glenheather Drive/Love Street intersection. | Install a new traffic signal, upgrade signal heads, and install retroreflective signal head backplates. | 1522300 | 1370070 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2025) | Due by 3/31/2028 | Yes (PE) | Not Started
H12-08-021 | 12 | 0 | 8 | Montclair | San Bernardino County | SCAG | SANBAG | Benson Avenue between Arrow Highway and Holt Boulevard. | Implement a road diet, install Class II bike lanes, right and left turn lanes, pedestrian countdown signal heads, and upgrade intersection pavement markings and pedestrian crossing at uncontrolled locations. | 3156900 | 2841210 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2025) | Due by 3/31/2028 | Yes (PE) | Not Started
H10-08-012 | 10 | 0 | 8 | Murrieta | Riverside County | SCAG | RCTC | Various locations citywide. | Install adaptive timing program at all City signalized intersections, including new traffic signal controllers and loops, as well as the required software and hardware at City Hall Traffic Management Center. | 854700 | 422350 | 0 | 0 | 0 | 0 | 0 | No PE | Past due (due 3/31/2025) | Yes (CON) | Not Started
H12-08-029 | 12 | 0 | 8 | Rialto | San Bernardino County | SCAG | SANBAG | 108 signalized intersections citywide. | Install new signal heads and controllers and implement leading pedestrian intervals (LPIs). | 5418000 | 4876200 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2025) | Due by 3/31/2028 | Yes (PE) | Not Started
H10-08-020 | 10 | 0 | 8 | San Jacinto | Riverside County | SCAG | RCTC | San Jacinto Ave. (formerly SR79) between Menlo Avenue and Commonwealth Ave. | Install Pedestrian Hybrid Beacon (PHB) with enhanced pedestrian refuge island mid-block; install sidewalk on west and east side of San Jacinto from Commonwealth to Menlo; install roadway lighting; and install additional signage. | 677100 | 440100 | 0 | 0 | 0 | 0 | 0 | No PE | Past due (due 3/31/2024) | Yes (CON) | Not Started
H12-09-005 | 12 | 0 | 9 | Ridgecrest | Kern County | KCOG | KCOG | Existing bike lanes along the following roadways: Ward Ave, Drummond Ave, Los Flores Ave, Ridgecrest Blvd, Upjohn Ave, Bowman Rd, Mahan St, Downs St, Norma St, China Lake Blvd, French Ave, Sunland St, Gateway Blvd, Richmond Rd, College Heights Blvd. | Upgrade bike lanes. | 1754600 | 1579140 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2025) | Due by 3/31/2028 | Yes (PE) | Not Started
H12-09-007 | 12 | 0 | 9 | Ridgecrest | Kern County | KCOG | KCOG | 14 signalized intersections on Downs Street, Norma Street, Drummond Ave, Bowman Rd, and China Lake Blvd. | Upgrade the signal hardware back-plates with retroreflective border and replace signal heads. | 543500 | 489150 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2025) | Due by 3/31/2028 | Yes (PE) | Not Started
H10-10-003 | 10 | 5241076 | 10 | Ceres | Stanislaus County | STANCOG | Stan COG | 3 unsignalized intersections on Mitchell Ave at Garrison St, Dale Ave, and Kay St. | Install raised medians on approaches, advanced pavement markings, and striping. | 514100 | 462690 | 2022-01-19 | 0 | 0 | 0 | 71190 | Authorized | Past due (due 9/30/2024) | Yes (CON) | PE
H10-10-004 | 10 | 5241077 | 10 | Ceres | Stanislaus County | STANCOG | Stan COG | Two signalized intersections: Fowler Road & Mitchell Road, and East Whitmore Avenue & Moffett Road. | Install raised medians on approaches; provide protected left-turn phasing; upgrade signal hardware on all approaches. | 740400 | 666360 | 2022-01-19 | 0 | 0 | 0 | 118980 | Authorized | Past due (due 9/30/2024) | Yes (CON) | PE
H10-10-010 | 10 | 5059254 | 10 | Modesto | Stanislaus County | STANCOG | Stan COG | The intersections of Standiford Ave. with Longbridge Dr. and Sylvan Ave. with Bridgeford Ln. | Install pedestrian refuge island with directional median openings, Pedestrian Hybrid Beacons and high visibility crosswalks with pedestrian signage. | 965800 | 919000 | 2021-12-22 | 0 | 0 | 0 | 100350 | Authorized | Past due (due 9/30/2024) | Yes (CON) | PE
H10-10-011 | 10 | 5059255 | 10 | Modesto | Stanislaus County | STANCOG | Stan COG | Oakdale Road from Lancey Drive to Celeste Drive. | Install Pedestrian Hybrid Beacon, Leading Pedestrian Intervals, pedestrian signals, blank-out no right turn signals/signage, directional median, high visibility crosswalk, median refuge island, ADA ramps, reconstruct driveway, and coordinate signals. | 1105900 | 1039330 | 2021-12-22 | 0 | 0 | 0 | 147510 | Authorized | Past due (due 9/30/2024) | Yes (CON) | PE
H12-10-003 | 12 | 0 | 10 | San Joaquin County | San Joaquin County | SJCOG | SJCOG | Seventeen (17) signalized intersections throughout unincorporated San Joaquin County. | Replace 203 existing signal heads, install 9 new signal heads on existing poles, and install 1 new signal head on a new pole. | 508900 | 458010 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2025) | Due by 3/31/2028 | Yes (PE) | Not Started
H12-10-005 | 12 | 5929347 | 10 | San Joaquin County | San Joaquin County | SJCOG | SJCOG | Fifteen (15) intersections in unincorporated San Joaquin County. | Install intersection lighting and advance warning flashing beacons. | 5430200 | 4887180 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2025) | Due by 3/31/2028 | Yes (PE) | Not Started
H10-10-018 | 10 | 5008202 | 10 | Stockton | San Joaquin County | SJCOG | SJCOG | Intersections of Madison Street with Willow Street, Vine Street, Rose Street, Magnolia Street, Acacia Street, Poplar Street, and Flora Street. | Install High-visibility crosswalks, pavement markings, ADA ramps, sight triangles and rapid-flashing beacons. | 721600 | 644940 | 2022-08-17 | 0 | 0 | 0 | 115200 | Authorized | Past due (due 12/31/2025) | Yes (CON) | PE
H12-10-011 | 12 | 0 | 10 | Tuolumne County | Tuolumne County | RURAL | TCTC | The non-signalized intersection at Tuolumne Road, Black Oak Road, and Woodhams Carne Road. | Add lighting, improve sight distance for vehicles, and install high-friction surface treatment (HFST) approaching and through the intersection. | 806500 | 725850 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2025) | Due by 3/31/2028 | Yes (PE) | Not Started
H12-10-012 | 12 | 0 | 10 | Tuolumne County | Tuolumne County | RURAL | TCTC | Multiple guardrail locations on Bonds Flat Road, La Grange Road, O'Byrnes Ferry Road, Parrotts Ferry Road, Rawhide Road, Kewin Mill Road, and Longeway Road. | Remove and replace existing guardrail systems with upgraded steel-post Midwest Guardrail System (MGS) guardrails. | 1109400 | 998460 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2025) | Due by 3/31/2028 | Yes (PE) | Not Started
H12-10-013 | 12 | 0 | 10 | Tuolumne County | Tuolumne County | RURAL | TCTC | Tuolumne Road from Mono Way in East Sonora to Tuolumne Road North in Tuolumne City. | Enhance the centerline striping with the addition of recessed retroreflective pavement markers. | 147200 | 132480 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2025) | Due by 3/31/2028 | Yes (PE) | Not Started
H12-11-001 | 12 | 0 | 11 | Chula Vista | San Diego County | SANDAG | SANDAG | Olympic Parkway from Brandywine Avenue to Eastlake Parkway. | Install separated bike lanes, variable speed feedback signs, and high-visibility crosswalks and signage. | 1955900 | 1760310 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2025) | Due by 3/31/2028 | Yes (PE) | Not Started
H10-11-010 | 10 | 0 | 11 | Imperial County | Imperial County | SCAG | ICTC | Correll Rd between Dogwood Dr and Heber Ave; Rio Vista St between San Diego Ave and Haskell Rd; Shore Hawk Ave near intersection with Shore Gem St; and S. Marina Dr at intersection with Sea Palm Ave. | Install Rectangular Rapid Flashing Beacons (RRFBs) near schools. | 158000 | 158000 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2021) | Past due (due 9/30/2024) | Yes (PE & CON) | Not Started
H10-11-017 | 10 | 5957143 | 11 | San Diego County | San Diego County | SANDAG | SANDAG | Various locations along Sunrise Highway (MP 14.5, MP 15.0, MP 15.5, and MP 17.0) in Unincorporated San Diego County. | Upgrade metal beam guardrail and end-treatment. | 1577700 | 1577700 | 2021-10-12 | 0 | 0 | 0 | 328900 | Authorized | Past due (due 10/10/2025) | Yes (CON) | PE
H12-12-003 | 12 | 0 | 12 | Fullerton | Orange County | SCAG | OCTA | Intersections of Orangethorpe Ave at Harbor Blvd, Orangethorpe Ave at Euclid St, Orangethorpe Ave at Brookhurst Rd, Orangethorpe Ave at Magnolia Ave, Harbor Blvd at Commonwealth Ave, and Harbor Blvd at Chapman Ave. | Improve signal hardware and install intersection lighting. Provide protected left turn phase. | 3576000 | 3218400 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2025) | Due by 3/31/2028 | Yes (PE) | Not Started

## Notes
Notes:
1. | The project delivery requirements for local safety programs are as follows: • The PE milestone is met within 9 months; and • The CON milestone is met within 36 months (3 years). Exceptions are: a. The PE milestone does not apply if the project does not need HSIP funding in PE. b. For a project that a consultant is used for the PE work, an additional time of 6 months is allowed for meeting the CON milestone. The additional time is for the agency to advertise and select the consultant for the work of the PE phase.
2. | The project delivery information ("PE Auth Date", "ROW Auth Date", "CON Auth Date", "Closed out Date", etc) in this report is based on the offical approvals. If a request for authorization/allocation has been submitted but not yet approved, the information is not reflected in this report.
3. | Values under "Milestone Status (PE)" and "Milestone Status (CON)"
Value | Meaning
Authorzied | This phase has been authorized.
Due by x/xx/xxxx | The milestone will be due on this date pur the HSIP Delivery Requirements.
Past due (due x/xx/xxxx) | The milestone was due on this past date. This project is considered "delayed".
RFA received x/xx/xxxx | Caltrans received Request for Authorization/Allocation (RFA) package though there is still no official approval. The milestone is considered "met" if the request can be approved within 3 months from this request date.
No PE (or No CON) | HSIP funds will not used in PE phase (or CON phase) so the milestone is not applicable. Example 1: only local funds is used for PE - "No PE"; Example 2: the construction of the project has been combined with another project so no construction authorization is needed under this project - "No CON".
Not tracked | The milestone is not tracked. Example: Caltrans takes the lead in delivering the project. The local agency has no full control over the schedule.
For more information on HSIP Delivery Requirements, please go to the below webpage:
https://dot.ca.gov/programs/local-assistance/fed-and-state-programs/highway-safety-improvement-program/delivery-requirements-status-approved-projects