## LIST_HSIPdelayed
Highway Safety Improvement Program (HSIP) Delivery Status Report for Delayed Projects
Sorted by Caltrans District and Agency, Status as of 04/07/2026
Columns A to L are General Project Information, M to Q are Actual Project Delivery Information, and R to T are Delivery Milestone Status. Please see notes on the other spreadsheet of this file.
(Rows 4,5, and 6 to be deleted for online reports; column u to be deleted) | [11 empty] | (need to delete and double click to expand row to fit)
General Project Information | [11 empty] | Actual Project Delivery Information (Offical approval dates/amount. Not reflected if the request has not yet been approved.) |  |  |  |  | Delivery Milestone Status (see notes on the other spreadsheet)
| 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 33 | 34 | 35 | 23
Unique Project ID | Cycle | Project Number | District | Agency | County | MPO | RTPA | Project Location | Description of Work | Total Cost ($) | HSIP Funds ($) | PE Auth Date | ROW Auth Date | CON Auth Date | Closed out Date | Obligated /Allocated Amt ($) | Milestone Status (PE) | Milestone Status (CON) | Delayed? | Project Phase
H11-01-005 | 11 | 5904198 | 1 | Humboldt County | Humboldt County | RURAL | HCAG | Various guardrails and bridges throughout Humboldt County. | Repair, replace and upgrade guardrails and end treatments to current safety standards. | 1107600 | 996840 | 2023-11-30 | 0 | 0 | 0 | 72000 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE
H11-01-006 | 11 | 5904197 | 1 | Humboldt County | Humboldt County | RURAL | HCAG | Intersection of Country Club Road and The Terrace Road in Willow Creek California. | Install pedestrian activated flashing beacon at crosswalk from The Terrace Road across County Club Road with an advance warning flashing sign on Country Club. | 158400 | 142560 | 2023-11-20 | 0 | 0 | 0 | 10800 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE
H12-01-010 | 12 | 0 | 1 | Humboldt County | Humboldt County | RURAL | HCAG | Three locations: intersection of Oak and F Streets in unincorporated Eureka area, intersection of Kimtu Road and Country Club Drive in Willow Creek area, and school crossing for Loleta School on Loleta Drive. | Install pedestrian crossing enhancements. | 388800 | 349920 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2025) | Due by 3/31/2028 | Yes (PE) | Not Started
H12-01-011 | 12 | 0 | 1 | Humboldt County | Humboldt County | RURAL | HCAG | Various guardrails and bridges throughout Humboldt County. | Repair, replace and upgrade guardrails and end treatments to current safety standards. | 1108300 | 997470 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2025) | Due by 3/31/2028 | Yes (PE) | Not Started
H11-01-008 | 11 | 5914131 | 1 | Lake County | Lake County | RURAL | LC/CAPC | Eight (8) mid-block and non-signalized intersection pedestrian crossings throughout Lake County: Upper Lake (3 locations), Lucerne (1 location), Lower Lake (2 locations) and Middletown (2 locations) | Install solar powered RRFBs and crosswalk signs, install/upgrade pavement markings and advanced signage, install/reconstruct sidewalks, and install no parking signs at select locations. | 1217500 | 1077930 | 2023-07-21 | 0 | 0 | 0 | 189270 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE
H11-01-009 | 11 | 5914132 | 1 | Lake County | Lake County | RURAL | LC/CAPC | Soda Bay Road, Butts Canyon Road, Nice-Lucerne Cutt-off Road, Lakeshore Boulevard, Morgan Valley Road, Sulphur Bank Drive, Bottle Rock Road, Scotts Valley Road, New Long Valley Road, Seigler Canyon Road, and Spruce Grove Road. | Install solar powered dynamic variable speed warning sign assemblies at 22 locations around Lake County. | 342000 | 307800 | 2023-07-26 | 0 | 0 | 0 | 49500 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE
H11-01-013 | 11 | 0 | 1 | Robinson Rancheria | Lake County | RURAL | LC/CAPC | Various locations on Robinson Rancheria, Lake County. | Install new street signs, regulatory, warning and information with new sign posts. Also replace existing guardrail on Acorn Drive and enhance crosswalk on Pomo Way. | 63000 | 56700 | 0 | 0 | 0 | 0 | 0 | No PE | Past due (due 3/31/2026) | Yes (CON) | Not Started
H11-01-014 | 11 | 0 | 1 | Ukiah | Mendocino County | RURAL | Mendocino COG | Various intersections throughout the city: State St at Talmage Rd, E. Gobbi St at S. Orchard Ave, Perkins St at Hospital Dr, Airport Park Blvd at Commerce Dr, and Airport Park Blvd at Talmage Rd. | Install traffic signal hardware, improve signal timing and coordination and provide protected left-turn phases. | 302900 | 151450 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2024) | Past due (due 3/31/2026) | Yes (PE & CON) | Not Started
H11-03-003 | 11 | 5912130 | 3 | Butte County | Butte County | BCAG | BCAG | Various road sections throughout Butte County. | Road Safety Signing Audit (RSSA) Project. Audit existing sign types, locations, retroreflectivity and size per MUTCD, identify missing signs per MUTCD and modify signage accordingly. | 1440500 | 1296450 | 2023-05-02 | 0 | 0 | 0 | 153000 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE
H11-03-006 | 11 | 5925202 | 3 | El Dorado County | El Dorado County | SACOG | El Dorado LTC | Various Locations - Mount Aukum Road MP 0.22, MP 0.72, MP 1.31, and at Middle Fork Cosumnes River; Cameron Park Drive between El Dorado Royale and Oxford; Bass Lake Road at Bass Lake; and Salmon Falls Rd MP 3.72, MP7.15, MP 9.76. | Replace guardrail and end treatment systems at various locations on Mount Aukum Road (E16), Cameron Park Drive, Bass Lake Road, and Salmon Falls Road. | 977900 | 880110 | 2023-11-22 | 0 | 0 | 0 | 117000 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE
H11-03-010 | 11 | 5260002 | 3 | Isleton | Sacramento County | SACOG | SACOG | Various intersections throughout the city: H St/Main St, 2nd St/A St./SR-160, SR-160/H St, and Union St./D St. | Install/upgrade STOP or intersection warning/regulatory signs, upgrade intersection pavement markings, and improve sight distance to intersection. | 109800 | 98820 | 2023-05-31 | 0 | 0 | 0 | 6840 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE
H11-03-011 | 11 | 5260004 | 3 | Isleton | Sacramento County | SACOG | SACOG | Various intersections throughout the city: H St/Main St; 2nd St/A St./SR-160; Union st/D St; and SR-160/C St. | Install pedestrian improvements (crossings, refuge island, and rectangular rapid flashing beacon) at unsignalized intersections. | 267500 | 240750 | 2023-09-18 | 0 | 0 | 0 | 17190 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE
H11-03-012 | 11 | 5089031 | 3 | Lincoln | Placer County | SACOG | Placer TPA | McBean Park Dr/4th St & B St; McBean Park Dr/4th St & D St; D St & 3rd St; and East Ave & 11th St. | High visibility marked mid-block crosswalks; raised median refuge island; rectangular rapid flashing beacon (RRFB); curb ramps; signing/striping enhancements; and sight distance improvements. | 304600 | 274140 | 2023-11-03 | 0 | 0 | 0 | 36000 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE
H11-03-013 | 11 | 0 | 3 | Loomis | Placer County | SACOG | Placer TPA | Various locations in Town. | Three (3) rapid rectangular flashing beacons, one (1) pedestrian activated, Yield to Pedestrian sign, twenty (20) high visibility crosswalks, and five (5) pedestrian curb ramps to accompany RRFB crosswalks. | 209300 | 188370 | 0 | 0 | 0 | 0 | 0 | No PE | Past due (due 3/31/2026) | Yes (CON) | Not Started
H10-03-019 | 10 | 5015036 | 3 | Placerville | El Dorado County | SACOG | El Dorado LTC | US Highway 50, PM 16.7 to PM 18.8 (within the City limits of Placerville). | Enhance pedestrian crossing safety through the use of dynamic warning signs at various state highway and local road at grade pedestrian/school crossings. | 250000 | 250000 | 2021-11-12 | 0 | 0 | 0 | 21500 | Authorized | Past due (due 3/2/2026) | Yes (CON) | PE
H11-03-027 | 11 | 5922126 | 3 | Yolo County | Yolo County | SACOG | SACOG | In Yolo County along County Road (CR) 102 between CR 29(N) and Pole Line Rd (City of Davis Limit). | Widen the shoulders and install centerline rumble strips. | 870600 | 783540 | 2023-10-02 | 0 | 0 | 0 | 108000 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE
H11-04-004 | 11 | 5038029 | 4 | Antioch | Contra Costa County | MTC | MTC | Delta de Anza Trail Xing at James Donlan Boulevard; Delta de Anza Trail Xing at Lone Tree Way; and Canada Valley Trail Xing at Hillcrest Avenue. | Install Hawk Signals at Trail Crossings to enhance Pedestrian and Bicycle Safety. | 920000 | 828000 | 2024-07-01 | 0 | 0 | 0 | 63000 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE
H11-04-006 | 11 | 5135064 | 4 | Concord | Contra Costa County | MTC | MTC | Various locations throughout the City of Concord. | Install new street lighting, upgrade existing street and intersection lighting, install pedestrian countdown signal heads, modify phasing to provide a Leading Pedestrian Interval (LPI), and install three new RRFBs and two HAWK Signals. | 8233300 | 7409970 | 2024-01-09 | 0 | 0 | 0 | 1240290 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE
H10-04-013 | 10 | 5196043 | 4 | Daly City | San Mateo County | MTC | MTC | The intersection of John Daly Boulevard and Skyline Boulevard in Daly City. | Upgrade intersection signal hardware and pedestrian countdown signal heads, convert traffic signal pole to pole with a mast arm, install raised pavement markers and striping and upgrade ADA curb ramps. | 380200 | 342180 | 2021-06-11 | 0 | 0 | 0 | 48600 | Authorized | Past due (due 2/28/2025) | Yes (CON) | PE
H11-04-018 | 11 | 5056024 | 4 | Dixon | Solano County | MTC | MTC | Pedestrian crossing locations at 5th St & E A St and E A St & the Good Neighbor School. | Install RRFBs and other standard crossing treatments including signing, striping and curb enhancements. | 167800 | 151020 | 2024-05-31 | 0 | 0 | 0 | 27000 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE
H10-04-019 | 10 | 5927126 | 4 | Marin County | Marin County | MTC | MTC | Intersection of Pt Reyes Petaluma Rd and Nicasio Valley Rd in Nicasio, County of Marin. | At southbound Pt Reyes Petaluma Rd, add left turn lane and associated roadway widening, asphalt paving and improve intersection traffic safety. | 2017100 | 1815390 | 2021-05-14 | 2023-01-04 | 0 | 0 | 247500 | Authorized | Past due (due 3/30/2026) | Yes (CON) | ROW
H11-04-030 | 11 | 5042064 | 4 | Napa | Napa County | MTC | MTC | Various uncontrolled crossing locations throughout the City of Napa. | Install Rectangular Rapid Flashing Beacons, ADA curb ramps, curb extensions, signage, and striping. | 711000 | 639900 | 2023-12-11 | 0 | 0 | 0 | 68580 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE
H11-04-031 | 11 | 5042065 | 4 | Napa | Napa County | MTC | MTC | 5 locations along the Lincoln Avenue corridor; 5 locations along the Browns Valley Road/First Street corridor. | Install High Friction Surface Treatments. | 516800 | 465120 | 2023-12-11 | 0 | 0 | 0 | 49860 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE
H11-04-033 | 11 | 5921090 | 4 | Napa County | Napa County | MTC | MTC | Intersections of Silverado Trail/Oak Knoll Ave and Silverado Trail/Zinfandel Ln. | Upgrade bike lane striping, incorporate street lighting, install advanced flashing beacons, and install right turn lane. | 1230200 | 1107180 | 2023-10-16 | 0 | 0 | 0 | 177930 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE
H11-04-034 | 11 | 5317019 | 4 | Newark | Alameda County | MTC | MTC | Two unsignalized intersections: Thornton Ave & Magnolia St and Enterprise Dr & Aleppo Dr. | Install Rectangular Rapid Flashing Beacons with accompanying signage, curb cuts and pavement striping. | 192800 | 173520 | 2023-10-16 | 0 | 0 | 0 | 26280 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE
H11-04-038 | 11 | 5126020 | 4 | Pinole | Contra Costa County | MTC | MTC | On San Pablo Avenue at the Third Ave. intersection and Quinan Street intersection. On Pinole Valley Road at the Savage Avenue intersection. | Install pedestrian crossing enhancements at three mid-block crossings on arterial roadways. The enhancements include continental markings, median refuge islands, advanced stop bars and Rectangular Rapid Flash Beacons. | 281133 | 250000 | ? | 0 | 0 | 0 | 30179 | Past due (due 5/31/2024) | Past due (due 3/31/2026) | Yes (PE & CON) | Not Started
H10-04-033 | 10 | 0 | 4 | Pleasanton | Alameda County | MTC | MTC | Various overcrossing on/off ramp locations along Interstate 580 between Hopyard Road, Hacienda Drive, and Santa Rita Road. | Install Rectangular Rapid Flashing Beacons and improve striping and pavement markings. | 321200 | 250000 | 0 | 0 | 0 | 0 | 0 | No PE | Past due (due 9/30/2024) | Yes (CON) | Not Started
H11-04-040 | 11 | 5137060 | 4 | Richmond | Contra Costa County | MTC | MTC | Barrett Avenue from Harbour Way to 24th Street. | Road diet including protected bike lanes, sidewalk widening, high visibility crosswalk enhancements, protected left-turn phasing, advanced stop bars, median refuge islands, and Rectangular Rapid Flashing Beacons (RRFBs). | 1563200 | 1406880 | 2025-01-27 | 0 | 0 | 0 | 251280 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE
H11-04-041 | 11 | 5099018 | 4 | Rio Vista | Solano County | MTC | MTC | Norman Richards Drive from Airport Road to Poppy House Road; Airport Road from Norman Richards Drive to ASTA Minerals Driveway. | Construct Class IV bike facilities on Airport Road and Class II bike facilities on Norman Richards Drive which include new signing, striping, pavement markings and barriers. | 276900 | 249210 | 2023-11-13 | 0 | 0 | 0 | 20700 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE
H11-04-042 | 11 | 5099019 | 4 | Rio Vista | Solano County | MTC | MTC | Three pedestrian crossings: Airport Road and Church Road; Airport Road and Norman Richard Drive; N Front Street and SR-84. | Install RRFBs and other standard crossing treatments including signing, striping and curb enhancements. | 268700 | 241830 | 2023-11-13 | 0 | 0 | 0 | 20430 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE
H11-04-046 | 11 | 5005176 | 4 | San Jose | Santa Clara County | MTC | MTC | Along Ocala Avenue between Everwood Court and Hillmont Avenue. | Construct a raised median island to replace the existing two-way left turn lane. | 501500 | 451350 | 2023-12-18 | 0 | 0 | 0 | 80460 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE
H10-04-039 | 10 | 5937226 | 4 | Santa Clara County | Santa Clara County | MTC | MTC | Foothill Expressway, Lawrence Expressway, and San Tomas Expressway. | Replace existing metal beam guardrail end treatments with modern variants and increase heights to meet current standards. | 999200 | 999200 | 2022-01-27 | 0 | 0 | 0 | 175000 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE
H11-04-058 | 11 | 0 | 4 | Vacaville | Solano County | MTC | MTC | The intersection of N. Orchard Ave and Valencia Lane; and the intersection of East Monte Vista Avenue and West Street. | Implement pedestrian crossing enhancements including high visibility crosswalks, advanced pedestrian warnings and signs, curb ramps, and Rectangular Rapid-Flashing Beacons (RRFBs). | 274700 | 247230 | 0 | 0 | 0 | 0 | 0 | No PE | Past due (due 3/31/2026) | Yes (CON) | Not Started
H11-04-059 | 11 | 0 | 4 | Vacaville | Solano County | MTC | MTC | Segments along Allison Pkwy, Meridian Rd, Orange Dr, Peabody Rd, Ulatis Dr, and Vaca Valley Pkwy. | Remove and replace edge-lines that have faded away or deteriorated. Remove and replace center line striping at various locations. | 272900 | 245610 | 0 | 0 | 0 | 0 | 0 | No PE | Past due (due 3/31/2026) | Yes (CON) | Not Started
H11-05-001 | 11 | 5084024 | 5 | El Paso De Robles | San Luis Obispo County | SLOCOG | SLOCOG | Intersections for bicycle safety improvements: 12th St at Riverside Ave, 16th St at Riverside Ave, and 10th St at Riverside Ave. | Green bike lane upgrades intersection improvement. | 269300 | 242370 | 0 | 0 | 0 | 0 | 0 | No PE | Past due (due 3/31/2026) | Yes (CON) | Not Started
H10-05-006 | 10 | 5943079 | 5 | San Benito County | San Benito County | AMBAG | San Benito COG | 21 locations on 10 roads (Panoche Rd, Limekiln Rd, Cienega Rd, Southside Rd, Enterprise Rd, San Juan Hollister Rd, San Juan Canyon Rd, Salinas Rd, Cannon Rd and Prescott Rd). | Replace damaged/destroyed guardrails to current standards. | 1013600 | 1000000 | 2021-06-23 | 0 | 0 | 0 | 170000 | Authorized | Past due (due 9/30/2025) | Yes (CON) | PE
H11-05-017 | 11 | 5248010 | 5 | Soledad | Monterey County | AMBAG | TAMC | Various locations throughout the City. | Install RRFB devices, beacons, bulb outs, crosswalks, bike boxes, streetlights, pavement markings, lead pedestrian interval timing, signage, construct median refuge islands, bike lane buffers, and roadway reconfiguration (one location). | 863600 | 777240 | 2023-05-15 | 0 | 0 | 0 | 137700 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE
H11-06-010 | 11 | 5143042 | 6 | Dinuba | Tulare County | TCAG | TCAG | 5 Locations within the City of Dinuba: 1) El Monte Way/Palm Drive; 2) N Crawford Avenue/E Saginaw Avenue; 3) W Kern Street/S M Street; 4) El Monte Way/N I Street/Eaton Avenue; and 5) Avenue 416/Road 92. | Install/upgrade pedestrian crossings with enhanced safety features and install median refuge islands on minor road approaches. | 227900 | 205110 | 2023-12-28 | 0 | 0 | 0 | 36000 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE
H11-06-011 | 11 | 5143043 | 6 | Dinuba | Tulare County | TCAG | TCAG | 3 Locations within the City of Dinuba: 1) El Monte Way between N Dickey Avenue and Palm Drive; 2) Crawford Avenue between Davis Drive and E Saginaw Avenue; and 3) S College Avenue between S M Street and Avenue 408. | Install/Upgrade Sidewalk Pathway along roadway segments. | 862100 | 775890 | 2023-12-28 | 0 | 0 | 0 | 117000 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE
H11-06-012 | 11 | 5143041 | 6 | Dinuba | Tulare County | TCAG | TCAG | E. North Way and Hayes Ave, S. College Ave and Academy Way, Euclid Ave and Franklin Way, Monte Vista Dr and West Drive Entrance to Walmart, and E. Tulare St and H St. | Install Rectangular Rapid Flashing Beacon to enhance pedestrian safety. | 249000 | 224100 | 2023-12-29 | 0 | 0 | 0 | 27000 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE
H11-06-013 | 11 | 5224029 | 6 | Firebaugh | Fresno County | FCOG | FCOG | At nine intersections. | Install/upgrade pedestrian crosswalks with high visibility crossings, advanced yield lines, warning signs, curb ramps, and medians with pedestrian refuge islands. | 249300 | 224370 | 2023-10-24 | 0 | 0 | 0 | 23040 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE
H11-06-028 | 11 | 5946213 | 6 | Tulare County | Tulare County | TCAG | TCAG | Various Locations. 8 Locations on 6 roads (Road 192, Road 124, Road 196, Road 152, Avenue 368, and Drive 60). | Upgrade existing, damaged, outdated, and destroyed guardrail to current standards. | 1111100 | 999990 | 2023-08-01 | 2024-09-05 | 0 | 0 | 198450 | Authorized | Past due (due 3/31/2026) | Yes (CON) | ROW
HSIP6-07-005R | 6 | 0 | 7 | Carson | Los Angeles County | SCAG | MTA | Various locations on Figueroa St, Main St, Victoria St, Avalon Blvd, University Dr, and Del Amo Blvd. | Install bike lanes. | 1124600 | 1012140 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2024) | Past due (due 6/30/2025) | Yes (PE & CON) | Not Started
H8-07-005 | 8 | 0 | 7 | Compton | Los Angeles County | SCAG | MTA | The Compton Blvd. corridor between Willowbrook Avenue and Central Avenue. | Install bike lanes and lighting along the corridor, and enhance pedestrian crossings at fifteen (15) intersections. | 1298000 | 1168200 | 0 | 0 | 0 | 0 | 0 | No PE | Past due (due 12/31/2022) | Yes (CON) | Not Started
H8-07-006 | 8 | 0 | 7 | Compton | Los Angeles County | SCAG | MTA | Citywide | Install (20) Pedestrian Countdown Heads. | 249800 | 249800 | 0 | 0 | 0 | 0 | 0 | No PE | Past due (due 9/30/2022) | Yes (CON) | Not Started
HSIP7-07-005 | 7 | 0 | 7 | Compton | Los Angeles County | SCAG | MTA | Compton Boulevard, from Willowbrook Avenue to eastern City limits. | Installation of raised medians and Class II bicycle lanes | 1928400 | 1691098 | 0 | 0 | 0 | 0 | 0 | No PE | Past due (due 12/31/2022) | Yes (CON) | Not Started
H10-07-003 | 10 | 0 | 7 | Covina | Los Angeles County | SCAG | MTA | Various uncontrolled crosswalk locations throughout the City of Covina. | Install inroad warning lights and/or rapid flashing beacons, signage, pavement markings, high visibility crosswalk and curb ramps. | 282500 | 250000 | 0 | 0 | 0 | 0 | 0 | No PE | Past due (due 3/31/2024) | Yes (CON) | Not Started
H11-07-007 | 11 | 5369016 | 7 | Cudahy | Los Angeles County | SCAG | MTA | 13 signalized intersections citywide. | Install retro-reflective backplates, other signal improvements, and implement Leading Pedestrian Interval (LPI) timing at all signals Citywide. Re-stripe crosswalks to implement high-visibility crosswalks at all signalized intersections. Furnish and install bulb outs. | 1353100 | 1217790 | 2023-10-11 | 0 | 0 | 0 | 180000 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE
H12-07-005 | 12 | 0 | 7 | Culver City | Los Angeles County | SCAG | MTA | Green Valley Cir from Sepulveda Blvd to Centinela Ave, and Buckingham Pkwy from Green Valley Cir to Slauson Ave, in the Fox Hills neighborhood. | Install new bikeways (Class II/IV). | 388800 | 349920 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2025) | Due by 3/31/2028 | Yes (PE) | Not Started
H12-07-006 | 12 | 0 | 7 | Culver City | Los Angeles County | SCAG | MTA | three (3) locations on Green Valley Cir between Sepulveda Blvd and Centinela Ave, in the Fox Hills Neighborhood. | Install pedestrian crossing enhancements. | 387900 | 349110 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2025) | Due by 3/31/2028 | Yes (PE) | Not Started
H11-07-010 | 11 | 5210036 | 7 | El Monte | Los Angeles County | SCAG | MTA | 4 signalized intersections along Tyler Ave and Valley Blvd. | Upgrade signal hardware and pedestrian countdown heads at three locations; convert signal to mast arm and install pedestrian countdown heads at one location. | 362400 | 326160 | 2024-05-16 | 0 | 0 | 0 | 58230 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE
H11-07-011 | 11 | 5210035 | 7 | El Monte | Los Angeles County | SCAG | MTA | Santa Anita Avenue between Valley Boulevard and Tyler Avenue. | Install Class II bike lane striping and signs. | 277000 | 249300 | 2024-05-16 | 0 | 0 | 0 | 44550 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE
H11-07-012 | 11 | 5144082 | 7 | Glendale | Los Angeles County | SCAG | MTA | Chevy Chase Dr & San Fernando Rd, Central Ave & Los Feliz Rd, Colorado St & Glendale Ave, Broadway & Brand Blvd, Verdugo Rd & Broadview Dr, San Fernando Rd & Los Feliz Rd, Chevy Chase Dr & Glendale Ave, Foothill Blvd & New York Ave | Proposed project would provide protected left turn phases, raised median on approaches and modify signal phasing to implement a Leading Pedestrian Interval (LPI) at eight signalized intersections. | 1127700 | 1014930 | 0 | 0 | 0 | 0 | 0 | No PE | Past due (due 3/31/2026) | Yes (CON) | Not Started
H11-07-013 | 11 | 5144083 | 7 | Glendale | Los Angeles County | SCAG | MTA | Various locations throughout the City of Glendale. | Install/upgrade signs with new fluorescent sheeting (regulatory or warning). | 4121200 | 3709080 | 2023-12-27 | 0 | 0 | 0 | 0 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE
H11-07-014 | 11 | 5144084 | 7 | Glendale | Los Angeles County | SCAG | MTA | S Glendale Ave: E Los Feliz-E Broadway, Verdugo Rd: E Colorado-N Glendale, W Colorado St: S Pacific-S Columbus, Montrose Ave: Pennsylvania-La Crescenta, Lexington Dr: N Pacific-N Verdugo, Western Ave: W Glenoaks -S Victory | Proposed projects would install edge-lines, centerlines, rectangular rapid flashing beacons and install/ upgrade pedestrian crossings (with enhanced safety features) along six roadway segments. | 1514300 | 1362870 | 0 | 0 | 0 | 0 | 0 | No PE | Past due (due 3/31/2026) | Yes (CON) | Not Started
H11-07-015 | 11 | 0 | 7 | Glendale | Los Angeles County | SCAG | MTA | Three roadway segments throughout city: (1) San Fernando Rd: W California Ave to Fierro St, (2) W Glenoaks Blvd: Thompson Ave to Concord St., and (3) Montrose Ave: Pennsylvania Ave to Ramsdell Ave. | Install dynamic/variable speed warning signs, and install/upgrade pedestrian crossing (with enhanced safety features). | 277700 | 249930 | 0 | 0 | 0 | 0 | 0 | No PE | Past due (due 3/31/2026) | Yes (CON) | Not Started
H12-07-017 | 12 | 0 | 7 | Glendora | Los Angeles County | SCAG | MTA | 10 intersections: Route 66 at Grand, Lone Hill, Pasadena, Loraine, Elwood, Glendora, Amelia, and Vermont; Grand Ave at Gladstone; and Glendora Ave at Baseline. | Convert signals from pedestal-mounted to mast arms at 8 intersections; and impove signal hardware at 2 intersections. | 2305100 | 2074590 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2025) | Due by 3/31/2028 | Yes (PE) | Not Started
H10-07-012 | 10 | 5422003 | 7 | La Habra Heights | Los Angeles County | SCAG | MTA | Various Locations Throughout the City | Replace damaged guardrail as well as those not meeting standards, and installation of new guardrails as needed to improve safety. | 880000 | 880000 | 2021-12-13 | 0 | 0 | 0 | 80000 | Authorized | Past due (due 9/30/2024) | Yes (CON) | PE
H10-07-015 | 10 | 5419061 | 7 | Lancaster | Los Angeles County | SCAG | MTA | 28 signalized intersections within the city limits of Lancaster. | Systemically upgrade vehicle detection to include advanced dilemma-zone detection, bike recognition and detection, as well as upgrading existing signal equipment. | 2908000 | 2908000 | 2021-11-30 | 0 | 0 | 0 | 335600 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE
H10-07-017 | 10 | 5419059 | 7 | Lancaster | Los Angeles County | SCAG | MTA | Five (5) intersections: Avenue K-8 & Challenger Way, Valley Central Way & Central Court, Valley Central Way & Commercial Driveways (550 ft South of Lancaster Blvd), Avenue J & 25th Street East, and Avenue K & 25th Street East. | Install low-cost, quick build roundabouts. | 2129200 | 2129200 | 2021-11-01 | 0 | 0 | 0 | 280000 | Authorized | Past due (due 9/30/2024) | Yes (CON) | PE
H12-07-021 | 12 | 0 | 7 | Long Beach | Los Angeles County | SCAG | MTA | Eight intersections in underserved areas of Long Beach. | Mark high-contrast thermoplastic continental crosswalks in place of faded or outdated parallel bar crosswalks. | 234000 | 210600 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2025) | Due by 3/31/2028 | Yes (PE) | Not Started
H8-07-034 | 8 | 0 | 7 | Norwalk | Los Angeles County | SCAG | MTA | Pioneer Boulevard between 166th Street (South City Limits) and Lakeland Road (North City Limits). | Upgrade signals to provide separate left-turn phasing at eight (8) intersections and provide various safety improvements at adjacent intersections. | 2911000 | 2911000 | 0 | 0 | 0 | 0 | 0 | No PE | Past due (due 12/31/2023) | Yes (CON) | Not Started
H8-07-035 | 8 | 0 | 7 | Norwalk | Los Angeles County | SCAG | MTA | Pioneer Boulevard between 166th Street (South City Limits) and Lakeland Avenue (North City Limits). | Update signal timing and coordinated operations of fifteen (15) signalized intersections, construct a fiber-optic communication network to integrate with the City's Traffic Management Center (TMC). | 1281700 | 640850 | 0 | 0 | 0 | 0 | 0 | No PE | Past due (due 12/31/2023) | Yes (CON) | Not Started
H8-07-036 | 8 | 0 | 7 | Norwalk | Los Angeles County | SCAG | MTA | Norwalk Boulevard from 166th Street (South City Limits) to Rosecrans Avenue; and from Adoree Street to Lakeland Road (North City Limits). | Upgrade signals to provide separate left turn phasing at six (6) intersections and provide various safety improvements at adjacent intersections. | 2294500 | 2294500 | 0 | 0 | 0 | 0 | 0 | No PE | Past due (due 12/31/2023) | Yes (CON) | Not Started
H8-07-037 | 8 | 0 | 7 | Norwalk | Los Angeles County | SCAG | MTA | Norwalk Boulevard from 166th Street (South City Limits) to Rosecrans Avenue; and from Adoree Street to Lakeland Road (North City Limits). | Update signal timing and coordinated operations of eleven (11) signalized intersections, construct a fiber-optic communication network to integrate with the City's Traffic Management Center (TMC). | 1135100 | 567550 | 0 | 0 | 0 | 0 | 0 | No PE | Past due (due 12/31/2023) | Yes (CON) | Not Started
H10-07-025 | 10 | 5129100 | 7 | Oxnard | Ventura County | SCAG | VCTC | Ten intersections including: Gonzales & Lombard, Gonzales & Solar, Rice & Camino Del Sol, Rose & Bard, Saviers & Hueneme, Ventura Rd & Doris, Vineyard & Esplanade, Pleasant Valley & C St, Harbor Blvd & 5th, and Saviers Rd & Laurel St. | Construct traffic signal improvements, including upgrading standards, mast arms, protected-left turn phasing, street lighting, emergency vehicle preemption, and accessible crossing. | 2998600 | 2998600 | 2021-06-28 | 0 | 0 | 0 | 297500 | Authorized | Past due (due 9/30/2024) | Yes (CON) | PE
H11-07-027 | 11 | 5129110 | 7 | Oxnard | Ventura County | SCAG | VCTC | Intersections and roadway on Ventura Road from Second Street to Wooley Road. | Install class II bike lanes (with green conflict areas), leading pedestrian intervals, additional signal heads, retroreflective backplates, advance stop bars, high visibility crosswalks, and bike and pedestrian warning signs. | 821100 | 738990 | 2023-12-04 | 0 | 0 | 0 | 130500 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE
H11-07-028 | 11 | 5129111 | 7 | Oxnard | Ventura County | SCAG | VCTC | Intersections and roadway on Bard Road from Saviers Road to Pleasant Valley Road. | Green bike conflict striping, leading pedestrian intervals, retroreflective backplates, advance stop bars, high visibility crosswalks, advance warning flashing beacons, upgraded signs, and movement restricting median improvements. | 775700 | 698130 | 2023-12-04 | 0 | 0 | 0 | 121500 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE
H11-07-029 | 11 | 5378051 | 7 | Palmdale | Los Angeles County | SCAG | MTA | Various locations throughout the City of Palmdale. | Conduct a City-wide signal modernization and pedestrian infrastructure replacement. Replace signal-head displays with current standards and replace pedestrian crosswalks and pedestrian buttons at crosswalks. | 6508800 | 5857920 | 2024-04-12 | 0 | 0 | 0 | 450000 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE
H11-07-033 | 11 | 5064098 | 7 | Pasadena | Los Angeles County | SCAG | MTA | Green St at Michigan Ave and Green St at Chester Ave intersections. | Installation of rapid rectangular flashing beacon with updated curb ramps, signage, lighting and striping. | 276800 | 249120 | 2023-09-12 | 0 | 0 | 0 | 18000 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE
H11-07-034 | 11 | 5064099 | 7 | Pasadena | Los Angeles County | SCAG | MTA | Fair Oaks ave, Walnut St, Lake Ave, Glenarm St, California Blvd, and Washington Blvd corridors and selected intersections. | Installation of reflective backplate and near side signal heads. | 441900 | 397710 | 2023-09-12 | 0 | 0 | 0 | 37800 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE
H11-07-036 | 11 | 5351045 | 7 | Pico Rivera | Los Angeles County | SCAG | MTA | 47 Signalized Intersections along Multiple Roadway Segments. | Improve signal hardware, install pedestrian countdown signal heads, and install advance stop bar before crosswalk (Bicycle Box). | 2130800 | 1917720 | 2023-11-17 | 0 | 0 | 0 | 324000 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE
H10-07-031 | 10 | 5413018 | 7 | Rancho Palos Verdes | Los Angeles County | SCAG | MTA | Palos Verdes Drive East between Palos Verdes Drive South and Palos Verdes Drive North. | Upgrade approx. 4,400 linear feet of guardrails. | 1000000 | 1000000 | 2024-12-16 | 0 | 0 | 0 | 88100 | Authorized | Past due (due 3/30/2026) | Yes (CON) | PE
H11-07-040 | 11 | 5349016 | 7 | Rolling Hills Estates | Los Angeles County | SCAG | MTA | 7 guardrail segments: 2 sections on Silver Spur Road; 2 sections on Hawthorne Boulevard; 1 section on Ranchview Road; and 2 sections on Palos Verdes Drive East. | Guardrail and end treatment upgrades. | 1111400 | 1000000 | 2023-12-12 | 0 | 0 | 0 | 176153 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE
H12-07-029 | 12 | 0 | 7 | San Gabriel | Los Angeles County | SCAG | MTA | Five (5) intersections along the San Gabriel Blvd corridor and the Las Tunas Dr. corridor, including the intersection of San Gabriel and Las Tunas. | Install delineators, reflectors and/or object markers, improve signal hardware, install raised pavement markers and striping , and modify signal phasing for leading pedestrian interval (LPI). | 121100 | 108990 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2025) | Due by 3/31/2028 | Yes (PE) | Not Started
H10-07-036 | 10 | 0 | 7 | South Gate | Los Angeles County | SCAG | MTA | Four uncontrolled crosswalks at Tweedy Boulevard and Virginia Avenue, Tweedy Boulevard and San Antonio Avenue, Tweedy Boulevard and Washington Avenue, Tweedy Boulevard and Walnut Avenue. | Upgrade 4 uncontrolled crosswalks with enhanced crosswalk features including rectangular rapid flashing beacons, high visibility signing and striping, and ADA curb ramps. | 250000 | 250000 | 0 | 0 | 0 | 0 | 0 | No PE | Past due (due 9/30/2024) | Yes (CON) | Not Started
H11-07-045 | 11 | 5257043 | 7 | South Gate | Los Angeles County | SCAG | MTA | Atlantic Ave & Southern Pl, Firestone Blvd & Alexander Ave, Firestone Blvd & Garfield Ave, Firestone Blvd & Santa Fe Ave, Firestone Blvd & San Juan Ave, Garfield Ave & El Paseo, and Garfield Ave & Garfield Pl (a total of 7 intersections). | Install safety countermeasures including upgrades to signal hardware, leading pedestrian intervals, raised median to restrict left turns, protected left turn phases, and high visibility crosswalks with advance limit line. | 1059000 | 953100 | 2023-11-16 | 0 | 0 | 0 | 153000 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE
H11-08-001 | 11 | 5408009 | 8 | Adelanto | San Bernardino County | SCAG | SANBAG | Intersections of Bellflower St/Victor St, Verbena Rd/Victor St, Aster Rd/Victor St, Rancho Rd/Adelanto Rd, Air Expressway/Aster Rd, and Air Expressway /Raccoon Ave. | Install all-way stop control including the installation of stop signs, stop ahead signs and legends, crosswalks, and the construction and reconstruction of ADA ramps. | 365900 | 329310 | 2025-07-17 | 0 | 0 | 0 | 40500 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE
H11-08-002 | 11 | 5214016 | 8 | Banning | Riverside County | SCAG | RCTC | 17 signalized intersections throughout the City of Banning. | Upgrade traffic signal hardware including LED safety lighting, retro-reflective backplates, countdown pedestrian signal heads, ADA-compliant pedestrian push buttons, and emergency vehicle preemption systems. | 433900 | 390510 | 2023-09-07 | 0 | 0 | 0 | 54000 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE
H11-08-003 | 11 | 5214017 | 8 | Banning | Riverside County | SCAG | RCTC | 19 intersections throughout the City of Banning. | Install curb extensions, ADA curb ramps, RRFBs, high visibility crosswalks, and advanced warning signs and pavement markings. | 585000 | 526500 | 2023-09-07 | 0 | 0 | 0 | 76500 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE
H11-08-004 | 11 | 5214018 | 8 | Banning | Riverside County | SCAG | RCTC | The intersection of Wilson St with 12th St. | Install curb extensions, ADA curb ramps, median refuge island, RRFB, high visibility crosswalks, and advanced warning signs and pavement markings. | 277000 | 249300 | 2023-09-07 | 0 | 0 | 0 | 44460 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE
H11-08-011 | 11 | 5384019 | 8 | Desert Hot Springs | Riverside County | SCAG | RCTC | 17 intersections (10 along Palm Dr, Hacienda Av & Mountain View Rd, 5 intersections along Pierson Bl, and Mission Lakes Bl & Indian Canyon Dr). | Install retroreflective signal back-plates and install signal phasing to implement Leading Pedestrian Interval system (all 17 intersections). Install high visibility thermoplastic crosswalks (8 intersections). | 623500 | 561150 | 2023-08-03 | 0 | 0 | 0 | 64170 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE
H11-08-012 | 11 | 5307037 | 8 | Fontana | San Bernardino County | SCAG | SANBAG | 118 signalized intersections throughout the City of Fontana. | Install traffic management software to improve safety by adding the ability to synchronize signals along major corridors throughout the City. | 1331800 | 665900 | 2023-08-23 | 0 | 0 | 0 | 19050 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE
H11-08-013 | 11 | 5449043 | 8 | Highland | San Bernardino County | SCAG | SANBAG | 5th Street from Del Rosa Drive to Victoria Avenue; Greenspot Road from SR210 to Greenspot Road Bridge; and Orange Street from Boulder Avenue to south City Limits. | Upgrade approximately 7 miles of roadway edge-line and centerline stripes to replace existing faded and worn roadway line delineation along the City of Highland's arterial roadway segments. | 155000 | 139500 | 2024-05-08 | 0 | 0 | 0 | 25650 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE
H12-08-013 | 12 | 0 | 8 | Highland | San Bernardino County | SCAG | SANBAG | Thirty-five (35) signalized intersections throughout the city and Church Street at Glenheather Drive/Love Street intersection. | Install a new traffic signal, upgrade signal heads, and install retroreflective signal head backplates. | 1522300 | 1370070 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2025) | Due by 3/31/2028 | Yes (PE) | Not Started
H11-08-017 | 11 | 5326027 | 8 | Montclair | San Bernardino County | SCAG | SANBAG | Adjacent to Montera Elementary School at multiple locations along Monte Vista Avenue, Bandera Street, Helena Avenue, Kingsley Street, Fremont Avenue, and Canoga Street. | Enhance pedestrian safety by installing edgelines and high visibility and/or ladder crosswalks, constructing ADA-compliant curb ramps, adding pedestrian signage, solar-powered speed feedback signage, and other safety measures. | 277700 | 249930 | 2024-06-18 | 0 | 0 | 0 | 27000 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE
H11-08-018 | 11 | 5326026 | 8 | Montclair | San Bernardino County | SCAG | SANBAG | 1.95 miles of Orchard Street at 10 signalized and non-signalized intersections: Mills Ave., Pradera Ave., Sunset Park entrances, Ramona Ave., Camulos Ave., Tudor Ave., Monte Vista Ave., Fremont Ave., Central Ave., and Benson Ave. | Install raised pavement markers and striping; Upgrade existing stop signs to flashing LED light stop signs; Install a HAWK system; Install/Upgrade pedestrian crossings at uncontrolled locations. | 402300 | 362070 | 2024-06-18 | 0 | 0 | 0 | 40500 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE
H10-08-012 | 10 | 0 | 8 | Murrieta | Riverside County | SCAG | RCTC | Various locations citywide. | Install adaptive timing program at all City signalized intersections, including new traffic signal controllers and loops, as well as the required software and hardware at City Hall Traffic Management Center. | 854700 | 422350 | 0 | 0 | 0 | 0 | 0 | No PE | Past due (due 3/31/2025) | Yes (CON) | Not Started
H11-08-023 | 11 | 5282051 | 8 | Palm Springs | Riverside County | SCAG | RCTC | Various signalized intersections in the City of Palm Springs. | Installing LED pedestrian countdown signal heads, intersection lighting, upgrading signal equipment, and installing Leading Pedestrian Interval (LPI). | 2335600 | 2102040 | 2023-11-27 | 0 | 0 | 0 | 270000 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE
H11-08-026 | 11 | 5083029 | 8 | Redlands | San Bernardino County | SCAG | SANBAG | The intersection of San Bernardino Avenue and Church Street. | Install traffic signal. | 653600 | 588240 | 2023-10-30 | 0 | 0 | 0 | 103500 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE
H11-08-027 | 11 | 5083028 | 8 | Redlands | San Bernardino County | SCAG | SANBAG | Various signalized intersections citywide. | Install larger signal heads and back-plate with reflective border. | 245000 | 220500 | 2023-10-25 | 0 | 0 | 0 | 38700 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE
H12-08-029 | 12 | 5205036 | 8 | Rialto | San Bernardino County | SCAG | SANBAG | 108 signalized intersections citywide. | Install new signal heads and controllers and implement leading pedestrian intervals (LPIs). | 5418000 | 4876200 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2025) | Due by 3/31/2028 | Yes (PE) | Not Started
H11-08-031 | 11 | 5954196 | 8 | San Bernardino County | San Bernardino County | SCAG | SANBAG | Nine rural roadway segments (Arrowhead Lake Road, Rock Springs Road/Roundup Way, Sheep Creek Road, Wilson Ranch Road, Santa Fe Avenue, Pioneertown Road, Pipes Canyon Road, Camp Rock Road and Parker Dam Road). | Install centerline and edgeline rumble stripes with raised pavement markers. | 5983300 | 4994830 | 2023-09-18 | 0 | 0 | 0 | 750600 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE
H11-08-032 | 11 | 5954197 | 8 | San Bernardino County | San Bernardino County | SCAG | SANBAG | 50 rural intersections along high-speed roadways with no intersection lighting. | Install stop signs and flashing beacons in advance of the stop signs, W4-4P 'Cross Traffic Does Not Stop' signs, and transverse rumble strips on County-maintained minor stop-controlled approaches. | 1392000 | 1252800 | 2023-08-11 | 0 | 0 | 0 | 164700 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE
H11-08-033 | 11 | 5954198 | 8 | San Bernardino County | San Bernardino County | SCAG | SANBAG | Cajon Boulevard from Cleghorn Road to Kenwood Avenue. | Install centerline and edgeline rumble stripes with raised pavement markers. Install a 2ft painted median, with flexible delineators where passing is not permitted. Install flashing beacon on "Stop Ahead" sign prior to Kenwood Avenue. | 1314500 | 1183050 | 2023-08-18 | 0 | 0 | 0 | 166500 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE
H11-08-034 | 11 | 5954199 | 8 | San Bernardino County | San Bernardino County | SCAG | SANBAG | Oak Glen Road east of the City of Yucaipa, generally between Chagall Road and Pisgah Peak-Oak Glen Road; Lone Pine Canyon Road, between Heath Creek Drive and SR-138; Lytle Creek Road between 1500 feet west of Sycamore Drive and Glen Helen Parkway. | Install centerline and edgeline rumble stripes with raised pavement markers. Install chevron signs on curved roadway segments. | 2854800 | 2569320 | 2023-08-18 | 0 | 0 | 0 | 360000 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE
H10-08-020 | 10 | 0 | 8 | San Jacinto | Riverside County | SCAG | RCTC | San Jacinto Ave. (formerly SR79) between Menlo Avenue and Commonwealth Ave. | Install Pedestrian Hybrid Beacon (PHB) with enhanced pedestrian refuge island mid-block; install sidewalk on west and east side of San Jacinto from Commonwealth to Menlo; install roadway lighting; and install additional signage. | 677100 | 440100 | 0 | 0 | 0 | 0 | 0 | No PE | Past due (due 3/31/2024) | Yes (CON) | Not Started
H11-08-043 | 11 | 0 | 8 | Wildomar | Riverside County | SCAG | RCTC | Mission Trail from Malaga Road to Corydon Street, and Corydon Street from Grand Avenue to Mission Trail. | Install pedestrian countdown signal heads, pedestrian crosswalk enhancements, ADA Systems at signalized intersections, high visibility crosswalks, and pedestrian curb ramps. | 176100 | 158490 | 0 | 0 | 0 | 0 | 0 | No PE | Past due (due 3/31/2026) | Yes (CON) | Not Started
H12-09-005 | 12 | 0 | 9 | Ridgecrest | Kern County | KCOG | KCOG | Existing bike lanes along the following roadways: Ward Ave, Drummond Ave, Los Flores Ave, Ridgecrest Blvd, Upjohn Ave, Bowman Rd, Mahan St, Downs St, Norma St, China Lake Blvd, French Ave, Sunland St, Gateway Blvd, Richmond Rd, College Heights Blvd. | Upgrade bike lanes. | 1754600 | 1579140 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2025) | Due by 3/31/2028 | Yes (PE) | Not Started
H12-09-007 | 12 | 0 | 9 | Ridgecrest | Kern County | KCOG | KCOG | 14 signalized intersections on Downs Street, Norma Street, Drummond Ave, Bowman Rd, and China Lake Blvd. | Upgrade the signal hardware back-plates with retroreflective border and replace signal heads. | 543500 | 489150 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2025) | Due by 3/31/2028 | Yes (PE) | Not Started
H10-10-003 | 10 | 5241076 | 10 | Ceres | Stanislaus County | STANCOG | Stan COG | 3 unsignalized intersections on Mitchell Ave at Garrison St, Dale Ave, and Kay St. | Install raised medians on approaches, advanced pavement markings, and striping. | 514100 | 462690 | 2022-01-19 | 0 | 0 | 0 | 71190 | Authorized | Past due (due 9/30/2024) | Yes (CON) | PE
H10-10-004 | 10 | 5241077 | 10 | Ceres | Stanislaus County | STANCOG | Stan COG | Two signalized intersections: Fowler Road & Mitchell Road, and East Whitmore Avenue & Moffett Road. | Install raised medians on approaches; provide protected left-turn phasing; upgrade signal hardware on all approaches. | 740400 | 666360 | 2022-01-19 | 0 | 0 | 0 | 118980 | Authorized | Past due (due 9/30/2024) | Yes (CON) | PE
H11-10-001 | 11 | 5939142 | 10 | Merced County | Merced County | MCAG | MCAG | Streets and roadways south of State Route 140 throughout the County of Merced. | Inventory and replacement of regularity and warning signs. | 1400000 | 1260000 | 2023-07-31 | 0 | 0 | 0 | 225000 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE
H10-10-010 | 10 | 5059254 | 10 | Modesto | Stanislaus County | STANCOG | Stan COG | The intersections of Standiford Ave. with Longbridge Dr. and Sylvan Ave. with Bridgeford Ln. | Install pedestrian refuge island with directional median openings, Pedestrian Hybrid Beacons and high visibility crosswalks with pedestrian signage. | 965800 | 919000 | 2021-12-22 | 0 | 0 | 0 | 100350 | Authorized | Past due (due 9/30/2024) | Yes (CON) | PE
H10-10-011 | 10 | 5059255 | 10 | Modesto | Stanislaus County | STANCOG | Stan COG | Oakdale Road from Lancey Drive to Celeste Drive. | Install Pedestrian Hybrid Beacon, Leading Pedestrian Intervals, pedestrian signals, blank-out no right turn signals/signage, directional median, high visibility crosswalk, median refuge island, ADA ramps, reconstruct driveway, and coordinate signals. | 1105900 | 1039330 | 2021-12-22 | 0 | 0 | 0 | 147510 | Authorized | Past due (due 9/30/2024) | Yes (CON) | PE
H11-10-002 | 11 | 5059267 | 10 | Modesto | Stanislaus County | STANCOG | Stan COG | Tokay Ave at La Cienega Dr, E Rumble Rd at Hampshire Ln, Robertson Rd at Hancock St, and Conant Ave at Budd St. | Install raised crosswalks. | 248200 | 223380 | 2025-06-26 | 0 | 0 | 0 | 39600 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE
H11-10-006 | 11 | 5244042 | 10 | Patterson | Stanislaus County | STANCOG | Stan COG | Intersection at Sperry Avenue and Highway 33. | Installation of traffic signal with paved shoulder widening. Install left turn lanes, roadway signing and striping. Railroad crossing improvements include at-grade railroad crossing on the side street approach less than 110 feet to the east. | 1283000 | 1154700 | 2023-06-13 | 0 | 0 | 0 | 175500 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE
H11-10-008 | 11 | 5008204 | 10 | Stockton | San Joaquin County | SJCOG | SJCOG | On Wilson Way between Hazelton Ave. and Anderson St. | Install safety lighting in the median. | 1457000 | 1311300 | 2023-06-16 | 0 | 0 | 0 | 215820 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE
H11-10-009 | 11 | 5008210 | 10 | Stockton | San Joaquin County | SJCOG | SJCOG | Various segments along South El Dorado Street between Clayton Avenue to Third Street. | Install RRFB devices, crosswalks, bulb outs, bike boxes, bicycle video detection at all intersections, install painted buffers, and cycle track; construct median refuge islands and sidewalks; and roadway reconfiguration within two segments. | 2350000 | 2115000 | 2023-11-28 | 0 | 0 | 0 | 355500 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE
H11-10-010 | 11 | 5008211 | 10 | Stockton | San Joaquin County | SJCOG | SJCOG | Hammer Lane corridor, including five intersections at Lower Sacramento Road on the west, Etna Street, El Dorado Street, Lan Ark Drive, and Tam O'Shanter Drive on the east. | Add edgeline, lane striping, pavement markings, speed feedback signs and pedestrian-scale lighting, install reflective signal backplates, and convert the existing Class II bike lanes to 7-ft protected bike lanes. | 1927800 | 1735020 | 2024-04-02 | 0 | 0 | 0 | 256500 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE
H11-10-012 | 11 | 5932108 | 10 | Tuolumne County | Tuolumne County | RURAL | TCTC | Various locations throughout the county. | Upgrade existing guardrails and end treatments. | 1111000 | 999900 | 2024-08-12 | 0 | 0 | 0 | 0 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE
H12-10-011 | 12 | 0 | 10 | Tuolumne County | Tuolumne County | RURAL | TCTC | The non-signalized intersection at Tuolumne Road, Black Oak Road, and Woodhams Carne Road. | Add lighting, improve sight distance for vehicles, and install high-friction surface treatment (HFST) approaching and through the intersection. | 806500 | 725850 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2025) | Due by 3/31/2028 | Yes (PE) | Not Started
H12-10-012 | 12 | 0 | 10 | Tuolumne County | Tuolumne County | RURAL | TCTC | Multiple guardrail locations on Bonds Flat Road, La Grange Road, O'Byrnes Ferry Road, Parrotts Ferry Road, Rawhide Road, Kewin Mill Road, and Longeway Road. | Remove and replace existing guardrail systems with upgraded steel-post Midwest Guardrail System (MGS) guardrails. | 1109400 | 998460 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2025) | Due by 3/31/2028 | Yes (PE) | Not Started
H12-10-013 | 12 | 0 | 10 | Tuolumne County | Tuolumne County | RURAL | TCTC | Tuolumne Road from Mono Way in East Sonora to Tuolumne Road North in Tuolumne City. | Enhance the centerline striping with the addition of recessed retroreflective pavement markers. | 147200 | 132480 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2025) | Due by 3/31/2028 | Yes (PE) | Not Started
H11-11-001 | 11 | 5167051 | 11 | Brawley | Imperial County | SCAG | ICTC | The intersection of Main Street with 8th Street. | Install traffic signal mast arm assembly, LED safety lighting, curb bulb out, median curb nose, ADA curb ramps, high visibility crosswalks, and pavement markings. | 277700 | 249930 | 2023-12-28 | 0 | 0 | 0 | 42210 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE
H11-11-010 | 11 | 5167053 | 11 | Brawley | Imperial County | SCAG | ICTC | Dogwood Road from 550ft south of Mead Road to 750ft north of Mead Road. | Install roadway lighting, guardrails, chevron curve warning signs, rumble strips, roadway striping, pavement markings, and outside shoulder widening. | 940000 | 846000 | 2023-12-28 | 0 | 0 | 0 | 94500 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE
H10-11-010 | 10 | 0 | 11 | Imperial County | Imperial County | SCAG | ICTC | Correll Rd between Dogwood Dr and Heber Ave; Rio Vista St between San Diego Ave and Haskell Rd; Shore Hawk Ave near intersection with Shore Gem St; and S. Marina Dr at intersection with Sea Palm Ave. | Install Rectangular Rapid Flashing Beacons (RRFBs) near schools. | 158000 | 158000 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2021) | Past due (due 9/30/2024) | Yes (PE & CON) | Not Started
H10-11-017 | 10 | 5957143 | 11 | San Diego County | San Diego County | SANDAG | SANDAG | Various locations along Sunrise Highway (MP 14.5, MP 15.0, MP 15.5, and MP 17.0) in Unincorporated San Diego County. | Upgrade metal beam guardrail and end-treatment. | 1577700 | 1577700 | 2021-10-12 | 0 | 0 | 0 | 328900 | Authorized | Past due (due 10/10/2025) | Yes (CON) | PE
H11-11-009 | 11 | 5957150 | 11 | San Diego County | San Diego County | SANDAG | SANDAG | Various Locations throughout San Diego County. | Metal Beam Guardrail and End-Treatment Upgrades. | 963600 | 751608 | 2023-12-01 | 0 | 0 | 0 | 116142 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE
H11-12-010 | 11 | 5073097 | 12 | Orange | Orange County | SCAG | OCTA | Existing crossing at Collins Avenue at California Street/Lynn Drive, Jordan Avenue at Esplanade Street, and La Veta Avenue at Malena Drive. | Replace existing beacons with Rectangular Rapid Flashing Beacons near schools. | 277300 | 249570 | 2023-09-28 | 0 | 0 | 0 | 18900 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE

## Notes
Notes:
1. | The project delivery requirements for local safety programs are as follows: • The PE milestone is met within 9 months; and • The CON milestone is met within 36 months (3 years). Exceptions are: a. The PE milestone does not apply if the project does not need HSIP funding in PE. b. For a project that a consultant is used for the PE work, an additional time of 6 months is allowed for meeting the CON milestone. The additional time is for the agency to advertise and select the consultant for the work of the PE phase.
2. | The project delivery information ("PE Auth Date", "ROW Auth Date", "CON Auth Date", "Closed out Date", etc) in this report is based on the offical approvals. If a request for authorization/allocation has been submitted but not yet approved, the information is not reflected in this report.
3. | Values under "Milestone Status (PE)" and "Milestone Status (CON)"
Value | Meaning
Authorzied | This phase has been authorized.
Due by x/xx/xxxx | The milestone will be due on this date pur the HSIP Delivery Requirements.
Past due (due x/xx/xxxx) | The milestone was due on this past date. This project is considered "delayed".
RFA received x/xx/xxxx | Caltrans received Request for Authorization/Allocation (RFA) package though there is still no official approval. The milestone is considered "met" if the request can be approved within 3 months from this request date.
No PE (or No CON) | HSIP funds will not used in PE phase (or CON phase) so the milestone is not applicable. Example 1: only local funds is used for PE - "No PE"; Example 2: the construction of the project has been combined with another project so no construction authorization is needed under this project - "No CON".
Not tracked | The milestone is not tracked. Example: Caltrans takes the lead in delivering the project. The local agency has no full control over the schedule.
For more information on HSIP Delivery Requirements, please go to the below webpage:
https://dot.ca.gov/programs/local-assistance/fed-and-state-programs/highway-safety-improvement-program/delivery-requirements-status-approved-projects