## LIST_HSIPdelayed
Highway Safety Improvement Program (HSIP) Delivery Status Report for Delayed Projects
Sorted by Caltrans District and Agency, Status as of 06/30/2026
Columns A to L are General Project Information, M to Q are Actual Project Delivery Information, and R to T are Delivery Milestone Status. Please see notes on the other spreadsheet of this file.
(Rows 4,5, and 6 to be deleted for online reports; column u to be deleted) | [11 empty] | (need to delete and double click to expand row to fit)
General Project Information | [11 empty] | Actual Project Delivery Information (Offical approval dates/amount. Not reflected if the request has not yet been approved.) |  |  |  |  | Delivery Milestone Status (see notes on the other spreadsheet)
| 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 33 | 34 | 35 | 23
Unique Project ID | Cycle | Project Number | District | Agency | County | MPO | RTPA | Project Location | Description of Work | Total Cost ($) | HSIP Funds ($) | PE Auth Date | ROW Auth Date | CON Auth Date | Closed out Date | Obligated /Allocated Amt ($) | Milestone Status (PE) | Milestone Status (CON) | Delayed? | Project Phase
H11-01-005 | 11 | 5904198 | 1 | Humboldt County | Humboldt County | RURAL | HCAG | Various guardrails and bridges throughout Humboldt County. | Repair, replace and upgrade guardrails and end treatments to current safety standards. | 1107600 | 996840 | 2023-11-30 | 0 | 0 | 0 | 72000 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE
H11-01-006 | 11 | 5904197 | 1 | Humboldt County | Humboldt County | RURAL | HCAG | Intersection of Country Club Road and The Terrace Road in Willow Creek California. | Install pedestrian activated flashing beacon at crosswalk from The Terrace Road across County Club Road with an advance warning flashing sign on Country Club. | 158400 | 142560 | 2023-11-20 | 0 | 0 | 0 | 10800 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE
H12-01-010 | 12 | 0 | 1 | Humboldt County | Humboldt County | RURAL | HCAG | Three locations: intersection of Oak and F Streets in unincorporated Eureka area, intersection of Kimtu Road and Country Club Drive in Willow Creek area, and school crossing for Loleta School on Loleta Drive. | Install pedestrian crossing enhancements. | 388800 | 349920 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2025) | Due by 3/31/2028 | Yes (PE) | Not Started
H12-01-011 | 12 | 0 | 1 | Humboldt County | Humboldt County | RURAL | HCAG | Various guardrails and bridges throughout Humboldt County. | Repair, replace and upgrade guardrails and end treatments to current safety standards. | 1108300 | 997470 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2025) | Due by 3/31/2028 | Yes (PE) | Not Started
H11-01-013 | 11 | 0 | 1 | Robinson Rancheria | Lake County | RURAL | LC/CAPC | Various locations on Robinson Rancheria, Lake County. | Install new street signs, regulatory, warning and information with new sign posts. Also replace existing guardrail on Acorn Drive and enhance crosswalk on Pomo Way. | 63000 | 56700 | 0 | 0 | 0 | 0 | 0 | No PE | Past due (due 3/31/2026) | Yes (CON) | Not Started
H11-03-006 | 11 | 5925202 | 3 | El Dorado County | El Dorado County | SACOG | El Dorado LTC | Various Locations - Mount Aukum Road MP 0.22, MP 0.72, MP 1.31, and at Middle Fork Cosumnes River; Cameron Park Drive between El Dorado Royale and Oxford; Bass Lake Road at Bass Lake; and Salmon Falls Rd MP 3.72, MP7.15, MP 9.76. | Replace guardrail and end treatment systems at various locations on Mount Aukum Road (E16), Cameron Park Drive, Bass Lake Road, and Salmon Falls Road. | 977900 | 880110 | 2023-11-22 | 0 | 0 | 0 | 117000 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE
H11-03-010 | 11 | 5260002 | 3 | Isleton | Sacramento County | SACOG | SACOG | Various intersections throughout the city: H St/Main St, 2nd St/A St./SR-160, SR-160/H St, and Union St./D St. | Install/upgrade STOP or intersection warning/regulatory signs, upgrade intersection pavement markings, and improve sight distance to intersection. | 109800 | 98820 | 2023-05-31 | 0 | 0 | 0 | 6840 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE
H11-03-011 | 11 | 5260004 | 3 | Isleton | Sacramento County | SACOG | SACOG | Various intersections throughout the city: H St/Main St; 2nd St/A St./SR-160; Union st/D St; and SR-160/C St. | Install pedestrian improvements (crossings, refuge island, and rectangular rapid flashing beacon) at unsignalized intersections. | 267500 | 240750 | 2023-09-18 | 0 | 0 | 0 | 17190 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE
H11-03-012 | 11 | 5089031 | 3 | Lincoln | Placer County | SACOG | Placer TPA | McBean Park Dr/4th St & B St; McBean Park Dr/4th St & D St; D St & 3rd St; and East Ave & 11th St. | High visibility marked mid-block crosswalks; raised median refuge island; rectangular rapid flashing beacon (RRFB); curb ramps; signing/striping enhancements; and sight distance improvements. | 304600 | 274140 | 2023-11-03 | 0 | 0 | 0 | 36000 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE
H11-03-013 | 11 | 0 | 3 | Loomis | Placer County | SACOG | Placer TPA | Various locations in Town. | Three (3) rapid rectangular flashing beacons, one (1) pedestrian activated, Yield to Pedestrian sign, twenty (20) high visibility crosswalks, and five (5) pedestrian curb ramps to accompany RRFB crosswalks. | 209300 | 188370 | 0 | 0 | 0 | 0 | 0 | No PE | Past due (due 3/31/2026) | Yes (CON) | Not Started
H11-03-027 | 11 | 5922126 | 3 | Yolo County | Yolo County | SACOG | SACOG | In Yolo County along County Road (CR) 102 between CR 29(N) and Pole Line Rd (City of Davis Limit). | Widen the shoulders and install centerline rumble strips. | 870600 | 783540 | 2023-10-02 | 0 | 0 | 0 | 108000 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE
H11-04-004 | 11 | 5038029 | 4 | Antioch | Contra Costa County | MTC | MTC | Delta de Anza Trail Xing at James Donlan Boulevard; Delta de Anza Trail Xing at Lone Tree Way; and Canada Valley Trail Xing at Hillcrest Avenue. | Install Hawk Signals at Trail Crossings to enhance Pedestrian and Bicycle Safety. | 920000 | 828000 | 2024-07-01 | 0 | 0 | 0 | 63000 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE
H11-04-006 | 11 | 5135064 | 4 | Concord | Contra Costa County | MTC | MTC | Various locations throughout the City of Concord. | Install new street lighting, upgrade existing street and intersection lighting, install pedestrian countdown signal heads, modify phasing to provide a Leading Pedestrian Interval (LPI), and install three new RRFBs and two HAWK Signals. | 8233300 | 7409970 | 2024-01-09 | 0 | 0 | 0 | 1240290 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE
H11-04-015 | 11 | 5318034 | 4 | Cupertino | Santa Clara County | MTC | MTC | Sections of 17 corridors: De Anza Blvd; Homestead Rd; Bollinger Rd; Wolfe Rd; McClellan Rd; Bubb Rd; Mariani Ave; Tantau Ave; Blaney Ave; Rainbow Dr; Miller Ave; Stelling Rd; Valley Green Dr; Calvert Dr; and Mary Ave. | Implement countermeasures including dynamic/variable speed warning signs at the curves along the corridor and improving pavement friction (HFST). | 3561800 | 3205620 | 2023-05-04 | 0 | 0 | 0 | 360000 | Authorized | Past due (due 5/31/2026) | Yes (CON) | PE
H10-04-013 | 10 | 5196043 | 4 | Daly City | San Mateo County | MTC | MTC | The intersection of John Daly Boulevard and Skyline Boulevard in Daly City. | Upgrade intersection signal hardware and pedestrian countdown signal heads, convert traffic signal pole to pole with a mast arm, install raised pavement markers and striping and upgrade ADA curb ramps. | 380200 | 342180 | 2021-06-11 | 0 | 0 | 0 | 48600 | Authorized | Past due (due 2/28/2025) | Yes (CON) | PE
H11-04-018 | 11 | 5056024 | 4 | Dixon | Solano County | MTC | MTC | Pedestrian crossing locations at 5th St & E A St and E A St & the Good Neighbor School. | Install RRFBs and other standard crossing treatments including signing, striping and curb enhancements. | 167800 | 151020 | 2024-05-31 | 0 | 0 | 0 | 27000 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE
H11-04-034 | 11 | 5317019 | 4 | Newark | Alameda County | MTC | MTC | Two unsignalized intersections: Thornton Ave & Magnolia St and Enterprise Dr & Aleppo Dr. | Install Rectangular Rapid Flashing Beacons with accompanying signage, curb cuts and pavement striping. | 192800 | 173520 | 2023-10-16 | 0 | 0 | 0 | 26280 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE
H11-04-038 | 11 | 5126020 | 4 | Pinole | Contra Costa County | MTC | MTC | On San Pablo Avenue at the Third Ave. intersection and Quinan Street intersection. On Pinole Valley Road at the Savage Avenue intersection. | Install pedestrian crossing enhancements at three mid-block crossings on arterial roadways. The enhancements include continental markings, median refuge islands, advanced stop bars and Rectangular Rapid Flash Beacons. | 281133 | 250000 | ? | 0 | 0 | 0 | 30179 | Past due (due 5/31/2024) | Past due (due 3/31/2026) | Yes (PE & CON) | Not Started
H10-04-033 | 10 | 0 | 4 | Pleasanton | Alameda County | MTC | MTC | Various overcrossing on/off ramp locations along Interstate 580 between Hopyard Road, Hacienda Drive, and Santa Rita Road. | Install Rectangular Rapid Flashing Beacons and improve striping and pavement markings. | 321200 | 250000 | 0 | 0 | 0 | 0 | 0 | No PE | Past due (due 9/30/2024) | Yes (CON) | Not Started
H11-04-040 | 11 | 5137060 | 4 | Richmond | Contra Costa County | MTC | MTC | Barrett Avenue from Harbour Way to 24th Street. | Road diet including protected bike lanes, sidewalk widening, high visibility crosswalk enhancements, protected left-turn phasing, advanced stop bars, median refuge islands, and Rectangular Rapid Flashing Beacons (RRFBs). | 1563200 | 1406880 | 2025-01-27 | 0 | 0 | 0 | 251280 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE
H10-04-039 | 10 | 5937226 | 4 | Santa Clara County | Santa Clara County | MTC | MTC | Foothill Expressway, Lawrence Expressway, and San Tomas Expressway. | Replace existing metal beam guardrail end treatments with modern variants and increase heights to meet current standards. | 999200 | 999200 | 2022-01-27 | 0 | 0 | 0 | 175000 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE
H11-04-058 | 11 | 0 | 4 | Vacaville | Solano County | MTC | MTC | The intersection of N. Orchard Ave and Valencia Lane; and the intersection of East Monte Vista Avenue and West Street. | Implement pedestrian crossing enhancements including high visibility crosswalks, advanced pedestrian warnings and signs, curb ramps, and Rectangular Rapid-Flashing Beacons (RRFBs). | 274700 | 247230 | 0 | 0 | 0 | 0 | 0 | No PE | Past due (due 3/31/2026) | Yes (CON) | Not Started
H11-04-059 | 11 | 0 | 4 | Vacaville | Solano County | MTC | MTC | Segments along Allison Pkwy, Meridian Rd, Orange Dr, Peabody Rd, Ulatis Dr, and Vaca Valley Pkwy. | Remove and replace edge-lines that have faded away or deteriorated. Remove and replace center line striping at various locations. | 272900 | 245610 | 0 | 0 | 0 | 0 | 0 | No PE | Past due (due 3/31/2026) | Yes (CON) | Not Started
H10-05-006 | 10 | 5943079 | 5 | San Benito County | San Benito County | AMBAG | San Benito COG | 21 locations on 10 roads (Panoche Rd, Limekiln Rd, Cienega Rd, Southside Rd, Enterprise Rd, San Juan Hollister Rd, San Juan Canyon Rd, Salinas Rd, Cannon Rd and Prescott Rd). | Replace damaged/destroyed guardrails to current standards. | 1013600 | 1000000 | 2021-06-23 | 0 | 0 | 0 | 170000 | Authorized | Past due (due 9/30/2025) | Yes (CON) | PE
H11-06-010 | 11 | 5143042 | 6 | Dinuba | Tulare County | TCAG | TCAG | 5 Locations within the City of Dinuba: 1) El Monte Way/Palm Drive; 2) N Crawford Avenue/E Saginaw Avenue; 3) W Kern Street/S M Street; 4) El Monte Way/N I Street/Eaton Avenue; and 5) Avenue 416/Road 92. | Install/upgrade pedestrian crossings with enhanced safety features and install median refuge islands on minor road approaches. | 227900 | 205110 | 2023-12-28 | 0 | 0 | 0 | 36000 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE
H11-06-011 | 11 | 5143043 | 6 | Dinuba | Tulare County | TCAG | TCAG | 3 Locations within the City of Dinuba: 1) El Monte Way between N Dickey Avenue and Palm Drive; 2) Crawford Avenue between Davis Drive and E Saginaw Avenue; and 3) S College Avenue between S M Street and Avenue 408. | Install/Upgrade Sidewalk Pathway along roadway segments. | 862100 | 775890 | 2023-12-28 | 0 | 0 | 0 | 117000 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE
H11-06-012 | 11 | 5143041 | 6 | Dinuba | Tulare County | TCAG | TCAG | E. North Way and Hayes Ave, S. College Ave and Academy Way, Euclid Ave and Franklin Way, Monte Vista Dr and West Drive Entrance to Walmart, and E. Tulare St and H St. | Install Rectangular Rapid Flashing Beacon to enhance pedestrian safety. | 249000 | 224100 | 2023-12-29 | 0 | 0 | 0 | 27000 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE
HSIP6-07-005R | 6 | 0 | 7 | Carson | Los Angeles County | SCAG | MTA | Various locations on Figueroa St, Main St, Victoria St, Avalon Blvd, University Dr, and Del Amo Blvd. | Install bike lanes. | 1124600 | 1012140 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2024) | Past due (due 6/30/2025) | Yes (PE & CON) | Not Started
H8-07-005 | 8 | 0 | 7 | Compton | Los Angeles County | SCAG | MTA | The Compton Blvd. corridor between Willowbrook Avenue and Central Avenue. | Install bike lanes and lighting along the corridor, and enhance pedestrian crossings at fifteen (15) intersections. | 1298000 | 1168200 | 0 | 0 | 0 | 0 | 0 | No PE | Past due (due 12/31/2022) | Yes (CON) | Not Started
H8-07-006 | 8 | 0 | 7 | Compton | Los Angeles County | SCAG | MTA | Citywide | Install (20) Pedestrian Countdown Heads. | 249800 | 249800 | 0 | 0 | 0 | 0 | 0 | No PE | Past due (due 9/30/2022) | Yes (CON) | Not Started
HSIP7-07-005 | 7 | 0 | 7 | Compton | Los Angeles County | SCAG | MTA | Compton Boulevard, from Willowbrook Avenue to eastern City limits. | Installation of raised medians and Class II bicycle lanes | 1928400 | 1691098 | 0 | 0 | 0 | 0 | 0 | No PE | Past due (due 12/31/2022) | Yes (CON) | Not Started
H10-07-003 | 10 | 0 | 7 | Covina | Los Angeles County | SCAG | MTA | Various uncontrolled crosswalk locations throughout the City of Covina. | Install inroad warning lights and/or rapid flashing beacons, signage, pavement markings, high visibility crosswalk and curb ramps. | 282500 | 250000 | 0 | 0 | 0 | 0 | 0 | No PE | Past due (due 3/31/2024) | Yes (CON) | Not Started
H11-07-007 | 11 | 5369016 | 7 | Cudahy | Los Angeles County | SCAG | MTA | 13 signalized intersections citywide. | Install retro-reflective backplates, other signal improvements, and implement Leading Pedestrian Interval (LPI) timing at all signals Citywide. Re-stripe crosswalks to implement high-visibility crosswalks at all signalized intersections. Furnish and install bulb outs. | 1353100 | 1217790 | 2023-10-11 | 0 | 0 | 0 | 180000 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE
H12-07-005 | 12 | 0 | 7 | Culver City | Los Angeles County | SCAG | MTA | Green Valley Cir from Sepulveda Blvd to Centinela Ave, and Buckingham Pkwy from Green Valley Cir to Slauson Ave, in the Fox Hills neighborhood. | Install new bikeways (Class II/IV). | 388800 | 349920 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2025) | Due by 3/31/2028 | Yes (PE) | Not Started
H12-07-006 | 12 | 0 | 7 | Culver City | Los Angeles County | SCAG | MTA | three (3) locations on Green Valley Cir between Sepulveda Blvd and Centinela Ave, in the Fox Hills Neighborhood. | Install pedestrian crossing enhancements. | 387900 | 349110 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2025) | Due by 3/31/2028 | Yes (PE) | Not Started
H11-07-010 | 11 | 5210036 | 7 | El Monte | Los Angeles County | SCAG | MTA | 4 signalized intersections along Tyler Ave and Valley Blvd. | Upgrade signal hardware and pedestrian countdown heads at three locations; convert signal to mast arm and install pedestrian countdown heads at one location. | 362400 | 326160 | 2024-05-16 | 0 | 0 | 0 | 58230 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE
H11-07-011 | 11 | 5210035 | 7 | El Monte | Los Angeles County | SCAG | MTA | Santa Anita Avenue between Valley Boulevard and Tyler Avenue. | Install Class II bike lane striping and signs. | 277000 | 249300 | 2024-05-16 | 0 | 0 | 0 | 44550 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE
H12-07-017 | 12 | 0 | 7 | Glendora | Los Angeles County | SCAG | MTA | 10 intersections: Route 66 at Grand, Lone Hill, Pasadena, Loraine, Elwood, Glendora, Amelia, and Vermont; Grand Ave at Gladstone; and Glendora Ave at Baseline. | Convert signals from pedestal-mounted to mast arms at 8 intersections; and impove signal hardware at 2 intersections. | 2305100 | 2074590 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2025) | Due by 3/31/2028 | Yes (PE) | Not Started
H10-07-012 | 10 | 5422003 | 7 | La Habra Heights | Los Angeles County | SCAG | MTA | Various Locations Throughout the City | Replace damaged guardrail as well as those not meeting standards, and installation of new guardrails as needed to improve safety. | 880000 | 880000 | 2021-12-13 | 0 | 0 | 0 | 80000 | Authorized | Past due (due 9/30/2024) | Yes (CON) | PE
H10-07-015 | 10 | 5419061 | 7 | Lancaster | Los Angeles County | SCAG | MTA | 28 signalized intersections within the city limits of Lancaster. | Systemically upgrade vehicle detection to include advanced dilemma-zone detection, bike recognition and detection, as well as upgrading existing signal equipment. | 2908000 | 2908000 | 2021-11-30 | 0 | 0 | 0 | 335600 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE
H10-07-017 | 10 | 5419059 | 7 | Lancaster | Los Angeles County | SCAG | MTA | Five (5) intersections: Avenue K-8 & Challenger Way, Valley Central Way & Central Court, Valley Central Way & Commercial Driveways (550 ft South of Lancaster Blvd), Avenue J & 25th Street East, and Avenue K & 25th Street East. | Install low-cost, quick build roundabouts. | 2129200 | 2129200 | 2021-11-01 | 0 | 0 | 0 | 280000 | Authorized | Past due (due 9/30/2024) | Yes (CON) | PE
H12-07-021 | 12 | 0 | 7 | Long Beach | Los Angeles County | SCAG | MTA | Eight intersections in underserved areas of Long Beach. | Mark high-contrast thermoplastic continental crosswalks in place of faded or outdated parallel bar crosswalks. | 234000 | 210600 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2025) | Due by 3/31/2028 | Yes (PE) | Not Started
H9-07-016 | 9 | 5250030 | 7 | Lynwood | Los Angeles County | SCAG | MTA | Intersection of Alameda St at Martin Luther King, Jr. Blvd. | Add left turn phases, detection and lighting, upgrade ramps and striping improvements. | 460900 | 460900 | 2019-12-04 | 0 | 0 | 0 | 21000 | Authorized | Past due (due 4/30/2026) | Yes (CON) | PE
H10-07-025 | 10 | 5129100 | 7 | Oxnard | Ventura County | SCAG | VCTC | Ten intersections including: Gonzales & Lombard, Gonzales & Solar, Rice & Camino Del Sol, Rose & Bard, Saviers & Hueneme, Ventura Rd & Doris, Vineyard & Esplanade, Pleasant Valley & C St, Harbor Blvd & 5th, and Saviers Rd & Laurel St. | Construct traffic signal improvements, including upgrading standards, mast arms, protected-left turn phasing, street lighting, emergency vehicle preemption, and accessible crossing. | 2998600 | 2998600 | 2021-06-28 | 0 | 0 | 0 | 297500 | Authorized | Past due (due 9/30/2024) | Yes (CON) | PE
H11-07-027 | 11 | 5129110 | 7 | Oxnard | Ventura County | SCAG | VCTC | Intersections and roadway on Ventura Road from Second Street to Wooley Road. | Install class II bike lanes (with green conflict areas), leading pedestrian intervals, additional signal heads, retroreflective backplates, advance stop bars, high visibility crosswalks, and bike and pedestrian warning signs. | 821100 | 738990 | 2023-12-04 | 0 | 0 | 0 | 130500 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE
H11-07-028 | 11 | 5129111 | 7 | Oxnard | Ventura County | SCAG | VCTC | Intersections and roadway on Bard Road from Saviers Road to Pleasant Valley Road. | Green bike conflict striping, leading pedestrian intervals, retroreflective backplates, advance stop bars, high visibility crosswalks, advance warning flashing beacons, upgraded signs, and movement restricting median improvements. | 775700 | 698130 | 2023-12-04 | 0 | 0 | 0 | 121500 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE
H11-07-029 | 11 | 5378051 | 7 | Palmdale | Los Angeles County | SCAG | MTA | Various locations throughout the City of Palmdale. | Conduct a City-wide signal modernization and pedestrian infrastructure replacement. Replace signal-head displays with current standards and replace pedestrian crosswalks and pedestrian buttons at crosswalks. | 6508800 | 5857920 | 2024-04-12 | 0 | 0 | 0 | 450000 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE
H11-07-036 | 11 | 5351045 | 7 | Pico Rivera | Los Angeles County | SCAG | MTA | 47 Signalized Intersections along Multiple Roadway Segments. | Improve signal hardware, install pedestrian countdown signal heads, and install advance stop bar before crosswalk (Bicycle Box). | 2130800 | 1917720 | 2023-11-17 | 0 | 0 | 0 | 324000 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE
H10-07-031 | 10 | 5413018 | 7 | Rancho Palos Verdes | Los Angeles County | SCAG | MTA | Palos Verdes Drive East between Palos Verdes Drive South and Palos Verdes Drive North. | Upgrade approx. 4,400 linear feet of guardrails. | 1000000 | 1000000 | 2024-12-16 | 0 | 0 | 0 | 88100 | Authorized | Past due (due 3/30/2026) | Yes (CON) | PE
H11-07-040 | 11 | 5349016 | 7 | Rolling Hills Estates | Los Angeles County | SCAG | MTA | 7 guardrail segments: 2 sections on Silver Spur Road; 2 sections on Hawthorne Boulevard; 1 section on Ranchview Road; and 2 sections on Palos Verdes Drive East. | Guardrail and end treatment upgrades. | 1111400 | 1000000 | 2023-12-12 | 0 | 0 | 0 | 176153 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE
H11-08-001 | 11 | 5408009 | 8 | Adelanto | San Bernardino County | SCAG | SANBAG | Intersections of Bellflower St/Victor St, Verbena Rd/Victor St, Aster Rd/Victor St, Rancho Rd/Adelanto Rd, Air Expressway/Aster Rd, and Air Expressway /Raccoon Ave. | Install all-way stop control including the installation of stop signs, stop ahead signs and legends, crosswalks, and the construction and reconstruction of ADA ramps. | 365900 | 329310 | 2025-07-17 | 0 | 0 | 0 | 40500 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE
H11-08-002 | 11 | 5214016 | 8 | Banning | Riverside County | SCAG | RCTC | 17 signalized intersections throughout the City of Banning. | Upgrade traffic signal hardware including LED safety lighting, retro-reflective backplates, countdown pedestrian signal heads, ADA-compliant pedestrian push buttons, and emergency vehicle preemption systems. | 433900 | 390510 | 2023-09-07 | 0 | 0 | 0 | 54000 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE
H11-08-003 | 11 | 5214017 | 8 | Banning | Riverside County | SCAG | RCTC | 19 intersections throughout the City of Banning. | Install curb extensions, ADA curb ramps, RRFBs, high visibility crosswalks, and advanced warning signs and pavement markings. | 585000 | 526500 | 2023-09-07 | 0 | 0 | 0 | 76500 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE
H11-08-004 | 11 | 5214018 | 8 | Banning | Riverside County | SCAG | RCTC | The intersection of Wilson St with 12th St. | Install curb extensions, ADA curb ramps, median refuge island, RRFB, high visibility crosswalks, and advanced warning signs and pavement markings. | 277000 | 249300 | 2023-09-07 | 0 | 0 | 0 | 44460 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE
H11-08-011 | 11 | 5384019 | 8 | Desert Hot Springs | Riverside County | SCAG | RCTC | 17 intersections (10 along Palm Dr, Hacienda Av & Mountain View Rd, 5 intersections along Pierson Bl, and Mission Lakes Bl & Indian Canyon Dr). | Install retroreflective signal back-plates and install signal phasing to implement Leading Pedestrian Interval system (all 17 intersections). Install high visibility thermoplastic crosswalks (8 intersections). | 623500 | 561150 | 2023-08-03 | 0 | 0 | 0 | 64170 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE
H11-08-013 | 11 | 5449043 | 8 | Highland | San Bernardino County | SCAG | SANBAG | 5th Street from Del Rosa Drive to Victoria Avenue; Greenspot Road from SR210 to Greenspot Road Bridge; and Orange Street from Boulder Avenue to south City Limits. | Upgrade approximately 7 miles of roadway edge-line and centerline stripes to replace existing faded and worn roadway line delineation along the City of Highland's arterial roadway segments. | 155000 | 139500 | 2024-05-08 | 0 | 0 | 0 | 25650 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE
H12-08-013 | 12 | 0 | 8 | Highland | San Bernardino County | SCAG | SANBAG | Thirty-five (35) signalized intersections throughout the city and Church Street at Glenheather Drive/Love Street intersection. | Install a new traffic signal, upgrade signal heads, and install retroreflective signal head backplates. | 1522300 | 1370070 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2025) | Due by 3/31/2028 | Yes (PE) | Not Started
H11-08-017 | 11 | 5326027 | 8 | Montclair | San Bernardino County | SCAG | SANBAG | Adjacent to Montera Elementary School at multiple locations along Monte Vista Avenue, Bandera Street, Helena Avenue, Kingsley Street, Fremont Avenue, and Canoga Street. | Enhance pedestrian safety by installing edgelines and high visibility and/or ladder crosswalks, constructing ADA-compliant curb ramps, adding pedestrian signage, solar-powered speed feedback signage, and other safety measures. | 277700 | 249930 | 2024-06-18 | 0 | 0 | 0 | 27000 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE
H11-08-018 | 11 | 5326026 | 8 | Montclair | San Bernardino County | SCAG | SANBAG | 1.95 miles of Orchard Street at 10 signalized and non-signalized intersections: Mills Ave., Pradera Ave., Sunset Park entrances, Ramona Ave., Camulos Ave., Tudor Ave., Monte Vista Ave., Fremont Ave., Central Ave., and Benson Ave. | Install raised pavement markers and striping; Upgrade existing stop signs to flashing LED light stop signs; Install a HAWK system; Install/Upgrade pedestrian crossings at uncontrolled locations. | 402300 | 362070 | 2024-06-18 | 0 | 0 | 0 | 40500 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE
H10-08-012 | 10 | 0 | 8 | Murrieta | Riverside County | SCAG | RCTC | Various locations citywide. | Install adaptive timing program at all City signalized intersections, including new traffic signal controllers and loops, as well as the required software and hardware at City Hall Traffic Management Center. | 854700 | 422350 | 0 | 0 | 0 | 0 | 0 | No PE | Past due (due 3/31/2025) | Yes (CON) | Not Started
H11-08-026 | 11 | 5083029 | 8 | Redlands | San Bernardino County | SCAG | SANBAG | The intersection of San Bernardino Avenue and Church Street. | Install traffic signal. | 653600 | 588240 | 2023-10-30 | 0 | 0 | 0 | 103500 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE
H11-08-027 | 11 | 5083028 | 8 | Redlands | San Bernardino County | SCAG | SANBAG | Various signalized intersections citywide. | Install larger signal heads and back-plate with reflective border. | 245000 | 220500 | 2023-10-25 | 0 | 0 | 0 | 38700 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE
H12-08-029 | 12 | 5205036 | 8 | Rialto | San Bernardino County | SCAG | SANBAG | 108 signalized intersections citywide. | Install new signal heads and controllers and implement leading pedestrian intervals (LPIs). | 5418000 | 4876200 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2025) | Due by 3/31/2028 | Yes (PE) | Not Started
H11-08-031 | 11 | 5954196 | 8 | San Bernardino County | San Bernardino County | SCAG | SANBAG | Nine rural roadway segments (Arrowhead Lake Road, Rock Springs Road/Roundup Way, Sheep Creek Road, Wilson Ranch Road, Santa Fe Avenue, Pioneertown Road, Pipes Canyon Road, Camp Rock Road and Parker Dam Road). | Install centerline and edgeline rumble stripes with raised pavement markers. | 5983300 | 4994830 | 2023-09-18 | 0 | 0 | 0 | 750600 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE
H11-08-032 | 11 | 5954197 | 8 | San Bernardino County | San Bernardino County | SCAG | SANBAG | 50 rural intersections along high-speed roadways with no intersection lighting. | Install stop signs and flashing beacons in advance of the stop signs, W4-4P 'Cross Traffic Does Not Stop' signs, and transverse rumble strips on County-maintained minor stop-controlled approaches. | 1392000 | 1252800 | 2023-08-11 | 0 | 0 | 0 | 164700 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE
H11-08-033 | 11 | 5954198 | 8 | San Bernardino County | San Bernardino County | SCAG | SANBAG | Cajon Boulevard from Cleghorn Road to Kenwood Avenue. | Install centerline and edgeline rumble stripes with raised pavement markers. Install a 2ft painted median, with flexible delineators where passing is not permitted. Install flashing beacon on "Stop Ahead" sign prior to Kenwood Avenue. | 1314500 | 1183050 | 2023-08-18 | 0 | 0 | 0 | 166500 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE
H11-08-034 | 11 | 5954199 | 8 | San Bernardino County | San Bernardino County | SCAG | SANBAG | Oak Glen Road east of the City of Yucaipa, generally between Chagall Road and Pisgah Peak-Oak Glen Road; Lone Pine Canyon Road, between Heath Creek Drive and SR-138; Lytle Creek Road between 1500 feet west of Sycamore Drive and Glen Helen Parkway. | Install centerline and edgeline rumble stripes with raised pavement markers. Install chevron signs on curved roadway segments. | 2854800 | 2569320 | 2023-08-18 | 0 | 0 | 0 | 360000 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE
H11-08-043 | 11 | 0 | 8 | Wildomar | Riverside County | SCAG | RCTC | Mission Trail from Malaga Road to Corydon Street, and Corydon Street from Grand Avenue to Mission Trail. | Install pedestrian countdown signal heads, pedestrian crosswalk enhancements, ADA Systems at signalized intersections, high visibility crosswalks, and pedestrian curb ramps. | 176100 | 158490 | 0 | 0 | 0 | 0 | 0 | No PE | Past due (due 3/31/2026) | Yes (CON) | Not Started
H12-09-005 | 12 | 0 | 9 | Ridgecrest | Kern County | KCOG | KCOG | Existing bike lanes along the following roadways: Ward Ave, Drummond Ave, Los Flores Ave, Ridgecrest Blvd, Upjohn Ave, Bowman Rd, Mahan St, Downs St, Norma St, China Lake Blvd, French Ave, Sunland St, Gateway Blvd, Richmond Rd, College Heights Blvd. | Upgrade bike lanes. | 1754600 | 1579140 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2025) | Due by 3/31/2028 | Yes (PE) | Not Started
H12-09-007 | 12 | 0 | 9 | Ridgecrest | Kern County | KCOG | KCOG | 14 signalized intersections on Downs Street, Norma Street, Drummond Ave, Bowman Rd, and China Lake Blvd. | Upgrade the signal hardware back-plates with retroreflective border and replace signal heads. | 543500 | 489150 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2025) | Due by 3/31/2028 | Yes (PE) | Not Started
H10-10-003 | 10 | 5241076 | 10 | Ceres | Stanislaus County | STANCOG | Stan COG | 3 unsignalized intersections on Mitchell Ave at Garrison St, Dale Ave, and Kay St. | Install raised medians on approaches, advanced pavement markings, and striping. | 514100 | 462690 | 2022-01-19 | 0 | 0 | 0 | 71190 | Authorized | Past due (due 9/30/2024) | Yes (CON) | PE
H10-10-004 | 10 | 5241077 | 10 | Ceres | Stanislaus County | STANCOG | Stan COG | Two signalized intersections: Fowler Road & Mitchell Road, and East Whitmore Avenue & Moffett Road. | Install raised medians on approaches; provide protected left-turn phasing; upgrade signal hardware on all approaches. | 740400 | 666360 | 2022-01-19 | 0 | 0 | 0 | 118980 | Authorized | Past due (due 9/30/2024) | Yes (CON) | PE
H10-10-010 | 10 | 5059254 | 10 | Modesto | Stanislaus County | STANCOG | Stan COG | The intersections of Standiford Ave. with Longbridge Dr. and Sylvan Ave. with Bridgeford Ln. | Install pedestrian refuge island with directional median openings, Pedestrian Hybrid Beacons and high visibility crosswalks with pedestrian signage. | 965800 | 919000 | 2021-12-22 | 0 | 0 | 0 | 100350 | Authorized | Past due (due 9/30/2024) | Yes (CON) | PE
H10-10-011 | 10 | 5059255 | 10 | Modesto | Stanislaus County | STANCOG | Stan COG | Oakdale Road from Lancey Drive to Celeste Drive. | Install Pedestrian Hybrid Beacon, Leading Pedestrian Intervals, pedestrian signals, blank-out no right turn signals/signage, directional median, high visibility crosswalk, median refuge island, ADA ramps, reconstruct driveway, and coordinate signals. | 1105900 | 1039330 | 2021-12-22 | 0 | 0 | 0 | 147510 | Authorized | Past due (due 9/30/2024) | Yes (CON) | PE
H11-10-002 | 11 | 5059267 | 10 | Modesto | Stanislaus County | STANCOG | Stan COG | Tokay Ave at La Cienega Dr, E Rumble Rd at Hampshire Ln, Robertson Rd at Hancock St, and Conant Ave at Budd St. | Install raised crosswalks. | 248200 | 223380 | 2025-06-26 | 0 | 0 | 0 | 39600 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE
H11-10-006 | 11 | 5244042 | 10 | Patterson | Stanislaus County | STANCOG | Stan COG | Intersection at Sperry Avenue and Highway 33. | Installation of traffic signal with paved shoulder widening. Install left turn lanes, roadway signing and striping. Railroad crossing improvements include at-grade railroad crossing on the side street approach less than 110 feet to the east. | 1283000 | 1154700 | 2023-06-13 | 0 | 0 | 0 | 175500 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE
H11-10-009 | 11 | 5008210 | 10 | Stockton | San Joaquin County | SJCOG | SJCOG | Various segments along South El Dorado Street between Clayton Avenue to Third Street. | Install RRFB devices, crosswalks, bulb outs, bike boxes, bicycle video detection at all intersections, install painted buffers, and cycle track; construct median refuge islands and sidewalks; and roadway reconfiguration within two segments. | 2350000 | 2115000 | 2023-11-28 | 0 | 0 | 0 | 355500 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE
H11-10-012 | 11 | 5932108 | 10 | Tuolumne County | Tuolumne County | RURAL | TCTC | Various locations throughout the county. | Upgrade existing guardrails and end treatments. | 1111000 | 999900 | 2024-08-12 | 0 | 0 | 0 | 0 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE
H12-10-012 | 12 | 0 | 10 | Tuolumne County | Tuolumne County | RURAL | TCTC | Multiple guardrail locations on Bonds Flat Road, La Grange Road, O'Byrnes Ferry Road, Parrotts Ferry Road, Rawhide Road, Kewin Mill Road, and Longeway Road. | Remove and replace existing guardrail systems with upgraded steel-post Midwest Guardrail System (MGS) guardrails. | 1109400 | 998460 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2025) | Due by 3/31/2028 | Yes (PE) | Not Started
H11-11-001 | 11 | 5167051 | 11 | Brawley | Imperial County | SCAG | ICTC | The intersection of Main Street with 8th Street. | Install traffic signal mast arm assembly, LED safety lighting, curb bulb out, median curb nose, ADA curb ramps, high visibility crosswalks, and pavement markings. | 277700 | 249930 | 2023-12-28 | 0 | 0 | 0 | 42210 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE
H11-11-010 | 11 | 5167053 | 11 | Brawley | Imperial County | SCAG | ICTC | Dogwood Road from 550ft south of Mead Road to 750ft north of Mead Road. | Install roadway lighting, guardrails, chevron curve warning signs, rumble strips, roadway striping, pavement markings, and outside shoulder widening. | 940000 | 846000 | 2023-12-28 | 0 | 0 | 0 | 94500 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE
H10-11-010 | 10 | 0 | 11 | Imperial County | Imperial County | SCAG | ICTC | Correll Rd between Dogwood Dr and Heber Ave; Rio Vista St between San Diego Ave and Haskell Rd; Shore Hawk Ave near intersection with Shore Gem St; and S. Marina Dr at intersection with Sea Palm Ave. | Install Rectangular Rapid Flashing Beacons (RRFBs) near schools. | 158000 | 158000 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2021) | Past due (due 9/30/2024) | Yes (PE & CON) | Not Started
H10-11-017 | 10 | 5957143 | 11 | San Diego County | San Diego County | SANDAG | SANDAG | Various locations along Sunrise Highway (MP 14.5, MP 15.0, MP 15.5, and MP 17.0) in Unincorporated San Diego County. | Upgrade metal beam guardrail and end-treatment. | 1577700 | 1577700 | 2021-10-12 | 0 | 0 | 0 | 328900 | Authorized | Past due (due 10/10/2025) | Yes (CON) | PE
H11-11-009 | 11 | 5957150 | 11 | San Diego County | San Diego County | SANDAG | SANDAG | Various Locations throughout San Diego County. | Metal Beam Guardrail and End-Treatment Upgrades. | 963600 | 751608 | 2023-12-01 | 0 | 0 | 0 | 116142 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE

## Notes
Notes:
1. | The project delivery requirements for local safety programs are as follows: • The PE milestone is met within 9 months; and • The CON milestone is met within 36 months (3 years). Exceptions are: a. The PE milestone does not apply if the project does not need HSIP funding in PE. b. For a project that a consultant is used for the PE work, an additional time of 6 months is allowed for meeting the CON milestone. The additional time is for the agency to advertise and select the consultant for the work of the PE phase.
2. | The project delivery information ("PE Auth Date", "ROW Auth Date", "CON Auth Date", "Closed out Date", etc) in this report is based on the offical approvals. If a request for authorization/allocation has been submitted but not yet approved, the information is not reflected in this report.
3. | Values under "Milestone Status (PE)" and "Milestone Status (CON)"
Value | Meaning
Authorzied | This phase has been authorized.
Due by x/xx/xxxx | The milestone will be due on this date pur the HSIP Delivery Requirements.
Past due (due x/xx/xxxx) | The milestone was due on this past date. This project is considered "delayed".
RFA received x/xx/xxxx | Caltrans received Request for Authorization/Allocation (RFA) package though there is still no official approval. The milestone is considered "met" if the request can be approved within 3 months from this request date.
No PE (or No CON) | HSIP funds will not used in PE phase (or CON phase) so the milestone is not applicable. Example 1: only local funds is used for PE - "No PE"; Example 2: the construction of the project has been combined with another project so no construction authorization is needed under this project - "No CON".
Not tracked | The milestone is not tracked. Example: Caltrans takes the lead in delivering the project. The local agency has no full control over the schedule.
For more information on HSIP Delivery Requirements, please go to the below webpage:
https://dot.ca.gov/programs/local-assistance/fed-and-state-programs/highway-safety-improvement-program/delivery-requirements-status-approved-projects