## LIST_HSIPdelayed
Highway Safety Improvement Program (HSIP) Delivery Status Report for Delayed Projects
Sorted by Caltrans District and Agency, Status as of 10/01/2026
Columns A to L are General Project Information, M to Q are Actual Project Delivery Information, and R to T are Delivery Milestone Status. Please see notes on the other spreadsheet of this file.
Unique Project ID | Cycle | Project Number | District | Agency | County | MPO | RTPA | Project Location | Description of Work | Total Cost ($) | HSIP Funds ($) | PE Auth Date | ROW Auth Date | CON Auth Date | Closed out Date | Obligated /Allocated Amt ($) | Milestone Status (PE) | Milestone Status (CON) | Delayed? | Project Phase | Funding Type
H12-01-010 | 12 | 0 | 1 | Humboldt County | Humboldt County | RURAL | HCAG | Three locations: intersection of Oak and F Streets in unincorporated Eureka area, intersection of Kimtu Road and Country Club Drive in Willow Creek area, and school crossing for Loleta School on Loleta Drive. | Install pedestrian crossing enhancements. | 388800 | 349920 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2025) | Due by 3/31/2028 | Yes (PE) | Not Started | State
H11-01-013 | 11 | 0 | 1 | Robinson Rancheria | Lake County | RURAL | LC/CAPC | Various locations on Robinson Rancheria, Lake County. | Install new street signs, regulatory, warning and information with new sign posts. Also replace existing guardrail on Acorn Drive and enhance crosswalk on Pomo Way. | 63000 | 56700 | 0 | 0 | 0 | 0 | 0 | No PE | Past due (due 3/31/2026) | Yes (CON) | Not Started | Federal
H11-02-001 | 11 | 5907085 | 2 | Lassen County | Lassen County | RURAL | Lassen LTC | 1.2 miles of CR A27 (Center Road) from 700ft west of Johnstonville Road to 1,500ft east of Cramer Lane in central unincorporated Lassen County. | Install edge rumble strips, centerline rumble strips and high friction surface treatment along length of corridor and advance curve warning and chevrons signs at two curves. | 323500 | 291150 | 0 | 0 | 0 | 0 | 0 | No PE | Past due (due 9/30/2026) | Yes (CON) | Not Started | State
H11-03-003 | 11 | 5912130 | 3 | Butte County | Butte County | BCAG | BCAG | Various road sections throughout Butte County. | Road Safety Signing Audit (RSSA) Project. Audit existing sign types, locations, retroreflectivity and size per MUTCD, identify missing signs per MUTCD and modify signage accordingly. | 1685700 | 1517130 | 2023-05-02 | 0 | 0 | 0 | 315000 | Authorized | Past due (due 9/30/2026) | Yes (CON) | PE | State
H11-03-010 | 11 | 5260002 | 3 | Isleton | Sacramento County | SACOG | SACOG | Various intersections throughout the city: H St/Main St, 2nd St/A St./SR-160, SR-160/H St, and Union St./D St. | Install/upgrade STOP or intersection warning/regulatory signs, upgrade intersection pavement markings, and improve sight distance to intersection. | 109800 | 98820 | 2023-05-31 | 0 | 0 | 0 | 6840 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE | State
H11-03-011 | 11 | 5260004 | 3 | Isleton | Sacramento County | SACOG | SACOG | Various intersections throughout the city: H St/Main St; 2nd St/A St./SR-160; Union st/D St; and SR-160/C St. | Install pedestrian improvements (crossings, refuge island, and rectangular rapid flashing beacon) at unsignalized intersections. | 267500 | 240750 | 2023-09-18 | 0 | 0 | 0 | 17190 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE | Federal
H11-03-012 | 11 | 5089031 | 3 | Lincoln | Placer County | SACOG | Placer TPA | McBean Park Dr/4th St & B St; McBean Park Dr/4th St & D St; D St & 3rd St; and East Ave & 11th St. | High visibility marked mid-block crosswalks; raised median refuge island; rectangular rapid flashing beacon (RRFB); curb ramps; signing/striping enhancements; and sight distance improvements. | 304600 | 274140 | 2023-11-03 | 0 | 0 | 0 | 36000 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE | State
H11-04-003 | 11 | 5038028 | 4 | Antioch | Contra Costa County | MTC | MTC | 69 Signalized Intersections along Multiple Roadway Segments. | Improve signal hardware: lenses, back-plates with retroreflective borders, mounting, size, and number; Install pedestrian countdown signal heads; and Install advance stop bar before crosswalk as needed. | 2800600 | 2520540 | 2024-08-08 | 0 | 0 | 0 | 369000 | Authorized | Past due (due 8/31/2026) | Yes (CON) | PE | Federal
H11-04-004 | 11 | 5038029 | 4 | Antioch | Contra Costa County | MTC | MTC | Delta de Anza Trail Xing at James Donlan Boulevard; Delta de Anza Trail Xing at Lone Tree Way; and Canada Valley Trail Xing at Hillcrest Avenue. | Install Hawk Signals at Trail Crossings to enhance Pedestrian and Bicycle Safety. | 920000 | 828000 | 2024-07-01 | 0 | 0 | 0 | 63000 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE | State
H11-04-006 | 11 | 5135064 | 4 | Concord | Contra Costa County | MTC | MTC | Various locations throughout the City of Concord. | Install new street lighting, upgrade existing street and intersection lighting, install pedestrian countdown signal heads, modify phasing to provide a Leading Pedestrian Interval (LPI), and install three new RRFBs and two HAWK Signals. | 8233300 | 7409970 | 2024-01-09 | 0 | 0 | 0 | 1240290 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE | Federal
H10-04-013 | 10 | 5196043 | 4 | Daly City | San Mateo County | MTC | MTC | The intersection of John Daly Boulevard and Skyline Boulevard in Daly City. | Upgrade intersection signal hardware and pedestrian countdown signal heads, convert traffic signal pole to pole with a mast arm, install raised pavement markers and striping and upgrade ADA curb ramps. | 380200 | 342180 | 2021-06-11 | 0 | 0 | 0 | 48600 | Authorized | Past due (due 2/28/2025) | Yes (CON) | PE | State
H11-04-018 | 11 | 5056024 | 4 | Dixon | Solano County | MTC | MTC | Pedestrian crossing locations at 5th St & E A St and E A St & the Good Neighbor School. | Install RRFBs and other standard crossing treatments including signing, striping and curb enhancements. | 167800 | 151020 | 2024-05-31 | 0 | 0 | 0 | 27000 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE | State
H11-04-038 | 11 | 5126020 | 4 | Pinole | Contra Costa County | MTC | MTC | On San Pablo Avenue at the Third Ave. intersection and Quinan Street intersection. On Pinole Valley Road at the Savage Avenue intersection. | Install pedestrian crossing enhancements at three mid-block crossings on arterial roadways. The enhancements include continental markings, median refuge islands, advanced stop bars and Rectangular Rapid Flash Beacons. | 281133 | 250000 | ? | 0 | 0 | 0 | 30179 | Past due (due 5/31/2024) | Past due (due 3/31/2026) | Yes (PE & CON) | Not Started | State
H10-04-033 | 10 | 0 | 4 | Pleasanton | Alameda County | MTC | MTC | Various overcrossing on/off ramp locations along Interstate 580 between Hopyard Road, Hacienda Drive, and Santa Rita Road. | Install Rectangular Rapid Flashing Beacons and improve striping and pavement markings. | 321200 | 250000 | 0 | 0 | 0 | 0 | 0 | No PE | Past due (due 9/30/2024) | Yes (CON) | Not Started | State
H11-04-040 | 11 | 5137060 | 4 | Richmond | Contra Costa County | MTC | MTC | Barrett Avenue from Harbour Way to 24th Street. | Road diet including protected bike lanes, sidewalk widening, high visibility crosswalk enhancements, protected left-turn phasing, advanced stop bars, median refuge islands, and Rectangular Rapid Flashing Beacons (RRFBs). | 1563200 | 1406880 | 2025-01-27 | 0 | 0 | 0 | 251280 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE | State
H11-04-051 | 11 | 5923133 | 4 | Solano County | Solano County | MTC | MTC | Multiple Rural Roads: 1) Lyon Road, 2) Vaca Valley, 3) Dixon Avenue, 4) Putah Creek Road, 5) Cordelia Road, 6) Fry Road, 7) Rockveille Road, 8) Pleasants Valley Road, 9) Meridian Road, 10) Holland Road, 11) Pedrick Road, and 12) Other Roads. | Install curve advance warning signs with flashing beacons, install delineators/reflectors/object markers and install/upgrade signs with new fluorescent sheeting. | 1192800 | 1073520 | 2023-08-17 | 0 | 0 | 0 | 191700 | Authorized | Past due (due 10/1/2026) | Yes (CON) | PE | Federal
H11-04-052 | 11 | 5923136 | 4 | Solano County | Solano County | MTC | MTC | Various unsignalized intersections throughout the County. | Install street lights, place high friction surface treatment, restripe, and relocate various markings/utility poles/signs to correct sight distance. | 1684700 | 1516230 | 2023-08-17 | 0 | 0 | 0 | 225000 | Authorized | Past due (due 8/28/2026) | Yes (CON) | PE | Federal
H11-04-053 | 11 | 5923135 | 4 | Solano County | Solano County | MTC | MTC | Five rural road corridors: (1) Putah Creek Rd, (2) Vaca Valley Rd, (3) Cordelia Rd, (4) Pleasants Valley Rd, and (5) Gibson Canyon Rd. | Install guardrail and/or high friction surface treatment at horizontal curves and spot locations. | 1868200 | 1681380 | 2023-08-17 | 0 | 0 | 0 | 202500 | Authorized | Past due (due 8/28/2026) | Yes (CON) | PE | Federal
H11-04-059 | 11 | 0 | 4 | Vacaville | Solano County | MTC | MTC | Segments along Allison Pkwy, Meridian Rd, Orange Dr, Peabody Rd, Ulatis Dr, and Vaca Valley Pkwy. | Remove and replace edge-lines that have faded away or deteriorated. Remove and replace center line striping at various locations. | 272900 | 245610 | 0 | 0 | 0 | 0 | 0 | No PE | Past due (due 3/31/2026) | Yes (CON) | Not Started | State
H10-05-004 | 10 | 5944143 | 5 | Monterey County | Monterey County | AMBAG | TAMC | San Miguel Canyon Road and Castroville Boulevard in Prunedale. | Install a roundabout. | 2189600 | 2189600 | 2021-09-29 | 2025-09-11 | 0 | 0 | 511000 | Authorized | Past due (due 8/31/2026) | Yes (CON) | ROW | State
H10-05-006 | 10 | 5943079 | 5 | San Benito County | San Benito County | AMBAG | San Benito COG | 21 locations on 10 roads (Panoche Rd, Limekiln Rd, Cienega Rd, Southside Rd, Enterprise Rd, San Juan Hollister Rd, San Juan Canyon Rd, Salinas Rd, Cannon Rd and Prescott Rd). | Replace damaged/destroyed guardrails to current standards. | 1013600 | 1000000 | 2021-06-23 | 0 | 0 | 0 | 170000 | Authorized | Past due (due 9/30/2025) | Yes (CON) | PE | State
H11-05-014 | 11 | 5138059 | 5 | Santa Maria | Santa Barbara County | SBCAG | SBCAG | Intersections of: Donovan Rd/Western Ave., Donovan Rd/Bay Ave, Alvin Ave/Palisade Dr., Battles Rd/Westgate Rd., and Miller Ave/Newlove Dr. | Construct/install pedestrian refuge islands, updated signage, road diets and Rectangular Rapid Flashing Beacons (RRFBs). | 275000 | 247500 | 2024-06-07 | 0 | 0 | 0 | 9000 | Authorized | Past due (due 8/31/2026) | Yes (CON) | PE | State
H11-05-016 | 11 | 5138061 | 5 | Santa Maria | Santa Barbara County | SBCAG | SBCAG | Skyway Drive between Betteravia Road and State Route 135 (Broadway). | Improve 24,000 LF of existing Class II Bicycle Lanes to Class IV Bicycle Lanes through lane width reduction and installation of paint and flexible bollards. | 322200 | 249480 | 0 | 0 | 0 | 0 | 0 | No PE | Past due (due 8/31/2026) | Yes (CON) | Not Started | State
H11-05-017 | 11 | 5248010 | 5 | Soledad | Monterey County | AMBAG | TAMC | Various locations throughout the City. | Install RRFB devices, beacons, bulb outs, crosswalks, bike boxes, streetlights, pavement markings, lead pedestrian interval timing, signage, construct median refuge islands, bike lane buffers, and roadway reconfiguration (one location). | 863600 | 777240 | 2023-05-15 | 0 | 0 | 0 | 137700 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE | State
H11-06-010 | 11 | 5143042 | 6 | Dinuba | Tulare County | TCAG | TCAG | 5 Locations within the City of Dinuba: 1) El Monte Way/Palm Drive; 2) N Crawford Avenue/E Saginaw Avenue; 3) W Kern Street/S M Street; 4) El Monte Way/N I Street/Eaton Avenue; and 5) Avenue 416/Road 92. | Install/upgrade pedestrian crossings with enhanced safety features and install median refuge islands on minor road approaches. | 227900 | 205110 | 2023-12-28 | 0 | 0 | 0 | 36000 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE | State
H11-06-011 | 11 | 5143043 | 6 | Dinuba | Tulare County | TCAG | TCAG | 3 Locations within the City of Dinuba: 1) El Monte Way between N Dickey Avenue and Palm Drive; 2) Crawford Avenue between Davis Drive and E Saginaw Avenue; and 3) S College Avenue between S M Street and Avenue 408. | Install/Upgrade Sidewalk Pathway along roadway segments. | 862100 | 775890 | 2023-12-28 | 0 | 0 | 0 | 117000 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE | State
H11-06-012 | 11 | 5143041 | 6 | Dinuba | Tulare County | TCAG | TCAG | E. North Way and Hayes Ave, S. College Ave and Academy Way, Crawford Ave and Olive Way, Monte Vista Dr and West Drive Entrance to Walmart, and E. Tulare St and H St. | Install Rectangular Rapid Flashing Beacon to enhance pedestrian safety. | 249000 | 224100 | 2023-12-29 | 0 | 0 | 0 | 27000 | Authorized | Past due (due 9/30/2026) | Yes (CON) | PE | State
HSIP6-07-005R | 6 | 0 | 7 | Carson | Los Angeles County | SCAG | MTA | Various locations on Figueroa St, Main St, Victoria St, Avalon Blvd, University Dr, and Del Amo Blvd. | Install bike lanes. | 1124600 | 1012140 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2024) | Past due (due 6/30/2025) | Yes (PE & CON) | Not Started | State
H8-07-005 | 8 | 5078039 | 7 | Compton | Los Angeles County | SCAG | MTA | The Compton Blvd. corridor between Willowbrook Avenue and Central Avenue. | Install bike lanes and lighting along the corridor, and enhance pedestrian crossings at fifteen (15) intersections. | 1298000 | 1168200 | 0 | 0 | 0 | 0 | 0 | No PE | Past due (due 12/31/2022) | Yes (CON) | Not Started | Federal
H8-07-006 | 8 | 5078037 | 7 | Compton | Los Angeles County | SCAG | MTA | Citywide | Install (20) Pedestrian Countdown Heads. | 249800 | 249800 | 0 | 0 | 0 | 0 | 0 | No PE | Past due (due 9/30/2022) | Yes (CON) | Not Started | Federal
HSIP7-07-005 | 7 | 5078038 | 7 | Compton | Los Angeles County | SCAG | MTA | Compton Boulevard, from Willowbrook Avenue to eastern City limits. | Installation of raised medians and Class II bicycle lanes | 1928400 | 1691098 | 0 | 0 | 0 | 0 | 0 | No PE | Past due (due 12/31/2022) | Yes (CON) | Not Started | Federal
H10-07-003 | 10 | 0 | 7 | Covina | Los Angeles County | SCAG | MTA | Various uncontrolled crosswalk locations throughout the City of Covina. | Install inroad warning lights and/or rapid flashing beacons, signage, pavement markings, high visibility crosswalk and curb ramps. | 282500 | 250000 | 0 | 0 | 0 | 0 | 0 | No PE | Past due (due 3/31/2024) | Yes (CON) | Not Started | State
H12-07-017 | 12 | 0 | 7 | Glendora | Los Angeles County | SCAG | MTA | 10 intersections: Route 66 at Grand, Lone Hill, Pasadena, Loraine, Elwood, Glendora, Amelia, and Vermont; Grand Ave at Gladstone; and Glendora Ave at Baseline. | Convert signals from pedestal-mounted to mast arms at 8 intersections; and impove signal hardware at 2 intersections. | 2305100 | 2074590 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2025) | Due by 3/31/2028 | Yes (PE) | Not Started | Federal
H10-07-012 | 10 | 5422003 | 7 | La Habra Heights | Los Angeles County | SCAG | MTA | Various Locations Throughout the City | Replace damaged guardrail as well as those not meeting standards, and installation of new guardrails as needed to improve safety. | 800000 | 800000 | 2021-12-13 | 0 | 0 | 0 | 80000 | Authorized | Past due (due 9/30/2024) | Yes (CON) | PE | State
H10-07-017 | 10 | 5419059 | 7 | Lancaster | Los Angeles County | SCAG | MTA | Five (5) intersections: Avenue K-8 & Challenger Way, Valley Central Way & Central Court, Valley Central Way & Commercial Driveways (550 ft South of Lancaster Blvd), Avenue J & 25th Street East, and Avenue K & 25th Street East. | Install low-cost, quick build roundabouts. | 2129200 | 2129200 | 2021-11-01 | 0 | 0 | 0 | 280000 | Authorized | Past due (due 9/30/2024) | Yes (CON) | PE | State
H9-07-016 | 9 | 5250030 | 7 | Lynwood | Los Angeles County | SCAG | MTA | Intersection of Alameda St at Martin Luther King, Jr. Blvd. | Add left turn phases, detection and lighting, upgrade ramps and striping improvements. | 460900 | 460900 | 2019-12-04 | 0 | 0 | 0 | 21000 | Authorized | Past due (due 4/30/2026) | Yes (CON) | PE | Federal
H11-07-025 | 11 | 5212015 | 7 | Manhattan Beach | Los Angeles County | SCAG | MTA | Manhattan Avenue and 36th Street; Valley Drive and Flournoy Road; and Highland Avenue and 40th Street. | Install new pedestrian crosswalk with Americans with Disabilities Act (ADA) ramps. | 245000 | 220500 | 2023-06-30 | 0 | 0 | 0 | 36000 | Authorized | Past due (due 9/30/2026) | Yes (CON) | PE | State
H11-07-027 | 11 | 5129110 | 7 | Oxnard | Ventura County | SCAG | VCTC | Intersections and roadway on Ventura Road from Second Street to Wooley Road. | Install class II bike lanes (with green conflict areas), leading pedestrian intervals, additional signal heads, retroreflective backplates, advance stop bars, high visibility crosswalks, and bike and pedestrian warning signs. | 821100 | 738990 | 2023-12-04 | 0 | 0 | 0 | 130500 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE | State
H11-07-028 | 11 | 5129111 | 7 | Oxnard | Ventura County | SCAG | VCTC | Intersections and roadway on Bard Road from Saviers Road to Pleasant Valley Road. | Green bike conflict striping, leading pedestrian intervals, retroreflective backplates, advance stop bars, high visibility crosswalks, advance warning flashing beacons, upgraded signs, and movement restricting median improvements. | 775700 | 698130 | 2023-12-04 | 0 | 0 | 0 | 121500 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE | State
H11-07-040 | 11 | 5349016 | 7 | Rolling Hills Estates | Los Angeles County | SCAG | MTA | 7 guardrail segments: 2 sections on Silver Spur Road; 2 sections on Hawthorne Boulevard; 1 section on Ranchview Road; and 2 sections on Palos Verdes Drive East. | Guardrail and end treatment upgrades. | 1111400 | 1000000 | 2023-12-12 | 0 | 0 | 0 | 176153 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE | State
H11-08-013 | 11 | 5449043 | 8 | Highland | San Bernardino County | SCAG | SANBAG | 5th Street from Del Rosa Drive to Victoria Avenue; Greenspot Road from SR210 to Greenspot Road Bridge; and Orange Street from Boulder Avenue to south City Limits. | Upgrade approximately 7 miles of roadway edge-line and centerline stripes to replace existing faded and worn roadway line delineation along the City of Highland's arterial roadway segments. | 155000 | 139500 | 2024-05-08 | 0 | 0 | 0 | 25650 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE | State
H11-08-015 | 11 | 5074024 | 8 | Lake Elsinore | Riverside County | SCAG | RCTC | Various locations throughout the City. | Install Rectangular Rapid Flashing Beacon (RRFB) signs at existing pedestrian crossings at various locations throughout the City. Install advanced yield line pavement markings and signs. | 250000 | 225000 | 0 | 0 | 0 | 0 | 0 | No PE | Past due (due 9/30/2026) | Yes (CON) | Not Started | State
H11-08-017 | 11 | 5326027 | 8 | Montclair | San Bernardino County | SCAG | SANBAG | Adjacent to Montera Elementary School at multiple locations along Monte Vista Avenue, Bandera Street, Helena Avenue, Kingsley Street, Fremont Avenue, and Canoga Street. | Enhance pedestrian safety by installing edgelines and high visibility and/or ladder crosswalks, constructing ADA-compliant curb ramps, adding pedestrian signage, solar-powered speed feedback signage, and other safety measures. | 277700 | 249930 | 2024-06-18 | 0 | 0 | 0 | 27000 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE | State
H11-08-018 | 11 | 5326026 | 8 | Montclair | San Bernardino County | SCAG | SANBAG | 1.95 miles of Orchard Street at 10 signalized and non-signalized intersections: Mills Ave., Pradera Ave., Sunset Park entrances, Ramona Ave., Camulos Ave., Tudor Ave., Monte Vista Ave., Fremont Ave., Central Ave., and Benson Ave. | Install raised pavement markers and striping; Upgrade existing stop signs to flashing LED light stop signs; Install a HAWK system; Install/Upgrade pedestrian crossings at uncontrolled locations. | 402300 | 362070 | 2024-06-18 | 0 | 0 | 0 | 40500 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE | State
H10-08-012 | 10 | 0 | 8 | Murrieta | Riverside County | SCAG | RCTC | Various locations citywide. | Install adaptive timing program at all City signalized intersections, including new traffic signal controllers and loops, as well as the required software and hardware at City Hall Traffic Management Center. | 854700 | 422350 | 0 | 0 | 0 | 0 | 0 | No PE | Past due (due 3/31/2025) | Yes (CON) | Not Started | State
H11-08-043 | 11 | 0 | 8 | Wildomar | Riverside County | SCAG | RCTC | Mission Trail from Malaga Road to Corydon Street, and Corydon Street from Grand Avenue to Mission Trail. | Install pedestrian countdown signal heads, pedestrian crosswalk enhancements, ADA Systems at signalized intersections, high visibility crosswalks, and pedestrian curb ramps. | 176100 | 158490 | 0 | 0 | 0 | 0 | 0 | No PE | Past due (due 3/31/2026) | Yes (CON) | Not Started | State
H12-09-005 | 12 | 0 | 9 | Ridgecrest | Kern County | KCOG | KCOG | Existing bike lanes along the following roadways: Ward Ave, Drummond Ave, Los Flores Ave, Ridgecrest Blvd, Upjohn Ave, Bowman Rd, Mahan St, Downs St, Norma St, China Lake Blvd, French Ave, Sunland St, Gateway Blvd, Richmond Rd, College Heights Blvd. | Upgrade bike lanes. | 1754600 | 1579140 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2025) | Due by 3/31/2028 | Yes (PE) | Not Started | Federal
H12-09-007 | 12 | 0 | 9 | Ridgecrest | Kern County | KCOG | KCOG | 14 signalized intersections on Downs Street, Norma Street, Drummond Ave, Bowman Rd, and China Lake Blvd. | Upgrade the signal hardware back-plates with retroreflective border and replace signal heads. | 543500 | 489150 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2025) | Due by 3/31/2028 | Yes (PE) | Not Started | State
H10-10-003 | 10 | 5241076 | 10 | Ceres | Stanislaus County | STANCOG | Stan COG | 3 unsignalized intersections on Mitchell Ave at Garrison St, Dale Ave, and Kay St. | Install raised medians on approaches, advanced pavement markings, and striping. | 514100 | 462690 | 2022-01-19 | 0 | 0 | 0 | 71190 | Authorized | Past due (due 9/30/2024) | Yes (CON) | PE | State
H10-10-004 | 10 | 5241077 | 10 | Ceres | Stanislaus County | STANCOG | Stan COG | Two signalized intersections: Fowler Road & Mitchell Road, and East Whitmore Avenue & Moffett Road. | Install raised medians on approaches; provide protected left-turn phasing; upgrade signal hardware on all approaches. | 740400 | 666360 | 2022-01-19 | 0 | 0 | 0 | 118980 | Authorized | Past due (due 9/30/2024) | Yes (CON) | PE | State
H10-10-010 | 10 | 5059254 | 10 | Modesto | Stanislaus County | STANCOG | Stan COG | The intersections of Standiford Ave. with Longbridge Dr. and Sylvan Ave. with Bridgeford Ln. | Install pedestrian refuge island with directional median openings, Pedestrian Hybrid Beacons and high visibility crosswalks with pedestrian signage. | 965800 | 919000 | 2021-12-22 | 0 | 0 | 0 | 100350 | Authorized | Past due (due 9/30/2024) | Yes (CON) | PE | State
H10-10-011 | 10 | 5059255 | 10 | Modesto | Stanislaus County | STANCOG | Stan COG | Oakdale Road from Lancey Drive to Celeste Drive. | Install Pedestrian Hybrid Beacon, Leading Pedestrian Intervals, pedestrian signals, blank-out no right turn signals/signage, directional median, high visibility crosswalk, median refuge island, ADA ramps, reconstruct driveway, and coordinate signals. | 1105900 | 1039330 | 2021-12-22 | 0 | 0 | 0 | 147510 | Authorized | Past due (due 9/30/2024) | Yes (CON) | PE | State
H11-10-002 | 11 | 5059267 | 10 | Modesto | Stanislaus County | STANCOG | Stan COG | Tokay Ave at La Cienega Dr, E Rumble Rd at Hampshire Ln, Robertson Rd at Hancock St, and Conant Ave at Budd St. | Install raised crosswalks. | 248200 | 223380 | 2025-06-26 | 0 | 0 | 0 | 39600 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE | State
H11-10-006 | 11 | 5244042 | 10 | Patterson | Stanislaus County | STANCOG | Stan COG | Intersection at Sperry Avenue and Highway 33. | Installation of traffic signal with paved shoulder widening. Install left turn lanes, roadway signing and striping. Railroad crossing improvements include at-grade railroad crossing on the side street approach less than 110 feet to the east. | 1283000 | 1154700 | 2023-06-13 | 0 | 0 | 0 | 175500 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE | State
H11-10-009 | 11 | 5008210 | 10 | Stockton | San Joaquin County | SJCOG | SJCOG | Various segments along South El Dorado Street between Clayton Avenue to Third Street. | Install RRFB devices, crosswalks, bulb outs, bike boxes, bicycle video detection at all intersections, install painted buffers, and cycle track; construct median refuge islands and sidewalks; and roadway reconfiguration within two segments. | 2350000 | 2115000 | 2023-11-28 | 0 | 0 | 0 | 355500 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE | Federal
H11-10-012 | 11 | 5932108 | 10 | Tuolumne County | Tuolumne County | RURAL | TCTC | Various locations throughout the county. | Upgrade existing guardrails and end treatments. | 1111000 | 999900 | 2024-08-12 | 0 | 0 | 0 | 0 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE | Federal
H11-11-001 | 11 | 5167051 | 11 | Brawley | Imperial County | SCAG | ICTC | The intersection of Main Street with 8th Street. | Install traffic signal mast arm assembly, LED safety lighting, curb bulb out, median curb nose, ADA curb ramps, high visibility crosswalks, and pavement markings. | 277700 | 249930 | 2023-12-28 | 0 | 0 | 0 | 42210 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE | State
H11-11-010 | 11 | 5167053 | 11 | Brawley | Imperial County | SCAG | ICTC | Dogwood Road from 550ft south of Mead Road to 750ft north of Mead Road. | Install roadway lighting, guardrails, chevron curve warning signs, rumble strips, roadway striping, pavement markings, and outside shoulder widening. | 940000 | 846000 | 2023-12-28 | 0 | 0 | 0 | 94500 | Authorized | Past due (due 3/31/2026) | Yes (CON) | PE | State
H10-11-010 | 10 | 0 | 11 | Imperial County | Imperial County | SCAG | ICTC | Correll Rd between Dogwood Dr and Heber Ave; Rio Vista St between San Diego Ave and Haskell Rd; Shore Hawk Ave near intersection with Shore Gem St; and S. Marina Dr at intersection with Sea Palm Ave. | Install Rectangular Rapid Flashing Beacons (RRFBs) near schools. | 158000 | 158000 | 0 | 0 | 0 | 0 | 0 | Past due (due 12/31/2021) | Past due (due 9/30/2024) | Yes (PE & CON) | Not Started | State
H11-11-005 | 11 | 5066057 | 11 | National City | San Diego County | SANDAG | SANDAG | Signalized Intersections along Highland Avenue from Division Street to 30th Street (excluding 28th Street), along Plaza Boulevard from L Avenue to 8th Street and along National City Boulevard from 4th Street to 24th Street/Miles of Cars Way. | Improve signal hardware with back-plates with retroreflective borders, install an advance stop bar before crosswalk (Bicycle Box), and modify signal phasing to implement a Leading Pedestrian Interval (LPI). | 947700 | 852930 | 2023-08-08 | 0 | 0 | 0 | 92250 | Authorized | Past due (due 9/30/2026) | Yes (CON) | PE | State

## Notes
Notes:
1. | The project delivery requirements for local safety programs are as follows: • The PE milestone is met within 9 months; and • The CON milestone is met within 36 months (3 years). Exceptions are: a. The PE milestone does not apply if the project does not need HSIP funding in PE. b. For a project that a consultant is used for the PE work, an additional time of 6 months is allowed for meeting the CON milestone. The additional time is for the agency to advertise and select the consultant for the work of the PE phase.
2. | The project delivery information ("PE Auth Date", "ROW Auth Date", "CON Auth Date", "Closed out Date", etc) in this report is based on the offical approvals. If a request for authorization/allocation has been submitted but not yet approved, the information is not reflected in this report.
3. | Values under "Milestone Status (PE)" and "Milestone Status (CON)"
Value | Meaning
Authorzied | This phase has been authorized.
Due by x/xx/xxxx | The milestone will be due on this date pur the HSIP Delivery Requirements.
Past due (due x/xx/xxxx) | The milestone was due on this past date. This project is considered "delayed".
RFA received x/xx/xxxx | Caltrans received Request for Authorization/Allocation (RFA) package though there is still no official approval. The milestone is considered "met" if the request can be approved within 3 months from this request date.
No PE (or No CON) | HSIP funds will not used in PE phase (or CON phase) so the milestone is not applicable. Example 1: only local funds is used for PE - "No PE"; Example 2: the construction of the project has been combined with another project so no construction authorization is needed under this project - "No CON".
Not tracked | The milestone is not tracked. Example: Caltrans takes the lead in delivering the project. The local agency has no full control over the schedule.
For more information on HSIP Delivery Requirements, please go to the below webpage:
https://dot.ca.gov/programs/local-assistance/fed-and-state-programs/highway-safety-improvement-program/delivery-requirements-status-approved-projects