## chartHSIP
Highway Safety Improvement Program (HSIP) Project Status by Phase (As of 06/30/2026)
|  | 1 |  | 2 |  | 3 |  | 4
|  | Cycle 2 (2008) |  | Cycle 3 (2010) |  | Cycle 4 (2011) |  | Cycle 5 (2012)
| Project Status | (Released July, 2008) |  | (Release Date 1/26/10) |  | (Release Date 2/23/11) |  | (Release Date 10/19/12)
|  | Project Count | % | Project Count | % | Project Count | % | Project Count | %
| No Phase Auth | 1 | 0.5587% | 0 | 0% | 0 | 0% | 0 | 0%
PE | In PE | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0%
ROW | In Right of Way | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0%
CON | In Construction | 1 | 0.5587% | 0 | 0% | 0 | 0% | 1 | 0.5025%
Closed | Project Closed | 177 | 98.88% | 107 | 100% | 159 | 100% | 198 | 99.5%
| Total | 179 | 100% | 107 | 100% | 159 | 100% | 199 | 100%
|  | Cycle 6 (2013) |  | Cycle 7 (2015) |  | Cycle 8 (2016) |  | Cycle 9 (2018)
| Project Status | (Release Date 11/14/13) |  | (Release Date 11/12/15) |  | (Release Date 11/21/16) |  | (Release Date 12/12/18)
|  | Project Count | % | Project Count | % | Project Count | % | Project Count | %
| No Phase Auth | 1 | 0.4651% | 1 | 0.5882% | 2 | 0.9434% | 6 | 2.871% | 36 | 3.77%
PE | In PE | 0 | 0% | 0 | 0% | 0 | 0% | 1 | 0.4785% | 104 | 10.89%
ROW | In Right of Way | 0 | 0% | 0 | 0% | 0 | 0% | 1 | 0.4785% | 4 | 0.4188%
CON | In Construction | 13 | 6.047% | 12 | 7.059% | 28 | 13.21% | 51 | 24.4% | 359 | 37.59%
Closed | Project Closed | 201 | 93.49% | 157 | 92.35% | 182 | 85.85% | 150 | 71.77% | 452 | 47.33%
| Total | 215 | 100% | 170 | 100% | 212 | 100% | 209 | 100% | 955
|  | Cycle 10 (2020) |  | Cycle 11 (2022) |  | Cycle 12 (2024) |  | All Cycles
| Project Status | (Release Date 3/30/21) |  | (Release Date 3/9/23) |  | (Release Date 2/21/25)
|  | Project Count | % | Project Count | % | Project Count | % | Project Count | %
| No Phase Auth | 7 | 2.682% | 21 | 7.692% | 72 | 25.99% | 111 | 4.66%
PE | In PE | 15 | 5.747% | 88 | 32.23% | 179 | 64.62% | 283 | 11.88%
ROW | In Right of Way | 2 | 0.7663% | 1 | 0.3663% | 3 | 1.083% | 7 | 0.2939%
CON | In Construction | 130 | 49.81% | 150 | 54.95% | 23 | 8.303% | 409 | 17.17%
Closed | Project Closed | 107 | 41% | 13 | 4.762% | 0 | 0% | 1572 | 65.99%
| Total | 261 | 100% | 273 | 100% | 277 | 100% | 2382 | 100%
Caltrans, Division of Local Assistance
Cycle 1 (2007)
(Released April&June, 2007)
|  | Project Count | %
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 0 | 0%
|  | 121 | 100%
|  | 121 | 100%

## Notes
Notes:
1. | The project delivery requirements for local safety programs are as follows: • The PE milestone is met within 9 months; and • The CON milestone is met within 36 months (3 years). Exceptions are: a. The PE milestone does not apply if the project does not need HSIP funding in PE. b. For a project that a consultant is used for the PE work, an additional time of 6 months is allowed for meeting the CON milestone. The additional time is for the agency to advertise and select the consultant for the work of the PE phase.
2. | The project delivery information ("PE Auth Date", "ROW Auth Date", "CON Auth Date", "Closed out Date", etc) in this report is based on the offical approvals. If a request for authorization/allocation has been submitted but not yet approved, the information is not reflected in this report.
3. | Values under "Milestone Status (PE)" and "Milestone Status (CON)"
Value | Meaning
Authorzied | This phase has been authorized.
Due by x/xx/xxxx | The milestone will be due on this date pur the HSIP Delivery Requirements.
Past due (due x/xx/xxxx) | The milestone was due on this past date. This project is considered "delayed".
RFA received x/xx/xxxx | Caltrans received Request for Authorization/Allocation (RFA) package though there is still no official approval. The milestone is considered "met" if the request can be approved within 3 months from this request date.
No PE (or No CON) | HSIP funds will not used in PE phase (or CON phase) so the milestone is not applicable. Example 1: only local funds is used for PE - "No PE"; Example 2: the construction of the project has been combined with another project so no construction authorization is needed under this project - "No CON".
Not tracked | The milestone is not tracked. Example: Caltrans takes the lead in delivering the project. The local agency has no full control over the schedule.
For more information on HSIP Delivery Requirements, please go to the below webpage:
https://dot.ca.gov/programs/local-assistance/fed-and-state-programs/highway-safety-improvement-program/delivery-requirements-status-approved-projects