## E-76 waiting-list
Location | PREFIX | Project NO | Agency | prepared date | submit to HQ date | HQ review date | submit to FHWA date | To FMIS date | Fed requested | AC requested | total requested | Status Comment | Locode | DIST | Status | Waiting Days | dist processing Days | HQ processing Days | FHWA processing Days | FTIP No | project location | Type of Work | SEQ | Date Request Initiated | date completed request | MPO | Today | Warning | UEI
DISTRICT | BRLS | 5904(162) | Humboldt County | 2024-01-17 | NA | NA | NA | NA | 305428.5 | 0 | 345000 | .. | 5904 | 01 | Prepared on 1/17/2024 | 43917 | NA | NA | NA | NA | Mattole Road Over Mattole River In Honeydew, Ca (br 04c0055) | Bridge Replacement Riparian Vegetation Reestablishment Monitoring | 1 | NA | NA | NON-MPO | 2024-03-28 |  | UBWEAY8NDL25
DISTRICT | RPSTPL | 5903(063) | Modoc County | 2024-01-29 | NA | NA | NA | NA | 4340520 | 0 | 4340520 | .. | 5903 | 02 | Prepared on 1/29/2024 | 59 | NA | NA | NA | NA | On County Road 111 North In Modoc County From State Route 139 Northward To County Road 108 | Rehabilitate Existing Road Pavement And Widen Shoulders Using County Standards. | 4 | NA | NA | NON-MPO |  |  | PR4KNB6J6SS3
DISTRICT | ACST-ER | 32L0(575) | Trinity County | 2023-07-21 | NA | NA | NA | NA | 453227.51 | 0 | 984908.3 | .. | 5905 | 02 | Prepared on 7/21/2023 | 251 | NA | NA | NA | NA | East Side Road, Trinity County | Permanent Restoration On East Side Road As Result Of Ca17-2 Disaster. | 3 | NA | NA | NON-MPO |  |  | L5JFNKZB8L75
DISTRICT | ACSTP | 15A5(026) | Trinity County | 2022-09-23 | NA | NA | NA | NA | 0 | 147515.76 | 166628 | .. | 5905 | 02 | Prepared on 9/23/2022 | 552 | NA | NA | NA | NA | Ca20-2 August Complex Pr Work Using Eo Procedures On Ruth Zenia Road Pm 16.20, 16.78, 17.42, | Permanent Restoration | 1 | NA | NA | SHASTA |  |  | L5JFNKZB8L75
DISTRICT | BRLO | 5909(082) | Plumas County | 2022-06-30 | NA | NA | NA | NA | 3135000 | 0 | 3135000 | .. | 5909 | 02 | Prepared on 6/30/2022 | 637 | NA | NA | NA | NA | Cr 435 (pm 0.04) Over Spanish Creek | Bridge Replacement | 6 | NA | NA | SHASTA |  |  | YXZZPBLCRFY6
DISTRICT | BRLKS | 5908(029) | Tehama County | 2023-11-22 | NA | NA | NA | NA | 280632 | -108004 | 215785 | .. | 5908 | 02 | Prepared on 11/22/2023 | 127 | NA | NA | NA | NA | Mccoy Road Over Dibble Creek, North Of Red Bluff In Tehama County | Replace One Lane Low Water Crossing (bridge # 00l0004) With Two Lane Bridge, (new | 8 | NA | NA | NON-MPO |  |  | JNGACGN2N453
DISTRICT | BRLO | 5916(107) | Yuba County | 2023-10-26 | NA | NA | NA | NA | -83637.61 | 0 | -83637.61 | Hold Engineer s Estimate missing, contains errors, or inconsistent with request. | 5916 | 03 | Prepared on 10/26/2023 | 154 | NA | NA | NA | NA | Along Rices Crossing Road 0.04 Miles Southeast Of Marysville Road. Br.# 16c0087 | Bridge Replacement (tc) | 6 | NA | NA | SACOG |  |  | LH3ELMEX1L73
DISTRICT | BRLO | 5913(058) | Sierra County | 2024-02-20 | NA | NA | NA | NA | 1800000 | 0 | 1800000 | NEED JUSTIFICATION FOR PED EXTENSION | 5913 | 03 | Prepared on 2/20/2024 | 37 | NA | NA | NA | NA | Plumbago Road At Kanaka Creek ~ 1.6 Mies South Of Alleghany. Br. # 13c0051. | Bridge Replacement (tc) | 5 | NA | NA | SACOG |  |  | NA7LYJSG63L8
DISTRICT | HSIPL | 5479(063) | Elk Grove | 2024-03-12 | NA | NA | NA | NA | 0 | 0 | 146013 | .. | 5479 | 03 | Prepared on 3/12/2024 | 16 | NA | NA | NA | NA | Four (4) Existing Trail Crossings Of Public Roads: Laguna Park Drive, Adobe Springs Way, | Install Crosswalks, Advance Yield Signs, Rapid Rectangular | 4 | NA | NA | SACOG |  |  | GHJBWTLJK3D7
DISTRICT | CML | 5479(065) | Elk Grove | 2024-01-31 | NA | NA | NA | NA | 0 | 966000 | 1491042 | .. | 5479 | 03 | Prepared on 1/31/2024 | 57 | NA | NA | NA | NA | In Elk Grove: Along The South Side Of Elk Grove Creek From Laguna Springs Drive To Oneto Park, | Construct A Separate Class I Bicycle/pedestrian Trail (along The South Side Of Elk | 3 | NA | NA | SACOG |  |  | GHJBWTLJK3D7
DISTRICT | CMLNI | 5925(191) | El Dorado County | 2022-04-18 | NA | NA | NA | NA | 169000 | 0 | 500000 | .. | 5925 | 03 | Prepared on 4/18/2022 | 710 | NA | NA | NA | NA | Eastern El Dorado County In The Tahoe Basin. | Equipment Purchase - Vacuum/rodder Truck | 1 | NA | NA | SACOG |  | Warning | R8JPSXALG464
DISTRICT | CML | 5919(158) | Placer County | 2024-03-26 | NA | NA | NA | NA | 0 | 225000 | 225000 | .. | 5919 | 03 | Prepared on 3/26/2024 | 2 | NA | NA | NA | NA | On The North Side Of Douglas Blvd., Between Melwood Lane And Oak Knoll Drive | Construct Pedestrian And Bicycle Facilities To Complete The Multi-modal Connection | 2 | NA | NA | SACOG |  | Warning | L786NC553FC1
DISTRICT | CPFL | 6168(006) | Southgate Recreation And Park District | 2024-03-20 | NA | NA | NA | NA | 48000 | 0 | 57600 | .. | 6168 | 03 | Prepared on 3/20/2024 | 8 | NA | NA | NA | NA | In Sacramento County, From Current Path North Of Smedberg Middle School To East Of The School. | Construct Class I Multi-path Gap Closure. | 1 | NA | NA | MTC |  | Warning | HNKAN7J28WE3
DISTRICT | BPMP | 5029(024) | Redwood City | 2023-04-10 | NA | NA | NA | NA | 304322.25 | 0 | 343750 | .. | 5029 | 04 | Prepared on 4/10/2023 | 353 | NA | NA | NA | VAR991007 | Bridge Parkway Over Marine World Lagoon | Preventative Maintenance | 2 | NA | NA | MTC |  |  | JDWVP8YNMME4
DISTRICT | BPMP | 5029(025) | Redwood City | 2023-04-10 | NA | NA | NA | NA | 304322.25 | 0 | 343750 | .. | 5029 | 04 | Prepared on 4/10/2023 | 353 | NA | NA | NA | VAR991007 | Bridge Parkway(right) Over Marine World Lagoon, East Of Marine World Parkway | Preventative Maintenance | 2 | NA | NA | MTC |  |  | JDWVP8YNMME4
DISTRICT | RPSTPLE | 5923(073) | Solano County | 2023-08-10 | NA | NA | NA | NA | 0 | 0 | 7940.38 | .. | 5923 | 04 | Prepared on 8/10/2023 | 231 | NA | NA | NA | NA | Cordelia Rd. From Lopes Rd To Pittman Rd. | Pedestrian Paths, Benches | 4 | NA | NA | MTC |  |  | XDLNTFCKM1A6
DISTRICT | BPMP | 5137(046) | Richmond | 2023-02-03 | NA | NA | NA | NA | 1859130 | 0 | 2150000 | .. | 5137 | 04 | Prepared on 2/3/2023 | 419 | NA | NA | NA | NA | In The City Of Richmond: Bridges 28c0472 And 28c0474 (left/right) On The Richmond Parkway And | Bridge Preventative Maintenance | 3 | NA | NA | MTC |  |  | W856SVG77LP8
DISTRICT | ER | 32L0(520) | Alameda County | 2022-06-21 | NA | NA | NA | NA | -216001 | 0 | -243986.23 | .. | 5933 | 04 | Prepared on 6/21/2022 | 646 | NA | NA | NA | NA | Crow Canyon Road Mm 6.08 & 6.21. Unincorporated Alameda County. . | Construction | 5 | NA | NA | MTC |  |  | KD49R5NLLPZ7
DISTRICT | CML | 5322(060) | Fremont | 2023-11-29 | NA | NA | NA | NA | 6510000 | 0 | 11855367.25 | .. | 5322 | 04 | Prepared on 11/29/2023 | 120 | NA | NA | NA | NA | Complete Streets Upgrade Of Relinquished Sr84. | Thornton Ave - Blacow Rd. To Fremont Blvd; Fremont Blvd - Alder Ave. To Mattos Dr; | 5 | NA | NA | MTC |  |  | Q3MWNS85DEF8
DISTRICT | CML | 5226(023) | San Bruno | 2024-01-05 | NA | NA | NA | NA | 0 | 0 | -65000 | .. | 5226 | 04 | Prepared on 1/5/2024 | 83 | NA | NA | NA | NA | San Bruno: On Huntington Ave From San Bruno Ave To The Entrance Of The Centennial Way Trail. | Bike/ped Facilities, Convert Right Lane On Nb Huntington Ave To A Two-way Cycle | 4 | NA | NA | MTC |  |  | Z3XAM3KDUFA5
DISTRICT | ATPL | 5014(047) | Alameda | 2023-04-27 | NA | NA | NA | NA | 10333000 | 0 | 13250766.94 | UTILITY ISSUE | 5014 | 04 | Prepared on 4/27/2023 | 336 | NA | NA | NA | NA | Central Between Pacific Avenue/main Street And Sherman Street/encinal Avenue. | Reduce Roadway From 4 To 3 Lanes For Bike Lanes And Separated Bikeway, Pedestrian | 3 | NA | NA | MTC |  |  | MGXCH5V9U5C5
DISTRICT | BRLO | 5920(177) | Sonoma County | 2023-01-23 | NA | NA | NA | NA | 192079 | 0 | 182079 | .. | 5920 | 04 | Prepared on 1/23/2023 | 430 | NA | NA | NA | NA | Hauser Bridge Road Over The South Fork Of The Gualala River (county Post Mile 8.76 To 8.78) | Mitigation (tc) | 2 | NA | NA | MTC |  |  | NPTPYM3QJGA1
DISTRICT | STPL | 5137(056) | Richmond | 2023-07-17 | NA | NA | NA | NA | 2821000 | 0 | 4083465 | .. | 5137 | 04 | Prepared on 7/17/2023 | 255 | NA | NA | NA | NA | Richmond: 13th Street Complete Streets Imps | Along 13th St From Harbour Way To Costa Ave: Implement Complete Streets | 1 | NA | NA | MTC |  |  | W856SVG77LP8
DISTRICT | CRAL | 5005(167) | San Jose | 2023-12-21 | NA | NA | NA | NA | 146576 | 0 | 183222 | .. | 5005 | 04 | Prepared on 12/21/2023 | 98 | NA | NA | NA | NA | San Jose: Various Locations In East San Jose: 21st Street From Roosevelt Park To East William | Various Locations In East San Jose: Build Bike Boulevard Corridors That Will | 2 | NA | NA | MTC |  |  | QUA4AULJ8FM3
DISTRICT | STPL | 5030(072) | Vallejo | 2023-07-21 | NA | NA | NA | NA | 1800000 | 0 | 3313282.21 | .. | 5030 | 04 | Prepared on 7/21/2023 | 251 | NA | NA | NA | NA | On Springs Rd From Humboldt St. To Maywood Dr | Pavement Preservation Including Remove And Replace Curb, Gutter, Sidewalk, And | 1 | NA | NA | MTC |  |  | KJKSES96KUN9
DISTRICT | STPLNI | 6480(026) | Alameda County Transportation Commission | 2024-03-06 | NA | NA | NA | NA | 289346.84 | 0 | 326871.71 | .. | 6480 | 04 | Prepared on 3/6/2024 | 22 | NA | NA | NA | NA | County Wide | Srts Program | 3 | NA | NA | MTC |  |  | GMJJYFAA2QJ6
DISTRICT | HSIPL | 6328(110) | City & County Of San Francisco, Mta/parking & Traffic | 2023-11-28 | NA | NA | NA | NA | 1969560 | 0 | 2188400 | .. | 6328 | 04 | Prepared on 11/28/2023 | 121 | NA | NA | NA | NA | Various Intersections And Streets Throughout The Entire City And County Of San Francisco | Enhance Traffic And Pedestrian Safety By Installing New And Replacement Signs With | 1 | NA | NA | MTC |  |  | GSL6KW4Z5UE1
DISTRICT | CPFL | 6364(028) | Sonoma County Transportation Authority | 2024-03-18 | NA | NA | NA | NA | 1500000 | 0 | 1694351 | .. | 6364 | 04 | Prepared on 3/18/2024 | 10 | NA | NA | NA | NA | In Sonoma County, Near Schellville, From 0.1 Miles West Of 8th Street East To 0.2 Miles East | Proposes Roadway And Intersection Improvements To State Route 121 (route 121) At | 1 | NA | NA | MTC |  |  | ZD77LGJBFMJ7
DISTRICT | STPLZ | 5920(056) | Sonoma County | 2024-02-15 | NA | NA | NA | NA | 0 | 0 | 5632 | .. | 5920 | 04 | Prepared on 2/15/2024 | 42 | NA | NA | NA | VAR991007 | Wohler Rd. At Markwest Cr. Br # 20-0139 | Replace Bridge, Local Seismic (tc) | 9 | NA | NA | MTC |  |  | NPTPYM3QJGA1
DISTRICT | ACSTP | 15J7(046) | Santa Cruz County | 2023-08-05 | NA | NA | NA | NA | 0 | 644300 | 644300 | ON HOLD FOR FHWA APPROVAL OF DAF AND 11-J | 5936 | 05 | Prepared on 8/5/2023 | 236 | NA | NA | NA | NA | Hazel Dell Pm 2.35 In Santa Cruz County | Emergency Opening | 1 | NA | NA | MTC |  |  | DQHKDRT8LVY8
DISTRICT | ACSTP | 15J7(065) | Santa Cruz County | 2023-07-26 | NA | NA | NA | NA | 0 | 747527 | 843600 | ON HOLD FOR NEPA AND 11-J | 5936 | 05 | Prepared on 7/26/2023 | 246 | NA | NA | NA | NA | Bear Creek Rd Pm 2.39 In Santa Cruz County | Emergency Opening And Permanent Restoration - Replace Culvert | 1 | NA | NA | MTC |  |  | DQHKDRT8LVY8
DISTRICT | ACSTP | 15J9(036) | Santa Cruz County | 2023-08-05 | NA | NA | NA | NA | 0 | 58118 | 65000 | ON HOLD FOR FHWA APPROVAL OF DAF AND 11-J | 5936 | 05 | Prepared on 8/5/2023 | 236 | NA | NA | NA | NA | Ice Cream Grade Pm 1.24 In Santa Cruz County | Emergency Opening And Permanent Restoration | 1 | NA | NA | MTC |  |  | DQHKDRT8LVY8
DISTRICT | ACSTP | 15J7(141) | Santa Cruz County | 2023-08-11 | NA | NA | NA | NA | 0 | 99650 | 99650 | ON HOLD FOR REVISED DAF | 5936 | 05 | Prepared on 8/11/2023 | 230 | NA | NA | NA | NA | East Cliff Dr Pm 1.69 In Santa Cruz County | Emergency Opening | 1 | NA | NA | MTC |  |  | DQHKDRT8LVY8
DISTRICT | ACSTP | 15J7(142) | Santa Cruz County | 2023-08-05 | NA | NA | NA | NA | 0 | 78250 | 88000 | ON HOLD FOR FHWA APPROVAL OF DAF AND 11-J | 5936 | 05 | Prepared on 8/5/2023 | 236 | NA | NA | NA | NA | Bear Creek Rd Pm 4.18 In Santa Cruz County | Emergency Opening And Permanent Restoration | 1 | NA | NA | AMBAG |  |  | DQHKDRT8LVY8
DISTRICT | ACSTP | 15J7(149) | Santa Cruz County | 2023-08-11 | NA | NA | NA | NA | 0 | 245060 | 245060 | ON HOLD FOR REVISED DAF | 5936 | 05 | Prepared on 8/11/2023 | 230 | NA | NA | NA | NA | Redwood Lodge Rd Pm 2.25 In Santa Cruz County | Emergency Opening | 1 | NA | NA | MTC |  |  | DQHKDRT8LVY8
DISTRICT | ACSTP | 15J7(150) | Santa Cruz County | 2023-12-26 | NA | NA | NA | NA | 0 | 423020 | 423020 | ON HOLD FOR R.W CERT AND 11-J | 5936 | 05 | Prepared on 12/26/2023 | 93 | NA | NA | NA | NA | Upper East Zayante Rd Pm 2.51 In Santa Cruz County | Emergency Opening | 1 | NA | NA | AMBAG |  |  | DQHKDRT8LVY8
DISTRICT | ACSTP | 15J7(155) | Santa Cruz County | 2023-08-11 | NA | NA | NA | NA | 0 | 23000 | 23000 | ON HOLD FOR REVISED DAF | 5936 | 05 | Prepared on 8/11/2023 | 230 | NA | NA | NA | NA | Eureka Canyon Rd Pm 5.09 In Santa Cruz County | Emergency Opening | 1 | NA | NA | MTC |  |  | DQHKDRT8LVY8
DISTRICT | ACSTP | 15J9(062) | Santa Cruz County | 2024-01-09 | NA | NA | NA | NA | 0 | 109236 | 123000 | ON HOLD FOR REVISED DAF | 5936 | 05 | Prepared on 1/9/2024 | 79 | NA | NA | NA | NA | North Rodeo Gulch Pm 3.77 In Santa Cruz County | Emergency Opening And Permanent Restoration - Repair Slipout | 1 | NA | NA | AMBAG |  |  | DQHKDRT8LVY8
DISTRICT | ACSTP | 15J9(066) | Santa Cruz County | 2023-10-04 | NA | NA | NA | NA | 0 | 83800 | 83800 | ON HOLD FOR REVISED DAF | 5936 | 05 | Prepared on 10/4/2023 | 176 | NA | NA | NA | NA | Granite Creek Rd Pm 0.16 In Santa Cruz County | Emergency Opening | 1 | NA | NA | AMBAG |  |  | DQHKDRT8LVY8
DISTRICT | ACSTP | 15J9(069) | Santa Cruz County | 2024-01-09 | NA | NA | NA | NA | 0 | 69397 | 78000 | ON HOLD FOR REVISED DAF | 5936 | 05 | Prepared on 1/9/2024 | 79 | NA | NA | NA | NA | Glen Canyon Rd Pm 0.39 In Santa Cruz County | Emergency Opening And Permanent Restoration - Replace Culvert | 1 | NA | NA | AMBAG |  |  | DQHKDRT8LVY8
DISTRICT | ACSTP | 15J9(072) | Santa Cruz County | 2023-08-22 | NA | NA | NA | NA | 90100 | 0 | 90100 | ON HOLD FOR FHWA APPROVAL OF DAF AND 11-J | 5936 | 05 | Prepared on 8/22/2023 | 219 | NA | NA | NA | NA | East Zayante Rd Pm 0.48 In Santa Cruz County | Emergency Opening | 1 | NA | NA | MTC |  |  | DQHKDRT8LVY8
DISTRICT | ACSTP | 15J9(073) | Santa Cruz County | 2024-01-09 | NA | NA | NA | NA | 0 | 2085500 | 2085500 | ON HOLD FOR NEPA | 5936 | 05 | Prepared on 1/9/2024 | 79 | NA | NA | NA | NA | Spreckles Dr Pm 0.04 In Santa Cruz County | Emergency Opening - Repair Slipout | 1 | NA | NA | MTC |  |  | DQHKDRT8LVY8
DISTRICT | ACSTP | 15J9(098) | Santa Cruz County | 2023-10-04 | NA | NA | NA | NA | 0 | 215261 | 215261 | ON HOLD FOR NEPA AND 11-J | 5936 | 05 | Prepared on 10/4/2023 | 176 | NA | NA | NA | NA | Eureka Canyon Rd Pm 5.17 In Santa Cruz County | Emergency Opening - Repair Slipout | 1 | NA | NA | AMBAG |  |  | DQHKDRT8LVY8
DISTRICT | ACSTP | 15J9(099) | Santa Cruz County | 2023-10-04 | NA | NA | NA | NA | 0 | 109475 | 109475 | ON HOLD FOR REVISED DAF | 5936 | 05 | Prepared on 10/4/2023 | 176 | NA | NA | NA | NA | Hazel Dell Rd Pm 1.40 In Santa Cruz County | Emergency Opening | 1 | NA | NA | AMBAG |  | Warning | DQHKDRT8LVY8
DISTRICT | ACSTP | 15J9(101) | Santa Cruz County | 2023-08-31 | NA | NA | NA | NA | 184089 | 0 | 184089 | ON HOLD FOR NEPA AND 11-J | 5936 | 05 | Prepared on 8/31/2023 | 210 | NA | NA | NA | NA | Hazel Dell Rd Pm 2.56 In Santa Cruz County | Emergency Opening - Repair Slipout | 1 | NA | NA | COFCG |  |  | DQHKDRT8LVY8
DISTRICT | ACSTP | 15J9(104) | Santa Cruz County | 2023-08-28 | NA | NA | NA | NA | 109236 | 0 | 123000 | ON HOLD FOR NEPA AND 11-J | 5936 | 05 | Prepared on 8/28/2023 | 213 | NA | NA | NA | NA | Hazel Dell Rd Pm 2.64 In Santa Cruz County | Emergency Opening And Permanent Restoration - Repair Slipout | 1 | NA | NA | MCTC |  |  | DQHKDRT8LVY8
DISTRICT | ACSTP | 15J9(123) | Santa Cruz County | 2024-01-09 | NA | NA | NA | NA | 0 | 56118 | 63000 | ON HOLD FOR REVISED DAF | 5936 | 05 | Prepared on 1/9/2024 | 79 | NA | NA | NA | NA | Eureka Canyon Rd Pm 4.75 In Santa Cruz County | Emergency Opening And Permanent Restoration - Repair Slipout | 1 | NA | NA | MCTC |  |  | DQHKDRT8LVY8
DISTRICT | ACSTP | 15J9(125) | Santa Cruz County | 2023-12-27 | NA | NA | NA | NA | 0 | 100383 | 113000 | ON HOLD FOR REVISED DAF | 5936 | 05 | Prepared on 12/27/2023 | 92 | NA | NA | NA | NA | Hazel Dell Rd Pm 2.69 | Emergency Opening And Permanent Restoration | 1 | NA | NA | COFCG |  | negatie or zero funding | DQHKDRT8LVY8
DISTRICT | ACSTP | 15J9(131) | Santa Cruz County | 2024-01-09 | NA | NA | NA | NA | 0 | 56118 | 63000 | ON HOLD FOR REVISED DAF | 5936 | 05 | Prepared on 1/9/2024 | 79 | NA | NA | NA | NA | Eureka Canyon Rd Pm 3.5 In Santa Cruz County | Emergency Opening And Permanent Restoration - Repair Slipout | 1 | NA | NA | COFCG |  | negatie or zero funding | DQHKDRT8LVY8
DISTRICT | ACSTP | 15J9(132) | Santa Cruz County | 2023-08-30 | NA | NA | NA | NA | 58462 | 0 | 65650 | ON HOLD FOR NEPA AND 11-J | 5936 | 05 | Prepared on 8/30/2023 | 211 | NA | NA | NA | NA | Laurel Glen Rd Pm 1.45 In Santa Cruz County | Emergency Opening And Permanent Restoration - Repair Slipout | 1 | NA | NA | MCTC |  | Warning | DQHKDRT8LVY8
DISTRICT | ACSTP | 15J9(141) | San Benito County | 2023-12-01 | NA | NA | NA | NA | 0 | 382500 | 382500 | ON HOLD FOR FHWA APPROVAL OF DAF, NEPA, AND 11-J | 5943 | 05 | Prepared on 12/1/2023 | 118 | NA | NA | NA | NA | San Juan Canyon Rd Pm 6.99 In San Benito County | Emergency Opening | 1 | NA | NA | MCTC |  | Warning | UX1PHLRE4QQ3
DISTRICT | ACSTP | 15J9(142) | San Benito County | 2023-12-01 | NA | NA | NA | NA | 0 | 291400 | 291400 | ON HOLD FOR FHWA APPROVAL OF DAF, NEPA, AND 11-J | 5943 | 05 | Prepared on 12/1/2023 | 118 | NA | NA | NA | NA | San Juan Canyon Rd Pm 7.58 In San Benito County | Emergency Opening | 1 | NA | NA | MCTC |  | Warning | UX1PHLRE4QQ3
DISTRICT | BRLO | 5943(055) | San Benito County | 2023-11-16 | NA | NA | NA | NA | 3383750 | 0 | 4049356 | Hold for right of way certification. | 5943 | 05 | Prepared on 11/16/2023 | 133 | NA | NA | NA | GP HBRR | Rosa Morada Bridge #43c0041 | Bridge Replacement (tc) | 8 | NA | NA | MCTC |  | Warning | UX1PHLRE4QQ3
DISTRICT | BRLO | 5942(226) | Fresno County | 2023-06-19 | NA | NA | NA | NA | 1400000 | 0 | 1400000 | .. | 5942 | 06 | Prepared on 6/19/2023 | 283 | NA | NA | NA | FRE040501 | Bridge 42c0413 On Lincoln Avenue Over Travers Creek | Bridge Replacement (tc) | 5 | NA | NA | MCTC |  | Warning | NCT6WZHM8NE1
DISTRICT | BRLO | 5942(227) | Fresno County | 2023-06-19 | NA | NA | NA | NA | 1100000 | 0 | 1100000 | .. | 5942 | 06 | Prepared on 6/19/2023 | 283 | NA | NA | NA | FRE040501 | Bridge 42c0417 On Parlier Avenue Over Travers Creek | Replace 2 Lane Bridge With 2 Lane Bridge (tc) | 5 | NA | NA | COFCG |  | Warning | NCT6WZHM8NE1
DISTRICT | BRLO | 5946(140) | Tulare County | 2023-06-15 | NA | NA | NA | NA | 3412500 | 0 | 3412500 | .. | 5946 | 06 | Prepared on 6/15/2023 | 287 | NA | NA | NA | NA | Bridge 46c0263 On Ave. 174 Over Friant-kern Canal | Replace 2 Lane Bridge With 2 Lane Bridge (tc) | 5 | NA | NA | COFCG |  | Warning | NN1GT1HPGN78
DISTRICT | BRLO | 5946(142) | Tulare County | 2023-06-15 | NA | NA | NA | NA | 2400000 | 0 | 2400000 | .. | 5946 | 06 | Prepared on 6/15/2023 | 287 | NA | NA | NA | NA | Bridge 46c0340 On Avenue 428 Over Sand Creek | Replace 2 Lane Bridge With 2 Lane Bridge (tc) | 5 | NA | NA | MCAG |  | Warning | NN1GT1HPGN78
DISTRICT | BRLO | 5942(237) | Fresno County | 2023-11-01 | NA | NA | NA | NA | 1952000 | 0 | 1952000 | .. | 5942 | 06 | Prepared on 11/1/2023 | 148 | NA | NA | NA | NA | Bridge 42c0486 On North Chateau Fresno Over Houghton Canal | Replace 2 Lane Bridge With 2 Lane Bridge (tc) | 5 | NA | NA | COFCG |  | Warning | NCT6WZHM8NE1
DISTRICT | BPMP | 5942(240) | Fresno County | 2023-06-19 | NA | NA | NA | NA | 1360600 | 0 | 1536881 | .. | 5942 | 06 | Prepared on 6/19/2023 | 283 | NA | NA | NA | NA | Pm00009 12 Bridges: 42c0097, 42c0104, 42c0178, 42c0179, 42c0328, 42c0367, 42c0455, 42c0458, | Bridge Preventative Maintenance Project | 5 | NA | NA | MCTC |  | Warning | NCT6WZHM8NE1
DISTRICT | CML | 5941(102) | Madera County | 2024-03-20 | NA | NA | NA | NA | 635000 | 0 | 635000 | PENDING RFA FOR CON | 5941 | 06 | Prepared on 3/20/2024 | 8 | NA | NA | NA | NA | Road 225 From Willow Creek Drive To Road 228 | Pedestrian Path And Bike Path (tc) | 4 | NA | NA | MCAG |  | Warning | KNPYKHLWNKE1
DISTRICT | BRLO | 5942(271) | Fresno County | 2024-03-27 | NA | NA | NA | NA | 88000 | 0 | 88000 | .. | 5942 | 06 | Prepared on 3/27/2024 | 1 | NA | NA | NA | NA | Bridge 42c0097 On South El Dorado Over Arroyo Pasajero Creek | Replace 2 Lane Bridge With 2 Lane Bridge (tc) | 2 | NA | NA | MCTC |  | Warning | NCT6WZHM8NE1
DISTRICT | BPMP | 5157(104) | Madera | 2023-11-01 | NA | NA | NA | NA | 128439 | 0 | 145080 | .. | 5157 | 06 | Prepared on 11/1/2023 | 148 | NA | NA | NA | NA | Pm00133 - Bridges 41c0009, 41c0043 & 41c0155 In The City Of Madera | Bridge Preventative Maintenance Program Project | 6 | NA | NA | MCTC |  | Warning | GM14DSJ51PR1
DISTRICT | BPMP | 5945(103) | Kings County | 2023-11-02 | NA | NA | NA | NA | 221325 | 0 | 250000 | PROJECT LIST UPDATE AFTER AWARD | 5945 | 06 | Prepared on 11/2/2023 | 147 | NA | NA | NA | NA | Pm00144 For 10 Bridges: 45c0006, 45c0015, 45c0033, 45c0044, 45c0081, 45c0095, 45c0096, | Bridge Preventative Maintenance Program (bpmp) Project | 4 | NA | NA | KCOG |  | Warning | MHSYMZNJMZB1
DISTRICT | BPMP | 5060(328) | Fresno | 2023-08-30 | NA | NA | NA | NA | 1692655 | 0 | 1911957 | AGENCY DECIDED TO REBID CONSTRUCTION CONTRACT | 5060 | 06 | Prepared on 8/30/2023 | 211 | NA | NA | NA | NA | Pm00116 5 Bridges: 42c0032, 42c0198, 42c0205, 42c0217 & 42c0611 | Bridge Preventative Maintenance Program | 4 | NA | NA | KCOG |  | Warning | ELPGKCJ7DJK7
DISTRICT | STPL | 5060(361) | Fresno | 2024-03-18 | NA | NA | NA | NA | 2193400 | 0 | 2193400 | .. | 5060 | 06 | Prepared on 3/18/2024 | 10 | NA | NA | NA | NA | Mckinely Avenue From Hughes To Marks Avenues. | Widen Mckinley Avenue To Include New Infrastructure To Consist Of Concrete Curb, | 3 | NA | NA | KCOG |  | Warning | ELPGKCJ7DJK7
DISTRICT | STPL | 5060(376) | Fresno | 2023-07-03 | NA | NA | NA | NA | 1632148 | 0 | 2858800 | CEQA APPROVAL | 5060 | 06 | Prepared on 7/3/2023 | 269 | NA | NA | NA | NA | Blackstone Ave. From Minarets To Nees Avenues. | Ac Overlay, Class Ii Bike Lane, Sidewalk, Curb Ramps, Signing And Striping, And | 3 | NA | NA | KCOG |  |  | ELPGKCJ7DJK7
DISTRICT | CML | 5109(266) | Bakersfield | 2024-01-24 | NA | NA | NA | NA | -146034.03 | 0 | -143491.6 | .. | 5109 | 06 | Prepared on 1/24/2024 | 64 | NA | NA | NA | NA | Pacheco Rd Between Stine Rd And Wible Rd. | Construct Multi-use Path | 2 | NA | NA | KCOG |  |  | YUJJHEWCPLZ5
DISTRICT | BRLO | 5946(198) | Tulare County | 2022-10-28 | NA | NA | NA | NA | 220000 | 0 | 220000 | .. | 5946 | 06 | Prepared on 10/28/2022 | 517 | NA | NA | NA | NA | Bridge 46c0208 On Avenue 364 Over Cottonwood Creek | Nepa Mitigation | 1 | NA | NA | KCOG |  |  | NN1GT1HPGN78
DISTRICT | ATPCML | 5109(272) | Bakersfield | 2024-01-25 | NA | NA | NA | NA | 146034.03 | 0 | 146034.03 | .. | 5109 | 06 | Prepared on 1/25/2024 | 63 | NA | NA | NA | NA | Construct A Multi-use Path (6 Miles) Along The Friant-kern Canal In Bakersfield: Bounded By | Construct Class I Multi-use Path. | 3 | NA | NA | MCTC |  | Warning | YUJJHEWCPLZ5
DISTRICT | CML | 5285(025) | Mendota | 2023-06-16 | NA | NA | NA | NA | 2448457 | 0 | 4024671 | Hold for right of way certification. | 5285 | 06 | Prepared on 6/16/2023 | 286 | NA | NA | NA | NA | City Of Mendota; Intersection Of Derrick (sr180) And Oller (sr33) | Construct Roundabout | 1 | NA | NA | MCTC |  | Warning | EUPGJVXPY451
DISTRICT | BRLO | 5157(129) | Madera | 2024-03-14 | NA | NA | NA | NA | 26559 | 0 | 30000 | .. | 5157 | 06 | Prepared on 3/14/2024 | 14 | NA | NA | NA | NA | Bridge 41c0155 On Clark Street Over Madera Irrigation District Canal | Replace 2-lane Timber Bridge With 2-lane Bridge. | 2 | NA | NA | MCTC |  |  | GM14DSJ51PR1
DISTRICT | BPMP | 5109(285) | Bakersfield | 2023-09-07 | NA | NA | NA | NA | 76984 | 0 | 96230 | .. | 5109 | 06 | Prepared on 9/7/2023 | 203 | NA | NA | NA | NA | Pm00171 11 Bridges: 50c0147, 50c0148, 50c0149, 50c0177, 50c0179r&l, 50c0180r&l, 50c0295, | Bridge Preventative Maintenance Project | 1 | NA | NA | MCTC |  |  | YUJJHEWCPLZ5
DISTRICT | CML | 5109(287) | Bakersfield | 2024-03-13 | NA | NA | NA | NA | 336768 | 0 | 380400 | .. | 5109 | 06 | Prepared on 3/13/2024 | 15 | NA | NA | NA | NA | Stockdale Hwy From Renfro Rd To Coffee Rd | Installation Of Adaptive Signal Coordination | 1 | NA | NA | KCOG |  |  | YUJJHEWCPLZ5
DISTRICT | CML | 5109(288) | Bakersfield | 2024-03-15 | NA | NA | NA | NA | 509048 | 0 | 575001 | WAITING FOR EMMISION CACLULATION | 5109 | 06 | Prepared on 3/15/2024 | 13 | NA | NA | NA | NA | H St From White Ln To Panama Ln, Panama Ln From Akers Rd To Parsons Wy | Installation Of Adaptive Signal Coordination | 1 | NA | NA | KCOG |  | Warning | YUJJHEWCPLZ5
DISTRICT | CRPL | 5109(290) | Bakersfield | 2024-03-26 | NA | NA | NA | NA | 605433 | 0 | 708873 | .. | 5109 | 06 | Prepared on 3/26/2024 | 2 | NA | NA | NA | NA | Calloway Dr From Rosedale Hwy To Olive Dr | Installation Of Adaptive Signal Coordination | 1 | NA | NA | MCTC |  | Warning | YUJJHEWCPLZ5
DISTRICT | CRPL | 5109(291) | Bakersfield | 2024-03-26 | NA | NA | NA | NA | 949395 | 0 | 1097400 | .. | 5109 | 06 | Prepared on 3/26/2024 | 2 | NA | NA | NA | NA | Panama Lane From Gosford Rd To Akers Rd | Installation Of Adaptive Signal Coordination | 1 | NA | NA | KCOG |  | Warning | YUJJHEWCPLZ5
DISTRICT | BHLS | 5122(036) | Porterville | 2023-10-06 | NA | NA | NA | NA | 786965.51 | 0 | 891730.99 | .. | 5122 | 06 | Prepared on 10/6/2023 | 174 | NA | NA | NA | TUL04-120 | Bridge 46c0099 On Jaye Street Over The Tule River | Bridge Rehabilitation | 14 | NA | NA | KCOG |  | Warning | NH6YWTB76QK8
DISTRICT | BRLO | 5941(081) | Madera County | 2023-11-01 | NA | NA | NA | NA | 4253200 | 0 | 4253200 | .. | 5941 | 06 | Prepared on 11/1/2023 | 148 | NA | NA | NA | MAD410001 | Bridge 41c0123 On Rd. 427 Over Oak Creek | Replace 2 Lane Bridge With 2 Lane Bridge (tc) | 8 | NA | NA | KCOG |  | Warning | KNPYKHLWNKE1
DISTRICT | BHLS | 5064(078) | Pasadena | 2024-03-21 | NA | NA | NA | NA | 375000 | 0 | 375000 | .. | 5064 | 07 | Prepared on 3/21/2024 | 7 | NA | NA | NA | NA | Holly Street Over Arroyo Bl & Arroyo Seco,0.2 Mi W Ventura Fwy 53c1041 | Bridge Rehabilitation & Seismic Retrofit (tc) | 4 | NA | NA | KCOG |  | Warning | JK7YAK6HPFM6
DISTRICT | BPMPL | 5953(688) | Los Angeles County | 2023-05-10 | NA | NA | NA | NA | 5527643.88 | -5527643.88 | 0 | .. | 5953 | 07 | Prepared on 5/10/2023 | 323 | NA | NA | NA | NA | 31 Bridges Within La County | Bridge Preventive Maintenance Program --- Group 7 & Group 8 (tc) | 3 | NA | NA | KCOG |  | Warning | ZLJUW5L9K685
DISTRICT | BPMPL | 5953(707) | Los Angeles County | 2021-08-11 | NA | NA | NA | NA | 1517507.78 | -1517507.78 | 0 | .. | 5953 | 07 | Prepared on 8/11/2021 | 960 | NA | NA | NA | NA | Six Bridges In The Cities Of Cerritos, Compton, Downey, Lakewood, Paramount, And La Palma | Bridge Preventative Maintenance Program - Group 9 (tc) | 2 | NA | NA | SACOG |  | Warning | ZLJUW5L9K685
DISTRICT | BPMPL | 5953(708) | Los Angeles County | 2023-05-10 | NA | NA | NA | NA | 1468374.07 | -1468374.07 | 0 | .. | 5953 | 07 | Prepared on 5/10/2023 | 323 | NA | NA | NA | NA | 25 Bridges Within The Unincoperated Areas Of La County | Bridge Preventive Maintenance Program --- Group 10 (tc) | 2 | NA | NA | NON-MPO |  | Warning | ZLJUW5L9K685
DISTRICT | CMLNI | 5953(717) | Los Angeles County | 2024-02-14 | NA | NA | NA | NA | -1079928 | 0 | -1574500 | .. | 5953 | 07 | Prepared on 2/14/2024 | 43 | NA | NA | NA | NA | County Of Los Angeles | Non Infrstructure :- - Information Exchange Network Phase Iii - Part 1 | 3 | NA | NA | MTC |  | Warning | ZLJUW5L9K685
DISTRICT | BPMPL | 5953(722) | Los Angeles County | 2020-08-17 | NA | NA | NA | NA | 306891.26 | 2368707.99 | 2694349.25 | .. | 5953 | 07 | Prepared on 8/17/2020 | 1319 | NA | NA | NA | NA | 45 Bridges Within Los Angeles County | Bridge Preventative Maintenance Program - Group 12 &13 (tc) | 1 | NA | NA | KCOG |  | Warning | ZLJUW5L9K685
DISTRICT | BPMPL | 5953(734) | Los Angeles County | 2020-06-24 | NA | NA | NA | NA | 1542519.19 | 0 | 1553769.19 | .. | 5953 | 07 | Prepared on 6/24/2020 | 1373 | NA | NA | NA | NA | 26 Bridges Within La County | Bridge Preventive Maintenance Program - Group 18 &19 (tc) | 1 | NA | NA | SCAG |  | Warning | ZLJUW5L9K685
DISTRICT | ATPL | 5006(855) | Los Angeles | 2023-12-27 | NA | NA | NA | NA | 0 | 0 | 4655552.86 | .. | 5006 | 07 | Prepared on 12/27/2023 | 92 | NA | NA | NA | NA | Downtown Los Angeles, Broadway Between 4th And 6th Streets | Pedestrian Safety Improvements Including Curb Extensions, Widened Sidewalk, | 4 | NA | NA | SCAG |  |  | RNA2HUB4ZBK4
DISTRICT | CML | 5006(863) | Los Angeles | 2023-04-26 | NA | NA | NA | NA | 476000 | 0 | 537670.84 | .. | 5006 | 07 | Prepared on 4/26/2023 | 337 | NA | NA | NA | NA | To Improve Bicycle Ridership, Reduce Traffic Speed And Improve Safety Features Along The | Construction Of Bicycle Friendly Street Treatments | 2 | NA | NA | SCAG |  | Warning | RNA2HUB4ZBK4
DISTRICT | FERPL17 | 5006(897) | Los Angeles | 2024-03-20 | NA | NA | NA | NA | -486423.52 | 0 | -608029.4 | .. | 5006 | 07 | Prepared on 3/20/2024 | 8 | NA | NA | NA | NA | I-405/sepulveda To The West; City Of Los Angeles City Boundary To The North And East, And | Intersection And Corridor Improvements That May Include New Traffic Signals, Left | 4 | NA | NA | SCAG |  | Warning | RNA2HUB4ZBK4
DISTRICT | STPL | 5006(910) | Los Angeles | 2023-10-25 | NA | NA | NA | NA | 500000 | 0 | 500000 | .. | 5006 | 07 | Prepared on 10/25/2023 | 155 | NA | NA | NA | NA | In The City Of Los Angeles, In The Community Of El Sereno, On Huntington Dr. Between Mission | This Project Is To Implement Mobility And Access Improvements That Will Include | 4 | NA | NA | SCAG |  | Warning | RNA2HUB4ZBK4
DISTRICT | ATPL | 5346(011) | Duarte | 2023-01-17 | NA | NA | NA | NA | 2023000 | 0 | 2732846 | HOLD - LOCAL AGENCY NEEDS TO VALIDATE ASSUMED UEI ON SMARTSHEET (7-14-2023). ENTER UEI MANUALLY | 5346 | 07 | Prepared on 1/17/2023 | 436 | NA | NA | NA | NA | Class Ii Bicycle And Pedestrian Gap Closure Improvements On Evergreen Street And Central | Pedestrian And Bike Path | 1 | NA | NA | SCAG |  | Warning | RN8MQ4EKP273
DISTRICT | HSIPL | 5078(037) | Compton | 2023-05-18 | NA | NA | NA | NA | 249800 | 0 | 249800 | .. | 5078 | 07 | Prepared on 5/18/2023 | 315 | NA | NA | NA | NA | Citywide | Install 20 Countdown Pedestrian Heads Improvement | 1 | NA | NA | SCAG |  | Warning | JHDWSLRMX795
DISTRICT | STPL | 5093(023) | Redondo Beach | 2023-07-11 | NA | NA | NA | NA | 1747973 | 0 | 4540549.2 | .. | 5093 | 07 | Prepared on 7/11/2023 | 261 | NA | NA | NA | NA | Manhattan Beach Boulevard Resurfacing From Aviation Blvd Toinglewood Ave | Mbb Resurfacing From Aviation Blvd To Inglewood Ave Includes Resurfacing, Concrete | 1 | NA | NA | SCAG |  | Warning | J6FHPTQ4JDC5
DISTRICT | CRASL | 5405(096) | Simi Valley | 2023-06-01 | NA | NA | NA | NA | 280820 | 0 | 280820 | .. | 5405 | 07 | Prepared on 6/1/2023 | 301 | NA | NA | NA | NA | Citywide Pavement Delineation | Project Consists Of Rehabilitation (repainting) Of Pavement Delineation On Four | 1 | NA | NA | SCAG |  | Warning | PNTGTKKJ37G1
DISTRICT | CRASL | 5129(108) | Oxnard | 2023-06-01 | NA | NA | NA | NA | 866000 | 0 | 866000 | .. | 5129 | 07 | Prepared on 6/1/2023 | 301 | NA | NA | NA | NA | Citywide | Traffic Signal Safety Preemption That Allows Priority For Emergency Vehicles. City | 1 | NA | NA | SCAG |  | Warning | JKLUB9N3DXH7
DISTRICT | BRLS | 5954(108) | San Bernardino County | 2022-08-11 | NA | NA | NA | NA | 41609.1 | 0 | 47000 | .. | 5954 | 08 | Prepared on 8/11/2022 | 595 | NA | NA | NA | 200619 | Glen Helen Parkway Over Cajon Wash, Br. No. 54c-0025 | Bridge Replacement | 6 | NA | NA | SCAG |  | Warning | CFXEZ75TPJ84
DISTRICT | BRLS | 5449(032) | Highland | 2023-02-01 | NA | NA | NA | NA | 1660823 | 0 | 3174500 | WAITING ON HBP EXHIBIT 6D, TO REMOVE HOLD ON FUNDS | 5449 | 08 | Prepared on 2/1/2023 | 421 | NA | NA | NA | NA | Baseline Street Over City Creek East Of Boulder Avenue, Br. No. 54c-0035 | Replace 4 Lane Bridge With 4 Lane Bridge | 4 | NA | NA | AMBAG |  |  | EDJVNAU35G76
DISTRICT | HSIPL | 5205(024) | Rialto | 2023-12-06 | NA | NA | NA | NA | 18450 | 0 | -238480 | .. | 5205 | 08 | Prepared on 12/6/2023 | 113 | NA | NA | NA | NA | Merrill Avenue Between Maple Avenue And Eucalyptus Avenue; Riverside Avenue Between Agua Mansa | Construct Class Ii & Iii Bike Lanes | 4 | NA | NA | SCAG |  | Warning | X161MBH28NJ8
DISTRICT | BRLS | 6507(003) | San Bernardino County Transportation Authority | 2023-11-03 | NA | NA | NA | NA | 39822830.32 | -39822830.32 | 0 | .. | 6507 | 08 | Prepared on 11/3/2023 | 146 | NA | NA | NA | NA | Mount Vernon Avenue Overhead At The Burlington Northern Santa Fe Railroad Yard From King | Bridge Replacement | 13 | NA | NA | SCAG |  | Warning | D36ZJBWRKJK1
DISTRICT | ATPLNI | 5033(054) | San Bernardino | 2024-01-26 | NA | NA | NA | NA | -32272.1 | 0 | -32272.1 | .. | 5033 | 08 | Prepared on 1/26/2024 | 62 | NA | NA | NA | NA | 48th Street From Magnolia Street To Reservoir Drive, Pepper Avenue From Randall Avenue To | Non-infrastructure Educational And Encouragement Activities (tc) | 3 | NA | NA | SCAG |  | Warning | EJLMHR1CMKM7
DISTRICT | HSIPL | 5033(057) | San Bernardino | 2024-02-09 | NA | NA | NA | NA | 0 | 0 | 0 | .. | 5033 | 08 | Prepared on 2/9/2024 | 48 | NA | NA | NA | NA | Forty-nine (49) Signalized Intersections On Mount Vernon Avenue From Highland Avenue To | Install Advanced Dilemma Zone Detection System | 3 | NA | NA | SCAG |  | Warning | EJLMHR1CMKM7
DISTRICT | CPFCDS | 5220(010) | Needles | 2024-01-29 | NA | NA | NA | NA | 0 | 0 | -232592.36 | UEI NOT CONFIRMED- REJECT | 5220 | 08 | Prepared on 1/29/2024 | 59 | NA | NA | NA | NA | Various Streets: Coronado St, Erin Dr, Loop, Collins St, Orange St, Park Ave, Highland St, L | Grind Existing Asphalt Concrete Pavement, Install Petronat And Construct 2" | 2 | NA | NA | SCAG |  | Warning | T9NEL5GM8SF1
DISTRICT | CMLSTPN | 6507(040) | San Bernardino County Transportation Authority | 2024-02-19 | NA | NA | NA | NA | 76148124 | 0 | 329148610 | .. | 6507 | 08 | Prepared on 2/19/2024 | 38 | NA | NA | NA | NA | I-15 Express Lanes (contract 1): Construct 1 Exp. Lane In Each Direction Between Cantu- | Toll Express Lanes - Hov Lane | 1 | NA | NA | SCAG |  | Warning | D36ZJBWRKJK1
DISTRICT | CPFCDSL | 5125(027) | Bishop | 2023-11-21 | NA | NA | NA | NA | 60000 | 0 | 67775 | .. | 5125 | 09 | Prepared on 11/21/2023 | 128 | NA | NA | NA | NA | South Warren Street Between West Line Street And West South Street | This Project Will Replace The Full Width 40-foot Pavement Section And Improve | 1 | NA | NA | SCAG |  | Warning | VWNLTLW4FWJ1
DISTRICT | RPL | 5932(076) | Tuolumne County | 2023-08-13 | NA | NA | NA | NA | 3284000 | 0 | 3284000 | THIS IS SOF, NOT FED | 5932 | 10 | Prepared on 8/13/2023 | 228 | NA | NA | NA | NA | Along Mono Way (old Route 108) Between Peaceful Oak Road And Via Este Road | Construct Operational And Safety Improvements | 1 | NA | NA | SCAG |  |  | NZ5KFMZLPMB9
DISTRICT | CML | 5165(081) | Turlock | 2022-07-22 | NA | NA | NA | NA | 1100000 | 0 | 1952182.5 | MISSING JUSTIFICATION FOR PED EXTENSION. USE OF TC? FTIP NOT APPROVED. | 5165 | 10 | Prepared on 7/22/2022 | 615 | NA | NA | NA | NA | Main St. And Tegner Rd. Intersection | Intersection Improvements (tc) | 3 | NA | NA | SCAG |  | Warning | JDYXAB12QLG1
DISTRICT | CML | 5059(222) | Modesto | 2023-02-01 | NA | NA | NA | NA | 0 | 0 | 0 | COST ESTIMATE; SUPPLEMENTAL WORK ON FL | 5059 | 10 | Prepared on 2/1/2023 | 421 | NA | NA | NA | NA | 11th St & Needham Ave; 1st St & H St; And Paradise Ave & H St | Upgrade Traffic Signals; Bid Alternatives (tc) | 6 | NA | NA | SCAG |  |  | C9NNEMEHETD8
DISTRICT | CML | 5254(030) | Atwater | 2024-03-18 | NA | NA | NA | NA | -70360 | 0 | -41084 | .. | 5254 | 10 | Prepared on 3/18/2024 | 10 | NA | NA | NA | NA | City Of Atwater Downtown - Includes Grove Ave, Fir Ave, Elm Ave, Drakeley Ave, Cedar Ave, | Atwater Ped Improvements To Connect With Downtown (phase 1) - Pedestrian And Bike | 4 | NA | NA | SCAG |  |  | FFMEDABPXQM7
DISTRICT | STPL | 6089(095) | Stanislaus Council Of Governments | 2023-06-02 | NA | NA | NA | NA | 2482961 | 0 | 13532961 | URBANIZED CODE & SHORT CRRSAA FUNDS | 6089 | 10 | Prepared on 6/2/2023 | 300 | NA | NA | NA | NA | Sr132- Dakota Avenue To Gates Road | Replace The Current Two-lane Highway With A Four-lane Access Controlled | 1 | NA | NA | SCAG |  |  | D9JKHAL5D2R1
DISTRICT | HSIPL | 5932(108) | Tuolumne County | 2024-02-19 | NA | NA | NA | NA | 36000 | 0 | 40000 | .. | 5932 | 10 | Prepared on 2/19/2024 | 38 | NA | NA | NA | NA | Various Locations Throughout Tuolumne County | Upgrade Existing Guardrails And End Treatments | 1 | NA | NA | SCAG |  |  | NZ5KFMZLPMB9
DISTRICT | CML | 5940(154) | Mariposa County | 2024-01-19 | NA | NA | NA | NA | 175000 | 0 | 175000 | .. | 5940 | 10 | Prepared on 1/19/2024 | 69 | NA | NA | NA | NA | The Unincorporated Community Of Mariposa | Install Pedestrian Access From Existing Sidewalk On Stroming Rpad To Mariposa | 1 | NA | NA | SACOG |  |  | L63AEQY86BZ4
DISTRICT | ACSTP | 15J9(192) | Stanislaus County | 2024-03-12 | NA | NA | NA | NA | 0 | 200000 | 200000 | .. | 5938 | 10 | Prepared on 3/12/2024 | 16 | NA | NA | NA | NA | Pm 13 - Del Puerto Canyon Road In Stanislaus County | Emergency Opening And Restoration | 1 | NA | NA | NON-MPO |  |  | JVUBT686JGX7
DISTRICT | ATPSB1L | 6066(151) | San Diego Association Of Governments | 2023-10-09 | NA | NA | NA | NA | 11743000 | 0 | 23187000 | .. | 6066 | 11 | Prepared on 10/9/2023 | 171 | NA | NA | NA | NA | In The City Of San Diego, Along Estrella Ave: From Orange Ave To University Ave; And Along | Construct 2.8 Miles Of Separated And Buffered Bike Lanes; Install High-visibility | 1 | NA | NA | MTC |  |  | CU82DUZEEL81
DISTRICT | BRLS | 5957(084) | San Diego County | 2023-11-13 | NA | NA | NA | NA | 398385 | 0 | 450000 | .. | 5957 | 11 | Prepared on 11/13/2023 | 136 | NA | NA | NA | CAL44 | Buckman Springs Rd. @ Cottonwood Creek (br #57c-0270) | Replacing Existing Bridge | 4 | NA | NA | MTC |  |  | GYNSUBBEJ6L8
DISTRICT | BPMPL | 5073(077) | Orange | 2023-04-11 | NA | NA | NA | NA | 1474661 | 0 | 1665720 | .. | 5073 | 12 | Prepared on 4/11/2023 | 352 | NA | NA | NA | ORA020501 | Various Bridge Locations Throughout The City Of Orange, Pm00086 | Bridge Preventive Maintenance Investigations | 3 | NA | NA | MTC |  |  | KF72Q5W8MG44
DISTRICT | BRLO | 5955(087) | Orange County | 2023-06-15 | NA | NA | NA | NA | 104000 | 0 | 104000 | .. | 5955 | 12 | Prepared on 6/15/2023 | 287 | NA | NA | NA | ORA020501 | Silverado Canyon Road Over Ladd Creek, Br. No. 55c-0175 | Bridge Replacement (tc) | 3 | NA | NA | NON-MPO |  | Warning | FTL9JMLK3727
DISTRICT | CML | 5955(114) | Orange County | 2022-06-29 | NA | NA | NA | NA | 600000 | 0 | 2218795 | AWAITING POST PROGRAMMING APPROVAL FROM MPO | 5955 | 12 | Prepared on 6/29/2022 | 638 | NA | NA | NA | NA | Santa Ana Gardens Channel Bikeway Extension Project - Class I, 0.75 Bikeway Along The Santa | Class I, 0.75 Mile Bikeway Along The Santa Ana Gardens Channel From West Monta | 2 | NA | NA | MTC |  |  | FTL9JMLK3727
DISTRICT | CRAL | 5151(032) | Newport Beach | 2023-05-31 | NA | NA | NA | NA | 252095 | 0 | 1320000 | .. | 5151 | 12 | Prepared on 5/31/2023 | 302 | NA | NA | NA | NA | Von Karman Avenue From Campus Drive To Macarthur Boulevard | The City Proposes Grinding And Overlaying The Asphalt Concrete Pavement To | 1 | NA | NA | NON-MPO |  |  | FPFYQSEFJ8M3
DISTRICT | STPL | 6203(070) | Caltrans | 2024-03-27 | NA | NA | NA | NA | 3000000 | 0 | 3000000 | .. | 6203 | 03 | Prepared on 3/27/2024 | 1 | NA | NA | NA | NA | I-80 And Us 50 In Solano, Yolo, And Sacramento Counties | On I-80 From The I-80/kidwell Road Interchange In Solano County, Through Yolo | 1 | NA | NA | SHASTA
DISTRICT | HP21LN | 6208(021) | Caltrans | 2021-09-30 | NA | NA | NA | NA | 0 | 0 | -631799.26 | .. | 6208 | 08 | Prepared on 9/30/2021 | 910 | NA | NA | NA | 44810 | I-10/tippecanoe Ave Interchange From 1.01 Miles West To 1.02 Miles East Of I/c | I-10/tippecanoe Ave I/c Improvements (tc) | 3 | NA | NA | NON-MPO
DISTRICT | STPLN | 6208(036) | Caltrans | 2024-02-19 | NA | NA | NA | NA | 6860764 | 0 | 6860764 | .. | 6208 | 08 | Prepared on 2/19/2024 | 38 | NA | NA | NA | NA | I-15 Express Lanes (contract 1): Construct 1 Exp. Lane In Each Direction Between Cantu- | Toll Express Lanes - Hov Lane (tc) | 1 | NA | NA | MTC
HQ | HIPRPL | 5910(134) | Mendocino County | 2024-03-18 | 2024-03-18 | NA | NA | NA | 75968 | 0 | 75968 | .. | 5910 | 01 | Prepared on 3/18/2024 | 10 | 3 | NA | NA | NA | North State Street, Cr 104, Mp .17 To <58 | Roundabouts At Intersections (tc) | 2 | 2024-03-15 | 2024-03-15 | NON-MPO |  | negatie or zero funding | JKULS1AA5J33
HQ | BRLO | 5919(087) | Placer County | 2024-03-08 | 2024-03-27 | NA | NA | NA | -52559.07 | 0 | -67355.07 | .. | 5919 | 03 | Prepared on 3/8/2024 | 1 | 34 | NA | NA | NA | Bowman Road At Uprr Xing #2 Br. No. 19c-0062 | Bridge Rehabilitation (tc) | 7 | 2024-02-22 | 2024-03-12 | SACOG |  | Warning | L786NC553FC1
HQ | STPLZ | 5920(137) | Sonoma County | 2024-02-06 | 2024-03-15 | NA | NA | NA | 345762 | 0 | 345762 | .. | 5920 | 04 | Prepared on 2/6/2024 | 13 | 44 | NA | NA | VAR110045 | Wohler Road Over Russian River Br#20c0155 | Seismic Retrofit (tc) | 10 | 2024-01-31 | 2024-03-14 | MTC |  |  | NPTPYM3QJGA1
HQ | CML | 5177(033) | South San Francisco | 2024-03-12 | 2024-03-21 | NA | NA | NA | 0 | 0 | -975579 | .. | 5177 | 04 | Prepared on 3/12/2024 | 7 | 10 | NA | NA | SM-130013 | El Camino Real (sr82: Pm20.6-20.9) Dr Chestnut To Arroyo Ave | Improve Ped. Crossings, Bulb Out, Ada Ramps | 5 | 2024-03-11 | 2024-03-21 | MTC |  |  | EES4XJFTXC28
HQ | ER | 40A0(089) | Marin County | 2024-03-01 | 2024-03-26 | NA | NA | NA | 0 | 305428 | 345000 | .. | 5927 | 04 | Prepared on 3/1/2024 | 2 | 27 | NA | NA | NA | Marshall-petaluma Rd At Pm 6.40 | Heavy Rain And Saturated Soil Caused Embankment Located On Eb Lane To Slip | 4 | 2024-02-28 | 2024-03-11 | MTC |  |  | DNTFCMS6YND3
HQ | CML | 5239(029) | El Cerrito | 2024-02-28 | 2024-03-21 | NA | NA | NA | 0 | 0 | -1475314 | .. | 5239 | 04 | Prepared on 2/28/2024 | 7 | 24 | NA | NA | NA | Project Will Be Located Along Bart Station Frontage, San Pablo Ave, Cutting Bl, Hill St, | Complete Streets Improvements To Access, Circulation And Safety For Bicyclists, | 5 | 2024-02-26 | 2024-03-20 | MTC |  |  | G2MDQE4KRGU3
HQ | STPL | 5927(131) | Marin County | 2024-03-01 | 2024-03-22 | NA | NA | NA | 270000 | 0 | 375050.5 | .. | 5927 | 04 | Prepared on 3/1/2024 | 6 | 28 | NA | NA | NA | 4 At Terners Drive @ Driveway Entrances To Multi-family Housing Closest To Donahue, 4 At | Improve Pedestrian Accessibility And Safety (new Curbs Ramps) | 2 | 2024-02-23 | 2024-03-07 | MTC |  |  | DNTFCMS6YND3
HQ | STPL | 5005(169) | San Jose | 2024-03-18 | 2024-03-18 | NA | NA | NA | 1629917.53 | -1629917.53 | 0 | .. | 5005 | 04 | Prepared on 3/18/2024 | 10 | 12 | NA | NA | NA | Various Locations In The Downtown Area. | San Jose: Various Locations In The Downtown Area (project Limits Include 3rd St | 3 | 2024-03-06 | 2024-03-14 | MTC |  |  | QUA4AULJ8FM3
HQ | ER | 15J7(107) | Livermore | 2024-03-15 | 2024-03-26 | NA | NA | NA | 0 | 475401.85 | 526406.36 | .. | 5053 | 04 | Prepared on 3/15/2024 | 2 | 39 | NA | NA | NA | Portola Ave From 0.2 Miles Se Of Tranquility Circle To 0.1 Miles Nw Of Tranquility Circle. | Installation Of Temp. Cover, Sandbags, And Fiber Rolls Closely Spaced Together To | 1 | 2024-02-16 | 2024-03-21 | ER NONE |  |  | KGBMZK3CQF36
HQ | STPL | 6510(010) | Napa Valley Transportation Authority | 2024-03-13 | 2024-03-21 | NA | NA | NA | 3000000 | 0 | 4345000 | .. | 6510 | 04 | Prepared on 3/13/2024 | 7 | 21 | NA | NA | NA | Sr-29 From Napa Junction Road To American Canyon Rd | Environmental Analysis For Operational And Multimodal Improvements | 1 | 2024-02-29 | 2024-03-21 | MTC |  | Warning | KTBCYAWLJML5
HQ | STPLNI | 5937(230) | Santa Clara County | 2024-03-14 | 2024-03-14 | NA | NA | NA | 450000 | 0 | 1200000 | .. | 5937 | 04 | Prepared on 3/14/2024 | 14 | 0 | NA | NA | NA | Santa Clara County | The General Plan Transportation Chapter (circulation And Mobility Element) Was | 1 | 2024-03-14 | 2024-03-14 | MTC |  | Warning | DM56XYHGSRA5
HQ | STPL | 6084(304) | Metropolitan Transportation Commission | 2024-03-20 | 2024-03-20 | NA | NA | NA | 2000000 | 0 | 2000000 | .. | 6084 | 04 | Prepared on 3/20/2024 | 8 | 78 | NA | NA | NA | San Francisco Bay Area. | Sf Bay Area: Regionwide: Develop And Maintain The Regional Its Architecture | 1 | 2024-01-02 | 2024-03-20 | MTC |  |  | UKDZHCRW3U97
HQ | CRPL | 6072(037) | Contra Costa Transportation Authority | 2024-03-27 | 2024-03-27 | NA | NA | NA | 1571000 | 0 | 1775000 | .. | 6072 | 04 | Prepared on 3/27/2024 | 1 | 1 | NA | NA | NA | Martinez Amtrak , Ca | Enhance Martinez Amtrak Station To A Shared Mobility Hub: Reconfigure Surface | 1 | 2024-03-26 | 2024-03-27 | MTC |  | Warning | XCKQJHZ2Y3R4
HQ | ER | 32L0(015) | Santa Cruz County | 2024-03-22 | 2024-03-25 | NA | NA | NA | -102124.31 | 0 | -110871.75 | .. | 5936 | 05 | Prepared on 3/22/2024 | 3 | 3 | NA | NA | NA | In The County Of Santa Cruz On North Rodeo Gulch Rd Pm 4.94 | Stabilize Slope And Reconstruct Roadway | 6 | 2024-03-22 | 2024-03-22 | AMBAG |  | Warning | DQHKDRT8LVY8
HQ | BRLS | 5946(170) | Tulare County | 2024-03-22 | 2024-03-26 | NA | NA | NA | 2974608 | -2974608 | 0 | .. | 5946 | 06 | Prepared on 3/22/2024 | 2 | 5 | NA | NA | NA | Bridge 46c0133 On Mountain Road 109 Over White River | Replace 1 Lane Bridge With 2 Lane Bridge. No Added Lane Capacity | 5 | 2024-03-21 | 2024-03-26 | TCAG |  | negatie or zero funding | NN1GT1HPGN78
HQ | CML | 5109(259) | Bakersfield | 2024-03-04 | 2024-03-22 | NA | NA | NA | -254885.91 | 0 | -287909.08 | .. | 5109 | 06 | Prepared on 3/4/2024 | 6 | 51 | NA | NA | NA | Hosking Ave. From Stine Rd. To H St.; Akers Rd. From Hosking Ave. To Panama Ln.; Brundage Ln. | Work Involves Installation Of Fiber Optic Cables, Conduits, Controller, Traffic | 4 | 2024-01-31 | 2024-03-04 | KCOG |  |  | YUJJHEWCPLZ5
HQ | ATPCML | 5146(031) | Coalinga | 2024-03-21 | 2024-03-25 | NA | NA | NA | 344225 | 0 | 540808 | .. | 5146 | 06 | Prepared on 3/21/2024 | 3 | 4 | NA | NA | NA | East Polk St. Between W. Glenn Ave To Hayes St., East Polk St. Between Hayes St And Alicia | Coalinga East Polk Street Bike/ped Safety And Connectivity Initiative: Sidewalks, | 2 | 2024-03-21 | 2024-03-21 | FCOG |  | negatie or zero funding | QJ6KB4438345
HQ | STPL | 5249(032) | Torrance | 2024-03-17 | 2024-03-26 | NA | NA | NA | 0 | 0 | 781306.97 | .. | 5249 | 07 | Prepared on 3/17/2024 | 2 | 7 | NA | NA | NA | Anza Ave From Del Amo Blvd To Sepulveda Blvd | Asphalt Pavement Rehabilitation, Repair Damaged Sidewalks, Curb And Gutter, | 3 | 2024-03-19 | 2024-03-26 | SCAG |  |  | PWA5XB184L37
HQ | BPMPL | 5952(223) | Ventura County | 2024-03-08 | 2024-03-12 | NA | NA | NA | 77520 | 0 | 96900 | .. | 5952 | 07 | Prepared on 3/8/2024 | 16 | NA | NA | NA | NA | 1. Bridge No. 52c0142 - Victoria Ave - 1.3 Mi South Route2. Bridge No. 52c0185 - Koenigstein | Project Consists Of Bridge Preventative Maintenance Work Consisting Of Cleaning, | 1 | NA | NA | SCAG |  |  | NHJ2G6B4WLH5
HQ | CML | 5399(029) | California City | 2024-03-14 | 2024-03-14 | NA | NA | NA | 846966 | 0 | 1023095 | .. | 5399 | 09 | Prepared on 3/14/2024 | 14 | 3 | NA | NA | NA | On Redwood Blvd. From 560-ft. East Of Hacienda Blvd. To 98th St. In The City Of California | This Project Includes Paving An Unpaved Section Of Roadway And Shoulders, | 1 | 2024-03-11 | 2024-03-14 | KCOG |  |  | L2GLQ2NMLST9
HQ | RPSTPL | 5947(065) | Mono County | 2024-02-27 | 2024-03-22 | NA | NA | NA | 3748000 | 0 | 3748000 | .. | 5947 | 09 | Prepared on 2/27/2024 | 6 | 24 | NA | NA | NA | Eastside Lane From Highway 395 To Offal Road And From Cunningham Lane To Topaz Lane In Walker | Road Rehabilitation (tc). Rehabilitation Of Existing Pavement, Rehabilitation | 1 | 2024-02-27 | 2024-03-22 | NON-MPO |  | Warning
HQ | ACSTP | 15Y0(021) | Inyo County | 2024-03-18 | 2024-03-18 | NA | NA | NA | 0 | 40000 | 40000 | .. | 5948 | 09 | Prepared on 3/18/2024 | 10 | 28 | NA | NA | NA | Death Valley Road | Backfill Shoulder And Compact As Necessary. Patch Any Missing Asphalt. Approx. 200 | 1 | 2024-02-19 | 2024-03-18 | NON-MPO |  |  | EU9KBPLKZ5K5
HQ | ACSTP | 15Y0(022) | Inyo County | 2024-03-18 | 2024-03-18 | NA | NA | NA | 0 | 30000 | 30000 | .. | 5948 | 09 | Prepared on 3/18/2024 | 10 | 28 | NA | NA | NA | Gill Station Coso Rd. | Approximately 3,500 Sf With A Depth Of More That 4f | 1 | 2024-02-19 | 2024-03-18 | NON-MPO |  |  | EU9KBPLKZ5K5
HQ | ACSTP | 15Y0(023) | Inyo County | 2024-03-18 | 2024-03-18 | NA | NA | NA | 0 | 96000 | 96000 | .. | 5948 | 09 | Prepared on 3/18/2024 | 10 | 28 | NA | NA | NA | Horseshoe Meadows Road | The Damaged Asphalt Sections Were Repaired That Was Approximately 288 Sf As Well | 1 | 2024-02-19 | 2024-03-18 | NON-MPO |  |  | EU9KBPLKZ5K5
HQ | ACSTP | 15Y0(024) | Inyo County | 2024-03-18 | 2024-03-18 | NA | NA | NA | 0 | 170000 | 170000 | .. | 5948 | 09 | Prepared on 3/18/2024 | 10 | 28 | NA | NA | NA | Onion Valley Road | Remove And Replace Damaged Asphalt. Fill Sinkhole With Material And Repair Asphalt | 1 | 2024-02-19 | 2024-03-18 | NON-MPO |  |  | EU9KBPLKZ5K5
HQ | ACSTP | 15Y0(025) | Inyo County | 2024-03-18 | 2024-03-18 | NA | NA | NA | 0 | 200000 | 200000 | .. | 5948 | 09 | Prepared on 3/18/2024 | 10 | 28 | NA | NA | NA | Trona Wildrose Road | Remove Broken Asphalt And Backfill With Material An Area Of 1,900 Sf. Compact | 1 | 2024-02-19 | 2024-03-18 | NON-MPO |  |  | EU9KBPLKZ5K5
HQ | BRLS | 5929(237) | San Joaquin County | 2024-03-25 | 2024-03-26 | NA | NA | NA | -308708.5 | 0 | -348704.5 | .. | 5929 | 10 | Prepared on 3/25/2024 | 2 | 1 | NA | NA | SJ07-3002 | Peltier Road Over Mokelumne River (bridge 29c0037) | Bridge Replacement | 6 | 2024-03-25 | 2024-03-25 | SJCOG |  | Warning | L3XZK6UCWTF3
HQ | CMLNI | 5059(263) | Modesto | 2024-03-26 | 2024-03-27 | NA | NA | NA | 822250 | 0 | 822250 | .. | 5059 | 10 | Prepared on 3/26/2024 | 1 | 5 | NA | NA | NA | 1010 10th St, In Modesto | Traffic Operations Center Upgrade (tc) | 1 | 2024-03-22 | 2024-03-22 | STANCOG |  | Warning | C9NNEMEHETD8
HQ | STPL | 5929(332) | San Joaquin County | 2024-03-20 | 2024-03-20 | NA | NA | NA | 600000 | 0 | 600000 | .. | 5929 | 10 | Prepared on 3/20/2024 | 8 | 6 | NA | NA | NA | The Project Located Northeast Of City Of Stockton, From Highway 26 To Eight Mile Road | Resurfacing Approximately 4.0 Miles Of Existing Rural Roadway. (tc) | 1 | 2024-03-14 | 2024-03-18 | SJCOG |  |  | L3XZK6UCWTF3
HQ | HPLULN | 6202(007) | Caltrans | 2024-03-07 | 2024-03-27 | NA | NA | NA | -2940 | 0 | -2940 | .. | 6202 | 02 | Prepared on 3/7/2024 | 1 | 69 | NA | NA | NA | Hwy 299 Between Trinity & Shasta Counties; Approx 20 Miles West Of Redding | Hwy Realignment (tc) | 2 | 2024-01-18 | 2024-03-13 | NON-MPO
HQ | CPFDS | 6204(136) | Caltrans | 2024-03-19 | 2024-03-21 | NA | NA | NA | 1000000 | 0 | 44000000 | .. | 6204 | 04 | Prepared on 3/19/2024 | 7 | 3 | NA | NA | NA | San Mateo: At The Us 101/sr 92 Interchange: | Improve Traffic Flow, Safety And Increase Mobility By Minimizing Traffic Conflict | 1 | 2024-03-18 | 2024-03-19 | MTC
HQ | CPFCDSL | 5914(133) | Lake County | 2024-03-08 | 2024-03-08 | NA | NA | NA | 55924 | 0 | 55924 | .. | 5914 | 01 | Prepared on 3/8/2024 | 20 | 16 | NA | NA | NA | Konocti Road In Kelseyville From Cole Creek Bridge To Oak Hills Lane | Improve Sidewalks, Crosswalks, And Bike Lanes Along Konocti Road In Kelseyville. | 1 | 2024-02-21 | 2024-03-04 | NON-MPO |  |  | PMJGFQ26A8A8
HQ | BRLS | 5906(138) | Shasta County | 2024-03-25 | 2024-03-25 | NA | NA | NA | 480000 | 0 | 600000 | .. | 5906 | 02 | Prepared on 3/25/2024 | 3 | 27 | NA | NA | NA | Approx. 4 Miles Southeast Of Anderson, Ca. Approx. 170 Feet East Of Intersection Of Balls | Bridge Replacement Project | 1 | 2024-02-27 | 2024-03-25 | SHASTA |  | Warning | N66MAN8T42J5
HQ | BRLO | 5925(090) | El Dorado County | 2024-03-19 | 2024-03-19 | NA | NA | NA | 1550000 | 0 | 1550000 | 3/21, NEED 6D AND BR. DATABASE IS DOWN | 5925 | 03 | Prepared on 3/19/2024 | 9 | 1 | NA | NA | ELD19339 | Mt Murphy Rd Over South Fork American River 0.1 Miles East Of Sr 49. Br. # 25c0004 | Bridge Replacement (tc) | 6 | 2024-03-18 | 2024-03-19 | SACOG |  |  | R8JPSXALG464
HQ | BRLO | 5919(099) | Placer County | 2024-03-18 | 2024-03-19 | NA | NA | NA | 3242500 | 0 | 3242500 | NEED 6-D & BRIDGE DATABASE IS DOWN | 5919 | 03 | Prepared on 3/18/2024 | 9 | 1 | NA | NA | PLA25505 | Yankee Jim Rd Over North American River 1.5 Miles West Of Shirttail Canyon Rd | Bridge Replacement (tc) | 6 | 2024-03-18 | 2024-03-19 | SACOG |  |  | L786NC553FC1
HQ | BRLO | 5916(106) | Yuba County | 2024-03-19 | 2024-03-20 | NA | NA | NA | 1823225 | 0 | 1823225 | .. | 5916 | 03 | Prepared on 3/19/2024 | 8 | 1 | NA | NA | VAR79008 | Spring Valley Road At Little Dry Crk Br. # 16c-0091 ~0.3 Mi West Of Marysville Rd. | Bridge Replacement (tc) | 6 | 2024-03-19 | 2024-03-20 | SACOG |  |  | LH3ELMEX1L73
HQ | LPPRPSB1 | 5288(046) | Folsom | 2024-02-28 | 2024-02-28 | NA | NA | NA | 0 | 0 | 2022312.59 | .. | 5288 | 03 | Prepared on 2/28/2024 | 29 | 6 | NA | NA | NA | In Folsom On White Rock Rd From Prairie City Rd To East Bidwell St. | Construct 4 Lane Road With 8 Foot Shoulders. (class 1 Trail To Be Built In Later | 4 | 2024-02-22 | 2024-02-23 | SACOG |  |  | FTDELPNDKKT7
HQ | BPMPL | 5023(023) | Grass Valley | 2023-12-27 | 2024-03-19 | NA | NA | NA | 73980 | 0 | 110094 | PENDING HBP FUNDS RESERVATION | 5023 | 03 | Prepared on 12/27/2023 | 9 | 91 | NA | NA | NA | Bpmp Varoius Bridges In The City Of Grass Valley | Bridge Preventive Maintenance | 1 | 2023-12-19 | 2024-03-19 | NON-MPO |  | Warning | C6RQEX468X21
HQ | CMLNI | 6236(026) | Sacramento Metropolitan Air Quality Management District | 2024-01-31 | 2024-02-29 | NA | NA | NA | 499999 | 0 | 499999 | .. | 6236 | 03 | Prepared on 1/31/2024 | 28 | 29 | NA | NA | NA | Phase 3 Of Sacramento Emergency Clean Air Transportation Programemission Benefits In Kg/day: | Secat Provides Grant Funds To New Zero And Low Emission Vehicles And Provides Trip | 1 | 2024-01-31 | 2024-02-29 | SACOG |  |  | D95DUST1M9Q5
HQ | CMLNI | 6236(027) | Sacramento Metropolitan Air Quality Management District | 2024-01-31 | 2024-02-29 | NA | NA | NA | 499999 | 0 | 499999 | Hold for FTIP amendment. | 6236 | 03 | Prepared on 1/31/2024 | 28 | 29 | NA | NA | NA | Phase 3 Of Sacramento Emergency Clean Air Transportation Programemission Benefits In Kg/day: | Secat Provides Grant Funds To New Zero And Low Emission Vehicles And Provides Trip | 1 | 2024-01-31 | 2024-02-29 | SACOG |  |  | D95DUST1M9Q5
HQ | CMLNI | 6236(028) | Sacramento Metropolitan Air Quality Management District | 2024-01-31 | 2024-02-29 | NA | NA | NA | 499999 | 0 | 499999 | Hold for FTIP amendment. | 6236 | 03 | Prepared on 1/31/2024 | 28 | 29 | NA | NA | NA | Phase 3 Of Sacramento Emergency Clean Air Transportation Programemission Benefits In Kg/day: | Secat Provides Grant Funds To New Zero And Low Emission Vehicles And Provides Trip | 1 | 2024-01-31 | 2024-02-29 | SACOG |  | Warning | D95DUST1M9Q5
HQ | CMLNI | 6236(029) | Sacramento Metropolitan Air Quality Management District | 2024-01-31 | 2024-02-29 | NA | NA | NA | 499999 | 0 | 499999 | Hold for FTIP amendment. | 6236 | 03 | Prepared on 1/31/2024 | 28 | 29 | NA | NA | NA | Phase 3 Of Sacramento Emergency Clean Air Transportation Programemission Benefits In Kg/day: | Secat Provides Grant Funds To New Zero And Low Emission Vehicles And Provides Trip | 1 | 2024-01-31 | 2024-02-29 | SACOG |  |  | D95DUST1M9Q5
HQ | CMLNI | 6236(030) | Sacramento Metropolitan Air Quality Management District | 2024-01-31 | 2024-02-29 | NA | NA | NA | 499999 | 0 | 499999 | Hold for FTIP amendment. | 6236 | 03 | Prepared on 1/31/2024 | 28 | 29 | NA | NA | NA | Phase 3 Of Sacramento Emergency Clean Air Transportation Programemission Benefits In Kg/day: | Secat Provides Grant Funds To New Zero And Low Emission Vehicles And Provides Trip | 1 | 2024-01-31 | 2024-02-29 | SACOG |  |  | D95DUST1M9Q5
HQ | CMLNI | 6236(031) | Sacramento Metropolitan Air Quality Management District | 2024-01-31 | 2024-02-29 | NA | NA | NA | 499999 | 0 | 499999 | Hold for FTIP amendment. | 6236 | 03 | Prepared on 1/31/2024 | 28 | 29 | NA | NA | NA | Phase 3 Of Sacramento Emergency Clean Air Transportation Programemission Benefits In Kg/day: | Secat Provides Grant Funds To New Zero And Low Emission Vehicles And Provides Trip | 1 | 2024-01-31 | 2024-02-29 | SACOG |  |  | D95DUST1M9Q5
HQ | CMLNI | 6236(032) | Sacramento Metropolitan Air Quality Management District | 2024-01-31 | 2024-02-29 | NA | NA | NA | 499999 | 0 | 499999 | Hold for FTIP amendment. | 6236 | 03 | Prepared on 1/31/2024 | 28 | 29 | NA | NA | NA | Phase 3 Of Sacramento Emergency Clean Air Transportation Programemission Benefits In Kg/day: | Secat Provides Grant Funds To New Zero And Low Emission Vehicles And Provides Trip | 1 | 2024-01-31 | 2024-02-29 | SACOG |  |  | D95DUST1M9Q5
HQ | STPL | 5916(153) | Yuba County | 2024-03-07 | 2024-03-20 | NA | NA | NA | 893000 | 0 | 893000 | .. | 5916 | 03 | Prepared on 3/7/2024 | 8 | 14 | NA | NA | NA | In Unincorporated Yuba County, On Linda Avenue From Hammonton-smartsville Road To North Beale | Pedestrian And Bicycle Improvements To Provide Safe, Multi-modal Access For | 1 | 2024-03-06 | 2024-03-07 | SACOG |  |  | LH3ELMEX1L73
HQ | STPL | 5922(127) | Yolo County | 2024-03-19 | 2024-03-22 | NA | NA | NA | 300000 | 0 | 338869 | .. | 5922 | 03 | Prepared on 3/19/2024 | 6 | 3 | NA | NA | NA | Town Of Esparto, Local Roads East Of Sr-16 | Preliminary Studies Of The Current Drainage Conditions On The Eastern Side Of | 1 | 2024-03-19 | 2024-03-19 | SACOG |  |  | F9LLL27DJFY4
HQ | BPMP | 5030(060) | Vallejo | 2024-03-07 | 2024-03-21 | NA | NA | NA | 10925487 | 0 | 12341000 | .. | 5030 | 04 | Prepared on 3/7/2024 | 7 | 42 | NA | NA | NA | Mare Island Causeway (g Street) Bridge Br No. 23c0248 | Preventive Maintenance Including Concrete Repairs On Supporting Piers, Precast | 5 | 2024-02-08 | 2024-03-21 | MTC |  |  | KJKSES96KUN9
HQ | ATPLNI | 5935(075) | San Mateo County | 2024-02-16 | 2024-02-16 | NA | NA | NA | -7651.8 | 0 | -3143651.8 | .. | 5935 | 04 | Prepared on 2/16/2024 | 41 | 8 | NA | NA | NA | San Mateo County: Countywide Including The Unincorporated Areas. | Promote Safe And Active Transportation To And From School | 3 | 2024-02-08 | 2024-02-09 | MTC |  |  | PGEMA4HEP1L5
HQ | STPCMLNI | 6480(013) | Alameda County Transportation Commission | 2024-02-29 | 2024-03-22 | NA | NA | NA | -289345.84 | 0 | -327485.99 | .. | 6480 | 04 | Prepared on 2/29/2024 | 6 | 39 | NA | NA | NA | County Wide- Approximately 300 Public School | Alameda County Safe Routs To School Program Outreach And Education. Work Program | 9 | 2024-02-12 | 2024-02-29 | MTC |  |  | GMJJYFAA2QJ6
HQ | STPL | 5923(123) | Solano County | 2024-03-13 | 2024-03-13 | NA | NA | NA | 0 | 0 | 0 | .. | 5923 | 04 | Prepared on 3/13/2024 | 15 | 5 | NA | NA | NA | Suisun Valley Rd, Abernathy Rd., Mankas Corners Rd., Rockville Rd | Construct 6.3 Miles And 1.94 Miles (non-participating) Of 6 Foot Class 2 Bike | 4 | 2024-03-08 | 2024-03-11 | MTC |  |  | XDLNTFCKM1A6
HQ | STPL | 6272(053) | San Francisco County Transportation Authority | 2023-05-24 | 2024-03-19 | NA | NA | NA | 2250000 | 0 | 5051000 | PROCESS CMAQ TOGETHER WITH ATP AND LPP AFTER MARCH CTC MEETING. | 6272 | 04 | Prepared on 5/24/2023 | 9 | 300 | NA | NA | NA | On Yerba Buena Island Along Hillcrest Rd And Treasure Island Rd. | Build New Two-way Class I Ada Compliant Pedestrian And Bicycle Connections | 3 | 2023-05-24 | 2023-05-26 | MTC |  |  | UX7LNHY4BRD1
HQ | STPL | 5434(027) | Danville | 2024-03-13 | 2024-03-14 | NA | NA | NA | 1605000 | 0 | 4181248 | .. | 5434 | 04 | Prepared on 3/13/2024 | 14 | 10 | NA | NA | NA | Danville: San Ramon Valley Blvd Between Hartz Ave And Southern Town Limits | Improvements Consists Of Pavement Slurry Seal, Pavement Rehabilitation (dig-out | 1 | 2024-03-04 | 2024-03-13 | MTC |  |  | YUPDYZZ1N4Y1
HQ | STPL | 5350(026) | Pacifica | 2024-01-31 | 2024-03-08 | NA | NA | NA | 1000000 | 0 | 2077062 | UEI HAS NOT BEEN CONFIRMED, DO NOT SEND TO FHWA. | 5350 | 04 | Prepared on 1/31/2024 | 20 | 37 | NA | NA | NA | Paloma Avenue, Carmel Avenue And Santa Maria Avenue From Francisco Boulevard To Beach | New Sidewalks, Curb And Gutter, Ada Curb Ramps, Ada Driveways, | 1 | 2024-01-31 | 2024-02-13 | MTC |  |  | DAPMSH8498J9
HQ | STPL | 5332(028) | Saratoga | 2024-03-13 | 2024-03-13 | NA | NA | NA | 443000 | 0 | 500396 | .. | 5332 | 04 | Prepared on 3/13/2024 | 15 | 84 | NA | NA | NA | Citywide Master Plan For Bikeways And Sidewalks | This Project Proposes To Create A Master Plan For Bikeways And Sidewalks In The | 1 | 2023-12-20 | 2024-03-06 | MTC |  |  | ZHGJYJ3Q7SQ1
HQ | ACSTP-ER | 32L0(199) | Santa Cruz County | 2024-01-22 | 2024-02-29 | NA | NA | NA | 0 | 749940 | 846714 | .. | 5936 | 05 | Prepared on 1/22/2024 | 28 | 38 | NA | NA | NA | In The County Of Santa Cruz On Smith Grade Road Pm 0.52 | Gegeotechnical Investigation, Crib Wall, Underdrain System, Structure Backfill And | 6 | 2024-01-22 | 2024-02-29 | AMBAG |  |  | DQHKDRT8LVY8
HQ | ACST-ER | 32L0(425) | Santa Cruz County | 2024-02-12 | 2024-02-26 | NA | NA | NA | 0 | 304109.62 | 343895.94 | .. | 5936 | 05 | Prepared on 2/12/2024 | 31 | 17 | NA | NA | NA | In The County Of Santa Cruz On Highland Way At Spanish Ranch | Prepare Engineered Plans, Soil Nail Wall, Culvert Replacement, Ac Dike, Ac | 6 | 2024-02-09 | 2024-02-22 | AMBAG |  |  | DQHKDRT8LVY8
HQ | ATPSB1 | 5481(022) | Goleta | 2024-02-09 | 2024-02-09 | NA | NA | NA | 15290000 | 0 | 25157322 | Hold for CTC allocation. | 5481 | 05 | Prepared on 2/9/2024 | 48 | 1 | NA | NA | NA | Along San Jose Creek And Sr-217 In The City Of Goleta. | Design And Construct 1.4-mile Multipurpose Path, Bike, And Pedestrian Bridge With | 1 | 2024-02-08 | 2024-02-08 | SBCAG |  | Warning | FWGDH8BMWFZ4
HQ | STPLX | 5025(084) | Santa Cruz | 2023-11-07 | 2024-02-20 | NA | NA | NA | 10000000 | -10000000 | 0 | WAITING FOR CONTRACT AWARD | 5025 | 05 | Prepared on 11/7/2023 | 37 | 105 | NA | NA | NA | Murray St Bridge 36c-0108 | Seismic Retrofit And Barrier Railing | 3 | 2023-11-07 | 2023-12-15 | AMBAG |  |  | RSA8LJM3KAR4
HQ | CML | 5109(260) | Bakersfield | 2024-02-22 | 2024-03-22 | NA | NA | NA | -204209.49 | 0 | -230667.48 | .. | 5109 | 06 | Prepared on 2/22/2024 | 6 | 51 | NA | NA | NA | Rosedale Hwy Between Verdugo Ln And Jet Way And Brimhall Rd Between Calloway Dr. And Jewetta | Interconnect Signals | 4 | 2024-01-31 | 2024-02-22 | KCOG |  |  | YUJJHEWCPLZ5
HQ | CML | 5109(281) | Bakersfield | 2024-02-22 | 2024-03-22 | NA | NA | NA | 459095.4 | 0 | 518576.56 | .. | 5109 | 06 | Prepared on 2/22/2024 | 6 | 51 | NA | NA | NA | Mt. Vernon Avenue From Bernard Street To Panorama Drive | Install Adaptive Signal Coordination | 2 | 2024-01-31 | 2024-02-22 | KCOG |  |  | YUJJHEWCPLZ5
HQ | CML | 5109(286) | Bakersfield | 2024-03-12 | 2024-03-12 | NA | NA | NA | 775080 | 0 | 875500 | SERF MISSING | 5109 | 06 | Prepared on 3/12/2024 | 16 | 5 | NA | NA | NA | White Lane From Buena Vista Rd To Wible Rd | Installation Of Adaptive Traffic Signal Along White Ln Between Buena Vista Rd And | 1 | 2024-03-07 | 2024-03-12 | KCOG |  |  | YUJJHEWCPLZ5
HQ | HSIPL | 5069(013) | Monrovia | 2024-02-28 | 2024-03-22 | NA | NA | NA | 1211000 | 0 | 399183.5 | .. | 5069 | 07 | Prepared on 2/28/2024 | 6 | 38 | NA | NA | HSIP4-07-037 | Huntington Dr./ 5th Ave; Foothill Blvd./sunset Pl & Foothill Blvd/ California Ave | Install Ped Safety Devices And Crosswalk Lighting System, Upgrade Traffic Signals | 5 | 2024-02-13 | 2024-03-22 | SCAG |  |  | EJFRLAQNN918
HQ | HSIPL | 5369(012) | Cudahy | 2024-03-18 | 2024-03-20 | NA | NA | NA | 0 | 0 | 0 | .. | 5369 | 07 | Prepared on 3/18/2024 | 8 | 6 | NA | NA | NA | Salt Lake Ave: From Walnut St. To Patata St. / Atlantic Ave. | Installation Of Pedestrian Safety , Install Class Ii Bike Lanes , Signage Etc. | 5 | 2024-03-14 | 2024-03-20 | SCAG |  |  | UZEDAAHT7K97
HQ | HSIPL | 5112(019) | Azusa | 2024-03-22 | 2024-03-22 | NA | NA | NA | 0 | 0 | -32315 | .. | 5112 | 07 | Prepared on 3/22/2024 | 6 | 2 | NA | NA | NA | One-mile Segment Of Arrow Highway Between Citrus Ave & Approx 500' West Of Azusa Ave. | Install Raised Medians | 5 | 2024-03-20 | 2024-03-22 | SCAG |  |  | RN7VHJX4NBE5
HQ | ATPL | 5251(026) | Ojai | 2024-03-22 | 2024-03-26 | NA | NA | NA | 2103000 | 0 | 2103000 | .. | 5251 | 07 | Prepared on 3/22/2024 | 2 | 4 | NA | NA | NA | Bike And Pedestrian Improvements On Sr 33 And Sr 150 Between El Roblar And Gridley Road | Adding A Clasii Bike Lane In Each Direction For The Entire Project Limit, 16 | 3 | 2024-03-22 | 2024-03-26 | SCAG |  |  | R2JJCXX4TJ26
HQ | HSIPL | 5378(051) | Palmdale | 2023-12-20 | 2024-03-25 | NA | NA | NA | 450000 | 0 | 500000 | .. | 5378 | 07 | Prepared on 12/20/2023 | 3 | 102 | NA | NA | NA | Various Locations Throughout The City Of Palmdale | Conduct A City-wide Signal Modernization And Pedestrian Infrastructure | 1 | 2023-12-14 | 2023-12-19 | SCAG |  |  | MCXAN71AG2Q8
HQ | HSIPL | 5430(034) | Cathedral City | 2024-03-06 | 2024-03-19 | NA | NA | NA | 1030500 | 0 | 1437990.8 | .. | 5430 | 08 | Prepared on 3/6/2024 | 9 | 60 | NA | NA | NA | Twelve (12) Intersections Throughout The City Of Cathedral City | Advanced Dilemma Zone Detection, Protected Left-turn Phases, And Pedestrian | 4 | 2024-01-19 | 2024-03-07 | SCAG |  |  | PBMZGAPS38P4
HQ | BRLS | 5294(018) | Coachella | 2024-03-19 | 2024-03-19 | NA | NA | NA | 1200000 | 0 | 1500000 | .. | 5294 | 08 | Prepared on 3/19/2024 | 9 | 5 | NA | NA | NA | Dillon Road From Cabazon Road/avenue 48 Intersection To Sr-86 Southbound Ramp Intersection. | Widen Dillon Rd From 2 To 6 Lanes, From Cabazon Rd To Sr-86 I/c, Including | 1 | 2024-03-14 | 2024-03-14 | SCAG |  |  | DZD1FWED7J53
HQ | BRLO | 5282(017) | Palm Springs | 2023-12-19 | 2024-03-14 | NA | NA | NA | 9838610 | 3312067 | 25767081 | .. | 5282 | 08 | Prepared on 12/19/2023 | 14 | 86 | NA | NA | NA | Indian Canyon Drive Overhead At The Union Pacific Railroad South Of Garnet Avenue, Br. No. | Bridge Widening To Six Lanes | 10 | 2023-12-19 | 2024-03-07 | SCAG |  |  | M81QLC23JVX5
HQ | ATPL | 5203(056) | Chula Vista | 2024-02-22 | 2024-03-12 | NA | NA | NA | 100000 | 0 | 204750 | .. | 5203 | 11 | Prepared on 2/22/2024 | 16 | 111 | NA | NA | NA | Mts Railroad Corridor Parallel To And West Of Bay Boulevard From E Street To Lagoon Drive/f | Construction Of 1/4 Mile Of Class I Bikeway, Installation Of One (1) High- | 1 | 2023-11-22 | 2024-02-28 | SANDAG |  |  | KVBYLRZMAGJ9
HQ | ATPL | 6066(212) | San Diego Association Of Governments | 2024-01-23 | 2024-02-06 | NA | NA | NA | 4700000 | 0 | 4700000 | .. | 6066 | 11 | Prepared on 1/23/2024 | 51 | 19 | NA | NA | NA | Pactac Seeks Pa&ed Funding For 11 Bike Lane Miles Of Class Iv Cycle Tracks On Pacific Highway | Bike Lane. The Locations Are :pactac Seeks Pa&ed Funding For 11 Bike Lane Miles | 1 | 2024-01-18 | 2024-01-23 | SANDAG |  |  | CU82DUZEEL81
HQ | ATPL | 6066(213) | San Diego Association Of Governments | 2024-02-01 | 2024-02-05 | NA | NA | NA | 339000 | 0 | 347000 | Hold for CTC allocation. | 6066 | 11 | Prepared on 2/1/2024 | 52 | 5 | NA | NA | NA | University Avenue Between Ibis St And First St In Mission Hills, And On San Diego Ave And | Design, Improve And Construct New Bikeway Infrastructure, Bike Lanes, Pavement | 1 | 2024-01-31 | 2024-02-01 | SANDAG |  |  | CU82DUZEEL81
HQ | RSTPL | 6066(215) | San Diego Association Of Governments | 2024-03-12 | 2024-03-12 | NA | NA | NA | 4080000 | 0 | 4080000 | .. | 6066 | 11 | Prepared on 3/12/2024 | 16 | 5 | NA | NA | NA | Del Mar Bluffs - Coast Blvd And Mcgonigle Road. (tc) Toll Credit Will Be Used. | Environmental Clearance For The Design And Construction Of Pedestrian Access | 1 | 2024-03-07 | 2024-03-12 | SANDAG |  |  | CU82DUZEEL81
HQ | BHLS | 5004(049) | San Diego | 2024-01-26 | 2024-02-02 | NA | NA | NA | 10321290 | -10322228.97 | 0 | .. | 5004 | 11 | Prepared on 1/26/2024 | 55 | 7 | NA | NA | NA | West Mission Bay Drive Over The San Diego River | Bridge Replacement, Br. No. 57c-0023 | 18 | 2024-01-26 | 2024-02-02 | SANDAG |  |  | GHMFAWY9J3N5
HQ | BRLO | 5912(092) | Butte County | 2024-03-18 | 2024-03-19 | 2024-03-26 | NA | NA | 555000 | 0 | 555000 | .. | 5912 | 03 | Prepared on 3/18/2024 | 9 | 1 | NA | NA | NA | Central House Road At Wyman Ravine ~0.2 Mi East Of Sr70 Br. #12c-0111 | Bridge Replacement (tc) | 7 | 2024-03-18 | 2024-03-19 | BCAG |  |  | G14XJJ9RPBP5
HQ | CMLNI | 6236(024) | Sacramento Metropolitan Air Quality Management District | 2024-01-31 | 2024-02-29 | 2024-03-04 | NA | NA | 499999 | 0 | 499999 | Hold for FTIP amendment. | 6236 | 03 | Prepared on 1/31/2024 | 28 | 29 | NA | NA | NA | Phase 3 Of Sacramento Emergency Clean Air Transportation Program. Emission Benefits In Kg/day: | Secat Provides Grant Funds To New Zero And Low Emission Vehicles And Provides Trip | 1 | 2024-01-31 | 2024-02-29 | SACOG |  |  | D95DUST1M9Q5
HQ | CMLNI | 6236(025) | Sacramento Metropolitan Air Quality Management District | 2024-01-31 | 2024-02-29 | 2024-03-04 | NA | NA | 499999 | 0 | 499999 | Hold for FTIP amendment. | 6236 | 03 | Prepared on 1/31/2024 | 28 | 29 | NA | NA | NA | Phase 3 Of Sacramento Emergency Clean Air Transportation Programemission Benefits In Kg/day: | Secat Provides Grant Funds To New Zero And Low Emission Vehicles And Provides Trip | 1 | 2024-01-31 | 2024-02-29 | SACOG |  |  | D95DUST1M9Q5
HQ | BRLO | 5919(086) | Placer County | 2023-06-14 | 2024-03-08 | 2024-03-19 | NA | NA | 61946.21 | -111923 | -49996.34 | .. | 5919 | 03 | Prepared on 6/14/2023 | 20 | 8 | NA | NA | NA | Bowman Rd At Uprr Xing #1 Br. No. 19c-0061 | Bridge Rehabilitation (tc) | 7 | 2024-02-29 | 2024-03-07 | SACOG |  |  | L786NC553FC1
HQ | BRLO | 5176(008) | Ross | 2024-03-11 | 2024-03-19 | 2024-03-27 | NA | NA | 126800 | 0 | 126800 | .. | 5176 | 04 | Prepared on 3/11/2024 | 9 | 11 | NA | NA | VAR110045 | Winship Ave Bridge Over San Anselmo Creek In The Town Of Ross | Bridge Replacement (tc) | 3 | 2024-03-08 | 2024-03-18 | MTC |  |  | KLMLSTNMKAU1
HQ | ACST-ER | 15A5(023) | Alameda County | 2023-10-04 | 2023-11-03 | 2023-11-09 | NA | NA | 0.15 | 410130.74 | 457956 | .. | 5933 | 04 | Prepared on 10/4/2023 | 146 | 120 | NA | NA | NA | Calaverras Road 8.65 Pm | Construction | 3 | 2023-07-06 | 2023-10-04 | MTC |  |  | KD49R5NLLPZ7
HQ | BRLO | 5937(106) | Santa Clara County | 2024-03-04 | 2024-03-22 | 2024-03-27 | NA | NA | 6185304 | 0 | 6986676 | .. | 5937 | 04 | Prepared on 3/4/2024 | 6 | 1 | NA | NA | NA | Llagas Creek At Uvas Road. Br No. 37c0096 | Bridge Replacement | 8 | 2024-03-21 | 2024-03-22 | MTC |  |  | DM56XYHGSRA5
HQ | BRLS | 5937(123) | Santa Clara County | 2023-12-22 | 2024-03-20 | 2024-03-27 | NA | NA | 1604164 | 0 | 1812011 | .. | 5937 | 04 | Prepared on 12/22/2023 | 8 | 7 | NA | NA | VAR991007 | Uvas Rd Over Uvas Creek, Bridge 37c0094 | Bridge Replacement | 10 | 2024-03-13 | 2024-03-20 | MTC |  | negatie or zero funding | DM56XYHGSRA5
HQ | ACST-ER | 32L0(007) | Santa Cruz County | 2024-03-11 | 2024-03-11 | 2024-03-11 | NA | NA | 116917.55 | -116917.55 | 0.01 | .. | 5936 | 05 | Prepared on 3/11/2024 | 17 | 0 | NA | NA | NA | In The County Of Santa Cruz On Branciforte Drive 2.22 | Stabilize And Reconstruct Roadway | 6 | 2024-03-11 | 2024-03-11 | AMBAG |  |  | DQHKDRT8LVY8
HQ | ER | 32L0(207) | Santa Cruz County | 2024-03-11 | 2024-03-11 | 2024-03-12 | NA | NA | 92021.17 | -92021.17 | 0.00NA999476131 | .. | 5936 | 05 | Prepared on 3/11/2024 | 17 | 0 | NA | NA | NA | In The County Of Santa Cruz On Redwood Lodge Road Pm 1.65 | Reconstruct Slope | 6 | 2024-03-11 | 2024-03-11 | AMBAG |  |  | DQHKDRT8LVY8
HQ | STPL | 5197(046) | Sanger | 2024-03-19 | 2024-03-19 | 2024-03-21 | NA | NA | 36652 | 0 | 134366 | FTIP | 5197 | 06 | Prepared on 3/19/2024 | 9 | 1 | NA | NA | NA | Almond Ave From Bethel Ave To Greenwood Ave | Pavement Reconstruction, Replacement Of Damaged Curb And Gutter, Reconstruction Of | 2 | 2024-03-18 | 2024-03-19 | FCOG |  |  | CEKKQKASFJM6
HQ | STPL | 5208(184) | Clovis | 2024-03-20 | 2024-03-20 | 2024-03-27 | NA | NA | 1030596 | 0 | 1164121 | .. | 5208 | 06 | Prepared on 3/20/2024 | 8 | 1 | NA | NA | NA | Gettysburg Ave, Clovis To Sierra Vista | Gettysburg Ave From Clovis Ave To Sierra Vista Pkwy; Road Rehabilitation Including | 1 | 2024-03-19 | 2024-03-27 | FCOG |  |  | FZXEQ4KUYKE7
HQ | BRLO | 5929(245) | San Joaquin County | 2024-03-14 | 2024-03-18 | 2024-03-20 | NA | NA | 180200 | 0 | 180200 | .. | 5929 | 10 | Prepared on 3/14/2024 | 10 | 5 | NA | NA | SJ07-3002 | Buckman Road Over Duck Creek (bridge 29c0227) | Bridge Replacement (tc) | 4 | 2024-03-13 | 2024-03-14 | SJCOG |  |  | L3XZK6UCWTF3
HQ | STPL | 5059(234) | Modesto | 2024-03-18 | 2024-03-18 | 2024-03-21 | NA | NA | 2389231 | 0 | 3103354 | .. | 5059 | 10 | Prepared on 3/18/2024 | 10 | 6 | NA | NA | NA | Tuolumne Blvd. - Sutter Ave. To Neece Dr. | Pavement Rehabilitation (tc) | 3 | 2024-03-12 | 2024-03-12 | STANCOG |  |  | C9NNEMEHETD8
HQ | ATPSCML | 5008(189) | Stockton | 2024-03-15 | 2024-03-18 | 2024-03-21 | NA | NA | 1495393 | 0 | 5407137 | .. | 5008 | 10 | Prepared on 3/15/2024 | 10 | 5 | NA | NA | NA | 1- Westwood Elementary School 2- Lincoln Elementary School 3- Alex G. Spanos Elementary 4- | Safe Routes To School Safety And Connectivity Improvements. Construct Bike Lanes, | 1 | 2024-03-13 | 2024-03-15 | SJCOG |  |  | YV3KNQAKJLQ7
HQ | BPMPL | 5938(277) | Stanislaus County | 2024-01-19 | 2024-02-29 | 2024-03-05 | NA | NA | 680000 | 0 | 850000 | .. | 5938 | 10 | Prepared on 1/19/2024 | 28 | 113 | NA | NA | NA | On 43 Bridges (see Funding Location Detail) | Bridge Preventive Maintenance (structural & Deck Repairs) | 1 | 2023-11-08 | 2024-02-28 | STANCOG |  |  | JVUBT686JGX7
FMIS | BRLO | 5914(077) | Lake County | 2024-01-10 | 2024-02-05 | 2024-03-21 | 2024-03-25 | 2024-03-25 | 0 | 0 | 0 | .. | 5914 | 01 | Prepared on 1/10/2024 | 3 | 27 | 49 | 0 | HBPLOCAL | 0.6 Miles Southeast Of State Route 29 On Clayton Creek Road Over Whey Creek | Bridge Replacement (tc) | 6 | 2024-01-09 | 2024-01-09 | NON-MPO |  |  | PMJGFQ26A8A8
FMIS | BRLO | 5910(099) | Mendocino County | 2024-02-12 | 2024-02-12 | 2024-03-25 | 2024-03-25 | 2024-03-25 | 225000 | 0 | 225000 | .. | 5910 | 01 | Prepared on 2/12/2024 | 3 | 0 | 42 | 0 | NA | In Mendocino County, Boonville, Lambert Lane Over Robinson Creek. Br.# 10c0146 | Replace Existing Bridge With New Bridge (tc) | 8 | 2024-02-12 | 2024-02-12 | NON-MPO |  |  | JKULS1AA5J33
FMIS | ATPL | 5906(140) | Shasta County | 2024-03-27 | 2024-03-27 | 2024-03-27 | 2024-03-27 | 2024-03-27 | -747722.7 | 0 | -743833.29 | .. | 5906 | 02 | Prepared on 3/27/2024 | 1 | 6 | 0 | 0 | NA | In The Unincorporated Community Of Cottonwood, On Main St, Gas Point Rd, 1st St, 4th St, | Pedestrian And Bike Path (tc) | 2 | 2024-03-21 | 2024-03-22 | SHASTA |  |  | N66MAN8T42J5
FMIS | BRLO | 5919(163) | Placer County | 2024-03-19 | 2024-03-20 | 2024-03-24 | 2024-03-25 | 2024-03-25 | 212000 | 0 | 265000 | .. | 5919 | 03 | Prepared on 3/19/2024 | 3 | 1 | 5 | 0 | NA | Dry Creek Road Over Rock Creek, 0.35 Miles West Of Placer Hills Road. Br. # 19c0163 | Rehabilitation Of Existing 2 Lane Bridge, Widen For Standard Lanes And Shoulders | 1 | 2024-03-19 | 2024-03-19 | SACOG |  |  | L786NC553FC1
FMIS | CMLNI | 6084(208) | Metropolitan Transportation Commission | 2024-02-27 | 2024-03-04 | 2024-03-15 | 2024-03-20 | 2024-03-20 | 7221540 | 0 | 7221540 | .. | 6084 | 04 | Prepared on 2/27/2024 | 8 | 25 | 16 | 0 | NA | San Francisco Bay Area | 511 Traveler Information Program. The Project Subsidizes Commuter Vanpools And | 3 | 2024-02-08 | 2024-02-27 | MTC |  |  | UKDZHCRW3U97
FMIS | ATPLNI | 6510(001) | Napa Valley Transportation Authority | 2024-03-27 | 2024-03-27 | 2024-03-27 | 2024-03-27 | 2024-03-27 | 0 | 0 | -542010.78 | .. | 6510 | 04 | Prepared on 3/27/2024 | 1 | 6 | 0 | 0 | NA | 38 Schools Within Napa County Area | Safe Routes To School Program(tc) | 3 | 2024-03-21 | 2024-03-22 | MTC |  |  | KTBCYAWLJML5
FMIS | STPLNI | 6084(232) | Metropolitan Transportation Commission | 2024-03-11 | 2024-03-19 | 2024-03-20 | 2024-03-22 | 2024-03-22 | 11344000 | 0 | 11344000 | .. | 6084 | 04 | Prepared on 3/11/2024 | 6 | 68 | 3 | 0 | NA | Sf Bay Area: Regionwide | Planning Assistance To Support Transportation Investments And Improve Their | 4 | 2024-01-11 | 2024-03-11 | MTC |  |  | UKDZHCRW3U97
FMIS | STPL | 5028(085) | Santa Rosa | 2024-03-26 | 2024-03-26 | 2024-03-26 | 2024-03-26 | 2024-03-26 | 0 | 0 | -201712.71 | .. | 5028 | 04 | Prepared on 3/26/2024 | 2 | 5 | 0 | 0 | NA | Hearn Avenue Between Stony Point Road, Dutton Avenue And Range Avenue Between Guerneville Road | Pavement Rehabilitation, Restripe Roadways To Add Class Ii Bike Lanes | 2 | 2024-03-21 | 2024-03-22 | MTC |  |  | MPMQPX61FMW7
FMIS | STPLNI | 6084(302) | Metropolitan Transportation Commission | 2024-02-21 | 2024-03-22 | 2024-03-25 | 2024-03-25 | 2024-03-25 | 15000000 | 0 | 15000000 | .. | 6084 | 04 | Prepared on 2/21/2024 | 3 | 36 | 3 | 0 | NA | San Francisco Bay Area | The Transportation Electrification Planning Program Will Focus On Three Main | 1 | 2024-02-15 | 2024-02-21 | MTC |  |  | UKDZHCRW3U97
FMIS | CPFL | 5019(038) | Santa Clara | 2024-03-01 | 2024-03-01 | 2024-03-12 | 2024-03-20 | 2024-03-20 | 1225000 | 0 | 1384138 | .. | 5019 | 04 | Prepared on 3/1/2024 | 8 | 3 | 19 | 0 | NA | De La Cruz Blvd, Lick Mill Blvd, And Scott Blvd Bicycle Projects. Demo Id Ca911 | Complete Traffic Analyses, Public Outreach, Design, And Construction Of Bicycle | 1 | 2024-02-27 | 2024-03-01 | MTC |  |  | RK62GLSXRUK9
FMIS | STPLNI | 6084(303) | Metropolitan Transportation Commission | 2024-02-27 | 2024-03-12 | 2024-03-25 | 2024-03-25 | 2024-03-25 | 1000000 | 0 | 1000000 | .. | 6084 | 04 | Prepared on 2/27/2024 | 3 | 26 | 13 | 0 | NA | Nine-county San Francisco Bay Area (mtc/abag Region) | The Active Transportation Technical Assistance (ta) Program Provides Technical | 1 | 2024-02-15 | 2024-02-21 | MTC |  |  | UKDZHCRW3U97
FMIS | ER | 32L0(205) | Santa Cruz County | 2024-03-26 | 2024-03-26 | 2024-03-26 | 2024-03-26 | 2024-03-26 | 0 | 0 | 67.17 | .. | 5936 | 05 | Prepared on 3/26/2024 | 2 | 5 | 0 | 0 | NA | In The County Of Santa Cruz On Redwood Lodge Rd Pm 2.02 | Reconstruct Road And Stabilize Slope | 6 | 2024-03-21 | 2024-03-22 | AMBAG |  |  | DQHKDRT8LVY8
FMIS | ER | 15J7(023) | Morro Bay | 2024-03-25 | 2024-03-25 | 2024-03-25 | 2024-03-25 | 2024-03-25 | -3000 | 0 | 34402.31 | .. | 5391 | 05 | Prepared on 3/25/2024 | 3 | 4 | 0 | 0 | NA | Main St And Radcliff Ave In Morro Bay | Remove/replace Failed Roadway Asphalt From Storm Damage | 2 | 2024-03-21 | 2024-03-22 | SLOCOG |  |  | KAFQZMM3MRA5
FMIS | ER | 15J9(001) | Morro Bay | 2024-03-25 | 2024-03-25 | 2024-03-25 | 2024-03-25 | 2024-03-25 | -169088.01 | 0 | -169088.01 | .. | 5391 | 05 | Prepared on 3/25/2024 | 3 | 4 | 0 | 0 | NA | South Bay Blvd Near Chorro Creek Bridge | Emergency Opening; Work Includes Agency Forces/staff Time For Road Closures During | 2 | 2024-03-21 | 2024-03-22 | SLOCOG |  |  | KAFQZMM3MRA5
FMIS | BRLS | 5397(010) | Carpinteria | 2024-03-21 | 2024-03-21 | 2024-03-24 | 2024-03-27 | 2024-03-27 | 12394953 | 0 | 14000850 | .. | 5397 | 05 | Prepared on 3/21/2024 | 1 | 1 | 6 | 0 | CT14 | Carpinteria Avenue Bridge #51c0172 | Bridge Replacement | 10 | 2024-03-20 | 2024-03-20 | SBCAG |  |  | DLY8Y5UGJUS7
FMIS | BRLO | 5946(108) | Tulare County | 2024-03-26 | 2024-03-26 | 2024-03-26 | 2024-03-26 | 2024-03-26 | 0 | 0 | -13886.97 | .. | 5946 | 06 | Prepared on 3/26/2024 | 2 | 5 | 0 | 0 | TUL11-120 | Bridge 46c0208 On Avenue 364 Over Cottonwood Creek | Replace 1 Lane Bridge With 2 Lane Bridge (tc) | 7 | 2024-03-21 | 2024-03-22 | TCAG |  |  | NN1GT1HPGN78
FMIS | CML | 5950(503) | Kern County | 2024-03-14 | 2024-03-19 | 2024-03-20 | 2024-03-27 | 2024-03-27 | 965910 | 0 | 1156174 | .. | 5950 | 06 | Prepared on 3/14/2024 | 1 | 8 | 8 | 0 | NA | Kern County (metro Bakersfield): Northside Of Casa Loma Dr (s Union Ave To Pogososo St) | Construct 0.25 Miles Of Sidewalk And Shoulders | 2 | 2024-03-11 | 2024-03-14 | KCOG |  |  | JTBAYSUJB446
FMIS | ACSTP | 15J9(168) | Madera County | 2024-02-27 | 2024-02-27 | 2024-03-13 | 2024-03-27 | 2024-03-27 | 0 | 73944.68 | 83525 | .. | 5941 | 06 | Prepared on 2/27/2024 | 1 | 4 | 29 | 0 | NA | Road 222(800) | Remove Roadway Structural Section. Excavate To Stable Material. Backfill Resulting | 1 | 2024-02-23 | 2024-02-27 | MCTC |  |  | KNPYKHLWNKE1
FMIS | ACSTP | 15J9(169) | Madera County | 2024-02-28 | 2024-02-28 | 2024-03-13 | 2024-03-27 | 2024-03-27 | 0 | 527683.06 | 596050 | .. | 5941 | 06 | Prepared on 2/28/2024 | 1 | 5 | 28 | 0 | NA | Road 274(838) | Remove Roadway Structural Section. Excavate Past The Slope Failure Plane. Bench | 1 | 2024-02-23 | 2024-02-27 | MCTC |  |  | KNPYKHLWNKE1
FMIS | HSIPL | 5351(035) | Pico Rivera | 2024-03-26 | 2024-03-26 | 2024-03-26 | 2024-03-26 | 2024-03-26 | 0 | 0 | 32360.16 | .. | 5351 | 07 | Prepared on 3/26/2024 | 2 | 5 | 0 | 0 | NA | Intersections Of Washington Blvd/crossway Dr, Paramount Blvd/beverly Blvd, Whittier | Traffic Signal Improvements | 3 | 2024-03-21 | 2024-03-22 | SCAG |  |  | RBR1AK1KTAN9
FMIS | HSIPL | 5164(033) | Inglewood | 2024-03-25 | 2024-03-25 | 2024-03-25 | 2024-03-25 | 2024-03-25 | -280964.98 | 0 | -1149960 | .. | 5164 | 07 | Prepared on 3/25/2024 | 3 | 4 | 0 | 0 | NA | Centinela Avenue From La Cienega Blvd To La Brea Ave | Centinela Ave Medians And Traffic Signal Improvements. | 3 | 2024-03-21 | 2024-03-22 | SCAG |  |  | YCN3V7DLSFG1
FMIS | BHLS | 5240(026) | Culver City | 2022-07-05 | 2024-02-27 | 2024-03-12 | 2024-03-27 | 2024-03-27 | 606613.32 | 0 | 660206.5 | .. | 5240 | 07 | Prepared on 7/5/2022 | 1 | 670 | 29 | 0 | LA0G451 | Higuera Street Bridge Over Ballona Creek, Br. No. 53c-0876 | Replacing The Existing 3-lane With A 4-lane Bridge | 7 | 2022-04-28 | 2024-02-26 | SCAG |  |  | M5B9GLV2LQN7
FMIS | ATPSB1L | 5275(035) | Indio | 2024-03-27 | 2024-03-27 | 2024-03-27 | 2024-03-27 | 2024-03-27 | 0 | 0 | -373104.72 | .. | 5275 | 08 | Prepared on 3/27/2024 | 1 | 6 | 0 | 0 | NA | The Project Is On Fourteen Street Segments In The City Of Indio In The Community Surrounding | Construct 5.5 Miles Of Sidewalk Along Fourteen (14) Street Segments And Upgrade | 3 | 2024-03-21 | 2024-03-22 | SCAG |  |  | L852WV7G8PK5
FMIS | BHLS | 5275(021) | Indio | 2023-12-21 | 2024-02-15 | 2024-02-27 | 2024-03-25 | 2024-03-25 | 78747 | 0 | 53184 | .. | 5275 | 08 | Prepared on 12/21/2023 | 3 | 80 | 39 | 0 | RIV050201 | Westbound Indio Boulevard Over Whitewater River, Br. No. 56c-0292 | Seismic Retrofit And Scour Countermeasures | 8 | 2023-11-27 | 2024-02-12 | SCAG |  |  | L852WV7G8PK5
FMIS | BRLO | 5141(015) | Jackson | 2024-03-12 | 2024-03-15 | 2024-03-19 | 2024-03-25 | 2024-03-25 | 2049700 | 0 | 2049700 | .. | 5141 | 10 | Prepared on 3/12/2024 | 3 | 3 | 10 | 0 | HBPLOCAL | French Bar Road Over Sf Jackson Creek (bridge 26c0035) | Bridge Replacement (tc) | 8 | 2024-03-12 | 2024-03-14 | NON-MPO |  |  | ERQKLDCSKQ78
FMIS | BRLO | 5939(082) | Merced County | 2024-03-06 | 2024-03-08 | 2024-03-14 | 2024-03-25 | 2024-03-25 | 107970 | 0 | 107970 | .. | 5939 | 10 | Prepared on 3/6/2024 | 3 | 8 | 17 | 0 | NA | Jorgensen Road Over Outside Canal (bridge 39c0217) | Bridge Replacement (tc) | 6 | 2024-02-29 | 2024-03-06 | MCAG |  |  | NJDZPHTGSUQ6
FMIS | BRLS | 5938(260) | Stanislaus County | 2024-02-15 | 2024-03-01 | 2024-03-07 | 2024-03-25 | 2024-03-25 | 88530 | 0 | 100000 | .. | 5938 | 10 | Prepared on 2/15/2024 | 3 | 17 | 24 | 0 | NA | Montpelier Road Over Turlock Irrigation District (t.i.d.) Main Canal (bridge 38c0157) | Bridge Replacement | 3 | 2024-02-13 | 2024-02-28 | STANCOG |  |  | JVUBT686JGX7
FMIS | HSIPL | 5446(024) | Encinitas | 2023-12-06 | 2024-03-04 | 2024-03-21 | 2024-03-27 | 2024-03-27 | 0 | 0 | 0 | .. | 5446 | 11 | Prepared on 12/6/2023 | 1 | 12 | 23 | 0 | NA | 14 Intersections & Project Corridors: Corridors Of 2nd St, Birmingham Dr, Coast Highway 101, | L.e.d. Street Lighting: Install Led Luminaire Safety Lighting At Signalized | 3 | 2024-02-21 | 2024-03-04 | SANDAG |  |  | N988C2JLJ4Z7
FMIS | CMLN | 6203(062) | Caltrans | 2024-03-18 | 2024-03-19 | 2024-03-21 | 2024-03-25 | 2024-03-25 | 60000 | 0 | 60000 | .. | 6203 | 03 | Prepared on 3/18/2024 | 3 | 1 | 6 | 0 | NA | I-80 West Of Davis From The Kidwell Ic To West El Camino Ic & I-80/us-50 Ic To Us-50/i-5 Ic | Construct Improvements Consisting Of Managed Lanes In Each Direction, Ped/bike | 4 | 2024-03-18 | 2024-03-18 | SACOG
Obligated | STPLR | 7500(270) | OAKLAND | NA | NA | NA | 2024-02-20 | 2024-02-28 | 0 | 0 | 0 | Authorized | 5012 | 00 | E-76 approved on | NA | NA | NA | NA | NA | City Of Oakland, At 29th Avenue (2) And Uprr | Grade Crossing Hazard Elimination (tc) | 4 |  |  | MTC |  |  | KWMRND8WK7A5
Obligated | ACSTP | 15J9(019) | Humboldt County | 2024-01-31 | 2024-01-31 | 2024-02-02 | 2024-02-06 | 2024-02-08 | 0 | 167410.23 | 189100 | Authorized | 5904 | 01 | E-76 approved on | NA | 0 | 6 | 2 | NA | Alderpoint Rd Pm 40.5 | Pending Geotech Report, Repair Slope Failure With Reinforced Embankment, | 1 | 2024-01-31 | 2024-01-31 | NON-MPO |  |  | UBWEAY8NDL25
Obligated | ACSTP | 15J9(020) | Humboldt County | 2024-02-15 | 2024-02-15 | 2024-02-20 | 2024-02-21 | 2024-02-23 | 0 | 39130.26 | 44200 | Authorized | 5904 | 01 | E-76 approved on | NA | 10 | 6 | 2 | NA | Bell Springs Rd Pm 4.84-4.87 In Humboldt County, Ca | Permanent Restoration-roadway Retreat And Rsp Buttress. | 1 | 2024-02-05 | 2024-02-05 | NON-MPO |  |  | UBWEAY8NDL25
Obligated | ACSTP | 15J9(026) | Humboldt County | 2024-02-15 | 2024-02-15 | 2024-02-20 | 2024-03-20 | 2024-03-22 | 0 | 64981.02 | 73400 | Authorized | 5904 | 01 | E-76 approved on | NA | 7 | 34 | 2 | NA | Kneeland Rd Pm 0.75-0.85 In Humboldt County, Ca | Permanent Restoration-geogrid Reinforced Embankment And Subdrainage Per | 1 | 2024-02-08 | 2024-02-08 | NON-MPO |  |  | UBWEAY8NDL25
Obligated | ACSTP | 15J9(028) | Humboldt County | 2024-01-31 | 2024-01-31 | 2024-02-02 | 2024-02-06 | 2024-02-09 | 0 | 122932.75 | 138860 | Authorized | 5904 | 01 | E-76 approved on | NA | 0 | 6 | 3 | NA | Mattole Road Pm 10.85 | Construct Soldier Pile Wall Based On Geotech Recommendations. | 1 | 2024-01-31 | 2024-01-31 | NON-MPO |  |  | UBWEAY8NDL25
Obligated | ACSTP | 15J9(022) | Humboldt County | 2024-02-01 | 2024-02-01 | 2024-02-02 | 2024-02-06 | 2024-02-08 | 0 | 247884 | 280000 | Authorized | 5904 | 01 | E-76 approved on | NA | 1 | 5 | 2 | NA | Bell Springs Road Pm 6.6 | Reconstruct Roadway With Soldier Pile Wall And Reinforced Embankment With | 1 | 2024-01-31 | 2024-01-31 | NON-MPO |  |  | UBWEAY8NDL25
Obligated | ACSTP | 15J9(024) | Humboldt County | 2024-02-01 | 2024-02-01 | 2024-02-02 | 2024-02-06 | 2024-02-08 | 0 | 98091.24 | 110800 | Authorized | 5904 | 01 | E-76 approved on | NA | 1 | 5 | 2 | NA | Briceland Thorne Rd Pm 5.25 | Repair Slope Failure With Reinforced Embankment, Geogrid And Underdrainage | 1 | 2024-01-31 | 2024-01-31 | NON-MPO |  |  | UBWEAY8NDL25
Obligated | ACSTP | 15J9(030) | Humboldt County | 2024-01-31 | 2024-01-31 | 2024-02-05 | 2024-02-06 | 2024-02-08 | 0 | 93045.03 | 105100 | Authorized | 5904 | 01 | E-76 approved on | NA | 0 | 6 | 2 | NA | Mattole Road Pm 15.47 | Pending Geotech Report, Repair Slope Failure With Mse Wall, Permeable | 1 | 2024-01-31 | 2024-01-31 | NON-MPO |  |  | UBWEAY8NDL25
Obligated | ACSTP | 15J9(032) | Humboldt County | 2024-02-01 | 2024-02-01 | 2024-02-06 | 2024-02-12 | 2024-02-14 | 0 | 145038.69 | 163830 | Authorized | 5904 | 01 | E-76 approved on | NA | 1 | 11 | 2 | NA | Mattole Road Pm 40.25 | Construct Soldier Pile Wall Per Geotechnical Investigation. | 1 | 2024-01-31 | 2024-01-31 | NON-MPO |  |  | UBWEAY8NDL25
Obligated | ACSTP | 15J9(034) | Humboldt County | 2024-02-15 | 2024-03-08 | 2024-03-12 | 2024-03-19 | 2024-03-22 | 0 | 169357.89 | 191300 | Authorized | 5904 | 01 | E-76 approved on | NA | 32 | 11 | 3 | NA | Mattole Rd Pm 26.90-27.20 In Humboldt County, Ca | Permanent Restoration-repair Road Section With Geogrid And Install Deep | 1 | 2024-02-05 | 2024-02-05 | NON-MPO |  |  | UBWEAY8NDL25
Obligated | ACSTP | 15J9(044) | Humboldt County | 2024-02-15 | 2024-02-15 | 2024-02-20 | 2024-02-22 | 2024-02-23 | 0 | 9649.77 | 10900 | Authorized | 5904 | 01 | E-76 approved on | NA | 7 | 7 | 1 | NA | Kneeland Rd Pm 2.25/2.30 In Humboldt County, Ca | Permanent Restoration-place Rsp At Damaged Embankment. | 1 | 2024-02-08 | 2024-02-08 | NON-MPO |  |  | UBWEAY8NDL25
Obligated | ACSTP | 15J9(046) | Humboldt County | 2024-02-15 | 2024-02-15 | 2024-02-20 | 2024-02-22 | 2024-02-23 | 0 | 84280.56 | 95200 | Authorized | 5904 | 01 | E-76 approved on | NA | 7 | 7 | 1 | NA | Kneeland Rd 4.70/4.85 In Humboldt County, Ca | Permanent Restoration-geogrid Reinforced Embankment And Subdrainage Per | 1 | 2024-02-08 | 2024-02-08 | NON-MPO |  |  | UBWEAY8NDL25
Obligated | ACSTP | 15J7(151) | Mendocino County | 2023-08-01 | 2024-01-30 | 2024-01-31 | 2024-02-06 | 2024-02-08 | 0 | 56250 | 56250 | Authorized | 5910 | 01 | E-76 approved on | NA | 201 | 7 | 2 | NA | Mendicino Pass Rd, Cr 338, Mp 16.75 | Placement Of 450 Tons Of Class 2 Base | 1 | 2023-07-13 | 2023-07-13 | NON-MPO |  |  | JKULS1AA5J33
Obligated | BRLSNI | 5904(200) | Humboldt County | 2023-12-04 | 2023-12-11 | 2024-01-30 | 2024-01-30 | 2024-02-05 | 115200 | 0 | 144000 | Authorized | 5904 | 01 | E-76 approved on | NA | 7 | 50 | 6 | HBPLOCAL | Alderpoint Road Bridge (04c0093) Over Burr Creek, 4 Miles South Of Sr 36 | Project Studies Only: Conduct Landslide Analysis To Stabilize The Abutments | 1 | 2023-12-04 | 2023-12-04 | NON-MPO |  |  | UBWEAY8NDL25
Obligated | ACSTP | 15J7(197) | Mendocino County | 2024-01-22 | 2024-03-12 | 2024-03-13 | 2024-03-19 | 2024-03-22 | 0 | 101453 | 113432 | Authorized | 5910 | 01 | E-76 approved on | NA | 54 | 7 | 3 | NA | Mendocino Pass Road, Cr 338, M.p. 15.50 | Rem. Debris From Dam. Facility & Regraded Road. Rem. Dam. Cmp Outlet & | 1 | 2024-01-18 | 2024-03-12 | NON-MPO |  |  | JKULS1AA5J33
Obligated | ACSTP | 15J7(198) | Mendocino County | 2024-01-22 | 2024-03-12 | 2024-03-13 | 2024-03-19 | 2024-03-22 | 0 | 70116 | 79201 | Authorized | 5910 | 01 | E-76 approved on | NA | 54 | 7 | 3 | NA | Mendocino Pass Road, Cr 338 | Replace (e) Cmp W/box Culvert. Place Rsp, Grade Inlet Channel. Recon. Road | 1 | 2024-01-18 | 2024-03-12 | NON-MPO |  |  | JKULS1AA5J33
Obligated | ACSTP | 15J7(201) | Lake County | 2024-01-30 | 2024-01-30 | 2024-01-30 | 2024-02-06 | 2024-02-08 | 0 | 163780.5 | 185000 | Authorized | 5914 | 01 | E-76 approved on | NA | 1 | 7 | 2 | NA | Sulfur Bank Road Pm 1.49 | Stabilize The Slip Out And Embankment. Restore The Paved Roadway Surface To | 1 | 2024-01-29 | 2024-01-29 | NON-MPO |  |  | PMJGFQ26A8A8
Obligated | BRLSZD | 5910(109) | Mendocino County | 2023-10-02 | 2023-12-28 | 2024-02-28 | 2024-03-04 | 2024-03-06 | 0 | 0 | 0 | Authorized | 5910 | 01 | E-76 approved on | NA | 104 | 67 | 2 | HBPLOCAL | Moore Street Over West Branch Russian River (br No 10c0048) | Riparian Habitat Mitigation Monitoring. | 2 | 2023-09-15 | 2023-12-27 | NON-MPO |  |  | JKULS1AA5J33
Obligated | BRLO | 5904(167) | Humboldt County | 2024-01-09 | 2024-01-09 | 2024-01-30 | 2024-01-30 | 2024-02-06 | 46000 | -46000 | 0 | Authorized | 5904 | 01 | E-76 approved on | NA | 263 | 21 | 7 | HBPLOCAL | Pine Hill Rd Over Swain Slough, 0.2 Mi E/o Elk River Rd In Humboldt County, | Re-vegetation Monitoring | 2 | 2023-04-21 | 2023-04-21 | NON-MPO |  |  | UBWEAY8NDL25
Obligated | ER | 15J8(011) | Humboldt County | 2024-02-08 | 2024-02-08 | 2024-02-08 | 2024-02-12 | 2024-02-14 | 292149 | -292149 | 0 | Authorized | 5904 | 01 | E-76 approved on | NA | 0 | 4 | 2 | NA | Blue Slide Road 2.66 | Repair Steel Crib Wall And Roadway Damage; Repair Shoulder Failure With | 2 | 2024-02-08 | 2024-02-08 | NON-MPO |  |  | UBWEAY8NDL25
Obligated | ER | 15J8(015) | Humboldt County | 2024-02-12 | 2024-02-12 | 2024-02-12 | 2024-02-13 | 2024-02-15 | 68876.34 | -68876.34 | 0 | Authorized | 5904 | 01 | E-76 approved on | NA | 0 | 1 | 2 | NA | F Street Pm .26 | Repair Slope Failure | 2 | 2024-02-12 | 2024-02-12 | NON-MPO |  |  | UBWEAY8NDL25
Obligated | ER | 15J8(013) | Humboldt County | 2024-02-12 | 2024-02-12 | 2024-02-12 | 2024-02-13 | 2024-02-15 | 3703.2 | -3703.2 | 0 | Authorized | 5904 | 01 | E-76 approved on | NA | 0 | 1 | 2 | NA | Elk River Road Pm 1.01 | Repair Asphalt Pavement | 2 | 2024-02-12 | 2024-02-12 | NON-MPO |  |  | UBWEAY8NDL25
Obligated | ER | 15J8(014) | Humboldt County | 2024-02-12 | 2024-02-12 | 2024-02-12 | 2024-02-13 | 2024-02-15 | 19122.48 | -19122.48 | 0 | Authorized | 5904 | 01 | E-76 approved on | NA | 0 | 1 | 2 | NA | Tompkins Hill Road Pm 1.0 | Place Cold Mix Asphalt In, And Seal, Cracks (eo); Then Repair Failing | 2 | 2024-02-12 | 2024-02-12 | NON-MPO |  |  | UBWEAY8NDL25
Obligated | ER | 15J8(012) | Humboldt County | 2024-02-12 | 2024-02-12 | 2024-02-12 | 2024-02-13 | 2024-02-15 | 3324.3 | -3324.3 | 0 | Authorized | 5904 | 01 | E-76 approved on | NA | 0 | 1 | 2 | NA | Elk River Road Pm .14 | Repair Asphalt Approaches North And Southbound | 2 | 2024-02-12 | 2024-02-12 | NON-MPO |  |  | UBWEAY8NDL25
Obligated | ER | 15J8(010) | Humboldt County | 2024-02-08 | 2024-02-08 | 2024-02-08 | 2024-02-12 | 2024-02-14 | 104642.46 | -104642.46 | 0 | Authorized | 5904 | 01 | E-76 approved on | NA | 0 | 4 | 2 | NA | Walnut Drive | 154' Of Roadway Repair Due To Earthquake Damage | 2 | 2024-02-08 | 2024-02-08 | NON-MPO |  |  | UBWEAY8NDL25
Obligated | ER | 15J8(017) | Humboldt County | 2024-02-12 | 2024-02-12 | 2024-02-12 | 2024-02-13 | 2024-02-15 | 57367.44 | -57367.44 | 0 | Authorized | 5904 | 01 | E-76 approved on | NA | 0 | 1 | 2 | NA | Blue Lake Bridge On Maple Creek Road Over North Fork Mad River | Replace Damaged Trusses And Repair Damaged Substructure Per The Structural | 2 | 2024-02-12 | 2024-02-12 | NON-MPO |  |  | UBWEAY8NDL25
Obligated | ER | 15J7(110) | Humboldt County | 2024-02-06 | 2024-02-06 | 2024-02-06 | 2024-02-07 | 2024-02-08 | 25319.58 | -25319.58 | 0 | Authorized | 5904 | 01 | E-76 approved on | NA | 0 | 1 | 1 | NA | Central Ave Pm 2.77 | Investigate Culvert Blockage Using Culvert Inspection | 2 | 2024-02-06 | 2024-02-06 | NON-MPO |  |  | UBWEAY8NDL25
Obligated | ER | 15J7(112) | Humboldt County | 2024-02-06 | 2024-02-06 | 2024-02-06 | 2024-02-09 | 2024-02-12 | 274443 | -274443 | 0 | Authorized | 5904 | 01 | E-76 approved on | NA | 0 | 3 | 3 | NA | Briceland Thorn Rd Pm 2.40 | Repair Slope Failure With Soldier Pile Wall Per Geotech | 2 | 2024-02-06 | 2024-02-06 | NON-MPO |  |  | UBWEAY8NDL25
Obligated | ER | 15J7(117) | Mendocino County | 2024-02-06 | 2024-02-06 | 2024-02-06 | 2024-02-09 | 2024-02-12 | 40000 | -40000 | 0 | Authorized | 5910 | 01 | E-76 approved on | NA | 0 | 3 | 3 | NA | Mountain View Road, Dr 510, Mp 1.69 | Restoration Of Roadway And Drainage Crossing. | 2 | 2024-02-06 | 2024-02-06 | NON-MPO |  |  | JKULS1AA5J33
Obligated | ER | 15J7(118) | Mendocino County | 2024-02-07 | 2024-02-07 | 2024-02-07 | 2024-02-09 | 2024-02-12 | 38634.49 | -38634.49 | 0 | Authorized | 5910 | 01 | E-76 approved on | NA | 0 | 2 | 3 | NA | Mountain View, Cr 510, Pm 1.69 | During Heavy Rains, Excessive Water Flows Overwhelmed The Existing Pipe | 2 | 2024-02-07 | 2024-02-07 | NON-MPO |  |  | JKULS1AA5J33
Obligated | ER | 15J7(152) | Mendocino County | 2024-02-07 | 2024-02-07 | 2024-02-12 | 2024-02-13 | 2024-02-15 | 29391.96 | -29391.96 | 0 | Authorized | 5910 | 01 | E-76 approved on | NA | 0 | 6 | 2 | NA | Mountain Pass Road, Cr338, Mp 16.75 | Restore Drainage Crossing And Roadway. | 2 | 2024-02-07 | 2024-02-07 | NON-MPO |  |  | JKULS1AA5J33
Obligated | ER | 15J7(178) | Lake County | 2024-02-08 | 2024-02-08 | 2024-02-08 | 2024-02-12 | 2024-02-14 | 110662.5 | -110662.5 | 0 | Authorized | 5914 | 01 | E-76 approved on | NA | 0 | 4 | 2 | NA | Elk Mountain Rd Pm 8.5-8.55 | Stabilize Slip Out With Cast In Drilled Hole Reinforced Concrete Pilings. | 2 | 2024-02-08 | 2024-02-08 | NON-MPO |  |  | PMJGFQ26A8A8
Obligated | ER | 32L0(268) | Humboldt County | 2024-02-16 | 2024-02-16 | 2024-02-16 | 2024-02-21 | 2024-02-23 | 0 | 0 | 0 | Authorized | 5904 | 01 | E-76 approved on | NA | 0 | 5 | 2 | NA | Alderpoint Rd Pm 2.10, Humboldt County | Permanent Restoration | 5 | 2024-02-16 | 2024-02-16 | NON-MPO |  |  | UBWEAY8NDL25
Obligated | ER | 32L0(271) | Humboldt County | 2024-02-16 | 2024-02-16 | 2024-02-16 | 2024-02-21 | 2024-02-23 | 0 | 0 | 0 | Authorized | 5904 | 01 | E-76 approved on | NA | 0 | 5 | 2 | NA | Alderpoint Road Pm 2.98 | Er Permanent Restoration For Disaster 17-2 | 5 | 2024-02-16 | 2024-02-16 | NON-MPO |  |  | UBWEAY8NDL25
Obligated | ER | 32L0(321) | Humboldt County | 2024-02-16 | 2024-02-16 | 2024-02-16 | 2024-02-21 | 2024-02-23 | 0 | 0 | 0 | Authorized | 5904 | 01 | E-76 approved on | NA | 0 | 5 | 2 | NA | Mattole Rd 17.83, Humboldt County | Permanent Restoration | 5 | 2024-02-16 | 2024-02-16 | NON-MPO |  |  | UBWEAY8NDL25
Obligated | ER | 40A0(060) | Humboldt County | 2024-02-16 | 2024-02-16 | 2024-02-16 | 2024-02-21 | 2024-02-23 | 0 | 0 | 0 | Authorized | 5904 | 01 | E-76 approved on | NA | 0 | 5 | 2 | NA | Briceland Thorne Rd, Pm 5.67 In Humboldt County | Permanent Restoration | 5 | 2024-02-16 | 2024-02-16 | NON-MPO |  |  | UBWEAY8NDL25
Obligated | BRLO | 5914(094) | Lake County | 2023-12-22 | 2023-12-22 | 2024-02-22 | 2024-02-23 | 2024-02-28 | 3085395 | 0 | 3085395 | Authorized | 5914 | 01 | E-76 approved on | NA | 1 | 63 | 5 | HBPLOCAL | Chalk Mountain Road Bridge Over North Fork Cache Creek, In Spring Valley | Bridge Replacement (tc) | 6 | 2023-12-21 | 2023-12-21 | NON-MPO |  |  | PMJGFQ26A8A8
Obligated | ACST-ER | 32D0(013) | Crescent City | 2024-03-08 | 2024-03-14 | 2024-03-15 | 2024-03-20 | 2024-03-22 | 0 | 293265.36 | 331261 | Authorized | 5013 | 01 | E-76 approved on | NA | 10 | 6 | 2 | NA | In Crescent City On Pebble Beach Drive From 7th Street To Preston Island | Permanent Restoration | 6 | 2024-03-04 | 2024-03-06 | NON-MPO |  |  | EJK8M8KRTY59
Obligated | ER | 40A0(061) | Humboldt County | 2024-02-16 | 2024-02-16 | 2024-02-16 | 2024-02-21 | 2024-02-23 | 0 | 0 | 0 | Authorized | 5904 | 01 | E-76 approved on | NA | 0 | 5 | 2 | NA | Alderpoint Rd Pm 1.20, Humboldt County | Permanent Restoration | 6 | 2024-02-16 | 2024-02-16 | NON-MPO |  |  | UBWEAY8NDL25
Obligated | ER | 40A0(038) | Mendocino County | 2024-03-06 | 2024-03-06 | 2024-03-11 | 2024-03-19 | 2024-03-22 | -20373 | 0 | -23010 | Authorized | 5910 | 01 | E-76 approved on | NA | 14 | 13 | 3 | NA | Mountain View Road Pm 1.65, Cr 510 | Excavate Slide Material, Stabilize With Rsp And Revegetate. | 6 | 2024-02-21 | 2024-03-05 | NON-MPO |  |  | JKULS1AA5J33
Obligated | ER | 40A0(050) | Humboldt County | 2024-02-13 | 2024-02-13 | 2024-02-13 | 2024-02-13 | 2024-02-15 | 0 | 0 | 0 | Authorized | 5904 | 01 | E-76 approved on | NA | 0 | 0 | 2 | NA | Briceland Thorne Road Pm 3.08 Pr | Permanent Restoration | 6 | 2024-02-13 | 2024-02-13 | NON-MPO |  |  | UBWEAY8NDL25
Obligated | ER | 32L0(125) | Humboldt County | 2024-02-26 | 2024-02-26 | 2024-02-26 | 2024-02-26 | 2024-02-28 | 0 | 0 | 0 | Authorized | 5904 | 01 | E-76 approved on | NA | 4 | 0 | 2 | NA | Alderpoint Road Pm 44.79, Humboldt County | Permanent Restoration | 7 | 2024-02-22 | 2024-02-23 | NON-MPO |  |  | UBWEAY8NDL25
Obligated | ER | 32L0(270) | Humboldt County | 2024-02-16 | 2024-02-16 | 2024-02-16 | 2024-02-21 | 2024-02-23 | 0 | 0 | 0 | Authorized | 5904 | 01 | E-76 approved on | NA | 0 | 5 | 2 | NA | Alderpoint Road 2.70 | Permanent Restoration | 7 | 2024-02-16 | 2024-02-16 | NON-MPO |  |  | UBWEAY8NDL25
Obligated | ER | 40A0(046) | Lakeport | 2024-02-13 | 2024-02-13 | 2024-02-13 | 2024-02-13 | 2024-02-15 | 32821.35 | -32821.35 | 0 | Authorized | 5076 | 01 | E-76 approved on | NA | 0 | 0 | 2 | NA | In The City Of Lakeport, South Main Street 167' N Of Martin St. 80' S Of | Permanent Restoration | 7 | 2024-02-13 | 2024-02-13 | NON-MPO |  |  | NT49J8BP91L8
Obligated | ER | 4400(046) | Humboldt County | 2024-02-13 | 2024-02-13 | 2024-02-13 | 2024-02-13 | 2024-02-15 | 0 | 0 | 0 | Authorized | 5904 | 01 | E-76 approved on | NA | 0 | 0 | 2 | NA | Alderpoint Road Pm 40.21 To 40.70 | Emergency Relief Pr Only | 7 | 2024-02-13 | 2024-02-13 | NON-MPO |  |  | UBWEAY8NDL25
Obligated | BHLS | 5910(081) | Mendocino County | 2024-02-12 | 2024-02-12 | 2024-03-08 | 2024-03-08 | 2024-03-12 | 13168836 | 0 | 14875000 | Authorized | 5910 | 01 | E-76 approved on | NA | 31 | 25 | 4 | HBPLOCAL | In Mendocino County: North State Street Bridge Over Ackerman Creek, 0.2 Mi N | Bridge Replacement | 7 | 2024-01-12 | 2024-01-12 | NON-MPO |  |  | JKULS1AA5J33
Obligated | BRLO | 5905(109) | Trinity County | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-05 | 0 | 0 | 0 | Authorized | 5905 | 02 | E-76 approved on | NA | 3 | 0 | 4 | HBPLOCAL | East Fork Hayfork Rd Over Hayfork Crk, 0.2 Mi E Wildwood Rd | Bridge Replacement (tc) | 2 | 2024-02-27 | 2024-03-01 | NON-MPO |  |  | L5JFNKZB8L75
Obligated | BRLO | 5905(111) | Trinity County | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-05 | 0 | 0 | 0 | Authorized | 5905 | 02 | E-76 approved on | NA | 3 | 0 | 4 | 230-0000-0031 | Lorenz Street, 100 Ft South Of Sr 299 | Bridge Replacement (tc) | 3 | 2024-02-27 | 2024-03-01 | NON-MPO |  |  | L5JFNKZB8L75
Obligated | BRLO | 5905(114) | Trinity County | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-05 | 0 | 0 | 0 | Authorized | 5905 | 02 | E-76 approved on | NA | 3 | 0 | 4 | 230-0000-0031 | Price Creek Br (05c-0164) 0.2 Miles South Of Sr 299 | Bridge Replacement (tc) | 3 | 2024-02-27 | 2024-03-01 | NON-MPO |  |  | L5JFNKZB8L75
Obligated | ER-ACST | 40A0(085) | Trinity County | 2024-02-28 | 2024-02-28 | 2024-02-28 | 2024-03-19 | 2024-03-25 | 0 | 0 | 0 | Authorized | 5905 | 02 | E-76 approved on | NA | 0 | 20 | 6 | NA | Hyampom Road Pm Begin 20.1 Pm End 20.3 | Place Signs And Barricades. Construct And Maintain Detour. | 3 | 2024-02-28 | 2024-02-28 | NON-MPO |  |  | L5JFNKZB8L75
Obligated | BHLS | 5068(039) | Redding | 2024-02-04 | 2024-02-04 | 2024-02-06 | 2024-02-06 | 2024-02-13 | 0 | 0 | 0 | Authorized | 5068 | 02 | E-76 approved on | NA | 19 | 2 | 7 | BRDGE-LUM | Girvan Road Over Olney Creek Br#06c0341 | Bridge Replacement | 4 | 2024-01-16 | 2024-02-06 | SHASTA |  |  | GRWNHECLZHF1
Obligated | SRTSL | 5908(092) | Tehama County | 2024-01-30 | 2024-01-30 | 2024-02-07 | 2024-02-07 | 2024-02-13 | 80947.07 | 0 | 80947.07 | Authorized | 5908 | 02 | E-76 approved on | NA | 4 | 8 | 6 | SRTS3-02-003 | Standford Avenue Between Rose Street And Grant Street In Los Molinos | Pedestrian Path & Curb, Install Crosswalk, Sign & Stripe Tc | 4 | 2024-01-26 | 2024-01-30 | NON-MPO |  |  | JNGACGN2N453
Obligated | ER | 32L0(545) | Redding | 2024-02-26 | 2024-02-26 | 2024-02-26 | 2024-02-26 | 2024-02-28 | 0 | 0 | 0 | Authorized | 5068 | 02 | E-76 approved on | NA | 4 | 0 | 2 | EMERGENCY | On Keswick Dam Road Approximately 2,250 Feet West Of Lake Boulevard. | Place Barricades And Close Roadway. Replace Culvert, Install Headwalls, | 4 | 2024-02-22 | 2024-02-23 | SHASTA |  |  | GRWNHECLZHF1
Obligated | BHLS | 5068(045) | Redding | 2024-01-31 | 2024-02-21 | 2024-03-01 | 2024-03-06 | 2024-03-11 | 867191 | -646269 | 249545 | Authorized | 5068 | 02 | E-76 approved on | NA | 41 | 14 | 5 | BRDGE-LUM | Old Alturas Road (bridge # 06c-0104) At Churn Creek, 1.5 Miles West Of Old | Bridge Rehab - Widening And Sidewalks | 7 | 2024-01-11 | 2024-02-21 | SHASTA |  |  | GRWNHECLZHF1
Obligated | BRLS | 5068(036) | Redding | 2024-03-06 | 2024-03-06 | 2024-03-06 | 2024-03-08 | 2024-03-11 | 0 | 0 | 0 | Authorized | 5068 | 02 | E-76 approved on | NA | 0 | 2 | 3 | BRDGE-LUM | Eastside Road At Olney Creek Br.# 06c0335 | Bridge Replacement | 8 | 2024-03-06 | 2024-03-06 | SHASTA |  |  | GRWNHECLZHF1
Obligated | BRLSZD | 5908(031) | Tehama County | 2024-02-01 | 2024-02-28 | 2024-03-15 | 2024-03-18 | 2024-03-20 | 3671129 | 0 | 4146763 | Authorized | 5908 | 02 | E-76 approved on | NA | 33 | 19 | 2 | HBPLOCAL | Jellys Ferry Rd Over Sacramento River Bridge (br. #08c0043) | Bridge Replacement On New Alignment | 17 | 2024-01-26 | 2024-03-15 | NON-MPO |  |  | JNGACGN2N453
Obligated | BRLO | 5924(209) | Sacramento County | 2024-01-18 | 2024-01-18 | 2024-01-23 | 2024-01-29 | 2024-02-01 | 150000 | 0 | 150000 | Authorized | 5924 | 03 | E-76 approved on | NA | 6 | 11 | 3 | SAC24772 | Tyler Is Br Rd Over Georgiana Slough, 1.5 Mi E Of Isleton. Br.# 24c0042 | Replace The Existing 2 Lane Bridge With A New 2 Lane Bridge. (tc) | 1 | 2024-01-12 | 2024-01-18 | SACOG |  |  | U4B4VX3V7GK3
Obligated | ACSTP | 15J7(059) | El Dorado County | 2024-03-18 | 2024-03-18 | 2024-03-19 | 2024-03-20 | 2024-03-27 | 0 | 114683.65 | 114683.65 | Authorized | 5925 | 03 | E-76 approved on | NA | 0 | 2 | 7 | NA | In El Dorado County On Latrobe Rd Near Cothrin Road. | Dig Out And Remove Existing 48" Cmp Culvert. Dug 14' Wide Trench Across | 1 | 2024-03-18 | 2024-03-18 | NON-MPO |  |  | R8JPSXALG464
Obligated | BPMPL | 5919(164) | Placer County | 2024-03-06 | 2024-03-06 | 2024-03-07 | 2024-03-11 | 2024-03-12 | 1203200 | 0 | 1504000 | Authorized | 5919 | 03 | E-76 approved on | NA | 5 | 5 | 1 | PLA25875 | 0.63 Mi East Of I-80 On Foresthill Road. Br.# 19c0060 | Perform Non-destructive Testing Of 280 Weld Locations. Work Includes | 1 | 2024-03-01 | 2024-03-06 | SACOG |  |  | L786NC553FC1
Obligated | BPMPL | 5924(282) | Sacramento County | 2024-02-06 | 2024-03-12 | 2024-03-14 | 2024-03-18 | 2024-03-20 | 528800 | 0 | 661000 | Authorized | 5924 | 03 | E-76 approved on | NA | 48 | 6 | 2 | SAC25084 | Bridge No. Pm00184, Bridge Preventive Maintenance Program (bpmp) Various | Bridge Preventative Maintenance Program Bpmp Various Bridges In Sacramento | 1 | 2024-01-24 | 2024-03-12 | SACOG |  |  | U4B4VX3V7GK3
Obligated | STPL | 5293(024) | Galt | 2024-01-16 | 2024-01-16 | 2024-01-19 | 2024-02-01 | 2024-02-08 | 0 | 275000 | 311000 | Authorized | 5293 | 03 | E-76 approved on | NA | 12 | 16 | 7 | SAC25349 | In The City Of Galt, On Fourth Street. | Complete The Remaining 225 Ft North To A Street. | 1 | 2024-01-04 | 2024-01-16 | SACOG |  | Warning | NLG5DK225EJ4
Obligated | CRPLNI | 6085(092) | Sacramento Area Council of Governments | 2024-02-06 | 2024-02-07 | 2024-02-07 | 2024-02-13 | 2024-02-23 | 100000 | 0 | 112957 | Authorized | 6085 | 03 | E-76 approved on | NA | 19 | 6 | 10 | VAR56290 | Sacog Six-county Region | Planning Work In Support Of The Regional Carbon Reduction Strategy Including | 1 | 2024-01-19 | 2024-02-05 | SACOG |  |  | YXLCCEGACKS3
Obligated | STPLNI | 6085(093) | Sacramento Area Council of Governments | 2024-02-21 | 2024-02-28 | 2024-02-28 | 2024-03-04 | 2024-03-07 | 1500000 | 0 | 1500000 | Authorized | 6085 | 03 | E-76 approved on | NA | 28 | 5 | 3 | VAR56283 | Sacog Six-county Region (el Dorado, Placer, Sacramento, Sutter, Yolo, Yuba) | In The Sacog Region: Promote Alternative Mode Use (such As Rideshare, | 1 | 2024-01-31 | 2024-02-27 | SACOG |  |  | YXLCCEGACKS3
Obligated | BRLS | 5917(115) | Nevada County | 2024-02-06 | 2024-02-06 | 2024-02-07 | 2024-02-07 | 2024-02-14 | 236000 | 0 | 295000 | Authorized | 5917 | 03 | E-76 approved on | NA | 0 | 1 | 7 | 230-0000-0031 | Br No 17c0051, Donner Pass Rd Approximately 0.5 Miles East Of Soda Springs | Bridge No. 17c0051, Donner Pass Rd, Over Soda Springs Creek, 0.5 Mi E Soda | 1 | 2024-02-06 | 2024-02-06 | NON-MPO |  |  | QDDBKGRJTRL5
Obligated | STPL | 5916(152) | Yuba County | 2024-02-26 | 2024-02-28 | 2024-03-01 | 2024-03-05 | 2024-03-11 | 300000 | 0 | 424000 | Authorized | 5916 | 03 | E-76 approved on | NA | 0 | 6 | 6 | YUB16103 | In The Unincorporated Community Of Olivehurst, Construct A Safe Routes To | Design For 5,300 Linear Feet Of Sidewalks, New Crosswalks, Striping, Ada | 1 | 2024-02-28 | 2024-02-28 | SACOG |  |  | LH3ELMEX1L73
Obligated | STPL | 5479(037) | Elk Grove | 2024-03-05 | 2024-03-06 | 2024-03-12 | 2024-03-13 | 2024-03-19 | 0 | 5627000 | 6356038 | Authorized | 5479 | 03 | E-76 approved on | NA | 5 | 7 | 6 | SAC24094 | Kammerer Rd From Bruceville Rd To I-5 (at Hood Franklin Rd) | Kammerer Rd. Extension | 2 | 2024-03-01 | 2024-03-05 | SACOG |  |  | GHJBWTLJK3D7
Obligated | BRLO | 5922(111) | Yolo County | 2024-02-15 | 2024-02-15 | 2024-02-20 | 2024-02-21 | 2024-02-26 | 388000 | 0 | 388000 | Authorized | 5922 | 03 | E-76 approved on | NA | 1 | 6 | 5 | YOL19390 | Cr-49 Over Hamilton Creek 0.11 Miles North Of Cr-50. Br.# 22c0095 | Replace Existing 2-lane Functionally Obsolete Bridge With A New 2-lane | 2 | 2024-02-14 | 2024-02-15 | SACOG |  |  | F9LLL27DJFY4
Obligated | BRLO | 5916(131) | Yuba County | 2024-03-01 | 2024-03-01 | 2024-03-05 | 2024-03-05 | 2024-03-11 | 0 | 0 | 0 | Authorized | 5916 | 03 | E-76 approved on | NA | 0 | 4 | 6 | yub16072 | Ellis Rd Over Simmerly Slough, 1.0 Miles East Of Sr 70. | Replace Existing 2 Lane Bridge With A 2 Lane (tc) | 2 | 2024-03-01 | 2024-03-05 | SACOG |  |  | LH3ELMEX1L73
Obligated | CMLNI | 6236(020) | Sacramento Metropolitan Air Quality Management District | 2024-02-20 | 2024-02-20 | 2024-02-21 | 2024-02-22 | 2024-02-28 | -4500001 | 0 | -4500001 | Authorized | 6236 | 03 | E-76 approved on | NA | 6 | 2 | 6 | VAR56195 | In Sacramento County. | Phase 3 Sacramento Emergency Clean Air Transportation Program (secat). (tc) | 2 | 2024-02-14 | 2024-02-20 | SACOG |  |  | D95DUST1M9Q5
Obligated | CML | 5447(055) | West Sacramento | 2023-09-19 | 2024-03-05 | 2024-03-14 | 2024-03-18 | 2024-03-20 | 3733861 | 0 | 4217623 | Authorized | 5447 | 03 | E-76 approved on | NA | 0 | 13 | 2 | YOL19531 | Project Spans Sacramento River From 2nd/d Street In West Sacramento, Up To | Convert The Upper Deck Of The Historic I Street Railroad Bridge From Motor | 2 | 2024-03-05 | 2024-03-05 | SACOG |  |  | MLGYAWLU57K3
Obligated | ER | 15J7(002) | Glenn County | 2024-02-05 | 2024-02-05 | 2024-02-05 | 2024-02-07 | 2024-02-14 | 0 | 0 | 0 | Authorized | 5911 | 03 | E-76 approved on | NA | 0 | 2 | 7 | NA | County Rd 306 Bridge Over Salt Creek | Remove Existing Fill And Embankment Behind Each Abutment, Place New | 2 | 2024-02-05 | 2024-02-05 | NON-MPO |  |  | MNEBKANJ89S5
Obligated | ER | 15J7(062) | El Dorado County | 2024-02-05 | 2024-02-05 | 2024-02-05 | 2024-02-09 | 2024-02-16 | 21704.01 | -21704.01 | 0 | Authorized | 5925 | 03 | E-76 approved on | NA | 0 | 4 | 7 | NA | In El Dorado County At Green Valley Rd. | Green Valley Rd Slip Undermining The Roadway. Saw Cut Existing Undermined | 2 | 2024-02-05 | 2024-02-05 | NON-MPO |  |  | R8JPSXALG464
Obligated | ER | 15J7(063) | El Dorado County | 2024-02-05 | 2024-02-05 | 2024-02-05 | 2024-02-15 | 2024-02-23 | 13738.67 | -13738.67 | 0 | Authorized | 5925 | 03 | E-76 approved on | NA | 0 | 10 | 8 | NA | Lotus Rd | Sinkhole In The Roadway. Saw Cut 4'x10' Piece Od Asphalt Where Undennining | 2 | 2024-02-05 | 2024-02-05 | NON-MPO |  |  | R8JPSXALG464
Obligated | ER | 15J7(064) | El Dorado County | 2024-02-05 | 2024-02-05 | 2024-02-05 | 2024-02-09 | 2024-02-16 | 263770.83 | -263770.83 | 0 | Authorized | 5925 | 03 | E-76 approved on | NA | 0 | 4 | 7 | NA | Newtown Road Near Big Barn Road | Newtown Road Culvert And Road Failure. Culvert Under Road Failed And Was | 2 | 2024-02-05 | 2024-02-05 | NON-MPO |  |  | R8JPSXALG464
Obligated | HSIPL | 5919(160) | Placer County | 2024-03-06 | 2024-03-06 | 2024-03-12 | 2024-03-20 | 2024-03-20 | 204210 | 0 | 226900 | Authorized | 5919 | 03 | E-76 approved on | NA | 13 | 14 | 0 | PLA25877 | Colfax/gold Run And Dutch Flat/alta. | Replace Old Guardrail With New Guardrail And End Treatments Along Magra Road | 2 | 2024-02-22 | 2024-03-04 | SACOG |  |  | L786NC553FC1
Obligated | STPL | 5293(024) | Galt | 2024-02-14 | 2024-02-14 | 2024-02-14 | 2024-02-20 | 2024-02-28 | 275000 | -275000 | 0 | Authorized | 5293 | 03 | E-76 approved on | NA | 5 | 6 | 8 | SAC25349 | In The City Of Galt, On Fourth Street. | Complete The Remaining 225 Ft North To A Street. | 2 | 2024-02-09 | 2024-02-14 | SACOG |  | negatie or zero funding | NLG5DK225EJ4
Obligated | BRLO | 5037(024) | Chico | 2024-02-21 | 2024-02-21 | 2024-02-21 | 2024-02-21 | 2024-02-26 | 0 | 0 | 0 | Authorized | 5037 | 03 | E-76 approved on | NA | 6 | 0 | 5 | 202-0000-0056 | Pomona Road At Little Chico Creek Bridge Br. No. 12c-328 ~0.4 M Se Of Miller | Bridge Replacement (tc) | 3 | 2024-02-15 | 2024-02-16 | BCAG |  |  | CBM1U23HUPK5
Obligated | ATPL | 5238(068) | Davis | 2024-02-20 | 2024-03-05 | 2024-03-05 | 2024-03-08 | 2024-03-12 | 0 | 0 | 966360.68 | Authorized | 5238 | 03 | E-76 approved on | NA | 14 | 3 | 4 | YOL19393 | Montgomery Elementary School, Olive Drive Neighborhood To The Two-way Multi- | Design And Construct Safe Routes To School Infrastructure Improvements For | 3 | 2024-02-20 | 2024-02-20 | SACOG |  |  | VKLKHSYNDZ99
Obligated | HSIPL | 5919(140) | Placer County | 2024-02-14 | 2024-02-16 | 2024-02-24 | 2024-02-26 | 2024-02-28 | 805339 | -100000 | 773503.53 | Authorized | 5919 | 03 | E-76 approved on | NA | 3 | 10 | 2 | PLA25778 | Foresthill Road Between Old Auburn-foresthill Road And Spring Garden Road. | Install High Friction Surface Treatment, Guardrail And Warning Signs(tc). | 3 | 2024-02-13 | 2024-02-15 | SACOG |  |  | L786NC553FC1
Obligated | CML | 5425(043) | Paradise | 2024-02-09 | 2024-02-09 | 2024-02-13 | 2024-02-13 | 2024-02-23 | 0 | 0 | 0 | Authorized | 5425 | 03 | E-76 approved on | NA | 17 | 4 | 10 | CMAQ18B2 | Neal Road Between Town Limits And Skyway, And Skyway Between Neal Road And | Construct A Grade Separated, Class I, Bike-ped Facility (tc) | 3 | 2024-01-23 | 2024-02-13 | BCAG |  |  | KQ7GRKNP8QS1
Obligated | CML | 5425(044) | Paradise | 2024-02-12 | 2024-02-12 | 2024-02-13 | 2024-02-13 | 2024-02-23 | 0 | 0 | 0 | Authorized | 5425 | 03 | E-76 approved on | NA | 20 | 1 | 10 | CMAQ18P3 | Oliver Curve Class I (oliver Road Between Skyway Andbille Rd And Bille Rd | Construct A Grade Separated Class I Bike-ped Facility (tc) | 3 | 2024-01-23 | 2024-02-13 | BCAG |  |  | KQ7GRKNP8QS1
Obligated | STPL | 5479(068) | Elk Grove | 2024-01-16 | 2024-01-16 | 2024-01-24 | 2024-01-29 | 2024-02-01 | 605000 | 0 | 1057319 | Authorized | 5479 | 03 | E-76 approved on | NA | 7 | 13 | 3 | SAC25172 | Lewis Stein Rd, From Sheldon Road To West Stockton Blvd; And West Stockton | Rehab 1.2 Miles Of Pavement, Replace Ada Curb Ramps And Install Detectable | 3 | 2024-01-09 | 2024-01-16 | SACOG |  |  | GHJBWTLJK3D7
Obligated | ATPCML | 5002(219) | Sacramento | 2024-01-29 | 2024-02-01 | 2024-02-08 | 2024-02-09 | 2024-02-21 | 8411000 | 9323000 | 21153042 | Authorized | 5002 | 03 | E-76 approved on | NA | 7 | 8 | 12 | SAC25195 | In Sacramento, Franklin Blvd., From 19th Ave. To Sutterville Rd | Reduce From 4 Lanes To 2 With 2-way Left Turn Lane (on Street Parking As | 3 | 2024-01-25 | 2024-02-01 | SACOG |  |  | J2BKNF7K3PY3
Obligated | STPL | 5925(182) | El Dorado County | 2024-01-29 | 2024-02-07 | 2024-02-16 | 2024-02-27 | 2024-02-29 | 2056000 | 0 | 4859352 | Authorized | 5925 | 03 | E-76 approved on | NA | 16 | 20 | 2 | GROUP1 | Apache Ave From Highway 50 To The Lake Tahoe Environmental Science Magnet | Active Transportation Improvements Along Apache Ave From Us50/sr89 | 3 | 2024-01-22 | 2024-02-07 | TAHOE |  |  | R8JPSXALG464
Obligated | STPL | 5925(183) | El Dorado County | 2024-02-04 | 2024-02-04 | 2024-02-04 | 2024-02-04 | 2024-02-07 | 0 | 0 | 0 | Authorized | 5925 | 03 | E-76 approved on | NA | 19 | 0 | 3 | GROUP1 | In Eastern Ei Dorado County, In The Tahoe Basin, In The City Of South Lake | Construct A Class 1 Pathway Approximately 1.2 Miles From The East End Of | 3 | 2024-01-16 | 2024-02-04 | TAHOE |  |  | R8JPSXALG464
Obligated | HIPCML | 5037(040) | Chico | 2024-02-27 | 2024-02-27 | 2024-03-01 | 2024-03-01 | 2024-03-11 | 0 | 0 | 0 | Authorized | 5037 | 03 | E-76 approved on | NA | 4 | 3 | 10 | CMAQ21C | Hegan Lane Business Park Access Improvements, Phase 1 Includes The | Operational And Safety Improvements To The Hegan Lane Business Park | 3 | 2024-02-23 | 2024-02-29 | BCAG |  |  | CBM1U23HUPK5
Obligated | ER | 15A5(041) | Butte County | 2024-02-14 | 2024-02-14 | 2024-02-14 | 2024-02-14 | 2024-02-21 | -134479.19 | 0 | -149996.31 | Authorized | 5912 | 03 | E-76 approved on | NA | 6 | 0 | 7 | NA | In Butte County - Lower Wyandotte Rd | Asphalt Grinding, With Addition Of Cement, And Asphalt Overlay With New | 3 | 2024-02-08 | 2024-02-09 | NON-MPO |  |  | G14XJJ9RPBP5
Obligated | ATPCML | 5479(072) | Elk Grove | 2024-02-01 | 2024-02-01 | 2024-02-06 | 2024-02-07 | 2024-02-14 | 598000 | 0 | 598000 | Authorized | 5479 | 03 | E-76 approved on | NA | 3 | 6 | 7 | SAC25295 | In Elk Grove At Laguna Creek And State Route 99, Between Sheldon Road And | Construct A Class 1 Bicycle And Pedestrian Crossing Over State Route 99. | 3 | 2024-01-29 | 2024-02-01 | SACOG |  |  | GHJBWTLJK3D7
Obligated | ER-ACST | 15J1(001) | Butte County | 2024-02-07 | 2024-02-07 | 2024-02-07 | 2024-02-09 | 2024-02-16 | 791488.13 | -791488.13 | 0 | Authorized | 5912 | 03 | E-76 approved on | NA | 0 | 2 | 7 | NA | In Butte County - Oro Quincy Hwy Near Mountain House | Replacing In Kind Damaged Roadway, Mse, Culverts, Rsp, Ac Dike, And | 3 | 2024-02-07 | 2024-02-07 | NON-MPO |  |  | G14XJJ9RPBP5
Obligated | ER | 15J7(003) | Butte County | 2024-02-05 | 2024-02-05 | 2024-02-05 | 2024-02-07 | 2024-02-14 | 255200 | -255200 | 0 | Authorized | 5912 | 03 | E-76 approved on | NA | 0 | 2 | 7 | NA | Due To Atmospheric River Winter Storms Of Jan 2023 3200 Lf Of Newly | Personnel Have Closed The Roadway And Cleared Roadway Of Downed Trees; | 3 | 2024-02-05 | 2024-02-05 | BCAG |  |  | G14XJJ9RPBP5
Obligated | STPCML | 5482(013) | Rancho Cordova | 2024-01-30 | 2024-01-30 | 2024-01-30 | 2024-01-30 | 2024-02-02 | 0 | 0 | 0 | Authorized | 5482 | 03 | E-76 approved on | NA | 5 | 0 | 3 | SAC25271 | In The City Of Rancho Cordova, On White Rock Rd From Fitzgerald Dr. To .5 | Widen From 2-4 Lanes, Add Center Medians, Bike Lanes, Install Traffic Signal | 4 | 2024-01-25 | 2024-01-26 | SACOG |  |  | ZPFZUH75WCL2
Obligated | BRLO | 5037(024) | Chico | 2024-02-27 | 2024-02-27 | 2024-02-27 | 2024-02-27 | 2024-03-01 | 0 | 0 | 2044.59 | Authorized | 5037 | 03 | E-76 approved on | NA | 5 | 0 | 3 | 202-0000-0056 | Pomona Road At Little Chico Creek Bridge Br. No. 12c-328 ~0.4 M Se Of Miller | Bridge Replacement (tc) | 4 | 2024-02-22 | 2024-02-23 | BCAG |  |  | CBM1U23HUPK5
Obligated | BRLO | 5912(091) | Butte County | 2024-02-20 | 2024-02-20 | 2024-02-20 | 2024-02-20 | 2024-02-27 | 0 | 0 | 0 | Authorized | 5912 | 03 | E-76 approved on | NA | 19 | 0 | 7 | 20RTP5-12 | East Rio Bonito Road At Hamilton Slough ~0.2 Mi E. Of Sr 99 - Br. #12c-0164 | Bridge Replacement (tc) | 4 | 2024-02-01 | 2024-02-20 | BCAG |  |  | G14XJJ9RPBP5
Obligated | BRLS | 5916(104) | Yuba County | 2024-02-12 | 2024-02-27 | 2024-02-29 | 2024-03-04 | 2024-03-11 | 5772156 | 0 | 6637376 | Authorized | 5916 | 03 | E-76 approved on | NA | 4 | 6 | 7 | YUB16031 | Los Verjeles Rd At Honcut Creek On The Yuba/butte County Line. Br. # | Bridge Replacement | 4 | 2024-02-23 | 2024-02-27 | SACOG |  |  | LH3ELMEX1L73
Obligated | CML | 5925(132) | El Dorado County | 2023-10-10 | 2024-01-12 | 2024-01-25 | 2024-01-30 | 2024-02-01 | 2917370 | 0 | 5140470 | Authorized | 5925 | 03 | E-76 approved on | NA | 94 | 18 | 2 | ELD19380 | On Missouri Flat Road, 0.9 Miles Se Of Us50 | Construct A Multi-use Ped/bike Over-crossing (tc) | 4 | 2023-10-10 | 2024-01-12 | SACOG |  |  | R8JPSXALG464
Obligated | BRLO | 5917(097) | Nevada County | 2024-02-20 | 2024-02-20 | 2024-02-23 | 2024-02-27 | 2024-03-11 | 1467500 | 0 | 1499050 | Authorized | 5917 | 03 | E-76 approved on | NA | 4 | 7 | 13 | HBPLOCAL | Hirschdale Road At Uprr Crossing. Br. # 17c0046. | Bridge Rehabilitation (tc) | 4 | 2024-02-16 | 2024-02-20 | NON-MPO |  |  | QDDBKGRJTRL5
Obligated | STPL | 5009(030) | Marysville | 2024-03-04 | 2024-03-06 | 2024-03-12 | 2024-03-13 | 2024-03-19 | 0 | 0 | 0 | Authorized | 5009 | 03 | E-76 approved on | NA | 0 | 7 | 6 | YUB16054 | 5th St From Sr70 To J St And 2nd St From Sr70 To J St, Including The Medical | 1. Rehabilitate Roadway (fifth Street (5th St) From Hwy 70 To J St , | 4 | 2024-03-06 | 2024-03-06 | SACOG |  |  | GN9MKMAANH97
Obligated | HSIPL | 5447(047) | West Sacramento | 2023-12-20 | 2024-01-26 | 2024-01-29 | 2024-01-31 | 2024-02-06 | 289774 | 0 | 321972 | Authorized | 5447 | 03 | E-76 approved on | NA | 37 | 5 | 6 | YOL19449 | Various Signalized And Non-signalized Intersections. | Install Approach Medians And Medians To Prohibit Left Turns. | 4 | 2023-12-20 | 2024-01-09 | SACOG |  |  | MLGYAWLU57K3
Obligated | HSIPL | 5447(048) | West Sacramento | 2023-12-25 | 2024-01-26 | 2024-01-29 | 2024-01-31 | 2024-02-06 | 719703 | 0 | 1039235 | Authorized | 5447 | 03 | E-76 approved on | NA | 37 | 5 | 6 | YOL19450 | Various Signalized Intersections | Improve Signal Hardware And Install Flashing Beacons(h9-03-027). | 4 | 2023-12-20 | 2024-01-24 | SACOG |  |  | MLGYAWLU57K3
Obligated | HSIPL | 5447(049) | West Sacramento | 2023-12-25 | 2024-01-31 | 2024-02-02 | 2024-02-06 | 2024-02-14 | 594782 | 0 | 675883 | Authorized | 5447 | 03 | E-76 approved on | NA | 21 | 6 | 8 | YOL19451 | Intersections Of Jefferson Blvd & 11th St, C St & 6th St, Sacramento Ave & | Install Crossings With Rrfbs And Refuge Islands, Construct Curb Extensions, | 4 | 2024-01-10 | 2024-01-24 | SACOG |  |  | MLGYAWLU57K3
Obligated | HSIPL | 5447(050) | West Sacramento | 2023-12-25 | 2024-02-06 | 2024-02-09 | 2024-02-13 | 2024-02-27 | 164939 | 0 | 164939 | Authorized | 5447 | 03 | E-76 approved on | NA | 48 | 7 | 14 | YOL19452 | Various Locatoins Including Reuter/andrews, Poplar/westfield Village Es, | Install Striping For High Visibility Crossings And Stop Bars, Install Rrfbs | 4 | 2023-12-20 | 2024-01-10 | SACOG |  |  | MLGYAWLU57K3
Obligated | STPL | 5479(068) | Elk Grove | 2024-02-27 | 2024-02-27 | 2024-03-08 | 2024-03-11 | 2024-03-12 | 966000 | 0 | 1491042 | Authorized | 5479 | 03 | E-76 approved on | NA | 4 | 13 | 1 | SAC25172 | Lewis Stein Rd, From Sheldon Road To West Stockton Blvd; And West Stockton | Rehab 1.2 Miles Of Pavement, Replace Ada Curb Ramps And Install Detectable | 4 | 2024-02-23 | 2024-02-27 | SACOG |  |  | GHJBWTLJK3D7
Obligated | CRRSASTL | 5924(266) | Sacramento County | 2024-01-31 | 2024-02-01 | 2024-02-06 | 2024-02-07 | 2024-02-14 | 1350000 | -1350000 | 0 | Authorized | 5924 | 03 | E-76 approved on | NA | 1 | 6 | 7 | SAC25302 | Multiple Locations | Construct Complete Street Improvements Consisting Of An Asphalt Concrete | 4 | 2024-01-31 | 2024-02-01 | SACOG |  |  | U4B4VX3V7GK3
Obligated | STPL | 5288(052) | Folsom | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-01 | 2024-03-11 | 0 | 0 | 0 | Authorized | 5288 | 03 | E-76 approved on | NA | 2 | 0 | 10 | SAC25310 | In The City Of Folsom. This Is An Its Master Plan. | The Project Will Design And Provide Plans, Specifications And Estimates | 4 | 2024-02-28 | 2024-03-01 | SACOG |  |  | FTDELPNDKKT7
Obligated | BRLO | 5912(093) | Butte County | 2024-02-20 | 2024-02-20 | 2024-02-20 | 2024-02-20 | 2024-02-28 | 0 | 0 | 0 | Authorized | 5912 | 03 | E-76 approved on | NA | 19 | 0 | 8 | 20RTP5-12 | East Rio Bonito Rd At Sutter Buttes Canal 0.8 Mi East Of Sr99 - Br. #12c- | Bridge Replacement (tc) | 5 | 2024-02-01 | 2024-02-20 | BCAG |  |  | G14XJJ9RPBP5
Obligated | BRLO | 5916(092) | Yuba County | 2024-03-01 | 2024-03-01 | 2024-03-04 | 2024-03-05 | 2024-03-11 | 0 | 0 | 0 | Authorized | 5916 | 03 | E-76 approved on | NA | 0 | 4 | 6 | YUB16023 | Waldo Rd At Dry Creek - 1.8 Mi. South Of Smartville Rd - Br. # 16c-0006 | Bridge Replacement (tc) | 5 | 2024-03-01 | 2024-03-04 | SACOG |  |  | LH3ELMEX1L73
Obligated | BRLO | 5917(084) | Nevada County | 2023-10-27 | 2024-01-22 | 2024-02-02 | 2024-02-05 | 2024-02-08 | 4500000 | 0 | 4500000 | Authorized | 5917 | 03 | E-76 approved on | NA | 144 | 14 | 3 | HBPLOCAL | Dog Bar Road At Bear River ~0.5 Miles South East Of Magnolia Road At County | Replace 1 Lane Bridge With 2 Lane Bridge (tc) | 5 | 2023-08-31 | 2024-01-22 | NON-MPO |  |  | QDDBKGRJTRL5
Obligated | CML | 5015(026) | Placerville | 2024-03-07 | 2024-03-07 | 2024-03-07 | 2024-03-07 | 2024-03-08 | 0 | 0 | 0 | Authorized | 5015 | 03 | E-76 approved on | NA | 7 | 0 | 1 | VAR79030 | On The North Side Of Fair Ln From The County Government Center To County | Consruct Sidewalk And Class Ii Bike Lane (tc) | 5 | 2024-02-29 | 2024-03-01 | SACOG |  |  | C1H8SPDCULC7
Obligated | CML | 5924(215) | Sacramento County | 2024-03-21 | 2024-03-21 | 2024-03-21 | 2024-03-21 | 2024-03-27 | 0 | 0 | 0 | Authorized | 5924 | 03 | E-76 approved on | NA | 7 | 0 | 6 | SAC24748 | Fair Oaks Blvd. From 500ft North Of Marconi Ave. To 400ft South Of Landis | Sidewalk, Medians, And Bike Lanes (tc) | 5 | 2024-03-14 | 2024-03-15 | SACOG |  |  | U4B4VX3V7GK3
Obligated | CML | 5002(178) | Sacramento | 2024-01-30 | 2024-02-12 | 2024-02-15 | 2024-02-20 | 2024-02-27 | 0 | 0 | -213256.8 | Authorized | 5002 | 03 | E-76 approved on | NA | 168 | 8 | 7 | SAC24745 | South Sacramento Parkway Trail- West. In The City Of Sacramento, Adjacent To | Construction Of New Class I Bike Trail | 5 | 2023-08-28 | 2024-02-08 | SACOG |  |  | J2BKNF7K3PY3
Obligated | BRLO | 5918(101) | Sutter County | 2024-02-24 | 2024-02-24 | 2024-03-17 | 2024-03-17 | 2024-03-19 | 0 | 0 | 0 | Authorized | 5918 | 03 | E-76 approved on | NA | 9 | 22 | 2 | SUT18925 | On Howsley Rd, 1.02 Mile East Of State Route 99 | Bridge Replacement (tc) | 5 | 2024-02-15 | 2024-03-17 | SACOG |  |  | Y94DGUBNJHG3
Obligated | ATPCML | 5182(074) | Roseville | 2024-01-30 | 2024-01-30 | 2024-01-30 | 2024-01-30 | 2024-02-01 | 0 | 0 | 0 | Authorized | 5182 | 03 | E-76 approved on | NA | 5 | 0 | 2 | PLA25702 | In The City Of Roseville Along Washington Blvd. Between All American Blvd. | Realign And Construct New Class 1 Bike Path, Improve Intersection Crossing | 5 | 2024-01-25 | 2024-01-26 | SACOG |  |  | W49TKZLUYCJ3
Obligated | HSIPL | 5475(041) | Citrus Heights | 2024-03-05 | 2024-03-05 | 2024-03-05 | 2024-03-05 | 2024-03-11 | 0 | 0 | 26317.3 | Authorized | 5475 | 03 | E-76 approved on | NA | 5 | 0 | 6 | SAC25053 | Various Signalized Intersections Throughout The City Of Citrus Heights. | Upgrade All Existing 8" And Combination Vehicle Signal Indications To 12" | 5 | 2024-02-29 | 2024-03-01 | SACOG |  |  | LAC8UN8JZAK9
Obligated | CML | 5398(013) | South Lake Tahoe | 2024-01-25 | 2024-01-25 | 2024-02-08 | 2024-02-08 | 2024-02-12 | -655.15 | 0 | -330453.91 | Authorized | 5398 | 03 | E-76 approved on | NA | -7 | 14 | 4 | 220-0000-0110 | Lake Tahoe Blvd From Viking Way To South Wye. | Class 1 Bike Trail (tc) | 5 | 2024-02-01 | 2024-02-02 | TAHOE |  |  | LMVWDXADCD38
Obligated | STPL | 5475(046) | Citrus Heights | 2024-01-31 | 2024-01-31 | 2024-02-11 | 2024-02-12 | 2024-02-21 | 1300000 | -1300000 | -989647 | Authorized | 5475 | 03 | E-76 approved on | NA | 1 | 12 | 9 | SAC25261 | In Citrus Heights - On San Juan Ave From Madison Ave To Spicer Dr; On San | Rehabilitate Pavement; Repair Curb, Gutter, And Sidewalk; Infill Pedestrian | 5 | 2024-01-30 | 2024-01-31 | SACOG |  |  | LAC8UN8JZAK9
Obligated | BRLO | 5912(092) | Butte County | 2024-01-30 | 2024-01-30 | 2024-02-04 | 2024-02-04 | 2024-02-07 | 0 | 0 | 0 | Authorized | 5912 | 03 | E-76 approved on | NA | -1 | 5 | 3 | CO_BRDIGE | Central House Road At Wyman Ravine ~0.2 Mi East Of Sr70 Br. #12c-0111 | Bridge Replacement (tc) | 6 | 2024-01-31 | 2024-02-04 | BCAG |  |  | G14XJJ9RPBP5
Obligated | CML | 5015(026) | Placerville | 2024-03-11 | 2024-03-11 | 2024-03-11 | 2024-03-11 | 2024-03-19 | 0 | 0 | 95047.89 | Authorized | 5015 | 03 | E-76 approved on | NA | 4 | 0 | 8 | VAR79030 | On The North Side Of Fair Ln From The County Government Center To County | Consruct Sidewalk And Class Ii Bike Lane (tc) | 6 | 2024-03-07 | 2024-03-08 | SACOG |  |  | C1H8SPDCULC7
Obligated | BPMPL | 5182(071) | Roseville | 2024-02-23 | 2024-02-23 | 2024-02-28 | 2024-03-04 | 2024-03-07 | -581385.2 | 0 | -815159 | Authorized | 5182 | 03 | E-76 approved on | NA | 3 | 10 | 3 | PLA25572 | Various Locations Within The City Of Roseville | Bridge Preventative Maintenance | 6 | 2024-02-20 | 2024-02-23 | SACOG |  |  | W49TKZLUYCJ3
Obligated | BRLO | 5917(092) | Nevada County | 2024-02-20 | 2024-02-27 | 2024-03-07 | 2024-03-08 | 2024-03-12 | 4740000 | 0 | 4868026 | Authorized | 5917 | 03 | E-76 approved on | NA | 116 | 10 | 4 | HBPLOCAL | Hirschdale Road At The Truckee River ~1.2 Miles Southeast Of State Highway | Replace The Existing One Lane Bridge With A One Lane Bridge. (tc) | 6 | 2023-11-03 | 2024-02-20 | NON-MPO |  |  | QDDBKGRJTRL5
Obligated | HSIPL | 5037(029) | Chico | 2024-03-21 | 2024-03-21 | 2024-03-21 | 2024-03-21 | 2024-03-27 | 0 | 0 | 0 | Authorized | 5037 | 03 | E-76 approved on | NA | 7 | 0 | 6 | 20RTP5-12 | Various Locations Within City Of Chico Limits | Citywide Systemic Safety Improvements Including Installation Of Improved | 6 | 2024-03-14 | 2024-03-15 | BCAG |  |  | CBM1U23HUPK5
Obligated | ATPCML | 5182(074) | Roseville | 2024-02-02 | 2024-02-02 | 2024-02-02 | 2024-02-02 | 2024-02-06 | -200 | 0 | 0 | Authorized | 5182 | 03 | E-76 approved on | NA | 8 | 0 | 4 | PLA25702 | In The City Of Roseville Along Washington Blvd. Between All American Blvd. | Realign And Construct New Class 1 Bike Path, Improve Intersection Crossing | 6 | 2024-01-25 | 2024-01-26 | SACOG |  |  | W49TKZLUYCJ3
Obligated | CML | 5023(021) | Grass Valley | 2024-02-15 | 2024-02-15 | 2024-02-28 | 2024-02-28 | 2024-03-07 | 0 | 0 | 0 | Authorized | 5023 | 03 | E-76 approved on | NA | 22 | 13 | 8 | BIKEPED-N | Wolf Creek Multi-use Trail - Construction Of A New Multi-use Trail From The | Installation Of An Asphalt Concrete Pavement Path. (tc) | 6 | 2024-01-24 | 2024-02-28 | NON-MPO |  | negatie or zero funding | C6RQEX468X21
Obligated | HIPCML | 6158(082) | Placer County Transportation Planning Agency | 2024-02-02 | 2024-02-29 | 2024-03-13 | 2024-03-18 | 2024-03-21 | 150000 | 1850000 | 2009813 | Authorized | 6158 | 03 | E-76 approved on | NA | 28 | 18 | 3 | PLA25670 | Various Locations Along Sr 49 From I-80 To Dry Creek Road. | Construct Ada Compliant Curb Ramps And Sidewalks/fill Gaps. (tc) | 6 | 2024-02-01 | 2024-02-29 | SACOG |  |  | RDNMNZ8QQ5H6
Obligated | ATPCML | 5002(155) | Sacramento | 2023-12-27 | 2023-12-27 | 2023-12-27 | 2024-02-08 | 2024-02-16 | 0 | 0 | 0 | Authorized | 5002 | 03 | E-76 approved on | NA | 12 | 43 | 8 | SAC24486 | South Side Of The American River Between State Route 160 And H Street | Pedestrian And Bike Path | 7 | 2023-12-15 | 2023-12-27 | SACOG |  |  | J2BKNF7K3PY3
Obligated | CML | 5919(128) | Placer County | 2024-02-15 | 2024-02-15 | 2024-02-15 | 2024-02-15 | 2024-02-23 | 0 | 0 | 0 | Authorized | 5919 | 03 | E-76 approved on | NA | 13 | 0 | 8 | PLA25549 | Martis Valley Connecting Northstar Village Roundabout To The Southerly | Class 1 Multipurpose Trail | 7 | 2024-02-02 | 2024-02-15 | SACOG |  |  | L786NC553FC1
Obligated | HSIPL | 5917(102) | Nevada County | 2024-02-12 | 2024-02-12 | 2024-02-12 | 2024-02-12 | 2024-02-21 | 0 | 0 | 1934.18 | Authorized | 5917 | 03 | E-76 approved on | NA | 4 | 0 | 9 | 230-0000-0159 | Various Road Corridors In Western Nevada County. | Conduct Guardrail Safety Audit, Identify Deficiencies, And Repair Or Upgrade | 7 | 2024-02-08 | 2024-02-09 | NON-MPO |  |  | QDDBKGRJTRL5
Obligated | BRLO | 5919(065) | Placer County | 2024-03-20 | 2024-03-20 | 2024-03-20 | 2024-03-20 | 2024-03-25 | -449446.04 | 0 | -460028.49 | Authorized | 5919 | 03 | E-76 approved on | NA | 6 | 0 | 5 | PLA25449 | Dowd Rd @ Coon Crk,0.4mi N/o Wise Rd 19c-0095 | Replace Existing 2-lane Bridge With A New 2-lane Bridge (tc) | 9 | 2024-03-14 | 2024-03-15 | SACOG |  |  | L786NC553FC1
Obligated | CML | 5038(025) | Antioch | 2023-07-20 | 2024-02-09 | 2024-02-11 | 2024-02-11 | 2024-02-21 | 1469000 | 0 | 1692079 | Authorized | 5038 | 04 | E-76 approved on | NA | 204 | 2 | 10 | CC170035 | L Street From Lemon Tree Way To Sycamore Drive And From 10th Street To The | Construction Of New Sidewalks Under The Railroad Tracks And Along The | 1 | 2023-07-20 | 2024-01-05 | MTC |  |  | VJ1LM7QMGEL3
Obligated | STPL | 5386(011) | Clayton | 2023-11-27 | 2024-01-24 | 2024-01-25 | 2024-02-04 | 2024-02-05 | 308000 | 0 | 839137 | Authorized | 5386 | 04 | E-76 approved on | NA | 65 | 11 | 1 | CC170047 | Fed-participation Includes (1) Mountaire Parkway (marsh Creek Rd To | Pavement Maintenance And Restoration, Including Replacing Pavement Markings. | 1 | 2023-11-20 | 2023-11-27 | MTC |  |  | WMANHWKQP2F9
Obligated | CML | 5299(019) | Millbrae | 2024-02-13 | 2024-02-13 | 2024-03-06 | 2024-03-07 | 2024-03-11 | 345150 | 0 | 390045 | Authorized | 5299 | 04 | E-76 approved on | NA | 8 | 23 | 4 | SM210010 | Near The Millbrae Transit Center | Install New Local Mobility Hub | 1 | 2024-02-05 | 2024-02-13 | MTC |  |  | LHC9LCUVL6F9
Obligated | BRLS | 5177(049) | South San Francisco | 2024-02-02 | 2024-02-07 | 2024-02-20 | 2024-02-22 | 2024-02-27 | 592000 | 0 | 740000 | Authorized | 5177 | 04 | E-76 approved on | NA | 6 | 15 | 5 | VAR170012 | Grand Ave Between Gateway Blvd & Dubuque Ave. 35c0148l & 35c0148r | Apply Methacrylate Or Polyester Treatment To Deck, Repair Spalled Concrete, | 1 | 2024-02-01 | 2024-02-02 | MTC |  |  | EES4XJFTXC28
Obligated | ACSTP | 15J9(163) | Contra Costa County | 2023-10-31 | 2024-02-07 | 2024-02-14 | 2024-02-20 | 2024-02-26 | 0 | 428485.2 | 484000 | Authorized | 5928 | 04 | E-76 approved on | NA | 117 | 13 | 6 | NA | Alhambra Valley Road - 1 Mile East Of Castro Ranch Rd. | Agency Installed Erosion Control Tarp, Sandbags, Traffic Control Delineator | 1 | 2023-10-13 | 2023-10-31 | MTC |  |  | KFYDUB91ZNB8
Obligated | ACSTP | 15J9(164) | Contra Costa County | 2024-02-07 | 2024-02-07 | 2024-02-14 | 2024-02-21 | 2024-02-26 | 380679 | 0 | 430000 | Authorized | 5928 | 04 | E-76 approved on | NA | 0 | 14 | 5 | NA | Alhambra Valley Road -site 2- 1.3 Miles East Of Castro Ranch Road To 1.32 | Install Soldier Pile Retaining Wall With Structural Backfill And Guardrail | 1 | 2024-02-07 | 2024-02-07 | MTC |  |  | KFYDUB91ZNB8
Obligated | ACSTP | 15J9(165) | Contra Costa County | 2024-02-07 | 2024-02-07 | 2024-02-14 | 2024-02-21 | 2024-02-26 | 0 | 380679 | 430000 | Authorized | 5928 | 04 | E-76 approved on | NA | 0 | 14 | 5 | NA | Alhambra Valley Road - Site 3- 1.6 Miles East Of Castro Ranch Rd. To 1.62 | Install Soldier Pile Retaining Wall With Guardrail To Restore/stabilize | 1 | 2024-02-07 | 2024-02-07 | MTC |  |  | KFYDUB91ZNB8
Obligated | CPFL | 5019(037) | Santa Clara | 2024-01-18 | 2024-01-25 | 2024-02-14 | 2024-02-15 | 2024-02-26 | 379432 | 0 | 430000 | Authorized | 5019 | 04 | E-76 approved on | NA | 7 | 21 | 11 | SCL230220 | Anna Drive Neighborhood. Demo Id Ca966 | Upsizing The Existing Storm Drain System | 1 | 2024-01-18 | 2024-01-25 | MTC |  |  | RK62GLSXRUK9
Obligated | BRLS | 5318(037) | Cupertino | 2023-11-16 | 2024-02-09 | 2024-02-12 | 2024-02-14 | 2024-02-21 | 184000 | 0 | 230000 | Authorized | 5318 | 04 | E-76 approved on | NA | 137 | 5 | 7 | VAR170012 | 0.2 Miles East Of Stevens Canyon Road. 37c0011 | Scour Countermeasure Project. Feasibility Study Will Be Prepared To Evaluate | 1 | 2023-09-25 | 2023-12-29 | MTC |  |  | DQ4CLU1A74G9
Obligated | STPL | 5028(088) | Santa Rosa | 2024-02-20 | 2024-02-20 | 2024-03-07 | 2024-03-08 | 2024-03-11 | 267000 | 0 | 314000 | Authorized | 5028 | 04 | E-76 approved on | NA | 7 | 17 | 3 | SON230203 | Hearn Ave From The Smart Tracks To Corby Ave | The Project Will Install A Class Iv Separated Multi-use Pathway Along The | 1 | 2024-02-13 | 2024-02-20 | MTC |  |  | MPMQPX61FMW7
Obligated | HSIPL | 5927(137) | Marin County | 2023-12-26 | 2024-01-12 | 2024-01-25 | 2024-01-29 | 2024-02-02 | 54000 | 0 | 60000 | Authorized | 5927 | 04 | E-76 approved on | NA | 31 | 17 | 4 | VAR170002 | 15 Locations Throughout Unincorporated Mrn Co. On Lucas Valley Rd, Nicasio | Replace And Upgrade Existing Guardrails And End Treatement In 15 Locations | 1 | 2023-12-12 | 2024-01-02 | MTC |  |  | DNTFCMS6YND3
Obligated | HSIPL | 5927(138) | Marin County | 2023-12-26 | 2024-01-17 | 2024-01-31 | 2024-02-29 | 2024-03-11 | 3150 | 0 | 3500 | Authorized | 5927 | 04 | E-76 approved on | NA | 35 | 43 | 11 | VAR170002 | Various Location Thourghout Co. Of Mrn-los Ranchitos Rd (san Rafael), | Install Radar Signs To Improve Traffic Safety Of Bicyclist And Pedestrians | 1 | 2023-12-13 | 2023-12-26 | MTC |  |  | DNTFCMS6YND3
Obligated | BRLS | 5927(139) | Marin County | 2024-02-06 | 2024-02-09 | 2024-03-07 | 2024-03-07 | 2024-03-11 | 400000 | 0 | 500000 | Authorized | 5927 | 04 | E-76 approved on | NA | 9 | 27 | 4 | VAR170012 | Lucas Valley Road Over Miller Creek. Br No 27c0016 | Replace Exisiting Scour Critical Bridge With Longer 3-span Structure With | 1 | 2024-01-31 | 2024-01-31 | MTC |  |  | DNTFCMS6YND3
Obligated | STPL | 5042(061) | Napa | 2024-02-27 | 2024-02-27 | 2024-02-27 | 2024-02-27 | 2024-03-01 | -0.01 | 0 | -411245.37 | Authorized | 5042 | 04 | E-76 approved on | NA | 5 | 0 | 3 | NAP170007 | West Side Of Soscol Avenue Between Vallejo Street And Third Street In | Multi-use Trail Construction | 2 | 2024-02-22 | 2024-02-23 | MTC |  |  | NC13XARFZ4K7
Obligated | STPL | 5309(019) | Los Altos | 2024-03-07 | 2024-03-07 | 2024-03-07 | 2024-03-07 | 2024-03-11 | 0 | 0 | 0 | Authorized | 5309 | 04 | E-76 approved on | NA | 7 | 0 | 4 | SCL170038 | Los Altos: Fremont Avenue Between Grant Rd And Stevens Creek (city Limit) | The City Of Los Altos Proposes To Rehabilitate The Roadway On Fremont Avenue | 2 | 2024-02-29 | 2024-03-01 | MTC
Obligated | STPLNI | 6084(263) | Metropolitan Transportation Commission | 2024-02-24 | 2024-02-24 | 2024-02-26 | 2024-02-26 | 2024-02-27 | 0 | 0 | 0 | Authorized | 6084 | 04 | E-76 approved on | NA | 10 | 2 | 1 | VAR190003 | I-80: In Alameda And Contra Costa Counties | Conduct Studies To Identify A Range Of Innovative Near To Mid-term | 2 | 2024-02-14 | 2024-02-25 | MTC |  |  | UKDZHCRW3U97
Obligated | CML | 5137(055) | Richmond | 2024-01-25 | 2024-01-26 | 2024-02-13 | 2024-02-14 | 2024-02-21 | 0 | 0 | 1200 | Authorized | 5137 | 04 | E-76 approved on | NA | 2 | 19 | 7 | CC170056 | In Richmond, Vicinity Of Lincoln Elementary School | The City Of Richmond Proposes Pedestrian Enhancements At Chanslor Avenue And | 2 | 2024-01-24 | 2024-01-25 | MTC |  |  | W856SVG77LP8
Obligated | ER | 15J7(108) | Marin County | 2024-02-07 | 2024-02-07 | 2024-02-07 | 2024-02-09 | 2024-02-12 | 45814 | -45814 | 0 | Authorized | 5927 | 04 | E-76 approved on | NA | 0 | 2 | 3 | NA | Paradise Pm 7.53daf Ltp Mrnco 003-0 Approved By Fhwa On 6/7/2023 | Northwestbound Lane At Paradise Drive Mp 7.53 In Tiburon - Slipout Along | 2 | 2024-02-07 | 2024-02-07 | MTC |  |  | DNTFCMS6YND3
Obligated | ER | 15J7(173) | Contra Costa County | 2024-03-06 | 2024-03-06 | 2024-03-06 | 2024-03-12 | 2024-03-19 | 31516.68 | -31516.68 | 0 | Authorized | 5928 | 04 | E-76 approved on | NA | 0 | 6 | 7 | NA | Highland Road, Livermore, Ca. | Contractor To Regrade And Hydroseed Approximatey 300 Sq.ft Of Eroded Area To | 2 | 2024-03-06 | 2024-03-06 | MTC |  |  | KFYDUB91ZNB8
Obligated | ACSTP | 15J9(164) | Contra Costa County | 2024-03-12 | 2024-03-12 | 2024-03-13 | 2024-03-19 | 2024-03-22 | -380679 | 380679 | 0 | Authorized | 5928 | 04 | E-76 approved on | NA | 0 | 7 | 3 | NA | Alhambra Valley Road -site 2- 1.3 Miles East Of Castro Ranch Road To 1.32 | Install Soldier Pile Retaining Wall With Structural Backfill And Guardrail | 2 | 2024-03-12 | 2024-03-12 | MTC |  |  | KFYDUB91ZNB8
Obligated | ER | 15J7(179) | San Leandro | 2024-02-08 | 2024-02-08 | 2024-02-08 | 2024-02-09 | 2024-02-12 | 146798 | -146798 | 0 | Authorized | 5041 | 04 | E-76 approved on | NA | 0 | 1 | 3 | NA | Lake Chabot Road | Site A: Construct Approximately 78 Linear Feet Of Retaining Wall, Replace | 2 | 2024-02-08 | 2024-02-08 | MTC |  |  | L3M8MGX1E6L3
Obligated | ACST-ER | 15J7(187) | Contra Costa County | 2024-03-06 | 2024-03-06 | 2024-03-06 | 2024-03-19 | 2024-03-25 | 17800 | -17800 | 0 | Authorized | 5928 | 04 | E-76 approved on | NA | 0 | 13 | 6 | NA | Port Chicago Highway, Contra Costa County. | Contractor To Replace The Existing Cmp Storm Drain With An Rcp Or Hdpe Pipe | 2 | 2024-03-06 | 2024-03-06 | MTC |  |  | KFYDUB91ZNB8
Obligated | ATPL | 5132(047) | Fairfield | 2024-03-06 | 2024-03-06 | 2024-03-18 | 2024-03-22 | 2024-03-27 | -213985.34 | 0 | -138000 | Authorized | 5132 | 04 | E-76 approved on | NA | 6 | 16 | 5 | SOL170006 | East Tabor Ave. From Railroad Tracks To Olive Ave., And On Tolenas Road From | Install Sidewalk And Widen Existing Sidewalks; Including Curb And Gutter, | 3 | 2024-02-29 | 2024-03-05 | MTC |  |  | RKK3CJAGJ3G4
Obligated | BPMP | 5920(163) | Sonoma County | 2023-03-30 | 2024-01-22 | 2024-01-25 | 2024-01-29 | 2024-02-02 | 1321363 | 0 | 1515013.83 | Authorized | 5920 | 04 | E-76 approved on | NA | 41 | 7 | 4 | VAR170012 | 24 Various Locations Within Sonoma County | Bridge Preventive Maintenance Program | 3 | 2023-12-12 | 2024-01-18 | MTC |  |  | NPTPYM3QJGA1
Obligated | STPCML | 5012(155) | Oakland | 2024-01-17 | 2024-01-17 | 2024-01-30 | 2024-02-01 | 2024-02-28 | 4392000 | 0 | 5034174.5 | Authorized | 5012 | 04 | E-76 approved on | NA | 8 | 15 | 27 | ALA170063 | In Oakland: On Harrison Street From 20th Street To 27th Street, Grand Avenue | Install Cycle Track, Parking Protect Bikeways And Intersections, Road Diet | 3 | 2024-01-09 | 2024-01-17 | MTC |  |  | KWMRND8WK7A5
Obligated | STPCML | 5050(046) | Hayward | 2023-11-17 | 2024-01-17 | 2024-01-31 | 2024-02-07 | 2024-02-12 | 1827818 | 0 | 3758605 | Authorized | 5050 | 04 | E-76 approved on | NA | 68 | 21 | 5 | ALA170065 | Main Street From Mckeever Avenue To D Street | Reduce Roadway From 4 To 3 Lanes, Construct Bike Lanes, Widen Sidewalks And | 3 | 2023-11-10 | 2023-11-17 | MTC |  |  | J7X4BD1ZTAJ7
Obligated | STPL | 6406(022) | Transportation Authority of Marin | 2024-01-23 | 2024-01-23 | 2024-02-12 | 2024-02-15 | 2024-02-27 | 0 | 0 | 0 | Authorized | 6406 | 04 | E-76 approved on | NA | -15 | 23 | 12 | MRN050034 | Route 101 In Novato From 0.5 Miles North Of Atherton Ave. Overcrossing To | Phase 2: Bridge Widening And Replacement, Interchange Modifications, | 3 | 2024-02-07 | 2024-02-12 | MTC |  |  | NSV1HF4Y5238
Obligated | STPLNI | 6084(244) | Metropolitan Transportation Commission | 2024-01-19 | 2024-01-19 | 2024-02-05 | 2024-02-13 | 2024-02-21 | -976000 | 0 | -976000 | Authorized | 6084 | 04 | E-76 approved on | NA | 1 | 25 | 8 | REG170018 | Sf Bay Area: Regionwide | Mtc Implementation Of The Connected And Automated Vehicle (c/av) Program. | 3 | 2024-01-18 | 2024-01-19 | MTC |  |  | UKDZHCRW3U97
Obligated | FERPL18 | 6264(087) | Santa Clara Valley Transportation Authority | 2024-02-04 | 2024-02-04 | 2024-02-06 | 2024-02-06 | 2024-02-12 | 0 | 0 | 0 | Authorized | 6264 | 04 | E-76 approved on | NA | 19 | 2 | 6 | SCL110002 | In Santa Clara County: Us 101 From I-880 In San Jose To Sr-237 In Sunnyvale | Convert Existing Carpool Lanes To Express Lanes (phase 5) | 3 | 2024-01-16 | 2024-02-06 | MTC |  |  | EAZVJZNJBS22
Obligated | HSIPL | 5003(032) | Benicia | 2024-02-07 | 2024-03-13 | 2024-03-14 | 2024-03-20 | 2024-03-27 | 0 | 0 | 0 | Authorized | 5003 | 04 | E-76 approved on | NA | 36 | 7 | 7 | VAR170002 | 21 Locations In City Of Benicia | Upgrade Existing Guardrails And End Treatments. | 3 | 2024-02-06 | 2024-02-06 | MTC |  |  | PDLHBKLS8A77
Obligated | HSIPL | 5022(062) | Petaluma | 2024-02-28 | 2024-02-28 | 2024-02-29 | 2024-02-29 | 2024-03-07 | -9605.64 | 0 | -8930 | Authorized | 5022 | 04 | E-76 approved on | NA | 6 | 1 | 7 | VAR170002 | Various Intersections Throughout The City Of Petaluma | Install Rectangular Rapid Flashing Beacons (rrfbs) At Various Uncontrolled | 3 | 2024-02-22 | 2024-02-23 | MTC |  |  | FFKALDR94J63
Obligated | HSIPL | 5003(033) | Benicia | 2024-02-14 | 2024-03-18 | 2024-03-19 | 2024-03-20 | 2024-03-27 | 0 | 0 | 46199.56 | Authorized | 5003 | 04 | E-76 approved on | NA | 35 | 2 | 7 | VAR170002 | The Intersections Of Military West And West 5th St. And Hastings Dr. And | Pedestrian Crossing Improvements, Including: Ada Ramps Rrfb System, Median | 3 | 2024-02-12 | 2024-02-13 | MTC |  |  | PDLHBKLS8A77
Obligated | HSIPL | 5041(049) | San Leandro | 2024-01-30 | 2024-01-30 | 2024-02-04 | 2024-02-04 | 2024-02-05 | 0 | 0 | 0 | Authorized | 5041 | 04 | E-76 approved on | NA | -1 | 5 | 1 | VAR170002 | The Intersection Of Wicks Blvd And Manor Blvd. | Install Southbound And Northbound Left-turn Signals; Upgrade Signal Heads | 3 | 2024-01-31 | 2024-02-04 | MTC |  |  | L3M8MGX1E6L3
Obligated | HSIPL | 5030(066) | Vallejo | 2024-03-15 | 2024-03-15 | 2024-03-15 | 2024-03-15 | 2024-03-19 | 0 | 0 | 333020.44 | Authorized | 5030 | 04 | E-76 approved on | NA | 8 | 0 | 4 | VAR170002 | Intersections Of: Foothill Dr. And Redwood Parkway, Valle Vista Ave. And | Construct Pedestrian Crossing Enhancements Such As Advanced Pedestrian | 3 | 2024-03-07 | 2024-03-08 | MTC |  |  | KJKSES96KUN9
Obligated | STPL | 5920(166) | Sonoma County | 2024-03-07 | 2024-03-07 | 2024-03-07 | 2024-03-07 | 2024-03-11 | 0 | 0 | 0 | Authorized | 5920 | 04 | E-76 approved on | NA | 7 | 0 | 4 | SON170013 | Corby Ave Between Hearn Ave And Santa Rosa City Limits, Dutton Ave Between | Pavement Rehabilitation | 3 | 2024-02-29 | 2024-03-01 | MTC |  |  | NPTPYM3QJGA1
Obligated | STPL | 5920(167) | Sonoma County | 2024-02-08 | 2024-02-08 | 2024-02-08 | 2024-02-08 | 2024-02-12 | 0 | 0 | 0 | Authorized | 5920 | 04 | E-76 approved on | NA | 7 | 0 | 4 | SON170010 | River Road From Trenton-healdsburg Road To Just West Of Smart Train Right Of | Rehabilitation Of Pavement And Striping For Bike Lanes. | 3 | 2024-02-01 | 2024-02-02 | MTC |  |  | NPTPYM3QJGA1
Obligated | HSIPL | 5032(033) | Suisun City | 2023-12-28 | 2024-01-29 | 2024-01-29 | 2024-02-01 | 2024-02-28 | 0 | 0 | 25318.22 | Authorized | 5032 | 04 | E-76 approved on | NA | 33 | 3 | 27 | VAR170002 | Three Locations: 1) Merganser Drive Between Sunset Avenue And Wigeon Way; 2) | Enhanced Pedestrian Crossings By The Addition Of Ada Curb Ramps, Rrfb | 3 | 2023-12-27 | 2024-01-10 | MTC |  |  | LEPDWR1WVT91
Obligated | STPL | 5137(052) | Richmond | 2024-02-28 | 2024-02-28 | 2024-02-28 | 2024-02-28 | 2024-03-01 | -100430.43 | 0 | -665791.6 | Authorized | 5137 | 04 | E-76 approved on | NA | 6 | 0 | 2 | CC-170057 | City Of Richmond: On Castro Rd (olinda Drive To The City Limit 400 Feet | Pavement Rehabilitation And Ada Improvement | 3 | 2024-02-22 | 2024-02-23 | MTC |  |  | W856SVG77LP8
Obligated | STPL | 5309(019) | Los Altos | 2024-03-12 | 2024-03-12 | 2024-03-12 | 2024-03-12 | 2024-03-19 | -0.01 | 0 | -413377.75 | Authorized | 5309 | 04 | E-76 approved on | NA | 5 | 0 | 7 | SCL170038 | Los Altos: Fremont Avenue Between Grant Rd And Stevens Creek (city Limit) | The City Of Los Altos Proposes To Rehabilitate The Roadway On Fremont Avenue | 3 | 2024-03-07 | 2024-03-08 | MTC
Obligated | ER | 15J1(004) | Marin County | 2024-02-06 | 2024-02-06 | 2024-02-06 | 2024-02-09 | 2024-02-12 | 42574 | -42574 | 0 | Authorized | 5927 | 04 | E-76 approved on | NA | 0 | 3 | 3 | NA | Sir Francis Drake Blvd At Mp 20.28 | Install Approx. 11 Ft High Conc Ret. Wall With Drilled Piers For Appro. 50 | 3 | 2024-02-06 | 2024-02-06 | MTC |  |  | DNTFCMS6YND3
Obligated | ER | 15J7(026) | Marin County | 2024-02-07 | 2024-02-07 | 2024-02-07 | 2024-02-09 | 2024-02-12 | 47942.88 | -47942.88 | 0 | Authorized | 5927 | 04 | E-76 approved on | NA | 0 | 2 | 3 | NA | Ca 23-1daf Ltp Mrnco 002-0 Approved By Fhwa Ltp By 3-23-2023site A -. Sb | Site A - Construct Appr 70' Rw, Repair Ext Gr And Prepare Rdwy | 3 | 2024-02-07 | 2024-02-07 | MTC |  |  | DNTFCMS6YND3
Obligated | ER | 15J7(102) | Marin County | 2024-02-07 | 2024-02-07 | 2024-02-07 | 2024-02-09 | 2024-02-12 | 239467 | -239467 | 0 | Authorized | 5927 | 04 | E-76 approved on | NA | 0 | 2 | 3 | NA | Fairfax Bolinas Rd Mp 1.34m (see Daf No Ltp Mrnco - 001-0) (ltp Approved 5- | Construction Of 230 Lf Retaining Wall To Support The Eb Lane Of Fairfax | 3 | 2024-02-07 | 2024-02-07 | MTC |  |  | DNTFCMS6YND3
Obligated | STPL | 5934(171) | San Francisco County | 2023-10-25 | 2023-10-25 | 2023-10-25 | 2024-03-15 | 2024-03-19 | -801.36 | 0 | 11598560.01 | Authorized | 5934 | 04 | E-76 approved on | NA | -134 | 142 | 4 | SF-130011 | 2nd Street From Market To King | Bicycle & Ped Improvements, Repave | 4 | 2024-03-07 | 2024-03-08 | MTC |  |  | CK7BAVKBDW28
Obligated | ATPL | 5196(040) | Daly City | 2024-03-14 | 2024-03-14 | 2024-03-14 | 2024-03-14 | 2024-03-19 | 0 | 0 | -41679.53 | Authorized | 5196 | 04 | E-76 approved on | NA | 7 | 0 | 5 | SM-150012 | On Junipero Serra Blvd, Eastmoor Ave, San Pablo Rd, E Market St, Guadalupe | Install Bicycle And Pedestrian Enhancements (tc) | 4 | 2024-03-07 | 2024-03-08 | MTC |  | negatie or zero funding | KS8RFKRF6ZE6
Obligated | HSIPL | 5127(034) | Pittsburg | 2024-02-12 | 2024-02-12 | 2024-02-12 | 2024-02-12 | 2024-02-21 | 0 | 0 | 0 | Authorized | 5127 | 04 | E-76 approved on | NA | 4 | 0 | 9 | VAR170002 | 3 Intersections Of Stoneman Avenue (at Meadowbrook Avenue, Meadowb,rook | Install Pedestrian Hawk Signals, Intersection Striping/signage Improvements, | 4 | 2024-02-08 | 2024-02-09 | MTC |  |  | DS5LP1EQ6Z95
Obligated | STPL | 6084(227) | Metropolitan Transportation Commission | 2024-02-24 | 2024-02-24 | 2024-02-25 | 2024-02-26 | 2024-02-27 | 0 | 0 | 0 | Authorized | 6084 | 04 | E-76 approved on | NA | 12 | 2 | 1 | REG170015 | Sf Bay Area | Sf Bay Area Regionwide: Deploy Advanced Technologies Along Arterial To | 4 | 2024-02-12 | 2024-02-25 | MTC |  |  | UKDZHCRW3U97
Obligated | CML | 5005(156) | San Jose | 2024-01-19 | 2024-01-19 | 2024-02-06 | 2024-02-07 | 2024-02-12 | 0 | 0 | -73718.38 | Authorized | 5005 | 04 | E-76 approved on | NA | 39 | 19 | 5 | SCL170031 | In San Jose: Various Locations In The Mount Pleasant Area. | Implement Traffic Safety Improvements To Serve Student Populations Of Seven | 4 | 2023-12-11 | 2024-01-11 | MTC |  |  | QUA4AULJ8FM3
Obligated | CML | 5127(036) | Pittsburg | 2023-12-18 | 2024-01-25 | 2024-01-31 | 2024-01-31 | 2024-02-05 | 0 | 0 | 359113 | Authorized | 5127 | 04 | E-76 approved on | NA | 45 | 6 | 5 | CC-170040 | In Pittsburg: On California Avenue, Bliss Avenue And Railroad Avenue In The | Construct Class I And Iv Bikeways And Associated Improvements. | 4 | 2023-12-11 | 2023-12-18 | MTC |  |  | DS5LP1EQ6Z95
Obligated | STPL | 5920(166) | Sonoma County | 2024-03-12 | 2024-03-12 | 2024-03-12 | 2024-03-12 | 2024-03-19 | 0 | 0 | 0 | Authorized | 5920 | 04 | E-76 approved on | NA | 5 | 0 | 7 | SON170013 | Corby Ave Between Hearn Ave And Santa Rosa City Limits, Dutton Ave Between | Pavement Rehabilitation | 4 | 2024-03-07 | 2024-03-08 | MTC |  |  | NPTPYM3QJGA1
Obligated | STPL | 5920(167) | Sonoma County | 2024-02-13 | 2024-02-13 | 2024-02-13 | 2024-02-13 | 2024-02-21 | 0 | 0 | 0 | Authorized | 5920 | 04 | E-76 approved on | NA | 5 | 0 | 8 | SON170010 | River Road From Trenton-healdsburg Road To Just West Of Smart Train Right Of | Rehabilitation Of Pavement And Striping For Bike Lanes. | 4 | 2024-02-08 | 2024-02-09 | MTC |  |  | NPTPYM3QJGA1
Obligated | CML | 5012(087) | Oakland | 2024-02-27 | 2024-02-27 | 2024-02-27 | 2024-02-27 | 2024-03-01 | 0 | 0 | -400966.22 | Authorized | 5012 | 04 | E-76 approved on | NA | 5 | 0 | 3 | ALA070011 | 66th Ave.from San Leandro To Internation Blvd | Streetscape | 4 | 2024-02-22 | 2024-02-23 | MTC |  |  | KWMRND8WK7A5
Obligated | HSIPL | 5127(034) | Pittsburg | 2024-02-22 | 2024-02-22 | 2024-02-22 | 2024-02-22 | 2024-02-27 | -0.03 | 0 | 4183.07 | Authorized | 5127 | 04 | E-76 approved on | NA | 7 | 0 | 5 | VAR170002 | 3 Intersections Of Stoneman Avenue (at Meadowbrook Avenue, Meadowb,rook | Install Pedestrian Hawk Signals, Intersection Striping/signage Improvements, | 5 | 2024-02-15 | 2024-02-16 | MTC |  |  | DS5LP1EQ6Z95
Obligated | LPPSTPL | 5472(021) | Windsor | 2023-11-22 | 2024-01-18 | 2024-02-02 | 2024-02-05 | 2024-02-12 | 0 | 0 | -107606.66 | Authorized | 5472 | 04 | E-76 approved on | NA | 91 | 18 | 7 | SON170001 | Intersection Of Windsor River Road And Windsor Road And Vicinity, Within The | The Windsor River Road/windsor Road Intersection Improvements And Multi-use | 5 | 2023-10-19 | 2023-12-05 | MTC |  |  | J44UK7CAJBQ3
Obligated | ER | 40A0(088) | Marin County | 2024-02-08 | 2024-02-08 | 2024-02-08 | 2024-02-09 | 2024-02-12 | 701670.76 | -701670.76 | 0 | Authorized | 5927 | 04 | E-76 approved on | NA | 0 | 1 | 3 | NA | Lucas Valley Road At Mp 9.60 | Per Approval Dafs "build +/- 100 Linear Feet Of Cidh Retaining Wall With +/- | 5 | 2024-02-08 | 2024-02-08 | MTC |  |  | DNTFCMS6YND3
Obligated | ER | 40A0(090) | Marin County | 2024-02-08 | 2024-02-08 | 2024-02-08 | 2024-02-12 | 2024-02-21 | 1469136.75 | -1469136.75 | 0 | Authorized | 5927 | 04 | E-76 approved on | NA | 0 | 4 | 9 | NA | Sir Francis Drake Blvd At Pm 20.97 | Site 1; Heavy Rain & Saturate Soil Caused Embankment To Slip, Exposing The | 5 | 2024-02-08 | 2024-02-08 | MTC |  |  | DNTFCMS6YND3
Obligated | ACST-ER | 40A0(091) | Marin County | 2023-12-29 | 2024-01-26 | 2024-02-20 | 2024-02-21 | 2024-02-27 | 0 | 60420 | 68250 | Authorized | 5927 | 04 | E-76 approved on | NA | 39 | 26 | 6 | NA | Marshall-pentaluma Rd At Mp 8.24 (see Daf Lpt Mrnco 006-0 , Ca 19-2, | Propose Work Is To Reinforce The Void Spaces With Rebar And Concrete | 5 | 2023-12-18 | 2024-01-02 | MTC |  |  | DNTFCMS6YND3
Obligated | ACST-ER | 40A0(103) | Sonoma County | 2024-02-06 | 2024-02-06 | 2024-02-06 | 2024-02-06 | 2024-02-13 | 2291382.86 | -2291382.86 | 0 | Authorized | 5020 | 04 | E-76 approved on | NA | 0 | 0 | 7 | NA | Stewarts Point/skaggs Springs Road | Remove And Replace Damaged Roadway. Install French Drainage. Drain To Extend | 5 | 2024-02-06 | 2024-02-06 | MTC |  |  | NW6EWPZR1516
Obligated | ER | 40A0(102) | Sonoma County | 2024-02-13 | 2024-02-13 | 2024-02-13 | 2024-02-13 | 2024-02-21 | 0 | 0 | 0 | Authorized | 5020 | 04 | E-76 approved on | NA | 0 | 0 | 8 | NA | Stewarts Points/skaggs Springs | Landslide 500 Ft L * 40ft W * 800 Ft (slope Length) Near Wheatfield Fork Of | 5 | 2024-02-13 | 2024-02-13 | MTC |  |  | NW6EWPZR1516
Obligated | ACST-ER | 40A0(104) | Sonoma County | 2024-02-13 | 2024-02-13 | 2024-02-13 | 2024-02-13 | 2024-02-21 | 0 | 0 | 0 | Authorized | 5020 | 04 | E-76 approved on | NA | 0 | 0 | 8 | NA | There Are 2 Locations : Stewarts Point/skaggs Springs Road Pm 13.61 And | Restoration. | 5 | 2024-02-13 | 2024-02-13 | MTC |  |  | NW6EWPZR1516
Obligated | BPMP | 5101(029) | Pleasanton | 2024-02-21 | 2024-02-21 | 2024-02-21 | 2024-02-21 | 2024-02-27 | 0 | 0 | 0 | Authorized | 5101 | 04 | E-76 approved on | NA | 6 | 0 | 6 | VAR170012 | City Of Pleasanton: 5 Bridges, 33c0454, 33c0099, 33c0453, 33c0461, And | Bridge Preventive Maintenance Project | 6 | 2024-02-15 | 2024-02-16 | MTC |  |  | ZQLCND5KBU99
Obligated | BRLS | 6272(047) | San Francisco County Transportation Authority | 2024-03-06 | 2024-03-06 | 2024-03-06 | 2024-03-06 | 2024-03-11 | 0 | 0 | 0 | Authorized | 6272 | 04 | E-76 approved on | NA | 0 | 0 | 5 | SF-070027 | On Yerba Buena Island, San Francisco - I-80 On And Off Ramps | Approach Roadway Realignments | 6 | 2024-03-06 | 2024-03-06 | MTC |  |  | UX7LNHY4BRD1
Obligated | STPLZ | 5444(018) | Orinda | 2024-01-18 | 2024-02-15 | 2024-03-07 | 2024-03-08 | 2024-03-11 | 113470 | 0 | 89129 | Authorized | 5444 | 04 | E-76 approved on | NA | 35 | 22 | 3 | VAR170012 | Bridge No. 28c0331, Bear Creek Rd, Over San Pablo Creek, 0.2 Mi East Of | Seismic Retrofit | 6 | 2024-01-11 | 2024-01-18 | MTC |  |  | YUPDYZZ1N4Y1
Obligated | STPLZ | 5444(019) | Orinda | 2024-02-01 | 2024-02-22 | 2024-03-01 | 2024-03-05 | 2024-03-07 | 173735 | 0 | 284306 | Authorized | 5444 | 04 | E-76 approved on | NA | 28 | 12 | 2 | VAR170012 | Miner Road Bridge Over San Pablo Creek (br #28c0330) | Seismic Retrofit | 6 | 2024-01-25 | 2024-02-01 | MTC |  |  | YUPDYZZ1N4Y1
Obligated | ER | 40A0(103) | Sonoma County | 2024-03-13 | 2024-03-13 | 2024-03-13 | 2024-03-19 | 2024-03-22 | 29998.14 | -29998.14 | 0 | Authorized | 5020 | 04 | E-76 approved on | NA | 0 | 6 | 3 | NA | Stewarts Point/skaggs Springs Road | Remove And Replace Damaged Roadway. Install French Drainage. Drain To Extend | 6 | 2024-03-13 | 2024-03-13 | MTC |  |  | NW6EWPZR1516
Obligated | ACST-ER | 40A0(104) | Sonoma County | 2024-03-13 | 2024-03-13 | 2024-03-13 | 2024-03-19 | 2024-03-22 | 719663.37 | -719663.37 | -1.1642e-10 | Authorized | 5020 | 04 | E-76 approved on | NA | 0 | 6 | 3 | NA | There Are 2 Locations : Stewarts Point/skaggs Springs Road Pm 13.61 And | Restoration. | 6 | 2024-03-13 | 2024-03-13 | MTC |  |  | NW6EWPZR1516
Obligated | STPLZ | 5920(111) | Sonoma County | 2024-02-16 | 2024-03-12 | 2024-03-18 | 2024-03-20 | 2024-03-27 | 5527036 | -5527036 | 0 | Authorized | 5920 | 04 | E-76 approved on | NA | 32 | 8 | 7 | VAR170012 | Geyser Road Over Sulphur Creek | Bridge Relpacement (tc) | 6 | 2024-02-09 | 2024-02-16 | MTC |  |  | NPTPYM3QJGA1
Obligated | BRLS | 5928(125) | Contra Costa County | 2024-03-05 | 2024-03-05 | 2024-03-05 | 2024-03-05 | 2024-03-11 | 0 | 0 | 0 | Authorized | 5928 | 04 | E-76 approved on | NA | 0 | 0 | 6 | VAR170012 | Two Bridges (28c-0143 And 28c-0145) On Marsh Creek Road Over Marsh Creek. | Replace Two Structurally Deficient Bridges With New Bridges Built To Current | 7 | 2024-03-05 | 2024-03-05 | MTC |  |  | KFYDUB91ZNB8
Obligated | HPLUL | 5438(011) | East Palo Alto | 2024-03-06 | 2024-03-06 | 2024-03-06 | 2024-03-06 | 2024-03-11 | -668185.42 | 0 | 3186683.83 | Authorized | 5438 | 04 | E-76 approved on | NA | 6 | 0 | 5 | SM-070004 | Bay Road: Clarke/illinois To Cooley Landing (bay Trail) | Road Widen, Resurface, Streetscape, Bike Lane | 8 | 2024-02-29 | 2024-03-01 | MTC |  |  | D5C3FMM23Y75
Obligated | BRLS | 5094(066) | Vacaville | 2024-02-12 | 2024-02-12 | 2024-02-12 | 2024-02-12 | 2024-02-21 | -632670.11 | 0 | -588324.85 | Authorized | 5094 | 04 | E-76 approved on | NA | 4 | 0 | 9 | VAR170012 | Buck Avenue Over Alamo Creekbr No. 23c0011 | Bridge Replacement | 9 | 2024-02-08 | 2024-02-09 | MTC |  |  | L5JNKWMDFNB8
Obligated | STPLZ | 5012(037) | Oakland | 2024-03-17 | 2024-03-17 | 2024-03-17 | 2024-03-17 | 2024-03-20 | 0 | 0 | 0 | Authorized | 5012 | 04 | E-76 approved on | NA | 11 | 0 | 3 | VAR110045 | Lake Merritt Channel Bridge (br.no.33c-0030) | Replace Bridge (per Seismic Strategy) | 12 | 2024-03-06 | 2024-03-17 | MTC |  |  | KWMRND8WK7A5
Obligated | STPLZ | 5920(059) | Sonoma County | 2024-02-15 | 2024-02-15 | 2024-02-15 | 2024-02-15 | 2024-02-27 | -13103.96 | 0 | 577504.24 | Authorized | 5920 | 04 | E-76 approved on | NA | 7 | 0 | 12 | VAR170012 | Sonoma Creek Br. @ Boyes Blvd (br.20c-0262) . | Bridge Replacement | 14 | 2024-02-08 | 2024-02-09 | MTC |  |  | NPTPYM3QJGA1
Obligated | HSIPL | 5949(187) | San Luis Obispo County | 2024-02-08 | 2024-02-21 | 2024-02-23 | 2024-02-29 | 2024-03-04 | 649505 | 0 | 649505 | Authorized | 5949 | 05 | E-76 approved on | NA | 13 | 8 | 4 | LOCALHSIP | Install Centerline Striping On Portions Of Adelaida Rd, Geneseo Rd, Oso | Centerline Striping & Rumble Strips | 1 | 2024-02-08 | 2024-02-13 | SLOCOG |  |  | M9MVG9PJJ5J3
Obligated | ACSTP | 15J7(072) | Santa Cruz County | 2023-07-11 | 2024-01-29 | 2024-01-31 | 2024-02-06 | 2024-02-13 | 0 | 55000 | 55000 | Authorized | 5936 | 05 | E-76 approved on | NA | 0 | 8 | 7 | NA | East Cliff Dr Pm 0.22 In Santa Cruz County | Emergency Opening - Shoulder Repair - Traffic Control, Warning Signs, | 1 | 2024-01-29 | 2024-01-29 | AMBAG |  |  | DQHKDRT8LVY8
Obligated | ACSTP | 15J7(144) | Santa Cruz County | 2023-10-24 | 2024-02-12 | 2024-02-20 | 2024-02-23 | 2024-02-27 | 0 | 895213 | 916670 | Authorized | 5936 | 05 | E-76 approved on | NA | 111 | 11 | 4 | NA | China Grade Pm 0.62 In Santa Cruz County | Emergency Opening And Permanent Restoration - Eo Work - Install Temporary | 1 | 2023-10-24 | 2024-02-12 | AMBAG |  |  | DQHKDRT8LVY8
Obligated | ACSTP | 15J7(145) | Santa Cruz County | 2023-08-05 | 2024-01-29 | 2024-01-31 | 2024-02-06 | 2024-02-13 | 0 | 94650 | 94650 | Authorized | 5936 | 05 | E-76 approved on | NA | 177 | 8 | 7 | NA | Valencia Rd Pm 0.33 In Santa Cruz County | Emergency Opening - Slipout Repair - Traffic Control, Clear And Grub, Extend | 1 | 2023-08-05 | 2024-01-29 | AMBAG |  |  | DQHKDRT8LVY8
Obligated | ACSTP | 15J7(154) | San Benito County | 2023-11-15 | 2024-01-22 | 2024-01-31 | 2024-03-20 | 2024-03-26 | 0 | 427300 | 427300 | Authorized | 5943 | 05 | E-76 approved on | NA | 69 | 58 | 6 | NA | Salinas Rd Pm 0.90 To 0.95 In San Benito County | Emergency Opening - Repair Slipout - Stabilize Embankment With Soil Nails | 1 | 2023-11-14 | 2024-01-22 | AMBAG |  |  | UX1PHLRE4QQ3
Obligated | ACSTP | 15J9(067) | Santa Cruz County | 2024-01-09 | 2024-02-26 | 2024-02-27 | 2024-03-19 | 2024-03-21 | 0 | 859925 | 859925 | Authorized | 5936 | 05 | E-76 approved on | NA | 48 | 22 | 2 | NA | Upper East Zayante Pm 1.18 In Santa Cruz County | Emergency Opening - Repair Slipout - Engineered Plans, Structure Excavation | 1 | 2024-01-09 | 2024-02-26 | AMBAG |  |  | DQHKDRT8LVY8
Obligated | ACSTP | 15J9(070) | Santa Cruz County | 2023-10-04 | 2024-02-26 | 2024-02-27 | 2024-03-19 | 2024-03-21 | 0 | 580250 | 580250 | Authorized | 5936 | 05 | E-76 approved on | NA | 145 | 22 | 2 | NA | Jamison Creek Rd Pm 1.09 In Santa Cruz County | Emergency Opening - Repair Slipout - Prepared Plans, Structure Excavation | 1 | 2023-10-04 | 2024-02-26 | AMBAG |  |  | DQHKDRT8LVY8
Obligated | ACSTP | 15J9(143) | San Benito County | 2023-12-01 | 2024-01-22 | 2024-01-23 | 2024-01-29 | 2024-02-01 | 0 | 153000 | 153000 | Authorized | 5943 | 05 | E-76 approved on | NA | 52 | 7 | 3 | NA | San Juan Canyon Rd Pm 3.10 In San Benito County | Emergency Opening - Repair Slipout - Reconstruct Roadway And Shoulder, Grade | 1 | 2023-12-01 | 2024-01-22 | AMBAG |  |  | UX1PHLRE4QQ3
Obligated | ACSTP | 15J7(199) | Department of Parks and Recreation | 2024-02-21 | 2024-02-21 | 2024-02-27 | 2024-03-19 | 2024-03-21 | 0 | 582426 | 582426 | Authorized | 6081 | 05 | E-76 approved on | NA | 0 | 27 | 2 | NA | Pecho Valley Rd | Geotechnical Investigation, Survey, Engineering Design & Traffic Control. | 1 | 2024-02-21 | 2024-02-21 | NON-MPO |  |  | VY39GJE3DQG1
Obligated | BRLO | 5936(132) | Santa Cruz County | 2024-01-04 | 2024-01-22 | 2024-01-24 | 2024-02-05 | 2024-02-07 | 150000 | 0 | 150000 | Authorized | 5936 | 05 | E-76 approved on | NA | 5 | 14 | 2 | GP HBRR | In The County Of Santa Cruz On Swanton Road At Big Creek 36c-0018 | Bridge Replacement(tc) | 2 | 2024-01-17 | 2024-01-17 | AMBAG |  |  | DQHKDRT8LVY8
Obligated | HSIPL | 5951(170) | Santa Barbara County | 2024-03-07 | 2024-03-07 | 2024-03-07 | 2024-03-07 | 2024-03-11 | 0 | 0 | 0 | Authorized | 5951 | 05 | E-76 approved on | NA | 0 | 0 | 4 | LOCALHSIP | Various Locations In The Unincorporated Area Of Santa Barbara County. | Installing Large Directional Arrow Signs And Object Markers On Top Of | 2 | 2024-03-07 | 2024-03-07 | SBCAG |  |  | Z4A8L588L9G5
Obligated | ER | 15J2(001) | Santa Cruz County | 2024-02-12 | 2024-02-12 | 2024-02-12 | 2024-02-13 | 2024-02-21 | 54397 | -54397 | 0 | Authorized | 5936 | 05 | E-76 approved on | NA | 0 | 1 | 8 | NA | Eureka Canyon Pm 8.11; Emergency Repairs (a.k.a. Eo): Placed Temporary | Heavy Rains Caused Water To Flow Over The Edge Of Roadway And Shoulder, | 2 | 2024-02-12 | 2024-02-12 | AMBAG |  |  | DQHKDRT8LVY8
Obligated | ER | 15J2(004) | Santa Cruz County | 2024-02-12 | 2024-02-12 | 2024-02-12 | 2024-02-13 | 2024-02-21 | 87198 | -87198 | 0 | Authorized | 5936 | 05 | E-76 approved on | NA | 0 | 1 | 8 | NA | Soquel San Jose Road Pm 5.55; Emergency Repairs (a.k.a. Eo): Placed | Due To High Winds A Large Oak Tree Tree Has Fallen And Uprooted, Causing The | 2 | 2024-02-12 | 2024-02-12 | AMBAG |  |  | DQHKDRT8LVY8
Obligated | ACST-ER | 15J2(005) | Santa Cruz County | 2024-02-12 | 2024-02-12 | 2024-02-12 | 2024-02-13 | 2024-02-21 | 76915 | -76915 | 0 | Authorized | 5936 | 05 | E-76 approved on | NA | 0 | 1 | 8 | NA | Highland Way Pm 5.60 | Repair Slipout | 2 | 2024-02-12 | 2024-02-12 | AMBAG |  |  | DQHKDRT8LVY8
Obligated | ER | 15J7(010) | Santa Cruz County | 2024-02-05 | 2024-02-05 | 2024-02-05 | 2024-02-06 | 2024-02-13 | 527122 | -527122 | 0 | Authorized | 5936 | 05 | E-76 approved on | NA | 0 | 1 | 7 | NA | East Zayante Rd Pm 4.48 In Santa Cruz County | Emergency Opening - Geotech Inv, Plans, Structure Ex And Backfill, Steel | 2 | 2024-02-05 | 2024-02-05 | AMBAG |  |  | DQHKDRT8LVY8
Obligated | ER | 15J7(015) | Santa Cruz County | 2024-02-05 | 2024-02-05 | 2024-02-05 | 2024-02-07 | 2024-02-15 | 775700 | -775700 | 0 | Authorized | 5936 | 05 | E-76 approved on | NA | 0 | 2 | 8 | NA | Felton Empire Rd Pm 0.57 In Santa Cruz County | Emergency Opening - Geotechnical Investigation, Structure Excavation And | 2 | 2024-02-05 | 2024-02-05 | AMBAG |  |  | DQHKDRT8LVY8
Obligated | CPFCDS | 5199(034) | Arroyo Grande | 2024-02-20 | 2024-02-20 | 2024-02-20 | 2024-02-20 | 2024-02-27 | 0 | 0 | -151048 | Authorized | 5199 | 05 | E-76 approved on | NA | 0 | 0 | 7 | 22300000961 | Arroyo Grande Swinging Pedestrian Bridge Rehabilitation Over Arroyo Grande | Rehab Pedestrian Bridge | 2 | 2024-02-20 | 2024-02-20 | SLOCOG |  |  | VKFHGF6PKWK7
Obligated | ER | 15J7(033) | San Luis Obispo County | 2024-02-05 | 2024-02-05 | 2024-02-05 | 2024-02-07 | 2024-02-13 | 284000 | -284000 | 0 | Authorized | 5949 | 05 | E-76 approved on | NA | 0 | 2 | 6 | NA | Huasna Rd Pm 9.336, 10.072, 10.201 In San Luis Obispo County | Emergency Opening | 2 | 2024-02-05 | 2024-02-05 | SLOCOG |  |  | M9MVG9PJJ5J3
Obligated | ER | 15J7(034) | San Luis Obispo County | 2024-02-05 | 2024-02-05 | 2024-02-05 | 2024-02-07 | 2024-02-13 | 67500 | -67500 | 0 | Authorized | 5949 | 05 | E-76 approved on | NA | 0 | 2 | 6 | NA | La Panza Rd Pm 0.309 In San Luis Obispo County | Emergency Opening - Reconstruct Roadway Embankment, Place Rsp Rock Slope | 2 | 2024-02-05 | 2024-02-05 | SLOCOG |  |  | M9MVG9PJJ5J3
Obligated | ER | 15J7(035) | San Luis Obispo County | 2024-02-05 | 2024-02-05 | 2024-02-05 | 2024-02-07 | 2024-02-13 | 60250 | -60250 | 0 | Authorized | 5949 | 05 | E-76 approved on | NA | 0 | 2 | 6 | NA | La Panza Rd Pm 1.614 & 4.782 In San Luis Obispo County | Emergency Opening - Re-compact Roadway Embankmenk, Place Rock Slope | 2 | 2024-02-05 | 2024-02-05 | SLOCOG |  |  | M9MVG9PJJ5J3
Obligated | ER | 15J7(037) | San Luis Obispo County | 2024-02-06 | 2024-02-06 | 2024-02-06 | 2024-02-09 | 2024-02-15 | 150500 | -150500 | 0 | Authorized | 5949 | 05 | E-76 approved on | NA | 0 | 3 | 6 | NA | Nacimiento Lake Dr Pm 0.039 & 10.724 In San Luis Obispo County | Emergency Opening - Rebuild Slope And Hydroseed. | 2 | 2024-02-06 | 2024-02-06 | SLOCOG |  |  | M9MVG9PJJ5J3
Obligated | ER | 15J7(038) | San Luis Obispo County | 2024-02-06 | 2024-02-06 | 2024-02-06 | 2024-02-09 | 2024-02-15 | 177000 | -177000 | 0 | Authorized | 5949 | 05 | E-76 approved on | NA | 0 | 3 | 6 | NA | Shell Creek Rd Pm 9.517 & 10.368 In San Luis Obispo County | Emergency Opening - Place 1-4 Ton Rock Slope Protection Method A To Protect | 2 | 2024-02-06 | 2024-02-06 | SLOCOG |  |  | M9MVG9PJJ5J3
Obligated | ER | 15J7(039) | San Luis Obispo County | 2024-02-06 | 2024-02-06 | 2024-02-06 | 2024-02-09 | 2024-02-15 | 20750 | -20750 | 0 | Authorized | 5949 | 05 | E-76 approved on | NA | 0 | 3 | 6 | NA | Templeton Rd Pm 5.084 In San Luis Obispo County | Emergency Opening - Backfill And Stabilize Road Edge With Erosion Control | 2 | 2024-02-06 | 2024-02-06 | SLOCOG |  |  | M9MVG9PJJ5J3
Obligated | ER | 15J7(040) | San Luis Obispo County | 2024-02-06 | 2024-02-06 | 2024-02-06 | 2024-02-09 | 2024-02-15 | 145000 | -145000 | 0 | Authorized | 5949 | 05 | E-76 approved on | NA | 0 | 3 | 6 | NA | Vineyard Dr Pm 6.714 & 8.135 In San Luis Obispo County | Emergency Opening - Clear Culvert Inlet And Outlet, Replace Existing Rock, | 2 | 2024-02-06 | 2024-02-06 | SLOCOG |  |  | M9MVG9PJJ5J3
Obligated | ER | 15J7(041) | San Luis Obispo County | 2024-02-06 | 2024-02-06 | 2024-02-06 | 2024-02-09 | 2024-02-15 | 52000 | -52000 | 0 | Authorized | 5949 | 05 | E-76 approved on | NA | 0 | 3 | 6 | NA | South Bay Blvd Pm 1.105 In San Luis Obispo County | Emergency Opening - Remove The Eroded Section Of The Road And Backfill It. | 2 | 2024-02-06 | 2024-02-06 | SLOCOG |  |  | M9MVG9PJJ5J3
Obligated | ER | 15J7(029) | San Luis Obispo County | 2024-02-05 | 2024-02-05 | 2024-02-05 | 2024-02-07 | 2024-02-13 | 569500 | -569500 | 0 | Authorized | 5949 | 05 | E-76 approved on | NA | 0 | 2 | 6 | NA | Adalaida Rd (pm 4.423, 6.415, 8.269, 9.038, 9.089, 11.188) And San Marcos Rd | Emergency Opening | 2 | 2024-02-05 | 2024-02-05 | SLOCOG |  |  | M9MVG9PJJ5J3
Obligated | ER | 15J7(031) | San Luis Obispo County | 2024-02-05 | 2024-02-05 | 2024-02-05 | 2024-02-09 | 2024-02-15 | 287000 | -287000 | 0 | Authorized | 5949 | 05 | E-76 approved on | NA | 0 | 4 | 6 | NA | El Campo Rd Pm 2.544 In San Luis Obispo County | Emergency Opening - Road And Culvert Repair | 2 | 2024-02-05 | 2024-02-05 | SLOCOG |  |  | M9MVG9PJJ5J3
Obligated | ER | 15J7(045) | Santa Cruz County | 2024-02-07 | 2024-02-07 | 2024-02-07 | 2024-02-09 | 2024-02-15 | 161000 | -161000 | 0 | Authorized | 5936 | 05 | E-76 approved on | NA | 0 | 2 | 6 | NA | Highland Way Pm 0.70 In Santa Cruz County | Structure Excavation And Backfill, New Ac Pavement And Dike, Rock Slope | 2 | 2024-02-07 | 2024-02-07 | AMBAG |  |  | DQHKDRT8LVY8
Obligated | ER | 15J7(043) | Santa Cruz County | 2024-02-06 | 2024-02-06 | 2024-02-06 | 2024-02-09 | 2024-02-15 | 160250 | -160250 | 0 | Authorized | 5936 | 05 | E-76 approved on | NA | 0 | 3 | 6 | NA | Granite Creek Rd Pm 1.26 In Santa Cruz County | Emergency Opening - Remove Damaged Culvert And Headwall, Place Newculvert | 2 | 2024-02-06 | 2024-02-06 | AMBAG |  |  | DQHKDRT8LVY8
Obligated | ER | 15J7(074) | Santa Cruz County | 2024-02-08 | 2024-02-08 | 2024-02-09 | 2024-02-12 | 2024-02-15 | 2595987.08 | -2595987.08 | 0 | Authorized | 5936 | 05 | E-76 approved on | NA | 0 | 4 | 3 | NA | Glenwood Dr Pm 2.91 In Santa Cruz County | Emergency Opening | 2 | 2024-02-08 | 2024-02-08 | AMBAG |  |  | DQHKDRT8LVY8
Obligated | ER | 15J7(082) | San Luis Obispo County | 2024-02-09 | 2024-02-09 | 2024-02-16 | 2024-02-20 | 2024-02-27 | 157500 | -157500 | 0 | Authorized | 5949 | 05 | E-76 approved on | NA | 0 | 11 | 7 | NA | Huasna Rd Pm 4.563, 4.811, 10.961 In San Luis Obispo County | Emergency Opening | 2 | 2024-02-09 | 2024-02-09 | SLOCOG |  |  | M9MVG9PJJ5J3
Obligated | ER | 15J7(083) | Santa Barbara County | 2024-02-09 | 2024-02-09 | 2024-02-09 | 2024-02-12 | 2024-02-15 | 694125 | -694125 | 0 | Authorized | 5951 | 05 | E-76 approved on | NA | 0 | 3 | 3 | NA | E Mountain Dr & San Ysidro Rd In Santa Barbara County | E Mountain Dr: Excavate Roadway, Remove And Reconstruct Existing Pipe. | 2 | 2024-02-09 | 2024-02-09 | SBCAG |  |  | Z4A8L588L9G5
Obligated | ER | 15J7(084) | Santa Barbara County | 2024-02-11 | 2024-02-11 | 2024-02-12 | 2024-02-12 | 2024-02-15 | 653780 | -653780 | 0 | Authorized | 5951 | 05 | E-76 approved on | NA | 0 | 1 | 3 | NA | Union Valley Parkway And Bradley Road In Orcutt | Emergency Opening | 2 | 2024-02-11 | 2024-02-11 | SBCAG |  |  | Z4A8L588L9G5
Obligated | ER | 15J7(086) | Santa Barbara County | 2024-02-12 | 2024-02-12 | 2024-02-12 | 2024-02-13 | 2024-02-21 | 292450 | -292450 | 0 | Authorized | 5951 | 05 | E-76 approved on | NA | 0 | 1 | 8 | NA | Foxen Canyon Rd Mp 2.8 In Santa Barbara County | Emergency Opening | 2 | 2024-02-12 | 2024-02-12 | SBCAG |  |  | Z4A8L588L9G5
Obligated | ACSTP | 15J7(088) | Santa Barbara County | 2024-01-19 | 2024-01-19 | 2024-01-23 | 2024-03-20 | 2024-03-26 | 0 | 75589 | 75589 | Authorized | 5951 | 05 | E-76 approved on | NA | 0 | 61 | 6 | NA | Santa Rosa Rd @ Mp 15.8 In Santa Barbara County | Rebuild Bench To Original Width And Sloped Into Hillside To Catch Future | 2 | 2024-01-19 | 2024-01-19 | SBCAG |  |  | Z4A8L588L9G5
Obligated | ER | 15J7(091) | Santa Barbara County | 2024-02-13 | 2024-02-13 | 2024-02-13 | 2024-02-15 | 2024-02-23 | 500913 | -500913 | 0 | Authorized | 5951 | 05 | E-76 approved on | NA | 0 | 2 | 8 | NA | Jalama Rd At Mp 3.4 In Santa Barbara County. | Emergency Opening | 2 | 2024-02-13 | 2024-02-13 | SBCAG |  |  | Z4A8L588L9G5
Obligated | ER | 15J7(092) | Santa Barbara County | 2024-02-14 | 2024-02-14 | 2024-02-14 | 2024-02-15 | 2024-02-23 | 485625 | -485625 | 0 | Authorized | 5951 | 05 | E-76 approved on | NA | 0 | 1 | 8 | NA | Modoc Rd At Arroyo Burro Creek In Santa Barbara County. | Emergency Opening-reconstruct The Embankment With Bench And Fill, Install | 2 | 2024-02-14 | 2024-02-14 | SBCAG |  |  | Z4A8L588L9G5
Obligated | ACST-ER | 15J7(093) | Santa Barbara County | 2024-02-19 | 2024-02-19 | 2024-02-20 | 2024-02-21 | 2024-02-26 | 96689 | -96689 | 0 | Authorized | 5951 | 05 | E-76 approved on | NA | 0 | 2 | 5 | NA | Orcutt-garey Rd & Palmer Rd Near Orcutt In Santa Barbara County | Orcutt-garey Rd: Restore Slope By Bench And Fill Method, Place Rsp At Toe Of | 2 | 2024-02-19 | 2024-02-19 | SBCAG |  |  | Z4A8L588L9G5
Obligated | ACSTP | 15J7(103) | San Luis Obispo County | 2024-01-24 | 2024-01-24 | 2024-01-31 | 2024-02-01 | 2024-02-27 | 0 | 0 | 0 | Authorized | 5949 | 05 | E-76 approved on | NA | 0 | 8 | 26 | NA | Creston Rd Bridge Pm 3.491 In San Luis Obispo County | Bridge Replacement - Bridge Design. Remove Existing Damaged Bridge. | 2 | 2024-01-24 | 2024-01-24 | SLOCOG |  |  | M9MVG9PJJ5J3
Obligated | ER | 15J7(054) | Santa Cruz | 2024-02-07 | 2024-02-07 | 2024-02-08 | 2024-02-09 | 2024-02-15 | 4506473 | -4506473 | 0 | Authorized | 5025 | 05 | E-76 approved on | NA | -1 | 2 | 6 | NA | At 4 Sites On West Cliff Dr In City Of Santa Cruz, Opposite Of 920 W. Cliff | Emergency Opening | 2 | 2024-02-08 | 2024-02-08 | AMBAG |  |  | RSA8LJM3KAR4
Obligated | ER | 15J7(113) | Capitola | 2024-02-15 | 2024-02-15 | 2024-02-15 | 2024-02-20 | 2024-02-27 | 743127 | -743127 | 0 | Authorized | 5304 | 05 | E-76 approved on | NA | 0 | 5 | 7 | NA | Cliff Drive Adjacent To 4850 Cliff Drive In Capitola, Ca | Construction Of An Armoring Structure, Currently Anticipated To Be A | 2 | 2024-02-15 | 2024-02-15 | AMBAG |  |  | RWHKKLXXFQD6
Obligated | ER | 15J7(011) | Santa Cruz County | 2024-02-05 | 2024-02-05 | 2024-02-05 | 2024-02-09 | 2024-02-15 | 554750 | -554750 | 0 | Authorized | 5936 | 05 | E-76 approved on | NA | 0 | 4 | 6 | NA | East Zayante Rd Pm 6.55 In Santa Cruz County | Emergency Opening - Geotechnical Investigation, Structure Excavation And | 2 | 2024-02-05 | 2024-02-05 | AMBAG |  |  | DQHKDRT8LVY8
Obligated | BRLO | 5951(184) | Santa Barbara County | 2024-02-06 | 2024-02-06 | 2024-02-06 | 2024-02-06 | 2024-02-13 | 0 | 0 | 0 | Authorized | 5951 | 05 | E-76 approved on | NA | 1 | 0 | 7 | CT14 | Foothill Rd @ Cuyama River (1.5 Mi W Of Sr 33) In Unincorporated Santa | Post-construction Environmental Mitigation & Monitoring For New Bridge | 2 | 2024-02-05 | 2024-02-05 | SBCAG |  |  | Z4A8L588L9G5
Obligated | BRLO | 5944(150) | Monterey County | 2024-02-05 | 2024-02-05 | 2024-02-05 | 2024-02-05 | 2024-02-07 | 0 | 0 | 0 | Authorized | 5944 | 05 | E-76 approved on | NA | 0 | 0 | 2 | GP HBRR | Boronda Rd Bridge At The Carmel River, 44c0099 | Seismic Retrofit And Bridge Painting | 2 | 2024-02-05 | 2024-02-05 | AMBAG |  |  | KRZEPPNNGLF3
Obligated | HSIPL | 5949(177) | San Luis Obispo County | 2024-03-05 | 2024-03-05 | 2024-03-05 | 2024-03-14 | 2024-03-19 | 0 | 0 | 0 | Authorized | 5949 | 05 | E-76 approved on | NA | 0 | 9 | 5 | 22300000851 | Non-signalized Intersections Various Locations: Burton Dr @ Burton Circle, | Install Led Street Lights | 3 | 2024-03-05 | 2024-03-05 | SLOCOG |  |  | M9MVG9PJJ5J3
Obligated | BRLO | NBIL(526) | SANTA BARBARA | 2024-01-23 | 2024-01-23 | 2024-01-25 | 2024-02-01 | 2024-02-05 | 4505200 | 0 | 4505200 | Authorized | 5951 | 05 | E-76 approved on | NA | 1 | 9 | 4 | CT14 | Mountain Dr. Over Cold Springs Creek In Sb County Near Montecito | New Bridge To Replace Lwc (tc) | 4 | 2024-01-22 | 2024-01-22 | SBCAG |  |  | Z4A8L588L9G5
Obligated | BRLS | 5007(071) | Santa Barbara | 2024-01-25 | 2024-01-25 | 2024-01-26 | 2024-02-01 | 2024-02-05 | 326676 | 0 | 369000 | Authorized | 5007 | 05 | E-76 approved on | NA | 0 | 7 | 4 | 208-0000-0008 | De La Vina St, Over Mission Creek, 0.1 Mi N Alamar St. | Bridge Replacement | 4 | 2024-01-25 | 2024-01-25 | SBCAG |  |  | L7F1A51PFHH3
Obligated | ER | 32L0(064) | Santa Cruz County | 2024-02-21 | 2024-02-21 | 2024-02-21 | 2024-02-23 | 2024-02-27 | 0 | 0 | 0 | Authorized | 5936 | 05 | E-76 approved on | NA | 0 | 2 | 4 | NA | In The County Of Santa Cruz On Browns Valley Road Pm 2.93 | Reconstruct And Stabilize The Embankment And Roadway | 4 | 2024-02-21 | 2024-02-21 | AMBAG |  |  | DQHKDRT8LVY8
Obligated | ACST-ER | 32L0(414) | Santa Cruz County | 2024-02-12 | 2024-02-12 | 2024-02-21 | 2024-02-23 | 2024-02-27 | 0 | 59327.83 | 67012.5 | Authorized | 5936 | 05 | E-76 approved on | NA | 3 | 11 | 4 | NA | In The County Of Santa Cruz On San Andreas Rd Pm 1.24 | Stabilize Embankment And Protect Slope | 4 | 2024-02-09 | 2024-02-12 | AMBAG |  |  | DQHKDRT8LVY8
Obligated | ER | 32L0(457) | Monterey County | 2023-12-21 | 2024-01-19 | 2024-01-24 | 2024-02-14 | 2024-02-23 | -80248.56 | 0 | -91111.32 | Authorized | 5944 | 05 | E-76 approved on | NA | 31 | 26 | 9 | NA | San Juan Grade Road At Mp 8.6 | County Forces Placed Barricades And Cold Mix. Pr Under Eo To Include | 4 | 2023-12-19 | 2024-01-19 | AMBAG |  |  | KRZEPPNNGLF3
Obligated | BRLO | NBIL(526) | SANTA BARBARA | 2024-03-15 | 2024-03-15 | 2024-03-15 | 2024-03-15 | 2024-03-19 | 0 | 0 | 0 | Authorized | 5951 | 05 | E-76 approved on | NA | 0 | 0 | 4 | CT14 | Mountain Dr. Over Cold Springs Creek In Sb County Near Montecito | New Bridge To Replace Lwc (tc) | 5 | 2024-03-15 | 2024-03-15 | SBCAG |  |  | Z4A8L588L9G5
Obligated | ER | 32L0(007) | Santa Cruz County | 2024-01-30 | 2024-01-31 | 2024-01-31 | 2024-02-06 | 2024-02-13 | 0 | 174479.5 | 197083.26 | Authorized | 5936 | 05 | E-76 approved on | NA | 1 | 6 | 7 | NA | In The County Of Santa Cruz On Branciforte Drive 2.22 | Stabilize And Reconstruct Roadway | 5 | 2024-01-30 | 2024-01-31 | AMBAG |  |  | DQHKDRT8LVY8
Obligated | ACST-ER | 32L0(013) | Santa Cruz County | 2024-03-12 | 2024-03-12 | 2024-03-12 | 2024-03-19 | 2024-03-22 | 213162.42 | -213162.42 | 0 | Authorized | 5936 | 05 | E-76 approved on | NA | 0 | 7 | 3 | NA | In The County Of Santa Cruz On North Rodeo Gulch Pm 3.82 | Reconstruct Retaining Wall | 5 | 2024-03-12 | 2024-03-12 | AMBAG |  |  | DQHKDRT8LVY8
Obligated | ER | 32L0(023) | Santa Barbara County | 2024-02-16 | 2024-02-16 | 2024-02-16 | 2024-02-20 | 2024-02-27 | 45010.9 | -45010.9 | 0 | Authorized | 5951 | 05 | E-76 approved on | NA | 0 | 4 | 7 | NA | San Marcos Road 1.94 Miles From Cathedral Oaks | Install Retaining Wall And Reconstruct Roadway | 5 | 2024-02-16 | 2024-02-16 | SBCAG |  |  | Z4A8L588L9G5
Obligated | ER | 32L0(207) | Santa Cruz County | 2024-01-30 | 2024-01-31 | 2024-01-31 | 2024-02-07 | 2024-02-13 | 0 | 92021.17 | 103942.12 | Authorized | 5936 | 05 | E-76 approved on | NA | 1 | 7 | 6 | NA | In The County Of Santa Cruz On Redwood Lodge Road Pm 1.65 | Reconstruct Slope | 5 | 2024-01-30 | 2024-01-31 | AMBAG |  |  | DQHKDRT8LVY8
Obligated | ER | 32L0(336) | Santa Cruz County | 2024-02-21 | 2024-02-21 | 2024-02-21 | 2024-02-23 | 2024-02-27 | 0 | 0 | 0 | Authorized | 5936 | 05 | E-76 approved on | NA | 0 | 2 | 4 | NA | In The County Of Santa Cruz On Glenwood Dr Pm 2.02 | Backfill Soldier Pile Wall | 5 | 2024-02-21 | 2024-02-21 | AMBAG |  |  | DQHKDRT8LVY8
Obligated | ER | 32L0(414) | Santa Cruz County | 2024-03-06 | 2024-03-06 | 2024-03-07 | 2024-03-19 | 2024-03-22 | 59327.83 | -59327.83 | 0.00NA999476131 | Authorized | 5936 | 05 | E-76 approved on | NA | 7 | 13 | 3 | NA | In The County Of Santa Cruz On San Andreas Rd Pm 1.24 | Stabilize Embankment And Protect Slope | 5 | 2024-02-28 | 2024-03-06 | AMBAG |  |  | DQHKDRT8LVY8
Obligated | ER | 32L0(260) | Santa Cruz County | 2024-02-21 | 2024-02-21 | 2024-02-21 | 2024-02-23 | 2024-02-27 | 0 | 0 | 0 | Authorized | 5936 | 05 | E-76 approved on | NA | 0 | 2 | 4 | NA | In The County Of Santa Cruz On Eureka Canyon Pm 8.39 | Stabilize And Reconstruct Roadway | 5 | 2024-02-21 | 2024-02-21 | AMBAG |  |  | DQHKDRT8LVY8
Obligated | HSIPL | 5138(053) | Santa Maria | 2024-02-12 | 2024-02-12 | 2024-02-12 | 2024-02-12 | 2024-02-15 | 0 | 0 | 40288 | Authorized | 5138 | 05 | E-76 approved on | NA | 4 | 0 | 3 | LOCALHSIP | In The City Of Santa Maria On N. Broadway (sr-135) Between Main Street (sr- | Remove Part Of Existing Median And Replace With Extended Left Turn Lanes, | 6 | 2024-02-08 | 2024-02-09 | SBCAG |  |  | KMK4VMLF3VFF9
Obligated | BPMPL | 5936(113) | Santa Cruz County | 2024-03-06 | 2024-03-06 | 2024-03-06 | 2024-03-06 | 2024-03-07 | 0 | 0 | 0 | Authorized | 5936 | 05 | E-76 approved on | NA | 6 | 0 | 1 | GP HBRR | Soquel Dr@rodeo Gulch 36c-0042 | Bridge Preventative Maintinence | 7 | 2024-02-29 | 2024-03-01 | AMBAG |  |  | DQHKDRT8LVY8
Obligated | ER | 32L0(012) | Santa Cruz County | 2024-03-06 | 2024-03-06 | 2024-03-06 | 2024-03-19 | 2024-03-22 | 8328 | -8328 | 0 | Authorized | 5936 | 05 | E-76 approved on | NA | 0 | 13 | 3 | NA | In The County Of Santa Cruz On Soquel-san Jose Pm 5.91 | Repair Slip Out Embankment And Roadway | 7 | 2024-03-06 | 2024-03-06 | AMBAG |  |  | DQHKDRT8LVY8
Obligated | BRLO | 5943(063) | San Benito County | 2023-11-16 | 2024-01-26 | 2024-01-29 | 2024-02-06 | 2024-02-15 | 2663750 | -2663750 | 0 | Authorized | 5943 | 05 | E-76 approved on | NA | 71 | 11 | 9 | GP HBRR | Limekiln Road Bridge #43c0054 In The County Of San Benito | Bridge Replacement (tc) | 8 | 2023-11-16 | 2024-01-26 | AMBAG |  |  | UX1PHLRE4QQ3
Obligated | ATPL | 5007(065) | Santa Barbara | 2024-02-01 | 2024-02-01 | 2024-02-01 | 2024-02-01 | 2024-02-06 | -0.02 | 0 | 83988.53 | Authorized | 5007 | 05 | E-76 approved on | NA | 7 | 0 | 5 | SBCITY3 | Along Las Positas And Modoc Roads In The City Of Santa Barbara | Multiuse Pathway For Bicyclists, Runners And Pedestrians (planning , | 9 | 2024-01-25 | 2024-01-26 | SBCAG |  |  | L7F1A51PFHH3
Obligated | BHLO | 5944(100) | Monterey County | 2024-03-19 | 2024-03-19 | 2024-03-19 | 2024-03-19 | 2024-03-22 | 0 | 0 | 0 | Authorized | 5944 | 05 | E-76 approved on | NA | 0 | 0 | 3 | GP_HBRR | Bradley Road Bridge At Salinas River | Scour Protection (tc) | 9 | 2024-03-19 | 2024-03-19 | AMBAG |  |  | KRZEPPNNGLF3
Obligated | BRLO | 5423(029) | Atascadero | 2024-03-08 | 2024-03-08 | 2024-03-11 | 2024-03-11 | 2024-03-12 | 0 | 0 | 0 | Authorized | 5423 | 05 | E-76 approved on | NA | 0 | 3 | 1 | 22300000832 | Santa Lucia Rd Over Graves Creek - Br. No. 49c-0164 (tc) | Bridge Replacement - Br.no. 49c-0164 (tc) | 10 | 2024-03-08 | 2024-03-08 | SLOCOG |  |  | J4ZKW85KJ1H8
Obligated | BRLO | 5951(141) | Santa Barbara County | 2024-02-12 | 2024-02-12 | 2024-02-12 | 2024-02-12 | 2024-02-15 | -625640.02 | 0 | -532546.68 | Authorized | 5951 | 05 | E-76 approved on | NA | 4 | 0 | 3 | CT14 | Fernald Pt. Ln. Bridge #51c0137 @ Romero Crk In Santa Barbara County | Bridge Replacement (tc) | 11 | 2024-02-08 | 2024-02-09 | SBCAG |  |  | Z4A8L588L9G5
Obligated | BRLS | 5943(043) | San Benito County | 2024-03-15 | 2024-03-15 | 2024-03-15 | 2024-03-15 | 2024-03-19 | 0 | 0 | 0 | Authorized | 5943 | 05 | E-76 approved on | NA | 0 | 0 | 4 | GP HBRR | Union Rd @ San Benito River (br# 43c0002) | Bridge Replacement | 11 | 2024-03-15 | 2024-03-15 | AMBAG |  |  | UX1PHLRE4QQ3
Obligated | CMLNI | 5223(016) | Corcoran | 2024-02-28 | 2024-03-01 | 2024-03-04 | 2024-03-11 | 2024-03-12 | 272000 | 0 | 365000 | Authorized | 5223 | 06 | E-76 approved on | NA | 14 | 10 | 1 | CM5223A | Corcoran At The City Corp Yard | Purchase Pm 10, Pm 2.5 Efficient Street Sweeper, Purchase One New Elgin | 1 | 2024-02-16 | 2024-03-06 | KCAG |  |  | L8JXLDCDAP44
Obligated | STPL | 5950(512) | Kern County | 2024-03-14 | 2024-03-14 | 2024-03-14 | 2024-03-19 | 2024-03-20 | 3200000 | 0 | 3614594 | Authorized | 5950 | 06 | E-76 approved on | NA | 1 | 5 | 1 | KER180403/KER | Buena Vista Blvd From South Fairfax Rd To Main St; Buena Vista Blvd From | Road Rehabilitation. | 1 | 2024-03-13 | 2024-03-13 | KCOG |  |  | JTBAYSUJB446
Obligated | CML | 5950(516) | Kern County | 2024-03-08 | 2024-03-08 | 2024-03-11 | 2024-03-12 | 2024-03-12 | 626174 | 0 | 707303 | Authorized | 5950 | 06 | E-76 approved on | NA | 0 | 4 | 0 | KER180507 | Intersection Of Snow Rd And Quail Creek Rd | Construct A Traffic Signal And Ancillary Facilities. | 1 | 2024-03-08 | 2024-03-08 | KCOG |  |  | JTBAYSUJB446
Obligated | BPMP | 5941(134) | Madera County | 2023-09-25 | 2024-02-20 | 2024-02-22 | 2024-02-26 | 2024-02-28 | 753840 | 0 | 942300 | Authorized | 5941 | 06 | E-76 approved on | NA | 148 | 6 | 2 | MAD410001 | Pm00183 35 Locations: Bridges: 41c0003, 41c0010, 41c0019, 41c0024, 41c0026, | Bridge Preventative Maintenance Project | 1 | 2023-09-25 | 2024-02-22 | MCTC |  |  | KNPYKHLWNKE1
Obligated | STPL | 5193(044) | Taft | 2024-01-17 | 2024-01-29 | 2024-02-14 | 2024-02-14 | 2024-02-21 | 252000 | 0 | 415883 | Authorized | 5193 | 06 | E-76 approved on | NA | 20 | 16 | 7 | KER180403 | 10th St Between Crosswalk At Bike/ped Path To Kern Street (sr 33) | Rehabilitation, Pavement Rehabilitation | 1 | 2024-01-09 | 2024-01-17 | KCOG |  |  | M355M1YAZH53
Obligated | STPL | 5208(187) | Clovis | 2024-02-13 | 2024-02-13 | 2024-02-14 | 2024-02-22 | 2024-02-27 | 1248273 | 0 | 1410000 | Authorized | 5208 | 06 | E-76 approved on | NA | 4 | 9 | 5 | FRE130064 | Shaw Ave From Armstrong Ave To Temperance Ave | Road Rehabilitation | 1 | 2024-02-09 | 2024-02-13 | FCOG |  |  | FZXEQ4KUYKE7
Obligated | ACSTP | 15J9(166) | Madera County | 2023-12-11 | 2024-02-27 | 2024-03-15 | 2024-03-19 | 2024-03-22 | 0 | 383357.03 | 433025 | Authorized | 5941 | 06 | E-76 approved on | NA | 15 | 21 | 3 | NA | Road 225 At Rainbow Drive (222) | Remove Roadway Structural Section. Excavate To Bench Into Existing Material. | 1 | 2024-02-12 | 2024-02-19 | MCTC |  |  | KNPYKHLWNKE1
Obligated | ACSTP | 15J9(167) | Madera County | 2024-02-27 | 2024-02-27 | 2024-03-15 | 2024-03-19 | 2024-03-22 | 0 | 102196.81 | 115437.5 | Authorized | 5941 | 06 | E-76 approved on | NA | 4 | 21 | 3 | NA | Road 274 At Road 229a | Cleanly Cut Roadway Structural Section. Excavate To Bench Into Existing | 1 | 2024-02-23 | 2024-02-23 | MCTC |  |  | KNPYKHLWNKE1
Obligated | BPMP | 5945(125) | Kings County | 2023-10-27 | 2024-01-12 | 2024-01-18 | 2024-02-07 | 2024-02-13 | 432000 | 0 | 540000 | Authorized | 5945 | 06 | E-76 approved on | NA | 77 | 26 | 6 | KIN-HBP | Pm00182 Bridges 45c0004, 45c0016, 45c0041, 45c0046, 45c0047, 45c0048, | Bridge Preventative Maintenance | 1 | 2023-10-27 | 2024-01-18 | KCOG |  |  | MHSYMZNJMZB1
Obligated | CMLNI | 6087(079) | Kern County Council of Governments | 2024-01-22 | 2024-01-22 | 2024-01-25 | 2024-02-06 | 2024-02-13 | 256470 | 0 | 289699 | Authorized | 6087 | 06 | E-76 approved on | NA | 0 | 15 | 7 | KER220501 | Kern County: Commutekern Rideshare Program | A Comprehensive Transportation Demand Management Program That Promotes | 1 | 2024-01-22 | 2024-01-22 | KCOG |  |  | T1Y6YMBTGKP4
Obligated | STPLNI | 6087(080) | Kern County Council of Governments | 2024-01-25 | 2024-01-25 | 2024-02-06 | 2024-02-06 | 2024-02-13 | 79677 | 0 | 90000 | Authorized | 6087 | 06 | E-76 approved on | NA | 0 | 12 | 7 | KER220401 | Throughout Kern County | Regional Traffic Count Program | 1 | 2024-01-25 | 2024-01-25 | KCOG |  |  | T1Y6YMBTGKP4
Obligated | CML | 5301(016) | Orange Cove | 2024-01-29 | 2024-01-29 | 2024-01-29 | 2024-01-29 | 2024-02-01 | 0 | 0 | 252.5 | Authorized | 5301 | 06 | E-76 approved on | NA | 4 | 0 | 3 | FRE130053 | Center Street Trail Connection From Park To Railroad | Construction Of Trail Connection (tc) | 2 | 2024-01-25 | 2024-01-26 | COFCG |  |  | TE9HGZKH8NR1
Obligated | HSIPSL | 5946(195) | Tulare County | 2024-02-07 | 2024-02-07 | 2024-02-13 | 2024-02-22 | 2024-02-27 | 60000 | 0 | 60000 | Authorized | 5946 | 06 | E-76 approved on | NA | 12 | 15 | 5 | TUL 12-144 | Total Of Eight Locations Along Road 236, Avenue 144, Road 196 North And | Replace Existing Non-standard, Damaged Or Obsolete Guardrails. | 2 | 2024-01-26 | 2024-02-07 | TCAG |  |  | NN1GT1HPGN78
Obligated | CML | 5223(023) | Corcoran | 2024-02-08 | 2024-02-08 | 2024-02-08 | 2024-02-08 | 2024-02-15 | 0 | 0 | 0 | Authorized | 5223 | 06 | E-76 approved on | NA | 15 | 0 | 7 | GP-BIKE | Phase 2 Includes Various Improvements On Several Corridors: North Ave, Otis | Construct Sidewalk, Ada Ramps, Lighted Crosswalks, And Cl Iii Bike Routes | 2 | 2024-01-24 | 2024-02-08 | KCAG |  |  | L8JXLDCDAP44
Obligated | CML | 5223(022) | Corcoran | 2024-02-08 | 2024-02-08 | 2024-02-08 | 2024-02-08 | 2024-02-15 | 0 | 0 | 0 | Authorized | 5223 | 06 | E-76 approved on | NA | 15 | 0 | 7 | GP-BIKE | Phase 1 Includes Various Improvements On Several Corridors: Orange Ave, Otis | Construct Sidewalks, Ada Ramps, Lighted Crosswalk, And Class Iii Bike Routes | 2 | 2024-01-24 | 2024-02-08 | KCAG |  |  | L8JXLDCDAP44
Obligated | CML | 5208(180) | Clovis | 2024-02-15 | 2024-02-15 | 2024-02-20 | 2024-02-22 | 2024-02-27 | 44265 | 0 | 50000 | Authorized | 5208 | 06 | E-76 approved on | NA | 401 | 7 | 5 | FRE190021 | Dewolf Avenue And Owens Mountain Parkway Intersection | Install A Roundabout And Associated Improvements. | 2 | 2023-01-10 | 2024-02-15 | FCOG |  |  | FZXEQ4KUYKE7
Obligated | CML | 5208(181) | Clovis | 2024-02-15 | 2024-02-15 | 2024-02-16 | 2024-02-16 | 2024-02-23 | 0 | 0 | 0 | Authorized | 5208 | 06 | E-76 approved on | NA | 0 | 1 | 7 | FRE190006 | Shepherd Avenue From Peach Avenue To Dewolf Avenue | Signal Interconnect Including Installation Of Fiber Optics And Associated | 2 | 2024-02-15 | 2024-02-16 | FCOG |  |  | FZXEQ4KUYKE7
Obligated | STPCML | 5252(035) | Parlier | 2024-02-24 | 2024-02-24 | 2024-02-26 | 2024-02-26 | 2024-02-28 | 0 | 0 | 0 | Authorized | 5252 | 06 | E-76 approved on | NA | 10 | 2 | 2 | FRE190021 | Intersection Of Parlier Ave And Newmark Ave In The City Of Parlier | Construct One-lane Roundabout With Pedestrian And Bicycle Crossing Facility | 2 | 2024-02-14 | 2024-02-26 | FCOG |  |  | VYM8LSDT1RA6
Obligated | STPL | 5060(401) | Fresno | 2024-03-04 | 2024-03-04 | 2024-03-06 | 2024-03-07 | 2024-03-11 | 20950 | 0 | 20950 | Authorized | 5060 | 06 | E-76 approved on | NA | 25 | 3 | 4 | FRE090611 | Cedar Avenue From Herndon Avenue To Alluval Avenue | Pavement Overlay, Buffered And Non-buffered Class Ii Facilities, Curb Ramp | 2 | 2024-02-08 | 2024-02-29 | FCOG |  |  | ELPGKCJ7DJK7
Obligated | STPL | 5060(403) | Fresno | 2024-03-01 | 2024-03-04 | 2024-03-05 | 2024-03-07 | 2024-03-11 | 24632 | 0 | 28008 | Authorized | 5060 | 06 | E-76 approved on | NA | 25 | 3 | 4 | FRE090611 | Shaw Ave; Fruit Ave East Of Palm Ave | Grind, Overlay, Curb Ramps, Median Nose Modification, Signage, Striping, And | 2 | 2024-02-08 | 2024-02-29 | FCOG |  |  | ELPGKCJ7DJK7
Obligated | CML | 5060(400) | Fresno | 2024-03-04 | 2024-03-04 | 2024-03-05 | 2024-03-07 | 2024-03-11 | 15050 | 0 | 17000 | Authorized | 5060 | 06 | E-76 approved on | NA | 25 | 3 | 4 | FRE090137 | Palm Avenue From Herndon Ave To Shaw Avenue | Install Adaptive Ts Synchronization And Pedestrian Improvements; Asct, | 2 | 2024-02-08 | 2024-02-29 | FCOG |  |  | ELPGKCJ7DJK7
Obligated | STPL | 5343(020) | Mcfarland | 2024-02-26 | 2024-02-28 | 2024-03-12 | 2024-03-12 | 2024-03-19 | 346601 | 0 | 391508 | Authorized | 5343 | 06 | E-76 approved on | NA | 2 | 13 | 7 | KER220403 | Mcfarland: Intersection Of W. Perkins Ave And 3rd St | Install Flashing Stop Lights, High Visibility Crosswalk, Resurfacing Road On | 2 | 2024-02-26 | 2024-02-26 | KCOG |  |  | JNWZKQ5J42Z9
Obligated | STPL | 5208(185) | Clovis | 2024-03-05 | 2024-03-05 | 2024-03-07 | 2024-03-11 | 2024-03-12 | 653422 | 0 | 1195135 | Authorized | 5208 | 06 | E-76 approved on | NA | 7 | 6 | 1 | FRE130064 | Temperance Ave: Herndon Avenue To State Route 168 | Temperance Ave From Herndon Ave To State Route 168; Road Rehabilitation | 2 | 2024-02-27 | 2024-03-05 | FCOG |  |  | FZXEQ4KUYKE7
Obligated | STPL | 5208(186) | Clovis | 2024-01-31 | 2024-01-31 | 2024-02-06 | 2024-02-07 | 2024-02-13 | 714898 | 0 | 1033364 | Authorized | 5208 | 06 | E-76 approved on | NA | 0 | 7 | 6 | FRE130064 | Willow Ave: Shaw Avenue To Barstow Avenue | Road Rehabilitation Including Grinding, Paving, Concrete, Installing Traffic | 2 | 2024-01-31 | 2024-01-31 | FCOG |  |  | FZXEQ4KUYKE7
Obligated | CML | 5091(064) | Hanford | 2024-02-12 | 2024-02-28 | 2024-02-29 | 2024-03-06 | 2024-03-11 | 109770 | 0 | 125500 | Authorized | 5091 | 06 | E-76 approved on | NA | 13 | 7 | 5 | GP-SIGNAL | Intersection Of 9th Ave And Lacey Blvd | Install New Traffic Signal, Including Ada Ramps And Lane Transitioning | 3 | 2024-02-15 | 2024-02-26 | KCAG |  |  | N5PAG72LU3S3
Obligated | CML | 5281(031) | Shafter | 2024-02-22 | 2024-02-22 | 2024-02-22 | 2024-02-22 | 2024-02-26 | 0 | 0 | 0 | Authorized | 5281 | 06 | E-76 approved on | NA | 7 | 0 | 4 | KER180507 | Santa Fe Way From Los Angeles Ave To Galpin St | Construct 8' Shoulders On Both Sides Of Roadway | 3 | 2024-02-15 | 2024-02-16 | KCOG |  |  | RP8KZKM1YJB8
Obligated | CML | 5950(484) | Kern County | 2024-02-22 | 2024-02-22 | 2024-02-22 | 2024-02-22 | 2024-02-26 | -8688.67 | 0 | 0 | Authorized | 5950 | 06 | E-76 approved on | NA | 7 | 0 | 4 | KER180507 | Intersection Of Manor Street At Day Avenue | Traffic Signal, Intersection Lighting, Striping, Curb Ramps, And Sidewalks | 3 | 2024-02-15 | 2024-02-16 | KCOG |  |  | JTBAYSUJB446
Obligated | STPCML | 5950(486) | Kern County | 2024-02-22 | 2024-03-18 | 2024-03-18 | 2024-03-19 | 2024-03-22 | -788852.7 | 0 | -1530876.67 | Authorized | 5950 | 06 | E-76 approved on | NA | 26 | 1 | 3 | KER180507 | Scofield Ave From Lerdo Highway To Wasco City Limit | Paving Hot Mix Asphalt, Pave Existing Shoulders, Painting Traffic Stripes | 3 | 2024-02-21 | 2024-03-13 | KCOG |  |  | JTBAYSUJB446
Obligated | CML | 5146(029) | Coalinga | 2024-02-12 | 2024-02-20 | 2024-02-21 | 2024-02-22 | 2024-02-27 | 0 | 0 | 0 | Authorized | 5146 | 06 | E-76 approved on | NA | 12 | 2 | 5 | FRE190011 | Alleys #38 Dorothy Street Between Polk And Valley, Alley #39 Between Hayes | Pave Seven Dirt Alleys. (tc) | 3 | 2024-02-08 | 2024-02-12 | COFCG |  |  | QJ6KB4438345
Obligated | STPL | 5370(028) | Arvin | 2024-01-29 | 2024-01-29 | 2024-01-29 | 2024-02-08 | 2024-02-12 | -79.19 | 0 | 215880.74 | Authorized | 5370 | 06 | E-76 approved on | NA | -3 | 10 | 4 | KER160402 | Franklin St. Between Derby St. And Stockton St. | Reconstruction/rehabilitation | 4 | 2024-02-01 | 2024-02-02 | KCOG |  |  | HQNHK2AHXM11
Obligated | STPL | 5208(161) | Clovis | 2024-02-15 | 2024-02-15 | 2024-02-15 | 2024-02-15 | 2024-02-23 | 0 | 0 | 0 | Authorized | 5208 | 06 | E-76 approved on | NA | 17 | 0 | 8 | FRE170005 | Villa-minnewawa Avenue From Herndon Avenue To Alluvial Avenue | Roadway Widening And Reconstruction, Including Bike Lanes, Sidewalk, | 4 | 2024-01-29 | 2024-02-15 | FCOG |  |  | FZXEQ4KUYKE7
Obligated | CML | 5060(363) | Fresno | 2024-01-30 | 2024-01-30 | 2024-01-30 | 2024-01-30 | 2024-02-01 | -766910.12 | 0 | -842380 | Authorized | 5060 | 06 | E-76 approved on | NA | 5 | 0 | 2 | FRE020133 | Clovis Avenue From Mckinley To Shield Avenues | Pedestrian And Bicycle Trail, Including Benching And Landscaping (tc) | 4 | 2024-01-25 | 2024-01-26 | COFCG |  |  | ELPGKCJ7DJK7
Obligated | STPL | 5285(020) | Mendota | 2024-02-25 | 2024-02-25 | 2024-02-27 | 2024-02-27 | 2024-03-04 | 0 | 0 | 0 | Authorized | 5285 | 06 | E-76 approved on | NA | 5 | 2 | 6 | FRE190003 | Sr33 Rrxg Between Bass Ave And Sr 180 Intersection, 9th St Rrxg Between | Safety-railroad/highway Crossing Improvement. Improve Railroad Corridor By | 4 | 2024-02-20 | 2024-02-27 | FCOG |  |  | EUPGJVXPY451
Obligated | ATPL | 5285(021) | Mendota | 2024-02-26 | 2024-02-26 | 2024-02-26 | 2024-02-26 | 2024-02-27 | -22400 | 0 | -96422 | Authorized | 5285 | 06 | E-76 approved on | NA | 4 | 0 | 1 | FRE150045 | Intersection Of 9th Street And Belmont Avenue | Install Overhead Flashing Beacons, Signage, Push Button On Overhead Flashing | 5 | 2024-02-22 | 2024-02-23 | FCOG |  |  | EUPGJVXPY451
Obligated | HSIPL | 5946(162) | Tulare County | 2024-01-30 | 2024-01-30 | 2024-01-30 | 2024-01-30 | 2024-02-01 | -1542.25 | 0 | 35260.35 | Authorized | 5946 | 06 | E-76 approved on | NA | 5 | 0 | 2 | TUL12-144 | Avenue 328 At Three Intersections: Road 112, Road 138 And Road 156. | Install Left-turn Lanes. | 6 | 2024-01-25 | 2024-01-26 | TCAG |  |  | NN1GT1HPGN78
Obligated | BRLO | 5942(214) | Fresno County | 2024-02-26 | 2024-02-26 | 2024-02-26 | 2024-02-26 | 2024-02-27 | 0 | 0 | 0 | Authorized | 5942 | 06 | E-76 approved on | NA | 4 | 0 | 1 | FRE111376 | Bridge 42c0261 On Italian Bar Road Over Redinger Lake | Replace 1 Lane Bridge With 2 Lane Bridge (tc) | 8 | 2024-02-22 | 2024-02-23 | FCOG |  |  | NCT6WZHM8NE1
Obligated | ATPL | 5006(891) | Los Angeles | 2024-02-15 | 2024-02-15 | 2024-02-20 | 2024-02-21 | 2024-02-28 | 185000 | 0 | 231000 | Authorized | 5006 | 07 | E-76 approved on | NA | 80 | 6 | 7 | LATP19S005 | 0.25-mile Vicinity Of 112th Street And Flournoy Elementary Schools In The | Transform Two Of The City's Most Traffic-stressed Schools Through The | 1 | 2023-11-27 | 2024-02-15 | SCAG |  |  | RNA2HUB4ZBK4
Obligated | BHLS | 5108(173) | Long Beach | 2023-12-06 | 2024-02-27 | 2024-03-05 | 2024-03-06 | 2024-03-08 | 164000 | 0 | 205000 | Authorized | 5108 | 07 | E-76 approved on | NA | 85 | 8 | 2 | LA000800 | Bridge No. 53c0218, Clark Ave, Over Los Cerritos Drain Chan, 100 S/o Spring | Rehabilitate Bridge. Widen Existing 6 Lane Bridge To 6 Lane Bridge With | 1 | 2023-12-04 | 2023-12-06 | SCAG |  | Warning | V4NMKFMJASD7
Obligated | ATPL | 5006(952) | Los Angeles | 2024-01-08 | 2024-01-26 | 2024-01-31 | 2024-02-06 | 2024-02-14 | 1099000 | 0 | 1294000 | Authorized | 5006 | 07 | E-76 approved on | NA | 114 | 11 | 8 | LATP23MPO113 | The 21-school Project In The City's Core Is Bounded By Oxford Avenue (west), | Creates 5.9 Miles Of Low-stress Streets With Pedestrian/bicycle Improvements | 1 | 2023-10-04 | 2024-01-26 | SCAG |  |  | RNA2HUB4ZBK4
Obligated | DEML05 | 6115(008) | Mountains Recreation And Conservation Auth. | 2023-11-29 | 2023-11-29 | 2023-11-30 | 2024-02-06 | 2024-02-14 | -436638.21 | 0 | -436638.21 | Authorized | 6115 | 07 | E-76 approved on | NA | 0 | 69 | 8 | LA0D458 | Picoma Wash Mountain Bikeway | Bikeway | 2 | 2023-11-29 | 2023-11-29 | SCAG |  |  | NQ8NMK9LAKK9
Obligated | HSIPL | 5953(758) | Los Angeles County | 2024-03-11 | 2024-03-12 | 2024-03-14 | 2024-03-14 | 2024-03-19 | 876518.5 | 0 | 876518.5 | Authorized | 5953 | 07 | E-76 approved on | NA | 11 | 2 | 5 | SCAG015 | San Francisquito Cyn Rd - Between Elizabeth Lake Rd & The City Of Santa | Install Chevron Signs, And Advance Curve Warning Signs | 2 | 2024-03-01 | 2024-03-11 | SCAG |  |  | ZLJUW5L9K685
Obligated | HSIPL | 5351(037) | Pico Rivera | 2024-02-02 | 2024-02-02 | 2024-02-02 | 2024-02-02 | 2024-02-06 | 0 | 0 | 0 | Authorized | 5351 | 07 | E-76 approved on | NA | 8 | 0 | 4 | SCAG015 | 19 Intersections Along Beverly Blvd, Paramount Blvd, Rosemead Blvd, Slauson | Install 12" Led Lenses, Back Plates, Signal Timing/emergency Vehicle | 2 | 2024-01-25 | 2024-01-26 | SCAG |  |  | RBR1AK1KTAN9
Obligated | HSIPL | 5953(776) | Los Angeles County | 2024-03-17 | 2024-03-17 | 2024-03-17 | 2024-03-17 | 2024-03-19 | 0 | 0 | 0 | Authorized | 5953 | 07 | E-76 approved on | NA | 4 | 0 | 2 | SCAG015 | Athens, Rancho Dominguez Hills, West Carson, Willlowbrook Areas, Et Al | Construct Various Traffic Signal Inmprovements, Including Upgrading | 2 | 2024-03-13 | 2024-03-17 | SCAG |  |  | ZLJUW5L9K685
Obligated | HSIPL | 5202(019) | San Fernando | 2024-03-04 | 2024-03-05 | 2024-03-12 | 2024-03-13 | 2024-03-19 | 453104 | 0 | 625227 | Authorized | 5202 | 07 | E-76 approved on | NA | 27 | 8 | 6 | SCAG015 | Nine (9) Intersections Along The Metrolink Rail Corridor (1st Street At | Install Larger Signal Heads, Additional Street Lighting, And Protected Left- | 2 | 2024-02-07 | 2024-03-05 | SCAG |  |  | RGEUDLBZH2K7
Obligated | DEMOL | 5006(919) | Los Angeles | 2024-02-18 | 2024-02-18 | 2024-03-15 | 2024-03-15 | 2024-03-19 | 0 | 0 | 0 | Authorized | 5006 | 07 | E-76 approved on | NA | 19 | 26 | 4 | LARE1701C | Located In City Of Los Angeles, On 7th Street Between S. Westlake Ave And S. | This Project Will Enhance The Pedestrian Areas Adjacent To Existing Transit | 2 | 2024-01-30 | 2024-03-06 | SCAG |  |  | RNA2HUB4ZBK4
Obligated | CML | 5952(214) | Ventura County | 2024-02-06 | 2024-02-06 | 2024-02-06 | 2024-02-06 | 2024-02-13 | 0 | 0 | 0 | Authorized | 5952 | 07 | E-76 approved on | NA | 15 | 0 | 7 | VEN210603 | East Side Of Ventura Avenue From 350 Feet North Of Crooked Palm Road To Los | Construction Of Sidewalks On The East Side Of Ventura Avenue, Class Ii And | 2 | 2024-01-22 | 2024-02-06 | SCAG |  |  | NHJ2G6B4WLH5
Obligated | CML | 5006(931) | Los Angeles | 2024-02-06 | 2024-02-08 | 2024-02-09 | 2024-02-09 | 2024-02-28 | 1200000 | 0 | 3500000 | Authorized | 5006 | 07 | E-76 approved on | NA | 8 | 1 | 19 | LAF9204 | Project Location Is On Slauson Ave - From Western Ave To Crenshaw Blvd | This Project Will Improve 0.8 Miles Of Slauson Ave: It Will Improve Street | 2 | 2024-01-31 | 2024-02-08 | SCAG |  |  | RNA2HUB4ZBK4
Obligated | BHLO | 5107(033) | Santa Monica | 2024-02-12 | 2024-02-23 | 2024-02-26 | 2024-02-27 | 2024-03-07 | 1850000 | 0 | 1850000 | Authorized | 5107 | 07 | E-76 approved on | NA | 15 | 4 | 9 | LA000800 | Colorado Ave. Over Appian Way/promenade, 0.6 Mi W/o Lincoln Blvd. | Replace Exist 2 Lane Br. With New 2 Lane Br. (tc) | 3 | 2024-02-08 | 2024-02-14 | SCAG |  |  | DEDCLBH5GBC3
Obligated | HSIPL | 5403(028) | Carson | 2024-01-31 | 2024-01-31 | 2024-01-31 | 2024-01-31 | 2024-02-02 | -202400 | 0 | -202400 | Authorized | 5403 | 07 | E-76 approved on | NA | 6 | 0 | 2 | SCAG015 | Intersection Of 190th Street / Victoria Street And Figueroa Street | Install Left Turn Lanes, Upgrade Signal Hardware And Upgrade Aps At The | 3 | 2024-01-25 | 2024-01-26 | SCAG |  | negatie or zero funding | DTBPJMA2QFC8
Obligated | CML | 5006(874) | Los Angeles | 2024-02-16 | 2024-02-16 | 2024-02-16 | 2024-02-16 | 2024-02-23 | 0 | 0 | 0 | Authorized | 5006 | 07 | E-76 approved on | NA | 11 | 0 | 7 | LAF7636 | Broadway Streetscape Between 8th And 9th Street | Constructing Curb Extensions, Widen Walkways, Pedestrian Lighting, Street | 3 | 2024-02-05 | 2024-02-16 | SCAG |  |  | RNA2HUB4ZBK4
Obligated | HSIPL | 5351(037) | Pico Rivera | 2024-02-21 | 2024-02-21 | 2024-02-21 | 2024-02-21 | 2024-02-28 | 0 | 0 | 0 | Authorized | 5351 | 07 | E-76 approved on | NA | 6 | 0 | 7 | SCAG015 | 19 Intersections Along Beverly Blvd, Paramount Blvd, Rosemead Blvd, Slauson | Install 12" Led Lenses, Back Plates, Signal Timing/emergency Vehicle | 3 | 2024-02-15 | 2024-02-16 | SCAG |  |  | RBR1AK1KTAN9
Obligated | STPL | 5108(199) | Long Beach | 2024-02-04 | 2024-02-04 | 2024-02-06 | 2024-02-06 | 2024-02-13 | 0 | 0 | 0 | Authorized | 5108 | 07 | E-76 approved on | NA | 17 | 2 | 7 | LA0G830 | Project Is Located At The Terminus Of The I-710 Freeway In Long Beach, Ca. | Bridge Replacement | 3 | 2024-01-18 | 2024-02-04 | SCAG |  | negatie or zero funding | V4NMKFMJASD7
Obligated | ER | 15A6(008) | Los Angeles County | 2023-10-18 | 2024-02-07 | 2024-02-14 | 2024-03-19 | 2024-03-22 | 659207.66 | 0 | 744615 | Authorized | 5953 | 07 | E-76 approved on | NA | -7 | 41 | 3 | NA | 106th St E At Mm 24.90, Turnbleweed Rd At Mm 0.35, Big Pines Hwy At 700 Ft | Installation And Removal Of Temporary K-rails; Removal And Replacement Of | 3 | 2024-02-14 | 2024-02-14 | SCAG |  |  | ZLJUW5L9K685
Obligated | BHLS | 5204(018) | Glendora | 2023-07-17 | 2024-01-12 | 2024-01-19 | 2024-01-29 | 2024-02-02 | 220315 | 0 | 248859 | Authorized | 5204 | 07 | E-76 approved on | NA | 29 | 17 | 4 | LA000800 | Bridge No. 53c0780, Lone Hill Ave Over San Dimas Wash, 0.1 Mi N Foothill | Bridge Rehabilitation. | 4 | 2023-12-14 | 2024-01-11 | SCAG |  |  | KVBYLRZMAGJ9
Obligated | BRLSZD | 5006(831) | Los Angeles | 2024-02-13 | 2024-02-13 | 2024-02-13 | 2024-02-13 | 2024-02-21 | 0 | 0 | 0 | Authorized | 5006 | 07 | E-76 approved on | NA | 0 | 0 | 8 | LA0G104 | Sixth Street Viaduct Over La River, Us 101, And Uprr, Bnsf, Amtrack, Lacmta | This Is Cmgc Package #4 Is For Foundations | 4 | 2024-02-13 | 2024-02-13 | SCAG |  |  | RNA2HUB4ZBK4
Obligated | STPL | 6155(090) | Ventura County Transportation Commission | 2024-02-16 | 2024-02-23 | 2024-02-26 | 2024-02-26 | 2024-02-28 | -1735137.29 | 0 | -1735137.29 | Authorized | 6155 | 07 | E-76 approved on | NA | 29 | 3 | 2 | VEN131201 | In County Of Ventura, Route 101 Pm 4.1 At Moorpark Road In Thousand Oaks To | The Route 101 Widening (constructing Hov Lanes.project, Proposes To | 4 | 2024-01-25 | 2024-02-21 | SCAG |  |  | JEVVZV6ALEN5
Obligated | ACST-ER | 30L0(008) | Los Angeles County | 2024-02-20 | 2024-02-20 | 2024-02-20 | 2024-02-21 | 2024-02-28 | 2638925.42 | -2638925.42 | 0 | Authorized | 5953 | 07 | E-76 approved on | NA | 0 | 1 | 7 | NA | Lake Hughes Rd 235 Ft S/o & 565 Ft N/o Mm 2.47 | Raise Portion Of Roadway By 7', Construct 35' Long Slab Bridge & 510' Of | 4 | 2024-02-20 | 2024-02-20 | SCAG |  |  | ZLJUW5L9K685
Obligated | ER | 30X0(007) | Los Angeles County | 2024-02-20 | 2024-02-20 | 2024-02-20 | 2024-02-20 | 2024-02-28 | 0 | 0 | 0 | Authorized | 5953 | 07 | E-76 approved on | NA | 5 | 0 | 8 | NA | Soledad Canyon Road @ Mm 16.80 & 18.46 | Replaced Destroyed Boardwall With Rip Rap. | 4 | 2024-02-15 | 2024-02-16 | SCAG |  |  | ZLJUW5L9K685
Obligated | STPL | 5334(063) | Downey | 2024-01-31 | 2024-01-31 | 2024-01-31 | 2024-01-31 | 2024-02-06 | 0 | 0 | 0 | Authorized | 5334 | 07 | E-76 approved on | NA | 6 | 0 | 6 | LAF5114 | Telegraph Rd. Between Rio Hondo River And Lakewood Blvd./rosemead Blvd.; | Construction Of Raised Median Island; Asphalt Concrete Pavement | 4 | 2024-01-25 | 2024-01-26 | SCAG |  |  | JPBXF4648WA3
Obligated | DEM08L | 5362(024) | Commerce | 2024-02-29 | 2024-02-29 | 2024-03-06 | 2024-03-11 | 2024-03-19 | 0 | 0 | 27756 | Authorized | 5362 | 07 | E-76 approved on | NA | 0 | 11 | 8 | LA0G349 | Commerce Way Between Eastern Avenue And Washington Blvd | Pavement Reconstruction, Localized Curb, Gutter And Raised Median | 4 | 2024-02-29 | 2024-02-29 | SCAG |  |  | C1H2LGLYFD63
Obligated | STPLG | 5364(011) | La Mirada | 2024-01-29 | 2024-01-29 | 2024-02-06 | 2024-02-06 | 2024-02-14 | 0 | 0 | 21000 | Authorized | 5364 | 07 | E-76 approved on | NA | 6 | 8 | 8 | LA11G1 | Imperial Hwy From Valley View Avenue To Wicker Drive. | Road Rehabilitation (tc) | 4 | 2024-01-23 | 2024-01-29 | SCAG |  |  | ZGYKWN5D1BE7
Obligated | BHLS | 5405(077) | Simi Valley | 2024-02-14 | 2024-02-22 | 2024-02-28 | 2024-02-28 | 2024-03-05 | 710893.5 | 0 | 803000 | Authorized | 5405 | 07 | E-76 approved on | NA | 43 | 6 | 6 | VENLS07 | Madera Road At Uprr Bridge, 0.3 Miles South Of The State Route 118. Br | Repair Cracks And Spalls On Bridge Sidewalk, Overlay Deck With Polyester | 5 | 2024-01-10 | 2024-02-13 | SCAG |  |  | PNTGTKKJ37G1
Obligated | BRLSZD | 5006(815) | Los Angeles | 2024-02-13 | 2024-02-13 | 2024-02-13 | 2024-02-13 | 2024-02-21 | 0 | 0 | 0 | Authorized | 5006 | 07 | E-76 approved on | NA | 0 | 0 | 8 | LA0G104 | Sixth Street Viaduct Adjacent To New Bent 7 | Construction Of Test Pile: Package 3 | 5 | 2024-02-13 | 2024-02-13 | SCAG |  |  | RNA2HUB4ZBK4
Obligated | HP21L | 5257(036) | South Gate | 2024-02-04 | 2024-02-04 | 2024-02-04 | 2024-02-04 | 2024-02-08 | 0 | 0 | 0 | Authorized | 5257 | 07 | E-76 approved on | NA | 4 | 0 | 4 | LA996347 | The On-ramp From The Eastbound Of Firestone Blvd To The Southbound Of The I- | Reconstruction Of The Ramp In Accordance With Caltrans Requirements. | 5 | 2024-01-31 | 2024-02-04 | SCAG |  |  | WL7DME3FJSW4
Obligated | STPL | 5334(063) | Downey | 2024-02-14 | 2024-02-14 | 2024-02-14 | 2024-02-14 | 2024-02-21 | -105575.8 | 0 | -1069358.74 | Authorized | 5334 | 07 | E-76 approved on | NA | 6 | 0 | 7 | LAF5114 | Telegraph Rd. Between Rio Hondo River And Lakewood Blvd./rosemead Blvd.; | Construction Of Raised Median Island; Asphalt Concrete Pavement | 5 | 2024-02-08 | 2024-02-09 | SCAG |  |  | JPBXF4648WA3
Obligated | ATPL | 5262(008) | Signal Hill | 2024-02-02 | 2024-02-02 | 2024-02-02 | 2024-02-02 | 2024-02-06 | -103790.26 | 0 | 31264.5 | Authorized | 5262 | 07 | E-76 approved on | NA | 8 | 0 | 4 | LATP17S010 | Spring Street Between Atlantic Avenue To Junipero Avenue | The Project Will Install Approximately 2.0 Lane Miles Of Bike Lanes(class | 5 | 2024-01-25 | 2024-01-26 | SCAG |  |  | QVY8BN29VXF7
Obligated | BRLSZD | 5006(811) | Los Angeles | 2024-02-13 | 2024-02-13 | 2024-02-13 | 2024-02-13 | 2024-02-21 | 0 | 0 | 0 | Authorized | 5006 | 07 | E-76 approved on | NA | 0 | 0 | 8 | LA0G104 | Sixth Street Viaduct Over La River, Us 101, And Uprr, Bnsf, Amtrack, Lacmta | Cmgc Package #2 Is For The Viaduct Demolition | 7 | 2024-02-13 | 2024-02-13 | SCAG |  |  | RNA2HUB4ZBK4
Obligated | BRLSZD | 5006(839) | Los Angeles | 2024-03-05 | 2024-03-05 | 2024-03-05 | 2024-03-05 | 2024-03-07 | 0 | 0 | 0 | Authorized | 5006 | 07 | E-76 approved on | NA | 0 | 0 | 2 | LA0G104 | Sixth Street Viaduct Over La River, Us 101, And Uprr, Bnsf, Amtrack, Lacmta | Cmgc Package #5 Viaduct | 14 | 2024-03-05 | 2024-03-05 | SCAG |  |  | RNA2HUB4ZBK4
Obligated | BHLS | 5006(193) | Los Angeles | 2024-03-05 | 2024-03-05 | 2024-03-05 | 2024-03-05 | 2024-03-07 | 0 | 0 | 0 | Authorized | 5006 | 07 | E-76 approved on | NA | 0 | 0 | 2 | LA000800 | Soto St Bridge Over Valley Blvd & Uprr; Bridge #53c0011 | Bridge Rehabilitation | 14 | 2024-03-05 | 2024-03-05 | SCAG |  |  | RNA2HUB4ZBK4
Obligated | HSIPL | 5452(020) | Hesperia | 2024-01-22 | 2024-01-29 | 2024-02-20 | 2024-02-20 | 2024-02-28 | 899300 | 0 | 1215071 | Authorized | 5452 | 08 | E-76 approved on | NA | 29 | 22 | 8 | SCAG015 | Main Street And Sultana Street/timberlane Ave. | Installation Of Traffic Signal Left Turn Lanes, Ada Pedestrian Crossings, | 1 | 2023-12-31 | 2024-01-25 | SCAG |  |  | VG2NTKNJULY7
Obligated | BRLS | 5275(039) | Indio | 2024-03-05 | 2024-03-05 | 2024-03-11 | 2024-03-11 | 2024-03-19 | 308000 | 0 | 385000 | Authorized | 5275 | 08 | E-76 approved on | NA | 34 | 6 | 8 | RIV050201 | Bridge No. 56c0283, Sb Indio Blvd Over Up Rr & Amtrak, 0.3 Mi W/o Jefferson | Project Studies, Project Scoping Only. | 1 | 2024-01-31 | 2024-01-31 | SCAG |  |  | L852WV7G8PK5
Obligated | BRLS | 5275(040) | Indio | 2024-02-14 | 2024-03-04 | 2024-03-11 | 2024-03-11 | 2024-03-19 | 464000 | 0 | 580000 | Authorized | 5275 | 08 | E-76 approved on | NA | 19 | 7 | 8 | RIV050201 | Jackson Street Bridge Over Indio Blvd And Uprr Between Avenue 45 And Civic | To Prepare Psr To Correct The Bridge Deficiencies Listed In The Bridge | 1 | 2024-02-14 | 2024-02-14 | NON-MPO |  |  | L852WV7G8PK5
Obligated | BPMP | 5275(041) | Indio | 2024-02-14 | 2024-02-14 | 2024-02-22 | 2024-02-22 | 2024-02-28 | 400000 | 0 | 500000 | Authorized | 5275 | 08 | E-76 approved on | NA | 0 | 8 | 6 | RIV050201 | City Of Indio At Various Locations Within The City Limits. | Complete The Corrective Measures Identified In The Bridge Preventative | 1 | 2024-02-14 | 2024-02-14 | SCAG |  |  | L852WV7G8PK5
Obligated | ACSTP | 15Y0(026) | San Bernardino County | 2024-02-05 | 2024-02-13 | 2024-02-22 | 2024-03-19 | 2024-03-22 | 0 | 60018.91 | 67795 | Authorized | 5954 | 08 | E-76 approved on | NA | 13 | 35 | 3 | NA | Phelan Rd, At Sheep Creek At Sheep Creek (pm Length 100 Ft) | Remove Compromised Soils, Guardrails, Damaged Pavement Approaches And | 1 | 2024-01-31 | 2024-02-06 | SCAG |  |  | CFXEZ75TPJ84
Obligated | ACSTP | 15Y0(027) | San Bernardino County | 2024-02-05 | 2024-02-13 | 2024-02-22 | 2024-02-23 | 2024-02-28 | 0 | 8450 | 8450 | Authorized | 5954 | 08 | E-76 approved on | NA | 379 | 10 | 5 | NA | Oak Glen Rd Bridge Little San Gorgonio Creek (54c0673) | Remove Damaged Box Culvert Interior Walls,repair With Structural Concrete | 1 | 2023-01-30 | 2024-02-09 | SCAG |  |  | CFXEZ75TPJ84
Obligated | ACSTP | 15Y0(028) | San Bernardino County | 2024-02-05 | 2024-02-13 | 2024-02-22 | 2024-02-23 | 2024-02-28 | 0 | 7490 | 7490 | Authorized | 5954 | 08 | E-76 approved on | NA | 14 | 10 | 5 | NA | Waters Drive | Saw Cut And Remove Partial Roadway To Fix Pipe Failure, Backfill And | 1 | 2024-01-30 | 2024-02-09 | SCAG |  |  | CFXEZ75TPJ84
Obligated | ACSTP | 15Y0(030) | San Bernardino County | 2024-02-23 | 2024-02-23 | 2024-02-28 | 2024-03-19 | 2024-03-22 | 0 | 29263 | 29263 | Authorized | 5954 | 08 | E-76 approved on | NA | 10 | 25 | 3 | NA | Trona Rd Between Pinnacle Road And Marshall Street | Traffic Control; Remove Debris. Eroded Shoulder. Edge; Backfill Shoulders | 1 | 2024-02-13 | 2024-02-23 | SCAG |  |  | CFXEZ75TPJ84
Obligated | ACSTP | 15Y0(031) | San Bernardino County | 2024-02-23 | 2024-02-23 | 2024-02-28 | 2024-03-19 | 2024-03-22 | 0 | 7098 | 7098 | Authorized | 5954 | 08 | E-76 approved on | NA | 2 | 25 | 3 | NA | From Antelope Wash To 55616 Pipes Canyon Road | Traffic Control, Remove Debris/eroded Shoulder Edge; Backfill Shoulders For | 1 | 2024-02-21 | 2024-02-23 | SCAG |  |  | CFXEZ75TPJ84
Obligated | ATPSB1L | 5448(010) | Twentynine Palms | 2024-02-24 | 2024-02-24 | 2024-02-24 | 2024-02-25 | 2024-02-28 | 0 | 0 | 0 | Authorized | 5448 | 08 | E-76 approved on | NA | 16 | 1 | 3 | 20190701 | In The Neighborhoods Surrounding Oasis And Twentynine Palms Elementary | Sidewalk And Asphalt Paths, Curb Ramps, Crosswalks, Pedestrian Hybrid | 2 | 2024-02-08 | 2024-02-24 | SCAG |  |  | QGNKPTNL2822
Obligated | ATPSB1L | 5186(020) | Hemet | 2024-02-06 | 2024-02-20 | 2024-02-20 | 2024-02-20 | 2024-02-28 | -97996 | 0 | -97996 | Authorized | 5186 | 08 | E-76 approved on | NA | 14 | 0 | 8 | RIV181010 | At City Of Hemet, Palm Avenue, Whittier Avenue, Johnston Avenue, Gilbert | Public Outreach And Safety Campaign In Connection With The Installation Of | 2 | 2024-02-06 | 2024-02-06 | SCAG |  |  | DJBVYNK4LEK8
Obligated | BRLO | 5459(022) | Temecula | 2024-01-22 | 2024-02-06 | 2024-02-07 | 2024-02-08 | 2024-02-14 | 534389 | 0 | 782830.6 | Authorized | 5459 | 08 | E-76 approved on | NA | 62 | 2 | 6 | RIV050201 | Main Street Bridge Over Murrieta Creek, Br. No. 56c-0227 | Replace 2-lane Bridge (tc) | 3 | 2023-12-06 | 2023-12-06 | SCAG |  |  | F2GZFYJMPWG6
Obligated | SRTSL | 5457(019) | Yucaipa | 2024-03-25 | 2024-03-25 | 2024-03-25 | 2024-03-25 | 2024-03-27 | -65123.84 | 0 | -33646.79 | Authorized | 5457 | 08 | E-76 approved on | NA | 4 | 0 | 2 | SCAG016 | 12th Street From Avenue "e" To Kentucky Street, 13th Street From Avenue "e" | Construct Sidewalks, Curb Ramps, Section Of Multi-use Path; And Install | 3 | 2024-03-21 | 2024-03-22 | SCAG |  |  | QVUWF3WJ3QF8
Obligated | BRLS | 5956(231) | Riverside County | 2024-01-26 | 2024-01-30 | 2024-02-08 | 2024-02-08 | 2024-02-14 | 0 | 531180 | 836610 | Authorized | 5956 | 08 | E-76 approved on | NA | 14 | 9 | 6 | RIV121203 | Airport Boulevard Over Whitewater River, Br. No. 56c-0020 | Replace Existing 2-lane Bridge | 3 | 2024-01-16 | 2024-01-26 | SCAG |  |  | TVFUYL55FE88
Obligated | STPL | 5104(046) | Corona | 2024-02-27 | 2024-02-27 | 2024-03-01 | 2024-03-01 | 2024-03-04 | 0 | 0 | 0 | Authorized | 5104 | 08 | E-76 approved on | NA | 6 | 3 | 3 | RIV160405 | Magnolia Avenue Over Temescal Wash From El Camino Avenue To 1,000 Feet East | Widen Bridge From 4 To 6 Lanes | 3 | 2024-02-21 | 2024-02-29 | SCAG |  |  | JCVFXGCJ8BK8
Obligated | ER | 40A0(072) | Indio | 2024-03-11 | 2024-03-11 | 2024-03-11 | 2024-03-11 | 2024-03-19 | -51045.21 | 0 | -57658.72 | Authorized | 5275 | 08 | E-76 approved on | NA | 4 | 0 | 8 | NA | Avenue 44 At Cv Stormwater Channel | Emergency Opening And Restoration Repair And Grout Road Section | 3 | 2024-03-07 | 2024-03-08 | SCAG |  |  | L852WV7G8PK5
Obligated | STBGSB1L | 6054(101) | Riverside County Transportation Commission | 2024-02-23 | 2024-02-23 | 2024-02-24 | 2024-02-24 | 2024-02-28 | 0 | 0 | 0 | Authorized | 6054 | 08 | E-76 approved on | NA | 16 | 1 | 4 | RIV031218B | Mid County Parkway (mcp) Phase 2 From Redlands Avenue And The Future | New Road (3-4 Lanes, 1-2 Wb Lns & 2 Eb Lns) | 3 | 2024-02-07 | 2024-02-24 | SCAG |  |  | JFE1DR73YB29
Obligated | PLHDL08 | 5954(145) | San Bernardino County | 2024-02-27 | 2024-02-28 | 2024-03-04 | 2024-03-04 | 2024-03-05 | -134399.92 | 0 | -134399.92 | Authorized | 5954 | 08 | E-76 approved on | NA | 1 | 5 | 1 | 20152202 | Needles Highway Segment 1b: 500' South Of Park Road To 1 Mile North | Roadway Improvements | 4 | 2024-02-27 | 2024-02-28 | SCAG |  |  | CFXEZ75TPJ84
Obligated | HSIPLN | 5282(047) | Palm Springs | 2024-02-16 | 2024-02-16 | 2024-02-26 | 2024-02-26 | 2024-02-28 | 0 | 0 | 0 | Authorized | 5282 | 08 | E-76 approved on | NA | 23 | 10 | 2 | SCAG015 | 14 Intersections Throughout The City Of Palm Springs | Modify Traffic Signals For Improved Visibility, Advanced Dilemma Zone | 4 | 2024-01-24 | 2024-01-24 | SCAG |  |  | M81QLC23JVX5
Obligated | FERPL16 | 5065(028) | Colton | 2024-02-23 | 2024-02-23 | 2024-02-23 | 2024-02-23 | 2024-02-28 | 0 | 0 | 0 | Authorized | 5065 | 08 | E-76 approved on | NA | 18 | 0 | 5 | 20170805 | Reche Canyon Road From 0.4 Miles South Of Washington Street North To The | Four-lane Roadway Realignment (tc) | 4 | 2024-02-05 | 2024-02-23 | SCAG |  |  | YFRKFKNGWKW3
Obligated | HSIPL | 5380(038) | Victorville | 2024-02-28 | 2024-02-28 | 2024-02-28 | 2024-02-28 | 2024-03-04 | -164670.5 | 0 | -164670.5 | Authorized | 5380 | 08 | E-76 approved on | NA | 6 | 0 | 5 | SCAG015 | Various Locations Throughout The City Along Major Roadways: National Trails | Upgrade Existing Guardrails And Terminal System End Treatments To Meet | 4 | 2024-02-22 | 2024-02-23 | SCAG |  |  | SB1RGMJ5U1M7
Obligated | HSIPL | 5448(009) | Twentynine Palms | 2024-02-04 | 2024-02-04 | 2024-02-04 | 2024-02-04 | 2024-02-08 | 0 | 0 | 0 | Authorized | 5448 | 08 | E-76 approved on | NA | 17 | 0 | 4 | SCAG015 | High-speed Rural Residential Areas Bordered By Two Mile Road On The North, | Upgrade Intersection Pavement Markings And Install Advance Warning Flashing | 4 | 2024-01-18 | 2024-02-04 | SCAG |  |  | QGNKPTNL2822
Obligated | BRLS | 6507(027) | San Bernardino County Transportation Authority | 2024-03-06 | 2024-03-06 | 2024-03-06 | 2024-03-06 | 2024-03-07 | 0 | 0 | 0 | Authorized | 6507 | 08 | E-76 approved on | NA | 0 | 0 | 1 | SBDLS08 | N 1st Avenue Over Bnsf Ry, Up Rr, Amtrak, 0.2 Mi N Main St In Barstow, Br. | Replace Existing 2 Lane Bridge With 2 Lane Bridge, Existing Bridge To Be | 4 | 2024-03-06 | 2024-03-06 | SCAG |  |  | D36ZJBWRKJK1
Obligated | BR | NBIL(506) | YUCAIPA | 2024-02-04 | 2024-02-04 | 2024-02-04 | 2024-02-04 | 2024-02-08 | 0 | 0 | 0 | Authorized | 5457 | 08 | E-76 approved on | NA | 26 | 0 | 4 | SBDLS08 | Pendleton Avenue Over Oak Glen Creek, Lwc # 00l0034 | Replace Low Water Crossing With 2-lane Bridge | 4 | 2024-01-09 | 2024-02-04 | SCAG |  |  | QVUWF3WJ3QF8
Obligated | ATPL | 5033(053) | San Bernardino | 2024-03-14 | 2024-03-14 | 2024-03-14 | 2024-03-14 | 2024-03-19 | -143396.07 | 0 | -143396.07 | Authorized | 5033 | 08 | E-76 approved on | NA | 7 | 0 | 5 | 20151502 | Intersections Of Pepper Avenue And Randall Avenue, 48th Street Aand Western | Curb And Gutter, Sidewalk, Ada-compliant Curb Ramps, Crosswalk Striping, And | 5 | 2024-03-07 | 2024-03-08 | SCAG |  |  | EJLMHR1CMKM7
Obligated | ATPL | 5441(069) | Moreno Valley | 2021-10-25 | 2024-01-16 | 2024-01-26 | 2024-02-05 | 2024-02-08 | 0 | 0 | 0 | Authorized | 5441 | 08 | E-76 approved on | NA | 830 | 20 | 3 | RIV160402 | Juan Bautista De Anza Historic Corridor From El Potrero Park To Iris Avenue | Construct Segment Of Multi-use Trail (tc) | 5 | 2021-10-08 | 2022-02-24 | SCAG |  |  | LJ4AVJ6C8NW5
Obligated | HSIPL | 5282(048) | Palm Springs | 2024-02-08 | 2024-02-08 | 2024-02-08 | 2024-02-08 | 2024-02-12 | 0 | 0 | -5087.25 | Authorized | 5282 | 08 | E-76 approved on | NA | 7 | 0 | 4 | SCAG015 | Gene Autry Trail From Salvia Road To 1,600 Feet South Of Salvia Road | Install Flashing Beacon And Delineators | 5 | 2024-02-01 | 2024-02-02 | SCAG |  |  | M81QLC23JVX5
Obligated | BHLS | 5275(017) | Indio | 2023-12-13 | 2024-02-28 | 2024-03-14 | 2024-03-14 | 2024-03-19 | 28706 | 0 | 32425 | Authorized | 5275 | 08 | E-76 approved on | NA | 93 | 15 | 5 | RIV050201 | Eastbound Indio Blvd Over Whitewater River Bridge, Br # 56c-0293 | Construct Scour Countermeasures | 5 | 2023-11-27 | 2024-02-07 | SCAG |  |  | L852WV7G8PK5
Obligated | BR | NBIL(514) | RANCHO MIRAGE | 2023-11-29 | 2023-11-29 | 2023-12-05 | 2024-02-15 | 2024-02-22 | -771125.2 | 0 | -871032.64 | Authorized | 5412 | 08 | E-76 approved on | NA | -71 | 78 | 7 | RIV050201 | Frank Sinatra Drive Across The Whitewater River, Lwc #00l0046 | Replace 4-lane Low Water Crossing With 4-lane Bridge | 6 | 2024-02-08 | 2024-02-09 | SCAG |  |  | EKCCGNXJK275
Obligated | BRLKS | 5275(024) | Indio | 2024-02-21 | 2024-02-22 | 2024-02-29 | 2024-02-29 | 2024-03-05 | 11581384 | -11581384 | 78385 | Authorized | 5275 | 08 | E-76 approved on | NA | 24 | 7 | 5 | RIV111202 | Avenue 44 Over The Coachella Valley Storm Channel, Lwc 00l0056 | Replace Low Water Crossing With A Four-lane Bridge | 6 | 2024-01-29 | 2024-02-21 | SCAG |  |  | L852WV7G8PK5
Obligated | BRLS | 5282(042) | Palm Springs | 2024-02-16 | 2024-02-21 | 2024-03-01 | 2024-03-01 | 2024-03-05 | 7203686 | 0 | 10536321 | Authorized | 5282 | 08 | E-76 approved on | NA | 27 | 9 | 4 | RIV050201 | South Palm Canyon Drive Over Tahquitz Creek, Br. No. 56c-0408 | Replace 4-lane Bridge | 6 | 2024-01-25 | 2024-02-16 | SCAG |  |  | M81QLC23JVX5
Obligated | BR | NBIL(533) | TWENTYNINE PALM | 2023-04-03 | 2024-01-23 | 2024-01-23 | 2024-01-29 | 2024-02-02 | 3263880 | 0 | 8363667 | Authorized | 5448 | 08 | E-76 approved on | NA | 299 | 6 | 4 | SBDLS08 | Split Rock Avenue Over The Twentynine Palms Flood Control Channel, Lwc | Replace Low-water Crossing With Two-lane Bridge | 6 | 2023-03-30 | 2023-12-19 | SCAG |  |  | QGNKPTNL2822
Obligated | PNRSL | 5104(033) | Corona | 2024-02-21 | 2024-02-21 | 2024-02-21 | 2024-02-21 | 2024-02-28 | 0 | 0 | 0 | Authorized | 5104 | 08 | E-76 approved on | NA | 6 | 0 | 7 | RIV011241 | Auto Center Drive At Bnsf Railroad South Of Railroad Street | New Overhead | 6 | 2024-02-15 | 2024-02-16 | SCAG |  |  | JCVFXGCJ8BK8
Obligated | DEM05UBL | 5380(028) | Victorville | 2024-02-20 | 2024-02-20 | 2024-02-20 | 2024-02-21 | 2024-02-28 | 0 | 0 | 0 | Authorized | 5380 | 08 | E-76 approved on | NA | 15 | 1 | 7 | SBD97147 | Green Tree Boulevard From Hesperia Road To Ridgecrest Boulevard | Extension Of 4-lane Road With New Overhead | 7 | 2024-02-05 | 2024-02-20 | SCAG |  |  | SB1RGMJ5U1M7
Obligated | ACSTP | 15J9(159) | Inyo County | 2023-09-20 | 2024-02-07 | 2024-02-13 | 2024-02-22 | 2024-02-27 | 0 | 529751 | 529751 | Authorized | 5948 | 09 | E-76 approved on | NA | 140 | 15 | 5 | NA | On Pine Creek Rd, From Pine Creek Pass Trailhead To Approximately 2.2 Miles | Agency Forces Set Up Traffic Control And Reinforced Berm. Emergency | 1 | 2023-09-20 | 2024-02-01 | NON-MPO |  |  | EU9KBPLKZ5K5
Obligated | STPL | 5399(033) | California City | 2024-01-22 | 2024-01-22 | 2024-01-30 | 2024-01-30 | 2024-02-01 | 313078 | 0 | 744757 | Authorized | 5399 | 09 | E-76 approved on | NA | 3 | 8 | 2 | KER180403 | On Hacienda Blvd. From Manzanita Ave. To Redwood Blvd., In The City Of | Pavement Rehabilitation, Install Curb & Gutters, Sidewalks And Ada Curb | 2 | 2024-01-19 | 2024-01-22 | KCOG |  |  | L2GLQ2NMLST9
Obligated | ACST-ER | 15J9(039) | Inyo County | 2024-02-07 | 2024-02-07 | 2024-02-20 | 2024-03-20 | 2024-03-27 | 0 | 1325825 | 1325825 | Authorized | 5948 | 09 | E-76 approved on | NA | 0 | 42 | 7 | NA | In Inyo County, On Whitney Portal Rd., Between Tuttle Creek Rd. Intersection | Emergency Opening Work That Included Some Agency Force Force Account And | 3 | 2024-02-07 | 2024-02-07 | NON-MPO |  |  | EU9KBPLKZ5K5
Obligated | CML | 5184(038) | Tehachapi | 2024-02-05 | 2024-02-05 | 2024-02-05 | 2024-02-05 | 2024-02-08 | -174491.13 | 0 | -196835.6 | Authorized | 5184 | 09 | E-76 approved on | NA | 4 | 0 | 3 | KER200505 | Pinon Street From Brandon Lane East To Dennison Road | Pave An Unpaved Portion Of Road And Install A Class Ii Bike Lane. | 4 | 2024-02-01 | 2024-02-02 | KCOG |  |  | FWZLF5N9FP79
Obligated | STPL | 5153(046) | Oakdale | 2023-12-24 | 2024-02-25 | 2024-03-05 | 2024-03-19 | 2024-03-25 | 285308 | 0 | 322273 | Authorized | 5153 | 10 | E-76 approved on | NA | 67 | 23 | 6 | VA02 | In City Of Oakdale, On D Street From 5th To Johnson, On E Street From Sierra | Pavement Maintenance, New Pavement Markings, And Various Concrete Repairs | 1 | 2023-12-20 | 2024-02-25 | STANCOG |  |  | JG74WUADUKE8
Obligated | BPMP | 5938(278) | Stanislaus County | 2024-01-19 | 2024-02-15 | 2024-02-20 | 2024-03-07 | 2024-03-11 | 660000 | 0 | 825000 | Authorized | 5938 | 10 | E-76 approved on | NA | 48 | 21 | 4 | STANCOG | Bridges: 38c0020; 38c0177; 38c0184 | Bridge Preventive Maintenance (scour Repairs) | 1 | 2023-12-29 | 2024-02-09 | STANCOG |  |  | JVUBT686JGX7
Obligated | STPHIPL | 6088(085) | San Joaquin Council of Governments | 2024-01-23 | 2024-01-24 | 2024-02-01 | 2024-02-09 | 2024-02-12 | 1330162 | 0 | 62170152 | Authorized | 6088 | 10 | E-76 approved on | NA | NA | 16 | 3 | SJ14-1004 | Sr 99/120 Connector Project Phase 1a. San Joaquin County. Route: 99 Pm | Widen The Eastbound Sr 120 To Southbound Sr 99 Connector Ramp From One-lane | 1 | NA | NA | SJCOG |  |  | U377E1A7TU27
Obligated | BPMPL | 5940(123) | Mariposa County | 2024-01-18 | 2024-03-18 | 2024-03-19 | 2024-03-19 | 2024-03-25 | -40124.73 | 0 | -45323.32 | Authorized | 5940 | 10 | E-76 approved on | NA | 166 | 1 | 6 | HBPLOCAL | Mariposa County - Multiple Locations (14 Total Bridges): 40c0003; 40c0010; | Bpmp For 14 Bridges In Mariposa County. Scoping Performed Under Federal | 2 | 2023-10-04 | 2024-01-29 | NON-MPO |  |  | L63AEQY86BZ4
Obligated | CML | 5008(193) | Stockton | 2024-03-22 | 2024-03-22 | 2024-03-22 | 2024-03-22 | 2024-03-27 | 0 | 0 | 0 | Authorized | 5008 | 10 | E-76 approved on | NA | 2 | 0 | 5 | SJ18-9013 | In Stockton, Intersection At Alpine Avenue And Alvarado Avenue | The Proposed Project Will Install A 3-way Traffic Signal At The Intersection | 2 | 2024-03-20 | 2024-03-22 | SJCOG |  |  | YV3KNQAKJLQ7
Obligated | STPL | 5153(044) | Oakdale | 2024-03-18 | 2024-03-18 | 2024-03-18 | 2024-03-18 | 2024-03-19 | 0 | 0 | 500 | Authorized | 5153 | 10 | E-76 approved on | NA | 4 | 0 | 1 | VA02 | J Street From West Of Sierra Avenue To South Fifth Avenue | Project Includes Removal And Replacement Of Existing Pavement, Replacement | 2 | 2024-03-14 | 2024-03-15 | STANCOG |  |  | JG74WUADUKE8
Obligated | BRLO | 5940(121) | Mariposa County | 2024-02-13 | 2024-02-13 | 2024-02-13 | 2024-02-13 | 2024-02-21 | 0 | 0 | 0 | Authorized | 5940 | 10 | E-76 approved on | NA | 5 | 0 | 8 | HBP-MPA | Foresta Road Over Crane Creek (bridge 40c0054) | Bridge Replacement (tc) | 3 | 2024-02-08 | 2024-02-09 | NON-MPO |  |  | L63AEQY86BZ4
Obligated | BRLO | 5940(122) | Mariposa County | 2024-02-20 | 2024-02-20 | 2024-02-20 | 2024-02-20 | 2024-02-23 | 0 | 0 | 0 | Authorized | 5940 | 10 | E-76 approved on | NA | 5 | 0 | 3 | HBP-MPA | Foresta Road Over Crane Creek (bridge 40c0055) | Bridge Replacement (tc) | 3 | 2024-02-15 | 2024-02-16 | NON-MPO |  |  | L63AEQY86BZ4
Obligated | CML | 5255(054) | Riverbank | 2024-03-22 | 2024-03-22 | 2024-03-23 | 2024-03-23 | 2024-03-27 | 0 | 0 | 0 | Authorized | 5255 | 10 | E-76 approved on | NA | 50 | 1 | 4 | VA03 | East Side Of Roselle Avenue Between Patterson Road And Pocket Avenue | Construct Sidewalk And Install Ada Ramps | 3 | 2024-02-01 | 2024-03-23 | STANCOG |  |  | F9C4G4WCLCM6
Obligated | STPL | 5929(300) | San Joaquin County | 2024-02-20 | 2024-02-20 | 2024-02-20 | 2024-02-20 | 2024-02-23 | 0 | 0 | 0 | Authorized | 5929 | 10 | E-76 approved on | NA | 5 | 0 | 3 | SJ07-3071 | West Ripon Road From Austin Road To Ripon City Limits | Resurface With 0.25' Hma Over Geosynthetic Pavement Interlayer (tc) | 3 | 2024-02-15 | 2024-02-16 | SJCOG |  |  | L3XZK6UCWTF3
Obligated | CMLNI | 6095(077) | Merced County Association of Governments | 2024-01-29 | 2024-01-29 | 2024-01-29 | 2024-01-29 | 2024-02-01 | 0 | 0 | 0 | Authorized | 6095 | 10 | E-76 approved on | NA | 4 | 0 | 3 | CMAQ17-10 | Merced County | Vanpool Program (tc) | 3 | 2024-01-25 | 2024-01-26 | MCAG |  |  | G9LMKWZEL2K3
Obligated | BDGL | 5938(265) | Stanislaus County | 2024-02-14 | 2024-02-14 | 2024-02-14 | 2024-02-15 | 2024-02-27 | 0 | 0 | 0 | Authorized | 5938 | 10 | E-76 approved on | NA | 21 | 1 | 12 | NCC01 | North County Corridor From Tully Road To State Route 120/108 (ultimate | Construct 2-6 Lanes Expressway (ultimate Build-out) - Phase 1 > Constructs 4 | 3 | 2024-01-24 | 2024-02-14 | STANCOG |  |  | JVUBT686JGX7
Obligated | STPL | 5165(098) | Turlock | 2024-02-02 | 2024-02-02 | 2024-02-02 | 2024-02-02 | 2024-02-05 | 0 | 0 | 0 | Authorized | 5165 | 10 | E-76 approved on | NA | 8 | 0 | 3 | VA02 | Hedstrom Road Between Geer Road And Colorado Avenue. | Road Rehabilitation. The Scope Of Work Includes Grinding Existing Pavement | 3 | 2024-01-25 | 2024-01-26 | STANCOG |  |  | JDYXAB12QLG1
Obligated | BRLS | 5938(200) | Stanislaus County | 2024-02-16 | 2024-02-16 | 2024-02-20 | 2024-02-20 | 2024-02-23 | 0 | 0 | 0 | Authorized | 5938 | 10 | E-76 approved on | NA | 17 | 4 | 3 | STANCOG | Las Palmas Avenue Over San Joaquin River (bridge 38c0033) | Bridge Preventive Maintenance | 4 | 2024-01-30 | 2024-02-20 | STANCOG |  |  | JVUBT686JGX7
Obligated | BRLO | 5940(122) | Mariposa County | 2024-03-21 | 2024-03-21 | 2024-03-21 | 2024-03-21 | 2024-03-27 | 0 | 0 | 0 | Authorized | 5940 | 10 | E-76 approved on | NA | 7 | 0 | 6 | HBP-MPA | Foresta Road Over Crane Creek (bridge 40c0055) | Bridge Replacement (tc) | 4 | 2024-03-14 | 2024-03-15 | NON-MPO |  |  | L63AEQY86BZ4
Obligated | STPL | 5938(233) | Stanislaus County | 2024-02-09 | 2024-02-09 | 2024-02-14 | 2024-02-15 | 2024-02-23 | 0 | 0 | 0 | Authorized | 5938 | 10 | E-76 approved on | NA | 16 | 6 | 8 | 98STA0141 | Mchenry Ave - Ladd Rd/patterson Rd To Stanislaus River | Widen 2 To 4 Lanes - 2 Way Left Turn Lanes (tc) | 4 | 2024-01-24 | 2024-02-13 | STANCOG |  |  | JVUBT686JGX7
Obligated | STPL | 5929(300) | San Joaquin County | 2024-03-20 | 2024-03-20 | 2024-03-20 | 2024-03-20 | 2024-03-25 | -27863.92 | 0 | -27863.92 | Authorized | 5929 | 10 | E-76 approved on | NA | 6 | 0 | 5 | SJ07-3071 | West Ripon Road From Austin Road To Ripon City Limits | Resurface With 0.25' Hma Over Geosynthetic Pavement Interlayer (tc) | 4 | 2024-03-14 | 2024-03-15 | SJCOG |  |  | L3XZK6UCWTF3
Obligated | CML | 5085(048) | Merced | 2024-02-01 | 2024-02-01 | 2024-02-09 | 2024-02-20 | 2024-02-23 | 0 | 0 | -1385 | Authorized | 5085 | 10 | E-76 approved on | NA | 21 | 19 | 3 | CMAQ17-4 | 1. I St From South Of W 25th St To W 28th St, 2. Martin Luther King Jr. Way | Construct Pedestrian Improvements Near John Muir School | 4 | 2024-01-11 | 2024-01-31 | MCAG |  |  | L6YVDNJHHSQ7
Obligated | HSIP | 5008(184) | Stockton | 2024-03-20 | 2024-03-20 | 2024-03-22 | 2024-03-22 | 2024-03-27 | 0 | 0 | 0 | Authorized | 5008 | 10 | E-76 approved on | NA | 1 | 2 | 5 | SJ07-3116 | In The City Of Stockton, Airport Way And Hazelton Avenue. | Add Designated Left-turn Lanes To The Intersection Of Airport Way/hazelton | 4 | 2024-03-19 | 2024-03-22 | SJCOG |  |  | YV3KNQAKJLQ7
Obligated | STPL | 5165(098) | Turlock | 2024-02-26 | 2024-02-26 | 2024-02-26 | 2024-02-26 | 2024-02-27 | 0 | 0 | -0.43 | Authorized | 5165 | 10 | E-76 approved on | NA | 4 | 0 | 1 | VA02 | Hedstrom Road Between Geer Road And Colorado Avenue. | Road Rehabilitation. The Scope Of Work Includes Grinding Existing Pavement | 4 | 2024-02-22 | 2024-02-23 | STANCOG |  |  | JDYXAB12QLG1
Obligated | BRLS | 5929(229) | San Joaquin County | 2024-01-19 | 2024-01-26 | 2024-02-01 | 2024-02-21 | 2024-02-23 | 1924336 | -1924336 | 0 | Authorized | 5929 | 10 | E-76 approved on | NA | 17 | 26 | 2 | SJ07-3002 | Bridge Locations: (29c0022; 29c0108; 29c0114; 29c0219) | Preventive Maintenance On Multiple Movable Bridges | 5 | 2024-01-09 | 2024-01-25 | SJCOG |  |  | L3XZK6UCWTF3
Obligated | BRLO | 5938(193) | Stanislaus County | 2024-02-09 | 2024-02-09 | 2024-02-15 | 2024-02-15 | 2024-02-23 | 0 | 0 | 0 | Authorized | 5938 | 10 | E-76 approved on | NA | 16 | 6 | 8 | STANCOG | St. Francis Road Over Modesto Irrigation District (mid) Main Canal (br | Bridge Replacement (tc) | 5 | 2024-01-24 | 2024-02-14 | STANCOG |  |  | JVUBT686JGX7
Obligated | BRLO | 5939(092) | Merced County | 2023-12-15 | 2024-02-01 | 2024-02-09 | 2024-02-29 | 2024-03-11 | 4825000 | 0 | 4825000 | Authorized | 5939 | 10 | E-76 approved on | NA | 71 | 28 | 11 | CT004 | Kibby Road Over Bear Creek (bridge 39c0350) | Bridge Replacement (tc) | 5 | 2023-11-22 | 2024-02-26 | MCAG |  |  | NJDZPHTGSUQ6
Obligated | BPMPL | 5929(261) | San Joaquin County | 2024-01-11 | 2024-03-07 | 2024-03-22 | 2024-03-22 | 2024-03-27 | 122171 | 0 | 138000 | Authorized | 5929 | 10 | E-76 approved on | NA | 84 | 15 | 5 | SJ07-3002 | Fine Road Over Channel B (bridge 29c0228) | Bridge Preventive Maintenance | 5 | 2023-12-14 | 2024-02-13 | SJCOG |  |  | L3XZK6UCWTF3
Obligated | CML | 5206(013) | Angels | 2023-12-13 | 2023-12-13 | 2024-02-29 | 2024-02-29 | 2024-03-11 | 0 | 0 | 54864.27 | Authorized | 5206 | 10 | E-76 approved on | NA | 13 | 78 | 11 | MURPHY | Murphy/rte49 Grade Rd/demarest Intersection, And Along Murphy Road. | Sidewalk And Intersection Improvement (tc) | 5 | 2023-11-30 | 2023-12-13 | NON-MPO |  |  | MWNNJ9HYQPV4
Obligated | HRRRL | 5932(090) | Tuolumne County | 2024-02-01 | 2024-02-01 | 2024-02-01 | 2024-02-26 | 2024-02-27 | -60178.53 | 0 | -53692.98 | Authorized | 5932 | 10 | E-76 approved on | NA | -21 | 25 | 1 | HSIP_RURL | Various Locations In Tuolumne County | Roadway Safety Signing Audit (rssa). Signing Upgrade And Roadway Safety | 5 | 2024-02-22 | 2024-02-23 | NON-MPO |  |  | NZ5KFMZLPMB9
Obligated | CMLNI | 6088(081) | San Joaquin Council of Governments | 2024-02-27 | 2024-02-27 | 2024-03-11 | 2024-03-20 | 2024-03-27 | 160000 | 0 | 160000 | Authorized | 6088 | 10 | E-76 approved on | NA | 12 | 22 | 7 | SJ11-9009 | Travel Demand Management Program (throughout San Joaquin And Merced | Conduct Ridesharing Activities Throughout San Joaquin And Merced Counties. | 5 | 2024-02-15 | 2024-02-16 | SJCOG |  |  | U377E1A7TU27
Obligated | BRLO | 5930(067) | Calaveras County | 2023-07-21 | 2023-12-20 | 2024-01-12 | 2024-03-20 | 2024-03-27 | -384049.39 | 0 | -383186.29 | Authorized | 5930 | 10 | E-76 approved on | NA | 152 | 91 | 7 | HBPLOCAL | Schadd Road Over Forest Creek (bridge 30c0084) | Bridge Replacement (tc) | 6 | 2023-07-21 | 2024-02-28 | NON-MPO |  |  | C5DPBGSMB5J9
Obligated | BRLO | 5141(015) | Jackson | 2024-01-25 | 2024-01-25 | 2024-02-01 | 2024-02-21 | 2024-02-23 | 0 | 0 | 0 | Authorized | 5141 | 10 | E-76 approved on | NA | 0 | 27 | 2 | HBPLOCAL | French Bar Road Over Sf Jackson Creek (bridge 26c0035) | Bridge Replacement (tc) | 7 | 2024-01-25 | 2024-01-25 | NON-MPO |  |  | ERQKLDCSKQ78
Obligated | BRLO | 5141(018) | Jackson | 2024-02-02 | 2024-02-26 | 2024-03-06 | 2024-03-12 | 2024-03-19 | 60000 | 0 | 60000 | Authorized | 5141 | 10 | E-76 approved on | NA | 32 | 15 | 7 | HBPLOCAL | Pitt Street Over Middle Fork Jackson Creek (bridge 26c0008) | Bridge Replacement (tc) | 7 | 2024-01-25 | 2024-02-26 | NON-MPO |  |  | ERQKLDCSKQ78
Obligated | BRLO | 5929(235) | San Joaquin County | 2024-02-05 | 2024-02-05 | 2024-02-05 | 2024-02-05 | 2024-02-08 | 0 | 0 | 0 | Authorized | 5929 | 10 | E-76 approved on | NA | 4 | 0 | 3 | SJ07-3002 | Wimer Road Over Indian Creek North Branch (bridge 29c0303) | Bridge Replacement (tc) | 8 | 2024-02-01 | 2024-02-02 | SJCOG |  |  | L3XZK6UCWTF3
Obligated | BRLO | 5939(083) | Merced County | 2023-12-29 | 2024-01-05 | 2024-01-12 | 2024-02-12 | 2024-02-21 | -164441.11 | 0 | -164441.11 | Authorized | 5939 | 10 | E-76 approved on | NA | 7 | 38 | 9 | CT004 | Los Cerritos Road Over Dry Creek (bridge 39c0225) | Bridge Replacement (tc) | 8 | 2023-12-29 | 2024-02-07 | MCAG |  |  | NJDZPHTGSUQ6
Obligated | BRLO | 5929(235) | San Joaquin County | 2024-02-26 | 2024-02-26 | 2024-02-26 | 2024-03-05 | 2024-03-11 | -577947.56 | 0 | 0 | Authorized | 5929 | 10 | E-76 approved on | NA | -3 | 8 | 6 | SJ07-3002 | Wimer Road Over Indian Creek North Branch (bridge 29c0303) | Bridge Replacement (tc) | 9 | 2024-02-29 | 2024-03-01 | SJCOG |  |  | L3XZK6UCWTF3
Obligated | STPBIPL | 6066(154) | San Diego Association of Governments | 2024-02-26 | 2024-02-26 | 2024-02-26 | 2024-02-26 | 2024-02-27 | -694.4 | 0 | -694.4 | Authorized | 6066 | 11 | E-76 approved on | NA | 4 | 0 | 1 | SAN267 | In San Diego And Tijuana At The San Ysidro And Otay Mesa Ports Of Entry | Develop And Install A Northbound Border Wait Time Data Collection System To | 2 | 2024-02-22 | 2024-02-23 | SANDAG |  |  | CU82DUZEEL81
Obligated | STPBIPL | 6066(155) | San Diego Association of Governments | 2024-02-21 | 2024-02-21 | 2024-02-21 | 2024-02-21 | 2024-02-26 | 0 | 0 | 0 | Authorized | 6066 | 11 | E-76 approved on | NA | 6 | 0 | 5 | V11 | In San Diego County And Mexico - On New Alignment From Sr-125 To The Us- | Develop An Investment Grade Traffic Revenue Study For The Sr-11/otay Mesa | 2 | 2024-02-15 | 2024-02-16 | SANDAG |  |  | CU82DUZEEL81
Obligated | ATPL | 5066(025) | National City | 2024-01-30 | 2024-01-30 | 2024-01-30 | 2024-01-30 | 2024-02-01 | -353427.07 | 0 | -395529.07 | Authorized | 5066 | 11 | E-76 approved on | NA | 5 | 0 | 2 | V14 / CAL386 | Various Street Locations Near Schools In National City | Srts Ped Enhancements (tc) | 4 | 2024-01-25 | 2024-01-26 | SANDAG |  |  | DWSKT6H5J5F3
Obligated | HSIPL | 5066(041) | National City | 2024-01-17 | 2024-02-08 | 2024-03-19 | 2024-03-20 | 2024-03-26 | 1201590 | 0 | 1492200 | Authorized | 5066 | 11 | E-76 approved on | NA | 42 | 41 | 6 | CAL105 / | Signalized At The Following Corridors: 8th Street, 18th Street, D Avenue, | Upgrade Existing Permissive Left-turn Phases And Signal Heads With Protected | 4 | 2023-12-28 | 2024-03-18 | SANDAG |  |  | DWSKT6H5J5F3
Obligated | STPL | 6066(174) | San Diego Association of Governments | 2024-02-13 | 2024-02-13 | 2024-02-13 | 2024-02-13 | 2024-02-21 | 0 | 0 | 0 | Authorized | 6066 | 11 | E-76 approved on | NA | 5 | 0 | 8 | CAL550 | In San Diego County Along Sr-52 From 1-5 To Sr-67 And Along Sr-67 From I-8 | This Is A Comprehensive Integrated Management Plan For Increasing | 4 | 2024-02-08 | 2024-02-09 | SANDAG |  |  | CU82DUZEEL81
Obligated | CMLG | 6066(180) | San Diego Association of Governments | 2024-03-04 | 2024-03-04 | 2024-03-19 | 2024-03-19 | 2024-03-22 | 13500000 | 0 | 13500000 | Authorized | 6066 | 11 | E-76 approved on | NA | 3 | 15 | 3 | SAN11A | Various Locations In San Diego County | Regional Rideshare Program-component Of Overall Tdm (tc) | 4 | 2024-03-01 | 2024-03-04 | SANDAG |  |  | CU82DUZEEL81
Obligated | STBGL | 5169(054) | El Centro | 2024-02-21 | 2024-02-21 | 2024-02-23 | 2024-02-23 | 2024-02-27 | 0 | 0 | 0 | Authorized | 5169 | 11 | E-76 approved on | NA | 16 | 2 | 4 | IMP190710 | S. Imperial Ave From Wake Ave To Danenberg Dr | Phase Ii - S. Imperial Avenue Extension - New Roadway From I-8 To Mccabe Rd. | 4 | 2024-02-05 | 2024-02-23 | SCAG |  |  | XVYWRM8J34J5
Obligated | HSIPL | 5957(126) | San Diego County | 2024-01-29 | 2024-01-29 | 2024-01-29 | 2024-01-29 | 2024-02-01 | -157488.14 | 0 | -129689.24 | Authorized | 5957 | 11 | E-76 approved on | NA | 4 | 0 | 3 | CAL 105 | Winter Gardens Boulevard From Woodside Ave To Lemoncrest Dr | Sidewalk/bike Lanes | 5 | 2024-01-25 | 2024-01-26 | SANDAG |  |  | GYNSUBBEJ6L8
Obligated | BHLSCR | 5957(062) | San Diego County | 2022-06-30 | 2024-01-04 | 2024-02-15 | 2024-02-26 | 2024-02-28 | 120000 | 0 | 150000 | Authorized | 5957 | 11 | E-76 approved on | NA | 553 | 53 | 2 | CAL44 | Willows Rd At Viejas Creek Bridge 57c0120 | Scour Monitoring & Countermeas(tc) | 8 | 2022-06-30 | 2023-10-19 | SANDAG |  |  | GYNSUBBEJ6L8
Obligated | BPMPL | 5181(192) | Huntington Beach | 2024-02-01 | 2024-02-21 | 2024-02-22 | 2024-02-22 | 2024-02-28 | 424300 | 0 | 424300 | Authorized | 5181 | 12 | E-76 approved on | NA | 20 | 1 | 6 | ORA020501 | Gilbert Dr. Bridge Over Shelter Channel In Huntington Harbour, Approx. 0.4 | Replace Corroded Steel Bearings, Repair/strengthen Corroded Steel Girders, | 1 | 2024-02-01 | 2024-02-21 | SCAG |  |  | LKKFRC4PW7L4
Obligated | CML | 5151(031) | Newport Beach | 2024-02-15 | 2024-02-15 | 2024-02-15 | 2024-02-15 | 2024-02-23 | 0 | 0 | 0 | Authorized | 5151 | 12 | E-76 approved on | NA | 22 | 0 | 8 | ORA172203 | Northeast Corner Of West Coast Highway And Superior Avenue Intersection. | The City Of Newport Beach Proposes To Construct A New Bicycle And Pedestrian | 2 | 2024-01-24 | 2024-02-15 | SCAG |  |  | FPFYQSEFJ8M3
Obligated | BPMPL | 5478(017) | Rancho Santa Margarita | 2024-01-31 | 2024-01-31 | 2024-02-05 | 2024-02-05 | 2024-02-08 | 269353 | 0 | 304250 | Authorized | 5478 | 12 | E-76 approved on | NA | 6 | 5 | 3 | ORA020501_HBP | E/b Santa Margarita Parkway Over Arroyo Trabuco (bridge #55c0520r) And | Bridge Preventive Maintenance Work | 2 | 2024-01-25 | 2024-01-30 | SCAG |  |  | N5JYK653LNG4
Obligated | CRAL | 5328(088) | Garden Grove | 2024-02-20 | 2024-02-20 | 2024-02-20 | 2024-02-20 | 2024-02-28 | 0 | 0 | 0 | Authorized | 5328 | 12 | E-76 approved on | NA | 5 | 0 | 8 | ORA211901 | Garden Grove Boulevard Between Harbor Boulevard And Fairview Street | Road Rehabilitation | 2 | 2024-02-15 | 2024-02-16 | SCAG |  |  | Y1NYWMLHKNM7
Obligated | BRLO | 5955(096) | Orange County | 2024-02-01 | 2024-02-14 | 2024-02-19 | 2024-02-20 | 2024-02-28 | 60000 | 0 | 60000 | Authorized | 5955 | 12 | E-76 approved on | NA | 15 | 6 | 8 | ORA020501 | Silverado Canyon Road Over Silverado Creek, 4.4 Miles East Of Santiago | Bridge Replacement (tc) | 3 | 2024-01-30 | 2024-02-13 | SCAG |  |  | FTL9JMLK3727
Obligated | CRAL | 5328(088) | Garden Grove | 2024-03-18 | 2024-03-18 | 2024-03-18 | 2024-03-18 | 2024-03-19 | 0 | 0 | 371827.48 | Authorized | 5328 | 12 | E-76 approved on | NA | 4 | 0 | 1 | ORA211901 | Garden Grove Boulevard Between Harbor Boulevard And Fairview Street | Road Rehabilitation | 3 | 2024-03-14 | 2024-03-15 | SCAG |  |  | Y1NYWMLHKNM7
Obligated | CRAL | 5372(017) | San Juan Capistrano | 2024-02-14 | 2024-03-11 | 2024-03-12 | 2024-03-14 | 2024-03-19 | -200000 | 0 | -600340 | Authorized | 5372 | 12 | E-76 approved on | NA | 153 | 3 | 5 | ORA211901 | Camino Capistrano Between Junipero Serra And Trabuco Creek Bridge | Pavement Rehabilitation Including Pavement Grind And Overlay, Installation | 3 | 2023-10-10 | 2024-03-07 | SCAG |  |  | JS3NCYEMAF44
Obligated | ATPSB1L | 5229(017) | Seal Beach | 2024-02-06 | 2024-02-07 | 2024-02-09 | 2024-02-09 | 2024-02-15 | 0 | 0 | 944962 | Authorized | 5229 | 12 | E-76 approved on | NA | 21 | 2 | 6 | ORA150104 | Lampson Avenue From Seal Beach Boulevard To Basswood Street In The City Of | Widen & Modify Lampson Ave. To Accommodate Class Ii Bike Lanes With Signage | 4 | 2024-01-17 | 2024-01-24 | SCAG |  |  | J2JWJVWQ8EA6
HQ | FTACML | 6478(010) | TAHOETRANDIST | 2023-07-06 | 2023-07-06 | 2023-07-06 | NA | NA | 1000000 | 0 | 1000000 | prog code Y400 | 6478 | 03 | FTA transferred waiting at HQ | NA | NA | 0 | NA | NA | FTA transfer | Fta Transfer | 1 | NA | NA | NA |  |  | LDD4FX68JLM8
HQ | FTACRPL | 6193(013) | LVMR AMA VY T A | 2024-02-06 | 2024-02-06 | 2024-03-07 | NA | NA | 6591250 | 0 | 6591250 | prog code Y601 | 6193 | 04 | FTA transferred waiting at HQ | NA | NA | 30 | NA | NA | FTA transfer | Hydrogen Fueling Station Construction | 1 | NA | NA | NA |  |  | NHQLF9T5FGJ7
HQ | FTACML | 6343(007) | MCTD | 2023-10-02 | 2023-10-02 | 2023-10-03 | NA | NA | 1600000 | 0 | 1600000 | prog code Y003 | 6343 | 04 | FTA transferred waiting at HQ | NA | NA | 1 | NA | NA | FTA transfer | Transit Corridor Improvements | 1 | NA | NA | NA |  |  | J3AWV32LJP58
HQ | FTASTPL | 6156(010) | CEN CC TRANS AU | 2023-08-10 | 2023-08-10 | 2023-10-18 | NA | NA | 400000 | 0 | 400000 | prog code Y230 | 6156 | 04 | FTA transferred waiting at HQ | NA | NA | 69 | NA | NA | FTA transfer | Cccta - Transit Corridors Study | 1 | NA | NA | NA |  |  | RKKMTQ9XQGQ5
HQ | FTASTPL | 6343(008) | MCTD | 2023-09-22 | 2023-09-22 | 2023-09-26 | NA | NA | 1107000 | 0 | 1107000 | prog code Y240 | 6343 | 04 | FTA transferred waiting at HQ | NA | NA | 4 | NA | NA | FTA transfer | Implement Part Time Transit Lane Pilot | 1 | NA | NA | NA |  |  | J3AWV32LJP58
HQ | FTASTPL | 6014(022) | SAN MATEO TD | 2023-12-07 | 2023-12-07 | 2023-12-12 | NA | NA | 407000 | 0 | 407000 | prog code Y230 | 6014 | 04 | FTA transferred waiting at HQ | NA | NA | 5 | NA | NA | FTA transfer | El Camino Real Mid-county Multimodal Corridor Plan | 1 | NA | NA | NA |  |  | RCG9BNHTZZE4
HQ | FTASTPL | 6510(009) | Napa Valley Transportation Authority | 2023-11-27 | 2023-11-27 | 2023-12-04 | NA | NA | 1060000 | 0 | 1060000 | prog code Y230 | 6510 | 04 | FTA transferred waiting at HQ | NA | NA | 7 | NA | NA | FTA transfer | Equipment Replacement And Upgrades | 1 | NA | NA | NA |  |  | KTBCYAWLJML5
HQ | FTASTPL | 6264(096) | VTA | 2023-12-08 | 2023-12-08 | 2023-12-13 | NA | NA | 575000 | 0 | 575000 | prog code Y230 | 6264 | 04 | FTA transferred waiting at HQ | NA | NA | 5 | NA | NA | FTA transfer | Road Diet And Bus Lane And Bicycle Lane | 1 | NA | NA | NA |  |  | EAZVJZNJBS22
HQ | FTACML | 6328(112) | SFPT | 2024-02-27 | 2024-02-27 | 2024-03-06 | NA | NA | 5976000 | 0 | 5976000 | prog code Y003 | 6328 | 04 | FTA transferred waiting at HQ | NA | NA | 8 | NA | NA | FTA transfer | Implement Travel Time & Reliability Improvements | 1 | NA | NA | NA |  |  | GSL6KW4Z5UE1
HQ | FTACML | 6000(076) | BAY AREA RT | 2024-02-08 | 2024-02-08 | 2024-02-13 | NA | NA | 1147000 | 0 | 1147000 | prog code Y003 | 6000 | 04 | FTA transferred waiting at HQ | NA | NA | 5 | NA | NA | FTA transfer | Bart Variable Parking Pricing | 1 | NA | NA | NA |  |  | K7KGWMHLN1N1
HQ | FTACRPL | 6000(077) | BAY AREA RT | 2024-01-31 | 2024-01-31 | 2024-02-07 | NA | NA | 3000000 | 0 | 3000000 | prog code Y601 | 6000 | 04 | FTA transferred waiting at HQ | NA | NA | 7 | NA | NA | FTA transfer | Dublin/pleasanton Access Improvements | 1 | NA | NA | NA |  |  | K7KGWMHLN1N1
HQ | FTACRPL | 6193(014) | LVMR AMA VY T A | 2024-02-06 | 2024-02-06 | 2024-03-07 | NA | NA | 6591250 | 0 | 6591250 | prog code Y601 | 6193 | 04 | FTA transferred waiting at HQ | NA | NA | 30 | NA | NA | FTA transfer | Hydrogen Fueling Station Construction | 1 | NA | NA | NA |  |  | NHQLF9T5FGJ7
HQ | FTASTPL | 6328(114) | SFPT | 2024-02-08 | 2024-02-08 | 2024-02-15 | NA | NA | 14899000 | 0 | 14899000 | prog code Y230 | 6328 | 04 | FTA transferred waiting at HQ | NA | NA | 7 | NA | NA | FTA transfer | Light Rail Vehicle Replacements | 1 | NA | NA | NA |  |  | GSL6KW4Z5UE1
HQ | FTACML | 6002(031) | ALA-CON COSTA T | 2024-02-27 | 2024-02-27 | 2024-03-06 | NA | NA | 2000000 | 0 | 2000000 | prog code Y003 | 6002 | 04 | FTA transferred waiting at HQ | NA | NA | 8 | NA | NA | FTA transfer | Install Transit Signal Priority(tsp) | 1 | NA | NA | NA |  |  | FAHMAAPZ8WL1
HQ | FTASTPL | 6002(032) | ALA-CON COSTA T | 2024-02-27 | 2024-02-27 | 2024-03-06 | NA | NA | 1500000 | 0 | 1500000 | prog code Y230 | 6002 | 04 | FTA transferred waiting at HQ | NA | NA | 8 | NA | NA | FTA transfer | Foothill Corridor Planning Study | 1 | NA | NA | NA |  |  | FAHMAAPZ8WL1
DISTRICT | FTACML | 6002(033) | ALA-CON COSTA T | NA | NA | NA | NA | NA | 2237000 | 0 | 2237000 | prog code Y003 | 6002 | 04 | FTA transferred waiting at DISTRICT | NA | NA | 0 | 0 | NA | FTA transfer | Macdonald Avenue Transit Signal Priority - Phase 1 | 1 | NA | NA | NA |  |  | FAHMAAPZ8WL1
HQ | CASB003 | 6190(033) | USDA FOREST SER | 2017-12-14 | 2017-12-14 | NA | NA | NA | 0 | 0 | 0 | prog code | 6190 | 07 | FTA transferred waiting at HQ | NA | NA | NA | NA | NA | FTA transfer | Fhwa Transfer: Corridor Management Planning | 1 | NA | NA | NA |  |  | ZCGHKT8CK366
HQ | FTACML | 5953(794) | LOS ANGELES | 2023-06-27 | 2023-06-27 | 2023-07-05 | NA | NA | 48416 | 0 | 48416 | prog code Z400 | 5953 | 07 | FTA transferred waiting at HQ | NA | NA | 8 | NA | NA | FTA transfer | Procures (1) 35-ft Clean Fuel Vehicle | 1 | NA | NA | NA |  |  | ZLJUW5L9K685
HQ | FTASTPL | 6312(032) | ACSR | 2023-06-15 | 2023-06-15 | 2023-06-21 | NA | NA | 80000000 | 0 | 80000000 | prog code Y230 | 6312 | 07 | FTA transferred waiting at HQ | NA | NA | 6 | NA | NA | FTA transfer | Transportation Services | 1 | NA | NA | NA |  |  | LE9TFZMHBCL6
HQ | FTACML | 6065(263) | LA CO M T A | 2023-06-21 | 2023-06-21 | 2023-07-03 | NA | NA | 128875000 | 0 | 128875000 | prog code Y400 | 6065 | 07 | FTA transferred waiting at HQ | NA | NA | 12 | NA | NA | FTA transfer | Operating Assistance For The Metro K Line And R.c. | 1 | NA | NA | NA |  |  | C2BXZ6YF52A5
HQ | FTACML | 7505(004) | VENTURA | 2023-06-07 | 2023-06-07 | 2023-06-20 | NA | NA | 11750204 | 0 | 11750204 | prog code Y400 | 7505 | 07 | FTA transferred waiting at HQ | NA | NA | 13 | NA | NA | FTA transfer | Youth Booster Service, Cng & Fceb Bus Replacements | 1 | NA | NA | NA
HQ | FTACRPL | 6065(265) | LA CO M T A | 2023-06-30 | 2023-06-30 | 2023-07-06 | NA | NA | 36728000 | 0 | 36728000 | prog code Y240 | 6065 | 07 | FTA transferred waiting at HQ | NA | NA | 6 | NA | NA | FTA transfer | Purchase 260 Ev Buses And Charging Infrastructure | 1 | NA | NA | NA |  |  | C2BXZ6YF52A5
HQ | FTACRPL | 6065(265) | LA CO M T A | 2023-06-30 | 2023-06-30 | 2023-07-06 | NA | NA | 16874271 | 0 | 16874271 | prog code Y601 | 6065 | 07 | FTA transferred waiting at HQ | NA | NA | 6 | NA | NA | FTA transfer | Purchase 260 Ev Buses And Charging Infrastructure | 1 | NA | NA | NA |  |  | C2BXZ6YF52A5
HQ | FTACRPL | 6065(265) | LA CO M T A | 2023-06-30 | 2023-06-30 | 2023-07-06 | NA | NA | 1041063 | 0 | 1041063 | prog code Y601 | 6065 | 07 | FTA transferred waiting at HQ | NA | NA | 6 | NA | NA | FTA transfer | Purchase 260 Ev Buses And Charging Infrastructure | 1 | NA | NA | NA |  |  | C2BXZ6YF52A5
HQ | FTACML | 6155(116) | VENTURA CO T C | 2023-06-14 | 2023-06-14 | 2023-06-21 | NA | NA | 2219187 | 0 | 2219187 | prog code Y003 | 6155 | 07 | FTA transferred waiting at HQ | NA | NA | 7 | NA | NA | FTA transfer | Purchase Of 2 Electric Buses And Transit Outreach | 1 | NA | NA | NA |  |  | JEVVZV6ALEN5
HQ | FTACML | 5006(950) | LOS ANGELES | 2023-07-10 | 2023-07-10 | 2023-07-12 | NA | NA | 492421.97 | 0 | 492421.97 | prog code Y003 | 5006 | 07 | FTA transferred waiting at HQ | NA | NA | 2 | NA | NA | FTA transfer | Implement A Pilot Shared Fleet Vehicle Program | 1 | NA | NA | NA |  |  | RNA2HUB4ZBK4
HQ | FTACML | 5006(950) | LOS ANGELES | 2023-07-10 | 2023-07-10 | 2023-07-12 | NA | NA | 715578.03 | 0 | 715578.03 | prog code Z003 | 5006 | 07 | FTA transferred waiting at HQ | NA | NA | 2 | NA | NA | FTA transfer | Implement A Pilot Shared Fleet Vehicle Program | 1 | NA | NA | NA |  |  | RNA2HUB4ZBK4
HQ | FTASTPL | 6312(037) | ACSR | 2023-07-16 | 2023-07-16 | 2023-07-17 | NA | NA | 6975298 | 0 | 6975298 | prog code Y230 | 6312 | 07 | FTA transferred waiting at HQ | NA | NA | 1 | NA | NA | FTA transfer | Transportation Services | 1 | NA | NA | NA |  |  | LE9TFZMHBCL6
HQ | FTASTPL | 6312(037) | ACSR | 2023-07-16 | 2023-07-16 | 2023-07-17 | NA | NA | 6838527 | 0 | 6838527 | prog code Y230 | 6312 | 07 | FTA transferred waiting at HQ | NA | NA | 1 | NA | NA | FTA transfer | Transportation Services | 1 | NA | NA | NA |  |  | LE9TFZMHBCL6
HQ | FTASTPL | 6312(037) | ACSR | 2023-07-16 | 2023-07-16 | 2023-07-17 | NA | NA | 5801769 | 0 | 5801769 | prog code Y230 | 6312 | 07 | FTA transferred waiting at HQ | NA | NA | 1 | NA | NA | FTA transfer | Transportation Services | 1 | NA | NA | NA |  |  | LE9TFZMHBCL6
HQ | FTASTPL | 6312(037) | ACSR | 2023-07-16 | 2023-07-16 | 2023-07-17 | NA | NA | 5688009 | 0 | 5688009 | prog code Y230 | 6312 | 07 | FTA transferred waiting at HQ | NA | NA | 1 | NA | NA | FTA transfer | Transportation Services | 1 | NA | NA | NA |  |  | LE9TFZMHBCL6
HQ | FTASTPL | 6312(037) | ACSR | 2023-07-16 | 2023-07-16 | 2023-07-17 | NA | NA | 2084153 | 0 | 2084153 | prog code Y230 | 6312 | 07 | FTA transferred waiting at HQ | NA | NA | 1 | NA | NA | FTA transfer | Transportation Services | 1 | NA | NA | NA |  |  | LE9TFZMHBCL6
HQ | FTASTPL | 6312(037) | ACSR | 2023-07-16 | 2023-07-16 | 2023-07-17 | NA | NA | 5390388 | 0 | 5390388 | prog code Y230 | 6312 | 07 | FTA transferred waiting at HQ | NA | NA | 1 | NA | NA | FTA transfer | Transportation Services | 1 | NA | NA | NA |  |  | LE9TFZMHBCL6
HQ | FTASTPL | 6312(037) | ACSR | 2023-07-16 | 2023-07-16 | 2023-07-17 | NA | NA | 2703937 | 0 | 2703937 | prog code Y230 | 6312 | 07 | FTA transferred waiting at HQ | NA | NA | 1 | NA | NA | FTA transfer | Transportation Services | 1 | NA | NA | NA |  |  | LE9TFZMHBCL6
HQ | FTASTPL | 6312(037) | ACSR | 2023-07-16 | 2023-07-16 | 2023-07-17 | NA | NA | 4086056 | 0 | 4086056 | prog code Y230 | 6312 | 07 | FTA transferred waiting at HQ | NA | NA | 1 | NA | NA | FTA transfer | Transportation Services | 1 | NA | NA | NA |  |  | LE9TFZMHBCL6
HQ | FTASTPL | 6312(037) | ACSR | 2023-07-16 | 2023-07-16 | 2023-07-17 | NA | NA | 137688051 | 0 | 137688051 | prog code Y230 | 6312 | 07 | FTA transferred waiting at HQ | NA | NA | 1 | NA | NA | FTA transfer | Transportation Services | 1 | NA | NA | NA |  |  | LE9TFZMHBCL6
HQ | FTASTPL | 6312(037) | ACSR | 2023-07-16 | 2023-07-16 | 2023-07-17 | NA | NA | 4443812 | 0 | 4443812 | prog code Y230 | 6312 | 07 | FTA transferred waiting at HQ | NA | NA | 1 | NA | NA | FTA transfer | Transportation Services | 1 | NA | NA | NA |  |  | LE9TFZMHBCL6
HQ | FTASTPL | 6065(266) | LA CO M T A | 2023-07-21 | 2023-07-21 | 2023-08-01 | NA | NA | 3393465 | 0 | 3393465 | prog code Y230 | 6065 | 07 | FTA transferred waiting at HQ | NA | NA | 11 | NA | NA | FTA transfer | Construct 2.56 Miles Of Underground Transit Extens | 1 | NA | NA | NA |  |  | C2BXZ6YF52A5
HQ | FTASTPL | 6065(266) | LA CO M T A | 2023-07-21 | 2023-07-21 | 2023-08-01 | NA | NA | 3326926 | 0 | 3326926 | prog code Y230 | 6065 | 07 | FTA transferred waiting at HQ | NA | NA | 11 | NA | NA | FTA transfer | Construct 2.56 Miles Of Underground Transit Extens | 1 | NA | NA | NA |  |  | C2BXZ6YF52A5
HQ | FTASTPL | 6065(266) | LA CO M T A | 2023-07-21 | 2023-07-21 | 2023-08-01 | NA | NA | 5174943 | 0 | 5174943 | prog code Y230 | 6065 | 07 | FTA transferred waiting at HQ | NA | NA | 11 | NA | NA | FTA transfer | Construct 2.56 Miles Of Underground Transit Extens | 1 | NA | NA | NA |  |  | C2BXZ6YF52A5
HQ | FTASTPL | 6065(266) | LA CO M T A | 2023-07-21 | 2023-07-21 | 2023-08-01 | NA | NA | 86993 | 0 | 86993 | prog code Y230 | 6065 | 07 | FTA transferred waiting at HQ | NA | NA | 11 | NA | NA | FTA transfer | Construct 2.56 Miles Of Underground Transit Extens | 1 | NA | NA | NA |  |  | C2BXZ6YF52A5
HQ | FTASTPL | 6065(266) | LA CO M T A | 2023-07-21 | 2023-07-21 | 2023-08-01 | NA | NA | 4698271 | 0 | 4698271 | prog code Y230 | 6065 | 07 | FTA transferred waiting at HQ | NA | NA | 11 | NA | NA | FTA transfer | Construct 2.56 Miles Of Underground Transit Extens | 1 | NA | NA | NA |  |  | C2BXZ6YF52A5
HQ | FTASTPL | 6065(266) | LA CO M T A | 2023-07-21 | 2023-07-21 | 2023-08-01 | NA | NA | 908424 | 0 | 908424 | prog code Y230 | 6065 | 07 | FTA transferred waiting at HQ | NA | NA | 11 | NA | NA | FTA transfer | Construct 2.56 Miles Of Underground Transit Extens | 1 | NA | NA | NA |  |  | C2BXZ6YF52A5
HQ | FTASTPL | 6065(266) | LA CO M T A | 2023-07-21 | 2023-07-21 | 2023-08-01 | NA | NA | 5459280 | 0 | 5459280 | prog code Y230 | 6065 | 07 | FTA transferred waiting at HQ | NA | NA | 11 | NA | NA | FTA transfer | Construct 2.56 Miles Of Underground Transit Extens | 1 | NA | NA | NA |  |  | C2BXZ6YF52A5
HQ | FTACML | 6155(120) | VENTURA CO T C | 2023-10-04 | 2023-10-04 | 2023-10-13 | NA | NA | 2228030 | 0 | 2228030 | prog code Y400 | 6155 | 07 | FTA transferred waiting at HQ | NA | NA | 9 | NA | NA | FTA transfer | Transportation Services | 1 | NA | NA | NA |  |  | JEVVZV6ALEN5
HQ | FTACRPL | 6155(121) | VENTURA CO T C | 2023-11-28 | 2023-11-28 | 2023-12-05 | NA | NA | 40000 | 0 | 40000 | prog code Y230 | 6155 | 07 | FTA transferred waiting at HQ | NA | NA | 7 | NA | NA | FTA transfer | Install Six (6) Microgrid Battery Pack To Suppleme | 1 | NA | NA | NA |  |  | JEVVZV6ALEN5
HQ | FTACRPL | 6155(121) | VENTURA CO T C | 2023-11-28 | 2023-11-28 | 2023-12-05 | NA | NA | 407926 | 0 | 407926 | prog code Y601 | 6155 | 07 | FTA transferred waiting at HQ | NA | NA | 7 | NA | NA | FTA transfer | Install Six (6) Microgrid Battery Pack To Suppleme | 1 | NA | NA | NA |  |  | JEVVZV6ALEN5
HQ | FTACRPL | 6155(121) | VENTURA CO T C | 2023-11-28 | 2023-11-28 | 2023-12-05 | NA | NA | 214307 | 0 | 214307 | prog code Y601 | 6155 | 07 | FTA transferred waiting at HQ | NA | NA | 7 | NA | NA | FTA transfer | Install Six (6) Microgrid Battery Pack To Suppleme | 1 | NA | NA | NA |  |  | JEVVZV6ALEN5
HQ | FTACRPL | 6155(121) | VENTURA CO T C | 2023-11-28 | 2023-11-28 | 2023-12-05 | NA | NA | 399927 | 0 | 399927 | prog code Y601 | 6155 | 07 | FTA transferred waiting at HQ | NA | NA | 7 | NA | NA | FTA transfer | Install Six (6) Microgrid Battery Pack To Suppleme | 1 | NA | NA | NA |  |  | JEVVZV6ALEN5
HQ | FTACML | 6046(020) | OMNI-TRANS | 2023-06-29 | 2023-06-29 | 2023-07-14 | NA | NA | 45602575 | 0 | 45602575 | prog code Y400 | 6046 | 08 | FTA transferred waiting at HQ | NA | NA | 15 | NA | NA | FTA transfer | Purchase Of Cng Powered And Zero Emission Vehicles | 1 | NA | NA | NA |  |  | ZDWLF25LVPP1I
HQ | FTACML | 6052(011) | SUNLINE TR AGCY | 2023-06-21 | 2023-06-21 | 2023-07-17 | NA | NA | 3201074 | 0 | 3201074 | prog code Y601 | 6052 | 08 | FTA transferred waiting at HQ | NA | NA | 26 | NA | NA | FTA transfer | Upgrade Existing Public Hydrogen Fueling Station | 1 | NA | NA | NA |  |  | W2YKNGK9JF66
HQ | FTACML | 6052(011) | SUNLINE TR AGCY | 2023-06-21 | 2023-06-21 | 2023-07-17 | NA | NA | 643388 | 0 | 643388 | prog code Y601 | 6052 | 08 | FTA transferred waiting at HQ | NA | NA | 26 | NA | NA | FTA transfer | Upgrade Existing Public Hydrogen Fueling Station | 1 | NA | NA | NA |  |  | W2YKNGK9JF66
HQ | FTACML | 6052(011) | SUNLINE TR AGCY | 2023-06-21 | 2023-06-21 | 2023-07-17 | NA | NA | 655538 | 0 | 655538 | prog code Y601 | 6052 | 08 | FTA transferred waiting at HQ | NA | NA | 26 | NA | NA | FTA transfer | Upgrade Existing Public Hydrogen Fueling Station | 1 | NA | NA | NA |  |  | W2YKNGK9JF66
HQ | FTACML | 6261(027) | VVTA | 2023-09-21 | 2023-09-21 | 2023-10-27 | NA | NA | 2725000 | 0 | 2725000 | prog code Y400 | 6261 | 08 | FTA transferred waiting at HQ | NA | NA | 36 | NA | NA | FTA transfer | Hydrogen Fuelcell Electricbus & Ev Infrastructure | 1 | NA | NA | NA |  |  | E329GCABH3Z8
HQ | FTACML | 6261(028) | VVTA | 2023-11-21 | 2023-11-21 | 2023-11-29 | NA | NA | 120000 | 0 | 120000 | prog code Y400 | 6261 | 08 | FTA transferred waiting at HQ | NA | NA | 8 | NA | NA | FTA transfer | Hydrogen Fuelcell Electricbus & Ev Infrastructure | 1 | NA | NA | NA |  |  | E329GCABH3Z8
HQ | FTACML | 6262(022) | SJRC | 2024-01-23 | 2024-01-23 | 2024-01-24 | NA | NA | 10000000 | 0 | 10000000 | prog code Y003 | 6262 | 10 | FTA transferred waiting at HQ | NA | NA | 1 | NA | NA | FTA transfer | Valley Rail New Service Operations | 1 | NA | NA | NA |  |  | LQF9KNKTYMC5
FHWA | FTACML | 6066(193) | SD ASSOC GOV'T | 2022-05-16 | 2022-05-16 | 2022-06-01 | 2022-06-01 | NA | 8000000 | 0 | 8000000 | prog code Y400 | 6066 | 11 | FTA transferred waiting at FHWA | NA | NA | 16 | 0 | NA | FTA transfer | Transit Equity Tdm Pilot Project | 1 | NA | NA | NA |  |  | CU82DUZEEL81
HQ | FTASTPL | 6066(203) | SD ASSOC GOV'T | 2023-07-03 | 2023-07-03 | 2023-07-03 | NA | NA | 1716690 | 0 | 1716690 | prog code Y230 | 6066 | 11 | FTA transferred waiting at HQ | NA | NA | 0 | NA | NA | FTA transfer | Blue Line Express Feasibility Study | 1 | NA | NA | NA |  |  | CU82DUZEEL81
HQ | FTASTPL | 6066(204) | SD ASSOC GOV'T | 2023-07-06 | 2023-07-06 | 2023-07-10 | NA | NA | 19400000 | 0 | 19400000 | prog code Y003 | 6066 | 11 | FTA transferred waiting at HQ | NA | NA | 4 | NA | NA | FTA transfer | Engineering Studies | 1 | NA | NA | NA |  |  | CU82DUZEEL81
HQ | FTASTPL | 6071(175) | ORA CO TRANS AU | 2023-03-02 | 2023-03-02 | 2023-03-06 | NA | NA | 4500000 | 0 | 4500000 | prog code Y230 | 6071 | 12 | FTA transferred waiting at HQ | NA | NA | 4 | NA | NA | FTA transfer | Track Replacement/rehabilitation | 1 | NA | NA | NA |  |  | ZS8MFUR5E1N3
HQ | FTASTPL | 6071(176) | ORA CO TRANS AU | 2023-03-02 | 2023-03-02 | 2023-03-06 | NA | NA | 1500000 | 0 | 1500000 | prog code Y230 | 6071 | 12 | FTA transferred waiting at HQ | NA | NA | 4 | NA | NA | FTA transfer | Track Replacement/rehabilitation | 1 | NA | NA | NA |  |  | ZS8MFUR5E1N3
HQ | FTACML | 6071(178) | ORA CO TRANS AU | 2023-03-29 | 2023-03-29 | 2023-04-03 | NA | NA | 4989000 | 0 | 4989000 | prog code Y400 | 6071 | 12 | FTA transferred waiting at HQ | NA | NA | 5 | NA | NA | FTA transfer | Oc Streetcar (fixed Guideway System) | 1 | NA | NA | NA |  |  | ZS8MFUR5E1N3
HQ | FTACML | 6071(179) | ORA CO TRANS AU | 2023-06-09 | 2023-06-09 | 2023-06-16 | NA | NA | 6700000 | 0 | 6700000 | prog code Y400 | 6071 | 12 | FTA transferred waiting at HQ | NA | NA | 7 | NA | NA | FTA transfer | Purchase 40' Alt Fuel Replacement Vehicles (165) | 1 | NA | NA | NA |  |  | ZS8MFUR5E1N3
HQ | FTACML | 6071(180) | ORA CO TRANS AU | 2023-05-02 | 2023-05-02 | 2023-05-03 | NA | NA | 1150550 | 0 | 1150550 | prog code Y400 | 6071 | 12 | FTA transferred waiting at HQ | NA | NA | 1 | NA | NA | FTA transfer | Alternative Fuel Replacement Vehicles | 1 | NA | NA | NA |  |  | ZS8MFUR5E1N3
HQ | FTACRAL | 6071(181) | ORA CO TRANS AU | 2023-06-01 | 2023-06-01 | 2023-06-01 | NA | NA | 3660000 | 0 | 3660000 | prog code Z970 | 6071 | 12 | FTA transferred waiting at HQ | NA | NA | 0 | NA | NA | FTA transfer | Transit Security And Operations Center (tsoc) | 1 | NA | NA | NA |  |  | ZS8MFUR5E1N3
HQ | FTASTPL | 6071(183) | ORA CO TRANS AU | 2023-06-08 | 2023-06-08 | 2023-06-12 | NA | NA | 1770000 | 0 | 1770000 | prog code Y230 | 6071 | 12 | FTA transferred waiting at HQ | NA | NA | 4 | NA | NA | FTA transfer | Coastal Rail Infrastructure Study - Study Only | 1 | NA | NA | NA |  |  | ZS8MFUR5E1N3
HQ | FTACML | 6071(184) | ORA CO TRANS AU | 2023-07-03 | 2023-07-03 | 2023-07-05 | NA | NA | 19430000 | 0 | 19430000 | prog code Y400 | 6071 | 12 | FTA transferred waiting at HQ | NA | NA | 2 | NA | NA | FTA transfer | 29 Replacement Vehicles | 1 | NA | NA | NA |  |  | ZS8MFUR5E1N3
HQ | FTACML | 6071(185) | ORA CO TRANS AU | 2023-07-05 | 2023-07-05 | 2023-07-06 | NA | NA | 9196.66 | 0 | 9196.66 | prog code M0E3 | 6071 | 12 | FTA transferred waiting at HQ | NA | NA | 1 | NA | NA | FTA transfer | Fta | 1 | NA | NA | NA |  |  | ZS8MFUR5E1N3
HQ | FTACML | 6071(185) | ORA CO TRANS AU | 2023-07-05 | 2023-07-05 | 2023-07-06 | NA | NA | 102390.15 | 0 | 102390.15 | prog code M40E | 6071 | 12 | FTA transferred waiting at HQ | NA | NA | 1 | NA | NA | FTA transfer | Fta | 1 | NA | NA | NA |  |  | ZS8MFUR5E1N3
HQ | FTACML | 6071(185) | ORA CO TRANS AU | 2023-07-05 | 2023-07-05 | 2023-07-06 | NA | NA | 5609413.19 | 0 | 5609413.19 | prog code Y400 | 6071 | 12 | FTA transferred waiting at HQ | NA | NA | 1 | NA | NA | FTA transfer | Fta | 1 | NA | NA | NA |  |  | ZS8MFUR5E1N3
HQ | FTACRPL | 6071(186) | ORA CO TRANS AU | 2023-07-05 | 2023-07-05 | 2023-07-06 | NA | NA | 5748000 | 0 | 5748000 | prog code Y601 | 6071 | 12 | FTA transferred waiting at HQ | NA | NA | 1 | NA | NA | FTA transfer | Replacement Fuel Cell Electric Buses | 1 | NA | NA | NA |  |  | ZS8MFUR5E1N3
HQ | FTACML | 6071(187) | ORA CO TRANS AU | 2023-07-05 | 2023-07-05 | 2023-07-06 | NA | NA | 4690000 | 0 | 4690000 | prog code Y400 | 6071 | 12 | FTA transferred waiting at HQ | NA | NA | 1 | NA | NA | FTA transfer | Replacement Vehicles Project | 1 | NA | NA | NA |  |  | ZS8MFUR5E1N3
HQ | FTACML | 6071(191) | ORA CO TRANS AU | 2024-01-08 | 2024-01-08 | 2024-01-09 | NA | NA | 970200 | 0 | 970200 | prog code Y400 | 6071 | 12 | FTA transferred waiting at HQ | NA | NA | 1 | NA | NA | FTA transfer | Octa Share Of Replacement Locomotives | 1 | NA | NA | NA |  |  | ZS8MFUR5E1N3
HQ | FTACML | 6071(192) | ORA CO TRANS AU | 2024-03-27 | 2024-03-27 | NA | NA | NA | 15285000 | 0 | 15285000 | prog code Y400 | 6071 | 12 | FTA transferred waiting at HQ | NA | NA | NA | NA | NA | FTA transfer | Replacement Fuel Cell Electric Buses | 1 | NA | NA | NA |  |  | ZS8MFUR5E1N3
HQ | FTACML | 6071(192) | ORA CO TRANS AU | 2024-03-27 | 2024-03-27 | NA | NA | NA | 465000 | 0 | 465000 | prog code Y400 | 6071 | 12 | FTA transferred waiting at HQ | NA | NA | NA | NA | NA | FTA transfer | Replacement Fuel Cell Electric Buses | 1 | NA | NA | NA |  |  | ZS8MFUR5E1N3
HQ | FTACRAL | 6071(193) | ORA CO TRANS AU | 2024-03-27 | 2024-03-27 | 2024-03-27 | NA | NA | 200000 | 0 | 200000 | prog code Z972 | 6071 | 12 | FTA transferred waiting at HQ | NA | NA | 0 | NA | NA | FTA transfer | Emergency Railroad Track Stabilization Mp 206.8 | 1 | NA | NA | NA |  |  | ZS8MFUR5E1N3
HQ | FTASTPL | 6071(195) | ORA CO TRANS AU | 2024-03-27 | 2024-03-27 | NA | NA | NA | 7980000 | 0 | 7980000 | prog code Y230 | 6071 | 12 | FTA transferred waiting at HQ | NA | NA | NA | NA | NA | FTA transfer | Transit Service Expansion Planning, Orange County | 1 | NA | NA | NA |  |  | ZS8MFUR5E1N3
HQ | FTASTPL | 6071(195) | ORA CO TRANS AU | 2024-03-27 | 2024-03-27 | NA | NA | NA | 20000 | 0 | 20000 | prog code Y230 | 6071 | 12 | FTA transferred waiting at HQ | NA | NA | NA | NA | NA | FTA transfer | Transit Service Expansion Planning, Orange County | 1 | NA | NA | NA |  |  | ZS8MFUR5E1N3