## quarterly_report_attachment_1_a
ATTACHMENT 1
State Highway Operation and Protection Program (SHOPP) Project List**
April 01 - June 30, 2022
All dollar amounts are represented in thousands
Row Number | District | PPNO | County | Route | Title | Location | Type of Work | PAED Approved Budget | PAED Allocated | PAED SHOPP Budget | PAED Expended | PAED SHOPP Expended | PAED EAC | PAED Over Budget | PSE Approved Budget | PSE Allocated | PSE SHOPP Budget | PSE Expended | PSE SHOPP Expended | PSE EAC | PSE Over Budget | RW Sup Approved Budget | RW Sup Allocated | RW Sup SHOPP Budget | RW Sup Expended | RW Sup SHOPP Expended | RW Sup EAC | RW Sup Over Budget | Con Sup Approved Budget | Con Sup Allocated | Con Sup SHOPP Budget | Con Sup Expended | Con Sup SHOPP Expended | Con Sup EAC | Con Sup Over Budget | RW Cap Approved Budget | RW Cap Allocated | RW Cap SHOPP Budget | RW Cap Expended | RW Cap SHOPP Expended | RW Cap EAC | RW Cap Over Budget | Con Cap Approved Budget | Con Cap Allocated | Con Cap SHOPP Budget | Con Cap Expended | Con Cap SHOPP Expended | Con Cap EAC | Con Cap Over Budget | Total Approved Budget | Total SHOPP Budget | Total Expended | Total SHOPP Expended | Total EAC | Baseline Actual Finish Date | PAED Approved Finish Date | PAED Actual Finish Date | PAED Current Finish Date | PAED Behind Schedule | RW Cert Approved Finish Date | RW Cert Actual Finish Date | RW Cert Current Finish Date | RW Cert Behind Schedule | RTL Approved Finish Date | RTL Actual Finish Date | RTL Current Finish Date | RTL Behind Schedule | Begin Const Approved Finish Date | Begin Const Actual Finish Date | Begin Const Current Finish Date | Beg Con Behind Schedule | End Const Approved Finish Date | End Const Actual Finish Date | End Const Current Finish Date | End Con Behind Schedule | Award Amount | Schedule Corrective Action Plan | Cost Corrective Action Plan | Scope Corrective Action Plan | Benefits Corrective Action Plan
1 | 01 | 0100V | DN | 101 | Dr. Fine Bridge Replacement | Near Crescent City from 0.3 mile south to 0.4 mile north of Smith River (Dr Ernest M Fine Memorial) Bridge No 01-0020. | Replace bridge. | 14391 | Yes | 14391 | 14370 | 14370 | 14370 | No | 4820 | Yes | 4820 | 4799 | 4799 | 4996 | Yes | 650 | Yes | 650 | 467 | 467 | 640 | No | 13355 | Yes | 13355 | 0 | 0 | 13872 | Yes | 6499 | No | 6499 | 1249 | 1249 | 6499 | No | 86566 | Yes | 86566 | 0 | 0 | 64677 | No | 126281 | 126281 | 20885 | 20885 | 105054 | 2020-06-24 | 2020-03-19 | 2020-03-19 |  |  | 2021-04-01 | 2021-04-15 |  |  | 2021-04-19 | 2021-05-03 |  |  | 2021-09-01 |  | 2022-08-08 | Yes |  |  | 2026-10-03 |  | 0 | Yes | No | No | No
2 | 01 | 1055 | DN | 199 | DN-199 Culverts | In Del Norte County, at various locations from 0.6 mile north of Hiouchi Drive to 0.1 mile south of the Oregon State line. | Culvert rehabilitation and fish passage. | 1410 | Yes | 1410 | 1121 | 1121 | 1121 | No | 783 | Yes | 783 | 782 | 782 | 782 | No | 52 | Yes | 52 | 6 | 6 | 52 | No | 814 | Yes | 814 | 151 | 151 | 775 | No | 78 | No | 78 | 36 | 36 | 26 | No | 1564 | Yes | 1564 | 593 | 593 | 1564 | No | 4701 | 4701 | 2689 | 2689 | 4320 |  |  | 2019-02-01 |  |  |  | 2020-03-03 |  |  |  | 2020-05-04 |  |  |  | 2020-08-20 |  |  |  |  | 2023-01-30 |  | 1564 | No | No | No | No
3 | 01 | 1072 | DN | 101 | Hunter/Panther Creek Bridge Replacement | Near Klamath, at Panther Creek Bridge No 01-0025 and at Hunter Creek Bridge No 01-0003. | Seismic retrofit. | 3729 | Yes | 3729 | 3724 | 3724 | 3724 | No | 3720 | Yes | 3720 | 2986 | 2986 | 2986 | No | 373 | Yes | 373 | 44 | 44 | 183 | No | 4426 | Yes | 4426 | 3943 | 3943 | 5841 | Yes | 5584 | No | 5584 | 2229 | 2229 | 2230 | No | 21171 | Yes | 21171 | 13539 | 13539 | 21171 | No | 39003 | 39003 | 26465 | 26465 | 36135 | 2019-01-31 | 2018-07-05 | 2018-07-05 |  |  | 2019-05-10 | 2019-04-16 |  |  | 2019-06-03 | 2019-10-14 |  |  | 2019-09-16 | 2020-05-08 |  |  |  |  | 2023-12-30 |  | 21171 | No | Yes | No | Yes
4 | 01 | 1113 | DN | 101 | Dominie Creek Fish Passage | Near Smith River, at Dominie Creek. | Replace box culvert with new bridge and remediate fish passage barrier. | 2000 | Yes | 2000 | 1395 | 1395 | 1395 | No | 1141 | Yes | 1141 | 896 | 896 | 896 | No | 118 | Yes | 118 | 33 | 33 | 71 | No | 1830 | Yes | 1830 | 1293 | 1293 | 1789 | No | 151 | No | 151 | 24 | 24 | 24 | No | 5269 | Yes | 5269 | 4816 | 4816 | 5269 | No | 10509 | 10509 | 8457 | 8457 | 9444 |  | 2019-01-15 | 2019-01-15 |  |  | 2020-01-03 | 2019-12-11 |  |  | 2020-01-17 | 2020-02-03 |  |  | 2020-07-22 | 2020-06-18 |  |  |  |  | 2023-01-02 |  | 5269 | No | No | No | No
5 | 01 | 1130 | DN | 199 | INSIDE PARK CULVERTS | Near Crescent City, at various locations from 0.3 mile north of Elk Valley Cross Road to 0.2 mile south of Walker Road. | Culvert rehabilitation and fish passage. | 449 | Yes | 449 | 447 | 447 | 447 | No | 624 | Yes | 624 | 598 | 598 | 598 | No | 76 | Yes | 76 | 38 | 38 | 94 | Yes | 452 | Yes | 452 | 212 | 212 | 465 | Yes | 88 | No | 88 | 24 | 24 | 24 | No | 2693 | Yes | 2693 | 274 | 274 | 2693 | No | 4382 | 4382 | 1593 | 1593 | 4321 |  | 2020-01-14 | 2020-01-14 |  |  | 2021-01-08 | 2021-01-19 |  |  | 2021-01-21 | 2021-04-28 |  |  | 2021-05-06 | 2021-08-26 |  |  |  |  | 2024-12-02 |  | 2692 | No | No | No | No
6 | 01 | 1148M | DN | 101 | Smith River BR/HAMBRO Off Site Mitigation | Near Crescent City at Elk Valley Road. | Offsite environmental mitigation and monitoring for project EA 43640. | 0 | No | 0 | 0 | 0 | 0 | No | 0 | No | 0 | 0 | 0 | 0 | No | 0 | No | 0 | 0 | 0 | 0 | No | 283 | Yes | 283 | 13 | 13 | 438 | Yes | 0 | No | 0 | 0 | 0 | 0 | No | 300 | Yes | 300 | 0 | 0 | 300 | No | 583 | 583 | 13 | 13 | 738 | [7 empty] | 2025-07-15 |  |  | 2021-05-03 |  |  |  |  | 2025-12-01 |  |  |  | 2027-12-01 |  | 0 | No | No | No | No
7 | 01 | 2301 | HUM | 101 | South Fork Eel River Bridge #04-123 | Near Myers Flat, at South Fork Eel River Bridge No 04-0123. | Seismic retrofit. | 4641 | Yes | 4641 | 3830 | 3830 | 3830 | No | 2072 | Yes | 2072 | 2029 | 2029 | 2029 | No | 218 | Yes | 218 | 86 | 86 | 213 | No | 2812 | Yes | 2812 | 290 | 290 | 2825 | Yes | 290 | No | 290 | 63 | 63 | 63 | No | 7066 | Yes | 7066 | 88 | 88 | 7066 | No | 17099 | 17099 | 6386 | 6386 | 16026 |  | 2019-11-26 | 2019-11-26 |  |  | 2021-03-18 | 2021-03-09 |  |  | 2021-04-01 | 2021-04-01 |  |  | 2021-08-01 | 2021-11-12 |  |  |  |  | 2023-11-01 |  | 7066 | No | No | No | No
8 | 01 | 2302 | HUM | 96 | Three HUM Bridges | In Humboldt County, at Willow Creek Bridge No 04 -0135 (PM 0.24) and Camp Creek Bridge No 04 -0666 (PM 37.25); also on Route 101 at G Street Overcrossing No 04-0243 (PM 86.77). | Seismic retrofit of three bridges. | 2366 | Yes | 2366 | 1468 | 1468 | 1468 | No | 1856 | Yes | 1856 | 649 | 649 | 649 | No | 171 | Yes | 171 | 30 | 30 | 152 | No | 1948 | Yes | 1948 | 918 | 918 | 1944 | No | 1089 | No | 1089 | 12 | 12 | 12 | No | 2799 | Yes | 2799 | 2152 | 2152 | 2799 | No | 10229 | 10229 | 5229 | 5229 | 7024 |  | 2019-02-01 | 2019-04-26 |  |  | 2020-02-01 | 2020-01-13 |  |  | 2020-02-15 | 2020-03-20 |  |  | 2020-09-01 | 2020-07-10 |  |  |  |  | 2023-12-01 |  | 2799 | No | No | No | No
9 | 01 | 2363 | HUM | 36 | Bridge Rail Replacement - 3 bridges | Near Bridgeville, at Hely Creek Bridge No 04-0092, Little Larabee Creek Bridge No 04-0102 (PM 25.3), and Butte Creek Bridge No 04-0116. | Upgrade bridge rails and widen at one bridge, and replace two bridges. (G13 Contingency). | 3442 | Yes | 3442 | 3438 | 3438 | 3438 | No | 2902 | Yes | 2902 | 2731 | 2731 | 3034 | Yes | 245 | Yes | 245 | 182 | 182 | 287 | Yes | 0 | No | 0 | 0 | 0 | 5908 | Yes | 1015 | No | 1015 | 359 | 359 | 470 | No | 0 | No | 0 | 0 | 0 | 17811 | Yes | 7604 | 7604 | 6710 | 6710 | 30948 |  | 2021-06-01 | 2021-06-14 |  |  | 2022-05-02 | 2022-05-26 |  |  | 2022-06-01 | 2022-06-27 |  |  | 2022-11-01 |  | 2023-01-23 | No |  |  | 2025-12-01 |  | 0 | No | Yes | No | No
10 | 01 | 2376 | HUM | 101 | Corridor Bridge Rails | Near Eureka, from 0.1 mile south of Jacoby Creek Bridge No 04-0023 to 0.1 mile north of Gannon Slough Bridge No 04-0024. | Upgrade bridge rails and replace bridge. | 1828 | No | 1828 | 1801 | 1801 | 1801 | No | 3014 | Yes | 3014 | 2866 | 2866 | 2866 | No | 238 | Yes | 238 | 44 | 44 | 198 | No | 2333 | Yes | 2333 | 1563 | 1563 | 2255 | No | 39 | No | 39 | 39 | 39 | 39 | No | 9084 | Yes | 9084 | 7545 | 7545 | 9084 | No | 16536 | 16536 | 13858 | 13858 | 16243 |  | 2017-01-10 | 2017-01-10 |  |  | 2019-03-15 | 2019-03-14 |  |  | 2019-04-01 | 2019-09-25 |  |  | 2019-11-21 | 2020-02-13 |  |  |  |  | 2024-01-01 |  | 9084 | No | No | No | No
11 | 01 | 2400 | HUM | 101 | HUM-101 Strengthen 2 Bridges | In Humboldt County, at South Fork Eel River Bridge and Separation No 04-0065; also at Arcata Overhead No 04-0079 (PM 87.8). | Strengthen two bridge structures. | 1010 | Yes | 1010 | 617 | 617 | 617 | No | 1355 | Yes | 1355 | 1212 | 1212 | 1212 | No | 65 | Yes | 65 | 13 | 13 | 54 | No | 2252 | Yes | 2252 | 1915 | 1915 | 2659 | Yes | 1359 | No | 1359 | 15 | 15 | 15 | No | 10933 | Yes | 10933 | 8339 | 8339 | 10933 | No | 16974 | 16974 | 12111 | 12111 | 15490 |  | 2018-09-01 | 2018-09-18 |  |  | 2019-06-01 | 2019-05-01 |  |  | 2019-06-01 | 2019-06-21 |  |  | 2019-11-14 | 2020-02-19 |  |  |  |  | 2023-08-01 |  | 9757 | No | No | No | No
12 | 01 | 2430 | HUM | 299 | 200/299 SEPARATION | Near Arcata, at the Route 200/299 Separation No 04-0184. | Establish standard vertical clearance. | 564 | Yes | 564 | 561 | 561 | 561 | No | 1010 | Yes | 1010 | 762 | 762 | 762 | No | 26 | Yes | 26 | 9 | 9 | 21 | No | 1306 | Yes | 1306 | 490 | 490 | 1367 | Yes | 31 | No | 31 | 9 | 9 | 9 | No | 3680 | Yes | 3680 | 771 | 771 | 3680 | No | 6617 | 6617 | 2602 | 2602 | 6400 |  | 2019-08-01 | 2019-09-27 |  |  | 2020-02-04 | 2020-01-22 |  |  | 2020-03-03 | 2020-05-01 |  |  | 2020-08-04 | 2020-10-02 |  |  |  |  | 2024-03-01 |  | 3680 | No | No | No | No
13 | 01 | 2433 | HUM | 299 | HUM-299 Culverts | Near Blue Lake and Willow Creek, from 0.1 mile east of Route 200 to 0.5 mile east of Boise Creek Campground. | Rehabilitate drainage culverts. | 1194 | Yes | 1194 | 1155 | 1155 | 1155 | No | 958 | Yes | 958 | 767 | 767 | 932 | No | 77 | Yes | 77 | 19 | 19 | 49 | No | 0 | Yes | 0 | 0 | 0 | 1935 | Yes | 102 | No | 102 | 106 | 106 | 106 | Yes | 0 | Yes | 0 | 0 | 0 | 7210 | Yes | 2331 | 2331 | 2047 | 2047 | 11387 |  | 2020-05-01 | 2020-06-02 |  |  | 2021-07-02 | 2022-02-25 |  |  | 2021-08-02 | 2022-04-22 |  |  | 2022-02-01 |  | 2022-10-19 | Yes |  |  | 2025-12-31 |  | 0 | Yes | Yes | No | No
14 | 01 | 2439 | HUM | 101 | TRINIDAD CAPM | Near Trinidad, from 1.3 miles south of School Road to 0.4 mile north of Big Lagoon Bridge. | Pavement rehabilitation. | 332 | Yes | 332 | 311 | 311 | 311 | No | 937 | Yes | 937 | 932 | 932 |  | No | 84 | Yes | 84 | 75 | 75 | 140 | Yes | 4499 | Yes | 4499 | 172 | 172 | 4257 | No | 12 | No | 12 | 0 | 0 | 0 | No | 29381 | Yes | 29381 | 592 | 592 | 29381 | No | 35245 | 35245 | 2082 | 2082 | 35021 | 2019-10-09 | 2019-07-31 | 2019-07-31 |  |  | 2020-11-01 | 2021-09-27 |  |  | 2020-11-15 | 2021-06-28 |  |  | 2021-06-01 | 2022-02-23 |  |  |  |  | 2023-12-01 |  | 29381 | No | No | No | No
15 | 01 | 2449 | HUM | 96 | HUM 96-169 5 BRIDGES Rail Upgrade | Near Weitchpec and Orleans, at Aikens Creek Bridge No 04-0059 (PM 28.1), Bluff Creek Bridge No 04-0063 (PM 28.3), Bluff Creek Bridge No 04-0225 (PM R28.9), and Slate Creek Bridge No 04-0061 (PM 29.9); also on Route 169 at Rube Creek Bridge No 04-0215 (PM 27.6). | Upgrade bridge rails at five locations and also strengthen for truck permit load capacity at two locations. | 1050 | Yes | 1050 | 704 | 704 | 704 | No | 2127 | Yes | 2127 | 1198 | 1198 | 1426 | No | 110 | Yes | 110 | 9 | 9 | 39 | No | 2242 | Yes | 2242 | 0 | 0 | 2594 | Yes | 278 | No | 278 | 4 | 4 | 4 | No | 9350 | Yes | 9350 | 0 | 0 | 9129 | No | 15157 | 15157 | 1915 | 1915 | 13896 |  | 2020-04-30 | 2020-04-30 |  |  | 2021-10-18 | 2021-10-18 |  |  | 2021-11-02 | 2021-12-31 |  |  | 2022-03-23 |  | 2022-08-15 | Yes |  |  | 2028-12-01 |  | 0 | Yes | No | No | No
16 | 01 | 2487 | HUM | 169 | REHAB HUM-169 CULVERTS | Near Weitchpec, from 0.6 mile east of Pecwan Creek Bridge to Route 96 at various locations. | Rehabilitate drainage systems. | 2499 | Yes | 2499 | 1402 | 1402 | 1402 | No | 1121 | No | 1121 | 0 | 0 | 1058 | No | 1397 | No | 1397 | 0 | 0 | 212 | No | 1718 | No | 1718 | 0 | 0 | 1826 | Yes | 474 | No | 474 | 3 | 3 | 366 | No | 5606 | No | 5606 | 0 | 0 | 4464 | No | 12815 | 12815 | 1405 | 1405 | 9328 |  | 2022-06-06 | 2022-06-21 |  |  | 2023-12-06 |  | 2023-12-06 | No | 2024-01-08 |  | 2024-01-08 | No | 2024-05-22 |  | 2024-05-22 | No |  |  | 2026-12-01 |  | 0 | No | No | No | No
17 | 01 | 2493 | HUM | 299 | Arcata to Blue Lake CAPM | In and near Arcata, from Route 101 to east of Blue Lake BoulevaRd Rehabilitate pavement and upgrade guardrail, lighting, and Transportation Management System (TMS) elements. | REHABILITATE PAVEMENT | 629 | Yes | 629 | 505 | 505 | 505 | No | 746 | Yes | 746 | 140 | 140 | 743 | No | 50 | Yes | 50 | 2 | 2 | 53 | Yes | 1424 | No | 1424 | 0 | 0 | 1526 | Yes | 9 | No | 9 | 0 | 0 | 23 | Yes | 15358 | No | 15358 | 0 | 0 | 13430 | No | 18216 | 18216 | 647 | 647 | 16280 |  | 2021-10-07 | 2021-10-07 |  |  | 2022-09-01 |  | 2022-09-01 | No | 2022-10-01 |  | 2022-10-01 | No | 2023-04-01 |  | 2023-04-01 | No |  |  | 2024-12-01 |  | 0 | No | No | No | No
18 | 01 | 2494 | HUM | 299 | HUM-299 CAPM | Near Blue Lake, from North Fork Mad River Bridge to Redwood Creek Bridge. | Rehabilitate roadway and upgrade guardrail and Transportation Management System (TMS) elements. | 605 | Yes | 605 | 442 | 442 | 442 | No | 816 | Yes | 816 | 110 | 110 | 870 | Yes | 37 | Yes | 37 | 2 | 2 | 29 | No | 2457 | No | 2457 | 0 | 0 | 2136 | No | 6 | No | 6 | 1 | 1 | 6 | No | 18367 | No | 18367 | 0 | 0 | 17832 | No | 22288 | 22288 | 555 | 555 | 21315 |  | 2021-11-01 | 2021-10-27 |  |  | 2022-09-15 |  | 2022-09-15 | No | 2023-01-13 |  | 2023-01-13 | No | 2023-07-14 |  | 2023-07-14 | No |  |  | 2024-11-01 |  | 0 | No | No | No | No
19 | 01 | 2495 | HUM | 36 | HUM-36 CAPM 201.121 | Near Fortuna, from 2.0 miles east of Redwood House Road to 1.7 miles west of Burr Valley Road. | Rehabilitate pavement and upgrade guardrail and Transportation Management System (TMS) elements. | 921 | Yes | 921 | 806 | 806 | 806 | No | 1090 | Yes | 1090 | 207 | 207 | 1141 | Yes | 123 | Yes | 123 | 3 | 3 | 119 | No | 3297 | No | 3297 | 0 | 0 | 2735 | No | 32 | No | 32 | 3 | 3 | 32 | No | 35000 | No | 35000 | 0 | 0 | 27515 | No | 40463 | 40463 | 1019 | 1019 | 32348 |  | 2022-01-10 | 2022-02-07 |  |  | 2023-02-16 |  | 2022-08-01 | No | 2023-03-01 |  | 2023-03-01 | No | 2023-07-19 |  | 2023-08-29 | No |  |  | 2024-12-01 |  | 0 | No | No | No | No
20 | 01 | 2497 | HUM | 101 | HUM-101 Drainage South | Near Rio Dell, from Mendocino County line to north of Wildwood Avenue at various locations. | Rehabilitate drainage systems and upgrade lighting and Transportation Management System (TMS) elements. | 2631 | Yes | 2631 | 1278 | 1278 | 2815 | Yes | 1657 | No | 1657 | 0 | 0 | 1459 | No | 350 | No | 350 | 0 | 0 | 312 | No | 3370 | No | 3370 | 0 | 0 | 2797 | No | 1775 | No | 1775 | 0 | 0 | 3255 | Yes | 17692 | No | 17692 | 0 | 0 | 14507 | No | 27475 | 27475 | 1278 | 1278 | 25145 |  | 2023-04-03 |  | 2023-05-15 | No | 2024-04-01 |  | 2024-04-01 | No | 2024-04-11 |  | 2024-04-11 | No | 2024-10-08 |  | 2024-10-08 | No |  |  | 2026-12-01 |  | 0 | No | Yes | No | Yes
21 | 01 | 2518 | HUM | 254 | HUM-254 culverts | Near Phillipsville and Weott, from south of Chimney Tree Gift Shop to south of Bull Creek Flats Road. | Rehabilitate drainage systems and reduce sediment loads to South Fork Eel River. | 1365 | Yes | 1365 | 1003 | 1003 | 1003 | No | 1066 | No | 1066 | 0 | 0 | 972 | No | 254 | No | 254 | 0 | 0 | 155 | No | 1069 | No | 1069 | 0 | 0 | 1059 | No | 550 | No | 550 | 0 | 0 | 63 | No | 2685 | No | 2685 | 0 | 0 | 2367 | No | 6989 | 6989 | 1003 | 1003 | 5619 |  | 2022-05-02 | 2022-06-13 |  |  | 2023-10-13 |  | 2023-10-13 | No | 2023-11-01 |  | 2023-11-01 | No | 2024-03-20 |  | 2024-03-20 | No |  |  | 2025-12-01 |  | 0 | Yes | Yes | Yes | Yes
22 | 01 | 2538 | HUM | 255 | Eureka-Arcata Corridor Combined Mitigation | IN HUMBOLDT COUNTY NEAR ARCATA FROM PACHACO LN TO V ST | COMBINED ENVIRONMENTAL MITIGATION | 190 | No | 0 | 821 | 0 | 821 | Yes | 1026 | No | 1026 | 422 | 422 | 422 | No | 123 | No | 123 | 25 | 25 | 27 | No | 2828 | No | 928 | 625 | 205 | 3182 | Yes | 0 | No | 0 | 1513 | 161 | 0 | No | 5178 | No | 1106 | 2551 | 549 | 5177 | No | 9345 | 3183 | 5957 | 1362 | 9629 |  |  | 2017-01-10 |  |  |  | 2020-01-17 |  |  |  | 2020-02-26 |  |  |  | 2020-07-23 |  |  |  |  | 2024-10-01 |  | 5177 | No | No | No | No
23 | 01 | 3107M | LAK | 20 | Bachelor Creek Bridge Mitigation | Near Upper Lake, at Bachelor Creek Bridge No 14-0001. | Environmental mitigation for project EA 0F490. | 0 | No | 0 | 0 | 0 | 0 | No | 0 | No | 0 | 0 | 0 | 0 | No | 0 | No | 0 | 0 | 0 | 0 | No | 218 | Yes | 218 | 0 | 0 | 224 | Yes | 0 | No | 0 | 0 | 0 | 0 | No | 166 | Yes | 166 | 0 | 0 | 0 | No | 384 | 384 | 0 | 0 | 224 |  |  | 2018-12-17 |  |  |  | 2020-04-07 |  |  | 2023-01-15 |  | 2023-01-15 | No | 2023-03-15 |  | 2023-03-15 | No |  |  | 2029-06-02 |  | 0 | No | No | No | No
24 | 01 | 3130 | LAK | 29 | Morrison, Robinson & Kelsey Creek | Near Upper Lake, at Robinson Creek Bridge No 14-0030; also on Route 175 at Kelsey Creek Bridge No 14-0044 (PM 19.48); also on Route 20 at Morrison Creek Bridge No 14-0004 (PM 16.81). | Widen bridge and upgrade bridge rails at Robinson Creek Bridge and Morrison Creek Bridge, and replace existing Kelsey Creek Bridge. | 1434 | Yes | 1434 | 1429 | 1429 | 1429 | No | 2220 | Yes | 2220 | 2076 | 2076 | 2076 | No | 223 | Yes | 223 | 185 | 185 | 222 | No | 2770 | Yes | 2770 | 679 | 679 | 3242 | Yes | 833 | No | 833 | 130 | 130 | 130 | No | 9526 | Yes | 9526 | 1102 | 1102 | 9526 | No | 17006 | 17006 | 5601 | 5601 | 16625 |  | 2020-06-15 | 2020-06-29 |  |  | 2021-04-21 | 2021-05-19 |  |  | 2021-06-18 | 2021-06-18 |  |  | 2021-09-01 | 2021-10-19 |  |  |  |  | 2023-12-01 |  | 9526 | Yes | Yes | Yes | Yes
25 | 01 | 3133 | LAK | 020 | Witter Springs Safety Combined | IN LAKE COUNTY NEAR UPPER LAKE FROM 0.4 MILE WEST OF WITTER SPRINGS ROAD TO 0.4 MILE EAST OF BACHELOR CREEK BRIDGE | COMBINED SAFETY AND BRIDGE REHAB | 2040 | No | 2040 | 2013 | 2013 | 2013 | No | 2585 | No | 2585 | 2363 | 2363 | 2363 | No | 158 | No | 158 | 86 | 86 | 86 | No | 2469 | No | 2469 | 2234 | 2234 | 2784 | Yes | 0 | No | 0 | 265 | 265 | 0 | No | 8910 | No | 8910 | 7842 | 7842 | 8910 | No | 16162 | 16162 | 14803 | 14803 | 16156 |  |  | 2019-04-03 |  |  |  | 2020-04-07 |  |  |  | 2020-06-23 |  |  |  | 2020-12-09 |  |  |  |  | 2023-01-30 |  | 8909 | No | No | No | No
26 | 01 | 4587 | MEN | 20 | Calpella 2 Bridge Replacements | Near Ukiah, from North Calpella Overcrossing to 0.5 mile east of County Road 144 at Russian River Bridge and Overhead No 10-0182 and Redwood Valley Undercrossing No 10-0183. | Replace two bridges with a single bridge on a new alignment. | 3424 | Yes | 3424 | 3412 | 3412 | 3412 | No | 3129 | Yes | 3129 | 2753 | 2753 | 2753 | No | 301 | Yes | 301 | 254 | 254 | 296 | No | 7534 | Yes | 7534 | 242 | 242 | 8217 | Yes | 2064 | No | 2064 | 879 | 879 | 1121 | No | 28701 | Yes | 28701 | 0 | 0 | 28701 | No | 45153 | 45153 | 7540 | 7540 | 44500 | 2020-08-12 | 2020-05-28 | 2020-05-28 |  |  | 2021-06-01 | 2021-07-08 |  |  | 2021-06-15 | 2021-07-08 |  |  | 2021-10-20 | 2022-06-09 |  |  |  |  | 2025-11-03 |  | 28701 | No | No | No | No
27 | 01 | 4588 | MEN | 1 | Elk Creek Bridge Replacement | Near Fort Bragg, at Elk Creek Bridge No 10-0120. | Replace bridge. | 2532 | Yes | 2532 | 2494 | 2494 | 2494 | No | 1660 | Yes | 1660 | 486 | 486 | 1686 | Yes | 221 | Yes | 221 | 63 | 63 | 269 | Yes | 3000 | No | 3000 | 0 | 0 | 3043 | Yes | 2250 | No | 2250 | 15 | 15 | 2589 | Yes | 10350 | No | 10350 | 0 | 0 | 10405 | Yes | 20013 | 20013 | 3058 | 3058 | 20486 |  | 2021-01-15 | 2021-12-24 |  |  | 2022-04-29 |  | 2023-07-01 | Yes | 2022-05-06 |  | 2023-07-15 | Yes | 2022-08-31 |  | 2023-05-02 | Yes |  |  | 2025-12-01 |  | 0 | Yes | No | No | No
28 | 01 | 4588B | MEN | 1 | Hare Creek Bridge | Near Fort Bragg, at Hare Creek Bridge No 10-0175. | Upgrade bridge rails and widen to make standaRd (G13 Contingency). | 3247 | Yes | 3247 | 2795 | 2795 | 3985 | Yes | 2979 | No | 2979 | 0 | 0 | 2658 | No | 183 | No | 183 | 0 | 0 | 346 | Yes | 0 | No | 0 | 0 | 0 | 5833 | Yes | 2500 | No | 2500 | 18 | 18 | 4162 | Yes | 0 | No | 0 | 0 | 0 | 12582 | Yes | 8909 | 8909 | 2813 | 2813 | 29566 |  | 2022-12-15 |  | 2023-07-15 | Yes | 2024-02-28 |  | 2024-02-28 | No | 2024-03-15 |  | 2024-03-15 | No | 2024-08-27 |  | 2024-08-27 | No |  |  | 2027-10-15 |  | 0 | Yes | Yes | No | No
29 | 01 | 4627 | MEN | 101 | South Fork Eel River Bridge Seismic | Near Piercy, from 0.4 mile south to 0.2 mile north of South Fork Eel River Bridge No 10-0218 (PM R106.57); also in Humboldt County (PM T0.0/T0.1). | Seismic bridge retrofit, bridge rail upgrade, and restripe for wider shoulders and bicycle access. | 739 | Yes | 739 | 729 | 729 | 729 | No | 1028 | Yes | 1028 | 961 | 961 | 1077 | Yes | 248 | Yes | 248 | 9 | 9 | 118 | No | 1030 | Yes | 1030 | 0 | 0 | 1074 | Yes | 0 | No | 0 | 3 | 3 | 3 | Yes | 4944 | Yes | 4944 | 0 | 0 | 4944 | No | 7989 | 7989 | 1702 | 1702 | 7945 |  | 2020-10-01 | 2020-12-24 |  |  | 2022-01-01 | 2021-12-15 |  |  | 2022-01-15 | 2022-03-28 |  |  | 2022-06-01 |  | 2022-09-23 | Yes |  |  | 2024-02-01 |  | 0 | Yes | No | No | No
30 | 01 | 4676 | MEN | 162 | COVELO PAVEMENT | Near Dos Rios, from Route 101 to 2.6 miles west of Grist Creek Bridge. | Rehabilitate roadway, upgrade guardrail and signs, apply High Friction Surface Treatment (HFST), replace Transportation Management System (TMS) elements, and enhance highway worker safety. (G13 Contingency). | 1810 | Yes | 1810 | 1756 | 1756 | 1756 | No | 1477 | No | 1477 | 0 | 0 | 1490 | Yes | 480 | No | 480 | 0 | 0 | 348 | No | 0 | No | 0 | 0 | 0 | 4984 | Yes | 109 | No | 109 | 2 | 2 | 92 | No | 0 | No | 0 | 0 | 0 | 36583 | Yes | 3876 | 3876 | 1758 | 1758 | 45253 |  | 2022-06-17 | 2022-06-10 |  |  | 2023-10-01 |  | 2023-10-01 | No | 2023-10-15 |  | 2023-10-15 | No | 2024-02-15 |  | 2024-02-15 | No |  |  | 2025-12-01 |  | 0 | No | Yes | No | No
31 | 01 | 4677 | MEN | 101 | Ridgewood Class 1 Pavement | Near Willits, from 1.1 miles north of West Road to 0.6 mile south of Haehl Creek Bridge. | Rehabilitate pavement, replace concrete median barrier, rehabilitate drainage systems, and upgrade guardrail, signs, lighting, and Transportation Management System (TMS) elements. | 561 | Yes | 561 | 471 | 471 | 471 | No | 910 | Yes | 910 | 334 | 334 | 939 | Yes | 33 | Yes | 33 | 2 | 2 | 22 | No | 3457 | No | 3457 | 0 | 0 | 3428 | No | 39 | No | 39 | 1 | 1 | 1 | No | 47888 | No | 47888 | 0 | 0 | 32229 | No | 52888 | 52888 | 808 | 808 | 37090 | 2021-12-08 | 2021-09-24 | 2021-09-24 |  |  | 2022-10-03 |  | 2022-11-03 | No | 2022-10-15 |  | 2022-11-15 | No | 2023-02-28 |  | 2023-03-03 | No |  |  | 2025-12-01 |  | 0 | No | No | No | No
32 | 01 | 4678 | MEN | 101 | OILWELL Class 1 Pavement | Near Willits, from 0.6 mile north of Upp Creek Bridge to 2.6 miles north of Ryan Creek Road. | Rehabilitate pavement and upgrade guardrail and signs. | 886 | Yes | 886 | 719 | 719 | 719 | No | 814 | Yes | 814 | 162 | 162 | 816 | Yes | 27 | Yes | 27 | 2 | 2 | 26 | No | 2217 | No | 2217 | 0 | 0 | 2178 | No | 16 | No | 16 | 0 | 0 | 14 | No | 10203 | No | 10203 | 0 | 0 | 9785 | No | 14163 | 14163 | 883 | 883 | 13538 |  | 2021-11-01 | 2021-10-28 |  |  | 2023-06-19 |  | 2023-07-06 | Yes | 2023-07-04 |  | 2023-07-24 | No | 2023-12-20 |  | 2024-01-03 | No |  |  | 2025-07-15 |  | 0 | Yes | No | No | No
33 | 01 | 4682 | MEN | 1 | Jack Peters Cr Bridge | Near the Mendocino community, at Jack Peters Creek Bridge No 10-0150 (PM 51.87). | Bridge rail upgrade and widening. | 968 | Yes | 968 | 957 | 957 | 957 | No | 1935 | Yes | 1935 | 565 | 565 | 2163 | Yes | 260 | Yes | 260 | 17 | 17 | 188 | No | 4000 | No | 4000 | 0 | 0 | 3573 | No | 385 | No | 385 | 13 | 13 | 717 | Yes | 13250 | No | 13250 | 0 | 0 | 8731 | No | 20798 | 20798 | 1552 | 1552 | 16329 |  | 2021-04-09 | 2022-02-25 |  |  | 2022-04-15 |  | 2023-07-27 | Yes | 2022-05-06 |  | 2023-08-15 | Yes | 2022-08-31 |  | 2024-01-24 | Yes |  |  | 2025-10-15 |  | 0 | Yes | Yes | Yes | Yes
34 | 01 | 4692 | MEN | 162 | Eel River Bridge Replacement | Near Longvale, from 8.2 miles to 8.3 miles east of Route 101 at Eel River Bridge No 10-0236. | Bridge seismic retrofit. | 1532 | Yes | 1532 | 1471 | 1471 | 1471 | No | 1881 | Yes | 1881 | 1860 | 1860 | 3279 | Yes | 364 | Yes | 364 | 311 | 311 | 505 | Yes | 4179 | No | 4179 | 0 | 0 | 4833 | Yes | 251 | No | 251 | 48 | 48 | 251 | No | 8150 | No | 8150 | 0 | 0 | 14392 | Yes | 16357 | 16357 | 3690 | 3690 | 24731 |  | 2020-10-01 | 2020-12-15 |  |  | 2021-12-30 |  | 2022-07-19 | Yes | 2022-01-15 |  | 2022-08-02 | Yes | 2022-06-01 |  | 2022-11-29 | Yes |  |  | 2026-12-01 |  | 0 | Yes | Yes | No | No
35 | 01 | 4694 | MEN | 101 | LONGVALE REHAB | Near Willits, from 0.5 mile south of Shimmins Ridge Road to north of Old Sherwood Road. | Rehabilitate roadway and upgrade guardrail and Transportation Management System (TMS) elements. | 820 | Yes | 820 | 218 | 218 | 761 | No | 732 | No | 732 | 0 | 0 | 757 | Yes | 126 | No | 126 | 0 | 0 | 115 | No | 2871 | No | 2871 | 0 | 0 | 2365 | No | 0 | No | 0 | 0 | 0 | 0 | No | 26973 | No | 26973 | 0 | 0 | 23411 | No | 31522 | 31522 | 218 | 218 | 27409 |  | 2022-09-01 |  | 2022-09-01 | No | 2023-10-02 |  | 2023-10-02 | No | 2023-10-16 |  | 2023-10-16 | No | 2024-02-15 |  | 2024-04-15 | No |  |  | 2024-12-02 |  | 0 | Yes | Yes | Yes | Yes
36 | 01 | 4696 | MEN | 1 | Rockport to Leggett CAPM | Near Leggett, from north of Rockport Street to Route 101 (PM 87.85/105.580). | Rehabilitate pavement and upgrade guardrail and Transportation Management System (TMS) elements. | 531 | Yes | 531 | 515 | 515 | 515 | No | 726 | Yes | 726 | 61 | 61 | 976 | Yes | 133 | Yes | 133 | 2 | 2 | 42 | No | 1865 | No | 1865 | 0 | 0 | 1641 | No | 20 | No | 20 | 7 | 7 | 19 | No | 23400 | No | 23400 | 0 | 0 | 23350 | No | 26675 | 26675 | 585 | 585 | 26543 |  | 2021-12-01 | 2021-12-22 |  |  | 2023-01-06 |  | 2023-01-06 | No | 2023-01-20 |  | 2023-01-20 | No | 2023-05-01 |  | 2023-05-01 | No |  |  | 2025-12-01 |  | 0 | No | No | No | No
37 | 01 | 4697 | MEN | 1 | Elk to Mendocino CAPM | Near the Mendocino community, from south of Philo Greenwood Road to north of Little Lake Road. | Rehabilitate pavement, upgrade guardrail, and replace rumble strips. | 701 | Yes | 701 | 719 | 719 | 719 | Yes | 900 | Yes | 900 | 34 | 34 | 1276 | Yes | 111 | Yes | 111 | 9 | 9 | 104 | No | 2502 | No | 2502 | 0 | 0 | 2724 | Yes | 38 | No | 38 | 2 | 2 | 11 | No | 27321 | No | 27321 | 0 | 0 | 24350 | No | 31573 | 31573 | 764 | 764 | 29184 |  | 2021-12-01 | 2021-12-01 |  |  | 2023-07-17 |  | 2023-07-17 | No | 2023-07-31 |  | 2023-07-31 | No | 2024-01-08 |  | 2024-01-08 | No |  |  | 2025-10-01 |  | 0 | No | Yes | No | No
38 | 01 | 4710 | MEN | 271 | McCoy Creek Revegetation | Near Piercy, from 0.7 mile north of Route 271/101 Separation Bridge No 10-0217 to 0.4 mile south of Sidehill Viaduct No 10-0100. | Mitigation planting and monitoring for EA 0A840. | 0 | No | 0 | 0 | 0 | 0 | No | 0 | No | 0 | 0 | 0 | 0 | No | 0 | No | 0 | 0 | 0 | 0 | No | 172 | Yes | 172 | 72 | 72 | 195 | Yes | 0 | No | 0 | 0 | 0 | 0 | No | 205 | Yes | 205 | 44 | 44 | 205 | No | 377 | 377 | 116 | 116 | 400 |  | 2017-04-27 | 2017-04-27 |  |  | 2018-04-15 | 2018-04-15 |  |  | 2020-07-15 | 2020-08-27 |  |  | 2020-09-15 | 2020-09-15 |  |  |  |  | 2022-08-01 |  | 377 | No | No | No | No
39 | 01 | 4745 | MEN | 101 | Reconstruct Drainage | Near Laytonville, Legget, and Piercy, from 0.8 mile south of Old Sherwood Road to 0.7 mile north of Piercy Separation (Route 271). | Replace and rehabilitate culverts. | 465 | Yes | 465 | 458 | 458 | 458 | No | 937 | Yes | 937 | 580 | 580 | 916 | No | 121 | Yes | 121 | 48 | 48 | 102 | No | 1500 | No | 1500 | 0 | 0 | 1679 | Yes | 103 | No | 103 | 77 | 77 | 103 | No | 4600 | No | 4600 | 0 | 0 | 4770 | Yes | 7726 | 7726 | 1163 | 1163 | 8028 |  | 2021-10-15 | 2021-10-15 |  |  | 2022-07-01 | 2022-06-16 |  |  | 2022-07-14 |  | 2022-10-07 | No | 2022-12-21 |  | 2023-03-21 | Yes |  |  | 2024-09-02 |  | 0 | No | No | No | No
40 | 01 | 4753 | MEN | 1 | Salmon Creek Sandblast Waste Abatement | Near Albion, from 2.2 miles north of Route 128 Junction to 0.2 mile north of Salmon Creek Bridge No 10-0134. | Lead abatement for bridge replacement project EA 40140. | 1000 | Yes | 1000 | 961 | 961 | 1823 | Yes | 2000 | No | 2000 | 0 | 0 | 1814 | No | 350 | No | 350 | 0 | 0 | 454 | Yes | 3000 | No | 3000 | 0 | 0 | 2715 | No | 5176 | No | 5176 | 0 | 0 | 5327 | Yes | 9000 | No | 9000 | 0 | 0 | 10209 | Yes | 20526 | 20526 | 961 | 961 | 22342 |  | 2021-03-11 |  | 2024-03-15 | Yes | 2022-03-01 |  | 2025-11-06 | Yes | 2022-03-17 |  | 2025-11-26 | Yes | 2022-07-20 |  | 2026-04-29 | Yes |  |  | 2026-12-31 |  | 0 | Yes | Yes | Yes | Yes
41 | 01 | 7002 | HUM | 101 | HUM-101/MEN-271 Culverts | Near Garberville, from Alderpoint Road Overcrossing to 1.3 miles south of Myers Flat Separation; also in Mendocino County, on Route 271 near Piercy, from Bear Pen Road to 0.5 mile north of Route 101 Separation (PM 16.1/20.0). | Rehabilitate or replace drainage culverts. | 978 | Yes | 978 | 953 | 953 | 953 | No | 866 | Yes | 866 | 746 | 746 | 812 | No | 309 | Yes | 309 | 174 | 174 | 230 | No | 1118 | Yes | 1118 | 1 | 1 | 1136 | Yes | 94 | No | 94 | 73 | 73 | 68 | No | 2236 | Yes | 2236 | 0 | 0 | 2487 | Yes | 5601 | 5601 | 1947 | 1947 | 5686 |  | 2020-03-25 | 2020-03-25 |  |  | 2021-03-01 | 2021-12-01 |  |  | 2021-03-01 | 2022-01-03 |  |  | 2021-08-01 |  | 2022-07-18 | Yes |  |  | 2024-12-02 |  | 0 | Yes | No | No | No
42 | 01 | 7029 | VAR | VAR | COMBINED TMS | IN LAKE AND MENDOCINO COUNTIES ON VARIOUS ROUTES AND AT VARIOUS LOCATIONS | Transportation Management Systems | 1205 | No | 1205 | 1118 | 1118 | 1118 | No | 1770 | No | 1770 | 1527 | 1527 | 1527 | No | 236 | No | 236 | 91 | 91 | 92 | No | 1748 | No | 1748 | 715 | 715 | 2143 | Yes | 0 | No | 0 | 12 | 12 | 0 | No | 4466 | No | 4466 | 2155 | 2155 | 4466 | No | 9425 | 9425 | 5618 | 5618 | 9346 |  |  | 2020-01-02 |  |  |  | 2021-02-24 |  |  |  | 2021-04-06 |  |  |  | 2021-11-02 |  |  |  |  | 2023-12-01 |  | 4466 | No | Yes | No | No
43 | 02 | 2711 | SHA | 299 | Lake Boulevard Pavement | In and near Redding, from Route 299 to east of Hootenanny Lane; also on Route 273 from 0.1 mile south to 0.1 mile north of Lake Boulevard (PM 18.5/18.7). | Rehabilitate pavement, upgrade facilities to meet Americans with Disabilities Act (ADA) standards, upgrade Transportation Management System (TMS) elements, rehabilitate drainage systems, and add complete streets elements such as multi-use bi-directional path, widen and overlay existing Class 1 bike path, and reconstruct onramp. | 895 | Yes | 895 | 880 | 880 | 880 | No | 1236 | Yes | 1236 | 89 | 89 | 1280 | Yes | 400 | Yes | 400 | 17 | 17 | 367 | No | 2410 | No | 2410 | 0 | 0 | 2292 | No | 468 | No | 468 | 38 | 38 | 468 | No | 30361 | No | 30361 | 0 | 0 | 26090 | No | 35770 | 35770 | 1024 | 1024 | 31377 |  | 2022-02-15 | 2022-04-12 |  |  | 2023-04-03 |  | 2023-05-05 | No | 2023-05-01 |  | 2023-05-26 | No | 2023-08-22 |  | 2023-10-24 | No |  |  | 2024-12-09 |  | 0 | No | No | No | No
44 | 02 | 3467 | LAS | 299 | Bieber to Adin Pavement | Near Adin, from 3.6 miles east of Bieber Lookout Road/Susanville Road to Adin Maintenance Station; also in Modoc County, from Lassen County line to 0.6 mile east of County Road 87 (PM 0.0/0.5 and PM 1.0/1.8); also in Modoc County, on Route 139 at junction with Route 299 (PM 0.116/R0.231). | Roadway rehabilitation. | 1790 | Yes | 1790 | 1680 | 1680 | 1680 | No | 1330 | Yes | 1330 | 1038 | 1038 | 1038 | No | 325 | Yes | 325 | 178 | 178 | 247 | No | 2150 | Yes | 2150 | 1597 | 1597 | 2174 | Yes | 811 | No | 811 | 1036 | 1036 | 1037 | Yes | 18196 | Yes | 18196 | 17666 | 17666 | 18196 | No | 24602 | 24602 | 23195 | 23195 | 24372 | 2019-03-14 | 2019-01-18 | 2019-01-18 |  |  | 2020-01-17 | 2020-01-23 |  |  | 2020-02-21 | 2020-03-16 |  |  | 2020-09-05 | 2020-08-13 |  |  |  |  | 2023-01-04 |  | 18196 | No | No | No | No
45 | 02 | 3468 | LAS | 036 | Good Fred | In Lassen County near Westwood from 1.3 miles west of Goodrich Creek Bridge to 1.0 mile west of Willard Creek Road. | Rehabilitate Roadway and Replace Bridge | 4484 | Yes | 4484 | 4435 | 4435 | 4435 | No | 3300 | Yes | 3300 | 3281 | 3281 | 3281 | No | 400 | Yes | 400 | 403 | 403 | 403 | Yes | 3700 | Yes | 3700 | 3569 | 3569 | 5091 | Yes | 9844 | No | 9844 | 4016 | 4016 | 4021 | No | 34155 | Yes | 34155 | 29358 | 29358 | 34155 | No | 55883 | 55883 | 45062 | 45062 | 51386 | 2018-10-17 | 2018-05-25 | 2018-05-25 |  |  | 2019-08-01 | 2019-12-06 |  |  | 2019-08-14 | 2019-12-09 |  |  | 2019-11-13 | 2020-06-03 |  |  |  |  | 2022-11-04 |  | 32890 | Yes | Yes | No | No
46 | 02 | 3485 | TRI | 3 | Swift Creek Bridge Replacement | Near Trinity Center, from 1.3 miles south to 0.7 mile north of Swift Creek Bridge No0059. | Replace Swift Creek Bridge No 05-0059. | 1530 | Yes | 1530 | 1506 | 1506 | 1506 | No | 2048 | Yes | 2048 | 1982 | 1982 | 1982 | No | 284 | Yes | 284 | 258 | 258 | 284 | No | 2500 | Yes | 2500 | 1997 | 1997 | 3175 | Yes | 751 | No | 751 | 401 | 401 | 501 | No | 13199 | Yes | 13199 | 8423 | 8423 | 13199 | No | 20312 | 20312 | 14567 | 14567 | 20647 |  | 2019-01-17 | 2018-12-13 |  |  | 2020-04-16 | 2020-06-19 |  |  | 2020-05-21 | 2020-06-26 |  |  | 2020-12-01 | 2021-03-25 |  |  |  |  | 2025-01-27 |  | 13198 | Yes | Yes | No | No
47 | 02 | 3515 | TEH | 5 | Sacramento River Bridge Seismic | In Red Bluff, at Sacramento River Bridge No 08-0095L/R. | Retrofit bridges. | 2290 | Yes | 2290 | 2227 | 2227 | 2227 | No | 2009 | Yes | 2009 | 1912 | 1912 | 1912 | No | 280 | Yes | 280 | 79 | 79 | 193 | No | 3962 | Yes | 3962 | 2320 | 2320 | 3930 | No | 152 | No | 152 | 68 | 68 | 71 | No | 15653 | Yes | 15240 | 13830 | 13441 | 15602 | No | 24346 | 23933 | 20436 | 20047 | 23935 | 2019-03-14 | 2018-05-21 | 2018-05-21 |  |  | 2020-02-12 | 2020-02-11 |  |  | 2020-03-04 | 2020-03-17 |  |  | 2020-06-24 | 2020-07-23 |  |  |  |  | 2023-07-30 |  | 14512 | No | No | No | No
48 | 02 | 3516 | TRI | 299 | Sis Tri Deck Rehab | In Trinity County, on Routes 299 and 36 and in Siskiyou County on Route 96 at various locations. | Bridge preventative maintenance at 9 bridges. | 1030 | Yes | 1030 | 536 | 536 | 536 | No | 1400 | Yes | 1400 | 601 | 601 | 601 | No | 150 | Yes | 150 | 53 | 53 | 68 | No | 1910 | Yes | 1910 | 1321 | 1321 | 1861 | No | 40 | No | 40 | 3 | 3 | 23 | No | 9454 | Yes | 9454 | 8588 | 8588 | 9754 | Yes | 13984 | 13984 | 11102 | 11102 | 12843 |  | 2018-09-28 | 2018-09-24 |  |  | 2019-09-06 | 2019-09-06 |  |  | 2019-09-13 | 2019-09-20 |  |  | 2020-02-14 | 2020-02-06 |  |  |  |  | 2022-10-11 |  | 8634 | No | No | No | No
49 | 02 | 3546 | SIS | 3 | Lower Moffett Creek Scour | Near Fort Jones, from 0.3 mile south to 0.3 mile north of West Moffett Creek Road at Moffett Creek Bridge No 02-0042. | Bridge replacement. | 1570 | Yes | 1570 | 1520 | 1520 | 1520 | No | 970 | Yes | 970 | 958 | 958 | 958 | No | 80 | Yes | 80 | 28 | 28 | 46 | No | 1540 | Yes | 1540 | 832 | 832 | 1394 | No | 237 | No | 237 | 28 | 28 | 105 | No | 4705 | Yes | 4705 | 4146 | 4146 | 4705 | No | 9102 | 9102 | 7512 | 7512 | 8728 |  | 2019-08-29 | 2019-08-29 |  |  | 2020-07-31 | 2020-03-23 |  |  | 2020-08-28 | 2020-12-07 |  |  | 2021-02-26 | 2021-04-16 |  |  |  |  | 2023-01-05 |  | 4705 | No | No | No | No
50 | 02 | 3549 | TEH | Var | District Wide Scour Counter-Measures | In Tehama County, on Routes 5, 32, and 36 at various locations; also in Shasta County on Routes 5 and 44; also in Lassen County on Route 299 at various locations. | Bridge scour prevention at nine bridges. | 920 | Yes | 920 | 714 | 714 | 714 | No | 720 | Yes | 720 | 683 | 683 | 683 | No | 265 | Yes | 265 | 176 | 176 | 192 | No | 714 | Yes | 714 | 468 | 468 | 711 | No | 517 | No | 517 | 64 | 64 | 66 | No | 2205 | Yes | 2205 | 1989 | 1989 | 2205 | No | 5341 | 5341 | 4094 | 4094 | 4571 |  | 2019-02-18 | 2019-03-27 |  |  | 2020-02-28 | 2020-02-20 |  |  | 2020-03-30 | 2020-06-26 |  |  | 2020-08-26 | 2020-10-29 |  |  |  |  | 2022-11-01 |  | 2205 | No | No | No | No
51 | 02 | 3586 | TRI | 3 | Trinity 3 Drainage | Near Trinity Center, from 0.2 mile north of East Weaver Creek Road to 1.7 miles north of Bowerman Ridge Road at various locations. | Drainage system restoration. | 1550 | Yes | 1550 | 974 | 974 | 974 | No | 1220 | Yes | 1220 | 1196 | 1196 | 1196 | No | 550 | Yes | 550 | 139 | 139 | 283 | No | 1580 | Yes | 1580 | 270 | 270 | 1360 | No | 79 | No | 79 | 19 | 19 | 20 | No | 2242 | Yes | 2242 | 1428 | 1428 | 2242 | No | 7221 | 7221 | 4026 | 4026 | 6075 |  | 2018-09-01 | 2018-11-01 |  |  | 2019-09-03 | 2020-03-06 |  |  | 2019-10-10 | 2020-06-25 |  |  | 2020-02-13 | 2020-11-17 |  |  |  |  | 2022-11-25 |  | 2241 | No | No | No | No
52 | 02 | 3587 | PLU | 70 | Plumas 70 Drainage | In Plumas County, from 0.4 mile east of Butte County line to 3.3 miles west of Route 89 at various locations. | Drainage rehabilitation. | 1200 | Yes | 1200 | 884 | 884 | 884 | No | 840 | Yes | 840 | 710 | 710 | 710 | No | 600 | Yes | 600 | 58 | 58 | 122 | No | 1000 | Yes | 1000 | 265 | 265 | 795 | No | 89 | No | 89 | 69 | 69 | 87 | No | 2472 | Yes | 2472 | 1806 | 1806 | 2472 | No | 6201 | 6201 | 3792 | 3792 | 5070 |  | 2018-09-01 | 2018-08-31 |  |  | 2019-06-04 | 2019-12-16 |  |  | 2019-07-11 | 2020-06-26 |  |  | 2020-02-13 | 2020-12-29 |  |  |  |  | 2023-07-14 |  | 2472 | No | No | No | Yes
53 | 02 | 3589 | MOD | 139 | Modoc 139 Drainage | Near Canby, from 1.3 miles north of Howards Gulch Bridge to 0.1 mile south of Clear Lake Road, at various locations. | Improve drainage facilities by repairing or replacing culverts. | 890 | Yes | 890 | 635 | 635 | 635 | No | 440 | Yes | 440 | 352 | 352 | 422 | No | 250 | Yes | 250 | 70 | 70 | 150 | No | 700 | No | 700 | 0 | 0 | 622 | No | 71 | No | 71 | 3 | 3 | 69 | No | 3045 | No | 3045 | 0 | 0 | 2190 | No | 5396 | 5396 | 1060 | 1060 | 4088 |  | 2021-05-15 | 2021-05-26 |  |  | 2022-05-22 | 2022-05-18 |  |  | 2022-06-01 | 2022-06-09 |  |  | 2022-09-20 |  | 2022-12-06 | No |  |  | 2024-01-08 |  | 0 | No | No | No | No
54 | 02 | 3614 | SIS | 5 | Sac River BOH Deck Replacement | In Dunsmuir, from Central Dunsmuir Undercrossing to 0.1 mile north of Siskiyou Avenue at Sacramento River Bridge and Overhead No 02-0002. | Replace southbound bridge deck. This is a Construction Manager/General Contractor (CMGC) project. (G13 Contingency). | 1440 | Yes | 1440 | 998 | 998 | 998 | No | 2660 | Yes | 2660 | 1449 | 1449 | 2622 | No | 450 | Yes | 450 | 328 | 328 | 448 | No | 0 | No | 0 | 0 | 0 | 2575 | Yes | 269 | No | 269 | 36 | 36 | 117 | No | 0 | No | 0 | 0 | 0 | 11786 | Yes | 4819 | 4819 | 2811 | 2811 | 18546 |  | 2020-04-15 | 2020-04-14 |  |  | 2021-12-21 | 2022-06-01 |  |  | 2022-01-21 | 2022-06-30 |  |  | 2022-07-25 |  | 2023-04-14 | Yes |  |  | 2026-05-01 |  | 0 | No | Yes | No | No
55 | 02 | 3618 | SHA | 299 | Burney CAPM | Near Burney, from 2.6 miles east of Carberry Flat Road to 0.3 mile east of Burney Mountain Power Road. | Rehabilitate pavement, upgrade guardrail, improve drainage, reconstruct sidewalks, and make curbs Americans with Disabilities Act (ADA) compliant. | 1430 | Yes | 1430 | 1119 | 1119 | 1119 | No | 1630 | Yes | 1630 | 1613 | 1613 | 2274 | Yes | 1020 | Yes | 1020 | 912 | 912 | 1709 | Yes | 2430 | No | 2430 | 0 | 0 | 2765 | Yes | 436 | No | 436 | 198 | 198 | 436 | No | 14800 | No | 14800 | 0 | 0 | 11749 | No | 21746 | 21746 | 3842 | 3842 | 20052 |  | 2020-09-08 | 2021-01-25 |  |  | 2022-03-04 | 2022-05-18 |  |  | 2022-04-04 | 2022-06-23 |  |  | 2022-08-30 |  | 2022-12-13 | Yes |  |  | 2025-01-28 |  | 0 | No | Yes | No | No
56 | 02 | 3619 | PLU | 70 | Cromberg Rehab | In and near Cromberg and Portola, from Gill Ranch Road to 0.2 mile west of Big Grizzly Creek Bridge. | Rehabilitate roadway, repair or replace culverts, upgrade guardrail, upgrade bridge railing at Humbug Creek Bridge No 09-0022, and make pedestrian facilities Americans with Disabilities Act (ADA) compliant. (G13 Contingency). | 5139 | Yes | 5139 | 5120 | 5120 | 5120 | No | 2620 | Yes | 2620 | 1669 | 1669 | 2799 | Yes | 1332 | Yes | 1332 | 1088 | 1088 | 1506 | Yes | 0 | No | 0 | 0 | 0 | 4839 | Yes | 911 | No | 911 | 361 | 361 | 767 | No | 0 | No | 0 | 0 | 0 | 90815 | Yes | 10002 | 10002 | 8238 | 8238 | 105846 | 2021-12-08 | 2021-09-01 | 2021-09-01 |  |  | 2022-06-22 |  | 2022-10-27 | Yes | 2022-06-30 |  | 2022-11-17 | Yes | 2022-12-27 |  | 2023-04-04 | Yes |  |  | 2026-01-12 |  | 0 | Yes | Yes | No | No
57 | 02 | 3620 | SIS | 96 | Portuguese and Cade Creek | Near Happy Camp, from 0.9 mile west to 0.4 mile west of Gordons Ferry Road at Cade Creek (PM 43.4 to 43.8); also near Seiad Valley at Portuguese Creek (PM 57.0). | Replace deteriorated large-diameter culverts with natural-bottom structures, reduce fish passage barriers, and adjust new approaches. (Additional contribution of $100,000 for PA&ED from US Fish and Wildlife Service (USFWS) Grant.). | 1820 | Yes | 1720 | 1619 | 1519 | 1619 | No | 2740 | Yes | 2740 | 783 | 783 | 2465 | No | 185 | Yes | 185 | 35 | 35 | 199 | Yes | 2840 | No | 2840 | 0 | 0 | 2332 | No | 36 | No | 36 | 4 | 4 | 35 | No | 12200 | No | 12200 | 0 | 0 | 11155 | No | 19821 | 19721 | 2441 | 2341 | 17805 |  | 2021-10-05 | 2021-10-05 |  |  | 2023-01-09 |  | 2022-12-14 | No | 2023-06-01 |  | 2023-01-26 | No | 2023-10-31 |  | 2023-07-05 | No |  |  | 2026-05-04 |  | 0 | No | No | No | No
58 | 02 | 3629 | SIS | 96 | Horse Creek Bridge Replacement | Near Horse Creek, at Horse Creek Bridge No 02-0117, from 0.4 mile west of Klamath River Bridge to 2.0 miles west of Kohl Creek. | Replace bridge on new alignment to correct scour critical conditions, improve safety, and reduce operational deficiencies. | 2640 | Yes | 2640 | 2095 | 2095 | 2095 | No | 2810 | Yes | 2810 | 178 | 178 | 2284 | No | 830 | Yes | 830 | 85 | 85 | 702 | No | 4300 | No | 4300 | 0 | 0 | 3365 | No | 993 | No | 993 | 498 | 498 | 744 | No | 32300 | No | 32300 | 0 | 0 | 28167 | No | 43873 | 43873 | 2856 | 2856 | 37357 |  | 2022-01-15 | 2022-02-01 |  |  | 2023-05-30 |  | 2023-05-30 | No | 2023-07-10 |  | 2023-05-30 | No | 2023-11-07 |  | 2023-11-07 | No |  |  | 2027-02-02 |  | 0 | No | No | No | No
59 | 02 | 3633 | TRI | 3 | Trinity Four Bridges | In Trinity County, at Dobbins Gulch Bridge No 05-0042 (PM 0.6), Stuart Fork Bridge No 05-0055 (PM 43.9) and Mule Creek Bridge No 05-0056 (PM 48.5); also on Route 299, at Grass Valley Creek Bridge No 05-0013 (PM 65.5). | Repair unsound concrete, clean and paint structural steel, repair bearings and anchor joints, replace joint seals, place deck-on-deck replacement, and replace guardrail and bridge barrier. | 900 | Yes | 900 | 723 | 723 | 723 | No | 1105 | Yes | 1105 | 1006 | 1006 | 1093 | No | 230 | Yes | 230 | 109 | 109 | 184 | No | 2060 | Yes | 2060 | 0 | 0 | 1624 | No | 206 | No | 206 | 34 | 34 | 84 | No | 4807 | Yes | 4807 | 0 | 0 | 4571 | No | 9308 | 9308 | 1872 | 1872 | 8279 |  | 2020-07-02 | 2020-10-08 |  |  | 2022-01-21 | 2022-02-16 |  |  | 2022-02-22 | 2022-03-25 |  |  | 2022-08-09 |  | 2022-08-01 | No |  |  | 2026-01-07 |  | 0 | No | No | No | No
60 | 02 | 3642 | TEH | 99 | Champlin Slough | Near Los Molinos, at Champlin Slough Bridge No 08-0006. | Replace bridge to correct scour critical conditions. | 1100 | Yes | 1100 | 927 | 927 | 927 | No | 1170 | Yes | 1170 | 1013 | 1013 | 1013 | No | 90 | Yes | 90 | 30 | 30 | 86 | No | 990 | Yes | 990 | 536 | 536 | 1318 | Yes | 90 | No | 90 | 38 | 38 | 109 | Yes | 3630 | Yes | 3630 | 1887 | 1887 | 3630 | No | 7070 | 7070 | 4431 | 4431 | 7083 |  | 2020-05-05 | 2020-05-07 |  |  | 2021-10-22 | 2021-05-05 |  |  | 2021-11-24 | 2021-06-28 |  |  | 2022-04-19 | 2021-12-02 |  |  |  |  | 2023-07-14 |  | 3630 | No | Yes | No | No
61 | 02 | 3643 | SIS | 3 | Yreka Rehab | In Yreka, from 0.4 mile north of Laura Lane to Juniper Drive; also on Route 263, from Route 3 to 1.0 mile south of Long Gulch Road (PM 49.07/49.41). | Reconstruct pavement structural section, replace sidewalk, driveways, curb ramps and pedestrian signals to meet current Americans with Disabilities Act (ADA) standards, designate bikeways with new signage and pavement delineation. This is a Construction Manager/General Contractor (CMGC) project. | 3758 | Yes | 3758 | 3377 | 3377 | 3377 | No | 3703 | Yes | 3703 | 3529 | 3529 | 3703 | No | 5880 | Yes | 5880 | 2591 | 2591 | 4571 | No | 0 | Yes | 0 | 0 | 0 | 8881 | Yes | 1482 | No | 1482 | 1163 | 1163 | 3117 | Yes | 0 | Yes | 0 | 0 | 0 | 52950 | Yes | 14823 | 14823 | 10660 | 10660 | 76599 | 2020-08-12 | 2020-04-21 | 2020-04-21 |  |  | 2022-03-07 | 2022-03-08 |  |  | 2022-03-21 | 2022-03-21 |  |  | 2022-07-21 |  | 2022-08-26 | No |  |  | 2025-11-17 |  | 0 | No | Yes | No | No
62 | 02 | 3660 | SIS | 96 | Scott River Bridge | Near Hamburg, at Scott River Bridge No 02-0079. | Replace existing bridge deck and widen bridge. (Long Lead Project). | 2130 | Yes | 2130 | 0 | 0 | 2107 | No | 0 | No | 0 | 0 | 0 | 1670 | Yes | 0 | No | 0 | 0 | 0 | 174 | Yes | 0 | No | 0 | 0 | 0 | 3200 | Yes | 0 | No | 0 | 0 | 0 | 543 | Yes | 0 | No | 0 | 0 | 0 | 12060 | Yes | 2130 | 2130 | 0 | 0 | 19754 |  |  |  | 2025-10-06 |  |  |  | 2026-10-06 |  |  |  | 2027-03-05 |  |  |  | 2027-06-26 |  |  |  | 2030-01-03 |  | 0 | No | Yes | No | No
63 | 02 | 3668 | TRI | 299 | Trinity Culverts | Near Salyer and Junction City, at various locations from 0.2 mile east of Madrone Street to 0.4 mile west of Slattery Pond Road. | Rehabilitate culverts. | 930 | Yes | 930 | 800 | 800 | 800 | No | 980 | Yes | 980 | 597 | 597 | 597 | No | 330 | Yes | 330 | 118 | 118 | 198 | No | 760 | Yes | 760 | 14 | 14 | 778 | Yes | 137 | No | 137 | 235 | 235 | 238 | Yes | 2737 | Yes | 2737 | 1 | 1 | 2737 | No | 5874 | 5874 | 1765 | 1765 | 5348 |  | 2020-07-01 | 2020-10-31 |  |  | 2021-07-19 | 2021-09-15 |  |  | 2021-08-19 | 2021-10-18 |  |  | 2021-12-14 | 2022-05-20 |  |  |  |  | 2024-01-02 |  | 2736 | No | No | No | No
64 | 02 | 3685 | SIS | 5 | Dunsmuir GAP | In and near Dunsmuir and Mt. | Shasta, from Sacramento River Bridge Overhead to Black Butte Overhead. Roadway rehabilitation. This is a Construction Manager/General Contractor (CMGC) project. (G13 Contingency). | 1982 | Yes | 1982 | 1607 | 1607 | 1607 | No | 6057 | Yes | 6057 | 4356 | 4356 | 5884 | No | 95 | Yes | 95 | 76 | 76 | 89 | No | 0 | No | 0 | 0 | 0 | 12854 | Yes | 135 | No | 135 | 38 | 38 | 135 | No | 0 | No | 0 | 0 | 0 | 101955 | Yes | 8269 | 8269 | 6077 | 6077 | 122524 | 2021-05-12 | 2021-01-15 | 2021-01-15 |  |  | 2021-12-21 | 2022-06-01 |  |  | 2022-03-10 | 2022-06-30 |  |  | 2022-08-02 |  | 2023-04-14 | Yes |  |  | 2026-05-01 |  | 0 | No | Yes | No | No
65 | 02 | 3697 | SIS | 5 | Grenada Pavement | Near Weed, from North Edgewood Overhead to north of Grenada Overcrossing. | Rehabilitate pavement, replace signs, add lighting, upgrade guardrail and Transportation Management System (TMS) elements, and rehabilitate drainage systems. | 2270 | Yes | 2270 | 1503 | 1503 | 1503 | No | 1890 | Yes | 1890 | 21 | 21 | 1670 | No | 40 | Yes | 40 | 0 | 0 | 29 | No | 3250 | No | 3250 | 0 | 0 | 2482 | No | 0 | No | 0 | 0 | 0 | 0 | No | 22130 | No | 22130 | 0 | 0 | 20350 | No | 29580 | 29580 | 1524 | 1524 | 26034 |  | 2022-01-18 | 2022-04-22 |  |  | 2022-07-18 |  | 2023-01-09 | Yes | 2023-02-27 |  | 2023-02-27 | No | 2023-09-12 |  | 2023-09-05 | No |  |  | 2025-01-07 |  | 0 | No | No | No | No
66 | 02 | 3699 | SHA | 5 | O Brien CAPM | Near Shasta Lake City, from north of Pit River Bridge to 1.8 miles north of Riverview Drive Undercrossing. | Rehabilitate pavement, upgrade guardrail and Transportation Management System (TMS) elements, and replace signs. | 890 | Yes | 890 | 777 | 777 | 777 | No | 1090 | Yes | 1090 | 9 | 9 | 1074 | No | 80 | Yes | 80 | 0 | 0 | 79 | No | 3650 | No | 3650 | 0 | 0 | 3408 | No | 54 | No | 54 | 2 | 2 | 22 | No | 25540 | No | 25540 | 0 | 0 | 25540 | No | 31304 | 31304 | 788 | 788 | 30900 |  | 2021-12-06 | 2022-06-20 |  |  | 2022-12-06 |  | 2023-01-25 | No | 2023-02-14 |  | 2023-02-14 | No | 2023-07-25 |  | 2023-09-05 | No |  |  | 2025-01-21 |  | 0 | No | No | No | No
67 | 02 | 3700 | PLU | 89 | Almanor West Rehab | Near Canyon Dam, from 0.6 mile north of Route 147 to Route 36 (PM 30.2/R42.185). | Rehabilitate roadway, upgrade guardrail and signs, rehabilitate drainage systems, and construct 3.7 miles of Class 1 bike lanes as complete streets. (G13 Contingency). | 1510 | Yes | 1510 | 1213 | 1213 | 1213 | No | 0 | Yes | 0 | 0 | 0 | 2074 | Yes | 0 | Yes | 0 | 0 | 0 | 86 | Yes | 0 | No | 0 | 0 | 0 | 1737 | Yes | 752 | No | 752 | 2 | 2 | 66 | No | 0 | No | 0 | 0 | 0 | 36400 | Yes | 2262 | 2262 | 1215 | 1215 | 41576 |  | 2022-06-16 | 2022-06-30 |  |  | 2024-03-12 |  | 2024-03-12 | No | 2024-04-12 |  | 2024-04-12 | No | 2024-08-27 |  | 2024-08-27 | No |  |  | 2026-12-31 |  | 0 | No | Yes | No | No
68 | 02 | 3701 | TRI | 299 | Del Loma Pavement | Near Del Loma, from 1.0 mile east of Trinity River Bridge to west of Prairie Creek Road. | Rehabilitate pavement, upgrade guardrail and Transportation Management System (TMS) elements, widen lanes to make standard, and rehabilitate drainage systems. | 1260 | Yes | 1260 | 1250 | 1250 | 1250 | No | 1360 | Yes | 1360 | 26 | 26 | 1391 | Yes | 70 | Yes | 70 | 1 | 1 | 45 | No | 1860 | No | 1860 | 0 | 0 | 1950 | Yes | 78 | No | 78 | 1 | 1 | 88 | Yes | 18790 | No | 18790 | 0 | 0 | 17016 | No | 23418 | 23418 | 1278 | 1278 | 21740 |  | 2022-05-03 | 2022-06-30 |  |  | 2023-07-03 |  | 2023-08-01 | No | 2023-08-28 |  | 2023-08-28 | No | 2024-01-02 |  | 2024-01-02 | No |  |  | 2024-12-04 |  | 0 | No | No | No | No
69 | 02 | 3706 | LAS | 44 | Shalas CAPM | Near Susanville, from Shasta County line to Plumas County line. | Rehabilitate pavement, upgrade guardrail and Transportation Management System (TMS) elements, and pave Maintenance Vehicle Pullouts (MVPs). | 850 | Yes | 850 | 834 | 834 | 834 | No | 1010 | Yes | 1010 | 7 | 7 | 1135 | Yes | 130 | Yes | 130 | 0 | 0 | 148 | Yes | 1730 | No | 1730 | 0 | 0 | 1608 | No | 116 | No | 116 | 0 | 0 | 116 | No | 35420 | No | 35420 | 0 | 0 | 36940 | Yes | 39256 | 39256 | 841 | 841 | 40781 |  | 2022-03-07 | 2022-03-01 |  |  | 2023-03-07 |  | 2023-03-07 | No | 2023-03-14 |  | 2023-03-14 | No | 2023-08-02 |  | 2023-09-05 | No |  |  | 2025-01-19 |  | 0 | No | No | No | No
70 | 02 | 3707 | TEH | 99 | VP2 | Near Los Molinos, from Butte County line to south of Los Molinos Creek Bridge. | Rehabilitate pavement, upgrade guardrail and Transportation Management System (TMS) elements, upgrade facilities to meet Americans with Disabilities Act (ADA) standards, rehabilitate drainage systems, and widen shoulders. (G13 Contingency). | 2090 | Yes | 2090 | 1210 | 1210 | 2354 | Yes | 2060 | No | 2060 | 0 | 0 | 2145 | Yes | 810 | No | 810 | 0 | 0 | 793 | No | 0 | No | 0 | 0 | 0 | 2646 | Yes | 744 | No | 744 | 1 | 1 | 769 | Yes | 0 | No | 0 | 0 | 0 | 33010 | Yes | 5704 | 5704 | 1211 | 1211 | 41717 |  | 2023-02-01 |  | 2023-03-01 | No | 2024-03-07 |  | 2024-03-01 | No | 2024-03-22 |  | 2024-04-25 | No | 2024-09-27 |  | 2024-10-22 | No |  |  | 2027-01-18 |  | 0 | No | Yes | No | No
71 | 02 | 3709 | PLU | 89 | Graeagle CAPM | Near Graeagle, from Sierra County line to Route 70. | Rehabilitate pavement, upgrade guardrail and signs, and widen shoulders. | 1290 | Yes | 1290 | 0 | 0 | 1241 | No | 1140 | No | 1140 | 0 | 0 | 970 | No | 230 | No | 230 | 0 | 0 | 210 | No | 2210 | No | 2210 | 0 | 0 | 1766 | No | 591 | No | 591 | 0 | 0 | 591 | No | 11200 | No | 11200 | 0 | 0 | 11200 | No | 16661 | 16661 | 0 | 0 | 15978 |  |  |  | 2024-08-06 |  |  |  | 2026-01-06 |  |  |  | 2026-03-03 |  |  |  | 2026-08-05 |  |  |  | 2027-12-20 |  | 0 | No | No | No | No
72 | 02 | 3712 | SIS | 97 | Dorris CAPM | In and near Dorris, from south of Sams Neck Road to Oregon State line; also on Route 161, from Route 97 to 0.4 mile east of Indian Tom Lake Road (PM 0.037/0.5). | Rehabilitate pavement and upgrade facilities to meet Americans with Disabilities Act (ADA) standards, and upgrade guardrail and Transportation Management System (TMS) elements. | 920 | Yes | 920 | 716 | 716 | 716 | No | 900 | Yes | 900 | 103 | 103 | 762 | No | 500 | Yes | 500 | 258 | 258 | 464 | No | 1120 | No | 1120 | 0 | 0 | 1079 | No | 170 | No | 170 | 53 | 53 | 170 | No | 13380 | No | 13380 | 0 | 0 | 12890 | No | 16990 | 16990 | 1130 | 1130 | 16081 |  | 2021-11-12 | 2021-12-24 |  |  | 2023-01-12 |  | 2023-01-27 | No | 2023-03-09 |  | 2023-03-16 | No | 2023-09-12 |  | 2023-09-05 | No |  |  | 2024-12-23 |  | 0 | No | No | No | No
73 | 02 | 3713 | PLU | 70 | Beckwourth CAPM | Near Portola, from west of Grizzly Road/Rocky Point Road to 0.9 mile west of Summit School Drive. | Rehabilitate pavement, add intersection lighting, upgrade signs and guardrail, install deer fencing, pave maintenance station parking lot, and rehabilitate drainage systems. (Additional contribution of $750,000 from Department of Water Resources.). | 1058 | Yes | 1058 | 980 | 980 | 1070 | Yes | 820 | No | 820 | 0 | 0 | 728 | No | 260 | No | 260 | 0 | 0 | 254 | No | 2080 | No | 2080 | 0 | 0 | 1702 | No | 59 | No | 59 | 22 | 22 | 58 | No | 17450 | No | 17450 | 0 | 0 | 19320 | Yes | 21727 | 21727 | 1002 | 1002 | 23132 |  | 2022-02-04 |  | 2022-07-29 | Yes | 2023-02-06 |  | 2023-11-06 | Yes | 2023-03-07 |  | 2024-01-16 | Yes | 2023-08-03 |  | 2024-05-07 | Yes |  |  | 2025-11-14 |  | 0 | Yes | No | No | No
74 | 02 | 3714 | PLU | 89 | Crescent Mills CAPM | Near Greenville, from 1.4 miles north of Indian Falls Road to south of Hot Springs Road; also from Mill Street to 0.4 mile north of Mill Street (PM 20.6/21.0). | Rehabilitate pavement, upgrade guardrail, replace Transportation Management System (TMS) elements and signs, rehabilitate drainage systems, and construct a Maintenance Vehicle Pullout (MVP). | 870 | Yes | 870 | 721 | 721 | 1024 | Yes | 850 | No | 850 | 0 | 0 | 825 | No | 460 | No | 460 | 0 | 0 | 173 | No | 1120 | No | 1120 | 0 | 0 | 1019 | No | 343 | No | 343 | 10 | 10 | 493 | Yes | 9350 | No | 9350 | 0 | 0 | 9350 | No | 12993 | 12993 | 731 | 731 | 12884 |  | 2022-07-15 |  | 2022-07-29 | No | 2023-12-26 |  | 2023-11-01 | No | 2024-02-20 |  | 2024-02-20 | No | 2024-09-05 |  | 2024-08-27 | No |  |  | 2026-12-22 |  | 0 | No | No | No | No
75 | 02 | 3718 | LAS | 139 | 139 Susanville Paving | Near Susanville, from north of Chestnut Street to 2.7 miles south of Horse Lake Road. | Rehabilitate pavement, upgrade guardrail and concrete barrier, pave Maintenance Vehicle Pullouts (MVPs) and chain area, rehabilitate drainage systems, upgrade facilities to meet Americans with Disabilities Act (ADA) standards and widen shoulders from PM 0.7 to PM 1.9 to provide multi-modal connectivity as complete streets elements. | 1120 | Yes | 1120 | 495 | 495 | 1343 | Yes | 1180 | No | 1180 | 0 | 0 | 1181 | Yes | 60 | No | 60 | 0 | 0 | 60 | No | 1193 | No | 1193 | 0 | 0 | 1090 | No | 129 | No | 129 | 0 | 0 | 129 | No | 13040 | No | 13040 | 0 | 0 | 13040 | No | 16722 | 16722 | 495 | 495 | 16843 |  | 2022-11-16 |  | 2022-11-16 | No | 2024-02-16 |  | 2024-02-23 | No | 2024-04-12 |  | 2024-04-12 | No | 2024-08-16 |  | 2024-08-16 | No |  |  | 2025-12-17 |  | 0 | No | No | No | No
76 | 02 | 3719 | TEH | 36 | Dibble Creek CAPM | Near Red Bluff, from 0.8 mile east of Salt Creek Bridge to Baker Road. | Rehabilitate pavement, upgrade guardrail and signs, add lighting, and rehabilitate drainage systems. | 1140 | Yes | 1140 | 773 | 773 | 773 | No | 1410 | No | 1410 | 0 | 0 | 1381 | No | 220 | No | 220 | 0 | 0 | 241 | Yes | 1470 | No | 1470 | 0 | 0 | 1387 | No | 164 | No | 164 | 0 | 0 | 83 | No | 21630 | No | 21630 | 0 | 0 | 21630 | No | 26034 | 26034 | 773 | 773 | 25495 |  | 2022-03-02 | 2022-06-10 |  |  | 2023-03-15 |  | 2023-05-01 | No | 2023-03-20 |  | 2023-05-12 | No | 2023-09-12 |  | 2023-12-19 | Yes |  |  | 2025-01-28 |  | 0 | No | No | No | No
77 | 02 | 3721 | SIS | 96 | Somes Bar CAPM | Near Somes Bar, from Humboldt County line to west of Dillon Creek Bridge. | Rehabilitate pavement and upgrade guardrails. | 1510 | Yes | 1510 | 0 | 0 | 1483 | No | 1090 | No | 1090 | 0 | 0 | 996 | No | 150 | No | 150 | 0 | 0 | 145 | No | 1950 | No | 1950 | 0 | 0 | 1557 | No | 31 | No | 31 | 0 | 0 | 31 | No | 15470 | No | 15470 | 0 | 0 | 15470 | No | 20201 | 20201 | 0 | 0 | 19682 |  |  |  | 2024-10-07 |  |  |  | 2025-10-07 |  |  |  | 2025-12-02 |  |  |  | 2026-04-13 |  |  |  | 2028-01-03 |  | 0 | No | No | No | No
78 | 02 | 3722 | PLU | 36 | Chester Causeway Rehab | Near Chester, from Melissa Avenue to Lassen County line; also in Lassen County from Plumas County line to 2.4 miles east of Road A21/Mooney Road (PM 0.0/6.1). | Rehabilitate pavement, upgrade signs and Transportation Management System (TMS) elements, and rehabilitate drainage systems. | 1960 | Yes | 1960 | 1367 | 1367 | 3575 | Yes | 2160 | No | 2160 | 0 | 0 | 2144 | No | 590 | No | 590 | 0 | 0 | 864 | Yes | 2590 | No | 2590 | 0 | 0 | 2199 | No | 483 | No | 483 | 0 | 0 | 868 | Yes | 25370 | No | 25370 | 0 | 0 | 25370 | No | 33153 | 33153 | 1367 | 1367 | 35020 |  | 2022-09-17 |  | 2022-09-17 | No | 2024-03-15 |  | 2024-03-20 | No | 2024-05-12 |  | 2024-05-12 | No | 2024-10-22 |  | 2024-10-22 | No |  |  | 2025-12-23 |  | 0 | Yes | Yes | No | No
79 | 02 | 3733 | TEH | 36 | Red Bluff Bridges | In Red Bluff, at East Sand Slough Bridge No 08-0090 (PM 41.95), Samson Slough Bridge No 08-0089 (PM 42.24), and Paynes Creek Slough Bridge No 08-0088 (PM 42.5). | Seismic retrofit of three bridges. | 990 | Yes | 990 | 647 | 647 | 1259 | Yes | 1270 | No | 1270 | 0 | 0 | 1397 | Yes | 330 | No | 330 | 0 | 0 | 361 | Yes | 980 | No | 980 | 0 | 0 | 852 | No | 309 | No | 309 | 0 | 0 | 309 | No | 3230 | No | 3230 | 0 | 0 | 3230 | No | 7109 | 7109 | 647 | 647 | 7408 |  | 2022-10-05 |  | 2022-10-05 | No | 2024-03-15 |  | 2024-03-15 | No | 2024-03-29 |  | 2024-03-29 | No | 2024-10-08 |  | 2024-10-08 | No |  |  | 2025-12-22 |  | 0 | No | No | No | No
80 | 02 | 3735 | TRI | 299 | Poker Bar Culverts | Near Weaverville and Douglas City, from 0.3 mile east of Glennison Gap Road/Jennings Road to 0.2 mile west of Shasta County line. | Rehabilitate drainage systems. | 1580 | Yes | 1580 | 0 | 0 | 1546 | No | 1250 | No | 1250 | 0 | 0 | 1140 | No | 360 | No | 360 | 0 | 0 | 356 | No | 1240 | No | 1240 | 0 | 0 | 1062 | No | 209 | No | 209 | 0 | 0 | 209 | No | 6400 | No | 6400 | 0 | 0 | 6400 | No | 11039 | 11039 | 0 | 0 | 10713 |  |  |  | 2024-10-07 |  |  |  | 2025-12-07 |  |  |  | 2026-02-01 |  |  |  | 2026-05-31 |  |  |  | 2027-12-14 |  | 0 | No | No | No | No
81 | 02 | 3737 | SHA | 89 | Burney Falls Pavement | Near Burney, from north of Route 299 to 1.4 miles north of Lake Britton Bridge. | Rehabilitate pavement, construct Maintenance Vehicle Pullouts (MVPs), replace guardrail and signs, and rehabilitate drainage systems. | 630 | Yes | 630 | 621 | 621 | 621 | No | 0 | Yes | 0 | 0 | 0 | 736 | Yes | 0 | Yes | 0 | 0 | 0 | 86 | Yes | 630 | No | 630 | 0 | 0 | 775 | Yes | 233 | No | 233 | 23 | 23 | 23 | No | 8350 | No | 8350 | 0 | 0 | 10440 | Yes | 9843 | 9843 | 644 | 644 | 12681 |  | 2022-05-02 | 2022-05-25 |  |  | 2023-07-03 |  | 2023-07-03 | No | 2023-07-28 |  | 2023-08-04 | No | 2023-12-26 |  | 2024-01-05 | No |  |  | 2025-01-02 |  | 0 | No | Yes | No | No
82 | 02 | 3752 | TRI | 299 | Burnt Ranch CAPM | Near Burnt Ranch, from 0.6 mile east of Gray Creek Road to 1.3 miles east of Mill Creek Road. | Rehabilitate pavement, upgrade guardrails, signs, and pavement markings, and rehabilitate drainage systems. | 1260 | Yes | 1260 | 0 | 0 | 1259 | No | 740 | No | 740 | 0 | 0 | 680 | No | 270 | No | 270 | 0 | 0 | 268 | No | 1630 | No | 1630 | 0 | 0 | 1402 | No | 95 | No | 95 | 0 | 0 | 95 | No | 9590 | No | 9590 | 0 | 0 | 9590 | No | 13585 | 13585 | 0 | 0 | 13294 |  |  |  | 2024-10-04 |  |  |  | 2025-12-04 |  |  |  | 2026-02-02 |  |  |  | 2026-06-03 |  |  |  | 2026-12-02 |  | 0 | No | No | No | No
83 | 02 | 3753 | SIS | 3 | Montague CAPM | In and near Yreka and Montague, from 0.5 mile north of Juniper Drive to north of Sixth Street. | Rehabilitate pavement, upgrade guardrails and signs, rehabilitate drainage systems, upgrade facilities to Americans with Disabilities Act (ADA) standards, and construct complete streets elements. | 1390 | Yes | 1390 | 0 | 0 | 1019 | No | 1010 | No | 1010 | 0 | 0 | 684 | No | 380 | No | 380 | 0 | 0 | 302 | No | 1620 | No | 1620 | 0 | 0 | 1019 | No | 148 | No | 148 | 0 | 0 | 148 | No | 8190 | No | 8190 | 0 | 0 | 8190 | No | 12738 | 12738 | 0 | 0 | 11362 |  |  |  | 2024-05-15 |  |  |  | 2025-11-17 |  |  |  | 2026-01-12 |  |  |  | 2026-06-02 |  |  |  | 2027-12-06 |  | 0 | No | No | No | No
84 | 02 | 3758 | MOD | 395 | Alturas CAPM | In and near Alturas, from 1.0 mile north of South Fork Pit River Bridge to south of County Road 118; also on Route 299, from Spruce Street to Route 395 (PM 40.4/40.6). | Rehabilitate pavement, upgrade guardrails and drainage systems, and upgrade curb ramps to Americans with Disabilities Act (ADA) standards. | 1670 | Yes | 1670 | 0 | 0 | 1603 | No | 1080 | No | 1080 | 0 | 0 | 1010 | No | 1100 | No | 1100 | 0 | 0 | 1073 | No | 2330 | No | 2330 | 0 | 0 | 2038 | No | 203 | No | 203 | 0 | 0 | 203 | No | 20330 | No | 20330 | 0 | 0 | 20330 | No | 26713 | 26713 | 0 | 0 | 26257 |  |  |  | 2024-04-06 |  |  |  | 2025-10-06 |  |  |  | 2026-01-08 |  |  |  | 2026-05-31 |  |  |  | 2027-12-30 |  | 0 | No | No | No | No
85 | 02 | 3766 | MOD | 299 | Cedarville ADA and CAPM | Near Cedarville, from west of Patterson Street to 0.6 mile east of Main Street. | Rehabilitate pavement and drainage systems, and upgrade facilities to Americans with Disabilities Act (ADA) standards. | 930 | Yes | 930 | 0 | 0 | 923 | No | 940 | No | 940 | 0 | 0 | 895 | No | 680 | No | 680 | 0 | 0 | 679 | No | 1150 | No | 1150 | 0 | 0 | 1059 | No | 218 | No | 218 | 0 | 0 | 218 | No | 4510 | No | 4510 | 0 | 0 | 4510 | No | 8428 | 8428 | 0 | 0 | 8284 |  |  |  | 2024-04-05 |  |  |  | 2025-10-06 |  |  |  | 2025-12-11 |  |  |  | 2026-04-01 |  |  |  | 2026-12-01 |  | 0 | No | No | No | No
86 | 02 | 3768 | TRI | 3 | Tangle Blue CAPM | Near Coffee Creek, from Coffee Creek Bridge to Siskiyou County line. | Rehabilitate pavement, pave ditches, upgrade bridge rails, guardrails, drainage systems, signs, and Transportation Management System (TMS) elements, and develop disposal sites. | 990 | Yes | 990 | 0 | 0 | 959 | No | 1060 | No | 1060 | 0 | 0 | 982 | No | 230 | No | 230 | 0 | 0 | 224 | No | 1530 | No | 1530 | 0 | 0 | 1312 | No | 657 | No | 657 | 0 | 0 | 657 | No | 20130 | No | 20130 | 0 | 0 | 20130 | No | 24597 | 24597 | 0 | 0 | 24264 |  |  |  | 2024-02-01 |  |  |  | 2025-04-15 |  |  |  | 2025-05-01 |  |  |  | 2025-08-26 |  |  |  | 2026-12-01 |  | 0 | No | No | No | No
87 | 02 | 3773 | SIS | 89 | McCloud CAPM | Near McCloud and Mount Shasta, from 1.1 miles south of Pilgrim Creek Road to Route 5. | Rehabilitate pavement, widen shoulders, rehabilitate drainage systems, and upgrade guardrail and signs. | 1210 | Yes | 1210 | 0 | 0 | 1066 | No | 840 | No | 840 | 0 | 0 | 750 | No | 160 | No | 160 | 0 | 0 | 137 | No | 1790 | No | 1790 | 0 | 0 | 1473 | No | 108 | No | 108 | 0 | 0 | 107 | No | 24070 | No | 24070 | 0 | 0 | 24070 | No | 28178 | 28178 | 0 | 0 | 27603 |  |  |  | 2024-01-16 |  |  |  | 2025-01-16 |  |  |  | 2025-03-13 |  |  |  | 2025-07-29 |  |  |  | 2027-01-26 |  | 0 | No | No | No | No
88 | 02 | 3789 | SHA | 299 | Diddy Roost Culverts | Near Redding, from west of Seamas Gulch Road to west of Fenders Ferry Road at various locations. | Rehabilitate drainage systems. | 1750 | Yes | 1750 | 0 | 0 | 1744 | No | 910 | No | 910 | 0 | 0 | 850 | No | 180 | No | 180 | 0 | 0 | 168 | No | 950 | No | 950 | 0 | 0 | 848 | No | 496 | No | 496 | 0 | 0 | 496 | No | 4240 | No | 4240 | 0 | 0 | 4240 | No | 8526 | 8526 | 0 | 0 | 8346 |  |  |  | 2024-09-16 |  |  |  | 2025-09-16 |  |  |  | 2025-11-12 |  |  |  | 2026-04-01 |  |  |  | 2026-12-01 |  | 0 | No | No | No | No
89 | 02 | 3861 | TEH | 5 | Thomes Creek Bridge MTCE | Near Corning, at Thomes Creek Bridge No 08-0165. | Apply polyester concrete overlay to bridge deck, replace joint seals, repair unsound concrete, and upgrade guardrail. (Bridge Deck Preservation). | 270 | Yes | 220 | 94 | 94 | 266 | No | 500 | No | 500 | 0 | 0 | 464 | No | 40 | No | 40 | 0 | 0 | 35 | No | 570 | No | 570 | 0 | 0 | 527 | No | 12 | No | 12 | 0 | 0 | 35 | Yes | 4130 | No | 4130 | 0 | 0 | 0 | No | 5522 | 5472 | 94 | 94 | 1327 |  |  |  | 2022-08-05 |  |  |  | 2023-01-18 |  |  |  | 2023-03-15 |  |  |  | 2023-07-18 |  |  |  | 2024-01-12 |  | 0 | No | No | No | No
90 | 03 | 2115 | BUT | 32 | BUT-32 Chico Rehab | In and near Chico, from Muir Avenue to Route 99 (PM 5.0/10.2L/R). | Rehabilitate pavement, install signals and lighting, upgrade Transportation Management System (TMS) elements, rehabilitate drainage systems, and upgrade facilities to Americans with Disabilities Act (ADA) standards. | 2400 | Yes | 2400 | 2396 | 2396 | 2396 | No | 1740 | Yes | 1740 | 588 | 588 | 1856 | Yes | 1770 | Yes | 1770 | 414 | 414 | 3102 | Yes | 2500 | No | 2500 | 0 | 0 | 2386 | No | 2430 | No | 2430 | 58 | 58 | 2430 | No | 24900 | No | 24900 | 0 | 0 | 28167 | Yes | 35740 | 35740 | 3456 | 3456 | 40337 |  | 2021-12-01 | 2021-12-06 |  |  | 2023-06-01 |  | 2023-06-01 | No | 2023-06-15 |  | 2023-06-15 | No | 2023-10-27 |  | 2023-10-08 | No |  |  | 2025-03-31 |  | 0 | No | Yes | No | No
91 | 03 | 2300 | BUT | 70 | Butte 70 CAPM | Near Pulga, from east of Big Ben Road to Plumas County line. | Rehabilitate pavement, drainage systems, lighting, sign panels, and Transportation Management System (TMS) elements. | 1240 | Yes | 1240 | 0 | 0 | 1260 | Yes | 1490 | No | 1490 | 0 | 0 | 1406 | No | 300 | No | 300 | 0 | 0 | 285 | No | 1250 | No | 1250 | 0 | 0 | 1114 | No | 880 | No | 880 | 0 | 0 | 872 | No | 12690 | No | 12690 | 0 | 0 | 10500 | No | 17850 | 17850 | 0 | 0 | 15437 |  |  |  | 2023-12-01 |  |  |  | 2025-09-10 |  |  |  | 2025-09-25 |  |  |  | 2026-02-16 |  |  |  | 2026-12-13 |  | 0 | No | No | No | No
92 | 03 | 2435 | BUT | 99 | Butte 99 Road Rehab in Gridley | In and near Gridley, from Hollis Lane to north of Ford Avenue. | Rehabilitate pavement, upgrade Transportation Management System (TMS) elements, rehabilitate drainage systems, upgrade lighting and bike and ped facilities along east side of SR99 to Americans with Disabilities Act (ADA) standards. | 915 | Yes | 915 | 861 | 861 | 861 | No | 1180 | No | 1180 | 0 | 0 | 1496 | Yes | 510 | No | 510 | 0 | 0 | 2837 | Yes | 1480 | No | 1480 | 0 | 0 | 1466 | No | 600 | No | 600 | 22 | 22 | 1661 | Yes | 15200 | No | 11700 | 0 | 0 | 14933 | No | 19885 | 16385 | 883 | 883 | 23254 |  | 2021-04-01 | 2022-06-27 |  |  | 2023-12-15 |  | 2023-12-15 | No | 2024-01-10 |  | 2024-01-10 | No | 2024-05-29 |  | 2024-05-29 | No | 2026-06-15 |  | 2026-06-15 | No | 0 | No | Yes | No | Yes
93 | 03 | 2437 | BUT | 99 | Chico ITS | In and near Chico, from Southgate Avenue to Garner Lane. | Install Transportation Management System (TMS) elements. | 636 | Yes | 636 | 581 | 581 | 581 | No | 1460 | Yes | 1460 | 1451 | 1451 | 1451 | No | 48 | Yes | 48 | 36 | 36 | 52 | Yes | 1352 | Yes | 1352 | 1141 | 1141 | 1456 | Yes | 35 | No | 35 | 21 | 21 | 21 | No | 8755 | Yes | 8755 | 8196 | 8196 | 8755 | No | 12286 | 12286 | 11426 | 11426 | 12316 |  | 2019-08-12 | 2019-08-12 |  |  | 2020-09-15 | 2020-11-19 |  |  | 2020-10-01 | 2020-12-04 |  |  | 2021-02-25 | 2021-03-30 |  |  |  |  | 2022-09-30 |  | 8755 | No | No | No | No
94 | 03 | 2442 | BUT | 99 | Bridge Deck Preservation | In Chico, at Cohasset Highway Overcrossing No 12-0168; also in Placer County, on Route 80 at Troy Undercrossing No 19-0106L/R (PM 68.55) and Kingvale Undercrossing No 19-0107L (PM 69.23). | Polyester concrete overlay to one bridge deck, and deck-on-deck replacement and bridge rail replacement at three bridges. (Bridge Deck Preservation). | 300 | Yes | 300 | 249 | 249 | 249 | No | 375 | No | 375 | 0 | 0 | 360 | No | 30 | No | 30 | 0 | 0 | 9 | No | 525 | No | 525 | 0 | 0 | 270 | No | 5 | No | 5 | 0 | 0 | 0 | No | 3355 | No | 3355 | 0 | 0 | 761 | No | 4590 | 4590 | 249 | 249 | 1649 |  |  | 2022-06-23 |  |  |  |  | 2022-11-01 |  |  |  | 2023-01-23 |  |  |  | 2023-06-16 |  |  |  | 2023-12-01 |  | 0 | No | No | No | No
95 | 03 | 2633 | GLE | 162 | Butte City Bridge Replacement | Near Butte City, from Route 45 to 0.4 mile east of McDougall Street. | Replace Sacramento River Bridge No 11-0017 and viaduct approach, and reconstruct east side roadway to conform with new structure. | 5500 | Yes | 5500 | 5219 | 5219 | 5219 | No | 5500 | Yes | 5500 | 4644 | 4644 | 4644 | No | 1400 | Yes | 1400 | 1240 | 1240 | 1455 | Yes | 10000 | Yes | 10000 | 1338 | 1338 | 10214 | Yes | 3000 | No | 3000 | 1923 | 1923 | 2263 | No | 80972 | Yes | 80972 | 13184 | 13184 | 80972 | No | 106372 | 106372 | 27548 | 27548 | 104767 | 2019-06-26 | 2019-05-01 | 2019-05-01 |  |  | 2021-02-15 | 2021-05-13 |  |  | 2021-03-01 | 2021-06-30 |  |  | 2021-07-31 | 2022-02-02 |  |  |  |  | 2025-12-01 |  | 80972 | No | No | No | No
96 | 03 | 2638 | BUT | 162 | Oroville CAPM | In and near Oroville, from Feather River Bridge to Foothill BoulevaRd Rehabilitate pavement and drainage systems, upgrade facilities to Americans with Disabilities Act (ADA) standards, and upgrade signs and guardrail. | Rehabilitate pavement and drainage systems, upgrade facilities to Americans with Disabilities Act (ADA) standards, and upgrade signs and guardrail. | 920 | Yes | 920 | 0 | 0 | 917 | No | 1380 | No | 1380 | 0 | 0 | 1323 | No | 540 | No | 540 | 0 | 0 | 534 | No | 1280 | No | 1280 | 0 | 0 | 1137 | No | 250 | No | 250 | 0 | 0 | 250 | No | 11290 | No | 11290 | 0 | 0 | 9638 | No | 15660 | 15660 | 0 | 0 | 13799 |  |  |  | 2023-10-10 |  |  |  | 2025-01-09 |  |  |  | 2025-01-24 |  |  |  | 2025-06-02 |  |  |  | 2026-01-01 |  | 0 | No | No | No | No
97 | 03 | 3290A | ED | 050 | Camino Safety Project Combined | Near Placerville and Camino from 0.2 miles west of Still Meadows Road to 0.4 mile east of Upper Carson Rd. | Install median barrier, widen shoulders, construct accel/decal lane, construct an undercrossing, and construct access to the undercrossing from local roads. | 3893 | No | 3733 | 3836 | 3836 | 3839 | No | 3840 | No | 3840 | 3809 | 3809 | 3809 | No | 1260 | No | 1260 | 1036 | 1036 | 1036 | No | 9323 | No | 6280 | 4490 | 3624 | 7278 | No | 950 | No | 0 | 572 | 432 | 0 | No | 28239 | No | 24597 | 15676 | 13631 | 28239 | No | 47505 | 39710 | 29419 | 26368 | 44201 |  | 2018-06-29 |  |  |  | 2019-04-20 | 2019-10-09 |  |  | 2019-05-04 | 2019-10-09 |  |  | 2019-09-01 | 2020-06-03 |  |  |  |  | 2022-12-15 |  | 28238 | No | No | No | No
98 | 03 | 3312 | ED | 50 | ED 50 Advance Warning & ITS | In El Dorado County, from the Sacramento County line to of Stateline Avenue at various locations. | Upgrade new Transportation Management System (TMS) elements. | 600 | Yes | 600 | 600 | 600 | 600 | No | 1300 | Yes | 1300 | 1279 | 1279 | 1279 | No | 580 | Yes | 580 | 102 | 102 | 565 | No | 1620 | Yes | 1620 | 1448 | 1448 | 1918 | Yes | 150 | No | 150 | 1 | 1 | 1 | No | 10793 | Yes | 10793 | 9078 | 9078 | 10793 | No | 15043 | 15043 | 12508 | 12508 | 15156 |  | 2017-09-01 | 2017-09-01 |  |  | 2020-01-15 | 2019-12-28 |  |  | 2020-02-01 | 2020-03-20 |  |  | 2020-09-01 | 2020-08-27 |  |  |  |  | 2022-07-29 |  | 10793 | No | No | No | No
99 | 03 | 3315A | ED | 050 | ED 50 Culvert Rehab | In El Dorado County at various locations from 0.3 mile west of Bass Lake Road Undercrossing to 0.1 mile west of Schnell School Road Undercrossing. | Rehabilitate culverts. | 1045 | No | 1045 | 944 | 944 | 944 | No | 1285 | No | 1285 | 1030 | 1030 | 1030 | No | 872 | No | 872 | 495 | 495 | 495 | No | 1900 | No | 1900 | 57 | 57 | 1845 | No | 620 | No | 620 | 26 | 26 | 0 | No | 5318 | No | 5318 | 346 | 346 | 5318 | No | 11040 | 11040 | 2898 | 2898 | 9632 |  |  | 2020-01-26 |  |  |  | 2021-09-29 |  |  |  | 2021-10-15 |  |  |  | 2022-03-30 |  |  |  |  | 2023-03-17 |  | 5318 | No | No | No | No
100 | 03 | 3337 | ED | 50 | Placerville CAPM | In and near Placerville, from west of Carson Road Overcrossing to west of Still Meadows Road; also near Camino, from 1.1 miles west of Snow Road Undercrossing to east of Sawmill Undercrossing (PM 24.2/R29.1). | Rehabilitate pavement, upgrade facilities to Americans with Disabilities Act (ADA) standards, rehabilitate drainage systems, upgrade concrete barrier, signs, and Transportation Management System (TMS) elements, and construct maintenance vehicle pullouts. | 2250 | Yes | 2250 | 10 | 10 | 2277 | Yes | 2110 | No | 2110 | 0 | 0 | 2085 | No | 500 | No | 500 | 0 | 0 | 479 | No | 2950 | No | 2950 | 0 | 0 | 2740 | No | 610 | No | 610 | 0 | 0 | 605 | No | 29050 | No | 29050 | 0 | 0 | 24043 | No | 37470 | 37470 | 10 | 10 | 32229 |  |  |  | 2024-02-01 |  |  |  | 2025-05-15 |  |  |  | 2025-05-30 |  |  |  | 2025-08-11 |  |  |  | 2027-08-13 |  | 0 | No | No | No | No
101 | 03 | 3338 | ED | 50 | South Tahoe CAPM | In South Lake Tahoe, from east of Blue Lake Road to the Nevada State line. | Rehabilitate pavement and drainage systems, upgrade facilities to Americans with Disabilities Act (ADA) standards, and replace Transportation Management System (TMS) elements. | 1600 | Yes | 1600 | 6 | 6 | 1614 | Yes | 2040 | No | 2040 | 0 | 0 | 1962 | No | 1440 | No | 1440 | 0 | 0 | 1414 | No | 3090 | No | 3090 | 0 | 0 | 2722 | No | 1520 | No | 1520 | 0 | 0 | 1512 | No | 17440 | No | 17440 | 0 | 0 | 14435 | No | 27130 | 27130 | 6 | 6 | 23659 |  |  |  | 2024-02-01 |  |  |  | 2026-04-01 |  |  |  | 2026-05-01 |  |  |  | 2026-10-01 |  |  |  | 2027-12-10 |  | 0 | No | No | No | No
102 | 03 | 3341 | ED | 50 | ED 50 CAPM | Near Pollock Pines, Kyburz, and Strawberry, from west of Icehouse Road to 0.5 mile east of Cedar Street. | Rehabilitate pavement and drainage systems, and upgrade lighting and guardrail. | 1980 | Yes | 1980 | 1 | 1 | 2028 | Yes | 2310 | No | 2310 | 0 | 0 | 2250 | No | 220 | No | 220 | 0 | 0 | 214 | No | 3030 | No | 3030 | 0 | 0 | 2829 | No | 1240 | No | 1240 | 0 | 0 | 1233 | No | 28940 | No | 28940 | 0 | 0 | 24719 | No | 37720 | 37720 | 1 | 1 | 33273 |  |  |  | 2024-01-15 |  |  |  | 2025-04-16 |  |  |  | 2025-05-01 |  |  |  | 2025-10-16 |  |  |  | 2026-02-10 |  | 0 | No | No | No | No
103 | 03 | 3712 | GLE | 5 | GLE-5 CAPM | Near Orland, from north of County Road 28 to Tehama County line. | Rehabilitate pavement, upgrade facilities to Americans with Disabilities Act (ADA) standards, rehabilitate drainage systems, replace concrete barrier and guardrail, and upgrade signs and Transportation Management System (TMS) elements. | 680 | Yes | 680 | 6 | 6 | 698 | Yes | 1060 | No | 1060 | 0 | 0 | 1060 | No | 40 | No | 40 | 0 | 0 | 31 | No | 2370 | No | 2370 | 0 | 0 | 2101 | No | 30 | No | 30 | 0 | 0 | 27 | No | 25540 | No | 25540 | 0 | 0 | 21142 | No | 29720 | 29720 | 6 | 6 | 25059 |  |  |  | 2023-07-01 |  |  |  | 2025-09-01 |  |  |  | 2025-10-01 |  |  |  | 2026-05-29 |  |  |  | 2027-04-01 |  | 0 | No | No | No | No
104 | 03 | 3790 | GLE | 32 | GLE 32 CAPM | In and near Orland and Hamilton City, from Route 5 to Butte County line. | Rehabilitate pavement and drainage systems, and upgrade facilities to Americans with Disabilities Act (ADA) standards. | 1360 | Yes | 1360 | 8 | 8 | 1477 | Yes | 1770 | No | 1770 | 0 | 0 | 1776 | Yes | 1140 | No | 1140 | 0 | 0 | 1153 | Yes | 1670 | No | 1670 | 0 | 0 | 1475 | No | 410 | No | 410 | 0 | 0 | 410 | No | 13960 | No | 13960 | 0 | 0 | 11925 | No | 20310 | 20310 | 8 | 8 | 18216 |  |  |  | 2023-07-01 |  |  |  | 2025-05-01 |  |  |  | 2025-07-01 |  |  |  | 2025-12-15 |  |  |  | 2026-11-01 |  | 0 | No | No | No | No
105 | 03 | 3918 | GLE | 162 | Willows CAPM | In and near Willows, from west of Route 5 to east of Tehama Street. | Rehabilitate pavement and drainage systems, upgrade curb ramps to Americans with Disabilities Act (ADA) standards, and upgrade signs and Transportation Management System (TMS) elements. | 1430 | Yes | 1430 | 7 | 7 | 1468 | Yes | 1420 | No | 1420 | 0 | 0 | 1396 | No | 1220 | No | 1220 | 0 | 0 | 1230 | Yes | 1720 | No | 1720 | 0 | 0 | 1510 | No | 530 | No | 530 | 0 | 0 | 524 | No | 13400 | No | 13400 | 0 | 0 | 11400 | No | 19720 | 19720 | 7 | 7 | 17528 |  |  |  | 2023-07-01 |  |  |  | 2025-01-01 |  |  |  | 2025-02-03 |  |  |  | 2025-07-07 |  |  |  | 2025-11-30 |  | 0 | No | No | No | No
106 | 03 | 4002 | NEV | 20 | Gold Nugget | In and near Grass Valley and Nevada City, from Route 20/49 Separation to east of Stonehill Road/Dow Road. | Rehabilitate pavement, replace sign panels, upgrade Transportation Management System (TMS) elements, rehabilitate drainage systems, and upgrade facilities to Americans with Disabilities Act (ADA) standards. | 1030 | Yes | 1030 | 908 | 908 | 908 | No | 1570 | Yes | 1570 | 988 | 988 | 1573 | Yes | 340 | Yes | 340 | 262 | 262 | 556 | Yes | 1700 | No | 1700 | 0 | 0 | 1548 | No | 250 | No | 250 | 19 | 19 | 222 | No | 19100 | No | 19100 | 0 | 0 | 18200 | No | 23990 | 23990 | 2177 | 2177 | 23007 |  | 2021-07-30 | 2021-07-30 |  |  | 2023-04-14 |  | 2023-04-14 | No | 2023-04-28 |  | 2023-04-28 | No | 2023-10-17 |  | 2023-10-17 | No |  |  | 2024-12-16 |  | 0 | No | No | No | No
107 | 03 | 4003 | NEV | 20 | Nev/Pla 20 CAPM | Near Nevada City and Emigrant Gap, from east of Dow Road to Placer County line (PM 20.0/41.287) and from Placer County line to Route 80 (PM 43.868/46.1); also in Placer County from Nevada County line to east of Lake Spaulding Road (PM 41.287/43.868). | Rehabilitate pavement and drainage systems, and upgrade guardrail, signs and Transportation Management System (TMS) elements. | 1770 | Yes | 1770 | 1 | 1 | 1772 | Yes | 1950 | No | 1950 | 0 | 0 | 1855 | No | 270 | No | 270 | 0 | 0 | 259 | No | 2720 | No | 2720 | 0 | 0 | 2425 | No | 420 | No | 420 | 0 | 0 | 413 | No | 23840 | No | 23840 | 0 | 0 | 20360 | No | 30970 | 30970 | 1 | 1 | 27084 |  |  |  | 2023-08-01 |  |  |  | 2025-04-30 |  |  |  | 2025-05-15 |  |  |  | 2025-08-25 |  |  |  | 2026-12-01 |  | 0 | No | No | No | No
108 | 03 | 4124 | NEV | 49 | Nev-49 Culvert Rehab (South) | Near Higgins Corner, from the Placer County line to 0.3 mile north of Lime Kiln Road; also in Placer County, at PM R8.42 and PM R10.23. | Rehabilitate drainage systems. | 513 | Yes | 513 | 398 | 398 | 398 | No | 743 | Yes | 743 | 674 | 674 | 674 | No | 547 | Yes | 547 | 360 | 360 | 498 | No | 510 | Yes | 510 | 218 | 218 | 547 | Yes | 200 | No | 200 | 22 | 22 | 23 | No | 1886 | Yes | 1886 | 528 | 528 | 1886 | No | 4399 | 4399 | 2200 | 2200 | 4026 |  | 2019-08-18 | 2019-08-18 |  |  | 2020-09-15 | 2021-01-22 |  |  | 2020-10-01 | 2021-02-01 |  |  | 2021-04-15 | 2021-07-08 |  |  |  |  | 2022-12-01 |  | 1886 | No | No | No | No
109 | 03 | 4125 | NEV | Var | Count Station Repair & Install | In various counties, on various routes at various locations. | Repair and install vehicle census count stations. | 1000 | Yes | 1000 | 348 | 348 | 348 | No | 1490 | Yes | 1490 | 1243 | 1243 | 1243 | No | 210 | Yes | 210 | 83 | 83 | 207 | No | 1800 | Yes | 1800 | 1714 | 1714 | 2133 | Yes | 30 | No | 30 | 0 | 0 | 0 | No | 9842 | Yes | 9842 | 7613 | 7613 | 9842 | No | 14372 | 14372 | 11001 | 11001 | 13773 |  | 2018-01-01 | 2018-03-27 |  |  | 2019-09-01 | 2019-09-27 |  |  | 2019-10-01 | 2019-10-11 |  |  | 2020-04-15 | 2020-07-02 |  |  |  |  | 2023-10-02 |  | 9841 | No | No | No | No
110 | 03 | 4291 | PLA | 80 | UPGRADE EMS SIGNS | In Placer, Nevada, and Yolo Counties, at various locations. | Upgrade Extinguishable Message Signs (EMS) to LED. | 290 | Yes | 290 | 215 | 215 | 215 | No | 410 | Yes | 410 | 400 | 400 | 400 | No | 180 | Yes | 180 | 86 | 86 | 118 | No | 700 | Yes | 700 | 509 | 509 | 705 | Yes | 35 | No | 35 | 0 | 0 | 0 | No | 1844 | Yes | 1844 | 1478 | 1478 | 1844 | No | 3459 | 3459 | 2688 | 2688 | 3282 |  | 2018-01-01 | 2018-03-19 |  |  | 2019-07-01 | 2019-08-15 |  |  | 2019-08-01 | 2019-09-03 |  |  | 2020-04-01 | 2020-05-08 |  |  |  |  | 2022-07-29 |  | 1843 | No | No | No | No
111 | 03 | 4305 | NEV | 80 | Yuba Pass SOH Bridge Replacement | Near Whitmore, from west of Crystal Lake Road to east of Route 20 Separation at Yuba Pass Separation and Overhead No 17-0023L/R (PM R58.7L/R/PM R60.2); also in Placer County, from PM R58.5L/R to PM R58.6L/R. | Replace and widen bridge, construct retaining walls in the median, rehabilitate drainage systems, and install Roadway Weather Information Systems (RWIS). | 3620 | Yes | 3620 | 2958 | 2958 | 2958 | No | 4210 | Yes | 4210 | 0 | 0 | 3950 | No | 430 | Yes | 430 | 0 | 0 | 357 | No | 8500 | No | 8500 | 0 | 0 | 7550 | No | 836 | No | 836 | 14 | 14 | 836 | No | 84500 | No | 84500 | 0 | 0 | 73753 | No | 102096 | 102096 | 2972 | 2972 | 89404 |  | 2022-01-15 | 2022-04-27 |  |  | 2023-02-15 |  | 2023-02-15 | No | 2023-03-01 |  | 2023-03-01 | No | 2023-08-01 |  | 2023-08-01 | No |  |  | 2027-06-30 |  | 0 | No | No | No | No
112 | 03 | 4319 | NEV | 080 | Nev 80 Rehab Pavement | In Truckee from West of Donner OC to Bridge Street Undercrossing. | Rehabilitate roadway, construct auxiliary lane, upgrade TMS elements, rehab drainage systems and upgrade facilities to ADA standards. | 1580 | No | 1580 | 1550 | 1550 | 1550 | No | 1950 | No | 1950 | 1512 | 1512 | 1512 | No | 220 | No | 220 | 55 | 55 | 55 | No | 2500 | No | 2500 | 352 | 352 | 2566 | Yes | 372 | No | 372 | 42 | 42 | 38 | No | 23927 | No | 23927 | 2519 | 2519 | 23927 | No | 30549 | 30549 | 6030 | 6030 | 29648 | [6 empty] | 2021-06-02 |  |  |  | 2021-06-15 |  |  |  | 2021-12-08 |  |  |  |  | 2023-12-11 |  | 23927 | No | No | No | No
113 | 03 | 4681 | PLA | 28 | PLA-28 Rehab | Near Tahoe City and Kings Beach, from Route 89 to Nevada State line. | Rehabilitate pavement, rehabilitate drainage systems, and upgrade facilities to Americans with Disabilities Act (ADA) standards. | 1460 | Yes | 1460 | 1447 | 1447 | 1447 | No | 1420 | Yes | 1420 | 526 | 526 | 1653 | Yes | 851 | Yes | 851 | 89 | 89 | 1118 | Yes | 1780 | No | 1780 | 0 | 0 | 1769 | No | 2077 | No | 2077 | 34 | 34 | 2077 | No | 18100 | No | 18100 | 0 | 0 | 17593 | No | 25688 | 25688 | 2096 | 2096 | 25657 |  | 2021-12-06 | 2021-12-06 |  |  | 2023-06-05 |  | 2023-12-01 | Yes | 2023-06-15 |  | 2023-12-15 | Yes | 2023-11-06 |  | 2024-04-19 | Yes |  |  | 2026-03-19 |  | 0 | Yes | No | No | No
114 | 03 | 5097 | PLA | 80 | PLA 80 Bridge Replacement | Near Dutch Flat and Cisco Grove, at Crystal Springs Road Overcrossing No 19-0112 (PM 46.3), Baxter Overcrossing No 19-0113 (PM 46.9), Drum Forebay Overcrossing No 19-0114 (PM 49.0), and Cisco Overcrossing No 19-0118 (PM R63.5). | Replace bridges at four locations. | 3000 | Yes | 3000 | 2671 | 2671 | 2671 | No | 6350 | Yes | 6350 | 4929 | 4929 | 4929 | No | 485 | Yes | 485 | 195 | 195 | 358 | No | 6430 | Yes | 6430 | 4098 | 4098 | 6461 | Yes | 550 | No | 550 | 50 | 50 | 139 | No | 31815 | Yes | 31815 | 22033 | 22033 | 31815 | No | 48630 | 48630 | 33976 | 33976 | 46373 | 2018-10-17 | 2018-04-17 | 2018-04-17 |  |  | 2020-04-20 | 2020-05-01 |  |  | 2020-05-07 | 2020-05-04 |  |  | 2020-08-27 | 2020-10-09 |  |  |  |  | 2023-06-01 |  | 31814 | No | No | No | No
115 | 03 | 5111 | NEV | 80 | Soda Springs Pavement Rehabilitation | Near Kingvale, from Placer County line to east of Donner Pass Road (PM 0.0/R2.7L/R); also in Placer County, from west of Troy Road Undercrossing to Nevada County line (PM 68.3/69.7). | Rehabilitate roadway, construct truck climbing lane in eastbound direction, replace Kingvale Undercrossing No 19-0107R and Troy Road Undercrossing No 19-0106R, replace sign panels, upgrade lighting and Transportation Management System (TMS) elements, and rehabilitate drainage systems. (G13 Contingency). | 3000 | Yes | 3000 | 2997 | 2997 | 2997 | No | 3584 | Yes | 3584 | 109 | 109 | 3948 | Yes | 500 | Yes | 500 | 1 | 1 | 122 | No | 0 | No | 0 | 0 | 0 | 8661 | Yes | 1687 | No | 1687 | 3 | 3 | 1687 | No | 0 | No | 0 | 0 | 0 | 63906 | Yes | 8771 | 8771 | 3110 | 3110 | 81321 |  | 2022-02-05 | 2022-02-24 |  |  | 2023-04-20 |  | 2023-04-20 | No | 2023-04-24 |  | 2023-04-24 | No | 2023-09-20 |  | 2023-10-02 | No |  |  | 2026-07-20 |  | 0 | No | Yes | No | No
116 | 03 | 5131 | PLA | 80 | Blue Canyon Pavement Rehabilitation | Near Applegate, from east of Crother Road Overcrossing to east of Weimar Overhead; also near Magra from PM 39.5 to PM 41.3; also near Emigrant Gap from PM 53.0 to PM 54.7. | Rehabilitate roadway, construct truck climbing lanes in eastbound direction, widen shoulders, replace or widen structures, upgrade median barrier and Transportation Management System (TMS) elements. (G13 Contingency). | 4600 | Yes | 4600 | 2953 | 2953 | 5046 | Yes | 5000 | No | 5000 | 0 | 0 | 4889 | No | 500 | No | 500 | 0 | 0 | 674 | Yes | 0 | No | 0 | 0 | 0 | 8244 | Yes | 2972 | No | 2972 | 0 | 0 | 2972 | No | 0 | No | 0 | 0 | 0 | 86817 | Yes | 13072 | 13072 | 2953 | 2953 | 108642 |  | 2023-08-18 |  | 2023-08-18 | No | 2024-06-14 |  | 2024-06-14 | No | 2024-06-21 |  | 2024-06-21 | No | 2024-12-31 |  | 2024-12-31 | No |  |  | 2027-12-31 |  | 0 | No | Yes | No | No
117 | 03 | 5133 | PLA | 80 | Monte Vista Pavement Rehabilitation | Near Gold Run, from west of Monte Vista Overcrossing to east of Drum Forebay Overcrossing (PM 42.7/49.3R). | Rehabilitate roadway, construct truck climbing lane, replace or widen structures, upgrade median concrete barrier, sign panels, and Transportation Management System (TMS) elements, and rehabilitate drainage systems. | 3500 | Yes | 3500 | 3060 | 3060 | 3399 | No | 3000 | No | 3000 | 0 | 0 | 3496 | Yes | 230 | No | 230 | 0 | 0 | 230 | No | 6500 | No | 6500 | 0 | 0 | 6843 | Yes | 2165 | No | 2165 | 4 | 4 | 2165 | No | 78688 | No | 78688 | 0 | 0 | 71593 | No | 94083 | 94083 | 3064 | 3064 | 87726 |  | 2022-05-10 |  | 2022-08-15 | Yes | 2023-04-20 |  | 2023-06-09 | No | 2023-04-24 |  | 2023-06-16 | No | 2023-09-20 |  | 2023-11-30 | No |  |  | 2025-12-31 |  | 0 | Yes | No | No | No
118 | 03 | 5140 | PLA | 80 | Alta CAPM | Near Colfax, from east of Route 174 Separation to east of Alta Road Undercrossing. | Rehabilitate pavement and drainage systems, and upgrade guardrail, signs, and Transportation Management System (TMS) elements. | 4110 | Yes | 4110 | 7 | 7 | 2051 | No | 2350 | No | 2350 | 0 | 0 | 2331 | No | 310 | No | 310 | 0 | 0 | 286 | No | 2540 | No | 2540 | 0 | 0 | 2324 | No | 830 | No | 830 | 0 | 0 | 829 | No | 22250 | No | 22250 | 0 | 0 | 19008 | No | 32390 | 32390 | 7 | 7 | 26829 |  |  |  | 2023-10-06 |  |  |  | 2025-01-20 |  |  |  | 2025-01-31 |  |  |  | 2025-06-30 |  |  |  | 2026-04-01 |  | 0 | No | No | No | No
119 | 03 | 5142 | PLA | 80 | Drum Forebay to Troy Drainage System Restoration | Near Emigrant Gap, from east of Drum Forebay Overcrossing (OC) to west of Yuba Gap OC (PM 49.3R/R58.7R) and from Nevada County line to west of Troy Undercrossing (PM R62.541R/68.5); also in Nevada County from west of Yuba Gap OC to Placer County line (PM R58.712R/R62.541R). | Rehabilitate drainage systems and upgrade Transportation Management System (TMS) elements. | 910 | Yes | 910 | 0 | 0 | 941 | Yes | 1180 | No | 1180 | 0 | 0 | 1189 | Yes | 150 | No | 150 | 0 | 0 | 140 | No | 1380 | No | 1380 | 0 | 0 | 1258 | No | 170 | No | 170 | 0 | 0 | 163 | No | 11600 | No | 11600 | 0 | 0 | 9909 | No | 15390 | 15390 | 0 | 0 | 13600 |  |  |  | 2023-07-07 |  |  |  | 2024-11-15 |  |  |  | 2024-12-02 |  |  |  | 2025-04-30 |  |  |  | 2026-12-01 |  | 0 | No | No | No | No
120 | 03 | 5292 | PLA | 89 | CAPM & Drainage Improvements | Near Truckee, from 0.8 mile north of Alpine Meadows Road to Nevada County line; also in Nevada County in Truckee, from Placer County line to Route 80 (PM 0.0/0.5). | Rehabilitate pavement and drainage systems, upgrade facilities to Americans with Disabilities Act (ADA) standards, and upgrade guardrail and Transportation Management System (TMS) elements. | 1020 | Yes | 1020 | 6 | 6 | 1017 | No | 1180 | No | 1180 | 0 | 0 | 1132 | No | 60 | No | 60 | 0 | 0 | 57 | No | 1300 | No | 1300 | 0 | 0 | 1157 | No | 30 | No | 30 | 0 | 0 | 23 | No | 10350 | No | 10350 | 0 | 0 | 8840 | No | 13940 | 13940 | 6 | 6 | 12226 |  |  |  | 2024-07-01 |  |  |  | 2025-04-24 |  |  |  | 2025-05-01 |  |  |  | 2025-10-01 |  |  |  | 2026-10-01 |  | 0 | No | No | No | No
121 | 03 | 5854A | SAC | 005 | Sac 5 Corridor Enhancement Project | In Sacramento, from 1.1 miles south of Elk Grove Blvd Overcrossing to Route 50 at American River Br (Br#24-68). | Roadway rehabilitation, construct HOV lanes, and install fiber optic cable | 9765 | No | 6580 | 5591 | 5591 | 5594 | No | 16970 | No | 10470 | 18483 | 11880 | 18483 | Yes | 3300 | No | 2450 | 1767 | 1428 | 2741 | No | 33070 | No | 30290 | 30173 | 26346 | 36242 | Yes | 2157 | No | 1007 | 729 | 106 | 788 | No | 289690 | No | 262670 | 260033 | 226128 | 299786 | Yes | 354952 | 313467 | 316776 | 271479 | 363634 |  | 2016-06-23 |  |  |  | 2017-04-24 |  |  |  | 2017-06-30 |  |  |  | 2018-10-22 | 2019-05-31 |  |  | 2022-12-15 |  | 2022-12-15 | No | 299785 | No | No | No | No
122 | 03 | 5859 | SAC | 5 | North Sac 5 Rehab | In and near the city of Sacramento, from American River Bridge to Sacramento River Bridge. | Rehabilitate pavement and drainage systems, upgrade facilities to Americans with Disabilities Act (ADA) standards, and upgrade guardrail, signs, and Transportation Management System (TMS) elements. | 1090 | Yes | 1090 | 0 | 0 | 1090 | No | 1900 | No | 1900 | 0 | 0 | 1871 | No | 530 | No | 530 | 0 | 0 | 530 | No | 5840 | No | 5840 | 0 | 0 | 5133 | No | 1340 | No | 1340 | 0 | 0 | 1340 | No | 46800 | No | 46800 | 0 | 0 | 38700 | No | 57500 | 57500 | 0 | 0 | 48664 |  |  |  | 2023-10-31 |  |  |  | 2025-06-24 |  |  |  | 2025-07-01 |  |  |  | 2025-12-10 |  |  |  | 2027-10-04 |  | 0 | No | No | No | No
123 | 03 | 5863 | SAC | 5 | I-5 West End Viaduct | In the city of Sacramento, at the West End Viaduct No 24-0069L/R. | Improve to standard truck capacity. (Long Lead Project). | 6170 | Yes | 6170 | 4882 | 4882 | 6129 | No | 0 | No | 0 | 0 | 0 | 5709 | Yes | 0 | No | 0 | 0 | 0 | 362 | Yes | 0 | No | 0 | 0 | 0 | 18826 | Yes | 0 | No | 0 | 2 | 0 | 2216 | Yes | 0 | No | 0 | 0 | 0 | 46100 | Yes | 6170 | 6170 | 4884 | 4882 | 79342 |  | 2022-06-30 |  | 2022-08-26 | Yes | 2026-04-25 |  | 2026-04-25 | No | 2026-07-15 |  | 2026-07-15 | No | 2026-11-07 |  | 2026-11-07 | No |  |  | 2031-09-15 |  | 0 | Yes | Yes | No | No
124 | 03 | 5868 | SAC | 5 | I-5 Permit Load Mobility Improvement | In the city of Sacramento, at South Connector Undercrossing No 24-0267. | Strengthen structure for permit loads. | 16780 | Yes | 16780 | 4909 | 4909 | 4909 | No | 827 | Yes | 827 | 579 | 579 | 833 | Yes | 50 | Yes | 50 | 11 | 11 | 46 | No | 1250 | No | 1250 | 0 | 0 | 1327 | Yes | 40 | No | 40 | 38 | 0 | 38 | No | 8000 | No | 8000 | 0 | 0 | 6701 | No | 26947 | 26947 | 5537 | 5499 | 13854 |  | 2020-07-01 | 2021-02-10 |  |  | 2022-05-09 | 2022-05-04 |  |  | 2022-05-23 | 2022-05-05 |  |  | 2022-10-21 |  | 2022-10-31 | No |  |  | 2024-05-30 |  | 0 | No | No | No | No
125 | 03 | 5960 | SAC | 12 | Rio Vista Bridge Rehab | In and near Rio Vista, at the Sacramento River Bridge No 23-0024; also in Solano County, from PM 26.3 to PM 26.4. | Rehabilitate bridge and upgrade Americans with Disabilities Act (ADA) facilities. (G13 Contingency). | 985 | Yes | 985 | 914 | 914 | 914 | No | 1675 | Yes | 1675 | 1569 | 1569 | 1654 | No | 20 | Yes | 20 | 20 | 20 | 38 | Yes | 1810 | Yes | 1810 | 0 | 0 | 1806 | No | 5 | No | 5 | 5 | 5 | 5 | No | 5788 | Yes | 5788 | 0 | 0 | 5789 | Yes | 10283 | 10283 | 2508 | 2508 | 10206 |  | 2020-12-11 | 2020-12-28 |  |  | 2022-03-10 | 2022-04-21 |  |  | 2022-03-25 | 2022-05-06 |  |  | 2022-07-22 |  | 2023-12-12 | Yes |  |  | 2025-06-27 |  | 0 | Yes | No | Yes | No
126 | 03 | 6247 | SAC | 50 | Sac 50 Paint | In the city of Sacramento, from the Sacramento River Viaduct (Pioneer Bridge) to 4th Street; also on Route 5 from 0.2 mile south of Broadway to S Street (PM 22.15 to 22.91). | Clean and paint steel bridges within Route 5/50 Interchange. | 575 | Yes | 575 | 346 | 346 | 346 | No | 940 | Yes | 940 | 865 | 865 | 865 | No | 30 | Yes | 30 | 26 | 26 | 28 | No | 3010 | Yes | 3010 | 685 | 685 | 2880 | No | 21 | No | 21 | 0 | 0 | 19 | No | 13554 | Yes | 13554 | 6449 | 6449 | 13554 | No | 18130 | 18130 | 8371 | 8371 | 17692 |  | 2019-06-20 | 2019-06-20 |  |  | 2021-02-01 | 2021-03-02 |  |  | 2021-02-01 | 2021-03-18 |  |  | 2021-09-01 | 2021-10-19 |  |  |  |  | 2024-10-01 |  | 13554 | No | No | No | No
127 | 03 | 6248 | SAC | 50 | Sac/ED Fiber Optics | In and near Rancho Cordova and Folsom, from Hazel Avenue to El Dorado County line; also in El Dorado County near El Dorado Hills, from Sacramento County line to Silva Valley Parkway/White Rock Road (PM 0.0/R1.9L/R). | Install fiber optic cable and wireless communication systems. | 400 | Yes | 400 | 346 | 346 |  | No | 1245 | Yes | 1245 | 1200 | 1200 | 1200 | No | 110 | Yes | 110 | 67 | 67 | 107 | No | 1200 | Yes | 1200 | 862 | 862 | 1163 | No | 5 | No | 5 | 2 | 2 | 3 | No | 4933 | Yes | 4933 | 2587 | 2587 | 4933 | No | 7893 | 7893 | 5064 | 5064 | 7752 |  | 2019-06-28 | 2019-06-28 |  |  | 2020-09-15 | 2020-11-02 |  |  | 2020-10-12 | 2020-12-01 |  |  | 2021-02-05 | 2021-03-18 |  |  |  |  | 2022-08-01 |  | 4933 | No | No | No | No
128 | 03 | 6250 | SAC | 50 | US 50 ICM Infrastructure | In and near the cities of Sacramento, Rancho Cordova, and Folsom, from Yolo County line to 0.8 mile east of Folsom Boulevard; also in Yolo County in West Sacramento, from Route 80 to Sacramento County line (PM 2.5/3.156). | Install Transportation Management System (TMS) field elements. | 940 | Yes | 940 | 795 | 795 | 795 | No | 3200 | Yes | 3200 | 2894 | 2894 | 2894 | No | 520 | Yes | 520 | 73 | 73 | 138 | No | 3900 | Yes | 3900 | 868 | 868 | 3939 | Yes | 200 | No | 200 | 23 | 23 | 23 | No | 32698 | Yes | 32698 | 8380 | 8380 | 32698 | No | 41458 | 41458 | 13033 | 13033 | 40487 | 2019-12-05 | 2019-08-13 | 2019-08-13 |  |  | 2020-09-16 | 2021-02-25 |  |  | 2020-10-15 | 2021-03-19 |  |  | 2021-04-05 | 2021-09-24 |  |  |  |  | 2023-12-21 |  | 32698 | No | No | No | No
129 | 03 | 6254 | SAC | 050 | Sac 50 Design-Build | In Sacramento County on Route 50 from I-5 Junction to Watt Ave. | Add high occupancy vehicle lane and pavement rehab. | 13600 | No | 7800 | 11992 | 6200 | 11997 | No | 13000 | No | 1400 | 10220 | 1385 | 10220 | No | 4300 | No | 1800 | 1351 | 577 | 1351 | No | 36800 | No | 25800 | 13379 | 9646 | 35749 | No | 5700 | No | 200 | 1481 | 33 | 0 | No | 368900 | No | 286900 | 215828 | 168873 | 397785 | Yes | 442300 | 323900 | 254251 | 186714 | 457102 |  | 2017-05-31 |  |  |  | 2020-02-03 | 2019-09-25 |  |  | 2020-02-14 | 2019-09-26 |  |  | 2020-07-15 | 2020-06-30 |  |  | 2024-12-01 |  | 2024-12-01 | No | 397785 | No | No | No | No
130 | 03 | 6402 | SAC | 51 | American River Bridge Rehabilitation | In the city of Sacramento, from north of B Street Underpass to north of Exposition Boulevard Overcrossing at the American River Bridge No 24-0003 and Cal Expo Undercrossing No 24-0133. | Widen and replace bridge deck and construct 0.14 mile of Class 1 bike and pedestrian path as a complete streets element. This is a Construction Manager/General Contractor (CMGC) project. (Additional $2,700,000 contribution for Const Cap from the city of Sacramento.) (G13 Contingency). | 4974 | Yes | 4974 | 4972 | 4972 | 4972 | No | 12000 | Yes | 12000 | 9433 | 9433 | 14643 | Yes | 600 | Yes | 600 | 436 | 436 | 700 | Yes | 0 | No | 0 | 0 | 0 | 17552 | Yes | 7634 | No | 7634 | 2606 | 2606 | 7634 | No | 0 | No | 0 | 0 | 0 | 118935 | Yes | 25208 | 25208 | 17447 | 17447 | 164436 | 2021-05-12 | 2021-02-17 | 2021-02-17 |  |  | 2023-07-01 |  | 2023-01-15 | No | 2023-08-01 |  | 2023-01-15 | No | 2024-02-01 |  | 2023-07-01 | No |  |  | 2027-12-01 |  | 0 | No | Yes | No | No
131 | 03 | 6402A | SAC | 51 | SR-51 ARB Child Project (CP1) | In the city of Sacramento, from north of B Street Underpass to north of Exposition Boulevard Overcrossing at the American River Bridge No 24-0003 and Cal Expo Undercrossing No 24-0133. | Early Work Package No 1 for Construction Manager/General Contractor (CMGC) parent project EA 3F070. Clear vegetation, construct equipment access, relocate Valley Elderberry bushes, and procure steel sheet piles and foundation piles. | 0 | No | 0 | 0 | 0 | 0 | No | 0 | No | 0 | 0 | 0 | 0 | No | 0 | No | 0 | 0 | 0 | 0 | No | 900 | Yes | 900 | 363 | 363 | 1026 | Yes | 0 | No | 0 | 0 | 0 | 0 | No | 12000 | Yes | 12000 | 3744 | 3744 | 11930 | No | 12900 | 12900 | 4107 | 4107 | 12956 |  |  | 2021-02-17 |  |  |  | 2021-11-03 |  |  |  | 2021-12-28 |  |  |  | 2022-01-20 |  |  |  |  | 2022-10-07 |  | 11929 | No | No | No | No
132 | 03 | 6402B | SAC | 51 | SR-51 ARB Child Project (CP2) | In the city of Sacramento, from north of B Street Underpass to north of Exposition Boulevard Overcrossing at the American River Bridge No 24-0003 and Cal Expo Undercrossing No24-0133. | Early Work Package No 2 for Construction Manager/General Contractor (CMGC) parent project EA 3F070. Procure steel girders. | 0 | No | 0 | 0 | 0 |  | No | 0 | No | 0 | 0 | 0 |  | No | 0 | No | 0 | 0 | 0 | 0 | No | 50 | Yes | 50 | 0 | 0 | 50 | No | 0 | No | 0 | 0 | 0 | 0 | No | 10900 | Yes | 10900 | 16 | 16 | 10899 | No | 10950 | 10950 | 16 | 16 | 10949 |  |  | 2021-02-17 |  |  |  | 2022-01-20 |  |  |  | 2022-03-30 |  |  |  | 2022-04-25 |  |  |  |  | 2023-07-01 |  | 10899 | No | No | No | No
133 | 03 | 6402C | SAC | 51 | SR-51 ARB Child Project (CP3) | In the city of Sacramento, from north of B Street Underpass to north of Exposition Boulevard Overcrossing at the American River Bridge No 24-0003 and Cal Expo Undercrossing No 24-0133. | Early Work Package No 3 for Construction Manager/General Contractor (CMGC) parent project EA 3F070. Construct the foundation for widening American River Bridge. | 0 | No | 0 | 0 | 0 |  | No | 0 | No | 0 | 0 | 0 |  | No | 0 | No | 0 | 0 | 0 | 0 | No | 7500 | Yes | 7500 | 0 | 0 | 5286 | No | 0 | No | 0 | 0 | 0 | 0 | No | 0 | Yes | 0 | 0 | 0 | 53000 | Yes | 7500 | 7500 | 0 | 0 | 58286 |  |  | 2021-02-17 |  |  |  | 2022-03-03 |  |  |  | 2022-06-16 |  |  |  | 2022-06-29 |  |  |  |  | 2024-12-01 |  | 4191 | No | Yes | No | No
134 | 03 | 6411 | SAC | 5 | SAC Connector Ramp Meters | In the city of Sacramento, at the Route 5/99 Interchange Connector ramps and the eastbound Route 51/160 Interchange Connector ramp. | Install connector ramp meters and Closed Circuit Televisions (CCTV). | 552 | Yes | 552 | 536 | 536 | 536 | No | 660 | Yes | 660 | 632 | 632 | 632 | No | 20 | Yes | 20 | 14 | 14 | 21 | Yes | 1020 | Yes | 1020 | 365 | 365 | 994 | No | 20 | No | 20 | 2 | 2 | 2 | No | 3817 | Yes | 3817 | 1880 | 1880 | 3817 | No | 6089 | 6089 | 3429 | 3429 | 6002 |  | 2019-12-02 | 2020-03-25 |  |  | 2021-03-10 | 2020-12-28 |  |  | 2021-03-25 | 2021-04-23 |  |  | 2021-07-21 | 2021-08-10 |  |  |  |  | 2022-12-02 |  | 3817 | No | No | No | No
135 | 03 | 6713 | SAC | 80 | Sac/Placer 80 Fiber Optics | In and near the cities of Sacramento and Citrus Heights, from 0.3 mile east of the Yolo County line to the Placer County line; also in Placer County, in the city of Roseville from the Sacramento County line to 0.7 mile east of the Sacramento County line (PM 0.0/0.7). | Install fiber optic communication line. | 1200 | Yes | 1200 | 389 | 389 | 389 | No | 1425 | Yes | 1425 | 1273 | 1273 | 1273 | No | 300 | Yes | 300 | 139 | 139 | 254 | No | 1800 | Yes | 1800 | 1627 | 1627 | 1804 | Yes | 50 | No | 50 | 29 | 29 | 30 | No | 11494 | Yes | 11494 | 10324 | 10324 | 11494 | No | 16269 | 16269 | 13781 | 13781 | 15244 |  | 2018-03-01 | 2018-06-15 |  |  | 2019-11-01 | 2019-10-18 |  |  | 2019-11-15 | 2019-10-24 |  |  | 2020-05-15 | 2020-06-08 |  |  |  |  | 2022-07-29 |  | 11494 | No | No | No | No
136 | 03 | 6714 | SAC | 80 | SAC 80 R&R RHMA | Near the city of Sacramento and Citrus Heights, from 0.2 mile east of Longview Drive to 0.4 mile east of Madison Avenue; also on Route 244, from Route 80 to 0.3 mile west of Auburn Boulevard (PM 0.0/0.8). | Pavement rehabilitation. | 50 | Yes | 50 | 35 | 35 | 35 | No | 1605 | Yes | 1605 | 1520 | 1520 | 1520 | No | 80 | Yes | 80 | 20 | 20 | 36 | No | 2500 | Yes | 2500 | 419 | 419 | 2585 | Yes | 100 | No | 100 | 0 | 0 | 0 | No | 13416 | Yes | 13416 | 1619 | 1619 | 13416 | No | 17751 | 17751 | 3613 | 3613 | 17592 | 2019-05-16 | 2019-01-25 | 2019-01-25 |  |  | 2020-10-07 | 2019-10-17 |  |  | 2020-10-22 | 2021-01-29 |  |  | 2021-02-04 | 2021-07-08 |  |  |  |  | 2023-06-30 |  | 13416 | No | No | No | No
137 | 03 | 6912 | SAC | 99 | Cosumnes Bridge Replc | In and near Elk Grove, from 0.3 mile south of Dillard Road Overcrossing to 0.6 mile south of Grant Line Road (replace Cosumnes River Bridge No 24-0020L/R, and Cosumnes River Overflow Bridge No 24-0021L/R; upgrade bridge rails at Dillard Road Overcrossing No 24-0163; construct new McConnell Overhead No 24-0392). | Bridge seismic retrofit, bridge scour retrofit, bridge rail replacement, and bridge replacement.This is a Construction Manager/General Contractor (CMGC) project. | 5150 | Yes | 5150 | 5068 | 5068 | 5068 | No | 15541 | Yes | 15541 | 13036 | 13036 | 13036 | No | 4000 | Yes | 4000 | 3402 | 3402 | 3989 | No | 5800 | Yes | 5800 | 2999 | 2999 | 5838 | Yes | 6000 | No | 6000 | 1293 | 1293 | 2555 | No | 56167 | Yes | 56167 | 41593 | 41593 | 51373 | No | 92658 | 92658 | 67391 | 67391 | 81859 | 2019-06-26 | 2019-05-19 | 2019-05-20 |  |  | 2020-04-16 | 2020-04-17 |  |  | 2020-05-01 | 2020-06-30 |  |  | 2020-10-30 | 2021-01-21 |  |  |  |  | 2022-12-30 |  | 51373 | No | No | No | No
138 | 03 | 6912C | SAC | 99 | McConnel OH Pre-cast Girders | n and near Elk Grove, from 0.3 mile south of Dillard Road Overcrossing to 0.6 mile south of Grant Line Road. | Early Work Package No 3 for Cosumnes River Bridge Construction Manager/General Contractor (CMGC) parent project EA 0F280. Fabricate pre-cast concrete girders for McConnell Overhead No 24-0048L. | 0 | No | 0 | 0 | 0 | 0 | No | 0 | No | 0 | 0 | 0 | 0 | No | 0 | No | 0 | 0 | 0 | 0 | No | 216 | Yes | 216 | 207 | 207 | 209 | No | 0 | No | 0 | 0 | 0 | 0 | No | 1655 | Yes | 1655 | 1566 | 1566 | 1655 | No | 1871 | 1871 | 1773 | 1773 | 1864 | [6 empty] | 2019-06-10 |  |  |  | 2019-08-26 |  |  |  | 2019-09-13 |  |  |  |  | 2024-10-29 |  | 1655 | No | No | No | No
139 | 03 | 6912D | SAC | 99 | McConnell OH | In and near Elk Grove, from 0.3 mile south of Dillard Road Overcrossing to 0.6 mile south of Grant Line Road. | Early Work Package No 4 for Cosumnes River Bridge Construction Manager/General Contractor (CMGC) parent project EA 0F280. Construct bridge over the railroad at McConnell Overhead No 24-0048L. | 0 | No | 0 | 0 | 0 |  | No | 0 | No | 0 | 0 | 0 |  | No | 0 | No | 0 | 0 | 0 | 0 | No | 1600 | Yes | 1600 | 1592 | 1592 | 1592 | No | 0 | No | 0 | 0 | 0 | 0 | No | 19030 | Yes | 19030 | 18219 | 18219 | 19030 | No | 20630 | 20630 | 19811 | 19811 | 20622 | [6 empty] | 2020-04-13 |  |  |  | 2020-04-24 |  |  |  | 2020-05-19 |  |  |  |  | 2022-12-31 |  | 19030 | No | No | No | No
140 | 03 | 6912F | SAC | 99 | River Bridges | In and near Elk Grove, from 0.3 mile south of Dillard Road Overcrossing to 0.6 mile south of Grant Line Road. | Early Work Package No 6 for Cosumnes River Bridge Construction Manager/General Contractor (CMGC) parent project EA 0F280. Remove and replace Cosumnes River Bridge No 24-0020L/R and Cosumnes River Overflow No 24-0021L/R (structure work only). | 0 | No | 0 | 0 | 0 |  | No | 0 | No | 0 | 0 | 0 |  | No | 0 | No | 0 | 0 | 0 | 0 | No | 5500 | Yes | 5500 | 5036 | 5036 | 5536 | Yes | 0 | No | 0 | 0 | 0 | 0 | No | 67659 | Yes | 67659 | 65383 | 65383 | 67658 | No | 73159 | 73159 | 70419 | 70419 | 73194 | [10 empty] | 2020-05-22 |  |  |  | 2020-06-30 |  |  |  |  | 2022-12-31 |  | 67657 | No | No | No | No
141 | 03 | 6924 | SAC | 99 | RHMA Overlay-ADA ramps/sw | In Galt, from the San Joaquin County line to Simmerhorn Road; also in the cities of Elk Grove and Sacramento, from 1.0 mile south of Elk Grove Boulevard to Martin Luther King Jr Boulevard (PM 11.8/21.6). | Pavement rehabilitation. | 1000 | Yes | 1000 | 858 | 858 | 858 | No | 2290 | Yes | 2290 | 2274 | 2274 | 2274 | No | 190 | Yes | 190 | 95 | 95 | 171 | No | 4160 | Yes | 4160 | 4042 | 4042 | 4155 | No | 22 | No | 22 | 10 | 10 | 10 | No | 38300 | Yes | 36153 | 35802 | 35802 | 38300 | No | 45962 | 43815 | 43081 | 43081 | 45768 | 2018-10-17 | 2017-05-15 | 2017-05-15 |  |  | 2019-01-10 | 2019-02-08 |  |  | 2019-01-25 | 2019-03-21 |  |  | 2019-05-07 | 2019-08-20 |  |  |  |  | 2022-08-31 |  | 36152 | No | No | No | No
142 | 03 | 6925 | SAC | 99 | Sac 99 Fiber Optics | In and near the cities of Elk Grove and Sacramento, from Grant Line Road to Route 50; also on Route 51, from Route 50 to 0.1 mile south of the Fort Sutter Viaduct (PM 0.0/0.1). | Install fiber optic cable. | 700 | Yes | 700 | 523 | 523 | 523 | No | 1215 | Yes | 1215 | 1142 | 1142 | 1170 | No | 50 | Yes | 50 | 45 | 45 | 53 | Yes | 1515 | Yes | 1515 | 0 | 0 | 1562 | Yes | 100 | No | 100 | 58 | 58 | 58 | No | 19255 | Yes | 19255 | 0 | 0 | 19267 | Yes | 22835 | 22835 | 1768 | 1768 | 22633 |  | 2019-06-28 | 2019-06-28 |  |  | 2021-07-16 | 2021-05-13 |  |  | 2021-08-02 | 2021-12-29 |  |  | 2022-01-10 |  | 2022-07-17 | Yes |  |  | 2023-11-30 |  | 0 | Yes | No | No | No
143 | 03 | 6931 | SAC | 99 | Sac 99 Fruitridge CAPM | In and near the city of Sacramento, from south of Martin Luther King Jr Boulevard to Route 50/51 Separation. | Rehabilitate pavement and drainage systems, upgrade facilities to Americans with Disabilities Act (ADA) standards, upgrade signs and Transportation Management System (TMS) elements, replace concrete barrier and guardrail, and construct maintenance vehicle pullouts. | 1170 | Yes | 1170 | 1 | 1 | 1156 | No | 2050 | No | 2050 | 0 | 0 | 1958 | No | 400 | No | 400 | 0 | 0 | 381 | No | 2940 | No | 2940 | 0 | 0 | 2653 | No | 620 | No | 620 | 0 | 0 | 617 | No | 27700 | No | 27700 | 0 | 0 | 22871 | No | 34880 | 34880 | 1 | 1 | 29636 |  |  |  | 2023-08-15 |  |  |  | 2025-11-14 |  |  |  | 2025-12-03 |  |  |  | 2026-04-13 |  |  |  | 2027-05-10 |  | 0 | No | No | No | No
144 | 03 | 6932 | SAC | 99 | SAC 99/51 Pump Plant Project | In and near Galt and city of Sacramento, on Routes 99 and 51 at various pump plant locations. | Rehabilitate and improve access to five pump plants. | 620 | Yes | 620 | 0 | 0 | 612 | No | 1640 | No | 1640 | 0 | 0 | 1585 | No | 50 | No | 50 | 0 | 0 | 25 | No | 2190 | No | 2190 | 0 | 0 | 1886 | No | 0 | No | 0 | 0 | 0 | 0 | No | 10900 | No | 10900 | 0 | 0 | 8974 | No | 15400 | 15400 | 0 | 0 | 13082 |  |  |  | 2023-10-03 |  |  |  | 2025-06-17 |  |  |  | 2025-07-02 |  |  |  | 2025-11-09 |  |  |  | 2027-11-01 |  | 0 | No | No | No | No
145 | 03 | 6936 | SAC | 99 | Willow Slough Replacement | Near Elk Grove, from Arno Road to south of Dillard Road at Willow Slough Bridge No 24-0046L/R. | Replace existing south bridge, close the median gap between southbound and northbound bridges, widen shoulders, upgrade guardrail, and install Transportation Management System (TMS) elements. | 1210 | Yes | 1210 | 8 | 8 | 1197 | No | 1820 | No | 1820 | 0 | 0 | 1643 | No | 140 | No | 140 | 0 | 0 | 131 | No | 2280 | No | 2280 | 0 | 0 | 2048 | No | 970 | No | 970 | 0 | 0 | 968 | No | 11100 | No | 11100 | 0 | 0 | 9172 | No | 17520 | 17520 | 8 | 8 | 15159 |  |  |  | 2023-11-13 |  |  |  | 2025-04-17 |  |  |  | 2025-05-01 |  |  |  | 2025-10-20 |  |  |  | 2027-10-15 |  | 0 | No | No | No | No
146 | 03 | 8376A | SUT | 099 | Live Oak Streetscape, Rehab & Safety | In Sutter County, in and near Live Oak, from south of Coleman Avenue to Nevada Street (North Intersection). | Rehabilitate pavement, improve pedestrian accessibility, add new electrical signals, upgrade drainage facilities, add streetscape elements & reduce traffic congestion by improving the vertical profile & providing two traffic lanes in each direction | 1330 | No | 520 | 1313 | 507 | 1314 | No | 2729 | No | 1511 | 2704 | 1497 | 2704 | No | 3375 | No | 745 | 2281 | 567 | 2282 | No | 2680 | No | 2576 | 2608 | 2505 | 2620 | No | 600 | No | 0 | 447 | 98 | 290 | No | 34720 | No | 26412 | 32935 | 25108 | 34482 | No | 45434 | 31764 | 42288 | 30282 | 43692 |  | 2017-08-01 |  |  |  | 2019-09-01 |  |  |  | 2019-09-01 |  |  |  | 2020-02-28 | 2020-06-09 |  |  |  |  | 2023-05-01 |  | 31899 | No | No | No | No
147 | 03 | 8784 | YOL | 80 | Yolo Pavement Rehab | In and near West Sacramento, from east of Mace Boulevard to Sacramento River Bridge; also on Route 50, from Route 80 to Jefferson Boulevard Overcrossing (PM 0.0/2.5). | Rehabilitate pavement by placing Continuous Reinforced Concrete Overlay, reconstruct existing pavement, rehabilitate bridge decks, bridge median widening at two locations, and upgrade bridge railings. (G13 Contingency). | 10337 | Yes | 10337 | 9600 | 9600 | 9600 | No | 9650 | Yes | 9650 | 8765 | 8765 | 9674 | Yes | 200 | Yes | 200 | 62 | 62 | 193 | No | 0 | No | 0 | 0 | 0 | 21894 | Yes | 50 | No | 50 | 50 | 43 | 50 | No | 0 | No | 0 | 0 | 0 | 242058 | Yes | 20237 | 20237 | 18477 | 18470 | 283469 | 2021-05-12 | 2021-02-01 | 2021-02-01 |  |  | 2022-04-18 | 2022-06-16 |  |  | 2022-04-28 | 2022-06-24 |  |  | 2022-11-03 |  | 2022-12-30 | No |  |  | 2027-12-05 |  | 0 | No | Yes | No | No
148 | 03 | 8901 | YOL | 80 | Sac River BOH (Bryte Bend) | In West Sacramento, from 0.2 mile west to 0.4 mile east of Sacramento River Bridge and Overhead No 22-0026L/R; also in Sacramento County, from Yolo County line to 0.9 mile west of West El Camino Avenue (PM M0.0/M0.5). | Rehabilitate bridge. | 1900 | Yes | 1900 | 1789 | 1789 | 1789 | No | 1750 | Yes | 1750 | 1653 | 1653 | 1653 | No | 75 | Yes | 75 | 69 | 69 | 75 | No | 4300 | Yes | 4300 | 3201 | 3201 | 4540 | Yes | 482 | No | 482 | 6 | 6 | 6 | No | 21780 | Yes | 21780 | 18855 | 18855 | 21780 | No | 30287 | 30287 | 25573 | 25573 | 29843 | 2018-12-06 | 2018-09-28 | 2018-09-28 |  |  | 2020-03-25 | 2020-03-13 |  |  | 2020-04-09 | 2020-03-23 |  |  | 2020-07-23 | 2020-09-11 |  |  |  |  | 2022-11-01 |  | 21780 | No | No | No | No
149 | 03 | 9579 | YUB | 20 | Browns Valley Rehab | Near Marysville, from Marysville Road to 0.1 mile east of Yuba River Bridge. | Rehabilitate roadway. | 4300 | Yes | 4300 | 3676 | 3676 | 3676 | No | 2800 | Yes | 2800 | 2762 | 2762 | 2762 | No | 2950 | Yes | 2950 | 2506 | 2506 | 2887 | No | 6900 | Yes | 6900 | 4893 | 4893 | 6792 | No | 9400 | No | 9400 | 3775 | 3775 | 5235 | No | 42500 | Yes | 42400 | 35720 | 35620 | 42500 | No | 68850 | 68750 | 53332 | 53232 | 63852 | 2018-10-17 | 2017-08-01 | 2017-08-01 |  |  | 2019-04-01 | 2019-06-17 |  |  | 2019-04-15 | 2019-06-20 |  |  | 2019-12-29 | 2020-01-22 |  |  |  |  | 2024-12-01 |  | 39600 | No | No | No | No
150 | 03 | 9732 | YUB | 65 | Wheatland Donut Hole HMA and ADA | In and near Wheatland, from north of State Street to north of Evergreen Drive. | Rehabilitate pavement, add bike lanes, rehabilitate drainage systems, upgrade facilities to Americans with Disabilities Act (ADA) standards, and construct Class 1 multi-use path, modify driveways, and enhance crosswalk visibility as complete streets elements. | 500 | Yes | 500 | 442 | 442 | 442 | No | 1113 | Yes | 1113 | 987 | 987 | 1206 | Yes | 510 | Yes | 510 | 279 | 279 | 648 | Yes | 580 | No | 580 | 0 | 0 | 539 | No | 270 | No | 270 | 93 | 93 | 252 | No | 7650 | No | 7650 | 0 | 0 | 7650 | No | 10623 | 10623 | 1801 | 1801 | 10737 |  | 2021-05-03 | 2021-05-03 |  |  | 2022-10-20 |  | 2022-11-18 | No | 2022-11-04 |  | 2022-12-02 | No | 2023-04-03 |  | 2023-04-03 | No |  |  | 2023-12-14 |  | 0 | No | No | No | No
151 | 03 | 9812 | YUB | 70 | Simmerly Slough (SHOPP) | Near Marysville, from 0.1 mile north of Binney Junction Underpass to 0.3 mile north of Laurellen Road, at Simmerly Slough Bridge No 16-0019. | Replace bridge. | 1960 | Yes | 1960 | 1926 | 1926 | 1926 | No | 3555 | Yes | 3555 | 3536 | 3536 | 3536 | No | 950 | Yes | 950 | 880 | 880 | 954 | Yes | 6580 | Yes | 6580 | 6570 | 6570 | 6626 | Yes | 3800 | No | 3800 | 2830 | 2830 | 3035 | No | 45046 | Yes | 45046 | 42547 | 42547 | 45046 | No | 61891 | 61891 | 58289 | 58289 | 61123 | 2018-10-17 | 2017-06-21 | 2017-06-21 |  |  | 2018-11-16 | 2019-02-01 |  |  | 2018-12-06 | 2019-03-25 |  |  | 2019-04-07 | 2019-08-23 |  |  |  |  | 2023-12-01 |  | 45045 | No | No | No | No
152 | 03 | 9820 | YUB | 70 | Marysville Railroad Bridge Rehab (SHOPP) | In and near Marysville, from south of 14th Street to north of Cemetery Road. | Roadway rehabilitation and operational improvements including turn pockets and auxiliary lanes. (G13 Contingency). | 3500 | Yes | 3500 | 3425 | 3425 | 3425 | No | 4534 | Yes | 4534 | 1917 | 1917 | 9259 | Yes | 2775 | Yes | 2775 | 953 | 953 | 3058 | Yes | 0 | No | 0 | 0 | 0 | 11127 | Yes | 15300 | No | 15300 | 643 | 643 | 15258 | No | 0 | No | 0 | 0 | 0 | 85960 | Yes | 26109 | 26109 | 6938 | 6938 | 128087 | 2021-03-25 | 2020-12-07 | 2020-12-07 |  |  | 2023-09-07 |  | 2023-09-07 | No | 2023-10-04 |  | 2023-10-04 | No | 2024-02-12 |  | 2024-02-12 | No |  |  | 2026-12-18 |  | 0 | No | Yes | No | No
153 | 03 | 9822 | YUB | 70 | YUB 70 Bridge Widening and Rail Replc | Near Marysville, at Feather River Boulevard Overcrossing No 16-0033 (PM 13.01) and South Marysville Undercrossing No 16-0035 (PM 13.23). | Upgrade bridge rails and construct median concrete barrier between project limits. | 900 | Yes | 900 | 875 | 875 | 875 | No | 1540 | Yes | 1540 | 900 | 900 | 900 | No | 30 | Yes | 30 | 29 | 29 | 39 | Yes | 1290 | Yes | 1290 | 521 | 521 | 1316 | Yes | 10 | No | 10 | 12 | 12 | 7 | No | 8046 | Yes | 8046 | 1717 | 1717 | 8046 | No | 11816 | 11816 | 4054 | 4054 | 11183 |  | 2021-01-04 | 2020-11-17 |  |  | 2022-07-15 | 2021-06-04 |  |  | 2022-08-15 | 2021-06-16 |  |  | 2023-02-01 | 2021-11-12 |  |  |  |  | 2022-12-15 |  | 8045 | No | No | No | No
154 | 04 | 0050N | ALA | 880 | Lake Merritt Railroad Bridge Replacement | In Oakland, near Lake Merrit Channel Bridge No 33-0027 and 5th Avenue. | Replace Hanlon Lead Railroad bridge. Mitigation for EA 1706U. | 500 | No | 500 | 1029 | 1029 | 1029 | Yes | 3179 | Yes | 3179 | 3483 | 3483 | 3483 | Yes | 892 | Yes | 892 | 858 | 858 | 956 | Yes | 3600 | Yes | 3600 | 344 | 344 | 3154 | No | 7500 | No | 7500 | 377 | 377 | 11995 | Yes | 7226 | Yes | 7226 | 88 | 88 | 7226 | No | 22897 | 22897 | 6179 | 6179 | 27843 |  |  | 2015-05-11 |  |  |  | 2021-07-15 |  |  |  | 2021-07-16 |  |  |  | 2022-03-30 |  |  |  |  | 2023-12-01 |  | 7225 | No | Yes | No | No
155 | 04 | 0064A | ALA | 80 | Install 26 Miles of Fiber Optics Trunk Line, Hubs and TOS/TMS Elements | In Alameda, Contra Costa, and Solano Counties, on Routes 80, 580, and 980 at various locations; also on local streets from Route 980 to the District 4 Transportation Management Center (TMC). | Install fiber optic cable and install and upgrade Transportation Management System (TMS) elements. | 2220 | No | 2220 | 2359 | 2359 | 2359 | Yes | 10497 | Yes | 10497 | 5637 | 5637 | 10781 | Yes | 121 | Yes | 121 | 110 | 110 | 228 | Yes | 4140 | No | 4140 | 17 | 17 | 7285 | Yes | 320 | No | 320 | 51 | 51 | 320 | No | 93346 | No | 93346 | 0 | 0 | 93346 | No | 110644 | 110644 | 8174 | 8174 | 114319 | 2020-10-22 | 2020-06-24 | 2016-05-13 |  |  | 2023-05-01 |  | 2022-11-30 | No | 2022-10-01 |  | 2023-01-20 | Yes | 2023-05-01 |  | 2023-08-09 | Yes |  |  | 2026-03-02 |  | 0 | Yes | Yes | Yes | No
156 | 04 | 0084B | ALA | 84 | NILES CANYON ALAMEDA CREEK BRIDGE REPLACEMENT PROJECT | In Fremont, from 0.3 mile south to 0.3 mile north of Alameda Creek Bridge No 33-0036. | Replace bridge. | 7800 | Yes | 7800 | 7478 | 7478 | 7478 | No | 6500 | Yes | 6500 | 6115 | 6115 | 6115 | No | 600 | Yes | 600 | 418 | 418 | 805 | Yes | 4700 | Yes | 4700 | 4109 | 4109 | 6058 | Yes | 275 | No | 275 | 528 | 528 | 551 | Yes | 20522 | Yes | 20522 | 10957 | 10957 | 20522 | No | 40397 | 40397 | 29605 | 29605 | 41529 | 2018-10-17 | 2017-09-25 | 2017-09-25 |  |  | 2019-05-20 | 2020-04-16 |  |  | 2019-06-03 | 2020-05-04 |  |  | 2019-12-08 | 2020-12-15 |  |  |  |  | 2024-12-01 |  | 20521 | No | Yes | No | No
157 | 04 | 0086R | CC | 580 | Scofield Ave UC Seismic Retrofit CMGC | In Richmond, at Scofield Avenue Undercrossing No 28-140L/R. | Seismic retrofit. This is a Construction Manager/General Contractor (CMGC) project. | 750 | No | 750 | 340 | 340 | 340 | No | 4914 | Yes | 4914 | 4703 | 4703 | 4703 | No | 227 | Yes | 227 | 175 | 175 | 204 | No | 6788 | Yes | 6788 | 4192 | 4192 | 6619 | No | 872 | No | 872 | 782 | 782 | 91 | No | 24974 | Yes | 24974 | 15607 | 15607 | 16782 | No | 38525 | 38525 | 25799 | 25799 | 28739 |  | 2019-10-14 |  |  |  | 2020-04-30 | 2021-01-22 |  |  | 2020-05-01 | 2021-01-22 |  |  | 2020-07-09 | 2021-04-13 |  |  |  |  | 2023-04-03 |  | 16782 | Yes | Yes | Yes | Yes
158 | 04 | 0222F | CC | 680 | BRIDGE DECK PROGRAM | In San Ramon, Danville, and Walnut Creek, at various locations. | Apply polyester concrete overlay to bridge decks. (Bridge Deck Preservation). | 109 | Yes | 109 | 108 | 108 | 108 | No | 1203 | Yes | 1203 | 754 | 754 | 1819 | Yes | 55 | Yes | 55 | 3 | 3 | 53 | No | 2343 | No | 2343 | 0 | 0 | 2416 | Yes | 0 | No | 0 | 0 | 0 | 0 | No | 8900 | No | 8900 | 0 | 0 | 8895 | No | 12610 | 12610 | 865 | 865 | 13291 |  |  | 2022-06-28 |  |  |  | 2022-06-29 |  |  |  | 2022-06-29 |  |  |  |  | 2022-09-23 |  |  |  | 2023-09-22 |  | 0 | No | No | No | No
159 | 04 | 0269H | CC | 242 | CC 242 Pavement Rehab | In Concord, from Route 680 to 0.1 mile north of Concord Avenue. | Pavement rehabilitation in northbound direction. | 1229 | Yes | 1229 | 1228 | 1228 | 1228 | No | 1340 | Yes | 1340 | 1337 | 1337 | 1337 | No | 110 | Yes | 110 | 20 | 20 | 78 | No | 1687 | Yes | 1687 | 1673 | 1673 | 1783 | Yes | 15 | No | 15 | 0 | 0 | 0 | No | 10911 | Yes | 10911 | 9342 | 9342 | 10911 | No | 15292 | 15292 | 13600 | 13600 | 15337 |  | 2018-06-29 | 2019-05-15 |  |  | 2020-03-04 | 2020-05-26 |  |  | 2020-06-30 | 2020-06-12 |  |  | 2020-12-18 | 2020-12-17 |  |  |  |  | 2022-07-15 |  | 10910 | No | No | No | No
160 | 04 | 0269M | SON | 12 | SON 12 Bridge Scour Mitigation | In and near Sonoma, at Sonoma Creek Bridge No 20-0027 and Hooker Creek Bridge No 20-0030. | Scour mitigation. | 1519 | Yes | 1519 | 1510 | 1510 | 1510 | No | 3710 | Yes | 3710 | 3485 | 3485 | 5313 | Yes | 500 | Yes | 500 | 417 | 417 | 488 | No | 1670 | Yes | 1670 | 0 | 0 | 3397 | Yes | 4420 | No | 4420 | 250 | 250 | 3404 | No | 9957 | Yes | 9957 | 0 | 0 | 12543 | Yes | 21776 | 21776 | 5662 | 5662 | 26655 |  | 2018-06-01 | 2018-09-12 |  |  | 2019-12-16 | 2021-12-31 |  |  | 2020-02-07 | 2022-01-05 |  |  | 2020-12-01 |  | 2022-07-22 | Yes |  |  | 2025-01-13 |  | 0 | Yes | Yes | No | No
161 | 04 | 0273S | ALA | 680 | HM315 Bridge Program | In and near Fremont and Hayward, on Routes 580, 680, 880 at various locations. | Apply polyester concrete overlay to bridge decks. (Bridge Deck Preservation). | 105 | Yes | 105 | 105 | 105 | 105 | No | 1631 | Yes | 1631 | 96 | 96 | 1811 | Yes | 28 | Yes | 28 | 1 | 1 | 55 | Yes | 2614 | No | 2614 | 0 | 0 | 2645 | Yes | 0 | No | 0 | 0 | 0 | 0 | No | 8600 | No | 8600 | 0 | 0 | 8600 | No | 12978 | 12978 | 202 | 202 | 13216 |  |  | 2022-03-16 | 2022-08-15 |  |  |  | 2023-04-06 |  |  |  | 2023-06-16 |  |  |  | 2023-09-22 |  |  |  | 2024-09-23 |  | 0 | No | No | No | Yes
162 | 04 | 0298E | CC | 4 | I-680/SR 4 Interchange - Widen Route 4 (Phase 3) | In Pacheco around the I-680/SR 4 Interchange: Widen State Route 4 in the median to provide a third lane in each direction from Morello Avenue to State Route 242. | Widen five bridge structures at Pacheco Blvd, I-680, Walnut Creek, Solano Way and Peralta Road, and replacement of Grayson Creek Bridge in each direction of SR 4. | 5000 | No | 0 | 5000 | 0 | 5000 | No | 9900 | No | 100 | 10089 | 0 | 10089 | Yes | 1000 | No | 0 | 1005 | 0 | 1005 | Yes | 0 | No | 0 | 10488 | 0 | 11117 | Yes | 18700 | No | 0 | 9566 | 0 | 9566 | No | 101695 | Yes | 21596 | 99132 | 21064 | 99749 | No | 136295 | 21696 | 135280 | 21064 | 136526 | 2018-10-17 | 2009-02-19 | 2009-02-19 |  |  | 2018-04-19 | 2018-04-19 |  |  | 2018-05-25 | 2018-05-30 |  |  | 2018-09-19 | 2018-12-03 |  |  | 2020-10-30 |  | 2023-06-16 | Yes | 97702 | Yes | Yes | No | No
163 | 04 | 0332C | MRN | 37 | Petaluma River Bridge | Near Novato, at Petaluma River Bridge No 27-0013. | Rehabilitate bridge deck, upgrade railings, replace fender system, and mitigate bridge scour. (G13 Contingency). | 1810 | Yes | 1810 | 1056 | 1056 | 1987 | Yes | 3630 | No | 3630 | 0 | 0 | 4136 | Yes | 110 | No | 110 | 0 | 0 | 112 | Yes | 0 | No | 0 | 0 | 0 | 7395 | Yes | 130 | No | 130 | 0 | 0 | 2146 | Yes | 0 | No | 0 | 0 | 0 | 26342 | Yes | 5680 | 5680 | 1056 | 1056 | 42118 |  | 2022-10-06 |  | 2022-10-06 | No | 2024-04-05 |  | 2024-04-05 | No | 2024-06-30 |  | 2024-06-30 | No | 2025-02-07 |  | 2025-02-07 | No |  |  | 2026-10-30 |  | 0 | No | Yes | No | No
164 | 04 | 0350H | MRN | 101 | Bridge replacement San Rafael harbor creek | In San Rafael, from Route 101 northbound offramp to 2nd Street at San Rafael Harbor Bridge No 27-0033S. | Replace bridge. | 1190 | Yes | 1190 | 1015 | 1015 | 1015 | No | 2540 | Yes | 2540 | 2539 | 2539 | 2539 | No | 300 | Yes | 300 | 262 | 262 | 325 | Yes | 4200 | Yes | 4200 | 2933 | 2933 | 3867 | No | 0 | No | 0 | 112 | 112 | 1279 | Yes | 15078 | Yes | 15078 | 11194 | 11194 | 15078 | No | 23308 | 23308 | 18055 | 18055 | 24103 |  |  | 2017-07-07 |  |  |  | 2020-03-06 |  |  |  | 2019-08-02 |  |  |  | 2020-05-26 |  |  |  |  | 2022-12-30 |  | 15078 | No | Yes | No | No
165 | 04 | 0386F | SCL | 9 | SCL 9 Saratoga Bridge Project | Near Saratoga, at Saratoga Creek Bridge No 37-0074. | Replace bridge. | 3720 | Yes | 3720 | 3702 | 3702 | 3702 | No | 4605 | Yes | 4605 | 4451 | 4451 | 4834 | Yes | 1200 | Yes | 1200 | 476 | 476 | 1042 | No | 3100 | No | 3100 | 0 | 0 | 3003 | No | 9111 | No | 9111 | 827 | 827 | 9111 | No | 15432 | No | 15432 | 0 | 0 | 11668 | No | 37168 | 37168 | 9456 | 9456 | 33360 |  | 2019-10-15 | 2020-01-28 |  |  | 2021-10-01 |  | 2022-07-15 | Yes | 2022-03-04 |  | 2022-08-12 | Yes | 2022-10-15 |  | 2023-02-17 | Yes |  |  | 2024-09-30 |  | 0 | Yes | No | No | No
166 | 04 | 0417A | ALA | 580 | Adeline St UC and Lakeshore Park UC Br Overlay | In Oakland, at Lakeshore Park Undercrossing No 33-0131; also at Adeline Street Undercrossing No 33-0280L (PM 45.7). | Overlay bridge decks with polyester concrete. | 994 | Yes | 994 | 0 | 0 | 995 | Yes | 1860 | No | 1860 | 0 | 0 | 1893 | Yes | 11 | No | 11 | 0 | 0 | 11 | No | 2384 | No | 2384 | 0 | 0 | 2387 | Yes | 0 | No | 0 | 0 | 0 | 0 | No | 6279 | No | 6279 | 0 | 0 | 6354 | Yes | 11528 | 11528 | 0 | 0 | 11640 |  |  |  | 2024-04-22 |  |  |  | 2025-11-03 |  |  |  | 2025-12-01 |  |  |  | 2026-06-01 |  |  |  | 2027-08-02 |  | 0 | No | No | No | No
167 | 04 | 0449A | SCL | 280 | SCL-SM-280 CAPM | In and near Los Altos, Los Altos Hills, and Palo Alto, from Foothill Boulevard to San Mateo County line (PM 11.5/20.625); also in San Mateo County, from Santa Clara County line to 0.5 mile north of Sand Hill Road (PM R0.0/R2.1). | Pavement rehabilitation. | 1853 | Yes | 1853 | 1482 | 1482 | 1482 | No | 3284 | Yes | 3284 | 3242 | 3242 | 3242 | No | 48 | Yes | 48 | 23 | 23 | 51 | Yes | 5500 | Yes | 5500 | 5269 | 5269 | 5615 | Yes | 50 | No | 50 | 0 | 0 | 50 | No | 53233 | Yes | 53233 | 46524 | 46524 | 53233 | No | 63968 | 63968 | 56540 | 56540 | 63673 | 2018-10-17 | 2017-12-01 | 2017-12-01 |  |  | 2019-04-15 | 2019-06-06 |  |  | 2019-05-01 | 2019-06-25 |  |  | 2019-11-01 | 2020-02-19 |  |  |  |  | 2022-07-29 |  | 53233 | No | No | No | No
168 | 04 | 0480A | ALA | 880 | PATTERSON SLOUGH CREEK BRIDGE DECK REPLACEMENT | In Fremont, from 0.4 mile south to 0.4 mile north of Patterson Slough Bridge No 33-0250 (PM 11.8). | Bridge rehabilitation. | 2200 | Yes | 2200 | 2012 | 2012 | 2012 | No | 2378 | Yes | 2378 | 2378 | 2378 | 2378 | No | 704 | Yes | 704 | 95 | 95 | 182 | No | 3012 | Yes | 3012 | 2786 | 2786 | 2973 | No | 427 | No | 427 | 52 | 52 | 427 | No | 8894 | Yes | 8894 | 8382 | 8382 | 8894 | No | 17615 | 17615 | 15705 | 15705 | 16866 | 2019-05-16 | 2019-03-07 | 2019-03-07 |  |  | 2020-06-29 | 2020-06-30 |  |  | 2020-06-30 | 2020-06-30 |  |  | 2021-02-10 | 2021-01-26 |  |  |  |  | 2022-07-15 |  | 8894 | No | No | No | No
169 | 04 | 0480B | CC | 24 | Caldecott Tunnel Rehab | In Orinda, at the Caldecott Tunnel No 28-0015R, 28-0015, and 28-0015L. | Rehabilitate Caldecott Tunnel Bores 1, 2, and 3. | 6269 | Yes | 6269 | 0 | 0 | 5169 | No | 8371 | No | 8371 | 0 | 0 | 1657 | No | 184 | No | 184 | 0 | 0 | 379 | Yes | 12090 | No | 12090 | 0 | 0 | 438 | No | 253 | No | 253 | 0 | 0 | 253 | No | 42320 | No | 42320 | 0 | 0 | 42320 | No | 69487 | 69487 | 0 | 0 | 50216 |  |  |  | 2024-10-01 |  |  |  | 2026-04-01 |  |  |  | 2026-05-01 |  |  |  | 2026-10-01 |  |  |  | 2029-03-01 |  | 0 | Yes | Yes | Yes | Yes
170 | 04 | 0480C | MRN | 1 | Millerton Gulch Br Scour Mitigation | Near Point Reyes Station, at Millerton Gulch Bridge No 27-0114. | Environmental mitigation for emergency project EA 4K500. | 1620 | Yes | 1620 | 1133 | 1133 | 1133 | No | 1080 | Yes | 1080 | 267 | 267 | 267 | No | 180 | Yes | 180 | 43 | 43 | 107 | No | 830 | Yes | 830 | 217 | 217 | 824 | No | 150 | No | 150 | 0 | 0 | 150 | No | 836 | Yes | 836 | 234 | 234 | 1000 | Yes | 4696 | 4696 | 1894 | 1894 | 3481 |  | 2017-12-01 | 2017-12-26 |  |  | 2019-06-07 | 2018-10-22 |  |  | 2019-06-21 | 2018-12-05 |  |  | 2020-02-04 | 2019-07-05 |  |  |  |  | 2023-07-31 |  | 740 | Yes | Yes | Yes | Yes
171 | 04 | 0480D | SOL | 84 | Real McCoy Fender & Ramp Replacement | Near Rio Vista, at the Cache Slough Ferry Crossing at Bridge No 23-0245 (ferry) and Bridge No 23-0034 (ferry landings). | Upgrade the existing fender 201.119 systems, concrete ramps, and swing gate systems, modify the ferry boat deck surface, and install traffic counter and Vehicle Detection Systems (VDS). (G13 Contingency). | 2080 | Yes | 2080 | 1474 | 1474 | 1474 | No | 2080 | No | 2080 | 0 | 0 | 2151 | Yes | 260 | No | 260 | 0 | 0 | 257 | No | 0 | No | 0 | 0 | 0 | 2620 | Yes | 350 | No | 350 | 3 | 3 | 321 | No | 0 | No | 0 | 0 | 0 | 12630 | Yes | 4770 | 4770 | 1477 | 1477 | 19453 |  | 2022-06-30 | 2022-06-28 |  |  | 2024-06-14 |  | 2024-06-14 | No | 2024-06-28 |  | 2024-06-28 | No | 2024-12-19 |  | 2024-12-19 | No |  |  | 2026-06-30 |  | 0 | No | Yes | No | No
172 | 04 | 0480N | SOL | 80 | Br Rehab+Scour | Near Dixon, at McCune Creek Bridge No 23-0084L/R; also in Vacaville on Route 505 at Horse Creek Bridge No 23-0077L (PM 0.21). | Bridge preventative maintenance. | 990 | Yes | 990 | 927 | 927 | 927 | No | 880 | Yes | 880 | 879 | 879 | 879 | No | 79 | Yes | 79 | 65 | 65 | 65 | No | 1273 | Yes | 1273 | 1147 | 1147 | 1328 | Yes | 715 | No | 715 | 251 | 251 | 715 | No | 2926 | Yes | 2926 | 1927 | 1927 | 2926 | No | 6863 | 6863 | 5196 | 5196 | 6840 |  | 2019-03-22 | 2019-03-22 |  |  | 2020-09-21 | 2020-09-23 |  |  | 2020-09-25 | 2020-10-09 |  |  | 2021-04-14 | 2021-04-01 |  |  |  |  | 2022-12-31 |  | 2926 | No | No | No | Yes
173 | 04 | 0480Q | SOL | 12 | Sol-12 Rehab - SEG 1 | Near Rio Vista, from Currie Road to Azevedo Road. | Rehabilitate roadway by resurfacing the pavement, upgrading guardrails and drainage systems, and upgrading curb ramps to Americans with Disabilities Act (ADA) standards. This project will improve safety and ride quality. | 5780 | No | 5780 | 5763 | 5763 | 5763 | No | 1000 | Yes | 1000 | 1664 | 1664 | 1732 | Yes | 49 | Yes | 49 | 102 | 102 | 142 | Yes | 1064 | Yes | 1064 | 0 | 0 | 1063 | No | 144 | No | 144 | 34 | 34 | 143 | No | 3707 | Yes | 3707 | 0 | 0 | 3692 | No | 11744 | 11744 | 7563 | 7563 | 12535 |  | 2019-11-22 | 2019-11-22 |  |  | 2022-01-01 | 2022-03-18 |  |  | 2022-02-01 | 2022-04-28 |  |  | 2022-08-01 |  | 2022-10-18 | No |  |  | 2023-12-29 |  | 0 | No | No | No | Yes
174 | 04 | 0480S | SOL | 12 | Sol-12 Rehab - SEG 3 | In Rio Vista, from Drouin Drive to Sacramento County line. | Roadway resurfacing and rehabilitation, widening, and sidewalk upgrade. (G13 Contingency). | 0 | No | 0 | 0 | 0 | 0 | No | 2780 | Yes | 2780 | 503 | 503 | 2920 | Yes | 1377 | Yes | 1377 | 35 | 35 | 918 | No | 0 | No | 0 | 0 | 0 | 2670 | Yes | 828 | No | 828 | 0 | 0 | 828 | No | 0 | No | 0 | 0 | 0 | 10940 | Yes | 4985 | 4985 | 538 | 538 | 18276 |  | 2019-11-22 | 2019-11-22 |  |  | 2023-04-30 |  | 2024-03-01 | Yes | 2023-06-01 |  | 2023-06-30 | No | 2023-10-01 |  | 2023-12-01 | No |  |  | 2024-12-31 |  | 0 | Yes | Yes | No | Yes
175 | 04 | 0480X | SOL | 12 | Sol 12 Rehab - SEG2 | In and near Rio Vista, from Summerset Road to Drouin Drive. | Roadway resurfacing and rehabilitation, realignment, and widening. (G13 Contingency). | 0 | No | 0 | 0 | 0 |  | No | 2000 | Yes | 2000 | 335 | 335 | 1956 | No | 1464 | Yes | 1464 | 24 | 24 | 1458 | No | 0 | No | 0 | 0 | 0 | 7826 | Yes | 2010 | No | 2010 | 5 | 5 | 2010 | No | 0 | No | 0 | 0 | 0 | 58568 | Yes | 5474 | 5474 | 364 | 364 | 71818 |  |  | 2019-11-22 |  |  |  |  | 2023-10-02 |  |  |  | 2023-10-16 |  |  |  | 2024-04-01 |  |  |  | 2024-12-31 |  | 0 | No | Yes | No | Yes
176 | 04 | 0481H | SCL | 101 | SCL 101 Br. Rail Replacement/Upgrade | Near Gilroy, at Sargent Bridge and Overhead No 37-0006L (PM R0.77), Pajaro River Bridge No 37-0007 (PM 0.03), and Carnadero Creek Bridge Nos. | 37-0008L/R (PM 4.2); also on Route 237 in Sunnyvale at Route 237/101 Separation No 37-0178 (PM 2.45). Bridge rail upgrade of five structures at four locations. | 1800 | Yes | 1800 | 1673 | 1673 | 1673 | No | 2250 | Yes | 2250 | 2269 | 2269 | 2269 | Yes | 50 | Yes | 50 | 42 | 42 | 46 | No | 2700 | Yes | 2700 | 1474 | 1474 | 3113 | Yes | 70 | No | 70 | 7 | 7 | 70 | No | 9606 | Yes | 9606 | 4118 | 4118 | 9606 | No | 16476 | 16476 | 9583 | 9583 | 16777 |  | 2018-09-14 | 2018-10-05 |  |  | 2020-03-16 | 2020-06-30 |  |  | 2020-06-15 | 2020-06-30 |  |  | 2020-12-21 | 2021-04-15 |  |  |  |  | 2023-06-01 |  | 9606 | No | No | No | No
177 | 04 | 0481M | ALA | 84 | Scour at Arroyo De La Laguna | Near Sunol, at Arroyo De La Laguna Bridge No 33-0043. | Replace bridge, realign roadway and construct roundabouts. | 2249 | Yes | 2249 | 2236 | 2236 | 2236 | No | 4200 | Yes | 4200 | 550 | 550 | 5302 | Yes | 275 | Yes | 275 | 1 | 1 | 275 | No | 4000 | No | 4000 | 0 | 0 | 3950 | No | 1500 | No | 1500 | 4 | 4 | 443 | No | 16000 | No | 16000 | 0 | 0 | 13000 | No | 28224 | 28224 | 2791 | 2791 | 25206 |  | 2021-11-30 | 2021-12-21 |  |  | 2023-04-15 |  | 2023-08-01 | Yes | 2023-09-01 |  | 2023-09-01 | No | 2024-05-19 |  | 2024-05-19 | No |  |  | 2026-12-01 |  | 0 | Yes | Yes | No | No
178 | 04 | 0481P | ALA | 680 | REHABILITATE PAVEMENT | In and near Pleasanton and Dublin, from Koopman Road Undercrossing to Alcosta BoulevaRd Roadway rehabilitation in northbound direction. | ROADWAY REHABILITATION. | 7150 | Yes | 7150 | 3233 | 3233 | 3233 | No | 7150 | Yes | 7150 | 6254 | 6254 | 7196 | Yes | 1500 | Yes | 1500 | 36 | 36 | 1474 | No | 9400 | Yes | 9400 | 311 | 311 | 9352 | No | 75 | No | 75 | 120 | 120 | 120 | Yes | 72730 | Yes | 72730 | 0 | 0 | 69900 | No | 98005 | 98005 | 9954 | 9954 | 91275 | 2019-06-26 | 2019-05-01 | 2019-05-01 |  |  | 2020-05-15 | 2021-06-17 |  |  | 2020-06-01 | 2021-06-21 |  |  | 2021-03-30 |  | 2022-05-12 | Yes |  |  | 2024-12-31 |  | 72730 | Yes | No | No | No
179 | 04 | 0481R | SOL | 80 | sol 80 raise oc | In Vallejo, from Magazine Street Overcrossing No 23-0066 to Redwood Street Overcrossing No 23-0114. | Increase vertical clearance at six overcrossing structures. ACCELERATED BRIDGE. | 2100 | Yes | 2100 | 2054 | 2054 | 2054 | No | 2154 | Yes | 2154 | 2183 | 2183 | 2183 | Yes | 154 | Yes | 154 | 11 | 11 | 11 | No | 7714 | Yes | 7714 | 6217 | 6217 | 7716 | Yes | 10 | No | 10 | 10 | 10 | 250 | Yes | 27963 | Yes | 27963 | 19282 | 19282 | 27963 | No | 40095 | 40095 | 29757 | 29757 | 40177 | 2018-10-17 | 2018-07-23 | 2018-07-23 |  |  | 2019-06-01 | 2019-06-24 |  |  | 2019-06-14 | 2019-06-28 |  |  | 2020-01-15 | 2020-04-16 |  |  |  |  | 2024-06-01 |  | 27963 | No | Yes | No | No
180 | 04 | 0487R | SOL | 80 | Suisun Crk Br Scour Mitigation | Near Fairfield, at Suisun Creek Bridge No 23-0007. | Scour mitigation. | 1550 | Yes | 1550 | 1238 | 1238 | 1238 | No | 714 | Yes | 714 | 713 | 713 | 713 | No | 99 | Yes | 99 | 65 | 65 | 80 | No | 1000 | Yes | 1000 | 809 | 809 | 1138 | Yes | 50 | No | 50 | 18 | 18 | 46 | No | 1364 | Yes | 1364 | 1124 | 1124 | 1364 | No | 4777 | 4777 | 3967 | 3967 | 4579 |  | 2018-09-03 | 2019-03-11 |  |  | 2020-04-01 | 2020-06-30 |  |  | 2020-04-01 | 2020-08-14 |  |  | 2020-10-01 | 2021-03-11 |  |  |  |  | 2023-11-30 |  | 1363 | No | No | No | Yes
181 | 04 | 0488K | SON | 12 | CAPM 12 | In and near Sonoma, from Vallejo Avenue to 0.2 mile east of Leveroni Road/Napa Road. | Pavement rehabilitation. | 1308 | Yes | 1308 | 1307 | 1307 | 1307 | No | 1333 | Yes | 1333 | 1325 | 1325 | 1325 | No | 248 | Yes | 248 | 68 | 68 | 115 | No | 1300 | Yes | 1300 | 1130 | 1130 | 1279 | No | 5 | No | 5 | 0 | 0 | 70 | Yes | 7838 | Yes | 7838 | 6420 | 6420 | 7838 | No | 12032 | 12032 | 10250 | 10250 | 11934 |  | 2018-04-01 | 2018-04-03 |  |  | 2020-01-02 | 2020-08-14 |  |  | 2020-02-01 | 2020-08-14 |  |  | 2020-07-30 | 2021-03-25 |  |  |  |  | 2022-08-30 |  | 7038 | No | No | No | No
182 | 04 | 0587K | NAP | 128 | SR 128 Conn Creek Bridge Replacement Plant Establishment | Near Rutherford, at Conn Creek Bridge No 21-0021. | Plant establishment mitigation for bridge replacement project EA 1G430. | 0 | No | 0 | 0 | 0 | 0 | No | 122 | Yes | 122 | 48 | 48 | 90 | No | 89 | Yes | 89 | 53 | 53 | 91 | Yes | 200 | Yes | 200 | 2 | 2 | 217 | Yes | 30 | No | 30 | 2 | 2 | 2 | No | 253 | Yes | 253 | 0 | 0 | 220 | No | 694 | 694 | 105 | 105 | 620 |  | 2015-10-05 | 2015-10-05 |  |  | 2021-04-02 | 2021-08-10 |  |  | 2021-05-07 | 2021-08-23 |  |  | 2022-02-04 |  | 2022-07-12 | Yes |  |  | 2031-10-31 |  | 0 | Yes | No | No | No
183 | 04 | 0587M | NAP | 29 | Env. Mitigation and Establishment | In Calistoga, at Napa River Bridge No 21-0018. | Environmental mitigation and plant establishment for bridge replacement project. | 0 | No | 0 | 0 | 0 |  | No | 640 | Yes | 640 | 608 | 608 | 608 | No | 400 | Yes | 400 | 72 | 72 | 94 | No | 150 | Yes | 150 | 131 | 131 | 216 | Yes | 85 | No | 85 | 0 | 0 | 0 | No | 314 | Yes | 314 | 113 | 113 | 314 | No | 1589 | 1589 | 924 | 924 | 1232 |  | 2015-02-09 | 2015-02-09 |  |  | 2019-06-14 | 2019-05-10 |  |  | 2019-06-28 | 2019-05-29 |  |  | 2019-12-27 | 2020-05-28 |  |  |  |  | 2024-06-30 |  | 314 | No | No | No | No
184 | 04 | 0658D | SCL,SM | 101 | US 101 Managed Lanes Project - Northern Segment | In the cities of San Carlos, Millbrae, Burlingame, San Mateo and Belmont in San Mateo County, and Menlo Park and East Palo Alto in Santa Clara County, from Matadero Creek to just North of I-380. | Construct Express Lanes, from Whipple Avenue to just North of I-380. | 21000 | No | 0 | 14335 | 0 | 14335 | No | 38477 | Yes | 0 | 22064 | 0 | 22064 | No | 1000 | No | 0 | 174 | 0 | 242 | No | 29000 | Yes | 0 | 15643 | 362 | 24076 | No | 4500 | No | 0 | 2147 | 0 | 2750 | No | 314540 | Yes | 0 | 340737 | 30929 | 359140 | Yes | 408517 | 0 | 395100 | 31291 | 422607 | 2018-08-15 | 2018-10-31 | 2018-10-31 |  |  | 2019-05-01 | 2019-10-03 |  |  | 2019-05-01 | 2019-10-04 |  |  | 2019-07-01 | 2020-01-09 |  |  | 2023-02-01 |  | 2023-02-01 | No | 359140 | No | Yes | No | No
185 | 04 | 0732J | SM | 280 | SM 280 Culvert Rehab | Near Redwood City, San Carlos and Belmont, from Edgewood Road to Route 92 and near Hillsborough at PM R12.7; also in Santa Clara County in and near Mountain View and Palo Alto, at various spot locations (PM 11.6, 12.8, 12.9, 18.8). | Replace failing culverts and restore damaged slopes, pavement, and bridge approaches at six locations. | 1800 | Yes | 1800 | 1798 | 1798 | 1798 | No | 2303 | Yes | 2303 | 2063 | 2063 | 2283 | No | 260 | Yes | 260 | 17 | 17 | 258 | No | 3000 | Yes | 3000 | 0 | 0 | 2992 | No | 50 | No | 50 | 8 | 8 | 50 | No | 0 | Yes | 0 | 0 | 0 | 21181 | Yes | 7413 | 7413 | 3886 | 3886 | 28562 |  | 2020-02-01 | 2020-04-14 |  |  | 2021-10-01 | 2022-03-25 |  |  | 2021-11-01 | 2022-04-08 |  |  | 2022-05-01 |  | 2022-11-04 | Yes |  |  | 2024-09-06 |  | 0 | Yes | Yes | No | No
186 | 04 | 0756K | MRN | 1 | Lagunitas Creek Bridge | Near Point Reyes Station, at Lagunitas Creek Bridge No 27-0023. | Replace bridge. | 5547 | Yes | 5547 | 4130 | 4130 | 4130 | No | 4545 | Yes | 4545 | 3001 | 3001 | 4058 | No | 750 | Yes | 750 | 314 | 314 | 1022 | Yes | 2625 | No | 2625 | 0 | 0 | 2959 | Yes | 6500 | No | 6500 | 8 | 8 | 4059 | No | 15580 | No | 15580 | 0 | 0 | 11552 | No | 35547 | 35547 | 7453 | 7453 | 27780 | 2018-10-17 | 2018-06-29 | 2018-06-29 |  |  | 2020-08-20 |  | 2023-05-15 | Yes | 2020-08-25 |  | 2023-06-16 | Yes | 2021-02-08 |  | 2024-01-18 | Yes |  |  | 2025-12-19 |  | 0 | Yes | No | No | No
187 | 04 | 0781P | SON | 101 | BRIDGE DECK PROGRAM | In and near Sonoma, Geyserville, Healdsburg, and Cloverdale, on Routes 12, 101, and 128 at various locations. | Apply polyester concrete overlay to bridge decks. (Bridge Deck Preservation). | 65 | Yes | 65 | 65 | 65 | 65 | No | 812 | Yes | 812 | 391 | 391 | 858 | Yes | 32 | Yes | 32 | 2 | 2 | 34 | Yes | 1384 | No | 1384 | 0 | 0 | 1460 | Yes | 0 | No | 0 | 0 | 0 | 0 | No | 5290 | No | 5290 | 0 | 0 | 5291 | Yes | 7583 | 7583 | 458 | 458 | 7708 |  |  | 2022-06-29 |  |  |  | 2022-06-30 |  |  |  | 2022-06-30 |  |  |  |  | 2022-09-23 |  |  |  | 2023-09-22 |  | 0 | Yes | No | No | Yes
188 | 04 | 0830B | NAP | 128 | Capell Creek Bridge Replacement | IN NAPA COUNTY, NEAR CITY OF NAPA AT CAPELL CREEK BRIDGE (BRIDGE NO. 21-0078). | REHABILITATE BRIDGE. | 1560 | No | 1560 | 1540 | 1540 | 1540 | No | 2510 | Yes | 2510 | 2507 | 2507 | 2507 | No | 437 | Yes | 437 | 379 | 379 | 450 | Yes | 6837 | Yes | 6837 | 6662 | 6662 | 7150 | Yes | 0 | No | 0 | 64 | 64 | 230 | Yes | 15793 | Yes | 15793 | 14661 | 14661 | 15793 | No | 27137 | 27137 | 25813 | 25813 | 27670 |  |  | 2016-06-16 |  |  |  | 2018-06-28 |  |  |  | 2018-06-29 |  |  |  | 2019-03-13 |  |  |  |  | 2023-03-31 |  | 14538 | Yes | Yes | Yes | Yes
189 | 04 | 1450C | ALA | 880 | Bridge Railings Replacement | In Hayward, San Leandro, and Oakland, at Tennyson Road Overcrossing (OC) No 33-0236 (PM 15.65), Washington Avenue OC No 33-0166 (PM 20.82), and Damon Slough southbound onramp No 33-0142K (PM 26.53); also on Route 77 in Oakland, at San Leandro OC No 33-0284 (PM 0.29). | Upgrade bridge rails, replace joint seals. | 935 | Yes | 935 | 934 | 934 | 934 | No | 2029 | Yes | 2029 | 1736 | 1736 | 2030 | Yes | 250 | Yes | 250 | 63 | 63 | 244 | No | 2200 | No | 2200 | 0 | 0 | 2406 | Yes | 25 | No | 25 | 6 | 6 | 20 | No | 10300 | No | 10300 | 0 | 0 | 10300 | No | 15739 | 15739 | 2739 | 2739 | 15934 |  | 2020-05-15 | 2020-05-22 |  |  | 2021-12-17 | 2022-06-27 |  |  | 2022-01-21 | 2022-06-28 |  |  | 2022-09-26 |  | 2023-01-23 | Yes |  |  | 2024-10-31 |  | 0 | No | No | No | No
190 | 04 | 1450E | SF | 101 | SF-101 & SM-1 Baluster Rails | In the City and County of San Francisco, from Alemany Boulevard onramp to Potrero Avenue onramp at Alemany Circle Undercrossing (UC) No 34-0064K, Alemany Circle UC No 34-0063S and Bayshore Boulevard UC No 34-0047S; also in San Mateo County on Route 1 in Pacifica, at Paloma Avenue Overcrossing No 35-0187 (PM R44.21). | Upgrade bridge rails. | 837 | Yes | 837 | 831 | 831 | 831 | No | 1931 | Yes | 1931 | 1853 | 1853 | 1853 | No | 164 | Yes | 164 | 18 | 18 | 141 | No | 1805 | Yes | 1805 | 147 | 147 | 1982 | Yes | 20 | No | 20 | 10 | 10 | 20 | No | 7118 | Yes | 7118 | 653 | 653 | 7118 | No | 11875 | 11875 | 3512 | 3512 | 11945 |  | 2020-05-01 | 2020-06-30 |  |  | 2021-01-01 | 2021-06-14 |  |  | 2021-03-01 | 2021-06-22 |  |  | 2021-10-01 | 2022-03-01 |  |  |  |  | 2023-05-16 |  | 7118 | No | No | No | No
191 | 04 | 1451A | SON | 101 | Replace Bridge Rails | In and near Santa Rosa, at Todd Road Overcrossing (OC) No 20-0172 (PM 16.54) and Baker Avenue OC No 20-0173 (PM 19.00); also in Marin County near Navato, at Miller Creek Road OC No 27-0082 (PM 15.57). | Upgrade bridge rails. | 650 | Yes | 650 | 612 | 612 | 612 | No | 900 | Yes | 900 | 899 | 899 | 899 | No | 130 | Yes | 130 | 31 | 31 | 132 | Yes | 1090 | Yes | 1090 | 0 | 0 | 1190 | Yes | 116 | No | 116 | 8 | 8 | 120 | Yes | 3808 | Yes | 3808 | 0 | 0 | 3808 | No | 6694 | 6694 | 1550 | 1550 | 6761 |  | 2019-10-01 | 2019-09-24 |  |  | 2021-08-02 | 2021-09-01 |  |  | 2021-09-01 | 2021-09-01 |  |  | 2022-03-01 | 2022-06-13 |  |  |  |  | 2023-03-01 |  | 3808 | No | No | No | No
192 | 04 | 1451C | NAP | 128 | Hopper Slough Bridge Replac | Near Rutherford, at Hopper Slough Bridge No 21-0019. | Replace bridge. | 3800 | Yes | 3800 | 3115 | 3115 | 3115 | No | 1988 | No | 1988 | 0 | 0 | 2147 | Yes | 206 | No | 206 | 0 | 0 | 220 | Yes | 3900 | No | 3900 | 0 | 0 | 3981 | Yes | 1514 | No | 1514 | 4 | 4 | 370 | No | 12200 | No | 12200 | 0 | 0 | 7864 | No | 23608 | 23608 | 3119 | 3119 | 17697 |  | 2022-06-10 | 2022-06-29 |  |  | 2024-04-19 |  | 2024-04-19 | No | 2024-05-03 |  | 2024-05-03 | No | 2025-01-31 |  | 2025-01-31 | No |  |  | 2026-12-31 |  | 0 | No | No | No | No
193 | 04 | 1452A | SM | 1 | SM-1 TOS | In and near the cities of Half Moon Bay, Pacifica and Daly City, from south of Miramontes Point Road to Clarinada Avenue Undercrossing, at various locations. | Install Bluetooth Detection Systems and Variable Message Signs (VMS), enable two existing Changeable Message Signs (CMS), modify Advanced Transportation Management System (ATMS), and construct Maintenance Vehicle Pullouts (MVPs) to improve the system performance. | 1073 | Yes | 1073 | 1059 | 1059 | 1059 | No | 781 | Yes | 781 | 683 | 683 | 770 | No | 30 | Yes | 30 | 17 | 17 | 31 | Yes | 444 | No | 444 | 0 | 0 | 418 | No | 36 | No | 36 | 27 | 27 | 36 | No | 2408 | No | 2408 | 0 | 0 | 2408 | No | 4772 | 4772 | 1786 | 1786 | 4722 |  | 2020-09-01 | 2021-05-10 |  |  | 2021-08-01 | 2022-06-27 |  |  | 2021-09-01 |  | 2022-10-31 | Yes | 2022-01-15 |  | 2023-01-13 | Yes |  |  | 2024-01-15 |  | 0 | Yes | No | No | No
194 | 04 | 1452B | MRN | 37 | MRN-37 11.2/14.6 CAPM | In and near Novato, from Route 101 to Sonoma County line. | Rehabilitate pavement, upgrade guardrail, and upgrade facilities to Americans with Disabilities Act (ADA) standards. | 2509 | Yes | 2509 | 919 | 919 | 2729 | Yes | 2405 | No | 2405 | 0 | 0 | 2611 | Yes | 350 | No | 350 | 0 | 0 | 354 | Yes | 1600 | No | 1600 | 0 | 0 | 1876 | Yes | 1038 | No | 1038 | 0 | 0 | 1031 | No | 18936 | No | 18936 | 0 | 0 | 15236 | No | 26838 | 26838 | 919 | 919 | 23837 |  | 2022-08-12 |  | 2022-08-12 | No | 2024-04-12 |  | 2024-04-12 | No | 2024-05-17 |  | 2024-05-17 | No | 2025-02-10 |  | 2025-02-10 | No |  |  | 2026-04-10 |  | 0 | No | Yes | No | No
195 | 04 | 1452F | SOL | 80 | Sol-80/29 Separation | In Vallejo, at Route 80/29 Separation Bridge No 23-0087. | Replace bridge. ACCELERATED BRIDGE. | 2057 | Yes | 2057 | 2032 | 2032 | 2032 | No | 2624 | Yes | 2624 | 2583 | 2583 | 2583 | No | 40 | Yes | 40 | 26 | 26 | 26 | No | 4300 | Yes | 4300 | 2671 | 2671 | 4357 | Yes | 15 | No | 15 | 0 | 0 | 0 | No | 19986 | Yes | 19986 | 7193 | 7193 | 19986 | No | 29022 | 29022 | 14505 | 14505 | 28984 |  | 2018-12-03 | 2018-06-21 |  |  | 2020-05-04 | 2020-05-01 |  |  | 2020-06-08 | 2020-06-19 |  |  | 2021-01-15 | 2021-04-22 |  |  |  |  | 2023-12-16 |  | 19986 | No | No | No | No
196 | 04 | 1452J | ALA | 61 | ALA-61 CAPM | In the city of Alameda, from Broadway/Encinal Avenue to Sherman Street. | Pavement rehabilitation, upgrade Americans with Disabilities Act (ADA) curb ramps, and improve crosswalks. | 1404 | Yes | 1404 | 1372 | 1372 | 1372 | No | 1420 | Yes | 1420 | 1412 | 1412 | 1412 | No | 50 | Yes | 50 | 36 | 36 | 50 | No | 1785 | Yes | 1785 | 228 | 228 | 1746 | No | 200 | No | 200 | 18 | 18 | 200 | No | 5989 | Yes | 5989 | 0 | 0 | 5989 | No | 10848 | 10848 | 3066 | 3066 | 10769 |  | 2020-06-01 | 2020-06-30 |  |  | 2021-05-15 | 2021-09-24 |  |  | 2021-06-01 | 2021-09-24 |  |  | 2021-11-01 | 2022-04-01 |  |  |  |  | 2023-07-03 |  | 5989 | No | No | No | No
197 | 04 | 1453C | SON | 1 | Rehabilitate Culvert | Near Bodega Bay, Carmet, and Jenner, from 0.7 mile south of Middle Road to 2.3 miles north of Meyers Grade Road at various locations. | Rehabilitate drainage systems. | 794 | Yes | 794 | 546 | 546 | 1008 | Yes | 718 | No | 718 | 0 | 0 | 718 | No | 58 | No | 58 | 0 | 0 | 60 | Yes | 687 | No | 687 | 0 | 0 | 673 | No | 655 | No | 655 | 0 | 0 | 5 | No | 3569 | No | 3569 | 0 | 0 | 2870 | No | 6481 | 6481 | 546 | 546 | 5334 |  | 2022-10-01 |  | 2023-01-18 | Yes | 2024-02-01 |  | 2024-02-01 | No | 2024-04-01 |  | 2024-04-01 | No | 2024-10-01 |  | 2024-10-01 | No |  |  | 2026-12-31 |  | 0 | No | No | No | No
198 | 04 | 1453J | SON | 1 | Son 1 Culverts Rehab | Near Jenner, from south of Fort Ross Road to north of Moon Rock Campground at various locations. | Rehabilitate drainage culverts. | 1018 | Yes | 1018 | 1008 | 1008 |  | No | 1369 | Yes | 1369 | 1354 | 1354 | 1478 | Yes | 429 | Yes | 429 | 151 | 151 | 539 | Yes | 1385 | No | 1385 | 0 | 0 | 1299 | No | 595 | No | 595 | 50 | 50 | 595 | No | 4256 | No | 4256 | 0 | 0 | 4256 | No | 9052 | 9052 | 2563 | 2563 | 9175 |  | 2019-12-29 | 2020-05-08 |  |  | 2022-05-15 |  | 2022-09-30 | Yes | 2022-06-01 |  | 2022-10-14 | Yes | 2023-01-01 |  | 2023-04-13 | Yes |  |  | 2024-07-31 |  | 0 | Yes | No | No | No
199 | 04 | 1453K | NAP | 29 | SHEEHY CRK CULVERT REHAB | In American Canyon, at Rio Del Mar; also near American Canyon at 0.3 mile south of North Kelly Road (PM 5.1). | Rehabilitate culverts. | 1086 | Yes | 1086 | 1079 | 1079 | 1079 | No | 1064 | Yes | 1064 | 732 | 732 | 932 | No | 350 | Yes | 350 | 189 | 189 | 360 | Yes | 706 | No | 706 | 0 | 0 | 700 | No | 294 | No | 294 | 36 | 36 | 402 | Yes | 3336 | No | 3336 | 0 | 0 | 3336 | No | 6836 | 6836 | 2036 | 2036 | 6809 |  | 2019-11-04 | 2020-02-04 |  |  | 2021-07-01 |  | 2022-09-01 | Yes | 2021-08-02 |  | 2022-09-23 | Yes | 2022-01-11 |  | 2023-05-15 | Yes |  |  | 2025-11-30 |  | 0 | Yes | No | No | Yes
200 | 04 | 1454G | ALA | 880 | CAPM ALA-880-0.0/12.0 | In Fremont, from Santa Clara County line to north of Fremont Boulevard Overcrossing. | Cold plane pavement, overlay with Rubberized Hot Mix Asphalt (RHMA-G) and Open Graded Friction Course (OGFC), upgrade Americans with Disabilities Act (ADA) curb ramps, upgrade metal beam guardrail, and replace loop detectors. (G13 Contingency). | 3000 | Yes | 3000 | 2999 | 2999 | 2999 | No | 7050 | Yes | 7050 | 6906 | 6906 | 7168 | Yes | 620 | Yes | 620 | 135 | 135 | 595 | No | 0 | No | 0 | 0 | 0 | 6394 | Yes | 185 | No | 185 | 12 | 12 | 185 | No | 0 | No | 0 | 0 | 0 | 70622 | Yes | 10855 | 10855 | 10052 | 10052 | 87963 | 2020-06-24 | 2020-03-02 | 2020-03-02 |  |  | 2021-11-01 | 2022-06-27 |  |  | 2022-03-01 | 2022-06-27 |  |  | 2023-03-01 |  | 2023-03-01 | No |  |  | 2024-12-31 |  | 0 | Yes | Yes | Yes | Yes
201 | 04 | 1457C | ALA | Var | CCTV Technology Replacement | In various counties, on various routes at various locations. | Replace obsolete electronic components in existing Closed Circuit Television (CCTV) camera systems. | 360 | Yes | 360 | 247 | 247 | 436 | Yes | 1075 | Yes | 1075 | 0 | 0 | 1020 | No | 15 | Yes | 15 | 0 | 0 | 14 | No | 2700 | No | 2700 | 0 | 0 | 2587 | No | 15 | No | 15 | 0 | 0 | 10 | No | 15960 | No | 15960 | 0 | 0 | 15946 | No | 20125 | 20125 | 247 | 247 | 20013 |  | 2021-12-31 |  | 2022-04-30 | Yes | 2022-09-01 |  | 2022-09-01 | No | 2022-10-01 |  | 2022-10-01 | No | 2023-06-15 |  | 2023-06-15 | No |  |  | 2026-06-14 |  | 0 | No | No | No | No
202 | 04 | 1462M | SON | 1 | Son 1 Culverts Rehab | Near Gualala, from 1.7 miles south of Kruse Ranch Road to 0.1 mile north of Vantage Road. | Rehabilitate drainage culverts. | 1355 | Yes | 1355 | 1353 | 1353 | 1353 | No | 1850 | Yes | 1850 | 1242 | 1242 | 1952 | Yes | 340 | Yes | 340 | 142 | 142 | 361 | Yes | 1545 | No | 1545 | 0 | 0 | 1119 | No | 175 | No | 175 | 66 | 66 | 175 | No | 5619 | No | 5619 | 0 | 0 | 4761 | No | 10884 | 10884 | 2803 | 2803 | 9721 |  | 2020-10-15 | 2020-10-15 |  |  | 2022-06-15 |  | 2022-09-30 | Yes | 2022-06-15 |  | 2022-10-14 | Yes | 2023-01-16 |  | 2023-04-13 | No |  |  | 2024-07-31 |  | 0 | Yes | No | No | No
203 | 04 | 1462N | SON | 1 | Son 1 Culverts Rehab | Near Sea Ranch, at 2.7 miles south of Skaggs Springs Road. | Rehabilitate damaged culvert. | 767 | Yes | 767 | 187 | 187 | 773 | Yes | 596 | No | 596 | 0 | 0 | 1162 | Yes | 315 | No | 315 | 0 | 0 | 94 | No | 309 | No | 309 | 0 | 0 | 410 | Yes | 165 | No | 165 | 0 | 0 | 125 | No | 995 | No | 995 | 0 | 0 | 750 | No | 3147 | 3147 | 187 | 187 | 3314 |  | 2023-01-30 |  | 2023-01-30 | No | 2024-06-07 |  | 2024-06-07 | No | 2024-06-21 |  | 2024-06-21 | No | 2025-01-17 |  | 2025-01-17 | No |  |  | 2025-10-31 |  | 0 | No | Yes | No | No
204 | 04 | 1462R | CC | 4 | CC-4 CAPM | In and near Concord and Pittsburg, from Route 242 to Loveridge Road. | Rehabilitate pavement, upgrade curb ramps to make Americans with Disabilities Act (ADA) compliant and upgrade guardrail to make standaRd (G13 Contingency). | 2720 | Yes | 2720 | 2592 | 2592 | 2592 | No | 6400 | Yes | 6400 | 4148 | 4148 | 6554 | Yes | 780 | Yes | 780 | 73 | 73 | 672 | No | 0 | No | 0 | 0 | 0 | 8001 | Yes | 93 | No | 93 | 13 | 13 | 40 | No | 0 | No | 0 | 0 | 0 | 62318 | Yes | 9993 | 9993 | 6826 | 6826 | 80177 | 2020-10-22 | 2020-06-16 | 2020-06-16 |  |  | 2022-05-02 | 2022-06-30 |  |  | 2022-06-01 | 2022-06-30 |  |  | 2023-01-20 |  | 2023-03-01 | No |  |  | 2025-03-05 |  | 0 | No | Yes | No | No
205 | 04 | 1464L | ALA | 980 | TMC Hardware Replacement | In Oakland, at the District 4 Transportation Management Center (TMC) at 111 Grand Avenue. | Upgrade or replace legacy TMC hardware components and related software by service contract to improve reliability and functionality. | 110 | Yes | 110 | 96 | 96 | 96 | No | 392 | Yes | 392 | 389 | 389 | 389 | No | 10 | No | 10 | 0 | 0 | 6 | No | 262 | Yes | 262 | 0 | 0 | 406 | Yes | 10 | No | 10 | 0 | 0 | 0 | No | 2570 | Yes | 2570 | 709 | 709 | 2570 | No | 3354 | 3354 | 1194 | 1194 | 3467 |  | 2018-10-01 | 2018-10-01 |  |  | 2019-09-01 | 2019-10-31 |  |  | 2019-12-01 | 2019-11-27 |  |  | 2020-11-01 | 2021-07-23 |  |  |  |  | 2023-07-07 |  | 1407 | No | No | No | No
206 | 04 | 1480A | MRN | 1 | MRN 1 CAPM | Near Point Reyes Station and Olema, from Olema Creek Bridge to north of Cypress Road; also near Tomales, from south of Tomales-Petaluma Road to south of Valley Ford Road (PM 45.0/50.5). | Pavement rehabilitation, improve drainage, and upgrade Americans with Disabilities Act (ADA) facilities. (G13 Contingency). | 2570 | Yes | 2570 | 2521 | 2521 | 2521 | No | 2850 | Yes | 2850 | 2731 | 2731 | 3446 | Yes | 418 | Yes | 418 | 416 | 416 | 553 | Yes | 0 | No | 0 | 0 | 0 | 2280 | Yes | 817 | No | 817 | 25 | 25 | 708 | No | 0 | No | 0 | 0 | 0 | 24523 | Yes | 6655 | 6655 | 5693 | 5693 | 34031 |  | 2020-08-14 | 2020-08-25 |  |  | 2022-04-15 |  | 2023-06-05 | Yes | 2022-04-29 |  | 2023-06-16 | Yes | 2022-10-31 |  | 2024-02-09 | Yes |  |  | 2026-04-10 |  | 0 | Yes | Yes | No | No
207 | 04 | 1480B | SCL | 17 | SCL 17 CAPM | In and near Los Gatos, Campbell and San Jose, from Hebard Way to Route 280. | Pavement rehabilitation. | 2400 | Yes | 2400 | 2372 | 2372 | 2372 | No | 3225 | Yes | 3225 | 3219 | 3219 | 3219 | No | 175 | Yes | 175 | 147 | 147 | 149 | No | 5900 | Yes | 5900 | 2759 | 2759 | 5905 | Yes | 56 | No | 56 | 33 | 33 | 53 | No | 52834 | Yes | 52834 | 15801 | 15801 | 52834 | No | 64590 | 64590 | 24331 | 24331 | 64532 | 2019-03-14 | 2018-10-10 | 2018-10-10 |  |  | 2020-01-17 | 2020-06-29 |  |  | 2020-01-27 | 2020-06-30 |  |  | 2020-07-15 | 2021-05-19 |  |  |  |  | 2023-10-09 |  | 52833 | No | No | No | No
208 | 04 | 1482F | SON | 101 | BIG PAVE SEGMENT 2 | In and near Windsor, Healdsburg, and Cloverdale, from Old Redwood Highway to 2.0 miles south of Mendocino County line. | Roadway rehabilitation. | 5149 | Yes | 5149 | 3791 | 3791 | 3791 | No | 6799 | Yes | 6799 | 5789 | 5789 | 5789 | No | 320 | Yes | 320 | 256 | 256 | 282 | No | 8968 | Yes | 8968 | 8881 | 8881 | 9660 | Yes | 890 | No | 890 | 126 | 126 | 868 | No | 67890 | Yes | 67890 | 56501 | 56501 | 67890 | No | 90016 | 90016 | 75344 | 75344 | 88280 | 2018-10-17 | 2018-04-19 | 2018-04-19 |  |  | 2019-06-03 | 2019-06-21 |  |  | 2019-06-03 | 2019-06-28 |  |  | 2019-12-01 | 2020-01-14 |  |  |  |  | 2023-06-30 |  | 67890 | No | No | No | No
209 | 04 | 1482Q | CC | 580 | CC-580 Stege Drain super-structure | In Richmond, at Stege Drain Bridge No 28-0091. | Bridge rehabilitation. | 970 | Yes | 970 | 945 | 945 | 945 | No | 1346 | Yes | 1346 | 1288 | 1288 | 1288 | No | 117 | Yes | 117 | 95 | 95 | 124 | Yes | 2800 | Yes | 2800 | 1749 | 1749 | 2706 | No | 5 | No | 5 | 2 | 2 | 2 | No | 10286 | Yes | 10286 | 4434 | 4434 | 10286 | No | 15524 | 15524 | 8513 | 8513 | 15351 |  | 2018-11-30 | 2019-03-22 |  |  | 2019-08-01 | 2020-06-30 |  |  | 2020-04-20 | 2020-06-30 |  |  | 2020-10-12 | 2021-03-11 |  |  |  |  | 2024-04-12 |  | 10286 | No | No | No | No
210 | 04 | 1482R | SCL | Var | SCL, VAR, Sub-Structure Rehab. | In various cities, on Routes 25, 82, 85, and 152 at Carnadero Creek Bridge No 37-0156, San Francisquito Creek Bridge No 37-0018, San Tomas Aquino Creek Bridge No 37-0524L, and Bodfish Creek Bridge No 37-0046. | Bridge preventative maintenance. | 900 | Yes | 900 | 879 | 879 | 879 | No | 1325 | Yes | 1325 | 1170 | 1170 | 1170 | No | 44 | Yes | 44 | 27 | 27 | 83 | Yes | 940 | Yes | 940 | 155 | 155 | 1158 | Yes | 10 | No | 10 | 108 | 108 | 112 | Yes | 3418 | Yes | 3418 | 54 | 54 | 3418 | No | 6637 | 6637 | 2393 | 2393 | 6820 |  | 2018-10-01 | 2019-03-01 |  |  | 2020-05-01 | 2021-05-04 |  |  | 2020-06-01 | 2021-05-19 |  |  | 2020-12-22 | 2022-01-11 |  |  |  |  | 2023-12-15 |  | 3418 | No | No | No | Yes
211 | 04 | 1482S | SCL | 237 | BRIDGE DECK PROGRAM | In Mountain View, Sunnyvale, and Milpitas, at Stevens Creek Bridge No 37-0200F (PM R0.35), North Mathilda Avenue Undercrossing No 37-0179 (PM 2.99), Fair Oaks Avenue Overcrossing No 37-0248 (PM R3.98), and Coyote Creek Bridge No 37-0084L (PM 8.72). | Apply polyester concrete overlay to bridge decks. (Bridge Deck Preservation). | 41 | Yes | 41 | 40 | 40 | 40 | No | 890 | Yes | 630 | 403 | 403 | 873 | No | 20 | Yes | 20 | 2 | 2 | 2 | No | 1020 | No | 1020 | 0 | 0 | 1031 | Yes | 0 | No | 0 | 0 | 0 | 0 | No | 3310 | No | 3310 | 0 | 0 | 3310 | No | 5281 | 5021 | 445 | 445 | 5256 |  |  | 2022-06-30 |  |  |  | 2021-11-30 |  |  |  | 2022-06-30 |  |  |  |  | 2022-09-23 |  |  |  | 2023-09-23 |  | 0 | No | No | No | Yes
212 | 04 | 1483C | SM | 101 | SM 101 Cordilleras Crk Br Replacement | In Redwood City, from 0.4 mile south to 0.5 mile north of Cordilleras Creek Bridge No 35-0019. | Replace bridge to restore structural integrity. (Additional $1,300,000 contribution for Const Cap from Local Measure A funds.) (G13 Contingency). | 4500 | Yes | 4500 | 3737 | 3737 | 3737 | No | 5175 | Yes | 5175 | 2517 | 2517 | 5098 | No | 1125 | Yes | 1125 | 37 | 37 | 542 | No | 0 | No | 0 | 0 | 0 | 7155 | Yes | 4285 | No | 4285 | 37 | 37 | 5114 | Yes | 0 | No | 0 | 0 | 0 | 32596 | Yes | 15085 | 15085 | 6328 | 6328 | 54242 | 2021-06-23 | 2021-05-07 | 2021-05-07 |  |  | 2022-05-13 |  | 2022-08-01 | Yes | 2022-06-20 |  | 2022-08-08 | Yes | 2023-05-16 |  | 2023-02-15 | No |  |  | 2024-06-15 |  | 0 | Yes | Yes | No | No
213 | 04 | 1483D | ALA | 880 | East Crk Slough Scour Mitigation | In Oakland, at East Creek Slough Bridge No 33-0143. | Mitigate eroded channel side-slope tidal scour and replace bridge approach slabs. | 1200 | Yes | 1200 | 1156 | 1156 | 1156 | No | 1867 | Yes | 1867 | 1620 | 1620 | 1929 | Yes | 160 | Yes | 160 | 110 | 110 | 162 | Yes | 2396 | No | 2396 | 0 | 0 | 2353 | No | 300 | No | 300 | 15 | 15 | 300 | No | 4395 | No | 4395 | 0 | 0 | 4395 | No | 10318 | 10318 | 2901 | 2901 | 10295 |  | 2020-10-01 | 2020-10-09 |  |  | 2022-05-14 |  | 2022-07-21 | Yes | 2022-06-01 |  | 2022-07-26 | Yes | 2023-01-15 |  | 2023-03-02 | No |  |  | 2024-01-15 |  | 0 | Yes | No | No | No
214 | 04 | 1483E | NAP | 29 | SR 29 3 bridges, scour measures | Near Calistoga, at Garnett Creek Bridge No 21-0005 (PM 39.08), Garnet Creek Branch Bridge No 21-0111 (PM 38.96), and No Name Creek Bridge No 21-0100 (PM 42.83). | Bridge preventative maintenance and scour mitigation. | 2867 | Yes | 2867 | 2875 | 2875 | 2875 | Yes | 4518 | Yes | 4518 | 2875 | 2875 | 4066 | No | 566 | Yes | 566 | 421 | 421 | 530 | No | 1950 | No | 1950 | 0 | 0 | 2466 | Yes | 2166 | No | 2166 | 21 | 21 | 2166 | No | 5266 | No | 5266 | 0 | 0 | 3944 | No | 17333 | 17333 | 6192 | 6192 | 16047 |  | 2019-02-01 | 2019-02-01 |  |  | 2020-11-01 |  | 2022-11-15 | Yes | 2020-12-15 |  | 2022-12-01 | Yes | 2021-06-15 |  | 2023-04-17 | Yes |  |  | 2024-02-29 |  | 0 | Yes | Yes | Yes | Yes
215 | 04 | 1483H | ALA | 80 | TMS Replace & Upgrade at Maze | In Emeryville and Oakland, from San Francisco-Oakland Bay Bridge Toll Plaza to north of Powell Street; also in Oakland, on Routes 580 and 880, at various locations. | Upgrade/replace Transportation Management System (TMS) elements. | 760 | Yes | 760 | 543 | 543 | 543 | No | 1100 | Yes | 1100 | 1099 | 1099 | 1099 | No | 260 | Yes | 260 | 199 | 199 | 1731 | Yes | 1044 | Yes | 1044 | 926 | 926 | 1815 | Yes | 12 | No | 12 | 6 | 6 | 12 | No | 3153 | Yes | 3153 | 2604 | 2604 | 3153 | No | 6329 | 6329 | 5377 | 5377 | 8353 |  | 2019-03-01 | 2018-10-24 |  |  | 2020-04-01 | 2020-04-21 |  |  | 2020-05-01 | 2020-04-30 |  |  | 2020-12-24 | 2021-02-02 |  |  |  |  | 2022-07-22 |  | 3153 | Yes | Yes | Yes | Yes
216 | 04 | 1483M | SM | 1 | SM-1/84, Pillarcitos/S.Gregorio RSP | In Half Moon Bay, at the Pilarcitos Creek Bridge No 35-0139L/R; also on Route 84 at San Gregorio Creek Bridge No 35-0166 (PM 7.55). | Retrofit scour critical bridges to preserve the structural integrity of the bridges by reinforcing with Rock Slope Protection (RSP). | 1575 | Yes | 1575 | 1395 | 1395 | 1395 | No | 1237 | Yes | 1237 | 1047 | 1047 | 2244 | Yes | 309 | Yes | 309 | 5 | 5 | 348 | Yes | 1752 | No | 1752 | 0 | 0 | 1663 | No | 343 | No | 343 | 2 | 2 | 424 | Yes | 6177 | No | 6177 | 0 | 0 | 5214 | No | 11393 | 11393 | 2449 | 2449 | 11288 |  | 2021-04-30 | 2021-04-30 |  |  | 2022-09-16 |  | 2022-09-16 | No | 2022-10-03 |  | 2023-02-15 | Yes | 2023-05-01 |  | 2023-06-01 | No |  |  | 2024-05-01 |  | 0 | Yes | Yes | No | Yes
217 | 04 | 1483S | SF | 80 | Bayshore Viaduct Structure Painting | In the City and County of San Francisco, on Route 80, at the Bayshore Viaduct No 34-0088 from Route 101 to 4th Street (PM 3.836/4.992). | Paint superstructure steel members. | 2500 | Yes | 2500 | 1944 | 1944 | 1944 | No | 9200 | Yes | 9200 | 4676 | 4676 | 4676 | No | 300 | Yes | 300 | 69 | 69 | 69 | No | 7500 | Yes | 7500 | 1673 | 1673 | 8693 | Yes | 76 | No | 76 | 0 | 0 | 76 | No | 24226 | Yes | 24226 | 7074 | 7074 | 24226 | No | 43802 | 43802 | 15436 | 15436 | 39684 | 2018-12-06 | 2018-12-01 |  |  |  | 2020-03-01 |  |  |  | 2020-04-01 |  |  |  | 2020-12-15 | 2021-06-04 |  |  |  |  | 2025-10-01 |  | 24225 | No | Yes | No | No
218 | 04 | 1483T | SF | 101 | Central Viaduct Structure Painting | In the City and County of San Francisco, at the Central Viaduct No 34-0077 from south of 17th Street to S Van Ness Avenue. | Paint superstructure steel members. | 0 | No | 0 | 0 | 0 | 0 | No | 0 | No | 0 | 0 | 0 | 0 | No | 0 | No | 0 | 0 | 0 | 0 | No | 7500 | Yes | 7500 | 1711 | 1711 | 7838 | Yes | 153 | No | 153 | 0 | 0 | 153 | No | 30993 | Yes | 30993 | 10666 | 10666 | 30993 | No | 38646 | 38646 | 12377 | 12377 | 38984 | [14 empty] | 2021-04-16 |  |  |  |  | 2025-06-01 |  | 30993 | No | No | No | No
219 | 04 | 1485E | MRN | 1 | Rehabilitate Culvert | Near Marshall, at 0.1 mile south of Clark Road. | Replace culvert. | 1250 | Yes | 1250 | 549 | 549 | 1545 | Yes | 1360 | No | 1360 | 0 | 0 | 1482 | Yes | 300 | No | 300 | 0 | 0 | 291 | No | 1400 | No | 1400 | 0 | 0 | 1438 | Yes | 176 | No | 176 | 0 | 0 | 211 | Yes | 2307 | No | 2307 | 0 | 0 | 2307 | No | 6793 | 6793 | 549 | 549 | 7274 |  | 2022-08-26 |  | 2022-12-14 | Yes | 2024-03-07 |  | 2024-03-07 | No | 2024-04-12 |  | 2024-04-12 | No | 2024-12-04 |  | 2024-12-04 | No |  |  | 2027-02-16 |  | 0 | Yes | Yes | No | No
220 | 04 | 1485K | SM | 101 | Bridge Rail Replacement | In East Palo Alto, Redwood City, San Mateo, Millbrae, and South San Francisco, from University Avenue Overcrossing to Sierra Point offramp separation. | Upgrade bridge rails at seven structures. | 1326 | Yes | 1326 | 1316 | 1316 | 1316 | No | 2243 | Yes | 2243 | 2213 | 2213 | 2450 | Yes | 130 | Yes | 130 | 29 | 29 | 110 | No | 1456 | No | 1456 | 0 | 0 | 1686 | Yes | 64 | No | 64 | 12 | 12 | 35 | No | 11519 | No | 11519 | 0 | 0 | 11519 | No | 16738 | 16738 | 3570 | 3570 | 17116 |  | 2020-08-01 | 2020-08-03 |  |  | 2021-12-01 | 2022-06-23 |  |  | 2022-03-01 | 2022-06-23 |  |  | 2022-09-01 |  | 2022-12-05 | Yes |  |  | 2024-04-01 |  | 0 | No | No | No | No
221 | 04 | 1487A | ALA | 580 | TMS on ALA-580 | In and near Oakland and San Leandro, from Route 238 to Route 80 (PM R30.8/46.5L/R). | Install and upgrade Transportation Management System (TMS) elements. | 2700 | Yes | 2700 | 1004 | 1004 | 1004 | No | 2700 | Yes | 2700 | 2689 | 2689 | 2689 | No | 50 | Yes | 50 | 16 | 16 | 55 | Yes | 3600 | Yes | 3600 | 2627 | 2627 | 3636 | Yes | 20 | No | 20 | 0 | 0 | 20 | No | 9832 | Yes | 9832 | 6015 | 6015 | 9832 | No | 18902 | 18902 | 12351 | 12351 | 17236 | 2018-10-17 | 2018-06-19 | 2018-06-19 |  |  | 2020-04-16 | 2020-06-29 |  |  | 2020-06-15 | 2020-06-29 |  |  | 2020-12-31 | 2021-04-16 |  |  |  |  | 2022-10-03 |  | 9831 | Yes | Yes | Yes | Yes
222 | 04 | 1487D | SON | 101 | San Antonio Creek | Near Petaluma, at San Antonio Creek Bridge No 20-0019Y. | Abutment scour mitigation and channel sediment cleaning to address flooding. | 1232 | Yes | 1232 | 1229 | 1229 | 1229 | No | 716 | Yes | 716 | 696 | 696 | 960 | Yes | 24 | Yes | 24 | 27 | 27 | 175 | Yes | 750 | No | 750 | 0 | 0 | 1020 | Yes | 160 | No | 160 | 20 | 20 | 191 | Yes | 2400 | No | 2400 | 0 | 0 | 996 | No | 5282 | 5282 | 1972 | 1972 | 4571 |  | 2020-10-01 | 2021-06-28 |  |  | 2021-12-01 | 2022-06-30 |  |  | 2021-12-01 | 2022-06-30 |  |  | 2022-06-01 |  | 2023-02-01 | Yes |  |  | 2025-12-31 |  | 0 | Yes | No | No | No
223 | 04 | 1487E | CC | 80 | CC-80 Roadway Rehab 2R | In and near Hercules, Rodeo, and Crocket, from Route 4 to the Carquinez Bridge. | Roadway rehabilitation. (G13 Contingency). | 3083 | Yes | 3083 | 2565 | 2565 | 2565 | No | 4624 | Yes | 4624 | 3688 | 3688 | 4610 | No | 206 | Yes | 206 | 18 | 18 | 202 | No | 0 | No | 0 | 0 | 0 | 7439 | Yes | 28 | No | 28 | 0 | 0 | 28 | No | 0 | No | 0 | 0 | 0 | 61317 | Yes | 7941 | 7941 | 6271 | 6271 | 76161 | 2020-12-03 | 2020-07-29 | 2020-07-29 |  |  | 2021-12-01 | 2022-06-24 |  |  | 2022-02-01 | 2022-06-27 |  |  | 2022-11-15 |  | 2023-02-22 | Yes |  |  | 2024-12-31 |  | 0 | Yes | Yes | Yes | Yes
224 | 04 | 1487J | SM | 101 | SM101 CAPM Curb Ramps Upgrade | In the cities of Burlingame, Millbrae, San Bruno and South San Francisco, from Broadway to Oyster Point BoulevaRd Pavement rehabilitation at onramps and offramps within project limits and 1.2 miles of mainline, and upgrade curb ramps. | CAPM AND CURB RAMPS UPGRADE | 1056 | Yes | 1056 | 816 | 816 | 816 | No | 1342 | Yes | 1342 | 1335 | 1335 | 1362 | Yes | 132 | Yes | 132 | 9 | 9 | 14 | No | 1085 | Yes | 1085 | 0 | 0 | 1365 | Yes | 100 | No | 100 | 0 | 0 | 20 | No | 12476 | Yes | 12476 | 0 | 0 | 10457 | No | 16191 | 16191 | 2160 | 2160 | 14034 | 2019-01-31 | 2018-12-28 | 2018-12-28 |  |  | 2019-10-15 | 2020-05-29 |  |  | 2019-11-01 | 2020-06-23 |  |  | 2020-05-15 |  | 2022-10-01 | Yes |  |  | 2024-03-01 |  | 0 | Yes | Yes | No | No
225 | 04 | 1488T | ALA | VAR | Detection Restoration Service Contract | IN ALAMEDA COUNTY ON ROUTES 13, 24, 580, 880, AT VARIOUS LOCATIONS. | REPAIR AND REPLACE EXISTING TRANSPORTATION MANAGEMENT SYSTEM ELEMENTS. | 64 | Yes | 64 | 56 | 56 | 56 | No | 624 | Yes | 624 | 628 | 628 | 628 | Yes | 10 | Yes | 10 | 0 | 0 | 8 | No | 901 | Yes | 901 | 363 | 363 | 925 | Yes | 0 | No | 0 | 0 | 0 | 0 | No | 1858 | Yes | 1858 | 883 | 883 | 1858 | No | 3457 | 3457 | 1930 | 1930 | 3475 |  |  | 2017-11-30 |  |  |  | 2018-03-15 |  |  |  | 2018-05-01 |  |  |  | 2021-05-17 |  |  |  |  | 2022-09-30 |  | 1857 | No | No | No | Yes
226 | 04 | 1488V | CC | VAR | Detection Restoration Service Contract | IN CONTRA COSTA COUNTY, ON ROUTES 4, 24, 80, 242, 580, AND 680 AT VARIOUS LOCATIONS. | REPAIR AND REPLACE EXISTING TRANSPORTATION MANAGEMENT SYSTEM ELEMENTS. | 50 | Yes | 50 | 40 | 40 | 40 | No | 526 | Yes | 526 | 479 | 479 | 479 | No | 10 | Yes | 10 | 3 | 3 | 7 | No | 722 | Yes | 722 | 467 | 467 | 700 | No | 0 | No | 0 | 0 | 0 | 0 | No | 1830 | Yes | 1830 | 558 | 558 | 1830 | No | 3138 | 3138 | 1547 | 1547 | 3056 |  |  | 2017-11-30 |  |  |  | 2018-03-15 |  |  |  | 2018-05-01 |  |  |  | 2021-10-05 |  |  |  |  | 2022-09-30 |  | 1830 | No | No | No | Yes
227 | 04 | 1488W | SCL | VAR | Detection Restoration Service Contract | IN SANTA CLARA COUNTY ON ROUTES 17, 85, 87, 101, 280, AND 680 AT VARIOUS LOCATIONS. | REPAIR AND REPLACE EXISTING TRANSPORTATION MANAGEMENT SYSTEM ELEMENTS. | 68 | Yes | 68 | 54 | 54 | 54 | No | 644 | Yes | 644 | 615 | 615 | 615 | No | 10 | Yes | 10 | 3 | 3 | 10 | No | 951 | Yes | 951 | 865 | 865 | 1109 | Yes | 0 | No | 0 | 0 | 0 | 15 | Yes | 5077 | Yes | 5077 | 2896 | 2896 | 5077 | No | 6750 | 6750 | 4433 | 4433 | 6880 |  |  | 2017-11-30 |  |  |  | 2018-03-15 |  |  |  | 2018-05-01 |  |  |  | 2021-06-03 |  |  |  |  | 2022-12-30 |  | 5077 | No | No | No | Yes
228 | 04 | 1488X | SM | 101 | Detection Restoration Service Contract | IN SAN MATEO COUNTY AT VARIOUS LOCATIONS | VEHICLE DETECTION SYSTEM RESTORATION | 37 | Yes | 37 | 26 | 26 | 26 | No | 429 | Yes | 429 | 455 | 455 | 455 | Yes | 10 | Yes | 10 | 2 | 2 | 6 | No | 545 | Yes | 545 | 443 | 443 | 619 | Yes | 10 | No | 10 | 6 | 6 | 6 | No | 1372 | Yes | 1372 | 655 | 655 | 1372 | No | 2403 | 2403 | 1587 | 1587 | 2484 |  |  | 2017-11-30 |  |  |  | 2018-03-15 |  |  |  | 2018-05-01 |  |  |  | 2021-07-13 |  |  |  |  | 2022-08-31 |  | 1372 | No | No | No | Yes
229 | 04 | 1488Y | MRN | 101 | Detection Restoration Service Contract | IN MARIN, SOLANO, AND SONOMA COUNTIES AT VARIOUS LOCATIONS | VEHICLE DETECTION SYSTEM RESTORATION | 101 | Yes | 101 | 83 | 83 | 83 | No | 856 | Yes | 856 | 879 | 879 | 879 | Yes | 10 | Yes | 10 | 4 | 4 | 11 | Yes | 1371 | Yes | 1371 | 795 | 795 | 1442 | Yes | 0 | No | 0 | 0 | 0 | 0 | No | 4629 | Yes | 4629 | 2645 | 2645 | 4629 | No | 6967 | 6967 | 4406 | 4406 | 7044 |  |  | 2017-11-30 |  |  |  | 2018-03-15 |  |  |  | 2018-05-01 |  |  |  | 2021-06-09 |  |  |  |  | 2022-09-30 |  | 4629 | No | No | No | Yes
230 | 04 | 1488Z | ALA | 980 | Controller replacement | In various counties, on various routes at various locations. | Upgrade controllers in vehicle detection and traffic signal systems. | 160 | Yes | 160 | 148 | 148 | 151 | No | 490 | Yes | 490 | 0 | 0 | 441 | No | 15 | Yes | 15 | 0 | 0 | 14 | No | 1240 | No | 1240 | 0 | 0 | 1191 | No | 15 | No | 15 | 0 | 0 | 15 | No | 7300 | No | 7300 | 0 | 0 | 7316 | Yes | 9220 | 9220 | 148 | 148 | 9128 |  | 2021-12-31 |  | 2022-04-30 | Yes | 2022-09-01 |  | 2022-09-01 | No | 2022-10-01 |  | 2022-10-01 | No | 2023-06-15 |  | 2023-06-15 | No |  |  | 2026-06-14 |  | 0 | No | No | No | No
231 | 04 | 1489K | NAP | 121 | Capell Br. Replacement | Near Napa, at Capell Creek Bridge No 21-0064. | Bridge rehabilitation. | 750 | Yes | 750 | 728 | 728 | 728 | No | 1083 | Yes | 1083 | 1061 | 1061 | 1061 | No | 100 | Yes | 100 | 98 | 98 | 100 | No | 821 | Yes | 821 | 732 | 732 | 869 | Yes | 225 | No | 225 | 13 | 13 | 13 | No | 1560 | Yes | 1560 | 1238 | 1238 | 1560 | No | 4539 | 4539 | 3870 | 3870 | 4331 |  | 2018-09-01 | 2018-09-20 |  |  | 2020-03-01 | 2020-04-20 |  |  | 2020-04-15 | 2020-05-18 |  |  | 2020-10-30 | 2020-12-09 |  |  |  |  | 2023-01-16 |  | 1559 | No | No | No | No
232 | 04 | 1490D | NAP | 29 | SR 29 York to 128 Split CAPM | In and near St Helena and Calistoga, from York Creek Bridge to Route 128. | Pavement rehabilitation. | 1190 | Yes | 1190 | 1069 | 1069 | 1069 | No | 1100 | Yes | 1100 | 1082 | 1082 | 1082 | No | 67 | Yes | 67 | 50 | 50 | 54 | No | 1100 | Yes | 1100 | 89 | 89 | 1568 | Yes | 20 | No | 20 | 0 | 0 | 0 | No | 8350 | Yes | 8350 | 0 | 0 | 8350 | No | 11827 | 11827 | 2290 | 2290 | 12123 |  | 2020-07-10 | 2020-06-30 |  |  | 2021-02-19 | 2021-05-24 |  |  | 2021-05-07 | 2021-06-11 |  |  | 2022-04-01 | 2022-03-16 |  |  |  |  | 2023-01-31 |  | 8350 | No | Yes | No | No
233 | 04 | 1492C | SCL | 87 | PSSR - SCL-87 Pavement 2R | In San Jose, from Route 85 to West Julian Street. | Roadway rehabilitation. (G13 Contingency). | 2767 | Yes | 2767 | 2631 | 2631 | 2631 | No | 4425 | Yes | 4425 | 3346 | 3346 | 4429 | Yes | 82 | Yes | 82 | 66 | 66 | 86 | Yes | 0 | No | 0 | 0 | 0 | 6581 | Yes | 304 | No | 304 | 0 | 0 | 85 | No | 0 | No | 0 | 0 | 0 | 52743 | Yes | 7578 | 7578 | 6043 | 6043 | 66555 | 2021-03-25 | 2020-11-05 | 2020-11-05 |  |  | 2022-04-01 | 2022-06-22 |  |  | 2022-04-30 | 2022-06-29 |  |  | 2023-02-01 |  | 2023-04-18 | No |  |  | 2025-03-03 |  | 0 | No | Yes | No | Yes
234 | 04 | 1493A | CC | 24 | Seismic Restoration | In Orinda, at St Stephens Drive Overcrossing No 28-0111. | Seismic retrofit. | 1122 | Yes | 1122 | 1080 | 1080 | 1080 | No | 1375 | Yes | 1375 | 1326 | 1326 | 1387 | Yes | 175 | Yes | 175 | 50 | 50 | 147 | No | 1700 | No | 1700 | 0 | 0 | 1700 | No | 68 | No | 68 | 21 | 21 | 68 | No | 5600 | No | 5600 | 0 | 0 | 5600 | No | 10040 | 10040 | 2477 | 2477 | 9982 |  | 2020-04-13 | 2020-05-18 |  |  | 2022-01-04 | 2022-05-26 |  |  | 2022-02-21 | 2022-06-02 |  |  | 2022-12-12 |  | 2022-12-21 | No |  |  | 2024-07-12 |  | 0 | No | No | No | No
235 | 04 | 1493C | NAP | 121 | Tulucay Creek Bridge Replacement | In the city of Napa, at Tulocay Creek Bridge No 21-0003 (PM 6.423). | Replace existing bridge with a single span precast concrete box girder bridge. | 3302 | Yes | 3302 | 1603 | 1603 | 3873 | Yes | 3248 | No | 3248 | 0 | 0 | 3397 | Yes | 1050 | No | 1050 | 0 | 0 | 1051 | Yes | 3510 | No | 3510 | 0 | 0 | 3538 | Yes | 6282 | No | 6282 | 0 | 0 | 3103 | No | 15580 | No | 15580 | 0 | 0 | 15580 | No | 32972 | 32972 | 1603 | 1603 | 30542 |  | 2022-10-20 |  | 2022-12-05 | No | 2024-05-03 |  | 2024-05-03 | No | 2024-05-03 |  | 2024-05-03 | No | 2025-02-24 |  | 2025-02-24 | No |  |  | 2027-12-03 |  | 0 | No | Yes | No | No
236 | 04 | 1493E | MRN | 101 | Multi-asset Interchange Improvement | In Corte Madera, at Tamalpais Drive Overcrossing No 27-0072 (PM 7.37). | Bridge seismic restoration and upgrade facilities to Americans with Disabilities Act (ADA) standards. | 2115 | Yes | 2115 | 1504 | 1504 | 2519 | Yes | 3462 | No | 3462 | 0 | 0 | 3989 | Yes | 169 | No | 169 | 0 | 0 | 274 | Yes | 2957 | No | 2957 | 0 | 0 | 3042 | Yes | 692 | No | 692 | 0 | 0 | 3255 | Yes | 16810 | No | 16810 | 0 | 0 | 13905 | No | 26205 | 26205 | 1504 | 1504 | 26984 |  | 2022-12-30 |  | 2022-12-30 | No | 2024-01-15 |  | 2024-05-31 | Yes | 2024-06-28 |  | 2024-06-28 | No | 2025-01-22 |  | 2025-01-22 | No |  |  | 2025-09-30 |  | 0 | No | Yes | No | No
237 | 04 | 1493K | MRN | 101 | Irwn Cr Br Rehab Culvert | In San Rafael, at Irwin Creek Bridge No 27-0097. | Rehabilitate corrugated metal arch culvert bridge and adjoining deteriorated culvert structures. | 1100 | Yes | 1100 | 1058 | 1058 | 1058 | No | 1057 | Yes | 1057 | 1043 | 1043 | 1043 | No | 215 | Yes | 215 | 94 | 94 | 170 | No | 610 | Yes | 610 | 17 | 17 | 861 | Yes | 944 | No | 944 | 8 | 8 | 8 | No | 811 | Yes | 811 | 0 | 0 | 811 | No | 4737 | 4737 | 2220 | 2220 | 3951 |  | 2019-12-02 | 2019-12-04 |  |  | 2021-09-01 | 2021-11-16 |  |  | 2021-10-01 | 2021-12-06 |  |  | 2022-03-16 | 2022-06-01 |  |  |  |  | 2023-11-13 |  | 811 | No | No | No | No
238 | 04 | 1493M | SON | 12 | SON 12 CAPM | In and near Santa Rosa, from Llano Road to Farmers Lane. | Rehabilitate pavement, upgrade guardrail to make standard and upgrade curb ramps to make Americans with Disabilities Act (ADA) compliant. (G13 Contingency). | 2084 | Yes | 2084 | 2084 | 2084 | 2084 | No | 2900 | Yes | 2900 | 2843 | 2843 | 2852 | No | 66 | Yes | 66 | 12 | 12 | 59 | No | 0 | No | 0 | 0 | 0 | 3358 | Yes | 280 | No | 280 | 18 | 18 | 215 | No | 0 | No | 0 | 0 | 0 | 27681 | Yes | 5330 | 5330 | 4957 | 4957 | 36249 |  | 2020-05-01 | 2020-06-29 |  |  | 2021-11-01 | 2022-06-14 |  |  | 2021-12-01 | 2022-06-24 |  |  | 2022-06-15 |  | 2023-01-20 | Yes |  |  | 2025-09-01 |  | 0 | Yes | Yes | No | No
239 | 04 | 1493N | ALA | 580 | 0K530 Install Ramp Metering | In and near San Leandro and Oakland, from Strobridge Avenue to 0.7 mile west of San Pablo Avenue at various locations (PM 30.36/46.5L/R). | Install and upgrade ramp meters and widen ramps to provide High-Occupancy Vehicle (HOV) bypass ramp lanes. (G13 Contingency). | 4627 | Yes | 4627 | 830 | 830 | 2226 | No | 3441 | No | 3441 | 0 | 0 | 3452 | Yes | 514 | No | 514 | 0 | 0 | 460 | No | 0 | No | 0 | 0 | 0 | 5570 | Yes | 85 | No | 85 | 0 | 0 | 10 | No | 0 | No | 0 | 0 | 0 | 37000 | Yes | 8667 | 8667 | 830 | 830 | 48718 |  | 2022-10-01 |  | 2022-10-01 | No | 2024-03-01 |  | 2024-03-01 | No | 2024-05-01 |  | 2024-05-01 | No | 2024-11-01 |  | 2024-11-01 | No |  |  | 2026-07-01 |  | 0 | No | Yes | No | No
240 | 04 | 1493P | SOL | 80 | BRIDGE DECK PROGRAM | In and near Fairfield, Vacaville, and Dixon, on Routes 12, 80, and 680 at various locations. | Apply polyester concrete overlay to bridge decks. (Bridge Deck Preservation). | 140 | Yes | 140 | 121 | 121 | 257 | Yes | 4147 | Yes | 2100 | 54 | 54 | 2120 | No | 70 | Yes | 70 | 1 | 1 | 68 | No | 2900 | No | 2900 | 0 | 0 | 2926 | Yes | 0 | No | 0 | 0 | 0 | 10 | Yes | 11400 | No | 11400 | 0 | 0 | 11400 | No | 18657 | 16610 | 176 | 176 | 16781 |  |  |  | 2022-08-15 |  |  |  | 2023-05-19 |  |  |  | 2023-06-16 |  |  |  | 2023-09-22 |  |  |  | 2024-09-23 |  | 0 | No | No | No | Yes
241 | 04 | 1494C | ALA | 185 | ALA 185 CAPM | In San Leandro, from 0.1 mile south of Bayfair Drive to Durant Avenue; also on Route 112 from Doolittle Drive to East 14th Street/Route 185 (PM R0.0/1.782). | Rehabilitate pavement and upgrade curb ramps to Americans with Disabilities Act (ADA) standards. | 1417 | Yes | 1417 | 1407 | 1407 | 1407 | No | 2497 | Yes | 2497 | 2327 | 2327 | 2926 | Yes | 375 | Yes | 375 | 69 | 69 | 417 | Yes | 2405 | No | 2405 | 0 | 0 | 2590 | Yes | 40 | No | 40 | 0 | 0 | 75 | Yes | 14928 | No | 14928 | 0 | 0 | 12860 | No | 21662 | 21662 | 3803 | 3803 | 20275 |  | 2020-03-02 | 2020-07-03 |  |  | 2021-07-01 | 2022-06-17 |  |  | 2021-10-08 | 2022-06-21 |  |  | 2022-05-04 |  | 2023-01-16 | Yes |  |  | 2025-01-17 |  | 0 | Yes | No | No | No
242 | 04 | 1494E | NAP | 29 | Bridge Rail Replacement | In and near Yountville, at Dry Creek Bridge No 21-0014 (PM 16.48), Perfume Creek Bridge No 21-0051 (PM 17.81), and California Drive Undercrossing No 21-0047 (PM 19.04). | Upgrade bridge rails and widen shoulders to make standaRd | 2600 | Yes | 2600 | 2594 | 2594 | 2594 | No | 1771 | Yes | 1771 | 1668 | 1668 | 2089 | Yes | 350 | Yes | 350 | 65 | 65 | 276 | No | 1500 | No | 1500 | 0 | 0 | 1495 | No | 295 | No | 295 | 23 | 23 | 173 | No | 7111 | No | 7111 | 0 | 0 | 7111 | No | 13627 | 13627 | 4350 | 4350 | 13738 |  | 2020-10-01 | 2020-10-22 |  |  | 2022-04-01 |  | 2022-10-07 | Yes | 2022-06-01 |  | 2022-12-01 | Yes | 2022-12-29 |  | 2023-04-28 | Yes |  |  | 2024-12-30 |  | 0 | Yes | Yes | Yes | Yes
243 | 04 | 1494F | SOL | 80 | SOL 80 Roadway Rehab CAPM | In and near Fairfield and Vacaville, from 1.5 miles east of Suisun Valley Road/Pittman Road to 0.8 mile east of Leisure Town Road/Vaca Valley Parkway. | Rehabilitate pavement, upgrade facilities to Americans with Disabilities Act (ADA) standards, and upgrade guardrail and Transportation Management System (TMS) elements. (G13 Contingency). | 1276 | Yes | 1276 | 963 | 963 | 1401 | Yes | 1456 | No | 1456 | 0 | 0 | 1382 | No | 29 | No | 29 | 0 | 0 | 32 | Yes | 0 | No | 0 | 0 | 0 | 206 | Yes | 25 | No | 25 | 0 | 0 | 20 | No | 0 | No | 0 | 0 | 0 | 25043 | Yes | 2786 | 2786 | 963 | 963 | 28084 |  | 2022-08-15 |  | 2022-08-15 | No | 2024-05-15 |  | 2024-05-15 | No | 2024-06-03 |  | 2024-06-03 | No | 2025-01-10 |  | 2025-01-07 | No |  |  | 2026-06-02 |  | 0 | No | Yes | No | No
244 | 04 | 1494G | SM | 1 | SM-1 Pescadero Crk. Br. Rails | Near Pescadero, at Pescadero Creek Bridge No 35-0028. | Upgrade bridge rails and repair approach slabs. | 1200 | Yes | 1200 | 999 | 999 | 999 | No | 1180 | Yes | 1180 | 1114 | 1114 | 1392 | Yes | 8 | Yes | 8 | 7 | 7 | 92 | Yes | 1200 | No | 1200 | 0 | 0 | 1520 | Yes | 260 | No | 260 | 2 | 2 | 260 | No | 4434 | No | 4434 | 0 | 0 | 4407 | No | 8282 | 8282 | 2122 | 2122 | 8670 |  | 2020-11-01 | 2020-11-01 |  |  | 2022-04-01 |  | 2022-09-01 | Yes | 2022-05-01 |  | 2022-09-12 | Yes | 2022-12-15 |  | 2023-04-25 | Yes |  |  | 2023-12-15 |  | 0 | Yes | No | No | No
245 | 04 | 1496K | CC | 680 | HM315-Bridge Program | In and near Walnut Creek and Martinez, at Rudgear Road Undercrossing No 28-0059 (PM R12.6), Olympic Boulevard Undercrossing No 28-0161 (PM 13.9), and Mococo Overhead No 28-0356R (PM 24.3). | Apply polyester concrete overlay to bridge decks. (Bridge Deck Preservation). | 167 | Yes | 167 | 161 | 161 | 262 | Yes | 5270 | Yes | 2310 | 49 | 49 | 2380 | No | 83 | Yes | 83 | 1 | 1 | 52 | No | 3290 | No | 3290 | 0 | 0 | 3318 | Yes | 0 | No | 0 | 0 | 0 | 0 | No | 13600 | No | 13600 | 0 | 0 | 13600 | No | 22410 | 19450 | 211 | 211 | 19612 |  |  |  | 2022-08-15 |  |  |  | 2023-05-19 |  |  |  | 2023-06-16 |  |  |  | 2023-09-22 |  |  |  | 2024-09-23 |  | 0 | No | No | No | Yes
246 | 04 | 1497A | SM | 84 | CAPM SR-84 | In and near Woodside and Redwood City, from Route 280 to Route 101. | Rehabilitate pavement, make curb ramps and sidewalks Americans with Disabilities Act (ADA) compliant, and upgrade guardrails to make standaRd | 2340 | Yes | 2340 | 2134 | 2134 | 2134 | No | 3275 | Yes | 3275 | 2964 | 2964 | 3913 | Yes | 243 | Yes | 243 | 268 | 268 | 314 | Yes | 3120 | No | 3120 | 0 | 0 | 3109 | No | 566 | No | 566 | 7 | 7 | 25 | No | 18225 | No | 18225 | 0 | 0 | 18225 | No | 27769 | 27769 | 5373 | 5373 | 27720 |  | 2020-05-01 | 2020-06-02 |  |  | 2021-06-01 |  | 2022-08-31 | Yes | 2021-08-01 |  | 2022-09-30 | Yes | 2022-03-01 |  | 2023-03-01 | Yes |  |  | 2023-12-15 |  | 0 | Yes | Yes | Yes | Yes
247 | 04 | 1498A | ALA | 84 | ALA DRAINAGE RESTORATION | Near Fremont, at Silver Spring Road Underpass; also on Route 580 at Fairmont Drive Overcrossing (PM 32.7) and Route 880 at Washington Avenue (PM 20.8); also in Solano County on Route 80 at Route 113 Junction (PM 42.84). | Upgrade drainage pump plants. | 1091 | Yes | 1091 | 182 | 182 | 1159 | Yes | 1787 | No | 1787 | 0 | 0 | 2139 | Yes | 155 | No | 155 | 0 | 0 | 148 | No | 2028 | No | 2028 | 0 | 0 | 2078 | Yes | 89 | No | 89 | 0 | 0 | 55 | No | 4483 | No | 4483 | 0 | 0 | 4483 | No | 9633 | 9633 | 182 | 182 | 10062 |  | 2022-10-31 |  | 2022-10-31 | No | 2024-05-30 |  | 2024-05-30 | No | 2024-06-07 |  | 2024-06-07 | No | 2025-01-30 |  | 2025-01-30 | No |  |  | 2026-05-29 |  | 0 | No | No | No | No
248 | 04 | 1498F | SCL | 82 | CAPM | In Mountain View, Los Altos, and Palo Alto, from 0.7 mile north of Route 237 to Sand Hill Road. | Pavement rehabilitation, and construct three pedestrian crossings and 1.1 miles of Class 2 bike lanes as complete streets elements. (G13 Contingency). | 888 | Yes | 888 | 885 | 885 | 885 | No | 1974 | Yes | 1974 | 1679 | 1679 | 2803 | Yes | 99 | Yes | 99 | 40 | 40 | 106 | Yes | 0 | No | 0 | 0 | 0 | 1983 | Yes | 360 | No | 360 | 48 | 48 | 48 | No | 0 | No | 0 | 0 | 0 | 26065 | Yes | 3321 | 3321 | 2652 | 2652 | 31890 |  | 2020-04-30 | 2020-05-28 |  |  | 2021-11-17 |  | 2022-11-15 | Yes | 2021-12-01 |  | 2022-12-01 | Yes | 2022-05-27 |  | 2023-06-05 | Yes |  |  | 2024-10-31 |  | 0 | Yes | Yes | No | No
249 | 04 | 1498G | SM | 280 | SM-280 Seismic at 5 Br.s | In and near Menlo Park and San Bruno, from Alpine Road to Route 380 at Alpine Road Undercrossing No 35-0009L/R (PM R0.05), Sand Hill Road Overcrossing (OC) (South) No 35-0007 (PM R1.56), Sand Hill Road OC (North) No 35-0008 (PM R1.62), and Route 280/380 Separation No 35-0217 (PM R20.97). | Structure seismic retrofit. | 860 | Yes | 860 | 858 | 858 | 858 | No | 2403 | Yes | 2403 | 2384 | 2384 | 2540 | Yes | 100 | Yes | 100 | 13 | 13 | 90 | No | 2584 | No | 2584 | 0 | 0 | 2946 | Yes | 262 | No | 262 | 33 | 33 | 262 | No | 14361 | No | 14361 | 0 | 0 | 18461 | Yes | 20570 | 20570 | 3288 | 3288 | 25157 |  | 2020-03-18 | 2020-03-27 |  |  | 2022-03-01 | 2022-06-03 |  |  | 2022-04-01 | 2022-06-30 |  |  | 2022-07-01 |  | 2023-02-08 | Yes |  |  | 2024-02-07 |  | 0 | No | Yes | No | No
250 | 04 | 1498N | SM | 280 | HM315 | In and near Woodside, South San Francisco and Daly City, at various locations. | Apply polyester concrete overlay to bridge decks. (Bridge Deck Preservation). | 110 | Yes | 110 | 107 | 107 | 107 | No | 1670 | Yes | 1670 | 91 | 91 | 1893 | Yes | 55 | Yes | 55 | 3 | 3 | 55 | No | 2480 | No | 2480 | 0 | 0 | 2511 | Yes | 0 | No | 0 | 0 | 0 | 50 | Yes | 9000 | No | 9000 | 0 | 0 | 9000 | No | 13315 | 13315 | 201 | 201 | 13616 |  |  |  | 2022-08-15 |  |  |  | 2023-05-19 |  |  |  | 2023-06-16 |  |  |  | 2023-09-22 |  |  |  | 2024-09-23 |  | 0 | No | No | No | Yes
251 | 04 | 2020B | ALA | 680 | BRIDGE SCOUR MITIGATION | Near Sunol, at Alameda Creek Bridge No 33-0047. | Scour mitigation, bridge deck rehabilitation, and joint seal replacement. | 1699 | Yes | 1699 | 1198 | 1198 | 2167 | Yes | 1602 | No | 1602 | 0 | 0 | 1664 | Yes | 223 | No | 223 | 0 | 0 | 219 | No | 2166 | No | 2166 | 0 | 0 | 2202 | Yes | 305 | No | 305 | 0 | 0 | 260 | No | 7461 | No | 7461 | 0 | 0 | 2000 | No | 13456 | 13456 | 1198 | 1198 | 8512 |  | 2022-08-12 |  | 2022-09-29 | No | 2024-02-01 |  | 2024-06-03 | Yes | 2024-03-01 |  | 2024-06-14 | Yes | 2024-10-01 |  | 2024-12-20 | No |  |  | 2026-04-01 |  | 0 | No | Yes | No | No
252 | 04 | 2020C | ALA | 680 | BRIDGE REHABILITATION | In Fremont, at Mission San Jose (680/238) Separation No 33-0294. | Bridge approach slabs replacement, bridge deck overlay, and joint seals replacement. | 712 | Yes | 712 | 708 | 708 | 708 | No | 1810 | Yes | 1810 | 372 | 372 | 2595 | Yes | 46 | Yes | 46 | 0 | 0 | 44 | No | 4165 | No | 4165 | 0 | 0 | 4407 | Yes | 139 | No | 139 | 0 | 0 | 25 | No | 14937 | No | 14937 | 0 | 0 | 14937 | No | 21809 | 21809 | 1080 | 1080 | 22716 |  | 2021-12-13 | 2022-02-04 |  |  | 2023-07-01 |  | 2023-07-01 | No | 2023-08-01 |  | 2023-09-01 | No | 2024-03-01 |  | 2024-05-24 | No |  |  | 2026-09-01 |  | 0 | No | Yes | No | No
253 | 04 | 2020F | SCL | 152 | SCL-152 Drainage Improvement and MGS | Near Gilroy, from 1.9 miles east of Bloomfield Avenue to west of Casa De Frita Parkway at various locations. | Rehabilitate drainage systems, upgrade guardrail, and pave roadside areas to prevent vegetation growth and enhance highway worker safety. | 977 | Yes | 977 | 714 | 714 | 714 | No | 0 | Yes | 0 | 0 | 0 | 1126 | Yes | 0 | Yes | 0 | 0 | 0 | 9 | Yes | 1020 | No | 1020 | 0 | 0 | 1303 | Yes | 31 | No | 31 | 0 | 0 | 0 | No | 4213 | No | 4213 | 0 | 0 | 4213 | No | 6241 | 6241 | 714 | 714 | 7365 |  | 2022-06-30 | 2022-06-21 |  |  | 2023-10-02 |  | 2023-10-02 | No | 2023-11-01 |  | 2023-11-01 | No | 2024-07-01 |  | 2024-07-01 | No |  |  | 2025-07-01 |  | 0 | No | Yes | No | Yes
254 | 04 | 2020G | SM | 101 | RAMP METERING SYSTEMS | In Alameda, Contra Costa, Santa Clara, San Mateo, and Solano Counties, on various routes at various locations. | Modify and enhance ramp metering systems to improve Transportation Management System (TMS) performance and install guardrail at ramps to enhance highway worker safety. | 1179 | Yes | 1179 | 1160 | 1160 | 1160 | No | 1230 | Yes | 1230 | 0 | 0 | 1274 | Yes | 40 | Yes | 40 | 0 | 0 | 40 | No | 2806 | No | 2806 | 0 | 0 | 1484 | No | 31 | No | 31 | 0 | 0 | 30 | No | 10400 | No | 10400 | 0 | 0 | 7550 | No | 15686 | 15686 | 1160 | 1160 | 11538 |  | 2022-04-15 | 2022-05-06 |  |  | 2023-05-15 |  | 2023-05-15 | No | 2023-05-30 |  | 2023-05-30 | No | 2023-12-06 |  | 2023-12-06 | No |  |  | 2024-12-20 |  | 0 | Yes | Yes | Yes | Yes
255 | 04 | 2020L | ALA | 13 | BRUNS DRIVE POC | In Oakland, at Burns Drive Pedestrian Overcrossing No 33-0244 (PM 7.91). | Replace pedestrian overcrossing and upgrade facilities to Americans with Disabilities Act (ADA) standards. | 2359 | Yes | 2359 | 1437 | 1437 | 2526 | Yes | 2584 | No | 2584 | 0 | 0 | 2579 | No | 93 | No | 93 | 0 | 0 | 60 | No | 4252 | No | 4252 | 0 | 0 | 4232 | No | 26 | No | 26 | 0 | 0 | 7 | No | 17450 | No | 17450 | 0 | 0 | 17450 | No | 26764 | 26764 | 1437 | 1437 | 26854 |  | 2022-06-15 |  | 2022-12-30 | Yes | 2024-02-20 |  | 2024-02-20 | No | 2024-06-15 |  | 2024-03-05 | No | 2024-09-03 |  | 2024-09-03 | No |  |  | 2025-10-03 |  | 0 | Yes | No | No | No
256 | 04 | 2020M | ALA | 580 | BRIDGE REHABILITATION | In Oakland, at Fruitvale Avenue Undercrossing No 33-0324 (PM R41.43), Van Buren Avenue Pedestrian Overcrossing (POC) No 33-0313 (PM 43.75), Santa Clara Avenue POC No 33-0312 (PM 43.76), and Broadway Richmond Boulevard Undercrossing No 33-0285 (PM 44.51). | Seismic retrofit and bridge rail replacement of two bridges, and demolish and replace two POCs. | 3170 | Yes | 3170 | 1755 | 1755 | 3746 | Yes | 3418 | No | 3418 | 0 | 0 | 3395 | No | 311 | No | 311 | 0 | 0 | 316 | Yes | 5301 | No | 5301 | 0 | 0 | 5286 | No | 146 | No | 146 | 0 | 0 | 260 | Yes | 26505 | No | 26505 | 0 | 0 | 25027 | No | 38851 | 38851 | 1755 | 1755 | 38030 |  | 2022-09-15 |  | 2022-11-30 | No | 2024-02-16 |  | 2024-02-16 | No | 2024-03-18 |  | 2024-04-18 | No | 2024-11-14 |  | 2024-11-14 | No |  |  | 2027-04-15 |  | 0 | No | Yes | No | Yes
257 | 04 | 2020N | MRN | 1 | Marin 1 Bridge Rail replacements | Near Mill Valley, Stinson Beach, and Olema, at Coyote Creek Bridge No 27-0018 (PM 0.42), Eskoot Creek Bridge No 27-0077 (PM 12.37), Olema Creek Bridge No 27-0020 (PM 22.81) and Olema Creek Bridge No 27-0021 (PM 22.96). | Upgrade bridge rails. | 1650 | Yes | 1650 | 905 | 905 | 1750 | Yes | 1755 | No | 1755 | 0 | 0 | 1800 | Yes | 444 | No | 444 | 0 | 0 | 448 | Yes | 2065 | No | 2065 | 0 | 0 | 2120 | Yes | 676 | No | 676 | 0 | 0 | 884 | Yes | 8091 | No | 8091 | 0 | 0 | 6232 | No | 14681 | 14681 | 905 | 905 | 13234 |  | 2022-10-06 |  | 2023-01-13 | Yes | 2024-04-05 |  | 2024-04-05 | No | 2024-05-01 |  | 2024-05-01 | No | 2025-01-17 |  | 2025-01-17 | No |  |  | 2026-08-30 |  | 0 | Yes | No | No | No
258 | 04 | 2020P | SCL | 680 | SCL 680 CAPM | In and near San Jose and Milpitas, from Route 101 to Alameda County line. | Rehabilitate pavement, upgrade guardrail, construct Maintenance Vehicle Pullout (MVP), upgrade facilities to Americans with Disabilities Act (ADA) standards, improve planting, irrigation, and roadside safety features, and provide stormwater mitigation. | 2474 | Yes | 2474 | 0 | 0 | 2484 | Yes | 4299 | No | 4299 | 0 | 0 | 4314 | Yes | 257 | No | 257 | 0 | 0 | 264 | Yes | 5792 | No | 5792 | 0 | 0 | 5807 | Yes | 101 | No | 101 | 0 | 0 | 28 | No | 29588 | No | 29588 | 0 | 0 | 29588 | No | 42511 | 42511 | 0 | 0 | 42485 |  |  |  | 2024-04-01 |  |  |  | 2025-11-17 |  |  |  | 2025-12-01 |  |  |  | 2026-08-01 |  |  |  | 2028-08-01 |  | 0 | No | No | No | No
259 | 04 | 2020Q | SOL | 113 | R-113 3R | Near Rio Vista, from Route 12 to 1.1 miles south of Brown Road. | Rehabilitate roadway and drainage systems, provide Class 2 bike lane, realign curves, and widen and replace bridges. (Long Lead Project). | 5961 | Yes | 5961 | 0 | 0 | 5873 | No | 0 | No | 0 | 0 | 0 | 5268 | Yes | 0 | No | 0 | 0 | 0 | 1177 | Yes | 0 | No | 0 | 0 | 0 | 12627 | Yes | 0 | No | 0 | 0 | 0 | 11569 | Yes | 0 | No | 0 | 0 | 0 | 37700 | Yes | 5961 | 5961 | 0 | 0 | 74214 |  |  |  | 2026-03-02 |  |  |  | 2029-05-01 |  |  |  | 2029-06-01 |  |  |  | 2030-03-01 |  |  |  | 2032-12-30 |  | 0 | No | Yes | No | Yes
260 | 04 | 2021B | SCL | 82 | BRIDGE RAIL SCL 82 | In the cities of Santa Clara and Palo Alto, at De La Cruz Boulevard Overcrossing (OC) No 37-0214 (PM R11.38), Mayfield Pedestrian Undercrossing (UC) No 37-0091 (PM 24.15), University Avenue OC No 37-0092 (PM 25.88), and San Francisquito Creek Bridge No 37-0018 (PM 26.36). | Upgrade bridge rails at three locations and abandon the Mayfield Pedestrian UC. | 638 | Yes | 638 | 637 | 637 | 637 | No | 1824 | Yes | 1824 | 494 | 494 | 1965 | Yes | 35 | Yes | 35 | 20 | 20 | 162 | Yes | 1350 | No | 1350 | 0 | 0 | 1343 | No | 43 | No | 43 | 0 | 0 | 35 | No | 6202 | No | 6202 | 0 | 0 | 9002 | Yes | 10092 | 10092 | 1151 | 1151 | 13144 |  | 2022-02-03 | 2022-01-25 |  |  | 2023-04-17 |  | 2023-06-06 | No | 2023-05-01 |  | 2023-06-20 | No | 2023-12-12 |  | 2024-02-08 | No |  |  | 2025-04-04 |  | 0 | No | Yes | No | Yes
261 | 04 | 2021J | SM | 1 | SM1 Br Seismic+Rail | Near San Gregorio, at San Gregorio Creek Bridge No 35-0030. | Bridge seismic retrofit and upgrade bridge rails. | 2866 | Yes | 2866 | 0 | 0 | 1511 | No | 2932 | No | 2932 | 0 | 0 | 804 | No | 183 | No | 183 | 0 | 0 | 77 | No | 3160 | No | 3160 | 0 | 0 | 582 | No | 438 | No | 438 | 0 | 0 | 0 | No | 12280 | No | 12280 | 0 | 0 | 2561 | No | 21859 | 21859 | 0 | 0 | 5535 |  |  |  | 2024-04-03 |  |  |  | 2026-01-01 |  |  |  | 2026-02-02 |  |  |  | 2026-08-03 |  |  |  | 2028-02-01 |  | 0 | No | No | No | No
262 | 04 | 2021K | SF | 101 | BRIDGE REHABILITATION | in the City and County of San Francisco, at Central Viaduct No 34-0077; also on Route 80 at Bayshore Viaduct No 34-0088 (PM L3.79/4.99). | Rehabilitate bridges by overlaying bridge deck, replacing joint seals, and upgrading bridge rails. (G13 Contingency). | 1941 | Yes | 1941 | 1182 | 1182 | 1182 | No | 3466 | Yes | 3466 | 4 | 4 | 1396 | No | 292 | Yes | 292 | 0 | 0 | 254 | No | 0 | No | 0 | 0 | 0 | 4537 | Yes | 52 | No | 52 | 14 | 14 | 246 | Yes | 0 | No | 0 | 0 | 0 | 28514 | Yes | 5751 | 5751 | 1200 | 1200 | 36129 |  | 2022-02-01 | 2022-06-30 |  |  | 2023-09-01 |  | 2023-09-01 | No | 2023-10-01 |  | 2023-10-01 | No | 2024-05-01 |  | 2024-05-01 | No |  |  | 2025-11-01 |  | 0 | No | Yes | No | No
263 | 04 | 2021L | SCL | 17 | SCL-17-BRIDGE RAIL UPGRADE AND REPLACEMENT | In Los Gatos, at Santa Cruz Avenue Undercrossing No 37-0124L (PM 6.16) and Main Street Overcrossing No 37-0117 (PM 6.55). | Upgrade bridge rails. | 794 | Yes | 794 | 768 | 768 | 768 | No | 1453 | No | 1453 | 0 | 0 | 1448 | No | 17 | No | 17 | 0 | 0 | 16 | No | 1471 | No | 1471 | 0 | 0 | 1471 | No | 26 | No | 26 | 0 | 0 | 15 | No | 4879 | No | 4879 | 0 | 0 | 4879 | No | 8640 | 8640 | 768 | 768 | 8597 |  | 2022-05-31 | 2022-06-20 |  |  | 2023-11-30 |  | 2023-11-30 | No | 2023-12-29 |  | 2023-12-29 | No | 2024-06-30 |  | 2024-08-12 | Yes |  |  | 2025-03-17 |  | 0 | Yes | No | No | No
264 | 04 | 2022B | SF | 280 | CAPM SF-280 | In the City and County of San Francisco, from San Mateo County line to Brannan Street. | Rehabilitate pavement, upgrade concrete median barrier, rehabilitate drainage systems, upgrade facilities to Americans with Disabilities Act (ADA) standards, and replace Whipple Avenue Pedestrian Overcrossing No 34-0096. (G13 Contingency). | 4101 | Yes | 4101 | 2014 | 2014 | 5265 | Yes | 6682 | No | 6682 | 0 | 0 | 7325 | Yes | 322 | No | 322 | 0 | 0 | 312 | No | 0 | No | 0 | 0 | 0 | 9358 | Yes | 1373 | No | 1373 | 0 | 0 | 1373 | No | 0 | No | 0 | 0 | 0 | 82958 | Yes | 12478 | 12478 | 2014 | 2014 | 106591 |  | 2022-07-29 |  | 2022-10-14 | No | 2024-01-02 |  | 2024-01-02 | No | 2024-02-01 |  | 2024-06-01 | Yes | 2024-09-02 |  | 2024-09-02 | No |  |  | 2027-03-01 |  | 0 | No | Yes | No | No
265 | 04 | 2022C | SM | 1 | SM 1 Multi-asset Roadway Rehab | In and near Half Moon Bay, from south of Wavecrest Road to south of Marine BoulevaRd Rehabilitate roadway, upgrade guardrail and Transportation Management System (TMS) elements, rehabilitate drainage systems, upgrade facilities to Americans with Disabilities Act (ADA) standards, and make bicycle improvements. (G13 Contingency). | REHABILITATE PAVEMENT AND OTHER ROADWAY INFRASTRUCTURES. | 2640 | Yes | 2640 | 1852 | 1852 | 3067 | Yes | 4055 | No | 4055 | 0 | 0 | 4303 | Yes | 147 | No | 147 | 0 | 0 | 132 | No | 0 | No | 0 | 0 | 0 | 5007 | Yes | 282 | No | 282 | 0 | 0 | 200 | No | 0 | No | 0 | 0 | 0 | 33836 | Yes | 7124 | 7124 | 1852 | 1852 | 46545 |  | 2022-10-14 |  | 2022-10-14 | No | 2024-04-01 |  | 2024-04-01 | No | 2024-04-12 |  | 2024-04-12 | No | 2024-10-01 |  | 2024-10-01 | No |  |  | 2026-10-01 |  | 0 | No | Yes | No | No
266 | 04 | 2022K | CC | 80 | I-80/APPIAN/CUMMINGS BRIDGE RAIL | In Pinole and Hercules, at Appian Way Overcrossing No 28-0146R (PM 7.60) and Cummings Skyway Overcrossing No 28-0149 (PM 12.75). | Upgrade bridge rails and widen bridges to comply with Americans with Disabilities Act (ADA) standards. | 1870 | Yes | 1870 | 1828 | 1828 | 1949 | Yes | 0 | Yes | 0 | 0 | 0 | 2891 | Yes | 0 | Yes | 0 | 0 | 0 | 17 | Yes | 4256 | No | 4256 | 0 | 0 | 4229 | No | 37 | No | 37 | 0 | 0 | 10 | No | 15528 | No | 15528 | 0 | 0 | 15528 | No | 21691 | 21691 | 1828 | 1828 | 24624 |  | 2022-04-01 |  | 2022-08-01 | Yes | 2024-02-02 |  | 2024-02-02 | No | 2024-03-29 |  | 2024-03-29 | No | 2024-11-01 |  | 2024-11-01 | No |  |  | 2026-02-02 |  | 0 | Yes | Yes | No | No
267 | 04 | 2022P | SON | 1 | Jenner Replace Culvert | Near Jenner, from south of Willow Creek Road to Burke Avenue. | Rehabilitate drainage systems at two locations. | 1663 | Yes | 1663 | 857 | 857 | 1796 | Yes | 2118 | No | 2118 | 0 | 0 | 2078 | No | 81 | No | 81 | 0 | 0 | 348 | Yes | 1684 | No | 1684 | 0 | 0 | 2013 | Yes | 831 | No | 831 | 0 | 0 | 840 | Yes | 4881 | No | 4881 | 0 | 0 | 4881 | No | 11258 | 11258 | 857 | 857 | 11956 |  | 2022-08-15 |  | 2022-12-15 | Yes | 2024-01-29 |  | 2024-01-29 | No | 2024-06-03 |  | 2024-06-03 | No | 2024-08-28 |  | 2024-08-28 | No |  |  | 2026-08-28 |  | 0 | No | Yes | Yes | No
268 | 04 | 2023K | SCL | 880 | SCL-880 Park Ave Bridge Rail Upgrade | In San Jose, at Park Avenue Overcrossing No 37-0127 (PM 1.73). | Upgrade bridge rails and upgrade facilities to Americans with Disabilities Act (ADA) standards. | 418 | Yes | 418 | 403 | 403 | 403 | No | 916 | Yes | 916 | 340 | 340 | 1311 | Yes | 57 | Yes | 57 | 4 | 4 | 59 | Yes | 529 | No | 529 | 0 | 0 | 1455 | Yes | 263 | No | 263 | 0 | 0 | 15 | No | 1539 | No | 1539 | 0 | 0 | 1183 | No | 3722 | 3722 | 747 | 747 | 4426 |  | 2021-11-01 | 2021-11-30 |  |  | 2023-02-01 |  | 2023-02-01 | No | 2023-03-01 |  | 2023-03-01 | No | 2023-09-01 |  | 2023-09-01 | No |  |  | 2024-09-02 |  | 0 | No | Yes | No | Yes
269 | 04 | 2024C | SM | 82 | HILLSDALE BLVD OC BRIDGE (#35-0198) BALUSTER RAILS UPGRADE AND REPLACE | In the city of San Mateo, at Hillsdale Boulevard Overcrossing No 35-0198 (PM 9.345). | Upgrade bridge rails and signals and upgrade facilities to Americans with Disabilities Act (ADA) standards. | 657 | Yes | 657 | 602 | 602 | 602 | No | 1550 | Yes | 1550 | 44 | 44 | 1714 | Yes | 69 | Yes | 69 | 1 | 1 | 101 | Yes | 746 | No | 746 | 0 | 0 | 936 | Yes | 76 | No | 76 | 0 | 0 | 15 | No | 1821 | No | 1821 | 0 | 0 | 1821 | No | 4919 | 4919 | 647 | 647 | 5189 |  | 2022-01-03 | 2022-02-23 |  |  | 2023-07-03 |  | 2023-07-03 | No | 2023-10-02 |  | 2023-10-02 | No | 2024-05-06 |  | 2024-05-06 | No |  |  | 2025-05-05 |  | 0 | No | No | No | No
270 | 04 | 2024F | SOL | 128 | Putah Creek, Bridge 23-0099 | Near Winters, at Putah Creek Bridge No 23-0099 (PM 0.72). | Rehabilitate bridges by upgrading bridge rails and overlaying bridge deck. | 801 | Yes | 801 | 760 | 760 | 1472 | Yes | 1936 | No | 1936 | 0 | 0 | 1828 | No | 140 | No | 140 | 0 | 0 | 95 | No | 1506 | No | 1506 | 0 | 0 | 1324 | No | 60 | No | 60 | 0 | 0 | 755 | Yes | 4587 | No | 4587 | 0 | 0 | 4587 | No | 9030 | 9030 | 760 | 760 | 10061 |  | 2022-10-03 |  | 2022-10-31 | No | 2024-01-25 |  | 2024-04-01 | No | 2024-02-01 |  | 2024-04-01 | No | 2024-09-09 |  | 2024-09-09 | No |  |  | 2025-09-30 |  | 0 | No | Yes | No | No
271 | 04 | 2024H | SM | 280 | NB I 280 SB SR-1 CONNECTOR | In Daly City, at northbound Route 280 to southbound Route 1 Connector No 35-0179G. | Seismic retrofit. | 651 | Yes | 651 | 0 | 0 | 650 | No | 1266 | No | 1266 | 0 | 0 | 1265 | No | 48 | No | 48 | 0 | 0 | 41 | No | 1298 | No | 1298 | 0 | 0 | 1533 | Yes | 7 | No | 7 | 0 | 0 | 0 | No | 1689 | No | 1689 | 0 | 0 | 718 | No | 4959 | 4959 | 0 | 0 | 4207 |  |  |  | 2024-03-01 |  |  |  | 2025-10-01 |  |  |  | 2026-02-02 |  |  |  | 2026-09-01 |  |  |  | 2027-12-01 |  | 0 | No | No | No | No
272 | 04 | 2025N | NAP | 121 | Minor Pavement Rehabilitation | In and near the city of Napa, from Route 29 to north of Vichy Avenue. | Rehabilitate pavement, upgrade signs and guardrail, rehabilitate drainage systems, upgrade facilities to Americans with Disabilities Act (ADA) standards, and construct sidewalks, high visibility crosswalks, curb ramps, Class 2 and 4 bike lanes, passive bicycle detection, transit islands, and green bikeway markings as complete streets elements. | 1140 | Yes | 1140 | 783 | 783 | 783 | No | 2535 | No | 2535 | 0 | 0 | 1873 | No | 3245 | No | 3245 | 0 | 0 | 2965 | No | 4120 | No | 4120 | 0 | 0 | 3331 | No | 1325 | No | 1325 | 0 | 0 | 1070 | No | 23942 | No | 23942 | 0 | 0 | 11037 | No | 36307 | 36307 | 783 | 783 | 21059 |  | 2022-06-30 | 2022-06-30 |  |  | 2023-07-21 |  | 2024-03-01 | Yes | 2023-08-04 |  | 2024-03-01 | Yes | 2024-02-01 |  | 2024-12-02 | Yes |  |  | 2026-12-07 |  | 0 | Yes | Yes | No | Yes
273 | 04 | 2026C | SCL | 101 | Route 101/680-Drainage Pump Plants | Near Morgan Hill, at Burnett Avenue and at Cochrane Road (PM R17.89); also in San Jose, on Route 680 at Alum Rock Avenue (PM M1.74). | Upgrade pump plants and increase storm water storage at the Alum Rock pump plant. | 713 | Yes | 713 | 672 | 672 | 672 | No | 2021 | Yes | 2021 | 301 | 301 | 2021 | No | 473 | Yes | 473 | 11 | 11 | 396 | No | 2830 | No | 2830 | 0 | 0 | 2808 | No | 33 | No | 33 | 0 | 0 | 33 | No | 9575 | No | 9575 | 0 | 0 | 7908 | No | 15645 | 15645 | 984 | 984 | 13838 |  | 2021-10-04 | 2021-09-20 |  |  | 2023-02-15 |  | 2023-03-08 | No | 2023-03-01 |  | 2023-03-15 | No | 2023-10-19 |  | 2023-10-24 | No |  |  | 2025-02-21 |  | 0 | No | No | No | Yes
274 | 04 | 2026F | SM | 82 | CAPM ON SR 82 | In and near South San Francisco, Colma, and Daly City, from Arroyo Drive to Route 280. | Rehabilitate pavement, upgrade facilities to Americans with Disabilities Act (ADA) standards, install bike lanes and separated bikeways, and upgrade guardrail. | 2550 | Yes | 2550 | 0 | 0 | 2544 | No | 3307 | No | 3307 | 0 | 0 | 3267 | No | 399 | No | 399 | 0 | 0 | 373 | No | 5676 | No | 5676 | 0 | 0 | 5488 | No | 1804 | No | 1804 | 0 | 0 | 1653 | No | 23972 | No | 23972 | 0 | 0 | 9922 | No | 37708 | 37708 | 0 | 0 | 23247 |  |  |  | 2024-03-27 |  |  |  | 2026-03-29 |  |  |  | 2026-03-31 |  |  |  | 2026-10-21 |  |  |  | 2027-12-17 |  | 0 | No | No | No | No
275 | 04 | 2026H | SF | 101 | 04-2Q460_SF 101-BRIDGE RAIL REPLACEMENT AND UPGRADE | In the City and County of San Francisco, at Twenty Third Street Overcrossing No 34-0035 (PM 3.37); also at Third Street Undercrossing No 34-0030S (PM 0.77). | Upgrade bridge rails. | 772 | Yes | 772 | 754 | 754 | 754 | No | 1255 | Yes | 1255 | 37 | 37 | 1295 | Yes | 125 | Yes | 125 | 0 | 0 | 124 | No | 1353 | No | 1353 | 0 | 0 | 1363 | Yes | 33 | No | 33 | 0 | 0 | 33 | No | 2750 | No | 2750 | 0 | 0 | 2750 | No | 6288 | 6288 | 791 | 791 | 6319 |  | 2021-12-01 | 2022-05-16 |  |  | 2023-07-01 |  | 2023-12-08 | Yes | 2023-07-01 |  | 2023-12-15 | Yes | 2024-03-01 |  | 2024-07-17 | Yes |  |  | 2025-03-01 |  | 0 | Yes | No | No | No
276 | 04 | 2027A | SON | 128 | SONOMA SR 128 PAVEMENT REHAB | Near Cloverdale, Geyserville, and Calistoga, from Mendocino County line to Napa County line. | Rehabilitate pavement, upgrade guardrail, and upgrade facilities to Americans with Disabilities Act (ADA) standards. | 3370 | Yes | 3370 | 0 | 0 | 3350 | No | 4892 | No | 4892 | 0 | 0 | 4902 | Yes | 151 | No | 151 | 0 | 0 | 62 | No | 3411 | No | 3411 | 0 | 0 | 3483 | Yes | 144 | No | 144 | 0 | 0 | 59 | No | 31271 | No | 31271 | 0 | 0 | 37866 | Yes | 43239 | 43239 | 0 | 0 | 49722 |  |  |  | 2024-10-01 |  |  |  | 2026-02-02 |  |  |  | 2026-03-16 |  |  |  | 2026-10-01 |  |  |  | 2028-12-29 |  | 0 | No | Yes | No | No
277 | 04 | 2027C | SOL | 29 | PAVEMENT PRESERVATION AND SAFETY IMPROVEMENTS | In Vallejo, from Route 80 to Napa County line (PM 0.0/5.955). | Rehabilitate pavement, upgrade facilities to Americans with Disabilities Act (ADA) standards, widen sidewalks, and construct 3.6 miles of Class 2 and 4 bikeways, curb extensions, Light Emitting Diode (LED) light fixtures, and green bikeway markings as complete streets elements. | 2481 | Yes | 2481 | 1794 | 1794 | 2283 | No | 3058 | No | 3058 | 0 | 0 | 2528 | No | 231 | No | 231 | 0 | 0 | 265 | Yes | 3616 | No | 3616 | 0 | 0 | 3325 | No | 200 | No | 200 | 0 | 0 | 10 | No | 26759 | No | 26759 | 0 | 0 | 24059 | No | 36345 | 36345 | 1794 | 1794 | 32470 |  | 2022-04-04 |  | 2023-01-16 | Yes | 2023-06-12 |  | 2023-06-12 | No | 2023-06-19 |  | 2023-06-30 | No | 2024-01-29 |  | 2023-12-15 | No |  |  | 2025-05-12 |  | 0 | Yes | No | No | No
278 | 04 | 2027D | SOL | 12 | PAVEMENT REHABILITATION | Near Suisun City, from 0.5 mile west of Walters Road to 0.5 mile west of Lambie Road/Shiloh Road. | Rehabilitate roadway and upgrade guardrail. | 2136 | Yes | 2136 | 1657 | 1657 | 2004 | No | 3198 | No | 3198 | 0 | 0 | 3231 | Yes | 68 | No | 68 | 0 | 0 | 68 | No | 3493 | No | 3493 | 0 | 0 | 3292 | No | 10 | No | 10 | 0 | 0 | 1560 | Yes | 23478 | No | 23478 | 0 | 0 | 13076 | No | 32383 | 32383 | 1657 | 1657 | 23231 |  | 2022-10-03 |  | 2022-11-07 | No | 2024-04-15 |  | 2024-04-15 | No | 2024-05-01 |  | 2024-05-01 | No | 2024-12-01 |  | 2024-12-01 | No |  |  | 2027-04-01 |  | 0 | No | Yes | No | Yes
279 | 04 | 2027F | CC | 4 | CAPITAL PREVENTATIVE MAINTENANCE | In and near Hercules, Martinez, and Concord, from San Pablo Avenue to east of Peralta Road Undercrossing. | Rehabilitate roadway, upgrade guardrail and signs, and upgrade facilities to Americans with Disabilities Act (ADA) standards. | 3324 | Yes | 3324 | 2709 | 2709 | 3609 | Yes | 4538 | Yes | 4538 | 0 | 0 | 4510 | No | 917 | Yes | 917 | 0 | 0 | 917 | No | 6228 | No | 6228 | 0 | 0 | 5893 | No | 29 | No | 29 | 0 | 0 | 111 | Yes | 45024 | No | 45024 | 0 | 0 | 51287 | Yes | 60060 | 60060 | 2709 | 2709 | 66327 |  | 2022-06-01 |  | 2022-07-07 | Yes | 2023-05-26 |  | 2023-05-26 | No | 2023-06-15 |  | 2023-06-15 | No | 2024-03-15 |  | 2024-03-15 | No |  |  | 2026-03-13 |  | 0 | Yes | Yes | No | No
280 | 04 | 2027G | ALA | 61 | PAVEMENT PRESERVATION | In the cities of San Leandro, Oakland, and Alameda, from Route 112 (Davis Street) to Encinal Avenue. | Rehabilitate pavement, upgrade guardrail, rehabilitate drainage systems, and upgrade facilities to Americans with Disabilities Act (ADA) standards. | 1530 | Yes | 1530 | 577 | 577 | 1555 | Yes | 2032 | No | 2032 | 0 | 0 | 2014 | No | 89 | No | 89 | 0 | 0 | 86 | No | 2597 | No | 2597 | 0 | 0 | 2535 | No | 200 | No | 200 | 0 | 0 | 200 | No | 16345 | No | 16345 | 0 | 0 | 16345 | No | 22793 | 22793 | 577 | 577 | 22735 |  | 2022-06-15 |  | 2022-08-26 | Yes | 2024-01-02 |  | 2024-05-30 | Yes | 2024-01-16 |  | 2024-06-13 | Yes | 2024-09-20 |  | 2025-03-12 | Yes |  |  | 2027-07-22 |  | 0 | Yes | No | No | No
281 | 04 | 2027J | ALA | 880 | INSTALL TOS/RM AND FIBERS | In Alameda, San Francisco, and San Mateo Counties, on Routes 80, 101, 880, and 980 at various locations. | Install and upgrade Transportation Management System (TMS) elements including Closed Circuit Television (CCTV) cameras, Vehicle Detection Systems (VDS), Changeable Message Signs (CMS), ramp meters, and fiber optic cable. (G13 Contingency). | 2155 | Yes | 2155 | 1401 | 1401 | 2695 | Yes | 10958 | No | 10958 | 0 | 0 | 11309 | Yes | 141 | No | 141 | 0 | 0 | 124 | No | 0 | No | 0 | 0 | 0 | 10108 | Yes | 63 | No | 63 | 0 | 0 | 63 | No | 0 | No | 0 | 0 | 0 | 85203 | Yes | 13317 | 13317 | 1401 | 1401 | 109502 |  | 2022-06-07 |  | 2022-07-29 | Yes | 2023-04-10 |  | 2023-04-30 | No | 2023-05-01 |  | 2023-05-31 | No | 2024-01-30 |  | 2024-02-04 | No |  |  | 2025-10-15 |  | 0 | Yes | Yes | Yes | Yes
282 | 04 | 2027P | NAP | 29 | Pavement Rehabilitation | In the city of Napa, from north of Napa River Bridge to south of Sierra Avenue. | Rehabilitate roadway, upgrade guardrail and Transportation Management System (TMS) elements, rehabilitate drainage systems, and upgrade facilities to Americans with Disabilities Act (ADA) standards. | 2454 | Yes | 2454 | 1485 | 1485 | 1485 | No | 0 | Yes | 0 | 0 | 0 | 2253 | Yes | 0 | Yes | 0 | 0 | 0 | 169 | Yes | 2488 | No | 2488 | 0 | 0 | 2446 | No | 107 | No | 107 | 0 | 0 | 90 | No | 23299 | No | 23299 | 0 | 0 | 23299 | No | 28348 | 28348 | 1485 | 1485 | 29742 |  | 2022-03-05 | 2022-04-20 |  |  | 2024-04-01 |  | 2024-02-23 | No | 2024-04-29 |  | 2024-03-01 | No | 2024-11-29 |  | 2024-11-29 | No |  |  | 2025-12-01 |  | 0 | No | Yes | No | Yes
283 | 04 | 2028B | ALA | Var | CCTV Technology Replacement | In various counties, on various routes at various locations. | Replace obsolete electronic components in existing Closed Circuit Television (CCTV) camera systems. | 365 | Yes | 365 | 306 | 306 | 557 | Yes | 1120 | Yes | 1120 | 0 | 0 | 1104 | No | 15 | Yes | 15 | 0 | 0 | 14 | No | 2700 | No | 2700 | 0 | 0 | 723 | No | 15 | No | 15 | 0 | 0 | 10 | No | 16650 | No | 16650 | 0 | 0 | 16662 | Yes | 20865 | 20865 | 306 | 306 | 19070 |  | 2021-12-31 |  | 2022-04-30 | Yes | 2023-07-01 |  | 2023-07-01 | No | 2023-08-01 |  | 2023-08-01 | No | 2024-04-15 |  | 2024-04-15 | No |  |  | 2027-04-14 |  | 0 | No | No | No | No
284 | 04 | 2028P | SON | 116 | SON 116 Bridge railing systems | Near Sebastopol, at Jones Creek Bridge No 20-0094 (PM 19.90), Blucher Creek Bridge No 20-0103 (PM 29.83) and Gossage Creek Bridge No 20-0104 (PM 33.37). | Upgrade bridge rails. | 1280 | Yes | 1280 | 361 | 361 | 1733 | Yes | 1780 | No | 1780 | 0 | 0 | 2322 | Yes | 170 | No | 170 | 0 | 0 | 226 | Yes | 1740 | No | 1740 | 0 | 0 | 2148 | Yes | 160 | No | 160 | 0 | 0 | 105 | No | 4310 | No | 4310 | 0 | 0 | 4310 | No | 9440 | 9440 | 361 | 361 | 10844 |  | 2023-02-01 |  | 2023-02-01 | No | 2024-04-05 |  | 2024-04-05 | No | 2024-05-01 |  | 2024-05-01 | No | 2025-01-17 |  | 2025-01-17 | No |  |  | 2026-08-31 |  | 0 | No | Yes | No | No
285 | 04 | 2028Q | SON | 121 | SON-121 Bridge railing upgrade | Near Schellville, at Yellow Creek Bridge No 20-0021 (PM 6.52) and Arroyo Seco Bridge No 20-0023 (PM 8.43). | Upgrade bridge rails. | 1750 | Yes | 1750 | 977 | 977 | 1742 | No | 2410 | No | 2410 | 0 | 0 | 2521 | Yes | 80 | No | 80 | 0 | 0 | 82 | Yes | 2370 | No | 2370 | 0 | 0 | 2234 | No | 190 | No | 190 | 0 | 0 | 10 | No | 7780 | No | 7780 | 0 | 0 | 7780 | No | 14580 | 14580 | 977 | 977 | 14369 |  | 2022-11-18 |  | 2022-11-18 | No | 2024-02-15 |  | 2024-02-15 | No | 2024-03-01 |  | 2024-03-01 | No | 2025-01-17 |  | 2025-01-17 | No |  |  | 2026-08-30 |  | 0 | No | No | No | No
286 | 04 | 2029C | SON | 101 | SON-101 Bridge rails at four locations | In and near Santa Rosa, at Mendocino Avenue Overcrossing No 20-0179 (PM 22.81), Fulton Road Overcrossing No 20-0200 (PM 25.90), Shiloh Road Overcrossing No 20-0202 (PM 27.62), and Limerick Lane Overcrossing No 20-0066 (PM 32.79). | Upgrade bridge rails. | 1528 | Yes | 1528 | 482 | 482 | 1471 | No | 1518 | No | 1518 | 0 | 0 | 1568 | Yes | 5 | No | 5 | 0 | 0 | 5 | No | 1484 | No | 1484 | 0 | 0 | 1472 | No | 252 | No | 252 | 0 | 0 | 32 | No | 8056 | No | 8056 | 0 | 0 | 8056 | No | 12843 | 12843 | 482 | 482 | 12604 |  | 2022-10-06 |  | 2022-10-06 | No | 2024-04-05 |  | 2024-04-05 | No | 2024-05-01 |  | 2024-05-01 | No | 2025-01-17 |  | 2025-01-17 | No |  |  | 2026-08-30 |  | 0 | No | No | No | No
287 | 04 | 2031T | ALA | 92 | ALA 92 CAPM | In Hayward, from west of San Mateo Hayward Bay Bridge Toll Station to Santa Clara Street. | Rehabilitate pavement and upgrade facilities to Americans with Disabilities Act (ADA) standards. | 1126 | Yes | 1126 | 0 | 0 | 1160 | Yes | 2460 | No | 2460 | 0 | 0 | 480 | No | 135 | No | 135 | 0 | 0 | 0 | No | 3335 | No | 3335 | 0 | 0 | 213 | No | 246 | No | 246 | 0 | 0 | 225 | No | 22870 | No | 22870 | 0 | 0 | 0 | No | 30172 | 30172 | 0 | 0 | 2078 |  |  |  | 2024-01-02 |  |  |  | 2025-04-01 |  |  |  | 2025-06-02 |  |  |  | 2026-01-02 |  |  |  | 2027-01-04 |  | 0 | No | No | No | No
288 | 04 | 2035D | MRN | 101 | CAPM | In and near Corte Madera, Larkspur, and San Rafael, from north of Nellen Avenue Undercrossing to south of Miller Creek Road. | Rehabilitate pavement and drainage systems, upgrade guardrail, and upgrade facilities to Americans with Disabilities Act (ADA) standards. | 1845 | Yes | 1845 | 0 | 0 | 1774 | No | 2907 | No | 2907 | 0 | 0 | 261 | No | 217 | No | 217 | 0 | 0 | 0 | No | 4132 | No | 4132 | 0 | 0 | 398 | No | 60 | No | 60 | 0 | 0 | 10 | No | 21571 | No | 21571 | 0 | 0 | 20088 | No | 30732 | 30732 | 0 | 0 | 22531 |  |  |  | 2024-05-01 |  |  |  | 2025-05-01 |  |  |  | 2025-06-02 |  |  |  | 2026-02-10 |  |  |  | 2028-03-01 |  | 0 | No | No | No | No
289 | 04 | 2804N | ALA | 580 | Bridge Health - Broadway-Richmond Blvd UC | In Oakland, at Broadway Richmond Boulevard Undercrossing No 33-0285. | Replace joint seals and overlay bridge deck with polyester concrete. | 649 | Yes | 649 | 0 | 0 | 564 | No | 1359 | No | 1359 | 0 | 0 | 621 | No | 54 | No | 54 | 0 | 0 | 0 | No | 1218 | No | 1218 | 0 | 0 | 718 | No | 6 | No | 6 | 0 | 0 | 5 | No | 6726 | No | 6726 | 0 | 0 | 0 | No | 10012 | 10012 | 0 | 0 | 1908 |  |  |  | 2024-08-26 |  |  |  | 2025-07-31 |  |  |  | 2025-09-29 |  |  |  | 2026-02-20 |  |  |  | 2026-12-01 |  | 0 | No | No | No | No
290 | 04 | 2904H | SCL | 280 | Pavement CAPM from Route 101/680 to Route 87 | In San Jose, from Route 680 to Route 87. | Rehabilitate pavement, upgrade facilities to Americans with Disabilities Act (ADA) standards, rehabilitate drainage systems, and upgrade guardrail and Transportation Management System (TMS) elements. | 1199 | Yes | 1199 | 1256 | 1256 | 1256 | Yes | 2307 | Yes | 2307 | 211 | 211 | 2711 | Yes | 20 | Yes | 20 | 2 | 2 | 6 | No | 2658 | No | 2658 | 0 | 0 | 2686 | Yes | 60 | No | 60 | 0 | 0 | 60 | No | 24968 | No | 24968 | 0 | 0 | 19322 | No | 31212 | 31212 | 1469 | 1469 | 26041 |  | 2022-03-01 | 2022-05-05 |  |  | 2023-04-13 |  | 2023-04-13 | No | 2023-05-01 |  | 2023-05-01 | No | 2023-11-20 |  | 2023-11-20 | No |  |  | 2024-11-20 |  | 0 | No | No | No | Yes
291 | 04 | 2904K | SF | 101 | 04-1Q820_SF 101-Roadway Rehab 3R | In the City and County of San Francisco, from San Mateo County line to Market Street. | Rehabilitate roadway, upgrade signs, concrete barrier, and Transportation Management System (TMS) elements, rehabilitate drainage, and upgrade facilities to Americans with Disabilities Act (ADA) standards. (G13 Contingency). | 2594 | Yes | 2594 | 1316 | 1316 | 2506 | No | 4500 | No | 4500 | 0 | 0 | 4306 | No | 223 | No | 223 | 0 | 0 | 195 | No | 0 | No | 0 | 0 | 0 | 6702 | Yes | 424 | No | 424 | 0 | 0 | 350 | No | 0 | No | 0 | 0 | 0 | 45556 | Yes | 7741 | 7741 | 1316 | 1316 | 59615 |  | 2022-11-01 |  | 2022-11-01 | No | 2024-01-02 |  | 2024-01-02 | No | 2024-02-01 |  | 2024-02-01 | No | 2024-10-01 |  | 2024-10-01 | No |  |  | 2026-06-01 |  | 0 | No | Yes | No | No
292 | 04 | 2904N | MRN | 131 | MARIN SR 131, CAPM | In and near Tiburon, from Route 101 to Main Street (PM 0.0/4.392). | Rehabilitate pavement, upgrade guardrail, rehabilitate drainage systems, upgrade facilities to Americans with Disabilities Act (ADA) standards, and construct Class 2 and Class 4 bikeways as complete streets elements. | 2193 | Yes | 2193 | 1233 | 1233 | 2508 | Yes | 3842 | No | 3842 | 0 | 0 | 3830 | No | 134 | No | 134 | 0 | 0 | 151 | Yes | 3341 | No | 3341 | 0 | 0 | 3129 | No | 611 | No | 611 | 0 | 0 | 531 | No | 12762 | No | 12762 | 0 | 0 | 10421 | No | 22883 | 22883 | 1233 | 1233 | 20570 |  | 2022-10-03 |  | 2023-03-15 | Yes | 2024-01-02 |  | 2024-01-02 | No | 2024-02-05 |  | 2024-06-05 | Yes | 2024-07-25 |  | 2024-07-25 | No |  |  | 2025-06-02 |  | 0 | Yes | No | Yes | No
293 | 04 | 2905B | ALA | 580 | Rehab ALA 580 | In and near Dublin and Castro Valley, from Route 680 to Route 238. | Rehabilitate pavement, construct concrete barrier, upgrade signs, guardrail, and Transportation Management System (TMS) elements, and upgrade facilities to Americans with Disabilities Act (ADA) standards. (Additional contributions from Proposition 1B). | 1973 | Yes | 1973 | 1704 | 1704 | 1704 | No | 3591 | No | 3591 | 0 | 0 | 3364 | No | 180 | No | 180 | 0 | 0 | 178 | No | 4165 | No | 4165 | 0 | 0 | 4093 | No | 5 | No | 5 | 0 | 0 | 50 | Yes | 63607 | No | 63607 | 0 | 0 | 83000 | Yes | 73521 | 73521 | 1704 | 1704 | 92389 |  | 2022-03-01 | 2022-06-22 |  |  | 2023-05-01 |  | 2023-04-14 | No | 2023-06-01 |  | 2023-06-01 | No | 2024-01-02 |  | 2024-01-15 | No |  |  | 2026-05-01 |  | 0 | No | Yes | No | Yes
294 | 04 | 2905H | ALA | 680 | i-680 Express Lanes/Rehab Project | IN ALAMEDA AND CONTRA COSTA COUNTIES AT SUNOL AND IN SAN RAMON BETWEEN 0.4 MILE SOUTH OF CALAVERAS ROAD UNDERCROSSING AND 0.9 MILE NORTH OF ALCOSTA BLVD.OVERCROSSING | CONSTRUCT EXPRESS LANES AND REHABILITATE ROADWAY. | 0 | No | 0 | 0 | 0 | 893 | Yes | 0 | No | 0 | 113 | 0 | 2093 | Yes | 0 | No | 0 | 0 | 0 | 0 | No | 0 | No | 0 | 0 | 0 | 15080 | Yes | 0 | No | 0 | 0 | 0 | 0 | No | 0 | No | 0 | 0 | 0 | 0 | No | 0 | 0 | 113 | 0 | 18066 | [6 empty] | 2021-10-08 |  |  |  | 2021-10-08 |  |  |  |  | 2022-09-29 |  |  |  | 2028-10-12 |  | 0 | No | Yes | No | No
295 | 04 | 2906A | CC | 680 | INSTALL TOS, RM & FIBER ON ROUTES 580, 680 & 780 IN ALA, CC & SOL | In Alameda, Contra Costa, and Solano Counties, on Routes 580, 680, and 780 at various locations. | Install and upgrade fiber optic cable, ramp metering systems, and Transportation Management System (TMS) elements, and widen ramps to provide High-Occupancy Vehicle (HOV) bypass ramp lanes. (G13 Contingency). | 5475 | Yes | 5475 | 2438 | 2438 | 5971 | Yes | 9620 | Yes | 9620 | 0 | 0 | 8994 | No | 632 | Yes | 632 | 0 | 0 | 624 | No | 0 | No | 0 | 0 | 0 | 7691 | Yes | 312 | No | 312 | 0 | 0 | 169 | No | 0 | No | 0 | 0 | 0 | 100331 | Yes | 16039 | 16039 | 2438 | 2438 | 123780 |  | 2022-06-01 |  | 2022-07-15 | Yes | 2024-02-01 |  | 2024-03-01 | No | 2024-03-01 |  | 2024-05-01 | No | 2024-09-01 |  | 2025-01-15 | Yes |  |  | 2027-12-30 |  | 0 | Yes | Yes | No | No
296 | 04 | 2906F | MRN | 101 | Corte Madera Bridge Maintenance | In Larkspur, at Corte Madera Creek Bridge No 27-0008K. | Patch deck spalls, replace joint seal, treat bridge deck with methacrylate and overlay with polyester concrete, place galvanic anode jacket system around columns, and build up bridge approaches. | 955 | Yes | 955 | 0 | 0 | 864 | No | 1626 | No | 1626 | 0 | 0 | 1538 | No | 113 | No | 113 | 0 | 0 | 110 | No | 2130 | No | 2130 | 0 | 0 | 2141 | Yes | 91 | No | 91 | 0 | 0 | 78 | No | 2696 | No | 2696 | 0 | 0 | 2320 | No | 7611 | 7611 | 0 | 0 | 7051 |  |  |  | 2024-04-01 |  |  |  | 2025-09-15 |  |  |  | 2025-10-10 |  |  |  | 2026-03-24 |  |  |  | 2027-01-25 |  | 0 | No | No | No | No
297 | 04 | 2910M | MRN | 1 | Marin Hwy 1 Combined Culvert replacement | Near Stinson Beach, Point Reyes, and Tomales, from north of Calle Del Arroyo to south of Tomales Petaluma Road at various locations. | Rehabilitate drainage systems. | 4000 | No | 4000 | 1322 | 1322 | 1325 | No | 3350 | No | 3350 | 0 | 0 | 683 | No | 1150 | No | 1150 | 0 | 0 | 0 | No | 3530 | No | 3530 | 0 | 0 | 14 | No | 1729 | No | 1729 | 0 | 0 | 0 | No | 10129 | No | 10129 | 0 | 0 | 0 | No | 23888 | 23888 | 1322 | 1322 | 2022 |  |  |  | 2023-05-05 |  |  |  | 2024-04-15 |  |  |  | 2024-05-13 |  |  |  | 2025-02-27 |  |  |  | 2027-04-15 |  | 0 | Yes | Yes | No | No
298 | 04 | 8195B | SOL | 37 | BRIDGE DECK PROGRAM | In Vallejo, at Napa RIver Bridge No 23-0064. | Apply polyester concrete overlay to bridge deck. (Bridge Deck Preservation). | 136 | Yes | 136 | 135 | 135 | 138 | Yes | 4395 | Yes | 1930 | 31 | 31 | 1950 | No | 68 | Yes | 68 | 1 | 1 | 1 | No | 3530 | No | 3530 | 0 | 0 | 3536 | Yes | 0 | No | 0 | 0 | 0 | 5 | Yes | 11100 | No | 11100 | 0 | 0 | 11100 | No | 19229 | 16764 | 167 | 167 | 16730 |  |  |  | 2022-08-15 |  |  |  | 2023-04-06 |  |  |  | 2023-06-16 |  |  |  | 2023-09-22 |  |  |  | 2024-09-23 |  | 0 | No | No | No | Yes
299 | 04 | 8315N | SOL | 080 | Dan Wilson Creek Br. | NEAR FAIRFIELD, AT DAN WILSON CREEK BRIDGE NO. 23-0006. REHABILITATE BRIDGE. | BRIDGE DECK REPLACEMENT | 1520 | No | 1520 | 1442 | 1442 | 1442 | No | 1011 | Yes | 1011 | 965 | 965 | 965 | No | 100 | Yes | 100 | 17 | 17 | 17 | No | 906 | Yes | 906 | 806 | 806 | 953 | Yes | 0 | No | 0 | 9 | 9 | 154 | Yes | 3325 | Yes | 3325 | 2834 | 2834 | 3325 | No | 6862 | 6862 | 6073 | 6073 | 6856 |  |  | 2017-02-22 |  |  |  | 2018-01-05 |  |  |  | 2018-02-01 |  |  |  | 2019-06-28 |  |  |  |  | 2023-01-20 |  | 3325 | No | No | No | Yes
300 | 05 | 0040C | SLO | 101 | North Paso Robles Mitigation Planting | In San Luis Obispo County near Paso Robles from 0.1 mile south to 0.1 mile north of San Marcos Creek Bridge and from 0.1 mile south to 0.1 mile north of South San Miguel Undercrossing. | Landscape mitigation. | 0 | No | 0 | 0 | 0 | 0 | No | 223 | Yes | 223 | 119 | 119 | 119 | No | 28 | Yes | 28 | 6 | 6 | 29 | Yes | 479 | Yes | 479 | 105 | 105 | 542 | Yes | 0 | No | 0 | 0 | 0 | 0 | No | 267 | Yes | 267 | 171 | 171 | 270 | Yes | 997 | 997 | 401 | 401 | 960 |  | 2013-09-04 | 2013-09-04 |  |  | 2019-03-15 | 2019-03-06 |  |  | 2019-06-03 | 2019-05-30 |  |  | 2019-11-18 | 2020-11-01 |  |  |  |  | 2024-04-30 |  | 142 | No | No | No | No
301 | 05 | 0072 | SLO | 1 | Toro Creek Bridge replacement | In Morro Bay, at Toro Creek Bridge No49-0068R. | Replace bridge. | 2343 | Yes | 2343 | 1575 | 1575 | 1575 | No | 2300 | Yes | 2300 | 2100 | 2100 | 2100 | No | 275 | Yes | 275 | 219 | 219 | 287 | Yes | 2804 | Yes | 2804 | 408 | 408 | 2335 | No | 4321 | No | 4321 | 1647 | 1647 | 4324 | Yes | 6613 | Yes | 6613 | 1200 | 1200 | 6613 | No | 18656 | 18656 | 7149 | 7149 | 17234 |  | 2018-06-18 | 2018-06-26 |  |  | 2020-04-17 | 2020-10-12 |  |  | 2020-06-29 | 2020-10-12 |  |  | 2021-02-04 | 2021-04-01 |  |  |  |  | 2024-06-19 |  | 6613 | No | No | No | Yes
302 | 05 | 0072A | SLO | 1 | Old Creek Bridge replacement | Near Morro Bay, at Old Creek Bridge No 49-0070R. | Replace bridge. | 2187 | Yes | 2187 | 1693 | 1693 | 1693 | No | 1900 | Yes | 1900 | 1750 | 1750 | 1750 | No | 200 | Yes | 200 | 64 | 64 | 89 | No | 3163 | Yes | 3163 | 338 | 338 | 2840 | No | 450 | No | 450 | 98 | 98 | 111 | No | 9331 | Yes | 9331 | 956 | 956 | 9331 | No | 17231 | 17231 | 4899 | 4899 | 15814 |  | 2017-11-02 | 2018-05-15 |  |  | 2020-01-02 | 2021-03-09 |  |  | 2020-04-28 | 2021-04-14 |  |  | 2020-11-13 | 2021-11-18 |  |  |  |  | 2024-03-14 |  | 9331 | No | No | No | Yes
303 | 05 | 0072B | SLO | 58 | Trout Creek Bridge replacement | Near Santa Margarita, at Trout Creek Bridge No 49-0091. | Replace bridge. | 2167 | Yes | 2167 | 1239 | 1239 | 1239 | No | 2500 | Yes | 2500 | 2160 | 2160 | 2160 | No | 210 | Yes | 210 | 79 | 79 | 215 | Yes | 2702 | Yes | 2702 | 1407 | 1407 | 2032 | No | 308 | No | 308 | 40 | 40 | 44 | No | 5215 | Yes | 5215 | 4660 | 4660 | 5215 | No | 13102 | 13102 | 9585 | 9585 | 10905 |  | 2017-11-01 | 2017-10-31 |  |  | 2019-12-02 | 2020-01-08 |  |  | 2020-01-08 | 2020-01-08 |  |  | 2020-08-12 | 2020-07-17 |  |  |  |  | 2022-12-30 |  | 5215 | No | No | No | Yes
304 | 05 | 0335 | SB | 192 | Arroyo Paredon Landscape Mitigation Planting | Near Carpinteria, at Arroyo Parida Creek Bridge No 51-113. | Environmental mitigation for emergency bridge replacement project EA 1J670. | 3 | No | 3 | 958 | 958 | 958 | Yes | 5146 | Yes | 5146 | 4699 | 4699 | 4699 | No | 692 | Yes | 692 | 441 | 441 | 480 | No | 600 | Yes | 600 | 97 | 97 | 549 | No | 381 | No | 381 | 217 | 214 | 337 | No | 245 | Yes | 245 | 153 | 153 | 300 | Yes | 7067 | 7067 | 6565 | 6562 | 7323 |  | 2009-06-29 | 2009-06-29 |  |  | 2019-09-03 | 2019-10-24 |  |  | 2020-01-21 | 2020-03-12 |  |  | 2020-08-07 | 2020-12-18 |  |  |  |  | 2024-04-26 |  | 232 | No | No | No | No
305 | 05 | 0900A | MON | 156 | Castroville Overhead | Near Castroville, from Route 183 to Castroville Boulevard at Bridge No 44-0033L. | Upgrade bridge railing and widen overhead. | 70 | No | 70 | 4 | 4 | 4 | No | 2880 | Yes | 2880 | 2727 | 2727 | 2727 | No | 198 | Yes | 198 | 156 | 156 | 265 | Yes | 2000 | Yes | 2000 | 335 | 335 | 1673 | No | 293 | No | 293 | 58 | 58 | 128 | No | 7007 | Yes | 7007 | 1073 | 1073 | 7007 | No | 12448 | 12448 | 4353 | 4353 | 11804 |  | 2014-09-02 | 2014-09-02 |  |  | 2020-08-03 | 2020-10-28 |  |  | 2020-10-05 | 2021-02-24 |  |  | 2021-04-07 | 2022-01-06 |  |  |  |  | 2023-07-03 |  | 7007 | No | No | No | No
306 | 05 | 1501Y | SB | 1 | Salsipuedes Biological Monitoring | Near Lompoc, at the Salsipuedes Creek Bridge No 51-0095. | Biological monitoring mitigation for project EA 0A050. | 0 | No | 0 | 0 | 0 | 0 | No | 0 | No | 0 | 0 | 0 | 0 | No | 0 | No | 0 | 0 | 0 | 0 | No | 100 | Yes | 100 | 11 | 11 | 103 | Yes | 0 | No | 0 | 0 | 0 | 0 | No | 0 | No | 0 | 0 | 0 | 0 | No | 100 | 100 | 11 | 11 | 103 |  | 2015-11-02 | 2015-11-02 |  |  | 2017-12-13 | 2017-12-13 |  |  | 2021-05-03 | 2020-10-15 |  |  | 2021-08-01 | 2021-03-01 | [6 empty] | 1 | No | No | No | No
307 | 05 | 1967 | SCR | 1 | DAVENPORT CULVERT REPLACEMENT | Near Davenport, from 1.4 miles north of Swanton Road to 0.6 mile south of Waddell Creek. | Replace and upgrade existing Corrugated Metal Pipe (CMP) culverts with Reinforced Concrete Pipe (RCP) culverts. | 1114 | Yes | 1114 | 918 | 918 | 918 | No | 1940 | Yes | 1940 | 1145 | 1145 | 1145 | No | 344 | Yes | 344 | 153 | 153 | 275 | No | 1597 | Yes | 1597 | 80 | 80 | 1751 | Yes | 262 | No | 262 | 98 | 98 | 135 | No | 6695 | Yes | 6695 | 602 | 602 | 6695 | No | 11952 | 11952 | 2996 | 2996 | 10919 |  | 2019-10-28 | 2019-10-24 |  |  | 2021-04-12 | 2021-07-20 |  |  | 2021-08-12 | 2021-07-26 |  |  | 2021-09-17 | 2022-03-22 |  |  |  |  | 2024-03-25 |  | 6695 | No | No | No | No
308 | 05 | 2386 | SB | 217 | San Jose Creek Bridge Replacement | Near Goleta, from 0.1 mile south to 0.4 mile north of San Jose Creek Bridge No 51-0217. | Replace bridge. | 3887 | Yes | 3887 | 3843 | 3843 | 3843 | No | 3459 | Yes | 3459 | 2271 | 2271 | 3423 | No | 156 | Yes | 156 | 84 | 84 | 158 | Yes | 6782 | No | 6782 | 0 | 0 | 5729 | No | 833 | No | 833 | 40 | 40 | 833 | No | 27157 | No | 27157 | 0 | 0 | 21582 | No | 42274 | 42274 | 6238 | 6238 | 35568 | 2021-01-28 | 2020-09-03 | 2020-09-03 |  |  | 2022-04-08 |  | 2022-06-16 | No | 2022-04-28 |  | 2022-07-18 | Yes | 2023-01-18 |  | 2023-05-01 | Yes |  |  | 2025-10-23 |  | 0 | Yes | No | No | No
309 | 05 | 2391 | SB | 154 | Alamo Pintado Ped Bridge | Near Los Olivos, at Alamo Pintado Pedestrian Bridge No 51-0076Y. | Replace bridge. | 1710 | Yes | 1710 | 1688 | 1688 | 1688 | No | 2130 | Yes | 2130 | 1378 | 1378 | 1879 | No | 50 | Yes | 50 | 31 | 31 | 70 | Yes | 1810 | No | 1810 | 0 | 0 | 1769 | No | 200 | No | 200 | 22 | 22 | 151 | No | 3800 | No | 3800 | 0 | 0 | 3819 | Yes | 9700 | 9700 | 3119 | 3119 | 9376 |  | 2020-01-15 | 2021-01-27 |  |  | 2021-09-15 |  | 2022-07-12 | Yes | 2022-01-15 |  | 2022-07-22 | Yes | 2022-09-01 |  | 2022-12-12 | Yes |  |  | 2024-12-20 |  | 0 | Yes | No | No | No
310 | 05 | 2392 | SB | 154 | Cold Spring Bridge Maintenance Inspection Access | Near Lake Cachuma, at Cold Spring Canyon Bridge No 51-0037. | Install inspection access system below bridge and paint structure. | 1110 | Yes | 1110 | 382 | 382 | 382 | No | 1740 | Yes | 1740 | 554 | 554 | 554 | No | 75 | Yes | 75 | 8 | 8 | 33 | No | 3880 | Yes | 3880 | 1192 | 1192 | 2562 | No | 50 | No | 50 | 0 | 0 | 0 | No | 8546 | Yes | 8546 | 6502 | 6502 | 8546 | No | 15401 | 15401 | 8638 | 8638 | 12077 | 2018-12-06 | 2018-11-09 | 2018-11-09 |  |  | 2019-08-15 | 2019-12-20 |  |  | 2020-01-15 | 2020-06-22 |  |  | 2020-08-03 | 2020-12-15 |  |  |  |  | 2023-07-14 |  | 8545 | No | No | No | No
311 | 05 | 2448 | SB | 101 | Refugio Bridge Replacement | Near Goleta, from 0.6 mile south and 0.4 mile north of Refugio Road Undercrossing No 51-0215L/R and Canada del Refugio No 51-0030S. | Replace two bridges and upgrade bridge railing on one bridge. | 3610 | Yes | 3610 | 3364 | 3364 | 3364 | No | 6630 | Yes | 6630 | 1791 | 1791 | 6431 | No | 320 | Yes | 320 | 127 | 127 | 260 | No | 11200 | No | 11200 | 0 | 0 | 10752 | No | 622 | No | 622 | 32 | 32 | 622 | No | 42500 | No | 42500 | 0 | 0 | 40343 | No | 64882 | 64882 | 5314 | 5314 | 61772 | 2021-06-23 | 2021-02-05 | 2021-02-05 |  |  | 2023-01-17 |  | 2023-03-01 | No | 2023-03-16 |  | 2023-06-14 | No | 2023-11-01 |  | 2024-02-12 | Yes |  |  | 2027-10-21 |  | 0 | No | No | No | No
312 | 05 | 2474 | MON | 101 | Salinas Rehab | On Route 101 in Monterey County in the City of Salinas between East Market Street Overcrossing and 0.3 Miles South of Russell/Espinosa Road | ROADWAY REHABILITATION | 806 | No | 806 | 805 | 805 | 805 | No | 2466 | Yes | 2466 | 2434 | 2434 | 2434 | No | 180 | Yes | 180 | 24 | 24 | 24 | No | 6789 | Yes | 6789 | 6430 | 6430 | 7152 | Yes | 80 | No | 80 | 17 | 17 | 17 | No | 41249 | Yes | 41249 | 39171 | 39171 | 41249 | No | 51570 | 51570 | 48881 | 48881 | 51681 |  |  | 2015-12-01 |  |  |  | 2017-11-20 |  |  |  | 2018-06-26 |  |  |  | 2019-01-07 |  |  |  |  | 2022-08-31 |  | 41248 | No | No | No | No
313 | 05 | 2522 | SB | 101 | 101/135 Bridge Replacement | In Los Alamos, from 0.3 mile south to 0.3 mile north of Route 101/135 Separation No 51-0073L/R; also on Route 135 (PM 0.1 ). | Replace bridges. | 915 | Yes | 915 | 750 | 750 | 750 | No | 2360 | Yes | 2360 | 2302 | 2302 | 2302 | No | 250 | Yes | 250 | 218 | 218 | 284 | Yes | 3500 | Yes | 3500 | 1986 | 1986 | 4246 | Yes | 30 | No | 30 | 24 | 24 | 15 | No | 12701 | Yes | 12701 | 6769 | 6769 | 12701 | No | 19756 | 19756 | 12049 | 12049 | 20298 |  | 2017-12-01 | 2017-12-15 |  |  | 2019-07-15 | 2020-05-13 |  |  | 2019-08-15 | 2020-06-18 |  |  | 2020-03-16 | 2020-12-15 |  |  |  |  | 2023-05-30 |  | 12701 | Yes | Yes | No | No
314 | 05 | 2548 | MON | 101 | King City Combined Projects | In Monterey County, in and near King City from 0.2 miles South of Wild Horse Road (PM R36.9) to Teague Avenue (PM47.7) | Pavement Rehabilitation, Seismic Retrofit with widening and median barrier | 2403 | No | 2403 | 2236 | 2236 | 2237 | No | 9110 | Yes | 9110 | 7464 | 7464 | 7464 | No | 356 | Yes | 356 | 222 | 222 | 223 | No | 16851 | Yes | 16851 | 9955 | 9955 | 17437 | Yes | 6705 | No | 6705 | 3565 | 3565 | 3020 | No | 88898 | Yes | 88898 | 56457 | 56457 | 88898 | No | 124323 | 124323 | 79899 | 79899 | 119279 | [10 empty] | 2018-06-25 |  |  |  | 2019-02-11 |  |  |  |  | 2023-06-01 |  | 88897 | No | No | No | No
315 | 05 | 2561 | SB | 101 | Nojoqui Creek Bridge (51-0018) Railing Upgrade | Near Buellton, from 0.1 mile south of Nojoqui Creek Bridge No 51-0018L/R to 0.3 mile south of Santa Rosa Road Overcrossing. | Bridge rail replacement and widening. | 1266 | Yes | 1266 | 912 | 912 | 912 | No | 1789 | Yes | 1789 | 1685 | 1685 | 1685 | No | 211 | Yes | 211 | 74 | 74 | 185 | No | 2018 | Yes | 2018 | 619 | 619 | 2017 | No | 99 | No | 99 | 16 | 16 | 25 | No | 6486 | Yes | 6486 | 1176 | 1176 | 6486 | No | 11869 | 11869 | 4482 | 4482 | 11310 |  | 2018-08-29 | 2018-08-17 |  |  | 2019-11-01 | 2020-02-19 |  |  | 2020-01-29 | 2020-03-20 |  |  | 2020-07-15 | 2020-09-21 |  |  |  |  | 2025-08-29 |  | 6486 | No | No | No | No
316 | 05 | 2563 | SB | 1 | Route 1/San Antonio Creek Bridge Scour Mitigation | Near Lompoc, at San Antonio Creek Bridge No 51-0237L/R. | Bridge scour mitigation. | 1050 | Yes | 1050 | 839 | 839 | 839 | No | 1692 | Yes | 1692 | 488 | 488 | 488 | No | 99 | Yes | 99 | 15 | 15 | 70 | No | 1106 | Yes | 1106 | 56 | 56 | 1319 | Yes | 83 | No | 83 | 11 | 11 | 24 | No | 599 | Yes | 599 | 122 | 122 | 599 | No | 4629 | 4629 | 1531 | 1531 | 3339 |  | 2019-06-24 | 2019-06-24 |  |  | 2021-02-19 | 2021-02-01 |  |  | 2021-07-12 | 2021-06-22 |  |  | 2022-01-07 | 2021-11-30 |  |  |  |  | 2023-05-09 |  | 599 | No | No | No | No
317 | 05 | 2629 | SB | 135 | Santa Maria CAPM | In and near Santa Maria, from Lakeview Road to Route 101. | Upgrade Americans with Disabilities Act (ADA) curb ramps, cold plane pavement, and place Rubberized Hot Mix Asphalt (RHMA) pavement. | 0 | No | 0 | 0 | 0 | 0 | No | 2011 | Yes | 2011 | 1898 | 1898 | 1898 | No | 1832 | Yes | 1832 | 1018 | 1018 | 1092 | No | 2396 | Yes | 2396 | 588 | 588 | 2222 | No | 378 | No | 378 | 135 | 135 | 189 | No | 13945 | Yes | 13945 | 7482 | 7482 | 13945 | No | 20562 | 20562 | 11121 | 11121 | 19346 | 2018-10-17 | 2017-06-16 | 2017-06-16 |  |  | 2020-09-30 | 2021-04-01 |  |  | 2020-11-19 | 2021-04-06 |  |  | 2021-05-24 | 2021-10-19 |  |  |  |  | 2022-11-30 |  | 13945 | No | No | No | No
318 | 05 | 2630 | SLO | 1 | Pismo Beach CAPM | In and near Pismo Beach, from Gracia Way to North Pismo (Route 101/Route 1) Separation. | Upgrade Americans with Disabilities Act (ADA) curb ramps, cold plane pavement, place Rubberized Hot Mix Asphalt (RHMA) pavement and widen shoulders and construct bike lanes as complete streets elements. | 1156 | Yes | 1156 | 822 | 822 | 822 | No | 2126 | Yes | 2126 | 1993 | 1993 | 2517 | Yes | 1670 | Yes | 1670 | 491 | 491 | 1289 | No | 2530 | No | 2530 | 0 | 0 | 2312 | No | 468 | No | 468 | 140 | 140 | 240 | No | 11603 | No | 11603 | 0 | 0 | 11148 | No | 19553 | 19553 | 3446 | 3446 | 18328 |  | 2018-12-03 | 2018-12-03 |  |  | 2022-04-06 | 2022-06-29 |  |  | 2022-04-06 | 2022-06-30 |  |  | 2022-08-23 |  | 2022-12-08 | Yes |  |  | 2023-10-02 |  | 0 | Yes | Yes | Yes | Yes
319 | 05 | 2631 | MON | 68 | Pacific Grove CAPM | In and near Pacific Grove and Monterey, from Forest Avenue to Route 1. | Upgrade Americans with Disabilities Act (ADA) curb ramps, cold plane pavement and place Rubberized Hot Mix Asphalt (RHMA) pavement. | 482 | Yes | 482 | 338 | 338 | 338 | No | 1638 | Yes | 1638 | 905 | 905 | 905 | No | 312 | Yes | 312 | 143 | 143 | 298 | No | 1710 | Yes | 1710 | 273 | 273 | 1670 | No | 103 | No | 103 | 20 | 20 | 20 | No | 6384 | Yes | 6384 | 2644 | 2644 | 6384 | No | 10629 | 10629 | 4323 | 4323 | 9615 |  | 2019-03-11 | 2019-03-11 |  |  | 2020-12-08 | 2021-06-28 |  |  | 2021-01-08 | 2021-06-30 |  |  | 2021-08-10 | 2021-11-24 |  |  |  |  | 2023-07-10 |  | 6383 | No | No | No | Yes
320 | 05 | 2632 | SB | 246 | Lompoc CAPM | In Lompoc, at combined segment of Route 246 and Route 1, on Route 246, from 0.3 mile west of V Street to H Street (PM 8.393/9.55); also on Route 1, from H Street to 12th Street (PM 19.3/20.6). | Upgrade Americans with Disabilities Act (ADA) curb ramps, cold plane pavement and place Hot Mix Asphalt (HMA) pavement. | 0 | No | 0 | 0 | 0 | 0 | No | 3630 | Yes | 3630 | 3055 | 3055 | 3504 | No | 2460 | Yes | 2460 | 389 | 389 | 868 | No | 2047 | Yes | 2047 | 0 | 0 | 2116 | Yes | 563 | No | 563 | 277 | 277 | 340 | No | 9278 | Yes | 9278 | 0 | 0 | 8587 | No | 17978 | 17978 | 3721 | 3721 | 15415 |  | 2017-04-24 | 2017-04-24 |  |  | 2021-10-25 | 2021-12-10 |  |  | 2021-12-15 | 2021-12-15 |  |  | 2022-07-27 |  | 2022-07-27 | No |  |  | 2023-11-15 |  | 0 | No | No | No | No
321 | 05 | 2649 | SB | 101 | San Jose Ck Bridge replacement | In Goleta, from Route 217 to 0.3 mile north of San Jose Creek Bridge No 51-0163L/R. | Replace bridges. (G13 Contingency). | 1400 | Yes | 1400 | 1347 | 1347 | 1347 | No | 2730 | Yes | 2730 | 1757 | 1757 | 2910 | Yes | 72 | Yes | 72 | 35 | 35 | 80 | Yes | 0 | No | 0 | 0 | 0 | 4405 | Yes | 168 | No | 168 | 55 | 55 | 83 | No | 0 | No | 0 | 0 | 0 | 21900 | Yes | 4370 | 4370 | 3194 | 3194 | 30725 |  | 2020-04-15 | 2020-10-08 |  |  | 2021-06-28 | 2022-02-14 |  |  | 2021-09-28 | 2022-06-28 |  |  | 2022-06-10 |  | 2023-01-26 | Yes |  |  | 2026-12-15 |  | 0 | Yes | Yes | No | No
322 | 05 | 2650 | SLO | 1 | Santa Maria River Bridge Replacement | Near Guadalupe, at the Santa Maria River Bridge No 49-0042; also in Santa Barbara County (PM 50.3/50.6). | The bridge is scour critical and needs to be replaced. The existing bridge will be used for traffic handling during construction and then demolished. The highway will need to be realigned as a result of the new bridge location. The new bridge will provide standard lane and shoulder widths and include a protected walkway. | 2523 | Yes | 2523 | 2493 | 2493 | 2493 | No | 3718 | Yes | 3718 | 1678 | 1678 | 3809 | Yes | 455 | Yes | 455 | 106 | 106 | 414 | No | 9660 | No | 9660 | 0 | 0 | 5786 | No | 1030 | No | 1030 | 141 | 141 | 1030 | No | 33880 | No | 33880 | 0 | 0 | 33262 | No | 51266 | 51266 | 4418 | 4418 | 46794 | 2021-03-25 | 2020-12-09 | 2020-12-09 |  |  | 2022-08-15 |  | 2023-04-14 | Yes | 2023-01-03 |  | 2023-05-15 | Yes | 2023-10-02 |  | 2024-02-15 | Yes |  |  | 2027-06-25 |  | 0 | No | No | No | No
323 | 05 | 2651 | SB | 154 | Rehab Primavera & La Colina Bridges | In the city of Santa Barbara, from La Colina Road Undercrossing (UC) No 51-0256 to Primavera Road UC No 51-0257. | Upgrade bridge railing and reconstruct abutment for bridge rehabilitation. | 928 | Yes | 928 | 241 | 241 | 241 | No | 2135 | Yes | 2135 | 1644 | 1644 | 1644 | No | 52 | Yes | 52 | 19 | 19 | 62 | Yes | 1956 | Yes | 1956 | 307 | 307 | 2025 | Yes | 3 | No | 3 | 0 | 0 | 0 | No | 5509 | Yes | 5509 | 1607 | 1607 | 5509 | No | 10583 | 10583 | 3818 | 3818 | 9481 |  | 2019-04-29 | 2019-04-29 |  |  | 2021-04-16 | 2021-04-29 |  |  | 2021-07-01 | 2021-06-24 |  |  | 2022-02-28 | 2021-12-09 |  |  |  |  | 2024-03-11 |  | 5509 | No | No | No | No
324 | 05 | 2654 | MON | 1 | Garrapata Creek Bridge Rehab | Near Carmel-By-The Sea, at Garrapata Creek No 44-0018. | Rehabilitate bridge to extend the service life and mitigate corrosion by applying Electrochemical Chloride Extraction (ECE) process and waterproofing to the structure. | 700 | Yes | 700 | 454 | 454 | 454 | No | 1500 | Yes | 1500 | 1205 | 1205 | 1205 | No | 90 | Yes | 90 | 43 | 43 | 122 | Yes | 2207 | Yes | 2207 | 728 | 728 | 2532 | Yes | 115 | No | 115 | 56 | 56 | 56 | No | 7331 | Yes | 7331 | 2191 | 2191 | 7331 | No | 11943 | 11943 | 4677 | 4677 | 11700 |  | 2019-05-08 | 2019-05-08 |  |  | 2020-09-16 | 2020-09-15 |  |  | 2021-01-28 | 2021-01-28 |  |  | 2021-07-29 | 2021-07-20 |  |  |  |  | 2023-09-29 |  | 7331 | No | No | No | Yes
325 | 05 | 2655 | SCR | 9 | San Lorenzo River Bridge and Kings Creek Bridge Replacement | Near Boulder Creek, at San Lorenzo River Bridge No 36-0052 and Kings Creek Bridge No 36-0054 (PM 15.49). | Replace bridges to maintain standards of safety and reliability. | 2692 | Yes | 2692 | 2262 | 2262 | 2262 | No | 2884 | Yes | 2884 | 2456 | 2456 | 3285 | Yes | 600 | Yes | 600 | 78 | 78 | 481 | No | 4158 | No | 4158 | 0 | 0 | 3994 | No | 660 | No | 660 | 140 | 140 | 156 | No | 14665 | No | 14665 | 0 | 0 | 16165 | Yes | 25659 | 25659 | 4936 | 4936 | 26343 |  | 2020-08-24 | 2021-02-08 |  |  | 2022-01-24 |  | 2023-12-01 | Yes | 2022-01-24 |  | 2023-12-01 | Yes | 2022-07-01 |  | 2024-05-13 | Yes |  |  | 2027-05-11 |  | 0 | Yes | No | No | No
326 | 05 | 2656 | MON | 1 | Castro Cyn Bridge Rail Upgrade | Near Big Sur, at the Castro Canyon Bridge No 44-0035. | Upgrade bridge railing and approach railings to meet current standards. | 869 | Yes | 869 | 868 | 868 | 868 | No | 1545 | Yes | 1545 | 1310 | 1310 | 1635 | Yes | 141 | Yes | 141 | 88 | 88 | 144 | Yes | 1155 | No | 1155 | 0 | 0 | 1178 | Yes | 73 | No | 73 | 8 | 8 | 80 | Yes | 2999 | No | 2999 | 0 | 0 | 2552 | No | 6782 | 6782 | 2274 | 2274 | 6457 |  | 2020-07-01 | 2020-08-11 |  |  | 2022-03-01 |  | 2024-01-31 | Yes | 2022-04-01 |  | 2024-02-15 | Yes | 2022-09-01 |  | 2024-08-28 | Yes |  |  | 2028-04-03 |  | 0 | Yes | No | No | No
327 | 05 | 2679 | MON | 101 | Prunedale CAPM | Near Prunedale, from 0.3 mile north of Boronda Road to north of Crazy Horse Canyon Road; and from 1.0 mile south of San Benito County line to San Benito County line (100.3/101.3). | Rehabilitate pavement, upgrade median barrier and guardrail, and repair drainage system. (G13 Contingency). | 4500 | Yes | 4500 | 2295 | 2295 | 2295 | No | 3580 | Yes | 3580 | 2629 | 2629 | 3756 | Yes | 415 | Yes | 415 | 174 | 174 | 441 | Yes | 0 | No | 0 | 0 | 0 | 6809 | Yes | 295 | No | 295 | 14 | 14 | 14 | No | 0 | No | 0 | 0 | 0 | 35200 | Yes | 8790 | 8790 | 5112 | 5112 | 48515 | 2021-08-18 | 2021-05-26 | 2021-05-26 |  |  | 2022-06-16 | 2022-06-16 |  |  | 2022-06-17 | 2022-06-24 |  |  | 2023-01-03 |  | 2022-12-30 | No |  |  | 2024-03-15 |  | 0 | No | Yes | No | No
328 | 05 | 2679X | MON | 101 | Prunedale Drainage | Near Prunedale, from 0.7 mile north of Crazy Horse Canyon Road to 1.1 miles south of San Juan Road. | Rehabilitate drainage culverts. | 1000 | Yes | 1000 | 582 | 582 | 1326 | Yes | 1606 | No | 1606 | 0 | 0 | 1606 | No | 875 | No | 875 | 0 | 0 | 688 | No | 1500 | No | 1500 | 0 | 0 | 2042 | Yes | 521 | No | 521 | 0 | 0 | 145 | No | 5605 | No | 5605 | 0 | 0 | 6260 | Yes | 11107 | 11107 | 582 | 582 | 12067 |  | 2022-03-15 |  | 2022-08-08 | Yes | 2023-12-11 |  | 2024-03-25 | Yes | 2024-01-11 |  | 2024-04-15 | Yes | 2024-07-25 |  | 2024-11-18 | Yes |  |  | 2025-11-03 |  | 0 | Yes | Yes | No | No
329 | 05 | 2696 | MON | 1 | Garrapata Creek Bridge Rail Replacement | Near Carmel-by-the-Sea, at the Garrapata Creek Bridge No 44-0018. | Replace bridge railing to meet current traffic safety standards. | 1600 | Yes | 1600 | 1207 | 1207 | 1207 | No | 1915 | Yes | 1915 | 695 | 695 | 1887 | No | 130 | Yes | 130 | 38 | 38 | 129 | No | 1391 | No | 1391 | 0 | 0 | 1305 | No | 58 | No | 58 | 12 | 12 | 57 | No | 3642 | No | 3642 | 0 | 0 | 3642 | No | 8736 | 8736 | 1952 | 1952 | 8227 |  | 2021-05-07 | 2021-05-07 |  |  | 2022-11-21 |  | 2022-12-01 | No | 2023-03-15 |  | 2023-05-15 | No | 2023-09-19 |  | 2024-01-05 | Yes |  |  | 2025-01-06 |  | 0 | No | No | No | Yes
330 | 05 | 2700 | SB | 101 | Gaviota-Nojoqui CAPM | Near Gaviota, from 0.1 mile south of Gaviota Beach State Park to Old Coast Highway. | Rehabilitate pavement. (G13 Contingency). | 2160 | Yes | 2160 | 1003 | 1003 | 1003 | No | 2648 | Yes | 2648 | 1910 | 1910 | 3106 | Yes | 76 | Yes | 76 | 11 | 11 | 75 | No | 0 | No | 0 | 0 | 0 | 6215 | Yes | 131 | No | 131 | 113 | 113 | 113 | No | 0 | No | 0 | 0 | 0 | 65600 | Yes | 5015 | 5015 | 3037 | 3037 | 76112 | 2020-06-24 | 2020-04-29 | 2020-04-29 |  |  | 2021-09-13 | 2022-01-04 |  |  | 2021-11-18 | 2022-06-14 |  |  | 2022-06-28 |  | 2023-01-05 | Yes |  |  | 2023-12-29 |  | 0 | Yes | Yes | No | No
331 | 05 | 2725 | SCR | 1 | Santa Cruz Route 1 CAPM | In and near the city of Santa Cruz, from south of River Street (Route 9) to north of Western Drive. | Rehabilitate pavement, reconstruct guardrail, replace sign panels, upgrade facilities to Americans with Disabilities Act (ADA) standards, update crosswalks, and repair Class 2 bike lanes. | 1591 | Yes | 1591 | 0 | 0 | 1533 | No | 2119 | No | 2119 | 0 | 0 | 1977 | No | 903 | No | 903 | 0 | 0 | 839 | No | 2111 | No | 2111 | 0 | 0 | 1848 | No | 190 | No | 190 | 0 | 0 | 189 | No | 8892 | No | 8892 | 0 | 0 | 8892 | No | 15806 | 15806 | 0 | 0 | 15278 |  |  |  | 2023-09-19 |  |  |  | 2025-09-19 |  |  |  | 2025-09-19 |  |  |  | 2026-04-08 |  |  |  | 2027-04-07 |  | 0 | No | No | No | No
332 | 05 | 2726 | SB | 101 | North Buellton CAPM | In Santa Barbara County on Route 101 from 0.25 miles south of the Santa Rosa Rd Interchange to 2.4 miles south of San Antonio Creek Bridge. | Preserve 34.492 lane miles of flexible Class 2 pavement using a CAPM Strategy, reconstruct guardrail, rehabilitate 2 culverts, replace 4 census stations and replace 53 sign panels as needed in Santa Barbara County. | 1229 | No | 1229 | 3 | 3 | 1211 | No | 0 | No | 0 | 0 | 0 | 2383 | Yes | 0 | No | 0 | 0 | 0 | 112 | Yes | 0 | No | 0 | 0 | 0 | 4108 | Yes | 0 | No | 0 | 0 | 0 | 117 | Yes | 0 | No | 0 | 0 | 0 | 28269 | Yes | 1229 | 1229 | 3 | 3 | 36200 |  |  |  | 2023-09-20 |  |  |  | 2024-11-04 |  |  |  | 2025-05-01 |  |  |  | 2025-11-24 |  |  |  | 2028-05-01 |  | 0 | No | Yes | No | No
333 | 05 | 2736 | SCR | 1 | Soquel Creek Scour Protection | In Capitola, at Soquel Creek Bridge No 36-0013. | Place Rock Slope Protection (RSP) to protect bridge foundation. | 1591 | Yes | 1591 | 705 | 705 | 705 | No | 1370 | Yes | 1370 | 724 | 724 | 724 | No | 196 | Yes | 196 | 7 | 7 | 81 | No | 1341 | Yes | 1341 | 0 | 0 | 1400 | Yes | 346 | No | 346 | 51 | 51 | 157 | No | 1291 | Yes | 1291 | 0 | 0 | 1291 | No | 6135 | 6135 | 1487 | 1487 | 4358 |  | 2019-12-31 | 2020-04-14 |  |  | 2021-04-29 | 2021-06-16 |  |  | 2021-07-01 | 2021-11-10 |  |  | 2022-02-01 | 2022-07-11 |  |  |  |  | 2023-03-15 |  | 1063 | No | No | No | No
334 | 05 | 2775 | SCR | 129 | 129 Paving, Sign Panels, Lighting, TMS Improvement | In and near Watsonville, from Route 1 to east of Blackburn Street; also on Route 152 (West Lake Avenue) from Main Street to Wagner Avenue (PM T2.8/1.33). | Rehabilitate pavement and lighting, replace sign panels, install Transportation Management System (TMS) elements, construct new sidewalk, curb ramps, high visibility crosswalks, flashing beacons, and Class 2 and Class 3 bike lanes as complete streets elements. | 1857 | Yes | 1857 | 1587 | 1587 | 1587 | No | 2919 | Yes | 2919 | 163 | 163 | 3002 | Yes | 2022 | Yes | 2022 | 1 | 1 | 2046 | Yes | 1904 | No | 1904 | 0 | 0 | 2122 | Yes | 726 | No | 726 | 0 | 0 | 943 | Yes | 8440 | No | 8440 | 0 | 0 | 9498 | Yes | 17868 | 17868 | 1751 | 1751 | 19198 |  | 2022-02-01 | 2022-02-24 |  |  | 2024-04-02 |  | 2024-04-02 | No | 2024-05-01 |  | 2024-05-01 | No | 2025-01-08 |  | 2025-01-08 | No |  |  | 2025-11-07 |  | 0 | No | Yes | No | No
335 | 05 | 2776 | SBT | 101 | SBT 101 Asset Management Project (SB1) | Near Prunedale, San Juan Bautista, Aromas and Sargent, from Monterey County line to Santa Clara County line. | Rehabilitate pavement and drainage systems, replace Transportation Management System (TMS) elements, upgrade lighting, and construct concrete barrier. (Long Lead Project). | 1665 | Yes | 1665 | 9 | 9 | 1624 | No | 0 | No | 0 | 0 | 0 | 2428 | Yes | 0 | No | 0 | 0 | 0 | 227 | Yes | 0 | No | 0 | 0 | 0 | 3891 | Yes | 0 | No | 0 | 0 | 0 | 186 | Yes | 0 | No | 0 | 0 | 0 | 29955 | Yes | 1665 | 1665 | 9 | 9 | 38311 |  |  |  | 2025-05-23 |  |  |  | 2026-09-16 |  |  |  | 2028-02-01 |  |  |  | 2028-09-01 |  |  |  | 2030-07-18 |  | 0 | No | Yes | No | No
336 | 05 | 2778 | SLO | 101 | SLO County Asset Management Improvements | In and near Pismo Beach, Arroyo Grande, and Nipomo, from Los Barros Road to south of Hinds Avenue Overcrossing. | Rehabilitate pavement, drainage systems, enhance highway worker safety, designate bikeways with pavement delineation, and install Transportation Management System (TMS) elements. (G13 Contingency). | 1610 | Yes | 1610 | 1395 | 1395 | 2373 | Yes | 3209 | No | 3209 | 0 | 0 | 3135 | No | 655 | No | 655 | 0 | 0 | 607 | No | 0 | No | 0 | 0 | 0 | 2611 | Yes | 230 | No | 230 | 0 | 0 | 206 | No | 0 | No | 0 | 0 | 0 | 32379 | Yes | 5704 | 5704 | 1395 | 1395 | 41311 |  | 2022-09-30 |  | 2022-09-30 | No | 2024-04-12 |  | 2024-04-12 | No | 2024-06-17 |  | 2024-06-17 | No | 2024-12-10 |  | 2024-12-10 | No |  |  | 2026-07-03 |  | 0 | Yes | Yes | No | Yes
337 | 05 | 2787 | MON | 68 | Route 68 Drainage Improvements | In and near the city of Monterey, from west of Sunset Drive to Toro Park Undercrossing. | Rehabilitate drainage systems and lighting, and install Transportation Management System (TMS) elements. | 1900 | Yes | 1900 | 1602 | 1602 | 1602 | No | 2600 | No | 2600 | 0 | 0 | 2598 | No | 2300 | No | 2300 | 0 | 0 | 2299 | No | 2500 | No | 2500 | 0 | 0 | 1811 | No | 900 | No | 900 | 3 | 3 | 897 | No | 7600 | No | 7600 | 0 | 0 | 7720 | Yes | 17800 | 17800 | 1605 | 1605 | 16927 |  | 2022-06-06 | 2022-06-24 |  |  | 2024-06-05 |  | 2024-06-05 | No | 2024-06-05 |  | 2024-06-05 | No | 2024-12-20 |  | 2024-12-20 | No |  |  | 2026-01-09 |  | 0 | No | No | No | Yes
338 | 05 | 2843 | SCR | 1 | SCr 1 Roadside Safety | In and near the cities of Capitola and Santa Cruz, from north of Larkin Valley Road Undercrossing to Laguna Road; also in Monterey County (PM R101.53). | Rehabilitate drainage systems, enhance highway worker safety, replace lighting and install Transportation Management System (TMS) elements. | 2206 | Yes | 2206 | 1245 | 1245 | 2438 | Yes | 3264 | No | 3264 | 0 | 0 | 3203 | No | 779 | No | 779 | 0 | 0 | 726 | No | 3209 | No | 3209 | 0 | 0 | 3003 | No | 174 | No | 174 | 0 | 0 | 221 | Yes | 12389 | No | 12389 | 0 | 0 | 10405 | No | 22021 | 22021 | 1245 | 1245 | 19996 |  | 2022-11-22 |  | 2022-12-22 | No | 2024-04-01 |  | 2024-04-22 | No | 2024-05-01 |  | 2024-06-12 | No | 2024-11-01 |  | 2025-02-27 | Yes |  |  | 2026-01-26 |  | 0 | No | No | No | No
339 | 05 | 2845 | SLO | 58 | Santa Margarita 58 CAPM | Near Santa Margarita, from I Street to Route 229. | Rehabilitate pavement and drainage, replace sign panels, and install Transportation Management System (TMS) elements. | 1622 | Yes | 1622 | 1023 | 1023 | 1723 | Yes | 2253 | No | 2253 | 0 | 0 | 2216 | No | 968 | No | 968 | 0 | 0 | 934 | No | 2103 | No | 2103 | 0 | 0 | 1875 | No | 2549 | No | 2549 | 0 | 0 | 375 | No | 6500 | No | 6500 | 0 | 0 | 6522 | Yes | 15995 | 15995 | 1023 | 1023 | 13645 |  | 2022-04-26 |  | 2023-01-01 | Yes | 2024-01-12 |  | 2024-01-12 | No | 2024-05-22 |  | 2024-06-01 | No | 2024-12-20 |  | 2024-12-20 | No |  |  | 2028-09-28 |  | 0 | Yes | No | No | No
340 | 05 | 2879 | SCR | 9 | South SCr 9 CAPM | In and near the city of Santa Cruz, Felton and Brackney, from Route 1 to south of El Solyo Heights Drive. | Rehabilitate pavement and drainage systems, upgrade Transportation Management System (TMS) elements, reconstruct guardrail, replace sign panels, upgrade facilities to Americans with Disabilities Act (ADA) standards, and construct sidewalks and Class 2 bike lanes. (Long Lead project). | 2364 | Yes | 2364 | 1 | 1 | 2244 | No | 0 | No | 0 | 0 | 0 | 2587 | Yes | 0 | No | 0 | 0 | 0 | 779 | Yes | 0 | No | 0 | 0 | 0 | 2738 | Yes | 0 | No | 0 | 0 | 0 | 887 | Yes | 0 | No | 0 | 0 | 0 | 14724 | Yes | 2364 | 2364 | 1 | 1 | 23959 |  |  |  | 2025-01-10 |  |  |  | 2026-10-02 |  |  |  | 2026-11-16 |  |  |  | 2027-05-26 |  |  |  | 2029-07-13 |  | 0 | No | Yes | No | No
341 | 05 | 2880 | SCR | 9 | Upper Hwy 9 CAPM | Near Boulder Creek and Saratoga, from south of Saratoga Toll Road to Route 35. | Rehabilitate pavement and drainage systems, and reconstruct guardrail. | 1322 | Yes | 1322 | 1 | 1 | 1247 | No | 2199 | No | 2199 | 0 | 0 | 1936 | No | 348 | No | 348 | 0 | 0 | 314 | No | 1675 | No | 1675 | 0 | 0 | 1419 | No | 72 | No | 72 | 0 | 0 | 72 | No | 7529 | No | 7529 | 0 | 0 | 7529 | No | 13145 | 13145 | 1 | 1 | 12517 |  |  |  | 2024-03-01 |  |  |  | 2025-08-29 |  |  |  | 2026-01-15 |  |  |  | 2026-07-01 |  |  |  | 2028-07-03 |  | 0 | No | No | No | No
342 | 05 | 2889 | MON | 1 | Moss Landing CAP-M | Near Castroville, Moss Landing, and Watsonville, from north of Molera Road to Santa Cruz County line. | Rehabilitate pavement, upgrade Transportation Management System (TMS) elements, upgrade facilities to Americans with Disabilities Act (ADA) standards, and replace guardrail and sign panels. | 2875 | Yes | 2875 | 10 | 10 | 2826 | No | 3578 | No | 3578 | 0 | 0 | 3375 | No | 179 | No | 179 | 0 | 0 | 165 | No | 3088 | No | 3088 | 0 | 0 | 2651 | No | 102 | No | 102 | 0 | 0 | 102 | No | 16810 | No | 16810 | 0 | 0 | 16810 | No | 26632 | 26632 | 10 | 10 | 25929 |  |  |  | 2024-08-26 |  |  |  | 2026-04-10 |  |  |  | 2026-06-01 |  |  |  | 2026-12-04 |  |  |  | 2027-09-22 |  | 0 | No | No | No | No
343 | 05 | 2899 | MON | 183 | Salinas to Castroville CAPM | Near Salinas and Castroville, from north of Davis Road to south of Del Monte Avenue. | Rehabilitate pavement and lighting, replace sign panels, and install Transportation Management System (TMS) elements. | 634 | Yes | 634 | 425 | 425 | 425 | No | 1650 | Yes | 1650 | 46 | 46 | 1708 | Yes | 50 | Yes | 50 | 1 | 1 | 79 | Yes | 1308 | No | 1308 | 0 | 0 | 1306 | No | 13 | No | 13 | 0 | 0 | 0 | No | 6950 | No | 6950 | 0 | 0 | 6913 | No | 10605 | 10605 | 472 | 472 | 10431 |  | 2021-11-30 | 2021-11-29 |  |  | 2023-03-02 |  | 2023-02-17 | No | 2023-06-30 |  | 2023-06-20 | No | 2024-01-24 |  | 2024-04-12 | No |  |  | 2025-01-14 |  | 0 | No | No | No | No
344 | 05 | 2900 | MON | 101 | King City CAPM | Near King City, from Jolon Road to Lagomarsino Avenue. | Rehabilitate pavement, drainage systems, and lighting, and install Transportation Management System (TMS) elements. (G13 Contingency). | 1151 | Yes | 1151 | 1032 | 1032 | 1032 | No | 2021 | No | 2021 | 0 | 0 | 2036 | Yes | 224 | No | 224 | 0 | 0 | 219 | No | 0 | No | 0 | 0 | 0 | 3824 | Yes | 156 | No | 156 | 3 | 3 | 147 | No | 0 | No | 0 | 0 | 0 | 28536 | Yes | 3552 | 3552 | 1035 | 1035 | 35794 |  | 2022-06-29 | 2022-06-29 |  |  | 2024-04-03 |  | 2024-04-03 | No | 2024-06-20 |  | 2024-06-20 | No | 2025-01-06 |  | 2025-01-06 | No |  |  | 2025-08-11 |  | 0 | No | Yes | No | Yes
345 | 05 | 2902 | SB | 101 | North Nojoqui Grade CAPM & Drainage | Near Buellton, from Old Coast Highway to south of Santa Rosa Road Overcrossing. | Rehabilitate pavement and drainage systems. (G13 Contingency). | 1312 | Yes | 1312 | 679 | 679 | 1170 | No | 1963 | No | 1963 | 0 | 0 | 1855 | No | 189 | No | 189 | 0 | 0 | 182 | No | 0 | No | 0 | 0 | 0 | 1893 | Yes | 48 | No | 48 | 0 | 0 | 173 | Yes | 0 | No | 0 | 0 | 0 | 18100 | Yes | 3512 | 3512 | 679 | 679 | 23373 |  | 2022-11-28 |  | 2022-10-14 | No | 2024-04-20 |  | 2024-03-29 | No | 2024-04-30 |  | 2024-03-29 | No | 2025-02-07 |  | 2024-12-17 | No |  |  | 2025-10-31 |  | 0 | No | Yes | No | No
346 | 05 | 2903 | SLO | 46 | Paso Robles 46 CAPM | In Paso Robles, from Route 101 to east of Airport Road. | Rehabilitate pavement, replace sign panels, install Transportation Management System (TMS) elements, and upgrade facilities to Americans with Disabilities Act (ADA) standards. | 477 | Yes | 477 | 426 | 426 | 426 | No | 1424 | Yes | 1424 | 714 | 714 | 1860 | Yes | 75 | Yes | 75 | 25 | 25 | 138 | Yes | 1693 | No | 1693 | 0 | 0 | 1522 | No | 124 | No | 124 | 1 | 1 | 121 | No | 7550 | No | 7550 | 0 | 0 | 7000 | No | 11343 | 11343 | 1166 | 1166 | 11067 |  | 2021-10-19 | 2021-10-19 |  |  | 2023-01-05 |  | 2023-01-09 | No | 2023-01-27 |  | 2023-01-31 | No | 2023-08-01 |  | 2023-08-03 | No |  |  | 2024-10-03 |  | 0 | No | Yes | No | No
347 | 05 | 2904 | MON | 101 | Bradley CAPM | Near Bradley, Nacimiento and San Miguel, from south of East Garrison Overcrossing to Jolon Road. | Replace bridges, rehabilitate pavement, reconstruct guardrail and drainage systems, and replace Transportation Management System (TMS) elements and signs. (Long Lead Project). | 3359 | Yes | 3359 | 3 | 3 | 3362 | Yes | 0 | No | 0 | 0 | 0 | 5241 | Yes | 0 | No | 0 | 0 | 0 | 664 | Yes | 0 | No | 0 | 0 | 0 | 8465 | Yes | 0 | No | 0 | 0 | 0 | 139 | Yes | 0 | No | 0 | 0 | 0 | 57842 | Yes | 3359 | 3359 | 3 | 3 | 75713 |  |  |  | 2025-01-15 |  |  |  | 2027-07-30 |  |  |  | 2028-07-25 |  |  |  | 2029-01-31 |  |  |  | 2031-04-11 |  | 0 | No | Yes | No | No
348 | 05 | 2918 | SB | 101 | Zaca Station to Orcutt Drainage Rehab | Near Los Alamos and Orcutt, from 1.8 miles north of Route 154 to 0.2 mile south of South Santa Maria Undercrossing. | Rehabilitate drainage systems and lighting, and install Transportation Management System (TMS) elements. | 1478 | Yes | 1478 | 1014 | 1014 | 1614 | Yes | 1900 | No | 1900 | 0 | 0 | 1564 | No | 214 | No | 214 | 0 | 0 | 202 | No | 1629 | No | 1629 | 0 | 0 | 1450 | No | 435 | No | 435 | 3 | 3 | 463 | Yes | 4566 | No | 4566 | 0 | 0 | 4566 | No | 10222 | 10222 | 1017 | 1017 | 9859 |  | 2022-11-02 |  | 2022-11-02 | No | 2024-06-25 |  | 2024-06-25 | No | 2024-06-25 |  | 2024-06-25 | No | 2025-01-15 |  | 2025-01-15 | No |  |  | 2026-05-27 |  | 0 | No | No | No | No
349 | 05 | 2919 | SB | 154 | Hwy 154 Drainage Improvements | In Santa Barbara County, at various locations. | Rehabilitate drainage systems and install Transportation Management System (TMS) elements. | 1926 | Yes | 1926 | 863 | 863 | 1267 | No | 2044 | No | 2044 | 0 | 0 | 2029 | No | 558 | No | 558 | 0 | 0 | 526 | No | 2342 | No | 2342 | 0 | 0 | 2381 | Yes | 139 | No | 139 | 0 | 0 | 590 | Yes | 10398 | No | 10398 | 0 | 0 | 10080 | No | 17407 | 17407 | 863 | 863 | 16873 |  | 2022-10-03 |  | 2022-11-30 | No | 2024-05-01 |  | 2024-05-21 | No | 2024-05-01 |  | 2024-06-06 | No | 2024-12-18 |  | 2025-04-15 | Yes |  |  | 2026-04-23 |  | 0 | No | Yes | No | No
350 | 05 | 2926 | SCR | 1 | SCr 1 Drainage Improvements | In and near Watsonville, from Monterey County line to north of Larkin Valley Road; also in Monterey County (PM R101.53). | Rehabilitate drainage systems and lighting, install Transportation Management System (TMS) elements, pave areas behind the gore and construct Maintenance Vehicle Pullouts (MVPs) to reduce maintenance and enhance highway worker safety. | 1570 | Yes | 1570 | 883 | 883 | 1502 | No | 2456 | No | 2456 | 0 | 0 | 2187 | No | 43 | No | 43 | 0 | 0 | 39 | No | 1813 | No | 1813 | 0 | 0 | 1599 | No | 20 | No | 20 | 0 | 0 | 272 | Yes | 9652 | No | 9652 | 0 | 0 | 10652 | Yes | 15554 | 15554 | 883 | 883 | 16251 |  | 2022-11-23 |  | 2022-11-23 | No | 2024-03-20 |  | 2024-03-20 | No | 2024-04-05 |  | 2024-04-05 | No | 2024-11-04 |  | 2024-11-04 | No |  |  | 2025-08-22 |  | 0 | No | Yes | No | No
351 | 05 | 3006 | SB | 166 | Guadalupe to Santa Maria SR 166 CAPM | In and near Guadalupe and Santa Maria, from Route 1 to Route 101. | Rehabilitate pavement, install Transportation Management System (TMS) elements, reconstruct guardrail, replace signs, and upgrade facilities to Americans with Disabilities Act (ADA) standards. | 1415 | Yes | 1415 | 1 | 1 | 1362 | No | 2553 | No | 2553 | 0 | 0 | 2314 | No | 733 | No | 733 | 0 | 0 | 643 | No | 4113 | No | 4113 | 0 | 0 | 3585 | No | 69 | No | 69 | 0 | 0 | 68 | No | 11191 | No | 11191 | 0 | 0 | 11191 | No | 20074 | 20074 | 1 | 1 | 19163 |  |  |  | 2023-08-30 |  |  |  | 2025-05-15 |  |  |  | 2025-09-24 |  |  |  | 2026-04-06 |  |  |  | 2026-08-25 |  | 0 | No | No | No | No
352 | 05 | 3009 | MON | 101 | North San Ardo Rehab | Near San Ardo and San Lucas, from Cattlemen Road to south of Paris Valley Road Overcrossing. | Rehabilitate roadway, reconstruct guardrail and drainage systems, and replace Transportation Management System (TMS) elements and signs. | 2078 | Yes | 2078 | 4 | 4 | 2093 | Yes | 2616 | No | 2616 | 0 | 0 | 3560 | Yes | 65 | No | 65 | 0 | 0 | 80 | Yes | 5608 | No | 5608 | 0 | 0 | 5481 | No | 80 | No | 80 | 0 | 0 | 80 | No | 37114 | No | 37114 | 0 | 0 | 37114 | No | 47561 | 47561 | 4 | 4 | 48408 |  |  |  | 2024-02-27 |  |  |  | 2025-07-09 |  |  |  | 2026-05-13 |  |  |  | 2026-11-16 |  |  |  | 2028-07-19 |  | 0 | No | Yes | No | No
353 | 05 | 3010 | SB | 246 | Route 246 Cap-M and Robinson Bridge | In and near Lompoc and Buellton, from Route 1 to east of Domingos Road. | Replace bridge, rehabilitate pavement and drainage systems, construct Class 1 bike and pedestrian path, and upgrade facilities to Americans with Disabilities Act (ADA) standards, guardrail and signs. (Additional contribution from the Santa Barbara County Association of Governments (SBCAG).) (Long Lead Project). | 4282 | Yes | 4282 | 12 | 12 | 3656 | No | 0 | No | 0 | 0 | 0 | 6231 | Yes | 0 | No | 0 | 0 | 0 | 1111 | Yes | 0 | No | 0 | 0 | 0 | 7928 | Yes | 0 | No | 0 | 0 | 0 | 15413 | Yes | 0 | No | 0 | 0 | 0 | 58403 | Yes | 4282 | 4282 | 12 | 12 | 92742 |  |  |  | 2025-03-06 |  |  |  | 2027-12-27 |  |  |  | 2028-07-05 |  |  |  | 2029-01-05 |  |  |  | 2034-05-22 |  | 0 | No | Yes | No | No
354 | 05 | 3013 | SB | 246 | Alamo Pintado Replacement Bridge | In and near Solvang, from Alamo Pintado Road to Entrance Road. | Replace bridge, construct Class 1 bike and pedestrian paths, and upgrade facilities to Americans with Disabilities Act (ADA) standards. (Additional $1,204,000 contribution from the city of Solvang.) (Long Lead Project). | 2473 | Yes | 2473 | 0 | 0 | 2118 | No | 0 | No | 0 | 0 | 0 | 3262 | Yes | 0 | No | 0 | 0 | 0 | 434 | Yes | 0 | No | 0 | 0 | 0 | 4090 | Yes | 0 | No | 0 | 0 | 0 | 2674 | Yes | 0 | No | 0 | 0 | 0 | 18462 | Yes | 2473 | 2473 | 0 | 0 | 31040 |  |  |  | 2024-08-23 |  |  |  | 2026-12-04 |  |  |  | 2027-02-12 |  |  |  | 2027-11-04 |  |  |  | 2029-02-21 |  | 0 | No | Yes | No | No
355 | 05 | 3034 | MON | 1 | Marina to Castroville CAPM | In and near Marina, from south of Lake Drive Undercrossing to Route 156. | Rehabilitate pavement and drainage systems, replace Transportation Management System (TMS) elements, and upgrade guardrail and lighting. | 1168 | Yes | 1168 | 11 | 11 | 1086 | No | 1964 | No | 1964 | 0 | 0 | 1870 | No | 100 | No | 100 | 0 | 0 | 83 | No | 2478 | No | 2478 | 0 | 0 | 2083 | No | 26 | No | 26 | 0 | 0 | 26 | No | 17640 | No | 17640 | 0 | 0 | 17640 | No | 23376 | 23376 | 11 | 11 | 22788 |  |  |  | 2024-10-04 |  |  |  | 2026-05-14 |  |  |  | 2026-06-25 |  |  |  | 2026-11-24 |  |  |  | 2027-05-24 |  | 0 | No | No | No | No
356 | 05 | 3078 | SLO | 101 | Bridge Maintenance | In San Luis Obispo County, in and near Santa Maria, Santa Margarita, Atascadero at various locations; also in Monterey County at North Bradley Undercrossing No 44-0142R (PM R7.94). | Apply polyester concrete overlay and replace joint seals. (Bridge Deck Preservation). | 77 | Yes | 75 | 9 | 9 | 54 | No | 332 | Yes | 330 | 17 | 17 | 425 | Yes | 10 | Yes | 10 | 0 | 0 | 55 | Yes | 650 | No | 650 | 0 | 0 | 689 | Yes | 0 | No | 0 | 0 | 0 | 0 | No | 2218 | No | 2218 | 0 | 0 | 2218 | No | 3287 | 3283 | 26 | 26 | 3441 |  |  |  | 2022-08-22 |  |  |  | 2022-10-21 |  |  |  | 2022-12-16 |  |  |  | 2023-05-02 |  |  |  | 2023-12-05 |  | 0 | No | No | No | No
357 | 05 | 4022 | SLO | 101 | SLO 101 N Cnty TMS | In San Luis Obispo County, from 0.3 mile north of Reservoir Canyon Road to 0.3 mile north of North Paso Robles Overhead; also on Route 46 from Theater Drive to Union Road (PM R21.7/31.9) at various locations. | Install vehicle detection systems, Changeable Message Signs (CMS), cameras, and loop detectors. | 450 | Yes | 450 | 388 | 388 | 388 | No | 1095 | Yes | 1095 | 694 | 694 | 694 | No | 78 | Yes | 78 | 29 | 29 | 83 | Yes | 707 | Yes | 707 | 446 | 446 | 872 | Yes | 5 | No | 5 | 0 | 0 | 0 | No | 2728 | Yes | 2728 | 2003 | 2003 | 2728 | No | 5063 | 5063 | 3560 | 3560 | 4765 |  | 2019-01-11 | 2019-01-11 |  |  | 2020-08-03 | 2020-08-03 |  |  | 2020-12-01 | 2020-12-02 |  |  | 2021-08-02 | 2021-05-07 |  |  |  |  | 2022-11-15 |  | 2728 | Yes | Yes | Yes | Yes
358 | 05 | 7101L | SBT | 101 | Carpinteria to Santa Barbara Widening – 4A Carpinteria Mitigation Pltg | In Santa Barbara County In Carpinteria From 0.2 Mile South of Bailard Avenue Overcrossing To 0.7 Mile South of South Padaro Lane | Install mitigation planting | 0 | No | 0 | 0 | 0 | 0 | No | 0 | No | 0 | 0 | 0 | 0 | No | 0 | No | 0 | 0 | 0 | 0 | No | 1000 | No | 500 | 0 | 0 | 1059 | Yes | 0 | No | 0 | 0 | 0 | 0 | No | 3536 | No | 1768 | 0 | 0 | 3537 | Yes | 4536 | 2268 | 0 | 0 | 4596 |  |  | 2020-12-18 |  |  |  | 2021-05-14 |  |  |  | 2021-06-24 |  |  |  | 2022-05-27 |  |  |  |  | 2026-08-06 |  | 3536 | No | No | No | No
359 | 05 | 7101P | SB | 101 | Carpinteria to Santa Barbara Widening - Segment 4A Combined | In Santa Barbara County In Carpenteria From 0.2 Mile South of Bailard Avenue Overcrossing To 0.7 Mile South of South Padaro Lane | Construct HOV lanes | 12245 | No | 9200 | 5862 | 2302 | 5862 | No | 9700 | No | 1380 | 10680 | 1435 | 10680 | Yes | 1140 | No | 220 | 1090 | 105 | 1090 | No | 18470 | No | 10040 | 9961 | 5415 | 16698 | No | 10620 | No | 4880 | 2016 | 731 | 0 | No | 89548 | No | 44478 | 84559 | 42612 | 79732 | No | 141723 | 70198 | 114168 | 52600 | 114062 |  | 2014-08-26 | 2014-08-26 |  |  | 2020-01-15 | 2020-02-04 |  |  | 2020-02-01 | 2020-02-04 |  |  | 2020-08-15 | 2020-04-02 |  |  | 2024-08-15 |  | 2023-08-22 | No | 79731 | No | No | No | No
360 | 05 | 7101R | SBT | 101 | Carpinteria to Santa Barbara Widening Project - (Segment 4B) Combined | In Santa Barbara County, in and near Carpinteria and at Summerland from 0.9 mile south of South Padaro Lane Undercrossing to 0.6 mile north of Padaro Lane Overcrossing | Construct HOV Lanes and rehabilitate roadway. | 2725 | No | 0 | 6526 | 3338 | 6526 | Yes | 14395 | No | 4370 | 15893 | 3845 | 15893 | Yes | 1010 | No | 290 | 443 | 74 | 443 | No | 31315 | No | 14855 | 5061 | 2401 | 25592 | No | 10900 | No | 410 | 115 | 80 | 0 | No | 164567 | No | 85907 | 55740 | 29679 | 162317 | No | 224912 | 105832 | 83778 | 39417 | 210771 |  | 2014-08-26 | 2018-06-04 |  |  | 2020-11-01 | 2021-02-05 |  |  | 2021-01-01 | 2021-03-19 |  |  | 2021-07-15 | 2021-05-26 |  |  | 2025-12-15 |  | 2025-01-24 | No | 162317 | No | No | No | No
361 | 05 | 7101S | SB | 101 | Carpinteria to Santa Barbara Widening Project - Segment 4C Combined | In Santa Barbara County, in and near Summerland from 0.2 miles north of Padaro Lane Overcrossing to San Ysidro Creek Bridge. | Construct HOV Lanes and rehabilitate roadway. | 2380 | No | 0 | 4667 | 1882 | 4667 | Yes | 7080 | No | 330 | 2742 | 537 | 2742 | No | 520 | No | 90 | 6 | 6 | 35 | No | 18430 | No | 7530 | 5696 | 2327 | 16995 | No | 3930 | No | 270 | 37 | 37 | 0 | No | 108761 | No | 34633 | 69870 | 22289 | 107672 | No | 141101 | 42853 | 83018 | 27078 | 132111 |  | 2014-08-26 | 2017-09-29 |  |  | 2020-11-01 | 2020-06-22 |  |  | 2021-01-01 | 2020-06-24 |  |  | 2021-07-15 | 2020-10-23 |  |  | 2025-12-15 |  | 2024-07-09 | No | 107672 | No | No | No | No
362 | 05 | 9700 | MON | 101 | North Soledad OH Deck Rehab | Near Soledad, from Route 146 to Front Street at the North Soledad Overhead No 44-0091R. | Rehabilitate bridge. | 94 | No | 94 | 94 | 94 | 94 | No | 4375 | Yes | 4375 | 3801 | 3801 | 3801 | No | 632 | Yes | 632 | 462 | 462 | 607 | No | 1568 | Yes | 1568 | 79 | 79 | 1585 | Yes | 1578 | No | 1578 | 61 | 61 | 122 | No | 4692 | Yes | 4692 | 0 | 0 | 4692 | No | 12939 | 12939 | 4497 | 4497 | 10901 |  | 2014-09-02 | 2014-09-02 |  |  | 2020-07-01 | 2021-12-03 |  |  | 2020-11-02 | 2021-12-03 |  |  | 2021-05-27 | 2022-04-08 |  |  |  |  | 2023-01-26 |  | 4692 | No | No | No | No
363 | 06 | 3425 | KER | 46 | SEMITROPIC CAPM | Near Lost Hills and Wasco, from east of Route 5 to west of Scofield Avenue. | Rehabilitate pavement, construct Maintenance Vehicle Pullouts (MVP), and upgrade bridge rails, guardrails, sign panels, and Transportation Management System (TMS) elements. | 1520 | Yes | 1520 | 0 | 0 | 1454 | No | 1700 | No | 1700 | 0 | 0 | 1530 | No | 10 | No | 10 | 0 | 0 | 8 | No | 2400 | No | 2400 | 0 | 0 | 2071 | No | 25 | No | 25 | 0 | 0 | 43 | Yes | 14300 | No | 14300 | 0 | 0 | 14300 | No | 19955 | 19955 | 0 | 0 | 19406 |  |  |  | 2024-08-01 |  |  |  | 2026-04-02 |  |  |  | 2026-04-10 |  |  |  | 2026-12-02 |  |  |  | 2027-10-01 |  | 0 | No | No | No | No
364 | 06 | 5335A | MAD | 99 | Madera 99 Widening | In and near Madera, from Avenue 12 Overcrossing to 0.9 mile north of Avenue 17 Overcrossing. | Additional contribution for the construction of one new lane in each direction. Roadway rehabilitation. | 2250 | No | 0 | 2245 | 0 | 2245 | No | 5545 | Yes | 1850 | 5853 | 1850 | 5853 | Yes | 402 | No | 0 | 407 | 0 | 559 | Yes | 8750 | Yes | 7500 | 7999 | 6856 | 8826 | Yes | 52 | No | 0 | 23 | 0 | 21 | No | 72146 | Yes | 58426 | 66764 | 57415 | 71006 | No | 89145 | 67776 | 83291 | 66121 | 88510 |  | 2015-08-14 | 2015-08-14 |  |  | 2018-05-01 | 2018-06-13 |  |  | 2018-06-01 | 2018-07-05 |  |  | 2019-11-01 | 2019-04-05 |  |  |  |  | 2022-09-01 |  | 71005 | No | No | No | No
365 | 06 | 6286 | TUL | 190 | TULARE CULVERT REPLACEMENT | Between Springville and Camp Nelson, from 2.4 miles east of Balch Park Road to 0.6 mile west of Wishon Drive. | Replace deteriorated culverts and upgrade existing Guardrail. | 1080 | Yes | 1080 | 813 | 813 | 813 | No | 1100 | Yes | 1100 | 1028 | 1028 | 1028 | No | 210 | Yes | 210 | 180 | 180 | 278 | Yes | 930 | Yes | 930 | 202 | 202 | 843 | No | 246 | No | 246 | 77 | 77 | 76 | No | 1893 | Yes | 1893 | 312 | 312 | 1893 | No | 5459 | 5459 | 2612 | 2612 | 4931 |  | 2018-11-17 | 2018-12-17 |  |  | 2020-03-01 | 2021-11-01 |  |  | 2020-03-15 | 2021-11-17 |  |  | 2021-02-01 | 2022-04-01 |  |  |  |  | 2022-12-07 |  | 1892 | No | No | No | Yes
366 | 06 | 6661 | KER | 099 | Bakersfield 99 Rehab I(North) | IN KERN COUNTY IN AND NEAR BAKERSFIELD FROM BRUNDAGE LN OC TO BEARDSLEY CANAL | Roadway Rehabilitation | 3500 | No | 3500 | 2776 | 2776 | 2776 | No | 5150 | Yes | 5150 | 4947 | 4947 | 4947 | No | 24 | Yes | 24 | 28 | 28 | 28 | Yes | 11000 | Yes | 11000 | 10241 | 10241 | 11633 | Yes | 220 | No | 220 | 217 | 217 | 217 | No | 72745 | Yes | 72745 | 65136 | 65136 | 72745 | No | 92639 | 92639 | 83345 | 83345 | 92346 |  |  | 2016-08-22 |  |  |  | 2018-03-14 |  |  |  | 2018-05-01 |  |  |  | 2018-10-25 |  |  |  |  | 2022-07-29 |  | 72744 | No | No | No | Yes
367 | 06 | 6661A | KER | 99 | Bakersfield 99 Rehab Replacement Planting | In Bakersfield, from Brundage Lane Overcrossing to Beardsley Canal Bridge. | Landscape mitigation for rehabilitate roadway project EA 0Q280. | 700 | Yes | 700 | 638 | 638 | 638 | No | 500 | Yes | 500 | 514 | 514 | 637 | Yes | 20 | Yes | 20 | 2 | 2 | 21 | Yes | 2500 | No | 2500 | 0 | 0 | 1664 | No | 20 | No | 20 | 0 | 0 | 66 | Yes | 6600 | No | 6600 | 0 | 0 | 6600 | No | 10340 | 10340 | 1154 | 1154 | 9626 |  | 2021-07-30 | 2021-08-23 |  |  | 2022-04-25 | 2022-03-09 |  |  | 2022-05-02 | 2022-05-03 |  |  | 2023-02-02 |  | 2023-03-02 | No |  |  | 2027-09-27 |  | 0 | No | No | No | No
368 | 06 | 6679 | TUL | 99 | Tipton Bridge Deck Rehab | In Tipton, at Avenue 152 Overcrossing No 46-0191. | Replace bridge. | 698 | Yes | 698 | 660 | 660 | 660 | No | 1930 | Yes | 1930 | 1907 | 1907 | 1907 | No | 259 | Yes | 259 | 215 | 215 | 258 | No | 1940 | Yes | 1940 | 1793 | 1793 | 1875 | No | 343 | No | 343 | 84 | 84 | 84 | No | 8657 | Yes | 8657 | 8021 | 8021 | 8657 | No | 13827 | 13827 | 12680 | 12680 | 13441 |  | 2018-02-01 | 2018-02-01 |  |  | 2020-02-03 | 2020-03-20 |  |  | 2020-03-02 | 2020-03-26 |  |  | 2020-08-03 | 2020-10-13 |  |  |  |  | 2022-06-01 |  | 8656 | No | No | No | No
369 | 06 | 6681 | KER | 99 | Union Ave to White Lane 2R Rehab | In and near Bakersfield, from 0.5 mile south of Old US 99 Overcrossing to 0.1 mile north of White Lane. | Rehabilitate pavement. | 960 | Yes | 960 | 955 | 955 | 955 | No | 2730 | Yes | 2730 | 2682 | 2682 | 2682 | No | 190 | Yes | 190 | 131 | 131 | 135 | No | 5700 | Yes | 5700 | 1030 | 1030 | 3793 | No | 770 | No | 770 | 5 | 5 | 5 | No | 56131 | Yes | 56131 | 17359 | 17359 | 56131 | No | 66481 | 66481 | 22162 | 22162 | 63701 | 2018-10-17 | 2018-03-02 | 2018-03-02 |  |  | 2020-02-03 | 2020-04-07 |  |  | 2020-03-02 | 2020-04-30 |  |  | 2020-08-17 | 2020-12-31 |  |  |  |  | 2023-11-01 |  | 56131 | No | No | No | Yes
370 | 06 | 6696 | TUL | 216 | Lovers Lane Rehab | In and near Visalia, from Route 198 to east of North McAuliff Street. | Rehabilitate roadway by replacing distressed asphalt, provide non-motorized transportation facilities and bring Americans with Disabilities Act (ADA) facilities to current standards. | 2950 | Yes | 2950 | 2585 | 2585 | 2585 | No | 2250 | Yes | 2250 | 1158 | 1158 | 2665 | Yes | 750 | Yes | 750 | 175 | 175 | 811 | Yes | 3300 | No | 3300 | 0 | 0 | 2668 | No | 1500 | No | 1500 | 19 | 19 | 2949 | Yes | 20900 | No | 20900 | 0 | 0 | 20364 | No | 31650 | 31650 | 3937 | 3937 | 32042 |  | 2021-06-29 | 2021-06-29 |  |  | 2023-04-26 |  | 2023-04-26 | No | 2023-05-03 |  | 2023-05-03 | No | 2023-10-02 |  | 2023-10-02 | No |  |  | 2025-01-02 |  | 0 | No | Yes | No | No
371 | 06 | 6708 | MAD | 41 | Ranchos Rehab | Near Fresno, from north of Avenue 15 to south of Route 145. | Roadway rehabilitation. | 2909 | Yes | 2909 | 2820 | 2820 | 2820 | No | 3020 | Yes | 3020 | 2802 | 2802 | 3320 | Yes | 1296 | Yes | 1296 | 332 | 332 | 1134 | No | 3000 | No | 3000 | 0 | 0 | 3227 | Yes | 4200 | No | 4200 | 934 | 934 | 4107 | No | 13900 | No | 13900 | 0 | 0 | 17999 | Yes | 28325 | 28325 | 6888 | 6888 | 32607 |  | 2020-05-13 | 2020-05-15 |  |  | 2021-05-01 | 2022-05-31 |  |  | 2021-05-03 | 2022-06-07 |  |  | 2021-11-01 |  | 2022-12-01 | Yes |  |  | 2024-07-01 |  | 0 | Yes | Yes | No | No
372 | 06 | 6725 | FRE | 5 | Tumey Gulch III | Near Mendota, at Tumey Gulch Bridge No 42-0246L/R. | Replace bridge. | 1395 | Yes | 1395 | 1323 | 1323 | 1323 | No | 2290 | Yes | 2290 | 2201 | 2201 | 2201 | No | 4 | No | 4 | 0 | 0 | 4 | No | 3100 | Yes | 3100 | 27 | 27 | 3020 | No | 3544 | No | 3544 | 47 | 47 | 626 | No | 12900 | Yes | 12900 | 0 | 0 | 11462 | No | 23233 | 23233 | 3598 | 3598 | 18636 |  | 2018-07-31 | 2018-10-12 |  |  | 2020-01-03 | 2019-12-17 |  |  | 2020-02-03 | 2021-11-26 |  |  | 2020-07-03 | 2022-06-16 |  |  |  |  | 2024-10-18 |  | 11462 | No | No | No | Yes
373 | 06 | 6727 | FRE | 99 | Kingsburg 99 Rehab | In and near Kingsburg, from Route 201 to 0.3 mile south of Second Street. | Roadway rehabilitation. | 677 | Yes | 677 | 656 | 656 | 656 | No | 1836 | Yes | 1836 | 1795 | 1795 | 1795 | No | 143 | Yes | 143 | 78 | 78 | 140 | No | 5000 | Yes | 5000 | 4446 | 4446 | 5002 | Yes | 375 | No | 375 | 40 | 40 | 40 | No | 35420 | Yes | 35420 | 34994 | 34994 | 35420 | No | 43451 | 43451 | 42009 | 42009 | 43053 | 2018-10-17 | 2017-08-03 | 2017-08-03 |  |  | 2019-04-01 | 2019-02-06 |  |  | 2019-04-15 | 2019-05-02 |  |  | 2019-08-08 | 2019-12-24 |  |  |  | 2022-06-07 |  |  | 35420 | No | No | No | No
374 | 06 | 6773 | FRE | 33 | Firebaugh & Buttonwillow Bridge Pile Repair | In Fresno County, at Colony Main Canal Bridge No 42-0031, Helm Canal Bridge No 42-0033 and Poso Canal Bridge No 42-0034; also in Kern County, on Route 58 at Main Drain Canal Bridge No 50-0013. | Repair erosion, clean and encase piers in concrete. | 775 | Yes | 775 | 796 | 796 | 796 | Yes | 893 | Yes | 893 | 645 | 645 | 945 | Yes | 334 | Yes | 334 | 202 | 202 | 335 | Yes | 830 | No | 830 | 0 | 0 | 823 | No | 910 | No | 910 | 85 | 85 | 175 | No | 2700 | No | 2700 | 0 | 0 | 2340 | No | 6442 | 6442 | 1728 | 1728 | 5414 |  | 2020-04-15 | 2020-05-05 |  |  | 2022-04-15 |  | 2023-07-03 | Yes | 2022-05-01 |  | 2023-07-03 | Yes | 2022-09-15 |  | 2023-11-29 | Yes |  |  | 2025-07-01 |  | 0 | Yes | No | No | Yes
375 | 06 | 6787 | TUL | 245 | Woodlake Bridge Replacement | Near Woodlake, at Yokohl Creek Bridge No 46-0011; also at Kaweah River Bridge No 46-0073 (PM 4.19/4.30). | Replace bridges to upgrade to current standards, facilitate bike lane shoulders, and upgrade guardrailing. | 1658 | Yes | 1658 | 1577 | 1577 | 1577 | No | 2486 | Yes | 2486 | 2392 | 2392 | 2392 | No | 645 | Yes | 645 | 346 | 346 | 600 | No | 3400 | Yes | 3400 | 248 | 248 | 3178 | No | 280 | No | 280 | 113 | 113 | 114 | No | 11159 | Yes | 11159 | 3372 | 3372 | 11159 | No | 19628 | 19628 | 8048 | 8048 | 19020 |  | 2019-08-14 | 2019-08-14 |  |  | 2021-03-15 | 2021-06-09 |  |  | 2021-04-01 | 2021-06-28 |  |  | 2021-10-19 | 2022-02-11 |  |  |  |  | 2023-08-11 |  | 11159 | No | No | No | No
376 | 06 | 6788 | TUL | 99 | Pixley-Earlimart Bridge Rail | In and near Pixley, at Avenue 48 Overcrossing (OC) No 46-0165 (PM 6.2), Davis Avenue OC No 46-0172 (PM 12.6), and Avenue 100 OC No 46-0173 (PM 12.8). | Upgrade bridge railing to current standards and install approach railings. | 740 | Yes | 740 | 389 | 389 | 389 | No | 1122 | Yes | 1122 | 706 | 706 | 706 | No | 30 | Yes | 30 | 8 | 8 | 27 | No | 1048 | Yes | 1048 | 643 | 643 | 1104 | Yes | 108 | No | 108 | 0 | 0 | 0 | No | 3112 | Yes | 3112 | 2573 | 2573 | 3112 | No | 6160 | 6160 | 4319 | 4319 | 5338 |  | 2019-11-01 | 2019-10-25 |  |  | 2021-01-15 | 2020-11-02 |  |  | 2021-02-01 | 2021-02-01 |  |  | 2021-10-15 | 2021-06-29 |  |  |  |  | 2022-07-29 |  | 3112 | No | No | No | No
377 | 06 | 6795 | TUL | 99 | Tul-Fre-Mad Pumping Plant Upgrades | In Tulare, Fresno and Madera Counties, on Route 99 at various locations. | Upgrade existing pumps and control systems at ten pumping plants. | 650 | Yes | 650 | 408 | 408 | 408 | No | 2060 | Yes | 2060 | 1447 | 1447 | 1447 | No | 620 | Yes | 620 | 45 | 45 | 615 | No | 2230 | Yes | 2230 | 1636 | 1636 | 2476 | Yes | 65 | No | 65 | 7 | 7 | 7 | No | 5381 | Yes | 5381 | 4630 | 4630 | 5381 | No | 11006 | 11006 | 8173 | 8173 | 10334 |  | 2018-07-13 | 2018-06-11 |  |  | 2019-11-08 | 2019-06-20 |  |  | 2019-11-20 | 2019-12-06 |  |  | 2020-05-11 | 2020-06-03 |  |  |  |  | 2022-08-15 |  | 5381 | No | No | No | No
378 | 06 | 6798 | KER | 184 | Morning Drive 3R Rehab | In and near Bakersfield, from 0.1 mile north of Edison Highway to 0.1 mile north of Chase Avenue. | Upgrade Americans with Disabilities Act (ADA) curbs and barrier railing, widen shoulders, cold plane pavement, place Hot Mix Asphalt (HMA) and Rubberized Hot Mix Asphalt (RHMA) pavement to rehabilitate roadway. | 1322 | Yes | 1322 | 1298 | 1298 | 1298 | No | 1800 | Yes | 1800 | 1565 | 1565 | 2192 | Yes | 250 | Yes | 250 | 226 | 226 | 332 | Yes | 1600 | No | 1600 | 0 | 0 | 1471 | No | 770 | No | 770 | 408 | 408 | 692 | No | 12900 | No | 12900 | 0 | 0 | 10875 | No | 18642 | 18642 | 3497 | 3497 | 16860 |  | 2020-10-01 | 2020-10-15 |  |  | 2022-04-01 |  | 2022-08-01 | Yes | 2022-05-02 |  | 2022-08-15 | Yes | 2022-11-14 |  | 2023-07-12 | Yes |  |  | 2024-01-02 |  | 0 | Yes | Yes | No | Yes
379 | 06 | 6800 | FRE | 99 | Selma to Fowler Rehab | In and near Selma and Fowler, from McCall Avenue Undercrossing to 0.5 mile north of Merced Street Undercrossing. | Replace pavement with Continuous Reinforced Concrete Pavement (CRCP). Update curb ramps to meet current Americans with Disabilities Act (ADA) standards. | 1130 | Yes | 1130 | 1088 | 1088 | 1088 | No | 2796 | Yes | 2796 | 2783 | 2783 | 2783 | No | 179 | Yes | 179 | 157 | 157 | 157 | No | 11000 | Yes | 11000 | 2876 | 2876 | 9484 | No | 153 | No | 153 | 49 | 49 | 49 | No | 70482 | Yes | 70482 | 29655 | 29655 | 70482 | No | 85740 | 85740 | 36608 | 36608 | 84043 | 2019-01-31 | 2018-12-18 | 2018-12-18 |  |  | 2020-03-03 | 2020-05-28 |  |  | 2020-04-14 | 2020-06-12 |  |  | 2020-08-25 | 2021-03-18 |  |  |  |  | 2024-11-22 |  | 70481 | No | No | No | No
380 | 06 | 6803 | KER | 184 | Weedpatch Hwy 3R Rehab | Near Bakersfield, from Dunnsmere Street to Breckenridge Road. | Upgrade Americans with Disabilities Act (ADA) curb ramps, install bike lanes, cold plane pavement, place Hot Mix Asphalt (HMA) and Rubberized Hot Mix Asphalt (RHMA) pavement, and construct sidewalks, bus turnouts, and improve pedestrian crossings as complete streets elements. | 2725 | Yes | 2725 | 2690 | 2690 | 2690 | No | 3000 | Yes | 3000 | 460 | 460 | 2547 | No | 2200 | Yes | 2200 | 747 | 747 | 1709 | No | 3100 | No | 3100 | 0 | 0 | 2668 | No | 2230 | No | 2230 | 284 | 284 | 3054 | Yes | 22400 | No | 22400 | 0 | 0 | 19800 | No | 35655 | 35655 | 4181 | 4181 | 32468 |  | 2020-12-15 | 2020-12-15 |  |  | 2023-04-04 |  | 2023-04-04 | No | 2023-04-14 |  | 2023-04-14 | No | 2023-11-20 |  | 2023-11-20 | No |  |  | 2025-11-20 |  | 0 | No | Yes | No | Yes
381 | 06 | 6805 | KER | 119 | Pumpkin Center 3R Rehab | Near Bakersfield, from 0.1 miles east of Ashe Road to Route 99 Separation. | Rehabilitate roadway with asphalt pavement, reconstruct ramp termini at southbound Route 99 offramp with concrete pavement, widen intersections and shoulders to meet current standards, add bicycle lanes, median lane to accommodate two-way turning, install drainage inlets and stormwater basin, sidewalks and upgrade Americans with Disabilities Act (ADA) ramps to current standards. | 3200 | Yes | 3200 | 2645 | 2645 | 2645 | No | 2500 | Yes | 2500 | 530 | 530 | 3491 | Yes | 4000 | Yes | 4000 | 445 | 445 | 3902 | No | 4600 | No | 4600 | 0 | 0 | 3512 | No | 15900 | Yes | 15900 | 171 | 171 | 15869 | No | 26500 | No | 26500 | 0 | 0 | 23000 | No | 56700 | 56700 | 3791 | 3791 | 52419 | 2021-03-25 | 2020-12-08 | 2020-12-08 |  |  | 2023-09-01 |  | 2023-09-01 | No | 2023-12-01 |  | 2023-12-01 | No | 2024-06-01 |  | 2024-06-01 | No |  |  | 2025-07-01 |  | 0 | No | Yes | No | Yes
382 | 06 | 6820 | KER | 5 | Lost Hills Rehab | Near Kettleman City, from 0.6 mile south of Twisselman Road Overcrossing to Kings County line. | Reconstruct the number two lane with Continuously Reinforced Concrete Pavement (CRCP) and grind the number one lane to rehabilitate pavement. | 440 | Yes | 440 | 439 | 439 | 439 | No | 1450 | Yes | 1450 | 1480 | 1480 | 1480 | Yes | 25 | Yes | 25 | 11 | 11 | 28 | Yes | 5242 | Yes | 5242 | 3435 | 3435 | 6579 | Yes | 65 | No | 65 | 0 | 0 | 0 | No | 43183 | Yes | 43183 | 23585 | 23585 | 36048 | No | 50405 | 50405 | 28950 | 28950 | 44574 | 2019-05-16 | 2019-01-24 | 2019-01-24 |  |  | 2019-09-06 | 2020-03-24 |  |  | 2019-10-04 | 2020-05-05 |  |  | 2020-04-12 | 2020-08-27 |  |  |  |  | 2023-03-01 |  | 26712 | No | Yes | No | No
383 | 06 | 6857 | MAD | 99 | COTTONWOOD CREEK BRIDGE REPLACEMENT (Br. No. 41-0065 L/R&S) | Near the city of Madera, at Cottonwood Creek Bridge No 41-065R, No 41-0065L and No 41-0065S. | Replace bridges to mitigate corrosion by chloride latent concrete. | 2840 | Yes | 2840 | 2819 | 2819 | 2819 | No | 3200 | Yes | 3200 | 2541 | 2541 | 3258 | Yes | 100 | Yes | 100 | 15 | 15 | 74 | No | 6100 | Yes | 6100 | 0 | 0 | 6341 | Yes | 172 | No | 172 | 48 | 48 | 92 | No | 24361 | Yes | 24361 | 0 | 0 | 28600 | Yes | 36773 | 36773 | 5423 | 5423 | 41184 |  | 2020-07-01 | 2020-07-09 |  |  | 2021-07-07 | 2021-08-03 |  |  | 2021-07-26 | 2021-09-10 |  |  | 2022-03-02 |  | 2022-07-22 | Yes |  |  | 2024-11-28 |  | 0 | Yes | Yes | No | No
384 | 06 | 6873 | KIN | 41 | Stratford Kings River Bridge Replacement | In and near Stratford, from 22nd Street to Laurel Avenue at the Kings River Bridge No 45-0007. | Replace 73-year old bridge due to extensive superstructure and substructure distress and susceptibility to liquefaction. (G13 Contingency). | 2550 | Yes | 2550 | 2535 | 2535 | 2535 | No | 2700 | Yes | 2700 | 1948 | 1948 | 2678 | No | 400 | Yes | 400 | 107 | 107 | 226 | No | 0 | No | 0 | 0 | 0 | 3954 | Yes | 319 | No | 319 | 73 | 73 | 338 | Yes | 0 | No | 0 | 0 | 0 | 26600 | Yes | 5969 | 5969 | 4663 | 4663 | 36331 |  | 2020-05-22 | 2020-10-06 |  |  | 2021-09-01 |  | 2022-11-25 | Yes | 2021-10-01 |  | 2022-11-28 | Yes | 2022-03-30 |  | 2023-05-29 | Yes |  |  | 2024-04-15 |  | 0 | Yes | Yes | No | No
385 | 06 | 6881 | FRE | 41 | Fre-41;99;168 & 180 Fiber Optic | In and near the city of Fresno, from 0.1 mile south of North Avenue to the Madera County line; also on Route 99 (PM 19.36/PM 21.9), Route 168 (PM R0.2L/R/PM R9.7), and Route 180 (PM R58.55/PM R59.85). | Replace and upgrade existing communication elements for the Transportation Management System (TMS). | 619 | Yes | 619 | 362 | 362 | 362 | No | 2009 | Yes | 2009 | 1993 | 1993 | 1993 | No | 165 | Yes | 165 | 32 | 32 | 93 | No | 1791 | Yes | 1791 | 156 | 156 | 1612 | No | 94 | No | 94 | 57 | 57 | 57 | No | 13056 | Yes | 13056 | 375 | 375 | 13056 | No | 17734 | 17734 | 2975 | 2975 | 17173 | 2019-01-31 | 2018-12-10 | 2018-12-10 |  |  | 2021-02-08 | 2021-06-24 |  |  | 2021-03-08 | 2021-06-24 |  |  | 2021-09-07 | 2021-12-02 |  |  |  |  | 2023-04-30 |  | 13056 | No | No | No | No
386 | 06 | 6894 | KER | 33 | Ker 33 Culvert Rehab | Near Taft, from 0.9 mile south of Henry Road to north of Cymric Road (north) at various locations. | Rehabilitate drainage systems. | 1700 | Yes | 1700 | 1639 | 1639 | 1639 | No | 1600 | Yes | 1600 | 3 | 3 | 1562 | No | 1500 | Yes | 1500 | 7 | 7 | 1238 | No | 1500 | No | 1500 | 0 | 0 | 1381 | No | 630 | No | 630 | 18 | 18 | 1086 | Yes | 4500 | No | 4500 | 0 | 0 | 4829 | Yes | 11430 | 11430 | 1667 | 1667 | 11735 |  | 2022-03-01 | 2022-04-05 |  |  | 2023-10-02 |  | 2023-10-02 | No | 2023-10-26 |  | 2023-10-26 | No | 2024-06-01 |  | 2024-06-03 | No |  |  | 2025-07-01 |  | 0 | Yes | Yes | Yes | No
387 | 06 | 6895 | KER | 5 | Fort Tejon 2R Rehab | Near Lebec, in the northbound direction from Los Angeles County line to south of Lebec Road. | Rehabilitate northbound roadway and upgrade guardrail and Transportation Management System (TMS) elements. | 1300 | Yes | 1300 | 996 | 996 | 996 | No | 1600 | Yes | 1600 | 1 | 1 | 1395 | No | 20 | Yes | 20 | 0 | 0 | 16 | No | 3000 | No | 3000 | 0 | 0 | 2834 | No | 50 | No | 50 | 0 | 0 | 34 | No | 25400 | No | 25400 | 0 | 0 | 26301 | Yes | 31370 | 31370 | 997 | 997 | 31576 |  | 2022-04-04 | 2022-04-05 |  |  | 2023-04-03 |  | 2023-04-03 | No | 2023-04-18 |  | 2023-04-18 | No | 2023-11-08 |  | 2023-11-08 | No |  |  | 2025-03-01 |  | 0 | No | No | No | Yes
388 | 06 | 6896 | KER | 166 | Maricopa Highway CAPM | In and near Maricopa, from Route 33 to 4.0 miles east of Basic School Road. | Rehabilitate pavement and culverts, upgrade guardrail and facilities to Americans with Disability Act (ADA) standards, and construct rumble strips. | 1600 | Yes | 1600 | 768 | 768 | 1522 | No | 1500 | No | 1500 | 0 | 0 | 1271 | No | 120 | No | 120 | 0 | 0 | 87 | No | 2000 | No | 2000 | 0 | 0 | 1808 | No | 120 | No | 120 | 0 | 0 | 175 | Yes | 10550 | No | 10550 | 0 | 0 | 9200 | No | 15890 | 15890 | 768 | 768 | 14063 |  | 2022-07-01 |  | 2022-08-01 | No | 2023-04-03 |  | 2023-04-03 | No | 2023-04-21 |  | 2023-04-21 | No | 2023-11-01 |  | 2023-11-01 | No |  |  | 2024-11-01 |  | 0 | No | No | No | No
389 | 06 | 6921 | FRE | 198 | Fresno 198 Culvert Rehab | In Fresno County, on Route 198 at various locations. | Improve drainage facilities by repairing or replacing culverts. | 3000 | Yes | 3000 | 1843 | 1843 | 1843 | No | 1600 | Yes | 1600 | 705 | 705 | 1951 | Yes | 700 | Yes | 700 | 423 | 423 | 810 | Yes | 2800 | No | 2800 | 0 | 0 | 2581 | No | 660 | No | 660 | 134 | 134 | 438 | No | 11700 | No | 11700 | 0 | 0 | 14900 | Yes | 20460 | 20460 | 3105 | 3105 | 22523 |  | 2020-12-15 | 2020-12-15 |  |  | 2023-01-15 |  | 2023-01-15 | No | 2023-02-15 |  | 2023-02-15 | No | 2023-09-11 |  | 2023-09-11 | No |  |  | 2025-11-28 |  | 0 | No | Yes | No | Yes
390 | 06 | 6923 | FRE | Var | TMS Detection Repair | In Fresno, Kern, Kings, Madera, and Tulare Counties, at various locations. | Repair Transportation Management System (TMS) elements. | 400 | Yes | 400 | 213 | 213 | 213 | No | 900 | Yes | 900 | 892 | 892 | 892 | No | 10 | Yes | 10 | 10 | 10 | 10 | No | 1600 | Yes | 1600 | 289 | 289 | 1580 | No | 70 | No | 70 | 0 | 0 | 66 | No | 3862 | Yes | 3862 | 1950 | 1950 | 3862 | No | 6842 | 6842 | 3354 | 3354 | 6623 |  | 2019-09-02 | 2019-11-05 |  |  | 2020-12-01 | 2020-12-23 |  |  | 2021-01-15 | 2021-01-15 |  |  | 2021-07-06 | 2021-07-08 |  |  |  |  | 2022-11-30 |  | 3862 | No | No | No | No
391 | 06 | 6925 | KER | 178 | Kern Canyon Culvert Rehab | Near Bakersfield, from east of Miramonte Drive to Vista Grande Drive. | Repair, replace, and/or clean culverts. | 2800 | Yes | 2800 | 1998 | 1998 | 1998 | No | 900 | Yes | 900 | 521 | 521 | 847 | No | 480 | Yes | 480 | 39 | 39 | 435 | No | 0 | Yes | 0 | 0 | 0 | 1495 | Yes | 465 | No | 465 | 78 | 78 | 96 | No | 0 | Yes | 0 | 0 | 0 | 6043 | Yes | 4645 | 4645 | 2636 | 2636 | 10914 |  | 2020-10-29 | 2021-01-04 |  |  | 2022-01-07 | 2022-04-28 |  |  | 2022-01-14 | 2022-04-29 |  |  | 2022-08-01 |  | 2022-10-03 | No |  |  | 2023-08-01 |  | 0 | No | Yes | No | No
392 | 06 | 6928 | KIN | 41 | Kettleman 2R Rehab | Near Kettleman City, from Quail Avenue to Nevada Avenue. | Rehabilitate roadway, upgrade lighting and guardrail, replace signs, construct rumble strips, and install Transportation Management System (TMS) elements. | 1000 | Yes | 1000 | 615 | 615 | 615 | No | 1800 | Yes | 1800 | 423 | 423 | 1965 | Yes | 20 | Yes | 20 | 9 | 9 | 33 | Yes | 2700 | No | 2700 | 0 | 0 | 2234 | No | 90 | No | 90 | 25 | 25 | 19 | No | 18200 | No | 18200 | 0 | 0 | 17000 | No | 23810 | 23810 | 1072 | 1072 | 21866 |  | 2021-07-29 | 2021-07-29 |  |  | 2022-12-01 |  | 2022-12-01 | No | 2023-01-06 |  | 2023-01-06 | No | 2023-06-15 |  | 2023-07-15 | Yes |  |  | 2024-11-01 |  | 0 | Yes | No | No | No
393 | 06 | 6934 | FRE | 145 | McMullin Grade CAPM | Near Helm, from Kamm Avenue to Manning Avenue. | Pavement rehabilitation. | 820 | Yes | 820 | 538 | 538 | 538 | No | 860 | Yes | 860 | 538 | 538 | 538 | No | 30 | Yes | 30 | 11 | 11 | 20 | No | 1300 | Yes | 1300 | 406 | 406 | 1250 | No | 40 | No | 40 | 12 | 12 | 13 | No | 4858 | Yes | 4858 | 4113 | 4113 | 4858 | No | 7908 | 7908 | 5618 | 5618 | 7217 |  | 2020-04-01 | 2020-03-26 |  |  | 2020-12-22 | 2021-01-27 |  |  | 2021-01-22 | 2021-01-28 |  |  | 2021-06-28 | 2021-07-01 |  |  |  |  | 2022-07-15 |  | 4858 | No | No | No | No
394 | 06 | 6935 | KIN | 41 | Stratford-Lemoore CAPM | Near Stratford, from Nevada Avenue to Route 198. | Rehabilitate pavement, replace signs, upgrade guardrail, construct rumble strips, rehabilitate drainage systems, and upgrade facilities to Americans with Disabilities Act (ADA) standards. | 1800 | Yes | 1800 | 669 | 669 | 1593 | No | 1800 | No | 1800 | 0 | 0 | 1603 | No | 130 | No | 130 | 0 | 0 | 128 | No | 3100 | No | 3100 | 0 | 0 | 2814 | No | 170 | No | 170 | 5 | 5 | 151 | No | 16400 | No | 16400 | 0 | 0 | 16400 | No | 23400 | 23400 | 674 | 674 | 22689 |  | 2022-04-04 |  | 2022-06-30 | No | 2023-10-30 |  | 2023-10-30 | No | 2023-12-06 |  | 2023-12-06 | No | 2024-05-01 |  | 2024-05-01 | No |  |  | 2025-07-01 |  | 0 | No | No | No | No
395 | 06 | 6944 | TUL | 99 | Tulare City Rehab | In the city of Tulare, from Paige Avenue to Prosperity Avenue Overcrossing. | Rehabilitate roadway, upgrade lighting and Transportation Management System (TMS) elements, replace signs, rehabilitate drainage systems, and enhance highway worker safety. (G13 Contingency). | 1800 | Yes | 1800 | 469 | 469 | 469 | No | 2800 | Yes | 2800 | 42 | 42 | 2741 | No | 103 | Yes | 103 | 1 | 1 | 101 | No | 0 | No | 0 | 0 | 0 | 3396 | Yes | 500 | No | 500 | 0 | 0 | 60 | No | 0 | No | 0 | 0 | 0 | 29800 | Yes | 5203 | 5203 | 512 | 512 | 36567 |  | 2021-12-01 | 2021-12-16 |  |  | 2023-11-01 |  | 2023-10-01 | No | 2023-11-02 |  | 2023-11-02 | No | 2024-06-03 |  | 2024-06-03 | No |  |  | 2026-07-01 |  | 0 | No | Yes | No | No
396 | 06 | 6950 | KER | 33 | South Taft Rehab | In and near Taft, from Cadet Road to south of Main Street/Gardner Field Road. | Rehabilitate roadway and drainage systems, replace sign panels, widen shoulders, install Transportation Management System (TMS) elements, and upgrade facilities to Americans with Disabilities Act (ADA) standards. | 2100 | Yes | 2100 | 0 | 0 | 1816 | No | 1800 | No | 1800 | 0 | 0 | 1760 | No | 1500 | No | 1500 | 0 | 0 | 1314 | No | 2600 | No | 2600 | 0 | 0 | 2286 | No | 7200 | No | 7200 | 0 | 0 | 7108 | No | 11300 | No | 11300 | 0 | 0 | 11300 | No | 26500 | 26500 | 0 | 0 | 25584 |  |  |  | 2024-12-02 |  |  |  | 2026-02-12 |  |  |  | 2026-03-16 |  |  |  | 2026-12-14 |  |  |  | 2028-11-01 |  | 0 | No | No | No | Yes
397 | 06 | 6957 | KER | 58 | Reward CAPM | Near McKittrick, from San Luis Obispo County line to Route 33. | Pavement rehabilitation, repair culverts, and upgrade Intelligent Transportation System (ITS) field elements. | 1500 | Yes | 1500 | 1250 | 1250 | 1250 | No | 1500 | Yes | 1500 | 929 | 929 | 929 | No | 233 | Yes | 233 | 41 | 41 | 226 | No | 1800 | Yes | 1800 | 402 | 402 | 1821 | Yes | 2669 | No | 2669 | 91 | 91 | 357 | No | 5615 | Yes | 5615 | 2533 | 2533 | 5615 | No | 13317 | 13317 | 5246 | 5246 | 10198 |  | 2020-07-16 | 2020-08-25 |  |  | 2021-02-01 | 2021-04-26 |  |  | 2021-04-15 | 2021-04-27 |  |  | 2021-10-03 | 2021-10-07 |  |  |  |  | 2022-08-01 |  | 5615 | No | No | No | No
398 | 06 | 6960 | KER | 155 | Delano SR-155 Rehab (3R) | In Deleno, from Fremont Street to west of Browning Road. | Rehabilitate roadway, widen shoulders, upgrade facilities to Americans with Disabilities Act (ADA) standards, and rehabilitate drainage systems. | 1700 | Yes | 1700 | 1451 | 1451 | 1451 | No | 2300 | Yes | 2300 | 0 | 0 | 2377 | Yes | 540 | Yes | 540 | 0 | 0 | 493 | No | 1800 | No | 1800 | 0 | 0 | 1534 | No | 1400 | No | 1400 | 20 | 20 | 1146 | No | 9000 | No | 9000 | 0 | 0 | 9268 | Yes | 16740 | 16740 | 1471 | 1471 | 16269 |  | 2022-03-01 | 2022-03-21 |  |  | 2024-03-01 |  | 2024-03-01 | No | 2024-03-15 |  | 2024-03-15 | No | 2024-09-01 |  | 2024-09-01 | No |  |  | 2025-12-01 |  | 0 | No | No | No | No
399 | 06 | 6963 | TUL | 99 | Delano to Pixley Rehab | Near Earlimart, from County line Road Overcrossing to 0.7 mile north of Court Avenue Overcrossing. | Rehabilitate roadway, construct median concrete barrier, replace signs, rehabilitate drainage systems, upgrade Transportation Management System (TMS) elements, and replace signs. (G13 Contingency). | 3360 | Yes | 3360 | 2510 | 2510 | 3624 | Yes | 4450 | No | 4450 | 0 | 0 | 3512 | No | 400 | No | 400 | 0 | 0 | 260 | No | 0 | No | 0 | 0 | 0 | 7185 | Yes | 225 | No | 225 | 0 | 0 | 3189 | Yes | 0 | No | 0 | 0 | 0 | 56800 | Yes | 8435 | 8435 | 2510 | 2510 | 74570 |  | 2023-05-05 |  | 2023-05-05 | No | 2024-04-02 |  | 2024-04-02 | No | 2024-05-03 |  | 2024-05-03 | No | 2024-10-14 |  | 2024-10-14 | No |  |  | 2026-10-01 |  | 0 | No | Yes | No | Yes
400 | 06 | 6967 | TUL | 99 | Tul 99 Culvert Rehab | In and near the city of Tulare, from 0.7 mile north of Avenue 152 Overcrossing to Fresno County line (PM 20.2/R53.939) at various locations. | Rehabilitate drainage systems. | 2350 | Yes | 2350 | 1470 | 1470 | 2425 | Yes | 2350 | No | 2350 | 0 | 0 | 2427 | Yes | 610 | No | 610 | 0 | 0 | 511 | No | 2610 | No | 2610 | 0 | 0 | 2181 | No | 150 | No | 150 | 0 | 0 | 391 | Yes | 9900 | No | 9900 | 0 | 0 | 9900 | No | 17970 | 17970 | 1470 | 1470 | 17835 |  | 2022-10-05 |  | 2022-10-05 | No | 2024-04-01 |  | 2024-04-01 | No | 2024-04-15 |  | 2024-04-15 | No | 2024-11-01 |  | 2024-11-01 | No |  |  | 2025-08-01 |  | 0 | No | Yes | No | Yes
401 | 06 | 6970 | FRE | 5 | Panoche CAPM | Near Mendota, from 1.0 mile south of Kamm Avenue 0.2 mile south of Panoche Road. | Pavement rehabilitation, repair culverts and upgrade Transportation Management Systems (TMS) field elements. | 2000 | Yes | 2000 | 1814 | 1814 | 1814 | No | 850 | Yes | 850 | 688 | 688 | 688 | No | 210 | Yes | 210 | 0 | 0 | 0 | No | 5200 | Yes | 5200 | 115 | 115 | 5142 | No | 3100 | No | 3100 | 165 | 165 | 2173 | No | 30381 | Yes | 30381 | 0 | 0 | 26609 | No | 41741 | 41741 | 2782 | 2782 | 36426 | 2021-05-12 | 2021-03-26 | 2021-03-26 |  |  | 2021-08-02 | 2021-08-06 |  |  | 2021-12-01 | 2021-12-01 |  |  | 2022-07-01 | 2022-07-01 |  |  |  |  | 2024-09-06 |  | 26608 | No | Yes | No | Yes
402 | 06 | 6971 | FRE | 5 | Shields to Nees CAPM | Near Los Banos, from Shields Avenue to Merced County line (PM 66.159). | Rehabilitate pavement, install Transportation Management System (TMS) elements, and upgrade signs, guardrail, and lighting. | 1491 | Yes | 1491 | 432 | 432 | 432 | No | 1100 | Yes | 1100 | 97 | 97 | 939 | No | 19 | Yes | 19 | 2 | 2 | 24 | Yes | 2130 | No | 2130 | 0 | 0 | 1956 | No | 10 | No | 10 | 0 | 0 | 53 | Yes | 16000 | No | 16000 | 0 | 0 | 16000 | No | 20750 | 20750 | 531 | 531 | 19404 |  | 2021-10-08 | 2021-10-14 |  |  | 2022-08-01 |  | 2022-12-16 | Yes | 2022-10-07 |  | 2023-01-13 | Yes | 2023-05-01 |  | 2023-07-03 | Yes |  |  | 2024-08-02 |  | 0 | Yes | No | No | No
403 | 06 | 6972 | FRE | 33 | Firebaugh 3R Rehab | In and near Firebaugh, from Morris Kyle Drive to 0.6 mile north of Clyde Fannon Drive. | Rehabilitate roadway, replace signs, install Transportation Management System (TMS) elements, upgrade guardrail, upgrade facilities to Americans with Disabilities Act (ADA) standards, replace signs, upgrade traffic signals and lighting, and rehabilitate drainage systems. | 1700 | Yes | 1700 | 1243 | 1243 | 1243 | No | 2100 | Yes | 2100 | 0 | 0 | 2031 | No | 150 | Yes | 150 | 0 | 0 | 345 | Yes | 2800 | No | 2800 | 0 | 0 | 2460 | No | 260 | No | 260 | 21 | 21 | 275 | Yes | 12000 | No | 12000 | 0 | 0 | 12500 | Yes | 19010 | 19010 | 1264 | 1264 | 18854 |  | 2022-03-18 | 2022-06-23 |  |  | 2023-04-07 |  | 2023-04-07 | No | 2023-04-28 |  | 2023-04-28 | No | 2023-10-26 |  | 2023-10-26 | No |  |  | 2025-04-01 |  | 0 | No | No | No | No
404 | 06 | 6978 | KER | 33 | Blackwell's Corner CAPM | Near McKittrick, from south of Lokern Road to 1.2 miles south of Route 46. | Rehabilitate pavement, replace signs, install Transportation Management System (TMS) elements, and rehabilitate drainage systems. | 1800 | Yes | 1800 | 1669 | 1669 | 1669 | No | 0 | Yes | 0 | 0 | 0 | 1257 | Yes | 0 | Yes | 0 | 0 | 0 | 302 | Yes | 2300 | No | 2300 | 0 | 0 | 2036 | No | 220 | No | 220 | 8 | 8 | 190 | No | 16600 | No | 16600 | 0 | 0 | 16274 | No | 20920 | 20920 | 1677 | 1677 | 21728 |  | 2022-04-15 | 2022-05-03 |  |  | 2023-04-15 |  | 2023-04-15 | No | 2023-04-18 |  | 2023-04-18 | No | 2023-11-03 |  | 2023-11-03 | No |  |  | 2024-12-01 |  | 0 | No | Yes | No | No
405 | 06 | 6981 | KER | 58 | Edison 2R Rehab | Near Edison, from west of Tejon Highway Overcrossing to 2.5 miles west of General Beale Road. | Rehabilitate roadway, replace signs, rehabilitate drainage systems, and upgrade guardrail and Transportation Management System (TMS) elements. | 910 | Yes | 910 | 562 | 562 | 562 | No | 1600 | Yes | 1600 | 75 | 75 | 1480 | No | 50 | Yes | 50 | 0 | 0 | 32 | No | 1500 | No | 1500 | 0 | 0 | 1418 | No | 10 | No | 10 | 0 | 0 | 14 | Yes | 10200 | No | 10200 | 0 | 0 | 10200 | No | 14270 | 14270 | 637 | 637 | 13706 |  | 2022-01-14 | 2022-01-28 |  |  | 2023-02-15 |  | 2023-02-15 | No | 2023-02-24 |  | 2023-04-10 | No | 2023-09-15 |  | 2023-09-15 | No |  |  | 2024-10-25 |  | 0 | Yes | No | No | No
406 | 06 | 6985 | KER | 5 | Wheeler Ridge CAPM | Near Grapevine, from Grapevine Road Undercrossing to Route 5/99 Separation. | Rehabilitate pavement, replace signs, install Transportation Management System (TMS) elements, and rehabilitate drainage systems. | 1400 | Yes | 1400 | 717 | 717 | 1000 | No | 2200 | No | 2200 | 0 | 0 | 1908 | No | 30 | No | 30 | 0 | 0 | 19 | No | 1900 | No | 1900 | 0 | 0 | 1658 | No | 20 | No | 20 | 4 | 4 | 13 | No | 16800 | No | 16800 | 0 | 0 | 16800 | No | 22350 | 22350 | 721 | 721 | 21398 |  | 2022-07-05 |  | 2022-07-05 | No | 2023-08-15 |  | 2023-11-01 | No | 2023-11-16 |  | 2023-11-16 | No | 2024-08-30 |  | 2024-08-30 | No |  |  | 2025-03-28 |  | 0 | No | No | No | No
407 | 06 | 7005 | MAD | 145 | Downtown Madera CAPM | In and near the city of Madera, from south of Avenue 13 to 1.0 mile north of Tozer Street. | Rehabilitate pavement, install Transportation Management System (TMS) elements, construct rumble strips, replace signs, rehabilitate drainage systems, install street lighting, construct curb extensions/bulb-outs, and restripe roadway to install bike lanes as complete streets elements. | 1080 | Yes | 1080 | 1027 | 1027 | 1027 | No | 0 | Yes | 0 | 0 | 0 | 2887 | Yes | 0 | Yes | 0 | 0 | 0 | 365 | Yes | 2000 | No | 2000 | 0 | 0 | 1582 | No | 300 | No | 300 | 3 | 3 | 209 | No | 13400 | No | 13400 | 0 | 0 | 13400 | No | 16780 | 16780 | 1030 | 1030 | 19470 |  | 2022-04-01 | 2022-05-03 |  |  | 2024-04-01 |  | 2024-04-01 | No | 2024-05-01 |  | 2024-05-01 | No | 2024-10-01 |  | 2024-10-01 | No |  |  | 2025-11-01 |  | 0 | No | Yes | No | No
408 | 06 | 7008 | TUL | 63 | Visalia Mall CAPM | In Visalia, from south of Caldwell Avenue to Route 198. | Rehabilitate pavement, upgrade Transportation Management System (TMS) elements, replace signs, and upgrade facilities to Americans with Disabilities Act (ADA) standards. | 1220 | Yes | 1220 | 849 | 849 | 849 | No | 2590 | Yes | 2590 | 596 | 596 | 2700 | Yes | 1180 | Yes | 1180 | 234 | 234 | 1356 | Yes | 2500 | No | 2500 | 0 | 0 | 2279 | No | 365 | No | 365 | 16 | 16 | 328 | No | 11800 | No | 11800 | 0 | 0 | 11800 | No | 19655 | 19655 | 1695 | 1695 | 19312 |  | 2021-06-29 | 2021-06-29 |  |  | 2023-03-01 |  | 2023-03-01 | No | 2023-03-06 |  | 2023-03-15 | No | 2023-08-30 |  | 2023-08-30 | No |  |  | 2025-01-06 |  | 0 | No | No | No | Yes
409 | 06 | 7015 | TUL | 198 | Tul 198 Culvert Rehab | In Tulare County, from Kings County line to east of Sequoia National Park Boundary at various locations. | Rehabilitate drainage systems. | 3515 | Yes | 3515 | 2069 | 2069 | 2069 | No | 3298 | No | 3298 | 0 | 0 | 2505 | No | 1759 | No | 1759 | 0 | 0 | 1518 | No | 3027 | No | 3027 | 0 | 0 | 2826 | No | 337 | No | 337 | 28 | 28 | 576 | Yes | 11088 | No | 11088 | 0 | 0 | 11548 | Yes | 23024 | 23024 | 2097 | 2097 | 21042 |  | 2022-04-20 | 2022-07-06 |  |  | 2023-05-24 |  | 2023-05-24 | No | 2023-05-30 |  | 2023-05-25 | No | 2024-02-01 |  | 2024-02-01 | No |  |  | 2025-08-01 |  | 0 | No | Yes | No | No
410 | 06 | 7064 | FRE | 41 | FRESNO SR 41 REHAB | Near the city of Fresno, Caruthers, Camden, and Riverdale, from King County line to north of East Elkhorn Avenue. | Rehabilitate pavement, install Transportation Management System (TMS) elements, and replace signal. | 500 | Yes | 500 | 0 | 0 | 567 | Yes | 1800 | No | 1800 | 0 | 0 | 1480 | No | 40 | No | 40 | 0 | 0 | 8 | No | 2400 | No | 2400 | 0 | 0 | 1214 | No | 60 | No | 60 | 0 | 0 | 60 | No | 12400 | No | 12400 | 0 | 0 | 12400 | No | 17200 | 17200 | 0 | 0 | 15729 |  |  |  | 2023-03-31 |  |  |  | 2024-05-01 |  |  |  | 2024-07-01 |  |  |  | 2024-12-02 |  |  |  | 2026-12-01 |  | 0 | No | No | No | No
411 | 06 | 7070 | KER | 5 | KER I5 CAPM | Near Bakersfield, from Route 99 to 0.9 mile north of Old River Road. | Rehabilitate roadway, upgrade guardrail, signs, and Transportation Management System (TMS) elements, and enhance highway worker safety. | 1470 | Yes | 1470 | 0 | 0 | 1455 | No | 1850 | No | 1850 | 0 | 0 | 1708 | No | 20 | No | 20 | 0 | 0 | 18 | No | 3430 | No | 3430 | 0 | 0 | 2981 | No | 53 | No | 53 | 0 | 0 | 52 | No | 28844 | No | 28844 | 0 | 0 | 28844 | No | 35667 | 35667 | 0 | 0 | 35058 |  |  |  | 2024-02-16 |  |  |  | 2025-02-03 |  |  |  | 2025-05-30 |  |  |  | 2025-12-18 |  |  |  | 2027-04-01 |  | 0 | No | No | No | No
412 | 06 | 7071 | FRE | 180 | Fresno County Culvert Improvements | In Fresno County, on Routes 180, 5, 33, 41, 63, 168, 198, 245, and 269 at various locations. | Rehabilitate drainage systems. | 2460 | Yes | 2460 | 0 | 0 | 2412 | No | 1960 | No | 1960 | 0 | 0 | 1793 | No | 955 | No | 955 | 0 | 0 | 865 | No | 2120 | No | 2120 | 0 | 0 | 1803 | No | 890 | No | 890 | 0 | 0 | 810 | No | 9340 | No | 9340 | 0 | 0 | 9333 | No | 17725 | 17725 | 0 | 0 | 17016 |  |  |  | 2023-08-01 |  |  |  | 2025-10-24 |  |  |  | 2025-11-05 |  |  |  | 2026-05-29 |  |  |  | 2028-04-07 |  | 0 | No | No | No | No
413 | 07 | 3734 | LA | 213 | Storm Drain Repair | In Rancho Palos Verdes, at 0.5 mile south of Palos Verdes Drive. | Replace two damaged drainage systems. | 402 | Yes | 402 | 333 | 333 | 333 | No | 1023 | Yes | 1023 | 817 | 817 | 817 | No | 310 | Yes | 310 | 303 | 303 | 318 | Yes | 423 | Yes | 423 | 1 | 1 | 412 | No | 260 | No | 260 | 47 | 47 | 260 | No | 1224 | Yes | 1224 | 0 | 0 | 1224 | No | 3642 | 3642 | 1501 | 1501 | 3364 |  | 2018-08-17 | 2018-09-28 |  |  | 2020-02-28 | 2020-06-29 |  |  | 2020-03-30 | 2020-06-30 |  |  | 2019-10-31 | 2021-11-25 |  |  |  |  | 2023-07-28 |  | 1224 | No | No | No | No
414 | 07 | 3985 | LA | 5 | I-5 HOV/Empire Ave & Burbank Blvd (Segments 2 & 3) | In Los Angeles County, on Route 5, from south of Magnolia Boulevard to just north of Buena Vista. | Construct one HOV lane in each direction and Empire Avenue Interchange. | 1173 | No | 0 | 877 | 0 | 877 | No | 49630 | No | 1630 | 48749 | 1597 | 48749 | No | 5062 | No | 230 | 4236 | 51 | 4368 | No | 55794 | Yes | 2261 | 46813 | 2261 | 48756 | No | 65481 | No | -19 | 56447 | -19 | 9201 | No | 289333 | Yes | 14195 | 252985 | 12434 | 289333 | No | 466473 | 18297 | 410107 | 16324 | 401284 |  | 2002-06-28 | 2000-12-29 |  |  | 2012-05-15 | 2012-05-23 |  |  | 2012-05-23 | 2012-05-23 |  |  | 2012-12-01 | 2012-12-20 |  |  | 2016-05-30 |  | 2023-07-14 | Yes | 195787 | Yes | Yes | No | No
415 | 07 | 4496 | VEN | 33 | Scour Mitigation & Rail Upgrade | Near Oak View, at San Antonio Creek Bridge No 52-0065. | Scour mitigation and bridge rail upgrade. | 2020 | Yes | 2020 | 1897 | 1897 | 1897 | No | 1423 | Yes | 1423 | 1416 | 1416 | 1416 | No | 600 | Yes | 600 | 536 | 536 | 597 | No | 2795 | Yes | 2795 | 664 | 664 | 2820 | Yes | 2753 | No | 2753 | 218 | 218 | 107 | No | 6176 | Yes | 6176 | 151 | 151 | 6176 | No | 15767 | 15767 | 4882 | 4882 | 13013 |  | 2017-06-30 | 2017-06-30 |  |  | 2019-01-04 | 2019-01-10 |  |  | 2019-01-25 | 2019-06-28 |  |  | 2019-09-06 | 2021-06-30 |  |  |  |  | 2024-03-22 |  | 6176 | No | No | No | No
416 | 07 | 4498 | LA | 1 | TRANCAS CREEK BRIDGE | In Malibu, from Guernsey Avenue to Trancas Canyon Road/Broad Beach Road. | Replace bridge. | 2737 | Yes | 2737 | 2721 | 2721 | 2721 | No | 3500 | Yes | 3500 | 3448 | 3448 | 3448 | No | 2000 | Yes | 2000 | 1476 | 1476 | 1715 | No | 3658 | Yes | 3658 | 956 | 956 | 3662 | Yes | 31716 | No | 31716 | 522 | 522 | 4019 | No | 12316 | Yes | 12316 | 3092 | 3092 | 12316 | No | 55927 | 55927 | 12215 | 12215 | 27881 | 2018-10-17 | 2017-06-30 | 2017-06-30 |  |  | 2020-08-21 | 2020-09-11 |  |  | 2020-09-30 | 2020-10-09 |  |  | 2021-03-30 | 2021-03-09 |  |  |  |  | 2027-09-30 |  | 12315 | No | No | No | No
417 | 07 | 4687 | VEN | 101 | Ven 101 Padre Juan Rehab | Near Mussel Shoals, from 0.5 mile south of Padre Juan Canyon Road to 0.3 mile north of Punta Gorda Pedestrian Undercrossing. | Rehabilitate roadway. | 530 | Yes | 530 | 509 | 509 | 509 | No | 3300 | Yes | 3300 | 3206 | 3206 | 3206 | No | 200 | Yes | 200 | 44 | 44 | 194 | No | 6340 | Yes | 6340 | 2552 | 2552 | 6455 | Yes | 150 | No | 150 | 1 | 1 | 150 | No | 36947 | Yes | 36947 | 13502 | 13502 | 36947 | No | 47467 | 47467 | 19814 | 19814 | 47461 | 2018-12-06 | 2018-09-28 | 2018-09-28 |  |  | 2020-01-10 | 2020-03-16 |  |  | 2020-02-14 | 2020-06-24 |  |  | 2020-08-28 | 2020-12-24 |  |  |  |  | 2023-12-22 |  | 36947 | No | No | No | No
418 | 07 | 4688 | VEN | 23 | VEN-23 REHAB | In and near cities of Thousand Oaks and Moorpark, from Route 101 to Route 118 (PM R11.451). | Rehabilitate pavement. | 1630 | Yes | 1630 | 1627 | 1627 | 1627 | No | 7500 | Yes | 7500 | 5079 | 5079 | 5079 | No | 100 | Yes | 100 | 18 | 18 | 90 | No | 14721 | Yes | 14721 | 9689 | 9689 | 14990 | Yes | 860 | No | 860 | 0 | 0 | 860 | No | 76622 | Yes | 76622 | 62793 | 62793 | 76622 | No | 101433 | 101433 | 79206 | 79206 | 99268 | 2018-10-17 | 2017-09-28 | 2017-09-28 |  |  | 2019-05-10 | 2019-06-13 |  |  | 2019-06-14 | 2019-06-28 |  |  | 2020-03-10 | 2020-03-02 |  |  |  |  | 2025-12-31 |  | 76621 | No | No | No | No
419 | 07 | 4699 | LA | 60 | Pavement Rehab | In and near Monterey Park, Montebello, Rosemead, and South El Monte, from 0.5 miles west of Route 710 to Route 605; also on Route 710, from 0.5 miles south to 0.5 miles north of Route 60. | Rehabilitate pavement. | 1173 | No | 1173 | 1170 | 1170 | 1170 | No | 9990 | Yes | 9990 | 9983 | 9983 | 9983 | No | 481 | Yes | 481 | 465 | 465 | 467 | No | 30000 | Yes | 30000 | 16276 | 16276 | 17924 | No | 165 | No | 165 | 86 | 86 | 1 | No | 127180 | Yes | 127180 | 119298 | 119298 | 125989 | No | 168989 | 168989 | 147278 | 147278 | 155534 | 2019-03-14 | 2015-08-31 | 2015-08-31 |  |  | 2018-05-29 | 2018-05-29 |  |  | 2019-01-14 | 2019-01-14 |  |  | 2019-09-30 | 2019-06-26 |  |  |  |  | 2024-02-02 |  | 116799 | No | No | No | No
420 | 07 | 4704 | LA | 91 | Seismic Retrofit | In Compton, at Compton Creek Bridge Overhead and offramp No 53-2235 and No 53-2237S; also in Long Beach, on Routes 710 and 110, at Harbor Scenic Drive Overhead No 53-2934 (PM 6.0) and Gaffy Street Bridge No 53-0397Y (PM R0.8). | Bridge seismic retrofit and bridge rail upgrade. (G13 Contingency). | 2260 | Yes | 2260 | 1692 | 1692 | 1692 | No | 3800 | Yes | 3800 | 1995 | 1995 | 3697 | No | 175 | Yes | 175 | 75 | 75 | 172 | No | 0 | No | 0 | 0 | 0 | 3133 | Yes | 1926 | No | 1926 | 59 | 59 | 1946 | Yes | 0 | No | 0 | 0 | 0 | 12833 | Yes | 8161 | 8161 | 3821 | 3821 | 23473 |  | 2020-09-30 | 2020-10-21 |  |  | 2022-02-25 |  | 2023-03-24 | Yes | 2022-03-30 |  | 2023-03-30 | Yes | 2022-11-30 |  | 2024-01-11 | Yes |  |  | 2025-01-30 |  | 0 | Yes | Yes | No | No
421 | 07 | 4712 | LA | 10 | LANE REPLACEMENT | In Baldwin Park and West Covina, from Route 605 to 0.2 mile west of Citrus Street. | Rehabilitate roadway. | 1289 | Yes | 1289 | 1272 | 1272 | 1272 | No | 8385 | Yes | 8385 | 3971 | 3971 | 3971 | No | 23 | Yes | 23 | 22 | 22 | 23 | No | 8444 | Yes | 8444 | 3487 | 3487 | 8615 | Yes | 147 | No | 147 | 7 | 7 | 96 | No | 53590 | Yes | 53590 | 36181 | 36181 | 53590 | No | 71878 | 71878 | 44940 | 44940 | 67567 | 2018-10-17 | 2018-06-20 | 2018-06-20 |  |  | 2020-02-26 | 2020-04-08 |  |  | 2020-02-28 | 2020-06-30 |  |  | 2021-01-15 | 2020-12-17 |  |  |  |  | 2024-06-14 |  | 53590 | No | No | No | Yes
422 | 07 | 4718 | LA | 57 | Lane Replacement | In and near Diamond Bar, from the Orange County line to Route 60. | Pavement rehabilitation. | 50 | No | 50 | 47 | 47 | 47 | No | 9900 | Yes | 9900 | 7707 | 7707 | 7707 | No | 10 | Yes | 10 | 8 | 8 | 9 | No | 13000 | Yes | 13000 | 6754 | 6754 | 13131 | Yes | 70 | No | 70 | 59 | 59 | 10 | No | 70316 | Yes | 70316 | 31508 | 31508 | 70316 | No | 93346 | 93346 | 46083 | 46083 | 91220 | 2018-10-17 | 2018-01-03 | 2018-01-03 |  |  | 2019-04-10 | 2019-03-07 |  |  | 2019-05-31 | 2019-06-18 |  |  | 2020-01-10 | 2020-06-29 |  |  |  |  | 2025-03-17 |  | 70316 | No | No | No | Yes
423 | 07 | 4721 | LA | 405 | REPLACE DRAINAGE INLETS | In Carson, at Dolores Yard Overhead No 53-1168. | Upgrade bridge drainage system to improve safety and extend the life and serviceability of the bridge. | 400 | Yes | 400 | 365 | 365 | 365 | No | 886 | Yes | 886 | 848 | 848 | 885 | No | 300 | Yes | 300 | 269 | 269 | 292 | No | 945 | Yes | 945 | 0 | 0 | 941 | No | 2657 | No | 2657 | 750 | 750 | 1953 | No | 2554 | Yes | 2554 | 0 | 0 | 2193 | No | 7742 | 7742 | 2232 | 2232 | 6629 |  | 2018-09-28 | 2018-09-28 |  |  | 2021-03-01 | 2022-01-05 |  |  | 2021-03-30 | 2022-03-08 |  |  | 2022-01-31 |  | 2023-07-05 | Yes |  |  | 2024-07-05 |  | 0 | Yes | No | No | No
424 | 07 | 4770 | LA | 101 | Pavement Rehab and ADA curb ramps | In the cities of Los Angeles and Calabasas, from Route 170 to Las Virgenes Road (PM 11.8L/31.1). | Rehabilitate pavement, construct and upgrade Americans with Disabilities Act (ADA) curb ramps. | 1074 | Yes | 1074 | 902 | 902 | 902 | No | 2474 | Yes | 2474 | 2449 | 2449 | 2449 | No | 649 | Yes | 649 | 240 | 240 | 545 | No | 1910 | Yes | 1910 | 1789 | 1789 | 2127 | Yes | 2412 | No | 2412 | 43 | 43 | 0 | No | 6489 | Yes | 6489 | 6079 | 6079 | 6489 | No | 15008 | 15008 | 11502 | 11502 | 12512 |  | 2018-03-26 | 2018-03-29 |  |  | 2019-12-19 | 2020-03-10 |  |  | 2020-03-19 | 2020-03-30 |  |  | 2020-08-20 | 2020-10-13 |  |  |  |  | 2022-08-31 |  | 6489 | Yes | Yes | Yes | Yes
425 | 07 | 4801 | LA | 210 | Roadway Rehabilitation | IN LOS ANGELES COUNTY IN LOS ANGELES FROM INTERSTATE 5 TO WHEATLAND AVENUE UNDERCROSSING | PAVEMENT REHABILITATION | 1721 | Yes | 1721 | 1476 | 1476 | 1476 | No | 11800 | Yes | 11800 | 8517 | 8517 | 8517 | No | 600 | Yes | 600 | 48 | 48 | 48 | No | 19500 | Yes | 19500 | 12706 | 12706 | 20160 | Yes | 596 | No | 596 | 40 | 40 | 0 | No | 147578 | Yes | 147578 | 103451 | 103451 | 147578 | No | 181795 | 181795 | 126238 | 126238 | 177779 | 2018-10-17 | 2017-09-29 | 2017-09-29 |  |  | 2019-04-30 | 2019-05-20 |  |  | 2019-05-31 | 2019-06-28 |  |  | 2020-02-25 | 2020-05-08 |  |  |  |  | 2025-03-03 |  | 147578 | No | No | No | No
426 | 07 | 4804 | LA | 138 | RHMA Overlay on NW LA-138 | Near Gorman and Lancaster, from Route 5 to Route 14. | Rehabilitate pavement. | 510 | No | 510 | 81 | 81 | 81 | No | 2150 | Yes | 2150 | 2025 | 2025 | 2025 | No | 22 | Yes | 22 | 20 | 20 | 20 | No | 3550 | Yes | 3550 | 3454 | 3454 | 3542 | No | 128 | No | 128 | 3 | 3 | 128 | No | 20501 | Yes | 20501 | 18822 | 18822 | 20501 | No | 26861 | 26861 | 24405 | 24405 | 26297 | 2018-10-17 | 2017-02-10 | 2017-02-10 |  |  | 2019-01-30 | 2019-01-31 |  |  | 2019-04-30 | 2019-04-30 |  |  | 2019-09-16 | 2019-11-04 |  |  |  |  | 2022-08-26 |  | 19501 | No | No | No | Yes
427 | 07 | 4817 | LA | 134 | LA-134 Pavement Preservation | In the cities of Los Angeles, Burbank, Glendale and Pasadena, from Route 170 to Route 210. | Rehabilitate pavement, upgrade guardrail and Americans with Disabilities Act (ADA) curb ramps to current standards. | 1380 | Yes | 1380 | 785 | 785 | 785 | No | 4744 | Yes | 4744 | 3762 | 3762 | 3762 | No | 254 | Yes | 254 | 63 | 63 | 172 | No | 5735 | Yes | 5735 | 3537 | 3537 | 5777 | Yes | 376 | No | 376 | 5 | 5 | 0 | No | 42013 | Yes | 42013 | 22579 | 22579 | 42013 | No | 54502 | 54502 | 30731 | 30731 | 52509 | 2018-10-17 | 2017-12-29 | 2017-12-29 |  |  | 2019-01-30 | 2019-05-21 |  |  | 2019-04-30 | 2019-05-24 |  |  | 2019-09-30 | 2020-05-08 |  |  |  |  | 2023-07-28 |  | 42013 | No | No | No | No
428 | 07 | 4819 | LA | 605 | Upgrade TMS | In various cities, from Orange County line to Route 210; also on Route 2 at the Transportation Management Center (TMC) (PM R18.7) and Route 5 (PM 6.8). | Upgrade Transportation Management System (TMS). | 25 | No | 25 | 21 | 21 | 21 | No | 2199 | Yes | 2199 | 1544 | 1544 | 1544 | No | 202 | Yes | 202 | 13 | 13 | 19 | No | 3220 | Yes | 3220 | 1410 | 1410 | 3022 | No | 0 | No | 0 | 0 | 0 | 0 | No | 8691 | Yes | 8691 | 5397 | 5397 | 8691 | No | 14337 | 14337 | 8385 | 8385 | 13297 |  | 2015-06-09 | 2015-06-09 |  |  | 2019-02-01 | 2019-02-20 |  |  | 2019-03-05 | 2019-04-15 |  |  | 2020-02-27 | 2019-11-14 |  |  |  |  | 2023-05-23 |  | 8691 | No | No | No | No
429 | 07 | 4830 | LA | 110 | TMS Installations | In the cities of Carson and Los Angeles, from Gaffey Street (PM R0.745) to 0.4 mile north of Route 5; also on Route 2 at the Transportation Management Center (TMC) Building (PM 18.7), Route 5 at Route 10 Interchange (PM 16.9) and Route 405 at Route 105 Interchange (PM 21.3). | Upgrade and completion of Transportation Management System (TMS). | 95 | Yes | 95 | 57 | 57 | 57 | No | 5900 | Yes | 5900 | 3498 | 3498 | 3498 | No | 200 | Yes | 200 | 127 | 127 | 198 | No | 5000 | Yes | 5000 | 2763 | 2763 | 5061 | Yes | 702 | No | 702 | 0 | 0 | 675 | No | 33613 | Yes | 33613 | 19970 | 19970 | 33613 | No | 45510 | 45510 | 26415 | 26415 | 43102 | 2018-10-17 | 2018-08-10 | 2018-08-10 |  |  | 2019-02-19 | 2019-02-28 |  |  | 2019-03-20 | 2019-05-06 |  |  | 2019-12-13 | 2020-03-03 |  |  |  |  | 2023-06-15 |  | 33613 | No | No | No | No
430 | 07 | 4846 | LA | 1 | Fish Passage and Culverts | In the cities of Los Angeles and Malibu, from 0.4 mile south of Temescal Canyon Road to Ventura County line; also in Ventura County, from Los Angeles County line to 0.1 mile north of Tonga Street (PM 0.0/0.9). | Rehabilitate culverts. | 2345 | Yes | 2345 | 2318 | 2318 | 2318 | No | 5785 | Yes | 5785 | 5230 | 5230 | 5762 | No | 2583 | Yes | 2583 | 1767 | 1767 | 2601 | Yes | 5000 | No | 5000 | 0 | 0 | 4890 | No | 14353 | Yes | 14353 | 176 | 176 | 14400 | Yes | 20900 | No | 20900 | 0 | 0 | 20900 | No | 50966 | 50966 | 9491 | 9491 | 50871 | 2019-06-26 | 2019-04-08 | 2019-04-08 |  |  | 2021-06-01 |  | 2022-10-03 | Yes | 2021-06-14 |  | 2022-11-18 | Yes | 2022-01-14 |  | 2023-08-20 | Yes |  |  | 2025-06-20 |  | 0 | Yes | No | No | Yes
431 | 07 | 4887 | LA | 14 | Reconstruct Pavement Structure and Ramps | In and near Palmdale and Lancaster, from Technology Drive to the Kern County line. | Replace distressed lanes/shoulders, cold plane and overlay ramps, upgrade guardrail, dikes, sign panels, curb ramps and traffic loop detectors. | 3000 | Yes | 3000 | 2087 | 2087 | 2087 | No | 13200 | Yes | 13200 | 8194 | 8194 | 8904 | No | 280 | Yes | 280 | 0 | 0 | 184 | No | 18600 | Yes | 18600 | 0 | 0 | 18346 | No | 210 | No | 210 | 34 | 34 | 34 | No | 128833 | Yes | 128833 | 0 | 0 | 126614 | No | 164123 | 164123 | 10315 | 10315 | 156169 | 2019-10-09 | 2019-07-31 | 2019-07-31 |  |  | 2021-02-08 | 2021-04-01 |  |  | 2021-03-15 | 2021-06-30 |  |  | 2022-01-10 |  | 2023-03-31 | Yes |  |  | 2025-10-02 |  | 0 | Yes | Yes | Yes | Yes
432 | 07 | 4902 | LA | 10S | Deck Replacement 19/20 | In El Monte, at Rio Hondo Busway Bridge No 53-2637. | Replace bridge deck. | 550 | Yes | 550 | 489 | 489 | 489 | No | 1633 | Yes | 1633 | 1025 | 1025 | 1714 | Yes | 304 | Yes | 304 | 131 | 131 | 293 | No | 2449 | No | 2449 | 0 | 0 | 2874 | Yes | 315 | No | 315 | 1 | 1 | 29 | No | 8620 | No | 8620 | 0 | 0 | 9929 | Yes | 13871 | 13871 | 1646 | 1646 | 15328 |  | 2017-12-29 | 2020-06-11 |  |  | 2019-11-27 |  | 2023-02-17 | Yes | 2019-12-30 |  | 2023-03-30 | Yes | 2020-06-17 |  | 2023-07-31 | Yes |  |  | 2024-06-20 |  | 0 | Yes | Yes | No | No
433 | 07 | 4915 | LA | 101 | Bridge Replacement | In the city of Los Angeles, near the neighborhood of Encino, at the Encino Pedestrian Overcrossing No 53-1289. | Remove pedestrian overcrossing. | 1336 | Yes | 1336 | 1317 | 1317 | 1317 | No | 4226 | Yes | 4226 | 3900 | 3900 | 4206 | No | 522 | Yes | 522 | 484 | 484 | 533 | Yes | 1500 | No | 1500 | 0 | 0 | 1505 | Yes | 995 | No | 995 | 258 | 258 | 1139 | Yes | 3160 | No | 3160 | 0 | 0 | 3388 | Yes | 11739 | 11739 | 5959 | 5959 | 12088 |  | 2018-03-30 | 2018-03-30 |  |  | 2022-07-15 | 2022-05-25 |  |  | 2022-08-15 | 2022-05-25 |  |  | 2023-02-15 |  | 2022-10-31 | No |  |  | 2024-03-29 |  | 0 | Yes | Yes | Yes | Yes
434 | 07 | 4967 | LA | 91 | Bridge Rehabilitation | In Long Beach, at the northbound Route 710 to eastbound Route 91 connector, below Artesia Boulevard Overcrossing No 53-0820 and E91-N710 Connector Overcrossing No 53-2241G. | Lower profile of connector to achieve standard vertical clearance. | 910 | Yes | 910 | 483 | 483 | 483 | No | 2468 | Yes | 2468 | 1208 | 1208 | 1208 | No | 43 | Yes | 43 | 4 | 4 | 38 | No | 1308 | Yes | 1308 | 297 | 297 | 1322 | Yes | 77 | No | 77 | 3 | 3 | 40 | No | 2763 | Yes | 2763 | 844 | 844 | 2763 | No | 7569 | 7569 | 2839 | 2839 | 5854 |  | 2019-10-15 | 2020-04-01 |  |  | 2021-02-12 | 2021-06-07 |  |  | 2021-03-15 | 2021-06-30 |  |  | 2022-04-15 | 2022-03-16 |  |  |  |  | 2023-07-10 |  | 2762 | No | No | No | No
435 | 07 | 4972 | VEN | 1 | OH span replacement | Near the city of Ventura, at Ventura Overhead No 52-0040. | Replace bridge. | 1200 | Yes | 1200 | 1051 | 1051 | 1051 | No | 2500 | Yes | 2500 | 2157 | 2157 | 5045 | Yes | 635 | Yes | 635 | 216 | 216 | 630 | No | 5247 | No | 5247 | 0 | 0 | 4703 | No | 983 | No | 983 | 9 | 9 | 4373 | Yes | 28096 | No | 28096 | 0 | 0 | 28096 | No | 38661 | 38661 | 3433 | 3433 | 43898 |  | 2019-06-26 | 2019-06-26 |  |  | 2023-01-23 |  | 2023-06-09 | Yes | 2023-02-01 |  | 2023-06-28 | Yes | 2023-09-21 |  | 2024-03-06 | Yes |  |  | 2025-12-26 |  | 0 | No | Yes | Yes | Yes
436 | 07 | 4979 | LA | 605 | Pavement Rehabilitation | In various cities, from Orange County line to 0.1 mile north of Telegraph Road; also on Route 91 from 0.2 mile west of Route 605 to Route 605 (PM R16.63/R16.83). | Pavement rehabilitation consisting of full structural section replacement and damaged slab replacement. Cold plane and overlay Rubberized Hot Mix Asphalt (RHMA-G) on right shoulders and apply High Friction Surface Treatment (HFST) onramps and connectors. (G13 Contingency). | 1960 | Yes | 1960 | 824 | 824 | 824 | No | 8100 | Yes | 8100 | 6116 | 6116 | 8292 | Yes | 150 | Yes | 150 | 11 | 11 | 130 | No | 0 | No | 0 | 0 | 0 | 9738 | Yes | 590 | No | 590 | 43 | 43 | 434 | No | 0 | No | 0 | 0 | 0 | 49434 | Yes | 10800 | 10800 | 6994 | 6994 | 68852 | 2019-10-09 | 2019-06-19 | 2019-06-19 |  |  | 2021-11-15 | 2022-06-08 |  |  | 2021-12-30 | 2022-06-30 |  |  | 2022-09-30 |  | 2022-12-30 | Yes |  |  | 2025-07-30 |  | 0 | No | Yes | No | No
437 | 07 | 4983 | LA | 1 | Bridge Rail Upgrade | In Long Beach, at the San Gabriel River Bridge No 53-0060. | Widen bridge and upgrade bridge rail. | 1555 | Yes | 1555 | 1607 | 1607 | 2883 | Yes | 2759 | No | 2759 | 0 | 0 | 3143 | Yes | 950 | No | 950 | 0 | 0 | 1509 | Yes | 4633 | No | 4633 | 0 | 0 | 5035 | Yes | 23210 | No | 23210 | 0 | 0 | 17915 | No | 16527 | No | 16527 | 0 | 0 | 16527 | No | 49634 | 49634 | 1607 | 1607 | 47012 |  | 2022-12-30 |  | 2023-03-30 | Yes | 2024-02-28 |  | 2024-02-28 | No | 2024-03-29 |  | 2024-03-29 | No | 2024-11-01 |  | 2024-11-01 | No |  |  | 2027-03-01 |  | 0 | No | Yes | No | No
438 | 07 | 4984 | LA | 405 | PSSR Bridge | In Long Beach, at the San Gabriel River Bridge No 53-1185 and SB 605 to NB I-405 Connector Bridge No 53-1737H; also in Orange County on Route 405 at the SB 405 to NB 605 Connector Bridge No 55-0413F. | Retrofit scour critical bridges to preserve the structural integrity of the bridges by enlarging and deepening pile cap, adding Cast in Drilled Hole (CIDH) piles and reinforcing the area with Rock Slope Protection (RSP). (G13 Contingency). | 2355 | Yes | 2355 | 2354 | 2354 | 2354 | No | 6140 | Yes | 6140 | 4056 | 4056 | 6115 | No | 342 | Yes | 342 | 216 | 216 | 332 | No | 0 | No | 0 | 0 | 0 | 6248 | Yes | 274 | No | 274 | 28 | 28 | 7100 | Yes | 0 | No | 0 | 0 | 0 | 15831 | Yes | 9111 | 9111 | 6654 | 6654 | 37980 |  | 2020-03-30 | 2020-06-30 |  |  | 2022-02-16 |  | 2023-09-29 | Yes | 2022-03-18 |  | 2023-10-31 | Yes | 2023-02-01 |  | 2024-07-05 | Yes |  |  | 2026-07-06 |  | 0 | Yes | Yes | No | No
439 | 07 | 4998 | LA | 1 | Cold Plane and Overlay AC | In the cities of Long Beach, Los Angeles, Lomita, and Torrance, from Orange County line to Paseo De Las Delicias. | Upgrade Americans with Disabilities Act (ADA) curb ramps, add pedestrian and bike improvements as complete streets elements, upgrade guardrail, grind pavement, and place Hot Mix Asphalt (HMA) and Rubberized Hot Mix Asphalt (RHMA) pavement to rehabilitate pavement. (G13 Contingency). | 2048 | Yes | 2048 | 1943 | 1943 | 1943 | No | 5186 | Yes | 5186 | 4794 | 4794 | 5195 | Yes | 920 | Yes | 920 | 488 | 488 | 843 | No | 0 | No | 0 | 0 | 0 | 7301 | Yes | 1554 | No | 1554 | 33 | 33 | 1188 | No | 0 | No | 0 | 0 | 0 | 36725 | Yes | 9708 | 9708 | 7258 | 7258 | 53195 | 2020-03-25 | 2019-12-31 | 2019-12-31 |  |  | 2021-08-30 |  | 2023-03-10 | Yes | 2021-09-30 |  | 2023-04-10 | Yes | 2022-02-28 |  | 2023-10-19 | Yes |  |  | 2025-09-30 |  | 0 | Yes | Yes | No | No
440 | 07 | 5002 | LA | 110 | Bridge Rail Upgrade | In the city of Los Angeles, at the 5th Street Overcrossing No 53-0685 and 6th Street Overcrossing No 53-0746. | Upgrade bridge railing. | 712 | Yes | 712 | 497 | 497 | 497 | No | 1823 | Yes | 1823 | 1747 | 1747 | 1747 | No | 30 | Yes | 30 | 24 | 24 | 25 | No | 2000 | Yes | 2000 | 623 | 623 | 1999 | No | 115 | No | 115 | 13 | 13 | 112 | No | 4109 | Yes | 4109 | 1283 | 1283 | 4109 | No | 8789 | 8789 | 4187 | 4187 | 8489 |  | 2019-10-01 | 2019-09-24 |  |  | 2021-03-15 | 2020-12-10 |  |  | 2021-04-26 | 2021-03-18 |  |  | 2021-07-30 | 2021-10-22 |  |  |  |  | 2023-07-31 |  | 4109 | Yes | Yes | Yes | Yes
441 | 07 | 5003 | LA | 134 | Bridge Rail Upgrade | In Pasadena, at Arroyo Seco Bridge No 53-0166 and Orange Grove Boulevard Onramp Overcrossing No 53-2197K. | Replace/upgrade bridge railing. | 1300 | Yes | 1300 | 716 | 716 | 716 | No | 2320 | Yes | 2320 | 2194 | 2194 | 2303 | No | 200 | Yes | 200 | 21 | 21 | 97 | No | 3700 | Yes | 3700 | 0 | 0 | 3129 | No | 10 | No | 10 | 0 | 0 | 10 | No | 7375 | Yes | 7375 | 0 | 0 | 6797 | No | 14905 | 14905 | 2931 | 2931 | 13052 |  | 2020-02-07 | 2020-02-28 |  |  | 2021-08-30 | 2021-12-07 |  |  | 2021-09-30 | 2021-12-21 |  |  | 2022-02-25 |  | 2022-09-15 | Yes |  |  | 2024-09-30 |  | 7375 | Yes | Yes | Yes | Yes
442 | 07 | 5004 | LA | 103 | Union Pacific OH Deck Rehabilitation | In the city of Los Angeles, at the Union Pacific Overhead No 53-2626. | Replace the bridge deck with composite reinforced concrete. (G13 Contingency). | 719 | Yes | 719 | 695 | 695 | 695 | No | 3482 | Yes | 3482 | 2290 | 2290 | 3821 | Yes | 376 | Yes | 376 | 317 | 317 | 386 | Yes | 0 | No | 0 | 0 | 0 | 4460 | Yes | 1730 | No | 1730 | 13 | 13 | 1036 | No | 0 | No | 0 | 0 | 0 | 18570 | Yes | 6307 | 6307 | 3315 | 3315 | 28968 |  | 2019-11-12 | 2020-06-30 |  |  | 2021-12-31 |  | 2023-07-01 | Yes | 2022-01-28 |  | 2023-08-04 | Yes | 2022-08-26 |  | 2024-07-01 | Yes |  |  | 2025-03-17 |  | 0 | Yes | Yes | No | No
443 | 07 | 5007 | LA | 27 | Overlay AC | In and near the city of Los Angeles, from Pacific Coast Highway (Route 1) to Devonshire Street. | Grind and overlay asphalt pavement, and upgrade curb ramps to meet Americans with Disabilities Act (ADA) standards. (G13 Contingency). | 1793 | Yes | 1793 | 1693 | 1693 | 1693 | No | 4205 | Yes | 4205 | 1606 | 1606 | 4111 | No | 389 | Yes | 389 | 77 | 77 | 364 | No | 0 | No | 0 | 0 | 0 | 4754 | Yes | 499 | No | 499 | 1 | 1 | 1796 | Yes | 0 | No | 0 | 0 | 0 | 32136 | Yes | 6886 | 6886 | 3377 | 3377 | 44854 | 2021-10-13 | 2021-07-30 | 2021-07-30 |  |  | 2022-03-03 |  | 2022-12-22 | Yes | 2022-03-17 |  | 2023-01-24 | Yes | 2022-11-17 |  | 2023-09-13 | Yes |  |  | 2026-09-21 |  | 0 | Yes | Yes | No | No
444 | 07 | 5013 | LA | 5 | I-5 Pavement Rehab | Near Castaic, from Lake Hughes Road Undercrossing to 1.9 miles north of Templin Highway. | Replace approach slabs, upgrade drainage systems and guardrail, and repair and stabilize slope by performing rock scaling, installing geogrid and rockfall net, and constructing soldier pile wall. | 100 | Yes | 100 | 100 | 100 | 100 | No | 6000 | Yes | 6000 | 5610 | 5610 | 5610 | No | 250 | Yes | 250 | 102 | 102 | 248 | No | 6670 | Yes | 6670 | 216 | 216 | 6840 | Yes | 10 | No | 10 | 2 | 2 | 2 | No | 28784 | Yes | 28784 | 169 | 169 | 28784 | No | 41814 | 41814 | 6199 | 6199 | 41584 | 2018-10-17 | 2018-03-28 | 2018-03-28 |  |  | 2020-12-30 | 2021-04-23 |  |  | 2021-01-29 | 2021-05-21 |  |  | 2021-02-26 | 2022-03-30 |  |  |  |  | 2025-12-05 |  | 28784 | No | No | No | No
445 | 07 | 5014 | VEN | 150 | CapM | In and near Ojai and Mira Monte, from Burham Road to Gorham Road. | Cold plane and overlay pavement, upgrade guardrail and signs. | 600 | Yes | 600 | 583 | 583 | 583 | No | 2144 | Yes | 2144 | 2043 | 2043 | 2212 | Yes | 275 | Yes | 275 | 264 | 264 | 270 | No | 1700 | No | 1700 | 0 | 0 | 1632 | No | 221 | No | 221 | 0 | 0 | 131 | No | 5588 | No | 5588 | 0 | 0 | 6335 | Yes | 10528 | 10528 | 2890 | 2890 | 11163 |  | 2019-09-18 | 2019-09-30 |  |  | 2021-06-01 | 2022-06-29 |  |  | 2021-06-15 | 2022-06-29 |  |  | 2022-02-15 |  | 2022-12-02 | Yes |  |  | 2024-01-02 |  | 0 | Yes | No | No | No
446 | 07 | 5018 | VEN | 1 | PCH CAPM | Near the city of Ventura, from North 101 Junction - Solimar Undercrossing to Mobil Pier Road. | Grind and overlay pavement, upgrade guardrail/end treatment, install traffic signs and crosswalks. | 625 | Yes | 625 | 621 | 621 | 621 | No | 1960 | Yes | 1960 | 1759 | 1759 | 2105 | Yes | 71 | Yes | 71 | 62 | 62 | 69 | No | 2557 | No | 2557 | 0 | 0 | 2839 | Yes | 1542 | No | 1542 | 61 | 61 | 951 | No | 9065 | No | 9065 | 0 | 0 | 9065 | No | 15820 | 15820 | 2503 | 2503 | 15650 |  | 2020-07-15 | 2020-10-30 |  |  | 2021-11-01 | 2022-03-18 |  |  | 2021-12-15 | 2022-06-29 |  |  | 2022-08-05 |  | 2023-01-05 | Yes |  |  | 2025-05-10 |  | 0 | No | No | No | No
447 | 07 | 5022 | LA | 22 | Cold Plane and AC Overlay | In Long Beach, from Route 1 to the Orange County line. | Cold plane pavement and overlay with Rubberized Hot Mixed Asphalt - Type G (RHMA-G), upgrade curb ramps to current Americans with Disabilities Act (ADA) standards, install guardrail and construct bus pads. | 670 | Yes | 670 | 472 | 472 | 472 | No | 2876 | Yes | 2876 | 1602 | 1602 | 1602 | No | 215 | Yes | 215 | 167 | 167 | 215 | No | 1859 | Yes | 1859 | 284 | 284 | 1848 | No | 476 | No | 476 | 62 | 62 | 240 | No | 5546 | Yes | 5546 | 107 | 107 | 5546 | No | 11642 | 11642 | 2694 | 2694 | 9923 |  | 2020-01-30 | 2019-12-18 |  |  | 2020-11-05 | 2021-05-12 |  |  | 2020-12-15 | 2021-06-25 |  |  | 2021-09-03 | 2022-04-18 |  |  |  |  | 2023-12-22 |  | 5546 | No | No | No | No
448 | 07 | 5024 | LA | 5 | Repair/upgrade pump stations | In the city of Los Angeles, at Humboldt Street, Glendale Boulevard, and Sheldon Street. | Upgrade pump plants. | 294 | Yes | 294 | 281 | 281 | 281 | No | 1135 | Yes | 1135 | 1105 | 1105 | 1105 | No | 32 | Yes | 32 | 12 | 12 | 14 | No | 1188 | Yes | 1188 | 0 | 0 | 1235 | Yes | 44 | No | 44 | 0 | 0 | 44 | No | 5493 | Yes | 5493 | 0 | 0 | 5493 | No | 8186 | 8186 | 1398 | 1398 | 8172 |  | 2019-12-02 | 2020-04-01 |  |  | 2020-12-31 | 2021-06-17 |  |  | 2021-02-26 | 2021-06-29 |  |  | 2021-11-30 | 2022-06-10 |  |  |  |  | 2024-07-01 |  | 5493 | No | No | No | No
449 | 07 | 5026 | LA | 210 | Hinge and Diaphragm Repairs | In Irwindale, on the San Gabriel River Bridge No 53-1867. | Reconstruct hinge diaphragms at hinge 4 and hinge 6, upgrade bridge railing and reinstall electroliers. (This is a Construction Manager/General Contractor (CMGC) project.). | 1311 | Yes | 1311 | 1112 | 1112 | 1112 | No | 3665 | Yes | 3665 | 3541 | 3541 | 3541 | No | 444 | Yes | 444 | 196 | 196 | 242 | No | 4554 | Yes | 4554 | 786 | 786 | 4845 | Yes | 862 | No | 862 | 861 | 861 | 862 | No | 19324 | Yes | 19324 | 5413 | 5413 | 19877 | Yes | 30160 | 30160 | 11909 | 11909 | 30479 |  | 2019-10-04 | 2019-10-31 |  |  | 2020-12-07 | 2021-06-30 |  |  | 2021-01-06 | 2021-06-30 |  |  | 2021-10-28 | 2022-03-08 |  |  |  |  | 2023-07-07 |  | 19877 | Yes | Yes | Yes | Yes
450 | 07 | 5029 | LA | 605 | Slab Replacement and Shoulder Resurfacing | In the cities of Irwindale and Baldwin Park, from Route 10 Interchange to the end of the freeway at Route 210. | Grind mainline pavement and replace damaged stabs with Jointed Plain Concrete Pavement (JPCP) rapid strength concrete and/or Individual Precast Slab Replacement (IPSR), cold plane and overlay median, shoulders, ramps with Hot Mix Asphalt (HMA), construct additional lane on southbound Arrow Highway offramp/modify signal, install and upgrade guardrail. | 1375 | Yes | 1375 | 964 | 964 | 964 | No | 6856 | Yes | 6856 | 3265 | 3265 | 3755 | No | 138 | Yes | 138 | 63 | 63 | 128 | No | 4916 | No | 4916 | 0 | 0 | 3777 | No | 162 | No | 162 | 0 | 0 | 824 | Yes | 16410 | No | 16410 | 0 | 0 | 16410 | No | 29857 | 29857 | 4292 | 4292 | 25858 | 2019-05-16 | 2018-12-06 | 2018-12-06 |  |  | 2021-10-08 | 2022-06-23 |  |  | 2021-11-08 | 2022-06-29 |  |  | 2022-09-06 |  | 2022-08-15 | No |  |  | 2024-11-06 |  | 0 | Yes | Yes | Yes | Yes
451 | 07 | 5032 | LA | 5 | Tejon Pass OC Bridge; Seismic Retrofit | Near Kern County line, at the Tejon Pass Overcrossing No 53-1779. | Seismic retrofit of bridge, widen bridge abutments, add steel casing to bent columns, retrofit bent foundation and install micropiles. | 700 | Yes | 700 | 287 | 287 | 287 | No | 1856 | Yes | 1856 | 1072 | 1072 | 1072 | No | 200 | Yes | 200 | 4 | 4 | 44 | No | 1500 | Yes | 1500 | 74 | 74 | 1477 | No | 100 | No | 100 | 10 | 10 | 87 | No | 2104 | Yes | 2104 | 0 | 0 | 2104 | No | 6460 | 6460 | 1447 | 1447 | 5071 |  | 2020-01-15 | 2019-11-22 |  |  | 2021-06-15 | 2021-07-01 |  |  | 2021-07-15 | 2021-08-16 |  |  | 2022-01-05 | 2022-03-16 |  |  |  |  | 2023-07-31 |  | 2104 | No | No | No | No
452 | 07 | 5034 | LA | 1 | Cold Plane and Overlay AC | In the cities of Torrance, Redondo Beach, Hermosa Beach, Manhattan Beach, El Segundo, and Los Angeles, from Paseo De Las Delicias to Dewey Street. | Upgrade Americans with Disabilities Act (ADA) curb ramps and guardrail, repair concrete pavement, reconstruct bus pads, replace asphalt pavement with Portland Cement Concrete (PCC) at intersections, grind pavement, and place Hot Mix Asphalt (HMA) and Rubberized Hot Mix Asphalt (RHMA) pavement to rehabilitate pavement. (G13 Contingency). | 2356 | Yes | 2356 | 2338 | 2338 | 2338 | No | 6770 | Yes | 6770 | 6303 | 6303 | 6666 | No | 780 | Yes | 780 | 748 | 748 | 857 | Yes | 0 | No | 0 | 0 | 0 | 9030 | Yes | 4671 | No | 4671 | 184 | 184 | 3643 | No | 0 | No | 0 | 0 | 0 | 47900 | Yes | 14577 | 14577 | 9573 | 9573 | 70434 | 2020-03-25 | 2019-12-31 | 2019-12-31 |  |  | 2021-08-30 |  | 2023-05-10 | Yes | 2021-09-30 |  | 2023-06-09 | Yes | 2022-02-28 |  | 2023-12-14 | Yes |  |  | 2025-11-14 |  | 0 | Yes | Yes | No | No
453 | 07 | 5035 | LA | 39 | SR- 39 Seismic Retrofit | In Azusa at the San Gabriel River Bridge No 53-0113 (PM 17.82); also in Pomona on Route 71 at the Ridgeway Street Undercrossing Bridge No 53-2052 (PM R0.92). | Seismic retrofit, barrier replacement, paint San Gabriel River Bridge. (G13 Contingency). | 1709 | Yes | 1709 | 1545 | 1545 | 1545 | No | 4000 | Yes | 4000 | 1689 | 1689 | 3687 | No | 488 | Yes | 488 | 10 | 10 | 290 | No | 0 | No | 0 | 0 | 0 | 2804 | Yes | 271 | No | 271 | 29 | 29 | 29 | No | 0 | No | 0 | 0 | 0 | 16327 | Yes | 6468 | 6468 | 3273 | 3273 | 24682 |  | 2020-03-16 | 2020-06-30 |  |  | 2021-10-04 | 2022-04-15 |  |  | 2021-11-03 | 2022-05-13 |  |  | 2022-06-10 |  | 2022-11-22 | Yes |  |  | 2024-11-21 |  | 0 | Yes | Yes | Yes | Yes
454 | 07 | 5040 | LA | 60 | Upgrade Transportation Management System | In and near the city of Los Angeles, from eastbound Route 60/5 Separation to Route 605; also on Route 2 (PM R18.7), Route 5 (PM 6.8), Route 10 (PM 18.3), and Route 605 (PM 20.2). | Upgrade the existing Transportation Management System (TMS) elements to improve traffic monitoring, data transmission, and network connectivity including the Los Angeles Regional Transportation Management Center (LARTMC) on Route 2, Route 5, Route 10, and Route 605. | 233 | Yes | 233 | 230 | 230 | 230 | No | 1331 | Yes | 1331 | 1317 | 1317 | 1317 | No | 45 | Yes | 45 | 36 | 36 | 45 | No | 1642 | Yes | 1642 | 209 | 209 | 1817 | Yes | 153 | No | 153 | 0 | 0 | 153 | No | 5394 | Yes | 5394 | 6 | 6 | 5394 | No | 8798 | 8798 | 1798 | 1798 | 8956 |  | 2018-12-31 | 2018-12-31 |  |  | 2020-10-09 | 2020-12-16 |  |  | 2020-11-05 | 2021-04-01 |  |  | 2021-08-19 | 2022-02-04 |  |  |  |  | 2023-08-24 |  | 5394 | No | No | No | No
455 | 07 | 5041 | LA | 1 | Upgrade TMS | In and near Santa Monica, from Lincoln Boulevard to McClure Tunnel; also on Route 10 (PM R2.155/18.3), Route 2 (PM R18.7), Route 101 (PM 11.8), and Route 105 (PM R1.95). | Upgrade the existing Transportation Management System (TMS) elements to improve traffic monitoring, data transmission, and network connectivity including the Los Angeles Regional Transportation Management Center (LARTMC) and communication hubs at Route 10, Route 101 and Route 105. | 539 | Yes | 539 | 110 | 110 | 110 | No | 3159 | Yes | 3159 | 2807 | 2807 | 2807 | No | 43 | Yes | 43 | 20 | 20 | 45 | Yes | 3797 | Yes | 3797 | 534 | 534 | 3822 | Yes | 327 | No | 327 | 0 | 0 | 327 | No | 15172 | Yes | 15172 | 2362 | 2362 | 15172 | No | 23037 | 23037 | 5833 | 5833 | 22283 | 2019-03-14 | 2018-12-31 | 2018-12-31 |  |  | 2020-08-21 | 2020-10-02 |  |  | 2020-10-21 | 2020-11-30 |  |  | 2021-05-21 | 2021-07-08 |  |  |  |  | 2023-08-07 |  | 15172 | No | No | No | No
456 | 07 | 5043 | LA | 103 | New Pump Station | In the city of Los Angeles, near Long Beach, at Henry Ford Avenue offramp. | Construct larger pump plant facility including replacing undersized pumps. | 1198 | Yes | 1198 | 1017 | 1017 | 1017 | No | 2586 | Yes | 2586 | 2031 | 2031 | 2031 | No | 420 | Yes | 420 | 190 | 190 | 192 | No | 4328 | Yes | 4328 | 0 | 0 | 4305 | No | 1657 | No | 1657 | 17 | 17 | 1176 | No | 14002 | Yes | 14002 | 0 | 0 | 14002 | No | 24191 | 24191 | 3255 | 3255 | 22723 |  | 2019-12-20 | 2020-02-05 |  |  | 2020-12-01 | 2021-06-24 |  |  | 2021-02-16 | 2021-06-30 |  |  | 2022-02-28 | 2022-06-09 |  |  |  |  | 2024-11-25 |  | 14002 | No | No | No | Yes
457 | 07 | 5067 | LA | 10 | San Gabriel Br OH | In El Monte, from Baldwin Avenue Overcrossing to Route 605 at Rio Hondo Bridge No 53-657, East El Monte Overhead No 53-0867 and San Gabriel River Bridge No 53-109L/R. | Replace overhang joints with reinforced concrete closure pours. | 813 | Yes | 813 | 782 | 782 | 782 | No | 2458 | Yes | 2458 | 1597 | 1597 | 2228 | No | 590 | Yes | 590 | 473 | 473 | 590 | No | 2189 | No | 2189 | 0 | 0 | 2242 | Yes | 1357 | No | 1357 | 20 | 20 | 1162 | No | 7083 | No | 7083 | 0 | 0 | 7083 | No | 14490 | 14490 | 2872 | 2872 | 14087 |  | 2020-01-07 | 2020-01-16 |  |  | 2022-01-03 |  | 2022-12-22 | Yes | 2022-02-01 |  | 2023-01-24 | Yes | 2022-11-23 |  | 2023-09-13 | Yes |  |  | 2025-03-20 |  | 0 | Yes | No | No | No
458 | 07 | 5184 | LA | 2 | Route 2 Cold plane & Overlay | In and near the city of Los Angeles, from Centinela Avenue to Cotner Avenue, North La Brea Avenue to North Oxford Avenue and North Hollywood Boulevard to Allesandro Street. | Grind and overlay pavement, upgrade curb ramps, reconstruct curb and gutter, construct bus pads and bicycle and intersection improvements as complete streets elements and relocate nine signal poles. (G13 Contingency). | 2590 | Yes | 2590 | 2514 | 2514 | 2514 | No | 5238 | Yes | 5238 | 4747 | 4747 | 5459 | Yes | 1308 | Yes | 1308 | 845 | 845 | 1155 | No | 0 | No | 0 | 0 | 0 | 5042 | Yes | 6639 | No | 6639 | 271 | 271 | 6369 | No | 0 | No | 0 | 0 | 0 | 21698 | Yes | 15775 | 15775 | 8377 | 8377 | 42237 | 2021-06-23 | 2020-12-31 | 2020-12-31 |  |  | 2022-04-15 | 2022-06-29 |  |  | 2022-04-30 | 2022-06-30 |  |  | 2022-10-20 |  | 2022-10-20 | No |  |  | 2024-10-30 |  | 0 | No | Yes | No | No
459 | 07 | 5188 | LA | 110 | Bluetooth Detection System | In various cities, from Gaffey Street to Route 405; also on Route 210 (PM R0.0/R35.8), Route 605 (PM R19.9/26.0), Route 710 (PM 5.0/9.4) and Route 2 (PM R18.7). | Install wireless bluetooth detection system to monitor travel time. | 240 | Yes | 240 | 139 | 139 | 139 | No | 435 | Yes | 435 | 392 | 392 | 392 | No | 0 | No | 0 | 0 | 0 | 0 | No | 355 | Yes | 355 | 50 | 50 | 343 | No | 10 | No | 10 | 0 | 0 | 10 | No | 1062 | Yes | 1062 | 0 | 0 | 1062 | No | 2102 | 2102 | 581 | 581 | 1946 |  | 2019-01-29 | 2019-01-29 |  |  | 2020-07-21 | 2020-07-29 |  |  | 2020-10-21 | 2020-12-10 |  |  | 2021-04-22 | 2021-08-10 |  |  |  |  | 2023-07-14 |  | 1062 | No | No | No | No
460 | 07 | 5219 | LA | 14 | Rte 14 Drainage Culvert | In Santa Clarita, from 0.8 mile to 0.5 mile south Golden Valley Road. | Replace damaged drainage system that includes seventeen culverts. | 556 | Yes | 556 | 396 | 396 | 396 | No | 1881 | Yes | 1881 | 1353 | 1353 | 1353 | No | 23 | Yes | 23 | 11 | 11 | 21 | No | 2074 | Yes | 2074 | 1667 | 1667 | 2199 | Yes | 10 | No | 10 | 0 | 0 | 10 | No | 5353 | Yes | 5353 | 4598 | 4598 | 5353 | No | 9897 | 9897 | 8025 | 8025 | 9332 |  | 2018-07-13 | 2018-10-15 |  |  | 2019-09-03 | 2020-01-29 |  |  | 2019-10-01 | 2020-05-29 |  |  | 2020-05-01 | 2020-11-05 |  |  |  |  | 2022-06-29 |  | 5353 | No | No | No | Yes
461 | 07 | 5221 | LA | 101 | LA-101 Upgrade CCTV/CMS | In various cities, from Route 10 to Route 405, Route 2 at Route 134 (PM R18.7) and Route 10 at 7th Street (PM 18.3). | Upgrade Transportation Management System (TMS) elements including Closed Circuit Television (CCTV) cameras, Ramp Metering Systems (RMS), Vehicle Detection Stations (VDS), Highway Advisory Radio (HAR), Changeable Message Signs (CMS) and the communication system network. These upgrades will improve efficiency and reliability of field systems. | 438 | Yes | 438 | 320 | 320 | 320 | No | 3008 | Yes | 3008 | 2238 | 2238 | 2853 | No | 162 | Yes | 162 | 9 | 9 | 159 | No | 2198 | Yes | 2198 | 0 | 0 | 2198 | No | 13 | No | 13 | 0 | 0 | 13 | No | 9708 | Yes | 9708 | 0 | 0 | 9718 | Yes | 15527 | 15527 | 2567 | 2567 | 15261 |  | 2019-02-28 | 2019-02-28 |  |  | 2021-09-03 | 2021-11-17 |  |  | 2022-01-03 | 2022-03-01 |  |  | 2022-08-01 |  | 2022-08-01 | No |  |  | 2024-07-01 |  | 0 | No | No | No | No
462 | 07 | 5222 | LA | 134 | LA-134 Upgrade TMS | In the city of Los Angeles, from Route 170 to Routes 210/710; also on Route 2 at Route 134 (PM R18.7), on Route 10 at Routes 5/10 (PM 18.3), and on Route 101 near Pleasant Valley Road (PM 11.8). | Upgrade Transportation Management System (TMS) elements including Closed Circuit Television (CCTV) cameras, Ramp Metering Systems (RMS), Vehicle Detection Systems (VDS), Highway Advisory Radio (HAR), Changeable Message Signs (CMS) and the communication system network. | 454 | Yes | 454 | 161 | 161 | 161 | No | 2840 | Yes | 2840 | 1746 | 1746 | 2592 | No | 154 | Yes | 154 | 14 | 14 | 154 | No | 1953 | No | 1953 | 0 | 0 | 1972 | Yes | 13 | No | 13 | 0 | 0 | 13 | No | 6194 | No | 6194 | 0 | 0 | 6194 | No | 11608 | 11608 | 1921 | 1921 | 11086 |  | 2018-12-26 | 2018-12-26 |  |  | 2021-09-03 | 2021-12-02 |  |  | 2022-01-03 | 2022-04-06 |  |  | 2022-08-01 |  | 2023-01-12 | Yes |  |  | 2024-07-01 |  | 0 | No | No | No | Yes
463 | 07 | 5226 | LA | 91 | Upgrade TMS | In and near Carson, from Route 110 to Orange County line; also on Route 2 (PM R18.7), Route 5 (PM 6.8), Route 405 (PM 21.1). | Upgrade the existing Transportation Management System (TMS) elements to improve traffic monitoring, data transmission, and network connectivity including the various communication hubs on Route 2, Route 5, and Route 405. | 511 | Yes | 511 | 262 | 262 | 262 | No | 3100 | Yes | 3100 | 2709 | 2709 | 3204 | Yes | 150 | Yes | 150 | 17 | 17 | 145 | No | 4749 | No | 4749 | 0 | 0 | 3856 | No | 267 | No | 267 | 0 | 0 | 267 | No | 16390 | No | 16390 | 0 | 0 | 16390 | No | 25167 | 25167 | 2988 | 2988 | 24124 | 2019-05-16 | 2018-12-28 | 2018-12-28 |  |  | 2022-01-14 | 2022-02-23 |  |  | 2022-03-01 | 2022-05-23 |  |  | 2023-01-13 |  | 2022-12-21 | No |  |  | 2024-09-01 |  | 0 | No | No | No | No
464 | 07 | 5246 | LA | 010 | ITS Restoration work in Shimelis area | ITS repair of RMS and VDS elements on various routes | ITS repair of RMS and VDS elements on various routes | 0 | No | 0 | 0 | 0 | 0 | No | 2295 | Yes | 2295 | 676 | 676 | 676 | No | 18 | Yes | 18 | 15 | 15 | 15 | No | 3645 | Yes | 3645 | 3505 | 3505 | 3609 | No | 0 | No | 0 | 0 | 0 | 10 | Yes | 17249 | Yes | 17249 | 14407 | 14407 | 15515 | No | 23207 | 23207 | 18603 | 18603 | 19825 | [6 empty] | 2017-12-14 |  |  |  | 2018-03-19 |  |  |  | 2018-07-29 |  |  |  |  | 2022-12-30 |  | 16999 | No | No | No | No
465 | 07 | 5297 | LA | 60 | Freight Corridor Improvements on LA-60 | In the City of Industry at Hacienda Boulevard Undercrossing (UC) No 53-1789 (PM 15.93), Stemson Avenue UC No 53-1784 (PM 16.30), Azusa Avenue Overcrossing No 53-1785 (PM 17.97) and Fullerton Road UC No 53-1786 (PM 19.46). | Improve freight corridor movement by modifying and replacing bridges to meet vertical clearance and load carrying capacity standards. ACCELERATED BRIDGE (PA&ED Only). | 3320 | Yes | 3320 | 1613 | 1613 | 1613 | No | 0 | No | 0 | 0 | 0 | 2395 | Yes | 0 | No | 0 | 0 | 0 | 140 | Yes | 0 | No | 0 | 0 | 0 | 2864 | Yes | 8 | No | 8 | 3 | 3 | 45 | Yes | 0 | No | 0 | 0 | 0 | 16000 | Yes | 3328 | 3328 | 1616 | 1616 | 23057 |  | 2019-10-31 | 2019-06-27 |  |  | 2020-05-29 |  | 2026-06-12 | Yes | 2020-06-30 |  | 2026-07-22 | Yes | 2021-07-30 |  | 2026-12-30 | Yes |  |  | 2027-09-10 |  | 0 | Yes | Yes | No | No
466 | 07 | 5298 | LA | 39 | LA-39/ N. Fork San Gabriel Bridge Replacement | Near Azusa, at the North Fork San Gabriel River Bridge No 53-2245. | Replace bridge. | 0 | No | 0 | 0 | 0 | 0 | No | 1930 | Yes | 1930 | 1451 | 1451 | 1451 | No | 20 | Yes | 20 | 29 | 29 | 29 | Yes | 4476 | Yes | 4476 | 2780 | 2780 | 4445 | No | 20 | No | 20 | 14 | 14 | 16 | No | 15339 | Yes | 15339 | 4404 | 4404 | 15339 | No | 21785 | 21785 | 8678 | 8678 | 21280 | 2018-10-17 | 2017-09-20 | 2017-09-20 |  |  | 2019-03-01 | 2019-02-26 |  |  | 2019-04-01 | 2019-04-19 |  |  | 2019-08-01 | 2019-11-12 |  |  |  |  | 2024-04-16 |  | 13956 | Yes | Yes | Yes | Yes
467 | 07 | 5353 | VEN | 150 | Pavement Rehab and Curb Ramps | In and near Santa Paula, from north of Bridge Road to Route 126 (PM 34.398). | Rehabilitate pavement, upgrade facilities to Americans with Disabilities Act (ADA) standards, rehabilitate Transportation Management System (TMS) elements, and upgrade guardrail. | 687 | Yes | 687 | 675 | 675 | 675 | No | 2971 | Yes | 2971 | 129 | 129 | 2983 | Yes | 1160 | Yes | 1160 | 3 | 3 | 1135 | No | 1809 | No | 1809 | 0 | 0 | 1628 | No | 2146 | No | 2146 | 0 | 0 | 1385 | No | 6358 | No | 6358 | 0 | 0 | 8760 | Yes | 15131 | 15131 | 807 | 807 | 16566 |  | 2021-12-15 | 2021-12-23 |  |  | 2024-02-15 |  | 2024-02-15 | No | 2024-03-15 |  | 2024-06-17 | Yes | 2024-11-08 |  | 2025-02-18 | Yes |  |  | 2026-05-12 |  | 0 | No | Yes | No | No
468 | 07 | 5355 | LA | 103 | Bridge Rail Upgrade | In the city of Los Angeles, near Wilmington, at the Anaheim Street Overhead No 53-2627. | Upgrade bridge rail. | 872 | Yes | 872 | 509 | 509 | 509 | No | 1945 | Yes | 1945 | 335 | 335 | 2163 | Yes | 104 | Yes | 104 | 2 | 2 | 37 | No | 1820 | No | 1820 | 0 | 0 | 1517 | No | 63 | No | 63 | 0 | 0 | 68 | Yes | 4320 | No | 4320 | 0 | 0 | 5568 | Yes | 9124 | 9124 | 846 | 846 | 9862 |  | 2021-11-03 | 2021-11-03 |  |  | 2024-02-15 |  | 2023-05-31 | No | 2024-03-29 |  | 2023-05-31 | No | 2024-12-09 |  | 2024-12-09 | No |  |  | 2027-03-15 |  | 0 | No | Yes | No | No
469 | 07 | 5357 | LA | 710 | Upgrade and Install TMS on LA-710 | In Los Angeles County, on various routes at various locations. | Rehabilitate and install new Transportation Management System (TMS) elements and upgrade communication systems. | 873 | Yes | 873 | 677 | 677 | 677 | No | 3305 | Yes | 3305 | 626 | 626 | 3330 | Yes | 312 | Yes | 312 | 0 | 0 | 134 | No | 3241 | No | 3241 | 0 | 0 | 3223 | No | 406 | No | 406 | 0 | 0 | 238 | No | 15559 | No | 15559 | 0 | 0 | 15559 | No | 23696 | 23696 | 1303 | 1303 | 23161 |  | 2021-10-13 | 2021-10-13 |  |  | 2023-02-01 |  | 2023-02-01 | No | 2023-03-01 |  | 2023-03-01 | No | 2024-02-01 |  | 2024-02-01 | No |  |  | 2025-11-03 |  | 0 | No | No | No | No
470 | 07 | 5364 | LA | 1 | LA 1, Bridge Seismic Retrofit | In Long Beach, at Los Angeles River Bridge No 53-0341 and De Forest Avenue Undercrossing No 53-1047. | Seismic retrofit, upgrade bridge rails, and upgrade facilities to Americans with Disabilities Act (ADA) standards. (G13 Contingency). | 1570 | Yes | 1570 | 1135 | 1135 | 1135 | No | 3204 | Yes | 3204 | 0 | 0 | 3202 | No | 420 | Yes | 420 | 0 | 0 | 351 | No | 0 | No | 0 | 0 | 0 | 3464 | Yes | 817 | No | 817 | 0 | 0 | 573 | No | 0 | No | 0 | 0 | 0 | 19877 | Yes | 6011 | 6011 | 1135 | 1135 | 28602 |  | 2021-12-02 | 2022-06-29 |  |  | 2023-02-02 |  | 2023-06-30 | Yes | 2023-03-08 |  | 2023-06-30 | Yes | 2023-11-01 |  | 2024-02-01 | Yes |  |  | 2028-09-29 |  | 0 | No | Yes | No | No
471 | 07 | 5365 | VEN | Var | Mobility (TMS) on Ven 23 | In Ventura and Los Angeles Counties, on various routes at various locations. | Upgrade and install new Transportation Management System (TMS) elements, install Maintenance Vehicle Pullouts (MVPs), and upgrade communication system at the Los Angeles Regional Transportation Management Center (LARTMC). | 1112 | Yes | 1112 | 816 | 816 | 816 | No | 3487 | Yes | 3487 | 323 | 323 | 3261 | No | 18 | Yes | 18 | 0 | 0 | 13 | No | 5345 | No | 5345 | 0 | 0 | 4491 | No | 22 | No | 22 | 0 | 0 | 75 | Yes | 22324 | No | 22324 | 0 | 0 | 20509 | No | 32308 | 32308 | 1139 | 1139 | 29165 |  | 2021-11-30 | 2021-12-10 |  |  | 2023-02-28 |  | 2023-02-14 | No | 2023-03-30 |  | 2023-03-16 | No | 2023-12-29 |  | 2023-10-05 | No |  |  | 2025-02-16 |  | 0 | No | No | No | No
472 | 07 | 5366 | LA | 101 | Nickname Required | In the city of Los Angeles, near Universal City, from south of Mulholland Drive to Route 170. | Rehabilitate pavement, upgrade facilities to Americans with Disabilities Act (ADA) standards, and upgrade guardrail. | 636 | Yes | 636 | 629 | 629 | 629 | No | 0 | Yes | 0 | 0 | 0 | 2146 | Yes | 0 | Yes | 0 | 0 | 0 | 40 | Yes | 3356 | No | 3356 | 0 | 0 | 3346 | No | 357 | No | 357 | 0 | 0 | 184 | No | 14382 | No | 14382 | 0 | 0 | 15936 | Yes | 18731 | 18731 | 629 | 629 | 22281 |  | 2022-03-30 | 2022-06-24 |  |  | 2023-07-03 |  | 2024-05-14 | Yes | 2023-08-03 |  | 2024-05-31 | Yes | 2024-03-22 |  | 2024-12-20 | Yes |  |  | 2027-05-28 |  | 0 | Yes | Yes | Yes | Yes
473 | 07 | 5373 | VEN | 232 | Pavement Rehab on Ven 232 | In and near Oxnard, from Route 101 to Route 118. | Rehabilitate pavement, upgrade facilities to Americans with Disabilities Act (ADA) standards, and upgrade guardrail. | 768 | Yes | 768 | 617 | 617 | 617 | No | 2840 | No | 2840 | 0 | 0 | 2702 | No | 472 | No | 472 | 0 | 0 | 160 | No | 2859 | No | 2859 | 0 | 0 | 2103 | No | 693 | No | 693 | 0 | 0 | 233 | No | 9982 | No | 9982 | 0 | 0 | 9982 | No | 17614 | 17614 | 617 | 617 | 15797 |  | 2021-12-30 | 2022-06-24 |  |  | 2024-02-28 |  | 2024-06-18 | Yes | 2024-03-29 |  | 2024-06-28 | No | 2024-12-30 |  | 2025-02-10 | No |  |  | 2026-12-30 |  | 0 | No | No | No | No
474 | 07 | 5374 | LA | 710 | LA-710, Drainage System Restoration | In Long Beach and Pasadena, at various locations. | Rehabilitate pump plants. | 909 | Yes | 909 | 464 | 464 | 464 | No | 2265 | Yes | 2265 | 950 | 950 | 2286 | Yes | 57 | Yes | 57 | 47 | 47 | 67 | Yes | 1861 | No | 1861 | 0 | 0 | 1821 | No | 38 | No | 38 | 0 | 0 | 39 | Yes | 4822 | No | 4822 | 0 | 0 | 5222 | Yes | 9952 | 9952 | 1461 | 1461 | 9899 |  | 2021-06-16 | 2021-06-16 |  |  | 2022-07-15 |  | 2022-07-15 | No | 2022-08-15 |  | 2022-08-15 | No | 2023-03-01 |  | 2023-03-01 | No |  |  | 2024-03-29 |  | 0 | No | No | No | No
475 | 07 | 5382 | LA | 405 | PaveRehab | In and near the city of Los Angeles, from Wilshire Boulevard to Victory BoulevaRd Rehabilitate roadway, rehabilitate culverts, replace bridge approach/departure slabs, replace overhead sign structures and sign panels, upgrade Transportation Management System (TMS) elements, upgrade guardrail, and upgrade facilities to Americans with Disabilities Act (ADA) standards. (G13 Contingency). | REHABILITATE ROADWAY, REHABILITATE CULVERTS, REPLACE BRIDGE APPROACH/DEPARTURE SLABS, UPGRADE TMS | 2474 | Yes | 2474 | 2514 | 2514 | 2514 | Yes | 6875 | Yes | 6875 | 0 | 0 | 6677 | No | 50 | Yes | 50 | 0 | 0 | 44 | No | 0 | No | 0 | 0 | 0 | 14093 | Yes | 311 | No | 311 | 0 | 0 | 40 | No | 0 | No | 0 | 0 | 0 | 123614 | Yes | 9710 | 9710 | 2514 | 2514 | 146982 |  | 2021-11-15 | 2022-06-30 |  |  | 2023-02-21 |  | 2023-02-21 | No | 2023-03-21 |  | 2023-03-21 | No | 2023-11-06 |  | 2023-11-06 | No |  |  | 2027-07-02 |  | 0 | Yes | Yes | Yes | Yes
476 | 07 | 5386 | LA | 210 | 210 Misc | In La Canada Flintridge and Pasadena, from West of Foothill Boulevard to Hill Avenue. | Seismic retrofit of Orange Grove Boulevard Overcrossing No 53-2195, rehabilitate irrigation system and landscaping, and rehabilitate culverts. | 800 | Yes | 800 | 719 | 719 | 719 | No | 2379 | No | 2379 | 0 | 0 | 2362 | No | 251 | No | 251 | 0 | 0 | 251 | No | 2883 | No | 2883 | 0 | 0 | 2502 | No | 83 | No | 83 | 0 | 0 | 123 | Yes | 11440 | No | 11440 | 0 | 0 | 11730 | Yes | 17836 | 17836 | 719 | 719 | 17687 |  | 2021-11-30 | 2022-02-11 |  |  | 2024-02-15 |  | 2024-02-15 | No | 2024-03-15 |  | 2024-03-15 | No | 2024-12-20 |  | 2024-12-20 | No |  |  | 2026-07-06 |  | 0 | Yes | Yes | Yes | Yes
477 | 07 | 5393 | LA | 210 | Upgrade Lighting Systems to LED | In La Canada Flintridge, from east of Route 2 to west of Angeles Crest Highway, on Alta Canyada Road Overcrossing No 53-2189, E2-W210 Connector Undercrossing No 53-2191G, and Foothill La Canada Separation No 53-2138. | Seismic retrofit of one bridge and add Light Emitting Diode (LED) lighting to one bridge and one tunnel. | 1160 | Yes | 1160 | 600 | 600 | 600 | No | 3403 | Yes | 3403 | 320 | 320 | 3218 | No | 225 | Yes | 225 | 4 | 4 | 221 | No | 4661 | No | 4661 | 0 | 0 | 4226 | No | 50 | No | 50 | 0 | 0 | 4721 | Yes | 17040 | No | 17040 | 0 | 0 | 17040 | No | 26539 | 26539 | 924 | 924 | 30026 |  | 2021-11-30 | 2022-02-08 |  |  | 2023-08-01 |  | 2023-08-01 | No | 2023-09-01 |  | 2023-09-01 | No | 2024-08-01 |  | 2024-08-01 | No |  |  | 2025-12-01 |  | 0 | No | Yes | No | No
478 | 07 | 5395 | LA | 5 | LA 2 ITS | In Los Angeles and Ventura Counties, on various routes at various locations. | Install and upgrade video cameras, install guardrail, and install Maintenance Vehicle Pullouts (MVPs). | 805 | Yes | 805 | 608 | 608 | 608 | No | 3167 | Yes | 3167 | 458 | 458 | 2717 | No | 280 | Yes | 280 | 25 | 25 | 63 | No | 3827 | No | 3827 | 0 | 0 | 3764 | No | 262 | No | 262 | 0 | 0 | 55 | No | 11109 | No | 11109 | 0 | 0 | 12775 | Yes | 19450 | 19450 | 1091 | 1091 | 19982 |  | 2021-06-10 | 2021-06-10 |  |  | 2022-12-30 |  | 2023-02-01 | No | 2023-02-28 |  | 2023-02-28 | No | 2025-04-28 |  | 2023-10-29 | No |  |  | 2026-07-01 |  | 0 | No | Yes | No | Yes
479 | 07 | 5396 | LA | 39 | Bridge rail upgrade | Near Azusa, at Van Orum Canyon Bridge No 53-0115. | Upgrade bridge rail and install guardrail. | 533 | Yes | 533 | 295 | 295 | 295 | No | 1484 | Yes | 1484 | 129 | 129 | 1410 | No | 14 | Yes | 14 | 2 | 2 | 13 | No | 1225 | No | 1225 | 0 | 0 | 1150 | No | 14 | No | 14 | 0 | 0 | 10 | No | 1125 | No | 1125 | 0 | 0 | 1112 | No | 4395 | 4395 | 426 | 426 | 3990 |  | 2021-09-02 | 2021-09-02 |  |  | 2023-08-11 |  | 2023-08-11 | No | 2023-10-06 |  | 2023-10-06 | No | 2024-07-19 |  | 2024-07-19 | No |  |  | 2026-01-23 |  | 0 | No | No | No | No
480 | 07 | 5397 | LA | 2 | DRAINAGE SYSTEM RESTORATION | Near Big Pines, from 1.3 miles west of Dawson Saddle to the San Bernardino County line. | Rehabilitate culverts. | 894 | Yes | 894 | 681 | 681 | 681 | No | 1729 | Yes | 1729 | 322 | 322 | 1714 | No | 24 | Yes | 24 | 7 | 7 | 22 | No | 1046 | No | 1046 | 0 | 0 | 1037 | No | 10 | No | 10 | 0 | 0 | 5 | No | 2136 | No | 2136 | 0 | 0 | 1820 | No | 5839 | 5839 | 1010 | 1010 | 5279 |  | 2021-09-27 | 2021-09-27 |  |  | 2023-02-28 |  | 2023-02-28 | No | 2023-03-29 |  | 2023-03-29 | No | 2023-12-08 |  | 2023-12-08 | No |  |  | 2025-01-15 |  | 0 | No | No | No | No
481 | 07 | 5400 | LA | 210 | Transportation Management System Upgrades | In Los Angeles County, on various routes at various locations. | Rehabilitate Transportation Management System (TMS) elements, install guardrail, and improve highway worker safety. | 529 | Yes | 529 | 314 | 314 | 314 | No | 1839 | Yes | 1839 | 370 | 370 | 1774 | No | 13 | Yes | 13 | 0 | 0 | 12 | No | 2277 | No | 2277 | 0 | 0 | 1635 | No | 28 | No | 28 | 0 | 0 | 10 | No | 5544 | No | 5544 | 0 | 0 | 5965 | Yes | 10230 | 10230 | 684 | 684 | 9710 |  | 2021-11-19 | 2021-12-17 |  |  | 2022-12-01 |  | 2022-12-01 | No | 2023-01-13 |  | 2023-01-13 | No | 2023-08-18 |  | 2023-08-18 | No |  |  | 2024-10-01 |  | 0 | No | No | No | No
482 | 07 | 5401 | LA | 170 | TMS Upgrade | In the city of Los Angeles, near North Hollywood, from Route 134 to Route 5. | Rehabilitate and install new Transportation Management System (TMS) elements, install guardrail, and enhance highway worker safety. | 702 | Yes | 702 | 208 | 208 | 208 | No | 2885 | Yes | 2885 | 291 | 291 | 2322 | No | 215 | Yes | 215 | 5 | 5 | 17 | No | 2393 | No | 2393 | 0 | 0 | 2207 | No | 232 | No | 232 | 0 | 0 | 54 | No | 10636 | No | 10636 | 0 | 0 | 10872 | Yes | 17063 | 17063 | 504 | 504 | 15680 |  | 2021-09-16 | 2021-09-16 |  |  | 2023-02-28 |  | 2023-02-28 | No | 2023-03-28 |  | 2023-03-28 | No | 2023-12-01 |  | 2023-11-01 | No |  |  | 2026-07-15 |  | 0 | No | No | No | No
483 | 07 | 5407 | LA | 2 | ATMS Upgrade | In the city of Los Angeles, near Eagle Rock, at the Los Angeles Regional Transportation Management Center (LARTMC) at 2901 West Broadway. | Update traffic management software to integrate Adaptive Traffic Signal Control (ATSC), video camera control, and to manage the Dynamic Lane Management System (DLMS) message signs. | 409 | Yes | 409 | 323 | 323 | 323 | No | 927 | Yes | 927 | 263 | 263 | 967 | Yes | 11 | Yes | 11 | 0 | 0 | 11 | No | 1048 | No | 1048 | 0 | 0 | 1039 | No | 10 | No | 10 | 0 | 0 | 10 | No | 2948 | No | 2948 | 0 | 0 | 2943 | No | 5353 | 5353 | 586 | 586 | 5293 |  | 2021-03-08 | 2021-03-08 |  |  | 2023-02-03 |  | 2023-02-03 | No | 2023-03-30 |  | 2023-03-30 | No | 2023-10-20 |  | 2023-10-20 | No |  |  | 2025-04-20 |  | 0 | No | No | No | No
484 | 07 | 5408 | LA | 1 | Comm. System Upgrade | In Los Angeles County, on various routes at various locations. | Upgrade existing fiber communication system and rehabilitate Transportation Management System (TMS) elements, including video cameras, ramp meters, and Changeable Message Signs (CMS). | 676 | Yes | 676 | 641 | 641 | 641 | No | 2366 | Yes | 2366 | 129 | 129 | 2378 | Yes | 47 | Yes | 47 | 0 | 0 | 29 | No | 2924 | No | 2924 | 0 | 0 | 2873 | No | 12 | No | 12 | 0 | 0 | 3 | No | 8956 | No | 8956 | 0 | 0 | 8956 | No | 14981 | 14981 | 770 | 770 | 14880 |  | 2021-09-30 | 2021-09-30 |  |  | 2024-02-28 |  | 2024-02-28 | No | 2024-03-29 |  | 2024-03-29 | No | 2025-01-30 |  | 2025-01-30 | No |  |  | 2027-03-01 |  | 0 | No | No | No | No
485 | 07 | 5409 | LA | 2 | LA 2 Video Wall | In the city of Los Angeles, near Eagle Rock, at the Los Angeles Regional Transportation Management Center (LARTMC) at 2901 West Broadway. | Update video wall in LARMTC, upgrade networking equipment, and upgrade traffic management software. | 632 | Yes | 632 | 428 | 428 | 428 | No | 1942 | Yes | 1942 | 174 | 174 | 2011 | Yes | 53 | Yes | 53 | 1 | 1 | 19 | No | 1337 | No | 1337 | 0 | 0 | 1335 | No | 10 | No | 10 | 0 | 0 | 10 | No | 5019 | No | 5019 | 0 | 0 | 5254 | Yes | 8993 | 8993 | 603 | 603 | 9057 |  | 2021-06-07 | 2021-06-07 |  |  | 2023-02-01 |  | 2023-02-01 | No | 2023-03-01 |  | 2023-03-01 | No | 2023-11-01 |  | 2023-11-01 | No |  |  | 2025-05-30 |  | 0 | No | No | No | No
486 | 07 | 5410 | LA | 405 | TMS | In Los Angeles County, on various routes at various locations. | Rehabilitate and add new Transportation Management System (TMS) elements and upgrade the communication system at the Los Angeles Regional Transportation Management Center (LARTMC). | 3076 | Yes | 3076 | 1824 | 1824 | 1824 | No | 6377 | No | 6377 | 0 | 0 | 6199 | No | 73 | No | 73 | 0 | 0 | 17 | No | 7227 | No | 7227 | 0 | 0 | 7194 | No | 66 | No | 66 | 0 | 0 | 13 | No | 29854 | No | 29854 | 0 | 0 | 29854 | No | 46673 | 46673 | 1824 | 1824 | 45101 |  | 2022-02-17 | 2022-06-10 |  |  | 2023-09-19 |  | 2024-02-23 | Yes | 2023-10-19 |  | 2024-03-22 | Yes | 2024-07-23 |  | 2024-09-20 | No |  |  | 2026-08-21 |  | 0 | Yes | Yes | Yes | Yes
487 | 07 | 5412 | LA | 2 | CCTV Replacement D7 wide | In Los Angeles and Ventura Counties, at various locations. | Upgrade Closed Circuit Television (CCTV) cameras, enhance highway worker safety, construct concrete barriers and guardrail, install crash cushions, and install retaining walls. | 962 | Yes | 962 | 893 | 893 | 893 | No | 0 | No | 0 | 0 | 0 | 2464 | Yes | 0 | No | 0 | 0 | 0 | 25 | Yes | 0 | No | 0 | 0 | 0 | 2396 | Yes | 0 | No | 0 | 0 | 0 | 23 | Yes | 0 | No | 0 | 0 | 0 | 16894 | Yes | 962 | 962 | 893 | 893 | 22695 |  | 2022-01-31 | 2022-06-29 |  |  | 2024-02-28 |  | 2024-02-28 | No | 2024-03-29 |  | 2024-03-29 | No | 2024-11-27 |  | 2024-11-27 | No |  |  | 2026-07-15 |  | 0 | No | Yes | No | No
488 | 07 | 5413 | LA | 2 | 7-LA/VEN-Various PMs Changeable Message Signs(CMS) Replacement Project | In Los Angeles and Ventura Counties, at various locations. | Upgrade Changeable Message Signs (CMS), upgrade overhead sign structures, construct guardrail, and enhance highway worker safety. (G13 Contingency). | 2102 | Yes | 2102 | 1716 | 1716 | 1716 | No | 10585 | Yes | 10585 | 19 | 19 | 7692 | No | 364 | Yes | 364 | 4 | 4 | 189 | No | 0 | No | 0 | 0 | 0 | 16403 | Yes | 1465 | No | 1465 | 0 | 0 | 465 | No | 0 | No | 0 | 0 | 0 | 87493 | Yes | 14516 | 14516 | 1739 | 1739 | 113958 |  | 2021-12-03 | 2022-05-05 |  |  | 2024-02-01 |  | 2024-02-01 | No | 2024-03-01 |  | 2024-03-01 | No | 2024-11-27 |  | 2024-09-27 | No |  |  | 2027-05-14 |  | 0 | No | Yes | No | Yes
489 | 07 | 5414 | LA | 2 | Seismic Retrofit of I-5/Route 2 Connector | In the city of Los Angeles, at E2-N5 Ramp and W2-S5 Ramp Tunnel No 53-0577. | Seismic retrofit existing tunnel and upgrade guardrail. | 1270 | Yes | 1270 | 1030 | 1030 | 1030 | No | 1950 | Yes | 1950 | 75 | 75 | 1869 | No | 55 | Yes | 55 | 0 | 0 | 24 | No | 2000 | No | 2000 | 0 | 0 | 1484 | No | 45 | No | 45 | 0 | 0 | 42 | No | 8194 | No | 8194 | 0 | 0 | 8193 | No | 13514 | 13514 | 1105 | 1105 | 12642 |  | 2021-11-19 | 2021-12-10 |  |  | 2023-03-01 |  | 2023-05-01 | No | 2023-03-30 |  | 2023-05-31 | No | 2023-12-15 |  | 2024-01-16 | No |  |  | 2024-06-17 |  | 0 | No | No | No | No
490 | 07 | 5429 | LA | 2 | LA-101, Bridge Rail Upgrade | In Los Angeles County, on various routes at Santa Monica Bridge No 53-0675, First Street Undercrossing No 53-0582, Alvarado Street Separation No 53-0617 and Avenue 60 on and offramp Bridge No 53-0986S. | Upgrade bridge rails, upgrade guardrail, and upgrade facilities to Americans with Disabilities Act (ADA) standards. | 1238 | Yes | 1238 | 572 | 572 | 1153 | No | 2764 | No | 2764 | 0 | 0 | 2466 | No | 69 | No | 69 | 0 | 0 | 64 | No | 2463 | No | 2463 | 0 | 0 | 2154 | No | 245 | No | 245 | 0 | 0 | 1400 | Yes | 5725 | No | 5725 | 0 | 0 | 5726 | Yes | 12504 | 12504 | 572 | 572 | 12963 |  | 2022-09-01 |  | 2022-09-01 | No | 2023-12-01 |  | 2023-12-01 | No | 2024-01-03 |  | 2024-01-03 | No | 2024-09-04 |  | 2024-09-04 | No |  |  | 2025-10-07 |  | 0 | No | Yes | No | No
491 | 07 | 5432 | VEN | 118 | Ven-118 CAPM | In Moorpark, from Montair Drive to Spring Road. | Rehabilitate pavement, upgrade guardrail, upgrade Transportation Management System (TMS) elements, and upgrade facilities to Americans with Disabilities Act (ADA) standards. | 1260 | Yes | 1260 | 1283 | 1283 | 1283 | Yes | 3220 | No | 3220 | 0 | 0 | 3542 | Yes | 1764 | No | 1764 | 0 | 0 | 243 | No | 2620 | No | 2620 | 0 | 0 | 3048 | Yes | 1412 | No | 1412 | 0 | 0 | 327 | No | 16744 | No | 16744 | 0 | 0 | 16225 | No | 27020 | 27020 | 1283 | 1283 | 24668 |  | 2022-02-01 | 2022-06-16 |  |  | 2024-03-22 |  | 2024-03-01 | No | 2024-03-29 |  | 2024-03-29 | No | 2024-11-15 |  | 2024-11-15 | No |  |  | 2026-03-13 |  | 0 | No | No | No | No
492 | 07 | 5440 | LA | 5 | I-5 North County Drainage Project | Near Castaic, from north of Lake Hughes Road to north of Vista Del Lago Road. | Rehabilitate culverts and replace a sand shed. | 1217 | Yes | 1217 | 1217 | 1217 | 1217 | No | 2980 | Yes | 2980 | 331 | 331 | 2864 | No | 242 | Yes | 242 | 1 | 1 | 170 | No | 2725 | No | 2725 | 0 | 0 | 2496 | No | 211 | No | 211 | 0 | 0 | 212 | Yes | 9850 | No | 9850 | 0 | 0 | 9848 | No | 17225 | 17225 | 1549 | 1549 | 16807 |  | 2021-12-17 | 2022-04-28 |  |  | 2023-06-16 |  | 2023-07-03 | Yes | 2023-08-01 |  | 2023-08-01 | No | 2024-02-02 |  | 2024-02-15 | No |  |  | 2025-07-25 |  | 0 | Yes | No | No | No
493 | 07 | 5484 | LA | 405 | LA-405, Pavement Rehabilitation | In and near the cities of Long Beach, Signal Hill, Los Angeles, and Carson, from the Orange County line to south of Route 110. | Rehabilitate pavement, upgrade signs, rehabilitate bridge, upgrade lighting, improve safety, rehabilitate Transportation Management System (TMS) elements and replace copper cabling with fiber, rehabilitate culverts, and upgrade facilities to Americans with Disabilities Act (ADA) standards. (G13 Contingency). | 2646 | Yes | 2646 | 2324 | 2324 | 2324 | No | 4800 | No | 4800 | 0 | 0 | 5514 | Yes | 703 | No | 703 | 0 | 0 | 440 | No | 0 | No | 0 | 0 | 0 | 9633 | Yes | 768 | No | 768 | 0 | 0 | 637 | No | 0 | No | 0 | 0 | 0 | 68995 | Yes | 8917 | 8917 | 2324 | 2324 | 87543 |  | 2021-12-28 | 2022-06-28 |  |  | 2024-03-08 |  | 2024-05-20 | No | 2024-04-05 |  | 2024-05-30 | No | 2024-10-25 |  | 2024-12-13 | No |  |  | 2028-07-24 |  | 0 | No | Yes | No | No
494 | 07 | 5490 | LA | 405 | LA-405 Bridge Seismic Restoration | In Lawndale, at Route 107, at Hawthorne Undercrossing Bridge No 53-1231. | Seismic retrofit of bridge and upgrade facilities to Americans with Disabilities Act (ADA) standards. | 543 | Yes | 543 | 356 | 356 | 356 | No | 2177 | Yes | 2177 | 737 | 737 | 2109 | No | 16 | Yes | 16 | 0 | 0 | 14 | No | 1926 | No | 1926 | 0 | 0 | 1730 | No | 43 | No | 43 | 0 | 0 | 43 | No | 3536 | No | 3536 | 0 | 0 | 3536 | No | 8241 | 8241 | 1093 | 1093 | 7788 |  | 2021-06-29 | 2021-06-29 |  |  | 2022-12-15 |  | 2023-03-01 | No | 2023-01-13 |  | 2023-03-30 | No | 2023-08-25 |  | 2023-08-25 | No |  |  | 2024-12-16 |  | 0 | No | No | No | No
495 | 07 | 5491 | LA | 1 | SR-1 Pavement Rehab (CAPM) in Malibu | In and near Malibu, from north of Serra Road to the Ventura County line (PM 62.867). | Rehabilitate pavement, upgrade facilities to Americans with Disabilities Act (ADA) standards, and upgrade guardrail. (G13 Contingency). | 1225 | Yes | 1225 | 1134 | 1134 | 1134 | No | 2960 | Yes | 2960 | 0 | 0 | 2808 | No | 320 | Yes | 320 | 0 | 0 | 299 | No | 0 | No | 0 | 0 | 0 | 3761 | Yes | 250 | No | 250 | 10 | 10 | 336 | Yes | 0 | No | 0 | 0 | 0 | 19897 | Yes | 4755 | 4755 | 1144 | 1144 | 28235 |  | 2022-01-18 | 2022-06-03 |  |  | 2024-02-12 |  | 2024-02-12 | No | 2024-03-15 |  | 2024-03-15 | No | 2024-11-15 |  | 2024-11-15 | No |  |  | 2027-02-26 |  | 0 | No | Yes | No | No
496 | 07 | 5499 | LA | 710 | Paint Hobart Yard OH Bridge | In Commerce and Vernon, at Hobart Rail Yard Overhead No 53-0840. | Rehabilitate, clean, and paint bridge. | 449 | Yes | 449 | 366 | 366 | 366 | No | 1602 | Yes | 1602 | 191 | 191 | 1674 | Yes | 413 | Yes | 413 | 6 | 6 | 361 | No | 3704 | No | 3704 | 0 | 0 | 3683 | No | 732 | No | 732 | 0 | 0 | 960 | Yes | 17117 | No | 17117 | 0 | 0 | 17117 | No | 24017 | 24017 | 563 | 563 | 24161 |  | 2021-11-15 | 2022-01-12 |  |  | 2024-01-16 |  | 2024-05-01 | Yes | 2024-03-29 |  | 2024-06-03 | No | 2025-01-22 |  | 2025-03-28 | No |  |  | 2028-09-25 |  | 0 | No | No | No | No
497 | 07 | 5506 | LA | 118 | LA 118 Drainage System Restoration | In the city of Los Angeles, near Pacoima, from east of Herrick Avenue to west of Foothill BoulevaRd Rehabilitate culverts. | LINING/REPLACE DAMAGED PIPE WITH HOLES | 511 | Yes | 511 | 486 | 486 | 486 | No | 1679 | Yes | 1679 | 0 | 0 | 1463 | No | 51 | Yes | 51 | 0 | 0 | 21 | No | 1318 | No | 1318 | 0 | 0 | 1282 | No | 272 | No | 272 | 0 | 0 | 272 | No | 2537 | No | 2537 | 0 | 0 | 2248 | No | 6368 | 6368 | 486 | 486 | 5772 |  | 2022-01-18 | 2022-06-15 |  |  | 2023-08-02 |  | 2023-08-02 | No | 2023-09-01 |  | 2023-09-01 | No | 2024-04-26 |  | 2024-04-26 | No |  |  | 2026-04-17 |  | 0 | No | No | No | No
498 | 07 | 5509 | LA | 2 | LA-2 Culvert | In and near the cities of Los Angeles, Glendale, La Canada Flintridge, and Pasadena, from east of Allesandro Street to the Mount Waterman ski lifts. | Rehabilitate drainage systems, enhance highway worker safety, and upgrade guardrail to concrete barrier. | 1246 | Yes | 1246 | 880 | 880 | 880 | No | 2332 | Yes | 2332 | 453 | 453 | 2333 | Yes | 13 | Yes | 13 | 0 | 0 | 13 | No | 2121 | No | 2121 | 0 | 0 | 1933 | No | 134 | No | 134 | 0 | 0 | 134 | No | 6976 | No | 6976 | 0 | 0 | 7111 | Yes | 12822 | 12822 | 1333 | 1333 | 12404 |  | 2021-08-31 | 2021-08-31 |  |  | 2022-11-07 |  | 2022-11-07 | No | 2022-12-05 |  | 2023-03-30 | Yes | 2023-08-28 |  | 2023-08-28 | No |  |  | 2025-11-04 |  | 0 | No | No | No | Yes
499 | 07 | 5515 | VEN | 34 | CAPM / ADA / Complete Streets | In and near Camarillo, from Rice Avenue to Route 118 (PM 17.663). | Rehabilitate pavement, upgrade guardrail, and upgrade facilities to Americans with Disabilities Act (ADA) standards. (G13 Contingency). | 1958 | Yes | 1958 | 1939 | 1939 | 1939 | No | 3983 | Yes | 3983 | 0 | 0 | 3892 | No | 2125 | No | 2125 | 0 | 0 | 2345 | Yes | 0 | No | 0 | 0 | 0 | 4890 | Yes | 484 | No | 484 | 0 | 0 | 1711 | Yes | 0 | No | 0 | 0 | 0 | 27434 | Yes | 8550 | 8550 | 1939 | 1939 | 42211 |  | 2022-05-24 | 2022-06-29 |  |  | 2024-04-15 |  | 2024-06-10 | No | 2024-05-15 |  | 2024-06-28 | No | 2025-02-19 |  | 2025-02-19 | No |  |  | 2026-12-03 |  | 0 | No | Yes | No | Yes
500 | 07 | 5516 | LA | 210 | Replacing pump plant | In Azusa, at North Vernon Avenue. | Upgrade pump plant. | 484 | Yes | 484 | 507 | 507 | 507 | Yes | 1017 | No | 1017 | 0 | 0 | 1733 | Yes | 77 | No | 77 | 0 | 0 | 16 | No | 789 | No | 789 | 0 | 0 | 699 | No | 17 | No | 17 | 0 | 0 | 3 | No | 1611 | No | 1611 | 0 | 0 | 1611 | No | 3995 | 3995 | 507 | 507 | 4569 |  | 2022-03-01 | 2022-06-28 |  |  | 2023-09-28 |  | 2023-12-02 | No | 2023-11-01 |  | 2024-01-02 | No | 2024-06-24 |  | 2024-08-01 | Yes |  |  | 2025-09-06 |  | 0 | Yes | Yes | No | No
501 | 07 | 5521 | LA | 605 | I-605 Rehab | In and near Santa Fe Springs, Whittier, Pico Rivera, Industry, and Baldwin Park, from Telegraph Road to Route 10. | Rehabilitate roadway, apply High Friction Surface Treatment (HFST), upgrade facilities to Americans with Disabilities Act (ADA) standards, upgrade guardrail, upgrade signs, enhance highway worker safety, and rehabilitate landscaping. (G13 Contingency). | 3096 | Yes | 3096 | 2536 | 2536 | 2536 | No | 9150 | Yes | 9150 | 1449 | 1449 | 8098 | No | 200 | Yes | 200 | 5 | 5 | 120 | No | 0 | No | 0 | 0 | 0 | 17531 | Yes | 40 | No | 40 | 0 | 0 | 40 | No | 0 | No | 0 | 0 | 0 | 182240 | Yes | 12486 | 12486 | 3990 | 3990 | 210565 |  | 2021-12-02 | 2021-12-02 |  |  | 2023-05-15 |  | 2023-05-15 | No | 2023-05-31 |  | 2023-05-31 | No | 2024-01-29 |  | 2024-01-29 | No |  |  | 2027-11-30 |  | 0 | No | Yes | No | No
502 | 07 | 5535 | LA | 5 | I-5, South Pavement Rehab | In Santa Fe Springs, Downey, and Commerce, from south of Route 5 to north of Atlantic BoulevaRd Rehabilitate pavement and replace concrete barrier. | PAVEMENT COLD PLANE AND OVERLAY | 1428 | Yes | 1428 | 917 | 917 | 917 | No | 3631 | Yes | 3631 | 1794 | 1794 | 3751 | Yes | 35 | Yes | 35 | 29 | 29 | 33 | No | 3600 | No | 3600 | 0 | 0 | 3476 | No | 20 | No | 20 | 0 | 0 | 12 | No | 24640 | No | 24640 | 0 | 0 | 24640 | No | 33354 | 33354 | 2740 | 2740 | 32829 |  | 2020-11-30 | 2021-05-25 |  |  | 2023-05-19 | 2022-05-10 |  |  | 2023-03-30 | 2022-06-29 |  |  | 2023-12-07 |  | 2023-01-13 | No |  |  | 2024-12-31 |  | 0 | No | No | No | No
503 | 07 | 5547 | LA | 10 | LA-10, Culvert Rehabilitation | In the city Los Angeles, from east of Bundy Drive to Route 5. | Rehabilitate culverts. | 609 | Yes | 609 | 516 | 516 | 516 | No | 1495 | Yes | 1495 | 4 | 4 | 1419 | No | 25 | Yes | 25 | 0 | 0 | 20 | No | 1694 | No | 1694 | 0 | 0 | 1284 | No | 10 | No | 10 | 0 | 0 | 18 | Yes | 6613 | No | 6613 | 0 | 0 | 3822 | No | 10446 | 10446 | 520 | 520 | 7079 |  | 2022-01-31 | 2022-04-15 |  |  | 2023-07-14 |  | 2023-08-10 | No | 2023-08-18 |  | 2023-09-18 | No | 2024-05-10 |  | 2024-03-11 | No |  |  | 2024-12-31 |  | 0 | No | No | No | No
504 | 07 | 5568 | VEN | 001 | BRIDGE RAIL UPGRADE | Near Seacliff & Ojai, upgrade bridge railings for #52-003 on Rte 1 & at #52-0044 & 52-0173 Rte 33 | Upgrade bridge railing | 1564 | No | 1564 | 1362 | 1362 | 1362 | No | 3306 | No | 3306 | 2218 | 2218 | 2219 | No | 326 | No | 326 | 40 | 40 | 40 | No | 3881 | No | 3881 | 0 | 0 | 3879 | No | 733 | No | 733 | 55 | 55 | 0 | No | 3480 | No | 3480 | 0 | 0 | 3480 | No | 13290 | 13290 | 3675 | 3675 | 10980 |  |  | 2019-09-30 |  |  |  | 2021-06-29 |  |  |  | 2021-06-30 |  |  |  |  | 2022-08-24 |  |  |  | 2024-08-09 |  | 0 | No | No | No | No
505 | 07 | 5619 | VEN | 33 | VEN-33 CAPM | In and near Ojai, from south of Parkview Drive to north of Foothill Trail. | Rehabilitate pavement, upgrade guardrail and traffic signals, install pedestrian crossings, and upgrade facilities to Americans with Disabilities Act (ADA) standards. | 1388 | Yes | 1388 | 0 | 0 | 1333 | No | 3057 | No | 3057 | 0 | 0 | 3626 | Yes | 2483 | No | 2483 | 0 | 0 | 2573 | Yes | 3013 | No | 3013 | 0 | 0 | 2828 | No | 3515 | No | 3515 | 0 | 0 | 3570 | Yes | 18325 | No | 18325 | 0 | 0 | 18325 | No | 31781 | 31781 | 0 | 0 | 32255 |  |  |  | 2023-09-30 |  |  |  | 2026-02-18 |  |  |  | 2026-03-20 |  |  |  | 2026-10-09 |  |  |  | 2028-02-21 |  | 0 | No | Yes | No | No
506 | 07 | 5640 | LA | 101 | Upgrade TMS elements on LA-101 | In the city of Los Angeles, from Route 405 to Route 27; also at Tujunga Avenue (PM 11.8L/R); also at the Los Angeles Regional Transportation Management Center (LARTMC) at 2901 West Broadway. | Upgrade Transportation Management System (TMS) elements, upgrade fiber optic lines, and upgrade communication equipment at hubs and at the LARTMC. | 973 | Yes | 973 | 4 | 4 | 972 | No | 3370 | No | 3370 | 0 | 0 | 3362 | No | 227 | No | 227 | 0 | 0 | 33 | No | 4269 | No | 4269 | 0 | 0 | 4162 | No | 718 | No | 718 | 0 | 0 | 718 | No | 21430 | No | 21430 | 0 | 0 | 21430 | No | 30987 | 30987 | 4 | 4 | 30677 |  |  |  | 2023-07-30 |  |  |  | 2025-02-07 |  |  |  | 2025-03-28 |  |  |  | 2025-11-26 |  |  |  | 2027-12-31 |  | 0 | No | No | No | No
507 | 07 | 5646 | LA | 14 | Upgrade and Install TMS on LA-14 | In and near Los Angeles and Santa Clarita, from Route 5 to Sand Canyon Road; also on Routes 101 (PM 11.8R), 405 (PM 48.48), and at the Los Angeles Regional Transportation Management Center (LARTMC) at 2901 West Broadway. | Upgrade Transportation Management System (TMS) elements, construct fiber optic lines, and upgrade communication equipment at hubs and at the LARTMC. | 1100 | Yes | 1100 | 0 | 0 | 950 | No | 2475 | No | 2475 | 0 | 0 | 2554 | Yes | 50 | No | 50 | 0 | 0 | 43 | No | 4550 | No | 4550 | 0 | 0 | 4452 | No | 61 | No | 61 | 0 | 0 | 61 | No | 25151 | No | 25151 | 0 | 0 | 25151 | No | 33387 | 33387 | 0 | 0 | 33211 |  |  |  | 2023-10-31 |  |  |  | 2025-01-22 |  |  |  | 2025-02-19 |  |  |  | 2025-09-10 |  |  |  | 2028-03-15 |  | 0 | No | No | No | No
508 | 07 | 5801 | VEN | 23 | Ven-23 Drainage, PE:JX | Near Fillmore, from Bellevue Avenue to Guiberson Road. | Rehabilitate trapezoidal earth channels and upgrade culverts. | 952 | Yes | 952 | 15 | 15 | 952 | No | 1758 | No | 1758 | 0 | 0 | 1723 | No | 20 | No | 20 | 0 | 0 | 20 | No | 1602 | No | 1602 | 0 | 0 | 1466 | No | 6 | No | 6 | 0 | 0 | 7 | Yes | 4685 | No | 4685 | 0 | 0 | 4685 | No | 9023 | 9023 | 15 | 15 | 8853 |  |  |  | 2023-04-14 |  |  |  | 2025-03-25 |  |  |  | 2025-04-15 |  |  |  | 2025-12-16 |  |  |  | 2026-12-16 |  | 0 | No | No | No | No
509 | 07 | 5802 | LA | 138 | Replace Drainage for Segment 9 | Near Longview, from west of 116th Street to Longview Road. | Construct Reinforced Concrete Box (RCB) culvert to replace perforated pipe system and concrete v-ditch. | 610 | Yes | 610 | 62 | 62 | 687 | Yes | 1550 | No | 1550 | 0 | 0 | 1557 | Yes | 1050 | No | 1050 | 0 | 0 | 1102 | Yes | 1175 | No | 1175 | 0 | 0 | 1111 | No | 743 | No | 743 | 0 | 0 | 743 | No | 5547 | No | 5547 | 0 | 0 | 3100 | No | 10675 | 10675 | 62 | 62 | 8300 |  |  |  | 2023-03-30 |  |  |  | 2025-02-25 |  |  |  | 2025-03-25 |  |  |  | 2025-11-04 |  |  |  | 2026-10-13 |  | 0 | No | No | No | No
510 | 07 | 5919 | LA | 91 | LA 91 Polyester | In Long Beach, at LA River (W91 - N710 & S710) Bridge No 53-2143F. | Replace portions of the bridge deck and apply polyester concrete overlay. (Bridge Deck Preservation). | 0 | No | 0 | 0 | 0 | 0 | No | 599 | Yes | 588 | 70 | 70 | 847 | Yes | 10 | Yes | 10 | 0 | 0 | 10 | No | 658 | No | 658 | 0 | 0 | 875 | Yes | 10 | No | 10 | 0 | 0 | 0 | No | 4350 | No | 4350 | 0 | 0 | 4240 | No | 5627 | 5616 | 70 | 70 | 5972 |  |  | 2021-10-08 |  |  |  |  | 2023-02-01 |  |  |  | 2023-03-31 |  |  |  | 2023-10-20 |  |  |  | 2023-11-01 |  | 0 | No | No | No | Yes
511 | 07 | 5920 | LA | 126 | Nickname Required | Near Santa Clarita, at Castaic Creek Bridge No 53-0093; also on Route 14 at Via Princessa Undercrossing No 53-2201k (PM R30.9). | Apply polyester concrete overlay to bridge deck and replace joint seals. (Bridge Deck Preservation). | 0 | No | 0 | 0 | 0 |  | No | 764 | Yes | 618 | 377 | 377 | 784 | Yes | 10 | Yes | 10 | 0 | 0 | 10 | No | 350 | No | 350 | 0 | 0 | 647 | Yes | 0 | No | 0 | 0 | 0 | 0 | No | 1318 | No | 1318 | 0 | 0 | 1318 | No | 2442 | 2296 | 377 | 377 | 2759 |  |  | 2021-10-18 |  |  |  | 2022-04-01 |  |  |  | 2022-06-15 |  |  |  |  | 2023-01-16 |  |  |  | 2023-11-17 |  | 0 | No | Yes | No | Yes
512 | 07 | 5921 | LA | 5 | LA 5 Methacrylate | In the city of Los Angeles, at Newell Street Undercrossing No 53-0162K; also on Route 110 at Beaudry Avenue Undercrossing No 53-0621H (PM 23.8); also on Route 2 at Avenue 36 Overcrossing No 53-0780 (PM 16.6). | Apply polyester concrete overlay to bridge decks, apply methacrylate bridge decks, repair spalls, and replace joint seals. (Bridge Deck Preservation). | 0 | No | 0 | 0 | 0 |  | No | 534 | Yes | 530 | 109 | 109 | 539 | Yes | 10 | Yes | 10 | 0 | 0 | 10 | No | 449 | No | 449 | 0 | 0 | 700 | Yes | 0 | No | 0 | 0 | 0 | 0 | No | 582 | No | 582 | 0 | 0 | 388 | No | 1575 | 1571 | 109 | 109 | 1637 |  |  | 2021-10-11 |  |  |  |  | 2023-02-01 |  |  |  | 2023-03-31 |  |  |  | 2023-10-20 |  |  |  | 2024-12-27 |  | 0 | No | Yes | No | Yes
513 | 07 | 5922 | LA | 210 | Nickname Required | In San Dimas, at the Metropolitan Water District Pipeline Undercrossing No 53-2071. | Apply polyester concrete overlay to bridge deck and replace joint seals. (Bridge Deck Preservation). | 0 | No | 0 | 0 | 0 |  | No | 517 | Yes | 460 | 275 | 275 | 560 | Yes | 10 | Yes | 10 | 0 | 0 | 10 | No | 366 | No | 366 | 0 | 0 | 588 | Yes | 0 | No | 0 | 0 | 0 | 0 | No | 780 | No | 780 | 0 | 0 | 780 | No | 1673 | 1616 | 275 | 275 | 1938 |  |  | 2021-10-08 |  |  |  | 2022-04-25 |  |  |  | 2022-06-28 |  |  |  |  | 2023-01-16 |  |  |  | 2023-11-28 |  | 0 | No | No | No | Yes
514 | 07 | 5994 | LA | 005 | LA 5 - Pavement Rehab | Pavement Preservation on Route 5 from 0.2 miles north of Lake Hughes to 0.7 miles south of Vista De Lago Road in Los Angeles County. | PAVEMENT PRESERVATION | 1408 | Yes | 1408 | 4 | 4 | 1503 | Yes | 0 | No | 0 | 0 | 0 | 3242 | Yes | 0 | No | 0 | 0 | 0 | 56 | Yes | 0 | No | 0 | 0 | 0 | 5661 | Yes | 0 | No | 0 | 0 | 0 | 298 | Yes | 0 | No | 0 | 0 | 0 | 37741 | Yes | 1408 | 1408 | 4 | 4 | 48501 |  |  |  | 2023-05-30 |  |  |  | 2024-11-27 |  |  |  | 2024-12-30 |  |  |  | 2025-06-30 |  |  |  | 2027-04-30 |  | 0 | No | Yes | No | No
515 | 08 | 0023C | RIV | 62 | RIV 62 MILL & OVERLAY | In and near Yucca Valley and Twentynine Palms, from 0.2 mile north of Indian Canyon Drive to the San Bernardino County line; also in San Bernardino County, from the Riverside County line to Yucca Mesa Road/La Contenta Road (PM 0.0/15.1) and from Bermuda Avenue to Athol Avenue (PM 29.3/33.6). | Pavement rehabilitation. | 1450 | No | 1450 | 1569 | 1569 | 1569 | Yes | 4050 | Yes | 4050 | 4025 | 4025 | 4025 | No | 1421 | Yes | 1421 | 1419 | 1419 | 1419 | No | 4658 | Yes | 4658 | 3425 | 3425 | 4650 | No | 2209 | No | 2209 | 267 | 267 | 972 | No | 28089 | Yes | 28089 | 23625 | 23625 | 28089 | No | 41877 | 41877 | 34330 | 34330 | 40724 | 2018-10-17 | 2016-06-28 | 2016-06-28 |  |  | 2019-12-16 | 2019-12-21 |  |  | 2020-03-16 | 2020-04-29 |  |  | 2021-01-15 | 2021-01-14 |  |  |  |  | 2022-11-30 |  | 25353 | No | No | No | No
516 | 08 | 0033E | SBD | 060 | SBd 60 - REPLACE PIPELINE, MONTE VISTA AND BENSON BRIDGES | IN CHINO FR PIPELINE AVE OC TO BENSON AVE OC | REMOVE & REPLACE OC STRUCTURES | 2243 | No | 2243 | 2123 | 2123 | 2123 | No | 3320 | Yes | 3320 | 3270 | 3270 | 3270 | No | 1280 | Yes | 1280 | 1122 | 1122 | 1183 | No | 5416 | Yes | 5416 | 5082 | 5082 | 5411 | No | 7795 | No | 7795 | 4901 | 4901 | 7763 | No | 21375 | Yes | 21299 | 19150 | 19074 | 21299 | No | 41429 | 41353 | 35648 | 35572 | 41049 |  |  | 2017-02-17 |  |  |  | 2018-05-21 |  |  |  | 2018-06-22 |  |  |  | 2019-04-09 |  |  |  |  | 2022-09-06 |  | 20399 | No | No | No | No
517 | 08 | 0043L | RIV | 60 | RIV 60 TRAFFIC OPERATIONS SYSTEM | In and near Moreno Valley, from west of Perris Boulevard to east of Gilman Springs Road. | Install Transportation Management System (TMS) elements. | 797 | Yes | 797 | 733 | 733 | 733 | No | 1587 | Yes | 1587 | 518 | 518 | 1129 | No | 23 | Yes | 23 | 1 | 1 | 57 | Yes | 2100 | No | 2100 | 0 | 0 | 2157 | Yes | 20 | No | 20 | 0 | 0 | 20 | No | 11427 | No | 11427 | 0 | 0 | 10030 | No | 15954 | 15954 | 1252 | 1252 | 14126 |  | 2021-11-03 | 2021-11-03 |  |  | 2023-04-03 |  | 2023-04-03 | No | 2023-04-28 |  | 2023-05-05 | No | 2023-12-07 |  | 2023-12-07 | No |  |  | 2025-08-15 |  | 0 | No | No | No | No
518 | 08 | 0046J | RIV | 60 | SR60 Truck Climbing/ Descending Lanes | Near Beaumont. | Construct new eastbound and westbuond truck lanes from Gilman Springs Road to 1.47 miles west of Jack Rabbit Trail and upgrade existing inside and outside shoulders to standard width. | 13880 | No | 4604 | 7995 | 2330 | 7995 | No | 12300 | No | 1500 | 3928 | 906 | 3928 | No | 200 | No | 200 | 0 | 0 | 0 | No | 3700 | No | 3700 | 0 | 0 | 17000 | Yes | 2853 | Yes | 806 | 106 | 6 | 270 | No | 118640 | Yes | 40000 | 63380 | 34762 | 106000 | No | 151573 | 50810 | 75409 | 38004 | 135193 |  | 2016-05-16 | 2016-05-16 |  |  | 2017-12-04 | 2018-06-11 |  |  | 2018-07-02 | 2018-08-15 |  |  | 2018-12-04 | 2019-01-25 |  |  | 2021-06-03 |  | 2024-11-15 | Yes | 95944 | Yes | Yes | No | Yes
519 | 08 | 0181J | SBD | 18 | SBD 18 CULVERTS | In and near Big Bear Lake and Lucerne Valley, at various locations, from Route 38 at Big Bear Lake Dam to Arctic Canyon Wash. | Replace culverts to ensure efficient drainage and preserve the integrity of the highway. | 1511 | Yes | 1511 | 1508 | 1508 | 1508 | No | 1555 | Yes | 1555 | 1323 | 1323 | 1547 | No | 1700 | Yes | 1700 | 523 | 523 | 935 | No | 1506 | Yes | 1506 | 0 | 0 | 1508 | Yes | 1400 | No | 700 | 118 | 0 | 124 | No | 2555 | Yes | 2555 | 0 | 0 | 2556 | Yes | 10227 | 9527 | 3472 | 3354 | 8178 |  | 2020-07-01 | 2020-08-21 |  |  | 2021-12-01 | 2022-02-09 |  |  | 2022-01-18 | 2022-03-28 |  |  | 2022-10-03 |  | 2022-12-01 | No |  |  | 2024-03-01 |  | 0 | No | No | No | No
520 | 08 | 0184C | SBD | 18 | SBD 18 RELINE OR REPLACE CULVERTS | In and near the city of San Bernardino, from 48th Street to Route 138. | Repair, reline and replace culverts. | 1016 | Yes | 1016 | 1013 | 1013 | 1013 | No | 1082 | Yes | 1082 | 1038 | 1038 | 1076 | No | 101 | Yes | 101 | 18 | 18 | 18 | No | 919 | Yes | 919 | 0 | 0 | 1007 | Yes | 385 | No | 385 | 36 | 36 | 353 | No | 6278 | Yes | 6278 | 0 | 0 | 6579 | Yes | 9781 | 9781 | 2105 | 2105 | 10046 |  | 2020-03-16 | 2020-03-23 |  |  | 2021-11-05 | 2021-07-01 |  |  | 2021-12-06 | 2021-12-08 |  |  | 2022-08-15 |  | 2022-07-26 | No |  |  | 2024-01-08 |  | 0 | Yes | No | No | Yes
521 | 08 | 0205C | SBD | 38 | SBd 38 Replace Culverts | Near Big Bear Lake, from Zaca Road to Route 18(PM 59.396). | Replace culverts. | 860 | Yes | 860 | 837 | 837 | 837 | No | 1930 | Yes | 1930 | 1904 | 1904 | 1904 | No | 2822 | Yes | 2822 | 1872 | 1872 | 1883 | No | 985 | Yes | 985 | 769 | 769 | 946 | No | 868 | No | 868 | 96 | 96 | 93 | No | 2294 | Yes | 2294 | 1270 | 1270 | 2294 | No | 9759 | 9759 | 6748 | 6748 | 7957 |  | 2018-10-17 | 2018-10-30 |  |  | 2020-03-02 | 2020-04-21 |  |  | 2020-03-16 | 2020-05-07 |  |  | 2020-09-15 | 2020-11-16 |  |  |  |  | 2022-08-01 |  | 2293 | No | No | No | No
522 | 08 | 0224N | VAR | VAR | SBD 60 Replace Lanes and Slabs - (G-13) | IN ONTARIO FR EUCLID AVE IC TO RIV CO LN & NEAR RIVERSIDE FROM SBD CO LN TO COUNTRY VILLAGE RD & FROM 0.7 MILES W/O VALLEY WAY TO JCT 60/91/215 IC | REPLACEMENT OF TWO OUTSIDE LANES AND CONCRETE SLABS | 2368 | No | 2368 | 2434 | 2434 | 2434 | Yes | 12074 | Yes | 12074 | 5303 | 5303 | 5303 | No | 106 | Yes | 106 | 32 | 32 | 32 | No | 12741 | Yes | 12741 | 12491 | 12491 | 12980 | Yes | 0 | No | 0 | 0 | 0 | 48 | Yes | 150717 | Yes | 150717 | 141507 | 141507 | 150717 | No | 178006 | 178006 | 161767 | 161767 | 171514 |  |  | 2016-02-18 |  |  |  | 2018-03-01 |  |  |  | 2018-06-20 |  |  |  | 2019-05-13 |  |  |  | 2022-06-06 |  |  | 145717 | Yes | Yes | Yes | Yes
523 | 08 | 3002C | RIV | 74 | RIV 74/79/371 UPGRADE TO STANDARD BRIDGE RAIL | In and near the cities of Lake Elsinore, Perris, Menifee and Hemet, at Leach Canyon Channel Bridge No 56-0750 and Blue Ridge Wash Bridge No 56-0257; also on Routes 79 and 371, at Arroyo Seco Bridge No 56-0189, and Cahuilla Bridge No 56-0490. | Bridge rail replacement, replace one bridges, and extend one culvert. | 1031 | Yes | 1031 | 1026 | 1026 | 1026 | No | 2850 | Yes | 2850 | 2756 | 2756 | 2756 | No | 80 | Yes | 80 | 70 | 70 | 70 | No | 2800 | Yes | 2800 | 1853 | 1853 | 2708 | No | 550 | No | 550 | 21 | 21 | 223 | No | 5910 | Yes | 5910 | 5581 | 5581 | 5910 | No | 13221 | 13221 | 11307 | 11307 | 12693 |  | 2018-04-02 | 2019-06-28 |  |  | 2019-06-03 | 2020-03-04 |  |  | 2019-08-01 | 2020-06-11 |  |  | 2020-03-02 | 2021-01-19 |  |  |  |  | 2024-04-05 |  | 5910 | No | No | No | No
524 | 08 | 3002S | SBD | 215 | SBD 215 MT VERNON/WASHINGTON ST OC | In Colton, from 0.3 mile south to 0.3 mile north of Washington Street Overcrossing No 54-0530. | Replace Overcrossing. | 1438 | Yes | 1438 | 1393 | 1393 | 1393 | No | 3894 | Yes | 3894 | 3840 | 3840 | 3840 | No | 864 | Yes | 664 | 829 | 663 | 851 | No | 4258 | Yes | 4258 | 2624 | 2624 | 5133 | Yes | 4357 | No | 4357 | 400 | 400 | 932 | No | 18539 | Yes | 16328 | 6519 | 5823 | 18539 | No | 33350 | 30939 | 15605 | 14743 | 30688 | 2018-10-17 | 2018-04-18 | 2018-04-18 |  |  | 2020-01-21 | 2020-04-13 |  |  | 2020-02-03 | 2020-06-02 |  |  | 2020-10-01 | 2021-03-25 |  |  |  |  | 2023-07-03 |  | 18538 | No | Yes | No | No
525 | 08 | 3003K | RIV | 15 | Temecula Lane Replacement | In and near Temecula, from the San Diego County line to 0.1 mile north of Temecula River Bridge; also in San Diego County from 0.1 mile south of the Riverside County line to the Riverside County line. | Rehabilitate roadway. | 1364 | Yes | 1364 | 959 | 959 | 959 | No | 1520 | Yes | 1520 | 1517 | 1517 | 1517 | No | 20 | Yes | 20 | 18 | 18 | 18 | No | 5065 | Yes | 5065 | 5035 | 5035 | 5067 | Yes | 10 | No | 10 | 0 | 0 | 10 | No | 32556 | Yes | 32556 | 27914 | 27914 | 32556 | No | 40535 | 40535 | 35443 | 35443 | 40127 | 2018-10-17 | 2018-03-23 | 2018-03-23 |  |  | 2019-04-02 | 2019-02-22 |  |  | 2019-08-06 | 2019-06-21 |  |  | 2020-01-22 | 2020-01-30 |  |  |  | 2022-05-06 |  |  | 32555 | No | No | No | No
526 | 08 | 3003M | RIV | 15 | RIV 015 CAPM & SLAB REPLACEMENT | In and near Corona and Norco, from 0.5 mile south of East Ontario Avenue to Route 60. | Concrete pavement slab replacement. | 1022 | Yes | 1022 | 859 | 859 | 859 | No | 1373 | Yes | 1373 | 1351 | 1351 | 1351 | No | 23 | Yes | 23 | 20 | 20 | 21 | No | 4834 | Yes | 4834 | 3663 | 3663 | 5327 | Yes | 36 | No | 36 | 0 | 0 | 36 | No | 25254 | Yes | 25254 | 20420 | 20420 | 25254 | No | 32542 | 32542 | 26313 | 26313 | 32848 | 2018-10-17 | 2018-04-13 | 2018-04-13 |  |  | 2020-01-03 | 2019-10-30 |  |  | 2020-03-02 | 2020-06-11 |  |  | 2021-01-15 | 2020-12-22 |  |  |  |  | 2022-11-15 |  | 25254 | No | No | No | No
527 | 08 | 3003U | SBD | 15 | SBD 15 REHAB | In Hesperia and Victorville, from Oak Hill Road to 0.1 mile south of Bear Valley Road. | Rehabilitate roadway. | 1190 | Yes | 1190 | 1173 | 1173 | 1173 | No | 7380 | Yes | 7380 | 7340 | 7340 | 7340 | No | 260 | Yes | 260 | 218 | 218 | 269 | Yes | 15391 | Yes | 15391 | 2404 | 2404 | 14134 | No | 298 | No | 298 | 203 | 203 | 298 | No | 133912 | Yes | 133912 | 21529 | 21529 | 133912 | No | 158431 | 158431 | 32867 | 32867 | 157126 | 2018-10-17 | 2018-05-17 | 2018-05-17 |  |  | 2019-11-04 | 2020-02-26 |  |  | 2020-02-03 | 2020-06-12 |  |  | 2020-10-29 | 2021-10-07 |  |  |  |  | 2025-01-07 |  | 133912 | No | No | No | No
528 | 08 | 3004C | SBD | 127 | SBD 127 NEAR BAKER PAVEMENT REHAB | Near Baker, from 2.3 miles north of Silver Lake Road to 3.8 miles south of the Inyo County line. | Rehabilitate pavement, upgrade guardrail, and construct shoulder backing. | 1749 | Yes | 1749 | 0 | 0 | 1715 | No | 2513 | No | 2513 | 0 | 0 | 2360 | No | 949 | No | 949 | 0 | 0 | 862 | No | 3427 | No | 3427 | 0 | 0 | 3110 | No | 92 | No | 92 | 0 | 0 | 92 | No | 36212 | No | 36212 | 0 | 0 | 36212 | No | 44942 | 44942 | 0 | 0 | 44351 |  | 2024-07-02 |  | 2024-07-02 | No | 2025-10-06 |  | 2025-10-06 | No | 2025-11-03 |  | 2025-11-03 | No | 2026-08-10 |  | 2026-08-10 | No |  |  | 2027-10-27 |  | 0 | No | No | No | No
529 | 08 | 3005Q | RIV | 74 | RIV 74 REPLACE 2 BRIDGES | Near Lake Elsinore, at Morrill Canyon Bridge No 56-0169; also near Hemet, at Strawberry Creek Bridge No 56-0180 (PM 53.4/54.7). | Replace structures/upgrade rails. | 2059 | Yes | 2059 | 2028 | 2028 | 2028 | No | 1839 | Yes | 1839 | 1755 | 1755 | 1954 | Yes | 173 | Yes | 173 | 62 | 62 | 309 | Yes | 3159 | No | 3159 | 0 | 0 | 3808 | Yes | 653 | No | 653 | 21 | 21 | 485 | No | 10948 | No | 10948 | 0 | 0 | 6991 | No | 18831 | 18831 | 3866 | 3866 | 15575 |  | 2021-03-01 | 2021-03-22 |  |  | 2022-03-01 | 2022-02-11 |  |  | 2022-04-01 | 2022-06-02 |  |  | 2022-12-01 |  | 2022-12-01 | No |  |  | 2024-12-02 |  | 0 | No | Yes | No | No
530 | 08 | 3006C | SBD | 10 | SBD 10 BRIDGE REHAB | In Colton at Colton Overhead No 54-0464R (PM R22.36). | Strengthen bridge and perform preventative maintenance. | 552 | Yes | 552 | 552 | 552 | 552 | No | 1058 | Yes | 1058 | 957 | 957 | 1043 | No | 130 | Yes | 130 | 69 | 69 | 120 | No | 0 | Yes | 0 | 0 | 0 | 592 | Yes | 62 | No | 62 | 5 | 5 | 3 | No | 0 | Yes | 0 | 0 | 0 | 1961 | Yes | 1802 | 1802 | 1583 | 1583 | 4271 |  | 2020-04-01 | 2020-07-24 |  |  | 2021-10-15 | 2022-03-28 |  |  | 2021-11-16 | 2022-05-02 |  |  | 2022-07-15 |  | 2022-12-01 | Yes |  |  | 2023-10-02 |  | 0 | No | Yes | No | No
531 | 08 | 3007L | SBD | 66 | SBD 066 UPGRADE TO STANDARD BRIDGE RAIL | In the city of San Bernardino, at Lytle Creek Channel Bridge No 54-0423; also on Route 215 at Little League Drive Overcrossing Bridge No 54-0533 (PM 14.9). | Upgrade bridge rails and widen bridges. | 967 | Yes | 967 | 666 | 666 | 666 | No | 2334 | No | 2334 | 0 | 0 | 2689 | Yes | 223 | No | 223 | 0 | 0 | 256 | Yes | 2914 | No | 2914 | 0 | 0 | 3402 | Yes | 377 | No | 377 | 0 | 0 | 0 | No | 6884 | No | 6884 | 0 | 0 | 5348 | No | 13699 | 13699 | 666 | 666 | 12361 |  | 2022-06-01 | 2022-06-29 |  |  | 2023-12-01 |  | 2024-04-02 | Yes | 2024-02-01 |  | 2024-05-01 | Yes | 2024-11-01 |  | 2025-01-03 | No |  |  | 2028-03-02 |  | 0 | No | Yes | No | No
532 | 08 | 3007M | SBD | 18 | SBD 18 PAVEMENT PRESERVATION | In and near Adelanto, from Route 395 Junction to Los Angeles County line. | Cold plane pavement and place Hot Mix Asphalt (HMA) and Rubberized Hot Mix Asphalt (RHMA) pavement. | 764 | Yes | 764 | 747 | 747 | 747 | No | 1947 | Yes | 1947 | 1945 | 1945 | 1945 | No | 300 | Yes | 300 | 299 | 299 | 299 | No | 2300 | Yes | 2300 | 783 | 783 | 1989 | No | 341 | No | 341 | 94 | 94 | 48 | No | 11415 | Yes | 11415 | 7392 | 7392 | 11415 | No | 17067 | 17067 | 11260 | 11260 | 16443 |  | 2019-11-01 | 2019-10-31 |  |  | 2021-04-01 | 2021-03-24 |  |  | 2021-05-03 | 2021-05-06 |  |  | 2022-02-01 | 2021-11-18 |  |  |  |  | 2023-02-01 |  | 11415 | No | No | No | No
533 | 08 | 3007P | SBD | 66 | SBD 66 CAPM | In San Bernardino, from Pepper Avenue to H Street (PM 20.14/23.156). | Rehabilitate pavement, add sidewalk as a complete streets element, and upgrade facilities to Americans with Disabilities Act (ADA) standards. | 1380 | Yes | 1380 | 1142 | 1142 | 1142 | No | 1743 | No | 1743 | 0 | 0 | 2643 | Yes | 2121 | No | 2121 | 0 | 0 | 2398 | Yes | 1576 | No | 1576 | 0 | 0 | 3043 | Yes | 2082 | No | 1041 | 21 | 0 | 0 | No | 12058 | No | 12058 | 0 | 0 | 13754 | Yes | 20960 | 19919 | 1163 | 1142 | 22980 |  | 2022-06-01 | 2022-06-29 |  |  | 2023-12-01 |  | 2024-04-02 | Yes | 2024-02-01 |  | 2024-05-01 | Yes | 2024-11-01 |  | 2025-01-03 | No |  |  | 2028-03-02 |  | 0 | No | Yes | No | No
534 | 08 | 3007S | SBD | 215 | SBD 215/259 INSTALL TMS FIELD ELEMENTS | In and near the city of San Bernardino, from Route 215/10 Connector to Route 215/15 Junction (PM 4.0/17.753); also on Route 259, from Route 259/215 Separation to Route 259/210 Junction (PM R0.0/1.5). | Install wireless Vehicle Detection Stations (VDS), Changeable Message Signs (CMS), Closed Circuit Television (CCTV) and Fiber Optic elements. | 436 | Yes | 436 | 387 | 387 | 387 | No | 1168 | Yes | 1168 | 1126 | 1126 | 1126 | No | 42 | Yes | 42 | 12 | 12 | 30 | No | 1301 | Yes | 1301 | 1098 | 1098 | 1667 | Yes | 10 | No | 10 | 0 | 0 | 0 | No | 6914 | Yes | 6914 | 5033 | 5033 | 6914 | No | 9871 | 9871 | 7656 | 7656 | 10124 |  | 2019-02-01 | 2019-02-27 |  |  | 2020-05-01 | 2020-02-20 |  |  | 2020-06-01 | 2020-05-04 |  |  | 2021-02-01 | 2020-12-15 |  |  |  |  | 2022-10-04 |  | 6914 | No | Yes | No | No
535 | 08 | 3008A | RIV | 10 | RIV 10 NR COACHELLA PVMT REHAB SEGMENT 1 (DESIGN/BUILD) | In and near Coachella, from 0.3 mile east of Coachella Canal to 0.2 mile east of Hazy Gulch Bridge. | Cold plane pavement and overlay with Portland Cement Concrete (PCC). Construct eastbound truck climbing lane. A one lane temporary detour will be constructed in the median for traffic handling. (This is a Design-Build project.). | 7900 | Yes | 7900 | 7546 | 7546 | 7546 | No | 2000 | Yes | 2000 | 1623 | 1623 | 1623 | No | 90 | Yes | 90 | 19 | 19 | 90 | No | 15400 | Yes | 15400 | 271 | 271 | 15338 | No | 0 | Yes | 0 | 13 | 0 | 13990 | Yes | 200497 | Yes | 200497 | 21669 | 21669 | 200497 | No | 225887 | 225887 | 31141 | 31128 | 239084 | 2021-01-28 | 2020-09-02 | 2020-09-17 |  |  | 2021-06-01 | 2021-03-01 |  |  | 2021-06-01 | 2021-04-30 |  |  | 2021-09-01 | 2022-03-28 |  |  |  |  | 2026-08-03 |  | 200496 | No | Yes | No | No
536 | 08 | 3008C | RIV | 74 | RIV 74 MILL AND OVERLAY PAVEMENT AND INCLUDE DIGOUTS | Near Perris and Hemet, from Route 215 (PM 27.540) to Route 79. | Rehabilitate pavement and install Transportation Management System (TMS) elements. (G13 Contingency). | 1568 | Yes | 1568 | 1541 | 1541 | 1541 | No | 1377 | Yes | 1377 | 262 | 262 | 1625 | Yes | 317 | Yes | 317 | 0 | 0 | 509 | Yes | 0 | No | 0 | 0 | 0 | 4161 | Yes | 80 | No | 80 | 1 | 1 | 81 | Yes | 0 | No | 0 | 0 | 0 | 16782 | Yes | 3342 | 3342 | 1804 | 1804 | 24699 |  | 2022-04-01 | 2022-03-25 |  |  | 2023-08-01 |  | 2023-08-01 | No | 2023-10-02 |  | 2023-10-02 | No | 2024-07-01 |  | 2024-07-01 | No |  |  | 2026-01-02 |  | 0 | No | Yes | No | No
537 | 08 | 3008G | RIV | 111 | RIV 111 PALM SPRINGS CAPM | In Palm Springs, from Golf Club Drive to West Gateway Drive. | Rehabilitate pavement. (G13 Contingency). | 901 | Yes | 901 | 781 | 781 | 781 | No | 0 | Yes | 0 | 0 | 0 | 1838 | Yes | 0 | Yes | 0 | 0 | 0 | 322 | Yes | 0 | No | 0 | 0 | 0 | 3082 | Yes | 10 | No | 10 | 1 | 1 | 64 | Yes | 0 | No | 0 | 0 | 0 | 15653 | Yes | 911 | 911 | 782 | 782 | 21740 |  | 2022-05-02 | 2022-05-06 |  |  | 2023-11-01 |  | 2023-11-01 | No | 2024-02-01 |  | 2024-01-16 | No | 2024-11-01 |  | 2024-10-01 | No |  |  | 2026-02-02 |  | 0 | No | Yes | No | Yes
538 | 08 | 3008K | SBD | 40 | SBD 40 BRIDGE SCOUR MITIGATION | Near Needles, at the Halfway Hills Wash Bridge No 54-0799L/R. | Replace bridges, replace and expand Rock Slope Protection (RSP) limits. (G13 Contingency). | 1732 | Yes | 1732 | 1732 | 1732 | 1732 | No | 2607 | Yes | 2607 | 2346 | 2346 | 2589 | No | 56 | Yes | 56 | 14 | 14 | 65 | Yes | 0 | Yes | 0 | 0 | 0 | 5231 | Yes | 151 | No | 121 | 51 | 51 | 53 | No | 0 | Yes | 0 | 0 | 0 | 18588 | Yes | 4546 | 4516 | 4143 | 4143 | 28258 |  | 2020-10-01 | 2021-01-29 |  |  | 2022-03-01 | 2022-03-01 |  |  | 2022-04-01 | 2022-05-09 |  |  | 2022-11-02 |  | 2022-11-14 | No |  |  | 2024-08-01 |  | 0 | No | Yes | No | No
539 | 08 | 3008N | RIV | 10 | RIV 10 REPLACE EXISTING ROCK SLOPE PROTECTION | Near Desert Center, from Krume Ditch to Wide Ditch. | Replace existing Rock Slope Protection (RSP) to prevent further scour damage and preserve the integrity of twenty-four bridges. (G13 Contingency). | 1264 | Yes | 1264 | 447 | 447 | 447 | No | 1441 | Yes | 1441 | 1312 | 1312 | 1542 | Yes | 259 | Yes | 259 | 36 | 36 | 186 | No | 3955 | Yes | 3955 | 0 | 0 | 3228 | No | 281 | No | 279 | 158 | 156 | 286 | Yes | 0 | Yes | 0 | 0 | 0 | 8400 | Yes | 7200 | 7198 | 1953 | 1951 | 14089 |  | 2020-09-23 | 2020-10-26 |  |  | 2022-02-16 | 2021-12-27 |  |  | 2022-03-16 | 2022-05-05 |  |  | 2022-11-04 |  | 2023-03-01 | Yes |  |  | 2025-01-02 |  | 0 | No | Yes | No | No
540 | 08 | 3008U | RIV | 010 | RIV 10 PAVEMENT REPLACEMENT | IN BEAUMONT & BANNING FROM JCT 10/60 SEP TO JCT 10/111 SEP | PAVEMENT REPLACEMENT LANES 3 & 4 & OUTSIDE SHOULDERS WITH JPCP, OVERLAY INSIDE SHOULDER, CONCRETE SLAB REPLACEMENT LANE 1 & 2 & UPGRADE CURB RAMPS | 5375 | No | 5375 | 728 | 728 | 728 | No | 10817 | No | 10817 | 7140 | 7140 | 7140 | No | 562 | No | 562 | 67 | 67 | 67 | No | 17342 | No | 17342 | 13530 | 13530 | 17397 | Yes | 32 | No | 32 | 0 | 0 | 10 | No | 202673 | No | 202673 | 148688 | 148688 | 202673 | No | 236801 | 236801 | 170153 | 170153 | 228015 |  |  | 2015-12-22 |  |  |  | 2018-02-08 |  |  |  | 2018-06-12 |  |  |  | 2019-12-16 |  |  |  |  | 2023-02-28 |  | 202672 | Yes | Yes | Yes | Yes
541 | 08 | 3008Y | RIV | 10 | RIV 10 DESERT CENTER PAVEMENT REHAB: MAINLINE, SHOULDERS, RAMPS G-13 | Near Blythe, from 0.2 mile west of Route 177 to 0.2 mile east of Teed Ditch Bridge. | Cold plane mainline pavement and overlay with Portland Cement Concrete (PCC). The shoulders and ramps will be milled and overlaid with Hot Mix Asphalt (HMA-A). | 16900 | Yes | 16900 | 12169 | 12169 | 12169 | No | 2000 | Yes | 2000 | 1949 | 1949 | 1949 | No | 153 | Yes | 153 | 21 | 21 | 153 | No | 37509 | Yes | 37509 | 5649 | 5649 | 34821 | No | 9000 | No | 9000 | 338 | 338 | 9010 | Yes | 289222 | Yes | 289222 | 92477 | 92477 | 289222 | No | 354784 | 354784 | 112603 | 112603 | 347324 | 2020-01-29 | 2019-11-15 | 2019-11-15 |  |  | 2020-05-01 | 2020-04-10 |  |  | 2020-06-01 | 2020-06-11 |  |  | 2021-05-03 | 2021-04-15 |  |  |  |  | 2024-07-01 |  | 289221 | No | No | No | No
542 | 08 | 3009A | SBD | 10 | SBD 10 INSTALL TMS ELEMENTS | In and near Redlands, from Route 210 Junction to the Riverside County line (PM R39.16). | Install wireless Vehicle Detection Stations (VDS) pole, Changeable Message Signs (CMS), Closed Circuit Television (CCTV), Data Node Cabinet and Fiber Optic elements. | 300 | Yes | 300 | 234 | 234 | 234 | No | 1000 | Yes | 1000 | 835 | 835 | 835 | No | 33 | Yes | 33 | 24 | 24 | 29 | No | 1600 | Yes | 1600 | 1477 | 1477 | 1808 | Yes | 10 | No | 10 | 0 | 0 | 60 | Yes | 6586 | Yes | 6586 | 5648 | 5648 | 6586 | No | 9529 | 9529 | 8218 | 8218 | 9552 |  | 2018-06-01 | 2018-06-18 |  |  | 2019-05-01 | 2019-02-19 |  |  | 2019-06-03 | 2019-06-12 |  |  | 2019-11-01 | 2019-11-22 |  |  |  |  | 2022-08-31 |  | 6586 | No | No | No | No
543 | 08 | 3009E | SBD | 210 | SBD 210 GAP CLOSURE PROJECT | FR HIGHLAND AVE TO JCT RTE 10 | ADD 1 MF LN IN EACH DIRECTION & RECONSTRUCT EXISTING EXIT AND ENTRANCE RAMPS, WIDEN SHOULDER IN MEDIAN, ADD AUXILIARY LNS AT SELECT LOCS & IMPROVE BASELINE RD IC | 0 | No | 0 | 1 | 0 | 1 | Yes | 0 | No | 0 | 22 | 6 | 22 | Yes | 0 | No | 0 | 0 | 0 | 0 | No | 0 | No | 0 | 0 | 0 | 0 | No | 0 | No | 0 | 0 | 0 | 0 | No | 110815 | No | 42121 | 28020 | 9333 | 110792 | No | 110815 | 42121 | 28043 | 9339 | 110815 |  |  | 2016-12-16 |  |  |  | 2019-01-02 |  |  |  | 2019-01-18 |  |  |  | 2019-11-15 |  |  |  |  | 2023-08-01 |  | 128826 | No | No | No | No
544 | 08 | 3009H | SBD | 395 | SBD 395 MILL 0.20’ AND OVERLAY 0.20’ RUBBERIZED ASPHALT WITH DIGOUTS | In and near Hesperia, Victorville, and Adelanto, from Route 15 to 3.1 miles north of Route 58. | Rehabilitate pavement (PM R3.981/11.2 and PM 16.6/35.5), install Changeable Message Signs (CMS), upgrade guardrail and sign panels, and upgrade facilities to Americans with Disabilities Act (ADA) standards. | 1240 | Yes | 1240 | 1234 | 1234 | 1234 | No | 0 | Yes | 0 | 0 | 0 | 1987 | Yes | 0 | Yes | 0 | 0 | 0 | 699 | Yes | 3837 | No | 3837 | 0 | 0 | 3635 | No | 363 | No | 363 | 6 | 6 | 331 | No | 31000 | No | 31000 | 0 | 0 | 26714 | No | 36440 | 36440 | 1240 | 1240 | 34600 |  | 2022-04-01 | 2022-05-17 |  |  | 2023-04-03 |  | 2023-04-03 | No | 2023-05-05 |  | 2023-05-05 | No | 2024-01-05 |  | 2024-01-05 | No |  |  | 2024-11-04 |  | 0 | No | Yes | No | No
545 | 08 | 3009K | RIV | 10 | Riv 10 Blythe Pavement Rehab: mainline, shoulders, ramps | In and near Blythe, from Teed Ditch Bridge to Arizona State line (PM 156.492). | Cold plane mainline pavement and overlay with concrete pavement. The shoulders and ramps will be milled and overlaid with asphalt pavement. A two lane temporary detour will be constructed in the median for traffic handling. (G13 Contingency). | 9000 | Yes | 9000 | 8378 | 8378 | 8378 | No | 11200 | Yes | 11200 | 9019 | 9019 | 11390 | Yes | 329 | Yes | 329 | 294 | 294 | 331 | Yes | 0 | No | 0 | 0 | 0 | 28967 | Yes | 18516 | No | 9258 | 153 | 0 | 9257 | No | 0 | No | 0 | 0 | 0 | 218526 | Yes | 39045 | 29787 | 17844 | 17691 | 276849 | 2020-10-22 | 2020-08-28 | 2020-08-28 |  |  | 2022-04-01 | 2022-06-01 |  |  | 2022-05-02 | 2022-06-27 |  |  | 2023-04-03 |  | 2023-04-03 | No |  |  | 2028-04-02 |  | 0 | No | Yes | No | No
546 | 08 | 3009N | SBD | 71 | SBD 71 INSTALL, CCTV, CMS, VDS & FIBER OPTIC COMM SYS | In and near Chino and Chino Hills, from the Los Angeles County line to the Riverside County line (PM R8.478); also in Riverside County, from San Bernardino County line to Route 91 (PM R0.0 to PM R3.0). | Replace and upgrade existing communication elements and install Closed Circuit Television Cameras (CCTV) for the Traffic Management System (TMS). | 561 | Yes | 561 | 414 | 414 | 414 | No | 1747 | Yes | 1747 | 1743 | 1743 | 1743 | No | 113 | Yes | 113 | 27 | 27 | 27 | No | 1746 | Yes | 1746 | 778 | 778 | 1772 | Yes | 99 | No | 99 | 0 | 0 | 73 | No | 7976 | Yes | 7976 | 5331 | 5331 | 7976 | No | 12242 | 12242 | 8293 | 8293 | 12005 |  | 2018-12-03 | 2018-12-14 |  |  | 2020-01-06 | 2019-12-30 |  |  | 2020-05-01 | 2020-04-15 |  |  | 2021-01-05 | 2020-11-17 |  |  |  |  | 2022-10-18 |  | 7975 | No | Yes | No | Yes
547 | 08 | 3009P | SBD,LA | 10 | I-10 Express Lanes-San Antonio Ave to Route 15 (Contract 1) | From LA/SBd Co Ln to I-10/I-15 Interchange & in LA County from 0.4 Mi W/o White Ave OC to LA/SBd Co Ln; Implement two express lanes in each direction for a total of four general purpose and two express lanes in each direction with auxiliary lanes, widening undercrossings, and reconstruction of ramps and lane transitions where needed. | This project will be delivered using Design-Build method (TCIF 128). | 213 | No | 0 | 166 | 0 | 213 | No | 62293 | No | 0 | 0 | 0 | 0 | No | 0 | No | 0 | 0 | 0 | 0 | No | 0 | No | 0 | 11831 | 0 | 0 | No | 49219 | No | 0 | 0 | 0 | 56500 | Yes | 817466 | Yes | 8213 | 193093 | 57424 | 810185 | No | 929191 | 8213 | 205090 | 57424 | 866898 | 2018-10-17 | 2017-07-06 |  |  |  | 2022-03-01 | 2018-01-16 |  |  | 2021-11-01 | 2018-01-16 |  |  | 2018-07-01 | 2018-09-07 |  |  | 2024-02-01 |  | 2023-08-01 | No | 807571 | No | Yes | No | No
548 | 08 | 3009R | SBD | 60 | SBD 60 @ RAMONA OC | In Chino, at Ramona Avenue Overcrossing No 54-0745. | Improve freight corridor movement by removing vertical clearance constraint. | 5822 | Yes | 5822 | 4164 | 4164 | 4164 | No | 1675 | Yes | 1675 | 1596 | 1596 | 1596 | No | 50 | Yes | 50 | 13 | 13 | 20 | No | 2420 | Yes | 2420 | 307 | 307 | 2379 | No | 120 | No | 120 | 14 | 14 | 25 | No | 9908 | Yes | 9908 | 698 | 698 | 9908 | No | 19995 | 19995 | 6792 | 6792 | 18092 |  | 2020-05-01 | 2020-06-03 |  |  | 2021-03-01 | 2020-12-17 |  |  | 2021-07-01 | 2021-06-11 |  |  | 2022-02-02 | 2022-02-04 |  |  |  |  | 2023-12-05 |  | 9908 | No | No | No | No
549 | 08 | 3011A | RIV | 60 | RIV 60 INSTALL NEW RAMP METERING SYSTEMS | In the cities of Jurupa Valley and Riverside, from Wineville Road to west of Route 91/215 Separation. | Install ramp meters and other Transportation Management System (TMS) elements, widen ramps for High-Occupancy Vehicle (HOV) bypass, upgrade facilities to Americans with Disabilities Act (ADA) standards, and install Maintenance Vehicle Pullouts (MVPs). | 1233 | Yes | 1233 | 1178 | 1178 | 1178 | No | 2083 | Yes | 2083 | 859 | 859 | 2060 | No | 64 | Yes | 64 | 22 | 22 | 68 | Yes | 2774 | No | 2774 | 0 | 0 | 2191 | No | 10 | No | 10 | 0 | 0 | 59 | Yes | 12595 | No | 12595 | 0 | 0 | 11133 | No | 18759 | 18759 | 2059 | 2059 | 16689 |  | 2021-10-11 | 2021-10-19 |  |  | 2022-12-01 |  | 2022-12-01 | No | 2023-01-03 |  | 2023-01-03 | No | 2023-09-07 |  | 2023-09-07 | No |  |  | 2025-09-08 |  | 0 | No | No | No | No
550 | 08 | 3011E | RIV | 215 | RIV 215 CAPM | Near Murrieta, from 1 mile north of Clinton Keith Road to 1 mile north of Newport Road. | Rehabilitate pavement, replace shoulder rumble strip, upgrade culverts, upgrade guardrail, stabilize slopes, and enhance highway worker safety. | 1374 | Yes | 1374 | 1119 | 1119 | 1119 | No | 2316 | Yes | 2316 | 701 | 701 | 2027 | No | 43 | Yes | 43 | 35 | 35 | 89 | Yes | 3544 | No | 3544 | 0 | 0 | 3332 | No | 20 | No | 20 | 2 | 2 | 78 | Yes | 27553 | No | 27553 | 0 | 0 | 25450 | No | 34850 | 34850 | 1857 | 1857 | 32095 |  | 2021-11-01 | 2021-11-03 |  |  | 2023-02-01 |  | 2023-03-15 | No | 2023-03-01 |  | 2023-04-05 | No | 2023-10-02 |  | 2023-11-01 | No |  |  | 2025-10-01 |  | 0 | No | No | No | No
551 | 08 | 3011F | SBD | 247 | SBD 247 PAVEMENT AND SHOULDER WIDENING | In and near Yucca Valley, from Route 62 to north of Gin Road. | Rehabilitate pavement and widen shoulders. | 1694 | Yes | 1694 | 1464 | 1464 | 1464 | No | 2073 | No | 2073 | 0 | 0 | 1740 | No | 2090 | No | 2090 | 0 | 0 | 2400 | Yes | 2700 | No | 2700 | 0 | 0 | 2380 | No | 787 | No | 787 | 24 | 24 | 1022 | Yes | 28500 | No | 28500 | 0 | 0 | 25087 | No | 37844 | 37844 | 1488 | 1488 | 34093 |  | 2022-03-01 | 2022-06-08 |  |  | 2024-03-01 |  | 2024-03-01 | No | 2024-04-02 |  | 2024-04-02 | No | 2025-01-03 |  | 2025-01-03 | No |  |  | 2026-07-31 |  | 0 | No | No | No | No
552 | 08 | 3011G | SBD | 83 | SBD 83 CAPM AND CURB RAMPS | In Ontario, from south of Cedar Street to Route 10. | Rehabilitate pavement and upgrade facilities to Americans with Disabilities Act (ADA) standards. (G13 Contingency). | 3342 | Yes | 3342 | 2258 | 2258 | 3818 | Yes | 5553 | No | 5553 | 0 | 0 | 5417 | No | 1772 | No | 1772 | 0 | 0 | 952 | No | 0 | No | 0 | 0 | 0 | 5150 | Yes | 646 | No | 646 | 0 | 0 | 748 | Yes | 0 | No | 0 | 0 | 0 | 21175 | Yes | 11313 | 11313 | 2258 | 2258 | 37260 |  | 2022-10-03 |  | 2023-08-14 | Yes | 2024-05-01 |  | 2024-05-20 | No | 2024-06-03 |  | 2024-06-17 | No | 2025-03-03 |  | 2025-03-03 | No |  |  | 2027-04-01 |  | 0 | Yes | Yes | No | No
553 | 08 | 3011H | RIV | 215 | RIV 215 CAPM IN PERRIS | In and near Perris, from south of San Jacinto River Bridge to north of Ramona Expressway. | Rehabilitate pavement, upgrade facilities to Americans with Disabilities Act (ADA) standards, upgrade guardrail, enhance highway worker safety, and install slope stabilization and erosion control measures. (G13 Contingency). | 1678 | Yes | 1678 | 1603 | 1603 | 1603 | No | 2576 | Yes | 2576 | 2904 | 328 | 2112 | No | 51 | Yes | 51 | 53 | 2 | 59 | Yes | 0 | No | 0 | 4261 | 0 | 3802 | Yes | 77 | No | 77 | 0 | 0 | 20 | No | 0 | No | 0 | 33041 | 0 | 33041 | Yes | 4382 | 4382 | 41862 | 1933 | 40637 |  | 2021-12-23 | 2021-12-23 |  |  | 2023-11-02 |  | 2023-11-02 | No | 2023-12-04 |  | 2023-12-04 | No | 2024-08-01 |  | 2024-08-01 | No |  |  | 2028-03-30 |  | 0 | No | Yes | No | No
554 | 08 | 3011J | SBD | 18 | SBD 18 CAPM MILL AND OVERLAY | In Apple Valley and Victorville, from Apple Valley Inn Road/Dale Evans Parkway to Route 15. | Rehabilitate pavement, rehabilitate drainage systems, upgrade facilities to Americans with Disabilities Act (ADA) standards, upgrade signs, and construct sidewalk, Light Emitting Diode (LED) lighting, enhanced crosswalks, bike lanes, and flashing beacons as complete streets elements. | 2112 | Yes | 2112 | 1830 | 1830 | 1830 | No | 2753 | Yes | 2753 | 0 | 0 | 2709 | No | 1657 | Yes | 1657 | 0 | 0 | 1860 | Yes | 3480 | No | 3480 | 0 | 0 | 3619 | Yes | 566 | No | 566 | 12 | 12 | 778 | Yes | 16274 | No | 16274 | 0 | 0 | 16441 | Yes | 26842 | 26842 | 1842 | 1842 | 27237 |  | 2022-04-01 | 2022-05-23 |  |  | 2023-10-02 |  | 2023-12-01 | No | 2024-01-02 |  | 2024-01-02 | No | 2024-09-16 |  | 2024-10-01 | No |  |  | 2026-04-01 |  | 0 | No | No | No | No
555 | 08 | 3011K | SBD | 18 | SBD DRAINAGE/CULVERTS AND ITS | Near Big Bear Lake, from Arrowbear Drive to Route 38. | Rehabilitate culverts and install Changeable Message Sign (CMS). | 1472 | Yes | 1472 | 1220 | 1220 | 1220 | No | 1260 | No | 1260 | 0 | 0 | 1451 | Yes | 23 | No | 23 | 0 | 0 | 333 | Yes | 1742 | No | 1742 | 0 | 0 | 1602 | No | 452 | No | 452 | 3 | 3 | 523 | Yes | 4988 | No | 4988 | 0 | 0 | 4571 | No | 9937 | 9937 | 1223 | 1223 | 9700 |  | 2022-05-02 | 2022-06-30 |  |  | 2023-11-15 |  | 2023-11-15 | No | 2023-12-15 |  | 2024-01-02 | No | 2024-08-08 |  | 2024-10-01 | No |  |  | 2026-11-02 |  | 0 | No | Yes | No | No
556 | 08 | 3011Q | RIV | 10 | BRIDGE SCOUR | Near Chiriaco Summit, at Three Star Ditch Bridge No 59-0129R/L; also at Determination Ditch Bridge No 59-0124R/L (PM R90.9). | Replace existing Rock Slope Protection (RSP) to restore scour protection. | 1250 | Yes | 1250 | 1019 | 1019 | 1301 | Yes | 1912 | No | 1912 | 0 | 0 | 2381 | Yes | 51 | No | 51 | 0 | 0 | 41 | No | 2651 | No | 2651 | 0 | 0 | 2525 | No | 395 | No | 395 | 0 | 0 | 250 | No | 10115 | No | 10115 | 0 | 0 | 6408 | No | 16374 | 16374 | 1019 | 1019 | 12906 |  | 2022-08-04 |  | 2022-08-04 | No | 2023-09-05 |  | 2023-09-05 | No | 2023-10-02 |  | 2023-10-02 | No | 2024-06-06 |  | 2024-06-06 | No |  |  | 2025-05-06 |  | 0 | No | Yes | No | No
557 | 08 | 3011R | SBD | 15 | SBD 15 Seismic Work | In Ontario, at S15-E10 Connector Overcrossing No 54-0910F. | Seismic retrofit and bridge rail upgrade to make standaRd | 1090 | Yes | 1090 | 1005 | 1005 | 1005 | No | 2241 | Yes | 2241 | 242 | 242 | 2306 | Yes | 31 | Yes | 31 | 0 | 0 | 26 | No | 2380 | No | 2380 | 0 | 0 | 2366 | No | 10 | No | 10 | 0 | 0 | 10 | No | 15130 | No | 15130 | 0 | 0 | 14145 | No | 20882 | 20882 | 1247 | 1247 | 19858 |  | 2022-01-18 | 2022-02-11 |  |  | 2023-07-03 |  | 2023-07-03 | No | 2023-08-01 |  | 2023-08-01 | No | 2024-05-01 |  | 2024-05-15 | No |  |  | 2025-10-15 |  | 0 | No | No | No | No
558 | 08 | 3011S | RIV | 243 | RIV 243 MILL AND OVERLAY PAVEMENT | Near Mountain Center, Idyllwild and Banning, from Route 74 to Route 10. | Rehabilitate pavement and drainage systems; upgrade guardrail, lighting, and sign panels; upgrade facilities to Americans with Disabilities Act (ADA) standards; and enhance highway worker safety improvements. | 1150 | Yes | 1150 | 1095 | 1095 | 1095 | No | 1311 | No | 1311 | 0 | 0 | 1482 | Yes | 60 | No | 60 | 0 | 0 | 58 | No | 2708 | No | 2708 | 0 | 0 | 2747 | Yes | 477 | No | 477 | 3 | 3 | 453 | No | 20794 | No | 20794 | 0 | 0 | 16437 | No | 26500 | 26500 | 1098 | 1098 | 22272 |  | 2022-06-03 | 2022-06-20 |  |  | 2023-12-05 |  | 2023-12-05 | No | 2024-03-06 |  | 2024-03-06 | No | 2025-01-03 |  | 2025-01-03 | No |  |  | 2026-10-08 |  | 0 | No | No | No | No
559 | 08 | 3011U | SBD | 215 | CAPITAL PREVENTIVE MAINTENANCE (CAPM) | In the cities of Colton and San Bernardino, from south of Route 10 to Mill Street. | Rehabilitate pavement, upgrade safety devices, upgrade facilities to Americans with Disabilities Act (ADA) standards, and enhance highway worker safety. | 645 | Yes | 645 | 573 | 573 | 573 | No | 1263 | Yes | 1263 | 538 | 538 | 1341 | Yes | 129 | Yes | 129 | 9 | 9 | 112 | No | 2030 | No | 2030 | 0 | 0 | 1565 | No | 22 | No | 22 | 0 | 0 | 23 | Yes | 15718 | No | 15718 | 0 | 0 | 13188 | No | 19807 | 19807 | 1120 | 1120 | 16802 |  | 2021-08-09 | 2021-08-09 |  |  | 2022-11-09 |  | 2022-11-03 | No | 2023-03-03 |  | 2023-02-01 | No | 2023-12-04 |  | 2023-09-05 | No |  |  | 2025-03-04 |  | 0 | No | No | No | No
560 | 08 | 3011V | RIV | 10 | RIV 010 Mill and overlay pavement | In and near Beaumont, from east of Brookside Avenue to Pennsylvania Avenue. | Rehabilitate roadway, lighting, and drainage systems, upgrade guardrail, improve highway worker safety, and upgrade facilities to Americans with Disabilities Act (ADA) standards. | 2261 | Yes | 2261 | 0 | 0 | 2374 | Yes | 4755 | No | 4755 | 0 | 0 | 4954 | Yes | 26 | No | 26 | 0 | 0 | 31 | Yes | 6294 | No | 6294 | 0 | 0 | 5359 | No | 26 | No | 26 | 0 | 0 | 26 | No | 53462 | No | 53462 | 0 | 0 | 53462 | No | 66824 | 66824 | 0 | 0 | 66206 |  |  |  | 2023-11-01 |  |  |  | 2025-12-01 |  |  |  | 2026-01-02 |  |  |  | 2026-10-02 |  |  |  | 2028-01-03 |  | 0 | No | No | No | No
561 | 08 | 3011W | RIV | 10 | RIV 10 PAVEMENT REHAB | In Calimesa, from the San Bernardino County line to east of Brookside Avenue. | Rehabilitate roadway, improve highway worker safety, upgrade median barrier, signs, guardrail, drainage, and upgrade facilities to Americans with Disabilities Act (ADA) standards. | 2988 | Yes | 2988 | 0 | 0 | 3092 | Yes | 3150 | No | 3150 | 0 | 0 | 2654 | No | 318 | No | 318 | 0 | 0 | 291 | No | 4762 | No | 4762 | 0 | 0 | 3746 | No | 56 | No | 56 | 0 | 0 | 56 | No | 57091 | No | 57091 | 0 | 0 | 57091 | No | 68365 | 68365 | 0 | 0 | 66930 |  |  |  | 2023-10-05 |  |  |  | 2025-01-08 |  |  |  | 2025-01-15 |  |  |  | 2025-10-15 |  |  |  | 2026-09-15 |  | 0 | No | No | No | No
562 | 08 | 3011Y | RIV | 215 | RIV 215 CAPM | In the city of Riverside, from south of Martin Luther King Boulevard to north of Chicago Avenue. | Rehabilitate pavement, upgrade curb ramps to Americans with Disabilities Act (ADA) standards, and replace sign structures and signs. (G13 Contingency). | 1022 | Yes | 1022 | 1011 | 1011 | 1011 | No | 1938 | Yes | 1938 | 240 | 240 | 1948 | Yes | 106 | Yes | 106 | 18 | 18 | 116 | Yes | 0 | No | 0 | 0 | 0 | 2904 | Yes | 22 | No | 22 | 2 | 2 | 22 | No | 0 | No | 0 | 0 | 0 | 18490 | Yes | 3088 | 3088 | 1271 | 1271 | 24491 |  | 2022-02-01 | 2022-01-31 |  |  | 2023-07-03 |  | 2023-07-03 | No | 2023-08-01 |  | 2023-08-01 | No | 2024-03-04 |  | 2024-04-02 | No |  |  | 2025-11-03 |  | 0 | Yes | Yes | Yes | Yes
563 | 08 | 3012J | RIV | 10 | RIV 10 REPLACE EXISTING ROCK SLOPE PROTECTION | Near Desert Center, at Orris Ditch Bridge No 56-0123L/R and at Aztec Ditch Bridge No 56-0545L/R. | Scour mitigation and bridge rail upgrade. | 1203 | Yes | 1203 | 973 | 973 | 973 | No | 1446 | No | 1446 | 0 | 0 | 1411 | No | 17 | No | 17 | 0 | 0 | 47 | Yes | 1717 | No | 1717 | 0 | 0 | 1572 | No | 10 | No | 10 | 3 | 3 | 232 | Yes | 3954 | No | 3954 | 0 | 0 | 3683 | No | 8347 | 8347 | 976 | 976 | 7918 |  | 2022-06-01 | 2022-06-22 |  |  | 2023-03-13 |  | 2023-03-13 | No | 2023-04-10 |  | 2023-04-10 | No | 2023-11-13 |  | 2023-12-13 | No |  |  | 2024-12-02 |  | 0 | No | Yes | No | No
564 | 08 | 3012K | SBD | 40 | PAVEMENT REHABILITATION (CAPM) | In and near Barstow, from Route 15 to 3.4 miles west of National Trails Highway; also on Main Street spur (PM S0.0/S0.8). | Pavement rehabilitation, upgrade signs and lighting, upgrade curb ramps to Americans with Disabilities Act (ADA) standards, and upgrade safety devices. (G13 Contingency). | 1445 | Yes | 1445 | 1397 | 1397 | 1397 | No | 0 | Yes | 0 | 0 | 0 | 2449 | Yes | 0 | Yes | 0 | 0 | 0 | 862 | Yes | 0 | No | 0 | 0 | 0 | 3998 | Yes | 235 | No | 235 | 9 | 9 | 364 | Yes | 0 | No | 0 | 0 | 0 | 36442 | Yes | 1680 | 1680 | 1406 | 1406 | 45512 |  | 2022-05-02 | 2022-05-05 |  |  | 2024-02-13 |  | 2024-03-01 | No | 2024-03-15 |  | 2024-04-01 | No | 2024-10-01 |  | 2025-01-03 | Yes |  |  | 2026-03-19 |  | 0 | No | Yes | No | No
565 | 08 | 3012M | SBD | Var | SBD VAR Install Changeable Message Signs (CMS) | Near Barstow, Needles, Yucca Valley, and Vidal Junction, on Routes 40, 58, 62, and 95 at various locations; also in Riverside County, on Route 62 near Desert Center at Route 177 (PM 82.5/87.5). | Install Changeable Message Signs (CMS), guardrail shielding, and Maintenance Vehicle Pullouts (MVPs). | 1028 | Yes | 1028 | 1026 | 1026 | 1026 | No | 1746 | Yes | 1746 | 584 | 584 | 1982 | Yes | 127 | Yes | 127 | 22 | 22 | 131 | Yes | 2300 | No | 2300 | 0 | 0 | 2151 | No | 20 | No | 20 | 0 | 0 | 10 | No | 12793 | No | 12793 | 0 | 0 | 11606 | No | 18014 | 18014 | 1632 | 1632 | 16906 |  | 2021-12-30 | 2021-12-30 |  |  | 2023-01-05 |  | 2023-01-05 | No | 2023-02-06 |  | 2023-02-06 | No | 2023-10-03 |  | 2023-10-03 | No |  |  | 2025-12-01 |  | 0 | No | No | No | No
566 | 08 | 3012N | SBD | Var | SBD INSTALL CMS VAR ROUTES | In San Bernardino County, on various routes at various locations. | Install Changeable Message Signs (CMS). | 1345 | Yes | 1345 | 1345 | 1345 | 1345 | No | 1461 | Yes | 1461 | 680 | 680 | 1753 | Yes | 118 | Yes | 118 | 10 | 10 | 326 | Yes | 2620 | No | 2620 | 0 | 0 | 2211 | No | 117 | No | 117 | 0 | 0 | 117 | No | 14374 | No | 14374 | 0 | 0 | 12555 | No | 20035 | 20035 | 2035 | 2035 | 18307 |  | 2021-11-22 | 2021-11-18 |  |  | 2023-01-03 |  | 2023-03-03 | No | 2023-02-01 |  | 2023-04-03 | No | 2023-10-05 |  | 2024-01-02 | No |  |  | 2025-06-02 |  | 0 | No | No | No | No
567 | 08 | 3012P | SBD | Var | SBD REPLACE CMS VAR ROUTES | In San Bernardino County, on routes 10, 15, 40, 58, 60, 210, and 215 at various locations. | Upgrade Changeable Message Signs (CMS). | 1061 | Yes | 1061 | 927 | 927 | 927 | No | 1727 | Yes | 1727 | 923 | 923 | 1963 | Yes | 223 | Yes | 223 | 24 | 24 | 325 | Yes | 3212 | No | 3212 | 0 | 0 | 3197 | No | 20 | No | 20 | 0 | 0 | 20 | No | 15640 | No | 15640 | 0 | 0 | 16519 | Yes | 21883 | 21883 | 1874 | 1874 | 22951 |  | 2021-05-27 | 2021-05-27 |  |  | 2022-08-01 |  | 2022-09-01 | No | 2022-09-01 |  | 2022-10-03 | No | 2023-07-03 |  | 2023-09-01 | No |  |  | 2025-04-02 |  | 0 | No | No | No | No
568 | 08 | 3012Q | RIV | Var | RIV VAR ROUTES AVMS | In Riverside County, on Routes 10, 15, 60, 62, 91, 111, and 215 at various locations; also in San Bernardino County, on Route 215 in Colton at Iowa Avenue (PM 0.2). | Upgrade Changeable Message Signs (CMS), guardrail shielding, and construct Maintenance Vehicle Pullouts (MVPs). | 863 | Yes | 863 | 745 | 745 | 745 | No | 1463 | Yes | 1463 | 515 | 515 | 1385 | No | 65 | Yes | 65 | 14 | 14 | 41 | No | 2300 | No | 2300 | 0 | 0 | 1399 | No | 42 | No | 42 | 0 | 0 | 42 | No | 6658 | No | 6658 | 0 | 0 | 6015 | No | 11391 | 11391 | 1274 | 1274 | 9627 |  | 2021-06-30 | 2021-06-30 |  |  | 2022-12-01 |  | 2023-02-01 | No | 2023-01-03 |  | 2023-03-01 | No | 2023-09-07 |  | 2023-12-01 | No |  |  | 2025-11-03 |  | 0 | No | No | No | No
569 | 08 | 3014F | SBD | Var | SBD COUNTY CENSUS STATIONS UPGRADE | In San Bernardino County, at various locations. | Upgrade traffic census stations. | 514 | Yes | 514 | 4 | 4 | 590 | Yes | 1043 | No | 1043 | 0 | 0 | 1061 | Yes | 45 | No | 45 | 0 | 0 | 41 | No | 1113 | No | 1113 | 0 | 0 | 1024 | No | 23 | No | 23 | 0 | 0 | 23 | No | 3542 | No | 3542 | 0 | 0 | 3542 | No | 6280 | 6280 | 4 | 4 | 6281 |  |  |  | 2024-01-04 |  |  |  | 2025-07-07 |  |  |  | 2025-08-04 |  |  |  | 2026-04-06 |  |  |  | 2028-04-06 |  | 0 | No | No | No | No
570 | 08 | 3014G | SBD | 38 | SBD 38 PAVEMENT REHAB | In near Redlands, from Occidental Drive to Crafton Avenue. | Rehabilitate pavement, upgrade Transportation Management System (TMS) elements, and upgrade facilities to Americans with Disabilities Act (ADA) standards. | 1802 | Yes | 1802 | 0 | 0 | 1974 | Yes | 1580 | No | 1580 | 0 | 0 | 1653 | Yes | 2238 | No | 2238 | 0 | 0 | 2209 | No | 2045 | No | 2045 | 0 | 0 | 1903 | No | 784 | No | 784 | 0 | 0 | 784 | No | 11697 | No | 11697 | 0 | 0 | 11697 | No | 20146 | 20146 | 0 | 0 | 20220 |  |  |  | 2024-02-01 |  |  |  | 2025-11-03 |  |  |  | 2025-12-04 |  |  |  | 2026-07-06 |  |  |  | 2027-08-02 |  | 0 | No | No | No | No
571 | 08 | 3014N | SBD | 38 | SBD 38 PAVEMENT REHAB | In Redlands, from Route 10 to Occidental Drive; also on spurs from Orange Street to Pearl Avenue (PM S0.372/S0.597) and from Eureka Street to Route 10 (PM S0.598/S0.855). | Rehabilitate pavement, upgrade Transportation Management System (TMS) elements, and upgrade facilities to Americans with Disabilities Act (ADA) standards. | 1669 | Yes | 1669 | 0 | 0 | 1750 | Yes | 1712 | No | 1712 | 0 | 0 | 1720 | Yes | 1964 | No | 1964 | 0 | 0 | 1864 | No | 2017 | No | 2017 | 0 | 0 | 1822 | No | 840 | No | 840 | 0 | 0 | 840 | No | 7740 | No | 7740 | 0 | 0 | 7740 | No | 15942 | 15942 | 0 | 0 | 15736 |  |  |  | 2023-09-01 |  |  |  | 2025-01-03 |  |  |  | 2025-02-03 |  |  |  | 2025-09-02 |  |  |  | 2026-11-02 |  | 0 | No | No | No | No
572 | 08 | 3015A | SBD | 247 | CAPM Pavement Repair | In and near Barstow, from Stoddard Wells Road to Route 15. | Rehabilitate pavement, replace sign panels, and upgrade facilities to Americans with Disabilities Act (ADA) standards. | 1480 | Yes | 1480 | 5 | 5 | 1518 | Yes | 1417 | No | 1417 | 0 | 0 | 1388 | No | 1415 | No | 1415 | 0 | 0 | 1356 | No | 1524 | No | 1524 | 0 | 0 | 1440 | No | 652 | No | 652 | 0 | 0 | 652 | No | 8394 | No | 8394 | 0 | 0 | 8394 | No | 14882 | 14882 | 5 | 5 | 14748 |  |  |  | 2024-01-04 |  |  |  | 2026-01-05 |  |  |  | 2026-02-04 |  |  |  | 2026-11-03 |  |  |  | 2027-11-04 |  | 0 | No | No | No | No
573 | 08 | 3015C | SBD | 83 | SBD 83 CHINO PAVEMENT REHAB | In and near Chino, from Route 71 to north of Chino Avenue. | Rehabilitate pavement, replace sign panels, upgrade lighting, construct bus pads, and upgrade facilities to Americans with Disabilities Act (ADA) standards. | 1530 | Yes | 1530 | 0 | 0 | 1673 | Yes | 1792 | No | 1792 | 0 | 0 | 1852 | Yes | 489 | No | 489 | 0 | 0 | 467 | No | 2835 | No | 2835 | 0 | 0 | 2711 | No | 128 | No | 128 | 0 | 0 | 128 | No | 15885 | No | 15885 | 0 | 0 | 15885 | No | 22659 | 22659 | 0 | 0 | 22716 |  |  |  | 2024-05-01 |  |  |  | 2025-11-03 |  |  |  | 2025-12-01 |  |  |  | 2026-08-14 |  |  |  | 2027-09-01 |  | 0 | No | No | No | No
574 | 08 | 3015H | SBD | 18 | SBD 18 LUCERNE VALLEY PAVEMENT REHAB | Near Lucerne Valley, from Camp Rock Road to Custer Avenue. | Rehabilitate pavement, upgrade guardrail and Transportation Management System (TMS) elements, and construct shoulders and rumble strips. | 3429 | Yes | 3429 | 0 | 0 | 3552 | Yes | 2472 | No | 2472 | 0 | 0 | 2403 | No | 3987 | No | 3987 | 0 | 0 | 3717 | No | 2265 | No | 2265 | 0 | 0 | 2048 | No | 5617 | No | 5617 | 0 | 0 | 5617 | No | 22942 | No | 22942 | 0 | 0 | 22942 | No | 40712 | 40712 | 0 | 0 | 40279 |  |  |  | 2024-04-04 |  |  |  | 2026-04-03 |  |  |  | 2026-04-15 |  |  |  | 2026-12-02 |  |  |  | 2027-09-03 |  | 0 | No | No | No | No
575 | 08 | 3015J | SBD | 15 | SBD 15 PAVEMENT REHAB | Near Baker, from south of Basin Road to 7.4 miles north of Route 127. | Rehabilitate pavement, drainage systems, and lighting, upgrade guardrail, and replace sign panels. | 2211 | Yes | 2211 | 0 | 0 | 2208 | No | 2543 | No | 2543 | 0 | 0 | 2391 | No | 25 | No | 25 | 0 | 0 | 24 | No | 5200 | No | 5200 | 0 | 0 | 4881 | No | 79 | No | 79 | 0 | 0 | 79 | No | 35508 | No | 35508 | 0 | 0 | 35508 | No | 45566 | 45566 | 0 | 0 | 45091 |  |  |  | 2024-05-01 |  |  |  | 2025-11-03 |  |  |  | 2025-12-01 |  |  |  | 2026-08-06 |  |  |  | 2027-12-06 |  | 0 | No | No | No | No
576 | 08 | 3015L | RIV | 215 | RIV 215 PAVEMENT REHAB | In and near the city of Riverside, from north of Ramona Expressway to south of Martin Luther King BoulevaRd Rehabilitate pavement, upgrade guardrail and Transportation Management System (TMS) elements, replace roadside sign panels, and upgrade facilities to Americans with Disabilities Act (ADA) standards. | CAPM PAVEMENT REPAIR & ROADSIDE SAFETY IMPROVEMENTS | 1851 | Yes | 1851 | 0 | 0 | 1851 | No | 2346 | No | 2346 | 0 | 0 | 2346 | No | 175 | No | 175 | 0 | 0 | 160 | No | 4829 | No | 4829 | 0 | 0 | 4528 | No | 46 | No | 46 | 0 | 0 | 46 | No | 48273 | No | 48273 | 0 | 0 | 48273 | No | 57520 | 57520 | 0 | 0 | 57204 |  |  |  | 2023-09-01 |  |  |  | 2025-01-03 |  |  |  | 2025-02-03 |  |  |  | 2025-11-03 |  |  |  | 2027-09-01 |  | 0 | No | No | No | No
577 | 08 | 3015M | RIV | 91 | RIV 91 RIVERSIDE PAVEMENT REHAB | In the city of Riverside, from east of Tyler Street to east of Madison Street. | Rehabilitate pavement, upgrade guardrail, sign panels, and Transportation Management System (TMS) elements, enhance highway worker safety, and implement stormwater Best Management Practices (BMPs) to capture and remove trash. | 1569 | Yes | 1569 | 0 | 0 | 1376 | No | 2258 | No | 2258 | 0 | 0 | 1992 | No | 219 | No | 219 | 0 | 0 | 125 | No | 3762 | No | 3762 | 0 | 0 | 3094 | No | 23 | No | 23 | 0 | 0 | 23 | No | 19917 | No | 19917 | 0 | 0 | 19917 | No | 27748 | 27748 | 0 | 0 | 26527 |  |  |  | 2023-09-05 |  |  |  | 2024-12-02 |  |  |  | 2025-01-02 |  |  |  | 2025-09-16 |  |  |  | 2027-06-01 |  | 0 | No | No | No | No
578 | 08 | 3015T | SBD | 95 | SBD 95 PAVEMENT REHAB | Near Needles, from Route 40 to 0.5 mile north of Goffs Road. | Rehabilitate pavement and replace Asphalt Concrete (AC) dike and rumble strips. | 1575 | Yes | 1575 | 11 | 11 | 1524 | No | 941 | No | 941 | 0 | 0 | 915 | No | 61 | No | 61 | 0 | 0 | 57 | No | 1623 | No | 1623 | 0 | 0 | 1541 | No | 350 | No | 350 | 0 | 0 | 350 | No | 7158 | No | 7158 | 0 | 0 | 6182 | No | 11708 | 11708 | 11 | 11 | 10569 |  |  |  | 2024-05-01 |  |  |  | 2025-03-03 |  |  |  | 2025-04-01 |  |  |  | 2025-12-01 |  |  |  | 2026-08-03 |  | 0 | No | No | No | Yes
579 | 08 | 3016F | SBD | 18 | SR-18 CAPM, CULVERT REPAIR, GUARDRAIL UPGRADE | Near Big Bear Lake, from 1.4 miles south of Baldwin Lake Road to Camp Rock Road. | Rehabilitate pavement and drainage systems, upgrade guardrail, and replace sign panels. | 1694 | Yes | 1694 | 0 | 0 | 1706 | Yes | 1642 | No | 1642 | 0 | 0 | 1562 | No | 944 | No | 944 | 0 | 0 | 822 | No | 2872 | No | 2872 | 0 | 0 | 2410 | No | 150 | No | 150 | 0 | 0 | 150 | No | 13703 | No | 13703 | 0 | 0 | 13703 | No | 21005 | 21005 | 0 | 0 | 20353 |  |  |  | 2024-04-02 |  |  |  | 2025-10-02 |  |  |  | 2026-01-02 |  |  |  | 2026-09-16 |  |  |  | 2028-05-01 |  | 0 | No | No | No | No
580 | 08 | 3016L | SBD | 210 | SR-210U FRONTAGE RD LYTLE CREEK BRIDGE SEISMIC RETROFIT | In the city of San Bernardino, at Lytle Creek Bridge No 54-0422. | Seismic retrofit. | 1598 | Yes | 1598 | 0 | 0 | 1596 | No | 2308 | No | 2308 | 0 | 0 | 2239 | No | 214 | No | 214 | 0 | 0 | 195 | No | 2342 | No | 2342 | 0 | 0 | 2098 | No | 597 | No | 597 | 0 | 0 | 597 | No | 6920 | No | 6920 | 0 | 0 | 6920 | No | 13979 | 13979 | 0 | 0 | 13645 |  |  |  | 2024-04-02 |  |  |  | 2025-11-03 |  |  |  | 2026-02-02 |  |  |  | 2026-08-03 |  |  |  | 2027-10-15 |  | 0 | No | No | No | No
581 | 08 | 3016M | SBD | 15 | SBD-15 BRIDGE REPAIR | Near the city of San Bernardino, at Devore Overhead Right Bridge No 54-0818R, Devore Overhead Left Bridge No 54-0818L, and Cajon Creek Right Bridge No 54-0781R. | Place polyester concrete on bridge decks, treat approach and departure slabs with methacrylate, and replace bridge joint seals. | 720 | Yes | 720 | 3 | 3 | 751 | Yes | 1279 | No | 1279 | 0 | 0 | 1226 | No | 49 | No | 49 | 0 | 0 | 46 | No | 1003 | No | 1003 | 0 | 0 | 929 | No | 45 | No | 45 | 0 | 0 | 45 | No | 3551 | No | 3551 | 0 | 0 | 3551 | No | 6647 | 6647 | 3 | 3 | 6548 |  |  |  | 2024-01-05 |  |  |  | 2025-01-03 |  |  |  | 2025-02-03 |  |  |  | 2025-11-03 |  |  |  | 2026-07-03 |  | 0 | No | No | No | No
582 | 08 | 3016N | SBD | 15 | SBD-15 - REPLACE RSP FOR 6 BRIDGES | Near Zzyzx and Mountain Pass, from Telephone Wash Bridge to Ivanpah Ditch Bridge at various locations. | Restore rock slope protection at six bridges to mitigate scour. | 1824 | Yes | 1824 | 10 | 10 | 1764 | No | 1724 | No | 1724 | 0 | 0 | 1666 | No | 168 | No | 168 | 0 | 0 | 150 | No | 2767 | No | 2767 | 0 | 0 | 2529 | No | 501 | No | 501 | 0 | 0 | 501 | No | 8612 | No | 8612 | 0 | 0 | 7093 | No | 15596 | 15596 | 10 | 10 | 13703 |  |  |  | 2024-08-01 |  |  |  | 2025-12-01 |  |  |  | 2026-01-08 |  |  |  | 2026-10-01 |  |  |  | 2028-04-03 |  | 0 | No | No | No | Yes
583 | 08 | 3017G | SBD | 18 | MOJAVE RIVER BRIDGE DECK OVERLAY | In Victorville, at Mojave River Bridge and Overhead No 54-0307. | Rehabilitate bridge. (Long Lead Project). | 1529 | Yes | 1529 | 0 | 0 | 1518 | No | 0 | No | 0 | 0 | 0 | 1677 | Yes | 0 | No | 0 | 0 | 0 | 192 | Yes | 0 | No | 0 | 0 | 0 | 1605 | Yes | 0 | No | 0 | 0 | 0 | 102 | Yes | 0 | No | 0 | 0 | 0 | 5364 | Yes | 1529 | 1529 | 0 | 0 | 10458 |  |  |  | 2025-11-03 |  |  |  | 2027-09-02 |  |  |  | 2027-10-04 |  |  |  | 2028-07-05 |  |  |  | 2029-08-01 |  | 0 | Yes | Yes | Yes | Yes
584 | 08 | 3017J | RIV | 15 | Culvert Repair | Near Temescal Valley, from south of Indian Truck Trail to south of Temescal Canyon Road. | Rehabilitate drainage systems. | 1203 | Yes | 1203 | 0 | 0 | 1179 | No | 1265 | No | 1265 | 0 | 0 | 1223 | No | 384 | No | 384 | 0 | 0 | 349 | No | 998 | No | 998 | 0 | 0 | 865 | No | 374 | No | 374 | 0 | 0 | 374 | No | 3044 | No | 3044 | 0 | 0 | 3044 | No | 7268 | 7268 | 0 | 0 | 7034 |  |  |  | 2024-05-01 |  |  |  | 2025-11-03 |  |  |  | 2025-12-01 |  |  |  | 2026-06-01 |  |  |  | 2028-07-03 |  | 0 | No | No | No | No
585 | 08 | 3017K | SBD | 40 | SBd Rte 40 RSP Replacement | Near Needles, from Woods Wash Bridge to Homer Wash Bridge at various locations. | Restore rock slope protection at eight bridges to mitigate scour. | 1930 | Yes | 1930 | 0 | 0 | 1967 | Yes | 1947 | No | 1947 | 0 | 0 | 1890 | No | 84 | No | 84 | 0 | 0 | 81 | No | 1838 | No | 1838 | 0 | 0 | 1667 | No | 565 | No | 565 | 0 | 0 | 565 | No | 6784 | No | 6784 | 0 | 0 | 6784 | No | 13148 | 13148 | 0 | 0 | 12954 |  |  |  | 2024-05-01 |  |  |  | 2025-12-01 |  |  |  | 2026-01-15 |  |  |  | 2026-06-19 |  |  |  | 2027-04-20 |  | 0 | No | No | No | No
586 | 08 | 3019G | RIV | 10 | RIV 10, 15, 74 PC OVERLAY | In Riverside County, on Routes 10, 15, and 74 at various locations. | Apply polyester concrete overlay to bridge decks and replace joint seals. (Bridge Deck Preservation). | 528 | Yes | 528 | 271 | 271 | 671 | Yes | 460 | No | 460 | 0 | 0 | 428 | No | 10 | No | 10 | 0 | 0 | 10 | No | 1090 | No | 1090 | 0 | 0 | 998 | No | 20 | No | 20 | 0 | 0 | 20 | No | 4110 | No | 4110 | 0 | 0 | 4110 | No | 6218 | 6218 | 271 | 271 | 6237 |  |  |  | 2022-09-01 |  |  |  | 2022-12-01 |  |  |  | 2023-02-01 |  |  |  | 2023-06-14 |  |  |  | 2024-03-04 |  | 0 | No | No | No | No
587 | 08 | 3019H | SBD | 15 | SBD-15, 40 POLYESTER CONCRETE OVERLAY | In Hesperia, at Joshua Street Overcrossing No 54-0666; also on Route 40 near Barstow at Nebo Street Undercrossing No 54-0662L; also on Route 40 near Needles at Fenner Overhead No 54-1270L. | Apply polyester concrete overlay to bridge decks and replace bridge rails. (Bridge Deck Preservation). | 570 | Yes | 570 | 314 | 314 | 600 | Yes | 370 | No | 370 | 0 | 0 | 365 | No | 10 | No | 10 | 0 | 0 | 10 | No | 1000 | No | 1000 | 0 | 0 | 762 | No | 10 | No | 10 | 0 | 0 | 127 | Yes | 4638 | No | 4638 | 0 | 0 | 4026 | No | 6598 | 6598 | 314 | 314 | 5890 |  |  |  | 2022-09-01 |  |  |  | 2022-12-01 |  |  |  | 2023-04-03 |  |  |  | 2023-08-11 |  |  |  | 2024-05-01 |  | 0 | No | No | No | No
588 | 09 | 2633 | KER | 14 | Rosamond-Mojave Rehab | Near Rosamond and Mojave, from 1.4 miles south of Dawn Road Overcrossing (OC) to 0.5 mile north of Silver Queen Road OC. | Rehabilitate lanes with Continuous Reinforced Concrete Pavement (CRCP), cold plane and overlay ramps with Rubberized Hot Mix Asphalt (RHMA-G). Replace guardrail, construct rumble strip, replace signs using retroreflective sheeting, and refresh pavement delineation. | 370 | Yes | 370 | 174 | 174 | 174 | No | 1806 | Yes | 1806 | 1610 | 1610 | 1610 | No | 250 | Yes | 250 | 7 | 7 | 93 | No | 4750 | Yes | 4750 | 2689 | 2689 | 2985 | No | 49 | No | 49 | 3 | 3 | 0 | No | 46192 | Yes | 46192 | 41612 | 41612 | 46192 | No | 53417 | 53417 | 46095 | 46095 | 51054 | 2018-12-06 | 2018-06-20 | 2018-06-20 |  |  | 2020-01-03 | 2020-01-07 |  |  | 2020-01-23 | 2020-01-27 |  |  | 2020-06-24 | 2020-08-07 |  |  |  |  | 2022-12-15 |  | 46191 | No | No | No | Yes
589 | 09 | 2653 | INY | 395 | BISHOP PAVEMENT | In and near Bishop, on Main Street from Jay Street to Barlow Lane, and on Route 168 (Line Street) from Pioneer Lane to Route 395 (Main Street) (PM 17.6/18.3). | Rehabilitate roadway and drainage, install Transportation Management System (TMS) elements, upgrade facilities to Americans with Disabilities Act (ADA) standards, and construct multi-use path as complete streets elements. | 1288 | Yes | 1288 | 565 | 565 | 565 | No | 1304 | Yes | 1304 | 28 | 28 | 1134 | No | 1614 | Yes | 1614 | 7 | 7 | 1598 | No | 1351 | No | 1351 | 0 | 0 | 1226 | No | 4142 | No | 4142 | 3 | 3 | 3475 | No | 15510 | No | 15510 | 0 | 0 | 15510 | No | 25209 | 25209 | 603 | 603 | 23508 |  | 2021-08-16 | 2021-08-16 |  |  | 2023-06-28 |  | 2023-06-28 | No | 2023-06-28 |  | 2023-06-28 | No | 2024-03-06 |  | 2024-03-06 | No |  |  | 2024-12-01 |  | 0 | No | No | No | Yes
590 | 09 | 2667 | INY | 395 | FISH SPRINGS PAVEMENT | Near Big Pine, from 1.3 miles south of Fish Springs Road (south) to Route 168 (east). | Rehabilitate pavement, install Transportation Management System (TMS) elements, and upgrade lighting, guardrail, and facilities to Americans with Disabilities Act (ADA) standards. (G13 Contingency). | 1378 | Yes | 1378 | 679 | 679 | 679 | No | 892 | No | 892 | 0 | 0 | 802 | No | 1224 | No | 1224 | 0 | 0 | 1080 | No | 0 | No | 0 | 0 | 0 | 2369 | Yes | 96 | No | 96 | 0 | 0 | 96 | No | 0 | No | 0 | 0 | 0 | 28596 | Yes | 3590 | 3590 | 679 | 679 | 33622 |  | 2021-12-02 | 2022-06-29 |  |  | 2023-12-05 |  | 2024-05-15 | Yes | 2024-01-16 |  | 2024-06-14 | Yes | 2024-06-26 |  | 2025-01-12 | Yes |  |  | 2025-11-12 |  | 0 | Yes | Yes | No | Yes
591 | 09 | 2669 | MNO | 395 | ROCK CREEK PAVEMENT | Near Toms Place, from 0.5 mile north of Rock Creek road to 1.3 miles south of South Landing Road. | Rehabilitate pavement, replace signs, rehabilitate drainage systems, and upgrade guardrail and lighting. | 652 | Yes | 652 | 421 | 421 | 421 | No | 705 | Yes | 705 | 6 | 6 | 657 | No | 77 | Yes | 77 | 4 | 4 | 72 | No | 1717 | No | 1717 | 0 | 0 | 1507 | No | 34 | No | 34 | 4 | 4 | 34 | No | 10358 | No | 10358 | 0 | 0 | 9041 | No | 13543 | 13543 | 435 | 435 | 11732 |  | 2022-01-14 | 2022-01-21 |  |  | 2023-05-18 |  | 2023-05-18 | No | 2023-10-27 |  | 2023-10-27 | No | 2024-04-12 |  | 2024-04-12 | No |  |  | 2025-01-15 |  | 0 | No | No | No | No
592 | 09 | 2670 | INY | 127 | 127 PAVEMENT | Near Shoshone, from 4.6 miles north of Route 178 (west) to 7.6 miles south of Route 190; also from 0.3 mile south of Route 190 to Nevada State line (PM 41.8/49.42). | Rehabilitate pavement and replace signs. | 164 | Yes | 164 | 44 | 44 | 44 | No | 272 | Yes | 272 | 158 | 158 | 265 | No | 2 | Yes | 2 | 0 | 0 | 2 | No | 1724 | No | 1724 | 0 | 0 | 1508 | No | 0 | No | 0 | 0 | 0 | 0 | No | 18367 | No | 18367 | 0 | 0 | 16710 | No | 20529 | 20529 | 202 | 202 | 18529 |  | 2021-01-06 | 2021-01-06 |  |  | 2022-07-01 | 2022-06-14 |  |  | 2022-08-01 |  | 2022-08-01 | No | 2023-02-08 |  | 2023-02-08 | No |  |  | 2023-11-15 |  | 0 | No | No | No | Yes
593 | 09 | 2671 | INY | 395 | MANZANAR PAVEMENT | Near Independence, from 3.0 miles south of Manzanar Reward Road to 0.3 mile north of Shabbell Lane. | Rehabilitate roadway, install Transportation Management System (TMS) elements, and upgrade facilities to Americans with Disabilities Act (ADA) standards. (G13 Contingency). | 1447 | Yes | 1447 | 564 | 564 | 564 | No | 1273 | Yes | 1273 | 28 | 28 | 1346 | Yes | 1203 | Yes | 1203 | 4 | 4 | 1056 | No | 0 | No | 0 | 0 | 0 | 2080 | Yes | 137 | No | 137 | 0 | 0 | 118 | No | 0 | No | 0 | 0 | 0 | 47202 | Yes | 4060 | 4060 | 596 | 596 | 52366 |  | 2021-12-29 | 2021-12-29 |  |  | 2023-11-01 |  | 2023-11-01 | No | 2023-12-01 |  | 2023-12-01 | No | 2024-05-08 |  | 2024-05-08 | No |  |  | 2024-11-22 |  | 0 | No | Yes | No | Yes
594 | 09 | 2672 | KER | 14 | FREEMAN 3 CAPM | Near Armistead, from 1.1 mile north of Red Rock Canyon Road to 4.9 mile south of Route 178 (west). | Rehabilitate pavement and upgrade signs. | 232 | Yes | 232 | 104 | 104 | 104 | No | 528 | Yes | 528 | 160 | 160 | 522 | No | 2 | Yes | 2 | 0 | 0 | 2 | No | 385 | No | 385 | 0 | 0 | 367 | No | 0 | No | 0 | 0 | 0 | 0 | No | 7560 | No | 7560 | 0 | 0 | 7560 | No | 8707 | 8707 | 264 | 264 | 8555 |  | 2021-08-27 | 2021-08-27 |  |  | 2022-07-08 | 2022-04-14 |  |  | 2022-08-08 |  | 2022-08-08 | No | 2023-01-11 |  | 2023-01-11 | No |  |  | 2023-04-11 |  | 0 | No | No | No | Yes
595 | 09 | 2673 | MNO | 395 | CEMETERY PAVEMENT | Near Mono City, from south of Cemetery Road to Route 167 (east). | Rehabilitate pavement, remove and replace dikes and signs, and upgrade guardrail. | 420 | Yes | 420 | 156 | 156 | 156 | No | 581 | Yes | 581 | 202 | 202 | 577 | No | 22 | Yes | 22 | 11 | 11 | 19 | No | 835 | No | 835 | 0 | 0 | 743 | No | 0 | No | 0 | 0 | 0 | 0 | No | 8337 | No | 8337 | 0 | 0 | 7350 | No | 10195 | 10195 | 369 | 369 | 8845 |  | 2021-06-29 | 2021-06-29 |  |  | 2022-02-01 | 2022-03-03 |  |  | 2022-08-12 |  | 2022-08-12 | No | 2023-01-27 |  | 2023-01-27 | No |  |  | 2024-01-02 |  | 0 | No | No | No | Yes
596 | 10 | 0157 | TUO | 108 | Long Barn CAPM | Near Long Barn, from 0.1 mile west of East Long Barn Road Connection to 2.3 miles east of Cow Creek Road. | Pavement rehabilitation. | 797 | Yes | 797 | 605 | 605 | 605 | No | 1152 | Yes | 1152 | 746 | 746 | 746 | No | 8 | Yes | 8 | 2 | 2 | 2 | No | 2092 | Yes | 2092 | 370 | 370 | 2228 | Yes | 8 | No | 8 | 0 | 0 | 0 | No | 14808 | Yes | 14808 | 2789 | 2789 | 14808 | No | 18865 | 18865 | 4512 | 4512 | 18389 |  | 2019-10-01 | 2019-11-13 |  |  | 2020-12-01 | 2020-10-05 |  |  | 2021-01-02 | 2021-02-24 |  |  | 2021-07-15 | 2021-08-17 |  |  |  |  | 2023-04-15 |  | 14808 | No | No | No | No
597 | 10 | 0167 | AMA | 88 | AMADOR SR 88 ROADWAY IMPROVEMENTS | Near Martell, from Route 124 to Route 49. | Rehabilitate pavement, modify traffic signals, upgrade guardrail, and rehabilitate drainage systems. | 980 | Yes | 980 | 787 | 787 | 787 | No | 0 | Yes | 0 | 0 | 0 | 1728 | Yes | 0 | Yes | 0 | 0 | 0 | 205 | Yes | 1674 | No | 1674 | 0 | 0 | 1576 | No | 126 | No | 126 | 3 | 3 | 63 | No | 11516 | No | 11516 | 0 | 0 | 13051 | Yes | 14296 | 14296 | 790 | 790 | 17410 |  | 2022-03-10 | 2022-03-17 |  |  | 2024-05-10 |  | 2024-05-10 | No | 2024-05-31 |  | 2024-05-31 | No | 2024-12-24 |  | 2024-12-24 | No |  |  | 2025-12-24 |  | 0 | Yes | Yes | Yes | Yes
598 | 10 | 1044 | ALP | 4 | SR4 Pavement Anchor Project | Near Bear Valley, from Calaveras County line to Route 89; also on Route 89 at 0.9 mile north of Route 4 (PM 10.84). | Rehabilitate pavement, replace guardrail and signs, place Rock Slope Protection (RSP), rehabilitate drainage systems, and enhance highway worker safety. (G13 Contingency). | 2213 | Yes | 2213 | 1516 | 1516 | 2200 | No | 2196 | No | 2196 | 0 | 0 | 2329 | Yes | 1076 | No | 1076 | 0 | 0 | 985 | No | 0 | No | 0 | 0 | 0 | 4463 | Yes | 575 | No | 575 | 5 | 5 | 510 | No | 0 | No | 0 | 0 | 0 | 31954 | Yes | 6060 | 6060 | 1521 | 1521 | 42441 |  | 2022-06-09 |  | 2022-10-01 | Yes | 2024-05-23 |  | 2024-06-15 | No | 2024-06-20 |  | 2024-06-25 | No | 2025-02-10 |  | 2025-01-06 | No |  |  | 2027-09-11 |  | 0 | Yes | Yes | No | No
599 | 10 | 2680 | AMA | 88 | PEDDLER HILL PAVEMENT ANCHOR | Near Kirkwood, from west of Foster Meadow Road to 1.1 miles east of Shot Rock Vista Point. | Rehabilitate pavement, upgrade guardrail, replace signs, rehabilitate culverts, and construct rumble strips. (G13 Contingency). | 1653 | Yes | 1653 | 775 | 775 | 775 | No | 2035 | Yes | 2035 | 4 | 4 | 1935 | No | 70 | Yes | 70 | 0 | 0 | 64 | No | 0 | No | 0 | 0 | 0 | 2372 | Yes | 1165 | No | 1165 | 0 | 0 | 5 | No | 0 | No | 0 | 0 | 0 | 11013 | Yes | 4923 | 4923 | 779 | 779 | 16164 |  | 2022-08-12 | 2022-05-19 |  |  | 2023-10-19 |  | 2023-05-10 | No | 2023-11-17 |  | 2023-11-13 | No | 2024-05-17 |  | 2024-05-13 | No |  |  | 2025-02-24 |  | 0 | No | Yes | No | No
600 | 10 | 3089 | MER | 99 | SR99 MERCED REHAB | In and near the city of Merced, from 0.4 mile south of Childs Avenue to 0.3 mile south of Franklin Road. | Roadway rehabilitation. | 2510 | Yes | 2510 | 2171 | 2171 | 2171 | No | 3700 | Yes | 3700 | 2873 | 2873 | 2873 | No | 122 | Yes | 122 | 30 | 30 | 30 | No | 10400 | Yes | 10400 | 2500 | 2500 | 9902 | No | 95 | No | 95 | 17 | 17 | 17 | No | 55529 | Yes | 55529 | 12170 | 12170 | 51724 | No | 72356 | 72356 | 19761 | 19761 | 66717 | 2018-12-06 | 2018-06-27 | 2018-06-27 |  |  | 2020-05-01 | 2020-04-06 |  |  | 2020-05-15 | 2020-05-15 |  |  | 2020-12-14 | 2021-02-11 |  |  |  |  | 2023-08-23 |  | 51724 | Yes | Yes | Yes | Yes
601 | 10 | 3102 | MER | 5 | D10 BRIDGE SUBSTRUCTURE REPAIRS | In Merced, San Joaquin, Mariposa and Stanislaus Counties, on various routes at various locations. | Scour mitigation and preventative structural maintenance measures at thirteen bridges. | 1025 | Yes | 1025 | 952 | 952 | 952 | No | 950 | Yes | 950 | 897 | 897 | 897 | No | 542 | Yes | 542 | 151 | 151 | 171 | No | 1417 | Yes | 1417 | 440 | 440 | 1588 | Yes | 496 | No | 496 | 245 | 245 | 327 | No | 3852 | Yes | 3852 | 2017 | 2017 | 3852 | No | 8282 | 8282 | 4702 | 4702 | 7787 |  | 2018-08-22 | 2018-08-22 |  |  | 2020-12-01 | 2020-11-23 |  |  | 2020-12-18 | 2020-12-30 |  |  | 2021-07-23 | 2021-06-22 |  |  |  |  | 2022-11-01 |  | 3852 | Yes | Yes | Yes | Yes
602 | 10 | 3113 | SJ | 4 | SJ BRIDGE MAINTENANCE | Near Discovery Bay, at Old River Bridge No 29-0045. | Upgrade mechanical and electrical equipment on movable bridge. | 748 | Yes | 748 | 660 | 660 | 660 | No | 1614 | Yes | 1614 | 1517 | 1517 | 1517 | No | 65 | Yes | 65 | 38 | 38 | 49 | No | 1549 | Yes | 1549 | 323 | 323 | 1933 | Yes | 220 | No | 220 | 25 | 25 | 86 | No | 7066 | Yes | 7066 | 91 | 91 | 7066 | No | 11262 | 11262 | 2654 | 2654 | 11311 |  | 2018-08-15 | 2018-08-22 |  |  | 2020-04-03 | 2020-04-02 |  |  | 2020-05-04 | 2020-06-29 |  |  | 2020-10-21 | 2021-03-25 |  |  |  |  | 2023-04-14 |  | 7066 | Yes | Yes | Yes | Yes
603 | 10 | 3118 | SJ | 5 | SJ I-5 BRIDGE REHAB | In San Joaquin County, from 0.2 mile south of and 0.2 mile north of Route 5/33 Separation and Overhead No 29-0260 L/R; also in Stanislaus County in Modesto on Route 99 at West Modesto Overhead No 38-0083 (PM 17.9). | Seismic retrofit of three bridges. | 621 | Yes | 621 | 426 | 426 | 426 | No | 2186 | Yes | 2186 | 2086 | 2086 | 2086 | No | 223 | Yes | 223 | 140 | 140 | 193 | No | 1783 | Yes | 1783 | 268 | 268 | 1626 | No | 384 | No | 384 | 163 | 163 | 282 | No | 9354 | Yes | 9354 | 1820 | 1820 | 9354 | No | 14551 | 14551 | 4903 | 4903 | 13967 |  | 2017-10-10 | 2017-10-10 |  |  | 2019-11-01 | 2021-06-30 |  |  | 2019-11-15 | 2021-06-30 |  |  | 2020-05-06 | 2021-11-29 |  |  |  |  | 2023-10-31 |  | 9354 | Yes | Yes | Yes | No
604 | 10 | 3122 | MER | 152 | MERCED SEISMIC RESTORATION | In Merced County, on Routes 152, 140, and 59 at various locations. | Seismic retrofit and bridge rail upgrade of seven bridges. | 2530 | Yes | 2530 | 2487 | 2487 | 2487 | No | 3000 | Yes | 3000 | 2221 | 2221 | 3263 | Yes | 400 | Yes | 400 | 136 | 136 | 300 | No | 3000 | No | 3000 | 0 | 0 | 3440 | Yes | 1700 | No | 1700 | 88 | 88 | 2354 | Yes | 13500 | No | 13500 | 0 | 0 | 13903 | Yes | 24130 | 24130 | 4932 | 4932 | 25747 |  | 2020-04-16 | 2020-04-16 |  |  | 2022-08-01 |  | 2022-08-01 | No | 2022-10-01 |  | 2022-10-01 | No | 2023-04-05 |  | 2023-04-05 | No |  |  | 2025-04-04 |  | 0 | Yes | Yes | Yes | Yes
605 | 10 | 3134 | ALP | 88 | MOUNTAIN COUNTIES BRIDGE RAILS | Near Markleeville, on Routes 4, 88, and 89 at various locations. | Bridge rail upgrade on two bridges, replace one bridge, and barricade another bridge. | 1410 | Yes | 1410 | 1296 | 1296 | 1296 | No | 2111 | Yes | 2111 | 1808 | 1808 | 1808 | No | 115 | Yes | 115 | 68 | 68 | 76 | No | 2795 | Yes | 2795 | 550 | 550 | 3200 | Yes | 313 | No | 313 | 147 | 147 | 149 | No | 6341 | Yes | 6341 | 1152 | 1152 | 6341 | No | 13085 | 13085 | 5021 | 5021 | 12870 |  | 2018-07-02 | 2019-01-15 |  |  | 2020-02-10 | 2020-04-23 |  |  | 2020-04-17 | 2020-06-29 |  |  | 2020-09-08 | 2021-04-21 |  |  |  |  | 2023-07-20 |  | 6341 | No | No | No | No
606 | 10 | 3138 | ALP | 88 | ALP/AMA/TUO CULVERT REHAB | In Alpine County on Routes 4, 88 and 207; also in Amador County on Routes 16 and 49; also in Tuolumne County on Route 108; at various locations. | Rehabilitate culverts. | 1310 | Yes | 1310 | 955 | 955 | 955 | No | 1347 | Yes | 1347 | 1337 | 1337 | 1337 | No | 317 | Yes | 317 | 114 | 114 | 114 | No | 1350 | Yes | 1350 | 1077 | 1077 | 1449 | Yes | 551 | No | 551 | 131 | 131 | 321 | No | 4560 | Yes | 4560 | 3149 | 3149 | 4560 | No | 9435 | 9435 | 6763 | 6763 | 8736 |  | 2018-07-02 | 2018-08-30 |  |  | 2019-12-01 | 2020-04-07 |  |  | 2020-01-15 | 2020-06-11 |  |  | 2020-09-01 | 2021-01-26 |  |  |  |  | 2023-01-02 |  | 4560 | No | No | No | No
607 | 10 | 3141 | SJ | 88 | SJ/ALP 88 DRAINAGE SYSTEM | Near Lockeford, from 0.1 mile north of East Jack Tone Road to 0.1 mile south of north Tully Road intersection; also near Kirkwood, in Alpine County (PM 0.2/2.5). | Replace culverts. | 795 | Yes | 795 | 684 | 684 | 684 | No | 1190 | Yes | 1190 | 1102 | 1102 | 1102 | No | 290 | Yes | 290 | 244 | 244 | 848 | Yes | 1036 | Yes | 1036 | 154 | 154 | 850 | No | 1306 | No | 1306 | 180 | 180 | 486 | No | 4360 | Yes | 4360 | 1580 | 1580 | 4360 | No | 8977 | 8977 | 3944 | 3944 | 8330 |  | 2018-12-14 | 2018-12-14 |  |  | 2020-12-24 | 2021-04-08 |  |  | 2021-01-09 | 2021-04-19 |  |  | 2021-07-21 | 2021-08-10 |  |  |  |  | 2022-09-30 |  | 4360 | No | Yes | No | No
608 | 10 | 3142 | ALP | 4 | ALPINE CULVERT REHAB | In Alpine County on Routes 4, 88, and 89 at various locations. | Rehabilitate culverts. | 1370 | Yes | 1370 | 1150 | 1150 | 1150 | No | 1494 | Yes | 1494 | 1222 | 1222 | 1222 | No | 359 | Yes | 359 | 89 | 89 | 283 | No | 1359 | Yes | 1359 | 109 | 109 | 1237 | No | 384 | No | 384 | 133 | 133 | 384 | No | 3452 | Yes | 3452 | 0 | 0 | 3452 | No | 8418 | 8418 | 2703 | 2703 | 7728 |  | 2018-07-02 | 2018-08-30 |  |  | 2019-10-13 | 2020-03-24 |  |  | 2020-01-02 | 2020-06-12 |  |  | 2020-09-01 | 2021-07-20 |  |  |  |  | 2024-11-01 |  | 3452 | Yes | Yes | Yes | Yes
609 | 10 | 3146 | SJ | 205 | SR205 SMART CORRIDOR - PHASE 2 | In Tracy, from Byron Road Undercrossing to Paradise Road Overcrossing. | Install ramp meters and other Transportation Management System (TMS) elements. | 1650 | Yes | 1650 | 1558 | 1558 | 1558 | No | 3925 | Yes | 3925 | 3911 | 3911 | 3911 | No | 979 | Yes | 979 | 628 | 628 | 875 | No | 6562 | Yes | 6562 | 54 | 54 | 6554 | No | 2010 | No | 2010 | 1517 | 1517 | 2011 | Yes | 20440 | Yes | 20440 | 0 | 0 | 20440 | No | 35566 | 35566 | 7668 | 7668 | 35349 | 2018-12-06 | 2018-09-11 | 2018-09-11 |  |  | 2020-12-17 | 2021-06-29 |  |  | 2021-01-01 | 2021-06-30 |  |  | 2021-07-23 | 2022-05-03 |  |  |  |  | 2024-02-23 |  | 20440 | No | No | No | No
610 | 10 | 3165 | SJ | 4 | SJ SR 4 Pavement Resurfacing and Restoration | In Stockton, from 0.2 mile east of Fresno Avenue to Center Street; also on Route 5 from Taylor Street Overhead to Stockton Channel Viaduct (PM 25.8/26.5). | Roadway rehabilitation. | 792 | Yes | 792 | 787 | 787 | 787 | No | 2478 | Yes | 2478 | 1934 | 1934 | 1934 | No | 19 | No | 19 | 0 | 0 | 0 | No | 5082 | Yes | 5082 | 2573 | 2573 | 6287 | Yes | 48 | No | 48 | 0 | 0 | 0 | No | 32631 | Yes | 32631 | 13245 | 13245 | 32631 | No | 41050 | 41050 | 18539 | 18539 | 41639 | 2018-12-06 | 2018-05-09 | 2018-05-09 |  |  | 2019-10-10 | 2019-10-09 |  |  | 2019-11-10 | 2019-12-12 |  |  | 2020-07-11 | 2020-12-29 |  |  |  |  | 2023-04-14 |  | 32630 | No | Yes | No | Yes
611 | 10 | 3167 | MPA | 140 | MPA Route 140 Pavement Preservation | Near the Mariposa community and El Portal, from East Whitlock Road to Yosemite National Park entrance. | Pavement rehabilitation. (G13 Contingency). | 1189 | Yes | 1189 | 1014 | 1014 | 1014 | No | 2261 | Yes | 2261 | 1114 | 1114 | 1863 | No | 35 | Yes | 35 | 9 | 9 | 33 | No | 0 | No | 0 | 0 | 0 | 2783 | Yes | 162 | No | 162 | 3 | 3 | 18 | No | 0 | No | 0 | 0 | 0 | 25425 | Yes | 3647 | 3647 | 2140 | 2140 | 31136 |  | 2020-10-15 | 2021-01-04 |  |  | 2021-10-01 | 2022-06-24 |  |  | 2022-04-15 | 2022-06-27 |  |  | 2022-05-16 |  | 2022-12-14 | Yes |  |  | 2024-07-02 |  | 0 | Yes | Yes | No | No
612 | 10 | 3169 | SJ | 26 | SJ Route 26 Increase Bridge Vertical Clearance | Near Stockton, at Route 26/99 Separation No 29-0142 (PM 1.11). | Establish standard vertical clearance. | 698 | Yes | 698 | 648 | 648 | 648 | No | 1827 | Yes | 1827 | 1555 | 1555 | 1555 | No | 13 | No | 13 | 0 | 0 | 0 | No | 3382 | Yes | 3382 | 540 | 540 | 3511 | Yes | 7 | No | 7 | 0 | 0 | 0 | No | 7075 | Yes | 7075 | 1964 | 1964 | 7075 | No | 13002 | 13002 | 4707 | 4707 | 12789 |  | 2019-06-17 | 2019-06-17 |  |  | 2020-12-15 | 2020-09-02 |  |  | 2021-01-15 | 2021-04-15 |  |  | 2021-07-01 | 2021-11-30 |  |  |  |  | 2024-01-08 |  | 7075 | Yes | Yes | Yes | Yes
613 | 10 | 3219 | AMA | 49 | Mokelumne River Bridge Upgrade | Near Jackson, at Mokelumne River Bridge No 26-0012. | Upgrade bridge rails and widen shoulders. | 1590 | Yes | 1590 | 1020 | 1020 | 1020 | No | 2010 | Yes | 2010 | 1256 | 1256 | 1842 | No | 135 | No | 135 | 0 | 0 | 0 | No | 2055 | No | 2055 | 0 | 0 | 1904 | No | 58 | No | 58 | 13 | 13 | 17 | No | 4254 | No | 4254 | 0 | 0 | 5306 | Yes | 10102 | 10102 | 2289 | 2289 | 10089 |  | 2020-07-02 | 2020-07-21 |  |  | 2022-04-28 | 2022-01-27 | 2022-09-01 | Yes | 2022-05-02 |  | 2022-09-09 | Yes | 2022-12-27 |  | 2023-03-09 | No |  |  | 2024-11-29 |  | 0 | Yes | Yes | No | No
614 | 10 | 3226 | SJ | 120 | D 10 TMS REPAIR | In San Joaquin, Amador, Calaveras, Merced, Mariposa, Stanislaus, and Tuolumne Counties, on Routes 4, 5, 26, 33, 49, 59, 99, 104, 108, 120, 132, 140, 152 and 205 at various locations. | Repair or replace damaged and nonfunctioning Traffic Management System (TMS) elements. | 632 | Yes | 632 | 430 | 430 | 430 | No | 1191 | Yes | 1191 | 793 | 793 | 793 | No | 107 | No | 107 | 0 | 0 | 0 | No | 951 | Yes | 951 | 428 | 428 | 1158 | Yes | 33 | No | 33 | 0 | 0 | 0 | No | 2899 | Yes | 2899 | 1487 | 1487 | 2899 | No | 5813 | 5813 | 3138 | 3138 | 5280 |  | 2019-05-22 | 2019-05-22 |  |  | 2020-11-05 | 2020-11-02 |  |  | 2021-01-05 | 2021-01-19 |  |  | 2021-07-06 | 2021-06-22 |  |  |  |  | 2022-11-15 |  | 2899 | No | No | No | No
615 | 10 | 3227 | SJ | 99 | D 10 MVDS replacement and upgrade | In San Joaquin, Merced, and Stanislaus Counties, on Routes 5, 59, 99, and 152 at various locations. | Upgrade or replace inefficient and damaged Transportation Management System (TMS) elements. | 1202 | Yes | 1202 | 703 | 703 | 703 | No | 1719 | Yes | 1719 | 992 | 992 | 992 | No | 465 | Yes | 465 | 22 | 22 | 22 | No | 2370 | Yes | 2370 | 1159 | 1159 | 2343 | No | 9 | No | 9 | 0 | 0 | 0 | No | 9028 | Yes | 9028 | 6344 | 6344 | 9028 | No | 14793 | 14793 | 9220 | 9220 | 13088 |  | 2019-04-01 | 2019-04-09 |  |  | 2020-02-14 | 2020-01-17 |  |  | 2020-03-16 | 2020-04-17 |  |  | 2020-09-15 | 2020-11-20 |  |  |  |  | 2022-09-15 |  | 9028 | No | No | No | No
616 | 10 | 3229 | SJ | 99 | SJ DRAINAGE PUMP PLANT UPGRADE | In and near Stockton and Lodi, at various locations from Eastside Underpass to Acampo Road; also on Route 4 at the Route 4/5 Separation (PM R16.10) and on Route 120 in Lathrop at Mossdale Underpass (PM R0.5). | Upgrade drainage pump plants. | 589 | Yes | 589 | 553 | 553 | 553 | No | 1600 | Yes | 1600 | 1003 | 1003 | 1353 | No | 59 | Yes | 59 | 59 | 59 | 59 | No | 1520 | Yes | 1520 | 0 | 0 | 1646 | Yes | 330 | No | 330 | 18 | 18 | 16 | No | 0 | Yes | 0 | 0 | 0 | 4827 | Yes | 4098 | 4098 | 1633 | 1633 | 8454 |  | 2019-11-22 | 2020-01-28 |  |  | 2022-02-14 | 2022-04-20 |  |  | 2022-03-04 | 2022-04-22 |  |  | 2022-07-05 |  | 2022-10-14 | Yes |  |  | 2023-11-06 |  | 0 | Yes | Yes | Yes | No
617 | 10 | 3230 | SJ | 120 | SR 120 TMC UPGRADE | In and near Manteca and Lathrop, from Route 5 to Route 99; also on Route 5 at PM R13.34 and on Route 99 at PM 4.56. | Install fiber optic cable as part of the Transportation Management System (TMS). | 373 | Yes | 373 | 254 | 254 | 254 | No | 1321 | Yes | 1321 | 1273 | 1273 | 1273 | No | 107 | Yes | 107 | 41 | 41 | 41 | No | 1480 | Yes | 1480 | 188 | 188 | 1673 | Yes | 97 | No | 97 | 73 | 73 | 79 | No | 4893 | Yes | 4893 | 179 | 179 | 4893 | No | 8271 | 8271 | 2008 | 2008 | 8213 |  | 2018-09-21 | 2018-09-21 |  |  | 2020-12-03 | 2021-05-28 |  |  | 2021-01-29 | 2021-06-07 |  |  | 2021-09-13 | 2021-12-14 |  |  |  |  | 2023-10-31 |  | 4893 | Yes | Yes | Yes | No
618 | 10 | 3247 | CAL | 26 | Upgrade bridge rails of three bridges in CAL Co | Near West Point, at South Fork Mokelumne River Bridge No 30-0022 (PM 30.0), and at North Fork Mokelumne River Bridge No 30-0049 (PM 38.3). | Upgrade bridge railing at two structures, also seismic retrofit at one location. | 1033 | Yes | 1033 | 863 | 863 | 863 | No | 1909 | Yes | 1909 | 1241 | 1241 | 1749 | No | 69 | Yes | 69 | 167 | 167 | 208 | Yes | 1844 | No | 1844 | 0 | 0 | 2053 | Yes | 685 | No | 685 | 49 | 49 | 659 | No | 5094 | No | 5094 | 0 | 0 | 5094 | No | 10634 | 10634 | 2320 | 2320 | 10626 |  | 2020-08-03 | 2020-10-15 |  |  | 2021-08-02 | 2022-05-03 |  |  | 2021-09-03 |  | 2022-08-15 | Yes | 2022-03-22 |  | 2022-12-28 | Yes |  |  | 2023-11-25 |  | 0 | Yes | No | No | No
619 | 10 | 3250 | SJ | 5 | SJ Changeable Message Signs | In and near Stockton, on Route 5 at various locations; also on Route 4 (PM 14.6/26.0) and Route 99 (PM 15.8/18.5) at various locations. | Install Transportation Management System (TMS) elements. (G13 Contingency). | 820 | Yes | 820 | 808 | 808 | 808 | No | 3005 | Yes | 3005 | 2835 | 2835 | 3042 | Yes | 380 | Yes | 380 | 319 | 319 | 429 | Yes | 0 | No | 0 | 0 | 0 | 1810 | Yes | 335 | No | 335 | 136 | 136 | 179 | No | 0 | No | 0 | 0 | 0 | 8420 | Yes | 4540 | 4540 | 4098 | 4098 | 14688 |  | 2018-09-13 | 2018-09-13 |  |  | 2021-11-23 |  | 2022-07-13 | Yes | 2021-12-22 |  | 2022-07-14 | Yes | 2022-07-14 |  | 2022-12-16 | Yes |  |  | 2023-08-29 |  | 0 | Yes | Yes | No | No
620 | 10 | 3251 | STA | 99 | Replace Drainage Pumps | In and near Ceres and Modesto, at various locations from Mitchell Road to Kansas Avenue; also in Merced County, on Route 59 near the city of Merced, at Childs Avenue (PM 14.0). | Upgrade drainage pump plants. | 330 | Yes | 330 | 195 | 195 | 195 | No | 1150 | Yes | 1150 | 1045 | 1045 | 1045 | No | 93 | No | 93 | 0 | 0 | 0 | No | 1991 | Yes | 1991 | 341 | 341 | 1416 | No | 13 | No | 13 | 4 | 4 | 4 | No | 5878 | Yes | 5878 | 626 | 626 | 5878 | No | 9455 | 9455 | 2211 | 2211 | 8538 |  | 2019-06-28 | 2019-06-28 |  |  | 2020-08-10 | 2020-08-11 |  |  | 2020-09-09 | 2021-04-28 |  |  | 2021-03-26 | 2021-10-19 |  |  |  |  | 2022-11-22 |  | 5878 | No | No | No | No
621 | 10 | 3252 | MPA | 140 | SR140 MARIPOSA CAPM | In and near the Mariposa community, from 1.7 miles east of Catheys Valley Park to the north Route 49 Junction. | Rehabilitate pavement and upgrade Americans with Disabilities Act (ADA) ramps. (G13 Contingency). | 1125 | Yes | 1125 | 1010 | 1010 | 1010 | No | 1496 | Yes | 1496 | 1213 | 1213 | 1525 | Yes | 416 | Yes | 416 | 306 | 306 | 599 | Yes | 0 | No | 0 | 0 | 0 | 1891 | Yes | 318 | No | 318 | 36 | 36 | 147 | No | 0 | No | 0 | 0 | 0 | 17311 | Yes | 3355 | 3355 | 2565 | 2565 | 22483 |  | 2020-04-01 | 2020-06-24 |  |  | 2022-05-01 |  | 2022-09-30 | Yes | 2022-06-01 |  | 2022-10-03 | Yes | 2022-12-01 |  | 2023-02-16 | No |  |  | 2024-06-01 |  | 0 | Yes | Yes | No | No
622 | 10 | 3255 | CAL | 4 | Bridge Replacement | Near Angels Camp, at West Branch Cherokee Creek Bridge No 30-0036. | Replace bridge. (Additional $300,000 for PS&E from local contribution.). | 866 | Yes | 866 | 802 | 802 | 802 | No | 1830 | Yes | 1530 | 1639 | 1371 | 1827 | No | 281 | Yes | 281 | 232 | 232 | 264 | No | 1500 | No | 1500 | 0 | 0 | 1116 | No | 278 | No | 278 | 97 | 97 | 129 | No | 5786 | No | 5786 | 0 | 0 | 4891 | No | 10541 | 10241 | 2770 | 2502 | 9029 |  | 2019-12-27 | 2019-12-19 |  |  | 2021-10-19 | 2022-05-02 |  |  | 2021-11-29 | 2022-05-16 |  |  | 2022-06-18 |  | 2022-12-20 | Yes |  |  | 2024-08-30 |  | 0 | Yes | Yes | No | No
623 | 10 | 3273 | SJ | 12 | Potato Slough Bridge Bearing Pads | Near Terminous, at Little Potato Slough Bridge No 29-0101. | Replace joint seals and bearing pads using temporary pile supports. | 808 | Yes | 808 | 640 | 640 | 640 | No | 1005 | Yes | 1005 | 505 | 505 | 505 | No | 2 | Yes | 2 | 1 | 1 | 1 | No | 1500 | Yes | 1500 | 269 | 269 | 1498 | No | 300 | No | 300 | 43 | 43 | 90 | No | 2797 | Yes | 2797 | 1251 | 1251 | 2797 | No | 6412 | 6412 | 2709 | 2709 | 5531 |  | 2020-07-20 | 2020-07-30 |  |  | 2021-02-17 | 2021-03-09 |  |  | 2021-05-20 | 2021-05-26 |  |  | 2021-12-15 | 2021-12-02 |  |  |  |  | 2022-12-30 |  | 2797 | No | No | No | No
624 | 10 | 3274 | SJ | 4 | SR-4 Ramp Metering System Installation | In Stockton, from Route 5 to Route 99. | Install ramp meters, traffic monitoring systems, Closed Circuit Television (CCTV), and synchronize intersection signals with ramp metering. | 2177 | Yes | 2177 | 1959 | 1959 | 1959 | No | 6057 | Yes | 6057 | 4569 | 4569 | 6000 | No | 695 | Yes | 695 | 129 | 129 | 684 | No | 9438 | No | 9438 | 0 | 0 | 7702 | No | 1332 | No | 1332 | 61 | 61 | 604 | No | 39097 | No | 39097 | 0 | 0 | 39712 | Yes | 58796 | 58796 | 6718 | 6718 | 56661 | 2020-08-12 | 2020-05-28 | 2020-05-28 |  |  | 2022-11-17 |  | 2022-11-17 | No | 2023-01-05 |  | 2023-01-05 | No | 2023-08-17 |  | 2023-08-17 | No |  |  | 2026-04-25 |  | 0 | No | No | No | No
625 | 10 | 3276 | SJ | 4 | SR 4 OLD RIVER BRIDGE MAINTENANCE | Near Discovery Bay, at Old River Bridge No 29-0045. | Remove and replace the deteriorated fender system. | 1591 | Yes | 1591 | 447 | 447 | 1372 | No | 1321 | No | 1321 | 0 | 0 | 1378 | Yes | 0 | No | 0 | 0 | 0 | 0 | No | 2099 | No | 2099 | 0 | 0 | 1893 | No | 872 | No | 872 | 0 | 0 | 344 | No | 6121 | No | 6121 | 0 | 0 | 4277 | No | 12004 | 12004 | 447 | 447 | 9264 |  | 2023-04-01 |  | 2023-04-01 | No | 2024-03-01 |  | 2024-03-01 | No | 2024-04-01 |  | 2024-04-01 | No | 2024-10-01 |  | 2024-10-01 | No |  |  | 2025-12-01 |  | 0 | No | No | No | No
626 | 10 | 3277 | SJ | 4 | SJ 4 CAPM | Near Stockton, from Route 99 to Stanislaus County line (PM 38.059); also in Stanislaus County from San Joaquin County line to 0.5 mile east of Dunton Road (PM 0.0/7.2). | Rehabilitate pavement, upgrade guardrail, construct rumble strips, upgrade facilities to Americans with Disabilities Act (ADA) standards, rehabilitate drainage systems, install Transportation Management System (TMS) elements, and upgrade bridge railing. (G13 Contingency). | 2660 | Yes | 2660 | 1458 | 1458 | 3072 | Yes | 2701 | No | 2701 | 0 | 0 | 2566 | No | 657 | No | 657 | 0 | 0 | 697 | Yes | 0 | No | 0 | 0 | 0 | 5545 | Yes | 379 | No | 379 | 0 | 0 | 508 | Yes | 0 | No | 0 | 0 | 0 | 31370 | Yes | 6397 | 6397 | 1458 | 1458 | 43758 |  | 2023-02-01 |  | 2023-02-01 | No | 2024-05-31 |  | 2024-05-31 | No | 2024-06-14 |  | 2024-06-14 | No | 2024-12-16 |  | 2024-12-16 | No |  |  | 2026-12-15 |  | 0 | No | Yes | No | No
627 | 10 | 3288 | CAL | 12 | CAL County Bridges Rehab | Near San Andreas, at North Fork Calaveras Creek Bridge No 30-0007. | Replace bridge. | 1172 | Yes | 1172 | 1043 | 1043 | 1043 | No | 0 | Yes | 0 | 0 | 0 | 2322 | Yes | 0 | Yes | 0 | 0 | 0 | 494 | Yes | 2293 | No | 2293 | 0 | 0 | 2666 | Yes | 145 | No | 145 | 3 | 3 | 688 | Yes | 8557 | No | 8557 | 0 | 0 | 11162 | Yes | 12167 | 12167 | 1046 | 1046 | 18375 |  | 2022-05-16 | 2022-05-18 |  |  | 2024-04-02 |  | 2024-04-02 | No | 2024-04-08 |  | 2024-04-08 | No | 2024-11-18 |  | 2024-11-18 | No |  |  | 2026-02-03 |  | 0 | No | Yes | No | No
628 | 10 | 3409 | CAL | 4 | CAL 4 Culvert Replacement | Near Forest Meadows, from 1.4 miles east of Forest Meadows Drive to Moran Road; also on Route 49 in Calaveras County (PM 5.78/16.98) and Tuolumne County (PM 12.64/17.17) at various locations. | Rehabilitate drainage systems. | 1248 | Yes | 1248 | 955 | 955 | 1302 | Yes | 987 | No | 987 | 0 | 0 | 1000 | Yes | 225 | No | 225 | 0 | 0 | 190 | No | 1134 | No | 1134 | 0 | 0 | 855 | No | 418 | No | 418 | 0 | 0 | 417 | No | 2677 | No | 2677 | 0 | 0 | 2215 | No | 6689 | 6689 | 955 | 955 | 5979 |  | 2022-10-07 |  | 2022-12-23 | No | 2024-02-05 |  | 2024-02-05 | No | 2024-04-10 |  | 2024-04-10 | No | 2025-02-06 |  | 2025-02-06 | No |  |  | 2026-02-16 |  | 0 | Yes | Yes | Yes | Yes
629 | 10 | 3411 | TUO | 120 | SR 120 TUO Drainage system | Near Groveland, from 4.7 miles west of La Grange Road to west of Ferretti Road; also in Calaveras County, on Route 26 and in Tuolumne County, on Route 108 at various locations. | Rehabilitate drainage systems. | 1182 | Yes | 1182 | 1083 | 1083 | 1323 | Yes | 1181 | No | 1181 | 0 | 0 | 1267 | Yes | 251 | No | 251 | 0 | 0 | 231 | No | 1307 | No | 1307 | 0 | 0 | 1235 | No | 247 | No | 247 | 0 | 0 | 334 | Yes | 3100 | No | 3100 | 0 | 0 | 2776 | No | 7268 | 7268 | 1083 | 1083 | 7166 |  | 2022-08-19 |  | 2022-09-23 | No | 2024-03-07 |  | 2024-03-07 | No | 2024-04-08 |  | 2024-04-08 | No | 2024-10-10 |  | 2024-10-10 | No |  |  | 2026-10-26 |  | 0 | Yes | Yes | Yes | No
630 | 10 | 3420 | STA | 5 | STA 5 BRIDGE REHAB | Near Patterson, from Fink Road Undercrossing No 38-0114L to Khaksa Road Undercrossing No 38-0127L/R at various locations. | Rehabilitate bridge decks with concrete overlay, replace joint seals and/or approach slabs. | 894 | Yes | 894 | 833 | 833 | 833 | No | 1947 | Yes | 1947 | 290 | 290 | 1639 | No | 15 | Yes | 15 | 1 | 1 | 17 | Yes | 1919 | No | 1919 | 0 | 0 | 1354 | No | 22 | No | 22 | 0 | 0 | 28 | Yes | 9814 | No | 9814 | 0 | 0 | 9894 | Yes | 14611 | 14611 | 1124 | 1124 | 13765 |  | 2021-08-26 | 2021-09-15 |  |  | 2023-03-28 |  | 2023-03-28 | No | 2023-04-28 |  | 2023-04-28 | No | 2023-11-30 |  | 2023-11-30 | No |  |  | 2024-08-30 |  | 0 | No | No | No | No
631 | 10 | 3422 | SJ | 5 | SR-4 ITS UPDATE | In San Joaquin County, on Routes 5, 4, 12, 26, 33, 88, 99, 120, and 205 at various locations. | Upgrade Transportation Management System (TMS) elements. | 962 | Yes | 962 | 488 | 488 | 1089 | Yes | 1436 | No | 1436 | 0 | 0 | 1634 | Yes | 158 | No | 158 | 0 | 0 | 147 | No | 1559 | No | 1559 | 0 | 0 | 1570 | Yes | 25 | No | 25 | 0 | 0 | 24 | No | 9090 | No | 9090 | 0 | 0 | 6224 | No | 13230 | 13230 | 488 | 488 | 10688 |  | 2022-11-01 |  | 2022-11-01 | No | 2024-02-20 |  | 2024-02-20 | No | 2024-04-03 |  | 2024-04-03 | No | 2024-11-15 |  | 2024-11-15 | No |  |  | 2025-08-15 |  | 0 | No | No | No | No
632 | 10 | 3425 | MER | 152 | Los Banos SR 152 Pavement Anchor | In Los Banos, from west of Badger Flat Road to west of Santa Fe Road. | Rehabilitate pavement and drainage systems, upgrade Transportation Management System (TMS) elements, roadway signs, guardrail and facilities to Americans with Disabilities Act (ADA) standards. | 1281 | Yes | 1281 | 12 | 12 | 1210 | No | 2244 | No | 2244 | 0 | 0 | 2192 | No | 1146 | No | 1146 | 0 | 0 | 991 | No | 3142 | No | 3142 | 0 | 0 | 2703 | No | 239 | No | 239 | 0 | 0 | 239 | No | 21919 | No | 21919 | 0 | 0 | 18784 | No | 29971 | 29971 | 12 | 12 | 26119 |  |  |  | 2023-09-01 |  |  |  | 2025-09-01 |  |  |  | 2025-09-15 |  |  |  | 2026-03-15 |  |  |  | 2027-12-01 |  | 0 | No | No | No | No
633 | 10 | 3427 | SJ | 5 | I-5 PAVEMENT ANCHOR PROJECT | In and near Stockton, from Hammer Lane to the Sacramento County line (PM 49.819). | Rehabilitate roadway, upgrade lighting, guardrail and bridge railing, install Transportation Management System (TMS) elements, replace signs, rehabilitate drainage systems, enhance highway worker safety, and upgrade facilities to Americans with Disabilities Act (ADA) standards. | 2108 | Yes | 2108 | 1683 | 1683 | 1683 | No | 4153 | Yes | 4153 | 650 | 650 | 4764 | Yes | 162 | Yes | 162 | 2 | 2 | 258 | Yes | 10953 | No | 10953 | 0 | 0 | 10995 | Yes | 69 | No | 69 | 0 | 0 | 69 | No | 98116 | No | 98116 | 0 | 0 | 98047 | No | 115561 | 115561 | 2335 | 2335 | 115816 |  | 2021-12-17 | 2022-01-26 |  |  | 2023-05-15 |  | 2023-05-15 | No | 2023-06-16 |  | 2023-06-16 | No | 2024-02-01 |  | 2024-02-01 | No |  |  | 2026-10-30 |  | 0 | No | No | No | No
634 | 10 | 3436 | ALP | 88 | Carson TMS | Near Kirkwood, on Routes 88, 4, and 89 in Alpine, Amador, and El Dorado Counties at various locations. | Install new Transportation Management System (TMS) elements and construct Maintenance Vehicle Pullouts (MPVs). (G13 Contingency). | 2094 | Yes | 2094 | 1153 | 1153 | 1881 | No | 2589 | No | 2589 | 0 | 0 | 2636 | Yes | 1073 | No | 1073 | 0 | 0 | 741 | No | 0 | No | 0 | 0 | 0 | 3194 | Yes | 820 | No | 820 | 3 | 3 | 316 | No | 0 | No | 0 | 0 | 0 | 16912 | Yes | 6576 | 6576 | 1156 | 1156 | 25680 |  | 2022-06-07 |  | 2022-08-16 | Yes | 2024-03-25 |  | 2024-03-25 | No | 2024-04-24 |  | 2024-04-24 | No | 2024-10-22 |  | 2024-10-22 | No |  |  | 2026-03-02 |  | 0 | Yes | Yes | No | No
635 | 10 | 3439 | MER | 59 | Merced Pavement Anchor Project | Near Merced, from Route 152 to Reilly Road. | Rehabilitate pavement, upgrade guardrail and lighting, replace sign panels, construct rumble strips, rehabilitate drainage, replace one bridge, and rehabilitate two bridge decks. (G13 Contingency). | 1757 | Yes | 1757 | 1420 | 1420 | 1420 | No | 1962 | No | 1962 | 0 | 0 | 2027 | Yes | 610 | No | 610 | 0 | 0 | 573 | No | 0 | No | 0 | 0 | 0 | 2650 | Yes | 908 | No | 908 | 3 | 3 | 384 | No | 0 | No | 0 | 0 | 0 | 20493 | Yes | 5237 | 5237 | 1423 | 1423 | 27547 |  | 2022-05-20 | 2022-05-23 |  |  | 2024-05-06 |  | 2024-05-06 | No | 2024-06-13 |  | 2024-06-13 | No | 2024-12-30 |  | 2024-12-30 | No |  |  | 2026-12-30 |  | 0 | No | Yes | No | No
636 | 10 | 3443 | STA | 99 | SJ & STA TMS | In Stanislaus and San Joaquin Counties, on various routes at various locations. | Install Transportation Management System (TMS) elements, and enhance highway worker safety. | 1100 | Yes | 1100 | 796 | 796 | 796 | No | 1420 | Yes | 1420 | 0 | 0 | 1707 | Yes | 100 | Yes | 100 | 0 | 0 | 156 | Yes | 1720 | No | 1720 | 0 | 0 | 1712 | No | 607 | No | 607 | 0 | 0 | 91 | No | 7855 | No | 7855 | 0 | 0 | 6000 | No | 12802 | 12802 | 796 | 796 | 10462 |  | 2022-06-17 | 2022-06-24 |  |  | 2024-03-01 |  | 2024-03-01 | No | 2024-05-03 |  | 2024-05-03 | No | 2025-01-06 |  | 2025-01-06 | No |  |  | 2026-03-16 |  | 0 | Yes | Yes | Yes | Yes
637 | 10 | 3496 | MER | 59 | SR 59 Pavement Anchor Project | In the city of Merced, from West Child Avenue to Route 99, also on Route 59 from Route 99 to north of Santa Fe Drive (PM 14.78/16.3). | Rehabilitate pavement and drainage systems, install Transportation Management System (TMS) elements, upgrade facilities to Americans with Disabilities Act (ADA) standards, and construct sidewalks and Class 2 bike lanes. | 1478 | Yes | 1478 | 0 | 0 | 1443 | No | 2621 | No | 2621 | 0 | 0 | 2567 | No | 1288 | No | 1288 | 0 | 0 | 1122 | No | 2191 | No | 2191 | 0 | 0 | 1913 | No | 868 | No | 868 | 0 | 0 | 784 | No | 11602 | No | 11602 | 0 | 0 | 11602 | No | 20048 | 20048 | 0 | 0 | 19431 |  |  |  | 2024-01-31 |  |  |  | 2025-12-17 |  |  |  | 2025-12-24 |  |  |  | 2026-07-31 |  |  |  | 2027-05-28 |  | 0 | No | No | No | No
638 | 10 | 3511 | ALP | 4 | Drainage System Restoration | Near Bear Valley, from east of Bear Valley Road to 1.2 miles west of Route 89 at various locations; also on Route 207 from 0.4 mile to 1.2 miles north of Route 4 (PM 0.38/1.19) at various locations. | Rehabilitate drainage systems. | 1101 | Yes | 1101 | 0 | 0 | 1081 | No | 1184 | No | 1184 | 0 | 0 | 1236 | Yes | 588 | No | 588 | 0 | 0 | 580 | No | 1279 | No | 1279 | 0 | 0 | 1357 | Yes | 3259 | No | 3259 | 0 | 0 | 3154 | No | 9391 | No | 9391 | 0 | 0 | 9391 | No | 16802 | 16802 | 0 | 0 | 16799 |  |  |  | 2024-09-02 |  |  |  | 2026-05-01 |  |  |  | 2026-06-01 |  |  |  | 2027-01-01 |  |  |  | 2028-10-06 |  | 0 | Yes | Yes | Yes | Yes
639 | 10 | 3515 | MPA | 49 | Repair/replace old TMS | In Mariposa, Alpine, and Tuolumne Counties, on Routes 49, 16, 88,104, 108 124, 132 and 140 at various locations. | Replace and install new Transportation Management System (TMS) elements. | 520 | Yes | 520 | 0 | 0 | 512 | No | 1110 | No | 1110 | 0 | 0 | 1113 | Yes | 30 | No | 30 | 0 | 0 | 27 | No | 630 | No | 630 | 0 | 0 | 581 | No | 36 | No | 36 | 0 | 0 | 13 | No | 1900 | No | 1900 | 0 | 0 | 3263 | Yes | 4226 | 4226 | 0 | 0 | 5509 |  |  |  | 2023-11-17 |  |  |  | 2024-10-06 |  |  |  | 2024-11-06 |  |  |  | 2025-05-12 |  |  |  | 2026-07-02 |  | 0 | No | Yes | No | No
640 | 10 | 3516 | SJ | 4 | HAR Signal Upgrade | In Stockton, from Route 5 to WIlson Road at various locations, and on Route 5 at March Lane. | Replace Transportation Management System (TMS) elements, rehabilitate drainage systems and upgrade facilities to Americans with Disabilities Act (ADA) standards. | 770 | Yes | 770 | 0 | 0 | 754 | No | 1940 | No | 1940 | 0 | 0 | 2251 | Yes | 220 | No | 220 | 0 | 0 | 311 | Yes | 1850 | No | 1850 | 0 | 0 | 1648 | No | 114 | No | 114 | 0 | 0 | 80 | No | 9430 | No | 9430 | 0 | 0 | 8520 | No | 14324 | 14324 | 0 | 0 | 13564 |  |  |  | 2023-11-17 |  |  |  | 2025-03-16 |  |  |  | 2025-07-15 |  |  |  | 2026-03-09 |  |  |  | 2027-07-01 |  | 0 | No | No | No | No
641 | 10 | 3517 | SJ | 4 | SJ 4 CAPM | Near Discovery Bay and Holt, from Contra Costa County line to east of South Whiskey Road. | Rehabilitate pavement, construct an approach slab, upgrade Transportation Management System (TMS) elements, install lighting, apply erosion control, and replace guardrail and sign panels. | 1164 | Yes | 1164 | 13 | 13 | 1114 | No | 2050 | No | 2050 | 0 | 0 | 1871 | No | 47 | No | 47 | 0 | 0 | 41 | No | 2412 | No | 2412 | 0 | 0 | 2060 | No | 156 | No | 156 | 0 | 0 | 150 | No | 14165 | No | 14165 | 0 | 0 | 21255 | Yes | 19994 | 19994 | 13 | 13 | 26491 |  |  |  | 2024-04-05 |  |  |  | 2025-09-15 |  |  |  | 2025-09-26 |  |  |  | 2026-04-06 |  |  |  | 2027-11-01 |  | 0 | No | Yes | No | No
642 | 10 | 3526 | STA | 4 | Hoods Creek Bridge Replacement | Near Copperopolis, at Hoods Creek Bridge No 38-0041. | Replace bridge. | 2058 | Yes | 2058 | 0 | 0 | 1866 | No | 2438 | No | 2438 | 0 | 0 | 2046 | No | 490 | No | 490 | 0 | 0 | 412 | No | 3391 | No | 3391 | 0 | 0 | 2897 | No | 1980 | No | 1980 | 0 | 0 | 1980 | No | 9012 | No | 9012 | 0 | 0 | 15220 | Yes | 19369 | 19369 | 0 | 0 | 24421 |  |  |  | 2024-11-07 |  |  |  | 2026-03-31 |  |  |  | 2026-05-01 |  |  |  | 2026-09-23 |  |  |  | 2027-10-29 |  | 0 | No | Yes | No | No
643 | 10 | 3533 | SJ | 5 | I 580 Separation Bridge MTCE | Near Lathrop, at the southbound Route 5 to westbound Route 205 Separation Bridge No 29-0242L. | Apply polyester concrete overlay to bridge deck. (Bridge Deck Preservation). | 120 | Yes | 120 | 69 | 69 | 69 | No | 200 | Yes | 200 | 0 | 0 | 382 | Yes | 0 | No | 0 | 0 | 0 | 0 | No | 290 | No | 290 | 0 | 0 | 315 | Yes | 0 | No | 0 | 0 | 0 | 0 | No | 1300 | No | 1300 | 0 | 0 | 941 | No | 1910 | 1910 | 69 | 69 | 1707 |  |  | 2022-07-08 |  |  |  |  | 2023-05-19 |  |  |  | 2023-06-17 |  |  |  | 2023-12-08 |  |  |  | 2024-10-04 |  | 0 | Yes | Yes | Yes | Yes
644 | 10 | 3534 | MER | 99 | Mer-99 Rehabilitate Four Bridges (39-0126L/0126R/0128L/0128R) | In Atwater, at East Atwater Overhead No 36-0126L/R; also at West Atwater Overhead No 39-128L/R (PM 23.47). | Apply polyester concrete overlay to bridge decks. (Bridge Deck Preservation). | 100 | Yes | 100 | 96 | 96 | 96 | No | 350 | Yes | 350 | 0 | 0 | 505 | Yes | 5 | Yes | 5 | 0 | 0 | 7 | Yes | 600 | No | 600 | 0 | 0 | 790 | Yes | 5 | No | 5 | 0 | 0 | 0 | No | 3471 | No | 3471 | 0 | 0 | 2751 | No | 4531 | 4531 | 96 | 96 | 4149 |  |  | 2022-05-20 |  |  |  |  | 2023-02-05 |  |  |  | 2023-02-21 |  |  |  | 2023-09-15 |  |  |  | 2024-09-30 |  | 0 | No | No | No | No
645 | 10 | 5431 | MER | 99 | MER-99 PAVEMENT REHABILITATION | In and near Atwater, from 0.4 mile south of Buhach Road to 0.7 mile south of Westside BoulevaRd Roadway rehabilitation. | PAVEMENT RESURFACING AND RESTORATION | 2223 | Yes | 2223 | 1987 | 1987 | 1987 | No | 5200 | Yes | 5200 | 2843 | 2843 | 2843 | No | 677 | Yes | 677 | 406 | 406 | 656 | No | 10000 | Yes | 10000 | 7387 | 7387 | 10060 | Yes | 3369 | No | 3369 | 2374 | 2374 | 2399 | No | 62340 | Yes | 62340 | 46623 | 46623 | 62340 | No | 83809 | 83809 | 61620 | 61620 | 80285 | 2018-10-17 | 2017-12-04 | 2017-12-04 |  |  | 2019-06-14 | 2019-06-24 |  |  | 2019-06-21 | 2019-06-28 |  |  | 2020-02-28 | 2019-12-31 |  |  |  |  | 2023-04-30 |  | 62340 | No | No | No | No
646 | 10 | 7546 | SJ | 88 | SR88 Pavement Anchor Project | Near Lockeford, east of Comstock Road to east of Disch Road. | Rehabilitate pavement, upgrade facilities to Americans with Disabilities Act (ADA) standards, reconstruct rumble strips, lengthen merge lanes, replace signs, upgrade Transportation Management System (TMS) elements, construct Class 2 and 3 bike lanes and sidewalks as complete streets elements. (G13 Contingency). | 2168 | Yes | 2168 | 2497 | 2497 | 3283 | Yes | 2267 | No | 2267 | 121 | 121 | 2529 | Yes | 800 | No | 800 | 38 | 38 | 1058 | Yes | 0 | No | 0 | 0 | 0 | 3543 | Yes | 1336 | No | 1336 | 0 | 0 | 4707 | Yes | 0 | No | 0 | 0 | 0 | 25193 | Yes | 6571 | 6571 | 2656 | 2656 | 40313 |  | 2022-07-27 |  | 2022-10-14 | No | 2024-02-24 |  | 2024-06-07 | Yes | 2024-03-15 |  | 2024-06-17 | Yes | 2024-09-17 |  | 2024-11-04 | No |  |  | 2025-10-15 |  | 0 | Yes | Yes | No | No
647 | 11 | 0615F | SD | 5 | I-5 North Coast Corridor HOV Extension - Phase 1 - Encinitas HOV | In the cities of Encinitas and Carlsbad from Manchester Avenue to Palomar Airport Road. | Construct one High Occupancy Vehicle (HOV) lane in each direction; construct multi-use facility at Manchester; construct bike paths and soundwalls (CMGC). | 0 | No | 0 | 0 | 0 | 0 | No | 0 | No | 0 | 1330 | 1330 | 1330 | Yes | 0 | No | 0 | 0 | 0 | 0 | No | 44670 | Yes | 5670 | 28682 | 3633 | 40639 | No | 0 | No | 0 | 0 | 0 | 0 | No | 256059 | Yes | 28981 | 233647 | 25741 | 256038 | No | 300729 | 34651 | 263659 | 30704 | 298007 | 2018-08-15 | 2014-08-30 |  |  |  | 2018-06-30 |  |  |  | 2018-06-30 |  |  |  | 2018-10-31 | 2018-11-16 |  |  | 2022-09-01 |  | 2022-12-30 | Yes | 256038 | No | Yes | No | No
648 | 11 | 1171 | SD | Var | TMS ELEMENT IN-HOUSE FIBER OPTIC | In San Diego County, on various routes at various locations. | Replace Changeable Message Signs (CMS) panels with Advanced Variable Message Signs (AVMS) panels. | 0 | No | 0 | 0 | 0 |  | No | 900 | Yes | 900 | 879 | 879 | 879 | No | 0 | No | 0 | 0 | 0 | 0 | No | 1257 | Yes | 1257 | 1074 | 1074 | 1261 | Yes | 0 | No | 0 | 0 | 0 | 0 | No | 4758 | Yes | 4758 | 3774 | 3774 | 4758 | No | 6915 | 6915 | 5727 | 5727 | 6898 |  | 2015-06-19 | 2015-06-19 |  |  | 2019-10-14 | 2019-06-14 |  |  | 2019-12-12 | 2019-07-15 |  |  | 2020-09-04 | 2020-04-16 |  |  |  |  | 2022-07-31 |  | 4757 | No | No | No | No
649 | 11 | 1177 | SD | 94 | SR-94 PAVEMENT REHAB | Near Spring Valley, from Spring Street to Route 54. | Pavement rehabilitation. | 577 | Yes | 577 | 565 | 565 | 565 | No | 1351 | Yes | 1351 | 1347 | 1347 | 1347 | No | 0 | Yes | 0 | 0 | 0 | 0 | No | 1855 | Yes | 1855 | 1820 | 1820 | 1850 | No | 0 | No | 0 | 0 | 0 | 0 | No | 12807 | Yes | 12807 | 11679 | 11679 | 12807 | No | 16590 | 16590 | 15411 | 15411 | 16569 |  | 2018-01-19 | 2018-01-12 |  |  | 2019-10-28 | 2019-10-23 |  |  | 2019-11-26 | 2019-12-13 |  |  | 2020-06-16 | 2020-08-07 |  |  |  |  | 2022-07-29 |  | 11538 | No | No | No | No
650 | 11 | 1188 | SD | 54 | SR 54 PAVEMENT PRESERVATION | In and near National City and Chula Vista, from Route 54/5 Separation to the Route 54/125 Junction. | Rehabilitate flexible and rigid pavement on the traveled way, shoulders, ramps and connectors, apply methacrylate to bridge decks, upgrade guardrail and dike. | 969 | Yes | 969 | 888 | 888 | 888 | No | 2730 | Yes | 2730 | 2575 | 2575 | 3085 | Yes | 24 | Yes | 24 | 24 | 24 | 26 | Yes | 2470 | No | 2470 | 0 | 0 | 2335 | No | 297 | No | 297 | 0 | 0 | 50 | No | 18161 | No | 18161 | 0 | 0 | 18161 | No | 24651 | 24651 | 3487 | 3487 | 24545 |  | 2020-02-07 | 2020-06-30 |  |  | 2021-08-31 | 2022-01-12 |  |  | 2021-10-22 | 2022-06-30 |  |  | 2022-05-20 |  | 2023-01-18 | Yes |  |  | 2024-05-31 |  | 0 | Yes | No | No | No
651 | 11 | 1194 | SD | 8 | I-8 CULVERT REPLACEMENT | Near Alpine, Pine Valley, and Boulder Oaks, from 1.2 miles east of Lake Jennings Park Road to Crestwood Road Undercrossing (PM R61.3R/L). | Rehabilitate culverts and energy dissipaters. | 954 | Yes | 954 | 752 | 752 | 752 | No | 1246 | Yes | 1246 | 1242 | 1242 | 1242 | No | 250 | Yes | 250 | 52 | 52 | 205 | No | 1842 | Yes | 1842 | 361 | 361 | 1941 | Yes | 125 | No | 125 | 116 | 116 | 116 | No | 6628 | Yes | 6628 | 996 | 996 | 6628 | No | 11045 | 11045 | 3519 | 3519 | 10884 |  | 2019-06-28 | 2019-06-28 |  |  | 2020-07-02 | 2021-02-25 |  |  | 2020-08-20 | 2021-06-25 |  |  | 2021-04-14 | 2022-02-24 |  |  |  |  | 2024-07-29 |  | 6628 | No | No | No | No
652 | 11 | 1241 | IMP,SD | VAR | Intelligent Transportation System Technology (Advanced Technology Corridors at Border Ports of Entry) | In San Diego County and Imperial County on various routes at various locations. | Install Intelligent Technology Statewide Border Wait Time, implement a fiber optic cable network to facilitate an advanced traveler information and border wait time system connecting the entire San Diego and Imperial border network. | 818 | Yes | 818 | 710 | 710 | 710 | No | 4038 | Yes | 1721 | 4118 | 1812 | 4118 | Yes | 62 | Yes | 62 | 19 | 19 | 49 | No | 5938 | Yes | 4404 | 2759 | 2046 | 5807 | No | 375 | No | 375 | 7 | 7 | 15 | No | 27945 | Yes | 19827 | 10795 | 7520 | 21507 | No | 39176 | 27207 | 18408 | 12114 | 32206 | 2018-08-15 | 2018-11-16 | 2018-10-15 |  |  | 2020-02-01 | 2020-06-23 |  |  | 2020-02-15 | 2020-06-24 |  |  | 2020-07-15 | 2021-04-08 |  |  | 2022-05-20 |  | 2023-08-03 | Yes | 21507 | Yes | No | No | No
653 | 11 | 1246 | SD | 8 | SD-008-L0.7/R23.0 - DRAINAGE SYSTEM RESTORATION | In and near the cities of San Diego, La Mesa, and El Cajon, from 0.5 mile west of Midway Drive Undercrossing to 0.6 mile west of Flinn Springs Road Undercrossing. | Repair, rehabilitate and replace culvert systems. | 1173 | Yes | 1173 | 961 | 961 | 961 | No | 1590 | Yes | 1590 | 1531 | 1531 | 1531 | No | 0 | No | 0 | 0 | 0 | 0 | No | 2020 | Yes | 2020 | 1555 | 1555 | 2068 | Yes | 80 | No | 80 | 0 | 0 | 0 | No | 5877 | Yes | 5877 | 4348 | 4348 | 5877 | No | 10740 | 10740 | 8395 | 8395 | 10437 |  | 2018-11-26 | 2018-12-13 |  |  | 2020-02-04 | 2020-04-17 |  |  | 2020-03-30 | 2020-06-05 |  |  | 2020-10-08 | 2020-11-05 |  |  |  |  | 2022-09-29 |  | 5877 | No | No | No | No
654 | 11 | 1247 | SD | 78 | CULVERT REPLACEMENT | In and near Oceanside, Vista, and San Marcos, at various locations from 0.3 mile east of Route 5 to 0.5 mile west of Route 15. | Rehabilitate and replace culverts and rehabilitate pavement. | 1091 | Yes | 1091 | 1091 | 1091 | 1091 | No | 2538 | Yes | 2538 | 2483 | 2483 | 2508 | No | 212 | Yes | 212 | 148 | 148 | 214 | Yes | 2707 | Yes | 2707 | 0 | 0 | 2627 | No | 204 | No | 204 | 17 | 17 | 204 | No | 11924 | Yes | 11924 | 0 | 0 | 8519 | No | 18676 | 18676 | 3739 | 3739 | 15163 |  | 2019-12-31 | 2020-03-27 |  |  | 2021-12-10 | 2021-12-21 |  |  | 2021-12-10 | 2021-12-21 |  |  | 2022-06-13 |  | 2022-09-07 | Yes |  |  | 2025-05-29 |  | 0 | Yes | No | No | No
655 | 11 | 1255 | SD | 8 | I8 - PAVEMENT REHAB | Near Alpine, from 0.5 mile east of Willows Road to Pine Valley Creek Bridge. | Upgrade guardrail, replace approach/departure slabs and construct rumble strips. | 1026 | Yes | 1026 | 1007 | 1007 | 1007 | No | 3762 | Yes | 3762 | 3214 | 3214 | 3214 | No | 0 | No | 0 | 0 | 0 | 0 | No | 5724 | Yes | 5724 | 63 | 63 | 5523 | No | 0 | No | 0 | 0 | 0 | 0 | No | 46830 | Yes | 46830 | 0 | 0 | 46830 | No | 57342 | 57342 | 4284 | 4284 | 56574 | 2019-08-15 | 2019-05-01 | 2019-05-01 |  |  | 2021-01-08 | 2021-01-04 |  |  | 2021-02-12 | 2021-06-22 |  |  | 2021-07-22 | 2022-05-03 |  |  |  |  | 2024-06-24 |  | 46830 | No | No | No | No
656 | 11 | 1256 | SD | 8 | E8-S163 CONNECTOR OC | In the city of San Diego, at the East Route 8 to South Route 163 Connector Overcrossing No 57-0355G. | Bridge rail replacement. | 374 | Yes | 374 | 355 | 355 | 355 | No | 969 | Yes | 969 | 963 | 963 | 963 | No | 0 | No | 0 | 0 | 0 | 0 | No | 848 | Yes | 848 | 359 | 359 | 820 | No | 0 | No | 0 | 0 | 0 | 0 | No | 1524 | Yes | 1524 | 799 | 799 | 1524 | No | 3715 | 3715 | 2476 | 2476 | 3662 |  | 2019-11-08 | 2019-12-23 |  |  | 2021-01-29 | 2021-03-16 |  |  | 2021-03-26 | 2021-06-14 |  |  | 2021-08-27 | 2022-01-13 |  |  |  |  | 2022-10-31 |  | 1523 | No | No | No | No
657 | 11 | 1257 | SD | 125 | SR-125 PAVEMENT REHAB | In and near La Mesa, El Cajon, Lemon Grove, and Santee, from the southern Route 94 Separation to Mission Gorge Road; also on Route 94 from the western Route 125 separation to the eastern Route 125 separation (PM R9.8/R10.6). | Rehabilitate pavement by grinding and replacing concrete slabs and cold plane and overlay shoulders with Rubberized Hot Mix Asphalt (RHMA-G). | 1383 | Yes | 1383 | 1331 | 1331 | 1331 | No | 2541 | Yes | 2541 | 2426 | 2426 | 2426 | No | 53 | Yes | 53 | 14 | 14 | 46 | No | 5420 | Yes | 5420 | 38 | 38 | 5177 | No | 30 | No | 30 | 0 | 0 | 0 | No | 30796 | Yes | 30796 | 0 | 0 | 30796 | No | 40223 | 40223 | 3809 | 3809 | 39776 | 2020-05-13 | 2020-02-06 | 2020-02-06 |  |  | 2021-06-22 | 2021-06-25 |  |  | 2021-08-17 | 2021-08-13 |  |  | 2022-01-07 | 2022-05-20 |  |  |  |  | 2025-04-11 |  | 30796 | No | No | No | No
658 | 11 | 1262 | SD | Var | REPAIR EXISTING LOOP DETECTORS | In San Diego County, at various locations. | Repair and install Vehicle Detection Station (VDS) elements including Microwave Vehicle Detection Systems (MVDS) and loop detectors. | 911 | Yes | 911 | 885 | 885 | 885 | No | 2160 | Yes | 2160 | 2030 | 2030 | 2030 | No | 0 | No | 0 | 0 | 0 | 0 | No | 2264 | Yes | 2264 | 1165 | 1165 | 2235 | No | 0 | No | 0 | 0 | 0 | 0 | No | 8747 | Yes | 8747 | 5511 | 5511 | 8747 | No | 14082 | 14082 | 9591 | 9591 | 13897 |  | 2018-08-22 | 2019-01-29 |  |  | 2019-11-15 | 2020-03-17 |  |  | 2019-12-13 | 2020-04-20 |  |  | 2020-05-15 | 2020-11-20 |  |  |  |  | 2023-12-29 |  | 8746 | No | No | No | No
659 | 11 | 1280 | SD | 805 | I-805 SWEETWATER RIVER BRIDGE UPGRADE | In and near Chula Vista, from 0.2 mile south of Sweetwater River Bridge No 57-0638R/L to Route 54. | Upgrade bridge rails, widen bridges to make standard, and repair approach slabs, joint seals, gore pavement, and shoulders. | 42 | No | 0 | 41 | 0 | 41 | No | 2029 | No | 0 | 1840 | 0 | 1840 | No | 15 | No | 0 | 0 | 0 | 0 | No | 5023 | Yes | 5023 | 4575 | 4575 | 5270 | Yes | 0 | No | 0 | 0 | 0 | 15 | Yes | 21536 | Yes | 21536 | 19407 | 19407 | 21536 | No | 28645 | 26559 | 25863 | 23982 | 28702 | 2018-10-17 | 2017-08-31 | 2017-08-31 |  |  | 2018-02-28 | 2018-02-28 |  |  | 2018-06-29 | 2018-06-29 |  |  | 2019-01-24 | 2019-01-09 |  |  |  |  | 2022-09-30 |  | 20186 | No | No | No | No
660 | 11 | 1302 | SD | 52 | SR-52 DIPS PAVEMENT REHAB | In the city of San Diego, from 0.4 mile west of Convoy Street Overcrossing (OC) to 0.3 mile east of Santo Road OC. | Roadway rehabilitation to mitigate highway settlement, construct auxiliary lane, Transportation Management System (TMS), lighting, and roadside safety improvements. (G13 Contingency). | 2066 | Yes | 2066 | 1611 | 1611 | 1611 | No | 3452 | Yes | 3452 | 2830 | 2830 | 3462 | Yes | 45 | No | 45 | 0 | 0 | 0 | No | 0 | No | 0 | 0 | 0 | 7334 | Yes | 15 | No | 15 | 0 | 0 | 0 | No | 0 | No | 0 | 0 | 0 | 44537 | Yes | 5578 | 5578 | 4441 | 4441 | 56944 | 2021-05-12 | 2021-03-22 | 2021-03-22 |  |  | 2022-02-01 | 2022-01-31 |  |  | 2022-05-13 | 2022-06-23 |  |  | 2022-12-12 |  | 2022-12-12 | No |  |  | 2026-08-03 |  | 0 | No | Yes | No | No
661 | 11 | 1303 | SD | 94 | SD-94 CULVERT REHAB | In and near the cities of San Diego and Lemon Grove, from Route 5 to 0.1 mile west of Millar Ranch Road; also on Route 15 at PM 2.1, Route 125 at PM 13.0/13.5, and Route 805 at PM 13.5. | Rehabilitate culverts, rehabilitate pavement, replace signs, upgrade Transportation Management System (TMS) elements, and upgrade facilities to Americans with Disabilities Act (ADA) standards. (G13 Contingency). | 2825 | Yes | 2825 | 1786 | 1786 | 2916 | Yes | 4147 | No | 4147 | 0 | 0 | 3984 | No | 1404 | No | 1404 | 0 | 0 | 801 | No | 0 | No | 0 | 0 | 0 | 7487 | Yes | 1800 | No | 1800 | 0 | 0 | 489 | No | 0 | No | 0 | 0 | 0 | 59314 | Yes | 10176 | 10176 | 1786 | 1786 | 74991 |  | 2022-07-15 |  | 2022-07-15 | No | 2024-01-12 |  | 2024-02-26 | No | 2024-03-15 |  | 2024-04-26 | No | 2024-10-02 |  | 2024-11-13 | No |  |  | 2029-10-29 |  | 0 | No | Yes | No | No
662 | 11 | 1306 | SD | 94 | SR94 CULVERT REHAB & SR188 CAPM | Near Jamul, Campo, and Boulevard, from south of Route 54/Jamacha Road to Route 8; also on Route 188, from the Mexico border to Route 94 (PM 0.0/1.850). | Rehabilitate culverts, upgrade curb ramps to Americans with Disabilities Act (ADA) standards, replace roadside signs, install rumble strips, and upgrade lighting. (G13 Contingency). | 2335 | Yes | 2335 | 1552 | 1552 | 2322 | No | 2118 | No | 2118 | 0 | 0 | 2005 | No | 1327 | No | 1327 | 0 | 0 | 1020 | No | 0 | No | 0 | 0 | 0 | 2632 | Yes | 1420 | No | 1420 | 0 | 0 | 511 | No | 0 | No | 0 | 0 | 0 | 18100 | Yes | 7200 | 7200 | 1552 | 1552 | 26590 |  | 2022-07-15 |  | 2023-06-19 | Yes | 2024-01-19 |  | 2024-05-19 | Yes | 2024-03-08 |  | 2024-06-08 | Yes | 2024-08-16 |  | 2025-01-16 | Yes |  |  | 2026-04-12 |  | 0 | No | Yes | No | No
663 | 11 | 1307 | SD | 76 | SD-76 CULVERT REHAB | Near Pala, Pauma Valley, Rincon, and La Jolla Amago, from east of Route 15 to west of Route 79. | Rehabilitate culverts, replace signs, upgrade lighting, and upgrade facilities to Americans with Disabilities Act (ADA) standards. | 1533 | Yes | 1533 | 741 | 741 | 1821 | Yes | 1506 | No | 1506 | 0 | 0 | 1806 | Yes | 1587 | No | 1587 | 0 | 0 | 1487 | No | 2224 | No | 2224 | 0 | 0 | 2021 | No | 500 | No | 500 | 0 | 0 | 0 | No | 13909 | No | 13909 | 0 | 0 | 14462 | Yes | 21259 | 21259 | 741 | 741 | 21597 |  | 2022-08-22 |  | 2023-06-29 | Yes | 2024-03-15 |  | 2025-03-04 | Yes | 2024-04-12 |  | 2025-04-03 | Yes | 2024-10-30 |  | 2025-10-20 | Yes |  |  | 2026-08-05 |  | 0 | Yes | No | No | No
664 | 11 | 1308 | SD | 805 | I805 NORTH MAINT & REHAB | In the city of San Diego, from north of Route 52 to Route 5. | Rehabilitate culverts, upgrade Transportation Management System (TMS) elements, replace signs, enhance highway worker safety, upgrade lighting, and upgrade facilities to Americans with Disabilities Act (ADA) standards. | 1479 | Yes | 1479 | 1208 | 1208 | 1208 | No | 4285 | No | 4285 | 0 | 0 | 4147 | No | 126 | No | 126 | 0 | 0 | 120 | No | 7289 | No | 7289 | 0 | 0 | 6499 | No | 1000 | No | 1000 | 0 | 0 | 200 | No | 32889 | No | 32889 | 0 | 0 | 32889 | No | 47068 | 47068 | 1208 | 1208 | 45063 |  | 2022-02-01 | 2022-05-12 |  |  | 2024-03-05 |  | 2024-01-02 | No | 2024-04-05 |  | 2024-02-01 | No | 2024-11-08 |  | 2024-08-15 | No |  |  | 2028-02-14 |  | 0 | No | No | No | No
665 | 11 | 1309 | SD | 805 | I805 MIDDLE MAINT & REHAB | In the city of San Diego, from Route 15 to Route 52. | Add and upgrade Transportation Management System (TMS) elements, rehabilitate pavement, rehabilitate drainage, replace signs, and enhance highway worker safety. (G13 Contingency). | 2863 | Yes | 2863 | 1857 | 1857 | 2827 | No | 5804 | No | 5804 | 0 | 0 | 5519 | No | 117 | No | 117 | 0 | 0 | 103 | No | 0 | No | 0 | 0 | 0 | 9258 | Yes | 360 | No | 360 | 0 | 0 | 165 | No | 0 | No | 0 | 0 | 0 | 63510 | Yes | 9144 | 9144 | 1857 | 1857 | 81382 |  | 2022-01-17 |  | 2022-06-30 | Yes | 2023-03-09 |  | 2023-07-03 | Yes | 2023-04-06 |  | 2023-09-22 | Yes | 2023-11-10 |  | 2023-12-28 | No |  |  | 2028-03-13 |  | 0 | Yes | Yes | No | No
666 | 11 | 1310 | SD | 125 | SD-125 (SD-54 TO SD-94) | In and near Lemon Grove, from south of Elkelton Place to Route 94. | Pavement rehabilitation. (G13 Contingency). | 3071 | Yes | 3071 | 1991 | 1991 | 1991 | No | 5557 | Yes | 5557 | 1865 | 1865 | 4973 | No | 317 | Yes | 317 | 29 | 29 | 315 | No | 0 | No | 0 | 0 | 0 | 6249 | Yes | 120 | No | 120 | 0 | 0 | 0 | No | 0 | No | 0 | 0 | 0 | 37300 | Yes | 9065 | 9065 | 3885 | 3885 | 50828 | 2020-10-22 | 2020-08-18 | 2020-08-18 |  |  | 2021-11-29 | 2022-05-06 |  |  | 2022-02-18 |  | 2022-08-18 | Yes | 2022-07-18 |  | 2023-03-02 | Yes |  |  | 2025-02-10 |  | 0 | Yes | Yes | No | No
667 | 11 | 1311 | SD | 805 | I-805 S. MAINT AND REHAB PROJECT | In and near the cities of San Diego, Chula Vista, and National City, from south of Route 5 (PM 0.149) to Route 15. | Rehabilitate roadway, rehabilitate culverts, construct auxiliary lanes, add bike trail and pedestrian bridge as complete streets elements, upgrade safety devices, enhance highway worker safety, upgrade lighting, and make bicycle and pedestrian improvements. (G13 Contingency). | 6652 | Yes | 6652 | 3770 | 3770 | 6260 | No | 16138 | No | 16138 | 0 | 0 | 13972 | No | 1660 | No | 1660 | 0 | 0 | 1261 | No | 0 | No | 0 | 0 | 0 | 21852 | Yes | 1305 | No | 1305 | 0 | 0 | 0 | No | 0 | No | 0 | 0 | 0 | 144385 | Yes | 25755 | 25755 | 3770 | 3770 | 187730 |  | 2022-07-01 |  | 2023-02-15 | Yes | 2024-04-30 |  | 2024-04-30 | No | 2024-05-31 |  | 2024-05-31 | No | 2024-12-06 |  | 2024-12-06 | No |  |  | 2031-04-30 |  | 0 | No | Yes | No | No
668 | 11 | 1313 | SD | 79 | SR-79 NORTH - CULVERT ASSET MANAGEMENT | Near Santa Ysabel, Warner Springs, and Holcomb Village, from north of Route 78 to the Riverside County line. | Rehabilitate culverts, replace sign panels, and make bicycle and pedestrian improvements. | 1243 | Yes | 1243 | 1051 | 1051 | 1414 | Yes | 1221 | No | 1221 | 0 | 0 | 1192 | No | 669 | No | 669 | 0 | 0 | 605 | No | 1399 | No | 1399 | 0 | 0 | 1364 | No | 175 | No | 175 | 0 | 0 | 254 | Yes | 7350 | No | 7350 | 0 | 0 | 7350 | No | 12057 | 12057 | 1051 | 1051 | 12179 |  | 2022-04-22 |  | 2022-09-30 | Yes | 2024-01-23 |  | 2024-02-23 | No | 2024-02-28 |  | 2024-06-28 | Yes | 2024-09-18 |  | 2024-12-20 | Yes |  |  | 2026-12-23 |  | 0 | Yes | No | No | No
669 | 11 | 1314 | SD | 67 | SR-67 DRAINAGE RESTORATION | Near Lakeside and Eucalyptus Hills, from north of Riverford Road to Ellie Lane. | Rehabilitate culverts, upgrade lighting, enhance highway worker safety, and upgrade facilities to Americans with Disabilities Act (ADA) standards. | 1128 | Yes | 1128 | 1125 | 1125 | 1436 | Yes | 1461 | No | 1461 | 0 | 0 | 1425 | No | 305 | No | 305 | 0 | 0 | 268 | No | 1527 | No | 1527 | 0 | 0 | 1468 | No | 350 | No | 350 | 0 | 0 | 527 | Yes | 8573 | No | 8573 | 0 | 0 | 8832 | Yes | 13344 | 13344 | 1125 | 1125 | 13956 |  | 2022-06-30 |  | 2022-11-28 | Yes | 2022-10-25 |  | 2023-09-22 | Yes | 2023-11-01 |  | 2024-04-12 | Yes | 2024-07-03 |  | 2024-09-06 | No |  |  | 2025-08-20 |  | 0 | Yes | No | No | No
670 | 11 | 1315 | SD | 15 | I-15 S - CULVERT/TUNNEL LIGHTING/ADA | In the city of San Diego, from Main Street to Route 52. | Rehabilitate culverts, upgrade lighting, replace signs, install new Transportation Management System (TMS) elements, and upgrade facilities to Americans with Disabilities (ADA) standards. | 1610 | Yes | 1610 | 789 | 789 | 1678 | Yes | 4466 | No | 4466 | 0 | 0 | 3838 | No | 197 | No | 197 | 0 | 0 | 98 | No | 3998 | No | 3998 | 0 | 0 | 3706 | No | 366 | No | 366 | 0 | 0 | 255 | No | 23819 | No | 23819 | 0 | 0 | 23819 | No | 34456 | 34456 | 789 | 789 | 33394 |  | 2022-02-25 |  | 2022-08-19 | Yes | 2023-04-21 |  | 2023-06-08 | No | 2023-06-09 |  | 2023-06-09 | No | 2024-01-08 |  | 2024-01-08 | No |  |  | 2025-08-15 |  | 0 | Yes | No | No | No
671 | 11 | 1319 | SD | 78 | SD-78 CORRIDOR REHABILITATION | In and near Oceanside, Vista, San Marcos, and Escondido, from Route 5 to North Broadway. | Rehabilitate pavement, upgrade facilities to Americans with Disabilities Act (ADA) standards, upgrade bridge rail, upgrade Transportation Management System (TMS) elements, replace damaged sign panels, upgrade safety features, and make operational improvements to reduce delay. | 6804 | Yes | 6804 | 4633 | 4633 | 4633 | No | 0 | No | 0 | 0 | 0 | 8160 | Yes | 0 | No | 0 | 0 | 0 | 816 | Yes | 0 | No | 0 | 0 | 0 | 14026 | Yes | 31 | No | 31 | 0 | 0 | 20 | No | 0 | No | 0 | 0 | 0 | 8546 | Yes | 6835 | 6835 | 4633 | 4633 | 36201 |  | 2022-03-01 | 2022-06-30 |  |  | 2023-05-03 |  | 2024-04-15 | Yes | 2023-05-17 |  | 2024-05-15 | Yes | 2023-10-02 |  | 2024-11-21 | Yes |  |  | 2029-11-20 |  | 0 | Yes | Yes | No | No
672 | 11 | 1329 | IMP | 8 | IMP BRIDGE STRUCTURE REHAB | In Imperial County, on Routes 8 and 78 at various locations. | Rehabilitation of six bridges, including painting, deck and column work. | 420 | Yes | 420 | 399 | 399 | 399 | No | 896 | Yes | 896 | 791 | 791 | 1370 | Yes | 0 | No | 0 | 0 | 0 | 0 | No | 1700 | No | 1700 | 0 | 0 | 1835 | Yes | 0 | No | 0 | 0 | 0 | 0 | No | 10189 | No | 10189 | 0 | 0 | 10189 | No | 13205 | 13205 | 1190 | 1190 | 13793 |  | 2020-03-03 | 2020-06-30 |  |  | 2021-08-13 | 2022-06-01 |  |  | 2021-11-30 | 2022-06-28 |  |  | 2022-03-17 |  | 2022-11-10 | Yes |  |  | 2024-06-06 |  | 0 | Yes | No | No | No
673 | 11 | 1336 | IMP | 8 | 11-IMP-008-BRIDGE REHABILITATION | Near Winterhaven, at Colorado River Viaduct Bridge No 58-0312L/R. | Patch spalls, polyester deck overlay, hinge bearing replacement, and joint replacement to preserve the structural integrity of two bridges. | 403 | Yes | 403 | 383 | 383 | 383 | No | 581 | Yes | 581 | 561 | 561 | 584 | Yes | 121 | Yes | 121 | 6 | 6 | 121 | No | 1612 | Yes | 806 | 0 | 0 | 1561 | No | 142 | No | 142 | 0 | 0 | 0 | No | 8309 | Yes | 4146 | 0 | 0 | 8292 | No | 11168 | 6199 | 950 | 950 | 10941 |  | 2020-01-20 | 2020-06-30 |  |  | 2020-12-28 | 2021-02-25 |  |  | 2021-02-09 | 2021-06-30 |  |  | 2021-12-15 |  | 2022-08-22 | Yes |  |  | 2023-04-04 |  | 0 | Yes | No | No | No
674 | 11 | 1339 | SD | 8 | I-8 EL CAJON BRIDGE REHAB | In La Mesa and El Cajon, at El Cajon Overhead No 57-0362 and Marshall Avenue Overhead No 57-0369. | Rehabilitate two bridge decks. | 550 | Yes | 550 | 478 | 478 | 478 | No | 1974 | Yes | 1974 | 1424 | 1424 | 2905 | Yes | 25 | Yes | 25 | 1 | 1 | 1 | No | 3880 | Yes | 3880 | 0 | 0 | 3737 | No | 15 | No | 15 | 1 | 1 | 166 | Yes | 18835 | Yes | 18835 | 0 | 0 | 19894 | Yes | 25279 | 25279 | 1904 | 1904 | 27181 |  | 2020-05-20 | 2020-06-25 |  |  | 2021-10-19 | 2021-11-18 |  |  | 2021-11-19 | 2021-11-18 |  |  | 2022-03-17 |  | 2022-08-31 | Yes |  |  | 2024-05-30 |  | 0 | Yes | No | No | No
675 | 11 | 1344 | SD | 67 | 11-SD-67 RHMA OVERLAY w/SAMI | In and near Poway, from 0.1 mile south of Lakeside Avenue to Route 78. | Rehabilitate asphalt pavement, drainage system restoration, curb ramp upgrades, guardrail upgrades, and enhance crosswalk visibility. | 807 | Yes | 807 | 243 | 243 | 243 | No | 3120 | Yes | 2910 | 2799 | 2770 | 2799 | No | 85 | Yes | 85 | 73 | 73 | 74 | No | 6030 | Yes | 5250 | 136 | 56 | 5110 | No | 326 | No | 326 | 70 | 70 | 99 | No | 37992 | Yes | 35316 | 38 | 35 | 37992 | No | 48360 | 44694 | 3359 | 3247 | 46317 |  | 2019-12-13 | 2020-01-29 |  |  | 2020-05-05 | 2020-12-21 |  |  | 2020-07-10 | 2021-01-29 |  |  | 2020-10-02 | 2022-04-21 |  |  |  |  | 2024-01-24 |  | 37992 | No | No | No | No
676 | 11 | 1350 | SD | 15 | I-15 CONCRETE LANE REPLACEMENT | In and near Escondido, from 0.2 mile south of Route 78 to 0.5 mile north of Deer Springs Road. | Rehabilitate pavement by replacing sections of the existing pavement and the outside shoulder with Continuously Reinforced Concrete Pavement (CRCP), pavement slab replacement, bridge approach slab replacement, bridge joint seal work, and sign panel replacement. | 2749 | Yes | 2749 | 1154 | 1154 | 1154 | No | 5497 | Yes | 5497 | 4888 | 4888 | 4888 | No | 200 | Yes | 200 | 3 | 3 | 3 | No | 10994 | Yes | 10994 | 0 | 0 | 10506 | No | 0 | No | 0 | 0 | 0 | 0 | No | 52228 | Yes | 52228 | 0 | 0 | 52228 | No | 71668 | 71668 | 6045 | 6045 | 68779 | 2020-06-24 | 2020-05-15 | 2020-05-04 |  |  | 2021-01-08 | 2021-03-18 |  |  | 2021-04-26 | 2021-06-30 |  |  | 2022-03-18 | 2022-06-27 |  |  |  |  | 2024-12-20 |  | 52228 | No | No | No | No
677 | 11 | 1355 | SD | 163 | SR163 MOBILITY | In the city of San Diego, from Friars Road to Kearny Villa Road. | Upgrade Transportation Management System (TMS) elements, upgrade Weigh-In-Motion (WIM) scale, enhance highway worker safety, and make pedestrian safety improvements. | 800 | Yes | 800 | 789 | 789 | 789 | No | 1180 | Yes | 1180 | 102 | 102 | 1209 | Yes | 0 | No | 0 | 0 | 0 | 0 | No | 1715 | No | 1715 | 0 | 0 | 1608 | No | 1 | No | 1 | 0 | 0 | 0 | No | 9033 | No | 9033 | 0 | 0 | 7297 | No | 12729 | 12729 | 891 | 891 | 10903 |  | 2022-02-18 | 2022-04-28 |  |  | 2023-05-17 |  | 2023-05-17 | No | 2023-06-28 |  | 2023-06-28 | No | 2023-11-30 |  | 2023-11-30 | No |  |  | 2025-06-26 |  | 0 | No | No | No | No
678 | 11 | 1433 | SD | 905 | OTAY MESA CVEF SCALE | Near San Diego, at the Otay Mesa Commercial Vehicle Enforcement Facility (CVEF). | Add new inspection lane and truck weighing system to reduce delay and emissions from idling vehicles. | 3631 | No | 3631 | 181 | 181 | 181 | No | 300 | Yes | 300 | 276 | 276 | 314 | Yes | 50 | No | 50 | 0 | 0 | 50 | No | 1222 | Yes | 1222 | 0 | 0 | 1169 | No | 0 | No | 0 | 0 | 0 | 0 | No | 6234 | Yes | 6234 | 0 | 0 | 6234 | No | 11437 | 11437 | 457 | 457 | 7948 |  |  | 2022-01-25 |  |  |  | 2022-03-01 |  |  |  | 2022-03-16 |  |  |  |  | 2022-10-28 |  |  |  | 2024-07-26 |  | 0 | No | No | No | No
679 | 11 | 1434 | SD | 5 | I-5 ASSET MGMT SPLIT | In the cities of San Diego, Chula Vista, and National City from Camino De La Plaza to 0.3 mile south of Via De La Valle. | Rehabilitate pavement, drainage, and signs, upgrade Transportation Management System (TMS) elements, and upgrade facilities to Americans with Disabilities Act (ADA) standards. | 3631 | No | 3631 | 3100 | 3100 | 3100 | No | 6415 | Yes | 6415 | 857 | 857 | 5698 | No | 780 | Yes | 780 | 0 | 0 | 737 | No | 12305 | No | 12305 | 0 | 0 | 11125 | No | 349 | No | 349 | 0 | 0 | 349 | No | 80379 | No | 80379 | 0 | 0 | 79623 | No | 103859 | 103859 | 3957 | 3957 | 100632 |  | 2021-10-29 | 2022-01-25 |  |  | 2023-06-23 |  | 2023-06-23 | No | 2023-06-29 |  | 2023-06-29 | No | 2023-12-21 |  | 2023-12-21 | No |  |  | 2025-01-31 |  | 0 | No | Yes | No | Yes
680 | 11 | 1467 | SD | 5 | REPAIR BRIDGE DECK | In Chula Vista and San Diego, at Palomar Street Overcrossing No 57-0354, Route 5/163 Separation No 57-0391, and De Anza offramp Undercrossing No 57-0287L. | Apply polyester concrete overlay to bridge decks, apply methacrylate to approach slabs, and repair spalls. (Bridge Deck Preservation). | 300 | Yes | 300 | 94 | 94 | 94 | No | 500 | No | 500 | 0 | 0 | 536 | Yes | 0 | No | 0 | 0 | 0 | 0 | No | 800 | No | 800 | 0 | 0 | 756 | No | 0 | No | 0 | 0 | 0 | 0 | No | 4203 | No | 4203 | 0 | 0 | 4203 | No | 5803 | 5803 | 94 | 94 | 5589 |  |  | 2022-06-30 |  |  |  |  | 2023-07-15 |  |  |  | 2023-08-01 |  |  |  | 2024-02-01 |  |  |  | 2024-10-01 |  | 0 | No | No | No | No
681 | 11 | 1468 | SD | 125 | SR125 AND SR52 BRIDGE PRESERVATION | In La Mesa, at Panorama Drive Undercrossing No 57-0309; also in the city of San Diego at San Diego River - Hollins Lake Bridge No 57-0983R. | Apply polyester concrete overlay to bridge decks, apply methacrylate to approach slabs, and repair spalls. (Bridge Deck Preservation). | 250 | Yes | 250 | 155 | 155 | 155 | No | 400 | No | 400 | 0 | 0 | 429 | Yes | 0 | No | 0 | 0 | 0 | 0 | No | 650 | No | 650 | 0 | 0 | 613 | No | 0 | No | 0 | 0 | 0 | 0 | No | 2100 | No | 2100 | 0 | 0 | 2100 | No | 3400 | 3400 | 155 | 155 | 3297 |  |  | 2022-06-30 |  |  |  |  | 2023-07-15 |  |  |  | 2023-08-01 |  |  |  | 2024-02-01 |  |  |  | 2024-10-01 |  | 0 | No | No | No | No
682 | 12 | 1203 | ORA | Var | 12-0Q690 detection system rehab. | On various locations, at various routes. | Replace and upgrade existing field elements for the Traffic Management System (TMS). | 0 | No | 0 | 0 | 0 | 0 | No | 2060 | Yes | 2060 | 1936 | 1936 | 1936 | No | 0 | No | 0 | 0 | 0 | 0 | No | 2052 | Yes | 2052 | 1248 | 1248 | 1997 | No | 24 | No | 24 | 0 | 0 | 6 | No | 5854 | Yes | 5854 | 3708 | 3708 | 5854 | No | 9990 | 9990 | 6892 | 6892 | 9793 |  | 2017-06-22 | 2017-06-22 |  |  | 2020-02-01 | 2020-01-30 |  |  | 2020-05-01 | 2020-03-13 |  |  | 2021-01-01 | 2020-08-27 |  |  |  |  | 2022-09-01 |  | 5854 | No | No | No | No
683 | 12 | 1204 | ORA | Var | 12-0Q930 Bridge Project on Route 5 and 133 | In Orange County, on Routes 5, 133, and 241 at various locations. | Rehabilitate 25 bridges. | 1215 | Yes | 1215 | 1203 | 1203 | 1203 | No | 2600 | Yes | 2600 | 2547 | 2547 | 2547 | No | 155 | Yes | 155 | 26 | 26 | 149 | No | 4166 | Yes | 4166 | 35 | 35 | 4139 | No | 77 | No | 77 | 2 | 2 | 77 | No | 16966 | Yes | 16966 | 0 | 0 | 16966 | No | 25179 | 25179 | 3813 | 3813 | 25081 |  | 2020-03-02 | 2020-01-30 |  |  | 2021-08-01 | 2021-10-28 |  |  | 2021-10-01 | 2021-11-24 |  |  | 2022-05-02 | 2022-06-21 |  |  |  |  | 2023-11-01 |  | 16966 | No | No | No | No
684 | 12 | 2246 | ORA | 1 | 12-0H150 PCH Laguna Beach Rehabilitate Pavement & ADA upgrades | In Laguna Beach, from Vista Del Sol to 7th Avenue; also from Ledroit Street to 0.1 mile north of Newport Coast Drive (PM 10.5/14.057). | Remove and replace existing pavement with Rubberized Hot Mix Asphalt (RHMA). | 0 | No | 0 | 0 | 0 | 0 | No | 3720 | Yes | 3720 | 3669 | 3669 | 3669 | No | 1 | No | 1 | 0 | 0 | 0 | No | 1900 | Yes | 1900 | 1846 | 1846 | 2004 | Yes | 65 | No | 65 | 22 | 22 | 65 | No | 7152 | Yes | 7152 | 6729 | 6729 | 7152 | No | 12838 | 12838 | 12266 | 12266 | 12890 |  | 2005-08-30 | 2005-08-30 |  |  | 2020-05-01 | 2020-02-28 |  |  | 2020-06-01 | 2020-05-08 |  |  | 2021-01-04 | 2020-09-24 |  |  |  |  | 2022-11-15 |  | 7152 | No | No | No | No
685 | 12 | 2257 | ORA | 001 | 12-0P69U Rte 1 Upgrade ADA curb ramps, widen sidewalk | In Orange County in Laguna Beach, on Route 1 From 7th Avenue To Ruby Street | Upgrade ADA in NB and SB of SR-1 | 1800 | No | 0 | 1756 | 0 | 1757 | No | 5220 | No | 5100 | 5157 | 5103 | 5237 | Yes | 3000 | No | 3000 | 2187 | 2187 | 2188 | No | 3915 | No | 3900 | 0 | 0 | 4090 | Yes | 3121 | No | 3121 | 928 | 928 | 0 | No | 12758 | No | 12643 | 0 | 0 | 0 | No | 29814 | 27764 | 10028 | 8218 | 13272 | [6 empty] | 2021-12-15 |  |  |  | 2022-01-21 |  |  |  |  | 2022-09-07 |  |  |  | 2025-07-01 |  | 0 | No | No | No | No
686 | 12 | 2300 | ORA | 001 | 12-0M82U Rte 001 Upgrade to ADA Standards & CAPM | In Orange County In Laguna Beach, on State Route 1 (also known as Pacific Coast Highway or SR-1) From Ruby Street (PM 7.9) To Ledroit Street (PM 10.5) | Upgrade Sidewalk to Americans with Disabilities Act Standards and Rehabilitate Pavement | 1500 | Yes | 1500 | 1435 | 1424 | 1435 | No | 2530 | Yes | 2530 | 2527 | 2527 | 2527 | No | 3230 | Yes | 3230 | 1660 | 1660 | 1660 | No | 2850 | Yes | 2850 | 892 | 892 | 2810 | No | 3100 | No | 3100 | 1480 | 1480 | 0 | No | 11321 | Yes | 11321 | 1320 | 1320 | 11321 | No | 24531 | 24531 | 9314 | 9303 | 19753 | 2019-03-14 | 2018-01-18 | 2018-01-18 |  |  | 2020-06-01 |  |  |  | 2020-06-01 |  |  |  | 2021-01-02 | 2021-02-18 |  |  |  |  | 2023-11-01 |  | 11320 | No | No | No | No
687 | 12 | 2330A | ORA | 001 | 12-0P68U, Rte 1, Upgrade Traffic Signals,Resurface Lanes,ADA | In Orange County at Various Locations from Crystal Heights Dr. to the Los Angeles/Orange County Line | Upgrade traffic signals, upgrade curb ramps to ADA standards, delineate Class II bike lanes and upgrade crosswalk, 14.9 miles of combined estimate | 3611 | No | 3611 | 2835 | 2835 | 2838 | No | 7981 | No | 7981 | 7679 | 7679 | 7698 | No | 2962 | No | 2962 | 2070 | 2070 | 2073 | No | 6700 | No | 6700 | 0 | 0 | 6055 | No | 1248 | No | 1248 | 483 | 483 | 0 | No | 27176 | No | 27176 | 0 | 0 | 24729 | No | 49678 | 49678 | 13067 | 13067 | 43393 |  | 2019-01-05 |  |  |  | 2021-05-15 |  |  |  | 2021-05-30 |  |  |  | 2022-01-30 |  | 2022-11-14 | Yes |  |  | 2025-05-23 |  | 0 | Yes | No | No | No
688 | 12 | 2374 | ORA | 1 | 12-0R410 PCH at Newport Beach CAPM w ADA & FO | In Newport Beach, from Jamboree Road to Santa Ana River Bridge. | Pavement rehabilitation. | 1980 | Yes | 1980 | 1501 | 1501 | 1501 | No | 3000 | Yes | 3000 | 2932 | 2932 | 3007 | Yes | 1045 | Yes | 1045 | 538 | 538 | 990 | No | 2438 | No | 2438 | 0 | 0 | 1983 | No | 630 | No | 630 | 130 | 130 | 221 | No | 11200 | No | 11200 | 0 | 0 | 10437 | No | 20293 | 20293 | 5101 | 5101 | 18139 |  | 2019-10-01 | 2019-10-31 |  |  | 2021-11-30 | 2022-04-20 |  |  | 2021-11-30 | 2022-05-03 |  |  | 2022-05-26 |  | 2022-11-14 | Yes |  |  | 2024-04-01 |  | 0 | Yes | No | No | No
689 | 12 | 2530N | ORA | 5 | 12-0R200 Interstate 5 Pavement Rehabilitation Project | In San Clemente, from the San Diego County line to 0.4 mile north of El Camino Real. | Pavement rehabilitation and upgrade safety devices. | 2569 | Yes | 2569 | 1459 | 1459 | 1459 | No | 3442 | Yes | 3442 | 3340 | 3340 | 3340 | No | 0 | No | 0 | 0 | 0 | 0 | No | 3849 | Yes | 3849 | 13 | 13 | 3759 | No | 0 | No | 0 | 0 | 0 | 0 | No | 20410 | Yes | 20410 | 42 | 42 | 20410 | No | 30270 | 30270 | 4854 | 4854 | 28968 |  | 2019-10-15 | 2019-12-20 |  |  | 2021-06-01 | 2021-11-15 |  |  | 2021-07-01 | 2021-11-30 |  |  | 2022-04-01 | 2022-05-12 |  |  |  |  | 2024-05-01 |  | 20410 | No | No | No | No
690 | 12 | 2531H | ORA | 5 | 12-0R970 I-5 South SD Co to Rt 74 Multi Asset Project | In San Clemente, Dana Point, and San Juan Capistrano, from the San Diego County line to north of Route 74. | Rehabilitate pavement, enhance highway worker safety, upgrade bridge rail, overhead sign structure, and lighting, restore drainage systems, construct stormwater treatment Best Management Practices (BMPs), and upgrade facilities to Americans with Disabilities Act (ADA) standards. | 2140 | Yes | 2140 | 4 | 4 | 2042 | No | 3320 | No | 3320 | 0 | 0 | 3259 | No | 0 | No | 0 | 0 | 0 | 0 | No | 3675 | No | 3675 | 0 | 0 | 3536 | No | 710 | No | 710 | 0 | 0 | 693 | No | 20255 | No | 20255 | 0 | 0 | 20255 | No | 30100 | 30100 | 4 | 4 | 29785 |  |  |  | 2023-10-18 |  |  |  | 2025-06-17 |  |  |  | 2025-07-15 |  |  |  | 2026-04-15 |  |  |  | 2027-10-12 |  | 0 | No | No | No | No
691 | 12 | 2563 | ORA | 5 | 12-0P700 Rt 5, Drainage restoration Segunda Deshecha Channel | In San Clemente, adjacent to northbound Avenida Pico offramp. | Restore hydraulic capacity of channel by repairing concrete panels in channel slope and bottom. | 550 | Yes | 550 | 505 | 505 | 505 | No | 1145 | Yes | 1145 | 969 | 969 | 969 | No | 111 | Yes | 111 | 61 | 61 | 103 | No | 1386 | Yes | 1386 | 624 | 624 | 1279 | No | 125 | No | 125 | 15 | 15 | 125 | No | 3254 | Yes | 3254 | 2373 | 2373 | 3254 | No | 6571 | 6571 | 4547 | 4547 | 6235 |  | 2019-03-01 | 2019-03-01 |  |  | 2020-05-01 | 2020-05-26 |  |  | 2020-06-01 | 2020-06-10 |  |  | 2020-12-11 | 2020-11-17 |  |  |  |  | 2023-12-18 |  | 3254 | No | No | No | No
692 | 12 | 2590A | ORA | 5 | 12-0S051, Rte 5, Multi Asset from I-405 to Yale Ave. OC | In and near Irvine, from Route 405 to Yale Avenue. | Rehabilitate roadway and drainage systems, enhance highway worker safety, replace roadside sign panels, and construct stormwater treatment Best Management Practices (BMPs). | 1120 | Yes | 1120 | 11 | 11 | 1103 | No | 2040 | No | 2040 | 0 | 0 | 1938 | No | 0 | No | 0 | 0 | 0 | 0 | No | 4310 | No | 4310 | 0 | 0 | 4279 | No | 10 | No | 10 | 0 | 0 | 0 | No | 24635 | No | 24635 | 0 | 0 | 24635 | No | 32115 | 32115 | 11 | 11 | 31955 |  |  |  | 2023-04-06 |  |  |  | 2024-10-01 |  |  |  | 2024-12-04 |  |  |  | 2025-07-26 |  |  |  | 2027-01-05 |  | 0 | No | No | No | No
693 | 12 | 2590B | ORA | 5 | 12-0S052, Rte5, Multi Asset Project from Yale Ave OC to SR55 | In and near Irvine and Tustin, from Yale Avenue to Route 55. | Rehabilitate roadway and drainage systems, enhance highway worker safety, and install census stations. | 760 | Yes | 760 | 10 | 10 | 751 | No | 1850 | No | 1850 | 0 | 0 | 1817 | No | 0 | No | 0 | 0 | 0 | 0 | No | 3340 | No | 3340 | 0 | 0 | 3268 | No | 0 | No | 0 | 0 | 0 | 0 | No | 13189 | No | 13189 | 0 | 0 | 13189 | No | 19139 | 19139 | 10 | 10 | 19025 |  |  |  | 2023-02-09 |  |  |  | 2024-02-06 |  |  |  | 2024-07-01 |  |  |  | 2025-03-18 |  |  |  | 2027-12-28 |  | 0 | No | No | No | No
694 | 12 | 2676A | ORA | 5 | 12-0S380, Rte 5, RT 74 to RT 405 Multi-Asset Project | In San Juan Capistrano, Mission Viejo, Laguna Niguel, and Irvine, from north of Route 74 to Route 405. | Rehabilitate pavement and drainage systems, upgrade lighting, enhance highway worker safety, replace overhead sign panels, and construct bicycle and pedestrian improvements. | 4550 | Yes | 4550 | 8 | 8 | 4482 | No | 4570 | No | 4570 | 0 | 0 | 4448 | No | 0 | No | 0 | 0 | 0 | 0 | No | 5730 | No | 5730 | 0 | 0 | 5713 | No | 0 | No | 0 | 0 | 0 | 0 | No | 39150 | No | 39150 | 0 | 0 | 39150 | No | 54000 | 54000 | 8 | 8 | 53793 |  |  |  | 2023-10-18 |  |  |  | 2025-04-15 |  |  |  | 2025-05-15 |  |  |  | 2026-02-10 |  |  |  | 2027-08-10 |  | 0 | No | No | No | No
695 | 12 | 2834B | ORA | 5 | 12-0S500, Rte 5, Multi Asset Project 55 to LA County | In and near the cities of Tustin, Santa Ana, Orange, Anaheim, Fullerton, and Buena Park, from Route 55 to the Los Angeles County line. | Rehabilitate roadway and drainage systems, upgrade guardrail and pump plant, enhance highway worker safety, replace overhead sign panels, and upgrade facilities to Americans with Disabilities Act (ADA) standards. | 2680 | Yes | 2680 | 25 | 25 | 2473 | No | 4350 | No | 4350 | 0 | 0 | 4215 | No | 0 | No | 0 | 0 | 0 | 0 | No | 5080 | No | 5080 | 0 | 0 | 4791 | No | 4 | No | 4 | 0 | 0 | 4 | No | 31126 | No | 31126 | 0 | 0 | 31126 | No | 43240 | 43240 | 25 | 25 | 42609 |  |  |  | 2023-12-13 |  |  |  | 2025-12-17 |  |  |  | 2026-02-16 |  |  |  | 2026-12-03 |  |  |  | 2028-02-03 |  | 0 | No | No | No | No
696 | 12 | 2859B | ORA | Var | 12-0P42U I-5, SR57, & SR 91 ICM123 Project combined with ICM 1,2, & 3 | In the cities of Orange, Anaheim, Santa Ana, Fullerton and Buena Park on Route 5, from PM 33.0 to PM 43.2; also on Route 57, from PM 10.7L to PM 16.6; also on Route 91, from PM R2.6 to PM R4.084L and PM 0.410 to PM 7.2. | Install and modify Intelligent Transportation System (ITS) elements. | 1655 | Yes | 1655 | 3072 | 3072 | 3072 | Yes | 2520 | Yes | 2520 | 5009 | 5009 | 5009 | Yes | 320 | No | 320 | 9 | 9 | 9 | No | 4715 | Yes | 4715 | 2466 | 2466 | 4021 | No | 24 | No | 24 | 0 | 0 | 0 | No | 20456 | Yes | 20456 | 10182 | 10182 | 20456 | No | 29690 | 29690 | 20738 | 20738 | 32567 | 2018-10-17 | 2018-06-19 | 2018-06-19 |  |  | 2020-03-18 | 2020-03-18 |  |  | 2020-05-01 | 2020-05-01 |  |  | 2021-01-04 | 2020-10-02 |  |  |  |  | 2024-02-01 |  | 20456 | No | No | No | No
697 | 12 | 2859C | ORA | Var | 12-0P671 Integrated Corridor Mgmt on 3 State Route | In Orange County, on Routes 5, 22, 55, 57, 91, and 405 at various locations. | Develop Information Technology (IT) and Information Exchange Network (IEN) to support the Orange County Triangle (Routes 5, 57, and 91) Integrated Corridor Management (ICM). | 2380 | Yes | 2380 | 947 | 947 | 947 | No | 4343 | Yes | 4343 | 1701 | 1701 | 1701 | No | 320 | Yes | 320 | 6 | 6 | 6 | No | 2990 | Yes | 2990 | 1323 | 1323 | 2864 | No | 0 | No | 0 | 0 | 0 | 0 | No | 8888 | Yes | 8888 | 332 | 332 | 8888 | No | 18921 | 18921 | 4309 | 4309 | 14406 | 2018-12-06 | 2018-11-01 | 2018-11-19 |  |  | 2020-04-15 | 2020-04-14 |  |  | 2020-05-01 | 2020-05-01 |  |  | 2021-02-01 | 2020-09-02 |  |  |  |  | 2024-02-01 |  | 8888 | No | No | No | No
698 | 12 | 2948 | ORA | 22 | 12-0N920 WB Rte 22 Haster Off - Upgrade Drainage | In Garden Grove, at Haster Street westbound offramp. | Upgrade drainage system. | 420 | Yes | 420 | 405 | 405 | 405 | No | 720 | Yes | 720 | 706 | 706 | 706 | No | 233 | Yes | 233 | 194 | 194 | 227 | No | 556 | Yes | 556 | 405 | 405 | 589 | Yes | 326 | No | 326 | 4 | 4 | 326 | No | 1279 | Yes | 1279 | 627 | 627 | 1279 | No | 3534 | 3534 | 2341 | 2341 | 3532 |  | 2017-08-01 | 2017-08-01 |  |  | 2019-04-01 | 2019-03-28 |  |  | 2019-05-01 | 2019-04-29 |  |  | 2020-01-02 | 2019-10-04 |  |  |  |  | 2023-08-04 |  | 1096 | No | No | No | No
699 | 12 | 2982 | ORA | 22 | 12-0S080 Rte 22, Maintenance Facility & TMS | In and near the cities of Santa Ana and Orange, from west of Cambridge Street to Route 55; also at the Orange Maintenance Station at 691 South Tustin Street. | Upgrade and install new Transportation Management System (TMS) elements, reconstruct buildings at the Orange Maintenance Station, and construct bicycle and pedestrian improvements. | 1383 | Yes | 1383 | 7 | 7 | 1375 | No | 2950 | No | 2950 | 0 | 0 | 2907 | No | 0 | No | 0 | 0 | 0 | 0 | No | 3450 | No | 3450 | 0 | 0 | 3404 | No | 0 | No | 0 | 0 | 0 | 0 | No | 19800 | No | 19800 | 0 | 0 | 19797 | No | 27583 | 27583 | 7 | 7 | 27483 |  |  |  | 2023-11-17 |  |  |  | 2026-01-06 |  |  |  | 2026-02-05 |  |  |  | 2026-09-03 |  |  |  | 2029-02-19 |  | 0 | No | No | No | No
700 | 12 | 3102A | ORA | 241 | 12-0Q980 SR 241 SB-1 Bridge, TMS & Roadside | In Rancho Santa Margarita, Mission Viejo, Lake Forest, and Irvine, from Oso Parkway (PM 14.545) to 0.7 mile north of Portola Parkway. | Rehabilitate Trabuco Creek Bridge No 55-0700R/L, upgrade Transportation Management System (TMS) elements, upgrade safety devices, and improve highway worker safety. | 1641 | Yes | 1641 | 1591 | 1591 | 1591 | No | 2954 | Yes | 2954 | 970 | 970 | 2893 | No | 0 | No | 0 | 0 | 0 | 0 | No | 2900 | No | 2900 | 0 | 0 | 2114 | No | 0 | No | 0 | 0 | 0 | 0 | No | 16583 | No | 16583 | 0 | 0 | 16582 | No | 24078 | 24078 | 2561 | 2561 | 23180 |  | 2021-10-08 | 2021-10-07 |  |  | 2022-10-03 |  | 2023-02-20 | Yes | 2023-03-08 |  | 2023-03-08 | No | 2023-09-07 |  | 2023-09-01 | No |  |  | 2025-03-14 |  | 0 | No | No | No | No
701 | 12 | 3402B | ORA | 55 | 12-0R320 Rte 55 Multi-Asset Project | In Newport Beach, Costa Mesa, Santa Ana, Tustin, Orange, and Anaheim, from Route 1 to Route 91. | Rehabilitate pavement, rehabilitate drainage, upgrade lighting, rehabilitate bridge rail, rehabilitate landscaping, upgrade Transportation Management System (TMS) elements, add bike and pedestrian improvements as complete streets elements, and improve highway worker safety. (G13 Contingency). | 5700 | Yes | 5700 | 5564 | 5564 | 5564 | No | 7900 | Yes | 7900 | 797 | 797 | 8870 | Yes | 0 | No | 0 | 0 | 0 | 0 | No | 0 | No | 0 | 0 | 0 | 8909 | Yes | 61 | No | 61 | 1 | 1 | 36 | No | 0 | No | 0 | 0 | 0 | 75508 | Yes | 13661 | 13661 | 6362 | 6362 | 98887 |  | 2022-02-28 | 2022-06-30 |  |  | 2024-03-01 |  | 2024-03-01 | No | 2024-06-07 |  | 2024-06-07 | No | 2024-12-04 |  | 2024-12-04 | No |  |  | 2026-07-01 |  | 0 | No | Yes | No | No
702 | 12 | 3450A | ORA | 55 | 12-0Q390 Bridge Seismic Restoration | In Costa Mesa, at the Route 55/73 Connector Overcrossing Bridge No 55-538F (PM 4.74). | Seismic restoration. | 1048 | Yes | 1048 | 884 | 884 | 884 | No | 2279 | Yes | 2279 | 2220 | 2220 | 2220 | No | 11 | No | 11 | 0 | 0 | 0 | No | 2750 | Yes | 2750 | 1040 | 1040 | 2732 | No | 0 | No | 0 | 0 | 0 | 0 | No | 6054 | Yes | 6054 | 1484 | 1484 | 6054 | No | 12142 | 12142 | 5628 | 5628 | 11890 |  | 2020-04-15 | 2020-04-06 |  |  | 2021-03-15 | 2021-02-05 |  |  | 2021-05-28 | 2021-04-28 |  |  | 2021-12-30 | 2021-10-05 |  |  |  |  | 2023-10-02 |  | 6054 | No | No | No | No
703 | 12 | 3759A | ORA | 57 | 12-0T120 Deck spall repairs and polyester concrete overlay | In Anaheim, at Stadium Overhead No 55-0399. | Apply polyester concrete overlay to bridge deck and repair spalls. (Bridge Deck Preservation). | 171 | Yes | 171 | 149 | 149 | 149 | No | 463 | Yes | 443 | 0 | 0 | 390 | No | 0 | No | 0 | 0 | 0 | 0 | No | 720 | No | 720 | 0 | 0 | 590 | No | 0 | No | 0 | 0 | 0 | 0 | No | 2294 | No | 2294 | 0 | 0 | 1850 | No | 3648 | 3628 | 149 | 149 | 2979 |  |  | 2022-06-06 |  |  |  |  | 2023-02-13 |  |  |  | 2023-03-01 |  |  |  | 2023-09-01 |  |  |  | 2024-12-13 |  | 0 | No | No | No | No
704 | 12 | 3959 | ORA | Var | 12-0R560 VAR Connector Rehab project. | In the cities of Santa Ana, Tustin, Irvine, Costa Mesa, Laguna Niguel and Anaheim on various routes. | Rehabilitate pavement by repairing broken concrete slabs and replacing asphalt concrete with Rubberized Hot Mix Asphalt (RHMA-G) at 16 connectors, two ramps and one freeway segment. (G13 Contingency). | 3250 | Yes | 3250 | 3043 | 3043 | 3043 | No | 5400 | Yes | 5400 | 4802 | 4802 | 5519 | Yes | 0 | No | 0 | 0 | 0 | 0 | No | 5500 | Yes | 5500 | 0 | 0 | 5928 | Yes | 0 | No | 0 | 0 | 0 | 0 | No | 27030 | Yes | 27030 | 0 | 0 | 27773 | Yes | 41180 | 41180 | 7845 | 7845 | 42263 | 2021-01-28 | 2020-09-30 | 2020-09-30 |  |  | 2022-04-01 | 2022-03-09 |  |  | 2022-05-01 | 2022-05-03 |  |  | 2022-11-01 |  | 2022-09-30 | No |  |  | 2024-10-02 |  | 0 | No | Yes | No | No
705 | 12 | 4080 | ORA | 73 | 12-0R340 RT 73 bridge decks and rehab approach slabs | In and near Laguna Hills, Laguna Niguel, Laguna Beach, Irvine, Newport Beach, and Costa Mesa from Moulton Parkway to Bristol Street. | Rehabilitate bridge decks, bridge joints and approach slabs to preserve service life on ten bridges. | 494 | Yes | 494 | 472 | 472 | 472 | No | 1488 | Yes | 1488 | 1427 | 1427 | 1427 | No | 0 | No | 0 | 0 | 0 | 0 | No | 1150 | Yes | 1150 | 346 | 346 | 1147 | No | 5 | No | 5 | 0 | 0 | 0 | No | 2051 | Yes | 2051 | 127 | 127 | 2051 | No | 5188 | 5188 | 2372 | 2372 | 5097 |  | 2020-04-02 | 2020-06-30 |  |  | 2021-07-02 | 2021-02-23 |  |  | 2021-08-02 | 2021-04-27 |  |  | 2022-06-01 | 2021-10-19 |  |  |  |  | 2023-06-01 |  | 2051 | No | No | No | No
706 | 12 | 4506F | ORA | 91 | 12-0R311 State Route 91 Multi-Asset Project | In La Palma, Buena Park, Anaheim, and Fullerton, from the Los Angeles County line to Acacia Street; also in Los Angeles County in the city of Los Angeles from 0.1 mile east of Carmenita Road to the Orange County line (PM R20.6/R20.7). | Rehabilitate pavement, rehabilitate culverts, upgrade lighting, upgrade Transportation Management System (TMS) elements and make highway worker safety improvements. (G13 Contingency). | 2150 | Yes | 2150 | 1927 | 1927 | 1927 | No | 3560 | Yes | 3560 | 47 | 47 | 3547 | No | 540 | Yes | 540 | 1 | 1 | 538 | No | 0 | No | 0 | 0 | 0 | 4293 | Yes | 264 | No | 264 | 0 | 0 | 264 | No | 0 | No | 0 | 0 | 0 | 38442 | Yes | 6514 | 6514 | 1975 | 1975 | 49011 | 2022-01-26 | 2021-10-29 | 2021-10-29 |  |  | 2024-03-01 |  | 2024-03-01 | No | 2024-03-29 |  | 2024-03-29 | No | 2024-12-02 |  | 2024-12-02 | No |  |  | 2027-12-01 |  | 0 | No | Yes | No | No
707 | 12 | 4506G | ORA | 91 | 12-0R312, Rte 091, Multi-Asset Project | In Anaheim and Placentia, from Acacia Street to La Palma Avenue. | Rehabilitate pavement, rehabilitate culverts, upgrade lighting, upgrade Transportation Management System (TMS) elements and make highway worker safety improvements. (G13 Contingency). | 885 | Yes | 885 | 777 | 777 | 777 | No | 1600 | Yes | 1600 | 321 | 321 | 1599 | No | 20 | Yes | 20 | 2 | 2 | 17 | No | 0 | No | 0 | 0 | 0 | 2009 | Yes | 0 | No | 0 | 0 | 0 | 4 | Yes | 0 | No | 0 | 0 | 0 | 20036 | Yes | 2505 | 2505 | 1100 | 1100 | 24442 |  | 2021-06-30 | 2021-06-30 |  |  | 2023-11-30 |  | 2023-11-30 | No | 2024-02-01 |  | 2024-02-06 | No | 2024-08-01 |  | 2024-08-01 | No |  |  | 2028-07-03 |  | 0 | No | Yes | No | No
708 | 12 | 4506H | ORA | 91 | 12-0R313, Rte 091, Multi-Asset Project | In and near Anaheim, from La Palma Avenue to Route 55. | Rehabilitate pavement, rehabilitate culverts, upgrade lighting, upgrade Transportation Management System (TMS) elements and make highway worker safety improvements. (G13 Contingency). | 2070 | Yes | 2070 | 1337 | 1337 | 1337 | No | 2660 | Yes | 2660 | 862 | 862 | 2666 | Yes | 20 | Yes | 20 | 2 | 2 | 17 | No | 0 | No | 0 | 0 | 0 | 3408 | Yes | 9 | No | 9 | 0 | 0 | 9 | No | 0 | No | 0 | 0 | 0 | 5525 | Yes | 4759 | 4759 | 2201 | 2201 | 12962 | 2021-10-13 | 2021-06-30 | 2021-06-30 |  |  | 2023-12-29 |  | 2023-12-29 | No | 2024-01-31 |  | 2024-01-17 | No | 2024-06-28 |  | 2024-06-28 | No |  |  | 2027-11-01 |  | 0 | No | Yes | No | No
709 | 12 | 4506I | ORA | 91 | 12-0R314, Rte 091, Multi-Asset Project | In Anaheim, from Route 55 to 0.7 mile west of Route 90. | Upgrade Transportation Management System (TMS) elements, upgrade lighting, and make highway worker safety improvements. (G13 Contingency). | 430 | Yes | 430 | 430 | 430 | 430 | No | 600 | Yes | 600 | 493 | 493 | 696 | Yes | 20 | Yes | 20 | 2 | 2 | 17 | No | 0 | No | 0 | 0 | 0 | 458 | Yes | 4 | No | 4 | 0 | 0 | 4 | No | 0 | No | 0 | 0 | 0 | 37060 | Yes | 1054 | 1054 | 925 | 925 | 38665 |  | 2021-06-30 | 2021-06-30 |  |  | 2023-05-01 |  | 2023-05-11 | No | 2023-07-03 |  | 2023-07-28 | No | 2023-12-01 |  | 2024-01-11 | No |  |  | 2026-01-02 |  | 0 | No | Yes | No | No
710 | 12 | 4506J | ORA | 91 | 12-0R315, Rte 091, Multi-Asset Project | In Anaheim, from 0.7 mile west of Route 90 to Riverside County line (PM 18.905). | Upgrade Transportation Management System (TMS) elements, rehabilitate culverts, upgrade lighting, and make highway worker safety improvements. (G13 Contingency). | 900 | Yes | 900 | 853 | 853 | 853 | No | 1140 | Yes | 1140 | 27 | 27 | 1136 | No | 23 | Yes | 23 | 1 | 1 | 23 | No | 0 | No | 0 | 0 | 0 | 1081 | Yes | 668 | No | 668 | 0 | 0 | 668 | No | 0 | No | 0 | 0 | 0 | 11193 | Yes | 2731 | 2731 | 881 | 881 | 14954 |  | 2021-10-29 | 2021-10-29 |  |  | 2024-03-01 |  | 2024-03-01 | No | 2024-03-29 |  | 2024-03-29 | No | 2024-12-02 |  | 2024-12-02 | No |  |  | 2027-12-01 |  | 0 | No | Yes | No | No
711 | 12 | 4794 | ORA | 133 | 12-0P94U SR-133 Widening and Drainage Improvement | In Orange County, in the City of Laguna Beach, from 0.2 mile south of El Toro Road to Route 73/133 Separation | Roadway widening, restriping and drainage work | 4102 | No | 2828 | 4034 | 2772 | 4039 | No | 6314 | No | 3857 | 5572 | 3122 | 5572 | No | 2148 | No | 1565 | 955 | 596 | 955 | No | 4453 | No | 3297 | 575 | 407 | 4450 | No | 6540 | No | 3531 | 4055 | 2961 | 6165 | No | 9432 | No | 5058 | 464 | 249 | 9432 | No | 32989 | 20136 | 15655 | 10107 | 30613 | [6 empty] | 2020-06-02 |  |  |  | 2020-06-17 |  |  |  | 2021-03-11 |  |  |  |  | 2029-03-01 |  | 9431 | No | No | No | No
712 | 12 | 5040B | ORA | 405 | 12-0R330, Rte 405 Multi-Objective Asset Management Project | In and near Costa Mesa, Fountain Valley, Huntington Beach, and Westminster, from Harbor Boulevard to south of McFadden Avenue. | Rehabilitate pavement and drainage systems, and add traffic census stations. | 617 | Yes | 617 | 48 | 48 | 604 | No | 1001 | No | 1001 | 0 | 0 | 1001 | No | 21 | No | 21 | 0 | 0 | 21 | No | 1127 | No | 1127 | 0 | 0 | 1124 | No | 0 | No | 0 | 0 | 0 | 0 | No | 9700 | No | 9700 | 0 | 0 | 9700 | No | 12466 | 12466 | 48 | 48 | 12450 |  |  |  | 2024-03-01 |  |  |  | 2025-04-01 |  |  |  | 2025-05-01 |  |  |  | 2026-01-05 |  |  |  | 2026-10-20 |  | 0 | No | No | No | No
713 | 12 | 5040D | ORA | 405 | 12-0Q970 Rte 405 (S.) Asset Management | In and near Irvine and Costa Mesa, from Route 5 to Harbor BoulevaRd Rehabilitate pavement, replace bridge approach and departure slabs, upgrade bridge railings, improve highway worker safety, upgrade safety devices, and upgrade Transportation Management System (TMS) elements. | This is a Design-Build project. (G13 Contingency). | 9700 | Yes | 9700 | 9512 | 9512 | 9512 | No | 13000 | Yes | 13000 | 1823 | 1823 | 12163 | No | 1000 | Yes | 1000 | 34 | 34 | 998 | No | 0 | No | 0 | 0 | 0 | 16926 | Yes | 634 | No | 634 | 1 | 1 | 709 | Yes | 0 | No | 0 | 0 | 0 | 150747 | Yes | 24334 | 24334 | 11370 | 11370 | 191055 | 2022-01-26 | 2021-10-21 | 2021-10-21 |  |  | 2022-08-01 |  | 2022-08-01 | No | 2022-08-01 | 2022-06-27 |  |  | 2023-09-01 |  | 2023-06-30 | No |  |  | 2026-12-01 |  | 0 | No | Yes | No | No
714 | 12 | 5094C | ORA | 405 | 12-0R570 RT 405 Multi-Asset Project | In Huntington Beach, Westminster, Garden Grove, and Seal Beach, from south of McFadden Avenue to the Los Angeles County line. | Rehabilitate pavement, improve highway worker safety, rehabilitate landscaping, and install a Weigh-In-Motion (WIM) system. (G13 Contingency). | 3146 | Yes | 3146 | 1771 | 1771 | 1771 | No | 5016 | Yes | 5016 | 463 | 463 | 4996 | No | 21 | Yes | 21 | 1 | 1 | 19 | No | 0 | No | 0 | 0 | 0 | 6400 | Yes | 0 | No | 0 | 0 | 0 | 0 | No | 0 | No | 0 | 0 | 0 | 49286 | Yes | 8183 | 8183 | 2235 | 2235 | 62472 |  | 2022-02-01 | 2022-01-31 |  |  | 2024-01-01 |  | 2024-01-12 | No | 2024-06-03 |  | 2024-06-03 | No | 2025-03-03 |  | 2025-02-01 | No |  |  | 2027-03-01 |  | 0 | No | Yes | No | No
715 | 12 | 5502 | ORA | 241 | 12-0H047 SR 241, Capital Preventive Maintenance Project | In and near Anaheim, from 0.4 mile north of Route 133 to 1.1 miles south of Route 91. | Pavement rehabilitation. | 0 | No | 0 | 0 | 0 | 0 | No | 3205 | Yes | 3205 | 3192 | 3192 | 3192 | No | 0 | No | 0 | 0 | 0 | 0 | No | 3668 | Yes | 3668 | 1155 | 1155 | 3578 | No | 0 | No | 0 | 0 | 0 | 0 | No | 15792 | Yes | 15792 | 1762 | 1762 | 15792 | No | 22665 | 22665 | 6109 | 6109 | 22562 | 2018-12-06 | 2018-08-13 | 2018-09-14 |  |  | 2021-02-26 | 2021-04-20 |  |  | 2021-04-01 | 2021-05-14 |  |  | 2021-11-30 | 2021-11-23 |  |  |  |  | 2023-08-15 |  | 15792 | No | No | No | No
EAC = Estimate at Completion
Approved = Last Commission action
** Includes all SHOPP projects with Road Maintenance and Rehabilitation Act (RMRA) funding.