## quarterly_report_attachment_1
ATTACHMENT 1
Trade Corridor Ehancement Program (TCEP) Project List
April 01 - June 30, 2022
District 02
District
| PPNO |  |  |  | Approved Budget ($1,000s) | TCEP Budget ($1,000s) | Total Expended ($1,000s) | TCEP Expended ($1,000s) |  |  | Approved Finish Date | Actual Finish Date | Current Finish Date | Award Amount ($1,000s)
County
EAC ($1,000s)
No. | Route | Title | Location and Type of Work | Phase | [5 empty] | Milestone |  |  |  |  | CAPs
1 | 02 | Fix 5 Cascade Gateway / I-5 Improvements Shasta | In Shasta County in Redding from 0.3 mile north of Cypress Avenue Undercrossing to 0.6 mile north of Oasis Road Overcrossing. | PAED | 1,600 | 0 | 1,753 | 0 | 1,753 | Baseline |  | 6/23/21 |  | 0
| 3597 |  |  | PSE | 5,849 | 1,735 | 0 | 0 | 3,954 | PAED | 8/4/20 | 8/4/20 |  |  | Cost
| SHA |  |  | RW Sup | 77 | 27 | 0 | 0 | 77 | RW Cert | 8/8/24 |  | 8/8/24
| 5 |  |  | Con Sup | 0 | 0 | 0 | 0 | 5,459 | RTL | 8/29/24 |  | 8/22/24
|  |  | Description: Provide standard vertical clearance over I-5 at the NB 273/NB 5 connector ramp. Provide improved vertical clearance under four structures at I-5 at Twin View Blvd and SR 299 crossings. Add a third mixed-flow through lane. Install high tension cable barrier and concrete barrier in the median as determined by the median width. Construct four auxiliary lanes. Widen seven bridges. Upgrade bridge rails on both sides. Place overhead signs, guide signs and warning signs as recommended by Traffic Operations. Remove and replace existing guardrail and end treatments. | RW Cap | 742 | 111 | 19 | 0 | 744 | Begin Const | 2/4/25 |  | 3/4/25
|  |  |  | Con Cap | 4,581 | 0 | 0 | 0 | 64,640 | End Const | 12/28/26 |  | 12/28/26
|  |  |  | Total | 12,849 | 1,873 | 1,772 | 0 | 76,627
District 03
District
| PPNO |  |  |  | Approved Budget ($1,000s) | TCEP Budget ($1,000s) | Total Expended ($1,000s) | TCEP Expended ($1,000s) |  |  | Approved Finish Date | Actual Finish Date | Current Finish Date | Award Amount ($1,000s)
County
EAC ($1,000s)
No. | Route | Title | Location and Type of Work | Phase | [5 empty] | Milestone |  |  |  |  | CAPs
2 | 03 | Capital Region Freight - Elkhorn | In Sacramento County, from West Elkhorn Boulevard to Crossfield Drive at Sacramento International Airport. | PAED | 1,000 | 0 | 1,000 | 0 | 1,000 | Baseline |  | 6/23/21 |  | 14,665
| 1812 |  |  | PSE | 1,000 | 0 | 496 | 0 | 496 | PAED | 4/23/21 | 4/23/21
| SAC |  |  | RW Sup | 0 | 0 | 0 | 0 | 0 | RW Cert | 7/1/21 | 8/26/21
|  |  |  | Con Sup | 0 | 0 | 0 | 0 | 0 | RTL | 11/1/21 | 1/11/22
|  |  | Construct an approximately 1 mile long 4 lane-lane roadway. Project also includes the extension of utility corridor along roadway and two roundabouts on Crossfield Dr | RW Cap | 0 | 0 | 0 | 0 | 0 | Begin Const | 3/1/22 | 4/26/22
|  |  |  | Con Cap | 24,000 | 11,000 | 1,694 | 0 | 24,000 | End Const | 12/1/22 |  | 4/28/23
|  |  |  | Total | 26,000 | 11,000 | 3,190 | 0 | 25,496
3 | 03 | Capital Region Freight - I-80 | In Placer County, from Douglas Boulevard to Riverside Avenue. | PAED | 405 | 0 | 405 | 0 | 405 | Baseline |  | 6/23/21 |  | 16,300 | Scope
| 5101A |  |  | PSE | 1,412 | 0 | 1,412 | 0 | 1,412 | PAED | 10/14/16 | 10/14/16 |  |  | Cost
| PLA |  |  | RW Sup | 115 | 0 | 115 | 0 | 115 | RW Cert | 8/31/21 | 3/30/22 |  |  | Schedule
| 80 |  |  | Con Sup | 2,955 | 2,118 | 0 | 0 | 2,955 | RTL | 4/29/22 | 4/29/22 |  |  | Benefits
|  |  | In the westbound direction, the project adds a 5th through lane on I-80 from east of Douglas Boulevard to west of Riverside Avenue in the city of Roseville. This improvement also includes reducing the existing I-80 westbound two-lane off-ramp at Douglas Boulevard to one-lane, and modifying the Douglas Boulevard on-ramps, Riverside Avenue off-ramp and northbound on-ramp to accommodate the new lane. | RW Cap | 466 | 0 | 466 | 0 | 466 | Begin Const | 11/14/22 |  | 11/14/22
|  |  |  | Con Cap | 21,545 | 14,182 | 0 | 0 | 21,545 | End Const | 3/24/25 |  | 3/24/25
|  |  |  | Total | 26,898 | 16,300 | 2,398 | 0 | 26,898
4 | 03 | Capital Region Freight - I-5 | On Interstate 5 (I-5) in Sacramento County from 0.1 mile south of Arena Blvd Interchange Interchange to 0.4 mile south of Yolo County line. | PAED | 2,000 | 0 | 0 | 0 | 0 | Baseline |  | 6/23/21 |  | 0
| 5876 |  |  | PSE | 1,900 | 1,900 | 1,564 | 1,564 | 1,921 | PAED | 4/30/21 | 4/30/21 |  |  | Cost
| SAC |  |  | RW Sup | 150 | 150 | 106 | 106 | 137 | RW Cert | 3/1/22 | 2/28/22
| 05 |  |  | Con Sup | 3,500 | 3,500 | 0 | 0 | 3,298 | RTL | 3/24/22 | 3/25/22
|  |  | Construct acceleration and deceleration merge lanes and Intelligent transportation system (ITS) infrastructure. | RW Cap | 50 | 50 | 44 | 20 | 80 | Begin Const | 9/22/22 |  | 9/22/22
|  |  |  | Con Cap | 30,100 | 30,100 | 0 | 0 | 28,099 | End Const | 3/22/24 |  | 3/22/24
|  |  |  | Total | 37,700 | 35,700 | 1,714 | 1,690 | 33,535
EAC = Estimate at Completion |  |  | CAP = Corrective Action Plan |  | Bold | Phase allocated |  |  |  | 3 to 6 months behind schedule
Approved = Last Commission action
6+ months behind schedule or delayed beyond fiscal year or EAC over budget
[14 empty] | Page 1 | of 14
ADA Notice: For individuals with sensory disabilities, this document is available in alternate formats. For alternate format information, contact the Office of Project Delivery and Workload Development at (916) 838-1157 or sb1.progress.reports@dot.ca.gov.
Trade Corridor Ehancement Program (TCEP) Project List
April 01 - June 30, 2022
District 04
District
| PPNO |  |  |  | Approved Budget ($1,000s) | TCEP Budget ($1,000s) | Total Expended ($1,000s) | TCEP Expended ($1,000s) |  |  | Approved Finish Date | Actual Finish Date | Current Finish Date | Award Amount ($1,000s)
County
EAC ($1,000s)
No. | Route | Title | Location and Type of Work | Phase | [5 empty] | Milestone |  |  |  |  | CAPs
5 | 04 | I-680/SR4 Interchange Improvements - Phases 1, 2 A | In Contra Costa County near Concord and Martinez, Phase 1 would construct a two-lane flyover direct connector from northbound I-680 to westbound SR 4 with ramp metering, remove the existing northbound I-680 to westbound SR 4 loop ramp, construct auxiliary lanes on westbound SR4 as well as northbound I-680, and add a slip ramp from northbound I-680 to Pacheco Blvd Phase 2A would extend the southbound I-680 collector-distributor ramp and install a ramp metering facility. | PAED | 0 | 0 | 0 | 0 |  | Baseline |  | 5/12/21 |  | 0 | Scope
| 0298F |  |  | PSE | 26,000 | 18,000 | 3,674 | 0 | 26,000 | PAED | 2/19/09 | 2/19/09 |  |  | Cost
| CC |  |  | RW Sup | 0 | 0 | 0 | 0 | 0 | RW Cert | 9/30/24 |  | 9/24/24 |  | Schedule
| 4,680 |  |  | Con Sup | 0 | 0 | 0 | 0 | 0 | RTL | 10/31/24 |  | 10/31/24
|  |  |  | RW Cap | 14,000 | 0 | 0 | 0 | 14,000 | Begin Const | 2/26/25 |  | 4/1/25
|  |  |  | Con Cap | 188,000 | 0 | 0 | 0 | 188,000 | End Const | 11/30/27 |  | 11/30/27
|  |  |  | Total | 228,000 | 18,000 | 3,674 | 0 | 228,000
MODIFY INTERSTATE 680/STATE ROUTE 4 INTERCHANGE TO...
6 | 04 | US 101 / State Route 25 Interchange - Phase 1 | In southern Santa Clara County at the interchange of US 101 and SR 25. | PAED | 1,000 | 0 | 1,000 | 0 | 1,000 | Baseline |  | 6/23/21 |  | 0 | Scope
| 0462G |  |  | PSE | 6,200 | 4,200 | 6,500 | 4,200 | 8,200 | PAED | 9/30/13 | 9/30/13 |  |  | Cost
| SCL |  |  | RW Sup | 0 | 0 | 118 | 0 | 0 | RW Cert | 2/28/23 |  | 2/28/23 |  | Schedule
| 101 |  |  | Con Sup | 0 | 0 | 0 | 0 | 0 | RTL | 2/28/23 |  | 2/28/23 |  | Benefits
|  |  | Reconstruct the interchange at a location just north of the existing interchange. The improvements will include a new, widened bridge to convey SR 25 over US 101. It will also improve ramps for all traffic movements between US 101 and SR 25. and minor realignment of SR 25 to the north. New traffic signals will be installed at the northbound and southbound ramp termini with SR 25. | RW Cap | 15,000 | 0 | 1,025 | 0 | 15,000 | Begin Const | 8/31/23 |  | 8/31/23
|  |  |  | Con Cap | 79,000 | 55,000 | 0 | 0 | 79,000 | End Const | 12/1/25 |  | 12/1/25
|  |  |  | Total | 101,200 | 59,200 | 8,643 | 4,200 | 103,200
7 | 04 | 7th Street Grade Separation (East) | In the city of Oakland within the Port of Oakland along 7th Street, from east of Maritime Street to just west of I-880 near Bay Street. | PAED | 5,400 | 0 | 5,400 | 0 | 5,400 | Baseline |  | 10/17/18 |  | 0
| 2103D |  |  | PSE | 15,240 | 0 | 0 | 0 | 15,200 | PAED | 10/25/18 | 10/25/18 |  |  | Cost
| ALA |  |  | RW Sup | 0 | 0 | 0 | 0 | 0 | RW Cert | 4/15/22 |  | 8/5/22 |  | Schedule
|  |  |  | Con Sup | 0 | 0 | 0 | 0 | 0 | RTL | 4/9/22 |  | 8/10/22
|  |  | Reconstruction of the existing underpass and multi-use path, and the reconstruction of rail tracks and other rail infrastructure at the UnionPacific Railroad (UPRR) mainline. | RW Cap | 63,450 | 0 | 0 | 0 | 73,708 | Begin Const | 1/26/23 |  | 3/23/23
|  |  |  | Con Cap | 232,910 | 175,000 | 0 | 0 | 270,192 | End Const | 12/31/25 |  | 8/28/26
|  |  |  | Total | 317,000 | 175,000 | 5,400 | 0 | 364,500
8 | 04 | I-80/I-680/Route 12 Interchange Package 2A | Eastbound SR12 to Eastbound I-80 Connector - This project would construct a new connector from Eastbound SR12 to Eastbound I-80, which will also connect two previous CMIA projects, ICP and Jameson Canyon widening projects. | PAED | 0 | 0 | 0 | 0 | 0 | Baseline |  | 10/18/18 |  | 67,000
| 5301X |  |  | PSE | 11,700 | 0 | 10,108 | 0 | 10,108 | PAED | 12/7/12 | 12/7/12 |  |  | Cost
| SOL |  |  | RW Sup | 600 | 0 | 0 | 0 | 0 | RW Cert | 3/31/20 | 6/30/20 |  |  | Schedule
| 80,12 |  |  | Con Sup | 10,000 | 10,000 | 8,071 | 8,071 | 10,448 | RTL | 3/31/20 | 6/30/20 |  |  | Benefits
|  |  | CONSTRUCTION EASTBOUND SR 12W TO EAST BOUND I-80 CONNECTOR | RW Cap | 4,400 | 0 | 0 | 0 | 0 | Begin Const | 6/30/20 | 8/26/20
|  |  |  | Con Cap | 67,000 | 43,200 | 55,027 | 35,476 | 67,000 | End Const | 6/30/22 |  | 3/31/23
|  |  |  | Total | 93,700 | 53,200 | 73,206 | 43,547 | 87,556
9 | 04 | Westbound I-80 Cordelia Commercial Vehicle Enforcement Facility | Near the city of Fairfield. | PAED | 0 | 0 | 0 | 0 |  | Baseline |  |  |  | 0
| 8273C |  |  | PSE | 29,270 | 24,002 | 2,056 | 1,686 | 9,007 | PAED | 12/10/12 | 12/10/12 |  |  | Cost
| SOL |  |  | RW Sup | 750 | 0 | 0 | 0 | 0 | RW Cert | 6/1/24 |  | 6/1/24
| 80,12 |  |  | Con Sup | 0 | 0 | 0 | 0 | 5,619 | RTL | 6/1/24 |  | 6/1/24 |  | Benefits
|  |  | The proposed project will replace the existing Westbound (WB) I-80 Cordelia Commercial Vehicle Enforcement Facility (CCVEF). The new facility will be relocated 0.7 mile east from its current location and will provide a new braided off-ramp connection and new entrance ramp connection to/from Westbound I-80. Direct access to the facility will also be provided from westbound State Route 12 . The new facility will have the capacity to inspect all westbound I-80 trucks passing the facility 24 hours per day, seven days a week. | RW Cap | 42,750 | 0 | 0 | 0 | 0 | Begin Const | 1/3/25 |  | 1/3/25
|  |  |  | Con Cap | 51,232 | 0 | 0 | 0 | 154,800 | End Const | 1/3/28 |  | 1/3/28
|  |  |  | Total | 124,002 | 24,002 | 2,056 | 1,686 | 169,426
EAC = Estimate at Completion |  |  | CAP = Corrective Action Plan |  | Bold | Phase allocated |  |  |  | 3 to 6 months behind schedule
Approved = Last Commission action
6+ months behind schedule or delayed beyond fiscal year or EAC over budget
[14 empty] | Page 2 | of 14
Trade Corridor Ehancement Program (TCEP) Project List
April 01 - June 30, 2022
District
| PPNO |  |  |  | Approved Budget ($1,000s) | TCEP Budget ($1,000s) | Total Expended ($1,000s) | TCEP Expended ($1,000s) |  |  | Approved Finish Date | Actual Finish Date | Current Finish Date | Award Amount ($1,000s)
County
EAC ($1,000s)
No. | Route | Title | Location and Type of Work | Phase | [5 empty] | Milestone |  |  |  |  | CAPs
10 | 04 | Freight Intelligent Transportation System | In the City of Oakland, within the Port of Oaklands Seaport Area, along West Grand Avenue, Maritime Street, 7th Street, and Middle Harbor Road. | PAED | 2,500 | 0 | 2,500 | 0 | 2,500 | Baseline |  | 10/17/18 |  | 26,186 | Scope
| T0003 |  |  | PSE | 4,100 | 0 | 3,860 | 0 | 3,860 | PAED | 10/31/18 | 8/31/18 |  |  | Cost
| ALA |  |  | RW Sup | 0 | 0 | 0 | 0 | 0 | RW Cert | 12/31/18 | 3/1/19 |  |  | Schedule
|  |  |  | Con Sup | 0 | 0 | 0 | 0 | 0 | RTL | 3/31/19 | 3/6/19
|  |  | Install and implement ITS elements and other technologies, which include changeable message signs, closed circuit TV, fiber optic and Wi-Fi communications, traffic signal enhancements, vehicle and queue detection, train queue detection, weigh-in-motion, information application, and smart parking system. | RW Cap | 0 | 0 | 0 | 0 | 0 | Begin Const | 8/1/19 | 10/24/19
|  |  |  | Con Cap | 24,000 | 12,456 | 0 | 0 | 34,841 | End Const | 12/31/21 |  | 12/31/23
|  |  |  | Total | 30,600 | 12,456 | 6,360 | 0 | 41,201
District 05
District
| PPNO |  |  |  | Approved Budget ($1,000s) | TCEP Budget ($1,000s) | Total Expended ($1,000s) | TCEP Expended ($1,000s) |  |  | Approved Finish Date | Actual Finish Date | Current Finish Date | Award Amount ($1,000s)
County
EAC ($1,000s)
No. | Route | Title | Location and Type of Work | Phase | [5 empty] | Milestone |  |  |  |  | CAPs
11 | 05 | Castroville Boulevard Interchange | In Monterey County at Castroville Boulevard from Post Mile R1.6 to 1.4. | PAED | 0 | 0 | 0 | 0 | 0 | Baseline |  | 6/23/21 |  | 0
| 0057D |  |  | PSE | 6,200 | 0 | 6,143 | 0 | 7,479 | PAED | 1/13/13 | 1/31/13 |  |  | Cost
| MON |  |  | RW Sup | 1,400 | 0 | 588 | 0 | 1,548 | RW Cert | 3/16/22 |  | 5/1/23 |  | Schedule
| 156 |  |  | Con Sup | 5,500 | 5,500 | 0 | 0 | 5,002 | RTL | 3/17/22 |  | 5/1/23
|  |  | Build a new interchange at Castroville Boulevard and Highway 156. The State Route 156 Castroville Interchange project is a safety, economic development, and congestion relief project in northern Monterey County, California, that will convert the existing at-grade signalized intersection at Castroville Boulevard into a new grade-separated interchange. The project will enhance safety for residents in the low-income rural community of Castroville, reduce traffic congestion for trucks traveling to and from the region’s largest agricultural distribution center, improve access for visitors to the world-famous Monterey Peninsula, and improve the quality of life for all communities along the corridor. | RW Cap | 18,412 | 0 | 138 | 0 | 20,026 | Begin Const | 10/24/22 |  | 12/7/23
|  |  |  | Con Cap | 24,000 | 14,500 | 0 | 0 | 30,157 | End Const | 7/1/24 |  | 8/13/25
|  |  |  | Total | 55,512 | 20,000 | 6,869 | 0 | 64,212
12 | 05 | SR 46 Expressway Conversion - Antelope Grade Segment | On State Route 46, in San Luis Obispo County near Cholame from east of State Route 46/41 Intersection east to Kern County Line. Convert existing 2-lane conventional highway to 4-lane divided expressway. | PAED | 0 | 0 | 848 | 0 | 848 | Baseline |  | 6/23/21 |  | 0 | Scope
| 0226L |  |  | PSE | 10,300 | 0 | 1,654 | 0 | 11,437 | PAED | 6/29/05 | 6/29/05 |  |  | Cost
| SLO,VAR |  |  | RW Sup | 1,400 | 1,400 | 1 | 0 | 2,382 | RW Cert | 6/5/23 |  | 5/28/24 |  | Schedule
|  |  |  | Con Sup | 0 | 0 | 0 | 0 | 9,074 | RTL | 6/7/23 |  | 5/28/24 |  | Benefits
46
|  |  |  | RW Cap | 7,600 | 5,900 | 0 | 0 | 13,971 | Begin Const | 1/12/24 |  | 9/27/24
Convert to 4 lane expressway
|  |  |  | Con Cap | 0 | 0 | 0 | 0 | 70,100 | End Const | 12/18/26 |  | 9/7/27
|  |  |  | Total | 19,300 | 7,300 | 2,503 | 0 | 107,812
13 | 05 | Carpinteria to Santa Barbara Widening - Segment 4A Combined | In Santa Barbara County In Carpenteria From 0.2 Mile South of Bailard Avenue Overcrossing To 0.7 Mile South of South Padaro Lane | PAED | 12,245 | 0 | 5,862 | 0 | 5,862 | Baseline |  |  |  | 79,731
| 7101P |  |  | PSE | 9,700 | 0 | 10,680 | 0 | 10,680 | PAED | 8/26/14 | 8/26/14
| SB |  |  | RW Sup | 1,140 | 0 | 1,090 | 0 | 1,090 | RW Cert | 1/15/20 | 2/4/20
| 101 |  |  | Con Sup | 18,470 | 8,400 | 9,961 | 4,530 | 16,698 | RTL | 2/1/20 | 2/4/20
|  |  | Construct HOV lanes | RW Cap | 10,620 | 0 | 2,016 | 0 | 0 | Begin Const | 8/15/20 | 4/2/20
|  |  |  | Con Cap | 89,548 | 42,600 | 84,559 | 39,605 | 79,732 | End Const | 8/15/24 |  | 8/22/23
|  |  |  | Total | 141,723 | 51,000 | 114,168 | 44,135 | 114,062
EAC = Estimate at Completion |  |  | CAP = Corrective Action Plan |  | Bold | Phase allocated |  |  |  | 3 to 6 months behind schedule
Approved = Last Commission action
6+ months behind schedule or delayed beyond fiscal year or EAC over budget
[14 empty] | Page 3 | of 14
Trade Corridor Ehancement Program (TCEP) Project List
April 01 - June 30, 2022
District 06
District
| PPNO |  |  |  | Approved Budget ($1,000s) | TCEP Budget ($1,000s) | Total Expended ($1,000s) | TCEP Expended ($1,000s) |  |  | Approved Finish Date | Actual Finish Date | Current Finish Date | Award Amount ($1,000s)
County
EAC ($1,000s)
No. | Route | Title | Location and Type of Work | Phase | [5 empty] | Milestone |  |  |  |  | CAPs
14 | 06 | Route 46 Expressway Segment 4C | In and near Lost Hills, from 1 mile west of Browns Material Road to California Aquaduct. | PAED | 0 | 0 | 0 | 0 | 0 | Baseline |  | 6/23/21 |  | 0
| 3386E |  |  | PSE | 500 | 0 | 1,550 | 0 | 2,193 | PAED | 6/14/05 | 6/14/05 |  |  | Cost
| KER |  |  | RW Sup | 400 | 0 | 213 | 0 | 637 | RW Cert | 7/1/22 |  | 8/11/22
| 46 |  |  | Con Sup | 5,400 | 0 | 0 | 0 | 3,816 | RTL | 7/1/22 |  | 8/12/22 |  | Benefits
|  |  | Convert from a 2-lane conventional highway to a 4-lane expressway. | RW Cap | 1,800 | 0 | 0 | 0 | 2,706 | Begin Const | 12/5/22 |  | 2/24/23
|  |  |  | Con Cap | 30,900 | 10,000 | 0 | 0 | 29,400 | End Const | 7/15/24 |  | 7/15/24
|  |  |  | Total | 39,000 | 10,000 | 1,763 | 0 | 38,752
15 | 06 | South Madera 6 Lane | In Madera County, from North of Fresno-Madera County line to South of Avenue 7 to North of Avenue 12. | PAED | 3,413 | 0 | 4,092 | 0 | 4,092 | Baseline |  |  |  | 0
| 6297 |  |  | PSE | 9,460 | 0 | 756 | 0 | 6,055 | PAED | 5/1/21 | 5/1/21 |  |  | Cost
| MAD |  |  | RW Sup | 1,500 | 1,270 | 191 | 191 | 1,521 | RW Cert | 6/30/23 |  | 5/31/24 |  | Schedule
| 99 |  |  | Con Sup | 0 | 0 | 0 | 0 | 12,585 | RTL | 8/1/23 |  | 6/14/24
|  |  | This project will improve goods movement and passenger travel along State Route 99 by median widening from 4 to 6 lanes. It will also upgrade drainage, construct drainage basins and median barrier, and increase vertical clearance at one structure. | RW Cap | 4,000 | 3,389 | 0 | 0 | 3,662 | Begin Const | 3/4/24 |  | 1/15/25
|  |  |  | Con Cap | 0 | 0 | 0 | 0 | 120,000 | End Const | 7/1/27 |  | 7/1/28
|  |  |  | Total | 18,373 | 4,659 | 5,039 | 191 | 147,915
16 | 06 | Route 58/99 Bakersfield Freeway Connector | The project is proposed at the State Route 58/State Route 99 interchange in Bakersfield, CA. | PAED | 0 | 0 | 0 | 0 | 0 | Baseline |  | 10/17/18 |  | 48,500
| 6955 |  |  | PSE | 0 | 0 | 0 | 0 | 0 | PAED | 12/4/15
| KER |  |  | RW Sup | 0 | 0 | 0 | 0 | 0 | RW Cert | 4/1/18 |  |  |  | Schedule
| 58,99 |  |  | Con Sup | 25 | 25 | 0 | 0 | 0 | RTL | 6/1/18 | 8/24/18 |  |  | Benefits
|  |  | The project proposes to grade separate exit and entry freeway ramps between two closely spaced interchanges (SR 58/SR 99 and SR 99/Ming Ave), and to construct a collector -distributor roadway and auxiliary lanes along the southbound State Route 99 mainline to safely accommodate on-ramp traffic. | RW Cap | 0 | 0 | 0 | 0 | 0 | Begin Const | 8/1/18 | 2/19/19
|  |  |  | Con Cap | 25,025 | 25 | 16,371 | 326 | 0 | End Const | 2/1/21 |  | 9/30/22
|  |  |  | Total | 25,050 | 50 | 16,371 | 326 | 0
District 07
District
| PPNO |  |  |  | Approved Budget ($1,000s) | TCEP Budget ($1,000s) | Total Expended ($1,000s) | TCEP Expended ($1,000s) |  |  | Approved Finish Date | Actual Finish Date | Current Finish Date | Award Amount ($1,000s)
County
EAC ($1,000s)
No. | Route | Title | Location and Type of Work | Phase | [5 empty] | Milestone |  |  |  |  | CAPs
17 | 07 | Route 71 Expressway to Freeway Conversion (South Segment) | In the City of Pomona from 0. | PAED | 4,922 | 0 | 2,283 | 0 | 2,283 | Baseline |  | 10/18/18 |  | 98,256 | Scope
| 2741S |  |  | PSE | 22,042 | 0 | 16,663 | 0 | 16,663 | PAED | 5/31/13 | 5/31/13 |  |  | Cost
| VAR,LA |  |  | RW Sup | 3,000 | 0 | 3,426 | 0 | 3,426 | RW Cert | 3/24/20 | 3/24/20 |  |  | Schedule
| 71 |  |  | Con Sup | 24,000 | 5,000 | 6,235 | 1,427 | 24,686 | RTL | 3/26/20 | 3/26/20 |  |  | Benefits
|  |  | 2 mile South of Mission Blvd to 0. 2 mile South of LA/SBD CL Add on mixed lane and one HOV lane in each direction. | RW Cap | 10,600 | 0 | 4,815 | 0 | 10,600 | Begin Const | 12/31/20 | 3/16/21
|  |  |  | Con Cap | 124,097 | 38,025 | 20,329 | 586 | 98,256 | End Const | 7/14/24 |  | 7/10/24
|  |  |  | Total | 188,661 | 43,025 | 53,751 | 2,013 | 155,914
18 | 07 | I-5 Golden State Chokepoint Relief | In northern Los Angeles County at the I-5 / SR-14 split. | PAED | 0 | 0 | 1,882 | 0 | 1,882 | Baseline |  |  |  | 379,957 | Scope
| 3189B |  |  | PSE | 31,000 | 0 | 7,697 | 0 | 7,697 | PAED | 9/29/09 | 9/29/09 |  |  | Cost
| LA |  |  | RW Sup | 0 | 0 | 598 | 0 | 0 | RW Cert | 5/1/19 | 3/19/20 |  |  | Schedule
| 5 |  |  | Con Sup | 0 | 0 | 0 | 0 | 0 | RTL | 5/1/19 | 4/8/20 |  |  | Benefits
|  |  | Construct truck lanes, HOV lanes, auxiliary lanes, soundwalls, and an ITS hub station. Widen seven bridges and improve access to weigh station. | RW Cap | 6,700 | 0 | 14 | 0 | 0 | Begin Const | 1/15/20 | 8/23/21
|  |  |  | Con Cap | 501,500 | 247,000 | 8 | 5 | 0 | End Const | 1/31/23 |  | 2/28/26
|  |  |  | Total | 539,200 | 247,000 | 10,199 | 5 | 9,579
EAC = Estimate at Completion |  |  | CAP = Corrective Action Plan |  | Bold | Phase allocated |  |  |  | 3 to 6 months behind schedule
Approved = Last Commission action
6+ months behind schedule or delayed beyond fiscal year or EAC over budget
[14 empty] | Page 4 | of 14
Trade Corridor Ehancement Program (TCEP) Project List
April 01 - June 30, 2022
District
| PPNO |  |  |  | Approved Budget ($1,000s) | TCEP Budget ($1,000s) | Total Expended ($1,000s) | TCEP Expended ($1,000s) |  |  | Approved Finish Date | Actual Finish Date | Current Finish Date | Award Amount ($1,000s)
County
EAC ($1,000s)
No. | Route | Title | Location and Type of Work | Phase | [5 empty] | Milestone |  |  |  |  | CAPs
19 | 07 | Rice Avenue & Fifth Street Grade Separation Project | In the City of Oxnard at the Rice Avenue / Fifth Street (State Route 34) intersection. | PAED | 3,132 | 0 | 3,132 | 0 | 3,132 | Baseline |  | 12/5/19 |  | 0 | Scope
| 4961 |  |  | PSE | 10,000 | 7,569 | 10,000 | 0 | 10,000 | PAED | 5/17/18 | 5/16/18 |  |  | Cost
| VEN |  |  | RW Sup | 0 | 0 | 0 | 0 | 0 | RW Cert | 7/7/22 |  | 8/30/22 |  | Schedule
| 34 |  |  | Con Sup | 0 | 0 | 0 | 0 | 0 | RTL | 7/15/22 |  | 8/31/22 |  | Benefits
|  |  | Construct grade separation structure to elevate Rice Avenue over State Route 34 (SR-34) and the UPRR track to eliminate the existing at-grade railroad crossing. The project also includes the construction of a connector ramp, in the southeast quadrant of the Rice Avenue grade separation, to provide access between Rice Avenue and Fifth Street/SR-34. | RW Cap | 23,500 | 23,500 | 23,500 | 0 | 23,500 | Begin Const | 12/15/22 |  | 12/15/22
|  |  |  | Con Cap | 80,900 | 75,900 | 80,900 | 0 | 80,900 | End Const | 8/30/26 |  | 8/30/26
|  |  |  | Total | 117,532 | 106,969 | 117,532 | 0 | 117,532
20 | 07 | State Route 47-Vincent Thomas Bridge and Harbor Boulevard-Front Street Interchange Improvement Project | The project entails modifying the existing on- and off-ramps to improve safety, access, and the efficient operation of the SR-47 / Front Street / Harbor Blvd Interchange. | PAED | 1,075 | 0 | 0 | 0 | 0 | Baseline |  | 6/23/21 |  | 0
| 5088 |  |  | PSE | 8,750 | 0 | 0 | 0 | 0 | PAED | 6/30/19 | 6/21/19
| LA |  |  | RW Sup | 0 | 0 | 0 | 0 | 0 | RW Cert | 12/31/21 |  | 12/8/22 |  | Schedule
| 47 |  |  | Con Sup | 6,459 | 0 | 0 | 0 | 0 | RTL | 5/31/22 |  | 12/22/22
|  |  | INTERCHANGE RECONFIGURATION | RW Cap | 0 | 0 | 0 | 0 | 0 | Begin Const | 12/1/22 |  | 10/12/23
|  |  |  | Con Cap | 54,216 | 13,383 | 0 | 0 | 0 | End Const | 11/30/25 |  | 10/11/26
|  |  |  | Total | 70,500 | 13,383 | 0 | 0 | 0
21 | 07 | Route 605 / 91 Interchange Improvement: Gateway Cities Freight Crossroads Project | In the cities of Artesia and Cerritos, from Shoemaker Avenue to I-605 Interchange and on I-605 from Alondra Blvd to the I-605/SR-91 interchange. The project would add one new mixed-flow lane on SR-91 in the westbound direction from the Artesia Boulevard on-ramp to I-605 Connector ramp joining at the point where the westbound SR-91 to the northbound I-605 connector ramp flares from one to two lanes. | PAED | 8,000 | 0 | 665 | 0 | 665 | Baseline |  | 6/23/21 |  | 0 | Scope
| 5388 |  |  | PSE | 12,000 | 3,000 | 5,981 | 0 | 12,000 | PAED | 1/18/19 | 1/18/19 |  |  | Cost
| LA |  |  | RW Sup | 0 | 0 | 0 | 0 | 0 | RW Cert | 12/31/22 |  | 12/30/22 |  | Schedule
| 91,605 |  |  | Con Sup | 0 | 0 | 0 | 0 | 0 | RTL | 12/31/22 |  | 12/30/22
|  |  |  | RW Cap | 23,100 | 17,100 | 0 | 0 | 23,100 | Begin Const | 9/30/23 |  | 9/1/23
|  |  |  | Con Cap | 114,300 | 69,670 | 0 | 0 | 114,300 | End Const | 12/1/25 |  | 7/7/26
|  |  |  | Total | 157,400 | 89,770 | 6,646 | 0 | 150,065
OPERATIONS AND CAPACITY IMPROVEMENT
22 | 07 | Route 57/60 Confluence: Chokepoint Relief Project | In Los Angeles County, in Diamond Bar and the City of Industry on Route 60 from EB 60 to SB 57 connector overcrossing to near Golden Springs Drive Undercrossing and Route 57 from NB 57 to WB 60 connector overcrossing to South 57/60 separation. Interchange modifications, including auxiliary lanes and three new bridges. | PAED | 0 | 0 | 0 | 0 | 0 | Baseline |  | 6/23/21 |  | 0 | Scope
| 5394 |  |  | PSE | 25,300 | 17,000 | 10,388 | 10,388 | 0 | PAED | 5/31/21 | 12/11/13 |  |  | Cost
| LA |  |  | RW Sup | 0 | 0 | 0 | 0 | 0 | RW Cert | 2/21/22 | 6/3/22 |  |  | Schedule
| 60,57 |  |  | Con Sup | 0 | 0 | 0 | 0 | 0 | RTL | 2/28/22 | 6/9/22 |  |  | Benefits
|  |  |  | RW Cap | 91,000 | 5,000 | 0 | 0 | 0 | Begin Const | 8/31/22 |  | 12/29/22
|  |  |  | Con Cap | 303,900 | 217,900 | 0 | 0 | 0 | End Const | 10/31/27 |  | 3/30/28
RECONSTRUCT GRAND AVE OC, RECONSTRUCT NB SR-57 CONNECTOR TO EB SR-60, CONSTRUCT EB SR-60 BY PASS OFF-RAMP TO GRAND AVE, CONSTRUCT EB SR-60 BYPASS, CONSTRUCT SB GRAND AVE TO EB SR-60 LOOP ON-RAMP
|  |  |  | Total | 420,200 | 239,900 | 10,388 | 10,388 | 0
23 | 07 | EB SR-91 Atlantic Ave to Cherry Ave. Aux Lane Project | In the City of Long Beach on SR-91 from I-710 to Cherry Avenue undercrossing. | PAED | 2,872 | 0 | 2,872 | 0 | 2,872 | Baseline |  |  |  | 0
| 5496 |  |  | PSE | 4,702 | 0 | 0 | 0 | 4,702 | PAED | 6/30/21 | 5/28/21 |  |  | Cost
| LA |  |  | RW Sup | 0 | 0 | 0 | 0 | 0 | RW Cert | 1/1/22 | 5/2/22 |  |  | Schedule
| 91 |  |  | Con Sup | 0 | 0 | 0 | 0 | 0 | RTL | 3/11/22 | 5/4/22 |  |  | Benefits
|  |  | The proposed improvements consist of adding one auxiliary lane in the eastbound direction, extending the outside #5 lane beyond the Atlantic Ave EB off-ramp to Cherry Ave then dropping it before the Cherry Ave undercrossing, and widening the Orange Ave and Walnut Ave undercrossings. | RW Cap | 43 | 0 | 0 | 0 | 43 | Begin Const | 3/1/23 |  | 5/4/23
|  |  |  | Con Cap | 87,133 | 48,332 | 0 | 0 | 87,133 | End Const | 8/31/26 |  | 8/31/26
|  |  |  | Total | 94,750 | 48,332 | 2,872 | 0 | 94,750
EAC = Estimate at Completion |  |  | CAP = Corrective Action Plan |  | Bold | Phase allocated |  |  |  | 3 to 6 months behind schedule
Approved = Last Commission action
6+ months behind schedule or delayed beyond fiscal year or EAC over budget
[14 empty] | Page 5 | of 14
Trade Corridor Ehancement Program (TCEP) Project List
April 01 - June 30, 2022
District
| PPNO |  |  |  | Approved Budget ($1,000s) | TCEP Budget ($1,000s) | Total Expended ($1,000s) | TCEP Expended ($1,000s) |  |  | Approved Finish Date | Actual Finish Date | Current Finish Date | Award Amount ($1,000s)
County
EAC ($1,000s)
No. | Route | Title | Location and Type of Work | Phase | [5 empty] | Milestone |  |  |  |  | CAPs
24 | 07 | Port of Los Angeles - Fenix Terminal Railyard Expansion & Modernization Project | The project is located entirely on the Fenix marine container terminal at the Port of Los Angeles (POLA) and makes improvements to the existing on-dock railyard at the Fenix terminal. | PAED | 300 | 0 | 300 | 0 | 300 | Baseline |  | 12/9/21 |  | 0 | Scope
| 5830 |  |  | PSE | 3,186 | 0 | 0 | 0 | 3,186 | PAED | 8/31/21 | 5/31/21 |  |  | Cost
| LA |  |  | RW Sup | 0 | 0 | 0 | 0 | 0 | RW Cert | 8/31/22 |  | 8/31/22 |  | Schedule
|  |  |  | Con Sup | 0 | 0 | 0 | 0 | 0 | RTL | 9/30/22 |  | 9/30/22 |  | Benefits
|  |  | The Fenix terminal and the entire POLA are also part of the United States Department of Transportation (USDOT) designated National Multimodal Freight Network (NMFN). The improvement project will increase capacity by adding five new working tracks just north of/parallel to the existing railyard, including tail track, pavement & turnouts. | RW Cap | 0 | 0 | 0 | 0 | 0 | Begin Const | 7/1/23 |  | 7/1/23
|  |  |  | Con Cap | 48,869 | 19,194 | 0 | 0 | 48,869 | End Const | 6/30/25 |  | 6/30/25
|  |  |  | Total | 52,355 | 19,194 | 300 | 0 | 52,355
25 | 07 | Alameda Corridor Southern Terminus Gap Closure | In Los Angeles County at the Port of Los Angeles. Extension of the TraPac lead track and San Pedro main line track of approximately 5000 linear feet and will connect to the Alameda Corridor. | PAED | 0 | 0 | 0 | 0 | 0 | Baseline |  | 10/18/18 |  | 11,867 | Scope
| T0005 |  |  | PSE | 969 | 0 | 969 | 0 | 969 | PAED | 11/16/18 | 12/6/19 |  |  | Cost
| LA |  |  | RW Sup | 0 | 0 | 0 | 0 | 0 | RW Cert |  | 3/11/20 |  |  | Schedule
|  |  |  | Con Sup | 0 | 0 | 0 | 0 | 0 | RTL | 8/1/19 | 6/25/20 |  |  | Benefits
|  |  | Work includes the relocation and/or protection of existing underground utilities and the relocation of power poles, utility meters, and perimeter fencing. | RW Cap | 0 | 0 | 0 | 0 | 0 | Begin Const | 1/31/20 | 12/17/20
|  |  |  | Con Cap | 8,560 | 5,992 | 11,446 | 677 | 13,343 | End Const | 1/31/21 |  | 7/31/22
|  |  |  | Total | 9,529 | 5,992 | 12,415 | 677 | 14,312
26 | 07 | Terminal Island Railyard Enhancement Project | In the Port of Los Angeles on Terminal Island. | PAED | 843 | 0 | 843 | 0 | 843 | Baseline |  |  |  | 57,947 | Scope
| T0006 |  |  | PSE | 2,249 | 0 | 2,249 | 0 | 2,249 | PAED | 11/16/18 | 4/14/20 |  |  | Cost
| LA |  |  | RW Sup | 0 | 0 | 0 | 0 | 0 | RW Cert |  | 8/6/20 |  |  | Schedule
|  |  |  | Con Sup | 0 | 0 | 0 | 0 | 0 | RTL | 1/2/20 | 5/20/21 |  |  | Benefits
|  |  | Addition of five staging/storage tracks (approximately 31,000 lineal feet) to the existing Pier 400 rail yard, which also includes a short rail bridge over water. The Pier 400 storage/staging rail yard supports on-dock rail yards for six terminals in the POLA and POLB. | RW Cap | 0 | 0 | 0 | 0 | 0 | Begin Const | 6/30/20 | 11/9/21
|  |  |  | Con Cap | 30,923 | 21,645 | 27,024 | 0 | 57,947 | End Const | 12/31/21 |  | 6/30/24
|  |  |  | Total | 34,015 | 21,645 | 30,116 | 0 | 61,039
27 | 07 | Pier G and J Double Track | At the Port of Long Beach from Pier G to Pier J. | PAED | 2,629 | 0 | 0 | 0 | 0 | Baseline |  | 10/17/18 |  | 14,000 | Scope
| T0007 |  |  | PSE | 0 | 0 | 2,901 | 0 | 2,901 | PAED | 11/11/16 | 4/25/19 |  |  | Cost
| LA |  |  | RW Sup | 0 | 0 | 0 | 0 | 0 | RW Cert | 4/1/20 | 4/26/19 |  |  | Schedule
|  |  |  | Con Sup | 0 | 0 | 0 | 0 | 0 | RTL | 2/18/18 | 4/29/19 |  |  | Benefits
|  |  | Construct new 9,000-foot mainline track for trains serving four marine terminals in the southeastern area of the Port between the northeast corner of Pier G terminal and Harbor Scenic Drive. | RW Cap | 1,502 | 0 | 0 | 0 | 0 | Begin Const | 2/28/18 | 11/25/19
|  |  |  | Con Cap | 20,869 | 14,000 | 26,263 | 0 | 26,263 | End Const | 7/30/21 | 2/17/22
|  |  |  | Total | 25,000 | 14,000 | 29,164 | 0 | 29,164
District 08
District
| PPNO |  |  |  | Approved Budget ($1,000s) | TCEP Budget ($1,000s) | Total Expended ($1,000s) | TCEP Expended ($1,000s) |  |  | Approved Finish Date | Actual Finish Date | Current Finish Date | Award Amount ($1,000s)
County
EAC ($1,000s)
No. | Route | Title | Location and Type of Work | Phase | [5 empty] | Milestone |  |  |  |  | CAPs
28 | 08 | Route 71/91 Interchange EB-NB Connector | Replace eastbound Rte 91 to northbound Rte 71 loop connector with a direct connector ramp. | PAED | 9,273 | 0 | 5,169 | 0 | 5,169 | Baseline |  | 6/23/21 |  | 0
| 0077G |  |  | PSE | 12,706 | 0 | 0 | 0 | 12,400 | PAED | 8/5/21 | 6/29/11 |  |  | Cost
| RIV |  |  | RW Sup | 0 | 0 | 0 | 0 | 0 | RW Cert | 9/24/21 | 3/4/22 |  |  | Schedule
| 71,91 |  |  | Con Sup | 0 | 0 | 0 | 0 | 0 | RTL | 12/20/21 | 4/20/22 |  |  | Benefits
|  |  | Realign the Green River Road eastbound entrance ramp to Rte 91, and construct a collector/distributor system on Rte 91 in the eastbound direction between the Green River Road and Serfas Club Drive. | RW Cap | 7,250 | 0 | 0 | 0 | 7,000 | Begin Const | 6/30/22 |  | 9/14/22
|  |  |  | Con Cap | 145,684 | 58,108 | 900 | 0 | 138,000 | End Const | 7/19/24 |  | 3/14/25
|  |  |  | Total | 174,913 | 58,108 | 6,069 | 0 | 162,569
EAC = Estimate at Completion |  |  | CAP = Corrective Action Plan |  | Bold | Phase allocated |  |  |  | 3 to 6 months behind schedule
Approved = Last Commission action
6+ months behind schedule or delayed beyond fiscal year or EAC over budget
[14 empty] | Page 6 | of 14
Trade Corridor Ehancement Program (TCEP) Project List
April 01 - June 30, 2022
District
| PPNO |  |  |  | Approved Budget ($1,000s) | TCEP Budget ($1,000s) | Total Expended ($1,000s) | TCEP Expended ($1,000s) |  |  | Approved Finish Date | Actual Finish Date | Current Finish Date | Award Amount ($1,000s)
County
EAC ($1,000s)
No. | Route | Title | Location and Type of Work | Phase | [5 empty] | Milestone |  |  |  |  | CAPs
29 | 08 | Interstate 15 Corridor Freight Improvement Project: Auxiliary Lanes and Express Lanes - Construction | In San Bernardino and Riverside Counties through the cities of Eastvale, Jurupa Valley, Ontario, and Rancho Cucamonga, on I-15 from Cantu-Galleano Road to Foothill Boulevard, construct auxiliary lanes and express lanes. | PAED | 10,373 | 0 | 10,373 | 0 | 10,373 | Baseline |  | 6/23/21 |  | 0
| 0167M |  |  | PSE | 32,606 | 0 | 0 | 0 | 32,606 | PAED | 12/20/18 |  |  |  | Cost
| SBD,RIV |  |  | RW Sup | 0 | 0 | 0 | 0 | 0 | RW Cert | 4/17/23 |  | 4/17/23
| 15 |  |  | Con Sup | 0 | 0 | 0 | 0 | 0 | RTL | 5/15/23 |  | 5/8/23
|  |  | An auxiliary lane will be added in the northbound direction from just south of Jurupa Street extending north to tie into existing auxiliary lanes north of Jurupa Street (1.21 miles). An additional northbound auxiliary lane will be added from just north of 4th Street to just south of Foothill Boulevard (1.6 miles). A new auxiliary lane will be added in the southbound direction from just south of the I-10/I-15 interchange to the Riverside County Line (2.05 miles). Express lanes will extend northerly from Cantu-Galleano Ranch Road/SR-60 to Foothill BoulevaRd Express lanes will be constructed in the median of I-15 joining the Express Lanes in Riverside County. | RW Cap | 2,679 | 0 | 0 | 0 | 3,796 | Begin Const | 11/1/23 |  | 12/20/23
|  |  |  | Con Cap | 262,151 | 118,739 | 0 | 0 | 250,780 | End Const | 5/28/27 |  | 8/26/26
|  |  |  | Total | 307,809 | 118,739 | 10,373 | 0 | 297,555
30 | 08 | McKinley Street Grade Separation | In Riverside County in the City of Corona on McKinley St from SR-91 to Magnolia Ave Construct a new four-lane overhead grade separation. | PAED | 1,694 | 0 | 1,694 | 0 | 1,694 | Baseline |  | 6/23/21 |  | 60,900 | Scope
| 1272 |  |  | PSE | 11,183 | 0 | 1,183 | 0 | 1,183 | PAED | 3/28/19 | 8/2/21 |  |  | Cost
| RIV |  |  | RW Sup | 0 | 0 | 0 | 0 | 0 | RW Cert | 7/10/21 | 9/1/21 |  |  | Schedule
| 91 |  |  | Con Sup | 0 | 0 | 0 | 0 | 0 | RTL | 7/10/21 | 9/1/21 |  |  | Benefits
|  |  | The new roadway will include a raised median, sidewalks, and ADA-compliant curb ramps. The project will construct a one-way ramp connecting southbound McKinley St to Sampson Ave and a new two-way loop road connecting McKinley St to Sampson Ave The SR-91 eastbound off-ramp will be realigned and widened and the SR-91 eastbound loop on-ramp and eastbound slip on-ramp will be reconstructed. | RW Cap | 28,517 | 0 | 28,517 | 0 | 28,517 | Begin Const | 9/1/21 | 11/17/21
|  |  |  | Con Cap | 81,332 | 20,600 | 0 | 0 | 81,332 | End Const | 6/30/23 |  | 1/31/24
|  |  |  | Total | 122,726 | 20,600 | 31,394 | 0 | 112,726
31 | 08 | I-10 Express Lanes-San Antonio Ave to Route 15 (Contract 1) | From LA/SBd Co Ln to I-10/I-15 Interchange & in LA County from 0.4 Mi W/o White Ave OC to LA/SBd Co Ln; Implement two express lanes in each direction for a total of four general purpose and two express lanes in each direction with auxiliary lanes, widening undercrossings, and reconstruction of ramps and lane transitions where needed. | PAED | 213 | 0 | 166 | 0 | 213 | Baseline |  | 10/17/18 |  | 807,571
| 3009P |  |  | PSE | 62,293 | 0 | 0 | 0 | 0 | PAED | 7/6/17 |  |  |  | Cost
| SBD,LA |  |  | RW Sup | 0 | 0 | 0 | 0 | 0 | RW Cert | 3/1/22 | 1/16/18
| 10 |  |  | Con Sup | 0 | 0 | 11,831 | 0 | 0 | RTL | 11/1/21 | 1/16/18
|  |  |  | RW Cap | 49,219 | 0 | 0 | 0 | 56,500 | Begin Const | 7/1/18 | 9/7/18
|  |  |  | Con Cap | 817,466 | 117,831 | 193,093 | 13,146 | 810,185 | End Const | 2/1/24 |  | 8/1/23
This project will be delivered using Design-Build method (TCIF 128).
|  |  |  | Total | 929,191 | 117,831 | 205,090 | 13,146 | 866,898
32 | 08 | I-10 Eastbound Truck Climbing Lane in Yucaipa | In San Bernardino County, from the 16th Street Overcrossing in Yucaipa to 0.2 miles east of the County Line Road Overcrossing in Calimesa (Riverside) . | PAED | 1,979 | 0 | 1,979 | 0 | 1,979 | Baseline |  | 6/24/21 |  | 0
| 3009Q |  |  | PSE | 3,850 | 0 | 1,056 | 0 | 3,288 | PAED | 11/16/20 | 11/12/20
| SBD,RIV |  |  | RW Sup | 0 | 0 | 0 | 0 | 0 | RW Cert | 5/6/22 | 4/22/22 |  |  | Schedule
| 10 |  |  | Con Sup | 0 | 0 | 0 | 0 | 0 | RTL | 5/6/22 |  | 8/29/22
|  |  | Construct a truck climbing lane in the eastbound direction. | RW Cap | 0 | 0 | 0 | 0 | 0 | Begin Const | 6/30/22 |  | 3/1/23
|  |  |  | Con Cap | 30,264 | 24,074 | 0 | 0 | 29,695 | End Const | 4/22/24 |  | 8/26/24
|  |  |  | Total | 36,093 | 24,074 | 3,035 | 0 | 34,962
33 | 08 | Route 60 Truck Safety and Efficiency Project - Phase 1A | This project is located on State Route 60 and Moreno Beach Drive in the City of Moreno Valley, County of Riverside. | PAED | 0 | 0 | 0 | 0 | 0 | Baseline |  | 10/18/18 |  | 23,985
| 3010T |  |  | PSE | 0 | 0 | 0 | 0 | 0 | PAED | 12/1/07 |  |  |  | Cost
| RIV |  |  | RW Sup | 0 | 0 | 0 | 0 | 0 | RW Cert | 3/1/05 | 8/3/20 |  |  | Schedule
| 60 |  |  | Con Sup | 0 | 0 | 0 | 0 | 0 | RTL | 6/30/19 | 10/19/20
|  |  | This specific project component is the second phase of an interchange project that will replace a 50-year old 2-lane bridge with a new 6-lane bridge, reconfigure the north side of SR 60/Moreno Beach Drive Interchange, and build an associated freeway auxiliary lane. Because the bridge is so narrow, trucks are restricted on the eastbound offramp to right-hand (southerly) turns only. | RW Cap | 0 | 0 | 0 | 0 | 0 | Begin Const | 12/1/19 | 5/4/21
|  |  |  | Con Cap | 24,000 | 16,800 | 2,753 | 2,717 | 0 | End Const | 12/1/21 |  | 5/19/23
|  |  |  | Total | 24,000 | 16,800 | 2,753 | 2,717 | 0
EAC = Estimate at Completion |  |  | CAP = Corrective Action Plan |  | Bold | Phase allocated |  |  |  | 3 to 6 months behind schedule
Approved = Last Commission action
6+ months behind schedule or delayed beyond fiscal year or EAC over budget
[14 empty] | Page 7 | of 14
Trade Corridor Ehancement Program (TCEP) Project List
April 01 - June 30, 2022
District
| PPNO |  |  |  | Approved Budget ($1,000s) | TCEP Budget ($1,000s) | Total Expended ($1,000s) | TCEP Expended ($1,000s) |  |  | Approved Finish Date | Actual Finish Date | Current Finish Date | Award Amount ($1,000s)
County
EAC ($1,000s)
No. | Route | Title | Location and Type of Work | Phase | [5 empty] | Milestone |  |  |  |  | CAPs
34 | 08 | Interstate 15 Corridor Freight Improvement Project: Toll System Provider (D/B Contract) | In San Bernardino and Riverside Counties through the cities of Eastvale, Jurupa Valley, Ontario, and Rancho Cucamonga, on I-15 from Cantu Galleano Road to Foothill BoulevaRd This project will construct the Toll System needed to operate the I-15 Express Lanes project (08-0167M). | PAED | 0 | 0 | 0 | 0 |  | Baseline |  | 6/23/21 |  | 0
| 3017N |  |  | PSE | 0 | 0 | 0 | 0 |  | PAED | 12/20/18 |  |  |  | Cost
| SBD,RIV |  |  | RW Sup | 0 | 0 | 0 | 0 | 0 | RW Cert | 4/17/23 |  | 4/17/23 |  | Schedule
| 15 |  |  | Con Sup | 0 | 0 | 0 | 0 | 0 | RTL | 4/7/21 |  | 5/15/23
|  |  |  | RW Cap | 0 | 0 | 0 | 0 | 0 | Begin Const | 4/7/21 |  | 1/8/24
TOLL SYSTEM PROVIDER (D/B CONTRACT)
|  |  |  | Con Cap | 7,600 | 0 | 0 | 0 | 8,764 | End Const | 5/28/27 |  | 5/28/27
|  |  |  | Total | 7,600 | 0 | 0 | 0 | 8,764
35 | 08 | Interstate 15 Corridor Freight Improvement Project: Establish Existing Planting | In San Bernardino and Riverside Counties through the cities of Eastvale, Jurupa Valley, Ontario, and Rancho Cucamonga, on I-15 from Cantu Galleano Road to Foothill BoulevaRd Highway planting project for 08-0167M. | PAED | 0 | 0 | 0 | 0 |  | Baseline |  | 6/23/21 |  | 0
| 3017P |  |  | PSE | 0 | 0 | 0 | 0 |  | PAED | 12/20/18
| SBD,RIV |  |  | RW Sup | 0 | 0 | 0 | 0 | 0 | RW Cert | 4/17/23 |  | 4/17/23
| 15 |  |  | Con Sup | 0 | 0 | 0 | 0 | 0 | RTL | 5/15/23 |  | 5/15/23
|  |  | ESTABLISH EXISTING PLANTING | RW Cap | 0 | 0 | 0 | 0 | 0 | Begin Const | 4/4/27 |  | 4/4/27
|  |  |  | Con Cap | 2,012 | 0 | 0 | 0 | 2,012 | End Const | 5/31/29 |  | 5/31/29
|  |  |  | Total | 2,012 | 0 | 0 | 0 | 2,012
36 | 08 | I-10 Corridor Freight and Express Lane Project - Contract 2 | Location: This project is located on the I-10 corridor, just east of I-15 to Pepper Avenue in Colton. Description: The project will provide one express lane in each direction from just east of I-15 to Pepper Avenue in Colton, connecting to the I-10 Corridor Contract 1 express lanes currently under construction. | PAED | 0 | 0 | 0 | 0 |  | Baseline |  |  |  | 0
| 3019M |  |  | PSE | 71,000 | 0 | 0 | 0 | 71,000 | PAED | 7/6/17 | 7/6/17
| SBD |  |  | RW Sup | 0 | 0 | 0 | 0 | 0 | RW Cert | 5/30/25 |  | 5/30/25
| 10 |  |  | Con Sup | 0 | 0 | 0 | 0 | 0 | RTL | 5/30/25 |  | 5/30/25
|  |  |  | RW Cap | 6,000 | 0 | 0 | 0 | 6,000 | Begin Const | 12/1/25 |  | 12/1/25
WIDEN TO 2 EXPRESS LANES IN EACH DIRECTION
|  |  |  | Con Cap | 606,000 | 85,000 | 0 | 0 | 606,000 | End Const | 12/30/28 |  | 12/30/28
|  |  |  | Total | 683,000 | 85,000 | 0 | 0 | 683,000
District 10
District
| PPNO |  |  |  | Approved Budget ($1,000s) | TCEP Budget ($1,000s) | Total Expended ($1,000s) | TCEP Expended ($1,000s) |  |  | Approved Finish Date | Actual Finish Date | Current Finish Date | Award Amount ($1,000s)
County
EAC ($1,000s)
No. | Route | Title | Location and Type of Work | Phase | [5 empty] | Milestone |  |  |  |  | CAPs
37 | 10 | Livingston Widening Northbound | In Livingston, from 0.8 mile south of Hammatt Avenue to Merced/Stanislaus county line. | PAED | 800 | 0 | 637 | 0 | 637 | Baseline |  | 10/17/18 |  | 35,460
| 0161A |  |  | PSE | 2,050 | 0 | 2,404 | 0 | 2,404 | PAED | 6/2/14 | 6/2/14 |  |  | Cost
| MER |  |  | RW Sup | 10 | 0 | 19 | 0 | 19 | RW Cert | 2/28/19 | 11/7/18 |  |  | Schedule
| 99 |  |  | Con Sup | 6,343 | 0 | 6,731 | 0 | 6,871 | RTL | 3/29/19 | 1/25/19 |  |  | Benefits
|  |  | Widen freeway from two lanes to three lanes in the northbound direction only. | RW Cap | 10 | 0 | 11 | 0 | 11 | Begin Const | 10/16/19 | 12/24/19
|  |  |  | Con Cap | 36,737 | 29,050 | 29,755 | 2,737 | 35,461 | End Const | 4/30/21 |  | 7/19/22
|  |  |  | Total | 45,950 | 29,050 | 39,557 | 2,737 | 45,403
38 | 10 | Route 132 Expressway, Phase 1 | In Modesto, on Route 132 from 0.2 mile east of Stone Avenue to 6th Street, and on Route 99 from I Street to Woodland Avenue. | PAED | 10,206 | 0 | 3,845 | 0 | 3,845 | Baseline |  |  |  | 21,000
| 0944M |  |  | PSE | 10,684 | 0 | 1,217 | 0 | 1,217 | PAED | 3/9/18 | 3/9/18
| STA |  |  | RW Sup | 455 | 0 | 499 | 0 | 0 | RW Cert | 1/1/19 | 5/26/19 |  |  | Schedule
| 99,132 |  |  | Con Sup | 0 | 0 | 0 | 0 | 0 | RTL | 1/2/19 | 5/26/19
|  |  | Construct 2-lane expressway and improve Route 132/99 interchange. | RW Cap | 14,476 | 0 | 35 | 0 | 0 | Begin Const | 4/15/19 | 9/24/19
|  |  |  | Con Cap | 122,572 | 21,000 | 49,978 | 3,390 | 0 | End Const | 12/31/20 |  | 9/30/22
|  |  |  | Total | 158,393 | 21,000 | 55,574 | 3,390 | 5,062
EAC = Estimate at Completion |  |  | CAP = Corrective Action Plan |  | Bold | Phase allocated |  |  |  | 3 to 6 months behind schedule
Approved = Last Commission action
6+ months behind schedule or delayed beyond fiscal year or EAC over budget
[14 empty] | Page 8 | of 14
Trade Corridor Ehancement Program (TCEP) Project List
April 01 - June 30, 2022
District
| PPNO |  |  |  | Approved Budget ($1,000s) | TCEP Budget ($1,000s) | Total Expended ($1,000s) | TCEP Expended ($1,000s) |  |  | Approved Finish Date | Actual Finish Date | Current Finish Date | Award Amount ($1,000s)
County
EAC ($1,000s)
No. | Route | Title | Location and Type of Work | Phase | [5 empty] | Milestone |  |  |  |  | CAPs
39 | 10 | I-580/ International Parkway Interchange | The Project is located in the City of Tracy at the I-580 and International Parkway/Patterson Pass Road interchange. | PAED | 1,340 | 0 | 0 | 0 | 0 | Baseline |  | 6/23/21 |  | 0 | Scope
| 3416 |  |  | PSE | 1,000 | 0 | 0 | 0 | 0 | PAED | 11/1/18 | 3/4/21
| SJ |  |  | RW Sup | 0 | 0 | 0 | 0 | 0 | RW Cert | 8/1/19 |  | 2/10/23 |  | Schedule
| 580 |  |  | Con Sup | 0 | 0 | 0 | 0 | 0 | RTL | 6/1/19 |  | 2/10/23 |  | Benefits
|  |  | Due to increased commercial truck and traffic demand from existing fulfillment and distribution center growth and planned future development in San Joaquin County, the Project proposes to modify the interchange from the existing compact diamond (Type L-1) to a Diverging Diamond Interchange (DDI). The Project reduces congestion, increases truck throughput, and eliminates a bottleneck for trucks accessing I-580, a key freight highway. The Project will improve interregional goods movement for trucks traveling between the Port of Oakland, Bay Area, local warehouses, Southern California, and out-of-state. | RW Cap | 2,692 | 0 | 0 | 0 | 0 | Begin Const | 12/1/19 |  | 7/6/23
|  |  |  | Con Cap | 44,151 | 24,884 | 0 | 0 | 0 | End Const | 11/30/20 |  | 1/31/25
|  |  |  | Total | 49,183 | 24,884 | 0 | 0 | 0
40 | 10 | North County Corridor Project - Phase 1 from Claribel Road to Clause Road. | The North County Corridor Project consists of 4 separate phases of construction totaling 18 miles in length. | PAED | 0 | 0 | 0 | 0 |  | Baseline |  | 6/23/21 |  | 0
| 3507 |  |  | PSE | 12,900 | 0 | 0 | 0 | 597 | PAED | 5/22/20 | 5/22/20 |  |  | Cost
| STA |  |  | RW Sup | 0 | 0 | 0 | 0 | 27 | RW Cert | 3/1/22 |  | 8/22/22 |  | Schedule
| 108 |  |  | Con Sup | 0 | 0 | 0 | 0 | 1,602 | RTL | 9/22/22 |  | 9/22/22
|  |  | The scope of this project is for Phase 1. The corridor will be a high capacity bypass around the cities of Modesto, Riverbank and Oakdale as shown in Exhibit 1. The Phase 1 project will be an ultimate 6-lane divided expressway beginning at the intersection of Claribel Road & Oakdale Road, extending eastward to the intersection of Claribel Road & Claus Road. It will be access controlled with a 40’-70’ median with grade separations over Roselle Avenue, Terminal Avenue and the Burlington Northern Santa Fe Railroad tracks. This new alignment will build a west-east expressway that will improve regional network circulation connecting from the western end of downtown Modesto to the eastward end joining SR-120 east of the City of Oakdale (Segments 1 to 4). | RW Cap | 33,000 | 0 | 0 | 0 | 0 | Begin Const | 6/1/23 |  | 6/1/23
|  |  |  | Con Cap | 117,100 | 20,000 | 0 | 0 | 0 | End Const | 11/1/25 |  | 11/1/25
|  |  |  | Total | 163,000 | 20,000 | 0 | 0 | 2,226
41 | 10 | Port of Stockton Rail Bridge, Phase I | Track rehabilitation, operational and capacity improvements between the Ports West Complex and the BNSF Stockton Subdivision, City of Stockton, San Joaquin County. | PAED | 0 | 0 | 0 | 0 |  | Baseline |  |  |  | 0
| T0018 |  |  | PSE | 6,333 | 4,433 | 0 | 0 | 1,900 | PAED | 6/30/21 | 9/30/21
| SJ |  |  | RW Sup | 0 | 0 | 0 | 0 | 0 | RW Cert | 10/15/22 |  | 10/23/23 |  | Schedule
| VAR |  |  | Con Sup | 0 | 0 | 0 | 0 | 0 | RTL | 9/15/22 |  | 11/30/23
|  |  | Track rehabilitation includes upgrading to 136# rail to accommodate heavier trains. Double track lead to minimize delays and accommodate Port future growth. Replacement of existing 1930 swing truss single track bridge with a new fixed span single track bridge to address seismic deficiencies, safety concerns (fire), remove obstacles to larger and heavier loads. | RW Cap | 1,300 | 910 | 0 | 0 | 390 | Begin Const | 4/15/23 |  | 3/4/24
|  |  |  | Con Cap | 0 | 0 | 0 | 0 | 0 | End Const | 10/15/25 |  | 10/31/25
|  |  |  | Total | 7,633 | 5,343 | 0 | 0 | 2,290
EAC = Estimate at Completion |  |  | CAP = Corrective Action Plan |  | Bold | Phase allocated |  |  |  | 3 to 6 months behind schedule
Approved = Last Commission action
6+ months behind schedule or delayed beyond fiscal year or EAC over budget
[14 empty] | Page 9 | of 14
Trade Corridor Ehancement Program (TCEP) Project List
April 01 - June 30, 2022
District 11
District
| PPNO |  |  |  | Approved Budget ($1,000s) | TCEP Budget ($1,000s) | Total Expended ($1,000s) | TCEP Expended ($1,000s) |  |  | Approved Finish Date | Actual Finish Date | Current Finish Date | Award Amount ($1,000s)
County
EAC ($1,000s)
No. | Route | Title | Location and Type of Work | Phase | [5 empty] | Milestone |  |  |  |  | CAPs
42 | 11 | East Otay Mesa Land Port of Entry - Segment 3 | Near San Diego on Route 11 at 1.9 miles east of Sanyo Avenue Undercrossing (Mexico border). | PAED | 0 | 0 | 0 | 0 |  | Baseline |  | 6/23/21 |  | 0
| 0999C |  |  | PSE | 35,771 | 5,900 | 0 | 0 | 35,771 | PAED | 4/1/12 | 4/1/12
| SD |  |  | RW Sup | 0 | 0 | 0 | 0 | 0 | RW Cert | 12/1/21 | 11/3/21 |  |  | Schedule
| 11 |  |  | Con Sup | 0 | 0 | 0 | 0 | 0 | RTL | 1/4/22 |  | 4/19/23
|  |  | Construct Port of Entry at the border with Mexico. | RW Cap | 36,383 | 0 | 0 | 0 | 36,383 | Begin Const | 7/20/22 |  | 11/9/23
|  |  |  | Con Cap | 0 | 0 | 0 | 0 | 0 | End Const | 12/20/24 |  | 10/31/25
|  |  |  | Total | 72,154 | 5,900 | 0 | 0 | 72,154
43 | 11 | Siempre Viva Interchange and Site Preparation Design for Commercial Vehicle Enforcement Facility - Segment 2B | Near San Diego at 1.9 miles east of Sanyo Avenue Undercrossing. Construct new interchange and begin site preparation design for Commercial Vehicle Enforcement Facility, which includes drainage and utilities. | PAED | 0 | 0 | 0 | 0 |  | Baseline |  | 8/15/18 |  | 17,899
| 0999E |  |  | PSE | 4,810 | 4,810 | 4,806 | 4,806 | 4,806 | PAED | 3/29/12 | 4/2/12
| SD |  |  | RW Sup | 0 | 0 | 0 | 0 | 0 | RW Cert | 4/12/19 | 3/27/20 |  |  | Schedule
| 11 |  |  | Con Sup | 5,096 | 5,096 | 3,530 | 3,530 | 5,072 | RTL | 4/15/19 | 4/15/20
|  |  | CONSTRUCT INTERCHANGE AT SIEMPRE VIVA ROAD | RW Cap | 0 | 0 | 0 | 0 | 0 | Begin Const | 10/15/19 | 3/30/21
|  |  |  | Con Cap | 27,189 | 27,189 | 13,791 | 13,791 | 17,899 | End Const | 6/1/21 |  | 8/1/22
|  |  |  | Total | 37,095 | 37,095 | 22,127 | 22,127 | 27,777
44 | 11 | Otay Mesa East Port of entry-Segment 3A | Near San Diego, on route 11 at 1.9 miles east of Sanyo Avenue Undercrossing. | PAED | 0 | 0 | 0 | 0 |  | Baseline |  | 6/23/21 |  | 20,750
| 0999F |  |  | PSE | 3,900 | 3,900 | 3,707 | 3,707 | 3,894 | PAED | 6/27/12 | 6/27/12
| SD |  |  | RW Sup | 4,410 | 4,410 | 1,679 | 1,679 | 4,330 | RW Cert | 7/1/21 | 11/3/21
| 11 |  |  | Con Sup | 4,150 | 0 | 0 | 0 | 4,057 | RTL | 1/4/22 | 12/6/21 |  |  | Benefits
|  |  | Site preparation to include earthwork and drainage. | RW Cap | 33,360 | 33,360 | 209 | 209 | 33,360 | Begin Const | 7/20/22 |  | 8/11/22
|  |  |  | Con Cap | 20,750 | 0 | 0 | 0 | 20,750 | End Const | 12/20/24 |  | 9/13/23
|  |  |  | Total | 66,570 | 41,670 | 5,595 | 5,595 | 66,391
45 | 11 | Route 125/905 Connector | In and near San Diego at Route 125/905 separation. | PAED | 0 | 0 | 0 | 0 |  | Baseline |  | 8/15/18 |  | 19,035
| 1036 |  |  | PSE | 4,857 | 0 | 4,848 | 0 | 4,848 | PAED | 7/30/04 | 7/30/04
| SD |  |  | RW Sup | 0 | 0 | 0 | 0 | 0 | RW Cert | 8/15/19 | 10/2/19 |  |  | Schedule
| 905,125 |  |  | Con Sup | 5,000 | 5,000 | 3,831 | 3,831 | 4,965 | RTL | 8/15/19 | 11/26/19 |  |  | Benefits
|  |  | Construct freeway to freeway South-West connector. | RW Cap | 0 | 0 | 0 | 0 | 0 | Begin Const | 3/2/20 | 8/27/20
|  |  |  | Con Cap | 28,056 | 16,980 | 15,680 | 9,491 | 19,035 | End Const | 4/4/22 |  | 8/30/23
|  |  |  | Total | 37,913 | 21,980 | 24,359 | 13,322 | 28,848
46 | 11 | Intelligent Transportation System Technology (Advanced Technology Corridors at Border Ports of Entry) | In San Diego County and Imperial County on various routes at various locations. | PAED | 818 | 0 | 710 | 0 | 710 | Baseline |  | 8/15/18 |  | 21,507
| 1241 |  |  | PSE | 4,038 | 2,317 | 4,118 | 2,306 | 4,118 | PAED | 11/16/18 | 10/15/18
| IMP,SD |  |  | RW Sup | 62 | 0 | 19 | 0 | 49 | RW Cert | 2/1/20 | 6/23/20 |  |  | Schedule
| VAR |  |  | Con Sup | 5,938 | 1,534 | 2,759 | 713 | 5,807 | RTL | 2/15/20 | 6/24/20
|  |  | Install Intelligent Technology Statewide Border Wait Time, implement a fiber optic cable network to facilitate an advanced traveler information and border wait time system connecting the entire San Diego and Imperial border network. | RW Cap | 375 | 0 | 7 | 0 | 15 | Begin Const | 7/15/20 | 4/8/21
|  |  |  | Con Cap | 27,945 | 8,118 | 10,795 | 3,275 | 21,507 | End Const | 5/20/22 |  | 8/3/23
|  |  |  | Total | 39,176 | 11,969 | 18,408 | 6,294 | 32,206
47 | 11 | Route 98 Widening | In Imperial County. | PAED | 2,957 | 0 | 2,539 | 0 | 2,539 | Baseline |  | 8/15/18 |  | 7,938
| 1258 |  |  | PSE | 1,650 | 0 | 1,748 | 0 | 1,748 | PAED | 2/18/09 | 2/18/09
| IMP |  |  | RW Sup | 1,000 | 0 | 1,013 | 0 | 1,017 | RW Cert | 7/30/19 | 12/31/19 |  |  | Schedule
| 98 |  |  | Con Sup | 1,525 | 750 | 378 | 186 | 1,491 | RTL | 8/30/19 | 2/3/20
|  |  | In Calexico from just west of State Route 111 to Rockwood Avenue. Widening Route 98 from 4 to 6 lanes. | RW Cap | 1,000 | 0 | 370 | 0 | 983 | Begin Const | 7/23/20 | 12/24/20
|  |  |  | Con Cap | 7,752 | 4,221 | 1,913 | 979 | 7,938 | End Const | 4/15/22 |  | 11/30/23
|  |  |  | Total | 15,884 | 4,971 | 7,961 | 1,165 | 15,716
EAC = Estimate at Completion |  |  | CAP = Corrective Action Plan |  | Bold | Phase allocated |  |  |  | 3 to 6 months behind schedule
Approved = Last Commission action
6+ months behind schedule or delayed beyond fiscal year or EAC over budget
[14 empty] | Page 10 | of 14
Trade Corridor Ehancement Program (TCEP) Project List
April 01 - June 30, 2022
District
| PPNO |  |  |  | Approved Budget ($1,000s) | TCEP Budget ($1,000s) | Total Expended ($1,000s) | TCEP Expended ($1,000s) |  |  | Approved Finish Date | Actual Finish Date | Current Finish Date | Award Amount ($1,000s)
County
EAC ($1,000s)
No. | Route | Title | Location and Type of Work | Phase | [5 empty] | Milestone |  |  |  |  | CAPs
48 | 11 | Otay Mesa Truck Route, Phase 4A | In San Diego at the existing east/west service road along the border fence on La Media Road. Widen and pave approximately 1.3 miles of existing service road, redirect laden/unladen trucks on dedicated route. | PAED | 0 | 0 | 0 | 0 | 0 | Baseline |  | 10/18/18 |  | 9,970
| 1334 |  |  | PSE | 0 | 0 | 0 | 0 | 0 | PAED | 2/3/16 | 2/3/16 |  |  | Cost
| SD |  |  | RW Sup | 0 | 0 | 0 | 0 | 0 | RW Cert | 12/31/18 | 4/30/19 |  |  | Schedule
|  |  |  | Con Sup | 0 | 0 | 0 | 0 | 0 | RTL | 11/30/18 | 8/28/19 |  |  | Benefits
|  |  | NULL | RW Cap | 0 | 0 | 0 | 0 | 0 | Begin Const | 6/3/19 | 2/24/20
|  |  |  | Con Cap | 12,524 | 6,000 | 6,418 | 2,996 | 15,946 | End Const | 2/28/20 |  | 2/24/23
|  |  |  | Total | 12,524 | 6,000 | 6,418 | 2,996 | 15,946
49 | 11 | Calexico East Port of Entry Truck Crossing Improvement | Near the city of Calexico, 0.7 mile south of Route 7 near the U.S./ Mexico border, at the Calexico East Port of Entry Truck Crossing. Widen bridge over the All American Canal to add truck lanes and passenger lanes along with eight foot shoulders. | PAED | 3,000 | 3,000 | 2,532 | 2,532 | 2,532 | Baseline |  | 6/23/21 |  | 23,519 | Scope
| 1335 |  |  | PSE | 3,798 | 937 | 97 | 0 | 97 | PAED | 6/1/19 | 5/20/20 |  |  | Cost
| IMP |  |  | RW Sup | 0 | 0 | 0 | 0 | 0 | RW Cert | 7/2/20 | 1/29/21 |  |  | Schedule
| 7 |  |  | Con Sup | 0 | 0 | 0 | 0 | 0 | RTL | 1/10/20 | 3/23/21 |  |  | Benefits
|  |  |  | RW Cap | 4 | 4 | 0 | 0 | 0 | Begin Const | 7/5/20 | 3/24/21
EAST CALEXICO PORT OF ENTRY BRIDGE WIDENING
|  |  |  | Con Cap | 25,736 | 6,540 | 0 | 0 | 608 | End Const | 11/5/21 |  | 2/24/23
|  |  |  | Total | 32,538 | 10,481 | 2,629 | 2,532 | 3,237
50 | 11 | La Media Road Improvements-TCEPSB1L 5004(212) | Located in the City of San Diego. | PAED | 1,245 | 0 | 1,245 | 0 | 1,245 | Baseline |  | 12/9/21 |  | 22,700
| 1435 |  |  | PSE | 1,850 | 0 | 0 | 0 | 1,850 | PAED | 6/1/21 | 6/1/21 |  |  | Cost
| SD |  |  | RW Sup | 0 | 0 | 0 | 0 | 0 | RW Cert | 11/1/21 |  | 9/30/22 |  | Schedule
|  |  |  | Con Sup | 0 | 0 | 0 | 0 | 5,300 | RTL | 12/1/21 |  | 9/30/22
|  |  | South of State Route 905 (SR-905), north of Siempre Viva Road, east of Britannia Road and west of Otay Mesa border crossing. Improving La Media Road into a six-lane primary arterial between SR-905 and Airway Road and five-lane major road between Airway Road and Siempre Viva Road with three southbound lanes and two northound lanes. | RW Cap | 5,000 | 0 | 0 | 0 | 1,800 | Begin Const | 7/1/22 |  | 1/1/23
|  |  |  | Con Cap | 34,605 | 22,700 | 0 | 0 | 40,805 | End Const | 12/1/23 |  | 6/30/24
|  |  |  | Total | 42,700 | 22,700 | 1,245 | 0 | 51,000
51 | 11 | Port of San Diego Tenth Avenue Marine Terminal Beyond Compliance Environmental Enhancement Project | In San Diego in the San Diego Bay at the Tenth Avenue Marine Terminal. Procurement of a barge-based vessel emissions capture system, also known as a Bonnet. | PAED | 0 | 0 | 0 | 0 | 0 | Baseline |  |  |  | 11,459
| T0013 |  |  | PSE | 0 | 0 | 0 | 0 | 0 | PAED | 12/13/16 | 12/13/16 |  |  | Cost
| SD |  |  | RW Sup | 0 | 0 | 0 | 0 | 0 | RW Cert |  |  |  |  | Schedule
|  |  |  | Con Sup | 0 | 0 | 0 | 0 | 0 | RTL | 10/15/19 | 12/8/21
|  |  | NULL | RW Cap | 0 | 0 | 0 | 0 | 0 | Begin Const | 12/1/19 | 6/6/22
|  |  |  | Con Cap | 7,000 | 4,900 | 4,590 | 0 | 11,459 | End Const | 12/31/22 |  | 10/3/22
|  |  |  | Total | 7,000 | 4,900 | 4,590 | 0 | 11,459
District 12
District
| PPNO |  |  |  | Approved Budget ($1,000s) | TCEP Budget ($1,000s) | Total Expended ($1,000s) | TCEP Expended ($1,000s) |  |  | Approved Finish Date | Actual Finish Date | Current Finish Date | Award Amount ($1,000s)
County
EAC ($1,000s)
No. | Route | Title | Location and Type of Work | Phase | [5 empty] | Milestone |  |  |  |  | CAPs
52 | 12 | 12-0J34U Rte 055 Construct additional HOV, GP and Aux Lane | In Orange County in Irvine, Santa Ana and Tustin on Route 5 at Newport Avenue Overcrossing and on Route 55 from 0.4 Mile North of Route 55/405 Separation to 0.1 Mile South of Route 5/55 Separation | PAED | 6,508 | 0 | 144 | 0 | 144 | Baseline |  |  |  | 213,158
| 3474 |  |  | PSE | 26,622 | 0 | 4,284 | 0 | 4,284 | PAED | 9/11/17 | 9/11/17
| ORA |  |  | RW Sup | 11,756 | 0 | 1,465 | 0 | 1,638 | RW Cert | 6/1/20 | 9/1/21 |  |  | Schedule
| 055 |  |  | Con Sup | 41,860 | 9,490 | 58 | 3 | 0 | RTL | 6/15/20 | 9/2/21
|  |  | Construct northbound auxiliary lane on Rte 55 between Dyer Road and Edinger Avenue interchanges and Widen Rte 55 for an additional high occupancy vehicle (HOV) lane and a general-purpose lane in each direction | RW Cap | 172,501 | 0 | 0 | 0 | 0 | Begin Const | 1/4/21 | 6/16/22
|  |  |  | Con Cap | 215,853 | 105,510 | 0 | 0 | 213,158 | End Const |  |  | 12/11/26
|  |  |  | Total | 475,100 | 115,000 | 5,951 | 3 | 219,224
EAC = Estimate at Completion |  |  | CAP = Corrective Action Plan |  | Bold | Phase allocated |  |  |  | 3 to 6 months behind schedule
Approved = Last Commission action
6+ months behind schedule or delayed beyond fiscal year or EAC over budget
[14 empty] | Page 11 | of 14
Trade Corridor Ehancement Program (TCEP) Project List
April 01 - June 30, 2022
District
| PPNO |  |  |  | Approved Budget ($1,000s) | TCEP Budget ($1,000s) | Total Expended ($1,000s) | TCEP Expended ($1,000s) |  |  | Approved Finish Date | Actual Finish Date | Current Finish Date | Award Amount ($1,000s)
County
EAC ($1,000s)
No. | Route | Title | Location and Type of Work | Phase | [5 empty] | Milestone |  |  |  |  | CAPs
53 | 12 | SR-57 - Lambert Road Interchange Improvements | In the City of Brea at the SR-57 & Lambert Road Interchange. | PAED | 1,000 | 0 | 0 | 0 | 0 | Baseline |  | 10/17/18 |  | 55,876
| 3834 |  |  | PSE | 6,872 | 0 | 360 | 0 | 360 | PAED | 11/25/15 | 11/25/15
| ORA |  |  | RW Sup | 0 | 0 | 0 | 0 | 0 | RW Cert | 4/1/19 | 9/24/18
| 57 |  |  | Con Sup | 16,000 | 16,000 | 10,675 | 1,221 | 13,476 | RTL | 5/1/19 | 9/24/18
|  |  | Reconfiguration of northbound ramps including construction of a loop on-ramp at the south-east quadrant; modify NB off-ramp; lower Lambert Road and widen NB Lambert Road UC bridge to to accommodate future truck-climbing lane. | RW Cap | 12,458 | 0 | 0 | 0 | 0 | Begin Const | 1/2/20 | 5/13/19
|  |  |  | Con Cap | 71,103 | 49,705 | 45,474 | 3,199 | 55,876 | End Const | 1/2/23 |  | 12/1/22
|  |  |  | Total | 107,433 | 65,705 | 56,509 | 4,420 | 69,712
District 75
District
| PPNO |  |  |  | Approved Budget ($1,000s) | TCEP Budget ($1,000s) | Total Expended ($1,000s) | TCEP Expended ($1,000s) |  |  | Approved Finish Date | Actual Finish Date | Current Finish Date | Award Amount ($1,000s)
County
EAC ($1,000s)
No. | Route | Title | Location and Type of Work | Phase | [5 empty] | Milestone |  |  |  |  | CAPs
54 | 75 | Rosecrans / Marquardt Grade Seperation | In Santa Fe Springs, at the intersection of Rosecrans Avenue and Marquardt Avenue, on the BNSF Right of Way. | PAED | 1,970 | 0 | 0 | 0 |  | Baseline |  | 10/17/17 |  | 48,376 | Scope
| 2002A |  |  | PSE | 6,360 | 0 | 0 | 0 | 0 | PAED | 11/7/18 | 3/1/16 |  |  | Cost
| LA |  |  | RW Sup | 0 | 0 | 0 | 0 | 0 | RW Cert | 5/21/20 | 12/22/20 |  |  | Schedule
|  |  |  | Con Sup | 0 | 0 | 0 | 0 | 0 | RTL | 6/19/20 | 8/5/21 |  |  | Benefits
|  |  | Construct grade separation at Rosecrans/Marquardt Avenue (Parent project = PPNO 2002). | RW Cap | 68,738 | 0 | 0 | 0 | 0 | Begin Const | 12/24/20 | 6/13/22
|  |  |  | Con Cap | 81,370 | 9,000 | 0 | 0 | 0 | End Const | 3/1/23 |  | 9/30/24
|  |  |  | Total | 158,438 | 9,000 | 0 | 0 | 0
55 | 75 | San Onofre to Pulgas Double Track Phase 2 | In Camp Pendleton along the LOSSAN corridor, from MP 216.5 to MP 218.1, construct 1.6 miles of additional second main track capacity adjacent to the main track, including new bridges at MP 217.3 and MP 218. | PAED | 0 | 0 | 0 | 0 |  | Baseline |  | 6/23/21 |  | 0
| 2190 |  |  | PSE | 1,744 | 567 | 0 | 0 | 1,744 | PAED | 3/31/12 | 3/31/12
| SD |  |  | RW Sup | 0 | 0 | 0 | 0 | 0 | RW Cert | 9/1/21 |  | 6/30/23 |  | Schedule
|  |  |  | Con Sup | 0 | 0 | 0 | 0 | 0 | RTL | 9/1/21 |  | 6/30/23
|  |  | NULL | RW Cap | 0 | 0 | 0 | 0 | 0 | Begin Const | 1/1/22 |  | 12/30/23
|  |  |  | Con Cap | 33,793 | 4,930 | 0 | 0 | 33,793 | End Const | 7/1/24 |  | 12/30/25
|  |  |  | Total | 35,537 | 5,497 | 0 | 0 | 35,537
56 | 75 | Stockton Diamond Grade Separation | In the City of Stockton, the two BNSF Stockton Subdivision mainline tracks running in an east-west direction cross at-grade perendicularly with the two UPPR Fresno Subdivion mainline tracks running in a north-south direction. | PAED | 3,500 | 0 | 0 | 0 |  | Baseline |  | 12/8/21 |  | 0
| 9883 |  |  | PSE | 13,500 | 0 | 0 | 0 | 13,500 | PAED | 6/1/21 | 6/1/21 |  |  | Cost
| SJ |  |  | RW Sup | 0 | 0 | 0 | 0 | 0 | RW Cert | 2/1/23 |  | 2/1/23
| UP |  |  | Con Sup | 0 | 0 | 0 | 0 | 0 | RTL | 2/1/23 |  | 2/1/23 |  | Benefits
|  |  | The at-grade crossing is know as "Stockton Diamond" and is also refferred to as Keddie Junction by the host railroads. The scope of the Project involves the completion of PS&E and RW for the construction of a flyover structure to provide the vertical clearance required by both railroads. The flyover structure will span the length of the Stockton Diamond and eliminate the interference between the two railroads. Scope will also involve railroad coordination and approvals, including operational modeling and analysis and right of way consultation for property owned by the railroads. | RW Cap | 13,200 | 0 | 0 | 0 | 13,200 | Begin Const | 6/1/23 |  | 6/1/23
|  |  |  | Con Cap | 206,933 | 100,000 | 0 | 0 | 206,933 | End Const | 6/30/26 |  | 6/30/26
|  |  |  | Total | 237,133 | 100,000 | 0 | 0 | 233,633
EAC = Estimate at Completion |  |  | CAP = Corrective Action Plan |  | Bold | Phase allocated |  |  |  | 3 to 6 months behind schedule
Approved = Last Commission action
6+ months behind schedule or delayed beyond fiscal year or EAC over budget
[14 empty] | Page 12 | of 14
Trade Corridor Ehancement Program (TCEP) Project List
April 01 - June 30, 2022
District
| PPNO |  |  |  | Approved Budget ($1,000s) | TCEP Budget ($1,000s) | Total Expended ($1,000s) | TCEP Expended ($1,000s) |  |  | Approved Finish Date | Actual Finish Date | Current Finish Date | Award Amount ($1,000s)
County
EAC ($1,000s)
No. | Route | Title | Location and Type of Work | Phase | [5 empty] | Milestone |  |  |  |  | CAPs
57 | 75 | San Dieguito Double Track Phase 1 | This project is Phase 1 of the San Dieguito River Double Track project. | PAED | 0 | 0 | 0 | 0 |  | Baseline |  | 6/23/21 |  | 0 | Scope
| LP003 |  |  | PSE | 4,234 | 0 | 0 | 0 | 4,234 | PAED | 1/5/16 | 1/5/16 |  |  | Cost
| SD |  |  | RW Sup | 0 | 0 | 0 | 0 | 0 | RW Cert | 7/30/22 |  | 3/27/23 |  | Schedule
|  |  |  | Con Sup | 0 | 0 | 0 | 0 | 0 | RTL | 7/31/22 |  | 3/28/23 |  | Benefits
|  |  | Phase 1 will provide a second main track from CP Valley (MP 242.2) to the north end of the existing San Dieguito Lagoon trestle bridge (MP 243.0), adding 0.8 miles of double track. Signal work will be required beyond the construction limits on either end of the project, estimated to be between MP 241.1 to 243.9. When combined with existing double track south of Solana Beach Station (MP 241.8) and the addition of a new crossover this second track will provide a freight passing area north of the San Dieguito River. A freight passing track is required at this location to increase freight capacity in San Diego per the April 2020 Draft “Freight Pathing between CP Atwood and the Port of San Diego and passenger service extensions south of San Diego” study commissioned (Freight Pathing Study) by BNSF and NCTD and prepared by DB Engineering & Consulting. | RW Cap | 1,250 | 0 | 0 | 0 | 1,250 | Begin Const | 3/31/23 |  | 10/27/23
|  |  |  | Con Cap | 56,329 | 30,528 | 0 | 0 | 56,329 | End Const | 8/31/25 |  | 11/3/25
|  |  |  | Total | 61,813 | 30,528 | 0 | 0 | 61,813
58 | 75 | Quiet Zone Safety Engineering Measures | In Emeryville, at three at-grade crossings on 65th Street, 66th Street, and 67th Street just east of Shellmound Street. | PAED | 75 | 0 | 75 | 0 | 75 | Baseline |  | 10/17/18 |  | 4,200 | Scope
| T0004 |  |  | PSE | 590 | 0 | 590 | 0 | 590 | PAED | 5/1/18 | 7/20/18 |  |  | Cost
| ALA |  |  | RW Sup | 0 | 0 | 0 | 0 | 0 | RW Cert | 4/1/19 | 2/1/21 |  |  | Schedule
|  |  |  | Con Sup | 0 | 0 | 0 | 0 | 0 | RTL | 2/1/19 | 2/1/21
|  |  | Install four quadrant gates, raised median, and sidewalks at three at-grade railroad crossings. | RW Cap | 0 | 0 | 0 | 0 | 0 | Begin Const | 9/1/19 | 2/15/22
|  |  |  | Con Cap | 8,210 | 4,200 | 0 | 0 | 8,200 | End Const | 5/1/20 |  | 6/30/23
|  |  |  | Total | 8,875 | 4,200 | 665 | 0 | 8,865
59 | 75 | Montebello Boulevard Grade Separation Project | In the City of Montebello, on Montebello Boulevard between Olympic Boulevard and Roosevelt Avenue. Separarte the roadway tracks on Montebello Boulevard in the City of Montebello, along the Alameda Corridor-East Trade Corridor. | PAED | 0 | 0 | 0 | 0 | 0 | Baseline |  |  |  | 0
| T0008 |  |  | PSE | 19,897 | 0 | 17,836 | 0 | 19,897 | PAED | 6/1/18 | 10/3/17 |  |  | Cost
| LA |  |  | RW Sup | 0 | 0 | 0 | 0 | 0 | RW Cert | 10/1/19 | 10/5/20 |  |  | Schedule
|  |  |  | Con Sup | 0 | 0 | 0 | 0 | 0 | RTL | 8/1/18 |  | 1/31/23 |  | Benefits
|  |  | NULL | RW Cap | 33,500 | 0 | 20,965 | 0 | 33,500 | Begin Const | 1/1/20 |  | 5/23/23
|  |  |  | Con Cap | 126,557 | 49,000 | 0 | 0 | 126,557 | End Const | 1/1/24 |  | 5/31/27
|  |  |  | Total | 179,954 | 49,000 | 38,801 | 0 | 179,954
60 | 75 | Turnbull Canyon Road Grade Separation Project | In the City of Industry and unincorporated Los Angeles County, along the Alameda Corridor-East Trade Corridor at Turnbull Canyon Road. | PAED | 0 | 0 | 0 | 0 |  | Baseline |  |  |  | 0
| T0009 |  |  | PSE | 10,106 | 0 | 0 | 0 | 10,106 | PAED | 6/1/18 | 10/23/17 |  |  | Cost
| LA |  |  | RW Sup | 0 | 0 | 0 | 0 | 0 | RW Cert | 5/1/21 |  | 5/1/23 |  | Schedule
|  |  |  | Con Sup | 0 | 0 | 0 | 0 | 0 | RTL | 7/1/21 |  | 7/1/23 |  | Benefits
|  |  | Replace at-grade crossing with a new grade separated undercrossing. Add sidewalks and bike lanes. | RW Cap | 33,885 | 0 | 0 | 0 | 33,885 | Begin Const | 1/30/22 |  | 4/1/24
|  |  |  | Con Cap | 42,255 | 29,000 | 0 | 0 | 42,255 | End Const | 10/30/23 |  | 4/1/27
|  |  |  | Total | 86,246 | 29,000 | 0 | 0 | 86,246
61 | 75 | Etiwanda Avenue Grade Separation | In the City of Rancho Cucamonga, Etiwanda Avenue Grade Separation at SCRRA and BNSF San Gabriel Rail Line, between Whittram Avenue and Napa Street. | PAED | 850 | 0 | 0 | 0 |  | Baseline |  | 8/15/18 |  | 0
| T0011 |  |  | PSE | 5,000 | 5,000 | 0 | 0 | 5,000 | PAED | 6/6/18 | 6/6/18
| SBD |  |  | RW Sup | 0 | 0 | 0 | 0 | 0 | RW Cert | 9/30/22 |  | 9/30/23 |  | Schedule
|  |  |  | Con Sup | 0 | 0 | 0 | 0 | 0 | RTL | 9/30/22 |  | 9/30/23
|  |  | The project will replace an existing at-grade crossing with a new grade-separated overcrossing and construct side-walk and bike lane. | RW Cap | 18,000 | 18,000 | 0 | 0 | 18,000 | Begin Const | 12/12/22 |  | 10/30/23
|  |  |  | Con Cap | 52,150 | 52,150 | 0 | 0 | 52,150 | End Const | 12/12/24 |  | 12/30/25
|  |  |  | Total | 76,000 | 75,150 | 0 | 0 | 75,150
EAC = Estimate at Completion |  |  | CAP = Corrective Action Plan |  | Bold | Phase allocated |  |  |  | 3 to 6 months behind schedule
Approved = Last Commission action
6+ months behind schedule or delayed beyond fiscal year or EAC over budget
[14 empty] | Page 13 | of 14
Trade Corridor Ehancement Program (TCEP) Project List
April 01 - June 30, 2022
District
| PPNO |  |  |  | Approved Budget ($1,000s) | TCEP Budget ($1,000s) | Total Expended ($1,000s) | TCEP Expended ($1,000s) |  |  | Approved Finish Date | Actual Finish Date | Current Finish Date | Award Amount ($1,000s)
County
EAC ($1,000s)
No. | Route | Title | Location and Type of Work | Phase | [5 empty] | Milestone |  |  |  |  | CAPs
62 | 75 | Sorrento to Miramar, Phase 2 Intermodal Improvements | In the city of San Diego along the LOSSAN rail corridor from Mile Post (MP) 250.9 near I-805 to MP 253 near Miramar Road. | PAED | 0 | 0 | 0 | 0 |  | Baseline |  | 10/18/18 |  | 0
| T0014 |  |  | PSE | 6,037 | 0 | 0 | 0 | 11,400 | PAED | 6/30/18 | 6/30/18 |  |  | Cost
| SD |  |  | RW Sup | 0 | 0 | 0 | 0 | 0 | RW Cert | 7/1/20 |  | 6/30/24 |  | Schedule
|  |  |  | Con Sup | 0 | 0 | 0 | 0 | 0 | RTL | 7/1/20 |  | 6/30/24
|  |  | Add double-track, curve straightening, and new signals. | RW Cap | 15,000 | 10,500 | 0 | 0 | 15,000 | Begin Const | 12/30/20 |  | 12/30/24
|  |  |  | Con Cap | 108,000 | 0 | 0 | 0 | 200,000 | End Const | 7/30/24 |  | 7/30/28
|  |  |  | Total | 129,037 | 10,500 | 0 | 0 | 226,400
63 | 75 | Del Mar Bluffs Phase 5 | In the City of Del Mar from MP 244.1 near Coast Boulevard to MP 245.7 at Carmel Valley Road on the San Diego Subdivision of the Los Angeles-San Diego-San Luis Obispo (LOSSAN) Corridor. | PAED | 3,073 | 0 | 3,073 | 0 | 3,073 | Baseline |  | 6/23/21 |  | 0
| T0015 |  |  | PSE | 3,774 | 0 | 0 | 0 | 3,774 | PAED | 6/2/21 | 6/2/21
| SD |  |  | RW Sup | 0 | 0 | 0 | 0 | 0 | RW Cert | 6/15/21 | 6/15/21
|  |  |  | Con Sup | 0 | 0 | 0 | 0 | 0 | RTL | 8/30/22 |  | 8/30/22
|  |  | Stabilize eroding areas of the Del Mar Bluffs. Stabilization efforts planned include installation of piles, lagging and retaining walls, drainage improvements and piped outlets to the beach, and other stabilization and erosion control measures on the upper bluffs. | RW Cap | 188 | 0 | 0 | 0 | 188 | Begin Const | 3/30/23 |  | 3/30/23
|  |  |  | Con Cap | 58,161 | 36,200 | 0 | 0 | 58,161 | End Const | 3/30/25 |  | 3/30/25
|  |  |  | Total | 65,196 | 36,200 | 3,073 | 0 | 65,196
64 | 75 | Broadway to Gaslamp Track Signalization and Platform | The Project involves the signalization of a 0.8-mile stretch of BNSF track from the Broadway crossing near Santa Fe Depot (MP 267.7) to the 5th Avenue crossing (MP268.5) in Downtown San Diego. | PAED | 0 | 0 | 0 | 0 | 0 | Baseline |  | 6/23/21 |  | 25,000 | Scope
| T0016 |  |  | PSE | 388 | 0 | 388 | 0 | 388 | PAED | 8/1/21 | 8/1/21 |  |  | Cost
| SD |  |  | RW Sup | 0 | 0 | 0 | 0 | 0 | RW Cert | 9/1/22 |  | 4/30/23 |  | Schedule
|  |  |  | Con Sup | 0 | 0 | 0 | 0 | 0 | RTL | 3/1/23 |  |  |  | Benefits
|  |  | Three new control points would be required for the new signalization. Positive Train Control (PTC) would be extended to cover this new service territory. Right of Way acquisition, or lease of BNSF property, as well as additional trackwork, crossing improvements, and landscaping are also included in the Project. It also involves the construction of a new siding and station platform between 1st 5th Avenues to alleviate a track capacity bottleneck at the Santa Fe Depot for freight trains passing through the station by terminating commuter trains at the new platform instead of the Depot. | RW Cap | 293 | 0 | 0 | 0 | 293 | Begin Const | 9/1/23 | 3/22/22
|  |  |  | Con Cap | 38,180 | 33,180 | 0 | 0 | 33,180 | End Const | 10/1/25 |  | 4/1/26
|  |  |  | Total | 38,861 | 33,180 | 388 | 0 | 33,861
65 | 75 | East Basin Rail Gateway Expansion: Fourth Track at Ocean | The Fourth Track at Ocean is located within POLB property along a Port-owned rail corridor that serves the easterly marine terminals at Middle Harbor, Pier G, and Pier J, which are collectively known as the East Basin. | PAED | 1,098 | 0 | 1,361 | 0 | 1,361 | Baseline |  | 7/16/21 |  | 8,000 | Scope
| T0019 |  |  | PSE | 3,172 | 0 | 2,976 | 0 | 2,976 | PAED | 10/15/19 | 10/15/19 |  |  | Cost
| LA |  |  | RW Sup | 0 | 0 | 0 | 0 | 0 | RW Cert | 6/1/21 | 7/6/21 |  |  | Schedule
|  |  |  | Con Sup | 0 | 0 | 0 | 0 | 0 | RTL | 8/26/21 | 10/28/21 |  |  | Benefits
|  |  | The Project site in Long Beach lies immediately west of the Los Angeles River and Interstate 710 (I-710), a major truck route. The Project’s value is amplified by its proximity to and relationship with the Alameda Corridor, a critical connector to the transcontinental rail network, and with the planned Pier B On-Dock Rail Support Facility at POLB. | RW Cap | 1,005 | 0 | 86 | 0 | 1,005 | Begin Const | 12/13/21 | 2/14/22
|  |  |  | Con Cap | 19,525 | 8,000 | 195 | 0 | 19,657 | End Const | 10/23/23
|  |  |  | Total | 24,800 | 8,000 | 4,618 | 0 | 24,999
EAC = Estimate at Completion |  |  | CAP = Corrective Action Plan |  | Bold | Phase allocated |  |  |  | 3 to 6 months behind schedule
Approved = Last Commission action
6+ months behind schedule or delayed beyond fiscal year or EAC over budget
[14 empty] | Page 14 | of 14