## SCCP Q3 Project List
ATTACHMENT 1 Solutions for Congested Corridors Program Project List - January 1, 2019 to March31, 2019 | [5 empty] | PAED | [5 empty] | PSE | [5 empty] | RW Support | [5 empty] | CON Support |  |  |  | RTL |  |  | RW Capital |  |  |  | CON Capital | [9 empty] | Total Project
No. | PPNO | County | District | Project Name | Project Description | Approved Budget ($1,000s) | SCCP Budget ($1,000s) | Expended | EAC | Actual Finish Date | Expended ($1,000s) | Approved Budget | SCCP Budget | EAC | Approved Finish Date | Actual Finish Date | Current Finish Date | Approved Budget | SCCP Budget | EAC Support | Approved RW Cert | Actual RW Cert | Current RW Cert | Approved Budget | SCCP Budget | Expended | EAC | Approved RTL | Actual RTL | Current RTL | Approved Budget | SCCP Budget | Expended | EAC | Approved Begin Con | Actual Begin Con | Current Begin Con | Approved Budget | SCCP Budget | Expended | EAC | Approved End Con | Current End Con | SCCP Award Amount ($1,000s) | Total Approved Budget | Total SCCP Budget | Total Expended | EAC Total
1 | 1787 | SAC | 03 | US 50 Multimodal Corridor Enhancement Project / Gold Line Light Rail Improvements Between Sunrise Blvd to Downtown Folsom | In Sacramento County, from Sacramento Valley Station to the Downtown Folsom Station. This project will enhance the light rail capacity on the Gold Line. The project consists of the construction of track sidings to allow trains to pass in the section of single tracks on the Gold Line between the Sunrise Station and Historic Folsom Station. This will permit trains to operate with 15-minute frequencies between those stations, where they currently operate with 30-minute frequencies. The additional frequencies will increase ridership and reduce vehicle miles traveled (VMT) on US-50. This will also help improve the traffic signal phasing for all the roadway intersections along Folsom Blvd. in Folsom, thus improving roadway traffic flow. This project is a co-applicant with the Caltrans Sacramento US 50 HOV Project from I-5 to Watt Ave for the SB1 Solutions for Congested Corridor Program funds. | 2568 | 0 | 0 | 2568 | 2019-04-03 |  | 3852 | 0 | 3852 | 2019-08-31 |  | 2019-08-31 | 0 | 0 | 0 | 2019-12-31 |  | 2019-12-31 | 0 | 0 | 0 | 0 | 2020-05-01 |  | 2020-05-01 | 1363 | 0 | 0 | 1363 | 2020-11-01 |  | 2020-11-01 | 40612 | 20300 | 0 | 40612 | 2022-10-31 | 2022-10-31 | 0 | 48395 | 20300 | 0 | 48395
2 | 1788 | SAC | 03 | Franklin Boulevard Cycle Track Phase 1 | In Sacramento County, construction of Class IV Bikeways parallel to I-5 on Franklin Boulevard from Big Horn Blvd in the City of Elk Grove to the Cosumnes River Light Rail Station at the intersection of Franklin Blvd and Cosumnes River Blvd in the City of Sacramento. The City of Sacramento project an additional 3,700 feet in the City of Elk Grove ending at Big Horn Boulevard. | 16 | 0 | 0 | 0 |  |  | 35 | 0 | 22 |  | 2018-07-13 |  | 0 | 0 | 0 |  | 2019-04-22 |  | 0 | 0 | 0 | 0 |  | 2019-04-23 |  | 0 | 0 | 0 | 0 |  |  | 2019-11-05 | 200 | 200 | 0 | 200 |  | 2020-02-12 | 0 | 251 | 200 | 3 | 222
3 | 3301 | SAC | 03 | US 50 Multimodal Corridor Enhancement Project/US 50 HOV Lanes(I-5 to Watt Ave) | In Sacramento County on US 50, from I-5 to 0.8 mile east of Watt Avenue. Construct 14 lane miles of HOV (or bus/carpool) lanes, widen twelve bridge structures, construct sound walls from Stockton Blvd to 65th Street, incorporate Intelligent Transportation System (ITS) elements into the HOV system, and replace and/or upgrade ancillary facilities including drainage systems, overhead signs, lighting, approach slabs, guard rail, and safety barriers. | 13617 | 0 | 5796 | 5796 | 2019-02-25 |  | 11400 | 0 | 9999 | 2017-05-31 | 2017-05-31 17:00 |  | 4300 | 0 | 931 | 2020-02-03 |  | 2020-02-03 17:00 | 35800 | 10000 | 0 | 0 | 2020-02-14 |  | 2020-02-14 17:00 | 4461 | 0 | 391 | 5504 | 2020-07-15 |  | 2020-08-15 17:00 | 372906 | 80000 | 182 | 76630 | 2024-12-01 | 2024-12-01 17:00 | 0 | 442484 | 90000 | 15564 | 98860
4 | 5854A | SAC | 03 | Sac 5 Corridor Enhancement Project | In Sacramento, from 1.1 miles south of Elk Grove Blvd Overcrossing to Route 50 at American River Br (Br#24-68).. Roadway rehabilitation, construct HOV lanes, and install fiber optic cable Roadway rehabilitation, construct HOV lanes, and install fiber optic cable | 0 | 0 | 5594 | 5594 |  |  | 0 | 0 | 0 |  |  |  | 2129 | 0 | 2571 |  |  |  | 31570 | 1280 | 0 | 29193 |  |  |  | 0 | 0 | 711 | 0 |  |  | 2019-05-27 17:00 | 303190 | 13520 | 0 | 302341 |  | 2022-12-15 17:00 | 0 | 336889 | 14800 | 26079 | 358185
5 | 0360Q | SON | 04 | Marin Sonoma Narrows Segment C2 - HOV Lanes Gap Closure | In Sonoma, Highway 101 and 116 connection to 0. 3 miles north of Corona Road; Construct HOV lanes and sound walls. | 0 | 0 | 0 | 0 | 2019-02-25 |  | 227 | 0 | 0 | 2009-10-29 | 2009-10-29 17:00 |  | 2000 | 0 | 1735 | 2018-12-30 | 2018-12-31 17:00 |  | 14000 | 12600 | 0 | 12036 | 2018-12-30 | 2018-12-31 17:00 |  | 6570 | 0 | 5428 | 6570 | 2019-08-21 |  | 2019-09-20 17:00 | 91000 | 72191 | 0 | 70605 | 2022-08-21 | 2022-08-22 17:00 | 0 | 113797 | 84791 | 6820 | 90946
6 | 0658D | SCL | 04 | US 101 Managed Lanes Project - Northern Segment | In the cities of San Carlos, Millbrae, Burlingame, San Mateo and Belmont in San Mateo County, and Menlo Park and East Palo Alto in Santa Clara County, from Matadero Creek to just North of I-380. Construct Express Lanes, from Whipple Avenue to just North of I-380 and install necessary Express Lanes infrastructure for both northern and southern segments. | 23749 | 0 | 16493 | 16493 | 2018-10-19 15:44 |  | 40027 | 0 | 21396 | 2018-10-15 | 2018-10-31 17:00 |  | 2000 | 0 | 1204 | 2019-05-01 |  | 2019-06-30 17:00 | 34000 | 16500 | 0 | 33755 | 2019-05-01 |  | 2019-08-30 17:00 | 16000 | 0 | 0 | 2730 | 2019-07-01 |  | 2019-11-15 17:00 | 328495 | 108690 | 0 | 328495 |  | 2021-07-01 17:00 | 0 | 444271 | 125190 | 26926 | 404073
7 | 0658H | SCL | 04 | US 101 Managed Lanes Project - Southern Segment | In Palo Alto, from 2 miles south of the Santa Clara County Line to Whipple Avenue Interchange. Convert existing HOV Lanes to Express Lanes. | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 2018-10-31 | 2018-10-31 |  | 0 | 0 | 0 | 2018-11-05 | 2018-11-05 |  | 7000 | 7000 | 361 | 6236 | 2018-11-05 | 2018-11-05 |  | 0 | 0 | 0 | 0 | 2019-01-04 | 2019-01-04 |  | 67810 | 67810 | 2180 | 66000 | 2020-11-04 | 2020-11-04 | 0 | 74810 | 74810 | 2541 | 72236
8 | 2015E | SCL | 04 | Silicon Valley Express Lanes Program - Phase 3 | On US 101 from SR 237 to the Santa Clara/San Mateo county line and on SR 85 from SR 237 to the SR 85/US 101 interchange. The project will: Convert existing single carpool lanes to express lanes at the following locations: US 101 from near SR 237 north to SR 85 (in Mountain View) SR 85 from SR 237 north to US 101 (in Mountain View) including the existing US 101/SR 85 carpool lane-to-carpool lane direct connector ramps Convert existing double carpool lanes to double express lanes on US 101 from SR 85 (in Mountain View) to the San Mateo County line in Palo Alto. | 0 | 0 | 0 | 0 | 2018-10-19 15:50 |  | 8700 | 0 | 0 | 2015-08-11 | 2015-08-11 17:00 |  | 0 | 0 | 0 | 2018-07-01 | 2018-06-29 17:00 |  | 0 | 0 | 0 | 0 | 2018-07-01 | 2018-06-29 17:00 |  | 518 | 0 | 0 | 0 | 2018-12-01 | 2018-12-07 17:00 |  | 47468 | 33200 | 0 | 47468 |  | 2021-09-29 17:00 | 33200 | 56686 | 33200 | 0 | 47468
9 | 2893 | SB | 05 | North Padaro Lane Coastal Access Improvements | In the County of Santa Barbara, south of community of Summerland along North Padaro Lane on the coast side of Highway 101. Construct 0.2 miles of sidewalk to complete gap in California Coastal Trail between Highway 101 and Loon Point Beach Parking area where coastal access exists. Add coastal trail signage along North Padaro Lane and for vertical acess to beach. | 60 | 0 | 0 | 0 | 2018-10-17 |  | 220 | 0 | 0 | 2019-03-01 |  | 2019-07-31 | 0 | 0 | 0 | 2020-03-31 |  | 2020-03-31 | 0 | 0 | 0 | 0 | 2020-03-31 |  | 2020-07-31 | 140 | 0 | 0 | 0 | 2022-01-01 |  | 2021-04-01 | 3270 | 3270 | 0 | 0 | 2022-12-31 | 2022-03-31 | 0 | 3690 | 3270 | 0 | 0
10 | 2894 | SB | 05 | Summerland Area Coastal Access Improvements | In the County of Santa Barbara, in and near the community of Summerland, on Via Real, Wallace Avenue and Finney Road on both the inland and coastal side of Highway 101. Construct 0.4 miles of sidewalk and add coastal access parking along Wallace Avenue. Along Via Real, construction 0. 4 miles of sidewalk to complete gap in California Coastal Trail between Greenwell Drive and North Padaro Lane and add a Class I multi purpose path. | 300 | 0 | 0 | 0 | 2018-10-17 |  | 680 | 0 | 0 | 2019-04-30 |  | 2019-09-25 | 0 | 0 | 0 | 2020-10-31 |  | 2020-10-31 | 0 | 0 | 0 | 0 | 2020-10-31 |  | 2020-10-31 | 520 | 0 | 0 | 0 | 2021-07-01 |  | 2021-07-01 | 8320 | 8320 | 0 | 0 | 2022-06-30 | 2022-06-30 | 0 | 9820 | 8320 | 0 | 0
11 | 2896 | SB | 05 | Santa Claus Lane Class I Bikeway | In in City of Carpinteria through Summerland between Carpinteria Avenue and Santa Claus Lane. Construct 0. 6 miles Class I bikeway to close a gap in the California Coastal Trail (CCT). | 500 | 0 | 0 | 0 | 2018-10-17 |  | 420 | 0 | 0 | 2019-02-01 |  | 2019-06-30 | 0 | 0 | 0 | 2020-01-01 |  | 2020-01-01 | 0 | 0 | 0 | 0 | 2020-01-01 |  | 2020-01-01 | 400 | 0 | 0 | 0 | 2020-07-01 |  | 2020-07-01 | 6830 | 6830 | 0 | 0 | 2021-03-31 | 2021-03-31 | 0 | 8150 | 6830 | 0 | 0
12 | 2897 | SB | 05 | Santa Claus Lane Streetscape, Coastal Access Parking and Railroad Crossing | Construct Class I bikeway along Santa Claus Lane (County of Santa Barbara) from Sandpoint Drive to South Padaro Lane to close a gap in the California Coastal Trail (CCT). To construct coastal access parking and improved and safe beach access across railroad tracks of UPRR. | 0 | 0 | 0 | 0 | 2018-10-17 |  | 800 | 0 | 0 | 2018-09-30 |  | 2019-09-30 | 0 | 0 | 0 | 2020-03-31 |  | 2020-03-31 | 0 | 0 | 0 | 0 | 2020-03-31 |  | 2020-03-31 | 200 | 0 | 0 | 0 | 2020-10-01 |  | 2020-10-01 | 7040 | 7040 | 0 | 0 | 2021-06-30 | 2021-06-30 | 0 | 8040 | 7040 | 0 | 0
13 | 2985 | SB | 05 | Santa Monica Road and Via Real Intersection Improvements | At the intersection of Santa Monica Road, Via Real and the Santa Monica NB on and off ramp from Highway 101. Construct intersection improvements to address forecast operational deficiencies at this all-way stop intersection. | 750 | 0 | 5 | 59 | 2019-01-29 |  | 450 | 0 | 216 | 2019-08-01 |  | 2019-05-08 17:00 | 300 | 0 | 1 | 2021-01-01 |  | 2020-10-05 17:00 | 750 | 750 | 0 | 12 | 2021-03-01 |  | 2020-12-02 17:00 | 379 | 0 | 0 | 799 | 2021-09-01 |  | 2021-06-09 17:00 | 2860 | 2860 | 0 | 2860 | 2023-09-01 | 2023-06-09 17:00 | 0 | 5489 | 3610 | 5 | 3947
14 | 7101C | SB | 05 | South Coast 101 HOV Lanes - Carpinteria (Segment 4A) | In Santa Barbara County, in Carpinteria from 0.2 miles south of Bailard Avenue to 0.5 miles south of S. Padaro Lane. Construct HOV lanes. This is a grandchild of parent project 05-0N700 (PPNO 7101) and child of parent 05-0N70A (PPNO 7101A). | 12245 | 0 | 0 | 0 | 2019-03-20 |  | 8320 | 0 | 3244 | 2014-08-26 | 2014-08-26 |  | 920 | 0 | 1033 | 2019-11-01 |  | 2020-01-15 | 22060 | 0 | 0 | 10191 | 2019-11-15 |  | 2020-01-31 | 5740 | 0 | 40 | 5423 | 2020-07-31 |  | 2020-08-14 | 86500 | 0 | 0 | 50810 |  | 2024-02-21 | 0 | 135785 | 0 | 671 | 70701
15 | 7101D | SB | 05 | South Coast 101 HOV-Padaro (Segment 4B) | In Santa Barbara County, near Carpinteria and Summerland from 0.9 miles south of S. Padaro Lane Undercrossing to 0.6 miles north of Padaro Lane Overcrossing. Construct HOV lanes. This is a grandchild of parent project 05-0N700 (PPNO 7101) and child of parent 05-0N70A (PPNO 7101A). | 2725 | 0 | 0 | 0 | 2019-03-20 |  | 10025 | 0 | 6099 | 2014-08-26 | 2014-08-26 17:00 |  | 1010 | 0 | 689 | 2020-11-01 |  | 2020-10-30 17:00 | 29990 | 12250 | 0 | 12931 | 2021-01-01 |  | 2020-12-31 17:00 | 10490 | 0 | 0 | 0 | 2021-07-15 |  | 2021-07-15 17:00 | 139310 | 49560 | 0 | 89150 | 2025-12-15 | 2025-10-02 17:00 | 0 | 193550 | 61810 | 174 | 108869
16 | 7101E | SB | 05 | South Coast 101 HOV-Summerland (Segment 4C) | In Santa Barbara County, in and near Summerland from 0.2 miles north of Padaro Lane Overcrossing to San Ysidro Creek Bridge. Construct HOV lanes. | 2380 | 0 | 0 | 0 | 2019-01-29 |  | 7280 | 0 | 748 | 2014-08-26 | 2014-08-26 08:00 |  | 520 | 0 | 0 | 2020-11-01 |  | 2020-10-30 17:00 | 17720 | 7940 | 0 | 10103 | 2021-01-01 |  | 2020-12-31 17:00 | 3930 | 0 | 0 | 0 | 2021-07-15 |  | 2021-07-15 17:00 | 88470 | 34060 | 0 | 60240 | 2025-12-15 | 2025-08-29 17:00 | 0 | 120300 | 42000 | 0 | 71091
17 | 5497 | LA | 07 | Airport Metro Connector 96th Street Transit Station | In Los Angeles near Aviation Boulevard / 96th Street. Construct new multi-modal transit station for the Metro Crenshaw / Los Angeles International (LAX) Line that will also add a stop to the Metro Green Line. Multi-modal transit station will include Light Rail Station, transit station/terminal building, bus plaza, bicycle hub, pedestrian improvements and passenger pickup/drop-off area. | 15750 | 0 | 0 | 0 | 2018-10-18 |  | 29250 | 0 | 0 | 2017-05-02 | 2017-05-02 |  | 0 | 0 | 0 | 2019-07-30 |  | 2019-07-30 | 0 | 0 | 0 | 0 | 2019-07-30 |  | 2019-07-30 | 76200 | 0 | 0 | 0 | 2019-12-31 |  | 2019-12-31 | 404000 | 150000 | 0 | 0 | 2023-06-01 | 2023-06-30 | 0 | 525200 | 150000 | 0 | 0
18 | 1230 | SBD | 08 | Redlands Passenger Rail Project | Located at five station locations: San Bernardino Transit Center, Tippecanoe Avenue Station, New York Street Station, Downtown Redlands Station, and the University Station. The rail service will run between San Bernardino Transit Center located at Rialto Avenue and E Street in downtown San Bernardino adjacent to San Manuel Stadium and will terminate at the University of Redlands. Construct nine-miles of Rail line. | 11384 | 0 | 11453 | 11453 | 2018-10-18 |  | 42340 | 0 | 27270 | 2015-02-01 | 2015-02-01 |  | 0 | 0 | 0 | 2018-07-15 | 2018-09-17 |  | 0 | 0 | 0 | 0 | 2018-08-01 | 2018-09-17 |  | 7866 | 0 | 7893 | 33426 | 2019-03-01 | 2019-04-17 |  | 230330 | 65000 | 16180 | 255899 | 2021-05-31 | 2021-11-30 | 0 | 291920 | 65000 | 62796 | 328048
19 | 0615F | SD | 11 | I-5 North Coast Corridor HOV Extension - Phase 1 - Encinitas HOV | IN SAN DIEGO COUNTY IN ENCINITAS AND CARLSBAD FROM SAN ELIJO LAGOON BRIDGE TO 0.3 MILE NORTH OF PALOMAR AIRPORT ROAD OVERCROSSING. CONSTRUCT HOV LANES, ITS ELEMENTS, CULVERT REHABILITATION, SOUNDWALLS, AND NC BIKE TRAIL. In the cities of Encinitas and Carlsbad from Manchester Avenue to Palomar Airport Road. Construct one High Occupancy Vehicle (HOV) lane in each direction; construct multi-use facility at Manchester; construct bike paths and soundwalls (CMGC) | 0 | 0 | 0 | 0 | 2018-10-19 16:15 |  | 0 | 0 | 0 | 2014-08-30 |  |  | 0 | 0 | 0 | 2018-06-30 |  |  | 44670 | 32000 | 1141 | 36571 | 2018-06-30 |  |  | 0 | 0 | 0 | 0 | 2018-10-31 | 2018-11-16 17:00 |  | 256059 | 163000 | 24486 | 256038 |  | 2022-09-01 17:00 | 195000 | 300729 | 195000 | 25627 | 292609
20 | 0615G | SD | 11 | I-5 North Coast Corridor HOV Extension - Phase 1 - Carlsbad HOV | In the city of Carlsbad from Palomar Airport Road to SR-78. Construct one High Occupancy Vehicle (HOV) lane in each direction; construct bike paths and soundwalls. (CMGC) | 0 | 0 | 0 | 0 | 2018-10-19 16:17 |  | 1316 | 0 | 4146 | 2014-08-30 | 2013-10-23 17:00 |  | 200 | 0 | 158 | 2019-07-15 |  | 2020-02-29 17:00 | 19194 | 0 | 0 | 18125 | 2019-07-15 |  | 2020-03-31 17:00 | 15 | 0 | 0 | 0 | 2020-09-15 |  | 2020-08-27 17:00 | 89969 | 0 | 0 | 89900 |  | 2024-05-13 17:00 | 0 | 110694 | 0 | 313 | 112329
21 | 2156 | ORA | 12 | Central Orange County Corridor - Bravo! Main Street Rapid Bus | In Orange County, Anaheim Regional Transportation intermodal Center to South Coast Metro Park and Ride. Purchase five zero-emission hydrogen buses. | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2020-07-01 | 0 | 0 | 0 |  |  | 2021-06-30 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2021-12-03 | 5414 | 4331 | 0 | 0 |  | 2023-12-30 | 0 | 5414 | 4331 | 0 | 0
22 | 2175 | ORA | 12 | Central Orange County Corridor - Traffic Light Synchronization - Warner Avenue | In the cities of Fountain Valley, Huntington Beach and Santa Ana from Pullman Street to Pacific Coast Highway. Signal Synchronization and required communications Infrastructure for 42 Signals - 14. 4 miles. | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2019-08-01 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2020-06-30 | 0 | 0 | 0 | 0 |  |  | 2020-07-01 | 5115 | 4092 | 0 | 0 |  | 2023-07-01 | 0 | 5115 | 4092 | 0 | 0
23 | 2176 | ORA | 12 | Central Orange County Corridor - Traffic Light Synchronization - MacArthur Boulevard | In the cities of Fountain Valley, Huntington Beach and Santa Ana from east of Beach Boulevard to Route 55. Signal Synchronization and required communications Infrastructure for 26 signals - 8. 2 miles. | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2019-08-01 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2020-06-30 | 0 | 0 | 0 | 0 |  |  | 2020-07-01 | 3689 | 2951 | 0 | 0 |  | 2023-07-01 | 0 | 3689 | 2951 | 0 | 0
24 | 2177 | ORA | 12 | Central Orange County Corridor - Traffic Light Synchronization - Edinger Avenue | In Fountain Valley, Huntington Beach, Santa Ana and Westminster from Bolsa Chica Street to Auto Mall. Signal Synchronization and required communications Infrastructure for 41 signals - 12. 2 miles. | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  | 2019-08-01 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2020-06-30 | 0 | 0 | 0 | 0 |  |  | 2020-07-01 | 6196 | 4957 | 0 | 0 |  | 2023-07-01 | 0 | 6196 | 4957 | 0 | 0
25 | 2178 | ORA | 12 | Warner Avenue Class II Bikeway | In Santa Ana and Tustin along Warner Avenue, from Wright Street, over State Route 55 to Red Hill Avenue. Construct Class II Bikeway along Warner Avenue. | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 |  |  | 2021-06-30 | 0 | 0 | 0 | 0 |  |  | 2021-12-31 | 1640 | 1443 | 0 | 0 |  | 2023-12-31 | 0 | 1640 | 1443 | 0 | 0
26 | 2179 | ORA | 12 | Red Hill Class II Bikeway | In the City of Tustin along southbound Red Hill Avenue, from the Santa Ana-Santa Fe Channel to Barranca Parkway. Construct Class II Bikeway. | 0 | 0 | 0 | 5 |  |  | 0 | 0 | 39 |  |  | 2019-06-30 | 0 | 0 | 0 |  |  | 2021-06-30 | 0 | 0 | 0 | 35 |  |  | 2021-06-30 | 0 | 0 | 0 | 0 |  |  | 2021-12-31 | 435 | 383 | 0 | 400 |  | 2022-12-30 | 0 | 435 | 383 | 0 | 479
27 | 2181 | ORA | 12 | Newport Avenue Class II Bikeway | . In the city of Tustin along Newport Avenue, from El Camino Real under Interstate 5 to the roadway southern terminus at the Santa Ana-Santa Fe Channel. Construct Class II Bikeway | 0 | 0 | 0 | 5 |  |  | 0 | 0 | 50 |  |  | 2019-06-30 | 0 | 0 | 55 |  |  | 2021-06-30 | 0 | 0 | 0 | 0 |  |  | 2021-06-30 | 0 | 0 | 0 | 496 |  |  | 2021-12-31 | 551 | 485 | 0 | 0 |  | 2023-12-30 | 0 | 551 | 485 | 0 | 606
28 | 2182 | ORA | 12 | Santa Ana-Santa Fe Channel Class I Bikeway | In the City of Tustin, along the Santa Ana-Santa Fe Channel (parallel to the LOSSAN Corridor), from Newport Avenue to Red Hill Avenue. Construct Class I Bikeway. | 0 | 0 | 0 | 12 |  |  | 0 | 0 | 104 |  |  | 2019-06-30 | 0 | 0 | 0 |  |  | 2020-12-30 | 0 | 0 | 0 | 116 |  |  | 2020-12-30 | 0 | 0 | 0 | 0 |  |  | 2021-08-01 | 1160 | 1021 | 0 | 1044 |  | 2022-06-30 | 0 | 1160 | 1021 | 0 | 1276
29 | 2183 | ORA | 12 | Main Street Class II Bikeway | In the City of Tustin on Main Street, westerly from downtown Tustin to the city boundary with Santa Ana. Construct Class II Bikeway. | 0 | 0 | 0 | 5 |  |  | 0 | 0 | 24 |  |  | 2019-06-30 | 0 | 0 | 0 |  |  | 2020-06-30 | 0 | 0 | 0 | 29 |  |  | 2020-06-30 | 0 | 0 | 0 | 0 |  |  | 2020-12-31 | 290 | 255 | 0 | 261 |  | 2021-06-30 | 0 | 290 | 255 | 0 | 319
EAC = Estimate at Completion | [10 empty] | Approved = Last Commission action | [32 empty] | Page -1 of 1