## TCEP Q3 Project List
ATTACHMENT 1 - Trade Corridor Enhancement Program Project List - January 1, 2019 to March 31, 2019 | [5 empty] | PAED | [6 empty] | PSE |  |  |  | R/W Support | [5 empty] | RTL |  |  | CON Support |  |  |  | R/W Capital |  |  |  | CON Capital | [8 empty] | Total Project
No. | PPNO | County | District | Project Name | Project Description | Approved PAED Budget ($1,000s) | TCEP Budget ($1,000s) | Expended PAED | EAC PAED | Actual PAED | Approved Finish PAED | Baseline Approval Date | Approved PSE Budget | TCEP PSE | Expended PSE | EAC PSE | Approved RW Sup | Expended RW Sup | EAC RW Sup | Approved RW Cert | Actual RW Cert | Current Finish RW Cert | Approved RTL | Actual RTL | Current RTL | Approved Con sup | TCEP Budget Con Sup | Expended Con Sup | EAC | Approved Budget RW Cap | TCEP Budget RW Cap | Expended RW Cap | EAC RW Cap | Approved Begin Con | Actual Begin Con | Current Finish Date | Approved Budget Con Cap | TCEP Con Cap | Expended Con Cap | EAC Total | Approved Finish Con Date | Current Finish Date | Total Approved Budget | Total TCEP Budget | Total Expended | Total EAC | Award Amount ($1,000s)
1 | 3445A | SHA | 02 | Redding to Anderson Six Lane - Phase 1 & 2 | In Shasta County in and near Anderson from Route 5/273 separation to 0.4 mile south of Churn Creek Road Overcrossing.. Widening to 6 lanes, bridge replacement and widening and roadway rehabilitation Widening to 6 lanes, bridge replacement and widening and roadway rehabilitation | 333 | 0 | 334 | 334 |  | 2013-03-29 | 2019-03-21 | 6140 | 0 | 8166 | 8166 | 280 | 481 | 481 | 2018-05-01 | 2018-05-01 17:00 |  | 2018-05-04 | 2018-05-04 17:00 |  | 17800 | 8700 | 912 | 15511 | 1262 | 0 | 456 | 0 | 2018-09-25 | 2018-11-30 17:00 |  | 132860 | 63178 | 382 | 132859 | 2021-10-02 | 2021-10-02 17:00 | 158675 | 71878 | 10731 | 157351 | 132859
2 | 0462G | SCL | 04 | US 101 / State Route 25 Interchange - Phase 1 | In southern Santa Clara County and Northern San Benito County, at the interchange of US 101 and SR 25. Reconstruct the interchange at a location just north of the existing interchange. The improvements will include a new, widened bridge to convey SR 25 over US 101. It will also improve ramps for all traffic movements between US 101 and SR 25. and minor realignment of SR 25 to the north. New traffic signals will be installed at the northbound and southbound ramp termini with SR 25. | 1000 | 0 | 0 | 0 | 2013-09-30 | 2013-09-30 | 2018-08-15 | 6000 | 4200 | 0 | 6000 | 0 | 0 | 0 | 2020-12-30 |  | 2020-12-30 | 2020-12-30 |  | 2020-12-30 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 2021-04-01 |  | 2021-04-01 | 19800 | 4200 | 0 | 0 |  | 2023-05-01 | 28600 | 8400 | 0 | 6000 | 0
3 | 2103D | ALA | 04 | 7th Street Grade Separation (East) | In the city of Oakland within the Port of Oakland along 7th Street, from east of Maritime Street to just west of I-880 near Bay Street. Reconstruction of the existing underpass and multi-use path, and the reconstruction of rail tracks and other rail infrastructure at the UnionPacific Railroad (UPRR) mainline. | 7500 | 0 | 5400 | 5400 | 2018-10-25 |  | 2019-01-30 | 19500 | 0 | 1670 | 21600 | 0 | 0 | 0 |  |  | 2020-02-05 |  |  | 2020-02-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2020-10-01 | 225000 | 175000 | 0 | 225000 |  | 2022-12-30 | 252000 | 175000 | 7070 | 252000 | 0
4 | 5301X | SOL | 04 | I-80/I-680/Route 12 Interchange Package 2A | IN SOLANO COUNTY. EB. SR-12 (JAMESON CANYON) TO EB. I-80 CONNECTOR. CONSTRUCTION EASTBOUND SR 12W TO EAST BOUNT I-80 CONNECTOR Eastbound SR12 to Eastbound I-80 Connector - This project would construct a new connector from Eastbound SR12 to Eastbound I-80, which will also connect two previous CMIA projects, ICP and Jameson Canyon widening projects. | 0 | 0 | 0 | 0 |  |  | 2018-10-17 | 11700 | 0 | 492 | 10061 | 600 | 0 | 0 |  |  | 2020-02-28 17:00 |  |  | 2020-02-28 17:00 | 10000 | 10000 | 0 | 5102 | 3400 | 0 | 0 | 0 |  |  | 2020-06-30 17:00 | 50300 | 43200 | 0 | 50300 |  | 2022-06-30 17:00 | 76000 | 53200 | 492 | 65463 | 0
5 | 7101C | SB | 05 | South Coast 101 HOV Lanes - Carpinteria (Segment 4A) | In Santa Barbara County, in Carpinteria from 0.2 miles south of Bailard Avenue to 0.5 miles south of S. Padaro Lane. Construct HOV lanes. This is a grandchild of parent project 05-0N700 (PPNO 7101) and child of parent 05-0N70A (PPNO 7101A). | 12245 | 0 | 0 | 0 | 2014-08-26 | 2014-08-26 | 2019-03-20 | 8320 | 0 | 481 | 3244 | 920 | 150 | 1033 | 2019-11-01 |  | 2020-01-15 | 2019-11-15 |  | 2020-01-31 | 22060 | 8400 | 0 | 10191 | 5740 | 0 | 40 | 5423 | 2020-07-31 |  | 2020-08-14 | 86500 | 42600 | 0 | 50810 |  | 2024-02-21 | 135785 | 51000 | 671 | 70701 | 0
6 | 7101D | SB | 05 | South Coast 101 HOV-Padaro (Segment 4B) | In Santa Barbara County, near Carpinteria and Summerland from 0.9 miles south of S. Padaro Lane Undercrossing to 0.6 miles north of Padaro Lane Overcrossing. Construct HOV lanes. This is a grandchild of parent project 05-0N700 (PPNO 7101) and child of parent 05-0N70A (PPNO 7101A). | 2725 | 0 | 0 | 0 | 2014-08-26 17:00 | 2014-08-26 | 2019-03-20 | 10025 | 0 | 174 | 6099 | 1010 | 0 | 689 | 2020-11-01 |  | 2020-10-30 17:00 | 2021-01-01 |  | 2020-12-31 17:00 | 29990 | 0 | 0 | 12931 | 10490 | 0 | 0 | 0 | 2021-07-15 |  | 2021-07-15 17:00 | 139310 | 0 | 0 | 89150 | 2025-12-15 | 2025-10-02 17:00 | 193550 | 0 | 174 | 108869 | 0
7 | 7101E | SB | 05 | South Coast 101 HOV-Summerland (Segment 4C) | In Santa Barbara County, in and near Summerland from 0.2 miles north of Padaro Lane Overcrossing to San Ysidro Creek Bridge. Construct HOV lanes. | 2380 | 0 | 0 | 0 | 2014-08-26 08:00 | 2014-08-26 | 2019-01-29 | 7280 | 0 | 0 | 748 | 520 | 0 | 0 | 2020-11-01 |  | 2020-10-30 17:00 | 2021-01-01 |  | 2020-12-31 17:00 | 17720 | 0 | 0 | 10103 | 3930 | 0 | 0 | 0 | 2021-07-15 |  | 2021-07-15 17:00 | 88470 | 0 | 0 | 60240 | 2025-12-15 | 2025-08-29 17:00 | 120300 | 0 | 0 | 71091 | 0
8 | 6955 | KER | 06 | Route 58/99 Bakersfield Freeway Connector | The project is proposed at the State Route 58/State Route 99 interchange in Bakersfield, CA. The project proposes to grade separate exit and entry freeway ramps between two closely spaced interchanges (SR 58/SR 99 and SR 99/Ming Ave), and to construct a collector -distributor roadway and auxiliary lanes along the southbound State Route 99 mainline to safely accommodate on-ramp traffic. | 0 | 0 | 0 | 0 |  | 2015-12-04 | 2019-02-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2018-04-01 |  |  | 2018-06-01 | 2018-08-24 |  | 0 | 0 | 0 | 2158 | 0 | 0 | 0 | 0 | 2018-08-01 | 2019-02-19 |  | 50000 | 25000 | 0 | 59000 | 2021-02-01 | 2021-02-01 | 50000 | 25000 | 0 | 61158 | 0
9 | 2741S | LA | 07 | Route 71 Expressway to Freeway Conversion (Mission Road to Route 60) | In Pomona from Mission Road to Route 60. Add on mixed lane and one HOV lane in each direction. | 0 | 0 | 0 | 0 | 2013-05-31 17:00 | 2013-05-31 | 2019-02-27 | 12544 | 0 | 0 | 10706 | 3000 | 0 | 2833 | 2019-08-14 |  | 2019-07-15 17:00 | 2019-08-14 |  | 2019-08-14 17:00 | 15847 | 5000 | 0 | 21132 | 26000 | 0 | 0 | 0 | 2020-02-21 |  | 2020-06-30 17:00 | 120000 | 39000 | 0 | 114000 | 2024-07-14 | 2023-07-14 17:00 | 177391 | 44000 | 0 | 148671 | 0
10 | 3189B | LA | 07 | I-5 Golden State Chokepoint Relief | In northern Los Angeles County at the I-5 / SR-14 split. Construct truck lanes, HOV lanes, auxiliary lanes, soundwalls, and an ITS hub station. Widen seven bridges and improve access to weigh station. | 479 | 0 | 0 | 0 | 2009-09-29 | 2009-09-29 | 2018-10-17 | 799 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-05-01 |  | 2019-05-30 | 2019-05-01 |  | 2019-06-30 | 0 | 0 | 0 | 0 | 6703 | 0 | 0 | 0 | 2020-01-15 |  | 2020-08-30 | 501500 | 247000 | 0 | 0 | 2023-01-31 | 2025-01-30 | 509481 | 247000 | 0 | 0 | 0
11 | 5388 | LA | 07 | Route 605 / 91 Interchange Improvement: Gateway Cities Freight Crossroads Project | In the cities of Artesia and Cerritos, from Shoemaker Avenue to I-605 Interchange and on I-605 from Alondra Blvd to the I-605/SR-91 interchange. Construct one mixed-flow lane, westbound from Artesia Boulevard on-ramp to I-605 Connector ramp; modify on/off ramps and upgrade non-standard features. | 776 | 0 | 6193 | 6193 | 2019-01-18 |  | 2019-03-21 | 25000 | 3000 | 0 | 12000 | 0 | 0 | 0 |  |  | 2022-01-07 |  |  | 2022-03-04 | 0 | 0 | 0 | 0 | 32200 | 29000 | 0 | 20800 |  |  | 2022-08-05 | 148600 | 17000 | 0 | 114000 |  | 2025-07-03 | 206576 | 49000 | 6193 | 152993 | 0
12 | 5394 | LA | 07 | Route 57/60 Confluence: Chokepoint Relief Project | In Los Angeles County, in Diamond Bar and the City of Industry on Route 60 from EB 60 to SB 57 connector overcrossing to near Golden Springs Drive Undercrossing and Route 57 from NB 57 to WB 60 connector overcrossing to South 57/60 separation. Interchange modifications, including auxiliary lanes and three new bridges. | 1600 | 0 | 0 | 0 | 2013-12-11 | 2013-12-01 | 2018-10-17 | 25000 | 17000 | 0 | 0 | 0 | 0 | 0 | 2020-04-15 |  | 2021-08-31 | 2020-04-15 |  | 2021-09-30 | 0 | 0 | 0 | 0 | 36200 | 5000 | 0 | 0 | 2024-07-01 |  | 2024-07-01 | 82800 | 0 | 0 | 0 | 2028-06-30 | 2028-06-30 | 145600 | 39000 | 0 | 0 | 0
13 | 0260J | SBD | 08 | Route 395 Widening from SR 18 to Chamberlaine Way | On US 395, between SR 18 and Chamberlaine Way in the City of Adelanto. Widen this section of US 395 from two to four lanes. Proposed improvements also include operational improvements such as adding turn lanes and signal improvements at intersections. | 0 | 0 | 0 | 0 | 2009-12-31 17:00 | 2009-12-31 | 2018-10-19 15:16 | 12497 | 0 | 5151 | 5189 | 3623 | 0 | 1142 | 2018-07-27 | 2018-04-12 17:00 |  | 2018-07-30 | 2018-04-17 17:00 |  | 0 | 0 | 0 | 1428 | 10822 | 0 | 0 | 8739 | 2019-02-06 |  | 2019-05-01 17:00 | 41933 | 24292 | 0 | 28168 |  | 2021-05-03 17:00 | 68875 | 24292 | 5151 | 44666 | 0
14 | 3009P | SBD | 08 | I-10 Express Lanes-San Antonio Ave to Route 15 (Contract 1) | From LA/SBd Co Ln to I-10/I-15 Interchange & in LA County from 0. 4 Mi W/o White Ave OC to LA/SBd Co Ln; Implement two express lanes in each direction for a total of four general purpose and two express lanes in each direction with auxiliary lanes, widening undercrossings, and reconstruction of ramps and lane transitions where needed. This project will be delivered using Design-Build method (TCIF 128) | 400 | 0 | 0 | 0 | 2017-07-07 | 2017-07-06 | 2019-03-14 | 30325 | 0 | 0 | 0 | 0 | 0 | 0 | 2022-03-01 | 2018-01-16 |  | 2021-11-01 | 2018-01-16 |  | 17900 | 0 | 0 | 0 | 47811 | 0 | 221 | 0 | 2018-08-13 | 2018-09-07 |  | 716366 | 122804 | 0 | 0 | 2024-02-01 | 2023-07-07 | 812802 | 122804 | 221 | 0 | 0
15 | 3010T | RIV | 08 | Route 60 Truck Safety and Efficiency Project - Phase 1A | This project is located on State Route 60 and Moreno Beach Drive in the City of Moreno Valley, County of Riverside. This specific project component is the second phase of an interchange project that will replace a 50-year old 2-lane bridge with a new 6-lane bridge, reconfigure the north side of SR 60/Moreno Beach Drive Interchange, and build an associated freeway auxiliary lane. Because the bridge is so narrow, trucks are restricted on the eastbound offramp to right-hand (southerly) turns only. | 0 | 0 | 0 | 0 | 2007-12-01 |  | 2018-10-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2015-03-01 |  |  |  | 2020-03-26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2020-10-30 | 24000 | 16800 | 0 | 24000 |  | 2022-08-02 | 24000 | 16800 | 0 | 24000 | 0
16 | 0161A | MER | 10 | Livingston Widening Northbound | In Livingston, from 0.8 mile south of Hammatt Avenue to Merced/Stanislaus county line. Widen freeway from two lanes to three lanes in the northbound direction only. | 800 | 0 | 638 | 638 | 2014-06-02 17:00 | 2014-06-02 | 2019-02-27 | 2050 | 0 | 2386 | 2449 | 10 | 3 | 3 | 2019-02-28 | 2018-11-07 17:00 |  | 2019-03-29 | 2019-01-25 17:00 |  | 6343 | 0 | 0 | 6339 | 10 | 0 | 7 | 8 | 2019-10-16 |  | 2019-07-24 17:00 | 30149 | 29050 | 0 | 34918 | 2021-04-30 | 2021-04-30 17:00 | 39362 | 29050 | 3034 | 44355 | 0
17 | 0944M | STA | 10 | Route 132 Expressway, Phase 1 | In Modesto, on Route 132 from 0.2 mile east of Stone Avenue to 6th Street, and on Route 99 from I Street to Woodland Avenue. Construct 2-lane expressway and improve Route 132/99 interchange. | 7865 | 0 | 7865 | 7865 | 2018-03-09 | 2018-03-09 | 2019-03-21 | 10684 | 0 | 8941 | 10684 | 0 | 0 | 0 | 2019-01-01 |  | 2019-04-26 | 2019-01-02 |  | 2019-04-29 | 0 | 0 | 0 | 0 | 14476 | 0 | 14440 | 14476 | 2019-04-15 |  | 2019-10-28 | 27665 | 122572 | 0 | 0 | 2020-12-31 | 2021-06-01 | 60690 | 21000 | 31246 | 33025 | 0
18 | 0999E | SD | 11 | Siempre Viva Interchange and Site Preparation Design for Commercial Vehicle Enforcement Facility - Segment 2B | Near San Diego at 1.9 miles east of Sanyo Avenue Undercrossing. Construct new interchange and begin site preparation design for Commercial Vehicle Enforcement Facility, which includes drainage and utilities. | 0 | 0 | 0 | 0 | 2012-04-02 17:00 | 2012-03-29 | 2018-10-19 15:59 | 4810 | 4810 | 727 | 4654 | 0 | 0 | 0 | 2019-04-12 |  | 2020-02-12 17:00 | 2019-04-15 |  | 2020-03-12 17:00 | 5096 | 5096 | 0 | 4675 | 0 | 0 | 0 | 263 | 2019-10-15 |  | 2020-10-01 17:00 | 27212 | 27212 | 0 | 27212 |  | 2022-06-01 17:00 | 37118 | 37118 | 727 | 36804 | 0
19 | 0999F | SD | 11 | Otay Mesa East Port of entry-Segment 3A | Near San Diego, on route 11 at 1.9 miles east of Sanyo Avenue Undercrossing. Begin site preparation which includes drainage and utilities. | 0 | 0 | 0 | 0 | 2012-04-02 17:00 | 2012-04-01 | 2018-10-19 16:03 | 3900 | 3900 | 368 | 3738 | 600 | 0 | 542 | 2019-04-07 |  | 2020-08-28 17:00 | 2019-04-15 |  | 2020-09-25 17:00 | 6100 | 0 | 0 | 5364 | 550 | 550 | 0 | 0 | 2019-10-20 |  | 2021-06-25 17:00 | 29200 | 0 | 0 | 29200 |  | 2023-08-24 17:00 | 40350 | 5050 | 368 | 38844 | 0
20 | 1036 | SD | 11 | Route 125/905 Connector | In and near San Diego at Route 125/905 separation. Construct freeway to freeway South-West connector. | 0 | 0 | 0 | 0 | 2004-07-30 17:00 | 2004-07-30 | 2018-10-19 15:56 | 9714 | 0 | 2319 | 4846 | 0 | 0 | 10 | 2019-07-09 |  | 2019-10-11 17:00 | 2019-08-02 |  | 2019-11-01 17:00 | 5000 | 5000 | 0 | 4536 | 0 | 0 | 0 | 131 | 2020-04-06 |  | 2020-08-17 17:00 | 26400 | 16980 | 0 | 20000 |  | 2022-08-15 17:00 | 41114 | 21980 | 2319 | 29523 | 0
21 | 1241 | IMP | 11 | Intelligent Transportation System Technology (Advanced Technology Corridors at Border Ports of Entry) | In San Diego County and Imperial County on various routes at various locations. Install Intelligent Technology Statewide Border Wait Time, implement a fiber optic cable network to facilitate an advanced traveler information and border wait time system connecting the entire San Diego and Imperial border network. | 1635 | 0 | 466 | 466 | 2018-10-15 17:00 | 2018-11-16 | 2018-07-05 07:54 | 5759 | 2317 | 286 | 4006 | 62 | 0 | 1 | 2020-01-31 |  | 2020-05-17 17:00 | 2020-02-15 |  | 2020-05-30 17:00 | 5938 | 1534 | 0 | 4826 | 375 | 0 | 0 | 0 | 2020-08-14 |  | 2020-11-02 17:00 | 27945 | 8118 | 0 | 26683 |  | 2022-09-07 17:00 | 41714 | 11969 | 752 | 35982 | 0
22 | 1258 | IMP | 11 | Route 98 Widening | In Imperial County. In Calexico from just west of State Route 111 to Rockwood Avenue. Widening Route 98 from 4 to 6 lanes. | 169 | 0 | 2383 | 2383 | 2009-02-18 17:00 | 2009-02-18 | 2019-01-09 09:59 | 1000 | 0 | 911 | 1056 | 2017 | 973 | 1010 | 2019-07-30 |  | 2019-07-12 17:00 | 2019-08-30 |  | 2019-08-30 17:00 | 661 | 0 | 0 | 1553 | 1983 | 0 | 24 | 1000 | 2020-02-13 |  | 2020-02-13 17:00 | 7141 | 3370 | 0 | 6600 |  | 2024-01-10 17:00 | 12971 | 3370 | 4291 | 13602 | 0
23 | 1335 | IMP | 11 | Calexico East Port of Entry Truck Crossing Improvement | Near the city of Calexico, 0.7 mile south of Route 7 near the U.S./ Mexico border, at the Calexico East Port of Entry Truck Crossing. Widen bridge over the All American Canal to add truck lanes and passenger lanes along with eight foot shoulders. | 3000 | 3000 | 539 | 3490 |  | 2019-06-01 | 2018-10-17 16:11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2020-07-02 |  | 2020-07-02 17:00 | 2020-01-10 |  |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2020-07-05 |  |  | 0 | 0 | 0 | 0 |  | 2023-02-02 17:00 | 3000 | 3000 | 539 | 3491 | 0
24 | 3834 | ORA | 12 | SR-57 - Lambert Road Interchange Improvements | In the City of Brea at the SR-57 & Lambert Road Interchange. Reconfiguration of northbound ramps including construction of a loop on-ramp at the south-east quadrant; modify NB off-ramp; lower Lambert Road and widen NB Lambert Road UC bridge to to accommodate future truck-climbing lane. | 1000 | 0 | 0 | 0 | 2015-11-25 17:00 | 2015-11-25 | 2019-02-28 | 1324 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-04-01 | 2018-09-24 17:00 |  | 2019-05-01 | 2018-09-24 17:00 |  | 16000 | 16000 | 0 | 16000 | 12458 | 0 | 0 | 0 | 2020-01-02 |  | 2019-05-10 17:00 | 62923 | 45087 | 0 | 62923 | 2023-01-02 | 2022-07-10 17:00 | 93705 | 61087 | 0 | 78923 | 0
25 | 1334 | SD | 11 | Otay Mesa Truck Route, Phase 4A | In San Diego at the existing east/west service road along the border fence on La Media Road. |  | 0 |  |  |  |  | 2016-02-03 | [21 empty] | 2019-06-03 |  |  | 12524 | 6000
26 | 2002A | LA | 75 | Rosecrans / Marquardt Grade Seperation | Widen and pave approximately 1.3 miles of existing service road, redirect laden/unladen trucks on dedicated route. | 1970 | 0 | 0 | 0 | 2016-03-01 | 2018-03-01 | 2019-03-21 | 6360 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-09-01 |  | 2020-06-19 | 2019-10-01 |  |  | 0 | 0 | 0 | 0 | 68738 | 0 | 0 | 0 | 2020-04-01 |  | 2021-03-01 | 81370 | 9000 | 0 | 0 | 2022-06-01 | 2023-06-30 | 158438 | 9000 | 0 | 0 | 0
27 | 4961 | VEN | 75 | Rice Avenue/Fifth Street/UPRR Grade Separation Project | In the City of Oxnard at the Rice Avenue / Fifth Street (Route 34) / UPRR intersection. Construct grade separation structure to elevate Rice Avenue over Fifth Street and the UPRR track to eliminate the existing at-grade railroad crossing. The project also includes the construction of two connector roads, one in the southeast quadrant and another in the southwest quadrant of the Rice Avenue grade separation, to provide access between Rice Avenue and Fifth Street. A 12-foot sidewalk would also be added on the west-bound side of Fifth Street. | 3132 | 0 | 3132 | 3132 | 2018-05-15 | 2018-05-16 | 2019-03-01 | 6837 | 4406 | 6837 | 6837 | 0 | 0 | 0 | 2019-12-01 |  | 2019-12-01 | 2019-12-01 |  | 2019-12-01 | 0 | 0 | 0 | 0 | 8000 | 8000 | 8000 | 8000 | 2020-06-01 |  | 2020-06-01 | 61200 | 56200 |  | 61200 | 2023-12-31 | 2023-12-31 | 79169 | 68606 | 79169 | 79169 | 0
28 | T0002 | SJ | 75 | Fyffe Avenue Grade Separation | In Stockton on the northern limits of the Navy Drive Bridge at the San Joaquin River to the Port of Stockton West Complex entrance. Construct a grade separated crossing; four lane overcrossing over the Fyffe Avenue rail line, realign McCloy Avenue south of its current location to form a stop-controlled intersection. | 200 | 0 | 0 | 0 | 2018-05-18 |  | 2018-08-15 | 1400 | 1000 | 0 | 1000 | 0 | 0 | 0 |  |  | 2019-09-30 |  |  |  | 0 | 0 | 0 | 0 | 400 | 0 | 0 | 0 |  |  | 2020-06-27 | 11000 | 8000 | 0 | 8000 |  | 2023-06-27 | 13000 | 9000 | 0 | 9000
29 | T0003 | ALA | 75 | Freight Intelligent Transportation System | In the City of Oakland, within the Port of Oaklands Seaport Area, along West Grand Avenue, Maritime Street, 7th Street, and Middle Harbor Road. Install and implement ITS elements and other technologies, which include changeable message signs, closed circuit TV, fiber optic and Wi-Fi communications, traffic signal enhancements, vehicle and queue detection, train queue detection, weigh-in-motion, information application, and smart parking system. | 2500 | 0 | 2500 | 2500 | 2018-08-31 |  | 2019-01-30 | 4100 | 0 | 3125 | 4100 | 0 | 0 | 0 |  | 2019-03-01 |  |  | 2019-03-06 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2019-10-01 | 24000 | 12456 | 0 | 24000 |  | 2021-12-31 | 30600 | 12456 | 5625 | 30600 | 0
30 | T0004 | ALA | 75 | Quiet Zone Safety Engineering Measures | In Emeryville, at three at-grade crossings on 65th Street, 66th Street, and 67th Street just east of Shellmound Street. Install four quadrant gates, raised median, and sidewalks at three at-grade railroad crossings. | 75 | 0 | 75 | 75 | 2018-05-01 |  | 2018-10-17 | 405 | 0 | 150 | 405 | 0 | 0 | 0 |  |  | 2020-02-01 |  |  | 2020-02-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2020-09-01 | 6000 | 4200 | 0 | 6000 |  | 2021-05-01 | 6480 | 4200 | 225 | 6480 | 0
31 | T0005 | LA | 75 | Alameda Corridor Southern Terminus Gap Closure | In Los Angeles County at the Port of Los Angeles. Extension of the TraPac lead track and San Pedro main line track of approximately 5000 linear feet and will connect to the Alameda Corridor. Work includes the relocation and/or protection of existing underground utilities and the relocation of power poles, utility meters, and perimeter fencing. | 0 | 0 | 0 | 0 |  | 2018-11-16 | 2018-10-17 | 969 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2019-08-01 | 2019-08-01 |  | 2019-10-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2020-01-31 |  | 2020-04-15 | 8560 | 5992 | 0 | 0 | 2021-01-31 | 2021-04-15 | 9529 | 5992 | 0 | 0 | 0
32 | T0006 | LA | 75 | Terminal Island Railyard Enhancement Project | In the Port of Los Angeles on Terminal Island. Addition of five staging/storage tracks (approximately 31,000 lineal feet) to the existing Pier 400 rail yard, which also includes a short rail bridge over water. The Pier 400 storage/staging rail yard supports on-dock rail yards for six terminals in the POLA and POLB. | 844 | 0 | 0 | 0 | 2018-10-04 | 2018-11-16 | 2019-02-28 | 2249 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2020-01-02 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2020-06-30 |  |  | 30923 | 21645 | 0 | 0 | 2021-12-31 |  | 34016 | 21645 | 0 | 0 | 0
33 | T0007 | LA | 75 | Pier G and J Double Track | At the Port of Long Beach from Pier G to Pier J. Construct new 9,000-foot mainline track for trains serving four marine terminals in the southeastern area of the Port between the northeast corner of Pier G terminal and Harbor Scenic Drive. | 2629 | 0 | 2722 | 2722 | 2019-04-25 | 2016-11-11 | 2018-07-23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2020-04-01 | 2019-04-26 |  | 2018-02-18 |  | 2019-04-29 | 0 | 0 | 0 | 0 | 1502 | 0 | 0 | 0 | 2018-02-28 |  | 2019-12-30 | 20869 | 14000 | 0 | 0 | 2021-07-30 | 2022-12-30 | 25000 | 14000 | 2722 | 2722 | 14000
34 | T0008 | LA | 75 | Montebello Boulevard Grade Separation Project | In the City of Montebello, along the Alameda Corridor-East Corridor at Montebello Boulevard. Replace at-grade crossing with a new grade separated undercrossing. | 0 | 0 | 0 | 0 | 2018-06-01 |  | 2018-10-17 | 14368 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2020-04-01 |  |  | 2020-06-01 | 0 | 0 | 0 | 0 | 19140 | 0 | 0 | 0 |  |  | 2021-01-01 | 95103 | 49000 | 0 | 75750 |  | 2024-01-01 | 128611 | 49000 | 0 | 75750 | 0
35 | T0009 | LA | 75 | Turnbull Canyon Road Grade Separation Project | In the City of Industry and unincorporated Los Angeles County, along the Alameda Corridor-East Trade Corridor at Turnbull Canyon Road. Replace at-grade crossing with a new grade separated undercrossing. Add sidewalks and bike lanes. | 0 | 0 | 0 | 0 |  |  | 2018-10-17 | 10106 | 0 | 0 | 10106 | 0 | 0 | 0 |  |  | 2020-03-01 |  |  | 2020-06-01 | 0 | 0 | 0 | 0 | 33885 | 0 | 0 | 33885 |  |  | 2021-01-01 | 42255 | 29000 | 0 | 42255 |  | 2023-03-01 | 86246 | 29000 | 0 | 86246 | 0
36 | T0011 | SBD | 75 | Etiwanda Avenue Grade Separation | In the City of Rancho Cucamonga, Etiwanda Avenue Grade Separation at SCRRA and BNSF San Gabriel Rail Line, between Whittram Avenue and Napa Street. The project will replace an existing at-grade crossing with a new grade-separated overcrossing and construct side-walk and bike lane. | 850 | 0 | 0 | 0 | 2018-06-06 | 2018-06-06 | 2019-03-18 | 2000 | 2000 | 0 | 2000 | 0 | 0 | 0 | 2020-01-31 |  | 2020-01-31 | 2020-01-31 |  | 2020-02-05 | 0 | 0 | 0 | 0 | 5000 | 5000 | 0 | 5000 | 2020-06-01 |  | 2020-06-03 | 52150 | 52150 | 0 | 52150 | 2021-12-30 | 2021-12-30 | 60000 | 59150 | 0 | 59150 | 0
37 | T0012 | SD | 75 | National City Marine Terminal Rail Track Extension Project | In National City at the National City Marine Terminal. Construct connector track and realign Marina Way. | 0 | 0 | 0 | 0 |  |  |  | 836 | 585 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 3685 | 0 | 0 | 0 |  |  | 4521 | 585 | 0 | 0 | 0
38 | T0013 | SD | 75 | Tenth Avenue Marine Terminal Beyond Compliance Environmental Enhancement Project | In San Diego in the San Diego Bay at the Tenth Avenue Marine Terminal. Expand shore power and purchase a barge-based Bonnet" system." | 0 | 0 | 0 | 0 |  |  | 2019-02-28 | 30 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2019-03-01 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-08-01 |  | 2019-08-01 | 8000 | 5600 | 0 | 0 | 2020-04-01 | 2020-04-01 | 8030 | 5600 | 0 | 0 | 0
39 | T0014 | SD | 75 | Sorrento to Miramar, Phase 2 Intermodal Improvements | In the city of San Diego along the LOSSAN rail corridor from Mile Post (MP) 250.9 near I-805 to MP 253 near Miramar Road. Add 1. 9 miles of double-track, curve straightening, and new signals. | 0 | 0 | 0 | 0 | 2018-05-23 |  | 2018-10-17 | 6037 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2020-06-30 |  |  | 2020-06-30 | 0 | 0 | 0 | 0 | 15000 | 10500 | 0 | 0 |  |  |  | 108000 | 0 | 0 | 0 |  |  | 129037 | 10500 | 0 | 0 | 0
[37 empty] | 24000 | 12456 | 4950 | 6600
EAC = Estimate at Completion