## Project_Data
No. | District | PPNO | County | Route | Title | Location and Type of Work | TOTAL SHOPP Funding | PAED Total Funding | PAED SHOPP Funding | PSE Total Funding | PSE SHOPP Funding | RW Sup Total Funding | RW Sup SHOPP Funding | Con Sup Total Funding | Con Sup SHOPP Funding | RW Cap Total Funding | RW Cap SHOPP Funding | Con Cap Total Funding | Con Cap SHOPP Funding | Contract Award Amount | PAED Total Exp | PAED SHOPP Exp | PAED EAC | PSE Total Exp | PSE SHOPP Exp | PSE EAC | RW Sup Total Exp | RW Sup SHOPP Exp | RW Sup EAC | Con Sup Total Exp | Con Sup SHOPP Exp | Con Sup EAC | RW Cap Total Exp | RW Cap SHOPP Exp | RW Cap EAC | Con Cap Total Exp | Con Cap SHOPP Exp | Con Cap EAC | PAED Approved Completion Date | RW Cert Approved Completion Date | RTL Approved Completion Date | Begin Con Approved Completion Date | End Con Approved Completion Date | Baseline Agreement Actual Completion Date | PAED Actual Completion Date | RW Cert Actual Completion Date | RTL Actual Completion Date | Begin Con Actual Completion Date | End Con Actual Completion Date | Baseline Agreement Planned Completion Date | PAED Planned Completion Date | RW Cert Planned Completion Date | RTL Planned Completion Date | Begin Con Planned Completion Date | End Con Planned Completion Date | Completion Report Actual Completion Date | Final Delivery Actual Completion Date
1 | 01 | 0100V | DN | 101 | Dr. Fine Bridge Replacement | Near Crescent City from 0.2 mile north of the Smith River Overflow Bridge. Replace bridge. | 85103 | 13655 | 13655 | 4200 | 4200 | 650 | 650 | 12250 | 12250 | 3900 | 3900 | 50448 | 50448 | 0 | 13443 | 13443 | 14410 | 0 | 0 | 4189 | 122 | 122 | 569 | 0 | 0 | 11562 | 37 | 37 | 6499 | 0 | 0 | 47887 | 2019-12-01 | 2021-03-19 | 2021-04-19 | 2021-12-10 | [8 empty] | 2020-03-02 | 2021-04-01 | 2021-04-19 | 2021-09-01 | 2025-10-03
2 | 01 | 0154T | MEN | 1 | Pudding Creek CAPM | In and near Fort Bragg, from Pudding Creek Bridge to 0.6 mile north of Wages Creek Bridge. Pavement rehabilitation. | 15113 | 336 | 336 | 501 | 501 | 36 | 36 | 657 | 657 | 1 | 1 | 13582 | 13582 | 0 | 326 | 326 | 326 | 478 | 478 | 544 | 1 | 1 | 12 | 0 | 0 | 914 | 0 | 0 | 0 | 0 | 0 | 13549 | 2018-09-01 | 2019-05-01 | 2019-05-15 | 2019-10-01 |  |  | 2018-11-28 | 2019-04-15 | 2019-05-22 | [6 empty] | 2019-12-18 | 2020-10-16
3 | 01 | 1055 | DN | 199 | DN-199 Culverts | In Del Norte County, at various locations from south of Myrtle Creek Bridge to south of the Oregon State line. Culvert rehabilitation and fish passage. | 3992 | 0 | 0 | 655 | 655 | 52 | 52 | 814 | 814 | 78 | 78 | 2393 | 2393 | 0 | 0 | 0 | 0 | 55 | 55 | 689 | 0 | 0 | 106 | 0 | 0 | 862 | 0 | 0 | 0 | 0 | 0 | 2393 | [6 empty] | 2019-02-01 | [6 empty] | 2020-04-01 | 2020-05-01 | 2020-08-26 | 2022-12-01
4 | 01 | 1072 | DN | 101 | Hunter/Panther Creek Bridge Replacement | Near Klamath, at Panther Creek Bridge No. 01-0025 and at Hunter Creek Bridge No. 01-0003. Seismic retrofit. | 34943 | 3729 | 3729 | 3720 | 3720 | 373 | 373 | 3842 | 3842 | 5589 | 5589 | 17690 | 17690 | 0 | 3726 | 3726 | 3726 | 1592 | 1592 | 2895 | 20 | 20 | 150 | 0 | 0 | 3734 | 2226 | 2226 | 2226 | 0 | 0 | 18800 | 2018-07-05 | 2019-05-10 | 2019-06-03 | 2019-09-16 |  | 2019-01-31 | 2018-07-05 | 2019-04-16 | [6 empty] | 2019-10-08 | 2020-05-04 | 2023-12-30
5 | 01 | 1113 | DN | 101 | Dominie Creek Fish Passage | Near the Smith River community, at Dominie Creek. Replace box culvert with new bridge and remediate fish passage barrier. | 10905 | 2000 | 2000 | 1141 | 1141 | 118 | 118 | 1643 | 1643 | 151 | 151 | 5852 | 5852 | 0 | 1392 | 1392 | 1392 | 171 | 171 | 1069 | 15 | 15 | 95 | 0 | 0 | 1824 | 13 | 13 | 33 | 0 | 0 | 4993 | 2019-01-15 | 2020-01-03 | 2020-01-17 | 2020-07-22 |  |  | 2019-01-15 | [6 empty] | 2020-01-03 | 2020-01-17 | 2020-07-01 | 2023-01-02
6 | 01 | 1130 | DN | 199 | INSIDE PARK CULVERTS | Near Crescent City, at various locations from north of Elk Valley Cross Road to south of Walker Road. Culvert rehabilitation and fish passage. | 3910 | 300 | 300 | 480 | 480 | 30 | 30 | 407 | 407 | 88 | 88 | 2605 | 2605 | 0 | 65 | 65 | 300 | 0 | 0 | 403 | 0 | 0 | 69 | 0 | 0 | 469 | 0 | 0 | 47 | 0 | 0 | 3248 | [12 empty] | 2020-01-14 | 2021-01-08 | 2021-01-21 | 2021-05-06 | 2021-12-01
7 | 01 | 2270 | HUM | 254 | Avenue Culvert Rehab | Near Miranda, from 2.3 miles south of Miranda Post Office to 0.9 mile south of Bear Creek Bridge. Upgrade drainage systems. | 1611 | 0 | 0 | 0 | 0 | 0 | 0 | 432 | 432 | 305 | 305 | 874 | 874 | 0 | 1386 | 1386 | 1386 | 942 | 942 | 1167 | 123 | 123 | 167 | 0 | 0 | 502 | 36 | 36 | 34 | 0 | 0 | 1105 | 2017-09-29 | 2018-12-01 | 2018-12-01 | 2019-07-01 |  |  | 2017-09-29 | 2018-12-21 | 2019-01-15 | [6 empty] | 2019-08-01 | 2021-01-01
8 | 01 | 2301 | HUM | 101 | South Fork Eel River Bridge #04-123 | Near Myers Flat, at South Fork Eel River Bridge No. 04-0123. Seismic retrofit. | 23045 | 4641 | 4641 | 2072 | 2072 | 218 | 218 | 2267 | 2267 | 85 | 85 | 13762 | 13762 | 0 | 2354 | 2354 | 3803 | 0 | 0 | 1820 | 0 | 0 | 116 | 0 | 0 | 2165 | 0 | 0 | 80 | 0 | 0 | 11675 | 2018-09-01 | 2020-01-01 | 2020-01-01 | 2020-07-01 | [8 empty] | 2019-12-01 | 2021-02-01 | 2021-02-01 | 2021-08-01 | 2023-09-29
9 | 01 | 2302 | HUM | 96 | Three HUM Bridges | In Humboldt County, at Willow Creek Bridge No. 04 -0135 (PM 0.2) and Camp Creek Bridge No. 04 -0666 (PM 37.2); also on Route 101 at G Street Overcrossing No. 04-0243 (PM 86.8). Seismic retrofit of three bridges. | 13601 | 2366 | 2366 | 1856 | 1856 | 171 | 171 | 1948 | 1948 | 1089 | 1089 | 6171 | 6171 | 0 | 1458 | 1458 | 1458 | 0 | 0 | 1294 | 8 | 8 | 154 | 0 | 0 | 1705 | 1 | 1 | 138 | 0 | 0 | 4063 | 2019-02-01 | 2020-02-01 | 2020-02-15 | 2020-09-01 |  |  | 2019-04-26 | [6 empty] | 2020-02-03 | 2020-02-17 | 2020-07-22 | 2023-12-01
10 | 01 | 2363 | HUM | 36 | Bridge Rail Replacement - 3 bridges | Near Bridgeville, at Hely Creek Bridge (No. 04-0092), Little Larabee Creek Bridge (No. 04-0102) (PM 25.3), and Butte Creek Bridge (No. 04-0116). Upgrade bridge rails and widen at one bridge, and replace two bridges. | 28061 | 2947 | 2947 | 3646 | 3646 | 268 | 268 | 4325 | 4325 | 874 | 874 | 16001 | 16001 | 0 | 1381 | 1381 | 2743 | 0 | 0 | 2852 | 0 | 0 | 221 | 0 | 0 | 3975 | 5 | 5 | 874 | 0 | 0 | 13573 | 2019-03-01 | 2020-03-01 | 2020-04-01 | 2020-08-30 | [8 empty] | 2020-10-03 | 2021-10-01 | 2021-11-01 | 2022-03-30 | 2025-06-30
11 | 01 | 2376 | HUM | 101 | Corridor Bridge Rails | Near Eureka, at various locations from 0.2 miles south of Eureka Slough Bridge to 0.2 miles north of Gannon Slough Bridge. Upgrade bridge rails and replace bridge. | 15678 | 1828 | 1828 | 3014 | 3014 | 238 | 238 | 2000 | 2000 | 287 | 287 | 8311 | 8311 | 0 | 1802 | 1802 | 1802 | 1639 | 1639 | 2018 | 15 | 15 | 173 | 0 | 0 | 2448 | 39 | 39 | 287 | 0 | 0 | 7430 | 2017-01-10 | 2019-03-15 | 2019-04-01 | 2019-11-21 |  |  | 2017-01-10 | 2019-03-14 | [6 empty] | 2019-08-14 | 2019-11-21 | 2021-12-01
12 | 01 | 2380 | HUM | 101 | Eureka CAPM | In Eureka, on 4th Street from Broadway to Eureka Slough Bridge; also on 5th street from O Street to Eureka Slough Bridge. Pavement rehabilitation. | 4811 | 232 | 232 | 384 | 384 | 314 | 314 | 725 | 725 | 21 | 21 | 3135 | 3135 | 0 | 218 | 218 | 218 | 257 | 257 | 528 | 18 | 18 | 284 | 0 | 0 | 678 | 0 | 0 | 16 | 0 | 0 | 3200 | 2018-05-01 | 2019-03-01 | 2019-03-15 | 2019-10-03 |  |  | 2018-06-14 | 2019-05-28 | 2019-06-24 | [6 empty] | 2019-11-01 | 2020-12-01
13 | 01 | 2382 | HUM | 101 | King Salmon Rehab 2R | In and near Eureka, from south of Fields Landing Overhead to north of Herrick Avenue Overcrossing. Roadway rehabilitation. (G13 Contingency) | 1969 | 646 | 646 | 1258 | 1258 | 54 | 54 | 0 | 0 | 11 | 11 | 0 | 0 | 0 | 495 | 495 | 495 | 0 | 0 | 883 | 0 | 0 | 47 | 0 | 0 | 5584 | 0 | 0 | 11 | 0 | 0 | 23331 | 2018-10-15 | 2020-01-15 | 2020-02-01 | 2020-07-06 |  |  | 2019-02-13 | [6 empty] | 2020-04-03 | 2020-05-01 | 2020-10-22 | 2022-04-01
14 | 01 | 2400 | HUM | 101 | HUM-101 Strengthen 2 Bridges | In Humboldt County, at South Fork Eel River Bridge and Separation No. 04-0065, South Fork Eel River Bridge No. 04-0076 (PM 35.5), and Arcata Overhead No. 04-0079R. Strengthen three bridge structures. | 16000 | 1010 | 1010 | 1355 | 1355 | 65 | 65 | 2102 | 2102 | 1359 | 1359 | 10109 | 10109 | 0 | 618 | 618 | 618 | 1088 | 1088 | 1325 | 10 | 10 | 47 | 0 | 0 | 1994 | 15 | 15 | 45 | 0 | 0 | 11529 | 2018-09-01 | 2019-06-01 | 2019-06-01 | 2019-11-14 |  |  | 2018-09-18 | 2019-05-01 | 2019-06-21 | [6 empty] | 2019-10-21 | 2021-10-04
15 | 01 | 2422 | HUM | 101 | Redcrest CAPM | Near Redcrest, from Englewood Park Undercrossing to Eel River Bridge and Overhead (R48.282). Pavement rehabilitation. | 21892 | 579 | 579 | 680 | 680 | 85 | 85 | 1518 | 1518 | 6 | 6 | 19024 | 19024 | 0 | 398 | 398 | 398 | 476 | 476 | 613 | 8 | 8 | 34 | 0 | 0 | 1459 | 3 | 3 | 3 | 0 | 0 | 17115 | 2018-06-14 | 2019-02-01 | 2019-02-01 | 2019-08-01 |  | 2018-10-17 | 2018-06-14 | 2019-01-31 | 2019-03-25 | [6 empty] | 2019-08-01 | 2020-12-01
16 | 01 | 2429 | HUM | 36 | 5 BRIDGES DECK PRESERVATION | Near Bridgeville, at Van Duzen River Bridge No. 04-0284 (PM 17.94) and Van Duzen River Bridge No. 04-0293 (PM R23.91); also on Route 211 near Ferndale at Salt River Bridge No. 04-131 (PM R75.15), in Lake County on Route 29 near Lakeport at Hill Road East Overcrossing No. 14-0039 (PM R43.75), and in Mendocino County on Route 101 near Longvale at Long Valley Creek Rest Area Bridge No. 10-0240Y (PM 61.82). Apply polyester concrete overlay or methacrylate treatment to bridge decks. | 3322 | 268 | 268 | 757 | 757 | 42 | 42 | 772 | 772 | 3 | 3 | 1480 | 1480 | 0 | 116 | 116 | 263 | 0 | 0 | 689 | 0 | 0 | 31 | 0 | 0 | 702 | 0 | 0 | 3 | 0 | 0 | 1340 | 2020-05-15 | 2021-07-20 | 2021-09-08 | 2022-04-11 | [8 empty] | 2020-05-15 | 2021-07-20 | 2021-09-08 | 2022-04-11 | 2023-12-29
17 | 01 | 2430 | HUM | 299 | 200/299 SEPARATION | Near Arcata, from 1.5 miles east to 2.0 miles east of Route 101 at the Route 200/299 Separation No. 04-0184. Establish standard vertical clearance. | 6630 | 564 | 564 | 857 | 857 | 26 | 26 | 1124 | 1124 | 31 | 31 | 4028 | 4028 | 0 | 347 | 347 | 590 | 0 | 0 | 786 | 0 | 0 | 21 | 0 | 0 | 1033 | 0 | 0 | 27 | 0 | 0 | 4022 | 2019-08-01 | 2020-02-04 | 2020-03-03 | 2020-08-04 | [8 empty] | 2019-10-01 | 2020-04-15 | 2020-05-01 | 2020-09-07 | 2021-12-01
18 | 01 | 2433 | HUM | 299 | HUM-299 Culverts | Near Blue Lake and Willow Creek, from 0.1 mile east of Route 200 to 0.5 mile east of Boise Creek Campground. Rehabilitate drainage culverts. | 8742 | 904 | 904 | 958 | 958 | 77 | 77 | 1615 | 1615 | 920 | 920 | 4268 | 4268 | 0 | 494 | 494 | 1069 | 0 | 0 | 1018 | 0 | 0 | 52 | 0 | 0 | 1540 | 0 | 0 | 900 | 0 | 0 | 4974 | 2020-05-01 | 2021-08-01 | 2021-08-01 | 2022-02-01 | [8 empty] | 2020-05-01 | 2021-07-02 | 2021-08-02 | 2022-02-01 | 2024-10-03
19 | 01 | 2439 | HUM | 101 | TRINIDAD CAPM | Near Trinidad, from 1.3 miles south of School Road to 0.4 mile north of Big Lagoon Bridge. Pavement rehabilitation. | 50631 | 332 | 332 | 561 | 561 | 84 | 84 | 4287 | 4287 | 12 | 12 | 45355 | 45355 | 0 | 198 | 198 | 312 | 0 | 0 | 520 | 0 | 0 | 59 | 0 | 0 | 3814 | 0 | 0 | 11 | 0 | 0 | 40470 | 2019-08-01 | 2020-11-01 | 2020-11-15 | 2021-06-01 | [8 empty] | 2019-08-01 | 2020-11-01 | 2020-11-15 | 2021-06-01 | 2022-12-01
20 | 01 | 2447 | HUM | 101 | Little Lost Man Fish Passage | Near Orick, at 0.2 mile south of Lost Man Creek Bridge. Remove fish passage barrier. | 10793 | 1505 | 1505 | 720 | 720 | 193 | 193 | 1933 | 1933 | 1523 | 1523 | 4919 | 4919 | 0 | 1219 | 1219 | 1219 | 650 | 650 | 712 | 25 | 25 | 101 | 0 | 0 | 2058 | 8 | 8 | 8 | 0 | 0 | 4909 | 2018-03-01 | 2019-03-01 | 2019-03-15 | 2019-10-15 |  |  | 2018-06-01 | 2019-03-01 | 2019-06-19 | [6 empty] | 2019-11-30 | 2021-12-01
21 | 01 | 2449 | HUM | 96 | HUM96-169 5 BRIDGES Rail Upgrade | Near Weitchpec and Orleans, at Aikens Creek Bridge No. 04-0059 (PM 28.07), Bluff Creek Bridge No. 04-0063 (PM 28.27), Bluff Creek Bridge No. 04-0225 (PM R28.91), and Slate Creek Bridge No. 04-0061 (PM 29.92); also on Route 169 at Rube Creek Bridge No. 04-0215 (PM 27.57). Upgrade bridge rails at five locations and also strengthen for truck permit load capacity at two locations. | 16293 | 1050 | 1050 | 2127 | 2127 | 110 | 110 | 2242 | 2242 | 278 | 278 | 10486 | 10486 | 0 | 199 | 199 | 998 | 0 | 0 | 1487 | 0 | 0 | 86 | 0 | 0 | 1860 | 0 | 0 | 278 | 0 | 0 | 8385 | 2020-04-01 | 2021-10-05 | 2021-12-15 | 2022-12-01 | [8 empty] | 2020-06-01 | 2021-09-01 | 2021-11-02 | 2022-03-23 | 2024-12-02
22 | 01 | 2524 | HUM | 254 | Avenue Culvert Rehab Revegetation | Near Miranda, from 0.3 mile north of Redwood Lane to 0. 9 mile south of Bear Creek Bridge Environmental mitigation for culvert rehabilitation project EA 40950. | 181 | 0 | 0 | 0 | 0 | 0 | 0 | 130 | 130 | 0 | 0 | 51 | 51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 126 | 0 | 0 | 0 | 0 | 0 | 0
23 | 01 | 3098 | LAK | 20 | Manning & Polk Jones Cattle Pass | Near Upper Lake, at Polk Jones Cattlepass Bridge No. 14-0034 (PM 9.41); also, on Route 29 at Manning Creek Bridge No. 14-0067 (PM R38.91). Replace and upgrade bridge rails. | 3780 | 1017 | 1017 | 410 | 410 | 126 | 126 | 625 | 625 | 11 | 11 | 1591 | 1591 | 0 | 1016 | 1016 | 1016 | 0 | 0 | 430 | 0 | 0 | 43 | 0 | 0 | 499 | 2 | 2 | 11 | 0 | 0 | 1392 | 2019-01-01 | 2019-07-01 | 2019-08-15 | 2020-01-01 |  |  | 2019-06-24 | [6 empty] | 2020-05-15 | 2020-05-30 | 2020-09-01 | 2022-01-01
24 | 01 | 3104 | LAK | 53 | EAST LAKE CO TMS | In Lake County, on Routes 20, 29, 53, and 175 at various locations. Upgrade the existing Transportation Management System (TMS) elements to improve traffic monitoring and data transmission. | 4883 | 618 | 618 | 844 | 844 | 186 | 186 | 1073 | 1073 | 39 | 39 | 2123 | 2123 | 0 | 263 | 263 | 580 | 0 | 0 | 737 | 0 | 0 | 157 | 0 | 0 | 1039 | 3 | 3 | 38 | 0 | 0 | 1801 | 2019-07-01 | 2020-06-25 | 2020-08-01 | 2020-12-17 | [8 empty] | 2020-01-02 | 2020-12-15 | 2021-01-04 | 2021-05-19 | 2022-12-01
25 | 01 | 3107 | LAK | 20 | Bachelor Creek Bridge | Near Upper Lake, at Bachelor Creek Bridge No. 14-0001. Replace multi-plate steel culvert bridge with precast concrete box culverts and wingwalls. | 6324 | 577 | 577 | 708 | 708 | 14 | 14 | 704 | 704 | 15 | 15 | 4306 | 4306 | 0 | 556 | 556 | 556 | 196 | 196 | 707 | 1 | 1 | 14 | 0 | 0 | 583 | 9 | 9 | 7 | 0 | 0 | 3806 | 2018-12-26 | 2019-06-24 | 2020-07-15 | 2020-12-17 |  |  | 2018-12-17 | [6 empty] | 2020-04-15 | 2020-05-01 | 2020-08-26 | 2022-12-01
26 | 01 | 3130 | LAK | 29 | Morrison, Robinson & Kelsey Creek | Near Upper Lake, at Robinson Creek Bridge No. 14-0030 (PM 50.82); also on Route 175 at Kelsey Creek Bridge No. 14-0044 (PM 19.48); also on Route 20 at Morrison Creek Bridge No. 14-0004 (PM 16.81). Widen bridge and upgrade bridge rails at Robinson Creek Bridge and Morrison Creek Bridge, and replace existing Kelsey Creek Bridge. | 12067 | 1434 | 1434 | 1882 | 1882 | 223 | 223 | 2030 | 2030 | 833 | 833 | 5665 | 5665 | 0 | 146 | 146 | 1311 | 0 | 0 | 1770 | 0 | 0 | 195 | 0 | 0 | 1829 | 0 | 0 | 0 | 0 | 0 | 5075 | [12 empty] | 2020-06-15 | 2021-04-21 | 2021-05-07 | 2021-09-01 | 2023-12-01
27 | 01 | 4442 | MEN | 101 | Hopland CAPM | Near Hopland, from 0.7 mile south of Geysers Road to Hopland Overhead. Pavement rehabilitation. | 16210 | 362 | 362 | 830 | 830 | 4 | 4 | 1724 | 1724 | 1 | 1 | 13289 | 13289 | 0 | 224 | 224 | 224 | 748 | 748 | 833 | 1 | 1 | 4 | 0 | 0 | 1679 | 0 | 0 | 0 | 0 | 0 | 15381 | 2018-09-01 | 2019-05-01 | 2019-05-15 | 2019-10-01 |  |  | 2018-09-24 | 2019-03-21 | 2019-05-28 | [6 empty] | 2019-12-16 | 2021-12-01
28 | 01 | 4491 | MEN | 1 | Salmon Creek Bridge Replacement | Near Albion, from 2.2 miles north of Route 128 Junction to 0.2 mile north of Salmon Creek Bridge No. 10-0134. Bridge replacement. (G13 Contingency) | 19085 | 6420 | 6420 | 5593 | 5593 | 748 | 748 | 0 | 0 | 6324 | 6324 | 0 | 0 | 0 | 5143 | 5143 | 7100 | 0 | 0 | 3130 | 0 | 0 | 668 | 0 | 0 | 7430 | 80 | 80 | 6324 | 0 | 0 | 33247 | 2018-11-15 | 2020-01-31 | 2020-02-14 | 2020-03-01 | [8 empty] | 2021-07-16 | 2022-04-25 | 2022-06-15 | 2022-10-01 | 2026-10-15
29 | 01 | 4507 | MEN | 1 | Mendocino Coast Two Bridges | Near the Mendocino community, at Jack Peters Creek Bridge No. 10-0150 (PM 51.87); also in Fort Bragg at Pudding Creek Bridge No. 10-0158 (PM 62.12). Upgrade and replace barrier rails and bridge replacement. | 31966 | 4587 | 4587 | 2825 | 2825 | 335 | 335 | 4750 | 4750 | 450 | 450 | 19019 | 19019 | 0 | 4183 | 4183 | 4954 | 0 | 0 | 2970 | 0 | 0 | 348 | 0 | 0 | 2971 | 20 | 20 | 153 | 0 | 0 | 4271 | 2018-12-14 | 2020-02-28 | 2020-03-06 | 2020-09-04 | [8 empty] | 2020-04-15 | 2021-06-11 | 2021-06-18 | 2021-10-20 | 2024-10-03
30 | 01 | 4587 | MEN | 20 | Calpella 2 Bridge Replacements | Near Ukiah, from east of Route 101 to east of Road 144 at Russian River Bridge and Overhead No. 10-0182 and Redwood Valley Undercrossing No. 10-0183. Replace two bridges with a single bridge on a new alignment. | 45210 | 2087 | 2087 | 3129 | 3129 | 301 | 301 | 9335 | 9335 | 4490 | 4490 | 25868 | 25868 | 0 | 1435 | 1435 | 3533 | 0 | 0 | 2549 | 0 | 0 | 300 | 0 | 0 | 6910 | 7 | 7 | 4490 | 0 | 0 | 23335 | 2019-02-15 | 2020-02-15 | 2020-03-01 | 2020-09-01 | [8 empty] | 2020-02-01 | 2021-05-14 | 2021-05-31 | 2021-10-20 | 2024-10-03
31 | 01 | 4588 | MEN | 1 | Elk Creek Bridge Replacement | Near Fort Bragg, at Elk Creek Bridge No. 10-0120. Replace bridge. | 13416 | 1363 | 1363 | 1445 | 1445 | 191 | 191 | 1759 | 1759 | 333 | 333 | 8325 | 8325 | 0 | 830 | 830 | 1559 | 0 | 0 | 1424 | 0 | 0 | 168 | 0 | 0 | 2921 | 0 | 0 | 333 | 0 | 0 | 9080 | 2019-09-13 | 2021-02-26 | 2021-03-12 | 2021-08-27 | [8 empty] | 2021-01-15 | 2022-04-29 | 2022-05-06 | 2022-08-31 | 2024-10-03
32 | 01 | 4588B | MEN | 1 | Hare Creek Bridge | Near Fort Bragg, at Hare Creek Bridge No. 10-0175. Upgrade bridge rails and widen to make standard. | 22356 | 2770 | 2770 | 2979 | 2979 | 183 | 183 | 3498 | 3498 | 474 | 474 | 12452 | 12452 | 0 | 230 | 230 | 1942 | 0 | 0 | 2462 | 0 | 0 | 152 | 0 | 0 | 2676 | 0 | 0 | 474 | 0 | 0 | 10137 | 2020-10-01 | 2022-04-01 | 2022-05-01 | 2022-12-01 | [8 empty] | 2021-01-15 | 2022-03-07 | 2022-03-15 | 2022-07-20 | 2025-10-03
33 | 01 | 4626 | MEN | 1 | POINT ARENA CAPM | In and near Point Arena, from Sonoma County line to 0.1 mile south of Mill Street. Pavement rehabilitation. | 16602 | 623 | 623 | 704 | 704 | 85 | 85 | 2590 | 2590 | 15 | 15 | 12585 | 12585 | 0 | 446 | 446 | 446 | 121 | 121 | 661 | 3 | 3 | 66 | 0 | 0 | 2393 | 6 | 6 | 5 | 0 | 0 | 12544 | 2018-12-01 | 2019-09-17 | 2019-10-01 | 2020-03-15 |  | 2018-12-06 | 2018-12-28 | [6 empty] | 2019-11-08 | 2019-11-22 | 2020-03-19 | 2020-10-15
34 | 01 | 4627 | MEN | 101 | South Fork Eel River Bridge Seismic | Near Piercy, at South Fork Eel River Bridge No. 10-0218 (PM R106.57); also in Humboldt County (PM T0.0 to T0.1). Seismic bridge retrofit, bridge rail upgrade, restripe for wider shoulders and bicycle access, and upgrade deck drainage. | 6924 | 739 | 739 | 1028 | 1028 | 248 | 248 | 1278 | 1278 | 26 | 26 | 3605 | 3605 | 0 | 177 | 177 | 701 | 0 | 0 | 849 | 0 | 0 | 199 | 0 | 0 | 995 | 0 | 0 | 18 | 0 | 0 | 3231 | 2020-10-01 | 2022-01-01 | 2022-01-15 | 2022-06-01 | [8 empty] | 2020-10-01 | 2022-01-01 | 2022-01-15 | 2022-06-01 | 2024-02-01
35 | 01 | 4692 | MEN | 162 | South Eel River Bridge Seismic | Near Longvale, from 8.2 miles to 8.3 miles east of Route 101 at Eel River Bridge No. 10-0236. Bridge seismic retrofit. | 13339 | 737 | 737 | 1295 | 1295 | 127 | 127 | 4179 | 4179 | 618 | 618 | 6383 | 6383 | 0 | 410 | 410 | 1216 | 0 | 0 | 1428 | 0 | 0 | 171 | 0 | 0 | 2513 | 0 | 0 | 152 | 0 | 0 | 5371 | 2020-10-01 | 2021-12-30 | 2022-01-15 | 2022-06-01 | [8 empty] | 2020-10-01 | 2021-12-30 | 2022-01-15 | 2022-06-01 | 2024-12-01
36 | 01 | 4710 | MEN | 271 | McCoy Creek Re-vegetation | Near Piercy, from 0.7 mile north of Routes 271/101 Separation Bridge No. 10-0217 to 0.4 mile south of Sidehill Viaduct No. 10-0100. Mitigation planting and monitoring for EA 0A840. | 377 | 0 | 0 | 0 | 0 | 0 | 0 | 172 | 172 | 0 | 0 | 205 | 205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 163 | 0 | 0 | 0 | 0 | 0 | 205 | 2017-04-27 | 2018-04-15 | 2020-07-15 | 2020-09-01 |  |  | 2017-04-27 | 2018-04-15 | [6 empty] | 2020-07-15 | 2020-09-15 | 2025-12-01
37 | 01 | 7002 | HUM | 101 | HUM-101/MEN-271 Culverts | Near Garberville, from north of Redwood Drive to 1.3 miles south of Myers Flat; also in Mendocino County, on Route 271 near Piercy, from 0.5 mile north of Confusion Hill to 0.5 mile north of Route 101 Separation (PM 16.1 to 20.0). Rehabilitate or replace drainage culverts. | 6171 | 878 | 878 | 866 | 866 | 309 | 309 | 909 | 909 | 403 | 403 | 2806 | 2806 | 0 | 403 | 403 | 831 | 0 | 0 | 749 | 0 | 0 | 249 | 0 | 0 | 887 | 0 | 0 | 696 | 0 | 0 | 1671 | 2020-03-01 | 2021-03-01 | 2021-03-01 | 2021-08-01 | [8 empty] | 2020-03-01 | 2021-03-01 | 2021-03-01 | 2021-08-01 | 2022-12-01
38 | 01 | 7017 | LAK | 29 | MT KONOCTI TMS | In Lake and Mendocino Counties, on Routes 20, 29, 101, 175, and 281 at various locations. Upgrade the existing Transportation Management System (TMS) elements to improve traffic monitoring and data transmission. | 4627 | 587 | 587 | 852 | 852 | 50 | 50 | 1021 | 1021 | 30 | 30 | 2087 | 2087 | 0 | 267 | 267 | 593 | 0 | 0 | 723 | 0 | 0 | 77 | 0 | 0 | 1002 | 3 | 3 | 30 | 0 | 0 | 1770 | 2019-07-01 | 2020-06-25 | 2020-08-01 | 2020-12-17 | [8 empty] | 2020-01-02 | 2020-12-15 | 2021-01-04 | 2021-05-19 | 2022-12-01
39 | 02 | 3445A | SHA | 005 | Redding to Anderson Widening, Phase 2 | In Shasta County near Redding from 0.6 mile south of Knighton Road Overcrossing to 0.4 mile south of Churn Creek Road Overcrossing and near Anderson from route 5/273 separation to the Sacrament River Bridge. Widen to six lanes. | 60522 | 333 | 0 | 6140 | 3000 | 280 | 220 | 17800 | 9100 | 1262 | 1221 | 129803 | 46981 | 132859 | 334 | 0 | 334 | 8166 | 3497 | 8166 | 484 | 425 | 485 | 2302 | 1197 | 14972 | 457 | 414 | 0 | 13986 | 5156 | 132859 | 2013-03-29 | 2018-05-01 | 2018-05-04 | 2018-09-25 | 2021-10-02 | 2018-10-17 |  | 2018-05-01 | 2018-05-04 | 2018-11-30 | [6 empty] | 2021-10-02
40 | 02 | 3467 | LAS | 299 | Bieber to Adin Pavement | Near Adin, from west of Boyd Hill Lookout Road to Butte Creek Bridge; also in Modoc County from Ash Creek Bridge to east of County Road 87 (PM 0.0/0.5 and PM 1.0/1.8);also in Modoc County on Route 139 (PM 0.116/R0.231). Roadway rehabilitation. | 25456 | 1790 | 1790 | 1330 | 1330 | 325 | 325 | 2150 | 2150 | 811 | 811 | 19050 | 19050 | 0 | 1682 | 1682 | 1682 | 198 | 198 | 1083 | 69 | 69 | 276 | 0 | 0 | 1668 | 68 | 68 | 811 | 0 | 0 | 18200 | 2019-01-17 | 2020-01-17 | 2020-02-21 | 2020-08-25 |  |  | 2019-01-18 | [6 empty] | 2020-01-17 | 2020-02-21 | 2020-09-05 | 2022-12-01
41 | 02 | 3468 | LAS | 036 | Good Fred | In Lassen County near Westwood from 1.3 miles west of Goodrich Creek Bridge to 1.0 mile west of Willard Creek Road.. Rehabilitate Roadway and Replace Bridge Rehabilitate Roadway and Replace Bridge | 7834 | 4484 | 4484 | 2950 | 2950 | 400 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4442 | 4442 | 4442 | 2062 | 2062 | 3188 | 297 | 297 | 447 | 0 | 0 | 3288 | 223 | 223 | 5011 | 0 | 0 | 29436 | 2018-05-25 | 2019-08-01 | 2019-08-14 | 2019-11-13 |  | 2018-10-17 | 2018-05-25 | [6 empty] | 2019-10-01 | 2019-10-09 | 2020-03-15 | 2022-04-15
42 | 02 | 3485 | TRI | 3 | Swift Creek Bridge Replacement | Near Trinity Center, from 1.3 miles south to 0.7 mile north of Swift Creek Bridge. Replace Swift Creek Bridge No. 05-0059. | 17825 | 1530 | 1530 | 1680 | 1680 | 284 | 284 | 2090 | 2090 | 751 | 751 | 11490 | 11490 | 0 | 1510 | 1510 | 1510 | 175 | 175 | 1298 | 107 | 107 | 277 | 0 | 0 | 2017 | 7 | 7 | 751 | 0 | 0 | 11490 | 2019-01-17 | 2020-04-16 | 2020-05-21 | 2020-12-01 |  |  | 2018-12-13 | [6 empty] | 2020-04-16 | 2020-05-21 | 2020-12-01 | 2022-12-29
43 | 02 | 3515 | TEH | 5 | Sacramento River Bridge Seismic | In Red Bluff, at Sacramento River Bridge No. 08-0095L/R. Retrofit bridges. | 24643 | 2290 | 2290 | 1659 | 1659 | 280 | 280 | 3962 | 3962 | 152 | 152 | 16300 | 16300 | 0 | 2228 | 2228 | 2228 | 971 | 971 | 1860 | 57 | 57 | 146 | 0 | 0 | 3532 | 38 | 38 | 152 | 0 | 0 | 16269 | 2018-07-17 | 2019-11-24 | 2019-12-25 | 2020-06-24 |  |  | 2018-05-21 | [6 empty] | 2020-02-12 | 2020-03-04 | 2020-07-23 | 2023-07-30
44 | 02 | 3516 | TRI | 299 | Sis Tri Deck Rehab | In Trinity County on Routes 299 and 36 and in Siskiyou County on Route 96 at various locations. Bridge preventative maintenance at 9 bridges. | 11330 | 1030 | 1030 | 1400 | 1400 | 150 | 150 | 1910 | 1910 | 40 | 40 | 6800 | 6800 | 0 | 536 | 536 | 536 | 347 | 347 | 988 | 3 | 3 | 139 | 0 | 0 | 1769 | 3 | 3 | 23 | 0 | 0 | 6595 | 2018-09-28 | 2019-09-06 | 2019-09-13 | 2020-02-14 |  |  | 2018-09-24 | [6 empty] | 2019-09-06 | 2019-10-15 | 2020-04-05 | 2022-10-11
45 | 02 | 3543 | VAR | 005 | Sims Crag Combine | In Shasta and Siskiyou Counties about 7 miles north of Pollard Flat from 0.8 mile south to 0.7 mile north of Sims Road Undercrossing and from 0.6 mile south of Castle Crags Drive Undercrossing to 0.2 mile south of South Dunsmuir Undercrossing.. Replace Bridges Replace Bridges | 30332 | 2320 | 2320 | 2880 | 2880 | 260 | 260 | 4799 | 4799 | 36 | 36 | 20037 | 20037 | 0 | 1678 | 1678 | 1678 | 2024 | 2024 | 2455 | 20 | 20 | 134 | 0 | 0 | 3415 | 4 | 4 | 16 | 0 | 0 | 20037 | 2018-02-01 | 2019-02-22 | 2019-03-26 | 2019-08-27 |  | 2018-10-17 | 2018-02-01 | 2019-02-22 | 2019-03-22 | [6 empty] | 2019-08-27 | 2021-12-31
46 | 02 | 3546 | SIS | 3 | Lower Moffett Creek Scour-DES Brokered Project | North of Fort Jones, from 0.3 mile south to 0.3 mile north of West Moffett Creek Road at Moffett Creek Bridge No. 02-0042. Bridge replacement. | 7877 | 1400 | 1400 | 700 | 700 | 80 | 80 | 1540 | 1540 | 237 | 237 | 3920 | 3920 | 0 | 1287 | 1287 | 1615 | 0 | 0 | 702 | 0 | 0 | 45 | 0 | 0 | 1440 | 7 | 7 | 130 | 0 | 0 | 6762 | 2019-09-06 | 2020-07-31 | 2020-08-28 | 2021-02-26 | [8 empty] | 2019-09-06 | 2020-07-31 | 2020-08-28 | 2021-02-26 | 2022-01-12
47 | 02 | 3549 | TEH | Var | District Wide Scour Counter-Measures | In Tehama County, on Routes 5, 32, and 36 at various locations; also in Shasta County on Routes 5 and 44; also in Lassen County on Route 299 at various locations. Bridge scour prevention at nine bridges. | 5422 | 920 | 920 | 720 | 720 | 265 | 265 | 600 | 600 | 517 | 517 | 2400 | 2400 | 0 | 716 | 716 | 716 | 87 | 87 | 677 | 76 | 76 | 194 | 0 | 0 | 583 | 54 | 54 | 517 | 0 | 0 | 2400 | 2019-02-18 | 2020-02-28 | 2020-03-30 | 2020-08-26 |  |  | 2019-03-27 | [6 empty] | 2020-02-28 | 2020-03-30 | 2020-09-04 | 2022-12-30
48 | 02 | 3550 | TEH | 36 | Red Bluff Drainage | Near Red Bluff, from 0.6 mile east of Teadoc Road to 1.3 miles west of Kinney Avenue at various locations. Drainage system restoration. | 6044 | 850 | 850 | 660 | 660 | 620 | 620 | 1310 | 1310 | 79 | 79 | 2525 | 2525 | 0 | 678 | 678 | 678 | 164 | 164 | 555 | 20 | 20 | 397 | 0 | 0 | 1262 | 34 | 34 | 79 | 0 | 0 | 2525 | 2018-07-23 | 2019-09-03 | 2019-10-10 | 2020-02-13 |  |  | 2018-07-18 | [6 empty] | 2019-09-03 | 2019-10-10 | 2020-04-10 | 2020-12-29
49 | 02 | 3556 | SIS | 5 | North Canyon TMS Improvement | In Siskiyou and Shasta Counties, on Routes 5 and 89 at various locations. Upgrade Transportation Management System (TMS) field elements. | 6430 | 485 | 485 | 1000 | 1000 | 429 | 429 | 720 | 720 | 196 | 196 | 3600 | 3600 | 0 | 419 | 419 | 419 | 885 | 885 | 979 | 398 | 398 | 402 | 0 | 0 | 650 | 206 | 206 | 375 | 0 | 0 | 3530 | 2017-12-15 | 2019-01-22 | 2019-01-28 | 2019-08-06 |  |  | 2017-12-05 | 2019-04-10 | 2019-05-02 | [6 empty] | 2019-09-05 | 2022-01-03
50 | 02 | 3558 | TEH | 36 | West Red Bluff CAPM | In Red Bluff, from east of Baker Road to east of East Sand Slough Bridge. Pavement rehabilitation. | 9617 | 700 | 700 | 915 | 915 | 260 | 260 | 1020 | 1020 | 122 | 122 | 6600 | 6600 | 0 | 641 | 641 | 641 | 732 | 732 | 941 | 150 | 150 | 274 | 0 | 0 | 780 | 50 | 50 | 122 | 0 | 0 | 6600 | 2017-12-22 | 2019-07-02 | 2019-08-02 | 2020-02-19 |  |  | 2017-12-21 | 2019-07-02 | [6 empty] | 2019-09-23 | 2020-02-07 | 2021-12-31
51 | 02 | 3586 | TRI | 3 | Trinity 3 Drainage | Near Trinity Center, from 0.5 mile south of Trinity River Bridge to 1.6 miles north of Bowerman Ridge Road at various locations. Drainage system restoration. | 8177 | 1550 | 1550 | 975 | 975 | 550 | 550 | 1580 | 1580 | 79 | 79 | 3443 | 3443 | 0 | 975 | 975 | 975 | 110 | 110 | 729 | 36 | 36 | 478 | 0 | 0 | 1284 | 15 | 15 | 79 | 0 | 0 | 3443 | 2018-09-01 | 2019-09-03 | 2019-10-10 | 2020-02-13 |  |  | 2018-11-01 | [6 empty] | 2020-02-28 | 2020-03-20 | 2020-09-04 | 2020-12-29
52 | 02 | 3587 | PLU | 70 | Plumas 70 Drainage | In Plumas County, from 0.4 mile east of Butte County line to 3.3 miles west of Route 89 at various locations. Drainage rehabilitation. | 6174 | 1200 | 1200 | 840 | 840 | 600 | 600 | 920 | 920 | 89 | 89 | 2525 | 2525 | 0 | 885 | 885 | 885 | 60 | 60 | 583 | 21 | 21 | 353 | 0 | 0 | 675 | 47 | 47 | 89 | 0 | 0 | 2525 | 2018-09-01 | 2019-06-04 | 2019-07-11 | 2020-02-13 |  |  | 2018-08-31 | [6 empty] | 2020-01-10 | 2020-01-17 | 2020-05-21 | 2020-12-29
53 | 02 | 3588 | BUT | 70 | Butte 70 Drainage | Near Pulga, from 3.0 miles west of Coal Canyon Road to Plumas County line at various locations. Drainage system restoration. | 6144 | 1175 | 1175 | 880 | 880 | 600 | 600 | 850 | 850 | 114 | 114 | 2525 | 2525 | 0 | 1057 | 1057 | 1057 | 82 | 82 | 762 | 219 | 219 | 401 | 0 | 0 | 752 | 18 | 18 | 114 | 0 | 0 | 2525 | 2018-09-01 | 2019-09-04 | 2019-10-11 | 2020-02-13 |  |  | 2018-08-31 | [6 empty] | 2020-01-10 | 2020-01-17 | 2020-05-21 | 2020-12-29
54 | 02 | 3589 | MOD | 139 | Modoc 139 Drainage | Near Canby, from 1.3 miles north of Howards Gulch Bridge to 0.1 mile south of Clear Lake Road, at various locations. Improve drainage facilities by repairing or replacing culverts. | 3752 | 890 | 890 | 360 | 360 | 250 | 250 | 700 | 700 | 71 | 71 | 1481 | 1481 | 0 | 117 | 117 | 688 | 0 | 0 | 355 | 0 | 0 | 241 | 0 | 0 | 620 | 0 | 0 | 70 | 0 | 0 | 1800 | [12 empty] | 2021-05-15 | 2022-05-22 | 2022-06-01 | 2022-09-20 | 2024-03-10
55 | 02 | 3599 | PLU | 70 | Chilcoot 2R | In Plumas and Lassen Counties, near Chilcoot, from 1.8 miles west of Route 49 to Route 395 (Plumas PM 90.3/95.964, Lassen PM 0.0/3.889). Roadway rehabilitation. | 23328 | 1200 | 1200 | 900 | 900 | 170 | 170 | 1693 | 1693 | 51 | 51 | 19314 | 19314 | 19314 | 989 | 989 | 989 | 686 | 686 | 686 | 110 | 110 | 166 | 236 | 236 | 1447 | 13 | 13 | 13 | 1647 | 1647 | 19314 | 2018-01-16 | 2019-02-25 | 2019-03-28 | 2019-08-27 |  | 2018-10-17 | 2018-01-16 | 2018-11-16 | 2018-12-07 | 2019-04-15 | [6 empty] | 2020-12-24
56 | 02 | 3601 | SIS | 96 | Ukonom 3 Drainage | Near Happy Camp, from 0.5 mile west of Clear Creek Bridge to 0.1 mile east of Doggett Creek Bridge. Drainage system restoration. | 5787 | 1450 | 1450 | 730 | 730 | 350 | 350 | 1060 | 1060 | 127 | 127 | 2070 | 2070 | 0 | 843 | 843 | 843 | 109 | 109 | 705 | 95 | 95 | 337 | 0 | 0 | 971 | 0 | 0 | 127 | 0 | 0 | 2070 | 2019-03-29 | 2020-02-17 | 2020-03-02 | 2020-09-01 |  |  | 2019-03-28 | [6 empty] | 2020-02-17 | 2020-03-02 | 2020-09-14 | 2022-11-15
57 | 02 | 3614 | SIS | 5 | Sac River BOH | In Dunsmuir, from Central Dunsmuir Undercrossing to 0.1 mile north of Siskiyou Avenue at Sacramento River Bridge and Overhead No. 02-0002. Replace southbound bridge deck. | 22649 | 1440 | 1440 | 2660 | 2660 | 450 | 450 | 3480 | 3480 | 269 | 269 | 14350 | 14350 | 0 | 598 | 598 | 1563 | 0 | 0 | 1909 | 0 | 0 | 145 | 0 | 0 | 2294 | 0 | 0 | 269 | 0 | 0 | 14350 | 2020-04-15 | 2021-12-15 | 2022-01-21 | 2022-09-20 | [8 empty] | 2020-04-15 | 2021-12-21 | 2022-01-21 | 2022-07-25 | 2025-12-31
58 | 02 | 3618 | SHA | 299 | Burney CAPM | Near Burney, from 2.6 miles east of Carberry Flat Road to 0.3 mile east of Burney Mountain Power Road. Rehabilitate pavement, upgrade guardrail, and make curbs Americans with Disabilities Act (ADA) compliant. | 17781 | 1430 | 1430 | 1300 | 1300 | 1020 | 1020 | 2430 | 2430 | 436 | 436 | 11165 | 11165 | 0 | 73 | 73 | 1263 | 0 | 0 | 1078 | 0 | 0 | 851 | 0 | 0 | 1702 | 0 | 0 | 436 | 0 | 0 | 11165 | 2020-09-08 | 2022-03-04 | 2022-04-04 | 2022-08-30 | [8 empty] | 2020-09-08 | 2022-03-04 | 2022-04-04 | 2022-08-30 | 2024-07-15
59 | 02 | 3619 | PLU | 70 | Cromberg Rehab | In and near Cromberg and Portola, from 0.2 mile east of Gill Ranch Road to 0.2 mile west of Big Grizzly Creek Bridge. Rehabilitate roadway, repair or replace culverts, upgrade guardrail, upgrade bridge railing at Humbug Creek Bridge No. 09-0022, and make pedestrian facilities American with Disabilities Act (ADA) compliant. (G13 Contingency) | 7744 | 3490 | 3490 | 2620 | 2620 | 1120 | 1120 | 0 | 0 | 514 | 514 | 0 | 0 | 0 | 952 | 952 | 3091 | 0 | 0 | 2017 | 0 | 0 | 677 | 0 | 0 | 4573 | 0 | 0 | 1209 | 0 | 0 | 88050 | 2020-11-05 | 2022-02-25 | 2022-03-28 | 2022-09-27 | [8 empty] | 2020-11-05 | 2022-02-25 | 2022-03-28 | 2022-09-27 | 2025-12-02
60 | 02 | 3620 | SIS | 96 | Portuguese and Cade Creek | Near Happy Camp, from 0.9 mile west to 0.4 mile west of Gordons Ferry Road at Cade Creek (PM 43.4 to 43.8); also, near Seiad Valley at Portuguese Creek (PM 57.0). Replace deteriorated large-diameter culverts with natural-bottom structures, reduce fish passage barriers, and adjust new approaches. (Long Lead Project) | 1720 | 1720 | 1720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 335 | 335 | 1567 | 0 | 0 | 1947 | 0 | 0 | 121 | 0 | 0 | 1810 | 0 | 0 | 45 | 0 | 0 | 6760 | 2021-09-07 | 2023-12-29 | 2024-01-29 | 2024-07-02 | [8 empty] | 2021-09-07 | 2023-12-29 | 2024-01-29 | 2024-07-02 | 2027-12-31
61 | 02 | 3622 | SIS | 96 | Stanshaw Creek and Sandy Bar | Near Somes Bar, from 0.6 mile east to 1.3 miles east of Irving Creek Bridge at Stanshaw Creek (PM R8.2); also, from 1.6 miles east of Irving Creek Bridge to 1.6 miles west of Ti Creek Bridge at Sandy Bar Creek (PM 9.1). Replace deteriorated large-diameter culverts with natural-bottom structures, reduce fish passage barriers, and adjust new approaches. (Long Lead Project) | 1910 | 1910 | 1910 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 215 | 215 | 1505 | 0 | 0 | 1846 | 0 | 0 | 118 | 0 | 0 | 2578 | 0 | 0 | 37 | 0 | 0 | 13700 | 2021-10-01 | 2024-01-19 | 2024-02-20 | 2024-08-27 | [8 empty] | 2021-10-01 | 2024-01-19 | 2024-02-20 | 2024-08-05 | 2027-12-31
62 | 02 | 3629 | SIS | 96 | Horse Creek Bridge Replacement | Near Horse Creek, at Horse Creek Bridge No. 02-0117, from 0.4 mile west of Klamath River Bridge to 2.0 miles west of Kohl Creek. Replace bridge on new alignment to correct scour critical conditions, improve safety, and reduce operational deficiencies. (Long Lead Project) | 2640 | 2640 | 2640 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 276 | 276 | 2200 | 0 | 0 | 2097 | 0 | 0 | 606 | 0 | 0 | 2623 | 0 | 0 | 810 | 0 | 0 | 14000 | 2021-09-01 | 2023-03-01 | 2023-10-01 | 2024-04-27 | [8 empty] | 2021-09-01 | 2023-03-01 | 2023-10-02 | 2024-04-26 | 2027-11-15
63 | 02 | 3630 | SHA | 5 | O Brien Deck and Rail Rehab | Near Lakehead, at O?Brien Undercrossing No. 06-0148L. Rehabilitate bridge deck with concrete overlay, upgrade bridge rails, and construct approach slabs. | 3692 | 250 | 250 | 600 | 600 | 40 | 40 | 580 | 580 | 7 | 7 | 2215 | 2215 | 0 | 203 | 203 | 203 | 278 | 278 | 390 | 4 | 4 | 21 | 0 | 0 | 459 | 0 | 0 | 0 | 0 | 0 | 2210 | 2019-11-05 | 2020-09-25 | 2020-10-26 | 2021-02-16 |  |  | 2019-01-31 | 2019-05-22 | 2019-05-30 | [6 empty] | 2019-12-24 | 2020-12-07
64 | 02 | 3631 | SIS | 5 | Azalea Deck and Rail Rehab | Near Mt. Shasta, at Azalea Road Overcrossing No. 02-0126. Rehabilitate bridge. | 3678 | 320 | 320 | 750 | 750 | 40 | 40 | 710 | 710 | 7 | 7 | 1851 | 1851 | 0 | 251 | 251 | 347 | 0 | 0 | 623 | 0 | 0 | 87 | 0 | 0 | 531 | 0 | 0 | 50 | 0 | 0 | 1851 | 2019-10-07 | 2020-09-25 | 2020-10-26 | 2021-04-10 | [8 empty] | 2019-10-07 | 2020-09-25 | 2020-10-26 | 2021-04-10 | 2022-07-15
65 | 02 | 3633 | TRI | 3 | Trinity Four Bridges | In Trinity County, at Dobbins Gulch Bridge No. 05-0042 (PM 0.6), Stuart Fork Bridge No. 05-0055 (PM 43.9) and Mule Creek Bridge No. 05-0056 (PM 48.5); also on Route 299, at Grass Valley Creek Bridge No. 05-0013 (PM 65.5). Repair unsound concrete, replace bearings and joint seals, repair bridge decks, and install barrier and approach slabs. | 10726 | 900 | 900 | 1030 | 1030 | 230 | 230 | 2060 | 2060 | 206 | 206 | 6300 | 6300 | 0 | 347 | 347 | 840 | 0 | 0 | 795 | 0 | 0 | 275 | 0 | 0 | 1393 | 0 | 0 | 206 | 0 | 0 | 6295 | 2020-07-02 | 2022-01-21 | 2022-02-22 | 2022-08-09 | [8 empty] | 2020-07-02 | 2022-01-21 | 2022-02-22 | 2022-08-09 | 2025-12-31
66 | 02 | 3642 | TEH | 99 | Champlin Slough | Near Los Molinos, from 0.2 mile south to 0.2 mile north of Champlin Slough Bridge No. 08-0006. Replace bridge to correct scour critical conditions. | 7560 | 850 | 850 | 1170 | 1170 | 90 | 90 | 990 | 990 | 90 | 90 | 4370 | 4370 | 0 | 364 | 364 | 945 | 0 | 0 | 1005 | 0 | 0 | 69 | 0 | 0 | 705 | 1 | 1 | 91 | 0 | 0 | 4054 | 2020-05-05 | 2021-10-22 | 2021-11-24 | 2022-04-19 | [8 empty] | 2020-05-05 | 2021-10-22 | 2021-11-24 | 2022-04-19 | 2024-01-02
67 | 02 | 3643 | SIS | 3 | Yreka Rehab | In Yreka, from 0.4 mile north of Laura Lane to Juniper Drive; also on Route 263 from Route 3 to 1.0 mile south of Long Gulch Road (PM 49.07 to 49.41). Reconstruct pavement structural section, replace sidewalk, driveways, curb ramps and pedestrian signals to meet current Americans with Disabilities Act (ADA) Standards, designate bikeways with new signage and pavement delineation. | 73992 | 1830 | 1830 | 2200 | 2200 | 5880 | 5880 | 9650 | 9650 | 1482 | 1482 | 52950 | 52950 | 0 | 952 | 952 | 1865 | 0 | 0 | 2073 | 0 | 0 | 5465 | 0 | 0 | 8105 | 1 | 1 | 1293 | 0 | 0 | 52950 | 2019-11-04 | 2022-03-04 | 2022-03-21 | 2022-09-27 | [8 empty] | 2020-05-01 | 2022-03-07 | 2022-03-21 | 2022-07-21 | 2025-11-17
68 | 02 | 3668 | TRI | 299 | Trinity Culverts | Near Salyer, at various locations from 0.1 mile west of White House Gulch Road to 0.4 mile west of Slattery Pond Road. Rehabilitate culverts. | 8931 | 930 | 930 | 980 | 980 | 330 | 330 | 990 | 990 | 311 | 311 | 5390 | 5390 | 0 | 408 | 408 | 833 | 0 | 0 | 741 | 0 | 0 | 306 | 0 | 0 | 705 | 1 | 1 | 56 | 0 | 0 | 3000 | 2020-06-03 | 2021-07-19 | 2021-08-19 | 2021-12-14 | [8 empty] | 2020-07-01 | 2021-07-19 | 2021-08-19 | 2021-12-14 | 2024-01-02
69 | 02 | 3685 | SIS | 5 | Dunsmuir GAP | In and near Dunsmuir and Mt. Shasta, from Sacramento River Bridge Overhead to Black Butte Overhead. Roadway rehabilitation. (G13 Contingency) | 6925 | 1620 | 1620 | 5090 | 5090 | 80 | 80 | 0 | 0 | 135 | 135 | 0 | 0 | 0 | 1280 | 1280 | 1883 | 0 | 0 | 4642 | 0 | 0 | 63 | 0 | 0 | 11282 | 0 | 0 | 135 | 0 | 0 | 116040 | 2020-10-02 | 2021-10-04 | 2022-03-10 | 2022-09-27 | [8 empty] | 2020-10-02 | 2021-10-04 | 2022-03-10 | 2022-09-27 | 2026-11-16
70 | 02 | 3696 | SIS | 5 | I 5 Big and Tall | In and near Yreka at Louie Road Overcrossing (OC) No. 02-0137 (PM R31.2), Moonlit Oaks Avenue Undercrossing (UC) No. 02-0159R&L (PM R45.6), Miner Street UC No. 02-0158R&L (PM R47.6), and North Yreka Separation No. 02-0150R&L (PM R48.2); also in Redding, Shasta County, at N273-N5 Connector OC No. 06-0137G (PM R18.5). Establish standard vertical clearance and improve to standard truck capacity. ACCELERATED BRIDGE (PA&ED Only) | 2790 | 2790 | 2790 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1203 | 1203 | 1203 | 0 | 0 | 1697 | 0 | 0 | 42 | 0 | 0 | 3317 | 0 | 0 | 21 | 0 | 0 | 19200 | 2019-03-01 | 2020-06-19 | 2020-07-21 | 2020-12-22 |  |  | 2019-03-01 | [6 empty] | 2025-06-19 | 2025-07-21 | 2025-12-22 | 2029-12-31
71 | 03 | 2425 | BUT | 99 | Cottonwood Creek Bridge Replacement | Near Richvale, at Cottonwood Creek Bridge No. 12-0120, from 0.3 mile south to 0.5 mile north of Nelson Avenue. Replace and realign scour-critical bridge. | 16190 | 1190 | 1190 | 1500 | 1500 | 270 | 270 | 2200 | 2200 | 934 | 934 | 10096 | 10096 | 0 | 1099 | 1099 | 1099 | 1180 | 1180 | 1860 | 19 | 19 | 145 | 0 | 0 | 1932 | 33 | 33 | 934 | 0 | 0 | 9624 | 2018-05-01 | 2019-10-01 | 2019-10-15 | 2020-05-15 |  |  | 2018-03-08 | [6 empty] | 2020-04-13 | 2020-06-01 | 2020-09-01 | 2021-11-01
72 | 03 | 2433 | BUT | 99 | But 99 Bridge Rail Replacement | In and near Chico, from north of Route 162 to north of Broyles Road. Bridge rail upgrade at six locations. | 9716 | 1080 | 1080 | 1400 | 1400 | 160 | 160 | 1425 | 1425 | 1246 | 1246 | 4405 | 4405 | 0 | 969 | 969 | 969 | 1059 | 1059 | 1496 | 19 | 19 | 101 | 0 | 0 | 1176 | 29 | 29 | 1246 | 0 | 0 | 4329 | 2018-02-01 | 2019-08-15 | 2019-08-15 | 2020-04-01 |  |  | 2018-02-15 | [6 empty] | 2019-08-01 | 2019-08-15 | 2020-04-01 | 2021-11-01
73 | 03 | 2437 | BUT | 99 | Chico TMS | In and near Chico, from Southgate Avenue to Garner Lane. Install Traffic Management System (TMS) elements. | 11711 | 636 | 636 | 1177 | 1177 | 41 | 41 | 1352 | 1352 | 35 | 35 | 8470 | 8470 | 0 | 516 | 516 | 652 | 0 | 0 | 1327 | 0 | 0 | 50 | 0 | 0 | 1210 | 0 | 0 | 42 | 0 | 0 | 8661 | 2019-07-02 | 2020-07-02 | 2020-08-01 | 2021-01-02 | [8 empty] | 2019-08-01 | 2020-09-15 | 2020-10-01 | 2021-02-25 | 2022-01-17
74 | 03 | 2633 | GLE | 162 | Butte City Bridge Replacement | At Butte City, from Route 45 to 0.1 mile east of McDougall Street. Replace Sacramento River Bridge an Viaduct No. 11-0017 and reconstruct east side roadway to conform with new structure. | 110400 | 5500 | 5500 | 5500 | 5500 | 1400 | 1400 | 10000 | 10000 | 3000 | 3000 | 85000 | 85000 | 0 | 5002 | 5002 | 5002 | 0 | 0 | 4033 | 0 | 0 | 1145 | 0 | 0 | 8056 | 17 | 17 | 2977 | 0 | 0 | 78141 | 2019-08-01 | 2021-09-01 | 2021-10-15 | 2022-04-01 |  |  | 2019-05-01 | [6 empty] | 2021-02-15 | 2021-03-01 | 2021-07-31 | 2023-10-01
75 | 03 | 3301 | SAC | 050 | US 50 Multimodal Corridor Enhancement Project/US 50 HOV Lanes(I-5 to Watt Ave) | In Sacramento County on US 50, from I-5 to 0.8 mile east of Watt Avenue. Construct 14 lane miles of HOV (or bus/carpool) lanes, widen twelve bridge structures, construct sound walls from Stockton Blvd to 65th Street, incorporate Intelligent Transportation System (ITS) elements into the HOV system, and replace and/or upgrade ancillary facilities including drainage systems, overhead signs, lighting, approach slabs, guard rail, and safety barriers. | 323900 | 13600 | 7800 | 13000 | 1400 | 4300 | 1800 | 36800 | 25800 | 5700 | 200 | 368900 | 286900 | 0 | 10183 | 4387 | 10183 | 8781 | 41 | 8781 | 701 | 37 | 5063 | 0 | 0 | 28534 | 486 | 33 | 0 | 182 | 0 | 0 | 2017-05-31 | 2020-02-03 | 2020-02-14 | 2020-07-15 | 2024-12-01 | 2018-10-17 | 2017-05-31 | [7 empty] | 2019-09-02 | 2020-02-03 | 2023-12-04
76 | 03 | 3312 | ED | 50 | ED 50 Advance Warning & ITS | In El Dorado County, from the Sacramento County line to east of Stateline Avenue. Upgrade new Transportation Management System (TMS) elements. | 13100 | 600 | 600 | 1000 | 1000 | 580 | 580 | 1620 | 1620 | 150 | 150 | 9150 | 9150 | 0 | 600 | 600 | 600 | 756 | 756 | 1045 | 68 | 68 | 522 | 0 | 0 | 1668 | 1 | 1 | 30 | 0 | 0 | 9504 | 2017-09-01 | 2020-01-15 | 2020-02-01 | 2020-09-01 |  |  | 2017-09-01 | [6 empty] | 2019-12-28 | 2020-01-11 | 2020-09-01 | 2021-12-01
77 | 03 | 3315 | ED | 50 | ED 50 Culverts | Near Cameron Park and Shingle Springs, from east of Silva Valley Parkway to west of El Dorado Road. Rehabilitate culverts. | 6855 | 725 | 725 | 570 | 570 | 540 | 540 | 940 | 940 | 180 | 180 | 3900 | 3900 | 0 | 424 | 424 | 727 | 0 | 0 | 544 | 0 | 0 | 515 | 0 | 0 | 925 | 2 | 2 | 171 | 0 | 0 | 3000 | 2020-02-01 | 2022-02-01 | 2022-02-01 | 2022-08-01 | [8 empty] | 2020-01-18 | 2022-03-09 | 2022-03-23 | 2022-08-02 | 2024-12-01
78 | 03 | 3317 | ED | 50 | ED 50 Culvert Rehab | In and near Placerville, from west of El Dorado Road to west of Schnell School Road. Rehabilitate deteriorated culverts. | 5620 | 320 | 320 | 600 | 600 | 120 | 120 | 960 | 960 | 620 | 620 | 3000 | 3000 | 0 | 199 | 199 | 258 | 0 | 0 | 556 | 0 | 0 | 115 | 0 | 0 | 984 | 0 | 0 | 835 | 0 | 0 | 3000 | 2020-05-01 | 2021-08-01 | 2021-08-15 | 2021-12-15 | [8 empty] | 2020-05-01 | 2021-08-01 | 2021-08-15 | 2021-12-15 | 2023-10-01
79 | 03 | 3335 | ED | 50 | Culvert Rehab and Wildlife Crossing | In and near Placerville, from west of Schnell School Road to east of Braeburn Lane. Rehabilitate deteriorated culverts and provide access for wildlife crossing the route. | 3923 | 183 | 183 | 290 | 290 | 60 | 60 | 480 | 480 | 310 | 310 | 2600 | 2600 | 0 | 146 | 146 | 146 | 90 | 90 | 313 | 29 | 29 | 53 | 0 | 0 | 403 | 18 | 18 | 15 | 0 | 0 | 2600 | [6 empty] | 2019-03-12 | [6 empty] | 2020-03-06 | 2020-03-06 | 2020-08-10 | 2023-09-11
80 | 03 | 4123 | NEV | 49 | Nev-49 Culvert Rehab (North) | In and near Grass Valley, from 0.2 mile north of Lime Kiln Road to Route 20 (PM R14.475). Rehabilitate culverts. | 4188 | 500 | 500 | 650 | 650 | 350 | 350 | 590 | 590 | 80 | 80 | 2018 | 2018 | 2018 | 274 | 274 | 274 | 460 | 460 | 460 | 199 | 199 | 232 | 62 | 62 | 504 | 5 | 5 | 5 | 296 | 296 | 2018 | 2017-08-31 | 2019-04-15 | 2019-04-30 | 2019-10-30 |  |  | 2017-08-31 | 2018-09-14 | 2018-09-28 | 2019-03-21 | [6 empty] | 2019-12-01
81 | 03 | 4124 | NEV | 49 | Nev-49 Culvert Rehab (South) | Near Higgins Corner, from the Placer County line to 0.3 mile north of Lime Kiln Road; also in Placer County, at PM R8.42 and PM R10.23. Rehabilitate drainage systems. | 5992 | 513 | 513 | 743 | 743 | 547 | 547 | 607 | 607 | 325 | 325 | 3257 | 3257 | 0 | 372 | 372 | 501 | 0 | 0 | 633 | 0 | 0 | 390 | 0 | 0 | 453 | 0 | 0 | 170 | 0 | 0 | 2064 | 2020-01-02 | 2021-10-01 | 2021-10-15 | 2022-04-15 | [8 empty] | 2019-08-14 | 2020-09-15 | 2020-10-01 | 2021-04-15 | 2021-12-01
82 | 03 | 4125 | NEV | 49 | COUNT STATION REPAIR & INSTALL | In various counties on various routes at various locations. Repair and install vehicle census count stations. | 13430 | 1000 | 1000 | 1190 | 1190 | 210 | 210 | 1800 | 1800 | 30 | 30 | 9200 | 9200 | 0 | 348 | 348 | 348 | 929 | 929 | 1181 | 19 | 19 | 159 | 0 | 0 | 1478 | 0 | 0 | 0 | 0 | 0 | 9200 | 2018-01-01 | 2019-09-01 | 2019-10-01 | 2020-04-15 |  |  | 2018-03-27 | [6 empty] | 2019-09-03 | 2019-10-01 | 2020-02-10 | 2023-10-02
83 | 03 | 4291 | PLA | 80 | UPGRADE EMS SIGNS | In various counties on various routes at various locations. Upgrade Extinguishable Message Signs (EMS) to LED. | 3015 | 290 | 290 | 410 | 410 | 180 | 180 | 500 | 500 | 35 | 35 | 1600 | 1600 | 0 | 215 | 215 | 215 | 370 | 370 | 398 | 39 | 39 | 85 | 0 | 0 | 591 | 0 | 0 | 35 | 0 | 0 | 1864 | 2018-01-01 | 2019-07-01 | 2019-08-01 | 2020-04-01 |  |  | 2018-03-19 | [6 empty] | 2019-08-15 | 2019-09-03 | 2020-02-07 | 2021-12-30
84 | 03 | 5079 | PLA | 80 | Colfax Culvert Rehabilitation | In and near Colfax, from west of Illinoistown Overcrossing to east of Cape Horn Undercrossing. Drainage system rehabilitation. | 4944 | 230 | 230 | 440 | 440 | 354 | 354 | 600 | 600 | 150 | 150 | 3170 | 3170 | 0 | 154 | 154 | 154 | 332 | 332 | 534 | 207 | 207 | 220 | 0 | 0 | 542 | 39 | 39 | 319 | 0 | 0 | 2867 | 2017-09-01 | 2019-12-15 | 2019-12-15 | 2020-08-05 |  |  | 2017-09-01 | [6 empty] | 2019-12-15 | 2019-12-15 | 2020-07-13 | 2021-08-01
85 | 03 | 5097 | PLA | 80 | PLA 80 Bridge Rehab | In Placer County, at various locations. Replace bridges at four locations. | 53515 | 3000 | 3000 | 6350 | 6350 | 485 | 485 | 6430 | 6430 | 550 | 550 | 36700 | 36700 | 0 | 2672 | 2672 | 2672 | 1968 | 1968 | 5606 | 37 | 37 | 508 | 0 | 0 | 4890 | 6 | 6 | 145 | 0 | 0 | 32872 | 2018-04-17 | 2020-04-20 | 2020-05-07 | 2020-08-27 |  | 2018-10-17 | 2018-04-17 | [6 empty] | 2020-04-20 | 2020-05-07 | 2020-08-27 | 2025-12-01
86 | 03 | 5105 | PLA | 80 | Culvert Rehab | Near Weimar, from 0.2 mile west of Crother Road to 0.1 mile west of Weimar Road at various locations. Drainage system rehabilitation. | 3456 | 220 | 220 | 470 | 470 | 140 | 140 | 610 | 610 | 70 | 70 | 1946 | 1946 | 1946 | 191 | 191 | 191 | 444 | 444 | 444 | 41 | 41 | 124 | 21 | 21 | 529 | 1 | 1 | 1 | 146 | 146 | 1946 | 2017-10-02 | 2018-10-01 | 2018-10-11 | 2019-02-15 |  |  | 2017-10-27 | 2018-10-19 | 2018-11-29 | 2019-04-11 | [6 empty] | 2019-12-01
87 | 03 | 5114 | PLA | 80 | Secret Town Culvert Rehabilitation | Near Magra, from Secret Town Overcrossing to the Gold Run Safety Roadside Rest Area (SRRA). Rehabilitate drainage systems. | 5386 | 429 | 429 | 667 | 667 | 195 | 195 | 806 | 806 | 220 | 220 | 3069 | 3069 | 0 | 312 | 312 | 441 | 0 | 0 | 504 | 0 | 0 | 161 | 0 | 0 | 603 | 1 | 1 | 34 | 0 | 0 | 2918 | 2019-12-15 | 2021-04-10 | 2021-04-20 | 2021-12-05 | [8 empty] | 2019-08-01 | 2020-11-24 | 2020-12-01 | 2021-07-02 | 2023-10-01
88 | 03 | 5863 | SAC | 5 | I-5 West End Viaduct | In the city of Sacramento, at the West End Viaduct No. 24-0069L/R. Improve to standard truck capacity. (Long Lead Project) | 5700 | 5700 | 5700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1649 | 1649 | 5653 | 0 | 0 | 4988 | 0 | 0 | 314 | 0 | 0 | 17852 | 2 | 0 | 1860 | 0 | 0 | 125600 | 2020-04-02 | 2023-07-14 | 2023-09-01 | 2024-03-06 | [8 empty] | 2020-08-31 | 2023-09-10 | 2023-11-30 | 2024-03-24 | 2026-07-02
89 | 03 | 5868 | SAC | 5 | I-5 Permit Load Mobility Improvement | In the city of Sacramento, from 0.5 mile south of Route 50 to Route 80 at South Connector Undercrossing No. 24-0267 (PM 22.42) and at American River Viaduct No. 24-0068L/R (PM 24.82). Improve to standard truck capacity. ACCELERATED BRIDGE (PA&ED Only) | 16780 | 16780 | 16780 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 2500 | 14791 | 0 | 0 | 4364 | 0 | 0 | 719 | 0 | 0 | 19622 | 0 | 0 | 2221 | 0 | 0 | 51643 | 2019-12-01 | 2021-11-01 | 2021-11-15 | 2022-04-15 | [8 empty] | 2020-07-01 | 2022-05-09 | 2022-05-23 | 2022-10-21 | 2027-05-09
90 | 03 | 5869 | YOL | 5 | I-5 Vertical Clearance (Colusa & Yolo) | Near Woodland, at County Road 96 Overcrossing (OC) No. 22-0155 (PM R14.27), County Road 95 OC No. 22-0156 (PM R15.85), and Zamora OC No. 22-0157 (PM R17.62); also in Colusa County, in and near Williams at E Street OC No. 15-0067 (PM R17.98) and Lurline Avenue OC No. 15-0075 (PM R22.74). Establish standard vertical clearance. ACCELERATED BRIDGE (PA&ED Only) | 1700 | 1700 | 1700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 781 | 781 | 1685 | 0 | 0 | 1623 | 0 | 0 | 337 | 0 | 0 | 2572 | 0 | 0 | 5 | 0 | 0 | 19080 | 2019-02-01 | 2020-04-01 | 2020-04-15 | 2020-09-15 | [8 empty] | 2021-02-01 | 2022-07-23 | 2022-08-07 | 2022-12-14 | 2024-11-01
91 | 03 | 5960 | SAC | 12 | Rio Vista Bridge Operation Overhaul | In and near Rio Vista, at the Sacramento River Bridge No. 23-0024; also in Solano County from PM 26.3 to PM 26.4. Rehabilitate movable bridge electrical and mechanical systems and upgrade Americans with Disabilities Act (ADA) facilities. | 22860 | 760 | 760 | 2460 | 2460 | 20 | 20 | 3120 | 3120 | 100 | 100 | 16400 | 16400 | 0 | 257 | 257 | 912 | 0 | 0 | 2096 | 0 | 0 | 9 | 0 | 0 | 2006 | 0 | 0 | 98 | 0 | 0 | 11333 | 2019-07-01 | 2021-06-01 | 2021-07-01 | 2022-02-01 | [8 empty] | 2020-12-11 | 2022-03-10 | 2022-03-25 | 2022-07-22 | 2023-11-30
92 | 03 | 6247 | SAC | 50 | Sac 50 Paint | In the city of Sacramento, from the Sacramento River Viaduct (Pioneer Bridge) to 4th Street; also on Route 5 from 0.2 mile south of Broadway to S Street (PM 22.15 to 22.91). Clean and paint steel bridge girders within Route 5/50 Interchange. | 21255 | 575 | 575 | 940 | 940 | 10 | 10 | 3010 | 3010 | 20 | 20 | 16700 | 16700 | 0 | 275 | 275 | 275 | 0 | 0 | 835 | 0 | 0 | 7 | 0 | 0 | 2593 | 0 | 0 | 171 | 0 | 0 | 17248 | 2019-07-01 | 2021-02-01 | 2021-02-01 | 2021-09-01 |  |  | 2019-06-20 | [6 empty] | 2021-02-01 | 2021-02-01 | 2021-09-01 | 2023-12-01
93 | 03 | 6248 | SAC | 50 | Sac/ED Fiber Optics | In and near Rancho Cordova and Folsom, from Hazel Avenue to the county line; also in El Dorado County near El Dorado Hills, from the county line to 0.1 mile east of White Rock Road (PM 0.0/R1.9). Install fiber optic cable and wireless communication systems. | 7165 | 400 | 400 | 950 | 950 | 110 | 110 | 1050 | 1050 | 5 | 5 | 4650 | 4650 | 0 | 344 | 344 | 344 | 17 | 17 | 879 | 1 | 1 | 99 | 0 | 0 | 871 | 0 | 0 | 5 | 0 | 0 | 4770 | 2018-11-01 | 2020-06-15 | 2020-07-01 | 2020-11-01 |  |  | 2019-06-28 | [6 empty] | 2020-09-15 | 2020-10-12 | 2021-02-05 | 2022-03-01
94 | 03 | 6250 | SAC | 50 | US 50 ICM Infrastructure | In and near the cities of Sacramento, Rancho Cordova, and Folsom, from Yolo County line to Folsom Boulevard; also in Yolo County in West Sacramento, from Route 80 to Sacramento County line (PM 0.0 to 3.156), and on Route 80 from Enterprise Boulevard to Route 50 (PM 9.2 to R9.552). Install Transportation Management System (TMS) field elements. | 46660 | 940 | 940 | 2700 | 2700 | 520 | 520 | 3900 | 3900 | 200 | 200 | 38400 | 38400 | 0 | 615 | 615 | 967 | 0 | 0 | 2532 | 0 | 0 | 121 | 0 | 0 | 2887 | 0 | 0 | 125 | 0 | 0 | 32500 | 2019-03-01 | 2020-09-15 | 2020-10-01 | 2021-04-01 | [8 empty] | 2019-08-13 | 2020-09-16 | 2021-03-01 | 2021-04-05 | 2023-12-01
95 | 03 | 6402 | SAC | 51 | Bridge Deck Replacement | In the city of Sacramento at the American River Bridge No.24-0003 from north of B Street Underpass to north of Exposition Boulevard Overcrossing. Widen and replace bridge deck. (G13 Contingency Project) | 18940 | 4340 | 4340 | 12000 | 12000 | 600 | 600 | 0 | 0 | 2000 | 2000 | 0 | 0 | 0 | 2245 | 2245 | 4281 | 0 | 0 | 8633 | 0 | 0 | 575 | 0 | 0 | 16589 | 7 | 7 | 4286 | 0 | 0 | 211626 | 2019-11-01 | 2021-10-01 | 2021-11-01 | 2022-02-15 | [8 empty] | 2020-06-01 | 2021-10-01 | 2021-10-20 | 2022-03-01 | 2025-12-01
96 | 03 | 6411 | SAC | 5 | SAC Connector Ramp Meters | In the city of Sacramento, at various locations and routes at the Route 5/99 Interchange Connector ramps and the eastbound Route 51/160 Interchange Connector ramp. Install connector ramp meters. | 5272 | 552 | 552 | 660 | 660 | 20 | 20 | 1020 | 1020 | 20 | 20 | 3000 | 3000 | 0 | 307 | 307 | 573 | 0 | 0 | 702 | 0 | 0 | 19 | 0 | 0 | 837 | 0 | 0 | 19 | 0 | 0 | 2850 | 2019-08-01 | 2020-07-01 | 2020-08-01 | 2021-01-01 | [8 empty] | 2019-12-02 | 2021-03-10 | 2021-03-25 | 2021-07-21 | 2021-10-29
97 | 03 | 6707 | SAC | 99 | Seismic Retrofit | In the city of Sacramento, at Southbound Route 99/5 Connector Overcrossing No. 24-0241F; also, on Route 80 at Longview Ramp Overcrossing No. 24-0281K (PM M9.15). Seismic retrofit two structures. | 3739 | 330 | 330 | 800 | 800 | 18 | 18 | 691 | 691 | 0 | 0 | 1900 | 1900 | 0 | 242 | 242 | 242 | 775 | 775 | 956 | 9 | 9 | 12 | 0 | 0 | 687 | 0 | 0 | 0 | 0 | 0 | 1321 | 2018-04-01 | 2019-11-01 | 2019-12-15 | 2020-06-01 |  |  | 2018-03-30 | [6 empty] | 2019-08-02 | 2019-08-19 | 2020-01-14 | 2021-11-30
98 | 03 | 6711 | SAC | 80 | Rehabilitate Connection Ramp Pavement at var. locations | In and near the city of Sacramento, from 0.2 mile west of West El Camino Avenue to 0.2 mile east of Route 244. Pavement rehabilitation. | 14601 | 1190 | 1190 | 1220 | 1220 | 105 | 105 | 2000 | 2000 | 25 | 25 | 10061 | 10061 | 8424 | 1189 | 1189 | 1189 | 1130 | 1130 | 1130 | 24 | 24 | 104 | 147 | 147 | 1827 | 0 | 0 | 0 | 1 | 1 | 8425 | 2017-10-03 | 2018-12-11 | 2019-01-11 | 2019-07-15 |  |  | 2018-03-30 | 2018-09-06 | 2018-09-28 | 2019-03-04 | [6 empty] | 2020-07-23
99 | 03 | 6713 | SAC | 80 | SAC/PLACER 80 FIBER OPTICS | In and near the cities of Sacramento and Citrus Heights, from east of the Yolo County line to the Placer County line; also in Placer County, in the city of Roseville from the Sacramento County line to east of the Sacramento County line (PM 0.0/0.7). Install fiber optic communication line. | 16975 | 1200 | 1200 | 1425 | 1425 | 300 | 300 | 1800 | 1800 | 50 | 50 | 12200 | 12200 | 0 | 390 | 390 | 390 | 719 | 719 | 1410 | 10 | 10 | 236 | 0 | 0 | 1930 | 15 | 15 | 39 | 0 | 0 | 13253 | 2018-03-01 | 2019-11-01 | 2019-11-15 | 2020-05-15 |  |  | 2018-06-15 | [6 empty] | 2019-10-19 | 2019-10-24 | 2020-02-28 | 2020-11-15
100 | 03 | 6714 | SAC | 80 | SAC 80 R&R RHMA | Near the city of Sacramento, from 0.2 mile east of Longview Drive to 0.4 mile east of Madison Avenue. Pavement rehabilitation. | 18230 | 50 | 50 | 1500 | 1500 | 80 | 80 | 2500 | 2500 | 100 | 100 | 14000 | 14000 | 0 | 35 | 35 | 35 | 1040 | 1040 | 1592 | 2 | 2 | 75 | 0 | 0 | 2215 | 0 | 0 | 95 | 0 | 0 | 14385 | 2019-08-01 | 2021-09-20 | 2021-10-15 | 2022-04-01 |  |  | 2019-01-25 | [6 empty] | 2020-10-07 | 2020-10-22 | 2021-02-04 | 2022-04-15
101 | 03 | 6717 | SAC | 80 | Repair Loop Detectors | In various counties, on various routes. Repair or replace damaged inductive loop vehicle detection elements. | 1629 | 94 | 94 | 211 | 211 | 22 | 22 | 365 | 365 | 15 | 15 | 922 | 922 | 0 | 0 | 0 | 0 | 0 | 0 | 89 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 971 | 2018-04-01 | 2018-09-15 | 2018-10-01 | 2019-05-05 |  |  |  | 2018-12-07 |  |  |  |  | 2019-09-09 |  | 2019-12-04
102 | 03 | 6912 | SAC | 99 | Cosumnes Br Replc | In and near Elk Grove, from 0.3 mile south of Dillard Road Overcrossing to south of Grant Line Road (replace Consumnes River Bridge No. 24-0020L/R, and Consumnes River Overflow Bridge No. 24-0021L/R; upgrade bridge rails at Dillard Road Overcrossing No. 24-0163; construct new McConnell Overhead No. 24-0048L. Bridge seismic retrofit, bridge scour retrofit, bridge rail replacement, and bridge replacement. (G13 Contingency) | 27150 | 5150 | 5150 | 12000 | 12000 | 4000 | 4000 | 0 | 0 | 6000 | 6000 | 0 | 0 | 0 | 5068 | 5068 | 5068 | 5687 | 5687 | 12518 | 413 | 413 | 2683 | 0 | 0 | 11007 | 57 | 57 | 3966 | 0 | 0 | 161198 | 2019-07-01 | 2020-04-01 | 2020-05-01 | 2020-10-15 |  |  | 2019-05-20 | [6 empty] | 2020-04-16 | 2020-05-01 | 2020-10-30 | 2024-10-29
103 | 03 | 6916 | SAC | 99 | Lagoon Creek and American River Bridge | On Route 99, at South Lagoon Creek Bridge No. 24 -0028L, Lagoon Creek Bridge No. 24-0045L (PM 5.0), and North Lagoon Creek Bridge No. 24-0027L (PM 5.1); also on Route 160 (PM R44.5) at American River Bridge No. 24-0001L. Scour mitigation and bridge replacement. | 27995 | 1470 | 1470 | 2400 | 2400 | 255 | 255 | 3100 | 3100 | 500 | 500 | 20270 | 20270 | 0 | 1465 | 1465 | 1465 | 2365 | 2365 | 2475 | 157 | 157 | 239 | 0 | 0 | 3368 | 132 | 132 | 167 | 0 | 0 | 23983 | 2018-01-30 | 2019-03-15 | 2019-05-01 | 2019-07-17 |  | 2018-10-17 | 2018-01-30 | 2019-04-15 | 2019-06-24 | [6 empty] | 2020-02-10 | 2022-02-10
104 | 03 | 6923 | ED | 50 | Sawmill UC | Near Pollock Pines, at Sawmill Undercrossing No. 25-0041; also at Sly Park Road (PM R30.17/R31.3). Replace bridge, restore culverts, and add highway lighting. | 12551 | 818 | 818 | 959 | 959 | 211 | 211 | 1660 | 1660 | 53 | 53 | 8850 | 8850 | 0 | 433 | 433 | 433 | 886 | 886 | 946 | 205 | 205 | 219 | 0 | 0 | 1749 | 5 | 5 | 53 | 0 | 0 | 10971 | 2017-11-15 | 2019-08-15 | 2019-09-01 | 2019-12-15 |  |  | 2018-01-09 | [6 empty] | 2019-08-15 | 2019-08-16 | 2019-12-17 | 2021-08-01
105 | 03 | 6923B | SAC | 99 | 21st Ave UC | In the city of Sacramento, at 21st Avenue Undercrossing No. 24-0154. Replace bridge deck. | 6875 | 818 | 818 | 464 | 464 | 203 | 203 | 825 | 825 | 5 | 5 | 4560 | 4560 | 0 | 385 | 385 | 385 | 375 | 375 | 464 | 132 | 132 | 315 | 0 | 0 | 1017 | 0 | 0 | 0 | 0 | 0 | 6087 | 2018-02-01 | 2019-07-01 | 2019-07-01 | 2020-01-15 |  |  | 2017-06-29 | [6 empty] | 2020-03-10 | 2020-03-25 | 2020-07-22 | 2022-11-30
106 | 03 | 6924 | SAC | 99 | RHMA Overlay-ADA ramps/sw | In Galt, from the San Joaquin County line to Simmerhorn Road; also in the cities of Elk Grove and Sacramento, from 1.0 mile south of Elk Grove Boulevard to Martin Luther King Jr. Boulevard (PM 11.8/21.6). Pavement rehabilitation. | 51411 | 1000 | 1000 | 2290 | 2290 | 190 | 190 | 3600 | 3600 | 22 | 22 | 44309 | 44309 | 0 | 858 | 858 | 858 | 2247 | 2247 | 2300 | 69 | 69 | 108 | 0 | 0 | 3514 | 10 | 10 | 10 | 0 | 0 | 44309 | 2017-05-15 | 2019-01-10 | 2019-01-25 | 2019-05-07 |  | 2018-10-17 | 2017-05-15 | 2019-02-08 | 2019-03-21 | [6 empty] | 2019-09-18 | 2021-11-30
107 | 03 | 6925 | SAC | 99 | Sac 99 Fiber Optics | In and near the cities of Elk Grove and Sacramento, from Grant Line Road to Route 50; also on Route 51, from Route 50 to 0.1 mile south of the Fort Sutter Viaduct (PM 0.0 to 0.1). Install fiber optic cable. | 12150 | 700 | 700 | 1000 | 1000 | 50 | 50 | 1300 | 1300 | 100 | 100 | 9000 | 9000 | 0 | 392 | 392 | 392 | 0 | 0 | 960 | 0 | 0 | 40 | 0 | 0 | 1286 | 0 | 0 | 22 | 0 | 0 | 9431 | 2020-10-01 | 2021-09-01 | 2021-10-01 | 2022-05-01 |  |  | 2019-06-28 | [6 empty] | 2021-07-16 | 2021-08-02 | 2022-01-10 | 2022-11-30
108 | 03 | 8140 | YUB | 20 | Feather River Scour | In Marysville, at the Feather River Bridge No. 18-009. Scour mitigation and retrofit piers. | 37618 | 2290 | 2290 | 2700 | 2700 | 200 | 200 | 4100 | 4100 | 1887 | 1887 | 26441 | 26441 | 0 | 2205 | 2205 | 2205 | 471 | 471 | 1642 | 19 | 19 | 165 | 0 | 0 | 3066 | 57 | 57 | 855 | 0 | 0 | 26105 | 2019-02-01 | 2021-03-01 | 2021-04-01 | 2021-07-01 |  |  | 2019-01-25 | [6 empty] | 2020-08-15 | 2020-09-01 | 2020-12-20 | 2023-11-01
109 | 03 | 8378 | SUT | 99 | Live Oak Rehab | In Live Oak, from 0.1 mile north of Coleman Avenue to 0.2 mile north of Ramsdell Drive. Roadway rehabilitation. | 20288 | 20 | 20 | 618 | 618 | 50 | 50 | 1500 | 1500 | 0 | 0 | 18100 | 18100 | 0 | 12 | 12 | 12 | 456 | 456 | 591 | 14 | 14 | 66 | 0 | 0 | 1340 | 0 | 0 | 0 | 0 | 0 | 16380 | 2017-08-01 | 2019-09-01 | 2019-09-01 | 2020-02-28 |  | 2018-10-17 | 2017-08-01 | [6 empty] | 2019-08-30 | 2019-08-30 | 2020-03-02 | 2021-10-01
110 | 03 | 8563 | YOL | 5 | I-5 Vertical Clearance (Yolo) | Near Woodland, at Wye Line Road Overcrossing (OC) No. 22-0158 (PM 4.49), County Road 6 OC No. 22-0138 (PM R25.57), County Line Road OC No. 22-0139 (R28.92). Establish standard vertical clearance. ACCELERATED BRIDGE (PA&ED Only) | 744 | 744 | 744 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 709 | 709 | 709 | 0 | 0 | 1005 | 0 | 0 | 100 | 0 | 0 | 1327 | 1 | 0 | 5 | 0 | 0 | 13117 | 2019-10-01 | 2021-03-01 | 2021-04-01 | 2021-10-01 |  |  | 2019-06-27 | [6 empty] | 2020-07-23 | 2020-08-07 | 2020-12-14 | 2022-11-01
111 | 03 | 8571 | YOL | 5 | AVC REPAIR & INSTALL | In various counties, on various routes at various locations. Repair and install permanent Automatic Vehicle Classification (AVC) truck data collection stations. | 17158 | 1000 | 1000 | 1300 | 1300 | 190 | 190 | 2200 | 2200 | 80 | 80 | 12388 | 12388 | 0 | 704 | 704 | 704 | 1256 | 1256 | 1287 | 86 | 86 | 120 | 0 | 0 | 2233 | 1 | 1 | 1 | 0 | 0 | 11107 | 2018-01-01 | 2018-09-01 | 2018-10-01 | 2019-03-01 |  |  | 2018-04-02 | 2019-02-13 | 2019-02-27 | [6 empty] | 2019-08-14 | 2020-10-01
112 | 03 | 8784 | YOL | 80 | 4F650 Yolo Pavement Rehab | In and near West Sacramento, from east of Mace Boulevard to Sacramento River Bridge; also on Route 50, from Route 80 to Jefferson Boulevard Overcrossing (PM 0.0/2.5). Rehabilitate pavement by placing Continuous Reinforced Concrete and asphalt pavement, rehabilitate bridge decks, median widening at three locations, and upgrade bridge railings. (Long Lead Project) | 10337 | 10337 | 10337 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1603 | 1603 | 8688 | 0 | 0 | 10550 | 0 | 0 | 508 | 0 | 0 | 16445 | 1 | 0 | 940 | 0 | 0 | 187484 | 2022-01-01 | 2023-12-01 | 2024-02-01 | 2024-11-01 | [8 empty] | 2022-01-01 | 2023-12-01 | 2024-02-01 | 2024-11-01 | 2027-10-01
113 | 03 | 8901 | YOL | 80 | Sac River BOH (Bryte Bend) 0F250 [03*75] | In West Sacramento, at the Sacramento River Bridge and Overhead No. 22-0026L/R. Rehabilitate bridge. | 40407 | 1900 | 1900 | 1550 | 1550 | 75 | 75 | 3640 | 3640 | 482 | 482 | 32760 | 32760 | 0 | 1789 | 1789 | 1789 | 641 | 641 | 1456 | 3 | 3 | 64 | 0 | 0 | 3381 | 6 | 6 | 40 | 0 | 0 | 29204 | 2018-09-28 | 2020-03-25 | 2020-04-09 | 2020-07-23 |  | 2018-12-06 | 2018-09-28 | [6 empty] | 2020-03-25 | 2020-04-13 | 2020-07-23 | 2022-11-01
114 | 03 | 8920 | SAC | 5 | Repair Field Elements | In Placer, Sacramento, and Yolo Counties, on routes 5, 80, 99, and 113. Replace obsolete Microwave Vehicle Detection System (MVDS) elements. | 2355 | 148 | 148 | 260 | 260 | 22 | 22 | 507 | 507 | 15 | 15 | 1403 | 1403 | 0 | 0 | 0 | 0 | 0 | 0 | 189 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1460 | 2018-04-01 | 2018-09-15 | 2018-10-01 | 2019-05-05 |  |  |  | 2018-12-07 |  |  |  |  | 2019-09-09 |  | 2019-12-04
115 | 03 | 9579 | YUB | 20 | Browns Valley Rehab | Near Marysville, from Marysville Road to Yuba River (Parks Bar) Bridge. Rehabilitate roadway. | 64450 | 4300 | 4300 | 2800 | 2800 | 2950 | 2950 | 6900 | 6900 | 9400 | 9400 | 38100 | 38100 | 0 | 3677 | 3677 | 3677 | 2623 | 2623 | 2927 | 2223 | 2223 | 2737 | 0 | 0 | 6242 | 2270 | 2270 | 8145 | 0 | 0 | 45373 | 2017-08-01 | 2019-04-01 | 2019-04-15 | 2019-12-29 |  | 2018-10-17 | 2017-08-01 | 2019-06-17 | 2019-06-20 | [6 empty] | 2020-01-15 | 2024-12-01
116 | 03 | 9587 | YUB | 20 | Loma Rica Rd./Spring Valley Road Widening & Rehab | Near Marysville, from 0.1 mile east of Loma Rica Road to 0.2 mile west of Spring Valley Road. Rehabilitate roadway. | 16835 | 1160 | 1160 | 2180 | 2180 | 1245 | 1245 | 1800 | 1800 | 1400 | 1400 | 9050 | 9050 | 9049 | 1098 | 1098 | 1098 | 2119 | 2119 | 2119 | 1147 | 1147 | 1236 | 454 | 454 | 1728 | 1016 | 1016 | 1266 | 2076 | 2076 | 9050 | 2016-06-13 | 2018-03-01 | 2018-03-15 | 2019-01-02 |  |  | 2016-06-13 | 2018-05-29 | 2018-06-14 | 2018-12-10 | [6 empty] | 2021-11-15
117 | 03 | 9812 | YUB | 70 | Simmerly Slough (SHOPP) | Near Marysville, from 0.1 mile north of Binney Junction Underpass to 0.3 mile north of Laurellen Road, at Simmerly Slough Bridge No. 16-0019. Replace bridge. | 93065 | 1960 | 1960 | 3555 | 3555 | 950 | 950 | 5800 | 5800 | 3800 | 3800 | 77000 | 77000 | 0 | 1927 | 1927 | 1927 | 3367 | 3367 | 3397 | 760 | 760 | 889 | 0 | 0 | 4671 | 2222 | 2222 | 2693 | 0 | 0 | 70077 | 2017-06-21 | 2018-11-16 | 2018-12-06 | 2019-04-07 |  | 2018-10-17 | 2017-06-21 | 2019-02-01 | 2019-03-25 | [6 empty] | 2019-08-26 | 2023-12-01
118 | 03 | 9820 | YUB | 70 | Marysville Railroad Bridge Rehab (SHOPP) | In and near Marysville, from south of 14th Street to north of Cemetery Road. Roadway rehabilitation. | 111000 | 3000 | 3000 | 3500 | 3500 | 2500 | 2500 | 12000 | 12000 | 5000 | 5000 | 85000 | 85000 | 0 | 2596 | 2596 | 3286 | 0 | 0 | 5907 | 0 | 0 | 2419 | 0 | 0 | 9647 | 5 | 5 | 3514 | 0 | 0 | 83350 | 2019-01-02 | 2020-09-18 | 2020-10-02 | 2021-03-26 | [8 empty] | 2020-11-02 | 2022-03-01 | 2022-03-15 | 2022-07-25 | 2026-12-15
119 | 04 | 0050N | ALA | 880 | Lake Merritt Railroad Bridge Replacement | In Oakland, near Lake Merrit Channel Bridge No. 33-0027 and 5th Avenue. Replace Hanlon Lead Railroad bridge. Mitigation for EA 1706U. | 15986 | 500 | 500 | 2629 | 2629 | 657 | 657 | 1700 | 1700 | 7500 | 7500 | 3000 | 3000 | 0 | 1029 | 1029 | 1029 | 2086 | 2086 | 2632 | 510 | 510 | 742 | 0 | 0 | 1955 | 333 | 333 | 7742 | 0 | 0 | 3112 | 2015-05-11 | 2019-06-03 | 2019-06-10 | 2019-12-04 |  |  | 2015-05-11 | [6 empty] | 2020-10-12 | 2020-11-18 | 2021-05-12 | 2023-10-01
120 | 04 | 0084B | ALA | 84 | NILES CANYON ALAMEDA CREEK BRIDGE REPLACEMENT PROJECT | In Fremont, at Alameda Creek Bridge No. 33-36. Replace bridge. | 44175 | 7800 | 7800 | 6500 | 6500 | 600 | 600 | 5000 | 5000 | 275 | 275 | 24000 | 24000 | 0 | 7448 | 7448 | 7448 | 3484 | 3484 | 5755 | 278 | 278 | 829 | 0 | 0 | 6384 | 73 | 73 | 244 | 0 | 0 | 24586 | 2017-09-25 | 2019-05-20 | 2019-06-03 | 2019-12-08 |  | 2018-10-17 | 2017-09-25 | [6 empty] | 2020-03-04 | 2020-04-01 | 2020-12-01 | 2023-12-01
121 | 04 | 0269H | CC | 242 | CC 242 Pavement Rehab | In Concord, from Route 680 to 0.1 mile north of Concord Avenue. Pavement rehabilitation in northbound direction. | 15898 | 1229 | 1229 | 1340 | 1340 | 110 | 110 | 1430 | 1430 | 15 | 15 | 11774 | 11774 | 0 | 1286 | 1286 | 1286 | 12 | 12 | 1340 | 0 | 0 | 22 | 0 | 0 | 1703 | 0 | 0 | 10 | 0 | 0 | 11774 | 2018-06-29 | 2020-03-04 | 2020-06-30 | 2020-12-18 |  |  | 2019-05-15 | [6 empty] | 2020-06-01 | 2020-06-15 | 2021-01-15 | 2021-12-31
122 | 04 | 0269M | SON | 12 | SON 12 Bridge Scour Mitigation | In and near Sonoma, at Sonoma Creek Bridge No. 20-0027 and Hooker Creek Bridge No. 20-0030. Scour mitigation. | 25289 | 1519 | 1519 | 2650 | 2650 | 500 | 500 | 3000 | 3000 | 4420 | 4420 | 13200 | 13200 | 0 | 1511 | 1511 | 1511 | 706 | 706 | 2874 | 17 | 17 | 392 | 0 | 0 | 2889 | 2 | 2 | 4420 | 0 | 0 | 12543 | 2018-06-01 | 2019-12-16 | 2020-02-07 | 2020-12-01 |  |  | 2018-09-12 | [6 empty] | 2020-06-30 | 2020-06-30 | 2020-12-21 | 2020-12-31
123 | 04 | 0334J | MRN | 101 | Ramp Metering | In and near Sausalito, Corte Madera, and Larkspur, from north of Golden Gate Bridge to 0.3 mile north of Sir Francis Drake Boulevard. Install ramp metering and Traffic Operations System (TOS) elements. | 10462 | 0 | 0 | 1697 | 1500 | 50 | 50 | 1900 | 1900 | 110 | 110 | 6902 | 6902 | 6901 | 0 | 0 | 0 | 1396 | 1234 | 1396 | 6 | 6 | 92 | 435 | 435 | 1935 | 13 | 13 | 9 | 2322 | 2322 | 6902 | 2014-05-07 | 2018-05-01 | 2018-06-01 | 2019-01-16 |  |  | 2014-05-07 | 2018-06-22 | 2018-06-29 | 2019-01-09 | [6 empty] | 2020-06-30
124 | 04 | 0386F | SCL | 9 | SCL 9 Saratoga Bridge Project | Near Saratoga, at Saratoga Creek Bridge No. 37-0074. Replace bridge. | 29093 | 3720 | 3720 | 4200 | 4200 | 1200 | 1200 | 1526 | 1526 | 6779 | 6779 | 11668 | 11668 | 0 | 3449 | 3449 | 3580 | 0 | 0 | 4357 | 0 | 0 | 770 | 0 | 0 | 2241 | 0 | 0 | 22367 | 0 | 0 | 11668 | 2018-06-15 | 2020-04-15 | 2020-05-06 | 2020-10-19 | [8 empty] | 2019-10-15 | 2021-10-01 | 2021-10-15 | 2022-04-14 | 2022-10-19
125 | 04 | 0449A | SCL | 280 | SCL-SM-280 CAPM | In and near Los Altos, Los Altos Hills, and Palo Alto, from Foothill Boulevard to north of Sand Hill Road (also in San Mateo County (PM R0.0/R2.1). Pavement rehabilitation. | 59470 | 1853 | 1853 | 3284 | 3284 | 48 | 48 | 6661 | 6661 | 50 | 50 | 47574 | 47574 | 0 | 1488 | 1488 | 1488 | 2565 | 2565 | 3258 | 22 | 22 | 25 | 0 | 0 | 6414 | 0 | 0 | 0 | 0 | 0 | 48088 | 2017-12-01 | 2019-04-15 | 2019-05-01 | 2019-11-01 |  | 2018-10-17 | 2017-12-01 | 2019-06-06 | 2019-06-25 | [6 empty] | 2020-02-13 | 2021-11-01
126 | 04 | 0480A | ALA | 880 | PATTERSON SLOUGH CREEK BRIDGE DECK REPLACEMENT | In Fremont, from 0.5 mile south to 0.5 mile north of Patterson Slough Bridge No. 33-0250 (PM 11.8). Bridge rehabilitation. | 19515 | 2200 | 2200 | 1980 | 1980 | 704 | 704 | 2420 | 2420 | 427 | 427 | 11784 | 11784 | 0 | 1594 | 1594 | 1594 | 0 | 0 | 2194 | 2 | 2 | 790 | 0 | 0 | 2634 | 0 | 0 | 434 | 0 | 0 | 12246 | 2019-05-22 | 2020-05-13 | 2020-06-01 | 2021-02-10 |  |  | 2019-03-07 | [6 empty] | 2020-06-29 | 2020-06-30 | 2021-02-10 | 2022-02-10
127 | 04 | 0480C | MRN | 1 | Millerton Gulch Br Scour Mitigation | Near Point Reyes Station, at Millerton Gulch Bridge No. 27-0114. Environmental mitigation for emergency project EA 4K500. | 4696 | 1620 | 1620 | 1080 | 1080 | 180 | 180 | 830 | 830 | 150 | 150 | 836 | 836 | 0 | 1134 | 1134 | 1134 | 241 | 241 | 241 | 31 | 31 | 127 | 0 | 0 | 860 | 0 | 0 | 150 | 0 | 0 | 1000 | 2017-12-01 | 2019-06-07 | 2019-06-21 | 2020-02-04 |  |  | 2017-12-26 | 2018-10-22 | 2018-12-05 | 2019-07-05 | [6 empty] | 2023-07-31
128 | 04 | 0480D | SOL | 84 | Real McCoy Ramp | Near Rio Vista, at the Cache Slough Ferry Crossing. Upgrade the existing fender systems, concrete ramps, and swing gate systems, modify the ferry boat deck surface, and install traffic counter and Vehicle Detection Systems (VDS). | 19480 | 2080 | 2080 | 2080 | 2080 | 260 | 260 | 2080 | 2080 | 350 | 350 | 12630 | 12630 | 0 | 11 | 11 | 1945 | 0 | 0 | 2061 | 0 | 0 | 250 | 0 | 0 | 2100 | 0 | 0 | 350 | 0 | 0 | 12630 | 2020-10-01 | 2022-05-01 | 2022-06-01 | 2022-12-01 | [8 empty] | 2021-04-01 | 2022-05-01 | 2022-06-01 | 2022-12-19 | 2023-11-20
129 | 04 | 0480J | ALA | 580 | GREENVILLE OH REHAB | Near Livermore, near Greenville Road at Greenville Overhead Bridge No. 33-0121R. Rehabilitate westbound structure. | 5792 | 600 | 600 | 900 | 900 | 120 | 120 | 800 | 800 | 334 | 334 | 3038 | 3038 | 0 | 574 | 574 | 574 | 664 | 664 | 1173 | 15 | 15 | 108 | 0 | 0 | 1157 | 2 | 2 | 334 | 0 | 0 | 3038 | 2018-01-15 | 2019-09-02 | 2019-10-01 | 2020-02-03 |  |  | 2017-12-29 | [6 empty] | 2020-04-01 | 2020-04-30 | 2020-11-02 | 2022-05-02
130 | 04 | 0480N | SOL | 80 | Br Rehab+Scour | In and near Dixon and Vacaville, at McCune Creek Bridge No. 23-0084L/R; also on Route 505 at Horse Creek Bridge No. 23-0077L. Bridge preventative maintenance. | 8754 | 990 | 990 | 880 | 880 | 79 | 79 | 1773 | 1773 | 715 | 715 | 4317 | 4317 | 0 | 928 | 928 | 928 | 40 | 40 | 833 | 17 | 17 | 276 | 0 | 0 | 739 | 2 | 2 | 715 | 0 | 0 | 3686 | 2018-08-31 | 2020-02-28 | 2020-05-31 | 2020-11-02 |  |  | 2019-03-22 | [6 empty] | 2020-09-21 | 2020-09-25 | 2021-04-14 | 2023-07-31
131 | 04 | 0480P | SOL | 12 | Sol 12 3R | In and near Rio Vista, from Currie Road to Sacramento County line. Roadway rehabilitation. (G13 Contingency) | 17433 | 5780 | 5780 | 5780 | 5780 | 2890 | 2890 | 0 | 0 | 2983 | 2983 | 0 | 0 | 0 | 1998 | 1998 | 4164 | 0 | 0 | 6351 | 0 | 0 | 1440 | 0 | 0 | 11553 | 0 | 0 | 3018 | 0 | 0 | 73200 | 2019-10-01 | 2022-02-01 | 2022-02-01 | 2022-08-01 | [8 empty] | 2019-10-01 | 2022-01-01 | 2022-02-01 | 2022-08-01 | 2024-09-30
132 | 04 | 0481H | SCL | 101 | SCL 101 Br. Rail Replacement/Upgrade | In various cities, on Routes 101 and 237 at various locations. Bridge rail upgrade of five structures at four locations. | 20120 | 1800 | 1800 | 2250 | 2250 | 30 | 30 | 2700 | 2700 | 70 | 70 | 13270 | 13270 | 0 | 1672 | 1672 | 1672 | 250 | 250 | 2464 | 2 | 2 | 38 | 0 | 0 | 3043 | 0 | 0 | 70 | 0 | 0 | 13270 | 2018-09-14 | 2020-03-16 | 2020-06-15 | 2020-12-21 |  |  | 2018-10-05 | [6 empty] | 2020-05-01 | 2020-05-15 | 2020-12-21 | 2022-12-14
133 | 04 | 0481M | ALA | 84 | Scour at Arroyo De La Laguna | Near Sunol, at Arroyo De La Laguna Bridge No. 33-0043. Replace/rehabilitate bridge for scour mitigation, bridge rail upgrade, and seismic retrofit. | 22813 | 1863 | 1863 | 3600 | 3600 | 250 | 250 | 3600 | 3600 | 500 | 500 | 13000 | 13000 | 0 | 977 | 977 | 2373 | 0 | 0 | 3011 | 0 | 0 | 130 | 0 | 0 | 3526 | 0 | 0 | 5 | 0 | 0 | 13000 | 2020-03-01 | 2022-03-01 | 2022-04-01 | 2022-12-07 | [8 empty] | 2020-10-01 | 2022-03-01 | 2022-04-01 | 2022-11-30 | 2024-11-30
134 | 04 | 0481P | ALA | 680 | REHABILITATE PAVEMENT | In and near Pleasanton and Dublin, from north of Route 84 to Alcosta Boulevard. Roadway rehabilitation. (G13 Contingency) | 15875 | 7150 | 7150 | 7150 | 7150 | 1500 | 1500 | 0 | 0 | 75 | 75 | 0 | 0 | 0 | 2594 | 2594 | 2594 | 7 | 7 | 6444 | 0 | 0 | 1200 | 0 | 0 | 16896 | 2 | 2 | 75 | 0 | 0 | 109853 | 2019-03-01 | 2020-06-01 | 2020-06-01 | 2021-03-30 |  |  | 2019-05-01 | [6 empty] | 2020-05-15 | 2020-06-01 | 2021-03-30 | 2023-10-02
135 | 04 | 0481R | SOL | 80 | sol 80 raise oc | In Vallejo, from Magazine Street Overcrossing No. 23-0066 to Redwood Street Overcrossing No. 23-0114. Increase vertical clearance at six overcrossing structures. ACCELERATED BRIDGE | 22228 | 2100 | 2100 | 2154 | 2154 | 154 | 154 | 1859 | 1859 | 10 | 10 | 15951 | 15951 | 0 | 2056 | 2056 | 2056 | 2240 | 2240 | 2590 | 0 | 0 | 38 | 0 | 0 | 1728 | 10 | 10 | 250 | 0 | 0 | 15951 | 2018-07-23 | 2019-06-01 | 2019-06-14 | 2020-01-15 |  | 2018-10-17 | 2018-07-23 | 2019-06-24 | 2019-06-28 | [6 empty] | 2020-01-30 | 2022-01-15
136 | 04 | 0487R | SOL | 80 | Suisun Crk Br Scour Mitigation | Near Fairfield, at Suisun Creek Bridge No. 23-0007. Scour mitigation. | 8173 | 1550 | 1550 | 714 | 714 | 39 | 39 | 1725 | 1725 | 320 | 320 | 3825 | 3825 | 0 | 1296 | 1296 | 1296 | 0 | 0 | 60 | 13 | 13 | 106 | 0 | 0 | 721 | 0 | 0 | 200 | 0 | 0 | 2119 | 2018-09-03 | 2020-04-01 | 2020-04-01 | 2020-10-01 |  |  | 2019-03-11 | [6 empty] | 2020-05-15 | 2020-05-29 | 2020-10-30 | 2023-11-30
137 | 04 | 0488K | SON | 12 | CAPM 12 | In and near Sonoma, from Vallejo Avenue to east of Leveroni Road/Napa Road. Pavement rehabilitation. | 10104 | 1308 | 1308 | 1030 | 1030 | 62 | 62 | 856 | 856 | 5 | 5 | 6843 | 6843 | 0 | 897 | 897 | 897 | 485 | 485 | 1652 | 2 | 2 | 27 | 0 | 0 | 1372 | 0 | 0 | 10 | 0 | 0 | 5665 | 2018-04-01 | 2020-01-02 | 2020-02-01 | 2020-07-30 |  |  | 2018-04-03 | [6 empty] | 2020-01-02 | 2020-02-01 | 2020-07-30 | 2021-06-30
138 | 04 | 0587D | SF | 101 | Alemany Circle UC Deck Replacement | Near San Francisco, at Alemany Circle Undercrossing No. 34-0033. Rehabilitate bridge. | 43230 | 4000 | 4000 | 3540 | 3540 | 20 | 20 | 3250 | 3250 | 20 | 20 | 32400 | 32400 | 0 | 3889 | 3889 | 3889 | 3077 | 3077 | 4257 | 12 | 12 | 25 | 0 | 0 | 3266 | 0 | 0 | 4 | 0 | 0 | 42659 | 2018-01-12 | 2019-05-15 | 2019-06-03 | 2019-12-02 |  | 2018-10-17 | 2018-01-12 | 2019-06-27 | 2019-06-27 | [6 empty] | 2019-12-02 | 2021-06-30
139 | 04 | 0587K | NAP | 128 | SR 128 Conn Creek Bridge Replacement Plant Establishment | Near Rutherford, at Conn Creek Bridge No. 21-0021. Plant establishment mitigation for bridge replacement project EA 1G430. | 500 | 0 | 0 | 30 | 30 | 20 | 20 | 200 | 200 | 30 | 30 | 220 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220 | [6 empty] | 2015-10-05 | [6 empty] | 2022-08-01 | 2022-08-01 | 2022-10-31 | 2027-01-19
140 | 04 | 0587M | NAP | 29 | Env. Mitigation and Establishment | In Calistoga, at Napa River Bridge No. 21-0018. Environmental mitigation and plant establishment for bridge replacement project. | 1775 | 0 | 0 | 640 | 640 | 400 | 400 | 150 | 150 | 85 | 85 | 500 | 500 | 0 | 0 | 0 | 0 | 336 | 336 | 418 | 19 | 19 | 127 | 0 | 0 | 695 | 0 | 0 | 0 | 0 | 0 | 314 | 2015-02-09 | 2019-06-14 | 2019-06-28 | 2019-12-27 |  |  | 2015-02-09 | 2019-05-10 | 2019-05-29 | [6 empty] | 2020-03-02 | 2024-03-29
141 | 04 | 0622B | SM | 1 | SM-1 CAPM | Near Pescadero, from Santa Cruz County line to south of Bean Hollow Road. Pavement rehabilitation. | 15592 | 1703 | 1703 | 1081 | 1081 | 46 | 46 | 1081 | 1081 | 10 | 10 | 11671 | 11671 | 0 | 1069 | 1069 | 1069 | 133 | 133 | 1285 | 0 | 0 | 41 | 0 | 0 | 1238 | 0 | 0 | 5 | 0 | 0 | 11671 | 2018-07-02 | 2019-06-01 | 2019-09-01 | 2020-01-15 |  |  | 2018-11-28 | [6 empty] | 2020-01-06 | 2020-01-15 | 2020-06-15 | 2021-07-15
142 | 04 | 0732J | SM | 280 | SM 280 Culvert Rehab | Near Redwood City, San Carlos and Belmont, from Edgewood Road to Route 92 and near Hillsborough at PM R12.7; also in Santa Clara County in and near Mountain View and Palo Alto, at various spot locations (PM 11.6, 12.8, 12.9, 18.8). Replace failing culverts and restore damaged slopes, pavement, and bridge approaches at six locations. | 23477 | 1800 | 1800 | 2000 | 2000 | 260 | 260 | 3000 | 3000 | 13 | 13 | 16404 | 16404 | 0 | 342 | 342 | 2321 | 0 | 0 | 2397 | 0 | 0 | 268 | 0 | 0 | 3294 | 0 | 0 | 13 | 0 | 0 | 16404 | 2020-02-01 | 2021-10-01 | 2021-11-01 | 2022-05-01 | [8 empty] | 2020-02-01 | 2021-10-01 | 2021-11-01 | 2022-05-01 | 2024-05-01
143 | 04 | 0756K | MRN | 1 | Lagunitas Creek Bridge | Near Point Reyes Station, at Lagunitas Creek Bridge No. 27-0023. Replace bridge. | 29699 | 5547 | 5547 | 2850 | 2850 | 750 | 750 | 2500 | 2500 | 6500 | 6500 | 11552 | 11552 | 0 | 4132 | 4132 | 4132 | 1425 | 1425 | 3938 | 93 | 93 | 797 | 0 | 0 | 2659 | 3 | 3 | 4059 | 0 | 0 | 11552 | 2018-06-29 | 2020-08-20 | 2020-08-25 | 2021-02-08 |  | 2018-10-17 | 2018-06-29 | [6 empty] | 2020-08-20 | 2020-08-25 | 2021-02-08 | 2022-12-30
144 | 04 | 0830C | NAP | 128 | Nickname Required | Near Napa, at Capell Creek Bridge No. 21-0078. Environmental mitigation and plant establishment for rehabilitate bridge project EA 4G840. | 1536 | 0 | 0 | 0 | 0 | 10 | 10 | 250 | 250 | 776 | 776 | 500 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 2016-06-16 | [6 empty] | 2021-07-15 | 2021-08-15 | 2022-03-15 | 2026-07-15
145 | 04 | 0886 | SOL | 84 | Miner Slough | Near Rio Vista, at Miner Slough Bridge No. 23-0035. Replace bridge. | 39632 | 3550 | 3550 | 4100 | 4100 | 1098 | 1098 | 3500 | 3500 | 2884 | 2884 | 24500 | 24500 | 0 | 3366 | 3366 | 3366 | 961 | 961 | 2945 | 85 | 85 | 670 | 0 | 0 | 4026 | 9 | 9 | 3009 | 0 | 0 | 24500 | 2017-09-29 | 2020-04-30 | 2020-05-30 | 2020-12-20 |  | 2018-10-17 | 2017-09-29 | [6 empty] | 2020-06-18 | 2020-06-25 | 2022-04-28 | 2024-11-07
146 | 04 | 1450C | ALA | 880 | Bridge Railings Replacement | In Hayward, San Leandro, and Oakland, at Tennyson Road Overcrossing (OC) No. 33-0236 (PM 15.65), Washington Avenue OC No. 33-0166 (PM 20.82), and Damon Slough Southboud onramp No. 33-0142K (PM 26.53); also on Route 77 in Oakland, at San Leandro OC No. 33-0284 (PM 0.29). Upgrade bridge rails, replace joint seals. | 15193 | 918 | 918 | 1500 | 1500 | 250 | 250 | 2200 | 2200 | 25 | 25 | 10300 | 10300 | 0 | 247 | 247 | 1183 | 0 | 0 | 1990 | 0 | 0 | 256 | 0 | 0 | 2484 | 0 | 0 | 450 | 0 | 0 | 10300 | 2020-03-16 | 2021-12-17 | 2022-01-21 | 2022-09-26 | [8 empty] | 2020-03-16 | 2021-12-17 | 2022-01-21 | 2022-09-26 | 2023-12-08
147 | 04 | 1450E | SF | 101 | SF-101 & SM-1 Baluster Rails | In the City and County of San Francisco, at Alemany Circle Undercrossing (UC) No. 34-0064K, Alemany Circle UC No. 34-0063S and Bayshore Boulevard UC No. 34-0047S; also in San Mateo County in Pacifica, at Paloma Avenue Overcrossing No. 35-0187 (PM R44.21). Upgrade bridge rails. | 9848 | 657 | 657 | 1751 | 1751 | 164 | 164 | 1805 | 1805 | 10 | 10 | 5461 | 5461 | 0 | 116 | 116 | 805 | 0 | 0 | 1795 | 0 | 0 | 171 | 0 | 0 | 2065 | 0 | 0 | 0 | 0 | 0 | 5461 | 2019-10-01 | 2021-01-01 | 2021-03-01 | 2021-10-01 | [8 empty] | 2020-05-01 | 2021-01-01 | 2021-03-01 | 2021-10-01 | 2022-10-01
148 | 04 | 1451A | SON | 101 | Replace Bridge Rails | In and near Santa Rosa, at Todd Road Overcrossing (OC) No. 20-0172 (PM 16.54) and Baker Avenue OC No. 20-0173 (PM 19.00); also in Marin County near Navato, at Miller Creek Road OC No. 27-0082 (PM 15.57). Upgrade bridge rails. | 7007 | 650 | 650 | 780 | 780 | 130 | 130 | 988 | 988 | 116 | 116 | 4343 | 4343 | 0 | 292 | 292 | 1223 | 0 | 0 | 1457 | 0 | 0 | 115 | 0 | 0 | 1041 | 0 | 0 | 120 | 0 | 0 | 4343 | 2019-10-01 | 2021-08-01 | 2021-09-01 | 2021-03-01 | [8 empty] | 2019-10-01 | 2021-08-02 | 2021-09-01 | 2022-03-01 | 2023-03-01
149 | 04 | 1451C | NAP | 128 | Hopper Slough Br. | Near Rutherford, at Hopper Slough Bridge No. 20-0019. Replace bridge. | 15660 | 2074 | 2074 | 1988 | 1988 | 206 | 206 | 2014 | 2014 | 1514 | 1514 | 7864 | 7864 | 0 | 523 | 523 | 2091 | 0 | 0 | 2413 | 0 | 0 | 163 | 0 | 0 | 2661 | 0 | 0 | 1514 | 0 | 0 | 7864 | 2020-10-01 | 2022-04-04 | 2022-05-02 | 2022-12-01 | [8 empty] | 2021-04-02 | 2022-04-01 | 2022-05-01 | 2023-01-10 | 2024-12-01
150 | 04 | 1452A | SM | 1 | SM-1 TOS | In and near the cities of Half Moon Bay, Pacifica and Daly City, from south of Miramontes Point Road to Clarinada Avenue Undercrossing, at various locations. Install Bluetooth Detection Systems and Variable Message Signs (VMS), enable two existing Changeable Message Signs (CMS), modify Advanced Transportation Management System (ATMS), and construct Maintenance Vehicle Pullouts (MVPs) to improve the system performance. | 3865 | 503 | 503 | 444 | 444 | 30 | 30 | 444 | 444 | 36 | 36 | 2408 | 2408 | 0 | 132 | 132 | 659 | 0 | 0 | 988 | 0 | 0 | 35 | 0 | 0 | 609 | 0 | 0 | 36 | 0 | 0 | 2408 | 2020-04-01 | 2021-08-01 | 2021-09-01 | 2022-01-15 | [8 empty] | 2020-09-01 | 2021-08-01 | 2021-09-01 | 2022-01-15 | 2023-01-15
151 | 04 | 1452D | SCL | 152 | SCL-152 CAPM | In Gilroy, from 0.3 miles west of Santa Teresa Boulevard to Route 101. Rehabilitate pavement. | 20938 | 1400 | 1400 | 1900 | 1900 | 68 | 68 | 2100 | 2100 | 125 | 125 | 15345 | 15345 | 15345 | 607 | 607 | 607 | 1412 | 1412 | 1412 | 64 | 64 | 68 | 22 | 22 | 1894 | 55 | 55 | 64 | 0 | 0 | 15345 | 2018-04-05 | 2018-12-03 | 2018-12-14 | 2019-06-14 |  | 2018-10-17 | 2018-04-05 | 2018-12-27 | 2018-12-31 | 2019-06-20 | [6 empty] | 2020-12-01
152 | 04 | 1452F | SOL | 80 | Sol-80/29 Separation | In Vallejo, at Route 80/29 Separation Bridge No. 23-0087. Replace bridge. ACCELERATED BRIDGE | 19618 | 2057 | 2057 | 2624 | 2624 | 22 | 22 | 2600 | 2600 | 15 | 15 | 12300 | 12300 | 0 | 2034 | 2034 | 2180 | 1150 | 1150 | 3351 | 23 | 23 | 38 | 0 | 0 | 2568 | 0 | 0 | 15 | 0 | 0 | 15800 | 2018-12-03 | 2020-05-04 | 2020-06-08 | 2021-01-15 |  |  | 2018-06-21 | 2019-06-18 | 2019-06-25 | [6 empty] | 2020-02-06 | 2021-01-30
153 | 04 | 1452H | ALA | 80 | University--Increase Vertical Clearance | In Berkeley, at University Avenue Overcrossing No. 33-0023. Establish standard vertical clearance. ACCELERATED BRIDGE (PA&ED Only) | 3380 | 3380 | 3380 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3424 | 3424 | 3424 | 0 | 0 | 12008 | 0 | 0 | 1039 | 0 | 0 | 11143 | 16 | 0 | 332 | 0 | 0 | 27678 | 2019-05-03 | 2020-05-01 | 2020-06-01 | 2020-12-01 |  |  | 2019-05-22 | [6 empty] | 2020-12-02 | 2021-02-03 | 2021-09-08 | 2024-05-01
154 | 04 | 1452J | ALA | 61 | ALA-61 CAPM | In the city of Alameda, from Broadway/Encinal Avenue to Sherman Street. Pavement rehabilitation, upgrade Americans with Disabilities Act (ADA) curb ramps, and improve crosswalks. | 8821 | 1220 | 1220 | 1200 | 1200 | 22 | 22 | 1500 | 1500 | 5 | 5 | 4874 | 4874 | 0 | 597 | 597 | 1390 | 0 | 0 | 1398 | 0 | 0 | 48 | 0 | 0 | 1805 | 0 | 0 | 440 | 0 | 0 | 4874 | 2020-02-01 | 2021-03-01 | 2021-05-01 | 2021-11-01 | [8 empty] | 2020-02-01 | 2021-03-01 | 2021-05-01 | 2021-11-01 | 2023-05-01
155 | 04 | 1453J | SON | 1 | Son 1 Culverts Rehab | Near Jenner, from south of Fort Ross Road to north of Moon Rock Campground at various locations. Rehabilitate drainage culverts. | 8504 | 744 | 744 | 1369 | 1369 | 429 | 429 | 1385 | 1385 | 321 | 321 | 4256 | 4256 | 0 | 586 | 586 | 1024 | 0 | 0 | 1091 | 0 | 0 | 393 | 0 | 0 | 1164 | 0 | 0 | 502 | 0 | 0 | 4256 | 2020-10-15 | 2022-06-15 | 2022-06-01 | 2023-01-01 | [8 empty] | 2019-12-29 | 2022-05-15 | 2022-06-01 | 2023-01-01 | 2024-05-15
156 | 04 | 1453K | NAP | 29 | SHEEHY CRK CULVERT REHAB | In American Canyon, at Rio Del Mar; also near American Canyon at 0.3 mile south of North Kelly Road (PM 5.1). Rehabilitate culverts. | 6558 | 1086 | 1086 | 786 | 786 | 350 | 350 | 706 | 706 | 294 | 294 | 3336 | 3336 | 0 | 699 | 699 | 1404 | 0 | 0 | 790 | 0 | 0 | 340 | 0 | 0 | 845 | 0 | 0 | 529 | 0 | 0 | 3336 | 2020-11-02 | 2022-05-02 | 2022-06-30 | 2023-01-11 | [8 empty] | 2019-11-04 | 2021-07-01 | 2021-08-02 | 2022-01-11 | 2022-09-01
157 | 04 | 1454C | ALA | 84 | CAPM ALA-84-6.9/10.8 | In Fremont, from Route 880 (PM 6.922) to Route 238. Rehabilitate pavement and upgrade curb ramps to make Americans with Disabilities Act (ADA) compliant. | 20327 | 2080 | 2080 | 2340 | 2340 | 780 | 780 | 2080 | 2080 | 173 | 173 | 12874 | 12874 | 0 | 57 | 57 | 1968 | 0 | 0 | 2050 | 0 | 0 | 757 | 0 | 0 | 1990 | 0 | 0 | 173 | 0 | 0 | 12874 | 2020-04-01 | 2021-12-01 | 2022-02-01 | 2022-09-01 | [8 empty] | 2020-11-02 | 2022-05-03 | 2022-06-01 | 2023-01-13 | 2023-12-29
158 | 04 | 1454G | ALA | 880 | CAPM ALA-880-0.0/12.0 | In Fremont, from Santa Clara County line to north of Fremont Boulevard Overcrossing. Cold plane pavement, overlay with Rubberized Hot Mix Asphalt (RHMA-G) and Open Graded Friction Course (OGFC), upgrade Americans with Disabilities Act (ADA) curb ramps, upgrade metal beam guardrail, and replace loop detectors. | 71236 | 3000 | 3000 | 5000 | 5000 | 620 | 620 | 5400 | 5400 | 50 | 50 | 57166 | 57166 | 0 | 691 | 691 | 1436 | 0 | 0 | 5170 | 0 | 0 | 510 | 0 | 0 | 5575 | 0 | 0 | 0 | 0 | 0 | 57166 | 2020-03-02 | 2021-09-01 | 2021-11-01 | 2022-06-04 | [8 empty] | 2020-03-02 | 2021-11-01 | 2022-03-01 | 2022-09-22 | 2024-12-31
159 | 04 | 1460R | ALA | 80 | MacArthur Maze/Increase Vertical Clearance | In Oakland, at the Routes 80/580/680 MacArthur Maze Bridge No. 33-0061R, 33-0061L, 33-0061L and 33-0611. Establish standard vertical clearance. ACCELERATED BRIDGE (PA&ED Only) | 6600 | 6600 | 6600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3299 | 3299 | 4923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300 | 0 | 0 | 105489 | 2019-11-18 | 2020-05-02 | 2020-06-01 | 2021-02-01 | [8 empty] | 2020-09-15
160 | 04 | 1462K | NAP | 29 | Bridge Rail Replacement | In St. Helena, at Sulphur Creek Bridge No. 21-0016 and York Creek Bridge No. 21-0017. Upgrade bridge rails. (Long Lead Project) | 1040 | 1040 | 1040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 215 | 215 | 1073 | 0 | 0 | 1484 | 0 | 0 | 421 | 0 | 0 | 1147 | 0 | 0 | 747 | 0 | 0 | 1000 | 2021-03-01 | 2023-01-03 | 2023-04-03 | 2023-10-02 | [8 empty] | 2021-03-01 | 2023-04-01 | 2023-04-03 | 2023-10-01 | 2025-12-01
161 | 04 | 1462M | SON | 1 | Son 1 Culverts Rehab | Near Gualala, from north of Moon Rock Campground to 0.1 mile north of Vantage Road. Rehabilitate drainage culverts. | 9090 | 1050 | 1050 | 1571 | 1571 | 286 | 286 | 1040 | 1040 | 382 | 382 | 4761 | 4761 | 0 | 693 | 693 | 1541 | 0 | 0 | 703 | 0 | 0 | 194 | 0 | 0 | 289 | 0 | 0 | 132 | 0 | 0 | 4761 | 2020-10-15 | 2022-06-15 | 2022-06-15 | 2023-01-16 | [8 empty] | 2020-10-15 | 2022-06-15 | 2022-06-15 | 2023-01-16 | 2024-05-28
162 | 04 | 1462R | CC | 4 | CC-4 CAPM | In and near Concord and Pittsburg, from Route 242 to Loveridge Road. Rehabilitate pavement, upgrade curb ramps to make Americans with Disabilities Act (ADA) compliant and upgrade guardrail to make standard. | 73594 | 2720 | 2720 | 6400 | 6400 | 780 | 780 | 8320 | 8320 | 93 | 93 | 55281 | 55281 | 0 | 312 | 312 | 2979 | 0 | 0 | 6865 | 0 | 0 | 244 | 0 | 0 | 5239 | 0 | 0 | 93 | 0 | 0 | 55281 | 2020-06-01 | 2022-03-01 | 2022-06-01 | 2022-12-01 | [8 empty] | 2020-06-01 | 2022-05-02 | 2022-06-01 | 2022-12-01 | 2024-12-02
163 | 04 | 1463D | ALA | 680 | Ala-680 Ramp Metering (Phase 2B) | In and near Fremont, Pleasanton, and Dublin, from 0.3 mile south of Scott Creek Road to 0.3 mile north of Alcosta Boulevard. Install ramp meters, ramp High Occupancy Vehicle (HOV) bypass lanes, and Traffic Operations Systems (TOS). | 24233 | 0 | 0 | 5800 | 5600 | 100 | 100 | 4500 | 4500 | 800 | 800 | 13233 | 13233 | 13233 | 0 | 0 | 0 | 2537 | 2448 | 2537 | 13 | 13 | 22 | 783 | 783 | 5168 | 0 | 0 | 677 | 4180 | 4180 | 13233 | 2016-11-16 | 2018-06-25 | 2018-06-29 | 2019-01-28 |  | 2018-08-15 | 2016-11-16 | 2018-06-25 | 2018-06-29 | 2018-12-27 | [6 empty] | 2020-12-01
164 | 04 | 1464L | ALA | 980 | TMC Hardware Replacement | In Oakland, at the District 4 Transportation Management Center (TMC). Upgrade or replace legacy TMC hardware components and related software by service contract to improve reliability and functionality. | 3354 | 110 | 110 | 392 | 392 | 10 | 10 | 262 | 262 | 10 | 10 | 2570 | 2570 | 0 | 96 | 96 | 96 | 153 | 153 | 456 | 0 | 0 | 10 | 0 | 0 | 278 | 0 | 0 | 0 | 0 | 0 | 2570 | 2018-10-01 | 2019-09-01 | 2019-12-01 | 2020-11-01 |  |  | 2018-10-01 | [6 empty] | 2019-11-01 | 2019-12-01 | 2020-11-01 | 2022-08-29
165 | 04 | 1480A | MRN | 1 | MRN 1 CAPM | Near Point Reyes Station and Olema, from Olema Creek Bridge to north of Cypress Road; also near Tomales, from south of Tomales-Petaluma Road to south of Valley Ford Road (PM 45.0/50.5). Pavement rehabilitation, improve drainage, and upgrade Americans with Disabilities Act (ADA) facilities. | 32528 | 2300 | 2300 | 2500 | 2500 | 66 | 66 | 2300 | 2300 | 817 | 817 | 24545 | 24545 | 0 | 1248 | 1248 | 2803 | 0 | 0 | 2715 | 3 | 3 | 381 | 0 | 0 | 2451 | 0 | 0 | 817 | 0 | 0 | 24545 | 2018-10-01 | 2019-12-02 | 2020-01-09 | 2020-07-09 | [8 empty] | 2020-08-14 | 2022-04-15 | 2022-04-29 | 2022-10-31 | 2023-10-24
166 | 04 | 1480B | SCL | 17 | SCL 17 CAPM | In and near Los Gatos, Campbell and San Jose, from Hebard Way to Route 280. Pavement rehabilitation. | 64481 | 2400 | 2400 | 2750 | 2750 | 175 | 175 | 5900 | 5900 | 56 | 56 | 53200 | 53200 | 0 | 2361 | 2361 | 2361 | 607 | 607 | 2769 | 60 | 60 | 192 | 0 | 0 | 2453 | 4 | 4 | 53 | 0 | 0 | 49344 | 2018-07-02 | 2020-01-17 | 2020-01-27 | 2020-07-15 |  |  | 2018-10-10 | [6 empty] | 2020-05-29 | 2020-06-15 | 2020-12-22 | 2022-09-19
167 | 04 | 1482F | SON | 101 | BIG PAVE SEGMENT 2 | In and near Windsor, Healdsburg, and Cloverdale, from Old Redwood Highway to 2.0 miles south of Mendocino County line. Roadway rehabilitation. | 88958 | 5149 | 5149 | 6799 | 6799 | 320 | 320 | 7600 | 7600 | 890 | 890 | 68200 | 68200 | 0 | 3796 | 3796 | 3796 | 3161 | 3161 | 7185 | 240 | 240 | 258 | 0 | 0 | 7952 | 119 | 119 | 890 | 0 | 0 | 68200 | 2018-04-19 | 2019-06-03 | 2019-06-03 | 2019-12-01 |  | 2018-10-17 | 2018-04-19 | 2019-06-21 | 2019-06-28 | [6 empty] | 2019-12-01 | 2021-12-30
168 | 04 | 1482Q | CC | 580 | CC-580 Stege Drain super-structure | In Richmond, at Stege Drain Bridge No. 28-0091. Bridge rehabilitation. | 15301 | 970 | 970 | 1042 | 1042 | 117 | 117 | 2367 | 2367 | 5 | 5 | 10800 | 10800 | 0 | 947 | 947 | 947 | 312 | 312 | 1339 | 2 | 2 | 117 | 0 | 0 | 2126 | 0 | 0 | 5 | 0 | 0 | 10800 | 2018-11-30 | 2019-08-01 | 2020-04-20 | 2020-10-12 |  |  | 2019-03-22 | [6 empty] | 2020-05-01 | 2020-05-08 | 2020-11-13 | 2022-10-28
169 | 04 | 1482R | SCL | Var | SCL, VAR, Sub-Structure Rehab. | In various cities, on various routes at Carnadero Creek Bridge No. 37-0156, San Francisquito Creek Bridge No. 37-0018, San Tomas Aquino Creek Bridge No. 37-0524L, and Bodfish Creek Bridge No. 37-0046. Bridge preventative maintenance. | 5739 | 900 | 900 | 750 | 750 | 44 | 44 | 790 | 790 | 10 | 10 | 3245 | 3245 | 0 | 884 | 884 | 884 | 102 | 102 | 918 | 1 | 1 | 44 | 0 | 0 | 762 | 0 | 0 | 10 | 0 | 0 | 3245 | 2018-10-01 | 2020-05-01 | 2020-06-01 | 2020-12-22 |  |  | 2019-03-01 | [6 empty] | 2020-05-01 | 2020-05-15 | 2020-12-22 | 2021-10-01
170 | 04 | 1483C | SM | 101 | SM 101 Cordilleras Crk Br Replacement | In Redwood City, at Cordilleras Creek Bridge No. 35-0019. Replace bridge to restore structural integrity. | 48480 | 4500 | 4500 | 4500 | 4500 | 1125 | 1125 | 7500 | 7500 | 4285 | 4285 | 26570 | 26570 | 0 | 118 | 118 | 3120 | 0 | 0 | 4065 | 0 | 0 | 1052 | 0 | 0 | 6669 | 0 | 0 | 4285 | 0 | 0 | 26570 | 2020-10-02 | 2022-06-30 | 2022-06-30 | 2023-01-11 | [8 empty] | 2020-12-15 | 2022-03-01 | 2022-03-15 | 2022-09-01 | 2024-09-01
171 | 04 | 1483D | ALA | 880 | East Crk Slough Scour Mitigation | In Oakland, at East Creek Slough Bridge No. 33-0143. Mitigate eroded channel side-slope tidal scour and replace bridge approach slabs. | 5587 | 1000 | 1000 | 850 | 850 | 160 | 160 | 1170 | 1170 | 100 | 100 | 2307 | 2307 | 0 | 864 | 864 | 1012 | 0 | 0 | 968 | 0 | 0 | 163 | 0 | 0 | 1310 | 0 | 0 | 186 | 0 | 0 | 2307 | 2020-06-15 | 2021-12-15 | 2022-01-15 | 2022-08-15 | [8 empty] | 2019-10-01 | 2021-04-01 | 2021-05-01 | 2021-12-01 | 2022-12-01
172 | 04 | 1483E | NAP | 029 | SR 29 3 bridges, scour measures | NEAR CALISTOGA, AT GARNETT CREEK BRIDGE NO. 21-0005 (PM 39.08), GARNETT CREEK BRANCH BRIDGE NO. 21-0111 (PM 38.96), AND NO NAME CREEK BRIDGE NO. 21-0100 (PM 42.83).. SUBSTRUCTURE REHAB/SCOUR MITIGATION & MAINTENANCE. SUBSTRUCTURE REHAB/SCOUR MITIGATION & MAINTENANCE. | 12101 | 0 | 0 | 2153 | 2153 | 566 | 566 | 1950 | 1950 | 2166 | 2166 | 5266 | 5266 | 0 | 2884 | 2884 | 5768 | 73 | 73 | 1908 | 5 | 5 | 632 | 0 | 0 | 2053 | 2 | 2 | 2166 | 0 | 0 | 3944 | [6 empty] | 2019-02-01 | [6 empty] | 2020-11-01 | 2020-12-15 | 2021-06-15 | 2021-12-01
173 | 04 | 1483H | ALA | 80 | TMS Replace & Upgrade at Maze | In Emeryville and Oakland, from San Francisco-Oakland Bay Bridge Toll Plaza to north of Powell Street; also in Oakland, on Routes 580 and 880, at various locations. Upgrade/replace Transportation Management System (TMS) elements. | 8061 | 760 | 760 | 850 | 850 | 260 | 260 | 1044 | 1044 | 12 | 12 | 5135 | 5135 | 0 | 543 | 543 | 543 | 388 | 388 | 1193 | 5 | 5 | 154 | 0 | 0 | 1225 | 0 | 0 | 10 | 0 | 0 | 5135 | 2019-03-01 | 2020-04-01 | 2020-05-01 | 2020-12-24 |  |  | 2018-10-24 | [6 empty] | 2020-03-03 | 2020-03-31 | 2020-12-24 | 2021-12-24
174 | 04 | 1483K | SCL | 280 | SCL, 280, Seismic Restoration, Arasteradero RD, UC and Bird Ave. OC | In San Jose, at Bird Avenue Overcrossing Bridge No. 37-0267 (PM R2.78); also in Los Altos Hills at Arastradero Road Undercrossing Bridge No. 37-0251 L/R (PM 17.8). Bridge seismic restoration. | 4956 | 1144 | 1144 | 1034 | 1034 | 66 | 66 | 600 | 600 | 90 | 90 | 2022 | 2022 | 0 | 598 | 598 | 598 | 816 | 816 | 922 | 4 | 4 | 31 | 0 | 0 | 668 | 0 | 0 | 0 | 0 | 0 | 2391 | 2018-02-27 | 2019-03-01 | 2019-03-15 | 2019-10-28 |  |  | 2018-02-27 | 2019-02-12 | 2019-03-13 | [6 empty] | 2019-10-28 | 2020-07-10
175 | 04 | 1483M | SM | 1 | Sub-Rehab+Scour | In Half Moon Bay, at the Pilarcitos Creek Bridge No. 35-0139L/R; also on Route 84 at San Gregorio Creek Bridge No. 35-0166 (PM 7.55). Retrofit scour critical bridges to preserve the structural integrity of the bridges by reinforcing with Rock Slope Protection (RSP). | 6129 | 1250 | 1250 | 1040 | 1040 | 260 | 260 | 1300 | 1300 | 343 | 343 | 1936 | 1936 | 0 | 239 | 239 | 1173 | 0 | 0 | 1095 | 0 | 0 | 275 | 0 | 0 | 1427 | 0 | 0 | 342 | 0 | 0 | 1609 | 2020-10-01 | 2022-02-01 | 2022-04-01 | 2022-11-01 | [8 empty] | 2020-10-01 | 2022-03-31 | 2022-04-01 | 2022-11-01 | 2024-11-01
176 | 04 | 1483S | SF | 80 | Bayshore Viaduct Structure Painting | In the City and County of San Francisco, on Route 80, at the Bayshore Viaduct No. 34-0088 from Route 101 to 4th Street. Paint superstructure steel members. | 69973 | 2500 | 2500 | 9200 | 9200 | 300 | 300 | 7500 | 7500 | 76 | 76 | 50397 | 50397 | 0 | 1944 | 1944 | 1944 | 915 | 915 | 915 | 16 | 16 | 16 | 0 | 0 | 6481 | 0 | 0 | 0 | 0 | 0 | 50397 | 2018-12-01 | 2020-03-01 | 2020-04-01 | 2020-12-15 |  | 2018-12-06 | 2018-12-21 | [6 empty] | 2020-06-26 | 2020-06-26 | 2021-01-15 | 2025-06-01
177 | 04 | 1483T | SF | 101 | Central Viaduct Structure Painting | In the City and County of San Francisco, at the Central Viaduct No. 34-0077 from south of 17th Street to S. Van Ness Avenue. Paint superstructure steel members. (G13 Contingency) | 153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 153 | 153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6481 | 0 | 0 | 0 | 0 | 0 | 50396 | [15 empty] | 2021-01-15 | 2025-06-01
178 | 04 | 1485K | SM | 101 | Bridge Rail Replacement | In East Palo Alto, Redwood City, Belmont, Burlingame, Millbrae, South San Francisco, and Brisbane, from University Avenue Overcrossing to Sierra Point offramp separation. Upgrade bridge rails at eight structures. | 12310 | 1326 | 1326 | 1586 | 1586 | 130 | 130 | 1456 | 1456 | 64 | 64 | 7748 | 7748 | 0 | 105 | 105 | 1238 | 0 | 0 | 1845 | 0 | 0 | 139 | 0 | 0 | 1482 | 0 | 0 | 64 | 0 | 0 | 7748 | 2020-03-01 | 2021-02-01 | 2022-03-01 | 2022-09-01 | [8 empty] | 2020-08-01 | 2021-05-01 | 2021-10-01 | 2022-04-01 | 2023-04-01
179 | 04 | 1487A | ALA | 580 | TMS on ALA-580 | In and near Oakland and San Leandro, from Route 238 to Route 80. Install and upgrade Transportation Management System (TMS) elements. | 26570 | 2700 | 2700 | 2700 | 2700 | 50 | 50 | 3600 | 3600 | 20 | 20 | 17500 | 17500 | 0 | 1005 | 1005 | 1005 | 151 | 151 | 727 | 15 | 15 | 27 | 0 | 0 | 346 | 0 | 0 | 20 | 0 | 0 | 17970 | 2018-06-19 | 2020-04-16 | 2020-06-15 | 2020-12-31 |  | 2018-10-17 | 2018-06-19 | [6 empty] | 2020-04-16 | 2020-06-15 | 2020-12-31 | 2021-11-15
180 | 04 | 1487D | SON | 101 | San Antonio Crk | Near Petaluma, at San Antonio Creek Bridges No. 20-0019L/R. Abutment scour mitigation and channel sediment cleaning to address flooding. | 3047 | 982 | 982 | 416 | 416 | 24 | 24 | 468 | 468 | 160 | 160 | 997 | 997 | 0 | 217 | 217 | 1133 | 0 | 0 | 728 | 0 | 0 | 7 | 0 | 0 | 459 | 0 | 0 | 161 | 0 | 0 | 996 | 2020-10-01 | 2021-12-01 | 2021-12-01 | 2022-06-01 | [8 empty] | 2020-10-01 | 2021-12-01 | 2021-12-01 | 2022-06-01 | 2023-02-01
181 | 04 | 1487E | CC | 80 | Roadway Rehab 2R | In and near Hercules, Rodeo, and Crocket, from Route 4 to the Carquinez Bridge. Roadway rehabilitation. (G13 Contingency) | 7941 | 3083 | 3083 | 4624 | 4624 | 206 | 206 | 0 | 0 | 28 | 28 | 0 | 0 | 0 | 1305 | 1305 | 3155 | 0 | 0 | 5098 | 0 | 0 | 268 | 0 | 0 | 7916 | 0 | 0 | 28 | 0 | 0 | 61317 | 2020-04-01 | 2021-12-01 | 2022-02-01 | 2022-11-15 | [8 empty] | 2020-04-15 | 2021-12-01 | 2022-02-01 | 2022-11-15 | 2024-12-31
182 | 04 | 1487J | SM | 101 | Blank | In the cities of Burlingame, Millbrae, San Bruno and South San Francisco, from Broadway to Oyster Point Boulevard. Pavement rehabilitation at onramps and offramps within project limits and 1. 2 miles of mainline, and upgrade curb ramps. | 14172 | 1056 | 1056 | 1342 | 1342 | 132 | 132 | 1085 | 1085 | 100 | 100 | 10457 | 10457 | 0 | 813 | 813 | 0 | 168 | 168 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2018-12-28 | 2019-10-15 | 2019-11-01 | 2020-05-15 |  | 2019-01-31
183 | 04 | 1487J | SM | 101 | Blank | In the cities of Burlingame, Millbrae, San Bruno and South San Francisco, from Broadway to Oyster Point Boulevard. Pavement rehabilitation at onramps and offramps within project limits and 1.2 miles of mainline, and upgrade curb ramps. | 14172 | 1056 | 1056 | 1342 | 1342 | 132 | 132 | 1085 | 1085 | 100 | 100 | 10457 | 10457 | 0 | 813 | 813 | 1056 | 329 | 329 | 1428 | 5 | 5 | 10 | 0 | 0 | 1654 | 0 | 0 | 20 | 0 | 0 | 25047 | [5 empty] | 2018-01-31 | 2018-12-28 | [6 empty] | 2020-05-01 | 2020-05-20 | 2021-03-01 | 2022-08-01
184 | 04 | 1487S | SM | 101 | Blank | In the cities of Burlingame, Millbrae, San Bruno and South San Francisco, from Broadway to 0.1 mile north of South Airport Boulevard. Pavement rehabilitation. | 28543 | 0 | 0 | 0 | 0 | 0 | 0 | 543 | 543 | 0 | 0 | 28000 | 28000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
185 | 04 | 1489K | NAP | 121 | Capell Br. Replacement | Near Napa, at Capell Creek Bridge No. 21-0064. Bridge rehabilitation. | 5120 | 750 | 750 | 870 | 870 | 100 | 100 | 735 | 735 | 225 | 225 | 2440 | 2440 | 0 | 729 | 729 | 729 | 303 | 303 | 1051 | 42 | 42 | 103 | 0 | 0 | 749 | 0 | 0 | 225 | 0 | 0 | 2440 | 2018-09-01 | 2020-03-01 | 2020-04-15 | 2020-10-30 |  |  | 2018-09-20 | [6 empty] | 2020-03-02 | 2020-04-15 | 2020-10-30 | 2021-12-01
186 | 04 | 1490D | NAP | 29 | SR 29 York to 128 Split CAPM | In and near St. Helena and Calistoga, from York Creek Bridge to Route 128. Pavement rehabilitation. | 12811 | 900 | 900 | 1100 | 1100 | 44 | 44 | 1100 | 1100 | 20 | 20 | 9647 | 9647 | 0 | 747 | 747 | 1167 | 0 | 0 | 1116 | 0 | 0 | 100 | 0 | 0 | 1092 | 0 | 0 | 20 | 0 | 0 | 9647 | 2019-10-01 | 2020-10-01 | 2020-11-02 | 2021-06-30 | [8 empty] | 2020-07-10 | 2020-11-02 | 2021-05-07 | 2022-04-01 | 2022-11-01
187 | 04 | 1490Q | SCL | 82 | CAPM and ADA ramps | In the cities of San Jose and Santa Clara, from McKendrie Street to north of Chapman Court. Pavement rehabilitation, Americans with Disabilities Act (ADA) upgrades, and installation of High-intensity Activated crossWalK (HAWK) systems. | 6242 | 470 | 470 | 833 | 833 | 180 | 180 | 979 | 979 | 180 | 180 | 3600 | 3600 | 0 | 58 | 58 | 58 | 825 | 825 | 985 | 39 | 39 | 49 | 0 | 0 | 984 | 11 | 11 | 90 | 0 | 0 | 3711 | 2017-07-14 | 2019-01-15 | 2019-03-01 | 2019-09-11 |  |  | 2017-08-04 | 2019-03-27 | 2019-03-29 | [6 empty] | 2019-12-27 | 2021-06-01
188 | 04 | 1492C | SCL | 87 | PSSR - SCL-87 Pavement 2R | In San Jose, from Route 85 to West Julian Street. Roadway rehabilitation. | 69390 | 2767 | 2767 | 4425 | 4425 | 50 | 50 | 6581 | 6581 | 304 | 304 | 55263 | 55263 | 0 | 871 | 871 | 3109 | 0 | 0 | 4698 | 0 | 0 | 52 | 0 | 0 | 6600 | 0 | 0 | 304 | 0 | 0 | 55263 | 2020-10-01 | 2022-04-01 | 2022-06-30 | 2023-02-01 | [8 empty] | 2020-10-01 | 2022-04-01 | 2022-04-30 | 2023-02-01 | 2025-03-03
189 | 04 | 1493A | CC | 24 | Seismic Restoration | In Orinda, at St. Stephens Drive Overcrossing No. 28-0111. Seismic retrofit. | 4755 | 925 | 925 | 1175 | 1175 | 175 | 175 | 375 | 375 | 38 | 38 | 2067 | 2067 | 0 | 545 | 545 | 703 | 0 | 0 | 1155 | 0 | 0 | 179 | 0 | 0 | 380 | 0 | 0 | 37 | 0 | 0 | 2067 | 2020-04-13 | 2022-01-04 | 2022-02-21 | 2022-12-22 | [8 empty] | 2020-04-13 | 2022-01-04 | 2022-02-21 | 2022-12-12 | 2024-12-12
190 | 04 | 1493K | MRN | 101 | Irwn Cr Br Rehab Culvert | In San Rafael, at Irwin Creek Bridge No. 27-0097. Rehabilitate corrugated metal arch culvert bridge and adjoining deteriorated culvert structures. | 5652 | 1100 | 1100 | 880 | 880 | 215 | 215 | 610 | 610 | 944 | 944 | 1903 | 1903 | 0 | 510 | 510 | 1478 | 0 | 0 | 1167 | 0 | 0 | 510 | 0 | 0 | 1070 | 0 | 0 | 126 | 0 | 0 | 1923 | 2020-08-01 | 2022-05-01 | 2022-06-01 | 2022-09-15 | [8 empty] | 2019-12-02 | 2021-09-01 | 2021-10-01 | 2022-03-16 | 2023-08-01
191 | 04 | 1493M | SON | 12 | SON 12 CAPM | In and near Santa Rosa, from Llano Road to Farmers Lane. Rehabilitate pavement, upgrade guardrail to make standard and upgrade curb ramps to make Americans with Disabilities Act (ADA) compliant. | 36361 | 2084 | 2084 | 2900 | 2900 | 66 | 66 | 3350 | 3350 | 280 | 280 | 27681 | 27681 | 0 | 539 | 539 | 2049 | 0 | 0 | 1247 | 0 | 0 | 30 | 0 | 0 | 1236 | 0 | 0 | 265 | 0 | 0 | 27681 | 2020-04-01 | 2021-11-01 | 2021-12-01 | 2022-05-02 | [8 empty] | 2020-05-01 | 2021-11-01 | 2021-12-01 | 2022-06-15 | 2024-03-20
192 | 04 | 1494C | ALA | 185 | ALA 185 CAPM | In and near Hayward and San Leandro, from A Street to Davis Street. Rehabilitate pavement and upgrade curb ramps to Americans with Disabilities Act (ADA) Standards. | 21258 | 1417 | 1417 | 2093 | 2093 | 375 | 375 | 2405 | 2405 | 40 | 40 | 14928 | 14928 | 0 | 200 | 200 | 1416 | 0 | 0 | 2504 | 0 | 0 | 255 | 0 | 0 | 2334 | 0 | 0 | 40 | 0 | 0 | 14928 | 2019-12-01 | 2021-07-01 | 2021-08-02 | 2022-02-23 | [8 empty] | 2020-03-02 | 2021-07-01 | 2021-10-08 | 2022-05-04 | 2024-05-03
193 | 04 | 1494E | NAP | 29 | Bridge Rail Replacement | In and near the cities of Napa and Yountville, at Craig Creek Bridge No. 21-0048 (PM 14.11), Dry Creek Bridge No. 21-0014 (PM 16.48), Perfume Creek Bridge No. 21-0051 (PM 17.81), and California Drive Undercrossing No. 21-0047 (PM 19.04). Upgrade bridge rails and widen shoulders to make standard. | 13056 | 2600 | 2600 | 1200 | 1200 | 350 | 350 | 1500 | 1500 | 295 | 295 | 7111 | 7111 | 0 | 1000 | 1000 | 2820 | 0 | 0 | 1199 | 0 | 0 | 286 | 0 | 0 | 1449 | 0 | 0 | 1361 | 0 | 0 | 7111 | 2020-06-30 | 2022-01-31 | 2022-04-15 | 2022-12-15 | [8 empty] | 2020-10-01 | 2022-04-01 | 2022-06-01 | 2022-12-29 | 2024-12-30
194 | 04 | 1494G | SM | 1 | SM-1 Pescadero Crk. Br. rails | Near Pescadero, at Pescadero Creek Bridge No. 35-0028. Upgrade bridge rails and repair approach slabs. | 8102 | 1200 | 1200 | 1000 | 1000 | 8 | 8 | 1200 | 1200 | 260 | 260 | 4434 | 4434 | 0 | 132 | 132 | 1334 | 0 | 0 | 1640 | 0 | 0 | 8 | 0 | 0 | 1318 | 0 | 0 | 260 | 0 | 0 | 4434 | 2020-11-01 | 2022-04-01 | 2022-05-01 | 2022-12-15 | [8 empty] | 2020-11-01 | 2022-04-01 | 2022-05-01 | 2022-12-15 | 2023-12-15
195 | 04 | 1494K | ALA | 580 | Bridge Rehab | In Oakland, at Foothill Boulevard Undercrossing No. 33-0334K. Bridge deck rehabilitation. | 991 | 0 | 0 | 398 | 398 | 21 | 21 | 212 | 212 | 0 | 0 | 360 | 360 | 0 | 0 | 0 | 0 | 252 | 252 | 315 | 0 | 0 | 22 | 0 | 0 | 213 | 0 | 0 | 0 | 0 | 0 | 419 | 2017-05-27 | 2019-12-31 | 2020-01-31 | 2020-08-31 |  |  | 2017-05-27 | 2019-04-23 | 2019-05-08 | [6 empty] | 2019-12-16 | 2020-12-16
196 | 04 | 1497A | SM | 84 | CAPM SR-84 | In and near Woodside and Redwood City, from Route 280 to Route 101. Rehabilitate pavement, make curb ramps and sidewalks Americans with Disabilities Act (ADA) compliant, and upgrade guardrails to make standard. | 27150 | 2340 | 2340 | 2860 | 2860 | 39 | 39 | 3120 | 3120 | 566 | 566 | 18225 | 18225 | 0 | 132 | 132 | 1366 | 0 | 0 | 2790 | 0 | 0 | 29 | 0 | 0 | 1768 | 0 | 0 | 44 | 0 | 0 | 18225 | 2020-06-01 | 2022-03-01 | 2022-04-01 | 2022-11-01 | [8 empty] | 2020-05-01 | 2021-06-01 | 2021-08-01 | 2022-03-01 | 2023-04-01
197 | 04 | 1498F | SCL | 82 | CAPM | In Mountain View, Los Altos, and Palo Alto, from 0.05 mile north of Route 237 to Sand Hill Road. Pavement rehabilitation. | 28180 | 888 | 888 | 1974 | 1974 | 99 | 99 | 1974 | 1974 | 360 | 360 | 22885 | 22885 | 0 | 185 | 185 | 1027 | 0 | 0 | 2124 | 0 | 0 | 101 | 0 | 0 | 2110 | 0 | 0 | 360 | 0 | 0 | 22885 | 2020-03-03 | 2021-07-06 | 2021-08-11 | 2021-11-30 | [8 empty] | 2020-05-01 | 2021-11-17 | 2021-12-01 | 2022-05-27 | 2023-12-14
198 | 04 | 1498G | SM | 280 | SM-280 Seismic at 6 Br.s | In and near Menlo Park and San Bruno, from Alpine Road to Route 380 at Alpine Road Undercrossing No. 35-0009L/R (PM R0.05), Sand Hill Road Overcrossing (OC) (South) No. 35-0007 (PM R1.56), Sand Hill Road OC (North) No. 35-0008 (PM R1.62), and Route 280/380 Separation No. 35-0217L/R (PM R20.97). Structure seismic retrofit. | 10432 | 600 | 600 | 1000 | 1000 | 100 | 100 | 1000 | 1000 | 262 | 262 | 7470 | 7470 | 0 | 388 | 388 | 862 | 0 | 0 | 999 | 0 | 0 | 96 | 0 | 0 | 1000 | 0 | 0 | 262 | 0 | 0 | 7470 | 2020-10-01 | 2022-05-01 | 2022-04-01 | 2022-10-01 | [8 empty] | 2020-03-18 | 2022-03-01 | 2022-04-01 | 2022-07-01 | 2023-06-01
199 | 04 | 1499J | ALA | 980 | ATMS and PCDC Upgrade Project | In Oakland, at the District 4 Transportation Management Center (TMC). Upgrade or replace legacy TMC software applications and interface components, and related system devices by service contract. | 4794 | 111 | 111 | 553 | 553 | 12 | 12 | 431 | 431 | 0 | 0 | 3687 | 3687 | 0 | 83 | 83 | 83 | 71 | 71 | 586 | 0 | 0 | 12 | 0 | 0 | 458 | 0 | 0 | 5 | 0 | 0 | 3687 | 2018-10-01 | 2019-09-01 | 2019-12-01 | 2020-11-01 |  |  | 2018-10-01 | [6 empty] | 2019-11-01 | 2019-12-01 | 2020-11-01 | 2025-08-29
200 | 04 | 8315X | ALA | 580 | Altamont Rehab Mitigation | Near Livermore, from San Joaquin county line to east of Greenville overcrossing; also on Route 205 (PM 0.0/1.0) from San Joaquin county line to Midway Road undercrossing. Environmental mitigation for EA 3G590. | 2250 | 0 | 0 | 0 | 0 | 150 | 150 | 0 | 0 | 2100 | 2100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59 | 59 | 189 | 0 | 0 | 0 | 802 | 802 | 2100 | 0 | 0 | 0 | 2014-09-15 | 2018-07-18 | 2018-09-30 | 2019-02-28 |  |  | 2017-07-17
201 | 05 | 0040C | SLO | 101 | North Paso Robles Mitigation Planting | In San Luis Obispo County near Paso Robles from 0.1 mile south to 0.1 mile north of San Marcos Creek Bridge and from 0.1 mile south to 0.1 mile north of South San Miguel Undercrossing. Landscape mitigation. | 1000 | 0 | 0 | 223 | 223 | 28 | 28 | 479 | 479 | 0 | 0 | 270 | 270 | 0 | 0 | 0 | 0 | 90 | 90 | 189 | 2 | 2 | 31 | 0 | 0 | 621 | 0 | 0 | 0 | 0 | 0 | 270 | 2013-09-04 | 2019-03-15 | 2019-06-03 | 2019-11-18 |  |  | 2013-09-04 | 2019-03-06 | 2019-05-30 | [6 empty] | 2020-06-01 | 2022-11-01
202 | 05 | 0072 | SLO | 1 | Toro Creek Bridge replacement | In Morro Bay, at Toro Creek Bridge No.49-0068R. Replace bridge. | 14130 | 0 | 0 | 2300 | 2300 | 275 | 275 | 2400 | 2400 | 906 | 906 | 8249 | 8249 | 0 | 1697 | 1697 | 1697 | 846 | 846 | 2345 | 15 | 15 | 177 | 0 | 0 | 2412 | 55 | 55 | 952 | 0 | 0 | 8249 | 2018-06-18 | 2020-04-17 | 2020-06-29 | 2021-02-04 |  |  | 2018-06-26 | [6 empty] | 2020-05-14 | 2020-05-29 | 2021-01-05 | 2023-12-12
203 | 05 | 0072A | SLO | 1 | Old Creek Bridge replacement | Near Morro Bay, at Old Creek Bridge No. 49-0070R. Replace bridge. | 18275 | 2187 | 2187 | 1900 | 1900 | 200 | 200 | 2702 | 2702 | 450 | 450 | 10836 | 10836 | 0 | 1775 | 1775 | 1775 | 844 | 844 | 2641 | 16 | 16 | 137 | 0 | 0 | 2627 | 24 | 24 | 447 | 0 | 0 | 10836 | 2017-11-02 | 2020-01-02 | 2020-04-28 | 2020-11-13 |  |  | 2018-05-15 | [6 empty] | 2020-02-25 | 2020-06-16 | 2020-12-21 | 2023-11-01
204 | 05 | 0072B | SLO | 58 | Trout Creek Bridge replacement | Near Santa Margarita, at Trout Creek Bridge No. 49-0091. Replace bridge. | 15658 | 2167 | 2167 | 2500 | 2500 | 210 | 210 | 2900 | 2900 | 308 | 308 | 7573 | 7573 | 0 | 1281 | 1281 | 1281 | 1279 | 1279 | 2574 | 30 | 30 | 241 | 0 | 0 | 2806 | 23 | 23 | 313 | 0 | 0 | 7573 | 2017-11-01 | 2019-12-02 | 2020-01-08 | 2020-08-12 |  |  | 2017-10-31 | [6 empty] | 2019-12-13 | 2020-01-08 | 2020-08-12 | 2023-04-25
205 | 05 | 0335 | SB | 192 | Arroyo Paredon Landscape Mitigation Planting | Near Carpinteria, at Arroyo Parida Creek Bridge No. 51-113. Environmental mitigation for emergency bridge replacement project EA 1J670/PPNO 05-0335A. | 8022 | 3 | 3 | 5146 | 5146 | 692 | 692 | 600 | 600 | 381 | 381 | 1200 | 1200 | 0 | 963 | 963 | 963 | 4504 | 4504 | 4982 | 427 | 427 | 474 | 0 | 0 | 494 | 281 | 278 | 288 | 0 | 0 | 1200 | 2009-06-29 | 2019-09-03 | 2020-01-21 | 2020-08-07 |  |  | 2009-06-29 | [6 empty] | 2019-11-01 | 2020-02-03 | 2020-09-02 | 2024-01-05
206 | 05 | 0900A | MON | 156 | Castroville Overhead | Near Castroville, from Route 183 to Castroville Boulevard. Upgrade bridge railing and widen overhead. | 11493 | 70 | 70 | 2532 | 2532 | 198 | 198 | 1800 | 1800 | 293 | 293 | 6600 | 6600 | 0 | 4 | 4 | 4 | 2069 | 2069 | 2916 | 104 | 104 | 242 | 0 | 0 | 1936 | 30 | 30 | 292 | 0 | 0 | 6600 | 2014-09-02 | 2019-07-05 | 2019-11-22 | 2020-05-27 |  |  | 2014-09-02 | [6 empty] | 2020-08-03 | 2020-10-05 | 2021-04-07 | 2022-07-11
207 | 05 | 1501Y | SB | 1 | Salsipuedes Biological Monitoring | Near Lompoc, at the Salsipuedes Creek Bridge No. 51-0095. Biological monitoring mitigation for project 05-0A050. | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0
208 | 05 | 1967 | SCR | 1 | DAVENPORT CULVERT REPLACEMENT | Near Davenport, from 1.4 miles north of Swanton Road to 0.6 mile south of Waddell Creek. Replace and upgrade existing Corrugated Metal Pipe (CMP) culverts with Reinforced Concrete Pipe (RCP) culverts. | 13140 | 1114 | 1114 | 1940 | 1940 | 344 | 344 | 1365 | 1365 | 172 | 172 | 8205 | 8205 | 0 | 843 | 843 | 1478 | 33 | 33 | 1912 | 5 | 5 | 368 | 0 | 0 | 1152 | 0 | 0 | 262 | 0 | 0 | 8205 | 2020-01-30 | 2021-07-09 | 2021-07-19 | 2021-12-27 | [8 empty] | 2019-10-28 | 2021-04-12 | 2021-04-12 | 2021-09-17 | 2023-09-22
209 | 05 | 2230 | MON | 1 | REPLACE CULVERT NEAR LIMEKILN CREEK | Near Lucia, at 0.6 mile south of Limekiln Creek Bridge. Replace culvert. | 4476 | 936 | 936 | 1300 | 1300 | 115 | 115 | 575 | 575 | 23 | 23 | 1527 | 1527 | 0 | 582 | 582 | 582 | 85 | 85 | 1293 | 8 | 8 | 114 | 0 | 0 | 582 | 2 | 2 | 26 | 0 | 0 | 1355 | 2018-10-01 | 2019-10-28 | 2020-02-03 | 2020-06-01 |  |  | 2018-11-14 | [6 empty] | 2019-10-28 | 2020-03-16 | 2020-07-13 | 2021-10-13
210 | 05 | 2386 | SB | 217 | San Jose Creek Bridge Replacement | Near Goleta, from 0.1 mile south to 0.4 mile north of San Jose Creek Bridge No. 51-0217. Replace bridge. | 42318 | 3887 | 3887 | 3459 | 3459 | 156 | 156 | 6782 | 6782 | 599 | 599 | 27435 | 27435 | 0 | 2787 | 2787 | 4044 | 0 | 0 | 2953 | 0 | 0 | 141 | 0 | 0 | 6039 | 3 | 3 | 598 | 0 | 0 | 27434 | 2019-06-20 | 2021-08-18 | 2021-10-19 | 2022-04-01 | [8 empty] | 2019-10-30 | 2021-08-18 | 2021-10-19 | 2022-04-08 | 2025-04-08
211 | 05 | 2391 | SB | 154 | Alamo Pintado Ped Bridge | Near Los Olivos, at Alamo Pintado Pedestrian Bridge No. 51-0076Y. Replace bridge. | 8648 | 1438 | 1438 | 2050 | 2050 | 50 | 50 | 1450 | 1450 | 200 | 200 | 3460 | 3460 | 0 | 958 | 958 | 1918 | 0 | 0 | 1731 | 0 | 0 | 78 | 0 | 0 | 1349 | 0 | 0 | 111 | 0 | 0 | 4080 | 2018-12-03 | 2019-10-15 | 2020-04-08 | 2020-10-06 | [8 empty] | 2020-01-15 | 2021-09-15 | 2022-01-15 | 2022-09-01 | 2024-09-01
212 | 05 | 2392 | SB | 154 | Cold Spring Bridge Maintenance Inspection Access | Near Lake Cachuma, at Cold Spring Canyon Bridge No. 51-0037. Install inspection access system below bridge and paint structure. | 23475 | 1110 | 1110 | 1740 | 1740 | 75 | 75 | 1500 | 1500 | 50 | 50 | 19000 | 19000 | 0 | 383 | 383 | 383 | 134 | 134 | 1027 | 3 | 3 | 24 | 0 | 0 | 3636 | 0 | 0 | 8 | 0 | 0 | 19000 | 2018-11-09 | 2019-08-15 | 2020-01-15 | 2020-08-03 |  | 2018-12-06 | 2018-11-09 | [6 empty] | 2020-02-15 | 2020-08-01 | 2021-02-01 | 2024-08-01
213 | 05 | 2426 | SB | 101 | SB 101 Rehab - Carpinteria (Segment 4A) | In Carpinteria, from Casitas Pass Overcrossing to 0.5 mile south of South Padaro Lane. Rehabilitate roadway. | 72710 | 9200 | 9200 | 1380 | 1380 | 220 | 220 | 10040 | 10040 | 10440 | 10440 | 41430 | 41430 | 0 | 2304 | 2304 | 2304 | 543 | 543 | 1557 | 15 | 15 | 301 | 0 | 0 | 10923 | 66 | 66 | 4241 | 0 | 0 | 41430 | [6 empty] | 2018-06-04 | [6 empty] | 2020-01-15 | 2020-01-31 | 2020-08-14 | 2024-02-21
214 | 05 | 2426A | SB | 101 | SB 101 Rehab - Padaro (Segment 4B) | In and near Summerland, from 0.9 mile south of South Padaro Lane Undercrossing to 0.6 mile north of Padaro Lane Overcrossing. Rehabilitate roadway. | 92970 | 9200 | 9200 | 4370 | 4370 | 290 | 290 | 12490 | 12490 | 5970 | 5970 | 60650 | 60650 | 0 | 3341 | 3341 | 3341 | 211 | 211 | 4743 | 2 | 2 | 160 | 0 | 0 | 9391 | 66 | 66 | 410 | 0 | 0 | 60650 | [6 empty] | 2018-06-04 | [6 empty] | 2020-10-30 | 2020-12-01 | 2021-07-15 | 2025-10-02
215 | 05 | 2426C | SB | 101 | SB 101 Rehab - Summerland (Segment 4C) | In and near Summerland, from 0.2 mile north of Padaro Lane Overcrossing to 0.2 mile north of Sheffield Avenue. Rehabilitate roadway. | 53720 | 9200 | 9200 | 330 | 330 | 90 | 90 | 6380 | 6380 | 5830 | 5830 | 31890 | 31890 | 0 | 1884 | 1884 | 1884 | 26 | 26 | 456 | 4 | 4 | 0 | 0 | 0 | 7011 | 37 | 37 | 0 | 0 | 0 | 31890 | [6 empty] | 2018-06-04 | [6 empty] | 2020-02-03 | 2020-03-03 | 2020-09-16 | 2024-10-31
216 | 05 | 2522 | SB | 101 | 101/135 Bridge Replacement | In Los Alamos, at Route 101/135 Separation No. 51 -0073L/R; also on Route 135 (PM 0.1). Replace bridges. | 20905 | 915 | 915 | 1800 | 1800 | 250 | 250 | 3240 | 3240 | 100 | 100 | 14600 | 14600 | 0 | 752 | 752 | 752 | 863 | 863 | 2172 | 8 | 8 | 224 | 0 | 0 | 2971 | 15 | 15 | 3 | 0 | 0 | 5700 | 2017-12-01 | 2019-07-15 | 2019-08-15 | 2020-03-16 |  |  | 2017-12-15 | [6 empty] | 2019-12-01 | 2020-03-31 | 2020-11-15 | 2023-01-15
217 | 05 | 2534 | MON | 1 | Big Sur CAPM | In and near Big Sur and Carmel, from Torre Canyon Bridge to San Luis Avenue. Pavement rehabilitation. | 29675 | 988 | 988 | 1427 | 1427 | 41 | 41 | 2828 | 2828 | 56 | 56 | 24335 | 24335 | 0 | 913 | 913 | 913 | 808 | 808 | 1287 | 14 | 14 | 45 | 0 | 0 | 4346 | 2 | 2 | 2 | 0 | 0 | 24335 | 2018-05-31 | 2019-05-28 | 2019-06-11 | 2020-01-02 |  |  | 2018-06-05 | 2019-05-14 | 2019-06-19 | [6 empty] | 2019-12-23 | 2021-04-05
218 | 05 | 2540 | MON | 101 | Salinas CAPM | In and near Salinas, from 0.5 mile north of North Gonzales Overcrossing to East Market Street. Pavement rehabilitation. | 37104 | 0 | 0 | 6000 | 6000 | 1200 | 1200 | 2300 | 2300 | 70 | 70 | 27534 | 27534 | 27534 | 0 | 0 | 0 | 2066 | 2066 | 2066 | 15 | 15 | 115 | 0 | 0 | 2668 | 8 | 8 | 8 | 0 | 0 | 27534 | 2016-06-30 | 2018-03-29 | 2018-10-29 | 2019-05-08 |  | 2018-10-17 | 2016-06-30 | 2018-03-29 | 2018-10-29 | 2019-06-05 | [6 empty] | 2020-07-28
219 | 05 | 2546 | MON | 101 | Paris Valley 2R Rehab | Near King City, from 0.1 mile south of Paris Valley Road Overcrossing to Rancho Undercrossing. Roadway rehabilitation. | 33118 | 11 | 11 | 1820 | 1820 | 42 | 42 | 3749 | 3749 | 14 | 14 | 27482 | 27482 | 27481 | 0 | 0 | 0 | 959 | 959 | 959 | 13 | 13 | 33 | 112 | 112 | 4000 | 7 | 7 | 16 | 8 | 8 | 27482 | 2014-07-01 | 2018-07-18 | 2018-12-07 | 2019-06-21 |  | 2018-10-17 | 2014-07-01 | 2018-07-18 | 2018-10-11 | 2019-05-01 | [6 empty] | 2020-12-23
220 | 05 | 2561 | SB | 101 | Nojoqui Creek Bridge (51-0018) Railing Upgrade | Near Buellton, at Nojoqui Creek Bridge No. 51-0018L/R. Bridge rail replacement and widening. | 11648 | 1266 | 1266 | 1789 | 1789 | 211 | 211 | 2018 | 2018 | 99 | 99 | 6265 | 6265 | 0 | 912 | 912 | 912 | 535 | 535 | 1842 | 31 | 31 | 226 | 0 | 0 | 2175 | 3 | 3 | 38 | 0 | 0 | 6109 | 2018-08-29 | 2019-11-01 | 2020-01-29 | 2020-07-15 |  |  | 2018-08-17 | [6 empty] | 2020-02-19 | 2020-03-20 | 2020-09-02 | 2022-11-01
221 | 05 | 2563 | SB | 1 | Route 1/San Antonio Creek Bridge Scour Mitigation | Near Lompoc, at San Antonio Creek Bridge No. 51-0237L/R. Bridge scour mitigation. | 5194 | 1050 | 1050 | 1692 | 1692 | 99 | 99 | 1029 | 1029 | 83 | 83 | 1241 | 1241 | 0 | 786 | 786 | 786 | 0 | 0 | 1468 | 0 | 0 | 82 | 0 | 0 | 969 | 2 | 2 | 83 | 0 | 0 | 1200 | 2019-07-05 | 2021-02-04 | 2021-07-07 | 2022-01-04 |  |  | 2019-06-24 | [6 empty] | 2021-02-16 | 2021-07-07 | 2022-01-04 | 2023-04-17
222 | 05 | 2565 | MON | 101 | San Antonio River bridge-seismic retrofit | Near Paso Robles, at San Antonio River Bridge No 44-0141L/R. Bridge seismic restoration. | 18391 | 1529 | 1529 | 1859 | 1859 | 59 | 59 | 2236 | 2236 | 841 | 841 | 11867 | 11867 | 0 | 946 | 946 | 946 | 300 | 300 | 2057 | 6 | 6 | 76 | 0 | 0 | 2259 | 9 | 9 | 73 | 0 | 0 | 9938 | 2018-09-07 | 2020-02-11 | 2020-04-29 | 2020-12-30 |  |  | 2018-09-07 | [6 empty] | 2020-03-30 | 2020-04-29 | 2020-12-30 | 2023-06-13
223 | 05 | 2567 | SB | 135 | San Antonio Cr Seismic Retrofit | Near Los Alamos, at San Antonio Creek Bridge No. 51-0006. Bridge seismic restoration. | 4922 | 784 | 784 | 1365 | 1365 | 23 | 23 | 640 | 640 | 132 | 132 | 1978 | 1978 | 0 | 502 | 502 | 502 | 135 | 135 | 1351 | 1 | 1 | 28 | 0 | 0 | 713 | 3 | 3 | 50 | 0 | 0 | 1897 | 2018-07-02 | 2019-09-01 | 2020-03-09 | 2020-09-17 |  |  | 2018-08-28 | [6 empty] | 2019-09-01 | 2020-03-09 | 2020-10-08 | 2021-10-22
224 | 05 | 2586 | SB | 1 | Solomon Canyon CAPM | Near Santa Maria, from California Boulevard to Route 166. Pavement rehabilitation. | 13171 | 1110 | 1110 | 916 | 916 | 104 | 104 | 905 | 905 | 253 | 253 | 9883 | 9883 | 0 | 770 | 770 | 770 | 540 | 540 | 1016 | 17 | 17 | 92 | 0 | 0 | 915 | 31 | 31 | 44 | 0 | 0 | 9883 | 2018-07-02 | 2019-08-01 | 2019-11-01 | 2020-05-21 |  |  | 2018-06-25 | [6 empty] | 2020-01-03 | 2020-01-03 | 2020-07-17 | 2021-04-22
225 | 05 | 2629 | SB | 135 | Santa Maria CAPM | In and near Santa Maria, from Lakeview Road to Route 101. Upgrade Americans with Disabilities Act (ADA) curb ramps, cold plane pavement, and place Rubberized Hot Mix Asphalt (RHMA) pavement. | 20847 | 0 | 0 | 1869 | 1869 | 1832 | 1832 | 2396 | 2396 | 378 | 378 | 14372 | 14372 | 0 | 0 | 0 | 0 | 827 | 827 | 2104 | 200 | 200 | 2049 | 0 | 0 | 2299 | 0 | 0 | 377 | 0 | 0 | 12565 | 2017-06-16 | 2020-09-30 | 2020-11-19 | 2021-05-24 |  | 2018-10-17 | 2017-06-16 | [6 empty] | 2020-10-01 | 2020-11-19 | 2021-05-24 | 2022-08-19
226 | 05 | 2630 | SLO | 1 | Pismo Beach CAPM | In and near Pismo Beach, from Gracia Way to North Pismo (Route 101/Route 1) Separation. Upgrade Americans with Disabilities Act (ADA) curb ramps, cold plane pavement and place Rubberized Hot Mix Asphalt (RHMA) pavement. | 15066 | 1156 | 1156 | 1751 | 1751 | 1670 | 1670 | 1568 | 1568 | 303 | 303 | 8618 | 8618 | 0 | 822 | 822 | 822 | 193 | 193 | 2120 | 0 | 0 | 1503 | 0 | 0 | 1773 | 0 | 0 | 309 | 0 | 0 | 8734 | 2019-02-01 | 2022-04-06 | 2022-04-06 | 2022-08-23 |  |  | 2018-12-03 | [6 empty] | 2022-04-06 | 2022-04-06 | 2022-08-23 | 2023-07-03
227 | 05 | 2631 | MON | 68 | Pacific Grove CAPM | In and near Pacific Grove, from Forest Avenue to Route 1. Upgrade Americans with Disabilities Act (ADA) curb ramps, cold plane pavement and place Rubberized Hot Mix Asphalt (RHMA) pavement. | 12173 | 482 | 482 | 1638 | 1638 | 312 | 312 | 1675 | 1675 | 70 | 70 | 7996 | 7996 | 0 | 338 | 338 | 338 | 8 | 8 | 1507 | 0 | 0 | 320 | 0 | 0 | 1433 | 0 | 0 | 98 | 0 | 0 | 8682 | 2019-02-26 | 2020-10-26 | 2020-12-11 | 2021-07-15 |  |  | 2019-03-11 | [6 empty] | 2020-10-26 | 2020-12-11 | 2021-07-15 | 2021-12-09
228 | 05 | 2632 | SB | 246 | Lompoc CAPM | In Lompoc, at combined segment of Route 246 and Route 1, on Route 246, from 0.3 mile west of V Street to H Street; also on Route 1, from H Street to 12th Street. Upgrade Americans with Disabilities Act (ADA) curb ramps, cold plane pavement and place Hot Mix Asphalt (HMA) pavement. | 15090 | 0 | 0 | 3630 | 3630 | 2460 | 2460 | 1750 | 1750 | 350 | 350 | 6900 | 6900 | 0 | 0 | 0 | 0 | 1026 | 1026 | 3367 | 30 | 30 | 1765 | 0 | 0 | 1535 | 0 | 0 | 760 | 0 | 0 | 6900 | 2017-04-24 | 2021-12-10 | 2021-12-15 | 2022-07-27 |  |  | 2017-04-24 | [6 empty] | 2021-10-25 | 2021-12-15 | 2022-07-27 | 2023-07-21
229 | 05 | 2649 | SB | 101 | San Jose Ck Bridge replacement | In Goleta, at San Jose Creek Bridge No. 51-0163L/R. Replace bridges to maintain standards of safety and reliability. | 16960 | 1400 | 1400 | 2730 | 2730 | 70 | 70 | 3480 | 3480 | 40 | 40 | 9240 | 9240 | 0 | 685 | 685 | 1672 | 0 | 0 | 2626 | 0 | 0 | 40 | 0 | 0 | 2863 | 0 | 0 | 34 | 0 | 0 | 9240 | 2020-04-20 | 2021-07-01 | 2021-10-01 | 2022-06-15 | [8 empty] | 2020-04-15 | 2021-06-28 | 2021-09-28 | 2022-06-10 | 2024-12-06
230 | 05 | 2651 | SB | 154 | Rehab Primavera & La Colina Bridges | In and near the city of Santa Barabara, from La Colina Road Undercrossing (UC) No. 51-0256 (PM R31.82) to Primavera Road UC No. 51-0257 (PM R32.07). Upgrade bridge railing and reconstruct abutment for bridge rehabilitation. | 13913 | 928 | 928 | 2135 | 2135 | 52 | 52 | 1956 | 1956 | 3 | 3 | 8839 | 8839 | 0 | 241 | 241 | 241 | 40 | 40 | 1982 | 0 | 0 | 51 | 0 | 0 | 1876 | 0 | 0 | 3 | 0 | 0 | 8839 | 2019-12-20 | 2021-04-15 | 2021-07-30 | 2022-01-05 |  |  | 2019-04-29 | [6 empty] | 2021-04-16 | 2021-07-01 | 2022-02-28 | 2023-07-27
231 | 05 | 2654 | MON | 1 | Garrapata Creek Bridge Rehab | Near Carmel-By-The Sea, at Garrapata Creek No. 44-0018. Rehabilitate bridge to extend the service life and mitigate corrosion by applying Electrochemical Chloride Extraction (ECE) process and waterproofing to the structure. | 11790 | 700 | 700 | 1500 | 1500 | 90 | 90 | 2100 | 2100 | 0 | 0 | 7400 | 7400 | 0 | 454 | 454 | 454 | 0 | 0 | 1818 | 1 | 1 | 107 | 0 | 0 | 2082 | 0 | 0 | 0 | 0 | 0 | 7400 | 2019-04-18 | 2020-09-15 | 2021-01-08 | 2021-07-12 |  |  | 2019-05-08 | [6 empty] | 2020-09-16 | 2021-01-28 | 2021-07-29 | 2022-09-30
232 | 05 | 2655 | SCR | 9 | San Lorenzo River Bridge and Kings Creek Bridge Replacement | Near Boulder Creek, at San Lorenzo River Bridge No. 36-0052 (PM 13.61) and Kings Creek Bridge No. 36-0054 (PM 15.49). Replace bridges to maintain standards of safety and reliability. | 23210 | 2692 | 2692 | 2884 | 2884 | 888 | 888 | 4158 | 4158 | 660 | 660 | 11928 | 11928 | 0 | 974 | 974 | 2852 | 0 | 0 | 3045 | 0 | 0 | 1094 | 0 | 0 | 4231 | 0 | 0 | 622 | 0 | 0 | 11928 | 2020-04-10 | 2021-09-03 | 2021-10-29 | 2022-03-04 | [8 empty] | 2020-08-24 | 2022-01-24 | 2022-01-24 | 2022-07-01 | 2026-03-27
233 | 05 | 2656 | MON | 1 | Castro Cyn Bridge Rail Upgrade | Near Big Sur, at the Castro Canon Bridge No. 44-0035. Upgrade bridge railing and approach railings to meet current standards. | 4601 | 608 | 608 | 1345 | 1345 | 141 | 141 | 794 | 794 | 41 | 41 | 1672 | 1672 | 0 | 435 | 435 | 971 | 0 | 0 | 1658 | 0 | 0 | 172 | 0 | 0 | 824 | 0 | 0 | 7 | 0 | 0 | 1672 | 2019-10-01 | 2020-12-01 | 2021-04-01 | 2021-12-01 | [8 empty] | 2019-10-01 | 2020-12-01 | 2021-04-05 | 2021-10-28 | 2022-06-01
234 | 05 | 2679 | MON | 101 | Prunedale Rehab | Near Salinas, from 0.3 mile north of Boronda Road to San Benito County line. Rehabilitate pavement, upgrade median barrier and guardrail, and repair drainage system. (G13 Contingency) | 12493 | 4500 | 4500 | 6300 | 6300 | 1300 | 1300 | 0 | 0 | 393 | 393 | 0 | 0 | 0 | 2919 | 2919 | 4667 | 0 | 0 | 5871 | 0 | 0 | 1198 | 0 | 0 | 10990 | 0 | 0 | 393 | 0 | 0 | 104000 | 2019-09-03 | 2021-05-12 | 2021-08-03 | 2022-02-25 | [8 empty] | 2020-07-10 | 2022-05-09 | 2022-06-09 | 2023-01-04 | 2024-12-03
235 | 05 | 2696 | MON | 1 | Garrapata Creek Bridge Rail Replacement | Near Carmel-by-the-Sea, at the Garrapata Creek Bridge No. 44-0018. Replace bridge railing to meet current traffic safety standards. (Long Lead Project) | 1600 | 1600 | 1600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63 | 63 | 1991 | 0 | 0 | 2003 | 0 | 0 | 111 | 0 | 0 | 1197 | 0 | 0 | 5 | 0 | 0 | 3000 | 2021-04-02 | 2022-10-21 | 2023-02-14 | [9 empty] | 2021-04-02 | 2022-10-21 | 2023-02-14 | 2023-09-08 | 2024-09-11
236 | 05 | 2700 | SB | 101 | Gaviota-Nojoqui Rehab | Near Gaviota, from 1.0 mile south of Gaviota Gorge Tunnel to 0.1 mile north of Nojoqui Creek Bridge. Upgrade guard railing, widen shoulders, place High Friction Surface Treatment (HSFT), construct retaining walls, cold plane pavement, place Hot Mix Asphalt (HMA) and Rubberized Hot Mix Asphalt (RHMA) pavement. (G13 Contingency) | 4903 | 2160 | 2160 | 2648 | 2648 | 74 | 74 | 0 | 0 | 21 | 21 | 0 | 0 | 0 | 1129 | 1129 | 2244 | 0 | 0 | 2217 | 0 | 0 | 64 | 0 | 0 | 3671 | 0 | 0 | 635 | 0 | 0 | 59218 | 2019-12-02 | 2021-05-21 | 2021-09-22 | 2022-05-02 | [8 empty] | 2020-03-16 | 2021-07-29 | 2021-09-23 | 2022-05-03 | 2023-04-28
237 | 05 | 2735 | MON | Var | TMS Detection Repair | In various counties, on various routes and at various locations. Replace and upgrade existing detection field elements for the Traffic Management System (TMS). | 5451 | 585 | 585 | 1160 | 1160 | 20 | 20 | 465 | 465 | 21 | 21 | 3200 | 3200 | 0 | 301 | 301 | 301 | 18 | 18 | 1285 | 2 | 2 | 43 | 0 | 0 | 484 | 0 | 0 | 0 | 0 | 0 | 3175 | 2018-09-05 | 2020-01-03 | 2020-04-01 | 2020-11-06 |  |  | 2018-10-15 | [6 empty] | 2020-03-13 | 2020-06-08 | 2021-02-01 | 2021-06-22
238 | 05 | 2736 | SCR | 1 | Soquel Creek Scour Protection | In Capitola, at Soquel Creek Bridge No. 36-0013. Place Rock Slope Protection (RSP) to protect bridge foundation. | 7703 | 1591 | 1591 | 1370 | 1370 | 196 | 196 | 1772 | 1772 | 546 | 546 | 2228 | 2228 | 0 | 519 | 519 | 1670 | 0 | 0 | 1475 | 0 | 0 | 205 | 0 | 0 | 1634 | 0 | 0 | 546 | 0 | 0 | 2580 | 2019-12-31 | 2021-04-29 | 2021-07-01 | 2022-02-01 | [8 empty] | 2019-12-31 | 2021-04-29 | 2021-07-01 | 2022-02-01 | 2023-09-29
239 | 05 | 2804 | SCR | 001 | Santa Cruz 1 CAPM and Bridge Rails | In and near Santa Cruz from North Aptos UP to Jct. Route 9. Pavement Rehabilitation, ADA Curb Ramps, Guardrail/Barrier rail/Bridge Rail Upgrades Pavement Rehabilitation, ADA Curb Ramps, Guardrail/Barrier rail/Bridge Rail Upgrades | 31105 | 606 | 606 | 2853 | 2853 | 121 | 121 | 2329 | 2329 | 19 | 19 | 25177 | 25177 | 25176 | 517 | 517 | 517 | 2803 | 2803 | 2803 | 61 | 61 | 61 | 115 | 115 | 2287 | 11 | 11 | 0 | 639 | 639 | 25177 | [6 empty] | 2016-08-22 | 2018-08-24 | 2018-10-08 | 2019-02-28 | [6 empty] | 2020-07-07
240 | 05 | 3330 | SB | 101 | Gaviota Culvert Replacement | Near Gaviota State Park. Rehabilitate and upgrade existing drainage system. | 12753 | 1120 | 1120 | 1430 | 1430 | 245 | 245 | 1111 | 1111 | 311 | 311 | 8536 | 8536 | 0 | 911 | 911 | 911 | 44 | 44 | 1155 | 6 | 6 | 216 | 0 | 0 | 960 | 3 | 3 | 656 | 0 | 0 | 9796 | 2018-08-27 | 2020-06-15 | 2020-06-15 | 2020-12-04 |  |  | 2019-03-05 | [6 empty] | 2020-05-21 | 2020-06-05 | 2020-12-18 | 2021-12-20
241 | 05 | 3330X | SB | 101 | Gaviota Culvert Replacement Seed Collection | Near Gaviota State Park. Landscape mitigation (erosion control seed collection) for drainage system restoration project EA 0K330. | 230 | 0 | 0 | 30 | 30 | 0 | 0 | 100 | 100 | 0 | 0 | 100 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 73 | 0 | 0 | 0 | 0 | 0 | 100 | [6 empty] | 2019-03-05 | 2019-06-10 | 2019-06-11 | [6 empty] | 2020-01-16 | 2021-11-15
242 | 05 | 3330Y | SB | 101 | Gaviota Culvert Replacement Landscape Mitigation | Near Gaviota State Park. Landscape mitigation (plant propagation) for drainage system restoration project EA 0K330. | 1034 | 0 | 0 | 120 | 120 | 0 | 0 | 600 | 600 | 0 | 0 | 314 | 314 | 0 | 0 | 0 | 0 | 0 | 0 | 169 | 0 | 0 | 25 | 0 | 0 | 195 | 0 | 0 | 0 | 0 | 0 | 314 | [6 empty] | 2019-03-05 | [6 empty] | 2019-09-20 | 2019-10-08 | 2020-03-25 | 2024-12-20
243 | 05 | 4020 | MON | 101 | Mon 101 TMS | In and near Salinas, from 0.4 mile north of Airport Boulevard Overcrossing to 0.3 mile south of San Miguel Canyon Road. Install vehicle detection systems, Changeable Message Signs (CMS), cameras, and a vehicle pullout. | 3338 | 260 | 260 | 1000 | 1000 | 45 | 45 | 500 | 500 | 9 | 9 | 1524 | 1524 | 0 | 137 | 137 | 137 | 389 | 389 | 677 | 7 | 7 | 43 | 0 | 0 | 621 | 0 | 0 | 0 | 0 | 0 | 1371 | 2018-07-16 | 2019-01-11 | 2019-04-15 | 2019-09-16 |  |  | 2018-07-19 | 2019-01-07 | 2019-04-15 | [6 empty] | 2019-09-16 | 2020-07-01
244 | 05 | 4022 | SLO | 101 | SLO 101 N Cnty TMS | In San Luis Obispo County, from 0.3 mile north of Reservoir Canyon Road to 0.3 mile north of North Paso Robles Overhead; also on Route 46 from Theater Drive to Union Road (PM R21.7/31.9) at various locations. Install vehicle detection systems, Changeable Message Signs (CMS), cameras, and loop detectors. | 5951 | 450 | 450 | 1095 | 1095 | 78 | 78 | 702 | 702 | 5 | 5 | 3621 | 3621 | 0 | 388 | 388 | 388 | 36 | 36 | 970 | 7 | 7 | 77 | 0 | 0 | 632 | 0 | 0 | 6 | 0 | 0 | 3621 | 2019-02-01 | 2020-08-03 | 2020-12-01 | 2022-04-01 |  |  | 2019-01-11 | [6 empty] | 2020-08-03 | 2020-12-01 | 2021-08-02 | 2022-01-03
245 | 05 | 9700 | MON | 101 | N. Soledad OH Deck Replacement | Near Soledad, from Route 146 to Front Street at the North Soledad Overhead No. 44-0091R. Rehabilitate bridge. | 17754 | 94 | 94 | 2565 | 2565 | 482 | 482 | 1535 | 1535 | 1578 | 1578 | 11500 | 11500 | 0 | 94 | 94 | 94 | 2249 | 2249 | 2535 | 300 | 300 | 538 | 0 | 0 | 1547 | 23 | 23 | 1599 | 0 | 0 | 11028 | 2014-09-02 | 2019-07-01 | 2019-11-01 | 2020-05-27 |  |  | 2014-09-02 | [6 empty] | 2020-07-01 | 2020-11-02 | 2021-05-27 | 2022-07-01
246 | 06 | 5335A | MAD | 99 | Madera 99 Widening | In and near Madera, from Avenue 12 Overcrossing to 0.9 mile north of Avenue 17 Overcrossing. Additional contribution for the construction of one new lane in each direction. Roadway rehabilitation. | 67776 | 2250 | 0 | 5545 | 1850 | 402 | 0 | 8750 | 7500 | 52 | 0 | 72146 | 58426 | 71005 | 2222 | 0 | 2222 | 6297 | 1849 | 6297 | 384 | 0 | 565 | 442 | 379 | 6896 | 23 | 0 | 21 | 5 | 3 | 71006 | 2015-08-14 | 2018-05-01 | 2018-06-01 | 2019-11-01 |  |  | 2015-08-14 | 2018-06-13 | 2018-07-05 | 2019-04-05 | [6 empty] | 2022-07-01
247 | 06 | 6286 | TUL | 190 | TULARE CULVERT REPLACEMENT | Between Springville and Camp Nelson, from east of Balch Park Road to west of Wishon Drive. Replace deteriorated culverts and upgrade existing Guardrail. | 6136 | 1080 | 1080 | 950 | 950 | 210 | 210 | 800 | 800 | 246 | 246 | 2850 | 2850 | 0 | 813 | 813 | 813 | 230 | 230 | 916 | 113 | 113 | 231 | 0 | 0 | 728 | 50 | 50 | 240 | 0 | 0 | 2850 | 2018-11-17 | 2020-03-01 | 2020-03-15 | 2021-02-01 |  |  | 2018-12-17 | [6 empty] | 2020-04-01 | 2020-04-07 | 2020-10-01 | 2021-10-01
248 | 06 | 6521 | TUL | 201 | Bridge Widening | Near Kingsburg, on Route 201 at Sand Creek Bridge No. 46-0137 and Friant-Kern Canal Bridge No. 46-0065; also on Route 216, at Kaweah River Bridge No.46-0091. Bridge rail replacement. | 22689 | 1268 | 1268 | 5140 | 5140 | 692 | 692 | 2800 | 2800 | 450 | 450 | 12339 | 12339 | 12338 | 1822 | 1822 | 1822 | 4793 | 4793 | 4793 | 627 | 627 | 691 | 945 | 945 | 2971 | 201 | 201 | 247 | 2639 | 2639 | 12339 | 2015-04-20 | 2017-06-21 | 2017-06-22 | 2019-01-21 |  |  | 2015-04-20 | 2017-06-21 | 2017-06-22 | 2018-12-18 | [6 empty] | 2021-07-19
249 | 06 | 6661A | KER | 99 | Bakersfield 99 Rehab Replacement Planting | In Bakersfield, from Brundage Lane Overcrossing to Beardsley Canal Bridge. Landscape mitigation for rehabilitate roadway project EA 0Q280. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 388 | 0 | 0 | 489 | 0 | 0 | 16 | 0 | 0 | 1428 | 0 | 0 | 0 | 0 | 0 | 6600 | [12 empty] | 2021-07-30 | 2022-04-25 | 2022-05-02 | 2023-02-02 | 2027-02-02
250 | 06 | 6679 | TUL | 99 | Tipton Bridge Deck Rehab | In Tipton, at Avenue 152 Overcrossing No. 46-0191. Replace bridge. | 14829 | 698 | 698 | 1730 | 1730 | 204 | 204 | 1354 | 1354 | 343 | 343 | 10500 | 10500 | 0 | 571 | 571 | 571 | 955 | 955 | 1895 | 124 | 124 | 243 | 0 | 0 | 1358 | 12 | 12 | 343 | 0 | 0 | 10500 | 2018-02-01 | 2020-02-03 | 2020-03-02 | 2020-08-03 |  |  | 2018-02-01 | [6 empty] | 2020-02-03 | 2020-03-02 | 2020-08-03 | 2021-10-01
251 | 06 | 6681 | KER | 99 | Union Ave to White Lane 2R Rehab | In and near Bakersfield, from 0.5 mile south of Old US 99 Overcrossing to 0.1 mile north of White Lane. Rehabilitate pavement. (G13 Contingency) | 4150 | 960 | 960 | 2300 | 2300 | 120 | 120 | 0 | 0 | 770 | 770 | 0 | 0 | 0 | 957 | 957 | 957 | 1264 | 1264 | 2119 | 32 | 32 | 86 | 0 | 0 | 4466 | 5 | 5 | 769 | 0 | 0 | 45440 | 2018-03-02 | 2020-02-03 | 2020-03-02 | 2020-08-17 |  | 2018-10-17 | 2018-03-02 | [6 empty] | 2020-04-02 | 2020-04-07 | 2020-11-02 | 2022-11-01
252 | 06 | 6708 | MAD | 41 | Ranchos Rehab | Near Fresno, from north of Avenue 15 to south of Route 145. Roadway rehabilitation. | 24780 | 2463 | 2463 | 2390 | 2390 | 1296 | 1296 | 3000 | 3000 | 4731 | 4731 | 10900 | 10900 | 0 | 1606 | 1606 | 2630 | 0 | 0 | 2590 | 0 | 0 | 1161 | 0 | 0 | 2817 | 0 | 0 | 4732 | 0 | 0 | 12323 | 2019-09-01 | 2020-02-01 | 2020-03-01 | 2020-10-01 | [8 empty] | 2020-05-13 | 2021-05-01 | 2021-05-03 | 2021-11-01 | 2023-12-01
253 | 06 | 6725 | FRE | 5 | Tumey Gulch III | Near Mendota, at Tumey Gulch Bridge No. 42-0246L/R. Replace bridge. | 17076 | 1395 | 1395 | 1900 | 1900 | 4 | 4 | 2800 | 2800 | 79 | 79 | 10898 | 10898 | 0 | 1323 | 1323 | 1323 | 246 | 246 | 1502 | 0 | 0 | 4 | 0 | 0 | 2550 | 2 | 2 | 14 | 0 | 0 | 12443 | 2018-07-31 | 2020-01-03 | 2020-02-03 | 2020-07-03 |  |  | 2018-10-12 | [6 empty] | 2020-01-03 | 2020-02-03 | 2020-07-03 | 2023-07-03
254 | 06 | 6726 | KER | 166 | Calif Aqueduct Bridge Rehab | Near Mettler, at California Aqueduct Bridge No. 50-0323. Bridge rehabilitation. | 45400 | 2400 | 2400 | 5100 | 5100 | 600 | 600 | 6200 | 6200 | 1100 | 1100 | 30000 | 30000 | 0 | 1498 | 1498 | 2302 | 0 | 0 | 4150 | 0 | 0 | 527 | 0 | 0 | 3603 | 5 | 5 | 3425 | 0 | 0 | 7300 | 2018-12-01 | 2020-11-15 | 2021-03-01 | 2021-11-15 | [8 empty] | 2020-07-01 | 2021-02-28 | 2021-03-01 | 2021-08-16 | 2023-10-02
255 | 06 | 6727 | FRE | 99 | Kingsburg 99 Rehab | In and near Kingsburg, from Route 201 to 0.3 mile south of Second Street. Roadway rehabilitation. | 51076 | 677 | 677 | 1746 | 1746 | 143 | 143 | 5000 | 5000 | 375 | 375 | 43135 | 43135 | 0 | 656 | 656 | 656 | 1634 | 1634 | 1896 | 70 | 70 | 155 | 0 | 0 | 4452 | 39 | 39 | 41 | 0 | 0 | 43135 | 2017-08-03 | 2019-04-01 | 2019-04-15 | 2019-08-08 |  | 2018-10-17 | 2017-08-03 | 2019-02-06 | 2019-05-02 | [6 empty] | 2019-11-01 | 2021-04-02
256 | 06 | 6737A | KER | 099 | Northbound 2R/Fast Freight Corridor | Near Bakersfield from Rte 5/99 Separation to 0.3 mi north of US 99 Overcrossing. Rehabilitate Pavement/Vertical Clearance Correction Rehabilitate Pavement/Vertical Clearance Correction | 76692 | 2850 | 2850 | 2270 | 2270 | 110 | 110 | 6700 | 6700 | 120 | 120 | 64642 | 64642 | 64641 | 2131 | 2131 | 2131 | 1754 | 1754 | 1754 | 10 | 10 | 10 | 476 | 476 | 5668 | 8 | 8 | 0 | 7641 | 7641 | 64642 | [6 empty] | 2017-09-22 | 2018-08-15 | 2018-08-27 | 2019-02-07 | [6 empty] | 2021-03-01
257 | 06 | 6749 | KER | 5 | Grapevine Channel Repair | Near Lebec, from 1.4 miles north of Fort Tejon to 1.3 miles south of Grapevine Road. Rehabilitate drainage systems. | 920 | 0 | 0 | 670 | 670 | 100 | 100 | 0 | 0 | 150 | 150 | 0 | 0 | 0 | 454 | 454 | 454 | 518 | 518 | 703 | 16 | 16 | 37 | 0 | 0 | 655 | 50 | 50 | 50 | 0 | 0 | 4244 | 2018-04-01 | 2019-02-01 | 2019-03-30 | 2019-11-01 |  |  | 2018-04-20 | 2019-04-25 | 2019-04-29 | [6 empty] | 2019-10-01 | 2020-07-01
258 | 06 | 6755 | KER | 43 | Enos Lane CAPM & ADA Curb Ramps | Near Bakersfield, from Route 119 to south of Noriega Road; also on Route 119, from Enos Lane to Route 5 (PM 18.1/19.8). Pavement rehabilitation. | 14954 | 800 | 800 | 700 | 700 | 81 | 81 | 650 | 650 | 23 | 23 | 12700 | 12700 | 0 | 783 | 783 | 783 | 175 | 175 | 719 | 31 | 31 | 96 | 0 | 0 | 749 | 4 | 4 | 11 | 0 | 0 | 10910 | 2018-08-01 | 2020-03-02 | 2020-04-01 | 2020-11-01 |  |  | 2018-07-27 | [6 empty] | 2020-04-01 | 2020-04-15 | 2020-12-01 | 2022-09-01
259 | 06 | 6756 | KER | 58 | West Rosedale CAPM | In and near Bakersfield, from Route 43 to 0.1 mile west of Allen Road. Pavement rehabilitation. | 13600 | 1400 | 1400 | 1200 | 1200 | 250 | 250 | 1900 | 1900 | 350 | 350 | 8500 | 8500 | 0 | 478 | 478 | 1099 | 0 | 0 | 1007 | 0 | 0 | 190 | 0 | 0 | 1693 | 0 | 0 | 350 | 0 | 0 | 8500 | 2020-10-01 | 2022-01-01 | 2022-03-01 | 2022-09-01 | [8 empty] | 2020-10-01 | 2022-02-01 | 2022-03-01 | 2022-09-01 | 2023-11-01
260 | 06 | 6766 | FRE | 180 | Kings Canyon Bridge Rail | Near Squaw Valley, at Mill Creek Bridge No. 42-0080; also near Cedar Grove, at South Fork Kings River Bridge No. 42-0024 (PM 130.1). Bridge rail upgrade. | 5471 | 480 | 480 | 1173 | 1173 | 10 | 10 | 814 | 814 | 4 | 4 | 2990 | 2990 | 0 | 457 | 457 | 457 | 1008 | 1008 | 1259 | 3 | 3 | 9 | 0 | 0 | 852 | 0 | 0 | 0 | 0 | 0 | 2990 | 2018-01-15 | 2019-01-21 | 2019-02-25 | 2019-09-02 |  |  | 2018-01-26 | 2019-01-18 | 2019-03-29 | [6 empty] | 2019-10-17 | 2020-11-10
261 | 06 | 6771 | FRE | 41 | SOUTH FRESNO VIADUCT POLYESTER CONCRETE OVERLAY | In Fresno, at the South Fresno Viaduct No. 42-0226L/R. Replace failed joint seals and rehabilitate worn bridge decks with polyester concrete overlay. | 8194 | 307 | 307 | 750 | 750 | 20 | 20 | 880 | 880 | 291 | 291 | 5946 | 5946 | 5946 | 281 | 281 | 281 | 490 | 490 | 490 | 5 | 5 | 17 | 22 | 22 | 815 | 0 | 0 | 0 | 0 | 0 | 5946 | 2017-09-29 | 2018-07-01 | 2018-09-01 | 2019-02-15 |  |  | 2017-09-29 | 2018-10-08 | 2018-12-03 | 2019-04-22 | [6 empty] | 2020-02-03
262 | 06 | 6773 | FRE | 33 | Firebaugh Bridge Pile Repair | In Fresno County, at Colony Main Canal Bridge No. 42-0031, Helm Canal Bridge No. 42-0033 and Poso Canal Bridge No. 42-0034; also in Kern County, on Route 58 at Main Drain Canal Bridge No. 50-0013. Repair erosion, clean and encase piers in concrete. | 4727 | 538 | 538 | 893 | 893 | 334 | 334 | 805 | 805 | 375 | 375 | 1782 | 1782 | 0 | 293 | 293 | 683 | 0 | 0 | 754 | 0 | 0 | 283 | 0 | 0 | 640 | 0 | 0 | 376 | 0 | 0 | 2000 | 2019-10-01 | 2021-01-01 | 2021-02-01 | 2021-07-15 | [8 empty] | 2020-04-15 | 2021-02-15 | 2021-03-01 | 2021-07-15 | 2023-08-01
263 | 06 | 6787 | TUL | 245 | Woodlake Bridge Replacement | Near Woodlake, at Yokohl Creek Bridge No. 46-0011 (PM 1.39); also at Kaweah River Bridge No. 46-0073 (PM 4.19). Replace bridges to upgrade to current standards, facilitate bike lane shoulders, and upgrade guard railing. | 18998 | 1658 | 1658 | 2260 | 2260 | 645 | 645 | 1940 | 1940 | 395 | 395 | 12100 | 12100 | 0 | 1467 | 1467 | 1643 | 0 | 0 | 2144 | 0 | 0 | 528 | 0 | 0 | 3253 | 10 | 10 | 278 | 0 | 0 | 12100 | 2019-12-13 | 2021-04-15 | 2021-04-26 | 2021-10-05 | [8 empty] | 2019-08-15 | 2021-03-15 | 2021-04-01 | 2021-10-19 | 2023-07-10
264 | 06 | 6788 | TUL | 99 | Pixley-Earlimart Bridge Rail | In and near Pixley, at Avenue 48 Overcrossing (OC) No. 46-0165 (PM 6.2), Davis Avenue OC No. 46-0172 (PM 12.6), and Avenue 100 OC No. 46-0173 (PM 12.8). Upgrade bridge railing to current standards and install approach railings. | 5168 | 740 | 740 | 1122 | 1122 | 30 | 30 | 1048 | 1048 | 108 | 108 | 2120 | 2120 | 0 | 160 | 160 | 727 | 0 | 0 | 833 | 0 | 0 | 29 | 0 | 0 | 701 | 0 | 0 | 86 | 0 | 0 | 3908 | 2019-11-20 | 2021-01-15 | 2021-02-01 | 2021-10-15 | [8 empty] | 2019-11-01 | 2021-01-15 | 2021-02-01 | 2021-10-15 | 2023-07-15
265 | 06 | 6789 | MAD | 99 | Berenda CAPM | In and near Madera, from 0.3 mile north of Avenue 16 Overcrossing to 0.9 mile north of Avenue 20 Overcrossing. Rehabilitate pavement on mainline and ramps. | 13843 | 0 | 0 | 1118 | 1118 | 109 | 109 | 1379 | 1379 | 27 | 27 | 11210 | 11210 | 0 | 0 | 0 | 0 | 770 | 770 | 1100 | 23 | 23 | 27 | 0 | 0 | 1313 | 0 | 0 | 0 | 0 | 0 | 11210 | 2016-05-11 | 2018-12-01 | 2019-01-23 | 2019-07-15 |  |  | 2016-05-11 | 2018-12-31 | 2019-01-25 | [6 empty] | 2021-04-01 | 2022-04-01
266 | 06 | 6795 | TUL | 99 | Tul-Fre-Mad Pumping Plant Upgrades | In Tulare, Fresno and Madera Counties, on Route 99 at various locations. Upgrade existing pumps and control systems at eleven pumping plants. | 10765 | 650 | 650 | 2060 | 2060 | 620 | 620 | 2230 | 2230 | 65 | 65 | 5140 | 5140 | 0 | 408 | 408 | 408 | 750 | 750 | 1881 | 41 | 41 | 553 | 0 | 0 | 1776 | 7 | 7 | 7 | 0 | 0 | 5140 | 2018-07-13 | 2019-11-08 | 2019-11-20 | 2020-05-11 |  |  | 2018-06-11 | [6 empty] | 2019-11-08 | 2019-12-06 | 2020-07-02 | 2022-01-01
267 | 06 | 6796 | KER | Var | Kern-Kings Pumping Plant Upgrades | In Kern and Kings Counties, on Route 99, 198 and 204 at various locations. Upgrade existing pumps and control systems at eleven pumping plants. | 10802 | 650 | 650 | 2190 | 2190 | 610 | 610 | 2150 | 2150 | 122 | 122 | 5080 | 5080 | 0 | 424 | 424 | 424 | 763 | 763 | 1292 | 53 | 53 | 304 | 0 | 0 | 1688 | 1 | 1 | 33 | 0 | 0 | 4494 | 2018-07-13 | 2019-11-08 | 2019-11-20 | 2020-05-11 |  |  | 2018-06-19 | [6 empty] | 2019-10-01 | 2019-10-11 | 2020-07-02 | 2021-10-31
268 | 06 | 6798 | KER | 184 | Morning Drive 3R Rehab | In and near Bakersfield, from 0.2 mile south of Edison Highway to Route 178. Upgrade Americans with Disabilities Act (ADA) curbs and barrier railing, widen shoulders, cold plane pavement, place Hot Mix Asphalt (HMA) and Rubberized Hot Mix Asphalt (RHMA) pavement to rehabilitate roadway. | 12140 | 1020 | 1020 | 1520 | 1520 | 50 | 50 | 1600 | 1600 | 350 | 350 | 7600 | 7600 | 0 | 430 | 430 | 1165 | 0 | 0 | 1405 | 0 | 0 | 47 | 0 | 0 | 1387 | 0 | 0 | 352 | 0 | 0 | 7600 | 2019-01-02 | 2020-09-09 | 2020-10-02 | 2021-04-11 | [8 empty] | 2020-09-01 | 2021-04-01 | 2021-05-01 | 2021-10-01 | 2022-12-01
269 | 06 | 6800 | FRE | 99 | Selma to Fowler Rehab | In and near Selma and Fowler, from 0.1 south of Rose Avenue Undercrossing to Merced Street Undercrossing. Replace pavement with Continuous Reinforced Concrete Pavement (CRCP). Update curb ramps to meet current Americans with Disabilities Act (ADA) Standards. (G13 Contingency) | 3570 | 1130 | 1130 | 2360 | 2360 | 24 | 24 | 0 | 0 | 56 | 56 | 0 | 0 | 0 | 1092 | 1092 | 1092 | 754 | 754 | 2315 | 13 | 13 | 27 | 0 | 0 | 10356 | 7 | 7 | 153 | 0 | 0 | 86000 | 2018-12-18 | 2020-03-03 | 2020-04-14 | 2020-08-25 |  | 2019-01-31 | 2018-12-18 | [6 empty] | 2020-04-01 | 2020-04-14 | 2020-08-25 | 2022-10-25
270 | 06 | 6802 | FRE | 198 | Fre-198/Ker-119 Culverts | In Fresno County, at various locations; also in Kern County, on Route 119 at various locations. Replace damaged drainage systems. | 3407 | 0 | 0 | 1247 | 1184 | 484 | 484 | 454 | 454 | 165 | 165 | 1120 | 1120 | 0 | 0 | 0 | 0 | 872 | 872 | 1234 | 57 | 57 | 425 | 0 | 0 | 426 | 14 | 14 | 15 | 0 | 0 | 1206 | 2017-05-22 | 2019-03-01 | 2019-04-01 | 2019-10-14 |  |  | 2017-05-22 | 2019-04-16 | 2019-04-29 | [6 empty] | 2020-07-01 | 2020-12-01
271 | 06 | 6803 | KER | 184 | Weedpatch Hwy 3R Rehab | Near Bakersfield, from south of Hickory Lane to north of Brundage Lane. Upgrade Americans with Disabilities Act (ADA) curb ramps, install bike lanes, cold plane pavement, place Hot Mix Asphalt (HMA) and Rubberized Hot Mix Asphalt (RHMA) pavement. | 31910 | 2425 | 2425 | 3175 | 3175 | 2630 | 2630 | 3750 | 3750 | 2230 | 2230 | 17700 | 17700 | 0 | 738 | 738 | 4178 | 0 | 0 | 2449 | 0 | 0 | 1610 | 0 | 0 | 2511 | 0 | 0 | 2230 | 0 | 0 | 17700 | 2019-10-01 | 2021-08-01 | 2021-08-16 | 2022-02-01 | [8 empty] | 2020-10-01 | 2022-03-01 | 2022-04-01 | 2022-11-01 | 2024-11-01
272 | 06 | 6809 | FRE | 168 | Morgan Canyon CAPM | Near Prather, from Sample Road to Oak Creek Road. Upgrade barrier railing, cold plane pavement, place Hot Mix Asphalt (HMA) and Rubberized Hot Mix Asphalt (RHMA) pavement. | 12026 | 750 | 750 | 1230 | 1230 | 1 | 1 | 1140 | 1140 | 5 | 5 | 8900 | 8900 | 0 | 390 | 390 | 390 | 187 | 187 | 1057 | 0 | 0 | 1 | 0 | 0 | 1089 | 0 | 0 | 0 | 0 | 0 | 5000 | 2019-02-15 | 2020-03-13 | 2020-03-26 | 2020-09-18 |  |  | 2018-10-29 | [6 empty] | 2020-01-15 | 2020-02-03 | 2020-09-15 | 2021-10-29
273 | 06 | 6810 | KER | 46 | Wasco Route 46 CAPM | In and near Wasco, from Magnolia Avenue to Route 43 South. Upgrade Americans with Disabilities Act (ADA) curb ramps, cold plane pavement, place Hot Mix Asphalt (HMA) and Rubberized Hot Mix Asphalt (RHMA) pavement. | 7665 | 710 | 710 | 950 | 950 | 415 | 415 | 900 | 900 | 90 | 90 | 4600 | 4600 | 0 | 508 | 508 | 508 | 286 | 286 | 1276 | 58 | 58 | 496 | 0 | 0 | 957 | 4 | 4 | 43 | 0 | 0 | 3856 | 2018-07-19 | 2020-04-03 | 2020-05-01 | 2020-10-29 |  |  | 2018-04-26 | [6 empty] | 2020-02-03 | 2020-03-02 | 2020-09-15 | 2021-09-30
274 | 06 | 6820 | KER | 5 | Lost Hills Rehab | Near Kettleman City, from 0.34 mile south of Twisselman Road Overcrossing to Kings County line. Reconstruct the number two lane with continuously reinforced concrete pavement (CRCP) and grind the number one lane to rehabilitate pavement. | 29330 | 440 | 440 | 1200 | 1200 | 25 | 25 | 1900 | 1900 | 65 | 65 | 25700 | 25700 | 0 | 424 | 424 | 424 | 315 | 315 | 1520 | 2 | 2 | 21 | 0 | 0 | 2560 | 0 | 0 | 0 | 0 | 0 | 21500 | 2019-01-24 | 2019-09-06 | 2019-10-04 | 2020-04-12 |  | 2019-05-16 | 2019-01-24 | [6 empty] | 2020-04-01 | 2020-04-02 | 2020-08-17 | 2021-10-01
275 | 06 | 6857 | MAD | 99 | COTTONWOOD CREEK BRIDGE REPLACEMENT (Br. No. 41-0065 L/R&S) | Near the city of Madera, at Cottonwood Creek Bridge No. 41-065R, No. 41-0065L and No. 41-0065S. Replace bridges to mitigate corrosion by chloride latent concrete. | 36437 | 2400 | 2400 | 3200 | 3200 | 100 | 100 | 6100 | 6100 | 137 | 137 | 24500 | 24500 | 0 | 1611 | 1611 | 2536 | 0 | 0 | 2080 | 0 | 0 | 61 | 0 | 0 | 4409 | 1 | 1 | 136 | 0 | 0 | 24500 | 2020-07-01 | 2021-07-07 | 2021-07-26 | 2022-03-02 | [8 empty] | 2020-07-01 | 2021-07-07 | 2021-07-26 | 2022-03-02 | 2024-10-10
276 | 06 | 6873 | KIN | 41 | STRATFORD KINGS RIVER BRIDGE REPLACEMENT | In and near Stratford, from 22nd Street to Laurel Avenue at the Kings River Bridge No. 45-0007. Replace 73 year old bridge due to extensive superstructure and substructure distress and susceptibility to liquefaction. | 33294 | 2300 | 2300 | 2700 | 2700 | 400 | 400 | 6400 | 6400 | 94 | 94 | 21400 | 21400 | 0 | 1172 | 1172 | 2209 | 0 | 0 | 1893 | 0 | 0 | 258 | 0 | 0 | 4012 | 5 | 5 | 232 | 0 | 0 | 23497 | 2020-04-02 | 2021-09-01 | 2021-10-01 | 2022-05-11 | [8 empty] | 2020-05-22 | 2021-09-01 | 2021-10-01 | 2022-03-30 | 2023-09-18
277 | 06 | 6877 | KER | 5 | I-5 Freight Corridor California Aqueduct | Near Grapevine, at California Aqueduct Bridge No. 50-0321L/R. Improve to standard load capacity. | 5222 | 1910 | 1910 | 430 | 430 | 10 | 10 | 725 | 725 | 10 | 10 | 2137 | 2137 | 2136 | 884 | 884 | 884 | 146 | 146 | 146 | 0 | 0 | 5 | 267 | 267 | 757 | 6 | 6 | 2 | 573 | 573 | 2137 | 2018-04-02 | 2018-07-02 | 2018-08-01 | 2018-12-14 |  |  | 2018-04-04 | 2018-07-02 | 2018-08-01 | 2019-01-15 | [6 empty] | 2019-12-13
278 | 06 | 6881 | FRE | 41 | Fre-41;99;168 & 180 Fiber Optic | In and near the city of Fresno, from 0.1 mile south of North Avenue to the Madera County line; also on Route 99 (PM 19.36 to PM 21.9), Route 168 (PM R0.2L/R to PM R9.7), and Route 180 (PM R58.55 to PM R59.85). Replace and upgrade existing communication elements for the Traffic Management System (TMS). | 20424 | 619 | 619 | 1809 | 1809 | 165 | 165 | 1791 | 1791 | 30 | 30 | 16010 | 16010 | 0 | 162 | 162 | 162 | 47 | 47 | 1631 | 1 | 1 | 137 | 0 | 0 | 1399 | 0 | 0 | 62 | 0 | 0 | 19200 | 2018-12-10 | 2021-02-08 | 2021-03-08 | 2021-09-07 |  | 2019-01-31 | 2018-12-10 | [6 empty] | 2021-02-08 | 2021-03-08 | 2021-09-07 | 2023-02-01
279 | 06 | 6883 | FRE | 99 | TMS Element Upgrade/Repair | In Fresno County, on Routes 99, 41, 168, and 180 at various locations; also in Madera County, on Route 99 at various locations. Repair vehicle detection systems. | 6278 | 800 | 800 | 1017 | 1017 | 250 | 250 | 1056 | 1056 | 119 | 119 | 3036 | 3036 | 0 | 271 | 271 | 271 | 76 | 76 | 1033 | 24 | 24 | 216 | 0 | 0 | 834 | 0 | 0 | 30 | 0 | 0 | 2887 | 2018-09-03 | 2019-12-02 | 2019-12-16 | 2020-06-01 |  |  | 2018-10-12 | [6 empty] | 2020-04-01 | 2020-04-05 | 2020-10-13 | 2021-11-30
280 | 06 | 6884 | KER | 5 | Grapevine Culvert Repair | In Kern County, from 2.4 miles north of Fort Tejon Overcrossing to 1.2 miles south of Grapevine Undercrossing at four locations. Repair reinforced concrete box culverts. | 14214 | 955 | 955 | 2173 | 2173 | 29 | 29 | 2763 | 2763 | 132 | 132 | 8162 | 8162 | 0 | 704 | 704 | 704 | 0 | 0 | 1305 | 0 | 0 | 27 | 0 | 0 | 2315 | 2 | 2 | 104 | 0 | 0 | 8162 | 2019-03-01 | 2020-02-01 | 2020-03-01 | 2020-09-16 |  |  | 2019-05-03 | [6 empty] | 2020-04-01 | 2020-04-10 | 2020-09-16 | 2021-09-16
281 | 06 | 6887 | MAD | 99 | SOUTH GATEWAY DRIVE OC DECK REHAB | Near the city of Madera, at South Gateway Drive Overcrossing No. 41-0046K. Replace bridge railing, grind deck, and place reinforced Portland Cement Concrete (PCC) to rehabilitate bridge. | 6081 | 950 | 950 | 1100 | 1100 | 1 | 1 | 1300 | 1300 | 30 | 30 | 2700 | 2700 | 0 | 325 | 325 | 325 | 199 | 199 | 941 | 0 | 0 | 0 | 0 | 0 | 602 | 0 | 0 | 0 | 0 | 0 | 1350 | 2019-03-15 | 2020-04-02 | 2020-05-01 | 2020-10-28 |  |  | 2019-01-17 | [6 empty] | 2020-01-15 | 2020-02-05 | 2020-07-17 | 2021-10-28
282 | 06 | 6889 | KER | 204 | Golden Empire CAPM | In Bakersfield, from F Street to Route 99. Cold plane pavement, place Hot Mix Asphalt (HMA) and Rubberized Hot Mix Asphalt (RHMA) pavement. | 5105 | 450 | 450 | 740 | 740 | 65 | 65 | 550 | 550 | 10 | 10 | 3290 | 3290 | 0 | 323 | 323 | 323 | 377 | 377 | 822 | 0 | 0 | 39 | 0 | 0 | 594 | 0 | 0 | 170 | 0 | 0 | 3290 | 2018-08-13 | 2019-11-15 | 2019-12-10 | 2020-06-15 |  |  | 2018-09-24 | [6 empty] | 2019-11-15 | 2019-12-10 | 2020-07-01 | 2021-12-15
283 | 06 | 6921 | FRE | 198 | Fresno 198 Culvert Rehab | In Fresno County, on Route 198 at various locations. Improve drainage facilities by repairing or replacing culverts. | 24560 | 3000 | 3000 | 1600 | 1600 | 1600 | 1600 | 2800 | 2800 | 660 | 660 | 14900 | 14900 | 0 | 693 | 693 | 1857 | 0 | 0 | 1400 | 0 | 0 | 1424 | 0 | 0 | 2345 | 0 | 0 | 628 | 0 | 0 | 14900 | 2019-12-06 | 2022-02-28 | 2022-03-18 | 2022-08-19 | [8 empty] | 2020-11-09 | 2023-01-13 | 2023-02-15 | 2023-09-11 | 2025-11-28
284 | 06 | 6923 | FRE | Var | TMS Detection Repair | In Fresno, Kern, Kings, Madera, and Tulare Counties, at various locations. Repair Transportation Management System (TMS) elements. | 6110 | 400 | 400 | 900 | 900 | 10 | 10 | 800 | 800 | 0 | 0 | 4000 | 4000 | 0 | 137 | 137 | 337 | 0 | 0 | 857 | 0 | 0 | 6 | 0 | 0 | 580 | 0 | 0 | 66 | 0 | 0 | 4000 | 2019-09-02 | 2020-12-01 | 2021-01-15 | 2021-07-01 | [8 empty] | 2019-09-02 | 2020-12-01 | 2021-01-15 | 2021-07-06 | 2022-10-01
285 | 06 | 6925 | KER | 178 | Kern Canyon Culvert Rehab | Near Bakersfield, from east of Miramonte Drive to Vista Grande Drive. Repair, replace, and/or clean culverts. | 13000 | 2800 | 2800 | 900 | 900 | 480 | 480 | 1700 | 1700 | 20 | 20 | 7100 | 7100 | 0 | 489 | 489 | 2268 | 0 | 0 | 768 | 0 | 0 | 570 | 0 | 0 | 1416 | 0 | 0 | 10 | 0 | 0 | 7100 | 2021-12-15 | 2022-04-01 | 2022-04-15 | 2022-12-30 | [8 empty] | 2020-10-29 | 2021-12-15 | 2022-01-14 | 2022-08-01 | 2023-08-01
286 | 06 | 6934 | FRE | 145 | McMullin Grade CAPM | Near Helm, from Kamm Avenue to Manning Avenue. Pavement rehabilitation. | 12050 | 820 | 820 | 860 | 860 | 30 | 30 | 2100 | 2100 | 40 | 40 | 8200 | 8200 | 0 | 240 | 240 | 763 | 0 | 0 | 837 | 0 | 0 | 18 | 0 | 0 | 1966 | 0 | 0 | 40 | 0 | 0 | 8200 | 2020-03-20 | 2020-12-22 | 2021-01-22 | 2021-06-28 | [8 empty] | 2020-04-01 | 2020-12-22 | 2021-01-22 | 2021-06-28 | 2023-06-28
287 | 06 | 6957 | KER | 58 | Reward CAPM | Near McKittrick, from San Luis Obispo County line to Route 33. Pavement rehabilitation, repair culverts, and upgrade Intelligent Transportation System (ITS) field elements. | 15970 | 1500 | 1500 | 1500 | 1500 | 30 | 30 | 1800 | 1800 | 140 | 140 | 11000 | 11000 | 0 | 230 | 230 | 1396 | 0 | 0 | 1296 | 0 | 0 | 29 | 0 | 0 | 1429 | 0 | 0 | 140 | 0 | 0 | 11000 | 2020-10-01 | 2021-02-01 | 2021-04-01 | 2021-10-01 | [8 empty] | 2020-10-01 | 2021-02-01 | 2021-04-01 | 2021-10-03 | 2022-08-01
288 | 06 | 6965 | KIN | 43 | Kings 43 CAPM | In and near Corcoran, from the Tulare County line to west of Santa Fe Avenue. Pavement rehabilitation. | 6900 | 550 | 550 | 900 | 900 | 150 | 150 | 700 | 700 | 100 | 100 | 4500 | 4500 | 0 | 255 | 255 | 255 | 17 | 17 | 935 | 0 | 0 | 31 | 0 | 0 | 666 | 0 | 0 | 4 | 0 | 0 | 4500 | 2019-03-30 | 2020-04-01 | 2020-04-08 | 2020-09-01 |  |  | 2019-03-28 | [6 empty] | 2020-04-01 | 2020-04-10 | 2020-10-16 | 2021-10-15
289 | 06 | 6970 | FRE | 5 | Panoche CAPM | Near Mendota, from north of Three Rocks Road to south of Panoche Road. Pavement rehabilitation, repair culverts and upgrade Transportation Management Systems (TMS) field elements. | 44710 | 2000 | 2000 | 1300 | 1300 | 10 | 10 | 5200 | 5200 | 300 | 300 | 35900 | 35900 | 0 | 150 | 150 | 1734 | 0 | 0 | 1132 | 0 | 0 | 8 | 0 | 0 | 4451 | 0 | 0 | 405 | 0 | 0 | 35900 | 2021-01-15 | 2021-08-02 | 2021-12-01 | 2022-07-01 | [8 empty] | 2021-01-15 | 2021-08-02 | 2021-12-01 | 2022-07-01 | 2024-09-06
290 | 07 | 3734 | LA | 213 | Storm Drain Repair | In Rancho Palos Verdes, from Caddington Drive to Peninsula Verde Drive. Replace two damaged drainage systems. | 3980 | 402 | 402 | 923 | 923 | 310 | 310 | 423 | 423 | 260 | 260 | 1662 | 1662 | 0 | 251 | 251 | 251 | 1 | 1 | 894 | 0 | 0 | 182 | 0 | 0 | 385 | 8 | 8 | 160 | 0 | 0 | 1662 | 2018-08-17 | 2020-02-28 | 2020-03-30 | 2019-10-31 |  |  | 2018-09-28 | [6 empty] | 2020-05-01 | 2020-06-01 | 2021-07-14 | 2022-07-12
291 | 07 | 4496 | VEN | 33 | Scour Mitigation & Rail Upgrade | Near Oak View, at San Antonio Creek Bridge No. 52-0065. Scour mitigation and bridge rail upgrade. | 9263 | 2020 | 2020 | 1423 | 1423 | 600 | 600 | 1460 | 1460 | 1300 | 1300 | 2460 | 2460 | 0 | 1898 | 1898 | 1898 | 1361 | 1361 | 1411 | 333 | 333 | 566 | 0 | 0 | 1728 | 109 | 109 | 2754 | 0 | 0 | 2460 | 2017-06-30 | 2019-01-04 | 2019-01-25 | 2019-09-06 |  |  | 2017-06-30 | 2019-01-10 | 2019-06-28 | [6 empty] | 2019-10-25 | 2021-12-21
292 | 07 | 4498 | LA | 1 | TRANCAS CREEK BRIDGE | In Malibu, from Guernsey Avenue to Trancas Canyon Road/Broad Beach Road. Replace bridge. | 52500 | 2737 | 2737 | 3000 | 3000 | 2000 | 2000 | 3100 | 3100 | 30035 | 30035 | 11628 | 11628 | 0 | 2722 | 2722 | 2722 | 1220 | 1220 | 3062 | 537 | 537 | 1004 | 0 | 0 | 2846 | 124 | 124 | 27350 | 0 | 0 | 11628 | 2017-06-30 | 2020-08-21 | 2020-09-30 | 2021-03-30 |  | 2018-10-17 | 2017-06-30 | [6 empty] | 2020-08-21 | 2020-09-30 | 2021-03-30 | 2022-12-30
293 | 07 | 4601 | VEN | 1 | Bridge Rail | Near Sea Cliff, at Willow Creek Bridge No. 52-003; also in Ojai, on Route 33 at North Fork Matilija Bridges No. 52-0044 (PM 15.8) and No. 52-0173 (PM16.1). Upgrade bridge railings to meet current standards. | 9501 | 1244 | 1244 | 2300 | 2300 | 465 | 465 | 2000 | 2000 | 835 | 835 | 2657 | 2657 | 0 | 891 | 891 | 1209 | 0 | 0 | 2237 | 0 | 0 | 437 | 0 | 0 | 1968 | 2 | 2 | 792 | 0 | 0 | 4868 | 2018-11-05 | 2020-11-01 | 2020-12-01 | 2021-07-02 | [8 empty] | 2019-08-15 | 2021-04-30 | 2021-06-01 | 2021-12-31 | 2023-07-21
294 | 07 | 4687 | VEN | 101 | Ven 101 Padre Juan Rehab | Near Sea Cliff, from 0.4 mile south of Padre Juan Canyon Road Overcrossing to 0.3 mile north of Punta Gorda Pedestrian Undercrossing. Rehabilitate roadway. | 52480 | 530 | 530 | 3300 | 3300 | 0 | 0 | 6000 | 6000 | 150 | 150 | 42500 | 42500 | 0 | 511 | 511 | 511 | 778 | 778 | 2262 | 0 | 0 | 193 | 0 | 0 | 5287 | 0 | 0 | 99 | 0 | 0 | 42500 | 2018-09-28 | 2020-01-10 | 2020-02-14 | 2020-08-28 |  | 2018-12-06 | 2018-09-28 | [6 empty] | 2020-02-14 | 2020-03-30 | 2020-08-28 | 2023-08-31
295 | 07 | 4688 | VEN | 23 | VEN-23 REHAB | In and near cities of Thousand Oaks and Moorpark, from Route 101 to Route 118. Rehabilitate pavement. | 119535 | 1630 | 1630 | 7500 | 7500 | 100 | 100 | 17000 | 17000 | 860 | 860 | 92445 | 92445 | 0 | 1642 | 1642 | 1642 | 4265 | 4265 | 6996 | 5 | 5 | 92 | 0 | 0 | 14721 | 0 | 0 | 51 | 0 | 0 | 92450 | 2017-09-28 | 2019-05-10 | 2019-06-14 | 2020-03-10 |  | 2018-10-17 | 2017-09-28 | 2019-06-13 | 2019-06-28 | [6 empty] | 2020-03-10 | 2023-09-15
296 | 07 | 4699 | LA | 60 | Pavement Rehab | In and near Monterey Park, Montebello, Rosemead, and South El Monte, from 0.5 miles west of Route 710 to Route 605; also on Route 710, from 0.5 miles south to 0.5 miles north of Route 60. Rehabilitate pavement. | 158791 | 1173 | 1173 | 9990 | 9990 | 481 | 481 | 30000 | 30000 | 347 | 347 | 116800 | 116800 | 106032 | 1170 | 1170 | 1170 | 9994 | 9994 | 9994 | 408 | 408 | 480 | 0 | 0 | 18672 | 46 | 46 | 165 | 0 | 0 | 106032 | 2015-08-31 | 2018-05-29 | 2018-11-30 | 2019-04-30 |  |  | 2015-08-31 | 2018-05-29 | 2019-01-14 | 2019-06-26 | [6 empty] | 2025-01-14
297 | 07 | 4704 | LA | 91 | Seismic Retrofit | In Compton, at Compton Creek Bridge Overhead and offramp No. 53-2235 and No. 53-2237S; also in Long Beach, on Routes 710 and 110, at Harbor Scenic Drive Overhead No. 53-2934 (PM 6.0) and Gaffy Street Bridge No. 53-0397Y (PM R0.8). Bridge seismic retrofit and bridge rail upgrade. | 24788 | 2260 | 2260 | 3500 | 3500 | 150 | 150 | 4100 | 4100 | 1926 | 1926 | 12852 | 12852 | 0 | 923 | 923 | 1994 | 0 | 0 | 3225 | 0 | 0 | 144 | 0 | 0 | 3260 | 0 | 0 | 1926 | 0 | 0 | 10712 | 2018-08-30 | 2020-02-28 | 2020-03-30 | 2020-12-30 | [8 empty] | 2020-09-30 | 2022-02-25 | 2022-03-30 | 2022-11-30 | 2024-11-27
298 | 07 | 4712 | LA | 10 | LANE REPLACEMENT | In Baldwin Park and West Covina, from Route 605 to Citrus Avenue. Rehabilitate roadway. (G13 Contingency) | 9844 | 1289 | 1289 | 8385 | 8385 | 23 | 23 | 0 | 0 | 147 | 147 | 0 | 0 | 0 | 1275 | 1275 | 1275 | 1258 | 1258 | 7987 | 0 | 0 | 17 | 0 | 0 | 8124 | 0 | 0 | 84 | 0 | 0 | 60496 | 2018-06-20 | 2020-02-26 | 2020-02-28 | 2021-01-15 |  | 2018-10-17 | 2018-06-20 | [6 empty] | 2020-04-15 | 2020-05-29 | 2021-02-26 | 2024-01-12
299 | 07 | 4718 | LA | 57 | Lane Replacement | In and near Diamond Bar, from the Orange County line to Route 60. Pavement rehabilitation. | 98950 | 50 | 50 | 9900 | 9900 | 10 | 10 | 13000 | 13000 | 70 | 70 | 75920 | 75920 | 0 | 49 | 49 | 49 | 6047 | 6047 | 7088 | 8 | 8 | 9 | 0 | 0 | 13030 | 49 | 49 | 70 | 0 | 0 | 75920 | 2018-01-03 | 2019-04-10 | 2019-05-31 | 2020-01-10 |  | 2018-10-17 | 2018-01-03 | 2019-03-07 | 2019-06-18 | [6 empty] | 2020-04-30 | 2022-12-01
300 | 07 | 4721 | LA | 405 | REPLACE DRAINAGE INLETS | In Carson, at Dolores Yard Overhead No. 53-1168. Upgrade bridge drainage system. | 4252 | 400 | 400 | 624 | 624 | 240 | 240 | 794 | 794 | 1 | 1 | 2193 | 2193 | 0 | 320 | 320 | 320 | 5 | 5 | 539 | 0 | 0 | 355 | 0 | 0 | 809 | 0 | 0 | 1952 | 0 | 0 | 2518 | 2018-07-18 | 2020-02-14 | 2020-03-30 | 2020-01-06 |  |  | 2018-09-28 | [6 empty] | 2021-03-01 | 2021-03-30 | 2022-01-31 | 2023-07-05
301 | 07 | 4770 | LA | 101 | Pavement Rehab and ADA curb ramps | In the cities of Los Angeles, Calabasas, and Hidden Hills, from Route 170 to Las Virgenes Road. Rehabilitate pavement, construct and upgrade Americans with Disabilities Act (ADA) curb ramps. | 15574 | 1074 | 1074 | 2224 | 2224 | 649 | 649 | 1607 | 1607 | 25 | 25 | 9995 | 9995 | 0 | 904 | 904 | 904 | 880 | 880 | 2208 | 53 | 53 | 550 | 0 | 0 | 1591 | 24 | 24 | 1386 | 0 | 0 | 9995 | 2018-03-26 | 2019-12-19 | 2020-03-19 | 2020-08-20 |  |  | 2018-03-29 | [6 empty] | 2020-02-19 | 2020-03-19 | 2020-10-01 | 2021-10-21
302 | 07 | 4788 | LA | 210 | Seismic Retrofit | In Los Angeles County, on Routes 210, 405 and 605 at various locations. Bridge seismic retrofit and bridge rail upgrade at five locations. | 9943 | 400 | 400 | 1398 | 1398 | 20 | 20 | 1600 | 1600 | 130 | 130 | 6395 | 6395 | 0 | 393 | 393 | 393 | 1099 | 1099 | 1336 | 1 | 1 | 19 | 0 | 0 | 1494 | 0 | 0 | 131 | 0 | 0 | 5824 | 2017-09-22 | 2019-08-30 | 2019-11-19 | 2020-04-10 |  |  | 2017-09-22 | [6 empty] | 2019-08-19 | 2019-09-19 | 2020-08-14 | 2021-06-16
303 | 07 | 4801 | LA | 210 | Pavement Preservation | In the city of Los Angeles, from Route 5 to North Wheatland Avenue. Rehabilitate roadway. | 146441 | 751 | 751 | 8200 | 8200 | 500 | 500 | 16500 | 16500 | 490 | 490 | 120000 | 120000 | 0 | 751 | 751 | 751 | 6256 | 6256 | 7291 | 6 | 6 | 426 | 0 | 0 | 14679 | 0 | 0 | 487 | 0 | 0 | 120000 | 2017-09-29 | 2019-04-30 | 2019-05-31 | 2020-02-25 |  | 2018-10-17 | 2017-09-29 | 2019-05-20 | 2019-06-28 | [6 empty] | 2020-06-30 | 2023-03-30
304 | 07 | 4804 | LA | 138 | RHMA Overlay on NW LA-138 | Near Gorman and Lancaster, from Route 5 to Route 14. Rehabilitate pavement. | 28040 | 510 | 510 | 2150 | 2150 | 22 | 22 | 3550 | 3550 | 128 | 128 | 21680 | 21680 | 0 | 82 | 82 | 82 | 1945 | 1945 | 2101 | 4 | 4 | 19 | 0 | 0 | 3156 | 3 | 3 | 128 | 0 | 0 | 21879 | 2017-02-10 | 2019-01-30 | 2019-04-30 | 2019-09-16 |  | 2018-10-17 | 2017-02-10 | 2019-01-31 | 2019-04-30 | [6 empty] | 2019-12-30 | 2021-07-30
305 | 07 | 4817 | LA | 134 | LA-134 Pavement Preservation | In the cities of Los Angeles, Burbank, Glendale and Pasadena, from Route 170 to Route 210. Rehabilitate pavement, upgrade guardrail and Americans with Disabilities Act (ADA) curb ramps to current standards. | 46523 | 1380 | 1380 | 4744 | 4744 | 254 | 254 | 5735 | 5735 | 376 | 376 | 34034 | 34034 | 0 | 786 | 786 | 786 | 3471 | 3471 | 4088 | 28 | 28 | 208 | 0 | 0 | 5843 | 0 | 0 | 801 | 0 | 0 | 34034 | 2017-12-29 | 2019-01-30 | 2019-04-30 | 2019-09-30 |  | 2018-10-17 | 2017-12-29 | 2019-05-21 | 2019-05-24 | [6 empty] | 2020-02-28 | 2022-07-29
306 | 07 | 4818 | LA | 107 | Pavement Rehab | In Torrance, from Route 1 to Redondo Beach Boulevard. Pavement rehabilitation. | 14795 | 351 | 351 | 1700 | 1700 | 100 | 100 | 1744 | 1744 | 0 | 0 | 10900 | 10900 | 0 | 365 | 365 | 365 | 1113 | 1113 | 1651 | 2 | 2 | 76 | 0 | 0 | 1857 | 0 | 0 | 50 | 0 | 0 | 10900 | 2016-10-11 | 2019-02-15 | 2019-03-19 | 2019-10-01 |  |  | 2016-10-11 | 2019-06-11 | 2019-06-27 | [6 empty] | 2020-03-03 | 2021-11-03
307 | 07 | 4819 | LA | 605 | Upgrade TMS | In various cities, from Orange County line to Route 210; also on Route 2 at the Transportation Management Center (TMC) (PM R18.7) and Route 5 (PM 6.8). Upgrade Transportation Management System (TMS). | 17264 | 25 | 25 | 2199 | 2199 | 202 | 202 | 3220 | 3220 | 0 | 0 | 11618 | 11618 | 0 | 21 | 21 | 21 | 1334 | 1334 | 1930 | 2 | 2 | 9 | 0 | 0 | 2542 | 0 | 0 | 0 | 0 | 0 | 11618 | 2015-06-09 | 2019-02-01 | 2019-03-05 | 2020-02-27 |  |  | 2015-06-09 | 2019-02-20 | 2019-04-15 | [6 empty] | 2019-11-01 | 2021-06-30
308 | 07 | 4830 | LA | 110 | TMS Installations | In the cities of San Pedro, Carson, Gardena and Los Angeles, from Gaffey Street to Route 5; also on Route 2 at the Transportation Management Center (TMC) Building (PM 18.7), Route 5 at Route 10 Interchange (PM 16.9) and Route 405 at Route 105 Interchange (PM 21.3). Upgrade and completion of Transportation Management System (TMS). | 40897 | 95 | 95 | 5900 | 5900 | 200 | 200 | 5000 | 5000 | 702 | 702 | 29000 | 29000 | 0 | 57 | 57 | 57 | 3103 | 3103 | 5881 | 8 | 8 | 189 | 0 | 0 | 4070 | 0 | 0 | 650 | 0 | 0 | 29000 | 2018-08-10 | 2019-02-19 | 2019-03-20 | 2019-12-13 |  | 2018-10-17 | 2018-08-10 | 2019-02-28 | 2019-05-06 | [6 empty] | 2020-02-13 | 2021-07-30
309 | 07 | 4845 | LA | 710 | Drainage Improvement, Culvert Repair, Replacement | In the cities of Los Angeles and Monterey Park, from Olympic Boulevard to Ramona Boulevard. Rehabilitate culverts. | 2488 | 310 | 310 | 669 | 669 | 47 | 47 | 205 | 205 | 50 | 50 | 1207 | 1207 | 0 | 52 | 52 | 52 | 593 | 593 | 645 | 10 | 10 | 21 | 0 | 0 | 294 | 0 | 0 | 10 | 0 | 0 | 1207 | 2017-06-30 | 2019-01-11 | 2019-04-30 | 2019-09-30 |  |  | 2017-06-30 | 2019-03-05 | 2019-04-30 | [6 empty] | 2020-01-06 | 2021-07-01
310 | 07 | 4846 | LA | 1 | Fish Passage and Culverts | In the cities of Los Angeles and Malibu, from south of Temescal Canyon Road to Ventura County line; also in Ventura County, from Los Angeles County line to Tonga Street (PM 0.0/0.9). Rehabilitate culverts. | 31518 | 2345 | 2345 | 4168 | 4168 | 2583 | 2583 | 6200 | 6200 | 5 | 5 | 16217 | 16217 | 0 | 2259 | 2259 | 2259 | 0 | 0 | 3153 | 0 | 0 | 2633 | 0 | 0 | 5309 | 7 | 7 | 14353 | 0 | 0 | 16217 | 2018-04-30 | 2020-07-02 | 2020-04-01 | 2020-08-03 |  |  | 2019-04-08 | [6 empty] | 2021-06-01 | 2021-06-14 | 2022-01-14 | 2026-04-03
311 | 07 | 4847 | LA | 5 | Drainage Rehabilitation | Near Pyramid Lake, 4.4 miles north of Templin Highway. Remove and replace two sections of damaged reinforced concrete pipe. | 3006 | 300 | 300 | 700 | 700 | 20 | 20 | 970 | 970 | 20 | 20 | 996 | 996 | 0 | 102 | 102 | 102 | 425 | 425 | 530 | 9 | 9 | 14 | 0 | 0 | 882 | 0 | 0 | 20 | 0 | 0 | 1817 | 2017-06-01 | 2018-07-31 | 2018-09-10 | 2019-03-25 |  |  | 2017-06-01 | 2018-08-21 | 2018-10-01 | [6 empty] | 2019-12-02 | 2020-09-15
312 | 07 | 4848 | LA | 134 | Drainage Improvement | In Glendale, from 0.3 mile west of North Pacific Avenue to Chevy Chase Drive at three locations. Restore culvert systems. | 2855 | 420 | 420 | 1200 | 1200 | 50 | 50 | 1175 | 1175 | 10 | 10 | 0 | 0 | 0 | 256 | 256 | 256 | 589 | 589 | 933 | 3 | 3 | 43 | 0 | 0 | 1046 | 0 | 0 | 10 | 0 | 0 | 1810 | 2017-10-19 | 2018-07-31 | 2018-09-10 | 2019-03-25 |  |  | 2017-10-19 | 2019-02-22 | 2019-03-29 | [6 empty] | 2019-12-12 | 2021-03-30
313 | 07 | 4849 | LA | 110 | Drainage Improvement & Replace Culvert System | Near Gardena, at 0.2 mile south of Redondo Beach Boulevard. Replace culvert. | 1705 | 310 | 310 | 1325 | 1325 | 20 | 20 | 0 | 0 | 50 | 50 | 0 | 0 | 0 | 173 | 173 | 173 | 628 | 628 | 1323 | 4 | 4 | 11 | 0 | 0 | 1003 | 0 | 0 | 50 | 0 | 0 | 2820 | 2018-01-17 | 2019-02-28 | 2019-03-29 | 2020-03-13 |  |  | 2018-01-26 | 2019-02-06 | 2019-03-29 | [6 empty] | 2020-01-22 | 2021-07-14
314 | 07 | 4853 | LA | 5 | Bridge Paint | In the city of Los Angeles, at Sun Valley Overhead No. 53-1134. Paint bridge and replace deck drain systems. | 10949 | 500 | 500 | 1200 | 1200 | 200 | 200 | 1800 | 1800 | 49 | 49 | 7200 | 7200 | 0 | 302 | 302 | 302 | 400 | 400 | 1174 | 2 | 2 | 98 | 0 | 0 | 1710 | 5 | 5 | 262 | 0 | 0 | 7200 | 2017-10-31 | 2019-07-10 | 2019-08-20 | 2020-01-17 |  |  | 2017-11-30 | [6 empty] | 2020-04-01 | 2020-05-01 | 2020-09-14 | 2022-01-14
315 | 07 | 4887 | LA | 14 | Reconstruct Pavement Structure and Ramps | In and near Palmdale and Lancaster, from Avenue P-8 to the Kern County line. Replace distressed lanes/shoulders, cold plane and overlay ramps, upgrade guardrail, dikes, sign panels, curb ramps and traffic loop detectors. | 177150 | 3000 | 3000 | 21200 | 21200 | 280 | 280 | 25800 | 25800 | 210 | 210 | 126660 | 126660 | 0 | 1120 | 1120 | 1946 | 0 | 0 | 9381 | 0 | 0 | 201 | 0 | 0 | 16636 | 0 | 0 | 242 | 0 | 0 | 126660 | 2019-04-11 | 2020-09-02 | 2020-11-06 | 2021-02-24 | [8 empty] | 2019-07-31 | 2021-02-08 | 2021-03-15 | 2022-01-10 | 2023-08-23
316 | 07 | 4902 | LA | 10S | Deck Replacement 19/20 | In El Monte, at Rio Hondo Busway Bridge No. 53-2637. Replace bridge deck. (PA&ED only) | 550 | 550 | 550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 425 | 425 | 425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 335 | 0 | 0 | 2553 | 2018-09-28 | 2019-11-27 | 2019-12-30 | 2020-07-10 |  |  | 2019-05-01 | [6 empty] | 2022-12-01 | 2023-01-17 | 2023-07-24 | 2025-01-22
317 | 07 | 4910 | LA | 5 | Upgrade Pumps | In Los Angeles County, on Routes 5, 101, 405 and 710 at various locations. Replace 9 pump plants. | 4512 | 360 | 360 | 1038 | 1038 | 30 | 30 | 3074 | 3074 | 10 | 10 | 0 | 0 | 0 | 345 | 345 | 345 | 845 | 845 | 951 | 7 | 7 | 28 | 0 | 0 | 2438 | 0 | 0 | 16 | 0 | 0 | 8800 | 2017-12-01 | 2018-12-31 | 2019-01-30 | 2019-08-14 |  |  | 2017-12-07 | 2019-02-13 | 2019-03-29 | [6 empty] | 2020-03-30 | 2022-02-01
318 | 07 | 4915 | LA | 101 | Bridge Replacement | Near Encino, at Encino Pedestrian Overcrossing. Replace pedestrian overcrossing. | 19587 | 1033 | 1033 | 3726 | 3726 | 500 | 500 | 2442 | 2442 | 1067 | 1067 | 10819 | 10819 | 0 | 946 | 946 | 946 | 3069 | 3069 | 3700 | 193 | 193 | 492 | 0 | 0 | 2450 | 440 | 440 | 767 | 0 | 0 | 10819 | 2018-03-26 | 2019-02-21 | 2019-03-21 | 2019-09-19 |  |  | 2018-03-30 | 2019-06-18 | 2019-06-25 | [6 empty] | 2020-02-12 | 2022-01-20
319 | 07 | 4966 | LA | 10 | Strengthen Bridge | In the city of Los Angeles, at the Normandie Avenue Undercrossing Bridge No. 53-1565. Strengthen girders with epoxy and reinforcement steel. | 5532 | 508 | 508 | 1493 | 1493 | 80 | 80 | 1188 | 1188 | 10 | 10 | 2253 | 2253 | 0 | 57 | 57 | 507 | 0 | 0 | 1465 | 0 | 0 | 3 | 0 | 0 | 1141 | 0 | 0 | 15 | 0 | 0 | 2253 | 2020-07-15 | 2021-09-22 | 2021-10-21 | 2022-05-22 | [8 empty] | 2020-07-17 | 2021-10-08 | 2021-11-12 | 2022-05-20 | 2023-12-01
320 | 07 | 4967 | LA | 91 | Nickname Required | In Long Beach, at the eastbound Route 91 to northbound Route 710 Connector Bridge No. 53-2241G over connector from northbound Route 710 to eastbound Route 91. Lower profile of connector to achieve standard vertical clearance | 8764 | 910 | 910 | 2468 | 2468 | 43 | 43 | 2073 | 2073 | 40 | 40 | 3230 | 3230 | 0 | 161 | 161 | 885 | 0 | 0 | 2629 | 0 | 0 | 40 | 0 | 0 | 1942 | 0 | 0 | 36 | 0 | 0 | 3230 | 2019-10-15 | 2021-02-15 | 2021-03-15 | 2022-04-15 | [8 empty] | 2019-10-15 | 2021-02-12 | 2021-03-15 | 2022-04-15 | 2023-04-03
321 | 07 | 4972 | VEN | 1 | OH span replacement | Near the city of Ventura, at Ventura Overhead No. 52-0040. Replace corroded steel spans of bridge and upgrade bridge railing to current standards. | 10438 | 1200 | 1200 | 2500 | 2500 | 540 | 540 | 1650 | 1650 | 983 | 983 | 3565 | 3565 | 0 | 853 | 853 | 853 | 0 | 0 | 1985 | 0 | 0 | 638 | 0 | 0 | 2486 | 0 | 0 | 2009 | 0 | 0 | 10348 | 2018-12-14 | 2021-11-15 | 2021-12-15 | 2022-08-15 |  |  | 2019-06-26 | [6 empty] | 2021-11-15 | 2021-12-15 | 2022-08-15 | 2023-09-15
322 | 07 | 4979 | LA | 605 | Pavement Rehabiliation | In various cities, from Orange County line to Telegraph Road. Pavement rehabilitation consisting of full structural section replacement and damaged slab replacement. Cold plane and overlay Rubberized Hot Mix Asphalt (RHMA-G) on right shoulders and apply High Friction Surface Treatment (HFST) onramps and connectors. (G13 Contingency) | 10235 | 1960 | 1960 | 8100 | 8100 | 150 | 150 | 0 | 0 | 25 | 25 | 0 | 0 | 0 | 862 | 862 | 862 | 0 | 0 | 7293 | 0 | 0 | 154 | 0 | 0 | 14102 | 0 | 0 | 589 | 0 | 0 | 46000 | 2019-02-15 | 2021-10-15 | 2022-02-15 | 2022-11-15 |  |  | 2019-06-19 | [6 empty] | 2021-11-15 | 2021-12-30 | 2022-09-30 | 2025-07-30
323 | 07 | 4984 | LA | 405 | PSSR Bridge | In Long Beach, at the San Gabriel River Bridge No. 53-1185 and SB LA-605 to NB I-405 connector Bridge No. 53-1737H; also in Orange County on I-405 at the SB 405 to NB 605 connector Bridge No. 55-0413F; 12-Ora-405-PM 24.1. Retrofit scour critical bridges to preserve the structural integrity of the bridges by enlarging and deepening pile cap, adding Cast in Drilled Hole (CIDH) piles and reinforcing the area with Rock Slope Protection (RSP). | 31205 | 2140 | 2140 | 6840 | 6840 | 300 | 300 | 5840 | 5840 | 254 | 254 | 15831 | 15831 | 0 | 640 | 640 | 2131 | 0 | 0 | 6447 | 0 | 0 | 299 | 0 | 0 | 5608 | 4 | 4 | 254 | 0 | 0 | 15831 | 2019-09-15 | 2022-02-16 | 2022-03-20 | 2022-11-04 | [8 empty] | 2020-03-30 | 2022-02-16 | 2022-03-18 | 2023-02-01 | 2024-11-05
324 | 07 | 4998 | LA | 1 | Cold Plane and Overlay AC | In and near Redondo Beach, from Orange County line to south of Topaz Street. Upgrade Americans with Disabilities Act (ADA) curb ramps, upgrade metal beam guardrail, cold plane pavement, and place Hot Mix Asphalt (HMA) and Rubberized Hot Mix Asphalt (RHMA) pavement to rehabilitate pavement. | 55312 | 2048 | 2048 | 4886 | 4886 | 920 | 920 | 7684 | 7684 | 1554 | 1554 | 38220 | 38220 | 0 | 1112 | 1112 | 2215 | 0 | 0 | 4435 | 0 | 0 | 783 | 0 | 0 | 7283 | 0 | 0 | 1554 | 0 | 0 | 38220 | 2018-12-15 | 2022-02-26 | 2022-03-30 | 2022-11-06 | [8 empty] | 2020-07-31 | 2022-02-25 | 2022-03-30 | 2022-10-12 | 2024-07-17
325 | 07 | 5002 | LA | 110 | Bridge Rail Upgrade | In the city of Los Angeles, at the 5th Street Overcrossing No. 53-0685 and 6th Street Overcrossing No. 53-0746. Upgrade bridge railing. | 7597 | 712 | 712 | 1673 | 1673 | 30 | 30 | 1632 | 1632 | 30 | 30 | 3520 | 3520 | 0 | 299 | 299 | 688 | 0 | 0 | 1626 | 0 | 0 | 30 | 0 | 0 | 1563 | 0 | 0 | 10 | 0 | 0 | 3520 | 2019-02-21 | 2020-07-15 | 2020-08-26 | 2021-04-01 | [8 empty] | 2019-10-01 | 2021-03-15 | 2021-04-26 | 2021-07-31 | 2023-08-24
326 | 07 | 5003 | LA | 134 | Bridge Rail Upgrade | In Pasadena, at the Arroyo Seco Bridge No. 53-0166. Replace/upgrade bridge railing. | 14810 | 1300 | 1300 | 2500 | 2500 | 200 | 200 | 2860 | 2860 | 2530 | 2530 | 5420 | 5420 | 0 | 171 | 171 | 990 | 0 | 0 | 1997 | 0 | 0 | 155 | 0 | 0 | 2964 | 0 | 0 | 2527 | 0 | 0 | 5300 | 2019-09-20 | 2021-07-15 | 2021-12-30 | 2022-02-26 | [8 empty] | 2020-02-07 | 2021-08-30 | 2021-09-30 | 2022-02-25 | 2024-10-01
327 | 07 | 5004 | LA | 103 | Union Pacific OH Deck Rehabilitation | In the city of Los Angeles, at the Union Pacific Overhead No. 53-2626. Replace the bridge deck with composite reinforced concrete. | 22963 | 669 | 669 | 3482 | 3482 | 376 | 376 | 4228 | 4228 | 1730 | 1730 | 12478 | 12478 | 0 | 453 | 453 | 667 | 0 | 0 | 2630 | 0 | 0 | 357 | 0 | 0 | 4072 | 0 | 0 | 581 | 0 | 0 | 12478 | 2019-11-12 | 2021-12-31 | 2022-01-30 | 2022-08-28 | [8 empty] | 2019-11-12 | 2021-12-31 | 2022-01-28 | 2022-08-26 | 2024-08-27
328 | 07 | 5007 | LA | 27 | Overlay AC | In and near Canoga Park, from Pacific Coast Highway to Entrada Road; also near Woodland Crest Drive to near Devonshire Street (PM 10.11/18.62). Cold plane and overlay asphalt pavement, repair damaged structural and upgrade curb ramps to meet Americans with Disabilities Act (ADA) Standards. | 43163 | 1593 | 1593 | 4405 | 4405 | 576 | 576 | 5540 | 5540 | 499 | 499 | 30550 | 30550 | 0 | 276 | 276 | 1434 | 0 | 0 | 3895 | 0 | 0 | 448 | 0 | 0 | 4863 | 0 | 0 | 499 | 0 | 0 | 30550 | 2020-03-28 | 2021-09-21 | 2021-10-21 | 2022-07-01 | [8 empty] | 2020-03-27 | 2021-09-21 | 2021-10-21 | 2022-07-01 | 2024-01-05
329 | 07 | 5008 | VEN | 33 | Bridge Structure Painting | Near Ojai, at North Fork Matilija Creek No. 52-0173. Paint steel portion of bridge and replace missing rivets of bottom flanges for preventative maintenance to preserve and extend the life of bridge. | 2530 | 320 | 320 | 850 | 850 | 50 | 50 | 620 | 620 | 30 | 30 | 660 | 660 | 0 | 189 | 189 | 189 | 8 | 8 | 825 | 0 | 0 | 49 | 0 | 0 | 616 | 0 | 0 | 40 | 0 | 0 | 660 | 2018-12-15 | 2021-09-01 | 2021-10-31 | 2022-06-02 |  |  | 2018-12-28 | [6 empty] | 2021-04-30 | 2021-06-01 | 2021-12-31 | 2023-07-21
330 | 07 | 5013 | LA | 5 | I-5 Pavement Rehab | Near Castaic and Valencia, from 0.2 mile north of Lake Hughes Road Undercrossing to 0.7 mile south of Vista Del Lago Road Overcrossing. Cold plane pavement and place Rubberized Hot Mix Asphalt concrete (RHMA), repair drainage systems, and perform upgrades to overhead signs, drainage curbs and guardrail. | 56880 | 100 | 100 | 6000 | 6000 | 250 | 250 | 7200 | 7200 | 250 | 250 | 43080 | 43080 | 0 | 100 | 100 | 100 | 660 | 660 | 5679 | 17 | 17 | 219 | 0 | 0 | 6641 | 0 | 0 | 260 | 0 | 0 | 43080 | 2018-03-28 | 2020-12-30 | 2021-01-29 | 2021-02-26 |  | 2018-10-17 | 2018-03-28 | [6 empty] | 2020-11-06 | 2021-01-29 | 2021-09-01 | 2023-03-01
331 | 07 | 5014 | VEN | 150 | CapM | In and near Ojai, Mira Monte and Meiners Oaks, from Burham Road to Gorham Road; also on Route 33 from 33/150 Junction to Meiners Road. Cold plane and overlay pavement, upgrade guardrail and signs. | 9859 | 600 | 600 | 1500 | 1500 | 250 | 250 | 1700 | 1700 | 221 | 221 | 5588 | 5588 | 0 | 254 | 254 | 635 | 0 | 0 | 1429 | 0 | 0 | 192 | 0 | 0 | 1658 | 0 | 0 | 222 | 0 | 0 | 5588 | 2019-09-03 | 2020-08-05 | 2020-10-05 | 2021-04-08 | [8 empty] | 2019-09-03 | 2021-12-03 | 2022-01-04 | 2022-05-02 | 2023-12-01
332 | 07 | 5018 | VEN | 1 | PCH CAPM | In the city of Ventura, from North 101 Junction - Solimar Undercrossing to Hobson County Park Road. Cold plane and overlay pavement, upgrade guardrail/end treatment, install traffic signs and crosswalks. | 16099 | 625 | 625 | 1850 | 1850 | 60 | 60 | 3350 | 3350 | 14 | 14 | 10200 | 10200 | 0 | 74 | 74 | 609 | 0 | 0 | 1477 | 0 | 0 | 58 | 0 | 0 | 2481 | 0 | 0 | 15 | 0 | 0 | 10200 | 2020-07-15 | 2021-11-01 | 2021-12-15 | 2022-08-05 | [8 empty] | 2020-07-15 | 2021-11-01 | 2021-12-15 | 2022-08-05 | 2024-12-13
333 | 07 | 5022 | LA | 22 | Cold Plane and AC Overlay | In Long Beach, from Route 1 to San Gabriel Undercrossing. Cold plane pavement and overlay with Rubberized Hot Mixed Asphalt - Type G (RHMA-G), upgrade curb ramps to current Americans with Disabilities Act (ADA) Standards, install guardrail and construct bus pads. | 9674 | 670 | 670 | 2523 | 2523 | 12 | 12 | 1967 | 1967 | 126 | 126 | 4376 | 4376 | 0 | 149 | 149 | 664 | 0 | 0 | 2524 | 0 | 0 | 12 | 0 | 0 | 1676 | 0 | 0 | 126 | 0 | 0 | 4376 | 2019-09-15 | 2020-11-05 | 2020-12-15 | 2021-09-05 | [8 empty] | 2020-01-30 | 2020-11-05 | 2020-12-15 | 2021-09-03 | 2023-06-30
334 | 07 | 5024 | LA | 5 | Repair/upgrade pump stations | In various cities, on Route 5 (PM 19.75/35.99), Route 10 (PM 22.32/23.88), Route 91 (PM R11.80), Route 605 (PM R14.07) and Route 710 (PM 18.7/21.01). Replace pumps with submersible pumps. | 8472 | 254 | 254 | 1075 | 1075 | 73 | 73 | 1110 | 1110 | 14 | 14 | 5946 | 5946 | 0 | 54 | 54 | 247 | 0 | 0 | 855 | 0 | 0 | 31 | 0 | 0 | 956 | 0 | 0 | 76 | 0 | 0 | 5946 | 2019-12-01 | 2021-01-01 | 2021-02-28 | 2021-11-30 | [8 empty] | 2019-12-02 | 2020-12-31 | 2021-02-26 | 2021-11-30 | 2022-09-30
335 | 07 | 5026 | LA | 210 | Hinge and Diaphragm Repairs | In Irwindale, on the San Gabriel River Bridge No. 53-1867. Reconstruct hinge diaphragms at hinge 4 and hinge 6, upgrade bridge railing and reinstall electroliers. | 28707 | 1061 | 1061 | 3665 | 3665 | 444 | 444 | 4244 | 4244 | 596 | 596 | 18697 | 18697 | 0 | 234 | 234 | 873 | 0 | 0 | 2538 | 0 | 0 | 379 | 0 | 0 | 4446 | 0 | 0 | 596 | 0 | 0 | 18697 | 2019-10-04 | 2020-11-06 | 2021-01-06 | 2021-10-28 | [8 empty] | 2019-10-04 | 2020-12-07 | 2021-01-06 | 2021-10-28 | 2023-04-28
336 | 07 | 5029 | LA | 605 | Slab Replacement and Shoulder Resurfacing | In the cities of Irwindale and Baldwin Park, from Route 10 Interchange to the end of the freeway at Route 210. Grind mainline pavement and replace damaged stabs with Jointed Plain Concrete Pavement (JPCP) rapid strength concrete and/or Individual Precast Slab Replacement (IPSR), cold plane and overlay median, shoulders, ramps with Hot Mix Asphalt (HMA), construct additional lane on southbound Arrow Highway offramp/modify signal, install and upgrade guardrail. | 29857 | 1375 | 1375 | 6856 | 6856 | 138 | 138 | 4916 | 4916 | 162 | 162 | 16410 | 16410 | 0 | 826 | 826 | 826 | 0 | 0 | 4509 | 0 | 0 | 122 | 0 | 0 | 3508 | 0 | 0 | 161 | 0 | 0 | 16410 | 2018-12-01 | 2021-08-09 | 2021-11-08 | 2022-09-06 |  |  | 2018-12-06 | [6 empty] | 2021-10-08 | 2021-11-08 | 2022-09-06 | 2024-11-06
337 | 07 | 5032 | LA | 5 | Tejon Pass OC Bridge; Seismic Retrofit | Near Kern County line, at the Tejon Pass Overcrossing No. 53-1779. Seismic retrofit of bridge, widen bridge abutments, add steel casing to bent columns, retrofit bent foundation and install micro piles. | 5950 | 700 | 700 | 1500 | 1500 | 400 | 400 | 1500 | 1500 | 50 | 50 | 1800 | 1800 | 0 | 89 | 89 | 610 | 0 | 0 | 1386 | 0 | 0 | 355 | 0 | 0 | 1402 | 0 | 0 | 50 | 0 | 0 | 1800 | 2019-10-01 | 2021-06-15 | 2021-07-15 | 2022-01-05 | [8 empty] | 2020-01-15 | 2021-06-15 | 2021-07-15 | 2022-01-05 | 2022-12-15
338 | 07 | 5034 | LA | 1 | Cold Plane and Overlay AC | In and near Redondo Beach, from Topaz Street to Dewey Street. Upgrade Americans with Disabilities Act (ADA) curb ramps and metal beam guardrail, repair concrete pavement, replace asphalt concrete pavement with Portland Cement Concrete (PCC) at intersections, cold plane pavement, and place Hot Mix Asphalt (HMA) and Rubberized Hot Mix Asphalt (RHMA) pavement to rehabilitate pavement. | 66476 | 2356 | 2356 | 6770 | 6770 | 780 | 780 | 8770 | 8770 | 1900 | 1900 | 45900 | 45900 | 0 | 1424 | 1424 | 2687 | 0 | 0 | 6488 | 0 | 0 | 659 | 0 | 0 | 8064 | 0 | 0 | 1932 | 0 | 0 | 45900 | 2018-12-15 | 2022-02-26 | 2022-03-30 | 2022-12-01 | [8 empty] | 2020-07-31 | 2022-02-25 | 2022-03-30 | 2022-10-12 | 2024-07-17
339 | 07 | 5035 | LA | 138 | 39, 71, 138 Seismic Retrofit | In and near Palmdale, Azusa and Pomona, at the California Aqueduct Bridge No. 53-2174; also on Route 39, at the San Gabriel River Bridge No. 53-0113 (PM 17.81) and Route 71 at the Ridgeway Street Undercrossing Bridge No. 53-2052 (PM R0.92). Seismic retrofit, barrier replacement, paint San Gabriel River Bridge. | 31525 | 1372 | 1372 | 4549 | 4549 | 488 | 488 | 5686 | 5686 | 101 | 101 | 19329 | 19329 | 0 | 553 | 553 | 1359 | 0 | 0 | 3045 | 0 | 0 | 147 | 0 | 0 | 4653 | 0 | 0 | 102 | 0 | 0 | 19329 | 2019-08-01 | 2021-08-07 | 2021-10-03 | 2022-06-10 | [8 empty] | 2020-03-16 | 2021-10-04 | 2021-11-03 | 2022-06-10 | 2024-05-10
340 | 07 | 5040 | LA | 60 | Upgrade Transportation Management System | In and near the city of Los Angeles, from EB Route 60/5 Separation to Route 605; also on Route 2 (PM R18.7), Route 5 (PM 6.8), Route 10 (PM 18.3), and Route 605 (PM 20.2). Upgrade the existing Transportation Management System (TMS) elements to improve traffic monitoring, data transmission, and network connectivity including the Los Angeles Regional Transportation Management Center (LARTMC) on Route 2, Route 5, Route 10, and Route 605. | 9583 | 233 | 233 | 1028 | 1028 | 45 | 45 | 1450 | 1450 | 153 | 153 | 6674 | 6674 | 0 | 135 | 135 | 135 | 100 | 100 | 1294 | 0 | 0 | 15 | 0 | 0 | 1222 | 0 | 0 | 147 | 0 | 0 | 6674 | 2018-06-15 | 2020-08-21 | 2020-10-21 | 2021-05-22 |  |  | 2018-12-31 | [6 empty] | 2020-10-09 | 2020-11-05 | 2021-08-19 | 2023-03-20
341 | 07 | 5041 | LA | 1 | Upgrade TMS | In and near Santa Monica, from Lincoln Boulevard to McClure Tunnel; also on Route 10 (PM 2.1/18.3), Route 2 (PM R18.7), Route 101 (PM 11.8), and Route 105 (PM R1.95). Upgrade the existing Transportation Management System (TMS) elements to improve traffic monitoring, data transmission, and network connectivity including the Los Angeles Regional Transportation Management Center (LARTMC) and communication hubs at Route 10, Route 101 and Route 105. | 24616 | 539 | 539 | 3159 | 3159 | 43 | 43 | 3284 | 3284 | 327 | 327 | 17264 | 17264 | 0 | 110 | 110 | 110 | 383 | 383 | 3048 | 0 | 0 | 40 | 0 | 0 | 3124 | 0 | 0 | 327 | 0 | 0 | 17264 | 2018-12-15 | 2020-08-22 | 2020-10-15 | 2021-05-13 |  |  | 2018-12-31 | [6 empty] | 2020-08-21 | 2020-10-21 | 2021-05-21 | 2023-05-16
342 | 07 | 5043 | LA | 103 | New Pump Station | In Long Beach, at Henry Ford Avenue offramp. Construct larger pump plant facility including replacing undersized pumps. | 32397 | 1198 | 1198 | 2586 | 2586 | 420 | 420 | 3954 | 3954 | 1646 | 1646 | 22593 | 22593 | 0 | 359 | 359 | 1202 | 0 | 0 | 1950 | 0 | 0 | 178 | 0 | 0 | 3552 | 0 | 0 | 1647 | 0 | 0 | 22593 | 2019-12-31 | 2021-01-15 | 2021-03-30 | 2021-10-01 | [8 empty] | 2019-12-20 | 2020-12-01 | 2021-02-16 | 2022-02-28 | 2024-03-22
343 | 07 | 5067 | LA | 10 | San Gabriel Br OH | In the city of El Monte, from Baldwin Avenue Overcrossing to Route 605 at Rio Hondo Bridge No. 53-657, East El Monte Overhead No. 53-0867 and San Gabriel River Bridge No. 53-109L/R. Replace overhang joints with reinforced concrete closure pours. | 18583 | 813 | 813 | 3927 | 3927 | 915 | 915 | 3526 | 3526 | 1262 | 1262 | 8140 | 8140 | 0 | 216 | 216 | 805 | 0 | 0 | 3914 | 0 | 0 | 906 | 0 | 0 | 3516 | 0 | 0 | 1262 | 0 | 0 | 8140 | 2019-10-01 | 2022-01-03 | 2022-02-01 | 2022-09-25 | [8 empty] | 2020-01-07 | 2022-01-03 | 2022-02-01 | 2022-11-23 | 2024-10-31
344 | 07 | 5069 | LA | 105 | 105-replace joint seals | In the city of South Gate, at Paramount Boulevard Overcrossing No. 53-2425; also in the city of Downey, at Ardis Avenue Overcrossing No. 53-2572. Remove and install new joint assemblies, apply waterproof coating, replace joint seals and apply methacrylate to Ardis Avenue Overcrossing deck. | 3565 | 259 | 259 | 891 | 891 | 26 | 26 | 1022 | 1022 | 27 | 27 | 1340 | 1340 | 0 | 105 | 105 | 260 | 0 | 0 | 867 | 0 | 0 | 25 | 0 | 0 | 980 | 0 | 0 | 10 | 0 | 0 | 1340 | 2019-08-01 | 2020-10-01 | 2020-12-01 | 2021-07-30 | [8 empty] | 2019-09-20 | 2020-10-01 | 2020-12-01 | 2021-07-20 | 2023-04-28
345 | 07 | 5184 | LA | 2 | Route 2 Cold plane & Overlay | In and near the city of Los Angeles, from Centinela Avenue to Cotner Avenue, North La Brea Avenue to North Oxford Avenue and North Hollywood Boulevard to Allesandro Street. Cold plane and overlay pavement, upgrade curb ramps, reconstruct curb and gutter, construct bus pads and replace traffic signals at several locations. | 31908 | 1900 | 1900 | 5000 | 5000 | 160 | 160 | 5000 | 5000 | 38 | 38 | 19810 | 19810 | 0 | 312 | 312 | 1618 | 0 | 0 | 2820 | 0 | 0 | 2 | 0 | 0 | 4101 | 0 | 0 | 10 | 0 | 0 | 20000 | 2020-07-01 | 2022-01-05 | 2022-03-01 | 2022-12-01 | [8 empty] | 2020-07-01 | 2022-01-05 | 2022-02-23 | 2022-07-29 | 2023-12-29
346 | 07 | 5188 | LA | 110 | Bluetooth Detection System | In the cities of Los Angeles, Wilmington, and Carson, from Gaffey Street to Route 405; also on Route 210 (PM R0.0/R35.8), Route 605 (PM 19.9/26.0), Route 710 (PM 5.0/9.4) and Route 2 (PM R18.7). Install wireless Bluetooth? detection system to monitor travel time. | 2158 | 240 | 240 | 235 | 235 | 0 | 0 | 300 | 300 | 10 | 10 | 1373 | 1373 | 0 | 133 | 133 | 133 | 0 | 0 | 190 | 0 | 0 | 0 | 0 | 0 | 286 | 0 | 0 | 10 | 0 | 0 | 1373 | 2018-12-28 | 2020-07-21 | 2020-10-21 | 2021-04-22 |  |  | 2019-01-29 | [6 empty] | 2020-07-21 | 2020-10-21 | 2021-04-22 | 2022-10-21
347 | 07 | 5219 | LA | 14 | Rte 14 Drainage Culvert | In the City of Santa Clarita, near southbound offramp to Sierra Highway. Replace damaged drainage system that includes seventeen culverts. | 6451 | 556 | 556 | 1881 | 1881 | 23 | 23 | 1262 | 1262 | 10 | 10 | 2719 | 2719 | 0 | 397 | 397 | 397 | 236 | 236 | 1847 | 1 | 1 | 23 | 0 | 0 | 1198 | 0 | 0 | 10 | 0 | 0 | 2719 | 2018-07-13 | 2019-09-03 | 2019-10-01 | 2020-05-01 |  |  | 2018-10-15 | [6 empty] | 2019-12-09 | 2020-01-06 | 2020-09-15 | 2022-01-14
348 | 07 | 5221 | LA | 101 | LA-101 Upgrade CCTV/CMS | In various ciites, from Routes 5/10 to Route 405, Route 2 at Route 134 (PM R18.7) and Route 10 at Route 5/10 (PM 18.3). Upgrade Transportation Management System (TMS) elements including Closed Circuit Television (CCTV) cameras, Ramp Metering Systems (RMS), Vehicle Detection Stations (VDS), Highway Advisory Radio (HAR), Changeable Message Signs (CMS) and the communication system network. | 15202 | 438 | 438 | 3008 | 3008 | 162 | 162 | 1863 | 1863 | 13 | 13 | 9718 | 9718 | 0 | 320 | 320 | 320 | 17 | 17 | 2995 | 0 | 0 | 149 | 0 | 0 | 1775 | 0 | 0 | 218 | 0 | 0 | 9718 | 2018-07-15 | 2021-09-03 | 2022-01-03 | 2022-08-01 |  |  | 2019-02-28 | [6 empty] | 2021-09-03 | 2022-01-03 | 2022-08-01 | 2024-07-01
349 | 07 | 5222 | LA | 134 | LA-134 Upgrade TMS | In the city of Los Angeles, from Route 170 to Routes 210/710; also on Route 2 at Route 134 (PM R18.7), on Route 10 at Routes 5/10 (PM 18.3), and on Route 101 near Pleasant Valley Road (PM 11.8). Upgrade Transportation Management System (TMS) elements including Closed Circuit Television (CCTV) cameras, Ramp Metering Systems (RMS), Vehicle Detection Stations (VDS), Highway Advisory Radio (HAR), Changeable Message Signs (CMS) and the communication system network. | 12819 | 454 | 454 | 2840 | 2840 | 0 | 0 | 1953 | 1953 | 13 | 13 | 7559 | 7559 | 0 | 161 | 161 | 161 | 0 | 0 | 2828 | 0 | 0 | 134 | 0 | 0 | 1937 | 0 | 0 | 10 | 0 | 0 | 7559 | 2018-07-15 | 2021-08-03 | 2022-01-03 | 2022-08-01 |  |  | 2018-12-26 | [6 empty] | 2021-09-03 | 2022-01-03 | 2022-08-01 | 2024-07-01
350 | 07 | 5223 | LA | 5 | Culvert Repair | In the city of Los Angeles, on the northbound connector at the Route 5/110 Separation. Replace compromised 18 inch Reinforced Concrete Culvert (RCP). | 7506 | 709 | 709 | 2548 | 2548 | 123 | 123 | 2462 | 2462 | 10 | 10 | 1654 | 1654 | 0 | 434 | 434 | 434 | 430 | 430 | 2553 | 0 | 0 | 123 | 0 | 0 | 2413 | 0 | 0 | 10 | 0 | 0 | 1654 | 2018-07-15 | 2019-09-01 | 2019-10-01 | 2020-05-01 |  |  | 2018-11-21 | [6 empty] | 2020-02-14 | 2020-03-13 | 2020-11-16 | 2022-04-15
351 | 07 | 5226 | LA | 91 | Upgrade TMS | In and near Carson, from Route 110 to Orange County line; also on Route 2 (PM R18.7), Route 5 (PM 6.8), Route 405 (PM 21.1). Upgrade the existing Transportation Management System (TMS) elements to improve traffic monitoring, data transmission, and network connectivity including the various communication hubs on Route 2, Route 5, and Route 405. | 25167 | 511 | 511 | 3100 | 3100 | 150 | 150 | 4749 | 4749 | 267 | 267 | 16390 | 16390 | 0 | 259 | 259 | 259 | 0 | 0 | 2935 | 0 | 0 | 11 | 0 | 0 | 3578 | 0 | 0 | 266 | 0 | 0 | 16390 | 2018-12-12 | 2021-08-03 | 2022-01-03 | 2022-08-01 |  |  | 2018-12-28 | [6 empty] | 2022-01-14 | 2022-03-01 | 2023-01-13 | 2025-03-14
352 | 07 | 5281 | LA | 5 | I-5 Freight Corridor | In Los Angeles County, at various locations. Establish standard vertical clearance. ACCELERATED BRIDGE (PA&ED Only) | 15640 | 15640 | 15640 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8621 | 8621 | 8621 | 0 | 0 | 11468 | 0 | 0 | 4470 | 0 | 0 | 29989 | 2 | 2 | 127262 | 0 | 0 | 123986 | 2019-04-18 | 2020-02-28 | 2020-03-30 | 2020-10-30 |  |  | 2019-06-28 | [6 empty] | 2022-10-18 | 2022-11-15 | 2023-06-06 | 2027-06-15
353 | 07 | 5297 | LA | 60 | Freight Corridor Improvements on LA-60 | In the City of Industry at Hacienda Boulevard Undercrossing (UC) No. 53-1789 (PM 15.93), Stemson Avenue UC No. 53-1784 (PM 16.30), Azusa Avenue Overcrossing No. 53-1785 (PM 17.97) and Fullerton Road UC No. 53-1786 (PM 19.46). Improve freight corridor movement by modifying and replacing bridges to meet vertical clearance and load carrying capacity standards. ACCELERATED BRIDGE (PA&ED Only) | 3320 | 3320 | 3320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1332 | 1332 | 1332 | 0 | 0 | 2010 | 0 | 0 | 122 | 0 | 0 | 2451 | 0 | 0 | 106 | 0 | 0 | 16000 | 2019-10-31 | 2020-05-29 | 2020-06-30 | 2021-07-30 |  |  | 2019-06-27 | [6 empty] | 2023-10-30 | 2023-11-30 | 2024-07-30 | 2026-07-30
354 | 07 | 5298 | LA | 39 | LA-39/ N. Fork San Gabriel Bridge Replacement | Near Azusa, at the North Fork San Gabriel River Bridge No. 53-2245. Replace bridge. | 6436 | 0 | 0 | 1930 | 1930 | 20 | 20 | 4476 | 4476 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 906 | 906 | 1084 | 8 | 8 | 21 | 0 | 0 | 3549 | 0 | 0 | 10 | 0 | 0 | 11742 | 2017-09-20 | 2019-03-01 | 2019-04-01 | 2019-08-01 |  | 2018-10-17 | 2017-09-20 | 2019-02-26 | 2019-04-19 | [6 empty] | 2019-12-16 | 2021-12-01
355 | 08 | 0023C | RIV | 62 | RIV 62 MILL & OVERLAY | In and near Yucca Valley and Twentynine Palms, from north of Indian Avenue to Utah Trail; also in San Bernardino County (PM 0.0/15.1 and PM 29.3/33.6). Pavement rehabilitation. (G13 Contingency) | 9080 | 1450 | 1450 | 4000 | 4000 | 1421 | 1421 | 0 | 0 | 2209 | 2209 | 0 | 0 | 0 | 1571 | 1571 | 1571 | 3293 | 3293 | 4008 | 1421 | 1421 | 1427 | 0 | 0 | 4658 | 255 | 255 | 2060 | 0 | 0 | 34511 | 2016-06-28 | 2019-12-16 | 2020-03-16 | 2021-01-15 |  | 2018-10-17 | 2016-06-28 | [6 empty] | 2020-01-02 | 2020-03-02 | 2021-01-15 | 2022-03-15
356 | 08 | 0046J | RIV | 060 | SR60 Truck Climbing/ Descending Lanes | IN RIVERSIDE COUNTY NEAR BEAUMONT ON RTE 60 FROM GILMAN SPRINGS RD TO 1.37 MILES W/O JACK RABBIT TRAIL. CONSTRUCT A TRUCK CLIMBING LANE (E/B) AND TRUCK DESCENDING LANE (W/B) WITH STANDARD INSIDE & OUTSIDE SHOULDERS BOTH DIRECTIONS CONSTRUCT A TRUCK CLIMBING LANE (E/B) AND TRUCK DESCENDING LANE (W/B) WITH STANDARD INSIDE & OUTSIDE SHOULDERS BOTH DIRECTIONS | 50810 | 13880 | 4604 | 12300 | 1500 | 200 | 200 | 3700 | 3700 | 2853 | 806 | 118640 | 40000 | 0 | 8002 | 2331 | 8002 | 3901 | 900 | 3901 | 0 | 0 | 169 | 0 | 0 | 16797 | 106 | 6 | 100 | 0 | 0 | 96385 | [6 empty] | 2016-05-16 | 2018-06-11 | 2018-08-15 | 2019-01-25 | [6 empty] | 2022-11-15
357 | 08 | 0066Q | RIV | 79 | RIV-79 NEAR TEMECULA MILL & OVERLAY | Near Temecula, from San Diego County line to Temecula city limits. Pavement rehabilitation. | 11417 | 1133 | 1133 | 926 | 926 | 17 | 17 | 800 | 800 | 10 | 10 | 8531 | 8531 | 0 | 699 | 699 | 699 | 832 | 832 | 924 | 12 | 12 | 13 | 0 | 0 | 744 | 0 | 0 | 10 | 0 | 0 | 8531 | 2018-05-15 | 2019-04-12 | 2019-05-10 | 2020-02-14 |  |  | 2018-06-27 | 2019-04-03 | 2019-05-06 | [6 empty] | 2019-12-04 | 2020-10-30
358 | 08 | 0181J | SBD | 18 | SBD 18 CULVERTS | Near Big Bear and Lucerne Valley, at various locations, from Route 38 at Big Bear Lake Dam to Artic Canyon Wash. Reline or replace culverts. | 11617 | 1192 | 1192 | 1493 | 1493 | 2708 | 2708 | 1417 | 1417 | 700 | 700 | 4107 | 4107 | 0 | 364 | 364 | 1142 | 0 | 0 | 1332 | 0 | 0 | 1796 | 0 | 0 | 1260 | 0 | 0 | 700 | 0 | 0 | 3770 | 2020-07-05 | 2021-12-01 | 2022-01-18 | 2022-07-15 | [8 empty] | 2020-07-01 | 2021-12-01 | 2022-01-18 | 2022-10-03 | 2023-12-01
359 | 08 | 0184C | SBD | 18 | SBD 18 RELINE OR REPLACE CULVERTS | In and near Arrowhead, from 48th Street to Route 138. Repair, reline and replace culverts. | 11975 | 1016 | 1016 | 1090 | 1090 | 1240 | 1240 | 1059 | 1059 | 385 | 385 | 7185 | 7185 | 0 | 611 | 611 | 1045 | 0 | 0 | 1050 | 0 | 0 | 862 | 0 | 0 | 996 | 0 | 0 | 385 | 0 | 0 | 3671 | 2020-05-01 | 2022-02-15 | 2022-05-02 | 2023-01-17 | [8 empty] | 2020-03-16 | 2021-12-01 | 2022-01-14 | 2022-08-15 | 2023-02-15
360 | 08 | 0205C | SBD | 38 | SBd 38 Replace Culverts | Near Big Bear Lake, from Zaca Road to Route 18. Replace culverts. | 10889 | 860 | 860 | 1730 | 1730 | 2822 | 2822 | 1029 | 1029 | 868 | 868 | 3580 | 3580 | 0 | 812 | 812 | 812 | 870 | 870 | 1727 | 691 | 691 | 2632 | 0 | 0 | 925 | 12 | 12 | 868 | 0 | 0 | 3285 | 2018-10-17 | 2020-03-02 | 2020-03-16 | 2020-09-15 |  |  | 2018-10-30 | [6 empty] | 2020-06-03 | 2020-06-10 | 2021-03-01 | 2023-08-01
361 | 08 | 3002C | RIV | 74 | RIV 74/79/371 UPGRADE TO STANDARD BRIDGE RAIL | In and near the cities of Lake Elsinore, Perris, Menifee and Hemet, at Leach Canyon Channel Bridge No. 56-0750 and Blue Ridge Wash Bridge No. 56-0257; also on Routes 79 and 371, at Arroyo Seco Bridge No. 56-0189, and Cahuilla Bridge No. 56-0490. Bridge rail replacement, replace one bridges, and extend one culvert. | 13406 | 1031 | 1031 | 2700 | 2700 | 80 | 80 | 2800 | 2800 | 550 | 550 | 6245 | 6245 | 0 | 1047 | 1047 | 1047 | 944 | 944 | 2601 | 11 | 11 | 53 | 0 | 0 | 2498 | 1 | 1 | 553 | 0 | 0 | 6638 | 2018-04-02 | 2019-06-03 | 2019-08-01 | 2020-03-02 |  |  | 2019-06-28 | [6 empty] | 2020-04-01 | 2020-05-01 | 2021-01-04 | 2022-01-03
362 | 08 | 3002F | RIV | 10 | RIV 10 REHAB SUBSTRUCTURE | Near Palm Springs, at Whitewater River Bridge No. 56-0004 L/R. Bridge rehabilitation and scour mitigation. | 18866 | 1218 | 1218 | 1916 | 1916 | 138 | 138 | 2300 | 2300 | 895 | 895 | 12399 | 12399 | 0 | 1144 | 1144 | 1144 | 1051 | 1051 | 1549 | 90 | 90 | 171 | 0 | 0 | 2675 | 132 | 132 | 895 | 0 | 0 | 14178 | 2018-05-02 | 2019-06-03 | 2019-06-18 | 2020-01-21 |  |  | 2018-06-18 | 2019-05-09 | 2019-06-20 | [6 empty] | 2020-02-21 | 2021-11-15
363 | 08 | 3002G | RIV | 10 | RIV 10 METHACRYLATE DECKS (VARIOUS ROUTES) | In Riverside County, on Routes 10 and 91, at various locations; also in San Bernardino County, on Routes 10 and 15, at various locations. Repair bridge decks. | 2725 | 350 | 350 | 760 | 760 | 50 | 50 | 660 | 660 | 30 | 30 | 875 | 875 | 875 | 313 | 313 | 313 | 667 | 667 | 667 | 20 | 20 | 27 | 27 | 27 | 632 | 7 | 7 | 40 | 0 | 0 | 875 | 2017-10-31 | 2018-06-20 | 2018-08-03 | 2019-04-30 |  |  | 2017-11-02 | 2018-07-18 | 2018-11-27 | 2019-05-01 | [6 empty] | 2019-10-24
364 | 08 | 3002S | SBD | 215 | WASHINGTON BR. - SBD 215 | In Colton, from 0.3 mile south to 0.3 mile north of Washington Street Overcrossing No. 54-0530. Replace Overcrossing. | 33048 | 1438 | 1438 | 3894 | 3894 | 864 | 664 | 4300 | 4300 | 4357 | 4357 | 20606 | 18395 | 0 | 1393 | 1393 | 1393 | 2079 | 2079 | 3587 | 688 | 620 | 761 | 0 | 0 | 3722 | 64 | 64 | 4367 | 0 | 0 | 17673 | 2018-04-18 | 2020-01-21 | 2020-02-03 | 2020-10-01 |  | 2018-10-17 | 2018-04-18 | [6 empty] | 2020-05-04 | 2020-06-01 | 2021-01-04 | 2022-10-03
365 | 08 | 3002V | SBD | 95 | SBD 95 Roadway Rehabilitation | Near Needles, from Route 62 to south of Havasu Lake Road. Rehabilitate pavement. | 12564 | 672 | 672 | 640 | 640 | 85 | 85 | 1500 | 1500 | 100 | 100 | 9567 | 9567 | 0 | 468 | 468 | 468 | 387 | 387 | 637 | 6 | 6 | 68 | 0 | 0 | 1732 | 39 | 39 | 20 | 0 | 0 | 9466 | 2018-05-04 | 2020-01-07 | 2020-02-21 | 2020-10-26 |  |  | 2018-05-18 | [6 empty] | 2019-10-01 | 2020-01-03 | 2020-07-31 | 2021-11-23
366 | 08 | 3003K | RIV | 15 | Temecula Lane Replacement | In and near Temecula, in Riverside County, from the San Diego county line to north of Temecula River Bridge; also in San Diego County from 0.1 mile south of the Riverside County line to the Riverside County line. Rehabilitate roadway. | 42985 | 1364 | 1364 | 1520 | 1520 | 20 | 20 | 5181 | 5181 | 10 | 10 | 34890 | 34890 | 0 | 962 | 962 | 962 | 1402 | 1402 | 1525 | 18 | 18 | 22 | 0 | 0 | 4378 | 0 | 0 | 10 | 0 | 0 | 36130 | 2018-03-23 | 2019-04-02 | 2019-08-06 | 2020-01-22 |  | 2018-10-17 | 2018-03-23 | 2019-02-22 | 2019-06-21 | [6 empty] | 2020-03-03 | 2021-12-03
367 | 08 | 3003L | RIV | 15 | RIV 015 Slab Replacement | In and near Lake Elsinore, from Nichols Road to 0.1 mile north of Temescal Canyon Road. Concrete pavement slab replacement. | 27730 | 1108 | 1108 | 926 | 926 | 20 | 20 | 3666 | 3666 | 10 | 10 | 22000 | 22000 | 0 | 763 | 763 | 763 | 853 | 853 | 904 | 12 | 12 | 12 | 0 | 0 | 3637 | 0 | 0 | 10 | 0 | 0 | 22000 | 2017-11-08 | 2019-02-01 | 2019-03-04 | 2020-01-15 |  | 2018-10-17 | 2017-11-08 | 2018-12-17 | 2019-03-04 | [6 empty] | 2019-11-15 | 2021-11-15
368 | 08 | 3003M | RIV | 15 | RIV 015 Bridge Maintenance | In and near Corona, from south of Ontario Avenue to Route 60. Concrete pavement slab replacement. | 47424 | 1022 | 1022 | 1066 | 1066 | 10 | 10 | 5250 | 5250 | 36 | 36 | 40040 | 40040 | 0 | 848 | 848 | 848 | 283 | 283 | 1128 | 9 | 9 | 15 | 0 | 0 | 4481 | 0 | 0 | 36 | 0 | 0 | 25190 | 2018-04-13 | 2020-01-03 | 2020-03-02 | 2021-01-15 |  | 2018-10-17 | 2018-04-13 | [6 empty] | 2020-01-03 | 2020-03-02 | 2021-01-15 | 2022-07-01
369 | 08 | 3003T | SBD | 15 | SBD 15 REHAB | In and near Fontana and Rialto, from Sierra Avenue to Glen Helen Parkway. Rehabilitate roadway. | 30980 | 827 | 827 | 1190 | 1190 | 30 | 30 | 2850 | 2850 | 10 | 10 | 26073 | 26073 | 0 | 751 | 751 | 751 | 1122 | 1122 | 1174 | 23 | 23 | 30 | 0 | 0 | 2695 | 0 | 0 | 10 | 0 | 0 | 25050 | 2018-01-23 | 2019-02-01 | 2019-03-01 | 2019-12-03 |  | 2018-10-17 | 2018-01-23 | 2018-12-20 | 2019-06-17 | [6 empty] | 2020-04-01 | 2021-06-01
370 | 08 | 3003U | SBD | 15 | SBD 15 REHAB (G-13) | In Hesperia and Victorville, from Oak Hill Road to south of Bear Valley Road. Rehabilitate roadway. (G13 Contingency) | 6862 | 1190 | 1190 | 5300 | 5300 | 210 | 210 | 0 | 0 | 162 | 162 | 0 | 0 | 0 | 1175 | 1175 | 1175 | 2494 | 2494 | 4898 | 98 | 98 | 185 | 0 | 0 | 14888 | 1 | 1 | 283 | 0 | 0 | 137054 | 2018-05-17 | 2019-11-04 | 2020-02-03 | 2020-10-29 |  | 2018-10-17 | 2018-05-17 | [6 empty] | 2020-01-30 | 2020-02-03 | 2021-03-05 | 2023-09-08
371 | 08 | 3003V | SBD | 15 | SBD 15 REHABILITATE EXISTING MAINLINE AND RAMP PAVEMENT | In Barstow, from Outlet Center Drive to Mojave River Bridge. Rehabilitate pavement. | 31058 | 600 | 600 | 1520 | 1520 | 30 | 30 | 2100 | 2100 | 10 | 10 | 26798 | 26798 | 0 | 525 | 525 | 525 | 1353 | 1353 | 1591 | 16 | 16 | 40 | 0 | 0 | 1870 | 0 | 0 | 23 | 0 | 0 | 24337 | 2017-09-14 | 2019-08-09 | 2019-10-02 | 2020-08-03 |  | 2018-10-17 | 2017-09-14 | [6 empty] | 2019-11-14 | 2019-12-02 | 2020-09-29 | 2021-10-04
372 | 08 | 3003X | SBD | 210 | SBD 210 INSTALL RAMP METERING SYSTEMS | In Rancho Cucamonga and Fontana, from East Avenue to 0.2 mile west of Beech Avenue; also on Route 15, at Route 210/15 Separation. Install Transportation Management System (TMS) elements. | 4827 | 410 | 410 | 649 | 649 | 70 | 70 | 526 | 526 | 19 | 19 | 3153 | 3153 | 0 | 396 | 396 | 396 | 604 | 604 | 654 | 34 | 34 | 52 | 0 | 0 | 700 | 0 | 0 | 19 | 0 | 0 | 3153 | 2017-10-27 | 2019-02-26 | 2019-03-15 | 2019-10-15 |  |  | 2018-01-08 | 2019-01-08 | 2019-04-30 | [6 empty] | 2019-12-11 | 2020-12-31
373 | 08 | 3003Y | SBD | 95 | SBD 95 Roadway Rehabilitation | Near Needles, from Goffs Road to Nevada State line. Rehabilitate pavement. | 9282 | 738 | 738 | 650 | 650 | 95 | 95 | 910 | 910 | 100 | 100 | 6789 | 6789 | 0 | 725 | 725 | 725 | 512 | 512 | 733 | 6 | 6 | 69 | 0 | 0 | 988 | 38 | 38 | 20 | 0 | 0 | 7225 | 2018-05-04 | 2020-01-07 | 2020-02-21 | 2020-10-26 |  |  | 2018-05-18 | [6 empty] | 2019-11-07 | 2019-12-03 | 2020-07-01 | 2021-11-29
374 | 08 | 3004A | SBD | 62 | SBD 62 Roadway Rehabilitation | Near Vidal, from 3.8 miles west of Route 95 to Arizona State line. Rehabilitate pavement and upgrade guardrail. | 16066 | 855 | 855 | 1050 | 1050 | 87 | 87 | 2660 | 2660 | 100 | 100 | 11314 | 11314 | 0 | 818 | 818 | 818 | 434 | 434 | 881 | 7 | 7 | 52 | 0 | 0 | 2375 | 37 | 37 | 100 | 0 | 0 | 9570 | 2018-05-04 | 2020-01-07 | 2020-02-21 | 2020-10-26 |  |  | 2018-06-12 | [6 empty] | 2019-10-01 | 2020-01-03 | 2020-07-31 | 2021-10-25
375 | 08 | 3005Q | RIV | 74 | RIV 74 REPLACE BRIDGES/UPGRADE RAIL | Near Lake Elsinore, at Morrill Canyon Bridge No. 56-0169; also near Hemet, at Strawberry Creek Bridge No. 56-0180 (PM 53.4/54.7). Replace structures/upgrade rails. | 13002 | 1690 | 1690 | 1295 | 1295 | 150 | 150 | 2390 | 2390 | 653 | 653 | 6824 | 6824 | 0 | 607 | 607 | 1643 | 0 | 0 | 1483 | 0 | 0 | 43 | 0 | 0 | 1119 | 0 | 0 | 653 | 0 | 0 | 9502 | 2021-02-22 | 2022-02-28 | 2022-03-30 | 2022-11-30 | [8 empty] | 2021-03-01 | 2022-03-01 | 2022-04-01 | 2022-12-01 | 2024-12-02
376 | 08 | 3006C | SBD | 18 | SBD 18/10/215 BRIDGE REHAB | In Victorville, at Mojave River Bridge No. 54-0307; also on Route 10, at Colton Overhead No. 54-0464R (PM R22.36); and Route 215 North/Route 10 East Connector Overhead No. 54-0482G (PM 3.72). Various repairs to three bridges. | 4591 | 320 | 320 | 780 | 780 | 100 | 100 | 690 | 690 | 62 | 62 | 2639 | 2639 | 0 | 157 | 157 | 384 | 0 | 0 | 660 | 0 | 0 | 33 | 0 | 0 | 704 | 0 | 0 | 62 | 0 | 0 | 806 | 2020-03-06 | 2021-09-17 | 2021-10-15 | 2022-04-29 | [8 empty] | 2020-04-02 | 2021-10-15 | 2021-11-16 | 2022-07-15 | 2023-02-15
377 | 08 | 3006W | RIV | Var | RIV/SBD REPAIR DETECTION SITES | In Riverside and San Bernardino Counties, on various routes and at various locations. Repair and replace vehicle detection equipment impacting the operations of the District Transportation Management Center (TMC). | 7847 | 346 | 346 | 1000 | 1000 | 90 | 90 | 1401 | 1401 | 10 | 10 | 5000 | 5000 | 4999 | 126 | 126 | 126 | 574 | 574 | 574 | 15 | 15 | 86 | 9 | 9 | 1134 | 0 | 0 | 10 | 99 | 99 | 5000 | 2018-02-15 | 2018-09-14 | 2018-10-15 | 2019-06-14 |  |  | 2018-02-13 | 2018-08-27 | 2018-10-01 | 2019-05-28 | [6 empty] | 2020-12-02
378 | 08 | 3007M | SBD | 18 | SBD 18 PAVEMENT PRESERVATION | In and near Adelanto, from Route 395 Junction to Los Angeles County line. Cold plane pavement and place Hot Mix Asphalt (HMA) and Rubberized Hot Mix Asphalt (RHMA) pavement. | 21202 | 664 | 664 | 1588 | 1588 | 77 | 77 | 2366 | 2366 | 65 | 65 | 16442 | 16442 | 0 | 463 | 463 | 602 | 0 | 0 | 1158 | 0 | 0 | 59 | 0 | 0 | 1638 | 0 | 0 | 65 | 0 | 0 | 13657 | 2019-07-15 | 2020-11-16 | 2021-02-16 | 2021-10-15 | [8 empty] | 2019-11-01 | 2020-10-01 | 2021-01-04 | 2021-09-01 | 2022-09-01
379 | 08 | 3007S | SBD | 215 | SBD 215/259 INSTALL TMS FIELD ELEMENTS | In and near the city of San Bernardino, from Route 215/10 Connector to Route 215/15 Junction; also on Route 259, from Route 259/215 Separation to Route 259/210 Junction. Install wireless Vehicle Detection Stations (VDS), Changeable Message Signs (CMS), Closed Circuit Television (CCTV) and Fiber Optic elements. | 12624 | 436 | 436 | 968 | 968 | 42 | 42 | 1930 | 1930 | 10 | 10 | 9238 | 9238 | 0 | 388 | 388 | 388 | 198 | 198 | 884 | 0 | 0 | 40 | 0 | 0 | 1921 | 0 | 0 | 10 | 0 | 0 | 9205 | 2019-02-01 | 2020-05-01 | 2020-06-01 | 2021-02-01 |  |  | 2019-02-28 | [6 empty] | 2020-03-01 | 2020-04-02 | 2020-12-02 | 2021-08-26
380 | 08 | 3008A | RIV | 10 | Riv 10 Blythe Pavement Rehab: mainline, shoulders, ramps | In and near Coachella, from 0.5 mile east of Coachella Canal to Hazy Gulch Bridge. Cold plane pavement and overlay with Portland Cement Concrete (PCC). Construct eastbound truck climbing lane. A one-lane temporary detour will be constructed in the median for traffic handling. (G13 Contingency) | 22900 | 7000 | 7000 | 15800 | 15800 | 90 | 90 | 0 | 0 | 10 | 10 | 0 | 0 | 0 | 2238 | 2238 | 6605 | 0 | 0 | 10536 | 0 | 0 | 79 | 0 | 0 | 19943 | 0 | 0 | 10 | 0 | 0 | 181000 | 2020-08-28 | 2022-04-22 | 2022-05-27 | 2013-01-13 | [8 empty] | 2020-09-02 | 2021-10-07 | 2022-03-03 | 2022-07-05 | 2025-07-08
381 | 08 | 3008K | SBD | 40 | SBD 40 BRIDGE SCOUR MITIGATION | Near Needles, at the Halfway Hills Wash Bridge No. 54-0799L/R. Retrofit bridge footings, replace and expand Rock Slope Protection (RSP) limits. | 15571 | 1393 | 1393 | 1903 | 1903 | 55 | 55 | 2538 | 2538 | 30 | 30 | 9652 | 9652 | 0 | 464 | 464 | 1436 | 0 | 0 | 1343 | 0 | 0 | 45 | 0 | 0 | 2179 | 0 | 0 | 30 | 0 | 0 | 13113 | 2020-09-14 | 2022-02-22 | 2022-03-15 | 2022-11-02 | [8 empty] | 2020-10-01 | 2022-03-01 | 2022-04-01 | 2022-11-02 | 2023-11-02
382 | 08 | 3008N | RIV | 10 | RIV 10 REPLACE EXISTING ROCK SLOPE PROTECTION | Near Desert Center, from Krume Ditch to Wide Ditch. Replace existing Rock Slope Protection (RSP) to prevent further scour damage and preserve the integrity of twenty-four bridges. | 16736 | 967 | 967 | 1232 | 1232 | 259 | 259 | 3648 | 3648 | 190 | 190 | 10440 | 10440 | 0 | 611 | 611 | 1118 | 0 | 0 | 1117 | 0 | 0 | 161 | 0 | 0 | 3402 | 0 | 0 | 353 | 0 | 0 | 14487 | 2020-09-23 | 2022-02-16 | 2022-03-16 | 2022-11-04 | [8 empty] | 2020-09-23 | 2022-02-16 | 2022-03-16 | 2022-11-04 | 2023-12-20
383 | 08 | 3008Y | RIV | 10 | Riv 10 Blythe Pavement Rehab: mainline, shoulders, ramps | Near Blythe, from west of Rice Road/SR-177 to east of Teed Ditch Bridge. Cold plane mainline pavement and overlay with Portland Cement Concrete (PCC). The shoulders and ramps will be milled and overlaid with Hot Mix Asphalt (HMA-A). (G13 Contingency) | 28063 | 16900 | 16900 | 2000 | 2000 | 153 | 153 | 0 | 0 | 9010 | 9010 | 0 | 0 | 0 | 4460 | 4460 | 14654 | 0 | 0 | 1866 | 0 | 0 | 104 | 0 | 0 | 32426 | 32 | 32 | 10 | 0 | 0 | 263010 | 2019-06-28 | 2020-04-24 | 2020-05-29 | 2021-01-15 | [8 empty] | 2020-02-03 | 2020-05-01 | 2020-06-01 | 2021-05-03 | 2024-05-01
384 | 08 | 3009A | SBD | 10 | SBD 10 INSTALL TMS ELEMENTS | In and near Redlands, from Route 210/10 Junction to the Riverside County line. Install wireless Vehicle Detection Stations (VDS) pole, Changeable Message Signs (CMS), Closed Circuit Television (CCTV), Data Node Cabinet and Fiber Optic elements. | 10597 | 300 | 300 | 1000 | 1000 | 33 | 33 | 1600 | 1600 | 10 | 10 | 7654 | 7654 | 0 | 234 | 234 | 234 | 692 | 692 | 1045 | 24 | 24 | 31 | 0 | 0 | 1585 | 0 | 0 | 60 | 0 | 0 | 8722 | 2018-06-01 | 2019-05-01 | 2019-06-03 | 2019-11-01 |  |  | 2018-06-18 | 2019-02-19 | 2019-06-12 | [6 empty] | 2020-02-02 | 2021-06-01
385 | 08 | 3009K | RIV | 10 | Riv 10 Blythe Pavement Rehab: mainline, shoulders, ramps | In and near Blythe, from Teed Ditch Bridge to Arizona State line. Cold plane mainline pavement and overlay with Portland Cement Concrete (PCC). The shoulders and ramps will be milled and overlaid with Hot Mix Asphalt (HMA-A). A two lane temporary detour will be constructed in the median for traffic handling. (G13 Contingency) | 30127 | 9000 | 9000 | 21000 | 21000 | 117 | 117 | 0 | 0 | 10 | 10 | 0 | 0 | 0 | 3167 | 3167 | 9352 | 0 | 0 | 19784 | 0 | 0 | 101 | 0 | 0 | 18936 | 0 | 0 | 5047 | 0 | 0 | 168000 | 2020-08-28 | 2022-04-22 | 2022-05-27 | 2023-01-10 | [8 empty] | 2020-08-03 | 2022-04-01 | 2022-05-02 | 2023-04-03 | 2026-04-01
386 | 08 | 3009N | SBD | 71 | SBD 71 INSTALL, CCTV, CMS, VDS & FIBER OPTIC COMM SYS | Near Chino Hills, from the Los Angeles County line to the Riverside County line (PM 8.478); also in Riverside County, from San Bernardino County line to Route 91 (PM R0.0 to PM R3.0). Replace and upgrade existing communication elements and install Closed Circuit Television Cameras (CCTV) for the Traffic Management System (TMS). | 15112 | 561 | 561 | 1515 | 1515 | 113 | 113 | 1657 | 1657 | 99 | 99 | 11167 | 11167 | 0 | 414 | 414 | 414 | 492 | 492 | 1274 | 4 | 4 | 99 | 0 | 0 | 1733 | 0 | 0 | 73 | 0 | 0 | 8260 | 2018-12-03 | 2020-01-06 | 2020-05-01 | 2021-01-05 |  |  | 2018-12-14 | [6 empty] | 2020-01-06 | 2020-05-01 | 2021-01-19 | 2022-10-18
387 | 08 | 3009R | SBD | 10 | SBD/RIV EXPAND MULTI-MODAL FREIGHT MOVEMENT | In San Bernardino County, at the Etiwanda San Sevain FCC Br. No. 54-0454L, Colton Overhead No. 54-0464R; also on Route 60, at Ramona Avenue Overcrossing No. 54-0745 (PM R1.37). In Riverside County, on Route 10 at Highland Springs Avenue Undercrossing No. 56-0432 (PM 9.3) and at Eagle Mountain Road Bridge No. 56-0575L/R (PM R102.0). Improve freight corridor movement by modifying and replacing bridges to meet vertical clearance and load-carrying capacity standards. ACCELERATED BRIDGE (PA&ED Only) | 5857 | 5822 | 5822 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 35 | 0 | 0 | 0 | 1116 | 1116 | 2108 | 0 | 0 | 2709 | 0 | 0 | 220 | 0 | 0 | 5623 | 3 | 3 | 1234 | 0 | 0 | 53740 | 2019-12-11 | 2021-02-12 | 2021-03-10 | 2022-01-05 | [8 empty] | 2019-11-08 | 2021-02-12 | 2021-03-10 | 2022-03-25 | 2024-03-12
388 | 09 | 0653 | INY | 178 | Shoshone Drainage | Near Shoshone, at 0.5 mile east of Route 127. Replace and install culverts. | 4590 | 405 | 405 | 620 | 620 | 150 | 150 | 405 | 405 | 800 | 800 | 2210 | 2210 | 0 | 314 | 314 | 314 | 56 | 56 | 480 | 32 | 32 | 93 | 0 | 0 | 391 | 8 | 8 | 236 | 0 | 0 | 2210 | 2018-07-01 | 2020-03-01 | 2020-03-20 | 2020-11-01 |  |  | 2018-06-22 | [6 empty] | 2020-03-01 | 2020-03-20 | 2020-08-19 | 2020-10-15
389 | 09 | 2633 | KER | 14 | Rosamond-Mojave Rehab | In and near Rosamond and Mojave, from 1.4 miles south of Dawn Road Overcrossing (OC) to 0.5 mile north of Silver Queen Road OC. Rehabilitate lanes with Continuous Reinforced Concrete Pavement (CRCP), cold plane and overlay ramps with Rubberized Hot Mix Asphalt (RHMA-G). Replace guardrail, construct rumble strip, replace signs using retroreflective sheeting, and refresh pavement delineation. (G13 Contingency) | 2102 | 370 | 370 | 1460 | 1460 | 250 | 250 | 0 | 0 | 22 | 22 | 0 | 0 | 0 | 174 | 174 | 174 | 774 | 774 | 1487 | 1 | 1 | 93 | 0 | 0 | 2340 | 0 | 0 | 0 | 0 | 0 | 80700 | 2018-06-20 | 2020-01-03 | 2020-01-23 | 2020-06-24 |  | 2018-12-06 | 2018-06-20 | [6 empty] | 2020-01-03 | 2020-01-23 | 2020-06-17 | 2022-06-24
390 | 10 | 0157 | TUO | 108 | Long Barn CAPM | Near Long Barn, from 0.1 mile east of the east junction of Long Barn Road to 2.3 miles east of Cow Creek Road. Pavement rehabilitation. | 22107 | 797 | 797 | 1152 | 1152 | 8 | 8 | 2092 | 2092 | 88 | 88 | 17970 | 17970 | 0 | 512 | 512 | 872 | 0 | 0 | 1129 | 0 | 0 | 8 | 0 | 0 | 1837 | 0 | 0 | 8 | 0 | 0 | 18100 | 2019-10-01 | 2020-12-01 | 2021-01-01 | 2021-07-15 | [8 empty] | 2019-10-01 | 2020-12-01 | 2021-01-02 | 2021-07-15 | 2023-10-01
391 | 10 | 0335 | TUO | 120 | CAPM East of Buck Meadows | Near Buck Meadows, from Ferretti Road to Yosemite National Park boundary. Pavement rehabilitation. | 26367 | 1000 | 1000 | 1158 | 1158 | 55 | 55 | 2793 | 2793 | 6 | 6 | 21355 | 21355 | 0 | 493 | 493 | 493 | 687 | 687 | 1199 | 6 | 6 | 44 | 0 | 0 | 2850 | 0 | 0 | 0 | 0 | 0 | 21335 | 2018-02-22 | 2019-03-18 | 2019-04-18 | 2019-11-29 |  | 2018-10-17 | 2018-02-22 | 2019-03-04 | 2019-04-22 | [6 empty] | 2019-11-29 | 2021-01-15
392 | 10 | 3089 | MER | 99 | SR99 MERCED REHAB | In and near the city of Merced, from south of Childs Avenue to south of Franklin Road. Roadway rehabilitation. (G13 Contingency) | 6427 | 2510 | 2510 | 3700 | 3700 | 122 | 122 | 0 | 0 | 95 | 95 | 0 | 0 | 0 | 2178 | 2178 | 2178 | 974 | 974 | 4639 | 9 | 9 | 152 | 0 | 0 | 13215 | 1 | 1 | 43 | 0 | 0 | 45344 | 2018-06-27 | 2020-05-01 | 2020-05-15 | 2020-12-14 |  | 2018-12-06 | 2018-06-27 | [6 empty] | 2020-05-01 | 2020-05-15 | 2020-12-14 | 2022-12-30
393 | 10 | 3102 | MER | 5 | D10 BRIDGE SUBSTRUCTURE REPAIRS | In Merced, San Joaquin, Mariposa and Stanislaus Counties, on various routes at various locations. Scour mitigation and preventative structural maintenance measures at thirteen bridges. | 7123 | 1025 | 1025 | 950 | 950 | 542 | 542 | 1200 | 1200 | 206 | 206 | 3200 | 3200 | 0 | 953 | 953 | 953 | 36 | 36 | 848 | 68 | 68 | 434 | 0 | 0 | 1193 | 3 | 3 | 206 | 0 | 0 | 2094 | 2018-07-02 | 2020-12-01 | 2020-12-18 | 2021-07-23 |  |  | 2018-08-22 | [6 empty] | 2020-12-01 | 2020-12-18 | 2021-07-23 | 2022-11-01
394 | 10 | 3113 | SJ | 4 | SJ BRIDGE MAINTENANCE | Near Discovery Bay, at Old River Bridge No. 29-0045. Upgrade mechanical and electrical equipment on movable bridge. | 9487 | 748 | 748 | 1414 | 1414 | 65 | 65 | 1319 | 1319 | 220 | 220 | 5721 | 5721 | 0 | 661 | 661 | 661 | 358 | 358 | 1689 | 30 | 30 | 149 | 0 | 0 | 1331 | 9 | 9 | 322 | 0 | 0 | 5720 | 2018-08-15 | 2020-04-03 | 2020-05-04 | 2020-10-21 |  |  | 2018-08-22 | [6 empty] | 2020-04-03 | 2020-05-04 | 2020-10-21 | 2022-04-21
395 | 10 | 3118 | SJ | 5 | SJ I-5 BRIDGE REHAB | In San Joaquin County, at two locations on Route 5/33 Separation and Overhead No. 29-0260 L/R; also in Stanislaus County in Modesto on Route 99 at West Modesto Overhead No. 38-0083. Seismic retrofit of three bridges. | 13640 | 621 | 621 | 1992 | 1992 | 223 | 223 | 1783 | 1783 | 263 | 263 | 8758 | 8758 | 0 | 429 | 429 | 429 | 896 | 896 | 1992 | 75 | 75 | 162 | 0 | 0 | 1587 | 33 | 33 | 382 | 0 | 0 | 5327 | 2017-10-10 | 2019-11-01 | 2019-11-15 | 2020-05-06 |  |  | 2017-10-10 | [6 empty] | 2020-02-12 | 2020-03-11 | 2020-10-29 | 2022-10-28
396 | 10 | 3119 | AMA | 88 | TUOLUMNE DRAINAGE RESTORATION | In Amador County, on Route 88 and in Tuolumne County on Routes 120,108 and 49, at various locations. Rehabilitate culverts. | 4136 | 475 | 475 | 778 | 778 | 65 | 65 | 616 | 616 | 55 | 55 | 2147 | 2147 | 0 | 454 | 454 | 454 | 428 | 428 | 767 | 14 | 14 | 16 | 0 | 0 | 614 | 33 | 33 | 54 | 0 | 0 | 2147 | 2018-03-01 | 2018-12-01 | 2019-01-02 | 2019-08-15 |  |  | 2018-03-14 | 2019-02-28 | 2019-03-29 | [6 empty] | 2019-10-15 | 2020-12-01
397 | 10 | 3134 | ALP | 88 | MOUNTAIN COUNTIES BRIDGE RAILS | Near Markleeville, on Routes 4, 88, and 89 at various locations. Bridge rail upgrade on three bridges and replace one bridge. | 13524 | 1410 | 1410 | 1737 | 1737 | 115 | 115 | 2369 | 2369 | 313 | 313 | 7580 | 7580 | 0 | 1298 | 1298 | 1298 | 88 | 88 | 1631 | 5 | 5 | 153 | 0 | 0 | 1823 | 2 | 2 | 454 | 0 | 0 | 6676 | 2018-07-02 | 2020-02-10 | 2020-04-17 | 2020-09-08 |  |  | 2019-01-15 | [6 empty] | 2020-05-01 | 2020-06-15 | 2020-12-01 | 2023-08-29
398 | 10 | 3138 | ALP | 88 | ALP/AMA/TUO CULVERT REHAB | In Alpine County on Routes 4, 88 and 207; also in Amador County on Routes 16 and 49; also in Tuolumne County on Route 108; at various locations. Rehabilitate culverts. | 8409 | 1310 | 1310 | 1043 | 1043 | 317 | 317 | 1180 | 1180 | 269 | 269 | 4290 | 4290 | 0 | 955 | 955 | 955 | 571 | 571 | 1258 | 43 | 43 | 286 | 0 | 0 | 1145 | 115 | 115 | 550 | 0 | 0 | 2390 | 2018-07-02 | 2019-12-01 | 2020-01-15 | 2020-09-01 |  |  | 2018-08-30 | [6 empty] | 2020-05-20 | 2020-05-22 | 2020-12-21 | 2022-09-01
399 | 10 | 3139 | MER | 152 | DRAINAGE RESTORATION | In Merced County on Routes 152, 59, and 99 and in San Joaquin County on Routes 5 and 12, at various locations. Rehabilitate culverts. | 2308 | 840 | 840 | 743 | 743 | 124 | 124 | 450 | 450 | 151 | 151 | 0 | 0 | 0 | 760 | 760 | 760 | 393 | 393 | 584 | 30 | 30 | 51 | 0 | 0 | 868 | 22 | 22 | 22 | 0 | 0 | 829 | 2018-06-04 | 2019-04-01 | 2019-05-01 | 2020-01-03 |  |  | 2018-05-11 | 2019-03-27 | 2019-05-02 | [6 empty] | 2020-01-03 | 2020-12-01
400 | 10 | 3140 | SJ | 5 | SJ CULVERTS | In San Joaquin County, on Routes 4, 5, and 99 at various locations. Rehabilitate culverts. | 4338 | 1003 | 1003 | 788 | 788 | 200 | 200 | 597 | 597 | 50 | 50 | 1700 | 1700 | 0 | 475 | 475 | 475 | 80 | 80 | 805 | 14 | 14 | 195 | 0 | 0 | 615 | 9 | 9 | 43 | 0 | 0 | 1380 | 2018-09-04 | 2020-05-22 | 2020-06-22 | 2020-12-01 |  |  | 2018-10-03 | [6 empty] | 2020-05-22 | 2020-06-22 | 2020-12-01 | 2021-12-01
401 | 10 | 3141 | SJ | 88 | SJ/ALP 88 DRAINAGE SYSTEM | Near Lockeford, from 0.1 mile nouth of East Jack Tone Road to 0.1 mile south of north Tully Road intersection; also near Kirkwood, in Alpine County (PM 0.2/2.6). Replace culverts. | 7922 | 795 | 795 | 900 | 900 | 290 | 290 | 875 | 875 | 1306 | 1306 | 3756 | 3756 | 0 | 685 | 685 | 685 | 66 | 66 | 1001 | 7 | 7 | 252 | 0 | 0 | 858 | 2 | 2 | 1305 | 0 | 0 | 3756 | 2018-12-03 | 2020-12-05 | 2020-12-20 | 2021-07-21 |  |  | 2018-12-14 | [6 empty] | 2020-12-24 | 2021-01-09 | 2021-07-21 | 2022-03-07
402 | 10 | 3142 | ALP | 4 | ALPINE CULVERT REHAB | In Alpine County on Routes 4, 88, and 89 at various locations. Rehabilitate culverts. | 7811 | 1370 | 1370 | 1176 | 1176 | 359 | 359 | 1203 | 1203 | 384 | 384 | 3319 | 3319 | 0 | 1150 | 1150 | 1150 | 270 | 270 | 1104 | 24 | 24 | 405 | 0 | 0 | 1609 | 83 | 83 | 384 | 0 | 0 | 3319 | 2018-07-02 | 2019-10-13 | 2020-01-02 | 2020-09-01 |  |  | 2018-08-30 | [6 empty] | 2020-04-01 | 2020-04-10 | 2020-10-01 | 2023-09-01
403 | 10 | 3146 | SJ | 205 | SR205 SMART CORRIDOR - PHASE 2 | In Tracy, from Byron Road Undercrossing to Paradise Road Overcrossing. Install ramp meters and other Transportation Management System (TMS) elements. | 41621 | 1650 | 1650 | 3500 | 3500 | 979 | 979 | 5600 | 5600 | 3260 | 3260 | 26632 | 26632 | 0 | 1560 | 1560 | 1560 | 441 | 441 | 4345 | 82 | 82 | 1542 | 0 | 0 | 6951 | 12 | 12 | 3018 | 0 | 0 | 31194 | 2018-09-11 | 2020-12-17 | 2021-01-01 | 2021-07-23 |  | 2018-12-06 | 2018-09-11 | [6 empty] | 2021-04-15 | 2021-07-08 | 2022-03-02 | 2023-12-20
404 | 10 | 3147 | SJ | 5 | AMA/MER/SJ/MPA/SCL/SBT TMS ELEMENT UPGRADES | In various counties, on various routes, at various locations. Upgrade Transportation Management System (TMS) elements. | 5752 | 392 | 392 | 1048 | 1048 | 138 | 138 | 697 | 697 | 15 | 15 | 3462 | 3462 | 0 | 200 | 200 | 200 | 1007 | 1007 | 1065 | 11 | 11 | 138 | 0 | 0 | 685 | 0 | 0 | 0 | 0 | 0 | 1346 | 2017-05-16 | 2019-05-07 | 2019-06-14 | 2019-12-27 |  |  | 2017-05-16 | 2019-04-16 | 2019-06-14 | [6 empty] | 2019-12-27 | 2020-12-28
405 | 10 | 3148 | SJ | 99 | SJ 4/99 BRIDGE REHAB | In Stockton, at Route 4/99 Separation (Farmington Road) Bridge No. 29-0155. Replace structure to provide standard vertical clearance. | 12865 | 893 | 893 | 2092 | 2092 | 300 | 300 | 1984 | 1984 | 298 | 298 | 7298 | 7298 | 0 | 698 | 698 | 698 | 1492 | 1492 | 2362 | 121 | 121 | 283 | 0 | 0 | 1876 | 109 | 109 | 301 | 0 | 0 | 7248 | 2017-11-09 | 2019-12-02 | 2019-12-16 | 2020-07-01 |  |  | 2017-11-29 | [6 empty] | 2019-12-02 | 2019-12-16 | 2020-07-01 | 2022-07-01
406 | 10 | 3158 | MPA | 41 | Culvert Rehabilitation near Fish Camp in Mariposa County | Near Fish Camp, from south of Miami Mountain Road to south of Yosemite National Park boundary; also in Madera County (PM D0.639/D1.841). Rehabilitate culverts. | 4597 | 650 | 650 | 929 | 929 | 84 | 84 | 905 | 905 | 80 | 80 | 1949 | 1949 | 1949 | 639 | 639 | 639 | 715 | 715 | 715 | 8 | 8 | 56 | 23 | 23 | 900 | 32 | 32 | 63 | 0 | 0 | 1949 | 2017-10-27 | 2018-12-03 | 2018-12-04 | 2019-07-01 |  |  | 2017-10-27 | 2018-12-14 | 2019-01-17 | 2019-05-13 | [6 empty] | 2020-07-01
407 | 10 | 3165 | SJ | 4 | SJ SR 4 Pavement Resurfacing and Restoration | In Stockton, from 0.2 mile east of Fresno Avenue to Center Street; also on Route 5 from Taylor Street Overhead to Stockton Channel Viaduct (PM 25.8/26.5). Roadway rehabilitation. | 43473 | 792 | 792 | 2478 | 2478 | 19 | 19 | 4979 | 4979 | 48 | 48 | 35157 | 35157 | 0 | 787 | 787 | 787 | 1168 | 1168 | 2193 | 0 | 0 | 0 | 0 | 0 | 5070 | 0 | 0 | 0 | 0 | 0 | 30814 | 2018-05-09 | 2019-10-10 | 2019-11-10 | 2020-07-11 |  | 2018-12-06 | 2018-05-09 | [6 empty] | 2019-10-10 | 2019-11-10 | 2020-07-11 | 2021-01-05
408 | 10 | 3167 | MPA | 140 | MPA Route 140 Pavement Preservation | Near the Mariposa community and El Portal, from East Whitlock Road to Yosemite National Park entrance. Pavement rehabilitation. | 29169 | 982 | 982 | 1900 | 1900 | 30 | 30 | 2330 | 2330 | 162 | 162 | 23765 | 23765 | 0 | 314 | 314 | 1094 | 0 | 0 | 2201 | 0 | 0 | 38 | 0 | 0 | 2474 | 0 | 0 | 163 | 0 | 0 | 21554 | 2020-05-01 | 2021-09-01 | 2021-10-01 | 2022-04-15 | [8 empty] | 2020-10-15 | 2021-10-01 | 2022-04-15 | 2022-05-16 | 2024-05-15
409 | 10 | 3169 | SJ | 26 | SJ Route 26 Increase Bridge Vertical Clearance | Near Stockton, at Route 26/99 Separation No. 29-0142 (PM 1.11). Establish standard vertical clearance. | 17302 | 698 | 698 | 1827 | 1827 | 13 | 13 | 3221 | 3221 | 7 | 7 | 11536 | 11536 | 0 | 649 | 649 | 649 | 0 | 0 | 2043 | 0 | 0 | 0 | 0 | 0 | 3517 | 0 | 0 | 4 | 0 | 0 | 6112 | 2019-05-01 | 2020-12-15 | 2021-01-15 | 2021-07-01 |  |  | 2019-06-17 | [6 empty] | 2020-12-15 | 2021-01-15 | 2021-07-01 | 2023-12-29
410 | 10 | 3193 | SJ | 5 | SJ SR 5 Bridge Deck Rehabilitation | In Stockton, at the Stockton Channel Viaduct No. 29-0176L/R. Bridge deck rehabilitation at spot locations. | 8096 | 335 | 335 | 1030 | 1030 | 10 | 10 | 1950 | 1950 | 5 | 5 | 4766 | 4766 | 0 | 224 | 224 | 224 | 232 | 232 | 878 | 0 | 0 | 7 | 0 | 0 | 1556 | 0 | 0 | 0 | 0 | 0 | 3039 | 2018-07-13 | 2019-09-20 | 2020-01-03 | 2020-07-13 |  |  | 2018-06-21 | [6 empty] | 2020-01-07 | 2020-02-12 | 2020-09-12 | 2021-06-12
411 | 10 | 3198 | SJ | 4 | SJ SR 4 Reconstruction of Hinge 32 | In Stockton, at Crosstown Freeway Viaduct No. 29-0269. Reconstruct hinge 32 (left and right) and three ramp joint seals. | 5707 | 648 | 648 | 848 | 848 | 37 | 37 | 631 | 631 | 115 | 115 | 3428 | 3428 | 0 | 300 | 300 | 300 | 702 | 702 | 1067 | 8 | 8 | 23 | 0 | 0 | 806 | 3 | 3 | 115 | 0 | 0 | 2542 | 2017-11-15 | 2019-03-01 | 2019-03-15 | 2019-11-29 |  |  | 2017-12-27 | 2019-06-12 | 2019-06-20 | [6 empty] | 2020-01-20 | 2021-01-20
412 | 10 | 3206 | SJ | 99 | SJ Route 99 Bridge Girder Replacement | Near Stockton, at Wilson Way Overcrossing No. 29-0118C. Remove existing damaged girder and build new overhang and barrier, resulting in reduced bridge width and increased vertical clearance. | 2971 | 172 | 172 | 817 | 817 | 7 | 7 | 493 | 493 | 4 | 4 | 1478 | 1478 | 0 | 72 | 72 | 72 | 508 | 508 | 876 | 2 | 2 | 8 | 0 | 0 | 542 | 4 | 4 | 2 | 0 | 0 | 1170 | 2017-07-13 | 2018-06-05 | 2018-07-05 | 2018-11-22 |  |  | 2017-11-16 | 2018-06-01 | 2019-01-15 | [6 empty] | 2019-12-24 | 2020-12-24
413 | 10 | 3219 | AMA | 49 | Mokelumne River Bridge Upgrade | Near Jackson, at Mokelumne River Bridge No. 26-0012. Upgrade bridge rails and widen shoulders. | 9889 | 1590 | 1590 | 2010 | 2010 | 135 | 135 | 2055 | 2055 | 185 | 185 | 3914 | 3914 | 0 | 283 | 283 | 1570 | 0 | 0 | 1828 | 0 | 0 | 115 | 0 | 0 | 1710 | 0 | 0 | 185 | 0 | 0 | 3166 | 2020-06-30 | 2022-04-28 | 2022-05-02 | 2022-12-27 | [8 empty] | 2020-07-02 | 2022-04-28 | 2022-05-02 | 2022-12-27 | 2024-03-30
414 | 10 | 3226 | SJ | 120 | D 10 TMS Repair | In San Joaquin, Amador, Calaveras, Merced, Mariposa, Stanislaus, and Tuolumne Counties, on Routes 4, 5, 26, 33, 49, 59, 88, 99, 104, 108, 120, 132, 140, 152 and 205 at various locations. Repair or replace damaged and nonfunctioning Traffic Management System (TMS) elements. | 5271 | 632 | 632 | 1191 | 1191 | 107 | 107 | 1243 | 1243 | 33 | 33 | 2065 | 2065 | 0 | 407 | 407 | 407 | 0 | 0 | 1180 | 0 | 0 | 97 | 0 | 0 | 1062 | 0 | 0 | 0 | 0 | 0 | 2065 | 2019-04-26 | 2020-11-05 | 2021-01-05 | 2021-07-06 |  |  | 2019-05-22 | [6 empty] | 2020-11-05 | 2021-01-05 | 2021-07-06 | 2022-07-06
415 | 10 | 3227 | SJ | 99 | D 10 MVDS replacement and upgrade | In San Joaquin, Merced, and Stanislaus Counties, on Routes 5, 12, 59, 99, and 152 at various locations. Upgrade or replace inefficient and damaged Transportation Management System (TMS) elements. | 13778 | 1202 | 1202 | 1719 | 1719 | 465 | 465 | 1994 | 1994 | 9 | 9 | 8389 | 8389 | 0 | 705 | 705 | 705 | 62 | 62 | 1629 | 3 | 3 | 417 | 0 | 0 | 1993 | 0 | 0 | 9 | 0 | 0 | 6862 | 2019-04-01 | 2020-02-14 | 2020-03-16 | 2020-09-15 |  |  | 2019-04-09 | [6 empty] | 2020-04-01 | 2020-04-15 | 2020-11-16 | 2022-03-14
416 | 10 | 3229 | SJ | 99 | SJ DRAINAGE PUMP PLANT UPGRADE | In and near Stockton and Lodi, at various locations from Eastside Underpass to Acampo Road; also on Route 4 at the Route 4/5 Separation (PM R16.10) and on Route 120 in Lathrop at Mossdale Underpass (PM R0.5). Upgrade drainage pump plants. | 8746 | 439 | 439 | 1530 | 1530 | 59 | 59 | 1289 | 1289 | 260 | 260 | 5169 | 5169 | 0 | 262 | 262 | 504 | 0 | 0 | 1455 | 0 | 0 | 60 | 0 | 0 | 1078 | 0 | 0 | 260 | 0 | 0 | 4634 | 2019-09-09 | 2021-12-13 | 2022-01-13 | 2022-07-05 | [8 empty] | 2019-11-22 | 2022-02-14 | 2022-03-04 | 2022-07-05 | 2023-11-06
417 | 10 | 3230 | SJ | 120 | SR 120 TMC Upgrade | In and near Manteca and Lathrop, from Route 5 to Route 99; also on Route 5 at PM R13.34 and on Route 99 at PM 4.56. Install Intelligent Transportation System (ITS) field elements. | 6333 | 373 | 373 | 1221 | 1221 | 0 | 0 | 1121 | 1121 | 68 | 68 | 3550 | 3550 | 0 | 255 | 255 | 255 | 236 | 236 | 1153 | 0 | 0 | 2 | 0 | 0 | 1375 | 0 | 0 | 58 | 0 | 0 | 7210 | 2018-08-17 | 2020-12-03 | 2021-01-29 | 2021-09-13 |  |  | 2018-09-21 | [6 empty] | 2020-12-03 | 2021-01-29 | 2021-09-13 | 2022-03-14
418 | 10 | 3233 | MPA | 49 | Mariposa SR 49 CAPM | Near the community of Mariposa, from Madera County line to the south junction with Route 140. Pavement rehabilitation. | 20562 | 403 | 403 | 1032 | 1032 | 9 | 9 | 2150 | 2150 | 7 | 7 | 16961 | 16961 | 0 | 380 | 380 | 380 | 99 | 99 | 1145 | 0 | 0 | 8 | 0 | 0 | 1232 | 0 | 0 | 7 | 0 | 0 | 16293 | 2018-12-20 | 2020-02-11 | 2020-03-16 | 2020-09-27 |  | 2019-01-31 | 2018-12-20 | [6 empty] | 2020-02-11 | 2020-04-27 | 2020-09-28 | 2021-12-06
419 | 10 | 3235B | SJ | 5 | DEUEL OVERHEAD UC | In and near Lathrop, at Deuel Overhead No. 29 -0262R/L (PM 10.646). Replace bridge rails and preventive maintenance on bridge. | 7033 | 798 | 798 | 925 | 925 | 70 | 70 | 1400 | 1400 | 440 | 440 | 3400 | 3400 | 0 | 493 | 493 | 493 | 495 | 495 | 1216 | 18 | 18 | 68 | 0 | 0 | 1256 | 0 | 0 | 299 | 0 | 0 | 3396 | 2017-12-30 | 2020-01-30 | 2020-02-28 | 2020-08-26 |  |  | 2018-01-09 | [6 empty] | 2020-01-30 | 2020-02-28 | 2020-09-25 | 2021-12-30
420 | 10 | 3247 | CAL | 26 | Upgrade bridge rails of three bridges in CAL Co | Near West Point, at South Fork Mokelumne River Bridge No. 30-0022 (PM 30.0), and at North Fork Mokelumne River Bridge No. 30-0049 (PM 38.3); also on Route 4 in Angels Camp, at Angels Creek Bridge No. 30-0008 (PM R21.4). Upgrade bridge railing at three structures, also seismic retrofit at one location. | 8781 | 1033 | 1033 | 1604 | 1604 | 60 | 60 | 1540 | 1540 | 8 | 8 | 4536 | 4536 | 0 | 258 | 258 | 1069 | 0 | 0 | 1650 | 0 | 0 | 56 | 0 | 0 | 1718 | 0 | 0 | 112 | 0 | 0 | 2843 | 2020-08-03 | 2021-05-03 | 2021-08-02 | 2022-01-03 | [8 empty] | 2020-08-03 | 2021-09-03 | 2021-08-02 | 2022-01-03 | 2024-01-02
421 | 10 | 3250 | SJ | 5 | SJ Changeable Message Signs | In and near Stockton, on Route 5 at various locations; also on Route 4 (PM 14.6/26.0) and Route 99 (PM 15.8/18.5) at various locations. Install Transportation Management System (TMS) elements. | 16263 | 820 | 820 | 2550 | 2550 | 380 | 380 | 1805 | 1805 | 335 | 335 | 10373 | 10373 | 0 | 811 | 811 | 811 | 342 | 342 | 2315 | 39 | 39 | 311 | 0 | 0 | 1633 | 2 | 2 | 324 | 0 | 0 | 10372 | 2018-08-28 | 2021-11-23 | 2021-12-22 | 2022-07-14 |  |  | 2018-09-13 | [6 empty] | 2021-11-23 | 2021-12-22 | 2022-07-14 | 2023-12-29
422 | 10 | 3251 | STA | 99 | Replace Drainage Pumps | In and near Ceres and Modesto, at various locations from Mitchell Road to Kansas Avenue; also in Merced County, on Route 59 near the city of Merced, at Childs Avenue (PM 14.0). Upgrade drainage pump plants. | 10017 | 330 | 330 | 1150 | 1150 | 93 | 93 | 1991 | 1991 | 13 | 13 | 6440 | 6440 | 0 | 194 | 194 | 194 | 0 | 0 | 1095 | 0 | 0 | 91 | 0 | 0 | 1106 | 0 | 0 | 16 | 0 | 0 | 6440 | 2019-06-29 | 2020-08-10 | 2020-09-09 | 2021-03-26 |  |  | 2019-06-28 | [6 empty] | 2020-08-10 | 2020-09-09 | 2021-03-26 | 2022-02-09
423 | 10 | 3252 | MPA | 140 | SR140 MARIPOSA CAPM | In and near the Mariposa community, from 1.7 miles east of Catheys Valley Park to the north Route 49 Junction. Rehabilitate pavement and upgrade Americans with Disabilities Act (ADA) ramps. | 23577 | 1025 | 1025 | 1095 | 1095 | 416 | 416 | 1689 | 1689 | 1989 | 1989 | 17363 | 17363 | 0 | 494 | 494 | 1038 | 0 | 0 | 1168 | 0 | 0 | 394 | 0 | 0 | 1546 | 0 | 0 | 192 | 0 | 0 | 18850 | 2020-02-01 | 2022-05-01 | 2022-06-01 | 2022-12-01 | [8 empty] | 2020-04-01 | 2022-05-01 | 2022-06-01 | 2022-12-01 | 2024-06-01
424 | 10 | 3255 | CAL | 4 | Bridge Replacement | Near Angels Camp, at West Branch Cherokee Creek Bridge No. 30-0036. Replace bridge. | 5880 | 866 | 866 | 1392 | 1392 | 103 | 103 | 1241 | 1241 | 278 | 278 | 2000 | 2000 | 0 | 545 | 545 | 818 | 0 | 0 | 1310 | 0 | 0 | 98 | 0 | 0 | 1016 | 0 | 0 | 294 | 0 | 0 | 1707 | 2019-08-06 | 2021-02-04 | 2021-08-11 | 2022-02-28 | [8 empty] | 2019-10-07 | 2021-10-19 | 2021-11-29 | 2022-06-18 | 2023-06-25
425 | 10 | 3273 | SJ | 12 | Potato Slough Bridge Bearing Pads | Near Terminous, at Little Potato Slough Bridge No. 29-0101. Replace joint seals and bearing pads using temporary pile supports. | 6645 | 553 | 553 | 905 | 905 | 2 | 2 | 1232 | 1232 | 925 | 925 | 3028 | 3028 | 0 | 289 | 289 | 670 | 0 | 0 | 914 | 0 | 0 | 2 | 0 | 0 | 1178 | 0 | 0 | 925 | 0 | 0 | 2927 | 2020-07-20 | 2021-02-17 | 2021-05-20 | 2021-12-15 | [8 empty] | 2020-07-20 | 2021-02-17 | 2021-05-20 | 2021-12-15 | 2022-12-30
426 | 10 | 3274 | SJ | 4 | SR-4 Ramp Metering System Installation | In Stockton, from Route 5 to Route 99. Install ramp meters, traffic monitoring systems, Closed Circuit Television (CCTV), and synchronize intersection signals with ramp metering. (Long Lead Project) | 2177 | 2177 | 2177 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 591 | 591 | 2032 | 0 | 0 | 4264 | 0 | 0 | 596 | 0 | 0 | 5714 | 0 | 0 | 1269 | 0 | 0 | 37521 | 2019-09-15 | 2022-03-15 | 2022-04-15 | 2022-12-01 | [8 empty] | 2020-03-02 | 2022-11-17 | 2023-01-05 | 2023-08-17 | 2025-09-15
427 | 10 | 3286 | STA | 5 | TTI SYSTEM UPGRADE | In Stockton, at 0.7 mile north of Hammer Lane; also in Sacramento County, near Thornton at 0.6 mile south of Twin Cities Road (PM 1.5). Install Transportation Management System (TMS) elements. | 2770 | 363 | 363 | 377 | 377 | 4 | 4 | 401 | 401 | 6 | 6 | 1619 | 1619 | 0 | 213 | 213 | 336 | 0 | 0 | 436 | 0 | 0 | 4 | 0 | 0 | 376 | 0 | 0 | 0 | 0 | 0 | 1411 | 2019-07-01 | 2020-01-28 | 2020-04-07 | 2020-08-17 | [8 empty] | 2019-10-01 | 2020-04-27 | 2020-05-22 | 2020-11-02 | 2021-12-01
428 | 10 | 5431 | MER | 99 | MER-99 PAVEMENT REHABILITATION | In and near Atwater, from 0.4 mile south of Buhach Road to south of Westside Boulevard. Roadway rehabilitation. | 81819 | 1973 | 1973 | 5200 | 5200 | 677 | 677 | 10000 | 10000 | 3369 | 3369 | 60600 | 60600 | 0 | 1989 | 1989 | 1989 | 2364 | 2364 | 2982 | 296 | 296 | 681 | 0 | 0 | 8916 | 2345 | 2345 | 3162 | 0 | 0 | 68148 | 2017-12-04 | 2019-06-14 | 2019-06-21 | 2020-02-28 |  | 2018-10-17 | 2017-12-04 | 2019-06-24 | 2019-06-28 | [6 empty] | 2020-01-02 | 2022-12-30
429 | 10 | 5431Y | MER | 99 | MER 99 Highway planting and irrigation | In and near Atwater, from 0.4 mile south of Buhach Road to south of Westside Boulevard. Landscape mitigation for roadway rehabilitation project EA 3A720. | 3205 | 400 | 400 | 690 | 690 | 10 | 10 | 1100 | 1100 | 5 | 5 | 1000 | 1000 | 0 | 0 | 0 | 400 | 0 | 0 | 690 | 0 | 0 | 10 | 0 | 0 | 1100 | 0 | 0 | 0 | 0 | 0 | 1000 | [12 empty] | 2020-05-29 | 2021-08-02 | 2021-09-01 | 2022-03-18 | 2026-03-02
430 | 11 | 1134 | SD | 78 | CULVERT REHABILITATION | Near Ballena, from 3.4 miles east of Route 67 to 4.3 miles west of Route 79. Culvert rehabilitation. | 6109 | 856 | 856 | 988 | 988 | 418 | 418 | 718 | 718 | 483 | 483 | 2646 | 2646 | 0 | 811 | 811 | 811 | 125 | 125 | 982 | 170 | 170 | 410 | 0 | 0 | 507 | 14 | 14 | 80 | 0 | 0 | 2646 | 2018-07-20 | 2019-05-22 | 2019-06-03 | 2019-10-18 |  |  | 2018-11-15 | [6 empty] | 2019-11-08 | 2019-11-15 | 2020-06-04 | 2020-11-04
431 | 11 | 1162 | SD | 78 | SR-78 PAVEMENT REHABILITATION | In and near Escondido, from west of North Broadway to Teepee Drive. Pavement rehabilitation. | 27935 | 1408 | 1408 | 3153 | 3153 | 1117 | 1117 | 3001 | 3001 | 4 | 4 | 19252 | 19252 | 0 | 1343 | 1343 | 1343 | 526 | 526 | 3150 | 14 | 14 | 487 | 0 | 0 | 1705 | 4 | 4 | 497 | 0 | 0 | 17731 | 2018-12-07 | 2020-03-18 | 2020-03-30 | 2021-02-25 |  | 2019-01-31 | 2018-12-07 | [6 empty] | 2020-03-18 | 2020-04-02 | 2020-10-19 | 2022-04-28
432 | 11 | 1171 | SD | Var | TMS ELEMENT IN-HOUSE FIBER OPTIC | In San Diego County, on various routes at various locations. Replace Changeable Message Signs (CMS) panels with Advanced Variable Message Signs (AVMS) panels. | 8042 | 0 | 0 | 840 | 840 | 0 | 0 | 1030 | 1030 | 0 | 0 | 6172 | 6172 | 0 | 0 | 0 | 0 | 670 | 670 | 847 | 0 | 0 | 0 | 0 | 0 | 1190 | 0 | 0 | 0 | 0 | 0 | 4401 | 2015-06-19 | 2019-10-14 | 2019-12-12 | 2020-09-04 |  |  | 2015-06-19 | 2019-06-12 | 2019-07-15 | [6 empty] | 2020-03-18 | 2022-04-20
433 | 11 | 1174 | SD | Var | DVMS PANELS | In San Diego County, on various routes at various locations. Replace Changeable Message Signs (CMS) panels with Advanced Variable Message Signs (AVMS) panels. | 5657 | 389 | 389 | 993 | 993 | 0 | 0 | 825 | 825 | 0 | 0 | 3450 | 3450 | 3450 | 381 | 381 | 381 | 968 | 968 | 968 | 0 | 0 | 0 | 211 | 211 | 823 | 0 | 0 | 0 | 273 | 273 | 3450 | 2017-03-24 | 2018-02-22 | 2018-05-25 | 2019-01-23 |  |  | 2017-03-24 | 2018-03-06 | 2018-06-18 | 2018-11-30 | [6 empty] | 2020-07-10
434 | 11 | 1177 | SD | 94 | SR-94 PAVEMENT REHAB | In the city of San Diego, from Spring Street to Route 54. Pavement rehabilitation. | 16177 | 577 | 577 | 1252 | 1252 | 0 | 0 | 1537 | 1537 | 0 | 0 | 12811 | 12811 | 0 | 565 | 565 | 565 | 463 | 463 | 1245 | 0 | 0 | 0 | 0 | 0 | 1410 | 0 | 0 | 0 | 0 | 0 | 12811 | 2018-01-19 | 2019-10-28 | 2019-11-26 | 2020-06-16 |  |  | 2018-01-12 | [6 empty] | 2019-10-25 | 2019-12-13 | 2020-05-29 | 2021-02-11
435 | 11 | 1188 | SD | 54 | SR 54 PAVEMENT PRESERVATION | In and near National City and Chula Vista, from Route 54/5 Separation to the Route 54/125 Junction. Rehabilitate flexible and rigid pavement on the traveled way, shoulders, ramps and connectors, upgrade guard rail and dike. | 27132 | 709 | 709 | 2260 | 2260 | 24 | 24 | 2513 | 2513 | 297 | 297 | 21329 | 21329 | 0 | 213 | 213 | 703 | 0 | 0 | 1959 | 0 | 0 | 21 | 0 | 0 | 2006 | 0 | 0 | 297 | 0 | 0 | 21330 | 2020-02-03 | 2021-08-27 | 2021-10-20 | 2022-05-05 | [8 empty] | 2020-02-07 | 2021-08-31 | 2021-10-22 | 2022-05-20 | 2023-12-04
436 | 11 | 1194 | SD | 8 | I-8 CULVERT REPLACEMENT | In San Diego County, from 0.7 mile west of Flinn Springs Road Undercrossing to 0.2 mile east of Crestwood Road Undercrossing. Rehabilitate culverts and energy dissipaters. | 10778 | 954 | 954 | 1246 | 1246 | 319 | 319 | 1636 | 1636 | 50 | 50 | 6573 | 6573 | 0 | 683 | 683 | 683 | 0 | 0 | 1188 | 0 | 0 | 304 | 0 | 0 | 1451 | 7 | 7 | 50 | 0 | 0 | 6573 | 2018-02-02 | 2019-05-23 | 2019-07-24 | 2020-03-20 |  |  | 2019-06-28 | [6 empty] | 2020-07-02 | 2020-08-20 | 2021-04-14 | 2023-08-04
437 | 11 | 1221 | SD | Var | BRIDGE PRESERVATION RT 5/54/94/125/163 | In San Diego County, at various locations. Apply methacrylate to bridge decks, replace joint seals, repair unsound concrete and replace approach slabs. | 5663 | 0 | 0 | 683 | 683 | 0 | 0 | 852 | 852 | 0 | 0 | 4128 | 4128 | 0 | 0 | 0 | 0 | 647 | 647 | 703 | 0 | 0 | 0 | 0 | 0 | 835 | 0 | 0 | 0 | 0 | 0 | 3542 | 2016-12-15 | 2018-12-05 | 2018-12-07 | 2019-04-05 |  |  | 2016-12-15 | 2018-12-04 | 2018-12-27 | [6 empty] | 2019-10-17 | 2020-05-15
438 | 11 | 1241 | IMP | VAR | Intelligent Transportation System Technology | In San Diego County and Imperial County on various routes at various locations. Install Intelligent Technology Statewide Border Wait Time, implement a fiber optic cable network to facilitate an advanced traveler information and border wait time system connecting the entire San Diego and Imperial border network. | 27206 | 817 | 817 | 4038 | 1721 | 62 | 62 | 5938 | 4404 | 375 | 375 | 27945 | 19827 | 0 | 524 | 524 | 524 | 814 | 347 | 4200 | 0 | 0 | 1 | 0 | 0 | 5301 | 0 | 0 | 0 | 0 | 0 | 26683 | 2018-11-16 | 2020-02-01 | 2020-02-15 | 2020-07-15 | 2022-05-20 | 2018-08-15 | 2018-10-15 | [6 empty] | 2020-05-17 | 2020-05-30 | 2020-11-02 | 2022-09-07
439 | 11 | 1246 | SD | 8 | SD-008-L0.7/R23.0 - DRAINAGE SYSTEM RESTORATION | In San Diego County, at various locations, from 0.5 mile west of Midway Drive Undercrossing to 0.6 mile west of Flinn Springs Road Undercrossing. Repair, rehabilitate and replace culvert systems. | 13230 | 1173 | 1173 | 1590 | 1590 | 0 | 0 | 2020 | 2020 | 80 | 80 | 8367 | 8367 | 0 | 961 | 961 | 961 | 100 | 100 | 1587 | 0 | 0 | 0 | 0 | 0 | 1832 | 0 | 0 | 116 | 0 | 0 | 8618 | 2018-11-26 | 2020-02-04 | 2020-03-30 | 2020-10-08 |  |  | 2018-12-13 | [6 empty] | 2020-04-17 | 2020-06-05 | 2020-10-23 | 2023-07-07
440 | 11 | 1247 | SD | 78 | CULVERT REPLACEMENT | In San Diego County, at various locations from 0.1 mile east of Route 78/5 Separation to Route 15/78 Separation. Rehabilitate and replace culverts including invert paving, joint repair grouting, Cured-in-Place Pipeliner (CIPP) and drainage inlet lid repair. | 14461 | 1091 | 1091 | 2388 | 2388 | 212 | 212 | 2047 | 2047 | 204 | 204 | 8519 | 8519 | 0 | 652 | 652 | 1144 | 0 | 0 | 1410 | 0 | 0 | 198 | 0 | 0 | 1647 | 0 | 0 | 204 | 0 | 0 | 8519 | 2020-03-18 | 2021-12-10 | 2021-12-10 | 2022-06-13 | [8 empty] | 2019-12-31 | 2021-12-10 | 2021-12-10 | 2022-06-13 | 2025-02-07
441 | 11 | 1255 | SD | 8 | I8 - PAVEMENT REHAB | Near Alpine, from Viejas Creek Bridge to Pine Valley Creek Bridge. Grind, remove and replace Jointed Plain Concrete Pavement (JPCP) lanes, remove and replace asphalt concrete outside shoulders and cold plane and overlay inside shoulders. Upgrade guardrail, replace approach/departure slabs and construct rumble strips. | 53549 | 1026 | 1026 | 3276 | 3276 | 0 | 0 | 5479 | 5479 | 0 | 0 | 43768 | 43768 | 0 | 901 | 901 | 901 | 0 | 0 | 3552 | 0 | 0 | 0 | 0 | 0 | 4795 | 0 | 0 | 0 | 0 | 0 | 43769 | 2019-12-04 | 2021-09-21 | 2021-11-03 | 2022-03-14 |  |  | 2019-05-01 | [6 empty] | 2021-01-08 | 2021-02-12 | 2021-07-22 | 2022-12-13
442 | 11 | 1256 | SD | 8 | E8-S163 CONNECTOR OC | In the city of San Diego, at the east Route 8 to south Route 163 Connector Overcrossing No. 57-0355G. Bridge rail replacement. | 4058 | 374 | 374 | 969 | 969 | 0 | 0 | 848 | 848 | 0 | 0 | 1867 | 1867 | 0 | 86 | 86 | 419 | 0 | 0 | 836 | 0 | 0 | 0 | 0 | 0 | 721 | 0 | 0 | 0 | 0 | 0 | 1867 | 2019-07-02 | 2020-10-26 | 2020-11-06 | 2021-03-11 | [8 empty] | 2019-11-08 | 2021-01-29 | 2021-03-26 | 2021-08-27 | 2023-04-19
443 | 11 | 1257 | SD | 125 | SR-125 CAPM | Near La Mesa and in Santee, from 0.2 mile south of Route 125/94 Separation to Mission Gorge Road. Rehabilitate pavement by grinding and replacing concrete slabs and cold plane and overlay shoulders with Rubberized Hot Mix Asphalt (RHMA-G). | 42277 | 1383 | 1383 | 2541 | 2541 | 53 | 53 | 3863 | 3863 | 252 | 252 | 34185 | 34185 | 0 | 841 | 841 | 1463 | 0 | 0 | 2363 | 0 | 0 | 43 | 0 | 0 | 3042 | 0 | 0 | 253 | 0 | 0 | 34185 | 2019-12-02 | 2021-09-30 | 2021-11-09 | 2022-06-08 | [8 empty] | 2019-11-15 | 2021-08-02 | 2021-09-22 | 2022-04-19 | 2023-08-22
444 | 11 | 1262 | SD | Var | REPAIR EXISTING LOOP DETECTORS | In San Diego County, at various locations. Repair and install Vehicle Detection Station (VDS) elements including Microwave Vehicle Detection Systems (MVDS) and loop detectors. | 16870 | 911 | 911 | 2160 | 2160 | 0 | 0 | 2264 | 2264 | 0 | 0 | 11535 | 11535 | 0 | 886 | 886 | 886 | 775 | 775 | 1936 | 0 | 0 | 0 | 0 | 0 | 2276 | 0 | 0 | 0 | 0 | 0 | 11535 | 2018-08-22 | 2019-11-15 | 2019-12-13 | 2020-05-15 |  |  | 2019-01-29 | [6 empty] | 2020-03-20 | 2020-04-20 | 2020-08-10 | 2022-05-20
445 | 11 | 1263 | SD | 15 | INSTALL RADAR DETECTION SYSTEMS | In San Diego County, at various locations. Update Microwave Vehicle Detection System (MVDS) elements for traffic flow monitoring and data collections. | 5215 | 372 | 372 | 865 | 865 | 0 | 0 | 654 | 654 | 0 | 0 | 3324 | 3324 | 0 | 150 | 150 | 150 | 766 | 766 | 864 | 0 | 0 | 0 | 0 | 0 | 997 | 0 | 0 | 0 | 0 | 0 | 3325 | 2018-04-18 | 2019-03-08 | 2019-05-08 | 2019-12-13 |  |  | 2018-08-06 | 2019-03-07 | 2019-05-10 | [6 empty] | 2020-01-21 | 2022-05-19
446 | 11 | 1280 | SD | 805 | I-805 SWEETWATER RIVER BRIDGE UPGRADE | In and near Chula Vista, from 0.2 mile south of Sweetwater River Bridge No. 57-0638R/L to Route 54. Upgrade bridge rails, widen bridges to make standard, and repair approach slabs, joint seals, gore pavement, and shoulders. | 25209 | 42 | 0 | 2029 | 0 | 15 | 0 | 5023 | 5023 | 0 | 0 | 20186 | 20186 | 20186 | 41 | 0 | 41 | 1845 | 0 | 1845 | 0 | 0 | 0 | 686 | 686 | 4776 | 0 | 0 | 15 | 1823 | 1823 | 20186 | 2017-08-31 | 2018-02-28 | 2018-06-29 | 2019-01-24 |  | 2018-10-17 | 2017-08-31 | 2018-02-28 | 2018-06-29 | 2019-01-09 | [6 empty] | 2023-03-07
447 | 11 | 1281 | SD | 5 | I-5NCC ITS ELEMENTS | In San Diego County, from 0.6 mile south of Route 5/8 Separation to 1.5 miles north of Route 5/76 Separation. Install Vehicle Detection Stations (VDS), Changeable Message Signs (CMS), Closed Circuit Television (CCTV), Ramp Metering, Traffic Signal and Fiber Optic Network elements. | 1622 | 0 | 0 | 1497 | 1497 | 122 | 122 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 1330 | 1330 | 1330 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19766 | 2013-10-23 | 2018-05-21 | 2018-06-29 | 2018-10-02 |  | 2018-08-15 | 2013-10-23 | 2018-06-06 | 2018-06-29 | 2018-11-16 | [6 empty] | 2021-12-03
448 | 11 | 1283 | IMP | VAR | IMPERIAL CULVERT REPLACEMENT | IN IMPERIAL COUNTY AT VARIOIUS LOCATIONS.. CULVERT REPLACEMENT. CULVERT REPLACEMENT. | 3381 | 394 | 394 | 780 | 780 | 0 | 0 | 391 | 391 | 18 | 0 | 1816 | 1816 | 0 | 367 | 367 | 367 | 419 | 419 | 556 | 0 | 0 | 0 | 0 | 0 | 165 | 17 | 0 | 0 | 0 | 0 | 1816 | [6 empty] | 2018-09-05 | 2019-03-12 | 2019-06-20 | [6 empty] | 2019-11-21 | 2020-07-10
449 | 11 | 1302 | SD | 52 | SD-52 DIPS PAVEMENT REHAB | In San Diego, from 0.4 mile west of Convoy Street Overcrossing to Santo Road Overcrossing. Roadway rehabilitation to mitigate highway settlement, construct auxiliary lane, transportation management systems, lighting, and roadside safety improvements. | 44970 | 2066 | 2066 | 3452 | 3452 | 45 | 45 | 5654 | 5654 | 15 | 15 | 33738 | 33738 | 0 | 56 | 56 | 2061 | 0 | 0 | 3154 | 0 | 0 | 40 | 0 | 0 | 5485 | 0 | 0 | 0 | 0 | 0 | 33738 | 2020-07-10 | 2021-11-29 | 2022-03-18 | 2022-07-29 | [8 empty] | 2020-07-10 | 2021-11-29 | 2022-03-18 | 2022-07-29 | 2025-03-28
450 | 11 | 1310 | SD | 125 | SD-125 (SD-54 TO SD-94) | In and near Lemon Grove, from 0.1 mile north of Jamacha Boulevard Overcrossing to Route 94. Pavement rehabilitation. | 72449 | 3071 | 3071 | 5557 | 5557 | 317 | 317 | 9027 | 9027 | 120 | 120 | 54357 | 54357 | 0 | 574 | 574 | 3151 | 0 | 0 | 5153 | 0 | 0 | 311 | 0 | 0 | 7099 | 0 | 0 | 0 | 0 | 0 | 37300 | 2020-07-10 | 2021-11-29 | 2022-02-18 | 2022-07-18 | [8 empty] | 2020-07-10 | 2021-11-29 | 2022-02-18 | 2022-07-18 | 2025-07-09
451 | 11 | 1329 | IMP | 8 | IMP BRIDGE STRUCTURE REHAB | In Imperial County, on Routes 8 and 78 at various locations. Rehabilitation of six bridges, including painting, deck and column work. | 15000 | 200 | 200 | 800 | 800 | 0 | 0 | 1700 | 1700 | 0 | 0 | 12300 | 12300 | 0 | 164 | 164 | 433 | 0 | 0 | 856 | 0 | 0 | 0 | 0 | 0 | 2047 | 0 | 0 | 200 | 0 | 0 | 0 | 2019-10-01 |  | 2021-10-01 | 2022-01-01 | [8 empty] | 2020-03-03 | 2021-08-13 | 2021-11-30 | 2022-03-17 | 2023-10-19
452 | 11 | 1332 | SD | 8 | SD-008-R25.1/R40.1 - REHABILITATE CULVERTS. | In San Diego County, from 0.6 mile west of Harbison Canyon Undercrossing to 0.4 mile east of Horsethief Road Undercrossing. Rehabilitate culverts. | 7987 | 262 | 262 | 1100 | 1100 | 200 | 200 | 1200 | 1200 | 25 | 25 | 5200 | 5200 | 0 | 262 | 262 | 262 | 579 | 579 | 1248 | 15 | 15 | 202 | 0 | 0 | 1064 | 15 | 15 | 25 | 0 | 0 | 5200 | [6 empty] | 2018-06-29 | 2019-05-13 | 2019-06-14 | [6 empty] | 2019-12-02 | 2021-05-31
453 | 11 | 1336 | IMP | 8 | 11-IMP-008-BRIDGE PRESERVATION | Near Winterhaven, at Colorado River Viaduct Bridge No. 58-0312L/R. Patch spalls, polyester deck overlay, hinge bearing replacement, and joint replacement to preserve the structural integrity of two bridges. | 5341 | 193 | 193 | 506 | 506 | 0 | 0 | 479 | 479 | 0 | 0 | 4163 | 4163 | 0 | 76 | 76 | 198 | 0 | 0 | 470 | 0 | 0 | 0 | 0 | 0 | 480 | 0 | 0 | 0 | 0 | 0 | 4163 | 2019-07-05 | 2020-12-28 | 2021-02-26 | 2021-06-22 | [8 empty] | 2020-01-20 | 2020-12-28 | 2021-02-09 | 2021-12-15 | 2023-01-13
454 | 11 | 1339 | SD | 8 | I-8 EL CAJON BRIDGE REHAB | In and near El Cajon, from Grossmont Boulevard to Mollison Avenue at various locations. Rehabilitate three bridge decks. | 27130 | 390 | 390 | 1974 | 1974 | 0 | 0 | 4031 | 4031 | 0 | 0 | 20735 | 20735 | 0 | 93 | 93 | 559 | 0 | 0 | 1728 | 0 | 0 | 0 | 0 | 0 | 3540 | 0 | 0 | 0 | 0 | 0 | 20734620 | 2019-10-31 | 2021-04-20 | 2021-08-03 | 2021-11-18 | [8 empty] | 2020-05-20 | 2021-10-19 | 2021-11-19 | 2022-03-17 | 2023-10-19
455 | 11 | 1342 | IMP | 98 | 11-IMP-98 COLD-IN-PLACE RECYCLE | Near Calexico, from Route 7 to 0.1 mile west of East Highline Canal Bridge. Rehabilitate roadway. | 9553 | 0 | 0 | 780 | 780 | 0 | 0 | 718 | 718 | 0 | 0 | 8055 | 8055 | 0 | 0 | 0 | 0 | 0 | 0 | 255 | 0 | 0 | 0 | 0 | 0 | 470 | 0 | 0 | 0 | 0 | 0 | 8055 | [6 empty] | 2019-05-06 | 2019-05-24 | [6 empty] | 2019-08-15 | 2020-01-23 | 2020-10-16
456 | 11 | 1344 | SD | 67 | 11-SD-67 RHMA OVERLAY w/SAMI | Near Lakeside and Ramona, from 0.2 mile north of San Diego River Bridge to Route 78. Rehabilitate asphalt pavement, drainage system restoration, curb ramp upgrades, guardrail upgrades, and enhance crosswalk visibility. | 35583 | 807 | 807 | 2690 | 2690 | 85 | 85 | 5110 | 5110 | 0 | 0 | 26891 | 26891 | 0 | 53 | 53 | 852 | 0 | 0 | 2765 | 0 | 0 | 82 | 0 | 0 | 5567 | 0 | 0 | 239 | 0 | 0 | 26891 | 2019-12-13 | 2020-05-05 | 2021-06-30 | 2021-10-02 | [8 empty] | 2019-12-13 | 2020-05-05 | 2020-07-10 | 2020-10-02 | 2021-09-24
457 | 11 | 1350 | SD | 15 | I-15 CONCRETE LANE REPLACEMENT | In and near Escondido, from 0.2 mile south of Route 78 to 0.5 mile north of Deer Springs Road. Rehabilitate pavement by replacing sections of the existing pavement and the outside shoulder with Continuously reinforced Concrete Pavement (CRCP), pavement slab replacement, bridge approach slab replacement, bridge joint seal work, and sign panel replacement. | 74860 | 2749 | 2749 | 5497 | 5497 | 200 | 200 | 10994 | 10994 | 0 | 0 | 55420 | 55420 | 0 | 512 | 512 | 2549 | 0 | 0 | 4969 | 0 | 0 | 176 | 0 | 0 | 8676 | 0 | 0 | 0 | 0 | 0 | 55419 | 2019-07-26 | 2021-01-08 | 2021-04-26 | 2022-06-23 | [8 empty] | 2019-10-01 | 2021-01-08 | 2021-04-26 | 2022-03-18 | 2025-01-03
458 | 12 | 1203 | ORA | Var | 12-0Q690 detection system rehab. | At various locations, on various routes. Replace and upgrade existing field elements for the Traffic Management System (TMS). | 10414 | 0 | 0 | 2060 | 2060 | 0 | 0 | 1800 | 1800 | 24 | 24 | 6530 | 6530 | 0 | 0 | 0 | 0 | 855 | 855 | 1770 | 0 | 0 | 0 | 0 | 0 | 1824 | 0 | 0 | 24 | 0 | 0 | 6530 | 2017-06-22 | 2020-02-01 | 2020-05-01 | 2021-01-01 |  |  | 2017-06-22 | [6 empty] | 2020-02-01 | 2020-03-15 | 2020-12-15 | 2022-07-01
459 | 12 | 1204 | ORA | Var | 12-0Q930 Bridge Project on Route 5 and 133 | In Orange County, on Routes 5, 133, and 241 at various locations. Rehabilitate 25 bridges. | 22197 | 1215 | 1215 | 2500 | 2500 | 155 | 155 | 3720 | 3720 | 58 | 58 | 14549 | 14549 | 0 | 450 | 450 | 1186 | 0 | 0 | 2495 | 0 | 0 | 155 | 0 | 0 | 3723 | 0 | 0 | 53 | 0 | 0 | 2753 | 2020-01-07 | 2021-08-02 | 2021-10-01 | 2022-05-02 | [8 empty] | 2020-03-02 | 2021-08-01 | 2021-10-01 | 2022-05-02 | 2023-11-01
460 | 12 | 2246 | ORA | 1 | 12-0H150 PCH Laguna Beach Rehabilitate Pavement & ADA upgrades | In Laguna Beach and Newport Beach, from 1,000 feet south of Vista Del Sol to Moss Street; also from Ledroit Street to Newport Coast Drive (PM 10.5/14.1). Remove and replace existing pavement with Rubberized Hot Mix Asphalt (RHMA). | 12076 | 0 | 0 | 3200 | 3200 | 1 | 1 | 1739 | 1739 | 65 | 65 | 7071 | 7071 | 0 | 0 | 0 | 0 | 1366 | 1366 | 3480 | 0 | 0 | 0 | 0 | 0 | 1670 | 0 | 0 | 65 | 0 | 0 | 6507 | 2005-08-30 | 2020-05-01 | 2020-06-01 | 2021-01-04 |  |  | 2005-08-30 | [6 empty] | 2020-02-28 | 2020-03-02 | 2020-09-08 | 2021-12-08
461 | 12 | 2246B | ORA | 1 | 12-0H153 CAPM Combined with ADA EA 0M820 | In Laguna Beach, from south of Ruby Street to Ledroit Street. Remove and replace pavment with Rubberized Hot Mix Asphalt (RHMA). | 4305 | 0 | 0 | 0 | 0 | 0 | 0 | 832 | 832 | 0 | 0 | 3473 | 3473 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3024 | 2018-01-31 | 2020-02-01 | 2020-03-01 | 2020-09-01 | [9 empty] | 2020-06-01 | 2020-06-01 | 2021-01-02
462 | 12 | 2293 | ORA | 1 | 12-0M990 PCH/Broadway Culvert Bridge | In Laguna Beach, at Route 133 (Broadway Street). Replace bridge. | 7176 | 490 | 490 | 925 | 925 | 790 | 790 | 600 | 600 | 800 | 800 | 3571 | 3571 | 0 | 473 | 473 | 484 | 369 | 369 | 928 | 91 | 91 | 714 | 0 | 0 | 604 | 0 | 0 | 684 | 0 | 0 | 3639 | 2018-06-01 | 2019-09-12 | 2019-09-12 | 2019-11-19 | [8 empty] | 2019-09-01 | 2019-12-01 | 2019-12-01 | 2020-05-08 | 2020-12-01
463 | 12 | 2330 | ORA | 1 | 12-0P680 Upgrade Traffic Signal | In the cities of Newport Beach, Huntington Beach and Seal Beach, from Crystal Heights Drive to First Street. Replace traffic signals, upgrade non-standard curb ramps to meet Americans with Disabilities Act (ADA) Standards and modify drainage. | 24877 | 1891 | 1891 | 4299 | 4299 | 1480 | 1480 | 3537 | 3537 | 745 | 745 | 12925 | 12925 | 0 | 1487 | 1487 | 1487 | 72 | 72 | 4545 | 0 | 0 | 1019 | 0 | 0 | 2177 | 13 | 13 | 745 | 0 | 0 | 12925 | 2019-01-05 | 2021-05-15 | 2021-05-30 | 2022-01-30 |  | 2018-12-06 | 2019-02-01 | [6 empty] | 2021-05-15 | 2021-05-30 | 2022-01-30 | 2023-04-30
464 | 12 | 2374 | ORA | 1 | 12-0R410 PCH at Newport Beach CAPM w ADA & FO | In Newport Beach, from Jamboree Road to Santa Ana River Bridge. Pavement rehabilitation. | 19335 | 1980 | 1980 | 2660 | 2660 | 1520 | 1520 | 2438 | 2438 | 132 | 132 | 10605 | 10605 | 0 | 554 | 554 | 2027 | 0 | 0 | 3008 | 0 | 0 | 1382 | 0 | 0 | 2759 | 0 | 0 | 132 | 0 | 0 | 10605 | 2019-10-01 | 2021-11-01 | 2021-11-01 | 2022-05-01 | [8 empty] | 2019-10-01 | 2021-11-30 | 2021-11-30 | 2022-05-26 | 2023-10-25
465 | 12 | 2403A | ORA | 1 | 12-0N930 PCH Clean and Rehab RCB | In Newport Beach, from 0.1 mile north of Superior Avenue to 60th Street. Rehabilitate drainage system. | 2471 | 300 | 300 | 600 | 600 | 0 | 0 | 400 | 400 | 10 | 10 | 1161 | 1161 | 0 | 300 | 300 | 300 | 471 | 471 | 882 | 0 | 0 | 0 | 0 | 0 | 447 | 0 | 0 | 0 | 0 | 0 | 1095 | 2017-10-20 | 2019-02-01 | 2019-04-02 | 2019-11-06 |  |  | 2017-10-20 | 2019-01-30 | 2019-04-03 | [6 empty] | 2019-11-06 | 2020-08-15
466 | 12 | 2499A | ORA | 1 | 12-0P590 Resurface 14.9 lane miles | In Huntington Beach, from Warner Avenue to Los Angeles County line. Upgrade Americans with Disabilities Act (ADA) curb ramps, cold plane pavement, and place Rubberized Hot Mix Asphalt (RHMA) pavement. | 20799 | 1720 | 1720 | 2932 | 2932 | 1482 | 1482 | 2358 | 2358 | 503 | 503 | 11804 | 11804 | 0 | 1281 | 1281 | 1281 | 76 | 76 | 2871 | 40 | 40 | 956 | 0 | 0 | 2013 | 12 | 12 | 503 | 0 | 0 | 8770 | 2019-01-05 | 2021-05-15 | 2021-05-30 | 2022-01-30 |  |  | 2019-02-01 | [6 empty] | 2021-05-15 | 2021-05-30 | 2022-01-30 | 2023-04-30
467 | 12 | 2530N | ORA | 5 | 12-0R200 Interstate 5 Pavement Rehabilitation Project | In San Clemente, from the San Diego County line to El Camino Real. Pavement rehabilitation and upgrade safety devices. | 34051 | 2569 | 2569 | 3824 | 3824 | 0 | 0 | 3849 | 3849 | 0 | 0 | 23809 | 23809 | 0 | 492 | 492 | 1980 | 0 | 0 | 3822 | 0 | 0 | 0 | 0 | 0 | 3849 | 0 | 0 | 0 | 0 | 0 | 22850 | 2019-12-02 | 2021-06-01 | 2021-07-01 | 2022-04-01 | [8 empty] | 2019-12-02 | 2021-06-01 | 2021-07-01 | 2022-04-01 | 2024-04-01
468 | 12 | 2563 | ORA | 5 | 12-0P700 Rt 5, Drainage restoration Segunda Deshecha Channel | In San Clemente, adjacent to northbound Avenida Pico offramp. Restore hydraulic capacity of channel by repairing concrete panels in channel slope and bottom. | 10915 | 550 | 550 | 1145 | 1145 | 111 | 111 | 1386 | 1386 | 123 | 123 | 7600 | 7600 | 0 | 498 | 498 | 498 | 17 | 17 | 1133 | 3 | 3 | 109 | 0 | 0 | 1079 | 2 | 2 | 125 | 0 | 0 | 4303 | 2019-03-01 | 2020-05-01 | 2020-06-01 | 2020-12-11 |  |  | 2019-03-01 | [6 empty] | 2020-03-15 | 2020-03-31 | 2020-12-01 | 2023-02-01
469 | 12 | 2859B | ORA | VAR | 12-0P42U I-5, SR57, & SR 91 ICM123 Project combined with ICM 1,2, & 3 | Install & modify ITS elements. Install & modify ITS elements Install & modify ITS elements | 27527 | 0 | 0 | 2400 | 2400 | 0 | 0 | 3045 | 3045 | 9 | 9 | 22073 | 22073 | 0 | 1621 | 1621 | 1621 | 641 | 641 | 2393 | 0 | 0 | 0 | 0 | 0 | 3115 | 0 | 0 | 9 | 0 | 0 | 22073 | 2018-06-19 | 2020-03-18 | 2020-05-01 | 2021-01-04 |  | 2018-10-17 | 2018-06-19 | [6 empty] | 2020-04-01 | 2020-05-01 | 2021-03-04 | 2023-02-01
470 | 12 | 2859D | ORA | 5 | Integrated Corridor Mgmt on 3 State Route | In Orange County, on Routes 5, 22, 55, 57, 91, and 405 at various locations. Install Transportation Management System (TMS) field elements to support the Orange County Triangle (Routes 5, 57, and 91) Integrated Corridor Management (ICM). | 9436 | 0 | 0 | 0 | 0 | 320 | 320 | 1670 | 1670 | 15 | 15 | 7431 | 7431 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7446
471 | 12 | 2895C | ORA | 5 | Integrated Corridor Mgmt on 3 State Route | In Orange County, on Routes 5, 22, 55, 57, 91, and 405 at various locations. Develop Information Technology (IT) and Information Exchange Network (IEN) to support the Orange County Triangle (Routes 5, 57, and 91) Integrated Corridor Management (ICM). | 18921 | 2380 | 2380 | 4343 | 4343 | 320 | 320 | 2990 | 2990 | 0 | 0 | 8888 | 8888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8888
472 | 12 | 2948 | ORA | 22 | 12-0N920 WB Rte 22 Haster Off - Upgrade Drainage | In Garden Grove, at Haster Street westbound offramp. Upgrade drainage system. | 3614 | 420 | 420 | 720 | 720 | 233 | 233 | 556 | 556 | 326 | 326 | 1359 | 1359 | 0 | 405 | 405 | 405 | 652 | 652 | 692 | 31 | 31 | 200 | 0 | 0 | 573 | 4 | 4 | 326 | 0 | 0 | 1149 | 2017-08-01 | 2019-04-01 | 2019-05-01 | 2020-01-02 |  |  | 2017-08-01 | 2019-03-28 | 2019-04-29 | [6 empty] | 2020-01-02 | 2021-07-01
473 | 12 | 3230A | ORA | 39 | 12-0F970 SR-39 Drainage and ADA | In Buena Park, from Auto Center Drive to Craig Avenue. Rehabilitate drainage systems, install new inlets, Reinforced Concrete Pipes (RCP) and replace flood damaged sections of curb and gutters. | 4569 | 0 | 0 | 870 | 870 | 153 | 153 | 906 | 906 | 414 | 414 | 2226 | 2226 | 0 | 71 | 71 | 71 | 688 | 688 | 903 | 30 | 30 | 159 | 0 | 0 | 995 | 11 | 11 | 34 | 0 | 0 | 2226 | 2017-06-26 | 2019-11-01 | 2019-11-15 | 2020-07-15 |  |  | 2017-06-26 | [6 empty] | 2019-11-01 | 2019-11-15 | 2020-07-15 | 2022-10-01
474 | 12 | 3450A | ORA | Var | 12-0Q390 Bridge Seismic Restoration | In Costa Mesa, at the Route 55/73 Connector Overcrossing Bridge No. 55-538F (PM 4.74), Route 91 Carmenita Road Pedestrian Overcrossing Bridge No. 55-0473 (PM 0.02) and Route 405 Laguna Canyon Road Overcrossing Bridge No. 55-0247 (PM 2.20). Seismic restoration. | 24175 | 1048 | 1048 | 2279 | 2279 | 11 | 11 | 5381 | 5381 | 0 | 0 | 15456 | 15456 | 0 | 343 | 343 | 1011 | 0 | 0 | 2592 | 0 | 0 | 0 | 0 | 0 | 5054 | 0 | 0 | 0 | 0 | 0 | 15456 | 2019-09-25 | 2021-01-15 | 2021-02-02 | 2021-09-09 | [8 empty] | 2020-04-15 | 2021-03-15 | 2021-05-28 | 2021-12-30 | 2023-10-02
475 | 12 | 3458A | ORA | 55 | 12-0Q660_ SB 55 to SB 405 connector, Replace Slab | In Costa Mesa and Santa Ana, at the southbound Route 55 connector to southbound Route 405. Correct vertical pavement profile, replace existing concrete pavement, build bridge structural departure slabs, and construct overhead sign structure. | 3938 | 90 | 90 | 880 | 880 | 0 | 0 | 700 | 700 | 0 | 0 | 2268 | 2268 | 0 | 282 | 282 | 282 | 658 | 658 | 801 | 0 | 0 | 0 | 0 | 0 | 749 | 0 | 0 | 0 | 0 | 0 | 2268 | 2017-12-28 | 2019-05-01 | 2019-07-01 | 2020-01-01 |  |  | 2017-12-28 | 2019-03-12 | 2019-04-30 | [6 empty] | 2019-09-09 | 2020-11-02
476 | 12 | 3959 | ORA | Var | 12-0R560 VAR Connector Rehab project. | In the cities of Santa Ana, Tustin, Irvine, Newport Beach, Costa Mesa, and Anaheim on various routes. Rehabilitate pavement by repairing broken concrete slabs and replacing asphalt concrete with Rubberized Hot Mix Asphalt (RHMA-G) at 17 connectors, one ramp and one overcrossing. | 40400 | 3000 | 3000 | 5400 | 5400 | 0 | 0 | 5500 | 5500 | 0 | 0 | 26500 | 26500 | 0 | 59 | 59 | 2891 | 0 | 0 | 5403 | 0 | 0 | 0 | 0 | 0 | 5393 | 0 | 0 | 0 | 0 | 0 | 26447 | 2020-08-01 | 2022-04-01 | 2022-05-01 | 2022-11-01 | [8 empty] | 2020-08-01 | 2022-04-01 | 2022-05-02 | 2022-11-03 | 2025-09-01
477 | 12 | 4080 | ORA | 73 | 12-0R340 RT 73 bridge decks and rehab approach slabs | In Laguna Hills, Laguna Niguel, Aliso Viejo, Laguna Beach, Irvine, Newport Beach, and Costa Mesa from Moulton Parkway to Bristol Street. Rehabilitate bridge decks, bridge joints and approach slabs to preserve service life on ten bridges. | 5894 | 494 | 494 | 1294 | 1294 | 0 | 0 | 1007 | 1007 | 5 | 5 | 3094 | 3094 | 0 | 1 | 1 | 502 | 0 | 0 | 1344 | 0 | 0 | 0 | 0 | 0 | 1080 | 0 | 0 | 0 | 0 | 0 | 3094 | 2020-04-02 | 2021-07-01 | 2021-08-02 | 2022-03-02 | [8 empty] | 2020-04-02 | 2021-07-02 | 2021-08-02 | 2022-06-01 | 2023-03-01
478 | 12 | 4337 | ORA | 90 | 12-0P580 Rte 90 CAPM | In and near Brea, from Harbor Boulevard to Randolph Avenue. Cold plane pavement and place Rubberized Hot Mix Asphalt (RHMA) pavement. | 12357 | 478 | 478 | 1249 | 1249 | 153 | 153 | 2269 | 2269 | 0 | 0 | 8208 | 8208 | 0 | 461 | 461 | 461 | 107 | 107 | 1286 | 1 | 1 | 137 | 0 | 0 | 2013 | 0 | 0 | 0 | 0 | 0 | 8208 | 2018-11-01 | 2019-12-03 | 2020-01-30 | 2020-09-01 |  |  | 2018-10-30 | [6 empty] | 2019-12-03 | 2020-01-30 | 2020-09-01 | 2022-09-30
479 | 12 | 4609B | ORA | 91 | 12- 0N320 Rte 91 Pvmt Rehab, Rte55 to Riv CL | In the city of Anaheim, from west of Lakeview Avenue to Orange/Riverside County line. Pavement rehabilitation. | 15305 | 0 | 0 | 1845 | 1845 | 0 | 0 | 2450 | 2450 | 10 | 10 | 11000 | 11000 | 0 | 0 | 0 | 0 | 1362 | 1362 | 1891 | 0 | 0 | 0 | 0 | 0 | 2605 | 0 | 0 | 0 | 0 | 0 | 11000 | 2015-06-03 | 2019-03-01 | 2019-04-01 | 2019-09-01 |  |  | 2015-06-03 | 2019-04-02 | 2019-06-17 | [6 empty] | 2020-02-15 | 2021-02-01
480 | 12 | 4792 | ORA | 133 | 12-0Q360 Drainage System Restoration | In Orange County, from 0.3 mile south of El Toro Road to 0.2 mile north of Route 73/133 Interchange. Construct detention basin, reconstruct channel, extend reinforced concrete box and regrade to prevent adverse flow. | 7698 | 0 | 0 | 2037 | 2037 | 911 | 911 | 1188 | 1188 | 1467 | 1467 | 2095 | 2095 | 0 | 0 | 0 | 0 | 0 | 0 | 1445 | 0 | 0 | 684 | 0 | 0 | 1103 | 0 | 0 | 435 | 0 | 0 | 2095 | 2018-10-02 | 2020-04-17 | 2020-06-15 | 2021-01-05 |  |  | 2018-10-02 | [6 empty] | 2020-05-01 | 2020-06-01 | 2020-12-01 | 2023-08-08
481 | 12 | 5502 | ORA | 241 | 12-0H047 SR 241, Capital Preventive Maintenance Project | In and near the cities of Anaheim, Irvine, and Orange, from Portola Parkway to Route 91. Pavement rehabilitation. | 23700 | 0 | 0 | 3205 | 3205 | 0 | 0 | 3668 | 3668 | 0 | 0 | 16827 | 16827 | 0 | 0 | 0 | 0 | 197 | 197 | 3110 | 0 | 0 | 0 | 0 | 0 | 3269 | 0 | 0 | 0 | 0 | 0 | 16827 | 2018-08-13 | 2021-02-26 | 2021-04-01 | 2021-11-30 |  | 2018-12-06 | 2018-08-13 | [6 empty] | 2021-02-15 | 2021-03-01 | 2021-11-30 | 2023-07-15