STEPS TO DELIVERING A LOCAL CARBON REDUCTION PROGRAM (CRP) PROJECT

The Local Agency will need to do the following to obligate their CRP funds:

- Submittal of Project Alignment Confirmation (PAC) Form to determine if Project is aligned with the Carbon Reduction Strategy (CRS) and that proposed funding/schedule is approved:

  - Local Partner submits online form at PAC Form Submittal Form.

  - Local Partner obtains Local Agency and MPO/RTPA signatures on PAC Form .PDF (PDF) that is automatically generated from the online form.

  - Local Partner emails signed PDF to carbon.reduction@dot.ca.gov.

  - Caltrans HQ Sustainability Office (Sustainability) reviews PDF for project alignment with the CRS.  If approved, Sustainability signs PDF and sends it to Caltrans Division of Local Assistance (DLA) for their review and approval.

  - DLA reviews proposed project funding and schedule.  If approved, DLA signs PDF and sends copy to MPO/RTPA, Caltrans DLAE, and Sustainability.

  - MPO or Rural RTPA notifies and sends copy of completed PDF to the Local Agency.

- The remainder steps follow the Federal Aid process (see Local Assistance Procedures Manual [LAPM] or ask District Local Assistance Engineer [DLAE]).

In general, these steps include, but may not be limited to, the following:

  - Local Agency works with MPO or Rural RTPA to program the project into FSTIP (Don’t forget this important step).

  - Local Agency submits Requests for Authorization (RFA) for PE

    - Local Agency receives E76 authorization for phase and begins reimbursable (authorized) work.

    - Local Agency invoices DLAE for CRP reimbursable work performed at a minimum of once every 6 months.

    - Local Agency completes NEPA prior to beginning final design, CON, or RW

  - Local Agency submits Requests for Authorization for RW

    - Local Agency receives E76 RW authorization for RW.

    - Local Agency completes RW Certification prior to beginning CON.

  - Local Agency submits Requests for Authorization for CON

    - Local Agency receives E76 RW authorization for CON.

    - Local Agency completes project.

  - Local Agency submits Final Report of Expenditures and Final Invoice

Note: The Local Agency should contact their DLAE for more guidance on the regular federal aid process each of their projects including the procedure for obligating and use of other state or federal funds awarded to the project.  For DLAE questions on the federal aid process, the District may contact their assigned Area Engineer in Office of Project Management Oversight (OPMO).